## Summary
No | Description | Qty | Unit | Rate | Amount | Previous Qty | This Month Qty | Cumulative Qty | Previous Amount | This Month Amount | Cumulative Amount | Column1
PART 1 - GENERAL ITEMS
Contractual requirements
A | Performance security | 1 | sum | 7100 | 7100 | 1 | 0 | 1 | 7100 | 0 | 7100
B | Insurance of the works | 1 | sum | 0 | 0 |  | 0 |  | 0 | 0 | 0
C | Third party insurance | 1 | sum | 3900 | 3900 | 1 | 0 | 1 | 3900 | 0 | 3900
D | Workmen's compensation insurance | 1 | sum | 0 | 0 |  | 0 |  | 0 | 0 | 0
E | Engineer's facilities | 1 | sum | 0 | 0 |  | 0 |  | 0 | 0 | 0
F | Contractor Facilities | 1 | sum | 0 | 0 |  | 0 |  | 0 | 0 | 0
G | Lighting, power and water for the Works | 1 | sum | 0 | 0 |  | 0 |  | 0 | 0 | 0
H | Security, safety of site,welfare & Transport of people | 1 | sum | 20000 | 20000 | 0.1 | 0.1 | 0.2 | 2000 | 2000 | 4000
J | Testing of works and materials | 1 | sum | 6250 | 6250 |  | 0.3 | 0.3 | 0 | 1875 | 1875
K | Temporary Works - Safety Arrangement & Traffic Management | 1 | sum | 70000 | 70000 | 0.1 | 0.2 | 0.3 | 7000 | 14000 | 21000
L | Allow for coordination with Service Authorities and provide all necessary facilities as required | 1 | sum | 19500 | 19500 | 0.5 | 0.1 | 0.6 | 9750 | 1950 | 11700
M | Project Sign Board | 1 | sum | 7500 | 7500 |  | 0 |  | 0 | 0 | 0
N | Miscellaneous Item | 1 | sum | 0 | 0 |  | 0 |  | 0 | 0 | 0
Additional Items
The tenderer to list with in this bill section, any additional items with quantities (enumerated or itemized) and rates which are not measured elsewhere in the section but required to complete the WORKS as per CONTRACT.
| Supervision & Labour | 2 | Month | 85000 | 170000 | 0.5 | 0.25 | 0.75 | 42500 | 21250 | 63750
| Plant & Equiment | 1 | sum | 9000 | 9000 | 0.1 | 0.4 | 0.5 | 900 | 3600 | 4500
| Monthly Report | 1 | sum | 1250 | 1250 |  | 0 |  | 0 | 0 | 0
PART 2 - GROUND INVESTIGATION
Trial pits and trenches
A | The contractor shall allow for any trial pits and trial trenches as required to recognize and expose existing services in accordance with specification and engineer's instruction. | 1 | item | 11000 | 11000 | 1 | 0 | 1 | 11000 | 0 | 11000
Additional Items
The tenderer to list with in this bill section, any additional items with quantities (enumerated or itemized) and rates which are not measured elsewhere in the section but required to complete the WORKS as per CONTRACT.
PART 3 - DEMOLITION & SITE CLEARANCE
A | General site clearance | 0.2 | ha | 2169 | 433.8 |  | 0 |  |  | 0 | 0
B | Break-out and remove existing kerb including base and backing, cart away to approved tip as directed by the Engineer. | 50 | m | 39.98 | 1999 |  | 43.1 | 43.1 |  | 1723.138 | 1723.138
C | Break-out and remove existing 60/80 mm thick interlocking block paving and cart to tip, including bed and under layer, as directed by the Engineer. | 100 | m2 | 65 | 6500 |  | 110.646 | 110.646 |  | 7191.99 | 7191.99
Additional Items
The tenderer to list with in this bill section, any additional items with quantities (enumerated or itemized) and rates which are not measured elsewhere in the section but required to complete the WORKS as per CONTRACT.
PART 4 - EARTHWORKS
General excavation
A | Excavation for cuttings; material other than top soil, rock or artificial hard material | 280 | m3 | 48 | 13440 |  | 0 |  |  | 0 | 0
Excavation ancillaries
B | Preparation of excavated surface; Material other than top soil, rock or artificial hard material | 1030 | m2 | 8 | 8240 |  | 0 |  |  | 0 | 0
C | Disposal of excavated material, material other than top soil, rock or artificial hard material | 280 | m3 | 77.5 | 21700 |  | 0 |  |  | 0 | 0
Additional Items
The tenderer to list with in this bill section, any additional items with quantities (enumerated or itemized) and rates which are not measured elsewhere in the section but required to complete the WORKS as per CONTRACT.
PART 5 - ROADS AND PAVINGS
Kerbs, channels and edging
Kerbs and edging including excavation, back filling,
Concrete bed and backing as per detail drawing
A | Precast concrete up stand kerbs; Straight or curve to radius exceeding 12m; (150 x 305mm) | 200 | m | 110 | 22000 |  | 0 |  |  | 0 | 0
B | Precast concrete flush kerb 150 x 210mm | 120 | m | 90 | 10800 |  | 0 |  |  | 0 | 0
C | Precast concrete heel kerb 75 x 150mm | 160 | m | 45 | 7200 |  | 0 |  |  | 0 | 0
D | Precast concrete dropped kerb 300 x 150 mm | 15 | m | 91 | 1365 |  | 0 |  |  | 0 | 0
E | Precast concrete up stand kerbs; curved to radius not exceeding 12m; (150 x 305mm) | 20 | m | 114.45 | 2289 |  | 0 |  |  | 0 | 0
Light Duty Pavements
F | Aggregate Sub base, depth 150mm; CBR ≥ 30% | 650 | m2 | 32 | 20800 |  | 0 |  |  | 0 | 0
G | Aggregate Sub base, depth 200mm; CBR ≥ 30% | 380 | m2 | 38 | 14440 |  | 0 |  |  | 0 | 0
H | Aggregate Road base, depth 200mm; CBR ≥ 80% | 380 | m2 | 40 | 15200 |  | 0 |  |  | 0 | 0
Precast concrete interlocking block paving; Including crushed sand bed; the colour and patterns of the paving blocks as specified by the Engineer
J | Precast concrete interlocking block 60 mm thick including 40mm thick crushed sand bed (Pedestrian Path) | 650 | m2 | 62 | 40300 |  | 0 |  |  | 0 | 0
K | Precast concrete interlocking block 80 mm thick including 50mm thick crushed sand bed (Vehicular Path) | 380 | m2 | 65 | 24700 |  | 0 |  |  | 0 | 0
L | Fill in 40-50mm gap between existing road and new kerb with concrete and AC wearing course including saw cutting, removal of asphalt pavement, tack coat etc. complete. | 115 | m | 125 | 14375 |  | 0 |  |  | 0 | 0
Ancillaries - Traffic signs
Traffic signs
A | Octagonal sign panel; size H=600mm on 2.1m high post Sign Type (301) | 1 | nr | 800 | 800 |  | 0 |  |  | 0 | 0
B | Triangular sign panel; dia.750mm on 2.1m high post Sign Type (302) | 5 | nr | 800 | 4000 |  | 0 |  |  | 0 | 0
C | Rectangular sign panel; size 350x 600mm on 2.1m high post Sign Type (453.1) | 1 | nr | 800 | 800 |  | 0 |  |  | 0 | 0
Non-illuminated warning and regulatory signs fixed on sharing posts (post measured elsewhere) as per the RTA Traffic Control Devices Manual.
D | Rectangular sign panel | 6 | nr | 563 | 3378 |  | 0 |  |  | 0 | 0
Ancillaries - Surface marking
Surface marking
Thermo plastic road marking as per the RTA Traffic Control Devices Manual.
E | Straight arrow signs; reference type 614.1 | 1 | nr | 163 | 163 |  | 0 |  |  | 0 | 0
F | Right turn arrow signs; refer. types 614.2 / 614.3 | 1 | nr | 188 | 188 |  | 0 |  |  | 0 | 0
G | White continuous lines;300 mm wide; type 601 | 15 | m | 19 | 285 |  | 0 |  |  | 0 | 0
H | White intermittent lines; 300 mm wide; type 602 | 10 | m | 19 | 190 |  | 0 |  |  | 0 | 0
J | Pedestrial crossing; 500mm wide; type 603 | 30 | m | 19 | 570 |  | 0 |  |  | 0 | 0
K | Sand blast and remove existing road marking complete as directed by the Engineer | 10 | m2 | 75 | 750 |  | 0 |  |  | 0 | 0
Painting
L | Chlorinated rubber based quick drying paint (black | 60 | m2 | 30 | 1800 |  | 0 |  |  | 0 | 0
and white) applied in two coats to exposed faces of
concrete up stand kerbs
Additional Items
The tenderer to list with in this bill section, any additional items with quantities (enumerated or itemized) and rates which are not measured elsewhere in the section but required to complete the WORKS as per CONTRACT.
PART 6 - ETISALAT WORKS
MISCELLANEOUS WORK
Protection
Protection of existing Etisalat duct, including excavate to exposing the existing Etisalat duct, and backfilling as per the Engineer approval
Cast in situ plain Concrete Class 25/20 around the existing Etisalat duct
A | Existing duct | 35 | m | 300 | 10500 |  | 0 |  |  | 0 | 0
Additional Items
The tenderer to list with in this bill section, any additional items with quantities (enumerated or itemized) and rates which are not measured elsewhere in the section but required to complete the WORKS as per CONTRACT.
1 | Relocation of JRC Manhole | 1 | nr | 0 | 0 |  | 0 |  |  | 0 | 0
PART 7 - ETIC-DU WORKS
Notes:
Du will provide all ducts, spacers and furniture for manholes and joint boxes, the tenderer shall include in his rate for collection and storage of these materials from Du stores in Dubai
Contractor is reminded to exercise extreme caution when working near Fiber Optic and Coaxial Cable Routes
MISCELLANEOUS WORK
Demolish existing redundant reinforced concrete joint box and manhole and cart to tip; including backfilling and compaction with suitable material
A | JRC | 1 | nr | 1396 | 1396 |  | 0 |  |  | 0 | 0
PIPEWORK - MANHOLES & PIPEWORK
ANCILLARIES
Manholes
Reinforced concrete joint boxes complete in accordance with Specifications and Drawings.
B | Type JRC | 1 | nr | 6875 | 6875 |  | 0 |  |  | 0 | 0
PIPE WORK - SUPPORTS AND PROTECTION,
ANCILLARIES TO LAYING AND EXCAVATION
Protection
Protection of existing Du duct, including excavate to exposing the existing duct, and backfilling as per the Engineer approval
Cast in situ plain Concrete Class 25/20 around the existing Du duct
C | Existing duct | 35 | m | 300 | 10500 |  | 0 |  |  | 0 | 0
Additional Items
The tenderer to list with in this bill section, any additional items with quantities (enumerated or itemized) and rates which are not measured elsewhere in the section but required to complete the WORKS as per CONTRACT.
A | Concrete Surround for exisitingg ITS Line | 42 | m | 300 | 12600 |  | 0 |  |  | 0 | 0
B | Relocation of MRC MANHOLE | 1 | m | 9000 | 9000 |  | 0 |  |  | 0 | 0
PART 8 - DEWA (WD) WORKS
Removal of Pipeline
Carefully excavate around existing redundant water supply pipelines, remove pipes and fittings, deliver to DEWA Stores and backfill trench with suitable material including reinstatement.
A | 300mm diameter pipe | 40 | m | 430 | 17200 |  | 0 |  |  | 0 | 0
PIPEWORK - PIPES
Supply and Lay Self-restrained GRE pipes in trench with couplings including excavation, backfilling, etc. on previously excavated trench with necessary modification.
A | 300mm diameter depth not exceeding 1.5m | 10 | m | 1170 | 11700 |  | 0 |  |  | 0 | 0
Supply and Lay Self-restrained GRE pipes not in trench with couplings including excavation, backfilling, etc. on previously excavated trench with necessary modification.
B | 300mm diameter depth not exceeding 1.5m | 30 | m | 1170 | 35100 |  | 0 |  |  | 0 | 0
PIPEWORK - MANHOLES & PIPEWORK
ANCILLARIES
Connection to existing line
Connect new GRE pipe to existing pipe line in the same direction (on both side of the each location to be considered as one connection), including necessary fittings (Bend, Tees & Joints), additional excavation, and backfilling etc and complete all in respects in accordance with DEAW Requirements
C | Connection of 300mm dia. pipeline to existing pipeline 300mm dia. | 3 | nr | 29000 | 87000 |  | 0 |  |  | 0 | 0
PIPE WORK - SUPPORTS AND PROTECTION,
ANCILLARIES TO LAYING AND EXCAVATION
Beds and Surrounds
sand material bed
A | 300mm diameter | 10 | m | 28 | 280 |  | 0 |  |  | 0 | 0
Selected excavated material surrounds including laying of warning tapes, etc.
B | 300mm diameter | 10 | m | 33 | 330 |  | 0 |  |  | 0 | 0
Protection
Stiffness and fully laminated with reinforced concrete encasement protection. As per Drawings & Standards. As directed by Engineer.
C | 300mm diameter pipe | 30 | m | 1260 | 37800 |  | 0 |  |  | 0 | 0
Additional Items
The tenderer to list with in this bill section, any additional items with quantities (enumerated or itemized) and rates which are not measured elsewhere in the section but required to complete the WORKS as per CONTRACT.
| Supply and install Steel sleeve including spacer, rollers, brackets, grouting complete as detailed on DEWA-Standard and specifications. For 300mm GRE Pipe | 1 | m | 3200 | 0 |  | 0 |  |  | 0 | 0
PART 9 - DEWA (ED) WORKS
PIPEWORK - MANHOLES AND PIPE WORKS
ANCILLARIES
Duct works
Supply and lay 'uPVC' duct in trench in trench beneath carriageways including excavation, backfilling ,ropes, endcap and duct markers as specified
A | 4 way 150mm uPVC duct; depth not exceeding 1.5m | 35 | m | 700 | 24500 |  | 0 |  |  | 0 | 0
PIPE WORK - SUPPORTS AND PROTECTION,
ANCILLARIES TO LAYING AND EXCAVATION
Beds & surrounds
Selected excavated material bed and surrounds
including laying of warning tapes;
B | 4 way 150mm dia. Duct | 35 | m | 32 | 1120 |  | 0 |  |  | 0 | 0
Additional Items
The tenderer to list with in this bill section, any additional items with quantities (enumerated or itemized) and rates which are not measured elsewhere in the section but required to complete the WORKS as per CONTRACT.
PART 10 - DRAINAGE WORKS
PIPE WORK - SUPPORTS AND PROTECTION,
ANCILLARIES TO LAYING AND EXCAVATION
Relocate Existing Gully
A | Remove & Refixing of set a side gully ,including all related earth works connections , fittings, painting, etc, complete | 4 | nr | 3750 | 15000 |  | 0 |  |  | 0 | 0
Additional Items
The tenderer to list with in this bill section, any additional items with quantities (enumerated or itemized) and rates which are not measured elsewhere in the section but required to complete the WORKS as per CONTRACT.
PART 12 - IRRIGATION WORK
PIPEWORK - MANHOLES AND PIPEWORK
ANCILLARIES
Removal of Pipeline
Carefully excavate, expose and remove existing pipes and dispose to approved location/ or hand over to service authority; including all fittings, thrust blocks, necessary earth works reinstatement of the existing surface, etc.
A | Pipe nominal bore 200mm | 70 | m | 350 | 24500 |  | 40.5 | 40.5 |  | 14175 | 14175
PIPEWORK - PIPES
Supply and lay Self-restrained GRP pipes in trench including couplings, all accessories, excavation, backfilling, compaction, warning tapes and necessary testing, cleaning, handing over to DM Irrigation department, etc. all as per DM Irrigation department standards & specification.
A | 200mm dia. GRP pipe; depth 1.5 | 70 | m | 800 | 56000 |  | 40.5 | 40.5 |  | 32400 | 32400
PIPE WORK - SUPPORTS AND PROTECTION,
ANCILLARIES TO LAYING AND EXCAVATION
Connection to existing line
Connect new pipe to existing pipe line in the same direction with self restrained at the joints (on both side of the each location to be considered as one connection), including necessary fittings, additional excavation, and backfilling etc.
B | Connection of 200mm dia. pipe to existing pipeline dia. 200mm depth not exceeding 1.5m | 3 | nr | 20000 | 60000 |  | 0.9 | 0.9 |  | 18000 | 18000
Bed and surround to Pipes
Granular bed & surround to pipes including laying of warning tapes; etc. as per detail drawings, Engineer approval and the Drainage & Irrigation department Requirements
C | 200mm dia pipe. | 15 | m | 84 | 1260 |  | 0 |  |  | 0 | 0
Wrapping and lagging
Geotextile filter fabric around the granular surround to irrigation pipes as detailed on drawings
D | 200mm dia pipe. | 15 | m | 19 | 285 |  | 0 |  |  | 0 | 0
Protection
Stiffness and fully laminated with reinforced concrete encasement protection. As per Drawings & Standards. As directed by Engineer.
E | 200mm diameter pipe | 55 | m | 892 | 49060 |  | 40.5 | 40.5 |  | 36126 | 36126
Additional Items
The tenderer to list with in this bill section, any additional items with quantities (enumerated or itemized) and rates which are not measured elsewhere in the section but required to complete the WORKS as per CONTRACT.
PART 13 - SEWERAGE WORKS
Ancillaries
A | Adjustment of existing manhole/chamber levels to suit finished levels by approximately +0.5m to +1.0m | 3 | nr | 5625 | 16875 |  | 0 |  |  | 0 | 0
Additional Items
The tenderer to list with in this bill section, any additional items with quantities (enumerated or itemized) and rates which are not measured elsewhere in the section but required to complete the WORKS as per CONTRACT.
PART 14 - SPARE DUCTS WORKS
PIPEWORK - MANHOLES AND PIPEWORK
ANCILLARIES
Supply and lay uPVC spare ducts in trench
including end caps, draw ropes, studs and
concrete duct markers as specified
Depth not exceeding 1.5m
A | Two way 200mm dia duct | 35 | m | 426 | 14910 |  | 0 |  |  | 0 | 0
PIPE WORK - SUPPORTS AND PROTECTION,
ANCILLARIES TO LAYING AND EXCAVATION
Bed & surrounds
Selected excavated material bed and surrounds
including laying of warning tapes;
B | Two way 200mm dia duct | 35 | m | 27 | 945 |  | 0 |  |  | 0 | 0
Additional Items
The tenderer to list with in this bill section, any additional items with quantities (enumerated or itemized) and rates which are not measured elsewhere in the section but required to complete the WORKS as per CONTRACT.
PART 15 - PROVISIONAL SUMS
Note:
The Provisional Sums given in the Bill of Quantities may be expended totally or in part or not at all, at the discretion of the Engineer.
The Contractor shall coordinate with the services authorities and provide all necessary facilities as may be required and as foreseeable by an experienced contractor. The cost of such coordination and facilities is deemed to be included in the respective item given in Bill No. 1 of the Bills of Quantities.
Service Authority Works
A | Allow the provisional sum for direct payment by the Employer to Service Authority. |  | Sum
Contingencies
F | Allow the Provisional Sum of contingencies to be expended at the discretion of the Employer |  | Sum
G | Percentage addition for Attendance, Overhead &
| Profit on Contingencies | 0.15 | %
[5 empty] | 1068941.8 |  |  |  | 84150 | 154291.128 | 238441.128
| Discount |  |  |  | -25000 |  | 0 |  | -1968.0679 | -3608.5016 | -5576.5695
[9 empty] | 82181.9321 | 150682.6264 | 232864.5585
| Advance Payment (20%) | [7 empty] | 208788.4 | 0 | 208788.4
| Advance Payment Recovery (20%) | [7 empty] | -16436.3864 | -30136.5253 | -46572.9117
[5 empty] | 1043941.8 |  |  |  | 274533.9457 | 120546.1011 | 395080.0468
[8 empty] | KCE Claim | 292938.4 | 147486.24 | 440424.64
[8 empty] | Difference | -18404.4543 | -26940.1389 | -45344.5932
Note on I30: Himal Kosala: 90% until WIR approval
Note on I164: Himal Kosala: 90% until WIR approval
Note on I167: Himal Kosala: 90% until WIR approval
Note on I172: Himal Kosala: 90% until WIR approval
Note on I181: Himal Kosala: 90% until WIR approval