## INV-003
Tax Invoice TRN NO. 100355710300003
Invoice No. | # 23007
Date: | 2023-01-13
Bill To:
Customer ID :
Customer Name : Sky Palaces Real Estate Development LLC
P.O. Box 12501
Tax Registration No:
PROJECT |  |  |  | Sub Contract / LOI REF. No:
The Residences Dorchester Collection by Omniyat, Business Bay, Dubai |  |  |  | F015/15.1.13/31649/PMTDG/0321 Variation Order No.1 dated 17/May/2022
S. No. |  |  | DESCRIPTION |  |  | UNIT | AMOUNT
|  | Supply, Installation, Testing and Commissioning of Hoods, Fire Suppression, Coldrooms, and Floor Grating at The Residences Dorchester Collection by Omniyat, Business Bay, Dubai |  |  |  | Total Amount Without VAT | 1023695
|  | Variation Order No.1 dated 17/May/2022 |  |  |  |  | 2359987
|  | Total Amount |  |  |  |  | 3383682
A |  | Claim for work done until 13/Jan/2023 as per the attached Document Ref. : DCD/KE/13A22/IC/INV003 |  |  |  |  | 278598.2375
B |  | Less: Recovery of advance payment |  |  |  | 30% | -83579.4713
C |  | Less: Retention |  |  |  | 10% | -27859.8238
C |  | Less: Retention (5% of A) |  |  |  |  | 0
A+B+C | [5 empty] | Total Billed (AED): | 167158.9425
|  |  |  | Less: Previously Invoiced Amount |  |  | 0
[5 empty] | Total Invoice Amount (AED): |  | 167158.95
[5 empty] | VAT 5% |  | 8357.9475
[5 empty] | Grand Total (AED): |  | 175516.8975
Total Amount Invoiced In Words:
One Hundred Seventy Five Thousand, Five Hundred and Sixteen UAE Dirhams & Ninety Fils
Authorised Signatory :
Make all checks payable to TSSC Kitchen & Laundry Equipment Trading LLC.
Our Bank Account : 0510036675784260016, Banque Banorient France Bank, PO Box 4370
IBAN: AE150140036675784260016 / Swift : BLOMAEAD
THANK YOU

## INV-003 - BOQ
[27 empty] | Project : Dorchester Collection, Dubai | [14 empty] | Sub Contractor : TSSC Kitchen & Laundry Equipment Trading LLC
[27 empty] | Package : Supply & Installation of Kitchen Equipment | [14 empty] | Document Ref. : DCD/KE/13A22/IC/INV003
[27 empty] | Client : Sky Palaces Real Estate Development LLC | [14 empty] | Date : 13th January 2023
Bill Of Quantities for Kitchen Equipment with claim for work done until 13/Jan/2023
Claim for Materials Delivered & Work Done
‡ - Basis of Cumulative Rate: Advance Payment - 30%, Material On Site - 90 % Installed - 95% & Commissioned Equipment - 100%.
S. No | Spacer | Bill No. | Building Code | Building | Building Area | Area Seq No. | AreaCode | Kitchen Area | Area Item Prefix | Check?? | Non-Supply Item | Show for Bill | Drawing No | Drawing rev | Page No | R1 Query | Titles | Marker | Variation Ref | Calc Change | Area | Price Updated | Details Updated | Equipment Category | Area | Composite Item No. | Item No | Qty | Unit | Area / Item Description | Manufacturer | Model | Origin | Unit Rate (UAE Dirhams) | Amount (UAE Dirhams) | MIR # Ref | Invoice Qty | % of Work Completed | Value of Work Completed | Prev. Claimed Amount For Work Complete | Net Current Claim (AED) | Comments
1 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | FL.00 | FL.00 FLOWER ROOM |  | Title Row | No | [5 empty] | Building Title |  | VO # 01 | Description Change | [9 empty] | BASEMENT 1
2 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | FL.00 | FL.00 FLOWER ROOM |  |  | No | [5 empty] | Area Title |  | VO # 01 | Description Change | [9 empty] | FL.00 FLOWER ROOM
3 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | FL.00 | FL.00 FLOWER ROOM |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | FL.01 | 1 | No. | Modular Coldroom complete with | TSSC. | Custom | U. A. E. | 967364 | 967364 |  | 1 | 7% | 67715.48 | 0 | 67715.48 | Since the price is the total for 22 Nos of cold rooms, Claimed amount is for the 2 Cold rooms panels delivered. Item Ref: BQ.14A
4 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | FL.00 | FL.00 FLOWER ROOM |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | FL.01A | 1 | No. | Control Panel | TSSC. | Custom | U. A. E. | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
5 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | FL.00 | FL.00 FLOWER ROOM |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | FL.01B | 1 | No. | Evaporator | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
6 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | FL.00 | FL.00 FLOWER ROOM |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | FL.01C | 1 | No. | Remote Air Cooled Compressor | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
7 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | LD.00 | LD.00 LOADING DOCK |  |  | No | [5 empty] | Area Title |  | VO # 01 | Description Change | [9 empty] | LD.00 LOADING DOCK
8 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | LD.00 | LD.00 LOADING DOCK |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | LD.07 | 3 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 487 | 1461 | MIR # 001 | 3 | 90% | 1314.9 | 0 | 1314.9
9 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | LD.00 | LD.00 LOADING DOCK |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | LD.08 | 1 | No. | Floor drain with stainless steel gratings. 10300 x 500 | PKI / Techsteel | Custom | U. A. E. | 7123 | 7123 | MIR # 001 | 1 | 90% | 6410.7 | 0 | 6410.7 | Item deleted
10 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | RD.00 | RD.00 RECEIVING & DECANT |  |  | No | [5 empty] | Area Title |  | VO # 01 | Description Change | [9 empty] | RD.00 RECEIVING & DECANT
11 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | RD.00 | RD.00 RECEIVING & DECANT |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | RD.08 | 1 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 488 | 488 | MIR # 001 | 1 | 90% | 439.2 | 0 | 439.2
12 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | RW.00 | RW.00 RAW WASH |  |  | No | [5 empty] | Area Title |  | VO # 01 | Description Change | [9 empty] | RW.00 RAW WASH
13 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | RW.00 | RW.00 RAW WASH |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | RW.03 | 1 | No. | Floor drain with stainless steel gratings. 1200 x 300 | PKI / Techsteel | Custom | U. A. E. | 861 | 861 | MIR # 001 | 1 | 90% | 774.9 | 0 | 774.9
14 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | CS.00 | CS.00 CENTRL FOOD AND BEVERAGE STORES |  |  | No | [5 empty] | Area Title |  | VO # 01 | Description Change | [9 empty] | CS.00 CENTRL FOOD AND BEVERAGE STORES
15 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | CS.00 | CS.00 CENTRL FOOD AND BEVERAGE STORES |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | CS.01 | 1 | No. | 5 Compartment Modular Coldroom/Freezer Room Suite Comprising: | TSSC. | Custom | U. A. E. | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
16 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | CS.00 | CS.00 CENTRL FOOD AND BEVERAGE STORES |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | CS.01A | 5 | No. | Control Panels | TSSC. | Custom | U. A. E. | 0 | 0 |  | 5 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
17 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | CS.00 | CS.00 CENTRL FOOD AND BEVERAGE STORES |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | CS.01B | 1 | No. | Evaporator (Vegetable & Fruit Coldroom) | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
18 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | CS.00 | CS.00 CENTRL FOOD AND BEVERAGE STORES |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | CS.01C | 1 | No. | Air Cooled Compressor (Vegetable & Fruit Coldroom) | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
19 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | CS.00 | CS.00 CENTRL FOOD AND BEVERAGE STORES |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | CS.01D | 1 | No. | Evaporator (Meat Coldroom) | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
20 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | CS.00 | CS.00 CENTRL FOOD AND BEVERAGE STORES |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | CS.01E | 1 | No. | Air Cooled Compressor (Meat Coldroom) | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
21 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | CS.00 | CS.00 CENTRL FOOD AND BEVERAGE STORES |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | CS.01F | 1 | No. | Evaporator (Poultry Coldroom) | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
22 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | CS.00 | CS.00 CENTRL FOOD AND BEVERAGE STORES |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | CS.01G | 1 | No. | Air Cooled Compressor (Poultry Coldroom) | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
23 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | CS.00 | CS.00 CENTRL FOOD AND BEVERAGE STORES |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | CS.01H | 1 | No. | Evaporator (Seafood Coldroom) | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
24 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | CS.00 | CS.00 CENTRL FOOD AND BEVERAGE STORES |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | CS.01I | 1 | No. | Air Cooled Compressor (Seafood Coldroom) | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
25 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | CS.00 | CS.00 CENTRL FOOD AND BEVERAGE STORES |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | CS.01J | 1 | No. | Evaporator (Fish Coldroom) | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
26 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | CS.00 | CS.00 CENTRL FOOD AND BEVERAGE STORES |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | CS.01K | 1 | No. | Air Cooled Compressor (Fish Coldroom) | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
27 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | CS.00 | CS.00 CENTRL FOOD AND BEVERAGE STORES |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | CS.06 | 8 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 487 | 3896 | MIR # 002 | 8 | 90% | 3506.4 | 0 | 3506.4
28 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | CS.00 | CS.00 CENTRAL FOOD & BEVERAGE STORES |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | CS.08 | 1 | No. | 3 Compartment Modular Coldroom Suite Comprising: | TSSC. | Custom | U. A. E. | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
29 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | CS.00 | CS.00 CENTRAL FOOD & BEVERAGE STORES |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | CS.08a | 3 | No. | Control Panels | TSSC. | Custom | U. A. E. | 0 | 0 |  | 3 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
30 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | CS.00 | CS.00 CENTRAL FOOD & BEVERAGE STORES |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | CS.08b | 1 | No. | Evaporator (General Purpose Coldroom) | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
31 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | CS.00 | CS.00 CENTRAL FOOD & BEVERAGE STORES |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | CS.08c | 1 | No. | Air Cooled Compressor (General Purpose Coldroom) | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
32 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | CS.00 | CS.00 CENTRAL FOOD & BEVERAGE STORES |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | CS.08d | 1 | No. | Evaporator (Beverage Coldroom 1) | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
33 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | CS.00 | CS.00 CENTRAL FOOD & BEVERAGE STORES |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | CS.08e | 1 | No. | Air Cooled Compressor(Beverage Coldroom 1) | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
34 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | CS.00 | CS.00 CENTRAL FOOD & BEVERAGE STORES |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | CS.08f | 2 | No. | Evaporator (Beverage Coldroom 2) | LU-VE | - | GERMANY | 0 | 0 |  | 2 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
35 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | CS.00 | CS.00 CENTRAL FOOD & BEVERAGE STORES |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | CS.08g | 2 | No. | Air Cooled Compressor(Beverage Coldroom 2) | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 2 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
36 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | CS.00 | CS.00 CENTRAL FOOD & BEVERAGE STORES |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | CS.09 | 1 | No. | 2 Compartment Modular Coldroom Suite Comprising: | TSSC. | Custom | U. A. E. | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
37 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | CS.00 | CS.00 CENTRAL FOOD & BEVERAGE STORES |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | CS.09a | 2 | No. | Control Panels | TSSC. | Custom | U. A. E. | 0 | 0 |  | 2 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
38 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | CS.00 | CS.00 CENTRAL FOOD & BEVERAGE STORES |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | CS.09b | 1 | No. | Evaporator (Freezer Room 1) | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
39 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | CS.00 | CS.00 CENTRAL FOOD & BEVERAGE STORES |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | CS.09c | 1 | No. | Air Cooled Compressor (Freezer Room 1) | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
40 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | CS.00 | CS.00 CENTRAL FOOD & BEVERAGE STORES |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | CS.09d | 1 | No. | Evaporator (Freezer Room 2) | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
41 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | CS.00 | CS.00 CENTRAL FOOD & BEVERAGE STORES |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | CS.09e | 1 | No. | Air Cooled Compressor(Freezer Room 2) | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
42 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | CS.00 | CS.00 CENTRAL FOOD & BEVERAGE STORES |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | CS.14 | 1 | No. | Modular Coldroom Comprising: | TSSC. | Custom | U. A. E. | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
43 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | CS.00 | CS.00 CENTRAL FOOD & BEVERAGE STORES |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | CS.14a | 1 | No. | Control Panel | TSSC. | Custom | U. A. E. | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
44 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | CS.00 | CS.00 CENTRAL FOOD & BEVERAGE STORES |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | CS.14b | 1 | No. | Evaporator | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
45 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | CS.00 | CS.00 CENTRAL FOOD & BEVERAGE STORES |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | CS.14c | 1 | No. | Air Cooled Compressor | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
46 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | P.00 | P.00 PREPARATION AREAS - Vegetable and Fruit Preparation Area |  |  | No | [5 empty] | Area Title |  | VO # 01 | Description Change | [9 empty] | P.00 PREPARATION AREAS - Vegetable and Fruit Preparation Area
47 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | P.00 | P.00 PREPARATION AREAS - Vegetable and Fruit Preparation Area |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | P.09 | 2 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 488 | 976 | MIR # 002 | 2 | 90% | 878.4 | 0 | 878.4
48 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | P.00 | P.00 PREPARATION AREAS - Meat Prep & Poultry Preparation Areas |  |  | No | [5 empty] | Area Title |  | VO # 01 | Description Change | [9 empty] | P.00 PREPARATION AREAS - Meat Prep & Poultry Preparation Areas
49 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | P.00 | P.00 PREPARATION AREAS - Meat Prep & Poultry Preparation Areas |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | P.19 | 2 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 488 | 976 | MIR # 002 | 2 | 90% | 878.4 | 0 | 878.4
50 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | P.00 | P.00 PREPARATION AREAS - Fish and Seafood Preparation Area |  |  | No | [5 empty] | Area Title |  | VO # 01 | Description Change | [9 empty] | P.00 PREPARATION AREAS - Fish and Seafood Preparation Area
51 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | P.00 | P.00 PREPARATION AREAS - Fish and Seafood Preparation Area |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | P.32 | 1 | No. | Floor drain with stainless steel gratings. 1000 x 300 | PKI / Techsteel | Custom | U. A. E. | 861 | 861 | MIR # 002 | 1 | 90% | 774.9 | 0 | 774.9
52 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | P.00 | P.00 PREPARATION AREAS - Fish and Seafood Preparation Area |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | P.47 | 1 | No. | Floor drain with stainless steel gratings. 500+1900+500 x 300 | PKI / Techsteel | Custom | U. A. E. | 1726 | 1726 | MIR # 002 | 1 | 90% | 1553.4 | 0 | 1553.4
53 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | P.00 | P.00 PREPARATION AREAS - Fish and Seafood Preparation Area |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | P.48 | 1 | No. | 2 Compartment Modular Coldroom Suite | TSSC. | Custom | U. A. E. | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
54 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | P.00 | P.00 PREPARATION AREAS - Fish and Seafood Preparation Area |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | P.48a | 1 | No. | Dual Compartment Control Panel | TSSC. | Custom | U. A. E. | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
55 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | P.00 | P.00 PREPARATION AREAS - Fish and Seafood Preparation Area |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | P.48b | 1 | No. | Evaporator (Coldroom 1) | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
56 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | P.00 | P.00 PREPARATION AREAS - Fish and Seafood Preparation Area |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | P.48c | 1 | No. | Evaporator (Coldroom 2) | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
57 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | P.00 | P.00 PREPARATION AREAS - Fish and Seafood Preparation Area |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | P.48d | 1 | No. | Air Cooled Compressor (Coldroom 1) | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
58 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | P.00 | P.00 PREPARATION AREAS - Fish and Seafood Preparation Area |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | P.48e | 1 | No. | Air Cooled Compressor (Coldroom 2) | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
59 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | BP.00 | BP.00 BAKERY & PASTRY |  |  | No | [5 empty] | Area Title |  | VO # 01 | Description Change | [9 empty] | BP.00 BAKERY & PASTRY
60 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | BP.00 | BP.00 BAKERY & PASTRY |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | BP.11 | 1 | No. | 2 Compartment Modular Coldroom Suite | TSSC. | Custom | U. A. E. | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
61 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | BP.00 | BP.00 BAKERY & PASTRY |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | BP.11a | 1 | No. | Dual Compartment Control Panel | TSSC. | Custom | U. A. E. | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
62 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | BP.00 | BP.00 BAKERY & PASTRY |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | BP.11b | 1 | No. | Evaporator (Coldroom) | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
63 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | BP.00 | BP.00 BAKERY & PASTRY |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | BP.11c | 1 | No. | Evaporator (Freezer Room) | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
64 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | BP.00 | BP.00 BAKERY & PASTRY |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | BP.11d | 1 | No. | Air Cooled Compressor (Coldroom) | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
65 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | BP.00 | BP.00 BAKERY & PASTRY |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | BP.11e | 1 | No. | Air Cooled Compressor (Freezer Room) | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
66 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | BP.00 | BP.00 BAKERY & PASTRY |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | BP.20 | 1 | No. | Floor drain with stainless steel gratings. 2030 x 300 | PKI / Techsteel | Custom | U. A. E. | 1199 | 1199 | MIR # 002 | 1 | 90% | 1079.1 | 0 | 1079.1
67 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | BP.00 | BP.00 BAKERY & PASTRY |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | BP.24 | 6 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 487 | 2922 | MIR # 002 | 6 | 90% | 2629.8 | 0 | 2629.8
68 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | BP.00 | BP.00 BAKERY & PASTRY |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | BP.35 | 1 | No. | Hood type: Baffle - Wall mount - Wall type - Double skin Hood dimension: 3100 (L) x 2450 (W) x 600 (H) , in 1 section(s) Material: AISI 304, 1.2 mm - Brush Finish Exhaust air: 4644 m3/h Make-up air by Ginox: 0 m3/h - Hood front Lights: Flurorescent panel, 2 unit(s) Drain type: Not applicable | GINOX Hoods | CUSTOM HOOD | U. A. E. | 26941 | 26941 |  | 1 | 0% | 0 | 0 | 0
69 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND.1614.L4.FB.SCH.001.00 | BP.00 | BP.00 BAKERY & PASTRY |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | BP.35.1 | 1 | No. | Incl. 3 x Automated Dampers, 1 x Touchpad (On/Off Control) | GINOX Hoods | CUSTOM | U. A. E. | 15197 | 15197 |  | 1 | 0% | 0 | 0 | 0
70 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | BP.00 | BP.00 BAKERY & PASTRY |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | BP.35a | 1 | No. | Fire Suppression System | AVENGER | WET CHEMICAL | U. S. A. | 0 | INCLUDED IN BP.37a |  | 1 | 0% | 0 | 0 | 0
71 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND.1614.L4.FB.SCH.001.00 | BP.00 | BP.00 BAKERY & PASTRY |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | BP.36 | 1 | No. | service distribution unit with grid shelf. 2850 x 200 | PKI / Techsteel | Custom - SDU | U. A. E. | 6041 | 6041 |  | 1 | 0% | 0 | 0 | 0
72 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | BP.00 | BP.00 BAKERY & PASTRY |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | BP.37 | 1 | No. | Hood type: UV - Wall mount - Wall type - Double skin Hood dimension: 2300 (L) x 1500 (W) x 600 (H) , in 1 section(s) Material: AISI 304, 1.2 mm - Brush Finish Exhaust air: 1530 m3/h Make-up air by Ginox: 0 m3/h - Hood front Lights: Flurorescent panel, 1 unit(s) Drain type: Not applicable | GINOX Hoods | CUSTOM HOOD | U. A. E. | 50439 | 50439 |  | 1 | 0% | 0 | 0 | 0
73 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND.1614.L4.FB.SCH.001.00 | BP.00 | BP.00 BAKERY & PASTRY |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | BP.37.1 | 1 | No. | Incl. 2 x Automated Dampers, 1 x Touchpad (On/Off Control) | GINOX Hoods | CUSTOM | U. A. E. | 10137 | 10137 |  | 1 | 0% | 0 | 0 | 0
74 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | BP.00 | BP.00 BAKERY & PASTRY |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | BP.37a | 1 | No. | Fire Suppression System | AVENGER | WET CHEMICAL | U. S. A. | 11603 | 11603 |  | 1 | 0% | 0 | 0 | 0
75 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | GM.00 | GM.00 GARDE MANGER |  |  | No | [5 empty] | Area Title |  | VO # 01 | Description Change | [9 empty] | GM.00 GARDE MANGER
76 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | GM.00 | GM.00 GARDE MANGER |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | GM.11 | 1 | No. | Modular Coldroom comprising | TSSC. | Custom | U. A. E. | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
77 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | GM.00 | GM.00 GARDE MANGER |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | GM.11a | 1 | No. | Control Panel | TSSC. | Custom | U. A. E. | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
78 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | GM.00 | GM.00 GARDE MANGER |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | GM.11b | 1 | No. | Evaporator | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
79 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | GM.00 | GM.00 GARDE MANGER |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | GM.11c | 1 | No. | Air Cooled Compressor | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
80 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | HK.00 | HK.00 HOT KITCHEN |  |  | No | [5 empty] | Area Title |  | VO # 01 | Description Change | [9 empty] | HK.00 HOT KITCHEN
81 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | HK.00 | HK.00 HOT KITCHEN |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | HK.09 | 1 | No. | Floor drain with stainless steel gratings. 3150+350+350 x 400/350 | PKI / Techsteel | Custom | U. A. E. | 3155 | 3155 | MIR # 002 | 1 | 90% | 2839.5 | 0 | 2839.5
82 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | HK.00 | HK.00 HOT KITCHEN |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | HK.10 | 1 | No. | Floor drain with stainless steel gratings. 850+300 x 400/350 | PKI / Techsteel | Custom | U. A. E. | 1316 | 1316 | MIR # 002 | 1 | 90% | 1184.4 | 0 | 1184.4
83 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | HK.00 | HK.00 HOT KITCHEN |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | HK.11 | 1 | No. | service distribution unit with grid shelf. 5460 x 250 | PKI / Techsteel | Custom - SDU | U. A. E. | 10696 | 10696 |  | 1 | 0% | 0 | 0 | 0
84 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | HK.00 | HK.00 HOT KITCHEN |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | HK.12 | 1 | No. | Hood type: UV - Island mount - Island type - Double skin Hood dimension: 6055 (L) x 2975 (W) x 600 (H) , in 2 section(s) Material: AISI 304, 1.2 mm - Brush Finish Exhaust air: 16,085 m3/h Make-up air by Ginox: 13,672 m3/h - Hood front Lights: Flurorescent panel, 8 unit(s) Drain type: Not applicable | GINOX Hoods | CUSTOM HOOD | U. A. E. | 183742 | 183742 |  | 1 | 0% | 0 | 0 | 0
85 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND.1614.L4.FB.SCH.001.00 | HK.00 | HK.00 HOT KITCHEN |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | HK.12.1 | 1 | No. | Incl. 6 x Automated Dampers, 1 x Touchpad (On/Off Control) | GINOX Hoods | CUSTOM | U. A. E. | 30381 | 30381 |  | 1 | 0% | 0 | 0 | 0
86 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | HK.00 | HK.00 HOT KITCHEN |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | HK.12a | 1 | No. | Fire Suppression System | AVENGER | WET CHEMICAL | U. S. A. | 19957 | 19957 |  | 1 | 0% | 0 | 0 | 0
87 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | HK.00 | HK.00 HOT KITCHEN |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | HK.15 | 1 | No. | Modular Coldroom comprising | TSSC. | Custom | U. A. E. | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
88 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | HK.00 | HK.00 HOT KITCHEN |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | HK.15a | 1 | No. | Control Panel | TSSC. | Custom | U. A. E. | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
89 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | HK.00 | HK.00 HOT KITCHEN |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | HK.15b | 1 | No. | Evaporator | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
90 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | HK.00 | HK.00 HOT KITCHEN |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | HK.15c | 1 | No. | Air Cooled Compressor | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
91 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | HK.00 | HK.00 HOT KITCHEN |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | HK.20 | 1 | No. | Modular Coldroom/Freezer comprising: | TSSC. | Custom | U. A. E. | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
92 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | HK.00 | HK.00 HOT KITCHEN |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | HK.20a | 1 | No. | Control Panel | TSSC. | Custom | U. A. E. | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
93 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | HK.00 | HK.00 HOT KITCHEN |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | HK.20b | 1 | No. | Evaporator | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
94 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | HK.00 | HK.00 HOT KITCHEN |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | HK.20c | 1 | No. | Air Cooled Compressor | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
95 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | HK.00 | HK.00 HOT KITCHEN |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | HK.24 | 1 | No. | Hood type: Water Wash - Wall mount - Wall type - Double skin Hood dimension: 4480 (L) x 1500 (W) x 600 (H) , in 2 section(s) Material: AISI 304, 1.2 mm - Brush Finish Exhaust air: 4,585 m3/h Make-up air by Ginox: 3,897 m3/h - Hood front Lights: Flurorescent panel, 2 unit(s) Drain type: Gravity | GINOX Hoods | CUSTOM HOOD | U. A. E. | 59489 | 59489 |  | 1 | 0% | 0 | 0 | 0
96 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND.1614.L4.FB.SCH.001.00 | HK.00 | HK.00 HOT KITCHEN |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | HK.24.1 | 1 | No. | Incl. 4 x Automated Dampers, 1 x Touchpad (On/Off Control) | GINOX Hoods | CUSTOM | U. A. E. | 20259 | 20259 |  | 1 | 0% | 0 | 0 | 0
97 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | HK.00 | HK.00 HOT KITCHEN |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | HK.24a | 1 | No. | Fire Suppression System | AVENGER | WET CHEMICAL | U. S. A. | 7890 | 7890 |  | 1 | 0% | 0 | 0 | 0
98 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | HK.00 | HK.00 HOT KITCHEN |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | HK.30 | 1 | No. | Hood type: Steam - Wall mount - Wall type - Single skin Hood dimension: 1500 (L) x 1250 (W) x 600 (H) , in 1 section(s) Material: AISI 304, 1.2 mm - Brush Finish Exhaust air: 2,425 m3/h Make-up air by Ginox: 0 m3/h - none Lights: No, 0 unit(s) Drain type: Not applicable | GINOX Hoods | CUSTOM HOOD | U. A. E. | 5136 | 5136 | MIR # 005 | 1 | 90% | 4622.4 | 0 | 4622.4
99 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | HK.00 | HK.00 HOT KITCHEN |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | HK.34 | 1 | No. | Floor drain with stainless steel gratings. 1400 x 300 | PKI / Techsteel | Custom | U. A. E. | 941 | 941 | MIR # 002 | 1 | 90% | 846.9 | 0 | 846.9
100 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | SDP.00 | SDP.00 STAFF DINING SUPPORT PANTRY |  |  | No | [5 empty] | Area Title |  | VO # 01 | Description Change | [9 empty] | SDP.00 STAFF DINING SUPPORT PANTRY
101 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | SDP.00 | SDP.00 STAFF DINING SUPPORT PANTRY |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | SDP.07 | 1 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 488 | 488 | MIR # 001 | 1 | 90% | 439.2 | 0 | 439.2
102 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | SDP.00 | SDP.00 STAFF DINING SUPPORT PANTRY |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | SD.09 | 1 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 488 | 488 | MIR # 001 | 1 | 90% | 439.2 | 0 | 439.2
103 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | SDP.00 | WW.00 STAFF DINING ROOM WAREWASH |  |  | No | [5 empty] | Area Title |  | VO # 01 | Description Change | [9 empty] | WW.00 STAFF DINING ROOM WAREWASH
104 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | WW.00 | WW.00 STAFF DINING ROOM WAREWASH |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | WW.07 | 1 | No. | Hood type: Steam - Wall mount - Wall type - Single skin Hood dimension: 1140 (L) x 1050 (W) x 600 (H) , in 1 section(s) Material: AISI 304, 1.2 mm - Brush Finish Exhaust air: 825 m3/h Make-up air by Ginox: 0 m3/h - none Lights: No, 0 unit(s) Drain type: Not applicable | GINOX Hoods | CUSTOM HOOD | U. A. E. | 4383 | 4383 | MIR # 005 | 1 | 90% | 3944.7 | 0 | 3944.7
105 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | WW.00 | WW.00 STAFF DINING ROOM WAREWASH |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | WW.08 | 2 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 488 | 976 | MIR # 001 | 2 | 90% | 878.4 | 0 | 878.4
106 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  | FND-1614-B1-FB-SCH-001 | WW.00 | WW.00 STAFF DINING ROOM WAREWASH |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | WW.10 | 1 | No. | Floor drain with stainless steel gratings. 1200 x 300 | PKI / Techsteel | Custom | U. A. E. | 861 | 861 | MIR # 001 | 1 | 90% | 774.9 | 0 | 774.9
107 | 1 1 | Variation Order No.1 dated 17/May/2022 | Laundry Room | BASEMENT 1 |  |  |  | R.00 CENTRAL REFUSE AREA |  | Title Row | No | [5 empty] | Area Title |  | VO # 01 | Description Change | [9 empty] | R.00 CENTRAL REFUSE AREA
108 | 1 1 | Variation Order No.1 dated 17/May/2022 | Laundry Room | BASEMENT 1 |  |  |  | R.00 CENTRAL REFUSE AREA |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | R.05 | 4 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 487 | 1948 | MIR # 002 | 4 | 90% | 1753.2 | 0 | 1753.2
109 | 1 1 | Variation Order No.1 dated 17/May/2022 | Laundry Room | BASEMENT 1 |  |  |  | R.00 CENTRAL REFUSE AREA |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | R.12 | 1 | No. | Modular Coldroom comprising: | TSSC. | Custom | U. A. E. | 0 | INCLUDED IN FL.01 |  | 1 | 0% | 0 | 0 | 0
110 | 1 1 | Variation Order No.1 dated 17/May/2022 | Laundry Room | BASEMENT 1 |  |  |  | R.00 CENTRAL REFUSE AREA |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | R.12a | 1 | No. | Control Panel | TSSC. | Custom | U. A. E. | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
111 | 1 1 | Variation Order No.1 dated 17/May/2022 | Laundry Room | BASEMENT 1 |  |  |  | R.00 CENTRAL REFUSE AREA |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | R.12b | 1 | No. | Air Cooled Compressor | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
112 | 1 1 | Variation Order No.1 dated 17/May/2022 | Laundry Room | BASEMENT 1 |  |  |  | R.00 CENTRAL REFUSE AREA |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | R.12c | 2 | No. | Evaporators | LU-VE | - | GERMANY | 0 | 0 |  | 2 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
113 | 1 1 | Variation Order No.1 dated 17/May/2022 | Laundry Room | BASEMENT 1 |  |  |  | R.00 CENTRAL REFUSE AREA |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | R.13 | 1 | No. | Floor drain with stainless steel gratings. 2770 x 2500 | PKI / Techsteel | Custom | U. A. E. | 9056 | 9056 | MIR # 002 | 1 | 90% | 8150.4 | 0 | 8150.4
114 | 1 1 | Variation Order No.1 dated 17/May/2022 | Laundry Room | BASEMENT 1 |  |  |  | R.00 CENTRAL REFUSE AREA |  | Title Row | No | [5 empty] | Area Title |  | VO # 01 | Description Change | [9 empty] | R.00 CENTRAL REFUSE AREA
115 | 1 1 | Variation Order No.1 dated 17/May/2022 | Laundry Room | BASEMENT 1 |  |  |  | R1.00 REFUSE STORE 1 |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | R1.03 | 1 | No. | Floor drain with stainless steel gratings. 2000 x 300 | PKI / Techsteel | Custom | U. A. E. | 1185 | 1185 | MIR # 002 | 1 | 90% | 1066.5 | 0 | 1066.5
116 | 1 1 | Variation Order No.1 dated 17/May/2022 | Laundry Room | BASEMENT 1 |  |  |  | R1.00 REFUSE STORE 1 |  | Title Row | No | [5 empty] | Area Title |  | VO # 01 | Description Change | [9 empty] | R1.00 REFUSE STORE 1
117 | 1 1 | Variation Order No.1 dated 17/May/2022 | Laundry Room | BASEMENT 1 |  |  |  | R2.00 REFUSE STORE 2 |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | R2.03 | 3 | No. | Floor drain with stainless steel gratings. 2000 x 300 | PKI / Techsteel | Custom | U. A. E. | 1181 | 3543 | MIR # 002 | 3 | 90% | 3188.7 | 0 | 3188.7
118 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  |  |  | R2.00 REFUSE STORE 2 |  | Check | No | [5 empty] | Building Subtotals |  | VO # 01 | [5 empty] | Sub-Total for BASEMENT 1 : |  | Sub-Total for Basement 1 : | [6 empty] | UAE Dirhams | 1476101 |  |  |  | 118083.98 | 0 | 118083.98
119 | 1 1 | Main Contract | Laundry Room | Laundry Room | [5 empty] | Title Row | No | [5 empty] | Building Title |  |  | Description Change | [9 empty] | Laundry Room |  |  |  | 0 | 0
120 | 1 1 | Variation Order No.1 dated 17/May/2022 | Laundry Room | LAUNDRY BASEMENT 1 |  | FND-1614-B1-LH-BOQ-001-00 |  |  |  | Title Row | No | [5 empty] | Area Title |  | VO # 01 | Description Change | [9 empty] | LAUNDRY BASEMENT 1
121 | 1 1 | Variation Order No.1 dated 17/May/2022 | Laundry Room | LAUNDRY BASEMENT 1 |  | FND-1614-B1-LH-BOQ-001-00 |  | UD.00 UNIFORM DISTRIBUTION AREA |  | Title Row | No | [5 empty] | Area Title |  | VO # 01 | UD.00 UNIFORM DISTRIBUTION AREA | [9 empty] | UD.00 UNIFORM DISTRIBUTION AREA
122 | 1 1 | Variation Order No.1 dated 17/May/2022 | Laundry Room | LAUNDRY BASEMENT 1 |  | FND-1614-B1-LH-BOQ-001-00 |  | UD.00 UNIFORM DISTRIBUTION AREA |  | OK | No | [7 empty] | VO # 01 | UD.00 UNIFORM DISTRIBUTION AREA | [6 empty] | UD.06 | 1 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 488 | 488 | MIR # 001 | 1 | 90% | 439.2 | 0 | 439.2
123 | 1 1 | Variation Order No.1 dated 17/May/2022 | Laundry Room | LAUNDRY BASEMENT 1 |  | FND-1614-B1-LH-BOQ-001-00 |  | UD.00 UNIFORM DISTRIBUTION AREA |  | Title Row | No | [5 empty] | Area Title |  | VO # 01 | Description Change | [9 empty] | UD.00 UNIFORM DISTRIBUTION AREA
124 | 1 1 | Variation Order No.1 dated 17/May/2022 | Laundry Room | LAUNDRY BASEMENT 1 |  | FND-1614-B2-SCH-001-00 |  | GV.00 GUEST VALET AND HOUSEKEEPING |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | GV.07 | 3 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 487 | 1461 | MIR # 001 | 3 | 90% | 1314.9 | 0 | 1314.9
125 | 1 1 | Variation Order No.1 dated 17/May/2022 | Laundry Room | LAUNDRY BASEMENT 2 |  | FND-1614-B2-SCH-001-00 |  |  |  | Title Row | No | [5 empty] | Area Title |  | VO # 01 | Description Change | [9 empty] | LAUNDRY BASEMENT 2
126 | 1 1 | Variation Order No.1 dated 17/May/2022 | Laundry Room | LAUNDRY BASEMENT 2 |  | FND-1614-B2-SCH-001-00 |  | LL.00 LOBBY LOUNGE SUPPORT AREAS |  | Title Row | No | [5 empty] | Area Title |  | VO # 01 | Description Change | [9 empty] | LL.00 LOBBY LOUNGE SUPPORT AREAS
127 | 1 1 | Variation Order No.1 dated 17/May/2022 | Laundry Room | LAUNDRY BASEMENT 2 |  | FND-1614-B2-SCH-001-00 |  | LL.00 LOBBY LOUNGE SUPPORT AREAS |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | DL.08 | 1 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 488 | 488 | MIR # 002 | 1 | 90% | 439.2 | 0 | 439.2
128 | 1 1 | Variation Order No.1 dated 17/May/2022 | Laundry Room | BASEMENT 1 |  |  |  | R2.00 REFUSE STORE 2 |  | Check | No | [5 empty] | Building Subtotals |  | VO # 01 | Item No. Change |  |  |  |  | Sub-Total for BASEMENT 1 : |  | Sub-Total for Laundry Room : | [6 empty] | UAE Dirhams | 2437 |  |  |  | 2193.3 | 0 | 2193.3
129 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | GROUND FLOOR |  | FND-1614-GF-FB-SCH-001-001 |  |  |  | Title Row | No | [5 empty] | Building Title |  | VO # 01 | Description Change | [9 empty] | GROUND FLOOR
130 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | GROUND FLOOR |  | FND-1614-GF-FB-SCH-001-001 | BQ.00 | BQ.00 BANQUET KITCHEN AND SUPPORT |  |  | No | [5 empty] | Area Title |  | VO # 01 | Description Change | [9 empty] | BQ.00 BANQUET KITCHEN AND SUPPORT
131 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | GROUND FLOOR |  | FND-1614-GF-FB-SCH-001-001 | BQ.00 | BQ.00 BANQUET KITCHEN AND SUPPORT |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | BQ.06 | 6 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 487 | 2922 | MIR # 002 | 6 | 90% | 2629.8 | 0 | 2629.8
132 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | GROUND FLOOR |  | FND-1614-GF-FB-SCH-001-001 | BQ.00 | BQ.00 BANQUET KITCHEN AND SUPPORT |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | BQ.08 | 1 | No. | Hood type: UV - Wall mount - Wall type - Double skin Hood dimension: 3850 (L) x 1550 (W) x 600 (H) , in 1 section(s) Material: AISI 304, 1.2 mm - Brush Finish Exhaust air: 3269 m3/h Make-up air by Ginox: 0 m3/h - Hood front Lights: Flurorescent panel, 2 unit(s) Drain type: Not applicable | GINOX Hoods | CUSTOM HOOD | U. A. E. | 65610 | 65610 | MIR # 003 | 1 | 90% | 59049 | 0 | 59049
133 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | GROUND FLOOR |  | FND.1614.L4.FB.SCH.001.00 | BQ.00 | BQ.00 BANQUET KITCHEN AND SUPPORT |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | BQ.08.1 | 1 | No. | Incl. 3 x Automated Dampers, 1 x Touchpad (On/Off Control) | GINOX Hoods | CUSTOM | U. A. E. | 15217 | 15217 | MIR # 003 | 1 | 90% | 13695.3 | 0 | 13695.3
134 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | GROUND FLOOR |  | FND-1614-GF-FB-SCH-001-001 | BQ.00 | BQ.00 BANQUET KITCHEN AND SUPPORT |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | BQ.08A | 1 | No. | service distribution unit. 3460 x 200 | PKI / Techsteel | Custom - SDU | U. A. E. | 5826 | 5826 | MIR # 004 | 1 | 90% | 5243.4 | 0 | 5243.4
135 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | GROUND FLOOR |  | FND-1614-GF-FB-SCH-001-001 | BQ.00 | BQ.00 BANQUET KITCHEN AND SUPPORT |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | BQ.08B | 1 | No. | Fire Suppression System | AVENGER | WET CHEMICAL | U. S. A. | 11603 | 11603 |  | 1 | 0% | 0 | 0 | 0
136 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | GROUND FLOOR |  | FND-1614-GF-FB-SCH-001-001 | BQ.00 | BQ.00 BANQUET KITCHEN AND SUPPORT |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | BQ.13 | 1 | No. | Hood type: UV - Wall mount - Wall type - Double skin Hood dimension: 2050 (L) x 1300 (W) x 600 (H) , in 1 section(s) Material: AISI 304, 1.2 mm - Brush Finish Exhaust air: 1339 m3/h Make-up air by Ginox: 0 m3/h - Hood front Lights: Flurorescent panel, 1 unit(s) Drain type: Not applicable | GINOX Hoods | CUSTOM HOOD | U. A. E. | 48151 | 48151 | MIR # 003 | 1 | 90% | 43335.9 | 0 | 43335.9
137 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | GROUND FLOOR |  | FND.1614.L4.FB.SCH.001.00 | BQ.00 | BQ.00 BANQUET KITCHEN AND SUPPORT |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | BQ.13.1 | 1 | No. | Incl. 2 x Automated Dampers, 1 x Touchpad (On/Off Control) | GINOX Hoods | CUSTOM | U. A. E. | 10137 | 10137 | MIR # 003 | 1 | 90% | 9123.3 | 0 | 9123.3
138 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | GROUND FLOOR |  | FND-1614-GF-FB-SCH-001-001 | BQ.00 | BQ.00 BANQUET KITCHEN AND SUPPORT |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | BQ.13A | 1 | No. | Fire Suppression System | AVENGER | WET CHEMICAL | U. S. A. | 0 | INCLUDED IN BQ.08B |  | 1 | 0% | 0 | 0 | 0
139 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | GROUND FLOOR |  | FND-1614-GF-FB-SCH-001-001 | BQ.00 | BQ.00 BANQUET KITCHEN AND SUPPORT |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | BQ.14 | 1 | No. | Coldroom Comprising: | TSSC. | Custom | U. A. E. | 0 | 0 | MIR # 006 | 1 | 90% | 0 | 0 | 0 | INCLUDED IN FL.01
140 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | GROUND FLOOR |  | FND-1614-GF-FB-SCH-001-001 | BQ.00 | BQ.00 BANQUET KITCHEN AND SUPPORT |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | BQ.14A | 1 | No. | Panel Sytem with 2 Single Door | TSSC. | Custom | U. A. E. | 0 | 0 | MIR # 006 | 1 | 90% | 0 | 0 | 0 | INCLUDED IN FL.01
141 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | GROUND FLOOR |  | FND-1614-GF-FB-SCH-001-001 | BQ.00 | BQ.00 BANQUET KITCHEN AND SUPPORT |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | BQ.14B | 1 | No. | Dual Compartment Control Panel | TSSC. | Custom | U. A. E. | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
142 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | GROUND FLOOR |  | FND-1614-GF-FB-SCH-001-001 | BQ.00 | BQ.00 BANQUET KITCHEN AND SUPPORT |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | BQ.14C | 1 | No. | Evaporator (Coldroom 01) | RIVACOLD | MONOBLOCK | ITALY | 6559 | 6559 |  | 1 | 0% | 0 | 0 | 0
143 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | GROUND FLOOR |  | FND-1614-GF-FB-SCH-001-001 | BQ.00 | BQ.00 BANQUET KITCHEN AND SUPPORT |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | BQ.14D | 1 | No. | Evaporator(Coldroom 02) | RIVACOLD | MONOBLOCK | ITALY | 6559 | 6559 |  | 1 | 0% | 0 | 0 | 0
144 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | GROUND FLOOR |  | FND-1614-GF-FB-SCH-001-001 | BQ.00 | BQ.00 BANQUET KITCHEN AND SUPPORT |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | BQ.14E | 1 | No. | Air-Cooled Compressor (Coldroom 01) | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
145 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | GROUND FLOOR |  | FND-1614-GF-FB-SCH-001-001 | BQ.00 | BQ.00 BANQUET KITCHEN AND SUPPORT |  | OK (With Note) | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | BQ.14F | 1 | No. | Air- Cooled Compressor(Coldroom 02) | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
146 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | GROUND FLOOR |  | FND-1614-GF-FB-SCH-001-001 | BQ.00 | BQ.00 BANQUET KITCHEN AND SUPPORT |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | BQ.23 | 2 | No. | Floor drain with stainless steel gratings. 1000 x 300 1200+525 x 300 | PKI / Techsteel | Custom | U. A. E. | 1111 | 2222 | MIR # 002 | 2 | 90% | 1999.8 | 0 | 1999.8
147 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | GROUND FLOOR |  | FND-1614-GF-FB-SCH-001-001 | BQ.00 | BQ.00 BANQUET KITCHEN AND SUPPORT |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | BQ.48 | 1 | No. | Hood type: Steam - Wall mount - Wall type - Single skin Hood dimension: 2000 (L) x 1200 (W) x 600 (H) , in 1 section(s) Material: AISI 304, 1.2 mm - Brush Finish Exhaust air: - m3/h Make-up air by Ginox: 0 m3/h - none Lights: No, 0 unit(s) Drain type: Not applicable | GINOX Hoods | CUSTOM HOOD | U. A. E. | 6188 | 6188 | MIR # 005 | 1 | 90% | 5569.2 | 0 | 5569.2
148 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | GROUND FLOOR |  |  |  | ADDITIONAL UNIT |  | Title Row | No | [5 empty] | Area Title |  | VO # 01 | Description Change | [9 empty] | ADDITIONAL UNIT
149 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | GROUND FLOOR |  |  |  | ADDITIONAL UNIT |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | 1 | 1 | Lot | FLOOR PANEL Floor panels constructed from 100 mm thick Rigid injected CFC free polyurethane foam finished with 1.4 mm thick AISI 304 stainless steel chequered plate on top, and 0.7 mm thick pre-painted GI sheet on unexposed side below. Overall sizes as per individual cold rooms listed above. | TSSC.. | Custom | U. A. E. | 135840 | 135840 |  | 1 | 0% | 0 | 0 | 0
150 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | GROUND FLOOR |  |  |  | ADDITIONAL UNIT |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | 2 | 1 | Lot | FIRE SUPPRESSION SYSTEM PRE PIPING | AVENGER | CUSTOM | U. S. A. | 25251 | 25251 |  | 1 | 0% | 0 | 0 | 0
151 | 1 1 | Variation Order No.1 dated 17/May/2022 | Laundry Room | GROUND FLOOR |  |  |  | R2.00 REFUSE STORE 2 |  | Check | No | [5 empty] | Building Subtotals |  | VO # 01 | Item No. Change |  |  |  |  | Sub-Total for GROUND FLOOR : |  | Sub-Total for Ground Floor : | [6 empty] | UAE Dirhams | 342085 |  |  |  | 140645.7 | 0 | 140645.7
152 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 2 |  | FND.1614.02.FB.SCH.001.00 | LP.00 | LP.00 LOBBY PATISSERIE |  | Title Row | No | [5 empty] | Building Title | [12 empty] | LEVEL 2
153 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 2 |  | FND.1614.02.FB.SCH.001.00 | LP.00 | LP.00 LOBBY PATISSERIE |  | Title Row | No | [5 empty] | Area Title | [12 empty] | LP.00 LOBBY PATISSERIE
154 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 2 |  | FND.1614.02.FB.SCH.001.00 | LP.00 | LP.00 LOBBY PATISSERIE |  | OK (With Note) | No | [15 empty] | LP.01 | 1 | No. | Refrigerated Display Counter | GINOX | Custom | U. A. E. | 0 | INCLUDED IN LP.01A |  | 1 | 0% | 0 | 0 | 0
155 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 2 |  | FND.1614.02.FB.SCH.001.00 | LP.00 | LP.00 LOBBY PATISSERIE |  | OK | No | [15 empty] | LP.01A | 1 | No. | Refrigerated venitlated display for cakes 1060 x 800 x 1200 Finishes on the front fascia, sides and stone not to be included within this package Remote compressor to be located within 20 lineal meters (excluded) | GINOX Refri. | DISPLAY | U. A. E. | 46685 | 46685 |  | 1 | 0% | 0 | 0 | 0
156 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 2 |  | FND.1614.02.FB.SCH.001.00 | LP.00 | LP.00 LOBBY PATISSERIE |  | OK (With Note) | No | [15 empty] | LP.01B | 1 | No. | Refrigerated venitlated display for cakes 1060 x 800 x 1200 Finishes on the front fascia, sides and stone not to be included within this package Remote compressor to be located within 20 lineal meters (excluded) | GINOX Refri. | DISPLAY | U. A. E. | 0 | INCLUDED IN LP.01A |  | 1 | 0% | 0 | 0 | 0
157 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 2 |  | FND.1614.02.FB.SCH.001.00 | LP.00 | LP.00 LOBBY PATISSERIE |  | OK | No | [15 empty] | LP.01C | 1 | No. | Work counter with: * Closed storage cabinet with shelf, * Void under. Excludes: Front fascia and any decorative/joinery works. 2200 x 800 x 900 | GINOX | Custom | U. A. E. | 11163 | 11163 |  | 1 | 0% | 0 | 0 | 0
158 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 2 |  | FND.1614.02.FB.SCH.001.00 | LP.00 | LP.00 LOBBY PATISSERIE |  | OK (With Note) | No | [15 empty] | LP.01D | 1 | No. | Undercounter refrigerator with two sets of two drawers 1350 x 660 x 780 | GINOX Refri. | Custom | U. A. E. | 0 | INCLUDED IN LP.01A |  | 1 | 0% | 0 | 0 | 0
159 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 2 |  | FND.1614.02.FB.SCH.001.00 | LP.00 | LP.00 LOBBY PATISSERIE |  | OK (With Note) | No | [15 empty] | LP.01E | 1 | No. | Closed storage cabinet with shelf | GINOX | Custom | U. A. E. | 0 | INCLUDED IN LP.01C |  | 1 | 0% | 0 | 0 | 0
160 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 2 |  | FND.1614.02.FB.SCH.001.00 | LP.00 | LP.00 LOBBY PATISSERIE |  | OK | No | [15 empty] | LP.02 | 1 | No. | Work counter with: * 3 x Utensil drawer with closed storage cabinet, * Service riser. Excludes: Front fascia and any decorative/joinery works. 1810 x 445 x 900 | GINOX | Custom | U. A. E. | 15396 | 15396 |  | 1 | 0% | 0 | 0 | 0
161 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 2 |  | FND.1614.02.FB.SCH.001.00 | LP.00 | LP.00 LOBBY PATISSERIE |  | OK | No | [15 empty] | LP.03 | 1 | No. | Pastry Working Counter with: * 1 x Utensil drawer with closed storage cabinet, * Void under. Excludes: Front fascia and any decorative/joinery works. 1715 x 750 x 900 | GINOX | Custom | U. A. E. | 7021 | 7021 |  | 1 | 0% | 0 | 0 | 0
162 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 2 |  | FND.1614.02.FB.SCH.001.00 | LP.00 | LP.00 LOBBY PATISSERIE |  | OK | No | [15 empty] | LP.03A | 1 | No. | Two doors biscuit top chiller 1/1GN with remote condensing unit, digital temperature display and controller Temperature ‐2ᵒC to +8ᵒC Interior and exterior in stainless steel Silicone gaskets Technical compartment on the right side and two sets of two drawers Remote compressor to be located at 30 lineal meters Dim: 1150 x 660 x 780 Remote compressor to be located within 20 lineal meters (excluded) | GINOX Refri. | CB721‐HD‐HD | U. A. E. | 12272 | 12272 |  | 1 | 0% | 0 | 0 | 0
163 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 2 |  | FND.1614.02.FB.SCH.001.00 | LP.00 | LP.00 LOBBY PATISSERIE |  | OK (With Note) | No | [15 empty] | LP.03B | 1 | No. | Utensil drawer with closed storage cabinet | GINOX | Custom | U. A. E. | 0 | INCLUDED IN LP.03 |  | 1 | 0% | 0 | 0 | 0
164 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 2 |  | FND.1614.02.FB.SCH.001.00 | LP.00 | LP.00 LOBBY PATISSERIE |  | OK | No | [15 empty] | LP.06 | 1 | No. | Work counter with: * 1 x WHB, * 1 x Waste bin cabinet, * Open storage cabinet. 1640 x 490 x 900 | GINOX | Custom | U. A. E. | 10136 | 10136 |  | 1 | 0% | 0 | 0 | 0
165 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 2 |  | FND.1614.02.FB.SCH.001.00 | LP.00 | LP.00 LOBBY PATISSERIE |  | OK | No | [15 empty] | LP.08 | 1 | No. | Work counter with: * 1 x Utility sink, * 1 x Waste bin cabinet, * 1 x Knock out drawer with closed cabinet * Closed storage cabinet, * Void under. 2990+735 x 640 x 900 | GINOX | Custom | U. A. E. | 17360 | 17360 |  | 1 | 0% | 0 | 0 | 0
166 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 2 |  | FND.1614.02.FB.SCH.001.00 | LP.00 | LP.00 LOBBY PATISSERIE |  | OK | No | [15 empty] | LP.14 | 1 | No. | Run of Heated, Chilled and Ambient Cupboards | GINOX | Custom | U. A. E. | 57732 | 57732 |  | 1 | 0% | 0 | 0 | 0
167 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | LEVEL 2 |  | FND.1614.02.FB.SCH.001.00 | TB.00 | TB.00 TERRACE BAR |  |  | No | [5 empty] | Area Title |  | VO # 01 | Description Change | [9 empty] | TB.00 TERRACE BAR
168 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | LEVEL 2 |  | FND.1614.02.FB.SCH.001.00 | TB.00 | TB.00 TERRACE BAR |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | TB.05 | 2 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 488 | 976 | MIR # 002 | 2 | 90% | 878.4 | 0 | 878.4
169 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | LEVEL 2 |  | FND.1614.02.FB.SCH.001.00 | SBP.00 | SBP.00 SECRET BAR PANTRY |  |  | No | [5 empty] | Area Title |  | VO # 01 | Description Change | [9 empty] | SBP.00 SECRET BAR PANTRY
170 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | LEVEL 2 |  | FND.1614.02.FB.SCH.001.00 | SBP.00 | SBP.00 SECRET BAR PANTRY |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | SBP.08 | 1 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 488 | 488 | MIR # 002 | 1 | 90% | 439.2 | 0 | 439.2
171 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | LEVEL 2 |  | FND.1614.02.FB.SCH.001.00 | LL.00 | LL.00 LOBBY LOUNGE SUPPORT PANTRY |  |  | No | [5 empty] | Area Title |  | VO # 01 | Description Change | [9 empty] | LL.00 LOBBY LOUNGE SUPPORT PANTRY
172 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | LEVEL 2 |  | FND.1614.02.FB.SCH.001.00 | LL.00 | LL.00 LOBBY LOUNGE SUPPORT PANTRY |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | LL.04 | 1 | No. | Floor drain with stainless steel gratings. 1200+525 x 300 | PKI / Techsteel | Custom | U. A. E. | 1446 | 1446 | MIR # 002 | 1 | 90% | 1301.4 | 0 | 1301.4
173 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | LEVEL 2 |  | FND.1614.02.FB.SCH.001.00 | LL.00 | LL.00 LOBBY LOUNGE SUPPORT PANTRY |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | LL.16 | 3 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 487 | 1461 | MIR # 002 | 3 | 90% | 1314.9 | 0 | 1314.9
174 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | LEVEL 2 |  | FND.1614.02.FB.SCH.001.00 | LL.00 | LL.00 LOBBY LOUNGE SUPPORT PANTRY |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | LL.22 | 1 | No. | Hood type: Steam - Wall mount - Wall type - Single skin Hood dimension: 1000 (L) x 1000 (W) x 600 (H) , in 1 section(s) Material: AISI 304, 1.2 mm - Brush Finish Exhaust air: 1350 m3/h Make-up air by Ginox: 0 m3/h - none Lights: No, 0 unit(s) Drain type: Not applicable | GINOX Hoods | CUSTOM HOOD | U. A. E. | 4089 | 4089 | MIR # 005 | 1 | 90% | 3680.1 | 0 | 3680.1
175 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | LEVEL 2 |  | FND.1614.L4.FB.SCH.001.00 | LL.00 | LL.00 LOBBY LOUNGE SUPPORT PANTRY |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | LL.46 | 1 | No. | Services Distribution Unit with Potshelf and panels | PKI / Techsteel | Custom - SDU | U. A. E. | 8781 | 8781 |  | 1 | 0% | 0 | 0 | 0
176 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | LEVEL 2 |  | FND.1614.02.FB.SCH.001.00 | LL.00 | LL.00 LOBBY LOUNGE SUPPORT PANTRY |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | LL.49 | 1 | No. | Hood type: UV - Wall mount - Wall type - Double skin Hood dimension: 3800 (L) x 1265 (W) x 600 (H) , in 1 section(s) Material: AISI 304, 1.2 mm - Brush Finish Exhaust air: 3700 m3/h Make-up air by Ginox: 3145 m3/h - Hood front Lights: Flurorescent panel, 2 unit(s) Drain type: Not applicable | GINOX Hoods | CUSTOM HOOD | U. A. E. | 64400 | 64400 |  | 1 | 0% | 0 | 0 | 0
177 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | LEVEL 2 |  | FND.1614.L4.FB.SCH.001.00 | LL.00 | LL.00 LOBBY LOUNGE SUPPORT PANTRY |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | LL.49.1 | 1 | No. | Incl. 3 x Automated Dampers, 1 x Touchpad (On/Off Control) | GINOX Hoods | CUSTOM | U. A. E. | 15197 | 15197 |  | 1 | 0% | 0 | 0 | 0
178 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | LEVEL 2 |  | FND.1614.02.FB.SCH.001.00 | LL.00 | LL.00 LOBBY LOUNGE SUPPORT PANTRY |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | LL.49A | 1 | No. | Fire Suppression System | AVENGER | WET CHEMICAL | U. S. A. | 7890 | 7890 |  | 1 | 0% | 0 | 0 | 0
179 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 2 |  | FND.1614.02.FB.SCH.001.00 | LP.00 | LP.00 LOBBY PATISSERIE |  | Check | No | [5 empty] | Building Subtotals | [7 empty] | Sub-Total for LEVEL 2 : |  | Sub-Total for LEVEL 2 : | [6 empty] | UAE Dirhams | 282493 |  |  |  | 7614 | 0 | 7614
180 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | RS.00 | RS.00 ROOM SERVICE BOH |  | Title Row | No | [5 empty] | Building Title |  | VO # 01 | Description Change | [9 empty] | LEVEL 4
181 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | RS.00 | RS.00 ROOM SERVICE BOH |  | Title Row | No | [5 empty] | Area Title |  | VO # 01 | Description Change | [9 empty] | RS.00 ROOM SERVICE BOH
182 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | RS.00 | RS.00 ROOM SERVICE BOH |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | RS.24 | 4 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 487 | 1948 | MIR # 002 | 4 | 90% | 1753.2 | 0 | 1753.2
183 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | RS.00 | RS.00 ROOM SERVICE BOH |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | RS.27 | 1 | No. | Hood type: UV - Wall mount - Wall type - Double skin Hood dimension: 4500 (L) x 1050 (W) x 600 (H) , in 2 section(s) Material: AISI 304, 1.2 mm - Brush Finish Exhaust air: 4310 m3/h Make-up air by Ginox: 3664 m3/h - Hood front Lights: Flurorescent panel, 2 unit(s) Drain type: Not applicable | GINOX Hoods | CUSTOM HOOD | U. A. E. | 70146 | 70146 |  | 1 | 0% | 0 | 0 | 0
184 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | RS.00 | RS.00 ROOM SERVICE BOH |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | RS.27.1 | 1 | No. | Incl. 4 x Automated Dampers, 1 x Touchpad (On/Off Control) | GINOX Hoods | CUSTOM | U. A. E. | 20259 | 20259 |  | 1 | 0% | 0 | 0 | 0
185 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | RS.00 | RS.00 ROOM SERVICE BOH |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | RS.27A | 1 | No. | Fire Suppression System | AVENGER | WET CHEMICAL | U. S. A. | 11603 | 11603 |  | 1 | 0% | 0 | 0 | 0
186 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | RS.00 | RS.00 ROOM SERVICE BOH |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | RS.27B | 1 | No. | Service distribution unit. 3950 x 200 | PKI / Techsteel | Custom - SDU | U. A. E. | 6650 | 6650 |  | 1 | 0% | 0 | 0 | 0
187 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | RS.00 | RS.00 ROOM SERVICE BOH |  | Check | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | RS.27C | 1 | No. | Demand control: Incl. 0 automated damper(s), 1 pair(s) optical sensors, 2 temp. sensor(s). |  |  |  | 0 | DELETED |  |  | 0 | 0 | 0 | 0
188 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | ADK.00 | ADK.00 ALL DAY DNING KITCHEN |  | Title Row | No | [5 empty] | Area Title |  | VO # 01 | Description Change | [9 empty] | ADK.00 ALL DAY DNING KITCHEN
189 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | ADK.00 | ADK.00 ALL DAY DNING KITCHEN |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | ADK.07 | 3 | No. | Floor drain with stainless steel gratings. 900 x 300 1200 X 250 | PKI / Techsteel | Custom | U. A. E. | 821 | 2463 | MIR # 002 | 3 | 90% | 2216.7 | 0 | 2216.7
190 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | ADK.00 | ADK.00 ALL DAY DNING KITCHEN |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | ADK.09 | 1 | No. | Hood type: Steam - Wall mount - Wall type - Single skin Hood dimension: 1025 (L) x 990 (W) x 600 (H) , in 1 section(s) Material: AISI 304, 1.2 mm - Brush Finish Exhaust air: 600 m3/h Make-up air by Ginox: 0 m3/h - none Lights: No, 0 unit(s) Drain type: Not applicable | GINOX Hoods | CUSTOM HOOD | U. A. E. | 4142 | 4142 |  | 1 | 0% | 0 | 0 | 0
191 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | ADK.00 | ADK.00 ALL DAY DNING KITCHEN |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | ADK.14 | 3 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 487 | 1461 | MIR # 002 | 3 | 90% | 1314.9 | 0 | 1314.9
192 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | ADK.00 | ADK.00 ALL DAY DNING KITCHEN |  | OK | No | [15 empty] | ADK.48 | 1 | No. | Stone Hearth Oven | Clay Oven | Bespoke | U. K. | 140235 | 140235 |  | 1 | 0% | 0 | 0 | 0
193 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | ADK.00 | ADK.00 ALL DAY DNING KITCHEN |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | ADK.49 | 1 | No. | Hood type: Water Mist Wash - Island mount - Island type - Double skin Hood dimension: 3950 (L) x 2350 (W) x 600 (H) , in 2 section(s) Material: AISI 304, 1.2 mm - Brush Finish Exhaust air: 10670 m3/h Make-up air by Ginox: 9072 m3/h - Hood front Lights: LED spot, 12 unit(s) Drain type: Gravity Note: Special finishes as per consultant specifications | GINOX Hoods | CUSTOM HOOD | U. A. E. | 136483 | 136483 |  | 1 | 0% | 0 | 0 | 0
194 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | ADK.00 | ADK.00 ALL DAY DNING KITCHEN |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | ADK.49.1 | 1 | No. | Incl. 4 x Automated Dampers, 1 x Touchpad (On/Off Control) | GINOX Hoods | CUSTOM | U. A. E. | 20259 | 20259 |  | 1 | 0% | 0 | 0 | 0
195 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | ADK.00 | ADK.00 ALL DAY DNING KITCHEN |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | ADK.49a | 1 | No. | Fire Suppression System | AVENGER | WET CHEMICAL | U. S. A. | 15316 | 15316 |  | 1 | 0% | 0 | 0 | 0
196 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | ADK.00 | ADK.00 ALL DAY DNING KITCHEN |  | Check | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | ADK.49b | 1 | No. | Demand control: Incl. 0 automated damper(s), 2 pair(s) optical sensors, 4 temp. sensor(s). |  |  |  | 0 | DELETED |  |  | 0 | 0 | 0 | 0
197 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | ADK.00 | ADK.00 ALL DAY DNING KITCHEN |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | ADK.55 | 1 | No. | Hood type: Steam - Wall mount - Wall type - Single skin Hood dimension: 2165 (L) x 900 (W) x 600 (H) , in 1 section(s) Material: AISI 304, 1.2 mm - Brush Finish Exhaust air: 918 m3/h Make-up air by Ginox: 0 m3/h - none Lights: No, 0 unit(s) Drain type: Not applicable | GINOX Hoods | CUSTOM HOOD | U. A. E. | 6541 | 6541 | MIR # 005 | 1 | 90% | 5886.9 | 0 | 5886.9
198 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | ADK.00 | ADK.00 ALL DAY DNING KITCHEN |  | OK | No | [15 empty] | ADK.56a | 2 | No. | Refrigerated ventilated vertical display for wine Composed of : Nr. 2 units with two doors, Nr. 1 unit with one door Special shelves for wine bottles, Remote compressor to be located within 20 lineal meters (excluded), No cladding, Internal mirror finish, Dimmable lighting 2700 x 550 x 2000 (As per drawings) | GINOX Refri. | DISPLAY | U. A. E. | 160170 | 320340 |  | 2 | 0% | 0 | 0 | 0
199 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | ADK.00 | ADK.00 ALL DAY DNING KITCHEN |  | OK | No | [8 empty] | Description Change | [6 empty] | ADK.56b | 1 | No. | Vertical Ambient display for wine Composed of : Nr. 2 units with two doors, Nr. 1 unit with one door Special shelves for wine bottles, No cladding Internal mirror finish, Dimmable lighting 2700 x 550 x 2000, (As per drawings) Finishes on the front fascia, sides and stone not to be included within this package Remote compressor to be located within 20 lineal meters (excluded) | GINOX Refri. | DISPLAY | U. A. E. | 101303 | 101303 |  | 1 | 0% | 0 | 0 | 0
200 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | ADK.00 | ADK.00 ALL DAY DNING KITCHEN |  | OK | No | [8 empty] | Description Change | [6 empty] | ADK.57 | 1 | No. | Display Ambient for wine Composed of : Nr. 1 units with 3 doors, Special shelves for wine bottle Special handles, No cladding, Internal mirror finish Dimmable lighting, 1600 x 550 x 2000 (As per drawings) Finishes on the front fascia, sides and stone not to be included within this package Remote compressor to be located within 20 lineal meters (excluded) | GINOX Refri. | DISPLAY | U. A. E. | 56029 | 56029 |  | 1 | 0% | 0 | 0 | 0
201 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | CB.00 | CB.00 CAFÉ BAR |  | Title Row | No | [5 empty] | Area Title |  | VO # 01 | Description Change | [9 empty] | CB.00 CAFÉ BAR
202 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | CB.00 | CB.00 CAFÉ BAR |  | OK | No | [15 empty] | CB.01 | 1 | No. | Kombucha Dispenser | KEGCO | KOM20S-1 | U. S. A. | 7205 | 7205 |  | 1 | 0% | 0 | 0 | 0
203 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | CB.00 | CB.00 CAFÉ BAR |  | OK | No | [15 empty] | CB.05 | 1 | No. | Nitro Cold Brew Dispenser With Filter | KEGCO | K163S-2 | U. S. A. | 9181 | 9181 |  | 1 | 0% | 0 | 0 | 0
204 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | CB.00 | CB.00 CAFÉ BAR |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | CB.11 | 1 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 488 | 488 | MIR # 002 | 1 | 90% | 439.2 | 0 | 439.2
205 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | CB.00 | CB.00 CAFÉ BAR |  | OK | No | [15 empty] | CB.15 | 1 | No. | 4 WELL ICE CREAM CHURNER | Carpigiani | CC400 | ITALY | 70779 | 70779 |  | 1 | 0% | 0 | 0 | 0
206 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | CB.00 | CB.00 CAFÉ BAR |  | OK | No | [15 empty] | CB.16 | 1 | No. | Double door bottle cooler (two sets of two drawers) with digital temperature display and controller Dim: 900 x 505 x 840 | GINOX Refri. | CF | U. A. E. | 10868 | 10868 |  | 1 | 0% | 0 | 0 | 0
207 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | CB.00 | CB.00 CAFÉ BAR |  | OK | No | [15 empty] | CB.17 | 1 | No. | Refrigerated ventilated display 700 x 500 x 1200 Finishes on the front fascia, sides and stone not to be included within this package Remote compressor to be located within 20 lineal meters (excluded) | GINOX Refri. | DISPLAY | U. A. E. | 18117 | 18117 |  | 1 | 0% | 0 | 0 | 0 | Item deleted
208 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | CB.00 | CB.00 CAFÉ BAR |  | OK | No | [15 empty] | CB.18 | 1 | No. | Hot display 700 x 500 x 1200 Finishes on the front fascia, sides and stone not to be included within this package | GINOX Refri. | DISPLAY | U. A. E. | 12078 | 12078 |  | 1 | 0% | 0 | 0 | 0 | Item deleted
209 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | CB.00 | CB.00 CAFÉ BAR |  | OK | No | [15 empty] | CB.19 | 1 | No. | "U" shaped bar counter with: * 1 x WHB, * 2 x Utility sink with closed storage cabinet, * 1 x Cutting board, * 1 x Cashier station, * Cocktail station with insulated ice well with sliding lids, partation and perforated false bottom. Unit to have condiment well to rear and speed rail to front, * Recessed blender station, * Closed storage cabinet with shelf, * Void under. Excludes: Front fascia and any decorative/joinery works. 5000+1100+5000 x 600 x 900 | GINOX | Custom | U. A. E. | 118616 | 118616 |  | 1 | 0% | 0 | 0 | 0
210 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | CB.00 | CB.00 CAFÉ BAR |  | OK (With Note) | No | [15 empty] | CB.19a | 1 | No. | Preparation Counter with inset cutting boards | GINOX | Custom | U. A. E. | 0 | included in CB.19 |  | 1 | 0% | 0 | 0 | 0
211 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | CB.00 | CB.00 CAFÉ BAR |  | OK (With Note) | No | [15 empty] | CB.19b | 1 | No. | Wash Hand Station | GINOX | Custom | U. A. E. | 0 | included in CB.19 |  | 1 | 0% | 0 | 0 | 0
212 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | CB.00 | CB.00 CAFÉ BAR |  | OK (With Note) | No | [15 empty] | CB.19c | 1 | No. | Panelled Recess for Undercounter Refrigerator | GINOX | Custom | U. A. E. | 0 | included in CB.19 |  | 1 | 0% | 0 | 0 | 0
213 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | CB.00 | CB.00 CAFÉ BAR |  | OK (With Note) | No | [15 empty] | CB.19d | 1 | No. | Panelled Recess for Ice Cream Unit | GINOX | Custom | U. A. E. | 0 | included in CB.19 |  | 1 | 0% | 0 | 0 | 0
214 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | CB.00 | CB.00 CAFÉ BAR |  | OK (With Note) | No | [15 empty] | CB.19e | 1 | No. | Recessed Worktop for Equipment | GINOX | Custom | U. A. E. | 0 | included in CB.19 |  | 1 | 0% | 0 | 0 | 0
215 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | CB.00 | CB.00 CAFÉ BAR |  | OK (With Note) | No | [15 empty] | CB.19f | 1 | No. | Ice Well with Double Speed Rail | GINOX | Custom | U. A. E. | 0 | included in CB.19 |  | 1 | 0% | 0 | 0 | 0
216 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | CB.00 | CB.00 CAFÉ BAR |  | OK (With Note) | No | [15 empty] | CB.19g | 1 | No. | Recessed Worktop for Equipment | GINOX | Custom | U. A. E. | 0 | included in CB.19 |  | 1 | 0% | 0 | 0 | 0
217 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | CB.00 | CB.00 CAFÉ BAR |  | OK (With Note) | No | [15 empty] | CB.19h | 1 | No. | Panelled Recess for Waste Bin | GINOX | Custom | U. A. E. | 0 | included in CB.19 |  | 1 | 0% | 0 | 0 | 0
218 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | CB.00 | CB.00 CAFÉ BAR |  | OK (With Note) | No | [15 empty] | CB.19i | 1 | No. | Sink Bowl with Shelf Under | GINOX | Custom | U. A. E. | 0 | included in CB.19 |  | 1 | 0% | 0 | 0 | 0
219 | 1 1 | Main Contract | Foodservice Equipment | LEVEL 4 |  | FND.1614.L4.FB.SCH.001.00 | CB.00 | CB.00 CAFÉ BAR |  | OK (With Note) | No | [15 empty] | CB.19j | 1 | No. | Panelled Recess for Ice Machine | GINOX | Custom | U. A. E. | 0 | included in CB.19 |  | 1 | 0% | 0 | 0 | 0
220 | 1 1 | Variation Order No.1 dated 17/May/2022 | Hoods, Fire Suppression, Coldrooms, and Floor Grating | BASEMENT 1 |  |  |  | R2.00 REFUSE STORE 2 |  | Check | No | [5 empty] | Building Subtotals |  | VO # 01 | [5 empty] | Sub-Total for BASEMENT 1 : |  | Sub-Total for Level 4 : | [6 empty] | UAE Dirhams | 1162510 |  |  |  | 11610.9 | 0 | 11610.9
221 | 1 1 | Variation Order No.1 dated 17/May/2022 | Remote Condensing Unit |  |  |  |  | Remote Condensing Unit |  | Title Row | No | [5 empty] | Building Title |  | VO # 01 | Description Change | [9 empty] | Remote Condensing Unit of Display Refrigeration as per the quotation ref: Ref: DCD/KLE/13A20/HP/MTS/BOQ013Pkg.1 a
222 | 1 1 | Variation Order No.1 dated 17/May/2022 | Remote Condensing Unit |  |  |  |  | Remote Condensing Unit |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | RCU-01 | 1 | Lot | Supply and Installation of the Remote Condensing Unit for the following item, where the limit of piping would be of 20 Meter. Level 4 ADK.56a Refrigerated ventilated vertical display for wine ADK.56b Vertical display for wine ADK.57 Display for wine CB.17 Refrigerated ventilated display Level 2 LP.01A Refrigerated venitlated display for cakes LP.01B Refrigerated venitlated display for cakes | GINOX Refri.. | Custom | U. A. E. | 101877 | 101877 |  | 1 | 0% | 0 | 0 | 0
223 | 1 1 | Variation Order No.1 dated 17/May/2022 | Design Charges |  |  |  |  | Design Charges |  | Title Row | No | [5 empty] | Building Title |  | VO # 01 | Description Change | [9 empty] | Design Charges - Engineering Work, Quotation Ref: VQTE-0002-HP-DCD-EW/KL/P1-27D21-JA-02
224 | 1 1 | Variation Order No.1 dated 17/May/2022 | Design Charges |  |  |  |  | Design Charges |  | OK | No | [7 empty] | VO # 01 | Item No. Change | [6 empty] | DC-01 | 1 | Lot | Scope of Engineering Work: (As per work completed under RPJV before change in scope) 1. Material Submittal for Approval 2. Shop Drawings including Equipment Layout & MEP Requirements in 2D 3. Coordination of drawings with Main Contractor | TSSC Dubai | Service | U. A. E. | 35000 | 35000 |  | 1 | 0% | 0 | 0 | 0
225
226
227 | 1 1 | [9 empty] | - |  |  |  |  | - | Building Subtotals | [7 empty] | Total For Food Service Equipment In All Areas As Listed (Installed & Commissioned) : |  | Grand Total For Kitchen Equipment In All Areas As Listed (Installed & Commissioned) : | [6 empty] | UAE Dirhams | 3402503 |  |  |  | 280147.88 | 0 | 280147.88
[27 empty] | Special Discount | [6 empty] | UAE Dirhams | -18821 |  |  | 8.234% | -1549.6425 | 0 | -1549.6425
[27 empty] | Total Amount After Discount | [6 empty] | UAE Dirhams | 3383682 |  |  |  | 278598.2375 | 0 | 278598.2375
[27 empty] | VAT 5% | [6 empty] | UAE Dirhams | 169184.1 |  |  |  | 13929.9119 | 0 | 13929.9119
[27 empty] | Grand Total | [6 empty] | UAE Dirhams | 3552866.1 |  |  |  | 292528.1494 | 0 | 292528.1494
(Three Million, Five Hundred and Fifty Two Thousand, Eight Hundred and Sixty Six UAE Dirhams)