## Annexure-5 Plant Summary
Sky Palaces Real Estate Development LLC
Annexure 5 - Breakdown of Plant Cost
Project: | Plot - 18 |  | Certificate Date:
Contractor: | Khansaheb Civil Engineering LLC |  | Certificate No:
Contract : | Base Build Works |  | Currency: | AED
Sn | KCE IPA Section Description | Previous | This Month | Cumulative
1 | General Preliminaries | 3259416.37 | 567678.27 | 3827094.64
2 | RPJV Debt Payments | 440610.35 | 0 | 440610.35
3 | Civil Work | 0 | 0 | 0
4 | Adjustments | 0 | 0 | 0
| TOTAL | 3700026.72 | 567678.27 | 4267704.99

## Cost Breakdown
No. | Plant Description | Unit | Rate | 2022-04-01 |  | 2022-05-01 |  | 2022-06-01 |  | 2022-07-01 |  | 2022-08-01 |  | 2022-09-01 |  | 2022-10-01 |  | 2022-11-01 |  | 2022-12-01 |  | 2023-01-01 |  | 2023-02-01 |  | 2023-03-01
|  |  |  | QTY | Amount | QTY | Amount | QTY | Amount | QTY | Amount | QTY | Amount | QTY | Amount | QTY | Amount | QTY | Amount | QTY | Amount | QTY | Amount | QTY | Amount | QTY | Amount
GENERATORS
01 | 142039,P, Generator - 650 KVA-Working | Hrs | 42.31 |  |  | 700 | 29617 | 300 | 13961 | 40 | 1692.4 | 590 | 24961.63 | 329.9832 | 13961.59 |  |  |  | 24538.55 |  | 73615.63 |  | 24538.55 |  | 23692.4 |  |  | 84193.62
02 | 142039,P, Generator - 500 KVA-Working | Hrs | 31.16 |  |  | 350 | 10906 | 330 | 9346 | 40 | 1246.4 | 590 | 18381.62 | 329.9503 | 10281.25 |  |  |  | 23147.05 |  | 27069.18 |  | 9346.59 |  | 8723.48 |  |  | 50161.27
03 | 142039,P, Generator - 350 KVA-Working | Hrs | 29.62 |  |  | 480 | 14217.6 | 370 | 10959.4 | 40 | 1184.8 | 190 | 5627.8 | 0 | [13 empty] | 31989.6
04 | Generator Cables (1C 240mm2 40Mtr x 30 Runs = 1200 Mtrs) | Hrs | 38.08 |  |  |  | 13327 |  |  | 0 |  | 840 | 31985.21 | 329.979 | 12565.6 |  |  |  | 22084.99 |  | 12565.6 |  | 11423.27 |  | 10661.72 |  |  | 57877.81
05 | CAT & Ginny Cable Locator M/Kit | Days | 18 |  |  |  | 0 | 26 | 468 | 26 | 468 | 27 | 486 | 26 | 468 | 26 | 468 |  | 468 |  | 486 |  | 468 |  | 432 |  |  | 2358
CRANES
06 | Derrick Crane - 12 Ton Capacity | [17 empty] | 42308.23 |  | 32788.88 |  | 31731.17 |  | 29615.76
07 | Derrick Crane - 5 Ton Capacity | Hrs | 93.08 |  |  |  | 64900 | 510 | 47470.8 | 30 | 2792.4 | 510 | 47470.8 | 279.9929 | 26061.74 |  |  |  | 46538.83 |  | 26061.74 |  | 24200.19 |  | 26061.72 |  |  | 226580.3
08 | Mobile Crane - 100 Ton | Hrs | 330 |  |  |  | 1246 |  |  |  |  | 10 | 3300 | 0 |  |  |  |  | 3300 |  |  |  | 3850 |  | 6050
09 | Mobile Crane - 70 Ton | [19 empty] | 21450
10 | Mobile Crane - 50 Ton | [17 empty] | 2640
11 | Mercedes Truck With Crane With IVMS | Days | 620 |  |  |  | 0 |  | 620 |  | 0 | 3 | 1860 | 0 |  |  |  |  | 2480
12 | Nissan Truck with Hiab Crane With IVMS | Days | 385 |  |  |  | 0 |  | 620 |  | 0 | 4 | 1540 | 2 | 770 | 3 | 2695 |  | 1544.8 |  | 3473.64 |  | 8093.64 |  | 3465 |  |  | Mini Floor Crane (Oslar Boy)
13 | Mini Crane (JEKKO SPX532) - 3.2 Ton | L | 660 | [10 empty] | 14.5 | 9570 | 1 | 660 |  | 30030 |  | 2200
14 | Mini Floor Crane (Oslar Boy) | [17 empty] | 1466.74 |  | 6050.55 |  | 60.51
| Jekko Mini Picker-1000kg | [19 empty] | 8275.41 |  | 12184.64 |  | 2538.47
| Mini Crane - 4 TON (URW547) | [21 empty] | 50270.99 |  | 44000.88
| Derrick Crane 2 Ton | [23 empty] | 3300.04
VANS & BUSES
15 | TOYOTA COASTER HI ROOF 23STR 4.0D MANUAL | Month | 4680 |  | 2307.95 |  | 4680 | 1 | 4680 | 1 | 4680 | 1 | 4680 | 1 | 4680 | 1 | 4680 |  | 4680 |  | 4680 |  | 9142.03 |  | 9360
16 | TOYOTA HIACE 13 SEAT BUS | Month | 3380 |  |  |  | 2666.66 | 1 | 3380 | 1 | 3380 | 1 | 3380 | 1 | 3380 | 1 | 3380 |  | 3380 |  | 3380 |  | 222.25
17 | Ashok Leyland Bus - DXB 85148H | Month | 5110 |  |  |  | 4368 | 0.59 | 3024 |  | 5040 | 1 | 5110 | 1 | 5110 | 1 | 5110 |  | 5110 |  | 5110 |  | 5110 |  | 41714
18 | Ashok Leyland Bus - DXB 86783H With IVMS | Month | 5110 |  |  |  | 0 | 0.39 | 2016 |  | 0 | 0.07 | 672 | 0.39452 | 2016 | 1 | 5110 |  | 5110 |  | 5110 |  | 4368
19 | Ashok Leyland Bus - DXB 87476H | Month | 5110 | [6 empty] | 0.36 | 1848 | -0.2 | -1008 | 0
20 | Ashok Leyland 71 Seat Bus | Month | 5850 |  |  |  | 0 | 0.72 | 4231.23 | 1 | 5850 | 1 | 5850 | 1 | 5850 | 1 | 5850 |  | 5850 |  | 5850 |  | 5850
21 | Ashok Leyland Bus - DXB 86848H | Month | 5110 |  |  | 0.39 | 2016 | 0.0658 | 336.238 | 0.03 | 1512 | 1 | 5110 | 1 | 5110 | 1 | 5110 |  | 5044 |  | 5110 |  | 5110
22 | Ashok Leyland Bus - DXB 52753J | Month | 5110 | [6 empty] | 0.62 |  | 0.92 | 4704 | 1 | 5110 | 1 | 5110 |  | 5110 |  | 3360 |  | 5110
23 | Ashok Leyland Bus - DXB 36303H | Month | 5110 | [6 empty] | 0.36 |  | 0.29 | 1512 | 0
24 | Ashok Leyland 59 Seat Bus - DXB 72353H | Month | 5610 | [6 empty] | 0.2 | 1106.63 | 0.65753 | 3688.77 | 1 | 5610 | 1 | 5610 |  | 5533.15 |  | 5610 |  | 4795.4
25 | Ashok Leyland Bus - DXB 15611M | Month | 5110 |  | 4368 | 0.62 | 3192 | 0.92 | 4704 | 0.66 | 3360 | 1.0481 | 5880 | 1 | 5110 | 1 | 5110 |  | 5110 |  | 5110 |  | 5110
26 | Ashok Leyland Bus - DXB 15496M | [19 empty] | 1848
| Ashok Leyland Bus - Dxb 92791Q With IVMS | [21 empty] | 840
| Ashok Leyland Bus - Dxb 51596J | [21 empty] | 3024
| Ashok Leyland Bus - DXB 15497M | [21 empty] | 840
LOADERS
27 | Case Sr200 Skid Steer Loader | Days | 146.15 |  |  | 7 | 1023.05 | 26 | 3799.9 | 26 | 3799.9 | 27 | 3946.05 | 26.0007 | 3800 | 26 | 3800 |  | 3800 |  | 3946.15 |  | 3800.02 |  | 1461.54 |  | 1840.38
28 | Case Sr150 Skid Steer Loader | Days | 93.46 |  |  |  | 0 | 9 | 841.14 | 26 | 2429.96 | 27 | 2523.42 | 26.0004 | 2430 | 26 | 2430 |  | 2430 |  | 2523.46 |  | 2430.01 |  | 3551.54 |  | 3364.61
29 | Hydraulic breaker CB 37S for skid steer loader | Days | 117.7 | [6 empty] | 23 | 2707.1 | 6 | 706.2 | 0
30 | backhoe Loader (3CX) with Operator | Hrs | 71.5 |  |  |  | 0 |  |  |  | 660 | 50 | 3575 | 8 | 572
31 | Skiding & loading Conrete Pump | [7 empty] | 13200
| Avant Compact Loader | [21 empty] | 2484.62 |  | 3507.69 |  | 3946.15
LIFTING VEHICLES
32 | Mast Climber | [17 empty] | 1692.33 |  | 27923.42 |  | 45692.67 |  | 47384.96
33 | Scissor Lift Electric- 8m | Days | 84.62 |  |  |  | 0 | 27 | 2284.74 | 26 | 2200.12 | 27 | 2284.74 | 26 | 2200.12 | 26 | 2200.12 |  | 2200.12 |  | 2200 |  | 3300 |  | 2030.88
34 | Scissor Lift Electric- 8m | Month | 2200 |  |  |  | 0 | 1.18 | 2603 | 1 | 2200 | 1 | 2200 | 1 | 2200 | 1 | 2200 |  | 2200 |  | 2284.74 |  | 6177.02 |  | 2200
35 | Scissor Lift Electric- 8m | Month | 2200 |  |  |  | 0 | 1.18 |  | 1 | 2200 | 1 | 2200 | 1 | 2200 | 1 | 2200 |  | 2200 |  | 2200 |  |  |  | 2200
36 | Scissor Lift Electric- 8m | Days | 84.62 | [12 empty] | 8 | 676.96 |  | 2200.12 |  | 2284.74 |  | 2623.22 |  | 2030.88
37 | Spider Lift 26 Mtr | [17 empty] | 880 |  | 23100 |  | 8250 |  | 22262.33
38 | Skyjack 8841Rt Scissor Lift | Days | 211.54 |  |  |  | 0 |  | 0 |  | 0 | 1 | 211.54 | 0
39 | Forklift 3 Ton With Long Fork-Working | Hrs | 33.85 |  |  |  | 0 | 140 | 5619 | 30 | 1015.5 | 449.9303 | 15230.14 | 551.8715 | 18680.85 |  |  |  | 35877.82 |  | 21385.14 |  | 18003.91 |  | 18954.32
40 | Forklify - 5 Ton | Hrs | [16 empty] | 1540 |  |  |  | 1540
41 | Forklift 15 Ton-Working | Hrs | 275 |  |  |  | 0 | 10 | 2750 |  | 0 | 10 | 2750 | 0
42 | Forklift 16 Ton-Working | Hrs | 275 |  |  |  |  | 0 |  |  | 1650 | 10 | 2750 | 0
| Moffett Forklift | [21 empty] | 654.23
43 | TCM Forklift - DXB 41076 | Hrs | 28.85 |  |  | 140 | 4039 | 150 | 4327.5 |  | 0 |  | 0 | 0
44 | Nano Lift 4.5 Meter | Hrs | 46.15 |  |  |  | 0 | 31 | 1430.65 | 26 | 1199.9 | 27 | 1246.05 | 26.0022 | 1200 | 26 | 1200 |  | 1200 |  | 1246.15 |  | 3600 |  | 1107.69
45 | Nano Lift 4.5 Meter | Hrs | 46.15 |  |  |  | 0 | 31 |  | 26 | 1199.9 | 27 | 1246.05 | 26.0022 | 1200 | 26 | 1200 |  | 1200 |  | 1246.15 |  |  |  | 1107.69
46 | Nano Lift 4.5 Meter | Hrs | 46.15 |  |  |  | 0 | 31 |  | 29 | 1338.35 | 27 | 1246.05 | 26.0022 | 1200 | 26 | 1200 |  | 1200 |  | 1246.15 |  |  |  | 1107.69
| Telehandler | [21 empty] | 1073.08 |  | 8584.62
| Electric Scissor Lift - 7.8 Mtr | [23 empty] | 9515
| Monorail - 20 Mtr | [23 empty] | 22846.25
| Electric Scissor Lift - 5.9 Mtr | [23 empty] | 1705
| Material Glass Lifter | [23 empty] | 6160
PICKUP
47 | Mini Excavator 3 Ton with Breaker | [17 empty] | 4840 |  |  |  | 990
PICKUP
48 | Pick Up - 3 Ton Double CabinWithout Driver | Hrs | 19.04 |  |  | 220 | 4188.8 | 420 | 7996.8 | 30 | 571.2 | 510 | 9710.4 | 279.9827 | 5330.87 |  |  |  | 9519.41 |  | 5330.87 |  | 5521.26 |  | 5330.88
RECOVERY VEHICLES
49 | Recovery Vehicle 3 Ton | L |  |  |  |  | 275 |  | 550 |  | 275 |  | 1320 |  |  | 1 | 330 | [5 empty] | 660
50 | Recovery Vehicle 7 Ton | [9 empty] | 440 |  | 0
FUEL TANKERS
51 | Diesel Tanker 9/68 Mercedes Fuel Tanker - DXB64273 | Hrs | 130.5 |  |  | 16 | 2088 | 4 | 522 |  | 0 | 4 | 522 | 4 | 522 | 20 | 2610 |  | 1044 |  | 1566 |  | 2088 |  | 1044
52 | Diesel Tanker - 9/69 Mercedes Fuel Tanker - DXB63219 | Hrs | 130.5 |  | 5742 | 104 | 13572 | 72 | 9918 |  | 0 | 32 | 4176 | 24 | 3132 | 36 | 4698 | [5 empty] | 8352 |  | 12006
53 | Diesel Tanker - 9/70 Mercedes Fuel Tanker - DXB65028 | Hrs | 130.5 |  |  |  | 0 | 40 | 5220 | 108 | 14094 | 112 | 14616 | 84 | 10962 | 80 | 10440 |  | 15138 |  | 14094 |  | 6264 |  | 1044
54 | Diesel Tanker - 9/72 Sweet Water Tanker 1 - DXB62723 | Hrs | 107.5 | [12 empty] | 39 | 4192.5 |  |  |  | 537.5
55 | Mercedes Water Tanker - DXB64272 | Days | 463 | [12 empty] | 6 | 2778 |  |  |  | 4167 |  |  |  | 463
56 | Mercedes Water Tanker - DXB62723 | [19 empty] | 2315
57 | Mercedes Water Tanker-DXB62979 | [19 empty] | 4167 |  | 4167
58 | Diesel Tanker- Scania Fuel Tanker | Hrs | 130.5 |  |  |  | 0 | 8 | 1044 |  | 0 |  | 0 | 0
SKIP TRUCKS
59 | 12/19 Skip Truck 1-Trip Isuzu 12Ton Truck - Dxb 83254O | Hrs | 273 |  |  |  | 0 | 9 | 2730 | 24 | 6781 | 29 | 7917 | 34 | 9282 | 46 | 12558 |  | 10920 |  | 10374 |  | 12285 |  | 24755
60 | 12/20 Skip Truck 1-Trip Hino 13.5 Ton Skip Truck | Hrs | 273 |  | 502 |  | 0 | 9 | 2457 | 6 | 1638 | 1 | 273 | 1 | 273 |  |  |  | 6332 |  | 1911 |  | 1092
61 | 12/17 Skip Truck 1-Trip Isuzu with Hiab Skip Loader - Dxb 70086 D | Hrs | 273 |  |  |  | 0 | 2 | 546 | 51 | 13923 | 46 | 12558 | 32 | 8736 | 38 | 10374 |  | 22659 |  | 12831 |  | 15288
Trailer
| Machinery Shifting Low Bed Semi Trailer 65Ton | [21 empty] | 248 |  | 1950
SALIK COST
62 | Salik | [5 empty] | 1743.4 |  | 2778.4 |  | 4391.7 |  | 3943.1 |  | 4075.8 |  | 3074.8 |  | 5302.7 |  | 3334.6 |  | 4047.9 |  | 4293
WASTE DISPOSAL
63 | Mixed Waste |  |  |  | 220 |  |  |  | 2990 |  | 5528 |  | 7584 |  | 8380 |  | 9550 |  | 11114 |  | 8560 |  | 7280 |  | 8480
64 | Demolition Waste | [9 empty] | 15770 |  | 13240 |  | 9600 |  | 5326.4 |  | 18638.4 |  | 7440 |  | 7820 |  | -605.96
65 | Concrete Waste | [9 empty] | 943.8 |  | 1266.8 |  | 1929.11 |  | 865.2 |  |  |  | 319.92
66 | Timber Waste | [9 empty] | 540.57 | [7 empty] | 1423.93 | [5 empty] | 2921.87
OTHER MISCELLANEOUS PLANT COSTS
67 | Boomag Plate Compactor Bpr25/50 | Days | 69.23 |  |  |  | 0 | 27 | 1869.21 | 26 | 1799.98 | 27 | 1869.21 | 26.0003 | 1800 | 3 | 207.69 |  | 623.08 |  | 1869.23 |  | 1800 |  | 1661.54 |  | 1869.23
68 | Thwaites Dumper - P 22157 | Days | 134.62 |  |  |  | 0 | 30 | 4038.6 | 26 | 3500.12 | 27 | 3634.74 | 26 | 3500.12 | 10 | 1346.2
69 | Flat Bed Semi Trailer - 55Ton | Days | 320 |  |  | 4 | 1280 | -2 | -640 |  | 0 |  | 0 | 0 |  |  |  |  | 640
70 | Electric Compressor | Days | 19.23 |  |  |  | 0 |  | 249.99 | -2 | -38.46 |  | 0 | 0
71 | Atlas Copco Air Compressor | Days | 129.81 |  |  |  | 0 |  |  | 28 | 3634.68 | 27 | 3504.87 | 26 | 3375.06 | 9 | 1168.29
72 | Livers Hf 4Kva Converter | Days | 40.5 |  |  | 30 | 1215 | 26 | 1053 | 26 | 1053 | 27 | 1093.5 | 26 | 1053 | 26 | 1053 |  | 1053 |  | 1093.5 |  | 1053 |  | 972
73 | Eco Cabin Type 1 | Days | 41.67 |  |  |  | 1666.66 | 52 | 2166.84 | 52 | 2166.84 | 54 | 2250.18 | 52 | 2166.84 | 52 | 2166.84 |  | 2166.84 |  | -833.4
74 | Thrid Party Inspection, tests, repairs, Historical Debts & Other |  |  |  | 1429 |  | 525773.07 |  | 13470 |  | 6000 |  | 9767.71 |  | 31169.96 |  | 9770.47 |  | 82388.53 |  | 15004.28 |  | 10527.03 |  | 63738.22
75 | Power Tower Duo - 5.1m | [13 empty] | 854.72 | 60 | 177.74 |  | 2784.58 |  | 1658.9 |  | 1540.4 |  | 1421.92
76 | Diesel Storage Tank | Days | 17.31 | [12 empty] | 8 | 138.48
77 | Sb Hopper Broom Attachment | Days | 53.85 | [12 empty] | 10 | 538.46 |  | 1400 |  | 1453.85 |  | 1400 |  | 1292.31 |  | 1453.85
78 | Spider Lift with Sky Guard | Days | [16 empty] | 7425
79 | Steel Pads Charges For Mini Crane 1.2x1.2 Mtr (4 Nos) | LS | [16 empty] | 1650
80 | MAN Tractor Unit - DXB 66748 | [17 empty] | 2010
81 | Floor Polishing Machine | [19 empty] | 4440
82 | Block Cutter | [19 empty] | 2850
| Cubicle Door Locks | [19 empty] | 424.08
| Gas Cutting Works | [21 empty] | 1045
| Grab Prefabricated Concrete | [21 empty] | 460.27
| Machinery Shifting Man Tractor Head - Dxb 25990-Low Bed | [21 empty] | 402
| Electric Cable - Single Core 240mm X 40 Mtr | [23 empty] | 7562.5
| Distribution Board - 2500Ams | [23 empty] | 4370.85
| Electric Cable - Single Core 240mm X 80 Mtr | [23 empty] | 7730.48
| Spider Boom Lift - 36 Mtr | [23 empty] | 880 |  | 38381.62
| Modification of Existing Platform (Mast Climber-MSM-42, MSM-71) | [23 empty] | 5500
| TOTAL |  |  |  | 14568.95 |  | 708000.24 |  | 201632.438 |  | 139773.79 |  | 316553.58 |  | 257479.63 |  | 149364.15 |  | 513167.2 |  | 455699.06 |  | 419648.87 |  | 524145.16 |  | 50855.84
[25 empty] | 524145.16 |  | 524145.16
[5 empty] | 14568.95 |  | 708000.24 |  | 201631.04 |  | 139773.85 |  | 316552.57 |  | 257479.63 |  | 149364.15 |  | 513163.2 |  | 455699.06 |  |  |  | 0 |  | 473289.32 | 1787370.43
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | -4 |  | 0

## Data
Monthly Transaction _ March 2023
Cost Code | Description | Fin Date | Cat | Src | Tran Type | Key | Int Ref | Ext Ref | Tran Date | Effective Date | Description | Composite Description | Amount | WA Ref. | Remarks
XXXD00130010 | Def Direct Costs at Site I-Earth moving machinery | 2023-03-31 | P | PC | PCHG | P000220110 | 1 4 5010962 | COST/68 | 2023-03-31 | 2023-03-31 | P000220110 Case Sr150 Skid Steer Loader | 162942,P,P000220110 Case Sr150 Skid Steer Loader | 2523.46 |  | Invoice attached
XXXD00130010 | Def Direct Costs at Site I-Earth moving machinery | 2023-03-31 | P | PC | PCHG | P000220110 | 1 4 5010962 | COST/69 | 2023-03-31 | 2023-03-31 | P000220110 Case Sr150 Skid Steer Loader-Holiday | 162942,P,P000220110 Case Sr150 Skid Steer Loader-Holiday | 0
XXXD00130010 | Def Direct Costs at Site I-Earth moving machinery | 2023-03-31 | P | PC | PCHG | P000220123 | 1 4 5010962 | COST/89 | 2023-03-10 | 2023-03-31 | P000220123 Case Sr150 Skid Steer Loader | 162942,P,P000220123 Case Sr150 Skid Steer Loader | 841.15 |  | Invoice attached
XXXD00130010 | Def Direct Costs at Site I-Earth moving machinery | 2023-03-31 | P | PC | PCHG | P000220123 | 1 4 5010962 | COST/90 | 2023-03-10 | 2023-03-31 | P000220123 Case Sr150 Skid Steer Loader-Holiday | 162942,P,P000220123 Case Sr150 Skid Steer Loader-Holiday | 0
XXXD00130010 | Def Direct Costs at Site I-Earth moving machinery | 2023-03-31 | P | PC | PCHG | P000220120 | 1 4 5010962 | COST/91 | 2023-03-14 | 2023-03-31 | P000220120 Case Sr200 Skid Steer Loader | 162942,P,P000220120 Case Sr200 Skid Steer Loader | 438.46 |  | Invoice attached
XXXD00130010 | Def Direct Costs at Site I-Earth moving machinery | 2023-03-31 | P | PC | PCHG | P000220120 | 1 4 5010962 | COST/92 | 2023-03-14 | 2023-03-31 | P000220120 Case Sr200 Skid Steer Loader-Holiday | 162942,P,P000220120 Case Sr200 Skid Steer Loader-Holiday | 0
XXXD00130010 | Def Direct Costs at Site I-Earth moving machinery | 2023-03-31 | P | PC | PCHG | P000220123 | 1 4 5010962 | COST/93 | 2023-03-31 | 2023-03-31 | P000220123 Case Sr150 Skid Steer Loader | 162942,P,P000220123 Case Sr150 Skid Steer Loader | 1401.92 |  | Invoice attached
XXXD00130010 | Def Direct Costs at Site I-Earth moving machinery | 2023-03-31 | P | PC | PCHG | P000220123 | 1 4 5010962 | COST/94 | 2023-03-31 | 2023-03-31 | P000220123 Case Sr150 Skid Steer Loader-Holiday | 162942,P,P000220123 Case Sr150 Skid Steer Loader-Holiday | 0
XXXD00130010 | Def Direct Costs at Site I-Earth moving machinery | 2023-03-31 | P | PC | PCHG | P000610012 | 1 4 5010962 | COST/131 | 2023-03-31 | 2023-03-31 | P000610012 Sb Hopper Broom Attachment | 162942,P,P000610012 Sb Hopper Broom Attachment | 1453.85 |  | Invoice attached
XXXD00130010 | Def Direct Costs at Site I-Earth moving machinery | 2023-03-31 | P | PC | PCHG | P000610012 | 1 4 5010962 | COST/132 | 2023-03-31 | 2023-03-31 | P000610012 Sb Hopper Broom Attachment-Holiday | 162942,P,P000610012 Sb Hopper Broom Attachment-Holiday | 0
XXXD00130010 | Def Direct Costs at Site I-Earth moving machinery | 2023-03-31 | P | PC | PCHG | P000500132 | 1 4 5010962 | COST/145 | 2023-03-05 | 2023-03-31 | P000500132 Bomag Plate Compactor Bpr25/50 | 162942,P,P000500132 Bomag Plate Compactor Bpr25/50 | 276.92 |  | Invoice attached
XXXD00130010 | Def Direct Costs at Site I-Earth moving machinery | 2023-03-31 | P | PC | PCHG | P000500132 | 1 4 5010962 | COST/146 | 2023-03-05 | 2023-03-31 | P000500132 Bomag Plate Compactor Bpr25/50-Holiday | 162942,P,P000500132 Bomag Plate Compactor Bpr25/50-Holiday | 0
XXXD00130010 | Def Direct Costs at Site I-Earth moving machinery | 2023-03-31 | P | PC | PCHG | P000500116 | 1 4 5010962 | COST/147 | 2023-03-31 | 2023-03-31 | P000500116 Bomag Rev Compactor Brp35/60D | 162942,P,P000500116 Bomag Rev Compactor Brp35/60D | 1592.31 |  | Invoice attached
XXXD00130010 | Def Direct Costs at Site I-Earth moving machinery | 2023-03-31 | P | PC | PCHG | P000500116 | 1 4 5010962 | COST/148 | 2023-03-31 | 2023-03-31 | P000500116 Bomag Rev Compactor Brp35/60D-Holiday | 162942,P,P000500116 Bomag Rev Compactor Brp35/60D-Holiday | 0
XXXD00130010 | Def Direct Costs at Site I-Earth moving machinery | 2023-03-31 | P | PC | PCHG | P000230121 | 1 4 5010962 | COST/175 | 2023-03-31 | 2023-03-31 | P000230121 Avant Compact Loader -Dxb62067 | 162942,P,P000230121 Avant Compact Loader -Dxb62067 | 3946.15 |  | Invoice attached
XXXD00130010 | Def Direct Costs at Site I-Earth moving machinery | 2023-03-31 | P | PC | PCHG | P000230121 | 1 4 5010962 | COST/176 | 2023-03-31 | 2023-03-31 | P000230121 Avant Compact Loader -Dxb62067-Holiday | 162942,P,P000230121 Avant Compact Loader -Dxb62067-Holiday | 0
XXXD00130020 | Def Direct Costs at Site I-Aerial lifts | 2023-03-31 | P | PC | PCHG | 2210180513 | 1 4 5010962 | COST/346 | 2023-03-03 | 2023-03-31 | Spider Boom Lift - 36 Mtr (LEO-36)-Working | 162942,P, Spider Boom Lift - 36 Mtr (LEO-36)-Working | 7260 |  | Invoice attached
XXXD00130020 | Def Direct Costs at Site I-Aerial lifts | 2023-03-31 | P | PC | PCHG | 2210180513 | 1 4 5010962 | COST/348 | 2023-03-10 | 2023-03-31 | Spider Boom Lift - 36 Mtr (LEO-36)-Working | 162942,P, Spider Boom Lift - 36 Mtr (LEO-36)-Working | 7260 |  | Invoice attached
XXXD00130020 | Def Direct Costs at Site I-Aerial lifts | 2023-03-31 | P | PC | PCHG | 2210180513 | 1 4 5010962 | COST/350 | 2023-03-17 | 2023-03-31 | Spider Boom Lift - 36 Mtr (LEO-36)-Working | 162942,P, Spider Boom Lift - 36 Mtr (LEO-36)-Working | 7260 |  | Invoice attached
XXXD00130020 | Def Direct Costs at Site I-Aerial lifts | 2023-03-31 | P | PC | PCHG | 2210180513 | 1 4 5010962 | COST/352 | 2023-03-24 | 2023-03-31 | Spider Boom Lift - 36 Mtr (LEO-36)-Working | 162942,P, Spider Boom Lift - 36 Mtr (LEO-36)-Working | 7260 |  | Invoice attached
XXXD00130020 | Def Direct Costs at Site I-Aerial lifts | 2023-03-31 | P | PC | PCHG | 2210180513 | 1 4 5010962 | COST/354 | 2023-03-31 | 2023-03-31 | Spider Boom Lift - 36 Mtr (LEO-36)-Working | 162942,P, Spider Boom Lift - 36 Mtr (LEO-36)-Working | 3630 |  | Invoice attached
XXXD00130020 | Def Direct Costs at Site I-Aerial lifts | 2023-03-31 | P | PC | PCHG | 2210180513 | 1 4 5010962 | COST/366 | 2023-03-03 | 2023-03-31 | Operator for Spider Boom Lift - 36 Mtr-Working | 162942,P, Operator for Spider Boom Lift - 36 Mtr-Working | 1269.25 |  | Invoice attached
XXXD00130020 | Def Direct Costs at Site I-Aerial lifts | 2023-03-31 | P | PC | PCHG | 2210180513 | 1 4 5010962 | COST/368 | 2023-03-10 | 2023-03-31 | Operator for Spider Boom Lift - 36 Mtr-Working | 162942,P, Operator for Spider Boom Lift - 36 Mtr-Working | 1269.25 |  | Invoice attached
XXXD00130020 | Def Direct Costs at Site I-Aerial lifts | 2023-03-31 | P | PC | PCHG | 2210180513 | 1 4 5010962 | COST/370 | 2023-03-17 | 2023-03-31 | Operator for Spider Boom Lift - 36 Mtr-Working | 162942,P, Operator for Spider Boom Lift - 36 Mtr-Working | 1269.25 |  | Invoice attached
XXXD00130020 | Def Direct Costs at Site I-Aerial lifts | 2023-03-31 | P | PC | PCHG | 2210180513 | 1 4 5010962 | COST/372 | 2023-03-24 | 2023-03-31 | Operator for Spider Boom Lift - 36 Mtr-Working | 162942,P, Operator for Spider Boom Lift - 36 Mtr-Working | 1269.25 |  | Invoice attached
XXXD00130020 | Def Direct Costs at Site I-Aerial lifts | 2023-03-31 | P | PC | PCHG | 2210180513 | 1 4 5010962 | COST/374 | 2023-03-31 | 2023-03-31 | Operator for Spider Boom Lift - 36 Mtr-Working | 162942,P, Operator for Spider Boom Lift - 36 Mtr-Working | 634.62 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | W000020068 | 1 4 5011046 | COST/1 | 2023-02-24 | 2023-03-28 | W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 162942,P,W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 522 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | W000020068 | 1 4 5011046 | COST/2 | 2023-02-25 | 2023-03-28 | W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 162942,P,W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 522 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | W000020068 | 1 4 5011046 | COST/3 | 2023-02-27 | 2023-03-28 | W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 162942,P,W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 522 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | W000020068 | 1 4 5011046 | COST/4 | 2023-02-28 | 2023-03-28 | W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 162942,P,W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 522 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | W000020068 | 1 4 5011046 | COST/5 | 2023-03-01 | 2023-03-28 | W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 162942,P,W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 522 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | W000020068 | 1 4 5011046 | COST/6 | 2023-03-02 | 2023-03-28 | W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 162942,P,W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 522 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | W000020068 | 1 4 5011046 | COST/7 | 2023-03-03 | 2023-03-28 | W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 162942,P,W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 522 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | W000020068 | 1 4 5011046 | COST/8 | 2023-03-04 | 2023-03-28 | W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 162942,P,W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 522 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | W000020068 | 1 4 5011046 | COST/9 | 2023-03-05 | 2023-03-28 | W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 162942,P,W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 522 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | W000020068 | 1 4 5011046 | COST/10 | 2023-03-06 | 2023-03-28 | W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 162942,P,W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 522 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | W000020068 | 1 4 5011046 | COST/11 | 2023-03-07 | 2023-03-28 | W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 162942,P,W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 522 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | W000020068 | 1 4 5011046 | COST/12 | 2023-03-08 | 2023-03-28 | W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 162942,P,W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 522 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | W000020068 | 1 4 5011046 | COST/13 | 2023-03-09 | 2023-03-28 | W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 162942,P,W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 522 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | W000020068 | 1 4 5011046 | COST/14 | 2023-03-10 | 2023-03-28 | W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 162942,P,W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 522 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | W000020068 | 1 4 5011046 | COST/15 | 2023-03-11 | 2023-03-28 | W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 162942,P,W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 522 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | W000020068 | 1 4 5011046 | COST/16 | 2023-03-12 | 2023-03-28 | W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 162942,P,W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 522 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | W000020068 | 1 4 5011046 | COST/17 | 2023-03-13 | 2023-03-28 | W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 162942,P,W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 522 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | W000020068 | 1 4 5011046 | COST/18 | 2023-03-14 | 2023-03-28 | W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 162942,P,W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 522 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | W000020068 | 1 4 5011046 | COST/19 | 2023-03-15 | 2023-03-28 | W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 162942,P,W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 522 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | W000020068 | 1 4 5011046 | COST/20 | 2023-03-16 | 2023-03-28 | W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 162942,P,W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 522 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | W000020068 | 1 4 5011046 | COST/21 | 2023-03-17 | 2023-03-28 | W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 162942,P,W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 522 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | W000020068 | 1 4 5011046 | COST/22 | 2023-03-18 | 2023-03-28 | W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 162942,P,W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 522 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | W000020068 | 1 4 5011046 | COST/23 | 2023-03-19 | 2023-03-28 | W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 162942,P,W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 522 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | W000020068 | 1 4 5011046 | COST/24 | 2023-03-20 | 2023-03-28 | W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 162942,P,W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 522 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | W000020068 | 1 4 5011046 | COST/25 | 2023-03-21 | 2023-03-28 | W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 162942,P,W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 522 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | W000020068 | 1 4 5011046 | COST/26 | 2023-03-22 | 2023-03-28 | W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 162942,P,W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 522 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | W000020068 | 1 4 5011046 | COST/27 | 2023-03-23 | 2023-03-28 | W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 162942,P,W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 522 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | W000020068 | 1 4 5011046 | COST/28 | 2023-03-24 | 2023-03-28 | W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 162942,P,W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 522 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | W000020068 | 1 4 5011046 | COST/29 | 2023-03-25 | 2023-03-28 | W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 162942,P,W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 522 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | W000020068 | 1 4 5011046 | COST/30 | 2023-03-26 | 2023-03-28 | W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 162942,P,W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 522 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | W000020068 | 1 4 5011046 | COST/31 | 2023-03-27 | 2023-03-28 | W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 162942,P,W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 522 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | W000020068 | 1 4 5011046 | COST/32 | 2023-03-28 | 2023-03-28 | W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 162942,P,W000020068 Diesel Tanker Charges - DT 9/68 Mercedes Fuel Tanker - DXB64273 | 522 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | W000020070 | 1 4 5011046 | COST/33 | 2023-02-26 | 2023-03-28 | W000020070 Diesel Tanker Charges - DT 9/70 Mercedes Fuel Tanker - DXB65028 | 162942,P,W000020070 Diesel Tanker Charges - DT 9/70 Mercedes Fuel Tanker - DXB65028 | 522 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | P000490100 | 1 4 5010962 | COST/64 | 2023-03-31 | 2023-03-31 | P000490100 Livers Hf 4Kva Converter | 162942,P,P000490100 Livers Hf 4Kva Converter | 1093.5 |  | Invoice attached
XXXD00130030 | Def Direct Costs at Site I-Building construction machinery and accessories | 2023-03-31 | P | PC | PCHG | P000490100 | 1 4 5010962 | COST/65 | 2023-03-31 | 2023-03-31 | P000490100 Livers Hf 4Kva Converter-Holiday | 162942,P,P000490100 Livers Hf 4Kva Converter-Holiday | 0
XXXD00130090 | Def Direct Costs at Site I-Industrial trucks | 2023-03-31 | P | CB | PCP | 2087 | MAR/12135/16 | BROKEN GLASS REMOVAL | 2023-03-08 | 2023-03-08 | 27743-CHRIS McCANN-201A22002 | 162415,P,27743-CHRIS McCANN-201A22002 | 701.3 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162303 | 1 4 5010962 | COST/54 | 2023-03-03 | 2023-03-31 | Derrick Crane - 5 Ton Capacity-Working | 162942,P, Derrick Crane - 5 Ton Capacity-Working | 6515.43 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162303 | 1 4 5010962 | COST/56 | 2023-03-10 | 2023-03-31 | Derrick Crane - 5 Ton Capacity-Working | 162942,P, Derrick Crane - 5 Ton Capacity-Working | 6515.43 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162303 | 1 4 5010962 | COST/58 | 2023-03-17 | 2023-03-31 | Derrick Crane - 5 Ton Capacity-Working | 162942,P, Derrick Crane - 5 Ton Capacity-Working | 6515.43 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162303 | 1 4 5010962 | COST/60 | 2023-03-24 | 2023-03-31 | Derrick Crane - 5 Ton Capacity-Working | 162942,P, Derrick Crane - 5 Ton Capacity-Working | 6515.43 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162303 | 1 4 5010962 | COST/62 | 2023-03-31 | 2023-03-31 | Derrick Crane - 5 Ton Capacity-Working | 162942,P, Derrick Crane - 5 Ton Capacity-Working | 2792.33 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | P000260081 | 1 4 5010962 | COST/70 | 2023-03-31 | 2023-03-31 | P000260081 Scissor Lift Electric- 8m | 162942,P,P000260081 Scissor Lift Electric- 8m | 2284.74 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | P000260081 | 1 4 5010962 | COST/71 | 2023-03-31 | 2023-03-31 | P000260081 Scissor Lift Electric- 8m-Holiday | 162942,P,P000260081 Scissor Lift Electric- 8m-Holiday | 0
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410160315 | 1 4 5010962 | COST/73 | 2023-03-03 | 2023-03-31 | Forklift 3 Ton With Long Fork-Working | 162942,P, Forklift 3 Ton With Long Fork-Working | 4400.11 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410160315 | 1 4 5010962 | COST/75 | 2023-03-10 | 2023-03-31 | Forklift 3 Ton With Long Fork-Working | 162942,P, Forklift 3 Ton With Long Fork-Working | 4400.11 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410160315 | 1 4 5010962 | COST/77 | 2023-03-17 | 2023-03-31 | Forklift 3 Ton With Long Fork-Working | 162942,P, Forklift 3 Ton With Long Fork-Working | 4400.11 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410160315 | 1 4 5010962 | COST/79 | 2023-03-24 | 2023-03-31 | Forklift 3 Ton With Long Fork-Working | 162942,P, Forklift 3 Ton With Long Fork-Working | 4400.11 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410160315 | 1 4 5010962 | COST/81 | 2023-03-31 | 2023-03-31 | Forklift 3 Ton With Long Fork-Working | 162942,P, Forklift 3 Ton With Long Fork-Working | 2369.29 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | P000260087 | 1 4 5010962 | COST/83 | 2023-03-31 | 2023-03-31 | P000260087 Nano Lift 4.5 Meter | 162942,P,P000260087 Nano Lift 4.5 Meter | 1246.15 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | P000260087 | 1 4 5010962 | COST/84 | 2023-03-31 | 2023-03-31 | P000260087 Nano Lift 4.5 Meter-Holiday | 162942,P,P000260087 Nano Lift 4.5 Meter-Holiday | 0
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | P000260049 | 1 4 5010962 | COST/85 | 2023-03-31 | 2023-03-31 | P000260049 Scissor Lift Electric- 8m | 162942,P,P000260049 Scissor Lift Electric- 8m | 2200 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | P000260082 | 1 4 5010962 | COST/86 | 2023-03-31 | 2023-03-31 | P000260082 Scissor Lift Electric- 8m | 162942,P,P000260082 Scissor Lift Electric- 8m | 2200 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | P000260092 | 1 4 5010962 | COST/87 | 2023-03-31 | 2023-03-31 | P000260092 Nano Lift 4.5 Meter | 162942,P,P000260092 Nano Lift 4.5 Meter | 1246.15 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | P000260092 | 1 4 5010962 | COST/88 | 2023-03-31 | 2023-03-31 | P000260092 Nano Lift 4.5 Meter-Holiday | 162942,P,P000260092 Nano Lift 4.5 Meter-Holiday | 0
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | P000260088 | 1 4 5010962 | COST/95 | 2023-03-31 | 2023-03-31 | P000260088 Nano Lift 4.5 Meter | 162942,P,P000260088 Nano Lift 4.5 Meter | 1246.15 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | P000260088 | 1 4 5010962 | COST/96 | 2023-03-31 | 2023-03-31 | P000260088 Nano Lift 4.5 Meter-Holiday | 162942,P,P000260088 Nano Lift 4.5 Meter-Holiday | 0
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161727 | 1 4 5010962 | COST/101 | 2023-03-03 | 2023-03-31 | Power Tower Duo - 5.1 Mtr-Working | 162942,P, Power Tower Duo - 5.1 Mtr-Working | 177.74 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161727 | 1 4 5010962 | COST/103 | 2023-03-10 | 2023-03-31 | Power Tower Duo - 5.1 Mtr-Working | 162942,P, Power Tower Duo - 5.1 Mtr-Working | 177.74 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161727 | 1 4 5010962 | COST/105 | 2023-03-17 | 2023-03-31 | Power Tower Duo - 5.1 Mtr-Working | 162942,P, Power Tower Duo - 5.1 Mtr-Working | 177.74 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161727 | 1 4 5010962 | COST/107 | 2023-03-24 | 2023-03-31 | Power Tower Duo - 5.1 Mtr-Working | 162942,P, Power Tower Duo - 5.1 Mtr-Working | 177.74 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161727 | 1 4 5010962 | COST/109 | 2023-03-31 | 2023-03-31 | Power Tower Duo - 5.1 Mtr-Working | 162942,P, Power Tower Duo - 5.1 Mtr-Working | 88.87 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161727 | 1 4 5010962 | COST/111 | 2023-03-03 | 2023-03-31 | Power Tower Duo - 5.1 Mtr-Working | 162942,P, Power Tower Duo - 5.1 Mtr-Working | 177.74 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161727 | 1 4 5010962 | COST/113 | 2023-03-10 | 2023-03-31 | Power Tower Duo - 5.1 Mtr-Working | 162942,P, Power Tower Duo - 5.1 Mtr-Working | 177.74 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161727 | 1 4 5010962 | COST/115 | 2023-03-17 | 2023-03-31 | Power Tower Duo - 5.1 Mtr-Working | 162942,P, Power Tower Duo - 5.1 Mtr-Working | 177.74 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161727 | 1 4 5010962 | COST/117 | 2023-03-24 | 2023-03-31 | Power Tower Duo - 5.1 Mtr-Working | 162942,P, Power Tower Duo - 5.1 Mtr-Working | 177.74 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161727 | 1 4 5010962 | COST/119 | 2023-03-31 | 2023-03-31 | Power Tower Duo - 5.1 Mtr-Working | 162942,P, Power Tower Duo - 5.1 Mtr-Working | 88.87 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162304 | 1 4 5010962 | COST/122 | 2023-03-03 | 2023-03-31 | Derrick Crane - 12 Ton-Working | 162942,P, Derrick Crane - 12 Ton-Working | 7403.94 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162304 | 1 4 5010962 | COST/124 | 2023-03-10 | 2023-03-31 | Derrick Crane - 12 Ton-Working | 162942,P, Derrick Crane - 12 Ton-Working | 7403.94 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162304 | 1 4 5010962 | COST/126 | 2023-03-17 | 2023-03-31 | Derrick Crane - 12 Ton-Working | 162942,P, Derrick Crane - 12 Ton-Working | 7403.94 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162304 | 1 4 5010962 | COST/128 | 2023-03-24 | 2023-03-31 | Derrick Crane - 12 Ton-Working | 162942,P, Derrick Crane - 12 Ton-Working | 7403.94 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162304 | 1 4 5010962 | COST/130 | 2023-03-31 | 2023-03-31 | Derrick Crane - 12 Ton-Working | 162942,P, Derrick Crane - 12 Ton-Working | 4230.82 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | P000260050 | 1 4 5010962 | COST/133 | 2023-03-31 | 2023-03-31 | P000260050 Scissor Lift - 8m | 162942,P,P000260050 Scissor Lift - 8m | 2284.74 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | P000260050 | 1 4 5010962 | COST/134 | 2023-03-31 | 2023-03-31 | P000260050 Scissor Lift - 8m-Holiday | 162942,P,P000260050 Scissor Lift - 8m-Holiday | 0
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410160402 | 1 4 5010962 | COST/136 | 2023-03-03 | 2023-03-31 | Mast Climber-Working | 162942,P, Mast Climber-Working | 5923.15 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410160402 | 1 4 5010962 | COST/138 | 2023-03-10 | 2023-03-31 | Mast Climber-Working | 162942,P, Mast Climber-Working | 5923.15 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410160402 | 1 4 5010962 | COST/140 | 2023-03-17 | 2023-03-31 | Mast Climber-Working | 162942,P, Mast Climber-Working | 5923.15 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410160402 | 1 4 5010962 | COST/142 | 2023-03-24 | 2023-03-31 | Mast Climber-Working | 162942,P, Mast Climber-Working | 5923.15 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410160402 | 1 4 5010962 | COST/144 | 2023-03-31 | 2023-03-31 | Mast Climber-Working | 162942,P, Mast Climber-Working | 3384.66 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410160402 | 1 4 5010962 | COST/150 | 2023-03-03 | 2023-03-31 | Mast Climber (Model: MSM SUPER)-Working | 162942,P, Mast Climber (Model: MSM SUPER)-Working | 5923.09 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410160402 | 1 4 5010962 | COST/152 | 2023-03-10 | 2023-03-31 | Mast Climber (Model: MSM SUPER)-Working | 162942,P, Mast Climber (Model: MSM SUPER)-Working | 5923.09 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410160402 | 1 4 5010962 | COST/154 | 2023-03-17 | 2023-03-31 | Mast Climber (Model: MSM SUPER)-Working | 162942,P, Mast Climber (Model: MSM SUPER)-Working | 5923.09 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410160402 | 1 4 5010962 | COST/156 | 2023-03-24 | 2023-03-31 | Mast Climber (Model: MSM SUPER)-Working | 162942,P, Mast Climber (Model: MSM SUPER)-Working | 5923.09 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410160402 | 1 4 5010962 | COST/158 | 2023-03-31 | 2023-03-31 | Mast Climber (Model: MSM SUPER)-Working | 162942,P, Mast Climber (Model: MSM SUPER)-Working | 3384.62 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162415 | 1 4 5010962 | COST/160 | 2023-02-10 | 2023-03-31 | Jekko Mini Picker-1000kg-Working | 162942,P, Jekko Mini Picker-1000kg-Working | 5076.94 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162415 | 1 4 5010962 | COST/162 | 2023-02-17 | 2023-03-31 | Jekko Mini Picker-1000kg-Working | 162942,P, Jekko Mini Picker-1000kg-Working | 3046.16 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162415 | 1 4 5010962 | COST/164 | 2023-02-24 | 2023-03-31 | Jekko Mini Picker-1000kg-Working | 162942,P, Jekko Mini Picker-1000kg-Working | 3046.16 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162415 | 1 4 5010962 | COST/166 | 2023-03-03 | 2023-03-31 | Jekko Mini Picker-1000kg-Working | 162942,P, Jekko Mini Picker-1000kg-Working | 3046.16 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162415 | 1 4 5010962 | COST/168 | 2023-03-10 | 2023-03-31 | Jekko Mini Picker-1000kg-Working | 162942,P, Jekko Mini Picker-1000kg-Working | 3046.16 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162415 | 1 4 5010962 | COST/170 | 2023-03-17 | 2023-03-31 | Jekko Mini Picker-1000kg-Working | 162942,P, Jekko Mini Picker-1000kg-Working | 3046.16 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162415 | 1 4 5010962 | COST/172 | 2023-03-24 | 2023-03-31 | Jekko Mini Picker-1000kg-Working | 162942,P, Jekko Mini Picker-1000kg-Working | 3046.16 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162415 | 1 4 5010962 | COST/174 | 2023-03-31 | 2023-03-31 | Jekko Mini Picker-1000kg-Working | 162942,P, Jekko Mini Picker-1000kg-Working | 1015.39 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/181 | 2023-03-03 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/183 | 2023-03-10 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/185 | 2023-03-17 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/187 | 2023-03-24 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/189 | 2023-03-31 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 165 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/192 | 2023-03-03 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/194 | 2023-03-10 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/196 | 2023-03-17 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/198 | 2023-03-24 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/200 | 2023-03-31 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 165 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/203 | 2023-03-03 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/205 | 2023-03-10 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/207 | 2023-03-17 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/209 | 2023-03-24 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/211 | 2023-03-31 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 165 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/214 | 2023-03-03 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/216 | 2023-03-10 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/218 | 2023-03-17 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/220 | 2023-03-24 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/222 | 2023-03-31 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 165 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410160401 | 1 4 5010962 | COST/224 | 2023-03-03 | 2023-03-31 | Monorail - 20 Mtr with Special Clamp & 2nos.Winches-Working | 162942,P, Monorail - 20 Mtr with Special Clamp & 2nos.Winches-Working | 4569.25 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410160401 | 1 4 5010962 | COST/226 | 2023-03-10 | 2023-03-31 | Monorail - 20 Mtr with Special Clamp & 2nos.Winches-Working | 162942,P, Monorail - 20 Mtr with Special Clamp & 2nos.Winches-Working | 4569.25 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410160401 | 1 4 5010962 | COST/228 | 2023-03-17 | 2023-03-31 | Monorail - 20 Mtr with Special Clamp & 2nos.Winches-Working | 162942,P, Monorail - 20 Mtr with Special Clamp & 2nos.Winches-Working | 4569.25 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410160401 | 1 4 5010962 | COST/230 | 2023-03-24 | 2023-03-31 | Monorail - 20 Mtr with Special Clamp & 2nos.Winches-Working | 162942,P, Monorail - 20 Mtr with Special Clamp & 2nos.Winches-Working | 4569.25 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410160401 | 1 4 5010962 | COST/232 | 2023-03-31 | 2023-03-31 | Monorail - 20 Mtr with Special Clamp & 2nos.Winches-Working | 162942,P, Monorail - 20 Mtr with Special Clamp & 2nos.Winches-Working | 2284.62 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162302 | 1 4 5010962 | COST/235 | 2023-03-03 | 2023-03-31 | Derrick Crane 2 Ton-Working | 162942,P, Derrick Crane 2 Ton-Working | 4442.36 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162302 | 1 4 5010962 | COST/237 | 2023-03-10 | 2023-03-31 | Derrick Crane 2 Ton-Working | 162942,P, Derrick Crane 2 Ton-Working | 4442.36 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162302 | 1 4 5010962 | COST/239 | 2023-03-17 | 2023-03-31 | Derrick Crane 2 Ton-Working | 162942,P, Derrick Crane 2 Ton-Working | 4442.36 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162302 | 1 4 5010962 | COST/241 | 2023-03-24 | 2023-03-31 | Derrick Crane 2 Ton-Working | 162942,P, Derrick Crane 2 Ton-Working | 4442.36 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162302 | 1 4 5010962 | COST/243 | 2023-03-31 | 2023-03-31 | Derrick Crane 2 Ton-Working | 162942,P, Derrick Crane 2 Ton-Working | 2538.49 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | MOB001 | 1 4 5010962 | COST/244 | 2023-03-31 | 2023-03-31 | Erection Charges of 2 Ton Derrick Crane | 162942,P, Erection Charges of 2 Ton Derrick Crane | 8250 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | MOB001 | 1 4 5010962 | COST/245 | 2023-03-31 | 2023-03-31 | Design, Calculation & Submittal Charges | 162942,P, Design, Calculation & Submittal Charges | 2750 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | MOB001 | 1 4 5010962 | COST/246 | 2023-03-31 | 2023-03-31 | Saddle Beam Cost For Derrick Crane | 162942,P, Saddle Beam Cost For Derrick Crane | 27500 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | MOB001 | 1 4 5010962 | COST/247 | 2023-03-31 | 2023-03-31 | Third Party Inspection Charges | 162942,P, Third Party Inspection Charges | 825 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/250 | 2023-03-03 | 2023-03-31 | Electric Scissor Lift - 5.9 Mtr-Working | 162942,P, Electric Scissor Lift - 5.9 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/252 | 2023-03-10 | 2023-03-31 | Electric Scissor Lift - 5.9 Mtr-Working | 162942,P, Electric Scissor Lift - 5.9 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/254 | 2023-03-17 | 2023-03-31 | Electric Scissor Lift - 5.9 Mtr-Working | 162942,P, Electric Scissor Lift - 5.9 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/256 | 2023-03-24 | 2023-03-31 | Electric Scissor Lift - 5.9 Mtr-Working | 162942,P, Electric Scissor Lift - 5.9 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/258 | 2023-03-31 | 2023-03-31 | Electric Scissor Lift - 5.9 Mtr-Working | 162942,P, Electric Scissor Lift - 5.9 Mtr-Working | 165 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162415 | 1 4 5010962 | COST/261 | 2023-03-03 | 2023-03-31 | Material Glass Lifter GML800-Working | 162942,P, Material Glass Lifter GML800-Working | 1650 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162415 | 1 4 5010962 | COST/263 | 2023-03-10 | 2023-03-31 | Material Glass Lifter GML800-Working | 162942,P, Material Glass Lifter GML800-Working | 1650 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162415 | 1 4 5010962 | COST/265 | 2023-03-17 | 2023-03-31 | Material Glass Lifter GML800-Working | 162942,P, Material Glass Lifter GML800-Working | 1650 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162415 | 1 4 5010962 | COST/267 | 2023-03-24 | 2023-03-31 | Material Glass Lifter GML800-Working | 162942,P, Material Glass Lifter GML800-Working | 1650 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162415 | 1 4 5010962 | COST/269 | 2023-03-31 | 2023-03-31 | Material Glass Lifter GML800-Working | 162942,P, Material Glass Lifter GML800-Working | 825 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/302 | 2023-03-03 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/304 | 2023-03-10 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/306 | 2023-03-17 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/308 | 2023-03-24 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/310 | 2023-03-31 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 165 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/313 | 2023-03-03 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/315 | 2023-03-10 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/317 | 2023-03-17 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/319 | 2023-03-24 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/321 | 2023-03-31 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 165 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161727 | 1 4 5010962 | COST/324 | 2023-03-03 | 2023-03-31 | Electric Scissor Lift - 5.9 Mtr-Working | 162942,P, Electric Scissor Lift - 5.9 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161727 | 1 4 5010962 | COST/326 | 2023-03-10 | 2023-03-31 | Electric Scissor Lift - 5.9 Mtr-Working | 162942,P, Electric Scissor Lift - 5.9 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161727 | 1 4 5010962 | COST/328 | 2023-03-17 | 2023-03-31 | Electric Scissor Lift - 5.9 Mtr-Working | 162942,P, Electric Scissor Lift - 5.9 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161727 | 1 4 5010962 | COST/330 | 2023-03-24 | 2023-03-31 | Electric Scissor Lift - 5.9 Mtr-Working | 162942,P, Electric Scissor Lift - 5.9 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161727 | 1 4 5010962 | COST/332 | 2023-03-31 | 2023-03-31 | Electric Scissor Lift - 5.9 Mtr-Working | 162942,P, Electric Scissor Lift - 5.9 Mtr-Working | 165 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161727 | 1 4 5010962 | COST/335 | 2023-03-03 | 2023-03-31 | Electric Scissor Lift - 5.9 Mtr-Working | 162942,P, Electric Scissor Lift - 5.9 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161727 | 1 4 5010962 | COST/337 | 2023-03-10 | 2023-03-31 | Electric Scissor Lift - 5.9 Mtr-Working | 162942,P, Electric Scissor Lift - 5.9 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161727 | 1 4 5010962 | COST/339 | 2023-03-17 | 2023-03-31 | Electric Scissor Lift - 5.9 Mtr-Working | 162942,P, Electric Scissor Lift - 5.9 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161727 | 1 4 5010962 | COST/341 | 2023-03-24 | 2023-03-31 | Electric Scissor Lift - 5.9 Mtr-Working | 162942,P, Electric Scissor Lift - 5.9 Mtr-Working | 330 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161727 | 1 4 5010962 | COST/343 | 2023-03-31 | 2023-03-31 | Electric Scissor Lift - 5.9 Mtr-Working | 162942,P, Electric Scissor Lift - 5.9 Mtr-Working | 165 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | MOB001 | 1 4 5010962 | COST/344 | 2023-03-31 | 2023-03-31 | Mob. & Demob. Charges For 4 Units Electric Scissor Lifts | 162942,P, Mob. & Demob. Charges For 4 Units Electric Scissor Lifts | 880 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162301 | 1 4 5010962 | COST/356 | 2023-03-03 | 2023-03-31 | Operator for Derrick Crane - 2 Ton-Working | 162942,P, Operator for Derrick Crane - 2 Ton-Working | 1332.72 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162301 | 1 4 5010962 | COST/358 | 2023-03-10 | 2023-03-31 | Operator for Derrick Crane - 2 Ton-Working | 162942,P, Operator for Derrick Crane - 2 Ton-Working | 1332.72 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162301 | 1 4 5010962 | COST/360 | 2023-03-17 | 2023-03-31 | Operator for Derrick Crane - 2 Ton-Working | 162942,P, Operator for Derrick Crane - 2 Ton-Working | 1332.72 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162301 | 1 4 5010962 | COST/362 | 2023-03-24 | 2023-03-31 | Operator for Derrick Crane - 2 Ton-Working | 162942,P, Operator for Derrick Crane - 2 Ton-Working | 1332.72 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162301 | 1 4 5010962 | COST/364 | 2023-03-31 | 2023-03-31 | Operator for Derrick Crane - 2 Ton-Working | 162942,P, Operator for Derrick Crane - 2 Ton-Working | 761.55 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | MOB001 | 1 4 5010962 | COST/383 | 2023-03-31 | 2023-03-31 | Mob. & Demob. Charges For Overhang Beam Model: LIBRO-800 | 162942,P, Mob. & Demob. Charges For Overhang Beam Model: LIBRO-800 | 1100 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | MOB001 | 1 4 5010962 | COST/384 | 2023-03-31 | 2023-03-31 | 3rd Party Certification & FamiliarizationTraining Charges For 8nos. Operators.Familiarization Charges AED-200X8 = 1,600/-Certifications Charges AED-350X8 = 2,800/-Total AED = 4,400/- | 162942,P, 3rd Party Certification & FamiliarizationTraining Charges For 8nos. Operators.Familiarization Charges AED-200X8 = 1,600/-Certifications Charges AED-350X8 = 2,800/-Total AED = 4,400/- | 825 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | P000260048 | 1 4 5010962 | COST/385 | 2023-03-31 | 2023-03-31 | P000260048 Scissor Lift Electric- 8m | 162942,P,P000260048 Scissor Lift Electric- 8m | 1269.3 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | P000260048 | 1 4 5010962 | COST/386 | 2023-03-31 | 2023-03-31 | P000260048 Scissor Lift Electric- 8m-Holiday | 162942,P,P000260048 Scissor Lift Electric- 8m-Holiday | 0
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/388 | 2023-03-24 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 220 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/390 | 2023-03-31 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 165 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/392 | 2023-03-24 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 220 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/394 | 2023-03-31 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 165 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/396 | 2023-03-24 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 220 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/398 | 2023-03-31 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 165 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/400 | 2023-03-24 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 220 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/402 | 2023-03-31 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 165 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/404 | 2023-03-24 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 220 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410161705 | 1 4 5010962 | COST/406 | 2023-03-31 | 2023-03-31 | Electric Scissor Lift - 7.8 Mtr-Working | 162942,P, Electric Scissor Lift - 7.8 Mtr-Working | 165 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | MOB001 | 1 4 5010962 | COST/407 | 2023-03-31 | 2023-03-31 | Mob. & Demob. Charges For (5 Units) Electric Scissor Lift | 162942,P, Mob. & Demob. Charges For (5 Units) Electric Scissor Lift | 1100 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162414 | 1 4 5010962 | COST/409 | 2023-03-24 | 2023-03-31 | Mini Floor Crane (JMG MC-32)-Working | 162942,P, Mini Floor Crane (JMG MC-32)-Working | 550 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | 2410162414 | 1 4 5010962 | COST/411 | 2023-03-31 | 2023-03-31 | Mini Floor Crane (JMG MC-32)-Working | 162942,P, Mini Floor Crane (JMG MC-32)-Working | 1650 |  | Invoice attached
XXXD00130100 | Def Direct Costs at Site I-Lifting equipment and accessories | 2023-03-31 | P | PC | PCHG | MOB001 | 1 4 5010962 | COST/412 | 2023-03-31 | 2023-03-31 | Mob. & Demob. Charges For Mini Floor Crane (JMG MC-32) | 162942,P, Mob. & Demob. Charges For Mini Floor Crane (JMG MC-32) | 880 |  | Invoice attached
XXXD00130110 | Def Direct Costs at Site I-Passenger motor vehicles | 2023-03-31 | P | PC | PCHG | 2510150704 | 1 4 5010962 | COST/43 | 2023-03-03 | 2023-03-31 | Pick Up - 3 Ton Double CabinWithout Driver-Working | 162942,P, Pick Up - 3 Ton Double CabinWithout Driver-Working | 1332.72 |  | Invoice attached
XXXD00130110 | Def Direct Costs at Site I-Passenger motor vehicles | 2023-03-31 | P | PC | PCHG | 2510150704 | 1 4 5010962 | COST/45 | 2023-03-10 | 2023-03-31 | Pick Up - 3 Ton Double CabinWithout Driver-Working | 162942,P, Pick Up - 3 Ton Double CabinWithout Driver-Working | 1332.72 |  | Invoice attached
XXXD00130110 | Def Direct Costs at Site I-Passenger motor vehicles | 2023-03-31 | P | PC | PCHG | 2510150704 | 1 4 5010962 | COST/47 | 2023-03-17 | 2023-03-31 | Pick Up - 3 Ton Double CabinWithout Driver-Working | 162942,P, Pick Up - 3 Ton Double CabinWithout Driver-Working | 1332.72 |  | Invoice attached
XXXD00130110 | Def Direct Costs at Site I-Passenger motor vehicles | 2023-03-31 | P | PC | PCHG | 2510150704 | 1 4 5010962 | COST/49 | 2023-03-24 | 2023-03-31 | Pick Up - 3 Ton Double CabinWithout Driver-Working | 162942,P, Pick Up - 3 Ton Double CabinWithout Driver-Working | 1332.72 |  | Invoice attached
XXXD00130110 | Def Direct Costs at Site I-Passenger motor vehicles | 2023-03-31 | P | PC | PCHG | 2510150704 | 1 4 5010962 | COST/51 | 2023-03-31 | 2023-03-31 | Pick Up - 3 Ton Double CabinWithout Driver-Working | 162942,P, Pick Up - 3 Ton Double CabinWithout Driver-Working | 761.55 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/34 | 2023-01-25 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 59215 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 59215 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/35 | 2023-01-25 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 59216 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 59216 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/36 | 2023-02-28 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57248 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57248 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/37 | 2023-02-28 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57250 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57250 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/38 | 2023-03-01 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57151 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57151 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/39 | 2023-03-02 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57155 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57155 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/40 | 2023-03-02 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57156 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57156 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/41 | 2023-03-03 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57157 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57157 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/42 | 2023-03-04 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57161 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57161 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/43 | 2023-03-06 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57164 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57164 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/44 | 2023-03-06 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 51762 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 51762 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/45 | 2023-03-07 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57166 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57166 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/46 | 2023-03-07 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57167 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57167 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/47 | 2023-03-08 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57171 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57171 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/48 | 2023-03-08 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57170 ) Skip Dump on 09/03/2023 Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57170 ) Skip Dump on 09/03/2023 Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/49 | 2023-03-08 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57169 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57169 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/50 | 2023-03-09 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57172) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57172) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/51 | 2023-03-10 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57175 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57175 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/52 | 2023-03-10 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57176 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57176 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/53 | 2023-03-12 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57179 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57179 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/54 | 2023-03-12 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57181 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57181 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/55 | 2023-03-12 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57178 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57178 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/56 | 2023-03-13 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57180 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57180 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/57 | 2023-03-14 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57183 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57183 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/58 | 2023-03-15 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57188 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57188 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/59 | 2023-03-15 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57186 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57186 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/60 | 2023-03-15 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57187 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57187 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/61 | 2023-03-17 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57193 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57193 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/62 | 2023-03-17 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57192 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57192 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/63 | 2023-03-18 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57195 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57195 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/64 | 2023-03-18 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57196 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57196 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/65 | 2023-03-19 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 59752 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 59752 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/66 | 2023-03-19 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 59753 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 59753 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/67 | 2023-03-20 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57198 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57198 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/68 | 2023-03-21 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57200 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57200 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/69 | 2023-03-22 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57504 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57504 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/70 | 2023-03-23 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57508 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57508 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/71 | 2023-03-23 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57506 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57506 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/72 | 2023-03-24 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57510 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57510 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/73 | 2023-03-24 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57511 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57511 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/74 | 2023-03-25 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57512 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57512 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/75 | 2023-03-26 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57515 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57515 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/76 | 2023-03-26 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 57516 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 57516 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120019 | 1 4 5011046 | COST/77 | 2023-03-27 | 2023-03-28 | P000120019 12/19 Skip Truck 1-Trip ( 59769 ) Isuzu 12Ton Truck - Dxb 83254O | 162942,P,P000120019 12/19 Skip Truck 1-Trip ( 59769 ) Isuzu 12Ton Truck - Dxb 83254O | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120020 | 1 4 5011046 | COST/78 | 2023-03-02 | 2023-03-28 | P000120020 1 Trip 12/20 Skip Truck ( 60141 ) Hino 13.5 Ton Skip Truck | 162942,P,P000120020 1 Trip 12/20 Skip Truck ( 60141 ) Hino 13.5 Ton Skip Truck | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120020 | 1 4 5011046 | COST/79 | 2023-03-04 | 2023-03-28 | P000120020 1 Trip 12/20 Skip Truck ( 58219 ) Hino 13.5 Ton Skip Truck | 162942,P,P000120020 1 Trip 12/20 Skip Truck ( 58219 ) Hino 13.5 Ton Skip Truck | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120020 | 1 4 5011046 | COST/80 | 2023-03-06 | 2023-03-28 | P000120020 1 Trip 12/20 Skip Truck ( 58221 ) Hino 13.5 Ton Skip Truck | 162942,P,P000120020 1 Trip 12/20 Skip Truck ( 58221 ) Hino 13.5 Ton Skip Truck | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000120020 | 1 4 5011046 | COST/81 | 2023-03-16 | 2023-03-28 | P000120020 1 Trip 12/20 Skip Truck ( 57189 ) Hino 13.5 Ton Skip Truck | 162942,P,P000120020 1 Trip 12/20 Skip Truck ( 57189 ) Hino 13.5 Ton Skip Truck | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/82 | 2023-02-28 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 58208 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 58208 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/83 | 2023-03-01 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 58211 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 58211 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/84 | 2023-03-01 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 58212 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 58212 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/85 | 2023-03-02 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 58214 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 58214 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/86 | 2023-03-02 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 58215 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 58215 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/87 | 2023-03-03 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 58217 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 58217 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/88 | 2023-03-07 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 58224 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 58224 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/89 | 2023-03-07 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 58226 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 58226 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/90 | 2023-03-08 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 58229 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 58229 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/91 | 2023-03-08 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 58228 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 58228 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/92 | 2023-03-08 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 58227 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 58227 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/93 | 2023-03-09 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 58231 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 58231 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/94 | 2023-03-09 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 58230 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 58230 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/95 | 2023-03-10 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 58233 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 58233 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/96 | 2023-03-11 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 58236 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 58236 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/97 | 2023-03-11 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 58235 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 58235 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/98 | 2023-03-13 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 58239 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 58239 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/99 | 2023-03-13 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 58237 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 58237 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/100 | 2023-03-14 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 58241 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 58241 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/101 | 2023-03-14 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 58240 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 58240 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/102 | 2023-03-15 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 58243 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 58243 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/103 | 2023-03-15 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 58244 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 58244 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/104 | 2023-03-16 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 58245 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 58245 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/105 | 2023-03-17 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 58248 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 58248 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/106 | 2023-03-17 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 58247 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 58247 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/107 | 2023-03-18 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 58250 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 58250 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/108 | 2023-03-19 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 59751 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 59751 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/109 | 2023-03-20 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 59756 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 59756 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/110 | 2023-03-20 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 59754 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 59754 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/111 | 2023-03-20 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 59755 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 59755 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/112 | 2023-03-21 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 59757 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 59757 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/113 | 2023-03-22 | 2023-03-28 | W000050017 12/17 Skip Truck 1- Trip ( 59760 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1- Trip ( 59760 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/114 | 2023-03-23 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 59763 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 59763 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/115 | 2023-03-23 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 59762 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 59762 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/116 | 2023-03-23 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 59761 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 59761 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/117 | 2023-03-24 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 59764 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 59764 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/118 | 2023-03-25 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 59766 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 59766 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/119 | 2023-03-26 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 59767 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 59767 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000050017 | 1 4 5011046 | COST/120 | 2023-03-27 | 2023-03-28 | W000050017 12/17 Skip Truck 1-Trip ( 59768 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 162942,P,W000050017 12/17 Skip Truck 1-Trip ( 59768 ) Isuzu with Hiab Skip Loader - Dxb 70086 D | 273 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000030020 | 1 4 5010962 | COST/375 | 2023-03-06 | 2023-03-31 | W000030020 Nissan Truck with Hiab Crane With IVMS | 162942,P,W000030020 Nissan Truck with Hiab Crane With IVMS | 1155 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000030020 | 1 4 5010962 | COST/376 | 2023-03-06 | 2023-03-31 | W000030020 Nissan Truck with Hiab Crane With IVMS-Holiday | 162942,P,W000030020 Nissan Truck with Hiab Crane With IVMS-Holiday | 0
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000030020 | 1 4 5010962 | COST/377 | 2023-03-12 | 2023-03-31 | W000030020 Nissan Truck with Hiab Crane With IVMS | 162942,P,W000030020 Nissan Truck with Hiab Crane With IVMS | 1155 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000030020 | 1 4 5010962 | COST/378 | 2023-03-12 | 2023-03-31 | W000030020 Nissan Truck with Hiab Crane With IVMS-Holiday | 162942,P,W000030020 Nissan Truck with Hiab Crane With IVMS-Holiday | 0
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000030018 | 1 4 5010962 | COST/379 | 2023-03-21 | 2023-03-31 | W000030018 Nissan Truck with Hiab Crane With IVMS | 162942,P,W000030018 Nissan Truck with Hiab Crane With IVMS | 3087.68 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | W000030018 | 1 4 5010962 | COST/380 | 2023-03-21 | 2023-03-31 | W000030018 Nissan Truck with Hiab Crane With IVMS-Holiday | 162942,P,W000030018 Nissan Truck with Hiab Crane With IVMS-Holiday | 0
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000100023 | 1 4 5010962 | COST/381 | 2023-03-14 | 2023-03-31 | P000100023 Mercedes Truck With Crane With IVMS | 162942,P,P000100023 Mercedes Truck With Crane With IVMS | 620 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000100022 | 1 4 5010962 | COST/382 | 2023-03-22 | 2023-03-31 | P000100022 Nissan Truck With Hiab Crane With IVMS | 162942,P,P000100022 Nissan Truck With Hiab Crane With IVMS | 385 |  | Invoice attached
XXXD00130130 | Def Direct Costs at Site I-Specialized and recreational vehicles | 2023-03-31 | P | PC | PCHG | P000100022 | 1 4 5010962 | COST/420 | 2023-03-28 | 2023-03-31 | P000100022 Nissan Truck With Hiab Crane With IVMS | 162942,P,P000100022 Nissan Truck With Hiab Crane With IVMS | 385 |  | Invoice attached
XXXD00130140 | Def Direct Costs at Site I-Truck tractors | 2023-03-31 | P | PC | PCHG | P000170028 | 1 4 5011046 | COST/121 | 2023-03-04 | 2023-03-28 | P000170028 Machinery Shifting Man Tractor Head - Dxb 25990-Low Bed | 162942,P,P000170028 Machinery Shifting Man Tractor Head - Dxb 25990-Low Bed | 402 |  | Invoice attached
XXXD00130140 | Def Direct Costs at Site I-Truck tractors | 2023-03-31 | P | PC | PCHG | P000170028 | 1 4 5011046 | COST/122 | 2023-03-11 | 2023-03-28 | P000170028 Machinery Shifting Man Tractor Head - Dxb 25990-Low Bed | 162942,P,P000170028 Machinery Shifting Man Tractor Head - Dxb 25990-Low Bed | 402 |  | Invoice attached
XXXD00130140 | Def Direct Costs at Site I-Truck tractors | 2023-03-31 | P | PC | PCHG | P000170029 | 1 4 5011046 | COST/123 | 2023-03-15 | 2023-03-28 | P000170029 Machinery Shifting Man Tractor Head - Dxb 25988-Low Bed | 162942,P,P000170029 Machinery Shifting Man Tractor Head - Dxb 25988-Low Bed | 402 |  | Invoice attached
XXXD00130160 | Def Direct Costs at Site I-Product and material trailers | 2023-03-31 | P | PC | PCHG | W000320031 | 1 4 5011046 | COST/124 | 2023-03-15 | 2023-03-28 | W000320031 Machinery Shifting Low Bed Semi Trailer 65Ton | 162942,P,W000320031 Machinery Shifting Low Bed Semi Trailer 65Ton | 248 |  | Invoice attached
XXXD00130160 | Def Direct Costs at Site I-Product and material trailers | 2023-03-31 | P | PC | PCHG | W000320032 | 1 4 5011046 | COST/125 | 2023-03-04 | 2023-03-28 | W000320032 Machinery Shifting Low Bed Semi Trailer 65Ton | 162942,P,W000320032 Machinery Shifting Low Bed Semi Trailer 65Ton | 248 |  | Invoice attached
XXXD00130160 | Def Direct Costs at Site I-Product and material trailers | 2023-03-31 | P | PC | PCHG | W000320032 | 1 4 5011046 | COST/126 | 2023-03-11 | 2023-03-28 | W000320032 Machinery Shifting Low Bed Semi Trailer 65Ton | 162942,P,W000320032 Machinery Shifting Low Bed Semi Trailer 65Ton | 248 |  | Invoice attached
XXXD00130170 | Def Direct Costs at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160110 | 1 4 5010962 | COST/271 | 2023-03-03 | 2023-03-31 | Electric Cable - Single Core 240mm X 40 Mtr-Working | 162942,P, Electric Cable - Single Core 240mm X 40 Mtr-Working | 962.5 |  | Invoice attached
XXXD00130170 | Def Direct Costs at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160110 | 1 4 5010962 | COST/273 | 2023-03-10 | 2023-03-31 | Electric Cable - Single Core 240mm X 40 Mtr-Working | 162942,P, Electric Cable - Single Core 240mm X 40 Mtr-Working | 962.5 |  | Invoice attached
XXXD00130170 | Def Direct Costs at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160110 | 1 4 5010962 | COST/275 | 2023-03-17 | 2023-03-31 | Electric Cable - Single Core 240mm X 40 Mtr-Working | 162942,P, Electric Cable - Single Core 240mm X 40 Mtr-Working | 962.5 |  | Invoice attached
XXXD00130170 | Def Direct Costs at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160110 | 1 4 5010962 | COST/277 | 2023-03-24 | 2023-03-31 | Electric Cable - Single Core 240mm X 40 Mtr-Working | 162942,P, Electric Cable - Single Core 240mm X 40 Mtr-Working | 962.5 |  | Invoice attached
XXXD00130170 | Def Direct Costs at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160110 | 1 4 5010962 | COST/279 | 2023-03-31 | 2023-03-31 | Electric Cable - Single Core 240mm X 40 Mtr-Working | 162942,P, Electric Cable - Single Core 240mm X 40 Mtr-Working | 550 |  | Invoice attached
XXXD00130170 | Def Direct Costs at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160110 | 1 4 5010962 | COST/281 | 2023-03-03 | 2023-03-31 | Distribution Board - 2500Ams-Working | 162942,P, Distribution Board - 2500Ams-Working | 444.29 |  | Invoice attached
XXXD00130170 | Def Direct Costs at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160110 | 1 4 5010962 | COST/283 | 2023-03-10 | 2023-03-31 | Distribution Board - 2500Ams-Working | 162942,P, Distribution Board - 2500Ams-Working | 444.29 |  | Invoice attached
XXXD00130170 | Def Direct Costs at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160110 | 1 4 5010962 | COST/285 | 2023-03-17 | 2023-03-31 | Distribution Board - 2500Ams-Working | 162942,P, Distribution Board - 2500Ams-Working | 444.29 |  | Invoice attached
XXXD00130170 | Def Direct Costs at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160110 | 1 4 5010962 | COST/287 | 2023-03-24 | 2023-03-31 | Distribution Board - 2500Ams-Working | 162942,P, Distribution Board - 2500Ams-Working | 444.29 |  | Invoice attached
XXXD00130170 | Def Direct Costs at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160110 | 1 4 5010962 | COST/289 | 2023-03-31 | 2023-03-31 | Distribution Board - 2500Ams-Working | 162942,P, Distribution Board - 2500Ams-Working | 253.88 |  | Invoice attached
XXXD00130170 | Def Direct Costs at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160110 | 1 4 5010962 | COST/291 | 2023-03-03 | 2023-03-31 | Electric Cable - Single Core 240mm X 80 Mtr-Working | 162942,P, Electric Cable - Single Core 240mm X 80 Mtr-Working | 2084.93 |  | Invoice attached
XXXD00130170 | Def Direct Costs at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160110 | 1 4 5010962 | COST/293 | 2023-03-10 | 2023-03-31 | Electric Cable - Single Core 240mm X 80 Mtr-Working | 162942,P, Electric Cable - Single Core 240mm X 80 Mtr-Working | 2084.93 |  | Invoice attached
XXXD00130170 | Def Direct Costs at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160110 | 1 4 5010962 | COST/295 | 2023-03-17 | 2023-03-31 | Electric Cable - Single Core 240mm X 80 Mtr-Working | 162942,P, Electric Cable - Single Core 240mm X 80 Mtr-Working | 2084.93 |  | Invoice attached
XXXD00130170 | Def Direct Costs at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160110 | 1 4 5010962 | COST/297 | 2023-03-24 | 2023-03-31 | Electric Cable - Single Core 240mm X 80 Mtr-Working | 162942,P, Electric Cable - Single Core 240mm X 80 Mtr-Working | 2084.93 |  | Invoice attached
XXXD00130170 | Def Direct Costs at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160110 | 1 4 5010962 | COST/299 | 2023-03-31 | 2023-03-31 | Electric Cable - Single Core 240mm X 80 Mtr-Working | 162942,P, Electric Cable - Single Core 240mm X 80 Mtr-Working | 1191.39 |  | Invoice attached
XXXD00130200 | Def Direct Costs at Site I-Masonry and concrete tools | 2023-03-31 | P | PC | PCHG | PTLT590049 | 1 4 5010962 | COST/419 | 2023-03-31 | 2023-03-31 | PTLT590049 Power Trowel | 162942,P,PTLT590049 Power Trowel | 115.07 |  | Invoice attached
XXXD00130295 | Def Direct Costs at Site I-Waste skip | 2023-03-31 | P | GL | JNL | 163016 | 163016 |  | 2023-03-30 | 2023-03-30 | Waste Management Fine Reversal-March 2023 | 163016,P,Waste Management Fine Reversal-March 2023 | -500 |  | Invoice attached
XXXD00130295 | Def Direct Costs at Site I-Waste skip | 2023-03-31 | P | GL | JNL | 162993 | 162993 |  | 2023-03-30 | 2023-03-30 | Waste Management-March 2023 | 162993,P,Waste Management-March 2023 | 17127.6 |  | Invoice attached
XXXD00130510 | Def Direct Costs at Site I-Pla | 2023-03-31 | P | FA | RCHG | S3135136 |  |  | 2023-03-04 | 2023-03-04 | S3135136-Light Tool Repair | 161086,P,S3135136-Light Tool Repair | 924.94 |  | Invoice attached
XXXD00130510 | Def Direct Costs at Site I-Pla | 2023-03-31 | P | FA | RCHG | S3135137 |  |  | 2023-03-04 | 2023-03-04 | S3135137-Light Tool Repair | 161087,P,S3135137-Light Tool Repair | 289.71 |  | Invoice attached
XXXD00130510 | Def Direct Costs at Site I-Pla | 2023-03-31 | P | FA | RCHG | S3135138 |  |  | 2023-03-04 | 2023-03-04 | S3135138-Light Tool Repair | 161088,P,S3135138-Light Tool Repair | 400 |  | Invoice attached
XXXD00130510 | Def Direct Costs at Site I-Pla | 2023-03-31 | P | FA | RCHG | S3135139 |  |  | 2023-03-04 | 2023-03-04 | S3135139-Light Tool Repair | 161089,P,S3135139-Light Tool Repair | 2695 |  | Invoice attached
XXXD00130510 | Def Direct Costs at Site I-Pla | 2023-03-31 | P | FA | RCHG | S3135141 |  |  | 2023-03-04 | 2023-03-04 | S3135141-Light Tool Repair | 161090,P,S3135141-Light Tool Repair | 372.92 |  | Invoice attached
XXXD00130510 | Def Direct Costs at Site I-Pla | 2023-03-31 | P | FA | RCHG | S3135142 |  |  | 2023-03-04 | 2023-03-04 | S3135142-Light Tool Repair | 161091,P,S3135142-Light Tool Repair | 1102.39 |  | Invoice attached
XXXD00130510 | Def Direct Costs at Site I-Pla | 2023-03-31 | P | FA | RCHG | S3134996 |  |  | 2023-03-04 | 2023-03-04 | S3134996-Light Tool Repair | 161100,P,S3134996-Light Tool Repair | 129.24 |  | Invoice attached
XXXD00130510 | Def Direct Costs at Site I-Pla | 2023-03-31 | P | FA | RCHG | S3135130 |  |  | 2023-03-04 | 2023-03-04 | S3135130-Light Tool Repair | 161101,P,S3135130-Light Tool Repair | 400 |  | Invoice attached
XXXD00130510 | Def Direct Costs at Site I-Pla | 2023-03-31 | P | FA | RCHG | S3134994 |  |  | 2023-03-04 | 2023-03-04 | S3134994-Light Tool Repair | 161125,P,S3134994-Light Tool Repair | 1179.47 |  | Invoice attached
XXXD00130510 | Def Direct Costs at Site I-Pla | 2023-03-31 | P | FA | RCHG | S3135133 |  |  | 2023-03-04 | 2023-03-04 | S3135133-Light Tool Repair | 161127,P,S3135133-Light Tool Repair | 393.07 |  | Invoice attached
XXXD00130510 | Def Direct Costs at Site I-Pla | 2023-03-31 | P | FA | RCHG | S3134586 |  |  | 2023-03-04 | 2023-03-04 | S3134586-Light Tool Repair | 161132,P,S3134586-Light Tool Repair | 100 |  | Invoice attached
XXXD00130510 | Def Direct Costs at Site I-Pla | 2023-03-31 | P | FA | RCHG | S3134680 |  |  | 2023-03-04 | 2023-03-04 | S3134680-Light Tool Repair | 161134,P,S3134680-Light Tool Repair | 17.69 |  | Invoice attached
XXXD00130510 | Def Direct Costs at Site I-Pla | 2023-03-31 | P | FA | RCHG | S3135467 |  |  | 2023-03-04 | 2023-03-04 | S3135467-I -Beam Cutting | 161136,P,S3135467-I -Beam Cutting | 475 |  | Invoice attached
XXXD00130510 | Def Direct Costs at Site I-Pla | 2023-03-31 | P | FA | RCHG | S3134992 |  |  | 2023-03-04 | 2023-03-04 | S3134992-Light Tool Repair | 161143,P,S3134992-Light Tool Repair | 187 |  | Invoice attached
XXXD00130510 | Def Direct Costs at Site I-Pla | 2023-03-31 | P | FA | RCHG | S3304948 |  |  | 2023-03-13 | 2023-03-13 | S3304948-Rerouting Temporary Air-Conditioner Pipe from Bond Lobby | 161993,P,S3304948-Rerouting Temporary Air-Conditioner Pipe from Bond Lobby | 11940 |  | Invoice attached
XXXD00130510 | Def Direct Costs at Site I-Pla | 2023-03-31 | P | FA | RCHG | S3304989 |  |  | 2023-03-13 | 2023-03-13 | S3304989-Third Party Certiciate for Tipping Skip (KTS009) | 162004,P,S3304989-Third Party Certiciate for Tipping Skip (KTS009) | 50 |  | Invoice attached
XXXD00130510 | Def Direct Costs at Site I-Pla | 2023-03-31 | P | FA | RCHG | S3136270 |  |  | 2023-03-30 | 2023-03-30 | S3136270-Repairing of Concrete Bucket | 162976,P,S3136270-Repairing of Concrete Bucket | 250 |  | Invoice attached
XXXD00130510 | Def Direct Costs at Site I-Pla | 2023-03-31 | P | FA | RCHG | S3135766 |  |  | 2023-03-30 | 2023-03-30 | S3135766-Supply of Torque Wrench & Torque Multiplier with Calibration Certification | 162981,P,S3135766-Supply of Torque Wrench & Torque Multiplier with Calibration Certification | 575 |  | Invoice attached
XXXD00130510 | Def Direct Costs at Site I-Pla | 2023-03-31 | P | FA | RCHG | S3135970 |  |  | 2023-03-30 | 2023-03-30 | S3135970-Concrete Bucket (KCB-010) Repair | 162983,P,S3135970-Concrete Bucket (KCB-010) Repair | 300 |  | Invoice attached
XXXD00130510 | Def Direct Costs at Site I-Pla | 2023-03-31 | P | FA | RCHG | S3135696 |  |  | 2023-03-30 | 2023-03-30 | S3135696-Light Tool Repair | 162985,P,S3135696-Light Tool Repair | 1604.19 |  | Invoice attached
XXXD00130510 | Def Direct Costs at Site I-Pla | 2023-03-31 | P | FA | RCHG | S3135542 |  |  | 2023-03-30 | 2023-03-30 | S3135542-Light Tool Repair | 162999,P,S3135542-Light Tool Repair | 187 |  | Invoice attached
XXXD00130510 | Def Direct Costs at Site I-Pla | 2023-03-31 | P | FA | RCHG | S3135544 |  |  | 2023-03-30 | 2023-03-30 | S3135544-Light Tool Repair | 163001,P,S3135544-Light Tool Repair | 372.69 |  | Invoice attached
XXXD00130510 | Def Direct Costs at Site I-Pla | 2023-03-31 | P | PC | PCHG | T039101439 | 1 4 5010962 | COST/233 | 2023-03-31 | 2023-03-31 | T039101439 Grab Prefabricated Concrete | 162942,P,T039101439 Grab Prefabricated Concrete | 1000 |  | Invoice attached
XXXD00130510 | Def Direct Costs at Site I-Pla | 2023-03-31 | P | PC | PCHG | KVS0010004 | 1 4 5010962 | COST/421 | 2023-03-31 | 2023-03-31 | KVS0010004 CAT & Ginny Cable Locator M/Kit | 162942,P,KVS0010004 CAT & Ginny Cable Locator M/Kit | 486 |  | Invoice attached
XXXD00130510 | Def Direct Costs at Site I-Pla | 2023-03-31 | P | PC | PCHG | KVS0010004 | 1 4 5010962 | COST/422 | 2023-03-31 | 2023-03-31 | KVS0010004 CAT & Ginny Cable Locator M/Kit-Holiday | 162942,P,KVS0010004 CAT & Ginny Cable Locator M/Kit-Holiday | 0
XXXD00130510 | Def Direct Costs at Site I-Pla | 2023-03-31 | P | FA | RCHG | S3304921 |  |  | 2023-03-31 | 2023-03-31 | S3304921-AC Relocation & Maintenance Works | 163208,P,S3304921-AC Relocation & Maintenance Works | 3010 |  | Invoice attached
XXXD00130510 | Def Direct Costs at Site I-Pla | 2023-03-31 | P | FA | RCHG | S3135306 |  |  | 2023-03-31 | 2023-03-31 | S3135306-Light Tool Repair | 163293,P,S3135306-Light Tool Repair | 462.16 |  | Invoice attached
XXXD00130510 | Def Direct Costs at Site I-Pla | 2023-03-31 | P | FA | RCHG | S3135152 |  |  | 2023-03-31 | 2023-03-31 | S3135152-Light Tool Repair | 163302,P,S3135152-Light Tool Repair | 492.04 |  | Invoice attached
XXXD00130510 | Def Direct Costs at Site I-Pla | 2023-03-31 | P | FA | RCHG | S3135058 |  |  | 2023-03-31 | 2023-03-31 | S3135058-Light Tool Repair | 163305,P,S3135058-Light Tool Repair | 676.07 |  | Invoice attached
XXXD00134110 | Def Direct Costs at Site E-Passenger motor vehicles | 2023-03-31 | P | GL | JNL | 162635 | 162635 |  | 2023-03-31 | 2023-03-31 | P000080667-KCE Salik Month Of March 2023 | 162635,P,P000080667-KCE Salik Month Of March 2023 | 296 |  | Invoice attached
XXXD00134110 | Def Direct Costs at Site E-Passenger motor vehicles | 2023-03-31 | P | GL | JNL | 162635 | 162635 |  | 2023-03-31 | 2023-03-31 | P000080664-KCE Salik Month Of March 2023 | 162635,P,P000080664-KCE Salik Month Of March 2023 | 344 |  | Invoice attached
XXXD00134110 | Def Direct Costs at Site E-Passenger motor vehicles | 2023-03-31 | P | GL | JNL | 162635 | 162635 |  | 2023-03-31 | 2023-03-31 | P000080687-KCE Salik Month Of March 2023 | 162635,P,P000080687-KCE Salik Month Of March 2023 | 232 |  | Invoice attached
XXXD00134110 | Def Direct Costs at Site E-Passenger motor vehicles | 2023-03-31 | P | GL | JNL | 162635 | 162635 |  | 2023-03-31 | 2023-03-31 | P000080685-KCE Salik Month Of March 2023 | 162635,P,P000080685-KCE Salik Month Of March 2023 | 400 |  | Invoice attached
XXXD00134110 | Def Direct Costs at Site E-Passenger motor vehicles | 2023-03-31 | P | GL | JNL | 162635 | 162635 |  | 2023-03-31 | 2023-03-31 | P000080690-KCE Salik Month Of March 2023 | 162635,P,P000080690-KCE Salik Month Of March 2023 | 272 |  | Invoice attached
XXXD00134110 | Def Direct Costs at Site E-Passenger motor vehicles | 2023-03-31 | P | GL | JNL | 162635 | 162635 |  | 2023-03-31 | 2023-03-31 | P000080681-KCE Salik Month Of March 2023 | 162635,P,P000080681-KCE Salik Month Of March 2023 | 256 |  | Invoice attached
XXXD00134110 | Def Direct Costs at Site E-Passenger motor vehicles | 2023-03-31 | P | GL | JNL | 162635 | 162635 |  | 2023-03-31 | 2023-03-31 | P000080694-KCE Salik Month Of March 2023 | 162635,P,P000080694-KCE Salik Month Of March 2023 | 56 |  | Invoice attached
XXXD00134110 | Def Direct Costs at Site E-Passenger motor vehicles | 2023-03-31 | P | GL | JNL | 162635 | 162635 |  | 2023-03-31 | 2023-03-31 | P000080696-KCE Salik Month Of March 2023 | 162635,P,P000080696-KCE Salik Month Of March 2023 | 336 |  | Invoice attached
XXXD00134110 | Def Direct Costs at Site E-Passenger motor vehicles | 2023-03-31 | P | GL | JNL | 162635 | 162635 |  | 2023-03-31 | 2023-03-31 | P000080701-KCE Salik Month Of March 2023 | 162635,P,P000080701-KCE Salik Month Of March 2023 | 384 |  | Invoice attached
XXXD00134120 | Def Direct Costs at Site E-Product and material transport vehicles | 2023-03-31 | P | PL | PINN | GOLD010 | 2303PL001213 | HT 14682 | 2023-03-30 | 2023-03-01 | Hire Pickup Salik -February 2023 | 28/02/23,HT 14682,GOLD010,Golden Palace Heavy and Light Trucks Transport LLC | 918 |  | Invoice attached
XXXD00134120 | Def Direct Costs at Site E-Product and material transport vehicles | 2023-03-31 | P | GL | JNL | 162633 | 162633 |  | 2023-03-31 | 2023-03-31 | TA00033100-Salik For February 2023 | 162633,P,TA00033100-Salik For February 2023 | 315 |  | Invoice attached
XXXD00134120 | Def Direct Costs at Site E-Product and material transport vehicles | 2023-03-31 | P | GL | JNL | 162633 | 162633 |  | 2023-03-31 | 2023-03-31 | TA00033109-Salik For February 2023 | 162633,P,TA00033109-Salik For February 2023 | 596.4 |  | Invoice attached
XXXP00130110 | Def Prelims at Site I-Passenger motor vehicles | 2023-03-31 | P | PC | PCHG | P000080690 | 1 4 5010962 | COST/1 | 2023-03-31 | 2023-03-31 | P000080690 Ashok Leyland Bus - DXB 15611M | 162942,P,P000080690 Ashok Leyland Bus - DXB 15611M | 5110 |  | Invoice attached
XXXP00130110 | Def Prelims at Site I-Passenger motor vehicles | 2023-03-31 | P | PC | PCHG | TA00033109 | 1 4 5010962 | COST/52 | 2023-03-31 | 2023-03-31 | TA00033109 TOYOTA COASTER HI ROOF 23STR 4.0D MANUAL | 162942,P,TA00033109 TOYOTA COASTER HI ROOF 23STR 4.0D MANUAL | 4680 |  | Invoice attached
XXXP00130110 | Def Prelims at Site I-Passenger motor vehicles | 2023-03-31 | P | PC | PCHG | TA00033100 | 1 4 5010962 | COST/63 | 2023-03-31 | 2023-03-31 | TA00033100 TOYOTA COASTER HI ROOF 23STR 4.0D MANUAL | 162942,P,TA00033100 TOYOTA COASTER HI ROOF 23STR 4.0D MANUAL | 4680 |  | Invoice attached
XXXP00130110 | Def Prelims at Site I-Passenger motor vehicles | 2023-03-31 | P | PC | PCHG | P000080687 | 1 4 5010962 | COST/66 | 2023-03-27 | 2023-03-31 | P000080687 Ashok Leyland Bus - DXB 85148H | 162942,P,P000080687 Ashok Leyland Bus - DXB 85148H | 4536 |  | Invoice attached
XXXP00130110 | Def Prelims at Site I-Passenger motor vehicles | 2023-03-31 | P | PC | PCHG | P000080694 | 1 4 5010962 | COST/67 | 2023-03-31 | 2023-03-31 | P000080694 Ashok Leyland 59 Seat Bus-DXB 72356 W | 162942,P,P000080694 Ashok Leyland 59 Seat Bus-DXB 72356 W | 737.75 |  | Invoice attached
XXXP00130110 | Def Prelims at Site I-Passenger motor vehicles | 2023-03-31 | P | PC | PCHG | P000080701 | 1 4 5010962 | COST/82 | 2023-03-31 | 2023-03-31 | P000080701 Ashok Leyland 71 Seat Bus | 162942,P,P000080701 Ashok Leyland 71 Seat Bus | 5850 |  | Invoice attached
XXXP00130110 | Def Prelims at Site I-Passenger motor vehicles | 2023-03-31 | P | PC | PCHG | P000080681 | 1 4 5010962 | COST/97 | 2023-03-31 | 2023-03-31 | P000080681 Ashok Leyland Bus - DXB 86848H | 162942,P,P000080681 Ashok Leyland Bus - DXB 86848H | 5110 |  | Invoice attached
XXXP00130110 | Def Prelims at Site I-Passenger motor vehicles | 2023-03-31 | P | PC | PCHG | P000080664 | 1 4 5010962 | COST/98 | 2023-03-31 | 2023-03-31 | P000080664 Ashok Leyland Bus - Dxb 52753J | 162942,P,P000080664 Ashok Leyland Bus - Dxb 52753J | 5110 |  | Invoice attached
XXXP00130110 | Def Prelims at Site I-Passenger motor vehicles | 2023-03-31 | P | PC | PCHG | P000080696 | 1 4 5010962 | COST/99 | 2023-03-31 | 2023-03-31 | P000080696 Ashok Leyland 59 Seat Bus-DXB 72353 W | 162942,P,P000080696 Ashok Leyland 59 Seat Bus-DXB 72353 W | 5610 |  | Invoice attached
XXXP00130110 | Def Prelims at Site I-Passenger motor vehicles | 2023-03-31 | P | PC | PCHG | P000080685 | 1 4 5010962 | COST/120 | 2023-03-31 | 2023-03-31 | P000080685 Ashok Leyland Bus - DXB 86783H With IVMS | 162942,P,P000080685 Ashok Leyland Bus - DXB 86783H With IVMS | 5110 |  | Invoice attached
XXXP00130110 | Def Prelims at Site I-Passenger motor vehicles | 2023-03-31 | P | PC | PCHG | P000080660 | 1 4 5010962 | COST/177 | 2023-03-02 | 2023-03-31 | P000080660 Ashok Leyland Bus - Dxb 92791Q With IVMS | 162942,P,P000080660 Ashok Leyland Bus - Dxb 92791Q With IVMS | 336 |  | Invoice attached
XXXP00130110 | Def Prelims at Site I-Passenger motor vehicles | 2023-03-31 | P | PC | PCHG | P000080667 | 1 4 5010962 | COST/178 | 2023-03-31 | 2023-03-31 | P000080667 Ashok Leyland Bus - Dxb 51596J | 162942,P,P000080667 Ashok Leyland Bus - Dxb 51596J | 4872 |  | Invoice attached
XXXP00130170 | Def Prelims at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160110 | 1 4 5010962 | COST/3 | 2023-03-03 | 2023-03-31 | Generator - 650 KVA-Working | 162942,P, Generator - 650 KVA-Working | 2961.55 |  | Invoice attached
XXXP00130170 | Def Prelims at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160110 | 1 4 5010962 | COST/5 | 2023-03-10 | 2023-03-31 | Generator - 650 KVA-Working | 162942,P, Generator - 650 KVA-Working | 2961.55 |  | Invoice attached
XXXP00130170 | Def Prelims at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160110 | 1 4 5010962 | COST/7 | 2023-03-17 | 2023-03-31 | Generator - 650 KVA-Working | 162942,P, Generator - 650 KVA-Working | 2961.55 |  | Invoice attached
XXXP00130170 | Def Prelims at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160110 | 1 4 5010962 | COST/9 | 2023-03-24 | 2023-03-31 | Generator - 650 KVA-Working | 162942,P, Generator - 650 KVA-Working | 2961.55 |  | Invoice attached
XXXP00130170 | Def Prelims at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160110 | 1 4 5010962 | COST/11 | 2023-03-31 | 2023-03-31 | Generator - 650 KVA-Working | 162942,P, Generator - 650 KVA-Working | 1692.31 |  | Invoice attached
XXXP00130170 | Def Prelims at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160109 | 1 4 5010962 | COST/13 | 2023-03-03 | 2023-03-31 | Generator - 500 KVA-Working | 162942,P, Generator - 500 KVA-Working | 2180.87 |  | Invoice attached
XXXP00130170 | Def Prelims at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160109 | 1 4 5010962 | COST/15 | 2023-03-10 | 2023-03-31 | Generator - 500 KVA-Working | 162942,P, Generator - 500 KVA-Working | 2180.87 |  | Invoice attached
XXXP00130170 | Def Prelims at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160109 | 1 4 5010962 | COST/17 | 2023-03-17 | 2023-03-31 | Generator - 500 KVA-Working | 162942,P, Generator - 500 KVA-Working | 2180.87 |  | Invoice attached
XXXP00130170 | Def Prelims at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160109 | 1 4 5010962 | COST/19 | 2023-03-24 | 2023-03-31 | Generator - 500 KVA-Working | 162942,P, Generator - 500 KVA-Working | 2180.87 |  | Invoice attached
XXXP00130170 | Def Prelims at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160109 | 1 4 5010962 | COST/21 | 2023-03-31 | 2023-03-31 | Generator - 500 KVA-Working | 162942,P, Generator - 500 KVA-Working | 1246.21 |  | Invoice attached
XXXP00130170 | Def Prelims at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160110 | 1 4 5010962 | COST/23 | 2023-03-03 | 2023-03-31 | Generator - 650 KVA-Working | 162942,P, Generator - 650 KVA-Working | 1269.23 |  | Invoice attached
XXXP00130170 | Def Prelims at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160110 | 1 4 5010962 | COST/25 | 2023-03-10 | 2023-03-31 | Generator - 650 KVA-Working | 162942,P, Generator - 650 KVA-Working | 2961.55 |  | Invoice attached
XXXP00130170 | Def Prelims at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160110 | 1 4 5010962 | COST/27 | 2023-03-17 | 2023-03-31 | Generator - 650 KVA-Working | 162942,P, Generator - 650 KVA-Working | 2961.55 |  | Invoice attached
XXXP00130170 | Def Prelims at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160110 | 1 4 5010962 | COST/29 | 2023-03-24 | 2023-03-31 | Generator - 650 KVA-Working | 162942,P, Generator - 650 KVA-Working | 2961.55 |  | Invoice attached
XXXP00130170 | Def Prelims at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160110 | 1 4 5010962 | COST/31 | 2023-03-31 | 2023-03-31 | Generator - 650 KVA-Working | 162942,P, Generator - 650 KVA-Working | 1692.31 |  | Invoice attached
XXXP00130170 | Def Prelims at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160109 | 1 4 5010962 | COST/33 | 2023-03-03 | 2023-03-31 | Cables - (1C 240mm2 40Mtr x 30 Runs =1200Mtrs)-Working | 162942,P, Cables - (1C 240mm2 40Mtr x 30 Runs =1200Mtrs)-Working | 2665.43 |  | Invoice attached
XXXP00130170 | Def Prelims at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160109 | 1 4 5010962 | COST/35 | 2023-03-10 | 2023-03-31 | Cables - (1C 240mm2 40Mtr x 30 Runs =1200Mtrs)-Working | 162942,P, Cables - (1C 240mm2 40Mtr x 30 Runs =1200Mtrs)-Working | 2665.43 |  | Invoice attached
XXXP00130170 | Def Prelims at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160109 | 1 4 5010962 | COST/37 | 2023-03-17 | 2023-03-31 | Cables - (1C 240mm2 40Mtr x 30 Runs =1200Mtrs)-Working | 162942,P, Cables - (1C 240mm2 40Mtr x 30 Runs =1200Mtrs)-Working | 2665.43 |  | Invoice attached
XXXP00130170 | Def Prelims at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160109 | 1 4 5010962 | COST/39 | 2023-03-24 | 2023-03-31 | Cables - (1C 240mm2 40Mtr x 30 Runs =1200Mtrs)-Working | 162942,P, Cables - (1C 240mm2 40Mtr x 30 Runs =1200Mtrs)-Working | 2665.43 |  | Invoice attached
XXXP00130170 | Def Prelims at Site I-Power generators | 2023-03-31 | P | PC | PCHG | 2611160109 | 1 4 5010962 | COST/41 | 2023-03-31 | 2023-03-31 | Cables - (1C 240mm2 40Mtr x 30 Runs =1200Mtrs)-Working | 162942,P, Cables - (1C 240mm2 40Mtr x 30 Runs =1200Mtrs)-Working | 1523.1 |  | Invoice attached
| Total Plant Cost ( AED ) | [11 empty] | 567678.27