## SUMMARY
DORCHESTER HOTEL & RESIDENCIES
INTERNAL GLAZING WORK | [7 empty] | 2022-08-01
JOSEPH DECORATIVE GALSS | [7 empty] | KCE PC 07
SN | WORK SCOPE | AMOUNT | WORK DONE UNDER ROBERTS | REMAINIING WORKS | WORK DONE UNDER KCE
[5 empty] | PREVIOUS | THIS MONTH | CUMULATIVE
A | Contract Main Scope | 2000000 | 995486 | 1004514 | 413177.7679 | 19176.1121 | 21.62% | 432353.88
B | Provisional Sum for Presidential/Royal suites | 72163 | 0 | 72163
Sub-Totals |  | 2072163 | 995486 | 1076677 | 413177.7679 | 19176.1121 | 20.86% | 432353.88
VARIATIONS
VO.01 | BOH glazed partitions, doors and mirrors (subject to remeasure) | 59858 | 0 | 59858 | 393.92 | 46798.08 | 78.84% | 47192
VO.02 | Mirrored cladding to D3b and D20 doors (subject to remeasure) | 126302 | 0 | 126302 | 0 | 0 | 0% | 0
Sub-Totals |  | 186160 | 0 | 186160 | 393.92 | 46798.08 | 25.35% | 47192
TOTAL AMOUNT |  | 2072163 | 995486 | 1262837 | 413571.6879 | 65974.1921 | 23.14% | 479545.88
| Advance Payment | 252477.4 |  | 252477.4 | 252477.4 | 0 |  | 252477.4
| Advance Payment Recovery |  |  |  | -82714.3376 | -13194.8384 |  | -95909.176
[5 empty] | 583334.7504 | 52779.3536 |  | 636114.104

## BOQ
Joseph Decorative Glass - Certification
SL.NO | DESCRIPTION | Door Type | Room Type | No of Room | JDG SPECIFICATION | As per BOQ |  |  |  | CERTIFIED - OCI (Feb 2022)
[6 empty] | UNIT | QTY | RATE | AMOUNT IN AED. | UNIT | QTY | RATE | AMOUNT IN AED.
1 | Standard Guestroom - 1A (8 Nos) |  |  | 8
| Door HO-GD-02 (800X2400) | HO-GD-02 | 1A | 8 | Frameless Glass Door: 12mm thick gradient frosted tempered float glass with polished edges fixed with wall to glass hinges. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 16 | 843.61 | 13497.76 | No | 16 | 843.61 | 13497.76 |  | FALSE
|  |  | 1A | 8 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 16 | 470 | 7520 | No | 16 | 470 | 7520 |  | FALSE
2 | Standard Guestroom - 1C (2 Nos) |  |  | 2 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
| Door HO-GD-02 (800X2400) | HO-GD-02 | 1C | 2 | Frameless Glass Door: 12mm thick gradient frosted tempered float glass with polished edges fixed with wall to glass hinges. Ironmongeries measured and quoted separately. Over all size: 800 x 2400mm high | No | 4 | 843.61 | 3374.44 | No | 4 | 843.61 | 3374.44 |  | FALSE
|  |  | 1C | 2 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 4 | 470 | 1880 | No | 4 | 470 | 1880 |  | FALSE
3 | Standard Guestroom - 1B (6 Nos) |  |  | 6 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
4 | Standard Guestrooms - 2A (13 Nos) |  |  | 13 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
| Door HO-GD-02 (800X2400) | HO-GD-02 | 2A | 13 | Frameless Glass Door: 12mm thick gradient frosted tempered float glass with polished edges fixed with wall to glass hinges. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 26 | 843.61 | 21933.86 | No | 24 | 843.61 | 20246.64 |  | FALSE
|  |  | 2A | 13 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 26 | 470 | 12220 | No | 24 | 470 | 11280 |  | FALSE
5 | Standard Guestrooms - 2B (16 Nos) |  |  | 16 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
| Door HO-GD-02 (800X2400) | HO-GD-02 | 2B | 16 | Frameless Glass Door: 12mm thick gradient frosted tempered float glass with polished edges fixed with wall to glass hinges. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 32 | 843.61 | 26995.52 | No | 32 | 843.61 | 26995.52 |  | FALSE
|  |  | 2B | 16 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 32 | 470 | 15040 | No | 32 | 470 | 15040 |  | FALSE
6 | Standard Guestrooms - 2C (8 Nos) |  |  | 8 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
| Door HO-GD-02 (800X2400) | HO-GD-02 | 2C | 8 | Frameless Glass Door: 12mm thick gradient frosted tempered float glass with polished edges fixed with wall to glass hinges. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 16 | 843.61 | 13497.76 | No | 14 | 843.61 | 11810.54 |  | FALSE
|  |  | 2C | 8 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 16 | 470 | 7520 | No | 14 | 470 | 6580 |  | FALSE
7 | Standard Guestrooms - 2D (7 Nos) |  |  | 7 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
| Door HO-GD-02 (800X2400) | HO-GD-02 | 2D | 7 | Frameless Glass Door: 12mm thick gradient frosted tempered float glass with polished edges fixed with wall to glass hinges. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 14 | 843.61 | 11810.54 | No | 14 | 843.61 | 11810.54 |  | FALSE
|  |  | 2D | 7 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 14 | 470 | 6580 | No | 14 | 470 | 6580 |  | FALSE
8 | Standard Guestrooms - 2E (9 Nos) |  |  | 9 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
| Door HO-GD-02 (800X2400) | HO-GD-02 | 2E | 9 | Frameless Glass Door: 12mm thick gradient frosted tempered float glass with polished edges fixed with wall to glass hinges. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 18 | 843.61 | 15184.98 | No | 18 | 843.61 | 15184.98 |  | FALSE
|  |  | 2E | 9 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 18 | 470 | 8460 | No | 18 | 470 | 8460 |  | FALSE
9 | Standard Guestrooms - 2F (8 Nos) |  |  | 8 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
| Door HO-GD-02 (800X2400) | HO-GD-02 | 2F | 8 | Frameless Glass Door: 12mm thick gradient frosted tempered float glass with polished edges fixed with wall to glass hinges. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 16 | 843.61 | 13497.76 | No | 16 | 843.61 | 13497.76 |  | FALSE
|  |  | 2F | 8 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 16 | 470 | 7520 | No | 16 | 470 | 7520 |  | FALSE
10 | Standard Guestrooms - 2G (9 Nos) |  |  | 9 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
| Door HO-GD-02 (800X2400) | HO-GD-02 | 2G | 9 | Frameless Glass Door: 12mm thick gradient frosted tempered float glass with polished edges fixed with wall to glass hinges. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 18 | 843.61 | 15184.98 | No | 18 | 843.61 | 15184.98 |  | FALSE
|  |  | 2G | 9 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 18 | 470 | 8460 | No | 18 | 470 | 8460 |  | FALSE
11 | Standard Guestrooms - 2H (1 Nos) |  |  | 1 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
| Door HO-GD-02 (800X2400) | HO-GD-02 | 2H | 1 | Frameless Glass Door: 12mm thick gradient frosted tempered float glass with polished edges fixed with wall to glass hinges. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 2 | 843.61 | 1687.22 | No | 2 | 843.61 | 1687.22 |  | FALSE
|  |  | 2H | 1 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 2 | 470 | 940 | No | 2 | 470 | 940 |  | FALSE
12 | Standard Guestrooms - 3A (15 Nos) |  |  | 15 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
| Door HO-GD-01 (840X2420) | HO-GD-01 | 3A | 15 | Framed Sliding Glass Door: 6mm thick clear Silver Float mirror with polished edges bonded on both sides of door including 316 Grade stainless steel frame all around in Brass finish. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 15 | 3793.98 | 56909.7 | No | 15 | 3793.98 | 56909.7 |  | FALSE
|  |  | 3A | 15 | Ironmongeries for the above item: Manual sliding mechanism with customized back to back handle in Brass finish. | No | 15 | 1985 | 29775 | No | 15 | 1985 | 29775 |  | FALSE
| Door HO-GD-02 (800X2400) | HO-GD-02 | 3A | 15 | Frameless Glass Door: 12mm thick gradient frosted tempered float glass with polished edges fixed with wall to glass hinges. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 30 | 843.61 | 25308.3 | No | 30 | 843.61 | 25308.3 |  | FALSE
|  |  | 3A | 15 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 30 | 470 | 14100 | No | 30 | 470 | 14100 |  | FALSE
13 | Standard Guestrooms - 3C (9 Nos) |  |  | 9 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
| Door HO-GD-01 (840X2420) | HO-GD-01 | 3C | 9 | Framed Sliding Glass Door: 6mm thick clear Silver Float mirror with polished edges bonded on both sides of door including 316 Grade stainless steel frame all around in Brass finish. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 9 | 3793.98 | 34145.82 | No | 9 | 3793.98 | 34145.82 |  | FALSE
|  |  | 3C | 9 | Ironmongeries for the above item: Manual sliding mechanism with customized back to back handle in Brass finish. | No | 9 | 1985 | 17865 | No | 9 | 1985 | 17865 |  | FALSE
| Door HO-GD-02 (800X2400) | HO-GD-02 | 3C | 9 | Frameless Glass Door: 12mm thick gradient frosted tempered float glass with polished edges fixed with wall to glass hinges. Ironmongeries measured and quoted separately. Over all size: 800 x 2400mm high | No | 18 | 796.8 | 14342.4 | No | 18 | 796.8 | 14342.4 |  | FALSE
|  |  | 3C | 9 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 18 | 470 | 8460 | No | 18 | 470 | 8460 |  | FALSE
14 | Standard Guestrooms - 3D (20 Nos) |  |  | 20 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
| Door HO-GD-01 (840X2420) | HO-GD-01 | 3D | 20 | Framed Sliding Glass Door: 6mm thick clear Silver Float mirror with polished edges bonded on both sides of door including 316 Grade stainless steel frame all around in Brass finish. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 20 | 3793.98 | 75879.6 | No | 20 | 3793.98 | 75879.6 |  | FALSE
|  |  | 3D | 20 | Ironmongeries for the above item: Manual sliding mechanism with customized back to back handle in Brass finish. | No | 20 | 1985 | 39700 | No | 20 | 1985 | 39700 |  | FALSE
| Door HO-GD-02 (800X2400) | HO-GD-02 | 3D | 20 | Frameless Glass Door: 12mm thick gradient frosted tempered float glass with polished edges fixed with wall to glass hinges. Ironmongeries measured and quoted separately. Over all size: 800 x 2400mm high | No | 40 | 843.61 | 33744.4 | No | 40 | 843.61 | 33744.4 |  | FALSE
|  |  | 3D | 20 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 40 | 470 | 18800 | No | 40 | 470 | 18800 |  | FALSE
15 | Standard Guestrooms - 3F (9 Nos) |  |  | 9 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
| Door HO-GD-01 (840X2420) | HO-GD-01 | 3F | 9 | Framed Sliding Glass Door: 6mm thick clear Silver Float mirror with polished edges bonded on both sides of door including 316 Grade stainless steel frame all around in Brass finish. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 9 | 3793.98 | 34145.82 | No | 8 | 3793.98 | 30351.84 |  | FALSE
|  |  | 3F | 9 | Ironmongeries for the above item: Manual sliding mechanism with customized back to back handle in Brass finish. | No | 9 | 1985 | 17865 | No | 8 | 1985 | 15880 |  | FALSE
| Door HO-GD-02 (800X2400) | HO-GD-02 | 3F | 9 | Frameless Glass Door: 12mm thick gradient frosted tempered float glass with polished edges fixed with wall to glass hinges. Ironmongeries measured and quoted separately. Over all size: 840 x 2400mm high | No | 18 | 843.61 | 15184.98 | No | 18 | 843.61 | 15184.98 |  | FALSE
|  |  | 3F | 9 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 18 | 470 | 8460 | No | 18 | 470 | 8460 |  | FALSE
16 | Standard Guestrooms - 3G (4 Nos) |  |  | 4 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
| Door HO-GD-01 (840X2420) | HO-GD-01 | 3G | 4 | Framed Sliding Glass Door: 6mm thick clear Silver Float mirror with polished edges bonded on both sides of door including 316 Grade stainless steel frame all around in Brass finish. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 4 | 3793.98 | 15175.92 | No | 4 | 3793.98 | 15175.92 |  | FALSE
|  |  | 3G | 4 | Ironmongeries for the above item: Manual sliding mechanism with customized back to back handle in Brass finish. | No | 4 | 1985 | 7940 | No | 4 | 1985 | 7940 |  | FALSE
| Door HO-GD-02 (800X2400) | HO-GD-02 | 3G | 4 | Frameless Glass Door: 12mm thick gradient frosted tempered float glass with polished edges fixed with wall to glass hinges. Ironmongeries measured and quoted separately. Over all size: 840 x 2400mm high | No | 8 | 843.61 | 6748.88 | No | 8 | 843.61 | 6748.88 |  | FALSE
|  |  | 3G | 4 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 8 | 470 | 3760 | No | 8 | 470 | 3760 |  | FALSE
17 | Junior Suite - 4A (4 Nos) |  |  | 4 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
| Door HO-GD-01 (840X2420) | HO-GD-01 | 4A | 4 | Framed Sliding Glass Door: 6mm thick clear Silver Float mirror with polished edges bonded on both sides of door including 316 Grade stainless steel frame all around in Brass finish. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 4 | 3793.98 | 15175.92 | No | 4 | 3793.98 | 15175.92 |  | FALSE
|  |  | 4A | 4 | Ironmongeries for the above item: Manual sliding mechanism with customized back to back handle in Brass finish. | No | 4 | 1985 | 7940 | No | 4 | 1985 | 7940 |  | FALSE
| Door HO-GD-02 (800X2400) | HO-GD-02 | 4A | 4 | Frameless Glass Door: 12mm thick gradient frosted tempered float glass with polished edges fixed with wall to glass hinges. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 8 | 843.61 | 6748.88 | No | 8 | 843.61 | 6748.88 |  | FALSE
|  |  | 4A | 4 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 8 | 470 | 3760 | No | 8 | 470 | 3760 |  | FALSE
| HO-GD-10 |  | 4A | 4 | Framed Glass Door: 10mm thick low iron clear tempered glass with polished edges. Glass door fixed with manual sliding mechanism and fixed glass fixed with stainless steel frame in Brass finish. Over all size: 3000 x 2550mm high | No | 4 | 8825 | 35300 | No | 4 | 8825 | 35300 |  | FALSE
|  |  | 4A | 4 | Ironmongeries for the above item: Manual sliding mechanism with customized back to back handle in Brass finish. | No | 4 | 3290 | 13160 | No | 4 | 3290 | 13160 |  | FALSE
18 | Junior Suite - 4B (1 Nos) |  |  | 1 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
| Door HO-GD-01 (840X2420) | HO-GD-01 | 4B | 1 | Framed Sliding Glass Door: 6mm thick clear Silver Float mirror with polished edges bonded on both sides of door including 316 Grade stainless steel frame all around in Brass finish. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 1 | 3793.98 | 3793.98 | No | 1 | 3793.98 | 3793.98 |  | FALSE
|  |  | 4B | 1 | Ironmongeries for the above item: Manual sliding mechanism with customized back to back handle in Brass finish. | No | 1 | 1985 | 1985 | No | 1 | 1985 | 1985 |  | FALSE
| Door HO-GD-02 (800X2400) | HO-GD-02 | 4B | 1 | Frameless Glass Door: 12mm thick gradient frosted tempered float glass with polished edges fixed with wall to glass hinges. Ironmongeries measured and quoted separately. Over all size: 840 x 2400mm high | No | 2 | 843.61 | 1687.22 | No | 2 | 843.61 | 1687.22 |  | FALSE
|  |  | 4B | 1 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 2 | 470 | 940 | No | 2 | 470 | 940 |  | FALSE
| HO-GD-10 |  | 4B | 1 | Framed Glass Door: 10mm thick low iron clear tempered glass with polished edges. Glass door with manual sliding mechanism and fixed glass with stainless steel frame in Brass finish. Over all size: 3000 x 2550mm high | No | 1 | 9490.5 | 9490.5 | No | 1 | 9490.5 | 9490.5 |  | FALSE
|  |  | 4B | 1 | Ironmongeries for the above item: Manual sliding mechanism with customized back to back handle in Brass finish. | No | 1 | 2980 | 2980 | No | 1 | 2980 | 2980 |  | FALSE
19 | Junior Suite - 5A (9 Nos) |  |  | 9 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
| Door HO-GD-01 (840X2420) | HO-GD-01 | 5A | 9 | Framed Sliding Glass Door: 6mm thick clear Silver Float mirror with polished edges bonded on both sides of door including 316 Grade stainless steel frame all around in Brass finish. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 9 | 3793.98 | 34145.82 | No | 9 | 3793.98 | 34145.82 |  | FALSE
|  |  | 5A | 9 | Ironmongeries for the above item: Manual sliding mechanism with customized back to back handle in Brass finish. | No | 9 | 1985 | 17865 | No | 9 | 1985 | 17865 |  | FALSE
| Door HO-GD-02 (800X2400) | HO-GD-02 | 5A | 9 | Frameless Glass Door: 12mm thick gradient frosted tempered float glass with polished edges fixed with wall to glass hinges. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 18 | 843.61 | 15184.98 | No | 14 | 843.61 | 11810.54 |  | FALSE
|  |  | 5A | 9 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 18 | 470 | 8460 | No | 14 | 470 | 6580 |  | FALSE
20 | Junior Suite - 6A (5 Nos) |  |  | 5 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
| Door HO-GD-02 (800X2400) | HO-GD-02 | 6A | 5 | Frameless Glass Door: 12mm thick gradient frosted tempered float glass with polished edges fixed with wall to glass hinges. Ironmongeries measured and quoted separately. Over all size: 8400 x 2420mm high | No | 10 | 843.61 | 8436.1 | No | 10 | 843.61 | 8436.1 |  | FALSE
|  |  | 6A | 5 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 10 | 470 | 4700 | No | 10 | 470 | 4700 |  | FALSE
21 | 1 Bed Duplex Suite - 7A (5 Nos) |  |  | 5 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
| Door HO-GD-01 (840X2420) | HO-GD-01 | 8A | 5 | Framed Sliding Glass Door: 6mm thick clear Silver Float mirror with polished edges bonded on both sides of door including 316 Grade stainless steel frame all around in Brass finish. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No |  | 3793.98 |  |  | 0 |  |  |  | FALSE
|  |  | 8A | 5 | Ironmongeries for the above item: Manual sliding mechanism with customized back to back handle in Brass finish. | No |  | 1985 |  |  | 0 |  |  |  | FALSE
| Door HO-GD-02 (800X2400) | HO-GD-02 | 6A | 5 | Frameless Glass Door: 12mm thick gradient frosted tempered float glass with polished edges fixed with wall to glass hinges. Ironmongeries measured and quoted separately. Over all size: 8400 x 2420mm high | No |  | 843.61 |  |  | 0 |  |  |  | FALSE
|  |  | 6A | 5 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No |  | 470 |  |  | 0 |  |  |  | FALSE
| Shower Cubical GD-09 |  | 7A | 5 | Framed Glass Door with Partition: 12mm thick clear tempered low iron glass with polished edges. Fixed glass fixed with stainless steel frame and glass door fixed with glass to glass hinges. Ironmongeries measured and quoted separately. Over all size: 4975 x 2450mm (In joints) | No | 5 | 13485.41 | 67427.05 | No | 5 | 13485.41 | 53941.64 |  | FALSE
|  |  | 7A | 5 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 5 | 470 | 2350 | No | 5 | 470 | 1880 |  | FALSE
| Mirror paneling in HTL-GL-01 Extra clear Mirror (5910 x 1960) as per drawing D1BS-707-200 |  | 7A | 5 | 6mm thick clear Silver Float mirror with polished edges fixed on 12mm thick MDF including carcass. Over all size: 1960 x 5910mm high (In joints) | No | 5 | 3226.86 | 16134.3 | No |  | 3226.86 | 0 |  | FALSE
| Metal frame for Mirror Paneling HTL-ME-01 Brushed Bronze paintina (5910X20) |  | 7A | 5 | 1.5mm thick 316 Grade stainless steel trim all around in Brushed Bronze finish for the above mirror paneling. Over all size: 1960 x 5910mm high (In joints) | No | 5 | 2436.6 | 12183 | No | 0 | 2436.6 | 0 |  | FALSE
| Staircase Hand Rail |  | 7A | 5 | Glass Balustrade: 12mm thick clear tempered low iron glass with polished edges fixed within 8mm thick galvanized channels. Height: 1200mm high from FFL. | No | 5 | 23460 | 117300 | No | 3 | 23460 | 70380 |  | FALSE
| Backlit mirror in Powder room Vanity - 3 sides |  | 7A | 5 | Backlit Mirror: 6mm thick clear Silver Float mirror with polished edges bonded on FSC plywood including 1.5mm thick 316 Grade stainless steel frame all around. Installation at site with hanging mechanism. Our quotation includes complete set with LED lights. Over all size: 1580 x 1330mm high | No | 5 | 3215.14 | 16075.7 | No |  | 3215.14 | 0 |  | FALSE
22 | 1 Bed Suite - 8A (5 Nos) |  |  | 5 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
| Door HO-GD-01 (840X2420) | HO-GD-01 | 8A | 5 | Framed Sliding Glass Door: 6mm thick clear Silver Float mirror with polished edges bonded on both sides of door including 316 Grade stainless steel frame all around in Brass finish. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 5 | 3793.98 | 18969.9 | No | 5 | 3793.98 | 18969.9 |  | FALSE
|  |  | 8A | 5 | Ironmongeries for the above item: Manual sliding mechanism with customized back to back handle in Brass finish. | No | 5 | 1985 | 9925 | No | 5 | 1985 | 9925 |  | FALSE
| Door HO-GD-02 (800X2400) | HO-GD-02 | 8A | 5 | Frameless Glass Door: 12mm thick gradient frosted tempered float glass with polished edges fixed with wall to glass hinges. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 10 | 843.61 | 8436.1 | No | 10 | 843.61 | 8436.1 |  | FALSE
|  |  | 8A | 5 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 10 | 470 | 4700 | No | 10 | 470 | 4700 |  | FALSE
23 | 1 Bed Suite - 9A (2 Nos) | [7 empty] | 0 |  |  | 0 | 0 |  | FALSE
| Door HO-GD-02 (800X2400) | HO-GD-02 | 9A | 2 | Frameless Glass Door: 12mm thick gradient frosted tempered float glass with polished edges fixed with wall to glass hinges. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 4 | 843.61 | 3374.44 | No | 4 | 843.61 | 3374.44 |  | FALSE
|  |  | 9A | 2 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 4 | 470 | 1880 | No | 4 | 470 | 1880 |  | FALSE
24 | 1 Bed Suite - 9B (2 Nos) |  |  | 2 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
| Door HO-GD-02 (800X2400) | HO-GD-02 | 9B | 2 | Frameless Glass Door: 12mm thick gradient frosted tempered float glass with polished edges fixed with wall to glass hinges. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 4 | 843.61 | 3374.44 | No | 4 | 843.61 | 3374.44 |  | FALSE
|  |  | 9B | 2 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 4 | 470 | 1880 | No | 4 | 470 | 1880 |  | FALSE
25 | 1 Bed Suite - 10A (5 Nos) |  |  | 5 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
| Door HO-GD-02 (800X2400) | HO-GD-02 | 10A | 5 | Frameless Glass Door: 12mm thick gradient frosted tempered float glass with polished edges fixed with wall to glass hinges. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 10 | 843.61 | 8436.1 | No | 6 | 843.61 | 5061.66 |  | FALSE
|  |  | 10A | 5 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 10 | 470 | 4700 | No | 6 | 470 | 2820 |  | FALSE
26 | 1 Bed Suite - 10B (3 Nos) |  |  | 3 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
| Door HO-GD-02 (800X2400) | HO-GD-02 | 10B | 3 | Frameless Glass Door: 12mm thick gradient frosted tempered float glass with polished edges fixed with wall to glass hinges. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 6 | 843.61 | 5061.66 | No | 1 | 843.61 | 843.61 |  | FALSE
|  |  | 10B | 3 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 6 | 470 | 2820 | No | 1 | 470 | 470 |  | FALSE
27 | 1 Bed Deluxe Suite - 11A (1 No) |  |  | 1 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
| Door HO-GD-04 (840X2420) | HO-GD-04 | 11A | 1 | Framed Sliding Glass Door: 6mm thick clear Silver Float mirror with polished edges bonded on both sides of door including 316 Grade stainless steel frame all around in Brass finish. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 1 | 3793.98 | 3793.98 | No | 1 | 3793.98 | 3793.98 |  | FALSE
|  |  | 11A | 1 | Ironmongeries for the above item: Manual sliding mechanism with customized back to back handle in Brass finish. | No | 1 | 1985 | 1985 | No | 1 | 1985 | 1985 |  | FALSE
| Door HO-GD-05 (760X2420) | HO-GD-05 | 11A | 1 | Framed Glass Door: 12mm thick gradient frosted tempered glass with polished edges fixed with wall to glass hinges including 1.5mm thick 316 Grade stainless steel frame all around in Brushed finish. Ironmongeries measured and quoted separately. Over all size:830 x 2415mm high | No | 2 | 2129.85 | 4259.7 | No | 0 | 2129.85 | 0 |  | FALSE
|  |  | 11A | 1 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 2 | 470 | 940 | No | 0 | 470 | 0 |  | FALSE
| Door HO-GD-06 | HO-GD-06 | 11A | 1 | Framed Sliding Glass Door: 6mm thick clear Silver Float mirror with polished edges bonded on both sides of door including 316 Grade stainless steel frame all around in Brass finish. Ironmongeries measured and quoted separately. Over all size: 1160 x 2430mm high | No | 1 | 4551.6 | 4551.6 | No | 1 | 4551.6 | 4551.6 |  | FALSE
|  |  | 11A | 1 | Ironmongeries for the above item: Manual sliding mechanism with customized back to back handle in Brass finish. | No | 1 | 1985 | 1985 | No | 1 | 1985 | 1985 |  | FALSE
| Door HO-GD-07 | HO-GD-07 | 11A | 1 | Framed Sliding Glass Door: 6mm thick clear Silver Float mirror with polished edges bonded on both sides of door including 316 Grade stainless steel frame all around in Brass finish. Ironmongeries measured and quoted separately. Over all size: 1160 x 2430mm high | No | 1 | 4551.6 | 4551.6 | No | 1 | 4551.6 | 4551.6 |  | FALSE
|  |  | 11A | 1 | Ironmongeries for the above item: Manual sliding mechanism with customized back to back handle in Brass finish. | No | 1 | 1985 | 1985 | No | 1 | 1985 | 1985 |  | FALSE
| Door HO-GD-08 | HO-GD-08 | 11A | 1 | Framed Swing Door: 6mm thick clear Silver Float mirror with polished edges bonded on both sides of door including 316 Grade stainless steel frame all around in Brass finish. Ironmongeries measured and quoted separately. Over all size: 845 x 2425mm high | No | 1 | 3569.66 | 3569.66 | No | 0 | 3569.66 | 0 |  | FALSE
|  |  | 11A | 1 | Ironmongeries for the above item: 4 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 1 | 695 | 695 | No | 0 | 695 | 0 |  | FALSE
28 | 1 Bed Deluxe Suite - 11B ( 4 No) |  |  | 4 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
| Door HO-GD-04 (840X2420) | HO-GD-04 | 11B | 4 | Framed Sliding Glass Door: 6mm thick clear Silver Float mirror with polished edges bonded on both sides of door including 316 Grade stainless steel frame all around in Brass finish. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 4 | 3793.98 | 15175.92 | No | 0 | 3793.98 | 0 |  | FALSE
|  |  | 11B | 4 | Ironmongeries for the above item: Manual sliding mechanism with customized back to back handle in Brass finish. | No | 4 | 1985 | 7940 | No | 0 | 1985 | 0 |  | FALSE
| Door HO-GD-05 (760X2420) | HO-GD-05 | 11B | 4 | Framed Glass Door: 12mm thick gradient frosted tempered glass with polished edges fixed with wall to glass hinges including 1.5mm thick 316 Grade stainless steel frame all around in Brushed finish. Ironmongeries measured and quoted separately. Over all size:830 x 2415mm high | No | 8 | 2129.85 | 17038.8 | No | 1 | 2129.85 | 2129.85 |  | FALSE
|  |  | 11B | 4 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 8 | 470 | 3760 | No | 1 | 470 | 470 |  | FALSE
| Door HO-GD-06 | HO-GD-06 | 11B | 4 | Framed Sliding Glass Door: 6mm thick clear Silver Float mirror with polished edges bonded on both sides of door including 316 Grade stainless steel frame all around in Brass finish. Ironmongeries measured and quoted separately. Over all size: 1145 x 2415mm high | No | 4 | 4494.67 | 17978.68 | No | 2 | 4494.67 | 8989.34 |  | FALSE
|  |  | 11B | 4 | Ironmongeries for the above item: Manual sliding mechanism with customized back to back handle in Brass finish. | No | 4 | 1985 | 7940 | No | 2 | 1985 | 3970 |  | FALSE
| Door HO-GD-07 | HO-GD-07 | 11B | 4 | Framed Sliding Glass Door: 6mm thick clear Silver Float mirror with polished edges bonded on both sides of door including 316 Grade stainless steel frame all around in Brass finish. Ironmongeries measured and quoted separately. Over all size: 1145 x 2415mm high | No | 4 | 4494.67 | 17978.68 | No | 2 | 4494.67 | 8989.34 |  | FALSE
|  |  | 11B | 4 | Ironmongeries for the above item: Manual sliding mechanism with customized back to back handle in Brass finish. | No | 4 | 1985 | 7940 | No | 2 | 1985 | 3970 |  | FALSE
| Door HO-GD-08 | HO-GD-08 | 11B | 4 | Framed Swing Door: 6mm thick clear Silver Float mirror with polished edges bonded on both sides of door including 316 Grade stainless steel frame all around in Brass finish. Ironmongeries measured and quoted separately. Over all size: 845 x 2425mm high | No | 4 | 3661.91 | 14647.64 | No | 0 | 3661.91 | 0 |  | FALSE
|  |  | 11B | 4 | Ironmongeries for the above item: 4 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 4 | 695 | 2780 | No | 0 | 695 | 0 |  | FALSE
29 | 1 Bed Deluxe Suite - 11C (11 No) |  |  | 11 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
| Door HO-GD-04 (840X2420) | HO-GD-04 | 11C | 11 | Framed Sliding Glass Door: 6mm thick clear Silver Float mirror with polished edges bonded on both sides of door including 316 Grade stainless steel frame all around in Brass finish. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 11 | 3793.98 | 41733.78 | No | 0 | 3793.98 | 0 |  | FALSE
|  |  | 11C | 11 | Ironmongeries for the above item: Manual sliding mechanism with customized back to back handle in Brass finish. | No | 11 | 1985 | 21835 | No | 0 | 1985 | 0 |  | FALSE
| Door HO-GD-05 (760X2420) | HO-GD-05 | 11C | 11 | Framed Glass Door: 12mm thick gradient frosted tempered glass with polished edges fixed with wall to glass hinges including 1.5mm thick 316 Grade stainless steel frame all around in Brushed finish. Ironmongeries measured and quoted separately. Over all size:830 x 2415mm high | No | 22 | 2129.85 | 46856.7 | No | 0 | 2129.85 | 0 |  | FALSE
|  |  | 11C | 11 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 22 | 490 | 10780 | No | 0 | 490 | 0 |  | FALSE
| Door HO-GD-06 | HO-GD-06 | 11C | 11 | Framed Sliding Glass Door: 6mm thick clear Silver Float mirror with polished edges bonded on both sides of door including 316 Grade stainless steel frame all around in Brass finish. Ironmongeries measured and quoted separately. Over all size: 1145 x 2415mm high | No | 11 | 4494.67 | 49441.37 | No | 11 | 4494.67 | 49441.37 |  | FALSE
|  |  | 11C | 11 | Ironmongeries for the above item: Manual sliding mechanism with customized back to back handle in Brass finish. | No | 11 | 1985 | 21835 | No | 11 | 1985 | 21835 |  | FALSE
| Door HO-GD-07 | HO-GD-07 | 11C | 11 | Framed Sliding Glass Door: 6mm thick clear Silver Float mirror with polished edges bonded on both sides of door including 316 Grade stainless steel frame all around in Brass finish. Ironmongeries measured and quoted separately. Over all size: 1145 x 2415mm high | No | 11 | 4494.67 | 49441.37 | No | 11 | 4494.67 | 49441.37 |  | FALSE
|  |  | 11C | 11 | Ironmongeries for the above item: Manual sliding mechanism with customized back to back handle in Brass finish. | No | 11 | 1985 | 21835 | No | 11 | 1985 | 21835 |  | FALSE
| Door HO-GD-08 | HO-GD-08 | 11C | 11 | Framed Swing Door: 6mm thick clear Silver Float mirror with polished edges bonded on both sides of door including 316 Grade stainless steel frame all around in Brass finish. Ironmongeries measured and quoted separately. Over all size: 845 x 2425mm high | No | 11 | 3661.91 | 40281.01 | No | 0 | 3661.91 | 0 |  | FALSE
|  |  | 11C | 11 | Ironmongeries for the above item: 4 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 11 | 695 | 7645 | No | 0 | 695 | 0 |  | FALSE
30 | 1 Bed Deluxe Suite - 11D (4 No) |  |  | 4 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
| Door HO-GD-04 (840X2420) | HO-GD-04 | 11D | 4 | Framed Sliding Glass Door: 6mm thick clear Silver Float mirror with polished edges bonded on both sides of door including 316 Grade stainless steel frame all around in Brass finish. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 4 | 3793.98 | 15175.92 | No | 0 | 3793.98 | 0 |  | FALSE
|  |  | 11D | 4 | Ironmongeries for the above item: Manual sliding mechanism with customized back to back handle in Brass finish. | No | 4 | 1985 | 7940 | No | 0 | 1985 | 0 |  | FALSE
| Door HO-GD-05 (760X2420) | HO-GD-05 | 11D | 4 | Framed Glass Door: 12mm thick gradient frosted tempered glass with polished edges fixed with wall to glass hinges including 1.5mm thick 316 Grade stainless steel frame all around in Brushed finish. Ironmongeries measured and quoted separately. Over all size:830 x 2415mm high | No | 6 | 2129.85 | 12779.1 | No | 0 | 2129.85 | 0 |  | FALSE
|  |  | 11D | 4 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 6 | 470 | 2820 | No | 0 | 470 | 0 |  | FALSE
| Door HO-GD-06 | HO-GD-06 | 11D | 4 | Framed Sliding Glass Door: 6mm thick clear Silver Float mirror with polished edges bonded on both sides of door including 316 Grade stainless steel frame all around in Brass finish. Ironmongeries measured and quoted separately. Over all size: 1145 x 2415mm high | No | 3 | 4494.67 | 13484.01 | No | 1 | 4494.67 | 4494.67 |  | FALSE
|  |  | 11D | 4 | Ironmongeries for the above item: Manual sliding mechanism with customized back to back handle in Brass finish. | No | 3 | 1985 | 5955 | No | 1 | 1985 | 1985 |  | FALSE
| Door HO-GD-07 | HO-GD-07 | 11D | 4 | Framed Sliding Glass Door: 6mm thick clear Silver Float mirror with polished edges bonded on both sides of door including 316 Grade stainless steel frame all around in Brass finish. Ironmongeries measured and quoted separately. Over all size: 1145 x 2415mm high | No | 3 | 4494.67 | 13484.01 | No | 1 | 4494.67 | 4494.67 |  | FALSE
|  |  | 11D | 4 | Ironmongeries for the above item: Manual sliding mechanism with customized back to back handle in Brass finish. | No | 3 | 1985 | 5955 | No | 1 | 1985 | 1985 |  | FALSE
| Door HO-GD-08 | HO-GD-08 | 11D | 4 | Framed Swing Door: 6mm thick clear Silver Float mirror with polished edges bonded on both sides of door including 316 Grade stainless steel frame all around in Brass finish. Ironmongeries measured and quoted separately. Over all size: 845 x 2425mm high | No | 3 | 3661.91 | 10985.73 | No | 0 | 3661.91 | 0 |  | FALSE
|  |  | 11D | 4 | Ironmongeries for the above item: 4 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 3 | 695 | 2085 | No | 0 | 695 | 0 |  | FALSE
31 | 1 Bed Suite - 12A (5 Nos) |  |  | 5 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
| Door HO-GD-02 (800X2400) | HO-GD-02 | 12A | 5 | Frameless Glass Door: 12mm thick gradient frosted tempered float glass with polished edges fixed with wall to glass hinges. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 10 | 843.61 | 8436.1 | No | 6 | 843.61 | 5061.66 |  | FALSE
|  |  | 12A | 5 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 10 | 470 | 4700 | No | 6 | 470 | 2820 |  | FALSE
32 | 1 Bed Suite - 13A (1 Nos) |  |  | 1 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
| Door HO-GD-01 (840X2420) | HO-GD-01 | 13A | 1 | Framed Sliding Glass Door: 6mm thick clear Silver Float mirror with polished edges bonded on both sides of door including 316 Grade stainless steel frame all around in Brass finish. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 1 | 3793.98 | 3793.98 | No | 1 | 3793.98 | 3793.98 |  | FALSE
|  |  | 13A | 1 | Ironmongeries for the above item: Manual sliding mechanism with customized back to back handle in Brass finish. | No | 1 | 1985 | 1985 | No | 1 | 1985 | 1985 |  | FALSE
| Door HO-GD-02 (800X2400) | HO-GD-02 | 13A | 1 | Frameless Glass Door: 12mm thick gradient frosted tempered float glass with polished edges fixed with wall to glass hinges. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 2 | 843.61 | 1687.22 | No | 0 | 843.61 | 0 |  | FALSE
|  |  | 13A | 1 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 2 | 470 | 940 | No | 0 | 470 | 0 |  | FALSE
33 | 1 Bed Suite - 14A (4 Nos) |  |  | 4 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
| Door HO-GD-01 (840X2420) | HO-GD-01 | 14A | 4 | Framed Sliding Glass Door: 6mm thick clear Silver Float mirror with polished edges bonded on both sides of door including 316 Grade stainless steel frame all around in Brass finish. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 4 | 3793.98 | 15175.92 | No | 4 | 3793.98 | 15175.92 |  | FALSE
|  |  | 14A | 4 | Ironmongeries for the above item: Manual sliding mechanism with customized back to back handle in Brass finish. | No | 4 | 1985 | 7940 | No | 4 | 1985 | 7940 |  | FALSE
| Door HO-GD-02 (800X2400) | HO-GD-02 | 14A | 4 | Frameless Glass Door: 12mm thick gradient frosted tempered float glass with polished edges fixed with wall to glass hinges. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 8 | 843.61 | 6748.88 | No | 1 | 843.61 | 843.61 |  | FALSE
|  |  | 14A | 4 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 8 | 470 | 3760 | No | 1 | 470 | 470 |  | FALSE
34 | Standard Guestroom corner - 15A (2 Nos) |  |  | 2 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
| Shower Cubical GD-09 |  | 15A | 2 | Framed Glass Door with Partition: 12mm thick clear tempered low iron glass with polished edges. Fixed glass fixed with stainless steel frame and glass door fixed with glass to glass hinges. Ironmongeries measured and quoted separately. Over all size: 4975 x 2450mm (In joints) | No | 4 | 13485.41 | 53941.64 | No | 0 | 13485.41 | 0 |  | FALSE
|  |  | 15A | 2 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 4 | 470 | 1880 | No | 0 | 470 | 0 |  | FALSE
35 | Standard Guestroom corner - 16A (3 Nos) |  |  | 3 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
| Door HO-GD-02 (800X2400) | HO-GD-02 | 16A | 3 | Frameless Glass Door: 12mm thick gradient frosted tempered float glass with polished edges fixed with wall to glass hinges. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 6 | 843.61 | 5061.66 | No | 2 | 843.61 | 1687.22 |  | FALSE
|  |  | 16A | 3 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 6 | 470 | 2820 | No | 2 | 470 | 940 |  | FALSE
36 | Standard Guestroom corner - 19A( 6 Nos) |  |  | 6 |  |  |  |  | 0 |  |  | 0 | 0 |  | FALSE
| Door HO-GD-01 (840X2420) | HO-GD-01 | 19A | 6 | Framed Sliding Glass Door: 6mm thick clear Silver Float mirror with polished edges bonded on both sides of door including 316 Grade stainless steel frame all around in Brass finish. Ironmongeries measured and quoted separately. Over all size: 800 x 2420mm high | No | 6 | 3793.98 | 22763.88 | No | 5 | 3793.98 | 18969.9 |  | FALSE
|  |  | 19A | 6 | Ironmongeries for the above item: Manual sliding mechanism with customized back to back handle in Brass finish. | No | 6 | 1985 | 11910 | No | 5 | 1985 | 9925 |  | FALSE
| Door HO-GD-02 (800X2400) | HO-GD-02 | 19A | 6 | Frameless Glass Door: 12mm thick gradient frosted tempered float glass with polished edges fixed with wall to glass hinges. Ironmongeries measured and quoted separately. Over all size: 840 x 2420mm high | No | 12 | 843.61 | 10123.32 | No | 6 | 843.61 | 5061.66 |  | FALSE
|  |  | 19A | 6 | Ironmongeries for the above item: 2 no's of wall to glass hinges, door stopper and PVC edges seal. All ironmongeries from JDG brand in polished finish in stainless steel 304 Grade. Towel bar provided by Client on FOC basis and installation by JDG. | No | 12 | 470 | 5640 | No | 6 | 470 | 2820 |  | FALSE
| Additional Item: | [7 empty] | 0 |  |  | 0 | 0 |  | FALSE
| Valet Box Door @ 11A, 11B, 11C, 11D |  |  |  | Framed Sliding Glass Door: 6mm thick clear Silver Float mirror with polished edges bonded on both sides of door including 316 Grade stainless steel frame all around in Brass finish. Ironmongeries measured and quoted separately. Over all size: 1150 x 2600mm high | No | 19 | 4778.3 | 90787.7 | No | 1 | 4778.3 | 4778.3 |  | FALSE
[5 empty] | Ironmongeries for the above item: Manual sliding mechanism with customized back to back handle in Brass finish. | No | 19 | 1985 | 37715 | No | 1 | 1985 | 1985 |  | FALSE
| Mirrored wall @ 15A |  |  |  | 6mm thick clear Silver Float mirror with polished edges fixed on timber backing including 1.5mm thick 316 Grade stainless steel frame all around in polished Chrome finish. Over all size: 1980 x 6440mm high (in joints) | No | 2 | 5522.53 | 11045.06 | No | 2 | 5522.53 | 11045.06 |  | FALSE
| Mirror ceiling @ 7A |  |  |  | Supply and installation of 6mm thick clear Silver Float mirror with polished edges including safety film at rear side fixed on timber backing. The cutout and holes are inclusive in our price. Over all size: 5670 x 3340mm | No | 5 | 9262.3 | 46311.5 | No | 5 | 9262.3 | 46311.5 | L25, L21, L16, L14, L7 | FALSE
[5 empty] | Secondary support structure for the ceiling mirror including timber backing before fixing mirror. Scaffolding and bottom support to be provided by client. | No | 5 | 5207.9 | 26039.5 | No | 5 | 5207.9 | 26039.5 |  | FALSE
| Bathroom wall mirror @ 7A |  |  |  | 6mm thick clear Silver Float mirror with polished edges fixed on timber backing including wooden frame all around. Over all size: 1200 x 2900mm high (in joints) | No | 5 | 2785.81 | 13929.05 | No | 1 | 2785.81 | 2785.81 |  | FALSE
New item | Glass shelves @ 3A, 3C, 3D, 3F, 3G |  |  |  | 12mm thick clear tempered glass shelves fixed with frame in Brass finish. Over all size: 442 x 180mm | No | 114 | 233.5 | 26619 | No |  | 233.5 | 0 |  | FALSE
[9 empty] | 2153495.4 |  |  |  | 1427839.88
| Discount | [7 empty] | -153495.4 |  |  |  | 0
[5 empty] | Final Value as per agreement |  | 1393 |  | 2000000 |  | 949 |  | 1427839.88
Note on O90: Himal Kosala: 80% done
Note on O91: Himal Kosala: 80% done

## Glass Doors Progress
Level / Room No. | Room Type | HO-GD-01 | HO-GD-02 | HO-GD-02 | HO-GD-04 | HO-GD-05 | HO-GD-06 | HO-GD-07 | HO-GD-08 | HO-GD-10
|  | Sliding | W C | Shower | [5 empty] | DB Sliding
701 | 8A | 1 | 1 | 1
702 | 2B |  | 1 | 1
703 | 2C |  | 1 | 1
704 | 3A | 1 | 1 | 1
705 | 3D | 1 | 1 | 1
706 | 2A |  | 1 | 1
707 | 7A
708 | 19A | 1 | 1 | 1
709 | 1C |  | 1 | 1
710 | 4B | 1 | 1 | 1
801 | 8A | 1 | 1 | 1
802 | 2B |  | 1 | 1
803 | 2C |  | 1 | 1
804 | 3A | 1 | 1 | 1
805 | 3D | 1 | 1 | 1
806 | 2A | 0 | 1 | 1
807 | 1B |  | 1 | 1
808 | 4A | 1 | 1 | 1 | [5 empty] | 1
809 | 1B | 0 | 1 | 1
901 | 8A | 1 | 1 | 1
902 | 2B |  | 1 | 1
903 | 2C |  | 1 | 1
904 | 3A | 1 | 1 | 1
905 | 3D | 1 | 1 | 1
906 | 2A | 0 | 1 | 1
907 | 9A |  | 1 | 1
908 | 9B |  | 1 | 1
909 | 1B
910 | 4A | 1 | 1 | 1 | [5 empty] | 1
1001 | 8A | 1 | 1 | 1
1002 | 2B |  | 1 | 1
1003 | 2C |  | 1 | 1
1004 | 3A | 1 | 1 | 1
1005 | 3D | 1 | 1 | 1
1006 | 2A |  | 1 | 1
1007 | 15A
1008 | 1B |  | 0 | 0
1009 | 4A | 1 | 1 | 1 | [5 empty] | 1
1101 | 8A | 1 | 1 | 1
1102 | 2B |  | 1 | 1
1103 | 2C |  | 1 | 1
1104 | 3A | 1 | 1 | 1
1105 | 3D | 1 | 1 | 1
1106 | 2A |  | 1 | 1
1107 | 16A |  | 1 | 1
1108 | 9B
1109 | 1B |  | 1 | 1
1110 | 4A | 1 | 1 | 1 | [5 empty] | 1
1201 | 10A |  | 1 | 1
1202 | 3G | 1 | 1 | 1
1203 | 2B |  | 1 | 1
1204 | 11C |  | 0 | 0 |  |  | 1 | 1
1205 | 3D | 1 | 1 | 1
1206 | 2B |  | 1 | 1
1207 | 11C |  | 0 | 0 |  |  | 1 | 1
1208 | 3D | 1 | 1 | 1
1209 | 2A | 0 | 1 | 1
1210 | 9A |  | 1 | 1
1211 | 9B |  | 1 | 1
1212 | 1A |  | 1 | 1
1213 | 2F |  | 1 | 1
1214 | 3C | 1 | 1 | 1
1215 | 3F | 1 | 1 | 1
1216 | 2G |  | 1 | 1
1217 | 2E |  | 1 | 1
1218 | 5A | 1 | 1 | 1
1301 | 10A |  | 1 | 1
1302 | 3G | 1 | 1 | 1
1303 | 2B |  | 1 | 1
1304 | 11C | [5 empty] | 1 | 1
1305 | 3D | 1 | 1 | 1 | [6 empty] | 2
1306 | 2B |  | 1 | 1
1307 | 11C | [5 empty] | 1 | 1
1308 | 3D | 1 | 1 | 1
1309 | 2A |  | 1 | 1
1310 | 7A |  | 0 | 0
1311 | 19A | 1 | 0 | 0
1312 | 1A |  | 1 | 1
1313 | 2F |  | 1 | 1
1314 | 3C | 1 | 1 | 1
1315 | 3F | 1 | 1 | 1
1316 | 2G |  | 1 | 1
1317 | 2E |  | 0 | 0
1318 | 5A | 1 | 1 | 1
1401 | 10A |  | 0 | 0
1402 | 3G | 1 | 1 | 1
1403 | 2B |  | 1 | 1
1404 | 11C |  | 0 | 0 |  |  | 1 | 1
1405 | 3D | 1 | 1 | 1
1406 | 2B |  | 1 | 1
1407 | 11C |  | 0 | 0 |  |  | 1 | 1
1408 | 3D | 1 | 1 | 1
1409 | 2A |  | 1 | 1
1410 | 7A |  | 0 | 0
1411 | 1A |  | 1 | 1
1412 | 2F |  | 1 | 1
1413 | 3C | 1 | 1 | 1
1414 | 3F | 1 | 0 | 0
1415 | 2G |  | 1 | 1
1416 | 2E |  | 1 | 1
1417 | 5A | 1 | 1 | 1
1501 | 10A |  | 0 | 0
1502 | 3G | 1 | 1 | 1
1503 | 2B |  | 1 | 1
1504 | 11C |  | 0 | 0 |  |  | 1 | 1
1505 | 3D | 1 | 1 | 1
1506 | 2B |  | 1 | 1
1507 | 11C |  | 0 | 0 |  |  | 1 | 1
1508 | 3D | 1 | 1 | 1
1509 | 2A |  | 1 | 1
1510 | 7A |  | 0 | 0
1511 | 19A | 1 | 1 | 1
1512 | 1A |  | 1 | 1
1513 | 2F |  | 1 | 1
1514 | 3C | 1 | 1 | 1
1515 | 3F |  | 1 | 1
1516 | 2G |  | 1 | 1
1517 | 2E |  | 1 | 1
1518 | 5A | 1 | 1 | 1
1601 | 10A |  | 1 | 1
1602 | 11D |  | 0 | 0 |  |  | 1 | 1
1603 | 2B |  | 1 | 1
1604 | 3A | 1 | 1 | 1
1605 | 3D | 1 | 1 | 1
1606 | 2B |  | 1 | 1
1607 | 11C |  | 0 | 0 |  |  | 1 | 1
1608 | 3D | 1 | 1 | 1
1609 | 2A |  | 1 | 1
1610 | 7A |  | 0 | 0
1611 | 1C |  | 1 | 1
1612 | 2H |  | 1 | 1
1613 | 3C | 1 | 1 | 1
1614 | 3F | 1 | 1 | 1
1615 | 2G |  | 1 | 1
1616 | 2E |  | 1 | 1
1617 | 5A | 1 | 1 | 1
1901 | 12A
1903 | 19A
1904 | 6A
17A
2001 | 12A
2002 | 2D |  | 1 | 1
2003 | 3A | 1 | 1 | 1
2004 | 11B
2006 | 19A | 1 | 1 | 1
2007 | 6A |  | 1 | 1
7A
2101 | 12A
2102 | 2D |  | 1 | 1
2103 | 3A | 1 | 1 | 1
2104 | 11B | [5 empty] | 1 | 1
2106 | 6A |  | 1 | 1
2201 | 12A
2202 | 11A | [5 empty] | 1 | 1
2203 | 3D | 1 | 1 | 1 | [6 empty] | 5
2204 | 2A |  | 1 | 1
2206 | 6A
15A
2301 | 12A
2302 | 2D |  | 1 | 1 | [6 empty] | 2
2303 | 3A | 1 | 1 | 1
2304 | 2A |  | 1 | 1
2305 | 16A
2306 | 6A |  | 1 | 1 | [6 empty] | 2
2401 | 13A | 1
2402 | 14A | 1
2403 | 2D |  | 1 | 1 | [6 empty] | 8
2404 | 3A |  | 1 | 1
2405 | 3D | 1 | 1 | 1
2406 | 2B |  | 1 | 1
2407 | 11C | [5 empty] | 1 | 1
2408 | 3D | 1 | 1 | 1 | [6 empty] | 2
2409 | 2B
2411 | 19A | 1
2412 | 1A |  | 1 | 1
2413 | 2F |  | 1 | 1
2414 | 3C | 1 | 1 | 1 | [6 empty] | 4
2415 | 3F | 1 | 1 | 1
2416 | 2G
2417 | 2E |  | 1 | 1 | [6 empty] | 2
2418 | 5A | 1 | 1 | 1
7A
2501 | 10B
2502 | 14A | 1 | 1
2503 | 2D
2504 | 3A | 1 | 1 | 1 | [6 empty] | 4
2505 | 3D | 1 | 1 | 1
2506 | 2B
2507 | 11C | [5 empty] | 1 | 1
2508 | 3D | 1 | 1 | 1 | [6 empty] | 2
2509 | 2B
2510 | 1A |  | 1 | 1
2511 | 2F |  | 1 | 1
2512 | 3C | 1 | 1 | 1
2513 | 3F | 1 | 1 | 1
2514 | 2G |  | 1 | 1
2515 | 2E |  | 1 | 1 | [6 empty] | 12
2516 | 5A | 1
2601 | 10B
2602 | 14A
2603 | 2D
2604 | 3A |  | 1 | 1
2605 | 3D |  | 1 | 1
2606 | 2C |  | 1 | 1
2607 | 3A | 1 | 1 | 1 | [6 empty] | 8
2609 | 1A
2610 | 2F |  | 1 | 1
2611 | 3C | 1 | 1 | 1
2612 | 3F | 1 | 1 | 1
2613 | 2G |  | 1 | 1 | [6 empty] | 8
2614 | 2E | [9 empty] | 1
2615 | 5A | 1
18A
2701 | 10B
2702 | 14A
2703 | 2D
2704 | 3A
2705 | 11B
2706 | 2C
2707 | 3A
2708 | 11D
2709 | 16A
2710 | 1A
2711 | 2F
2712 | 3C
2713 | 3F
2714 | 2G
2715 | 2E
2716 | 5A | [11 empty] | 45
Total |  | 76 | 154 | 153 | 0 | 0 | 14 | 14 | 0 | 4 |  | 415 | 280
62
Summary
| Room Type | HO-GD-01 | HO-GD-02 | HO-GD-04 | HO-GD-05 | HO-GD-06 | HO-GD-07 | HO-GD-08 | HO-GD-10
| 1A | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0
1C | 1B | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0
| 2A | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0
| 2B | 0 | 36 | 0 | 0 | 1 | 1 | 0 | 0
| 2C | 0 | 14 | 0 | 0 | 1 | 1 | 0 | 0
| 2D | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0
| 2E | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
| 2F | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0
| 2G | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
| 2H | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| 3A | 15 | 30 | 0 | 0 | 0 | 0 | 0 | 0
| 3C | 9 | 18 | 0 | 0 | 0 | 0 | 0 | 0
| 3D | 21 | 42 | 0 | 0 | 0 | 0 | 0 | 0
| 3F | 8 | 18 | 0 | 0 | 0 | 0 | 0 | 0
| 3G | 4 | 8 | 0 | 0 | 0 | 0 | 0 | 0
| 4A | 4 | 8 | 0 | 0 | 0 | 0 | 0 | 4
| 4B | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 1
| 5A | 9 | 14 | 0 | 0 | 0 | 0 | 0 | 0
| 6A | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0
| 7A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8A | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0
| 9A | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0
| 9B | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0
| 10A | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0
| 10B | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| 11A | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0
| 11B | 0 | 0 | 0 | 1 | 2 | 2 | 0 | 0
| 11C | 0 | 1 | 0 | 0 | 11 | 11 | 0 | 0
| 11D | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
| 12A | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0
| 13A | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 14A | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| 15A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 16A | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| 17A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 18A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 19A | 5 | 6 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 86 | 361 | 1 | 1 | 17 | 17 | 0 | 5 |  | 488

## VO.01
VO: SUPPLY, DELIVERY & INSTALLATION OF BOH MIRRORS, GLASS DOORS, GLASS PARTITIONS
Item. No. | Description | Unit | Quantity | Rate | Amount | PREVIOUS |  | THIS MONTH |  | CUMULATIVE
[6 empty] | Qty | Amount | Qty | Amount | % | Qty | Amount
Supply & installtion of Mirror, including necessary framing, sub frames, transoms, stops, ironmongeries, sealants, fittings, backing support. Fixing boards, etc and like all in accordance with the drawings and specifications
1 | Mirror 6mm - (600x1000mm) | No's | 29 | 228 | 6612 | 0 | 0 | 0 | 0 | 3.448% | 1 | 228
Supply & installation of Glasss Doors complete with metal frames, sub frames, transoms, door steps, insulation, sealant, compression/edge seal, protective and decorative coatings, metal strips, cut moulding, ironmongeries, all in accordance with the drawings and specifications
2 | Glass Door 10mm low iron glass door with polished edges (1024x2700) | No's | 13 | 1467 | 19071 | 0 | 0 | 0 | 0 | 90% | 13 | 17163.9
Supply and installation of Glass Partition including all necessary framing. Fitting, fixing, backing, framing support, decoration, provision of the niche, grouting , pointing , polishing shadow gaps, etc and the like all in accordance with the drawings and specifications
3 | Glass Partition - 10mm Low iron glass partition with polished edges fixed with SS u channels in brush finsih | Sq.m | 56 | 551 | 30856 | 0 | 0 | 0 | 0 | 90% | 56 | 27770.4
| Prelimineries | Item | 1 | 3318.47 | 3318.47 | 0 | 0 | 0 | 0 | 61.15% |  | 2029.2253
| Total |  |  |  | 59858 | 0 | 0 | 0 | 0 | 78.84% |  | 47192
Note on K13: Himal Kosala: 90% until WIR approval
Note on K17: Himal Kosala: 90% until WIR approval

## VO.02
VO: SUPPLY, DELIVERY & INSTALLATION OF MIRROR CLADDING TO TIMBER DOORS
Item. No. | Description | Unit | Quantity | Rate | Amount | PREVIOUS |  | THIS MONTH |  | CUMULATIVE
[6 empty] | Qty | Amount | Qty | Amount | % | Qty | Amount
Supply & Installation of 6mm thick silver mirror with polished edges fixed to timber door with silicon and 1.2mm thick 10x10 mm SS L angle all around with mirror finish
1 | 1200x2100 mm - Stair Doors D - 03B | No's | 47 | 1188 | 55836
2 | 1200x2100 mm - Other Door D - 20B | No's | 57 | 1188 | 67716
3 | Shop drawings, samples etc |  |  |  | 1250
4 | Transport and handling |  |  |  | 1500
| TOTAL in AED (excluding VAT) |  |  |  | 126302

## WFA Valuation
DORCHESTER COLLECTION HOTEL & RESIDENCES (PLOT 18) |  |  |  |  | 2022-05-05
VALUATION OF REMAINING SUBCONTRACT WORKS |  |  |  |  | Ver. 1
Trade Package: | Internal Glazing
Subcontractor: | Joseph Decorative Glass
Subcontract Ref: | TBC
ORIGINAL SUBCONTRACT WORKS |  | TOTAL VALUE OF SUBCONTRACT WORKS | VALUE OF WORKS COMPLETED TO 28-FEB-2022 |  | VALUE OF WORKS UNDER NEW SUBCONTRACT
A | Glass doors | 1739356 | 57.23% | 995486 | 743870
B | Glass shelves | 26619 | 0% | 0 | 26619
C | Wall finishes/mirrors | 69367 | 0% | 0 | 69367
D | Mirror to ceiling | 72851 | 0% | 0 | 72851
E | Glass handrails | 117300 | 0% | 0 | 117300
F | Doors to valet boxes | 128503 | 0% | 0 | 128503
G | Provisional Sum for Presidential/Royal suites | 72163 | 0% | 0 | 72163
H | Discount | -153996 | 0% | 0 | -153996
Sub-Totals |  | 2072163 | 48.04% | 995486 | 1076677
VARIATIONS |  | TOTAL VALUE OF SUBCONTRACT WORKS | VALUE OF WORKS COMPLETED TO 28-FEB-2022 |  | VALUE OF WORKS UNDER NEW SUBCONTRACT
| BOH glazed partitions, doors and mirrors (subject to remeasure) | 59858 | 0% | 0 | 59858
| Mirrored cladding to D3b and D20 doors (subject to remeasure) | 126302 | 0% | 0 | 126302
Sub-Totals |  | 186160 | 0% | 0 | 186160
MATERIALS ON SITE |  | TOTAL VALUE OF SUBCONTRACT WORKS | VALUE OF WORKS COMPLETED TO 28-FEB-2022 |  | VALUE OF WORKS UNDER NEW SUBCONTRACT
| None | 0 |  | 0 | 0
Sub-Totals |  | 0 |  | 0 | 0
Totals |  | 2258323 | 44.08% | 995486 | 1262837
NOTES |  | NEW SUBCONTRACT
|  | Value of Remaining Subcontract Works |  |  | 1076677
1) The amount included at "Payments to Date" is subject to final validation by the Employer's Representative. The Subcontractor shall provide evidence substantiating the amount paid to date under the previous subcontract. 2) Payment of amounts due under the previous RPJV subcontract (including retention) will be made pursuant to the terms of the WFA between the Employer and the Subcontractor. 3) The subcontract shall provide security for its performance of the Subcontract Works in the amount of AED 225,832.00 in the form of an unconditional and irrevocable bank guarantee for the benefit of the Employer. |  | Value of Remaining Variation Works |  |  | 186160
|  | Less Value of Materials on Site at 28-Feb-22 |  |  | 0
|  | New Subcontract Price |  |  | 1262837
WORKS COMPLETED TO 28-FEB-22
|  | Value of Completed Subcontract Works |  |  | 995486
|  | Value of Completed Variation Works |  |  | 0
|  | Value of Materials on Site at 28-Feb-22 |  |  | 0
|  | Value of Works Completed to 28-Feb-22 |  |  | 995486
|  | Less Cash Retention to 28-Feb-22 (10%) |  |  | -99548.6
|  | Less Payments to Date (incl. Advance Payment) |  |  | -830767
|  | Outstanding amount for Works Completed to 28-Feb-22 |  |  | 65170.4
All amounts exclude VAT