## Summary
No | Description | Qty | Unit | Rate | Amount | Previous Qty | This Month Qty | Cumulative Qty | Previous Amount | This Month Amount | Cumulative Amount
WA-C010
A | RCC Walls and Slabs
upto 52mm dia
A.1 | 150mm - 200mm thick | 5 | No | 40 | 200 | 112 | 0 | 112 | 4480 | 0 | 4480
A.2 | 201mm - 250mm thick | 5 | No | 44 | 220 | 715 | 1 | 716 | 31460 | 44 | 31504
A.3 | 251mm - 350mm thick | 5 | No | 47 | 235 | 128 | 0 | 128 | 6016 | 0 | 6016
A.4 | 351mm - 400mm thick | 5 | No | 52 | 260 | 26 | 0 | 26 | 1352 | 0 | 1352
A.4 | 401mm - 500mm thick | 5 | No | 60 | 300 | 158 | 6 | 164 | 9480 | 360 | 9840
53mm dia 102mm dia
A.6 | 150mm - 200mm thick | 25 | No | 50 | 1250 | 255 | 0 | 255 | 12750 | 0 | 12750
A.7 | 201mm - 250mm thick | 25 | No | 55 | 1375 | 6 | 2 | 8 | 330 | 110 | 440
A.8 | 251mm - 350mm thick | 5 | No | 64 | 320 | 86 | 9 | 95 | 5504 | 576 | 6080
A.9 | 351mm - 400mm thick | 5 | No | 67 | 335 | 50 | 14 | 64 | 3350 | 938 | 4288
A.10 | 401mm - 500mm thick | 5 | No | 75 | 375 | 49 | 57 | 106 | 3675 | 4275 | 7950
103mm dia 152mm dia
A.11 | 150mm - 200mm thick | 25 | No | 60 | 1500 | 37 | 2 | 39 | 2220 | 120 | 2340
A.12 | 201mm - 250mm thick | 25 | No | 65 | 1625 | 30 | 8 | 38 | 1950 | 520 | 2470
A.13 | 251mm - 350mm thick | 5 | No | 78 | 390 | 263 | 6 | 269 | 20514 | 468 | 20982
A.14 | 351mm - 400mm thick | 5 | No | 84 | 420 | 87 | 7 | 94 | 7308 | 588 | 7896
A.15 | 401mm - 500mm thick | 5 | No | 90 | 450 | 50 | 12 | 62 | 4500 | 1080 | 5580
153mm dia 202mm dia
A.16 | 150mm - 200mm thick | 25 | No | 70 | 1750 | 111 | 0 | 111 | 7770 | 0 | 7770
A.17 | 201mm - 250mm thick | 25 | No | 74 | 1850 | 132 | 0 | 132 | 9768 | 0 | 9768
A.18 | 251mm - 350mm thick | 5 | No | 88 | 440 | 325 | 0 | 325 | 28600 | 0 | 28600
A.19 | 351mm - 400mm thick | 5 | No | 95 | 475 | 175 | 1 | 176 | 16625 | 95 | 16720
A.20 | 401mm - 500mm thick | 5 | No | 110 | 550 | 199 | 2 | 201 | 21890 | 220 | 22110
203mm dia 302mm dia
A.21 | 150mm - 200mm thick | 25 | No | 112 | 2800 | 7 | 0 | 7 | 784 | 0 | 784
A.22 | 201mm - 250mm thick | 25 | No | 125 | 3125 | 14 | 0 | 14 | 1750 | 0 | 1750
A.23 | 251mm - 350mm thick | 5 | No | 150 | 750 | 32 | 0 | 32 | 4800 | 0 | 4800
A.24 | 351mm - 400mm thick | 5 | No | 158 | 790 | 8 | 0 | 8 | 1264 | 0 | 1264
A.25 | 401mm - 500mm thick | 5 | No | 175 | 875 | 17 | 0 | 17 | 2975 | 0 | 2975
B | Scanning
B.1 | Concrete Scanning to locate Rebar / PT strands with reports | 25 | No | 150 | 3750 | 86 | 12 | 98 | 12900 | 1800 | 14700
C | Mobilization
C.1 | Mobilization & demobilization charge for markings less than 5 Nos | 20 | No | 250 | 5000 | 40 | 0 | 40 | 10000 | 0 | 10000
C.2 | Mobilization & demobilization charge for markings less than 10 Nos | 20 | No | 200 | 4000 | 43 | 0 | 43 | 8600 | 0 | 8600
[9 empty] | 242615 | 11194 | 253809
Variation
WA-C023 R1
| Demolition of Jumpform columns (3m x 1.6m x 0.5m) | 2 | no | 6600 | 13200 | 2 |  | 2 | 13200 | 0 | 13200
| Demolition of Jumpform columns (3m x 1.2m x 0.5m) | 2 | no | 4900 | 9800 | 2 |  | 2 | 9800 | 0 | 9800
| RCC wall opening water tank wall access opening (Level 31-32) (0.6m x 0.6m x 0.5m) | 4 | no | 2450 | 9800 | 2 |  | 2 | 4900 | 0 | 4900
| RCC opeining (Level 30) (1.1m x 1.4m x 0.5m) | 1 | no | 3700 | 3700 | 1 |  | 1 | 3700 | 0 | 3700
| RCC opeining (Level 31) (1.1m x 1.4m x 0.5m) | 1 | no | 3700 | 3700 | 0 |  | 0 | 0 | 0 | 0
| RCC opeining (Level 31) (1.25m x 0.95m x 0.5m) | 1 | no | 2900 | 2900 | 0 |  | 0 | 0 | 0 | 0
| RCC diamond wet cutting of wall in hotel ground floor LV room (1.25m x 0.93m x 0.5m) | 2 | no | 2900 | 5800 | 2 |  | 2 | 5800 | 0 | 5800
WA-C023 R2
| Demolition of existing plinth for Devit base at Level 32 | 42 | no | 950 | 39900 | 2 |  | 2 | 1900 | 0 | 1900
| Demolition of 400mm top portion including proper diamond cutting | 144 | m | 710 | 102240 | 144.4 |  | 144.4 | 102524 | 0 | 102524
| Cutting of beam LB28 (3.6m x 0.8m x 0.5m) | 1 | item | 6700 | 6700 | 1 |  | 1 | 6700 | 0 | 6700
| Cutting of corewll (1.2m x 0.6m x 0.5m) | 1 | Nos | 3300 | 3300 | 1 |  | 1 | 3300 | 0 | 3300
WA-C023 R3
| Demolition of existing plinth due to change in the layout | 1 | item | 6600 | 6600 | 1 |  | 1 | 6600 | 0 | 6600
WA-C023 R4
| Demolition of Planter wall & slab at Level 17 | 1 | item | 31000 | 31000 | 0 |  | 0 | 0 | 0 | 0
| Demolition of rasised slab at Level 2 | 1 | item | 19000 | 19000 | 0 |  | 0 | 0 | 0 | 0
WA-C031
| Demolition, removal and cartaway of Office containers including breaking, removal of concrete foundation, pebbles and isolation of MEP services, strip off of MEP fixtures | 1 | item | 97200 | 97200 | 1 |  | 1 | 97200 | 0 | 97200
WA-C031 R1
| Demolition, removal and cartaway of Office containers including breaking, removal of concrete foundation, pebbles and isolation of MEP services, strip off of MEP fixtures | 1 | item | -97200 | -97200 | 1 |  | 1 | -97200 | 0 | -97200
| Partial demolition works | 1 | item | 46082.45 | 46082.45 | 1 |  | 1 | 46082.45 | 0 | 46082.45
WA-C048
| Partition wall removal, debris handing to DM approved yard | 1 | item | 8650 | 8650 | 0 |  | 0 | 0 | 0 | 0
WA-C059
| Column cutting at Level 28 to 29 | 2 | nos | 5200 | 10400 | 2 |  | 2 | 10400 | 0 | 10400
| No WA |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0
53mm dia - 102mm dia
| 501mm thick to 700mm thick |  |  | 105 | 0 | 7 |  | 7 | 735 | 0 | 735
103mm dia - 152mm dia
| 500mm - 700 mm thick |  |  | 148 | 0 | 2 |  | 2 | 296 | 0 | 296
153mm dia - 202mm dia
| 500mm thick to 700mm thick |  |  | 154 | 0 | 14 |  | 14 | 2156 | 0 | 2156
203mm dia - 302mm dia
| 700mm thick to 800mm thick |  |  | 560 | 0 | 2 |  | 2 | 1120 | 0 | 1120
350mm dia
| 201mm thick - 250mm thick |  |  | 245 | 0 | 3 |  | 3 | 735 | 0 | 735
| 251mm thick - 350mm thick |  |  | 260 | 0 | 1 |  | 1 | 260 | 0 | 260
| 350mm thick - 400mm thck |  |  | 280 | 0 | 1 |  | 1 | 280 | 0 | 280
450mm dia
| 201mm thick - 250mm thick |  |  | 740 | 0 | 3 |  | 3 | 2220 | 0 | 2220
| Wet cutting of slab - 1.3mx0.55mx0.2m |  |  | 3200 | 0 | 2 |  | 2 | 6400 | 0 | 6400
| Wall Cutting level-29 |  |  | 7300 | 0 | 1 |  | 1 | 7300 | 0 | 7300
| Planther box-Level-17 (E11/510) (80% work completed) |  |  | 40600 | 0 | 1 |  | 1 | 36540 | 0 | 36540
| Slab cutting level-24,25,29 (E11/637) |  |  | 2800 | 0 | 4 |  | 4 | 10080 | 0 | 10080
| 21.42M Length x 1.15-0.85-0.00M H x 0.2M T- (QT-2023-0017) |  |  | 8200 | 0 | 0 |  | 0 | 0 | 0 | 0
| Total of Variation |  |  |  | 0 |  |  | 0 | 283028.45 | 0 | 283028.45
| Original Contract | [7 empty] | 242615 | 11194 | 253809
| Variation | [7 empty] | 283028.45 | 0 | 283028.45
0
| Adjustment |  |  |  | 0 |  |  |  | 22373 | 0 | 22373
0
| Total | [7 empty] | 548016.45 | 11194 | 559210.45
[9 empty] | 548016.45 |  | 548016.45
11194
Note on J113: Tharaka Rathnayaka: need to be checked previous assessments to verify the figure