## CL (hidden)
Payment Application
Bond Interior Design LLC
PO Box 15758 |  |  |  |  | PA Date: | 2023-02-28
Dubai, UAE |  |  |  |  | Due Date: | Immediate
Tel: +971-4-2711727 |  |  |  |  | Client Ref: | LOI
Fax: +971-4-2713797 | [5 empty] | 201A22002/SW/ARM/167
TRN: 100033819200003 |  |  |  |  | Payment Application Number: | 08
[5 empty] | Payment Application Type: | Interim 08
M/s. Khansaheb Civil Engineering L.L.C. |  |  |  | Project Number: |  | 1410/1522
Construction Division, |  |  |  | Contract Date: |  | 2022-05-19
Al Rashidiya |  |  |  | Original Contract Value: |  | 4325954.996
P.O. Box 2716, Dubai, UAE. |  |  |  |  | Variations: | 59537
Tel. : +971 4 605 7200 |  |  |  | Revised Contract Value: |  | 4385491.996
TRN :
Kind Attention : Mr. Chris McCann
Project: | Fit-out works at Hotel FOH (SPA, Lobby & All Day Dining) on Plot 18, Business Bay, Dubai
Unit | Item Description |  |  | Amount | VAT | VAT Amount
1 | Value of Work Done |  |  | 3512303.8443
| Gross Invoice Amount(AED) |  |  | 3512303.8443
Less:
1 | Retention 10% |  |  | -351230.38
2 | Previous Certified Amount |  |  | -2072117.7
3 | Previous submitted but not certified-January |  |  | -384735.02
| Total Deductions (AED) |  |  | -2808083.1
Net Invoice Amount Excluding VAT (AED) |  |  |  | 704220.74 | 5% | 35211.04
|  |  | Total Invoice Amount EX- VAT (AED) |  |  | 704220.74
|  |  | VAT Amount (AED) |  |  | 35211.04
|  |  | Total Payable Amount Including VAT (AED) |  |  | 739431.78
(AED : Four Hundred Fifty-Two Thousand One Hundred Sixty-Six and Fils Ninety Only)
Bank : | Arab Bank for Investment and Foreign Trade (Al Masraf)
Dubai Branch, Dubai
Beneficiary: | Bond Interior Design LLC
IBAN Account No.AE 170080000994000016394
Swift Code: ABINAEAA
For Bond Interior Design L.L.C.
Prepared By |  | Checked By | Authorised By | Received By: | (Acknowledgement Receipt)
Name:
Title:
Mohamed Thariq |  | Sanjay Gaikwad | Saad A. Moaswes | Signature:
Sr. Quantity Surveyor |  | Sr.Project Manager | Managing Director | Date: |  | Time:

## SUMMARY
DORCHESTER HOTEL & RESIDENCIES
FITOUT & ELECTRICAL PACKAGE FOR HOTEL L2,L4,L28
PROGRESS SUMMARY
| Sr. No. | Description | Amount | Amount Certified by Omniyat | Amount to be claimed from Khansaheb | Value of Work Done under Khansaheb Contract |  |  | This is our assessment (previously done by Mithun)
[6 empty] | Previous | Current | Cumulative | Bond Claimed | Assessment | Cumulative
ORIGINAL SCOPE
| 1 | Fitout of hotel lobby at L2 | 3816677 | 2345348.0027 | 1471328.9973 | 1465454.0253 | 5199.4721 | 1470653.4973 | 99.95% | 95% | 1397762.5475
| 2 | Fit out of hotel all day dining at L4 | 3286191 | 2536282.0002 | 749908.9998 | 745120.034 | 3172.9658 | 748292.9998 | 99.78% | 95% | 712413.5498
| 3 | Fitout of hotel spa at L28 | 3692282 | 2024108.9945 | 1668173.0055 | 525288.339 | 348256.5337 | 873544.8727 | 52.37% | 45% | 750677.8525 |  | 519439.8196 | -231238.0328
| 4 | Discount | -199930 | -129355 | -70575 | -29045.97 | -6604.8948 | -29045.97 | 41.16% | 73.55% | -51911.3993
| 5 | MEP preliminaries | 102000 | 65994.0006 | 36005.9994 | 20968.6005 | 4056.9018 | 20968.6005 | 58.24% | 58.24% | 20968.6005
| 6 | MEP works to hotel lobby - L2 | 212378 | 130506.0033 | 81871.9967 | 81061.9967 | 0 | 81061.9967 | 99.01% | 85% | 69591.1972
| 7 | MEP works to all day dining - L4 | 286720 | 221289.998 | 65430.002 | 60503.652 | 0 | 60503.652 | 92.47% | 85% | 55615.5017
| 8 | MEP works to spa - L28 | 150573 | 82544.0048 | 68028.9952 | 23650.1752 | 20140.02 | 43790.1952 | 64.37% | 45% | 30613.0479 |  | 10204.3493 | -20408.6986
|  | Subtotal - 1 | 11346891 | 7276718.004 | 4070172.996 | 2893000.8527 | 374220.9986 | 3269769.8443 |  |  | 2985730.8978 | -284038.9466 | -284038.9466
VARIATIONS
| 1 | Sanitaryware additions and omissions | 18415 |  | 18415 | 18415 | 0 | 18415 | 100% | 85% | 15652.75 | at Level 2
| 2 | Omission of water basin to L28 spa area | -14685 |  | -14685 | -14685 | 0 | -14685 | 100% | 100% | -14685
| 3 | Provisional sum adjustment for lift car | -9612 |  | -9612 | -9612 | 0 | -9612 | 100% | 100% | -9612
| 4 | Supply of cisterns for spa area | 4251 | 4251 | 0 | 0 | 0 | 0
| 5 | Supply and application of waterproofing | 46991 | 46991 | 0 | 0 | 0 | 0
| 6 | Supply and installation of additional partitions to L28 | 201091 | 100545 | 100546 | 100546 | 0 | 100546 | 100% | 100% | 100546
| 7 | Provisional sum adjustment for ironmongery | 10621 |  | 10621 | 10621 | 0 | 10621 | 100% | 73.55% | 7812.2702 | at Level 2, 4 & 28
| 8 | Supply and installation of shaft wall ceilings at L28 | 13303 | 13303 | 0 | 0 | 0 | 0
| 9 | Supply and installation of sanitaryware to L28 | 13068 |  | 13068 | 13068 | -13068 | 0 | 0% | 0% | 0
| 10 | Supply and installation of baby change station | 4166 |  | 4166 | 4166 | -180 | 3986 | 95.68% | 50% | 2083 | at Level 2
| 11 | Additional works to L2 and L28 | 113263 |  | 113263 | 113263 | 0 | 113263 | 100% | 68.43% | 77508.7274 | at Level 2 & 28
| 12 | Rectification works as per damage report | 20000 |  | 20000 | 20000 | 0 | 20000 | 100% | 50% | 10000 | Damage due to rain in Jan 2022 at Level 2
| 13 | Gym Area Electrical Works |  | 0 | 59537 | 59537 |  |  | 0% |  | 0 | Cannot include, as it should be the part of WFA
|  | Subtotal - 2 | 420872 | 165090 | 255782 | 315319 | -13248 | 242534 |  |  | 189305.7477 | -53228.2523 | -53228.2523
|  | Material On Site | 0 | 0
|  | Subtotal - 3 | 0 | 0 | 0
| TOTAL |  | 11767763 | 7441808.004 | 4325954.996 | 3208319.8527 | 360972.9986 | 3512303.8443 |  |  | 3175036.6454 | -337267.1989 | -337267.1989

## Prelims-Fitout (hidden)
#REF!
PRELIMINARY BREAKDOWN - FITOUT PACKAGE
| Description | Qty | Rate | Amount | Progress
[5 empty] | Previous |  |  |  | Total
[5 empty] | % | Amount | % | Amount | % | Amount
| Mobilisation | 0.1 | 759999.03 | 75999.903 | 100% | 75999.903 | 0% | 0 | 100% | 75999.903
| Time related | 0.3 | 759999.03 | 227999.709 | 87.5% | 199499.7454 | 0% | 0 | 87.5% | 199499.7454
| Progress related | 0.6 | 759999.03 | 455999.418 | 63.94% | 291583.312 | 0% | 0 | 63.94% | 291583.312
0%
| Total Preliminaries | 1 |  | 759999.03 | 74.62% | 567082.9604 | 0% | 0 | 74.62% | 567082.9604