## Summary
No | Description | BOQ | Previous | This Month | Cumulative
| Original Scope | 918183.61 | 835292.76 | 45230.6 | 880523.36
| Variation |  | 45030.5 | 32777.445 | 77807.945
|  |  | 880323.26 | 78008.045 | 958331.305
| Advance Payment |  | 75000 |  | 75000
| Advance Payment Recovery |  | -75000 | 0 | -75000
|  |  | 880323.26 | 78008.045 | 958331.305
|  | KCE Claim | 880323.37 | 86619.68 | 966943.05
|  | Difference | -0.11 | -8611.635 | -8611.745

## Breakdown
No | Description | Qty | Unit | Rate | Amount | Previous Amount | This Month Amount | % | Cumulative Amount
Partitions
To Male toilet
1 | DW- 6, 100 mm partition, 4 MTR HEIGHT | 50.62 | m2 | 235 | 11895.7 | 11895.7 | 0 | 100% | 11895.7
2 | DW- 3 150 mm, HEIGHT 4 MTR | 88.84 | m2 | 235 | 20877.4 | 20877.4 | 0 | 100% | 20877.4
3 | DW- 3a 150 mm HEIGHT 8 MTR | 67.42 | m2 | 300 | 20226 | 20226 | 0 | 100% | 20226
4 | DW- 4, 150 mm partition, HEIGHT 4 MTR | 4.8 | m2 | 220 | 1056 | 1056 | 0 | 100% | 1056
5 | DW-2 200 mm partition, HEIGHT 4 MTR | 13.5 | m2 | 210 | 2835 | 2835 | 0 | 100% | 2835
To Female toilet
6 | DW- 6, 100 mm partition, 4 MTR HEIGHT | 49.4 | m2 | 235 | 11609 | 11609 | 0 | 100% | 11609
7 | DW- 3 150 mm partition, 4 MTR HEIGHT | 56.56 | m2 | 235 | 13291.6 | 13291.6 | 0 | 100% | 13291.6
8 | DW-1 300 mm partition | 30.5 |  | 238 | 7259 | 7259 | 0 | 100% | 7259
Meeting Room 1 & 2
9 | DW-3.1 Gypsum Board - 150mm thk 8 MTR HEIGHT | 637.2 | m2 | 290 | 184788 | 184788 | 0 | 100% | 184788
10 | DW-3.1a Gypsum Board - 150 mm thk 4 MTR HEIGHT | 195 | m2 | 195 | 38025 | 38025 | 0 | 100% | 38025
11 | DW-5.1 Gypsum Board - 150 mm thk 4 MTR HEIGHT | 138 | m2 | 330 | 45540 | 45540 | 0 | 100% | 45540
12 | DW-6.1 Gypsum Board - 100 mm thk 8 MTR HEIGHT | 802 | m2 | 145 | 116290 | 116290 | 0 | 100% | 116290
13 | DW-6.2 Gypsum Board - 100 mm thk 6.2 MTR HEIGHT (DRYWALL PARTITIONS AS PER NEW DESIGN) | 105 | m2 | 275 | 28875 | 20212.5 | 8662.5 | 100% | 28875
14 | DW-7 Gypsum Board - 100 mm thk 4 MTR HEIGHT (Wall Lining) | 30 | m2 | 145 | 4350 | 4350 | 0 | 100% | 4350
15 | DW-7.1 Gypsum Board - 100 mm thk 6.2 MTR HEIGHT (Wall Lining) | 320 | m2 | 145 | 46400 | 43355 | 3045 | 100% | 46400
Partition Total
Ceiling
BALL ROOM
16 | Gypsum Board ceiling; type HTL-WC-20 | 383.68 | m2 | 95 | 36449.6 | 30982.16 | 5467.44 | 100% | 36449.6
17 | Bulkhead; type HTL-WC-20, 200 mm height | 409 | m | 95 | 38855 | 33026.75 | 0 | 85% | 33026.75
18 | Light cove; type HTL-PT-08, 225 mm x 100 mm | 189 | m | 90 | 17010 | 11907 | 5103 | 100% | 17010
19 | Curtain Pelmet | 15.5 | m | 135 | 2092.5 | 2092.5 | 0 | 100% | 2092.5
Meeting room 1
20 | Gypsum Board ceiling; type HTL-WC-19 | 42.3 | m2 | 90 | 3807 | 3807 | 0 | 100% | 3807
21 | Cornice; type HTL-WC-19 400 mm long curved section | 47 | m | 125 | 5875 | 5875 | 0 | 100% | 5875
22 | Light Cove - 250 x 90 mm 'L' shaped section | 47 | m | 85 | 3995 | 2796.5 | 1198.5 | 100% | 3995
23 | Curtain Pelmet | 19.7 | m | 135 | 2659.5 | 2659.5 | 0 | 100% | 2659.5
Meeting room 2
24 | Gypsum Board ceiling; type HTL-WC-19 | 58.5 | m2 | 95 | 5557.5 | 5557.5 | 0 | 100% | 5557.5
25 | Vaulted ceiling; type HTL-WC-19 | 6 | m2 | 220 | 1320 | 1188 | 0 | 90% | 1188
26 | Cornice; type HTL-WC-19 400 mm long curved section | 26 | m | 125 | 3250 | 3250 | 0 | 100% | 3250
27 | Light Cove - 250 x 90 mm 'L' shaped section | 26 | m | 85 | 2210 | 1547 | 663 | 100% | 2210
28 | Curtain Pelmet | 18.35 | m | 135 | 2477.25 | 2477.25 | 0 | 100% | 2477.25
Corridor
29 | Vaulted ceiling; type HTL-WC-19 | 343 | m2 | 220 | 75460 | 71687 | 3773 | 100% | 75460
Disable Lift lobby
30 | Ceiling; type HTL-WC-19 | 16 | m2 | 90 | 1440 | 1008 | 432 | 100% | 1440
Hall
31 | Gypsum Board ceiling; type HTL-WC-19 | 72.684 | m2 | 90 | 6541.56 | 6541.2 | 0.36 | 100% | 6541.56
32 | Cornice; type HTL-WC-19 400 mm long curved section | 29 | m | 125 | 3625 | 2537.5 | 1087.5 | 100% | 3625
33 | Light Cove - 250 x 90 mm 'L' shaped section | 29 | m | 85 | 2465 | 1725.5 | 739.5 | 100% | 2465
34 | Vaulted ceiling; type HTL-WC-19 | 13 | m2 | 220 | 2860 | 2002 | 858 | 100% | 2860
Lift lobby
35 | Gypsum Board ceiling; type HTL-WC-19 | 21 | m2 | 90 | 1890 | 1890 | 0 | 100% | 1890
36 | Bulkhead; type HTL-PT-08, 100 mm height | 51 | m | 90 | 4590 | 4590 | 0 | 100% | 4590
37 | Lit cornice; type HTL-WC-20, 100 mm height | 55 | m | 90 | 4950 | 4950 | 0 | 100% | 4950
Pre-function space
38 | Prefunction area; type HTL-PT-08 | 117.9 | m2 | 90 | 10611 | 9549.9 | 1061.1 | 100% | 10611
39 | Bulkhead; type HTL-PT-08, 1000 mm height | 57 | m | 90 | 5130 | 3591 | 1539 | 100% | 5130
Breakout space
40 | Gypsum Board ceiling; type HTL-PT-08 | 78.3 | m2 | 90 | 7047 | 7047 | 0 | 100% | 7047
41 | Bulkhead; type HTL-PT-08, including 150 mm high bulkhead and 150 x 90 x 90 mm cove light | 60 | m | 175 | 10500 | 10500 | 0 | 100% | 10500
Meeting rooms & Breakout Space
42 | Vertical Bulkhead / Wall lining - 4 mtr height | 68 | m2 | 150 | 10200 | 10200 | 0 | 100% | 10200
Ballroom male toilet
43 | Gypsum Board Ceiling; type HTL-PT-03 | 46 | m2 | 110 | 5060 | 3542 | 1518 | 100% | 5060
44 | Cavetto cornice; type HTL-PT-03 | 30 | m | 150 | 4500 | 4050 | 450 | 100% | 4500
Ballroom female toilet
45 | Gypsum Board Ceiling; type HTL-PT-03 | 39 | m2 | 110 | 4290 | 4290 | 0 | 100% | 4290
46 | Gypsum Board Ceiling; with covering; type HTL-WC-17 | 2 | m2 | 150 | 300 | 300 | 0 | 100% | 300
47 | Cavetto cornice type HTL-PT-03 | 29 | m | 150 | 4350 | 4350 | 0 | 100% | 4350
Storage
48 | Gypsum Board ceiling; type HTL-PT-08 | 4 | m2 | 110 | 440 | 440 | 0 | 100% | 440
BOH
49 | Gypsum Board ceiling; type HTL-PT-08 | 73.8 | m2 | 110 | 8118 | 6900.3 | 1217.7 | 100% | 8118
Ballroom
Ceiling Finishes
50 | Bulkhead; type HTL-WC-20, 100 mm height | 150 | m | 90 | 13500 | 12150 | 1350 | 100% | 13500
Meeting room 1
51 | Bulkhead; 300 mm height | 38 | m | 90 | 3420 | 3420 | 0 | 100% | 3420
Meeting room 2
52 | Bulkhead; 300 mm height | 36 | m | 90 | 3240 | 3240 | 0 | 100% | 3240
Near Corridor and Toilet
53 | Gypsum Board ceiling; type HTL-WC-19 | 35 | m2 | 90 | 3150 | 2835 | 315 | 100% | 3150
Hall
54 | Bulkhead; 300 mm height | 27 | m | 90 | 2430 | 2430 | 0 | 100% | 2430
BOH
55 | Access Panels and Temporary openings
56 | Access Panels - 600 x 600 mm | 70 | Nos | 185 | 12950 |  | 0
57 | Temporary Openings and closing - 600 x 600 mm | 350 | Nos | 75 | 26250 | 750 | 6750 | 28.57% | 7500
[5 empty] | 918183.61 | 835292.76 | 45230.6 |  | 880523.36
Variation
1 | Variation 01- secindary support for curved ceiling. | 1 | LS | 45030.5 | 45030.5 | 45030.5 | -4503.05 | 90% | 40527.45
2 | Omission
| DW-6.1 Gypsum Board - 100 mm thk 8 MTR HEIGHT | -802 | m2 | 145 | -116290 |  | -116290 | 100% | -116290
Addition
| DW-6.1 Gypsum Board - 100 mm thk 8 MTR HEIGHT | 295 | m2 | 330 | 97350 |  | 97350 | 100% | 97350
3 | DW-3a Variation addetional wall done
| 152mm 4 mtr high accoustic wall done | 6.55 | m2 | 235 | 1539.25 |  | 1385.325 | 90% | 1385.325
4 | DW-3 Variation addetional wall done
| 152mm 8 mtr high accoustic wall done | 12.79 | m2 | 300 | 3837 |  | 3453.3 | 90% | 3453.3
5 | DW-6.1 Variation addetional wall done
| wall lining done @ dorma sliding pocket area | 64.94 | m2 | 145 | 9416.3 |  | 8474.67 | 90% | 8474.67
6 | DW-3 Variation addetional wall done
| 152mm 8 mtr high accoustic wall done near BOH area | 85.2 | m2 | 290 | 24708 |  | 22237.2 | 90% | 22237.2
7 | light cove Variation
| 152mm 8 mtr high accoustic wall done near BOH area | 1 | Nos | 22020.5 | 22020.5 |  | 0
8 | Access panel Variation v-05
| Supplay and instalation of 600x600 acces panel inluding taping and jointing. | 31 | Nos | 185 | 5735 |  | 2294 | 40% | 2294
| Supplay and instalation of 300x300 acces panel inluding taping and jointing. | 46 | Nos | 170 | 7820 |  | 3128 | 40% | 3128
| Supplay and instalation of 450x450 acces panel inluding taping and jointing. | 21 | Nos | 175 | 3675 |  | 1470 | 40% | 1470
| Supplay and instalation of 250x300 acces panel inluding taping and jointing. | 3 | Nos | 160 | 480 |  | 192 | 40% | 192
| Supplay and instalation of 500x500 acces panel inluding taping and jointing. | 4 | Nos | 175 | 700 |  | 280 | 40% | 280
| Supplay and instalation of 800x800 acces panel inluding taping and jointing. | 2 | Nos | 235 | 470 |  | 188 | 40% | 188
| Supplay and instalation of 400x400 acces panel inluding taping and jointing. | 1 | Nos | 165 | 165 |  | 66 | 40% | 66
| Supplay and instalation of 600x300 acces panel inluding taping and jointing. | 20 | Nos | 180 | 3600 |  | 1440 | 40% | 1440
| Supplay and instalation of 400x300 acces panel inluding taping and jointing. | 1 | Nos | 160 | 160 |  | 64 | 40% | 64
| Supplay and instalation of 900x300 acces panel inluding taping and jointing. | 1 | Nos | 250 | 250 |  | 100 | 40% | 100
| GRG in corridor entrance area Variation V-06 | 1 | LS | 5250 | 5250 |  | 2100 | 40% | 2100
| New accoustic partition Variation V-07 | 1 | LS | 23370 | 23370 |  | 9348 | 40% | 9348
[5 empty] | 139286.55 | 45030.5 | 32777.445 |  | 77807.945
[5 empty] | 1057470.16 | 880323.26 | 78008.045 |  | 958331.305
Note on I146: Himal Kosala: 90% until rate approval from OME