## Summary
No | Description | BOQ | Previous | This Month | Cumulative
| Original Scope | 918183.61 | 661099.345 | 174193.523 | 835292.868
| Variation |  | 45030.5 | 0 | 45030.5
|  |  | 706129.845 | 174193.523 | 880323.368
| Advance Payment |  | 75000 |  | 75000
| Advance Payment Recovery |  | -70612.9845 | -4387.0155 | -75000
|  |  | 710516.8605 | 169806.5075 | 880323.368

## Ceiling & Part
PAYMENT APPLICATION BREAKDOWN
S.No | Description | Unit | Orginal Quantity | % Deduction | Final Qty | Rate | Amount | Previous Qty | Current Qty | Cumulative | Percentage % | Total Work Done
PARTITION
To Male toilet
1 | DW- 6, 100 mm partition, 4 MTR HEIGHT | SQM | 101.24 | 50% | 50.62 | 235 | 11895.7
| Delivery of materials 40% | SQM |  |  | 50.62 | 94 | 4758.28 | 50.62 |  | 50.62 | 100% | 4758.28
| Installation of framing 30% | SQM |  |  | 50.62 | 70.5 | 3568.71 | 50.62 | 0 | 50.62 | 100% | 3568.71
| Installation of gypsum boards one side with insulation 10% | SQM |  |  | 50.62 | 23.5 | 1189.57 | 50.62 | 0 | 50.62 | 100% | 1189.57
| Installation of gypsum boards second side 10% | SQM |  |  | 50.62 | 23.5 | 1189.57 | 50.62 | 0 | 50.62 | 100% | 1189.57
| Installation of joint tapping 10% | SQM |  |  | 50.62 | 23.5 | 1189.57 | 50.62 | 0 | 50.62 | 100% | 1189.57
2 | DW- 3 150 mm, HEIGHT 4 MTR | SQM | 177.68 | 50% | 88.84 | 235 | 20877.4
| Delivery of materials 40% | SQM |  |  | 88.84 | 94 | 8350.96 | 88.84 | 0 | 88.84 | 100% | 8350.96
| Installation of framing 30% | SQM |  |  | 88.84 | 70.5 | 6263.22 | 88.84 | 0 | 88.84 | 100% | 6263.22
| Installation of gypsum boards one side with insulation 10% | SQM |  |  | 88.84 | 23.5 | 2087.74 | 88.84 | 0 | 88.84 | 100% | 2087.74
| Installation of gypsum boards second side 10% | SQM |  |  | 88.84 | 23.5 | 2087.74 | 88.84 | 0 | 88.84 | 100% | 2087.74
| Installation of joint tapping 10% | SQM |  |  | 88.84 | 23.5 | 2087.74 | 88.84 | 0 | 88.84 | 100% | 2087.74
3 | DW- 3a 150 mm HEIGHT 8 MTR | SQM | 134.84 | 50% | 67.42 | 300 | 20226
| Delivery of materials 40% | SQM |  |  | 67.42 | 120 | 8090.4 | 67.42 | 0 | 67.42 | 100% | 8090.4
| Installation of framing 30% | SQM |  |  | 67.42 | 90 | 6067.8 | 67.42 | 0 | 67.42 | 100% | 6067.8
| Installation of gypsum boards one side with insulation 10% | SQM |  |  | 67.42 | 30 | 2022.6 | 67.42 | 0 | 67.42 | 100% | 2022.6
| Installation of gypsum boards second side 10% | SQM |  |  | 67.42 | 30 | 2022.6 | 67.42 | 0 | 67.42 | 100% | 2022.6
| Installation of joint tapping 10% | SQM |  |  | 67.42 | 30 | 2022.6 | 67.42 | 0 | 67.42 | 100% | 2022.6
4 | DW- 4, 150 mm partition, HEIGHT 4 MTR | SQM | 9.6 | 50% | 4.8 | 220 | 1056
| Delivery of materials 40% | SQM |  |  | 4.8 | 88 | 422.4 | 4.8 | 0 | 4.8 | 100% | 422.4
| Installation of framing 30% | SQM |  |  | 4.8 | 66 | 316.8 | 4.8 | 0 | 4.8 | 100% | 316.8
| Installation of gypsum boards one side with insulation 10% | SQM |  |  | 4.8 | 22 | 105.6 | 4.8 | 0 | 4.8 | 100% | 105.6
| Installation of gypsum boards second side 10% | SQM |  |  | 4.8 | 22 | 105.6 | 4.8 | 0 | 4.8 | 100% | 105.6
| Installation of joint tapping 10% | SQM |  |  | 4.8 | 22 | 105.6 | 4.8 | 0 | 4.8 | 100% | 105.6
5 | DW-2 200 mm partition, HEIGHT 4 MTR | SQM | 27 | 50% | 13.5 | 210 | 2835
| Delivery of materials 40% | SQM |  |  | 13.5 | 84 | 1134 | 13.5 | 0 | 13.5 | 100% | 1134
| Installation of framing 30% | SQM |  |  | 13.5 | 63 | 850.5 | 13.5 | 0 | 13.5 | 100% | 850.5
| Installation of gypsum boards one side with insulation 10% | SQM |  |  | 13.5 | 21 | 283.5 | 13.5 | 0 | 13.5 | 100% | 283.5
| Installation of gypsum boards second side 10% | SQM |  |  | 13.5 | 21 | 283.5 | 13.5 | 0 | 13.5 | 100% | 283.5
| Installation of joint tapping 10% | SQM |  |  | 13.5 | 21 | 283.5 | 13.5 | 0 | 13.5 | 100% | 283.5
To Female toilet
7 | DW- 6, 100 mm partition, 4 MTR HEIGHT | SQM | 98.8 | 50% | 49.4 | 235 | 11609
| Delivery of materials 40% | SQM |  |  | 49.4 | 94 | 4643.6 | 49.4 | 0 | 49.4 | 100% | 4643.6
| Installation of framing 30% | SQM |  |  | 49.4 | 70.5 | 3482.7 | 49.4 | 0 | 49.4 | 100% | 3482.7
| Installation of gypsum boards one side with insulation 10% | SQM |  |  | 49.4 | 23.5 | 1160.9 | 49.4 | 0 | 49.4 | 100% | 1160.9
| Installation of gypsum boards second side 10% | SQM |  |  | 49.4 | 23.5 | 1160.9 | 49.4 | 0 | 49.4 | 100% | 1160.9
| Installation of joint tapping 10% | SQM |  |  | 49.4 | 23.5 | 1160.9 | 49.4 | 0 | 49.4 | 100% | 1160.9
8 | DW- 3 150 mm partition, 4 MTR HEIGHT | SQM | 113.12 | 50% | 56.56 | 235 | 13291.6
| Delivery of materials 40% | SQM |  |  | 56.56 | 94 | 5316.64 | 56.56 | 0 | 56.56 | 100% | 5316.64
| Installation of framing 30% | SQM |  |  | 56.56 | 70.5 | 3987.48 | 56.56 | 0 | 56.56 | 100% | 3987.48
| Installation of gypsum boards one side with insulation 10% | SQM |  |  | 56.56 | 23.5 | 1329.16 | 56.56 | 0 | 56.56 | 100% | 1329.16
| Installation of gypsum boards second side 10% | SQM |  |  | 56.56 | 23.5 | 1329.16 | 56.56 | 0 | 56.56 | 100% | 1329.16
| Installation of joint tapping 10% | SQM |  |  | 56.56 | 23.5 | 1329.16 | 56.56 | 0 | 56.56 | 100% | 1329.16
9 | DW-1 300 mm partition |  | 61 | 50% | 30.5 | 238 | 7259
| Delivery of materials 40% | SQM |  |  | 30.5 | 95.2 | 2903.6 | 30.5 | 0 | 30.5 | 100% | 2903.6
| Installation of framing 30% | SQM |  |  | 30.5 | 71.4 | 2177.7 | 30.5 | 0 | 30.5 | 100% | 2177.7
| Installation of gypsum boards one side with insulation 10% | SQM |  |  | 30.5 | 23.8 | 725.9 | 30.5 | 0 | 30.5 | 100% | 725.9
| Installation of gypsum boards second side 10% | SQM |  |  | 30.5 | 23.8 | 725.9 | 30.5 | 0 | 30.5 | 100% | 725.9
| Installation of joint tapping 10% | SQM |  |  | 30.5 | 23.8 | 725.9 | 30.5 | 0 | 30.5 | 100% | 725.9
Meeting Room 1 & 2
10 | DW-3.1 Gypsum Board - 150mm thk 8 MTR HEIGHT | SQM | 1062 | 60% | 637.2 | 290 | 184788
| Delivery of materials 40% | SQM |  |  | 637.2 | 116 | 73915.2 | 637.2 | 0 | 637.2 | 100% | 73915.2
| Installation of framing 30% | SQM |  |  | 637.2 | 87 | 55436.4 | 637.2 | 0 | 637.2 | 100% | 55436.4
| Installation of gypsum boards one side with insulation 10% | SQM |  |  | 637.2 | 29 | 18478.8 | 637.2 | 0 | 637.2 | 100% | 18478.8
| Installation of gypsum boards second side 10% | SQM |  |  | 637.2 | 29 | 18478.8 | 637.2 | 0 | 637.2 | 100% | 18478.8
| Installation of joint tapping 10% | SQM |  |  | 637.2 | 29 | 18478.8 | 637.2 | 0 | 637.2 | 100% | 18478.8
11 | DW-3.1a Gypsum Board - 150 mm thk 4 MTR HEIGHT | SQM | 325 | 60% | 195 | 195 | 38025
| Delivery of materials 40% | SQM |  |  | 195 | 78 | 15210 | 195 | 0 | 195 | 100% | 15210
| Installation of framing 30% | SQM |  |  | 195 | 58.5 | 11407.5 | 195 | 0 | 195 | 100% | 11407.5
| Installation of gypsum boards one side with insulation 10% | SQM |  |  | 195 | 19.5 | 3802.5 | 195 | 0 | 195 | 100% | 3802.5
| Installation of gypsum boards second side 10% | SQM |  |  | 195 | 19.5 | 3802.5 | 195 | 0 | 195 | 100% | 3802.5
| Installation of joint tapping 10% | SQM |  |  | 195 | 19.5 | 3802.5 | 195 | 0 | 195 | 100% | 3802.5
| DW-5.1 Gypsum Board - 150 mm thk 4 MTR HEIGHT | SQM | 138 | 100% | 138 | 330 | 45540
| Delivery of materials 40% | SQM |  |  | 138 | 132 | 18216 | 138 | 0 | 138 | 100% | 18216
| Installation of framing 30% | SQM |  |  | 138 | 99 | 13662 | 138 | 0 | 138 | 100% | 13662
| Installation of gypsum boards one side with insulation 10% | SQM |  |  | 138 | 33 | 4554 | 138 | 0 | 138 | 100% | 4554
| Installation of gypsum boards second side 10% | SQM |  |  | 138 | 33 | 4554 | 138 | 0 | 138 | 100% | 4554
| Installation of joint tapping 10% | SQM |  |  | 138 | 33 | 4554 | 138 | 0 | 138 | 100% | 4554
13 | DW-6.1 Gypsum Board - 100 mm thk 8 MTR HEIGHT | SQM | 802 | 100% | 802 | 145 | 116290
| Delivery of materials 40% | SQM |  |  | 802 | 58 | 46516 | 802 | 0 | 802 | 100% | 46516
| Installation of framing 30% | SQM |  |  | 802 | 43.5 | 34887 | 802 | 0 | 802 | 100% | 34887
| Installation of gypsum boards one side with insulation 10% | SQM |  |  | 802 | 14.5 | 11629 | 802 | 0 | 802 | 100% | 11629
| Installation of gypsum boards second side 10% | SQM |  |  | 802 | 14.5 | 11629 | 802 |  | 802 | 100% | 11629
| Installation of joint tapping 10% | SQM |  |  | 802 | 14.5 | 11629 | 802 |  | 802 | 100% | 11629
13 | DW-6.1 Gypsum Board - 100 mm thk 8 MTR HEIGHT | SQM | TBC
| Delivery of materials 40% | SQM |  |  | 0 |  |  |  |  | 0 |  | 0
| Installation of framing 30% | SQM |  |  | 0 |  |  |  |  | 0 |  | 0
| Installation of gypsum boards one side with insulation 10% | SQM |  |  | 0 |  |  |  |  | 0 |  | 0
| Installation of gypsum boards second side 10% | SQM |  |  | 0 |  |  |  |  | 0 |  | 0
| Installation of joint tapping 10% | SQM |  |  | 0 |  |  |  |  | 0 |  | 0
14 | DW-6.2 Gypsum Board - 100 mm thk 6.2 MTR HEIGHT (DRYWALL PARTITIONS AS PER NEW DESIGN) | m2 | 105 | 100% | 105 | 275 | 28875
| Delivery of materials 40% | SQM |  |  | 105 | 110 | 11550 | 105 | 0 | 105 | 100% | 11550
| Installation of framing 30% | SQM |  |  | 105 | 82.5 | 8662.5 |  | 52.5 | 52.5 | 50% | 4331.25
| Installation of gypsum boards one side with insulation 20% | SQM |  |  | 105 | 55 | 5775 |  | 52.5 | 52.5 | 50% | 2887.5
| Installation of joint tapping 10% | SQM |  |  | 105 | 27.5 | 2887.5 |  | 52.5 | 52.5 | 50% | 1443.75
15 | DW-7 Gypsum Board - 100 mm thk 4 MTR HEIGHT (Wall Lining) | m2 | 30 | 100% | 30 | 145 | 4350
| Delivery of materials 40% | SQM |  |  | 30 | 58 | 1740 | 30 | 0 | 30 | 100% | 1740
| Installation of framing 30% | SQM |  |  | 30 | 43.5 | 1305 | 30 | 0 | 30 | 100% | 1305
| Installation of gypsum boards one side with insulation 20% | SQM |  |  | 30 | 29 | 870 | 30 | 0 | 30 | 100% | 870
| Installation of joint tapping 10% | SQM |  |  | 30 | 14.5 | 435 | 30 | 0 | 30 | 100% | 435
16 | DW-7.1 Gypsum Board - 100 mm thk 6.2 MTR HEIGHT (Wall Lining) | m2 | 320 | 100% | 320 | 145 | 46400
| Delivery of materials 40% | SQM |  |  | 320 | 58 | 18560 | 320 | 0 | 320 | 100% | 18560
| Installation of framing 30% | SQM |  |  | 320 | 43.5 | 13920 | 320 | 0 | 320 | 100% | 13920
| Installation of gypsum boards one side with insulation 20% | SQM |  |  | 320 | 29 | 9280 | 0 | 250 | 250 | 78.12% | 7250
| Installation of joint tapping 10% | SQM |  |  | 320 | 14.5 | 4640 |  | 250 | 250 | 78.12% | 3625
| Partition Total | [5 empty] | 553317.7 |  |  |  |  | 541610.2
CEILING
BALL ROOM
17 | Gypsum Board ceiling; type HTL-WC-20 | m2 | 383.68 | 100% | 383.68 | 95
| Delivery of materials 40% |  |  |  | 383.68 | 38 | 14579.84 | 383.68 | 0 | 383.68 | 100% | 14579.84
| Installation of framing 30% |  |  |  | 383.68 | 28.5 | 10934.88 | 191.84 | 191.84 | 383.68 | 100% | 10934.88
| Installation of gypsum board 20% |  |  |  | 383.68 | 19 | 7289.92 |  | 191.84 | 191.84 | 50% | 3644.96
| Installation of joint tapping 10% |  |  |  | 383.68 | 9.5 | 3644.96 |  | 191.84 | 191.84 | 50% | 1822.48
18 | Bulkhead; type HTL-WC-20, 200 mm height | m | 409 | 100% |  | 95
| Delivery of materials 40% |  |  |  | 409 | 38 | 15542 | 204.5 | 204.5 | 409 | 100% | 15542
| Installation of framing 30% |  |  |  | 409 | 28.5 | 11656.5 | 204.5 | 204.5 | 409 | 100% | 11656.5
| Installation of gypsum board 20% |  |  |  | 409 | 19 | 7771 |  |  | 204.5 | 50% | 3885.5
| Installation of joint tapping 10% |  |  |  | 409 | 9.5 | 3885.5 |  |  | 204.5 | 50% | 1942.75
19 | Light cove; type HTL-PT-08, 225 mm x 100 mm | m | 189 | 100% |  | 90
| Delivery of materials 40% |  |  |  | 189 | 36 | 6804 |  | 189 | 189 | 100% | 6804
| Installation of framing 30% |  |  |  | 189 | 27 | 5103 |  | 189 | 189 | 100% | 5103 |  | 1088.004
| Installation of gypsum board 20% |  |  |  | 189 | 18 | 3402 |  |  | 0 | 0% | 0
| Installation of joint tapping 10% |  |  |  | 189 | 9 | 1701 |  |  | 0 | 0% | 0
20 | Curtain Pelmet | m | 15.5 | 100% |  | 135
| Delivery of materials 40% |  |  |  | 15.5 | 54 | 837 | 15.5 |  | 15.5 | 100% | 837
| Installation of framing 30% |  |  |  | 15.5 | 40.5 | 627.75 | 15.5 |  | 15.5 | 100% | 627.75
| Installation of gypsum board 20% |  |  |  | 15.5 | 27 | 418.5 | 15.5 |  | 15.5 | 100% | 418.5
| Installation of joint tapping 10% |  |  |  | 15.5 | 13.5 | 209.25 | 15.5 |  | 15.5 | 100% | 209.25
Meeting room 1
21 | Gypsum Board ceiling; type HTL-WC-19 | m2 | 42.3 |  | 42.3 | 90
| Delivery of materials 40% |  |  |  | 42.3 | 36 | 1522.8 | 42.3 |  | 42.3 | 100% | 1522.8
| Installation of framing 30% |  |  |  | 42.3 | 27 | 1142.1 | 42.3 |  | 42.3 | 100% | 1142.1
| Installation of gypsum board 20% |  |  |  | 42.3 | 18 | 761.4 |  | 42.3 | 42.3 | 100% | 761.4
| Installation of joint tapping 10% |  |  |  | 42.3 | 9 | 380.7 |  | 42.3 | 42.3 | 100% | 380.7
22 | Cornice; type HTL-WC-19 400 mm long curved section | m | 47 |  |  | 125
| Delivery of materials 40% |  |  |  | 47 | 50 | 2350 |  | 47 | 47 | 100% | 2350
| Installation of framing 30% |  |  |  | 47 | 37.5 | 1762.5 |  | 47 | 47 | 100% | 1762.5
| Installation of gypsum board 20% |  |  |  | 47 | 25 | 1175 |  | 47 | 47 | 100% | 1175
| Installation of joint tapping 10% |  |  |  | 47 | 12.5 | 587.5 |  | 47 | 47 | 100% | 587.5
23 | Light Cove - 250 x 90 mm 'L' shaped section | m | 47 |  |  | 85
| Delivery of materials 40% |  |  |  | 47 | 34 | 1598 |  | 47 | 47 | 100% | 1598
| Installation of framing 30% |  |  |  | 47 | 25.5 | 1198.5 |  | 47 | 47 | 100% | 1198.5
| Installation of gypsum board 20% |  |  |  | 47 | 17 | 799 |  |  | 0 | 0% | 0
| Installation of joint tapping 10% |  |  |  | 47 | 8.5 | 399.5 |  |  | 0 | 0% | 0
24 | Curtain Pelmet | m | 19.7 |  |  | 135
| Delivery of materials 40% |  |  |  | 19.7 | 54 | 1063.8 | 19.7 |  | 19.7 | 100% | 1063.8
| Installation of framing 30% |  |  |  | 19.7 | 40.5 | 797.85 | 19.7 |  | 19.7 | 100% | 797.85
| Installation of gypsum board 20% |  |  |  | 19.7 | 27 | 531.9 | 19.7 |  | 19.7 | 100% | 531.9
| Installation of joint tapping 10% |  |  |  | 19.7 | 13.5 | 265.95 | 19.7 |  | 19.7 | 100% | 265.95
Meeting room 2
25 | Gypsum Board ceiling; type HTL-WC-19 | m2 | 58.5 |  |  | 95 | [5 empty] | 0
| Delivery of materials 40% |  |  |  | 58.5 | 38 | 2223 | 58.5 |  | 58.5 | 100% | 2223
| Installation of framing 30% |  |  |  | 58.5 | 28.5 | 1667.25 | 58.5 |  | 58.5 | 100% | 1667.25
| Installation of gypsum board 20% |  |  |  | 58.5 | 19 | 1111.5 |  | 58.5 | 58.5 | 100% | 1111.5
| Installation of joint tapping 10% |  |  |  | 58.5 | 9.5 | 555.75 |  | 58.5 | 58.5 | 100% | 555.75
26 | Vaulted ceiling; type HTL-WC-19 | m2 | 6 |  |  | 220 |  |  |  | 0 |  | 0
| Delivery of materials 40% |  |  |  | 6 | 88 | 528 |  | 6 | 6 | 100% | 528
| Installation of framing 30% |  |  |  | 6 | 66 | 396 |  | 6 | 6 | 100% | 396
| Installation of gypsum board 20% |  |  |  | 6 | 44 | 264 |  | 6 | 6 | 100% | 264
| Installation of joint tapping 10% |  |  |  | 6 | 22 | 132 |  |  | 0 | 0% | 0
27 | Cornice; type HTL-WC-19 400 mm long curved section | m | 26 |  |  | 125 |  |  |  | 0 |  | 0
| Delivery of materials 40% |  |  |  | 26 | 50 | 1300 |  | 26 | 26 | 100% | 1300
| Installation of framing 30% |  |  |  | 26 | 37.5 | 975 |  | 26 | 26 | 100% | 975
| Installation of gypsum board 20% |  |  |  | 26 | 25 | 650 |  | 26 | 26 | 100% | 650
| Installation of joint tapping 10% |  |  |  | 26 | 12.5 | 325 |  | 26 | 26 | 100% | 325
28 | Light Cove - 250 x 90 mm 'L' shaped section | m | 26 |  |  | 85 | [5 empty] | 0
| Delivery of materials 40% |  |  |  | 26 | 34 | 884 |  | 26 | 26 | 100% | 884
| Installation of framing 30% |  |  |  | 26 | 25.5 | 663 |  | 26 | 26 | 100% | 663
| Installation of gypsum board 20% |  |  |  | 26 | 17 | 442 |  |  | 0 | 0% | 0
| Installation of joint tapping 10% |  |  |  | 26 | 8.5 | 221 |  |  | 0 | 0% | 0
29 | Curtain Pelmet | m | 18.35 |  |  | 135 | [5 empty] | 0
| Delivery of materials 40% |  |  |  | 18.35 | 54 | 990.9 | 18.35 |  | 18.35 | 100% | 990.9
| Installation of framing 30% |  |  |  | 18.35 | 40.5 | 743.175 | 18.35 |  | 18.35 | 100% | 743.175
| Installation of gypsum board 20% |  |  |  | 18.35 | 27 | 495.45 |  | 18.35 | 18.35 | 100% | 495.45
| Installation of joint tapping 10% |  |  |  | 18.35 | 13.5 | 247.725 |  | 18.35 | 18.35 | 100% | 247.725
Corridor
30 | Vaulted ceiling; type HTL-WC-19 | m2 | 343 |  |  | 220
| Delivery of materials 40% |  |  |  | 343 | 88 | 30184 | 343 | 0 | 343 | 100% | 30184
| Installation of framing 30% |  |  |  | 343 | 66 | 22638 | 343 |  | 343 | 100% | 22638
| Installation of gypsum board 20% |  |  |  | 343 | 44 | 15092 |  | 343 | 343 | 100% | 15092
| Installation of joint tapping 10% |  |  |  | 343 | 22 | 7546 |  | 171.5 | 171.5 | 50% | 3773
Disable Lift lobby
31 | Ceiling; type HTL-WC-19 | m2 | 16 |  |  | 90 | [5 empty] | 0
| Delivery of materials 40% |  |  |  | 16 | 36 | 576 | 16 |  | 16 | 100% | 576
| Installation of framing 30% |  |  |  | 16 | 27 | 432 | 16 |  | 16 | 100% | 432
| Installation of gypsum board 20% |  |  |  | 16 | 18 | 288 |  |  | 0 | 0% | 0
| Installation of joint tapping 10% |  |  |  | 16 | 9 | 144 |  |  | 0 | 0% | 0
Hall
32 | Gypsum Board ceiling; type HTL-WC-19 | m2 | 72.684 |  |  | 90
| Delivery of materials 40% |  |  |  | 72.684 | 36 | 2616.624 | 72.68 |  | 72.68 | 99.99% | 2616.48
| Installation of framing 30% |  |  |  | 72.684 | 27 | 1962.468 | 72.68 |  | 72.68 | 99.99% | 1962.36
| Installation of gypsum board 20% |  |  |  | 72.684 | 18 | 1308.312 |  | 72.684 | 72.684 | 100% | 1308.312
| Installation of joint tapping 10% |  |  |  | 72.684 | 9 | 654.156 |  | 72.684 | 72.684 | 100% | 654.156
33 | Cornice; type HTL-WC-19 400 mm long curved section | m | 29 |  |  | 125
| Delivery of materials 40% |  |  |  | 29 | 50 | 1450 |  | 29 | 29 | 100% | 1450
| Installation of framing 30% |  |  |  | 29 | 37.5 | 1087.5 |  | 29 | 29 | 100% | 1087.5
| Installation of gypsum board 20% |  |  |  | 29 | 25 | 725 |  |  | 0 | 0% | 0
| Installation of joint tapping 10% |  |  |  | 29 | 12.5 | 362.5 |  |  | 0 | 0% | 0
34 | Light Cove - 250 x 90 mm 'L' shaped section | m | 29 |  |  | 85
| Delivery of materials 40% |  |  |  | 29 | 34 | 986 |  | 29 | 29 | 100% | 986
| Installation of framing 30% |  |  |  | 29 | 25.5 | 739.5 |  | 29 | 29 | 100% | 739.5
| Installation of gypsum board 20% |  |  |  | 29 | 17 | 493 |  |  | 0 | 0% | 0
| Installation of joint tapping 10% |  |  |  | 29 | 8.5 | 246.5 |  |  | 0 | 0% | 0
35 | Vaulted ceiling; type HTL-WC-19 | m2 | 13 |  |  | 220
| Delivery of materials 40% |  |  |  | 13 | 88 | 1144 |  | 13 | 13 | 100% | 1144
| Installation of framing 30% |  |  |  | 13 | 66 | 858 |  | 13 | 13 | 100% | 858
| Installation of gypsum board 20% |  |  |  | 13 | 44 | 572 |  |  | 0 | 0% | 0
| Installation of joint tapping 10% |  |  |  | 13 | 22 | 286 |  |  | 0 | 0% | 0
Lift lobby
36 | Gypsum Board ceiling; type HTL-WC-19 | m2 | 21 |  |  | 90
| Delivery of materials 40% |  |  |  | 21 | 36 | 756 | 21 |  | 21 | 100% | 756
| Installation of framing 30% |  |  |  | 21 | 27 | 567 | 21 |  | 21 | 100% | 567
| Installation of gypsum board 20% |  |  |  | 21 | 18 | 378 | 21 |  | 21 | 100% | 378
| Installation of joint tapping 10% |  |  |  | 21 | 9 | 189 | 21 |  | 21 | 100% | 189
37 | Bulkhead; type HTL-PT-08, 100 mm height | m | 51 |  |  | 90
| Delivery of materials 40% |  |  |  | 51 | 36 | 1836 | 51 |  | 51 | 100% | 1836
| Installation of framing 30% |  |  |  | 51 | 27 | 1377 | 51 |  | 51 | 100% | 1377
| Installation of gypsum board 20% |  |  |  | 51 | 18 | 918 | 51 |  | 51 | 100% | 918
| Installation of joint tapping 10% |  |  |  | 51 | 9 | 459 | 51 |  | 51 | 100% | 459
38 | Lit cornice; type HTL-WC-20, 100 mm height | m | 55 |  |  | 90
| Delivery of materials 40% |  |  |  | 55 | 36 | 1980 | 55 |  | 55 | 100% | 1980
| Installation of framing 30% |  |  |  | 55 | 27 | 1485 | 55 |  | 55 | 100% | 1485
| Installation of gypsum board 20% |  |  |  | 55 | 18 | 990 | 55 |  | 55 | 100% | 990
| Installation of joint tapping 10% |  |  |  | 55 | 9 | 495 | 55 |  | 55 | 100% | 495
Pre-function space
39 | Prefunction area; type HTL-PT-08 | m2 | 117.9 |  |  | 90
| Delivery of materials 40% |  |  |  | 117.9 | 36 | 4244.4 | 117.9 |  | 117.9 | 100% | 4244.4
| Installation of framing 30% |  |  |  | 117.9 | 27 | 3183.3 |  | 117.9 | 117.9 | 100% | 3183.3
| Installation of gypsum board 20% |  |  |  | 117.9 | 18 | 2122.2 |  | 117.9 | 117.9 | 100% | 2122.2
| Installation of joint tapping 10% |  |  |  | 117.9 | 9 | 1061.1 |  |  | 0 | 0% | 0
40 | Bulkhead; type HTL-PT-08, 1000 mm height | m | 57 |  |  | 90
| Delivery of materials 40% |  |  |  | 57 | 36 | 2052 | 57 |  | 57 | 100% | 2052
| Installation of framing 30% |  |  |  | 57 | 27 | 1539 |  | 57 | 57 | 100% | 1539
| Installation of gypsum board 20% |  |  |  | 57 | 18 | 1026 |  |  | 0 | 0% | 0
| Installation of joint tapping 10% |  |  |  | 57 | 9 | 513 |  |  | 0 | 0% | 0
Breakout space
41 | Gypsum Board ceiling; type HTL-PT-08 | m2 | 78.3 |  |  | 90
| Delivery of materials 40% |  |  |  | 78.3 | 36 | 2818.8 | 78.3 |  | 78.3 | 100% | 2818.8
| Installation of framing 30% |  |  |  | 78.3 | 27 | 2114.1 | 78.3 |  | 78.3 | 100% | 2114.1
| Installation of gypsum board 20% |  |  |  | 78.3 | 18 | 1409.4 | 78.3 |  | 78.3 | 100% | 1409.4
| Installation of joint tapping 10% |  |  |  | 78.3 | 9 | 704.7 | 78.3 |  | 78.3 | 100% | 704.7
42 | Bulkhead; type HTL-PT-08, including 150 mm high bulkhead and 150 x 90 x 90 mm cove light | m | 60 |  |  | 175
| Delivery of materials 40% |  |  |  | 60 | 70 | 4200 | 60 |  | 60 | 100% | 4200
| Installation of framing 30% |  |  |  | 60 | 52.5 | 3150 | 60 |  | 60 | 100% | 3150
| Installation of gypsum board 20% |  |  |  | 60 | 35 | 2100 | 60 |  | 60 | 100% | 2100
| Installation of joint tapping 10% |  |  |  | 60 | 17.5 | 1050 | 60 |  | 60 | 100% | 1050
Meeting rooms & Breakout Space
43 | Vertical Bulkhead / Wall lining - 4 mtr height | sqm | 68 |  |  | 150
| Delivery of materials 40% |  |  |  | 68 | 60 | 4080 | 68 |  | 68 | 100% | 4080
| Installation of framing 30% |  |  |  | 68 | 45 | 3060 | 68 |  | 68 | 100% | 3060
| Installation of gypsum board 20% |  |  |  | 68 | 30 | 2040 | 68 |  | 68 | 100% | 2040
| Installation of joint tapping 10% |  |  |  | 68 | 15 | 1020 | 68 |  | 68 | 100% | 1020
Ballroom male toilet
44 | Gypsum Board Ceiling; type HTL-PT-03 | m2 | 46 |  |  | 110
| Delivery of materials 40% |  |  |  | 46 | 44 | 2024 | 46 | 0 | 46 | 100% | 2024
| Installation of framing 30% |  |  |  | 46 | 33 | 1518 | 46 | 0 | 46 | 100% | 1518
| Installation of gypsum board 20% |  |  |  | 46 | 22 | 1012 |  | 0 | 0 | 0% | 0
| Installation of joint tapping 10% |  |  |  | 46 | 11 | 506 |  |  | 0 | 0% | 0
45 | Cavetto cornice; type HTL-PT-03 | m | 30 |  |  | 150
| Delivery of materials 50% |  |  |  | 30 | 75 | 2250 | 30 |  | 30 | 100% | 2250
| Installation of Cavetto cornice 40% |  |  |  | 30 | 60 | 1800 | 30 |  | 30 | 100% | 1800
| Installation of joint tapping 10% |  |  |  | 30 | 15 | 450 |  | 0 | 0 | 0% | 0
Ballroom female toilet
46 | Gypsum Board Ceiling; type HTL-PT-03 | m2 | 39 |  |  | 110
| Delivery of materials 40% |  |  |  | 39 | 44 | 1716 | 39 |  | 39 | 100% | 1716
| Installation of framing 30% |  |  |  | 39 | 33 | 1287 | 39 |  | 39 | 100% | 1287
| Installation of gypsum board 20% |  |  |  | 39 | 22 | 858 |  | 39 | 39 | 100% | 858
| Installation of joint tapping 10% |  |  |  | 39 | 11 | 429 |  | 39 | 39 | 100% | 429
47 | Gypsum Board Ceiling; with covering; type HTL-WC-17 | m2 | 2 |  |  | 150
| Delivery of materials 40% |  |  |  | 2 | 60 | 120 | 2 |  | 2 | 100% | 120
| Installation of framing 30% |  |  |  | 2 | 45 | 90 | 2 |  | 2 | 100% | 90
| Installation of gypsum board 20% |  |  |  | 2 | 30 | 60 | 2 |  | 2 | 100% | 60
| Installation of joint tapping 10% |  |  |  | 2 | 15 | 30 | 2 |  | 2 | 100% | 30
48 | Cavetto cornice type HTL-PT-03 | m | 29 |  |  | 150
| Delivery of materials 50% |  |  |  | 29 | 75 | 2175 | 29 | 0 | 29 | 100% | 2175
| Installation of Cavetto cornice 40% |  |  |  | 29 | 60 | 1740 | 29 |  | 29 | 100% | 1740
| Installation of joint tapping 10% |  |  |  | 29 | 15 | 435 | 29 |  | 29 | 100% | 435
Storage
49 | Gypsum Board ceiling; type HTL-PT-08 | m2 | 4 |  |  | 110
| Delivery of materials 40% |  |  |  | 4 | 44 | 176 | 4 |  | 4 | 100% | 176
| Installation of framing 30% |  |  |  | 4 | 33 | 132 | 4 |  | 4 | 100% | 132
| Installation of gypsum board 20% |  |  |  | 4 | 22 | 88 |  | 4 | 4 | 100% | 88
| Installation of joint tapping 10% |  |  |  | 4 | 11 | 44 |  | 4 | 4 | 100% | 44
BOH
50 | Gypsum Board ceiling; type HTL-PT-08 | m2 | 73.8 |  |  | 110
| Delivery of materials 40% |  |  |  | 73.8 | 44 | 3247.2 | 73.8 |  | 73.8 | 100% | 3247.2
| Installation of framing 30% |  |  |  | 73.8 | 33 | 2435.4 | 73.8 |  | 73.8 | 100% | 2435.4
| Installation of gypsum board 20% |  |  |  | 73.8 | 22 | 1623.6 |  | 36.9 | 36.9 | 50% | 811.8
| Installation of joint tapping 10% |  |  |  | 73.8 | 11 | 811.8 |  | 36.9 | 36.9 | 50% | 405.9
Ballroom
Ceiling Finishes
51 | Bulkhead; type HTL-WC-20, 100 mm height | m | 150 |  |  | 90
| Delivery of materials 40% |  |  |  | 150 | 36 | 5400 |  | 150 | 150 | 100% | 5400
| Installation of framing 30% |  |  |  | 150 | 27 | 4050 |  | 150 | 150 | 100% | 4050
| Installation of gypsum board 20% |  |  |  | 150 | 18 | 2700 |  | 150 | 150 | 100% | 2700
| Installation of joint tapping 10% |  |  |  | 150 | 9 | 1350 |  |  | 0 | 0% | 0
Meeting room 1
53 | Bulkhead; 300 mm height | m | 38 |  |  | 90
| Delivery of materials 40% |  |  |  | 38 | 36 | 1368 | 38 |  | 38 | 100% | 1368
| Installation of framing 30% |  |  |  | 38 | 27 | 1026 | 38 |  | 38 | 100% | 1026
| Installation of gypsum board 20% |  |  |  | 38 | 18 | 684 |  | 38 | 38 | 100% | 684
| Installation of joint tapping 10% |  |  |  | 38 | 9 | 342 |  | 38 | 38 | 100% | 342
Meeting room 2
54 | Bulkhead; 300 mm height | m | 36 |  |  | 90
| Delivery of materials 40% |  |  |  | 36 | 36 | 1296 |  | 36 | 36 | 100% | 1296
| Installation of framing 30% |  |  |  | 36 | 27 | 972 |  | 36 | 36 | 100% | 972
| Installation of gypsum board 20% |  |  |  | 36 | 18 | 648 |  | 36 | 36 | 100% | 648
| Installation of joint tapping 10% |  |  |  | 36 | 9 | 324 |  | 36 | 36 | 100% | 324
Near Corridor and Toilet
55 | Gypsum Board ceiling; type HTL-WC-19 | m2 | 35 |  |  | 90
| Delivery of materials 40% |  |  |  | 35 | 36 | 1260 |  | 35 | 35 | 100% | 1260
| Installation of framing 30% |  |  |  | 35 | 27 | 945 |  | 35 | 35 | 100% | 945
| Installation of gypsum board 20% |  |  |  | 35 | 18 | 630 |  | 35 | 35 | 100% | 630
| Installation of joint tapping 10% |  |  |  | 35 | 9 | 315 |  |  | 0 | 0% | 0
Hall
56 | Bulkhead; 300 mm height | m | 27 |  |  | 90
| Delivery of materials 40% |  |  |  | 27 | 36 | 972 |  | 27 | 27 | 100% | 972
| Installation of framing 30% |  |  |  | 27 | 27 | 729 |  | 27 | 27 | 100% | 729
| Installation of gypsum board 20% |  |  |  | 27 | 18 | 486 |  | 27 | 27 | 100% | 486
| Installation of joint tapping 10% |  |  |  | 27 | 9 | 243 |  | 27 | 27 | 100% | 243
BOH
57 | Access Panels and Temporary openings
58 | Access Panels - 600 x 600 mm | Nos | 70 |  |  | 185
| Delivery of materials 40% |  |  |  | 70 | 74 | 5180 |  |  | 0 | 0% | 0
| Installation of acces panel and fininhing 60% |  |  |  | 70 | 111 | 7770 |  |  | 0 | 0% | 0
59 | Temporary Openings and closing - 600 x 600 mm | Nos | 350 |  |  | 75
| openins 40% |  |  |  | 350 | 30 | 10500 | 5 | 5 | 10 | 2.857% | 300
| closing of temporary opening and fininhing 60% |  |  |  | 350 | 45 | 15750 | 5 | 5 | 10 | 2.857% | 450
60 | Variation 01- secindary support for curved ceiling. |  |  |  |  | 45030.5
| Delivery of materials | Ls | 1 |  | 1 | 34915.9 | 34915.9 | 1 |  | 1 | 100% | 34915.9
| Installation of secondary support |  |  |  | 1 | 10114.6 | 10114.6 | 1 | 0 | 1 | 100% | 10114.6
| TOTAL FOR PARTITION | [5 empty] | 553317.7 |  | 4861.788 |  |  | 541610.2 | 11707.5
| TOTAL FOR CEILING | [5 empty] | 364865.91 |  |  |  |  | 293682.668 | 71183.242
| TOTAL FOR VARIATION | [5 empty] | 45030.5 |  |  |  |  | 45030.5
| TOTAL FOR CEILING and PARTITION | [5 empty] | 918183.61 |  |  |  |  | 835292.868
880323.368
82890.742