## Summary
#REF!
G E N E R A L S U M M A R Y
APL PROGRESS CLAIM
ITEM NO | DESCRIPTION | CONTRACT AMOUNT (DHS) | CURRENT (DHS) | PREVIOUS (DHS) | THIS APPLICATION (DHS)
The Design and Construction of GRC Cladding
GRP Cladding System at Plot 18, Business Bay, Dubai, Project
1 | Glass Reinforced Concrete (GRC) Edge Profile | 460467 | 63204 | 62200 | 1004 | 13.73%
2 | Balcony Separator | 145549 | 29767 | 29767 | 0 | 20.45%
3 | Additional Items (Structural Steel Support) | 154264 | 21174 | 20838 | 336 | 13.73%
4 | Scaffold | 28083 | 3855 | 3793 | 62 | 13.73%
5 | Preliminaries | 207278 | 31025 | 30656 | 369 | 14.97%
6 | Additional Works (A) | 1440824 | 694099 | 420190 | 273909 | 48.17%
7 | Additional Works (B) | 234190 | 14347 | 14347 | 0 | 6.126%
8 | Additional Preliminaries | 1485000 | 1155000 | 1155000 | 0 | 77.78%
| SUB-TOTAL | 4155655 | 2012471 | 1736791 | 275680 | 48.43%
6 | Variations |  | 253613.61 | 160731.7 | 92881.91
7 | Materials On Site |  | 0 | 0 | 0
| GRAND TOTAL | 4155655 | 2266084.61 | 1897522.7 | 368561.91 | 54.53%

## BOQ (KCE)
PROJECT: |  | DORCHESTER COLLECTION & HOTEL RESIDENCES, PLOT BB.B03.018, BUSINESS BAY DUBAI
SUB-CONTRACTOR: |  | ARABIAN PROFILE COMPANY LIMITED | [11 empty] | #REF! | #REF!
DOCUMENT TITLE: |  | SUB-CONTRACT PRICE SUM | [12 empty] | #REF!
PACKAGE: |  | The Completion of All GRC Remaining Works
PROGRESS
BOQ REF. | ITEM | DESCRIPTION | QUANT | UNIT | UNIT RATE | TOTAL | Certified Progress | Certified MOS | Certified Materials Offsite | QUANT | UNIT | UNIT RATE | TOTAL | % | Amount
1 |  | GRC CLADDING SYSTEM |  |  |  | 12180830 | 11203481 | 281000 | 235882 |  |  |  | 995641 |  | 149025
Glass reinforced concrete (GRC) edge profile complete with all necessary fixing accessories, supporting frame work, hoisting into position, fixing, sealant between panels and the like all in accordance with specification and drawings
2nd and 3rd Levels
| A | 800 mm wide GRC Edge profile Type EWS-101 | 584 | lm | 2380 | 1389920 | 1262325 | 33000 | 33139 | 1 | LS | 61456 | 61456 | 37.2% | 22859
| B | Ditto, Curved
Apartment 4th and Hotel 4th Levels
| C | 800 mm wide GRC Edge profile Type EWS-101 | 530 | lm | 2380 | 1261400 | 1072282 | 69000 |  | 1 | LS | 120118 | 120118 | 0% | 0
| D | Ditto, Curved
Apartment 6th and Hotel 7th Levels
| E | 600 mm wide GRC Edge profile Type EWS-101 | 387 | lm | 2670 | 1033290 | 835910 | 69000 | 11175 | 1 | LS | 117205 | 117205 | 0% | 0
| F | Ditto, Curved
Apartment 7th to 31st Levels
| G | 600 mm wide GRC Edge profile Type EWS-101 | 3691 | lm | 955 | 3524905 | 3276505 | 71000 | 85848 | 1 | LS | 91552 | 91552 | 25.6% | 23433
| H | Ditto, Curved
| J | 900 mm wide GRC Edge profile Type EWS-101 | 578 | lm | 1355 | 783190 | 743354 | 10000 | 15690 | 1 | LS | 14146 | 14146 | 0% | 0
| K | Ditto, Curved
Hotel Level 8th to 29th
| L | 600 mm wide GRC Edge profile Type EWS-101 | 3808 | lm | 955 | 3636640 | 3461620 | 29000 | 90030 | 1 | LS | 55990 | 55990 | 30.2% | 16912
| M | Ditto, Curved
| N | 900 mm wide GRC Edge profile Type EWS-101 | 407 | lm | 1355 | 551485 | 551485
| P | Ditto, Curved
|  | Balcony Separator |  |  |  | 1371559 | 1205929 | 20000 | 81
|  | Apartment Level 6 to 31 |  |  |  | 0
| C | Balcony Separator Type EWS-105 | 63 | Nr | 5483 | 345429 | 276343 |  | 81 | 1 | LS | 69005 | 69005 | 0% | 0
|  | Hotel Level 7th to 29th | 214 | Nr | 4795 | 1026130 | 929586 | 20000 |  | 1 | LS | 76544 | 76544 | 38.89% | 29767
| D | Balcony Separator Type EWS-105
| E | Reintroduction of the Hotel Balcony area refer to façade commented drawings |  | Item | [5 empty] | 1 | Item
|  | Structural Steel Support |  |  |  | 1922611 | 1768347 | 0 | 0
| A | Structural steel support for fixing GRC Works (Epoxy paint finish without fire protection) | 1 | Item | 1922611 | 1922611 | 1768347 |  |  | 1 | Item | 154264 | 154264 | 13.73% | 21174
|  | Scaffold |  |  |  | 350000 | 321917 | 0 | 0
| E | Equipment and aluminium scaffold towers | 1 | Item | 350000 | 350000 | 321917 |  |  | 1 | Item | 28083 | 28083 | 13.73% | 3855
|  | Preliminaries |  |  |  | 2475000 | 2267722 |  |  | 1 | Item | 207278 | 207278 | 14.97% | 31025
| E | Engineering Works | 1 | Item | 650000 | 650000
| F | QA / QC & Safety | 1 | Item | 150000 | 150000
| G | Site Management | 1 | Item | 1435000 | 1435000
| H | Finance Cost | 1 | Item | 240000 | 240000
2 |  | ADDITIONAL WORKS (A) |  |  |  | 3123094 | 1511611 | 0 | 170659 |  |  |  | 1440824 |  | 694099
| S.I. 079 | Engineering, Procurement & Installation Works for the Additional Steel Support Bracket for GRC Edge Panel | 1 | LS | 185000 | 185000 | 185000 |  |  | 1 | LS |  | 0
| S.I. 110 | Redesign of Brackets | 1 | LS | 60000 | 60000 | 60000 |  |  | 1 | LS |  | 0
| S.I. 130 | Engineering, Procurement & Installation Works for the Additional GRC Panel | 1 | LS | 280988 | 280988 | 157420 |  | 13447 | 1 | LS | 110121 | 110121 | 100% | 110121
| S.I. 224 | Rectification Works by Designing brackets consistent with the as-built conditions and structural requirements and re-installing | 1 | LS | 15000 | 15000 | 15000 |  |  | 1 | LS | 0 | 0 |  | 0
| S.I. 257 | Site Instruction - BSBG - Fluted GRC Cladding at Hotel Podium Entrance | 1 | LS | 441540 | 441540 | 88308 |  | 14658 | 1 | LS | 338574 | 338574 | 20% | 67715
| S.I. 266 | To proceed with the GRC Omission at Residential levels 26 and 28 | 1 | LS | -65791 | -65791 |  |  |  | 1 | LS | -65791 | -65791 | 0% | 0
| S.I. 285 | To proceed with the works associated with GRC cladding around stair plaza | 1 | LS | 605018 | 605018 | 393262 |  |  | 1 | LS | 211756 | 211756 | 20% | 42351
| S.I. 289 | GRC on Top of Parapet for Hotel Level 29 | 1 | LS | 52541 | 52541 | 2627 |  |  | 1 | LS | 49914 | 49914 | 100% | 49914
| S.I. 292 | To proceed with the Removal and Re-installation of Damaged GRC panels in the Residential Tower Road Elevation for Levels 15, 21, & 23 | 1 | LS | 20000 | 20000 | 20000 |  |  | 1 | LS | 0 | 0 |  | 0
| S.I. 296 | To proceed with the Works associated with residential tower non typical GRC profile as per attached RFI confirmation from the Employer (Belly/Underpool Panels at Residential L-24, 25, 26, 27, & 29) | 1 | LS | 419800 | 419800 | 419800 |  |  | 1 | LS | 0 | 0 |  | 0
| S.I. 299 | Residential Podium GRC Entrance Door Frame | 1 | LS | 17837 | 17837 |  |  |  | 1 | LS | 17837 | 17837 | 0% | 0
| S.I. 337 | Supply & Installation GRC Wall Cladding at Hotel Levels 8,11,14,16,21,23,25&27 | 1 | LS | 60313 | 60313 | 60313 |  |  | 1 | LS | 0 | 0 |  | 0
| S.I. 361 | Extension of GRC works at Hotel Tower Level 18 | 1 | LS | 10441 | 10441 | 10441 |  |  | 1 | LS | 0 | 0 |  | 0
| S.I. 364 | Supply & Installation of Fluted GRC Wall Cladding at Hotel Rooftop Pool Area - Level 29 | 1 | LS | 489665 | 489665 | 24483 |  | 1373 | 1 | LS | 463809 | 463809 | 41.42% | 192107
| S.I. 365 | Level 29 Pool View & Sky Deck Regions - GRP/GRC Cladding Work | 1 | LS | 86747 | 86747 | 69398 |  |  | 1 | LS | 17349 | 17349 | 0% | 0
| S.I. 347 | Supply & Installation GRC Wall Cladding at Hotel Levels 8 Duplex Slab Extension | 1 | LS | 5559 | 5559 | 5559 |  |  | 1 | LS | 0 | 0 |  | 0
| ERI/056 | GRC Nosing & GRC Edge Wall Cladding at Level 31 Residential Canopy | 1 | LS | 438436 | 438436 |  |  | 141181 | 1 | LS | 297255 | 297255 | 78.01% | 231891
3 |  | ADDITIONAL WORKS (B) |  |  |  | 248537 | 14347 | 0 | 0 |  |  |  | 234190 |  | 14347
| S.I. 367 | GRC Cladding at Level 10 Residential Canopy | 1 | LS | 179190 | 179190 |  |  |  | 1 | LS | 179190 | 179190 | 0% | 0
| S.I. 397 | Supply & Installation of GRC Wall Cladding to Podium Level Openings | 1 | LS | 22572 | 22572 |  |  |  | 1 | LS | 22572 | 22572 | 0% | 0
| S.I. 400 | Thermal Insulation Behind the Fluted GRC Cladding | 1 | LS | 28694 | 28694 | 14347 |  |  | 1 | LS | 14347 | 14347 | 100% | 14347
| S.I. 497 | GRC Flat Panel and Structural Steel Support System for the GRC Edge Profile Behind the Core Wall at Level 30 | 1 | LS | 18081 | 18081 |  |  |  | 1 | LS | 18081 | 18081 | 0% | 0
4 |  | ADDITIONAL PRELIMS |  |  |  | 1485000 | 0 | 0 | 0 |  |  |  | 1485000 |  | 1155000
|  | (For New Subcontract Period) | 9 | mo | 165000 | 1485000 |  |  |  | 1 | LS | 1485000 | 1485000 | 77.78% | 1155000
|  | To Collection |  |  |  | 23156631 | 18293354 | 301000 | 406622 |  |  |  | 4155655 |  | 2012471
|  | TOTAL CARRIED TO BILL SUMMARY |  |  |  | 23156631 | 18293354 | 301000 | 406622 |  |  |  | 4155655 |  | 2012471
Note on O60: Himal Kosala: Please provide markup drawings, WIRs, and measurement sheets
Note on O62: Himal Kosala: Please provide markup drawings, WIRs, and measurement sheets
Note on O81: Himal Kosala: No certified any due to more work balance at the site

## Res & Hotel - 800mm(Qty)
Quantity Take Off- Service Apartment ( Tower ) & Hotel ( Tower )
S. No. | Wall Type | Width | Floor Level | Qty Per Floor |  |  |  |  | GRC PANEL PRODUCED |  | GRC PANEL DELIVERED ONSITE |  |  |  | GRC PANEL INSTALLATION |  |  |  | Remarks
[6 empty] | CODE | L | Qty | Mat'l Produced | Length | DO No. | MIR No. | Mat'l On Site | Length | Work Done (Previous) | Work Done (This) | Work Done (Cumm.) | Length (This)
1 | EWS-101 | 800 | 2 | 1 |  | R2-N/01 | 2.84 | 1 | 1 | 2.84 | 2269 | 223 | 1 | 2.84 | 100% |  | 100% | 2.84
[6 empty] | R2-N/02 | 2.84 | 1 | 1 | 2.84 | 2274 |  | 1 | 2.84 | 100% |  | 100% | 2.84
[6 empty] | R2-N/03 | 3.08 | 1 | 1 | 3.08 | 2282 | 228 | 1 | 3.08 | 100% |  | 100% | 3.08
[6 empty] | R2-N/04 | 3.31 | 1 | 1 | 3.31 | 2293 | 228 | 1 | 3.31 | 100% |  | 100% | 3.31
[6 empty] | R2-N/05 | 3.75 | 1 | 1 | 3.75 | 2282,2288 | 228 | 1 | 3.75 | 100% |  | 100% | 3.75
[6 empty] | R2-N/06 | 3.4 | 1 | 1 | 3.4 | 2288 | 228 | 1 | 3.4 | 100% |  | 100% | 3.4
[6 empty] | R2-N/07 | 4.49 | 1 | 1 | 4.49 | 2288 | 228 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | R2-N/08 | 4.49 | 1 | 1 | 4.49 | 2211,2214 | 216 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | R2-N/09 | 4.49 | 1 | 1 | 4.49 | 2214,2216 |  | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | R2-N/10 | 4.49 | 1 | 1 | 4.49 | 2209,2214,2221 | 216,217 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | R2-N/11 | 4.49 | 1 | 1 | 4.49 | 2221,170954,2241 | 217,220 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | R2-N/12 | 4.49 | 1 | 1 | 4.49 | 2216,2217 | 217 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | R2-N/13 | 4.49 | 1 | 1 | 4.49 | 2214,2217 | 216,217 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | R2-N/14 | 4.49 | 1 | 1 | 4.49 | 2344 | 230 | 1 | 4.49 | 40% | 0% | 40% | 1.796 | WIR-L2-01254
[6 empty] | R2-N/15 | 4.49 | 1 | 1 | 4.49 | 2293 | 228 | 1 | 4.49 | 40% | 0% | 40% | 1.796 | WIR-L2-01254
[6 empty] | R2-N/16 | 4.49 | 1 | 1 | 4.49 | 2296,2344 | 228 | 1 | 4.49 | 40% | 0% | 40% | 1.796 | WIR-L2-01254
[6 empty] | R2-N/17 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | Cradle Area (Core Wall Access)
[6 empty] | R2-N/18 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | Cradle Area (Core Wall Access)
[6 empty] | R2-N/19 | 4.49 | 1 | 1 | 4.49 |  |  | 0.5 | 2.245 |  |  |  | 0 | Cradle Area (Core Wall Access)
[6 empty] | R2-N/20 | 4.49 | 1 | 1 | 4.49 | 2204,2207 | 214,215 | 1 | 4.49 |  |  |  | 0 | Cradle Area (Core Wall Access)
[6 empty] | R2-N/21 | 4.49 | 1 | 1 | 4.49 | 2204,2209 | 214,216 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | R2-N/22 | 1.7 | 1 | 1 | 1.7 | 2207,2214 | 215,216 | 1 | 1.7 | 100% |  | 100% | 1.7
[6 empty] | R2-N/23 | 3.75 | 1 | 1 | 3.75 | 2224 | 217 | 1 | 3.75 | 100% |  | 100% | 3.75
[6 empty] | R2-N/24 | 3.45 | 1 | 1 | 3.45 | 2209,2221 | 216,217 | 1 | 3.45 | 100% |  | 100% | 3.45
[6 empty] | R2-N/25 | 4.15 | 1 | 1 | 4.15 | 170954,2241 | 220 | 1 | 4.15 | 100% |  | 100% | 4.15
[6 empty] | R2-N/26 | 3.75 | 1 | 1 | 3.75 | 170954,2241 | 220 | 1 | 3.75 | 100% |  | 100% | 3.75
[6 empty] | R2-N/27 | 3.75 | 1 | 1 | 3.75 | 2209,2217 | 216,217 | 1 | 3.75 | 100% |  | 100% | 3.75
[6 empty] | R2-N/28 | 3.75 | 1 | 1 | 3.75 | 2209,2217 | 216,217 | 1 | 3.75 | 100% |  | 100% | 3.75
[6 empty] | R2-N/29 | 3.13 | 1 | 1 | 3.13 | 2224 | 217 | 1 | 3.13 | 100% |  | 100% | 3.13
[6 empty] | R2-N/30 | 3.2 | 1 | 1 | 3.2 | 2211,170954,2241,2689 | 216,220,275 | 1 | 3.2 | 100% |  | 100% | 3.2
[6 empty] | R2-N/31 | 3.2 | 1 | 1 | 3.2 | 2211,2214,2689 | 216,275 | 1 | 3.2 | 100% |  | 100% | 3.2
[6 empty] | R2-N/32 | 2.89 | 1 | 1 | 2.89 | 2228,170954,2241,2689 | 218,220,275 | 1 | 2.89 | 100% |  | 100% | 2.89
[6 empty] | R2-N/33 | 4.49 | 1 | 1 | 4.49 | 2179,2183,2689 | 209,210,275 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | R2-N/34 | 4.49 | 1 | 1 | 4.49 | 2177,2180,2689 | 209,275 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | R2-N/35 | 4.49 | 1 | 1 | 4.49 | 2177,2180,2689 | 209,275 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | R2-N/36 | 3.32 | 1 | 1 | 3.32 | 2188,2194,2689 | 211'213,275 | 1 | 3.32 | 100% |  | 100% | 3.32
[6 empty] | R2-N/37 | 3.32 | 1 | 1 | 3.32 | 2185,2193,2689 | 211,213,275 | 1 | 3.32 | 100% |  | 100% | 3.32
[6 empty] | R2-N/38 | 4.08 | 1 | 1 | 4.08 | 2203,2666 | 214,275 | 1 | 4.08 | 100% |  | 100% | 4.08
[6 empty] | R2-N/39 | 4.08 | 1 | 1 | 4.08 | 2203,2666 | 214,275 | 1 | 4.08 | 100% |  | 100% | 4.08
[6 empty] | R2-N/40 | 4.08 | 1 | 1 | 4.08 | 2203,2666 | 21,275 | 1 | 4.08 | 100% |  | 100% | 4.08
[6 empty] | R2-N/41 | 4.08 | 1 | 1 | 4.08 | 2202,2203,2666 | 214,275 | 1 | 4.08 | 100% |  | 100% | 4.08
[6 empty] | R2-N/42 | 4.08 | 1 | 1 | 4.08 | 2194,2202,2666 | 213,214,275 | 1 | 4.08 | 100% |  | 100% | 4.08
[6 empty] | R2-N/43 | 4.08 | 1 | 1 | 4.08 | 2192,2194,2666 | 213,275 | 1 | 4.08 | 100% |  | 100% | 4.08
[6 empty] | R2-N/44 | 4.08 | 1 | 1 | 4.08 | 2189,2192,2666 | 211,213,275 | 1 | 4.08 | 100% |  | 100% | 4.08
[6 empty] | R2-N/45 | 4.08 | 1 | 1 | 4.08 | 2204,2207,2666 | 214,215,275 | 1 | 4.08 | 100% |  | 100% | 4.08
[6 empty] | R2-N/46 | 3.68 | 1 | 1 | 3.68 | 2189,2666 | 211,275 | 1 | 3.68 | 100% |  | 100% | 3.68
[6 empty] | R2-N/47 | 3.51 | 1 | 1 | 3.51 | 2194,2202 | 213,214 | 1 | 3.51 | 100% |  | 100% | 3.51
[6 empty] | R2-N/48 | 3.51 | 1 | 1 | 3.51 | 2192,2202,2326 | 213,214 | 1 | 3.51 | 100% |  | 100% | 3.51
[6 empty] | R2-N/49 | 3.26 | 1 | 1 | 3.26 | 2204,2257 | 214,222 | 1 | 3.26 | 100% |  | 100% | 3.26
[6 empty] | R2-N/50 | 4.31 | 1 | 1 | 4.31 | 2207,2217 | 215,217 | 1 | 4.31 | 100% |  | 100% | 4.31
[6 empty] | R2-N/51 | 4.31 | 1 | 1 | 4.31 | 2208,2211 | 215,216 | 1 | 4.31 | 100% |  | 100% | 4.31
[6 empty] | R2-N/52 | 4.31 | 1 | 1 | 4.31 | 2208,2209 | 215 | 1 | 4.31 | 100% |  | 100% | 4.31
[6 empty] | R2-N/53 | 4.31 | 1 | 1 | 4.31 | 2211,2214 | 216 | 1 | 4.31 | 100% |  | 100% | 4.31
[6 empty] | R2-N/54 | 4.31 | 1 | 1 | 4.31 | 2211,2214 | 216 | 1 | 4.31 | 100% |  | 100% | 4.31
[6 empty] | R2-N/55 | 4.31 | 1 | 1 | 4.31 | 2214,2221 | 216,217 | 1 | 4.31 | 100% |  | 100% | 4.31
[6 empty] | R2-N/56 | 4.31 | 1 | 1 | 4.31 | 2214,2221 | 216,217 | 1 | 4.31 | 100% |  | 100% | 4.31
[6 empty] | R2-N/57 | 4.31 | 1 | 1 | 4.31 | 2209,2216 | 216 | 1 | 4.31 | 100% |  | 100% | 4.31
[6 empty] | R2-N/58 | 4.31 | 1 | 1 | 4.31 | 2209,2216 | 216 | 1 | 4.31 | 100% |  | 100% | 4.31
[6 empty] | R2-N/59 | 4.31 | 1 | 1 | 4.31 | 2216,2266 | 222 | 1 | 4.31 | 100% |  | 100% | 4.31
[6 empty] | R2-N/60 | 4.31 | 1 | 1 | 4.31 | 2216,170954,2241 | 220 | 1 | 4.31 | 100% |  | 100% | 4.31
[6 empty] | R2-N/61 | 4.31 | 1 | 1 | 4.31 | 2217,2221 | 217 | 1 | 4.31 | 100% |  | 100% | 4.31
[6 empty] | R2-N/62 | 4.31 | 1 | 1 | 4.31 | 2217 | 217 | 1 | 4.31 | 100% |  | 100% | 4.31
[6 empty] | R2-N/63 | 4.08 | 1 | 1 | 4.08 | 2185,2193,2384 | 211,213 | 1 | 4.08 | 100% |  | 100% | 4.08
[6 empty] | R2-N/64 | 4.49 | 1 | 1 | 4.49 | 2180 | 209 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | R2-N/65 | 4.49 | 1 | 1 | 4.49 | 2188,2193 | 211,213 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | R2-N/66 | 4.49 | 1 | 1 | 4.49 | 2296 | 228 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | R2-N/67 | 2.19 | 1 | 0 | 0 |  |  |  | 0 |  |  |  | 0
[6 empty] | R2-N/68 | 1.61 | 1 | 0 | 0 |  |  |  | 0 |  |  |  | 0
[6 empty] | R2-N/69 | 3.03 | 1 | 0 | 0 |  |  |  | 0 |  |  |  | 0
[6 empty] | R2-N/70 | 4.45 | 1 | 1 | 4.45 | 2185,2188 | 211 | 1 | 4.45 | 100% |  | 100% | 4.45
[6 empty] | R2-N/71 | 4.45 | 1 | 1 | 4.45 | 2185,2188 | 211 | 1 | 4.45 | 100% |  | 100% | 4.45
[6 empty] | R2-N/72 | 2.78 | 1 | 1 | 2.78 | 2189,2192 | 211,213 | 1 | 2.78 | 100% |  | 100% | 2.78
[9 empty] | TOTAL | 275.26 |  |  | TOTAL | 264.035 | TOTAL |  | TOTAL | 249.218
2 | EWS-101 | 800 | 2 | 1 |  | H2-N/01 | 2.05 | 1 | 1 | 2.05 | 2228 | 218 | 1 | 2.05 | 100% |  | 100% | 2.05
[6 empty] | H2-N/02 | 2.05 | 1 | 1 | 2.05 | 2232 | 218 | 1 | 2.05 | 100% |  | 100% | 2.05
[6 empty] | H2-N/03 | 3.95 | 1 | 1 | 3.95 | 2189,2192 | 211,213 | 1 | 3.95 | 100% |  | 100% | 3.95
[6 empty] | H2-N/04 | 3.95 | 1 | 1 | 3.95 | 2189,2192 | 211,213 | 1 | 3.95 | 100% |  | 100% | 3.95
[6 empty] | H2-N/05 | 3.95 | 1 | 1 | 3.95 | 2188,2189,2192 | 211,213 | 1 | 3.95 | 100% |  | 100% | 3.95
[6 empty] | H2-N/06 | 3.95 | 1 | 1 | 3.95 | 2188,2194 | 211'213 | 1 | 3.95 | 100% |  | 100% | 3.95
[6 empty] | H2-N/07 | 2.82 | 1 | 1 | 2.82 | 2228 | 218 | 1 | 2.82 | 100% |  | 100% | 2.82
[6 empty] | H2-N/08 | 4.22 | 1 | 1 | 4.22 | 2188,2192 | 211,213 | 1 | 4.22 | 100% |  | 100% | 4.22
[6 empty] | H2-N/09 | 4.22 | 1 | 1 | 4.22 | 2188,2189 | 211 | 1 | 4.22 | 100% |  | 100% | 4.22
[6 empty] | H2-N/10 | 4.22 | 1 | 1 | 4.22 | 2190 | 211 | 1 | 4.22 | 100% |  | 100% | 4.22
[6 empty] | H2-N/11 | 4.22 | 1 | 1 | 4.22 | 2200,2202 | 214 | 1 | 4.22 | 100% |  | 100% | 4.22
[6 empty] | H2-N/12 | 4.22 | 1 | 1 | 4.22 | 2192,2200 | 213,214 | 1 | 4.22 | 100% |  | 100% | 4.22
[6 empty] | H2-N/13 | 4.22 | 1 | 1 | 4.22 | 2200,2204 | 214 | 1 | 4.22 | 100% |  | 100% | 4.22
[6 empty] | H2-N/14 | 4.22 | 1 | 1 | 4.22 | 2200 | 214 | 1 | 4.22 | 100% |  | 100% | 4.22
[6 empty] | H2-N/15 | 4.22 | 1 | 1 | 4.22 | 2202,2203 | 214 | 1 | 4.22 | 100% |  | 100% | 4.22
[6 empty] | H2-N/16 | 4.22 | 1 | 1 | 4.22 | 2202,2203 | 214 | 1 | 4.22 | 100% |  | 100% | 4.22
[6 empty] | H2-N/17 | 4.22 | 1 | 1 | 4.22 | 2200,2202 | 214 | 1 | 4.22 | 100% |  | 100% | 4.22
[6 empty] | H2-N/18 | 4.22 | 1 | 1 | 4.22 | 2200,2202 | 214 | 1 | 4.22 | 100% |  | 100% | 4.22
[6 empty] | H2-N/19 | 4.22 | 1 | 1 | 4.22 | 2202,2208 | 214,215 | 1 | 4.22 | 100% |  | 100% | 4.22
[6 empty] | H2-N/20 | 4.22 | 1 | 1 | 4.22 | 2202,2208 | 214,215 | 1 | 4.22 | 100% |  | 100% | 4.22
[6 empty] | H2-N/21 | 4.22 | 1 | 1 | 4.22 | 2204,2208 | 214,215 | 1 | 4.22 | 100% |  | 100% | 4.22
[6 empty] | H2-N/22 | 4.22 | 1 | 1 | 4.22 | 2208,2233 | 215,218 | 1 | 4.22 | 100% |  | 100% | 4.22
[6 empty] | H2-N/23 | 4.22 | 1 | 1 | 4.22 | 2207 | 215 | 1 | 4.22 | 100% |  | 100% | 4.22
[6 empty] | H2-N/24 | 4.22 | 1 | 1 | 4.22 | 2204,2207 | 214,215 | 1 | 4.22 | 100% |  | 100% | 4.22
[6 empty] | H2-N/25 | 3.58 | 1 | 1 | 3.58 | 2232 | 218 | 1 | 3.58 | 100% |  | 100% | 3.58
[6 empty] | H2-N/26 | 4.28 | 1 | 1 | 4.28 | 2231,2233 | 218 | 1 | 4.28 | 100% |  | 100% | 4.28
[6 empty] | H2-N/27 | 4.28 | 1 | 1 | 4.28 | 2231,2257 | 218,222 | 1 | 4.28 | 100% |  | 100% | 4.28
[6 empty] | H2-N/28 | 4.28 | 1 | 1 | 4.28 | 2231,2257 | 218,222 | 1 | 4.28 | 100% |  | 100% | 4.28
[6 empty] | H2-N/29 | 4.28 | 1 | 1 | 4.28 | 2231,2257 | 218,222 | 1 | 4.28 | 100% |  | 100% | 4.28
[6 empty] | H2-N/30 | 4.28 | 1 | 1 | 4.28 | 2232,2266 | 218,222 | 1 | 4.28 | 100% |  | 100% | 4.28
[6 empty] | H2-N/31 | 4.28 | 1 | 1 | 4.28 | 2232,2266 | 218,222 | 1 | 4.28 | 100% |  | 100% | 4.28
[6 empty] | H2-N/32 | 4.28 | 1 | 1 | 4.28 | 2228,2266 | 218,222 | 1 | 4.28 | 100% |  | 100% | 4.28
[6 empty] | H2-N/33 | 3.14 | 1 | 1 | 3.14 | 2633 | 276,275 | 1 | 3.14 | 100% |  | 100% | 3.14 | WIR 1199
[6 empty] | H2-N/34 | 3.14 | 1 | 1 | 3.14 | 2633 | 276,275 | 1 | 3.14 | 100% |  | 100% | 3.14 | WIR 1199
[6 empty] | H2-N/35 | 3.65 | 1 | 1 | 3.65 | 2604,2633 | 276,275 | 1 | 3.65 | 100% | 0% | 100% | 3.65 | WIR-L2-01261
[6 empty] | H2-N/36 | 3.65 | 1 | 1 | 3.65 | 2604,2621 | 272 | 1 | 3.65 | 100% | 0% | 100% | 3.65 | WIR-L2-01261
[6 empty] | H2-N/37 | 3.65 | 1 | 1 | 3.65 | 2604,2621 | 272 | 1 | 3.65 | 100% | 0% | 100% | 3.65 | WIR-L2-01261
[6 empty] | H2-N/38 | 3.65 | 1 | 1 | 3.65 | 2604,2621 | 272 | 1 | 3.65 | 100% | 0% | 100% | 3.65 | WIR-L2-01261
[6 empty] | H2-N/39 | 2.21 | 1 | 1 | 2.21 | 3117 | 327 | 1 | 2.21 | 100% | 0% | 100% | 2.21 | WIR-L2-01275; 1279
[6 empty] | H2-N/40 | 4.61 | 1 | 1 | 4.61 | 2424,2431 |  | 1 | 4.61 |  |  |  | 0
[6 empty] | H2-N/41 | 4.49 | 1 | 1 | 4.49 | 2271,2424,2431 | 223 | 1 | 4.49 | 100% |  | 100% | 4.49 | WIR 1095 R2
[6 empty] | H2-N/42 | 4.49 | 1 | 1 | 4.49 | 2293,2423 | 228 | 1 | 4.49 | 100% |  | 100% | 4.49 | WIR 1095 R2
[6 empty] | H2-N/43 | 4.49 | 1 | 1 | 4.49 | 2293,2423 | 228 | 1 | 4.49 | 100% |  | 100% | 4.49 | WIR 1095 R2
[6 empty] | H2-N/44 | 4.49 | 1 | 1 | 4.49 | 2344,2424,2431 | 230 | 1 | 4.49 | 100% |  | 100% | 4.49 | WIR 1095 R2
[6 empty] | H2-N/45 | 4.49 | 1 | 1 | 4.49 | 2271,2423,2431 | 223 | 1 | 4.49 | 100% |  | 100% | 4.49 | WIR 1095 R2
[6 empty] | H2-N/46 | 4.49 | 1 | 1 | 4.49 | 2271,2434 | 223 | 1 | 4.49 | 100% |  | 100% | 4.49 | WIR 1095 R2
[6 empty] | H2-N/47 | 4.49 | 1 | 1 | 4.49 | 2253,2255 | 221 | 1 | 4.49 | 100% |  | 100% | 4.49 | WIR 1095 R2
[6 empty] | H2-N/48 | 4.491 | 1 | 1 | 4.491 | 2253,2255 | 221 | 1 | 4.491 | 100% |  | 100% | 4.491
[6 empty] | H2-N/49 | 4.491 | 1 | 1 | 4.491 | 2233,2255 | 218,221 | 1 | 4.491 | 100% |  | 100% | 4.491
[6 empty] | H2-N/50 | 4.491 | 1 | 1 | 4.491 | 2253,2255 | 221 | 1 | 4.491 | 100% |  | 100% | 4.491
[6 empty] | H2-N/51 | 4.491 | 1 | 1 | 4.491 | 2253,2255 | 221 | 1 | 4.491 | 100% |  | 100% | 4.491
[6 empty] | H2-N/52 | 4.491 | 1 | 1 | 4.491 | 2253 | 221 | 1 | 4.491 | 100% |  | 100% | 4.491
[6 empty] | H2-N/53 | 2.04 | 1 | 1 | 2.04 | 2266 | 222 | 1 | 2.04 | 100% |  | 100% | 2.04
[6 empty] | H2-N/54 | 2.04 | 1 | 1 | 2.04 | 2257 | 222 | 1 | 2.04 | 100% |  | 100% | 2.04
[6 empty] | H2-N/55 | 3.77 | 1 | 1 | 3.77 | 2228,2266 | 218,222 | 1 | 3.77 | 100% |  | 100% | 3.77
[6 empty] | H2-N/56 | 3.77 | 1 | 1 | 3.77 | 2231,2233 | 218 | 1 | 3.77 | 100% |  | 100% | 3.77
[6 empty] | H2-N/57 | 3.64 | 1 | 1 | 3.64 | 2255 | 221 | 1 | 3.64 | 100% |  | 100% | 3.64
[9 empty] | TOTAL | 224.845 |  |  | TOTAL | 224.845 | TOTAL |  | TOTAL | 220.235
3 | EWS-101 | 800 | 4 | 1 |  | R4-N/01 | 4.49 | 1 | 1 | 4.49 | 2231 | 218 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | R4-N/02 | 4.49 | 1 | 1 | 4.49 | 2231,2334 | 218 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | R4-N/03 | 4.49 | 1 | 1 | 4.49 | 2278,2326 | 224 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | R4-N/04 | 4.49 | 1 | 1 | 4.49 | 2232,2278,2334 | 218,224 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | R4-N/05 | 4.49 | 1 | 1 | 4.49 | 2334 |  | 1 | 4.49 | 100% |  | 100% | 4.49 | after Level 6 completion
[6 empty] | R4-N/06 | 4.49 | 1 | 1 | 4.49 | 2326,2334 |  | 1 | 4.49 |  |  |  | 0 | after Level 6 completion
[6 empty] | R4-N/07 | 4.49 | 1 | 1 | 4.49 | 2233,2269 | 218,223 | 1 | 4.49 |  |  |  | 0 | after Level 6 completion
[6 empty] | R4-N/08 | 4.49 | 1 | 1 | 4.49 | 2233,2269 | 218,223 | 1 | 4.49 |  |  |  | 0 | after Level 6 completion
[6 empty] | R4-N/09 | 4.49 | 1 | 1 | 4.49 | 2233,2267 | 218,223 | 1 | 4.49 |  |  |  | 0 | after Level 6 completion
[6 empty] | R4-N/10 | 4.49 | 1 | 1 | 4.49 | 2317 | 228 | 1 | 4.49 |  |  |  | 0 | Cradle Area (Core Wall Access)
[6 empty] | R4-N/11 | 4.49 | 1 | 1 | 4.49 | 2726 | 287 | 1 | 4.49 |  |  |  | 0 | Cradle Area (Core Wall Access)
[6 empty] | R4-N/12 | 4.49 | 1 | 1 | 4.49 | 2726 | 287 | 1 | 4.49 |  |  |  | 0 | Cradle Area (Core Wall Access)
[6 empty] | R4-N/13 | 4.49 | 1 | 1 | 4.49 | 2317,2726 | 228,287 | 1 | 4.49 |  |  |  | 0 | Cradle Area (Core Wall Access)
[6 empty] | R4-N/14 | 4.49 | 1 | 1 | 4.49 | 2317,2726 | 228,287 | 0.5 | 2.245 |  |  |  | 0 | Cradle Area (Core Wall Access)
[6 empty] | R4-N/15 | 4.49 | 1 | 1 | 4.49 | 2317 | 228 | 1 | 4.49 |  |  |  | 0 | Cradle Area (Core Wall Access)
[6 empty] | R4-N/16 | 4.49 | 1 | 1 | 4.49 | 2233,2267 | 218,223 | 1 | 4.49 |  |  |  | 0 | Cradle Area (Core Wall Access)
[6 empty] | R4-N/17 | 4.49 | 1 | 1 | 4.49 | 2267,2269,2321 | 223,228 | 1 | 4.49 |  |  |  | 0 | after Level 6 completion
[6 empty] | R4-N/18 | 1.87 | 1 | 1 | 1.87 | 2321 | 228 | 1 | 1.87 |  |  |  | 0
[6 empty] | R4-N/19 | 3.18 | 1 | 1 | 3.18 | 2267,2269 | 223 | 1 | 3.18 | 100% |  | 100% | 3.18
[6 empty] | R4-N/20 | 2.05 | 1 | 1 | 2.05 | 2321 | 228 | 1 | 2.05 | 100% |  | 100% | 2.05
[6 empty] | R4-N/21 | 2.06 | 1 | 1 | 2.06 | 2267 | 223 | 1 | 2.06 | 100% |  | 100% | 2.06
[6 empty] | R4-N/22 | 3.75 | 1 | 1 | 3.75 | 2267,2269,2321 | 223228 | 1 | 3.75 | 100% |  | 100% | 3.75
[6 empty] | R4-N/23 | 3.75 | 1 | 1 | 3.75 | 2267,2269,2321 | 223,228 | 1 | 3.75 | 100% |  | 100% | 3.75
[6 empty] | R4-N/24 | 2.91 | 1 | 1 | 2.91 | 2332 |  | 1 | 2.91 | 100% |  | 100% | 2.91
[6 empty] | R4-N/25 | 3.32 | 1 | 1 | 3.32 | 2100 | 199 | 1 | 3.32 | 100% |  | 100% | 3.32
[6 empty] | R4-N/26 | 3.32 | 1 | 1 | 3.32 | 2111 | 2020 | 1 | 3.32 | 100% |  | 100% | 3.32
[6 empty] | R4-N/27 | 2.89 | 1 | 1 | 2.89 | 2163 | 208 | 1 | 2.89 | 100% |  | 100% | 2.89
[6 empty] | R4-N/28 | 4.49 | 1 | 1 | 4.49 | 2086 | 2086 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | R4-N/29 | 4.49 | 1 | 1 | 4.49 | 2086 | 2086 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | R4-N/30 | 4.49 | 1 | 1 | 4.49 | 2086,2344 | 2086 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | R4-N/31 | 3.66 | 1 | 1 | 3.66 | 2179,2183,2326 | 209,210 | 1 | 3.66 | 100% |  | 100% | 3.66
[6 empty] | R4-N/32 | 3.66 | 1 | 1 | 3.66 | 2170 | 208 | 1 | 3.66 | 100% |  | 100% | 3.66
[6 empty] | R4-N/33 | 4.08 | 1 | 1 | 4.08 | 2094 | 198 | 1 | 4.08 | 100% |  | 100% | 4.08
[6 empty] | R4-N/34 | 4.08 | 1 | 1 | 4.08 | 2094 | 198 | 1 | 4.08 | 100% |  | 100% | 4.08
[6 empty] | R4-N/35 | 4.08 | 1 | 1 | 4.08 | 2094 | 198 | 1 | 4.08 | 100% |  | 100% | 4.08
[6 empty] | R4-N/36 | 4.08 | 1 | 1 | 4.08 | 2095 | 198 | 1 | 4.08 | 100% |  | 100% | 4.08
[6 empty] | R4-N/37 | 4.08 | 1 | 1 | 4.08 | 2095 | 198 | 1 | 4.08 | 100% |  | 100% | 4.08
[6 empty] | R4-N/38 | 4.08 | 1 | 1 | 4.08 | 2095 | 198 | 1 | 4.08 | 100% |  | 100% | 4.08
[6 empty] | R4-N/39 | 4.08 | 1 | 1 | 4.08 | 2088 | 197 | 1 | 4.08 | 100% |  | 100% | 4.08
[6 empty] | R4-N/40 | 4.08 | 1 | 1 | 4.08 | 2100 | 199 | 1 | 4.08 | 100% |  | 100% | 4.08
[6 empty] | R4-N/41 | 2.98 | 1 | 1 | 2.98 | 2103 | 200 | 1 | 2.98 | 100% |  | 100% | 2.98
[6 empty] | R4-N/42 | 2.75 | 1 | 1 | 2.75 | 2156,2157 | 207 | 1 | 2.75 | 100% |  | 100% | 2.75
[6 empty] | R4-N/43 | 2.75 | 1 | 1 | 2.75 | 2163 | 208 | 1 | 2.75 | 100% |  | 100% | 2.75
[6 empty] | R4-N/44 | 4.27 | 1 | 1 | 4.27 | 2014,2148 | 206 | 1 | 4.27 | 100% |  | 100% | 4.27
[6 empty] | R4-N/45 | 4.27 | 1 | 1 | 4.27 | 2151 | 207 | 1 | 4.27 | 100% |  | 100% | 4.27
[6 empty] | R4-N/46 | 4.27 | 1 | 1 | 4.27 | 2156,2157 | 207 | 1 | 4.27 | 100% |  | 100% | 4.27
[6 empty] | R4-N/47 | 2.13 | 1 | 1 | 2.13 | 2171 | 208 | 1 | 2.13 | 100% |  | 100% | 2.13
[6 empty] | R4-N/48 | 2.13 | 1 | 1 | 2.13 | 2177 | 209 | 1 | 2.13 | 100% |  | 100% | 2.13
[6 empty] | R4-N/49 | 3.73 | 1 | 1 | 3.73 | 2017 | 185 | 1 | 3.73 | 100% |  | 100% | 3.73
[6 empty] | R4-N/50 | 3.73 | 1 | 1 | 3.73 | 1988 | 182 | 1 | 3.73 | 100% |  | 100% | 3.73
[6 empty] | R4-N/51 | 2.54 | 1 | 1 | 2.54 | 2085,2087 | 197 | 1 | 2.54 | 100% |  | 100% | 2.54
[6 empty] | R4-N/52 | 2.54 | 1 | 1 | 2.54 | 2085,2087 | 197 | 1 | 2.54 | 100% |  | 100% | 2.54
[6 empty] | R4-N/53 | 3.07 | 1 | 1 | 3.07 | 1976 | 180 | 1 | 3.07 | 100% |  | 100% | 3.07
[6 empty] | R4-N/54 | 3.06 | 1 | 1 | 3.06 | 1976 | 180 | 1 | 3.06 | 100% |  | 100% | 3.06
[6 empty] | R4-N/55 | 3.07 | 1 | 1 | 3.07 | 1969 | 179 | 1 | 3.07 | 100% |  | 100% | 3.07
[6 empty] | R4-N/56 | 2.06 | 1 | 1 | 2.06 | 2096,2100 | 198,199 | 1 | 2.06 | 100% |  | 100% | 2.06
[6 empty] | R4-N/57 | 2.06 | 1 | 1 | 2.06 | 2103 | 200 | 1 | 2.06 | 100% |  | 100% | 2.06
[6 empty] | R4-N/58 | 2.76 | 1 | 1 | 2.76 | 1988 | 182 | 1 | 2.76 | 100% |  | 100% | 2.76
[6 empty] | R4-N/59 | 2.76 | 1 | 1 | 2.76 | 1988 | 182 | 1 | 2.76 | 100% |  | 100% | 2.76
[6 empty] | R4-N/60 | 2.66 | 1 | 1 | 2.66 | 2111 | 2020 | 1 | 2.66 | 100% |  | 100% | 2.66
[6 empty] | R4-N/61 | 2.66 | 1 | 1 | 2.66 | 2112 | 202 | 1 | 2.66 | 100% |  | 100% | 2.66
[6 empty] | R4-N/62 | 4.49 | 1 | 1 | 4.49 | 2143 | 205 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | R4-N/63 | 4.49 | 1 | 1 | 4.49 | 2085,2087 | 197 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | R4-N/64 | 4.49 | 1 | 1 | 4.49 | 2085,2087 | 197 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | R4-N/65 | 4.49 | 1 | 1 | 4.49 | 2096,2100 | 198,199 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | R4-N/66 | 4.49 | 1 | 1 | 4.49 | 2088 | 197 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | R4-N/67 | 4.49 | 1 | 1 | 4.49 | 2103 | 200 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | R4-N/68 | 4.07 | 1 | 1 | 4.07 | 2127 | 204 | 1 | 4.07 | 100% |  | 100% | 4.07
[6 empty] | R4-N/69 | 4.21 | 1 | 1 | 4.21 | 1955 | 178 | 1 | 4.21 | 100% |  | 100% | 4.21
[6 empty] | R4-N/70 | 4.21 | 1 | 1 | 4.21 | 1955 | 178 | 1 | 4.21 | 100% |  | 100% | 4.21
[6 empty] | R4-N/71 | 4.21 | 1 | 1 | 4.21 | 1955 | 178 | 1 | 4.21 | 100% |  | 100% | 4.21
[6 empty] | R4-N/72 | 4.21 | 1 | 1 | 4.21 | 1969 | 179 | 1 | 4.21 | 100% |  | 100% | 4.21
[6 empty] | R4-N/73 | 4.21 | 1 | 1 | 4.21 | 1969 | 179 | 1 | 4.21 | 100% |  | 100% | 4.21
[6 empty] | R4-N/74 | 3.03 | 1 | 1 | 3.03 | 2111,2116 | 202,203 | 1 | 3.03 | 100% |  | 100% | 3.03
[6 empty] | R4-N/75 | 3.67 | 1 | 1 | 3.67 | 1937 | 176 | 1 | 3.67 | 100% |  | 100% | 3.67
[6 empty] | R4-N/76 | 3.67 | 1 | 1 | 3.67 | 1937 | 176 | 1 | 3.67 | 100% |  | 100% | 3.67
[6 empty] | R4-N/77 | 3.67 | 1 | 1 | 3.67 | 1937 | 176 | 1 | 3.67 | 100% |  | 100% | 3.67
[6 empty] | R4-N/78 | 3.67 | 1 | 1 | 3.67 | 1950 | 178 | 1 | 3.67 | 100% |  | 100% | 3.67
[6 empty] | R4-N/79 | 3.67 | 1 | 1 | 3.67 | 1950 | 178 | 1 | 3.67 | 100% |  | 100% | 3.67
[9 empty] | TOTAL | 294.55 |  |  | TOTAL | 292.305 | TOTAL |  | TOTAL | 238.8
4 | EWS-101 | 800 | 4 | 1 |  | H4-N/01 | 2.06 | 1 | 1 | 2.06 | 2115,2942 | 203,304 | 1 | 2.06 | 100% |  | 100% | 2.06
[6 empty] | H4-N/02 | 2.06 | 1 | 1 | 2.06 | 2115 | 203 | 1 | 2.06 | 100% |  | 100% | 2.06
[6 empty] | H4-N/03 | 4.04 | 1 | 1 | 4.04 | 2049 | 190 | 1 | 4.04 | 100% |  | 100% | 4.04
[6 empty] | H4-N/04 | 4.04 | 1 | 1 | 4.04 | 2049 | 190 | 1 | 4.04 | 100% |  | 100% | 4.04
[6 empty] | H4-N/05 | 2.81 | 1 | 1 | 2.81 | 2137 | 205 | 1 | 2.81 | 100% |  | 100% | 2.81
[6 empty] | H4-N/06 | 3.2 | 1 | 1 | 3.2 | 1917 | 174 | 1 | 3.2 | 100% |  | 100% | 3.2
[6 empty] | H4-N/07 | 4.49 | 1 | 1 | 4.49 | 1916 | 173 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | H4-N/08 | 4.49 | 1 | 1 | 4.49 | 1916 | 173 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | H4-N/09 | 4.49 | 1 | 1 | 4.49 | 1916 | 173 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | H4-N/10 | 4.49 | 1 | 1 | 4.49 | 1917 | 174 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | H4-N/11 | 4.49 | 1 | 1 | 4.49 | 1917 | 174 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | H4-N/12 | 3.09 | 1 | 1 | 3.09 | 2151 | 207 | 1 | 3.09 | 100% |  | 100% | 3.09
[6 empty] | H4-N/13 | 3.64 | 1 | 1 | 3.64 | 2142 | 205 | 1 | 3.64 | 100% |  | 100% | 3.64
[6 empty] | H4-N/14 | 2.68 | 1 | 1 | 2.68 | 2148 |  | 1 | 2.68 | 100% |  | 100% | 2.68
[6 empty] | H4-N/15 | 2.86 | 1 | 1 | 2.86 | 2156,2157 | 207 | 1 | 2.86 | 100% |  | 100% | 2.86
[6 empty] | H4-N/16 | 4.493 | 1 | 1 | 4.493 | 2128 | 204 | 1 | 4.493 | 100% |  | 100% | 4.493
[6 empty] | H4-N/17 | 4.493 | 1 | 1 | 4.493 | 2115 | 203 | 1 | 4.493 | 100% |  | 100% | 4.493
[6 empty] | H4-N/18 | 4.493 | 1 | 1 | 4.493 | 2112 | 202 | 1 | 4.493 | 100% |  | 100% | 4.493
[6 empty] | H4-N/19 | 4.493 | 1 | 1 | 4.493 | 2112 | 202 | 1 | 4.493 | 100% |  | 100% | 4.493
[6 empty] | H4-N/20 | 4.493 | 1 | 1 | 4.493 | 2119 | 203 | 1 | 4.493 | 100% |  | 100% | 4.493
[6 empty] | H4-N/21 | 4.493 | 1 | 1 | 4.493 | 2119 | 203 | 1 | 4.493 | 100% |  | 100% | 4.493
[6 empty] | H4-N/22 | 4.493 | 1 | 1 | 4.493 | 2128 | 204 | 1 | 4.493 | 100% |  | 100% | 4.493
[6 empty] | H4-N/23 | 4.493 | 1 | 1 | 4.493 | 2128 | 204 | 1 | 4.493 | 100% |  | 100% | 4.493
[6 empty] | H4-N/24 | 2.46 | 1 | 1 | 2.46 | 2157 | 207 | 1 | 2.46 | 100% |  | 100% | 2.46
[6 empty] | H4-N/25 | 2.07 | 1 | 1 | 2.07 | 2145 | 206 | 1 | 2.07 | 100% |  | 100% | 2.07
[6 empty] | H4-N/26 | 4.18 | 1 | 1 | 4.18 | 1987 | 182 | 1 | 4.18 | 100% |  | 100% | 4.18
[6 empty] | H4-N/27 | 4.18 | 1 | 1 | 4.18 | 1987 | 182 | 1 | 4.18 | 100% |  | 100% | 4.18
[6 empty] | H4-N/28 | 4.18 | 1 | 1 | 4.18 | 1987,2326 | 182 | 1 | 4.18 | 100% |  | 100% | 4.18
[6 empty] | H4-N/29 | 4.18 | 1 | 1 | 4.18 | 2034 | 188 | 1 | 4.18 | 100% |  | 100% | 4.18
[6 empty] | H4-N/30 | 4.18 | 1 | 1 | 4.18 | 2034 | 188 | 1 | 4.18 | 100% |  | 100% | 4.18
[6 empty] | H4-N/31 | 4.18 | 1 | 1 | 4.18 | 2030 | 187 | 1 | 4.18 | 100% |  | 100% | 4.18
[6 empty] | H4-N/32 | 4.18 | 1 | 1 | 4.18 | 2030 | 187 | 1 | 4.18 | 100% |  | 100% | 4.18
[6 empty] | H4-N/33 | 2.72 | 1 | 1 | 2.72 | 2577 | 261 | 1 | 2.72 | 100% |  | 100% | 2.72
[6 empty] | H4-N/34 | 2.72 | 1 | 1 | 2.72 | 2577 | 261 | 1 | 2.72 | 100% |  | 100% | 2.72
[6 empty] | H4-N/35 | 4.49 | 1 | 1 | 4.49 | 2577 | 261 |  | 0 |  |  |  | 0 | after Level 7 completion
[6 empty] | H4-N/36 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | after Level 7 completion
[6 empty] | H4-N/37 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | Cradle Area (Core Wall Access)
[6 empty] | H4-N/38 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | Cradle Area (Core Wall Access)
[6 empty] | H4-N/39 | 4.49 | 1 | 1 | 4.49 | 2606 | 270 | 0.5 | 2.245 |  |  |  | 0 | Cradle Area (Core Wall Access)
[6 empty] | H4-N/40 | 4.49 | 1 | 1 | 4.49 | 2606 | 270 | 0.5 | 2.245 |  |  |  | 0 | Cradle Area (Core Wall Access)
[6 empty] | H4-N/41 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | Cradle Area (Core Wall Access)
[6 empty] | H4-N/42 | 4.49 | 1 | 1 | 4.49 | 2706 | 282 | 1 | 4.49 |  |  |  | 0 | Cradle Area (Core Wall Access)
[6 empty] | H4-N/43 | 4.49 | 1 | 1 | 4.49 | 2706 | 282 | 1 | 4.49 |  |  |  | 0 | Cradle Area (Core Wall Access)
[6 empty] | H4-N/44 | 4.49 | 1 | 1 | 4.49 | 2706 | 282 | 1 | 4.49 | 100% |  | 100% | 4.49 | WIR 1216
[6 empty] | H4-N/45 | 4.49 | 1 | 1 | 4.49 | 2606,2614 | 270271 | 1 | 4.49 | 100% |  | 100% | 4.49 | WIR 1167
[6 empty] | H4-N/46 | 4.49 | 1 | 1 | 4.49 | 2606,2614 | 270271 | 1 | 4.49 | 100% |  | 100% | 4.49 | WIR 1167
[6 empty] | H4-N/47 | 4.49 | 1 | 1 | 4.49 | 2606,2614 | 270271 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | H4-N/48 | 4.49 | 1 | 1 | 4.49 | 2364 | 232 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | H4-N/49 | 4.49 | 1 | 1 | 4.49 | 2364 | 232 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | H4-N/50 | 4.49 | 1 | 1 | 4.49 | 2364 | 232 | 1 | 4.49 | 100% |  | 100% | 4.49
[6 empty] | H4-N/51 | 3.95 | 1 | 1 | 3.95 |  |  | 1 | 3.95 | 100% |  | 100% | 3.95
[6 empty] | H4-N/52 | 3.83 | 1 | 1 | 3.83 | 2336 |  | 1 | 3.83 | 100% |  | 100% | 3.83
[6 empty] | H4-N/53 | 3.95 | 1 | 1 | 3.95 |  |  | 1 | 3.95 | 100% |  | 100% | 3.95
[9 empty] | TOTAL | 211.674 |  |  | TOTAL | 184.734 | TOTAL |  |  | 171.264
[6 empty] | LVL | L | Qty |  | Mat'l Produced (Length) |  |  | Mat'l On Site | Mat'l On Site (Length) | Work Done |  |  | Work Done (Length)
[6 empty] | L2 | 506.935 | 72 |  | 500.105 |  |  | 96.44% | 488.88 | 92.61% |  |  | 469.453
[6 empty] | L4 | 506.224 | 189 |  | 506.224 |  |  | 94.23% | 477.039 | 81% |  |  | 410.064
[6 empty] | TOTAL (BOQ A) | 59.68 | 16 | 13 | 52.85 |  |  | 10.5 | 41.625 |  |  | 37.2% | 22.198
[6 empty] | TOTAL (BOQ C) | 96.16 | 22 | 22 | 96.16 |  |  | 15.5 | 66.975 |  |  | 0% | 0
MOS
Mat OFFSITE
JC TO BE RELEASED

## Residential - 600mm(Qty)
Quantity Take Off- Service Apartment ( Tower ) | [19 empty] | RPJV ASSESSMENT - NOV 2020
S. No. | Wall Type | Width | Floor Level | Qty Per Floor |  |  |  |  | GRC PANEL PRODUCED |  | GRC PANEL DELIVERED ONSITE |  |  |  | GRC PANEL INSTALLATION |  |  |  | Remarks |  | GRC PANEL ONSITE |  | GRC PANEL INSTALLATION
[6 empty] | CODE | L | Qty | Mat'l Produced | Length | DO No. | MIR No. | Mat'l On Site | Length | Work Done (Previous) | Work Done (This) | Work Done (Cumm.) | Length (This) |  | L | Mat'l On Site | Length | Work Done | Length | Mat'l On Site | Length
1 | EWS-101 | 600 | 6 | 1 | With corner panel | R6-N/01 | 4.49 | 1 | 1 | 4.49 | 2165,2177,2183 | 208,209,210 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 6.29 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R6-N/02 | 4.49 | 1 | 1 | 4.49 | 1999 | 184 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R6-N/03 | 4.49 | 1 | 1 | 4.49 | 1999,2565 | 184,259 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R6-N/04 | 4.49 | 1 | 1 | 4.49 | 1999,2405 | 184 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R6-N/05 | 4.49 | 1 | 1 | 4.49 | 1945 | 177 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R6-N/06 | 4.49 | 1 | 1 | 4.49 | 1945 | 177 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R6-N/07 | 4.49 | 1 | 1 | 4.49 | 1945 | 177 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 0.25 | 1.1225 |  | 0 | -3.3675 | -4.49
[6 empty] | R6-N/08 | 4.49 | 1 | 1 | 4.49 | 1977 | 180 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R6-N/09 | 4.49 | 1 | 1 | 4.49 | 1977 | 180 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R6-N/10 | 4.49 | 1 | 1 | 4.49 | 1941,1945 | 176,177 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 0.75 | 3.3675 |  | 0 | -1.1225 | -4.49
[6 empty] | R6-N/11 | 4.49 | 1 | 1 | 4.49 | 1941,1945 | 176,177 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 0.75 | 3.3675 |  | 0 | -1.1225 | -4.49
[6 empty] | R6-N/12 | 4.49 | 1 | 1 | 4.49 | 1941 | 176 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | R6-N/13 | 4.49 | 1 | 1 | 4.49 | 1961 , 2405 | 179 , 236 | 1 | 4.49 | 100% |  | 100% | 4.49 | WIR 1051 | 4.49 | 0.75 | 3.3675 |  | 0 | -1.1225 | -4.49
[6 empty] | R6-N/14 | 4.49 | 1 | 1 | 4.49 | 1961 | 179 | 1 | 4.49 | 100% |  | 100% | 4.49 | WIR 1051 | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | R6-N/15 | 4.49 | 1 | 1 | 4.49 | 1963 | 179 | 1 | 4.49 | 100% |  | 100% | 4.49 | WIR 1051 | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R6-N/16 | 4.49 | 1 | 1 | 4.49 | 1978 | 181 | 1 | 4.49 | 100% |  | 100% | 4.49 | WIR 1051 | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R6-N/17 | 3.37 | 1 | 1 | 3.37 | 1978 | 181 | 1 | 3.37 | 100% |  | 100% | 3.37 | WIR 1051 | 3.365 |  | 0 |  | 0 | -3.37 | -3.37
[6 empty] | R6-N/18 | 3.37 | 1 | 1 | 3.37 | 1978 | 181 | 1 | 3.37 | 100% |  | 100% | 3.37 | WIR 1051 | 3.365 |  | 0 |  | 0 | -3.37 | -3.37
[5 empty] | Curve with C Panel | R6-N/19 | 3.31 | 1 | 1 | 3.31 | 2332,2336,2565 | 259 | 1 | 3.31 | 100% |  | 100% | 3.31 |  | 3.258 |  | 0 |  | 0 | -3.31 | -3.31
[5 empty] | Curve with C Panel | R6-N/20 | 4.08 | 1 | 1 | 4.08 | 2332,2336,2565 | 259 | 1 | 4.08 | 100% |  | 100% | 4.08 |  | 4.074 |  | 0 |  | 0 | -4.08 | -4.08
[5 empty] | 900mm | R6-N/21 | [7 empty] | - |  |  |  | 0 | refer to SA - 900mm(Qty) worksheet |  |  | - |  | -
[5 empty] | 900mm | R6-N/22 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R6-N/23 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R6-N/24 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | Curve with C Panel | R6-N/25 | 4.09 | 1 | 1 | 4.09 | 2565,2609,2621 | 259,270,272 | 1 | 4.09 | 100% |  | 100% | 4.09 | WIR 1117 | 4.074 |  | 0 |  | 0 | -4.09 | -4.09
[5 empty] | Curve with C Panel | R6-N/26 | 3.31 | 1 | 1 | 3.31 | 2332,2565,2608,2609 | 259,270 | 1 | 3.31 | 100% |  | 100% | 3.31 | WIR 1117 | 3.258 |  | 0 |  | 0 | -3.31 | -3.31
[6 empty] | R6-N/27 | 3.37 | 1 | 1 | 3.37 | 1998 | 184 | 1 | 3.37 | 100% |  | 100% | 3.37 |  | 3.365 |  | 0 |  | 0 | -3.37 | -3.37
[6 empty] | R6-N/28 | 3.37 | 1 | 1 | 3.37 | 1998 | 184 | 1 | 3.37 | 100% |  | 100% | 3.37 |  | 3.365 |  | 0 |  | 0 | -3.37 | -3.37
[6 empty] | R6-N/29 | 4.49 | 1 | 1 | 4.49 | 2005 | 184 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R6-N/30 | 4.49 | 1 | 1 | 4.49 | 2005 | 184 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R6-N/31 | 4.49 | 1 | 1 | 4.49 | 2010 | 184 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R6-N/32 | 4.49 | 1 | 1 | 4.49 | 2010 | 184 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R6-N/33 | 4.49 | 1 | 1 | 4.49 | 2011 | 185 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R6-N/34 | 4.49 | 1 | 1 | 4.49 | 2011 | 185 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R6-N/35 | 4.49 | 1 | 1 | 4.49 | 2454,2624 |  | 1 | 4.49 |  |  |  | 0 |  | 4.49 |  | 0 |  | 0 | -4.49 | 0
[6 empty] | R6-N/36 | 4.49 | 1 | 1 | 4.49 | 2454,2624 |  | 1 | 4.49 |  |  |  | 0 |  | 4.49 |  | 0 |  | 0 | -4.49 | 0
[6 empty] | R6-N/37 | 4.49 | 1 | 1 | 4.49 | 2454,2459,2624 |  | 1 | 4.49 |  |  |  | 0 |  | 4.49 |  | 0 |  | 0 | -4.49 | 0
[6 empty] | R6-N/38 | 4.49 | 1 | 1 | 4.49 | 2459,2624 | 272 | 1 | 4.49 |  |  |  | 0 |  | 4.49 |  | 0 |  | 0 | -4.49 | 0
[6 empty] | R6-N/39 | 4.49 | 1 | 1 | 4.49 | 2459,2624 | 272 | 1 | 4.49 |  |  |  | 0 |  | 4.49 |  | 0 |  | 0 | -4.49 | 0
[6 empty] | R6-N/40 | 4.49 | 1 | 1 | 4.49 | 2459,2624 | 272 | 1 | 4.49 |  |  |  | 0 |  | 4.49 |  | 0 |  | 0 | -4.49 | 0
[6 empty] | R6-N/41 | 4.49 | 1 | 1 | 4.49 | 2022 | 186 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R6-N/42 | 4.49 | 1 | 1 | 4.49 | 2007,2405 | 184 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[5 empty] | With corner panel | R6-N/43 | 4.49 | 1 | 1 | 4.49 | 2007 | 184 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R6-N/44 | 4.49 | 1 | 1 | 4.49 | 2165,2177,2193 | 208,209,213 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 6.29 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R6-N/45 | 4.98 | 1 | 1 | 4.98 | 2179,2190 | 209 | 1 | 4.98 | 100% |  | 100% | 4.98 |  | 3.205 |  | 0 |  | 0 | -4.98 | -4.98
[6 empty] | R6-N/46 | 4.35 | 1 | 1 | 4.35 | 2165,2179 | 208,209 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 |  | 0 |  | 0 | -4.35 | -4.35
[6 empty] | R6-N/47 | 4.35 | 1 | 1 | 4.35 | 2165,2192,2193 | 208,213 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 |  | 0 |  | 0 | -4.35 | -4.35
[6 empty] | R6-N/48 | 4.35 | 1 | 1 | 4.35 | 2171 | 208 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 |  | 0 |  | 0 | -4.35 | -4.35
[6 empty] | R6-N/49 | 4.35 | 1 | 1 | 4.35 | 2171,2180 | 208,209 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 |  | 0 |  | 0 | -4.35 | -4.35
[6 empty] | R6-N/50 | 5.17 | 1 | 1 | 5.17 | 2177,2190,2202 | 209,211,214 | 1 | 5.17 | 100% |  | 100% | 5.17 |  | 3.395 |  | 0 |  | 0 | -5.17 | -5.17
[9 empty] | TOTAL | 199.5 |  |  | TOTAL | 199.5 | TOTAL |  |  | 172.56 |  |  | TOTAL | 20.205 | TOTAL | 0
2 | EWS-101 | 600 | 7 | 1 |  | R7-N/01 | 4.49 | 1 | 1 | 4.49 | 1486,1156 | 018,123 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 6.29 | 1 | 6.29 | 100% | 6.29 | 1.8 | 1.8
[6 empty] | R7-N/02 | 4.49 | 1 | 1 | 4.49 | 1486,1156 | 018,123 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R7-N/03 | 4.49 | 1 | 1 | 4.49 | 1156 | 018 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R7-N/04 | 4.49 | 1 | 1 | 4.49 | 1156 | 018 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R7-N/05 | 4.49 | 1 | 1 | 4.49 | 1156 | 018 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R7-N/06 | 4.49 | 1 | 1 | 4.49 | 1156 | 018 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R7-N/07 | 4.49 | 1 | 1 | 4.49 | 1156 | 018 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R7-N/08 | 4.49 | 1 | 1 | 4.49 | 1156 | 018 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R7-N/09 | 4.49 | 1 | 1 | 4.49 | 1161 | 021 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R7-N/10 | 4.49 | 1 | 1 | 4.49 | 1161 | 021 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R7-N/11 | 4.49 | 1 | 1 | 4.49 | 1161 | 021 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R7-N/12 | 4.49 | 1 | 1 | 4.49 | 1161 | 021 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R7-N/13 | 4.49 | 1 | 1 | 4.49 | 1161 | 021 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R7-N/14 | 4.49 | 1 | 1 | 4.49 | 1161 | 021 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R7-N/15 | 4.49 | 1 | 1 | 4.49 | 1161 | 021 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R7-N/16 | 4.49 | 1 | 1 | 4.49 | 1161 | 021 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Curve with flat panel | R7-N/17 | 2.2 | 1 | 1 | 2.2 | 1294, 1386 | 077, 097 | 1 | 2.2 | 100% |  | 100% | 2.2 |  | 2.354 | 1 | 2.354 | 100% | 2.354 | 0.154 | 0.154
[5 empty] | 900mm | R7-N/18 | [7 empty] | - |  |  |  | 0 | refer to SA - 900mm(Qty) worksheet |  |  | - |  | -
[5 empty] | 900mm | R7-N/19 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | Curve with C Panel | R7-N/20 | 4.1 | 1 | 1 | 4.1 | 1218 | 047 | 1 | 4.1 | 100% |  | 100% | 4.1 |  | 4.072 | 1 | 4.072 | 100% | 4.072 | -0.028 | -0.028
[5 empty] | Curve with C Panel | R7-N/21 | 3.3 | 1 | 1 | 3.3 | 1218 | 047 | 1 | 3.3 | 100% |  | 100% | 3.3 |  | 3.251 | 1 | 3.251 | 100% | 3.251 | -0.049 | -0.049
[6 empty] | R7-N/22 | 3.4 | 1 | 1 | 3.4 | 1191 | 033 | 1 | 3.4 | 100% |  | 100% | 3.4 |  | 3.365 | 1 | 3.365 | 100% | 3.365 | -0.035 | -0.035
[6 empty] | R7-N/23 | 3.4 | 1 | 1 | 3.4 | 1165 | 022 | 1 | 3.4 | 100% |  | 100% | 3.4 |  | 3.365 | 1 | 3.365 | 100% | 3.365 | -0.035 | -0.035
[6 empty] | R7-N/24 | 4.49 | 1 | 1 | 4.49 | 1165 | 022 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R7-N/25 | 4.49 | 1 | 1 | 4.49 | 1165 | 022 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R7-N/26 | 4.49 | 1 | 1 | 4.49 | 1165 | 022 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R7-N/27 | 4.49 | 1 | 1 | 4.49 | 1165 | 022 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R7-N/28 | 4.49 | 1 | 1 | 4.49 | 1165 | 022 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R7-N/29 | 4.49 | 1 | 1 | 4.49 | 1165 | 022 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Curve with flat panel | R7-N/30 | 4.8 | 1 | 1 | 4.8 | 2449 | 240 | 1 | 4.8 | 100% |  | 100% | 4.8 |  | 4.49 |  | 0 |  | 0 | -4.8 | -4.8
[5 empty] | 900mm | R7-N/31 | [7 empty] | - |  |  |  | 0 | refer to SA - 900mm(Qty) worksheet |  |  | - |  | -
[5 empty] | 900mm | R7-N/32 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R7-N/33 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R7-N/34 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | Curve with flat panel | R7-N/35 | 4.8 | 1 | 1 | 4.8 | 2440,2454,2942 | 239,304 | 1 | 4.8 | 100% |  | 100% | 4.8 |  | 4.49 |  | 0 |  | 0 | -4.8 | -4.8
[6 empty] | R7-N/36 | 4.49 | 1 | 1 | 4.49 | 1168 | 023 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R7-N/37 | 4.49 | 1 | 1 | 4.49 | 1168 | 023 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R7-N/38 | 4.49 | 1 | 1 | 4.49 | 1168 | 023 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R7-N/39 | 4.49 | 1 | 1 | 4.49 | 1168 | 023 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 6.29 | 1 | 6.29 | 100% | 6.29 | 1.8 | 1.8
[6 empty] | R7-N/40 | 5 | 1 | 1 | 5 | 1241 | 058 | 1 | 5 | 100% |  | 100% | 5 |  | 3.205 | 1 | 3.205 | 100% | 3.205 | -1.795 | -1.795
[6 empty] | R7-N/41 | 4.4 | 1 | 1 | 4.4 | 1168,1231 | 023'054 | 1 | 4.4 | 100% |  | 100% | 4.4 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.06 | -0.06
[6 empty] | R7-N/42 | 4.4 | 1 | 1 | 4.4 | 1168 | 023 | 1 | 4.4 | 100% |  | 100% | 4.4 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.06 | -0.06
[6 empty] | R7-N/43 | 4.4 | 1 | 1 | 4.4 | 1168 | 023 | 1 | 4.4 | 100% |  | 100% | 4.4 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.06 | -0.06
[6 empty] | R7-N/44 | 4.4 | 1 | 1 | 4.4 | 1168 | 023 | 1 | 4.4 | 100% |  | 100% | 4.4 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.06 | -0.06
[6 empty] | R7-N/45 | 5.2 | 1 | 1 | 5.2 | 1241 | 058 | 1 | 5.2 | 100% |  | 100% | 5.2 |  | 3.995 | 1 | 3.995 | 100% | 3.995 | -1.205 | -1.205
[9 empty] | TOTAL | 170.54 |  |  | TOTAL | 170.54 | TOTAL |  |  | 170.54 |  |  | TOTAL | 161.307 | TOTAL | 161.307
3 | EWS-101 | 600 | 8 | 1 |  | R8-N/01 | 2.79 | 1 | 1 | 2.79 | 1308, 1311,1494 | 080,081,125 | 1 | 2.79 | 100% |  | 100% | 2.79 |  | 2.787 | 1 | 2.787 | 100% | 2.787 | -0.003 | -0.003
[6 empty] | R8-N/02 | 3 | 1 | 1 | 3 | 1494 | 125 | 1 | 3 | 100% |  | 100% | 3 |  | 3.055 | 1 | 3.055 | 100% | 3.055 | 0.055 | 0.055
[6 empty] | R8-N/03 | 4.49 | 1 | 1 | 4.49 | 1076 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R8-N/04 | 4.49 | 1 | 1 | 4.49 | 1076 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R8-N/05 | 4.49 | 1 | 1 | 4.49 | 1076 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R8-N/06 | 4.49 | 1 | 1 | 4.49 | 1076 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R8-N/07 | 4.49 | 1 | 1 | 4.49 | 1076 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R8-N/08 | 4.49 | 1 | 1 | 4.49 | 1113 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R8-N/09 | 4.49 | 1 | 1 | 4.49 | 1076 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R8-N/10 | 4.49 | 1 | 1 | 4.49 | 1076 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R8-N/11 | 4.49 | 1 | 1 | 4.49 | 1076 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R8-N/12 | 4.49 | 1 | 1 | 4.49 | 1081 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R8-N/13 | 4.49 | 1 | 1 | 4.49 | 1081 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R8-N/14 | 4.49 | 1 | 1 | 4.49 | 1081 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R8-N/15 | 4.49 | 1 | 1 | 4.49 | 1081 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R8-N/16 | 4.49 | 1 | 1 | 4.49 | 1081 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R8-N/17 | 3.38 | 1 | 1 | 3.38 | 1186 | 030 | 1 | 3.38 | 100% |  | 100% | 3.38 |  | 3.365 | 1 | 3.365 | 100% | 3.365 | -0.015 | -0.015
[6 empty] | R8-N/18 | 3.38 | 1 | 1 | 3.38 | 1186 | 030 | 1 | 3.38 | 100% |  | 100% | 3.38 |  | 3.365 | 1 | 3.365 | 100% | 3.365 | -0.015 | -0.015
[5 empty] | Curve with C Panel | R8-N/19 | 3.32 | 1 | 1 | 3.32 | 1201 | 040 | 1 | 3.32 | 100% |  | 100% | 3.32 |  | 3.251 | 1 | 3.251 | 100% | 3.251 | -0.069 | -0.069
[5 empty] | Curve with C Panel | R8-N/20 | 4.08 | 1 | 1 | 4.08 | 1201 | 040 | 1 | 4.08 | 100% |  | 100% | 4.08 |  | 4.072 | 1 | 4.072 | 100% | 4.072 | -0.008 | -0.008
[5 empty] | 900mm | R8-N/21 | [7 empty] | - |  |  |  | 0 | refer to SA - 900mm(Qty) worksheet |  |  | - |  | -
[5 empty] | 900mm | R8-N/22 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R8-N/23 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R8-N/24 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | Curve with C Panel | R8-N/25 | 4.08 | 1 | 1 | 4.08 | 1201 | 040 | 1 | 4.08 | 100% |  | 100% | 4.08 |  | 4.072 | 1 | 4.072 | 100% | 4.072 | -0.008 | -0.008
[5 empty] | Curve with C Panel | R8-N/26 | 3.32 | 1 | 1 | 3.32 | 1201 | 040 | 1 | 3.32 | 100% |  | 100% | 3.32 |  | 3.251 | 1 | 3.251 | 100% | 3.251 | -0.069 | -0.069
[6 empty] | R8-N/27 | 3.38 | 1 | 1 | 3.38 | 1186 | 030 | 1 | 3.38 | 100% |  | 100% | 3.38 |  | 3.365 | 1 | 3.365 | 100% | 3.365 | -0.015 | -0.015
[6 empty] | R8-N/28 | 3.38 | 1 | 1 | 3.38 | 1186 | 030 | 1 | 3.38 | 100% |  | 100% | 3.38 |  | 3.365 | 1 | 3.365 | 100% | 3.365 | -0.015 | -0.015
[6 empty] | R8-N/29 | 4.49 | 1 | 1 | 4.49 | 1081 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R8-N/30 | 4.49 | 1 | 1 | 4.49 | 1081 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R8-N/31 | 4.49 | 1 | 1 | 4.49 | 1113 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R8-N/32 | 4.49 | 1 | 1 | 4.49 | 1081 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R8-N/33 | 4.49 | 1 | 1 | 4.49 | 1113 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R8-N/34 | 4.49 | 1 | 1 | 4.49 | 1113 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Curve with flat panel | R8-N/35 | 4.8 | 1 | 1 | 4.8 | 2456 | 241 | 1 | 4.8 | 100% |  | 100% | 4.8 |  | 4.49 |  | 0 |  | 0 | -4.8 | -4.8
[5 empty] | 900mm | R8-N/36 | [7 empty] | - |  |  |  | 0 | refer to SA - 900mm(Qty) worksheet |  |  | - |  | -
[5 empty] | 900mm | R8-N/37 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R8-N/38 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R8-N/39 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | Curve with flat panel | R8-N/40 | 4.8 | 1 | 1 | 4.8 | 2454,2456 | 241 | 1 | 4.8 |  |  |  | 0 |  | 4.49 |  | 0 |  | 0 | -4.8 | 0
[6 empty] | R8-N/41 | 4.49 | 1 | 1 | 4.49 | 1113 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R8-N/42 | 4.49 | 1 | 1 | 4.49 | 1113 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R8-N/43 | 2.87 | 1 | 1 | 2.87 |  |  | 1 | 2.87 | 100% |  | 100% | 2.87 |  | 2.895 | 1 | 2.895 | 100% | 2.895 | 0.025 | 0.025
[9 empty] | TOTAL | 145.36 |  |  | TOTAL | 145.36 | TOTAL |  |  | 140.56 |  |  | TOTAL | 135.623 | TOTAL | 135.623
4 | EWS-101 | 600 | 9 | 1 |  | R9-N/01 | 4.49 | 1 | 1 | 4.49 | 1051 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 6.29 | 1 | 6.29 | 100% | 6.29 | 1.8 | 1.8
[6 empty] | R9-N/02 | 4.49 | 1 | 1 | 4.49 | 1051 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R9-N/03 | 4.49 | 1 | 1 | 4.49 | 1051 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R9-N/04 | 4.49 | 1 | 1 | 4.49 | 1051 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R9-N/05 | 4.49 | 1 | 1 | 4.49 | 1051 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R9-N/06 | 4.49 | 1 | 1 | 4.49 | 1051 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R9-N/07 | 4.49 | 1 | 1 | 4.49 | 1051 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R9-N/08 | 4.49 | 1 | 1 | 4.49 | 1051 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R9-N/09 | 4.49 | 1 | 1 | 4.49 | 1052 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R9-N/10 | 4.49 | 1 | 1 | 4.49 | 1052 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R9-N/11 | 4.49 | 1 | 1 | 4.49 | 1057 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R9-N/12 | 4.49 | 1 | 1 | 4.49 | 1052 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R9-N/13 | 4.49 | 1 | 1 | 4.49 | 1052 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R9-N/14 | 4.49 | 1 | 1 | 4.49 | 1057 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R9-N/15 | 4.49 | 1 | 1 | 4.49 | 1057 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R9-N/16 | 4.49 | 1 | 1 | 4.49 | 1057 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Curve with flat panel | R9-N/17 | 2.93 | 1 | 1 | 2.93 | 1303 | 079 | 1 | 2.93 | 100% |  | 100% | 2.93 |  | 3.341 | 1 | 3.341 | 100% | 3.341 | 0.411 | 0.411
[5 empty] | 900mm | R9-N/18 | [7 empty] | - |  |  |  | 0 | refer to SA - 900mm(Qty) worksheet |  |  | - |  | -
[5 empty] | 900mm | R9-N/19 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | Curve with C Panel | R9-N/20 | 4.08 | 1 | 1 | 4.08 | 1218 | 047 | 1 | 4.08 | 100% |  | 100% | 4.08 |  | 4.072 | 1 | 4.072 | 100% | 4.072 | -0.008 | -0.008
[5 empty] | Curve with C Panel | R9-N/21 | 3.32 | 1 | 1 | 3.32 | 1218 | 047 | 1 | 3.32 | 100% |  | 100% | 3.32 |  | 3.256 | 1 | 3.256 | 100% | 3.256 | -0.064 | -0.064
[6 empty] | R9-N/22 | 3.38 | 1 | 1 | 3.38 | 1199 | 037 | 1 | 3.38 | 100% |  | 100% | 3.38 |  | 3.365 | 1 | 3.365 | 100% | 3.365 | -0.015 | -0.015
[6 empty] | R9-N/23 | 3.38 | 1 | 1 | 3.38 | 1059 |  | 1 | 3.38 | 100% |  | 100% | 3.38 |  | 3.365 | 1 | 3.365 | 100% | 3.365 | -0.015 | -0.015
[6 empty] | R9-N/24 | 4.49 | 1 | 1 | 4.49 | 1057 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R9-N/25 | 4.49 | 1 | 1 | 4.49 | 1057 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R9-N/26 | 4.49 | 1 | 1 | 4.49 | 1057 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R9-N/27 | 4.49 | 1 | 1 | 4.49 | 1057 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R9-N/28 | 4.49 | 1 | 1 | 4.49 | 1059 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R9-N/29 | 4.49 | 1 | 1 | 4.49 | 1059 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Curve with flat panel | R9-N/30 | 4.82 | 1 | 1 | 4.82 | 2463,2456,2709 | 242 | 1 | 4.82 | 100% |  | 100% | 4.82 | WIR 1223 | 4.49 |  | 0 |  | 0 | -4.82 | -4.82
[5 empty] | 900mm | R9-N/31 | [7 empty] | - |  |  |  | 0 | refer to SA - 900mm(Qty) worksheet |  |  | - |  | -
[5 empty] | 900mm | R9-N/32 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R9-N/33 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R9-N/34 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | Curve with flat panel | R9-N/35 | 4.82 | 1 | 1 | 4.82 | 2454,2463,2709 | 242 | 1 | 4.82 | 100% |  | 100% | 4.82 | WIR 1223 | 4.49 |  | 0 |  | 0 | -4.82 | -4.82
[6 empty] | R9-N/36 | 4.49 | 1 | 1 | 4.49 | 1059 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R9-N/37 | 4.49 | 1 | 1 | 4.49 | 1060 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 50% | 2.245 | 0 | -2.245
[6 empty] | R9-N/38 | 4.49 | 1 | 1 | 4.49 | 1063 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R9-N/39 | 4.49 | 1 | 1 | 4.49 | 1063 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 6.29 | 1 | 6.29 | 100% | 6.29 | 1.8 | 1.8
[5 empty] | Corner panel | R9-N/40 | 4.98 | 1 | 1 | 4.98 | 1229 | 053 | 1 | 4.98 | 100% |  | 100% | 4.98 |  | 3.205 | 1 | 3.205 | 100% | 3.205 | -1.775 | -1.775
[6 empty] | R9-N/41 | 4.35 | 1 | 1 | 4.35 | 1060 |  | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[6 empty] | R9-N/42 | 4.35 | 1 | 1 | 4.35 | 1060 |  | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[6 empty] | R9-N/43 | 4.35 | 1 | 1 | 4.35 | 1060 |  | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[6 empty] | R9-N/44 | 4.35 | 1 | 1 | 4.35 | 1063 |  | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[5 empty] | Corner panel | R9-N/45 | 5.17 | 1 | 1 | 5.17 |  |  | 1 | 5.17 | 100% |  | 100% | 5.17 |  | 3.395 | 1 | 3.395 | 100% | 3.395 | -1.775 | -1.775
[9 empty] | TOTAL | 171.02 |  |  | TOTAL | 171.02 | TOTAL |  |  | 171.02 |  |  | TOTAL | 161.699 | TOTAL | 159.454
5 | EWS-101 | 600 | 10 | 1 |  | R10-N/01 | 2.79 | 1 | 1 | 2.79 | 1428 | 106 | 1 | 2.79 | 100% |  | 100% | 2.79 |  | 2.787 | 1 | 2.787 | 100% | 2.787 | -0.003 | -0.003
[6 empty] | R10-N/02 | 3.03 | 1 | 1 | 3.03 | 1672 | 152 | 1 | 3.03 | 100% |  | 100% | 3.03 |  | 3.055 | 1 | 3.055 | 100% | 3.055 | 0.025 | 0.025
[6 empty] | R10-N/03 | 4.49 | 1 | 1 | 4.49 | 1205 | 041 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R10-N/04 | 4.49 | 1 | 1 | 4.49 | 1201 | 039 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 50% | 2.245 | 0 | -2.245
[6 empty] | R10-N/05 | 4.49 | 1 | 1 | 4.49 | 1201 | 039 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R10-N/06 | 4.49 | 1 | 1 | 4.49 | 1201 | 040 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R10-N/07 | 4.49 | 1 | 1 | 4.49 | 1201 | 040 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R10-N/08 | 4.49 | 1 | 1 | 4.49 | 1205 | 041 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R10-N/09 | 4.49 | 1 | 1 | 4.49 | 1201 | 039 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R10-N/10 | 4.49 | 1 | 1 | 4.49 | 1201 | 039 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R10-N/11 | 4.49 | 1 | 1 | 4.49 | 1201 | 039 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R10-N/12 | 4.49 | 1 | 1 | 4.49 | 1201 | 039 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R10-N/13 | 4.49 | 1 | 1 | 4.49 | 1199 | 037 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R10-N/14 | 4.49 | 1 | 1 | 4.49 | 1201 | 039 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R10-N/15 | 4.49 | 1 | 1 | 4.49 | 1218 | 047 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R10-N/16 | 4.49 | 1 | 1 | 4.49 | 1201 | 039 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R10-N/17 | 4.49 | 1 | 1 | 4.49 | 1205 | 041 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 3.365 | 1 | 3.365 | 100% | 3.365 | -1.125 | -1.125
[6 empty] | R10-N/18 | 2.26 | 1 | 1 | 2.26 | 1231 | 054 | 1 | 2.26 | 100% |  | 100% | 2.26 |  | 3.365 | 1 | 3.365 | 100% | 3.365 | 1.105 | 1.105
[5 empty] | Curve Panel | R10-N/19 | 3.32 | 1 | 1 | 3.32 |  |  | 1 | 3.32 | 100% |  | 100% | 3.32 |  | 3.251 | 1 | 3.251 | 100% | 3.251 | -0.069 | -0.069
[5 empty] | Curve Panel | R10-N/20 | 4.1 | 1 | 1 | 4.1 |  |  | 1 | 4.1 | 100% |  | 100% | 4.1 |  | 4.072 | 1 | 4.072 | 100% | 4.072 | -0.028 | -0.028
[6 empty] | R10-N/21 | 3.82 | 1 | 1 | 3.82 |  |  | 1 | 3.82 | 100% |  | 100% | 3.82 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.018 | -0.018
[6 empty] | R10-N/22 | 3.82 | 1 | 1 | 3.82 | 1205 | 041 | 1 | 3.82 | 100% |  | 100% | 3.82 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.018 | -0.018
[6 empty] | R10-N/23 | 3.82 | 1 | 1 | 3.82 |  |  | 1 | 3.82 | 100% |  | 100% | 3.82 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.018 | -0.018
[6 empty] | R10-N/24 | 3.82 | 1 | 1 | 3.82 |  |  | 1 | 3.82 | 100% |  | 100% | 3.82 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.018 | -0.018
[5 empty] | Curve Panel | R10-N/25 | 4.1 | 1 | 1 | 4.1 |  |  | 1 | 4.1 | 100% |  | 100% | 4.1 |  | 4.072 | 1 | 4.072 | 100% | 4.072 | -0.028 | -0.028
[5 empty] | Curve Panel | R10-N/26 | 3.32 | 1 | 1 | 3.32 |  |  | 1 | 3.32 | 100% |  | 100% | 3.32 |  | 3.251 | 1 | 3.251 | 100% | 3.251 | -0.069 | -0.069
[6 empty] | R10-N/27 | 2.26 | 1 | 1 | 2.26 |  |  | 1 | 2.26 | 100% |  | 100% | 2.26 |  | 3.365 | 1 | 3.365 | 100% | 3.365 | 1.105 | 1.105
[6 empty] | R10-N/28 | 4.49 | 1 | 1 | 4.49 | 1205 | 041 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 3.365 | 1 | 3.365 | 100% | 3.365 | -1.125 | -1.125
[6 empty] | R10-N/29 | 4.49 | 1 | 1 | 4.49 | 1205 | 041 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R10-N/30 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R10-N/31 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R10-N/32 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R10-N/33 | 4.49 | 1 | 1 | 4.49 | 1229 | 053 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R10-N/34 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Curve with flat panel | R10-N/35 | 4.8 | 1 | 1 | 4.8 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[5 empty] | 900mm | R10-N/36 | [7 empty] | - |  |  |  | 0 | refer to SA - 900mm(Qty) worksheet |  |  | - |  | -
[5 empty] | 900mm | R10-N/37 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R10-N/38 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R10-N/39 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | Curve with flat panel | R10-N/40 | 4.8 | 1 | 1 | 4.8 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | R10-N/41 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R10-N/42 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R10-N/43 | 2.87 | 1 | 1 | 2.87 |  |  | 1 | 2.87 | 100% |  | 100% | 2.87 |  | 2.895 | 1 | 2.895 | 100% | 2.895 | 0.025 | 0.025
[9 empty] | TOTAL | 160.69 |  |  | TOTAL | 151.09 | TOTAL |  |  | 151.09 |  |  | TOTAL | 150.831 | TOTAL | 148.586
6 | EWS-101 | 600 | 11 | 1 |  | R11-N/01 | 4.49 | 1 | 1 | 4.49 | 1188 | 031 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R11-N/02 | 4.49 | 1 | 1 | 4.49 | 1188 | 031 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R11-N/03 | 4.49 | 1 | 1 | 4.49 | 1188 | 031 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R11-N/04 | 4.49 | 1 | 1 | 4.49 | 1188 | 031 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R11-N/05 | 4.49 | 1 | 1 | 4.49 | 1188 | 031 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R11-N/06 | 4.49 | 1 | 1 | 4.49 | 1188 | 031 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R11-N/07 | 4.49 | 1 | 1 | 4.49 | 1188 | 031 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R11-N/08 | 4.49 | 1 | 1 | 4.49 | 1188 | 031 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R11-N/09 | 4.49 | 1 | 1 | 4.49 | 1194 | 034 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R11-N/10 | 4.49 | 1 | 1 | 4.49 | 1194 | 034 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R11-N/11 | 2.97 | 1 | 1 | 2.97 |  |  | 1 | 2.97 | 100% |  | 100% | 2.97 |  | 2.95 | 1 | 2.95 | 100% | 2.95 | -0.02 | -0.02
[5 empty] | Curve with flat panel | R11-N/12 | 2.35 | 1 | 1 | 2.35 | 1311, 1386 | 081, 097 | 1 | 2.35 | 100% |  | 100% | 2.35 |  | 3.336 | 1 | 3.336 | 100% | 3.336 | 0.986 | 0.986
[5 empty] | Corner panel | R11-N/13 | 2.04 | 1 | 1 | 2.04 | 1463,1645 | 113,148 | 1 | 2.04 | 100% |  | 100% | 2.04 |  | 2.355 | 1 | 2.355 | 100% | 2.355 | 0.315 | 0.315
[5 empty] | Corner panel | R11-N/14 | 3.3 | 1 | 1 | 3.3 | 1463,1645 | 113,148 | 1 | 3.3 | 100% |  | 100% | 3.3 |  | 3.61 | 1 | 3.61 | 100% | 3.61 | 0.31 | 0.31
[5 empty] | Curve with flat panel | R11-N/15 | 4.81 | 1 | 1 | 4.81 | 2472 | 244 | 1 | 4.81 |  |  |  | 0 |  | 4.49 |  | 0 |  | 0 | -4.81 | 0
[5 empty] | 900mm | R11-N/16 | [7 empty] | - |  |  |  | 0 | refer to SA - 900mm(Qty) worksheet |  |  | - |  | -
[5 empty] | 900mm | R11-N/17 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R11-N/18 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R11-N/19 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | Curve with flat panel | R11-N/20 | 4.8 | 1 | 1 | 4.8 | 2472 | 244 | 1 | 4.8 |  |  |  | 0 |  | 4.49 |  | 0 |  | 0 | -4.8 | 0
[6 empty] | R11-N/21 | 4.49 | 1 | 1 | 4.49 | 2472 | 244 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R11-N/22 | 4.49 | 1 | 1 | 4.49 | 1194 | 034 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R11-N/23 | 4.49 | 1 | 1 | 4.49 | 1194 | 034 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R11-N/24 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Corner panel | R11-N/25 | 1.49 | 1 | 1 | 1.49 |  |  | 1 | 1.49 | 100% |  | 100% | 1.49 |  | 1.8 | 1 | 1.8 | 100% | 1.8 | 0.31 | 0.31
[5 empty] | Corner panel | R11-N/26 | 3.49 | 1 | 1 | 3.49 |  |  | 1 | 3.49 | 100% |  | 100% | 3.49 |  | 3.805 | 1 | 3.805 | 100% | 3.805 | 0.315 | 0.315
[6 empty] | R11-N/27 | 4.35 | 1 | 1 | 4.35 |  |  | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[6 empty] | R11-N/28 | 4.35 | 1 | 1 | 4.35 |  |  | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[6 empty] | R11-N/29 | 4.35 | 1 | 1 | 4.35 |  |  | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[6 empty] | R11-N/30 | 4.35 | 1 | 1 | 4.35 | 1289, 1291 | 079 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[6 empty] | R11-N/31 | 3.68 | 1 | 1 | 3.68 |  |  | 1 | 3.68 | 100% |  | 100% | 3.68 |  | 3.995 | 1 | 3.995 | 100% | 3.995 | 0.315 | 0.315
[6 empty] | R11-N/32 | 1.49 | 1 | 1 | 1.49 |  |  | 1 | 1.49 | 100% |  | 100% | 1.49 |  | 1.8 | 1 | 1.8 | 100% | 1.8 | 0.31 | 0.31
[9 empty] | TOTAL | 110.68 |  |  | TOTAL | 110.68 | TOTAL |  |  | 101.07 |  |  | TOTAL | 103.871 | TOTAL | 103.871
7 | EWS-101 | 600 | 12 | 1 |  | R12-N/01 | 2.8 | 1 | 1 | 2.8 | 1386 | 097 | 1 | 2.8 | 100% |  | 100% | 2.8 |  | 2.793 | 1 | 2.793 | 100% | 2.793 | -0.007 | -0.007
[6 empty] | R12-N/02 | 2.13 | 1 | 1 | 2.13 | 1386 | 097 | 1 | 2.13 | 100% |  | 100% | 2.13 |  | 3.049 | 1 | 3.049 | 100% | 3.049 | 0.919 | 0.919
[6 empty] | R12-N/03 | 0.89 | 1 | 1 | 0.89 | 1207 | 042 | 1 | 0.89 | 100% |  | 100% | 0.89 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 3.6 | 3.6
[6 empty] | R12-N/04 | 4.49 | 1 | 1 | 4.49 | 1207 | 042 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R12-N/05 | 4.49 | 1 | 1 | 4.49 | 1207 | 042 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R12-N/06 | 4.49 | 1 | 1 | 4.49 | 1207 | 042 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R12-N/07 | 4.49 | 1 | 1 | 4.49 | 1207 | 042 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R12-N/08 | 4.49 | 1 | 1 | 4.49 | 1207 | 042 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R12-N/09 | 4.49 | 1 | 1 | 4.49 | 1207 | 042 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R12-N/10 | 4.49 | 1 | 1 | 4.49 | 1207 | 042 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R12-N/11 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R12-N/12 | 3.51 | 1 | 1 | 3.51 |  |  | 1 | 3.51 | 100% |  | 100% | 3.51 |  | 3.5 | 1 | 3.5 | 100% | 3.5 | -0.01 | -0.01
[5 empty] | Curve with C Panel | R12-N/13 | 3.25 | 1 | 1 | 3.25 | 1386, 1405 | 097, 100 | 1 | 3.25 | 100% |  | 100% | 3.25 |  | 3.24 | 1 | 3.24 | 100% | 3.24 | -0.01 | -0.01
[5 empty] | Curve with C Panel | R12-N/14 | 4.02 | 1 | 1 | 4.02 | 1386, 1405 | 097, 100 | 1 | 4.02 | 100% |  | 100% | 4.02 |  | 4.005 | 1 | 4.005 | 100% | 4.005 | -0.015 | -0.015
[6 empty] | R12-N/15 | 3.81 | 1 | 1 | 3.81 |  |  | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.008 | -0.008
[6 empty] | R12-N/16 | 3.81 | 1 | 1 | 3.81 |  |  | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.008 | -0.008
[6 empty] | R12-N/17 | 3.81 | 1 | 1 | 3.81 |  |  | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.008 | -0.008
[6 empty] | R12-N/18 | 3.81 | 1 | 1 | 3.81 |  |  | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.008 | -0.008
[5 empty] | Curve with C Panel | R12-N/19 | 4.02 | 1 | 1 | 4.02 | 1386,1419 | 097,105 | 1 | 4.02 | 100% |  | 100% | 4.02 |  | 4.005 | 1 | 4.005 | 100% | 4.005 | -0.015 | -0.015
[5 empty] | Curve with C Panel | R12-N/20 | 3.25 | 1 | 1 | 3.25 | 1386,1405 | 097,100 | 1 | 3.25 | 100% |  | 100% | 3.25 |  | 3.24 | 1 | 3.24 | 100% | 3.24 | -0.01 | -0.01
[6 empty] | R12-N/21 | 3.5 | 1 | 1 | 3.5 |  |  | 1 | 3.5 | 100% |  | 100% | 3.5 |  | 3.5 | 1 | 3.5 | 100% | 3.5 | 0 | 0
[6 empty] | R12-N/22 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Curve with flat panel | R12-N/23 | 4.8 | 1 | 1 | 4.8 | 2479,2480, 2726, 2913 | 247287 | 1 | 4.8 |  |  |  | 0 |  | 4.49 |  | 0 |  | 0 | -4.8 | 0
[5 empty] | 900mm | R12-N/24 | [7 empty] | - |  |  |  | 0 | refer to SA - 900mm(Qty) worksheet |  |  | - |  | -
[5 empty] | 900mm | R12-N/25 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R12-N/26 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R12-N/27 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | Curve with flat panel | R12-N/28 | 4.8 | 1 | 1 | 4.8 | 2479,2480,2726 | 2162,47,287 | 1 | 4.8 |  |  |  | 0 |  | 4.49 |  | 0 |  | 0 | -4.8 | 0
[6 empty] | R12-N/29 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | R12-N/30 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | R12-N/31 | 2.87 | 1 | 1 | 2.87 | 1386 | 097 | 1 | 2.87 | 100% |  | 100% | 2.87 |  | 2.895 | 1 | 2.895 | 100% | 2.895 | 0.025 | 0.025
[9 empty] | TOTAL | 104.47 |  |  | TOTAL | 104.47 | TOTAL |  |  | 94.87 |  |  | TOTAL | 99.315 | TOTAL | 90.335
8 | EWS-101 | 600 | 13 | 1 |  | R13-N/01 | 2.06 | 1 | 1 | 2.06 |  |  | 1 | 2.06 | 100% |  | 100% | 2.06 |  | 2.05 | 1 | 2.05 | 100% | 2.05 | -0.01 | -0.01
[6 empty] | R13-N/02 | 3.81 | 1 | 1 | 3.81 | 1316 | 082 | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.008 | -0.008
[6 empty] | R13-N/03 | 3.81 | 1 | 1 | 3.81 | 1311 | 081 | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.008 | -0.008
[5 empty] | Curve with C Panel | R13-N/04 | 4.15 | 1 | 1 | 4.15 | 1386,1437 | 097,107 | 1 | 4.15 | 100% |  | 100% | 4.15 |  | 4.138 | 1 | 4.138 | 100% | 4.138 | -0.012 | -0.012
[5 empty] | Curve with C Panel | R13-N/05 | 2.96 | 1 | 1 | 2.96 | 1386,1419 | 097,105 | 1 | 2.96 | 100% |  | 100% | 2.96 |  | 4.138 | 1 | 4.138 | 100% | 4.138 | 1.178 | 1.178
[6 empty] | R13-N/06 | 3.67 | 1 | 1 | 3.67 | 1390 | 098 | 1 | 3.67 | 100% |  | 100% | 3.67 |  | 3.659 | 1 | 3.659 | 100% | 3.659 | -0.011 | -0.011
[6 empty] | R13-N/07 | 4.49 | 1 | 1 | 4.49 | 1241,1390 | 058,098 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Curve with flat panel | R13-N/08 | 4.8 | 1 | 1 | 4.8 | 2535,2716 | 256,284 | 1 | 4.8 | 100% |  | 100% | 4.8 | WIR 1229 | 4.49 |  | 0 |  | 0 | -4.8 | -4.8
[5 empty] | 900mm | R13-N/09 | [7 empty] | - |  |  |  | 0 | refer to SA - 900mm(Qty) worksheet |  |  | - |  | -
[5 empty] | 900mm | R13-N/10 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R13-N/11 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R13-N/12 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | Curve with flat panel | R13-N/13 | 4.8 | 1 | 1 | 4.8 | 2485,2492,2716 | 284 | 1 | 4.8 | 100% |  | 100% | 4.8 | WIR 1229 | 4.49 |  | 0 |  | 0 | -4.8 | -4.8
[6 empty] | R13-N/14 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | R13-N/15 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R13-N/16 | 4.49 | 1 | 1 | 4.49 | 1238 | 057 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R13-N/17 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Corner panel | R13-N/18 | 4.98 | 1 | 1 | 4.98 | 1423 | 106 | 1 | 4.98 | 100% |  | 100% | 4.98 |  | 5.005 | 1 | 5.005 | 100% | 5.005 | 0.025 | 0.025
[6 empty] | R13-N/19 | 4.35 | 1 | 1 | 4.35 | 1238 | 057 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[6 empty] | R13-N/20 | 4.35 | 1 | 1 | 4.35 |  |  | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[6 empty] | R13-N/21 | 4.35 | 1 | 1 | 4.35 |  |  | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[6 empty] | R13-N/22 | 4.35 | 1 | 1 | 4.35 |  |  | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[5 empty] | Corner panel | R13-N/23 | 5.17 | 1 | 1 | 5.17 | 1428,1437 | 106,107 | 1 | 5.17 | 100% |  | 100% | 5.17 |  | 5.195 | 1 | 5.195 | 100% | 5.195 | 0.025 | 0.025
[6 empty] | R13-N/24 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R13-N/25 | 4.49 | 1 | 1 | 4.49 | 1238 | 057 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R13-N/26 | 4.49 | 1 | 1 | 4.49 | 1241 | 058 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R13-N/27 | 4.49 | 1 | 1 | 4.49 | 1241 | 058 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R13-N/28 | 4.49 | 1 | 1 | 4.49 | 1241 | 058 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R13-N/29 | 4.49 | 1 | 1 | 4.49 | 1241 | 058 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R13-N/30 | 4.49 | 1 | 1 | 4.49 | 1241 | 058 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R13-N/31 | 4.49 | 1 | 1 | 4.49 | 1238 | 057 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R13-N/32 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R13-N/33 | 2.59 | 1 | 1 | 2.59 | 1289 | 076 | 1 | 2.59 | 100% |  | 100% | 2.59 |  | 2.583 | 1 | 2.583 | 100% | 2.583 | -0.007 | -0.007
[5 empty] | Curve Panel | R13-N/34 | 4.24 | 1 | 1 | 4.24 | 1390 | 098 | 1 | 4.24 | 100% |  | 100% | 4.24 |  | 4.938 | 1 | 4.938 | 100% | 4.938 | 0.698 | 0.698
[9 empty] | TOTAL | 127.3 |  |  | TOTAL | 127.3 | TOTAL |  |  | 127.3 |  |  | TOTAL | 119.53 | TOTAL | 115.04
9 | EWS-101 | 600 | 14 | 1 |  | R14-N/01 | 2.8 | 1 | 1 | 2.8 | 1428,1471,1474 | 106,116,118 | 1 | 2.8 | 100% |  | 100% | 2.8 |  | 2.793 | 1 | 2.793 | 33.33% | 0.931 | -0.007 | -1.869
[6 empty] | R14-N/02 | 3.03 | 1 | 1 | 3.03 | 1428,1444 | 106,108 | 1 | 3.03 | 100% |  | 100% | 3.03 |  | 3.049 | 1 | 3.049 | 100% | 3.049 | 0.019 | 0.019
[6 empty] | R14-N/03 | 4.49 | 1 | 1 | 4.49 | 1248 | 061 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R14-N/04 | 4.49 | 1 | 1 | 4.49 | 1244 | 060 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R14-N/05 | 4.49 | 1 | 1 | 4.49 | 1244 | 060 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R14-N/06 | 4.49 | 1 | 1 | 4.49 | 1248 | 061 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R14-N/07 | 4.49 | 1 | 1 | 4.49 | 1248 | 061 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R14-N/08 | 4.49 | 1 | 1 | 4.49 | 1248 | 061 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R14-N/09 | 4.49 | 1 | 1 | 4.49 | 1244 | 060 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R14-N/10 | 4.49 | 1 | 1 | 4.49 | 1244 | 060 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R14-N/11 | 4.49 | 1 | 1 | 4.49 | 1416 | 104 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R14-N/12 | 3.1 | 1 | 1 | 3.1 | 1416 | 104 | 1 | 3.1 | 100% |  | 100% | 3.1 |  | 3.5 | 1 | 3.5 | 100% | 3.5 | 0.4 | 0.4
[5 empty] | Curve with C Panel | R14-N/13 | 3.25 | 1 | 1 | 3.25 | 1386,1419,1444 | 097,105 | 1 | 3.25 | 100% |  | 100% | 3.25 |  | 3.24 | 1 | 3.24 | 100% | 3.24 | -0.01 | -0.01
[5 empty] | Curve with C Panel | R14-N/14 | 4.02 | 1 | 1 | 4.02 | 1386,1416 | 097,104 | 1 | 4.02 | 100% |  | 100% | 4.02 |  | 4.005 | 0.66667 | 2.67 | 66.67% | 2.67 | -1.35 | -1.35
[6 empty] | R14-N/15 | 3.81 | 1 | 1 | 3.81 | 1316 | 082 | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.008 | -0.008
[6 empty] | R14-N/16 | 3.81 | 1 | 1 | 3.81 | 1322 | 084 | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.008 | -0.008
[6 empty] | R14-N/17 | 3.81 | 1 | 1 | 3.81 | 1322 | 084 | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.008 | -0.008
[6 empty] | R14-N/18 | 3.81 | 1 | 1 | 3.81 | 1322 | 084 | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.008 | -0.008
[5 empty] | Curve with C Panel | R14-N/19 | 4.02 | 1 | 1 | 4.02 | 1419,1473 | 105,118 | 1 | 4.02 | 100% |  | 100% | 4.02 |  | 4.005 | 0.66667 | 2.67 | 66.67% | 2.67 | -1.35 | -1.35
[5 empty] | Curve with C Panel | R14-N/20 | 3.25 | 1 | 1 | 3.25 | 1473,1416 | 104 | 1 | 3.25 | 100% |  | 100% | 3.25 |  | 3.24 | 0.66667 | 2.16 | 66.67% | 2.16 | -1.09 | -1.09
[6 empty] | R14-N/21 | 3.51 | 1 | 1 | 3.51 | 1423 | 106 | 1 | 3.51 | 100% |  | 100% | 3.51 |  | 3.5 | 1 | 3.5 | 100% | 3.5 | -0.01 | -0.01
[6 empty] | R14-N/22 | 4.49 | 1 | 1 | 4.49 | 1428 | 106 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Curve with flat panel | R14-N/23 | 4.8 | 1 | 1 | 4.8 | 2492,2516,2716 | 284 | 1 | 4.8 | 100% |  | 100% | 4.8 | WIR 1222 | 4.49 |  | 0 |  | 0 | -4.8 | -4.8
[5 empty] | 900mm | R14-N/24 | [7 empty] | - |  |  |  | 0 | refer to SA - 900mm(Qty) worksheet |  |  | - |  | -
[5 empty] | 900mm | R14-N/25 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R14-N/26 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R14-N/27 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | Curve with flat panel | R14-N/28 | 4.8 | 1 | 1 | 4.8 | 2492,2716 | 284 | 1 | 4.8 | 100% |  | 100% | 4.8 | WIR 1222 | 4.49 |  | 0 |  | 0 | -4.8 | -4.8
[6 empty] | R14-N/29 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | R14-N/30 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | R14-N/31 | 2.87 | 1 | 1 | 2.87 | 1386,1458 | 097,112 | 1 | 2.87 | 100% |  | 100% | 2.87 |  | 2.895 | 1 | 2.895 | 66.67% | 1.93 | 0.025 | -0.94
[9 empty] | TOTAL | 108.57 |  |  | TOTAL | 108.57 | TOTAL |  |  | 108.57 |  |  | TOTAL | 95.565 | TOTAL | 83.758
10 | EWS-101 | 600 | 15 | 1 |  | R15-N/01 | 2.06 | 1 | 1 | 2.06 |  |  | 1 | 2.06 | 100% |  | 100% | 2.06 |  | 2.05 | 1 | 2.05 | 100% | 2.05 | -0.01 | -0.01
[6 empty] | R15-N/02 | 3.81 | 1 | 1 | 3.81 | 1322 | 084 | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.008 | -0.008
[6 empty] | R15-N/03 | 3.81 | 1 | 1 | 3.81 | 1316 | 082 | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.008 | -0.008
[5 empty] | Curve with C Panel | R15-N/04 | 4.15 | 1 | 1 | 4.15 | 1437,1450 | 107,110 | 1 | 4.15 | 100% |  | 100% | 4.15 |  | 4.138 | 1 | 4.138 | 100% | 4.138 | -0.012 | -0.012
[5 empty] | Curve with C Panel | R15-N/05 | 2.96 | 1 | 1 | 2.96 | 1437,1450 | 107,110 | 1 | 2.96 | 100% |  | 100% | 2.96 |  | 4.138 | 1 | 4.138 | 100% | 4.138 | 1.178 | 1.178
[6 empty] | R15-N/06 | 3.67 | 1 | 1 | 3.67 | 1423 | 106 | 1 | 3.67 | 100% |  | 100% | 3.67 |  | 3.659 | 1 | 3.659 | 100% | 3.659 | -0.011 | -0.011
[6 empty] | R15-N/07 | 4.49 | 1 | 1 | 4.49 | 1523 | 128 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Curve with flat panel | R15-N/08 | 4.8 | 1 | 1 | 4.8 | 2514,2714 | 284 | 1 | 4.8 | 100% |  | 100% | 4.8 | WIR 1207 | 4.49 |  | 0 |  | 0 | -4.8 | -4.8
[5 empty] | 900mm | R15-N/09 | [7 empty] | - |  |  |  | 0 | refer to SA - 900mm(Qty) worksheet |  |  | - |  | -
[5 empty] | 900mm | R15-N/10 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R15-N/11 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R15-N/12 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | Curve with flat panel | R15-N/13 | 4.8 | 1 | 1 | 4.8 | 2511,2714 | 284 | 1 | 4.8 | 100% |  | 100% | 4.8 | WIR 1207 | 4.49 |  | 0 |  | 0 | -4.8 | -4.8
[6 empty] | R15-N/14 | 4.49 | 1 | 1 | 4.49 | 1255 | 064 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | R15-N/15 | 4.49 | 1 | 1 | 4.49 | 1255 | 064 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | R15-N/16 | 4.49 | 1 | 1 | 4.49 | 1255,1967 | 064,179 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R15-N/17 | 4.49 | 1 | 1 | 4.49 | 1248 | 061 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Corner panel | R15-N/18 | 4.98 | 1 | 1 | 4.98 | 1505,1525 | 127,128 | 1 | 4.98 | 100% |  | 100% | 4.98 |  | 5.005 | 1 | 5.005 | 100% | 5.005 | 0.025 | 0.025
[6 empty] | R15-N/19 | 4.35 | 1 | 1 | 4.35 | 1255 | 064 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[6 empty] | R15-N/20 | 4.35 | 1 | 1 | 4.35 | 1248 | 061 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[6 empty] | R15-N/21 | 4.35 | 1 | 1 | 4.35 | 1248 | 061 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[6 empty] | R15-N/22 | 4.35 | 1 | 1 | 4.35 | 1255 | 064 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[5 empty] | Corner panel | R15-N/23 | 5.17 | 1 | 1 | 5.17 | 1505,1553 | 127,132 | 1 | 5.17 | 100% |  | 100% | 5.17 |  | 5.195 | 1 | 5.195 | 100% | 5.195 | 0.025 | 0.025
[6 empty] | R15-N/24 | 4.49 | 1 | 1 | 4.49 | 1255 | 064 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R15-N/25 | 4.49 | 1 | 1 | 4.49 | 1261 | 066 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R15-N/26 | 4.49 | 1 | 1 | 4.49 | 1248 | 061 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R15-N/27 | 4.49 | 1 | 1 | 4.49 | 1255 | 064 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R15-N/28 | 4.49 | 1 | 1 | 4.49 | 1255 | 064 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R15-N/29 | 4.49 | 1 | 1 | 4.49 | 1252 | 062 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R15-N/30 | 4.49 | 1 | 1 | 4.49 | 1252 | 062 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R15-N/31 | 4.49 | 1 | 1 | 4.49 | 1252 | 062 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R15-N/32 | 4.49 | 1 | 1 | 4.49 | 1252 | 062 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R15-N/33 | 2.59 | 1 | 1 | 2.59 | 1553 | 132 | 1 | 2.59 | 100% |  | 100% | 2.59 |  | 2.583 | 1 | 2.583 | 100% | 2.583 | -0.007 | -0.007
[5 empty] | Curve Panel | R15-N/34 | 4.24 | 1 | 1 | 4.24 | 1486 | 123 | 1 | 4.24 | 100% |  | 100% | 4.24 |  | 4.938 | 1 | 4.938 | 100% | 4.938 | 0.698 | 0.698
[9 empty] | TOTAL | 127.3 |  |  | TOTAL | 127.3 | TOTAL |  |  | 127.3 |  |  | TOTAL | 119.53 | TOTAL | 110.55
11 | EWS-101 | 600 | 16 | 1 |  | R16-N/01 | 2.8 | 1 | 1 | 2.8 | 1553, 1577 | 132 | 1 | 2.8 | 100% |  | 100% | 2.8 |  | 2.793 | 1 | 2.793 | 100% | 2.793 | -0.007 | -0.007
[6 empty] | R16-N/02 | 3.03 | 1 | 1 | 3.03 | 1553,1695 | 132,155 | 1 | 3.03 | 100% |  | 100% | 3.03 |  | 3.049 | 1 | 3.049 | 100% | 3.049 | 0.019 | 0.019
[6 empty] | R16-N/03 | 4.49 | 1 | 1 | 4.49 | 1272 | 070 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R16-N/04 | 4.49 | 1 | 1 | 4.49 | 1272 | 070 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R16-N/05 | 4.49 | 1 | 1 | 4.49 | 1272 | 070 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R16-N/06 | 4.49 | 1 | 1 | 4.49 | 1272 | 070 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R16-N/07 | 4.49 | 1 | 1 | 4.49 | 1272 | 070 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R16-N/08 | 4.49 | 1 | 1 | 4.49 | 1272 | 070 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R16-N/09 | 4.49 | 1 | 1 | 4.49 | 1272 | 070 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R16-N/10 | 4.49 | 1 | 1 | 4.49 | 1272 | 070 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R16-N/11 | 4.49 | 1 | 1 | 4.49 | 1553 | 132 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R16-N/12 | 3.51 | 1 | 1 | 3.51 | 1567 | 133 | 1 | 3.51 | 100% |  | 100% | 3.51 |  | 3.5 | 1 | 3.5 | 100% | 3.5 | -0.01 | -0.01
[5 empty] | Curve with C Panel | R16-N/13 | 3.25 | 1 | 1 | 3.25 | 1473,1481 | 118,121 | 1 | 3.25 | 100% |  | 100% | 3.25 |  | 3.24 | 1 | 3.24 | 100% | 3.24 | -0.01 | -0.01
[5 empty] | Curve with C Panel | R16-N/14 | 4.02 | 1 | 1 | 4.02 | 1473,1496 | 118 | 1 | 4.02 | 100% |  | 100% | 4.02 |  | 4.005 | 1 | 4.005 | 100% | 4.005 | -0.015 | -0.015
[6 empty] | R16-N/15 | 3.81 | 1 | 1 | 3.81 |  |  | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.008 | -0.008
[6 empty] | R16-N/16 | 3.81 | 1 | 1 | 3.81 |  |  | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.008 | -0.008
[6 empty] | R16-N/17 | 3.81 | 1 | 1 | 3.81 |  |  | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.008 | -0.008
[6 empty] | R16-N/18 | 3.81 | 1 | 1 | 3.81 |  |  | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.008 | -0.008
[5 empty] | Curve with C Panel | R16-N/19 | 4.02 | 1 | 1 | 4.02 | 1450,1465 | 110,114 | 1 | 4.02 | 100% |  | 100% | 4.02 |  | 4.005 | 1 | 4.005 | 100% | 4.005 | -0.015 | -0.015
[5 empty] | Curve with C Panel | R16-N/20 | 3.25 | 1 | 1 | 3.25 | 1450,1465 | 110,114 | 1 | 3.25 | 100% |  | 100% | 3.25 |  | 3.24 | 1 | 3.24 | 100% | 3.24 | -0.01 | -0.01
[6 empty] | R16-N/21 | 3.51 | 1 | 1 | 3.51 | 1444 | 108 | 1 | 3.51 | 100% |  | 100% | 3.51 |  | 3.5 | 1 | 3.5 | 100% | 3.5 | -0.01 | -0.01
[6 empty] | R16-N/22 | 3.51 | 1 | 1 | 3.51 | 1444 | 108 | 1 | 3.51 | 100% |  | 100% | 3.51 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0.98 | 0.98
[5 empty] | Curve with flat panel | R16-N/23 | 4.8 | 1 | 1 | 4.8 | 2516,2531,2716 | 254,284 | 1 | 4.8 | 100% |  | 100% | 4.8 | WIR 1206 | 4.49 |  | 0 |  | 0 | -4.8 | -4.8
[5 empty] | 900mm | R16-N/24 | [7 empty] | - |  |  |  | 0 | refer to SA - 900mm(Qty) worksheet |  |  | - |  | -
[5 empty] | 900mm | R16-N/25 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R16-N/26 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R16-N/27 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | Curve with flat panel | R16-N/28 | 4.8 | 1 | 1 | 4.8 | 2520,2716 | 284 | 1 | 4.8 | 100% |  | 100% | 4.8 | WIR 1206 | 4.49 | 1 | 4.49 |  | 0 | -0.31 | -4.8
[6 empty] | R16-N/29 | 4.49 | 1 | 1 | 4.49 | 066 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | R16-N/30 | 4.49 | 1 | 1 | 4.49 | 066 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | R16-N/31 | 2.87 | 1 | 1 | 2.87 | 1471,1529 | 116129 | 1 | 2.87 | 100% |  | 100% | 2.87 |  | 2.895 | 1 | 2.895 | 100% | 2.895 | 0.025 | 0.025
[9 empty] | TOTAL | 108 |  |  | TOTAL | 108 | TOTAL |  |  | 108 |  |  | TOTAL | 103.805 | TOTAL | 90.335
12 | EWS-101 | 600 | 17 | 1 |  | R17-N/01 | 2.06 | 1 | 1 | 2.06 | 1444 | 108 | 1 | 2.06 | 100% |  | 100% | 2.06 |  | 2.05 | 1 | 2.05 | 100% | 2.05 | -0.01 | -0.01
[6 empty] | R17-N/02 | 3.81 | 1 | 1 | 3.81 |  |  | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.008 | -0.008
[6 empty] | R17-N/03 | 3.81 | 1 | 1 | 3.81 |  |  | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.008 | -0.008
[5 empty] | Curve with C Panel | R17-N/04 | 4.15 | 1 | 1 | 4.15 | 1453,1471 | 111,116 | 1 | 4.15 | 100% |  | 100% | 4.15 |  | 4.138 | 1 | 4.138 | 100% | 4.138 | -0.012 | -0.012
[5 empty] | Curve with C Panel | R17-N/05 | 2.96 | 1 | 1 | 2.96 | 1453,1471 | 111,116 | 1 | 2.96 | 100% |  | 100% | 2.96 |  | 4.138 | 1 | 4.138 | 100% | 4.138 | 1.178 | 1.178
[6 empty] | R17-N/06 | 3.67 | 1 | 1 | 3.67 | 1450 | 110 | 1 | 3.67 | 100% |  | 100% | 3.67 |  | 3.659 | 1 | 3.659 | 100% | 3.659 | -0.011 | -0.011
[6 empty] | R17-N/07 | 4.49 | 1 | 1 | 4.49 | 1445 | 109 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Curve with flat panel | R17-N/08 | 4.8 | 1 | 1 | 4.8 | 2524,2563 | 254,259 | 1 | 4.8 | 100% |  | 100% | 4.8 | WIR 1205 | 4.49 |  | 0 |  | 0 | -4.8 | -4.8
[5 empty] | 900mm | R17-N/09 | [7 empty] | - |  |  |  | 0 | refer to SA - 900mm(Qty) worksheet |  |  | - |  | -
[5 empty] | 900mm | R17-N/10 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R17-N/11 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R17-N/12 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | Curve with flat panel | R17-N/13 | 4.8 | 1 | 1 | 4.8 | 2531,2531,2601 | 254 | 1 | 4.8 | 100% |  | 100% | 4.8 | WIR 1205 | 4.49 |  | 0 |  | 0 | -4.8 | -4.8
[6 empty] | R17-N/14 | 4.49 | 1 | 1 | 4.49 | 1304 | 079 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R17-N/15 | 4.49 | 1 | 1 | 4.49 | 1304 | 079 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R17-N/16 | 4.49 | 1 | 1 | 4.49 | 1302 | 078 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R17-N/17 | 4.49 | 1 | 1 | 4.49 | 1302 | 078 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Corner panel | R17-N/18 | 4.98 | 1 | 1 | 4.98 | 1502 | 127 | 1 | 4.98 | 100% |  | 100% | 4.98 |  | 5.005 | 1 | 5.005 | 100% | 5.005 | 0.025 | 0.025
[6 empty] | R17-N/19 | 4.35 | 1 | 1 | 4.35 | 1302 | 078 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[6 empty] | R17-N/20 | 4.35 | 1 | 1 | 4.35 | 1302 | 078 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[6 empty] | R17-N/21 | 4.35 | 1 | 1 | 4.35 | 1304 | 079 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[6 empty] | R17-N/22 | 4.35 | 1 | 1 | 4.35 | 1308 | 080 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[5 empty] | Corner panel | R17-N/23 | 5.17 | 1 | 1 | 5.17 | 1502 | 127 | 1 | 5.17 | 100% |  | 100% | 5.17 |  | 5.195 | 1 | 5.195 | 100% | 5.195 | 0.025 | 0.025
[6 empty] | R17-N/24 | 4.49 | 1 | 1 | 4.49 | 1292 | 076 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R17-N/25 | 4.49 | 1 | 1 | 4.49 | 1282 | 075 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R17-N/26 | 4.49 | 1 | 1 | 4.49 | 1282 | 075 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R17-N/27 | 4.49 | 1 | 1 | 4.49 | 1282 | 075 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R17-N/28 | 4.49 | 1 | 1 | 4.49 | 1282 | 075 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R17-N/29 | 4.49 | 1 | 1 | 4.49 | 1281 | 074 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R17-N/30 | 4.49 | 1 | 1 | 4.49 | 1281 | 074 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R17-N/31 | 4.49 | 1 | 1 | 4.49 | 1281 | 074 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R17-N/32 | 4.49 | 1 | 1 | 4.49 | 1281 | 074 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R17-N/33 | 2.59 | 1 | 1 | 2.59 | 1577 |  | 1 | 2.59 | 100% |  | 100% | 2.59 |  | 2.583 | 1 | 2.583 | 100% | 2.583 | -0.007 | -0.007
[5 empty] | Curve Panel | R17-N/34 | 4.24 | 1 | 1 | 4.24 | 1592 | 140 | 1 | 4.24 | 100% |  | 100% | 4.24 |  | 4.938 | 1 | 4.938 | 100% | 4.938 | 0.698 | 0.698
[9 empty] | TOTAL | 127.3 |  |  | TOTAL | 127.3 | TOTAL |  |  | 127.3 |  |  | TOTAL | 119.53 | TOTAL | 119.53
13 | EWS-101 | 600 | 18 | 1 | Corner panel | R18-N/01 | 2.87 | 1 | 1 | 2.87 | 1725,1734,1977 | 160,180 | 1 | 2.87 | 100% |  | 100% | 2.87 | WIR 1064 R4 | 3.495 | 0.66667 | 2.33 | 0.66667 | 2.33 | -0.54 | -0.54
[6 empty] | R18-N/02 | 4.49 | 1 | 1 | 4.49 | 2022 | 186 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R18-N/03 | 4.49 | 1 | 1 | 4.49 | 2022 | 186 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R18-N/04 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 |  |  |  | 0 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 4.49
[6 empty] | R18-N/05 | 4.49 | 1 | 1 | 4.49 | 2601 |  | 1 | 4.49 |  |  |  | 0 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 4.49
[6 empty] | R18-N/06 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | R18-N/07 | 4.49 | 1 | 1 | 4.49 | 2601 |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | R18-N/08 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | R18-N/09 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | R18-N/10 | 4.49 | 1 | 1 | 4.49 | 1706 |  | 1 | 4.49 | 100% |  | 100% | 4.49 | WIR 0585 R2 | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R18-N/11 | 4.49 | 1 | 1 | 4.49 | 1706 |  | 1 | 4.49 | 100% |  | 100% | 4.49 | WIR 0585 R2 | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R18-N/12 | 4.49 | 1 | 1 | 4.49 | 1499,1697,1699 | 126156 | 1 | 4.49 | 100% |  | 100% | 4.49 | WIR 0585 R2 | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R18-N/13 | 4.49 | 1 | 1 | 4.49 | 1697 | 156 | 1 | 4.49 | 100% |  | 100% | 4.49 | WIR 0585 R2 | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R18-N/14 | 4.49 | 1 | 1 | 4.49 | 1630,1660 | 146'150 | 1 | 4.49 | 100% |  | 100% | 4.49 | WIR 0547 R2 | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R18-N/15 | 4.49 | 1 | 1 | 4.49 | 1630,1660 | 146,150 | 1 | 4.49 | 100% |  | 100% | 4.49 | WIR 0547 R2 | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R18-N/16 | 4.49 | 1 | 1 | 4.49 | 1630,1672,1706 | 146,152 | 1 | 4.49 | 100% |  | 100% | 4.49 | WIR 0547 R2 | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R18-N/17 | 4.49 | 1 | 1 | 4.49 | 1499,1652 | 126,149 | 1 | 4.49 | 100% |  | 100% | 4.49 | WIR 0547 R2 | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R18-N/18 | 4.49 | 1 | 1 | 4.49 | 1639,1645 | 147,148 | 1 | 4.49 | 100% |  | 100% | 4.49 | WIR 0547 R2 | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Curve with C Panel | R18-N/19 | 4.44 | 1 | 1 | 4.44 | 2060,2183 | 191,210 | 0.83 | 3.6852 |  |  |  | 0 | Scaffolding not handover | 4.226 |  | 0 |  | 0 | -3.6852 | 0
[5 empty] | Curve with C Panel | R18-N/20 | 4.41 | 1 | 1 | 4.41 | 1652,2060,2183 | 149,191,210 | 0.83 | 3.6603 |  |  |  | 0 | Scaffolding not handover | 4.201 |  | 0 |  | 0 | -3.6603 | 0
[6 empty] | R18-N/21 | 3.81 | 1 | 1 | 3.81 | 1563 | 133 | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.008 | -0.008
[6 empty] | R18-N/22 | 3.81 | 1 | 1 | 3.81 | 1630,1818 | 146,165 | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.008 | -0.008
[6 empty] | R18-N/23 | 3.81 | 1 | 1 | 3.81 | 156716301818 | 133146165 | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.008 | -0.008
[6 empty] | R18-N/24 | 3.91 | 1 | 1 | 3.91 | 156716301818 | 133146165 | 1 | 3.91 | 100% |  | 100% | 3.91 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.108 | -0.108
[5 empty] | Curve with C Panel | R18-N/25 | 4.41 | 1 | 1 | 4.41 | 2096,2108,2183 | 199,201,210 | 1 | 4.41 | 100% |  | 100% | 4.41 |  | 4.201 |  | 0 |  | 0 | -4.41 | -4.41
[5 empty] | Curve with C Panel | R18-N/26 | 4.44 | 1 | 1 | 4.44 | 2108,2183 | 201,210 | 1 | 4.44 | 100% |  | 100% | 4.44 | WIR 0755 R3 | 4.226 |  | 0 |  | 0 | -4.44 | -4.44
[6 empty] | R18-N/27 | 4.49 | 1 | 1 | 4.49 | 1639,1659 | 147,150 | 1 | 4.49 | 100% |  | 100% | 4.49 | WIR 0755 R3 | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R18-N/28 | 4.49 | 1 | 1 | 4.49 | 1637,1672 | 147,152 | 1 | 4.49 | 100% |  | 100% | 4.49 | WIR 0546 R2 | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R18-N/29 | 4.49 | 1 | 1 | 4.49 | 1634,1637 | 146,147 | 1 | 4.49 | 100% |  | 100% | 4.49 | WIR 0546 R2 | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R18-N/30 | 4.49 | 1 | 1 | 4.49 | 1634,1637 | 146,147 | 1 | 4.49 | 100% |  | 100% | 4.49 | WIR 0546 R2 | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R18-N/31 | 4.49 | 1 | 1 | 4.49 | 1634,1639 | 146,147 | 1 | 4.49 | 100% |  | 100% | 4.49 | WIR 0546 R2 | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R18-N/32 | 4.49 | 1 | 1 | 4.49 | 1697 | 156 | 1 | 4.49 | 100% |  | 100% | 4.49 | WIR 0546 R2 | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R18-N/33 | 4.49 | 1 | 1 | 4.49 | 1697,1699 | 156 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R18-N/34 | 4.49 | 1 | 1 | 4.49 | 1645,1699 | 148 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R18-N/35 | 4.49 | 1 | 1 | 4.49 | 1645 | 148 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R18-N/36 | 4.49 | 1 | 1 | 4.49 | 1648 | 148 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R18-N/37 | 4.49 | 1 | 1 | 4.49 | 1648 | 148 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R18-N/38 | 4.49 | 1 | 1 | 4.49 | 1648 | 148 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R18-N/39 | 4.49 | 1 | 1 | 4.49 | 1648 | 148 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R18-N/40 | 4.49 | 1 | 1 | 4.49 | 1648 | 148 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R18-N/41 | 4.49 | 1 | 1 | 4.49 | 1645 | 148 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R18-N/42 | 4.49 | 1 | 1 | 4.49 | 1645 | 148 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R18-N/43 | 4.49 | 1 | 1 | 4.49 | 1645 | 148 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Corner panel | R18-N/44 | 3.02 | 1 | 1 | 3.02 | 1672,1678,1725 | 152,153,160 | 1 | 3.02 | 100% |  | 100% | 3.02 | WIR 1064 R4 | 3.04 | 1 | 3.04 | 100% | 3.04 | 0.02 | 0.02
[6 empty] | R18-N/45 | 2.8 | 1 | 1 | 2.8 | 1725,1881,1977 | 160,167,170 | 1 | 2.8 | 100% |  | 100% | 2.8 | WIR 1064 R4 | 2.792 | 1 | 2.792 | 100% | 2.792 | -0.008 | -0.008
[9 empty] | TOTAL | 194.39 |  |  | TOTAL | 174.9255 | TOTAL |  |  | 158.6 |  |  | TOTAL | 149.09 | TOTAL | 149.09
14 | EWS-101 | 600 | 19 | 1 |  | R19-N/01 | 1.7 | 1 | 1 | 1.7 | 1630 | 146 | 1 | 1.7 | 100% |  | 100% | 1.7 |  | 1.69 | 1 | 1.69 | 100% | 1.69 | -0.01 | -0.01
[6 empty] | R19-N/02 | 4.99 | 1 | 1 | 4.99 | 1720 | 159 | 1 | 4.99 | 100% |  | 100% | 4.99 |  | 4.99 | 1 | 4.99 | 100% | 4.99 | 0 | 0
[6 empty] | R19-N/03 | 4.49 | 1 | 1 | 4.49 | 1288 | 076 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R19-N/04 | 4.49 | 1 | 1 | 4.49 | 1288 | 076 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R19-N/05 | 4.49 | 1 | 1 | 4.49 | 1288 | 076 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R19-N/06 | 4.49 | 1 | 1 | 4.49 | 1288 | 076 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R19-N/07 | 4.49 | 1 | 1 | 4.49 | 1292 | 076 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R19-N/08 | 4.49 | 1 | 1 | 4.49 | 1292 | 076 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R19-N/09 | 4.49 | 1 | 1 | 4.49 | 1292 | 076 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Curve with flat panel | R19-N/10 | 4.8 | 1 | 1 | 4.8 | 2534,2563,2714 | 256,259,284 | 1 | 4.8 | 100% |  | 100% | 4.8 | WIR 1204 | 4.49 |  | 0 |  | 0 | -4.8 | -4.8
[5 empty] | 900mm | R19-N/11 | [7 empty] | - |  |  |  | 0 | refer to SA - 900mm(Qty) worksheet |  |  | - |  | -
[5 empty] | 900mm | R19-N/12 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R19-N/13 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R19-N/14 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | Curve with flat panel | R19-N/15 | 4.8 | 1 | 1 | 4.8 | 2601,2714 | 284 | 1 | 4.8 | 100% |  | 100% | 4.8 | WIR 1204 | 4.49 |  | 0 |  | 0 | -4.8 | -4.8
[6 empty] | R19-N/16 | 4.49 | 1 | 1 | 4.49 | 1288 | 076 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | R19-N/17 | 4.49 | 1 | 1 | 4.49 | 1288 | 076 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R19-N/18 | 4.49 | 1 | 1 | 4.49 | 1288 | 076 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R19-N/19 | 4.49 | 1 | 1 | 4.49 | 1288,2062 | 076,193 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R19-N/20 | 1.83 | 1 | 1 | 1.83 |  |  | 1 | 1.83 | 100% |  | 100% | 1.83 |  | 1.8 | 1 | 1.8 | 100% | 1.8 | -0.03 | -0.03
[6 empty] | R19-N/21 | 3.15 | 1 | 1 | 3.15 |  |  | 1 | 3.15 | 100% |  | 100% | 3.15 |  | 3.14 | 1 | 3.14 | 100% | 3.14 | -0.01 | -0.01
[6 empty] | R19-N/22 | 4.35 | 1 | 1 | 4.35 | 1279 | 073 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[6 empty] | R19-N/23 | 4.35 | 1 | 1 | 4.35 | 1279 | 073 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[6 empty] | R19-N/24 | 4.35 | 1 | 1 | 4.35 | 1279 | 073 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[6 empty] | R19-N/25 | 4.35 | 1 | 1 | 4.35 | 1294 | 077 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[6 empty] | R19-N/26 | 3.34 | 1 | 1 | 3.34 | 1540 | 130 | 1 | 3.34 | 100% |  | 100% | 3.34 |  | 3.33 | 1 | 3.33 | 100% | 3.33 | -0.01 | -0.01
[6 empty] | R19-N/27 | 1.83 | 1 | 1 | 1.83 | 1540 | 130 | 1 | 1.83 | 100% |  | 100% | 1.83 |  | 1.8 | 1 | 1.8 | 100% | 1.8 | -0.03 | -0.03
[6 empty] | R19-N/28 | 4.49 | 1 | 1 | 4.49 | 1271 | 070 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R19-N/29 | 4.49 | 1 | 1 | 4.49 | 1271 | 070 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R19-N/30 | 4.49 | 1 | 1 | 4.49 | 1271 | 070 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R19-N/31 | 4.49 | 1 | 1 | 4.49 | 1271 | 070 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R19-N/32 | 4.49 | 1 | 1 | 4.49 | 1280 | 073 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R19-N/33 | 4.49 | 1 | 1 | 4.49 | 1280 | 073 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R19-N/34 | 4.49 | 1 | 1 | 4.49 | 1280 | 073 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R19-N/35 | 4.49 | 1 | 1 | 4.49 | 1280 | 073 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R19-N/36 | 4.49 | 1 | 1 | 4.49 | 1280 | 073 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R19-N/37 | 4.49 | 1 | 1 | 4.49 | 1280 | 073 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R19-N/38 | 4.49 | 1 | 1 | 4.49 | 1280 | 073 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R19-N/39 | 4.49 | 1 | 1 | 4.49 | 1280 | 073 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R19-N/40 | 4.49 | 1 | 1 | 4.49 | 1279 | 073 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R19-N/41 | 4.49 | 1 | 1 | 4.49 | 1279 | 073 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R19-N/42 | 4.49 | 1 | 1 | 4.49 | 1279 | 073 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R19-N/43 | 4.49 | 1 | 1 | 4.49 | 1279 | 073 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R19-N/44 | 4.49 | 1 | 1 | 4.49 | 1279 | 073 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R19-N/45 | 4.49 | 1 | 1 | 4.49 | 1630 | 146 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.99 | 1 | 4.99 | 100% | 4.99 | 0.5 | 0.5
[6 empty] | R19-N/46 | 1.7 | 1 | 1 | 1.7 | 1540 | 130 | 1 | 1.7 | 100% |  | 100% | 1.7 |  | 1.69 | 1 | 1.69 | 100% | 1.69 | -0.01 | -0.01
[9 empty] | TOTAL | 175.75 |  |  | TOTAL | 175.75 | TOTAL |  |  | 175.75 |  |  | TOTAL | 166.51 | TOTAL | 162.02
15 | EWS-101 | 600 | 20 | 1 |  | R20-N/01 | 2.87 | 1 | 1 | 2.87 | 1787,1853 | 164,168 | 1 | 2.87 | 100% |  | 100% | 2.87 |  | 2.355 | 0.66667 | 1.57 | 66.67% | 1.57 | -1.3 | -1.3
[6 empty] | R20-N/02 | 4.49 | 1 | 1 | 4.49 | 1458 | 1112 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.99 | 1 | 4.99 |  | 0 | 0.5 | -4.49
[6 empty] | R20-N/03 | 4.49 | 1 | 1 | 4.49 | 1469 | 115 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[5 empty] | Curve with flat panel | R20-N/04 | 4.8 | 1 | 1 | 4.8 | 2535,2549 | 256,258 | 1 | 4.8 | 100% |  | 100% | 4.8 | WIR 1203 | 4.49 |  | 0 |  | 0 | -4.8 | -4.8
[5 empty] | 900mm | [8 empty] | - |  |  |  | 0 | refer to SA - 900mm(Qty) worksheet |  |  | - |  | -
[5 empty] | 900mm | [8 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | [8 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | [8 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | Curve with flat panel | R20-N/09 | 4.8 | 1 | 1 | 4.8 | 2534,2563 | 256,259 | 1 | 4.8 | 100% |  | 100% | 4.8 | WIR 1203 | 4.49 |  | 0 |  | 0 | -4.8 | -4.8
[6 empty] | R20-N/10 | 4.49 | 1 | 1 | 4.49 | 1465 | 114 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R20-N/11 | 4.49 | 1 | 1 | 4.49 | 1469 | 115 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R20-N/12 | 4.49 | 1 | 1 | 4.49 | 1469 | 115 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R20-N/13 | 4.49 | 1 | 1 | 4.49 | 1472 | 171 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R20-N/14 | 4.49 | 1 | 1 | 4.49 | 1472 | 171 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R20-N/15 | 4.49 | 1 | 1 | 4.49 | 1472 | 171 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R20-N/16 | 4.49 | 1 | 1 | 4.49 | 1472,1481 | 171,121 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R20-N/17 | 4.49 | 1 | 1 | 4.49 | 1474 | 118 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R20-N/18 | 4.49 | 1 | 1 | 4.49 | 1474 | 118 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[5 empty] | Curve with C Panel | R20-N/19 | 4.44 | 1 | 1 | 4.44 | 1659,1765,2055 | 150,162,191 | 1 | 4.44 |  |  |  | 0 | WIR 1226 | 4.226 | 0.66667 | 2.8173 | 66.67% | 2.8173 | -1.6227 | 2.8173
[5 empty] | Curve with C Panel | R20-N/20 | 4.2 | 1 | 1 | 4.2 | 1558,2055 | 133,191 | 1 | 4.2 |  |  |  | 0 | WIR 1226 | 4.201 | 1 | 4.201 |  | 0 | 0.001 | 0
[6 empty] | R20-N/21 | 4.42 | 1 | 1 | 4.42 | 1872 | 170 | 1 | 4.42 | 67% |  | 67% | 2.9614 |  | 3.802 | 1 | 3.802 | 50% | 1.901 | -0.618 | -1.0604
[6 empty] | R20-N/22 | 3.81 | 1 | 1 | 3.81 | 1872 | 170 | 1 | 3.81 | 67% |  | 67% | 2.5527 |  | 3.803 | 1 | 3.803 | 50% | 1.9015 | -0.007 | -0.6512
[6 empty] | R20-N/23 | 3.81 | 1 | 1 | 3.81 | 1872 | 170 | 1 | 3.81 | 67% |  | 67% | 2.5527 |  | 3.802 | 1 | 3.802 | 50% | 1.901 | -0.008 | -0.6517
[6 empty] | R20-N/24 | 3.81 | 1 | 1 | 3.81 | 1872 | 170 | 1 | 3.81 | 67% |  | 67% | 2.5527 |  | 3.803 | 1 | 3.803 | 50% | 1.9015 | -0.007 | -0.6512
[5 empty] | Curve with C Panel | R20-N/25 | 4.42 | 1 | 1 | 4.42 | 2072,2180 | 194,209 | 1 | 4.42 |  |  |  | 0 | WIR 0754 R2 | 4.201 |  | 0 |  | 0 | -4.42 | 0
[5 empty] | Curve with C Panel | R20-N/26 | 4.44 | 1 | 1 | 4.44 | 2017,2180 | 185,209 | 1 | 4.44 |  |  |  | 0 | WIR 0754 R2 | 4.226 | 1 | 4.226 | 100% | 4.226 | -0.214 | 4.226
[6 empty] | R20-N/27 | 4.49 | 1 | 1 | 4.49 | 1478 | 119 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 1.8 | 1 | 1.8 | 100% | 1.8 | -2.69 | -1.2083
[6 empty] | R20-N/28 | 4.49 | 1 | 1 | 4.49 | 1478 | 119 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R20-N/29 | 4.49 | 1 | 1 | 4.49 | 1480 | 119 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R20-N/30 | 4.49 | 1 | 1 | 4.49 | 1480 | 119 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R20-N/31 | 4.49 | 1 | 1 | 4.49 | 1481 | 121 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R20-N/32 | 4.49 | 1 | 1 | 4.49 | 1482 | 122 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R20-N/33 | 4.49 | 1 | 1 | 4.49 | 1492 | 124 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R20-N/34 | 4.49 | 1 | 1 | 4.49 | 1492 | 124 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R20-N/35 | 4.49 | 1 | 1 | 4.49 | 1503 | 127 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R20-N/36 | 4.49 | 1 | 1 | 4.49 | 1505 | 127 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R20-N/37 | 4.49 | 1 | 1 | 4.49 | 1505 | 127 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R20-N/38 | 4.49 | 1 | 1 | 4.49 | 1505 | 127 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R20-N/39 | 4.49 | 1 | 1 | 4.49 | 1543 | 130 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R20-N/40 | 4.49 | 1 | 1 | 4.49 | 1543 | 130 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R20-N/41 | 4.49 | 1 | 1 | 4.49 | 1543 | 130 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R20-N/42 | 4.49 | 1 | 1 | 4.49 | 1543 | 130 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R20-N/43 | 4.49 | 1 | 1 | 4.49 | 1542 | 130 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R20-N/44 | 3.03 | 1 | 1 | 3.03 |  |  | 1 | 3.03 | 67% |  | 67% | 2.0301 |  | 3.04 | 1 | 3.04 | 66.67% | 2.0267 | 0.01 | -0.0034333
[6 empty] | R20-N/45 | 2.8 | 1 | 1 | 2.8 | 1553,1971 | 132,180 | 1 | 2.8 | 67% |  | 67% | 1.876 |  | 2.792 | 1 | 2.792 | 66.67% | 1.8613 | -0.008 | -0.014667
[9 empty] | TOTAL | 177.37 |  |  | TOTAL | 177.37 |  |  |  | 127.5267 |  |  | TOTAL | 152.8963 | TOTAL | 129.6663
16 | EWS-101 | 600 | 21 | 1 |  | R21-N/01 | 1.7 | 1 | 1 | 1.7 | 1771 | 162 | 1 | 1.7 | 67% |  | 67% | 1.139 |  | 1.69 | 1 | 1.69 | 100% | 1.69 | -0.01 | 0.551
[6 empty] | R21-N/02 | 4.99 | 1 | 1 | 4.99 | 1645 | 148 | 1 | 4.99 | 67% |  | 67% | 3.3433 |  | 4.99 | 1 | 4.99 | 100% | 4.99 | 0 | 1.6467
[6 empty] | R21-N/03 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R21-N/04 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R21-N/05 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R21-N/06 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R21-N/07 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R21-N/08 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R21-N/09 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[5 empty] | Curve with flat panel | R21-N/10 | 4.8 | 1 | 1 | 4.8 | 2560,2563 | 257,259 | 1 | 4.8 | 67% |  | 67% | 3.216 | WIR 1202 | 4.49 |  | 0 |  | 0 | -4.8 | -3.216
[5 empty] | 900mm | R21-N/11 | [7 empty] | - |  |  |  | 0 | refer to SA - 900mm(Qty) worksheet |  |  | - |  | -
[5 empty] | 900mm | R21-N/12 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R21-N/13 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R21-N/14 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | Curve with flat panel | R21-N/15 | 4.8 | 1 | 1 | 4.8 | 2560 | 257 | 1 | 4.8 | 67% |  | 67% | 3.216 | WIR 1202 | 4.49 |  | 0 |  | 0 | -4.8 | -3.216
[6 empty] | R21-N/16 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -3.0083
[6 empty] | R21-N/17 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -3.0083
[6 empty] | R21-N/18 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R21-N/19 | 4.49 | 1 | 1 | 4.49 | 1963,2055 | 179 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.226 | 1 | 4.226 | 100% | 4.226 | -0.264 | 1.2177
[6 empty] | R21-N/20 | 1.81 | 1 | 1 | 1.81 | 1967,2055 | 179 | 1 | 1.81 | 67% |  | 67% | 1.2127 |  | 1.8 | 1 | 1.8 | 100% | 1.8 | -0.01 | 0.5873
[6 empty] | R21-N/21 | 3.15 | 1 | 1 | 3.15 |  |  | 1 | 3.15 | 67% |  | 67% | 2.1105 |  | 3.14 | 1 | 3.14 | 100% | 3.14 | -0.01 | 1.0295
[6 empty] | R21-N/22 | 4.35 | 1 | 1 | 4.35 |  |  | 1 | 4.35 | 67% |  | 67% | 2.9145 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | 1.4255
[6 empty] | R21-N/23 | 4.35 | 1 | 1 | 4.35 |  |  | 1 | 4.35 | 67% |  | 67% | 2.9145 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | 1.4255
[6 empty] | R21-N/24 | 4.35 | 1 | 1 | 4.35 |  |  | 1 | 4.35 | 67% |  | 67% | 2.9145 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | 1.4255
[6 empty] | R21-N/25 | 4.35 | 1 | 1 | 4.35 |  |  | 1 | 4.35 | 67% |  | 67% | 2.9145 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | 1.4255
[6 empty] | R21-N/26 | 3.34 | 1 | 1 | 3.34 |  |  | 1 | 3.34 | 67% |  | 67% | 2.2378 |  | 3.33 | 1 | 3.33 | 100% | 3.33 | -0.01 | 1.0922
[6 empty] | R21-N/27 | 1.81 | 1 | 1 | 1.81 |  |  | 1 | 1.81 | 67% |  | 67% | 1.2127 |  | 1.8 | 1 | 1.8 | 100% | 1.8 | -0.01 | 0.5873
[6 empty] | R21-N/28 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R21-N/29 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R21-N/30 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R21-N/31 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R21-N/32 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R21-N/33 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R21-N/34 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R21-N/35 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R21-N/36 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 50% | 2.245 | 0 | -0.7633
[6 empty] | R21-N/37 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 50% | 2.245 | 0 | -0.7633
[6 empty] | R21-N/38 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R21-N/39 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R21-N/40 | 4.49 | 1 | 1 | 4.49 | 1381 | 096 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R21-N/41 | 4.49 | 1 | 1 | 4.49 | 1381 | 096 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R21-N/42 | 4.49 | 1 | 1 | 4.49 | 1381 | 096 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R21-N/43 | 4.49 | 1 | 1 | 4.49 | 1390 | 098 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R21-N/44 | 4.49 | 1 | 1 | 4.49 | 1381 | 096 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R21-N/45 | 4.99 | 1 | 1 | 4.99 | 1645 | 148 | 1 | 4.99 | 67% |  | 67% | 3.3433 |  | 4.99 | 1 | 4.99 | 100% | 4.99 | 0 | 1.6467
[6 empty] | R21-N/46 | 1.69 | 1 | 1 | 1.69 | 1771 | 162 | 1 | 1.69 | 67% |  | 67% | 1.1323 |  | 1.69 | 1 | 1.69 | 100% | 1.69 | 0 | 0.5577
[9 empty] | TOTAL | 176.2 |  |  | TOTAL | 176.2 |  |  |  | 118.054 |  |  | TOTAL | 166.246 | TOTAL | 152.776
17 | EWS-101 | 600 | 22 | 1 |  | R22-N/01 | 2.87 | 1 | 1 | 2.87 | 1806,2099 | 165,199 | 1 | 2.87 | 67% |  | 67% | 1.9229 | WIR 1065 | 1.69 | 1 | 1.69 | 66.67% | 1.1267 | -1.18 | -0.79623
[6 empty] | R22-N/02 | 4.49 | 1 | 1 | 4.49 | 1526 | 129 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.99 | 1 | 4.99 |  | 0 | 0.5 | -3.0083
[6 empty] | R22-N/03 | 4.49 | 1 | 1 | 4.49 | 1503 | 127 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -3.0083
[5 empty] | Curve with flat panel | R22-N/04 | 4.8 | 1 | 1 | 4.8 | 2548,2699 | 257,282 | 1 | 4.8 | 67% |  | 67% | 3.216 | WIR 1201 | 4.49 |  | 0 |  | 0 | -4.8 | -3.216
[5 empty] | 900mm | R22-N/05 | [7 empty] | - |  |  |  | 0 | refer to SA - 900mm(Qty) worksheet |  |  | - |  | -
[5 empty] | 900mm | R22-N/06 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R22-N/07 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R22-N/08 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | Curve with flat panel | R22-N/09 | 4.8 | 1 | 1 | 4.8 | 2548,2699 | 257,282 | 1 | 4.8 | 67% |  | 67% | 3.216 | WIR 1201 | 4.49 |  | 0 |  | 0 | -4.8 | -3.216
[6 empty] | R22-N/10 | 4.49 | 1 | 1 | 4.49 | 1525 | 128 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R22-N/11 | 4.49 | 1 | 1 | 4.49 | 1544 | 131 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R22-N/12 | 4.49 | 1 | 1 | 4.49 |  | 129 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R22-N/13 | 4.49 | 1 | 1 | 4.49 | 1544 | 131 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R22-N/14 | 4.49 | 1 | 1 | 4.49 | 1544 | 131 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R22-N/15 | 4.49 | 1 | 1 | 4.49 | 1544 | 131 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R22-N/16 | 4.49 | 1 | 1 | 4.49 | 1544 | 131 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R22-N/17 | 4.49 | 1 | 1 | 4.49 | 1544 | 131 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R22-N/18 | 4.49 | 1 | 1 | 4.49 | 1544 | 131 | 1 | 4.49 | 67% |  | 67% | 3.0083 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 1.4817
[6 empty] | R22-N/19 | 4.44 | 1 | 1 | 4.44 | 1544 | 131 | 1 | 4.44 | 67% |  | 67% | 2.9748 | WIR 1149 | 4.226 | 1 | 4.226 | 66.67% | 2.8173 | -0.214 | -0.15747
[6 empty] | R22-N/20 | 4.42 | 1 | 1 | 4.42 | 1547, 1553 | 131,132 | 1 | 4.42 | 67% |  | 67% | 2.9614 | WIR 1149 | 1.8 | 1 | 1.8 |  | 0 | -2.62 | -2.9614
[6 empty] | R22-N/21 | 3.81 | 1 | 1 | 3.81 | 1547,1902 | 131,174 | 1 | 3.81 | 67% |  | 67% | 2.5527 | WIR 1150 | 3.14 |  | 0 |  | 0 | -3.81 | -2.5527
[6 empty] | R22-N/22 | 3.81 | 1 | 1 | 3.81 | 1902 | 174 | 1 | 3.81 | 67% |  | 67% | 2.5527 | WIR 1150 | 4.34 |  | 0 |  | 0 | -3.81 | -2.5527
[6 empty] | R22-N/23 | 3.81 | 1 | 1 | 3.81 | 1902 | 174 | 1 | 3.81 | 67% |  | 67% | 2.5527 | WIR 1150 | 4.34 |  | 0 |  | 0 | -3.81 | -2.5527
[6 empty] | R22-N/24 | 3.81 | 1 | 1 | 3.81 | 1558 | 133 | 1 | 3.81 | 67% |  | 67% | 2.5527 | WIR 1150 | 4.34 | 1 | 4.34 |  | 0 | 0.53 | -2.5527
[6 empty] | R22-N/25 | 4.42 | 1 | 1 | 4.42 | 2082,2183 | 196,210 | 1 | 4.42 | 0% |  | 0% | 0 | WIR 0753 R3 | 4.34 |  | 0 |  | 0 | -4.42 | 0
[6 empty] | R22-N/26 | 4.44 | 1 | 1 | 4.44 | 2017,2183 | 185,210 | 1 | 4.44 | 0% |  | 0% | 0 | WIR 0753 R3 | 3.33 |  | 0 |  | 0 | -4.44 | 0
[6 empty] | R22-N/27 | 4.49 | 1 | 1 | 4.49 | 1547 | 131 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 1.8 | 1 | 1.8 | 100% | 1.8 | -2.69 | -2.69
[6 empty] | R22-N/28 | 4.49 | 1 | 1 | 4.49 | 1547 | 131 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R22-N/29 | 4.49 | 1 | 1 | 4.49 | 1547 | 131 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R22-N/30 | 4.49 | 1 | 1 | 4.49 | 1556 | 133 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R22-N/31 | 4.49 | 1 | 1 | 4.49 | 1556 | 133 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R22-N/32 | 4.49 | 1 | 1 | 4.49 | 1556 | 133 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R22-N/33 | 4.49 | 1 | 1 | 4.49 | 1556 | 133 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R22-N/34 | 4.49 | 1 | 1 | 4.49 | 1556 | 133 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R22-N/35 | 4.49 | 1 | 1 | 4.49 | 1558 | 133 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R22-N/36 | 4.49 | 1 | 1 | 4.49 | 1558 | 133 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R22-N/37 | 4.49 | 1 | 1 | 4.49 | 1558 | 133 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R22-N/38 | 4.49 | 1 | 1 | 4.49 | 1558 | 133 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R22-N/39 | 4.49 | 1 | 1 | 4.49 | 1558 | 133 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R22-N/40 | 4.49 | 1 | 1 | 4.49 | 1558 | 133 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R22-N/41 | 4.49 | 1 | 1 | 4.49 | 1558 | 133 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R22-N/42 | 4.49 | 1 | 1 | 4.49 | 1558 | 133 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R22-N/43 | 4.49 | 1 | 1 | 4.49 | 1558 | 133 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R22-N/44 | 3.03 | 1 | 1 | 3.03 | 1553,1639 | 132,147 | 1 | 3.03 | 100% |  | 100% | 3.03 | WIR 1065 | 4.49 | 1 | 4.49 | 100% | 4.49 | 1.46 | 1.46
[6 empty] | R22-N/45 | 2.8 | 1 | 1 | 2.8 | 1553,2062 | 193132 | 1 | 2.8 | 100% |  | 100% | 2.8 | WIR 1065 | 4.99 | 1 | 4.99 | 100% | 4.99 | 2.19 | 2.19
[9 empty] | TOTAL | 176.98 |  |  | TOTAL | 176.98 | TOTAL |  |  | 139.7532 |  |  | TOTAL | 145.066 | TOTAL | 127.474
18 | EWS-101 | 600 | 23 | 1 |  | R23-N/01 | 4.49 | 1 | 1 | 4.49 | 1423 | 106 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.99 | 1 | 4.99 |  | 0 | 0.5 | -4.49
[6 empty] | R23-N/02 | 4.49 | 1 | 1 | 4.49 | 1428 | 106 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.99 | 1 | 4.99 |  | 0 | 0.5 | -4.49
[6 empty] | R23-N/03 | 4.49 | 1 | 1 | 4.49 | 1428 | 106 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.99 | 1 | 4.99 | 100% | 4.99 | 0.5 | 0.5
[6 empty] | R23-N/04 | 4.49 | 1 | 1 | 4.49 | 1437 | 107 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.99 | 1 | 4.99 | 100% | 4.99 | 0.5 | 0.5
[6 empty] | R23-N/05 | 4.49 | 1 | 1 | 4.49 | 1437 | 107 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.99 | 1 | 4.99 | 100% | 4.99 | 0.5 | 0.5
[6 empty] | R23-N/06 | 4.49 | 1 | 1 | 4.49 | 1437 | 107 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.99 | 1 | 4.99 | 100% | 4.99 | 0.5 | 0.5
[6 empty] | R23-N/07 | 4.49 | 1 | 1 | 4.49 | 1437 | 107 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.99 | 1 | 4.99 | 100% | 4.99 | 0.5 | 0.5
[6 empty] | R23-N/08 | 4.49 | 1 | 1 | 4.49 | 1445 | 109 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.99 | 1 | 4.99 | 100% | 4.99 | 0.5 | 0.5
[6 empty] | R23-N/09 | 4.49 | 1 | 1 | 4.49 | 1444 | 108 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.99 | 1 | 4.99 | 100% | 4.99 | 0.5 | 0.5
[6 empty] | R23-N/10 | 4.49 | 1 | 1 | 4.49 | 1458 | 1112 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.99 | 1 | 4.99 | 100% | 4.99 | 0.5 | 0.5
[6 empty] | R23-N/11 | 4.49 | 1 | 1 | 4.49 | 1445 | 109 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.99 | 1 | 4.99 | 100% | 4.99 | 0.5 | 0.5
[6 empty] | R23-N/12 | 4.49 | 1 | 1 | 4.49 | 1458 | 1112 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.99 | 1 | 4.99 | 100% | 4.99 | 0.5 | 0.5
[6 empty] | R23-N/13 | 4.49 | 1 | 1 | 4.49 | 1450 | 110 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.99 | 1 | 4.99 | 100% | 4.99 | 0.5 | 0.5
[6 empty] | R23-N/14 | 4.49 | 1 | 1 | 4.49 | 1453 | 111 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.99 | 1 | 4.99 | 100% | 4.99 | 0.5 | 0.5
[6 empty] | R23-N/15 | 4.49 | 1 | 1 | 4.49 | 1453 | 111 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.99 | 1 | 4.99 | 100% | 4.99 | 0.5 | 0.5
[6 empty] | R23-N/16 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.99 | 1 | 4.99 | 100% | 4.99 | 0.5 | 0.5
[6 empty] | R23-N/17 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.99 | 1 | 4.99 | 100% | 4.99 | 0.5 | 0.5
[6 empty] | R23-N/18 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.99 | 1 | 4.99 | 100% | 4.99 | 0.5 | 0.5
[6 empty] | R23-N/19 | 4.49 | 1 | 1 | 4.49 | 1465 | 114 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.99 | 1 | 4.99 | 100% | 4.99 | 0.5 | 0.5
[5 empty] | Curve with flat panel | R23-N/20 | 4.49 | 1 | 1 | 4.49 | 2579 | 261 | 1 | 4.49 | 100% |  | 100% | 4.49 | WIR 1182 | 4.485 |  | 0 |  | 0 | -4.49 | -4.49
[5 empty] | Curve with flat panel | R23-N/21 | 4.99 | 1 | 1 | 4.99 | 2938 | 302 | 1 | 4.99 | 100% |  | 100% | 4.99 | WIR 1243 | 4.985 |  | 0 |  | 0 | -4.99 | -4.99
[6 empty] | R23-N/22 | 19.896 | 1 | 1 | 19.896 | 1463, 2938 | 113, 302 | 1 | 19.896 | 100% | 0% | 100% | 19.896 | WIR 0753 R3, WIR 1243 |  |  | 0 |  | 0 | -19.896 | -19.896
[5 empty] | Curve with flat panel | R23-N/23 | 5.02 | 1 | 1 | 5.02 | 1463,3064 | 113 | 1 | 5.02 | 100% |  | 100% | 5.02 | WIR 1243 | 4.558 |  | 0 |  | 0 | -5.02 | -5.02
[5 empty] | Curve with flat panel | R23-N/24 | 4.49 | 1 | 1 | 4.49 | 2579,3064 | 261 | 1 | 4.49 | 100% |  | 100% | 4.49 | WIR 1181 | 4.485 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R23-N/25 | 4.49 | 1 | 1 | 4.49 | 1465 | 114 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.99 | 1 | 4.99 | 100% | 4.99 | 0.5 | 0.5
[6 empty] | R23-N/26 | 4.49 | 1 | 1 | 4.49 | 1469 | 115 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.99 | 1 | 4.99 | 100% | 4.99 | 0.5 | 0.5
[6 empty] | R23-N/27 | 4.49 | 1 | 1 | 4.49 | 1469 | 115 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.99 | 1 | 4.99 | 100% | 4.99 | 0.5 | 0.5
[6 empty] | R23-N/28 | 4.49 | 1 | 1 | 4.49 | 1472 | 171 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.99 | 1 | 4.99 | 100% | 4.99 | 0.5 | 0.5
[6 empty] | R23-N/29 | 4.49 | 1 | 1 | 4.49 | 1472 | 171 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.99 | 1 | 4.99 | 100% | 4.99 | 0.5 | 0.5
[6 empty] | R23-N/30 | 4.49 | 1 | 1 | 4.49 | 1472 | 171 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R23-N/31 | 4.49 | 1 | 1 | 4.49 | 1472 | 171 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R23-N/32 | 4.49 | 1 | 1 | 4.49 | 1474 | 118 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R23-N/33 | 4.49 | 1 | 1 | 4.49 | 1480 | 119 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R23-N/34 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | R23-N/35 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | R23-N/36 | 4.49 | 1 | 1 | 4.49 | 2579 | 261 |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | R23-N/37 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | R23-N/38 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | R23-N/39 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | R23-N/40 | 4.49 | 1 | 1 | 4.49 | 1478 | 119 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R23-N/41 | 4.49 | 1 | 1 | 4.49 | 1529 | 129 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R23-N/42 | 4.49 | 1 | 1 | 4.49 | 1482 | 122 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R23-N/43 | 4.49 | 1 | 1 | 4.49 | 1480 | 119 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R23-N/44 | 4.99 | 1 | 1 | 4.99 | 1577,1963 | 179 | 1 | 4.99 | 100% |  | 100% | 4.99 |  | 5.605 | 1 | 5.605 | 100% | 5.605 | 0.615 | 0.615
[6 empty] | R23-N/45 | 4.35 | 1 | 1 | 4.35 | 1481 | 121 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[6 empty] | R23-N/46 | 4.35 | 1 | 1 | 4.35 | 1496 |  | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[6 empty] | R23-N/47 | 4.35 | 1 | 1 | 4.35 | 1482 | 122 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[6 empty] | R23-N/48 | 4.35 | 1 | 1 | 4.35 | 1492 | 124 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[6 empty] | R23-N/49 | 5.18 | 1 | 1 | 5.18 | 1577 | 135 | 1 | 5.18 | 100% |  | 100% | 5.18 |  | 5.8 |  | 0 |  | 0 | -5.18 | -5.18
[6 empty] | R23-N/50 |  | 1 | 1 | [5 empty] | 100% |  | 100% | 0 | WIR 1243
[6 empty] | R23-N/51 |  | 1 | 1 | [5 empty] | 100% |  | 100% | 0 | WIR 1243
[6 empty] | R23-N/51 |  | 1 | 1 | [5 empty] | 100% |  | 100% | 0 | WIR 1243
[6 empty] | R23-N/53 |  | 1 | 1 | [5 empty] | 100% |  | 100% | 0 | WIR 1243
[9 empty] | TOTAL | 237.076 |  |  | TOTAL | 210.136 | TOTAL |  |  | 210.136 |  |  | TOTAL | 169.665 | TOTAL | 159.685
19 | EWS-101 | 600 | 24 | 1 |  | R24-N/01 | 4.49 | 1 | 1 | 4.49 | 1444 | 108 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R24-N/02 | 4.49 | 1 | 1 | 4.49 | 1444 | 108 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R24-N/03 | 4.49 | 1 | 1 | 4.49 | 1444 | 108 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R24-N/04 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R24-N/05 | 4.49 | 1 | 1 | 4.49 | 1450 | 110 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R24-N/06 | 4.49 | 1 | 1 | 4.49 | 1445 | 109 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R24-N/07 | 4.49 | 1 | 1 | 4.49 | 1453 | 111 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R24-N/08 | 4.49 | 1 | 1 | 4.49 | 1453 | 111 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R24-N/09 | 4.49 | 1 | 1 | 4.49 | 1453 | 111 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R24-N/10 | 4.49 | 1 | 1 | 4.49 | 1473 | 118 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R24-N/11 | 3.25 | 1 | 1 | 3.25 | 1473 | 118 | 1 | 3.25 | 100% |  | 100% | 3.25 |  | 3.238 | 1 | 3.238 | 100% | 3.238 | -0.012 | -0.012
[6 empty] | R24-N/12 | 3.25 | 1 | 1 | 3.25 | 1465 | 114 | 1 | 3.25 | 100% |  | 100% | 3.25 |  | 3.238 | 1 | 3.238 | 100% | 3.238 | -0.012 | -0.012
[5 empty] | Curve Panel | R24-N/13 | 3.27 | 1 | 1 | 3.27 | 1567 | 133 | 1 | 3.27 | 100% |  | 100% | 3.27 |  | 3.258 | 1 | 3.258 | 100% | 3.258 | -0.012 | -0.012
[5 empty] | Curve Panel | R24-N/14 | 4.09 | 1 | 1 | 4.09 | 1553,1625 | 132,145 | 1 | 4.09 | 100% |  | 100% | 4.09 |  | 4.078 | 1 | 4.078 | 100% | 4.078 | -0.012 | -0.012
[6 empty] | R24-N/15 | 3.81 | 1 | 1 | 3.81 | 1465 | 114 | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.008 | -0.008
[6 empty] | R24-N/16 | 3.81 | 1 | 1 | 3.81 | 1469 | 115 | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.008 | -0.008
[6 empty] | R24-N/17 | 3.81 | 1 | 1 | 3.81 | 1469 | 115 | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.008 | -0.008
[6 empty] | R24-N/18 | 3.91 | 1 | 1 | 3.91 | 1474 | 118 | 1 | 3.91 | 100% |  | 100% | 3.91 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.108 | -0.108
[6 empty] | R24-N/19 | 3.81 | 1 | 1 | 3.81 | 1558 | 133 | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.008 | -0.008
[5 empty] | Corner Panel | R24-N/20 | 2.19 | 1 | 1 | 2.19 | 1553 | 132 | 1 | 2.19 | 100% |  | 100% | 2.19 |  | 2.814 | 1 | 2.814 | 100% | 2.814 | 0.624 | 0.624
[6 empty] | R24-N/21 | 4.49 | 1 | 1 | 4.49 | 1463 | 113 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R24-N/22 | 4.49 | 1 | 1 | 4.49 | 1465 | 114 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R24-N/23 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | R24-N/24 | 4.49 | 1 | 1 | 4.49 | 30943101 | 322323 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | extended slab | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R24-N/25 | 4.49 | 1 | 1 | 4.49 | 3143 | 331 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | extended slab | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R24-N/26 | 4.49 | 1 | 1 | 4.49 | 3143 | 331 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | extended slab | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R24-N/27 | 4.49 | 1 | 1 | 4.49 | 3143 | 331 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | extended slab | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R24-N/28 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | R24-N/29 | 4.49 | 1 | 1 | 4.49 | 1469 | 115 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | R24-N/30 | 4.49 | 1 | 1 | 4.49 | 1474 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | R24-N/31 | 3.14 | 1 | 1 | 3.14 | 1478 | 119 | 1 | 3.14 | 100% |  | 100% | 3.14 |  | 3.313 | 1 | 3.313 | 100% | 3.313 | 0.173 | 0.173
[6 empty] | R24-N/32 | 3.32 | 1 | 1 | 3.32 | 1563 | 133 | 1 | 3.32 | 100% |  | 100% | 3.32 |  | 3.312 | 1 | 3.312 | 100% | 3.312 | -0.008 | -0.008
[5 empty] | Curve Panel | R24-N/33 | 3.27 | 1 | 1 | 3.27 | 1563 | 133 | 1 | 3.27 | 100% |  | 100% | 3.27 |  | 3.256 | 1 | 3.256 | 100% | 3.256 | -0.014 | -0.014
[5 empty] | Curve Panel | R24-N/34 | 3.61 | 1 | 1 | 3.61 | 1563 | 133 | 1 | 3.61 | 100% |  | 100% | 3.61 |  | 3.256 | 1 | 3.256 | 100% | 3.256 | -0.354 | -0.354
[6 empty] | R24-N/35 | 4.01 | 1 | 1 | 4.01 | 1553 | 132 | 1 | 4.01 | 100% |  | 100% | 4.01 |  | 3.995 | 1 | 3.995 | 100% | 3.995 | -0.015 | -0.015
[6 empty] | R24-N/36 | 4.35 | 1 | 1 | 4.35 | 1478 | 119 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[6 empty] | R24-N/37 | 4.35 | 1 | 1 | 4.35 | 1481 | 121 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[6 empty] | R24-N/38 | 4.35 | 1 | 1 | 4.35 | 1482 | 122 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[5 empty] | Corner Panel | R24-N/39 | 5.17 | 1 | 1 | 5.17 | 1553 | 132 | 1 | 5.17 | 100% |  | 100% | 5.17 |  | 5.8 | 1 | 5.8 | 100% | 5.8 | 0.63 | 0.63
[9 empty] | TOTAL | 160.57 |  |  | TOTAL | 151.59 | TOTAL |  |  | 151.59 |  |  | TOTAL | 134.448 | TOTAL | 125.468
20 | EWS-101 | 600 | 25 | 1 |  | R25-N/01 | 4.49 | 1 | 1 | 4.49 | 1982,2073 | 184,195 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R25-N/02 | 4.49 | 1 | 1 | 4.49 | 1982,2419 | 184237 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R25-N/03 | 4.49 | 1 | 1 | 4.49 | 1523 | 128 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R25-N/04 | 4.49 | 1 | 1 | 4.49 | 1496 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R25-N/05 | 4.49 | 1 | 1 | 4.49 | 1496 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R25-N/06 | 4.49 | 1 | 1 | 4.49 | 1492 | 124 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R25-N/07 | 4.49 | 1 | 1 | 4.49 | 1523 | 128 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R25-N/08 | 4.49 | 1 | 1 | 4.49 | 1526 | 129 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R25-N/09 | 4.49 | 1 | 1 | 4.49 | 1523 | 128 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R25-N/10 | 4.49 | 1 | 1 | 4.49 | 1525 | 128 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R25-N/11 | 3.25 | 1 | 1 | 3.25 | 1529 | 129 | 1 | 3.25 | 100% |  | 100% | 3.25 |  | 3.238 | 1 | 3.238 | 100% | 3.238 | -0.012 | -0.012
[6 empty] | R25-N/12 | 3.25 | 1 | 1 | 3.25 | 1525 | 128 | 1 | 3.25 | 100% |  | 100% | 3.25 |  | 3.238 | 1 | 3.238 | 100% | 3.238 | -0.012 | -0.012
[5 empty] | Curve Panel | R25-N/13 | 3.27 | 1 | 1 | 3.27 | 1583 | 139 | 1 | 3.27 | 100% |  | 100% | 3.27 |  | 3.258 | 1 | 3.258 | 100% | 3.258 | -0.012 | -0.012
[5 empty] | Curve Panel | R25-N/14 | 4.09 | 1 | 1 | 4.09 | 1583 | 139 | 1 | 4.09 | 100% |  | 100% | 4.09 |  | 4.078 | 1 | 4.078 | 100% | 4.078 | -0.012 | -0.012
[6 empty] | R25-N/15 | 3.81 | 1 | 1 | 3.81 | 1503 | 127 | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.008 | -0.008
[6 empty] | R25-N/16 | 3.81 | 1 | 1 | 3.81 | 1583 | 139 | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.008 | -0.008
[6 empty] | R25-N/17 | 3.81 | 1 | 1 | 3.81 | 1502 | 127 | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.008 | -0.008
[6 empty] | R25-N/18 | 3.81 | 1 | 1 | 3.81 | 1583 | 139 | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.008 | -0.008
[6 empty] | R25-N/19 | 3.81 | 1 | 1 | 3.81 | 1720 | 159 | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.008 | -0.008
[5 empty] | Corner Panel | R25-N/20 | 2.19 | 1 | 1 | 2.19 | 1720 | 159 | 1 | 2.19 | 100% |  | 100% | 2.19 |  | 2.814 | 1 | 2.814 | 100% | 2.814 | 0.624 | 0.624
[6 empty] | R25-N/21 | 4.49 | 1 | 1 | 4.49 | 1526 | 129 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R25-N/22 | 4.49 | 1 | 1 | 4.49 | 1503 | 127 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R25-N/23 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | R25-N/24 | 4.49 | 1 | 1 | 4.49 | 3094 | 322 | 1 | 4.49 | 30% | 0% | 30% | 1.347 | extended slab | 4.49 |  | 0 |  | 0 | -4.49 | -1.347
[6 empty] | R25-N/25 | 4.49 | 1 | 1 | 4.49 | 1706 |  | 1 | 4.49 | 30% | 70% | 100% | 4.49 | extended slab | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R25-N/26 | 4.49 | 1 | 1 | 4.49 | 1706 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 | extended slab | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R25-N/27 | 4.49 | 1 | 1 | 4.49 |  |  | 0.3 | 1.347 | 100% | 0% | 100% | 4.49 | extended slab | 4.49 |  | 0 |  | 0 | -1.347 | -4.49
[6 empty] | R25-N/28 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | R25-N/29 | 4.49 | 1 | 1 | 4.49 | 2062 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R25-N/30 | 4.49 | 1 | 1 | 4.49 | 1526 | 129 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | R25-N/31 | 3.32 | 1 | 1 | 3.32 | 1982,2419 | 184237 | 1 | 3.32 | 100% |  | 100% | 3.32 |  | 3.313 |  | 0 |  | 0 | -3.32 | -3.32
[6 empty] | R25-N/32 | 3.32 | 1 | 1 | 3.32 | 1980,2072 | 181,194 | 1 | 3.32 | 100% |  | 100% | 3.32 |  | 3.312 |  | 0 |  | 0 | -3.32 | -3.32
[5 empty] | Curve Panel | R25-N/33 | 3.27 | 1 | 1 | 3.27 | 2073 | 195 | 1 | 3.27 | 100% |  | 100% | 3.27 |  | 3.256 |  | 0 |  | 0 | -3.27 | -3.27
[5 empty] | Curve Panel | R25-N/34 | 3.27 | 1 | 1 | 3.27 | 2085,2108 | 197,201 | 1 | 3.27 | 100% |  | 100% | 3.27 |  | 3.256 |  | 0 |  | 0 | -3.27 | -3.27
[6 empty] | R25-N/35 | 4.01 | 1 | 1 | 4.01 | 1980,2073 | 181,195 | 1 | 4.01 | 100% |  | 100% | 4.01 |  | 3.995 |  | 0 |  | 0 | -4.01 | -4.01
[6 empty] | R25-N/36 | 4.35 | 1 | 1 | 4.35 | 1980,2062 | 181,193 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 |  | 0 |  | 0 | -4.35 | -4.35
[6 empty] | R25-N/37 | 4.35 | 1 | 1 | 4.35 | 1771 | 162 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[6 empty] | R25-N/38 | 4.35 | 1 | 1 | 4.35 | 1982,2072 | 184,194 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 |  | 0 |  | 0 | -4.35 | -4.35
[5 empty] | Corner Panel | R25-N/39 | 5.17 | 1 | 1 | 5.17 | 2103,2062 | 193,200 | 1 | 5.17 | 100% |  | 100% | 5.17 |  | 5.8 |  | 0 |  | 0 | -5.17 | -5.17
[9 empty] | TOTAL | 160.31 |  |  | TOTAL | 148.187 | TOTAL |  |  | 148.187 |  |  | TOTAL | 89.366 | TOTAL | 84.876
21 | EWS-101 | 600 | 26 | 1 |  | R26-N/01 | 2.04 | 1 | 1 | 2.04 | 1765 | 162 | 1 | 2.04 | 100% |  | 100% | 2.04 |  | 2.355 | 1 | 2.355 | 100% | 2.355 | 0.315 | 0.315
[6 empty] | R26-N/02 | 4.84 | 1 | 1 | 4.84 | 1765 | 162 | 1 | 4.84 | 100% |  | 100% | 4.84 |  | 5.15 | 1 | 5.15 | 100% | 5.15 | 0.31 | 0.31
[6 empty] | R26-N/03 | 4.49 | 1 | 1 | 4.49 | 1564 | 133 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R26-N/04 | 4.49 | 1 | 1 | 4.49 | 1564 | 133 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R26-N/05 | 4.49 | 1 | 1 | 4.49 | 1564 | 133 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R26-N/06 | 4.49 | 1 | 1 | 4.49 | 1564 | 133 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R26-N/07 | 4.49 | 1 | 1 | 4.49 | 1564 | 133 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R26-N/08 | 3.25 | 1 | 1 | 3.25 | 1564 | 133 | 1 | 3.25 | 100% |  | 100% | 3.25 |  | 3.238 | 1 | 3.238 | 100% | 3.238 | -0.012 | -0.012
[6 empty] | R26-N/09 | 3.25 | 1 | 1 | 3.25 | 1564 | 133 | 1 | 3.25 | 100% |  | 100% | 3.25 |  | 3.237 | 1 | 3.237 | 100% | 3.237 | -0.013 | -0.013
[5 empty] | Curve Panel | R26-N/10 | 3.27 | 1 | 1 | 3.27 | 1787 | 164 | 1 | 3.27 | 100% |  | 100% | 3.27 |  | 3.258 | 1 | 3.258 | 100% | 3.258 | -0.012 | -0.012
[5 empty] | Curve Panel | R26-N/11 | 4.09 | 1 | 1 | 4.09 | 1659,1787 | 150,164 | 1 | 4.09 | 100% |  | 100% | 4.09 |  | 4.078 | 1 | 4.078 | 100% | 4.078 | -0.012 | -0.012
[6 empty] | R26-N/12 | 3.81 | 1 | 1 | 3.81 | 1564 | 133 | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.803 | 1 | 3.803 | 100% | 3.803 | -0.007 | -0.007
[6 empty] | R26-N/13 | 3.81 | 1 | 1 | 3.81 | 1564 | 133 | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.008 | -0.008
[6 empty] | R26-N/14 | 3.81 | 1 | 1 | 3.81 | 1564 | 133 | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 4.078 | 1 | 4.078 | 100% | 4.078 | 0.268 | 0.268
[6 empty] | R26-N/15 | 3.81 | 1 | 1 | 3.81 | 1787 | 164 | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.008 | -0.008
[6 empty] | R26-N/16 | 3.81 | 1 | 1 | 3.81 | 1787 | 164 | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 | 100% | 3.802 | -0.008 | -0.008
[6 empty] | R26-N/17 | 2.19 | 1 | 1 | 2.19 | 1540 | 130 | 1 | 2.19 | 100% |  | 100% | 2.19 |  | 2.799 | 1 | 2.799 | 100% | 2.799 | 0.609 | 0.609
[6 empty] | R26-N/18 | 4.49 | 1 | 1 | 4.49 | 1564 | 133 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R26-N/19 | 4.49 | 1 | 1 | 4.49 | 1564'2614 | 133 | 1 | 4.49 |  |  |  | 0 | WIR 628 | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 4.49
[5 empty] | Curve with flat panel | R26-N/20 | 4.8 | 1 | 1 | 4.8 | 2566,2570 | 259 | 1 | 4.8 |  |  |  | 0 |  | 4.49 |  | 0 |  | 0 | -4.8 | 0
[5 empty] | 900mm | R26-N/21 | [7 empty] | - |  |  |  | 0 | refer to SA - 900mm(Qty) worksheet |  |  | - |  | -
[5 empty] | 900mm | R26-N/22 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R26-N/23 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R26-N/24 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | Curve with flat panel | R26-N/25 | 4.8 | 1 | 1 | 4.8 | 2566,2570 | 259 | 1 | 4.8 | 100% |  | 100% | 4.8 |  | 4.49 |  | 0 |  | 0 | -4.8 | -4.8
[6 empty] | R26-N/26 | 2.57 | 1 | 1 | 2.57 | 2446 | 240 | 1 | 2.57 | 100% |  | 100% | 2.57 | WIR 1180 | 3.2 |  | 0 |  | 0 | -2.57 | -2.57
[9 empty] | TOTAL | 85.58 |  |  | TOTAL | 85.58 | TOTAL |  |  | 76.29 |  |  | TOTAL | 74.832 | TOTAL | 74.832
22 | EWS-101 | 600 | 27 | 1 |  | R27-N/01 | 4.49 | 1 | 1 | 4.49 | 1971,2116 | 180,203 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R27-N/02 | 4.49 | 1 | 1 | 4.49 | 1971,2419 | 180 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R27-N/03 | 4.49 | 1 | 1 | 4.49 | 1540,1971 | 130,180 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R27-N/04 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | R27-N/05 | 4.49 | 1 | 1 | 4.49 | 1569 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R27-N/06 | 4.49 | 1 | 1 | 4.49 | 1569 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R27-N/07 | 4.49 | 1 | 1 | 4.49 | 1569 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R27-N/08 | 4.49 | 1 | 1 | 4.49 | 1569 |  | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R27-N/09 | 3.29 | 1 | 1 | 3.29 | 1581 | 139 | 1 | 3.29 | 100% |  | 100% | 3.29 |  | 3.277 | 1 | 3.277 | 100% | 3.277 | -0.013 | -0.013
[6 empty] | R27-N/10 | 3.29 | 1 | 1 | 3.29 | 1583 | 139 | 1 | 3.29 | 100% |  | 100% | 3.29 |  | 3.277 | 1 | 3.277 | 100% | 3.277 | -0.013 | -0.013
[5 empty] | Curve Panel | R27-N/11 | 3.27 | 1 | 1 | 3.27 | 1659,2589 | 150 | 1 | 3.27 | 100% |  | 100% | 3.27 |  | 3.258 | 1 | 3.258 |  | 0 | -0.012 | -3.27
[5 empty] | Curve Panel | R27-N/12 | 4.09 | 1 | 1 | 4.09 | 1902,2589,2721 | 174,287 | 1 | 4.09 | 100% |  | 100% | 4.09 |  | 4.079 |  | 0 |  | 0 | -4.09 | -4.09
[6 empty] | R27-N/13 | 3.81 | 1 | 1 | 3.81 | 1895 | 171 | 1 | 3.81 | 100% |  | 100% | 3.81 | WIR 1123 | 3.802 | 1 | 3.802 |  | 0 | -0.008 | -3.81
[6 empty] | R27-N/14 | 3.81 | 1 | 1 | 3.81 | 1895 | 171 | 1 | 3.81 | 100% |  | 100% | 3.81 | WIR 1123 | 3.802 | 1 | 3.802 |  | 0 | -0.008 | -3.81
[6 empty] | R27-N/15 | 3.81 | 1 | 1 | 3.81 | 1659 | 150 | 1 | 3.81 | 100% |  | 100% | 3.81 | WIR 1123 | 3.802 | 1 | 3.802 |  | 0 | -0.008 | -3.81
[6 empty] | R27-N/16 | 3.81 | 1 | 1 | 3.81 | 1895 | 171 | 1 | 3.81 | 100% |  | 100% | 3.81 | WIR 1123 | 3.802 | 1 | 3.802 |  | 0 | -0.008 | -3.81
[6 empty] | R27-N/17 | 3.81 | 1 | 1 | 3.81 | 1895 | 171 | 1 | 3.81 | 100% |  | 100% | 3.81 | WIR 1123 | 3.802 | 1 | 3.802 |  | 0 | -0.008 | -3.81
[6 empty] | R27-N/18 | 2.27 | 1 | 1 | 2.27 | 1902,2721 | 174287 | 1 | 2.27 | 100% |  | 100% | 2.27 | WIR 1123 | 2.891 | 1 | 2.891 |  | 0 | 0.621 | -2.27
[5 empty] | Curve with flat panel | R27-N/19 | 4.8 | 1 | 1 | 4.8 | 2568 | 259 | 1 | 4.8 | 100% |  | 100% | 4.8 |  | 4.49 |  | 0 |  | 0 | -4.8 | -4.8
[5 empty] | 900mm | R27-N/20 | [7 empty] | - |  |  |  | 0 | refer to SA - 900mm(Qty) worksheet |  |  | - |  | -
[5 empty] | 900mm | R27-N/21 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R27-N/22 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | 900mm | R27-N/23 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[5 empty] | Curve with flat panel | R27-N/24 | 4.8 | 1 | 1 | 4.8 | 2572 | 259 | 1 | 4.8 | 100% |  | 100% | 4.8 |  | 4.49 |  | 0 |  | 0 | -4.8 | -4.8
[6 empty] | R27-N/25 | 4.49 | 1 | 1 | 4.49 | 2006 | 184 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R27-N/26 | 4.49 | 1 | 1 | 4.49 | 2006 | 184 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R27-N/27 | 3.31 | 1 | 1 | 3.31 | 2006,2419 | 184 | 1 | 3.31 | 100% |  | 100% | 3.31 |  | 3.312 |  | 0 |  | 0 | -3.31 | -3.31
[6 empty] | R27-N/28 | 3.31 | 1 | 1 | 3.31 | 2006,2123 | 184,204 | 1 | 3.31 | 100% |  | 100% | 3.31 |  | 3.312 |  | 0 |  | 0 | -3.31 | -3.31
[5 empty] | Curve Panel | R27-N/29 | 3.27 | 1 | 1 | 3.27 | 2127,2128 | 204 | 1 | 3.27 | 100% |  | 100% | 3.27 |  | 3.256 |  | 0 |  | 0 | -3.27 | -3.27
[5 empty] | Curve Panel | R27-N/30 | 3.27 | 1 | 1 | 3.27 | 2123,2142,2938 | 204,205,302 | 1 | 3.27 | 100% |  | 100% | 3.27 |  | 3.256 |  | 0 |  | 0 | -3.27 | -3.27
[6 empty] | R27-N/31 | 4.01 | 1 | 1 | 4.01 | 2007,2136 | 184,205 | 1 | 4.01 | 100% |  | 100% | 4.01 |  | 3.995 |  | 0 |  | 0 | -4.01 | -4.01
[6 empty] | R27-N/32 | 4.35 | 1 | 1 | 4.35 | 2007,2143,2145,2147 | 184,205,206 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 |  | 0 |  | 0 | -4.35 | -4.35
[6 empty] | R27-N/33 | 4.35 | 1 | 1 | 4.35 | 2007,2116 | 184,203 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 |  | 0 |  | 0 | -4.35 | -4.35
[6 empty] | R27-N/34 | 4.35 | 1 | 1 | 4.35 | 2007,2123 | 184'204 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 |  | 0 |  | 0 | -4.35 | -4.35
[6 empty] | R27-N/35 | 3.68 | 1 | 1 | 3.68 | 2116,2151,2148 | 203,207 | 1 | 3.68 | 100% |  | 100% | 3.68 |  | 3.995 |  | 0 |  | 0 | -3.68 | -3.68
[6 empty] | R27-N/36 | 1.5 | 1 | 1 | 1.5 | 2116 | 203 | 1 | 1.5 | 100% |  | 100% | 1.5 |  | 1.8 |  | 0 |  | 0 | -1.5 | -1.5
[9 empty] | TOTAL | 125.16 |  |  | TOTAL | 125.16 | TOTAL |  |  | 125.16 |  |  | TOTAL | 54.163 | TOTAL | 24.514
23 | EWS-101 | 600 | 28 | 1 |  | R28-N/01 | 2.04 | 1 | 1 | 2.04 | 1922 | 176 | 1 | 2.04 | 100% |  | 100% | 2.04 | WIR 1179 | 2.355 | 1 | 2.355 |  | 0 | 0.315 | -2.04
[6 empty] | R28-N/02 | 4.84 | 1 | 1 | 4.84 | 1922 | 176 | 1 | 4.84 | 100% |  | 100% | 4.84 |  | 5.152 |  | 0 |  | 0 | -4.84 | -4.84
[6 empty] | R28-N/03 | 4.49 | 1 | 1 | 4.49 | 1725 | 160 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R28-N/04 | 4.49 | 1 | 1 | 4.49 | 1725 | 160 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R28-N/05 | 4.49 | 1 | 1 | 4.49 | 1725 | 160 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R28-N/06 | 3.29 | 1 | 1 | 3.29 | 1725 | 160 | 1 | 3.29 | 100% |  | 100% | 3.29 |  | 3.277 | 1 | 3.277 | 100% | 3.277 | -0.013 | -0.013
[6 empty] | R28-N/07 | 3.29 | 1 | 1 | 3.29 | 1725 | 160 | 1 | 3.29 | 100% |  | 100% | 3.29 |  | 3.277 | 1 | 3.277 | 100% | 3.277 | -0.013 | -0.013
[6 empty] | R28-N/08 | 3.27 | 1 | 1 | 3.27 | 2278,2704 | 224 | 1 | 3.27 | 100% |  | 100% | 3.27 |  | 3.258 |  | 0 |  | 0 | -3.27 | -3.27
[6 empty] | R28-N/09 | 4.09 | 1 | 1 | 4.09 | 2278,2704 | 224 | 1 | 4.09 | 100% |  | 100% | 4.09 |  | 4.079 |  | 0 |  | 0 | -4.09 | -4.09
[6 empty] | R28-N/10 | 3.81 | 1 | 1 | 3.81 | 2000 | 184 | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 |  | 0 |  | 0 | -3.81 | -3.81
[6 empty] | R28-N/11 | 3.81 | 1 | 1 | 3.81 | 2000 | 184 | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 |  | 0 |  | 0 | -3.81 | -3.81
[6 empty] | R28-N/12 | 3.81 | 1 | 1 | 3.81 | 2000 | 184 | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 |  | 0 |  | 0 | -3.81 | -3.81
[6 empty] | R28-N/13 | 3.81 | 1 | 1 | 3.81 | 2000 | 184 | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 |  | 0 |  | 0 | -3.81 | -3.81
[6 empty] | R28-N/14 | 3.81 | 1 | 1 | 3.81 | 1922 | 176 | 1 | 3.81 | 100% |  | 100% | 3.81 |  | 3.802 | 1 | 3.802 |  | 0 | -0.008 | -3.81
[6 empty] | R28-N/15 | 2.27 | 1 | 1 | 2.27 | 1922 | 176 | 1 | 2.27 | 100% |  | 100% | 2.27 |  | 2.893 | 1 | 2.893 |  | 0 | 0.623 | -2.27
[6 empty] | R28-N/16 | 4.8 | 1 | 1 | 4.8 | 2575 | 259 | 1 | 4.8 |  |  |  | 0 |  | 4.49 |  | 0 |  | 0 | -4.8 | 0
[6 empty] | R28-N/17 | [7 empty] | - |  |  |  | 0 | refer to SA - 900mm(Qty) worksheet |  |  | - |  | -
[6 empty] | R28-N/18 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[6 empty] | R28-N/19 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[6 empty] | R28-N/20 | [7 empty] | - |  |  |  | 0 |  |  |  | - |  | -
[6 empty] | R28-N/21 | 4.8 | 1 | 1 | 4.8 | 2575 | 259 | 1 | 4.8 |  |  |  | 0 |  | 4.49 |  | 0 |  | 0 | -4.8 | 0
[6 empty] | R28-N/22 | 3.63 | 1 | 1 | 3.63 | 1922 | 176 | 1 | 3.63 |  |  |  | 0 |  | 3.622 | 1 | 3.622 |  | 0 | -0.008 | 0
[6 empty] | R28-N/23 | 3.63 | 1 | 1 | 3.63 | 1942 | 176 | 1 | 3.63 |  |  |  | 0 |  | 3.622 | 1 | 3.622 |  | 0 | -0.008 | 0
[6 empty] | R28-N/24 | 3.02 | 1 | 1 | 3.02 | 2336 |  | 1 | 3.02 |  |  |  | 0 | WIR 1178 | 3.007 |  | 0 |  | 0 | -3.02 | 0
[6 empty] | R28-N/25 | 3.02 | 1 | 1 | 3.02 | 2334 |  | 1 | 3.02 |  |  |  | 0 | WIR 1178 | 3.007 |  | 0 |  | 0 | -3.02 | 0
[6 empty] | R28-N/26 | 4.01 | 1 | 1 | 4.01 | 1942 | 176 | 1 | 4.01 |  |  |  | 0 | WIR 1178 | 3.995 | 1 | 3.995 |  | 0 | -0.015 | 0
[6 empty] | R28-N/27 | 4.35 | 1 | 1 | 4.35 | 1942 | 176 | 1 | 4.35 |  |  |  | 0 | WIR 1178 | 4.34 | 1 | 4.34 |  | 0 | -0.01 | 0
[6 empty] | R28-N/28 | 1.85 | 1 | 1 | 1.85 | 2614 | 271 | 1 | 1.85 |  |  |  | 0 | WIR 1178 | 1.84 |  | 0 |  | 0 | -1.85 | 0
[9 empty] | TOTAL | 88.72 |  |  | TOTAL | 88.72 |  |  |  | 55.61 |  |  | TOTAL | 44.653 | TOTAL | 20.024
24 | EWS-101 | 600 | 29 | 1 |  | R29-N/01 | 4.49 | 1 | 1 | 4.49 | 1881,2205'2274,2321 | 167,170,215,224,228 | 1 | 4.49 |  |  |  | 0 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | 0
[6 empty] | R29-N/02 | 4.49 | 1 | 1 | 4.49 | 1863,2419 | 169 | 1 | 4.49 |  |  |  | 0 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | 0
[6 empty] | R29-N/03 | 4.49 | 1 | 1 | 4.49 | 1765 | 162 | 1 | 4.49 |  |  |  | 0 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | 0
[6 empty] | R29-N/04 | 4.49 | 1 | 1 | 4.49 | 1765 | 162 | 1 | 4.49 |  |  |  | 0 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | 0
[6 empty] | R29-N/05 | 4.49 | 1 | 1 | 4.49 | 1758 | 161 | 1 | 4.49 |  |  |  | 0 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 4.49
[6 empty] | R29-N/06 | 4.49 | 1 | 1 | 4.49 | 1758 | 161 | 1 | 4.49 |  |  |  | 0 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 4.49
[6 empty] | R29-N/07 | 4.49 | 1 | 1 | 4.49 | 1758 | 161 | 1 | 4.49 |  |  |  | 0 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 4.49
[6 empty] | R29-N/08 | 4.49 | 1 | 1 | 4.49 | 1765 | 162 | 1 | 4.49 |  |  |  | 0 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 4.49
[6 empty] | R29-N/09 | 3.28 | 1 | 1 | 3.28 | 1765 | 162 | 1 | 3.28 |  |  |  | 0 |  | 3.277 | 1 | 3.277 | 100% | 3.277 | -0.003 | 3.277
[6 empty] | R29-N/10 | 3.28 | 1 | 1 | 3.28 | 1795 | 164 | 1 | 3.28 |  |  |  | 0 |  | 3.277 | 1 | 3.277 | 100% | 3.277 | -0.003 | 3.277
[6 empty] | R29-N/11 | 3.28 | 1 | 1 | 3.28 | 2192,2276,2321,2589 | 213,224,228 | 1 | 3.28 |  |  |  | 0 |  | 3.258 |  | 0 |  | 0 | -3.28 | 0
[6 empty] | R29-N/12 | 4.09 | 1 | 1 | 4.09 | 2192,2194,2589 | 213 | 1 | 4.09 |  |  |  | 0 |  | 4.079 |  | 0 |  | 0 | -4.09 | 0
[6 empty] | R29-N/13 | 3.81 | 1 | 1 | 3.81 | 1887 | 170 | 1 | 3.81 |  |  |  | 0 |  | 3.802 | 1 | 3.802 |  | 0 | -0.008 | 0
[6 empty] | R29-N/14 | 3.81 | 1 | 1 | 3.81 | 1863 | 169 | 1 | 3.81 |  |  |  | 0 |  | 3.802 | 1 | 3.802 |  | 0 | -0.008 | 0
[6 empty] | R29-N/15 | 3.81 | 1 | 1 | 3.81 | 1863 | 169 | 1 | 3.81 |  |  |  | 0 |  | 3.802 | 1 | 3.802 |  | 0 | -0.008 | 0
[6 empty] | R29-N/16 | 3.81 | 1 | 1 | 3.81 | 1863 | 169 | 1 | 3.81 |  |  |  | 0 |  | 3.802 | 1 | 3.802 |  | 0 | -0.008 | 0
[6 empty] | R29-N/17 | 3.81 | 1 | 1 | 3.81 |  |  | 1 | 3.81 |  |  |  | 0 |  | 3.802 | 1 | 3.802 |  | 0 | -0.008 | 0
[6 empty] | R29-N/18 | 2.27 | 1 | 1 | 2.27 | 2192 | 213 | 1 | 2.27 |  |  |  | 0 |  | 2.891 |  | 0 |  | 0 | -2.27 | 0
[6 empty] | R29-N/19 | 4.49 | 1 | 1 | 4.49 |  |  | 0.3 | 1.347 | 30% | 0% | 30% | 1.347 | extended slab | 4.49 |  | 0 |  | 0 | -1.347 | -1.347
[6 empty] | R29-N/20 | 4.49 | 1 | 1 | 4.49 | 30943123 | 322328 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | extended slab | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R29-N/21 | 4.49 | 1 | 1 | 4.49 | 31233143 | 328331 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | extended slab | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R29-N/22 | 4.49 | 1 | 1 | 4.49 | 3123 | 328 | 0.33 | 1.4817 | 100% | 0% | 100% | 4.49 | extended slab | 4.49 |  | 0 |  | 0 | -1.4817 | -4.49
[6 empty] | R29-N/23 | 4.49 | 1 | 1 | 4.49 | 3123 | 328 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | extended slab | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | R29-N/24 | 4.49 | 1 | 1 | 4.49 |  |  | 0.3 | 1.347 | 30% | 0% | 30% | 1.347 | extended slab | 4.49 |  | 0 |  | 0 | -1.347 | -1.347
[6 empty] | R29-N/25 | 4.49 | 1 | 1 | 4.49 | 1896 | 173 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | R29-N/26 | 4.49 | 1 | 1 | 4.49 | 1863 | 169 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | R29-N/27 | 3.32 | 1 | 1 | 3.32 | 1863,2419 | 169 | 1 | 3.32 | 100% |  | 100% | 3.32 |  | 3.312 | 0.66667 | 2.208 |  | 0 | -1.112 | -3.32
[6 empty] | R29-N/28 | 3.32 | 1 | 1 | 3.32 | 1863,2276,2282 | 169224228 | 1 | 3.32 | 100% |  | 100% | 3.32 |  | 3.312 | 0.66667 | 2.208 |  | 0 | -1.112 | -3.32
[6 empty] | R29-N/29 | 3.27 | 1 | 1 | 3.27 | 1863,2205,2212,2276,3143 | 169,215,216,224,330 | 1 | 3.27 | 100% |  | 100% | 3.27 |  | 3.256 |  | 0 |  | 0 | -3.27 | -3.27
[6 empty] | R29-N/30 | 3.27 | 1 | 1 | 3.27 | 2205,2213,2276 | 215,224 | 1 | 3.27 | 100% |  | 100% | 3.27 |  | 3.256 |  | 0 |  | 0 | -3.27 | -3.27
[6 empty] | R29-N/31 | 4.01 | 1 | 1 | 4.01 | 1881,2274 | 167,170,224 | 1 | 4.01 | 100% |  | 100% | 4.01 |  | 3.995 | 0.66667 | 2.6633 |  | 0 | -1.3467 | -4.01
[6 empty] | R29-N/32 | 4.35 | 1 | 1 | 4.35 | 1896,2274,2276 | 173,224,224 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 0.66667 | 2.8933 |  | 0 | -1.4567 | -4.35
[6 empty] | R29-N/33 | 4.35 | 1 | 1 | 4.35 | 1881,2274 | 167,170,224 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 0.66667 | 2.8933 |  | 0 | -1.4567 | -4.35
[6 empty] | R29-N/34 | 4.35 | 1 | 1 | 4.35 | 1881,2205,2276 | 167,170,215,224 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 0.66667 | 2.8933 |  | 0 | -1.4567 | -4.35
[6 empty] | R29-N/35 | 3.68 | 1 | 1 | 3.68 | 2205,2276,2282 | 215,224,228 | 1 | 3.68 | 100% |  | 100% | 3.68 |  | 3.995 |  | 0 |  | 0 | -3.68 | -3.68
[6 empty] | R29-N/36 | 1.49 |  | 1 | 1.49 | 2205,2212 | 215,216 | 1 | 1.49 | 100% |  | 100% | 1.49 |  | 1.8 |  | 0 |  | 0 | -1.49 | -1.49
[9 empty] | TOTAL | 142.5 |  |  | TOTAL | 133.2057 | TOTAL |  |  | 65.044 |  |  | TOTAL | 86.2233 | TOTAL | 24.514
25 | EWS-101 | 600 | 30 | 1 |  | R30-N/01 | 4.49 | 1 | 1 | 4.49 | 1795 | 164 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R30-N/02 | 4.49 | 1 | 1 | 4.49 | 1802 | 165 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R30-N/03 | 4.49 | 1 | 1 | 4.49 | 1802 | 165 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R30-N/04 | 4.49 | 1 | 1 | 4.49 | 1802 | 165 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R30-N/05 | 4.49 | 1 | 1 | 4.49 | 1802 | 165 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R30-N/06 | 4.49 | 1 | 1 | 4.49 | 1795 | 164 | 1 | 4.49 | 100% |  | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | R30-N/07 | 3.29 | 1 | 1 | 3.29 | 1795 | 164 | 1 | 3.29 | 100% |  | 100% | 3.29 |  | 3.277 | 1 | 3.277 | 100% | 3.277 | -0.013 | -0.013
[6 empty] | R30-N/08 | 3.29 | 1 | 1 | 3.29 | 1887 | 170 | 1 | 3.29 | 100% |  | 100% | 3.29 |  | 3.277 | 1 | 3.277 | 100% | 3.277 | -0.013 | -0.013
[6 empty] | R30-N/09 | 3.58 | 1 | 1 | 3.58 | 2143 | 205 | 1 | 3.58 | 100% |  | 100% | 3.58 |  | 3.57 |  | 0 |  | 0 | -3.58 | -3.58
[6 empty] | R30-N/10 | 2.86 | 1 | 1 | 2.86 | 2145,2147 | 206 | 1 | 2.86 | 100% |  | 100% | 2.86 |  | 2.846 |  | 0 |  | 0 | -2.86 | -2.86
[6 empty] | R30-N/11 | 3.81 | 1 | 1 | 3.81 | 1891 | 171 | 1 | 3.81 |  |  |  | 0 | Scaffolding not handover | 3.802 |  | 0 |  | 0 | -3.81 | 0
[6 empty] | R30-N/12 | 3.81 | 1 | 1 | 3.81 | 1891 | 171 | 1 | 3.81 |  |  |  | 0 | Scaffolding not handover | 3.802 |  | 0 |  | 0 | -3.81 | 0
[6 empty] | R30-N/13 | 3.81 | 1 | 1 | 3.81 | 1887 | 170 | 1 | 3.81 |  |  |  | 0 | Scaffolding not handover | 3.802 |  | 0 |  | 0 | -3.81 | 0
[6 empty] | R30-N/14 | 3.81 | 1 | 1 | 3.81 | 1891 | 171 | 1 | 3.81 |  |  |  | 0 | Scaffolding not handover | 3.802 |  | 0 |  | 0 | -3.81 | 0
[6 empty] | R30-N/15 | 3.11 | 1 | 1 | 3.11 | 2082 | 196 | 1 | 3.11 |  |  |  | 0 | Scaffolding not handover | 3.421 |  | 0 |  | 0 | -3.11 | 0
[6 empty] | R30-N/16 | 1.42 | 1 | 1 | 1.42 | 2082 | 196 | 1 | 1.42 |  |  |  | 0 | Scaffolding not handover | 1.729 |  | 0 |  | 0 | -1.42 | 0
[6 empty] | R30-N/17 | 4.49 | 1 | 1 | 4.49 | 2709 | 283 | 1 | 4.49 |  |  |  | 0 |  | 4.49 |  | 0 |  | 0 | -4.49 | 0
[6 empty] | R30-N/18 | 4.49 | 1 | 1 | 4.49 | 2709 | 283 | 1 | 4.49 |  |  |  | 0 |  | 4.49 |  | 0 |  | 0 | -4.49 | 0
[6 empty] | R30-N/19 | 4.49 | 1 | 1 | 4.49 | 2709 | 283 | 1 | 4.49 |  |  |  | 0 |  | 4.49 |  | 0 |  | 0 | -4.49 | 0
[6 empty] | R30-N/20 | 4.49 | 1 | 1 | 4.49 | 2711 | 284 | 1 | 4.49 |  |  |  | 0 |  | 4.49 |  | 0 |  | 0 | -4.49 | 0
[6 empty] | R30-N/21 | 4.49 | 1 | 1 | 4.49 | 2711 | 284 | 1 | 4.49 |  |  |  | 0 |  | 4.49 |  | 0 |  | 0 | -4.49 | 0
[6 empty] | R30-N/22 | 4.49 | 1 | 1 | 4.49 | 2711 | 284 | 1 | 4.49 |  |  |  | 0 |  | 4.49 |  | 0 |  | 0 | -4.49 | 0
[6 empty] | R30-N/23 | 4.04 | 1 | 1 | 4.04 | 1891 | 171 | 1 | 4.04 | 100% |  | 100% | 4.04 |  | 4.027 |  | 0 |  | 0 | -4.04 | -4.04
[6 empty] | R30-N/24 | 4.04 | 1 | 1 | 4.04 | 1934 | 175 | 1 | 4.04 | 100% |  | 100% | 4.04 |  | 4.027 | 1 | 4.027 |  | 0 | -0.013 | -4.04
[6 empty] | R30-N/25 | 2.49 | 1 | 1 | 2.49 | 2123 | 204 | 1 | 2.49 | 100% |  | 100% | 2.49 |  | 2.477 |  | 0 |  | 0 | -2.49 | -2.49
[6 empty] | R30-N/26 | 2.49 | 1 | 1 | 2.49 | 2127 | 204 | 1 | 2.49 | 100% |  | 100% | 2.49 |  | 2.477 |  | 0 |  | 0 | -2.49 | -2.49
[6 empty] | R30-N/27 | 3.43 | 1 | 1 | 3.43 | 1934 | 175 | 1 | 3.43 | 100% |  | 100% | 3.43 |  | 3.421 | 1 | 3.421 | 100% | 3.421 | -0.009 | -0.009
[6 empty] | R30-N/28 | 4.35 | 1 | 1 | 4.35 | 1934 | 175 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[6 empty] | R30-N/29 | 4.35 | 1 | 1 | 4.35 | 1887 | 170 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[6 empty] | R30-N/30 | 4.35 | 1 | 1 | 4.35 | 1934 | 175 | 1 | 4.35 | 100% |  | 100% | 4.35 |  | 4.34 | 1 | 4.34 | 100% | 4.34 | -0.01 | -0.01
[6 empty] | R30-N/31 | 2.14 | 1 | 1 | 2.14 | 2082 | 196 | 1 | 2.14 | 100% |  | 100% | 2.14 |  | 2.45 |  | 0 |  | 0 | -2.14 | -2.14
[6 empty] | R30-N/32 | 1.91 | 1 | 1 | 1.91 | 2082 | 196 | 1 | 1.91 | 100% |  | 100% | 1.91 |  | 2.225 |  | 0 |  | 0 | -1.91 | -1.91
[9 empty] | TOTAL | 120.26 |  |  | TOTAL | 120.26 | TOTAL |  |  | 73.55 |  |  | TOTAL | 53.962 | TOTAL | 49.935
[6 empty] | LVL | L | Qty |  | Mat'l Produced (Length) |  |  | Mat'l On Site | Mat'l On Site (Length) | Work Done |  |  | Work Done (Length) |  | L | Mat'l On Site | Mat'l On Site (Length) | Work Done | Work Done (Length) | L | L
| BOQ Item E |  |  |  |  | R6 | 199.5 | 46 |  | 199.5 |  |  | 100% | 199.5 | 86.5% |  |  | 172.56 |  | 199.364 | 10.13% | 20.205 | 0% | 0 | -179.295 | -172.56
| BOQ Item G |  |  |  |  | R7 to R31 | 3482.096 | 838 |  | 3482.096 |  |  | 97.52% | 3395.6942 | 87.67% |  |  | 3052.8709 |  | 3479.106 | 82.14% | 2857.7267 | 74.83% | 2603.2633 | -537.9675 | -449.6076
[6 empty] | TOTAL (BOQ E) | 26.94 | 6 | 6 | 26.94 |  |  | 6 | 26.94 |  |  | 0% | 0
[6 empty] | TOTAL (BOQ G) | 286.486 | 62 | 62 | 286.486 |  |  | 42.89 | 200.0842 |  |  | 25.6% | 73.327
[25 empty] | #REF! | #REF!

## Residential - 900mm(Qty)
Quantity Take Off- Service Apartment ( Tower )
S. No. | Wall Type | Width | Floor Level | Qty Per Floor |  |  |  | GRC PANEL PRODUCED |  | GRC PANEL DELIVERED ONSITE |  |  |  | GRC PANEL INSTALLATION |  |  |  | Remarks
[5 empty] | CODE | L | Qty | Mat'l Produced | Length | DO No. | MIR No. | Mat'l On Site | Length | Work Done (Previous) | Work Done (This) | Work Done (Cumm.) | Length (This)
1 | EWS-101 | 900 | 6 | 1 | R6-N/21 | 3.81 | 1 | 1 | 3.81 | 2565,2608,2609 | 259,270 | 1 | 3.81 | 100% | 0% | 100% | 3.81 | WIR 1117
[5 empty] | R6-N/22 | 3.81 | 1 | 1 | 3.81 | 2608,2609,2624 | 270,272 | 1 | 3.81 | 100% | 0% | 100% | 3.81 | WIR 1117
[5 empty] | R6-N/23 | 3.81 | 1 | 1 | 3.81 | 2608,2609,2624 | 270,272 | 1 | 3.81 | 100% | 0% | 100% | 3.81 | WIR 1117
[5 empty] | R6-N/24 | 3.81 | 1 | 1 | 3.81 | 2608,2609 | 270 | 1 | 3.81 | 100% | 0% | 100% | 3.81 | WIR 1117
[8 empty] | TOTAL | 15.24 |  |  | TOTAL | 15.24 | TOTAL | TOTAL |  | 15.24
2 | EWS-101 | 900 | 7 | 1 | R7-N/18 | 3.3 | 1 | 1 | 3.3 | 1261 | 066 | 1 | 3.3 | 100% | 0% | 100% | 3.3
[5 empty] | R7-N/19 | 3.8 | 1 | 1 | 3.8 | 1231 | 054 | 1 | 3.8 | 100% | 0% | 100% | 3.8
[5 empty] | R7-N/31 | 4.49 | 1 | 1 | 4.49 | 2449 | 240 | 1 | 4.49 | 100% | 0% | 100% | 4.49
[5 empty] | R7-N/32 | 4.49 | 1 | 1 | 4.49 | 2440,2449 | 239,240 | 1 | 4.49 | 100% | 0% | 100% | 4.49
[5 empty] | R7-N/33 | 4.49 | 1 | 1 | 4.49 | 2440 | 239 | 1 | 4.49 | 100% | 0% | 100% | 4.49
[5 empty] | R7-N/34 | 4.49 | 1 | 1 | 4.49 | 2440 | 239 | 1 | 4.49 | 100% | 0% | 100% | 4.49
[8 empty] | TOTAL | 25.06 |  |  | TOTAL | 25.06 | TOTAL | TOTAL |  | 25.06
3 | EWS-101 | 900 | 8 | 1 | R8-N/21 | 3.81 | 1 | 1 | 3.81 |  |  | 1 | 3.81 | 100% | 0% | 100% | 3.81
[5 empty] | R8-N/22 | 3.81 | 1 | 1 | 3.81 |  |  | 1 | 3.81 | 100% | 0% | 100% | 3.81
[5 empty] | R8-N/23 | 3.81 | 1 | 1 | 3.81 |  |  | 1 | 3.81 | 100% | 0% | 100% | 3.81
[5 empty] | R8-N/24 | 3.81 | 1 | 1 | 3.81 |  |  | 1 | 3.81 | 100% | 0% | 100% | 3.81
[5 empty] | R8-N/36 | 4.49 | 1 | 1 | 4.49 | 1219,2502 | 048 | 1 | 4.49 | 100% | 0% | 100% | 4.49
[5 empty] | R8-N/37 | 4.49 | 1 | 1 | 4.49 | 1219,2502 | 048 | 1 | 4.49 | 100% | 0% | 100% | 4.49
[5 empty] | R8-N/38 | 4.49 | 1 | 1 | 4.49 | 121912292502 | 048,053 | 1 | 4.49 | 100% | 0% | 100% | 4.49
[5 empty] | R8-N/39 | 4.49 | 1 | 1 | 4.49 | 121912292502 | 048,053 | 1 | 4.49 | 100% | 0% | 100% | 4.49
[8 empty] | TOTAL | 33.2 |  |  | TOTAL | 33.2 | TOTAL | TOTAL |  | 33.2
4 | EWS-101 | 900 | 9 | 1 | R9-N/18 | 3.27 | 1 | 1 | 3.27 | 1303 | 079 | 1 | 3.27 | 100% | 0% | 100% | 3.27
[5 empty] | R9-N/19 | 3.81 | 1 | 1 | 3.81 | 1219 | 048 | 1 | 3.81 | 100% | 0% | 100% | 3.81
[5 empty] | R9-N/31 | 4.49 | 1 | 1 | 4.49 | 2463 | 242 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1223
[5 empty] | R9-N/32 | 4.49 | 1 | 1 | 4.49 | 2453 | 241 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1223
[5 empty] | R9-N/33 | 4.49 | 1 | 1 | 4.49 | 2453 | 241 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1223
[5 empty] | R9-N/34 | 4.49 | 1 | 1 | 4.49 | 2453 | 241 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1223
[8 empty] | TOTAL | 25.04 |  |  | TOTAL | 25.04 | TOTAL | TOTAL |  | 25.04
5 | EWS-101 | 900 | 10 | 1 | R10-N/36 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab
[5 empty] | R10-N/37 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab
[5 empty] | R10-N/38 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab
[5 empty] | R10-N/39 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab
[8 empty] | TOTAL | 17.96 |  |  | TOTAL | 0 | TOTAL |  |  | 0
6 | EWS-101 | 900 | 11 | 1 | R11-N/16 | 4.49 | 1 | 1 | 4.49 | 2202,2472 | 214244 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1140 R2
[5 empty] | R11-N/17 | 4.49 | 1 | 1 | 4.49 | 2202,2472 | 214244 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1140 R2
[5 empty] | R11-N/18 | 4.49 | 1 | 1 | 4.49 | 2212,2472 | 216,244 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1140 R2
[5 empty] | R11-N/19 | 4.49 | 1 | 1 | 4.49 | 2212,2213,2472,2614 | 216,244,271 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1140 R2
[8 empty] | TOTAL | 17.96 |  |  | TOTAL | 17.96 | TOTAL |  |  | 17.96
7 | EWS-101 | 900 | 12 | 1 | R12-N/24 | 4.49 | 1 | 1 | 4.49 | 2213,2479 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1141
[5 empty] | R12-N/25 | 4.49 | 1 | 1 | 4.49 | 2213,2479 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1141
[5 empty] | R12-N/26 | 4.49 | 1 | 1 | 4.49 | 2213,2479,2549 | 258 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1141
[5 empty] | R12-N/27 | 4.49 | 1 | 1 | 4.49 | 2212,2213,2479 | 216 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1141
[8 empty] | TOTAL | 17.96 |  |  | TOTAL | 17.96 | TOTAL |  |  | 17.96
8 | EWS-101 | 900 | 13 | 1 | R13-N/09 | 4.49 | 1 | 1 | 4.49 | 2212,2213, 2485,2535 | 216 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1142
[5 empty] | R13-N/10 | 4.49 | 1 | 1 | 4.49 | 2212,2213,2485 | 216 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1142
[5 empty] | R13-N/11 | 4.49 | 1 | 1 | 4.49 | 2485,2492 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1142
[5 empty] | R13-N/12 | 4.49 | 1 | 1 | 4.49 | 2213,2485 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1142
[8 empty] | TOTAL | 17.96 |  |  | TOTAL | 17.96 | TOTAL |  |  | 17.96
9 | EWS-101 | 900 | 14 | 1 | R14-N/24 | 4.49 | 1 | 1 | 4.49 | 2490 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1151 R1
[5 empty] | R14-N/25 | 4.49 | 1 | 1 | 4.49 | 2490 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1151 R1
[5 empty] | R14-N/26 | 4.49 | 1 | 1 | 4.49 | 2490 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1151 R1
[5 empty] | R14-N/27 | 4.49 | 1 | 1 | 4.49 | 2490 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1151 R1
[8 empty] | TOTAL | 17.96 |  |  | TOTAL | 17.96 | TOTAL |  |  | 17.96
10 | EWS-101 | 900 | 15 | 1 | R15-N/09 | 4.49 | 1 | 1 | 4.49 | 2514 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1152 R1
[5 empty] | R15-N/10 | 4.49 | 1 | 1 | 4.49 | 2514 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1152 R1
[5 empty] | R15-N/11 | 4.49 | 1 | 1 | 4.49 | 2511 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1152 R1
[5 empty] | R15-N/12 | 4.49 | 1 | 1 | 4.49 | 2511 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1152 R1
[8 empty] | TOTAL | 17.96 |  |  | TOTAL | 17.96 | TOTAL |  |  | 17.96
11 | EWS-101 | 900 | 16 | 1 | R16-N/24 | 4.49 | 1 | 1 | 4.49 | 2521 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1153
[5 empty] | R16-N/25 | 4.49 | 1 | 1 | 4.49 | 2521 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1153
[5 empty] | R16-N/26 | 4.49 | 1 | 1 | 4.49 | 2521 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1153
[5 empty] | R16-N/27 | 4.49 | 1 | 1 | 4.49 | 2531 | 254 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1153
[8 empty] | TOTAL | 17.96 |  |  | TOTAL | 17.96 | TOTAL |  |  | 17.96
12 | EWS-101 | 900 | 17 | 1 | R17-N/09 | 4.49 | 1 | 1 | 4.49 | 2524 | 254 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1154 R1
[5 empty] | R17-N/10 | 4.49 | 1 | 1 | 4.49 | 2524 | 254 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1154 R1
[5 empty] | R17-N/11 | 4.49 | 1 | 1 | 4.49 | 2524 | 254 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1154 R1
[5 empty] | R17-N/12 | 4.49 | 1 | 1 | 4.49 | 1444,2531 | 254 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1154 R1
[8 empty] | TOTAL | 17.96 |  |  | TOTAL | 17.96 | TOTAL |  |  | 17.96
13 | EWS-101 | 900 | 19 | 1 | R19-N/11 | 4.49 | 1 | 1 | 4.49 | 2534 | 256 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1204
[5 empty] | R19-N/12 | 4.49 | 1 | 1 | 4.49 | 2534 | 256 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1204
[5 empty] | R19-N/13 | 4.49 | 1 | 1 | 4.49 | 2534 | 256 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1204
[5 empty] | R19-N/14 | 4.49 | 1 | 1 | 4.49 | 2560 | 257 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1204
[8 empty] | TOTAL | 17.96 |  |  | TOTAL | 17.96 | TOTAL |  |  | 17.96
14 | EWS-101 | 900 | 20 | 1 | R20-N/05 | 4.49 | 1 | 1 | 4.49 | 2540 | 256 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1203
[5 empty] | R20-N/06 | 4.49 | 1 | 1 | 4.49 | 2535 | 256 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1203
[5 empty] | R20-N/07 | 4.49 | 1 | 1 | 4.49 | 2540 | 256 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1203
[5 empty] | R20-N/08 | 4.49 | 1 | 1 | 4.49 | 2540 | 256 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1203
[8 empty] | TOTAL | 17.96 |  |  | TOTAL | 17.96 | TOTAL |  |  | 17.96
15 | EWS-101 | 900 | 21 | 1 | R21-N/11 | 4.49 | 1 | 1 | 4.49 | 2556,2560 | 257 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1202
[5 empty] | R21-N/12 | 4.49 | 1 | 1 | 4.49 | 2556,2560 | 257 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1202
[5 empty] | R21-N/13 | 4.49 | 1 | 1 | 4.49 | 2556,2560 | 257 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1202
[5 empty] | R21-N/14 | 4.49 | 1 | 1 | 4.49 | 2556,2560 | 257 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1202
[8 empty] | TOTAL | 17.96 |  |  | TOTAL | 17.96 | TOTAL |  |  | 17.96
16 | EWS-101 | 900 | 22 | 1 | R22-N/5 | 4.49 | 1 | 1 | 4.49 | 2546 | 256 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1201
[5 empty] | R22-N/6 | 4.49 | 1 | 1 | 4.49 | 2546 | 256 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1201
[5 empty] | R22-N/7 | 4.49 | 1 | 1 | 4.49 | 2546 | 256 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1201
[5 empty] | R22-N/8 | 4.49 | 1 | 1 | 4.49 | 2546,2548 | 256,257 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1201
[8 empty] | TOTAL | 17.96 |  |  | TOTAL | 17.96 | TOTAL |  |  | 17.96
17 | EWS-101 | 900 | 23 | 1 |  |  | 1 | [5 empty] | 0 |  |  |  | 0
[7 empty] | 1 | [5 empty] | 0 |  |  |  | 0
[7 empty] | 1 | [5 empty] | 0 |  |  |  | 0
[7 empty] | 1 | [5 empty] | 0 |  |  |  | 0
[12 empty] | TOTAL | 0 | TOTAL |  |  | 0
18 | EWS-101 | 900 | 24 | 1 |  |  | 1 | [5 empty] | 0 |  |  |  | 0
[7 empty] | 1 | [5 empty] | 0 |  |  |  | 0
[7 empty] | 1 | [5 empty] | 0 |  |  |  | 0
[7 empty] | 1 | [5 empty] | 0 |  |  |  | 0
[12 empty] | TOTAL | 0 | TOTAL |  |  | 0
19 | EWS-101 | 900 | 25 | 1 |  |  | 1 | [5 empty] | 0 |  |  |  | 0
[7 empty] | 1 | [5 empty] | 0 |  |  |  | 0
[7 empty] | 1 | [5 empty] | 0 |  |  |  | 0
[7 empty] | 1 | [5 empty] | 0 |  |  |  | 0
[12 empty] | TOTAL | 0 | TOTAL |  |  | 0
20 | EWS-101 | 900 | 26 | 1 | R26-N/21 | 4.49 | 1 | 1 | 4.49 | 2549 | 258 | 1 | 4.49 | 100% | 0% | 100% | 4.49
[5 empty] | R26-N/22 | 4.49 | 1 | 1 | 4.49 | 2549 | 258 | 1 | 4.49 | 100% | 0% | 100% | 4.49
[5 empty] | R26-N/23 | 4.49 | 1 | 1 | 4.49 | 2566,2614 | 259 | 1 | 4.49 | 100% | 0% | 100% | 4.49
[5 empty] | R26-N/24 | 4.49 | 1 | 1 | 4.49 | 2566 | 259 | 1 | 4.49 | 100% | 0% | 100% | 4.49
[8 empty] | TOTAL | 17.96 |  |  | TOTAL | 17.96 | TOTAL |  |  | 17.96
21 | EWS-101 | 900 | 27 | 1 | R27-N/20 | 4.49 | 1 | 1 | 4.49 | 2568 | 259 | 1 | 4.49 | 100% | 0% | 100% | 4.49
[5 empty] | R27-N/21 | 4.49 | 1 | 1 | 4.49 | 2568 | 259 | 1 | 4.49 | 100% | 0% | 100% | 4.49
[5 empty] | R27-N/22 | 4.49 | 1 | 1 | 4.49 | 2570 | 259 | 1 | 4.49 | 100% | 0% | 100% | 4.49
[5 empty] | R27-N/23 | 4.49 | 1 | 1 | 4.49 | 2572 | 259,271 | 1 | 4.49 | 100% | 0% | 100% | 4.49
[8 empty] | TOTAL | 17.96 |  |  | TOTAL | 17.96 | TOTAL |  |  | 17.96
22 | EWS-101 | 900 | 28 | 1 | R28-N/17 | 4.49 | 1 | 1 | 4.49 | 2573 | 259 | 1 | 4.49 | 100% | 0% | 100% | 4.49
[5 empty] | R28-N/18 | 4.49 | 1 | 1 | 4.49 | 2573 | 259 | 1 | 4.49 | 100% | 0% | 100% | 4.49
[5 empty] | R28-N/19 | 4.49 | 1 | 1 | 4.49 | 2573 | 259 | 1 | 4.49 | 100% | 0% | 100% | 4.49
[5 empty] | R28-N/20 | 4.49 | 1 | 1 | 4.49 | 2572 | 259 | 1 | 4.49 | 100% | 0% | 100% | 4.49
[8 empty] | TOTAL | 17.96 |  |  | TOTAL | 17.96 | TOTAL |  |  | 17.96
23 | EWS-101 | 900 | 29 | 1 |  |  | 1 | [5 empty] | 0 |  |  |  | 0
[7 empty] | 1 | [5 empty] | 0 |  |  |  | 0
[7 empty] | 1 | [5 empty] | 0 |  |  |  | 0
[7 empty] | 1 | [5 empty] | 0 |  |  |  | 0
[12 empty] | TOTAL | 0 | TOTAL |  |  | 0
24 | EWS-101 | 900 | 30 | 1 |  |  | 1 | [5 empty] | 0 |  |  |  | 0
[7 empty] | 1 | [5 empty] | 0 |  |  |  | 0
[7 empty] | 1 | [5 empty] | 0 |  |  |  | 0
[7 empty] | 1 | [5 empty] | 0 |  |  |  | 0
[12 empty] | TOTAL | 0 | TOTAL |  |  | 0
[5 empty] | LVL | L | Qty |  | Mat'l Produced (Length) |  |  | Mat'l On Site | Mat'l On Site (Length) | Work Done |  |  | Work Done (Length)
| BOQ Item J |  |  |  | R6 to R31 | 367.94 | 96 |  | 367.94 |  |  | 95.12% | 349.98 | 95.12% |  |  | 349.98
[5 empty] | TOTAL (BOQ J) | 17.96 | 4 | 4 | 17.96 |  |  | 0 | 0 |  |  | 0% | 0

## Hotel - 600mm(Qty)
Quantity Take Off- Hotel ( Tower ) | [19 empty] | RPJV ASSESSMENT - NOV 2020
S. No. | Wall Type | Width | Floor Level | Qty Per Floor |  |  |  |  | GRC PANEL PRODUCED |  | GRC PANEL DELIVERED ONSITE |  |  |  | GRC PANEL INSTALLATION |  |  |  | Remarks |  | GRC PANEL ONSITE |  | GRC PANEL INSTALLATION |  | GRC PANEL INSTALLATION
[6 empty] | CODE | L | Qty | Mat'l Produced | Length | DO No. | MIR No. | Mat'l On Site | Length | Work Done (Previous) | Work Done (This) | Work Done (Cumm.) | Length (This) |  | L | Mat'l On Site | Length | Work Done | Length | Work Done | Length
1 | EWS-101 | 600 | 7 | 1 | Corner panel | H7-N/01 | 4.17 | 1 | 1 | 4.17 | 1619,2044 | 144,190 | 1 | 4.17 | 100% | 0% | 100% | 4.17 | WIR 0763 R2 | 4.155 | 0.5 | 2.0775 |  | 0 | -2.0925 | -4.17
[6 empty] | H7-N/02 | 4.49 | 1 | 1 | 4.49 | 2026 | 187 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 0763 R2 | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H7-N/03 | 4.49 | 1 | 1 | 4.49 | 1619,1697 | 144.156 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H7-N/04 | 4.49 | 1 | 1 | 4.49 | 1625,1697 | 145156 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H7-N/05 | 4.49 | 1 | 1 | 4.49 | 1619,1625,1648 | 144145148 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H7-N/06 | 4.49 | 1 | 1 | 4.49 | 1619,1686 | 144,154 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H7-N/07 | 4.49 | 1 | 1 | 4.49 | 1619,1686 | 144,154 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H7-N/08 | 4.49 | 1 | 1 | 4.49 | 1395 | 099 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H7-N/09 | 4.49 | 1 | 1 | 4.49 | 1625,1672,2151 | 145,152,207 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H7-N/10 | 4.49 | 1 | 1 | 4.49 | 1625,1660.2099 | 145,150,199 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H7-N/11 | 3.38 | 1 | 1 | 3.38 | 1660,1659 | 150 | 1 | 3.38 | 100% | 0% | 100% | 3.38 |  | 3.365 | 1 | 3.365 | 100% | 3.365 | -0.015 | -0.015
[5 empty] | Curve | H7-N/12 | 3.38 | 1 | 1 | 3.38 | 1660,1659 | 150 | 1 | 3.38 | 100% | 0% | 100% | 3.38 |  | 3.365 | 1 | 3.365 | 100% | 3.365 | -0.015 | -0.015
[5 empty] | Curve | H7-N/13 | 3.41 | 1 | 1 | 3.41 | 2137,2147 | 205,206 | 1 | 3.41 | 100% | 0% | 100% | 3.41 | WIR 0765 R2 | 3.255 |  | 0 |  | 0 | -3.41 | -3.41
[6 empty] | H7-N/14 | 3.77 | 1 | 1 | 3.77 | 2142,2163,2148 | 205,208 | 1 | 3.77 | 100% | 0% | 100% | 3.77 | WIR 0765 R2 | 3.762 |  | 0 |  | 0 | -3.77 | -3.77
[6 empty] | H7-N/15 | 3.92 | 1 | 1 | 3.92 | 1660,1659 | 150 | 1 | 3.92 | 100% | 0% | 100% | 3.92 | WIR 0765 R2 | 3.91 | 1 | 3.91 |  | 0 | -0.01 | -3.92
[6 empty] | H7-N/16 | 3.92 | 1 | 1 | 3.92 | 1936 | 175 | 1 | 3.92 | 100% | 0% | 100% | 3.92 | WIR 0765 R2 | 3.91 |  | 0 |  | 0 | -3.92 | -3.92
[6 empty] | H7-N/17 | 3.92 | 1 | 1 | 3.92 | 2108,2119 | 201,203 | 1 | 3.92 | 100% | 0% | 100% | 3.92 | WIR 0765 R2 | 3.91 |  | 0 |  | 0 | -3.92 | -3.92
[5 empty] | Curve | H7-N/18 | 3.92 | 1 | 1 | 3.92 | 1660,1659 | 150 | 1 | 3.92 | 100% | 0% | 100% | 3.92 | WIR 0765 R2 | 3.91 | 1 | 3.91 |  | 0 | -0.01 | -3.92
[5 empty] | Curve | H7-N/19 | 3.77 | 1 | 1 | 3.77 | 2156,2157,2163 | 207,208 | 1 | 3.77 | 100% | 0% | 100% | 3.77 | WIR 0765 R2 | 3.762 |  | 0 |  | 0 | -3.77 | -3.77
[6 empty] | H7-N/20 | 3.41 | 1 | 1 | 3.41 | 2157,2170,2148 | 207,208 | 1 | 3.41 | 100% | 0% | 100% | 3.41 | WIR 0765 R2 | 3.4 |  | 0 |  | 0 | -3.41 | -3.41
[6 empty] | H7-N/21 | 3.37 | 1 | 1 | 3.37 | 1619,1625,2044 | 145,190 | 1 | 3.37 | 100% | 0% | 100% | 3.37 |  | 3.365 | 0.25 | 0.84125 |  | 0 | -2.5288 | -3.37
[6 empty] | H7-N/22 | 3.37 | 1 | 1 | 3.37 | 2068 | 194 | 1 | 3.37 | 100% | 0% | 100% | 3.37 |  | 3.365 | 0.66667 | 2.2433 |  | 0 | -1.1267 | -3.37
[5 empty] | Curve with flat panel | H7-N/23 | 4.49 | 1 | 1 | 4.49 | 2061 | 193 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H7-N/24 | 4.49 | 1 | 1 | 4.49 | 2100,2736,2738 | 199 | 1 | 4.49 |  | 0% | 0% | 0 | Cradle Area (Core Wall Access) | 4.49 |  | 0 |  | 0 | -4.49 | 0
[6 empty] | H7-N/25 | 4.49 | 1 | 1 | 4.49 | 2100,2736,2738 | 199 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR-L7-01256 | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H7-N/26 | 4.49 | 1 | 1 | 4.49 | 2736,2738 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR-L7-01256 | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H7-N/27 | 4.49 | 1 | 1 | 4.49 | 2736,2738 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR-L7-01256 | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[5 empty] | Curve with flat panel | H7-N/28 | 4.49 | 1 | 1 | 4.49 | 2486 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR-L7-01256 | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H7-N/29 | 4.49 | 1 | 1 | 4.49 | 2486 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR-L7-01256 | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H7-N/30 | 4.49 | 1 | 1 | 4.49 | 2041 | 189 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR-L7-01255 | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H7-N/31 | 4.49 | 1 | 1 | 4.49 | 2026 | 187 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR-L7-01255 | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H7-N/32 | 4.17 | 1 | 1 | 4.17 | 2142,2061 | 193,205 | 1 | 4.17 | 100% | 0% | 100% | 4.17 | WIR-L7-01255 | 4.155 |  | 0 |  | 0 | -4.17 | -4.17
[6 empty] | H7-N/33 | 5.01 | 1 | 1 | 5.01 | 2142,2147,2156 | 205,206,207 | 1 | 5.01 | 100% | 0% | 100% | 5.01 |  | 5.03 |  | 0 |  | 0 | -5.01 | -5.01
[6 empty] | H7-N/34 | 4.49 | 1 | 1 | 4.49 | 2136 | 205 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H7-N/35 | 4.49 | 1 | 1 | 4.49 | 2136,2147 | 206 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H7-N/36 | 4.49 | 1 | 1 | 4.49 | 2041 | 189 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H7-N/37 | 4.49 | 1 | 1 | 4.49 | 2142,2145,2156,2190,2402,2423 | 205,206,207,211 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[5 empty] | Corner panel | H7-N/38 | 5.01 | 1 | 1 | 5.01 | 2142,2145,2151,2402 | 205,206,207 | 1 | 5.01 | 100% | 0% | 100% | 5.01 |  | 5.03 |  | 0 |  | 0 | -5.01 | -5.01
[9 empty] | TOTAL | 160.68 |  |  | TOTAL | 160.68 | TOTAL |  |  | 156.19 |  |  | TOTAL | 55.6321 | TOTAL | 42.65
2 | EWS-101 | 600 | 8 | 1 | Corner panel | H8-N/01 | 2.58 | 1 | 1 | 2.58 | 1395,2192 | 099,213 | 1 | 2.58 | 100% | 0% | 100% | 2.58 |  | 2.61 | 1 | 2.61 | 100% | 2.61 | 0.03 | 0.03
[6 empty] | H8-N/02 | 4.49 | 1 | 1 | 4.49 | 1065 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H8-N/03 | 4.49 | 1 | 1 | 4.49 | 1065 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H8-N/04 | 4.49 | 1 | 1 | 4.49 | 1065 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H8-N/05 | 4.49 | 1 | 1 | 4.49 | 1075 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H8-N/06 | 4.49 | 1 | 1 | 4.49 | 1065 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H8-N/07 | 4.49 | 1 | 1 | 4.49 | 1075 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H8-N/08 | 4.49 | 1 | 1 | 4.49 | 1113 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H8-N/09 | 4.49 | 1 | 1 | 4.49 | 1113 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H8-N/10 | 3.38 | 1 | 1 | 3.38 | 1191 | 033 | 1 | 3.38 | 100% | 0% | 100% | 3.38 |  | 3.365 | 1 | 3.365 | 100% | 3.365 | -0.015 | -0.015
[6 empty] | H8-N/11 | 3.38 | 1 | 1 | 3.38 | 1191 | 033 | 1 | 3.38 | 100% | 0% | 100% | 3.38 |  | 3.365 | 1 | 3.365 | 100% | 3.365 | -0.015 | -0.015
[5 empty] | Curve | H8-N/12 | 3.41 | 1 | 1 | 3.41 | 1303 | 079 | 1 | 3.41 | 100% | 0% | 100% | 3.41 |  | 3.4 | 1 | 3.4 | 100% | 3.4 | -0.01 | -0.01
[5 empty] | Curve | H8-N/13 | 3.77 | 1 | 1 | 3.77 | 1303 | 079 | 1 | 3.77 | 100% | 0% | 100% | 3.77 |  | 3.762 | 1 | 3.762 | 100% | 3.762 | -0.008 | -0.008
[6 empty] | H8-N/14 | 3.92 | 1 | 1 | 3.92 | 1075 |  | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 | 100% | 3.91 | -0.01 | -0.01
[6 empty] | H8-N/15 | 3.92 | 1 | 1 | 3.92 | 1075 |  | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 | 100% | 3.91 | -0.01 | -0.01
[6 empty] | H8-N/16 | 3.92 | 1 | 1 | 3.92 | 1065 |  | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 | 100% | 3.91 | -0.01 | -0.01
[6 empty] | H8-N/17 | 3.92 | 1 | 1 | 3.92 | 1065 |  | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 | 100% | 3.91 | -0.01 | -0.01
[6 empty] | H8-N/18 | 3.77 | 1 | 1 | 3.77 | 1315 | 083 | 1 | 3.77 | 100% | 0% | 100% | 3.77 |  | 3.762 | 1 | 3.762 | 100% | 3.762 | -0.008 | -0.008
[5 empty] | Curve | H8-N/19 | 3.41 | 1 | 1 | 3.41 | 1295 | 077 | 1 | 3.41 | 100% | 0% | 100% | 3.41 |  | 3.4 | 1 | 3.4 | 100% | 3.4 | -0.01 | -0.01
[5 empty] | Curve | H8-N/20 | 3.38 | 1 | 1 | 3.38 |  |  | 1 | 3.38 | 100% | 0% | 100% | 3.38 |  | 3.365 | 1 | 3.365 | 100% | 3.365 | -0.015 | -0.015
[6 empty] | H8-N/21 | 3.38 | 1 | 1 | 3.38 |  |  | 1 | 3.38 | 100% | 0% | 100% | 3.38 |  | 3.365 | 1 | 3.365 | 100% | 3.365 | -0.015 | -0.015
[6 empty] | H8-N/22 | 4.49 | 1 | 1 | 4.49 | 1065 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Curve with flat panel | H8-N/23 | 4.72 | 1 | 1 | 4.72 | 2351 |  | 1 | 4.72 | 100% | 0% | 100% | 4.72 | WIR 1086 R1 | 4.49 |  | 0 |  | 0 | -4.72 | -4.72
[5 empty] | 900mm | H8-N/24 | [7 empty] | - |  |  |  | - | refer to Hotel - 900mm(Qty) worksheet |  |  | - |  | -
[5 empty] | 900mm | H8-N/25 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[5 empty] | 900mm | H8-N/26 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[5 empty] | 900mm | H8-N/27 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[5 empty] | Curve with flat panel | H8-N/28 | 4.72 | 1 | 1 | 4.72 | 2351 ,2362,2347 | 234 | 1 | 4.72 | 100% | 0% | 100% | 4.72 | WIR 1086 R1 | 4.49 |  | 0 |  | 0 | -4.72 | -4.72
[6 empty] | H8-N/29 | 4.49 | 1 | 1 | 4.49 | 1065 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Corner panel | H8-N/30 | 2.57 | 1 | 1 | 2.57 | 1386 | 097 | 1 | 2.57 | 100% | 0% | 100% | 2.57 |  | 3.805 | 1 | 3.805 | 100% | 3.805 | 1.235 | 1.235
[9 empty] | TOTAL | 103.05 |  |  | TOTAL | 103.05 | TOTAL |  |  | 103.05 |  |  | TOTAL | 94.739 | TOTAL | 94.739
3 | EWS-101 | 600 | 9 | 1 |  | H9-N/01 | 4.17 | 1 | 1 | 4.17 | 1214,1579 | 046 | 1 | 4.17 | 100% | 0% | 100% | 4.17 |  | 4.155 | 1 | 4.155 | 100% | 4.155 | -0.015 | -0.015
[6 empty] | H9-N/02 | 4.49 | 1 | 1 | 4.49 | 1171,1579 | 026 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H9-N/03 | 4.49 | 1 | 1 | 4.49 | 1171,1579 | 026 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H9-N/04 | 4.49 | 1 | 1 | 4.49 | 1171,1579 | 026 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H9-N/05 | 4.49 | 1 | 1 | 4.49 | 1171,1579 | 026 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H9-N/06 | 4.49 | 1 | 1 | 4.49 | 1171,1579 | 026 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H9-N/07 | 4.49 | 1 | 1 | 4.49 | 1171 | 026 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H9-N/08 | 4.49 | 1 | 1 | 4.49 | 1171 | 026 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H9-N/09 | 4.49 | 1 | 1 | 4.49 | 1171 | 026 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H9-N/10 | 4.49 | 1 | 1 | 4.49 | 1178 | 027 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H9-N/11 | 3.38 | 1 | 1 | 3.38 | 1219 | 048 | 1 | 3.38 | 100% | 0% | 100% | 3.38 |  | 3.365 | 1 | 3.365 | 100% | 3.365 | -0.015 | -0.015
[6 empty] | H9-N/12 | 3.38 | 1 | 1 | 3.38 | 1199 | 037 | 1 | 3.38 | 100% | 0% | 100% | 3.38 |  | 3.365 | 1 | 3.365 | 100% | 3.365 | -0.015 | -0.015
[5 empty] | Curve | H9-N/13 | 3.41 | 1 | 1 | 3.41 |  |  | 1 | 3.41 | 100% | 0% | 100% | 3.41 |  | 3.4 | 1 | 3.4 | 100% | 3.4 | -0.01 | -0.01
[5 empty] | Curve | H9-N/14 | 3.77 | 1 | 1 | 3.77 |  |  | 1 | 3.77 | 100% | 0% | 100% | 3.77 |  | 3.762 | 1 | 3.762 | 100% | 3.762 | -0.008 | -0.008
[6 empty] | H9-N/15 | 3.92 | 1 | 1 | 3.92 | 1178 | 027 | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 | 100% | 3.91 | -0.01 | -0.01
[6 empty] | H9-N/16 | 3.92 | 1 | 1 | 3.92 | 1178 | 027 | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 | 100% | 3.91 | -0.01 | -0.01
[6 empty] | H9-N/17 | 3.92 | 1 | 1 | 3.92 | 1178 | 027 | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 | 100% | 3.91 | -0.01 | -0.01
[6 empty] | H9-N/18 | 3.92 | 1 | 1 | 3.92 | 1178 | 027 | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 | 100% | 3.91 | -0.01 | -0.01
[5 empty] | Curve | H9-N/19 | 3.77 | 1 | 1 | 3.77 |  |  | 1 | 3.77 | 100% | 0% | 100% | 3.77 |  | 3.762 | 1 | 3.762 | 100% | 3.762 | -0.008 | -0.008
[5 empty] | Curve | H9-N/20 | 3.41 | 1 | 1 | 3.41 |  |  | 1 | 3.41 | 100% | 0% | 100% | 3.41 |  | 3.4 | 1 | 3.4 | 100% | 3.4 | -0.01 | -0.01
[6 empty] | H9-N/21 | 3.38 | 1 | 1 | 3.38 | 1214 | 046 | 1 | 3.38 | 100% | 0% | 100% | 3.38 |  | 3.365 | 1 | 3.365 | 100% | 3.365 | -0.015 | -0.015
[6 empty] | H9-N/22 | 3.38 | 1 | 1 | 3.38 | 1214 | 046 | 1 | 3.38 | 100% | 0% | 100% | 3.38 |  | 3.365 | 1 | 3.365 | 100% | 3.365 | -0.015 | -0.015
[6 empty] | H9-N/23 | 4.49 | 1 | 1 | 4.49 | 1178 | 027 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Curve with flat panel | H9-N/24 | 4.72 | 1 | 1 | 4.72 | 1543,2035,2347 | 130,188 | 1 | 4.72 | 100% | 0% | 100% | 4.72 | WIR 1087 R1 | 4.49 |  | 0 |  | 0 | -4.72 | -4.72
[5 empty] | 900mm | H9-N/25 | [7 empty] | - |  |  |  | - | refer to Hotel - 900mm(Qty) worksheet |  |  | - |  | -
[5 empty] | 900mm | H9-N/26 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[5 empty] | 900mm | H9-N/27 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[5 empty] | 900mm | H9-N/28 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[5 empty] | Curve with flat panel | H9-N/29 | 4.72 | 1 | 1 | 4.72 | 1543,2035,2347 | 130,188 | 1 | 4.72 | 100% | 0% | 100% | 4.72 | WIR 1087 R1 | 4.49 |  | 0 |  | 0 | -4.72 | -4.72
[6 empty] | H9-N/30 | 4.49 | 1 | 1 | 4.49 | 1178 | 027 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H9-N/31 | 4.49 | 1 | 1 | 4.49 | 1178 | 027 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H9-N/32 | 4.17 | 1 | 1 | 4.17 | 1214 | 046 | 1 | 4.17 | 100% | 0% | 100% | 4.17 |  | 4.155 | 1 | 4.155 | 100% | 4.155 | -0.015 | -0.015
[5 empty] | Corner panel | H9-N/33 | 5.01 | 1 | 1 | 5.01 | 1386,1395 | 097,099 | 1 | 5.01 | 100% | 0% | 100% | 5.01 |  | 5.03 | 1 | 5.03 | 100% | 5.03 | 0.02 | 0.02
[6 empty] | H9-N/34 | 4.49 | 1 | 1 | 4.49 | 1180 | 028 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H9-N/35 | 4.49 | 1 | 1 | 4.49 | 1180 | 028 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H9-N/36 | 4.49 | 1 | 1 | 4.49 | 1180 | 028 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 842 | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H9-N/37 | 4.49 | 1 | 1 | 4.49 | 1180 | 028 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 842 | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[5 empty] | Corner panel | H9-N/38 | 5.01 | 1 | 1 | 5.01 | 1386,1395 | 097,099 | 1 | 5.01 | 100% | 0% | 100% | 5.01 |  | 5.035 | 1 | 5.035 | 100% | 5.035 | 0.025 | 0.025
[9 empty] | TOTAL | 143.2 |  |  | TOTAL | 143.2 | TOTAL |  |  | 143.2 |  | 142.619 | TOTAL | 133.639 | TOTAL | 124.659
4 | EWS-101 | 600 | 10 | 1 |  | H10-N/01 | 4.17 | 1 | 1 | 4.17 | 1471 | 116 | 1 | 4.17 | 100% | 0% | 100% | 4.17 |  | 4.155 | 1 | 4.155 | 100% | 4.155 | -0.015 | -0.015
[6 empty] | H10-N/02 | 4.49 | 1 | 1 | 4.49 | 1191,1945 | 033,177 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H10-N/03 | 4.49 | 1 | 1 | 4.49 | 1191 | 033 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H10-N/04 | 4.49 | 1 | 1 | 4.49 | 1191 | 033 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H10-N/05 | 4.49 | 1 | 1 | 4.49 | 1191 | 033 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H10-N/06 | 4.49 | 1 | 1 | 4.49 | 1191 | 033 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H10-N/07 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H10-N/08 | 4.49 | 1 | 1 | 4.49 | 1205 | 041 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H10-N/09 | 4.49 | 1 | 1 | 4.49 | 1205 | 041 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H10-N/10 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H10-N/11 | 3.38 | 1 | 1 | 3.38 | 1256 | 065 | 1 | 3.38 | 100% | 0% | 100% | 3.38 |  | 3.365 | 1 | 3.365 | 100% | 3.365 | -0.015 | -0.015
[6 empty] | H10-N/12 | 3.38 | 1 | 1 | 3.38 | 1256 | 065 | 1 | 3.38 | 100% | 0% | 100% | 3.38 |  | 3.365 | 1 | 3.365 | 100% | 3.365 | -0.015 | -0.015
[5 empty] | Curve | H10-N/13 | 3.41 | 1 | 1 | 3.41 | 1395 | 099 | 1 | 3.41 | 100% | 0% | 100% | 3.41 |  | 3.4 | 1 | 3.4 | 100% | 3.4 | -0.01 | -0.01
[5 empty] | Curve | H10-N/14 | 3.77 | 1 | 1 | 3.77 | 1395 | 099 | 1 | 3.77 | 100% | 0% | 100% | 3.77 |  | 3.762 | 1 | 3.762 | 100% | 3.762 | -0.008 | -0.008
[6 empty] | H10-N/15 | 3.92 | 1 | 1 | 3.92 |  |  | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 | 100% | 3.91 | -0.01 | -0.01
[6 empty] | H10-N/16 | 3.92 | 1 | 1 | 3.92 |  |  | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 | 100% | 3.91 | -0.01 | -0.01
[6 empty] | H10-N/17 | 3.92 | 1 | 1 | 3.92 |  |  | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 | 100% | 3.91 | -0.01 | -0.01
[6 empty] | H10-N/18 | 3.92 | 1 | 1 | 3.92 |  |  | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 | 100% | 3.91 | -0.01 | -0.01
[5 empty] | Curve | H10-N/19 | 3.77 | 1 | 1 | 3.77 | 1416 | 104 | 1 | 3.77 | 100% | 0% | 100% | 3.77 |  | 3.762 | 1 | 3.762 | 100% | 3.762 | -0.008 | -0.008
[5 empty] | Curve | H10-N/20 | 3.41 | 1 | 1 | 3.41 | 1408 | 101 | 1 | 3.41 | 100% | 0% | 100% | 3.41 |  | 3.4 | 1 | 3.4 | 100% | 3.4 | -0.01 | -0.01
[6 empty] | H10-N/21 | 3.37 | 1 | 1 | 3.37 | 1256 | 065 | 1 | 3.37 | 100% | 0% | 100% | 3.37 |  | 3.365 | 1 | 3.365 | 100% | 3.365 | -0.005 | -0.005
[6 empty] | H10-N/22 | 3.37 | 1 | 1 | 3.37 | 1256 | 065 | 1 | 3.37 | 100% | 0% | 100% | 3.37 |  | 3.365 | 1 | 3.365 | 100% | 3.365 | -0.005 | -0.005
[6 empty] | H10-N/23 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Curve with flat panel | H10-N/24 | 4.72 | 1 | 1 | 4.72 | 1543,2035,2347 | 130,188 | 1 | 4.72 | 100% | 0% | 100% | 4.72 | WIR 1088 R1 | 4.49 |  | 0 |  | 0 | -4.72 | -4.72
[5 empty] | 900mm | H10-N/25 | [7 empty] | - |  |  |  | - | refer to Hotel - 900mm(Qty) worksheet |  |  | - |  | -
[5 empty] | 900mm | H10-N/26 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[5 empty] | 900mm | H10-N/27 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[5 empty] | 900mm | H10-N/28 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[5 empty] | Curve with flat panel | H10-N/29 | 4.72 | 1 | 1 | 4.72 | 2035 | 188 | 1 | 4.72 | 100% | 0% | 100% | 4.72 | WIR 1088 R1 | 4.49 |  | 0 |  | 0 | -4.72 | -4.72
[6 empty] | H10-N/30 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H10-N/31 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H10-N/32 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.155 | 1 | 4.155 | 100% | 4.155 | -0.335 | -0.335
[5 empty] | Corner panel | H10-N/33 | 5.01 | 1 | 1 | 5.01 |  |  | 1 | 5.01 | 100% | 0% | 100% | 5.01 |  | 5.03 | 1 | 5.03 | 100% | 5.03 | 0.02 | 0.02
[6 empty] | H10-N/34 | 4.49 | 1 | 1 | 4.49 | 1199 | 037 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H10-N/35 | 4.49 | 1 | 1 | 4.49 | 1199 | 037 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H10-N/36 | 4.49 | 1 | 1 | 4.49 | 1199 | 037 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H10-N/37 | 4.49 | 1 | 1 | 4.49 | 1199 | 037 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Corner panel | H10-N/38 | 5.01 | 1 | 1 | 5.01 |  |  | 1 | 5.01 | 100% | 0% | 100% | 5.01 |  | 5.035 | 1 | 5.035 | 100% | 5.035 | 0.025 | 0.025
[9 empty] | TOTAL | 143.5 |  |  | TOTAL | 143.5 | TOTAL |  |  | 143.5 |  |  | TOTAL | 133.639 | TOTAL | 129.149
5 | EWS-101 | 600 | 11 | 1 | Corner panel | H11-N/01 | 2.64 | 1 | 1 | 2.64 | 1419,1450 | 105,110 | 1 | 2.64 | 100% | 0% | 100% | 2.64 |  | 2.635 | 1 | 2.635 | 100% | 2.635 | -0.005 | -0.005
[6 empty] | H11-N/02 | 2.58 | 1 | 1 | 2.58 | 1416 | 104 | 1 | 2.58 | 100% | 0% | 100% | 2.58 |  | 2.605 | 1 | 2.605 | 100% | 2.605 | 0.025 | 0.025
[6 empty] | H11-N/03 | 4.49 | 1 | 1 | 4.49 | 1180 | 028 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H11-N/04 | 4.49 | 1 | 1 | 4.49 | 1180 | 028 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H11-N/05 | 4.49 | 1 | 1 | 4.49 | 1180 | 028 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H11-N/06 | 4.49 | 1 | 1 | 4.49 | 1180 | 028 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H11-N/07 | 4.49 | 1 | 1 | 4.49 | 1186 | 030 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H11-N/08 | 4.49 | 1 | 1 | 4.49 | 1186 | 030 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H11-N/09 | 4.49 | 1 | 1 | 4.49 | 1186 | 030 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H11-N/10 | 4.49 | 1 | 1 | 4.49 | 1186 | 030 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H11-N/11 | 4.49 | 1 | 1 | 4.49 | 1244 | 060 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H11-N/12 | 2.25 | 1 | 1 | 2.25 | 1244 | 060 | 1 | 2.25 | 100% | 0% | 100% | 2.25 |  | 2.24 | 1 | 2.24 | 100% | 2.24 | -0.01 | -0.01
[5 empty] | Curve | H11-N/13 | 3.41 | 1 | 1 | 3.41 | 1386 | 097 | 1 | 3.41 | 100% | 0% | 100% | 3.41 |  | 3.4 | 1 | 3.4 | 100% | 3.4 | -0.01 | -0.01
[5 empty] | Curve | H11-N/14 | 3.77 | 1 | 1 | 3.77 |  |  | 1 | 3.77 | 100% | 0% | 100% | 3.77 |  | 3.762 | 1 | 3.762 | 100% | 3.762 | -0.008 | -0.008
[6 empty] | H11-N/15 | 3.92 | 1 | 1 | 3.92 | 1184 | 029 | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 | 100% | 3.91 | -0.01 | -0.01
[6 empty] | H11-N/16 | 3.92 | 1 | 1 | 3.92 | 1184 | 029 | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 | 100% | 3.91 | -0.01 | -0.01
[6 empty] | H11-N/17 | 3.92 | 1 | 1 | 3.92 | 1184 | 029 | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 | 100% | 3.91 | -0.01 | -0.01
[6 empty] | H11-N/18 | 3.92 | 1 | 1 | 3.92 | 1184 | 029 | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.762 | 1 | 3.762 | 100% | 3.762 | -0.158 | -0.158
[5 empty] | Curve | H11-N/19 | 3.77 | 1 | 1 | 3.77 |  |  | 1 | 3.77 | 100% | 0% | 100% | 3.77 |  | 3.762 | 1 | 3.762 | 100% | 3.762 | -0.008 | -0.008
[5 empty] | Curve | H11-N/20 | 3.41 | 1 | 1 | 3.41 |  |  | 1 | 3.41 | 100% | 0% | 100% | 3.41 |  | 3.4 | 1 | 3.4 | 100% | 3.4 | -0.01 | -0.01
[6 empty] | H11-N/21 | 2.25 | 1 | 1 | 2.25 | 1311 | 081 | 1 | 2.25 | 100% | 0% | 100% | 2.25 |  | 2.24 | 1 | 2.24 | 100% | 2.24 | -0.01 | -0.01
[6 empty] | H11-N/22 | 4.49 | 1 | 1 | 4.49 | 1311 | 081 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H11-N/23 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Curve with flat panel | H11-N/24 | 4.72 | 1 | 1 | 4.72 | 2416 | 237 | 1 | 4.72 | 100% | 0% | 100% | 4.72 | WIR 1089 R1 | 4.49 | 0.66667 | 2.9933 |  | 0 | -1.7267 | -4.72
[5 empty] | 900mm | H11-N/25 | [7 empty] | - |  |  |  | - | refer to Hotel - 900mm(Qty) worksheet |  |  | - |  | -
[5 empty] | 900mm | H11-N/26 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[5 empty] | 900mm | H11-N/27 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[5 empty] | 900mm | H11-N/28 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[5 empty] | Curve with flat panel | H11-N/29 | 4.72 | 1 | 1 | 4.72 | 2419 | 237 | 1 | 4.72 | 100% | 0% | 100% | 4.72 | WIR 1089 R1 | 4.49 |  | 0 |  | 0 | -4.72 | -4.72
[6 empty] | H11-N/30 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[5 empty] | Corner panel | H11-N/31 | 3.31 | 1 | 1 | 3.31 | 1408,1413 | 101,102 | 1 | 3.31 | 100% | 0% | 100% | 3.31 |  | 3.332 | 1 | 3.332 | 100% | 3.332 | 0.022 | 0.022
[9 empty] | TOTAL | 106.39 |  |  | TOTAL | 106.39 | TOTAL |  |  | 106.39 |  |  | TOTAL | 99.7413 | TOTAL | 87.768
6 | EWS-101 | 600 | 12 | 1 |  | H12-N/01 | 4.16 | 1 | 1 | 4.16 | 1471 | 116 | 1 | 4.16 | 100% | 0% | 100% | 4.16 |  | 4.155 | 0.5 | 2.0775 |  | 0 | -2.0825 | -4.16
[6 empty] | H12-N/02 | 4.49 | 1 | 1 | 4.49 | 1463,2092 | 113 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H12-N/03 | 4.49 | 1 | 1 | 4.49 | 1463,2092 | 113 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H12-N/04 | 4.49 | 1 | 1 | 4.49 | 1471 | 116 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H12-N/05 | 4.49 | 1 | 1 | 4.49 | 1471 | 116 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H12-N/06 | 4.49 | 1 | 1 | 4.49 | 1471 | 116 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H12-N/07 | 4.49 | 1 | 1 | 4.49 | 1473 | 118 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H12-N/08 | 4.49 | 1 | 1 | 4.49 | 1473 | 118 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H12-N/09 | 4.49 | 1 | 1 | 4.49 | 1473 | 118 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H12-N/10 | 4.49 | 1 | 1 | 4.49 | 1473 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H12-N/11 | 4.49 | 1 | 1 | 4.49 | 1481 | 121 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H12-N/12 | 4.49 | 1 | 1 | 4.49 | 1684,1840 | 154,167 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H12-N/13 | 4.49 | 1 | 1 | 4.49 | 1697,1706 | 156157 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H12-N/14 | 4.49 | 1 | 1 | 4.49 | 1663 | 152 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H12-N/15 | 4.49 | 1 | 1 | 4.49 | 1663 | 152 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H12-N/16 | 4.49 | 1 | 1 | 4.49 | 1663 | 152 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H12-N/17 | 4.31 | 1 | 1 | 4.31 | 1684 | 154 | 1 | 4.31 | 100% | 0% | 100% | 4.31 |  | 4.297 | 1 | 4.297 | 100% | 4.297 | -0.013 | -0.013
[6 empty] | H12-N/18 | 4.31 | 1 | 1 | 4.31 | 1684 | 154 | 1 | 4.31 | 100% | 0% | 100% | 4.31 |  | 4.297 | 1 | 4.297 | 100% | 4.297 | -0.013 | -0.013
[5 empty] | Curve with C Panel | H12-N/19 | 2.45 | 1 | 1 | 2.45 | 2041,2075,2558,2596 | 189,195,257,262 | 1 | 2.45 | 100% | 0% | 100% | 2.45 |  | 3.762 |  | 0 |  | 0 | -2.45 | -2.45
[5 empty] | Curve with C Panel | H12-N/20 | 3.43 | 1 | 1 | 3.43 | 2041,2075,2558 | 189,195,257 | 1 | 3.43 | 100% | 0% | 100% | 3.43 |  | 2.44 |  | 0 |  | 0 | -3.43 | -3.43
[6 empty] | H12-N/21 | 4.24 | 1 | 1 | 4.24 | 1678,2418 | 153 | 1 | 4.24 | 100% | 0% | 100% | 4.24 |  | 4.228 | 1 | 4.228 |  | 0 | -0.012 | -4.24
[6 empty] | H12-N/22 | 4.24 | 1 | 1 | 4.24 | 1678,2418 | 153 | 1 | 4.24 | 100% | 0% | 100% | 4.24 |  | 4.229 | 0.5 | 2.1145 |  | 0 | -2.1255 | -4.24
[6 empty] | H12-N/23 | 4.24 | 1 | 1 | 4.24 | 1678,2418 | 153 | 1 | 4.24 | 100% | 0% | 100% | 4.24 |  | 4.229 | 1 | 4.229 |  | 0 | -0.011 | -4.24
[6 empty] | H12-N/24 | 4.24 | 1 | 1 | 4.24 | 2068,2479 | 194 | 1 | 4.24 | 100% | 0% | 100% | 4.24 |  | 4.229 |  | 0 |  | 0 | -4.24 | -4.24
[5 empty] | Curve with C Panel | H12-N/25 | 4.2 | 1 | 1 | 4.2 | 2041,2075, 2431,2558 | 189,195,257 | 1 | 4.2 | 100% | 0% | 100% | 4.2 | Scaffolding not handover | 4.072 |  | 0 |  | 0 | -4.2 | -4.2
[5 empty] | Curve with C Panel | H12-N/26 | 4.08 | 1 | 1 | 4.08 | 2041,2075, 2431,2558 | 189,195,257 | 1 | 4.08 | 100% | 0% | 100% | 4.08 | Scaffolding not handover | 4.072 |  | 0 |  | 0 | -4.08 | -4.08
[6 empty] | H12-N/27 | 3.26 | 1 | 1 | 3.26 | 1684 | 154 | 1 | 3.26 | 100% | 0% | 100% | 3.26 | WIR 0594 R2 | 3.254 | 1 | 3.254 | 100% | 3.254 | -0.006 | -0.006
[6 empty] | H12-N/28 | 3.26 | 1 | 1 | 3.26 | 1678 | 153 | 1 | 3.26 | 100% | 0% | 100% | 3.26 | WIR 0594 R2 | 3.254 | 1 | 3.254 | 100% | 3.254 | -0.006 | -0.006
[6 empty] | H12-N/29 | 4.49 | 1 | 1 | 4.49 | 1674 | 153 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 0594 R2 | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H12-N/30 | 4.49 | 1 | 1 | 4.49 | 1674 | 153 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 0594 R2 | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H12-N/31 | 4.49 | 1 | 1 | 4.49 | 1674 | 153 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 0594 R2 | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H12-N/32 | 4.49 | 1 | 1 | 4.49 | 1684, 1686 | 154 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 0594 R2 | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H12-N/33 | 4.49 | 1 | 1 | 4.49 | 1706,1712 | 157159 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 0594 R2 | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H12-N/34 | 4.49 | 1 | 1 | 4.49 | 1684,1686 | 154 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 0594 R2 | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H12-N/35 | 4.49 | 1 | 1 | 4.49 | 1684 | 154 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 0594 R2 | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H12-N/36 | 4.49 | 1 | 1 | 4.49 | 1481 | 121 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H12-N/37 | 4.49 | 1 | 1 | 4.49 | 1481 | 121 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H12-N/38 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | H12-N/39 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | H12-N/40 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | H12-N/41 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | H12-N/42 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | H12-N/43 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | H12-N/44 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H12-N/45 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H12-N/46 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.155 | 1 | 4.155 | 100% | 4.155 | -0.335 | -0.335
[5 empty] | Corner panel | H12-N/47 | 1.82 | 1 | 1 | 1.82 |  |  | 1 | 1.82 | 100% | 0% | 100% | 1.82 |  | 2.135 | 1 | 2.135 | 100% | 2.135 | 0.315 | 0.315
[5 empty] | Corner panel | H12-N/48 | 3.18 | 1 | 1 | 3.18 |  |  | 1 | 3.18 | 100% | 0% | 100% | 3.18 |  | 3.495 | 1 | 3.495 | 100% | 3.495 | 0.315 | 0.315
[6 empty] | H12-N/49 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H12-N/50 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H12-N/51 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H12-N/52 | 4.49 | 1 | 1 | 4.49 | 2025 | 186 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[5 empty] | Corner panel | H12-N/53 | 3.18 | 1 | 1 | 3.18 |  |  | 1 | 3.18 | 100% | 0% | 100% | 3.18 |  | 3.495 | 1 | 3.495 |  | 0 | 0.315 | -3.18
[5 empty] | Corner panel | H12-N/54 | 1.82 | 1 | 1 | 1.82 |  |  | 1 | 1.82 | 100% | 0% | 100% | 1.82 |  | 2.135 |  | 0 |  | 0 | -1.82 | -1.82
[9 empty] | TOTAL | 226.55 |  |  | TOTAL | 199.61 | TOTAL |  |  | 199.61 |  |  | TOTAL | 171.241 | TOTAL | 141.627
7 | EWS-101 | 600 | 13 | 1 |  | H13-N/01 | 4.16 | 1 | 1 | 4.16 | 1413 | 102 | 1 | 4.16 | 100% | 0% | 100% | 4.16 |  | 4.155 | 1 | 4.155 |  | 0 | -0.005 | -4.16
[6 empty] | H13-N/02 | 4.49 | 1 | 1 | 4.49 | 1208 | 043 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 0.5 | 2.245 |  | 0 | -2.245 | -4.49
[6 empty] | H13-N/03 | 4.49 | 1 | 1 | 4.49 | 1208 | 043 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H13-N/04 | 4.49 | 1 | 1 | 4.49 | 1208 | 043 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H13-N/05 | 4.49 | 1 | 1 | 4.49 | 1208 | 043 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H13-N/06 | 4.49 | 1 | 1 | 4.49 | 1208,1840 | 043,167 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H13-N/07 | 4.49 | 1 | 1 | 4.49 | 1208 | 043 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H13-N/08 | 4.49 | 1 | 1 | 4.49 | 1208 | 043 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H13-N/09 | 4.49 | 1 | 1 | 4.49 | 1208 | 043 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H13-N/10 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H13-N/11 | 4.49 | 1 | 1 | 4.49 | 2535 | 256 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H13-N/12 | 4.49 | 1 | 1 | 4.49 | 2100 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H13-N/13 | 4.49 | 1 | 1 | 4.49 | 2092 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H13-N/14 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H13-N/15 | 4.49 | 1 | 1 | 4.49 | 2092 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H13-N/16 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H13-N/17 | 4.49 | 1 | 1 | 4.49 | 1238 | 057 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H13-N/18 | 4.11 | 1 | 1 | 4.11 | 1238 | 057 | 1 | 4.11 | 100% | 0% | 100% | 4.11 |  | 4.104 | 1 | 4.104 | 100% | 4.104 | -0.006 | -0.006
[5 empty] | Curve with C Panel | H13-N/19 | 2.45 | 1 | 1 | 2.45 | 1308,1840 | 080,167 | 1 | 2.45 | 100% | 0% | 100% | 2.45 |  | 2.44 | 1 | 2.44 | 100% | 2.44 | -0.01 | -0.01
[5 empty] | Curve with C Panel | H13-N/20 | 3.43 | 1 | 1 | 3.43 | 1308,1840 | 080,167 | 1 | 3.43 | 100% | 0% | 100% | 3.43 |  | 3.417 | 1 | 3.417 | 100% | 3.417 | -0.013 | -0.013
[6 empty] | H13-N/21 | 4.24 | 1 | 1 | 4.24 |  |  | 1 | 4.24 | 100% | 0% | 100% | 4.24 |  | 4.228 | 1 | 4.228 | 100% | 4.228 | -0.012 | -0.012
[6 empty] | H13-N/22 | 4.24 | 1 | 1 | 4.24 | 1238 | 057 | 1 | 4.24 | 100% | 0% | 100% | 4.24 |  | 4.229 | 1 | 4.229 | 100% | 4.229 | -0.011 | -0.011
[6 empty] | H13-N/23 | 4.24 | 1 | 1 | 4.24 |  |  | 1 | 4.24 | 100% | 0% | 100% | 4.24 |  | 4.229 | 1 | 4.229 | 100% | 4.229 | -0.011 | -0.011
[6 empty] | H13-N/24 | 4.24 | 1 | 1 | 4.24 | 1244 | 060 | 1 | 4.24 | 100% | 0% | 100% | 4.24 |  | 4.229 | 1 | 4.229 | 100% | 4.229 | -0.011 | -0.011
[5 empty] | Curve with C Panel | H13-N/25 | 4.2 | 1 | 1 | 4.2 | 1308,1840 | 080,167 | 1 | 4.2 | 100% | 0% | 100% | 4.2 | WIR 1197 | 4.194 | 1 | 4.194 | 100% | 4.194 | -0.006 | -0.006
[5 empty] | Curve with C Panel | H13-N/26 | 4.08 | 1 | 1 | 4.08 | 1308,1840 | 080,167 | 1 | 4.08 | 100% | 0% | 100% | 4.08 | WIR 1197 | 4.072 | 1 | 4.072 | 100% | 4.072 | -0.008 | -0.008
[6 empty] | H13-N/27 | 2.03 | 1 | 1 | 2.03 |  |  | 1 | 2.03 | 100% | 0% | 100% | 2.03 |  | 2.017 | 1 | 2.017 | 100% | 2.017 | -0.013 | -0.013
[6 empty] | H13-N/28 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H13-N/29 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H13-N/30 | 4.49 | 1 | 1 | 4.49 | 1219 | 048 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H13-N/31 | 4.49 | 1 | 1 | 4.49 | 1219 | 048 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H13-N/32 | 4.49 | 1 | 1 | 4.49 | 1214 | 046 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H13-N/33 | 4.49 | 1 | 1 | 4.49 | 1214 | 046 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H13-N/34 | 4.49 | 1 | 1 | 4.49 | 1214 | 046 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H13-N/35 | 4.49 | 1 | 1 | 4.49 | 1214 | 046 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H13-N/36 | 4.49 | 1 | 1 | 4.49 | 1229 | 053 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H13-N/37 | 4.49 | 1 | 1 | 4.49 | 1229 | 053 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Curve with flat panel | H13-N/38 | 4.72 | 1 | 1 | 4.72 | 2434,2442 | 239,240 | 1 | 4.72 | 100% | 0% | 100% | 4.72 | WIR 1108 R1 | 4.49 |  | 0 |  | 0 | -4.72 | -4.72
[5 empty] | 900mm | H13-N/39 | [7 empty] | - |  |  |  | - | refer to Hotel - 900mm(Qty) worksheet |  |  | - |  | -
[5 empty] | 900mm | H13-N/40 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[5 empty] | 900mm | H13-N/41 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[5 empty] | 900mm | H13-N/42 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[5 empty] | Curve with flat panel | H13-N/43 | 4.72 | 1 | 1 | 4.72 | 2434,2447 | 240 | 1 | 4.72 | 100% | 0% | 100% | 4.72 | WIR 1108 R1 | 4.49 |  | 0 |  | 0 | -4.72 | -4.72
[6 empty] | H13-N/44 | 4.49 | 1 | 1 | 4.49 | 1229 | 053 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H13-N/45 | 4.49 | 1 | 1 | 4.49 | 1229 | 053 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H13-N/46 | 4.49 | 1 | 1 | 4.49 | 1416 | 104 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.155 | 1 | 4.155 | 100% | 4.155 | -0.335 | -0.335
[5 empty] | Corner panel | H13-N/47 | 5.01 | 1 | 1 | 5.01 | 1416 | 104 | 1 | 5.01 | 100% | 0% | 100% | 5.01 |  | 5.03 | 1 | 5.03 | 100% | 5.03 | 0.02 | 0.02
[6 empty] | H13-N/48 | 4.49 | 1 | 1 | 4.49 | 1231 | 054 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H13-N/49 | 4.49 | 1 | 1 | 4.49 | 1231 | 054 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H13-N/50 | 4.49 | 1 | 1 | 4.49 | 1231 | 054 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H13-N/51 | 4.49 | 1 | 1 | 4.49 | 1405,2068 | 100,194 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Corner panel | H13-N/52 | 5.01 | 1 | 1 | 5.01 | 1419 | 105 | 1 | 5.01 | 100% | 0% | 100% | 5.01 |  | 5.03 | 1 | 5.03 |  | 0 | 0.02 | -5.01
[9 empty] | TOTAL | 209.05 |  |  | TOTAL | 209.05 | TOTAL |  |  | 209.05 |  |  | TOTAL | 196.964 | TOTAL | 185.534
8 | EWS-101 | 600 | 14 | 1 | Corner panel | H14-N/01 | 2.58 | 1 | 1 | 2.58 | 1419,1471 | 105,116 | 1 | 2.58 | 100% | 0% | 100% | 2.58 |  | 2.6 | 1 | 2.6 | 100% | 2.6 | 0.02 | 0.02
[6 empty] | H14-N/02 | 4.49 | 1 | 1 | 4.49 | 1244 | 060 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H14-N/03 | 4.49 | 1 | 1 | 4.49 | 1252,1840 | 062,167 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H14-N/04 | 4.49 | 1 | 1 | 4.49 | 1252 | 062 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H14-N/05 | 4.49 | 1 | 1 | 4.49 | 1252 | 062 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H14-N/06 | 4.49 | 1 | 1 | 4.49 | 1252 | 062 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H14-N/07 | 4.49 | 1 | 1 | 4.49 | 1261 | 066 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H14-N/08 | 4.49 | 1 | 1 | 4.49 | 1261 | 066 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H14-N/09 | 4.49 | 1 | 1 | 4.49 | 1261 | 066 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H14-N/10 | 4.49 | 1 | 1 | 4.49 | 1261 | 066 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H14-N/11 | 4.49 | 1 | 1 | 4.49 | 1262 | 067 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H14-N/12 | 4.49 | 1 | 1 | 4.49 | 1254 | 063 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H14-N/13 | 4.49 | 1 | 1 | 4.49 | 1254 | 063 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H14-N/14 | 4.49 | 1 | 1 | 4.49 | 1254 | 063 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H14-N/15 | 4.49 | 1 | 1 | 4.49 | 1254 | 063 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H14-N/16 | 2.68 | 1 | 1 | 2.68 | 1408 | 101 | 1 | 2.68 | 100% | 0% | 100% | 2.68 |  | 2.673 | 1 | 2.673 | 100% | 2.673 | -0.007 | -0.007
[5 empty] | Curve Panel | H14-N/17 | 3.55 | 1 | 1 | 3.55 |  |  | 1 | 3.55 | 100% | 0% | 100% | 3.55 |  | 4.728 | 1 | 4.728 | 100% | 4.728 | 1.178 | 1.178
[5 empty] | Curve Panel | H14-N/18 | 3.4 | 1 | 1 | 3.4 |  |  | 1 | 3.4 | 100% | 0% | 100% | 3.4 |  | 4.597 | 1 | 4.597 | 100% | 4.597 | 1.197 | 1.197
[6 empty] | H14-N/19 | 2.55 | 1 | 1 | 2.55 | 1408 | 101 | 1 | 2.55 | 100% | 0% | 100% | 2.55 |  | 2.542 | 1 | 2.542 | 100% | 2.542 | -0.008 | -0.008
[6 empty] | H14-N/20 | 4.49 | 1 | 1 | 4.49 | 1256 | 065 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H14-N/21 | 4.49 | 1 | 1 | 4.49 | 1256 | 065 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H14-N/22 | 4.49 | 1 | 1 | 4.49 | 1256 | 065 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H14-N/23 | 4.49 | 1 | 1 | 4.49 | 1256 | 065 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H14-N/24 | 4.49 | 1 | 1 | 4.49 | 1264 | 068 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H14-N/25 | 4.49 | 1 | 1 | 4.49 | 1262 | 067 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H14-N/26 | 4.49 | 1 | 1 | 4.49 | 1262 | 067 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H14-N/27 | 4.49 | 1 | 1 | 4.49 | 1264 | 068 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Curve with flat panel | H14-N/28 | 4.72 | 1 | 1 | 4.72 | 2442 | 240 | 1 | 4.72 | 100% | 0% | 100% | 4.72 | WIR 1109 R1 | 4.49 |  | 0 |  | 0 | -4.72 | -4.72
[5 empty] | 900mm | H14-N/29 | [7 empty] | - |  |  |  | - | refer to Hotel - 900mm(Qty) worksheet |  |  | - |  | -
[5 empty] | 900mm | H14-N/30 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[5 empty] | 900mm | H14-N/31 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[5 empty] | 900mm | H14-N/32 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[5 empty] | Curve with flat panel | H14-N/33 | 4.72 | 1 | 1 | 4.72 | 2445 | 240 | 1 | 4.72 | 100% | 0% | 100% | 4.72 | WIR 1109 R1 | 4.49 |  | 0 |  | 0 | -4.72 | -4.72
[6 empty] | H14-N/34 | 4.49 | 1 | 1 | 4.49 | 1262 | 067 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Corner panel | H14-N/35 | 2.58 | 1 | 1 | 2.58 | 1444 | 108 | 1 | 2.58 | 100% | 0% | 100% | 2.58 |  | 3.205 | 1 | 3.205 | 100% | 3.205 | 0.625 | 0.625
[9 empty] | TOTAL | 130.05 |  |  | TOTAL | 130.05 | TOTAL |  |  | 130.05 |  |  | TOTAL | 123.615 | TOTAL | 123.615
9 | EWS-101 | 600 | 15 | 1 |  | H15-N/01 | 4.16 | 1 | 1 | 4.16 | 1413 | 102 | 1 | 4.16 | 100% | 0% | 100% | 4.16 |  | 4.155 | 1 | 4.155 |  | 0 | -0.005 | -4.16
[6 empty] | H15-N/02 | 4.49 | 1 | 1 | 4.49 | 1271 | 070 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H15-N/03 | 4.49 | 1 | 1 | 4.49 | 1271 | 070 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H15-N/04 | 4.49 | 1 | 1 | 4.49 | 1271 | 070 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H15-N/05 | 4.49 | 1 | 1 | 4.49 | 1271 | 070 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H15-N/06 | 4.49 | 1 | 1 | 4.49 | 1273 | 071 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H15-N/07 | 4.49 | 1 | 1 | 4.49 | 1273,1840 | 071,167 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H15-N/08 | 4.49 | 1 | 1 | 4.49 | 1273,1840 | 071,167 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H15-N/09 | 4.49 | 1 | 1 | 4.49 | 1273 | 071 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H15-N/10 | 4.49 | 1 | 1 | 4.49 | 1301 | 078 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H15-N/11 | 4.49 | 1 | 1 | 4.49 | 1277 | 072 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H15-N/12 | 4.49 | 1 | 1 | 4.49 | 1277 | 072 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H15-N/13 | 4.49 | 1 | 1 | 4.49 | 1277 | 072 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H15-N/14 | 4.49 | 1 | 1 | 4.49 | 1273 | 071 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H15-N/15 | 4.49 | 1 | 1 | 4.49 | 1273 | 071 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H15-N/16 | 4.49 | 1 | 1 | 4.49 | 1273 | 071 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H15-N/17 | 4.49 | 1 | 1 | 4.49 | 1273 | 071 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H15-N/18 | 4.11 | 1 | 1 | 4.11 | 1301 | 078 | 1 | 4.11 | 100% | 0% | 100% | 4.11 |  | 4.104 | 1 | 4.104 |  | 0 | -0.006 | -4.11
[5 empty] | Curve with C Panel | H15-N/19 | 2.45 | 1 | 1 | 2.45 | 1315,1322,2599 | 083, 084 | 1 | 2.45 | 100% | 0% | 100% | 2.45 |  | 2.44 | 1 | 2.44 | 100% | 2.44 | -0.01 | -0.01
[5 empty] | Curve with C Panel | H15-N/20 | 3.43 | 1 | 1 | 3.43 | 1316, 1322 | 082, 084 | 1 | 3.43 | 100% | 0% | 100% | 3.43 |  | 3.417 | 1 | 3.417 | 100% | 3.417 | -0.013 | -0.013
[6 empty] | H15-N/21 | 4.24 | 1 | 1 | 4.24 | 1302 | 078 | 1 | 4.24 | 100% | 0% | 100% | 4.24 |  | 4.228 | 1 | 4.228 | 100% | 4.228 | -0.012 | -0.012
[6 empty] | H15-N/22 | 4.24 | 1 | 1 | 4.24 | 1302 | 078 | 1 | 4.24 | 100% | 0% | 100% | 4.24 |  | 4.229 | 1 | 4.229 | 100% | 4.229 | -0.011 | -0.011
[6 empty] | H15-N/23 | 4.24 | 1 | 1 | 4.24 | 1302 | 078 | 1 | 4.24 | 100% | 0% | 100% | 4.24 |  | 4.229 | 1 | 4.229 | 100% | 4.229 | -0.011 | -0.011
[6 empty] | H15-N/24 | 4.24 | 1 | 1 | 4.24 | 1302 | 078 | 1 | 4.24 | 100% | 0% | 100% | 4.24 |  | 4.229 | 1 | 4.229 | 100% | 4.229 | -0.011 | -0.011
[5 empty] | Curve with C Panel | H15-N/25 | 4.2 | 1 | 1 | 4.2 | 1316 | 082 | 1 | 4.2 | 100% | 0% | 100% | 4.2 | WIR 1119 | 4.194 | 1 | 4.194 | 100% | 4.194 | -0.006 | -0.006
[5 empty] | Curve with C Panel | H15-N/26 | 4.08 | 1 | 1 | 4.08 | 1322 | 084 | 1 | 4.08 | 100% | 0% | 100% | 4.08 | WIR 1119 | 4.072 | 1 | 4.072 | 100% | 4.072 | -0.008 | -0.008
[6 empty] | H15-N/27 | 2.03 | 1 | 1 | 2.03 | 1277 | 072 | 1 | 2.03 | 100% | 0% | 100% | 2.03 |  | 2.017 | 1 | 2.017 | 100% | 2.017 | -0.013 | -0.013
[6 empty] | H15-N/28 | 4.49 | 1 | 1 | 4.49 | 1276 | 072 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H15-N/29 | 4.49 | 1 | 1 | 4.49 | 1276 | 072 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H15-N/30 | 4.49 | 1 | 1 | 4.49 | 1276 | 072 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H15-N/31 | 4.49 | 1 | 1 | 4.49 | 1276 | 072 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H15-N/32 | 4.49 | 1 | 1 | 4.49 | 1276 | 072 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H15-N/33 | 4.49 | 1 | 1 | 4.49 | 1276 | 072 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H15-N/34 | 4.49 | 1 | 1 | 4.49 | 1276 | 072 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H15-N/35 | 4.49 | 1 | 1 | 4.49 | 1276 | 072 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H15-N/36 | 4.49 | 1 | 1 | 4.49 | 1277 | 072 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H15-N/37 | 4.49 | 1 | 1 | 4.49 | 1277 | 072 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Curve with flat panel | H15-N/38 | 4.72 | 1 | 1 | 4.72 | 2447 | 240 | 1 | 4.72 | 100% | 0% | 100% | 4.72 | WIR 1110 R1 | 4.49 |  | 0 |  | 0 | -4.72 | -4.72
[5 empty] | 900mm | H15-N/39 | [7 empty] | - |  |  |  | - | refer to Hotel - 900mm(Qty) worksheet |  |  | - |  | -
[5 empty] | 900mm | H15-N/40 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[5 empty] | 900mm | H15-N/41 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[5 empty] | 900mm | H15-N/42 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[5 empty] | Curve with flat panel | H15-N/43 | 4.72 | 1 | 1 | 4.72 | 2450 | 241 | 1 | 4.72 | 100% | 0% | 100% | 4.72 | WIR 1110 R1 | 4.49 |  | 0 |  | 0 | -4.72 | -4.72
[6 empty] | H15-N/44 | 4.49 | 1 | 1 | 4.49 | 1301 | 078 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H15-N/45 | 4.49 | 1 | 1 | 4.49 | 1301 | 078 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H15-N/46 | 4.17 | 1 | 1 | 4.17 | 1413 | 102 | 1 | 4.17 | 100% | 0% | 100% | 4.17 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0.32 | 0.32
[5 empty] | Corner panel | H15-N/47 | 5.01 | 1 | 1 | 5.01 | 1419,1463 | 105,113 | 1 | 5.01 | 100% | 0% | 100% | 5.01 |  | 5.03 | 1 | 5.03 | 100% | 5.03 | 0.02 | 0.02
[6 empty] | H15-N/48 | 4.49 | 1 | 1 | 4.49 | 1301 | 078 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H15-N/49 | 4.49 | 1 | 1 | 4.49 | 1301 | 078 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H15-N/50 | 4.49 | 1 | 1 | 4.49 | 1301 | 078 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H15-N/51 | 4.49 | 1 | 1 | 4.49 | 1301 | 078 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[5 empty] | Corner panel | H15-N/52 | 5.01 | 1 | 1 | 5.01 | 1419,1473 | 052,118 | 1 | 5.01 | 100% | 0% | 100% | 5.01 |  | 5.03 | 1 | 5.03 |  | 0 | 0.02 | -5.01
[9 empty] | TOTAL | 208.73 |  |  | TOTAL | 208.73 | TOTAL |  |  | 208.73 |  |  | TOTAL | 199.544 | TOTAL | 159.315
10 | EWS-101 | 600 | 16 | 1 | Corner panel | H16-N/01 | 2.58 | 1 | 1 | 2.58 | 1532 | 130 | 1 | 2.58 | 100% | 0% | 100% | 2.58 |  | 2.605 | 1 | 2.605 | 100% | 2.605 | 0.025 | 0.025
[6 empty] | H16-N/02 | 4.49 | 1 | 1 | 4.49 | 1264 | 068 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H16-N/03 | 4.49 | 1 | 1 | 4.49 | 1265 | 068 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H16-N/04 | 4.49 | 1 | 1 | 4.49 | 1265,2092 | 068 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H16-N/05 | 4.49 | 1 | 1 | 4.49 | 1265,2092 | 068 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H16-N/06 | 4.49 | 1 | 1 | 4.49 | 1265 | 068 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H16-N/07 | 4.49 | 1 | 1 | 4.49 | 1231,2099 | 054 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H16-N/08 | 4.49 | 1 | 1 | 4.49 | 1267 | 069 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H16-N/09 | 4.49 | 1 | 1 | 4.49 | 1267 | 069 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H16-N/10 | 4.49 | 1 | 1 | 4.49 | 1267 | 069 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H16-N/11 | 4.49 | 1 | 1 | 4.49 | 1267 | 069 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H16-N/12 | 4.49 | 1 | 1 | 4.49 | 1262 | 067 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H16-N/13 | 4.49 | 1 | 1 | 4.49 | 1262 | 067 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H16-N/14 | 4.49 | 1 | 1 | 4.49 | 1262 | 067 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H16-N/15 | 4.49 | 1 | 1 | 4.49 | 1262 | 067 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H16-N/16 | 2.68 | 1 | 1 | 2.68 | 1532 | 130 | 1 | 2.68 | 100% | 0% | 100% | 2.68 |  | 2.673 | 1 | 2.673 | 100% | 2.673 | -0.007 | -0.007
[5 empty] | Curve Panel | H16-N/17 | 3.57 | 1 | 1 | 3.57 |  |  | 1 | 3.57 | 100% | 0% | 100% | 3.57 |  | 4.728 | 1 | 4.728 | 100% | 4.728 | 1.158 | 1.158
[5 empty] | Curve Panel | H16-N/18 | 3.4 | 1 | 1 | 3.4 |  |  | 1 | 3.4 | 100% | 0% | 100% | 3.4 |  | 4.597 | 1 | 4.597 | 100% | 4.597 | 1.197 | 1.197
[6 empty] | H16-N/19 | 2.55 | 1 | 1 | 2.55 | 1532 | 130 | 1 | 2.55 | 100% | 0% | 100% | 2.55 |  | 2.542 | 1 | 2.542 | 100% | 2.542 | -0.008 | -0.008
[6 empty] | H16-N/20 | 4.49 | 1 | 1 | 4.49 | 1264 | 068 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H16-N/21 | 4.49 | 1 | 1 | 4.49 | 1264 | 068 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H16-N/22 | 4.49 | 1 | 1 | 4.49 | 1264 | 068 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H16-N/23 | 4.49 | 1 | 1 | 4.49 | 1264 | 068 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H16-N/24 | 4.49 | 1 | 1 | 4.49 | 1264 | 068 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H16-N/25 | 4.49 | 1 | 1 | 4.49 | 1267 | 069 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H16-N/26 | 4.49 | 1 | 1 | 4.49 | 1267 | 069 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H16-N/27 | 4.49 | 1 | 1 | 4.49 | 1267 | 069 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Curve with flat panel | H16-N/28 | 4.72 | 1 | 1 | 4.72 | 2471 | 244 | 1 | 4.72 | 100% | 0% | 100% | 4.72 | WIR 1153 R1 | 4.49 |  | 0 |  | 0 | -4.72 | -4.72
[5 empty] | 900mm | H16-N/29 | [7 empty] | - |  |  |  | - | refer to Hotel - 900mm(Qty) worksheet |  |  | - |  | -
[5 empty] | 900mm | H16-N/30 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[5 empty] | 900mm | H16-N/31 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[5 empty] | 900mm | H16-N/32 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[5 empty] | Curve with flat panel | H16-N/33 | 4.72 | 1 | 1 | 4.72 | 2446,2471 | 240 | 1 | 4.72 |  |  |  | 0 | WIR 1153 R1 | 4.49 |  | 0 |  | 0 | -4.72 | 0
[6 empty] | H16-N/34 | 4.49 | 1 | 1 | 4.49 | 1267 | 069 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Corner panel | H16-N/35 | 2.58 | 1 | 1 | 2.58 | 1734 | 160 | 1 | 2.58 | 100% | 0% | 100% | 2.58 |  | 3.205 | 1 | 3.205 | 100% | 3.205 | 0.625 | 0.625
[9 empty] | TOTAL | 130.07 |  |  | TOTAL | 130.07 | TOTAL |  |  | 125.35 |  |  | TOTAL | 123.62 | TOTAL | 123.62
11 | EWS-101 | 600 | 17 | 1 |  | H17-N/01 | 6.02 | 1 | 1 | 6.02 | 2011 | 185 | 1 | 6.02 | 100% | 0% | 100% | 6.02 |  | 4.155 | 1 | 4.155 |  | 0 | -1.865 | -6.02
[6 empty] | H17-N/02 | 4.49 | 1 | 1 | 4.49 | 2011 | 185 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H17-N/03 | 4.49 | 1 | 1 | 4.49 | 1847 | 168 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H17-N/04 | 4.49 | 1 | 1 | 4.49 | 1847 | 168 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H17-N/05 | 4.49 | 1 | 1 | 4.49 | 1847,3106 | 168324 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H17-N/06 | 4.49 | 1 | 1 | 4.49 | 1847,3106 | 168324 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H17-N/07 | 4.49 | 1 | 1 | 4.49 | 1853 | 168 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H17-N/08 | 4.49 | 1 | 1 | 4.49 | 1853 | 168 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H17-N/09 | 4.49 | 1 | 1 | 4.49 | 1853 | 168 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H17-N/10 | 4.49 | 1 | 1 | 4.49 | 1853 | 168 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H17-N/11 | 4.49 | 1 | 1 | 4.49 | 1672 | 152 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H17-N/12 | 4.49 | 1 | 1 | 4.49 | 1712 | 159 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H17-N/13 | 4.49 | 1 | 1 | 4.49 | 1706,1847 | 157,168 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H17-N/14 | 4.49 | 1 | 1 | 4.49 | 1706 | 157 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H17-N/15 | 4.49 | 1 | 1 | 4.49 | 1706 | 157 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H17-N/16 | 4.49 | 1 | 1 | 4.49 | 1706,1847 | 157,168 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H17-N/17 | 4.31 | 1 | 1 | 4.31 | 1749 | 161 | 1 | 4.31 | 100% | 0% | 100% | 4.31 |  | 4.297 | 1 | 4.297 | 100% | 4.297 | -0.013 | -0.013
[6 empty] | H17-N/18 | 4.31 | 1 | 1 | 4.31 | 1758 | 161 | 1 | 4.31 | 100% | 0% | 100% | 4.31 |  | 4.297 | 1 | 4.297 | 100% | 4.297 | -0.013 | -0.013
[5 empty] | Curve Panel | H17-N/19 | 2.47 | 1 | 1 | 2.47 | 1771 | 162 | 1 | 2.47 | 100% | 0% | 100% | 2.47 |  | 2.461 | 1 | 2.461 | 100% | 2.461 | -0.009 | -0.009
[5 empty] | Curve Panel | H17-N/20 | 3.45 | 1 | 1 | 3.45 | 1771 | 162 | 1 | 3.45 | 100% | 0% | 100% | 3.45 |  | 3.438 | 1 | 3.438 | 100% | 3.438 | -0.012 | -0.012
[6 empty] | H17-N/21 | 4.24 | 1 | 1 | 4.24 | 1672 | 152 | 1 | 4.24 | 100% | 0% | 100% | 4.24 |  | 4.225 | 1 | 4.225 | 100% | 4.225 | -0.015 | -0.015
[6 empty] | H17-N/22 | 4.24 | 1 | 1 | 4.24 | 1795 | 164 | 1 | 4.24 | 100% | 0% | 100% | 4.24 |  | 4.229 | 1 | 4.229 | 100% | 4.229 | -0.011 | -0.011
[6 empty] | H17-N/23 | 4.24 | 1 | 1 | 4.24 | 1795 | 164 | 1 | 4.24 | 100% | 0% | 100% | 4.24 |  | 4.229 | 1 | 4.229 | 100% | 4.229 | -0.011 | -0.011
[6 empty] | H17-N/24 | 4.24 | 1 | 1 | 4.24 | 2100 |  | 1 | 4.24 | 100% | 0% | 100% | 4.24 |  | 4.229 | 1 | 4.229 |  | 0 | -0.011 | -4.24
[5 empty] | Curve Panel | H17-N/25 | 4.24 | 1 | 1 | 4.24 | 2100 |  | 1 | 4.24 | 100% | 0% | 100% | 4.24 |  | 4.229 | 1 | 4.229 |  | 0 | -0.011 | -4.24
[5 empty] | Curve Panel | H17-N/26 | 4.12 | 1 | 1 | 4.12 | 1840 | 167 | 1 | 4.12 | 100% | 0% | 100% | 4.12 |  | 4.107 | 1 | 4.107 |  | 0 | -0.013 | -4.12
[6 empty] | H17-N/27 | 3.26 | 1 | 1 | 3.26 | 1840 | 167 | 1 | 3.26 | 100% | 0% | 100% | 3.26 |  | 3.254 | 1 | 3.254 | 100% | 3.254 | -0.006 | -0.006
[6 empty] | H17-N/28 | 3.26 | 1 | 1 | 3.26 | 1840 | 167 | 1 | 3.26 | 100% | 0% | 100% | 3.26 |  | 3.254 | 1 | 3.254 | 100% | 3.254 | -0.006 | -0.006
[6 empty] | H17-N/29 | 4.49 | 1 | 1 | 4.49 | 1806 | 165 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H17-N/30 | 4.49 | 1 | 1 | 4.49 | 1840 | 167 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H17-N/31 | 4.49 | 1 | 1 | 4.49 | 1795 | 164 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H17-N/32 | 4.49 | 1 | 1 | 4.49 | 1795 | 164 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H17-N/33 | 4.49 | 1 | 1 | 4.49 | 1795 | 164 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H17-N/34 | 4.49 | 1 | 1 | 4.49 | 1795 | 164 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H17-N/35 | 4.49 | 1 | 1 | 4.49 | 1806,1818 | 165 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H17-N/36 | 4.49 | 1 | 1 | 4.49 | 1818 | 165 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H17-N/37 | 4.49 | 1 | 1 | 4.49 | 1818 | 165 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H17-N/38 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | H17-N/39 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | H17-N/40 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | H17-N/41 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | H17-N/42 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | H17-N/43 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | H17-N/44 | 4.49 | 1 | 1 | 4.49 | 2015 | 185 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H17-N/45 | 4.49 | 1 | 1 | 4.49 | 2009 | 183 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H17-N/46 | 4.17 | 1 | 1 | 4.17 | 2015 | 185 | 1 | 4.17 | 100% | 0% | 100% | 4.17 |  | 4.155 |  | 0 |  | 0 | -4.17 | -4.17
[5 empty] | Corner Panel | H17-N/47 | 5.08 | 1 | 1 | 5.08 | 2020 |  | 1 | 5.08 | 100% | 0% | 100% | 5.08 |  | 5.63 |  | 0 |  | 0 | -5.08 | -5.08
[6 empty] | H17-N/48 | 4.49 | 1 | 1 | 4.49 | 2011 | 185 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H17-N/49 | 4.49 | 1 | 1 | 4.49 | 2020 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H17-N/50 | 4.49 | 1 | 1 | 4.49 | 2020 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H17-N/51 | 4.49 | 1 | 1 | 4.49 | 2015 | 185 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H17-N/52 | 5.08 | 1 | 1 | 5.08 | 2011,2020 | 185 | 1 | 5.08 | 100% | 0% | 100% | 5.08 |  | 5.63 |  | 0 |  | 0 | -5.08 | -5.08
[9 empty] | TOTAL | 228.37 |  |  | TOTAL | 201.43 | TOTAL |  |  | 201.43 |  |  | TOTAL | 153.674 | TOTAL | 101.034
12 | EWS-101 | 600 | 18 | 1 |  | H18-N/01 | 4.49 | 1 | 1 | 4.49 | 1289,1989 | 079,183 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H18-N/02 | 4.49 | 1 | 1 | 4.49 | 1289 | 079 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H18-N/03 | 4.49 | 1 | 1 | 4.49 | 1289 | 079 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H18-N/04 | 4.49 | 1 | 1 | 4.49 | 1289 | 079 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H18-N/05 | 4.49 | 1 | 1 | 4.49 | 1289 | 079 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H18-N/06 | 4.49 | 1 | 1 | 4.49 | 1289 | 079 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H18-N/07 | 4.49 | 1 | 1 | 4.49 | 1289 | 079 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H18-N/08 | 4.49 | 1 | 1 | 4.49 | 1289 | 079 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H18-N/09 | 4.49 | 1 | 1 | 4.49 | 1294 | 077 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H18-N/10 | 3.45 | 1 | 1 | 3.45 | 1294 | 077 | 1 | 3.45 | 100% | 0% | 100% | 3.45 |  | 3.44 | 1 | 3.44 | 100% | 3.44 | -0.01 | -0.01
[5 empty] | Curve with C-panel | H18-N/11 | 3.27 | 1 | 1 | 3.27 | 1532,1989 | 130,183 | 1 | 3.27 | 100% | 0% | 100% | 3.27 |  | 3.256 | 1 | 3.256 |  | 0 | -0.014 | -3.27
[5 empty] | Curve with C-panel | H18-N/12 | 3.77 | 1 | 1 | 3.77 | 1499,1989 | 126183 | 1 | 3.77 | 100% | 0% | 100% | 3.77 |  | 3.755 | 0.5 | 1.8775 |  | 0 | -1.8925 | -3.77
[6 empty] | H18-N/13 | 3.92 | 1 | 1 | 3.92 | 1292 | 076 | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 |  | 0 | -0.01 | -3.92
[6 empty] | H18-N/14 | 3.92 | 1 | 1 | 3.92 | 1292 | 076 | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 |  | 0 | -0.01 | -3.92
[6 empty] | H18-N/15 | 3.92 | 1 | 1 | 3.92 | 1292 | 076 | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 |  | 0 | -0.01 | -3.92
[6 empty] | H18-N/16 | 3.92 | 1 | 1 | 3.92 | 1292 | 076 | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 |  | 0 | -0.01 | -3.92
[5 empty] | Curve with C-panel | H18-N/17 | 3.77 | 1 | 1 | 3.77 | 1499,1989, 2510 | 126183 | 1 | 3.77 | 100% | 0% | 100% | 3.77 | WIR 1177 | 4.728 | 0.66667 | 3.152 |  | 0 | -0.618 | -3.77
[5 empty] | Curve with C-panel | H18-N/18 | 3.27 | 1 | 1 | 3.27 | 1989,2041, 1989,2510 | 183,189 | 1 | 3.27 | 100% | 0% | 100% | 3.27 | WIR 1177 | 4.597 |  | 0 |  | 0 | -3.27 | -3.27
[6 empty] | H18-N/19 | 3.45 | 1 | 1 | 3.45 | 1291 | 076 | 1 | 3.45 | 100% | 0% | 100% | 3.45 |  | 3.44 | 1 | 3.44 | 100% | 3.44 | -0.01 | -0.01
[5 empty] | Curve with C-panel | H18-N/20 | 4.72 | 1 | 1 | 4.72 | 2481,2482 |  | 1 | 4.72 |  | 0% | 0% | 0 |  | 4.49 |  | 0 |  | 0 | -4.72 | 0
[6 empty] | H18-N/21 | [7 empty] | - |  |  |  | - | refer to Hotel - 900mm(Qty) worksheet |  |  | - |  | -
[6 empty] | H18-N/22 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[6 empty] | H18-N/23 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[6 empty] | H18-N/24 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[5 empty] | Curve with C-panel | H18-N/25 | 4.72 | 1 | 1 | 4.72 | 2481,2491,2714 | 284 | 1 | 4.72 |  |  |  | 0 |  | 4.49 |  | 0 |  | 0 | -4.72 | 0
[6 empty] | H18-N/26 | 4.49 | 1 | 1 | 4.49 | 1291 | 076 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H18-N/27 | 4.49 | 1 | 1 | 4.49 | 1291 | 076 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H18-N/28 | 4.49 | 1 | 1 | 4.49 | 1291,1989 | 076,183 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Corner Panel | H18-N/29 | 4.67 | 1 | 1 | 4.67 | 1652 | 149 | 1 | 4.67 | 100% | 0% | 100% | 4.67 |  | 4.63 | 1 | 4.63 | 100% | 4.63 | -0.04 | -0.04
[6 empty] | H18-N/30 | 4.49 | 1 | 1 | 4.49 | 1291 | 076 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H18-N/31 | 4.49 | 1 | 1 | 4.49 | 1291 | 076 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H18-N/32 | 4.49 | 1 | 1 | 4.49 | 1291 | 076 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H18-N/33 | 4.49 | 1 | 1 | 4.49 | 1291,2059 | 076,191 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1145 | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[5 empty] | Corner Panel | H18-N/34 | 4.67 | 1 | 1 | 4.67 | 1734,1989 | 160,183 | 1 | 4.67 | 100% | 0% | 100% | 4.67 |  | 5.295 | 1 | 5.295 |  | 0 | 0.625 | -4.67
[9 empty] | TOTAL | 127.28 |  |  | TOTAL | 127.28 | TOTAL |  |  | 117.84 |  |  | TOTAL | 108.0805 | TOTAL | 69.88
13 | EWS-101 | 600 | 19 | 1 | Corner Panel | H19-N/01 | 2.58 | 1 | 1 | 2.58 | 1734 | 160 | 1 | 2.58 | 100% | 0% | 100% | 2.58 | Scaffolding not handover | 2.605 | 0.5 | 1.3025 |  | 0 | -1.2775 | -2.58
[6 empty] | H19-N/02 | 4.49 | 1 | 1 | 4.49 | 1296 | 077 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H19-N/03 | 4.49 | 1 | 1 | 4.49 | 1296 | 077 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H19-N/04 | 4.49 | 1 | 1 | 4.49 | 1296 | 077 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H19-N/05 | 4.49 | 1 | 1 | 4.49 | 1296 | 077 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H19-N/06 | 4.49 | 1 | 1 | 4.49 | 1295 | 077 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H19-N/07 | 4.49 | 1 | 1 | 4.49 | 1295 | 077 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H19-N/08 | 4.49 | 1 | 1 | 4.49 | 1567 | 133 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H19-N/09 | 3.45 | 1 | 1 | 3.45 |  |  | 1 | 3.45 | 100% | 0% | 100% | 3.45 |  | 3.44 | 0.5 | 1.72 |  | 0 | -1.73 | -3.45
[6 empty] | H19-N/10 | 3.27 | 1 | 1 | 3.27 | 1567,1896 | 133173 | 1 | 3.27 | 100% | 0% | 100% | 3.27 | WIR 1037 | 3.256 |  | 0 |  | 0 | -3.27 | -3.27
[6 empty] | H19-N/11 | 3.77 | 1 | 1 | 3.77 | 1567,1896 | 133173 | 1 | 3.77 | 100% | 0% | 100% | 3.77 | WIR 1037 | 3.755 |  | 0 |  | 0 | -3.77 | -3.77
[6 empty] | H19-N/12 | 3.92 | 1 | 1 | 3.92 | 1567 | 133 | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 | 100% | 3.91 | -0.01 | -0.01
[6 empty] | H19-N/13 | 3.92 | 1 | 1 | 3.92 | 1567 | 133 | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 | 100% | 3.91 | -0.01 | -0.01
[6 empty] | H19-N/14 | 3.92 | 1 | 1 | 3.92 | 1567 | 133 | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 | 100% | 3.91 | -0.01 | -0.01
[6 empty] | H19-N/15 | 3.92 | 1 | 1 | 3.92 | 1567 | 133 | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 | 100% | 3.91 | -0.01 | -0.01
[6 empty] | H19-N/16 | 3.77 | 1 | 1 | 3.77 | 1567,1896 | 133173 | 1 | 3.77 | 100% | 0% | 100% | 3.77 |  | 3.755 |  | 0 |  | 0 | -3.77 | -3.77
[6 empty] | H19-N/17 | 3.27 | 1 | 1 | 3.27 | 1567,2041 | 133,189 | 1 | 3.27 | 100% | 0% | 100% | 3.27 | WIR 1037 | 3.256 | 0.5 | 1.628 |  | 0 | -1.642 | -3.27
[6 empty] | H19-N/18 | 3.45 | 1 | 1 | 3.45 | 1567 | 133 | 1 | 3.45 | 100% | 0% | 100% | 3.45 | WIR 1037 | 3.44 | 0.5 | 1.72 |  | 0 | -1.73 | -3.45
[5 empty] | Curve with C-panel | H19-N/19 | 4.77 | 1 | 1 | 4.77 | 2489 |  | 1 | 4.77 | 100% | 0% | 100% | 4.77 | WIR 1209 | 4.49 |  | 0 |  | 0 | -4.77 | -4.77
[6 empty] | H19-N/20 | [7 empty] | - |  |  |  | - | refer to Hotel - 900mm(Qty) worksheet |  |  | - |  | -
[6 empty] | H19-N/21 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[6 empty] | H19-N/22 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[6 empty] | H19-N/23 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[5 empty] | Curve with C-panel | H19-N/24 | 4.77 | 1 | 1 | 4.77 | 2491 |  | 1 | 4.77 | 100% | 0% | 100% | 4.77 | WIR 1209 | 4.49 |  | 0 |  | 0 | -4.77 | -4.77
[6 empty] | H19-N/25 | 4.49 | 1 | 1 | 4.49 | 1296 | 077 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[5 empty] | Corner Panel | H19-N/26 | 2.58 | 1 | 1 | 2.58 | 1896 | 173 | 1 | 2.58 | 100% | 0% | 100% | 2.58 | Scaffolding not handover | 2.605 |  | 0 |  | 0 | -2.58 | -2.58
[9 empty] | TOTAL | 87.28 |  |  | TOTAL | 87.28 | TOTAL |  |  | 87.28 |  |  | TOTAL | 53.4405 | TOTAL | 15.64
13 | EWS-101 | 600 | 20 | 1 |  | H20-N/01 | 4.49 | 1 | 1 | 4.49 | 1645 | 148 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H20-N/02 | 4.49 | 1 | 1 | 4.49 | 1295 | 077 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H20-N/03 | 4.49 | 1 | 1 | 4.49 | 1294, 1296 | 077 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H20-N/04 | 4.49 | 1 | 1 | 4.49 | 1295 | 077 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H20-N/05 | 4.49 | 1 | 1 | 4.49 | 1295 | 077 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H20-N/06 | 4.49 | 1 | 1 | 4.49 | 1294, 1296 | 077 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H20-N/07 | 4.49 | 1 | 1 | 4.49 | 1294, 1296 | 077 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H20-N/08 | 4.49 | 1 | 1 | 4.49 | 1304 | 079 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H20-N/09 | 4.49 | 1 | 1 | 4.49 | 1294, 1296 | 077 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H20-N/10 | 3.45 | 1 | 1 | 3.45 | 1645 | 148 | 1 | 3.45 | 100% | 0% | 100% | 3.45 |  | 3.44 |  | 0 |  | 0 | -3.45 | -3.45
[5 empty] | Curve with C-panel | H20-N/11 | 3.27 | 1 | 1 | 3.27 | 1645,1765 | 148,162 | 1 | 3.27 | 100% | 0% | 100% | 3.27 | WIR 1059 R1 | 3.256 | 1 | 3.256 | 100% | 3.256 | -0.014 | -0.014
[5 empty] | Curve with C-panel | H20-N/12 | 3.277 | 1 | 1 | 3.277 | 1650,1765 | 149,162 | 1 | 3.277 | 100% | 0% | 100% | 3.277 | WIR 1059 R1 | 3.755 | 1 | 3.755 | 100% | 3.755 | 0.478 | 0.478
[6 empty] | H20-N/13 | 3.92 | 1 | 1 | 3.92 | 1316 | 082 | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 | 100% | 3.91 | -0.01 | -0.01
[6 empty] | H20-N/14 | 3.92 | 1 | 1 | 3.92 | 1315 | 083 | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 | 100% | 3.91 | -0.01 | -0.01
[6 empty] | H20-N/15 | 3.92 | 1 | 1 | 3.92 | 1315 | 083 | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 | 100% | 3.91 | -0.01 | -0.01
[6 empty] | H20-N/16 | 3.92 | 1 | 1 | 3.92 | 1315 | 083 | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 | 100% | 3.91 | -0.01 | -0.01
[5 empty] | Curve with C-panel | H20-N/17 | 3.77 | 1 | 1 | 3.77 | 1650 | 149 | 1 | 3.77 | 100% | 0% | 100% | 3.77 | WIR 1059 R1 | 3.755 | 1 | 3.755 | 100% | 3.755 | -0.015 | -0.015
[5 empty] | Curve with C-panel | H20-N/18 | 3.27 | 1 | 1 | 3.27 | 1650 | 149 | 1 | 3.27 | 100% | 0% | 100% | 3.27 | WIR 1059 R1 | 3.256 | 1 | 3.256 | 100% | 3.256 | -0.014 | -0.014
[6 empty] | H20-N/19 | 3.45 | 1 | 1 | 3.45 | 1650,1672 | 149,152 | 1 | 3.45 | 100% | 0% | 100% | 3.45 |  | 3.44 | 1 | 3.44 | 100% | 3.44 | -0.01 | -0.01
[5 empty] | Curve with C-panel | H20-N/20 | 4.72 | 1 | 1 | 4.72 | 2499 | 249 | 1 | 4.72 | 100% | 0% | 100% | 4.72 | WIR 1183 R1 | 4.49 |  | 0 |  | 0 | -4.72 | -4.72
[6 empty] | H20-N/21 | [7 empty] | - |  |  |  | - | refer to Hotel - 900mm(Qty) worksheet |  |  | - |  | -
[6 empty] | H20-N/22 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[6 empty] | H20-N/23 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[6 empty] | H20-N/24 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[5 empty] | Curve with C-panel | H20-N/25 | 4.72 | 1 | 1 | 4.72 | 2496,2563 | 249,259 | 1 | 4.72 | 100% | 0% | 100% | 4.72 | WIR 1183 R1 | 4.49 |  | 0 |  | 0 | -4.72 | -4.72
[6 empty] | H20-N/26 | 4.49 | 1 | 1 | 4.49 | 1294, 1296 | 077 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H20-N/27 | 4.49 | 1 | 1 | 4.49 | 1294, 1296 | 077 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H20-N/28 | 4.49 | 1 | 1 | 4.49 | 2033 | 187 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[5 empty] | Corner Panel | H20-N/29 | 4.67 | 1 | 1 | 4.67 | 2026 | 187 | 1 | 4.67 | 100% | 0% | 100% | 4.67 |  | 4.63 |  | 0 |  | 0 | -4.67 | -4.67
[6 empty] | H20-N/30 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H20-N/31 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H20-N/32 | 4.49 | 1 | 1 | 4.49 | 1296 | 077 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H20-N/33 | 4.49 | 1 | 1 | 4.49 | 1304 | 079 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[5 empty] | Corner Panel | H20-N/34 | 4.67 | 1 | 1 | 4.67 | 2031 | 187 | 1 | 4.67 | 100% | 0% | 100% | 4.67 |  | 5.295 |  | 0 |  | 0 | -4.67 | -4.67
[9 empty] | TOTAL | 126.787 |  |  | TOTAL | 126.787 | TOTAL |  |  | 126.787 |  |  | TOTAL | 100.452 | TOTAL | 64.532
14 | EWS-101 | 600 | 21 | 1 | Corner Panel | H21-N/01 | 2.58 | 1 | 1 | 2.58 | 17951787 | 164 | 1 | 2.58 | 100% | 0% | 100% | 2.58 | WIR 229 | 2.605 | 1 | 2.605 |  | 0 | 0.025 | -2.58
[6 empty] | H21-N/02 | 4.49 | 1 | 1 | 4.49 | 1391 | 098 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 901 | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H21-N/03 | 4.49 | 1 | 1 | 4.49 | 1391 | 098 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H21-N/04 | 4.49 | 1 | 1 | 4.49 | 1391 | 098 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H21-N/05 | 4.49 | 1 | 1 | 4.49 | 1381 | 096 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H21-N/06 | 4.49 | 1 | 1 | 4.49 | 1381 | 096 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H21-N/07 | 4.49 | 1 | 1 | 4.49 | 1381 | 096 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H21-N/08 | 4.49 | 1 | 1 | 4.49 | 1381 | 096 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H21-N/09 | 3.45 | 1 | 1 | 3.45 | 1391 | 098 | 1 | 3.45 | 100% | 0% | 100% | 3.45 |  | 3.44 | 1 | 3.44 | 100% | 3.44 | -0.01 | -0.01
[6 empty] | H21-N/10 | 3.27 | 1 | 1 | 3.27 | 1543,1672 | 130,152 | 1 | 3.27 | 100% | 0% | 100% | 3.27 |  | 3.256 | 1 | 3.256 | 66.67% | 2.1707 | -0.014 | -1.0993
[6 empty] | H21-N/11 | 3.77 | 1 | 1 | 3.77 | 1543,1672 | 130,152 | 1 | 3.77 | 100% | 0% | 100% | 3.77 |  | 3.755 | 1 | 3.755 | 66.67% | 2.5033 | -0.015 | -1.2667
[6 empty] | H21-N/12 | 3.92 | 1 | 1 | 3.92 | 1405 | 100 | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 | 100% | 3.91 | -0.01 | -0.01
[6 empty] | H21-N/13 | 3.92 | 1 | 1 | 3.92 | 1413 | 102 | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 | 100% | 3.91 | -0.01 | -0.01
[6 empty] | H21-N/14 | 3.92 | 1 | 1 | 3.92 | 1391,1405 | 098,100 | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 | 100% | 3.91 | -0.01 | -0.01
[6 empty] | H21-N/15 | 3.92 | 1 | 1 | 3.92 | 1405 | 100 | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 | 100% | 3.91 | -0.01 | -0.01
[6 empty] | H21-N/16 | 3.77 | 1 | 1 | 3.77 | 1543,1734 | 130160 | 1 | 3.77 | 100% | 0% | 100% | 3.77 |  | 3.755 | 1 | 3.755 | 66.67% | 2.5033 | -0.015 | -1.2667
[6 empty] | H21-N/17 | 3.27 | 1 | 1 | 3.27 | 1543,1734 | 130160 | 1 | 3.27 | 100% | 0% | 100% | 3.27 |  | 3.256 | 1 | 3.256 | 66.67% | 2.1707 | -0.014 | -1.0993
[6 empty] | H21-N/18 | 3.45 | 1 | 1 | 3.45 | 1391 | 098 | 1 | 3.45 | 100% | 0% | 100% | 3.45 |  | 3.44 | 1 | 3.44 | 100% | 3.44 | -0.01 | -0.01
[5 empty] | Curve with C-panel | H21-N/19 | 4.77 | 1 | 1 | 4.77 | 2495 |  | 1 | 4.77 | 100% | 0% | 100% | 4.77 | WIR 1184 R1 | 4.49 |  | 0 |  | 0 | -4.77 | -4.77
[6 empty] | H21-N/20 | [7 empty] | - |  |  |  | - | refer to Hotel - 900mm(Qty) worksheet |  |  | - |  | -
[6 empty] | H21-N/21 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[6 empty] | H21-N/22 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[6 empty] | H21-N/23 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[5 empty] | Curve with C-panel | H21-N/24 | 4.77 | 1 | 1 | 4.77 | 2496 |  | 1 | 4.77 | 100% | 0% | 100% | 4.77 | WIR 1184 R1 | 4.49 |  | 0 |  | 0 | -4.77 | -4.77
[6 empty] | H21-N/25 | 4.49 | 1 | 1 | 4.49 | 1391 | 098 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Corner Panel | H21-N/26 | 2.58 | 1 | 1 | 2.58 | 1765 | 162 | 1 | 2.58 | 100% | 0% | 100% | 2.58 |  | 2.605 | 1 | 2.605 | 100% | 2.605 | 0.025 | 0.025
[9 empty] | TOTAL | 87.28 |  |  | TOTAL | 87.28 | TOTAL |  |  | 87.28 |  |  | TOTAL | 77.672 | TOTAL | 70.393
15 | EWS-101 | 600 | 22 | 1 | Corner Panel | H22-N/01 | 4.49 | 1 | 1 | 4.49 | 2033 | 187 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 2.605 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H22-N/02 | 4.49 | 1 | 1 | 4.49 | 1303 | 079 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H22-N/03 | 4.49 | 1 | 1 | 4.49 | 1304 | 079 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H22-N/04 | 4.49 | 1 | 1 | 4.49 | 1304 | 079 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H22-N/05 | 4.49 | 1 | 1 | 4.49 | 1303 | 079 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H22-N/06 | 4.49 | 1 | 1 | 4.49 | 1303 | 079 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H22-N/07 | 4.49 | 1 | 1 | 4.49 | 1303 | 079 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H22-N/08 | 4.49 | 1 | 1 | 4.49 | 1304 | 079 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H22-N/09 | 4.49 | 1 | 1 | 4.49 | 1316 | 082 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 3.44 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H22-N/10 | 3.45 | 1 | 1 | 3.45 | 1758 | 161 | 1 | 3.45 | 100% | 0% | 100% | 3.45 |  | 3.256 |  | 0 |  | 0 | -3.45 | -3.45
[6 empty] | H22-N/11 | 3.27 | 1 | 1 | 3.27 | 1758,1787 | 161164 | 1 | 3.27 | 100% | 0% | 100% | 3.27 |  | 3.755 | 0.33333 | 1.2517 |  | 0 | -2.0183 | -3.27
[6 empty] | H22-N/12 | 3.77 | 1 | 1 | 3.77 | 1771,1787 | 162164 | 1 | 3.77 | 100% | 0% | 100% | 3.77 |  | 3.91 | 0.33333 | 1.3033 |  | 0 | -2.4667 | -3.77
[6 empty] | H22-N/13 | 3.92 | 1 | 1 | 3.92 | 1316 | 082 | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 | 100% | 3.91 | -0.01 | -0.01
[6 empty] | H22-N/14 | 3.92 | 1 | 1 | 3.92 | 1315 | 083 | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 | 100% | 3.91 | -0.01 | -0.01
[6 empty] | H22-N/15 | 3.92 | 1 | 1 | 3.92 | 1315 | 083 | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 | 100% | 3.91 | -0.01 | -0.01
[6 empty] | H22-N/16 | 3.92 | 1 | 1 | 3.92 | 1315 | 083 | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.755 | 1 | 3.755 | 100% | 3.755 | -0.165 | -0.165
[6 empty] | H22-N/17 | 3.77 | 1 | 1 | 3.77 | 1758,1765,1787 | 161,162'164 | 1 | 3.77 | 100% | 0% | 100% | 3.77 |  | 3.256 | 0.33333 | 1.0853 |  | 0 | -2.6847 | -3.77
[6 empty] | H22-N/18 | 3.27 | 1 | 1 | 3.27 | 1758,1765,1787 | 161,162'164 | 1 | 3.27 | 100% | 0% | 100% | 3.27 |  | 3.44 | 0.33333 | 1.1467 |  | 0 | -2.1233 | -3.27
[6 empty] | H22-N/19 | 3.45 | 1 | 1 | 3.45 |  |  | 1 | 3.45 | 100% | 0% | 100% | 3.45 |  | 4.49 |  | 0 |  | 0 | -3.45 | -3.45
[5 empty] | Curve with C-panel | H22-N/20 | 4.72 | 1 | 1 | 4.72 | 2503 |  | 1 | 4.72 | 100% | 0% | 100% | 4.72 | WIR 1185 R1 | 4.49 |  | 0 |  | 0 | -4.72 | -4.72
[6 empty] | H22-N/21 | [7 empty] | - |  |  |  | - | refer to Hotel - 900mm(Qty) worksheet |  |  | - |  | -
[6 empty] | H22-N/22 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[6 empty] | H22-N/23 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[6 empty] | H22-N/24 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[5 empty] | Curve with C-panel | H22-N/25 | 4.72 | 1 | 1 | 4.72 | 2499 |  | 1 | 4.72 | 100% | 0% | 100% | 4.72 | WIR 1185 R1 | 4.49 |  | 0 |  | 0 | -4.72 | -4.72
[6 empty] | H22-N/26 | 4.49 | 1 | 1 | 4.49 | 1322 | 084 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H22-N/27 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H22-N/28 | 4.49 | 1 | 1 | 4.49 | 2033 | 187 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H22-N/29 | 4.67 | 1 | 1 | 4.67 | 1765,2026 | 162,187 | 1 | 4.67 | 100% | 0% | 100% | 4.67 |  | 4.63 | 1 | 4.63 |  | 0 | -0.04 | -4.67
[6 empty] | H22-N/30 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 0.5 | 2.245 |  | 0 | -2.245 | -4.49
[6 empty] | H22-N/31 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H22-N/32 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 0.33333 | 1.4967 |  | 0 | -2.9933 | -4.49
[6 empty] | H22-N/33 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H22-N/34 | 4.67 | 1 | 1 | 4.67 | 2026 | 187 | 1 | 4.67 | 100% | 0% | 100% | 4.67 |  | 5.295 |  | 0 |  | 0 | -4.67 | -4.67
[9 empty] | TOTAL | 127.28 |  |  | TOTAL | 127.28 | TOTAL |  |  | 127.28 |  |  | TOTAL | 78.0337 | TOTAL | 51.405
16 | EWS-101 | 600 | 23 | 1 | Corner Panel | H23-N/01 | 2.69 | 1 | 1 | 2.69 | 2055 | 191 | 1 | 2.69 | 100% | 0% | 100% | 2.69 |  | 2.605 |  | 0 |  | 0 | -2.69 | -2.69
[6 empty] | H23-N/02 | 2.58 | 1 | 1 | 2.58 | 2055 | 191 | 1 | 2.58 | 100% | 0% | 100% | 2.58 |  | 4.49 |  | 0 |  | 0 | -2.58 | -2.58
[6 empty] | H23-N/03 | 4.49 | 1 | 1 | 4.49 | 1390 | 098 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H23-N/04 | 4.49 | 1 | 1 | 4.49 | 1390 | 098 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H23-N/05 | 4.49 | 1 | 1 | 4.49 | 1390 | 098 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H23-N/06 | 4.49 | 1 | 1 | 4.49 | 1395 | 099 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H23-N/07 | 4.49 | 1 | 1 | 4.49 | 1395 | 099 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H23-N/08 | 4.49 | 1 | 1 | 4.49 | 1395 | 099 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H23-N/09 | 4.49 | 1 | 1 | 4.49 | 1405 | 100 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 3.44 | 1 | 3.44 | 100% | 3.44 | -1.05 | -1.05
[6 empty] | H23-N/10 | 3.45 | 1 | 1 | 3.45 | 1408 | 101 | 1 | 3.45 | 100% | 0% | 100% | 3.45 |  | 3.256 | 1 | 3.256 | 100% | 3.256 | -0.194 | -0.194
[6 empty] | H23-N/11 | 3.27 | 1 | 1 | 3.27 | 1934,1936 | 175 | 1 | 3.27 | 100% | 0% | 100% | 3.27 |  | 3.755 |  | 0 |  | 0 | -3.27 | -3.27
[6 empty] | H23-N/12 | 3.77 | 1 | 1 | 3.77 | 1934,1936 | 175 | 1 | 3.77 | 100% | 0% | 100% | 3.77 |  | 3.91 |  | 0 |  | 0 | -3.77 | -3.77
[6 empty] | H23-N/13 | 3.92 | 1 | 1 | 3.92 | 1390 | 098 | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 | 100% | 3.91 | -0.01 | -0.01
[6 empty] | H23-N/14 | 3.92 | 1 | 1 | 3.92 |  |  | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 | 100% | 3.91 | -0.01 | -0.01
[6 empty] | H23-N/15 | 3.92 | 1 | 1 | 3.92 | 1395 | 099 | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.91 | 1 | 3.91 | 100% | 3.91 | -0.01 | -0.01
[6 empty] | H23-N/16 | 3.92 | 1 | 1 | 3.92 | 1395 | 099 | 1 | 3.92 | 100% | 0% | 100% | 3.92 |  | 3.755 | 1 | 3.755 | 100% | 3.755 | -0.165 | -0.165
[6 empty] | H23-N/17 | 3.77 | 1 | 1 | 3.77 | 1934,1936 | 175 | 1 | 3.77 | 100% | 0% | 100% | 3.77 |  | 3.256 |  | 0 |  | 0 | -3.77 | -3.77
[6 empty] | H23-N/18 | 3.27 | 1 | 1 | 3.27 | 1934,1936 | 175 | 1 | 3.27 | 100% | 0% | 100% | 3.27 |  | 3.44 |  | 0 |  | 0 | -3.27 | -3.27
[5 empty] | Curve with C-panel | H23-N/19 | 3.45 | 1 | 1 | 3.45 | 1408 | 101 | 1 | 3.45 | 100% | 0% | 100% | 3.45 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 1.04 | 1.04
[6 empty] | H23-N/20 | 4.72 | 1 | 1 | 4.72 | 2497 |  | 1 | 4.72 | 100% | 0% | 100% | 4.72 | WIR 1186 R1 | 4.49 |  |  |  |  | -4.72 | -4.72
[6 empty] | H23-N/21 | [7 empty] | - |  |  |  | - | refer to Hotel - 900mm(Qty) worksheet |  |  | - |  | -
[6 empty] | H23-N/22 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[6 empty] | H23-N/23 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[5 empty] | Curve with C-panel | H23-N/24 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[6 empty] | H23-N/25 | 4.72 | 1 | 1 | 4.72 | 2505 |  | 1 | 4.72 | 100% | 0% | 100% | 4.72 | WIR 1186 R1 | 4.49 |  | 0 |  | 0 | -4.72 | -4.72
[5 empty] | Corner Panel | H23-N/26 | 4.49 | 1 | 1 | 4.49 | 1408 | 101 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H23-N/27 | 3.12 | 1 | 1 |  | 1765 | 162 | 1 | 3.12 | 100% | 0% | 100% | 3.12 |  | 3.1 | 1 | 3.1 | 100% | 3.1 | -0.02 | -0.02 | H23-N/27
[9 empty] | TOTAL | 87.29 |  |  | TOTAL | 90.41 | TOTAL |  |  | 90.41 |  |  | TOTAL | 56.711 | TOTAL | 56.711
17 | EWS-101 | 600 | 24 | 1 |  | H24-N/01 | 4.11 | 1 | 1 | 4.11 | 1942 | 176 | 1 | 4.11 | 100% | 0% | 100% | 4.11 |  | 4.099 | 1 | 4.099 | 100% | 4.099 | -0.011 | -0.011
[6 empty] | H24-N/02 | 4.49 | 1 | 1 | 4.49 | 1686,1693'1695 | 154,155 | 1 | 4.49 |  |  |  | 0 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 4.49
[6 empty] | H24-N/03 | 4.49 | 1 | 1 | 4.49 | 1693 | 155 | 1 | 4.49 |  |  |  | 0 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 4.49
[6 empty] | H24-N/04 | 4.49 | 1 | 1 | 4.49 | 1686,1693 | 154,155 | 1 | 4.49 |  |  |  | 0 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 4.49
[6 empty] | H24-N/05 | 4.49 | 1 | 1 | 4.49 | 1693,1695 | 155 | 1 | 4.49 |  |  |  | 0 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 4.49
[6 empty] | H24-N/06 | 4.49 | 1 | 1 | 4.49 | 1693,1695,1720 | 155159 | 1 | 4.49 |  |  |  | 0 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 4.49
[6 empty] | H24-N/07 | 4.49 | 1 | 1 | 4.49 | 1734 | 160 | 1 | 4.49 |  |  |  | 0 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 4.49
[6 empty] | H24-N/08 | 4.49 | 1 | 1 | 4.49 | 1734 | 160 | 1 | 4.49 |  |  |  | 0 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 4.49
[6 empty] | H24-N/09 | 4.49 | 1 | 1 | 4.49 | 1585 | 139 | 1 | 4.49 |  |  |  | 0 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 4.49
[6 empty] | H24-N/10 | 4.49 | 1 | 1 | 4.49 | 1585 | 139 | 1 | 4.49 |  |  |  | 0 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 4.49
[6 empty] | H24-N/11 | 4.49 | 1 | 1 | 4.49 | 1585 | 139 | 1 | 4.49 |  |  |  | 0 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 4.49
[6 empty] | H24-N/12 | 4.49 | 1 | 1 | 4.49 | 1585 | 139 | 1 | 4.49 |  |  |  | 0 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 4.49
[6 empty] | H24-N/13 | 4.49 | 1 | 1 | 4.49 | 1585 | 139 | 1 | 4.49 |  |  |  | 0 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 4.49
[6 empty] | H24-N/14 | 4.49 | 1 | 1 | 4.49 | 1591,1663 | 140 | 1 | 4.49 |  |  |  | 0 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 4.49
[6 empty] | H24-N/15 | 4.49 | 1 | 1 | 4.49 | 1591,1663 | 140 | 1 | 4.49 |  |  |  | 0 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 4.49
[6 empty] | H24-N/16 | 4.49 | 1 | 1 | 4.49 | 1591,1663 | 140 | 1 | 4.49 |  |  |  | 0 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 4.49
[6 empty] | H24-N/17 | 4.49 | 1 | 1 | 4.49 | 1591 | 140 | 1 | 4.49 |  |  |  | 0 |  | 4.49 |  | 0 |  | 0 | -4.49 | 0
[6 empty] | H24-N/18 | 4.16 | 1 | 1 | 4.16 | 1591 | 140 | 1 | 4.16 |  |  |  | 0 |  | 4.49 |  | 0 |  | 0 | -4.16 | 0
[5 empty] | Corner Panel | H24-N/19 | 5.01 | 1 | 1 | 5.01 | 2024 | 186 | 1 | 5.01 |  |  |  | 0 |  | 5.295 |  | 0 |  | 0 | -5.01 | 0
[6 empty] | H24-N/20 | 4.49 | 1 | 1 | 4.49 | 2020 |  | 1 | 4.49 |  |  |  | 0 |  | 4.49 |  | 0 |  | 0 | -4.49 | 0
[6 empty] | H24-N/21 | 4.49 | 1 | 1 | 4.49 | 2020 |  | 1 | 4.49 |  |  |  | 0 |  | 4.49 |  | 0 |  | 0 | -4.49 | 0
[6 empty] | H24-N/22 | 4.49 | 1 | 1 | 4.49 | 2020 |  | 1 | 4.49 |  |  |  | 0 |  | 4.49 |  | 0 |  | 0 | -4.49 | 0
[6 empty] | H24-N/23 | 4.49 | 1 | 1 | 4.49 | 2020 |  | 1 | 4.49 |  |  |  | 0 |  | 4.49 |  | 0 |  | 0 | -4.49 | 0
[5 empty] | Corner Panel | H24-N/24 | 5.01 | 1 | 1 | 5.01 | 2049 | 190 | 1 | 5.01 |  |  |  | 0 |  | 5.295 |  | 0 |  | 0 | -5.01 | 0
[6 empty] | H24-N/25 | 4.17 | 1 | 1 | 4.17 | 2024 | 186 | 1 | 4.17 |  |  |  | 0 |  | 4.49 |  | 0 |  | 0 | -4.17 | 0
[6 empty] | H24-N/26 | 4.49 | 1 | 1 | 4.49 | 2024 | 186 | 1 | 4.49 |  |  |  | 0 |  | 4.49 |  | 0 |  | 0 | -4.49 | 0
[6 empty] | H24-N/27 | 4.49 | 1 | 1 | 4.49 | 2024 | 186 | 1 | 4.49 |  |  |  | 0 |  | 4.49 |  | 0 |  | 0 | -4.49 | 0
[6 empty] | H24-N/28 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 |  |  |  | 0 |  | 4.49 |  | 0 |  | 0 | -4.49 | 0
[6 empty] | H24-N/29 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 |  |  |  | 0 |  | 4.49 |  | 0 |  | 0 | -4.49 | 0
[6 empty] | H24-N/30 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | H24-N/31 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | H24-N/32 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | H24-N/33 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | H24-N/34 | 4.49 | 1 | 1 | 4.49 | 1771 | 162 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 608 R2 | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H24-N/35 | 4.49 | 1 | 1 | 4.49 | 1734 | 160 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 608 R2 | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H24-N/36 | 4.49 | 1 | 1 | 4.49 | 1734 | 160 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 0607 R2 | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H24-N/37 | 4.49 | 1 | 1 | 4.49 | 1720 | 159 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 0607 R2 | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H24-N/38 | 4.49 | 1 | 1 | 4.49 | 1720 | 159 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 0607 R2 | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H24-N/39 | 4.49 | 1 | 1 | 4.49 | 1720 | 159 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 0607 R2 | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H24-N/40 | 4.49 | 1 | 1 | 4.49 | 1720 | 159 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 0607 R2 | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H24-N/41 | 4.49 | 1 | 1 | 4.49 | 1720,1725 | 159160 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 0607 R2 | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H24-N/42 | 4.49 | 1 | 1 | 4.49 | 1916 | 173 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 0708 R2 | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H24-N/43 | 3.26 | 1 | 1 | 3.26 | 2049 | 190 | 1 | 3.26 |  |  |  | 0 | WIR 0607 R2 | 3.251 | 1 | 3.251 | 100% | 3.251 | -0.009 | 3.251
[6 empty] | H24-N/44 | 3.26 | 1 | 1 | 3.26 | 2044 | 190 | 1 | 3.26 |  |  |  | 0 | WIR 0607 R2 | 3.251 | 1 | 3.251 | 100% | 3.251 | -0.009 | 3.251
[6 empty] | H24-N/45 | 4.08 | 1 | 1 | 4.08 | 2716 | 284 | 0.25 | 1.02 |  |  |  | 0 | after Level 29 completion | 4.074 |  | 0 |  | 0 | -1.02 | 0
[6 empty] | H24-N/46 | 4.21 | 1 | 1 | 4.21 | 2716 | 284 | 0.25 | 1.0525 |  |  |  | 0 | after Level 29 completion | 4.196 |  | 0 |  | 0 | -1.0525 | 0
[6 empty] | H24-N/47 | 4.24 | 1 | 1 | 4.24 |  |  | 1 | 4.24 | 100% | 0% | 100% | 4.24 |  | 4.23 |  | 0 |  | 0 | -4.24 | -4.24
[6 empty] | H24-N/48 | 4.24 | 1 | 1 | 4.24 |  |  | 1 | 4.24 | 100% | 0% | 100% | 4.24 |  | 4.23 |  | 0 |  | 0 | -4.24 | -4.24
[6 empty] | H24-N/49 | 4.24 | 1 | 1 | 4.24 |  |  | 1 | 4.24 | 100% | 0% | 100% | 4.24 |  | 4.23 |  | 0 |  | 0 | -4.24 | -4.24
[6 empty] | H24-N/50 | 4.24 | 1 | 1 | 4.24 |  |  | 1 | 4.24 | 100% | 0% | 100% | 4.24 |  | 4.23 |  | 0 |  | 0 | -4.24 | -4.24
[6 empty] | H24-N/51 | 3.43 | 1 | 1 | 3.43 | 2716 | 284 | 1 | 3.43 | 100% | 0% | 100% | 3.43 |  | 3.415 |  | 0 |  | 0 | -3.43 | -3.43
[6 empty] | H24-N/52 | 2.45 | 1 | 1 | 2.45 | 2716 | 284 | 1 | 2.45 | 100% | 0% | 100% | 2.45 |  | 2.442 |  | 0 |  | 0 | -2.45 | -2.45
[9 empty] | TOTAL | 226.24 |  |  | TOTAL | 202.0625 | TOTAL |  |  | 67.36 |  |  | TOTAL | 113.871 | TOTAL | 113.871
18 | EWS-101 | 600 | 25 | 1 |  | H25-N/01 | 1.39 | 1 | 1 | 1.39 |  |  | 1 | 1.39 | 100% | 0% | 100% | 1.39 |  | 1.39 |  | 0 |  | 0 | -1.39 | -1.39
[6 empty] | H25-N/02 | 1.18 | 1 | 1 | 1.18 | 2068 | 194 | 1 | 1.18 | 100% | 0% | 100% | 1.18 |  | 1.15 |  | 0 |  | 0 | -1.18 | -1.18
[6 empty] | H25-N/03 | 4.49 | 1 | 1 | 4.49 | 1610 | 143 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H25-N/04 | 4.49 | 1 | 1 | 4.49 | 1610 | 143 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H25-N/05 | 4.49 | 1 | 1 | 4.49 | 1610 | 143 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H25-N/06 | 4.49 | 1 | 1 | 4.49 | 1610 | 143 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H25-N/07 | 4.49 | 1 | 1 | 4.49 | 1614 | 143 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H25-N/08 | 4.49 | 1 | 1 | 4.49 | 1614 | 143 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H25-N/09 | 4.49 | 1 | 1 | 4.49 | 1614 | 143 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H25-N/10 | 4.49 | 1 | 1 | 4.49 | 1610 | 143 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H25-N/11 | 4.49 | 1 | 1 | 4.49 | 1614 | 143 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H25-N/12 | 4.49 | 1 | 1 | 4.49 | 1607 | 142 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H25-N/13 | 4.49 | 1 | 1 | 4.49 | 1607 | 142 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H25-N/14 | 4.49 | 1 | 1 | 4.49 | 1607 | 142 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H25-N/15 | 4.49 | 1 | 1 | 4.49 | 1607 | 142 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H25-N/16 | 4.49 | 1 | 1 | 4.49 | 1607 | 142 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H25-N/17 | 2.68 | 1 | 1 | 2.68 | 1634 | 146 | 1 | 2.68 | 100% | 0% | 100% | 2.68 |  | 2.673 | 1 | 2.673 | 100% | 2.673 | -0.007 | -0.007
[5 empty] | Curve Panel | H25-N/18 | 4.05 | 1 | 1 | 4.05 | 1620,2624,2704 | 144,272 | 1 | 4.05 | 100% | 0% | 100% | 4.05 |  | 4.728 | 1 | 4.728 | 100% | 4.728 | 0.678 | 0.678
[5 empty] | Curve Panel | H25-N/19 | 3.89 | 1 | 1 | 3.89 | 1620 | 144 | 1 | 3.89 | 100% | 0% | 100% | 3.89 |  | 4.597 | 1 | 4.597 | 100% | 4.597 | 0.707 | 0.707
[6 empty] | H25-N/20 | 2.55 | 1 | 1 | 2.55 | 1634,1637 | 146,147 | 1 | 2.55 | 100% | 0% | 100% | 2.55 |  | 2.542 | 1 | 2.542 | 100% | 2.542 | -0.008 | -0.008
[6 empty] | H25-N/21 | 4.49 | 1 | 1 | 4.49 | 1614 | 143 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H25-N/22 | 4.49 | 1 | 1 | 4.49 | 1620 | 144 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H25-N/23 | 4.49 | 1 | 1 | 4.49 | 1620 | 144 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H25-N/24 | 4.49 | 1 | 1 | 4.49 | 1622,1672 | 144,152 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H25-N/25 | 4.49 | 1 | 1 | 4.49 | 1622 | 144 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H25-N/26 | 4.49 | 1 | 1 | 4.49 | 1622 | 144 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H25-N/27 | 4.49 | 1 | 1 | 4.49 | 1622 | 144 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H25-N/28 | 4.49 | 1 | 1 | 4.49 | 1622 | 144 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1187 | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H25-N/29 | 4.72 | 1 | 1 | 4.72 | 2508 |  | 1 | 4.72 | 100% | 0% | 100% | 4.72 | WIR 1187 R1 | 4.49 |  | 0 |  | 0 | -4.72 | -4.72
[6 empty] | H25-N/30 | [7 empty] | - |  |  |  | - | refer to Hotel - 900mm(Qty) worksheet |  |  | - |  | -
[6 empty] | H25-N/31 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[6 empty] | H25-N/32 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[6 empty] | H25-N/33 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[6 empty] | H25-N/34 | 4.72 | 1 | 1 | 4.72 | 2532 | 256 | 1 | 4.72 | 100% | 0% | 100% | 4.72 | WIR 1187 R1 | 4.49 |  | 0 |  | 0 | -4.72 | -4.72
[6 empty] | H25-N/35 | 4.49 | 1 | 1 | 4.49 | 2033 | 187 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H25-N/36 | 0.84 | 1 | 1 | 0.84 | 2031 | 187 | 1 | 0.84 | 100% | 0% | 100% | 0.84 |  | 1.15 |  | 0 |  | 0 | -0.84 | -0.84
[6 empty] | H25-N/37 | 1.74 | 1 | 0 | 0 |  |  |  | 0 | 100% | 0% | 100% | 1.74 |  | 1.39 |  | 0 |  | 0 | 0 | -1.74
[9 empty] | TOTAL | 129.29 |  |  | TOTAL | 129.29 | TOTAL |  |  | 131.03 |  |  | TOTAL | 113.32 | TOTAL | 113.32
19 | EWS-101 | 600 | 26 | 1 |  | H26-N/01 | 4.3 | 1 | 1 | 4.3 | 1765 | 162 | 1 | 4.3 | 100% | 0% | 100% | 4.3 |  | 4.294 | 1 | 4.294 |  | 0 | -0.006 | -4.3
[6 empty] | H26-N/02 | 4.3 | 1 | 1 | 4.3 | 1765 | 162 | 1 | 4.3 | 100% | 0% | 100% | 4.3 |  | 4.295 | 1 | 4.295 |  | 0 | -0.005 | -4.3
[6 empty] | H26-N/03 | 4.49 | 1 | 1 | 4.49 | 1592 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H26-N/04 | 4.49 | 1 | 1 | 4.49 | 1592 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H26-N/05 | 4.49 | 1 | 1 | 4.49 | 1592 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H26-N/06 | 4.49 | 1 | 1 | 4.49 | 1595 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H26-N/07 | 4.49 | 1 | 1 | 4.49 | 1595 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H26-N/08 | 4.49 | 1 | 1 | 4.49 | 1595 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H26-N/09 | 4.49 | 1 | 1 | 4.49 | 1595 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H26-N/10 | 4.49 | 1 | 1 | 4.49 | 1595 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H26-N/11 | 4.49 | 1 | 1 | 4.49 | 1598 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H26-N/12 | 4.49 | 1 | 1 | 4.49 | 1598 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H26-N/13 | 4.49 | 1 | 1 | 4.49 | 1598 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H26-N/14 | 4.49 | 1 | 1 | 4.49 | 1598 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H26-N/15 | 4.49 | 1 | 1 | 4.49 | 1598 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H26-N/16 | 4.49 | 1 | 1 | 4.49 | 1604 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H26-N/17 | 4.49 | 1 | 1 | 4.49 | 1604 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H26-N/18 | 4.49 | 1 | 1 | 4.49 | 1604 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H26-N/19 | 4.67 | 1 | 1 | 4.67 | 1604 |  | 1 | 4.67 | 100% | 0% | 100% | 4.67 |  | 5.295 | 1 | 5.295 |  | 0 | 0.625 | -4.67
[6 empty] | H26-N/20 | 4.49 | 1 | 1 | 4.49 | 2009 | 183 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H26-N/21 | 4.49 | 1 | 1 | 4.49 | 2009 | 183 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H26-N/22 | 4.49 | 1 | 1 | 4.49 | 2009 | 183 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H26-N/23 | 4.49 | 1 | 1 | 4.49 | 1979 | 181 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H26-N/24 | 4.67 | 1 | 1 | 4.67 | 1979 | 181 | 1 | 4.67 | 100% | 0% | 100% | 4.67 |  | 5.295 |  | 0 |  | 0 | -4.67 | -4.67
[6 empty] | H26-N/25 | 4.49 | 1 | 1 | 4.49 | 1979 | 181 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H26-N/26 | 4.49 | 1 | 1 | 4.49 | 1979 | 181 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H26-N/27 | 4.49 | 1 | 1 | 4.49 | 1979 | 181 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[5 empty] | Curve with C Panel | H26-N/28 | 4.72 | 1 | 1 | 4.72 |  |  | 1 | 4.72 | 100% | 0% | 100% | 4.72 | WIR 1188 R1 | 4.49 |  | 0 |  | 0 | -4.72 | -4.72
[6 empty] | H26-N/29 | [7 empty] | - |  |  |  | - | refer to Hotel - 900mm(Qty) worksheet |  |  | - |  | -
[6 empty] | H26-N/30 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[6 empty] | H26-N/31 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[6 empty] | H26-N/32 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[5 empty] | Curve with C Panel | H26-N/33 | 4.72 | 1 | 1 | 4.72 | 2517,2599 |  | 1 | 4.72 | 100% | 0% | 100% | 4.72 | WIR 1188 R1 | 4.49 |  | 0 |  | 0 | -4.72 | -4.72
[6 empty] | H26-N/34 | 4.49 | 1 | 1 | 4.49 | 1625 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H26-N/35 | 4.49 | 1 | 1 | 4.49 | 1625 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H26-N/36 | 4.49 | 1 | 1 | 4.49 | 1625 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H26-N/37 | 4.49 | 1 | 1 | 4.49 | 1625 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H26-N/38 | 4.49 | 1 | 1 | 4.49 | 1625 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H26-N/39 | 4.49 | 1 | 1 | 4.49 | 1626 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H26-N/40 | 4.49 | 1 | 1 | 4.49 | 1626 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H26-N/41 | 4.49 | 1 | 1 | 4.49 | 1626 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H26-N/42 | 4.49 | 1 | 1 | 4.49 | 1626 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H26-N/43 | 3.25 | 1 | 1 | 3.25 | 1626 |  | 1 | 3.25 | 100% | 0% | 100% | 3.25 |  | 3.244 | 1 | 3.244 |  | 0 | -0.006 | -3.25
[6 empty] | H26-N/44 | 3.25 | 1 | 1 | 3.25 | 1976 | 180 | 1 | 3.25 | 100% | 0% | 100% | 3.25 |  | 3.244 |  | 0 |  | 0 | -3.25 | -3.25
[5 empty] | Curve with C Panel | H26-N/45 | 3.25 | 1 | 1 | 3.25 | 1963,2041 | 179,189 | 1 | 3.25 | 100% | 0% | 100% | 3.25 | WIR 1221 | 4.081 |  | 0 |  | 0 | -3.25 | -3.25
[5 empty] | Curve with C Panel | H26-N/46 | 4.21 | 1 | 1 | 4.21 | 1963,2041 | 179,189 | 1 | 4.21 | 100% | 0% | 100% | 4.21 | WIR 1221 | 4.203 |  | 0 |  | 0 | -4.21 | -4.21
[6 empty] | H26-N/47 | 4.24 | 1 | 1 | 4.24 | 1963 | 179 | 1 | 4.24 | 100% | 0% | 100% | 4.24 |  | 4.23 |  | 0 |  | 0 | -4.24 | -4.24
[6 empty] | H26-N/48 | 4.24 | 1 | 1 | 4.24 | 1963 | 179 | 1 | 4.24 | 100% | 0% | 100% | 4.24 |  | 4.23 |  | 0 |  | 0 | -4.24 | -4.24
[6 empty] | H26-N/49 | 4.24 | 1 | 1 | 4.24 | 1949 | 177 | 1 | 4.24 | 100% | 0% | 100% | 4.24 |  | 4.23 | 1 | 4.23 |  | 0 | -0.01 | -4.24
[6 empty] | H26-N/50 | 4.24 | 1 | 1 | 4.24 | 1949 | 177 | 1 | 4.24 | 100% | 0% | 100% | 4.24 |  | 4.23 | 1 | 4.23 |  | 0 | -0.01 | -4.24
[5 empty] | Curve with C Panel | H26-N/51 | 3.43 | 1 | 1 | 3.43 | 1963,2041,2705 | 177,189,282 | 1 | 3.43 | 100% | 0% | 100% | 3.43 | WIR 1208 | 3.415 |  | 0 |  | 0 | -3.43 | -3.43
[5 empty] | Curve with C Panel | H26-N/52 | 2.45 | 1 | 1 | 2.45 | 1963,2041 | 177,189 | 1 | 2.45 | 100% | 0% | 100% | 2.45 | WIR 1208 | 2.442 |  | 0 |  | 0 | -2.45 | -2.45
[9 empty] | TOTAL | 207.86 |  |  | TOTAL | 207.86 | TOTAL |  |  | 207.86 |  |  | TOTAL | 137.838 | TOTAL | 103.27
20 | EWS-101 | 600 | 27 | 1 |  | H27-N/01 | 1.74 | 1 | 1 | 1.74 | 1626,2107 |  | 1 | 1.74 | 100% | 0% | 100% | 1.74 | WIR 1227 | 1.39 |  | 0 |  | 0 | -1.74 | -1.74
[6 empty] | H27-N/02 | 0.84 | 1 | 1 | 0.84 | 1626,2107,2183 | 210 | 1 | 0.84 | 100% | 0% | 100% | 0.84 | WIR 1227 | 1.15 |  | 0 |  | 0 | -0.84 | -0.84
[6 empty] | H27-N/03 | 4.49 | 1 | 1 | 4.49 | 1634,2099 | 146 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
|  |  | ` |  |  | H27-N/04 | 4.49 | 1 | 1 | 4.49 | 1626,2099 | 145 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H27-N/05 | 4.49 | 1 | 1 | 4.49 | 1626,2099 | 145 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H27-N/06 | 4.49 | 1 | 1 | 4.49 | 1626,2107 | 145 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H27-N/07 | 4.49 | 1 | 1 | 4.49 | 1626,2107 | 145 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H27-N/08 | 4.49 | 1 | 1 | 4.49 | 1637 | 147 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H27-N/09 | 4.49 | 1 | 1 | 4.49 | 1637 | 147 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H27-N/10 | 4.49 | 1 | 1 | 4.49 | 1634 | 146 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H27-N/11 | 4.49 | 1 | 1 | 4.49 | 1634 | 146 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H27-N/12 | 4.49 | 1 | 1 | 4.49 | 1634 | 146 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H27-N/13 | 4.49 | 1 | 1 | 4.49 | 1639 | 147 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H27-N/14 | 4.49 | 1 | 1 | 4.49 | 1634 | 146 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H27-N/15 | 4.49 | 1 | 1 | 4.49 | 1634 | 146 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H27-N/16 | 4.49 | 1 | 1 | 4.49 | 1639 | 147 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H27-N/17 | 2.68 | 1 | 1 | 2.68 | 1684 | 154 | 1 | 2.68 | 100% | 0% | 100% | 2.68 |  | 2.673 | 1 | 2.673 | 100% | 2.673 | -0.007 | -0.007
[5 empty] | Curve Panel | H27-N/18 | 4.05 | 1 | 1 | 4.05 | 1706, 2938 | 157, 302 | 1 | 4.05 | 100% | 0% | 100% | 4.05 |  | 4.728 | 1 | 4.728 | 100% | 4.728 | 0.678 | 0.678
[5 empty] | Curve Panel | H27-N/19 | 3.89 | 1 | 1 | 3.89 | 1706,2942 | 157,304 | 1 | 3.89 | 100% | 0% | 100% | 3.89 |  | 4.597 | 1 | 4.597 | 100% | 4.597 | 0.707 | 0.707
[6 empty] | H27-N/20 | 2.55 | 1 | 1 | 2.55 | 1684 | 154 | 1 | 2.55 | 100% | 0% | 100% | 2.55 |  | 2.542 | 1 | 2.542 | 100% | 2.542 | -0.008 | -0.008
[6 empty] | H27-N/21 | 4.49 | 1 | 1 | 4.49 | 1655 | 149 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H27-N/22 | 4.49 | 1 | 1 | 4.49 | 1655 | 149 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H27-N/23 | 4.49 | 1 | 1 | 4.49 | 1655 | 149 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H27-N/24 | 4.49 | 1 | 1 | 4.49 | 1672 | 152 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H27-N/25 | 4.49 | 1 | 1 | 4.49 | 1655 | 149 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H27-N/26 | 4.49 | 1 | 1 | 4.49 | 1672 | 152 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H27-N/27 | 4.49 | 1 | 1 | 4.49 | 1672 | 152 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H27-N/28 | 4.49 | 1 | 1 | 4.49 | 1655 | 149 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[5 empty] | Curve with C Panel | H27-N/29 | 4.72 | 1 | 1 | 4.72 |  |  | 1 | 4.72 | 100% | 0% | 100% | 4.72 | WIR 1189 R1 | 4.49 |  | 0 |  | 0 | -4.72 | -4.72
[6 empty] | H27-N/30 | [7 empty] | - |  |  |  | - | refer to Hotel - 900mm(Qty) worksheet |  |  | - |  | -
[6 empty] | H27-N/31 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[6 empty] | H27-N/32 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[6 empty] | H27-N/33 | [7 empty] | - |  |  |  | - |  |  |  | - |  | -
[5 empty] | Curve with C Panel | H27-N/34 | 4.72 | 1 | 1 | 4.72 |  |  | 1 | 4.72 | 100% | 0% | 100% | 4.72 | WIR 1189 R1 | 4.49 |  | 0 |  | 0 | -4.72 | -4.72
[6 empty] | H27-N/35 | 4.49 | 1 | 1 | 4.49 | 1672 | 152 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H27-N/36 | 0.84 | 1 | 1 | 0.84 | 2170 | 208 | 1 | 0.84 | 100% | 0% | 100% | 0.84 |  | 1.15 |  | 0 |  | 0 | -0.84 | -0.84
[6 empty] | H27-N/37 | 1.74 | 1 | 1 | 1.74 |  |  | 1 | 1.74 | 100% | 0% | 100% | 1.74 |  | 1.39 |  | 0 |  | 0 | -1.74 | -1.74
[9 empty] | TOTAL | 131.04 |  |  | TOTAL | 131.04 | TOTAL |  |  | 131.04 |  |  | TOTAL | 113.32 | TOTAL | 113.32
21 | EWS-101 | 600 | 28 | 1 |  | H28-N/01 | 4.11 | 1 | 1 | 4.11 | 1951 | 178 | 1 | 4.11 | 100% | 0% | 100% | 4.11 | WIR 1168 | 4.099 | 0.5 | 2.0495 |  | 0 | -2.0605 | -4.11
[6 empty] | H28-N/02 | 4.49 | 1 | 1 | 4.49 | 1951 | 178 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H28-N/03 | 4.49 | 1 | 1 | 4.49 | 1720 | 159 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 50% | 2.245 | 0 | -2.245
[6 empty] | H28-N/04 | 4.49 | 1 | 1 | 4.49 | 1720 | 159 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 50% | 2.245 | 0 | -2.245
[6 empty] | H28-N/05 | 4.49 | 1 | 1 | 4.49 | 1720 | 159 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1105 | 4.49 | 1 | 4.49 | 50% | 2.245 | 0 | -2.245
[6 empty] | H28-N/06 | 4.49 | 1 | 1 | 4.49 | 1706 | 157 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1105 | 4.49 | 1 | 4.49 | 50% | 2.245 | 0 | -2.245
[6 empty] | H28-N/07 | 4.49 | 1 | 1 | 4.49 | 1706 | 157 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1114 | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H28-N/08 | 4.49 | 1 | 1 | 4.49 | 1712 | 159 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1114 | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H28-N/09 | 4.49 | 1 | 1 | 4.49 | 1712 | 159 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1114 | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H28-N/10 | 4.49 | 1 | 1 | 4.49 | 1712 | 159 | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1114 | 4.49 | 0.5 | 2.245 |  | 0 | -2.245 | -4.49
[6 empty] | H28-N/11 | 4.49 | 1 | 1 | 4.49 | 1697 | 156 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 50% | 2.245 | 0 | -2.245
[6 empty] | H28-N/12 | 4.49 | 1 | 1 | 4.49 | 1697 | 156 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 50% | 2.245 | 0 | -2.245
[6 empty] | H28-N/13 | 4.49 | 1 | 1 | 4.49 | 1697,1699 | 156 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H28-N/14 | 4.49 | 1 | 1 | 4.49 | 1697 | 156 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H28-N/15 | 4.49 | 1 | 1 | 4.49 | 1697,1699 | 156 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 50% | 2.245 | 0 | -2.245
[6 empty] | H28-N/16 | 4.49 | 1 | 1 | 4.49 | 1697,1699 | 156 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 50% | 2.245 | 0 | -2.245
[6 empty] | H28-N/17 | 4.49 | 1 | 1 | 4.49 | 1951 | 178 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H28-N/18 | 4.49 | 1 | 1 | 4.49 | 1951 | 178 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H28-N/19 | 4.61 | 1 | 1 | 4.61 | 2059 | 2059 | 1 | 4.61 | 100% | 0% | 100% | 4.61 |  | 5.235 |  | 0 |  | 0 | -4.61 | -4.61
[6 empty] | H28-N/20 | 4.49 | 1 | 1 | 4.49 | 2031 | 187 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H28-N/21 | 4.49 | 1 | 1 | 4.49 | 1967 | 179 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H28-N/22 | 4.49 | 1 | 1 | 4.49 | 1967,2565 | 179,259 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 |  | 0 | 0 | -4.49
[6 empty] | H28-N/23 | 4.49 | 1 | 1 | 4.49 | 1989,2271 | 183,223 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H28-N/24 | 4.67 | 1 | 1 | 4.67 | 2059 | 2059 | 1 | 4.67 | 100% | 0% | 100% | 4.67 |  | 4.695 |  | 0 |  | 0 | -4.67 | -4.67
[6 empty] | H28-N/25 | 4.49 | 1 | 1 | 4.49 | 1945 | 177 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H28-N/26 | 4.49 | 1 | 1 | 4.49 | 1945 | 177 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H28-N/27 | 4.49 | 1 | 1 | 4.49 | 1989 | 183 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H28-N/28 | 4.49 | 1 | 1 | 4.49 | 2723 | 287 | 1 | 4.49 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | -4.49 | 0
[6 empty] | H28-N/29 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | H28-N/30 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | H28-N/31 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | H28-N/32 | 4.49 | 1 | 1 | 4.49 |  |  |  | 0 |  |  |  | 0 | extended slab | 4.49 |  | 0 |  | 0 | 0 | 0
[6 empty] | H28-N/33 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 |  |  |  | 0 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 4.49
[6 empty] | H28-N/34 | 4.49 | 1 | 1 | 4.49 | 1950 | 178 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H28-N/35 | 4.49 | 1 | 1 | 4.49 | 1744 | 160 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H28-N/36 | 4.49 | 1 | 1 | 4.49 | 1744 | 160 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H28-N/37 | 4.49 | 1 | 1 | 4.49 | 1744 | 160 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H28-N/38 | 4.49 | 1 | 1 | 4.49 | 1744 | 160 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H28-N/39 | 4.49 | 1 | 1 | 4.49 | 1749 | 161 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 | 1 | 4.49 | 100% | 4.49 | 0 | 0
[6 empty] | H28-N/40 | 4.49 | 1 | 1 | 4.49 | 1749 | 161 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H28-N/41 | 4.49 | 1 | 1 | 4.49 | 1749 | 161 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H28-N/42 | 4.49 | 1 | 1 | 4.49 | 2055 | 191 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  | 4.49 |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H28-N/43 | 3.26 | 1 | 1 | 3.26 | 1989 | 183 | 1 | 3.26 | 100% | 0% | 100% | 3.26 |  | 3.251 |  | 0 |  | 0 | -3.26 | -3.26
[6 empty] | H28-N/44 | 3.26 | 1 | 1 | 3.26 | 1989 | 183 | 1 | 3.26 | 100% | 0% | 100% | 3.26 |  | 3.251 |  | 0 |  | 0 | -3.26 | -3.26
[6 empty] | H28-N/45 | 4.08 | 1 | 1 | 4.08 | 2251 | 221 | 1 | 4.08 | 100% | 0% | 100% | 4.08 | WIR 1200 | 4.074 |  | 0 |  | 0 | -4.08 | -4.08
[6 empty] | H28-N/46 | 4.21 | 1 | 1 | 4.21 | 2251 | 221 | 1 | 4.21 | 100% | 0% | 100% | 4.21 | WIR 1200 | 4.196 |  | 0 |  | 0 | -4.21 | -4.21
[6 empty] | H28-N/47 | 4.24 | 1 | 1 | 4.24 | 1980 | 181 | 1 | 4.24 | 100% | 0% | 100% | 4.24 |  | 4.23 |  | 0 |  | 0 | -4.24 | -4.24
[6 empty] | H28-N/48 | 4.24 | 1 | 1 | 4.24 | 2030 | 187 | 1 | 4.24 | 100% | 0% | 100% | 4.24 |  | 4.23 |  | 0 |  | 0 | -4.24 | -4.24
[6 empty] | H28-N/49 | 4.24 | 1 | 1 | 4.24 | 2034 | 188 | 1 | 4.24 | 100% | 0% | 100% | 4.24 |  | 4.23 |  | 0 |  | 0 | -4.24 | -4.24
[6 empty] | H28-N/50 | 4.24 | 1 | 1 | 4.24 | 2015 | 185 | 1 | 4.24 | 100% | 0% | 100% | 4.24 |  | 4.23 |  | 0 |  | 0 | -4.24 | -4.24
[6 empty] | H28-N/51 | 3.43 | 1 | 1 | 3.43 | 2251 | 221 | 1 | 3.43 | 100% | 0% | 100% | 3.43 | WIR 1168 | 3.415 |  | 0 |  | 0 | -3.43 | -3.43
[6 empty] | H28-N/52 | 2.45 | 1 | 1 | 2.45 | 2251 | 221 | 1 | 2.45 | 100% | 0% | 100% | 2.45 | WIR 1168 | 2.442 |  | 0 |  | 0 | -2.45 | -2.45
[9 empty] | TOTAL | 226.15 |  |  | TOTAL | 208.19 | TOTAL |  |  | 199.21 |  |  | TOTAL | 107.5645 | TOTAL | 53.88
22 | EWS-101 | 600 | 29 | 1 |  | H29-N/01 | 4.11 | 1 | 1 | 4.11 | 2384,2457 | 234 | 1 | 4.11 | 100% | 0% | 100% | 4.11 |  |  |  | 0 |  | 0 | -4.11 | -4.11
[6 empty] | H29-N/02 | 4.49 | 1 | 1 | 4.49 | 2384,2386 | 234 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/03 | 4.49 | 1 | 1 | 4.49 | 2384,2386 | 234 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/04 | 4.49 | 1 | 1 | 4.49 | 2384,2386 | 234 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/05 | 4.49 | 1 | 1 | 4.49 | 2465 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/06 | 4.49 | 1 | 1 | 4.49 | 2465, 2938 | 302 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/07 | 4.49 | 1 | 1 | 4.49 | 2465 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/08 | 4.49 | 1 | 1 | 4.49 | 2465 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/09 | 4.49 | 1 | 1 | 4.49 | 2384'2457 | 234 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/10 | 4.49 | 1 | 1 | 4.49 | 2384,2457 | 234 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/11 | 4.49 | 1 | 1 | 4.49 | 2384,2457 | 234 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/12 | 4.49 | 1 | 1 | 4.49 | 2384,2457 | 234 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/13 | 4.49 | 1 | 1 | 4.49 | 2384,2386 | 234 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/14 | 4.49 | 1 | 1 | 4.49 | 2461 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/15 | 4.49 | 1 | 1 | 4.49 | 2461 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/16 | 4.49 | 1 | 1 | 4.49 | 2386,2461 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/17 | 4.49 | 1 | 1 | 4.49 | 2451,2386 | 239 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/18 | 4.49 | 1 | 1 | 4.49 | 2438 | 239 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/19 | 4.74 | 1 | 1 | 4.74 | 2437 | 239 | 1 | 4.74 | 100% | 0% | 100% | 4.74 |  |  |  | 0 |  | 0 | -4.74 | -4.74
[6 empty] | H29-N/20 | 4.49 | 1 | 1 | 4.49 | 2451 | 241 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/21 | 4.49 | 1 | 1 | 4.49 | 2451 | 241 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/22 | 4.49 | 1 | 1 | 4.49 | 2438 | 239 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/23 | 4.49 | 1 | 1 | 4.49 | 2438 | 239 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/24 | 4.74 | 1 | 1 | 4.74 | 2437 | 239 | 1 | 4.74 | 100% | 0% | 100% | 4.74 |  |  |  | 0 |  | 0 | -4.74 | -4.74
[6 empty] | H29-N/25 | 4.49 | 1 | 1 | 4.49 | 2438,2461 | 239 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/26 | 4.49 | 1 | 1 | 4.49 | 2451 | 241 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/27 | 4.49 | 1 | 1 | 4.49 | 2451,2457 | 241 | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/28 | 4.49 | 1 | 1 | 4.49 | 2465 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 | WIR 1220 |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/29 | 4.49 | 1 | 1 | 4.49 | 2465 |  | 1 | 4.49 |  |  |  | 0 | Scaffolding not handover |  |  | 0 |  | 0 | -4.49 | 0
[6 empty] | H29-N/30 | 4.49 | 1 | 1 | 4.49 | 2465 |  | 1 | 4.49 |  |  |  | 0 | Scaffolding not handover |  |  | 0 |  | 0 | -4.49 | 0
[6 empty] | H29-N/31 | 4.49 | 1 | 1 | 4.49 | 2465 |  | 1 | 4.49 |  |  |  | 0 | Scaffolding not handover |  |  | 0 |  | 0 | -4.49 | 0
[6 empty] | H29-N/32 | 4.49 | 1 | 1 | 4.49 | 2464 |  | 1 | 4.49 |  |  |  | 0 | Scaffolding not handover |  |  | 0 |  | 0 | -4.49 | 0
[6 empty] | H29-N/33 | 4.49 | 1 | 1 | 4.49 | 2464 |  | 1 | 4.49 |  |  |  | 0 | Scaffolding not handover |  |  | 0 |  | 0 | -4.49 | 0
[6 empty] | H29-N/34 | 4.49 | 1 | 1 | 4.49 | 2461 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/35 | 4.49 | 1 | 1 | 4.49 | 2461 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/36 | 4.49 | 1 | 1 | 4.49 | 2473 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/37 | 4.49 | 1 | 1 | 4.49 | 2473 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/38 | 4.49 | 1 | 1 | 4.49 | 2473 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/39 | 4.49 | 1 | 1 | 4.49 | 2473 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/40 | 4.49 | 1 | 1 | 4.49 | 2476 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/41 | 4.49 | 1 | 1 | 4.49 | 2476 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/42 | 4.49 | 1 | 1 | 4.49 | 2476 |  | 1 | 4.49 | 100% | 0% | 100% | 4.49 |  |  |  | 0 |  | 0 | -4.49 | -4.49
[6 empty] | H29-N/43 | 3.26 | 1 | 1 | 3.26 | 2476 |  | 1 | 3.26 | 100% | 0% | 100% | 3.26 |  |  |  | 0 |  | 0 | -3.26 | -3.26
[6 empty] | H29-N/44 | 3.26 | 1 | 1 | 3.26 | 2464 |  | 1 | 3.26 | 100% | 0% | 100% | 3.26 |  |  |  | 0 |  | 0 | -3.26 | -3.26
[6 empty] | H29-N/45 | 4.43 | 1 | 1 | 4.43 | 2483 |  | 1 | 4.43 | 100% | 0% | 100% | 4.43 |  |  |  | 0 |  | 0 | -4.43 | -4.43
[6 empty] | H29-N/46 | 4.38 | 1 | 1 | 4.38 | 2483 |  | 1 | 4.38 | 100% | 0% | 100% | 4.38 |  |  |  | 0 |  | 0 | -4.38 | -4.38
[6 empty] | H29-N/47 | 4.24 | 1 | 1 | 4.24 | 2396 | 236 | 1 | 4.24 | 100% | 0% | 100% | 4.24 |  |  |  | 0 |  | 0 | -4.24 | -4.24
[6 empty] | H29-N/48 | 4.24 | 1 | 1 | 4.24 | 2396 | 236 | 1 | 4.24 | 100% | 0% | 100% | 4.24 |  |  |  | 0 |  | 0 | -4.24 | -4.24
[6 empty] | H29-N/49 | 4.24 | 1 | 1 | 4.24 | 2396 | 236 | 1 | 4.24 | 100% | 0% | 100% | 4.24 |  |  |  | 0 |  | 0 | -4.24 | -4.24
[6 empty] | H29-N/50 | 4.24 | 1 | 1 | 4.24 | 2396 | 236 | 1 | 4.24 | 100% | 0% | 100% | 4.24 |  |  |  | 0 |  | 0 | -4.24 | -4.24
[6 empty] | H29-N/51 | 3.33 | 1 | 1 | 3.33 | 2464 |  | 1 | 3.33 | 100% | 0% | 100% | 3.33 |  |  |  | 0 |  | 0 | -3.33 | -3.33
[6 empty] | H29-N/52 | 2.79 | 1 | 1 | 2.79 | 2483 |  | 1 | 2.79 | 100% | 0% | 100% | 2.79 |  |  |  | 0 |  | 0 | -2.79 | -2.79
[9 empty] | TOTAL | 227.11 |  |  | TOTAL | 227.11 | TOTAL |  |  | 204.66 |  |  | TOTAL | 0 | TOTAL | 0
[6 empty] | LVL | L | Qty |  | Mat'l Produced (Length) |  |  | Mat'l On Site | Mat'l On Site (Length) | Work Done |  |  | Work Done (Length) |  | L | Mat'l On Site | Mat'l On Site (Length) | Work Done | Work Done (Length) | Work Done | Work Done (Length)
| BOQ Item E |  |  |  |  | H7 | 160.68 | 38 |  | 160.68 |  |  | 100% | 160.68 | 97.21% |  |  | 156.19 |  | 160.429 | 34.68% | 55.6321 | 26.58% | 42.65 | -105.0479 | -113.54
| BOQ Item L |  |  |  |  | H8 to H29 | 3424.707 | 812 |  | 3419.847 |  |  | 97.15% | 3326.9495 | 91.93% |  |  | 3148.397 |  | 3348.639 | 74.38% | 2490.7195 | 62.63% | 2097.282 | -836.23 | -1051.115
[6 empty] | TOTAL (BOQ L) | 234.5 | 54 | 54 | 234.5 |  |  | 32.5 | 138.4825 |  |  | 30.2% | 70.83
[25 empty] | #REF! | #REF!

## Hotel - 900mm(Qty) (hidden)
Quantity Take Off- Hotel ( Tower )
S. No. | Wall Type | Width | Floor Level | Qty Per Floor |  |  |  |  | GRC PANEL PRODUCED |  | GRC PANEL DELIVERED ONSITE |  |  |  | GRC PANEL INSTALLATION |  |  | Remarks
[6 empty] | CODE | L | Qty | Mat'l Produced | Length | DO No. | MIR No. | Mat'l On Site | Length | Work Done (Previous) | Work Done (This) | Length (This)
1 | EWS-101 | 900 | 7 | 1 | 900mm | H7-N/24 | 4.49 | 1 | [5 empty] | 0 |  |  | 0
[5 empty] | 900mm | H7-N/25 | 4.49 | 1 | [5 empty] | 0 |  |  | 0
[5 empty] | 900mm | H7-N/26 | 4.49 | 1 | [5 empty] | 0 |  |  | 0
[5 empty] | 900mm | H7-N/27 | 4.49 | 1 | [5 empty] | 0 |  |  | 0
[13 empty] | TOTAL | 0 | TOTAL |  | 0
2 | EWS-101 | 900 | 8 | 1 | 900mm | H8-N/24 | 4.49 | 1 | 1 | 4.49 | 2205,2351,2347 | 215 | 1 | 4.49 | 100% |  | 4.49 | WIR 1086 R1
[5 empty] | 900mm | H8-N/25 | 4.49 | 1 | 1 | 4.49 | 2212,2351,2347 | 216 | 1 | 4.49 | 100% |  | 4.49 | WIR 1086 R1
[5 empty] | 900mm | H8-N/26 | 4.49 | 1 | 1 | 4.49 | 2351,2347 |  | 1 | 4.49 | 100% |  | 4.49 | WIR 1086 R1
[5 empty] | 900mm | H8-N/27 | 4.49 | 1 | 1 | 4.49 | 2351,2347 |  | 1 | 4.49 | 100% |  | 4.49 | WIR 1086 R1
[9 empty] | TOTAL | 17.96 |  |  | TOTAL | 17.96 | TOTAL |  | 17.96
3 | EWS-101 | 900 | 9 | 1 | 900mm | H9-N/25 | 4.49 | 1 | 1 | 4.49 | 2049,2055 | 190,191 | 1 | 4.49 | 100% |  | 4.49 | WIR 1087 R1
[5 empty] | 900mm | H9-N/26 | 4.49 | 1 | 1 | 4.49 | 2035,2049 | 188,190 | 1 | 4.49 | 100% |  | 4.49 | WIR 1087 R1
[5 empty] | 900mm | H9-N/27 | 4.49 | 1 | 1 | 4.49 | 2025,2049 | 190 | 1 | 4.49 | 100% |  | 4.49 | WIR 1087 R1
[5 empty] | 900mm | H9-N/28 | 4.49 | 1 | 1 | 4.49 | 2025,2049 | 190 | 1 | 4.49 | 100% |  | 4.49 | WIR 1087 R1
[9 empty] | TOTAL | 17.96 |  |  | TOTAL | 17.96 | TOTAL |  | 17.96
4 | EWS-101 | 900 | 10 | 1 | 900mm | H10-N/25 | 4.49 | 1 | 1 | 4.49 | 2035,2049 | 188,190 | 1 | 4.49 | 100% |  | 4.49 | WIR 1088 R1
[5 empty] | 900mm | H10-N/26 | 4.49 | 1 | 1 | 4.49 | 2025 | 186 | 1 | 4.49 | 100% |  | 4.49 | WIR 1088 R1
[5 empty] | 900mm | H10-N/27 | 4.49 | 1 | 1 | 4.49 | 2035 | 188 | 1 | 4.49 | 100% |  | 4.49 | WIR 1088 R1
[5 empty] | 900mm | H10-N/28 | 4.49 | 1 | 1 | 4.49 | 2035 | 188 | 1 | 4.49 | 100% |  | 4.49 | WIR 1088 R1
[9 empty] | TOTAL | 17.96 |  |  | TOTAL | 17.96 | TOTAL |  | 17.96
5 | EWS-101 | 900 | 11 | 1 | 900mm | H11-N/25 | 4.49 | 1 | 1 | 4.49 | 2416 | 237 | 1 | 4.49 | 100% |  | 4.49 | WIR 1089 R1
[5 empty] | 900mm | H11-N/26 | 4.49 | 1 | 1 | 4.49 | 2416 | 237 | 1 | 4.49 | 100% |  | 4.49 | WIR 1089 R1
[5 empty] | 900mm | H11-N/27 | 4.49 | 1 | 1 | 4.49 | 2419 | 237 | 1 | 4.49 | 100% |  | 4.49 | WIR 1089 R1
[5 empty] | 900mm | H11-N/28 | 4.49 | 1 | 1 | 4.49 | 2419 | 237 | 1 | 4.49 | 100% |  | 4.49 | WIR 1089 R1
[9 empty] | TOTAL | 17.96 |  |  | TOTAL | 17.96 | TOTAL |  | 17.96
6 | EWS-101 | 900 | 13 | 1 | 900mm | H13-N/39 | 4.49 | 1 | 1 | 4.49 | 2425,2434 | 238,239 | 1 | 4.49 | 100% |  | 4.49 | WIR 1108 R1
[5 empty] | 900mm | H13-N/40 | 4.49 | 1 | 1 | 4.49 | 2425 | 238 | 1 | 4.49 | 100% |  | 4.49 | WIR 1108 R1
[5 empty] | 900mm | H13-N/41 | 4.49 | 1 | 1 | 4.49 | 2425 | 238 | 1 | 4.49 | 100% |  | 4.49 | WIR 1108 R1
[5 empty] | 900mm | H13-N/42 | 4.49 | 1 | 1 | 4.49 | 2425 | 238 | 1 | 4.49 | 100% |  | 4.49 | WIR 1108 R1
[9 empty] | TOTAL | 17.96 |  |  | TOTAL | 17.96 | TOTAL |  | 17.96
7 | EWS-101 | 900 | 14 | 1 | 900mm | H14-N/29 | 4.49 | 1 | 1 | 4.49 | 2442 | 240 | 1 | 4.49 | 100% |  | 4.49 | WIR 1109 R1
[5 empty] | 900mm | H14-N/30 | 4.49 | 1 | 1 | 4.49 | 2442 | 240 | 1 | 4.49 | 100% |  | 4.49 | WIR 1109 R1
[5 empty] | 900mm | H14-N/31 | 4.49 | 1 | 1 | 4.49 | 2445 | 240 | 1 | 4.49 | 100% |  | 4.49 | WIR 1109 R1
[5 empty] | 900mm | H14-N/32 | 4.49 | 1 | 1 | 4.49 | 2445 | 240 | 1 | 4.49 | 100% |  | 4.49 | WIR 1109 R1
[9 empty] | TOTAL | 17.96 |  |  | TOTAL | 17.96 | TOTAL |  | 17.96
8 | EWS-101 | 900 | 15 | 1 | 900mm | H15-N/39 | 4.49 | 1 | 1 | 4.49 | 2447,2447,2448 | 240 | 1 | 4.49 | 100% |  | 4.49 | WIR 1110 R1
[5 empty] | 900mm | H15-N/40 | 4.49 | 1 | 1 | 4.49 | 2448 | 240 | 1 | 4.49 | 100% |  | 4.49 | WIR 1110 R1
[5 empty] | 900mm | H15-N/41 | 4.49 | 1 | 1 | 4.49 | 2448 | 240 | 1 | 4.49 | 100% |  | 4.49 | WIR 1110 R1
[5 empty] | 900mm | H15-N/42 | 4.49 | 1 | 1 | 4.49 | 2450 | 241 | 1 | 4.49 | 100% |  | 4.49 | WIR 1110 R1
[9 empty] | TOTAL | 17.96 |  |  | TOTAL | 17.96 | TOTAL |  | 17.96
9 | EWS-101 | 900 | 16 | 1 | 900mm | H16-N/29 | 4.49 | 1 | 1 | 4.49 | 2336,2450 | 229,241 | 1 | 4.49 | 100% |  | 4.49 | WIR 1153 R1
[5 empty] | 900mm | H16-N/30 | 4.49 | 1 | 1 | 4.49 | 2471 | 224 | 1 | 4.49 | 100% |  | 4.49 | WIR 1153 R1
[5 empty] | 900mm | H16-N/31 | 4.49 | 1 | 1 | 4.49 | 2336,2471 | 229,241 | 1 | 4.49 | 100% |  | 4.49 | WIR 1153 R1
[5 empty] | 900mm | H16-N/32 | 4.49 | 1 | 1 | 4.49 | 2336,2471 | 229,241 | 1 | 4.49 | 100% |  | 4.49 | WIR 1153 R1
[9 empty] | TOTAL | 17.96 |  |  | TOTAL | 17.96 | TOTAL |  | 17.96
10 | EWS-101 | 900 | 18 | 1 | 900mm | H18-N/21 | 4.49 | 1 | 1 | 4.49 | 2481,2482 |  | 1 | 4.49 | 100% |  | 4.49
[5 empty] | 900mm | H18-N/22 | 4.49 | 1 | 1 | 4.49 | 2481,2482 |  | 1 | 4.49 | 100% |  | 4.49
[5 empty] | 900mm | H18-N/23 | 4.49 | 1 | 1 | 4.49 | 2481,2482 |  | 1 | 4.49 | 100% |  | 4.49
[5 empty] | 900mm | H18-N/24 | 4.49 | 1 | 1 | 4.49 | 2481,2482,2614 | 271 | 1 | 4.49 | 100% |  | 4.49
[9 empty] | TOTAL | 17.96 |  |  | TOTAL | 17.96 | TOTAL |  | 17.96
11 | EWS-101 | 900 | 19 | 1 | 900mm | H19-N/20 | 4.49 | 1 | 1 | 4.49 | 2489,2491 |  | 1 | 4.49 | 100% |  | 4.49 | WIR 1209
[5 empty] | 900mm | H19-N/21 | 4.49 | 1 | 1 | 4.49 | 2489,2491 |  | 1 | 4.49 | 100% |  | 4.49 | WIR 1209
[5 empty] | 900mm | H19-N/22 | 4.49 | 1 | 1 | 4.49 | 2489 |  | 1 | 4.49 | 100% |  | 4.49 | WIR 1209
[5 empty] | 900mm | H19-N/23 | 4.49 | 1 | 1 | 4.49 | 2491 |  | 1 | 4.49 | 100% |  | 4.49 | WIR 1209
[9 empty] | TOTAL | 17.96 |  |  | TOTAL | 17.96 | TOTAL |  | 17.96
12 | EWS-101 | 900 | 20 | 1 | 900mm | H20-N/21 | 4.49 | 1 | 1 | 4.49 | 2493 |  | 1 | 4.49 | 100% |  | 4.49 | WIR 1183 R1
[5 empty] | 900mm | H20-N/22 | 4.49 | 1 | 1 | 4.49 | 2493 |  | 1 | 4.49 | 100% |  | 4.49 | WIR 1183 R1
[5 empty] | 900mm | H20-N/23 | 4.49 | 1 | 1 | 4.49 | 2493 |  | 1 | 4.49 | 100% |  | 4.49 | WIR 1183 R1
[5 empty] | 900mm | H20-N/24 | 4.49 | 1 | 1 | 4.49 | 2496 |  | 1 | 4.49 | 100% |  | 4.49 | WIR 1183 R1
[9 empty] | TOTAL | 17.96 |  |  | TOTAL | 17.96 | TOTAL |  | 17.96
13 | EWS-101 | 900 | 21 | 1 | 900mm | H21-N/20 | 4.49 | 1 | 1 | 4.49 | 2494,2495 |  | 1 | 4.49 | 100% |  | 4.49 | WIR 1184 R1
[5 empty] | 900mm | H21-N/21 | 4.49 | 1 | 1 | 4.49 | 2494,2495 |  | 1 | 4.49 | 100% |  | 4.49 | WIR 1184 R1
[5 empty] | 900mm | H21-N/22 | 4.49 | 1 | 1 | 4.49 | 2494,2495 |  | 1 | 4.49 | 100% |  | 4.49 | WIR 1184 R1
[5 empty] | 900mm | H21-N/23 | 4.49 | 1 | 1 | 4.49 | 2496 |  | 1 | 4.49 | 100% |  | 4.49 | WIR 1184 R1
[9 empty] | TOTAL | 17.96 |  |  | TOTAL | 17.96 | TOTAL |  | 17.96
14 | EWS-101 | 900 | 22 | 1 | 900mm | H22-N/21 | 4.49 | 1 | 1 | 4.49 | 2503 |  | 1 | 4.49 | 100% |  | 4.49 | WIR 1185 R1
[5 empty] | 900mm | H22-N/22 | 4.49 | 1 | 1 | 4.49 | 2503 |  | 1 | 4.49 | 100% |  | 4.49 | WIR 1185 R1
[5 empty] | 900mm | H22-N/23 | 4.49 | 1 | 1 | 4.49 | 2498 |  | 1 | 4.49 | 100% |  | 4.49 | WIR 1185 R1
[5 empty] | 900mm | H22-N/24 | 4.49 | 1 | 1 | 4.49 | 2498 |  | 1 | 4.49 | 100% |  | 4.49 | WIR 1185 R1
[9 empty] | TOTAL | 17.96 |  |  | TOTAL | 17.96 | TOTAL |  | 17.96
15 | EWS-101 | 900 | 23 | 1 | 900mm | H23-N/21 | 4.49 | 1 | 1 | 4.49 | 2497 |  | 1 | 4.49 | 100% |  | 4.49 | WIR 1186 R1
[5 empty] | 900mm | H23-N/22 | 4.49 | 1 | 1 | 4.49 | 2497 |  | 1 | 4.49 | 100% |  | 4.49 | WIR 1186 R1
[5 empty] | 900mm | H23-N/23 | 4.49 | 1 | 1 | 4.49 | 2505 |  | 1 | 4.49 | 100% |  | 4.49 | WIR 1186 R1
[5 empty] | 900mm | H23-N/24 | 4.49 | 1 | 1 | 4.49 | 2505 |  | 1 | 4.49 | 100% |  | 4.49 | WIR 1186 R1
[9 empty] | TOTAL | 17.96 |  |  | TOTAL | 17.96 | TOTAL |  | 17.96
16 | EWS-101 | 900 | 25 | 1 | 900mm | H25-N/30 | 4.49 | 1 | 1 | 4.49 | 2508 |  | 1 | 4.49 | 100% |  | 4.49 | WIR 1187 R1
[5 empty] | 900mm | H25-N/31 | 4.49 | 1 | 1 | 4.49 | 2508 |  | 1 | 4.49 | 100% |  | 4.49 | WIR 1187 R1
[5 empty] | 900mm | H25-N/32 | 4.49 | 1 | 1 | 4.49 | 2532 | 256 | 1 | 4.49 | 100% |  | 4.49 | WIR 1187 R1
[5 empty] | 900mm | H25-N/33 | 4.49 | 1 | 1 | 4.49 | 2532 | 256 | 1 | 4.49 | 100% |  | 4.49 | WIR 1187 R1
[9 empty] | TOTAL | 17.96 |  |  | TOTAL | 17.96 | TOTAL |  | 17.96
17 | EWS-101 | 900 | 26 | 1 | 900mm | H26-N/29 | 4.49 | 1 | 1 | 4.49 | 2599 |  | 1 | 4.49 | 100% |  | 4.49 | WIR 1188 R1
[5 empty] | 900mm | H26-N/30 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% |  | 4.49 | WIR 1188 R1
[5 empty] | 900mm | H26-N/31 | 4.49 | 1 | 1 | 4.49 | 2517 |  | 1 | 4.49 | 100% |  | 4.49 | WIR 1188 R1
[5 empty] | 900mm | H26-N/32 | 4.49 | 1 | 1 | 4.49 | 2517 |  | 1 | 4.49 | 100% |  | 4.49 | WIR 1188 R1
[9 empty] | TOTAL | 17.96 |  |  | TOTAL | 17.96 | TOTAL |  | 17.96
18 | EWS-101 | 900 | 27 | 1 | 900mm | H27-N/30 | 4.49 | 1 | 1 | 4.49 | 2542 | 256 | 1 | 4.49 | 100% |  | 4.49 | WIR 1189 R1
[5 empty] | 900mm | H27-N/31 | 4.49 | 1 | 1 | 4.49 | 2542 | 256 | 1 | 4.49 | 100% |  | 4.49 | WIR 1189 R1
[5 empty] | 900mm | H27-N/32 | 4.49 | 1 | 1 | 4.49 | 2542 | 256 | 1 | 4.49 | 100% |  | 4.49 | WIR 1189 R1
[5 empty] | 900mm | H27-N/33 | 4.49 | 1 | 1 | 4.49 |  |  | 1 | 4.49 | 100% |  | 4.49 | WIR 1189 R1
[9 empty] | TOTAL | 17.96 |  |  | TOTAL | 17.96 | TOTAL |  | 17.96
[6 empty] | LVL | L | Qty |  | Mat'l Produced (Length) |  |  | Mat'l On Site | Mat'l On Site (Length) | Work Done |  | Work Done (Length)
[6 empty] | H7 | 17.96 | [5 empty] | 0% | 0 | 0% |  | 0
| BOQ Item N |  |  |  | 900mm | H8 to H29 | 305.32 |  |  | 305.32 |  |  | 100% | 305.32 | 100% |  | 305.32
[6 empty] | TOTAL | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | #DIV/0! | 0

## Breakdown - Divider
PROJECT: PLOT 18, BUSINESS BAY, DUBAI, PROJECT
SUB-CONTRACTOR: ARABIAN PROFILE COMPANY LIMITED
DOCUMENT TITLE: SUB-CONTRACT PRICE SUM
PACKAGE: The Design and Construction of GRC Cladding System at Plot 18, Business Bay, Dubai, Project
| GRC BALCONY SEPARATOR / DIVIDER PANEL | BOQ Qty | Unit | Sum | % | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Apartment 6th to 31st Levels |  | nos | 4
| Material Produced |  |  | 3 | 75%
| Delivered |  |  | 3 | 75%
| Projected Progress |  |  | 0 | 0%
6th Level - Apartment
| Nos. |  |  | 2
| Material Produced |  |  | 2 |  | 1 | 1
| Delivered Onsite |  |  | 2 |  | 1 | 1
| D.N. No. |  |  |  |  | 1916 | 2054
| MIR Ref No. |  |  |  |  | 173 | 191
| Projected Progress |  |  | 0 | 0%
WIR Ref No.
7th Level - Apartment
| Nos. |  |  | 2
| Material Produced |  |  | 2 |  | 1 | 1
| Delivered |  |  | 2 |  | 1 | 1
| D.N. No. |  |  |  |  | 1916
| MIR Ref No. |  |  |  |  | 173
| Projected Progress |  |  | 2 | 100% | 1 | 1
WIR Ref No.
8th Level - Apartment
| Nos. |  |  | 2
| Material Produced |  |  | 2 |  | 1 | 1
| Delivered |  |  | 2 |  | 1 | 1
| D.N. No. |  |  |  |  | 1194
| MIR Ref No. |  |  |  |  | 034
| Projected Progress |  |  | 2 | 100% | 1 | 1
WIR Ref No.
9th Level - Apartment
| Nos. |  |  | 2
| Material Produced |  |  | 2 |  | 1 | 1
| Delivered |  |  | 2 |  | 1 | 1
| D.N. No. | [5 empty] | 1818
| MIR Ref No. | [5 empty] | 165
| Projected Progress |  |  | 2 | 100% | 1 | 1
WIR Ref No.
10th Level - Apartment
| Nos. |  |  | 1
| Material Produced |  |  | 1 |  | 1
| Delivered |  |  | 1 |  | 1
| D.N. No. |  |  |  |  | 1153,1828
| MIR Ref No. |  |  |  |  | 166
| Projected Progress |  |  | 1 | 100% | 1
WIR Ref No.
11th Level - Apartment
| Nos. |  |  | 1
| Material Produced |  |  | 1 |  | 1
| Delivered |  |  | 1 |  | 1
| D.N. No. |  |  |  |  | 1828
| MIR Ref No. |  |  |  |  | 166
| Projected Progress |  |  | 1 | 100% | 1
WIR Ref No.
12th Level - Apartment
| Nos. |  |  | 1
| Material Produced |  |  | 1 |  | 1
| Delivered |  |  | 1 |  | 1
| D.N. No. |  |  |  |  | 1828
| MIR Ref No. |  |  |  |  | 166
| Projected Progress |  |  | 1 | 100% | 1
WIR Ref No.
13th Level - Apartment
| Nos. |  |  | 1
| Material Produced |  |  | 1 |  | 1
| Delivered |  |  | 1 |  | 1
| D.N. No. |  |  |  |  | 1828
| MIR Ref No. |  |  |  |  | 166
| Projected Progress |  |  | 1 | 100% | 1
WIR Ref No.
14th Level - Apartment
| Nos. |  |  | 1
| Material Produced |  |  | 1 |  | 1
| Delivered |  |  | 1 |  | 1
| D.N. No. |  |  |  |  | 1818,1828
| MIR Ref No. |  |  |  |  | 165,166
| Projected Progress |  |  | 1 | 100% | 1
WIR Ref No.
15th Level - Apartment
| Nos. |  |  | 1
| Material Produced |  |  | 1 |  | 1
| Delivered |  |  | 1 |  | 1
| D.N. No. |  |  |  |  | 1828
MIR Ref No.
| Projected Progress |  |  | 1 | 100% | 1
WIR Ref No.
16th Level - Apartment
| Nos. |  |  | 1
| Material Produced |  |  | 1 |  | 1
| Delivered |  |  | 1 |  | 1
| D.N. No. |  |  |  |  | 2019
| MIR Ref No. |  |  |  |  | 185
| Projected Progress |  |  | 1 | 100% | 1
WIR Ref No.
17th Level - Apartment
| Nos. |  |  | 1
| Material Produced |  |  | 1 |  | 1
| Delivered |  |  | 1 |  | 1
| D.N. No. |  |  |  |  | 2019
| MIR Ref No. |  |  |  |  | 185
| Projected Progress |  |  | 1 | 100% | 1
WIR Ref No.
18th Level - Apartment
| Nos. |  |  | 2
| Material Produced |  |  | 2 |  | 1 | 1
| Delivered |  |  | 2 |  | 1 | 1
| D.N. No. |  |  |  |  | 2018 | 2018
| MIR Ref No. |  |  |  |  | 185 | 185
| Projected Progress |  |  | 2 | 100% | 1 | 1
WIR Ref No.
19th Level - Apartment
| Nos. |  |  | 3
| Material Produced |  |  | 3 |  | 1 | 1 | 1
| Delivered |  |  | 3 |  | 1 | 1 | 1
| D.N. No. |  |  |  |  | 2018 | 2018 | 2054
| MIR Ref No. |  |  |  |  | 185 | 185 | 191
| Projected Progress |  |  | 3 | 100% | 1 | 1 | 1
| WIR Ref No. |  |  |  |  | 976 | 976
20th Level - Apartment
| Nos. |  |  | 2
| Material Produced |  |  | 2 |  | 1 | 1
| Delivered |  |  | 2 |  | 1 | 1
| D.N. No. |  |  |  |  | 2054 | 2054
| MIR Ref No. |  |  |  |  | 191 | 191
| Projected Progress |  |  | 2 | 100% | 1 | 1
WIR Ref No.
21st Level - Apartment
| Nos. |  |  | 3
| Material Produced |  |  | 3 |  | 1 | 1 | 1
| Delivered |  |  | 3 |  | 1 | 1 | 1
| D.N. No. |  |  |  |  | 2055 | 2055 | 2072
| MIR Ref No. |  |  |  |  | 191 | 191 | 194
| Projected Progress |  |  | 3 | 100% | 1 | 1 | 1
WIR Ref No.
22nd Level - Apartment
| Nos. |  |  | 2
| Material Produced |  |  | 2 |  | 1 | 1
| Delivered |  |  | 2 |  | 1 | 1
| D.N. No. |  |  |  |  | 2019 | 2019
| MIR Ref No. |  |  |  |  | 185 | 185
| Projected Progress |  |  | 2 | 100% | 1 | 1
WIR Ref No.
23rd Level - Apartment
| Nos. |  |  | 0
| Material Produced |  |  | 0
| Delivered |  |  | 0
D.N. No.
MIR Ref No.
| Projected Progress |  |  | 0
WIR Ref No.
24th Level - Apartment
| Nos. |  |  | 0
| Material Produced |  |  | 0
| Delivered |  |  | 0
D.N. No.
MIR Ref No.
| Projected Progress |  |  | 0
WIR Ref No.
25th Level - Apartment
| Nos. |  |  | 0
| Material Produced |  |  | 0
| Delivered |  |  | 0
D.N. No.
MIR Ref No.
| Projected Progress |  |  | 0
WIR Ref No.
26th Level - Apartment
| Nos. |  |  | 0
| Material Produced |  |  | 0
| Delivered |  |  | 0
D.N. No.
MIR Ref No.
| Projected Progress |  |  | 0
WIR Ref No.
27th Level - Apartment
| Nos. |  |  | 1 |  | 1
| Material Produced |  |  | 1 |  | 1
| Delivered |  |  | 1 |  | 1
| D.N. No. |  |  |  |  | 3101
| MIR Ref No. |  |  |  |  | 323
| Projected Progress |  |  | 0 | 0%
WIR Ref No.
28th Level - Apartment
| Nos. |  |  | 1
| Material Produced |  |  | 0
| Delivered |  |  | 0
D.N. No.
MIR Ref No.
| Projected Progress |  |  | 0 | 0%
WIR Ref No.
29th Level - Apartment
| Nos. |  |  | 0
| Material Produced |  |  | 0
| Delivered |  |  | 0
D.N. No.
MIR Ref No.
| Projected Progress |  |  | 0
WIR Ref No.
30th Level - Apartment
| Nos. |  |  | 0
| Material Produced |  |  | 0
| Delivered |  |  | 0
D.N. No.
MIR Ref No.
| Projected Progress |  |  | 0
WIR Ref No.
31st Level - Apartment
| Nos. |  |  | 0
| Material Produced |  |  | 0
| Delivered |  |  | 0
D.N. No.
MIR Ref No.
| Projected Progress |  |  | 0
WIR Ref No.
| Hotel Level 7th to 29th (600mm) |  | nos | 18
| Material Produced |  |  | 20 | 111.1%
| Delivered |  |  | 20 | 111.1%
| Projected Progress |  |  | 7 | 38.89%
7th Level - Hotel
| Nos. |  |  | 7
| Material Produced |  |  | 7 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Delivered |  |  | 7 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
| D.N. No. |  |  |  |  | 2402,2405,2960 | 2050,2466 | 2050 | 2050 | 2071 | 2071
| MIR Ref No. | [5 empty] | 192 | 192 | 192 | 194 | 194
| Projected Progress |  |  | 7 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1
WIR Ref No.
8th Level - Hotel
| Nos. |  |  | 7
| Material Produced |  |  | 7 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Delivered |  |  | 7 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
| D.N. No. |  |  |  |  | 1543,2261 | 1543 | 1543 | 1543 | 1553 | 1553 | 1553
| MIR Ref No. |  |  |  |  | 222
| Projected Progress |  |  | 7 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1
WIR Ref No.
9th Level - Hotel
| Nos. |  |  | 7
| Material Produced |  |  | 7 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Delivered |  |  | 7 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
| D.N. No. |  |  |  |  | 1579,2402 | 1579,2418 | 1579 | 1579 | 1579 | 1579 | 1581
| MIR Ref No. | [10 empty] | 139
| Projected Progress |  |  | 7 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1
WIR Ref No.
10th Level - Hotel
| Nos. |  |  | 1
| Material Produced |  |  | 1 |  |  | 1
| Delivered |  |  | 1 |  |  | 1
| D.N. No. |  |  |  |  | 1581,2405 | 1581,2464,2466 | 1581 | 1956 | 1818 | 2023 | 1944
| MIR Ref No. |  |  |  |  | 139 | 139 | 139 | 178 | 165 | 186 | 177
| Projected Progress |  |  | 1 | 100% |  | 1
WIR Ref No.
11th Level - Hotel
| Nos. |  |  | 7
| Material Produced |  |  | 7 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Delivered |  |  | 7 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
| D.N. No. |  |  |  |  | 1944,2402 | 1944 | 1944 | 1973 | 2080 | 2080 | 2080
| MIR Ref No. |  |  |  |  | 177 | 177 | 177 | 180 | 195 | 195 | 195
| Projected Progress |  |  | 7 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1
| WIR Ref No. |  |  |  |  | 0652 | 0652 | 0652 | 0652 | 0652 | 0652
12th Level - Hotel
| Nos. |  |  | 15
| Material Produced |  |  | 15 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Delivered |  |  | 15 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| D.N. No. |  |  |  |  | 1956,2271,2428 | 1818,2092,2464,2466 | 1818,2092 | 1973 | 1956 | 2080 | 2082 | 2083 | 1863 | 1863 | 1863 |  | 1863 | 1863 | 1863
| MIR Ref No. |  |  |  |  | 178,223 | 165,198 | 165,198 | 180 | 178 | 195 | 196 | 196 | 169 | 169 | 169 |  | 169 | 169 | 169
| Projected Progress |  |  | 15 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
WIR Ref No.
| 13th Level - Hotel |  |  |  |  | H13-D/01
| Nos. |  |  | 15
| Material Produced |  |  | 15 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Delivered |  |  | 15 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| D.N. No. |  |  |  |  | 2083 | 2052,2464,2466 | 2051 | 2051 | 2051 |  | 2082 | 2051 | 2052 | 2052 | 2052 | 2100 | 2092 | 2083 | 2092
| MIR Ref No. |  |  |  |  | 196 | 190 | 190 | 190 | 190 |  | 196 | 190 | 190 | 190 | 190 | 199 | 1 | 196 | 198
| Projected Progress |  |  | 15 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
WIR Ref No.
14th Level - Hotel
| Nos. |  |  | 14
| Material Produced |  |  | 14 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Delivered |  |  | 14 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| D.N. No. |  |  |  |  | 2051 | 2052 |  | 1944 | 1978 | 2023 | 1956 | 1978 | 1978 | 1978 | 1981 | 1996 | 2082 | 1978
| MIR Ref No. |  |  |  |  | 190 | 190 |  | 177 | 181 | 186 | 178 | 181 | 181 | 181 | 182 | 183 | 196 | 181
| Projected Progress |  |  | 14 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| WIR Ref No. |  |  |  |  | 0795 | 0795 | 0795 | 0795 | 1004 | 0795 | 0795 | 1004 | 0795 | 0795 | 0795 | 0795 | 0795 | 0795
15th Level - Hotel
| Nos. |  |  | 1
| Material Produced |  |  | 1 |  | 1
| Delivered |  |  | 1 |  | 1
| D.N. No. |  |  |  |  | 1956 | 2023,2464,2466 | 2083 | 1944 | 1981 | 1981 |  |  | 2023 | 2082 | 1973 | 1973 | 1981 | 1973 | 1981
| MIR Ref No. |  |  |  |  | 178 | 186 | 196 | 177 | 182 | 182 |  |  | 186 | 196 | 180 | 180 | 182 | 180 | 182
| Projected Progress |  |  | 0 | 0%
| WIR Ref No. | [12 empty] | 860 | 860 | 860 | 860 | 860 | 860 | 860
16th Level - Hotel
| Nos. |  |  | 3
| Material Produced |  |  | 3 | [6 empty] | 1 | 1 | 1
| Delivered |  |  | 3 | [6 empty] | 1 | 1 | 1
| D.N. No. |  |  |  |  | 2067 | 2071 | 2067 | 2092 | 2092 | 2067 | 2099 | 2067 | 2509 | 2509 | 2509 | 2509 | 2518 | 2518
| MIR Ref No. |  |  |  |  | 194 | 194 | 194 |  |  | 194 | 199 | 194
| Projected Progress |  |  | 0 | 0%
WIR Ref No.
17th Level - Hotel
| Nos. |  |  | 0
| Material Produced |  |  | 0
| Delivered |  |  | 0
D.N. No.
MIR Ref No.
| Projected Progress |  |  | 0
WIR Ref No.
18th Level - Hotel
| Nos. |  |  | 2
| Material Produced |  |  | 0
| Delivered |  |  | 0
D.N. No.
MIR Ref No.
| Projected Progress |  |  | 0 | 0%
WIR Ref No.
19th Level - Hotel
| Nos. |  |  | 1
| Material Produced |  |  | 1 |  |  | 1
| Delivered |  |  | 1 |  |  | 1
| D.N. No. |  |  |  |  | 2071 | 2074
| MIR Ref No. |  |  |  |  | 194 | 195
| Projected Progress |  |  | 1 | 100% |  | 1
WIR Ref No.
20th Level - Hotel
| Nos. |  |  | 4
| Material Produced |  |  | 4 |  | 1 | 1 | 1 | 1
| Delivered |  |  | 4 |  | 1 | 1 | 1 | 1
| D.N. No. |  |  |  |  | 2023 | 1996,2464 | 1996 | 1996
| MIR Ref No. |  |  |  |  | 186 | 183 | 183 | 183
| Projected Progress |  |  | 4 | 100% | 1 | 1 | 1 | 1
WIR Ref No.
21st Level - Hotel
| Nos. |  |  | 4
| Material Produced |  |  | 4 |  | 1 | 1 | 1 | 1
| Delivered |  |  | 4 |  | 1 | 1 | 1 | 1
| D.N. No. |  |  |  |  | 1997 | 1997 | 1997 | 1997
| MIR Ref No. |  |  |  |  | 183 | 183 | 183 | 183
| Projected Progress |  |  | 4 | 100% | 1 | 1 | 1 | 1
WIR Ref No.
22nd Level - Hotel
| Nos. |  |  | 4
| Material Produced |  |  | 4 |  | 1 | 1 | 1 | 1
| Delivered |  |  | 4 |  | 1 | 1 | 1 | 1
| D.N. No. |  |  |  |  | 2040 | 2040 | 2040 | 2053
| MIR Ref No. |  |  |  |  | 188 | 188 | 188 | 190
| Projected Progress |  |  | 4 | 100% | 1 | 1 | 1 | 1
WIR Ref No.
23rd Level - Hotel
| Nos. |  |  | 4
| Material Produced |  |  | 4 |  | 1 | 1 | 1 | 1
| Delivered |  |  | 4 |  | 1 | 1 | 1 | 1
| D.N. No. |  |  |  |  | 2053 | 2040 | 2053 | 2053
| MIR Ref No. |  |  |  |  | 190 | 188 | 190 | 190
| Projected Progress |  |  | 4 | 100% | 1 | 1 | 1 | 1
WIR Ref No.
24th Level - Hotel
| Nos. |  |  | 15
| Material Produced |  |  | 15 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Delivered |  |  | 15 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| D.N. No. |  |  |  |  | 2058 | 2058,2466 | 2058 | 2058 | 2074 | 2074 | 2068 | 2068 | 2068 | 2336 | 2356 | 2356 | 2356 | 2356 | 2357
| MIR Ref No. |  |  |  |  | 191 | 191 | 191 | 191 | 195 | 195 | 194 | 194 | 194 |  | 230 | 230 | 230 | 230
| Projected Progress |  |  | 15 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| WIR Ref No. | [13 empty] | 1170
25th Level - Hotel
| Nos. |  |  | 15
| Material Produced |  |  | 15 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Delivered |  |  | 15 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| D.N. No. |  |  |  |  | 2066 | 2066 | 2075 | 2075 | 2075 | 2068 | 2075 | 2074 | 2357 | 2506 | 2357 | 2357 | 2506 | 2506 | 2506
| MIR Ref No. |  |  |  |  | 193 | 193 | 195 | 195 | 195 | 194 | 195 | 195
| Projected Progress |  |  | 15 | 100% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| WIR Ref No. |  |  |  |  | 1171 | 1171 | 1171 | 1171 | 1171 | 1171 | 1171 | 1171 | 1171 | 1171 | 1171 | 1171 | 1171 | 1171 | 1171
26th Level - Hotel
| Nos. |  |  | 1
| Material Produced |  |  | 1 | [8 empty] | 1
| Delivered |  |  | 1 | [8 empty] | 1
| D.N. No. |  |  |  |  | 2032 | 2066 | 2066 | 2032 | 2032 | 2032 | 2050 | 2032 | 2382 | 2382 | 2382 | 2518 | 2518 | 2382
| MIR Ref No. |  |  |  |  | 189 | 193 | 193 | 189 | 189 | 189 | 192 | 189 | 234 | 234 | 234 |  |  | 234
| Projected Progress |  |  | 1 | 100% | [7 empty] | 1
WIR Ref No.
27th Level - Hotel
| Nos. |  |  | 9
| Material Produced |  |  | 13 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Delivered |  |  | 13 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| D.N. No. |  |  |  |  | 2107 | 2107 | 2099 | 2099 | 2099 | 2107 | 2107 | 2634 | 2634 | 2634 | 2634 | 2614 | 2614
| MIR Ref No. |  |  |  |  | 201 | 201 | 199 | 199 | 199 | 201 | 201 | 274 | 274,321 | 274,321 | 274 | 271 | 271
| Projected Progress |  |  | 4 | 44.44% | [6 empty] | 1 | 1 | 1 | 1
WIR Ref No.
28th Level - Hotel
| Nos. |  |  | 0
| Material Produced |  |  | 0
| Delivered |  |  | 0
D.N. No.
MIR Ref No.
| Projected Progress |  |  | 0
WIR Ref No.
29th Level - Hotel
| Nos. |  |  | 0
| Material Produced |  |  | 0
| Delivered |  |  | 0
D.N. No.
MIR Ref No.
| Projected Progress |  |  | 0
WIR Ref No.
Note on J124: Could not be installed removed from scope
Note on J140: Could not be installed removed from scope
Note on I258: WIR-L10-01250
Note on H282: WIR-L13-01246
Note on I330: WIR-L19-01252

## SI 130 - Progress (hidden)
Project Name: PLOT 18 OMNIYAT
Package: Supply and Installation of GRC Cladding
Subj.: | S.I. 130 - Engineering, Procurement & Installation Works for the Additional GRC Panel
INSTALLATION PROGRESS
Item | Drawing Ref | Description | Level | A1 | A2 | A3 | A4 | Quantities (m2) | A1 | A2 | A3 | A4 | Quantities (m2) | WIR Ref. | Remarks
| Dwg. Ref. | Description
1 | APL-AX-SD-L7-00029-Rev 02 | GRC PANELS | Residential Level 7 | 4.76 | 4.76 | 4.66 | 0.74 | 14.92 | 4.76 | 4.76 | 4.66 | 0.74 | 14.92 | L7-0070-R1
2 | APL-AX-SD-L7-00029-Rev 02 | GRC PANELS | Residential Level 7 |  |  |  |  | 0 |  |  |  |  | 0
2 | APL-AX-SD-L8-00030-Rev 02 | GRC PANELS | Residential Level 8 | 4.78 | 4.78 | 4.69 | 4.82 | 19.07 | 4.78 | 4.78 | 4.69 | 4.82 | 19.07 | L8-0057-R1
4 | APL-AX-SD-L8-00030-Rev 02 | GRC PANELS | Residential Level 8 |  |  |  |  | 0 |  |  |  |  | 0
3 | APL-AX-SD-L9-00031 Rev 01 | GRC PANELS | Residential Level 9 | 4.76 | 4.76 | 4.66 | 0.74 | 14.92 | 4.76 | 4.76 | 4.66 | 0.74 | 14.92 | L9-01223-R0, L9-0311-R3
6 | APL-AX-SD-L9-00031 Rev 01 | GRC PANELS | Residential Level 9 |  |  |  |  | 0 |  |  |  |  | 0
4 | APL-AX-SD-L11-00034 Rev 01 | GRC PANELS | Residential Level 11 | 5.05 | 5.05 |  | 1.93 | 12.03 | 5.05 | 5.05 |  | 1.93 | 12.03 | L11-00435-R4, L11-01140-R2
5 | APL-AX-SD-L12-00035 Rev 00 | GRC PANELS | Residential Level 12 | 4.78 | 4.78 | 3.69 | 3.63 | 16.88 | 4.78 | 4.78 | 3.69 | 3.63 | 16.88 | L12-00850-R1, L12-01141-R0, L12-01242-R0
9 | APL-AX-SD-L12-00035 Rev 00 | GRC PANELS | Residential Level 12 |  |  |  |  | 0 |  |  |  |  | 0
6 | APL-AX-SD-L13-00036 Rev 00 | GRC PANELS | Residential Level 13 | 4.76 | 4.76 | 3.73 |  | 13.25 | 4.76 | 4.76 | 3.73 |  | 13.25 | L13-01229-R0
11 | APL-AX-SD-L13-00036 Rev 01 | GRC PANELS | Residential Level 13 |  |  |  |  | 0 |  |  |  |  | 0
7 | APL-AX-SD-L14-00037 Rev 00 | GRC PANELS | Residential Level 14 | 4.78 | 4.78 | 3.69 |  | 13.25 | 4.78 | 4.78 | 3.69 |  | 13.25 | L14-00852-R1, L14-01222-R0
13 | APL-AX-SD-L14-00037 Rev 00 | GRC PANELS | Residential Level 14 |  |  |  |  | 0 |  |  |  |  | 0
8 | APL-AX-SD-L15-00038 Rev 00 | GRC PANELS | Residential Level 15 | 4.76 | 4.76 | 3.73 |  | 13.25 | 4.76 | 4.76 | 3.73 |  | 13.25 | L15-01207-R0, L15-01156-R0
15 | APL-AX-SD-L15-00038 Rev 00 | GRC PANELS | Residential Level 15 |  |  |  |  | 0 |  |  |  |  | 0
9 | APL-AX-SD-L16-00039 Rev 00 | GRC PANELS | Residential Level 16 | 4.78 | 4.78 | 3.69 | 3.73 | 16.98 | 4.78 | 4.78 | 3.69 | 3.73 | 16.98 | L16-01157-R0, L16-01206-R0
17 | APL-AX-SD-L16-00039 Rev 00 | GRC PANELS | Residential Level 16 |  |  |  |  | 0 |  |  |  |  | 0
10 | APL-AX-SD-L17-00040 Rev 00 | GRC PANELS | Residential Level 17 | 4.76 | 4.76 | 3.73 |  | 13.25 | 4.76 | 4.76 | 3.73 |  | 13.25 | L17-01158-R0, L17-01205-R0
19 | APL-AX-SD-L17-00040 Rev 00 | GRC PANELS | Residential Level 17 |  |  |  |  | 0 |  |  |  |  | 0
11 | APL-AX-SD-L17-00041 Rev 02 | GRC PANELS | Residential Level 18 |  |  | 5.24 | 3.93 | 9.17 |  |  | 5.24 | 3.93 | 9.17 | L18-00755-R3, L18-01130-R0
12 | APL-AX-SD-L19-00042 Rev 01 | GRC PANELS | Residential Level 19 | 4.76 | 4.76 |  |  | 9.52 | 4.76 | 4.76 |  |  | 9.52 | L19-01213-R0
13 | APL-AX-SD-L20-00043 Rev 01 | GRC PANELS | Residential Level 20 | 4.77 | 4.77 | 5.24 | 3.93 | 18.71 | 4.77 | 4.77 | 5.24 | 3.93 | 18.71 | L20-01203-R0' L20-01212-R0
22 | APL-AX-SD-L20-00043 Rev 01 | GRC PANELS | Residential Level 20 |  |  |  |  | 0 |  |  |  |  | 0
14 | APL-AX-SD-L21-00044 Rev 00 | GRC PANELS | Residential Level 21 | 4.76 | 4.76 |  |  | 9.52 | 4.76 | 4.76 |  |  | 9.52 | L21-01202-R0
15 | APL-AX-SD-L22-00045 Rev 01 | GRC PANELS | Residential Level 22 | 4.77 | 4.77 | 5.24 | 3.93 | 18.71 | 4.77 | 4.77 | 5.24 | 3.93 | 18.71 | L22-00753-R3, L22-01201-R0, L22-01210-R0
25 | APL-AX-SD-L22-00045 Rev 01 | GRC PANELS | Residential Level 22 |  |  |  |  | 0 |  |  |  |  | 0
16 | APL-AX-SD-L22-00046 Rev 01 | GRC PANELS | Residential Level 23 |  |  | 5.44 | 4.09 | 9.53 |  |  | 5.44 | 4.09 | 9.53 | L23-01244-R0, L23-01268-R0 | DN No. AJM003064
17 | APL-AX-SD-L26-00049 Rev 00 | GRC PANELS | Residential Level 26 | 5.14 | 7.26 |  |  | 12.4 | 5.14 | 7.26 |  |  | 12.4 | L26-01034-R1
18 | APL-AX-SD-L27-00050 Rev 03 | GRC PANELS | Residential Level 27 | 5 | 7.76 |  | 1.16 | 13.92 | 5 | 7.76 |  | 1.16 | 13.92 | L27-01123-R1, L12-01242-R0
19 | APL-AX-SD-L28-00051 Rev 00 | GRC PANELS | Residential Level 28 | 4.76 | 4.76 |  |  | 9.52 | 4.76 | 4.76 |  |  | 9.52 | L28-01045-R1
20 | APL-AX-SD-L28-00052 Rev 02 | GRC PANELS | Residential Level 29 |  |  |  | 1.16 | 1.16 |  |  |  | 1.16 | 1.16 | L28-01052-R0
| SUB - TOTAL QUANTITY | [6 empty] | 259.96 |  |  |  |  | 259.96 | 0
1 | APL-AX-SD-L8-00005-Rev 01 | GRC PANELS | Hotel Level 8 | 2.13 | 2.13 |  |  | 4.26 | 2.13 | 2.13 |  |  | 4.26 | L8-01086-R1
2 | APL-AX-SD-L9-00006-Rev 01 | GRC PANELS | Hotel Level 9 | 2.13 | 2.55 |  |  | 4.68 | 2.13 | 2.55 |  |  | 4.68 | L9-01087-R1
3 | APL-AX-SD-L10-00007-Rev 01 | GRC PANELS | Hotel Level 10 | 2.13 | 2.55 |  |  | 4.68 | 2.13 | 2.55 |  |  | 4.68 | L10-01088-R1
4 | APL-AX-SD-L11-00008-Rev 00 | GRC PANELS | Hotel Level 11 | 2.13 | 2.13 |  |  | 4.26 | 2.13 | 2.13 |  |  | 4.26 | L11-01089-R1
5 | APL-AX-SD-L12-00009-Rev 02 | GRC PANELS | Hotel Level 12 |  |  | 3.26 | 4.18 | 7.44 |  |  | 3.26 | 4.18 | 7.44 | L12-01075-R0
6 | APL-AX-SD-L13-00010-Rev 01 | GRC PANELS | Hotel Level 13 | 2.15 | 2.58 | 3.26 | 4.18 | 12.17 | 2.15 | 2.58 | 3.26 | 4.18 | 12.17 | L13-01062-R0, L13-01108-R1, L13-01197-R0
7 | APL-AX-SD-L14-00011-Rev 00 | GRC PANELS | Hotel Level 14 | 2.15 | 2.58 |  |  | 4.73 | 2.15 | 2.58 |  |  | 4.73 | L14-01109-R1
8 | APL-AX-SD-L15-00012-Rev 01 | GRC PANELS | Hotel Level 15 | 2.15 | 2.58 | 3.26 | 4.18 | 12.17 | 2.15 | 2.58 | 3.26 | 4.18 | 12.17 | L15-01079-R0, L15-01110-R1, L15-01119-R0,
9 | APL-AX-SD-L16-00013-Rev 01 | GRC PANELS | Hotel Level 16 | 2.15 | 2.58 |  |  | 4.73 | 2.15 | 2.58 |  |  | 4.73 | L16-01111-R1
10 | APL-AX-SD-L18-00015-Rev 00 | GRC PANELS | Hotel Level 18 | 2.13 | 2.57 | 2.58 | 2.56 | 9.84 | 2.13 | 2.57 | 2.58 | 2.56 | 9.84 | L18-01177-R0, L18-01147-R2
11 | APL-AX-SD-L19-00016-Rev 00 | GRC PANELS | Hotel Level 19 | 2.11 | 2.11 | 2.58 | 2.56 | 9.36 | 2.11 | 2.11 | 2.58 | 2.56 | 9.36 | L19-01037-R1, L19-01209-R1
12 | APL-AX-SD-L20-00017-Rev 00 | GRC PANELS | Hotel Level 20 | 2.11 | 2.57 | 2.58 | 2.56 | 9.82 | 2.11 | 2.57 | 2.58 | 2.56 | 9.82 | L20-01059-R1, L20-01183-R1
13 | APL-AX-SD-L21-00018-Rev 00 | GRC PANELS | Hotel Level 21 | 2.11 | 2.11 | 2.58 | 2.56 | 9.36 | 2.11 | 2.11 | 2.58 | 2.56 | 9.36 | L21-01184-R1, L21-01060-R0
14 | APL-AX-SD-L20-00019-Rev 00 | GRC PANELS | Hotel Level 22 | 2.11 | 2.57 | 2.58 | 2.56 | 9.82 | 2.11 | 2.57 | 2.58 | 2.56 | 9.82 | L22-01061-R0, L22-01185-R1
15 | APL-AX-SD-L23-00020-Rev 00 | GRC PANELS | Hotel Level 23 | 2.11 | 2.11 | 2.58 | 2.56 | 9.36 | 2.11 | 2.11 | 2.58 | 2.56 | 9.36 | L23-01186-R1, L23-01193-R0
16 | APL-AX-SD-L24-00021-Rev 02 | GRC PANELS | Hotel Level 24 |  |  | 4.57 | 3.22 | 7.79 |  |  | 4.57 | 3.22 | 7.79 | L24-01271
17 | APL-AX-SD-L25-00022-Rev 01 | GRC PANELS | Hotel Level 25 | 2.15 | 2.58 |  |  | 4.73 | 2.15 | 2.58 |  |  | 4.73 | L25-01187-R1
18 | APL-AX-SD-L26-00023-Rev 00 | GRC PANELS | Hotel Level 26 | 2.15 | 2.58 | 4.6 | 3.25 | 12.58 | 2.15 | 2.58 | 4.6 | 3.25 | 12.58 | L26-01188-R1, L26-01208-R0, L26-01221-R0
19 | APL-AX-SD-L26-00027-Rev 00 | GRC PANELS | Hotel Level 27 | 2.15 | 2.58 |  |  | 4.73 | 2.15 | 2.58 |  |  | 4.73 | L27-01189-R1
| SUB-TOTAL QUANTITY | [6 empty] | 146.51 |  |  |  |  | 146.51 | 0
| TOTAL QUANTITY | [6 empty] | 406.47 |  |  |  |  | 406.47 | 0
| UNIT RATE (AED PER M2) | [6 empty] | 691.2884 |  |  |  |  | 691.2884 | 0
| TOTAL AMOUNT (PREVIOUS SUB-CONTRACT - RPJV) | [6 empty] | 280988 |  |  |  |  | 280988 | 0
| LESS: PREVIOUS AMOUNT CERTIFIED BY OMNIYAT | [6 empty] | -170867 |  |  |  |  | -170867
| TOTAL AMOUNT (NEW SUB-CONTRACT - KCE) | [6 empty] | 110121 |  |  |  |  | 110121 |  | 100%

## SI 400 - Progress (hidden)
Project: | ROBERTS-PLOT 18
Subject: | SITE INSTRUCTION NO. 000400 - ADDITIONAL THERMAL INSULATION BEHIND FLUTTED GRC WALL CLADDING
INSTALLATION PROGRESS
Item No. | Description of Item | No. | Height | Width | Qty | Unit | Unit Rate | Total Amount (AED) | Qty | % | Total Amount (AED) | Remarks
1.1 | 50mm thk. Semi-Rigid Rockwool 60kg/m3 Fixed on Wall/Steel by Pin at Residential Podium Entrance - Ground Level
| Top Door Frame | 1 | 1.14 | 3.24 | 3.6936 | m2 | 49 | 181 | 3.6936 | 100% | 180.9864
| Side Door Frame | 2 | 6 | 1.4 | 16.8 | m2 | 49 | 823 | 16.8 | 100% | 823.2
1.2 | 50mm thk. Semi-Rigid Rockwool 60kg/m3 Fixed on Wall/Steel by Pin at Hotell Podium Entrance - Ground Level
| Fluted GRC Wall Cladding - Ground Level | 1 | 3.4 | 18 | 61.2 | m2 | 49 | 2999 | 61.2 | 100% | 2998.8
1.3 | 50mm thk. Semi-Rigid Rockwool 60kg/m3 Fixed on Wall/Steel by Pin at Hotel Podium Entrance - Level 2
| Fluted GRC Wall Cladding | 1 | 3.4 | 30 | 102 | m2 | 49 | 4998 | 102 | 100% | 4998
1.4 | 70mm thk. Semi-Rigid Rockwool 60kg/m3 with One Side Alum. Foil Fixed on Wall/steel by Pin at Hotel Level 29
at Gridline V', 16'-18'
| Fluted GRC Wall | 1 | 3.85 | 18.8 | 72.38 | m2 | 75 | 5429 | 72.38 | 100% | 5428.5
| Less Door Opening | -1 | 2.5 | 1.12 | -2.8 | m2 | 75 | -210 | -2.8 | 100% | -210
| Less Door Opening | -1 | 2.5 | 1.5 | -3.75 | m2 | 75 | -281 | -3.75 | 100% | -281.25
at Gridline V, 18'-22
| Fluted GRC Wall | 1 | 3.85 | 29.5 | 113.575 | m2 | 75 | 8518 | 113.575 | 100% | 8518.125
| Less Door Opening | -2 | 2.5 | 1.1 | -5.5 | m2 | 75 | -413 | -5.5 | 100% | -412.5
| Less Door Opening | -1 | 2.5 | 1.076 | -2.69 | m2 | 75 | -202 | -2.69 | 100% | -201.75
| Less Fire Hose Cabinet | -2 | 1.62 | 0.92 | -2.9808 | m2 | 75 | -224 | -2.9808 | 100% | -223.56
| at Gridline 22, V-X | 1
| Fluted GRC Wall | 1 | 3.85 | 11.52 | 44.352 | m2 | 75 | 3326 | 44.352 | 100% | 3326.4
| Less Door Opening | -1 | 2.5 | 1.1 | -2.75 | m2 | 75 | -206 | -2.75 | 100% | -206.25
2 | Preliminaries: (Engineering Works, QA/QC, Safety, Site Management, etc.) |  |  |  | 1 | LS | 3956 | 3956 | 1 | 100% | 3956
3 | Scaffolding | [6 empty] | excluded |  |  | excluded | by RPJV
| TOTAL (Excluding VAT) | [6 empty] | 28694 |  |  | 28694.7014
| TOTAL AMOUNT | [6 empty] | 28694 |  |  | 28694.7014
| TOTAL AMOUNT (PREVIOUS SUB-CONTRACT - RPJV) | [6 empty] | 28694 |  |  | 28694
| LESS: PREVIOUS AMOUNT CERTIFIED BY OMNIYAT | [6 empty] | -14347 |  |  | -14347
| TOTAL AMOUNT (NEW SUB-CONTRACT - KCE) | [6 empty] | 14347 |  |  | 14347 | 100%

## ERI-056
Project: | ROBERTS-PLOT 18
Subject: | ADDITIONAL GRC NOSING & GRC EDGE WALL CLADDING - REV. 01
PROGRESS
Item No. | Description of Item | No. | Girth | Length | Qty | Unit | Unit Rate | Total Amount (AED) | Qty | Total Amount (AED) | Remarks
1 | Supply and Installation of GRC Cladding complete wilth necessary fixing accessories:
1.1 | GRC Nosing at Residential/Apartment Levels 31st Level | 1 | 3.15 | 154.6 | 486.99 | m2 | 717 | 349172 | 371.064 | 266053 | BOQ Rate
1.1.1 | GRC Edge Wall Cladding | 1 | 1 | 40.2 | 40.2 | m2 | 717 | 28823 | 40.2 | 28823 | BOQ Rate
1.2 | Preliminaries: (Engineering Works, QA/QC, Safety, Site Management, etc.) |  |  |  | 1 | LS | 60441 | 60441 | 78.01% | 47151
1.3 | Structural Steel Support for fixing GRC Works (Epoxy paint finish without fire protection) | [9 empty] | by Structural Steel Sub-Contractor
1.4 | Scaffolding | [6 empty] | excluded |  |  | by RPJV
| TOTAL (Excluding VAT) | [6 empty] | 438436 | 78.01% | 342027
| LESS: PREVIOUS AMOUNT CERTIFIED BY OMNIYAT | [6 empty] | -141181
| TOTAL AMOUNT (NEW SUB-CONTRACT - KCE) | [6 empty] | 297255
Note on J9: Himal Kosala: WIR not approved, some balance work need to done

## VO
Project: Plot 18, Business Bay, Dubai, Project
Contractor: M/s. Khansaheb Civil Engineering LLC
Subject: VARIATION AND CLAIMS SCHEDULE
Ref No. | Brief Description of Change | Reason to Claim (Instruction / Notice) | [5 empty] | Date KHANSAHEB received acknowledgement receipt from GSL | Site Work Status | APL Statement | [10 empty] | KHANSAHEB Assessment and Certification (XXX 2022) |  | Diff in KHANSAHEB | Status | Remarks
|  | Instruction / Drawing / Letter | SI / Letter Ref. | Date | ERI Ref. | EI / VR | Date |  | Start / Finish | VO No. | APL Letter References | ACONEX Mail No. | KHANSAHEB Received Date | Time Impact | Engineering Works | Total Value | PRC Amendment Status | % Progress | Amount Claimed | Agreed (refer to the "Addendum") | KHANSAHEB Ref. No. | Amount |  |  |  | Remarks | Delivery Note No. | MIR Ref. | WIR Ref.
1 | Supply and Installtion of Thermal Insulation | E11/K117/SK/dm/056 |  | 2022-07-07 | [6 empty] | 22/180040/HH/L/24128R1/SEM/lr, dated 19th July 2022 | APCO-SUBCONLET-000316 | 2022-08-02 |  |  | 3628 | released | 100% | 3628 | [6 empty] | as per KCE letter ref. 201A22002/K117/Kd/qa/0132 dated 10th Oct 2022 this is agreed in principle by Employer, but final value remains to be agreed |  | APL-AX-MR-ML-00295, dated 2nd Aug 2022
| GRC Edge Profile Extension & Additional GRC Coping at Residential Level 32 | EK11/K117/SC/dm/080 |  | 2022-08-01 | [6 empty] | 22/180040/HH/L/24164/FS/jb, dated 9th Aug 2022 | APCO-SUBCONLET-000319 | 2022-08-10 |  |  | 129,082.00 | - |  | 0 | [6 empty] | SUPERSEDED by KCE letter ref. no. E11/K117/SK/dm/190
2 | Removal and Installation of GRC Panel for Drain Pipe Installation at Hotel Level 7 | EK11/K117/SC/dm/081 |  | 2022-08-01 | [6 empty] | 22/180040/HH/L/24168/FS/jb, dated 10th Aug 2022 | APCO-SUBCONLET-000320 | 2022-08-11 |  |  | 5562 | released | 100% | 5562 | [6 empty] | as per KCE letter ref. 201A22002/K117/Kd/qa/0132 dated 10th Oct 2022 this is agreed in principle by Employer, but final value remains to be agreed
3 | Removal and Installation of GRC Panels at the Retail Lobby Staircase, Hotel Level 2 | E11/K117/NA/dm/077 |  | 2022-07-27 | [6 empty] | 22/180040/HH/L/24171/FS/jb, dated 11th Aug 2022 | APCO-SUBCONLET-000321 | 2022-08-11 |  |  | 61851 | refer to remarks |  | 0 | [6 empty] | as per KCE letter ref. 201A22002/K117/Kd/qa/0132 dated 10th Oct 2022 this is agreed in principle by Employer, but final value remains to be agreed / On hold by KCE due to design change.
4 | New GRC Panels in Line with the Site Condition at Hotel Level 24 | E11/K117/SK/dm/089 |  | 2022-08-09 | [6 empty] | 22/180040/HH/L/24194/FS/jb, dated 17th Aug 2022 | APCO-SUBCONLET-000322 | 2022-08-18 |  |  | 4491 | released | 100% | 4491 | [6 empty] | as per KCE letter ref. 201A22002/K117/Kd/qa/0132 dated 10th Oct 2022 this is agreed in principle by Employer, but final value remains to be agreed |  |  | APL-AX-WR-L24-01249, dated 22nd Sep 2022
5 | Removal and Re-Installation of Fluted GRC Panel and Rockwool Insulation at Hotel Entrance Ground Floor & Level 2 | KCE letter ref. no. E11/K117/PK/dm/177 |  | 2022-09-10 | [6 empty] | 22/180040/HH/L/24354/FS/jb, dated 14th Sep 2022 | APCO-SUBCONLET-000329 | 2022-09-15 |  |  | 52196 | n.a. | 100% | 52196 | [6 empty] | WIR: APL-AX-WR-L2-01277, WIR: APL-AX-WR-L2-01278
6 | GRC Edge Profile Extension at Residential Level 32 - Rev. 02 | KCE letter ref. no. E11/K117/SK/dm/190 |  | 2022-09-13 | [6 empty] | 22/180040/HH/L/24366/FS/jb, dated 20th Sep 2022 | APCO-SUBCONLET-000330 | 2022-09-21 |  |  | 82509 | released | 90% | 74258.1
7 | Removal of Existing GRC Coping Panels Installed Above the Roof Parapet at Hotel Level 29 | KCE letter ref. no. E11/K117/JA/dm/218 |  | 2022-09-20 | [6 empty] | 22/180440/HH/L/24395/FS/jb, dated 28th Sep 2022 | APCO-SUBCONLET-000333 | 2022-09-30 |  |  | 16239 | n.a. | 100% | 16239 | [6 empty] | WIR: APL-AX-WA-L29-01262
8 | Omission of Fluted GRC Panels due to the Revised Cladding at Hotel Podium Entrance Level 2 | KCE letter ref. no. E11/K117/SN/dm/233 |  | 2022-09-23 | [6 empty] | 22/180440/HH/L/24396/FS/jb, dated 28th Sep 2022 | APCO-SUBCONLET-000336 | 2022-09-30 |  |  | -12124 | n.a. | 100% | -12124
9 | GRC Façade Cleaning | KCE letter ref. no. E11/K117/SK/dm/247 |  | 2022-09-26 | [6 empty] | 22/180440/HH/L/24398/FS/jb, dated 29th Sep 2022 | APCO-SUBCONLET-000335 | 2022-09-30 |  |  | 59560 | n.a. |  | 0
| GRC Flat Panel for Non-Accessible Balcony Areas at Hotel and Residential Towers | KCE letter ref. no. E11/K117/SC/dm/325 |  | 2022-10-17 | [6 empty] | 22/180440/HH/L/24400/FS/jb, dated 30th Sep 2022 | APCO-SUBCONLET-000337 | 2022-09-30 |  |  | 81,254.00 | released | [8 empty] | SUPERSEDED by KCE letter ref. no. E11/K117/SC/dm/398-R1 dated 2nd Nov 2022
10 | New GRC Top Panels at Hotel Level 8 | KCE letter ref. no. E11/K117/JA/dm/253 |  | 2022-09-27 | [6 empty] | 22/180440/HH/L/24420/FS/jb, dated 10th Oct 2022 | APCO-SUBCONLET-000338 | 2022-10-11 |  |  | 4528 | released
11 | Removal and Installation of GRC Balcony separator Panels for Balcony Floor Drain Installation at Hotel Levels 10, 13, 15, 20, & 25 | KCE letter ref. no. E11/K117/KK/dm/278 |  | 2022-10-03 | [6 empty] | 22/180440/HH/L/24421/FS/jb, dated 10th Oct 2022 | APCO-SUBCONLET-000339 | 2022-10-11 |  |  | 21911 | released | 100% | 21911 | [6 empty] | WIR: APL-AX-WR-ML-01263; WIR: APL-AX-WR-ML-01273
| Removal and Installation of GRC Panel at Sky Deck, Hotel Level 29 | KCE letter ref. no. E11/K117/JA/dm/218-R1 |  | 2022-10-01 | [6 empty] | 22/180440/HH/L/24432/FS/jb, dated 12th Oct 2022 | APCO-SUBCONLET-000340 | 2022-10-12 |  |  | 3,430.00 | - | [8 empty] | SUPERSEDED by KCE email dated 18th Oct 2022
12 | Removal GRC Panel at Sky Deck, Hotel Level 29 - Rev. 01 | KCE letter ref. no. E11/K117/JA/dm/218-R1 KCE e-mail dated 18th Oct 2022 |  | 2022-10-06 | [6 empty] | 22/180440/HH/L/24559/FS/jb, dated 25th Oct 2022 | APCO-SUBCONLET-000347 | 2022-10-26 |  |  | 3201 | n.a. | 100% | 3201 | [6 empty] | WIR: APL-AX-WR-L29-01267
| Removal of GRC Panels for Drain Pipe Installation at Residential Tower Level 14 | KCE letter ref. E11/K117/MS/dm/275 |  | 2022-10-28 | [6 empty] | 22/180440/HH/L/24564/FS/jb, dated 25th Oct 2022 | APCO-SUBCONLET-000344 | 2022-10-26 |  |  | 3,201.00 | - |  | 0 | [6 empty] | SUPERSEDED by KCE letter ref. E11/K117/MS/dm/275-R1, dated 28th Oct 2022
13 | Removal and Reinstate of GRC Balcony Separator Panels for Drain Pipe Installation at Residential Tower Level 14 | KCE letter ref. E11/K117/MS/dm/275-R1 |  | 2022-10-28 | [6 empty] | 22/180440/HH/L/24582/FS/jb, dated 7th Nov 2022 | APCO-SUBCONLET-000357 | 2022-11-08 |  |  | 4781 | released | 100% | 4781 | [6 empty] | DN. No. AJM003057; MIR-320 WIR: APL-AX-WR-L14-01264 WIR: APL-AX-WR-L14-01270
14 | New GRC Panels at Residential Tower Level 25, 26 and 29 | KCE letter ref. E11/K117/KD/dm/312-R1 |  | 2022-10-14 | [6 empty] | 22/180440/HH/L/24573/FS/jb, dated 1st Nov 2022 | APCO-SUBCONLET-000351 | 2022-11-01 |  |  | TBA | released
15 | GRC Finished Floor Panel as per RFI No. KCE-AX-RFI-L17-00228 at Hotel Level 17 | KCE e-mail dated 19th Oct 2022; KCE letter ref. E11/K117/AK/dm/364 |  | 2022-10-24 | [6 empty] | 22/180440/HH/L/24565/FS/jb, dated 25th Oct 2022 | APCO-SUBCONLET-000346 | 2022-10-26 |  |  | 58553 | released | 7.084% | 4148 | [6 empty] | WIR: APL-AX-WR-L17-01282
16 | GRC Coping to the Entire Areas Where the GRC Coping Removed for the 400mm Cutting to the Parapet Wall | KCE letter ref. E11/K117/JA/dm/362 |  | 2022-10-24 | [6 empty] | 22/180440/HH/L/24578/FS/jb, dated 2nd Nov 2022 | APCO-SUBCONLET-000352 | 2022-11-03 |  |  | 44886 | released | 100% | 44886 | [6 empty] | WIR: APL-AX-WR-L29-01284 'WIR: APL-AX-WR-L29-01288
17 | Supply & Installation of Additional Insulation Behind GRC Window Frame Cladding as per RFI No. KCE-AX-RFI-PW-00244 Rev. 0 | KCE letter ref. E11/K117/SC/dm/323 |  | 2022-10-26 | [6 empty] | 22/180440/HH/L/24566/FS/jb, dated 26th Oct 2022 | APCO-SUBCONLET-000343 | 2022-10-26 |  |  | 7404 | released |  | 0
18 | GRC Works at Slab Extension Area at Residential Level 18 as per RFI ref. KCE-AX-RFI-L18-00226 Rev. 0 | KCE letter ref. E11/K117/SC/dm/374 |  | 2022-10-26 | [6 empty] | 22/180440/HH/L/24579/FS/jb, dated 2nd November 2022 | APCO-SUBCONLET-000354 | 2022-11-03 |  |  | 27858 | released |  | 0
| Removal of 2 Bottom GRC Panels in Residence Level 6 for Mast Climber Installation | KCE letter ref. E11/K117/JJ/dm/375 |  | 2022-10-26 | [6 empty] | 22/180440/HH/L/24581/FS/jb, dated 3rd November 2022 | APCO-SUBCONLET-000353 | 2022-11-03 |  |  | 1,200.00 | - |  | 0 | [6 empty] | superseded by APL L-24605 dated 9th Nov 2022
19 | Removal & Reinstate 2 Bottom GRC Panels in Residence Level 6 for Mast Climber Installation | KCE letter ref. E11/K117/JJ/dm/375 |  | 2022-10-26 | [6 empty] | 22/180440/HH/L/24605/FS/jb, dated 9th November 2022 | APCO-SUBCONLET-000353 | 2022-11-03 |  |  | 3796 | released | 50% | 1898 | [6 empty] | Removed All panels 100% And waiting for Mast Climber to remove so that APL can reinstall (WIR : APL-AX-WR-L6-01265)
20 | GRC Finished Floor Panels at Non-Accessible Balcony Areas | KCE letter ref. E11/K117/SC/dm/398-R1 |  | 2022-11-02 | [6 empty] | 22/180440/HH/L/24585/FS/jb, dated 7th November 2022 | APCO-SUBCONLET-000355 | 2022-11-07 |  |  | 143567 | released | 30.65% | 43998
21 | Removal & Re-Installation of 3 nos. GRC Panels at Residence Tower Level 2 | KCE letter ref. no. E11/K117/JJ/dm/399 |  | 2022-11-01 | [6 empty] | 22/180440/HH/L/24586/FS/jb, dated 7th November 2022 | APCO-SUBCONLET-000356 | 2022-11-08 |  |  | 6002 | n.a. | 50% | 3001 | [6 empty] | Removed All panels 100% And waiting for Mast Climber to remove so that APL can reinstall (WIR : APL-AX-WR-L2-01266)
22 | GRC Finished Floor Panels at Residential Level 4 | KCE letter ref. no. E11/K117/SC/dm/271 |  | 2022-10-01 | [6 empty] | 22/180440/HH/L/24639/FS/jb, dated 25th November 2022 | APCO-SUBCONLET-000359 | 2022-11-25 |  |  | 6844 | released |  | 0
22 | GRC Finished Floor Panels at Non-Accessible Balcony Area at Residential level 10 | KCE letter ref. no. E11/K117/AK/dm/426 |  | 2022-11-11 | [6 empty] | 22/180440/HH/L/24640/FS/jb, dated 25th November 2022 | APCO-SUBCONLET-000360 | 2022-11-25 |  |  | 35256 | released |  | 0
23 | Removal of GRC Nosing Panel and Bottom Panel (8 nos.) to proceed with Mast Climber Installation Works at Hotel Tower Level 7 | KCE letter ref. no. E11/K117/JA/dm/496 |  | 2022-12-06 | [6 empty] | 22/180440/HH/L/24762/FS/jb, dated 12th December 2022 | APCO-SUBCONLET-000363 | 2022-12-12 |  |  | 3201 | n.a. | 100% | 3201 | [6 empty] | Removed All panels 100% And waiting for Mast Climber to remove so that APL can reinstall (WIR : APL-AX-WR-L7-01269)
24 | GRC Fluted Profile Level 3.9m LVL and Flat Panel to Varies Level as per RFI Ref. KCE-AX-RF-GF-00293 Rev 0 | KCE letter ref. no. E11/K117/KD/sr/520 R1 |  | 2022-12-27 | [11 empty] | TBA | released
25 | Replacement of GRC Panel in Line with Balustrade Alignment at Retail Stair Hotel Tower Level 2 | KCE letter ref. no. E11/K117/KD/sr/531 |  | 2022-12-15 | [6 empty] | 22/180440/HH/L/24640/FS/jb, dated 25th November 2022 | APCO-SUBCONLET-000365 | 2022-12-21 |  |  | 3315 | released |  | 0
25 | Removal of GRC Panels at Hotel Level 29 | KCE letter ref. no, E11/K/117/SK/SR/571 |  | 2022-12-27 | [6 empty] | 23/180440/HH/L/24824/FS/jb, dated 4th January 2023 | APCO-SUBCONLET-000367 | 2023-01-04 |  |  | 2801 | n.a. |  | 0
26 | Supply and Installation of New GRC Edge Profile at Hotel Tower Level 29 | KCE letter ref. no, E11/K/117/SK/SR/573 |  | 2022-12-28 | [6 empty] | 23/180440/HH/L/24825/FS/jb, dated 4th January 2023 | APCO-SUBCONLET-000368 | 2023-01-04 |  |  | 4974 | released |  | 0
27 | Removal, Supply and Installation of New GRC Nosing Panels at Residential Tower Level 32 | KCE letter ref. no, E11/K/117/SK/SR/733 |  | 2022-02-10 | [6 empty] | 23/180440/HH/L/24825/FS/jb, dated 20th February 2023 | APCO-SUBCONLET-000 | 2023-02-20 |  |  | 2965 | released | 90% | 2668.5
28 | Cutting and Fixing the GRC Coping Panels at Hotel Tower Level 29 | KCE letter ref. no. E11/K117/TP/dm/816, |  | 2023-03-17 | [6 empty] | 23/180440/HH/L/25131/FS/jb, dated 17th March 2023 |  |  |  |  | 1200 |  | 90% | 1080
28 | Supply and Installation of New GRC Panels at Sky Deck, Hotel Level 29 | [9 empty] | 23/180440/HH/L/24993/FS/jb, dated 8th February 2023 | APCO-SUBCONLET-000373 | 2023-02-09 |  |  | 3077 |  | 90% | 2769.3
| SUB - TOTAL | [12 empty] | #REF! | #REF! | 664032 |  |  | 253613.61 | 0 |  | 0 | 0
Note on P6: (site management team supervision, temporary works, protection works)
Note on Q6: (design and coordination, calculations, 3D model, shop dwg, fabrication dwg.)
Note on T13: Himal Kosala: No WIR
Note on R31: Himal Kosala: Variation amount change why? Previous amount 142,226.00
Note on T40: Himal Kosala: No Supporting
Note on U44: Himal Kosala: 90% untiil Variation approval

## SI-000079 (hidden)
Project: | PLOT 18
Subject: | SI-000079 (APCP-CAV-000076)
ADDITIONAL SUPPORT BRACKET FOR THE GRC EDGE PROFILE
Progress
Item No. | Description of Item | Unit | Qty | Rate (AED) | Amount | Qty | Amount
A | SUPPLY & INSTALL ADDITIOANAL MS Brackets
1 | CWM-01
1.1 | Hotel-Level 8, 9, 10, 11, 13, 14, 15, 16, 18, 19, 20, 21, 22, 23, 25, 26, 27 | NOS | 170 | 392 |  | 170
1.2 | Residence- Level 5, 7, 8, 9, 11, 12, 13, 14, 15, 16, 17, 19, 20, 21, 22, 26, 27, 28 | NOS | 252 | 392 |  | 252
2 | CWE-01
2.1 | Hotel-Level 8, 9, 10, 11, 13, 14, 15, 16, 18, 19, 20, 21, 22, 23, 25, 26, 27 | NOS | 51 | 392 |  | 51
2.2 | Residence- Level 5, 7, 8, 9, 11, 12, 13, 14, 15, 16, 17, 19, 20, 21, 22, 26, 27, 28 | NOS | 0 | 392
3 | Engineering Works | LS |  |  |  | 1
4 | Preliminaries | LS |  |  |  | 1
| TOTAL COST OF BRACKET (Excluding VAT) |  | 473 |  | 185000 | 100% | 185000
Notes:

## SI-000110 (hidden)
Project: | PLOT 18
Subject: | SI-000110 (APCP-CAV-000075)
Redesign of 128 nos. Brackets as per the as-built condition at Residential Level 7 & 8 and Hotel Level 8
BILL OF QUANTITY | [5 empty] | Progress
Item No. | Description of Item | Unit | Qty | Rate (AED) | Amount | % | Amount | Remarks
A | Redesign of Brackets
1 | Removal of All Installed Brackets | ls | 1 | 4500 |  | 100%
2 | Scaffolding rent during stopped work from 30th Sep to 25th October | ls | 1 | 59000 |  | 100%
3 | Abortive Materials - M12 Fischer anchor bolts & screws | nos | 80 | 8 |  | 100%
4 | Modification of affected Bracket | nos | 128 | 139.5 |  | 100%
5 | Re-Engineering | Ls | 1 | 14230 |  | 100%
6 | Transportation Cost | LS | 1 | 5000 |  | 100%
7 | OH & Profit 6% (As per SC, Clause13.2) | LS |  |  |  | 100%
| TOTAL COST FOR THE REDESIGN OF BRACKET Rev.1 |  |  |  | 60000 | 100% | 60000

## SI-000130 (hidden)
Project: | ROBERTS-PLOT 18
Subject: | SITE INSTRUCTION NO. 000130
ADDITIONAL GRC PANEL AT RESIDENTIAl & HOTEL TOWER
Progress
Item No. | Description of Item | Unit | Qty | Unit Rate | Total Amount (AED) | % | Amount | Previous % | This %
1 | Supply and Installation of GRC Cladding:
1.1 | Residential Tower - GRC panel
| Residential Level 7 | m2 | 14.92 | 598 | 8922.16 | 100% | 8922.16 | 36% | 64%
| Residential Level 8 | m2 | 19.07 | 598 | 11403.86 | 100% | 11403.86 | 50% | 50%
| Residential Level 9 | m2 | 14.92 | 598 | 8922.16 | 100% | 8922.16 | 36% | 64%
| Residential Level 11 | m2 | 12.03 | 598 | 7193.94 | 100% | 7193.94 | 16% | 84%
| Residential Level 12 | m2 | 16.88 | 598 | 10094.24 | 100% | 10094.24 | 43% | 57%
| Residential Level 13 | m2 | 13.25 | 598 | 7923.5 | 100% | 7923.5 | 28% | 72%
| Residential Level 14 | m2 | 13.25 | 598 | 7923.5 | 100% | 7923.5 | 56% | 44%
| Residential Level 15 | m2 | 13.25 | 598 | 7923.5 | 100% | 7923.5 | 28% | 72%
| Residential Level 16 | m2 | 16.98 | 598 | 10154.04 | 100% | 10154.04 | 44% | 56%
| Residential Level 17 | m2 | 13.25 | 598 | 7923.5 | 100% | 7923.5 | 28% | 72%
| Residential Level 18 | m2 | 9.17 | 598 | 5483.66 | 43% | 2357.9738 | 43% | 0%
| Residential Level 19 | m2 | 9.52 | 598 | 5692.96 |  | 0 |  | 0%
| Residential Level 20 | m2 | 18.71 | 598 | 11188.58 |  | 0 |  | 0%
| Residential Level 21 | m2 | 9.52 | 598 | 5692.96 |  | 0 |  | 0%
| Residential Level 22 | m2 | 18.71 | 598 | 11188.58 |  | 0 |  | 0%
| Residential Level 23 | m2 | 9.53 | 598 | 5698.94 |  | 0 |  | 0%
| Residential Level 26 | m2 | 12.4 | 598 | 7415.2 |  | 0 |  | 0%
| Residential Level 27 | m2 | 13.92 | 598 | 8324.16 |  | 0 |  | 0%
| Residential Level 28 | m2 | 9.52 | 598 | 5692.96 |  | 0 |  | 0%
| Residential Level 29 | m2 | 1.16 | 598 | 693.68 | 100% | 693.68 |  | 100%
1.2 | Hotel Tower - GRC panel
| Hotel Level 8 | m2 | 4.26 | 598 | 2547.48 |  | 0 |  | 0%
| Hotel Level 9 | m2 | 4.68 | 598 | 2798.64 |  | 0 |  | 0%
| Hotel Level 10 | m2 | 4.68 | 598 | 2798.64 |  | 0 |  | 0%
| Hotel Level 11 | m2 | 4.26 | 598 | 2547.48 |  | 0 |  | 0%
| Hotel Level 12 | m2 | 7.44 | 598 | 4449.12 |  | 0 |  | 0%
| Hotel Level 13 | m2 | 12.17 | 598 | 7277.66 | 52% | 3784.3832 | 0% | 52%
| Hotel Level 14 | m2 | 4.73 | 598 | 2828.54 | 100% | 2828.54 |  | 100%
| Hotel Level 15 | m2 | 12.17 | 598 | 7277.66 | 39% | 2838.2874 | 28% | 11%
| Hotel Level 16 | m2 | 4.73 | 598 | 2828.54 | 100% | 2828.54 |  | 100%
| Hotel Level 18 | m2 | 9.84 | 598 | 5884.32 | 80% | 4707.456 | 26% | 54%
| Hotel Level 19 | m2 | 9.36 | 598 | 5597.28 | 86% | 4813.6608 | 41% | 45%
| Hotel Level 20 | m2 | 9.82 | 598 | 5872.36 | 100% | 5872.36 | 52% | 48%
| Hotel Level 21 | m2 | 9.36 | 598 | 5597.28 | 100% | 5597.28 | 55% | 45%
| Hotel Level 22 | m2 | 9.82 | 598 | 5872.36 | 100% | 5872.36 | 52% | 48%
| Hotel Level 23 | m2 | 9.36 | 598 | 5597.28 | 100% | 5597.28 | 55% | 45%
| Hotel Level 24 | m2 | 7.79 | 598 | 4658.42 |  | 0 |  | 0%
| Hotel Level 25 | m2 | 4.73 | 598 | 2828.54 |  | 0 |  | 0%
| Hotel Level 26 | m2 | 12.58 | 598 | 7522.84 |  | 0 |  | 0%
| Hotel Level 27 | m2 | 4.73 | 598 | 2828.54 |  | 0 |  | 0%
1.3 | Preliminaries: Engineering Works, QA/QC & Safety, Site Management, etc.) | LS |  |  | 37918.7734 |  | 21243.4874
| TOTAL (Excluding VAT) |  |  |  | 280987.8334 | 56.02% | 157420

## SI-000296 (hidden)
Project: | ROBERTS-PLOT 18
Subject: | SITE INSTRUCTION NO. 000296- ADDITIONAL GRC PANELS AT RESIDENTIAL TOWER REV. 01 AS PER RFI
(REF. APL-AX-RFI-RT-003817) CONFIRMATION FROM THE EMPLOYER
Progress
Item No. | Description of Item | Unit | Qty | Unit Rate | Total Amount (AED) | % | Amount | Remarks
1 | Supply and Installation of GRC Cladding:
1.1 | Residential Tower - GRC Belly Panel | m2 | 539.26 | 598 | 322477 | 100% | 322477 | progress: 118.5 m2 (3no x 21.35m x 1.85m)
1.2 | Structural Steel Support | LS | 1 | 45759.4863 | 45759 | 100% | 45759
1.3 | Preliminaries: | LS | 1 | 51564.0723 | 51564 | 100% | 51564
| TOTAL (Excluding VAT) |  |  |  | 419800 | 100% | 419800

## SI-000365 (hidden)
Project: | ROBERTS-PLOT 18
Subject: | SITE INSTRUCTION NO. 000365 - GRP CLADDING AT POOL VIEW DECK & GRC FACIA AT SKY DECK, HOTEL LEVEL 29
Progress
Item No. | Description of Item | No. | Length | Width/ Girth | Qty | Unit | Unit Rate | Total Amount (AED) | % | Amount | Remarks
Supply and Installation of GPR Facia, Wall & Ceiling Cladding complete wilth necessary fixing accessories:
LEVEL 29 HOTEL VIEW DECK
1.1 | GRP Bullnose Cladding 26mm thk, 630mm Girth. as per drawing ref. nos. LA-GA-L29-0220F & LA-GA-L29-0224A, (Annexure 6) | 1 | 14.4 | 0.63 | 14.4 | lm | 1217 | 17525 | 100% | 17525
1.2 | GRP Wall & Ceiling Cladding 26mm thk. as per drawing ref. nos. LA-GA-L29-0220F & LA-GA-L29-0224A, (Annexure 6) | 1 | 5.7 | 4.8 | 27.36 | m2 | 1595 | 43639
LEVEL 29 HOTEL SKY DECK
2.1 | GRC Facia Cladding (530mm Girth) | 1 | 14.4 | 0.53 | 7.632 | m2 | 717 | 5472 |  |  | BOQ rate
3 | Structural Steel Support for Fixing GRP/GRC Works (Epoxy paint finish without fire protection) |  |  |  | 1 | LS | 776 | 9456 |  | 2487
4 | Preliminaries: (Engineering Works, QA/QC, Safety, Site Management, etc.) |  |  |  | 1 | LS | 9780 | 10655 |  | 2802
5 | Scaffolding | [6 empty] | excluded |  |  | by RPJV
| TOTAL (Excluding VAT) | [6 empty] | 86747 |  | 22814

## KCE-SI-278
Project: | PLOT 18
Subject: | REMOVAL & INSTALLATION OF GRC BALCONY SEPARATOR PANELS AT HOTEL LEVELS 10, 13, 15, 20 and 25
PROGRESS
Item No. | Description of Item | No. | Girth | Length | Qty | Unit | Unit Rate | Total Amount (AED) | Qty | Total Amount (AED) | Remarks
1 | Removal of GRC Balcony Separator Panel for Balcony Floor Drain Installation (8 workers, 5 days) |  |  |  | 1 | LS | 6900 | 6900 | 1 | 6900
2 | Supply and Installation of New GRC Balcony Separator
2.1 | H10-DV-02D & 02E |  |  |  | 0.5 | no. | 4795 | 2398 | 0.5 | 2398 | refer to BOQ rate from previous Contractor
2.2 | H13-DV-02D & 02E |  |  |  | 0.5 | no. | 4795 | 2398 | 0.5 | 2398
2.3 | H15-DV-02D & 02E |  |  |  | 0.5 | no. | 4795 | 2398 | 0.5 | 2398
2.4 | H20-DV-02D & 02E |  |  |  | 0.5 | no. | 4795 | 2398 | 0.5 | 2398
2.5 | H24-DV-02D & 02E |  |  |  | 0.5 | no. | 4795 | 2398 | 0.5 | 2398
2.2 | Preliminaries: (Engineering Works, QA/QC, Safety, Site Management, etc.) |  |  |  | 1 | LS | 3021 | 3021 | 1 | 3021
| TOTAL (Excluding VAT) | [6 empty] | 21911 | 100% | 21911

## KCE-SI-364
Project: | PLOT 18 - DORCHESTER HOTEL & RESIDENCES
Subject: | GRC FINISHED FLOOR PANELS AT HOTEL LEVEL 17
PROGRESS
Item No. | Description of Item | Unit | Qty | Unit Rate | Total Amount (AED) | Qty | Total Amount (AED) | Remarks
1 | Supply and Installation of GRC Finished Floor Panels
1.1 | Hotel Tower | m2 | 84.7 | 598 | 50651 | 6 | 3588
| Hotel Level 17 - Grid 20-21/S |  | 6
| Hotel Level 17 - Grid 17-23/W-X |  | 78.7
2 | Preliminaries: (Engineering, Coordination, QA/QC, Safety, Site Management, etc.) | LS | 1 | 7901.556 | 7902 |  | 560
| Scaffolding / Access |  |  |  | excluded |  |  | by KCE
| Structural steel support for fixing GRC Works (Epoxy paint finish without fire protection), if any |  |  |  | excluded
| TOTAL (Excluding VAT) |  |  |  | 58553 | 7.084% | 4148

## MOS
| Project : PLOT 18, BUSINESS BAY, DUBAI, PROJECT | [8 empty] | #REF!
| Contractor : ROBERTS-PIZZAROTTI JV | [8 empty] | #REF! | #REF!
Sub-Contractor : ARABIAN PROFILE COMPANY LIMITED
Materials On Site
Item no. | Description | BOQ Ref | MIR No | Delivery Note. No | Unit | Materials Status |  |  | Quantity Used | Balanced Quantity | Approx: Rate (Supply of Materials) | Amount (Dhs) | Remarks | Approx. BOQ Qty (Residential) | Approx. BOQ Qty (Hotel) | Approx. BOQ Qty | % Delivered | MOS | BOQ Rate | Amount
[6 empty] | Previous | This month | To-date
SUMMARY:
1 | GRC Panel (800 mm wide GRC Edge profile Type EWS-101) - 2nd and 3rd Levels & Apartment 4th and Hotel 4th Levels | A&C |  |  | lm | 22.6 | 0 | 22.6 | 22.198 | 0 | 1904 | 0 |  |  |  | 155.84 | 14.5% | 23 | 2380 | 0
2 | GRC Panel (600 mm wide GRC Edge profile Type EWS-101) - Apartment 6th and Hotel 7th Levels | E |  |  | lm | 0 | 0 | 0 | 0 | 0 | 2136 | 0 |  |  |  | 26.94 | 0% | 0 | 2670 | 0
3 | GRC Panel (600 mm wide GRC Edge profile Type EWS-101) - Apartment 7th to 31st Levels & Hotel Level 8th to 29th | G&L |  |  | lm | 126.5667 | 0 | 126.5667 | 144.157 | -18 | 764 | -13752 |  | 286.486 | 234.5 | 520.986 | 24.29% | 127 | 955 | -17190
4 | GRC Panel (900 mm wide GRC Edge profile Type EWS-101) - Apartment 7th to 31st Levels & Hotel Level 7th to 29th | J&N |  |  | lm | 0 | 0 | 0 | 0 | 0 | 1084 | 0 |  | 17.96 | 0 | 17.96 | 0% | 0 | 1355 | 0
5 | Balcony Separator Type EWS-105 (Apartment Level 6 to 31) | C |  |  | no. | 0 | 0 | 0 | 0 | 0 | 4386.4 | 0 |  |  |  | 4 | 0% | 0 | 5483 | 0
6 | Balcony Separator Type EWS-105 (Hotel Level 7th to 29th) | D |  |  | no. | 7 | 0 | 7 | 7 | 0 | 3836 | 0 |  |  |  | 18 | 38.89% | 7 | 4795 | 0
| TOTAL | [7 empty] | Total Value of Material |  |  | -13752 |  | 304.446 | 234.5 | 721.726 |  | 150 |  | -17190
[10 empty] | MOS Applied for Certification |  | 75% |  |  |  | 22 |  | 7
[10 empty] | Total Invoice Value for Material |  | -10314 | [7 empty] | 60%

## KCE-SI-398 R1
Project: | PLOT 18 - DORCHESTER HOTEL & RESIDENCES
Subject: | S.I. 398 R1 - GRC FINISHED FLOOR PANEL IN NON-ACCESSIBLE AREAS
PROGRESS
Item No. | Description of Item | Unit | Qty | Unit Rate | Total Amount (AED) | Qty | Total Amount (AED) | Remarks
1 | Supply and Installation of GRC Finished Flat Floor Panels
1.1 | Hotel Tower | m2 | 156.66 | 598 | 93683
| Hotel Level 8 |  | 9.15
| Hotel Level 11 |  | 9.3
| Hotel Level 12 |  | 38.5
| Hotel Level 14 |  | 8.65
| Hotel Level 16 |  | 8.65
| Hotel Level 19 |  | 9.12 |  |  | 9.12 | 5454
| Hotel Level 21 |  | 9.12 |  |  | 9.12 | 5454
| Hotel Level 23 |  | 9.12 |  |  | 9.12 | 5454
| Hotel Level 24 |  | 37.75
| Hotel Level 25 |  | 8.65 |  |  | 8.65 | 5173 | D.N. AJM003238
| Hotel Level 27 |  | 8.65 |  |  | 8.65 | 5173 | D.N. AJM003238
1.2 | Residential Tower | m2 | 51.02 | 598 | 30510
| Residential Level 11 |  | 4.74
| Residential Level 18 |  | 40.4
| Residential Level 27 |  | 1.97
| Residential Level 24 |  |  |  |  | 9.52 | 5693
| Residential Level 25 |  |  |  |  | 9.52 | 5693
| Residential Level 28 |  | 1.97
| Residential Level 29 |  | 1.94 |  |  | 9.52 | 5693
1.3 | Preliminaries: (Engineering, Coordination, QA/QC, Safety, Site Management, etc.) | LS | 1 | 19374.108 | 19374 | 35.26% | 211
| Scaffolding / Access |  |  |  | excluded |  |  | by KCE
| Structural steel support for fixing GRC Works (Epoxy paint finish without fire protection), if any |  |  |  | excluded
| TOTAL (Excluding VAT) |  |  |  | 143567 | 30.65% | 43998
Note:

## SI-364
Project: | ROBERTS-PLOT 18
Subject: | SITE INSTRUCTION NO. 000364 - ADDITIONAL FLUTED GRC WALL CLADDING AT HOTEL LEVEL 29 - Rev. 01
PROGRESS
Item No. | Description of Item | No. | Height | Width | Qty | Unit | Unit Rate | Total Amount (AED) | Qty | Total Amount (AED) | Remarks
1 | Supply and Installation of Fluted GRC Wall Cladding (Rough Finish) at Hotel Level 29, complete wilth necessary fixing accessories:
at Gridline V', 16'-18'
| Fluted GRC Wall | 1 | 3.85 | 18.8 | 72.38 | m2 | 1716 | 124204 | 46.2 | 79279
| Less Door Opening | -1 | 2.5 | 1.6 | -4 | m2 | 1716 | -6864
| GRC Cladding Return at Door Opening | 1 | 0.25 | 6.6 | 1.65 | m2 | 1716 | 2831
at Gridline V, 18'-22
| Fluted GRC Wall | 1 | 3.85 | 29.5 | 113.575 | m2 | 1716 | 194895
| Less Door Opening | -2 | 2.5 | 1 | -5 | m2 | 1716 | -8580
| Less Door Opening | -1 | 2.5 | 2.6 | -6.5 | m2 | 1716 | -11154
| Less Fire Hose Cabinet | -2 | 1.5 | 0.8 | -2.4 | m2 | 1716 | -4118
| GRC Cladding Return at Door Opening | 1 | 0.25 | 19.6 | 4.9 | m2 | 1716 | 8408
| at Gridline 22, V-X | 1
| Fluted GRC Wall | 1 | 3.85 | 11.52 | 44.352 | m2 | 1716 | 76108 | 44.352 | 76108
| Less Door Opening | -1 | 2.5 | 0.45 | -1.125 | m2 | 1716 | -1931 | -1.125 | -1931
| Return Door Opening | 1 | 0.25 | 5.45 | 1.3625 | m2 | 1716 | 2338 | 1.3625 | 2338
1.2 | Structural Steel Support for Fixing GRC Works (Epoxy paint finish without fire protection) |  |  |  | 1 | LS | 53374 | 53374 | 41.42% | 22107
1.3 | Preliminaries: (Engineering Works, QA/QC, Safety, Site Management, etc.) |  |  |  | 1 | LS | 60144 | 60144 | 41.42% | 24911
1.4 | Scaffolding | [6 empty] | excluded |  |  | by RPJV
| TOTAL (Excluding VAT) | [6 empty] | 489655 | 41.42% | 202812
| LESS: PREVIOUS AMOUNT CERTIFIED BY OMNIYAT | [6 empty] | -25846
| TOTAL AMOUNT (NEW SUB-CONTRACT - KCE) | [6 empty] | 463809 | 41.42% | 192107