## SUMMARY
DORCHESTER HOTEL & RESIDENCIES
WATERPROOFING & GUNITNG WORKS - IKK | [8 empty] | 2022-11-01
SUMMARY | [8 empty] | KCE PC 10
| ITEM NO | DESCRIPTION | CONTRACT AMOUNT | WORK DONE UNDER RPJV | REMAINING WORK | PREVIOUS | THIS MONTH | CUMULATIVE
[8 empty] | % | AMOUNT
| 01 | Guniting | 1827639 | 1035776.39 | 793557 | 223339.8368 | 0 | 28.14% | 223339.8368
| 02 | Waterproofing | 687282.9584 | 324907.6571 | 362375.3013 | 208379.0788 | 0 | 57.5% | 208379.0788
|  | Variations |  |  |  | 0 | 127563.52 |  | 127563.52
|  |  | 2514921.9584 | 1360684.0471 | 1155932.3013 | 431718.9156 | 127563.52 | 48.38% | 559282.4356

## Guniting
DORCHESTER HOTEL & RESIDENCIES
WATERPROOFING WORK - IKK
SUMMARY
ITEM NO | DESCRIPTION | CONTRACT AMOUNT | WORK DONE UNDER RPJV | REMAINING WORK | PREVIOUS | THIS MONTH | CUMULATIVE
[7 empty] | % | AMOUNT
| Guniting Work Done | 1827639 | 1035776.39 | 793557 | 254679.8368 | 0 |  | 254679.8368
| Gunite Material Recovery |  |  |  | -31340 | 0 |  | -31340
| SUB-TOTAL | 1827639 | 1023477.4205 | 804161.5795 | 223339.8368 | 0 | 0 | 223339.8368

## WP
DORCHESTER HOTEL & RESIDENCIES
WATERPROOFING WORK - IKK | [7 empty] | 2022-11-01
SUMMARY | [7 empty] | KCE PC 10
ITEM NO | DESCRIPTION | CONTRACT AMOUNT | WORK DONE UNDER RPJV | REMAINING WORK | PREVIOUS | THIS MONTH | CUMULATIVE
[7 empty] | % | AMOUNT
1 | Waterproofing to Planters | 383018.6684 | 112650.8506 | 270367.8178 | 169818.0753 | 0 | 62.81% | 169818.0753
2 | Waterproofing to Hardscape | 0 | 0 | 0 | 0 | 0 |  | 0
3 | Waterproofing to Water Features | 66084.33 | 62028.2065 | 4056.1235 | 4056.1235 | 0 | 100% | 4056.1235
4 | Waterproofing to Swimming Pools | 238179.96 | 150228.6 | 87951.36 | 31266.48 | 0 | 35.55% | 31266.48
5 | Additional Items | 0 | 0 | 0 | 3238.4 | 0 |  | 3238.4
| SUB-TOTAL | 687282.9584 | 324907.6571 | 362375.3013 | 208379.0788 | 0 | 57.5% | 208379.0788

## BOQ - WP
DORCHESTER HOTEL & RESIDENCIES
WATERPROOFING WORK - IKK | [10 empty] | 2022-11-01
PROGRESS BOQ | [10 empty] | KCE PC 10
BOQ Ref: | Item Description | Unit | BOQ Qty. | Rate | Total Amount | Quantities |  |  | Amount - (A.E.D)
[6 empty] | Previous | This Month | Total to Date | Previous | This Month | Total to Date
WATERPROOFING
WATERPROOFING TO PLANTERS
| Supply and installation of 4mm SBS Balck finish membrane with ANTI ROOT property |  |  | One layer Biflex PL anti-root 4mm/180
A | Ground Level | m2 | 4462.9725 | 32 | 142815.1213 | 61.27% | 0% | 61.27% | 87501.4896 | 0 | 87501.4896
B | Level 02 | m2 | 1954.0125 | 32 | 62528.4 | 75.33% | 0% | 75.33% | 47100.8544 | 0 | 47100.8544
C | Level 04 | m2 | 2048 | 32 | 65536 | 100.1% | 0% | 100.1% | 65632.3648 | 0 | 65632.3648
D | Level 10 | m2 | 180.84 | 32 | 5786.88 | 100% | 0% | 100% | 5786.88 | 0 | 5786.88
E | Level 17 | m2 | 457.1341 | 32 | 14628.2912 |  |  |  |  | 0
F | Level 23 | m2 | 125.58 | 32 | 4018.56 | 100% | 0% | 100% | 4018.56 | 0 | 4018.56
G | Level 24 to 29 Residential | m2 | 254.64 | 32 | 8148.48 | 1 | 0% | 100% | 8148.48 | 0 | 8148.48
H | Level 29 Hotel | m2 | 31.91 | 32 | 1021.12 | 1 | 0% | 100% | 1021.12 | 0 | 1021.12
PROTECTION BOARD SIDES OF WALL 3mm thick protection board by spot bonding to vertical membrane
J | Ground Level | m2 | 2489.9725 | 14 | 34859.6156 | 78.49% | 0% | 78.49% | 27359.6617 | 0 | 27359.6617
K | Level 02 | m2 | 1255.8425 | 14 | 17581.795 | 80.26% | 0% | 80.26% | 14111.8838 | 0 | 14111.8838
L | Level 04 | m2 | 1128.092 | 14 | 15793.288 | 98.21% | 0% | 98.21% | 15511.2916 | 0 | 15511.2916
M | Level 10 | m2 | 137.35 | 14 | 1922.9 | 100% | 0% | 100% | 1922.9 | 0 | 1922.9
N | Level 17 | m2 | 287.4841 | 14 | 4024.7774 |  |  |  |  | 0
P | Level 23 | m2 | 90.87 | 14 | 1272.18 | 100% | 0% | 100% | 1272.18 | 0 | 1272.18
Q | Level 24 to 29 Residential | m2 | 201.25 | 14 | 2817.5 | 100% | 0% | 100% | 2817.5 | 0 | 2817.5
R | Level 29 Hotel | m2 | 18.84 | 14 | 263.76 | 100% | 0% | 100% | 263.76 | 0 | 263.76
ADD | Termination into groove using sealant (20x20mm groove by main contractor) | L.m | Item | 0 | Included
WATERPROOFING TO HARDSCAPE
| Supply and Installation One coat of Primer and lay one layer of Sopralene Flam 180 4P 4mm Black finish SBS modified non woven polyester reinforcement torch on membrane with 75 mm side and end laps fully bonded to the primed surface of the Substructures, including 3.2mm thick protection board for vertical areas, sealant for termination. |  |  | Sloping screed (By Others)+1 layer of Biflex PL 5mm/180 (-20c)
A | Ground Level | m2 |  | 28 | (Rate only)
B | Level 02 | m2 |  | 28 | (Rate only)
C | Level 04 | m2 |  | 28 | (Rate only)
D | Level 10 | m2 |  | 28 | (Rate only)
E | Level 17 | m2 |  | 28 | (Rate only)
F | Level 23 | m2 |  | 28 | (Rate only)
G | Level 24 | m2 |  | 28 | (Rate only)
H | Level 25 | m2 |  | 28 | (Rate only)
J | Level 26 | m2 |  | 28 | (Rate only)
K | Level 27 | m2 |  | 28 | (Rate only)
L | Level 29 Residential | m2 |  | 28 | (Rate only)
M | Level 29 Hotel | m2 |  | 28 | (Rate only)
| To Supply & Apply 3.2mm thick bituminous protection board | m2 |  | 17 | (Rate only)
WATERPROOFING TO WATER FEATURES
Supply and Apply Masterseal 588 two component acrylic modified Cementitious coating to the horizontal and vertical areas of to the thickness of 1.5mm
A | Level 02 | m2 | 284 | 28 | 7952 | 100% | 0% | 100% | 7952 | 0 | 7952
B | Level 04 | m2 | 128.33 | 28 | 3593.24 | 100% | 0% | 100% | 3593.24 | 0 | 3593.24
C | Level 23 | m2 | 567.29 | 28 | 15884.12 | 100% | 0% | 100% | 15884.12 | 0 | 15884.12
| Supply and installation One coat of Primer and lay one layer of Sopralene Flam 180 4P 5mm Black finish SBS modified non woven polyester reinforcement torch on membrane with 75 mm side and end laps fully bonded to the primed surface of the Substructures, including 3.2mm thick protection board for horizontal & vertical areas and sealant for termination |  | One layer of Biflex PL 5MM 180 (-20) + 3.2mm thick Protection board
D | Level 02 | m2 | 193 | 43.5 | 8395.5 | 100% | 0% | 100% | 8395.5 | 0 | 8395.5
E | Level 04 | m2 | 128.33 | 43.5 | 5582.355 | 100% | 0% | 100% | 5582.355 | 0 | 5582.355
F | Level 23 | m2 | 567.29 | 43.5 | 24677.115 | 100% | 0% | 100% | 24677.115 | 0 | 24677.115
ADD | Termination into groove using sealant (20x20mm groove by main contractor) | L.m | Item | 0 | Included
WATERPROOFING TO SWIMMING POOLS
Supply and Apply Masterseal 588 two component acrylic modified Cementitious coating to the horizontal and vertical areas of to the thickness of 1.5mm
A | Level 04 | m2 | 570 | 28 | 15960 | 1 | 0% | 100% | 15960 | 0 | 15960
B | Level 10 | m2 | 171 | 28 | 4788
C | Level 24 | m2 | 182.22 | 28 | 5102.16 | 1 | 0% | 100% | 5102.16 | 0 | 5102.16
D | Level 25 | m2 | 182.22 | 28 | 5102.16 | 1 | 0% | 100% | 5102.16 | 0 | 5102.16
E | Level 26 | m2 | 161.46 | 28 | 4520.88 |  | 0% |  | 0 | 0 | 0
F | Level 27 | m2 | 182.22 | 28 | 5102.16 | 1 | 0% | 100% | 5102.16 | 0 | 5102.16
G | Level 29 - RESIDENTIAL | m2 | 182.22 | 28 | 5102.16 | 100% | 0% | 100% | 5102.16 | 0 | 5102.16
H | Level 29 - HOTEL | m2 | 1692 | 28 | 47376
| Supply and installation One coat of Primer and lay one layer of Sopralene Flam 180 4P 5mm Black finish SBS modified non woven polyester reinforcement torch on membrane with 75 mm side and end laps fully bonded to the primed surface of the Substructures, including 3.2mm thick protection board for horizontal & vertical areas and sealant for termination |  | One layer of Biflex PL 5MM 180 (-20) + 3.2mm thick Protection board
J | Level 04 | m2 | 481.9 | 43.5 | 20962.65 | 100% | 0% | 100% | 20962.65 | 0 | 20962.65
K | Level 10 | m2 | 171 | 43.5 | 7438.5 | 100% | 0% | 100% | 7438.5 | 0 | 7438.5
L | Level 24 | m2 | 196.2 | 43.5 | 8534.7 | 100% | 0% | 100% | 8534.7 | 0 | 8534.7
M | Level 25 | m2 | 196.2 | 43.5 | 8534.7 | 100% | 0% | 100% | 8534.7 | 0 | 8534.7
N | Level 26 | m2 | 167.54 | 43.5 | 7287.99 | 100% | 0% | 100% | 7287.99 | 0 | 7287.99
P | Level 27 | m2 | 196.2 | 43.5 | 8534.7 | 100% | 0% | 100% | 8534.7 | 0 | 8534.7
Q | Level 29 - RESIDENTIAL | m2 | 196.2 | 43.5 | 8534.7 | 100% | 0% | 100% | 8534.7 | 0 | 8534.7
R | Level 29 - HOTEL | m2 | 1731 | 43.5 | 75298.5 | 100% | 0% | 100% | 75298.5 | 0 | 75298.5
ADD | Termination into groove using sealant (20x20mm groove by main contractor) | L.m |  | 0 | Included
ADDITIONAL ITEMS
Additional waterproofing below the planter void area
| Horizontal & Vertical | m2 | 678.1665 | 45 | (Rate Only) | 70.4 | 0 | 70.4 | 2252.8 | 0 | 2252.8
| Protection Board | m2 | 286.7415 | 45 | (Rate Only) | 70.4 | 0 | 70.4 | 985.6 | 0 | 985.6
| To Supply & Apply Protectdrain - HDPE drainage board 0.6mm thick | m2 | Item | 25.5 | (Rate Only)
TOTAL |  |  |  |  | 687282.9584 |  |  |  | 533286.7359 | 0 | 533286.7359

## Variation
No | Description | Qty | Unit | Rate | Amount | Pervious | Current | Cumulative | Pervious | Current | % | Cumulative
WA: PS-0033 R0
| Additional Screed work at Hotel Level 29, Swimming pool at accommodate the fiber optic cables and conduit | 1 | item | -33600 | -33600 | 0 | 1 | 1 | 0 | -26880 | 80% | -26880
WA: PS-0033 R1
| Supply and installation of 50mm bonded screed at Level 29 using pre-bagged 20N/mm2 from M/s Colmef | 1 | item | 193054.4 | 193054.4 | 0 | 1 | 1 | 0 | 154443.52 | 80% | 154443.52
127563.52

## GF
Job # 14345 - Plot BB.B03.018 Business Bay
Horizontal and vertical Waterproofing
SL. Nr. | Description | Type | LOCATION |  |  |  | Nr. | L | W | H | Horizontal Surface (M2) | Vertical Surface (M2)
|  |  | X1 | X2 | Y1 | Y2
IKK-LX-SD-GF-00001_00 Ground floor
| Planter | Horizontal | 20 | 24 | A |  | 1 | 75.97 |  |  | 75.97 |  | 2493.4
|  | Vertical |  |  |  |  | 1 | 106.12 |  | 1.95 |  | 413.868
| Planter | Horizontal |  |  |  |  | 1 | 23.2 |  |  | 23.2
|  | Vertical |  |  |  |  | 1 | 20.71 |  | 2.56 |  | 106.0352
| Planter | Horizontal |  |  |  |  | 1 | 6.66 |  |  | 6.66
|  | Vertical |  |  |  |  | 1 | 23.36 |  | 1 |  | 46.72
| Planter | Horizontal |  |  |  |  | 1 | 30.36 |  |  | 30.36
|  | Vertical |  |  |  |  | 1 | 55.94 |  | 0.9 |  | 100.692
| Planter | Horizontal |  |  |  |  | 1 | 124.18 |  |  | 124.18
|  | Vertical |  |  |  |  | 1 | 57.83 |  | 1.825 |  | 105.5397
| Planter | Horizontal |  |  |  |  | 1 | 117.52 |  |  | 117.52
|  | Vertical |  |  |  |  | 1 | 81.61 |  | 1.8 |  | 146.898
| Planter | Horizontal | 19 | 20 | A |  | 1 | 33.69 |  |  | 33.69
|  | Vertical |  |  |  |  | 1 | 27.27 |  | 2.56 |  | 139.6224
| Planter | Horizontal | 2 | 3 | A | B | 1 | 6.95 |  |  | 6.95
|  | Vertical |  |  |  |  | 1 | 20.67 |  | 1 |  | 41.34
| Planter | Horizontal | 4 | 5 | A | B | 1 | 6.88 |  |  | 6.88
|  | Vertical |  |  |  |  | 1 | 22.42 |  | 1 |  | 44.84
| Planter | Horizontal | Y2 | Y3 | H | I | 1 | 21.32 |  |  | 21.32
|  | Vertical |  |  |  |  | 1 | 21.94 |  | 2 |  | 87.76
| Planter | Horizontal | 1 | 2 | H | I | 1 | 23.16 |  |  | 23.16
|  | Vertical |  |  |  |  | 1 | 18.28 |  | 2 |  | 73.12
| Planter | Horizontal | 3 | 4 | H | I | 1 | 81.56 |  |  | 81.56
|  | Vertical |  |  |  |  | 1 | 37.31 |  | 2.25 |  | 167.895
| Planter | Horizontal | 2 | 3 | A |  | 1 | 66.95 |  |  | 66.95
|  | Vertical |  |  |  |  | 1 | 17.12 |  | 2.13 |  | 72.9312
| Planter | Horizontal |  |  |  |  | 1 | 1.63 |  |  | 1.63
|  | Vertical |  |  |  |  | 1 | 6.8 |  | 0.6 |  | 4.08
| Planter | Horizontal |  |  |  |  | 1 | 4.3 |  |  | 4.3
|  | Vertical |  |  |  |  | 1 | 16.09 |  | 0.6 |  | 9.654
| Planter | Horizontal |  |  |  |  | 1 | 2.61 |  |  | 2.61
|  | Vertical |  |  |  |  | 1 | 9.93 |  | 1 |  | 9.93
| Planter | Horizontal |  |  |  |  | 1 | 2.45 |  |  | 2.45
|  | Vertical |  |  |  |  | 1 | 9.38 |  | 1 |  | 9.38
| Planter | Horizontal |  |  |  |  | 1 | 37.5 |  |  | 37.5
|  | Vertical |  |  |  |  | 1 | 26.8 |  | 2.53 |  | 67.804
| Planter | Horizontal |  |  |  |  | 1 | 11.9 |  |  | 11.9
|  | Vertical |  |  |  |  | 1 | 29.62 |  | 1 |  | 29.62
| Planter | Horizontal |  |  |  |  | 1 | 3.51 |  |  | 3.51
|  | Vertical |  |  |  |  | 1 | 14.5 |  | 1 |  | 14.5
| Planter | Horizontal |  |  |  |  | 2 | 4.31 |  |  | 8.62
|  | Vertical |  |  |  |  | 2 | 16.28 |  | 1 |  | 32.56
| Planter | Horizontal |  |  |  |  | 1 | 1.2 |  |  | 1.2
|  | Vertical |  |  |  |  | 1 | 5.37 |  | 1 |  | 5.37
| Planter | Horizontal |  |  |  |  | 1 | 36.54 |  |  | 36.54
|  | Vertical |  |  |  |  | 1 | 36.57 |  | 1.8 |  | 65.826
| Planter | Horizontal |  |  |  |  | 1 | 18.9 |  |  | 18.9
|  | Vertical |  |  |  |  | 1 | 23.3 |  | 1.8 |  | 41.94
| Planter | Horizontal |  |  |  |  | 1 | 18.71 |  |  | 18.71
|  | Vertical |  |  |  |  | 1 | 28.04 |  | 2.2 |  | 61.688
| Planter | Horizontal |  |  |  |  | 1 | 7.59 |  |  | 7.59
|  | Vertical |  |  |  |  | 1 | 13.28 |  | 2.2 |  | 29.216
| Planter | Horizontal |  |  |  |  | 1 | 6.3 |  |  | 6.3
|  | Vertical |  |  |  |  | 1 | 11.56 |  | 2.2 |  | 25.432
TOTAL QUANTITY | [10 empty] | 780.16 | 1954.2615

## L2
Job # 14345 - Plot BB.B03.018 Business Bay
Horizontal and vertical Waterproofing
SL. Nr. | Description | Type | LOCATION |  |  |  | Nr. | L | W | H | Horizontal Surface (M2) | Vertical Surface (M2)
|  |  | X1 | X2 | Y1 | Y2
LA-GA-L2-0011-DWG_A Level 2
| Planter | Horizontal |  |  |  |  | 1 | 71.51 |  |  | 71.51 |  | 2493.4
|  | Vertical |  |  |  |  | 1 | 118.34 |  | 1.33 |  | 314.7844
| Planter | Horizontal |  |  |  |  | 8 | 0.96 |  |  | 7.68
|  | Vertical |  |  |  |  | 8 | 4 |  | 1.3 |  | 83.2
| Planter | Horizontal |  |  |  |  | 1 | 2.23 |  |  | 2.23
|  | Vertical |  |  |  |  | 1 | 6.67 |  | 0.9 |  | 6.003
| Planter | Horizontal |  |  |  |  | 1 | 4.69 |  |  | 4.69
|  | Vertical |  |  |  |  | 1 | 11.95 |  | 0.9 |  | 10.755
| Planter | Horizontal |  |  |  |  | 1 | 29.28 |  |  | 29.28
|  | Vertical |  |  |  |  | 1 | 21.67 |  | 1.65 |  | 35.7555
| Planter | Horizontal |  |  |  |  | 1 | 78.16 |  |  | 78.16
|  | Vertical |  |  |  |  | 1 | 38 |  | 1.65 |  | 62.7
| Planter | Horizontal |  |  |  |  | 1 | 42.08 |  |  | 42.08
|  | Vertical |  |  |  |  | 1 | 26.74 |  | 1.85 |  | 49.469
| Planter | Horizontal |  |  |  |  | 1 | 18.69 |  |  | 18.69
|  | Vertical |  |  |  |  | 1 | 31.52 |  | 0.965 |  | 30.4168
| Planter | Horizontal |  |  |  |  | 1 | 21.21 |  |  | 21.21
|  | Vertical |  |  |  |  | 1 | 48 |  | 0.7 |  | 33.6
| Planter | Horizontal |  |  |  |  | 1 | 16.25 |  |  | 16.25
|  | Vertical |  |  |  |  | 1 | 23.71 |  | 2 |  | 47.42
| Planter | Horizontal |  |  |  |  | 1 | 9.13 |  |  | 9.13
|  | Vertical |  |  |  |  | 1 | 15.97 |  | 2 |  | 31.94
| Planter | Horizontal |  |  |  |  | 1 | 30.1 |  |  | 30.1
|  | Vertical |  |  |  |  | 1 | 58.28 |  | 1.15 |  | 67.022
| Planter | Horizontal |  |  |  |  | 1 | 2.95 |  |  | 2.95
|  | Vertical |  |  |  |  | 1 | 7.07 |  | 0.9 |  | 12.726
| Planter | Horizontal |  |  |  |  | 1 | 21.4 |  |  | 21.4
|  | Vertical |  |  |  |  | 1 | 31.65 |  | 0.9 |  | 56.97
| Planter | Horizontal |  |  |  |  | 1 | 27.12 |  |  | 27.12
|  | Vertical |  |  |  |  | 1 | 34.9 |  | 0.9 |  | 62.82
| Planter | Horizontal |  |  |  |  | 1 | 81.43 |  |  | 81.43
|  | Vertical |  |  |  |  | 1 | 73.15 |  | 1.4 |  | 102.41
TOTAL QUANTITY | [10 empty] | 463.91 | 1007.9917

## L4
Job # 14345 - Plot BB.B03.018 Business Bay
Horizontal and vertical Waterproofing
SL. Nr. | Description | Type | LOCATION |  |  |  | Nr. | L | W | H | Horizontal Surface (M2) | Vertical Surface (M2)
|  |  | X1 | X2 | Y1 | Y2
IKK-LX-SD-L4-00003_00 Level 4
| Planter | Horizontal | X1 | X3 | Y1 | Y2 | 1 | 56 |  |  | 56 |  | 2493.4
|  | Vertical |  |  |  |  | 1 | 65 |  | 1.4 |  | 91
| Planter | Horizontal | X1 | X3 | Y3 |  | 1 | 31.41 |  |  | 31.41
|  | Vertical |  |  |  |  | 1 | 44.01 |  | 1.4 |  | 61.614
| Planter | Horizontal | Q | X | 22 | 24 | 1 | 74.58 |  |  | 74.58
|  | Vertical |  |  |  |  | 1 | 94.22 |  | 1.7 |  | 160.174
| Planter | Horizontal |  |  |  |  | 1 | 1.58 |  |  | 1.58
|  | Vertical |  |  |  |  | 1 | 5.22 |  | 1 |  | 5.22
| Planter | Horizontal |  |  |  |  | 1 | 1.91 |  |  | 1.91
|  | Vertical |  |  |  |  | 1 | 6.38 |  | 1 |  | 6.38
| Planter | Horizontal |  |  |  |  | 1 | 2.32 |  |  | 2.32
|  | Vertical |  |  |  |  | 1 | 7.47 |  | 1 |  | 7.47
| Planter | Horizontal |  |  |  |  | 1 | 7.34 |  |  | 7.34
|  | Vertical |  |  |  |  | 1 | 11.74 |  | 1 |  | 11.74
| Planter | Horizontal |  |  |  |  | 1 | 2.4 |  |  | 2.4
|  | Vertical |  |  |  |  | 1 | 9.21 |  | 0.6 |  | 5.526
| Planter | Horizontal |  |  |  |  | 1 | 182.55 |  |  | 182.55
|  | Vertical |  |  |  |  | 1 | 270.12 |  | 0.8 |  | 216.096
| Planter | Horizontal |  |  |  |  | 1 | 176.05 |  |  | 176.05
|  | Vertical |  |  |  |  | 1 | 182.08 |  | 1.4 |  | 254.912
| Planter | Horizontal |  |  |  |  | 1 | 8.8 |  |  | 8.8
|  | Vertical |  |  |  |  | 1 | 12.78 |  | 1.1 |  | 14.058
| Planter | Horizontal |  |  |  |  | 1 | 20.09 |  |  | 20.09
|  | Vertical |  |  |  |  | 1 | 50.33 |  | 1 |  | 50.33
| Planter | Horizontal |  |  |  |  | 1 | 265.11 |  |  | 265.11
|  | Vertical |  |  |  |  | 1 | 84.12 |  | 0.7 |  | 58.884
| Planter | Horizontal |  |  |  |  | 1 | 63.23 |  |  | 63.23
|  | Vertical |  |  |  |  | 1 | 55.33 |  | 1.4 |  | 77.462
| Planter | Horizontal |  |  |  |  | 1 | 12.12 |  |  | 12.12
|  | Vertical |  |  |  |  | 1 | 17.86 |  | 1 |  | 17.86
| Planter | Horizontal |  |  |  |  | 7 | 0.636 |  |  | 4.452
|  | Vertical |  |  |  |  | 7 | 5.827 |  | 0.6 |  | 24.4734
| Planter | Horizontal |  |  |  |  | 1 | 33.12 |  |  | 33.12
|  | Vertical |  |  |  |  | 1 | 44.75 |  | 1 |  | 44.75
TOTAL QUANTITY | [10 empty] | 943.062 | 1107.9494

## L23
Job # 14345 - Plot BB.B03.018 Business Bay
Horizontal and vertical Waterproofing
SL. Nr. | Description | Type | LOCATION |  |  |  | Nr. | L | W | H | Horizontal Surface (M2) | Vertical Surface (M2)
|  |  | X1 | X2 | Y1 | Y2
LA-GA-L23-0200_ Level 23
| Planter | Horizontal | 8 | 11 | G |  | 1 | 34.71 |  |  | 34.71 |  | 2493.4
|  | Vertical |  |  |  |  | 1 | 46.6 |  | 1.95 |  | 90.87
TOTAL QUANTITY | [10 empty] | 34.71 | 90.87

## L24-L29
Job # 14345 - Plot BB.B03.018 Business Bay
Horizontal and vertical Waterproofing
SL. Nr. | Description | Type | LOCATION |  |  |  | Nr. | L | W | H | Horizontal Surface (M2) | Vertical Surface (M2)
|  |  | X1 | X2 | Y1 | Y2
LA-GA-L24-0010_ Level 24
| Planter | Horizontal | 2 | 3 | D | E | 1 | 4.62 |  |  | 4.62
|  | Vertical |  |  |  |  | 1 | 16.2 |  | 1 |  | 16.2
| Planter | Horizontal | 2 | 3 | F | G | 1 | 2.16 |  |  | 2.16
|  | Vertical |  |  |  |  | 1 | 8 |  | 1 |  | 8
| Planter | Horizontal | 2 | 3 | G | H | 1 | 3.96 |  |  | 3.96
|  | Vertical |  |  |  |  | 1 | 10.2 |  | 1 |  | 10.2
LA-GA-L25-0010_ Level 25
| Planter | Horizontal | 2 | 3 | D | E | 1 | 4.62 |  |  | 4.62
|  | Vertical |  |  |  |  | 1 | 16.2 |  | 1 |  | 16.2
| Planter | Horizontal | 2 | 3 | F | G | 1 | 2.16 |  |  | 2.16
|  | Vertical |  |  |  |  | 1 | 8 |  | 1 |  | 8
LA-GA-L26-0010_ Level 26
| Planter | Horizontal | 7 | 8 | D | E | 1 | 7.19 |  |  | 7.19
|  | Vertical |  |  |  |  | 1 | 11.56 |  | 2 |  | 23.12
| Planter | Horizontal | 7 | 8 | E | G | 1 | 19.89 |  |  | 19.89
|  | Vertical |  |  |  |  | 1 | 26.1 |  | 2 |  | 52.2
LA-GA-L27-0010_ Level 27
| Planter | Horizontal | 2 | 3 | D | E | 1 | 4.62 |  |  | 4.62
|  | Vertical |  |  |  |  | 1 | 16.2 |  | 1 |  | 16.2
| Planter | Horizontal | 2 | 3 | F | G | 1 | 2.16 |  |  | 2.16
|  | Vertical |  |  |  |  | 1 | 8 |  | 1 |  | 8
LA-GA-L29-0010_ Level 29
| Planter | Horizontal | 2 | 3 | D | E | 1 | 4.62 |  |  | 4.62
|  | Vertical |  |  |  |  | 1 | 16.2 |  | 1 |  | 16.2
| Planter | Horizontal | 2 | 3 | F | G | 1 | 2.16 |  |  | 2.16
|  | Vertical |  |  |  |  | 1 | 8 |  | 1 |  | 8
| Planter | Horizontal | 2 | 3 | G | H | 1 | 3.96 |  |  | 3.96
|  | Vertical |  |  |  |  | 1 | 10.2 |  | 1 |  | 10.2
TOTAL QUANTITY | [10 empty] | 62.12 | 192.52