## Sheet1
No | Description | Qty | Unit | Rate | Amount | Previous | This Month | % | Cumulative | Remark
Carpet Works - Khansaheb - Dorchester Hotel
Supply & Installation Customized Tufted Printed Carpet
| Area: RES-FA-05 - Meeting Room | 35.2 | m2 | 265 | 9328 | 7462.4 | 466.4 | 85% | 7928.8 | 85% until MIR raised and approved
| Area: RES-FA-05 - Multifunction Room | 43.8 | m2 | 265 | 11607 | 9285.6 | 580.35 | 85% | 9865.95 | 85% until MIR raised and approved
Wooden Flooring Works - Khansaheb - Dorchester Hotel
Supply & Installation Engineered Wooden Flooring - Chevron
| Area: RES-WD-01 - Ground Floor Lobby Corridor | 62 | L Sum | 283 | 17546 | 14036.8 | 1754.6 | 90% | 15791.4 | 90% until WIR approval
| Area: RES-WD-01 - Ground Floor Lift Lobby | 14 | L Sum | 293 | 4102 | 3281.6 | 410.2 | 90% | 3691.8 | 90% until WIR approval
| Area: RES-WD-01 - Level 2 Corridor | 25 | L Sum | 283 | 7075 | 5660 | 353.75 | 85% | 6013.75 | 85% until MIR raised and approved
| Area: RES-WD-01 - Level 2 Lift Lobby | 12 | L Sum | 293 | 3516 | 2812.8 | 175.8 | 85% | 2988.6 | 85% until MIR raised and approved
| Area: RES-WD-01 - Level 4 Fitness & Yoga | 160 | L Sum | 267 | 42720 | 34176 | 4272 | 90% | 38448 | 90% until WIR approval
| Area: RES-WD-01 - Level 4 Lift Lobby | 12 | L Sum | 283 | 3396 | 2716.8 | 169.8 | 85% | 2886.6 | 85% until MIR raised and approved
| Area: RES-WD-01 - Level 23 Corridor | 37 | L Sum | 283 | 10471 | 8376.8 | 523.55 | 85% | 8900.35 | 85% until MIR raised and approved
| Area: RES-WD-01 - Level 23 Lift Lobby | 19 | L Sum | 283 | 5377 | 4301.6 | 268.85 | 85% | 4570.45 | 85% until MIR raised and approved
| Storage Charges - from 18.03.2022 (189Days) | 1 | L Sum | 18522 | 18522 | 18522 | 0 | 100% | 18522
Variation
| Storage Charges - from 01.11.2022 (61Days) | 1 | L Sum | 5978 | 5978 | 5978 | 0 | 100% | 5978
[5 empty] | 133660 | 116610.4 | 8975.3 |  | 125585.7
| Discount |  |  |  | -203 | -177.1054 | -13.6315 |  | -190.7369
[5 empty] | 133457 | 116433.2946 | 8961.6685 |  | 125394.9631
| Advance Payment |  |  |  |  | 34477.2 | 0 |  | 34477.2
| Advance Payment Recovery |  |  |  |  | -27579.9884 | -2688.5006 | 30% | -30268.4889
[6 empty] | 123330.5062 | 6273.168 |  | 129603.6742
[5 empty] | KCE Claim | 127949.2 | 6425.45 |  | 134374.65
[5 empty] | Difference | -4618.6938 | -152.282 | 0 | -4770.9758