## Sheet1
No | Description | Qty | Unit | Rate | Amount | Previous | This Month | % | Cumulative | Remark
Carpet Works - Khansaheb - Dorchester Hotel
Supply & Installation Customized Tufted Printed Carpet
| Area: RES-FA-05 - Meeting Room | 35.2 | m2 | 265 | 9328 | 0 | 7462.4 | 80% | 7462.4 | 80% until MIR raised and approved
| Area: RES-FA-05 - Multifunction Room | 43.8 | m2 | 265 | 11607 | 0 | 9285.6 | 80% | 9285.6 | 80% until MIR raised and approved
Wooden Flooring Works - Khansaheb - Dorchester Hotel
Supply & Installation Engineered Wooden Flooring - Chevron
| Area: RES-WD-01 - Ground Floor Lobby Corridor | 62 | L Sum | 283 | 17546 | 0 | 14036.8 | 80% | 14036.8 | 80% until MIR raised and approved
| Area: RES-WD-01 - Ground Floor Lift Lobby | 14 | L Sum | 293 | 4102 | 0 | 3281.6 | 80% | 3281.6 | 80% until MIR raised and approved
| Area: RES-WD-01 - Level 2 Corridor | 25 | L Sum | 283 | 7075 | 0 | 5660 | 80% | 5660 | 80% until MIR raised and approved
| Area: RES-WD-01 - Level 2 Lift Lobby | 12 | L Sum | 293 | 3516 | 0 | 2812.8 | 80% | 2812.8 | 80% until MIR raised and approved
| Area: RES-WD-01 - Level 4 Fitness & Yoga | 160 | L Sum | 267 | 42720 | 0 | 34176 | 80% | 34176 | 80% until MIR raised and approved
| Area: RES-WD-01 - Level 4 Lift Lobby | 12 | L Sum | 283 | 3396 | 0 | 2716.8 | 80% | 2716.8 | 80% until MIR raised and approved
| Area: RES-WD-01 - Level 23 Corridor | 37 | L Sum | 283 | 10471 | 0 | 8376.8 | 80% | 8376.8 | 80% until MIR raised and approved
| Area: RES-WD-01 - Level 23 Lift Lobby | 19 | L Sum | 283 | 5377 | 0 | 4301.6 | 80% | 4301.6 | 80% until MIR raised and approved
| Storage Charges - from 18.03.2022 (189Days) | 1 | L Sum | 18522 | 18522 | 18533 | -11 | 100% | 18522
Variation
| Storage Charges - from 01.11.2022 (61Days) | 1 | L Sum | 5978 | 5978 | 0 | 5978 | 100% | 5978
[5 empty] | 133660 | 18533 | 98077.4 |  | 116610.4
| Discount |  |  |  | -203 | 0 | -177.1054 |  | -177.1054
[5 empty] | 133457 | 18533 | 97900.2946 |  | 116433.2946
| Advance Payment |  |  |  |  | 34477.2 | 0 |  | 34477.2
| Advance Payment Recovery |  |  |  |  | 0 | -27579.9884 | 30% | -27579.9884
[6 empty] | 53010.2 | 70320.3062 |  | 123330.5062