## Summary
2023-01-30
TABLE SUMMARY
1.1. Advance Payment
| Table No. | Description | Amount
| Table 1 | Supply , Delivery and Installation of Metal Works to Landscape areas & Gabion Wall and Agreed Variation - Advance Payment | 499566
AED 3,330,440.00 x 15% = AED 499,566.00
|  | TOTAL AMOUNT AED. | 499566
Carried to Item 1.1 @ Payment Application no. 09
1.2. External Metal Works & Agreed Variations
| Table No. | Description | Amount
| Table 1 | External Metal Works & Agreed Variations as per the Contract | 1586862.4
| Table 2 | Other Agreed Variations | 3059419.33
|  | TOTAL AMOUNT AED. | 4646281.73 | 5079695.4616 | 433413.7315
Carried to Item 1.2 @ Payment Application no. 09

## T1 - As per Contract
PLOT 18 - DORCHESTER HOTEL | [11 empty] | 2023-01-30
PAYMENT APPLICATION
PACKAGE: SUPPLY, DELIVERY & INSTALLATION OF METAL WORKS TO LANDSCAPE AREAS & GABION WALL | [11 empty] | Table 1
Item | DESCRIPTION | Qty | Unit | Rate | Amount (Dhs.) | Certified % |  |  | Certified Quantity |  |  | Certified Amount [AED]
[6 empty] | Previous | This Month | Work Completed | Previous | This Month | Work Completed | Previous | This Month | Amount Claimed (AED)
METAL CLADDING WORKS
A | Supply and Installation of Powder coated Aluminum cladding over the block planters as per attached sketch no. AMI-SK-001_01.
1 | Type EC-03-A wall cladding to planter box, Anthracite Grey, powder coated finish as per sketch no. AMI-SK-001_01 - GROUND FLOOR. | 25 | m2 | 820 | 20500 | 100% | 0% | 100% | 89.6 | 0 | 89.6 | 73472 | 0 | 73472
2 | Type EC-05-A wall cladding to planter box, RAL 7016 Anthracite Grey, powder coated finish, as per sketch no. AMI-SK-001_01 - LEVEL 2. | 25 | m2 | 820 | 20500 |  |  |  |  | 0 |  | 0 | 0 | 0
3 | Type EC-05-A wall cladding to planter box, RAL 7016 Anthracite Grey, powder coated finish, as per sketch no. AMI-SK-001_01 - LEVEL 4 HOTEL. | 119.82 | m2 | 820 | 98252.4 |  |  |  |  | 0 |  | 0 | 0 | 0
4 | Type EC-06-A wall cladding to planter box, RAL 7016 Anthracite Grey, powder coated finish, as per sketch no. AMI-SK-001_01 - LEVEL 4 HOTEL. | 27.12 | m2 | 820 | 22238.4 |  |  |  |  | 0 |  | 0 | 0 | 0
5 | Type EC-03-A wall cladding to planter box, RAL 7016 Anthracite Grey, powder coated finish, as per sketch no. AMI-SK-001_01 - LEVEL 10. | 13.28 | m2 | 820 | 10889.6 | 100% | 0% | 100% | 13.28 | 0 | 13.28 | 10889.6 | 0 | 10889.6
6 | Type EC-04-A wall cladding to planter box, RAL 7016 Anthracite Grey, powder coated finish, as per sketch no. AMI-SK-001_01 - LEVEL 10. | 22.04 | m2 | 820 | 18072.8 | 100% | 0% | 100% | 22.04 | 0 | 22.04 | 18072.8 | 0 | 18072.8
7 | EC-01-B Planter wall cladding with mild steel, RAL 7016 Anthracite Grey colour, Powder coated Matt finish, as per sketch no. AMI-SK-001_01 - LEVEL 24 to LEVEL 29 RESIDENTIAL. | 125 | m2 | 820 | 102500 | 100% | 0% | 100% | 12.35 | 0 | 12.35 | 10127 | 0 | 10127
8 | RAL 7016 Anthracite Grey Colour, powder coated Matt finish, Shadow Gap, ST-01-C; Height = 100 mm, Powder Coated Aluminum Angle 100x50x3 mm thick with countersunk screws. - LEVEL 24 to LEVEL 29 RESIDENTIAL | 18.4 | m | 195 | 3588 |  |  |  |  | 0 |  | 0 | 0 | 0
METAL PLANTER BOX
B | Supply & Installation of Planter Box
1 | Planter box 1200 x 1200 x 1335 mm as per Sketch no. AMI-SK-003_01 to be made of 5 mm thick Powder Coated Aluminum Sheet - GROUND LEVEL | 12 | Nos. | 8000 | 96000 |  |  |  |  | 0 |  | 0 | 0 | 0
2 | Planter box 1000 x 1000 x 1650 mm, as per Sketch no. AMI-SK-003_01 to be made of 5 mm thick Powder Coated Aluminum Sheet - LEVEL 4 RESIDENTIAL | 38 | Nos. | 8250 | 313500 |  |  |  |  | 0 |  | 0 | 0 | 0
3 | Raised Planter 8860 x 750 x 620 mm, as per Sketch no. AMI-SK-003_01 to be made of 5 mm thick Powder Coated Aluminum Sheet - LEVEL 04 HOTEL. | 1 | No. | 15000 | 15000 |  |  |  |  | 0 |  | 0 | 0 | 0
4 | Raised planter 5530 x 500 x 620 mm, as per Sketch no. AMI-SK-003_01 to be made of 5 mm thick Powder Coated Aluminum Sheet - LEVEL 04 HOTEL. | 1 | No. | 9400 | 9400 |  |  |  |  | 0 |  | 0 | 0 | 0
5 | Raised planter 3500 x 1300 / 500 x 620 mm, as per Sketch no. AMI-SK-003_01 to be made of 5 mm thick Powder Coated Aluminum Sheet - LEVEL 04 HOTEL. | 1 | No. | 6250 | 6250 |  |  |  |  | 0 |  | 0 | 0 | 0
6 | Raised planter 1320 x 1300/ 800 x 620 mm, as per Sketch no. AMI-SK-003_01 to be made of 5 mm thick Powder Coated Aluminum Sheet - LEVEL 04 HOTEL. | 1 | No. | 3375 | 3375 |  |  |  |  | 0 |  | 0 | 0 | 0
7 | Raised planter 5860 x 500 x 620 mm, as per Sketch no. AMI-SK-003_01 to be made of 5 mm thick Powder Coated Aluminum Sheet - LEVEL 04 HOTEL. | 1 | No. | 10000 | 10000 |  |  |  |  | 0 |  | 0 | 0 | 0
8 | Raised planter 7000 x 500 x 620 mm, as per Sketch no. AMI-SK-003_01 to be made of 5 mm thick Powder Coated Aluminum Sheet - LEVEL 04 HOTEL. | 2 | Nos. | 11750 | 23500 |  |  |  |  | 0 |  | 0 | 0 | 0
9 | Raised planter 8730 x 1540 x 1170 mm, as per Sketch no. AMI-SK-003_01 to be made of 5 mm thick Powder Coated Aluminum Sheet - LEVEL 04 HOTEL. | 1 | No. | 30000 | 30000 |  |  |  |  | 0 |  | 0 | 0 | 0
10 | Planter on slab 4380 x 900 x 665 mm, as per Sketch no. AMI-SK-003_01 to be made of 5 mm thick Powder Coated Aluminum Sheet - LEVEL 24. | 1 | No. | 8750 | 8750 |  |  |  |  | 0 |  | 0 | 0 | 0
11 | Planter on slab 3600 x 600 x 665 mm, as per Sketch no. AMI-SK-003_01 to be made of 5 mm thick Powder Coated Aluminum Sheet - LEVEL 24. | 1 | No. | 7000 | 7000 |  |  |  |  | 0 |  | 0 | 0 | 0
12 | Planter on slab 7700 x 600 x 665 mm, as per Sketch no. AMI-SK-003_01 to be made of 5 mm thick Powder Coated Aluminum Sheet - LEVEL 24. | 1 | No. | 13750 | 13750 |  |  |  |  | 0 |  | 0 | 0 | 0
13 | Planter on slab 3600 x 600 x 665 mm, as per Sketch no. AMI-SK-003_01 to be made of 5 mm thick Powder Coated Aluminum Sheet - LEVEL 25. | 1 | No. | 7000 | 7000 |  |  |  |  | 0 |  | 0 | 0 | 0
14 | Planter on slab 7700 x 600 x 665 mm, as per Sketch no. AMI-SK-003_01 to be made of 5 mm thick Powder Coated Aluminum Sheet - LEVEL 25. | 1 | No. | 13750 | 13750 |  |  |  |  | 0 |  | 0 | 0 | 0
15 | Planter on slab 3600 x 600 x 665 mm, as per Sketch no. AMI-SK-003_01 to be made of 5 mm thick Powder Coated Aluminum Sheet - LEVEL 27. | 1 | No. | 7000 | 7000 |  |  |  |  | 0 |  | 0 | 0 | 0
16 | Planter on slab 7700 x 600 x 665 mm, as per Sketch no. AMI-SK-003_01 to be made of 5 mm thick Powder Coated Aluminum Sheet - LEVEL 27. | 1 | No. | 13750 | 13750 |  |  |  |  | 0 |  | 0 | 0 | 0
17 | Planter on slab 4400 x 900 x 665 mm, as per Sketch no. AMI-SK-003_01 to be made of 5 mm thick Powder Coated Aluminum Sheet - LEVEL 29. | 1 | No. | 8750 | 8750 |  |  |  |  | 0 |  | 0 | 0 | 0
18 | Planter on slab 3600 x 600 x 665 mm, as per Sketch no. AMI-SK-003_01 to be made of 5 mm thick Powder Coated Aluminum Sheet - LEVEL 29. | 1 | No. | 7000 | 7000 |  |  |  |  | 0 |  | 0 | 0 | 0
19 | Planter on slab 7700 x 600 x 665 mm, as per Sketch no. AMI-SK-003_01 to be made of 5 mm thick Powder Coated Aluminum Sheet - LEVEL 29. | 1 | No. | 13750 | 13750 |  |  |  |  | 0 |  | 0 | 0 | 0
METAL FENCES, GATES AND BALUSTRADES
C | Fabrication, Supply & Installation of Metal fences, gates and balustrades
1 | EC-05-A, Ballroom Sunken Garden Gate-01, 2m wide single leaf, 1m high, Powder Coated Aluminum - GROUND LEVEL | 1 | No. | 2800 | 2800 |  |  |  |  | 0 |  | 0 | 0 | 0
2 | EC-06-A, Ballroom Sunken Garden Gate-02, 3.5m wide sliding gate, 3 mtr. High, Powder Coated Aluminum - GROUND LEVEL | 1 | No. | 4900 | 4900 | 100% | 0% | 100% | 1 | 0 | 1 | 4900 | 0 | 4900
3 | EC-07-A, Ballroom Sunken Garden Gate-03, 1.2m wide single leaf, 1 m. High, Powder Coated Aluminum - GROUND LEVEL | 2 | Nos. | 1680 | 3360 | 100% | 0% | 100% | 1 | 0 | 1 | 1680 | 0 | 1680
4 | EC-08-A, 1.65m High Fence - GROUND LEVEL | 5 | m | 1240 | 6200 | 0% | 100% | 100% |  | 5 | 5 | 0 | 6200 | 6200
5 | EC-08-A, 1.65m High Gate, double leaf, 2m wide - GROUND LEVEL | 1 | No. | 4650 | 4650 | 0% | 100% | 100% |  | 1 | 1 | 0 | 4650 | 4650
6 | EC-10-A Hedge balustrade 1200 mm high as per drawing LA-LD-GL-3509, Powder Coated Aluminum - GROUND LEVEL | 50 | m | 595 | 29750 |  |  |  |  | 0 |  | 0 | 0 | 0
7 | Handrail 900 mm high, brushed stainless steel, as per drawing LA-LD-GL-3651 - GROUND LEVEL | 15 | m | 920 | 13800 | 0% | 70% | 70% |  | 15 | 15 | 0 | 9660 | 9660
8 | EC-06-A, Gate Panel, 1.0 m high, Powder coated Aluminum - LEVEL 02 | 1.1 | L.M | 1400 | 1540 |  |  |  |  | 0 |  | 0 | 0 | 0
9 | EC-07-A, 1200 mm high hedge balustrade, Powder Coated Aluminum - LEVEL 02 | 71.34 | L.M | 595 | 42447.3 |  |  |  |  | 0 |  | 0 | 0 | 0
10 | Type EC-05-A, hedge balustrade, 1600 mm high, Powder Coated Aluminum. LEVEL 04 RESIDENTIAL | 87.94 | m | 800 | 70352 |  |  |  |  | 0 |  | 0 | 0 | 0
11 | Handrail 900 mm high, brushed stainless steel, as per drawing LA-LD-L4-3661, wall mounted - LEVEL 04 RESIDENTIAL | 15 | m | 550 | 8250 | 0% | 70% | 70% |  | 15 | 15 | 0 | 5775 | 5775
12 | EC-07-A Hedge Balustrade aluminum, Powder Coated Aluminum, RAL7016 anthracite grey, 1300mm high - LEVEL 04 HOTEL | 25.62 | m | 645 | 16524.9 |  |  |  |  | 0 |  | 0 | 0 | 0
13 | EC-08-A Gate Aluminum, Powder Coated finish, RAL 7016 anthracite grey, Single swing, 1200 mm high, 1400 mm width - LEVEL 04 Hotel | 1 | No | 2350 | 2350 |  |  |  |  | 0 |  | 0 | 0 | 0
14 | EC-04-A Sliding Gate Aluminum to Private Dining, powder coated finish, RAL 7016 anthracite grey, 2150 mm length, 1200 mm High, Powder Coated Aluminum - LEVEL 04 HOTEL | 1 | No. | 3650 | 3650 | 85% | 15% | 100% | 0.85 | 0.15 | 1 | 3102.5 | 547.5 | 3650
15 | Handrail 900 mm high, brushed stainless steel as per drawing LA-LD-L4-3651 - LEVEL 04 HOTEL (Material On Site = 15 L.M x .70% = 10.5 L.M) | 15 | m | 920 | 13800 | 0% | 70% | 70% |  | 10.5 | 10.5 | 0 | 6762 | 6762
16 | EC-05-A Hedge Balustrade, 1200 mm high, Powder Coated Aluminum - LEVEL 10 RESIDENTIAL | 50 | L.M | 595 | 29750 |  |  |  |  | 0 |  | 0 | 0 | 0
17 | Handrail 900 mm high, brushed stainless steel as per drawing LA-LD-L10-3651 - LEVEL 10 RESIDENTIAL (Material On Site = 15 L.M x .70% = 10.5 L.M) | 15 | L.M | 920 | 13800 | 0% | 70% | 70% |  | 10.5 | 10.5 | 0 | 6762 | 6762
18 | Handrail 900 mm high, brushed stainless steel as per drawing LA-LD-L17-3651, wall mounted - LEVEL 17 | 15 | m | 550 | 8250 |  |  |  |  | 0 |  | 0 | 0 | 0
19 | Type EC-03-A, Stainless steel sheet screen, decorative, average height 1 m (Square mesh) - C002 Bronze mirror, Water ripple C002 finish - LEVEL 17 | 129.92 | m | - | Excluded
20 | Handrail 900 mm high, brushed stainless steel as per drawing LA-LD-L23-3651 - LEVEL 23 RESIDENTIAL (Material On Site = 15 L.M x .70% = 10.5 L.M) | 15 | L.M | 920 | 13800 | 0% | 70% | 70% |  | 10.5 | 10.5 | 0 | 6762 | 6762
21 | EC-04-A Hedge Balustrade, 1200 mm high, Powder Coated Aluminum - LEVEL 26 RESIDENTIAL | 50 | m | 595 | 29750 |  |  |  |  | 0 |  | 0 | 0 | 0
22 | Handrail 900 mm high, brushed stainless steel as per drawing LA-LD-L26-3601 - LEVEL 26 RESIDENTIAL | 15 | m | 920 | 13800 |  |  |  |  | 0 |  | 0 | 0 | 0
23 | Handrail 900 mm high, brushed stainless steel as per drawing LA-LD-L29-3651 - LEVEL 29 HOTEL | 15 | m | 920 | 13800 |  |  |  |  | 0 |  | 0 | 0 | 0
24 | Handrail 900 mm high, brushed stainless steel as per drawing LA-LD-L29-3652, wall mounted - LEVEL 29 HOTEL | 15 | m | 550 | 8250 |  |  |  |  | 0 |  | 0 | 0 | 0
25 | Handrail 900 mm high, brushed stainless steel as per drawing LA-LD-L29-3653 - LEVEL 29 HOTEL | 15 | m | 920 | 13800 |  |  |  |  | 0 |  | 0 | 0 | 0
26 | Handrail 900 mm high, brushed stainless steel as per drawing LA-LD-L29-3654 - LEVEL 29 HOTEL | 15 | m | 2500 | 37500 |  |  |  |  | 0 |  | 0 | 0 | 0
GABION WALLS
D | Fabrication, Supply and Installation of galvanized mild steel mesh to gabion wall to be made of Ф4 mm thick wire mesh, 100 x 50 mm thick opening with galvanized mild steel brackets; all as per the submitted & approved sample. | 280 | m2 | 825 | 231000 |  |  |  |  | 0 |  | 0 | 0 | 0
1 | Structural calculation - if required | 1 | LS | 18000 | Rate only |  |  |  |  | 0 |  | 0 | 0 | 0
E | AGREED VARATIONS
1 | Supply and Installation of decorative fins to hotel and residential tower | 1 | Sum | 1650000 | 1650000 | 46% | 39% | 85% | 0.46 | 0.39 | 0.85 | 759000 | 643500 | 1402500
2 | Supply and Installation of pergola at L29 | 1 | Sum | 93750 | 93750 |  |  |  |  | 0 |  | 0 | 0 | 0 | 0.34352
3 | Supply and Installation of stainless steel ladders to swimming pools | 1 | Sum | 15000 | 15000 | 50% | 50% | 100% | 0.5 | 0.5 | 1 | 7500 | 7500 | 15000
4 | Supply and Installation of stainless shower to L4 and L29 | 1 | Sum | 29750 | 29750 |  |  |  |  | 0 |  | 0 | 0 | 0
-0.4
| Total Amount [AED] |  |  |  | 3330440 | [6 empty] | 888743.9 | 698118.5 | 1586862.4
Note on L55: Himal Kosala: Material @ site
Note on L59: Himal Kosala: Material @ site
Note on L63: Himal Kosala: Material @ site
Note on L65: Himal Kosala: Material @ site
Note on L68: Himal Kosala: Material @ site

## T1 - VO additional Agreed Varia
PLOT 18 - DORCHESTER HOTEL | [9 empty] | 2023-01-30
PAYMENT APPLICATION
PACKAGE: ADDITIONAL AGREED VARIATIONS | [9 empty] | Table 2
Item | DESCRIPTION | Qty | Unit | Rate | Amount (Dhs.) |  | Certified Quantity |  |  | Certified Amount [AED]
[6 empty] | Total Amount each item | Previous | This Month | Work Completed | Previous | This Month | Amount Claimed (AED)
1 | WA ref. PS001R1 & SI ref. E11/K108/SK/dm/009 R1 dated 26-Jun-2022 & Quotation ref. AMI/QTN/22/4912 dated 22-Jun-2022. Supply and Installation of Hotel Roof Deck cabana. |  |  |  |  | 473000
A | Fabrication, supply and installation of Steel Structure for the Cabana. Size 16.8 mtr. (L) x 8.52 mtr. (W) x 3.575 mtr. (H) as per your drawings ref. A-4014 & S-2335 | 1 | No. | 116000 | 116000 |  |  | 1 | 1 | 0 | 116000 | 116000 | 473000
B | Fabrication, supply and installation of Aluminum Frame to support the cladding for the Cabana of size 16.8 mtr (L) x 8.5 mtr (W). | 1 | No. | 82500 | 82500 |  |  | 1 | 1 | 0 | 82500 | 82500
C | Fabrication, supply and installation of ACP/m2 Cladding 4 mm thick for Cabana to upper Roof, roof edge boundary and internal sides of Roof openings. Approximate Area (180 m2). | 1 | No. | 111500 | 111500 |  |  | 0 |  | 0 | 0 | 0
D | Fabrication, supply, and installation of 1.2 mm thick Water ripple Stainless steel Grade 316 panels cladding for Cabana bottom roof ONLY, approximate Area (130 m2). - As per the supplier from Omniyat and consultant with the same details received from supplier. Client/ Consultant to choose the panels and design from supplier limitations and availability. Payment to this item as per the supplier condition. | 1 | No. | 146000 | 146000 |  |  | 0 |  | 0 | 0 | 0
E | Design and Structural Calculation of Steel Structure & connections covered the following. - Preparing the necessary analysis model for the steel structure design. - Design the section as per American standard. - Design all connections; Steel/Steel and Steel/Concrete. - Prepare the design calculations sheets. - Prepare Sketches for the design of section and connections and the Shop drawings approval. | 1 | LS | 17000 | 17000 |  | 1 | 0 | 1 | 17000 | 0 | 17000
2 | WA ref. PS08 R0 & SI ref. E11/K108/SK/dm/027 dated 10-Jun-2022 & Quotation ref. AMI/QTN/22/4925 dated 30-Jun-2022 Supply and Installation of Steel Plates to the Shaft openings |  |  |  |  | 429331.25 | [6 empty] | 429331.25
A | Shaft opening at Level 18 - Grid V-U (Elevation W41)
| 25 mm and 35 mm thick plates | 6.4 | MT | 19925 | 127520 |  | 6.4 | 0 | 6.4 | 127520 | 0 | 127520
| M36 Grade 10.9 bolts and nuts for outside plates 600 mm Length - Supply and installation. | 116 | Nos. | 330 | 38280 |  | 116 | 0 | 116 | 38280 | 0 | 38280
B | Shaft opening at Level 18 - near to Grid T (Elevation W41)
| 25 mm and 35 mm thick plates | 2.52 | MT | 19925 | 50211 |  | 2.52 | 0 | 2.52 | 50211 | 0 | 50211
| M36 Grade 10.9 bolts and nuts for outside plates 600 mm Length - Supply and installation. | 42 | Nos. | 330 | 13860 |  | 103 | 0 | 103 | 33990 | 0 | 33990
C | Shaft opening at Level 18 - near to Grid T (Elevation W41A)
| 25 mm and 35 mm thick plates | 2.52 | MT | 19925 | 50211 |  | 2.52 | 0 | 2.52 | 50211 | 0 | 50211
| M36 Grade 10.9 bolts and nuts for outside plates 600 mm Length - Supply and installation. | 42 | Nos. | 330 | 13860 |  | 103 | 0 | 103 | 33990 | 0 | 33990
D | Shaft opening at Level 28 - Grid V-U (Elevation W44)
| 25 mm and 35 mm thick plates | 0.88 | MT | 19925 | 17534 |  |  | 0 |  | 0 | 0 | 0
| M36 Grade 10.9 bolts and nuts for outside plates 600 mm Length - Supply and installation. | 48 | Nos. | 330 | 15840 |  |  | 0 |  | 0 | 0 | 0
E | Shaft opening at Shaft at Level 28 - Grid V-U (Elevation W44A)
| 25 mm and 35 mm thick plates | 0.88 | MT | 19925 | 17534 |  |  | 0 |  | 0 | 0 | 0
| M36 Grade 10.9 bolts and nuts for outside plates 600 mm Length - Supply and installation. | 48 | Nos. | 330 | 15840 |  |  | 0 |  | 0 | 0 | 0
F | Shaft opening at Shaft at Level 5
| 25 mm and 35 mm thick plates | 2.65 | MT | 19925 | 52801.25 |  | 2.65 | 0 | 2.65 | 52801.25 | 0 | 52801.25
| M36 Grade 10.9 bolts and nuts for outside plates 600 mm Length - Supply and installation. | 48 | Nos. | 330 | 15840 |  | 40 | 0 | 40 | 13200 | 0 | 13200
Note: - Any useful material will found at the site to be used and submitted as deduction from our payment as agreed and minuted at the Minutes no. 3 dated 08.06.2022. item no. 6.1. - The cost of fabricated useful materials will be provided with a breakdown and to be agreed at due courses.
3 | As per our email dated 21.01.2023 for the lastest revised Quotation ref. AMI/QTN/23/5159 dated 21.01.2023 and your WA ref. PS08 R0 & SI ref. E11/K108/SK/dm/029 dated 10-Jun-2022 & Quotation ref. AMI/QTN/22/4924 dated 30-Jun-2022 Supply and Installation of Slab Extensions. |  |  |  |  | 990726.5005 | [6 empty] | 1045111.762
Residence Tower
A | Deck slab at Level - 10
| Fabrication, primer painting and supply of steel work. | 4385.48 | Kg. | 16.95 | 74333.886 |  | 2285 | 0 | 2285 | 38730.75 | 0 | 38730.75
| Supply, and fixing of deck sheet | 54.825 | m2 | 225 | 12335.63 |  |  | 0 |  | 0 | 0 | 0
| Supply and apply of 2 hours intumescent fire rating to steel beams (water based). | 66.94 | m2 | 380 | 25437.2 |  | 65.88 | 0 | 65.88 | 25034.4 | 0 | 25034.4
B | Deck slab at Level - 18
| Fabrication, primer painting and supply of steel work. | 3919.75 | Kg. | 16.95 | 66439.7625 |  | 2030 | 0 | 2030 | 34408.5 | 0 | 34408.5
| Supply, and fixing of deck sheet | 59.125 | m2 | 225 | 13303.13 |  |  | 0 |  | 0 | 0 | 0
| Supply and apply of 2 hours intumescent fire rating to steel beams (water based). | 69.74 | m2 | 380 | 26501.2 |  | 51.19 | 0 | 51.19 | 19452.2 | 0 | 19452.2
C | Deck slab at Levels - 23, 24, 25
| Fabrication, primer painting and supply of steel work. | 11698.2 | Kg. | 16.95 | 198284.49 |  | 6708 | 0 | 6708 | 113700.6 | 0 | 113700.6
| Supply, and fixing of deck sheet | 133.77 | m2 | 225 | 30098.25 |  |  | 0 |  | 0 | 0 | 0
| Supply and apply of 2 hours intumescent fire rating to steel beams (water based). | 207.87 | m2 | 380 | 78990.6 |  | 153.57 | 0 | 153.57 | 58356.6 | 0 | 58356.6
D | Deck slab at Levels - 29 & 30
| Fabrication, primer painting and supply of steel work. | 3899.4 | Kg. | 16.95 | 66094.83 |  | 2236 | 0 | 2236 | 37900.2 | 0 | 37900.2
| Supply, and fixing of deck sheet | 116.7 | m2 | 225 | 26257.5 |  |  | 0 |  | 0 | 0 | 0
| Supply and apply of 2 hours intumescent fire rating to steel beams (water based). | 69.29 | m2 | 380 | 26330.2 |  | 51.19 | 0 | 51.19 | 19452.2 | 0 | 19452.2
Hotel Tower
E | Deck slab at Levels - 17
| Fabrication, primer painting and supply of steel work. | 3193.19 | Kg. | 16.95 | 54124.5705 |  | 180 | 0 | 180 | 3051 | 0 | 3051
| Supply, and fixing of deck sheet | 35.853 | m2 | 225 | 8066.93 |  |  | 0 |  | 0 | 0 | 0
| Supply and apply of 2 hours intumescent fire rating to steel beams (water based). | 58.14 | m2 | 380 | 22093.2 |  |  | 0 |  | 0 | 0 | 0
F | Deck slab at Levels - 24 (Material On Site)
| Fabrication, primer painting and supply of steel work. (MOS = 3193.19 kg x 70% =2,235.23 kg.) | 3193.19 | Kg. | 16.95 | 54124.5705 |  | 180 | 1735.914 | 1915.914 | 3051 | 29423.7423 | 32474.7423 |  | 3193.19 | 60% | 1915.914
| Supply, and fixing of deck sheet (MOS = 35.85 m2 x 70% = 25.10 m2) | 35.853 | m2 | 225 | 8066.93 |  |  | 21.5118 | 21.5118 | 0 | 4840.158 | 4840.158
| Supply and apply of 2 hours intumescent fire rating to steel beams (water based). | 58.14 | m2 | 380 | 22093.2 |  |  | 34.884 | 34.884 | 0 | 13255.92 | 13255.92
G | Deck slab at Levels - 28 (Material On Site)
| Fabrication, primer painting and supply of steel work. (MOS = 3,213.87 kg x 70% = 2,249.71 kg.) | 3213.87 | Kg. | 16.95 | 54475.0965 |  | 180 | 1748.322 | 1928.322 | 3051 | 29634.0579 | 32685.0579
| Supply, and fixing of deck sheet (MOS = 35.63 m2 x .70% = 24.94 m2.) | 35.631 | m2 | 225 | 8016.98 |  |  | 21.3786 | 21.3786 | 0 | 4810.188 | 4810.188
| Supply and apply of 2 hours intumescent fire rating to steel beams (water based). | 58.14 | m2 | 380 | 22093.2 |  |  | 34.884 | 34.884 | 0 | 13255.92 | 13255.92
H | Deck slab at Levels - 29 (Material On Site)
| Fabrication, primer painting and supply of steel work. (MOS = 3717.11 kg x 70% = 2,601.98 kg.) | 3717.11 | Kg. | 16.95 | 63005.0145 |  | 1824 | 777.977 | 2601.977 | 30916.8 | 13186.7101 | 44103.5101
| Supply, and fixing of deck sheet (MOS = 35.85 m2 x .70% = 25.10 m2.) | 35.853 | m2 | 225 | 8066.93 |  |  | 25.0971 | 25.0971 | 0 | 5646.851 | 5646.851
| Supply and apply of 2 hours intumescent fire rating to steel beams (water based). | 58.14 | m2 | 380 | 22093.2 |  | 48.25 | 9.89 | 58.14 | 18335 | 3758.2 | 22093.2
H.1 | Additional Deck slab at Levels - 29A (Material On Site)
| Fabrication, primer painting and supply of steel work. (MOS = 3208.57 kg x 70% = 2,246 kg.) | 3208.57 | Kg. | 16.95 | 54385.2615 |  |  | 2245.999 | 2245.999 | 0 | 38069.683 | 38069.683
| Supply, and fixing of deck sheet (MOS = 35.85 m2 x .70% = 25.10 m2.) | 35.85 | m2 | 225 | 8066.25 |  |  | 25.095 | 25.095 | 0 | 5646.375 | 5646.375 | 22093.2
| Supply and apply of 2 hours intumescent fire rating to steel beams (water based). | 58.14 | m2 | 380 | 22093.2 |  |  | 58.14 | 58.14 | 0 | 22093.2 | 22093.2
H.1 | Additional Deck slab at Levels - 12
| Fabrication, primer painting and supply of steel work. | 3207.35 | Kg. | 16.95 | 54364.5825 |  |  | 0 |  | 0 | 0 | 0
| Supply, and fixing of deck sheet | 35.85 | m2 | 225 | 8066.25 |  |  | 0 |  | 0 | 0 | 0 | 29237.2
| Supply and apply of 2 hours intumescent fire rating to steel beams (water based). | 76.94 | m2 | 380 | 29237.2 |  |  | 0 |  | 0 | 0 | 0
4 | WA ref. PS08 R0 & SI ref. E11/K108/KD/dm/037 dated 16-Jun-2022 & Quotation ref. AMI/QTN/22/4905 dated 20-Jun-2022 Supply and Installation of Stainless Steel handrails at Level 4 Swimming pool - 5 L.M |  |  |  |  | 4600 | [6 empty] | 4600
A | Fabrication, supply and installation of Brushed Stainless-Steel Handrails at Level 4 Swimming pool as per our drawing no. AMI-AX-SD-L4-00108_00. Note: Similar to the Contract unit rate. | 5 | L.M | 920 | 4600 |  | 5 | 0 | 5 | 4600 | 0 | 4600
5 | WA ref. PS08 R0 & SI ref. E11/K108/SC/dm/039 dated 21-Jun-2022 & Quotation ref. AMI/QTN/22/4910 dated 22-Jun-2022 Supply and Installation of Canopy in Level 10 Residential Building. |  |  |  |  | 89500 | [6 empty] | 89500
A | Fabrication, Supply, and Installation of Painted Mild Steel Structural to Canopy as per your drawing no. S-9102_Rev.0. L10 Size: 20685 x 4917 mm | 1 | No. | 77500 | 77500 |  |  | 0 |  | 0 | 0 | 0
B | Structural Calculation | 1 | L/S | 12000 | 12000 |  | 1 | 0 | 1 | 12000 | 0 | 12000
6 | WA ref. PS08 R1 & SI ref. E11/K108/SC/dm/066 dated 18-Jul-2022 & Quotation ref. AMI/QTN/22/4975 dated 3-Aug-2022 Hotel - Level 5 Core wall strengthening / Epoxy Painted Mild Steel UB - 1 No. |  |  |  |  | 9900 | [6 empty] | 9900
A | Fabrication, Supply, and Installation of Epoxy Painted Mild Steel UB-203 x 133 x 30 kg Vertical beam, 2800 mm height with cutting and welding of the existing horizontal beam. Note: Any Structural Calculation not included. | 1 | No. | 9900 | 9900 |  | 1 | 0 | 1 | 9900 | 0 | 9900
7 | WA ref. PS08 R1 & SI ref. E11/K108/PK/dm/073 dated 29-Jul-2022 & Quotation ref. AMI/QTN/22/4977 dated 03-Aug-2022 Powder Coated Aluminum Planter Box at level 04 to be made of 5 mm thick Aluminum Sheet - 1 No. |  |  |  |  | 8250 | [6 empty] | 8250
A | Fabrication, Supply, and Installation of Additional 5 mm thick Powder Coated Aluminum Planter box for Level 04. Note: The used Unit rate as per the agreed contract. | 1 | No. | 8250 | 8250 |  |  | 0 |  | 0 | 0 | 0
8 | WA ref. PS08 R0 & SI ref. E11/K108/SC/dm/128 dated 23-Aug-2022 & Quotation ref. AMI/QTN/22/4913 dated 23-Jun-2022 Design Services for the Steel structure works & Connections for Additional works. |  |  |  |  | 35750 | [6 empty] | 35750
Design and Structural Calculation of Steel Structure & connections for covered the following. - Preparing the necessary analysis model for the steel structure design. - Design the section as per American standard. - Design all connections; Steel/Steel and Steel/Concrete. - Prepare the design calculations sheets. - Prepare Sketches for the design of section and connections and the Shop drawings approval.
| Slab Deck (10 Floors) | 1 | L/S | 16500 | 16500 |  | 1 | 0 | 1 | 16500 | 0 | 16500
| View Deck canopy | 1 | L/S | 14500 | 14500 |  | 1 | 0 | 1 | 14500 | 0 | 14500
| Hedge Balustrade | 1 | L/S | 4750 | 4750 |  | 1 | 0 | 1 | 4750 | 0 | 4750
9 | As per our email dated 19.01.2023 for the lastest revised Quotation ref. AMI/QTN/23/5158 dated 19.01.2023 and WA ref. PS08 R0 & SI ref. E11/K108/SC/dm/128 dated 23-Aug-2022 & Quotation ref. AMI/QTN/22/4926 dated 30-Jun-2022 Residential Canopy Steel Work at L32 |  |  |  |  | 539782.9725 | [6 empty] | 539782.9725
A | Fabrication, primer painting and supply of steel work. | 25276.19 | Kg. | 17.75 | 448652.3725 |  | 11266.5 | 11482.071 | 22748.571 | 199980.375 | 203806.7602 | 403787.1352
B | Supply, and fixing of deck sheet | 30 | m2 | 245 | 7350 |  |  | 27 | 27 | 0 | 6615 | 6615
C | Supply and apply of 2 hours intumescent fire rating to steel beams (water based). | 178.37 | m2 | 380 | 67780.6 |  | 60 | 100.533 | 160.533 | 22800 | 38202.54 | 61002.54
D | Design and Structural Calculation of Steel Structure & connections for covered the following. - Preparing the necessary analysis model for the steel structure design. - Design the section as per American standard. - Design all connections; Steel/Steel and Steel/Concrete. - Prepare the design calculations sheets. - Prepare Sketches for the design of section and connections and the Shop drawings approval. | 1 | L/S | 16000 | 16000 |  | 1 | 0 | 1 | 16000 | 0 | 16000
10 | WA ref. PS08 R0 & SI ref. E11/K108/SC/dm/128 dated 23-Aug-2022 & Quotation ref. AMI/QTN/22/4955 dated 21-Jul-2022 Fire Testing & Certification for the Aluminum Architectural Decorative Fins. |  |  |  |  | 107099.5 | [6 empty] | 107099.5
A | 100% Advance Payment of Fire Testing & Certification for the Aluminum Architectural Decorative Fins. As per our notes and condition to submitted cost. | 1 | No. | 107099.5 | 107099.5 |  | 1 | 0 | 1 | 107099.5 | 0 | 107099.5
11 | WA ref. PS08 R0 & SI ref. E11/K108/SC/dm/128 dated 23-Aug-2022 & Quotation ref. AMI/QTN/22/4958 dated 23-Jul-2022 Powder Coated Aluminum Coping cover above sliding gate rail - 2 Nos. |  |  |  |  | 4500 | [6 empty] | 4500
| Fabrication, supply and installation for Powder Coated Aluminum coping cover above sliding gate rail to be made of 4 mm thick Aluminum Sheet as per your drawing no. KCE-SK-0001 Rev. 0. Size: 320 mm (Width) x 3560 mm (Length). | 2 | Nos. | 2250 | 4500 |  |  | 0 |  | 0 | 0 | 0
12 | WA ref. PS08 R1 & SI ref. E11/K108/SC/dm/128 dated 23-Aug-2022 & Quotation ref. AMI/QTN/22/4981 dated 08-Aug-2022 Stainless Steel Gabion Wall at Hotel - Ground floor instead of Galvanized Mild Steel mesh. |  |  |  |  | 823000 | [6 empty] | 805000
A | As per your RFI - Fabrication, Supply, and Installation of Stainless-Steel Mesh to Gabion Wall to be made of Ф 4 mm thick wire mesh, 50 x 50 mm thick opening with Stainless Steel brackets. Sq.mtr. 280 m2 Note: - Any stone materials not included for both supply and installation (by others). | 280 | m2 | 2875 | 805000 |  |  | 0 |  | 0 | 0 | 0
B | Structural Calculation – If required. | 1 | L/S | 18000 | 18000 |  | 1 | 0 | 1 | 18000 | 0 | 18000
13 | WA ref. PS08 R1 & SI ref. E11/K108/SC/dm/128 dated 23-Aug-2022 & Quotation ref. AMI/QTN/22/4974 dated 02-Aug-2022 Stainless Steel Sheet Screen Decorative at level 17 - C002 Bronze mirror water ripple. |  |  |  |  | 289250 | [6 empty] | 289250
A | Fabrication, supply and installation of 1.2 mm thick Stainless steel sheet screen, decorative – C002 Bronze mirror. Water ripple C002 finish to Level 17. C002 to be as per the attached photos & sketches received from the source of China supplier with normal Stainless steel angle supports backside. Height = 1100 mm – 1500 mm | 130 | m2 | 2225 | 289250 |  |  | 0 |  | 0 | 0 | 0
14 | As per Request for Information (RFI) ref. KCE-LX-RFI-PW-00140 dated Rev.00 & Aconex mail ref. KCE-TRANSMIT-001057 dated 07-Sep-2022 & Quotation ref. AMI/QTN/22/5024 dated 08-Sep-2022 Request to change Aluminum Cladding from Agreed thickness in the Contract of 5 mm thick to new thickness of 10mm thick. |  |  |  |  | 852470
METAL PLANTER BOX
Supply & Installation of Planter Box
1 | Planter box 1200 x 1200 x 1335 mm as per Sketch no. AMI-SK-003_01 to be made of 10 mm thick Powder Coated Aluminum Sheet - GROUND LEVEL | 12 | Nos. | 11200 | 134400 |  | 12 | 0 | 12 | 134400 | 0 | 134400
2 | Planter box 1000 x 1000 x 1650 mm, as per Sketch no. AMI-SK-003_01 to be made of 10 mm thick Powder Coated Aluminum Sheet - LEVEL 4 RESIDENTIAL | 38 | Nos. | 11550 | 438900 |  | 3 | 16 | 19 | 34650 | 162855 | 197505
3 | Raised Planter 8860 x 750 x 620 mm, as per Sketch no. AMI-SK-003_01 to be made of 10 mm thick Powder Coated Aluminum Sheet - LEVEL 04 HOTEL. | 1 | No. | 20850 | 20850 |  |  | 0 |  | 0 | 0 | 0
4 | Raised planter 5530 x 500 x 620 mm, as per Sketch no. AMI-SK-003_01 to be made of 10 mm thick Powder Coated Aluminum Sheet - LEVEL 04 HOTEL. | 1 | No. | 13100 | 13100 |  |  | 0 |  | 0 | 0 | 0
5 | Raised planter 3500 x 1300 / 500 x 620 mm, as per Sketch no. AMI-SK-003_01 to be made of 10 mm thick Powder Coated Aluminum Sheet - LEVEL 04 HOTEL. | 1 | No. | 10450 | 10450 |  |  | 0 |  | 0 | 0 | 0
6 | Raised planter 1320 x 1300/ 800 x 620 mm, as per Sketch no. AMI-SK-003_01 to be made of 10 mm thick Powder Coated Aluminum Sheet - LEVEL 04 HOTEL. | 1 | No. | 5670 | 5670 |  |  | 0 |  | 0 | 0 | 0
7 | Raised planter 5860 x 500 x 620 mm, as per Sketch no. AMI-SK-003_01 to be made of 10 mm thick Powder Coated Aluminum Sheet - LEVEL 04 HOTEL. | 1 | No. | 13800 | 13800 |  |  | 0 |  | 0 | 0 | 0
8 | Raised planter 7000 x 500 x 620 mm, as per Sketch no. AMI-SK-003_01 to be made of 10 mm thick Powder Coated Aluminum Sheet - LEVEL 04 HOTEL. | 2 | Nos. | 16300 | 32600 |  |  | 0 |  | 0 | 0 | 0
9 | Raised planter 8730 x 1540 x 1170 mm, as per Sketch no. AMI-SK-003_01 to be made of 10 mm thick Powder Coated Aluminum Sheet - LEVEL 04 HOTEL. | 1 | No. | 42000 | 42000 |  |  | 0 |  | 0 | 0 | 0
10 | Planter on slab 4380 x 900 x 665 mm, as per Sketch no. AMI-SK-003_01 to be made of 10 mm thick Powder Coated Aluminum Sheet - LEVEL 24. | 1 | No. | 12250 | 12250 |  |  | 0 |  | 0 | 0 | 0
11 | Planter on slab 3600 x 600 x 665 mm, as per Sketch no. AMI-SK-003_01 to be made of 10 mm thick Powder Coated Aluminum Sheet - LEVEL 24. | 1 | No. | 9800 | 9800 |  |  | 0 |  | 0 | 0 | 0
12 | Planter on slab 7700 x 600 x 665 mm, as per Sketch no. AMI-SK-003_01 to be made of 10 mm thick Powder Coated Aluminum Sheet - LEVEL 24. | 1 | No. | 19250 | 19250 |  |  | 0 |  | 0 | 0 | 0
13 | Planter on slab 3600 x 600 x 665 mm, as per Sketch no. AMI-SK-003_01 to be made of 10 mm thick Powder Coated Aluminum Sheet - LEVEL 25. | 1 | No. | 9800 | 9800 |  |  | 0 |  | 0 | 0 | 0
14 | Planter on slab 7700 x 600 x 665 mm, as per Sketch no. AMI-SK-003_01 to be made of 10 mm thick Powder Coated Aluminum Sheet - LEVEL 25. | 1 | No. | 19250 | 19250 |  |  | 0 |  | 0 | 0 | 0
15 | Planter on slab 3600 x 600 x 665 mm, as per Sketch no. AMI-SK-003_01 to be made of 10 mm thick Powder Coated Aluminum Sheet - LEVEL 27. | 1 | No. | 9800 | 9800 |  |  | 0 |  | 0 | 0 | 0
16 | Planter on slab 7700 x 600 x 665 mm, as per Sketch no. AMI-SK-003_01 to be made of 10 mm thick Powder Coated Aluminum Sheet - LEVEL 27. | 1 | No. | 19250 | 19250 |  |  | 0 |  | 0 | 0 | 0
17 | Planter on slab 4400 x 900 x 665 mm, as per Sketch no. AMI-SK-003_01 to be made of 10 mm thick Powder Coated Aluminum Sheet - LEVEL 29. | 1 | No. | 12250 | 12250 |  |  | 0 |  | 0 | 0 | 0
18 | Planter on slab 3600 x 600 x 665 mm, as per Sketch no. AMI-SK-003_01 to be made of 10 mm thick Powder Coated Aluminum Sheet - LEVEL 29. | 1 | No. | 9800 | 9800 |  |  | 0 |  | 0 | 0 | 0
19 | Planter on slab 7700 x 600 x 665 mm, as per Sketch no. AMI-SK-003_01 to be made of 10 mm thick Powder Coated Aluminum Sheet - LEVEL 29. | 1 | No. | 19250 | 19250 |  |  | 0 |  | 0 | 0 | 0
15 | SI ref. E11/K108/SC/dm/262 dated 29-Sep-2022 & Quotation ref. AMI/QTN/22/5064 dated 12-Oct-2022 |  |  |  |  | 250950
Fabrication, supply and installation of Top and Bottom Runners Galvanized Mild Steel Structure behind the Aluminum Fins at Level 05 as per your Sketch at your SI ref. E11/K108/SC/dm/262.
| 1. Residential Area | 105 | L.M | 1195 | 125475 |  | 82 | 0 | 82 | 97990 | 0 | 97990
| 2. Hotel Tower | 105 | L.M | 1195 | 125475 |  | 94.5 | 10.5 | 105 | 112927.5 | 12547.5 | 125475
16 | As per Quotation ref. AMI/QTN/22/5065 dated 12-Oct-2022 Supply and Installation of Additional level for External Façade Deck Slabs at Hotel Level 12 |  |  |  |  | 75212.13
Hotel Tower
1 | Deck slab at Levels - 12
| Fabrication, primer painting and supply of steel work. | 2236.4602 | Kg. | 16.95 | 37908 |  |  | 0 |  | 0 | 0 | 0
| Supply, and fixing of deck sheet | 35.853 | m2 | 225 | 8066.93 |  |  | 0 |  | 0 | 0 | 0
| Supply and apply of 2 hours intumescent fire rating to steel beams (water based). | 76.94 | m2 | 380 | 29237.2 |  |  | 0 |  | 0 | 0 | 0
17 | As per Quotation ref. AMI/QTN/22/5067 dated 12-Oct-2022 Supply and Installation of Additional level for External Façade Deck Slabs at Hotel Level 29A |  |  |  |  | 68068.13
Hotel Tower
1 | Deck slab at Levels - 29A
| Fabrication, primer painting and supply of steel work. | 2236.4602 | Kg. | 16.95 | 37908 |  |  | 0 |  | 0 | 0 | 0
| Supply, and fixing of deck sheet | 35.853 | m2 | 225 | 8066.93 |  |  | 0 |  | 0 | 0 | 0
| Supply and apply of 2 hours intumescent fire rating to steel beams (water based). | 58.14 | m2 | 380 | 22093.2 |  |  | 0 |  | 0 | 0 | 0
18 | As per Quotation ref. AMI/QTN/22/5074 dated 18-Oct-2022 Modification of the External Façade Deck Slabs |  |  |  |  | 159079.21
1 | Modification for each extended steel beam | 103 | Nos. | 1006.59 | 103678.77 |  | 46.35 | 3.65 | 50 | 46655.4465 | 3674.0535 | 50329.5
2 | Modification for each Stub | 103 | Nos. | 384.52 | 39605.56 |  | 77.25 | 25.75 | 103 | 29704.17 | 9901.39 | 39605.56
3 | Modification for each horizontal beam | 1 | L/S | 5794.88 | 5794.88 |  |  | 0 |  | 0 | 0 | 0
4 | Fire proofing for the additional items. | 1 | L/S | 10000 | 10000 |  | 0.8 | 0.2 | 1 | 8000 | 2000 | 10000
19 | Site Instruction ref. E11/K108/SK/dm/413 dated 09-Nov-2022 & E11/K108/SK/dm/541 dated 20-Dec-2022 Quotation ref. AMI/QTN/22/5090 dated 02-Nov-2022 Supply and Apply of 2 hours Intumescent fire rating to the additional steel plate support to the existing structure in Hotel & Residential area at Level 05 - Additional Work. |  |  |  |  | 15750
| Plate Size: 175 x 195 x 10 mm thick | 1 | L/S | 15750 | 15750 |  | 0.85 | 0.05 | 0.9 | 13387.5 | 787.5 | 14175
Quantitiy: 170 nos.
20 | As per Quotation ref. AMI/QTN/22/5123 dated 29-Nov-2022 Painted Mild Steel Hedge Balustrade Request to change of full design for the Hedge Balustrade at Hotel and Residential Multilvel as per RFI ref. KCE-LX-RFI-ML-00229_Rev. 00 was received in Aconex mail no. KCE-TRANSMIT-001951 dated 05-Nov-2022. |  |  |  |  | 574781.32
1 | EC-10-A Hedge balustrade 1200 mm high as per drawing LA-LD-GL-3509, GROUND LEVEL | 50 | L.M | 1569 | 78450 |  |  | 50 | 50 | 0 | 78450 | 78450
2 | EC-07-A, 1200 mm high hedge balustrade, LEVEL 02 | 71.34 | L.M | 1569 | 111932.46 |  |  | 0 |  | 0 | 0 | 0
3 | Type EC-05-A, hedge balustrade, 1600 mm high, LEVEL 04 RESIDENTIAL | 87.94 | L.M | 2092 | 183970.48 |  | 35.18 | 68.82 | 104 | 73596.56 | 122214.64 | 195811.2
4 | EC-07-A Hedge Balustrade aluminum, RAL7016 anthracite grey, 1300mm high - LEVEL 04 HOTEL | 25.62 | L.M | 1699 | 43528.38 |  |  | 25.62 | 25.62 | 0 | 39175.542 | 39175.542
5 | EC-05-A Hedge Balustrade, 1200 mm high, LEVEL 10 RESIDENTIAL | 50 | L.M | 1569 | 78450 |  |  | 0 |  | 0 | 0 | 0
6 | EC-04-A Hedge Balustrade, 1200 mm high, LEVEL 26 RESIDENTIAL | 50 | L.M | 1569 | 78450 |  |  | 0 |  | 0 | 0 | 0
21 | As per Quotation ref. AMI/QTN/22/5039 dated 14-Sep-2022 Painted Mild Steel View Deck at Hotel Level 29 Request to change the full design and loading for the View deck at Hotel Level 29 and additional platform 6 mm thick Chequered plate as per RFI ref. KCE-AX-RFI-L29-00052_00. |  |  |  |  | 205320.53
1 | New Rate for the Fabrication, Supply and Installation of View deck at Hotel Level 29 and additional platform 6 mm thick Chequered plate | 1 | No. | 205320.53 | 205320.53 |  | 0.7 | 0 | 0.7 | 143724.371 | 0 | 143724.371
22 | As per Quotation ref. AMI/QTN/22/5136 dated 12-Dec-2022 Supply and Apply of Water based intumescent including Top coat View Deck at Hotel Level 29 Request to supply and apply of water based intumescent including Topcoat for View Deck at Hotel Level 29. |  |  |  |  | 48640
| - Product : 1200 WF + Top coat - Fire Rating : 120 mins. | 128 | m2 | 380 | 48640 |  |  | 0 | 0 | 0 | 0 | 0
23 | As per Quotation ref. AMI/QTN/22/5141 dated 14-Dec-2022 Request to Fabrication, supply and and installation of Galvanized Mild Steel Supports for the Slab Deck at Residential Level 24,25 and 29 |  |  |  |  | 59177.196
| Galvanized Mild Steel Supports for the Slab Deck at Residential Level 24,25 and 29 to be made of 200 x 150 x 6 mm thick Mild Steel Box and 150 x 90 x 9 mm thick Angle | 3491.28 | Kg | 16.95 | 59177.196 |  | 1047.38 | 2443.9 | 3491.28 | 17753.091 | 35506.3854 | 53259.4764
24 | Site Instruction ref. E11/K108/SC/dm/286 dated 11-Oct-2022 & Quotation ref. AMI/QTN/22/5143 dated 17-Dec-2022 |  |  |  |  | 49250
1 | Supply, supply, and installation of Stainless-steel Floor mounted Handrails with Brushed Finish as per approved drawing ref. AMI-AX-SD-L29-00139_00 to 00140_00, AMI-AX-SD-L29-00134_00 to 00135_00, AMI-AX-SD-L29-00138_00, AMI-AX-SD-L26-00153.
| 1. Roof Top Pool Level 29 | 18 | L.M | 1250 | 22500 |  |  | 0 |  | 0 | 0 | 0
| 2. Hotel Level 29, Stair ST-01 | 3 | L.M | 1250 | 3750 |  |  | 0 |  | 0 | 0 | 0
| 3. Hotel Level 29, Stair ST-02 | 3 | L.M | 1250 | 3750 |  |  | 0 |  | 0 | 0 | 0
| 4. Hotel Level 29 Stair ST-04 | 4 | L.M | 1250 | 5000 |  |  | 0 |  | 0 | 0 | 0
| 5. Residential Pool Level 26 | 3 | L.M | 1250 | 3750 |  |  | 0 |  | 0 | 0 | 0
2 | Supply, supply, and installation of Stainless-steel Pool Ladders with Brushed finish as per the approved drawing ref. AMI-AX-SD-L29-00129_00 to 00130_00, AMI-AX-SD-L10-00152_00 | [6 empty] | 0 |  | 0 | 0 | 0
| 1. Hotel Roof Top Level 29 Size: 610 mm (W) x 1500 mm (H) | 1 | No. | 5250 | 5250 |  |  | 0 |  | 0 | 0 | 0
| 2. Penthouse Level 10 Size: 660 mm (W) x 1750 mm (H) | 1 | No. | 5250 | 5250 |  |  | 0 |  | 0 | 0 | 0
25 | As per Quotation ref. AMI/QTN/22/5177 dated 30-Jan-2023 and your SI ref. E11/K108/SC/AK/0591 dated 06.01.2023 Cost Breakdown for Engineering & Design Works. |  |  |  |  | 0
Engineering works such as Approval of Shop drawings, material submittals etc. work started on June 2022 until November 2022.
| AED 231,000.00 x 30% = AED 69,300.00 (i.e., values taken from original scope cost). | 1 | L/S | 69300 | 69300 |  |  | 0 | 0 | 0 | 0 | 0
| Design and Structural Calculation started on November 2022. | 1 | L/S | 18000 | 18000 |  |  | 0 | 0 | 0 | 0 | 0
| Total Amount [AED] |  |  |  | 6426901.483 | 6163388.739 |  |  |  | 1961562.0135 | 1097857.3166 | 3059419.33 | 3892405.8845
Note on M66: Himal Kosala: 60% only
Note on M67: Himal Kosala: 60% only
Note on M68: Himal Kosala: 60% only
Note on M70: Himal Kosala: 60% only
Note on M71: Himal Kosala: 60% only
Note on M72: Himal Kosala: 60% only
Note on M101: Himal Kosala: only 90%
Note on M102: Himal Kosala: only 90%
Note on M103: Himal Kosala: only 90%
Note on P121: Himal Kosala: 90% only
Note on M161: Himal Kosala: 90% only
Note on P167: Himal Kosala: 90% only
Note on P168: Himal Kosala: 90% only
Note on P176: Himal Kosala: 90% only
Note on M190: Himal Kosala: Please provide the supporting
Note on M191: Himal Kosala: Calculation sheet attached, but need to recheck the rate and this scope