## Summary
No | Description | Previous | This Month | Cumulative
1 | Delivery (70%) | 119827.8655 | 31403.046 | 151230.9115
2 | Installation (15%) | 6246.612 | 0 | 6246.612
3 | Installation (15%) | 4994.9497 | 0 | 4994.9497
|  | 131069.4272 | 31403.046 | 162472.4732
| Advance Payment | 24449.21 | 0 | 24449.21
| Advance Payment on Variation | 34223.218 | 0 | 34223.218
Ddt
| Advance payment recovery (20%) | -26213.8855 | -6280.6092 | -32494.4946
|  | 163527.9698 | 25122.4368 | 188650.4066
| KCE Claim | 77105.922 | 92383.178 | 169489.1
| Difference | 86422.0478 | -67260.7412 | 19161.3066

## Measurements Summary
[11 empty] | Previous |  |  | Current |  |  | Cumulative
Floor | Door Type | Door Name | Qty | Rate | Amount | MIR | WIR | Delivery | Installation | Installation7 | Delivery8 | Installation9 | Installation10 | Delivery11 | Installation12 | Installation13 | Delivery14 | Installation15 | Installation16 | Remark | Column1
[11 empty] | 70% | 15% | 15% | 70% | 15% | 15% | 70% | 15% | 15%
GF | D-09a | LGF10 | 1 | 2653.285 | 2653.285 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
GF | D-01c | LGF122 | 1 | 1540.25 | 1540.25 | KCE-ID-MR-GF-R0 |  | 100% |  |  | 1078.175 | 0 | 0 | 0 | 0 | 0 | 1078.175 | 0 | 0
GF | I | LGF123 | 1 | 1540.25 | 1540.25 | IND-AX-MR-ML-00007 | IND-AX-WR-ML-00003 | 100% | 100% | 100% | 1078.175 | 231.0375 | 231.0375 | 0 | 0 | 0 | 1078.175 | 231.0375 | 231.0375
GF | D-01b | LGF125 | 1 | 1540.25 | 1540.25 | KCE-ID-MR-GF-00009 |  | 100% | 100% | 50% | 1078.175 | 231.0375 | 115.5187 | 0 | 0 | 0 | 1078.175 | 231.0375 | 115.5187 | No WIR
GF | D-01e | LGF13 | 1 | 1778.3 | 1778.3 | IND-AX-MR-ML-00014 |  | 100% |  |  | 0 | 0 | 0 | 1244.81 | 0 | 0 | 1244.81 | 0 | 0
GF | D-01c | LGF139 | 1 | 1540.25 | 1540.25 | IND-AX-MR-ML-00016 |  | 100% |  |  | 1078.175 | 0 | 0 | 0 | 0 | 0 | 1078.175 | 0 | 0
GF | AH-03 | LGF198 | 1 | 1374.9375 | 1374.9375 | KCE-AX-MR-ML-00067 |  | 100% | 100% | 50% | 962.4562 | 206.2406 | 103.1203 | 0 | 0 | 0 | 962.4562 | 206.2406 | 103.1203 | NoWIR
GF | D-01h | LGF51 | 1 | 2196.21 | 2196.21 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF | D-09a | LGF57 | 1 | 3855.4375 | 3855.4375 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF | D-01h | LGF58 | 1 | 2063.96 | 2063.96 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF | D-01d | LGF62 | 1 | 1599.7625 | 1599.7625 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF | D-01e | LGF64 | 1 | 1778.3 | 1778.3 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L01 | D-06e | L0108 | 1 | 1540.25 | 1540.25 | KCE-AX-MR-ML-00067 |  | 100% | 100% | 50% | 1078.175 | 231.0375 | 115.5187 | 0 | 0 | 0 | 1078.175 | 231.0375 | 115.5187 | No WIR
L01 | D-01c | L0109 | 1 | 1540.25 | 1540.25 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L02 | D-04a | L02118 | 1 | 1899.97 | 1899.97 | KCE-AX-MR-ML-00067 |  | 100% | 100% | 50% | 1329.979 | 284.9955 | 142.4977 | 0 | 0 | 0 | 1329.979 | 284.9955 | 142.4977 | No WIR
L02 | D-01c | L0212 | 1 | 1540.25 | 1540.25 | IND-AX-MR-ML-00016 |  | 100% |  |  | 1078.175 | 0 | 0 | 0 | 0 | 0 | 1078.175 | 0 | 0
L02 | D-01c | L0213 | 1 | 1540.25 | 1540.25 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L02 | D-04a | L02120 | 1 | 1635.47 | 1635.47 | KCE-AX-MR-ML-00067 |  | 100% | 100% | 50% | 1144.829 | 245.3205 | 122.6603 | 0 | 0 | 0 | 1144.829 | 245.3205 | 122.6603 | No WIR
L02 | D-03b | L0220 | 1 | 2246.465 | 2246.465 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L03 | D-01c | L0304 | 1 | 1804.75 | 1804.75 | KCE-AX-MR-ML-00067 |  | 100% | 100% | 50% | 1263.325 | 270.7125 | 135.3562 | 0 | 0 | 0 | 1263.325 | 270.7125 | 135.3562 | No WIR
L03 | D-01c | L0318 | 1 | 1540.25 | 1540.25 | IND-AX-MR-ML-00017 |  | 100% |  |  | 0 | 0 | 0 | 1078.175 | 0 | 0 | 1078.175 | 0 | 0
L03 | D-01c | L0319 | 1 | 1540.25 | 1540.25 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L04 | D-01c | L0407 | 1 | 1540.25 | 1540.25 | IND-AX-MR-ML-00016 |  | 100% |  |  | 1078.175 | 0 | 0 | 0 | 0 | 0 | 1078.175 | 0 | 0
L04 | D-01c | L0444 | 1 | 1540.25 | 1540.25 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L04 | D-01c | L0447 | 1 | 1540.25 | 1540.25 | KCE-ID-MR-GF-R0 |  | 100% |  |  | 1078.175 | 0 | 0 | 0 | 0 | 0 | 1078.175 | 0 | 0
L04 | D-01c | L0448 | 1 | 1540.25 | 1540.25 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L05 | D-01c | L0503 | 1 | 1672.5 | 1672.5 | KCE-AX-MR-ML-00067 |  | 100% | 100% | 50% | 1170.75 | 250.875 | 125.4375 | 0 | 0 | 0 | 1170.75 | 250.875 | 125.4375 | No WIR
L05 | D-01c | L0506 | 1 | 1540.25 | 1540.25 | IND-AX-MR-ML-00016 |  | 100% |  |  | 1078.175 | 0 | 0 | 0 | 0 | 0 | 1078.175 | 0 | 0
L05 | D-01c | L0517 | 1 | 1540.25 | 1540.25 | KCE-ID-MR-GF-R0 |  | 100% |  |  | 1078.175 | 0 | 0 | 0 | 0 | 0 | 1078.175 | 0 | 0
L06 | D-01d | L06R13 | 1 | 1599.7625 | 1599.7625 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L07 | D-01c | L07R10 | 1 | 1540.25 | 1540.25 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L10 | D-03b | L10R22 | 1 | 1989.2387 | 1989.2387 | IND-AX-MR-ML-00014 |  | 100% |  |  | 0 | 0 | 0 | 1392.4671 | 0 | 0 | 1392.4671 | 0 | 0
L13 | D-01c | L14H09 | 1 | 1672.5 | 1672.5 | IND-AX-MR-ML-00007 | IND-AX-WR-ML-00003 | 100% | 100% | 100% | 1170.75 | 250.875 | 250.875 | 0 | 0 | 0 | 1170.75 | 250.875 | 250.875
L14 | D-01c | L15H09 | 1 | 1672.5 | 1672.5 | IND-AX-MR-ML-00007 | IND-AX-WR-ML-00003 | 100% | 100% | 100% | 1170.75 | 250.875 | 250.875 | 0 | 0 | 0 | 1170.75 | 250.875 | 250.875
L14 | D-01d | L15H10 | 1 | 1599.7625 | 1599.7625 | KCE/AX/MR/ML/00090 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L17 | D-03b | L18H01 | 1 | 2246.465 | 2246.465 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L17 | D-20b | L18H03 | 1 | 2246.465 | 2246.465 | KCE/AX/MR/ML/00090 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L17 | D-20b | L18H04 | 1 | 2378.715 | 2378.715 | KCE/AX/MR/ML/00090 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L17 | D-01g | L18H05 | 1 | 2148.6 | 2148.6 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L17 | D-01c | L18H09 | 1 | 1672.5 | 1672.5 | IND-AX-MR-ML-00007 | IND-AX-WR-ML-00003 | 100% | 100% | 100% | 1170.75 | 250.875 | 250.875 | 0 | 0 | 0 | 1170.75 | 250.875 | 250.875
L17 | D-03b | L18H20 | 1 | 2246.465 | 2246.465 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L17 | D-02e | L18H21 | 1 | 3438.85 | 3438.85 | KCE/AX/MR/ML/00090 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L18 | D-20b | L19H03 | 1 | 2246.465 | 2246.465 | KCE/AX/MR/ML/00090 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L18 | D-20b | L19H04 | 1 | 2378.715 | 2378.715 | IND-AX-MR-ML-00016 |  | 100% |  |  | 1665.1005 | 0 | 0 | 0 | 0 | 0 | 1665.1005 | 0 | 0
L18 | D-01g | L19H05 | 1 | 2148.6 | 2148.6 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L18 | D-03b | L19H06 | 1 | 2246.465 | 2246.465 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L18 | D-20b | L19H07 | 1 | 2378.715 | 2378.715 | IND-AX-MR-ML-00016 |  | 100% |  |  | 1665.1005 | 0 | 0 | 0 | 0 | 0 | 1665.1005 | 0 | 0
L18 | D-01c | L19H09 | 1 | 1672.5 | 1672.5 | IND-AX-MR-ML-00007 | IND-AX-WR-ML-00003 | 100% | 100% | 100% | 1170.75 | 250.875 | 250.875 | 0 | 0 | 0 | 1170.75 | 250.875 | 250.875
L18 | D-01g | L19H11 | 1 | 1849.715 | 1849.715 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L18 | D-01g | L19H12 | 1 | 1849.715 | 1849.715 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L18 | D-01g | L19H13 | 1 | 1849.715 | 1849.715 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L18 | D-01g | L19H15 | 1 | 1849.715 | 1849.715 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L18 | D-01c | L20H09 | 1 | 1672.5 | 1672.5 | IND-AX-MR-ML-00007 | IND-AX-WR-ML-00003 | 100% | 100% | 100% | 1170.75 | 250.875 | 250.875 | 0 | 0 | 0 | 1170.75 | 250.875 | 250.875
L23 | D-19a | L24R04 | 1 | 2949.525 | 2949.525 | KCE-ID-MR-GF-R0 |  | 100% |  |  | 2064.6675 | 0 | 0 | 0 | 0 | 0 | 2064.6675 | 0 | 0
L23 | D-01c | L24R12 | 1 | 1540.25 | 1540.25 | IND-AX-MR-ML-00017 |  | 100% |  |  | 0 | 0 | 0 | 1078.175 | 0 | 0 | 1078.175 | 0 | 0
L28 | D-03b | L29H06 | 1 | 2246.465 | 2246.465 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L28 | D-20b | L29H07 | 1 | 2378.715 | 2378.715 | IND-AX-MR-ML-00016 |  | 100% |  |  | 1665.1005 | 0 | 0 | 0 | 0 | 0 | 1665.1005 | 0 | 0 | No MIR
L28 | D-03b | L29H11 | 1 | 2246.465 | 2246.465 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L28 | D-01d | L29H12 | 1 | 1870.875 | 1870.875 | IND-AX-MR-ML-00016 |  | 100% |  |  | 1309.6125 | 0 | 0 | 0 | 0 | 0 | 1309.6125 | 0 | 0 | No MIR
L28 | D-04b | L29H14 | 1 | 1599.7625 | 1599.7625 | KCE/AX/MR/ML/00090 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L28 | D-01d | L29H16 | 1 | 1599.7625 | 1599.7625 | KCE/AX/MR/ML/00090 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L28 | D-01d | L29H43 | 1 | 1870.875 | 1870.875 | KCE/AX/MR/ML/00090 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L28 | D-01d | L29H44 | 1 | 1870.875 | 1870.875 | KCE/AX/MR/ML/00090 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L31 | D-03b | L32R06 | 1 | 2274.2375 | 2274.2375 | IND-AX-MR-ML-00017 |  | 100% |  |  | 0 | 0 | 0 | 1591.9662 | 0 | 0 | 1591.9662 | 0 | 0
B01 | D-14 | LB1227 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B01 | D-14 | LB1229 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF | D-04h | LGF04 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF | D-01h | LGF05 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF | D-02k | LGF06 | 1 | 450 | 450 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF | D-03d | LGF07 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF | D-09c | LGF47 | 1 | 450 | 450 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF | D-03b | LGF48 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF | D-03b | LGF49 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF | D-03a | LGF52 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF | D-09e | LGF53 | 1 | 450 | 450 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF | D-03d | LGF54 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF | D-03d | LGF55 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF | D-12c | LGF56 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF | D-02e | LGF71 | 1 | 450 | 450 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF | D-02e | LGF77 | 1 | 450 | 450 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L01 | D-03a | L0102 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L01 | D-01d | L0110 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L02 | D-03d | L0201 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L02 | D-05c | L0202 | 1 | 450 | 450 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L02 | D-05c | L0203 | 1 | 450 | 450 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L02 | D-05c | L0204 | 1 | 450 | 450 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L02 | D-03a | L0207 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L02 | D-03a | L0221 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L02 | D-01g | L0223 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L02 | D-01g | L0226 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L02 | D-01d | L0230 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L02 | D-01c | L0237 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L03 | D-03a | L0302 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L03 | D-03d | L0312 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L03 | D-01d | L0320 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L03 | D-01d | L0338 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L04 | D-01d | L0419 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L04 | D-03a | L0431 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L04 | D-01g | L0442 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L04 | D-03a | L0452 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L05 | D-03b | L0501 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L05 | D-02g | L0502 | 1 | 450 | 450 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L05 | D-01g | L0505 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L05 | D-01g | L0514 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L05 | D-03b | L0515 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L05 | D-01d | L0518 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L05 | D-01d | L0524 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L08 | D-01c | L08H08 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L10 | D-01c | L10H08 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L10 | D-01c | L10R23 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L11 | D-01c | L11H08 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L14 | D-01c | L15H08 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L17 | D-01c | L18H08 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L19 | D-01g | L20H05 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L20 | D-01g | L21H05 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L20 | D-01c | L21H08 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L20 | D-01c | L21H09 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L21 | D-01c | L22H09 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L22 | D-01c | L23H08 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L22 | D-01c | L23H09 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L23 | D-01c | L24H08 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L23 | D-01c | L24H09 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L23 | D-02d | L24R01 | 1 | 450 | 450 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L23 | D-01g | L24R05 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L23 | D-01c | L24R06 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L23 | D-03b | L24R21 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L23 | D-02d | L24R28 | 1 | 450 | 450 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L24 | D-01c | L25H09 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L25 | D-01c | L26H08 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L25 | D-01c | L26H09 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L26 | D-01c | L27H09 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L27 | D-01c | L28H08 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L27 | D-01c | L28H09 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L28 | D-01c | L29AH01 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L28 | D-01c | L29AH02 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L28 | D-01g | L29H05 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L28 | D-01c | L29H08 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L28 | D-01c | L29H09 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L28 | D-01g | L29H53 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L29 | D-01c | L30R07 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L30 | D-03a | L31H01 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L30 | D-01d | L31H04 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L30 | D-01c | L31R11 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L31 | D-03b | L32R01 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L31 | D-01g | L32R02 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L31 | D-01d | L32R04 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L31 | D-01g | L32R05 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L31 | D-03b | L32R07 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L31 | D-01g | L32R09 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L31 | D-01g | L32R10 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L31 | D-01d | L32R11 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L31 | D-01d | L32R12 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L31 | D-01c | L32R13 | 1 | 350 | 350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 154496.0487 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Variation
GF | D-03b | LGF16 | 1 | 2149.715 | 2149.715 | IND/AX/MR/ML/00015-00 |  | 100% |  |  | 1504.8005 | 0 | 0 | 0 | 0 | 0 | 1504.8005 | 0 | 0
GF | D-03b | LGF17 | 1 | 2149.715 | 2149.715 | IND/AX/MR/ML/00015-00 |  | 100% |  |  | 1504.8005 | 0 | 0 | 0 | 0 | 0 | 1504.8005 | 0 | 0
GF | D-04g | LGF21 | 1 | 1981.965 | 1981.965 | IND/AX/MR/ML/00015-00 |  | 100% |  |  | 1387.3755 | 0 | 0 | 0 | 0 | 0 | 1387.3755 | 0 | 0
GF | D-03b | LGF26 | 1 | 2281.965 | 2281.965 | IND/AX/MR/ML/00015-00 |  | 100% |  |  | 1597.3755 | 0 | 0 | 0 | 0 | 0 | 1597.3755 | 0 | 0
GF | D-03b | LGF27 | 1 | 2281.965 | 2281.965 | IND/AX/MR/ML/00015-00 |  | 100% |  |  | 1597.3755 | 0 | 0 | 0 | 0 | 0 | 1597.3755 | 0 | 0
GF | D-03d | LGF41 | 1 | 3162.75 | 3162.75 | IND/AX/MR/ML/00015-00 |  | 100% |  |  | 2213.925 | 0 | 0 | 0 | 0 | 0 | 2213.925 | 0 | 0
GF | D-03d | LGF42 | 1 | 2496.21 | 2496.21 | IND/AX/MR/ML/00015-00 |  | 100% |  |  | 1747.347 | 0 | 0 | 0 | 0 | 0 | 1747.347 | 0 | 0
GF | D-03d | LGF08 | 1 | 2353.38 | 2353.38 | IND/AX/MR/ML/00015-00 |  | 100% |  |  | 1647.366 | 0 | 0 | 0 | 0 | 0 | 1647.366 | 0 | 0
GF | D-12c | LGF78 | 1 | 2196.21 | 2196.21 | IND-AX-MR-ML-0014 |  | 80% |  |  | 0 | 0 | 0 | 1229.8776 | 0 | 0 | 1229.8776 | 0 | 0 |  | Until rate is finalized
L04 | D-03a | L0449 | 1 | 2156.9887 | 2156.9887 | IND-AX-MR-ML-00016 |  | 100% |  |  | 1509.8921 | 0 | 0 | 0 | 0 | 0 | 1509.8921 | 0 | 0
B01 | ELECTRIC CABINET | LB1206 | 1 | 4044.84 | 4044.84 | IND-AX-MR-ML-00012 |  | 100% |  |  | 2831.388 | 0 | 0 | 0 | 0 | 0 | 2831.388 | 0 | 0
B01 | ELECTRIC CABINET | LB1241 | 1 | 4129.94 | 4129.94 | IND-AX-MR-ML-00012 |  | 100% |  |  | 2890.958 | 0 | 0 | 0 | 0 | 0 | 2890.958 | 0 | 0
B01 | ELECTRIC CABINET | LB1205 | 1 | 4064.48 | 4064.48 | IND-AX-MR-ML-00012 |  | 100% |  |  | 2845.136 | 0 | 0 | 0 | 0 | 0 | 2845.136 | 0 | 0
B01 | ELECTRIC CABINET | LB1203 | 1 | 4182.31 | 4182.31 | IND-AX-MR-ML-00012 |  | 100% |  |  | 2927.617 | 0 | 0 | 0 | 0 | 0 | 2927.617 | 0 | 0
B01 | ELECTRIC CABINET | LB1201 | 1 | 4830.41 | 4830.41 | IND-AX-MR-ML-00013 |  | 80% |  |  | 0 | 0 | 0 | 2705.0296 | 0 | 0 | 2705.0296 | 0 | 0 |  | Until rate is finalized
B01 | ELECTRIC CABINET | LB1199 | 1 | 3521.13 | 3521.13 | IND-AX-MR-ML-00012 |  | 100% |  |  | 2464.791 | 0 | 0 | 0 | 0 | 0 | 2464.791 | 0 | 0
B01 | ELECTRIC CABINET | LB1143 | 1 | 4568.55 | 4568.55 | IND-AX-MR-ML-00012 |  | 100% |  |  | 3197.985 | 0 | 0 | 0 | 0 | 0 | 3197.985 | 0 | 0
B01 | ELECTRIC CABINET | LB1198 | 1 | 4830.41 | 4830.41 | IND-AX-MR-ML-00012 |  | 100% |  |  | 3381.287 | 0 | 0 | 0 | 0 | 0 | 3381.287 | 0 | 0
B01 | ELECTRIC CABINET | LB266A | 1 | 4280.51 | 4280.51 | IND-AX-MR-ML-00012 |  | 100% |  |  | 2996.357 | 0 | 0 | 0 | 0 | 0 | 2996.357 | 0 | 0
B01 | ELECTRIC CABINET | LB266 | 1 | 4280.51 | 4280.51 | IND-AX-MR-ML-00012 |  | 100% |  |  | 2996.357 | 0 | 0 | 0 | 0 | 0 | 2996.357 | 0 | 0
L04 | D-01e | L04001 | 1 | 2272.5 | 2272.5 | IND-AX-MR-ML-00013 / KCE-AX-MR-ML-0090 |  | 80% |  |  | 0 | 0 | 0 | 1272.6 | 0 | 0 | 1272.6 | 0 | 0 |  | Until rate is finalized
L04 | D-01e | L04002 | 1 | 2272.5 | 2272.5 | IND-AX-MR-ML-00013 / KCE-AX-MR-ML-0090 |  | 80% |  |  | 0 | 0 | 0 | 1272.6 | 0 | 0 | 1272.6 | 0 | 0 |  | Until rate is finalized
L04 | D-01e | L04003 | 1 | 2272.5 | 2272.5 | IND-AX-MR-ML-00013 / KCE-AX-MR-ML-0090 |  | 80% |  |  | 0 | 0 | 0 | 1272.6 | 0 | 0 | 1272.6 | 0 | 0 |  | Until rate is finalized
L04 | D-01e | L04004 | 1 | 2272.5 | 2272.5 | IND-AX-MR-ML-00013 / KCE-AX-MR-ML-0090 |  | 80% |  |  | 0 | 0 | 0 | 1272.6 | 0 | 0 | 1272.6 | 0 | 0 |  | Until rate is finalized
L04 | D-01e | L04005 | 1 | 2272.5 | 2272.5 | IND-AX-MR-ML-00013 / KCE-AX-MR-ML-0090 |  | 80% |  |  | 0 | 0 | 0 | 1272.6 | 0 | 0 | 1272.6 | 0 | 0 |  | Until rate is finalized
L04 | D-01e | L04006 | 1 | 2272.5 | 2272.5 | IND-AX-MR-ML-00013 / KCE-AX-MR-ML-0090 |  | 80% |  |  | 0 | 0 | 0 | 1272.6 | 0 | 0 | 1272.6 | 0 | 0 |  | Until rate is finalized
L04 | D-01e | L04007 | 1 | 2272.5 | 2272.5 | IND-AX-MR-ML-00013 / KCE-AX-MR-ML-0090 |  | 80% |  |  | 0 | 0 | 0 | 1272.6 | 0 | 0 | 1272.6 | 0 | 0 |  | Until rate is finalized
L20 | D-01c | L21H09 | 1 | 1672.5 | 1672.5 | KCE-AX-MR-ML-00057 | IND-AX-WR-ML-00003 | 100% | 100% | 100% | 1170.75 | 250.875 | 250.875 | 0 | 0 | 0 | 1170.75 | 250.875 | 250.875
L21 | D-01c | L22H09 | 1 | 1672.5 | 1672.5 | KCE-AX-MR-ML-00057 | IND-AX-WR-ML-00003 | 100% | 100% | 100% | 1170.75 | 250.875 | 250.875 | 0 | 0 | 0 | 1170.75 | 250.875 | 250.875
L22 | D-01c | L23H09 | 1 | 1672.5 | 1672.5 | KCE-AX-MR-ML-00057 | IND-AX-WR-ML-00003 | 100% | 100% | 100% | 1170.75 | 250.875 | 250.875 | 0 | 0 | 0 | 1170.75 | 250.875 | 250.875
L23 | D-01c | L24H09 | 1 | 1672.5 | 1672.5 | KCE-AX-MR-ML-00057 | IND-AX-WR-ML-00003 | 100% | 100% | 100% | 1170.75 | 250.875 | 250.875 | 0 | 0 | 0 | 1170.75 | 250.875 | 250.875
L24 | D-01c | L25H09 | 1 | 1672.5 | 1672.5 | KCE-AX-MR-ML-00057 | IND-AX-WR-ML-00003 | 100% | 100% | 100% | 1170.75 | 250.875 | 250.875 | 0 | 0 | 0 | 1170.75 | 250.875 | 250.875
L25 | D-01c | L26H09 | 1 | 1672.5 | 1672.5 | KCE-AX-MR-ML-00057 | IND-AX-WR-ML-00003 | 100% | 100% | 100% | 1170.75 | 250.875 | 250.875 | 0 | 0 | 0 | 1170.75 | 250.875 | 250.875
L26 | D-01c | L27H09 | 1 | 1672.5 | 1672.5 | KCE-AX-MR-ML-00057 | IND-AX-WR-ML-00003 | 100% | 100% | 100% | 1170.75 | 250.875 | 250.875 | 0 | 0 | 0 | 1170.75 | 250.875 | 250.875
L27 | D-01c | L28H09 | 1 | 1672.5 | 1672.5 | KCE-AX-MR-ML-00057 | IND-AX-WR-ML-00003 | 100% | 100% | 100% | 1170.75 | 250.875 | 250.875 | 0 | 0 | 0 | 1170.75 | 250.875 | 250.875
L28 | D-01c | L29H09 | 1 | 1672.5 | 1672.5 | KCE-AX-MR-ML-00057 | IND-AX-WR-ML-00003 | 100% | 100% | 100% | 1170.75 | 250.875 | 250.875 | 0 | 0 | 0 | 1170.75 | 250.875 | 250.875
GF |  | LGF11 | 1 | 1350 | 1350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF |  | LGF12 | 1 | 1350 | 1350 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B01 | D-14 | LB1227 | 1 | 2054.75 | 2054.75 | IND-AX-MR-ML-00010_00 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B01 | D-14 | LB1229 | 1 | 2054.75 | 2054.75 | IND-AX-MR-ML-00010_00 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B01 | D-14 | LB128 | 1 | 2054.75 | 2054.75 | IND-AX-MR-ML-00010_00 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B01 | D-14 | LB129 | 1 | 2054.75 | 2054.75 | IND-AX-MR-ML-00010_00 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF | D-04h | LGF04 | 1 | 2063.96 | 2063.96 | IND-AX-MR-ML-00016 |  | 100% |  |  | 1444.772 | 0 | 0 | 0 | 0 | 0 | 1444.772 | 0 | 0
GF | D-02k | LGF06 | 1 | 2199.6675 | 2199.6675 | IND-AX-MR-ML-00016 |  | 100% |  |  | 1539.7672 | 0 | 0 | 0 | 0 | 0 | 1539.7672 | 0 | 0
GF | D-09c | LGF47 | 1 | 3753.19 | 3753.19 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF | D-09e | LGF53 | 1 | 4181.68 | 4181.68 | IND-AX-MR-ML-00012 |  | 100% |  |  | 2927.176 | 0 | 0 | 0 | 0 | 0 | 2927.176 | 0 | 0
GF | D-02e | LGF71 | 1 | 3520.94 | 3520.94 | IND-AX-MR-ML-00014 |  | 80% |  |  | 0 | 0 | 0 | 1971.7264 | 0 | 0 | 1971.7264 | 0 | 0 |  | Until rate is finalized
GF | D-02e | LGF77 | 1 | 3620.94 | 3620.94 | KCE-ID-MR-GF-00009 |  | 100% | 100% | 50% | 2534.658 | 543.141 | 271.5705 | 0 | 0 | 0 | 2534.658 | 543.141 | 271.5705 | No WIR
L02 | D-01g | L0223 | 1 | 2148.6 | 2148.6 | IND-AX-MR-ML-00016 |  | 100% |  |  | 1504.02 | 0 | 0 | 0 | 0 | 0 | 1504.02 | 0 | 0
L02 | D-01g | L0226 | 1 | 2148.6 | 2148.6 | IND-AX-MR-ML-00016 |  | 100% |  |  | 1504.02 | 0 | 0 | 0 | 0 | 0 | 1504.02 | 0 | 0
L03 | D-01a | L0300 | 1 | 1540.25 | 1540.25 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L03 | D-01a | L0305 | 1 | 1540.25 | 1540.25 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L03 | D-01a | L0306 | 1 | 1540.25 | 1540.25 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L03 | D-01a | L0307 | 1 | 1540.25 | 1540.25 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L03 | D-01a | L0308 | 1 | 1540.25 | 1540.25 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L03 | D-01d | L0331 | 1 | 1870.875 | 1870.875 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L03 | D-01d | L0332 | 1 | 1870.875 | 1870.875 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L03 | D-01d | L0334 | 1 | 1870.875 | 1870.875 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L03 | D-01d | L0335 | 1 | 1870.875 | 1870.875 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L03 | D-01d | L0336 | 1 | 1870.875 | 1870.875 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L03 | D-01d | L0337 | 1 | 1870.875 | 1870.875 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L03 | D-01d | L0338 | 1 | 1599.7625 | 1599.7625 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L03 | D-01d | L0339 | 1 | 1870.875 | 1870.875 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L03 | D-02L | L0343 | 1 | 1937.8125 | 1937.8125 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L03 | D-02L | L0344 | 1 | 1937.8125 | 1937.8125 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L03 | D-02L | L0345 | 1 | 1937.8125 | 1937.8125 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L03 | D-02L | L0346 | 1 | 1937.8125 | 1937.8125 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L03 | D-01a | L0348 | 1 | 1540.25 | 1540.25 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L03 | D-01a | L0349 | 1 | 1540.25 | 1540.25 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L04 | D-03a | L0431 | 1 | 2024.7387 | 2024.7387 | IND-AX-MR-ML-00016 |  | 100% |  |  | 1417.3171 | 0 | 0 | 0 | 0 | 0 | 1417.3171 | 0 | 0
L05 | D-02g | L0502 | 1 | 2949.525 | 2949.525 | IND-AX-MR-ML-00016 |  | 100% |  |  | 2064.6675 | 0 | 0 | 0 | 0 | 0 | 2064.6675 | 0 | 0
L02 | D-03b | L0202 | 1 | 2149.715 | 2149.715 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L28 | D-01g | L29H53/L29H36 | 1 | 2149.715 | 2149.715 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L29 | D-01c | L30H08 | 1 | 1540.25 | 1540.25 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L29 | D-01d | L30H55 | 1 | 1599.7625 | 1599.7625 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L29 | D-01D | L30H47 | 1 | 1778.3 | 1778.3 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L29 | D-01A | L30H54 | 1 | 1778.3 | 1778.3 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L29 | D-01A | L30H53 | 1 | 1778.3 | 1778.3 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L30 | D-03d | L31H01 | 1 | 2156.9887 | 2156.9887 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L30 | D-01d | L31H04 | 1 | 1732.0125 | 1732.0125 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L10 | D-01c | L10R23 | 1 | 1922.5 | 1922.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L23 | D-01g | L24R05 | 1 | 1849.715 | 1849.715 | IND-AX-MR-ML-00016 |  | 100% |  |  | 1294.8005 | 0 | 0 | 0 | 0 | 0 | 1294.8005 | 0 | 0
L23 | D-01c | L24R06 | 1 | 1870.875 | 1870.875 | IND-AX-MR-ML-00016 |  | 100% |  |  | 1309.6125 | 0 | 0 | 0 | 0 | 0 | 1309.6125 | 0 | 0
L28 | D-03b | L29R02 | 1 | 2177.4875 | 2177.4875 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L28 | D-03b | L29R01 | 1 | 2024.7387 | 2024.7387 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L31 | D-01g | L32R02 | 1 | 2231.9175 | 2231.9175 | IND-AX-MR-ML-00016 |  | 100% |  |  | 1562.3422 | 0 | 0 | 0 | 0 | 0 | 1562.3422 | 0 | 0
L31 | D-01d | L32R04 | 1 | 1870.875 | 1870.875 | IND-AX-MR-ML-00017 |  | 80% |  |  | 0 | 0 | 0 | 1047.69 | 0 | 0 | 1047.69 | 0 | 0 |  | Until rate is finalized
L31 | D-01g | L32R05 | 1 | 2231.9175 | 2231.9175 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF | D-01e | LGF40 | 1 | 2069.25 | 2069.25 | IND-AX-MR-ML-00014 |  | 80% |  |  | 0 | 0 | 0 | 1158.78 | 0 | 0 | 1158.78 | 0 | 0 |  | Until rate is finalized
GF | D-08b | LGF-177 | 1 | 2196.21 | 2196.21 | IND-AX-MR-ML-00016 |  | 100% |  |  | 1537.347 | 0 | 0 | 0 | 0 | 0 | 1537.347 | 0 | 0
L29 | D-01d | L30H* | 1 | 1732.0125 | 1732.0125 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L02 | D-05e | L02101 | 1 | 2962.75 | 2962.75 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L02 | D-01g | L0239 | 1 | 2148.6 | 2148.6 | IND-AX-MR-ML-00016 |  | 100% |  |  | 1504.02 | 0 | 0 | 0 | 0 | 0 | 1504.02 | 0 | 0
B01 | D-01d | LB1106 | 1 | 1940.3063 | 1940.3063 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B01 | D-02h | LB1108 | 1 | 3914.95 | 3914.95 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B01 | D-02h | LB1109 | 1 | 3438.85 | 3438.85 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B01 | D-01e | LB1152 | 1 | 1778.3 | 1778.3 | IND-AX-MR-ML-00017 |  | 80% |  |  | 0 | 0 | 0 | 995.848 | 0 | 0 | 995.848 | 0 | 0 |  | Until rate is finalized
B01 | D-02f | LB1214 | 1 | 3296.02 | 3296.02 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF | D-01h | LGF05 | 1 | 2063.96 | 2063.96 | IND-AX-MR-ML-00016 |  | 100% |  |  | 1444.772 | 0 | 0 | 0 | 0 | 0 | 1444.772 | 0 | 0
GF | D-03b | LGF48 | 1 | 2149.715 | 2149.715 | IND-AX-MR-ML-00016 |  | 100% |  |  | 1504.8005 | 0 | 0 | 0 | 0 | 0 | 1504.8005 | 0 | 0
GF | D-03b | LGF49 | 1 | 2149.715 | 2149.715 | IND-AX-MR-ML-00016 |  | 100% |  |  | 1504.8005 | 0 | 0 | 0 | 0 | 0 | 1504.8005 | 0 | 0
GF | D-03a | LGF52 | 1 | 2156.9887 | 2156.9887 | IND-AX-MR-ML-00012 |  | 100% |  |  | 1509.8921 | 0 | 0 | 0 | 0 | 0 | 1509.8921 | 0 | 0
GF | D-03d | LGF54 | 1 | 2363.96 | 2363.96 | IND-AX-MR-ML-00016 |  | 100% |  |  | 1654.772 | 0 | 0 | 0 | 0 | 0 | 1654.772 | 0 | 0
GF | D-03d | LGF55 | 1 | 2363.96 | 2363.96 | IND-AX-MR-ML-00016 |  | 100% |  |  | 1654.772 | 0 | 0 | 0 | 0 | 0 | 1654.772 | 0 | 0
GF | D-12c | LGF56 | 1 | 2446.21 | 2446.21 | IND-AX-MR-ML-00012 |  | 100% |  |  | 1712.347 | 0 | 0 | 0 | 0 | 0 | 1712.347 | 0 | 0
GF | D-12a | LGF59 | 1 | 1599.7625 | 1599.7625 | KCE-ID-MR-GF-00009 |  | 100% | 100% | 50% | 1119.8338 | 239.9644 | 119.9822 | 0 | 0 | 0 | 1119.8338 | 239.9644 | 119.9822 | No WIR
L01 | D-03a | L0102 | 1 | 2024.7387 | 2024.7387 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L02 | D-01d | L0230 | 1 | 1599.7625 | 1599.7625 | IND-AX-MR-ML-00013 / KCE-AX-MR-ML-0090 |  | 80% |  |  | 0 | 0 | 0 | 895.867 | 0 | 0 | 895.867 | 0 | 0 |  | Until rate is finalized
L03 | D-03d | L0312 | 1 | 2363.96 | 2363.96 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L03 | D-01d | L0320 | 1 | 1599.7625 | 1599.7625 | IND-AX-MR-ML-00013 / KCE-AX-MR-ML-0090 |  | 80% |  |  | 0 | 0 | 0 | 895.867 | 0 | 0 | 895.867 | 0 | 0 |  | Until rate is finalized
L05 | D-01d | L0518 | 1 | 1599.7625 | 1599.7625 | IND-AX-MR-ML-00016 |  | 100% |  |  | 1119.8338 | 0 | 0 | 0 | 0 | 0 | 1119.8338 | 0 | 0
L08 | D-01d | L08H10 | 1 | 1599.7625 | 1599.7625 | IND-AX-MR-ML-00013 / KCE-AX-MR-ML-0090 |  | 80% |  |  | 0 | 0 | 0 | 895.867 | 0 | 0 | 895.867 | 0 | 0 |  | Until rate is finalized
L13 | D-01g | L14H05 | 1 | 1849.715 | 1849.715 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L23 | D-02d | L24R01 | 1 | 2574.5963 | 2574.5963 | IND-AX-MR-ML-00016 |  | 100% |  |  | 1802.2174 | 0 | 0 | 0 | 0 | 0 | 1802.2174 | 0 | 0
L30 | D-01c | L31R11 | 1 | 1540.25 | 1540.25 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 1 | 2500 | 2500 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF |  | LGF10 | 1 | 400 | 400 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF |  | LGF13 | 1 | 275 | 275 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF |  | LGF16 | 1 | 275 | 275 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF |  | LGF17 | 1 | 275 | 275 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF |  | LGF21 | 1 | 275 | 275 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF |  | LGF26 | 1 | 275 | 275 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF |  | LGF27 | 1 | 275 | 275 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF |  | LGF40 | 1 | 275 | 275 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF |  | LGF41 | 1 | 300 | 300 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF |  | LGF42 | 1 | 275 | 275 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF |  | LGF08 | 1 | 275 | 275 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF |  | LGF-177 | 1 | 275 | 275 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF |  | LGF78 | 1 | 275 | 275 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L02 |  | L02101 | 1 | 400 | 400 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L02 |  | L0239 | 1 | 275 | 275 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L04 |  | L0449 | 1 | 275 | 275 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L09 |  | L10R22 | 1 | 275 | 275 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B01 | D01E | LB1103 | 1 | 2069.25 | 2069.25 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GF | D03D | LGF07 | 1 | 2149.715 | 2149.715 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L02 | D03A | L0221 | 1 | 2024.7387 | 2024.7387 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L02 | D01C | L0237 | 1 | 1540.25 | 1540.25 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| D01C | L0H08 | 1 | 1540.25 | 1540.25 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L09 | D01C | L10H08 | 1 | 1540.25 | 1540.25 | IND-AX-MR-ML-00017 |  | 80% |  |  | 0 | 0 | 0 | 862.54 | 0 | 0 | 862.54 | 0 | 0 |  | Until rate is finalized
L10 | D01C | L11H08 | 1 | 1540.25 | 1540.25 | IND-AX-MR-ML-00017 |  | 80% |  |  | 0 | 0 | 0 | 862.54 | 0 | 0 | 862.54 | 0 | 0 |  | Until rate is finalized
L14 | D01C | L15H08 | 1 | 1540.25 | 1540.25 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L20 | D01C | L21H08 | 1 | 1540.25 | 1540.25 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L22 | D01C | L23H08 | 1 | 1540.25 | 1540.25 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L23 | D01C | L24H08 | 1 | 1540.25 | 1540.25 | IND-AX-MR-ML-00017 |  | 80% |  |  | 0 | 0 | 0 | 862.54 | 0 | 0 | 862.54 | 0 | 0 |  | Until rate is finalized
L25 | D01C | L26H08 | 1 | 1540.25 | 1540.25 | IND-AX-MR-ML-00017 |  | 80% |  |  | 0 | 0 | 0 | 862.54 | 0 | 0 | 862.54 | 0 | 0 |  | Until rate is finalized
L27 | D01C | L28H08 | 1 | 1540.25 | 1540.25 | IND-AX-MR-ML-00017 |  | 80% |  |  | 0 | 0 | 0 | 862.54 | 0 | 0 | 862.54 | 0 | 0 |  | Until rate is finalized
L09 | D01C | L10-014 | 1 | 1540.25 | 1540.25 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
292667.3362
[11 empty] | 119827.8655 | 6246.612 | 4994.9497 | 31403.046 | 0 | 0 | 151230.9115 | 6246.612 | 4994.9497