## Summary
DORCHESTER COLLECTION HOTEL & RESIDENCES (PLOT 18)
VALUATION OF PROGRESS OF WORKS - Feb 2023
Trade Package: Facade Works |  |  |  | Certificate Period |  | Feb 2023
Subcontractor:Glassline Alumnium LLC |  |  |  | Certificate No. |  | KCE PC 13
Subcontract Ref:17001DH/SCA/D&B/4041-GLASSLINE
Ref | SUBCONTRACT WORKS | TOTAL VALUE OF SUBCONTRACT WORKS | VALUE OF WORKS UNDER NEW SUBCONTRACT | Previous | This Month | Current Cumilative Progress
A | Preliminaries | 6020000 | 33333 | 33333 | 0 | 33333
B | Podium Facade | 9146139.004 | 1055111.004 | 649413.8438 | 0 | 649413.8438
C | Hotel and Apartment Tower Facade | 34536193.997 | 1217697.997 | 702355.315 | 0 | 702355.315
D | Doors in the Podium | 2473643 | 1758607 | 1013100.7578 | 501053.9364 | 1514154.6942
E | Doors in the Apt/Hotel Tower | 196708.998 | 222223 | -94884.5974 | 0 | -94884.5974
F | Level 5 Facade EWS-701 | 3611540 | 117548 | 117401.4645 | 0 | 117401.4645
G | Roof Canopies | 2265775 | 960223 | 778855 | 0 | 778855
Sub-Totals |  | 58249999.999 | 5364743.001 | 3199574.7837 | 501053.9364 | 3700628.7201
VARIATIONS
| Variations (additions) approved by RPJV (refer to separate list) | 8263865 | 2190528 | 1273650.11 | 0 | 1273650.11
| Variations (omissions) approved by RPJV (refer to separate list) | -7013865 | 0 |  | 0
| Prolongation costs approved by RPJV | 2200000 | 0 |  | 0
| Soffit channel/cove to L3 to hotel tower (subject to remeasure) | 645007 | 645007 | 32250.35 | 0 | 32250.35
| Facade extension at ground floor | 53020 | 53020 | 47718 | 0 | 47718
| Upper roof canopy to hotel tower | 312774 | 312774 | 124327.665 | 122763.795 | 247091.46
| Vertical gas louvre to podium levels | 13827 | 13827 | 13550.1179 | 0 | 13550.1179
| Facade support brackets at L18 | 15000 | 15000 | 15000 | 0 | 15000
| New hardware and profile to aluminium swing doors | 69300 | 69300 | 34650 | 0 | 34650
| Panic bars Pull handles to facade doors (subject to remeasure) | 103500 | 801072 | 0 | 0 | 0
| and other hardware (Provisional Sum) | 697572
| Additional preliminaries (for new subcontract period) | 2100000 | 2100000 | 1764651.2133 | 67069.7573 | 1831720.9707 | 67069.7573
3495631.0086
VARIATIONS UNDER KCE
| Variations Claimed as instructed by KCE |  |  | 390905.2406 | 8114.4 | 399019.6406
Sub-Totals |  | 7460000 | 6200528 | 3696702.6969 | 197947.9523 | 3894650.6492
MATERIALS ON SITE
| Materials on Site | 0 | -847423 | -847423 | 0 | -847423
Sub-Totals |  | 0 | -847423 | -847423 | 0 | -847423
Totals |  | 65709999.999 | 10273401.999 | 6048854.4806 | 699001.8887 | 6747856.3693
8114.4
6739741.9693

## Accomp. Breakdown-Dec
PLOT-18 | [41 empty] | Remaining to Claim | [18 empty] | 2022-12-30
BILL OF QUANTITIES | [41 empty] | Material Delivery | [7 empty] | Installation | [10 empty] | Material Delivery | [11 empty] | Installation | [11 empty] | Previous Value |  | This Period | [7 empty] | 1514154.6942 |  |  | =BK245+BK164+BK132
PROGRESS PAYMENT APPLICATION BREAKDOWN | [41 empty] | First Fix |  | Frames |  | Glass/ Panel |  | Finishing |  | First Fix |  | Frames |  | Glass |  | Finishing |  |  |  |  | First Fix |  |  | Frames |  |  | Glass/ Panel |  |  | Finishing |  |  | First Fix |  |  | Frames |  |  | Glass |  |  | Finishing
Item | Description | [40 empty] | 25% |  | 35% |  | 35% |  | 5% |  | 25% |  | 35% |  | 35% |  | 5% |  | % | Amount |  | 25% |  |  | 35% |  |  | 35% |  |  | 5% |  |  | 25% |  |  | 35% |  |  | 35% |  |  | 5% | [6 empty] | Glassline Claimed Prpgress-Dec 22 |  | Glassline Claimed Prpgress-January 23 |  | Sky Palaces Certified Prpgress-January 23 |  | Sky Palaces Certified Prpgress Breakdown-Dec 22
[6 empty] | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | % | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | % | Amount | Balance Qty / % | Balance Amount | Balance Qty / % | Balance Amount | Balance Qty / % | Balance Amount | Balance Qty / % | Balance Amount | Balance Qty / % | Balance Amount | Balance Qty / % | Balance Amount | Balance Qty / % | Balance Amount | Balance Qty / % | Balance Amount |  |  |  | Balance Qty / % | Curr. Progress | Amount | Balance Qty / % | Curr. Progress | Amount | Balance Qty / % | Curr. Progress | Amount | Balance Qty / % | Curr. Progress | Amount | Balance Qty / % | Curr. Progress | Amount | Balance Qty / % | Curr. Progress | Amount | Balance Qty / % | Curr. Progress | Amount | Balance Qty / % | Curr. Progress | Amount | % | Amount | % | Amount | % | Amount |  |  | % | Amount | Podium Facade | Hotel and Apartment Tower Facade | Doors in the Podium | Doors in the Apt/Hotel Tower | Level 5 Facade EWS-701 | Roof Canopies
|  | Qty. | Unit | Rate | Amount | [53 empty] | 4886963.5932 | [30 empty] | 3410556.792 |  |  |  | 3762180.3175 | 649413.8438 | 663609.9491 | 1514154.6942 | 38745.3659 | 117401.4645 | 778855
ALUMINIUM AND GLAZING WORKS
Glaze facade cladding system
Ground and 1st Levels
A | Type EWS -121 (Straight) | 1399 | m2 | 1300 | 1818700 | 1399 | 341006.25 | 1399 | 477408.75 | 1399 | 477408.75 | 1399 | 68201.25 | 1399 | 113668.75 | 1399 | 159136.25 | 1399 | 159136.25 | 1399 | 22733.75 | 100% | 1818700 | 1399 | 341006.25 | 1399 | 477408.75 | 1399 | 477408.75 | 1399 | 68201.25 | 1399 | 113668.75 | 1399 | 159136.25 | 1399 | 159136.25 | 1399 | 22733.75 | 100% | 1818700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | [13 empty] | SA + Hotel |  | 0 | 1818700
A1 | Type EWS -121 (Curved) | 188 | m2 | 2391 | 449508 | 188 | 84282.75 | 188 | 117995.85 | 188 | 117995.85 | 188 | 16856.55 | 188 | 28094.25 | 188 | 39331.95 | 188 | 39331.95 | 188 | 5618.85 | 100% | 449508 | 188 | 84282.75 | 188 | 117995.85 | 188 | 117995.85 | 188 | 16856.55 | 188 | 28094.25 | 188 | 39331.95 | 188 | 39331.95 | 188 | 5618.85 | 100% | 449508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | [13 empty] | SA + Hotel |  | 2.9104e-11 | 449508
|  | 1587 |  |  |  | 1587 |  | 1587 |  | 1587 |  | 1587 |  | 1587 |  | 1587 |  | 1587 |  | 1587 |  |  |  | 1587 |  | 1587 |  | 1587 |  | 1587 |  | 1587 |  | 1587 |  | 1587 |  | 1587
B | Type EWS -122 (Straight and Curved) |  | m2 | 0 | Included
C | Type EWS-141 (Straight) | 1137 | m2 | 1205 | 1370085 | 1137 | 256890.9375 | 1137 | 359647.3125 | 1137 | 359647.3125 | 1137 | 51378.1875 | 1137 | 85630.3125 | 1137 | 119882.4375 | 1137 | 119882.4375 | 1137 | 17126.0625 | 100% | 1370085 | 1137 | 256890.9375 | 1137 | 359647.3125 | 1137 | 359647.3125 | 1137 | 51378.1875 | 877.5358 | 66089.4137 | 877.5358 | 92525.1792 | 877.5358 | 92525.1792 | 877.5358 | 13217.8827 | 94.29% | 1291921.4048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259.4642 | 19540.8988 | 259.4642 | 27357.2583 | 259.4642 | 27357.2583 | 259.4642 | 3908.1798 | 5.705% | 78163.5952 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 259.4642 | 100% | 19540.8988 | 259.4642 | 100% | 27357.2583 | 259.4642 | 100% | 27357.2583 | 259.4642 | 0% | 0 | 95% | 74255.4154 | 0% | 0 | 95% | 74255.4154 | 95% | 74255.4154 | [11 empty] | SA |  | 0 | 1291921.4048 | 78163.5952 | 342521.25 | 22.82% | 877.5358
C1 | Type EWS-141 (Curved) | 147 | m2 | 2085 | 306495 | 147 | 57467.8125 | 147 | 80454.9375 | 147 | 80454.9375 | 147 | 11493.5625 | 147 | 19155.9375 | 147 | 26818.3125 | 147 | 26818.3125 | 147 | 3831.1875 | 100% | 306495 | 147 | 57467.8125 | 147 | 80454.9375 | 147 | 80454.9375 | 147 | 11493.5625 | 87.8369 | 11446.2414 | 87.8369 | 16024.738 | 87.8369 | 16024.738 | 87.8369 | 2289.2483 | 89.94% | 275656.2157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59.1631 | 7709.6961 | 59.1631 | 10793.5745 | 59.1631 | 10793.5745 | 59.1631 | 1541.9392 | 10.06% | 30838.7843 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 59.1631 | 100% | 7709.6961 | 59.1631 | 100% | 10793.5745 | 59.1631 | 100% | 10793.5745 | 59.1631 | 0% | 0 | 95% | 29296.8451 | 0% | 0 | 95% | 29296.8451 | 95% | 29296.8451 | [11 empty] | SA |  | 2.7285e-11 | 275656.2157 | 30838.7843 | 76623.75 | 40.25% | 87.8369
|  | 1284 |  |  |  | 1284 |  | 1284 |  | 1284 |  | 1284 |  | 1284 |  | 1284 |  | 1284 |  | 1284 |  |  |  | 1284 |  | 1284 |  | 1284 |  | 1284 |  | 965.3726 |  | 965.3726 |  | 965.3726 |  | 965.3726 | [20 empty] | 109002.3795 | [29 empty] | 95% | 103552.2605 |  | 103552.2605 | 95% | 103552.2605 | 103552.2605
Doors-Ground Floor
D | Door Type D-23, Manual Door | 16 | Nr. | 13750 | 220000 | 16 | 41250 | 16 | 57750 | 16 | 57750 | 16 | 8250 | 16 | 13750 | 16 | 19250 | 16 | 19250 | 16 | 2750 | 100% | 220000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 16 | 41250 | 16 | 57750 | 16 | 57750 | 16 | 8250 | 16 | 13750 | 16 | 19250 | 16 | 19250 | 16 | 2750 | 100% | 220000 |  | 16 | 90% | 37125 | 16 | 90% | 51975 | 16 | 90% | 51975 | 16 | 90% | 7425 | 16 | 15% | 2062.5 | 16 | 15% | 2887.5 | 16 | 15% | 2887.5 | 16 |  | 0 | 0% | 0 | 71.06% | 156337.5 | 71.06% | 156337.5 | 77% | 169400
D1 | D-23, Automatic Door Type EWS-123 | 12 | Nr. | 50700 | 608400 | 12 | 114075 | 12 | 159705 | 12 | 159705 | 12 | 22815 | 12 | 38025 | 12 | 53235 | 12 | 53235 | 12 | 7605 | 100% | 608400 | 0.3751 | 3565.7475 | 0.3751 | 4992.0465 | 0.3751 | 4992.0465 | 0.3751 | 713.1495 | 0.3751 | 1188.5825 | 0.3751 | 1664.0155 | 0.3751 | 1664.0155 | 0.3751 | 237.7165 | 3.126% | 19017.32 | 11.6249 | 110509.2525 | 11.6249 | 154712.9535 | 11.6249 | 154712.9535 | 11.6249 | 22101.8505 | 11.6249 | 36836.4175 | 11.6249 | 51570.9845 | 11.6249 | 51570.9845 | 11.6249 | 7367.2835 | 96.87% | 589382.68 |  | 11.6249 | 100% | 110509.2525 | 11.6249 | 100% | 154712.9535 | 11.6249 | 100% | 154712.9535 | 11.6249 | 100% | 22101.8505 | 11.6249 | 100% | 36836.4175 | 11.6249 | 100% | 51570.9845 | 11.6249 | 100% | 51570.9845 | 11.6249 | 100% | 7367.2835 | 0% | 0 | 100% | 589382.68 | 100% | 589382.68 | 100% | 589382.68 |  | 751518.2601 | [12 empty] | 19017.32 | 589382.68 | 608400 | 96.87% | 0.3751
E | Door Type D-25 | 1 | Nr. | 13750 | 13750 | 1 | 2578.125 | 1 | 3609.375 | 1 | 3609.375 | 1 | 515.625 | 1 | 859.375 | 1 | 1203.125 | 1 | 1203.125 | 1 | 171.875 | 100% | 13750 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 1 | 2578.125 | 1 | 3609.375 | 1 | 3609.375 | 1 | 515.625 | 1 | 859.375 | 1 | 1203.125 | 1 | 1203.125 | 1 | 171.875 | 100% | 13750 |  | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0
F | Door Type D-8 1300x2550mm | 1 | Nr. | 6862.5 | 6862.5 | 1 | 1286.7188 | 1 | 1801.4062 | 1 | 1801.4062 | 1 | 257.3438 | 1 | 428.9062 | 1 | 600.4688 | 1 | 600.4688 | 1 | 85.7812 | 100% | 6862.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 1 | 1286.7188 | 1 | 1801.4062 | 1 | 1801.4062 | 1 | 257.3438 | 1 | 428.9062 | 1 | 600.4688 | 1 | 600.4688 | 1 | 85.7812 | 100% | 6862.5 |  | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0
G | Door Type D-8 1250x2800mm | 1 | Nr. | 6862.5 | 6862.5 | 1 | 1286.7188 | 1 | 1801.4062 | 1 | 1801.4062 | 1 | 257.3438 | 1 | 428.9062 | 1 | 600.4688 | 1 | 600.4688 | 1 | 85.7812 | 100% | 6862.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 1 | 1286.7188 | 1 | 1801.4062 | 1 | 1801.4062 | 1 | 257.3438 | 1 | 428.9062 | 1 | 600.4688 | 1 | 600.4688 | 1 | 85.7812 | 100% | 6862.5 |  | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0
[59 empty] | 836857.68 | [29 empty] | 89.11% | 745720.18 | 90.67% | 758782.68 | 89.8% | 751518.2601 |  |  | 751518.2601 |  |  |  | 5% | 41842.884
H&SA | 2nd and 3rd Levels
A | Type EWS121 (Straight) | 927 | m2 | 1377 | 1276479 | 927 | 239339.8125 | 927 | 335075.7375 | 927 | 335075.7375 | 927 | 47867.9625 | 927 | 79779.9375 | 927 | 111691.9125 | 927 | 111691.9125 | 927 | 15955.9875 | 100% | 1276479 | 927 | 239339.8125 | 927 | 335075.7375 | 927 | 335075.7375 | 927 | 47867.9625 | 511.7682 | 44044.0509 | 511.7682 | 61661.6712 | 511.7682 | 61661.6712 | 511.7682 | 8808.8102 | 88.8% | 1133535.4536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 415.2318 | 35735.8866 | 415.2318 | 50030.2413 | 415.2318 | 50030.2413 | 415.2318 | 7147.1773 | 11.2% | 142943.5464 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 415.2318 | 100% | 35735.8866 | 415.2318 | 100% | 50030.2413 | 415.2318 | 100% | 50030.2413 | 415.2318 |  | 0 | 95% | 135796.3691 | 0% | 0 | 95% | 135796.3691 | 95% | 135796.3691 | [11 empty] | SA + Hotel |  | 1.3824e-10 | 1133535.4536 | 142943.5464 | 319119.75 | 44.79% | 511.7682
0
A1 | Type EWS121 (Curved) | 97 | m2 | 2289 | 222033 | 97 | 41631.1875 | 97 | 58283.6625 | 97 | 58283.6625 | 97 | 8326.2375 | 97 | 13877.0625 | 97 | 19427.8875 | 97 | 19427.8875 | 97 | 2775.4125 | 100% | 222033 | 97 | 41631.1875 | 97 | 58283.6625 | 97 | 58283.6625 | 97 | 8326.2375 | 2.6059 | 372.8068 | 2.6059 | 521.9296 | 2.6059 | 521.9296 | 2.6059 | 74.5614 | 75.67% | 168015.9774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94.3941 | 13504.2557 | 94.3941 | 18905.9579 | 94.3941 | 18905.9579 | 94.3941 | 2700.8511 | 24.33% | 54017.0226 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 94.3941 | 100% | 13504.2557 | 94.3941 | 100% | 18905.9579 | 94.3941 | 100% | 18905.9579 | 94.3941 |  | 0 | 95% | 51316.1715 | 0% | 0 | 95% | 51316.1715 | 95% | 51316.1715 | [11 empty] | SA + Hotel |  |  | 168015.9774 | 54017.0226 | 55508.25 | 97.31% | 2.6059
|  | 1024 |  |  |  | 1024 |  | 1024 |  | 1024 |  | 1024 |  | 1024 |  | 1024 |  | 1024 |  | 1024 |  |  |  | 1024 |  | 1024 |  | 1024 |  | 1024 |  | 514.3741 |  | 514.3741 |  | 514.3741 |  | 514.3741
| Sliding Door Type D-26 for EWS-121 size 2 x 3 | 1 | Nos | 49500 | 49500 | 1 | 9281.25 | 1 | 12993.75 | 1 | 12993.75 | 1 | 1856.25 | 1 | 3093.75 | 1 | 4331.25 | 1 | 4331.25 | 1 | 618.75 | 100% | 49500 | 0.74396 | 6904.89 | 0.74396 | 9666.846 | 0.74396 | 9666.846 | 0.74396 | 1380.978 | 0.74396 | 2301.63 | 0.74396 | 3222.282 | 0.74396 | 3222.282 | 0.74396 | 460.326 | 74.4% | 36826.0799 | 0.25604 | 2376.36 | 0.25604 | 3326.904 | 0.25604 | 3326.904 | 0.25604 | 475.272 | 0.25604 | 792.12 | 0.25604 | 1108.968 | 0.25604 | 1108.968 | 0.25604 | 158.424 | 25.6% | 12673.9201 |  | 0.25604 | 100% | 2376.36 | 0.25604 | 100% | 3326.904 | 0.25604 | 100% | 3326.904 | 0.25604 | 100% | 475.272 | 0.25604 | 100% | 792.12 | 0.25604 | 100% | 1108.968 | 0.25604 | 100% | 1108.968 | 0.25604 |  | 0 | 98.75% | 12515.4961 | 0% | 0 | 98.75% | 12515.4961 | 98.75% | 12515.4961 | [13 empty] | 9505.4401 | 36826.0799 | 12673.9201 | 49500 | 25.6% | 0.74396
B | Type EWS122 (Straight and Curved) |  | m2 | 0 | Included
C | Type EWS124 (Straight and Curved) | 53 | m2 | 5349 | 283497 | 53 | 53155.6875 | 53 | 74417.9625 | 53 | 74417.9625 | 53 | 10631.1375 | 53 | 17718.5625 | 53 | 24805.9875 | 53 | 24805.9875 | 53 | 3543.7125 | 100% | 283497 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 53 | 53155.6875 | 53 | 74417.9625 | 53 | 74417.9625 | 53 | 10631.1375 | 53 | 17718.5625 | 53 | 24805.9875 | 53 | 24805.9875 | 53 | 3543.7125 | 100% | 283497 |  | 53 | 60% | 31893.4125 | 53 | 60% | 44650.7775 | 53 | 60% | 44650.7775 | 53 | 60% | 6378.6825 | 53 | 60% | 10631.1375 | 53 | 60% | 14883.5925 | 53 | 60% | 14883.5925 | 53 | 60% | 2126.2275 | 40% | 113398.8 | 20% | 56699.4 | 60% | 170098.2 | 60% | 170098.2 | [11 empty] | H, L2
H
D | Type EWS125 (Straight) | 138 | m2 | 1165 | 160770 | 138 | 30144.375 | 138 | 42202.125 | 138 | 42202.125 | 138 | 6028.875 | 138 | 10048.125 | 138 | 14067.375 | 138 | 14067.375 | 138 | 2009.625 | 100% | 160770 | 138 | 30144.375 | 138 | 42202.125 | 138 | 42202.125 | 138 | 6028.875 | 136.62 | 9947.6438 | 136.62 | 13926.7013 | 136.62 | 13926.7013 | 136.62 | 1989.5288 | 99.75% | 160368.075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.38 | 100.4812 | 1.38 | 140.6737 | 1.38 | 140.6737 | 1.38 | 20.0962 | 0.25% | 401.925 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1.38 | 100% | 100.4812 | 1.38 | 100% | 140.6737 | 1.38 | 100% | 140.6737 | 1.38 |  | 0 | 95% | 381.8287 | 0% | 0 | 95% | 381.8287 | 95% | 381.8287 | [11 empty] | H, L2 |  | 1.3642e-11 | 160368.075 | 401.925 | 40192.5 | 1% | 136.62
D1 | Type EWS125 (Curved) | 24 | m2 | 2947 | 70728 | 24 | 13261.5 | 24 | 18566.1 | 24 | 18566.1 | 24 | 2652.3 | 24 | 4420.5 | 24 | 6188.7 | 24 | 6188.7 | 24 | 884.1 | 100% | 70728 | 24 | 13261.5 | 24 | 18566.1 | 24 | 18566.1 | 24 | 2652.3 | 23.76 | 4376.295 | 23.76 | 6126.813 | 23.76 | 6126.813 | 23.76 | 875.259 | 99.75% | 70551.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24 | 44.205 | 0.24 | 61.887 | 0.24 | 61.887 | 0.24 | 8.841 | 0.25% | 176.82 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0.24 | 100% | 44.205 | 0.24 | 100% | 61.887 | 0.24 | 100% | 61.887 | 0.24 |  | 0 | 95% | 167.979 | 0% | 0 | 95% | 167.979 | 95% | 167.979 | [11 empty] | H, L2 |  | 0 | 70551.18 | 176.82 | 17682 | 1% | 23.76
|  | 162 |  |  |  | 162 |  | 162 |  | 162 |  | 162 |  | 162 |  | 162 |  | 162 |  | 162 |  |  |  | 162 |  | 162 |  | 162 |  | 162 |  | 160.38 |  | 160.38 |  | 160.38 |  | 160.38
| Extra over Operable Panel for EWS-125 size 4.5 x 3 | 1 | Nos | 100000 | 100000 | 1 | 18750 | 1 | 26250 | 1 | 26250 | 1 | 3750 | 1 | 6250 | 1 | 8750 | 1 | 8750 | 1 | 1250 | 100% | 100000 | 0.9975 | 18703.125 | 0.9975 | 26184.375 | 0.9975 | 26184.375 | 0.9975 | 3740.625 | 0.9975 | 6234.375 | 0.9975 | 8728.125 | 0.9975 | 8728.125 | 0.9975 | 1246.875 | 99.75% | 99750 | 0.0025 | 46.875 | 0.0025 | 65.625 | 0.0025 | 65.625 | 0.0025 | 9.375 | 0.0025 | 15.625 | 0.0025 | 21.875 | 0.0025 | 21.875 | 0.0025 | 3.125 | 0.25% | 250 |  | 0.0025 |  | 0 | 0.0025 |  | 0 | 0.0025 |  | 0 | 0.0025 |  | 0 | 0.0025 |  | 0 | 0.0025 |  | 0 | 0.0025 |  | 0 | 0.0025 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | [13 empty] | 187.5 | 99750 | 250 | 100000 | 0.25% | 0.9975
E | Type EWS141 (Straight and Curved) |  | m2 | 0 | Included
SA
F | Type EWS142 (Straight) | 455 | m2 | 1117 | 508235 | 455 | 95294.0625 | 455 | 133411.6875 | 455 | 133411.6875 | 455 | 19058.8125 | 455 | 31764.6875 | 455 | 44470.5625 | 455 | 44470.5625 | 455 | 6352.9375 | 100% | 508235 | 455 | 95294.0625 | 455 | 133411.6875 | 455 | 133411.6875 | 455 | 19058.8125 | 384.9175 | 26872.0505 | 384.9175 | 37620.8708 | 384.9175 | 37620.8708 | 384.9175 | 5374.4101 | 96.15% | 488664.4522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70.0825 | 4892.637 | 70.0825 | 6849.6917 | 70.0825 | 6849.6917 | 70.0825 | 978.5274 | 3.851% | 19570.5478 |  | 0 | 9% | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 70.0825 | 100% | 4892.637 | 70.0825 | 100% | 6849.6917 | 70.0825 | 100% | 6849.6917 | 70.0825 |  | 0 | 95% | 18592.0205 | 0% | 0 | 95% | 18592.0205 | 95% | 18592.0205 | [11 empty] | SA, L2 |  | 5.457e-11 | 488664.4522 | 19570.5478 | 127058.75 | 15.4% | 384.9175
F1 | Type EWS142 (Curved) | 59 | m2 | 2202 | 129918 | 59 | 24359.625 | 59 | 34103.475 | 59 | 34103.475 | 59 | 4871.925 | 59 | 8119.875 | 59 | 11367.825 | 59 | 11367.825 | 59 | 1623.975 | 100% | 129918 | 59 | 24359.625 | 59 | 34103.475 | 59 | 34103.475 | 59 | 4871.925 | 10.6107 | 1460.3038 | 10.6107 | 2044.4253 | 10.6107 | 2044.4253 | 10.6107 | 292.0608 | 79.5% | 103279.7152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48.3893 | 6659.5712 | 48.3893 | 9323.3997 | 48.3893 | 9323.3997 | 48.3893 | 1331.9142 | 20.5% | 26638.2848 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 48.3893 | 100% | 6659.5712 | 48.3893 | 100% | 9323.3997 | 48.3893 | 100% | 9323.3997 | 48.3893 |  | 0 | 95% | 25306.3706 | 0% | 0 | 95% | 25306.3706 | 95% | 25306.3706 | [11 empty] | SA, L2 |  | 1.6371e-11 | 103279.7152 | 26638.2848 | 32479.5 | 82.02% | 10.6107
|  | 514 |  | 0.84483 |  | 514 |  | 514 |  | 514 |  | 514 |  | 514 |  | 514 |  | 514 |  | 514 |  |  |  | 514 |  | 514 |  | 514 |  | 514 |  | 395.5282 |  | 395.5282 |  | 395.5282 |  | 395.5282
SA |  |  |  | 0.15517
G | Type EWS145 (Straight) | 343 | m2 | 1646 | 564578 | 343 | 105858.375 | 343 | 148201.725 | 343 | 148201.725 | 343 | 21171.675 | 343 | 35286.125 | 343 | 49400.575 | 343 | 49400.575 | 343 | 7057.225 | 100% | 564578 | 343 | 105858.375 | 343 | 148201.725 | 343 | 148201.725 | 343 | 21171.675 | 343 | 35286.125 | 343 | 49400.575 | 343 | 49400.575 | 343 | 7057.225 | 100% | 564578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0% | 0 |  | 0 |  | 0 | [11 empty] | SA, L2 |  | 4.3656e-11 | 564578
G1 | Type EWS145 (Curved) | 63 | m2 | 2345 | 147735 | 63 | 27700.3125 | 63 | 38780.4375 | 63 | 38780.4375 | 63 | 5540.0625 | 63 | 9233.4375 | 63 | 12926.8125 | 63 | 12926.8125 | 63 | 1846.6875 | 100% | 147735 | 63 | 27700.3125 | 63 | 38780.4375 | 63 | 38780.4375 | 63 | 5540.0625 | 63 | 9233.4375 | 63 | 12926.8125 | 63 | 12926.8125 | 63 | 1846.6875 | 100% | 147735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0% | 0 |  | 0 |  | 0 | [11 empty] | SA, L2 |  | 1.3642e-11 | 147735
|  | 406 |  |  |  | 406 |  | 406 |  | 406 |  | 406 |  | 406 |  | 406 |  | 406 |  | 406 |  |  |  | 406 |  | 406 |  | 406 |  | 406 |  | 406 |  | 406 |  | 406 |  | 406
[59 empty] | 540169.0668 | [29 empty] | 76.67% | 414174.4355 | 76.67% | 414174.4355 | 77% | 415930.1815 | 415930.1815
Doors
H | Curved sliding door /Airlock in accordance with drawing EWS-120-102 | 1 | Nr. | 425000 | 425000 | 1 | 79687.5 | 1 | 111562.5 | 1 | 111562.5 | 1 | 15937.5 | 1 | 26562.5 | 1 | 37187.5 | 1 | 37187.5 | 1 | 5312.5 | 100% | 425000 | 0.46833 | 37320.074 | 0.46833 | 52248.1036 | 0.46833 | 52248.1036 | 0.46833 | 7464.0148 | 0.46833 | 12440.0247 | 0.46833 | 17416.0345 | 0.46833 | 17416.0345 | 0.46833 | 2488.0049 | 46.83% | 199040.3948 | 0.53167 | 42367.426 | 0.53167 | 59314.3964 | 0.53167 | 59314.3964 | 0.53167 | 8473.4852 | 0.53167 | 14122.4753 | 0.53167 | 19771.4655 | 0.53167 | 19771.4655 | 0.53167 | 2824.4951 | 53.17% | 225959.6052 |  | 0.53167 | 100% | 42367.426 | 0.53167 | 100% | 59314.3964 | 0.53167 | 100% | 59314.3964 | 0.53167 | 100% | 8473.4852 | 0.53167 | 100% | 14122.4753 | 0.53167 | 100% | 19771.4655 | 0.53167 | 100% | 19771.4655 | 0.53167 | 100% | 2824.4951 | 0% | 0 | 100% | 225959.6052 | 100% | 225959.6052 | 100% | 225959.6052 | [14 empty] | 199040.3948 | 225959.6052 | 425000 | 53.17% | 0.46833
J | Door Type D-23, Manual | 14 | Nr. | 13750 | 192500 | 14 | 36093.75 | 14 | 50531.25 | 14 | 50531.25 | 14 | 7218.75 | 14 | 12031.25 | 14 | 16843.75 | 14 | 16843.75 | 14 | 2406.25 | 100% | 192500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 14 | 36093.75 | 14 | 50531.25 | 14 | 50531.25 | 14 | 7218.75 | 14 | 12031.25 | 14 | 16843.75 | 14 | 16843.75 | 14 | 2406.25 | 100% | 192500 |  | 14 | 40% | 14437.5 | 14 | 40% | 20212.5 | 14 | 40% | 20212.5 | 14 | 40% | 2887.5 | 14 | 14% | 1684.375 | 14 | 14% | 2358.125 | 14 | 14% | 2358.125 | 14 |  | 0 | 13.5% | 25987.5 | 19.82% | 38163.125 | 33.32% | 64150.625 | 39.5% | 76037.5
J1 | D-23, Automatic Door Type EWS-123 | 3 | Nr. | 50700 | 152100 | 3 | 28518.75 | 3 | 39926.25 | 3 | 39926.25 | 3 | 5703.75 | 3 | 9506.25 | 3 | 13308.75 | 3 | 13308.75 | 3 | 1901.25 | 100% | 152100 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 3 | 28518.75 | 3 | 39926.25 | 3 | 39926.25 | 3 | 5703.75 | 3 | 9506.25 | 3 | 13308.75 | 3 | 13308.75 | 3 | 1901.25 | 100% | 152100 |  | 3 |  | 0 | 3 |  | 0 | 3 |  | 0 | 3 |  | 0 | 3 |  | 0 | 3 |  | 0 | 3 |  | 0 | 3 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 |  | 651261.4341
K | Door Type D-8 size 1100x2900mm, Automatic Door Type EWS-123 | 4 | Nr. | 28700 | 114800 | 4 | 21525 | 4 | 30135 | 4 | 30135 | 4 | 4305 | 4 | 7175 | 4 | 10045 | 4 | 10045 | 4 | 1435 | 100% | 114800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 4 | 21525 | 4 | 30135 | 4 | 30135 | 4 | 4305 | 4 | 7175 | 4 | 10045 | 4 | 10045 | 4 | 1435 | 100% | 114800 |  | 4 |  | 0 | 4 |  | 0 | 4 |  | 0 | 4 |  | 0 | 4 |  | 0 | 4 |  | 0 | 4 |  | 0 | 4 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0
L | Door Type D-8 size 1200x 4000mm, Automatic Door Type EWS-123 | 3 | Nr. | 28700 | 86100 | 3 | 16143.75 | 3 | 22601.25 | 3 | 22601.25 | 3 | 3228.75 | 3 | 5381.25 | 3 | 7533.75 | 3 | 7533.75 | 3 | 1076.25 | 100% | 86100 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 3 | 16143.75 | 3 | 22601.25 | 3 | 22601.25 | 3 | 3228.75 | 3 | 5381.25 | 3 | 7533.75 | 3 | 7533.75 | 3 | 1076.25 | 100% | 86100 |  | 3 |  | 0 | 3 |  | 0 | 3 |  | 0 | 3 |  | 0 | 3 |  | 0 | 3 |  | 0 | 3 |  | 0 | 3 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0
[59 empty] | 771459.6052 | [29 empty] | 37.61% | 290110.2302 | 39.15% | 301997.1052 | 84.42% | 651261.4341 |  |  | 651261.4341
Apartment 4th & 5th Levels and Hotel 4th to 6th Levels
A | Type EWS 141 (Straight) | 456 | m2 | 1325 | 604200 | 456 | 113287.5 | 456 | 158602.5 | 456 | 158602.5 | 456 | 22657.5 | 456 | 37762.5 | 456 | 52867.5 | 456 | 52867.5 | 456 | 7552.5 | 100% | 604200 | 456 | 113287.5 | 456 | 158602.5 | 456 | 158602.5 | 456 | 22657.5 | 433.2 | 35874.375 | 433.2 | 50224.125 | 433.2 | 50224.125 | 433.2 | 7174.875 | 98.75% | 596647.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.8 | 1888.125 | 22.8 | 2643.375 | 22.8 | 2643.375 | 22.8 | 377.625 | 1.25% | 7552.5 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 22.8 | 100% | 1888.125 | 22.8 | 100% | 2643.375 | 22.8 | 100% | 2643.375 | 22.8 | 90% | 339.8625 | 99.5% | 7514.7375 | 0% | 0 | 99.5% | 7514.7375 | 99.5% | 7514.7375 | 99.5% | 7514.7375 | 7514.7375 | [8 empty] | H, SA |  |  | 596647.5 | 7552.5 | 151050 | 5% | 433.2
A1 | Type EWS 141 (Curved) | 52 | m2 | 2486 | 129272 | 52 | 24238.5 | 52 | 33933.9 | 52 | 33933.9 | 52 | 4847.7 | 52 | 8079.5 | 52 | 11311.3 | 52 | 11311.3 | 52 | 1615.9 | 100% | 129272 | 52 | 24238.5 | 52 | 33933.9 | 52 | 33933.9 | 52 | 4847.7 | 49.4 | 7675.525 | 49.4 | 10745.735 | 49.4 | 10745.735 | 49.4 | 1535.105 | 98.75% | 127656.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6 | 403.975 | 2.6 | 565.565 | 2.6 | 565.565 | 2.6 | 80.795 | 1.25% | 1615.9 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2.6 | 100% | 403.975 | 2.6 | 100% | 565.565 | 2.6 | 100% | 565.565 | 2.6 | 90% | 72.7155 | 99.5% | 1607.8205 | 0% | 0 | 99.5% | 1607.8205 | 99.5% | 1607.8205 | 99.5% | 1607.8205 | 1607.8205 | [8 empty] | H, SA |  |  | 127656.1 | 1615.9 | 32318 | 5% | 49.4
|  | 508 |  |  |  | 508 |  | 508 |  | 508 |  | 508 |  | 508 |  | 508 |  | 508 |  | 508 |  |  |  | 508 |  | 508 |  | 508 |  | 508 |  | 482.6 |  | 482.6 |  | 482.6 |  | 482.6
B | Type EWS 701-louvered wall system (including aluminium panels) | 1795 | m2 | 2012 | 3611540 | 1795 | 677163.75 | 1795 | 948029.25 | 1795 | 948029.25 | 1795 | 135432.75 | 1795 | 225721.25 | 1795 | 316009.75 | 1795 | 316009.75 | 1795 | 45144.25 | 100% | 3611540 | 1736.5763 | 655123.425 | 1736.5763 | 917172.795 | 1736.5763 | 917172.795 | 1736.5763 | 131024.685 | 1736.5763 | 218374.475 | 1736.5763 | 305724.265 | 1736.5763 | 305724.265 | 1736.5763 | 43674.895 | 96.75% | 3493991.6 | 58.4237 | 22040.325 | 58.4237 | 30856.455 | 58.4237 | 30856.455 | 58.4237 | 4408.065 | 58.4237 | 7346.775 | 58.4237 | 10285.485 | 58.4237 | 10285.485 | 58.4237 | 1469.355 | 3.255% | 117548.4 |  | 58.4237 | 100% | 22040.325 | 58.4237 | 100% | 30856.455 | 58.4237 | 100% | 30856.455 | 58.4237 | 100% | 4408.065 | 58.4237 | 100% | 7346.775 | 58.4237 | 100% | 10285.485 | 58.4237 | 100% | 10285.485 | 58.4237 | 90% | 1322.4195 | 99.88% | 117401.4645 | 0% | 0 | 99.88% | 117401.4645 | 99.88% | 117401.4645 | 99.88% | 117401.4645 |  |  |  |  | 117401.4645 |  |  |  | 48% |  | MOS |  | 3493991.6 | 117548.4 | 3611540 | 3.255% | 1736.5763
| Aluminum Panel for EWS-701 size 1.4 (Folded Length) |  |  | 0 | Included | [99 empty] | #REF!
| Aluminum Panel for EWS-701 size 0.87 (Folded Length) |  |  | 0 | Included
[59 empty] | 126716.8 | [29 empty] | 99.85% | 126524.0225 | 99.85% | 126524.0225 | 95% | 126524.0225 | 9122.558 |  |  |  | 117401.4645
Doors
C | Door Type D-23 | 9 | Nr. | 13750 | 123750 | 9 | 23203.125 | 9 | 32484.375 | 9 | 32484.375 | 9 | 4640.625 | 9 | 7734.375 | 9 | 10828.125 | 9 | 10828.125 | 9 | 1546.875 | 100% | 123750 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 9 | 23203.125 | 9 | 32484.375 | 9 | 32484.375 | 9 | 4640.625 | 9 | 7734.375 | 9 | 10828.125 | 9 | 10828.125 | 9 | 1546.875 | 100% | 123750 |  | 9 | 30% | 6960.9375 | 9 | 30% | 9745.3125 | 9 | 30% | 9745.3125 | 9 | 30% | 1392.1875 | 9 | 25% | 1933.5938 | 9 | 25% | 2707.0312 | 9 |  | 0 | 9 |  | 0 | 1.875% | 2320.3125 | 24.38% | 30164.0625 | 26.25% | 32484.375 | 26.25% | 32484.375 |  | 111375
D | Door Type D-16,Folding Door | 1 | Nr. | 107978 | 107978 | 1 | 20245.875 | 1 | 28344.225 | 1 | 28344.225 | 1 | 4049.175 | 1 | 6748.625 | 1 | 9448.075 | 1 | 9448.075 | 1 | 1349.725 | 100% | 107978 | 1 | 20245.875 | 1 | 28344.225 | 1 | 28344.225 | 1 | 4049.175 | 1 | 6748.625 | 1 | 9448.075 | 1 | 9448.075 | 1 | 1349.725 | 100% | 107978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0% | 0 |  | 0 |  | 0 | [14 empty] | 107978 | 0 | 107978 | 0% | 1
[59 empty] | 123750 | [29 empty] | 26.25% | 32484.375 | 26.25% | 32484.375 | 90% | 111375 |  |  | 111375
Apartment Level 6 to 31
A | Type EWS-103 (Straight including openable sliding doors) | 6980 | m2 | 1176 | 8208480 | 6980 | 1539090 | 6980 | 2154726 | 6980 | 2154726 | 6980 | 307818 | 6980 | 513030 | 6980 | 718242 | 6980 | 718242 | 6980 | 102606 | 100% | 8208480 | 6980 | 1539090 | 6980 | 2154726 | 6980 | 2154726 | 6980 | 307818 | 6976.2641 | 512755.4115 | 6976.2641 | 717857.5761 | 6976.2641 | 717857.5761 | 6976.2641 | 102551.0823 | 99.99% | 8207381.6459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7359 | 274.5885 | 3.7359 | 384.4239 | 3.7359 | 384.4239 | 3.7359 | 54.9177 | 0.01338% | 1098.3541 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 3.7359 | 100% | 274.5885 | 3.7359 |  | 0 | 3.7359 |  | 0 | 3.7359 |  | 0 | 25% | 274.5885 | 0% | 0 | 25% | 274.5885 | 25% | 274.5885 | [14 empty] | 8207381.6459 | 1098.3541 | 2052120 | 0.05352% | 6976.2641
| Openable/Sliding for EWS-103 size 2.25 x 3.1 |  |  | 0 | Included
B | Type EWS-104 (Straight including openable sliding doors) | 1179 | m2 | 1152 | 1358208 | 1179 | 254664 | 1179 | 356529.6 | 1179 | 356529.6 | 1179 | 50932.8 | 1179 | 84888 | 1179 | 118843.2 | 1179 | 118843.2 | 1179 | 16977.6 | 100% | 1358208 | 1179 | 254664 | 1179 | 356529.6 | 1179 | 356529.6 | 1179 | 50932.8 | 1178.369 | 84842.5655 | 1178.369 | 118779.5917 | 1178.369 | 118779.5917 | 1178.369 | 16968.5131 | 99.99% | 1358026.2619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.63103 | 45.4345 | 0.63103 | 63.6083 | 0.63103 | 63.6083 | 0.63103 | 9.0869 | 0.01338% | 181.7381 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0.63103 | 100% | 45.4345 | 0.63103 |  | 0 | 0.63103 |  | 0 | 0.63103 |  | 0 | 25% | 45.4345 | 0% | 0 | 25% | 45.4345 | 25% | 45.4345 | [14 empty] | 1358026.2619 | 181.7381 | 339552 | 0.05352% | 1178.369
| Openable/Sliding for EWS-104 size 2.25 x 3.1 |  |  | 0 | Included
C | Type EWS-110 (Straight including all louvres) | 3551 | m2 | 1269 | 4506219 | 3551 | 844916.0625 | 3551 | 1182882.4875 | 3551 | 1182882.4875 | 3551 | 168983.2125 | 3551 | 281638.6875 | 3551 | 394294.1625 | 3551 | 394294.1625 | 3551 | 56327.7375 | 100% | 4506219 | 3551 | 844916.0625 | 3551 | 1182882.4875 | 3551 | 1182882.4875 | 3551 | 168983.2125 | 2111.7764 | 167490.2619 | 2111.7764 | 234486.3666 | 2111.7764 | 234486.3666 | 2111.7764 | 33498.0524 | 89.87% | 4049625.2974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.2236 | 114148.4256 | 1439.2236 | 159807.7959 | 1439.2236 | 159807.7959 | 1439.2236 | 22829.6851 | 10.13% | 456593.7026 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1439.2236 | 100% | 114148.4256 | 1439.2236 | 100% | 159807.7959 | 1439.2236 | 100% | 159807.7959 | 1439.2236 | 50% | 11414.8426 | 97.5% | 445178.86 | 0% | 0 | 97.5% | 445178.86 | 97.5% | 445178.86 | [14 empty] | 4049625.2974 | 456593.7026 | 1126554.75 | 40.53% | 2111.7764
| Extra over Louver for EWS-110 size 0.65 x 3.8 |  |  | 0 | Included
| Extra over Louver for EWS-110 size 0.65 x 3.65 |  |  | 0 | Included
| Extra over Louver for EWS-110 size 0.65 x 4 |  |  | 0 | Included
| Extra over Louver for EWS-110 size 0.65 x 4.65 |  |  | 0 | Included
| Extra over Louver for EWS-110 size 0.65 x 3 |  |  | 0 | Included
D | Type EWS-111 (Straight including doors) |  | m2 | 0 | Included
| Extra over Door Type D-7 for EWS-111 size 2 x 2.7 | 2 | Nos | 12500 | 25000 | 2 | 4687.5 | 2 | 6562.5 | 2 | 6562.5 | 2 | 937.5 | 2 | 1562.5 | 2 | 2187.5 | 2 | 2187.5 | 2 | 312.5 | 100% | 25000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 2 | 4687.5 | 2 | 6562.5 | 2 | 6562.5 | 2 | 937.5 | 2 | 1562.5 | 2 | 2187.5 | 2 | 2187.5 | 2 | 312.5 | 100% | 25000 |  | 2 |  | 0 | 2 |  | 0 | 2 |  | 0 | 2 |  | 0 | 2 |  | 0 | 2 |  | 0 | 2 |  | 0 | 2 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0
E | Type EWS-112 (Curved) | 567 | m2 | 1721 | 975807 | 567 | 182963.8125 | 567 | 256149.3375 | 567 | 256149.3375 | 567 | 36592.7625 | 567 | 60987.9375 | 567 | 85383.1125 | 567 | 85383.1125 | 567 | 12197.5875 | 100% | 975807 | 567 | 182963.8125 | 567 | 256149.3375 | 567 | 256149.3375 | 567 | 36592.7625 | 567 | 60987.9375 | 567 | 85383.1125 | 567 | 85383.1125 | 567 | 12197.5875 | 100% | 975807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0% | 0 |  | 0 |  | 0 | [14 empty] | 975807 | 0 | 243951.75 | 0% | 567
F | Type EWS-151(Straight including openable sliding doors) | 1825 | m2 | 1220 | 2226500 | 1825 | 417468.75 | 1825 | 584456.25 | 1825 | 584456.25 | 1825 | 83493.75 | 1825 | 139156.25 | 1825 | 194818.75 | 1825 | 194818.75 | 1825 | 27831.25 | 100% | 2226500 | 1825 | 417468.75 | 1825 | 584456.25 | 1825 | 584456.25 | 1825 | 83493.75 | 1803.556 | 137521.1414 | 1803.556 | 192529.5979 | 1803.556 | 192529.5979 | 1803.556 | 27504.2283 | 99.71% | 2219959.5654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.444 | 1635.1086 | 21.444 | 2289.1521 | 21.444 | 2289.1521 | 21.444 | 327.0217 | 0.2938% | 6540.4346 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 21.444 | 100% | 1635.1086 | 21.444 | 100% | 2289.1521 | 21.444 | 100% | 2289.1521 | 21.444 | 90% | 294.3196 | 99.5% | 6507.7324 | 0% | 0 | 99.5% | 6507.7324 | 99.5% | 6507.7324 | [14 empty] | 2219959.5654 | 6540.4346 | 556625 | 1.175% | 1803.556
| Sliding for EWS-151 size 2.25 x 3.2 |  |  | 0 | Included
G | Type EWS-703 (Straight and Curved) |  | m2 | 0 | Excluded(VE)
[59 empty] | 489414.2294 | [29 empty] | 92.36% | 452006.6155 | 92.36% | 452006.6155 | 85% | 416002.095 |  | 416002.095
Doors
H | Door Type D-23 | 3 | Nr. | 13440 | 40320 | 3 | 7560 | 3 | 10584 | 3 | 10584 | 3 | 1512 | 3 | 2520 | 3 | 3528 | 3 | 3528 | 3 | 504 | 100% | 40320 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 3 | 7560 | 3 | 10584 | 3 | 10584 | 3 | 1512 | 3 | 2520 | 3 | 3528 | 3 | 3528 | 3 | 504 | 100% | 40320 |  | 3 |  | 0 | 3 |  | 0 | 3 |  | 0 | 3 |  | 0 | 3 |  | 0 | 3 |  | 0 | 3 |  | 0 | 3 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0
J | Door Type D-8 Size 1200x2100mm | 5 | Nr. | 6800 | 34000 | 5 | 6375 | 5 | 8925 | 5 | 8925 | 5 | 1275 | 5 | 2125 | 5 | 2975 | 5 | 2975 | 5 | 425 | 100% | 34000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 5 | 6375 | 5 | 8925 | 5 | 8925 | 5 | 1275 | 5 | 2125 | 5 | 2975 | 5 | 2975 | 5 | 425 | 100% | 34000 |  | 5 |  | 0 | 5 |  | 0 | 5 |  | 0 | 5 |  | 0 | 5 |  | 0 | 5 |  | 0 | 5 |  | 0 | 5 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0
[59 empty] | 74320 | [29 empty] | 0% | 0 |  | 0
Hotel Level 7 to 29
A | Type EWS-103 (Straight and Curved and including openable sliding doors) | 6397 | m2 | 1130 | 7228610 | 6397 | 1355364.375 | 6397 | 1897510.125 | 6397 | 1897510.125 | 6397 | 271072.875 | 6397 | 451788.125 | 6397 | 632503.375 | 6397 | 632503.375 | 6397 | 90357.625 | 100% | 7228610 | 6397 | 1355364.375 | 6397 | 1897510.125 | 6397 | 1897510.125 | 6397 | 271072.875 | 5817.0594 | 410829.821 | 5817.0594 | 575161.7494 | 5817.0594 | 575161.7494 | 5817.0594 | 82165.9642 | 97.73% | 7064776.7841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579.9406 | 40958.304 | 579.9406 | 57341.6256 | 579.9406 | 57341.6256 | 579.9406 | 8191.6608 | 2.266% | 163833.2159 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 579.9406 | 100% | 40958.304 | 579.9406 | 100% | 57341.6256 | 579.9406 | 100% | 57341.6256 | 579.9406 |  | 0 | 95% | 155641.5551 | 0% | 0 | 95% | 155641.5551 | 95% | 155641.5551 | [10 empty] | EWS-103/111 |  |  |  | 7064776.7841 | 163833.2159 | 1807152.5 | 9.066% | 5817.0594
| Openable/Sliding for EWS-103 size 2.25 x 3.1 |  |  | 0 | Included
B | Type EWS-104 (Straight including openable sliding doors) | 1815 | m2 | 1140 | 2069100 | 1815 | 387956.25 | 1815 | 543138.75 | 1815 | 543138.75 | 1815 | 77591.25 | 1815 | 129318.75 | 1815 | 181046.25 | 1815 | 181046.25 | 1815 | 25863.75 | 100% | 2069100 | 1815 | 387956.25 | 1815 | 543138.75 | 1815 | 543138.75 | 1815 | 77591.25 | 1650.4553 | 117594.9432 | 1650.4553 | 164632.9205 | 1650.4553 | 164632.9205 | 1650.4553 | 23518.9886 | 97.73% | 2022204.773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164.5447 | 11723.8068 | 164.5447 | 16413.3295 | 164.5447 | 16413.3295 | 164.5447 | 2344.7614 | 2.266% | 46895.227 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 164.5447 | 100% | 11723.8068 | 164.5447 | 100% | 16413.3295 | 164.5447 | 100% | 16413.3295 | 164.5447 |  | 0 | 95% | 44550.4657 | 0% | 0 | 95% | 44550.4657 | 95% | 44550.4657 | [10 empty] | EWS-104 |  |  |  | 2022204.773 | 46895.227 | 517275 | 9.066% | 1650.4553
| Openable/Sliding for EWS-104 size 2.25 x 3.1 |  |  | 0 | Included | [101 empty] | 0
C | Type EWS-110 (Straight including louvres) | 3499 | m2 | 1311 | 4587189 | 3499 | 860097.9375 | 3499 | 1204137.1125 | 3499 | 1204137.1125 | 3499 | 172019.5875 | 3499 | 286699.3125 | 3499 | 401379.0375 | 3499 | 401379.0375 | 3499 | 57339.8625 | 100% | 4587189 | 3499 | 860097.9375 | 3499 | 1204137.1125 | 3499 | 1204137.1125 | 3499 | 172019.5875 | 3477.6147 | 284947.056 | 3477.6147 | 398925.8784 | 3477.6147 | 398925.8784 | 3477.6147 | 56989.4112 | 99.85% | 4580179.9741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.3853 | 1752.2565 | 21.3853 | 2453.1591 | 21.3853 | 2453.1591 | 21.3853 | 350.4513 | 0.1528% | 7009.0259 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 21.3853 | 100% | 1752.2565 | 21.3853 | 100% | 2453.1591 | 21.3853 | 100% | 2453.1591 | 21.3853 |  | 0 | 95% | 6658.5746 | 0% | 0 | 95% | 6658.5746 | 95% | 6658.5746 | [10 empty] | EWS-110 |  |  |  | 4580179.9741 | 7009.0259 | 1146797.25 | 0.6112% | 3477.6147
| Extra over Top Hung Window for EWS-110 size 0.65 x 2 | 22 | Nos | 19042.3635 | 418931.997 | 22 | 78549.7494 | 22 | 109969.6492 | 22 | 109969.6492 | 22 | 15709.9499 | 22 | 26183.2498 | 22 | 36656.5497 | 22 | 36656.5497 | 22 | 5236.65 | 100% | 418931.997 | 22 | 78549.7494 | 22 | 109969.6492 | 22 | 109969.6492 | 22 | 15709.9499 | 22 | 26183.2498 | 22 | 36656.5497 | 22 | 36656.5497 | 22 | 5236.65 | 100% | 418931.997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0% | 0 |  | 0 |  | 0 | [14 empty] | 418932 | -0.003 | 418931.997 | -7.161e-07% | 22
| Actuators |  |  |  | Included
| Extra over Louver for EWS-110 size 0.65 x 2 |  |  |  | Included
D | Type EWS-111 (Straight including doors) |  | m2 | 0 | Included
| Extra over Door Type D-8 for EWS-111 size 1.2 x 3 | 4 | Nos | 6850 | 27400 | 4 | 5137.5 | 4 | 7192.5 | 4 | 7192.5 | 4 | 1027.5 | 4 | 1712.5 | 4 | 2397.5 | 4 | 2397.5 | 4 | 342.5 | 100% | 27400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 4 | 5137.5 | 4 | 7192.5 | 4 | 7192.5 | 4 | 1027.5 | 4 | 1712.5 | 4 | 2397.5 | 4 | 2397.5 | 4 | 342.5 | 100% | 27400 |  | 4 |  | 0 | 4 |  | 0 | 4 |  | 0 | 4 |  | 0 | 4 |  | 0 | 4 |  | 0 | 4 |  | 0 | 4 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0
E | Type EWS-112 (Curved) | 595 | m2 | 1698 | 1010310 | 595 | 189433.125 | 595 | 265206.375 | 595 | 265206.375 | 595 | 37886.625 | 595 | 63144.375 | 595 | 88402.125 | 595 | 88402.125 | 595 | 12628.875 | 100% | 1010310 | 595 | 189433.125 | 595 | 265206.375 | 595 | 265206.375 | 595 | 37886.625 | 486.2464 | 51602.9027 | 486.2464 | 72244.0638 | 486.2464 | 72244.0638 | 486.2464 | 10320.5805 | 95.43% | 964144.111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108.7536 | 11541.4723 | 108.7536 | 16158.0612 | 108.7536 | 16158.0612 | 108.7536 | 2308.2945 | 4.569% | 46165.889 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 108.7536 | 100% | 11541.4723 | 108.7536 | 100% | 16158.0612 | 108.7536 | 100% | 16158.0612 | 108.7536 | 100% | 2308.2945 | 100% | 46165.889 | 0% | 0 | 100% | 46165.889 | 100% | 46165.889 | [10 empty] | EWS-112 |  |  |  | 964144.111 | 46165.889 | 252577.5 | 18.28% | 486.2464
F | Type EWS-703 (Straight and Curved) |  | m2 | 0 | Excluded(VE)
[59 empty] | 291303.3578 | [29 empty] | 86.86% | 253016.4844 | 86.86% | 253016.4844 | 85% | 247607.8542 |  | 247607.8542
Doors
G | Door Type D-23 | 2 | Nr. | 12500 | 25000 | 2 | 4687.5 | 2 | 6562.5 | 2 | 6562.5 | 2 | 937.5 | 2 | 1562.5 | 2 | 2187.5 | 2 | 2187.5 | 2 | 312.5 | 100% | 25000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 2 | 4687.5 | 2 | 6562.5 | 2 | 6562.5 | 2 | 937.5 | 2 | 1562.5 | 2 | 2187.5 | 2 | 2187.5 | 2 | 312.5 | 100% | 25000 |  | 2 |  | 0 | 2 |  | 0 | 2 |  | 0 | 2 |  | 0 | 2 |  | 0 | 2 |  | 0 | 2 |  | 0 | 2 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0
H | Door Type D-21 | 3 | Nr. | 12500 | 37500 | 3 | 7031.25 | 3 | 9843.75 | 3 | 9843.75 | 3 | 1406.25 | 3 | 2343.75 | 3 | 3281.25 | 3 | 3281.25 | 3 | 468.75 | 100% | 37500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 3 | 7031.25 | 3 | 9843.75 | 3 | 9843.75 | 3 | 1406.25 | 3 | 2343.75 | 3 | 3281.25 | 3 | 3281.25 | 3 | 468.75 | 100% | 37500 |  | 3 |  | 0 | 3 |  | 0 | 3 |  | 0 | 3 |  | 0 | 3 |  | 0 | 3 |  | 0 | 3 |  | 0 | 3 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0
J | Door Type D-7 | 2 | Nr. | 6700 | 13400 | 2 | 2512.5 | 2 | 3517.5 | 2 | 3517.5 | 2 | 502.5 | 2 | 837.5 | 2 | 1172.5 | 2 | 1172.5 | 2 | 167.5 | 100% | 13400 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 2 | 2512.5 | 2 | 3517.5 | 2 | 3517.5 | 2 | 502.5 | 2 | 837.5 | 2 | 1172.5 | 2 | 1172.5 | 2 | 167.5 | 100% | 13400 |  | 2 |  | 0 | 2 |  | 0 | 2 |  | 0 | 2 |  | 0 | 2 |  | 0 | 2 |  | 0 | 2 |  | 0 | 2 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0
[59 empty] | 75900 | [29 empty] | 0% | 0 |  |  |  | 0 |  |  |  | 0
K | Reintroduction of the Hotel Balcony area refer to façade commented drawings. (LV07 to LV30) | 1 | Item | 412713 | 412713 | 1 | 77383.6875 | 1 | 108337.1625 | 1 | 108337.1625 | 1 | 15476.7375 | 1 | 25794.5625 | 1 | 36112.3875 | 1 | 36112.3875 | 1 | 5158.9125 | 100% | 412713 | 1 | 77383.6875 | 1 | 108337.1625 | 1 | 108337.1625 | 1 | 15476.7375 | 0.97806 | 25228.592 | 0.97806 | 35320.0287 | 0.97806 | 35320.0287 | 0.97806 | 5045.7184 | 99.45% | 410449.1178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021941 | 565.9705 | 0.021941 | 792.3588 | 0.021941 | 792.3588 | 0.021941 | 113.1941 | 0.5485% | 2263.8822 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0.021941 |  | 0 | 0.021941 |  | 0 | 0.021941 |  | 0 | 0.021941 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | [16 empty] | 410449.1178 | 2263.8822 | 103178.25 | 2.194% | 0.97806
ROOF CANOPIES
Duplex stainless steel composite or aluminum honeycomb panels including complete steel frame all necessary fixing, fittings and accessories
A | Hotel tower ceiling soffit as shown on drawing F-40-01 | 700 | m2 | 1309 | 916300 | 700 | 171806.25 | 700 | 240528.75 | 700 | 240528.75 | 700 | 34361.25 | 700 | 57268.75 | 700 | 80176.25 | 700 | 80176.25 | 700 | 11453.75 | 100% | 916300 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 700 | 171806.25 | 700 | 240528.75 | 700 | 240528.75 | 700 | 34361.25 | 700 | 57268.75 | 700 | 80176.25 | 700 | 80176.25 | 700 | 11453.75 | 100% | 916300 |  | 700 | 100% | 171806.25 | 700 | 100% | 240528.75 | 700 | 100% | 240528.75 | 700 |  | 0 | 700 | 92% | 52687.25 | 700 | 92% | 73762.15 | 700 | 60% | 48105.75 | 700 |  | 0 | 89.42% | 819401.275 | 0.875% | 8017.625 | 90.3% | 827418.9 | 91.91% | 842194.2375 | 85% | 778855
B | Apartment tower ceiling soffit as shown on drawing F-40-02 | 1425 | Item | 947 | 1349475 | 1425 | 253026.5625 | 1425 | 354237.1875 | 1425 | 354237.1875 | 1425 | 50605.3125 | 1425 | 84342.1875 | 1425 | 118079.0625 | 1425 | 118079.0625 | 1425 | 16868.4375 | 100% | 1349475 | 1378.6191 | 244791.0544 | 1378.6191 | 342707.4761 | 1378.6191 | 342707.4761 | 1378.6191 | 48958.2109 | 1378.6191 | 81597.0181 | 1378.6191 | 114235.8254 | 1378.6191 | 114235.8254 | 1378.6191 | 16319.4036 | 96.75% | 1305552.29 | 46.3809 | 8235.5081 | 46.3809 | 11529.7114 | 46.3809 | 11529.7114 | 46.3809 | 1647.1016 | 46.3809 | 2745.1694 | 46.3809 | 3843.2371 | 46.3809 | 3843.2371 | 46.3809 | 549.0339 | 3.255% | 43922.71 |  | 46.3809 |  | 0 | 46.3809 |  | 0 | 46.3809 |  | 0 | 46.3809 |  | 0 | 46.3809 |  | 0 | 46.3809 |  | 0 | 46.3809 |  | 0 | 46.3809 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | [14 empty] | 1305552.29 | 43922.71 | 1349475 | 3.255% | 1378.6191
[59 empty] | 962486.5922 | [29 empty] | 85.97% | 827418.9 | 87.5% | 842194.2375 | 80.92% | 778855 | [5 empty] | 778855
Additional Items
Ground and 1st Levels
H | Type EWS -123 (Straight) | 63 | m2 | 1050 | 66150 | 63 | 12403.125 | 63 | 17364.375 | 63 | 17364.375 | 63 | 2480.625 | 63 | 4134.375 | 63 | 5788.125 | 63 | 5788.125 | 63 | 826.875 | 100% | 66150 | 29.5048 | 5808.7598 | 29.5048 | 8132.2637 | 29.5048 | 8132.2637 | 29.5048 | 1161.752 | 29.5048 | 1936.2533 | 29.5048 | 2710.7546 | 29.5048 | 2710.7546 | 29.5048 | 387.2507 | 46.83% | 30980.052 | 33.4952 | 6594.3652 | 33.4952 | 9232.1113 | 33.4952 | 9232.1113 | 33.4952 | 1318.873 | 33.4952 | 2198.1217 | 33.4952 | 3077.3704 | 33.4952 | 3077.3704 | 33.4952 | 439.6243 | 53.17% | 35169.948 |  | 33.4952 |  | 0 | 33.4952 |  | 0 | 33.4952 |  | 0 | 33.4952 |  | 0 | 33.4952 |  | 0 | 33.4952 |  | 0 | 33.4952 |  | 0 | 33.4952 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | [13 empty] | Hotel - Entrance Lobby |  |  | 30980.052 | 35169.948 | 66150 | 53.17% | 29.5048
| Automatic Door Type EWS-123 | 4 | Nos | 50700 | 202800 | 4 | 38025 | 4 | 53235 | 4 | 53235 | 4 | 7605 | 4 | 12675 | 4 | 17745 | 4 | 17745 | 4 | 2535 | 100% | 202800 | 1.8733 | 17808.2612 | 1.8733 | 24931.5657 | 1.8733 | 24931.5657 | 1.8733 | 3561.6522 | 1.8733 | 5936.0871 | 1.8733 | 8310.5219 | 1.8733 | 8310.5219 | 1.8733 | 1187.2174 | 46.83% | 94977.3931 | 2.1267 | 20216.7388 | 2.1267 | 28303.4343 | 2.1267 | 28303.4343 | 2.1267 | 4043.3478 | 2.1267 | 6738.9129 | 2.1267 | 9434.4781 | 2.1267 | 9434.4781 | 2.1267 | 1347.7826 | 53.17% | 107822.6069 |  | 2.1267 |  | 0 | 2.1267 |  | 0 | 2.1267 |  | 0 | 2.1267 |  | 0 | 2.1267 |  | 0 | 2.1267 |  | 0 | 2.1267 |  | 0 | 2.1267 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 |  |  | Included | [13 empty] | 94977.3931 | 107822.6069 | 202800 | 53.17% | 1.8733
| Door Type D-8 1100x3000mm | 1 | Nr. | 6750 | 6750 | 1 | 1265.625 | 1 | 1771.875 | 1 | 1771.875 | 1 | 253.125 | 1 | 421.875 | 1 | 590.625 | 1 | 590.625 | 1 | 84.375 | 100% | 6750 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 1 | 1265.625 | 1 | 1771.875 | 1 | 1771.875 | 1 | 253.125 | 1 | 421.875 | 1 | 590.625 | 1 | 590.625 | 1 | 84.375 | 100% | 6750 |  | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 |  |  | Included
| Door Type D-7 size 2.2 x 3 | 2 | Nr. | 12500 | 25000 | 2 | 4687.5 | 2 | 6562.5 | 2 | 6562.5 | 2 | 937.5 | 2 | 1562.5 | 2 | 2187.5 | 2 | 2187.5 | 2 | 312.5 | 100% | 25000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 2 | 4687.5 | 2 | 6562.5 | 2 | 6562.5 | 2 | 937.5 | 2 | 1562.5 | 2 | 2187.5 | 2 | 2187.5 | 2 | 312.5 | 100% | 25000 |  | 2 |  | 0 | 2 |  | 0 | 2 |  | 0 | 2 |  | 0 | 2 |  | 0 | 2 |  | 0 | 2 |  | 0 | 2 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 |  |  | Included
| Window Type05-2 size 5.46m x 2.3m | 1 | Nr. | 16141 | 16141 | 1 | 3026.4375 | 1 | 4237.0125 | 1 | 4237.0125 | 1 | 605.2875 | 1 | 1008.8125 | 1 | 1412.3375 | 1 | 1412.3375 | 1 | 201.7625 | 100% | 16141 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 1 | 3026.4375 | 1 | 4237.0125 | 1 | 4237.0125 | 1 | 605.2875 | 1 | 1008.8125 | 1 | 1412.3375 | 1 | 1412.3375 | 1 | 201.7625 | 100% | 16141 |  | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 |  |  | Included
| Window Type05-1 size 14.3m x 2.3m | 1 | Nr. | 40654 | 40654 | 1 | 7622.625 | 1 | 10671.675 | 1 | 10671.675 | 1 | 1524.525 | 1 | 2540.875 | 1 | 3557.225 | 1 | 3557.225 | 1 | 508.175 | 100% | 40654 | 1 | 7622.625 | 1 | 10671.675 | 1 | 10671.675 | 1 | 1524.525 | 1 | 2540.875 | 1 | 3557.225 | 1 | 3557.225 | 1 | 508.175 | 100% | 40654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0% | 0 |  | 0 | [16 empty] | 40654 | 0 | 40654 | 0% | 1
[59 empty] | 190883.5548 | [29 empty] | 0% | 0
2nd and 3rd Levels
| Glass Partition 3100mm (H) | 110 | m2 | 1245 | 136950 | 110 | 25678.125 | 110 | 35949.375 | 110 | 35949.375 | 110 | 5135.625 | 110 | 8559.375 | 110 | 11983.125 | 110 | 11983.125 | 110 | 1711.875 | 100% | 136950 | 81.8357 | 19103.5289 | 81.8357 | 26744.9405 | 81.8357 | 26744.9405 | 81.8357 | 3820.7058 | 81.8357 | 6367.843 | 81.8357 | 8914.9802 | 81.8357 | 8914.9802 | 81.8357 | 1273.5686 | 74.4% | 101885.4877 | 28.1643 | 6574.5961 | 28.1643 | 9204.4345 | 28.1643 | 9204.4345 | 28.1643 | 1314.9192 | 28.1643 | 2191.532 | 28.1643 | 3068.1448 | 28.1643 | 3068.1448 | 28.1643 | 438.3064 | 25.6% | 35064.5123 |  | 28.1643 |  | 0 | 28.1643 |  | 0 | 28.1643 |  | 0 | 28.1643 |  | 0 | 28.1643 |  | 0 | 28.1643 |  | 0 | 28.1643 |  | 0 | 28.1643 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | [16 empty] | 101885.4877 |  |  | 74.4% | 81.8357
| Extra over Door Type D-8 size 0.8 x 2.1 | 5 | Nr. | 6000 | 30000 | 5 | 5625 | 5 | 7875 | 5 | 7875 | 5 | 1125 | 5 | 1875 | 5 | 2625 | 5 | 2625 | 5 | 375 | 100% | 30000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 5 | 5625 | 5 | 7875 | 5 | 7875 | 5 | 1125 | 5 | 1875 | 5 | 2625 | 5 | 2625 | 5 | 375 | 100% | 30000 |  | 5 |  | 0 | 5 |  | 0 | 5 |  | 0 | 5 |  | 0 | 5 |  | 0 | 5 |  | 0 | 5 |  | 0 | 5 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0
| LW-11 size 9m x 2.4m | 1 | no. | 43978 | 43978 | 1 | 8245.875 | 1 | 11544.225 | 1 | 11544.225 | 1 | 1649.175 | 1 | 2748.625 | 1 | 3848.075 | 1 | 3848.075 | 1 | 549.725 | 100% | 43978 | 0.74396 | 6134.6111 | 0.74396 | 8588.4556 | 0.74396 | 8588.4556 | 0.74396 | 1226.9222 | 0.74396 | 2044.8704 | 0.74396 | 2862.8185 | 0.74396 | 2862.8185 | 0.74396 | 408.9741 | 74.4% | 32717.9261 | 0.25604 | 2111.2639 | 0.25604 | 2955.7694 | 0.25604 | 2955.7694 | 0.25604 | 422.2528 | 0.25604 | 703.7546 | 0.25604 | 985.2565 | 0.25604 | 985.2565 | 0.25604 | 140.7509 | 25.6% | 11260.0739 |  | 0.25604 |  | 0 | 0.25604 |  | 0 | 0.25604 |  | 0 | 0.25604 |  | 0 | 0.25604 |  | 0 | 0.25604 |  | 0 | 0.25604 |  | 0 | 0.25604 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | [16 empty] | 32717.9261 | 11260.0739 | 43978 | 25.6% | 0.74396
| LW-12 size 6.74m x 2.4m | 1 | no. | 32934 | 32934 | 1 | 6175.125 | 1 | 8645.175 | 1 | 8645.175 | 1 | 1235.025 | 1 | 2058.375 | 1 | 2881.725 | 1 | 2881.725 | 1 | 411.675 | 100% | 32934 | 0.74396 | 4594.0535 | 0.74396 | 6431.6749 | 0.74396 | 6431.6749 | 0.74396 | 918.8107 | 0.74396 | 1531.3512 | 0.74396 | 2143.8916 | 0.74396 | 2143.8916 | 0.74396 | 306.2702 | 74.4% | 24501.6185 | 0.25604 | 1581.0715 | 0.25604 | 2213.5001 | 0.25604 | 2213.5001 | 0.25604 | 316.2143 | 0.25604 | 527.0238 | 0.25604 | 737.8334 | 0.25604 | 737.8334 | 0.25604 | 105.4048 | 25.6% | 8432.3815 |  | 0.25604 |  | 0 | 0.25604 |  | 0 | 0.25604 |  | 0 | 0.25604 |  | 0 | 0.25604 |  | 0 | 0.25604 |  | 0 | 0.25604 |  | 0 | 0.25604 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | [16 empty] | 24501.6185 | 8432.3815 | 32934 | 25.6% | 0.74396
| LW-11a size 7.85m x 0.9m | 2 | no. | 14384 | 28768 | 2 | 5394 | 2 | 7551.6 | 2 | 7551.6 | 2 | 1078.8 | 2 | 1798 | 2 | 2517.2 | 2 | 2517.2 | 2 | 359.6 | 100% | 28768 | 1.4879 | 4012.9268 | 1.4879 | 5618.0975 | 1.4879 | 5618.0975 | 1.4879 | 802.5854 | 1.4879 | 1337.6423 | 1.4879 | 1872.6992 | 1.4879 | 1872.6992 | 1.4879 | 267.5285 | 74.4% | 21402.2761 | 0.51208 | 1381.0732 | 0.51208 | 1933.5025 | 0.51208 | 1933.5025 | 0.51208 | 276.2146 | 0.51208 | 460.3577 | 0.51208 | 644.5008 | 0.51208 | 644.5008 | 0.51208 | 92.0715 | 25.6% | 7365.7239 |  | 0.51208 |  | 0 | 0.51208 |  | 0 | 0.51208 |  | 0 | 0.51208 |  | 0 | 0.51208 |  | 0 | 0.51208 |  | 0 | 0.51208 |  | 0 | 0.51208 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | [16 empty] | 21402.2761 | 7365.7239 | 28768 | 25.6% | 1.4879
| LW-11b size 14m x 0.9m | 2 | no. | 25654 | 51308 | 2 | 9620.25 | 2 | 13468.35 | 2 | 13468.35 | 2 | 1924.05 | 2 | 3206.75 | 2 | 4489.45 | 2 | 4489.45 | 2 | 641.35 | 100% | 51308 | 1.4879 | 7157.0928 | 1.4879 | 10019.93 | 1.4879 | 10019.93 | 1.4879 | 1431.4186 | 1.4879 | 2385.6976 | 1.4879 | 3339.9767 | 1.4879 | 3339.9767 | 1.4879 | 477.1395 | 74.4% | 38171.1618 | 0.51208 | 2463.1572 | 0.51208 | 3448.42 | 0.51208 | 3448.42 | 0.51208 | 492.6314 | 0.51208 | 821.0524 | 0.51208 | 1149.4733 | 0.51208 | 1149.4733 | 0.51208 | 164.2105 | 25.6% | 13136.8382 |  | 0.51208 |  | 0 | 0.51208 |  | 0 | 0.51208 |  | 0 | 0.51208 |  | 0 | 0.51208 |  | 0 | 0.51208 |  | 0 | 0.51208 |  | 0 | 0.51208 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | [16 empty] | 38171.1618 | 13136.8382 | 51308 | 25.6% | 1.4879
| Door Type D-7 size 2.2 x 3 | 2 | Nr. | 0 | Included
| Door Type D-8 size 1250x 2975mm | 1 | Nr. | 0 | Included
[59 empty] | 105259.5299 | [29 empty] | 0% | 0
Apartment 4th & 5th Levels and Hotel 4th to 6th Levels
SA-CW | Type EWS-110 | 115 | m2 | 1207 | 138805 | 115 | 26025.9375 | 115 | 36436.3125 | 115 | 36436.3125 | 115 | 5205.1875 | 115 | 8675.3125 | 115 | 12145.4375 | 115 | 12145.4375 | 115 | 1735.0625 | 100% | 138805 | 115 | 26025.9375 | 115 | 36436.3125 | 115 | 36436.3125 | 115 | 5205.1875 | 108.1 | 8154.7938 | 108.1 | 11416.7113 | 108.1 | 11416.7113 | 108.1 | 1630.9588 | 98.5% | 136722.925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.9 | 520.5187 | 6.9 | 728.7262 | 6.9 | 728.7262 | 6.9 | 104.1037 | 1.5% | 2082.075 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 6.9 | 100% | 520.5187 | 6.9 | 100% | 728.7262 | 6.9 | 100% | 728.7262 | 6.9 |  | 0 | 95% | 1977.9712 | 0% | 0 | 95% | 1977.9712 | 95% | 1977.9712 | [14 empty] | 136722.925 | 2082.075 | 34701.25 | 6% | 108.1
| EWS -121 4th to 6th Floor Level. Straight | 226 | m2 | 1595 | 360470 | 226 | 67588.125 | 226 | 94623.375 | 226 | 94623.375 | 226 | 13517.625 | 226 | 22529.375 | 226 | 31541.125 | 226 | 31541.125 | 226 | 4505.875 | 100% | 360470 | 226 | 67588.125 | 226 | 94623.375 | 226 | 94623.375 | 203.4 | 12165.8625 |  | 0 |  | 0 |  | 0 |  | 0 | 74.62% | 269000.7375 | 0 | 0 | 0 | 0 | 0 | 0 | 22.6 | 1351.7625 | 226 | 22529.375 | 226 | 31541.125 | 226 | 31541.125 | 226 | 4505.875 | 25.38% | 91469.2625 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 22.6 | 100% | 1351.7625 | 226 | 100% | 22529.375 | 226 | 100% | 31541.125 | 226 | 100% | 31541.125 | 226 | 96% | 4325.64 | 99.8% | 91289.0275 | 0% | 0 | 99.8% | 91289.0275 | 99.8% | 91289.0275 | [14 empty] | 269000.7375 | 12165.8625 | 13517.625 | 90% | 203.4
| EWS -121 4th to 6th Floor Level. Curved | 36 | m2 | 2278.889 | 82040.004 | 36 | 15382.5008 | 36 | 21535.501 | 36 | 21535.501 | 36 | 3076.5002 | 36 | 5127.5003 | 36 | 7178.5004 | 36 | 7178.5004 | 36 | 1025.5001 | 100% | 82040.004 | 36 | 15382.5008 | 36 | 21535.501 | 36 | 21535.501 | 36 | 3076.5002 | 23.4 | 3332.8752 | 23.4 | 4666.0252 | 23.4 | 4666.0252 | 23.4 | 666.575 | 91.25% | 74861.5037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.6 | 1794.6251 | 12.6 | 2512.4751 | 12.6 | 2512.4751 | 12.6 | 358.925 | 8.75% | 7178.5003 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 12.6 | 100% | 1794.6251 | 12.6 | 100% | 2512.4751 | 12.6 | 100% | 2512.4751 | 12.6 | 96% | 344.568 | 99.8% | 7164.1433 | 0% | 0 | 99.8% | 7164.1433 | 99.8% | 7164.1433 | [14 empty] | 74861.5037 | 7178.5003 | 20510.001 | 35% | 23.4
| EWS -152 4th to 6th Floor Level | 62 | m2 | 1729 | 107198 | 62 | 20099.625 | 62 | 28139.475 | 62 | 28139.475 | 62 | 4019.925 | 62 | 6699.875 | 62 | 9379.825 | 62 | 9379.825 | 62 | 1339.975 | 100% | 107198 | 62 | 20099.625 | 62 | 28139.475 | 62 | 28139.475 | 62 | 4019.925 | 0.83779 | 90.5335 | 0.83779 | 126.7469 | 0.83779 | 126.7469 | 0.83779 | 18.1067 | 75.34% | 80760.6339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61.1622 | 6609.3415 | 61.1622 | 9253.0781 | 61.1622 | 9253.0781 | 61.1622 | 1321.8683 | 24.66% | 26437.3661 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 61.1622 | 100% | 6609.3415 | 61.1622 | 100% | 9253.0781 | 61.1622 | 100% | 9253.0781 | 61.1622 | 96% | 1268.9936 | 99.8% | 26384.4914 | 0% | 0 | 99.8% | 26384.4914 | 99.8% | 26384.4914 | [11 empty] | SA+H |  |  | 80760.6339 | 26437.3661 | 26799.5 | 98.65% | 0.83779
| Extra over Louver for EWS-110 size 0.65 x 4.08 | 1 | Nr. | 0 | Included
(Vision=17.54m2, Spandrel=92.62m2)
[59 empty] | 127167.204 | [29 empty] | 99.72% | 126815.6335 | 99.72% | 126815.6335 | 95% | 120808.8438 | 120808.8438
Apartment Level 6 to 31
| Door Type D-21 size 1.2 x 2.7 | 3 | Nr. | 0 | Included
| Door Type D-7 size 2 x 2.7 | 1 | Nr. | 0 | Included
| Type EWS-145 | 121.8 | m2 | 0 | Included
(Vision=0m2, Spandrel=122m2)
Hotel Level 7 to 29
| Type EWS-145 (Straight) | 1052 | m2 | 1333 | 1402316 | 1052 | 262934.25 | 1052 | 368107.95 | 1052 | 368107.95 | 1052 | 52586.85 | 1052 | 87644.75 | 1052 | 122702.65 | 1052 | 122702.65 | 1052 | 17528.95 | 100% | 1402316 | 1052 | 262934.25 | 1052 | 368107.95 | 1052 | 368107.95 | 1052 | 52586.85 | 929.6526 | 77451.6829 | 929.6526 | 108432.3561 | 929.6526 | 108432.3561 | 929.6526 | 15490.3366 | 97.09% | 1361543.7316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122.3474 | 10193.0671 | 122.3474 | 14270.2939 | 122.3474 | 14270.2939 | 122.3474 | 2038.6134 | 2.907% | 40772.2684 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 122.3474 | 100% | 10193.0671 | 122.3474 | 100% | 14270.2939 | 122.3474 | 100% | 14270.2939 | 122.3474 |  | 0 | 95% | 38733.655 | 0% | 0 | 95% | 38733.655 | 95% | 38733.655 | [14 empty] | 1361543.7316 | 40772.2684 | 350579 | 11.63% | 929.6526
| Type EWS-145 (Curved) | 53 | m2 | 1970 | 104410 | 53 | 19576.875 | 53 | 27407.625 | 53 | 27407.625 | 53 | 3915.375 | 53 | 6525.625 | 53 | 9135.875 | 53 | 9135.875 | 53 | 1305.125 | 100% | 104410 | 53 | 19576.875 | 53 | 27407.625 | 53 | 27407.625 | 53 | 3915.375 | 52.975 | 6522.5432 | 52.975 | 9131.5604 | 52.975 | 9131.5604 | 52.975 | 1304.5086 | 99.99% | 104397.6727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02503 | 3.0818 | 0.02503 | 4.3146 | 0.02503 | 4.3146 | 0.02503 | 0.61637 | 0.01181% | 12.3273 |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0.02503 |  | 0 | 0.02503 |  | 0 | 0.02503 |  | 0 | 0.02503 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | [16 empty] | 104397.6727 | 12.3273 | 26102.5 | 0.04723% | 52.975
[59 empty] | 40784.5957 | [29 empty] | 94.97% | 38733.655 |  | 38733.655 | 95% | 38745.3659 |  |  |  | 38745.3659
| Extra over Door Type D-8 for EWS-145 size 1.2 x 4.45 | 1 | Nr. | 8000 | 8000 | 1 | 1500 | 1 | 2100 | 1 | 2100 | 1 | 300 | 1 | 500 | 1 | 700 | 1 | 700 | 1 | 100 | 100% | 8000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 1 | 1500 | 1 | 2100 | 1 | 2100 | 1 | 300 | 1 | 500 | 1 | 700 | 1 | 700 | 1 | 100 | 100% | 8000 |  | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 1 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0
| Extra over Door Type D-8 for EWS-145 size 1.2 x 2.4 | 2 | Nr. | 6744.499 | 13488.998 | 2 | 2529.1871 | 2 | 3540.862 | 2 | 3540.862 | 2 | 505.8374 | 2 | 843.0624 | 2 | 1180.2873 | 2 | 1180.2873 | 2 | 168.6125 | 100% | 13488.998 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 2 | 2529.1871 | 2 | 3540.862 | 2 | 3540.862 | 2 | 505.8374 | 2 | 843.0624 | 2 | 1180.2873 | 2 | 1180.2873 | 2 | 168.6125 | 100% | 13488.998 |  | 2 |  | 0 | 2 |  | 0 | 2 |  | 0 | 2 |  | 0 | 2 |  | 0 | 2 |  | 0 | 2 |  | 0 | 2 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0
[59 empty] | 21488.998 | [29 empty] | 0% | 0
B | Podium Facade | [57 empty] | 820676.9983 | [30 empty] | 653664.8875 |  | 653664.8875 |  | 649413.8438
B1 | Basement Façade | [57 empty] | 105259.5299
C | Hotel and Apartment Tower Facade | [57 empty] | 821502.1829 | [30 empty] | 743756.7548 |  | 743756.7548 |  | 702355.315
D | Doors in the Podium | [57 empty] | 1887780.892 | [30 empty] | 1068314.7852 |  | 1093264.1602 |  | 1514154.6942
E | Doors in the Apt/Hotel Tower | [57 empty] | 171708.998
F | Level 5 Facade EWS-701 | [57 empty] | 117548.4 | [30 empty] | 117401.4645 |  | 117401.4645 |  | 117401.4645
G | Roof Canopies | [57 empty] | 962486.5922 | [30 empty] | 827418.9 |  | 842194.2375 |  | 778855 | 87.5%
[59 empty] | 4886963.5932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3410556.792 |  | 3450281.5045 | 0 | 3762180.3175 |  | 0
Note on B48: Mei Lee Yong: Air lock Door
Note on B71: Mei Lee Yong: Air Lock Door

## Doors Progress
GROUND FLOOR -Residence
Item No. | Glassline Door Reference | BOQ Door Reference |  |  |  | Site Opening |  | Drawing Opening |  | BOQ Rate | BOQ Amount | Progress % | Progress Amount
[6 empty] | Width | Height | Width | Height
01 | R-GF-D01-A | D-23e | 1 | Nr. | 992571.2869 | 2.2 | 3.2 | 2.14 | 3.15 | 35448.9745 | 35448.9745 | 90% | 31904.0771 | No WIR ref
02 | R-GF-D01-B | D-23e | 1 | Nr. | 28 | 2.2 | 3.2 | 2.14 | 3.15 | 35448.9745 | 35448.9745 | 90% | 31904.0771 | No WIR ref
03 | R-GF-D01-C | 0 | 1 | Nr. | 35448.9745 | 2.2 | 3.2 | 2.14 | 3.15 | 35448.9745 | 35448.9745 | 80% | 28359.1796 | No WIR ref
04 | R-GF-D01-D | 0 | 1 | Nr. |  | 2.2 | 3.2 | 2.2 | 3.15 | 35448.9745 | 35448.9745 | 90% | 31904.0771 | No WIR ref
05 | R-GF-D01-E | 0 | 1 | Nr. |  | 2.2 | 3.2 | 2.2 | 3.15 | 35448.9745 | 35448.9745 | 90% | 31904.0771 | No WIR ref
06 | R-GF-D01-F | 0 | 1 | Nr. |  | 2.2 | 3.2 | 2.2 | 3.15 | 35448.9745 | 35448.9745 | 90% | 31904.0771 | No WIR ref
07 | R-GF-D01-G | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.2 | 3.15 | 35448.9745 | 35448.9745 | 90% | 31904.0771 | No WIR ref
08 | R-GF-D01-H | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.2 | 3.15 | 35448.9745 | 35448.9745 | 90% | 31904.0771 | No WIR ref
09 | R-GF-D01-I | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.2 | 3.15 | 35448.9745 | 35448.9745 | 90% | 31904.0771 | No WIR ref
10 | R-GF-D01-J | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.2 | 3.15 | 35448.9745 | 35448.9745 | 90% | 31904.0771 | No WIR ref
11 | R-GF-D01-K | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.1 | 3.15 | 35448.9745 | 35448.9745 | 90% | 31904.0771 | No WIR ref
12 | R-GF-D01-L | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 1.95 | 3.15 | 35448.9745 | 35448.9745 | 90% | 31904.0771 | No WIR ref
13 | R-GF-D01-M | 0 | 1 | Nr. |  | 2.2 | 3.2 | 2.2 | 3.15 | 35448.9745 | 35448.9745 | 90% | 31904.0771 | No WIR ref
14 | R-GF-D01-N | 0 | 1 | Nr. |  | 2.2 | 3.2 | 2.2 | 3.15 | 35448.9745 | 35448.9745 | 90% | 31904.0771 | No WIR ref
15 | R-GF-D01-O | 0 | 1 | Nr. |  | 2.2 | 3.2 | 2.2 | 3.15 | 35448.9745 | 35448.9745 | 90% | 31904.0771 | No WIR ref
16 | R-GF-D01-P | 0 | 1 | Nr. |  | 2.2 | 3.2 | 2.2 | 3.15 | 35448.9745 | 35448.9745 | 30% | 10634.6924 | Material deliver (no MIR reference)
17 | R-GF-D01-Q | D-23e | 2 | Nr. |  | 1.8 | 3.2 | 2.2 | 3.15 | 35448.9745 | 70897.9491 | 30% | 21269.3847 | Material deliver (no MIR reference)
GROUND FLOOR-Hotel | [12 empty] | 0
01 | H-GF-D01-A | D-23e | 2 | Nr. |  | 2.2 | 3.2 | 1.843 | 3.213 | 35448.9745 | 70897.9491 | 75% | 53173.4618 | No WIR ref
02 | H-GF-D01-B | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 1.843 | 3.213 | 35448.9745 | 35448.9745 | 90% | 31904.0771 | No WIR ref
03 | H-GF-D01-C | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.067 | 3.213 | 35448.9745 | 35448.9745 | 90% | 31904.0771 | No WIR ref
04 | H-GF-D01-D | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.067 | 3.213 | 35448.9745 | 35448.9745 | 90% | 31904.0771 | No WIR ref
05 | H-GF-D01-E | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.178 | 3.213 | 35448.9745 | 35448.9745 | 90% | 31904.0771 | No WIR ref
06 | H-GF-D01-F | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.178 | 3.213 | 35448.9745 | 35448.9745 | 90% | 31904.0771 | No WIR ref
07 | H-GF-D01-G | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.178 | 3.213 | 35448.9745 | 35448.9745 | 0% | 0
08 | H-GF-D01-H | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.178 | 3.213 | 35448.9745 | 35448.9745 | 0% | 0
10 | H-GF-D01-J | D-23e | 1 | Nr. |  | 2.1 | 3.2 |  |  | 35448.9745 | 35448.9745 | 90% | 31904.0771 | No WIR ref
[11 empty] | 992571.2869 | 20.15 | 751518.2601
LEVEL 02- Residence
01 | R-L02-D01-A | D-23e | 1 | Nr. | 545500 | 2.2 | 3.2 | 2.124 | 3.13 | 22729.1667 | 22729.1667 | 90% | 20456.25 | No WIR ref
02 | R-L02-D01-B | D-23e | 1 | Nr. | 24 | 2.2 | 3.2 | 2.124 | 3.13 | 22729.1667 | 22729.1667 | 90% | 20456.25 | No WIR ref
03 | R-L02-D01-C | D-23e | 1 | Nr. | 22729.1667 | 2.2 | 3.2 | 2.094 | 3.13 | 22729.1667 | 22729.1667 | 90% | 20456.25 | No WIR ref
04 | R-L02-D01-D | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.094 | 3.13 | 22729.1667 | 22729.1667 | 90% | 20456.25 | No WIR ref
05 | R-L02-D01-E | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.034 | 3.13 | 22729.1667 | 22729.1667 | 90% | 20456.25 | No WIR ref
06 | R-L02-D01-F | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.18 | 3.13 | 22729.1667 | 22729.1667 | 90% | 20456.25 | No WIR ref
07 | R-L02-D01-G | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.18 | 3.13 | 22729.1667 | 22729.1667 | 90% | 20456.25 | No WIR ref
08 | R-L02-D01-H | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.18 | 3.13 | 22729.1667 | 22729.1667 | 90% | 20456.25 | No WIR ref
09 | R-L02-D01-I | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.18 | 3.13 | 22729.1667 | 22729.1667 | 90% | 20456.25 | No WIR ref
10 | R-L02-D01-J | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.18 | 3.13 | 22729.1667 | 22729.1667 | 90% | 20456.25 | No WIR ref
11 | R-L02-D01-K | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.18 | 3.13 | 22729.1667 | 22729.1667 | 90% | 20456.25 | No WIR ref
12 | R-L02-D01-L | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.18 | 3.13 | 22729.1667 | 22729.1667 | 90% | 20456.25 | No WIR ref
13 | R-L02-D01-M | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.18 | 3.13 | 22729.1667 | 22729.1667 | 90% | 20456.25 | No WIR ref
14 | R-L02-D01-N | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.18 | 3.13 | 22729.1667 | 22729.1667 | 90% | 20456.25 | No WIR ref
15 | R-L02-D01-O | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.18 | 3.13 | 22729.1667 | 22729.1667 | 90% | 20456.25 | No WIR ref
16 | R-L02-D01-P | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.18 | 3.13 | 22729.1667 | 22729.1667 | 90% | 20456.25 | No WIR ref
17 | R-L02-D01-Q | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.18 | 3.13 | 22729.1667 | 22729.1667 | 90% | 20456.25 | No WIR ref
18 | R-L02-D01-R | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.18 | 3.13 | 22729.1667 | 22729.1667 | 90% | 20456.25 | No WIR ref
18 | R-L02-D01-S | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.18 | 3.13 | 22729.1667 | 22729.1667 | 90% | 20456.25 | No WIR ref
Level 02-Hotel
01 | H-L02-D01-A |  | 1 | Nr. |  | 2.2 | 3.2 | 2.187 | 3.13 | 22729.1667 | 22729.1667 | 90% | 20456.25 | No WIR ref
02 | H-L02-D01-B |  | 1 | Nr. |  | 2.2 | 3.2 | 2.187 | 3.13 | 22729.1667 | 22729.1667 | 0% | 0 | Permanent door is not fixed only a temporary door
03 | H-L02-D01-C |  | 1 | Nr. |  | 2.2 | 3.2 | 2.187 | 3.13 | 22729.1667 | 22729.1667 | 90% | 20456.25 | No WIR ref
04 | H-L02-D01-D |  | 1 | Nr. |  | 2.2 | 3.2 | 2.026 | 3.13 | 22729.1667 | 22729.1667 | 90% | 20456.25 | No WIR ref
05 | H-L02-D01-E |  | 1 | Nr. |  | 2.2 | 3.2 | 2.026 | 3.13 | 22729.1667 | 22729.1667 | 90% | 20456.25 | No WIR ref
06 | H-L02-D01-F |  | 1 |  |  | 2.2 | 3.2 |  |  | 225959.6052 | 225959.6052 | 80% | 180767.6841 | No WIR ref
07 | H-L02-D01-G |  |  |  |  | 2.2 | 3.2 | [5 empty] | 0
08 | H-L02-D01-H |  |  |  |  | 1.3 | 3.2 | [5 empty] | 0
LEVEL 04- Residence | [10 empty] | 771459.6052 |  | 651261.4341
01 | R-L4-D01-A | D-23e | 1 | Nr. | 123750 | 2.2 | 3.2 | 2.2 | 3.2 | 13750 | 9519.2308 | 90% | 8567.3077 | No WIR ref
02 | R-L4-D01-B | D-23e | 1 | Nr. | 13 | 2.2 | 3.2 | 2.2 | 3.2 | 13750 | 9519.2308 | 90% | 8567.3077 | No WIR ref
03 | R-L4-D01-C | D-23e | 1 | Nr. | 9519.2308 | 2.2 | 3.2 | 2.2 | 3.2 | 13750 | 9519.2308 | 90% | 8567.3077 | No WIR ref
04 | R-L4-D01-D | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.2 | 3.2 | 13750 | 9519.2308 | 90% | 8567.3077 | No WIR ref
05 | R-L4-D01-E | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.2 | 3.2 | 13750 | 9519.2308 | 90% | 8567.3077 | No WIR ref
LEVEL 04- Hotel
01 | H-L04-D01-A | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.195 | 3.175 | 13750 | 9519.2308 | 90% | 8567.3077 | No WIR ref
02 | H-L04-D01-B | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.195 | 3.175 | 13750 | 9519.2308 | 90% | 8567.3077 | No WIR ref
03 | H-L04-D01-C | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.195 | 3.175 | 13750 | 9519.2308 | 90% | 8567.3077 | No WIR ref
04 | H-L04-D01-D | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.195 | 3.175 | 13750 | 9519.2308 | 90% | 8567.3077 | No WIR ref
05 | H-L04-D01-E | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.195 | 3.175 | 13750 | 9519.2308 | 90% | 8567.3077 | No WIR ref
06 | H-L04-D01-F | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 2.165 | 3.175 | 13750 | 9519.2308 | 90% | 8567.3077 | No WIR ref
07 | H-L04-D01-G | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 1.425 | 3.175 | 13750 | 9519.2308 | 90% | 8567.3077 | No WIR ref
07 | H-L04-D01-H | D-23e | 1 | Nr. |  | 2.2 | 3.2 | 1.425 | 3.175 | 13750 | 9519.2308 | 90% | 8567.3077 | No WIR ref
[11 empty] | 123750 |  | 111375
1514154.6942

## Roof Canopy
Hotel Roof Canopy
Progress Calculation-Lower Roof Canopy
1 | Item | Material |  |  |  | Installation
2 | Breakdown |  | 75% |  |  |  | 25%
3 | Item Breakdown | First Fix | Frames | Panel | Finishing | First Fix | Frames | Panel | Finishing
4 | % Breakdown | 25% | 35% | 35% | 5% | 25% | 35% | 35% | 5%
5 | Item Progress | 75% | 75% | 75% | 75% | 75% | 75% | 65% | 0%
6 | Overall Item Progress | 14.06% | 19.69% | 19.69% | 2.813% | 4.688% | 6.562% | 5.687% | 0%
| Total Progress | 73.19%
Progress Calculation-Lower Roof Canopy
1 | Item | Material |  |  |  | Installation
2 | Breakdown |  | 75% |  |  |  | 25%
3 | Item Breakdown | First Fix | Frames | Panel | Finishing | First Fix | Frames | Panel | Finishing
4 | % Breakdown | 25% | 35% | 35% | 5% | 25% | 35% | 35% | 5%
5 | Item Progress | 100% | 100% | 80% | 80% | 40% | 40% | 40% | 40%
6 | Overall Item Progress | 18.75% | 26.25% | 21% | 3% | 2.5% | 3.5% | 3.5% | 0.5%
| Total Progress | 79%

## VO Schedule
PLOT-18
FAÇADE WORKS PROGRESS BREAKDOWN -AUGUST 2022
VARIATIONS
GL New VO No. | Description | Contract Amount | New Contract Amount | Balance Amount | Previous | This Month | Current Cumilative Progress
Variations under the Main Contract - Agreed
1 | Building Permit 5 Changes to Glass and Aluminium Works Contract | 4500000 | 4012351.942 | 487648.058 | 404106.0718 | 0 | 404106.0718 | 487648.2462 |  | 21865.2447 |  | 509513.4909
2 | Louver Fin Design confirmation |  |  | 0
3 | Instruction to provide previously deleted louvre -reintroduction in Hotel Level 18 and Level 23rd Floor and Residential Apartments Level 3rd and 23rd Floor | 335000 | 318250 | 16750 | 16750 | 0 | 16750 | 16750 |  | 0 |  | 16750
4 | Full height glass at core wall lift lobby | 125000 | 125000 | 0 |  | 0
5 | Lift Lobby Temporary Enclosure & doors for sales centre corridor | 28804 | 28804 | 0 |  | 0
6 | Aluminium Cladding to Double Height Horizontal Steel-Structural Steel Cladding to duplex for both Hotel and Residential towers. | 398242 | 0 | 398242 |  | 0
7 | Glass & Aluminium - Change in Canopy Material | 95625 | 19125 | 76500 | 76500 | 0 | 76500 | 76500 |  | 0 |  | 76500
8 | Vitrocsa framing | 168745 | 16874.5 | 151870.5 | 83436 | 0 | 83436 | 83436 |  | 0 |  | 83436
9 | Change in Podium Modulation-As inclusion of additional doors, removal of doors, mullions, steps, change the position of doors, removal of internal partitions, straight glass corner and associated changes in podium. | 30250 | 30250 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
10 | Change in Apt 24-29 Modulation | 15004 |  | 15004 | 12003.2 | 0 | 12003.2 | 12003.2 |  | 0 |  | 12003.2
11 | Additioanl Aluminium flashing to Penthouse Transom to provide aluminium flashing at pent house level 23 -29 | 207547.17 | 0 | 207547.17 | 0 | 0 | 0 | 0 |  | 0 |  | 0
12 | -Ditto L8 | 49383 | 49383 | 0 |  | 0
13 | Cost incurred against Engineering & installed mockup | 16250 |  | 16250 | 0 | 0 | 0 | 0 |  | 0 |  | 0
14 | Abortive engineering works due to design changes - Façade | 2475 | 2475 | 0 |  | 0
15 | Glass and Aluminium - Additional Sliding Door and Foldable Door in Podium | 111835.38 | 0 | 111835.38 |  | 0
16 | Additional works associated with powder coated aluminium cover to door contact in hotel tower as per the approved WIR | 40000 | 37600 | 2400 |  | 0
17 | Skylight to All Day Dining | 49692.5 |  | 49692.5 | 47957.875 | 0 | 47957.875 | 38851.0938 |  | 9106.7812 |  | 47957.875
18 | Engineering reworks due to the requirements of full width sliding panels at Juliette balconies of the spa level - Hotel Tower.Requirements of the full width sliding panels at Juliette balconies | 24750 | 24750 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
19 | Glass & Aluminium - Instruction of Skylight to Staff Dining As per the ER RFI confirmation Glazed roof to be provided at Basement 1 staff dining area | 145355.28 | 0 | 145355.28 | 128978.2997 | 0 | 128978.2997 | 26250 |  | 102728.2997 |  | 128978.2997
20 | Glass and Aluminium - Change in Level 29 Hotel Glass Modulation Hotel Roof top Facade Modulation changes (Engineers Instruction - 41 ) Glass line | 405188.52 | 192464.547 | 212723.973 | 212723.97 | 0 | 212723.97 | 212723.97 |  | 0 |  | 212723.97
21 | Glass and Alunimium - Additional Windows in level 3 Employer's Representative instructed Roberts-Pizzarotti JV to provide additional windows in the Podium | 32954 | 11533.9 | 21420.1 | 20543 | 0 | 20543 | 19065 |  | 1478 |  | 20543
22 | Sales Office | 70007.11 | 70007.11 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
23 | Instruction to Provide Rainwater Pipe Cover | 69080 | 69080 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
24 | Broken Glass | 229051.61 | 144302.5143 | 84749.0957 | 84749.0997 | 0 | 84749.0997 | 84749.0997 |  | 0 |  | 84749.0997
25 | Additional Doors and Change of Door for Facade Scope in Level 17 | 48347 | 0 | 48347 | 45960 | 0 | 45960 | 44872 |  | 1088 |  | 45960
26 | Podium Façade Shop drawings | 11687.5 | 11687.5 | 0 |  | 0
27 | Abortive engineering works due to design changes - Façade | 92840 | 92840 | 0 |  | 0
30 | To proceed with GI packing behind core wall bracket in Hotel Tower | 126060 | 126060 | 0 |  | 0
31 | Submission of cost for requirement of additional steel brackets at Hotel Level 5 slab edges (Grid-T) | 3254.5 | 3254.5 | 0 |  | 0
32 | Changes due to the concrete nib deletion at core | 600000 | 594000 | 6000 | 5999.9978 | 0 | 5999.9978 | 5999.9978 |  | 0 |  | 5999.9978
33 | To proceed with works associated EPDM membrane at dry wall façade termination area | 40003.7 | 40003.7 | 0 |  | 0
34 | To proceed with works associated with brackets redesign due to clash with GAS recess | 23892 | 23892 | 0 |  | 0
35 | Cost of Subcontractor's cradle and access equipment used by other Subcontractors | 13578.37 | 13578.37 | 0 |  | 0
36 | Cradle | 9829.49 | 9829.49 | 0 |  | 0
37 | Cradle | 5940 | 5940 | 0 |  | 0
38 29 | Increased Canopy Area | 138192 | 0 | 138192 | 133942.596 | 0 | 133942.596 | 125219.226 |  | 8723.37 |  | 133942.596
| Glass & Aluminium - Reduction in Glass height on Level 5 parapet |  | 0 | 0 |  | 0
| Glass and Aluminium - Abortive Engineering | 0 | 0 | 0 |  | 0
|  | 8263864.13 | 6073337.0733 | 2190527.0567 | 1273650.11 | 0 | 1273650.11 | 1234067.8335 | 0 | 144989.6957 | 0 | 1379057.5292
Additional Variations - Not yet Agreed
1 | Site Instrution to procced with Level 03 soffit channel / cove requirement throughout the perimeter of the hotel tower | 645007.36 |  |  | 64500.7363 | 0 | 64500.7363 |  | 64500.7363
2 | Ground floor façade Extension | 53020 | 0 |  | 52357.25 | 0 | 52357.25 |  | 52357.25
3 | Site instruction - Panic Bars & Pull handle to façade Doors | 801071.99 |  |  | 0 | 0 | 0
4 | Hotel upper roof cannopy works | 312774 |  |  | 300472.3837 | 0 | 300472.3837
5 | Site instructions - design and construction of verticle gas louver to podium levels | 13826.65 |  |  | 13550.1179 | 0 | 13550.1179
6 | Bracket to support façade at L18 | 15000 | 0 |  | 15000 | 0 | 15000
7 | New doors hardware and aluminium profiles to double swing doors | 69300 |  |  | 34650 | 0 | 34650
|  | 1910000 |  |  | 480530.488 | 0 | 480530.488
Note on I27: Himal Kosala: Balance will release after curved glass fixed
Note on I54: Himal Kosala: Only 50%

## Additional Works_KCE
Plot -18
Additional Works-KCE
Description | Estimated Total | Claimed Progress | Certified Progrss
Glass Broken Due to NIS Inclusion at Hotel & Residence Towers | 142074 | 56412.4425 | 14103.1106
PDM Termination to Wall under Slab Extension | 271975 | 267895.375 | 224316.3
Remove and Reinstall Sandwich Panels at Residence Tower Roadside Core Wal | 30250 | 30250 | 30250
Sliding Glass Door at Lift Lobby on the Ground Floor of the Hotel Tower | 3292
Black Opaque Film Covering to L4 Room Service Kitchen Facade Glass | 14850
Louver modification at Hotel & Residence Level 5 | 33824 | 33401 | 17588.48
Light Cove Work on Level 29 Hotel Tower & Residential Tower Balcony Level 23 & 26 | 64178 | 15793 | 32089
Install Glazed Curtain Wall Façade at Level 17 of the Hotel Tower. | 74387 |  | 33474.15 | Material only
Door and Fixed Glass as Replacement of Existing Door at Level 17 of the Hotel Tower. | 25089 |  | 12544.5 | Frame only fixed
3036
Removal and Reinstallation of Façade Glass Panels for Mast Climber Support Bracket Installation at Level 18 of the Resident Tower | 3036
Glass Broken in Ballroom area at Ground Floor of the Hotel Tower | 4558
Curtain Wall GI Sheet to be Cut and Refill in Residential and Hotel Towers | 1591.7
Removal and Reinstatement of Water Nib Cladding in Level 13 | 651.2 |  | 325.6 | 50% only
Removal of 1 No. Each Glazing Unit of 2405 & 2809 Rooms Temporarily and Re-fix the Glass Units | 2238.5 |  | 1119.25 | 50% only
Removal of Installed EPDM with Sheet Where Hotel Mast Climber Area Support Brackets are Going to Install from Level 9 to Roof at Hotel Tower | 14592.6 |  | 7296.3 | 50% only
Supply and Installation Fixed Glass Window at Level 29 of the Hotel Tower | 9360 |  | 3744 | Frame fixed
Removal of 1 No. of Glazing Panel of Room 2405 at Level -23 of the Hotel Tower Temporarily and Re-fix the Glazing Panel | 1367.3
Supply & Install Temporary Safety Glass to the Management Suite Windows | 5255.8 |  | 2627.9 | 50% only
Supply and Installation of Temporary Doors in Ballroom of Ground Floor and Level-2 of the Hotel and Residence Towers | 30341.3 |  | 15170.65 | 50% only
Changes to Hotel level 17 CW facade at Grid 18/T-V | 10926 |  | 4370.4 | Frame fixed
Removal and Reinstallation of Feature Fin Louver at Level 29 of the Hotel and Residence Towers and Mullion and Fin at Level 29 of Residence Tower | 1621.4
| 745458.8 | 406787.8175 | 399019.6406

## VO -1 Break Down
Plot -18
Certification Summary -GL VO-1
GL VO Ref. | Description | GL VO Cost Break down | GL Agreed VO Cost Break down | Progress % | Progress Amount | Agreed VO Cost Break down | Progress % | Progress Amount |  |  |  |  | Installation
01 R | Increase in quantity of double volume façade | 2009685 | 1512809.5477 | 100% | 1512809.5477 | 785919.8629 | 100% | 785919.8629 |  |  |  |  | 100%
02 R | Additional cladding area due to recess glass façade line. | 256700.0505 | 193233.4109 | 85% | 164248.3992 | 248419.0976 | 100% | 248419.0976 | 28985.0116 | 100% | 28985.0116 |  | First Fix | Frames | Glass | Finishing
03A R | Additional area of curtain walls as per BP 5 Architectural drawings. | 2022245 | 1522264.2074 | 75% | 1141698.1556 | 1006613.7715 | 58.92% | 593083.0181 | 380566.0519 | 90.5% | 344412.2769 |  | 25% | 35% | 35% | 5%
03B R | Additional quantity of doors as per BP 5 Architectural drawings. | 76654.816 | 57702.6437 | 0% | 0 | 41826.6365 | 0% | 0 | 57702.6437 | 40% | 23081.0575 |  | 100% | 100% | 80% | 50%
03C R | Additional quantity of louvers at GF & 1st floor as per BP 5 Architectural drawings. | 17423.8116 | 13115.9403 | 98% | 12853.6215 | 17423.7901 | 100% | 17423.7901 | 262.3188 |  | 0 | 90.5% | 25% | 35% | 28% | 2.5%
04 R | Re Modulation and addiotional transome for EWS-110 | 76221 | 57376.0846 | 99% | 56802.3237 |  |  |  | 573.7608 |  | 0
05 R | Floor Height Increase / Decrease | 380796 | 286647.8202 | 100% | 286647.8202 | 103342.3742 | 100% | 103342.3742 | 0 |  | 0
06 R | Additional Steel Structure due to increase in floor heights | 795527 | 598840.5352 | 100% | 598840.5352 | 795527 | 40% | 318210.8 | 0 |  | 0
01 H | Aluminum louver type EWS -701 changed to curtain wall type EWS-141 as per BP 5 Architectural drawings. | 174610.866 | 131439.9944 | 85.12% | 111881.7233 | 118867.6475 | 0% | 0 | 19558.2712 | 39% | 7627.7258
02 H | Additional curtain wall due to increase in recess depth of U shaped façade (EWS 145) | 19080.846 | 14363.2888 | 100% | 14363.2888 | 19080.846 | 100% | 19080.846 | 0 |  | 0
03 H | Double height façade (EWS - 104) changed to slab to slab façade (EWS 103) as per BP 5 Architectural drawings. | -11142.747 | -8387.8091 | 100% | -8387.8091 | -107107.71 | 100% | -107107.71 | 0 |  | 0
04 H | Double height façades changed to double volume façades as per BP 5 Architectural drawings. | 160203 | 120594.3359 | 100% | 120594.3359 | 122057.5345 | 100% | 122057.5345 | 0 |  | 0
| Total | 5978004.6431 | 4500000 | 89.16% | 4012351.942 | 3151970.8506 | 66.64% | 2100429.6133 | 487648.058 | 82.87% | 404106.0718 | 487648.058
VO-3AR Progress calculation
| Total for VO-3RA Submitted by GL | 1974861
| L30-31 Façade | 691000
| L30-31 Façade | 151000
| L30-31 Façade | 120300
| Total L30-31 Façade | 962300
| Progress | 48.73%

## KCE VO
DORCHESTER HOTEL & RESIDENCIES | [5 empty] | KCE PC 10
GLASSLINE - FAÇADE | [5 empty] | 2022-11-01
KCE VARIATIONS
Additional Variations - Not yet Agreed |  | Amount | Previous | This Month | % | Cumulative
1 | Omission of Glass Balustrade at Residential Level 30 | 9684 | 8450.88 | 0 | 87.27% | 8450.88
2 | EPDM Termination to Wall under Slab Extension | 271975 | 222525 | 0 | 81.82% | 222525
3 | Remove and Reinstall Sandwich Panels at Residence Tower Roadside Core Wall | 30250 | 12100 | 0 | 40% | 12100
4 | Louver modification at Hotel & Residence Level 5 | 33824 | 21146 | 0 | 62.52% | 21146
5 | Light Cove Work on Level 29 Hotel Tower & Residential Tower Balcony Level 23 & 26 | 64178 | 11281 | 0 | 17.58% | 11281
6 | Removal and Reinstallation of Façade Glass Panels for Mast Climber Support Bracket Installation at Level 18 of the Resident Tower | 3036 | 774.4 | 0 | 25.51% | 774.4
TOTAL - KCE VARIATIONS |  | 412947 | 276277.28 | 0 | 66.9% | 276277.28

## VO with KCE
Additional Works with KCE | [6 empty] | 2022-10-31
[7 empty] | Material Delivery | [7 empty] | Installation | [7 empty] | Previous Total |  | This Period |  | Total to Date
[7 empty] | 75% | [7 empty] | 25%
[7 empty] | First Fix |  | Frames |  | Glass/ Panel |  | Finishing |  | First Fix |  | Frames |  | Glass |  | Finishing
Variation Ref. | GL New VO No. | Description | Qty. | Unit | Rate | Amount | 25% |  | 35% |  | 35% |  | 5% |  | 25% |  | 35% |  | 35% |  | 5%
[6 empty] | (Dhs.) | Curr. Progress | Amount | Curr. Progress | Amount | Curr. Progress | Amount | Curr. Progress | Amount | Curr. Progress | Amount | Curr. Progress | Amount | Curr. Progress | Amount | Curr. Progress | Amount | % | Amount | % | Amount | % | Amount
E. Variations with M/s. Khansaheb
| 1 | NOC# 01, 02 03 & 05 - Broken Glass Submission of Cost for the Installed Glass Broken Due to NIS Inclusion at Hotel & Residence Towers-Batch-1 Glassline's Letter ref. GL-PL18-KC-ZH-630-L-008-22 dated August 8, 2022 Approved vide Khasaheb letter E11-K119-SK-dm-117 dated 13 August 2022 | [5 empty] | Overall for dismantling & material on site | [7 empty] | Overall for installation
|  | Overall Amount | 1 | Item | 26097 | 26097 |  | 0 | [7 empty] | 0 | [8 empty] | 0% | 0 | 0% | 0
|  | Over Head & Profit |  | 0.1 |  | 2610 |  | 0 | [7 empty] | 0 | [8 empty] | 0% | 0 | 0% | 0
|  | Total |  |  |  | 28707 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 2 | NOC# 04 - Omission of Glass Balustrade at Residential Level 30 Valuation of Variation Glassline's Letter ref. GL-PL18-KC-ZH-630-L-012-22 dated September 1, 2022
|  | 1. Omission of Fabrication & Installation cost for façade at Level 31 in residential apartment | 123 | m2 | -262 | -32226 | 100% | -6042.375 | 100% | -8459.325 | 100% | -8459.325 | 100% | -1208.475 | 100% | -2014.125 | 98% |  | 80% | -2255.82 |  | 0 | 88.25% | -28439.445 | 0% | 0 | 88.25% | -28439.445
|  | 2. Additional material (Waterproofing, Aluminum flashings, Rockwool insulation for periphery closure) fabrication and installation | 38 | mtr | 575 | 21850 | 100% | 4096.875 | 100% | 5735.625 | 100% | 5735.625 | 100% | 819.375 | 100% | 1365.625 | 98% | 1873.6375 | 80% | 1529.5 |  | 0 | 96.83% | 21156.2625 | 0% | 0 | 96.83% | 21156.2625
|  | 3. Engineering for the above works (Item 2) | 130 | MH | 125 | 16250 | 100% | 3046.875 | 100% | 4265.625 | 100% | 4265.625 | 100% | 609.375 | 100% | 1015.625 | 98% | 1393.4375 | 80% | 1137.5 |  | 0 | 96.82% | 15734.0625 | 0% | 0 | 96.82% | 15734.0625
|  | 4. Over Head & Profit on above Ityems 2 & 3. |  |  | 10% | 3810 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0% | 0 | 0% | 0
|  | Total |  |  |  | 9684 |  | 1101.375 |  | 1541.925 |  | 1541.925 |  | 220.275 |  | 367.125 |  | 3267.075 |  | 411.18 |  | 0 |  | 0 |  | 0 |  | 8450.88
| 3 | NOC# 06 - Valuation of Variation Site Instruction - EPDM Termination to Wall under Slab Extension Glassline's Letter ref. GL-PL18-KC-ZH-630-L-019-22 dated September 20, 2022, Approved by KCE vide letter E11-K119-SK-dm-149-R1 Dated 29 September 2022.
|  | 1. Abortive Engineering Works due to the Site Instruction -EPDM Termination to wall under slab extension | 60 | Hour | 125 | 7500 | 100% | 1406.25 | 100% | 1968.75 | 100% | 1968.75 | 100% | 281.25 | 50% | 234.375 | 50% | 328.125 | 50% | 328.125 | 50% | 46.875 | 87.5% | 6562.5 | 2.5% | 187.5 | 90% | 6750
|  | 2. Supply and Installation of the Flashing, EPDM, rockwool insulation works | 350 | lm | 685 | 239750 | 100% | 44953.125 | 100% | 62934.375 | 100% | 62934.375 | 100% | 8990.625 | 50% | 7492.1875 | 50% | 10489.0625 | 50% | 10489.0625 | 50% | 1498.4375 | 87.5% | 209781.25 | 2.5% | 5993.75 | 90% | 215775
a. Hotel:
Level 12, 17, 24, 28 and 29.
b. Residence:
Level 10, 18, 23, 24, 25, 29 and 30.
|  | 3. Over Head & Profit on above Ityems 2 & 3. |  |  | 10% | 24725 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0% | 0 | 0% | 0
|  | Total |  |  |  | 271975 |  | 46359.375 |  | 64903.125 |  | 64903.125 |  | 9271.875 |  | 7726.5625 |  | 10817.1875 |  | 10817.1875 |  | 1545.3125 |  | 216343.75 |  | 6181.25 |  | 222525 | 63.64%
| 1 Batch-2 | NOC# 0 07, 08 & 11 - Broken Glass Submission of Cost for the Installed Glass Broken Due to NIS Inclusion at Hotel & Residence Towers-Batch-2 Glassline's Letter ref. GL-PL18-KC-ZH-630-L-025-22 dated September 30, 2022 | [5 empty] | Overall for dismantling & material on site | [7 empty] | Overall for installation
|  | Overall Amount | 1 | Item | 35375 | 35375 |  | 0 | [7 empty] | 0 | [8 empty] | 0% | 0 | 0% | 0
|  | Over Head & Profit |  | 0.1 |  | 3538 |  | 0 | [7 empty] | 0 | [8 empty] | 0% | 0 | 0% | 0
|  | Total |  |  |  | 38913 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 1 Batch-3 | NOC# 15 - Broken Glass Submission of Cost for the Installed Glass Broken Due to NIS Inclusion at Hotel & Residence Towers-Batch-3 Glassline's Letter ref. GL-PL18-KC-ZH-630-L-032-22 dated 11 October, 2022 | [5 empty] | Overall for dismantling & material on site | [7 empty] | Overall for installation
|  | Overall Amount | 1 | Item | 13741 | 13741 |  | 0 | [7 empty] | 0 | [8 empty] | 0% | 0 | 0% | 0
|  | Over Head & Profit |  | 0.1 |  | 1374 |  | 0 | [7 empty] | 0 | [8 empty] | 0% | 0 | 0% | 0
|  | Total |  |  |  | 15115 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 4 | NOC# 20 - Valuation of Variation Remove and Reinstall Sandwich Panels at Residence Tower Roadside Core Wall. Glassline's Letter ref. GL-PL18-KC-ZH-630-L-038-22 dated 8 November, 2022
|  | 1. Removal of Sandwich Panels at Residence Tower Roadside Core Wall | 500 | Hour | 22 | 11000 | 100% | 2062.5 | 100% | 2887.5 | 100% | 2887.5 | 100% | 412.5 | 100% | 687.5 | 100% | 962.5 | 100% | 962.5 | 100% | 137.5 |  |  | 100% | 11000 | 100% | 11000
Location:
From level-7 to Level-32, Total 25 floors (1 Day / 2 Labors/ Per floor).
|  | 2. Reinstalaltion of Sandwich Panels at Residence Tower Roadside Core Wall | 750 | Hour | 22 | 16500 | 100% | 3093.75 | 100% | 4331.25 | 100% | 4331.25 | 100% | 618.75 | 100% | 1031.25 | 100% | 1443.75 | 100% | 1443.75 | 100% | 206.25
Location:
From level-7 to Level-32, Total 25 floors (1 Day / 3 Labors/ Per floor).
|  | 3. Over Head & Profit on above Ityems 2 & 3. |  |  | 10% | 2750 | 100% | 515.625 | 100% | 721.875 | 100% | 721.875 | 100% | 103.125 | 100% | 171.875 | 100% | 240.625 | 100% | 240.625 | 100% | 34.375 |  |  | 100% | 1100 | 40% | 1100
|  | Total |  |  |  | 30250 |  | 5671.875 |  | 7940.625 |  | 7940.625 |  | 1134.375 |  | 1890.625 |  | 2646.875 |  | 2646.875 |  | 378.125 |  |  |  | 12100 |  | 12100
| 5 | NOC# 09 - Valuation of Variation Supply and Installation of Black Opaque Film Covering to L4 Room Service Kitchen Facade Glass @Grid U-V/22. Glassline's Letter ref. GL-PL18-KC-ZH-630-L-041-22 dated 21 November, 2022
|  | 1. Removal of Service Kitchen Facade Glass @Grid U-V/22 | 56 | Hour | 22 | 1232 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0
Level 4, Glass Panels 4 Pcs. (14 Hrs./Panel.)
Supply and install the Black Opaque film in to Façade Glass Panels by Contractor
|  | 2. Reinstallation of Service Kitchen Facade Glass @Grid U-V/22 | 80 | Hour | 22 | 1760 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0
Level 4, Glass Panels 4 Pcs. (20 Hrs./Panel.)
|  | 3. Over Head & Profit on above Items 2 & 3. |  |  | 10% | 300 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0
|  | Total |  |  |  | 3292 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 6 | NOC# 12 - Variation VO# 06 – Valuation of Variation - Sliding Glass Door at Lift Lobby on the Ground Floor of the Hotel Tower. Glassline's Letter ref. GL-PL18-KC-ZH-630-L-043-22 dated 23 November, 2022
|  | 1. Aluminum Double Leaf Hinged Door ( 1900x2400mm ) | 1 | No. | 13750 | 13750 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0
|  | 2. Engineering | 8 | Hour | 125 | 1000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0
|  | 3. Over Head & Profit on above Item 2. |  |  | 10% | 100 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0
|  | Total |  |  |  | 14850 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 7 | NOC# 13 - Variation VO# 07 – Valuation of Variation - Louver modification at Hotel & Residence Level 5. Glassline's Letter ref. GL-PL18-KC-ZH-630-L-044-22 dated 23 November, 2022
|  | 1. Sand trap louver; L5H-LV-01; 1820x3320mm | 6.0424 | m2 | 2012 | 12157.3088 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 |  | 0 | 0% | 0 | 80% | 9725.847 | 80% | 9725.847
|  | 2. Sand trap louver; L5H-LV-02 ; 1120x3280mm | 3.6736 | m2 | 2012 | 7391.2832 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0
|  | 3. Sand trap louver; L5H-LV-08 ; 1193x260mm | 5.1818 | m2 | 2012 | 10425.7816 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 |  | 0 | 0% | 0 | 80% | 8340.6253 | 80% | 8340.6253
|  | 4. Sand trap louver; L5R-New ; 690x990mm | 0.6831 | m2 | 2012 | 1374.3972 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 |  | 0 | 0% | 0 | 80% | 1099.5178 | 80% | 1099.5178
|  | 5. Engineering | 18 | MH | 125 | 2250 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 |  | 0 | 0% | 0 | 80% | 1800 | 80% | 1800
|  | 6. Over Head & Profit on above Item 5. |  |  | 10% | 225 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 |  | 0 | 0% | 0 | 80% | 180 | 80% | 180
|  | Total |  |  |  | 33824 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 21146 |  | 21146
| 8 | NOC# 14 - Variation VO# 08 – Valuation of Variation - Light Cove Work on Level 29 Hotel Tower & Residential Tower Balcony Level 23 & 26. Glassline's Letter ref. GL-PL18-KC-ZH-630-L-045-22 dated 23 November, 2022
|  | 1. Aluminum light cove, straight; Hotel L 29 | 131.595 | lm | 274.82 | 36164.9379 | 100% | 0 | 20% | 0 |  | 0 |  | 0 | 40% | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 25% | 9041.2345 | 25% | 9041.2345
|  | 2. Aluminum light cove, curved ; Hotel L 29 | 15.405 | lm | 581.49 | 8957.8535 | 100% | 0 | 20% | 0 |  | 0 |  | 0 | 40% | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 25% | 2239.4634 | 25% | 2239.4634
|  | 3. Aluminum light cove, straight; Residential Tower L 23 | 38.9 | lm | 274.82 | 10690.498 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0
|  | 4. Aluminum light cove, curved ; Residential Tower L 23 | 4.35 | lm | 581.49 | 2529.4815 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0
|  | 5. Over Head & Profit on all above Items |  |  | 10% | 5835 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0
|  | Total |  |  |  | 64178 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 11281 |  | 11281
| 9 | NOC# 17 - Variation VO# 09 – Valuation of Variation - Supply and Install Glazed Curtain Wall Façade at Level 17 of the Hotel Tower. Glassline's Letter ref. GL-PL18-KC-ZH-630-L-046-22 dated 23 November, 2022
|  | 1. Additional Fixed curtain wall & Lift & sliding door ( overall size 7165 x 3865mm ) | 27.6927 | m2 | 1130 | 31292.7793 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0
|  | 1a. Steel reinforcement in mullion/transom due to jumbo glass panel | 115 | Kg | 12 | 1380 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0
|  | 2. Additional Curved Fixed curtain wall ( overall size 3290 x 3865mm ) | 12.7159 | m2 | 1698 | 21591.5133 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0
|  | 3. Add on for Aluminum Horizontal Louver type EWS-703 | 10.455 | lm | 662.0553 | 6921.7885 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0
|  | 4. Engineering | 95 | MH | 125 | 11875 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0
|  | 5. Over Head & Profit on above Item 1a & 4. |  |  | 10% | 1325.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0
|  | Total |  |  |  | 74387 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 10 | NOC# 21 - Variation VO# 10 – Valuation of Variation - Door and Fixed Glass as Replacement of Existing Door at Level 17 of the Hotel Tower. Glassline's Letter ref. GL-PL18-KC-ZH-630-L-047-22 dated 23 November, 2022
|  | 1. Abortive material procured for double leaf hinged door size 2160 x 3150mm as per approved shop drawing. | 6.804 | m2 | 847.5 | 5766.39 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0
|  | 2. Addition for supply & instalaltion for fixed curtain wall panel as a replacement of above door size 2160x3150mm | 6.804 | m2 | 1130 | 7688.52 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0
Note: Door closer/panic bar to be supplied by MC.
|  | 3. Removal of already installed fixed curtain wall panel size 1250 x 3150mm | 5 | MH | 22 | 110 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0
|  | 4. Addition for single leaf hinged door in replacement of above removed fixed curtain wall size 1250x3150mm | 1 | No | 6700 | 6700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0
|  | 5. Engineering | 35 | MH | 125 | 4375 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0
|  | 6. Over Head & Profit on above Items 3 & 5. |  |  | 10% | 448.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0
|  | Total |  |  |  | 25089 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 11 | NOC# 33 - Removal and Reinstallation of Façade Glass Panels for Mast Climber Support Bracket Installation at Level 18 of the Resident Tower. Glassline's Letter ref. GL-PL18-KC-ZH-630-L-062-22 dated 23 December, 2022
|  | 1. Removal of 3 Nos of façade glass panels at level 18 of the Residence Tower | 40 | Hours | 22 | 880 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 |  |  | 80% | 704 | 80% | 704
|  | 2 Days / 2 Labors/ 20 Hrs/Day. | [25 empty] | 0
|  | 2. Reinstallation of 3 Nos of façade glass panels at level 18 of the Residence Tower | 40 | Hours | 22 | 880 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 |  |  | 80% | 0 | 0% | 0
|  | 2 Days / 2 Labors/ 20 Hrs/Day. | [25 empty] | 0
|  | 3. Consumables | 1 | LS | 1000 | 1000 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 | 100% | 0 |  |  | 80% | 0 | 0% | 0
|  | 4. Over Head & Profit on above Items 2 & 3. |  |  | 10% | 276 | 100% | 276 | [16 empty] | 80% | 70.4 | 80% | 70.4
|  | Total |  |  |  | 3036 |  | 276 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 774.4 |  | 774.4
| 12 | NOC# 34 -Valuation of Variation GL-SOR-170 - Installed Glass Broken in Ballroom area at Ground Floor of the Hotel Tower by the Contractor, Glassline's Letter ref. GL-PL18-KC-ZH-630-L-063-22 dated 23 December, 2022 | [5 empty] | Overall for dismantling & material on site | [7 empty] | Overall for installation
|  | Overall Amount | 1 | Item | 4144 | 4144 |  | 0 | [7 empty] | 0 | [6 empty] | 0% | 0 | 0% | 0 | 0% | 0
|  | Over Head & Profit |  | 0.1 |  | 414 |  | 0 | [7 empty] | 0 | [6 empty] | 0% | 0 | 0% | 0 | 0% | 0
|  | Total |  |  |  | 4558 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
E. Total for the Variations with M/s. Khansaheb | [5 empty] | 364394 |  | 47460.75 |  | 66445.05 |  | 66445.05 |  | 9492.15 |  | 8093.6875 |  | 14084.2625 |  | 11228.3675 |  | 1545.3125 |  | 216343.75 |  | 6181.25 |  | 276277.28

## Summary Sheet (MOS Only) (hidden)
Plot 18, Plot no. BB.B03,018, Business Bay Dubai
Glassline Aluminum LLC |  | Payment Application Nr: |  | PA-P-18-018
P.O. Box 51690, Abu Dhabi
United Arab Emirates |  | Payment Application Date:
Contact: Zaki Housari |  |  |  | 2020-05-28 |  | Submission date 25th of each month
Contact Nr.: 02-5501787 / 056 867 6747 |  | Expected Payment Date: |  |  | Material 75%
To: |  |  |  | 2020-07-19 | 7days for Certficate | 45 days for Payment | 52
M/s. Roberts-Pizzarotti JV |  | Sub-Contract: |  |  | Installation 25%
P.O. Box 184886, Dubai, U.A.E. |  | Conf. Ref.: 17001DH/SCA/D&B/4041-GLASSLINE dtd 11th of Oct., 2018 |  |  | 15 days for Certficate | 37 days for Payment | 52
Tel No.: | Fax No.: | CBOQ Ref.: 17001DH/SCA/D&B/4041-GLASSLINE Annexure J
The Design and Construction of Aluminium and Glazing Façade System at Plot 18, Business Bay , Dubai, Project
Sub-Contract Value:
|  | Original Contract Value |  | #REF! | #REF!
|  | Changes in Scope of Works |  | #REF!
|  | Variaiton 01 (BP5) |  | 6409476.3438
|  | Total Contract Value |  | #REF!
Payment Details | Contract Value | To Date | Previous | Period Total
|  |  | Total | PA-P-18-018
Advance Payment 5% | #REF! |  |  | -
Add VAT 5% | #REF!
#REF!
MAIN SCOPE
Preliminaries | #REF! | #REF! | 6020000 | #REF!
Material Delivery (75%) | #REF! | #REF! | 18845400.4771 | #REF!
Installation (35%) | #REF! | 3809100.5223 | 3809100.5223 | 0
ADDITIONAL WORKS
Material Delivery (75%) | #REF! | 74108.332 | 74108.332 | 0
Installation (25%) | #REF! | 24702.7773 | 24702.7773 | 0
VARIAITON 01 BP5
Material Delivery (75%) | 4807107.2578 | 1793886.8809 | 1793886.8809 | 0
Installation (25%) | 1602369.0859 | 640947.6344 | 640947.6344 | 0 | #REF!
(A) Net Sub-Total | #REF! | #REF! | 31208146.624 | #REF! | 2818176.1895
Less Amortisiation of Adv Payment @ 5% |  | #REF! | -1555466.7757 | #REF! | #REF!
Less: 10% Retention on (A) |  | #REF! | -3120814.6624 | #REF!
(B) Net Sub-Total |  | #REF! | 26531865.1859 | #REF!
ADD 5% VAT (B) |  | #REF! | 1326593.2593 | #REF!
Net Valuation Sum This Period (B+C) |  | #REF! | 27858458.4452 | #REF!
Prepared By: |  |  | Noted By:
Sweta K.K. |  |  | Zaki Housari
Projects Co-ordinator / Q.S. (Civil) |  |  | Senior Projects Manager

## Sheet2 (hidden)
LEVEL 17 |  | New Design | Initial Design
EWS103/111
CW 01H
Frames all delivered?
Certified @80% only
CW 02S
Frames all delivered?
Certified @50% only
LEVEL 17
EWS112
| CW 01M | Certified @ 0%
| CW 01L | Certified @ 0%
| CW 01Q | Certified @ 0%

## BRKT QTY (hidden)
BRACKET QUANTITY FOR HOTEL TOWER
|  | Est. Required QTY. |  |  | Installed |  | Loose
S/N | LEVEL | BOTTOM | TOP | TOTAL | BOT(At Frame) | TOP | TOP | Total MOS | % MOS
1 | 7th FLOOR | 181 | 181 | 362 | 181 | 169 | 12 | 362 | 100%
2 | 8th FLOOR | 82 | 82 | 164 | 70 | 70 | 12 | 152 | 92.68%
3 | 9th FLOOR | 127 | 127 | 254 | 112 | 115 | 12 | 239 | 94.09%
4 | 10th FLOOR | 150 | 150 | 300 | 138 | 138 | 12 | 288 | 96%
5 | 11th FLOOR | 108 | 108 | 216 | 93 | 96 | 12 | 201 | 93.06%
6 | 12th FLOOR | 172 | 172 | 344 | 172 | 172 | 0 | 344 | 100%
7 | 13th FLOOR | 256 | 256 | 512 | 246 | 114 | 142 | 502 | 98.05%
8 | 14th FLOOR | 104 | 104 | 208 | 55 | 104 | 0 | 159 | 76.44%
9 | 15th FLOOR | 256 | 256 | 512 | 237 | 194 | 62 | 493 | 96.29%
10 | 16th FLOOR | 104 | 104 | 208 | 98 | 54 | 50 | 202 | 97.12%
11 | 17th FLOOR |  |  | 0
12 | 18th FLOOR |  |  | 0
13 | 19th FLOOR | 117 | 117 | 234 |  |  | 117 | 117 | 50%
14 | 20th FLOOR | 162 | 162 | 324 |  |  | 162 | 162 | 50%
15 | 21st FLOOR | 61 | 61 | 122 |  |  |  | 0 | 0%
16 | 22nd FLOOR | 122 | 122 | 244 |  |  |  | 0 | 0%
17 | 23rd FLOOR | 78 | 78 | 156 |  |  |  | 0 | 0%
18 | 24th FLOOR |  |  | 0
19 | 25th FLOOR |  |  | 0
20 | 26th FLOOR |  |  | 0
21 | 27th FLOOR |  |  | 0
22 | 28th FLOOR |  |  | 0
| TOTAL | 2080 | 2080 | 4160 | 1402 | 1226 | 593 | 3221
BRACKET QUANTITY FOR RESIDENCE TOWER
|  | Est. Required QTY. |  |  | Installed |  | Loose
S/N | LEVEL | BOTTOM | TOP | TOTAL | BOT(At Frame) | TOP | TOP | Total MOS | % MOS
1 | 6th FLOOR | 178 | 178 | 356 | 169 | 178 | 0 | 347 | 97.47%
2 | 7th FLOOR | 181 | 181 | 362 | 175 | 181 | 0 | 356 | 98.34%
3 | 8th FLOOR | 193 | 193 | 386 | 178 | 193 | 0 | 371 | 96.11%
4 | 9th FLOOR | 181 | 181 | 362 | 175 | 175 | 6 | 356 | 98.34%
5 | 10th FLOOR | 131 | 131 | 262 | 118 | 38 | 73 | 229 | 87.4%
6 | 11th FLOOR | 128 | 128 | 256 | 54 | 32 | 76 | 162 | 63.28%
7 | 12th FLOOR | 180 | 180 | 360 | 90 | 46 | 104 | 240 | 66.67%
8 | 13th FLOOR | 86 | 86 | 172 | 39 | 42 | 19 | 100 | 58.14%
9 | 14th FLOOR | 180 | 180 | 360 | 99 | 46 | 114 | 259 | 71.94%
10 | 15th FLOOR | 86 | 86 | 172 | 39 | 16 | 50 | 105 | 61.05%
11 | 16th FLOOR | 180 | 180 | 360 | 99 | 38 | 105 | 242 | 67.22%
12 | 17th FLOOR | 86 | 86 | 172 | 39 | 0 | 46 | 85 | 49.42%
13 | 18th FLOOR
14 | 19th FLOOR
15 | 20th FLOOR
16 | 21st FLOOR
17 | 22nd FLOOR
18 | 23rd FLOOR
19 | 24th FLOOR
20 | 25th FLOOR
21 | 26th FLOOR
22 | 27th FLOOR
23 | 28th FLOOR
| TOTAL | 1612 | 1612 | 3224 | 1105 | 807 | 593 | 2505

## Flysheet_VO_Not Used in IPA 28 (hidden)
#REF!
#REF!
#REF!
Substantiation Document for Corrected Glass Code & Associated Glass tags
Hotel & Residential

## Sheet1 (hidden)
SUMMARY OF QUANTITY TAKE OFF
HOTEL |  |  |  | Residential
|  | #REF! | Differences |  |  | #REF! | Differences
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
subtotal | #REF! | #REF! | #REF! | subtotal | #REF! | #REF! | #REF!
TOTAL
|  | CBOQ | Differences
#REF! | #REF! | #REF! | #REF!
#REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
subtotal | #REF! | #REF! | #REF!
Prepared By:
Sweta K K
Project Coordinator / Quantity Surveryor (Civil)

## NOC No.56_Cradle (hidden)
Project: Plot-18
#REF!
#REF!
Variation
NOC No. 56 - Cost of Subcontractor's Cradle and Access Equipment Used by Other Sub-contractors between 12 March 2020 and 31 August 2020
Ref. : | Glassline's Letter ref. GL-PL18-ZH-630-L-287-20 dated 15 September 2020
S. No. | Description | Amount | % Workdone to date | Amount | Remarks
1 | Cradle & Access Equipment Cost - Hotel | 7963.72 | 100% | 7963.72 | Refer to breakdown attached
2 | Cradle & Access Equipment Cost - Residential | 4380.26 | 100% | 4380.26 | Refer to breakdown attached
| Sub-total | 12343.98 |  | 12343.98
| OH & P, 10% | 1234.398 |  | 1234.398
| Grand Total (Carried to Summary) | 13578.378 |  | 13578.378

## NOC 56_BOQ_Hotel (hidden)
2020-08-31
Plot-18 - Cradle Utilized by Others-Hotel Tower
Date | Description | Cradle No. | Tower | Used By | Qty | Unit | Unit Rate | Amount | Remarks
2020-03-12 | Cradle usage | 1 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-03-12 | Cradle usage | 3 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-03-12 | Cradle usage | 2 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-03-18 | Cradle usage | 1 | Hotel | NMCC | 1 | Day | 105.1282 | 105.1282
2020-03-18 | Cradle usage | 1 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-03-19 | Cradle usage | 2 | Hotel | NMCC | 1 | Day | 105.1282 | 105.1282
2020-03-22 | Cradle usage | 1 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-03-22 | Cradle usage | 2 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-03-23 | Cradle usage | 1 | Hotel | NMCC | 1 | Day | 105.1282 | 105.1282
2020-03-23 | Cradle usage | 2 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-03-23 | Cradle usage | 3 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-03-24 | Cradle usage | 2 & 3 | Hotel | NMCC | 1 | Day | 105.1282 | 105.1282
2020-03-24 | Cradle usage | 2 & 3 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-03-25 | Cradle usage | 1 | Hotel | NMCC | 1 | Day | 105.1282 | 105.1282
2020-03-25 | Cradle usage | 2 | Hotel | NMCC | 1 | Day | 105.1282 | 105.1282
2020-03-25 | Cradle usage | 2 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-03-25 | Cradle usage | 3 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-03-28 | Cradle usage | 2 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-03-29 | Cradle usage | 3 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-03-31 | Cradle usage | 1 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-03-31 | Cradle usage | 3 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-04-01 | Cradle usage | 2 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-04-02 | Cradle usage | 3 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-04-02 | Cradle usage | 2 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-05-11 | Cradle usage | 3 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-05-11 | Cradle usage | 1 | Hotel | NMCC | 1 | Day | 105.1282 | 105.1282
2020-05-12 | Cradle usage | 3 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-05-12 | Cradle usage | 1 | Hotel | NMCC | 1 | Day | 105.1282 | 105.1282
2020-05-13 | Cradle usage | 1 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-05-13 | Cradle usage | 2 | Hotel | NMCC | 1 | Day | 105.1282 | 105.1282
2020-05-14 | Cradle usage | 2 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-05-14 | Cradle usage | 3 | Hotel | NMCC | 1 | Day | 105.1282 | 105.1282
2020-05-16 | Cradle usage | 3 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-05-16 | Cradle usage | 2 | Hotel | NMCC | 1 | Day | 105.1282 | 105.1282
2020-05-17 | Cradle usage | 1 | Hotel | Arabian Profiles | 0.5 | Day | 105.1282 | 52.5641
2020-05-17 | Cradle usage | 1 | Hotel | NMCC | 0.5 | Day | 105.1282 | 52.5641
2020-05-17 | Monorail usage |  | Hotel | NMCC | 1 | Day | 384.6154 | 384.6154
2020-05-18 | Cradle usage | 2 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-05-18 | Cradle usage | 1 | Hotel | NMCC | 1 | Day | 105.1282 | 105.1282
2020-05-19 | Cradle usage | 1 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-05-20 | Cradle usage | 1 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-05-27 | Cradle usage | 1 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-05-28 | Cradle usage | 3 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-05-30 | Cradle usage | 2 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-05-31 | Cradle usage | 1 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-06-01 | Cradle usage | 2 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-06-02 | Cradle usage | 3 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-06-03 | Cradle usage | 3 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-06-04 | Cradle usage | 3 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-06-06 | Cradle usage | 2 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-06-07 | Cradle usage | 1 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-08-04 | Cradle usage | 3 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-08-05 | Cradle usage | 2 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-08-06 | Cradle usage | 1 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-08-08 | Cradle usage | 2 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-08-09 | Cradle usage | 2 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-08-10 | Cradle usage | 1 | Hotel | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-08-11 | Cradle usage | 2 | Hotel | Arabian Profiles | 1 | Day | 106.1282 | 106.1282
2020-08-12 | Cradle usage | 3 | Hotel | Arabian Profiles | 1 | Day | 107.1282 | 107.1282
2020-08-13 | Cradle usage | 1 | Hotel | Arabian Profiles | 1 | Day | 108.1282 | 108.1282
2020-08-15 | Cradle usage | 1 | Hotel | Arabian Profiles | 1 | Day | 109.1282 | 109.1282
2020-08-16 | Cradle usage | 2 | Hotel | Arabian Profiles | 1 | Day | 110.1282 | 110.1282
2020-08-17 | Cradle usage | 2 | Hotel | Arabian Profiles | 1 | Day | 111.1282 | 111.1282
2020-08-18 | Cradle usage | 2 | Hotel | Arabian Profiles | 1 | Day | 112.1282 | 112.1282
2020-08-19 | Cradle usage | 1 | Hotel | Arabian Profiles | 1 | Day | 113.1282 | 113.1282
2020-08-20 | Cradle usage | 2 | Hotel | Arabian Profiles | 1 | Day | 114.1282 | 114.1282
2020-08-22 | Cradle usage | 3 | Hotel | Arabian Profiles | 1 | Day | 115.1282 | 115.1282
2020-08-24 | Cradle usage | 3 | Hotel | Arabian Profiles | 1 | Day | 115.1282 | 115.1282
2020-08-25 | Cradle usage | 2 | Hotel | Arabian Profiles | 1 | Day | 115.1282 | 115.1282
2020-08-26 | Cradle usage | 1 | Hotel | Arabian Profiles | 1 | Day | 115.1282 | 115.1282
2020-08-29 | Cradle usage | 1 | Hotel | Arabian Profiles | 1 | Day | 115.1282 | 115.1282
2020-08-30 | Cradle usage | 2 | Hotel | Arabian Profiles | 1 | Day | 115.1282 | 115.1282
2020-08-31 | Cradle usage | 3 | Hotel | Arabian Profiles | 1 | Day | 115.1282 | 115.1282
Subtotal |  |  |  |  | 71 |  |  | 7963.7179 |  | 12343.9744
| Over Head & Profit | [5 empty] | 10% | 796.3718 |  | 1234.3974
Total |  |  |  |  | 71 |  |  | 8760.0897 |  | 13578.3718

## NOC 56_BOQ_Residential (hidden)
2020-08-31
Plot-18 - Cradle Utilized by Others-Residence Tower
Date | Description | Cradle No. | Tower | Used By | Qty | Unit | Unit Rate | Amount | Remarks
2020-04-02 | Cradle usage | 4 | Residence | NMCC | 1 | Day | 105.1282 | 105.1282
2020-04-02 | Cradle usage | 5 | Residence | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-05-10 | Cradle usage | 4 | Residence | Unigas | 1 | Day | 105.1282 | 105.1282
2020-05-12 | Cradle usage | 4 | Residence | Unigas | 1 | Day | 105.1282 | 105.1282
2020-05-13 | Cradle usage | 4 | Residence | Unigas | 1 | Day | 105.1282 | 105.1282
2020-05-14 | Cradle usage | 4 | Residence | Unigas | 1 | Day | 105.1282 | 105.1282
2020-05-15 | Cradle usage | 4 | Residence | Unigas | 1 | Day | 105.1282 | 105.1282
2020-05-16 | Cradle usage | 4 | Residence | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-05-17 | Cradle usage | 5 | Residence | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-05-18 | Cradle usage | 4 | Residence | Unigas | 1 | Day | 105.1282 | 105.1282
2020-05-18 | Cradle usage | 5 | Residence | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-05-19 | Cradle usage | 6 | Residence | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-05-20 | Cradle usage | 4 | Residence | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-05-21 | Cradle usage | 5 | Residence | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-05-26 | Cradle usage | 6 | Residence | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-05-27 | Cradle usage | 4 | Residence | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-05-28 | Cradle usage | 5 | Residence | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-05-30 | Cradle usage | 6 | Residence | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-05-31 | Cradle usage | 4 | Residence | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-06-01 | Cradle usage | 5 | Residence | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-06-02 | Cradle usage | 6 | Residence | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-08-03 | Cradle usage | 6 | Residence | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-08-04 | Cradle usage | 4 | Residence | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-08-05 | Cradle usage | 4 | Residence | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-08-09 | Cradle usage | 4 | Residence | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-08-10 | Cradle usage | 5 | Residence | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-08-11 | Cradle usage | 6 | Residence | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-08-12 | Cradle usage | 4 | Residence | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-08-15 | Cradle usage | 6 | Residence | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-08-16 | Cradle usage | 4 | Residence | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-08-18 | Cradle usage | 5 | Residence | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-08-19 | Cradle usage | 6 | Residence | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-08-20 | Cradle usage | 4 | Residence | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-08-22 | Cradle usage | 4 | Residence | Arabian Profiles | 1 | Day | 105.1282 | 105.1282
2020-08-24 | Cradle usage | 5 | Residence | Arabian Profiles | 1 | Day | 115.1282 | 115.1282
2020-08-25 | Cradle usage | 5 | Residence | Arabian Profiles | 1 | Day | 115.1282 | 115.1282
2020-08-26 | Cradle usage | 4 | Residence | Arabian Profiles | 1 | Day | 115.1282 | 115.1282
2020-08-27 | Cradle usage | 4 | Residence | Arabian Profiles | 1 | Day | 115.1282 | 115.1282
2020-08-29 | Cradle usage | 6 | Residence | Arabian Profiles | 1 | Day | 115.1282 | 115.1282
2020-08-30 | Cradle usage | 6 | Residence | Arabian Profiles | 1 | Day | 115.1282 | 115.1282
2020-08-31 | Cradle usage | 5 | Residence | Arabian Profiles | 1 | Day | 115.1282 | 115.1282
Subtotal |  |  |  |  | 41 |  |  | 4380.2564
| Over Head & Profit | [5 empty] | 10% | 438.0256
Total |  |  |  |  | 41 |  |  | 4818.2821