## Summary
No | Description | BOQ Amount | Previous Amount | Current Amount | % | Cumulative Amount
| Main Scope | 54387.15 | 64747.549 | 0 | 119% | 64747.549
| Variations |  | 449858.935 | 18867.52 |  | 468726.455
|  |  | 514606.484 | 18867.52 |  | 533474.004
Note on E3: Himal Kosala: Only 80% will certified due to following reasons Variation not finalized (hold 10%) WIR not raised (hold 10%)

## BOQ
Project Name : DORCHESTER HOTEL & RESIDENCES Sub Contractor: Data Link Technical Services L.L.C Main Contractor - KHANSAHEB ENGINEERING L.L.C Dubai- UAE PAYMENT APPLICATION NO :01
SL | Description | QTY | Unit | RATE for framing with supports | RATE for One Side boarding with tape & Joint | RATE | Workdone Progress Quantity |  |  | Workdone Progress Amount(AED)
[7 empty] | Previous | Current | Total | Previous | Current | Total
BOQ
GROUND FLOOR
1 | Location-1; Size 5300 x 6500 mm | 34.45 | M2 | 50 | 35 |  | 34.45 |  | 34.45 | 2928.25 |  | 2928.25
2 | Location-2; Size 1220 x 2220 mm | 2.71 | M2 | 50 | 35 |  | 2.71 |  | 2.71 | 230.35 |  | 230.35
3 | Location-3; Size 1220 x 2150 mm- 2 nos | 0 | M2 | 50 | 35 |  |  | 0 | 0 | 0 |  | 0
4 | Location-4; Size 2200 x 3350 mm | 7.37 | M2 | 50 | 35 |  | 7.37 |  | 7.37 | 626.45 |  | 626.45
5 | Location-5; Size 2200 x 3350 mm | 7.37 | M2 | 50 | 35 |  | 7.37 |  | 7.37 | 626.45 |  | 626.45
6 | Location-6; Size 2200 x 3350 mm | 7.37 | M2 | 50 | 35 |  | 7.37 |  | 7.37 | 626.45 |  | 626.45
7 | Location-7; Size 1950 x 3350 mm | 6.5325 | M2 | 50 | 35 |  | 6.5325 |  | 6.5325 | 555.2625 |  | 555.2625
8 | Location-8; Size 2100 x 3350 mm | 7.035 | M2 | 50 | 35 |  | 7.035 |  | 7.035 | 597.975 |  | 597.975
9 | Location-9 |  | M2 | 50 | 35 |  |  | 0 | 0 | 0 |  | 0
10 | Location-10 |  | M2 | 50 | 35 |  |  | 0 | 0 | 0 |  | 0
11 | Location-11; Size 4200 x 6500 mm | 27.3 | M2 | 50 | 35 |  | 27.3 |  | 27.3 | 2320.5 |  | 2320.5
12 | Location-12; Size 1930 x 2600 mm | 5.018 | M2 | 50 | 35 |  | 5.018 |  | 5.018 | 426.53 |  | 426.53
13 | Location-13; Size 1250 x 2150 mm- x 2 nos | 5.375 | M2 | 50 | 35 |  | 5.375 |  | 5.375 | 456.875 |  | 456.875
14 | Location-14; Size 1200 x 2420 mm | 2.904 | M2 | 50 | 35 |  | 2.904 |  | 2.904 | 246.84 |  | 246.84
15 | Location-15; Size 1200 x 2100 mm | 2.52 | M2 | 50 | 35 |  | 2.52 |  | 2.52 | 214.2 |  | 214.2
16 | Location-16; Size 1220 x 2550 mm | 3.111 | M2 | 50 | 35 |  | 3.111 |  | 3.111 | 264.435 |  | 264.435
17 | Location-17; Size 2150 x 3450 mm | 7.4175 | M2 | 50 | 35 |  | 7.4175 |  | 7.4175 | 630.4875 |  | 630.4875
18 | Location-18; Size 4400 x 3450 mm | 15.18 | M2 | 50 | 35 |  | 15.18 |  | 15.18 | 1290.3 |  | 1290.3
19 | Location-19; Size 2150 x 3450 mm | 7.4175 | M2 | 50 | 35 |  | 7.4175 |  | 7.4175 | 630.4875 |  | 630.4875
20 | Location-20; Size 2150 x 3450 mm | 7.4175 | M2 | 50 | 35 |  | 7.4175 |  | 7.4175 | 630.4875 |  | 630.4875
21 | Location-21; Size 2150 x 3450 mm | 7.4175 | M2 | 50 | 35 |  | 7.4175 |  | 7.4175 | 630.4875 |  | 630.4875
22 | Location-22; Size 2150 x 3450 mm | 7.4175 | M2 | 50 | 35 |  | 7.4175 |  | 7.4175 | 630.4875 |  | 630.4875
23 | Location-23; Size 2050 x 3450 mm Ref: Additional Work | [6 empty] | 0 | 0 | 0 |  | 0
24 | Location-24; Size 2050 x 3450 mm Ref: Additional Work
25 | Single Doors | 8 | Nos. |  |  | 250 | 8 |  | 8 | 2000 |  | 2000
26 | Double Door | 1 | Nos. |  |  | 250 | 1 |  | 1 | 250 |  | 250
| 2ND FLOOR | [6 empty] | 0 | 0 | 0 |  | 0
27 | Location-1; Size 3200 x 3100 mm | 9.92 | M2 | 50 | 35 |  | 9.92 |  | 9.92 | 843.2 |  | 843.2
28 | Location-2; Size 2150 x 3130 mm | 6.7295 | M2 | 50 | 35 |  | 6.7295 |  | 6.7295 | 572.0075 |  | 572.0075
29 | Location-3; Size 1100 x 2140 mm | 2.354 | M2 | 50 | 35 |  | 2.354 |  | 2.354 | 200.09 |  | 200.09
30 | Location-4; Size 2130 x 3320 mm |  | M2 | 50 | 35 |  |  | 0 | 0 | 0 |  | 0
31 | Location-5; Size 2150 x 3320 mm |  | M2 | 50 | 35 |  |  | 0 | 0 | 0 |  | 0
32 | Location-6; Size 2150 x 3320 mm Ref: Additional Work | 7.138 | M2 | [6 empty] | 0 |  | 0
33 | Location-7; Size 2150 x 3320 mm Ref: Additional Work | 7.138 | M2 | [6 empty] | 0 |  | 0
34 | Location-8; Size 2150 x 4350 mm Ref: Additional Work | 9.3525 | M2 | [6 empty] | 0 |  | 0
35 | Location-9; Size 2150 x 3320 mm Ref: Additional Work | 7.138 | M2 | [6 empty] | 0 |  | 0
36 | Location-10; Size 2150 x 4350 mm Ref: Additional Work | 9.3525 | M2 | [6 empty] | 0 |  | 0
37 | Location-12; Size 4650 x 8500 mm | 39.525 | M2 | 50 | 35 |  | 39.525 |  | 39.525 | 3359.625 |  | 3359.625
38 | Location-12 A; Size 1200 x 8500 mm | 10.2 | M2 | 50 | 35 |  | 10.2 |  | 10.2 | 867 |  | 867
39 | Location-13; Size 2160 x 3250 mm | 7.02 | M2 | 50 | 35 |  | 7.02 |  | 7.02 | 596.7 |  | 596.7
40 | Location-13 A; Size 2160 x 3250 mm | 7.02 | M2 | 50 | 35 |  | 7.02 |  | 7.02 | 596.7 |  | 596.7
41 | Location-13 B; Size 2160 x 3250 mm | 7.02 | M2 | 50 | 35 |  | 7.02 |  | 7.02 | 596.7 |  | 596.7
42 | Location-14; Size 2000 x 3350 mm | 6.7 | M2 | 50 | 35 |  | 6.7 |  | 6.7 | 569.5 |  | 569.5
43 | Location-15; Size 2000 x 3350 mm | 6.7 | M2 | 50 | 35 |  | 6.7 |  | 6.7 | 569.5 |  | 569.5
44 | Location-16; Size 1500 x 2300 mm | 3.45 | M2 | 50 | 35 |  | 3.45 |  | 3.45 | 293.25 |  | 293.25
45 | Location-17; Size 1200 x 2100 mm | 2.52 | M2 | 50 | 35 |  | 2.52 |  | 2.52 | 214.2 |  | 214.2
46 | Location-18; Size 1200 x 2100 mm |  | M2 | 50 | 35 |  |  | 0 | 0 | 0 |  | 0
47 | Location-19; Size 3200 x 7200 mm | 23.04 | M2 | 50 | 35 |  | 23.04 |  | 23.04 | 1958.4 |  | 1958.4
48 | Location-20; Size 1200 x 2100 mm | 2.52 | M2 | 50 | 35 |  | 2.52 |  | 2.52 | 214.2 |  | 214.2
49 | Location-21; Size 1000 x 2200 mm | 2.52 | M2 | 50 | 35 |  | 2.52 |  | 2.52 | 214.2 |  | 214.2
50 | Location-22; Size 2150 x 3130 mm |  | M2 | 50 | 35 |  |  | 0 | 0 | 0 |  | 0
51 | Location-23; Size 1150 x 2100 mm |  | M2 | 50 | 35
52 | Doors | 6 | Nos. |  |  | 250 | 6 |  | 6 | 1500 |  | 1500
[8 empty] | 0 | 0 | 0 |  | 0
| 4th FLOOR | [6 empty] | 0 | 0 | 0 |  | 0
53 | Location-1; Size 2200 x 3350 mm | 7.37 | M2 | 50 | 35 |  | 7.37 |  | 7.37 | 626.45 |  | 626.45
54 | Location-2; Size 1200 x 2130 mm | 2.556 | M2 | 50 | 35 |  | 2.556 |  | 2.556 | 217.26 |  | 217.26
55 | Location-3; Size 1200 x 2100 mm | 2.52 | M2 | 50 | 35 |  | 2.52 |  | 2.52 | 214.2 |  | 214.2
56 | Location-4; Size 2200 x 3210 mm | 7.062 | M2 | 50 | 35 |  | 7.06 |  | 7.06 | 600.1 |  | 600.1
57 | Location-5; Size 2200 x 3210 mm | 7.062 | M2 | 50 | 35 |  | 7.062 |  | 7.062 | 600.27 |  | 600.27
58 | Location-6; Size 1800 x 3250 mm | 5.85 | M2 | 50 | 35 |  | 5.85 |  | 5.85 | 497.25 |  | 497.25
59 | Location-7; Size 2170 x 3250 mm | 7.0525 | M2 | 50 | 35 |  | 7.0525 |  | 7.0525 | 599.4625 |  | 599.4625
60 | Location-8; Size 2200 x 3250 mm | 7.15 | M2 | 50 | 35 |  | 7.15 |  | 7.15 | 607.75 |  | 607.75
61 | Location-9; Size 2170 x 3250 mm | 7.0525 | M2 | 50 | 35 |  | 7.0525 |  | 7.0525 | 599.4625 |  | 599.4625
62 | Location-9 A; Size 2170 x 3250 mm | 7.0525 | M2 | 50 | 35 |  | 7.0525 |  | 7.0525 | 599.4625 |  | 599.4625
63 | Location-9 B; Size 2400 X 4200 mm (Ceiling area) | 10.08 | M2 | 50 | 35 |  | 10.08 |  | 10.08 | 856.8 |  | 856.8
64 | Location-10; Size 2460 x 2130 mm | 5.2398 | M2 | 50 | 35 |  | 5.2398 |  | 5.2398 | 445.383 |  | 445.383
65 | Location-11; Size 2200 x 3250 mm | 7.15 | M2 | 50 | 35 |  | 7.15 |  | 7.15 | 607.75 |  | 607.75
66 | Location-12; Size 1230 x 2100 mm | 2.583 | M2 | 50 | 35 |  | 2.583 |  | 2.583 | 219.555 |  | 219.555
67 | Location-13; Size 2200 x 3350 mm | 7.37 | M2 | 50 | 35 |  | 7.37 |  | 7.37 | 626.45 |  | 626.45
68 | Location-14; Size 2200 x 3250 mm | 7.15 | M2 | 50 | 35 |  | 7.15 |  | 7.15 | 607.75 |  | 607.75
69 | Location-15; Size 2200 x 3250 mm | 7.15 | M2 | 50 | 35 |  | 7.15 |  | 7.15 | 607.75 |  | 607.75
70 | Location-16; Size 2200 x 3250 mm | 7.15 | M2 | 50 | 35 |  | 7.15 |  | 7.15 | 607.75 |  | 607.75
71 | Location-17; Size 1600 x 4300 mm | 6.88 | M2 | 50 | 35 |  | 6.88 |  | 6.88 | 584.8 |  | 584.8
72 | Doors | 10 | Nos |  |  | 250 | 10 |  | 10 | 2500 |  | 2500
7th FLOOR
73 | Doors | 2 | Nos |  |  | 250 | 2 |  | 2 | 500 |  | 500
| 9th FLOOR | [6 empty] | 0 | 0 | 0 |  | 0
74 | Location-1; Size 1200 x 2100 mm | 2.52 | M2 | 50 | 35 |  | 2.52 |  | 2.52 | 214.2 |  | 214.2
75 | Location-2; Size 1200 x 2100 mm | 2.52 | M2 | 50 | 35 |  | 2.52 |  | 2.52 | 214.2 |  | 214.2
76 | Doors | 2 | Nos |  |  | 250 | 2 |  | 2 | 500 |  | 500
| 10th FLOOR | [6 empty] | 0 | 0 | 0 |  | 0
77 | Location-1; Size 1200 x 2100 mm | 2.52 | M2 | 50 | 35 |  | 2.52 |  | 2.52 | 214.2 |  | 214.2
78 | Location-2; Size 1200 x 2100 mm | 2.52 | M2 | 50 | 35 |  | 2.52 |  | 2.52 | 214.2 |  | 214.2
79 | Doors | 2 | Nos |  |  | 250 | 2 |  | 2 | 500 |  | 500
| 11th FLOOR | [6 empty] | 0 | 0 | 0 |  | 0
80 | Location-1; Size 1200 x 2100 mm | 2.52 | M2 | 50 | 35 |  | 2.52 |  | 2.52 | 214.2 |  | 214.2
81 | Location-2; Size 1200 x 2100 mm | 2.52 | M2 | 50 | 35 |  | 2.52 |  | 2.52 | 214.2 |  | 214.2
82 | Doors | 2 | Nos |  |  | 250 | 2 |  | 2 | 500 |  | 500
| 12th FLOOR | [6 empty] | 0 | 0 | 0 |  | 0
83 | Location-1; Size 1250 x 2110 mm | 2.6375 | M2 | 50 | 35 |  | 2.6375 |  | 2.6375 | 224.1875 |  | 224.1875
84 | Location-2; Size 1200 x 2100 mm | 2.52 | M2 | 50 | 35 |  | 2.52 |  | 2.52 | 214.2 |  | 214.2
85 | Location-3; Size 1200 x 2100 mm | 2.52 | M2 | 50 | 35 |  | 2.52 |  | 2.52 | 214.2 |  | 214.2
86 | Doors | 3 | Nos |  |  | 250 | 3 |  | 3 | 750 |  | 750
| 13th FLOOR | [6 empty] | 0 | 0 | 0 |  | 0
87 | Location-1; Size 1200 x 2130 mm | 2.556 | M2 | 50 | 35 |  | 2.556 |  | 2.556 | 217.26 |  | 217.26
88 | Location-2; Size 1200 x 2100 mm | 2.52 | M2 | 50 | 35 |  | 2.52 |  | 2.52 | 214.2 |  | 214.2
89 | Location-2; Size 1250 x 2100 mm | 2.625 | M2 | 50 | 35 |  | 2.625 |  | 2.625 | 223.125 |  | 223.125
90 | Doors | 3 | Nos |  |  | 250 | 3 |  | 3 | 750 |  | 750
| 14th FLOOR | [6 empty] | 0 | 0 | 0 |  | 0
91 | Location-1; Size 1200 x 2100 mm | 2.52 | M2 | 50 | 35 |  | 2.52 |  | 2.52 | 214.2 |  | 214.2
92 | Location-2; Size 1200 x 2100 mm | 2.52 | M2 | 50 | 35 |  | 2.52 |  | 2.52 | 214.2 |  | 214.2
93 | Location-2; Size 1250 x 2100 mm | 2.625 | M2 | 50 | 35 |  | 2.625 |  | 2.625 | 223.125 |  | 223.125
94 | Doors | 3 | Nos |  |  | 250 | 3 |  | 3 | 750 |  | 750
| 15th FLOOR | [6 empty] | 0 | 0 | 0 |  | 0
95 | Location-1; Size 1200 x 2110 mm | 2.532 | M2 | 50 | 35 |  | 2.532 |  | 2.532 | 215.22 |  | 215.22
96 | Location-2; Size 1200 x 2130 mm | 2.556 | M2 | 50 | 35 |  | 2.556 |  | 2.556 | 217.26 |  | 217.26
97 | Location-2; Size 1250 x 2120 mm | 2.65 | M2 | 50 | 35 |  | 2.65 |  | 2.65 | 225.25 |  | 225.25
98 | Doors | 3 | Nos |  |  | 250 | 3 |  | 3 | 750 |  | 750
| 16th FLOOR | [6 empty] | 0 | 0 | 0 |  | 0
99 | Location-1; Size 1200 x 2130 mm | 2.556 | M2 | 50 | 35 |  | 2.556 |  | 2.556 | 217.26 |  | 217.26
100 | Location-2; Size 1200 x 2120 mm | 2.544 | M2 | 50 | 35 |  | 2.544 |  | 2.544 | 216.24 |  | 216.24
101 | Doors | 2 | Nos |  |  | 250 | 2 |  | 2 | 500 |  | 500
| 17th FLOOR | [6 empty] | 0 | 0 | 0 |  | 0
102 | Doors | 2 | Nos |  |  | 250 | 2 |  | 2 | 500 |  | 500
| 18th FLOOR | [7 empty] | 0 | 0 |  | 0
103 | Doors | 1 | Nos |  |  | 250 | 1 |  | 1 | 250 |  | 250
| 19th FLOOR | [7 empty] | 0 | 0 |  | 0
104 | Doors | 2 | Nos |  |  | 250 | 2 |  | 2 | 500 |  | 500
| 20th FLOOR | [7 empty] | 0 | 0 |  | 0
105 | Doors | 2 | Nos |  |  | 250 | 2 |  | 2 | 500 |  | 500
| 21st FLOOR | [7 empty] | 0 | 0 |  | 0
106 | Doors | 2 | Nos |  |  | 250 | 2 |  | 2 | 500 |  | 500
| 22nd FLOOR | [7 empty] | 0 | 0 |  | 0
107 | Doors | 2 | Nos |  |  | 250 | 2 |  | 2 | 500 |  | 500
| 23rd FLOOR | [6 empty] | 0 | 0 | 0 |  | 0
108 | Partitions 2100x2100 and 2150x3200 (Residential Tower) | 11.29 | M2 | 50 | 35 |  | 11.29 |  | 11.29 | 959.65 |  | 959.65
109 | Doors (Residential Tower) | 4 |  |  |  | 250 | 4 |  | 4 | 1000 |  | 1000
110 | Doors (Hotel Tower) | 2 | Nos |  |  | 250 | 2 |  | 2 | 500 |  | 500
| 24thFLOOR | [7 empty] | 0 | 0 |  | 0
111 | Doors | 3 | Nos |  |  | 250 | 3 |  | 3 | 750 |  | 750
| 25th FLOOR | [7 empty] | 0 | 0 |  | 0
112 | Doors | 3 | Nos |  |  | 250 | 3 |  | 3 | 750 |  | 750
| 26th FLOOR | [7 empty] | 0 | 0 |  | 0
113 | Doors | 3 | Nos |  |  | 250 | 3 |  | 3 | 750 |  | 750
| 27th FLOOR | [7 empty] | 0 | 0 |  | 0
114 | Doors | 3 | Nos |  |  | 250 | 3 |  | 3 | 750 |  | 750
| 28th FLOOR | [6 empty] | 0 | 0 | 0 |  | 0
115 | Location-1; Size 1200 x 2150 mm | 2.58 | M2 | 50 | 35 |  | 2.58 |  | 2.58 | 219.3 |  | 219.3
116 | Location-2; Size 1800 x 3250 mm | 5.85 | M2 | 50 | 35 |  | 5.85 |  | 5.85 | 497.25 |  | 497.25
117 | Location-3; Size 1200 x 2150 mm | 2.58 | M2 | 50 | 35 |  | 2.58 |  | 2.58 | 219.3 |  | 219.3
118 | Location-4; Size 1230 x 2150 mm | 2.6445 | M2 | 50 | 35 |  | 2.6445 |  | 2.6445 | 224.7825 |  | 224.7825
119 | Location-5; Size 1300 x 2600 mm | 3.38 | M2 | 50 | 35 |  | 3.38 |  | 3.38 | 287.3 |  | 287.3
120 | Location-6; Size 1000 x 2200 mm | 2.64 | M2 | 50 | 35 |  | 2.64 |  | 2.64 | 224.4 |  | 224.4
121 | Location-7; Size 1860 x 3160 mm | 5.8776 | M2 | 50 | 35 |  | 5.8776 |  | 5.8776 | 499.596 |  | 499.596
122 | Location-8; Size 1240 x 2150 mm | 2.666 | M2 | 50 | 35 |  | 2.666 |  | 2.666 | 226.61 |  | 226.61
123 | Location-9; Size 1000 x 2200 mm |  | M2 | 50 | 35 |  |  | 0 | 0 | 0 | 0 | 0
124 | Location-10; Size 800 x 2000 mm |  | M2 | 50 | 35 |  |  | 0 | 0 | 0 | 0 | 0
125 | Doors | 6 | Nos |  |  | 250 | 6 |  | 6 | 1500 |  | 1500
| Additional work | [6 empty] | 0 | 0 | 0 | 0 | 0
| GROUND FLOOR : New Glass Line Office | [8 empty] | 0
126 | Location-23; Size 2050 x 3450 mm Two side Gypsum board partition | 7.0725 | M2 | 50 | 70 |  | 7.0725 |  | 7.0725 | 848.7 |  | 848.7
127 | Location-24; Size 2050 x 3450 mm Two side Gypsum board partition | 7.0725 | M2 | 50 | 70 |  | 7.0725 |  | 7.0725 | 848.7 |  | 848.7
128 | Doors Gf Location 23 & 24 | 2 | Nos. |  |  | 250 | 2 |  | 2 | 500 |  | 500
129 | Two side Partition between Office ; Size 4150 x 3300 mm | 13.695 | M2 | 50 | 70 |  | 13.695 |  | 13.695 | 1643.4 |  | 1643.4
0
| GROUND FLOOR : MAIN LIFT LOBBY | [8 empty] | 0
130 | New Door Added to the Existing Partition (Cut the board + add supports + paint & Rectify the area) Ref : picture | 1 | NO |  |  | 500 | 1 |  | 1 | 500 |  | 500
| LEVEL 2 :New workers laydown area + Canteen | [6 empty] | 0 | 0 | 0 |  | 0
131 | Two side Gypsum board partition @ Canteen (Ref: pic-01) | 69 | M2 | 50 |  | 70 | 69 |  | 69 | 8280 |  | 8280
132 | Gypsum Board Ceiling With Supports @ Canteen (Ref: pic-01) | 21.4 | M2 | 65 |  | 35 | 21.4 |  | 21.4 | 2140 |  | 2140
133 | Canteen Counter @ Canteen (Ref: pic-01) | 1 | No |  |  | 500 | 1 |  | 1 | 500 |  | 500
134 | Location-6; Size 2150 x 3320 mm (Two side Gypsum board partition (Ref: pic-04) | 7.138 | M2 | 50 |  | 70 | 7.138 |  | 7.138 | 856.56 |  | 856.56
135 | Location-7; Size 2150 x 3320 mm (Two side Gypsum board partition (Ref: pic-04) | 7.138 | M2 | 50 |  | 70 | 7.138 |  | 7.138 | 856.56 |  | 856.56
136 | Location-8; Size 2150 x 4350 mm (Ref: pic-03) | 9.3525 | M2 | 50 | 35 |  | 9.3525 |  | 9.3525 | 794.9625 |  | 794.9625
137 | Location-9; Size 2150 x 3320 mm (Two side Gypsum board partition (Ref: pic-04) | 7.138 | M2 | 50 |  | 70 | 7.138 |  | 7.138 | 856.56 |  | 856.56
138 | Location-10; Size 2150 x 4350 mm (Ref: pic-03) | 9.3525 | M2 | 50 | 35 |  | 9.3525 |  | 9.3525 | 794.9625 |  | 794.9625
139 | 250 x 2150 mm * 12 Nos. Opening Closing Above Doors Area ( Bulkhead) (Ref: pic-02) | 25.8 | LM |  |  | 70 | 25.8 |  | 25.8 | 1806 |  | 1806
140 | Opening Closing High Area @ Staircase ( 1150 x 2400 mm & 1230 x 2400mm ) (Ref: pic-02) | 5.712 | M2 | 50 | 35 |  | 5.712 |  | 5.712 | 485.52 |  | 485.52
141 | Doors | 6 | Nos. |  |  | 250 | 6 |  | 6 | 1500 |  | 1500
SITE OFFICE MODIFICATIONS (Additional work 02)
Ground Floor KCE Staff Office
142 | Two side gypsum board Partition 3040+3200 & 7400+500 = 14140 LM x 2500 mm Height | 35.35 | M2 | 50 |  | 70 | 35.35 |  | 35.35 | 4242 |  | 4242
143 | Painting @ Office; Size 2570 x 3760 mm | 70.7 | M2 |  |  | 15 | 70.7 |  | 70.7 | 1060.5 |  | 1060.5
144 | door | 3 | Nos. |  |  | 250 | 3 |  | 3 | 750 |  | 750
BASEMENT 2 @ Office
145 | Two side Partition @ Office; Size 2570 x 3760 mm | 9.66 | M2 | 50 |  | 70 | 9.66 |  | 9.66 | 1159.2 |  | 1159.2
146 | Painting @ Office; Size 2570 x 3760 mm | 19.32 | M2 |  |  | 15 | 19.32 |  | 19.32 | 289.8 |  | 289.8
147 | door | 1 | Nos. |  |  | 250 | 1 |  | 1 | 250 |  | 250
| LEVEL 2 - KMEP OFFICE | [10 empty] | 0
148 | Two side Gypsum board partitions 150+1140+8220+2060 = 11570 LM x 2400 mm Height | 27.77 | M2 | 50 |  | 70 | 27.77 |  | 27.77 | 3332.4 |  | 3332.4
149 | Painting @ Office; Size 2570 x 3760 mm | 55.54 | M2 |  |  | 15 | 55.54 |  | 55.54 | 833.1 |  | 833.1
150 | door | 2 | Nos. |  |  | 250 | 2 |  | 2 | 500 |  | 500
Basement 1 - workers laydown area (Rest Area)
151 | Gypsum board partitions (As per Sketch) | 197.25 | M2 | 50 | 35 |  | 197.25 |  | 197.25 | 16766.25 |  | 16766.25
152 | Gypsum Tile Ceiling (As per Sketch) | 171.6 | M2 | 42 | 26 |  | 171.6 |  | 171.6 | 11668.8 |  | 11668.8
153 | 600mm Gypsum board Bulkhead (As per Sketch) | 53.05 | LM |  |  | 33 | 53.05 |  | 53.05 | 1750.65 |  | 1750.65
154 | Doors | 3 | Nos |  |  | 250 | 3 |  | 3 | 750 |  | 750
Guest Room Doors
155 | 24thFLOOR Guest Rooms Temporary Doors | 9 | Nos |  |  | 250 | 9 |  | 9 | 2250 | 0 | 2250
156 | 25thFLOOR Guest Rooms Temporary Doors | 13 | Nos |  |  | 250 | 13 |  | 13 | 3250 | 0 | 3250
157 | 26thFLOOR Guest Rooms Temporary Doors | 16 | Nos |  |  | 250 | 16 |  | 16 | 4000 | 0 | 4000
158 | 27thFLOOR Guest Rooms Temporary Doors | 16 | Nos |  |  | 250 | 16 |  | 16 | 4000 | 0 | 4000
[8 empty] | 0 | 0 |  | 0 | 0
| GROUND FLOOR - Sales Office Corridor (Quotation 03) | [6 empty] | 0 | 0 |  | 0 | 0
159 | Supply and Installation of Gypsum board partitions (as per Dwgs) | 238.26 | M2 |  |  | 105 | 238.26 |  | 238.26 | 25017.3 | 0 | 25017.3
160 | Supply and Installation of Cement board Cladding -outside area (as per Dwgs) (100 % completed) | 238.26 | M2 |  |  | 65 | 238.26 |  | 238.26 | 15486.9 | 0 | 15486.9
161 | Supply and Apply of Painting (Inside only) ceiling & partition including Cove Light | 332.91 | M2 |  |  | 19 | 332.91 |  | 332.91 | 6325.29 | 0 | 6325.29
162 | Supply and Installation of TOP LAYER Cement board Ceiling (Above AC Duct Area) | 102.57 | M2 |  |  | 115 | 102.57 |  | 102.57 | 11795.55 | 0 | 11795.55
163 | Supply and Installation of Gypsum board Ceiling (100 % completed) | 94.65 | M2 |  |  | 85 | 94.65 | 0 | 94.65 | 8045.25 | 0 | 8045.25
164 | Supply and Installation of Cove Light (100 % completed) | 79.14 | LM |  |  | 65 | 79.14 | 0 | 79.14 | 5144.1 | 0 | 5144.1
165 | Supply and Installation of insulation @ partition area only | 238.26 | M2 |  |  | 22 | 238.26 |  | 238.26 | 5241.72 | 0 | 5241.72
| Modifications of site Facilities (Quotation 04) | [6 empty] | 0 | 0 |  | 0 | 0
| GROUND FLOOR – Safety Office area | [6 empty] | 0 | 0 |  | 0 | 0
166 | Removing Existing Partitions Near Column = 1.3 +1.3x7.5=19.5m2 | 19.5 | LS |  |  | 500 | 19.5 |  | 19.5 | 500 |  | 500
167 | Supply Installation of Two side Gypsum board partitions 1.67+1.98x2.4 = 8.76 m2 | 8.76 | M2 | 50 |  | 70 | 8.76 |  | 8.76 | 1051.2 |  | 1051.2
| Level 2 – Omniyat Office change Entrance | [6 empty] | 0 | 0 |  | 0 | 0
168 | Supply Installation of Two side Gypsum board partitions 2.27x2.50=5.67 m2 | 5.67 |  | 50 |  | 70 | 5.67 |  | 5.67 | 680.4 |  | 680.4
169 | Modify Partition and double Door added | 1 | No |  |  | 500 | 1 |  | 1 | 500 | 0 | 500
170 | Single Door | 1 | No |  |  | 250 | 1 |  | 1 | 250 |  | 250
| LEVEL 2 – Site Canteen Modifications | [6 empty] | 0 | 0 |  | 0 | 0
171 | Two side Gypsum board partition | 69 | M2 | 50 |  | 70 | 69 |  | 69 | 8280 |  | 8280
172 | Gypsum Board Ceiling | 21.4 | M2 | 65 |  | 35 | 21.4 |  | 21.4 | 2140 |  | 2140
173 | Canteen Counter + Door | 1 | No |  |  | 500 | 1 |  | 1 | 500 |  | 500
| GF KCE Office change Entrance | [6 empty] | 0 | 0 |  | 0 | 0
174 | Supply Installation of Two side Gypsum board partitions 3.2+1.2x2.5=11.0 m2 | 11 | M2 | 50 |  | 70 | 11 |  | 11 | 1320 |  | 1320
175 | Door | 1 | No |  |  | 250 | 1 |  | 1 | 250 | 0 | 250
[8 empty] | 0 | 0 |  | 0 | 0
| Basement 1 Canteen | [6 empty] | 0 | 0 |  | 0 | 0
176 | Supply and Installation of 2 Side Gypsum board partitions 14.32 LM x 3 M | 43.32 | M2 | 50 |  | 70 | 43.32 |  | 43.32 | 5198.4 |  | 5198.4
177 | Gypsum Board Ceiling 3.16x4.06=12.82m2 | 12.82 | M2 | 65 |  | 35 | 12.82 |  | 12.82 | 1282 |  | 1282
178 | Door | 1 | No |  |  | 250 | 1 |  | 1 | 250 | 0 | 250
179 | Counter | 1 | No |  |  | 500 | 1 |  | 1 | 500 |  | 500
Level 2 : KMEP Staff Pantry
180 | Partition -1; Size 2150 x 3250 mm | 6.9875 | M2 | 50 | 35 |  | 6.9875 |  | 6.9875 | 594.15 |  | 594.15
181 | Door | 1 | No |  |  | 250 | 1 |  | 1 | 250 |  | 250
| Level 2 : KMEP Staff Office | [7 empty] | 0 |  | 0 | 0
182 | Partition -1; Size 4500 x 2400 mm | 10.8 | M2 | 50 |  | 70 | 10.8 |  | 10.8 | 1296 |  | 1296
183 | Door | 1 | No |  |  | 250 | 1 |  | 1 | 250 |  | 250
[9 empty] | 0 |  | 0
184 | GF Lift Lobby Partition (ref:pics 01) 2.5M x 4.5M) | 11.25 | M2 | 50 |  | 70 | 11.25 |  | 11.25 | 1350 |  | 1350
185 | GF Lift Lobby Partition with paint (ref:pics 02) 410x5200mm H | 1 | LS |  |  | 500 | 1 |  | 1 | 500 |  | 500
AHK - CEILING BALANCE WORKS
B2 – Residential Lift Lobby
186 | supply and installation of balance ceiling areas including closing of all opening and final painting | 1 | Sum |  |  | 558 | 1 | 0 | 1 | 558 |  | 558
186a | Access Panel - 450 x 450 mm | 4 | Nos. |  |  | 145 | 4 | 0 | 4 | 580 | 0 | 580
186b | Access Panel - 300 x 300 mm | 1 | Nos. |  |  | 130 | 1 |  | 1 | 130 | 0 | 130
186c | Temperary Opening and Rectification - After AC Grill Fixing | 2 | Nos. |  |  | 120 |  | 2 | 1 | 0 | 240 | 240
B1 – Residential Lift Lobby
187 | supply and installation of balance ceiling areas including closing of all opening and final painting | 1 | Sum |  |  | 768 | 1 | 0 | 1 | 768 |  | 768
187a | Access Panel - 450 x 450 mm | 4 | Nos. |  |  | 145 | 4 | 0 | 4 | 580 | 0 | 580
187b | Access Panel - 300 x 300 mm | 1 | Nos. |  |  | 130 | 1 |  | 1 | 130 | 0 | 130
186c | Temperary Opening and Rectification - After AC Grill Fixing | 2 | Nos. |  |  | 120 |  | 2 | 1 | 0 | 240 | 240
| Ground Floor – residential entrance lobby, corridor and lift lobby | [10 empty] | 0
188 | supply and installation of balance ceiling areas including closing of all opening and final painting (90 %) | 1 | Sum |  |  | 5290 | 0.9 | 0 | 0.9 | 4761 | 0 | 4761
188a | Temperary Opening Clossing (100 % completed) | 16 | Nos. |  |  | 70 | 16 | 0 | 16 | 1120 | 0 | 1120
188b | Ceiling removed with Suspensions and Refixing | 2 | Nos. |  |  | 1000 | 2 | 0 | 2 | 2000 | 0 | 2000
188c | Access Panel - 600 x 600 mm | 6 | Nos. |  |  | 160 | 6 | 0 | 6 | 960 | 0 | 960
188d | Access Panel - 450 x 450 mm | 4 | Nos. |  |  | 145 | 4 | 0 | 4 | 580 | 0 | 580
188e | Access Panel - 300 x 300 mm | 2 | Nos. |  |  | 130 | 1 | 1 | 2 | 130 | 130 | 260 | No WIR
188f | Access Panel - 600 x 45 mm | 1 | Nos. |  |  | 170 | 1 | 0 | 1 | 170 | 0 | 170
188h | Ceiling Bulk Head Rectification with paint (75 % completed) E11/K104/PK/DM/523 | 31.8 | LM |  |  | 40 | 23.85 | 0 | 23.85 | 954 | 0 | 954
188 i | Ceiling - Small Room @ Reception - GF (right side) | 1.8 | M2 |  |  | 80 | 1.8 | 0 | 1.8 | 144 | 0 | 144
188j | Cladding with paint - Small Room @ Reception - GF (right side) | 5 | M2 |  |  | 135 | 5 | 0 | 5 | 675 | 0 | 675
188k | Cement Board Cladding - Small Room @ Reception - GF (right and Left side) Size 1.4x.84m 2nos | 2.35 | M2 |  |  | 160 | 2.35 | 0 | 2.35 | 376 | 0 | 376
188 L | Ceiling - Small Room @ Reception - GF (Left side) | 1.8 | M2 |  |  | 80 | 1.8 | 0 | 1.8 | 144 | 0 | 144
188m | Concrete Wall Rectification with Paint and Dome shape wall painting E11/K104/PK/DM/523 | 1 | Sum |  |  | 2500 | 1 | 0 | 1 | 2500 | 0 | 2500
188n | Gyproc Gypsum Wall Lining (Framing 400mm @ Center to center with Paint finish (Size 9.9 rm x 4.51 H =44.6m2 -1.92rm x2.06 h opening =3.95m2 total 44.6-3.95=40.65m2 E11/K104/PK/DM/523 R1 | 40.65 | M2 |  |  | 160 | 40.65 | 0 | 40.65 | 6504 | 0 | 6504
188o | L-Shape Gypsum Bulkhead with paint@ Lift lobby -Curtain Wall Area (Size 140x250mm) | 2.3 | LM |  |  | 160 | 2.3 | 0 | 2.3 | 368 | 0 | 368
188p | AdditionalTemperary Opening Clossing | 7 | Nos. |  |  | 70 |  | 7 | 7 | 0 | 490 | 490
188Q | Ceiling removed with Suspensions and Refixing (Reception Area) | 4 |  |  |  | 90 |  | 4 | 4 | 0 | 360 | 360
Level 2 – corridor and lift lobby.
189 | supply and installation of balance ceiling areas including closing of all opening and final painting (90%completed) | 1 | Sum |  |  | 3153 | 0.5 | 0.4 | 0.9 | 1576.5 | 1261.2 | 2837.7 | No WIR, some areas balance
189a | Z-Shape Gypsum Bulkhead with paint@ Lift lobby -Curtain Wall Area (Size 100x300x150mm 3.3LM) | 3.3 | LM |  |  | 190 | 3.3 | 0 | 3.3 | 627 | 0 | 627
189b | Access Panel - 600 x 600 mm | 4 |  |  |  | 160 | 1 | 3 | 4 | 160 | 480 | 640 | No WIR
189c | Access Panel - 300 x 30 mm | 1 |  |  |  | 130 | 1 | 0 | 1 | 130 | 0 | 130
189d | Temperary Opening Clossing (Previous Month) | 4 |  |  |  | 70 | 4 | 0 | 4 | 280 | 0 | 280
189e | Additional Temporary Opening Closing (Current Month) | 4 |  |  |  | 70 |  | 4 | 4 | 0 | 280 | 280
Level 4 – lift lobby, corridor, gymnasium/changing rooms.
190 | supply and installation of balance ceiling areas including closing of all opening and final painting (100%completed) | 1 | Sum |  |  | 16696 | 1 | 0 | 1 | 16696 | 0 | 16696
190a | Temperary Opening Clossing | 55 | Nos. |  |  | 70 | 55 |  | 55 | 3850 | 0 | 3850
190b | Access Panel - 300 x 30 mm | 7 |  |  |  | 130 | 7 | 0 | 7 | 910 | 0 | 910
190c | Access Panel - 450 x 450 mm | 2 |  |  |  | 145 | 2 | 0 | 2 | 290 | 0 | 290
190d | Access Panel - 600 x 600 mm | 8 |  |  |  | 160 | 8 | 0 | 8 | 1280 | 0 | 1280
190e | Access Panel - 1200 x 600 mm | 1 |  |  |  | 240 | 1 | 0 | 1 | 240 | 0 | 240
190f | Temperary Opening Clossing (100 % completed) Ref:E11 | 7 | Nos. |  |  | 70 | 7 | 0 | 7 | 490 | 0 | 490
190g | Cove Light @ Gym Area - 4F | 68.6 | LM |  |  | 90 | 68.6 | 0 | 68.6 | 6174 | 0 | 6174
190h | New Temperary Opening Clossing (After Paint Finished) | 24 | Nos. |  |  | 70 | 23 | 1 | 24 | 1610 | 70 | 1680
190i | Wall Rectification and Paint (Above Curtain Wall and Abouve Marble Cladding Area + Columns) | 121.45 | LM |  |  | 16 |  | 121.45 | 121.45 | 0 | 1943.2 | 1943.2 | No WIR
Level 23 – lift lobby, corridor, members lounge/toilets.
191 | supply and installation of balance ceiling areas including closing of all opening and final painting | 1 | Sum |  |  | 17588 | 0.9 | 0.1 | 1 | 15829.2 | 1758.8 | 17588 | No WIR only 90%
191a | Ceiling Gypsum Board with suspensions was removed and the waste materials were transferred to the kce bin. New Suspension added after MEP clearance | 92 | Sum |  |  | 90 | 92 | 0 | 92 | 8280 | 0 | 8280
191b | Wash basin in toilets:-Cement board cladding (round) and top | 1 | Sum |  |  | 1200 | 1 | 0 | 1 | 1200 | 0 | 1200
192 | Access Panel - 600 x 600 mm | 8 | Nos. |  |  | 160 | 3 | 5 | 8 | 480 | 800 | 1280 | No WIR
193 | Access Panel - 450 x 450 mm | 15 | Nos. |  |  | 145 | 1 | 14 | 15 | 145 | 2030 | 2175 | No WIR
194 | Access Panel - 300 x 300 mm | 5 | Nos. |  |  | 130 | 2 | 3 | 5 | 260 | 390 | 650 | No WIR
195 | Access Panel - 500 x 500 mm |  | Nos. |  |  | 150
196 | Access Panel - 1200 x 600 mm |  | Nos. |  |  | 240
196a | cove light @ Corridor | 44.3 | LM |  |  | 120 | 44.3 | 0 | 44.3 | 5316 | 0 | 5316
196b | Ledge Wall | 4 | Nos. |  |  | 500 | 4 |  | 4 | 2000 | 0 | 2000
196c | cove light @ Wash room 100% completed | 19 | LM |  |  | 120 | 9.5 | 9.5 | 19 | 1140 | 1140 | 2280 | No WIR
196d | cove light @ Passage between Meeting and Multi Function | 14 | LM |  |  | 120 | 14 | 0 | 14 | 1680 | 0 | 1680
196e | MR Ceiling @ Pantry | 19.5 | M2 |  |  | 90 | 19.5 | 0 | 19.5 | 1755 | 0 | 1755
196f | Temperary Opening Clossing | 17 | Nos. |  |  | 70 | 17 |  | 17 | 1190 | 0 | 1190
[9 empty] | 0 | 0 | 0 | 0
196g | Gyproc Gypsum Wall Lining | 153.69 | M2 |  |  | 140 | 153.69 | 0 | 153.69 | 21516.6 | 0 | 21516.6
196h | Ceiling and Suspensions remove, some area Ceiling Dropped 100mm and Reinstalled (MR & RG) | 61 | M2 |  |  | 90 | 61 | 0 | 61 | 5490 | 0 | 5490
196i | New Temperary Opening Clossing | 6 | Nos. |  |  | 70 | 6 | 0 | 6 | 420 | 0 | 420
196j | March Month Temperary Opening Clossing | 48 | Nos. |  |  | 70 | 0 | 48 | 48 | 0 | 3360 | 3360
196k | L-shape Bulk head added (ceiling height change) | 7.3 | LM |  |  | 120 | 0 | 7.3 | 7.3 | 0 | 876 | 876
196l | Ceiling removed and refixed for MEP | 6.44 | M2 |  |  | 90 | 0 | 6.44 | 6.44 | 0 | 579.6 | 579.6
Corridor Wash Area
196m | Ceiling MR (2060x2440mm) | 5.0264 | M2 |  |  | 90 | 0 | 5.03 | 5.03 | 0 | 452.7 | 452.7 | No WIR
196n | cove light | 2.06 | LM |  |  | 120 | 0 | 2.06 | 2.06 | 0 | 247.2 | 247.2 | No WIR
196o | Ledge Wall | 1 | Nos. |  |  | 500 | 0 | 1 | 1 | 0 | 500 | 500 | No WIR
Basement 1
197 | Gypsum board partitions Size = 2300x2700 | 6.21 | M2 | 50 | 35 |  |  |  | 6.21 | 527.85 |  | 527.85
198 | Paint Size = 2300x2700 | 6.21 | M2 |  |  | 15 | 6.21 |  | 6.21 | 93.15 |  | 93.15
199 | Gypsum board partitions Size = 1500x2700 | 4.05 | M2 | 50 | 35 |  | 6.21 |  | 4.05 | 344.25 |  | 344.25
200 | Paint Size = 1500x2700 | 4.05 | M2 |  |  | 15 | 4.05 |  | 4.05 | 60.75 |  | 60.75
4.05
TOILETS FOR LABOURS @ BASEMENT-1
201 | Supply and Installation of Gypsum board partitions TYPE-W1 (as per Dwgs) Inside (MR) Moisture Resistant Board & Outside RG Board - Framing (70mm Stud) Center to Center 400mm (Two side) | 49.4 | M2 |  |  | 135 |  | 0 | 49.4 | 6669 | 0 | 6669
202 | Supply and Installation of Gypsum board partitions TYPE-W2 (as per Dwgs) Inside (MR) Moisture Resistant Board & Outside RG Board - Framing (70mm Stud) Center to Center 600mm (Two side) | 85.35 | M2 |  |  | 125 | 49.4 | 0 | 85.35 | 10668.75 | 0 | 10668.75
203 | Supply and Installation of Gypsum board partitions TYPE-W3 (as per Dwgs) Both side(MR) Moisture Resistant Board (70mm Stud) Center to Center 600mm | 94.4 | M2 |  |  | 130 | 85.35 | 0 | 94.4 | 12272 | 0 | 12272
204 | Supply and Installation of Gypsum board partitions TYPE-W4 (as per Dwgs) Both side(MR) Moisture Resistant Board Size:W75xL400xH1200mm (PARTITION BETWEEN URINALS) | 21 | Nos |  |  | 120 | 94.4 | 0 | 21 | 2520 | 0 | 2520
205 | Supply and Installation of Ceiling (Gypsum Tile) | 79.12 | M2 |  |  | 70 | 21 | 0 | 79.12 | 5538.4 | 0 | 5538.4
206 | Doors (Single) | 16 | Nos |  |  | 250 | 79.12 | 0 | 16 | 4000 | 0 | 4000
207 | Paint (paint Inside All Area & Outside Front side only balance area primer Only (2 side and back side) | 400.36 | M2 |  |  | 15 | 16 | 0 | 400.36 | 6005.4 | 0 | 6005.4
400.36
GROUND FLOOR LIFT LOBBY
208 | Gypsum board partitions Size = 3700x4500 | 16.65 | M2 | 50 | 35 |  |  | 0 | 16.65 | 1415.25 | 0 | 1415.25
208 | Paint Partition = 3700x4500 | 16.65 | M2 |  |  | 15 | 16.65 | 0 | 16.65 | 249.75 | 0 | 249.75
16.65
4th FLOOR HOTEL AREA
209 | Partitions REF : (E11/K104/PK/AK/556) | 20.5 | M2 | 50 | 35 |  |  | 0 | 20.5 | 1742.5 | 0 | 1742.5
210 | Partitions REF : (E11/K104/PK/AK/556) PAINT | 20.5 | M2 |  |  | 15 | 20.5 | 0 | 20.5 | 307.5 | 0 | 307.5
20.5
NEW TOILETS AND REST AREA FOR LABOUR @ BASEMENT-1 (REF:E11)
211 | Supply and Installation of Gypsum board partitions TYPE-W1 Inside (MR) Moisture Resistant Board & Outside RG Board - Framing (70mm Stud) Center to Center 400mm | 51.35 | M2 | 60 | 75 |  | 51.35 | 0 | 51.35 | 6932.25 | 0 | 6932.25
212 | Supply and Installation of Gypsum board partitions TYPE-W2 Inside (MR) Moisture Resistant Board & Outside RG Board - Framing (70mm Stud) Center to Center 600mm | 89.7 | M2 | 50 | 75 |  | 89.7 | 0 | 89.7 | 11212.5 | 0 | 11212.5
213 | Supply and Installation of Gypsum board partitions TYPE-W3 Both side(MR) Moisture Resistant Board (70mm Stud) Center to Center 600mm | 152 | M2 | 50 | 80 |  | 152 | 0 | 152 | 19760 | 0 | 19760
214 | Supply and Installation of Gypsum board partitions / Ply Wood Divider TYPE-W4 Size:L400xH1200mm (PARTITION BETWEEN URINALS) | 21 | Nos |  |  | 100 | 21 | 0 | 21 | 2100 | 0 | 2100
215 | Supply and Installation of Ceiling (Gypsum Tile) | 126 | M2 |  |  | 70 | 126 | 0 | 126 | 8820 | 0 | 8820
216 | Doors (Single) | 20 | Nos |  |  | 250 | 20 | 0 | 20 | 5000 | 0 | 5000
217 | Paint (paint Inside All Area & Outside Front side only balance area primer Only (2 side and back side) | 491 | M2 |  |  | 15 | 491 | 0 | 491 | 7365 | 0 | 7365
| New Rest Area | [7 empty] | 0 | 0 | 0 | 0
218 | Supply and Installation of Gypsum board partitions TYPE-W5 RG Board with 70mm Stud Framing | 100.56 |  | 50 | 70 |  | 100.56 | 0 | 100.56 | 12067.2 | 0 | 12067.2
219 | Supply and Installation of Ceiling (Gypsum Tile) | 155 | M2 |  |  | 70 | 155 | 0 | 155 | 10850 | 0 | 10850
220 | Doors (Single) | 1 | Nos |  |  | 250 | 1 | 0 | 1 | 250 | 0 | 250
221 | Paint (Outside Front side only and balance area primer only) | 65 | M2 |  |  | 15 | 65 | 0 | 65 | 975 | 0 | 975
[9 empty] | 0 | 0 | 0 | 0
222 | Temp. Gypsum board partition @ L2 Hotel Lift Lobby (Size 2000x3040mm) | 6.08 | M2 | 50 | 35 |  | 6.08 | 0 | 6.08 | 516.8 | 0 | 516.8
223 | Temp. Gypsum board partition @ FF Client Office Area (Size 2.97x2.5 + 3.75x2.5) | 16.77 | M2 | 50 | 35 |  | 16.77 | 0 | 16.77 | 1425.45 | 0 | 1425.45
224 | Temp. Gypsum board partition @ GF KCE office area (Size 3.2x2.5m) 2 side board | 8 | M2 | 50 | 70 |  | 8 | 0 | 8 | 960 | 0 | 960
225 | Temp. Gypsum board partition With Insulation@ B1 Hotel Area(Size 7.0x4.5m) 2 side board | 31.5 | M2 | 50 | 90 |  | 0 | 31.5 | 31.5 | 0 | 4410 | 4410
226 | Permanent MR Gypsum board partition With @ B1 Hotel Area (Gyproc System) | 10.66 | M2 | 60 | 85 |  | 0 | 10.66 | 10.66 | 0 | 1545.7 | 1545.7
0
[8 empty] | 0 | 0 |  | 0 | 0
| Total | [8 empty] | 514606.484 | 23584.4 | 538190.884
| Total Progress Amount | [10 empty] | 538190.884