## Summary
No | Description | BOQ | Workdone % | Cumulative Amount | Remark
Original Scope
A | Installation of Steel Beam | 77965 | 95% | 74066.75 | WIR VE-SX-WR-PW-00003 not approved
| Demolition | 33000 | 95% | 31350 | WIR VE-SX-WR-PW-00004 not approved
Variation
B | Design Calcuation | 10000 | 90% | 9000 | Only 90% until variation approval
| Slab Trimming | 89000 | 90% | 80100 | Only 90% until variation approval
| Fire Proofing | 34500 | 90% | 31050 | Only 90% until variation approval, WIR VE-SX-WR-PW-00005 not approved
225566.75
| Previous Certified |  |  | 225566.75
| Advance Payment |  |  | 204175.4
| Advance Payment Recovery |  |  | -33290
| This Month |  |  | 170885.4
396452.15
|  | KCE Claim | 244465 | 170885.4 | 415350.4
|  | Difference | -18898.25 | 0 | -18898.25