## Sheet1
No | Description | BOQ | Workdone % | Cumulative Amount | Remark
Original Scope
A | Installation of Steel Beam | 77965 | 95% | 74066.75 | Please submit the TOC if 100% completed
| Demolition | 33000 | 95% | 31350 | Please submit the TOC if 100% completed
Variation
B | Design Calcuation | 10000 | 90% | 9000 | Only 90% until variation approval
| Slab Trimming | 89000 | 90% | 80100 | Only 90% until variation approval
| Fire Proofing | 34500 | 90% | 31050 | Only 90% until variation approval
225566.75
| Previous Certified |  |  | 77965
| Advance Payment |  |  | 33290
| Advance Payment Recovery |  |  | -33290
| This Month |  |  | 147601.75