## Summary WM PA No. 9
Project | : DORCHESTER HOTEL AND RESIDENCES (PLOT 18) | [5 empty] | WM PA No. 9
Contract Ref. No. | : LOI-201A22002/SW/ARM/151 | [5 empty] | February, 2023
SN | Description | BOQ Amount | Valuation for WFA | New Subcontract | Last Month - KCE PC 12 (Jan, 2023) | This month | Cummalative - WM PA No. 9
1 | Swimming Pool | 2642215.855 | 872479.6904 | 1769736.1646 | 1382350.1329 | 48870.5411 | 1431220.6739
2 | Water Feature | 569944.865 | 167529.1874 | 402415.6776 | 256498.5715 | 16569.9378 | 273068.5093
3 | ACRYLIC WALLS | 541119.28 | 0 | 541119.28 | 541119.2754 | 0 | 541119.2754
4 | DESIGN FEES | 60000 | 60000 | 0 | 0 | 0 | 0
5 | VO (P22-073-C-VO-4) |  |  | 138654.3
6 | VO (P22-073-C-VO-5) |  |  | 209211.36
| Sub Total -1 | 3813280 | 1100008.8779 | 3061136.7821 | 2179967.9797 | 65440.4789 | 2245408.4587 | Work Done
7 | MOS Value (SWP + WTF) at 75% |  |  |  | 126848.4843 | 0 | 126848.4843 | MOS
8 | MOS Value (P22-073-C-VO-4) at 75% |  |  |  | 64943.2394 | 0 | 64943.2394
9 | MOS Value (P22-073-C-VO-5) at 75% |  |  |  | 0 | 0 | 0
| Sub Total -2 |  | 0 | 0 | 191791.7237 | 0 | 191791.7237
10 | Materials on Site dated 28-Feb-22 |  | 584620 | -584620 | -584620 | 0 | -584620 | Material at site
| Sub Total -3 |  | 584620 | -584620 | -584620 | 0 | -584620 | -392828.2763
| Gross Total | 3813280 | 1684628.8779 | 2476516.7821 | 1787139.7035 | 65440.4789 | 1852580.1824
[5 empty] | 72.16% | 2.642% | 74.81%

## SUMM
PLOT-18 |  |  |  | WM Ref. No.: D20/054-12/C
BILL :- SWIMMING POOLS & WATER FEATURES |  |  |  | Date: 06-05-2021
SUMMARY
[10 empty] | WM-Khansaheb BOQ |  | WM-Khansaheb Progress Claim - February 2023 | [5 empty] | OMNIYAT RECOMMENDATION - as per 17001DH/SCA/40-01-33-WM Ver 2 dated 11 April 2022
SR.NO | DESCRIPTION | FROM | Unit Rate | Amount | Amount after Discount | Last Month |  | This Month |  | TOTAL |  | Last Month - KCE PC 12 (Jan, 2023) |  | This Month |  | Total To Date |  | Last Month |  | This Month |  | Total To Date
|  | PAGE | (Dhs.) | (Dhs.) | (Dhs.) | % | Value | % | Value | % | Value | % | Value | % | Value | % | Value | % | Value | % | Value | % | Value
SUMMARY
1 | SWIMMING POOLS | 1/24 |  | 3248965 | 2642215.8567 |  |  |  |  | 66.98% | 1769736.1662 | 43.72% | 1155235.449 | 10.45% | 275985.225 | 54.17% | 1431220.6739 | 33.02% | 872479.6904 | 0% | 0 | 33.02% | 872479.6904
2 | WATER FEATURES | 2/8 |  | 700825 | 569944.8679 |  |  |  |  | 70.61% | 402415.6805 | 40.65% | 231696.5258 | 7.259% | 41371.9834 | 47.91% | 273068.5093 | 29.39% | 167529.1874 | 0% | 0 | 29.39% | 167529.1874
3 | ACRYLIC WALLS FOR LEVEL 10 & 26 SWIMMING POOLS | 3/2 |  | 665380 | 541119.2754 |  |  |  |  | 100% | 541119.2754 | 100% | 541119.2754 | 0% | 0 | 100% | 541119.2754 | 0% | 0 | 0% | 0 | 0% | 0
4 | STAINLESS STEEL TANK FOR PENTHOUSE POOLS (LEVEL 24, 25, 27 AND 29 RESIDENTIAL) |  |  | FOC | FOC
5 | CONTROL SYSTEM FOR HEAT EXCHANGERS FOR PENTHOUSE POOLS |  |  | FOC | FOC
6 | BIM MODEL |  | 100000 | Rate Only | Rate Only
| DESIGN FEES |  | 60000 | 60000 | 60000 | [12 empty] | 100% | 60000 | 0% | 0 | 100% | 60000
Notes:
1. Pipe Insulations: Thermal insulation is included in the pool specialist package for the heat/cool pump lines. Thermal insulation for the primary heat exchanger lines are by Main MEP Contractor - scope of the work for Pool Contractor will be at the heat exchanger only. Acoustic insulation will be part of Pool Contractor package only for gravity lines and above critical areas.
2. Vertical movement/lifting of all equipment is excluded from this offer.
3. Base offer for Fiber Optic Lighting for Level 29 Roof Pools are considered without end fittings and with IP20 projectors with metallic enclosure. Optional additional price was provided for fiber optic lighting system with end fittings (projectors are still with IP20 protection rating)
| TOTAL AMOUNT TO MAIN SUMMARY (EXCLUDING VAT) |  |  | 4675170
| TOTAL AMOUNT AFTER SPECIAL DISCOUNT (EXCLUDING V.A.T.) |  |  | 3753280 | 3813280 | 0% | 0 | 0% | 0 | 71.15% | 2713271.1221 | 50.56% | 1928051.2502 | 8.322% | 317357.2084 | 58.88% | 2245408.4587 | 28.85% | 1100008.8779 | 0% | 0 | 28.85% | 1100008.8779
Discount Rate
80.28%
|  |  |  | 921890 |  | FOR CHECKING PURPOSES ONLY | [17 empty] | 921890 | 19.72%

## SWP
PLOT-18 | [5 empty] | WM Ref. No.: D20/054-12/C
BILL OF QUANTITIES | [5 empty] | Date: 06-05-2021 | [32 empty] | Discount Rate
BILL :- SWIMMING POOLS | [38 empty] | 81.32%
[8 empty] | A | [8 empty] | C=A-B | [17 empty] | B
[15 empty] | WM-Khansaheb BOQ |  |  | WM-Khansaheb Progress Claim - February 2023 | [8 empty] | OMNIYAT RECOMMENDATION - as per 17001DH/SCA/40-01-33-WM Ver 2 dated 11 April 2022 | [8 empty] | ITEM CODE | WIR |  | 18.68%
Item | Description | Make | Qty. | Unit | Rate | Amount | Rate | Amount after Discount | Last Month |  |  | This Month |  |  | TOTAL |  |  | Last Month - KCE PC 12 (Jan, 2023) |  |  | This Month |  |  | Total To Date |  |  | Last Month |  |  | This Month |  |  | Total To Date
[6 empty] | (Dhs.) | after Discount | (Dhs.) | % | Qty | Value | % | Qty | Value | % | Qty | Value | % | Qty | Value | % | Qty | Value | % | Qty | Value | % | Qty | Value | % | Qty | Value | % | Qty | Value
SWIMMING POOLS
LEVEL 04 RESIDENTIAL
Filtration System
A | Laminated Bobbin wound sand filter, simultaneous projection of resin and fibre glass, 41.5 m3/h, Ø1050mm Ø1200mm, complete with stand media and manual multiport valve, 1 duty + 1 standby | Aqua, Italy | 2 | Nos | 9600 | 19200 | 7807.1854 | 15614.3709 | [7 empty] | 2 | 15614.3709 | 95% | 1.9 | 14833.65 | 0% | 0 | 0.0023248 | 95% | 1.9 | 14833.6523 |  |  |  |  | 0 | 0 |  |  |  | MU-1200N-VS | WME-SW-WR-L3-00032_01 | 0.95
0
B | Plastic centrifugal pump, 41.5 m3/h @ 14m head, 4.5HP, 1 duty + 1 standby | Aqua, Italy | 2 | Nos | 4930 | 9860 | 4009.315 | 8018.63 | [7 empty] | 2 | 8018.63 | 95% | 1.9 | 7617.7 | 0% | 0 | -0.0014624 | 95% | 1.9 | 7617.6985 |  |  |  |  | 0 | 0 |  |  |  | KPA-450 | WME-SW-WR-L3-00032_01 | 0.95
0
| Water Treatment System | [15 empty] | 0
0
C | Automatic pH/RX dosing controller |  | 1 | Nos |  | 0 | 0 | 0 | [8 empty] | 0
0
D | Manual analog dosing pumps - pH (20L/h-5 bar) |  | 1 | Nos |  | 0 | 0 | 0 | [8 empty] | 0
0
E | Manual analog dosing pumps - RX (20L/h-5 bar) |  | 1 | Nos |  | 0 | 0 | 0 | [8 empty] | 0
0
| Pre-assembled panel - Twin Dosing System - 10L/h @ 4 bars (pH & Rx) | Aqua, Italy | 2 | Nos | 6030 | 12060 | 4903.8884 | 9807.7767 | [7 empty] | 2 | 9807.7767 | 95% | 1.9 | 9317.39 | 0% | 0 | -0.0021335 | 95% | 1.9 | 9317.3879 |  |  |  | 0% | 0 | 0 |  |  |  | ADPS101 | WME-SW-WR-L3-00032_01 | 0.95
0
F | Polyethylene dosing tanks, 250L 200L | Aqua, Italy | 4 | Nos | 1030 | 4120 | 837.6459 | 3350.5837 | [7 empty] | 4 | 3350.5837 | 95% | 3.8 | 3183.05 | 0% | 0 | 0.0045614 | 95% | 3.8 | 3183.0546 |  |  |  | 0% | 0 | 0 |  |  |  | ADTANK010 | WME-SW-WR-L3-00032_01 | 0.95
0
G | Manual stirrers | Aqua, Italy | 4 | Nos | 420 | 1680 | 341.5644 | 1366.2575 | [7 empty] | 4 | 1366.2575 | 95% | 3.8 | 1297.94 | 0% | 0 | 0.0045784 | 95% | 3.8 | 1297.9446 |  |  |  | 0% | 0 | 0 |  |  |  | ADAGMP06 | WME-SW-WR-L3-00032_01 | 0.95
0
H | UV Sterilizer, Flow: 65 m³/h at 3 bar pressure | AtecPool, Spain | 1 | Nos | 38890 | 38890 | 31627.2335 | 31627.2335 | [7 empty] | 1 | 31627.2335 | 95% | 0.95 | 30045.87 | 0% | 0 | 0.0018184 | 95% | 0.95 | 30045.8718 |  |  |  |  | 0 | 0 |  |  |  | UV-5205 | WME-SW-WR-L3-00032_01 | 0.95
0
| Fittings | [15 empty] | 0
0
J | Stainless steel main drain, 200x200mm | Aqua, Italy | 2 | Nos | 800 | 1600 | 650.5988 | 1301.1976 | [7 empty] | 2 | 1301.1976 | 95% | 1.9 | 1236.14 | 0% | 0 | -0.0023063 | 95% | 1.9 | 1236.1377 |  |  |  |  | 0 | 0 |  |  |  | F-155 | WME-SW-WR-L4-00066_00_B | 0.95
0
K | Stainless steel floor inlet | Aqua, Italy | 22 | Nos | 710 | 15620 | 577.4064 | 12702.9413 | [7 empty] | 22 | 12702.9413 | 95% | 20.9 | 12067.79 | 0% | 0 | 0.0042351 | 95% | 20.9 | 12067.7942 |  |  |  |  | 0 | 0 |  |  |  | F-230 | WME-SW-WR-L4-00066_00_B | 0.95
0
K | Stainless steel wall inlet | Aqua, Italy | 20 | Nos | 280 | 5600 | 227.7096 | 4554.1915 | [7 empty] | 20 | 4554.1915 | 95% | 19 | 4326.48 | 0% | 0 | 0.0019281 | 95% | 19 | 4326.4819 |  |  |  | 0% | 0 | 0 |  |  |  | F-219/A | WME-SW-WR-L4-00066_00_B | 0.95
0
L | Stainless steel vacuum point | Aqua, Italy | 4 | Nos | 300 | 1200 | 243.9745 | 975.8982 | [7 empty] | 4 | 975.8982 | 95% | 3.8 | 927.1 | 0% | 0 | 0.0032703 | 95% | 3.8 | 927.1033 |  |  |  | 0% | 0 | 0 |  |  |  | F-240/A | WME-SW-WR-L4-00066_00_B | 0.95
0
M | Stainless steel overflow fittings | AtecPool, Spain | 42 | Nos | 440 | 18480 | 357.8293 | 15028.832 | [7 empty] | 42 | 15028.832 | 95% | 39.9 | 14277.39 | 0% | 0 | 0.00036265 | 95% | 39.9 | 14277.3904 |  |  |  |  | 0 | 0 |  |  |  | 03100282-1 | WME-SW-WR-L4-00066_00_B | 0.95
0
M | Provision for overflow drain without fittings - Ø160mm |  | 8 | Nos | 880 | 7040 | 715.6587 | 5725.2693 | [7 empty] | 8 | 5725.2693 | 95% | 7.6 | 5439.01 | 0% | 0 | -0.0041476 | 95% | 7.6 | 5439.0059 |  |  |  |  | 0 | 0 |  |  |  | - | WME-SW-WR-L3-00032_01 | 0.95
0
| Overflow Effect System | [15 empty] | 0
0
N | Overflow effect cast iron pump with cast iron impeller plastic pump, 70.1 m3/h @ 15m head, 7.5HP, 1 duty | Aqua, Italy | 1 | Nos | 7350 | 7350 | 5977.3763 | 5977.3763 | [7 empty] | 1 | 5977.3763 | 95% | 0.95 | 5678.51 | 0% | 0 | -0.0024694 | 95% | 0.95 | 5678.5075 |  |  |  |  | 0 | 0 |  |  |  | KPA 750 | WME-SW-WR-L3-00032_01 | 0.95
| To Collection Dhs. |  |  |  |  | 142700 |  | 116050.5585 |  |  | 0 |  |  | 0 |  |  | 116050.5585 |  |  | 110248.02 |  |  | 0.01056 |  |  | 110248.0306 |  |  | 0 |  |  | 0 |  |  | 0
SWIMMING POOLS (CONT'D)
LEVEL 04 RESIDENTIAL (CONT'D)
Maintenance Kit
A | Vacuum head | Aqua, Italy | 1 | Nos | 830 | 830 | 674.9962 | 674.9962 | [8 empty] | 674.9962 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  |  | 0 | 0
B | Telescopic handle |  | 1 | Nos
C | Vacuum hose |  | 1 | Nos
D | Pool brush |  | 1 | Nos
E | Leaf skimmer |  | 1 | Nos
F | Leaf rake |  | 1 | Nos
G | Algae brush |  | 1 | Nos
H | Hose fitting |  | 1 | Nos
J | Test kit |  | 1 | Nos
0
| Control Panel Board | [15 empty] | 0
0
K | Control Panel Board | Al Fanar/ Scheinder | 1 | Nos | 31500 | 31500 | 25617.3272 | 25617.3272 | [7 empty] | 1 | 25617.3272 | 95% | 0.95 | 24336.4608 | 0% | 0 | 0 | 95% | 0.95 | 24336.4608 |  |  |  |  | 0 | 0 |  |  | 0 |  | WME-SW-WR-L4-00063_00 | 0.95
0
L | MEP Works including piping, cabling, containment, etc. | Cosmoplast/Atlas/Cepex/Ducab | 1 | Nos | 100000 | 100000 | 81324.8483 | 81324.8483 | [7 empty] | 0.1 | 8132.4848 | 50% | 0.05 | 4066.2424 | 0% | 0 | 0 | 50% | 0.05 | 4066.2424 | 90% | 0.9 | 73192.3634 | 0% | 0 | 0 | 90% | 0.9 | 73192.3634 |  | WME-SW-WR-ML-00004 WME-SW-WR-L4-00016 WME-SW-WR-L4-00019 WME-SW-WR-L4-00018 WME-SW-WR-L4-00040_00_B WME-SW-WR-L4-00063_00 WME-SW-WR-L4-00064_00 WME-SW-WR-L4-00074_00 WME-SW-WR-L4-00078_00 | 0.5
0
M | Testing and Commissioning |  | 1 | Item |  | Included | [10 empty] | 0
| To Collection Dhs. |  |  |  |  | 132330 |  | 107617.1717 |  |  | 0 |  |  | 0 |  |  | 34424.8083 |  |  | 28402.7033 |  |  | 0 |  |  | 28402.7033 |  |  | 73192.3634 |  |  | 0 |  |  | 73192.3634
SWIMMING POOLS (CONT'D)
LEVEL 04 RESIDENTIAL (CONT'D)
Underwater lights
A | X-W11 (as per VE comparison table & data sheet) | Luce & Light | 8 | Nos | 4010 | 32080 | 3261.1264 | 26089.0113 | [7 empty] | 8 | 26089.0113 | 95% | 7.6 | 24784.5608 | 0% | 0 | 0 | 95% | 7.6 | 24784.5608 |  |  |  |  | 0 | 0 |  |  |  | X-W11 | WME-SW-WR-L4-00046 WME-SW-WR-L4-00067_00_B | 0.95
0
B | X-W12 (as per VE comparison table & data sheet) | Luce & Light | 6 | Nos | 3990 | 23940 | 3244.8614 | 19469.1687 | [7 empty] | 6 | 19469.1687 | 95% | 5.7 | 18495.7102 | 0% | 0 | 0 | 95% | 5.7 | 18495.7102 |  |  |  |  | 0 | 0 |  |  |  | X-W17 (CW300009MI + WC5006) | WME-SW-WR-L4-00046 WME-SW-WR-L4-00067_00_B | 0.95
0
C | X-L12 (as per VE comparison table & data sheet) | Global Lights | 15 | m | 815 | 12225 | 662.7975 | 9941.9627 | [7 empty] | 15 | 9941.9627 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 |  |  |  |  | 0 | 0
0
| Heating/Cooling System | [15 empty] | 0
0
D | Air-to-water Heat/Cool Pump Heating Capacity: 160 kW Cooling Capacity: 120 kW | Astral, Spain | 2 | Nos | 87690 | 175380 | 71313.7594 | 142627.5189 | [7 empty] | 2 | 142627.5189 | 95% | 1.9 | 135496.143 | 0% | 0 | 0 | 95% | 1.9 | 135496.143 |  |  |  | 0% | 0 | 0 |  |  |  | AHP400-SU R4 | WME-SW-WR-L3-00032_01 | 0.95
0
| Plastic booster pump, 40 m3/h @ 20m head, 7.5HP, 2 duty | Aqua, Italy | 2 | Nos | 7350 | 14700 | 5977.3763 | 11954.7527 | [7 empty] | 2 | 11954.7527 | 95% | 1.9 | 11357.0151 | 0% | 0 | 0 | 95% | 1.9 | 11357.0151 |  |  |  |  | 0 | 0 |  |  |  | KPA 750 | WME-SW-WR-L3-00032_01 | 0.95
0
0
| Water Tanks | [15 empty] | 0
0
| GRP Panel Balancing Tank, 18 m3 (4.0x3.0x1.5m) Non-insulated | Al Bassam - AquaSystem | 1 | Nos | 37980 | 37980 | 30887.1774 | 30887.1774 | [7 empty] | 1 | 30887.1774 | 95% | 0.95 | 29342.8185 | 0% | 0 | 0 | 95% | 0.95 | 29342.8185 |  |  |  | 0% | 0 | 0 |  |  |  | - | WME-SW-WR-L3-00032_01 | 0.95
0
| GRP Panel Backwash Tank, 1.5 m3 (1.0x1.0x1.5m) Non-insulated | Al Bassam - AquaSystem | 1 | Nos | 9800 | 9800 | 7969.8351 | 7969.8351 | [7 empty] | 1 | 7969.8351 | 95% | 0.95 | 7571.3434 | 0% | 0 | 0 | 95% | 0.95 | 7571.3434 |  |  |  | 0% | 0 | 0 |  |  |  | - | WME-SW-WR-L3-00032_01 | 0.95
0
0
| Pool Surround | [15 empty] | 0
0
| Pool ladder, 4 steps | Aqua, Italy | 2 | Nos | 1590 | 3180 | 1293.0651 | 2586.1302 | [7 empty] | 2 | 2586.1302 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 |  |  |  | 0% | 0 | 0 |  |  |  | L-106-316
| To Collection Dhs. |  |  |  |  | 309285 |  | 251525.557 |  |  | 0 |  |  | 0 |  |  | 251525.557 |  |  | 227047.5909 |  |  | 0 |  |  | 227047.5909 |  |  | 0 |  |  | 0 |  |  | 0
SWIMMING POOLS (CONT'D)
LEVEL 10 PENTHOUSE POOL
Filtration System
B | Laminated fiberglass Bobbin wound sand filter, 13.15 m3/h, Ø650mm, complete with sand media and manual multiport valve, 1 duty | Aqua, Italy | 1 | Nos | 1680 | 1680 | 1366.2575 | 1366.2575 | [7 empty] | 1 | 1366.2575 |  |  |  | 90% | 0.9 | 1229.6317 | 90% | 0.9 | 1229.6317 |  |  |  | 0% | 0 | 0 |  |  |  | MU-650N-VS
0
C | Plastic self-priming pump, 13.15 m3/h @ 15m head, 1.5HP, 1 duty + 1 standby | Aqua, Italy | 2 | Nos | 1810 | 3620 | 1471.9798 | 2943.9595 | [7 empty] | 2 | 2943.9595 |  |  |  | 45% | 0.9 | 1324.7818 | 45% | 0.9 | 1324.7818 |  |  |  | 0% | 0 | 0 |  |  |  | Euroswim 150M/A
0
| Water Treatment System | [15 empty] | 0
0
D | Automatic pH/RX dosing controller |  | 1 | Nos |  | 0 | 0 | 0 | [8 empty] | 0
0
E | Manual analog dosing pumps - pH (10L/h - 5 bar) |  | 1 | Nos |  | 0 | 0 | 0 | [8 empty] | 0
0
F | Manual analog dosing pumps - RX (10L/h - 5 bar) |  | 1 | Nos |  | 0 | 0 | 0 | [8 empty] | 0
0
| Pre-assembled panel - Twin Dosing System - 10L/h @ 4 bars (pH & Rx) | Aqua, Italy | 1 | Nos | 6030 | 6030 | 4903.8884 | 4903.8884 | [7 empty] | 1 | 4903.8884 |  |  |  | 95% | 0.95 | 4658.6939 | 95% | 0.95 | 4658.6939 |  |  |  | 0% | 0 | 0 |  |  |  | ADPS101
0
G | Polyethylene dosing tanks, 125L 100L | Aqua, Italy | 2 | Nos | 530 | 1060 | 431.0217 | 862.0434 | [7 empty] | 2 | 862.0434 |  |  |  | 95% | 1.9 | 818.9412 | 95% | 1.9 | 818.9412 |  |  |  | 0% | 0 | 0 |  |  |  | ADTANK010 |  | 0.6
0
H | Manual stirrers | Aqua, Italy | 2 | Nos | 410 | 820 | 333.4319 | 666.8638 | [7 empty] | 2 | 666.8638 | 95% | 1.9 | 633.5206 | 0% | 0 | 0 | 95% | 1.9 | 633.5206 |  |  |  | 0% | 0 | 0 |  |  |  | ADAGMP06 |  | 0.95
0
| Fittings | [15 empty] | 0
0
J | Stainless steel main drain, 200x200mm | Aqua, Italy | 2 | Nos | 800 | 1600 | 650.5988 | 1301.1976 | [7 empty] | 2 | 1301.1976 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  |  | 0 | 0 |  |  |  | F-155
0
K | Stainless steel floor inlet | Aqua, Italy | 6 | Nos | 710 | 4260 | 577.4064 | 3464.4385 | [7 empty] | 6 | 3464.4385 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  |  | 0 | 0 |  |  |  | F-230
0
L | Stainless steel vacuum point | Aqua, Italy | 1 | Nos | 300 | 300 | 243.9745 | 243.9745 | [7 empty] | 1 | 243.9745 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  | 0% | 0 | 0 |  |  |  | F-240/A
0
M | ABS skimmer fittings with stainless steel faceplate | AtecPool, Spain | 2 | Nos | 820 | 1640 | 666.8638 | 1333.7275 | [7 empty] | 2 | 1333.7275 | 95% | 1.9 | 1267.0411 | 0% | 0 | 0 | 95% | 1.9 | 1267.0411 |  |  |  |  | 0 | 0 |  |  |  | 015901010 | WME-SW-WR-00080_00 | 0.95
| To Collection Dhs. |  |  |  |  | 21010 |  | 17086.3506 |  |  | 0 |  |  | 0 |  |  | 17086.3506 |  |  | 1900.5617 |  |  | 8032.0486 |  |  | 9932.6103 |  |  | 0 |  |  | 0 |  |  | 0
SWIMMING POOLS (CONT'D)
LEVEL 10 PENTHOUSE POOL (CONT'D)
Maintenance Kit
A | Vacuum head | Aqua, Italy | 1 | Nos | 830 | 830 | 674.9962 | 674.9962 | [8 empty] | 674.9962 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  |  | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
B | Telescopic handle |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
C | Vacuum hose |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
D | Pool brush |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
E | Leaf skimmer |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
F | Leaf rake |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
G | Algae brush |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
H | Hose fitting |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
J | Test kit |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
0
| Control Panel Board | [15 empty] | 0
0
K | Control Panel Board | Al Fanar/ Scheinder | 1 | Nos | 14000 | 14000 | 11385.4788 | 11385.4788 | [7 empty] | 1 | 11385.4788 |  |  |  | 90% | 0.9 | 10246.9309 | 90% | 0.9 | 10246.9309 |  |  |  |  | 0 | 0 |  |  | 0
0
L | MEP Works including piping, cabling, containment, etc. | Cosmoplast/Atlas/Cepex/Ducab | 1 | Nos | 70000 | 70000 | 56927.3938 | 56927.3938 | [7 empty] | 0.4 | 22770.9575 | 87.5% | 0.35 | 19924.5878 | 0% | 0 | 0 | 87.5% | 0.35 | 19924.5878 | 60% | 0.6 | 34156.4363 | 0% | 0 | 0 | 60% | 0.6 | 34156.4363 |  | WME-SW-WR-L10-00017 | 0.875
0
M | Testing and Commissioning |  | 1 | Item |  | Included | [10 empty] | 0
| To Collection Dhs. |  |  |  |  | 84830 |  | 68987.8688 |  |  | 0 |  |  | 0 |  |  | 34831.4325 |  |  | 19924.5878 |  |  | 10246.9309 |  |  | 30171.5187 |  |  | 34156.4363 |  |  | 0 |  |  | 34156.4363
SWIMMING POOLS (CONT'D)
LEVEL 10 PENTHOUSE POOL (CONT'D)
Underwater lights
A | X-W17 (as per LT902-LA-L10-SL-0110-01-[D]) (as per VE comparison table & data sheet) | Luce & Light | 9 | Nos | 4210 | 37890 | 3423.7761 | 30813.985 | [7 empty] | 9 | 30813.985 | 95% | 8.55 | 29273.2858 | 0% | 0 | 0 | 95% | 8.55 | 29273.2858 |  |  |  |  | 0 | 0 |  |  |  | CW16009LI + WC5003 | WIR TO FOLLOW - JA | 0.95
0
| Heating/Cooling System | [15 empty] | 0
0
B | Plate Heat Exchanger, Titanium, 65 kW heating capacity | Aqua, Italy | 1 | Nos | 10110 | 10110 | 8221.9422 | 8221.9422 | [7 empty] | 1 | 8221.9422 | 0% |  | 0 | 90% | 0.9 | 7399.7479 | 90% | 0.9 | 7399.7479 |  |  |  |  | 0 | 0 |  |  |  | Custom Made
0
C | Plate Heat Exchanger, Titanium, 38 kW cooling capacity | Aqua, Italy | 1 | Nos | 11950 | 11950 | 9718.3194 | 9718.3194 | [7 empty] | 1 | 9718.3194 | 0% |  | 0 | 90% | 0.9 | 8746.4874 | 90% | 0.9 | 8746.4874 |  |  |  |  | 0 | 0 |  |  |  | Custom Made
0
| Pool Surround | [15 empty] | 0
0
| Pool ladder, 3 steps | Aqua, Italy | 1 | Nos | 1210 | 1210 | 984.0307 | 984.0307 | [7 empty] | 1 | 984.0307 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 |  |  |  | 0% | 0 | 0 |  |  |  | L-106-316
0
0
| LEVEL 24 RESIDENTIAL POOL | [15 empty] | 0
0
| Filtration System | [15 empty] | 0
0
E | Laminated fiberglass Bobbin wound sand filter, 6.25 m3/h, Ø450mm, complete with sand media and manual multiport valve, 1 duty | Aqua, Italy | 1 | Nos | 1130 | 1130 | 918.9708 | 918.9708 | [7 empty] | 1 | 918.9708 | 95% | 0.95 | 873.0222 | 0% | 0 | 0 | 95% | 0.95 | 873.0222 |  |  |  | 0% | 0 | 0 |  |  |  | MU-450N-VS | WME-SW-WR-L24-00030_00 | 0.95
0
F | Plastic self-priming pump, 6.25 m3/h @ 15m head, 1HP, 1 duty + 1 standby | Aqua, Italy | 2 | Nos | 1630 | 3260 | 1325.595 | 2651.1901 | [7 empty] | 2 | 2651.1901 | 95% | 1.9 | 2518.6306 | 0% | 0 | 0 | 95% | 1.9 | 2518.6306 |  |  |  |  | 0 | 0 |  |  |  | EUROSWIM 100M/A | WME-SW-WR-L24-00030_00 | 0.95
0
| Water Treatment System | [15 empty] | 0
0
G | Automatic pH/RX dosing controller |  | 1 | Nos |  | 0 | [10 empty] | 0
0
H | Manual analog dosing pumps - pH (10L/h - 5 bar) |  | 1 | Nos |  | 0 | [10 empty] | 0
0
J | Manual analog dosing pumps - RX (10L/h - 5 bar) |  | 1 | Nos |  | 0 | [10 empty] | 0
0
| Pre-assembled panel - Twin Dosing System - 10L/h @ 4 bars (pH & Rx) | Aqua, Italy | 1 | Nos | 6030 | 6030 | 4903.8884 | 4903.8884 | [7 empty] | 1 | 4903.8884 | 95% | 0.95 | 4658.6939 | 0% | 0 | 0 | 95% | 0.95 | 4658.6939 |  |  |  |  | 0 | 0 |  |  |  | ADPS101 | WME-SW-WR-L24-00030_00 | 0.95
0
K | Polyethylene dosing tanks, 125L 100L | Aqua, Italy | 2 | Nos | 530 | 1060 | 431.0217 | 862.0434 | [7 empty] | 2 | 862.0434 | 95% | 1.9 | 818.9412 | 0% | 0 | 0 | 95% | 1.9 | 818.9412 |  |  |  | 0% | 0 | 0 |  |  |  | ADTANK010 | WME-SW-WR-L24-00030_00 | 0.95
0
L | Manual stirrers | Aqua, Italy | 2 | Nos | 410 | 820 | 333.4319 | 666.8638 | [7 empty] | 2 | 666.8638 | 95% | 1.9 | 633.5206 | 0% | 0 | 0 | 95% | 1.9 | 633.5206 |  |  |  | 0% | 0 | 0 |  |  |  | ADAGMP06 | WME-SW-WR-L24-00030_00 | 0.95
| To Collection Dhs. |  |  |  |  | 73460 |  | 59741.2335 |  |  | 0 |  |  | 0 |  |  | 59741.2335 |  |  | 38776.0943 |  |  | 16146.2354 |  |  | 54922.3297 |  |  | 0 |  |  | 0 |  |  | 0
SWIMMING POOLS (CONT'D)
LEVEL 24 RESIDENTIAL POOL (CONT'D)
Fittings
A | Stainless steel main drain, 200x200mm | Aqua, Italy | 2 | Nos | 800 | 1600 | 650.5988 | 1301.1976 | [7 empty] | 2 | 1301.1976 | 95% | 1.9 | 1236.1377 | 0% | 0 | 0 | 95% | 1.9 | 1236.1377 |  |  |  |  | 0 | 0 |  |  |  | F-155 | WME-SW-WR-L24-00056_00_B | 0.95
0
B | Stainless steel floor inlet | Aqua, Italy | 4 | Nos | 710 | 2840 | 577.4064 | 2309.6257 | [7 empty] | 4 | 2309.6257 | 95% | 3.8 | 2194.1444 | 0% | 0 | 0 | 95% | 3.8 | 2194.1444 |  |  |  |  | 0 | 0 |  |  |  | F-230 | WME-SW-WR-L24-00056_00_B | 0.95
0
C | Stainless steel vacuum point | Aqua, Italy | 1 | Nos | 300 | 300 | 243.9745 | 243.9745 | [7 empty] | 1 | 243.9745 | 95% | 0.95 | 231.7758 | 0% | 0 | 0 | 95% | 0.95 | 231.7758 |  |  |  | 0% | 0 | 0 |  |  |  | F-240/A | WME-SW-WR-L24-00056_00_B | 0.95
0
D | Stainless steel overflow fittings | AtecPool, Spain | 8 | Nos | 440 | 3520 | 357.8293 | 2862.6347 | [7 empty] | 8 | 2862.6347 | 95% | 7.6 | 2719.5029 | 0% | 0 | 0 | 95% | 7.6 | 2719.5029 |  |  |  |  | 0 | 0 |  |  |  | 03100282-1 | WME-SW-WR-L24-00056_00_B | 0.95
0
| Maintenance Kit | [15 empty] | 0
0
E | Vacuum head | Aqua, Italy | 1 | Nos | 830 | 830 | 674.9962 | 674.9962 | [8 empty] | 674.9962 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  |  | 0 | 0
[31 empty] | 0 | 0
F | Telescopic handle |  | 1 | Nos | [26 empty] | 0 | 0
[31 empty] | 0 | 0
G | Vacuum hose |  | 1 | Nos | [26 empty] | 0 | 0
[31 empty] | 0 | 0
H | Pool brush |  | 1 | Nos | [26 empty] | 0 | 0
[31 empty] | 0 | 0
J | Leaf skimmer |  | 1 | Nos | [26 empty] | 0 | 0
[31 empty] | 0 | 0
K | Leaf rake |  | 1 | Nos | [26 empty] | 0 | 0
[31 empty] | 0 | 0
L | Algae brush |  | 1 | Nos | [26 empty] | 0 | 0
[31 empty] | 0 | 0
M | Hose fitting |  | 1 | Nos | [26 empty] | 0 | 0
[31 empty] | 0 | 0
N | Test kit |  | 1 | Nos | [26 empty] | 0 | 0
0
| Control Panel Board | [15 empty] | 0
0
P | Control Panel Board | Al Fanar/ Scheinder | 1 | Nos | 14000 | 14000 | 11385.4788 | 11385.4788 | [7 empty] | 1 | 11385.4788 | 90% | 0.9 | 10246.9309 | 0% | 0 | 0 | 90% | 0.9 | 10246.9309 |  |  |  | 0% | 0 | 0 |  |  |  |  | WME-SW-WR-L24-00050
0
Q | MEP Works including piping, cabling, containment, etc. | Cosmoplast/Atlas/Cepex/Ducab | 1 | Nos | 70000 | 70000 | 56927.3938 | 56927.3938 | [7 empty] | 0.2 | 11385.4788 | 75% | 0.15 | 8539.1091 |  | 0 | 0 | 75% | 0.15 | 8539.1091 | 80% | 0.8 | 45541.915 | 0% | 0 | 0 | 80% | 0.8 | 45541.915 |  | WME-SW-WR-ML-00005 (WME-SW-WR-L24-00005) WME-SW-WR-L24-00025_00 WME-SW-WR-L24-00039 WME-SW-WR-L24-00047 WME-SW-WR-L24-00050 WME-SW-WR-L24-00076_00 | 0.75
0
R | Testing and Commissioning |  | 1 | Item |  | Included | [10 empty] | 0
| To Collection Dhs. |  |  |  |  | 93090 |  | 75705.3013 |  |  | 0 |  |  | 0 |  |  | 30163.3862 |  |  | 25167.6008 |  |  | 0 |  |  | 25167.6008 |  |  | 45541.915 |  |  | 0 |  |  | 45541.915
SWIMMING POOLS (CONT'D)
LEVEL 24 RESIDENTIAL POOL (CONT'D)
Underwater lights
A | X-W16 (as per VE comparison table & data sheet) | Luce & Light | 4 | Nos | 3830 | 15320 | 3114.7417 | 12458.9668 | [7 empty] | 4 | 12458.9668 | 95% | 3.8 | 11836.0184 | 0% | 0 | 0 | 95% | 3.8 | 11836.0184 |  |  |  |  | 0 | 0 |  |  | 0 | CW16009LI + WC5003 | WME-SW-WR-L24-00045 WME-SW-WR-L24-00060_00_B | 0.95
0
B | X-W17 (as per VE comparison table & data sheet) | Luce & Light | 3 | Nos | 4210 | 12630 | 3423.7761 | 10271.3283 | [7 empty] | 3 | 10271.3283 | 95% | 2.85 | 9757.7619 | 0% | 0 | 0 | 95% | 2.85 | 9757.7619 |  |  |  |  | 0 | 0 |  |  | 0 | CW300009MI + WC5006 | WME-SW-WR-L24-00045 WME-SW-WR-L24-00060_00_B | 0.95
0
| Heating/Cooling System | [15 empty] | 0
0
C | Plate Heat Exchanger, Titanium, 38 kW heating capacity | Aqua, Italy | 1 | Nos | 5760 | 5760 | 4684.3113 | 4684.3113 | [7 empty] | 1 | 4684.3113 | 95% | 0.95 | 4450.0957 | 0% | 0 | 0 | 95% | 0.95 | 4450.0957 |  |  |  |  | 0 | 0 |  |  | 0 | Custom Made | WME-SW-WR-L24-00030_00 | 0.95
0
D | Plate Heat Exchanger, Titanium, 15 kW cooling capacity | Aqua, Italy | 1 | Nos | 5190 | 5190 | 4220.7596 | 4220.7596 | [7 empty] | 1 | 4220.7596 | 95% | 0.95 | 4009.7216 | 0% | 0 | 0 | 95% | 0.95 | 4009.7216 |  |  |  |  | 0 | 0 |  |  | 0 | Custom Made | WME-SW-WR-L24-00030_00 | 0.95
0
0
| Pool Surround | [15 empty] | 0
0
| Pool ladder-overflow type, 3 steps | Aqua, Italy | 2 | Nos | 1400 | 2800 | 1138.5479 | 2277.0958 | [7 empty] | 2 | 2277.0958 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 |  |  |  |  | 0 | 0 |  |  | 0
| To Collection Dhs. |  |  |  |  | 41700 |  | 33912.4617 |  |  | 0 |  |  | 0 |  |  | 33912.4617 |  |  | 30053.5977 |  |  | 0 |  |  | 30053.5977 |  |  | 0 |  |  | 0 |  |  | 0
SWIMMING POOLS (CONT'D)
LEVEL 25 RESIDENTIAL POOL
Filtration System
B | Laminated fiberglass Bobbin wound sand filter, 6.25 m3/h, Ø450mm, complete with sand media and manual multiport valve, 1 duty | Aqua, Italy | 1 | Nos | 1130 | 1130 | 918.9708 | 918.9708 | [7 empty] | 1 | 918.9708 | 95% | 0.95 | 873.0222 | 0% | 0 | 0 | 95% | 0.95 | 873.0222 |  |  |  | 0% | 0 | 0 |  |  |  | MU-450N-VS | WME-SW-WR-L25-00033_01 | 0.95
0
C | Plastic self-priming pump, 6.25 m3/h @ 15m head, 1HP, 1 duty + 1 standby | Aqua, Italy | 2 | Nos | 1630 | 3260 | 1325.595 | 2651.1901 | [7 empty] | 2 | 2651.1901 | 95% | 1.9 | 2518.6306 | 0% | 0 | 0 | 95% | 1.9 | 2518.6306 |  |  |  |  | 0 | 0 |  |  |  | EUROSWIM 100M/A | WME-SW-WR-L25-00033_01 | 0.95
0
| Water Treatment System | [15 empty] | 0
0
D | Automatic pH/RX dosing controller |  | 1 | Nos |  | 0 | [10 empty] | 0
0
E | Manual analog dosing pumps - pH (10L/h - 5 bar) |  | 1 | Nos |  | 0 | [10 empty] | 0
0
F | Manual analog dosing pumps - RX (10L/h - 5 bar) |  | 1 | Nos |  | 0 | [10 empty] | 0
0
| Pre-assembled panel - Twin Dosing System - 10L/h @ 4 bars (pH & Rx) | Aqua, Italy | 1 | Nos | 6030 | 6030 | 4903.8884 | 4903.8884 | [7 empty] | 1 | 4903.8884 | 95% | 0.95 | 4658.6939 | 0% | 0 | 0 | 95% | 0.95 | 4658.6939 |  |  |  |  | 0 | 0 |  |  |  | ADPS101 | WME-SW-WR-L25-00033_01 | 0.95
0
G | Polyethylene dosing tanks, 125L 100L | Aqua, Italy | 2 | Nos | 530 | 1060 | 431.0217 | 862.0434 | [7 empty] | 2 | 862.0434 | 95% | 1.9 | 818.9412 | 0% | 0 | 0 | 95% | 1.9 | 818.9412 |  |  |  | 0% | 0 | 0 |  |  |  | ADTANK010 | WME-SW-WR-L25-00033_01 | 0.95
0
H | Manual stirrers | Aqua, Italy | 2 | Nos | 410 | 820 | 333.4319 | 666.8638 | [7 empty] | 2 | 666.8638 | 95% | 1.9 | 633.5206 | 0% | 0 | 0 | 95% | 1.9 | 633.5206 |  |  |  | 0% | 0 | 0 |  |  |  | ADAGMP06 | WME-SW-WR-L25-00033_01 | 0.95
0
| Fittings | [15 empty] | 0
0
J | Stainless steel main drain, 200x200mm | Aqua, Italy | 2 | Nos | 800 | 1600 | 650.5988 | 1301.1976 | [7 empty] | 2 | 1301.1976 | 95% | 1.9 | 1236.1377 | 0% | 0 | 0 | 95% | 1.9 | 1236.1377 |  |  |  |  | 0 | 0 |  |  |  | F-155 | WME-SW-WR-L25-00057_00_B | 0.95
0
K | Stainless steel floor inlet | Aqua, Italy | 4 | Nos | 710 | 2840 | 577.4064 | 2309.6257 | [7 empty] | 4 | 2309.6257 | 95% | 3.8 | 2194.1444 | 0% | 0 | 0 | 95% | 3.8 | 2194.1444 |  |  |  |  | 0 | 0 |  |  |  | F-230 | WME-SW-WR-L25-00057_00_B | 0.95
0
L | Stainless steel vacuum point | Aqua, Italy | 1 | Nos | 300 | 300 | 243.9745 | 243.9745 | [7 empty] | 1 | 243.9745 | 95% | 0.95 | 231.7758 | 0% | 0 | 0 | 95% | 0.95 | 231.7758 |  |  |  | 0% | 0 | 0 |  |  |  | F-240/A | WME-SW-WR-L25-00057_00_B | 0.95
0
M | Stainless steel overflow fittings | AtecPool, Spain | 8 | Nos | 440 | 3520 | 357.8293 | 2862.6347 | [7 empty] | 8 | 2862.6347 | 95% | 7.6 | 2719.5029 | 0% | 0 | 0 | 95% | 7.6 | 2719.5029 |  |  |  |  | 0 | 0 |  |  |  | 03100282-1 | WME-SW-WR-L25-00057_00_B | 0.95
| To Collection Dhs. |  |  |  |  | 20560 |  | 16720.3888 |  |  | 0 |  |  | 0 |  |  | 16720.3888 |  |  | 15884.3694 |  |  | 0 |  |  | 15884.3694 |  |  | 0 |  |  | 0 |  |  | 0
SWIMMING POOLS (CONT'D)
LEVEL 25 RESIDENTIAL POOL (CONT'D)
Maintenance Kit
A | Vacuum head | Aqua, Italy | 1 | Nos | 830 | 830 | 674.9962 | 674.9962 | [8 empty] | 674.9962 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  |  | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
B | Telescopic handle |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
C | Vacuum hose |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
D | Pool brush |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
E | Leaf skimmer |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
F | Leaf rake |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
G | Algae brush |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
H | Hose fitting |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
J | Test kit |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
0
| Control Panel Board | [15 empty] | 0
0
K | Control Panel Board | Al Fanar/ Scheinder | 1 | Nos | 14000 | 14000 | 11385.4788 | 11385.4788 | [7 empty] | 1 | 11385.4788 | 90% | 0.9 | 10246.9309 | 0% | 0 | 0 | 90% | 0.9 | 10246.9309 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  | WME-SW-WR-L25-00051
0
L | MEP Works including piping, cabling, containment, etc. | Cosmoplast/Atlas/Cepex/Ducab | 1 | Nos | 70000 | 70000 | 56927.3938 | 56927.3938 | [7 empty] | 0.2 | 11385.4788 | 75% | 0.15 | 8539.1091 | 0% | 0 | 0 | 75% | 0.15 | 8539.1091 | 80% | 0.8 | 45541.915 | 0% | 0 | 0 | 80% | 0.8 | 45541.915 |  | WME-SW-WR-L25-00021 WME-SW-WR-L25-00048 WME-SW-WR-L25-00051 WME-SW-WR-L25-00077_00 | 0.75 | 56927.3938 | 1138548% | 0.75
0
M | Testing and Commissioning |  | 1 | Item |  | Included | [10 empty] | 0
| To Collection Dhs. |  |  |  |  | 84830 |  | 68987.8688 |  |  | 0 |  |  | 0 |  |  | 23445.9538 |  |  | 18786.04 |  |  | 0 |  |  | 18786.04 |  |  | 45541.915 |  |  | 0 |  |  | 45541.915
SWIMMING POOLS (CONT'D)
LEVEL 25 RESIDENTIAL POOL (CONT'D)
Underwater lights
A | X-W16 (as per VE comparison table & data sheet) | Luce & Light | 6 | Nos | 3830 | 22980 | 3114.7417 | 18688.4501 |  |  |  | 0% | 6 | 18688.4501 |  | 6 | 18688.4501 | 95% | 5.7 | 17754.0276 | 0% | 0 | 0 | 95% | 5.7 | 17754.0276 |  |  |  |  | 0 | 0 |  |  |  | CW16009LI + WC5003 | WME-SW-WR-L25-00061_00_B | 0.95
0
B | X-W17 (as per VE comparison table & data sheet) | Luce & Light | 3 | Nos | 4210 | 12630 | 3423.7761 | 10271.3283 |  |  |  | 0% | 3 | 10271.3283 |  | 3 | 10271.3283 | 95% | 2.85 | 9757.7619 | 0% | 0 | 0 | 95% | 2.85 | 9757.7619 |  |  |  |  | 0 | 0 |  |  |  | CW300009MI + WC5006 | WME-SW-WR-L25-00061_00_B | 0.95
0
| Heating/Cooling System | [15 empty] | 0
0
C | Plate Heat Exchanger, Titanium, 38 kW heating capacity | Aqua, Italy | 1 | Nos | 5760 | 5760 | 4684.3113 | 4684.3113 |  |  |  | 0% | 1 | 4684.3113 |  | 1 | 4684.3113 | 95% | 0.95 | 4450.0957 | 0% | 0 | 0 | 95% | 0.95 | 4450.0957 |  |  |  |  | 0 | 0 |  |  |  | Custom Made | WME-SW-WR-L25-00033_01 | 0.95
0
D | Plate Heat Exchanger, Titanium, 15 kW cooling capacity | Aqua, Italy | 1 | Nos | 5190 | 5190 | 4220.7596 | 4220.7596 |  |  |  | 0% | 1 | 4220.7596 |  | 1 | 4220.7596 | 95% | 0.95 | 4009.7216 | 0% | 0 | 0 | 95% | 0.95 | 4009.7216 |  |  |  |  | 0 | 0 |  |  |  | Custom Made | WME-SW-WR-L25-00033_01 | 0.95
0
0
| Pool Surround | [15 empty] | 0
0
| Pool ladder-overflow type, 3 steps | Aqua, Italy | 2 | Nos | 1400 | 2800 | 1138.5479 | 2277.0958 |  |  |  | 0% | 2 | 2277.0958 |  | 2 | 2277.0958 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 |  |  |  |  | 0 | 0
0
0
| LEVEL 26 RESIDENTIAL POOL | [15 empty] | 0
0
| Filtration System | [15 empty] | 0
0
F | Laminated fiberglass Bobbin wound sand filter, 6.2 m3/h, Ø450mm, complete with sand media and manual multiport valve, 1 duty | Aqua, Italy | 1 | Nos | 1130 | 1130 | 918.9708 | 918.9708 |  |  |  | 0% | 1 | 918.9708 |  | 1 | 918.9708 | 95% | 0.95 | 873.0222 | 0% | 0 | 0 | 95% | 0.95 | 873.0222 |  |  |  | 0% | 0 | 0 |  |  |  | MU-450N-VS | WME-SW-WR-L26-00034_01 | 0.95
0
G | Plastic self-priming pump, 6.2 m3/h @ 15m head, 1HP, 1 duty + 1 standby | Aqua, Italy | 2 | Nos | 1630 | 3260 | 1325.595 | 2651.1901 |  |  |  | 0% | 2 | 2651.1901 |  | 2 | 2651.1901 | 95% | 1.9 | 2518.6306 | 0% | 0 | 0 | 95% | 1.9 | 2518.6306 |  |  |  |  | 0 | 0 |  |  |  | EUROSWIM 100M/A | WME-SW-WR-L26-00034_01 | 0.95
| To Collection Dhs. |  |  |  |  | 53750 |  | 43712.1059 |  |  | 0 |  |  | 43712.1059 |  |  | 43712.1059 |  |  | 39363.2597 |  |  | 0 |  |  | 39363.2597 |  |  | 0 |  |  | 0 |  |  | 0
SWIMMING POOLS (CONT'D)
LEVEL 26 RESIDENTIAL POOL (CONT'D)
Water Treatment System
A | Automatic pH/RX dosing controller |  | 1 | Nos |  | 0
B | Manual analog dosing pumps - pH (10L/h - 5 bar) |  | 1 | Nos |  | 0
C | Manual analog dosing pumps - RX (10L/h - 5 bar) |  | 1 | Nos |  | 0
| Pre-assembled panel - Twin Dosing System - 10L/h @ 4 bars (pH & Rx) | Aqua, Italy | 1 | Nos | 6030 | 6030 | 4903.8884 | 4903.8884 |  |  |  | 0% | 1 | 4903.8884 |  | 1 | 4903.8884 | 95% | 0.95 | 4658.6939 | 0% | 0 | 0 | 95% | 0.95 | 4658.6939 |  |  |  |  | 0 | 0 |  |  |  | ADPS101 | WME-SW-WR-L26-00034_01 | 0.95
0
D | Polyethylene dosing tanks, 125L 100L | Aqua, Italy | 2 | Nos | 530 | 1060 | 431.0217 | 862.0434 |  |  |  | 0% | 2 | 862.0434 |  | 2 | 862.0434 | 95% | 1.9 | 818.9412 | 0% | 0 | 0 | 95% | 1.9 | 818.9412 |  |  |  | 0% | 0 | 0 |  |  |  | ADTANK010 | WME-SW-WR-L26-00034_01 | 0.95
0
E | Manual stirrers | Aqua, Italy | 2 | Nos | 410 | 820 | 333.4319 | 666.8638 |  |  |  | 0% | 2 | 666.8638 |  | 2 | 666.8638 | 95% | 1.9 | 633.5206 | 0% | 0 | 0 | 95% | 1.9 | 633.5206 |  |  |  | 0% | 0 | 0 |  |  |  | ADAGMP06 | WME-SW-WR-L26-00034_01 | 0.95
0
| Fittings | [15 empty] | 0
0
F | Stainless steel main drain, 200x200mm | Aqua, Italy | 2 | Nos | 800 | 1600 | 650.5988 | 1301.1976 |  |  |  | 0% | 2 | 1301.1976 |  | 2 | 1301.1976 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  |  | 0 | 0 |  |  |  | F-155
0
G | Stainless steel wall floor inlet | Aqua, Italy | 4 | Nos | 710 | 2840 | 577.4064 | 2309.6257 |  |  |  | 0% | 4 | 2309.6257 |  | 4 | 2309.6257 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  |  | 0 | 0 |  |  |  | F-230
0
H | Stainless steel vacuum point | Aqua, Italy | 1 | Nos | 300 | 300 | 243.9745 | 243.9745 |  |  |  | 0% | 1 | 243.9745 |  | 1 | 243.9745 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  | 0% | 0 | 0 |  |  |  | F-240/A
0
J | ABS skimmer fittings with stainless steel faceplate | AtecPool, Spain | 2 | Nos | 820 | 1640 | 666.8638 | 1333.7275 |  |  |  | 0% | 2 | 1333.7275 |  | 2 | 1333.7275 | 45% | 0.9 | 600.1774 | 0% | 0 | 0 | 45% | 0.9 | 600.1774 |  |  |  |  | 0 | 0 |  |  |  | 015901010 | WME-SW-WR-L26-00053
Maintenance Kit
K | Vacuum head | Aqua, Italy | 1 | Nos | 830 | 830 | 674.9962 | 674.9962 |  |  |  | 0% | 0 | 674.9962 |  |  | 674.9962 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  |  | 0 | 0
[12 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0
L | Telescopic handle |  | 1 | Nos | [7 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0
[12 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0
M | Vacuum hose |  | 1 | Nos | [7 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0
[12 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0
N | Pool brush |  | 1 | Nos | [7 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0
[12 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0
P | Leaf skimmer |  | 1 | Nos | [7 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0
[12 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0
Q | Leaf rake |  | 1 | Nos | [7 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0
[12 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0
R | Algae brush |  | 1 | Nos | [7 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0
[12 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0
S | Hose fitting |  | 1 | Nos | [7 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0
[12 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0
T | Test kit |  | 1 | Nos | [7 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0
| To Collection Dhs. |  |  |  |  | 15120 |  | 12296.3171 |  |  | 0 |  |  | 12296.3171 |  |  | 12296.3171 |  |  | 6711.3331 |  |  | 0 |  |  | 6711.3331 |  |  | 0 |  |  | 0 |  |  | 0
SWIMMING POOLS (CONT'D)
LEVEL 26 RESIDENTIAL POOL (CONT'D)
Control Panel Board
A | Control Panel Board | Al Fanar/ Scheinder | 1 | Nos | 14000 | 14000 | 11385.4788 | 11385.4788 |  |  |  | 0% | 1 | 11385.4788 |  | 1 | 11385.4788 |  |  |  | 90% | 0.9 | 10246.9309 | 90% | 0.9 | 10246.9309 |  |  |  |  | 0 | 0 |  |  | 0
0
B | MEP Works including piping, cabling, containment, etc. | Cosmoplast/Atlas/Cepex/Ducab | 1 | Nos | 70000 | 70000 | 56927.3938 | 56927.3938 |  |  |  | 0% | 0.4 | 22770.9575 |  | 0.4 | 22770.9575 | 87.5% | 0.35 | 19924.5878 | 0% | 0 | 0 | 87.5% | 0.35 | 19924.5878 | 60% | 0.6 | 34156.4363 |  | 0 | 0 | 60% | 0.6 | 34156.4363 |  | WME-SW-WR-L26-00022 | 0.875
0
C | Testing and Commissioning |  | 1 | Item |  | Included | [10 empty] | 0
0
| Underwater lights | [15 empty] | 0
0
D | X-W16 |  | 4 | Nos |  | 0 | [10 empty] | 0
0
D | X-W17 (AS PER LT902-LA-L26-SL-0110-01-[A]_E) (as per VE comparison table & data sheet) | Luce & Light | 8 | Nos | 4210 | 33680 | 3423.7761 | 27390.2089 |  |  |  | 0% | 8 | 27390.2089 |  | 8 | 27390.2089 | 95% | 7.6 | 26020.6985 | 0% | 0 | 0 | 95% | 7.6 | 26020.6985 |  |  |  |  | 0 | 0 |  |  | 0 | CW300009MI + WC5006 | WIR TO FOLLOW - JA | 0.95
0
| Heating/Cooling System | [15 empty] | 0
0
E | Plate Heat Exchanger, Titanium, 32 kW heating capacity | Aqua, Italy | 1 | Nos | 5190 | 5190 | 4220.7596 | 4220.7596 |  |  |  | 0% | 1 | 4220.7596 |  | 1 | 4220.7596 | 95% | 0.95 | 4009.7216 | 0% | 0 | 0 | 95% | 0.95 | 4009.7216 |  |  |  |  | 0 | 0 |  |  | 0 | Custom Made | WME-SW-WR-L26-00034_01 | 0.95
0
F | Plate Heat Exchanger, Titanium, 15 kW cooling capacity | Aqua, Italy | 1 | Nos | 5190 | 5190 | 4220.7596 | 4220.7596 |  |  |  | 0% | 1 | 4220.7596 |  | 1 | 4220.7596 | 95% | 0.95 | 4009.7216 | 0% | 0 | 0 | 95% | 0.95 | 4009.7216 |  |  |  |  | 0 | 0 |  |  | 0 | Custom Made | WME-SW-WR-L26-00034_01 | 0.95
0
0
| Pool Surround | [15 empty] | 0
0
| Pool ladder, 3 steps | Aqua, Italy | 1 | Nos | 1210 | 1210 | 984.0307 | 984.0307 |  |  |  | 0% | 1 | 984.0307 |  | 1 | 984.0307 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  |  | 0 | 0 |  |  | 0
| To Collection Dhs. |  |  |  |  | 129270 |  | 105128.6314 |  |  | 0 |  |  | 70972.1951 |  |  | 70972.1951 |  |  | 53964.7296 |  |  | 10246.9309 |  |  | 64211.6605 |  |  | 34156.4363 |  |  | 0 |  |  | 34156.4363
SWIMMING POOLS (CONT'D)
LEVEL 27 RESIDENTIAL POOL
Filtration System
B | Laminated fiberglass Bobbin wound sand filter, 6.25 m3/h, Ø450mm, complete with sand media and manual multiport valve, 1 duty | Aqua, Italy | 1 | Nos | 1130 | 1130 | 918.9708 | 918.9708 |  |  |  | 0% | 1 | 918.9708 |  | 1 | 918.9708 | 95% | 0.95 | 873.0222 | 0% | 0 | 0 | 95% | 0.95 | 873.0222 |  |  |  | 0% | 0 | 0 |  |  |  | MU-450N-VS | WME-SW-WR-L27-00035_01 | 0.95
0
C | Plastic self-priming pump, 6.25 m3/h @ 15m head, 1HP, 1 duty + 1 standby | Aqua, Italy | 2 | Nos | 1630 | 3260 | 1325.595 | 2651.1901 |  |  |  | 0% | 2 | 2651.1901 |  | 2 | 2651.1901 | 95% | 1.9 | 2518.6306 | 0% | 0 | 0 | 95% | 1.9 | 2518.6306 |  |  |  |  | 0 | 0 |  |  |  | EUROSWIM 100M/A | WME-SW-WR-L27-00035_01 | 0.95
0
| Water Treatment System | [15 empty] | 0
0
D | Automatic pH/RX dosing controller |  | 1 | Nos |  | 0 | [10 empty] | 0
0
E | Manual analog dosing pumps - pH (10L/h - 5 bar) |  | 1 | Nos |  | 0 | [10 empty] | 0
0
F | Manual analog dosing pumps - RX (10L/h - 5 bar) |  | 1 | Nos |  | 0 | [10 empty] | 0
0
| Pre-assembled panel - Twin Dosing System - 10L/h @ 4 bars (pH & Rx) | Aqua, Italy | 1 | Nos | 6030 | 6030 | 4903.8884 | 4903.8884 |  |  |  | 0% | 1 | 4903.8884 |  | 1 | 4903.8884 | 95% | 0.95 | 4658.6939 | 0% | 0 | 0 | 95% | 0.95 | 4658.6939 |  |  |  |  | 0 | 0 |  |  |  | ADPS101 | WME-SW-WR-L27-00035_01 | 0.95
0
G | Polyethylene dosing tanks, 125L 100L | Aqua, Italy | 2 | Nos | 530 | 1060 | 431.0217 | 862.0434 |  |  |  | 0% | 2 | 862.0434 |  | 2 | 862.0434 | 95% | 1.9 | 818.9412 | 0% | 0 | 0 | 95% | 1.9 | 818.9412 |  |  |  | 0% | 0 | 0 |  |  |  | ADTANK010 | WME-SW-WR-L27-00035_01 | 0.95
0
H | Manual stirrers | Aqua, Italy | 2 | Nos | 410 | 820 | 333.4319 | 666.8638 |  |  |  | 0% | 2 | 666.8638 |  | 2 | 666.8638 | 95% | 1.9 | 633.5206 | 0% | 0 | 0 | 95% | 1.9 | 633.5206 |  |  |  | 0% | 0 | 0 |  |  |  | ADAGMP06 | WME-SW-WR-L27-00035_01 | 0.95
0
| Fittings | [15 empty] | 0
0
J | Stainless steel main drain, 200x200mm | Aqua, Italy | 2 | Nos | 800 | 1600 | 650.5988 | 1301.1976 |  |  |  | 0% | 2 | 1301.1976 |  | 2 | 1301.1976 | 95% | 1.9 | 1236.1377 | 0% | 0 | 0 | 95% | 1.9 | 1236.1377 |  |  |  |  | 0 | 0 |  |  |  | F-155 | WME-SW-WR-L27-00058_00_B | 0.95
0
K | Stainless steel floor inlet | Aqua, Italy | 4 | Nos | 710 | 2840 | 577.4064 | 2309.6257 |  |  |  | 0% | 4 | 2309.6257 |  | 4 | 2309.6257 | 95% | 3.8 | 2194.1444 | 0% | 0 | 0 | 95% | 3.8 | 2194.1444 |  |  |  |  | 0 | 0 |  |  |  | F-230 | WME-SW-WR-L27-00058_00_B | 0.95
0
L | Stainless steel vacuum point | Aqua, Italy | 1 | Nos | 300 | 300 | 243.9745 | 243.9745 |  |  |  | 0% | 1 | 243.9745 |  | 1 | 243.9745 | 95% | 0.95 | 231.7758 | 0% | 0 | 0 | 95% | 0.95 | 231.7758 |  |  |  | 0% | 0 | 0 |  |  |  | F-240/A | WME-SW-WR-L27-00058_00_B | 0.95
0
M | Stainless steel overflow fittings | AtecPool, Spain | 8 | Nos | 440 | 3520 | 357.8293 | 2862.6347 |  |  |  | 0% | 8 | 2862.6347 |  | 8 | 2862.6347 | 95% | 7.6 | 2719.5029 | 0% | 0 | 0 | 95% | 7.6 | 2719.5029 |  |  |  |  | 0 | 0 |  |  |  | 03100282-1 | WME-SW-WR-L27-00058_00_B | 0.95
| To Collection Dhs. |  |  |  |  | 20560 |  | 16720.3888 |  |  | 0 |  |  | 16720.3888 |  |  | 16720.3888 |  |  | 15884.3694 |  |  | 0 |  |  | 15884.3694 |  |  | 0 |  |  | 0 |  |  | 0
SWIMMING POOLS (CONT'D)
LEVEL 27 RESIDENTIAL POOL (CONT'D)
Maintenance Kit
A | Vacuum head | Aqua, Italy | 1 | Nos | 830 | 830 | 674.9962 | 674.9962 |  |  |  | 0% | 0 | 674.9962 |  |  | 674.9962 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  |  | 0 | 0 |  |  | 0
[12 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0 |  |  | 0
B | Telescopic handle |  | 1 | Nos | [7 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0 |  |  | 0
[12 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0 |  |  | 0
C | Vacuum hose |  | 1 | Nos | [7 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0 |  |  | 0
[12 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0 |  |  | 0
D | Pool brush |  | 1 | Nos | [7 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0 |  |  | 0
[12 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0 |  |  | 0
E | Leaf skimmer |  | 1 | Nos | [7 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0 |  |  | 0
[12 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0 |  |  | 0
F | Leaf rake |  | 1 | Nos | [7 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0 |  |  | 0
[12 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0 |  |  | 0
G | Algae brush |  | 1 | Nos | [7 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0 |  |  | 0
[12 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0 |  |  | 0
H | Hose fitting |  | 1 | Nos | [7 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0 |  |  | 0
[12 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0 |  |  | 0
J | Test kit |  | 1 | Nos | [7 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0 |  |  | 0
Control Panel Board
K | Control Panel Board | Al Fanar/ Scheinder | 1 | Nos | 14000 | 14000 | 11385.4788 | 11385.4788 |  |  |  | 0% | 1 | 11385.4788 |  | 1 | 11385.4788 | 90% | 0.9 | 10246.9309 | 0% | 0 | 0 | 90% | 0.9 | 10246.9309 |  |  |  |  | 0 | 0 |  |  | 0 |  | WME-SW-WR-L27-00052
0
L | MEP Works including piping, cabling, containment, etc. | Cosmoplast/Atlas/Cepex/Ducab | 1 | Nos | 70000 | 70000 | 56927.3938 | 56927.3938 | 80% | 0.8 | 45541.915 | -80% | -0.6 | -34156.4363 |  | 0.2 | 11385.4788 | 75% | 0.15 | 8539.1091 | 0% | 0 | 0 | 75% | 0.15 | 8539.1091 | 80% | 0.8 | 45541.915 | 0% | 0 | 0 | 80% | 0.8 | 45541.915 |  | WME-SW-WR-L27-00027 WME-SW-WR-L27-00049 WME-SW-WR-L27-00052 WME-SW-WR-L27-00075_00 | 0.75
0
M | Testing and Commissioning |  | 1 | Item |  | Included | [10 empty] | 0
0
| Underwater lights | [15 empty] | 0
0
N | X-W16 (as per VE comparison table & data sheet) | Luce & Light | 6 | Nos | 3830 | 22980 | 3114.7417 | 18688.4501 |  |  |  | 0% | 6 | 18688.4501 |  | 6 | 18688.4501 | 95% | 5.7 | 17754.0276 | 0% | 0 | 0 | 95% | 5.7 | 17754.0276 |  |  |  |  | 0 | 0 |  |  | 0 | CW16009LI + WC5003 | WME-SW-WR-L27-00044 | 0.95
0
P | X-W17 (as per VE comparison table & data sheet) | Luce & Light | 3 | Nos | 4210 | 12630 | 3423.7761 | 10271.3283 |  |  |  | 0% | 3 | 10271.3283 |  | 3 | 10271.3283 | 95% | 2.85 | 9757.7619 | 0% | 0 | 0 | 95% | 2.85 | 9757.7619 |  |  |  |  | 0 | 0 |  |  | 0 | CW300009MI + WC5006 | WME-SW-WR-L27-00044 | 0.95
| To Collection Dhs. |  |  |  |  | 120440 |  | 97947.6473 |  |  | 45541.915 |  |  | 6863.8172 |  |  | 52405.7322 |  |  | 46297.8295 |  |  | 0 |  |  | 46297.8295 |  |  | 45541.915 |  |  | 0 |  |  | 45541.915
SWIMMING POOLS (CONT'D)
LEVEL 27 RESIDENTIAL POOL (CONT'D)
Heating/Cooling System
A | Plate Heat Exchanger, Titanium, 38 kW heating capacity | Aqua, Italy | 1 | Nos | 5760 | 5760 | 4684.3113 | 4684.3113 |  |  |  | 0% | 1 | 4684.3113 |  | 1 | 4684.3113 | 95% | 0.95 | 4450.0957 | 0% | 0 | 0 | 95% | 0.95 | 4450.0957 |  |  |  |  | 0 | 0 |  |  |  | Custom Made | WME-SW-WR-L27-00035_01 | 0.95
0
B | Plate Heat Exchanger, Titanium, 15 kW cooling capacity | Aqua, Italy | 1 | Nos | 5190 | 5190 | 4220.7596 | 4220.7596 |  |  |  | 0% | 1 | 4220.7596 |  | 1 | 4220.7596 | 95% | 0.95 | 4009.7216 | 0% | 0 | 0 | 95% | 0.95 | 4009.7216 |  |  |  |  | 0 | 0 |  |  |  | Custom Made | WME-SW-WR-L27-00035_01 | 0.95
0
0
| Pool Surround | [15 empty] | 0
0
| Pool ladder-overflow type, 3 steps | Aqua, Italy | 2 | Nos | 1400 | 2800 | 1138.5479 | 2277.0958 |  |  |  | 0% | 2 | 2277.0958 |  | 2 | 2277.0958 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 |  |  |  |  | 0 | 0
0
0
| LEVEL 29 RESIDENTIAL POOL | [15 empty] | 0
0
| Filtration System | [15 empty] | 0
0
D | Laminated fiberglass Bobbin wound sand filter, 6.25 m3/h, Ø450mm, complete with sand media and manual multiport valve, 1 duty | Aqua, Italy | 1 | Nos | 1130 | 1130 | 918.9708 | 918.9708 |  |  |  | 0% | 1 | 918.9708 |  | 1 | 918.9708 | 95% | 0.95 | 873.0222 | 0% | 0 | 0 | 95% | 0.95 | 873.0222 |  |  |  | 0% | 0 | 0 |  |  |  | MU-450N-VS | WME-SW-WR-L29-00036_01 | 0.95
0
E | Plastic self-priming pump, 6.25 m3/h @ 15m head, 1HP, 1 duty + 1 standby | Aqua, Italy | 2 | Nos | 1630 | 3260 | 1325.595 | 2651.1901 |  |  |  | 0% | 2 | 2651.1901 |  | 2 | 2651.1901 | 95% | 1.9 | 2518.6306 | 0% | 0 | 0 | 95% | 1.9 | 2518.6306 |  |  |  |  | 0 | 0 |  |  |  | EUROSWIM 100M/A | WME-SW-WR-L29-00036_01 | 0.95
0
| Water Treatment System | [15 empty] | 0
0
F | Automatic pH/RX dosing controller |  | 1 | Nos |  | 0 | [10 empty] | 0
0
G | Manual analog dosing pumps - pH (10L/h - 5 bar) |  | 1 | Nos |  | 0 | [10 empty] | 0
0
H | Manual analog dosing pumps - RX (10L/h - 5 bar) |  | 1 | Nos |  | 0 | [10 empty] | 0
0
| Pre-assembled panel - Twin Dosing System - 10L/h @ 4 bars (pH & Rx) | Aqua, Italy | 1 | Nos | 6030 | 6030 | 4903.8884 | 4903.8884 |  |  |  | 0% | 1 | 4903.8884 |  | 1 | 4903.8884 | 95% | 0.95 | 4658.6939 | 0% | 0 | 0 | 95% | 0.95 | 4658.6939 |  |  |  |  | 0 | 0 |  |  |  | ADPS101 | WME-SW-WR-L29-00036_01 | 0.95
0
J | Polyethylene dosing tanks, 125L 100L | Aqua, Italy | 2 | Nos | 530 | 1060 | 431.0217 | 862.0434 |  |  |  | 0% | 2 | 862.0434 |  | 2 | 862.0434 | 95% | 1.9 | 818.9412 | 0% | 0 | 0 | 95% | 1.9 | 818.9412 |  |  |  | 0% | 0 | 0 |  |  |  | ADTANK010 | WME-SW-WR-L29-00036_01 | 0.95
0
K | Manual stirrers | Aqua, Italy | 2 | Nos | 410 | 820 | 333.4319 | 666.8638 |  |  |  | 0% | 2 | 666.8638 |  | 2 | 666.8638 | 95% | 1.9 | 633.5206 | 0% | 0 | 0 | 95% | 1.9 | 633.5206 |  |  |  | 0% | 0 | 0 |  |  |  | ADAGMP06 | WME-SW-WR-L29-00036_01 | 0.95
0
| Fittings | [15 empty] | 0
0
L | Stainless steel main drain, 200x200mm | Aqua, Italy | 2 | Nos | 800 | 1600 | 650.5988 | 1301.1976 |  |  |  | 0% | 2 | 1301.1976 |  | 2 | 1301.1976 | 95% | 1.9 | 1236.1377 | 0% | 0 | 0 | 95% | 1.9 | 1236.1377 |  |  |  |  | 0 | 0 |  |  |  | F-155 | WME-SW-WR-L29-00059_00_B | 0.95
0
M | Stainless steel floor inlet | Aqua, Italy | 4 | Nos | 710 | 2840 | 577.4064 | 2309.6257 |  |  |  | 0% | 4 | 2309.6257 |  | 4 | 2309.6257 | 95% | 3.8 | 2194.1444 | 0% | 0 | 0 | 95% | 3.8 | 2194.1444 |  |  |  |  | 0 | 0 |  |  |  | F-230 | WME-SW-WR-L29-00059_00_B | 0.95
0
N | Stainless steel vacuum point | Aqua, Italy | 1 | Nos | 300 | 300 | 243.9745 | 243.9745 |  |  |  | 0% | 1 | 243.9745 |  | 1 | 243.9745 | 95% | 0.95 | 231.7758 | 0% | 0 | 0 | 95% | 0.95 | 231.7758 |  |  |  |  | 0 | 0 |  |  |  | F-240/A | WME-SW-WR-L29-00059_00_B | 0.95
0
P | Stainless steel overflow fittings | AtecPool, Spain | 8 | Nos | 440 | 3520 | 357.8293 | 2862.6347 |  |  |  | 0% | 8 | 2862.6347 |  | 8 | 2862.6347 | 95% | 7.6 | 2719.5029 | 0% | 0 | 0 | 95% | 7.6 | 2719.5029 |  |  |  |  | 0 | 0 |  |  |  | 03100282-1 | WME-SW-WR-L29-00059_00_B | 0.95
| To Collection Dhs. |  |  |  |  | 34310 |  | 27902.5554 |  |  | 0 |  |  | 27902.5554 |  |  | 27902.5554 |  |  | 24344.1867 |  |  | 0 |  |  | 24344.1867 |  |  | 0 |  |  | 0 |  |  | 0
SWIMMING POOLS (CONT'D)
LEVEL 29 RESIDENTIAL POOL (CONT'D)
Maintenance Kit
A | Vacuum head | Aqua, Italy | 1 | Nos | 830 | 830 | 674.9962 | 674.9962 |  |  |  | 0% | 0 | 674.9962 |  |  | 674.9962 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  |  | 0 | 0 |  |  | 0
[12 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0 |  |  | 0
B | Telescopic handle |  | 1 | Nos | [7 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0 |  |  | 0
[12 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0 |  |  | 0
C | Vacuum hose |  | 1 | Nos | [7 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0 |  |  | 0
[12 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0 |  |  | 0
D | Pool brush |  | 1 | Nos | [7 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0 |  |  | 0
[12 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0 |  |  | 0
E | Leaf skimmer |  | 1 | Nos | [7 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0 |  |  | 0
[12 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0 |  |  | 0
F | Leaf rake |  | 1 | Nos | [7 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0 |  |  | 0
[12 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0 |  |  | 0
G | Algae brush |  | 1 | Nos | [7 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0 |  |  | 0
[12 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0 |  |  | 0
H | Hose fitting |  | 1 | Nos | [7 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0 |  |  | 0
[12 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0 |  |  | 0
J | Test kit |  | 1 | Nos | [7 empty] | 0% | 0 | 0 | [16 empty] | 0 | 0 |  |  | 0
Control Panel Board
K | Control Panel Board | Al Fanar/ Scheinder | 1 | Nos | 14000 | 14000 | 11385.4788 | 11385.4788 |  |  |  | 0% | 1 | 11385.4788 |  | 1 | 11385.4788 | 95% | 0.95 | 10816.2048 | 0% | 0 | 0 | 95% | 0.95 | 10816.2048 |  |  |  |  | 0 | 0 |  |  | 0 |  | WIR TO FOLLOW - JA | 0.95
0
L | MEP Works including piping, cabling, containment, etc. | Cosmoplast/Atlas/Cepex/Ducab | 1 | Nos | 70000 | 70000 | 56927.3938 | 56927.3938 | 80% | 0.8 | 45541.915 | -80% | -0.6 | -34156.4363 |  | 0.2 | 11385.4788 | 75% | 0.15 | 8539.1091 | 0% | 0 | 0 | 75% | 0.15 | 8539.1091 | 80% | 0.8 | 45541.915 |  | 0 | 0 | 80% | 0.8 | 45541.915 |  | WME-SW-WR-L29-00009 WME-SW-WR-L29-00012 WME-SW-WR-L29-00024_00 WME-SW-WR-L29-00054_00_B WME-SW-WR-L29-00055_00_B | 0.75
0
M | Testing and Commissioning |  | 1 | Item |  | included | [10 empty] | 0
0
| Underwater lights | [15 empty] | 0
0
N | X-W16 (as per VE comparison table & data sheet) | Luce & Light | 6 | Nos | 3830 | 22980 | 3114.7417 | 18688.4501 |  |  |  | 0% | 6 | 18688.4501 |  | 6 | 18688.4501 | 95% | 5.7 | 17754.0276 | 0% | 0 | 0 | 95% | 5.7 | 17754.0276 |  |  |  |  | 0 | 0 |  |  | 0 | CW16009LI + WC5003 | WIR TO FOLLOW - JA | 0.95
0
P | X-W17 (as per VE comparison table & data sheet) | Luce & Light | 3 | Nos | 4210 | 12630 | 3423.7761 | 10271.3283 |  |  |  | 0% | 3 | 10271.3283 |  | 3 | 10271.3283 | 95% | 2.85 | 9757.7619 | 0% | 0 | 0 | 95% | 2.85 | 9757.7619 |  |  |  |  | 0 | 0 |  |  | 0 | CW300009MI + WC5006 | WIR TO FOLLOW - JA | 0.95
| To Collection Dhs. |  |  |  |  | 120440 |  | 97947.6473 |  |  | 45541.915 |  |  | 6863.8172 |  |  | 52405.7322 |  |  | 46867.1034 |  |  | 0 |  |  | 46867.1034 |  |  | 45541.915 |  |  | 0 |  |  | 45541.915
SWIMMING POOLS (CONT'D)
LEVEL 29 RESIDENTIAL POOL (CONT'D)
Heating/Cooling System
A | Plate Heat Exchanger, Titanium, 38 kW heating capacity | Aqua, Italy | 1 | Nos | 5760 | 5760 | 4684.3113 | 4684.3113 |  |  |  | 0% | 1 | 4684.3113 |  | 1 | 4684.3113 | 95% | 0.95 | 4450.0957 | 0% | 0 | 0 | 95% | 0.95 | 4450.0957 |  |  |  |  | 0 | 0 |  |  |  | Custom Made | WME-SW-WR-L29-00036_01 | 0.95
0
B | Plate Heat Exchanger, Titanium, 15 kW cooling capacity | Aqua, Italy | 1 | Nos | 5190 | 5190 | 4220.7596 | 4220.7596 |  |  |  | 0% | 1 | 4220.7596 |  | 1 | 4220.7596 | 95% | 0.95 | 4009.7216 | 0% | 0 | 0 | 95% | 0.95 | 4009.7216 |  |  |  |  | 0 | 0 |  |  |  | Custom Made | WME-SW-WR-L29-00036_01 | 0.95
0
0
| Pool Surround | [15 empty] | 0
0
| Pool ladder-overflow type, 3 steps | Aqua, Italy | 2 | Nos | 1400 | 2800 | 1138.5479 | 2277.0958 |  |  |  | 0% | 2 | 2277.0958 |  | 2 | 2277.0958 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 |  |  |  |  | 0 | 0
0
0
| LEVEL 29 HOTEL ROOF TOP POOL | [15 empty] | 0
0
| Filtration System | [15 empty] | 0
0
D | Laminated Bobbin wound sand filter, simultaneous projection of resin and fibre glass, 25.95 m3/h, Ø900mm, complete with sand media and manual valve manifold, 6 duties | Aqua, Italy | 6 | Nos | 3730 | 22380 | 3033.4168 | 18200.501 |  |  |  | 0% | 6 | 18200.501 |  | 6 | 18200.501 | 95% | 5.7 | 17290.476 | 0% | 0 | 0 | 95% | 5.7 | 17290.476 |  |  |  |  | 0 | 0 |  |  |  | MU-900N-VS | WME-SW-WR-L29-00029_00 | 0.95
0
E | Plastic self-priming pump, 52.0 m3/h @ 16m head, 7.5HP, 3 duty + 1 standby | Aqua, Italy | 4 | Nos | 7350 | 29400 | 5977.3763 | 23909.5054 |  |  |  | 0% | 4 | 23909.5054 |  | 4 | 23909.5054 | 95% | 3.8 | 22714.0301 | 0% | 0 | 0 | 95% | 3.8 | 22714.0301 |  |  |  |  | 0 | 0 |  |  |  | KPA1000 | WME-SW-WR-L29-00029_00 | 0.95
0
| Water Treatment System | [15 empty] | 0
0
F | Automatic pH/RX dosing controller |  | 1 | Nos |  | 0 | [10 empty] | 0
0
G | Manual analog dosing pumps - pH (20L/h-5 bar) |  | 2 | Nos |  | 0 | [10 empty] | 0
0
H | Manual analog dosing pumps - RX (20L/h-5 bar) |  | 2 | Nos |  | 0 | [10 empty] | 0
0
| Pre-assembled panel - Twin Dosing System - 10L/h @ 4 bars (pH & Rx) | Aqua, Italy | 4 | Nos | 6030 | 24120 | 4903.8884 | 19615.5534 |  |  |  | 0% | 4 | 19615.5534 |  | 4 | 19615.5534 | 95% | 3.8 | 18634.7757 | 0% | 0 | 0 | 95% | 3.8 | 18634.7757 |  |  |  |  | 0 | 0 |  |  |  | ADPS101 | WME-SW-WR-L29-00029_00 | 0.95
0
J | Polyethylene dosing tanks, 1000L | Aqua, Italy | 4 | Nos | 3410 | 13640 | 2773.1773 | 11092.7093 |  |  |  | 0% | 4 | 11092.7093 |  | 4 | 11092.7093 | 95% | 3.8 | 10538.0738 | 0% | 0 | 0 | 95% | 3.8 | 10538.0738 |  |  |  |  | 0 | 0 |  |  |  | ADTANK100 | WME-SW-WR-L29-00029_00 | 0.95
0
K | Manual stirrers | Aqua, Italy | 4 | Nos | 440 | 1760 | 357.8293 | 1431.3173 |  |  |  | 0% | 4 | 1431.3173 |  | 4 | 1431.3173 | 95% | 3.8 | 1359.7515 | 0% | 0 | 0 | 95% | 3.8 | 1359.7515 |  |  |  | 0% | 0 | 0 |  |  |  | ADAGMP06 | WME-SW-WR-L29-00029_00 | 0.95
0
L | UV Sterilizer, Flow: 95 m³/h at 3 bar pressure | AtecPool, Spain | 2 | Nos | 44830 | 89660 | 36457.9295 | 72915.859 |  |  |  | 0% | 2 | 72915.859 |  | 2 | 72915.859 | 95% | 1.9 | 69270.066 | 0% | 0 | 0 | 95% | 1.9 | 69270.066 |  |  |  |  | 0 | 0 |  |  |  | UV-5205 | WME-SW-WR-L29-00029_00 | 0.95
0
| Fittings | [15 empty] | 0
0
M | Stainless steel main drain, 400x400mm | Aqua, Italy | 7 | Nos | 1460 | 10220 | 1187.3428 | 8311.3995 |  |  |  | 0% | 7 | 8311.3995 |  | 7 | 8311.3995 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  |  | 0 | 0 |  |  |  | F-158
0
N | Stainless steel floor inlet | Aqua, Italy | 64 | Nos | 710 | 45440 | 577.4064 | 36954.0111 |  |  |  | 0% | 64 | 36954.0111 |  | 64 | 36954.0111 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  |  | 0 | 0 |  |  |  | F-230
0
N | Stainless steel wall inlet | Aqua, Italy | 46 | Nos | 280 | 12880 | 227.7096 | 10474.6405 |  |  |  | 0% | 46 | 10474.6405 |  | 46 | 10474.6405 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  |  | 0 | 0
0
P | Stainless steel vacuum point | Aqua, Italy | 8 | Nos | 300 | 2400 | 243.9745 | 1951.7964 |  |  |  | 0% | 8 | 1951.7964 |  | 8 | 1951.7964 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  | 0% | 0 | 0 |  |  |  | F-240/A
0
Q | Stainless steel overflow fittings | AtecPool or eq. | 127 | Nos | 440 | 55880 | 357.8293 | 45444.3252 |  |  |  | 0% | 127 | 45444.3252 |  | 127 | 45444.3252 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  |  | 0 | 0 |  |  |  | 03100282-1
| To Collection Dhs. |  |  |  |  | 321530 |  | 261483.7846 |  |  | 0 |  |  | 261483.7846 |  |  | 261483.7846 |  |  | 148266.9905 |  |  | 0 |  |  | 148266.9905 |  |  | 0 |  |  | 0 |  |  | 0
SWIMMING POOLS (CONT'D)
LEVEL 29 HOTEL ROOF TOP POOL (CONT'D)
Overflow Effect System
A | Overflow effect cast iron pump with cast iron impeller plastic pump, 87.8 m3/h @ 16m head, 10HP, 3Ph, 2 duty | Aqua, Italy | 2 | Nos | 8790 | 17580 | 7148.4542 | 14296.9083 |  |  |  | 0% | 2 | 14296.9083 |  | 2 | 14296.9083 | 95% | 1.9 | 13582.06 | 0% | 0 | 0.0029099 | 95% | 1.9 | 13582.0629 |  |  |  |  | 0 | 0 |  |  | 0 |  | WME-SW-WR-L29-00029_00 | 0.95
Maintenance Kit
D | Flexible vacuum head | Aqua, Italy | 1 | Nos | 830 | 830 | 674.9962 | 674.9962 |  |  |  | 0% | 0 | 674.9962 |  |  | 674.9962 | 0% |  | - | 0% | 0 |  | 0% | 0 | 0 |  |  |  | 0% | 0 | 0 |  |  |  | C-151
[12 empty] | 0% | 0 | 0 | [15 empty] | 0% | 0 | 0
E | Telescopic handle |  | 1 | Nos | [7 empty] | 0% | 0 | 0 | [15 empty] | 0% | 0 | 0 |  |  |  | C-137
[12 empty] | 0% | 0 | 0 | [15 empty] | 0% | 0 | 0
F | Vacuum hose |  | 1 | Nos | [7 empty] | 0% | 0 | 0 | [15 empty] | 0% | 0 | 0 |  |  |  | C-133
[12 empty] | 0% | 0 | 0 | [15 empty] | 0% | 0 | 0
G | Pool brush |  | 1 | Nos | [7 empty] | 0% | 0 | 0 | [15 empty] | 0% | 0 | 0 |  |  |  | C-151
[12 empty] | 0% | 0 | 0 | [15 empty] | 0% | 0 | 0
H | Leaf skimmer |  | 1 | Nos | [7 empty] | 0% | 0 | 0 | [15 empty] | 0% | 0 | 0 |  |  |  | C-151
[12 empty] | 0% | 0 | 0 | [15 empty] | 0% | 0 | 0
J | Leaf rake |  | 1 | Nos | [7 empty] | 0% | 0 | 0 | [15 empty] | 0% | 0 | 0 |  |  |  | C-145
[12 empty] | 0% | 0 | 0 | [15 empty] | 0% | 0 | 0
K | Algae brush |  | 1 | Nos | [7 empty] | 0% | 0 | 0 | [15 empty] | 0% | 0 | 0 |  |  |  | C-122
[12 empty] | 0% | 0 | 0 | [15 empty] | 0% | 0 | 0
L | Hose fitting |  | 1 | Nos | [7 empty] | 0% | 0 | 0 | [15 empty] | 0% | 0 | 0 |  |  |  | C-135
[12 empty] | 0% | 0 | 0 | [15 empty] | 0% | 0 | 0
M | Test kit |  | 1 | Nos | [7 empty] | 0% | 0 | 0 | [15 empty] | 0% | 0 | 0 |  |  |  | C-151
Control Panel Board
N | Control Panel Board | Al Fanar/ Scheinder | 1 | Nos | 43750 | 43750 | 35579.6211 | 35579.6211 |  |  |  | 0% | 1 | 35579.6211 |  | 1 | 35579.6211 | 95% | 0.95 | 33800.64 | 0% | 0 | 6.3096e-05 | 95% | 0.95 | 33800.6401 |  |  |  |  | 0 | 0 |  |  | 0 |  | WME-SW-WR-L28-00073_00 | 0.95
0
P | MEP Works including piping, cabling, containment, etc. | Cosmoplast/Atlas/Cepex/Ducab | 1 | Nos | 250000 | 250000 | 203312.1207 | 203312.1207 | 88% | 0.88 | 178914.6662 | -88% | -0.76 | -154517.2117 |  | 0.12 | 24397.4545 | 55% | 0.07 | 13418.6 | 0% | -0.004 | -3.5102e-05 | 55% | 0.066 | 13418.6 | 88% | 0.88 | 178914.6662 | 0% | 0 | 0 | 88% | 0.88 | 178914.6662 | - | WME-SW-WR-L29-00001 WME-SW-WR-L29-00011_00 WME-SW-WR-ML-00014 WME-SW-WR-L28-00072_00 WME-SW-WR-L28-00073_00 | 0.55
0
Q | Testing and Commissioning |  | 1 | Item |  | Included | [10 empty] | 0
0
| Underwater lights | [15 empty] | 0
N | X-F1 UFO - Fiber optic system - Consisting of: 3 x Light source, IP20 with metallic enclosure No. of Points: 750 points Cable Size: 0.75mm2 (80%), 1.0 mm2 (18%) and 1.5 mm2 (2%) Cable length: average 20m WITHOUT END FITTINGS | UFO, UK | 1 | Item | 197540 | 197540 | 160649.1053 | 160649.1053 |  |  |  | 0% | 1 | 160649.1053 |  | 1 | 160649.1053 | 95% | 0.95 | 152616.65 | 0% | 0 | 1.2892e-05 | 95% | 0.95 | 152616.65 |  |  |  | 0% | 0 | 0 |  |  |  | - | WME-SW-WR-L29-00079_00 | 0.95
0
P | X-F2 UFO - Fiber optic system - Consisting of: 2 x Light source, IP20 with metallic enclosure No. of Points: 200 points Cable Size: 0.75mm2 (80%), 1.0 mm2 (18%) and 1.5 mm2 (2%) Cable length: average 20m WITHOUT END FITTINGS | UFO, UK | 1 | Item | 89670 | 89670 | 72923.9914 | 72923.9914 |  |  |  | 0% | 1 | 72923.9914 |  | 1 | 72923.9914 | 95% | 0.95 | 69277.79 | 0% | 0 | 0.0018733 | 95% | 0.95 | 69277.7919 |  |  |  | 0% | 0 | 0 |  |  |  | - | WME-SW-WR-L29-00079_00 | 0.95
| To Collection Dhs. |  |  |  |  | 599370 |  | 487436.7431 |  |  | 178914.6662 |  |  | 129607.4107 |  |  | 308522.0769 |  |  | 282695.74 |  |  | 0.0048241 |  |  | 282695.7448 |  |  | 178914.6662 |  |  | 0 |  |  | 178914.6662
SWIMMING POOLS (CONT'D)
LEVEL 29 HOTEL ROOF TOP POOL (CONT'D)
Heating/Cooling System
R | Air-to-water Heat/Cool Pump Brand: Astral, Spain Heating Capacity: 210 kW Cooling Capacity: 150 kW | Astral, Spain | 4 | Nos | 102770 | 411080 | 83577.5466 | 334310.1863 | 88.53% | 3.5414 | 295977.6 | -88.53% | -3.0827 | -257645.0137 |  | 0.45865 | 38332.5863 | 12.79% | 0.058647 | 4901.5695 | 0% | 0 | 0 | 12.79% | 0.058647 | 4901.5695 | 88.53% | 3.5414 | 295977.6 | 0% | 0 | 0 | 88.53% | 3.5414 | 295977.6 | AHP500-SU R4 | WME-SW-WR-ML-00006 (WME-SW-WR-L29-00006) WME-SW-WR-L29-00029_00 | 0.12787 | checked formula - progress cumulative total 90% | 12.79%
0
| Plastic booster pump, 40 m3/h @ 20m head, 12.5HP, 4 duty | Aqua, Italy | 4 | Nos | 10300 | 41200 | 8376.4594 | 33505.8375 | 0% |  | 0 | 0% | 4 | 33505.8375 |  | 4 | 33505.8375 | 95% | 3.8 | 31830.5456 | 0% | 0 | 0 | 95% | 3.8 | 31830.5456 |  |  | 0 |  | 0 | 0 | 0% |  | 0 | KPA600 | WME-SW-WR-L29-00029_00 | 0.95
0
| Control Panel Board | Al Fanar/ Scheinder | 1 | Nos | 26250 | 26250 | 21347.7727 | 21347.7727 | 0% |  | 0 | 0% | 1 | 21347.7727 |  | 1 | 21347.7727 | 95% | 0.95 | 20280.384 | 0% | 0 | 0 | 95% | 0.95 | 20280.384 |  |  | 0 |  | 0 | 0 | 0% |  | 0 |  | WME-SW-WR-L28-00073_00 | 0.95
0
| Water Tanks | [15 empty] | 0
0
| GRP Panel Balancing Tank, 48 m3 (6.0x4.0x2.0m) Non-insulated |  | 1 | Nos | 103250 | 103250 | 83967.9058 | 83967.9058 | 80% | 0.8 | 67174.3247 | -80% | -0.6 | -50380.7435 |  | 0.2 | 16793.5812 | 50% | 0.1 | 8396.7906 | 25% | 0.05 | 4198.3953 | 75% | 0.15 | 12595.1859 | 80% | 0.8 | 67174.3247 | 0% | 0 | 0 | 80% | 0.8 | 67174.3247 | - | WME-SW-WR-L29-00029_00 | 0.5 | checked formula - progress cumulative total 90% | 50%
0
| GRP Panel Backwash Tank, 3 m3 (1.5x1.0x2.0m) Non-insulated |  | 1 | Nos | 10360 | 10360 | 8425.2543 | 8425.2543 | 80% | 0.8 | 6740.2034 | -80% | -0.6 | -5055.1526 |  | 0.2 | 1685.0509 | 50% | 0.1 | 842.5254 | 0% | 0 | 0 | 50% | 0.1 | 842.5254 | 80% | 0.8 | 6740.2034 | 0% | 0 | 0 | 80% | 0.8 | 6740.2034 | - | WME-SW-WR-L29-00029_00 | 0.5 | not installed at site but paid under RPJV
| To Collection Dhs. |  |  |  |  | 592140 |  | 481556.9566 |  |  | 369892.1281 |  |  | -258227.2996 |  |  | 111664.8285 |  |  | 66251.8152 |  |  | 4198.3953 |  |  | 70450.2105 |  |  | 369892.1281 |  |  | 0 |  |  | 369892.1281
SWIMMING POOLS (CONT'D)
ADDITIONAL ITEMS
A | Pipe acoustic insulations for gravity lines and above critical areas only
| Swimming Pool @ Level 4 |  | 1 | Nos | 15000 | 15000 | 12198.7272 | 12198.7272 |  |  |  | 0% | 1 | 12198.7272 |  | 1 | 12198.7272 | 95% | 0.95 | 11588.7909 | 0% | 0 | 0 | 95% | 0.95 | 11588.7909 |  |  |  |  | 0 | 0 |  |  | 0 |  | WME-SW-WR-L3-00032_01 | 0.95
0
| Swimming Pool @ Level 10 |  | 1 | Nos | 7000 | 7000 | 5692.7394 | 5692.7394 |  |  |  | 0% | 1 | 5692.7394 |  | 1 | 5692.7394 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 |  |  |  |  | 0 | 0 |  |  | 0
0
| Swimming Pool @ Level 24 |  | 1 | Nos | 7000 | 7000 | 5692.7394 | 5692.7394 |  |  |  | 0% | 1 | 5692.7394 |  | 1 | 5692.7394 | 95% | 0.95 | 5408.1024 | 0% | 0 | 0 | 95% | 0.95 | 5408.1024 |  |  |  |  | 0 | 0 |  |  | 0 |  | WME-SW-WR-L24-00030_00 | 0.95
0
| Swimming Pool @ Level 25 |  | 1 | Nos | 7000 | 7000 | 5692.7394 | 5692.7394 |  |  |  | 0% | 1 | 5692.7394 |  | 1 | 5692.7394 | 95% | 0.95 | 5408.1024 | 0% | 0 | 0 | 95% | 0.95 | 5408.1024 |  |  |  |  | 0 | 0 |  |  | 0 |  | WME-SW-WR-L25-00033_01 | 0.95
0
| Swimming Pool @ Level 26 |  | 1 | Nos | 7000 | 7000 | 5692.7394 | 5692.7394 |  |  |  | 0% | 1 | 5692.7394 |  | 1 | 5692.7394 | 95% | 0.95 | 5408.1024 | 0% | 0 | 0 | 95% | 0.95 | 5408.1024 |  |  |  |  | 0 | 0 |  |  | 0 |  | WME-SW-WR-L26-00034_01 | 0.95
0
| Swimming Pool @ Level 27 |  | 1 | Nos | 7000 | 7000 | 5692.7394 | 5692.7394 |  |  |  | 0% | 1 | 5692.7394 |  | 1 | 5692.7394 | 95% | 0.95 | 5408.1024 | 0% | 0 | 0 | 95% | 0.95 | 5408.1024 |  |  |  |  | 0 | 0 |  |  | 0 |  | WME-SW-WR-L27-00035_01 | 0.95
0
| Swimming Pool @ Level 29 (Residential) |  | 1 | Nos | 7000 | 7000 | 5692.7394 | 5692.7394 |  |  |  | 0% | 1 | 5692.7394 |  | 1 | 5692.7394 | 95% | 0.95 | 5408.1024 | 0% | 0 | 0 | 95% | 0.95 | 5408.1024 |  |  |  |  | 0 | 0 |  |  | 0 |  | WME-SW-WR-L29-00036_01 | 0.95
0
| Swimming Pool @ Level 29 (Roof) |  | 1 | Nos | 37500 | 37500 | 30496.8181 | 30496.8181 |  |  |  | 0% | 1 | 30496.8181 |  | 1 | 30496.8181 | 95% | 0.95 | 28971.9772 | 0% | 0 | 0 | 95% | 0.95 | 28971.9772 |  |  |  |  | 0 | 0 |  |  | 0 |  | WME-SW-WR-L29-00029_00 | 0.95
0
0
B | Level 10 Swimming Pool Lights (as per LT902-LA-L10-SL-0110-01-[D]) | [15 empty] | 0
0
| X-W16 (as per VE comparison table & data sheet) | Luce & Light | 3 | Nos | 3830 | 11490 | 3114.7417 | 9344.2251 |  |  |  | 0% | 3 | 9344.2251 |  | 3 | 9344.2251 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  |  | 0 | 0 |  |  | 0
| To Collection Dhs. |  |  |  |  | 105990 |  | 86196.2067 |  |  | 0 |  |  | 86196.2067 |  |  | 86196.2067 |  |  | 67601.2801 |  |  | 0 |  |  | 67601.2801 |  |  | 0 |  |  | 0 |  |  | 0
SWIMMING POOLS (CONT'D)
ADDITIONAL ITEMS
A | Lifesaving Equipment
| Swimming Pool @ Level 4 - Lifeguard chair (1 no.) - Lifebuoy (2 nos.) + accessories | Aqua, Italy | 1 | Item | 8870 | 8870 | 7213.514 | 7213.514 |  |  |  | 0% | 1 | 7213.514 |  | 1 | 7213.514 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  | 0% | 0 | 0 |  |  |  | PG-14, PG-15 & 'PG-16
| Swimming Pool @ Level 10 - Lifeguard chair (1 no.) - Lifebuoy (2 nos.) + accessories | Aqua, Italy | 1 | Item | 8870 | Rate only
| Swimming Pool @ Level 24 - Lifeguard chair (1 no.) - Lifebuoy (2 nos.) + accessories | Aqua, Italy | 1 | Item | 8870 | Rate only
| Swimming Pool @ Level 25 - Lifeguard chair (1 no.) - Lifebuoy (2 nos.) + accessories | Aqua, Italy | 1 | Item | 8870 | Rate only
| Swimming Pool @ Level 26 - Lifeguard chair (1 no.) - Lifebuoy (2 nos.) + accessories | Aqua, Italy | 1 | Item | 8870 | Rate only
| Swimming Pool @ Level 27 - Lifeguard chair (1 no.) - Lifebuoy (2 nos.) + accessories | Aqua, Italy | 1 | Item | 8870 | Rate only
| Swimming Pool @ Level 29 - Lifeguard chair (1 no.) - Lifebuoy (2 nos.) + accessories | Aqua, Italy | 1 | Item | 8870 | Rate only
| Swimming Pool @ Level 29 (Roof) - Lifeguard chair (4 no.) - Lifebuoy (8 nos.) + accessories | Aqua, Italy | 1 | Item | 35480 | 35480 | 28854.0562 | 28854.0562 |  |  |  | 0% | 1 | 28854.0562 |  | 1 | 28854.0562 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  | 0% | 0 | 0 |  |  |  | PG-14, PG-15 & 'PG-16
B | Fiber Optic Light System with end fittings
| X-F1 UFO - Fiber optic system - Consisting of: 3 x Light source, IP20 with metallic enclosure No. of Points: 750 points Cable Size: 1.5 mm2 (100%) Cable length: average 20m WITH P4G END FITTINGS | UFO, UK | 1 | Item | 252280 | Rate only to add on base price
| X-F2 UFO - Fiber optic system - Consisting of: 2 x Light source, IP20 with metallic enclosure No. of Points: 200 points Cable Size: 1.5 mm2 (100%) Cable length: average 20m WITH P4G END FITTINGS | UFO, UK | 1 | Item | 57520 | Rate only to add on base price
| To Collection Dhs. |  |  |  |  | 44350 |  | 36067.5702 |  |  | 0 |  |  | 36067.5702 |  |  | 36067.5702 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
SWIMMING POOLS (CONT'D)
ADDITIONAL ITEMS
A | Level 29 Roof Swimming Pools Suspended GRP
| GRP Tank, (4.0x2.0x1.0m), 8 m3 | Al Bassam - AquaSystem | 1 | Nos | 19170 | 19170 | 15589.9734 | 15589.9734 |  |  |  | 0% | 1 | 15589.9734 |  | 1 | 15589.9734 | 95% | 0.95 | 14810.4747 | 0% | 0 | 0 | 95% | 0.95 | 14810.4747 |  |  |  | 0% | 0 | 0 |  |  |  | - | WME-SW-WR-L29-00029_00 | 0.95
0
| Plastic Discharge/Booster Pump, 146.5 m3/h @ 8m head, 12.5 HP, 1 duty + 1 standby | Aqua, Italy | 2 | Nos | 10300 | 20600 | 8376.4594 | 16752.9187 |  |  |  | 0% | 2 | 16752.9187 |  | 2 | 16752.9187 | 95% | 1.9 | 15915.2728 | 0% | 0 | 0 | 95% | 1.9 | 15915.2728 |  |  |  |  | 0 | 0 |  |  |  | KPA1250 | WME-SW-WR-L29-00029_00 | 0.95
0
| Control Panel Provision | Al Fanar/ Scheinder | 1 | Nos | 4380 | 4380 | 3562.0284 | 3562.0284 |  |  |  | 0% | 1 | 3562.0284 |  | 1 | 3562.0284 | 95% | 0.95 | 3383.9269 | 0% | 0 | 0 | 95% | 0.95 | 3383.9269 |  |  |  |  | 0 | 0 | [5 empty] | 0.95
0
| MEP Works including piping, cabling, containment, etc. | Cosmoplast/Atlas/Cepex/Ducab | 1 | Nos | 43750 | 43750 | 35579.6211 | 35579.6211 |  |  |  | 0% | 1 | 35579.6211 |  | 1 | 35579.6211 | 95% | 0.95 | 33800.6401 | 0% | 0 | 0 | 95% | 0.95 | 33800.6401 |  |  |  |  | 0 | 0 |  |  |  |  | WME-SW-WR-L28-00072_00 | 0.95
0
0
0
| To Collection Dhs. |  |  |  |  | 87900 |  | 71484.5416 |  |  | 0 |  |  | 71484.5416 |  |  | 71484.5416 |  |  | 67910.3145 |  |  | 0 |  |  | 67910.3145 |  |  | 0 |  |  | 0 |  |  | 0
SWIMMING POOLS (CONT'D)
COLLECTION
| Page 1 / 1 |  |  |  |  | 142700 |  | 116050.5585 |  |  | 0 |  |  | 0 |  |  | 116050.5585 |  |  | 110248.02 |  |  | 0.01056 |  |  | 110248.0306 |  |  | 0 |  |  | 0 |  |  | 0
| Page 1 / 2 |  |  |  |  | 132330 |  | 107617.1717 |  |  | 0 |  |  | 0 |  |  | 34424.8083 |  |  | 28402.7033 |  |  | 0 |  |  | 28402.7033 |  |  | 73192.3634 |  |  | 0 |  |  | 73192.3634
| Page 1 / 3 |  |  |  |  | 309285 |  | 251525.557 |  |  | 0 |  |  | 0 |  |  | 251525.557 |  |  | 227047.5909 |  |  | 0 |  |  | 227047.5909 |  |  | 0 |  |  | 0 |  |  | 0
| Page 1 / 4 |  |  |  |  | 21010 |  | 17086.3506 |  |  | 0 |  |  | 0 |  |  | 17086.3506 |  |  | 1900.5617 |  |  | 8032.0486 |  |  | 9932.6103 |  |  | 0 |  |  | 0 |  |  | 0
| Page 1 / 5 |  |  |  |  | 84830 |  | 68987.8688 |  |  | 0 |  |  | 0 |  |  | 34831.4325 |  |  | 19924.5878 |  |  | 10246.9309 |  |  | 30171.5187 |  |  | 34156.4363 |  |  | 0 |  |  | 34156.4363
| Page 1 / 6 |  |  |  |  | 73460 |  | 59741.2335 |  |  | 0 |  |  | 0 |  |  | 59741.2335 |  |  | 38776.0943 |  |  | 16146.2354 |  |  | 54922.3297 |  |  | 0 |  |  | 0 |  |  | 0
| Page 1 / 7 |  |  |  |  | 93090 |  | 75705.3013 |  |  | 0 |  |  | 0 |  |  | 30163.3862 |  |  | 25167.6008 |  |  | 0 |  |  | 25167.6008 |  |  | 45541.915 |  |  | 0 |  |  | 45541.915
| Page 1 / 8 |  |  |  |  | 41700 |  | 33912.4617 |  |  | 0 |  |  | 0 |  |  | 33912.4617 |  |  | 30053.5977 |  |  | 0 |  |  | 30053.5977 |  |  | 0 |  |  | 0 |  |  | 0
| Page 1 / 9 |  |  |  |  | 20560 |  | 16720.3888 |  |  | 0 |  |  | 0 |  |  | 16720.3888 |  |  | 15884.3694 |  |  | 0 |  |  | 15884.3694 |  |  | 0 |  |  | 0 |  |  | 0
| Page 1 / 10 |  |  |  |  | 84830 |  | 68987.8688 |  |  | 0 |  |  | 0 |  |  | 23445.9538 |  |  | 18786.04 |  |  | 0 |  |  | 18786.04 |  |  | 45541.915 |  |  | 0 |  |  | 45541.915
| Page 1 / 11 |  |  |  |  | 53750 |  | 43712.1059 |  |  | 0 |  |  | 43712.1059 |  |  | 43712.1059 |  |  | 39363.2597 |  |  | 0 |  |  | 39363.2597 |  |  | 0 |  |  | 0 |  |  | 0
| Page 1 / 12 |  |  |  |  | 15120 |  | 12296.3171 |  |  | 0 |  |  | 12296.3171 |  |  | 12296.3171 |  |  | 6711.3331 |  |  | 0 |  |  | 6711.3331 |  |  | 0 |  |  | 0 |  |  | 0
| Page 1 / 13 |  |  |  |  | 129270 |  | 105128.6314 |  |  | 0 |  |  | 70972.1951 |  |  | 70972.1951 |  |  | 53964.7296 |  |  | 10246.9309 |  |  | 64211.6605 |  |  | 34156.4363 |  |  | 0 |  |  | 34156.4363
| Page 1 / 14 |  |  |  |  | 20560 |  | 16720.3888 |  |  | 0 |  |  | 16720.3888 |  |  | 16720.3888 |  |  | 15884.3694 |  |  | 0 |  |  | 15884.3694 |  |  | 0 |  |  | 0 |  |  | 0
| Page 1 / 15 |  |  |  |  | 120440 |  | 97947.6473 |  |  | 45541.915 |  |  | 6863.8172 |  |  | 52405.7322 |  |  | 46297.8295 |  |  | 0 |  |  | 46297.8295 |  |  | 45541.915 |  |  | 0 |  |  | 45541.915
| Page 1 / 16 |  |  |  |  | 34310 |  | 27902.5554 |  |  | 0 |  |  | 27902.5554 |  |  | 27902.5554 |  |  | 24344.1867 |  |  | 0 |  |  | 24344.1867 |  |  | 0 |  |  | 0 |  |  | 0
| Page 1 / 17 |  |  |  |  | 120440 |  | 97947.6473 |  |  | 45541.915 |  |  | 6863.8172 |  |  | 52405.7322 |  |  | 46867.1034 |  |  | 0 |  |  | 46867.1034 |  |  | 45541.915 |  |  | 0 |  |  | 45541.915
| Page 1 / 18 |  |  |  |  | 321530 |  | 261483.7846 |  |  | 0 |  |  | 261483.7846 |  |  | 261483.7846 |  |  | 148266.9905 |  |  | 0 |  |  | 148266.9905 |  |  | 0 |  |  | 0 |  |  | 0
| Page 1 / 19 |  |  |  |  | 599370 |  | 487436.7431 |  |  | 178914.6662 |  |  | 129607.4107 |  |  | 308522.0769 |  |  | 282695.74 |  |  | 0.0048241 |  |  | 282695.7448 |  |  | 178914.6662 |  |  | 0 |  |  | 178914.6662
| Page 1 / 20 |  |  |  |  | 592140 |  | 481556.9566 |  |  | 369892.1281 |  |  | -258227.2996 |  |  | 111664.8285 |  |  | 66251.8152 |  |  | 4198.3953 |  |  | 70450.2105 |  |  | 369892.1281 |  |  | 0 |  |  | 369892.1281
| Page 1 / 21 |  |  |  |  | 105990 |  | 86196.2067 |  |  | 0 |  |  | 86196.2067 |  |  | 86196.2067 |  |  | 67601.2801 |  |  | 0 |  |  | 67601.2801 |  |  | 0 |  |  | 0 |  |  | 0
| Page 1 / 22 |  |  |  |  | 44350 |  | 36067.5702 |  |  | 0 |  |  | 36067.5702 |  |  | 36067.5702 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Page 1 / 23 |  |  |  |  | 87900 |  | 71484.5416 |  |  | 0 |  |  | 71484.5416 |  |  | 71484.5416 |  |  | 67910.3145 |  |  | 0 |  |  | 67910.3145 |  |  | 0 |  |  | 0 |  |  | 0
| To Summary |  |  |  |  | 3248965 |  | 2642215.8567 | 24.22% |  | 639890.6244 | 19.38% |  | 511943.411 | 66.98% |  | 1769736.1662 | 52.32% |  | 1382350.1175 | 1.85% |  | 48870.5565 | 54.17% |  | 1431220.6739 | 33.02% |  | 872479.6904 | 0% |  | 0 | 33.02% |  | 872479.6904 |  |  |  | 2642215.8567
FOR CHECKING PURPOSES ONLY

## WTF
PLOT-18 | [5 empty] | WM Ref. No.: D20/054-12/C
BILL OF QUANTITIES | [5 empty] | Date: 06-05-2021 | [32 empty] | Discount Rate
BILL :- WATER FEATURES | [38 empty] | 81.32%
[8 empty] | A | [8 empty] | C=A-B | [17 empty] | B
[15 empty] | WM-Khansaheb BOQ |  |  | WM-Khansaheb Progress Claim - February 2023 | [8 empty] | OMNIYAT RECOMMENDATION - as per 17001DH/SCA/40-01-33-WM Ver 2 dated 11 April 2022 | [8 empty] | ITEM CODE | WIR |  | 18.68%
Item | Description | Make | Qty. | Unit | Rate | Amount | Rate | Amount after Discount | Last Month |  |  | This Month |  |  | TOTAL |  |  | Last Month - KCE PC 12 (Jan, 2023) |  |  | This Month |  |  | Total To Date |  |  | Last Month |  |  | This Month |  |  | Total To Date
[6 empty] | (Dhs.) | after Discount | (Dhs.) | % | Qty | Value | % | Qty | Value | % | Qty | Value | % | Qty | Value | % | Qty | Value | % | Qty | Value | % | Qty | Value | % | Qty | Value | % | Qty | Value
WATER FEATURES
LEVEL 02
Filtration System
B | Laminated fiberglass Bobbin wound sand filter, 5.9 m3/h, Ø450mm, complete with sand media and manual multiport valve, 1 duty | Aqua, Italy | 1 | Nos | 1130 | 1130 | 918.9708 | 918.9708 | [7 empty] | 1 | 918.9708 | 95% | 0.95 | 873.0222 | 0% | 0 | 0 | 95% | 0.95 | 873.0222 |  |  |  | 0% | 0 | 0 |  |  |  | MU-450N-VS | WME-SW-WR-L02-00023_00 | 0.95
0
C | Plastic self-priming pump, 5.9 m3/h @ 15m head, 1.0HP, 1 duty + 1 standby | Aqua, Italy | 2 | Nos | 1630 | 3260 | 1325.595 | 2651.1901 | [7 empty] | 2 | 2651.1901 | 95% | 1.9 | 2518.6306 | 0% | 0 | 0 | 95% | 1.9 | 2518.6306 |  |  |  |  | 0 | 0 |  |  |  | EUROSWIM 100M/A | WME-SW-WR-L02-00023_00 | 0.95
0
| Water Treatment System | [15 empty] | 0
0
D | Automatic pH/RX dosing controller |  | 1 | Nos |  | 0 | [10 empty] | 0
0
E | Manual analog dosing pumps - pH (10L/h - 5 bar) |  | 1 | Nos |  | 0 | [10 empty] | 0
0
F | Manual analog dosing pumps - RX (10L/h - 5 bar) |  | 1 | Nos |  | 0 | [10 empty] | 0
0
| Pre-assembled panel - Twin Dosing System - 10L/h @ 4 bars (pH & Rx) | Aqua, Italy | 1 | Nos | 6030 | 6030 | 4903.8884 | 4903.8884 | [7 empty] | 1 | 4903.8884 | 95% | 0.95 | 4658.6939 | 0% | 0 | 0 | 95% | 0.95 | 4658.6939 |  |  |  | 0% | 0 | 0 |  |  |  | ADPS101 | WME-SW-WR-L02-00023_00 | 0.95
0
G | Polyethylene dosing tanks, 125L 100L | Aqua, Italy | 2 | Nos | 530 | 1060 | 431.0217 | 862.0434 | [7 empty] | 2 | 862.0434 | 95% | 1.9 | 818.9412 | 0% | 0 | 0 | 95% | 1.9 | 818.9412 |  |  |  | 0% | 0 | 0 |  |  |  | ADTANK010 | WME-SW-WR-L02-00023_00 | 0.95
0
H | Manual stirrers | Aqua, Italy | 2 | Nos | 410 | 820 | 333.4319 | 666.8638 | [7 empty] | 2 | 666.8638 | 95% | 1.9 | 633.5206 | 0% | 0 | 0 | 95% | 1.9 | 633.5206 |  |  |  | 0% | 0 | 0 |  |  |  | ADAGMP06 | WME-SW-WR-L02-00023_00 | 0.95
0
| Fittings | [15 empty] | 0
0
J | Stainless steel main drain, Ø300mm | Astral, Spain | 2 | Nos | 350 | 700 | 284.637 | 569.2739 | [7 empty] | 2 | 569.2739 | 95% | 1.9 | 540.8102 | 0% | 0 | 0 | 95% | 1.9 | 540.8102 |  |  |  |  | 0 | 0 |  |  |  | 00282 | WME-SW-WR-L2-00065_00_B | 0.95
0
K | Stainless steel floor inlet | Aqua, Italy | 38 | Nos | 710 | 26980 | 577.4064 | 21941.4441 | [7 empty] | 38 | 21941.4441 | 95% | 36.1 | 20844.3719 | 0% | 0 | 0 | 95% | 36.1 | 20844.3719 |  |  |  |  | 0 | 0 |  |  |  | F-230 | WME-SW-WR-L2-00065_00_B | 0.95
0
L | Stainless steel vacuum point | Aqua, Italy | 1 | Nos | 300 | 300 | 243.9745 | 243.9745 | [7 empty] | 1 | 243.9745 | 95% | 0.95 | 231.7758 | 0% | 0 | 0 | 95% | 0.95 | 231.7758 |  |  |  | 0% | 0 | 0 |  |  |  | F-240/A | WME-SW-WR-L2-00065_00_B | 0.95
0
M | Stainless steel overflow fittings | AtecPool, Spain | 54 | Nos | 440 | 23760 | 357.8293 | 19322.7839 | [7 empty] | 54 | 19322.7839 | 95% | 51.3 | 18356.6448 | 0% | 0 | 0 | 95% | 51.3 | 18356.6448 |  |  |  |  | 0 | 0 |  |  |  | 03100282-1 | WME-SW-WR-L2-00065_00_B | 0.95
0
| Overflow Effect System (4mm water film thickness) | [15 empty] | 0
0
N | Overflow effect cast iron pump with cast iron impeller plastic pump, 113.1 m3/h @ 18m head, 15HP, 2 duty | Aqua, Italy | 2 | Nos | 10300 | 20600 | 8376.4594 | 16752.9187 | [7 empty] | 2 | 16752.9187 | 95% | 1.9 | 15915.2728 | 0% | 0 | 0 | 95% | 1.9 | 15915.2728 |  |  |  | 0% | 0 | 0 |  |  |  | KPA1250 | WME-SW-WR-L02-00023_00 | 0.95
| To Collection Dhs. |  |  |  |  | 84640 |  | 68833.3516 |  |  | 0 |  |  | 0 |  |  | 68833.3516 |  |  | 65391.684 |  |  | 0 |  |  | 65391.684 |  |  | 0 |  |  | 0 |  |  | 0
WATER FEATURES (CONT'D)
LEVEL 02 (CONT'D)
Maintenance Kit
A | Vacuum head | Aqua, Italy | 1 | Nos | 830 | 830 | 674.9962 | 674.9962 | [8 empty] | 674.9962 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  |  | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
B | Telescopic handle |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
C | Vacuum hose |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
D | Pool brush |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
E | Leaf skimmer |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
F | Leaf rake |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
G | Algae brush |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
H | Hose fitting |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
J | Test kit |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
0
| Control Panel Board | [15 empty] | 0
0
K | Control Panel Board | Al Fanar/ Scheinder | 1 | Nos | 26250 | 26250 | 21347.7727 | 21347.7727 | [7 empty] | 1 | 21347.7727 | 95% | 0.95 | 20280.384 | 0% | 0 | 0 | 95% | 0.95 | 20280.384 |  |  |  |  | 0 | 0 |  |  | 0 |  | WME-SW-WR-L2-00062_00 | 0.95
0
L | MEP Works including piping, cabling, containment, etc. | Cosmoplast/Atlas/Cepex/Ducab | 1 | Nos | 100000 | 100000 | 81324.8483 | 81324.8483 | [7 empty] | 0.2 | 16264.9697 | 75% | 0.15 | 12198.7272 | 0% | 0 | 0 | 75% | 0.15 | 12198.7272 | 80% | 0.8 | 65059.8786 | 0% | 0 | 0 | 80% | 0.8 | 65059.8786 | - | WME-SW-WR-L2-00007_00_D WME-SW-WR-L2-00008_00_D WME-SW-WR-L2-00013 WME-SW-WR-L2-00015 WME-SW-WR-L2-00037_00 WME-SW-WR-L2-00041_00-B WME-SW-WR-L2-00062_00 | 0.75
0
M | Testing and Commissioning |  | 1 | Item |  | Included | [10 empty] | 0
0
| Underwater lights | [15 empty] | 0
0
N | X-L11 _ LED Neon Flex, SMD 5050, 72 LEDs/m, 12W/m, 3000K, DC24V, IP68 Including: - Aluminium Profiles with self-lock mechanism, IP68 Front connectors and End caps - Driver, 150W, 24V, DALI Dimming, IP67, - Stainless steel deck box |  | 28 | m |  | X-L11 is at high level and excluded from our scope | [10 empty] | 0
| X-L7 (as per LT902-LA-L02-SL-0100-00-[D]) (as per VE comparison table & data sheet) | Global Light | 28 | m | 815 | 22820 | 662.7975 | 18558.3304 | [7 empty] | 28 | 18558.3304 | 0% |  | 0 | 89.29% | 25 | 16569.9378 | 89.29% | 25 | 16569.9378 |  |  |  |  | 0 | 0
0
| Water Tanks | [15 empty] | 0
0
| GRP Panel Balancing Tank, 12 m3 (4.0x1.5x2.0m) Non-insulated | Al Bassam - AquaSystem | 1 | Item | 26250 | 26250 | 21347.7727 | 21347.7727 | [7 empty] | 1 | 21347.7727 | 95% | 0.95 | 20280.384 | 0% | 0 | 0 | 95% | 0.95 | 20280.384 |  |  |  | 0% | 0 | 0 |  |  |  | - | WME-SW-WR-L02-00023_00 | 0.95
| To Collection Dhs. |  |  |  |  | 176150 |  | 143253.7202 |  |  | 0 |  |  | 0 |  |  | 78193.8416 |  |  | 52759.4953 |  |  | 16569.9378 |  |  | 69329.4332 |  |  | 65059.8786 |  |  | 0 |  |  | 65059.8786
WATER FEATURES (CONT'D)
LEVEL 04
Filtration System
B | Laminated fiberglass Bobbin wound sand filter, 3.0 m3/h, Ø350mm Ø450mm, complete with sand media and manual multiport valve, 1 duty | Aqua, Italy | 1 | Nos | 1130 | 1130 | 918.9708 | 918.9708 | [7 empty] | 1 | 918.9708 | 95% | 0.95 | 873.0222 | 0% | 0 | 0 | 95% | 0.95 | 873.0222 |  |  |  | 0% | 0 | 0 |  |  |  | MU-450N-VS | WME-SW-WR-L04-00028_00 | 0.95
0
C | Plastic self-priming pump, 3.0 m3/h @ 14m head, 3/4HP, 1 duty + 1 standby | Aqua, Italy | 2 | Nos | 1570 | 3140 | 1276.8001 | 2553.6002 | [7 empty] | 2 | 2553.6002 | 95% | 1.9 | 2425.9202 | 0% | 0 | 0 | 95% | 1.9 | 2425.9202 |  |  |  | 0% | 0 | 0 |  |  |  | Eurowsim 75M/A | WME-SW-WR-L04-00028_00 | 0.95
0
| Water Treatment System | [15 empty] | 0
0
D | Automatic pH/RX dosing controller |  | 1 | Nos |  | 0 | [10 empty] | 0
0
E | Manual analog dosing pumps - pH (10L/h - 5 bar) |  | 1 | Nos |  | 0 | [10 empty] | 0
0
F | Manual analog dosing pumps - RX (10L/h - 5 bar) |  | 1 | Nos |  | 0 | [10 empty] | 0
0
| Pre-assembled panel - Twin Dosing System - 10L/h @ 4 bars (pH & Rx) | Aqua, Italy | 1 | Nos | 6030 | 6030 | 4903.8884 | 4903.8884 | [7 empty] | 1 | 4903.8884 | 95% | 0.95 | 4658.6939 | 0% | 0 | 0 | 95% | 0.95 | 4658.6939 |  |  |  | 0% | 0 | 0 |  |  |  | ADPS101 | WME-SW-WR-L04-00028_00 | 0.95
0
G | Polyethylene dosing tanks, 125L 100L | Aqua, Italy | 2 | Nos | 530 | 1060 | 431.0217 | 862.0434 | [7 empty] | 2 | 862.0434 | 95% | 1.9 | 818.9412 | 0% | 0 | 0 | 95% | 1.9 | 818.9412 |  |  |  | 0% | 0 | 0 |  |  |  | ADTANK010 | WME-SW-WR-L04-00028_00 | 0.95
0
H | Manual stirrers | Aqua, Italy | 2 | Nos | 410 | 820 | 333.4319 | 666.8638 | [7 empty] | 2 | 666.8638 | 95% | 1.9 | 633.5206 | 0% | 0 | 0 | 95% | 1.9 | 633.5206 |  |  |  | 0% | 0 | 0 |  |  |  | ADAGMP06 | WME-SW-WR-L04-00028_00 | 0.95
0
| Fittings | [15 empty] | 0
0
J | Stainless steel main drain, 200x200mm | Aqua, Italy | 2 | Nos | 800 | 1600 | 650.5988 | 1301.1976 | [7 empty] | 2 | 1301.1976 | 95% | 1.9 | 1236.1377 | 0% | 0 | 0 | 95% | 1.9 | 1236.1377 |  |  |  |  | 0 | 0 |  |  |  | F-155 | WME-SW-WR-L4-00068_00_B | 0.95
0
| Stainless steel main drain, Ø300mm | Astral, Spain | 1 | Nos | 350 | 350 | 284.637 | 284.637 | [7 empty] | 1 | 284.637 | 95% | 0.95 | 270.4051 | 0% | 0 | 0 | 95% | 0.95 | 270.4051 |  |  |  |  | 0 | 0 |  |  |  |  | WME-SW-WR-L4-00068_00_B | 0.95
0
K | Provision for drain without fittings - Ø20mm |  | 3 | Nos | 180 | 540 | 146.3847 | 439.1542 | [7 empty] | 3 | 439.1542 | 95% | 2.85 | 417.1965 | 0% | 0 | 0 | 95% | 2.85 | 417.1965 |  |  |  |  | 0 | 0 |  |  |  | - | WME-SW-WR-L04-00028_00 | 0.95
0
Q | Provision for inlet without fittings - Ø20mm |  | 12 | Nos | 180 | 2160 | 146.3847 | 1756.6167 | [7 empty] | 12 | 1756.6167 | 95% | 11.4 | 1668.7859 | 0% | 0 | 0 | 95% | 11.4 | 1668.7859 |  |  |  |  | 0 | 0 |  |  |  | - | WME-SW-WR-L04-00028_00 | 0.95
0
P | Stainless steel floor inlet | Aqua, Italy | 4 | Nos | 710 | 2840 | 577.4064 | 2309.6257 | [7 empty] | 4 | 2309.6257 | 95% | 3.8 | 2194.1444 | 0% | 0 | 0 | 95% | 3.8 | 2194.1444 |  |  |  |  | 0 | 0 |  |  |  | F-230 | WME-SW-WR-L4-00068_00_B | 0.95
0
L | Stainless steel vacuum point | Aqua, Italy | 2 | Nos | 300 | 600 | 243.9745 | 487.9491 | [7 empty] | 2 | 487.9491 | 95% | 1.9 | 463.5516 | 0% | 0 | 0 | 95% | 1.9 | 463.5516 |  |  |  | 0% | 0 | 0 |  |  |  | F-240/A | WME-SW-WR-L4-00068_00_B | 0.95
0
M | Stainless steel overflow fittings | AtecPool, Spain | 6 | Nos | 440 | 2640 | 357.8293 | 2146.976 | [7 empty] | 6 | 2146.976 | 95% | 5.7 | 2039.6272 | 0% | 0 | 0 | 95% | 5.7 | 2039.6272 |  |  |  |  | 0 | 0 |  |  |  | 03100282-1 | WME-SW-WR-L4-00068_00_B | 0.95
0
R | Provision for overflow drain without fittings - Ø20mm |  | 17 | Nos | 180 | 3060 | 146.3847 | 2488.5404 | [7 empty] | 17 | 2488.5404 | 95% | 16.15 | 2364.1133 | 0% | 0 | 0 | 95% | 16.15 | 2364.1133 |  |  |  |  | 0 | 0 |  |  |  | - | WME-SW-WR-L04-00028_00 | 0.95
0
| Cascade System | [15 empty] | 0
0
N | Overflow effect cast iron pump with cast iron impeller, 5.0 m3/h 6.6 m3/h @ 20m head, 10HP, 1 duty (as per WME-SW-SC-L4-0050) | Aqua, Italy | 1 | Nos | 8790 | 8790 | 7148.4542 | 7148.4542 | [7 empty] | 1 | 7148.4542 | 95% | 0.95 | 6791.0315 | 0% | 0 | 0 | 95% | 0.95 | 6791.0315 |  |  |  |  | 0 | 0 |  |  |  | Euroswim 200M/A | WME-SW-WR-L04-00028_00 | 0.95
| To Collection Dhs. |  |  |  |  | 34760 |  | 28268.5173 |  |  | 0 |  |  | 0 |  |  | 28268.5173 |  |  | 26855.0914 |  |  | 0 |  |  | 26855.0914 |  |  | 0 |  |  | 0 |  |  | 0
WATER FEATURES (CONT'D)
LEVEL 04 (CONT'D)
Maintenance Kit
A | Vacuum head | Aqua, Italy | 1 | Nos | 830 | 830 | 674.9962 | 674.9962 | [8 empty] | 674.9962 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  |  | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
B | Telescopic handle |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
C | Vacuum hose |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
D | Pool brush |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
E | Leaf skimmer |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
F | Leaf rake |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
G | Algae brush |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
H | Hose fitting |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
J | Test kit |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
0
| Control Panel Board | [15 empty] | 0
0
K | Control Panel Board | Al Fanar/ Scheinder | 1 | Nos | 17500 | 17500 | 14231.8484 | 14231.8484 | [7 empty] | 1 | 14231.8484 | 95% | 0.95 | 13520.256 | 0% | 0 | 0 | 95% | 0.95 | 13520.256 |  |  |  |  | 0 | 0 |  |  |  |  | WME-SW-WR-L4-00063_00_B | 0.95
0
L | MEP Works including piping, cabling, containment, etc. | Cosmoplast/Atlas/Cepex/Ducab | 1 | Nos | 90000 | 90000 | 73192.3634 | 73192.3634 | [7 empty] | 0.2 | 14638.4727 | 75% | 0.15 | 10978.8545 | 0% | 0 | 0 | 75% | 0.15 | 10978.8545 | 80% | 0.8 | 58553.8908 |  | 0 |  | 80% | 0.8 | 58553.8908 |  | WME-SW-WR-L4-00002 WME-SW-WR-L4-00010_00_D | 0.75
0
M | Testing and Commissioning |  | 1 | Item |  | Included | [10 empty] | 0
0
| Underwater lights | [15 empty] | 0
0
N | X-L4 _ LED Neon Flex, SMD 5050, 72 LEDs/m, 12W/m, 3000K, DC24V, IP68 Including: - Aluminium Profiles with self-lock mechanism, IP68 Front connectors and End caps - Driver, 150W, 24V, DALI Dimming, IP67, - Stainless steel deck box (as per VE comparison table & data sheet) | Global Light | 41 | m | 815 | 33415 | 662.7975 | 27174.6981 | [7 empty] | 41 | 27174.6981 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  |  | 0 | 0
0
P | X-L7 _ LED Neon Flex, SMD 5050, 72 LEDs/m, 12W/m, 4000K, DC24V, IP68 Including: - Aluminium Profiles with self-lock mechanism, IP68 Front connectors and End caps - Driver, 150W, 24V, DALI Dimming, IP67, - Stainless steel deck box (as per VE comparison table & data sheet) | Global Light | 36 | m | 815 | 29340 | 662.7975 | 23860.7105 | [7 empty] | 36 | 23860.7105 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  |  | 0 | 0
0
| Water Tanks | [15 empty] | 0
| GRP Panel Balancing Tank, 1.5 m3 (1.0x1.0x1.5m) Non-insulated | Al Bassam - AquaSystem | 1 | Item | 9800 | 9800 | 7969.8351 | 7969.8351 | [7 empty] | 1 | 7969.8351 | 95% | 0.95 | 7571.3434 | 0% | 0 | 0 | 95% | 0.95 | 7571.3434 |  |  |  |  | 0 | 0 |  |  |  | - | WME-SW-WR-L04-00028_00 | 0.95
| To Collection Dhs. |  |  |  |  | 180885 |  | 147104.4518 |  |  | 0 |  |  | 0 |  |  | 88550.561 |  |  | 32070.4539 |  |  | 0 |  |  | 32070.4539 |  |  | 58553.8908 |  |  | 0 |  |  | 58553.8908
WATER FEATURES (CONT'D)
LEVEL 23 A, B, & C
Filtration System
B | Laminated fiberglass Bobbin wound sand filter, 18.75 m3/h, Ø750mm, 13.93 m3/h, Ø650mm, complete with sand media and manual multiport valve, 1 duty (as per WME-SW-SC-L23-0062) | Aqua, Italy | 1 | Nos | 1680 | 1680 | 1366.2575 | 1366.2575 | [7 empty] | 1 | 1366.2575 | 95% | 0.95 | 1297.9446 | 0% | 0 | 0 | 95% | 0.95 | 1297.9446 |  |  |  | 0% | 0 | 0 |  |  |  | MU-650N-VS | WME-SW-WR-L23-00070_00_B | 0.95
0
C | Plastic self-priming pump, 18.75 m3/h @ 14m head, 2HP, 13.93 m3/h @ 15m head, 1.5HP, 1 duty + 1 standby (as per WME-SW-SC-L23-0062) | Aqua, Italy | 2 | Nos | 1990 | 3980 | 1618.3645 | 3236.729 | [7 empty] | 2 | 3236.729 | 95% | 1.9 | 3074.8925 | 0% | 0 | 0 | 95% | 1.9 | 3074.8925 |  |  |  | 0% | 0 | 0 |  |  |  | Euroswim 200M/A | WME-SW-WR-L23-00070_00_B | 0.95
0
| Water Treatment System | [15 empty] | 0
0
D | Automatic pH/RX dosing controller |  | 1 | Nos |  | 0 | [10 empty] | 0
0
E | Manual analog dosing pumps - pH (10L/h - 5 bar) |  | 1 | Nos |  | 0 | [10 empty] | 0
0
F | Manual analog dosing pumps - RX (10L/h - 5 bar) |  | 1 | Nos |  | 0 | [10 empty] | 0
0
| Pre-assembled panel - Twin Dosing System - 10L/h @ 4 bars (pH & Rx) | Aqua, Italy | 1 | Nos | 6030 | 6030 | 4903.8884 | 4903.8884 | [7 empty] | 1 | 4903.8884 | 95% | 0.95 | 4658.6939 | 0% | 0 | 0 | 95% | 0.95 | 4658.6939 |  |  |  |  | 0 | 0 |  |  |  | ADPS101 | WME-SW-WR-L23-00070_00_B | 0.95
0
G | Polyethylene dosing tanks, 125L 100L | Aqua, Italy | 2 | Nos | 530 | 1060 | 431.0217 | 862.0434 | [7 empty] | 2 | 862.0434 | 95% | 1.9 | 818.9412 | 0% | 0 | 0 | 95% | 1.9 | 818.9412 |  |  |  | 0% | 0 | 0 |  |  |  | ADTANK020 | WME-SW-WR-L23-00070_00_B | 0.95
0
H | Manual stirrers | Aqua, Italy | 2 | Nos | 410 | 820 | 333.4319 | 666.8638 | [7 empty] | 2 | 666.8638 | 95% | 1.9 | 633.5206 | 0% | 0 | 0 | 95% | 1.9 | 633.5206 |  |  |  | 0% | 0 | 0 |  |  |  | ADAGMP07 | WME-SW-WR-L23-00070_00_B | 0.95
0
| Fittings | [15 empty] | 0
0
J | Stainless steel main drain, 200x200mm | Aqua, Italy | 6 | Nos | 800 | 4800 | 650.5988 | 3903.5927 | [7 empty] | 6 | 3903.5927 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  |  | 0 | 0 |  |  |  | F-155
0
K | Stainless steel main drain | AtecPool, Spain | 4 | Nos | 440 | 1760 | 357.8293 | 1431.3173 | [7 empty] | 4 | 1431.3173 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  |  | 0 | 0
0
| Stainless steel floor inlet | Aqua, Italy | 21 | Nos | 710 | 14910 | 577.4064 | 12125.5349 | [7 empty] | 21 | 12125.5349 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  |  | 0 | 0 |  |  |  | F-230
0
L | Stainless steel wall inlet | Aqua, Italy | 4 | Nos | 280 | 1120 | 227.7096 | 910.8383 | [7 empty] | 4 | 910.8383 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  | 0% | 0 | 0 |  |  |  | F-219/A
0
M | Stainless steel vacuum point | Aqua, Italy | 4 | Nos | 300 | 1200 | 243.9745 | 975.8982 | [7 empty] | 4 | 975.8982 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  | 0% | 0 | 0 |  |  |  | F-240/A
0
N | Stainless steel overflow fittings | AtecPool, Spain | 32 | Nos | 440 | 14080 | 357.8293 | 11450.5386 | [7 empty] | 32 | 11450.5386 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  |  | 0 | 0 |  |  |  | 03100282-1
0
| Overflow Effect System | [15 empty] | 0
0
P | Plastic overflow effect pump, 31.68 m3/h @ 14m head, 4.5HP, 16.2 m3/h @ 15m head, 2HP, 1 duty (WF23A) (as per WME-SW-SC-L23-0062) | Aqua, Italy | 1 | Nos | 1990 | 1990 | 1618.3645 | 1618.3645 | [7 empty] | 1 | 1618.3645 | 95% | 0.95 | 1537.4463 | 0% | 0 | 0 | 95% | 0.95 | 1537.4463 |  |  |  | 0% | 0 | 0 |  |  |  | Euroswim 200M/A | WME-SW-WR-L23-00070_00_B | 0.95
0
Q | Plastic overflow effect pump, 50.3 m3/h @ 14m head, 5.5HP, 16.2 m3/h @ 15m head, 2HP, 1 duty (WF23B) (as per WME-SW-SC-L23-0062) | Aqua, Italy | 1 | Nos | 1990 | 1990 | 1618.3645 | 1618.3645 | [7 empty] | 1 | 1618.3645 | 95% | 0.95 | 1537.4463 | 0% | 0 | 0 | 95% | 0.95 | 1537.4463 |  |  |  | 0% | 0 | 0 |  |  |  | Euroswim 200M/A | WME-SW-WR-L23-00070_00_B | 0.95
| To Collection Dhs. |  |  |  |  | 55420 |  | 45070.2309 |  |  | 0 |  |  | 0 |  |  | 45070.2309 |  |  | 13558.8853 |  |  | 0 |  |  | 13558.8853 |  |  | 0 |  |  | 0 |  |  | 0
WATER FEATURES (CONT'D)
LEVEL 23 A, B, & C (CONT'D)
Maintenance Kit
A | Vacuum head | Aqua, Italy | 1 | Nos | 830 | 830 | 674.9962 | 674.9962 | [8 empty] | 674.9962 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  |  | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
B | Telescopic handle |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
C | Vacuum hose |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
D | Pool brush |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
E | Leaf skimmer |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
F | Leaf rake |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
G | Algae brush |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
H | Hose fitting |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
[31 empty] | 0 | 0 |  |  | 0
J | Test kit |  | 1 | Nos | [26 empty] | 0 | 0 |  |  | 0
0
| Control Panel Board | [15 empty] | 0
0
K | Control Panel Board | Al Fanar/ Scheinder | 1 | Nos | 26250 | 26250 | 21347.7727 | 21347.7727 | [7 empty] | 1 | 21347.7727 | 95% | 0.95 | 20280.384 | 0% | 0 | 0 | 95% | 0.95 | 20280.384 |  |  |  |  | 0 | 0 |  |  |  |  | WME-SW-WR-L23-00071_00_B | 0.95
0
L | MEP Works including piping, cabling, containment, etc. | Cosmoplast/Atlas/Cepex/Ducab | 1 | Nos | 90000 | 90000 | 73192.3634 | 73192.3634 | [7 empty] | 0.4 | 29276.9454 | 95% | 0.38 | 27813.0981 | 0% | 0 | 0 | 95% | 0.38 | 27813.0981 | 60% | 0.6 | 43915.4181 |  | 0 | 0 | 60% | 0.6 | 43915.4181 |  | WME-SW-WR-L23-00020 WME-SW-WR-L23-00031 WME-SW-WR-L23-00038 WME-SW-WR-L23-00070_00_B WME-SW-WR-L23-00071_00_B | 0.95
0
M | Testing and Commissioning |  | 1 | Item |  | Included | [10 empty] | 0
0
| Underwater lights | [15 empty] | 0
0
N | X-L12 _ LED Neon Flex, SMD 5050, 72 LEDs/m, 12W/m, 4000K, DC24V, IP68 Including: - Aluminium Profiles with self-lock mechanism, IP68 Front connectors and End caps - Driver, 150W, 24V, DALI Dimming, IP67, - Stainless steel deck box (as per VE comparison table & data sheet) | Global Light | 12 | m | 815 | 9780 | 662.7975 | 7953.5702 | [7 empty] | 12 | 7953.5702 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  |  | 0 | 0
0
0
| Water Tanks | [15 empty] | 0
0
| GRP Panel Balancing Tank, 6.0 m3 (4.0x1.5x1.0m) Non-insulated | Al Bassam - AquaSystem | 1 | Item | 19110 | 19110 | 15541.1785 | 15541.1785 | [7 empty] | 1 | 15541.1785 |  |  |  | 0% | 0 | 0 | 0% |  | 0 |  |  |  | 0% | 0 | 0 |  |  |  | -
| To Collection Dhs. |  |  |  |  | 145970 |  | 118709.881 |  |  | 0 |  |  | 0 |  |  | 74794.463 |  |  | 48093.4821 |  |  | 0 |  |  | 48093.4821 |  |  | 43915.4181 |  |  | 0 |  |  | 43915.4181
WATER FEATURES (CONT'D)
ADDITIONAL ITEMS
A | Pipe acoustic insulations for gravity lines and above critical areas only
| Water Feature @ Level 2 |  | 1 | Nos | 5000 | 5000 | 4066.2424 | 4066.2424 | [7 empty] | 1 | 4066.2424 | 95% | 0.95 | 3862.9303 | 0% | 0 | 0 | 95% | 0.95 | 3862.9303 |  |  |  |  | 0 | 0 |  |  |  |  | WME-SW-WR-L02-00023_00 | 0.95
0
| Water Feature @ Level 4 |  | 1 | Nos | 4500 | 4500 | 3659.6182 | 3659.6182 | [7 empty] | 1 | 3659.6182 | 95% | 0.95 | 3476.6373 | 0% | 0 | 0 | 95% | 0.95 | 3476.6373 |  |  |  |  | 0 | 0 |  |  |  |  | WME-SW-WR-L04-00028_00 | 0.95
0
| Water Features @ Level 23 |  | 1 | Nos | 13500 | 13500 | 10978.8545 | 10978.8545 | [7 empty] | 1 | 10978.8545 | 95% | 0.95 | 10429.9118 | 0% | 0 | 0 | 95% | 0.95 | 10429.9118 |  |  |  |  | 0 | 0 |  |  |  |  | WME-SW-WR-L23-00070_00_B | 0.95
| To Collection Dhs. |  |  |  |  | 23000 |  | 18704.7151 |  |  | 0 |  |  | 0 |  |  | 18704.7151 |  |  | 17769.4793 |  |  | 0 |  |  | 17769.4793 |  |  | 0 |  |  | 0 |  |  | 0
WATER FEATURES (CONT'D)
COLLECTION
| Page 2 / 1 |  |  |  |  | 84640 |  | 68833.3516 |  |  | 0 |  |  | 0 |  |  | 68833.3516 |  |  | 65391.684 |  |  | 0 |  |  | 65391.684 |  |  | 0 |  |  | 0 |  |  | 0
| Page 2 / 2 |  |  |  |  | 176150 |  | 143253.7202 |  |  | 0 |  |  | 0 |  |  | 78193.8416 |  |  | 52759.4953 |  |  | 16569.9378 |  |  | 69329.4332 |  |  | 65059.8786 |  |  | 0 |  |  | 65059.8786
| Page 2 / 3 |  |  |  |  | 34760 |  | 28268.5173 |  |  | 0 |  |  | 0 |  |  | 28268.5173 |  |  | 26855.0914 |  |  | 0 |  |  | 26855.0914 |  |  | 0 |  |  | 0 |  |  | 0
| Page 2 / 4 |  |  |  |  | 180885 |  | 147104.4518 |  |  | 0 |  |  | 0 |  |  | 88550.561 |  |  | 32070.4539 |  |  | 0 |  |  | 32070.4539 |  |  | 58553.8908 |  |  | 0 |  |  | 58553.8908
| Page 2 / 5 |  |  |  |  | 55420 |  | 45070.2309 |  |  | 0 |  |  | 0 |  |  | 45070.2309 |  |  | 13558.8853 |  |  | 0 |  |  | 13558.8853 |  |  | 0 |  |  | 0 |  |  | 0
| Page 2 / 6 |  |  |  |  | 145970 |  | 118709.881 |  |  | 0 |  |  | 0 |  |  | 74794.463 |  |  | 48093.4821 |  |  | 0 |  |  | 48093.4821 |  |  | 43915.4181 |  |  | 0 |  |  | 43915.4181
| Page 2 / 7 |  |  |  |  | 23000 |  | 18704.7151 |  |  | 0 |  |  | 0 |  |  | 18704.7151 |  |  | 17769.4793 |  |  | 0 |  |  | 17769.4793 |  |  | 0 |  |  | 0 |  |  | 0
| To Summary |  |  |  |  | 700825 |  | 569944.8679 | 0% |  | 0 | 0% |  | 0 | 70.61% |  | 402415.6805 | 45% |  | 256498.5715 | 2.907% |  | 16569.9378 | 47.91% |  | 273068.5093 | 29.39% |  | 167529.1874 | 0% |  | 0 | 29.39% |  | 167529.1874 |  |  |  | 569944.8679
FOR CHECKING PURPOSES ONLY

## ACRYLIC
PLOT-18 | [5 empty] | WM Ref. No.: D20/054-12/C
BILL OF QUANTITIES | [5 empty] | Date: 06-05-2021 | [23 empty] | Discount Rate
BILL :- ACRYLIC WALL PANELS | [29 empty] | 81.32%
[15 empty] | WM-Khansaheb BOQ |  |  | WM-Khansaheb Progress Claim - February 2023 | [8 empty] | ITEM CODE | WIR |  | 18.68%
Item | Description | Make | Qty. | Unit | Rate | Amount | Rate | Amount after Discount | Last Month |  |  | This Month |  |  | TOTAL |  |  | Last Month - KCE PC 12 (Jan, 2023) |  |  | This Month |  |  | Total To Date
[6 empty] | (Dhs.) | after Discount | (Dhs.) | % | Qty | Value | % | Qty | Value | % | Qty | Value | % | Qty | Value | % | Qty | Value | % | Qty | Value
SWIMMING POOL ACRYLIC WALLS
LEVEL 10
Acrylic Pool Walls
A | Acrylic Pool Walls Panel 1-A - 4240(L)x1350(Viewing Height)x100mm(t) _ 0 join Panel 1-B - 11240(L)x1350(Viewing Height)x100mm(t) _ 1 join | Exclusive Acrylic | 1 | Item | 383000 | 383000 | 311474.1689 | 311474.1689 | [7 empty] | 1 | 311474.1689 | 100% | 1 | 311474.1689 | 0% | 0 | 0 | 100% | 1 | 311474.1689 |  | WME-SW-WR-L10-00069_01 | 1
LEVEL 26
Acrylic Pool Walls
B | Acrylic Pool Walls Panel 2-A - 3300(L)x1250(Viewing Height)x90mm(t) _ 0 join Panel 2-B - 9290(L)x1250(Viewing Height)x90mm(t) _ 1 join | Exclusive Acrylic | 1 | Item | 282380 | 282380 | 229645.1066 | 229645.1066 | [7 empty] | 1 | 229645.1066 | 100% | 1 | 229645.1066 | 0% | 0 | 0 | 100% | 1 | 229645.1066 |  | WME-SW-WR-L26-00042 | 1
| To Collection Dhs. |  |  |  |  | 665380 |  | 541119.2754 |  |  | 0 |  |  | 0 |  |  | 541119.2754 |  |  | 541119.2754 |  |  | 0 |  |  | 541119.2754
SWIMMING POOL ACRYLIC WALLS (CONT'D)
COLLECTION
| Page 3 / 1 |  |  |  |  | 665380 |  | 541119.2754 |  |  | 0 |  |  | 0 |  |  | 541119.2754 |  |  | 541119.2754 |  |  | 0 |  |  | 541119.2754
| To Summary |  |  |  |  | 665380 |  | 541119.2754 |  |  | 0 |  |  | 0 |  |  | 541119.2754 | 100% |  | 541119.2754 | 0% |  | 0 | 100% |  | 541119.2754 |  |  |  | 541119.2754
[20 empty] | 195198.3406 |  |  | 34446.766 |  |  | 229645.1066
FOR CHECKING PURPOSES ONLY

## SWP MOS
PLOT-18 | [5 empty] | WM Ref. No.: D20/054-12/C
BILL OF QUANTITIES | [5 empty] | Date: 06-05-2021 | [22 empty] | Discount Rate
BILL :- SWIMMING POOLS | [28 empty] | 81.32%
[15 empty] | WM MOS Claim |  |  | WM-Khansaheb MOS Claim - February 2023 |  |  |  | OMNIYAT RECOMMENDATION - as per 17001DH/SCA/40-01-33-WM Ver 2 dated 11 April 2022 |  |  |  | ITEM CODE | MIR |  | 18.68%
Item | Description | Make | Qty. | Unit | Rate | Amount | Rate | Amount after Discount | Last Month |  |  | This Month |  |  | TOTAL |  |  | Avaiable Qty | BOQ rate less OHP (85%) (A) | Allocation for Material invoice value (75% from A) | MOS Value | Avaiable Qty | BOQ rate less OHP (85%) (A) | Allocation for Material invoice value (75% from A) | MOS Value
[6 empty] | (Dhs.) | after Discount | (Dhs.) | % | Qty | Value | % | Qty | Value | % | Qty | Value |  | 85% | 75% |  |  | 85% | 75%
SWIMMING POOLS
LEVEL 04 RESIDENTIAL
Filtration System
A | Laminated Bobbin wound sand filter, simultaneous projection of resin and fibre glass, 41.5 m3/h, Ø1050mm Ø1200mm, complete with stand media and manual multiport valve, 1 duty + 1 standby | Aqua, Italy | 2 | Nos | 9600 | 19200 | 7807.1854 | 15614.3709 | [13 empty] | 0 | 6636.1076 | 4977.0807 | 0 | MU-1200N-VS | WME-SW-MR-ML-00015
B | Plastic centrifugal pump, 41.5 m3/h @ 14m head, 4.5HP, 1 duty + 1 standby | Aqua, Italy | 2 | Nos | 4930 | 9860 | 4009.315 | 8018.63 | [13 empty] | 0 | 3407.9178 | 2555.9383 | 0 | KPA-450 | WME-SW-MR-ML-00015
Water Treatment System
C | Automatic pH/RX dosing controller |  | 1 | Nos |  | 0 | 0 | 0
D | Manual analog dosing pumps - pH (20L/h-5 bar) |  | 1 | Nos |  | 0 | 0 | 0
E | Manual analog dosing pumps - RX (20L/h-5 bar) |  | 1 | Nos |  | 0 | 0 | 0
| Pre-assembled panel - Twin Dosing System - 10L/h @ 4 bars (pH & Rx) | Aqua, Italy | 2 | Nos | 6030 | 12060 | 4903.8884 | 9807.7767 | [13 empty] | 0 | 4168.3051 | 3126.2288 | 0 | ADPS101 | WME-SW-MR-ML-00005
F | Polyethylene dosing tanks, 250L 200L | Aqua, Italy | 4 | Nos | 1030 | 4120 | 837.6459 | 3350.5837 | [13 empty] | 0 | 711.999 | 533.9993 | 0 | ADTANK010 | WME-SW-MR-ML-00005
G | Manual stirrers | Aqua, Italy | 4 | Nos | 420 | 1680 | 341.5644 | 1366.2575 | [13 empty] | 0 | 290.3297 | 217.7473 | 0 | ADAGMP06 | WME-SW-MR-ML-00005
H | UV Sterilizer, Flow: 65 m³/h at 3 bar pressure | AtecPool, Spain | 1 | Nos | 38890 | 38890 | 31627.2335 | 31627.2335 | [13 empty] | 0 | 26883.1485 | 20162.3614 | 0 | UV-5205 | WME-SW-MR-ML-00017
Fittings
J | Stainless steel main drain, 200x200mm | Aqua, Italy | 2 | Nos | 800 | 1600 | 650.5988 | 1301.1976 | [13 empty] | 0 | 553.009 | 414.7567 | 0 | F-155 | WME-SW-MR-ML-00015
K | Stainless steel floor inlet | Aqua, Italy | 22 | Nos | 710 | 15620 | 577.4064 | 12702.9413 | [13 empty] | 0 | 490.7955 | 368.0966 | 0 | F-230 | WME-SW-MR-ML-00019
K | Stainless steel wall inlet | Aqua, Italy | 20 | Nos | 280 | 5600 | 227.7096 | 4554.1915 | [13 empty] | 0 | 193.5531 | 145.1649 | 0 | F-219/A | WME-SW-MR-ML-00008
L | Stainless steel vacuum point | Aqua, Italy | 4 | Nos | 300 | 1200 | 243.9745 | 975.8982 | [13 empty] | 0 | 207.3784 | 155.5338 | 0 | F-240/A | WME-SW-MR-ML-00008
M | Stainless steel overflow fittings | AtecPool, Spain | 42 | Nos | 440 | 18480 | 357.8293 | 15028.832 | [13 empty] | 0 | 304.1549 | 228.1162 | 0 | 03100282-1 | WME-SW-MR-ML-00013
M | Provision for overflow drain without fittings - Ø160mm |  | 8 | Nos | 880 | 7040 | 715.6587 | 5725.2693 | [9 empty] | 0 | 608.3099 | 456.2324 | 0
Overflow Effect System
N | Overflow effect cast iron pump with cast iron impeller plastic pump, 70.1 m3/h @ 15m head, 7.5HP, 1 duty | Aqua, Italy | 1 | Nos | 7350 | 7350 | 5977.3763 | 5977.3763 | [9 empty] | 0 | 5080.7699 | 3810.5774 | 0 |  |  |  |  | KPA 750 | WME-SW-MIR-L4-00025
| To Collection Dhs. |  |  |  |  | 142700 |  | 116050.5585
SWIMMING POOLS (CONT'D)
LEVEL 04 RESIDENTIAL (CONT'D)
Maintenance Kit
A | Vacuum head | Aqua, Italy | 1 | Nos | 830 | 830 | 674.9962 | 674.9962 | [9 empty] | 0 | 573.7468 | 430.3101 | 0
B | Telescopic handle |  | 1 | Nos
C | Vacuum hose |  | 1 | Nos
D | Pool brush |  | 1 | Nos
E | Leaf skimmer |  | 1 | Nos
F | Leaf rake |  | 1 | Nos
G | Algae brush |  | 1 | Nos
H | Hose fitting |  | 1 | Nos
J | Test kit |  | 1 | Nos
Control Panel Board
K | Control Panel Board | Al Fanar/ Scheinder | 1 | Nos | 31500 | 31500 | 25617.3272 | 25617.3272 | [9 empty] | 0 | 21774.7281 | 16331.0461 | 0 | [5 empty] | WME-SW-MR-ML-00028
L | MEP Works including piping, cabling, containment, etc. | Cosmoplast/Atlas/Cepex/Ducab | 1 | Nos | 100000 | 100000 | 81324.8483 | 81324.8483 | [18 empty] | WME-SW-MR-ML-00009
M | Testing and Commissioning |  | 1 | Item |  | Included
| To Collection Dhs. |  |  |  |  | 132330 |  | 107617.1717
SWIMMING POOLS (CONT'D)
LEVEL 04 RESIDENTIAL (CONT'D)
Underwater lights
A | X-W11 (as per VE comparison table & data sheet) | Luce & Light | 8 | Nos | 4010 | 32080 | 3261.1264 | 26089.0113 | [9 empty] | 0 | 2771.9575 | 2078.9681 | 0 | 0 | 2771.9575 | 2078.9681 | 0 | X-W11 | WME-SW-MIR-ML-00014 WME-SW-MR-ML-00027_00 | cost of SS Junction Box (25%) |  | 8 nos. lights
B | X-W12 (as per VE comparison table & data sheet) | Luce & Light | 6 | Nos | 3990 | 23940 | 3244.8614 | 19469.1687 | [9 empty] | 0 | 2758.1322 | 2068.5992 | 0 | 0 | 2758.1322 | 2068.5992 | 0 | X-W17 (CW300009MI + WC5006) | DN-21-1613 WME-SW-MR-ML-00027_00 | cost of SS Junction Box (25%) |  | 4 nos. lights
C | X-L12 (as per VE comparison table & data sheet) | Global Lights | 15 | m | 815 | 12225 | 662.7975 | 9941.9627 | [9 empty] | 0 | 563.3779 | 422.5334 | 0 | 3.75 | 563.3779 | 422.5334 | 1584.5003 |  | DN-21-1613 | cost of SS Junction Box (25%)
Heating/Cooling System
D | Air-to-water Heat/Cool Pump Heating Capacity: 160 kW Cooling Capacity: 120 kW | Astral, Spain | 2 | Nos | 87690 | 175380 | 71313.7594 | 142627.5189 | [13 empty] | 0 | 60616.6955 | 45462.5216 | 0 | AHP400-SU R4 | WME-SW-MR-ML-00012
| Plastic booster pump, 40 m3/h @ 20m head, 7.5HP, 2 duty | Aqua, Italy | 2 | Nos | 7350 | 14700 | 5977.3763 | 11954.7527 | [9 empty] | 0 | 5080.7699 | 3810.5774 | 0 |  |  |  |  | KPA 750 | WME-SW-MIR-L4-00025
Water Tanks
| GRP Panel Balancing Tank, 18 m3 (4.0x3.0x1.5m) Non-insulated | Al Bassam - AquaSystem | 1 | Nos | 37980 | 37980 | 30887.1774 | 30887.1774 | [13 empty] | 0 | 26254.1008 | 19690.5756 | 0 | - | WME-SW-MR-ML-00007
| GRP Panel Backwash Tank, 1.5 m3 (1.0x1.0x1.5m) Non-insulated | Al Bassam - AquaSystem | 1 | Nos | 9800 | 9800 | 7969.8351 | 7969.8351 | [13 empty] | 0 | 6774.3599 | 5080.7699 | 0 | - | WME-SW-MR-ML-00007
Pool Surround
| Pool ladder, 4 steps | Aqua, Italy | 2 | Nos | 1590 | 3180 | 1293.0651 | 2586.1302 | [13 empty] | 2 | 1099.1053 | 824.329 | 1648.658 | L-106-316 | WME-SW-MR-ML-00005
| To Collection Dhs. |  |  |  |  | 309285 |  | 251525.557
SWIMMING POOLS (CONT'D)
LEVEL 10 PENTHOUSE POOL
Filtration System
B | Laminated fiberglass Bobbin wound sand filter, 13.15 m3/h, Ø650mm, complete with sand media and manual multiport valve, 1 duty | Aqua, Italy | 1 | Nos | 1680 | 1680 | 1366.2575 | 1366.2575 | [13 empty] | 1 | 1161.3188 | 870.9891 | 870.9891 | MU-650N-VS | WME-SW-MR-ML-00005
C | Plastic self-priming pump, 13.15 m3/h @ 15m head, 1.5HP, 1 duty + 1 standby | Aqua, Italy | 2 | Nos | 1810 | 3620 | 1471.9798 | 2943.9595 | [13 empty] | 2 | 1251.1828 | 938.3871 | 1876.7742 | Euroswim 150M/A | WME-SW-MR-ML-00008
Water Treatment System
D | Automatic pH/RX dosing controller |  | 1 | Nos |  | 0 | 0 | 0
E | Manual analog dosing pumps - pH (10L/h - 5 bar) |  | 1 | Nos |  | 0 | 0 | 0
F | Manual analog dosing pumps - RX (10L/h - 5 bar) |  | 1 | Nos |  | 0 | 0 | 0
| Pre-assembled panel - Twin Dosing System - 10L/h @ 4 bars (pH & Rx) | Aqua, Italy | 1 | Nos | 6030 | 6030 | 4903.8884 | 4903.8884 | [13 empty] | 1 | 4168.3051 | 3126.2288 | 3126.2288 | ADPS101 | WME-SW-MR-ML-00005
G | Polyethylene dosing tanks, 125L 100L | Aqua, Italy | 2 | Nos | 530 | 1060 | 431.0217 | 862.0434 | [13 empty] | 2 | 366.3684 | 274.7763 | 549.5527 | ADTANK010 | WME-SW-MR-ML-00005
H | Manual stirrers | Aqua, Italy | 2 | Nos | 410 | 820 | 333.4319 | 666.8638 | [13 empty] | 0 | 283.4171 | 212.5628 | 0 | ADAGMP06 | WME-SW-MR-ML-00005
Fittings
J | Stainless steel main drain, 200x200mm | Aqua, Italy | 2 | Nos | 800 | 1600 | 650.5988 | 1301.1976 | [13 empty] | 2 | 553.009 | 414.7567 | 829.5135 | F-155 | WME-SW-MR-ML-00015
K | Stainless steel floor inlet | Aqua, Italy | 6 | Nos | 710 | 4260 | 577.4064 | 3464.4385 | [13 empty] | 6 | 490.7955 | 368.0966 | 2208.5796 | F-230 | WME-SW-MR-ML-00019
L | Stainless steel vacuum point | Aqua, Italy | 1 | Nos | 300 | 300 | 243.9745 | 243.9745 | [13 empty] | 1 | 207.3784 | 155.5338 | 155.5338 | F-240/A | WME-SW-MR-ML-00008
M | ABS skimmer fittings with stainless steel faceplate | AtecPool, Spain | 2 | Nos | 820 | 1640 | 666.8638 | 1333.7275 | [13 empty] | 0 | 566.8342 | 425.1256 | 0 | 015901010 | WME-SW-MR-ML-00020
| To Collection Dhs. |  |  |  |  | 21010 |  | 17086.3506
SWIMMING POOLS (CONT'D)
LEVEL 10 PENTHOUSE POOL (CONT'D)
Maintenance Kit
A | Vacuum head | Aqua, Italy | 1 | Nos | 830 | 830 | 674.9962 | 674.9962 | [9 empty] | 0 | 573.7468 | 430.3101 | 0
B | Telescopic handle |  | 1 | Nos
C | Vacuum hose |  | 1 | Nos
D | Pool brush |  | 1 | Nos
E | Leaf skimmer |  | 1 | Nos
F | Leaf rake |  | 1 | Nos
G | Algae brush |  | 1 | Nos
H | Hose fitting |  | 1 | Nos
J | Test kit |  | 1 | Nos
Control Panel Board
K | Control Panel Board | Al Fanar/ Scheinder | 1 | Nos | 14000 | 14000 | 11385.4788 | 11385.4788 | [9 empty] | 1 | 9677.6569 | 7258.2427 | 7258.2427 | [5 empty] | WME-SW-MR-ML-00029
L | MEP Works including piping, cabling, containment, etc. | Cosmoplast/Atlas/Cepex/Ducab | 1 | Nos | 70000 | 70000 | 56927.3938 | 56927.3938
M | Testing and Commissioning |  | 1 | Item |  | Included
| To Collection Dhs. |  |  |  |  | 84830 |  | 68987.8688
SWIMMING POOLS (CONT'D)
LEVEL 10 PENTHOUSE POOL (CONT'D)
Underwater lights
A | X-W17 (as per LT902-LA-L10-SL-0110-01-[D]) (as per VE comparison table & data sheet) | Luce & Light | 9 | Nos | 4210 | 37890 | 3423.7761 | 30813.985 | [9 empty] | 0 | 2910.2097 | 2182.6573 | 0 | 0 | 2910.2097 | 2182.6573 | 0 | CW16009LI + WC5003 | DN-21-1613 WME-SW-MR-ML-00027_00 | cost of SS Junction Box (25%) |  | 9 nos. lights
Heating/Cooling System
B | Plate Heat Exchanger, Titanium, 65 kW heating capacity | Aqua, Italy | 1 | Nos | 10110 | 10110 | 8221.9422 | 8221.9422 | [9 empty] | 1 | 6988.6508 | 5241.4881 | 5241.4881 |  |  |  |  | Custom Made | WME-SW-MR-ML-00023_00
C | Plate Heat Exchanger, Titanium, 38 kW cooling capacity | Aqua, Italy | 1 | Nos | 11950 | 11950 | 9718.3194 | 9718.3194 | [9 empty] | 1 | 8260.5715 | 6195.4286 | 6195.4286 |  |  |  |  | Custom Made | WME-SW-MR-ML-00023_00
Pool Surround
| Pool ladder, 3 steps | Aqua, Italy | 1 | Nos | 1210 | 1210 | 984.0307 | 984.0307 | [13 empty] | 1 | 836.4261 | 627.3195 | 627.3195 | L-106-316 | WME-SW-MR-ML-00005
LEVEL 24 RESIDENTIAL POOL
Filtration System
E | Laminated fiberglass Bobbin wound sand filter, 6.25 m3/h, Ø450mm, complete with sand media and manual multiport valve, 1 duty | Aqua, Italy | 1 | Nos | 1130 | 1130 | 918.9708 | 918.9708 | [13 empty] | 0 | 781.1252 | 585.8439 | 0 | MU-450N-VS | WME-SW-MR-ML-00005
F | Plastic self-priming pump, 6.25 m3/h @ 15m head, 1HP, 1 duty + 1 standby | Aqua, Italy | 2 | Nos | 1630 | 3260 | 1325.595 | 2651.1901 | [13 empty] | 0 | 1126.7558 | 845.0668 | 0 | EUROSWIM 100M/A | WME-SW-MR-ML-00014
Water Treatment System
G | Automatic pH/RX dosing controller |  | 1 | Nos |  | 0
H | Manual analog dosing pumps - pH (10L/h - 5 bar) |  | 1 | Nos |  | 0
J | Manual analog dosing pumps - RX (10L/h - 5 bar) |  | 1 | Nos |  | 0
| Pre-assembled panel - Twin Dosing System - 10L/h @ 4 bars (pH & Rx) | Aqua, Italy | 1 | Nos | 6030 | 6030 | 4903.8884 | 4903.8884 | [13 empty] | 0 | 4168.3051 | 3126.2288 | 0 | ADPS101 | WME-SW-MR-ML-00018
K | Polyethylene dosing tanks, 125L 100L | Aqua, Italy | 2 | Nos | 530 | 1060 | 431.0217 | 862.0434 | [13 empty] | 0 | 366.3684 | 274.7763 | 0 | ADTANK010 | WME-SW-MR-ML-00005
L | Manual stirrers | Aqua, Italy | 2 | Nos | 410 | 820 | 333.4319 | 666.8638 | [13 empty] | 0 | 283.4171 | 212.5628 | 0 | ADAGMP06 | WME-SW-MR-ML-00005
| To Collection Dhs. |  |  |  |  | 73460 |  | 59741.2335
SWIMMING POOLS (CONT'D)
LEVEL 24 RESIDENTIAL POOL (CONT'D)
Fittings
A | Stainless steel main drain, 200x200mm | Aqua, Italy | 2 | Nos | 800 | 1600 | 650.5988 | 1301.1976 | [13 empty] | 0 | 553.009 | 414.7567 | 0 | F-155 | WME-SW-MR-ML-00015
B | Stainless steel floor inlet | Aqua, Italy | 4 | Nos | 710 | 2840 | 577.4064 | 2309.6257 | [13 empty] | 0 | 490.7955 | 368.0966 | 0 | F-230 | WME-SW-MR-ML-00019
C | Stainless steel vacuum point | Aqua, Italy | 1 | Nos | 300 | 300 | 243.9745 | 243.9745 | [13 empty] | 0 | 207.3784 | 155.5338 | 0 | F-240/A | WME-SW-MR-ML-00008
D | Stainless steel overflow fittings | AtecPool, Spain | 8 | Nos | 440 | 3520 | 357.8293 | 2862.6347 | [13 empty] | 0 | 304.1549 | 228.1162 | 0 | 03100282-1 | WME-SW-MR-ML-00013
Maintenance Kit
E | Vacuum head | Aqua, Italy | 1 | Nos | 830 | 830 | 674.9962 | 674.9962 | [9 empty] | 0 | 573.7468 | 430.3101 | 0
F | Telescopic handle |  | 1 | Nos
G | Vacuum hose |  | 1 | Nos
H | Pool brush |  | 1 | Nos
J | Leaf skimmer |  | 1 | Nos
K | Leaf rake |  | 1 | Nos
L | Algae brush |  | 1 | Nos
M | Hose fitting |  | 1 | Nos
N | Test kit |  | 1 | Nos
Control Panel Board
P | Control Panel Board | Al Fanar/ Scheinder | 1 | Nos | 14000 | 14000 | 11385.4788 | 11385.4788 | [9 empty] | 0 | 9677.6569 | 7258.2427 | 0 | [5 empty] | WME-SW-MR-ML-00026_00-B.
Q | MEP Works including piping, cabling, containment, etc. | Cosmoplast/Atlas/Cepex/Ducab | 1 | Nos | 70000 | 70000 | 56927.3938 | 56927.3938 | [18 empty] | WME-SW-MR-ML-00009
R | Testing and Commissioning |  | 1 | Item |  | Included
| To Collection Dhs. |  |  |  |  | 93090 |  | 75705.3013
SWIMMING POOLS (CONT'D)
LEVEL 24 RESIDENTIAL POOL (CONT'D)
Underwater lights
A | X-W16 (as per VE comparison table & data sheet) | Luce & Light | 4 | Nos | 3830 | 15320 | 3114.7417 | 12458.9668 | [9 empty] | 0 | 2647.5304 | 1985.6478 | 0 | 0 | 2647.5304 | 1985.6478 | 0 | CW16009LI + WC5003 | WME-SW-MIR-ML-00014 WME-SW-MR-ML-00027_00 | cost of SS Junction Box (25%) |  | 4 nos. lights
B | X-W17 (as per VE comparison table & data sheet) | Luce & Light | 3 | Nos | 4210 | 12630 | 3423.7761 | 10271.3283 | [9 empty] | 0 | 2910.2097 | 2182.6573 | 0 | 0 | 2910.2097 | 2182.6573 | 0 | CW300009MI + WC5006 | WME-SW-MIR-ML-00014 WME-SW-MR-ML-00027_00 | cost of SS Junction Box (25%) |  | 3 nos. lights
Heating/Cooling System
C | Plate Heat Exchanger, Titanium, 38 kW heating capacity | Aqua, Italy | 1 | Nos | 5760 | 5760 | 4684.3113 | 4684.3113 | [9 empty] | 0 | 3981.6646 | 2986.2484 | 0 |  |  |  |  | Custom Made | WME-SW-MR-ML-00023_00
D | Plate Heat Exchanger, Titanium, 15 kW cooling capacity | Aqua, Italy | 1 | Nos | 5190 | 5190 | 4220.7596 | 4220.7596 | [9 empty] | 0 | 3587.6457 | 2690.7343 | 0 |  |  |  |  | Custom Made | WME-SW-MR-ML-00023_00
Pool Surround
| Pool ladder-overflow type, 3 steps | Aqua, Italy | 2 | Nos | 1400 | 2800 | 1138.5479 | 2277.0958 | [9 empty] | 0 | 967.7657 | 725.8243 | 0
| To Collection Dhs. |  |  |  |  | 41700 |  | 33912.4617
SWIMMING POOLS (CONT'D)
LEVEL 25 RESIDENTIAL POOL
Filtration System
B | Laminated fiberglass Bobbin wound sand filter, 6.25 m3/h, Ø450mm, complete with sand media and manual multiport valve, 1 duty | Aqua, Italy | 1 | Nos | 1130 | 1130 | 918.9708 | 918.9708 | [13 empty] | 0 | 781.1252 | 585.8439 | 0 | MU-450N-VS | WME-SW-MR-ML-00005
C | Plastic self-priming pump, 6.25 m3/h @ 15m head, 1HP, 1 duty + 1 standby | Aqua, Italy | 2 | Nos | 1630 | 3260 | 1325.595 | 2651.1901 | [13 empty] | 0 | 1126.7558 | 845.0668 | 0 | EUROSWIM 100M/A | WME-SW-MR-ML-00014
Water Treatment System
D | Automatic pH/RX dosing controller |  | 1 | Nos |  | 0
E | Manual analog dosing pumps - pH (10L/h - 5 bar) |  | 1 | Nos |  | 0
F | Manual analog dosing pumps - RX (10L/h - 5 bar) |  | 1 | Nos |  | 0
| Pre-assembled panel - Twin Dosing System - 10L/h @ 4 bars (pH & Rx) | Aqua, Italy | 1 | Nos | 6030 | 6030 | 4903.8884 | 4903.8884 | [13 empty] | 0 | 4168.3051 | 3126.2288 | 0 | ADPS101 | WME-SW-MR-ML-00018
G | Polyethylene dosing tanks, 125L 100L | Aqua, Italy | 2 | Nos | 530 | 1060 | 431.0217 | 862.0434 | [13 empty] | 0 | 366.3684 | 274.7763 | 0 | ADTANK010 | WME-SW-MR-ML-00005
H | Manual stirrers | Aqua, Italy | 2 | Nos | 410 | 820 | 333.4319 | 666.8638 | [13 empty] | 0 | 283.4171 | 212.5628 | 0 | ADAGMP06 | WME-SW-MR-ML-00005
Fittings
J | Stainless steel main drain, 200x200mm | Aqua, Italy | 2 | Nos | 800 | 1600 | 650.5988 | 1301.1976 | [13 empty] | 0 | 553.009 | 414.7567 | 0 | F-155 | WME-SW-MR-ML-00015
K | Stainless steel floor inlet | Aqua, Italy | 4 | Nos | 710 | 2840 | 577.4064 | 2309.6257 | [13 empty] | 0 | 490.7955 | 368.0966 | 0 | F-230 | WME-SW-MR-ML-00019
L | Stainless steel vacuum point | Aqua, Italy | 1 | Nos | 300 | 300 | 243.9745 | 243.9745 | [13 empty] | 0 | 207.3784 | 155.5338 | 0 | F-240/A | WME-SW-MR-ML-00008
M | Stainless steel overflow fittings | AtecPool, Spain | 8 | Nos | 440 | 3520 | 357.8293 | 2862.6347 | [13 empty] | 0 | 304.1549 | 228.1162 | 0 | 03100282-1 | WME-SW-MR-ML-00013
| To Collection Dhs. |  |  |  |  | 20560 |  | 16720.3888
SWIMMING POOLS (CONT'D)
LEVEL 25 RESIDENTIAL POOL (CONT'D)
Maintenance Kit
A | Vacuum head | Aqua, Italy | 1 | Nos | 830 | 830 | 674.9962 | 674.9962 | [9 empty] | 0 | 573.7468 | 430.3101 | 0
B | Telescopic handle |  | 1 | Nos
C | Vacuum hose |  | 1 | Nos
D | Pool brush |  | 1 | Nos
E | Leaf skimmer |  | 1 | Nos
F | Leaf rake |  | 1 | Nos
G | Algae brush |  | 1 | Nos
H | Hose fitting |  | 1 | Nos
J | Test kit |  | 1 | Nos
Control Panel Board
K | Control Panel Board | Al Fanar/ Scheinder | 1 | Nos | 14000 | 14000 | 11385.4788 | 11385.4788 | [9 empty] | 0 | 9677.6569 | 7258.2427 | 0 | [5 empty] | WME-SW-MR-ML-00026_00-B.
L | MEP Works including piping, cabling, containment, etc. | Cosmoplast/Atlas/Cepex/Ducab | 1 | Nos | 70000 | 70000 | 56927.3938 | 56927.3938 | [18 empty] | WME-SW-MR-ML-00009
M | Testing and Commissioning |  | 1 | Item |  | Included
| To Collection Dhs. |  |  |  |  | 84830 |  | 68987.8688
SWIMMING POOLS (CONT'D)
LEVEL 25 RESIDENTIAL POOL (CONT'D)
Underwater lights
A | X-W16 (as per VE comparison table & data sheet) | Luce & Light | 6 | Nos | 3830 | 22980 | 3114.7417 | 18688.4501 | [9 empty] | 0 | 2647.5304 | 1985.6478 | 0 | 0 | 2647.5304 | 1985.6478 | 0 | CW16009LI + WC5003 | DN-21-1613 WME-SW-MR-ML-00027_00 | cost of SS Junction Box (25%) |  | 6nos. lights
B | X-W17 (as per VE comparison table & data sheet) | Luce & Light | 3 | Nos | 4210 | 12630 | 3423.7761 | 10271.3283 | [9 empty] | 0 | 2910.2097 | 2182.6573 | 0 | 0 | 2910.2097 | 2182.6573 | 0 | CW300009MI + WC5006 | DN-21-1613 WME-SW-MR-ML-00027_00 | cost of SS Junction Box (25%) |  | 3 nos. lights
Heating/Cooling System
C | Plate Heat Exchanger, Titanium, 38 kW heating capacity | Aqua, Italy | 1 | Nos | 5760 | 5760 | 4684.3113 | 4684.3113 | [9 empty] | 0 | 3981.6646 | 2986.2484 | 0 |  |  |  |  | Custom Made | WME-SW-MR-ML-00023_00
D | Plate Heat Exchanger, Titanium, 15 kW cooling capacity | Aqua, Italy | 1 | Nos | 5190 | 5190 | 4220.7596 | 4220.7596 | [9 empty] | 0 | 3587.6457 | 2690.7343 | 0 |  |  |  |  | Custom Made | WME-SW-MR-ML-00023_00
Pool Surround
| Pool ladder-overflow type, 3 steps | Aqua, Italy | 2 | Nos | 1400 | 2800 | 1138.5479 | 2277.0958 | [9 empty] | 0 | 967.7657 | 725.8243 | 0
LEVEL 26 RESIDENTIAL POOL
Filtration System
F | Laminated fiberglass Bobbin wound sand filter, 6.2 m3/h, Ø450mm, complete with sand media and manual multiport valve, 1 duty | Aqua, Italy | 1 | Nos | 1130 | 1130 | 918.9708 | 918.9708 | [13 empty] | 0 | 781.1252 | 585.8439 | 0 | MU-450N-VS | WME-SW-MR-ML-00005
G | Plastic self-priming pump, 6.2 m3/h @ 15m head, 1HP, 1 duty + 1 standby | Aqua, Italy | 2 | Nos | 1630 | 3260 | 1325.595 | 2651.1901 | [13 empty] | 0 | 1126.7558 | 845.0668 | 0 | EUROSWIM 100M/A | WME-SW-MR-ML-00014
| To Collection Dhs. |  |  |  |  | 53750 |  | 43712.1059
SWIMMING POOLS (CONT'D)
LEVEL 26 RESIDENTIAL POOL (CONT'D)
Water Treatment System
A | Automatic pH/RX dosing controller |  | 1 | Nos |  | 0
B | Manual analog dosing pumps - pH (10L/h - 5 bar) |  | 1 | Nos |  | 0
C | Manual analog dosing pumps - RX (10L/h - 5 bar) |  | 1 | Nos |  | 0
| Pre-assembled panel - Twin Dosing System - 10L/h @ 4 bars (pH & Rx) | Aqua, Italy | 1 | Nos | 6030 | 6030 | 4903.8884 | 4903.8884 | [13 empty] | 0 | 4168.3051 | 3126.2288 | 0 | ADPS101 | WME-SW-MR-ML-00018
D | Polyethylene dosing tanks, 125L 100L | Aqua, Italy | 2 | Nos | 530 | 1060 | 431.0217 | 862.0434 | [13 empty] | 0 | 366.3684 | 274.7763 | 0 | ADTANK010 | WME-SW-MR-ML-00005
E | Manual stirrers | Aqua, Italy | 2 | Nos | 410 | 820 | 333.4319 | 666.8638 | [13 empty] | 0 | 283.4171 | 212.5628 | 0 | ADAGMP06 | WME-SW-MR-ML-00005
Fittings
F | Stainless steel main drain, 200x200mm | Aqua, Italy | 2 | Nos | 800 | 1600 | 650.5988 | 1301.1976 | [13 empty] | 2 | 553.009 | 414.7567 | 829.5135 | F-155 | WME-SW-MR-ML-00015
G | Stainless steel wall floor inlet | Aqua, Italy | 4 | Nos | 710 | 2840 | 577.4064 | 2309.6257 | [13 empty] | 4 | 490.7955 | 368.0966 | 1472.3864 | F-230 | WME-SW-MR-ML-00019
H | Stainless steel vacuum point | Aqua, Italy | 1 | Nos | 300 | 300 | 243.9745 | 243.9745 | [13 empty] | 1 | 207.3784 | 155.5338 | 155.5338 | F-240/A | WME-SW-MR-ML-00008
J | ABS skimmer fittings with stainless steel faceplate | AtecPool, Spain | 2 | Nos | 820 | 1640 | 666.8638 | 1333.7275 | [13 empty] | 0 | 566.8342 | 425.1256 | 0 | 015901010 | WME-SW-MR-ML-00020
Maintenance Kit
K | Vacuum head | Aqua, Italy | 1 | Nos | 830 | 830 | 674.9962 | 674.9962 | [9 empty] | 0 | 573.7468 | 430.3101 | 0
L | Telescopic handle |  | 1 | Nos
M | Vacuum hose |  | 1 | Nos
N | Pool brush |  | 1 | Nos
P | Leaf skimmer |  | 1 | Nos
Q | Leaf rake |  | 1 | Nos
R | Algae brush |  | 1 | Nos
S | Hose fitting |  | 1 | Nos
T | Test kit |  | 1 | Nos
| To Collection Dhs. |  |  |  |  | 15120 |  | 12296.3171
SWIMMING POOLS (CONT'D)
LEVEL 26 RESIDENTIAL POOL (CONT'D)
Control Panel Board
A | Control Panel Board | Al Fanar/ Scheinder | 1 | Nos | 14000 | 14000 | 11385.4788 | 11385.4788 | [9 empty] | 1 | 9677.6569 | 7258.2427 | 7258.2427 | [5 empty] | WME-SW-MR-ML-00029
B | MEP Works including piping, cabling, containment, etc. | Cosmoplast/Atlas/Cepex/Ducab | 1 | Nos | 70000 | 70000 | 56927.3938 | 56927.3938
C | Testing and Commissioning |  | 1 | Item |  | Included
Underwater lights
D | X-W16 |  | 4 | Nos |  | 0
D | X-W17 (AS PER LT902-LA-L26-SL-0110-01-[A]_E) (as per VE comparison table & data sheet) | Luce & Light | 8 | Nos | 4210 | 33680 | 3423.7761 | 27390.2089 | [9 empty] | 0 | 2910.2097 | 2182.6573 | 0 | 0 | 2910.2097 | 2182.6573 | 0 | CW300009MI + WC5006 | DN-21-1613 WME-SW-MR-ML-00027_00 | cost of SS Junction Box (25%) |  | 8 nos. lights
Heating/Cooling System
E | Plate Heat Exchanger, Titanium, 32 kW heating capacity | Aqua, Italy | 1 | Nos | 5190 | 5190 | 4220.7596 | 4220.7596 | [9 empty] | 0 | 3587.6457 | 2690.7343 | 0 |  |  |  |  | Custom Made | WME-SW-MR-ML-00023_00
F | Plate Heat Exchanger, Titanium, 15 kW cooling capacity | Aqua, Italy | 1 | Nos | 5190 | 5190 | 4220.7596 | 4220.7596 | [9 empty] | 0 | 3587.6457 | 2690.7343 | 0 |  |  |  |  | Custom Made | WME-SW-MR-ML-00023_00
Pool Surround
| Pool ladder, 3 steps | Aqua, Italy | 1 | Nos | 1210 | 1210 | 984.0307 | 984.0307 | [9 empty] | 0 | 836.4261 | 627.3195 | 0
| To Collection Dhs. |  |  |  |  | 129270 |  | 105128.6314
SWIMMING POOLS (CONT'D)
LEVEL 27 RESIDENTIAL POOL
Filtration System
B | Laminated fiberglass Bobbin wound sand filter, 6.25 m3/h, Ø450mm, complete with sand media and manual multiport valve, 1 duty | Aqua, Italy | 1 | Nos | 1130 | 1130 | 918.9708 | 918.9708 | [13 empty] | 0 | 781.1252 | 585.8439 | 0 | MU-450N-VS | WME-SW-MR-ML-00005
C | Plastic self-priming pump, 6.25 m3/h @ 15m head, 1HP, 1 duty + 1 standby | Aqua, Italy | 2 | Nos | 1630 | 3260 | 1325.595 | 2651.1901 | [13 empty] | 0 | 1126.7558 | 845.0668 | 0 | EUROSWIM 100M/A | WME-SW-MR-ML-00014
Water Treatment System
D | Automatic pH/RX dosing controller |  | 1 | Nos |  | 0
E | Manual analog dosing pumps - pH (10L/h - 5 bar) |  | 1 | Nos |  | 0
F | Manual analog dosing pumps - RX (10L/h - 5 bar) |  | 1 | Nos |  | 0
| Pre-assembled panel - Twin Dosing System - 10L/h @ 4 bars (pH & Rx) | Aqua, Italy | 1 | Nos | 6030 | 6030 | 4903.8884 | 4903.8884 | [13 empty] | 0 | 4168.3051 | 3126.2288 | 0 | ADPS101 | WME-SW-MR-ML-00018
G | Polyethylene dosing tanks, 125L 100L | Aqua, Italy | 2 | Nos | 530 | 1060 | 431.0217 | 862.0434 | [13 empty] | 0 | 366.3684 | 274.7763 | 0 | ADTANK010 | WME-SW-MR-ML-00005
H | Manual stirrers | Aqua, Italy | 2 | Nos | 410 | 820 | 333.4319 | 666.8638 | [13 empty] | 0 | 283.4171 | 212.5628 | 0 | ADAGMP06 | WME-SW-MR-ML-00005
Fittings
J | Stainless steel main drain, 200x200mm | Aqua, Italy | 2 | Nos | 800 | 1600 | 650.5988 | 1301.1976 | [13 empty] | 0 | 553.009 | 414.7567 | 0 | F-155 | WME-SW-MR-ML-00015
K | Stainless steel floor inlet | Aqua, Italy | 4 | Nos | 710 | 2840 | 577.4064 | 2309.6257 | [13 empty] | 0 | 490.7955 | 368.0966 | 0 | F-230 | WME-SW-MR-ML-00019
L | Stainless steel vacuum point | Aqua, Italy | 1 | Nos | 300 | 300 | 243.9745 | 243.9745 | [13 empty] | 0 | 207.3784 | 155.5338 | 0 | F-240/A | WME-SW-MR-ML-00008
M | Stainless steel overflow fittings | AtecPool, Spain | 8 | Nos | 440 | 3520 | 357.8293 | 2862.6347 | [13 empty] | 0 | 304.1549 | 228.1162 | 0 | 03100282-1 | WME-SW-MR-ML-00013
| To Collection Dhs. |  |  |  |  | 20560 |  | 16720.3888
SWIMMING POOLS (CONT'D)
LEVEL 27 RESIDENTIAL POOL (CONT'D)
Maintenance Kit
A | Vacuum head | Aqua, Italy | 1 | Nos | 830 | 830 | 674.9962 | 674.9962 | [9 empty] | 0 | 573.7468 | 430.3101 | 0
B | Telescopic handle |  | 1 | Nos
C | Vacuum hose |  | 1 | Nos
D | Pool brush |  | 1 | Nos
E | Leaf skimmer |  | 1 | Nos
F | Leaf rake |  | 1 | Nos
G | Algae brush |  | 1 | Nos
H | Hose fitting |  | 1 | Nos
J | Test kit |  | 1 | Nos
Control Panel Board
K | Control Panel Board | Al Fanar/ Scheinder | 1 | Nos | 14000 | 14000 | 11385.4788 | 11385.4788 | [9 empty] | 0 | 9677.6569 | 7258.2427 | 0 | [5 empty] | WME-SW-MR-ML-00026_00-B.
L | MEP Works including piping, cabling, containment, etc. | Cosmoplast/Atlas/Cepex/Ducab | 1 | Nos | 70000 | 70000 | 56927.3938 | 56927.3938 | [18 empty] | WME-SW-MR-ML-00009
M | Testing and Commissioning |  | 1 | Item |  | Included
Underwater lights
N | X-W16 (as per VE comparison table & data sheet) | Luce & Light | 6 | Nos | 3830 | 22980 | 3114.7417 | 18688.4501 | [9 empty] | 0 | 2647.5304 | 1985.6478 | 0 | 0 | 2647.5304 | 1985.6478 | 0 | CW16009LI + WC5003 | DN-21-1613 WME-SW-MR-ML-00027_00 | cost of SS Junction Box (25%) |  | 6 nos. lights
P | X-W17 (as per VE comparison table & data sheet) | Luce & Light | 3 | Nos | 4210 | 12630 | 3423.7761 | 10271.3283 | [9 empty] | 0 | 2910.2097 | 2182.6573 | 0 | 0 | 2910.2097 | 2182.6573 | 0 | CW300009MI + WC5006 | DN-21-1613 WME-SW-MR-ML-00027_00 | cost of SS Junction Box (25%) |  | 3 nos. lights
| To Collection Dhs. |  |  |  |  | 120440 |  | 97947.6473
SWIMMING POOLS (CONT'D)
LEVEL 27 RESIDENTIAL POOL (CONT'D)
Heating/Cooling System
A | Plate Heat Exchanger, Titanium, 38 kW heating capacity | Aqua, Italy | 1 | Nos | 5760 | 5760 | 4684.3113 | 4684.3113 | [9 empty] | 0 | 3981.6646 | 2986.2484 | 0 |  |  |  |  | Custom Made | WME-SW-MR-ML-00023_00
B | Plate Heat Exchanger, Titanium, 15 kW cooling capacity | Aqua, Italy | 1 | Nos | 5190 | 5190 | 4220.7596 | 4220.7596 | [9 empty] | 0 | 3587.6457 | 2690.7343 | 0 |  |  |  |  | Custom Made | WME-SW-MR-ML-00023_00
Pool Surround
| Pool ladder-overflow type, 3 steps | Aqua, Italy | 2 | Nos | 1400 | 2800 | 1138.5479 | 2277.0958 | [9 empty] | 0 | 967.7657 | 725.8243 | 0
LEVEL 29 RESIDENTIAL POOL
Filtration System
D | Laminated fiberglass Bobbin wound sand filter, 6.25 m3/h, Ø450mm, complete with sand media and manual multiport valve, 1 duty | Aqua, Italy | 1 | Nos | 1130 | 1130 | 918.9708 | 918.9708 | [13 empty] | 0 | 781.1252 | 585.8439 | 0 | MU-450N-VS | WME-SW-MR-ML-00005
E | Plastic self-priming pump, 6.25 m3/h @ 15m head, 1HP, 1 duty + 1 standby | Aqua, Italy | 2 | Nos | 1630 | 3260 | 1325.595 | 2651.1901 | [13 empty] | 0 | 1126.7558 | 845.0668 | 0 | EUROSWIM 100M/A | WME-SW-MR-ML-00014
Water Treatment System
F | Automatic pH/RX dosing controller |  | 1 | Nos |  | 0
G | Manual analog dosing pumps - pH (10L/h - 5 bar) |  | 1 | Nos |  | 0
H | Manual analog dosing pumps - RX (10L/h - 5 bar) |  | 1 | Nos |  | 0
| Pre-assembled panel - Twin Dosing System - 10L/h @ 4 bars (pH & Rx) | Aqua, Italy | 1 | Nos | 6030 | 6030 | 4903.8884 | 4903.8884 | [13 empty] | 0 | 4168.3051 | 3126.2288 | 0 | ADPS101 | WME-SW-MR-ML-00018
J | Polyethylene dosing tanks, 125L 100L | Aqua, Italy | 2 | Nos | 530 | 1060 | 431.0217 | 862.0434 | [13 empty] | 0 | 366.3684 | 274.7763 | 0 | ADTANK010 | WME-SW-MR-ML-00005
K | Manual stirrers | Aqua, Italy | 2 | Nos | 410 | 820 | 333.4319 | 666.8638 | [13 empty] | 0 | 283.4171 | 212.5628 | 0 | ADAGMP06 | WME-SW-MR-ML-00005
Fittings
L | Stainless steel main drain, 200x200mm | Aqua, Italy | 2 | Nos | 800 | 1600 | 650.5988 | 1301.1976 | [13 empty] | 0 | 553.009 | 414.7567 | 0 | F-155 | WME-SW-MR-ML-00015
M | Stainless steel floor inlet | Aqua, Italy | 4 | Nos | 710 | 2840 | 577.4064 | 2309.6257 | [13 empty] | 0 | 490.7955 | 368.0966 | 0 | F-230 | WME-SW-MR-ML-00019
N | Stainless steel vacuum point | Aqua, Italy | 1 | Nos | 300 | 300 | 243.9745 | 243.9745 | [13 empty] | 0 | 207.3784 | 155.5338 | 0 | F-240/A | WME-SW-MR-ML-00008
P | Stainless steel overflow fittings | AtecPool, Spain | 8 | Nos | 440 | 3520 | 357.8293 | 2862.6347 | [13 empty] | 0 | 304.1549 | 228.1162 | 0 | 03100282-1 | WME-SW-MR-ML-00013
| To Collection Dhs. |  |  |  |  | 34310 |  | 27902.5554
SWIMMING POOLS (CONT'D)
LEVEL 29 RESIDENTIAL POOL (CONT'D)
Maintenance Kit
A | Vacuum head | Aqua, Italy | 1 | Nos | 830 | 830 | 674.9962 | 674.9962 | [9 empty] | 0 | 573.7468 | 430.3101 | 0
B | Telescopic handle |  | 1 | Nos
C | Vacuum hose |  | 1 | Nos
D | Pool brush |  | 1 | Nos
E | Leaf skimmer |  | 1 | Nos
F | Leaf rake |  | 1 | Nos
G | Algae brush |  | 1 | Nos
H | Hose fitting |  | 1 | Nos
J | Test kit |  | 1 | Nos
Control Panel Board
K | Control Panel Board | Al Fanar/ Scheinder | 1 | Nos | 14000 | 14000 | 11385.4788 | 11385.4788 | [9 empty] | 0 | 9677.6569 | 7258.2427 | 0 | [5 empty] | WME-SW-MR-ML-00029
L | MEP Works including piping, cabling, containment, etc. | Cosmoplast/Atlas/Cepex/Ducab | 1 | Nos | 70000 | 70000 | 56927.3938 | 56927.3938 | [18 empty] | WME-SW-MR-ML-00009
M | Testing and Commissioning |  | 1 | Item |  | included
Underwater lights
N | X-W16 (as per VE comparison table & data sheet) | Luce & Light | 6 | Nos | 3830 | 22980 | 3114.7417 | 18688.4501 | [9 empty] | 0 | 2647.5304 | 1985.6478 | 0 | 0 | 2647.5304 | 1985.6478 | 0 | CW16009LI + WC5003 | DN-21-1613 WME-SW-MR-ML-00027_00 | cost of SS Junction Box (25%) |  | 6 nos. lights
P | X-W17 (as per VE comparison table & data sheet) | Luce & Light | 3 | Nos | 4210 | 12630 | 3423.7761 | 10271.3283 | [9 empty] | 0 | 2910.2097 | 2182.6573 | 0 | 0 | 2910.2097 | 2182.6573 | 0 | CW300009MI + WC5006 | DN-21-1613 WME-SW-MR-ML-00027_00 | cost of SS Junction Box (25%) |  | 3 nos. lights
| To Collection Dhs. |  |  |  |  | 120440 |  | 97947.6473
SWIMMING POOLS (CONT'D)
LEVEL 29 RESIDENTIAL POOL (CONT'D)
Heating/Cooling System
A | Plate Heat Exchanger, Titanium, 38 kW heating capacity | Aqua, Italy | 1 | Nos | 5760 | 5760 | 4684.3113 | 4684.3113 | [9 empty] | 0 | 3981.6646 | 2986.2484 | 0 |  |  |  |  | Custom Made | WME-SW-MR-ML-00023_00
B | Plate Heat Exchanger, Titanium, 15 kW cooling capacity | Aqua, Italy | 1 | Nos | 5190 | 5190 | 4220.7596 | 4220.7596 | [9 empty] | 0 | 3587.6457 | 2690.7343 | 0 |  |  |  |  | Custom Made | WME-SW-MR-ML-00023_00
Pool Surround
| Pool ladder-overflow type, 3 steps | Aqua, Italy | 2 | Nos | 1400 | 2800 | 1138.5479 | 2277.0958 | [9 empty] | 0 | 967.7657 | 725.8243 | 0
LEVEL 29 HOTEL ROOF TOP POOL
Filtration System
D | Laminated Bobbin wound sand filter, simultaneous projection of resin and fibre glass, 25.95 m3/h, Ø900mm, complete with sand media and manual valve manifold, 6 duties | Aqua, Italy | 6 | Nos | 3730 | 22380 | 3033.4168 | 18200.501 | [13 empty] | 0 | 2578.4043 | 1933.8032 | 0 | MU-900N-VS | WME-SW-MR-ML-00019
E | Plastic self-priming pump, 52.0 m3/h @ 16m head, 7.5HP, 3 duty + 1 standby | Aqua, Italy | 4 | Nos | 7350 | 29400 | 5977.3763 | 23909.5054 | [13 empty] | 0 | 5080.7699 | 3810.5774 | 0 | KPA1000 | WME-SW-MR-ML-00014
Water Treatment System
F | Automatic pH/RX dosing controller |  | 1 | Nos |  | 0
G | Manual analog dosing pumps - pH (20L/h-5 bar) |  | 2 | Nos |  | 0
H | Manual analog dosing pumps - RX (20L/h-5 bar) |  | 2 | Nos |  | 0
| Pre-assembled panel - Twin Dosing System - 10L/h @ 4 bars (pH & Rx) | Aqua, Italy | 4 | Nos | 6030 | 24120 | 4903.8884 | 19615.5534 | [13 empty] | 0 | 4168.3051 | 3126.2288 | 0 | ADPS101 | WME-SW-MR-ML-00018
J | Polyethylene dosing tanks, 1000L | Aqua, Italy | 4 | Nos | 3410 | 13640 | 2773.1773 | 11092.7093 | [13 empty] | 0 | 2357.2007 | 1767.9005 | 0 | ADTANK100 | WME-SW-MR-ML-00014 WME-SW-MR-ML-00018
K | Manual stirrers | Aqua, Italy | 4 | Nos | 440 | 1760 | 357.8293 | 1431.3173 | [13 empty] | 0 | 304.1549 | 228.1162 | 0 | ADAGMP06 | WME-SW-MR-ML-00005
L | UV Sterilizer, Flow: 95 m³/h at 3 bar pressure | AtecPool, Spain | 2 | Nos | 44830 | 89660 | 36457.9295 | 72915.859 | [13 empty] | 0 | 30989.2401 | 23241.93 | 0 | UV-5205 | WME-SW-MR-ML-00017
Fittings
M | Stainless steel main drain, 400x400mm | Aqua, Italy | 7 | Nos | 1460 | 10220 | 1187.3428 | 8311.3995 | [13 empty] | 7 | 1009.2414 | 756.931 | 5298.5172 | F-158 | WME-SW-MR-ML-00016 DN-21-1857 (1 Nos)
N | Stainless steel floor inlet | Aqua, Italy | 64 | Nos | 710 | 45440 | 577.4064 | 36954.0111 | [13 empty] | 64 | 490.7955 | 368.0966 | 23558.182 | F-230 | WME-SW-MR-ML-00021
N | Stainless steel wall inlet | Aqua, Italy | 46 | Nos | 280 | 12880 | 227.7096 | 10474.6405 | [9 empty] | 0 | 193.5531 | 145.1649 | 0
P | Stainless steel vacuum point | Aqua, Italy | 8 | Nos | 300 | 2400 | 243.9745 | 1951.7964 | [13 empty] | 8 | 207.3784 | 155.5338 | 1244.2702 | F-240/A | WME-SW-MR-ML-00008
Q | Stainless steel overflow fittings | AtecPool or eq. | 127 | Nos | 440 | 55880 | 357.8293 | 45444.3252 | [13 empty] | 127 | 304.1549 | 228.1162 | 28970.7573 | 03100282-1 | WME-SW-MR-ML-00013
| To Collection Dhs. |  |  |  |  | 321530 |  | 261483.7846
SWIMMING POOLS (CONT'D)
LEVEL 29 HOTEL ROOF TOP POOL (CONT'D)
Overflow Effect System
A | Overflow effect cast iron pump with cast iron impeller plastic pump, 87.8 m3/h @ 16m head, 10HP, 3Ph, 2 duty | Aqua, Italy | 2 | Nos | 8790 | 17580 | 7148.4542 | 14296.9083 | [9 empty] | 0 | 6076.186 | 4557.1395 | 0
Maintenance Kit
D | Flexible vacuum head | Aqua, Italy | 1 | Nos | 830 | 830 | 674.9962 | 674.9962 | [17 empty] | C-151 | WME-SW-MR-ML-00005
E | Telescopic handle |  | 1 | Nos | [21 empty] | C-137 | WME-SW-MR-ML-00015
F | Vacuum hose |  | 1 | Nos | [21 empty] | C-133 | WME-SW-MR-ML-00015
G | Pool brush |  | 1 | Nos | [21 empty] | C-151 | WME-SW-MR-ML-00005
H | Leaf skimmer |  | 1 | Nos | [17 empty] | 1 | 573.7468 | 430.3101 | 430.3101 | C-151 | WME-SW-MR-ML-00005
J | Leaf rake |  | 1 | Nos | [21 empty] | C-145 | WME-SW-MR-ML-00005
K | Algae brush |  | 1 | Nos | [21 empty] | C-122 | WME-SW-MR-ML-00005
L | Hose fitting |  | 1 | Nos | [21 empty] | C-135 | WME-SW-MR-ML-00015
M | Test kit |  | 1 | Nos | [21 empty] | C-151 | WME-SW-MR-ML-00005
Control Panel Board
N | Control Panel Board | Al Fanar/ Scheinder | 1 | Nos | 43750 | 43750 | 35579.6211 | 35579.6211 | [9 empty] | 0 | 30242.678 | 22682.0085 | 0 | [5 empty] | WME-SW-MR-ML-00028
P | MEP Works including piping, cabling, containment, etc. | Cosmoplast/Atlas/Cepex/Ducab | 1 | Nos | 250000 | 250000 | 203312.1207 | 203312.1207 | [17 empty] | - | WME-SW-MR-ML-00001 WME-SW-MR-ML-00009
Q | Testing and Commissioning |  | 1 | Item |  | Included
Underwater lights
N | X-F1 UFO - Fiber optic system - Consisting of: 3 x Light source, IP20 with metallic enclosure No. of Points: 750 points Cable Size: 0.75mm2 (80%), 1.0 mm2 (18%) and 1.5 mm2 (2%) Cable length: average 20m WITHOUT END FITTINGS | UFO, UK | 1 | Item | 197540 | 197540 | 160649.1053 | 160649.1053 | [13 empty] | 0 | 136551.7395 | 102413.8046 | 0 | - | WME-SW-MR-L29-00006 WME-SW-MR-L29-00030
P | X-F2 UFO - Fiber optic system - Consisting of: 2 x Light source, IP20 with metallic enclosure No. of Points: 200 points Cable Size: 0.75mm2 (80%), 1.0 mm2 (18%) and 1.5 mm2 (2%) Cable length: average 20m WITHOUT END FITTINGS | UFO, UK | 1 | Item | 89670 | 89670 | 72923.9914 | 72923.9914 | [13 empty] | 0 | 61985.3927 | 46489.0445 | 0 | - | WME-SW-MR-L29-00006 WME-SW-MR-L29-00030
| To Collection Dhs. |  |  |  |  | 599370 |  | 487436.7431
SWIMMING POOLS (CONT'D)
LEVEL 29 HOTEL ROOF TOP POOL (CONT'D)
Heating/Cooling System
R | Air-to-water Heat/Cool Pump Brand: Astral, Spain Heating Capacity: 210 kW Cooling Capacity: 150 kW | Astral, Spain | 4 | Nos | 102770 | 411080 | 83577.5466 | 334310.1863 | [9 empty] | 0 | 71040.9146 | 53280.6859 | 0 |  |  |  |  | AHP500-SU R4 | WME-SW-MR-ML-00012
| Plastic booster pump, 40 m3/h @ 20m head, 12.5HP, 4 duty | Aqua, Italy | 4 | Nos | 10300 | 41200 | 8376.4594 | 33505.8375 | [13 empty] | 0 | 7119.9905 | 5339.9928 | 0 | KPA600 | WME-SW-MIR-ML-00014 DN-21-1610 (3 Nos)
| Control Panel Board | Al Fanar/ Scheinder | 1 | Nos | 26250 | 26250 | 21347.7727 | 21347.7727 | [9 empty] | 0 | 18145.6068 | 13609.2051 | 0 | [5 empty] | WME-SW-MR-ML-00028
Water Tanks
| GRP Panel Balancing Tank, 48 m3 (6.0x4.0x2.0m) Non-insulated |  | 1 | Nos | 103250 | 103250 | 83967.9058 | 83967.9058 | [17 empty] | - | WME-SW-MR-L29-00004
| GRP Panel Backwash Tank, 3 m3 (1.5x1.0x2.0m) Non-insulated |  | 1 | Nos | 10360 | 10360 | 8425.2543 | 8425.2543 | [9 empty] | 0 | 7161.4661 | 5371.0996 | 0 |  |  |  |  | - | WME-SW-MR-L29-00004
| To Collection Dhs. |  |  |  |  | 592140 |  | 481556.9566
SWIMMING POOLS (CONT'D)
ADDITIONAL ITEMS
A | Pipe acoustic insulations for gravity lines and above critical areas only
| Swimming Pool @ Level 4 |  | 1 | Nos | 15000 | 15000 | 12198.7272 | 12198.7272
| Swimming Pool @ Level 10 |  | 1 | Nos | 7000 | 7000 | 5692.7394 | 5692.7394
| Swimming Pool @ Level 24 |  | 1 | Nos | 7000 | 7000 | 5692.7394 | 5692.7394
| Swimming Pool @ Level 25 |  | 1 | Nos | 7000 | 7000 | 5692.7394 | 5692.7394
| Swimming Pool @ Level 26 |  | 1 | Nos | 7000 | 7000 | 5692.7394 | 5692.7394
| Swimming Pool @ Level 27 |  | 1 | Nos | 7000 | 7000 | 5692.7394 | 5692.7394
| Swimming Pool @ Level 29 (Residential) |  | 1 | Nos | 7000 | 7000 | 5692.7394 | 5692.7394
| Swimming Pool @ Level 29 (Roof) |  | 1 | Nos | 37500 | 37500 | 30496.8181 | 30496.8181
B | Level 10 Swimming Pool Lights (as per LT902-LA-L10-SL-0110-01-[D])
| X-W16 (as per VE comparison table & data sheet) | Luce & Light | 3 | Nos | 3830 | 11490 | 3114.7417 | 9344.2251 | [9 empty] | 0 | 2647.5304 | 1985.6478 | 0 | 0.75 | 2647.5304 | 1985.6478 | 1489.2359 |  | DN-21-1613 | cost of SS Junction Box (25%)
| To Collection Dhs. |  |  |  |  | 105990 |  | 86196.2067
SWIMMING POOLS (CONT'D)
ADDITIONAL ITEMS
A | Lifesaving Equipment
| Swimming Pool @ Level 4 - Lifeguard chair (1 no.) - Lifebuoy (2 nos.) + accessories | Aqua, Italy | 1 | Item | 8870 | 8870 | 7213.514 | 7213.514 | [13 empty] | 1 | 6131.4869 | 4598.6152 | 4598.6152 | PG-14, PG-15 & 'PG-16 | WME-SW-MR-ML-00005 WME-SW-MR-ML-00015
| Swimming Pool @ Level 10 - Lifeguard chair (1 no.) - Lifebuoy (2 nos.) + accessories | Aqua, Italy | 1 | Item | 8870 | Rate only
| Swimming Pool @ Level 24 - Lifeguard chair (1 no.) - Lifebuoy (2 nos.) + accessories | Aqua, Italy | 1 | Item | 8870 | Rate only
| Swimming Pool @ Level 25 - Lifeguard chair (1 no.) - Lifebuoy (2 nos.) + accessories | Aqua, Italy | 1 | Item | 8870 | Rate only
| Swimming Pool @ Level 26 - Lifeguard chair (1 no.) - Lifebuoy (2 nos.) + accessories | Aqua, Italy | 1 | Item | 8870 | Rate only
| Swimming Pool @ Level 27 - Lifeguard chair (1 no.) - Lifebuoy (2 nos.) + accessories | Aqua, Italy | 1 | Item | 8870 | Rate only
| Swimming Pool @ Level 29 - Lifeguard chair (1 no.) - Lifebuoy (2 nos.) + accessories | Aqua, Italy | 1 | Item | 8870 | Rate only
| Swimming Pool @ Level 29 (Roof) - Lifeguard chair (4 no.) - Lifebuoy (8 nos.) + accessories | Aqua, Italy | 1 | Item | 35480 | 35480 | 28854.0562 | 28854.0562 | [13 empty] | 1 | 24525.9477 | 18394.4608 | 18394.4608 | PG-14, PG-15 & 'PG-16 | WME-SW-MR-ML-00005 WME-SW-MR-ML-00015
B | Fiber Optic Light System with end fittings
| X-F1 UFO - Fiber optic system - Consisting of: 3 x Light source, IP20 with metallic enclosure No. of Points: 750 points Cable Size: 1.5 mm2 (100%) Cable length: average 20m WITH P4G END FITTINGS | UFO, UK | 1 | Item | 252280 | Rate only to add on base price
| X-F2 UFO - Fiber optic system - Consisting of: 2 x Light source, IP20 with metallic enclosure No. of Points: 200 points Cable Size: 1.5 mm2 (100%) Cable length: average 20m WITH P4G END FITTINGS | UFO, UK | 1 | Item | 57520 | Rate only to add on base price
| To Collection Dhs. |  |  |  |  | 44350 |  | 36067.5702
SWIMMING POOLS (CONT'D)
ADDITIONAL ITEMS
A | Level 29 Roof Swimming Pools Suspended GRP
| GRP Tank, (4.0x2.0x1.0m), 8 m3 | Al Bassam - AquaSystem | 1 | Nos | 19170 | 19170 | 15589.9734 | 15589.9734 | [13 empty] | 0 | 13251.4774 | 9938.6081 | 0 | - | WME-SW-MR-L29-00004
| Plastic Discharge/Booster Pump, 146.5 m3/h @ 8m head, 12.5 HP, 1 duty + 1 standby | Aqua, Italy | 2 | Nos | 10300 | 20600 | 8376.4594 | 16752.9187 | [13 empty] | 0 | 7119.9905 | 5339.9928 | 0 | KPA1250 | WME-SW-MIR-ML-00005
| Control Panel Provision | Al Fanar/ Scheinder | 1 | Nos | 4380 | 4380 | 3562.0284 | 3562.0284 | [9 empty] | 1 | 3027.7241 | 2270.7931 | 2270.7931 | [5 empty] | WME-SW-MR-ML-00028
| MEP Works including piping, cabling, containment, etc. | Cosmoplast/Atlas/Cepex/Ducab | 1 | Nos | 43750 | 43750 | 35579.6211 | 35579.6211
| TOTAL FOR MOS IN SWIMMING POOLS | [9 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 28224.1952 |  |  |  | 99919.4317
FOR CHECKING PURPOSES ONLY
[21 empty] | 28224.1952 |  |  |  | 99919.4317

## WTF MOS
PLOT-18 | [5 empty] | WM Ref. No.: D20/054-12/C
BILL OF QUANTITIES | [5 empty] | Date: 06-05-2021 | [22 empty] | Discount Rate
BILL :- WATER FEATURES | [28 empty] | 81.32%
[15 empty] | WM MOS Claim |  |  | WM-Khansaheb MOS Claim - February 2023 |  |  |  | OMNIYAT RECOMMENDATION - as per 17001DH/SCA/40-01-33-WM Ver 2 dated 11 April 2022 |  |  |  | ITEM CODE | MIR |  | 18.68%
Item | Description | Make | Qty. | Unit | Rate | Amount | Rate | Amount after Discount | Last Month |  |  | This Month |  |  | TOTAL |  |  | Avaiable Qty | BOQ rate less OHP (85%) (A) | Allocation for Material invoice value (75% from A) | MOS Value | Avaiable Qty | BOQ rate less OHP (85%) (A) | Allocation for Material invoice value (75% from A) | MOS Value
[6 empty] | (Dhs.) | after Discount | (Dhs.) | % | Qty | Value | % | Qty | Value | % | Qty | Value |  | 85% | 75% |  |  | 85% | 75%
WATER FEATURES
LEVEL 02
Filtration System
B | Laminated fiberglass Bobbin wound sand filter, 5.9 m3/h, Ø450mm, complete with sand media and manual multiport valve, 1 duty | Aqua, Italy | 1 | Nos | 1130 | 1130 | 918.9708 | 918.9708 | [13 empty] | 0 | 781.1252 | 585.8439 | 0 | MU-450N-VS | WME-SW-MR-ML-00005
C | Plastic self-priming pump, 5.9 m3/h @ 15m head, 1.0HP, 1 duty + 1 standby | Aqua, Italy | 2 | Nos | 1630 | 3260 | 1325.595 | 2651.1901 | [13 empty] | 0 | 1126.7558 | 845.0668 | 0 | EUROSWIM 100M/A | WME-SW-MR-ML-00014
Water Treatment System
D | Automatic pH/RX dosing controller |  | 1 | Nos |  | 0
E | Manual analog dosing pumps - pH (10L/h - 5 bar) |  | 1 | Nos |  | 0
F | Manual analog dosing pumps - RX (10L/h - 5 bar) |  | 1 | Nos |  | 0
| Pre-assembled panel - Twin Dosing System - 10L/h @ 4 bars (pH & Rx) | Aqua, Italy | 1 | Nos | 6030 | 6030 | 4903.8884 | 4903.8884 | [13 empty] | 0 | 4168.3051 | 3126.2288 | 0 | ADPS101 | WME-SW-MR-ML-00005
G | Polyethylene dosing tanks, 125L 100L | Aqua, Italy | 2 | Nos | 530 | 1060 | 431.0217 | 862.0434 | [13 empty] | 0 | 366.3684 | 274.7763 | 0 | ADTANK010 | WME-SW-MR-ML-00005
H | Manual stirrers | Aqua, Italy | 2 | Nos | 410 | 820 | 333.4319 | 666.8638 | [13 empty] | 0 | 283.4171 | 212.5628 | 0 | ADAGMP06 | WME-SW-MR-ML-00005
Fittings
J | Stainless steel main drain, Ø300mm | Astral, Spain | 2 | Nos | 350 | 700 | 284.637 | 569.2739 | [13 empty] | 0 | 241.9414 | 181.4561 | 0 | 00282 | WME-SW-MR-L2-00011
K | Stainless steel floor inlet | Aqua, Italy | 38 | Nos | 710 | 26980 | 577.4064 | 21941.4441 | [13 empty] | 0 | 490.7955 | 368.0966 | 0 | F-230 | WME-SW-MR-ML-00019 WME-SW-MR-ML-00021
L | Stainless steel vacuum point | Aqua, Italy | 1 | Nos | 300 | 300 | 243.9745 | 243.9745 | [13 empty] | 0 | 207.3784 | 155.5338 | 0 | F-240/A | WME-SW-MR-ML-00008
M | Stainless steel overflow fittings | AtecPool, Spain | 54 | Nos | 440 | 23760 | 357.8293 | 19322.7839 | [13 empty] | 0 | 304.1549 | 228.1162 | 0 | 03100282-1 | WME-SW-MR-ML-00010
Overflow Effect System (4mm water film thickness)
N | Overflow effect cast iron pump with cast iron impeller plastic pump, 113.1 m3/h @ 18m head, 15HP, 2 duty | Aqua, Italy | 2 | Nos | 10300 | 20600 | 8376.4594 | 16752.9187 | [13 empty] | 0 | 7119.9905 | 5339.9928 | 0 | KPA1250 | WME-SW-MR-ML-00005
| To Collection Dhs. |  |  |  |  | 84640 |  | 68833.3516
WATER FEATURES (CONT'D)
LEVEL 02 (CONT'D)
Maintenance Kit
A | Vacuum head | Aqua, Italy | 1 | Nos | 830 | 830 | 674.9962 | 674.9962 | [9 empty] | 0 | 573.7468 | 430.3101 | 0
B | Telescopic handle |  | 1 | Nos
C | Vacuum hose |  | 1 | Nos
D | Pool brush |  | 1 | Nos
E | Leaf skimmer |  | 1 | Nos
F | Leaf rake |  | 1 | Nos
G | Algae brush |  | 1 | Nos
H | Hose fitting |  | 1 | Nos
J | Test kit |  | 1 | Nos
Control Panel Board
K | Control Panel Board | Al Fanar/ Scheinder | 1 | Nos | 26250 | 26250 | 21347.7727 | 21347.7727 | [9 empty] | 0 | 18145.6068 | 13609.2051 | 0 | [5 empty] | WME-SW-MR-ML-00028
L | MEP Works including piping, cabling, containment, etc. | Cosmoplast/Atlas/Cepex/Ducab | 1 | Nos | 100000 | 100000 | 81324.8483 | 81324.8483 | [17 empty] | - | WME-SW-MR-ML-00001 WME-SW-MR-ML-00009
M | Testing and Commissioning |  | 1 | Item |  | Included
Underwater lights
N | X-L11 _ LED Neon Flex, SMD 5050, 72 LEDs/m, 12W/m, 3000K, DC24V, IP68 Including: - Aluminium Profiles with self-lock mechanism, IP68 Front connectors and End caps - Driver, 150W, 24V, DALI Dimming, IP67, - Stainless steel deck box |  | 28 | m |  | X-L11 is at high level and excluded from our scope
| X-L7 (as per LT902-LA-L02-SL-0100-00-[D]) (as per VE comparison table & data sheet) | Global Light | 28 | m | 815 | 22820 | 662.7975 | 18558.3304 | [9 empty] | 0 | 563.3779 | 422.5334 | 0 | 7 | 563.3779 | 422.5334 | 2957.7339 |  | WME-SW-MIR-ML-00014 | cost of SS Junction Box (25%)
Water Tanks
| GRP Panel Balancing Tank, 12 m3 (4.0x1.5x2.0m) Non-insulated | Al Bassam - AquaSystem | 1 | Item | 26250 | 26250 | 21347.7727 | 21347.7727 | [13 empty] | 0 | 18145.6068 | 13609.2051 | 0 | - | WME-SW-MR-ML-00007
| To Collection Dhs. |  |  |  |  | 176150 |  | 143253.7202
WATER FEATURES (CONT'D)
LEVEL 04
Filtration System
B | Laminated fiberglass Bobbin wound sand filter, 3.0 m3/h, Ø350mm Ø450mm, complete with sand media and manual multiport valve, 1 duty | Aqua, Italy | 1 | Nos | 1130 | 1130 | 918.9708 | 918.9708 | [13 empty] | 0 | 781.1252 | 585.8439 | 0 | MU-450N-VS | WME-SW-MR-ML-00005
C | Plastic self-priming pump, 3.0 m3/h @ 14m head, 3/4HP, 1 duty + 1 standby | Aqua, Italy | 2 | Nos | 1570 | 3140 | 1276.8001 | 2553.6002 | [13 empty] | 0 | 1085.2801 | 813.9601 | 0 | Euroswim 75M/A | WME-SW-MR-ML-00008
Water Treatment System
D | Automatic pH/RX dosing controller |  | 1 | Nos |  | 0
E | Manual analog dosing pumps - pH (10L/h - 5 bar) |  | 1 | Nos |  | 0
F | Manual analog dosing pumps - RX (10L/h - 5 bar) |  | 1 | Nos |  | 0
| Pre-assembled panel - Twin Dosing System - 10L/h @ 4 bars (pH & Rx) | Aqua, Italy | 1 | Nos | 6030 | 6030 | 4903.8884 | 4903.8884 | [13 empty] | 0 | 4168.3051 | 3126.2288 | 0 | ADPS101 | WME-SW-MR-ML-00005
G | Polyethylene dosing tanks, 125L 100L | Aqua, Italy | 2 | Nos | 530 | 1060 | 431.0217 | 862.0434 | [13 empty] | 0 | 366.3684 | 274.7763 | 0 | ADTANK010 | WME-SW-MR-ML-00005
H | Manual stirrers | Aqua, Italy | 2 | Nos | 410 | 820 | 333.4319 | 666.8638 | [13 empty] | 0 | 283.4171 | 212.5628 | 0 | ADAGMP06 | WME-SW-MR-ML-00005
Fittings
J | Stainless steel main drain, 200x200mm | Aqua, Italy | 2 | Nos | 800 | 1600 | 650.5988 | 1301.1976 | [13 empty] | 0 | 553.009 | 414.7567 | 0 | F-155 | WME-SW-MR-ML-00015
| Stainless steel main drain, Ø300mm | Astral, Spain | 1 | Nos | 350 | 350 | 284.637 | 284.637 | [9 empty] | 0 | 241.9414 | 181.4561 | 0
K | Provision for drain without fittings - Ø20mm |  | 3 | Nos | 180 | 540 | 146.3847 | 439.1542 | [9 empty] | 0 | 124.427 | 93.3203 | 0
Q | Provision for inlet without fittings - Ø20mm |  | 12 | Nos | 180 | 2160 | 146.3847 | 1756.6167 | [9 empty] | 0 | 124.427 | 93.3203 | 0
P | Stainless steel floor inlet | Aqua, Italy | 4 | Nos | 710 | 2840 | 577.4064 | 2309.6257 | [13 empty] | 0 | 490.7955 | 368.0966 | 0 | F-230 | WME-SW-MR-ML-00019
L | Stainless steel vacuum point | Aqua, Italy | 2 | Nos | 300 | 600 | 243.9745 | 487.9491 | [13 empty] | 0 | 207.3784 | 155.5338 | 0 | F-240/A | WME-SW-MR-ML-00008
M | Stainless steel overflow fittings | AtecPool, Spain | 6 | Nos | 440 | 2640 | 357.8293 | 2146.976 | [13 empty] | 0 | 304.1549 | 228.1162 | 0 | 03100282-1 | WME-SW-MR-ML-00010
R | Provision for overflow drain without fittings - Ø20mm |  | 17 | Nos | 180 | 3060 | 146.3847 | 2488.5404 | [9 empty] | 0 | 124.427 | 93.3203 | 0
Cascade System
N | Overflow effect cast iron pump with cast iron impeller, 5.0 m3/h 6.6 m3/h @ 20m head, 10HP, 1 duty (as per WME-SW-SC-L4-0050) | Aqua, Italy | 1 | Nos | 8790 | 8790 | 7148.4542 | 7148.4542 | [13 empty] | 0 | 6076.186 | 4557.1395 | 0 | Euroswim 200M/A | WME-SW-MR-ML-00008
| To Collection Dhs. |  |  |  |  | 34760 |  | 28268.5173
WATER FEATURES (CONT'D)
LEVEL 04 (CONT'D)
Maintenance Kit
A | Vacuum head | Aqua, Italy | 1 | Nos | 830 | 830 | 674.9962 | 674.9962 | [9 empty] | 0 | 573.7468 | 430.3101 | 0
B | Telescopic handle |  | 1 | Nos
C | Vacuum hose |  | 1 | Nos
D | Pool brush |  | 1 | Nos
E | Leaf skimmer |  | 1 | Nos
F | Leaf rake |  | 1 | Nos
G | Algae brush |  | 1 | Nos
H | Hose fitting |  | 1 | Nos
J | Test kit |  | 1 | Nos
Control Panel Board
K | Control Panel Board | Al Fanar/ Scheinder | 1 | Nos | 17500 | 17500 | 14231.8484 | 14231.8484 | [9 empty] | 0 | 12097.0712 | 9072.8034 | 0 | [5 empty] | WME-SW-MR-ML-00028
L | MEP Works including piping, cabling, containment, etc. | Cosmoplast/Atlas/Cepex/Ducab | 1 | Nos | 90000 | 90000 | 73192.3634 | 73192.3634 | [18 empty] | WME-SW-MR-ML-00001 WME-SW-MR-ML-00009
M | Testing and Commissioning |  | 1 | Item |  | Included
Underwater lights
N | X-L4 _ LED Neon Flex, SMD 5050, 72 LEDs/m, 12W/m, 3000K, DC24V, IP68 Including: - Aluminium Profiles with self-lock mechanism, IP68 Front connectors and End caps - Driver, 150W, 24V, DALI Dimming, IP67, - Stainless steel deck box (as per VE comparison table & data sheet) | Global Light | 41 | m | 815 | 33415 | 662.7975 | 27174.6981 | [9 empty] | 0 | 563.3779 | 422.5334 | 0 | 10.25 | 563.3779 | 422.5334 | 4330.9675 |  | DN-21-1613 | cost of SS Junction Box (25%)
P | X-L7 _ LED Neon Flex, SMD 5050, 72 LEDs/m, 12W/m, 4000K, DC24V, IP68 Including: - Aluminium Profiles with self-lock mechanism, IP68 Front connectors and End caps - Driver, 150W, 24V, DALI Dimming, IP67, - Stainless steel deck box (as per VE comparison table & data sheet) | Global Light | 36 | m | 815 | 29340 | 662.7975 | 23860.7105 | [9 empty] | 0 | 563.3779 | 422.5334 | 0 | 9 | 563.3779 | 422.5334 | 3802.8007 |  | DN-21-1613 | cost of SS Junction Box (25%)
Water Tanks
| GRP Panel Balancing Tank, 1.5 m3 (1.0x1.0x1.5m) Non-insulated | Al Bassam - AquaSystem | 1 | Item | 9800 | 9800 | 7969.8351 | 7969.8351 | [13 empty] | 0 | 6774.3599 | 5080.7699 | 0 | - | WME-SW-MR-ML-00007
| To Collection Dhs. |  |  |  |  | 180885 |  | 147104.4518
WATER FEATURES (CONT'D)
LEVEL 23 A, B, & C
Filtration System
B | Laminated fiberglass Bobbin wound sand filter, 18.75 m3/h, Ø750mm, 13.93 m3/h, Ø650mm, complete with sand media and manual multiport valve, 1 duty (as per WME-SW-SC-L23-0062) | Aqua, Italy | 1 | Nos | 1680 | 1680 | 1366.2575 | 1366.2575 | [13 empty] | 0 | 1161.3188 | 870.9891 | 0 | MU-650N-VS | WME-SW-MR-ML-00005
C | Plastic self-priming pump, 18.75 m3/h @ 14m head, 2HP, 13.93 m3/h @ 15m head, 1.5HP, 1 duty + 1 standby (as per WME-SW-SC-L23-0062) | Aqua, Italy | 2 | Nos | 1990 | 3980 | 1618.3645 | 3236.729 | [13 empty] | 0 | 1375.6098 | 1031.7074 | 0 | Euroswim 200M/A | WME-SW-MR-ML-00008
Water Treatment System
D | Automatic pH/RX dosing controller |  | 1 | Nos |  | 0
E | Manual analog dosing pumps - pH (10L/h - 5 bar) |  | 1 | Nos |  | 0
F | Manual analog dosing pumps - RX (10L/h - 5 bar) |  | 1 | Nos |  | 0
| Pre-assembled panel - Twin Dosing System - 10L/h @ 4 bars (pH & Rx) | Aqua, Italy | 1 | Nos | 6030 | 6030 | 4903.8884 | 4903.8884 | [13 empty] | 0 | 4168.3051 | 3126.2288 | 0 | ADPS101 | WME-SW-MR-ML-00018
G | Polyethylene dosing tanks, 125L 100L | Aqua, Italy | 2 | Nos | 530 | 1060 | 431.0217 | 862.0434 | [13 empty] | 0 | 366.3684 | 274.7763 | 0 | ADTANK020 | WME-SW-MR-ML-00005
H | Manual stirrers | Aqua, Italy | 2 | Nos | 410 | 820 | 333.4319 | 666.8638 | [13 empty] | 0 | 283.4171 | 212.5628 | 0 | ADAGMP07 | WME-SW-MR-ML-00005
Fittings
J | Stainless steel main drain, 200x200mm | Aqua, Italy | 6 | Nos | 800 | 4800 | 650.5988 | 3903.5927 | [13 empty] | 6 | 553.009 | 414.7567 | 2488.5404 | F-155 | WME-SW-MR-ML-00015
K | Stainless steel main drain | AtecPool, Spain | 4 | Nos | 440 | 1760 | 357.8293 | 1431.3173 | [9 empty] | 0 | 304.1549 | 228.1162 | 0
| Stainless steel floor inlet | Aqua, Italy | 21 | Nos | 710 | 14910 | 577.4064 | 12125.5349 | [13 empty] | 21 | 490.7955 | 368.0966 | 7730.0285 | F-230 | WME-SW-MR-ML-00019
L | Stainless steel wall inlet | Aqua, Italy | 4 | Nos | 280 | 1120 | 227.7096 | 910.8383 | [13 empty] | 4 | 193.5531 | 145.1649 | 580.6594 | F-219/A | WME-SW-MR-ML-00008
M | Stainless steel vacuum point | Aqua, Italy | 4 | Nos | 300 | 1200 | 243.9745 | 975.8982 | [13 empty] | 4 | 207.3784 | 155.5338 | 622.1351 | F-240/A | WME-SW-MR-ML-00008
N | Stainless steel overflow fittings | AtecPool, Spain | 32 | Nos | 440 | 14080 | 357.8293 | 11450.5386 | [13 empty] | 32 | 304.1549 | 228.1162 | 7299.7184 | 03100282-1 | WME-SW-MR-ML-00010
Overflow Effect System
P | Plastic overflow effect pump, 31.68 m3/h @ 14m head, 4.5HP, 16.2 m3/h @ 15m head, 2HP, 1 duty (WF23A) (as per WME-SW-SC-L23-0062) | Aqua, Italy | 1 | Nos | 1990 | 1990 | 1618.3645 | 1618.3645 | [13 empty] | 0 | 1375.6098 | 1031.7074 | 0 | Euroswim 200M/A | WME-SW-MR-ML-00008
Q | Plastic overflow effect pump, 50.3 m3/h @ 14m head, 5.5HP, 16.2 m3/h @ 15m head, 2HP, 1 duty (WF23B) (as per WME-SW-SC-L23-0062) | Aqua, Italy | 1 | Nos | 1990 | 1990 | 1618.3645 | 1618.3645 | [13 empty] | 0 | 1375.6098 | 1031.7074 | 0 | Euroswim 200M/A | WME-SW-MR-ML-00008
| To Collection Dhs. |  |  |  |  | 55420 |  | 45070.2309
WATER FEATURES (CONT'D)
LEVEL 23 A, B, & C (CONT'D)
Maintenance Kit
A | Vacuum head | Aqua, Italy | 1 | Nos | 830 | 830 | 674.9962 | 674.9962 | [9 empty] | 0 | 573.7468 | 430.3101 | 0
B | Telescopic handle |  | 1 | Nos
C | Vacuum hose |  | 1 | Nos
D | Pool brush |  | 1 | Nos
E | Leaf skimmer |  | 1 | Nos
F | Leaf rake |  | 1 | Nos
G | Algae brush |  | 1 | Nos
H | Hose fitting |  | 1 | Nos
J | Test kit |  | 1 | Nos
Control Panel Board
K | Control Panel Board | Al Fanar/ Scheinder | 1 | Nos | 26250 | 26250 | 21347.7727 | 21347.7727 | [9 empty] | 0 | 18145.6068 | 13609.2051 | 0 | [5 empty] | WME-SW-MR-ML-00028
L | MEP Works including piping, cabling, containment, etc. | Cosmoplast/Atlas/Cepex/Ducab | 1 | Nos | 90000 | 90000 | 73192.3634 | 73192.3634
M | Testing and Commissioning |  | 1 | Item |  | Included
Underwater lights
N | X-L12 _ LED Neon Flex, SMD 5050, 72 LEDs/m, 12W/m, 4000K, DC24V, IP68 Including: - Aluminium Profiles with self-lock mechanism, IP68 Front connectors and End caps - Driver, 150W, 24V, DALI Dimming, IP67, - Stainless steel deck box (as per VE comparison table & data sheet) | Global Light | 12 | m | 815 | 9780 | 662.7975 | 7953.5702 | [9 empty] | 0 | 563.3779 | 422.5334 | 0 | 3 | 563.3779 | 422.5334 | 1267.6002 |  | WME-SW-MIR-ML-00014 | cost of SS Junction Box (25%)
Water Tanks
| GRP Panel Balancing Tank, 6.0 m3 (4.0x1.5x1.0m) Non-insulated | Al Bassam - AquaSystem | 1 | Item | 19110 | 19110 | 15541.1785 | 15541.1785 | [13 empty] | 1 | 13210.0017 | 9907.5013 | 9907.5013 | - | WME-SW-MR-ML-00007
| To Collection Dhs. |  |  |  |  | 145970 |  | 118709.881
WATER FEATURES (CONT'D)
ADDITIONAL ITEMS
A | Pipe acoustic insulations for gravity lines and above critical areas only
| Water Feature @ Level 2 |  | 1 | Nos | 5000 | 5000 | 4066.2424 | 4066.2424 | [9 empty] | 0 | 3456.3061 | 2592.2295 | 0
| Water Feature @ Level 4 |  | 1 | Nos | 4500 | 4500 | 3659.6182 | 3659.6182 | [9 empty] | 0 | 3110.6754 | 2333.0066 | 0
| Water Features @ Level 23 |  | 1 | Nos | 13500 | 13500 | 10978.8545 | 10978.8545 | [9 empty] | 0 | 9332.0263 | 6999.0198 | 0
| TOTAL FOR MOS IN WATER FEATURES | [9 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 40987.6854
FOR CHECKING PURPOSES ONLY
[21 empty] | 0 |  |  |  | 40987.6854

## ACRYLIC MOS
PLOT-18 | [5 empty] | WM Ref. No.: D20/054-12/C
BILL OF QUANTITIES | [5 empty] | Date: 06-05-2021 | [17 empty] | Discount Rate
BILL :- ACRYLIC WALL PANELS | [23 empty] | 81.32%
[15 empty] | WM MOS Claim |  |  | WM-Khansaheb MOS Claim - February 2023 |  |  |  | ITEM CODE | MIR | 18.68%
Item | Description | Make | Qty. | Unit | Rate | Amount | Rate | Amount after Discount | Last Month |  |  | This Month |  |  | TOTAL |  |  | Avaiable Qty | BOQ rate less OHP (85%) (A) | Allocation for Material invoice value (75% from A) | MOS Value
[6 empty] | (Dhs.) | after Discount | (Dhs.) | % | Qty | Value | % | Qty | Value | % | Qty | Value |  | 90% | 91.89%
SWIMMING POOL ACRYLIC WALLS
LEVEL 10
Acrylic Pool Walls
A | Acrylic Pool Walls Panel 1-A - 4240(L)x1350(Viewing Height)x100mm(t) _ 0 join Panel 1-B - 11240(L)x1350(Viewing Height)x100mm(t) _ 1 join | Exclusive Acrylic | 1 | Item | 383000 | 383000 | 311474.1689 | 311474.1689 | [9 empty] | 0 | 280326.752 | 257585.8904 | 0 |  | WME-SW-MR-ML-00022_00 WME-SW-MR-L10-00031
LEVEL 26
Acrylic Pool Walls
B | Acrylic Pool Walls Panel 2-A - 3300(L)x1250(Viewing Height)x90mm(t) _ 0 join Panel 2-B - 9290(L)x1250(Viewing Height)x90mm(t) _ 1 join | Exclusive Acrylic | 1 | Item | 282380 | 282380 | 229645.1066 | 229645.1066 | [9 empty] | 0 | 206680.5959 | 189914.109 | 0 |  | WME-SW-MR-ML-00022_00 WME-SW-MR-L26-00024_00
| TOTAL FOR MOS IN ACRYLIC POOL WALLS |  |  |  |  | 665380 |  | 541119.2754 |  |  | 0 |  |  | 0 | [6 empty] | 0
0
FOR CHECKING PURPOSES ONLY