## 1172-001 (hidden)
PAYMENT APPLICATION
M/s. | Khansaheb Civil Engineering L.L.C | [5 empty] | 2023-01-20
| Al Rashidiya | [5 empty] | PY-2879-1172-008
PO Box. 2716
Dubai , United Arab Emirates
Attn: | Chris McCann
Project Manager
Project Name/ Title: |  | Dorchester Hotel & Residences
Sub-Contract Agreement No.: |  | SC Ref No. 201A220002/K100/KD/SK/0045 Dated On 2nd June 2022
Date of Performance: |  | From 21st Dec 2022 to 20th Jan 2023
L-25 & ABOVE PREPACKEDSCREED
Dear Sir,
We are submitting the completed measurements as attached and invoice bill as follows:
S.R. No. | Particular | Previous |  | Current |  | Cummulative |  |  | =K29-D32
|  | Area (m2) | Amount (AED) | Area (m2) | Amount (AED) | Area (m2) | Amount (AED) |  | 386401.7729 | =H32-K29
1 | Supply and Installation of Floor Screed | 4114.29 | 319733.8805 | 2556.554 | 215680.2998 | 6670.844 | 535414.1803 |  | 9156.71 | 664354.5214 | 9156.71 | 664354.5214 | 535414.1803 | 6670.844
2 | Supply and Installation Insulation | 1286.28 | 66667.8924 | 1199.586 | 62272.4487 | 2485.866 | 128940.3411 |  | 400 | -799.586 | 2485.866 |  | 128940.3411 | 2485.866
TOTAL AMOUNT |  | 5400.57 | 386401.7729 | 3756.14 | 277952.7485 | 9156.71 | 664354.5214
|  |  |  | Less: Previous Certified Amount (Dec -22) |  |  | 378896.84 |  |  | BOQ QTY | SUM QTY | BOQ AMT | SUM AMT
|  |  |  | Sub Total |  |  | 285457.6814 |  |  | 9156.71 | 9156.71 | 646056.2417 | 664354.5214
|  |  |  | Less: 10% Retention |  |  | 28545.7681 |  |  | OK | OK | NOT OK | NOT OK
|  |  |  | Net Amount due to this Invoice = |  |  | 256911.9133 | 980.12 | 69891.2986
Amount in words: Two Hundred Fifty Six Thousand Four and 40/100 Dirhams Only ***
“It is hereby declared and agreed that if the Value Added Tax (VAT)is applicable to receipts of this invoice retrospectively from inception or prospectively from the date of implementation of VAT, the company reserves its right to collect the same from the recipient of this invoice and whose name is written above, in line with the impending VAT laws and regulations as implemented in the UAE.”
This is for your kind approval and further proceedings.
Thanks and best regards,
Sr. Project Manager | [5 empty] | Mr. Sreeraj Raju
QS Manager
Mobile #: 055-1658707
Email: sreeraj.raju@gcsconcrete.ae

## Summary
GCS Progress Assessment
No | Description | Amount
Cumulative
| Original Scope | 576112.9433
| Variation | 69943.2984
646056.2417
| Previous Certified (Dec 22) | 378896.84
267159.4017
| Retention (10%) | 26715.9402
240443.4616

## BOQ
BOQ Summary | [11 empty] | 2023-01-20
PY-2879-1172-008
ITEM | Description | REMAINING AREA AS PER KHANSAHEB LATESR QUOTE |  |  |  | GCS Monthly claim
[6 empty] | Previous |  | Current |  | Cumulative
|  | UNIT | RATE | Area (m2) | Amount (AED) | Area (m2) | Amount (AED) | Area (m2) | Amount (AED) | Area (m2) | Amount (AED) | Remarks
A | SCREED WORKS
Basement wet areas and podium areas in 10th,17th, 23rd and 29th Levels
Supply and Apply of sand cement level screed as drawing A-6522 section detail 8
A | From 51mm to 60mm | m2 | 57.69 |  | Rate Only | 0 | 0 | 144.688 | 9972.1863 | 144.688 | 9972.1863
B | From 41mm to 50mm | m2 | 54.74 |  | Rate Only | 235.93 | 12914.8082 | 0 | 0 | 235.93 | 12914.8082 |  | 45.5 | 10.7348
C | From 61mm to 70mm | m2 | 62.25 |  | Rate Only | 139.12 | 8660.22 | 237.631 | 17413.1244 | 376.751 | 26073.3444 |  | 65.5 | 24.6772
D | From 71mm to 80mm | m2 | 65.05 |  | Rate Only | 0 | 0 | 426.5 | 33110.901 | 426.5 | 33110.901 |  |  | 0
E | From 81mm to 90mm | m2 | 68.95 |  | Rate Only | [8 empty] | 0
F | From 91mm to 100mm | m2 | 73.11 |  | Rate Only | [8 empty] | 0
0
| Balconies/Terraces | [12 empty] | 0
0
| Supply and Apply of Screed (unbonded) to falls, minimum of 70-100mm thick as drawing A-6523 detail 5 | [12 empty] | 0
0
G | From 71mm to 80mm | m2 | 91.4 |  | Rate Only | [8 empty] | 0
H | From 61mm to 70mm | m2 | 87.37 | 753.97 | 65874.3589 | 953.7 | 83324.769 | 79.3 | 6928.441 | 1033 | 90253.21 | Pre-Pcked Screed Due to Logistic Constaints and for Balcony Area | 65.5 | 67.6615
J | From 81mm to 90mm | m2 | 98.97 |  | Rate Only | [8 empty] | 0
K | From 91mm to 100mm | m2 | 105.57 |  | Rate Only | [8 empty] | 0
0
| Supply and Laying of 25mm thick Rigid Insulation in accordance with the specifications and drawings | [12 empty] | 0
L | To Horizontal |  |  |  |  | 961.95 | 49857.8685 | 381.381 | 19864.8835 | 1343.331 | 69722.752 |  |  | 0
0
| Supply and Laying of 25mm thick Rigid Insulation (XPS Insulation, density 32-35 kg/m3) | [12 empty] | 0
M | To Horizontal | m2 | 51.83 | 753.97 | 39078.27 | 324.33 | 16810.0239 | 818.205 | 42407.5651 | 1142.535 | 59217.589 | Due to increase in Raw Material Prices the Rate for Insulation is Increased |  | 0
0
| Podium areas in Ground, 2nd, 4th Levels | [12 empty] | 0
0
| Supply and Apply of Screed (unbonded) to falls, minimum of 70-100mm thick as drawing A-6522 detail 7 | [12 empty] | 0
A | From 71mm to 80mm | m2 | 65.05 |  | Rate Only | [7 empty] | 75.5 | 0
B | From 61mm to 70mm | m2 | 62.25 |  | Rate Only | [7 empty] | 65.5 | 0
C | From 81mm to 90mm | m2 | 68.95 |  | Rate Only | [7 empty] | 85.5 | 0
D | From 91mm to 100mm | m2 | 73.11 |  | Rate Only | 101.48 | 7419.2028 | 0 | 0 | 101.48 | 7419.2028 |  | 95.5 | 9.6913
0
| Supply and Laying of 50mm thick Rigid Insulation in accordance with the specifications and drawings | [12 empty] | 0
E | To Horizontal | [12 empty] | 0
0
| Supply and Laying of 50mm thick Rigid Insulation (XPS Insulation, density 32-35 kg/m3) | [12 empty] | 0
F | To Horizontal | m2 | [11 empty] | 0
0
| Supply and Apply cement unbonded sand screed to receive finishes all in accordance with the contract requirements, drawings and specifications based on readymix concrete screed from DM approved supplier as drawing A-6523 detail 3 | [12 empty] | 0
A | Hotel tower suites upto 51mm to 60mm | m2 | 57.69 | 796.27 | 45936.82 | 1103.42 | 63656.2998 | 502.56 | 34637.4403 | 1605.98 | 98293.7401 | Due to the increase in Raw Material Prices (Sand,Cement, Diese etc.) there is a increaseb in the cost further all Additional Rate only items is included in this Rates | 55.5 | 89.1319
B | Hotel tower corridors upto 51mm to 60mm | m2 | 57.69 |  | Rate Only | [8 empty] | 0
C | Apartment tower suites upto 51mm to 60mm | m2 | 57.69 |  | Rate Only | [8 empty] | 0
D | Apartment tower corridors upto 51mm to 60mm | m2 | 57.69 |  | Rate Only | [8 empty] | 0
E | All other areas upto 51mm to 60mm | m2 | 57.69 |  | Rate Only | [8 empty] | 0
F | From 41mm to 50mm | m2 | 54.74 |  | Rate Only | [8 empty] | 0
G | Ditto from 61mm to 70mm | m2 | 62.25 |  | Rate Only | 245.78 | 15299.805 | 275.765 | 20207.5077 | 521.545 | 35507.3127 |  |  | 0
H | Ditto from 71mm to 80mm | m2 | 65.05 | 915.74 | 59568.89 | 188.41 | 12256.0705 | 0 | 0 | 188.41 | 12256.0705 | Due to the increase in Raw Material Prices (Sand,Cement, Diese etc.) there is a increaseb in the cost further all Additional Rate only items is included in this Rates |  | 0
J | Ditto from 81mm to 90mm | m2 | 68.95 |  | Rate Only | [8 empty] | 0
K | Ditto from 91mm to 100mm | m2 | 73.11 |  | Rate Only | 49.47 | 3616.7517 | 0 | 0 | 49.47 | 3616.7517 |  |  | 0
0
| Supply and Apply cement unbonded sand screed to receive finishes all in accordance with the contract requirements, drawings and specifications based on readymix concrete screed from DM approved supplier as drawing A-6522 detail 3 | [12 empty] | 0
L | From 51mm to 60mm | m2 | 80.37 | 354.88 | 28521.71 | 410.46 | 32988.6702 | 0 | 0 | 410.46 | 32988.6702 | Pre-Pcked Screed Due to Logistic Constaints for Higher Level Areas | 55.5 | 22.7805
M | From 41mm to 50mm | m2 |  |  | Rate Only | 29 | 2330.73 | 0 | 0 | 29 | 2330.73 |  | 45.5 | 1.3195
N | From 61mm to 70mm | m2 | 87.37 |  | Rate Only | 48.02 | 4195.5074 | 0 | 0 | 48.02 | 4195.5074 |  | 65.5 | 3.1453
P | From 71mm to 80mm | m2 | 91.4 |  | Rate Only | 59.31 | 4915.014 | 0 | 0 | 59.31 | 4915.014 |  | 75.5 | 4.4779
Q | From 81mm to 90mm | m2 | 98.97 |  | Rate Only | [6 empty] | Pre-Packed Variation for higher thickness V. Ref: GCS-UAE-EY-VA-DR-SC1583-01 |  | 0
R | From 91mm to 100mm | m2 | 105.57 |  | Rate Only | [8 empty] | 0
| From 101mm to 110mm | m2 | 112.17 |  | Rate Only | [8 empty] | 0
| From 111mm to 120mm | m2 | 118.87 |  | Rate Only | 0 | 0 | 424.823 | 42695.986 | 606.89 | 42695.986 |  |  | 0
| From 121mm to 130mm | m2 | 125.67 |  | Rate Only | [8 empty] | 0
| From 131mm to 140mm | m2 | 132.57 |  | Rate Only | [8 empty] | 0
| From 141mm to 150mm | m2 | 139.57 |  | Rate Only | [8 empty] | 0
| From 151mm to 160mm | m2 | 146.67 |  | Rate Only | [8 empty] | 0
| From 161mm to 170mm | m2 | 153.87 |  | Rate Only | [8 empty] | 0
| From 171mm to 180mm | m2 | 161.17 |  | Rate Only | 137.71 | 22194.7207 | 0 | 0 | 137.71 | 22194.7207 |  | 175.5 | 24.1681
| From 181mm to 190mm | m2 | 168.57 |  | Rate Only | [8 empty] | 0
| From 191mm to 200mm | m2 | 176.07 |  | Rate Only | [8 empty] | 0
0
0
| Supply and Apply cement unbonded sand screed to receive finishes all in accordance with the contract requirements, drawings and specifications based on readymix concrete screed from DM approved supplier as drawing A-6522 detail 3 | [12 empty] | 0
A | Upto 150mm | m2 | 96.13 |  | Rate Only | 87.74 | 8434.4462 | 0 | 0 | 87.74 | 8434.4462 |  | 150 | 13.161
B | 6mm reinforcement in screed for crack control | [12 empty] | 0
0
| Supply and Laying of Regupol 7210 C Acoustic Underlay insulation including perimeter strips and masking tape (Airborne Sound Insulation: 49 dB DnTw) as per the drawing and specification | [12 empty] | 0
C | 5mm thick; 49dB DnTw | [12 empty] | 0
0
| Additional Items The Subcontractor is to detail below any additional items with quantities and rates not previously included to complete the build up of the lump sum Subcontractor fail to insert any items hereunder, it will be deemed that his lump sum price for the Subcontract includes all works as required by the tender drawings and specification and no subsequent claim for any additional item will be entertained | [12 empty] | 0
A | Additional Pump bosting charges for level 25 and above | [12 empty] | 0
0
| Variation | [12 empty] | 0
| As per the Ref.GCS-UAE-EY-VA-BB-SC1409-00 on 5th january 2021 Supply and Apply of Un-Bonded Diamond Poly Fibre Modified Screed System (Dry density 20250+/-50Kg/m3), with 500 guage Ploythene Sheet as a seperation layer to receive finishes. Surface Regularity 1/2, in situ crushing resistance category A/B, compressive strength between20-25 MPa after 28 days, all in accordance with BS 8204.01.2003 | [12 empty] | 0
| Up to 170 mm | m2 | 98.4 |  |  | 0 | 0 | 29.34 | 3718.4929 | 29.34 | 3718.4929 |  |  | 0
| Up to 180 mm | m2 | 114.25 | 3558.39 | 406546.06 | 263.98 | 30159.715 | 41.57 | 4749.3725 | 305.55 | 34909.0875 | In our Previous Price Quote this thickness was not included but as per Site condition this thickness is coming in the Ground ,Level 2 & Level 4 areas so it is included in the BOQ | 180 | 54.999 | 34909.0875 | 0 | 105.25 | 32159.1375
| Up to 190 mm | m2 | 112.8 |  |  | 0 | 0 | 212.31 | 23948.568 | 212.31 | 23948.568 |  |  | 0
| Up to 200 mm | m2 | 121.25 |  |  | 60.76 | 7367.15 | 0 | 0 | 60.76 | 7367.15 |  | 200 | 12.152
TOTAL = |  |  |  | 7133.22 | 645526.0889 | 5400.57 | 386401.7729 | 3574.073 | 259654.4688 | 9156.71 | 646056.2417 |  |  | 338.1001
|  |  |  | 7133.22 | 645526.09
[10 empty] | 0 | 18298.2797
Note on J72: Himal Kosala: Not Include in Original Scope
Note on L72: Himal Kosala: Not Include in Original Scope
Note on L78: Himal Kosala: Not Include in Original Scope

## sum-screed (hidden)
Summary | [5 empty] | 2023-01-20
PY-2879-1172-008
S.R. No. | Particular | Previous |  | Current |  | Cummulative
|  | Area (m2) | Amount (AED) | Area (m2) | Amount (AED) | Total (m2) | Total Amt (AED)
SCREED MEASUREMENT | [7 empty] | current | cumu
1 | Basement-01 | 173.41 | 16279.3079 | 111.938 | 7714.9908 | 285.348 | 23994.2987 | 0.3546 | 25.2422
2 | GROUND FLOOR | 1294.57 | 105144.4533 | 573.47 | 43105.3057 | 1868.04 | 148249.759 |  | 132.1221
3 | LEVEL 01 | 19.2 | 1248.96 | 0 | 0 | 19.2 | 1248.96 |  | 1.44
4 | LEVEL 02 | 108.77 | 6274.9413 | 81.4 | 9181.92 | 190.17 | 15456.8613 |  | 8.0351
5 | LEVEL 03
6 | LEVEL 04 | 627.31 | 43973.5591 | 130.91 | 14766.648 | 758.22 | 58740.2071 |  | 66.4106
7 | LEVEL 05 | 31.58 | 3829.075 | 0 | 0 | 31.58 | 3829.075 | 0 | 6.316
8 | LEVEL 06 | 174.74 | 12083.8274 | 0 | 0 | 174.74 | 12083.8274 | 0 | 11.8823
9 | LEVEL 07 | 0 | 0 | 26.316 | 1928.3838 | 26.316 | 1928.3838
10 | LEVEL 08 | 10 | 622.5 | 0 | 0 | 10 | 622.5 |  | 0.68
11 | LEVEL 09
12 | LEVEL 10 | 0 | 0 | 247.91 | 18166.349 | 247.91 | 18166.349
13 | LEVEL 14 | 14 | 1125.18 | 0 | 0 | 14 | 1125.18 |  | 0.7
14 | LEVEL 15
15 | LEVEL 16 | 15 | 1205.55 | 9.306 | 681.9251 | 24.306 | 1887.4751 |  | 1.3828
16 | LEVEL 17
17 | LEVEL 18 | 139.12 | 8660.22 | 0 | 0 | 139.12 | 8660.22 | 0 | 9.4602
18 | LEVEL 19 | 259.3 | 15421.5027 | 0 | 0 | 259.3 | 15421.5027 | 0 | 13.4439
19 | LEVEL 20 | 22 | 1922.14 | 0 | 0 | 22 | 1922.14 | 0 | 1.496
20 | LEVEL 21 | 0 | 0 | 9.153 | 670.7135 | 9.153 | 670.7135 |  | 1.5844
21 | LEVEL 22 | 23.3 | 2035.721 | 0 | 0 | 23.3 | 2035.721 | 0 | 1.5844
22 | LEVEL 23 | 124.3 | 10819.771 | 670.565 | 50852.8371 | 794.865 | 61672.6081 |  | 44.4913
23 | LEVEL 24
24 | LEVEL 25 | 114.6 | 7108.5876 | 9.396 | 688.5201 | 123.996 | 7797.1077 | 0.63893 | 8.3874
25 | LEVEL 26 | 504.24 | 43532.2688 | 0 | 0 | 504.24 | 43532.2688 | 0 | 33.6904
26 | LEVEL 27 | 349.94 | 30409.8306 | 21.85 | 1909.0345 | 371.79 | 32318.8651 | 1.4858 | 25.2374
27 | LEVEL 28 | 45.08 | 4055.9932 | 57.45 | 5019.4065 | 102.53 | 9075.3997 | 0 | 7.1759
28 | LEVEL 29 | 39.31 | 2638.2668 | 606.89 | 60994.2657 | 646.2 | 63632.5325 | 0 | 2.5235
29 | LEVEL 30 | 24.52 | 1342.2248 | 0 | 0 | 24.52 | 1342.2248 | 0 | 1.226
TOTAL AMOUNT |  | 4114.29 | 319733.8805 | 2556.554 | 215680.2998 | 6670.844 | 535414.1803 | 2.1247 | 404.5119
[8 empty] | 5.432 | 2698.4355

## sum -insulation (hidden)
Summary | [5 empty] | 2023-01-20
PY-2879-1172-008
S.R. No. | Particular | Previous |  | Current |  | Cummulative
|  | Area (m2) | Amount (AED) | Area (m2) | Amount (AED) | Total (m2) | Total Amt (AED)
INSULATION MEASUREMENT | [7 empty] | current | cumu
1 | Basement-01 | 49.37 | 2558.8471 | 0 | 0 | 49.37 | 2558.8471
2 | LEVEL 1
3 | LEVEL 2
4 | LEVEL 3
5 | LEVEL 4
6 | LEVEL 5
7 | LEVEL 6 | 174.74 | 9056.7742 | 0 | 0 | 174.74 | 9056.7742
8 | LEVEL 7 | 0 | 0 | 26.316 | 1363.9583 | 26.316 | 1363.9583
9 | LEVEL 8 | 10 | 518.3 | 0 | 0 | 10 | 518.3
10 | LEVEL 10 | 0 | 0 | 247.91 | 12849.1753 | 247.91 | 12849.1753
11 | LEVEL 15 | [6 empty] | 0 | 0
12 | LEVEL 16 | 0 | 0 | 9.306 | 482.33 | 9.306 | 482.33 | 0 | 0
13 | LEVEL 17 | [6 empty] | 0 | 0
14 | LEVEL 18 | 139.12 | 7210.5896 | 0 | 0 | 139.12 | 7210.5896 | 0 | 0
15 | LEVEL 19 | [6 empty] | 0 | 0
16 | LEVEL 20 | 22 | 1140.26 | 0 | 0 | 22 | 1140.26 | 0 | 0
17 | LEVEL 21 | 0 | 0 | 9.153 | 474.4 | 9.153 | 474.4 | 0 | 0
18 | LEVEL 22 | 23.3 | 1207.639 | 0 | 0 | 23.3 | 1207.639 | 0 | 0
19 | LEVEL 23 | 90.54 | 4692.6882 | 211.315 | 10952.4564 | 301.855 | 15645.1446 | 0 | 0
20 | LEVEL 24
21 | LEVEL 25 | 109.06 | 5652.5798 | 9.396 | 584.901 | 118.456 | 6237.4808
22 | LEVEL 26 | 307.79 | 15952.7557 | 0 | 0 | 307.79 | 15952.7557
23 | LEVEL 27 | 344.4 | 17850.252 | 21.85 | 1132.4855 | 366.25 | 18982.7375
24 | LEVEL 28 | 15.96 | 827.2068 | 57.45 | 2977.6335 | 73.41 | 3804.8403
25 | LEVEL 29 | 0 | 0 | 606.89 | 31455.1087 | 606.89 | 31455.1087
TOTAL AMOUNT |  | 1286.28 | 66667.8924 | 1199.586 | 62272.4487 | 2485.866 | 128940.3411 | 0 | 0

## sc--b-01
GCS German Concrete Works LLC
Screed Measurements - Basement-01 | [8 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | Room Number | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) | current qty | current volume | cumulative volume | cumulative volume
[5 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 51mm to 60mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Zone-03 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Upto 180mm thick
1 | AREA-01 GL 01 -02 MONTH OF JULY 22 |  | 180 | 114.25 | 23.02 | 2630.035 |  |  | 23.02 | 2630.035 | 0 | 0 | 23.02 | 4.1436
2 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
Upto 150mm thick | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
1 | Loading Dock GL 17-18 |  | 150 | 96.13 | 87.74 | 8434.4462 |  |  | 87.74 | 8434.4462 | 0 | 0 | 87.74 | 13.161
Upto 200mm thick | [10 empty] | 0 | 0 | 0 | 0
1 | AREA-01 GL A-D MONTH OF JULY 22 |  | 200 | 121.25 | 13.18 | 1598.075 |  | 0 | 13.18 | 1598.075 | 0 | 0 | 13.18 | 2.636
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
From 81mm to 90mm thick | [10 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
From 91mm to 100mm thick | [10 empty] | 0 | 0 | 0 | 0
1 | EXTERNAL SEATING AREA |  | 100 | 73.11 | 49.47 | 3616.7517 |  |  | 49.47 | 3616.7517 | 0 | 0 | 49.47 | 4.947
From 51mm to 60mm thick
1 | Flower cold room |  | 60 | 68.922 |  |  | 7 | 482.454 | 7 | 482.454
2 | Bevarage cold room-02 |  | 60 | 68.922 |  |  | 19.46 | 1341.2221 | 19.46 | 1341.2221
3 | Bevarage cold room-01 |  | 60 | 68.922 |  |  | 9 | 620.298 | 9 | 620.298
4 | General purpose cold room |  | 60 | 68.922 |  |  | 13.51 | 931.1362 | 13.51 | 931.1362
5 | Block ice production room |  | 60 | 68.922 |  |  | 14.283 | 984.4129 | 14.283 | 984.4129
6 | Freezer room 1&2 |  | 60 | 68.922 |  |  | 15 | 1033.83 | 15 | 1033.83
7 | Fish cold room |  | 60 | 68.922 |  |  | 3.3 | 227.4426 | 3.3 | 227.4426
8 | Seafood cold room |  | 60 | 68.922 |  |  | 4.45 | 306.7029 | 4.45 | 306.7029
9 | Prepare food cold room1 |  | 60 | 68.922 |  |  | 3.69 | 254.3222 | 3.69 | 254.3222
10 | Feezer Room |  | 60 | 68.922 |  |  | 5.16 | 355.6375 | 5.16 | 355.6375
11 | Holding cold room |  | 60 | 68.922 |  | 0 | 5.91 | 407.329 | 5.91 | 407.329 | 5.91 | 0.3546 | 5.91 | 0.3546
12 | cold room LB168 |  | 60 | 68.922 |  |  | 5.91 | 407.329 | 5.91 | 407.329
13 | cold room LB1191 |  | 60 | 68.922 |  |  | 5.265 | 362.8743 | 5.265 | 362.8743
14 |  |  | 60 | 57.69 |  |  |  | 0 | 0 | 0
15 |  |  | 60 | 57.69 |  |  |  | 0 | 0 | 0
16 |  |  | 60 | 57.69 |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL (Screed Measurements - Basement-01 ) = |  |  |  |  | 173.41 | 16279.3079 | 111.938 | 7714.9908 | 285.348 | 23994.2987 | 5.91 | 0.3546 | 179.32 | 25.2422
[9 empty] | 285.348 | 23994.2987
0
| Upto 180mm thick |  |  |  | 23.02 | 2630.035 | 0 | 0 | 23.02 | 2630.035
| Upto 150mm thick |  |  |  | 87.74 | 8434.4462 | 0 | 0 | 87.74 | 8434.4462
| Upto 200mm thick |  |  |  | 13.18 | 1598.075 | 0 | 0 | 13.18 | 1598.075
| From 91mm to 100mm thick |  |  |  | 49.47 | 3616.7517 | 0 | 0 | 49.47 | 3616.7517
| From 51mm to 60mm thick |  |  |  | 0 | 0 | 111.938 | 7714.9908 | 111.938 | 7714.9908
| TOTAL |  |  |  | 173.41 | 16279.3079 | 111.938 | 7714.9908 | 285.348 | 23994.2987
Note on E42: Himal Kosala: 90% until Variation Approval
Note on E43: Himal Kosala: 90% until Variation Approval
Note on E44: Himal Kosala: 90% until Variation Approval
Note on E45: Himal Kosala: 90% until Variation Approval
Note on E46: Himal Kosala: 90% until Variation Approval
Note on H46: Himal Kosala: WIR is excluded this
Note on E47: Himal Kosala: 90% until Variation Approval
Note on E48: Himal Kosala: 90% until Variation Approval
Note on E49: Himal Kosala: 90% until Variation Approval
Note on E50: Himal Kosala: 90% until Variation Approval
Note on E51: Himal Kosala: 90% until Variation Approval
Note on E52: Himal Kosala: 90% until Variation Approval
Note on E53: Himal Kosala: 90% until Variation Approval
Note on E54: Himal Kosala: 90% until Variation Approval
Note on H54: Himal Kosala: WIR is excluded this

## SC-GL
GCS German Concrete Works LLC
Screed Measurements - Ground floor | [9 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | Room Number | wir no | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) | current qty | current volume | cumulative volume | cumulative volume
[6 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 51mm to 60mm thick
1 | AREA-01 MONTH OF AUG-22 |  | GCS-LX-WR-GF-00398_00_B | 60 | 57.69 | 21.32 | 1229.9508 |  |  | 21.32 | 1229.9508 | 0 | 0 | 21.32 | 1.2792
2 | AREA-02 MONTH OF AUG-22 |  | GCS-LX-WR-GF-00398_00_B | 60 | 57.69 | 23.15 | 1335.5235 |  |  | 23.15 | 1335.5235 | 0 | 0 | 23.15 | 1.389
3 | AREA-03 MONTH OF AUG-22 |  | GCS-LX-WR-GF-00398_00_B | 60 | 57.69 | 81.56 | 4705.1964 |  |  | 81.56 | 4705.1964 | 0 | 0 | 81.56 | 4.8936
4 | AREA-04 MONTH OF AUG-22 |  | GCS-LX-WR-GF-00398_00_B | 60 | 57.69 | 6.88 | 396.9072 |  |  | 6.88 | 396.9072 | 0 | 0 | 6.88 | 0.4128 | From 91mm to 100mm | m2 | 73.11
5 | AREA-05 MONTH OF AUG-22 |  | GCS-LX-WR-GF-00391_01_B | 60 | 57.69 | 109.67 | 6326.8623 |  |  | 109.67 | 6326.8623 | 0 | 0 | 109.67 | 6.5802
6 | LPG Tank |  | GCS-LX-WR-GF-00406 | 60 | 57.69 | 91 | 5249.79 |  |  | 91 | 5249.79 | 0 | 0 | 91 | 5.46
7 | AREA-01 MONTH OF SEP-22 (PLANTER AREA ) |  | GCS-LX-WR-GF-00416 | 60 | 57.69 | 31 | 1788.39 |  |  | 31 | 1788.39 | 0 | 0 | 31 | 1.86
8 | AREA-02 MONTH OF SEP-22 (PLANTER AREA GL 8-11 ) |  | GCS-LX-WR-GF-00416 | 60 | 57.69 | 117 | 6749.73 |  |  | 117 | 6749.73 | 0 | 0 | 117 | 7.02
9 | AREA-03 MONTH OF SEP-22 (PLANTER AREA GL 17-18 ) |  | GCS-LX-WR-GF-00416 | 60 | 57.69 | 23 | 1326.87 |  |  | 23 | 1326.87 | 0 | 0 | 23 | 1.38
10 | AREA -01 MONTH NOV -2022 |  | GCS-LX-WR-GF-00442 | 60 | 57.69 | 71.47 | 4123.1043 |  |  | 71.47 | 4123.1043 | 0 | 0 | 71.47 | 4.2882
11 | LANDSCAPE AREA NOV-2022 |  | GCS-LX-WR-GF-00432 | 60 | 57.69 | 222.37 | 12828.5253 |  |  | 222.37 | 12828.5253 | 0 | 0 | 222.37 | 13.3422
12 | Planter area GL 07-11 AREA-01 MONTH OF JAN -23 |  |  | 60 | 68.922 |  |  | 162 | 11165.364 | 162 | 11165.364
13 | Planter area GL 01-07 & A-D AREA-02 MONTH OF JAN -23 |  |  | 60 | 68.922 |  |  | 99 | 6823.278 | 99 | 6823.278
14 | AREA -03 MONTH JAN -23 GL 11-18 & C-I |  |  | 60 | 68.922 |  |  | 222.3 | 15321.3606 | 222.3 | 15321.3606
15 | AREA -04 MONTH JAN -23 GL 18-21 & Y-Z |  |  | 60 | 68.922 |  |  | 19.26 | 1327.4377 | 19.26 | 1327.4377
16 |  |  |  | 60 | 57.69 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 |  |  |  | 60 | 57.69 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 91mm to 100mm thick | [11 empty] | 0 | 0 | 0 | 0
1 | ATTIC SLAB AREA REF oct-22 drawing |  | GCS-AX-WR-GF-00419 | 100 | 73.11 | 93 | 6799.23 |  |  | 93 | 6799.23 | 0 | 0 | 93 | 9.3
2 | COLD ROOM 2 NOS |  | GCS-AX-WR-GF-00431 | 100 | 73.11 | 8.48 | 619.9728 |  |  | 8.48 | 619.9728 | 0 | 0 | 8.48 | 0.848
Upto 170 mm thick
1 | AREA -05 MONTH JAN -23 GL 24 & A-U |  |  | 170 | 126.738 |  |  | 29.34 | 3718.4929 | 29.34 | 3718.4929
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Upto 180 mm thick | [11 empty] | 0 | 0 | 0 | 0
1 | FEMALE WC | 36 | GCS-AX-WR-GF-00413 | 175 | 114.25 | 55.72 | 6366.01 |  |  | 55.72 | 6366.01 | 0 | 0 | 55.72 | 9.751
2 | BALL ROOM VESTIBULE |  | GCS-AX-WR-GF-00411 | 175 | 114.25 | 59.64 | 6813.87 |  |  | 59.64 | 6813.87 | 0 | 0 | 59.64 | 10.437
3 | LIFT LOBBY |  | GCS-AX-WR-GF-00422 | 180 | 114.25 | 41.47 | 4737.9475 |  |  | 41.47 | 4737.9475 | 0 | 0 | 41.47 | 7.4646
4 | STORAGE AREA |  | GCS-AX-WR-GF-00422 | 180 | 114.25 | 4.37 | 499.2725 |  |  | 4.37 | 499.2725 | 0 | 0 | 4.37 | 0.7866
5 | BALL ROOM AREA REF OCT-22 DRAWING |  | GCS-AX-WR-GF-00422 | 180 | 114.25 | 35.54 | 4060.445 |  |  | 35.54 | 4060.445 | 0 | 0 | 35.54 | 6.3972
9 | ROOFTOP POOL LOBBY |  | GCS-AX-WR-GF-00438 | 175 | 114.25 | 44.22 | 5052.135 |  |  | 44.22 | 5052.135 | 0 | 0 | 44.22 | 7.7385
10 | Room service support area GL 19-20 | 43 |  | 175 | 114.25 |  |  | 15 | 1713.75 | 15 | 1713.75
11 | Mech Room | 45 |  | 175 | 114.25 |  |  | 2.6 | 297.05 | 2.6 | 297.05
12 | Ball room areas gl 20-24 & |  |  | 175 | 114.25 |  |  | 23.97 | 2738.5725 | 23.97 | 2738.5725 | 23.97 | 4.1947 | 23.97 | 4.1947
171- 180 mm thick - PREPACKED SCREED | [11 empty] | 0 | 0 | 0 | 0
1 | MALE WC |  | GCS-AX-WR-GF-00443 | 175 | 161.17 | 44.72 | 7207.5224 |  |  | 44.72 | 7207.5224 | 0 | 0 | 44.72 | 7.826
2 | BOH CORRIDOR |  | GCS-AX-WR-GF-00443 | 175 | 161.17 | 12.06 | 1943.7102 |  |  | 12.06 | 1943.7102 | 0 | 0 | 12.06 | 2.1105
3 | STORAGE |  | GCS-AX-WR-GF-00443 | 175 | 161.17 | 9.94 | 1602.0298 |  |  | 9.94 | 1602.0298 | 0 | 0 | 9.94 | 1.7395
4 | CORRIDOR |  | GCS-AX-WR-GF-00434 | 175 | 161.17 | 70.99 | 11441.4583 |  |  | 70.99 | 11441.4583 | 0 | 0 | 70.99 | 12.4232
[6 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
Upto 200 mm thick | [11 empty] | 0 | 0 | 0 | 0
1 | House Keeping Lobby |  | GCS-AX-WR-GF-00389 | 200 | 121.25 | 16 | 1940 |  |  | 16 | 1940 | 0 | 0 | 16 | 3.2
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 71mm to 80mm thick | [11 empty] | 0 | 0 | 0 | 0
[5 empty] | 91.4 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 91.4 | [6 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 81mm to 90mm thick | [11 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 91mm to 100mm thick | [11 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Up to 150mm thick + 6mm reinforcement | [11 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL (Screed Measurements - Ground floor ) = | [5 empty] | 1294.57 | 105144.4533 | 573.47 | 43105.3057 | 1868.04 | 148249.759 | 23.97 | 4.1947 | 1318.54 | 132.1221
[10 empty] | 1868.04 | 148249.759
0
| From 51mm to 60mm thick |  |  |  |  | 798.42 | 46060.8498 | 502.56 | 34637.4403 | 1300.98 | 80698.2901
| From 91mm to 100mm thick |  |  |  |  | 101.48 | 7419.2028 | 0 | 0 | 101.48 | 7419.2028
| Upto 180 mm thick |  |  |  |  | 240.96 | 27529.68 | 41.57 | 4749.3725 | 282.53 | 32279.0525
| Upto 170 mm thick |  |  |  |  | 0 | 0 | 29.34 | 3718.4929 | 29.34 | 3718.4929
| 171- 180 mm thick - PREPACKED SCREED |  |  |  |  | 137.71 | 22194.7207 | 0 | 0 | 137.71 | 22194.7207
| Upto 200 mm thick |  |  |  |  | 16 | 1940 | 0 | 0 | 16 | 1940
| TOTAL |  |  |  |  | 1294.57 | 105144.4533 | 573.47 | 43105.3057 | 1868.04 | 148249.759
Note on F22: Himal Kosala: 90% until Variation Approval
Note on I22: Himal Kosala: only 90% until WIR approve
Note on F23: Himal Kosala: 90% until Variation Approval
Note on I23: Himal Kosala: only 90% until WIR approve
Note on F24: Himal Kosala: 90% until Variation Approval
Note on I24: Himal Kosala: only 90% until WIR approve
Note on F25: Himal Kosala: 90% until Variation Approval
Note on I25: Himal Kosala: only 90% until WIR approve
Note on F34: Himal Kosala: 90% until Variation Approval

## SC-L-01 (hidden)
GCS German Concrete Works LLC
Screed Measurements - L-1 | [9 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | Room Number | wir no | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) | current qty | current volume | cumulative volume | cumulative volume
[6 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | GCS-AX-WR-L4-00390_00_B
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 51mm to 60mm thick | [11 empty] | 0 | 0 | 0 | 0
[5 empty] | 57.69 | [6 empty] | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0
From 61mm to 70mm thick | [11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
From 71mm to 80mm thick | [11 empty] | 0 | 0 | 0 | 0
1 | Room Service Support AREA |  | GCS-AX-WR-GF-00423 | 75 | 65.05 | 19.2 | 1248.96 |  | 0 | 19.2 | 1248.96 | 0 | 0 | 19.2 | 1.44
[12 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 81mm to 90mm thick | [11 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 91mm to 100mm thick | [11 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Up to 150mm thick + 6mm reinforcement | [11 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL (Screed Measurements - L-1 ) = | [5 empty] | 19.2 | 1248.96 | 0 | 0 | 19.2 | 1248.96 | 0 | 0 | 19.2 | 1.44
[10 empty] | 19.2 | 1248.96
0
| From 51mm to 60mm thick |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| From 71mm to 80mm thick |  |  |  |  | 19.2 | 1248.96 | 0 | 0 | 19.2 | 1248.96
| TOTAL |  |  |  |  | 19.2 | 1248.96 | 0 | 0 | 19.2 | 1248.96

## SC-L-02
GCS German Concrete Works LLC
Screed Measurements - L-2 | [9 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | Room Number | wir no | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) | current qty | current volume | cumulative volume | cumulative volume
[6 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 51mm to 60mm thick
1 | AREA-01 MONTH OF AUG-22 |  | GCS-LX-WR-L02-00399_00_B | 60 | 57.69 | 6.92 | 399.2148 |  |  | 6.92 | 399.2148 | 0 | 0 | 6.92 | 0.4152
2 | AREA-02 MONTH OF AUG-22 |  | GCS-LX-WR-L02-00399_00_B | 60 | 57.69 | 23.58 | 1360.3302 |  |  | 23.58 | 1360.3302 | 0 | 0 | 23.58 | 1.4148
3 | AREA-03 MONTH OF AUG-22 |  | GCS-LX-WR-L02-00399_00_B | 60 | 57.69 | 17.87 | 1030.9203 |  |  | 17.87 | 1030.9203 | 0 | 0 | 17.87 | 1.0722
4 | AREA-04 MONTH OF AUG-22 |  | GCS-LX-WR-L02-00399_00_B | 60 | 57.69 | 2.95 | 170.1855 |  |  | 2.95 | 170.1855 | 0 | 0 | 2.95 | 0.177
5 | AREA-05 MONTH OF AUG-22 |  | GCS-AX-WR-GF-00392_00_B | 60 | 57.69 | 57.45 | 3314.2905 |  |  | 57.45 | 3314.2905 | 0 | 0 | 57.45 | 3.447
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 61mm to 70mm thick | [11 empty] | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 71mm to 80mm thick | [11 empty] | 0 | 0 | 0 | 0
[5 empty] | 91.4 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 91.4 | [6 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 81mm to 90mm thick | [11 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 91mm to 100mm thick | [11 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Up to 190mm thick | [11 empty] | 0 | 0 | 0 | 0
1 | PANTRY |  | GCS-AX-WR-L02-00454 | 191 | 112.8 |  | 0 | 7.9 | 891.12 | 7.9 | 891.12 | 7.9 | 1.5089 | 7.9 | 1.5089
2 | Back of house arae GL 22-24 & T-V |  | GCS-AX-WR-L02-00454 | 191 | 112.8 |  |  | 73.5 | 8290.8 | 73.5 | 8290.8
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL (Screed Measurements - L-2 ) = | [5 empty] | 108.77 | 6274.9413 | 81.4 | 9181.92 | 190.17 | 15456.8613 | 7.9 | 1.5089 | 116.67 | 8.0351
[10 empty] | 190.17 | 15456.8613
0
| From 51mm to 60mm thick |  |  |  |  | 108.77 | 6274.9413 | 0 | 0 | 108.77 | 6274.9413
| Up to 190mm thick |  |  |  |  | 0 | 0 | 81.4 | 9181.92 | 81.4 | 9181.92
| TOTAL |  |  |  |  | 108.77 | 6274.9413 | 81.4 | 9181.92 | 190.17 | 15456.8613

## SC-L-4
GCS German Concrete Works LLC
Screed Measurements - L-4 | [9 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | Room Number | wir no | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) | current qty | current volume | cumulative volume | cumulative volume
[6 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 51mm to 60mm thick - PREPACKED SCREED
1 | Area 1 - Nov 2022 |  | GCS-AX-WR-L04-00439 | 60 | 80.37 | 282.07 | 22669.9659 |  |  | 282.07 | 22669.9659 | 0 | 0 | 282.07 | 16.9242 | GCS-AX-WR-L4-00390_00_B
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 51mm to 60mm thick | [11 empty] | 0 | 0 | 0 | 0
1 | AREA-01 MONTH OF AUG-22(planter area) |  | GCS-AX-WR-L4-00390_00_B | 60 | 57.69 | 8.78 | 506.5182 |  |  | 8.78 | 506.5182 | 0 | 0 | 8.78 | 0.5268
2 | AREA-01 MONTH OF SEP-22(planter area) |  | GCS-LX-WR-L04-00407 | 60 | 57.69 | 57.56 | 3320.6364 |  |  | 57.56 | 3320.6364 | 0 | 0 | 57.56 | 3.4536
3 | PLANTING GL14-16 |  | GCS-LX-WR-L04-00415 | 60 | 57.69 | 20.02 | 1154.9538 |  | 0 | 20.02 | 1154.9538 | 0 | 0 | 20.02 | 1.2012
4 | PLANTING GL9-16 |  | GCS-LX-WR-L04-00425 | 60 | 57.69 | 70.47 | 4065.4143 |  | 0 | 70.47 | 4065.4143 | 0 | 0 | 70.47 | 4.2282
From 61mm to 70mm thick | [11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
From 71mm to 80mm thick | [11 empty] | 0 | 0 | 0 | 0
1 | AREA-02 MONTH OF SEP-22(planter area) |  | GCS-LX-WR-L04-00407 | 80 | 65.05 | 159 | 10342.95 |  |  | 159 | 10342.95 | 0 | 0 | 159 | 12.72
2 | AREA-03 MONTH OF SEP-22(planter area) |  | GCS-LX-WR-L04-00407 | 80 | 65.05 | 29.41 | 1913.1205 |  |  | 29.41 | 1913.1205 | 0 | 0 | 29.41 | 2.3528
[7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 81mm to 90mm thick | [11 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 91mm to 100mm thick | [11 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Up to 190mm thick | [11 empty] | 0 | 0 | 0 | 0
1 | Restaurant boh & Room services GL 19-23 & U-X (jan -23) |  | GCS-AX-WR-L04-00452 | 191 | 112.8 |  | 0 | 130.91 | 14766.648 | 130.91 | 14766.648 | 130.91 | 25.0038 | 130.91 | 25.0038
[12 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL (Screed Measurements - L-4 ) = | [5 empty] | 627.31 | 43973.5591 | 130.91 | 14766.648 | 758.22 | 58740.2071 | 130.91 | 25.0038 | 758.22 | 66.4106
[10 empty] | 758.22 | 58740.2071
| From 51mm to 60mm thick - PREPACKED SCREED |  |  |  |  | 282.07 | 22669.9659 | 0 | 0 | 282.07 | 22669.9659
0
| From 51mm to 60mm thick |  |  |  |  | 156.83 | 9047.5227 | 0 | 0 | 156.83 | 9047.5227
| From 71mm to 80mm thick |  |  |  |  | 188.41 | 12256.0705 | 0 | 0 | 188.41 | 12256.0705
| Up to 190mm thick |  |  |  |  | 0 | 0 | 130.91 | 14766.648 | 130.91 | 14766.648
| TOTAL |  |  |  |  | 627.31 | 43973.5591 | 130.91 | 14766.648 | 758.22 | 58740.2071

## sc-05 (hidden)
GCS German Concrete Works LLC
Screed Measurements - L-05 | [9 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | Room Number | WIR NO | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) |  | current qty | current volume | cumulative volume | cumulative volume
[6 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[7 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 51mm to 60mm thick
[7 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Zone-03 | [6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Upto 200mm thick | [16 empty] | GCS-AX-WR-L27-00386
1 | AREA-01 MONTH OF JULY-22(House keeping lobby & garbage Room ) |  | GCS-AX-WR-L05-00385 | 200 | 121.25 | 12.88 | 1561.7 |  |  | 12.88 | 1561.7 | GCS-AX-WR-L05-00385-FOR POLYTHENE | 0 | 0 | 12.88 | 2.576
2 | Room Service |  |  | 200 | 121.25 | 18.7 | 2267.375 |  | 0 | 18.7 | 2267.375 | GCS-AX-WR-L05-00385 | 0 | 0 | 18.7 | 3.74
[7 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0
[7 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0
From 71mm to 80mm thick | [12 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 81mm to 90mm thick | [12 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 91mm to 100mm thick | [12 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Up to 150mm thick + 6mm reinforcement | [12 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
TOTAL (Screed Measurements - L-05 ) = | [5 empty] | 31.58 | 3829.075 | 0 | 0 | 31.58 | 3829.075 |  | 0 | 0 | 31.58 | 6.316
[10 empty] | 31.58 | 3829.075
0
| Upto 200mm thick |  |  |  |  | 31.58 | 3829.075 | 0 | 0 | 31.58 | 3829.075
| TOTAL |  |  |  |  | 31.58 | 3829.075 | 0 | 0 | 31.58 | 3829.075

## SC-06 (hidden)
GCS German Concrete Works LLC
Screed Measurements - L-06 | [8 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | wir number | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) |  | current qty | current volume | cumulative volume | cumulative volume
[5 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 51mm to 60mm thick
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Zone-03 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 61mm to 70mm thick
1 | BALCONY GL C -G & 01-04 |  | 68 | 62.25 | 126.72 | 7888.32 |  | 0 | 126.72 | 7888.32 | 62.25 | 0 | 0 | 126.72 | 8.617
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | GFHG65556
[12 empty] | 0 | 0 | 0 | 0
From 61mm to 70mm thick - PREPACKED SCREED | [11 empty] | 0 | 0 | 0 | 0
2 | BALCONY GL 03 - 04 & 07 - 09 | GCS-AX-WR-L-06-00441 | 68 | 87.37 | 48.02 | 4195.5074 |  |  | 48.02 | 4195.5074 |  | 0 | 0 | 48.02 | 3.2654 | GFHG65556
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0
From 71mm to 80mm thick | [11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 81mm to 90mm thick | [11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 91mm to 100mm thick | [11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Up to 150mm thick + 6mm reinforcement | [11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
TOTAL (Screed Measurements - L-06 ) = |  |  |  |  | 174.74 | 12083.8274 | 0 | 0 | 174.74 | 12083.8274 |  | 0 | 0 | 174.74 | 11.8823
[9 empty] | 174.74 | 12083.8274
0
| From 61mm to 70mm thick |  |  |  | 126.72 | 7888.32 | 0 | 0 | 126.72 | 7888.32
| From 61mm to 70mm thick - PREPACKED SCREED |  |  |  | 48.02 | 4195.5074 | 0 | 0 | 48.02 | 4195.5074
| TOTAL |  |  |  | 174.74 | 12083.8274 | 0 | 0 | 174.74 | 12083.8274

## sc-07
GCS German Concrete Works LLC
Screed Measurements - L-07 | [8 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | wir number | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) |  | current qty | current volume | cumulative volume | cumulative volume
[5 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 51mm to 60mm thick
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Zone-03 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 61mm to 70mm thick
1 | BALCONY GL V-X & 21-24 | GCS-AX-WR-ML-00462 | 68 | 73.278 |  |  | 26.316 | 1928.3838 | 26.316 | 1928.3838 | 62.25 | 26.316 | 1.7895 | 26.316 | 1.7895
[8 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | GFHG65556
[12 empty] | 0 | 0 | 0 | 0
From 61mm to 70mm thick - PREPACKED SCREED | [11 empty] | 0 | 0 | 0 | 0
|  |  | 68 | 87.37 |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | GFHG65556
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0
From 71mm to 80mm thick | [11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 81mm to 90mm thick | [11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 91mm to 100mm thick | [11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Up to 150mm thick + 6mm reinforcement | [11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
TOTAL (Screed Measurements - L-07 ) = |  |  |  |  | 0 | 0 | 26.316 | 1928.3838 | 26.316 | 1928.3838 |  | 26.316 | 1.7895 | 26.316 | 1.7895
[9 empty] | 26.316 | 1928.3838
0
| From 61mm to 70mm thick |  |  |  | 0 | 0 | 26.316 | 1928.3838 | 26.316 | 1928.3838
| From 61mm to 70mm thick - PREPACKED SCREED |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL |  |  |  | 0 | 0 | 26.316 | 1928.3838 | 26.316 | 1928.3838
Note on E19: Himal Kosala: 90% until Variation Approval
Note on H19: Himal Kosala: WIR is not approved

## sc-08 (hidden)
GCS German Concrete Works LLC
Screed Measurements - L-08 | [8 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | WIR NUMBER | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) |  | current qty | current volume | cumulative volume | cumulative volume
[5 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 51mm to 60mm thick
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Zone-03 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 61mm to 70mm thick
1 | BALCONY GL U-X & 22-23 | GCS-AX-WR-L08-00412 | 68 | 62.25 | 10 | 622.5 |  |  | 10 | 622.5 | 62.25 | 0 | 0 | 10 | 0.68
[6 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | GFHG65556
[6 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0
From 71mm to 80mm thick | [11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 81mm to 90mm thick | [11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 91mm to 100mm thick | [11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Up to 150mm thick + 6mm reinforcement | [11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
TOTAL (Screed Measurements - L-08 ) = |  |  |  |  | 10 | 622.5 | 0 | 0 | 10 | 622.5 |  | 0 | 0 | 10 | 0.68
[9 empty] | 10 | 622.5
0
| From 61mm to 70mm thick |  |  |  | 10 | 622.5 | 0 | 0 | 10 | 622.5
| TOTAL |  |  |  | 10 | 622.5 | 0 | 0 | 10 | 622.5

## SC-10
GCS German Concrete Works LLC
Screed Measurements - L-10 | [8 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | WIR NUMBER | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) |  | current qty | current volume | cumulative volume | cumulative volume
[5 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 51mm to 60mm thick
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Zone-03 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 61mm to 70mm thick
1 | Penthouse po0l deck area Ref Drawing | GCS-AX-WR-L10-00461 | 68 | 73.278 | 0 | 0 | 247.91 | 18166.349 | 247.91 | 18166.349 | 62.25 | 247.91 | 16.8579 | 247.91 | 16.8579
[6 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | GFHG65556
[6 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0
From 71mm to 80mm thick | [11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 81mm to 90mm thick | [11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 91mm to 100mm thick | [11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Up to 150mm thick + 6mm reinforcement | [11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
TOTAL (Screed Measurements - L-10 ) = |  |  |  |  | 0 | 0 | 247.91 | 18166.349 | 247.91 | 18166.349 |  | 247.91 | 16.8579 | 247.91 | 16.8579
[9 empty] | 247.91 | 18166.349
0
| From 61mm to 70mm thick |  |  |  | 0 | 0 | 247.91 | 18166.349 | 247.91 | 18166.349
| TOTAL |  |  |  | 0 | 0 | 247.91 | 18166.349 | 247.91 | 18166.349
Note on E19: Himal Kosala: 90% until Variation Approval

## SC-14 (hidden)
GCS German Concrete Works LLC
Screed Measurements - L-14 | [8 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | WIR NUMBER | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) |  | current qty | current volume | cumulative volume | cumulative volume
[5 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 51mm to 60mm thick
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Zone-03 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 51mm to 60mm thick(Prepacked Screed)
1 | AREA-01 MONTH OF OCT -22 | GCS-LX-WR-L04-00426 | 50 | 80.37 | 14 | 1125.18 |  | 0 | 14 | 1125.18 | 62.25 | 0 | 0 | 14 | 0.7
[6 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | GFHG65556
[6 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0
From 71mm to 80mm thick | [11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 81mm to 90mm thick | [11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 91mm to 100mm thick | [11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Up to 150mm thick + 6mm reinforcement | [11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
TOTAL (Screed Measurements - L-14 ) = |  |  |  |  | 14 | 1125.18 | 0 | 0 | 14 | 1125.18 |  | 0 | 0 | 14 | 0.7
[9 empty] | 14 | 1125.18
0
| From 51mm to 60mm thick(Prepacked Screed) |  |  |  | 14 | 1125.18 | 0 | 0 | 14 | 1125.18
| TOTAL |  |  |  | 14 | 1125.18 | 0 | 0 | 14 | 1125.18

## SC-16
GCS German Concrete Works LLC
Screed Measurements - L-16 | [8 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | WIR NUMBER | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) |  | current qty | current volume | cumulative volume | cumulative volume
[5 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 51mm to 60mm thick
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Zone-03 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 51mm to 60mm thick(Prepacked Screed)
1 | AREA-01 MONTH OF OCT -22 | GCS-LX-WR-L04-00426 | 50 | 80.37 | 15 | 1205.55 |  | 0 | 15 | 1205.55 | 62.25 | 0 | 0 | 15 | 0.75
[6 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | GFHG65556
[6 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0
From 61mm to 70mm thick | [11 empty] | 0 | 0 | 0 | 0
1 | Balcony GL U-X & 22-23 | GCS-AX-WR-ML-00462 | 68 | 73.278 |  | 0 | 9.306 | 681.9251 | 9.306 | 681.9251 |  | 9.306 | 0.63281 | 9.306 | 0.63281
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 81mm to 90mm thick | [11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 91mm to 100mm thick | [11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Up to 150mm thick + 6mm reinforcement | [11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
TOTAL (Screed Measurements - L-16 ) = |  |  |  |  | 15 | 1205.55 | 9.306 | 681.9251 | 24.306 | 1887.4751 |  | 9.306 | 0.63281 | 24.306 | 1.3828
[9 empty] | 24.306 | 1887.4751
0
| From 51mm to 60mm thick(Prepacked Screed) |  |  |  | 15 | 1205.55 | 0 | 0 | 15 | 1205.55
| From 61mm to 70mm thick |  |  |  | 0 | 0 | 9.306 | 681.9251 | 9.306 | 681.9251
| TOTAL |  |  |  | 15 | 1205.55 | 9.306 | 681.9251 | 24.306 | 1887.4751
Note on E24: Himal Kosala: 90% until Variation Approval
Note on H24: Himal Kosala: WIR not approved

## SC-18 (hidden)
GCS German Concrete Works LLC
Screed Measurements - L-18 | [8 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | WIR NUMBER | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) |  | current qty | current volume | cumulative volume | cumulative volume
[5 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 51mm to 60mm thick
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Balcony areas | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 61mm to 70mm thick
1 | BALCONY GL 18 - 23 & S - X & 21- 23 | GCS-LX-WR-L04-00433 | 68 | 62.25 | 139.12 | 8660.22 |  |  | 139.12 | 8660.22 | 62.25 | 0 | 0 | 139.12 | 9.4602
[6 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | GFHG65556
[6 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0
From 71mm to 80mm thick | [11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 81mm to 90mm thick | [11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 91mm to 100mm thick | [11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Up to 150mm thick + 6mm reinforcement | [11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
TOTAL (Screed Measurements - L-18 ) = |  |  |  |  | 139.12 | 8660.22 | 0 | 0 | 139.12 | 8660.22 |  | 0 | 0 | 139.12 | 9.4602
[9 empty] | 139.12 | 8660.22
0
| From 61mm to 70mm thick |  |  |  | 139.12 | 8660.22 | 0 | 0 | 139.12 | 8660.22
| TOTAL |  |  |  | 139.12 | 8660.22 | 0 | 0 | 139.12 | 8660.22

## SC-19 (hidden)
GCS German Concrete Works LLC
Screed Measurements - L-19 | [8 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | WIR NUMBER | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) |  | current qty | current volume | cumulative volume | cumulative volume
[5 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 51mm to 60mm thick
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
HOTEL | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 41mm to 50mm thick
1 | AREA-01 MONTH OF NOV -22 | GCS-LX-WR-L04-00430 | 50 | 54.74 | 211.41 | 11572.5834 |  |  | 211.41 | 11572.5834 | 62.25 | 0 | 0 | 211.41 | 10.5705
[6 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0
From 51mm to 60mm thick(Prepacked Screed) | [11 empty] | 0 | 0 | 0 | 0
1 | AREA-01 MONTH OF Dec -22 | GCS-AX-WR-L19-00447 | 60 | 80.37 | 47.89 | 3848.9193 | 0 | 0 | 47.89 | 3848.9193 |  | 0 | 0 | 47.89 | 2.8734
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 81mm to 90mm thick | [11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 91mm to 100mm thick | [11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Up to 150mm thick + 6mm reinforcement | [11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
TOTAL (Screed Measurements - L-19 ) = |  |  |  |  | 259.3 | 15421.5027 | 0 | 0 | 259.3 | 15421.5027 |  | 0 | 0 | 259.3 | 13.4439
[9 empty] | 259.3 | 15421.5027
0
| From 41mm to 50mm thick |  |  |  | 211.41 | 11572.5834 | 0 | 0 | 211.41 | 11572.5834
| From 51mm to 60mm thick(Prepacked Screed) |  |  |  | 47.89 | 3848.9193 | 0 | 0 | 47.89 | 3848.9193
| TOTAL |  |  |  | 259.3 | 15421.5027 | 0 | 0 | 259.3 | 15421.5027

## sc-l-20 (hidden)
GCS German Concrete Works LLC
Screed Measurements - L-20 | [8 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | Room Number | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) | current qty | current volume | cumulative volume | cumulative volume
[5 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 51mm to 60mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Balcony areas | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 61mm to 70mm thick
1 | Balcony GL 21-24 |  | 68 | 87.37 | 22 | 1922.14 |  |  | 22 | 1922.14 | 0 | 0 | 22 | 1.496
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
From 71mm to 80mm thick | [10 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 81mm to 90mm thick | [10 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 91mm to 100mm thick | [10 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Up to 150mm thick + 6mm reinforcement | [10 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL (Screed Measurements - L-20 ) = |  |  |  |  | 22 | 1922.14 | 0 | 0 | 22 | 1922.14 | 0 | 0 | 22 | 1.496
[9 empty] | 22 | 1922.14
0
| From 61mm to 70mm thick |  |  |  | 22 | 1922.14 | 0 | 0 | 22 | 1922.14
| TOTAL |  |  |  | 22 | 1922.14 | 0 | 0 | 22 | 1922.14

## SC-21
GCS German Concrete Works LLC
Screed Measurements - L-21 | [8 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | WIR NUMBER | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) | current qty | current volume | cumulative volume | cumulative volume
[5 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 51mm to 60mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Zone-03 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 51mm to 60mm thick(Prepacked Screed)
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | GFHG65556
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
From 61mm to 70mm thick | [10 empty] | 0 | 0 | 0 | 0
1 | Balcony GL U-X & 22-23 | GCS-AX-WR-ML-00462 | 68 | 73.278 |  | 0 | 9.153 | 670.7135 | 9.153 | 670.7135 | 9.153 | 0.6224 | 9.153 | 0.6224
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 81mm to 90mm thick | [10 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 91mm to 100mm thick | [10 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Up to 150mm thick + 6mm reinforcement | [10 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL (Screed Measurements - L-21 ) = |  |  |  |  | 0 | 0 | 9.153 | 670.7135 | 9.153 | 670.7135 | 9.153 | 0.6224 | 9.153 | 0.6224
[9 empty] | 9.153 | 670.7135
0
| From 51mm to 60mm thick(Prepacked Screed) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| From 61mm to 70mm thick |  |  |  | 0 | 0 | 9.153 | 670.7135 | 9.153 | 670.7135
| TOTAL |  |  |  | 0 | 0 | 9.153 | 670.7135 | 9.153 | 670.7135
Note on E23: Himal Kosala: 90% until Variation Approval
Note on H23: Himal Kosala: WIR not approved

## sc-l-22 (hidden)
GCS German Concrete Works LLC
Screed Measurements - L-22 | [8 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | Room Number | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) | current qty | current volume | cumulative volume | cumulative volume
[5 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 51mm to 60mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Balcony areas | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 61mm to 70mm thick
1 | Balcony GL 21-24 |  | 68 | 87.37 | 23.3 | 2035.721 |  |  | 23.3 | 2035.721 | 0 | 0 | 23.3 | 1.5844
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 71mm to 80mm thick | [10 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 81mm to 90mm thick | [10 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 91mm to 100mm thick | [10 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Up to 150mm thick + 6mm reinforcement | [10 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL (Screed Measurements - L-22 ) = |  |  |  |  | 23.3 | 2035.721 | 0 | 0 | 23.3 | 2035.721 | 0 | 0 | 23.3 | 1.5844
[9 empty] | 23.3 | 2035.721
0
| From 61mm to 70mm thick |  |  |  | 23.3 | 2035.721 | 0 | 0 | 23.3 | 2035.721
| TOTAL |  |  |  | 23.3 | 2035.721 | 0 | 0 | 23.3 | 2035.721

## SC-L-23
GCS German Concrete Works LLC
Screed Measurements - L-23 | [8 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | WIR NUMBER | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) | current qty | current volume | cumulative volume | cumulative volume
[5 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 51mm to 60mm thick
1 | Planter Screed month of jan -23 GL8-11 & D-E | GCS-LX-WR-L23-00459 | 60 | 68.922 |  | 0 | 1.56 | 107.5183 | 1.56 | 107.5183 | 1.56 | 0.0936 | 1.56 | 0.0936
2 | Planter Screed month of jan -23 GL8-11 & G-X5 | GCS-LX-WR-L23-00459 | 60 | 68.922 |  | 0 | 31.19 | 2149.6772 | 31.19 | 2149.6772 | 31.19 | 1.8714 | 31.19 | 1.8714
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 51mm to 60mm thick(Prepacked Screed)
1 | AREA 2 NO. -NOV 2022 | GCS-AX-WR-L023-00429 | 60 | 80.37 | 5.76 | 462.9312 |  |  | 5.76 | 462.9312 | 0 | 0 | 5.76 | 0.3456
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
From 61mm to 70mm thick(Prepacked)
1 | Pump Room/BHU Storage | GCS-AX-WR-L023-00428 | 68 | 87.37 | 28 | 2446.36 |  |  | 28 | 2446.36 | 0 | 0 | 28 | 1.904
2 | BALCONY GL 02 - 08 | GCS-AX-WR-L023-00435 | 68 | 87.37 | 90.54 | 7910.4798 |  |  | 90.54 | 7910.4798 | 0 | 0 | 90.54 | 6.1567
From 61-70 mm thick
1 | Balcony GL C TO H | GCS-AX-WR-L23-00455 | 68 | 73.278 |  |  | 55.79 | 4088.1796 | 55.79 | 4088.1796
2 | Balcony GL 7 TO 12 & C-D | GCS-AX-WR-L23-00455 | 68 | 73.278 |  |  | 67.91 | 4976.309 | 67.91 | 4976.309
3 | Balcony GL 7 TO 12 & G-H | GCS-AX-WR-L23-00455 | 68 | 73.278 |  |  | 67.32 | 4933.075 | 67.32 | 4933.075
4 | Balcony GL U-X & 22-23 | GCS-AX-WR-ML-00462 | 68 | 73.278 |  |  | 20.295 | 1487.177 | 20.295 | 1487.177
[8 empty] | 0 | 0 | 0
From 71mm to 80mm thick
1 | Plant room area month of jan -23 gl 2-4 | GCS-AX-WR-L23-00457 | 80 | 77.634 |  |  | 321 | 24920.514 | 321 | 24920.514 | 321 | 25.68 | 321 | 25.68
2 | Plant room area month of jan -23 gl 4-6 | GCS-AX-WR-L23-00458 | 80 | 77.634 |  |  | 105.5 | 8190.387 | 105.5 | 8190.387 | 105.5 | 8.44 | 105.5 | 8.44
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 81mm to 90mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 91mm to 100mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Up to 150mm thick + 6mm reinforcement
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL (Screed Measurements - L-23 ) = |  |  |  |  | 124.3 | 10819.771 | 670.565 | 50852.8371 | 794.865 | 61672.6081 | 459.25 | 36.085 | 583.55 | 44.4913
[9 empty] | 794.865 | 61672.6081
| From 51mm to 60mm thick |  |  |  | 0 | 0 | 32.75 | 2257.1955 | 32.75 | 2257.1955
| From 61mm to 70mm thick(Prepacked) |  |  |  | 118.54 | 10356.8398 | 0 | 0 | 118.54 | 10356.8398
| From 51mm to 60mm thick(Prepacked Screed) |  |  |  | 5.76 | 462.9312 | 0 | 0 | 5.76 | 462.9312
| From 61-70 mm thick |  |  |  | 0 | 0 | 211.315 | 15484.7406 | 211.315 | 15484.7406
| From 71mm to 80mm thick |  |  |  | 0 | 0 | 426.5 | 33110.901 | 426.5 | 33110.901
| TOTAL |  |  |  | 124.3 | 10819.771 | 670.565 | 50852.8371 | 794.865 | 61672.6081
Note on E8: Himal Kosala: 90% until Variation Approval
Note on E9: Himal Kosala: 90% until Variation Approval
Note on E23: Himal Kosala: 90% until Variation Approval
Note on E24: Himal Kosala: 90% until Variation Approval
Note on E25: Himal Kosala: 90% until Variation Approval
Note on E26: Himal Kosala: 90% until Variation Approval
Note on H26: Himal Kosala: WIR not approved
Note on E29: Himal Kosala: 90% until Variation Approval
Note on E30: Himal Kosala: 90% until Variation Approval

## SC-L-25
GCS German Concrete Works LLC
Screed Measurements - L-25 | [9 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | Room Number | wir no | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) | current qty | current volume | cumulative volume | cumulative volume
[6 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 51mm to 60mm thick
1 | AREA-01 MONTH OF AUG-22 |  | GCS-LX-WR-ML-00404 | 60 | 57.69 | 5.54 | 319.6026 |  |  | 5.54 | 319.6026 | 0 | 0 | 5.54 | 0.3324
[6 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
From 61mm to 70mm thick | [6 empty] | 0
1 | Balcony GL 21-22 |  |  | 68 | 62.25 | 10.76 | 669.81 |  |  | 10.76 | 669.81 | 0 | 0 | 10.76 | 0.73168
2 | Balcony GL 18-19 |  |  | 68 | 62.25 | 8.04 | 500.49 |  |  | 8.04 | 500.49 | 0 | 0 | 8.04 | 0.54672
3 | Balcony GL 14-15 |  |  | 68 | 62.25 | 9.88 | 615.03 |  |  | 9.88 | 615.03 | 0 | 0 | 9.88 | 0.67184
4 | Pool plant area balcony |  |  | 68 | 62.25 | 80.38 | 5003.655 |  |  | 80.38 | 5003.655 | 0 | 0 | 80.38 | 5.4658
5 | Balcony GL U-X & 22-23 |  | GCS-AX-WR-ML-00462 | 68 | 73.278 |  |  | 9.396 | 688.5201 | 9.396 | 688.5201 | 9.396 | 0.63893 | 9.396 | 0.63893
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 71mm to 80mm thick
[5 empty] | 91.4 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 91.4 | [6 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 81mm to 90mm thick
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 91mm to 100mm thick
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Up to 150mm thick + 6mm reinforcement
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL (Screed Measurements - L-25 ) = | [5 empty] | 114.6 | 7108.5876 | 9.396 | 688.5201 | 123.996 | 7797.1077 | 9.396 | 0.63893 | 123.996 | 8.3874
| From 51mm to 60mm thick |  |  |  |  | 5.54 | 319.6026 | 0 | 0 | 5.54 | 319.6026
| From 61mm to 70mm thick |  |  |  |  | 109.06 | 6788.985 | 9.396 | 688.5201 | 118.456 | 7477.5051
| TOTAL |  |  |  |  | 109.06 | 6788.985 | 9.396 | 688.5201 | 118.456 | 7477.5051
Note on F22: Himal Kosala: 90% until Variation Approval
Note on I22: Himal Kosala: WIR not approved

## SC-L-26 (hidden)
GCS German Concrete Works LLC
Screed Measurements - L-26 | [8 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | WIR NUMBER | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) | current qty | current volume | cumulative volume | cumulative volume
[5 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 51mm to 60mm thick(Prepacked Screed)
1 | AREA -01 Dec 2022 | GCS-AX-WR-L26-00451& 00446 | 60 | 80.37 | 74.74 | 6006.8538 | 0 | 0 | 74.74 | 6006.8538 | 0 | 0 | 74.74 | 4.4844
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 61mm to 70mm thick(Prepacked)
1 | Balcony GL 18-19 | GCS-AX-WR-L26-00408 | 68 | 87.37 | 8.32 | 726.9184 |  |  | 8.32 | 726.9184 | 0 | 0 | 8.32 | 0.56576
2 | Balcony GL 14-15 | GCS-AX-WR-L26-00408 | 68 | 87.37 | 10 | 873.7 |  |  | 10 | 873.7 | 0 | 0 | 10 | 0.68
3 | Balcony GL 20-24 | GCS-AX-WR-L26-00408 | 68 | 87.37 | 144 | 12581.28 |  |  | 144 | 12581.28 | 0 | 0 | 144 | 9.792
4 | Balcony GL 12-15 | GCS-AX-WR-L26-00420 | 68 | 87.37 | 13.17 | 1150.6629 |  | 0 | 13.17 | 1150.6629 | 0 | 0 | 13.17 | 0.89556
5 | PENTHOUSE P4 BALCONY | GCS-AX-WR-L26-00413 | 68 | 87.37 | 132.3 | 11559.051 |  | 0 | 132.3 | 11559.051 | 0 | 0 | 132.3 | 8.9964
6 | AREA NOV 2022 | GCS-AX-WR-L26-00446 | 68 | 87.37 | 121.71 | 10633.8027 |  |  | 121.71 | 10633.8027 | 0 | 0 | 121.71 | 8.2763
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 71mm to 80mm thick | [10 empty] | 0 | 0 | 0 | 0
|  |  |  | 91.4 | [6 empty] | 0 | 0 | 0 | 0
|  |  |  | 91.4 | [6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 81mm to 90mm thick | [10 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 91mm to 100mm thick | [10 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Up to 150mm thick + 6mm reinforcement | [10 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL (Screed Measurements - L-26 ) = |  |  |  |  | 504.24 | 43532.2688 | 0 | 0 | 504.24 | 43532.2688 | 0 | 0 | 504.24 | 33.6904
[9 empty] | 504.24 | 43532.2688
0
| From 61mm to 70mm thick(Prepacked) |  |  |  | 429.5 | 37525.415 | 0 | 0 | 429.5 | 37525.415
| From 51mm to 60mm thick(Prepacked Screed) |  |  |  | 74.74 | 6006.8538 | 0 | 0 | 74.74 | 6006.8538
| TOTAL |  |  |  | 504.24 | 43532.2688 | 0 | 0 | 504.24 | 43532.2688

## sc-l-27
GCS German Concrete Works LLC
Screed Measurements - L-27 | [9 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | Room Number | WIR NO | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) | current qty | current volume | cumulative volume | cumulative volume
[6 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 51mm to 60mm thick | [11 empty] | 0 | 0 | 0 | 0
1 | AREA-01 MONTH OF AUG-22 |  | GCS-LX-WR-ML-00404 | 60 | 57.69 | 5.54 | 319.6026 |  |  | 5.54 | 319.6026 | 0 | 0 | 5.54 | 0.3324
[6 empty] | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
From 61mm to 70mm thick | [11 empty] | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0
From 61mm to 70mm thick(Pre Packed ) | [11 empty] | 0 | 0 | 0 | 0
1 | Area-01 month of july -22(Zone-03) |  | GCS-AX-WR-L27-00386 | 68 | 87.37 | 85.62 | 7480.6194 |  |  | 85.62 | 7480.6194 | 0 | 0 | 85.62 | 5.8222
2 | Balcony GL 15-22 |  | GCS-AX-WR-L27-00384 | 68 | 87.37 | 93.28 | 8149.8736 |  |  | 93.28 | 8149.8736 | 0 | 0 | 93.28 | 6.343
3 | Balcony GL 15-19 |  | GCS-AX-WR-L27-00384 | 68 | 87.37 | 48.81 | 4264.5297 |  |  | 48.81 | 4264.5297 | 0 | 0 | 48.81 | 3.3191
4 | Pool plant area balcony |  |  | 68 | 87.37 | 69.62 | 6082.6994 |  |  | 69.62 | 6082.6994 | 0 | 0 | 69.62 | 4.7342
5 | Balcony GL 03-04 |  |  | 68 | 87.37 | 18.34 | 1602.3658 |  |  | 18.34 | 1602.3658 | 0 | 0 | 18.34 | 1.2471
6 | Balcony GL 03-04 |  | GCS-AX-WR-L27-00414 | 68 | 87.37 | 15.65 | 1367.3405 |  | 0 | 15.65 | 1367.3405 | 0 | 0 | 15.65 | 1.0642
7 | Balcony GL 14-15 |  | GCS-AX-WR-L27-00444 | 68 | 87.37 | 13.08 | 1142.7996 |  | 0 | 13.08 | 1142.7996 | 0 | 0 | 13.08 | 0.88944
8 | Balcony GL U-X & 22-23 |  | GCS-AX-WR-L27-00448 | 68 | 87.37 |  |  | 21.85 | 1909.0345 | 21.85 | 1909.0345 | 21.85 | 1.4858 | 21.85 | 1.4858
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 81mm to 90mm thick | [11 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 91mm to 100mm thick | [11 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Up to 150mm thick + 6mm reinforcement | [11 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL (Screed Measurements - L-27 ) = | [5 empty] | 349.94 | 30409.8306 | 21.85 | 1909.0345 | 371.79 | 32318.8651 | 21.85 | 1.4858 | 371.79 | 25.2374
| From 51mm to 60mm thick |  |  |  |  | 5.54 | 319.6026 | 0 | 0 | 5.54 | 319.6026
| From 61mm to 70mm thick |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| From 61mm to 70mm thick(Pre Packed ) |  |  |  |  | 344.4 | 30090.228 | 21.85 | 1909.0345 | 366.25 | 31999.2625
| TOTAL |  |  |  |  | 349.94 | 30409.8306 | 21.85 | 1909.0345 | 371.79 | 32318.8651

## sc-l-28
GCS German Concrete Works LLC
Screed Measurements - L-28 | [8 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | WIR Number | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) | current qty | current volume | cumulative volume | cumulative volume
[5 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 51mm to 60mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 61mm to 70mm thick(Pre Packed )
1 | Penthouse P5 balcony | GCS-AX-WR-L28-00421 | 68 | 87.37 | 15.96 | 1394.4252 |  | 0 | 15.96 | 1394.4252 | 0 | 0 | 15.96 | 1.0853
2 | Balcony GL Q-Y & 22-24 | GCS-AX-WR-L28-00463 | 68 | 87.37 | 0 |  | 57.45 | 5019.4065 | 57.45 | 5019.4065 |  |  |  | 3.9066
|  |  | 68 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0
[8 empty] | 0 | 0 | 0 |  |  |  | 0
[8 empty] | 0 | 0 | 0 |  |  |  | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 71mm to 80mm thick | [13 empty] | 0
1 | D-01-C |  | 75 | 91.4 | 6.12 | 559.368 |  |  | 6.12 | 559.368 | 0 | 0 | 6.12 | 0.459
2 | FTR |  | 75 | 91.4 | 7 | 639.8 |  |  | 7 | 639.8 | 0 | 0 | 7 | 0.525
3 | Corridor |  | 75 | 91.4 | 16 | 1462.4 |  |  | 16 | 1462.4 | 0 | 0 | 16 | 1.2
4 |  |  | 75 | 91.4 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
From 81mm to 90mm thick | [13 empty] | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 91mm to 100mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Up to 150mm thick + 6mm reinforcement
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL (Screed Measurements - L-28 ) = |  |  |  |  | 45.08 | 4055.9932 | 57.45 | 5019.4065 | 102.53 | 9075.3997 | 0 | 0 | 45.08 | 7.1759
[9 empty] | 102.53 | 9075.3997
0
| From 71mm to 80mm thick |  |  |  | 29.12 | 2661.568 | 0 | 0 | 29.12 | 2661.568
| From 61mm to 70mm thick(Pre Packed ) |  |  |  | 15.96 | 1394.4252 | 57.45 | 5019.4065 | 73.41 | 6413.8317
| TOTAL |  |  |  | 45.08 | 4055.9932 | 57.45 | 5019.4065 | 102.53 | 9075.3997

## sc-l-29
GCS German Concrete Works LLC
Screed Measurements - L-29 | [9 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | Room Number | wir no | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) | current qty | current volume | cumulative volume | cumulative volume
[6 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick | [15 empty] | GCS-LX-WR-L29-000393_00_B
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 51mm to 60mm thick
1 | AREA-01 MONTH OF AUG-22 |  | GCS-LX-WR-ML-00404 | 60 | 57.69 | 5.54 | 319.6026 |  |  | 5.54 | 319.6026 | 0 | 0 | 5.54 | 0.3324
2 | AREA-01 MONTH OF sep-22(Planter Area Gl 13-15) |  |  | 60 | 57.69 | 22.78 | 1314.1782 |  |  | 22.78 | 1314.1782 | 0 | 0 | 22.78 | 1.3668
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 71mm to 80mm thick | [11 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Electrical Room |  |  | 75 | 91.4 | 6.29 | 574.906 |  |  | 6.29 | 574.906 | 0 | 0 | 6.29 | 0.47175
2 | GSM Room |  |  | 75 | 91.4 | 4.7 | 429.58 |  |  | 4.7 | 429.58 | 0 | 0 | 4.7 | 0.3525
From 111mm to 120mm thick
1 | Area-01 month of Jan - GL 13-23 & Q-X |  | GCS-AX-WR-L29-00453&00460 | 120 | 100.503 |  |  | 606.89 | 60994.2657 | 606.89 | 60994.2657
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL (Screed Measurements - L-29 ) = | [5 empty] | 39.31 | 2638.2668 | 606.89 | 60994.2657 | 646.2 | 63632.5325 | 0 | 0 | 39.31 | 2.5235
| From 51mm to 60mm thick |  |  |  |  | 28.32 | 1633.7808 | 0 | 0 | 28.32 | 1633.7808
| From 71mm to 80mm thick |  |  |  |  | 10.99 | 1004.486 | 0 | 0 | 10.99 | 1004.486
| From 111mm to 120mm thick |  |  |  |  | 0 | 0 | 606.89 | 60994.2657 | 606.89 | 60994.2657
| TOTAL |  |  |  |  | 10.99 | 1004.486 | 606.89 | 60994.2657 | 617.88 | 61998.7517
Note on F26: Himal Kosala: 90% until Variation Approval

## SC-L-30 (hidden)
GCS German Concrete Works LLC
Screed Measurements - L-30 | [9 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | Room Number | wir no | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) | current qty | current volume | cumulative volume | cumulative volume
[6 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
1 | FF LOBBY |  | GCS-AX-WR-L30-0038 | 50 | 54.74 | 14.91 | 816.1734 |  |  | 14.91 | 816.1734 | 0 | 0 | 14.91 | 0.7455
2 | HOUSE KEEPING LOBBY |  | GCS-AX-WR-L30-0039 | 50 | 54.74 | 9.61 | 526.0514 |  |  | 9.61 | 526.0514 | 0 | 0 | 9.61 | 0.4805
[7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
From 51mm to 60mm thick | [11 empty] | 0 | 0 | 0 | 0
|  |  |  | 60 | 57.69 | [6 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 61mm to 70mm thick | [11 empty] | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 71mm to 80mm thick | [11 empty] | 0 | 0 | 0 | 0
[5 empty] | 91.4 | [6 empty] | 0 | 0 | 0 | 0
[5 empty] | 91.4 | [6 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 81mm to 90mm thick | [11 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 91mm to 100mm thick | [11 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Up to 150mm thick + 6mm reinforcement | [11 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL (Screed Measurements - L-30 ) = | [5 empty] | 24.52 | 1342.2248 | 0 | 0 | 24.52 | 1342.2248 | 0 | 0 | 24.52 | 1.226
[10 empty] | 24.52 | 1342.2248
0
| From 41mm to 50mm thick |  |  |  |  | 24.52 | 1342.2248 | 0 | 0 | 24.52 | 1342.2248
| TOTAL |  |  |  |  | 24.52 | 1342.2248 | 0 | 0 | 24.52 | 1342.2248

## IN-b-01 (2) (hidden)
GCS German Concrete Works LLC
Insulation Measurements - Basement-01 | [8 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | Room Number | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) | current qty | current volume | cumulative volume | cumulative volume
[5 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 51mm to 60mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Upto 25 mm Thickness Insulation
1 | External Seating Area |  | 25 | 51.83 | 49.37 | 2558.8471 |  |  | 49.37 | 2558.8471 | 0 | 0 | 49.37 | 1.2343
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
From 71mm to 80mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 81mm to 90mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 91mm to 100mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Up to 150mm thick + 6mm reinforcement
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL (Insulation Measurements - Basement-01 ) = |  |  |  |  | 49.37 | 2558.8471 | 0 | 0 | 49.37 | 2558.8471 | 0 | 0 | 49.37 | 1.2343
[9 empty] | 49.37 | 2558.8471
0
| Upto 25 mm Thickness Insulation |  |  |  | 49.37 | 2558.8471 | 0 | 0 | 49.37 | 2558.8471
| TOTAL |  |  |  | 49.37 | 2558.8471 | 0 | 0 | 49.37 | 2558.8471

## in-l-06 (hidden)
GCS German Concrete Works LLC
Insulation Measurements - Level -06 | [8 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | wir number | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) | current qty | current volume | cumulative volume | cumulative volume
[5 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 51mm to 60mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Upto 25 mm Thickness Insulation
1 | BALCONY GL C -G & 01-04 | GCS-AX-WR-L-06-00402 | 25 | 51.83 | 126.72 | 6567.8976 |  |  | 126.72 | 6567.8976 | 0 | 0 | 126.72 | 3.168 | 21.66 | 1348.335 | 126.72
2 | BALCONY GL 03 - 04 & 07 - 09 | GCS-AX-WR-L-06-00441 | 25 | 51.83 | 48.02 | 2488.8766 |  |  | 48.02 | 2488.8766 | 0 | 0 | 48.02 | 1.2005 |  | GFHG65556
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
From 71mm to 80mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 81mm to 90mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 91mm to 100mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Up to 150mm thick + 6mm reinforcement
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL (Insulation Measurements - Level -06 ) = |  |  |  |  | 174.74 | 9056.7742 | 0 | 0 | 174.74 | 9056.7742 | 0 | 0 | 174.74 | 4.3685
[9 empty] | 174.74 | 9056.7742
0
| Upto 25 mm Thickness Insulation |  |  |  | 174.74 | 9056.7742 | 0 | 0 | 174.74 | 9056.7742
| TOTAL |  |  |  | 174.74 | 9056.7742 | 0 | 0 | 174.74 | 9056.7742

## IN-L-07
GCS German Concrete Works LLC
Insulation Measurements - Level -07 | [8 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | wir number | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) | current qty | current volume | cumulative volume | cumulative volume
[5 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 51mm to 60mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Upto 25 mm Thickness Insulation
1 | BALCONY GL V-X & 21-24 | GCS-AX-WR-ML-00462 | 25 | 51.83 |  |  | 26.316 | 1363.9583 | 26.316 | 1363.9583 | 26.316 | 0.6579 | 26.316 | 0.6579 | 21.66 | 1348.335 | 126.72
2 |  |  | 25 | 51.83 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | GFHG65556
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
From 71mm to 80mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 81mm to 90mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 91mm to 100mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Up to 150mm thick + 6mm reinforcement
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL (Insulation Measurements - Level -07 ) = |  |  |  |  | 0 | 0 | 26.316 | 1363.9583 | 26.316 | 1363.9583 | 26.316 | 0.6579 | 26.316 | 0.6579
[9 empty] | 26.316 | 1363.9583
0
| Upto 25 mm Thickness Insulation |  |  |  | 0 | 0 | 26.316 | 1363.9583 | 26.316 | 1363.9583
| TOTAL |  |  |  | 0 | 0 | 26.316 | 1363.9583 | 26.316 | 1363.9583
Note on H19: Himal Kosala: WIR not approved

## in-l-8 (hidden)
GCS German Concrete Works LLC
Insulation Measurements - Level -08 | [8 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | wir number | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) | current qty | current volume | cumulative volume | cumulative volume
[5 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 51mm to 60mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Upto 25 mm Thickness Insulation
1 | BALCONY GL U-X & 22-23 | GCS-AX-WR-L08-00412 | 25 | 51.83 | 10 | 518.3 |  |  | 10 | 518.3 | 0 | 0 | 10 | 0.25 | 21.66 | 1348.335 | 126.72
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
From 71mm to 80mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 81mm to 90mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 91mm to 100mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Up to 150mm thick + 6mm reinforcement
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL (Insulation Measurements - Level -08 ) = |  |  |  |  | 10 | 518.3 | 0 | 0 | 10 | 518.3 | 0 | 0 | 10 | 0.25
[9 empty] | 10 | 518.3
0
| Upto 25 mm Thickness Insulation |  |  |  | 10 | 518.3 | 0 | 0 | 10 | 518.3
| TOTAL |  |  |  | 10 | 518.3 | 0 | 0 | 10 | 518.3

## in-l-10
GCS German Concrete Works LLC
Insulation Measurements - Level -10 | [8 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | wir number | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) | current qty | current volume | cumulative volume | cumulative volume
[5 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 51mm to 60mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Upto 25 mm Thickness Insulation
1 | Penthouse po0l deck area Ref Drawing | GCS-AX-WR-L10-00461 | 25 | 51.83 | 0 | 0 | 247.91 | 12849.1753 | 247.91 | 12849.1753 | 247.91 | 6.1978 | 247.91 | 6.1978 | 21.66 | 1348.335 | 126.72
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
From 71mm to 80mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 81mm to 90mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 91mm to 100mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Up to 150mm thick + 6mm reinforcement
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL (Insulation Measurements - Level -10 ) = |  |  |  |  | 0 | 0 | 247.91 | 12849.1753 | 247.91 | 12849.1753 | 247.91 | 6.1978 | 247.91 | 6.1978
[9 empty] | 247.91 | 12849.1753
0
| Upto 25 mm Thickness Insulation |  |  |  | 0 | 0 | 247.91 | 12849.1753 | 247.91 | 12849.1753
| TOTAL |  |  |  | 0 | 0 | 247.91 | 12849.1753 | 247.91 | 12849.1753

## IN-L-16
GCS German Concrete Works LLC
Insulation Measurements - Level -16 | [8 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | wir number | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) | current qty | current volume | cumulative volume | cumulative volume
[5 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 51mm to 60mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Upto 25 mm Thickness Insulation
1 | Balcony GL U-X & 22-23 | GCS-AX-WR-ML-00462 | 68 | 51.83 |  | 0 | 9.306 | 482.33 | 9.306 | 482.33 | 9.306 | 0.63281 | 9.306 | 0.63281 | 21.66 | 1348.335 | 126.72
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
From 71mm to 80mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 81mm to 90mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 91mm to 100mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Up to 150mm thick + 6mm reinforcement
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL (Insulation Measurements - Level -16 ) = |  |  |  |  | 0 | 0 | 9.306 | 482.33 | 9.306 | 482.33 | 9.306 | 0.63281 | 9.306 | 0.63281
[9 empty] | 9.306 | 482.33
0
| Upto 25 mm Thickness Insulation |  |  |  | 0 | 0 | 9.306 | 482.33 | 9.306 | 482.33
| TOTAL |  |  |  | 0 | 0 | 9.306 | 482.33 | 9.306 | 482.33
Note on H19: Himal Kosala: WIR not approved

## in-18 (hidden)
GCS German Concrete Works LLC
Insulation Measurements - Level -18 | [8 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | WIR NUMBER | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) |  | current qty | current volume | cumulative volume | cumulative volume
[5 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 51mm to 60mm thick
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Upto 25 mm Thickness Insulation
1 | BALCONY GL 18 - 23 & S - X & 21- 23 | GCS-LX-WR-L04-00433 | 25 | 51.83 | 139.12 | 7210.5896 |  |  | 139.12 | 7210.5896 | 62.25 | 0 | 0 | 139.12 | 3.478
[6 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | GFHG65556
[6 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0
From 71mm to 80mm thick
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 81mm to 90mm thick
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 91mm to 100mm thick
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Up to 150mm thick + 6mm reinforcement
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
TOTAL (Insulation Measurements - Level -18 ) = |  |  |  |  | 139.12 | 7210.5896 | 0 | 0 | 139.12 | 7210.5896 |  | 0 | 0 | 139.12 | 3.478
[9 empty] | 139.12 | 7210.5896
0
| Upto 25 mm Thickness Insulation |  |  |  | 139.12 | 7210.5896 | 0 | 0 | 139.12 | 7210.5896
| TOTAL |  |  |  | 139.12 | 7210.5896 | 0 | 0 | 139.12 | 7210.5896

## IN-L-20 (hidden)
GCS German Concrete Works LLC
Insulation Measurements - L-20 | [8 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | Room Number | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) | current qty | current volume | cumulative volume | cumulative volume
[5 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
Balcony areas | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Upto 25 mm Thickness Insulation
1 | Balcony GL 21-24 |  | 25 | 51.83 | 22 | 1140.26 |  |  | 22 | 1140.26 | 0 | 0 | 22 | 0.55
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL (Insulation Measurements - L-20 ) = |  |  |  |  | 22 | 1140.26 | 0 | 0 | 22 | 1140.26 | 0 | 0 | 22 | 0.55
[9 empty] | 22 | 1140.26
#REF!
| Upto 25 mm Thickness Insulation |  |  |  | 22 | 1140.26 | 0 | 0 | 22 | 1140.26
| TOTAL |  |  |  | 22 | 1140.26 | 0 | 0 | 22 | 1140.26

## IN-L-21
GCS German Concrete Works LLC
Insulation Measurements - Level -21 | [8 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | wir number | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) | current qty | current volume | cumulative volume | cumulative volume
[5 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 51mm to 60mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Upto 25 mm Thickness Insulation
1 | Balcony GL U-X & 22-23 | GCS-AX-WR-ML-00462 | 68 | 51.83 |  | 0 | 9.153 | 474.4 | 9.153 | 474.4 | 9.153 | 0.6224 | 9.153 | 0.6224 | 21.66 | 1348.335 | 126.72
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
From 71mm to 80mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 81mm to 90mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 91mm to 100mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Up to 150mm thick + 6mm reinforcement
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL (Insulation Measurements - Level -21 ) = |  |  |  |  | 0 | 0 | 9.153 | 474.4 | 9.153 | 474.4 | 9.153 | 0.6224 | 9.153 | 0.6224
[9 empty] | 9.153 | 474.4
0
| Upto 25 mm Thickness Insulation |  |  |  | 0 | 0 | 9.153 | 474.4 | 9.153 | 474.4
| TOTAL |  |  |  | 0 | 0 | 9.153 | 474.4 | 9.153 | 474.4
Note on H19: Himal Kosala: WIR not approved

## in-l-22 (hidden)
GCS German Concrete Works LLC
Insulation Measurements - L-22 | [8 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | Room Number | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) | current qty | current volume | cumulative volume | cumulative volume
[5 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
Balcony areas | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Upto 25 mm Thickness Insulation
1 | Balcony GL 21-24 |  | 25 | 51.83 | 23.3 | 1207.639 |  |  | 23.3 | 1207.639 | 0 | 0 | 23.3 | 0.5825
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL (Insulation Measurements - L-22 ) = |  |  |  |  | 23.3 | 1207.639 | 0 | 0 | 23.3 | 1207.639 | 0 | 0 | 23.3 | 0.5825
[9 empty] | 23.3 | 1207.639
#REF!
| Upto 25 mm Thickness Insulation |  |  |  | 23.3 | 1207.639 | 0 | 0 | 23.3 | 1207.639
| TOTAL |  |  |  | 23.3 | 1207.639 | 0 | 0 | 23.3 | 1207.639

## in-23
GCS German Concrete Works LLC
Insulation Measurements - Level -23 | [8 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | WIR NUMBER | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) |  | current qty | current volume | cumulative volume | cumulative volume
[5 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
From 51mm to 60mm thick
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Upto 25 mm Thickness Insulation
1 | BALCONY GL 02 - 08 | GCS-AX-WR-L023-00435 | 25 | 51.83 | 90.54 | 4692.6882 |  |  | 90.54 | 4692.6882 | 62.25 | 0 | 0 | 90.54 | 2.2635
1 | Balcony GL C TO H | GCS-AX-WR-L23-00455 | 25 | 51.83 |  |  | 55.79 | 2891.5957 | 55.79 | 2891.5957 |  | 55.79 | 1.3947 | 55.79 | 1.3947 | GFHG65556
2 | Balcony GL 7 TO 12 & C-D | GCS-AX-WR-L23-00455 | 25 | 51.83 |  |  | 67.91 | 3519.7753 | 67.91 | 3519.7753 |  | 67.91 | 1.6978 | 67.91 | 1.6978
3 | Balcony GL 7 TO 12 & G-H | GCS-AX-WR-L23-00455 | 25 | 51.83 |  |  | 67.32 | 3489.1956 | 67.32 | 3489.1956 |  | 67.32 | 1.683 | 67.32 | 1.683
4 | Balcony GL U-X & 22-23 | GCS-AX-WR-ML-00462 | 68 | 51.83 |  |  | 20.295 | 1051.8899 | 20.295 | 1051.8899 |  | 20.295 | 1.3801 | 20.295 | 1.3801
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
TOTAL (Insulation Measurements - Level -23 ) = |  |  |  |  | 90.54 | 4692.6882 | 211.315 | 10952.4564 | 301.855 | 15645.1446 |  | 211.315 | 6.1556 | 301.855 | 8.4191
[9 empty] | 301.855 | 15645.1446
0
| Upto 25 mm Thickness Insulation |  |  |  | 90.54 | 4692.6882 | 211.315 | 10952.4564 | 301.855 | 15645.1446
| TOTAL |  |  |  | 90.54 | 4692.6882 | 211.315 | 10952.4564 | 301.855 | 15645.1446

## IN-L-25
GCS German Concrete Works LLC
Insulation Measurements - Level -25 | [9 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | Room Number | wir no | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) | current qty | current volume | cumulative volume | cumulative volume
[6 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 51mm to 60mm thick
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Upto 25 mm Thickness Insulation
1 | Balcony GL 21-22 |  |  | 25 | 51.83 | 10.76 | 557.6908 |  |  | 10.76 | 557.6908 | 0 | 0 | 10.76 | 0.269
2 | Balcony GL 18-19 |  |  | 25 | 51.83 | 8.04 | 416.7132 |  |  | 8.04 | 416.7132 | 0 | 0 | 8.04 | 0.201 | GCS-LX-WR-L25-00380
3 | Balcony GL 14-15 |  |  | 25 | 51.83 | 9.88 | 512.0804 |  |  | 9.88 | 512.0804 | 0 | 0 | 9.88 | 0.247
4 | Pool plant area balcony |  | GCS-LX-WR-L25-00396_00_B &GCS-LX-WR-L25-00380 | 25 | 51.83 | 80.38 | 4166.0954 |  |  | 80.38 | 4166.0954 | 0 | 0 | 80.38 | 2.0095
5 | Balcony GL U-X & 22-23 |  | GCS-AX-WR-ML-00462 | 68 | 62.25 |  |  | 9.396 | 584.901 | 9.396 | 584.901 | 9.396 | 0.63893 | 9.396 | 0.63893
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL (Insulation Measurements - Level -25 ) = | [5 empty] | 109.06 | 5652.5798 | 9.396 | 584.901 | 118.456 | 6237.4808 | 9.396 | 0.63893 | 118.456 | 3.3654
[10 empty] | 118.456 | 6237.4808
0
| Upto 25 mm Thickness Insulation |  |  |  |  | 109.06 | 5652.5798 | 9.396 | 584.901 | 118.456 | 6237.4808
| TOTAL |  |  |  |  | 109.06 | 5652.5798 | 9.396 | 584.901 | 118.456 | 6237.4808

## IN-L-26 (hidden)
GCS German Concrete Works LLC
Insulation Measurements - Level -26 | [8 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | Room Number | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) | current qty | current volume | cumulative volume | cumulative volume
[5 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 51mm to 60mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Upto 25 mm Thickness Insulation
1 | Balcony GL 18-19 |  | 25 | 51.83 | 8.32 | 431.2256 |  |  | 8.32 | 431.2256 | 0 | 0 | 8.32 | 0.208
2 | Balcony GL 14-15 | GCS-AX-WR-L26-00408 | 25 | 51.83 | 10 | 518.3 |  |  | 10 | 518.3 | 0 | 0 | 10 | 0.25
3 | Balcony GL 20-24 | GCS-AX-WR-L26-00408 | 25 | 51.83 | 144 | 7463.52 |  |  | 144 | 7463.52 | 0 | 0 | 144 | 3.6
4 | Balcony GL 12-15 | GCS-AX-WR-L26-00420 | 25 | 51.83 | 13.17 | 682.6011 |  | 0 | 13.17 | 682.6011
5 | PENTHOUSE P4 BALCONY | GCS-AX-WR-L26-00413 | 68 | 51.83 | 132.3 | 6857.109 |  | 0 | 132.3 | 6857.109 | 0 | 0 | 132.3 | 8.9964
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL (Insulation Measurements - Level -26 ) = |  |  |  |  | 307.79 | 15952.7557 | 0 | 0 | 307.79 | 15952.7557 | 0 | 0 | 294.62 | 13.0544
[9 empty] | 307.79 | 15952.7557
0
| Upto 25 mm Thickness Insulation |  |  |  | 307.79 | 15952.7557 | 0 | 0 | 307.79 | 15952.7557
| TOTAL |  |  |  | 307.79 | 15952.7557 | 0 | 0 | 307.79 | 15952.7557

## in-l-27
GCS German Concrete Works LLC
Insulation Measurements - Level -27 | [9 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | Room Number | wir no | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) | current qty | current volume | cumulative volume | cumulative volume
[6 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 51mm to 60mm thick
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Upto 25 mm Thickness Insulation
1 | Balcony GL 15-22 |  | GCS-AX-WR-L27-00377 | 25 | 51.83 | 93.28 | 4834.7024 |  |  | 93.28 | 4834.7024 | 0 | 0 | 93.28 | 2.332
2 | Balcony GL 15-19 |  | GCS-AX-WR-L27-00377 | 25 | 51.83 | 48.81 | 2529.8223 |  |  | 48.81 | 2529.8223 | 0 | 0 | 48.81 | 1.2203
3 | Pool plant area balcony |  | GCS-AX-WR-L27-00386&GCS-LX-WR-L27-00397_00_B | 25 | 51.83 | 155.24 | 8046.0892 |  |  | 155.24 | 8046.0892 |  |  |  |  | GCS-LX-WR-L27-00397_00_B (1)
4 | Balcony GL 03-04 |  | GCS-AX-WR-L27-00386 | 25 | 51.83 | 18.34 | 950.5622 |  |  | 18.34 | 950.5622
5 | Balcony GL 03-04 |  | GCS-AX-WR-L27-00414 | 25 | 51.83 | 15.65 | 811.1395 |  |  | 15.65 | 811.1395
6 | Balcony GL 14-15 |  | GCS-AX-WR-L27-00444 | 25 | 51.83 | 13.08 | 677.9364 |  |  | 13.08 | 677.9364 |  |  |  | 0.327
7 | Balcony GL U-X & 22-23 |  | GCS-AX-WR-L27-00448 | 25 | 51.83 |  |  | 21.85 | 1132.4855 | 21.85 | 1132.4855 | 21.85 | 0.54625 | 21.85 | 0.54625
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL (Insulation Measurements - Level -27 ) = | [5 empty] | 344.4 | 17850.252 | 21.85 | 1132.4855 | 366.25 | 18982.7375 | 21.85 | 0.54625 | 163.94 | 4.4255
[10 empty] | 366.25 | 18982.7375
0
| Upto 25 mm Thickness Insulation |  |  |  |  | 344.4 | 17850.252 | 21.85 | 1132.4855 | 366.25 | 18982.7375
| TOTAL |  |  |  |  | 344.4 | 17850.252 | 21.85 | 1132.4855 | 366.25 | 18982.7375

## IN-L-28
GCS German Concrete Works LLC
Insulation Measurements - Level -28 | [9 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | Room Number | wir no | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) | current qty | current volume | cumulative volume | cumulative volume
[6 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 51mm to 60mm thick
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Upto 25 mm Thickness Insulation
1 | Penthouse P5 balcony |  | GCS-AX-WR-L28-00421 | 25 | 51.83 | 15.96 | 827.2068 |  | 0 | 15.96 | 827.2068 | 0 | 0 | 15.96 | 0.399
2 | Balcony GL Q-X & 22-24 |  | GCS-AX-WR-L28-00463 | 25 | 51.83 |  | 0 | 57.45 | 2977.6335 | 57.45 | 2977.6335
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL (Insulation Measurements - Level -28 ) = | [5 empty] | 15.96 | 827.2068 | 57.45 | 2977.6335 | 73.41 | 3804.8403 | 0 | 0 | 15.96 | 0.399
[10 empty] | 73.41 | 3804.8403
0
| Upto 25 mm Thickness Insulation |  |  |  |  | 15.96 | 827.2068 | 57.45 | 2977.6335 | 73.41 | 3804.8403
| TOTAL |  |  |  |  | 15.96 | 827.2068 | 57.45 | 2977.6335 | 73.41 | 3804.8403

## in-l-29
GCS German Concrete Works LLC
Insulation Measurements - Level -29 | [8 empty] | 2023-01-20
PY-2879-1172-008
SN | Description | wir no | Thickness (mm) | Rate (AED) | Previous |  | Current |  | Total Area (m2) | Total Amount (AED) | current qty | current volume | cumulative volume | cumulative volume
[5 empty] | Area (m2) | Amount (AED) | Area (m2) | Amount (AED)
From 41mm to 50mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
From 51mm to 60mm thick
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Upto 25 mm Thickness Insulation
1 | Area-01 month of Jan - GL 13-23 & Q-X | GCS-AX-WR-L29-00453&00460 | 25 | 51.83 |  |  | 606.89 | 31455.1087 | 606.89 | 31455.1087 | 606.89 | 15.1723 | 606.89 | 15.1723
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL (Insulation Measurements - Level -29 ) = |  |  |  |  | 0 | 0 | 606.89 | 31455.1087 | 606.89 | 31455.1087 | 606.89 | 15.1723 | 606.89 | 15.1723
[9 empty] | 606.89 | 31455.1087
0
| Upto 25 mm Thickness Insulation |  |  |  | 0 | 0 | 606.89 | 31455.1087 | 606.89 | 31455.1087
| TOTAL |  |  |  | 0 | 0 | 606.89 | 31455.1087 | 606.89 | 31455.1087