## Summary
No | Description | Previous | This Month | Cumulative
1 | Delivery (70%) | 18614.106 | 42501.6947 | 61115.8007
2 | Installation (15%) | 3988.737 | 0 | 3988.737
3 | Installation (15%) | 0 | 0 | 0
|  | 22602.843 | 42501.6947 | 65104.5377
| Advance payment recovery (20%) | 4520.5686 | 8500.3389 | 13020.9075
|  | 18082.2744 | 34001.3558 | 52083.6302

## Khansaheb - Door Schedule
SL NO | DOOR TYPE | DOOR NAME | JAMB DEPTH | SOW | SOH | DOOR DESIGN | FRAME SHEET THICKNESS | LEAF SHEET THICKNESS | STC | INFILL | FR IN MINS | INSULATED | QTY | TOTAL UNIT PRICE | TOTAL AMOUNT IN AED | SHOP DRAWING NUMBER | STATUS | SITE INSTRUCTION | WORK ORDER | DELIVERY DATE | DO NUMBER | MIR NUMBER | STATUS | PC-01 - PREVIOUS |  |  | PC-02 - CURRENT |  |  | CUMULATIVE
GROUND FLOOR | [23 empty] | 70% Del | 15% Instn | 15% Instn | 70% Del | 15% Instn | 15% Instn | 70% Del | 15% Instn | 15% Instn
1 | D-09a | LGF10 | 150 | 1450 | 2400 | DOUBLE LEAF STEEL DOOR | 1.5MM | 1.2MM | 32 DB | ROCKWOOL | NFR | YES | 1 | 2653.285 | 2653.285 |  |  | MAIN ORDER | [11 empty] | 0
2 | D-01c | LGF122 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1 HR | NO | 1 | 1540.25 | 1540.25 | IND-AX-SD-ML-86241 |  | MAIN ORDER | 709-06 | [10 empty] | 0
3 | I | LGF123 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HR | NO | 1 | 1540.25 | 1540.25 |  |  | MAIN ORDER | 709 | 2022-10-17 | JJTR02138 | IND-AX-MR-ML-00007 | APPROVED | 1078.175 | 231.0375 |  |  |  |  | 1078.175 | 231.0375
4 | D-01b | LGF125 | 150 | 800 | 2400 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | NFR | NO | 1 | 1540.25 | 1540.25 | IND-AX-SD-ML-86237 |  | MAIN ORDER | 709-02 | 2022-12-23 | JJTR02191 | KCE-ID-MR-GF-00009 | APPROVED | 1078.175 | 231.0375 |  |  |  |  | 1078.175 | 231.0375
5 | D-01e | LGF13 | 150 | 1000 | 2400 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | NFR | NO | 1 | 1778.3 | 1778.3 | IND-AX-SD-ML-86297 |  | MAIN ORDER | 709-03 | [10 empty] | 0
6 | D-01c | LGF139 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1 HR | NO | 1 | 1540.25 | 1540.25 | IND-AX-SD-ML-86245 | APPROVED | MAIN ORDER | [11 empty] | 0
7 | AH-03 | LGF198 | 150 | 900 | 1200 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | ROCKWOOL | 1.5 HR | YES | 1 | 1374.9375 | 1374.9375 | IND-AX-SD-ML-86279 | APPROVED | MAIN ORDER | 709-01 | 2022-11-29 | JJTR02174 | KCE-AX-MR-ML-00067 | APPROVED | 962.4562 | 206.2406 |  |  |  |  | 962.4562 | 206.2406
8 | D-01h | LGF51 | 150 | 1200 | 2400 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | ROCKWOOL | NFR | YES | 1 | 2196.21 | 2196.21 | IND-AX-SD-ML-86261 | APPROVED | MAIN ORDER | [11 empty] | 0
9 | D-09a | LGF57 | 150 | 2000 | 2750 | DOUBLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | ROCKWOOL | 1.5 HR | YES | 1 | 3855.4375 | 3855.4375 |  |  | MAIN ORDER | [11 empty] | 0
10 | D-01h | LGF58 | 150 | 1200 | 2400 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HR | NO | 1 | 2063.96 | 2063.96 | IND-AX-SD-ML-86263 | APPROVED | MAIN ORDER | [11 empty] | 0
11 | D-01d | LGF62 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | NFR | NO | 1 | 1599.7625 | 1599.7625 | IND-AX-SD-ML-86257 | APPROVED | MAIN ORDER | [11 empty] | 0
12 | D-01e | LGF64 | 150 | 1000 | 2400 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1 HR | NO | 1 | 1778.3 | 1778.3 | IND-AX-SD-ML-86259 | APPROVED | MAIN ORDER | [11 empty] | 0
LEVEL - 01 | [13 empty] | 0 | 0 | [14 empty] | 0
13 | D-06e | L0108 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1 HR | NO | 1 | 1540.25 | 1540.25 | IND-AX-SD-ML-86271 | APPROVED | MAIN ORDER | 709-01 | 2022-11-29 | JJTR02174 | KCE-AX-MR-ML-00067 | APPROVED | 1078.175 | 231.0375 |  |  |  |  | 1078.175 | 231.0375
14 | D-01c | L0109 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HR | NO | 1 | 1540.25 | 1540.25 | IND-AX-SD-ML-86239 |  | MAIN ORDER | [11 empty] | 0
LEVEL - 02 | [13 empty] | 0 | 0 | [14 empty] | 0
15 | D-04a | L02118 | 150 | 900 | 2400 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | HONEYCOMB | NFR | NO | 1 | 1899.97 | 1899.97 | IND-AX-SD-ML-86267 | APPROVED | MAIN ORDER | 709-01 | 2022-11-29 | JJTR02174 | KCE-AX-MR-ML-00067 | APPROVED | 1329.979 | 284.9955 |  |  |  |  | 1329.979 | 284.9955
16 | D-01c | L0212 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HR | NO | 1 | 1540.25 | 1540.25 | IND-AX-SD-ML-86245 | APPROVED | MAIN ORDER | [11 empty] | 0
17 | D-01c | L0213 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HR | NO | 1 | 1540.25 | 1540.25 | IND-AX-SD-ML-86239 |  | MAIN ORDER | [11 empty] | 0
18 | D-04a | L02120 | 150 | 900 | 2400 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | NFR | NO | 1 | 1635.47 | 1635.47 | IND-AX-SD-ML-86269 | APPROVED | MAIN ORDER | 709-01 | 2022-11-29 | JJTR02174 | KCE-AX-MR-ML-00067 | APPROVED | 1144.829 | 245.3205 |  |  |  |  | 1144.829 | 245.3205
19 | D-03b | L0220 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HR | NO | 1 | 2246.465 | 2246.465 |  |  | MAIN ORDER | [11 empty] | 0
LEVEL - 03 | [13 empty] | 0 | 0 | [14 empty] | 0
20 | D-01c | L0304 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.5MM | 43 DB | ROCKWOOL | 1 HR | YES | 1 | 1804.75 | 1804.75 | IND-AX-SD-ML-86247 | APPROVED | MAIN ORDER | 709-01 | 2022-11-29 | JJTR02174 | KCE-AX-MR-ML-00067 | APPROVED | 1263.325 | 270.7125 |  |  |  |  | 1263.325 | 270.7125
21 | D-01c | L0318 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1 HR | NO | 1 | 1540.25 | 1540.25 | IND-AX-SD-ML-86243 |  | MAIN ORDER | [11 empty] | 0
22 | D-01c | L0319 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HR | NO | 1 | 1540.25 | 1540.25 | IND-AX-SD-ML-86239 |  | MAIN ORDER | [11 empty] | 0
LEVEL - 04 | [13 empty] | 0 | 0 | [14 empty] | 0
23 | D-01c | L0407 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HR | NO | 1 | 1540.25 | 1540.25 | IND-AX-SD-ML-86245 | APPROVED | MAIN ORDER | [11 empty] | 0
24 | D-01c | L0444 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HR | NO | 1 | 1540.25 | 1540.25 | IND-AX-SD-ML-86239 |  | MAIN ORDER | [11 empty] | 0
25 | D-01c | L0447 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1 HR | NO | 1 | 1540.25 | 1540.25 | IND-AX-SD-ML-86241 |  | MAIN ORDER | 709-06 | [10 empty] | 0
26 | D-01c | L0448 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HR | NO | 1 | 1540.25 | 1540.25 | IND-AX-SD-ML-86239 |  | MAIN ORDER | [11 empty] | 0
LEVEL - 05 | [13 empty] | 0 | 0 | [14 empty] | 0
27 | D-01c | L0503 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | ROCKWOOL | 1 HR | YES | 1 | 1672.5 | 1672.5 | IND-AX-SD-ML-86247 | APPROVED | MAIN ORDER | 709-01 | 2022-11-29 | JJTR02174 | KCE-AX-MR-ML-00067 | APPROVED | 1170.75 | 250.875 |  |  |  |  | 1170.75 | 250.875
28 | D-01c | L0506 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HR | NO | 1 | 1540.25 | 1540.25 | IND-AX-SD-ML-86245 | APPROVED | MAIN ORDER | [11 empty] | 0
29 | D-01c | L0517 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1 HR | NO | 1 | 1540.25 | 1540.25 | IND-AX-SD-ML-86241 |  | MAIN ORDER | 709-06 | [10 empty] | 0
LEVEL - 06 | [13 empty] | 0 | 0 | [14 empty] | 0
30 | D-01d | L06R13 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HR | NO | 1 | 1599.7625 | 1599.7625 | IND-AX-SD-ML-86249 | APPROVED | MAIN ORDER | [11 empty] | 0
LEVEL - 07 | [13 empty] | 0 | 0 | [14 empty] | 0
31 | D-01c | L07R10 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HR | NO | 1 | 1540.25 | 1540.25 | IND-AX-SD-ML-86245 | APPROVED | MAIN ORDER | [11 empty] | 0
LEVEL - 10 | [13 empty] | 0 | 0 | [14 empty] | 0
32 | D-03b | L10R22 | 150 | 1100 | 2100 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | HONEYCOMB | NFR | NO | 1 | 1989.2387 | 1989.2387 | IND-AX-SD-ML-86299 |  | MAIN ORDER | 709-04 | [10 empty] | 0
LEVEL - 13 | [13 empty] | 0 | 0 | [14 empty] | 0
33 | D-01c | L14H09 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | ROCKWOOL | 1.5 HR | YES | 1 | 1672.5 | 1672.5 | IND-AX-SD-ML-86102 | APPROVED | MAIN ORDER | 709 | 2022-10-17 | JJTR02138 | IND-AX-MR-ML-00007 | APPROVED | 1170.75 | 250.875 |  |  |  |  | 1170.75 | 250.875
LEVEL - 14 | [13 empty] | 0 | 0 | [14 empty] | 0
34 | D-01c | L15H09 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | ROCKWOOL | 1.5 HR | YES | 1 | 1672.5 | 1672.5 | IND-AX-SD-ML-86102 | APPROVED | MAIN ORDER | 709 | 2022-10-17 | JJTR02138 | IND-AX-MR-ML-00007 | APPROVED | 1170.75 | 250.875 |  |  |  |  | 1170.75 | 250.875
35 | D-01d | L15H10 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HR | NO | 1 | 1599.7625 | 1599.7625 | IND-AX-SD-ML-86249/ IND-AX-SD-ML-86311 | APPROVED | MAIN ORDER | 709-05 | 2023-01-26 | JJTR02219 | [8 empty] | 0
LEVEL - 17 | [13 empty] | 0 | 0 | [14 empty] | 0
36 | D-03b | L18H01 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HR | NO | 1 | 2246.465 | 2246.465 |  |  | MAIN ORDER | [11 empty] | 0
37 | D-20b | L18H03 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1 HR | NO | 1 | 2246.465 | 2246.465 | IND-AX-SD-ML-86273 | APPROVED | MAIN ORDER | 709-05 | 2023-01-26 | JJTR02219 | [8 empty] | 0
38 | D-20b | L18H04 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | 35 DB | ROCKWOOL | 1 HR | NO | 1 | 2378.715 | 2378.715 | IND-AX-SD-ML-86277 | APPROVED | MAIN ORDER | 709-05 | 2023-01-26 | JJTR02219 | [8 empty] | 0
39 | D-01g | L18H05 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.5MM | 43 DB | ROCKWOOL | 1.5 HR | NO | 1 | 2148.6 | 2148.6 |  |  | MAIN ORDER | [11 empty] | 0
40 | D-01c | L18H09 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | ROCKWOOL | 1.5 HR | YES | 1 | 1672.5 | 1672.5 | IND-AX-SD-ML-86102 | APPROVED | MAIN ORDER | 709 | 2022-10-17 | JJTR02138 | IND-AX-MR-ML-00007 | APPROVED | 1170.75 | 250.875 |  |  |  |  | 1170.75 | 250.875
41 | D-03b | L18H20 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HR | NO | 1 | 2246.465 | 2246.465 |  |  | MAIN ORDER | [11 empty] | 0
42 | D-02e | L18H21 | 150 | 1800 | 2400 | DOUBLE LEAF STEEL DOOR | 1.5MM | 1.5MM | 43 DB | ROCKWOOL | 1.5 HR | NO | 1 | 3438.85 | 3438.85 | IND-AX-SD-ML-86265 | APPROVED | MAIN ORDER | 709-05 | 2023-01-26 | JJTR02219 | [8 empty] | 0
LEVEL - 18 | [13 empty] | 0 | 0 | [14 empty] | 0
43 | D-20b | L19H03 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1 HR | NO | 1 | 2246.465 | 2246.465 | IND-AX-SD-ML-86273 | APPROVED | MAIN ORDER | 709-05 | 2023-01-26 | JJTR02219 | [8 empty] | 0
44 | D-20b | L19H04 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | 35 DB | ROCKWOOL | 1 HR | NO | 1 | 2378.715 | 2378.715 | IND-AX-SD-ML-86275 | APPROVED | MAIN ORDER | [11 empty] | 0
45 | D-01g | L19H05 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.5MM | 43 DB | ROCKWOOL | 1.5 HR | NO | 1 | 2148.6 | 2148.6 |  |  | MAIN ORDER | [11 empty] | 0
46 | D-03b | L19H06 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HR | NO | 1 | 2246.465 | 2246.465 |  |  | MAIN ORDER | [11 empty] | 0
47 | D-20b | L19H07 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | 35 DB | ROCKWOOL | 1 HR | NO | 1 | 2378.715 | 2378.715 | IND-AX-SD-ML-86275 | APPROVED | MAIN ORDER | [11 empty] | 0
48 | D-01c | L19H09 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | ROCKWOOL | 1.5 HR | YES | 1 | 1672.5 | 1672.5 | IND-AX-SD-ML-86102 | APPROVED | MAIN ORDER | 709 | 2022-10-17 | JJTR02138 | IND-AX-MR-ML-00007 | APPROVED | 1170.75 | 250.875 |  |  |  |  | 1170.75 | 250.875
49 | D-01g | L19H11 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HR | NO | 1 | 1849.715 | 1849.715 |  |  | MAIN ORDER | [11 empty] | 0
50 | D-01g | L19H12 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HR | NO | 1 | 1849.715 | 1849.715 |  |  | MAIN ORDER | [11 empty] | 0
51 | D-01g | L19H13 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HR | NO | 1 | 1849.715 | 1849.715 |  |  | MAIN ORDER | [11 empty] | 0
52 | D-01g | L19H15 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HR | NO | 1 | 1849.715 | 1849.715 |  |  | MAIN ORDER | [11 empty] | 0
53 | D-01c | L20H09 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | ROCKWOOL | 1.5 HR | YES | 1 | 1672.5 | 1672.5 | IND-AX-SD-ML-86102 | APPROVED | MAIN ORDER | 709 | 2022-10-17 | JJTR02138 | IND-AX-MR-ML-00007 | APPROVED | 1170.75 | 250.875 |  |  |  |  | 1170.75 | 250.875
LEVEL - 23 | [13 empty] | 0 | 0 | [14 empty] | 0
54 | D-19a | L24R04 | 150 | 2000 | 2100 | DOUBLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1 HR | NO | 1 | 2949.525 | 2949.525 | IND-AX-SD-ML-86285 | APPROVED | MAIN ORDER | 709-06 | [10 empty] | 0
55 | D-01c | L24R12 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HR | NO | 1 | 1540.25 | 1540.25 | IND-AX-SD-ML-86298 |  | MAIN ORDER | [11 empty] | 0
LEVEL - 28 | [13 empty] | 0 | 0 | [14 empty] | 0
56 | D-03b | L29H06 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HR | NO | 1 | 2246.465 | 2246.465 |  |  | MAIN ORDER | [11 empty] | 0
57 | D-20b | L29H07 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | 35 DB | ROCKWOOL | 1 HR | NO | 1 | 2378.715 | 2378.715 | IND-AX-SD-ML-86275 | APPROVED | MAIN ORDER | [11 empty] | 0
58 | D-03b | L29H11 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HR | NO | 1 | 2246.465 | 2246.465 |  |  | MAIN ORDER | [11 empty] | 0
59 | D-01d | L29H12 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.5MM | 43 DB | ROCKWOOL | 1 HR | NO | 1 | 1870.875 | 1870.875 | IND-AX-SD-ML-86255 | APPROVED | MAIN ORDER | [11 empty] | 0
60 | D-04b | L29H14 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1 HR | NO | 1 | 1599.7625 | 1599.7625 | IND-AX-SD-ML-86283 | APPROVED | MAIN ORDER | 709-05 | 2023-01-26 | JJTR02219 | [8 empty] | 0
61 | D-01d | L29H16 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HR | NO | 1 | 1599.7625 | 1599.7625 | IND-AX-SD-ML-86281 | APPROVED | MAIN ORDER | 709-05 | 2023-01-26 | JJTR02219 | [8 empty] | 0
62 | D-01d | L29H43 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.5MM | 43 DB | ROCKWOOL | 1.5 HR | NO | 1 | 1870.875 | 1870.875 | IND-AX-SD-ML-86253 | APPROVED | MAIN ORDER | 709-05 | 2023-01-26 | JJTR02219 | [8 empty] | 0
63 | D-01d | L29H44 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.5MM | 43 DB | ROCKWOOL | 1.5 HR | NO | 1 | 1870.875 | 1870.875 | IND-AX-SD-ML-86251 | APPROVED | MAIN ORDER | 709-05 | 2023-01-26 | JJTR02219 | [8 empty] | 0
LEVEL - 31 | [29 empty] | 0
64 | D-03b | L32R06 | 150 | 1100 | 2100 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.5MM | 43 DB | ROCKWOOL | NFR | YES | 1 | 2274.2375 | 2274.2375 |  |  | MAIN ORDER | [11 empty] | 0
SUB TOTAL FOR SUPPLY AND INSTALLATION WORKS FOR STEEL DOORS | [12 empty] | 64 |  | 122246.0487 |  |  | MAIN ORDER | [11 empty] | 0
BASEMENT - B1 | [29 empty] | 0
1 | D-14 | LB1227 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
2 | D-14 | LB1229 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
GROUND FLOOR | [29 empty] | 0
3 | D-04h | LGF04 | 150 | 1200 | 2400 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
4 | D-01h | LGF05 | 150 | 1200 | 2400 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
5 | D-02k | LGF06 | 150 | 1400 | 2100 | DOUBLE LEAF STEEL DOOR INSTALLATION WORKS | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 450 | 450 |  |  | MAIN ORDER | [11 empty] | 0
6 | D-03d | LGF07 | 150 | 1200 | 2400 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
7 | D-09c | LGF47 | 150 | 1800 | 2400 | DOUBLE LEAF STEEL DOOR INSTALLATION WORKS | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 450 | 450 |  |  | MAIN ORDER | [11 empty] | 0
8 | D-03b | LGF48 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
9 | D-03b | LGF49 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
10 | D-03a | LGF52 | 150 | 1100 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
11 | D-09e | LGF53 | 150 | 2100 | 2400 | DOUBLE LEAF STEEL DOOR INSTALLATION WORKS | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 450 | 450 |  |  | MAIN ORDER | [11 empty] | 0
12 | D-03d | LGF54 | 150 | 1200 | 2400 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
13 | D-03d | LGF55 | 150 | 1200 | 2400 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
14 | D-12c | LGF56 | 150 | 1200 | 2400 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
15 | D-02e | LGF71 | 150 | 1800 | 2400 | DOUBLE LEAF STEEL DOOR INSTALLATION WORKS | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 450 | 450 |  |  | MAIN ORDER | [11 empty] | 0
16 | D-02e | LGF77 | 150 | 1800 | 2400 | DOUBLE LEAF STEEL DOOR INSTALLATION WORKS | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 450 | 450 | IND-AX-SD-ML-86329 |  | MAIN ORDER | [11 empty] | 0
LEVEL - 01 | [29 empty] | 0
17 | D-03a | L0102 | 150 | 1100 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
18 | D-01d | L0110 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
LEVEL - 02 | [29 empty] | 0
19 | D-03d | L0201 | 150 | 1200 | 2400 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
20 | D-05c | L0202 | 150 | 1500 | 2100 | DOUBLE LEAF STEEL DOOR INSTALLATION WORKS | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 450 | 450 |  |  | MAIN ORDER | [11 empty] | 0
21 | D-05c | L0203 | 150 | 1500 | 2100 | DOUBLE LEAF STEEL DOOR INSTALLATION WORKS | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 450 | 450 |  |  | MAIN ORDER | [11 empty] | 0
22 | D-05c | L0204 | 150 | 1500 | 2100 | DOUBLE LEAF STEEL DOOR INSTALLATION WORKS | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 450 | 450 |  |  | MAIN ORDER | [11 empty] | 0
23 | D-03a | L0207 | 150 | 1100 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
24 | D-03a | L0221 | 150 | 1100 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
25 | D-01g | L0223 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
26 | D-01g | L0226 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
27 | D-01d | L0230 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
28 | D-01c | L0237 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
LEVEL - 03 | [29 empty] | 0
29 | D-03a | L0302 | 150 | 1100 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
30 | D-03d | L0312 | 150 | 1200 | 2400 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
31 | D-01d | L0320 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
32 | D-01d | L0338 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
LEVEL - 04 | [29 empty] | 0
33 | D-01d | L0419 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
34 | D-03a | L0431 | 150 | 1100 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
35 | D-01g | L0442 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
36 | D-03a | L0452 | 150 | 1100 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
LEVEL - 05 | [29 empty] | 0
37 | D-03b | L0501 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
38 | D-02g | L0502 | 150 | 2000 | 2100 | DOUBLE LEAF STEEL DOOR INSTALLATION WORKS | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 450 | 450 |  |  | MAIN ORDER | [11 empty] | 0
39 | D-01g | L0505 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
40 | D-01g | L0514 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
41 | D-03b | L0515 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
42 | D-01d | L0518 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
43 | D-01d | L0524 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
LEVEL - 08 | [29 empty] | 0
44 | D-01c | L08H08 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
LEVEL - 10 | [29 empty] | 0
45 | D-01c | L10H08 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
46 | D-01c | L10R23 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
LEVEL - 11 | [29 empty] | 0
47 | D-01c | L11H08 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
LEVEL - 14 | [29 empty] | 0
48 | D-01c | L15H08 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
LEVEL - 17 | [29 empty] | 0
49 | D-01c | L18H08 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
LEVEL - 19 | [29 empty] | 0
50 | D-01g | L20H05 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
LEVEL - 20 | [29 empty] | 0
51 | D-01g | L21H05 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
52 | D-01c | L21H08 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
53 | D-01c | L21H09 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
LEVEL - 21 | [29 empty] | 0
54 | D-01c | L22H09 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
LEVEL - 22 | [29 empty] | 0
55 | D-01c | L23H08 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
56 | D-01c | L23H09 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
LEVEL - 23 | [29 empty] | 0
57 | D-01c | L24H08 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
58 | D-01c | L24H09 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
59 | D-02d | L24R01 | 150 | 1700 | 2100 | DOUBLE LEAF STEEL DOOR INSTALLATION WORKS | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 450 | 450 |  |  | MAIN ORDER | [11 empty] | 0
60 | D-01g | L24R05 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
61 | D-01c | L24R06 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
62 | D-03b | L24R21 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
63 | D-02d | L24R28 | 150 | 1700 | 2100 | DOUBLE LEAF STEEL DOOR INSTALLATION WORKS | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 450 | 450 |  |  | MAIN ORDER | [11 empty] | 0
LEVEL - 24 | [29 empty] | 0
64 | D-01c | L25H09 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
LEVEL - 25 | [29 empty] | 0
65 | D-01c | L26H08 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
66 | D-01c | L26H09 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
LEVEL - 26 | [29 empty] | 0
67 | D-01c | L27H09 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
LEVEL - 27 | [29 empty] | 0
68 | D-01c | L28H08 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
69 | D-01c | L28H09 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
LEVEL - 28 | [29 empty] | 0
70 | D-01c | L29AH01 | 150 | 1100 | 1900 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
71 | D-01c | L29AH02 | 150 | 1100 | 1900 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
72 | D-01g | L29H05 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
73 | D-01c | L29H08 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
74 | D-01c | L29H09 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
75 | D-01g | L29H53 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
LEVEL - 29 | [29 empty] | 0
76 | D-01c | L30R07 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
LEVEL - 30 | [29 empty] | 0
77 | D-03a | L31H01 | 150 | 1100 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
78 | D-01d | L31H04 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
79 | D-01c | L31R11 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
LEVEL - 31 | [29 empty] | 0
80 | D-03b | L32R01 | 150 | 1100 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
81 | D-01g | L32R02 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
82 | D-01d | L32R04 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
83 | D-01g | L32R05 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
84 | D-03b | L32R07 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
85 | D-01g | L32R09 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
86 | D-01g | L32R10 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
87 | D-01d | L32R11 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
88 | D-01d | L32R12 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
89 | D-01c | L32R13 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR INSTALLATION WORKS ONLY | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 350 | 350 |  |  | MAIN ORDER | [11 empty] | 0
SUB TOTAL FOR INSTALLATION WORKS FOR STEEL DOORS | [12 empty] | 89 |  | 32250 |  |  | MAIN ORDER | [11 empty] | 0
GRAND TOTAL IN AED ONE HUNDRED FIFTY FOUR THOUSAND FOUR HUNDRED NINETY SIX AND FIVE FILS ONLY | [14 empty] | 154496.0487 | [14 empty] | 0
SITE INSTRUCTION NO : E11/K145/AK/dm/212 | [29 empty] | 0
65 | D-03b | LGF16 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HRS | N/A | 1 | 2149.715 | 2149.715 | IND-AX-SD-ML-86289 |  | E11/K145/AK/dm/212 | 765 | [10 empty] | 0
66 | D-03b | LGF17 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HRS | N/A | 1 | 2149.715 | 2149.715 | IND-AX-SD-ML-86289 |  | E11/K145/AK/dm/212 | 765 | [10 empty] | 0
67 | D-04g | LGF21 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | 35 | ROCKWOOL | 1 HRS | N/A | 1 | 1981.965 | 1981.965 | IND-AX-SD-ML-86294 |  | E11/K145/AK/dm/212 | 765 | [10 empty] | 0
68 | D-03b | LGF26 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | ROCKWOOL | 1.5 HRS | YES | 1 | 2281.965 | 2281.965 | IND-AX-SD-ML-86290 |  | E11/K145/AK/dm/212 | 765 | [10 empty] | 0
69 | D-03b | LGF27 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | ROCKWOOL | 1.5 HRS | YES | 1 | 2281.965 | 2281.965 | IND-AX-SD-ML-86290 |  | E11/K145/AK/dm/212 | 765 | [10 empty] | 0
70 | D-03d | LGF41 | 150 | 1200 | 3000 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | ROCKWOOL | 1.5 HRS | YES | 1 | 3162.75 | 3162.75 | IND-AX-SD-ML-86295 |  | E11/K145/AK/dm/212 | 765 | [10 empty] | 0
71 | D-03d | LGF42 | 150 | 1200 | 2400 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | ROCKWOOL | 1.5 HRS | YES | 1 | 2496.21 | 2496.21 | IND-AX-SD-ML-86292 | 916 | E11/K145/AK/dm/212 | 765 | [10 empty] | 0
72 | D-03d | LGF08 | 150 | 1200 | 2200 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | ROCKWOOL | 1.5 HRS | YES | 1 | 2353.38 | 2353.38 | IND-AX-SD-ML-86290 |  | E11/K145/AK/dm/212 | 765 | [10 empty] | 0
73 | D-12c | LGF78 | 150 | 1200 | 2400 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | ROCKWOOL | 1 HRS | YES | 1 | 2196.21 | 2196.21 | IND-AX-SD-ML-86293 |  | E11/K145/AK/dm/212 | 765 | [10 empty] | 0
74 | D-03a | L0449 | 150 | 1100 | 2100 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | ROCKWOOL | 1.5 HRS | YES | 1 | 2156.9887 | 2156.9887 | IND-AX-SD-ML-86291 |  | E11/K145/AK/dm/212 | [11 empty] | 0
SITE INSTRUCTION NO : E11/K145/AK/dm/223 | [29 empty] | 0
75 | ELECTRIC CABINET | LB1206 | 150 | 2000 | 2200 | DOUBLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HRS | N/A | 1 | 4044.84 | 4044.84 | IND-AX-SD-ML-86288 |  | E11/K145/AK/dm/223 | 767 |  | JJTR02208 | IND-AX-MR-ML-00012 | APPROVED |  |  |  | 2831.388 |  |  | 2831.388 | 0
76 | ELECTRIC CABINET | LB1241 | 150 | 2000 | 2200 | DOUBLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HRS | N/A | 1 | 4129.94 | 4129.94 | IND-AX-SD-ML-86288 |  | E11/K145/AK/dm/223 | 767 |  | JJTR02208 | IND-AX-MR-ML-00012 | APPROVED |  |  |  | 2890.958 |  |  | 2890.958 | 0
77 | ELECTRIC CABINET | LB1205 | 150 | 2000 | 2200 | DOUBLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HRS | N/A | 1 | 4064.48 | 4064.48 | IND-AX-SD-ML-86287 |  | E11/K145/AK/dm/223 | 767-01 |  | JJTR02208 | IND-AX-MR-ML-00012 | APPROVED |  |  |  | 2845.136 |  |  | 2845.136 | 0
78 | ELECTRIC CABINET | LB1203 | 150 | 2000 | 2200 | DOUBLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HRS | N/A | 1 | 4182.31 | 4182.31 | IND-AX-SD-ML-86287 |  | E11/K145/AK/dm/223 | 767-01 |  | JJTR02208 | IND-AX-MR-ML-00012 | APPROVED |  |  |  | 2927.617 |  |  | 2927.617 | 0
79 | ELECTRIC CABINET | LB1201 | 150 | 2000 | 2200 | (FOUR) DOUBLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HRS | N/A | 1 | 4830.41 | 4830.41 | IND-AX-SD-ML-86287 |  | E11/K145/AK/dm/223 | 767-01 | 2023-01-26 | JJTR02218 | [8 empty] | 0
80 | ELECTRIC CABINET | LB1199 | 150 | 2000 | 2200 | DOUBLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HRS | N/A | 1 | 3521.13 | 3521.13 | IND-AX-SD-ML-86287 |  | E11/K145/AK/dm/223 | 767-01 |  | JJTR02208 | IND-AX-MR-ML-00012 | APPROVED |  |  |  | 2464.791 |  |  | 2464.791 | 0
81 | ELECTRIC CABINET | LB1143 | 150 | 2000 | 2200 | DOUBLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HRS | N/A | 1 | 4568.55 | 4568.55 | IND-AX-SD-ML-86287 |  | E11/K145/AK/dm/223 | 767-01 |  | JJTR02208 | IND-AX-MR-ML-00012 | APPROVED |  |  |  | 3197.985 |  |  | 3197.985 | 0
82 | ELECTRIC CABINET | LB1198 | 150 | 2000 | 2200 | DOUBLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HRS | N/A | 1 | 4830.41 | 4830.41 | IND-AX-SD-ML-86288 |  | E11/K145/AK/dm/223 | 767 |  | JJTR02208 | IND-AX-MR-ML-00012 | APPROVED |  |  |  | 3381.287 |  |  | 3381.287 | 0
83 | ELECTRIC CABINET | LB266A | 150 | 2000 | 2200 | DOUBLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HRS | N/A | 1 | 4280.51 | 4280.51 | IND-AX-SD-ML-86288 |  | E11/K145/AK/dm/223 | 767 |  | JJTR02208 | IND-AX-MR-ML-00012 | APPROVED |  |  |  | 2696.7213 |  |  | 2696.7213 | 0
84 | ELECTRIC CABINET | LB266 | 150 | 2000 | 2200 | DOUBLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HRS | N/A | 1 | 4280.51 | 4280.51 | IND-AX-SD-ML-86288 |  | E11/K145/AK/dm/223 | 767 |  | JJTR02208 | IND-AX-MR-ML-00012 | APPROVED |  |  |  | 2696.7213 |  |  | 2696.7213 | 0
SITE INSTRUCTION NO : E11/K145/AK/dm/225 | [29 empty] | 0
85 | D-01e | L04001 | 150 | 1000 | 2400 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1 HR | NO | 1 | 2272.5 | 2272.5 | IND-AX-SD-ML-86302 |  | E11/K145/AK/dm/225 | 773 | 2023-01-26 | JJTR02214 | [8 empty] | 0
86 | D-01e | L04002 | 150 | 1000 | 2400 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1 HR | NO | 1 | 2272.5 | 2272.5 | IND-AX-SD-ML-86302 |  | E11/K145/AK/dm/225 | 773 | 2023-01-26 | JJTR02214 | [8 empty] | 0
87 | D-01e | L04003 | 150 | 1000 | 2400 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1 HR | NO | 1 | 2272.5 | 2272.5 | IND-AX-SD-ML-86302 |  | E11/K145/AK/dm/225 | 773 | 2023-01-26 | JJTR02214 | [8 empty] | 0
88 | D-01e | L04004 | 150 | 1000 | 2400 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1 HR | NO | 1 | 2272.5 | 2272.5 | IND-AX-SD-ML-86302 |  | E11/K145/AK/dm/225 | 773 | 2023-01-26 | JJTR02214 | [8 empty] | 0
89 | D-01e | L04005 | 150 | 1000 | 2400 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1 HR | NO | 1 | 2272.5 | 2272.5 | IND-AX-SD-ML-86302 |  | E11/K145/AK/dm/225 | 773 | 2023-01-26 | JJTR02214 | [8 empty] | 0
90 | D-01e | L04006 | 150 | 1000 | 2400 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1 HR | NO | 1 | 2272.5 | 2272.5 | IND-AX-SD-ML-86302 |  | E11/K145/AK/dm/225 | 773 | 2023-01-26 | JJTR02214 | [8 empty] | 0
91 | D-01e | L04007 | 150 | 1000 | 2400 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1 HR | NO | 1 | 2272.5 | 2272.5 | IND-AX-SD-ML-86302 |  | E11/K145/AK/dm/225 | 773 | 2023-01-26 | JJTR02214 | [8 empty] | 0
SITE INSTRUCTION NO : E11/K145/AK/dm/409 | [29 empty] | 0
92 | D-01c | L21H09 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | ROCKWOOL | 1.5 HR | YES | 1 | 1672.5 | 1672.5 | IND-AX-SD-ML-86102 |  | E11/K145/AK/dm/409 | 753 | 2022-11-14 | JJTR02151 | KCE-AX-MR-ML-00057 | APPROVED |  |  |  | 1053.675 |  |  | 1053.675 | 0
93 | D-01c | L22H09 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | ROCKWOOL | 1.5 HR | YES | 1 | 1672.5 | 1672.5 | IND-AX-SD-ML-86102 |  | E11/K145/AK/dm/409 | 753 | 2022-11-14 | JJTR02151 | KCE-AX-MR-ML-00057 | APPROVED |  |  |  | 1170.75 |  |  | 1170.75 | 0
94 | D-01c | L23H09 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | ROCKWOOL | 1.5 HR | YES | 1 | 1672.5 | 1672.5 | IND-AX-SD-ML-86102 |  | E11/K145/AK/dm/409 | 753 | 2022-11-14 | JJTR02151 | KCE-AX-MR-ML-00057 | APPROVED |  |  |  | 1170.75 |  |  | 1170.75 | 0
95 | D-01c | L24H09 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | ROCKWOOL | 1.5 HR | YES | 1 | 1672.5 | 1672.5 | IND-AX-SD-ML-86102 |  | E11/K145/AK/dm/409 | 753 | 2022-11-14 | JJTR02151 | KCE-AX-MR-ML-00057 | APPROVED |  |  |  | 1170.75 |  |  | 1170.75 | 0
96 | D-01c | L25H09 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | ROCKWOOL | 1.5 HR | YES | 1 | 1672.5 | 1672.5 | IND-AX-SD-ML-86102 |  | E11/K145/AK/dm/409 | 753 | 2022-11-14 | JJTR02151 | KCE-AX-MR-ML-00057 | APPROVED |  |  |  | 1170.75 |  |  | 1170.75 | 0
97 | D-01c | L26H09 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | ROCKWOOL | 1.5 HR | YES | 1 | 1672.5 | 1672.5 | IND-AX-SD-ML-86102 |  | E11/K145/AK/dm/409 | 753 | 2022-11-14 | JJTR02151 | KCE-AX-MR-ML-00057 | APPROVED |  |  |  | 1170.75 |  |  | 1170.75 | 0
98 | D-01c | L27H09 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | ROCKWOOL | 1.5 HR | YES | 1 | 1672.5 | 1672.5 | IND-AX-SD-ML-86102 |  | E11/K145/AK/dm/409 | 753 | 2022-11-14 | JJTR02151 | KCE-AX-MR-ML-00057 | APPROVED |  |  |  | 1170.75 |  |  | 1170.75 | 0
99 | D-01c | L28H09 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | ROCKWOOL | 1.5 HR | YES | 1 | 1672.5 | 1672.5 | IND-AX-SD-ML-86102 |  | E11/K145/AK/dm/409 | 753 | 2022-11-14 | JJTR02151 | KCE-AX-MR-ML-00057 | APPROVED |  |  |  | 1170.75 |  |  | 1170.75 | 0
100 | D-01c | L29H09 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | ROCKWOOL | 1.5 HR | YES | 1 | 1672.5 | 1672.5 | IND-AX-SD-ML-86102 |  | E11/K145/AK/dm/409 | 753 | 2022-11-14 | JJTR02151 | KCE-AX-MR-ML-00057 | APPROVED |  |  |  | 1170.75 |  |  | 1170.75 | 0
SITE INSTRUCTION NO : E11/K145/AK/dm/205 | [29 empty] | 0
1 |  | LGF11 | 150 | 2000 | 3000 | DOUBLE LEAF STEEL DOOR REPOWDERCOATING | [6 empty] | 1 | 1350 | 1350 |  |  | E11/K145/AK/dm/265 | [11 empty] | 0
2 |  | LGF12 | 150 | 2000 | 3000 | DOUBLE LEAF STEEL DOOR REPOWDERCOATING | [6 empty] | 1 | 1350 | 1350 |  |  | E11/K145/AK/dm/265 | [11 empty] | 0
AS PER ANIL EMAIL | [29 empty] | 0
101 | D-14 | LB1227 | 150 | 900 | 2100 | SINGLE LEAF STEEL SLIDING DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | ROCKWOOL | NFR | YES | 1 | 2054.75 | 2054.75 |  |  | E11/K145/AK/dm/537 | 761 | 2022-12-16 | 2186 | IND-AX-MR-ML-00010_00 | [7 empty] | 0
102 | D-14 | LB1229 | 150 | 900 | 2100 | SINGLE LEAF STEEL SLIDING DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | ROCKWOOL | NFR | YES | 1 | 2054.75 | 2054.75 |  |  | E11/K145/AK/dm/537 | 761 | 2022-12-16 | 2186 | IND-AX-MR-ML-00010_00 | [7 empty] | 0
103 | D-14 | LB128 | 150 | 900 | 2100 | SINGLE LEAF STEEL SLIDING DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | ROCKWOOL | NFR | YES | 1 | 2054.75 | 2054.75 |  |  | E11/K145/AK/dm/537 | 761 | 2022-12-16 | 2186 | IND-AX-MR-ML-00010_00 | [7 empty] | 0
104 | D-14 | LB129 | 150 | 900 | 2100 | SINGLE LEAF STEEL SLIDING DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | ROCKWOOL | NFR | YES | 1 | 2054.75 | 2054.75 |  |  | E11/K145/AK/dm/537 | 761 | 2022-12-16 | 2186 | IND-AX-MR-ML-00010_00 | [7 empty] | 0
105 | D-04h | LGF04 | 150 | 1200 | 2400 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | NFR | NO | 1 | 2063.96 | 2063.96 | 86342 | APPROVED | [12 empty] | 0
106 | D-02k | LGF06 | 150 | 1400 | 2100 | DOUBLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | NFR | NO | 1 | 2199.6675 | 2199.6675 | 86333 | APPROVED | [12 empty] | 0
107 | D-09c | LGF47 | 150 | 1800 | 2400 | DOUBLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | ROCKWOOL | 1.5 HRS | YES | 1 | 3753.19 | 3753.19 | 86345 | APPROVED | [12 empty] | 0
108 | D-09e | LGF53 | 150 | 2100 | 2400 | DOUBLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | ROCKWOOL | 1.5 HRS | YES | 1 | 4181.68 | 4181.68 | IND-AX-SD-ML-86346 |  |  | 761-03 |  | JJTR02209 | IND-AX-MR-ML-00012 | APPROVED |  |  |  | 2927.176 |  |  | 2927.176 | 0
109 | D-02e | LGF71 | 150 | 1800 | 2400 | DOUBLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | HONEYCOMB | NFR | NO | 1 | 3520.94 | 3520.94 | 86328 | APPROVED |  | 761-05 | [10 empty] | 0
110 | D-02e | LGF77 | 150 | 1800 | 2400 | DOUBLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1 HR | NO | 1 | 3620.94 | 3620.94 | IND-AX-SD-ML-86329 |  |  | 761-01 | 2022-12-23 | JJTR02190 | KCE-ID-MR-GF-00009 | APPROVED | 2534.658 | 543.141 |  |  |  |  | 2534.658 | 543.141
111 | D-01g | L0223 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | 35 DB | ROCKWOOL | 1 HR | NO | 1 | 2148.6 | 2148.6 | 86321 | APPROVED | [12 empty] | 0
112 | D-01g | L0226 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | 35 DB | ROCKWOOL | 1 HR | NO | 1 | 2148.6 | 2148.6 | 86321 | APPROVED | [12 empty] | 0
113 | D-01a | L0300 | 150 | 800 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | NFR | NO | 1 | 1540.25 | 1540.25 | [14 empty] | 0
114 | D-01a | L0305 | 150 | 800 | 2200 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | NFR | NO | 1 | 1540.25 | 1540.25 | [14 empty] | 0
115 | D-01a | L0306 | 150 | 800 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | NFR | NO | 1 | 1540.25 | 1540.25 | [14 empty] | 0
116 | D-01a | L0307 | 150 | 800 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | NFR | NO | 1 | 1540.25 | 1540.25 | [14 empty] | 0
117 | D-01a | L0308 | 150 | 800 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | NFR | NO | 1 | 1540.25 | 1540.25 | [14 empty] | 0
118 | D-01d | L0331 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | 35 DB | ROCKWOOL | 1 HR | NO | 1 | 1870.875 | 1870.875 | [14 empty] | 0
119 | D-01d | L0332 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | 35 DB | ROCKWOOL | 1 HR | NO | 1 | 1870.875 | 1870.875 | [14 empty] | 0
120 | D-01d | L0334 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | 35 DB | ROCKWOOL | 1 HR | NO | 1 | 1870.875 | 1870.875 | [14 empty] | 0
121 | D-01d | L0335 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | 35 DB | ROCKWOOL | 1 HR | NO | 1 | 1870.875 | 1870.875 | [14 empty] | 0
122 | D-01d | L0336 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | 35 DB | ROCKWOOL | 1 HR | NO | 1 | 1870.875 | 1870.875 | [14 empty] | 0
123 | D-01d | L0337 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | 35 DB | ROCKWOOL | 1 HR | NO | 1 | 1870.875 | 1870.875 | [14 empty] | 0
124 | D-01d | L0338 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HRS | NO | 1 | 1599.7625 | 1599.7625 | [14 empty] | 0
125 | D-01d | L0339 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | 35 DB | ROCKWOOL | 1 HR | NO | 1 | 1870.875 | 1870.875 | [14 empty] | 0
126 | D-02L | L0343 | 150 | 1000 | 2100 | DOUBLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1 HR | NO | 1 | 1937.8125 | 1937.8125 | [14 empty] | 0
127 | D-02L | L0344 | 150 | 1000 | 2100 | DOUBLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1 HR | NO | 1 | 1937.8125 | 1937.8125 | [14 empty] | 0
128 | D-02L | L0345 | 150 | 1000 | 2100 | DOUBLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1 HR | NO | 1 | 1937.8125 | 1937.8125 | [14 empty] | 0
129 | D-02L | L0346 | 150 | 1000 | 2100 | DOUBLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1 HR | NO | 1 | 1937.8125 | 1937.8125 | [14 empty] | 0
130 | D-01a | L0348 | 150 | 800 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | NFR | NO | 1 | 1540.25 | 1540.25 | [14 empty] | 0
131 | D-01a | L0349 | 150 | 800 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | NFR | NO | 1 | 1540.25 | 1540.25 | [14 empty] | 0
132 | D-03a | L0431 | 150 | 1100 | 2100 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HRS | NO | 1 | 2024.7387 | 2024.7387 | 86335 | APPROVED | [12 empty] | 0
133 | D-02g | L0502 | 150 | 2000 | 2100 | DOUBLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1 HR | NO | 1 | 2949.525 | 2949.525 | 86331 | APPROVED | [12 empty] | 0
134 | D-03b | L0202 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HRS | NO | 1 | 2149.715 | 2149.715 | [14 empty] | 0
135 | D-01g | L29H53/L29H36 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | HONEYCOMB | 2 HRS | NO | 1 | 2149.715 | 2149.715 | IND-AX-SD-ML-86319 | [13 empty] | 0
136 | D-01c | L30H08 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | NFR | NO | 1 | 1540.25 | 1540.25 | [14 empty] | 0
137 | D-01d | L30H55 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1 HR | NO | 1 | 1599.7625 | 1599.7625 | [14 empty] | 0
138 | D-01D | L30H47 | 150 | 1000 | 2400 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | NFR | NO | 1 | 1778.3 | 1778.3 | [14 empty] | 0
139 | D-01A | L30H54 | 150 | 1000 | 2400 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | NFR | NO | 1 | 1778.3 | 1778.3 | [14 empty] | 0
140 | D-01A | L30H53 | 150 | 1000 | 2400 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | NFR | NO | 1 | 1778.3 | 1778.3 | [14 empty] | 0
141 | D-03d | L31H01 | 150 | 1100 | 2100 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | ROCKWOOL | 1.5 HRS | YES | 1 | 2156.9887 | 2156.9887 | 86336 | APPROVED | [12 empty] | 0
142 | D-01d | L31H04 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | ROCKWOOL | 1.5 HRS | YES | 1 | 1732.0125 | 1732.0125 | [14 empty] | 0
143 | D-01c | L10R23 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | ROCKWOOL | NFR | YES | 1 | 1922.5 | 1922.5 | [14 empty] | 0
144 | D-01g | L24R05 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HRS | NO | 1 | 1849.715 | 1849.715 | 86325 | APPROVED | [12 empty] | 0
145 | D-01c | L24R06 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.5MM | 43 DB | ROCKWOOL | 1 HR | NO | 1 | 1870.875 | 1870.875 | 86309 | APPROVED | [12 empty] | 0
146 | D-03b | L29R02 | 150 | 1100 | 2100 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HRS | NO | 1 | 2177.4875 | 2177.4875 | IND-AX-SD-ML-86300 | [13 empty] | 0
147 | D-03b | L29R01 | 150 | 1100 | 2100 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HRS | NO | 1 | 2024.7387 | 2024.7387 | [14 empty] | 0
148 | D-01g | L32R02 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.5MM | 43 DB | ROCKWOOL | NFR | YES | 1 | 2231.9175 | 2231.9175 | 86320 | APPROVED | [12 empty] | 0
149 | D-01d | L32R04 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | ROCKWOOL | NFR | YES | 1 | 1870.875 | 1870.875 | [14 empty] | 0
150 | D-01g | L32R05 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.5MM | 43 DB | ROCKWOOL | NFR | YES | 1 | 2231.9175 | 2231.9175 | [14 empty] | 0
151 | D-01e | LGF40 | 150 | 1000 | 2400 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | ROCKWOOL | NFR | YES | 1 | 2069.25 | 2069.25 | IND-AX-SD-ML-86296 |  |  | 761-03 | [10 empty] | 0
152 | D-08b | LGF-177 | 150 | 1200 | 2400 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | ROCKWOOL | NFR | YES | 1 | 2196.21 | 2196.21 | [14 empty] | 0
153 | D-01d | L30H* | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | ROCKWOOL | NFR | YES | 1 | 1732.0125 | 1732.0125 | [14 empty] | 0
154 | D-05e | L02101 | 150 | 1500 | 2400 | DOUBLE LEAF STEEL DOOR | 1.5MM | 1.2MM | 35 DB | ROCKWOOL | NFR | NO | 1 | 2962.75 | 2962.75 | 86343 | APPROVED | [12 empty] | 0
155 | D-01g | L0239 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | 32 DB | ROCKWOOL | NFR | YES | 1 | 2148.6 | 2148.6 | 86322 | APPROVED | [12 empty] | 0
156 | D-01d | LB1106 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.5MM | 43 DB | ROCKWOOL | 1.5 HRS | YES | 1 | 1940.3063 | 1940.3063 | [14 empty] | 0
157 | D-02h | LB1108 | 150 | 2000 | 2400 | DOUBLE LEAF STEEL DOOR | 1.5MM | 1.5MM | 43 DB | ROCKWOOL | 1.5 HRS | NO | 1 | 3914.95 | 3914.95 | 86332 | APPROVED | [12 empty] | 0
158 | D-02h | LB1109 | 150 | 2000 | 2400 | DOUBLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | ROCKWOOL | 1.5 HRS | YES | 1 | 3438.85 | 3438.85 | [14 empty] | 0
159 | D-01e | LB1152 | 150 | 1000 | 2400 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | NFR | NO | 1 | 1778.3 | 1778.3 | IND-AX-SD-ML-86318 | [13 empty] | 0
160 | D-02f | LB1214 | 150 | 1900 | 2400 | DOUBLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | ROCKWOOL | 1.5 HRS | YES | 1 | 3296.02 | 3296.02 | [14 empty] | 0
161 | D-01h | LGF05 | 150 | 1200 | 2400 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HRS | NO | 1 | 2063.96 | 2063.96 | 86326 | APPROVED | [12 empty] | 0
162 | D-03b | LGF48 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HRS | NO | 1 | 2149.715 | 2149.715 | 86339 | APPROVED | [12 empty] | 0
163 | D-03b | LGF49 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HRS | NO | 1 | 2149.715 | 2149.715 | 86339 | APPROVED | [12 empty] | 0
164 | D-03a | LGF52 | 150 | 1100 | 2100 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | ROCKWOOL | 1.5 HRS | YES | 1 | 2156.9887 | 2156.9887 | IND-AX-SD-ML-86337 |  |  | 761-03 |  | JJTR02209 | IND-AX-MR-ML-00012 | APPROVED |  |  |  | 1509.8921 |  |  | 1509.8921 | 0
165 | D-03d | LGF54 | 150 | 1200 | 2400 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HRS | NO | 1 | 2363.96 | 2363.96 | 86341 | APPROVED | [12 empty] | 0
166 | D-03d | LGF55 | 150 | 1200 | 2400 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HRS | NO | 1 | 2363.96 | 2363.96 | 86341 | APPROVED | [12 empty] | 0
167 | D-12c | LGF56 | 150 | 1200 | 2400 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | ROCKWOOL | NFR | YES | 1 | 2446.21 | 2446.21 | IND-AX-SD-ML-86348 |  |  | 761-03 |  | JJTR02209 | IND-AX-MR-ML-00012 | APPROVED |  |  |  | 1712.347 |  |  | 1712.347 | 0
168 | D-12a | LGF59 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1 HR | NO | 1 | 1599.7625 | 1599.7625 | IND-AX-SD-ML-86347 |  |  | 761-02 | 2022-12-23 | JJTR02190 | KCE-ID-MR-GF-00009 | APPROVED | 1119.8338 | 239.9644 |  |  |  |  | 1119.8338 | 239.9644
169 | D-03a | L0102 | 150 | 1100 | 2100 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HRS | NO | 1 | 2024.7387 | 2024.7387 | 86335 | APPROVED | [12 empty] | 0
170 | D-01d | L0230 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HRS | NO | 1 | 1599.7625 | 1599.7625 | IND-AX-SD-ML-86311 |  |  | 761-04 | 2023-01-26 | JJTR02220 | [8 empty] | 0
171 | D-03d | L0312 | 150 | 1200 | 2400 | SINGLE LEAF STEEL DOOR WITH VISION PANEL | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HRS | NO | 1 | 2363.96 | 2363.96 | 86341 | APPROVED | [12 empty] | 0
172 | D-01d | L0320 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HRS | NO | 1 | 1599.7625 | 1599.7625 | IND-AX-SD-ML-86311 |  |  | 761-04 | 2023-01-26 | JJTR02220 | [8 empty] | 0
173 | D-01d | L0518 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HRS | NO | 1 | 1599.7625 | 1599.7625 | IND-AX-SD-ML-86311 |  |  | 761-04 | [10 empty] | 0
174 | D-01d | L08H10 | 150 | 1000 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HRS | NO | 1 | 1599.7625 | 1599.7625 | IND-AX-SD-ML-86311 |  |  | 761-04 | 2023-01-26 | JJTR02220 | [8 empty] | 0
175 | D-01g | L14H05 | 150 | 1200 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HRS | NO | 1 | 1849.715 | 1849.715 | [14 empty] | 0
176 | D-02d | L24R01 | 150 | 1700 | 2100 | DOUBLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1.5 HRS | NO | 1 | 2574.5963 | 2574.5963 | 86327 | APPROVED | [12 empty] | 0
177 | D-01c | L31R11 | 150 | 900 | 2100 | SINGLE LEAF STEEL DOOR | 1.5MM | 1.2MM | N/A | HONEYCOMB | 1 HR | NO | 1 | 1540.25 | 1540.25 | 86308 | APPROVED | [12 empty] | 0
SITE INSTRUCTION NO : E11/K145/AK/dm/538 | [29 empty] | 0
205 | [5 empty] | TEMPORARY GLASS FOR FORSTER WINDOWS | [6 empty] | 1 | 2500 | 2500 |  |  | E11/K145/AK/dm/538 | 764 |  | DELIVERED | [8 empty] | 0
| TOTAL AMOUNT :- | [13 empty] | 419026.9313 | [8 empty] | 18614.106 | 3988.737 |  | 42501.6947 |  |  | 61115.8007 | 3988.737 | 0
Note on AB219: Himal Kosala: Check the Door code with MIR reference
Note on AB220: Himal Kosala: Check the Door code with MIR reference
Note on AB230: Himal Kosala: Check the Door code with MIR reference