## Contract
FIRE STOP WORKS ON MEP PENETRATIONS AND JOINTS | [11 empty] | FIRE STOP |  | Certified Amount
[6 empty] | Quantity |  |  | Progress Amount (AED) |  |  |  |  | Quantity |  |  | Progress Amount (AED)
S.Nr | Description | Qty | Unit | Rate | Amount | Previous | Current | Cumulative | Previous | Current | Cumulative | WIR Ref./ Remarks |  | Previous | Current | Cumulative | Previous | Current | Cumulative
G | Supply and installation of firestop sealant and mineral wool to Head of wall / Wall to wall joints (Single Sided)
G1 | Upto 20mm joint width | 500 | m | 14 | 7000 | 2664.87 | 466.5 | 3131.37 | 37308.18 | 6531 | 43839.18 |  |  | 2664.87 | 466.5 | 3131.37 | 37308.18 | 6531 | 43839.18
G2 | Upto 30mm joint width | 500 | m | 20 | 10000 | 39 |  | 39 | 780 | 0 | 780 |  |  | 39 | 0 | 39 | 780 | 0 | 780
G3 | Upto 35mm joint width | 150 | m | 27 | 4050 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
H | Supply and installation of Sealant and mineral wool non-fire rated Head of wall / Wall to wall joints (Single Sided) | [13 empty] | 0 | 0 |  | 0 | 0
H1 | Upto 20mm joint width | 250 | m | 10 | 2500 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
[15 empty] | 0 | 0 |  | 0 | 0
[15 empty] | 0 | 0 |  | 0 | 0
A | Supply and apply firestop sealant and mineral wool backing to non-insulated metallic/ non-combustible pipes (Single Sided) | [13 empty] | 0 | 0 |  | 0 | 0
A1 | Upto and including 2"ɸ | 100 | No. | 14 | 1400 | 37 |  | 37 | 518 | 0 | 518 |  |  | 37 | 0 | 37 | 518 | 0 | 518
A2 | Upto and including 3"ɸ | 100 | No. | 16 | 1600 | 34 |  | 34 | 544 | 0 | 544 |  | 0 | 34 | 0 | 34 | 544 | 0 | 544
A3 | Upto and including 4"ɸ | 100 | No. | 21 | 2100 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
A4 | Upto and including 6"ɸ | 100 | No. | 27 | 2700 | 2 |  | 2 | 54 | 0 | 54 |  | 0 | 2 | 0 | 2 | 54 | 0 | 54
A5 | Upto and including 8"ɸ | 50 | No. | 46 | 2300 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
A6 | Upto and including 24"ɸ | 10 | No. | 141 | 1410 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
B | Supply and apply firestop sealant and mineral wool backing to insulated metallic/ non-combustible pipes (Single Sided) | [13 empty] | 0 | 0 |  | 0 | 0
B1 | Upto and including 2"ɸ | 200 | No. | 20 | 4000 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
B2 | Upto and including 3"ɸ | 200 | No. | 23 | 4600 | 65 |  | 65 | 1495 | 0 | 1495 |  | 0 | 65 | 0 | 65 | 1495 | 0 | 1495
B3 | Upto and including 4"ɸ | 200 | No. | 29 | 5800 | 4 |  | 4 | 116 | 0 | 116 |  | 0 | 4 | 0 | 4 | 116 | 0 | 116
B4 | Upto and including 6"ɸ | 200 | No. | 35 | 7000 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
B5 | Upto and including 8"ɸ | 100 | No. | 47 | 4700 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
B6 | Upto and including 16"ɸ | 50 | No. | 170 | 8500 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
C | Supply and apply firestop sealant and mineral wool backing to PVC conduits & cable pipes | [13 empty] | 0 | 0 |  | 0 | 0
C1 | Upto and including 2"ɸ |  |  | 18 |  | 2 |  | 2 | 36 | 0 | 36 |  | 0 | 2 | 0 | 2 | 36 | 0 | 36
C | Supply and apply firestop sealant and mineral wool backing to PVC/ combustible pipes (Single Sided) | [13 empty] | 0 | 0 |  | 0 | 0
C1 | Upto and including 2"ɸ | 400 | No. | 28 | 11200 | 5 |  | 5 | 140 | 0 | 140 |  | 0 | 5 | 0 | 5 | 140 | 0 | 140
C2 | Upto and including 3"ɸ | 400 | No. | 30 | 12000 | 162 |  | 162 | 4860 | 0 | 4860 |  | 0 | 162 | 0 | 162 | 4860 | 0 | 4860
C3 | Upto and including 4"ɸ | 400 | No. | 65 | 26000 | 19 |  | 19 | 1235 | 0 | 1235 |  | 0 | 19 | 0 | 19 | 1235 | 0 | 1235
C4 | Upto and including 6"ɸ | 250 | No. | 125 | 31250 | 21 |  | 21 | 2625 | 0 | 2625 |  | 0 | 21 | 0 | 21 | 2625 | 0 | 2625
C5 | Upto and including 8"ɸ | 250 | No. | 250 | 62500 | 3 |  | 3 | 750 | 0 | 750 |  | 0 | 3 | 0 | 3 | 750 | 0 | 750
D | Supply and apply firestop board material to cable tray openings, shaft openings and openings (Single Board) | [13 empty] | 0 | 0 |  | 0 | 0
D1 | For an area upto 0.05 m2 | 100 | No. | 50 | 5000 | 47 | 5 | 52 | 2350 | 250 | 2600 |  | 0 | 47 | 5 | 52 | 2350 | 250 | 2600
D2 | For an area upto 0.10 m2 | 100 | No. | 95 | 9500 | 84 | 18 | 102 | 7980 | 1710 | 9690 |  | 0 | 84 | 18 | 102 | 7980 | 1710 | 9690
D3 | For an area upto 0.15 m2 | 100 | No. | 150 | 15000 | 41 | 17 | 58 | 6150 | 2550 | 8700 |  | 0 | 41 | 17 | 58 | 6150 | 2550 | 8700
D4 | For an area upto 0.25 m2 | 100 | No. | 180 | 18000 | 47 | 8 | 55 | 8460 | 1440 | 9900 |  | 0 | 46 | 8 | 54 | 8280 | 1440 | 9720
D5 | For an area upto 0.35 m2 | 100 | No. | 245 | 24500 | 7 | 3 | 10 | 1715 | 735 | 2450 |  | 0 | 7 | 3 | 10 | 1715 | 735 | 2450
D6 | For an area upto 0.50 m2 | 50 | No. | 310 | 15500 | 33 | 6 | 39 | 10230 | 1860 | 12090 |  | 0 | 33 | 6 | 39 | 10230 | 1860 | 12090
D7 | For an area upto 0.65 m2 | 50 | No. | 340 | 17000 | 4 | 6 | 10 | 1360 | 2040 | 3400 |  | 0 | 4 | 6 | 10 | 1360 | 2040 | 3400
D8 | For an area upto 0.80 m2 | 50 | No. | 400 | 20000 | 4 | 3 | 7 | 1600 | 1200 | 2800 |  | 0 | 4 | 3 | 7 | 1600 | 1200 | 2800
D9 | For an area upto 1.00 m2 | 25 | m2 | 450 | 11250 | 28.0885 | 48.246 | 76.3345 | 12639.836 | 21710.6828 | 34350.5188 |  | 0 | 28.0885 | 48.246 | 76.3345 | 12639.836 | 21710.6828 | 34350.5188
E | Supply and apply firestopping materials to Metallic Duct with Fire Damper and L-angle (Single Sided) | [13 empty] | 0 | 0 |  | 0 | 0
E1 | For an area upto 0.05 m2 | 100 | No. | 32 | 3200 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
E2 | For an area upto 0.10 m2 | 100 | No. | 46 | 4600 | 16 |  | 16 | 736 | 0 | 736 |  | 0 | 16 | 0 | 16 | 736 | 0 | 736
E3 | For an area upto 0.20 m2 | 100 | No. | 51 | 5100 | 4 |  | 4 | 204 | 0 | 204 |  | 0 | 4 | 0 | 4 | 204 | 0 | 204
E4 | For an area upto 0.30 m2 | 100 | No. | 64 | 6400 | 2 |  | 2 | 128 | 0 | 128 |  | 0 | 2 | 0 | 2 | 128 | 0 | 128
E5 | For an area upto 0.40 m2 | 100 | No. | 74 | 7400 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
E6 | For an area upto 0.50 m2 | 100 | No. | 82 | 8200 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
E7 | For an area upto 0.60 m2 | 100 | No. | 88 | 8800 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
E8 | For an area upto 0.70 m2 | 50 | No. | 98 | 4900 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
E9 | For an area upto 0.80 m2 | 50 | No. | 103 | 5150 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
E10 | For an area upto 0.90 m2 | 25 | No. | 110 | 2750 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
E11 | For an area upto 1.00 m2 | 25 | m2 | 116 | 2900 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | 0 | 0 |  | 0 | 0
F | Supply and installation of Nullfire FR 230 firestop mortar material (100mm thickness) to Electrical Openings (Single Sided) | [13 empty] | 0 | 0 |  | 0 | 0
F1 | For an area upto 1.00 m2 | 50 | m2 | 680 | 34000 | 25.355 | 10.1128 | 35.4678 | 17241.4 | 6876.704 | 24118.104 |  | 0 | 24.875 | 10.1128 | 34.9878 | 16915 | 6876.704 | 23791.704
| TOTAL AMOUNT OF CONSTRUCTION JOINTS |  |  |  | 441760 | 3400.3135 | 590.8588 | 3991.1723 | 121255.416 | 46903.3868 | 168158.8028 |  |  | 3398.8335 | 590.8588 | 3989.6923 | 120749.016 | 46903.3868 | 167652.4028
[9 empty] | 121255.416 | 46903.3868 | 168158.8028
[9 empty] | 0 | 0 | 0

## Joints
Project: |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  | Khansaheb Civil Engineering - Construction Division
Period of Completed Works: |  |  | December 2022
Summary of Completed Firestopping Works (Construction Joints)
No. | Sos Number | Level | WIR No. | Location | Type | Joint Size (in meter) |  |  | Sides | Rate (AED) | Nos | Total (AED) |  |  | Hotel / Residence | QTY | Remarks
Hotel
December 2022 - Hotel | [14 empty] | Hotel
1 | Sheet 62273 | Level 18 | WIR - 00182 | AHU for F-B- NX Rm | Head of wall joint | 0.02 | 38.4 | @ | 1 | 14 | 1 | 537.6 | 20 | Sheet 62273 | Hotel | 38.4
2 | Sheet 62273 | Level 18 | WIR - 00182 | AHU for F-B- NX Rm | Vertical joint | 0.02 | 4 | @ | 1 | 14 | 1 | 56 | 20 |  | Hotel | 4
Hotel
December 2022 - Hotel | [14 empty] | Hotel
1 | Sheet 62283 | Ground Level | WIR - 00192 | Food Storage Rm | Horizontal joint | 0.02 | 29.8 | @ | 1 | 14 | 1 | 417.2 | 20 | Sheet 62283 | Hotel | 29.8
2 | Sheet 62283 | Ground Level | WIR - 00192 | Food Storage Rm | Vertical joint | 0.02 | 2.2 | @ | 1 | 14 | 2 | 61.6 | 20 |  | Hotel | 4.4
3 | Sheet 62283 | Ground Level | WIR - 00192 | Window High | Horizontal joint | 0.02 | 18.9 | @ | 1 | 14 | 1 | 264.6 | 20 |  | Hotel | 18.9
4 | Sheet 62283 | Ground Level | WIR - 00192 | Kitchen | Horizontal joint | 0.02 | 27.5 | @ | 1 | 14 | 1 | 385 | 20 |  | Hotel | 27.5
5 | Sheet 62283 | Ground Level | WIR - 00192 | BOH Corridor | Horizontal joint | 0.02 | 24.2 | @ | 1 | 14 | 1 | 338.8 | 20 |  | Hotel | 24.2
6 | Sheet 62283 | Ground Level | WIR - 00192 | BOH Corridor | Vertical joint | 0.02 | 4 | @ | 1 | 14 | 4 | 224 | 20 |  | Hotel | 16
Residence
December 2022 - Residence | [14 empty] | Residence
1 | Sheet 62277 | Level 29 | WIR - 00185 | Shaft | Horizontal joint | 0.02 | 5.4 | @ | 2 | 14 | 1 | 151.2 | 20 | Sheet 62277 | Residence | 10.8
2 | Sheet 62277 | Level 29 | WIR - 00185 | Shaft | Vertical joint | 0.02 | 4.6 | @ | 2 | 14 | 2 | 257.6 | 20 |  | Residence | 18.4
3 | Sheet 62277 | Level 29 | WIR - 00185 | Gas Shaft | Horizontal joint | 0.02 | 1.4 | @ | 2 | 14 | 1 | 39.2 | 20 |  | Residence | 2.8
4 | Sheet 62277 | Level 29 | WIR - 00185 | Gas Shaft | Vertical joint | 0.02 | 4.6 | @ | 2 | 14 | 2 | 257.6 | 20 |  | Residence | 18.4
5 | Sheet 62277 | Level 29 | WIR - 00185 | Wall | Horizontal joint | 0.02 | 29 | @ | 2 | 14 | 1 | 812 | 20 |  | Residence | 58
6 | Sheet 62277 | Level 29 | WIR - 00185 | Wall | Vertical joint | 0.02 | 4.6 | @ | 2 | 14 | 2 | 257.6 | 20 |  | Residence | 18.4
7 | Sheet 62277 | Level 29 | WIR - 00185 | Wall | Vertical joint | 0.02 | 2.3 | @ | 2 | 14 | 1 | 64.4 | 20 |  | Residence | 4.6
8 | Sheet 62277 | Level 29 | WIR - 00185 | Shaft | Horizontal joint | 0.02 | 3.4 | @ | 2 | 14 | 1 | 95.2 | 20 |  | Residence | 6.8
9 | Sheet 62277 | Level 29 | WIR - 00185 | Shaft | Horizontal joint | 0.02 | 3.4 | @ | 2 | 14 | 1 | 95.2 | 20 |  | Residence | 6.8
10 | Sheet 62277 | Level 29 | WIR - 00185 | Shaft | Horizontal joint | 0.02 | 3 | @ | 2 | 14 | 1 | 84 | 20 |  | Residence | 6
11 | Sheet 62277 | Level 29 | WIR - 00185 | Shaft | Vertical joint | 0.02 | 2 | @ | 2 | 14 | 1 | 56 | 20 |  | Residence | 4
12 | Sheet 62277 | Level 29 | WIR - 00185 | Housekeeping | Horizontal joint | 0.02 | 12.8 | @ | 2 | 14 | 1 | 358.4 | 20 |  | Residence | 25.6
13 | Sheet 62277 | Level 29 | WIR - 00185 | Housekeeping | Vertical joint | 0.02 | 4.6 | @ | 2 | 14 | 2 | 257.6 | 20 |  | Residence | 18.4
14 | Sheet 62277 | Level 29 | WIR - 00185 | Lift lobby | Horizontal joint | 0.02 | 15 | @ | 2 | 14 | 1 | 420 | 20 |  | Residence | 30
15 | Sheet 62277 | Level 29 | WIR - 00185 | Lift lobby | Vertical joint | 0.02 | 4 | @ | 2 | 14 | 4 | 448 | 20 |  | Residence | 32
16 | Sheet 62277 | Level 29 | WIR - 00185 | Corridor Entry Dr. | Horizontal joint | 0.02 | 2 | @ | 2 | 14 | 1 | 56 | 20 |  | Residence | 4
17 | Sheet 62277 | Level 29 | WIR - 00185 | Corridor Entry Dr. | Vertical joint | 0.02 | 2.3 | @ | 2 | 14 | 2 | 128.8 | 20 |  | Residence | 9.2
18 | Sheet 62277 | Level 29 | WIR - 00185 | Shaft | Horizontal joint | 0.02 | 2.65 | @ | 2 | 14 | 1 | 74.2 | 20 |  | Residence | 5.3
19 | Sheet 62277 | Level 29 | WIR - 00185 | FF Lobby | Horizontal joint | 0.02 | 8.1 | @ | 2 | 14 | 1 | 226.8 | 20 |  | Residence | 16.2
20 | Sheet 62277 | Level 29 | WIR - 00185 | FF Lobby | Vertical joint | 0.02 | 1.9 | @ | 2 | 14 | 2 | 106.4 | 20 |  | Residence | 7.6
[10 empty] | Grand Total |  | 6531 |  |  |  | 466.5
[10 empty] | Joints |  | 6531
[10 empty] | FR230 opening (Civil) |  | 6876.704
[10 empty] | MEP Opening (Civil) |  | 33495.6828
[10 empty] | Civil Total |  | 46903.3868
WIR List as per SOS
|  |  |  | Level 18 | WIR - 00182
|  |  |  | Ground Level | WIR - 00192
|  |  |  | Level 29 | WIR - 00185

## FR230 opening (Civil)
Project: |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  | Khansaheb Civil Engineering - Construction Division
Period of Completed Works: |  |  | December 2022 | [14 empty] | all mortar openings priced by sqm diff
Summary of Completed Firestopping Works
No. | Sos Number | Level | WIR No. | Location | Penetrant Type | Penetrant Size (in meter) |  | SquareMeters | Opening Size (in meter) |  | SquareMeters | Diffirence | Sides | Rate (AED) | Nos | Total (AED) |  |  | Hotel / Residence | QTY
Residence
December 2022 - Residence | [18 empty] | Residence
1 | Sheet 62286 | Level 30 | WIR - 00191 | Electrical Room | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 3 | 0 | FR230 | Sheet 62286 | Residence | 3
2 | Sheet 62286 | Level 30 | WIR - 00191 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 3 | 0 | FR230 |  | Residence | 3
3 | Sheet 62286 | Level 30 | WIR - 00191 | Electrical Room | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Residence | 1
4 | Sheet 62286 | Level 30 | WIR - 00191 | Electrical Room | opening Mortar |  |  |  | 0.54 | 1.37 | 0.7398 | 0.6548 | 1 | 680 | 1 | 445.264 | FR230 |  | Residence | 0.6548
5 | Sheet 62286 | Level 30 | WIR - 00191 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR230 |  | Residence | 2
6 | Sheet 62286 | Level 30 | WIR - 00191 | Electrical Room | opening Mortar |  |  |  | 0.25 | 0.3 | 0.075 | 0.055 | 1 | 680 | 1 | 37.4 | FR230 |  | Residence | 0.055
7 | Sheet 62286 | Level 29 | WIR - 00191 | Electrical Room | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 3 | 0 | FR230 |  | Residence | 3
8 | Sheet 62286 | Level 29 | WIR - 00191 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 3 | 0 | FR230 |  | Residence | 3
9 | Sheet 62286 | Level 29 | WIR - 00191 | Electrical Room | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Residence | 1
10 | Sheet 62286 | Level 29 | WIR - 00191 | Electrical Room | opening Mortar |  |  |  | 0.5 | 1.35 | 0.675 | 0.59 | 1 | 680 | 1 | 401.2 | FR230 |  | Residence | 0.59
11 | Sheet 62286 | Level 29 | WIR - 00191 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR230 |  | Residence | 2
12 | Sheet 62286 | Level 29 | WIR - 00191 | Electrical Room | opening Mortar |  |  |  | 0.25 | 0.3 | 0.075 | 0.055 | 1 | 680 | 1 | 37.4 | FR230 |  | Residence | 0.055
13 | Sheet 62286 | Level 28 | WIR - 00191 | Electrical Room | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 3 | 0 | FR230 |  | Residence | 3
14 | Sheet 62286 | Level 28 | WIR - 00191 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 3 | 0 | FR230 |  | Residence | 3
15 | Sheet 62286 | Level 28 | WIR - 00191 | Electrical Room | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Residence | 1
16 | Sheet 62286 | Level 28 | WIR - 00191 | Electrical Room | opening Mortar |  |  |  | 0.48 | 1.35 | 0.648 | 0.563 | 1 | 680 | 1 | 382.84 | FR230 |  | Residence | 0.563
17 | Sheet 62286 | Level 28 | WIR - 00191 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR230 |  | Residence | 2
18 | Sheet 62286 | Level 28 | WIR - 00191 | Electrical Room | opening Mortar |  |  |  | 0.25 | 0.3 | 0.075 | 0.055 | 1 | 680 | 1 | 37.4 | FR230 |  | Residence | 0.055
Residence
December 2022 - Residence | [18 empty] | Residence
1 | Sheet 62285 | Level 06 | WIR - 00190 | Electrical Room | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 3 | 0 | FR230 | Sheet 62285 | Residence | 3
2 | Sheet 62285 | Level 06 | WIR - 00190 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR230 |  | Residence | 2
3 | Sheet 62285 | Level 06 | WIR - 00190 | Electrical Room | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Residence | 1
4 | Sheet 62285 | Level 06 | WIR - 00190 | Electrical Room | opening Mortar |  |  |  | 0.5 | 1.3 | 0.65 | 0.575 | 1 | 680 | 1 | 391 | FR230 |  | Residence | 0.575
5 | Sheet 62285 | Level 06 | WIR - 00190 | Electrical Room | bus bar | 0.05 | 0.1 | 0.005 |  |  |  |  | 1 |  | 4 | 0 | FR230 |  | Residence | 4
6 | Sheet 62285 | Level 06 | WIR - 00190 | Electrical Room | opening Mortar |  |  |  | 0.75 | 1 | 0.75 | 0.73 | 1 | 680 | 1 | 496.4 | FR230 |  | Residence | 0.73
7 | Sheet 62285 | Level 06 | WIR - 00190 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR230 |  | Residence | 2
8 | Sheet 62285 | Level 06 | WIR - 00190 | Electrical Room | opening Mortar |  |  |  | 0.25 | 0.3 | 0.075 | 0.055 | 1 | 680 | 1 | 37.4 | FR230 |  | Residence | 0.055
9 | Sheet 62285 | Level 07 | WIR - 00190 | Electrical Room | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 3 | 0 | FR230 |  | Residence | 3
10 | Sheet 62285 | Level 07 | WIR - 00190 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR230 |  | Residence | 2
11 | Sheet 62285 | Level 07 | WIR - 00190 | Electrical Room | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Residence | 1
12 | Sheet 62285 | Level 07 | WIR - 00190 | Electrical Room | opening Mortar |  |  |  | 0.5 | 1.3 | 0.65 | 0.575 | 1 | 680 | 1 | 391 | FR230 |  | Residence | 0.575
13 | Sheet 62285 | Level 07 | WIR - 00190 | Electrical Room | bus bar | 0.05 | 0.1 | 0.005 |  |  |  |  | 1 |  | 4 | 0 | FR230 |  | Residence | 4
14 | Sheet 62285 | Level 07 | WIR - 00190 | Electrical Room | opening Mortar |  |  |  | 0.75 | 1 | 0.75 | 0.73 | 1 | 680 | 1 | 496.4 | FR230 |  | Residence | 0.73
15 | Sheet 62285 | Level 07 | WIR - 00190 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR230 |  | Residence | 2
16 | Sheet 62285 | Level 07 | WIR - 00190 | Electrical Room | opening Mortar |  |  |  | 0.25 | 0.3 | 0.075 | 0.055 | 1 | 680 | 1 | 37.4 | FR230 |  | Residence | 0.055
17 | Sheet 62285 | Level 08 | WIR - 00190 | Electrical Room | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 3 | 0 | FR230 |  | Residence | 3
18 | Sheet 62285 | Level 08 | WIR - 00190 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR230 |  | Residence | 2
19 | Sheet 62285 | Level 08 | WIR - 00190 | Electrical Room | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Residence | 1
20 | Sheet 62285 | Level 08 | WIR - 00190 | Electrical Room | opening Mortar |  |  |  | 0.5 | 1.3 | 0.65 | 0.575 | 1 | 680 | 1 | 391 | FR230 |  | Residence | 0.575
21 | Sheet 62285 | Level 08 | WIR - 00190 | Electrical Room | bus bar | 0.05 | 0.1 | 0.005 |  |  |  |  | 1 |  | 4 | 0 | FR230 |  | Residence | 4
22 | Sheet 62285 | Level 08 | WIR - 00190 | Electrical Room | opening Mortar |  |  |  | 0.75 | 1 | 0.75 | 0.73 | 1 | 680 | 1 | 496.4 | FR230 |  | Residence | 0.73
23 | Sheet 62285 | Level 08 | WIR - 00190 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR230 |  | Residence | 2
24 | Sheet 62285 | Level 08 | WIR - 00190 | Electrical Room | opening Mortar |  |  |  | 0.25 | 0.3 | 0.075 | 0.055 | 1 | 680 | 1 | 37.4 | FR230 |  | Residence | 0.055
Residence
December 2022 - Residence | [18 empty] | Residence
1 | Sheet 62284 | Level 02 | WIR - 00189 | Electrical Room | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 3 | 0 | FR230 | Sheet 62284 | Residence | 3
2 | Sheet 62284 | Level 02 | WIR - 00189 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR230 |  | Residence | 2
3 | Sheet 62284 | Level 02 | WIR - 00189 | Electrical Room | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Residence | 1
4 | Sheet 62284 | Level 02 | WIR - 00189 | Electrical Room | opening Mortar |  |  |  | 0.5 | 1.3 | 0.65 | 0.575 | 1 | 680 | 1 | 391 | FR230 |  | Residence | 0.575
5 | Sheet 62284 | Level 02 | WIR - 00189 | Electrical Room | bus bar | 0.05 | 0.1 | 0.005 |  |  |  |  | 1 |  | 4 | 0 | FR230 |  | Residence | 4
6 | Sheet 62284 | Level 02 | WIR - 00189 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Residence | 1
7 | Sheet 62284 | Level 02 | WIR - 00189 | Electrical Room | opening Mortar |  |  |  | 0.75 | 1 | 0.75 | 0.72 | 1 | 680 | 1 | 489.6 | FR230 |  | Residence | 0.72
8 | Sheet 62284 | Level 02 | WIR - 00189 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR230 |  | Residence | 2
9 | Sheet 62284 | Level 02 | WIR - 00189 | Electrical Room | opening Mortar |  |  |  | 0.25 | 0.3 | 0.075 | 0.055 | 1 | 680 | 1 | 37.4 | FR230 |  | Residence | 0.055
10 | Sheet 62284 | Level 04 | WIR - 00189 | Electrical Room | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 3 | 0 | FR230 |  | Residence | 3
11 | Sheet 62284 | Level 04 | WIR - 00189 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR230 |  | Residence | 2
12 | Sheet 62284 | Level 04 | WIR - 00189 | Electrical Room | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Residence | 1
13 | Sheet 62284 | Level 04 | WIR - 00189 | Electrical Room | opening Mortar |  |  |  | 0.5 | 1.3 | 0.65 | 0.575 | 1 | 680 | 1 | 391 | FR230 |  | Residence | 0.575
14 | Sheet 62284 | Level 04 | WIR - 00189 | Electrical Room | bus bar | 0.05 | 0.1 | 0.005 |  |  |  |  | 1 |  | 4 | 0 | FR230 |  | Residence | 4
15 | Sheet 62284 | Level 04 | WIR - 00189 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Residence | 1
16 | Sheet 62284 | Level 04 | WIR - 00189 | Electrical Room | opening Mortar |  |  |  | 0.75 | 1 | 0.75 | 0.72 | 1 | 680 | 1 | 489.6 | FR230 |  | Residence | 0.72
17 | Sheet 62284 | Level 04 | WIR - 00189 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR230 |  | Residence | 2
18 | Sheet 62284 | Level 04 | WIR - 00189 | Electrical Room | opening Mortar |  |  |  | 0.25 | 0.3 | 0.075 | 0.055 | 1 | 680 | 1 | 37.4 | FR230 |  | Residence | 0.055
19 | Sheet 62284 | Level 05 | WIR - 00189 | Electrical Room | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 3 | 0 | FR230 |  | Residence | 3
20 | Sheet 62284 | Level 05 | WIR - 00189 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR230 |  | Residence | 2
21 | Sheet 62284 | Level 05 | WIR - 00189 | Electrical Room | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Residence | 1
22 | Sheet 62284 | Level 05 | WIR - 00189 | Electrical Room | opening Mortar |  |  |  | 0.5 | 1.3 | 0.65 | 0.575 | 1 | 680 | 1 | 391 | FR230 |  | Residence | 0.575
23 | Sheet 62284 | Level 05 | WIR - 00189 | Electrical Room | bus bar | 0.05 | 0.1 | 0.005 |  |  |  |  | 1 |  | 4 | 0 | FR230 |  | Residence | 4
24 | Sheet 62284 | Level 05 | WIR - 00189 | Electrical Room | opening Mortar |  |  |  | 0.75 | 1 | 0.75 | 0.73 | 1 | 680 | 1 | 496.4 | FR230 |  | Residence | 0.73
25 | Sheet 62284 | Level 05 | WIR - 00189 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR230 |  | Residence | 2
26 | Sheet 62284 | Level 05 | WIR - 00189 | Electrical Room | opening Mortar |  |  |  | 0.25 | 0.3 | 0.075 | 0.055 | 1 | 680 | 1 | 37.4 | FR230 |  | Residence | 0.055
[14 empty] | Grand Total |  | 6876.704 |  |  |  | 111.1128
WIR List as per SOS
|  |  |  | Level 30 | WIR - 00191
|  |  |  | Level 29 | WIR - 00191
|  |  |  | Level 28 | WIR - 00191
|  |  |  | Level 06 | WIR - 00190
|  |  |  | Level 07 | WIR - 00190
|  |  |  | Level 08 | WIR - 00190
|  |  |  | Level 02 | WIR - 00189
|  |  |  | Level 04 | WIR - 00189
|  |  |  | Level 05 | WIR - 00189

## MEP opening (Civil)
Project: |  |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  |  | Khansaheb Civil Engineering - Construction Division
Period of Completed Works: |  |  |  | December 2022 | [14 empty] | all mortar openings priced by sqm diff
Summary of Completed Firestopping Works
No. | Sos Number | Serial No | Level | WIR No. | Location | Penetrant Type | Penetrant Size (in meter) |  | SquareMeters | Opening Size (in meter) |  | SquareMeters | Diffirence | Sides | Rate (AED) | Nos | Total (AED) |  |  | Hotel / Residence | QTY
Residence
December 2022 - Residence | [19 empty] | Residence
1 | Sheet 62274 | 1 | Level 29 | WIR - 01839 | Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 |  | 1 |  | 2 | 0 | FS702 | Sheet 62274 | Residence | 2
2 | Sheet 62274 | 2 | Level 29 | WIR - 01839 | Shaft | duct | 0.2 | 0.6 | 0.12 | 0.25 | 0.65 | 0.1625 |  | 1 |  | 1 | 0 | FS702 |  | Residence | 1
3 | Sheet 62274 | 3 | Level 29 | WIR - 01839 | Shaft | PVC pipe | 4" |  |  | 6" |  |  |  | 2 |  | 4 | 0 | FS702/FP302 |  | Residence | 8
4 | Sheet 62274 | 4 | Level 29 | WIR - 01839 | Shaft | CHW pipe | 2" |  |  | 4" |  |  |  | 2 |  | 2 | 0 | FS709 |  | Residence | 4
5 | Sheet 62274 | 5 | Level 29 | WIR - 01839 | Shaft | gas pipe | 1" |  |  | 3" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Residence | 2
6 | Sheet 62274 | 6 | Level 29 | WIR - 01839 | Wall | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 2 | 0 | FS709 |  | Residence | 4
7 | Sheet 62274 | 7 | Level 29 | WIR - 01839 | Wall | PVC pipe | 4" |  |  | 6" |  |  |  | 2 |  | 2 | 0 | FS702/FP302 |  | Residence | 4
8 | Sheet 62274 | 8 | Level 29 | WIR - 01839 | Shaft | PVC pipe | 4" |  |  | 6" |  |  |  | 2 |  | 3 | 0 | FS702/FP302 |  | Residence | 6
9 | Sheet 62274 | 9 | Level 29 | WIR - 01839 | Shaft | PVC pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Residence | 2
10 | Sheet 62274 | 10 | Level 29 | WIR - 01839 | Wall | fire fighting pipe | 3" |  |  | 5" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Residence | 2
11 | Sheet 62274 | 11 | Level 29 | WIR - 01839 | Wall | fire fighting pipe | 1" |  |  | 3" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Residence | 2
12 | Sheet 62274 | 12 | Level 29 | WIR - 01839 | Wall | CHW pipe | 4" |  |  | 6" |  |  |  | 2 |  | 2 | 0 | FS709 |  | Residence | 4
13 | Sheet 62274 | 13 | Level 29 | WIR - 01839 | Wall | cable tray |  |  |  | 0.15 | 0.2 | 0.03 |  | 2 |  | 1 | 0 | FS702/FB750 |  | Residence | 2
14 | Sheet 62274 | 14 | Level 29 | WIR - 01839 | Wall | cable trunking |  |  |  | 0.08 | 0.08 | 0.0064 |  | 2 |  | 1 | 0 | FS702/FB750 |  | Residence | 2
15 | Sheet 62274 | 15 | Level 29 | WIR - 01839 | Wall | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 3 | 0 | FS709 |  | Residence | 6
16 | Sheet 62274 | 16 | Level 29 | WIR - 01839 | Wall | CHW pipe | 3" |  |  | 5" |  |  |  | 2 |  | 2 | 0 | FS709 |  | Residence | 4
17 | Sheet 62274 | 17 | Level 29 | WIR - 01839 | Wall | PPR pipe | 2" |  |  | 4" |  |  |  | 2 |  | 3 | 0 | FS702/FP302 |  | Residence | 6
18 | Sheet 62274 | 18 | Level 29 | WIR - 01839 | Wall | fire fighting pipe | 3" |  |  | 5" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Residence | 2
19 | Sheet 62274 | 19 | Level 29 | WIR - 01839 | Shaft | PVC pipe | 4" |  |  | 6" |  |  |  | 2 |  | 2 | 0 | FS702/FP302 |  | Residence | 4
20 | Sheet 62274 | 20 | Level 29 | WIR - 01839 | Shaft | PVC pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Residence | 2
21 | Sheet 62274 | 21 | Level 29 | WIR - 01839 | Wall | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 13 | 0 | FS709 |  | Residence | 26
22 | Sheet 62274 | 22 | Level 29 | WIR - 01839 | Wall | fire fighting pipe | 1" |  |  | 3" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Residence | 2
23 | Sheet 62274 | 23 | Level 29 | WIR - 01839 | Wall | fire fighting pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Residence | 2 | 1 | -0.0010134
24 | Sheet 62274 | 23 | Level 29 | WIR - 01839 | Wall | opening |  |  |  | 0.2 | 0.3 | 0.06 | 0.059509 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Residence | 2 |  | 0.12 | 0.11899 | 0.059477
25 | Sheet 62274 | 24 | Level 29 | WIR - 01839 | FTR work | cable tray | 0.05 | 0.2 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Residence | 2 |  | -0.02
26 | Sheet 62274 | 25 | Level 29 | WIR - 01839 | FTR work | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Residence | 2 |  | -0.02
27 | Sheet 62274 | 25 | Level 29 | WIR - 01839 | FTR work | opening |  |  |  | 0.2 | 0.75 | 0.15 | 0.13 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Residence | 2 |  | 0.3 | 0.26 | 0.13
28 | Sheet 62274 | 26 | Level 29 | WIR - 01839 | Shaft | PVC pipe | 4" |  |  | 6" |  |  |  | 2 |  | 2 | 0 | FS702/FP302 |  | Residence | 4
29 | Sheet 62274 | 27 | Level 29 | WIR - 01839 | Shaft | PVC pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Residence | 2
Residence
December 2022 - Residence | [19 empty] | Residence
1 | Sheet 62275 | 28 | Level 29 | WIR - 01839 | Staircase | fire fighting pipe | 3" |  |  | 5" |  |  |  | 2 |  | 1 | 0 | FS702 | Sheet 62275 | Residence | 2
2 | Sheet 62275 | 29 | Level 29 | WIR - 01839 | Housekeeping | CHW pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Residence | 4 | 2 | -0.0081073
3 | Sheet 62275 | 30 | Level 29 | WIR - 01839 | Housekeeping | fire fighting pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Residence | 2 | 3 | -0.0091207
4 | Sheet 62275 | 31 | Level 29 | WIR - 01839 | Housekeeping | conduit pipe | 0.5" |  | 0.00013266 |  |  |  |  | 2 |  | 4 | 0 | FS709/FB750 |  | Residence | 8 | 0.5 | -0.0010134
5 | Sheet 62275 | 31 | Level 29 | WIR - 01839 | Housekeeping | opening |  |  |  | 0.4 | 0.8 | 0.32 | 0.31113 | 2 | 245 | 1 | 490 | FS702/FB750 |  | Residence | 2 |  | 0.64 | 0.62176 | 0.31063
6 | Sheet 62275 | 32 | Level 29 | WIR - 01839 | Shaft | fire fighting pipe | 4" |  |  | 6" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Residence | 2
7 | Sheet 62275 | 33 | Level 29 | WIR - 01839 | Shaft | fire fighting pipe | 3" |  |  | 5" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Residence | 2
8 | Sheet 62275 | 34 | Level 29 | WIR - 01839 | Shaft | CDP pipe | 3" |  |  | 5" |  |  |  | 2 |  | 2 | 0 | FS702/FP302 |  | Residence | 4
9 | Sheet 62275 | 35 | Level 29 | WIR - 01839 | Shaft | PVC pipe | 3" |  |  | 5" |  |  |  | 2 |  | 2 | 0 | FS702/FP302 |  | Residence | 4
10 | Sheet 62275 | 36 | Level 29 | WIR - 01839 | Shaft | PPR pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Residence | 2
11 | Sheet 62275 | 37 | Level 29 | WIR - 01839 | Shaft | fire fighting pipe | 1" |  |  | 3" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Residence | 2
12 | Sheet 62275 | 38 | Level 29 | WIR - 01839 | Shaft | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 |  | 1 |  | 2 | 0 | FS702 |  | Residence | 2
13 | Sheet 62275 | 39 | Level 29 | WIR - 01839 | Corridor Entry Dr. | duct | 0.2 | 0.2 | 0.04 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750 |  | Residence | 4 |  | -0.16
14 | Sheet 62275 | 39 | Level 29 | WIR - 01839 | Corridor Entry Dr. | opening |  |  |  | 0.25 | 0.3 | 0.075 | 0.07 | 2 | 95 | 2 | 380 | FS702/FB750 |  | Residence | 4 |  | 0.3 | 0.14 | 0.07
15 | Sheet 62275 | 40 | Level 29 | WIR - 01839 | Corridor Entry Dr. | duct | 0.2 | 0.3 | 0.06 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Residence | 2 |  | -0.12
16 | Sheet 62275 | 40 | Level 29 | WIR - 01839 | Corridor Entry Dr. | opening |  |  |  | 0.25 | 0.35 | 0.0875 | 0.0275 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Residence | 2 |  | 0.175 | 0.055 | 0.0275
17 | Sheet 62275 | 41 | Level 29 | WIR - 01839 | Corridor Entry Dr. | fire fighting pipe | 3" |  |  | 5" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Residence | 2
18 | Sheet 62275 | 42 | Level 29 | WIR - 01839 | Corridor Entry Dr. | CHW pipe | 2" |  |  | 4" |  |  |  | 2 |  | 2 | 0 | FS709 |  | Residence | 4
19 | Sheet 62275 | 43 | Level 29 | WIR - 01839 | Corridor Entry Dr. | cable tray |  |  |  | 0.2 | 0.3 | 0.06 |  | 2 |  | 1 | 0 | FS702/FB750 |  | Residence | 2
20 | Sheet 62275 | 44 | Level 29 | WIR - 01839 | Corridor Entry Dr. | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 18 | 0 | FS709 |  | Residence | 36
21 | Sheet 62275 | 45 | Level 29 | WIR - 01839 | Lobby | CHW pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Residence | 4 | 2 | -0.0081073
22 | Sheet 62275 | 46 | Level 29 | WIR - 01839 | Lobby | conduit pipe | 0.5" |  | 0.00013266 |  |  |  |  | 2 |  | 8 | 0 | FS709/FB750 |  | Residence | 16 | 0.5 | -0.0020268
23 | Sheet 62275 | 46 | Level 29 | WIR - 01839 | Lobby | opening |  |  |  | 0.3 | 0.3 | 0.09 | 0.085014 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Residence | 2 |  | 0.18 | 0.16987 | 0.084852
24 | Sheet 62275 | 47 | Level 29 | WIR - 01839 | Lobby | CDP pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Residence | 2
25 | Sheet 62275 | 48 | Level 29 | WIR - 01839 | Lobby | fire fighting pipe | 1" |  |  | 3" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Residence | 2
26 | Sheet 62275 | 49 | Level 29 | WIR - 01839 | Lobby | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 3 | 0 | FS709 |  | Residence | 6
27 | Sheet 62275 | 50 | Level 29 | WIR - 01839 | Electrical Room | duct | 0.2 | 0.4 | 0.08 | 0.25 | 0.45 | 0.1125 |  | 1 |  | 1 | 0 | FS702 |  | Residence | 1
28 | Sheet 62275 | 51 | Level 29 | WIR - 01839 | Electrical Room | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 5 | 0 | FS709 |  | Residence | 10
29 | Sheet 62275 | 52 | Level 29 | WIR - 01839 | Corridor Entry Dr. | duct | 0.2 | 0.2 | 0.04 |  |  |  |  | 2 |  | 3 | 0 | FS702/FB750 |  | Residence | 6 |  | -0.24
30 | Sheet 62275 | 52 | Level 29 | WIR - 01839 | Corridor Entry Dr. | opening |  |  |  | 0.26 | 0.3 | 0.078 | 0.114 | 2 | 150 | 3 | 900 | FS702/FB750 |  | Residence | 6 |  | 0.468 | 0.228 | 0.114
31 | Sheet 62275 | 53 | Level 29 | WIR - 01839 | Corridor Entry Dr. | CHW pipe | 2" |  |  | 4" |  |  |  | 2 |  | 2 | 0 | FS709 |  | Residence | 4
32 | Sheet 62275 | 54 | Level 29 | WIR - 01839 | Corridor Entry Dr. | fire fighting pipe | 4" |  |  | 6" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Residence | 2
Residence
December 2022 - Residence | [19 empty] | Residence
1 | Sheet 62276 | 55 | Level 29 | WIR - 01839 | Corridor Entry Dr. | cable tray |  |  |  | 0.1 | 0.3 | 0.03 |  | 2 |  | 1 | 0 | FS702/FB750 | Sheet 62276 | Residence | 2
2 | Sheet 62276 | 56 | Level 29 | WIR - 01839 | Corridor Entry Dr. | CDP pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Residence | 2
3 | Sheet 62276 | 57 | Level 29 | WIR - 01839 | Corridor Entry Dr. | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 10 | 0 | FS709 |  | Residence | 20
4 | Sheet 62276 | 58 | Level 29 | WIR - 01839 | Shaft | CHW pipe | 4" |  |  | 6" |  |  |  | 2 |  | 2 | 0 | FS709 |  | Residence | 4
5 | Sheet 62276 | 59 | Level 29 | WIR - 01839 | Shaft | CHW pipe | 2" |  |  | 4" |  |  |  | 2 |  | 2 | 0 | FS709 |  | Residence | 4
6 | Sheet 62276 | 60 | Level 29 | WIR - 01839 | Water Meter Rm | PPR pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 2 | 0 | FS702/FP302/FB750 |  | Residence | 4 | 2 | -0.0081073
7 | Sheet 62276 | 61 | Level 29 | WIR - 01839 | Water Meter Rm | fire fighting pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Residence | 2 | 1 | -0.0010134
8 | Sheet 62276 | 62 | Level 29 | WIR - 01839 | Water Meter Rm | conduit pipe | 0.5" |  | 0.00013266 |  |  |  |  | 2 |  | 1 | 0 | FS709/FB750 |  | Residence | 2 | 0.5 | -0.00025335
9 | Sheet 62276 | 62 | Level 29 | WIR - 01839 | Water Meter Rm | opening |  |  |  | 0.25 | 0.6 | 0.15 | 0.14545 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Residence | 2 |  | 0.3 | 0.29063 | 0.14517
10 | Sheet 62276 | 63 | Level 29 | WIR - 01839 | Water Meter Rm | CDP pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Residence | 2
11 | Sheet 62276 | 64 | Level 29 | WIR - 01839 | FF Lobby | fire fighting pipe | 1" |  |  | 3" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Residence | 2
12 | Sheet 62276 | 65 | Level 29 | WIR - 01839 | FF Lobby | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 3 | 0 | FS709 |  | Residence | 6
13 | Sheet 62276 | 66 | Level 29 | WIR - 01839 | FHC | fire fighting pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Residence | 2
14 | Sheet 62276 | 67 | Level 29 | WIR - 01839 | Shaft | PPR pipe | 2" |  |  | 4" |  |  |  | 2 |  | 2 | 0 | FS702/FP302 |  | Residence | 4
15 | Sheet 62276 | 68 | Level 29 | WIR - 01839 | Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 |  | 1 |  | 1 | 0 | FS702 |  | Residence | 1
16 | Sheet 62276 | 69 | Level 29 | WIR - 01839 | Shaft | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 4 | 0 | FS709 |  | Residence | 8
17 | Sheet 62276 | 70 | Level 29 | WIR - 01839 | Staircase | fire fighting pipe | 3" |  |  | 5" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Residence | 2
Hotel
December 2022 - Hotel | [19 empty] | Hotel
1 | Sheet 62271 | 1 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | duct | 0.86 | 11.38 | 9.7868 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 | Sheet 62271 | Hotel | 1 |  | -9.7868
2 | Sheet 62271 | 1 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | opening |  |  |  | 1.3 | 11.425 | 14.8525 | 5.0657 | 1 | 450 | 1 | 2279.565 | FS702/FB750 |  | Hotel | 5.0657 |  | 14.8525 | 5.0657 | 0
3 | Sheet 62271 | 1 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | duct | 0.86 | 11.38 | 9.7868 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 | Sheet 62271 | Hotel | 1 |  | -9.7868
4 | Sheet 62271 | 1 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | opening |  |  |  | 1.3 | 11.425 | 14.8525 | 5.0657 | 1 | 450 | 1 | 2279.565 | FS702/FB750 |  | Hotel | 5.0657 |  | 14.8525 | 5.0657 | 0
5 | Sheet 62271 | 2 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | duct | 0.32 | 0.34 | 0.1088 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1 |  | -0.1088
6 | Sheet 62271 | 2 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | opening |  |  |  | 0.42 | 0.37 | 0.1554 | 0.0466 | 1 | 50 | 1 | 50 | FS702/FB750 |  | Hotel | 1 |  | 0.1554 | 0.0466 | 0
7 | Sheet 62271 | 3 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | PVC pipe | 3" |  |  | 5" |  |  |  | 1 |  | 1 | 0 | FS702/FP302 |  | Hotel | 1
8 | Sheet 62271 | 4 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | PVC pipe | 2" |  |  | 4" |  |  |  | 1 |  | 1 | 0 | FS702/FP302 |  | Hotel | 1
9 | Sheet 62271 | 5 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | fire fighting pipe | 2" |  |  | 4" |  |  |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
10 | Sheet 62271 | 6 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | CHW pipe | 8" |  |  | 10" |  |  |  | 1 |  | 2 | 0 | FS709 |  | Hotel | 2
11 | Sheet 62271 | 7 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | CDP pipe | 2" |  |  | 4" |  |  |  | 1 |  | 1 | 0 | FS702/FP302 |  | Hotel | 1
12 | Sheet 62271 | 8 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 1 |  | 8 | 0 | FS709 |  | Hotel | 8
13 | Sheet 62271 | 9 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | PPR pipe | 1" |  |  | 3" |  |  |  | 1 |  | 1 | 0 | FS702/FP302 |  | Hotel | 1
14 | Sheet 62271 | 10 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | CHW pipe | 3" |  |  | 5" |  |  |  | 1 |  | 2 | 0 | FS709 |  | Hotel | 2
15 | Sheet 62271 | 11 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | cable tray |  |  |  | 0.33 | 0.42 | 0.1386 |  | 1 |  | 2 | 0 | FS702/FB750 |  | Hotel | 2
16 | Sheet 62271 | 12 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | cable trunking |  |  |  | 0.2 | 0.32 | 0.064 |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
17 | Sheet 62271 | 13 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | fire fighting pipe | 2" |  |  | 4" |  |  |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
18 | Sheet 62271 | 14 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | CHW pipe | 4" |  |  | 6" |  |  |  | 1 |  | 2 | 0 | FS709 |  | Hotel | 2
19 | Sheet 62271 | 15 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | CHW pipe | 8" |  |  | 10" |  |  |  | 1 |  | 2 | 0 | FS709 |  | Hotel | 2
20 | Sheet 62271 | 16 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | PVC pipe | 8" |  | 0.032349 |  |  |  |  | 1 |  | 2 | 0 | FS702/FP302/FB750 |  | Hotel | 2 | 8 | -0.064859
21 | Sheet 62271 | 17 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | PVC pipe | 6" |  | 0.017662 |  |  |  |  | 1 |  | 2 | 0 | FS702/FP302/FB750 |  | Hotel | 2 | 6 | -0.036483
22 | Sheet 62271 | 18 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | PVC pipe | 4" |  | 0.00785 |  |  |  |  | 1 |  | 1 | 0 | FS702/FP302/FB750 |  | Hotel | 1 | 4 | -0.0081073
23 | Sheet 62271 | 19 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | CHW pipe | 8" |  | 0.032349 |  |  |  |  | 1 |  | 2 | 0 | FS709/FB750 |  | Hotel | 2 | 8 | -0.064859
24 | Sheet 62271 | 20 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 2 | 0 | FS702/FB750 |  | Hotel | 2 |  | -0.03
25 | Sheet 62271 | 21 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | PPR pipe | 1" |  | 0.00049063 |  |  |  |  | 1 |  | 1 | 0 | FS702/FP302/FB750 |  | Hotel | 1 | 1 | -0.00050671
26 | Sheet 62271 | 21 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | opening |  |  |  | 0.76 | 1.9 | 1.444 | 1.2409 | 1 | 450 | 1 | 558.4222 | FS702/FB750 |  | Hotel | 1.2409 |  | 1.444 | 1.2392 | -0.0017522
27 | Sheet 62271 | 22 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | duct | 1.05 | 1.6 | 1.68 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1.68 |  | -1.68
28 | Sheet 62271 | 23 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | CHW pipe | 8" |  | 0.032349 |  |  |  |  | 1 |  | 2 | 0 | FS709/FB750 |  | Hotel | 2 | 8 | -0.064859
29 | Sheet 62271 | 23 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | opening |  |  |  | 1.6 | 1.75 | 2.8 | 1.0553 | 1 | 450 | 1 | 474.8858 | FS702/FB750 |  | Hotel | 1.0553 |  | 2.8 | 1.0551 | -0.00016043
30 | Sheet 62271 | 24 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | PVC pipe | 4" |  |  | 6" |  |  |  | 1 |  | 1 | 0 | FS702/FP302 |  | Hotel | 1
Hotel
December 2022 - Hotel | [19 empty] | Hotel
1 | Sheet 62272 | 1 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | CHW pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 | Sheet 62272 | Hotel | 4 | 4 | -0.032429
2 | Sheet 62272 | 1 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | PVC pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 2 | 0 | FS702/FP302/FB750 |  | Hotel | 4 | 6 | -0.072966
3 | Sheet 62272 | 2 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | opening |  |  |  | 0.47 | 2.7 | 1.269 | 1.218 | 2 | 450 | 1 | 1096.1775 | FS702/FB750 |  | Hotel | 2.4359 |  | 2.538 | 2.4326 | 1.2146
4 | Sheet 62272 | 2 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | CHW pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Hotel | 4 | 4 | -0.032429
5 | Sheet 62272 | 3 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | PVC pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 2 | 0 | FS702/FP302/FB750 |  | Hotel | 4 | 6 | -0.072966
6 | Sheet 62272 | 4 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | PVC pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 | FS702/FP302/FB750 |  | Hotel | 2 | 2 | -0.0040537
7 | Sheet 62272 | 5 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | opening |  |  |  | 0.85 | 2.7 | 2.295 | 2.242 | 2 | 450 | 1 | 2017.8113 | FS702/FB750 |  | Hotel | 4.484 |  | 4.59 | 4.4806 | 2.2385
8 | Sheet 62272 | 6 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | CHW pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Hotel | 4 | 4 | -0.032429
9 | Sheet 62272 | 7 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | PVC pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 2 | 0 | FS702/FP302/FB750 |  | Hotel | 4 | 6 | -0.072966
10 | Sheet 62272 | 8 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | PVC pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 | FS702/FP302/FB750 |  | Hotel | 2 | 2 | -0.0040537
11 | Sheet 62272 | 9 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | opening |  |  |  | 0.85 | 2.7 | 2.295 | 2.242 | 2 | 450 | 1 | 2017.8113 | FS702/FB750 |  | Hotel | 4.484 |  | 4.59 | 4.4806 | 2.2385
Hotel
December 2022 - Hotel | [19 empty] | Hotel
1 | Sheet 62280 | 1 | Ground Level | WIR - 01955 | BOH Corridor | duct | 0.3 | 0.5 | 0.15 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 | Sheet 62280 | Hotel | 2 |  | -0.3
2 | Sheet 62280 | 1 | Ground Level | WIR - 01955 | BOH Corridor | opening |  |  |  | 0.38 | 0.58 | 0.2204 | 0.0704 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2 |  | 0.4408 | 0.1408 | 0.0704
3 | Sheet 62280 | 2 | Ground Level | WIR - 01955 | BOH Corridor | duct | 0.25 | 0.4 | 0.1 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2 |  | -0.2
4 | Sheet 62280 | 2 | Ground Level | WIR - 01955 | BOH Corridor | opening |  |  |  | 0.3 | 0.46 | 0.138 | 0.038 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2 |  | 0.276 | 0.076 | 0.038
5 | Sheet 62280 | 3 | Ground Level | WIR - 01955 | BOH Corridor | duct | 0.25 | 0.6 | 0.15 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2 |  | -0.3
6 | Sheet 62280 | 3 | Ground Level | WIR - 01955 | BOH Corridor | opening |  |  |  | 0.32 | 0.7 | 0.224 | 0.074 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2 |  | 0.448 | 0.148 | 0.074
7 | Sheet 62280 | 4 | Ground Level | WIR - 01955 | BOH Corridor | CHW pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Hotel | 4 | 2 | -0.0081073
8 | Sheet 62280 | 5 | Ground Level | WIR - 01955 | BOH Corridor | PPR pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 3 | 0 | FS702/FP302/FB750 |  | Hotel | 6 | 2 | -0.012161
9 | Sheet 62280 | 6 | Ground Level | WIR - 01955 | BOH Corridor | fire fighting pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2 | 3 | -0.0091207
10 | Sheet 62280 | 7 | Ground Level | WIR - 01955 | BOH Corridor | PVC pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 1 | 0 | FS702/FP302/FB750 |  | Hotel | 2 | 4 | -0.016215
11 | Sheet 62280 | 8 | Ground Level | WIR - 01955 | BOH Corridor | PVC pipe | 8" |  | 0.032349 |  |  |  |  | 2 |  | 2 | 0 | FS702/FP302/FB750 |  | Hotel | 4 | 8 | -0.12972
12 | Sheet 62280 | 9 | Ground Level | WIR - 01955 | BOH Corridor | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 2 |  | 3 | 0 | FS702/FB750 |  | Hotel | 6 |  | -0.015
13 | Sheet 62280 | 10 | Ground Level | WIR - 01955 | BOH Corridor | cable tray | 0.05 | 0.2 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2 |  | -0.02
14 | Sheet 62280 | 11 | Ground Level | WIR - 01955 | BOH Corridor | conduit pipe | 0.5" |  | 0.00013266 |  |  |  |  | 2 |  | 8 | 0 | FS709/FB750 |  | Hotel | 16 | 0.5 | -0.0020268
15 | Sheet 62280 | 12 | Ground Level | WIR - 01955 | BOH Corridor | cable trunking | 0.15 | 0.15 | 0.0225 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2 |  | -0.045
16 | Sheet 62280 | 12 | Ground Level | WIR - 01955 | BOH Corridor | opening |  |  |  | 0.8 | 1.9 | 1.52 | 1.3697 | 2 | 450 | 1 | 1232.6962 | FS702/FB750 |  | Hotel | 2.7393 |  | 3.04 | 2.7827 | 1.413
17 | Sheet 62280 | 13 | Ground Level | WIR - 01955 | BOH Corridor | cable tray | 0.05 | 0.1 | 0.005 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2 |  | -0.01
18 | Sheet 62280 | 14 | Ground Level | WIR - 01955 | BOH Corridor | cable trunking | 0.15 | 0.15 | 0.0225 |  |  |  |  | 2 |  | 3 | 0 | FS702/FB750 |  | Hotel | 6 |  | -0.135
19 | Sheet 62280 | 15 | Ground Level | WIR - 01955 | BOH Corridor | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750 |  | Hotel | 4 |  | -0.01
20 | Sheet 62280 | 15 | Ground Level | WIR - 01955 | BOH Corridor | opening |  |  |  | 0.25 | 1.2 | 0.3 | 0.2075 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2 |  | 0.6 | 0.445 | 0.2375
21 | Sheet 62280 | 16 | Ground Level | WIR - 01955 | BOH Corridor | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 2 |  | 3 | 0 | FS702/FB750 |  | Hotel | 6 |  | -0.06
22 | Sheet 62280 | 17 | Ground Level | WIR - 01955 | BOH Corridor | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750 |  | Hotel | 4 |  | -0.01
23 | Sheet 62280 | 18 | Ground Level | WIR - 01955 | BOH Corridor | cable tray | 0.05 | 0.1 | 0.005 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2 |  | -0.01
24 | Sheet 62280 | 18 | Ground Level | WIR - 01955 | BOH Corridor | opening |  |  |  | 0.25 | 1 | 0.25 | 0.195 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2 |  | 0.5 | 0.42 | 0.225
25 | Sheet 62280 | 19 | Ground Level | WIR - 01955 | BOH Corridor | duct | 0.2 | 0.5 | 0.1 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2 |  | -0.2
26 | Sheet 62280 | 20 | Ground Level | WIR - 01955 | BOH Corridor | CDP pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 1 | 0 | FS702/FP302/FB750 |  | Hotel | 2 | 3 | -0.0091207
27 | Sheet 62280 | 21 | Ground Level | WIR - 01955 | BOH Corridor | CHW pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Hotel | 4 | 2 | -0.0081073
28 | Sheet 62280 | 22 | Ground Level | WIR - 01955 | BOH Corridor | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750 |  | Hotel | 4 |  | -0.01
29 | Sheet 62280 | 23 | Ground Level | WIR - 01955 | BOH Corridor | cable trunking | 0.15 | 0.15 | 0.0225 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2 |  | -0.045
30 | Sheet 62280 | 24 | Ground Level | WIR - 01955 | BOH Corridor | cable tray | 0.05 | 0.2 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2 |  | -0.02
31 | Sheet 62280 | 24 | Ground Level | WIR - 01955 | BOH Corridor | opening |  |  |  | 0.4 | 0.8 | 0.32 | 0.15916 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2 |  | 0.64 | 0.34777 | 0.18861
32 | Sheet 62280 | 25 | Ground Level | WIR - 01955 | BOH Corridor | CDP pipe | 3" |  |  | 5" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
Hotel
December 2022 - Hotel | [19 empty] | Hotel
1 | Sheet 62281 | 26 | Ground Level | WIR - 01955 | Kitchen | duct | 8" |  | 0.032349 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 | Sheet 62281 | Hotel | 1 | 8 | -0.032429
2 | Sheet 62281 | 26 | Ground Level | WIR - 01955 | Kitchen | opening |  |  |  | 0.4 | 0.4 | 0.16 | 0.12765 | 1 | 150 | 1 | 150 | FS702/FB750 |  | Hotel | 1 |  | 0.16 | 0.12757 | -8.0214e-05
3 | Sheet 62281 | 27 | Ground Level | WIR - 01955 | Kitchen | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1 |  | -0.015
4 | Sheet 62281 | 28 | Ground Level | WIR - 01955 | Kitchen | fire fighting pipe | 2" |  | 0.0019625 |  |  |  |  | 1 |  | 2 | 0 | FS702/FB750 |  | Hotel | 2 | 2 | -0.0040537
5 | Sheet 62281 | 29 | Ground Level | WIR - 01955 | Kitchen | PVC pipe | 3" |  | 0.0044156 |  |  |  |  | 1 |  | 1 | 0 | FS702/FP302/FB750 |  | Hotel | 1 | 3 | -0.0045604
6 | Sheet 62281 | 30 | Ground Level | WIR - 01955 | Kitchen | CHW pipe | 2" |  | 0.0019625 |  |  |  |  | 1 |  | 2 | 0 | FS709/FB750 |  | Hotel | 2 | 2 | -0.0040537
7 | Sheet 62281 | 30 | Ground Level | WIR - 01955 | Kitchen | opening |  |  |  | 0.85 | 0.9 | 0.765 | 0.73773 | 1 | 400 | 1 | 400 | FS702/FB750 |  | Hotel | 1 |  | 0.765 | 0.73733 | -0.00040206
8 | Sheet 62281 | 31 | Ground Level | WIR - 01955 | Kitchen | PVC pipe | 3" |  |  | 5" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
9 | Sheet 62281 | 32 | Ground Level | WIR - 01955 | Kitchen | CDP pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
10 | Sheet 62281 | 33 | Ground Level | WIR - 01955 | Kitchen | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 3 | 0 | FS709 |  | Hotel | 6
11 | Sheet 62281 | 34 | Ground Level | WIR - 01955 | Kitchen | gas pipe | 3" |  |  | 5" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
12 | Sheet 62281 | 35 | Ground Level | WIR - 01955 | Kitchen | duct | 0.3 | 0.5 | 0.15 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2 |  | -0.3
13 | Sheet 62281 | 35 | Ground Level | WIR - 01955 | Kitchen | opening |  |  |  | 0.4 | 0.6 | 0.24 | 0.09 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2 |  | 0.48 | 0.18 | 0.09
14 | Sheet 62281 | 36 | Ground Level | WIR - 01955 | Kitchen | CDP pipe | 3" |  |  | 5" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
15 | Sheet 62281 | 37 | Ground Level | WIR - 01955 | Kitchen | gas pipe | 3" |  |  | 5" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
16 | Sheet 62281 | 38 | Ground Level | WIR - 01955 | Kitchen | duct | 0.2 | 1 | 0.2 | 0.26 | 1.05 | 0.273 |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
17 | Sheet 62281 | 39 | Ground Level | WIR - 01955 | Kitchen | duct | 0.4 | 0.6 | 0.24 | 0.46 | 0.68 | 0.3128 |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
18 | Sheet 62281 | 40 | Ground Level | WIR - 01955 | Kitchen | duct | 0.2 | 0.9 | 0.18 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2 |  | -0.36
19 | Sheet 62281 | 40 | Ground Level | WIR - 01955 | Kitchen | opening |  |  |  | 0.3 | 1.4 | 0.42 | 0.24 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2 |  | 0.84 | 0.48 | 0.24
20 | Sheet 62281 | 41 | Ground Level | WIR - 01955 | Kitchen | fire fighting pipe | 1" |  |  | 3" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
21 | Sheet 62281 | 42 | Ground Level | WIR - 01955 | Kitchen | PVC pipe | 2" |  |  | 4" |  |  |  | 2 |  | 2 | 0 | FS702/FP302 |  | Hotel | 4
22 | Sheet 62281 | 43 | Ground Level | WIR - 01955 | Kitchen | CHW pipe | 2" |  |  | 4" |  |  |  | 2 |  | 2 | 0 | FS709 |  | Hotel | 4
23 | Sheet 62281 | 44 | Ground Level | WIR - 01955 | Kitchen | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 6 | 0 | FS709 |  | Hotel | 12
24 | Sheet 62281 | 45 | Ground Level | WIR - 01955 | Kitchen | CDP pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
25 | Sheet 62281 | 46 | Ground Level | WIR - 01955 | Kitchen | duct | 0.4 | 0.6 | 0.24 | 0.48 | 0.68 | 0.3264 |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
26 | Sheet 62281 | 47 | Ground Level | WIR - 01955 | Kitchen | CDP pipe | 2" |  |  | 4" |  |  |  | 1 |  | 1 | 0 | FS702/FP302 |  | Hotel | 1
27 | Sheet 62281 | 48 | Ground Level | WIR - 01955 | Kitchen | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 1 |  | 4 | 0 | FS709 |  | Hotel | 4
28 | Sheet 62281 | 49 | Ground Level | WIR - 01955 | Kitchen | CHW pipe | 2" |  | 0.0019625 |  |  |  |  | 1 |  | 2 | 0 | FS709/FB750 |  | Hotel | 2 | 2 | -0.0040537
29 | Sheet 62281 | 50 | Ground Level | WIR - 01955 | Kitchen | fire fighting pipe | 1" |  | 0.00049063 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1 | 1 | -0.00050671
30 | Sheet 62281 | 51 | Ground Level | WIR - 01955 | Kitchen | cable tray | 0.05 | 0.2 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FS702/FB750 |  | Hotel | 2 |  | -0.02
31 | Sheet 62281 | 52 | Ground Level | WIR - 01955 | Kitchen | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1 |  | -0.01
32 | Sheet 62281 | 53 | Ground Level | WIR - 01955 | Kitchen | conduit pipe | 0.5" |  | 0.00013266 |  |  |  |  | 1 |  | 2 | 0 | FS709/FB750 |  | Hotel | 2 | 0.5 | -0.00025335
33 | Sheet 62281 | 53 | Ground Level | WIR - 01955 | Kitchen | opening |  |  |  | 0.4 | 0.8 | 0.32 | 0.28532 | 1 | 245 | 1 | 245 | FS702/FB750 |  | Hotel | 1 |  | 0.32 | 0.28519 | -0.00013277
Hotel
December 2022 - Hotel | [19 empty] | Hotel
1 | Sheet 62282 | 54 | Ground Level | WIR - 01955 | Window High | duct | 0.2 | 1 | 0.2 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 | Sheet 62282 | Hotel | 2 |  | -0.4
2 | Sheet 62282 | 54 | Ground Level | WIR - 01955 | Window High | opening |  |  |  | 0.3 | 1.15 | 0.345 | 0.145 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2 |  | 0.69 | 0.29 | 0.145
3 | Sheet 62282 | 55 | Ground Level | WIR - 01955 | Window High | duct | 0.2 | 1 | 0.2 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2 |  | -0.4
4 | Sheet 62282 | 55 | Ground Level | WIR - 01955 | Window High | opening |  |  |  | 0.25 | 1.06 | 0.265 | 0.065 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2 |  | 0.53 | 0.13 | 0.065
5 | Sheet 62282 | 56 | Ground Level | WIR - 01955 | Window High | PVC pipe | 2" |  |  | 4" |  |  |  | 2 |  | 2 | 0 | FS702/FP302 |  | Hotel | 4
6 | Sheet 62282 | 57 | Ground Level | WIR - 01955 | Window High | PPR pipe | 2" |  |  | 4" |  |  |  | 2 |  | 5 | 0 | FS702/FP302 |  | Hotel | 10
7 | Sheet 62282 | 58 | Ground Level | WIR - 01955 | Window High | fire fighting pipe | 1" |  |  | 3" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
8 | Sheet 62282 | 59 | Ground Level | WIR - 01955 | Window High | CHW pipe | 2" |  |  | 4" |  |  |  | 2 |  | 2 | 0 | FS709 |  | Hotel | 4
9 | Sheet 62282 | 60 | Ground Level | WIR - 01955 | Window High | cable tray |  |  |  | 0.2 | 0.3 | 0.06 |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
10 | Sheet 62282 | 61 | Ground Level | WIR - 01955 | Window High | PVC pipe | 3" |  |  | 5" |  |  |  | 2 |  | 2 | 0 | FS702/FP302 |  | Hotel | 4
11 | Sheet 62282 | 62 | Ground Level | WIR - 01955 | Window High | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 2 | 0 | FS709 |  | Hotel | 4
12 | Sheet 62282 | 63 | Ground Level | WIR - 01955 | Window High | duct | 0.25 | 0.8 | 0.2 | 0.3 | 0.86 | 0.258 |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
13 | Sheet 62282 | 64 | Ground Level | WIR - 01955 | Window High | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 4 | 0 | FS709 |  | Hotel | 8
14 | Sheet 62282 | 65 | Ground Level | WIR - 01955 | Window High | duct | 0.25 | 1 | 0.25 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2 |  | -0.5
15 | Sheet 62282 | 65 | Ground Level | WIR - 01955 | Window High | opening |  |  |  | 0.35 | 1.08 | 0.378 | 0.128 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2 |  | 0.756 | 0.256 | 0.128
16 | Sheet 62282 | 66 | Ground Level | WIR - 01955 | Window High | CHW pipe | 2" |  |  | 4" |  |  |  | 2 |  | 2 | 0 | FS709 |  | Hotel | 4
17 | Sheet 62282 | 67 | Ground Level | WIR - 01955 | Window High | PPR pipe | 2" |  |  | 4" |  |  |  | 2 |  | 3 | 0 | FS702/FP302 |  | Hotel | 6
18 | Sheet 62282 | 68 | Ground Level | WIR - 01955 | Window High | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 1 | 0 | FS709 |  | Hotel | 2
19 | Sheet 62282 | 69 | Ground Level | WIR - 01955 | Window High | fire fighting pipe | 1" |  |  | 3" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
20 | Sheet 62282 | 71 | Ground Level | WIR - 01955 | Food Storage Rm | CHW pipe | 3" |  |  | 5" |  |  |  | 2 |  | 2 | 0 | FS709 |  | Hotel | 4
21 | Sheet 62282 | 72 | Ground Level | WIR - 01955 | Food Storage Rm | CDP pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
22 | Sheet 62282 | 73 | Ground Level | WIR - 01955 | Food Storage Rm | cable tray | 0.05 | 0.2 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2 |  | -0.02
23 | Sheet 62282 | 74 | Ground Level | WIR - 01955 | Food Storage Rm | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750 |  | Hotel | 4 |  | -0.01
24 | Sheet 62282 | 74 | Ground Level | WIR - 01955 | Food Storage Rm | opening |  |  |  | 0.3 | 0.6 | 0.18 | 0.15 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2 |  | 0.36 | 0.33 | 0.18
25 | Sheet 62282 | 75 | Ground Level | WIR - 01955 | Food Storage Rm | conduit pipe | 0.5" |  | 0.00013266 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Hotel | 4 | 0.5 | -0.00050671
26 | Sheet 62282 | 75 | Ground Level | WIR - 01955 | Food Storage Rm | opening |  |  |  | 0.08 | 1 | 0.08 | 0.079735 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2 |  | 0.16 | 0.15949 | 0.079759
27 | Sheet 62282 | 76 | Ground Level | WIR - 01955 | Food Storage Rm | PVC pipe | 8" |  |  | 10" |  |  |  | 2 |  | 5 | 0 | FS702/FP302 |  | Hotel | 10
28 | Sheet 62282 | 77 | Ground Level | WIR - 01955 | Food Storage Rm | PVC pipe | 4" |  |  | 6" |  |  |  | 2 |  | 3 | 0 | FS702/FP302 |  | Hotel | 6
29 | Sheet 62282 | 78 | Ground Level | WIR - 01955 | Food Storage Rm | PVC pipe | 2" |  |  | 4" |  |  |  | 1 |  | 3 | 0 | FS702/FP302 |  | Hotel | 3
30 | Sheet 62282 | 79 | Ground Level | WIR - 01955 | Food Storage Rm | PPR pipe | 2" |  |  | 4" |  |  |  | 2 |  | 2 | 0 | FS702/FP302 |  | Hotel | 4
31 | Sheet 62282 | 80 | Ground Level | WIR - 01955 | Food Storage Rm | fire fighting pipe | 1" |  |  | 3" |  |  |  | 2 |  | 2 | 0 | FS702 |  | Hotel | 4
32 | Sheet 62282 | 81 | Ground Level | WIR - 01955 | Food Storage Rm | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 7 | 0 | FS709 |  | Hotel | 14
Hotel
December 2022 - Hotel | [19 empty] | Hotel
1 | Sheet 62279 | 1 | Level 28 | WIR - 00188 | Shaft Opening 01 | duct | 0.4 | 0.4 | 0.16 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750 | Sheet 62279 | Hotel | 4 |  | -0.64
2 | Sheet 62279 | 1 | Level 28 | WIR - 00188 | Shaft Opening 01 | duct | 0.3 | 0.75 | 0.225 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2 |  | -0.45
3 | Sheet 62279 | 1 | Level 28 | WIR - 00188 | Shaft Opening 01 | CHW pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Hotel | 4 | 4 | -0.032429
4 | Sheet 62279 | 1 | Level 28 | WIR - 00188 | Shaft Opening 01 | opening |  |  |  | 0.85 | 2.65 | 2.2525 | 1.6918 | 2 | 450 | 1 | 1522.62 | FS702/FB750 |  | Hotel | 3.3836 |  | 4.505 | 3.3826 | 1.6908
5 | Sheet 62279 | 2 | Level 28 | WIR - 00188 | Shaft Opening 02 | duct | 0.4 | 0.4 | 0.16 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750 |  | Hotel | 4 |  | -0.64
6 | Sheet 62279 | 2 | Level 28 | WIR - 00188 | Shaft Opening 02 | duct | 0.3 | 0.75 | 0.225 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2 |  | -0.45
7 | Sheet 62279 | 2 | Level 28 | WIR - 00188 | Shaft Opening 02 | CHW pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Hotel | 4 | 4 | -0.032429
8 | Sheet 62279 | 2 | Level 28 | WIR - 00188 | Shaft Opening 02 | PVC pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 1 | 0 | FS702/FP302/FB750 |  | Hotel | 2 | 4 | -0.016215
9 | Sheet 62279 | 2 | Level 28 | WIR - 00188 | Shaft Opening 02 | opening |  |  |  | 0.85 | 2.65 | 2.2525 | 1.684 | 2 | 450 | 1 | 1515.555 | FS702/FB750 |  | Hotel | 3.3679 |  | 4.505 | 3.3664 | 1.6824
10 | Sheet 62279 | 3 | Level 28 | WIR - 00188 | Shaft Opening 03 | duct | 0.4 | 0.4 | 0.16 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2 |  | -0.32
11 | Sheet 62279 | 3 | Level 28 | WIR - 00188 | Shaft Opening 03 | CDP pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 1 | 0 | FS702/FP302/FB750 |  | Hotel | 2 | 3 | -0.0091207
12 | Sheet 62279 | 3 | Level 28 | WIR - 00188 | Shaft Opening 03 | opening |  |  |  | 1.15 | 1.4 | 1.61 | 1.4456 | 2 | 450 | 1 | 1301.0259 | FS702/FB750 |  | Hotel | 2.8912 |  | 3.22 | 2.8909 | 1.4453
13 | Sheet 62279 | 3 | Level 28 | WIR - 00188 | Shaft Opening 03 | CHW pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Hotel | 4 | 4 | -0.032429
14 | Sheet 62279 | 3 | Level 28 | WIR - 00188 | Shaft Opening 03 | duct | 0.4 | 0.4 | 0.16 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2 |  | -0.32
15 | Sheet 62279 | 3 | Level 28 | WIR - 00188 | Shaft Opening 03 | duct | 0.3 | 0.75 | 0.225 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2 |  | -0.45
16 | Sheet 62279 | 3 | Level 28 | WIR - 00188 | Shaft Opening 03 | opening |  |  |  | 1.02 | 1.25 | 1.275 | 0.8743 | 2 | 450 | 1 | 900 | FS702/FB750 |  | Hotel | 2 |  | 2.55 | 1.7476 | 0.87327
17 | Sheet 62279 | 4 | Level 28 | WIR - 00188 | Shaft Opening 04 | duct | 0.4 | 0.4 | 0.16 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750 |  | Hotel | 4 |  | -0.64
18 | Sheet 62279 | 4 | Level 28 | WIR - 00188 | Shaft Opening 04 | duct | 0.3 | 0.75 | 0.225 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2 |  | -0.45
19 | Sheet 62279 | 4 | Level 28 | WIR - 00188 | Shaft Opening 04 | PVC pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 1 | 0 | FS702/FP302/FB750 |  | Hotel | 2 | 6 | -0.036483
20 | Sheet 62279 | 4 | Level 28 | WIR - 00188 | Shaft Opening 04 | CDP pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 1 | 0 | FS702/FP302/FB750 |  | Hotel | 2 | 3 | -0.0091207
21 | Sheet 62279 | 4 | Level 28 | WIR - 00188 | Shaft Opening 04 | CHW pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Hotel | 4 | 4 | -0.032429
22 | Sheet 62279 | 4 | Level 28 | WIR - 00188 | Shaft Opening 04 | opening |  |  |  | 0.85 | 2.65 | 2.2525 | 1.6697 | 2 | 450 | 1 | 1502.7497 | FS702/FB750 |  | Hotel | 3.3394 |  | 4.505 | 3.337 | 1.6672
Residence
December 2022 - Residence | [19 empty] | Residence
1 | Sheet 62278 |  | Level 30 | WIR - 00184 | Corridor Shaft 03 | CHW pipe | 12" |  | 0.073025 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 | Sheet 62278 | Residence | 4 | 12 | -0.29186
2 | Sheet 62278 |  | Level 30 | WIR - 00184 | Corridor Shaft 03 | conduit pipe | 0.5" |  | 0.00013266 |  |  |  |  | 2 |  | 6 | 0 | FS709/FB750 |  | Residence | 12 | 0.5 | -0.0015201
3 | Sheet 62278 |  | Level 30 | WIR - 00184 | Corridor Shaft 03 | opening |  |  |  | 0.7 | 2.6 | 1.82 | 1.6732 | 2 | 450 | 1 | 1505.8393 | FS702/FB750 |  | Residence | 3.3463 |  | 3.64 | 3.3466 | 1.6735
4 | Sheet 62278 |  | Level 29 | WIR - 00184 | Corridor Shaft 03 | CHW pipe | 12" |  | 0.073025 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Residence | 4 | 12 | -0.29186
5 | Sheet 62278 |  | Level 29 | WIR - 00184 | Corridor Shaft 03 | conduit pipe | 0.5" |  | 0.00013266 |  |  |  |  | 2 |  | 5 | 0 | FS709/FB750 |  | Residence | 10 | 0.5 | -0.0012668
6 | Sheet 62278 |  | Level 29 | WIR - 00184 | Corridor Shaft 03 | opening |  |  |  | 0.7 | 2.6 | 1.82 | 1.6733 | 2 | 450 | 1 | 1505.9587 | FS702/FB750 |  | Residence | 3.3466 |  | 3.64 | 3.3469 | 1.6736
7 | Sheet 62278 |  | Level 27 | WIR - 00187 | Corridor Shaft 03 | CHW pipe | 12" |  | 0.073025 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Residence | 4 | 12 | -0.29186
8 | Sheet 62278 |  | Level 27 | WIR - 00187 | Corridor Shaft 03 | conduit pipe | 0.5" |  | 0.00013266 |  |  |  |  | 2 |  | 3 | 0 | FS709/FB750 |  | Residence | 6 | 0.5 | -0.00076006
9 | Sheet 62278 |  | Level 27 | WIR - 00187 | Corridor Shaft 03 | opening |  |  |  | 0.55 | 1.15 | 0.6325 | 0.48605 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Residence | 2 |  | 1.265 | 0.97238 | 0.48632
10 | Sheet 62278 |  | Level 26 | WIR - 00187 | Corridor Shaft 03 | CHW pipe | 12" |  | 0.073025 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Residence | 4 | 12 | -0.29186
11 | Sheet 62278 |  | Level 26 | WIR - 00187 | Corridor Shaft 03 | opening |  |  |  | 0.68 | 1.04 | 0.7072 | 0.56115 | 2 | 340 | 1 | 680 | FS702/FB750 |  | Residence | 2 |  | 1.4144 | 1.1225 | 0.56139
12 | Sheet 62278 |  | Level 22 | WIR - 00186 | Corridor Shaft 03 | CHW pipe | 12" |  | 0.073025 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Residence | 4 | 12 | -0.29186
13 | Sheet 62278 |  | Level 22 | WIR - 00186 | Corridor Shaft 03 | conduit pipe | 0.5" |  | 0.00013266 |  |  |  |  | 2 |  | 5 | 0 | FS709/FB750 |  | Residence | 10 | 0.5 | -0.0012668
14 | Sheet 62278 |  | Level 22 | WIR - 00186 | Corridor Shaft 03 | opening |  |  |  | 0.7 | 0.9 | 0.63 | 0.48329 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Residence | 2 |  | 1.26 | 0.96687 | 0.48358
15 | Sheet 62278 |  | Level 21 | WIR - 00186 | Corridor Shaft 03 | CHW pipe | 12" |  | 0.073025 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Residence | 4 | 12 | -0.29186
16 | Sheet 62278 |  | Level 21 | WIR - 00186 | Corridor Shaft 03 | conduit pipe | 0.5" |  | 0.00013266 |  |  |  |  | 2 |  | 6 | 0 | FS709/FB750 |  | Residence | 12 | 0.5 | -0.0015201
17 | Sheet 62278 |  | Level 21 | WIR - 00186 | Corridor Shaft 03 | opening |  |  |  | 0.7 | 0.95 | 0.665 | 0.51815 | 2 | 340 | 1 | 680 | FS702/FB750 |  | Residence | 2 |  | 1.33 | 1.0366 | 0.51846
18 | Sheet 62278 |  | Level 09 | WIR - 00183 | Corridor Shaft 03 | CHW pipe | 12" |  | 0.073025 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Residence | 4 | 12 | -0.29186
19 | Sheet 62278 |  | Level 09 | WIR - 00183 | Corridor Shaft 03 | conduit pipe | 0.5" |  | 0.00013266 |  |  |  |  | 2 |  | 6 | 0 | FS709/FB750 |  | Residence | 12 | 0.5 | -0.0015201
20 | Sheet 62278 |  | Level 09 | WIR - 00183 | Corridor Shaft 03 | opening |  |  |  | 0.72 | 0.98 | 0.7056 | 0.55875 | 2 | 340 | 1 | 680 | FS702/FB750 |  | Residence | 2 |  | 1.4112 | 1.1178 | 0.55906
21 | Sheet 62278 |  | Level 07 | WIR - 00183 | Corridor Shaft 03 | CHW pipe | 12" |  | 0.073025 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Residence | 4 | 12 | -0.29186
22 | Sheet 62278 |  | Level 07 | WIR - 00183 | Corridor Shaft 03 | conduit pipe | 0.5" |  | 0.00013266 |  |  |  |  | 2 |  | 5 | 0 | FS709/FB750 |  | Residence | 10 | 0.5 | -0.0012668
23 | Sheet 62278 |  | Level 07 | WIR - 00183 | Corridor Shaft 03 | opening |  |  |  | 0.7 | 1.2 | 0.84 | 0.69329 | 2 | 400 | 1 | 800 | FS702/FB750 |  | Residence | 2 |  | 1.68 | 1.3869 | 0.69358
24 | Sheet 62278 |  | Level 06 | WIR - 00183 | Corridor Shaft 03 | CHW pipe | 12" |  | 0.073025 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Residence | 4 | 12 | -0.29186
25 | Sheet 62278 |  | Level 06 | WIR - 00183 | Corridor Shaft 03 | conduit pipe | 0.5" |  | 0.00013266 |  |  |  |  | 2 |  | 5 | 0 | FS709/FB750 |  | Residence | 10 | 0.5 | -0.0012668
26 | Sheet 62278 |  | Level 06 | WIR - 00183 | Corridor Shaft 03 | opening |  |  |  | 0.65 | 1 | 0.65 | 0.50329 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Residence | 2 |  | 1.3 | 1.0069 | 0.50358
37.7968
[15 empty] | Grand Total |  | 33495.6828 |  |  |  | 941.926
WIR List as per SOS
[5 empty] | Level 29 | WIR - 01839
[5 empty] | Level 18 | WIR - 01768
[5 empty] | Ground Level | WIR - 01955
[5 empty] | Level 28 | WIR - 00188
[5 empty] | Level 30 | WIR - 00184
[5 empty] | Level 29 | WIR - 00184
[5 empty] | Level 27 | WIR - 00187
[5 empty] | Level 26 | WIR - 00187
[5 empty] | Level 22 | WIR - 00186
[5 empty] | Level 21 | WIR - 00186
[5 empty] | Level 09 | WIR - 00183
[5 empty] | Level 07 | WIR - 00183
[5 empty] | Level 06 | WIR - 00183