## IPC-6 (hidden)
PROJECT |  | DORCHESTER HOTEL AND RESIDENCES | [6 empty] | IPC-06
EMPLOYER |  | SKY PALACES REAL ESTATE DEVELOPMENT LLC
EMPLOYER'S REP |  | OMNIYAT CONCEPT INVESTMENTS LLC
ENGINEER |  | BREWER SMITH BREWER GULG ( BSBG )
MAIN CONTRACTOR |  | KHANSAHEB CIVIL ENGINEERING
FOR THE PERIOD ENDING |  | 2022-07-31
FIRE STOP WORKS ON MEP PENETRATIONS AND JOINTS
Item | Description | Contract Amount (AED) | Progress Completion (%) |  |  | Work Done (AED) |  |  | Remarks
|  |  | Previous | This Month | Cumulative | Previous | This Month | Cumulative
FIRESTOP MIDDLE EAST INVOICE REF.FME-INV-2022-0147
A | Firestop to MEP Penetrations | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
B | Firestop to Construction Joints | 441760 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Total MEP Amount | #REF! |  |  |  | #REF! | #REF! | #REF!

## Contract
FIRE STOP WORKS ON MEP PENETRATIONS AND JOINTS | [11 empty] | FIRE STOP |  | Certified Amount
[6 empty] | Quantity |  |  | Progress Amount (AED) |  |  |  |  | Quantity |  |  | Progress Amount (AED)
S.Nr | Description | Qty | Unit | Rate | Amount | Previous | Current | Cumulative | Previous | Current | Cumulative | WIR Ref./ Remarks |  | Previous | Current | Cumulative | Previous | Current | Cumulative
G | Supply and installation of firestop sealant and mineral wool to Head of wall / Wall to wall joints (Single Sided)
G1 | Upto 20mm joint width | 500 | m | 14 | 7000 | 3863.97 | 423.14 | 4287.11 | 54095.58 | 5923.96 | 60019.54 |  | 0 | 3863.97 | 423.14 | 4287.11 | 54095.58 | 5923.96 | 60019.54
G2 | Upto 30mm joint width | 500 | m | 20 | 10000 | 39 |  | 39 | 780 | 0 | 780 |  | 0 | 39 | 0 | 39 | 780 | 0 | 780
G3 | Upto 35mm joint width | 150 | m | 27 | 4050 |  |  |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0
H | Supply and installation of Sealant and mineral wool non-fire rated Head of wall / Wall to wall joints (Single Sided) | [12 empty] | 0 |  | 0 | 0 | 0 | 0
H1 | Upto 20mm joint width | 250 | m | 10 | 2500 |  |  |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  | 0 | 0 | 0 | 0
A | Supply and apply firestop sealant and mineral wool backing to non-insulated metallic/ non-combustible pipes (Single Sided) | [12 empty] | 0 |  | 0 | 0 | 0 | 0
A1 | Upto and including 2"ɸ | 100 | No. | 14 | 1400 | 55 | 4 | 59 | 770 | 56 | 826 |  | 0 | 55 | 4 | 59 | 770 | 56 | 826
A2 | Upto and including 3"ɸ | 100 | No. | 16 | 1600 | 42 | 14 | 56 | 672 | 224 | 896 |  | 0 | 42 | 14 | 56 | 672 | 224 | 896
A3 | Upto and including 4"ɸ | 100 | No. | 21 | 2100 | 8 | 1 | 9 | 168 | 21 | 189 |  | 0 | 8 | 1 | 9 | 168 | 21 | 189
A4 | Upto and including 6"ɸ | 100 | No. | 27 | 2700 | 6 | 9 | 15 | 162 | 243 | 405 |  | 0 | 6 | 9 | 15 | 162 | 243 | 405
A5 | Upto and including 8"ɸ | 50 | No. | 46 | 2300 | 2 | 3 | 5 | 92 | 138 | 230 |  | 0 | 2 | 3 | 5 | 92 | 138 | 230
A6 | Upto and including 24"ɸ | 10 | No. | 141 | 1410 |  |  |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0
B | Supply and apply firestop sealant and mineral wool backing to insulated metallic/ non-combustible pipes (Single Sided) | [12 empty] | 0 |  | 0 | 0 | 0 | 0
B1 | Upto and including 2"ɸ | 200 | No. | 20 | 4000 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | Upto and including 3"ɸ | 200 | No. | 23 | 4600 | 65 |  | 65 | 1495 | 0 | 1495 |  | 0 | 65 | 0 | 65 | 1495 | 0 | 1495
B3 | Upto and including 4"ɸ | 200 | No. | 29 | 5800 | 10 | 10 | 20 | 290 | 290 | 580 |  | 0 | 10 | 10 | 20 | 290 | 290 | 580
B4 | Upto and including 6"ɸ | 200 | No. | 35 | 7000 |  | 4 | 4 | 0 | 140 | 140 |  | 0 | 0 | 4 | 4 | 0 | 140 | 140
B5 | Upto and including 8"ɸ | 100 | No. | 47 | 4700 |  | 8 | 8 | 0 | 376 | 376 |  | 0 | 0 | 8 | 8 | 0 | 376 | 376
B6 | Upto and including 16"ɸ | 50 | No. | 170 | 8500 | 4 |  | 4 | 680 | 0 | 680 |  | 0 | 4 | 0 | 4 | 680 | 0 | 680
C | Supply and apply firestop sealant and mineral wool backing to PVC conduits & cable pipes | [12 empty] | 0 |  | 0 | 0 | 0 | 0
C1 | Upto and including 2"ɸ |  |  | 18 |  | 17 |  | 17 | 306 | 0 | 306 |  | 0 | 17 | 0 | 17 | 306 | 0 | 306
C | Supply and apply firestop sealant and mineral wool backing to PVC/ combustible pipes (Single Sided) | [12 empty] | 0 |  | 0 | 0 | 0 | 0
C1 | Upto and including 2"ɸ | 400 | No. | 28 | 11200 | 13 |  | 13 | 364 | 0 | 364 |  | 0 | 13 | 0 | 13 | 364 | 0 | 364
C2 | Upto and including 3"ɸ | 400 | No. | 30 | 12000 | 173 | 7 | 180 | 5190 | 210 | 5400 |  | 0 | 173 | 7 | 180 | 5190 | 210 | 5400
C3 | Upto and including 4"ɸ | 400 | No. | 65 | 26000 | 29 |  | 29 | 1885 | 0 | 1885 |  | 0 | 29 | 0 | 29 | 1885 | 0 | 1885
C4 | Upto and including 6"ɸ | 250 | No. | 125 | 31250 | 39 | 8 | 47 | 4875 | 1000 | 5875 |  | 0 | 39 | 8 | 47 | 4875 | 1000 | 5875
C5 | Upto and including 8"ɸ | 250 | No. | 250 | 62500 | 37 | 19 | 56 | 9250 | 4750 | 14000 |  | 0 | 37 | 19 | 56 | 9250 | 4750 | 14000
D | Supply and apply firestop board material to cable tray openings, shaft openings and openings (Single Board) | [12 empty] | 0 |  | 0 | 0 | 0 | 0
D1 | For an area upto 0.05 m2 | 100 | No. | 50 | 5000 | 69 | 39 | 108 | 3450 | 1950 | 5400 |  | 0 | 69 | 39 | 108 | 3450 | 1950 | 5400
D2 | For an area upto 0.10 m2 | 100 | No. | 95 | 9500 | 139 | 53 | 192 | 13205 | 5035 | 18240 |  | 0 | 139 | 53 | 192 | 13205 | 5035 | 18240
D3 | For an area upto 0.15 m2 | 100 | No. | 150 | 15000 | 88 | 31 | 119 | 13200 | 4650 | 17850 |  | 0 | 88 | 31 | 119 | 13200 | 4650 | 17850
D4 | For an area upto 0.25 m2 | 100 | No. | 180 | 18000 | 70 | 28 | 98 | 12600 | 5040 | 17640 |  | 0 | 69 | 28 | 97 | 12420 | 5040 | 17460
D5 | For an area upto 0.35 m2 | 100 | No. | 245 | 24500 | 22 | 2 | 24 | 5390 | 490 | 5880 |  | 0 | 22 | 2 | 24 | 5390 | 490 | 5880
D6 | For an area upto 0.50 m2 | 50 | No. | 310 | 15500 | 57 | 21 | 78 | 17670 | 6510 | 24180 |  | 0 | 55 | 21 | 76 | 17050 | 6510 | 23560
D7 | For an area upto 0.65 m2 | 50 | No. | 340 | 17000 | 15 | 7 | 22 | 5100 | 2380 | 7480 |  | 0 | 14 | 7 | 21 | 4760 | 2380 | 7140
D8 | For an area upto 0.80 m2 | 50 | No. | 400 | 20000 | 9 | 2 | 11 | 3600 | 800 | 4400 |  | 0 | 9 | 2 | 11 | 3600 | 800 | 4400
D9 | For an area upto 1.00 m2 | 25 | m2 | 450 | 11250 | 102.1754 | 25.6979 | 127.8734 | 45978.9466 | 11564.0711 | 57543.0178 |  | 0 | 99.6534 | 25.6979 | 125.3514 | 44844.0466 | 11564.0711 | 56408.1178
E | Supply and apply firestopping materials to Metallic Duct with Fire Damper and L-angle (Single Sided) | [12 empty] | 0 |  | 0 | 0 | 0 | 0
E1 | For an area upto 0.05 m2 | 100 | No. | 32 | 3200 | 12 |  | 12 | 384 | 0 | 384 |  | 0 | 12 | 0 | 12 | 384 | 0 | 384
E2 | For an area upto 0.10 m2 | 100 | No. | 46 | 4600 | 16 |  | 16 | 736 | 0 | 736 |  | 0 | 16 | 0 | 16 | 736 | 0 | 736
E3 | For an area upto 0.20 m2 | 100 | No. | 51 | 5100 | 12 |  | 12 | 612 | 0 | 612 |  | 0 | 12 | 0 | 12 | 612 | 0 | 612
E4 | For an area upto 0.30 m2 | 100 | No. | 64 | 6400 | 2 |  | 2 | 128 | 0 | 128 |  | 0 | 2 | 0 | 2 | 128 | 0 | 128
E5 | For an area upto 0.40 m2 | 100 | No. | 74 | 7400 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
E6 | For an area upto 0.50 m2 | 100 | No. | 82 | 8200 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
E7 | For an area upto 0.60 m2 | 100 | No. | 88 | 8800 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
E8 | For an area upto 0.70 m2 | 50 | No. | 98 | 4900 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
E9 | For an area upto 0.80 m2 | 50 | No. | 103 | 5150 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
E10 | For an area upto 0.90 m2 | 25 | No. | 110 | 2750 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
E11 | For an area upto 1.00 m2 | 25 | m2 | 116 | 2900 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0
F | Supply and installation of Nullfire FR 230 firestop mortar material (100mm thickness) to Electrical Openings (Single Sided) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
F1 | For an area upto 1.00 m2 | 50 | m2 | 680 | 34000 | 35.4678 |  | 35.4678 | 24118.104 | 0 | 24118.104 |  | 0 | 34.9878 | 0 | 34.9878 | 23791.704 | 0 | 23791.704
| TOTAL AMOUNT OF CONSTRUCTION JOINTS |  |  |  | 441760 | 5051.6132 | 718.8379 | 5770.4512 | 227246.6306 | 51791.0311 | 279037.6618 |  |  | 5044.6112 | 718.8379 | 5763.4492 | 224645.3306 | 51791.0311 | 276436.3618
[16 empty] | KCE Claim | 227246.63 | 51791.03 | 279037.66
[16 empty] | Difference | -2601.2994 | 0.0011325 | -2601.2982

## Joints 20mm
Project: |  |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  |  | Khansaheb Civil Engineering
Period of Completed Works: |  |  |  | up to July 2022
Summary of Completed Firestopping Works (Construction Joints)
No. | Sos Number | Level | WIR No. | Location | Type | Joint Size (in meter) |  |  | Sides | Rate (AED) | Nos | Total (AED) |  |  | Hotel / Residence | QTY | Remarks
1 | Sheet 61023 | Level 25 | FSM-AX-WR-L25-00161 | Corridor | Head of wall joint | 0.02 | 35 | @ | 2 | 14 | 1 | 980 | 20 | Sheet 61023 | Residence | 70
2 | Sheet 61023 | Level 25 | FSM-AX-WR-L25-00161 | Corridor | Head of wall joint | 0.02 | 4 | @ | 2 | 14 | 3 | 336 | 20 |  | Residence | 24
3 | Sheet 61023 | Level 25 | FSM-AX-WR-L25-00161 | FF Lobby | Head of wall joint | 0.02 | 18 | @ | 2 | 14 | 1 | 504 | 20 |  | Residence | 36
4 | Sheet 61023 | Level 25 | FSM-AX-WR-L25-00161 | Housekeeping | Head of wall joint | 0.02 | 10 | @ | 2 | 14 | 1 | 280 | 20 |  | Residence | 20
5 | Sheet 61023 | Level 25 | FSM-AX-WR-L25-00161 | Garbage Room | Head of wall joint | 0.02 | 13 | @ | 2 | 14 | 1 | 364 | 20 |  | Residence | 26
6 | Sheet 61023 | Level 25 | FSM-AX-WR-L25-00161 | Passanger Lift lobby | Head of wall joint | 0.02 | 25 | @ | 2 | 14 | 1 | 700 | 20 |  | Residence | 50
7 | Sheet 61023 | Level 25 | FSM-AX-WR-L25-00161 | Water meter Rm | Head of wall joint | 0.02 | 12 | @ | 2 | 14 | 1 | 336 | 20 |  | Residence | 24
8 | Sheet 61023 | Level 25 | FSM-AX-WR-L25-00161 | Apartment, Shaft | Head of wall joint | 0.02 | 3.5 | @ | 2 | 14 | 3 | 294 | 20 |  | Residence | 21
9 | Sheet 61023 | Level 25 | FSM-AX-WR-L25-00161 | Apartment, Shaft | Head of wall joint | 0.02 | 5.1 | @ | 2 | 14 | 1 | 142.8 | 20 |  | Residence | 10.2
1 | Sheet 61024 | Level 24 | FSM-AX-WR-L24-00162 | Corridor | Head of wall joint | 0.02 | 35 | @ | 2 | 14 | 1 | 980 | 20 | Sheet 61024 | Residence | 70
2 | Sheet 61024 | Level 24 | FSM-AX-WR-L24-00162 | Corridor | Head of wall joint | 0.02 | 4 | @ | 2 | 14 | 3 | 336 | 20 |  | Residence | 24
3 | Sheet 61024 | Level 24 | FSM-AX-WR-L24-00162 | FF Lobby | Head of wall joint | 0.02 | 18 | @ | 2 | 14 | 1 | 504 | 20 |  | Residence | 36
4 | Sheet 61024 | Level 24 | FSM-AX-WR-L24-00162 | Housekeeping | Head of wall joint | 0.02 | 10 | @ | 2 | 14 | 1 | 280 | 20 |  | Residence | 20
5 | Sheet 61024 | Level 24 | FSM-AX-WR-L24-00162 | Garbage Room | Head of wall joint | 0.02 | 13 | @ | 2 | 14 | 1 | 364 | 20 |  | Residence | 26
6 | Sheet 61024 | Level 24 | FSM-AX-WR-L24-00162 | Passanger Lift lobby | Head of wall joint | 0.02 | 25 | @ | 2 | 14 | 1 | 700 | 20 |  | Residence | 50
7 | Sheet 61024 | Level 24 | FSM-AX-WR-L24-00162 | Water meter Rm | Head of wall joint | 0.02 | 12 | @ | 2 | 14 | 1 | 336 | 20 |  | Residence | 24
8 | Sheet 61024 | Level 24 | FSM-AX-WR-L24-00162 | Apartment, Shaft | Head of wall joint | 0.02 | 3.5 | @ | 2 | 14 | 3 | 294 | 20 |  | Residence | 21
9 | Sheet 61024 | Level 24 | FSM-AX-WR-L24-00162 | Apartment, Shaft | Head of wall joint | 0.02 | 5.1 | @ | 2 | 14 | 1 | 142.8 | 20 |  | Residence | 10.2
1 | Sheet 61032 | Level 06 | FSM-AX-WR-L6-00163 | Apart. no. 4A | Head of wall joint | 0.02 | 37 | @ | 2 | 14 | 1 | 1036 | 20 | Sheet 61032 | Residence | 74
2 | Sheet 61032 | Level 06 | FSM-AX-WR-L6-00163 | Apart. no. 4A | Head of wall joint | 0.02 | 3.5 | @ | 2 | 14 | 5 | 490 | 20 |  | Residence | 35
3 | Sheet 61032 | Level 06 | FSM-AX-WR-L6-00163 | Apart. no. 3B | Head of wall joint | 0.02 | 9 | @ | 2 | 14 | 1 | 252 | 20 |  | Residence | 18
4 | Sheet 61032 | Level 06 | FSM-AX-WR-L6-00163 | Apart. no. 3B | Head of wall joint | 0.02 | 2.45 | @ | 2 | 14 | 1 | 68.6 | 20 |  | Residence | 4.9
5 | Sheet 61032 | Level 06 | FSM-AX-WR-L6-00163 | Apart. no. 3B | Head of wall joint | 0.02 | 3.5 | @ | 2 | 14 | 2 | 196 | 20 |  | Residence | 14
6 | Sheet 61032 | Level 06 | FSM-AX-WR-L6-00163 | Apart. no. 2A | Head of wall joint | 0.02 | 3.5 | @ | 2 | 14 | 1 | 98 | 20 |  | Residence | 7
7 | Sheet 61032 | Level 06 | FSM-AX-WR-L6-00163 | Apart. no. 2A | Head of wall joint | 0.02 | 7.5 | @ | 2 | 14 | 1 | 210 | 20 |  | Residence | 15
8 | Sheet 61032 | Level 06 | FSM-AX-WR-L6-00163 | Apart. no. 2A | Head of wall joint | 0.02 | 10 | @ | 2 | 14 | 1 | 280 | 20 |  | Residence | 20
9 | Sheet 61032 | Level 06 | FSM-AX-WR-L6-00163 | Apart. no. 2A | Head of wall joint | 0.02 | 7.8 | @ | 2 | 14 | 1 | 218.4 | 20 |  | Residence | 15.6
10 | Sheet 61032 | Level 06 | FSM-AX-WR-L6-00163 | Corridor | Head of wall joint | 0.02 | 26 | @ | 2 | 14 | 1 | 728 | 20 |  | Residence | 52
11 | Sheet 61032 | Level 06 | FSM-AX-WR-L6-00163 | Corridor | Head of wall joint | 0.02 | 3.5 | @ | 2 | 14 | 1 | 98 | 20 |  | Residence | 7
12 | Sheet 61033 | Level 06 | FSM-AX-WR-L6-00163 | Garbage Room | Head of wall joint | 0.02 | 4 | @ | 2 | 14 | 1 | 112 | 20 | Sheet 61033 | Residence | 8
13 | Sheet 61033 | Level 06 | FSM-AX-WR-L6-00163 | Garbage Room | Head of wall joint | 0.02 | 3.5 | @ | 2 | 14 | 2 | 196 | 20 |  | Residence | 14
14 | Sheet 61033 | Level 06 | FSM-AX-WR-L6-00163 | Housekeeping | Head of wall joint | 0.02 | 3.5 | @ | 2 | 14 | 1 | 98 | 20 |  | Residence | 7
15 | Sheet 61033 | Level 06 | FSM-AX-WR-L6-00163 | Housekeeping | Head of wall joint | 0.02 | 3.5 | @ | 2 | 14 | 2 | 196 | 20 |  | Residence | 14
16 | Sheet 61033 | Level 06 | FSM-AX-WR-L6-00163 | Lift lobby | Head of wall joint | 0.02 | 4 | @ | 2 | 14 | 2 | 224 | 20 |  | Residence | 16
17 | Sheet 61033 | Level 06 | FSM-AX-WR-L6-00163 | Lift lobby | Head of wall joint | 0.02 | 2.5 | @ | 2 | 14 | 2 | 140 | 20 |  | Residence | 10
18 | Sheet 61033 | Level 06 | FSM-AX-WR-L6-00163 | FF Lobby | Head of wall joint | 0.02 | 8.5 | @ | 2 | 14 | 1 | 238 | 20 |  | Residence | 17
19 | Sheet 61033 | Level 06 | FSM-AX-WR-L6-00163 | Staircase 3&4 | Head of wall joint | 0.02 | 2.5 | @ | 2 | 14 | 2 | 140 | 20 |  | Residence | 10
20 | Sheet 61033 | Level 06 | FSM-AX-WR-L6-00163 | Staircase 3&4 | Head of wall joint | 0.02 | 3.5 | @ | 2 | 14 | 4 | 392 | 20 |  | Residence | 28
1 | Sheet 61041 | Level 04 | FSM-AX-WR-L4-00164 | FF Lobby | Head of wall joint | 0.02 | 9 | @ | 2 | 14 | 1 | 252 | 20 | Sheet 61041 | Residence | 18
2 | Sheet 61041 | Level 04 | FSM-AX-WR-L4-00164 | FF Lobby | Head of wall joint | 0.02 | 4 | @ | 2 | 14 | 2 | 224 | 20 |  | Residence | 16
3 | Sheet 61041 | Level 04 | FSM-AX-WR-L4-00164 | Chilled Room | Head of wall joint | 0.02 | 3 | @ | 2 | 14 | 1 | 84 | 20 |  | Residence | 6
4 | Sheet 61041 | Level 04 | FSM-AX-WR-L4-00164 | Chilled Room | Head of wall joint | 0.02 | 4 | @ | 2 | 14 | 2 | 224 | 20 |  | Residence | 16
5 | Sheet 61041 | Level 04 | FSM-AX-WR-L4-00164 | Passanger Lift lobby | Head of wall joint | 0.02 | 8.3 | @ | 2 | 14 | 2 | 464.8 | 20 |  | Residence | 33.2
6 | Sheet 61041 | Level 04 | FSM-AX-WR-L4-00164 | Passanger Lift lobby | Head of wall joint | 0.02 | 2.8 | @ | 2 | 14 | 4 | 313.6 | 20 |  | Residence | 22.4
7 | Sheet 61041 | Level 04 | FSM-AX-WR-L4-00164 | housekeeping | Head of wall joint | 0.02 | 5.5 | @ | 2 | 14 | 1 | 154 | 20 |  | Residence | 11
8 | Sheet 61041 | Level 04 | FSM-AX-WR-L4-00164 | housekeeping | Head of wall joint | 0.02 | 4 | @ | 2 | 14 | 1 | 112 | 20 |  | Residence | 8
9 | Sheet 61041 | Level 04 | FSM-AX-WR-L4-00164 | Garbage Room | Head of wall joint | 0.02 | 2.8 | @ | 2 | 14 | 1 | 78.4 | 20 |  | Residence | 5.6
10 | Sheet 61041 | Level 04 | FSM-AX-WR-L4-00164 | Garbage Room | Head of wall joint | 0.02 | 4 | @ | 2 | 14 | 1 | 112 | 20 |  | Residence | 8
11 | Sheet 61041 | Level 04 | FSM-AX-WR-L4-00164 | Staircase | Head of wall joint | 0.02 | 2.5 | @ | 2 | 14 | 2 | 140 | 20 |  | Residence | 10
12 | Sheet 61041 | Level 04 | FSM-AX-WR-L4-00164 | Staircase | Head of wall joint | 0.02 | 4 | @ | 2 | 14 | 4 | 448 | 20 |  | Residence | 32
1 | Sheet 61868 | Level 26 | FSM-AX-WR-L26-00167 | Lift Lobby | Head of wall joint | 0.02 | 9.8 | @ | 1 | 14 | 1 | 137.2 | 20 | Sheet 61868 | Hotel | 9.8
2 | Sheet 61868 | Level 26 | FSM-AX-WR-L26-00167 | Lift Lobby | Head of wall joint | 0.02 | 2.6 | @ | 1 | 14 | 4 | 145.6 | 20 |  | Hotel | 10.4
3 | Sheet 61868 | Level 26 | FSM-AX-WR-L26-00167 | Lift Lobby | Head of wall joint | 0.02 | 7.8 | @ | 1 | 14 | 1 | 109.2 | 20 |  | Hotel | 7.8
4 | Sheet 61868 | Level 26 | FSM-AX-WR-L26-00167 | Corridor | Head of wall joint | 0.02 | 112.7 | @ | 1 | 14 | 1 | 1577.8 | 20 |  | Hotel | 112.7
5 | Sheet 61868 | Level 26 | FSM-AX-WR-L26-00167 | Corridor | Head of wall joint | 0.02 | 3.2 | @ | 1 | 14 | 3 | 134.4 | 20 |  | Hotel | 9.6
1 | Sheet 61853 | Level 25 | FSM-AX-WR-L25-00166 | Lift Lobby | Head of wall joint | 0.02 | 9.8 | @ | 1 | 14 | 1 | 137.2 | 20 | Sheet 61853 | Hotel | 9.8
2 | Sheet 61853 | Level 25 | FSM-AX-WR-L25-00166 | Lift Lobby | Head of wall joint | 0.02 | 2.6 | @ | 1 | 14 | 4 | 145.6 | 20 |  | Hotel | 10.4
3 | Sheet 61853 | Level 25 | FSM-AX-WR-L25-00166 | Corridor | Head of wall joint | 0.02 | 127.5 | @ | 1 | 14 | 1 | 1785 | 20 |  | Hotel | 127.5
4 | Sheet 61853 | Level 25 | FSM-AX-WR-L25-00166 | Corridor | Head of wall joint | 0.02 | 3.2 | @ | 1 | 14 | 6 | 268.8 | 20 |  | Hotel | 19.2
1 | Sheet 61858 | Level 24 | FSM-AX-WR-L24-00165 | Lift Lobby | Head of wall joint | 0.02 | 9.8 | @ | 1 | 14 | 1 | 137.2 | 20 | Sheet 61858 | Hotel | 9.8
2 | Sheet 61858 | Level 24 | FSM-AX-WR-L24-00165 | Lift Lobby | Head of wall joint | 0.02 | 2.6 | @ | 1 | 14 | 4 | 145.6 | 20 |  | Hotel | 10.4
3 | Sheet 61858 | Level 24 | FSM-AX-WR-L24-00165 | Corridor | Head of wall joint | 0.02 | 7.8 | @ | 1 | 14 | 1 | 109.2 | 20 |  | Hotel | 7.8
4 | Sheet 61858 | Level 24 | FSM-AX-WR-L24-00165 | Corridor | Head of wall joint | 0.02 | 139 | @ | 1 | 14 | 1 | 1946 | 20 |  | Hotel | 139
[10 empty] | Cumulative Joints total |  | #REF!
1 | Sheet 61872 | Level 19 | WIR - 0168 | Corridor | Head of wall joint | 0.02 | 55.7 | @ | 1 | 14 | 1 | 779.8 | 20 | Sheet 61872 | Hotel | 55.7
2 | Sheet 61872 | Level 19 | WIR - 0168 | Corridor | Vertical joint | 0.02 | 3.3 | @ | 1 | 14 | 2 | 92.4 | 20 | Sheet 61872 | Hotel | 6.6
1 | Sheet 61883 | Level 27 | WIR - 0169 | Corridor | Head of wall joint | 0.02 | 122 | @ | 1 | 14 | 1 | 1708 | 20 | Sheet 61883 | Hotel | 122
2 | Sheet 61883 | Level 27 | WIR - 0169 | Corridor | Vertical joint | 0.02 | 3.5 | @ | 1 | 14 | 6 | 294 | 20 | Sheet 61883 | Hotel | 21
3 | Sheet 61883 | Level 27 | WIR - 0169 | Corridor | Head of wall joint | 0.02 | 7 | @ | 1 | 14 | 1 | 98 | 20 | Sheet 61883 | Hotel | 7
4 | Sheet 61883 | Level 27 | WIR - 0169 | Corridor | Vertical joint | 0.02 | 2.5 | @ | 1 | 14 | 4 | 140 | 20 | Sheet 61883 | Hotel | 10
1 | Sheet 61909 | Level 29 | WIR - 0172 | Electrical Room | Head of wall joint | 0.02 | 10.3 | @ | 2 | 14 | 1 | 288.4 | 20 | Sheet 61909 | Hotel | 20.6
2 | Sheet 61909 | Level 29 | WIR - 0172 | Electrical Room | Head of wall joint | 0.02 | 8.15 | @ | 2 | 14 | 1 | 228.2 | 20 |  | Hotel | 16.3
3 | Sheet 61909 | Level 29 | WIR - 0172 | Electrical Room | Vertical joint | 0.02 | 2.55 | @ | 1 | 14 | 1 | 35.7 | 20 |  | Hotel | 2.55
1 | Sheet 61913 | Ground Level | WIR - 0173 | Ball Room | Horizontal joint | 0.02 | 19.7 | @ | 1 | 14 | 1 | 275.8 | 20 | Sheet 61913 | Hotel | 19.7
2 | Sheet 61913 | Ground Level | WIR - 0173 | Ball Room | Vertical joint | 0.02 | 8 | @ | 1 | 14 | 2 | 224 | 20 |  | Hotel | 16
3 | Sheet 61913 | Ground Level | WIR - 0173 | Ball Room | Horizontal joint | 0.02 | 10.5 | @ | 1 | 14 | 1 | 147 | 20 |  | Hotel | 10.5
4 | Sheet 61913 | Ground Level | WIR - 0173 | Ball Room | Horizontal joint | 0.02 | 17 | @ | 1 | 14 | 1 | 238 | 20 |  | Hotel | 17
5 | Sheet 61913 | Ground Level | WIR - 0173 | Lobby | Horizontal joint | 0.02 | 16.8 | @ | 2 | 14 | 1 | 470.4 | 20 |  | Hotel | 33.6
6 | Sheet 61913 | Ground Level | WIR - 0173 | Lobby | Vertical joint | 0.02 | 3.5 | @ | 2 | 14 | 4 | 392 | 20 |  | Hotel | 28
7 | Sheet 61913 | Ground Level | WIR - 0173 | Lobby | Horizontal joint | 0.02 | 35.2 | @ | 1 | 14 | 1 | 492.8 | 20 |  | Hotel | 35.2
8 | Sheet 61913 | Ground Level | WIR - 0173 | Lobby | Vertical joint | 0.02 | 3.6 | @ | 1 | 14 | 6 | 302.4 | 20 |  | Hotel | 21.6
1 | Sheet 61914 | Level 01 | WIR - 0171 | Wall | Horizontal joint | 0.02 | 95 | @ | 1 | 14 | 1 | 1330 | 20 | Sheet 61914 | Hotel | 95
2 | Sheet 61914 | Level 01 | WIR - 0171 | Wall | Vertical joint | 0.02 | 4 | @ | 1 | 14 | 5 | 280 | 20 |  | Hotel | 20
3 | Sheet 61914 | Level 01 | WIR - 0171 | Wall | Vertical joint | 0.02 | 8 | @ | 1 | 14 | 3 | 336 | 20 |  | Hotel | 24
4 | Sheet 61914 | Level 01 | WIR - 0171 | Wall | Horizontal joint | 0.02 | 32 | @ | 1 | 14 | 1 | 448 | 20 |  | Hotel | 32
1 | Sheet 61924 | Level 23 | WIR - 00176 | Corridor | Head of wall joint | 0.02 | 50.5 | @ | 1 | 14 | 1 | 707 | 20 | Sheet 61924 | Hotel | 50.5
1 | Sheet 61929 | Level 22 | WIR - 00175 | Corridor | Head of wall joint | 0.02 | 55.5 | @ | 1 | 14 | 1 | 777 | 20 | Sheet 61929 | Hotel | 55.5
[10 empty] | Joints Total |  | #REF!
1 | Sheet 62263 | Level 17 | WIR - 00179 | Plant Room | Head of wall joint | 0.02 | 20.6 | @ | 2 | 14 | 1 | 576.8 | 20 | Sheet 62263 | Hotel | 41.2
2 | Sheet 62263 | Level 17 | WIR - 00179 | Plant Room | Vertical joint | 0.02 | 4.4 | @ | 2 | 14 | 1 | 123.2 | 20 |  | Hotel | 8.8
1 | Sheet 62258 | Level 19 | WIR - 00178 | Room no. 02 | Head of wall joint | 0.02 | 48.5 | @ | 1 | 14 | 1 | 679 | 20 | Sheet 62258 | Hotel | 48.5
1 | Sheet 62270 | Level 18 | WIR - 00181 | AHU Room | Head of wall joint | 0.02 | 7.5 | @ | 1 | 14 | 1 | 105 | 20 | Sheet 62270 | Hotel | 7.5
1 | Sheet 62255 | Level 21 | WIR - 00177 | Civil Work | Head of wall joint | 0.02 | 19.3 | @ | 1 | 14 | 1 | 270.2 | 20 | Sheet 62255 | Hotel | 19.3
1 | Sheet 62268 | Ground Level | WIR - 00180 | BOH 01 | Head of wall joint | 0.02 | 11.4 | @ | 2 | 14 | 1 | 319.2 | 20 | Sheet 62268 | Hotel | 22.8
2 | Sheet 62268 | Ground Level | WIR - 00180 | BOH 02 | Head of wall joint | 0.02 | 14.26 | @ | 2 | 14 | 1 | 399.28 | 20 |  | Hotel | 28.52
3 | Sheet 62268 | Ground Level | WIR - 00180 | BOH 03 | Head of wall joint | 0.02 | 14.2 | @ | 2 | 14 | 1 | 397.6 | 20 |  | Hotel | 28.4
4 | Sheet 62268 | Ground Level | WIR - 00180 | BOH 03 | Vertical joint | 0.02 | 4 | @ | 2 | 14 | 1 | 112 | 20 |  | Hotel | 8
5 | Sheet 62268 | Ground Level | WIR - 00180 | Female Toilet | Head of wall joint | 0.02 | 48.9 | @ | 2 | 14 | 1 | 1369.2 | 20 |  | Hotel | 97.8
6 | Sheet 62268 | Ground Level | WIR - 00180 | Female Toilet | Vertical joint | 0.02 | 3.6 | @ | 1 | 14 | 4 | 201.6 | 20 |  | Hotel | 14.4
1 | Sheet 62273 | Level 18 | WIR - 00182 | AHU for F-B- NX Rm | Head of wall joint | 0.02 | 38.4 | @ | 1 | 14 | 1 | 537.6 | 20 | Sheet 62273 | Hotel | 38.4
2 | Sheet 62273 | Level 18 | WIR - 00182 | AHU for F-B- NX Rm | Vertical joint | 0.02 | 4 | @ | 1 | 14 | 1 | 56 | 20 |  | Hotel | 4
1 | Sheet 62283 | Ground Level | WIR - 00192 | Food Storage Rm | Horizontal joint | 0.02 | 29.8 | @ | 1 | 14 | 1 | 417.2 | 20 | Sheet 62283 | Hotel | 29.8
2 | Sheet 62283 | Ground Level | WIR - 00192 | Food Storage Rm | Vertical joint | 0.02 | 2.2 | @ | 1 | 14 | 2 | 61.6 | 20 |  | Hotel | 4.4
3 | Sheet 62283 | Ground Level | WIR - 00192 | Window High | Horizontal joint | 0.02 | 18.9 | @ | 1 | 14 | 1 | 264.6 | 20 |  | Hotel | 18.9
4 | Sheet 62283 | Ground Level | WIR - 00192 | Kitchen | Horizontal joint | 0.02 | 27.5 | @ | 1 | 14 | 1 | 385 | 20 |  | Hotel | 27.5
5 | Sheet 62283 | Ground Level | WIR - 00192 | BOH Corridor | Horizontal joint | 0.02 | 24.2 | @ | 1 | 14 | 1 | 338.8 | 20 |  | Hotel | 24.2
6 | Sheet 62283 | Ground Level | WIR - 00192 | BOH Corridor | Vertical joint | 0.02 | 4 | @ | 1 | 14 | 4 | 224 | 20 |  | Hotel | 16
1 | Sheet 62277 | Level 29 | WIR - 00185 | Shaft | Horizontal joint | 0.02 | 5.4 | @ | 2 | 14 | 1 | 151.2 | 20 | Sheet 62277 | Residence | 10.8
2 | Sheet 62277 | Level 29 | WIR - 00185 | Shaft | Vertical joint | 0.02 | 4.6 | @ | 2 | 14 | 2 | 257.6 | 20 |  | Residence | 18.4
3 | Sheet 62277 | Level 29 | WIR - 00185 | Gas Shaft | Horizontal joint | 0.02 | 1.4 | @ | 2 | 14 | 1 | 39.2 | 20 |  | Residence | 2.8
4 | Sheet 62277 | Level 29 | WIR - 00185 | Gas Shaft | Vertical joint | 0.02 | 4.6 | @ | 2 | 14 | 2 | 257.6 | 20 |  | Residence | 18.4
5 | Sheet 62277 | Level 29 | WIR - 00185 | Wall | Horizontal joint | 0.02 | 29 | @ | 2 | 14 | 1 | 812 | 20 |  | Residence | 58
6 | Sheet 62277 | Level 29 | WIR - 00185 | Wall | Vertical joint | 0.02 | 4.6 | @ | 2 | 14 | 2 | 257.6 | 20 |  | Residence | 18.4
7 | Sheet 62277 | Level 29 | WIR - 00185 | Wall | Vertical joint | 0.02 | 2.3 | @ | 2 | 14 | 1 | 64.4 | 20 |  | Residence | 4.6
8 | Sheet 62277 | Level 29 | WIR - 00185 | Shaft | Horizontal joint | 0.02 | 3.4 | @ | 2 | 14 | 1 | 95.2 | 20 |  | Residence | 6.8
9 | Sheet 62277 | Level 29 | WIR - 00185 | Shaft | Horizontal joint | 0.02 | 3.4 | @ | 2 | 14 | 1 | 95.2 | 20 |  | Residence | 6.8
10 | Sheet 62277 | Level 29 | WIR - 00185 | Shaft | Horizontal joint | 0.02 | 3 | @ | 2 | 14 | 1 | 84 | 20 |  | Residence | 6
11 | Sheet 62277 | Level 29 | WIR - 00185 | Shaft | Vertical joint | 0.02 | 2 | @ | 2 | 14 | 1 | 56 | 20 |  | Residence | 4
12 | Sheet 62277 | Level 29 | WIR - 00185 | Housekeeping | Horizontal joint | 0.02 | 12.8 | @ | 2 | 14 | 1 | 358.4 | 20 |  | Residence | 25.6
13 | Sheet 62277 | Level 29 | WIR - 00185 | Housekeeping | Vertical joint | 0.02 | 4.6 | @ | 2 | 14 | 2 | 257.6 | 20 |  | Residence | 18.4
14 | Sheet 62277 | Level 29 | WIR - 00185 | Lift lobby | Horizontal joint | 0.02 | 15 | @ | 2 | 14 | 1 | 420 | 20 |  | Residence | 30
15 | Sheet 62277 | Level 29 | WIR - 00185 | Lift lobby | Vertical joint | 0.02 | 4 | @ | 2 | 14 | 4 | 448 | 20 |  | Residence | 32
16 | Sheet 62277 | Level 29 | WIR - 00185 | Corridor Entry Dr. | Horizontal joint | 0.02 | 2 | @ | 2 | 14 | 1 | 56 | 20 |  | Residence | 4
17 | Sheet 62277 | Level 29 | WIR - 00185 | Corridor Entry Dr. | Vertical joint | 0.02 | 2.3 | @ | 2 | 14 | 2 | 128.8 | 20 |  | Residence | 9.2
18 | Sheet 62277 | Level 29 | WIR - 00185 | Shaft | Horizontal joint | 0.02 | 2.65 | @ | 2 | 14 | 1 | 74.2 | 20 |  | Residence | 5.3
19 | Sheet 62277 | Level 29 | WIR - 00185 | FF Lobby | Horizontal joint | 0.02 | 8.1 | @ | 2 | 14 | 1 | 226.8 | 20 |  | Residence | 16.2
20 | Sheet 62277 | Level 29 | WIR - 00185 | FF Lobby | Vertical joint | 0.02 | 1.9 | @ | 2 | 14 | 2 | 106.4 | 20 |  | Residence | 7.6
1 | Sheet 62300 | Gorund Level | WIR - 00195/00196 | Male Toilet | Horizontal joint | 0.02 | 32 | @ | 2 | 14 | 1 | 896 | 20 | Sheet 62300 | Hotel | 64
2 | Sheet 62300 | Gorund Level | WIR - 00195/00196 | Male Toilet | Horizontal joint | 0.02 | 7 | @ | 1 | 14 | 1 | 98 | 20 |  | Hotel | 7
3 | Sheet 62300 | Gorund Level | WIR - 00195/00196 | Male Toilet | Vertical joint | 0.02 | 4 | @ | 2 | 14 | 2 | 224 | 20 |  | Hotel | 16
4 | Sheet 62300 | Gorund Level | WIR - 00195/00196 | Male Toilet | Vertical joint | 0.02 | 3.6 | @ | 1 | 14 | 1 | 50.4 | 20 |  | Hotel | 3.6
5 | Sheet 62300 | Gorund Level | WIR - 00195/00196 | Ball Room | Horizontal joint | 0.02 | 15.3 | @ | 2 | 14 | 1 | 428.4 | 20 |  | Hotel | 30.6
6 | Sheet 62300 | Gorund Level | WIR - 00195/00196 | Ball Room | Horizontal joint | 0.02 | 24 | @ | 2 | 14 | 1 | 672 | 20 |  | Hotel | 48
7 | Sheet 62300 | Gorund Level | WIR - 00195/00196 | Ball Room | Horizontal joint | 0.02 | 7 | @ | 1 | 14 | 1 | 98 | 20 |  | Hotel | 7
8 | Sheet 62300 | Gorund Level | WIR - 00195/00196 | Ball Room | Horizontal joint | 0.02 | 8 | @ | 2 | 14 | 1 | 224 | 20 |  | Hotel | 16
9 | Sheet 62300 | Gorund Level | WIR - 00195/00196 | Ball Room | Horizontal joint | 0.02 | 61.5 | @ | 2 | 14 | 1 | 1722 | 20 |  | Hotel | 123
10 | Sheet 62300 | Gorund Level | WIR - 00195/00196 | Lobby | Horizontal joint | 0.02 | 9.95 | @ | 2 | 14 | 1 | 278.6 | 20 |  | Hotel | 19.9
11 | Sheet 62300 | Gorund Level | WIR - 00195/00196 | Lobby | Vertical joint | 0.02 | 3.8 | @ | 2 | 14 | 3 | 319.2 | 20 |  | Hotel | 22.8
12 | Sheet 62300 | Gorund Level | WIR - 00195/00196 | Housekeeping | Horizontal joint | 0.02 | 13.7 | @ | 2 | 14 | 1 | 383.6 | 20 |  | Hotel | 27.4
13 | Sheet 62300 | Gorund Level | WIR - 00195/00196 | Housekeeping | Vertical joint | 0.02 | 3.6 | @ | 2 | 14 | 3 | 302.4 | 20 |  | Hotel | 21.6
1 | Sheet 61943 | Level 18 | WIR - 00197 | Fire Pump Room | Horizontal joint | 0.02 | 27.5 | @ | 1 | 14 | 1 | 385 | 20 | Sheet 61943 | Hotel | 27.5
2 | Sheet 61943 | Level 18 | WIR - 00197 | Fire Pump Room | Horizontal joint | 0.02 | 17.4 | @ | 2 | 14 | 1 | 487.2 | 20 |  | Hotel | 34.8
3 | Sheet 61943 | Level 18 | WIR - 00197 | Corridor | Horizontal joint | 0.02 | 11.2 | @ | 1 | 14 | 1 | 156.8 | 20 |  | Hotel | 11.2
4 | Sheet 61943 | Level 18 | WIR - 00197 | Corridor | Vertical joint | 0.02 | 4 | @ | 1 | 14 | 2 | 112 | 20 |  | Hotel | 8
5 | Sheet 61943 | Level 18 | WIR - 00197 | Housekeeping | Horizontal joint | 0.02 | 15.5 | @ | 2 | 14 | 1 | 434 | 20 |  | Hotel | 31
6 | Sheet 61943 | Level 18 | WIR - 00197 | Housekeeping | Vertical joint | 0.02 | 4.5 | @ | 2 | 14 | 4 | 504 | 20 |  | Hotel | 36
7 | Sheet 61943 | Level 18 | WIR - 00197 | Lift Lobby | Horizontal joint | 0.02 | 15.4 | @ | 2 | 14 | 1 | 431.2 | 20 |  | Hotel | 30.8
8 | Sheet 61943 | Level 18 | WIR - 00197 | Lift Lobby | Vertical joint | 0.02 | 4.6 | @ | 2 | 14 | 4 | 515.2 | 20 |  | Hotel | 36.8
9 | Sheet 61943 | Level 18 | WIR - 00197 | Room Service | Horizontal joint | 0.02 | 7.6 | @ | 2 | 14 | 1 | 212.8 | 20 |  | Hotel | 15.2
10 | Sheet 61943 | Level 18 | WIR - 00197 | Room Service | Vertical joint | 0.02 | 2.4 | @ | 2 | 14 | 2 | 134.4 | 20 |  | Hotel | 9.6
11 | Sheet 61943 | Level 18 | WIR - 00197 | FF lobby | Horizontal joint | 0.02 | 1.65 | @ | 2 | 14 | 1 | 46.2 | 20 |  | Hotel | 3.3
12 | Sheet 61943 | Level 18 | WIR - 00197 | FF lobby | Vertical joint | 0.02 | 5.4 | @ | 2 | 14 | 2 | 302.4 | 20 |  | Hotel | 21.6
1 | Sheet 62299 | Level 01 | WIR - 00193 | Lift Lobby | Horizontal joint | 0.02 | 8.5 | @ | 1 | 14 | 1 | 119 | 20 | Sheet 62299 | Hotel | 8.5
2 | Sheet 62299 | Level 01 | WIR - 00193 | Equpment Room | Horizontal joint | 0.02 | 12.6 | @ | 2 | 14 | 1 | 352.8 | 20 |  | Hotel | 25.2
3 | Sheet 62299 | Level 01 | WIR - 00193 | Equpment Room | Horizontal joint | 0.02 | 26.2 | @ | 1 | 14 | 1 | 366.8 | 20 |  | Hotel | 26.2
1 | Sheet 62323 | Level 23 | WIR - 00203/00199 | Housekeeping | Horizontal joint | 0.02 | 11.4 | @ | 2 | 14 | 1 | 319.2 | 20 | Sheet 62323 | Residence | 22.8
2 | Sheet 62323 | Level 23 | WIR - 00203/00199 | Housekeeping | Vertical joint | 0.02 | 4 | @ | 2 | 14 | 3 | 336 | 20 |  | Residence | 24
3 | Sheet 62323 | Level 23 | WIR - 00203/00199 | Meeting Room | Horizontal joint | 0.02 | 1.5 | @ | 2 | 14 | 1 | 42 | 20 |  | Residence | 3
4 | Sheet 62323 | Level 23 | WIR - 00203/00199 | Pantry Room | Horizontal joint | 0.02 | 4 | @ | 2 | 14 | 2 | 224 | 20 |  | Residence | 16
5 | Sheet 62323 | Level 23 | WIR - 00203/00199 | Lobby | Vertical joint | 0.02 | 9 | @ | 2 | 14 | 1 | 252 | 20 |  | Residence | 18
6 | Sheet 62323 | Level 23 | WIR - 00203/00199 | Corridor | Horizontal joint | 0.02 | 10.7 | @ | 1 | 14 | 1 | 149.8 | 20 |  | Residence | 10.7
7 | Sheet 62323 | Level 23 | WIR - 00203/00199 | Pump Room | Horizontal joint | 0.02 | 20.2 | @ | 1 | 14 | 1 | 282.8 | 20 |  | Residence | 20.2
1 | Sheet 62322 | Level 01 | WIR - 00202 | Female Prayer Rm | Horizontal joint | 0.02 | 26.7 | @ | 1 | 14 | 1 | 373.8 | 20 | Sheet 62322 | Hotel | 26.7
2 | Sheet 62322 | Level 01 | WIR - 00202 | Female Prayer Rm | Vertical joint | 0.02 | 3.02 | @ | 2 | 14 | 1 | 84.56 | 20 |  | Hotel | 6.04
3 | Sheet 62322 | Level 01 | WIR - 00202 | Male Prayer Rm | Horizontal joint | 0.02 | 38.6 | @ | 1 | 14 | 1 | 540.4 | 20 |  | Hotel | 38.6
4 | Sheet 62322 | Level 01 | WIR - 00202 | Housekeeping | Horizontal joint | 0.02 | 16.2 | @ | 1 | 14 | 1 | 226.8 | 20 |  | Hotel | 16.2
5 | Sheet 62322 | Level 01 | WIR - 00202 | Housekeeping | Vertical joint | 0.02 | 3.7 | @ | 2 | 14 | 2 | 207.2 | 20 |  | Hotel | 14.8
6 | Sheet 62322 | Level 01 | WIR - 00202 | FF Lobby | Horizontal joint | 0.02 | 2 | @ | 2 | 14 | 1 | 56 | 20 |  | Hotel | 4
7 | Sheet 62322 | Level 01 | WIR - 00202 | FF Lobby | Vertical joint | 0.02 | 3.7 | @ | 2 | 14 | 2 | 207.2 | 20 |  | Hotel | 14.8
8 | Sheet 62322 | Level 01 | WIR - 00202 | Entry door | Horizontal joint | 0.02 | 3.65 | @ | 2 | 14 | 1 | 102.2 | 20 |  | Hotel | 7.3
9 | Sheet 62322 | Level 01 | WIR - 00202 | Entry door | Vertical joint | 0.02 | 3.6 | @ | 2 | 14 | 1 | 100.8 | 20 |  | Hotel | 7.2
10 | Sheet 62322 | Level 01 | WIR - 00202 | Plant Room | Horizontal joint | 0.02 | 12.3 | @ | 2 | 14 | 1 | 344.4 | 20 |  | Hotel | 24.6
11 | Sheet 62322 | Level 01 | WIR - 00202 | Plant Room | Vertical joint | 0.02 | 3.6 | @ | 2 | 14 | 1 | 100.8 | 20 |  | Hotel | 7.2
12 | Sheet 62322 | Level 01 | WIR - 00202 | Plant Room | Horizontal joint | 0.02 | 11.3 | @ | 1 | 14 | 1 | 158.2 | 20 |  | Hotel | 11.3
13 | Sheet 62322 | Level 01 | WIR - 00202 | Lobby | Horizontal joint | 0.02 | 11.2 | @ | 1 | 14 | 1 | 156.8 | 20 |  | Hotel | 11.2
14 | Sheet 62322 | Level 01 | WIR - 00202 | Corridor | Horizontal joint | 0.02 | 40.8 | @ | 1 | 14 | 1 | 571.2 | 20 |  | Hotel | 40.8
1 | Sheet 62328 | Level 12 | WIR - 00207 | Room Service | Head of Wall joint | 0.02 | 3.2 | @ | 1 | 14 | 1 | 44.8 | 20 | Sheet 62328 | Hotel | 3.2
2 | Sheet 62328 | Level 07 | WIR - 00207 | Room Service | Head of Wall joint | 0.02 | 3.2 | @ | 1 | 14 | 1 | 44.8 | 20 |  | Hotel | 3.2
3 | Sheet 62328 | Level 08 | WIR - 00207 | Room Service | Head of Wall joint | 0.02 | 3 | @ | 1 | 14 | 1 | 42 | 20 |  | Hotel | 3
1 | Sheet 61946 | Level 23 | WIR - 00201 | Corridor, Entry Dr | Head of Wall joint | 0.02 | 2.25 | @ | 2 | 14 | 1 | 63 | 20 | Sheet 61946 | Hotel | 4.5
2 | Sheet 61946 | Level 23 | WIR - 00201 | Corridor, Entry Dr | Head of Wall joint | 0.02 | 0.9 | @ | 2 | 14 | 2 | 50.4 | 20 |  | Hotel | 3.6
1 | Sheet 62319 | Level 26 | WIR - 00206 | Room no. 05 | Head of Wall joint | 0.02 | 13.2 | @ | 1 | 14 | 1 | 184.8 | 20 | Sheet 62319 | Hotel | 13.2
1 | Sheet 62321 | Level 09 | WIR - 00204 | Room Service | Head of Wall joint | 0.02 | 3.8 | @ | 1 | 14 | 1 | 53.2 | 20 | Sheet 62321 | Hotel | 3.8
1 | Sheet 62317 | Level 28 | WIR - 00205 | Civil work | Head of Wall joint | 0.02 | 37.7 | @ | 1 | 14 | 1 | 527.8 | 20 | Sheet 62317 | Hotel | 37.7
2 | Sheet 62317 | Level 28 | WIR - 00205 | Civil work | Head of Wall joint | 0.02 | 5.5 | @ | 1 | 14 | 1 | 77 | 20 |  | Hotel | 5.5
[10 empty] | Grand Total |  | #REF! |  |  | Total qty | 4287.11

## Joints 30mm
Project: |  |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  |  | Khansaheb Civil Engineering
Period of Completed Works: |  |  |  | up to July 2022
Summary of Completed Firestopping Works (Construction Joints)
No. | Sos Number | Level | WIR No. | Location | Type | Joint Size (in meter) |  |  | Sides | Rate (AED) | Nos | Total (AED) |  |  | Hotel / Residence | QTY | Remarks
1 | Sheet 61862 | Basement 01 | FSM-AX-WR-LB1-00170 | CEF Room | Head of wall joint | 0.03 | 20 | @ | 1 | 20 | 1 | 400 | 30 | Sheet 61862 | Residence | 20
2 | Sheet 61862 | Basement 01 | FSM-AX-WR-LB1-00170 | CEF Room | Head of wall joint | 0.03 | 6.5 | @ | 1 | 20 | 2 | 260 | 30 |  | Residence | 13
3 | Sheet 61862 | Basement 01 | FSM-AX-WR-LB1-00170 | Electrical Cabinet | Head of wall joint | 0.03 | 3 | @ | 2 | 20 | 1 | 120 | 30 |  | Residence | 6
[10 empty] | Grand Total |  | 780 |  |  | Total qty | 39

## FF 2"
Project: |  |  |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  |  |  | Khansaheb Civil Engineering
Period of Completed Works: |  |  |  |  | up to July 2022
Summary of Completed Firestopping Works
No. | Sos Number | Serial No | Level | WIR No. | Location | Penetrant Type | Penetrant Size (in meter) | SquareMeters | Opening Size (in meter) | SquareMeters | Diffirence | Sides | Rate (AED) | Nos | Total (AED) |  |  | Hotel / Residence | QTY
32 | Sheet 61871 | 2 | Level 19 | WIR - 0168 | Outer sleeve | fire fighting pipe | 2" | 0.0019625 |  |  |  | 1 | 14 | 1 | 14 |  |  | Hotel | 1
36 | Sheet 61871 | 4 | Level 19 | WIR - 0168 | Outer sleeve | fire fighting pipe | 2" |  | 4" |  |  | 1 | 14 | 1 | 14 |  |  | Hotel | 1
37 | Sheet 61871 | 5 | Level 19 | WIR - 0168 | Outer sleeve | fire fighting pipe | 2" |  | 4" |  |  | 1 | 14 | 1 | 14 |  |  | Hotel | 1
42 | Sheet 61871 | 10 | Level 19 | WIR - 0168 | Outer sleeve | fire fighting pipe | 2" |  | 4" |  |  | 1 | 14 | 1 | 14 |  |  | Hotel | 1
34 | Sheet 61884 | 2 | Level 27 | WIR - 0169 | Outer sleeve | fire fighting pipe | 2" |  | 4" |  |  | 1 | 14 | 1 | 14 |  |  | Hotel | 1
100 | Sheet 61886 | 68 | Level 27 | WIR - 0169 | Outer sleeve | fire fighting pipe | 2" |  | 4" |  |  | 1 | 14 | 1 | 14 |  |  | Hotel | 1
103 | Sheet 61886 | 71 | Level 27 | WIR - 0169 | Outer sleeve | fire fighting pipe | 2" |  | 4" |  |  | 1 | 14 | 1 | 14 |  |  | Hotel | 1
111 | Sheet 61886 | 79 | Level 27 | WIR - 0169 | Outer sleeve | fire fighting pipe | 2" |  | 4" |  |  | 1 | 14 | 1 | 14 |  |  | Hotel | 1
2 | Sheet 62267 | 2 | Ground Level | WIR - 00180 | BOH 01 | fire fighting pipe | 2" |  | 4" |  |  | 2 | 14 | 1 | 28 |  |  | Hotel | 2
3 | Sheet 62267 | 3 | Ground Level | WIR - 00180 | BOH 02 | fire fighting pipe | 2" |  | 4" |  |  | 2 | 14 | 3 | 84 |  |  | Hotel | 6
8 | Sheet 62267 | 8 | Ground Level | WIR - 00180 | Female Toilet | fire fighting pipe | 2" |  | 4" |  |  | 2 | 14 | 2 | 56 |  |  | Hotel | 4
12 | Sheet 62267 | 12 | Ground Level | WIR - 00180 | Female Toilet | fire fighting pipe | 2" |  | 4" |  |  | 2 | 14 | 2 | 56 |  |  | Hotel | 4
19 | Sheet 62267 | 19 | Ground Level | WIR - 00180 | Female Toilet | fire fighting pipe | 2" |  | 4" |  |  | 2 | 14 | 3 | 84 |  |  | Hotel | 6
11 | Sheet 62256 | 9 | Level 21 | WIR - 00177 | Room Entry Door | fire fighting pipe | 1" | 0.00049063 |  |  |  | 2 | 14 | 1 | 28 |  |  | Hotel | 2
16 | Sheet 62256 | 13 | Level 21 | WIR - 00177 | Room Entry Door | fire fighting pipe | 1" | 0.00049063 |  |  |  | 2 | 14 | 1 | 28 |  |  | Hotel | 2
19 | Sheet 62256 | 15 | Level 21 | WIR - 00177 | Room Entry Door | fire fighting pipe | 2" |  | 4" |  |  | 2 | 14 | 1 | 28 |  |  | Hotel | 2
25 | Sheet 62256 | 21 | Level 21 | WIR - 00177 | Room Wall | fire fighting pipe | 2" |  | 4" |  |  | 1 | 14 | 1 | 14 |  |  | Hotel | 1
1 | Sheet 61937 | 1 | Ground Level | WIR - 0194 | Male Toilet | fire fighting pipe | 2" |  | 4" |  |  | 2 | 14 | 2 | 56 | FS702 | Sheet 61937 | Hotel | 4
20 | Sheet 61937 | 20 | Ground Level | WIR - 0194 | Ball Room | fire fighting pipe | 2" |  | 4" |  |  | 2 | 14 | 1 | 28 | FS702 |  | Hotel | 2
21 | Sheet 61937 | 21 | Ground Level | WIR - 0194 | Ball Room | fire fighting pipe | 2" |  | 4" |  |  | 2 | 14 | 3 | 84 | FS702 |  | Hotel | 6
3 | Sheet 61938 | 28 | Ground Level | WIR - 0194 | Ball Room | fire fighting pipe | 2" |  | 4" |  |  | 2 | 14 | 2 | 56 | FS702 |  | Hotel | 4
15 | Sheet 61938 | 40 | Ground Level | WIR - 0194 | Ball Room | fire fighting pipe | 2" |  | 4" |  |  | 2 | 14 | 1 | 28 | FS702 |  | Hotel | 2
5 | Sheet 62328 |  | Level 12 | WIR - 00207 | Room Service | fire fighting pipe | 2" |  | 4" |  |  | 1 | 14 | 1 | 14 | FS702 | Sheet 62328 | Hotel | 1
12 | Sheet 62328 |  | Level 08 | WIR - 00207 | Room Service | fire fighting pipe | 2" |  | 4" |  |  | 1 | 14 | 1 | 14 | FS702 | Sheet 62328 | Hotel | 1
21 | Sheet 62328 |  | Level 07 | WIR - 00207 | Room Service | fire fighting pipe | 2" |  | 4" |  |  | 1 | 14 | 1 | 14 | FS702 | Sheet 62328 | Hotel | 1
8 | Sheet 62321 |  | Level 09 | WIR - 00204 | Room Service | fire fighting pipe | 2" |  | 4" |  |  | 1 | 14 | 1 | 14 | FS702 | Sheet 62321 | Hotel | 1
[13 empty] | Grand Total |  | 826 |  |  | Total qty | 59

## FF 3"
Project: |  |  |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  |  |  | Khansaheb Civil Engineering
Period of Completed Works: |  |  |  |  | up to July 2022
Summary of Completed Firestopping Works
No. | Sos Number | Serial No | Level | WIR No. | Location | Penetrant Type | Penetrant Size (in meter) | SquareMeters | Opening Size (in meter) | SquareMeters | Diffirence | Sides | Rate (AED) | Nos | Total (AED) |  |  | Hotel / Residence | QTY
39 | Sheet 61871 | 7 | Level 19 | WIR - 0168 | Outer sleeve | fire fighting pipe | 3" |  | 5" |  |  | 1 | 16 | 1 | 16 |  |  | Hotel | 1
44 | Sheet 61871 | 12 | Level 19 | WIR - 0168 | Outer sleeve | fire fighting pipe | 3" |  | 5" |  |  | 1 | 16 | 1 | 16 |  |  | Hotel | 1
35 | Sheet 61884 | 3 | Level 27 | WIR - 0169 | Outer sleeve | fire fighting pipe | 3" |  | 5" |  |  | 1 | 16 | 1 | 16 |  |  | Hotel | 1
40 | Sheet 61884 | 8 | Level 27 | WIR - 0169 | Outer sleeve | fire fighting pipe | 3" |  | 5" |  |  | 1 | 16 | 1 | 16 |  |  | Hotel | 1
42 | Sheet 61884 | 10 | Level 27 | WIR - 0169 | Outer sleeve | fire fighting pipe | 3" |  | 5" |  |  | 1 | 16 | 1 | 16 |  |  | Hotel | 1
49 | Sheet 61884 | 17 | Level 27 | WIR - 0169 | Outer sleeve | fire fighting pipe | 3" |  | 5" |  |  | 1 | 16 | 1 | 16 |  |  | Hotel | 1
55 | Sheet 61884 | 23 | Level 27 | WIR - 0169 | Outer sleeve | fire fighting pipe | 3" |  | 5" |  |  | 1 | 16 | 1 | 16 |  |  | Hotel | 1
56 | Sheet 61884 | 24 | Level 27 | WIR - 0169 | Outer sleeve | fire fighting pipe | 3" |  | 5" |  |  | 1 | 16 | 1 | 16 |  |  | Hotel | 1
58 | Sheet 61884 | 26 | Level 27 | WIR - 0169 | Outer sleeve | fire fighting pipe | 3" |  | 5" |  |  | 1 | 16 | 1 | 16 |  |  | Hotel | 1
64 | Sheet 61885 | 32 | Level 27 | WIR - 0169 | Outer sleeve | fire fighting pipe | 3" |  | 5" |  |  | 1 | 16 | 1 | 16 |  |  | Hotel | 1
65 | Sheet 61885 | 33 | Level 27 | WIR - 0169 | Outer sleeve | fire fighting pipe | 3" |  | 5" |  |  | 1 | 16 | 1 | 16 |  |  | Hotel | 1
68 | Sheet 61885 | 36 | Level 27 | WIR - 0169 | Outer sleeve | fire fighting pipe | 3" |  | 5" |  |  | 1 | 16 | 1 | 16 |  |  | Hotel | 1
69 | Sheet 61885 | 37 | Level 27 | WIR - 0169 | Outer sleeve | fire fighting pipe | 3" |  | 5" |  |  | 1 | 16 | 1 | 16 |  |  | Hotel | 1
74 | Sheet 61885 | 42 | Level 27 | WIR - 0169 | Outer sleeve | fire fighting pipe | 3" |  | 5" |  |  | 2 | 16 | 1 | 32 |  |  | Hotel | 2
76 | Sheet 61885 | 44 | Level 27 | WIR - 0169 | Outer sleeve | fire fighting pipe | 3" |  | 5" |  |  | 1 | 16 | 1 | 16 |  |  | Hotel | 1
80 | Sheet 61885 | 48 | Level 27 | WIR - 0169 | Outer sleeve | fire fighting pipe | 3" |  | 5" |  |  | 1 | 16 | 1 | 16 |  |  | Hotel | 1
83 | Sheet 61885 | 51 | Level 27 | WIR - 0169 | Outer sleeve | fire fighting pipe | 3" |  | 5" |  |  | 1 | 16 | 1 | 16 |  |  | Hotel | 1
92 | Sheet 61886 | 60 | Level 27 | WIR - 0169 | Outer sleeve | fire fighting pipe | 3" |  | 5" |  |  | 1 | 16 | 1 | 16 |  |  | Hotel | 1
1 | Sheet 62267 | 1 | Ground Level | WIR - 00180 | BOH 01 | fire fighting pipe | 3" |  | 5" |  |  | 2 | 16 | 2 | 64 |  | Sheet 62267 | Hotel | 4
9 | Sheet 62267 | 9 | Ground Level | WIR - 00180 | Female Toilet | fire fighting pipe | 3" |  | 5" |  |  | 2 | 16 | 3 | 96 |  |  | Hotel | 6
3 | Sheet 62256 | 3 | Level 21 | WIR - 00177 | Entry Door | fire fighting pipe | 3" |  | 5" |  |  | 2 | 16 | 1 | 32 |  |  | Hotel | 2
27 | Sheet 62256 | 23 | Level 21 | WIR - 00177 | Corridor | fire fighting pipe | 3" |  | 5" |  |  | 2 | 16 | 1 | 32 |  |  | Hotel | 2
9 | Sheet 62260 | 6 | Level 19 | WIR - 00178 | Outer Sleeve | fire fighting pipe | 3" |  | 5" |  |  | 1 | 16 | 1 | 16 |  |  | Hotel | 1
5 | Sheet 61937 | 5 | Ground Level | WIR - 0194 | Male Toilet | fire fighting pipe | 3" |  | 5" |  |  | 2 | 16 | 1 | 32 | FS702 |  | Hotel | 2
10 | Sheet 61937 | 10 | Ground Level | WIR - 0194 | Male Toilet | fire fighting pipe | 3" |  | 5" |  |  | 2 | 16 | 1 | 32 | FS702 |  | Hotel | 2
24 | Sheet 61937 | 24 | Ground Level | WIR - 0194 | Ball Room | fire fighting pipe | 3" |  | 5" |  |  | 2 | 16 | 1 | 32 | FS702 |  | Hotel | 2
11 | Sheet 61938 | 36 | Ground Level | WIR - 0194 | Ball Room | fire fighting pipe | 3" |  | 5" |  |  | 2 | 16 | 1 | 32 | FS702 |  | Hotel | 2
14 | Sheet 62328 |  | Level 08 | WIR - 00207 | Room Service | fire fighting pipe | 3" |  | 5" |  |  | 1 | 16 | 1 | 16 | FS702 | Sheet 62328 | Hotel | 1
4 | Sheet 62319 |  | Level 26 | WIR - 00206 | Room no. 05 | fire fighting pipe | 3" |  | 5" |  |  | 1 | 16 | 1 | 16 | FS702 | Sheet 62319 | Hotel | 1
5 | Sheet 62317 |  | Level 28 | WIR - 00205 | Outer Sleeve | fire fighting pipe | 3" |  | 5" |  |  | 2 | 16 | 6 | 192 | FS702 | Sheet 62317 | Hotel | 12
[13 empty] | Grand Total |  | 896 |  |  | Total qty | 56

## FF 4"
Project: |  |  |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  |  |  | Khansaheb Civil Engineering
Period of Completed Works: |  |  |  |  | up to July 2022
Summary of Completed Firestopping Works
No. | Sos Number | Serial No | Level | WIR No. | Location | Penetrant Type | Penetrant Size (in meter) | SquareMeters | Opening Size (in meter) | SquareMeters | Diffirence | Sides | Rate (AED) | Nos | Total (AED) |  |  | Hotel / Residence | QTY
22 | Sheet 61937 | 22 | Ground Level | WIR - 0194 | Ball Room | fire fighting pipe | 4" |  | 6" |  |  | 2 | 21 | 1 | 42 | FS702 |  | Hotel | 2
5 | Sheet 61938 | 30 | Ground Level | WIR - 0194 | Ball Room | fire fighting pipe | 4" |  | 6" |  |  | 2 | 21 | 1 | 42 | FS702 |  | Hotel | 2
14 | Sheet 61938 | 39 | Ground Level | WIR - 0194 | Ball Room | fire fighting pipe | 4" |  | 6" |  |  | 2 | 21 | 2 | 84 | FS702 |  | Hotel | 4
1 | Sheet 62328 |  | Level 08 | WIR - 00207 | Room Service | fire fighting pipe | 4" |  | 6" |  |  | 1 | 21 | 1 | 21 | FS702 | Sheet 62328 | Hotel | 1
[13 empty] | Grand Total |  | 189 |  |  | Total qty | 9

## FF 6"
Project: |  |  |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  |  |  | Khansaheb Civil Engineering
Period of Completed Works: |  |  |  |  | up to July 2022
Summary of Completed Firestopping Works
No. | Sos Number | Serial No | Level | WIR No. | Location | Penetrant Type | Penetrant Size (in meter) | SquareMeters | Opening Size (in meter) | SquareMeters | Diffirence | Sides | Rate (AED) | Nos | Total (AED) |  |  | Hotel / Residence | QTY
1 | Sheet 62267 | 4 | Ground Level | WIR - 00180 | BOH 02 | fire fighting pipe | 5" |  | 7" |  |  | 2 | 27 | 1 | 54 |  |  | Hotel | 2
1 | Sheet 61938 | 38 | Ground Level | WIR - 0194 | Ball Room | fire fighting pipe | 6" |  | 8" |  |  | 2 | 27 | 2 | 108 | FS702 |  | Hotel | 4
4 | Sheet 62328 |  | Level 12 | WIR - 00207 | Room Service | fire fighting pipe | 5" |  | 7" |  |  | 1 | 27 | 1 | 27 | FS702 | Sheet 62328 | Hotel | 1
11 | Sheet 62328 |  | Level 08 | WIR - 00207 | Room Service | fire fighting pipe | 5" |  | 7" |  |  | 1 | 27 | 1 | 27 | FS702 | Sheet 62328 | Hotel | 1
20 | Sheet 62328 |  | Level 07 | WIR - 00207 | Room Service | fire fighting pipe | 5" |  | 7" |  |  | 1 | 27 | 1 | 27 | FS702 | Sheet 62328 | Hotel | 1
6 | Sheet 62321 |  | Level 09 | WIR - 00204 | Room Service | fire fighting pipe | 6" |  | 8" |  |  | 1 | 27 | 1 | 27 | FS702 | Sheet 62321 | Hotel | 1
7 | Sheet 62321 |  | Level 09 | WIR - 00204 | Room Service | fire fighting pipe | 5" |  | 7" |  |  | 1 | 27 | 1 | 27 | FS702 | Sheet 62321 | Hotel | 1
7 | Sheet 62317 |  | Level 28 | WIR - 00205 | Outer Sleeve | fire fighting pipe | 5" |  | 7" |  |  | 2 | 27 | 2 | 108 | FS702 | Sheet 62317 | Hotel | 4
[13 empty] | Grand Total |  | 405 |  |  | Total qty | 15

## FF 8"
Project: |  |  |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  |  |  | Khansaheb Civil Engineering
Period of Completed Works: |  |  |  |  | up to July 2022
Summary of Completed Firestopping Works
No. | Sos Number | Serial No | Level | WIR No. | Location | Penetrant Type | Penetrant Size (in meter) | SquareMeters | Opening Size (in meter) | SquareMeters | Diffirence | Sides | Rate (AED) | Nos | Total (AED) |  |  | Hotel / Residence | QTY
1 | Sheet 61937 | 16 | Ground Level | WIR - 0194 | Male Toilet | fire fighting pipe | 8" |  | 10" |  |  | 2 | 46 | 1 | 92 | FS702 |  | Hotel | 2
3 | Sheet 62328 |  | Level 12 | WIR - 00207 | Room Service | fire fighting pipe | 8" |  | 10" |  |  | 1 | 46 | 1 | 46 | FS702 | Sheet 62328 | Hotel | 1
10 | Sheet 62328 |  | Level 08 | WIR - 00207 | Room Service | fire fighting pipe | 8" |  | 10" |  |  | 1 | 46 | 1 | 46 | FS702 | Sheet 62328 | Hotel | 1
19 | Sheet 62328 |  | Level 07 | WIR - 00207 | Room Service | fire fighting pipe | 8" |  | 10" |  |  | 1 | 46 | 1 | 46 | FS702 | Sheet 62328 | Hotel | 1
[13 empty] | Grand Total |  | 230 |  |  | Total qty | 5

## CHW 3"
Project: |  |  |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  |  |  | Khansaheb Civil Engineering
Period of Completed Works: |  |  |  |  | up to July 2022
Summary of Completed Firestopping Works
No. | Sos Number | Serial No | Level | WIR No. | Location | Penetrant Type | Penetrant Size (in meter) | SquareMeters | Opening Size (in meter) | SquareMeters | Diffirence | Sides | Rate (AED) | Nos | Total (AED) | Hotel / Residence | QTY
40 | Sheet 61871 | 8 | Level 19 | WIR - 0168 | Outer sleeve | CHW pipe | 3" |  | 5" |  |  | 1 | 23 | 2 | 46 | Hotel | 2
43 | Sheet 61871 | 11 | Level 19 | WIR - 0168 | Outer sleeve | CHW pipe | 3" |  | 5" |  |  | 1 | 23 | 1 | 23 | Hotel | 1
43 | Sheet 61884 | 11 | Level 27 | WIR - 0169 | Outer sleeve | CHW pipe | 3" |  | 5" |  |  | 1 | 23 | 2 | 46 | Hotel | 2
46 | Sheet 61884 | 14 | Level 27 | WIR - 0169 | Outer sleeve | CHW pipe | 3" |  | 5" |  |  | 1 | 23 | 2 | 46 | Hotel | 2
48 | Sheet 61884 | 16 | Level 27 | WIR - 0169 | Outer sleeve | CHW pipe | 3" |  | 5" |  |  | 1 | 23 | 2 | 46 | Hotel | 2
51 | Sheet 61884 | 19 | Level 27 | WIR - 0169 | Outer sleeve | CHW pipe | 3" |  | 5" |  |  | 1 | 23 | 2 | 46 | Hotel | 2
54 | Sheet 61884 | 22 | Level 27 | WIR - 0169 | Outer sleeve | CHW pipe | 3" |  | 5" |  |  | 1 | 23 | 2 | 46 | Hotel | 2
59 | Sheet 61884 | 27 | Level 27 | WIR - 0169 | Outer sleeve | CHW pipe | 3" |  | 5" |  |  | 1 | 23 | 2 | 46 | Hotel | 2
61 | Sheet 61885 | 29 | Level 27 | WIR - 0169 | Outer sleeve | CHW pipe | 3" |  | 5" |  |  | 1 | 23 | 2 | 46 | Hotel | 2
62 | Sheet 61885 | 30 | Level 27 | WIR - 0169 | Outer sleeve | CHW pipe | 3" |  | 5" |  |  | 1 | 23 | 2 | 46 | Hotel | 2
82 | Sheet 61885 | 50 | Level 27 | WIR - 0169 | Outer sleeve | CHW pipe | 3" |  | 5" |  |  | 1 | 23 | 2 | 46 | Hotel | 2
85 | Sheet 61886 | 53 | Level 27 | WIR - 0169 | Outer sleeve | CHW pipe | 3" |  | 5" |  |  | 1 | 23 | 2 | 46 | Hotel | 2
90 | Sheet 61886 | 58 | Level 27 | WIR - 0169 | Outer sleeve | CHW pipe | 3" |  | 5" |  |  | 1 | 23 | 2 | 46 | Hotel | 2
93 | Sheet 61886 | 61 | Level 27 | WIR - 0169 | Outer sleeve | CHW pipe | 3" |  | 5" |  |  | 1 | 23 | 2 | 46 | Hotel | 2
95 | Sheet 61886 | 63 | Level 27 | WIR - 0169 | Outer sleeve | CHW pipe | 3" |  | 5" |  |  | 1 | 23 | 2 | 46 | Hotel | 2
97 | Sheet 61886 | 65 | Level 27 | WIR - 0169 | Outer sleeve | CHW pipe | 3" |  | 5" |  |  | 1 | 23 | 2 | 46 | Hotel | 2
102 | Sheet 61886 | 70 | Level 27 | WIR - 0169 | Outer sleeve | CHW pipe | 3" |  | 5" |  |  | 1 | 23 | 2 | 46 | Hotel | 2
104 | Sheet 61886 | 72 | Level 27 | WIR - 0169 | Outer sleeve | CHW pipe | 3" |  | 5" |  |  | 1 | 23 | 2 | 46 | Hotel | 2
109 | Sheet 61886 | 77 | Level 27 | WIR - 0169 | Outer sleeve | CHW pipe | 3" |  | 5" |  |  | 1 | 23 | 2 | 46 | Hotel | 2
13 | Sheet 62267 | 13 | Ground Level | WIR - 00180 | Female Toilet | CHW pipe | 3" |  | 5" |  |  | 2 | 23 | 4 | 184 | Hotel | 8
16 | Sheet 62267 | 16 | Ground Level | WIR - 00180 | Female Toilet | CHW pipe | 3" |  | 5" |  |  | 2 | 23 | 4 | 184 | Hotel | 8
10 | Sheet 62256 | 8 | Level 21 | WIR - 00177 | Room Entry Door | CHW pipe | 3" | 0.0044156 |  |  |  | 2 | 23 | 2 | 92 | Hotel | 4
22 | Sheet 62256 | 18 | Level 21 | WIR - 00177 | Shaft | CHW pipe | 3" |  | 5" |  |  | 1 | 23 | 2 | 46 | Hotel | 2
5 | Sheet 62260 | 4 | Level 19 | WIR - 00178 | Outer Sleeve | CHW pipe | 3" | 0.0044156 |  |  |  | 1 | 23 | 2 | 46 | Hotel | 2
22 | Sheet 62260 | 16 | Level 19 | WIR - 00178 | Outer Sleeve | CHW pipe | 3" |  | 5" |  |  | 1 | 23 | 2 | 46 | Hotel | 2
24 | Sheet 62260 | 18 | Level 19 | WIR - 00178 | Outer Sleeve | CHW pipe | 3" | 0.0044156 |  |  |  | 1 | 23 | 1 | 23 | Hotel | 1
26 | Sheet 62260 | 19 | Level 19 | WIR - 00178 | Outer Sleeve | CHW pipe | 3" | 0.0044156 |  |  |  | 1 | 23 | 1 | 23 | Hotel | 1
[13 empty] | Grand Total |  | 1495 | Total qty | 65

## CHW 4"
Project: |  |  |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  |  |  | Khansaheb Civil Engineering
Period of Completed Works: |  |  |  |  | up to July 2022
Summary of Completed Firestopping Works
No. | Sos Number | Serial No | Level | WIR No. | Location | Penetrant Type | Penetrant Size (in meter) | SquareMeters | Opening Size (in meter) | SquareMeters | Diffirence | Sides | Rate (AED) | Nos | Total (AED) |  |  | Hotel / Residence | QTY
1 | Sheet 62267 | 5 | Ground Level | WIR - 00180 | BOH 02 | CHW pipe | 4" |  | 6" |  |  | 2 | 29 | 2 | 116 |  |  | Hotel | 4
6 | Sheet 61937 | 6 | Ground Level | WIR - 0194 | Male Toilet | CHW pipe | 4" |  | 6" |  |  | 2 | 29 | 2 | 116 | FS702 |  | Hotel | 4
12 | Sheet 61937 | 12 | Ground Level | WIR - 0194 | Male Toilet | CHW pipe | 4" |  | 6" |  |  | 2 | 29 | 1 | 58 | FS702 |  | Hotel | 2
1 | Sheet 62328 |  | Level 12 | WIR - 00207 | Room Service | CHW pipe | 4" |  | 6" |  |  | 1 | 29 | 2 | 58 | FS702 | Sheet 62328 | Hotel | 2
8 | Sheet 62328 |  | Level 08 | WIR - 00207 | Room Service | CHW pipe | 4" |  | 6" |  |  | 1 | 29 | 2 | 58 | FS702 | Sheet 62328 | Hotel | 2
17 | Sheet 62328 |  | Level 07 | WIR - 00207 | Room Service | CHW pipe | 4" |  | 6" |  |  | 1 | 29 | 2 | 58 | FS702 | Sheet 62328 | Hotel | 2
2 | Sheet 62319 |  | Level 26 | WIR - 00206 | Room no. 05 | CHW pipe | 4" |  | 6" |  |  | 1 | 29 | 2 | 58 | FS702 | Sheet 62319 | Hotel | 2
3 | Sheet 62321 |  | Level 09 | WIR - 00204 | Room Service | CHW pipe | 4" |  | 6" |  |  | 1 | 29 | 2 | 58 | FS702 | Sheet 62321 | Hotel | 2
[13 empty] | Grand Total |  | 580 |  |  | Total qty | 20

## CHW 6"
Project: |  |  |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  |  |  | Khansaheb Civil Engineering
Period of Completed Works: |  |  |  |  | up to July 2022
Summary of Completed Firestopping Works
No. | Sos Number | Serial No | Level | WIR No. | Location | Penetrant Type | Penetrant Size (in meter) | SquareMeters | Opening Size (in meter) | SquareMeters | Diffirence | Sides | Rate (AED) | Nos | Total (AED) |  |  | Hotel / Residence | QTY
1 | Sheet 62317 |  | Level 28 | WIR - 00205 | Outer Sleeve | CHW pipe | 6" |  | 8" |  |  | 2 | 35 | 2 | 140 | FS702 | Sheet 62317 | Hotel | 4
[13 empty] | Grand Total |  | 140 |  |  | Total qty | 4

## CHW 8"
Project: |  |  |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  |  |  | Khansaheb Civil Engineering
Period of Completed Works: |  |  |  |  | up to July 2022
Summary of Completed Firestopping Works
No. | Sos Number | Serial No | Level | WIR No. | Location | Penetrant Type | Penetrant Size (in meter) | SquareMeters | Opening Size (in meter) | SquareMeters | Diffirence | Sides | Rate (AED) | Nos | Total (AED) |  |  | Hotel / Residence | QTY
1 | Sheet 62317 |  | Level 28 | WIR - 00205 | Outer Sleeve | CHW pipe | 8" |  | 10" |  |  | 2 | 47 | 4 | 376 | FS702 | Sheet 62317 | Hotel | 8
[13 empty] | Grand Total |  | 376 |  |  | Total qty | 8

## CHW 16"
Project: |  |  |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  |  |  | Khansaheb Civil Engineering
Period of Completed Works: |  |  |  |  | up to July 2022
Summary of Completed Firestopping Works
No. | Sos Number | Serial No | Level | WIR No. | Location | Penetrant Type | Penetrant Size (in meter) | SquareMeters | Opening Size (in meter) | SquareMeters | Diffirence | Sides | Rate (AED) | Nos | Total (AED) |  | Hotel / Residence | QTY
1 | Sheet 61937 | 17 | Ground Level | WIR - 0194 | Male Toilet | CHW pipe | 12" |  | 14" |  |  | 2 | 170 | 2 | 680 | FS702 | Hotel | 4
[13 empty] | Grand Total |  | 680 |  | Total qty | 4

## conduit & cable pipe
Project: |  |  |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  |  |  | Khansaheb Civil Engineering
Period of Completed Works: |  |  |  |  | up to July 2022
Summary of Completed Firestopping Works
No. | Sos Number | Serial No | Level | WIR No. | Location | Penetrant Type | Penetrant Size (in meter) | SquareMeters | Opening Size (in meter) | SquareMeters | Diffirence | Sides | Rate (AED) | Nos | Total (AED) |  | Hotel / Residence | QTY
1 | Sheet 62256 | 14 | Level 21 | WIR - 00177 | Room Entry Door | conduit pipe | 0.5" | 0.00013266 |  |  |  | 2 | 18 | 1 | 36 |  | Hotel | 2
1 | Sheet 62288 | 35 | Ground Level | WIR - 0194 | Staircase 04 | conduit pipe | 0.5" | 0.00013266 |  |  |  | 1 | 18 | 15 | 270 | FS702 | Residence | 15
[13 empty] | Grand Total |  | 306 |  | Total qty | 17

## Plastic pipe 2"
Project: |  |  |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  |  |  | Khansaheb Civil Engineering
Period of Completed Works: |  |  |  |  | up to July 2022
Summary of Completed Firestopping Works
No. | Sos Number | Serial No | Level | WIR No. | Location | Penetrant Type | Penetrant Size (in meter) | SquareMeters | Opening Size (in meter) | SquareMeters | Diffirence | Sides | Rate (AED) | Nos | Total (AED) |  | Hotel / Residence | QTY
12 | Sheet 62256 | 10 | Level 21 | WIR - 00177 | Room Entry Door | PVC pipe | 2" | 0.0019625 |  |  |  | 2 | 28 | 1 | 56 |  | Hotel | 2
3 | Sheet 62260 | 3 | Level 19 | WIR - 00178 | Outer Sleeve | PVC pipe | 2" | 0.0019625 |  |  |  | 1 | 28 | 1 | 28 |  | Hotel | 1
18 | Sheet 62260 | 14 | Level 19 | WIR - 00178 | Outer Sleeve | PVC pipe | 2" | 0.0019625 |  |  |  | 1 | 28 | 1 | 28 |  | Hotel | 1
30 | Sheet 62260 | 21 | Level 19 | WIR - 00178 | Outer Sleeve | PVC pipe | 2" | 0.0019625 |  |  |  | 1 | 28 | 1 | 28 |  | Hotel | 1
1 | Sheet 61938 | 31 | Ground Level | WIR - 0194 | Ball Room | PVC pipe | 2" |  | 4" |  |  | 2 | 28 | 4 | 224 | FS702 | Hotel | 8
[13 empty] | Grand Total |  | 364 |  | Total qty | 13

## Plastic pipe 3"
Project: |  |  |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  |  |  | Khansaheb Civil Engineering
Period of Completed Works: |  |  |  |  | up to July 2022
Summary of Completed Firestopping Works
No. | Sos Number | Serial No | Level | WIR No. | Location | Penetrant Type | Penetrant Size (in meter) | SquareMeters | Opening Size (in meter) | SquareMeters | Diffirence | Sides | Rate (AED) | Nos | Total (AED) |  |  | Hotel / Residence | QTY
31 | Sheet 61871 | 1 | Level 19 | WIR - 0168 | Outer sleeve | PPR pipe | 3" | 0.0044156 |  |  |  | 1 | 30 | 3 | 90 |  |  | Hotel | 3
34 | Sheet 61871 | 3 | Level 19 | WIR - 0168 | Outer sleeve | PPR pipe | 3" | 0.0044156 |  |  |  | 1 | 30 | 3 | 90 |  |  | Hotel | 3
38 | Sheet 61871 | 6 | Level 19 | WIR - 0168 | Outer sleeve | PPR pipe | 3" |  | 5" |  |  | 1 | 30 | 3 | 90 |  |  | Hotel | 3
41 | Sheet 61871 | 9 | Level 19 | WIR - 0168 | Outer sleeve | PPR pipe | 3" |  | 5" |  |  | 1 | 30 | 3 | 90 |  |  | Hotel | 3
33 | Sheet 61884 | 1 | Level 27 | WIR - 0169 | Outer sleeve | PPR pipe | 3" |  | 5" |  |  | 1 | 30 | 3 | 90 |  |  | Hotel | 3
39 | Sheet 61884 | 7 | Level 27 | WIR - 0169 | Outer sleeve | PPR pipe | 3" |  | 5" |  |  | 1 | 30 | 3 | 90 |  |  | Hotel | 3
41 | Sheet 61884 | 9 | Level 27 | WIR - 0169 | Outer sleeve | PPR pipe | 3" |  | 5" |  |  | 1 | 30 | 3 | 90 |  |  | Hotel | 3
50 | Sheet 61884 | 18 | Level 27 | WIR - 0169 | Outer sleeve | PPR pipe | 3" |  | 5" |  |  | 1 | 30 | 3 | 90 |  |  | Hotel | 3
53 | Sheet 61884 | 21 | Level 27 | WIR - 0169 | Outer sleeve | PPR pipe | 3" |  | 5" |  |  | 1 | 30 | 3 | 90 |  |  | Hotel | 3
57 | Sheet 61884 | 25 | Level 27 | WIR - 0169 | Outer sleeve | PPR pipe | 3" |  | 5" |  |  | 1 | 30 | 3 | 90 |  |  | Hotel | 3
63 | Sheet 61885 | 31 | Level 27 | WIR - 0169 | Outer sleeve | PPR pipe | 3" |  | 5" |  |  | 1 | 30 | 3 | 90 |  |  | Hotel | 3
67 | Sheet 61885 | 35 | Level 27 | WIR - 0169 | Outer sleeve | PPR pipe | 3" |  | 5" |  |  | 1 | 30 | 3 | 90 |  |  | Hotel | 3
72 | Sheet 61885 | 40 | Level 27 | WIR - 0169 | Outer sleeve | PPR pipe | 3" |  | 5" |  |  | 2 | 30 | 3 | 180 |  |  | Hotel | 6
79 | Sheet 61885 | 47 | Level 27 | WIR - 0169 | Outer sleeve | PPR pipe | 3" |  | 5" |  |  | 1 | 30 | 3 | 90 |  |  | Hotel | 3
81 | Sheet 61885 | 49 | Level 27 | WIR - 0169 | Outer sleeve | PPR pipe | 3" |  | 5" |  |  | 1 | 30 | 3 | 90 |  |  | Hotel | 3
89 | Sheet 61886 | 57 | Level 27 | WIR - 0169 | Outer sleeve | PPR pipe | 3" |  | 5" |  |  | 1 | 30 | 3 | 90 |  |  | Hotel | 3
91 | Sheet 61886 | 59 | Level 27 | WIR - 0169 | Outer sleeve | PPR pipe | 3" |  | 5" |  |  | 1 | 30 | 3 | 90 |  |  | Hotel | 3
94 | Sheet 61886 | 62 | Level 27 | WIR - 0169 | Outer sleeve | CDP pipe | 3" |  | 5" |  |  | 1 | 30 | 1 | 30 |  |  | Hotel | 1
98 | Sheet 61886 | 66 | Level 27 | WIR - 0169 | Outer sleeve | CDP pipe | 3" |  | 5" |  |  | 1 | 30 | 1 | 30 |  |  | Hotel | 1
99 | Sheet 61886 | 67 | Level 27 | WIR - 0169 | Outer sleeve | PPR pipe | 3" |  | 5" |  |  | 1 | 30 | 3 | 90 |  |  | Hotel | 3
101 | Sheet 61886 | 69 | Level 27 | WIR - 0169 | Outer sleeve | PPR pipe | 3" |  | 5" |  |  | 1 | 30 | 3 | 90 |  |  | Hotel | 3
110 | Sheet 61886 | 78 | Level 27 | WIR - 0169 | Outer sleeve | PPR pipe | 3" |  | 5" |  |  | 1 | 30 | 3 | 90 |  |  | Hotel | 3
10 | Sheet 62267 | 10 | Ground Level | WIR - 00180 | Female Toilet | PVC pipe | 3" |  | 5" |  |  | 2 | 30 | 2 | 120 |  |  | Hotel | 4
11 | Sheet 62267 | 11 | Ground Level | WIR - 00180 | Female Toilet | PPR pipe | 3" |  | 5" |  |  | 2 | 30 | 6 | 360 |  |  | Hotel | 12
14 | Sheet 62267 | 14 | Ground Level | WIR - 00180 | Female Toilet | CDP pipe | 3" |  | 5" |  |  | 2 | 30 | 1 | 60 |  |  | Hotel | 2
17 | Sheet 62267 | 17 | Ground Level | WIR - 00180 | Female Toilet | PVC pipe | 3" |  | 5" |  |  | 2 | 30 | 3 | 180 |  |  | Hotel | 6
18 | Sheet 62267 | 18 | Ground Level | WIR - 00180 | Female Toilet | PPR pipe | 3" |  | 5" |  |  | 2 | 30 | 9 | 540 |  |  | Hotel | 18
2 | Sheet 62256 | 2 | Level 21 | WIR - 00177 | Entry Door | PPR pipe | 3" |  | 5" |  |  | 1 | 30 | 3 | 90 |  |  | Hotel | 3
5 | Sheet 62256 | 5 | Level 21 | WIR - 00177 | Entry Door | PPR pipe | 3" | 0.0044156 |  |  |  | 1 | 30 | 3 | 90 |  |  | Hotel | 3
8 | Sheet 62256 | 7 | Level 21 | WIR - 00177 | Shaft | CDP pipe | 3" | 0.0044156 |  |  |  | 1 | 30 | 1 | 30 |  |  | Hotel | 1
13 | Sheet 62256 | 11 | Level 21 | WIR - 00177 | Room Entry Door | PPR pipe | 3" | 0.0044156 |  |  |  | 2 | 30 | 3 | 180 |  |  | Hotel | 6
15 | Sheet 62256 | 12 | Level 21 | WIR - 00177 | Room Entry Door | PPR pipe | 3" | 0.0044156 |  |  |  | 2 | 30 | 3 | 180 |  |  | Hotel | 6
20 | Sheet 62256 | 16 | Level 21 | WIR - 00177 | Shaft | PPR pipe | 3" |  | 5" |  |  | 1 | 30 | 3 | 90 |  |  | Hotel | 3
21 | Sheet 62256 | 17 | Level 21 | WIR - 00177 | Shaft | CDP pipe | 3" |  | 5" |  |  | 1 | 30 | 2 | 60 |  |  | Hotel | 2
24 | Sheet 62256 | 20 | Level 21 | WIR - 00177 | Shaft | PVC pipe | 3" |  | 5" |  |  | 1 | 30 | 1 | 30 |  |  | Hotel | 1
26 | Sheet 62256 | 22 | Level 21 | WIR - 00177 | Corridor | PPR pipe | 3" |  | 5" |  |  | 2 | 30 | 3 | 180 |  |  | Hotel | 6
1 | Sheet 62260 | 1 | Level 19 | WIR - 00178 | Outer Sleeve | PVC pipe | 3" |  | 5" |  |  | 1 | 30 | 1 | 30 |  | Sheet 62260 | Hotel | 1
7 | Sheet 62260 | 5 | Level 19 | WIR - 00178 | Outer Sleeve | PPR pipe | 3" | 0.0044156 |  |  |  | 1 | 30 | 3 | 90 |  |  | Hotel | 3
10 | Sheet 62260 | 7 | Level 19 | WIR - 00178 | Outer Sleeve | PPR pipe | 3" |  | 5" |  |  | 2 | 30 | 3 | 180 |  |  | Hotel | 6
11 | Sheet 62260 | 8 | Level 19 | WIR - 00178 | Outer Sleeve | PPR pipe | 3" |  | 5" |  |  | 2 | 30 | 3 | 180 |  |  | Hotel | 6
13 | Sheet 62260 | 10 | Level 19 | WIR - 00178 | Outer Sleeve | PVC pipe | 3" |  | 5" |  |  | 2 | 30 | 1 | 60 |  |  | Hotel | 2
14 | Sheet 62260 | 11 | Level 19 | WIR - 00178 | Outer Sleeve | PVC pipe | 3" |  | 5" |  |  | 2 | 30 | 2 | 120 |  |  | Hotel | 4
15 | Sheet 62260 | 12 | Level 19 | WIR - 00178 | Outer Sleeve | PVC pipe | 3" |  | 5" |  |  | 1 | 30 | 2 | 60 |  |  | Hotel | 2
4 | Sheet 61937 | 4 | Ground Level | WIR - 0194 | Male Toilet | PVC pipe | 3" |  | 5" |  |  | 2 | 30 | 1 | 60 | FS702 |  | Hotel | 2
7 | Sheet 61937 | 7 | Ground Level | WIR - 0194 | Male Toilet | CDP pipe | 3" |  | 5" |  |  | 2 | 30 | 1 | 60 | FS702 |  | Hotel | 2
13 | Sheet 61937 | 13 | Ground Level | WIR - 0194 | Male Toilet | PPR pipe | 3" |  | 5" |  |  | 2 | 30 | 3 | 180 | FS702 |  | Hotel | 6
11 | Sheet 62288 | 36 | Ground Level | WIR - 0194 | Staircase 04 | CDP pipe | 3" | 0.0044156 |  |  |  | 1 | 30 | 1 | 30 | FS702 |  | Residence | 1
1 | Sheet 62319 |  | Level 26 | WIR - 00206 | Room no. 05 | CDP pipe | 3" |  | 5" |  |  | 1 | 30 | 1 | 30 | FS702 | Sheet 62319 | Hotel | 1
6 | Sheet 62317 |  | Level 28 | WIR - 00205 | Outer Sleeve | PPR pipe | 3" |  | 5" |  |  | 2 | 30 | 3 | 180 | FS702 | Sheet 62317 | Hotel | 6
[13 empty] | Grand Total |  | 5400 |  |  | Total qty | 180

## Plastic pipe 4"
Project: |  |  |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  |  |  | Khansaheb Civil Engineering
Period of Completed Works: |  |  |  |  | up to July 2022
Summary of Completed Firestopping Works
No. | Sos Number | Serial No | Level | WIR No. | Location | Penetrant Type | Penetrant Size (in meter) | SquareMeters | Opening Size (in meter) | SquareMeters | Diffirence | Sides | Rate (AED) | Nos | Total (AED) |  | Hotel / Residence | QTY
1 | Sheet 61884 | 13 | Level 27 | WIR - 0169 | Outer sleeve | PVC pipe | 4" |  | 6" |  |  | 1 | 65 | 1 | 65 |  | Hotel | 1
15 | Sheet 62267 | 15 | Ground Level | WIR - 00180 | Female Toilet | PVC pipe | 4" |  | 6" |  |  | 2 | 65 | 4 | 520 |  | Hotel | 8
2 | Sheet 62260 | 2 | Level 19 | WIR - 00178 | Outer Sleeve | PVC pipe | 4" | 0.00785 |  |  |  | 1 | 65 | 3 | 195 |  | Hotel | 3
12 | Sheet 62260 | 9 | Level 19 | WIR - 00178 | Outer Sleeve | PVC pipe | 4" |  | 6" |  |  | 2 | 65 | 1 | 130 |  | Hotel | 2
16 | Sheet 62260 | 13 | Level 19 | WIR - 00178 | Outer Sleeve | PVC pipe | 4" | 0.00785 |  |  |  | 1 | 65 | 1 | 65 |  | Hotel | 1
20 | Sheet 62260 | 15 | Level 19 | WIR - 00178 | Outer Sleeve | PVC pipe | 4" | 0.00785 |  |  |  | 1 | 65 | 2 | 130 |  | Hotel | 2
28 | Sheet 62260 | 20 | Level 19 | WIR - 00178 | Outer Sleeve | PVC pipe | 4" | 0.00785 |  |  |  | 1 | 65 | 1 | 65 |  | Hotel | 1
32 | Sheet 62260 | 22 | Level 19 | WIR - 00178 | Outer Sleeve | PVC pipe | 4" | 0.00785 |  |  |  | 1 | 65 | 1 | 65 |  | Hotel | 1
8 | Sheet 61937 | 8 | Ground Level | WIR - 0194 | Male Toilet | PVC pipe | 4" |  | 6" |  |  | 2 | 65 | 1 | 130 | FS702 | Hotel | 2
9 | Sheet 61937 | 9 | Ground Level | WIR - 0194 | Male Toilet | PPR pipe | 4" |  | 6" |  |  | 2 | 65 | 3 | 390 | FS702 | Hotel | 6
11 | Sheet 61937 | 11 | Ground Level | WIR - 0194 | Male Toilet | CDP pipe | 4" |  | 6" |  |  | 2 | 65 | 1 | 130 | FS702 | Hotel | 2
[13 empty] | Grand Total |  | 1885 |  | Total qty | 29

## Plastic pipe 6"
Project: |  |  |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  |  |  | Khansaheb Civil Engineering
Period of Completed Works: |  |  |  |  | up to July 2022
Summary of Completed Firestopping Works
No. | Sos Number | Serial No | Level | WIR No. | Location | Penetrant Type | Penetrant Size (in meter) | SquareMeters | Opening Size (in meter) | SquareMeters | Diffirence | Sides | Rate (AED) | Nos | Total (AED) |  |  | Hotel / Residence | QTY
36 | Sheet 61884 | 4 | Level 27 | WIR - 0169 | Outer sleeve | PVC pipe | 6" |  | 8" |  |  | 1 | 125 | 1 | 125 |  |  | Hotel | 1
37 | Sheet 61884 | 5 | Level 27 | WIR - 0169 | Outer sleeve | PVC pipe | 5" |  | 7" |  |  | 1 | 125 | 1 | 125 |  |  | Hotel | 1
38 | Sheet 61884 | 6 | Level 27 | WIR - 0169 | Outer sleeve | PVC pipe | 6" |  | 8" |  |  | 1 | 125 | 1 | 125 |  |  | Hotel | 1
44 | Sheet 61884 | 12 | Level 27 | WIR - 0169 | Outer sleeve | PVC pipe | 6" |  | 8" |  |  | 1 | 125 | 1 | 125 |  |  | Hotel | 1
52 | Sheet 61884 | 20 | Level 27 | WIR - 0169 | Outer sleeve | PVC pipe | 6" |  | 8" |  |  | 1 | 125 | 1 | 125 |  |  | Hotel | 1
60 | Sheet 61885 | 28 | Level 27 | WIR - 0169 | Outer sleeve | PVC pipe | 6" |  | 8" |  |  | 1 | 125 | 1 | 125 |  |  | Hotel | 1
66 | Sheet 61885 | 34 | Level 27 | WIR - 0169 | Outer sleeve | PVC pipe | 6" |  | 8" |  |  | 1 | 125 | 1 | 125 |  |  | Hotel | 1
75 | Sheet 61885 | 43 | Level 27 | WIR - 0169 | Outer sleeve | PVC pipe | 6" |  | 8" |  |  | 1 | 125 | 1 | 125 |  |  | Hotel | 1
77 | Sheet 61885 | 45 | Level 27 | WIR - 0169 | Outer sleeve | PVC pipe | 6" |  | 8" |  |  | 1 | 125 | 1 | 125 |  |  | Hotel | 1
78 | Sheet 61885 | 46 | Level 27 | WIR - 0169 | Outer sleeve | PVC pipe | 6" |  | 8" |  |  | 1 | 125 | 1 | 125 |  |  | Hotel | 1
84 | Sheet 61885 | 52 | Level 27 | WIR - 0169 | Outer sleeve | PVC pipe | 5" |  | 7" |  |  | 1 | 125 | 1 | 125 |  |  | Hotel | 1
86 | Sheet 61886 | 54 | Level 27 | WIR - 0169 | Outer sleeve | PVC pipe | 6" |  | 8" |  |  | 1 | 125 | 1 | 125 |  |  | Hotel | 1
88 | Sheet 61886 | 56 | Level 27 | WIR - 0169 | Outer sleeve | PVC pipe | 5" |  | 7" |  |  | 1 | 125 | 1 | 125 |  |  | Hotel | 1
96 | Sheet 61886 | 64 | Level 27 | WIR - 0169 | Outer sleeve | PVC pipe | 6" |  | 8" |  |  | 1 | 125 | 1 | 125 |  |  | Hotel | 1
106 | Sheet 61886 | 74 | Level 27 | WIR - 0169 | Outer sleeve | PVC pipe | 6" |  | 8" |  |  | 1 | 125 | 1 | 125 |  |  | Hotel | 1
107 | Sheet 61886 | 75 | Level 27 | WIR - 0169 | Outer sleeve | PVC pipe | 5" |  | 7" |  |  | 1 | 125 | 1 | 125 |  |  | Hotel | 1
108 | Sheet 61886 | 76 | Level 27 | WIR - 0169 | Outer sleeve | PVC pipe | 5" |  | 7" |  |  | 1 | 125 | 1 | 125 |  |  | Hotel | 1
6 | Sheet 62267 | 6 | Ground Level | WIR - 00180 | BOH 03 | PVC pipe | 6" |  | 8" |  |  | 2 | 125 | 1 | 250 |  |  | Hotel | 2
23 | Sheet 62256 | 19 | Level 21 | WIR - 00177 | Shaft | PVC pipe | 6" |  | 8" |  |  | 1 | 125 | 2 | 250 |  |  | Hotel | 2
25 | Sheet 61937 | 25 | Ground Level | WIR - 0194 | Ball Room | PVC pipe | 6" |  | 8" |  |  | 2 | 125 | 1 | 250 | FS702 |  | Hotel | 2
2 | Sheet 61938 | 27 | Ground Level | WIR - 0194 | Ball Room | PVC pipe | 6" |  | 8" |  |  | 2 | 125 | 1 | 250 | FS702 |  | Hotel | 2
4 | Sheet 61938 | 29 | Ground Level | WIR - 0194 | Ball Room | PVC pipe | 6" |  | 8" |  |  | 2 | 125 | 4 | 1000 | FS702 |  | Hotel | 8
7 | Sheet 61938 | 32 | Ground Level | WIR - 0194 | Ball Room | PVC pipe | 6" |  | 8" |  |  | 2 | 125 | 1 | 250 | FS702 |  | Hotel | 2
9 | Sheet 61938 | 34 | Ground Level | WIR - 0194 | Ball Room | PVC pipe | 6" |  | 8" |  |  | 2 | 125 | 1 | 250 | FS702 |  | Hotel | 2
10 | Sheet 61938 | 35 | Ground Level | WIR - 0194 | Ball Room | PVC pipe | 6" |  | 8" |  |  | 2 | 125 | 1 | 250 | FS702 |  | Hotel | 2
3 | Sheet 62323 |  | Level 23 | WIR - 00203/00199 | Outer Sleeve | PVC pipe | 6" |  | 8" |  |  | 1 | 125 | 1 | 125 |  | Sheet 62323 | Residence | 1
2 | Sheet 62328 |  | Level 12 | WIR - 00207 | Room Service | PVC pipe | 6" |  | 8" |  |  | 1 | 125 | 1 | 125 | FS702 | Sheet 62328 | Hotel | 1
9 | Sheet 62328 |  | Level 08 | WIR - 00207 | Room Service | PVC pipe | 6" |  | 8" |  |  | 1 | 125 | 1 | 125 | FS702 | Sheet 62328 | Hotel | 1
3 | Sheet 62319 |  | Level 26 | WIR - 00206 | Room no. 05 | PVC pipe | 5" |  | 7" |  |  | 1 | 125 | 2 | 250 | FS702 | Sheet 62319 | Hotel | 2
5 | Sheet 62321 |  | Level 09 | WIR - 00204 | Room Service | PVC pipe | 6" |  | 8" |  |  | 1 | 125 | 1 | 125 | FS702 | Sheet 62321 | Hotel | 1
2 | Sheet 62317 |  | Level 28 | WIR - 00205 | Outer Sleeve | PVC pipe | 6" |  | 8" |  |  | 2 | 125 | 1 | 250 | FS702 | Sheet 62317 | Hotel | 2
[13 empty] | Grand Total |  | 5875 |  |  | Total qty | 47

## Plastic pipe 8"
Project: |  |  |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  |  |  | Khansaheb Civil Engineering
Period of Completed Works: |  |  |  |  | up to July 2022
Summary of Completed Firestopping Works
No. | Sos Number | Serial No | Level | WIR No. | Location | Penetrant Type | Penetrant Size (in meter) | SquareMeters | Opening Size (in meter) | SquareMeters | Diffirence | Sides | Rate (AED) | Nos | Total (AED) |  |  | Hotel / Residence | QTY
73 | Sheet 61885 | 41 | Level 27 | WIR - 0169 | Outer sleeve | PVC pipe | 8" |  | 10" |  |  | 2 | 250 | 1 | 500 |  |  | Hotel | 2
87 | Sheet 61886 | 55 | Level 27 | WIR - 0169 | Outer sleeve | PVC pipe | 8" |  | 10" |  |  | 1 | 250 | 1 | 250 |  |  | Hotel | 1
14 | Sheet 61937 | 14 | Ground Level | WIR - 0194 | Male Toilet | PVC pipe | 8" |  | 10" |  |  | 2 | 250 | 1 | 500 | FS702 |  | Hotel | 2
15 | Sheet 61937 | 15 | Ground Level | WIR - 0194 | Male Toilet | PVC pipe | 8" |  | 10" |  |  | 2 | 250 | 2 | 1000 | FS702 |  | Hotel | 4
18 | Sheet 61937 | 18 | Ground Level | WIR - 0194 | Male Toilet | PVC pipe | 8" |  | 10" |  |  | 2 | 250 | 5 | 2500 | FS702 |  | Hotel | 10
19 | Sheet 61937 | 19 | Ground Level | WIR - 0194 | Male Toilet | PVC pipe | 8" |  | 10" |  |  | 2 | 250 | 1 | 500 | FS702 |  | Hotel | 2
23 | Sheet 61937 | 23 | Ground Level | WIR - 0194 | Ball Room | PVC pipe | 8" |  | 10" |  |  | 2 | 250 | 1 | 500 | FS702 |  | Hotel | 2
1 | Sheet 61938 | 26 | Ground Level | WIR - 0194 | Ball Room | PVC pipe | 8" |  | 10" |  |  | 2 | 250 | 2 | 1000 | FS702 | Sheet 61938 | Hotel | 4
8 | Sheet 61938 | 33 | Ground Level | WIR - 0194 | Ball Room | PVC pipe | 8" |  | 10" |  |  | 2 | 250 | 1 | 500 | FS702 |  | Hotel | 2
16 | Sheet 61938 | 41 | Ground Level | WIR - 0194 | Ball Room | PVC pipe | 8" |  | 10" |  |  | 2 | 250 | 4 | 2000 | FS702 |  | Hotel | 8
2 | Sheet 62323 |  | Level 23 | WIR - 00203/00199 | Outer Sleeve | PVC pipe | 8" |  | 10" |  |  | 1 | 250 | 2 | 500 |  | Sheet 62323 | Residence | 2
18 | Sheet 62328 |  | Level 07 | WIR - 00207 | Room Service | PVC pipe | 8" |  | 10" |  |  | 1 | 250 | 1 | 250 | FS702 | Sheet 62328 | Hotel | 1
4 | Sheet 62321 |  | Level 09 | WIR - 00204 | Room Service | PVC pipe | 8" |  | 10" |  |  | 1 | 250 | 2 | 500 | FS702 | Sheet 62321 | Hotel | 2
1 | Sheet 62317 |  | Level 28 | WIR - 00205 | Outer Sleeve | PVC pipe | 8" |  | 10" |  |  | 2 | 250 | 5 | 2500 | FS702 | Sheet 62317 | Hotel | 10
3 | Sheet 62317 |  | Level 28 | WIR - 00205 | Outer Sleeve | PVC pipe | 8" |  | 10" |  |  | 2 | 250 | 2 | 1000 | FS702 | Sheet 62317 | Hotel | 4
[13 empty] | Grand Total |  | 14000 |  |  | Total qty | 56

## civil opening
Project: |  |  |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  |  |  | Khansaheb Civil Engineering
Period of Completed Works: |  |  |  |  | up to July 2022
Summary of Completed Firestopping Works
No. | Sos Number | Serial No | Level | WIR No. | Location | Penetrant Type | Penetrant Size (in meter) | SquareMeters | Opening Size (in meter) |  | SquareMeters | Diffirence | Sides | Rate (AED) | Nos | Total (AED) |  |  | Hotel / Residence | QTY
6 | Sheet 61907 | 5 | Level 29 | WIR - 01160 | Electrical Room | cable trunking |  |  | 0.15 | 0.15 | 0.0225 |  | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
9 | Sheet 61907 | 7 | Level 29 | WIR - 01160 | Electrical Room | opening |  |  | 0.2 | 0.2 | 0.04 | 0.029509 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
12 | Sheet 61907 | 9 | Level 29 | WIR - 01160 | Telephone Room | opening |  |  | 0.2 | 0.2 | 0.04 | 0.029509 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
17 | Sheet 61907 | 13 | Level 29 | WIR - 01160 | Telephone Room | cable trunking |  |  | 0.15 | 0.17 | 0.0255 |  | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
20 | Sheet 61907 | 15 | Level 29 | WIR - 01160 | Telephone Room | opening |  |  | 0.2 | 0.25 | 0.05 | 0.039509 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
29 | Sheet 61907 | 22 | Level 29 | WIR - 01160 | Male Toilet | cable trunking |  |  | 0.15 | 0.2 | 0.03 |  | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
21 | Sheet 61910 | 17 | Basement 01 | WIR - 0977 | Corridor, Entry D. | cable tray |  |  | 0.1 | 0.4 | 0.04 |  | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
23 | Sheet 61910 | 18 | Basement 01 | WIR - 0977 | Corridor, Entry D. | opening |  |  | 0.25 | 0.5 | 0.125 | 0.045 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
16 | Sheet 61911 | 37 | Basement 01 | WIR - 0977 | Corridor, Entry D. | cable tray |  |  | 0.09 | 0.16 | 0.0144 |  | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
17 | Sheet 61911 | 38 | Basement 01 | WIR - 0977 | Corridor, Entry D. | cable trunking |  |  | 0.15 | 0.15 | 0.0225 |  | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
1 | Sheet 61022 |  | Level 24 | MEP-AX-WR-L24-00333 | Corridor | blank opening |  |  | 0.15 | 0.15 | 0.0225 | 0.0225 | 2 | 50 | 1 | 100 |  |  | Residence | 2
2 | Sheet 61022 |  | Level 24 | MEP-AX-WR-L24-00333 | Corridor | blank opening |  |  | 0.3 | 0.15 | 0.045 | 0.045 | 2 | 50 | 1 | 100 |  |  | Residence | 2
5 | Sheet 61026 |  | Level 06 | MEP-AX-WR-L6-00532 | Passanger Lift lobby | opening |  |  | 6" |  | 0.017663 | 0.016461 | 2 | 50 | 1 | 100 |  |  | Residence | 2
29 | Sheet 61864 |  | Level 26 | MEP-AX-WR-L26-00686 | FF Lobby | opening |  |  | 6" |  | 0.017662 | 0.016681 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
29 | Sheet 61855 |  | Level 25 | MEP-AX-WR-L25-00608 | Room Service | opening |  |  | 4" |  | 0.00785 | 0.0068688 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
20 | Sheet 61861 |  | Basement 01 | MEP-AX-WR-B1-00849 | CEF Room | opening |  |  | 0.15 | 0.2 | 0.03 | 0.028037 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Residence | 2
2 | Sheet 62259 | 21 | Level 19 | WIR - 01529 | Room no. 02, wall | opening |  |  | 0.25 | 0.35 | 0.0875 | 0.0475 | 1 | 50 | 1 | 50 | FS702/FB750 |  | Hotel | 1
7 | Sheet 62259 | 25 | Level 19 | WIR - 01529 | Room no. 02, wall | opening |  |  | 0.15 | 0.4 | 0.06 | 0.045 | 1 | 50 | 1 | 50 | FS702/FB750 |  | Hotel | 1
9 | Sheet 62259 | 26 | Level 19 | WIR - 01529 | Room no. 02, wall | opening |  |  | 0.25 | 0.3 | 0.075 | 0.035 | 1 | 50 | 1 | 50 | FS702/FB750 |  | Hotel | 1
2 | Sheet 62265 | 7 | Ground Level | WIR - 01634 | BOH 02 | opening |  |  | 0.25 | 0.3 | 0.075 | 0.035 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
4 | Sheet 62265 | 8 | Ground Level | WIR - 01634 | BOH 02 | opening |  |  | 0.3 | 0.3 | 0.09 | 0.05 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
8 | Sheet 62265 | 24 | Ground Level | WIR - 01634 | Female Toilet | opening |  |  | 0.38 | 0.38 | 0.1444 | 0.0544 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
17 | Sheet 62260 | 13 | Level 19 | WIR - 00178 | Outer Sleeve | opening |  |  | 0.2 | 0.3 | 0.06 | 0.05215 | 1 | 50 | 1 | 50 |  |  | Hotel | 1
19 | Sheet 62260 | 14 | Level 19 | WIR - 00178 | Outer Sleeve | opening |  |  | 0.15 | 0.2 | 0.03 | 0.028037 | 1 | 50 | 1 | 50 |  |  | Hotel | 1
25 | Sheet 62260 | 18 | Level 19 | WIR - 00178 | Outer Sleeve | opening |  |  | 0.1 | 0.25 | 0.025 | 0.020584 | 1 | 50 | 1 | 50 |  |  | Hotel | 1
27 | Sheet 62260 | 19 | Level 19 | WIR - 00178 | Outer Sleeve | opening |  |  | 0.1 | 0.25 | 0.025 | 0.020584 | 1 | 50 | 1 | 50 |  |  | Hotel | 1
29 | Sheet 62260 | 20 | Level 19 | WIR - 00178 | Outer Sleeve | opening |  |  | 0.2 | 0.3 | 0.06 | 0.05215 | 1 | 50 | 1 | 50 |  |  | Hotel | 1
31 | Sheet 62260 | 21 | Level 19 | WIR - 00178 | Outer Sleeve | opening |  |  | 0.1 | 0.1 | 0.01 | 0.0080375 | 1 | 50 | 1 | 50 |  |  | Hotel | 1
16 | Sheet 62275 | 40 | Level 29 | WIR - 01839 | Corridor Entry Dr. | opening |  |  | 0.25 | 0.35 | 0.0875 | 0.0275 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Residence | 2
6 | Sheet 62271 | 2 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | opening |  |  | 0.42 | 0.37 | 0.1554 | 0.0466 | 1 | 50 | 1 | 50 | FS702/FB750 |  | Hotel | 1
4 | Sheet 62280 | 2 | Ground Level | WIR - 01955 | BOH Corridor | opening |  |  | 0.3 | 0.46 | 0.138 | 0.038 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
3 | Sheet 62291 | 2 | Ground Level | WIR - 02185 | Male Toilet | opening |  |  | 4" |  | 0.00785 | 0.0068688 | 2 | 50 | 1 | 100 | FS702 |  | Hotel | 2
7 | Sheet 62291 | 5 | Ground Level | WIR - 02185 | Male Toilet | opening |  |  | 0.1 | 0.1 | 0.01 | 0.005 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
8 | Sheet 62292 | 30 | Ground Level | WIR - 02185 | Male Toilet | opening |  |  | 0.3 | 0.38 | 0.114 | 0.0515 | 1 | 50 | 1 | 50 | FS702/FB750 |  | Hotel | 1
15 | Sheet 62292 | 35 | Ground Level | WIR - 02185 | Male Toilet | opening |  |  | 0.3 | 0.46 | 0.138 | 0.038 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
15 | Sheet 62294 | 85 | Ground Level | WIR - 02185 | Ball Room | opening |  |  | 0.15 | 0.25 | 0.0375 | 0.0175 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
28 | Sheet 62295 | 122 | Ground Level | WIR - 02185 | Ball Room | opening |  |  | 0.35 | 0.4 | 0.14 | 0.010604 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
15 | Sheet 62297 | 167 | Ground Level | WIR - 02185 | Housekeeping | opening |  |  | 0.2 | 0.5 | 0.1 | 0.045 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
13 | Sheet 62298 | 189 | Ground Level | WIR - 02185 | Kitchen | opening |  |  | 0.3 | 0.33 | 0.099 | 0.0365 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
15 | Sheet 61941 | 66 | Level 18 | WIR - 02249 | Housekeeping | opening |  |  | 6" |  | 0.017662 | 0.0157 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
27 | Sheet 62309 | 52 | Level 01 | WIR - 02537 | Housekeeping | opening |  |  | 0.25 | 0.3 | 0.075 | 0.0425 | 2 | 50 | 1 | 100 | FS702/FB750 | Sheet 62309 | Hotel | 2
30 | Sheet 62309 | 54 | Level 01 | WIR - 02537 | Housekeeping | opening |  |  | 0.2 | 0.3 | 0.06 | 0.049735 | 2 | 50 | 1 | 100 | FS702/FB750 | Sheet 62309 | Hotel | 2
12 | Sheet 62311 | 92 | Level 01 | WIR - 02537 | Service lobby | opening |  |  | 6" |  | 0.017662 | 0.017397 | 2 | 50 | 1 | 100 | FS702/FB750 | Sheet 62311 | Hotel | 2
14 | Sheet 62311 | 93 | Level 01 | WIR - 02537 | Service lobby | opening |  |  | 4" |  | 0.00785 | 0.0073594 | 2 | 50 | 1 | 100 | FS702/FB750 | Sheet 62311 | Hotel | 2
1 | Sheet 62312 | 110 | Level 01 | WIR - 02537 | Entry Door | cable trunking |  |  | 0.08 | 0.08 | 0.0064 |  | 2 | 50 | 1 | 100 | FS702/FB750 | Sheet 62312 | Hotel | 2
16 | Sheet 62312 | 124 | Level 01 | WIR - 02537 | Lobby, Wall | cable tray |  |  | 0.1 | 0.25 | 0.025 |  | 1 | 50 | 1 | 50 | FS702/FB750 | Sheet 62312 | Hotel | 1
19 | Sheet 62312 | 126 | Level 01 | WIR - 02537 | Lobby, Wall | opening |  |  | 0.2 | 0.2 | 0.04 | 0.039509 | 2 | 50 | 1 | 100 | FS702/FB750 | Sheet 62312 | Hotel | 2
4 | Sheet 62313 | 140 | Level 01 | WIR - 02537 | Plant room | cable trunking |  |  | 0.2 | 0.2 | 0.04 |  | 2 | 50 | 1 | 100 | FS702/FB750 | Sheet 62313 | Hotel | 2
13 | Sheet 62314 | 10 | Level 23 | WIR - 02536 | Female Change Rm | opening |  |  | 0.35 | 0.75 | 0.2625 | 0.0525 | 1 | 50 | 1 | 50 | FS702/FB750 | Sheet 62314 | Residence | 1
35 | Sheet 62314 | 26 | Level 23 | WIR - 02536 | Male Change Rm | opening |  |  | 0.2 | 0.2 | 0.04 | 0.03215 | 2 | 50 | 1 | 100 | FS702/FB750 | Sheet 62314 | Residence | 2
17 | Sheet 62316 | 12 | Level 28 | WIR - 02557 | Gym Room | opening |  |  | 0.35 | 0.48 | 0.168 | 0.048 | 1 | 50 | 1 | 50 | FS702/FB750 | Sheet 62316 | Hotel | 1
13 | Sheet 61947 | 11 | Level 12 | WIR - 02330 | Housekeeping | cable trunking |  |  | 0.15 | 0.15 | 0.0225 |  | 2 | 50 | 1 | 100 | FS702/FB750 | Sheet 61947 | Hotel | 2
19 | Sheet 61949 | 15 | Level 20 | WIR - 02329 | Housekeeping | opening |  |  | 0.25 | 0.25 | 0.0625 | 0.042235 | 2 | 50 | 1 | 100 | FS702/FB750 | Sheet 61949 | Hotel | 2
25 | Sheet 61950 | 20 | Level 21 | WIR - 02329 | Housekeeping | opening |  |  | 0.2 | 0.25 | 0.05 | 0.048038 | 2 | 50 | 1 | 100 | FS702/FP302 | Sheet 61950 | Hotel | 2
22 | Sheet 62302 | 18 | Level 23 | WIR - 02329 | Housekeeping | opening |  |  | 0.2 | 0.4 | 0.08 | 0.049337 | 2 | 50 | 1 | 100 | FS702/FB750 | Sheet 62302 | Hotel | 2
15 | Sheet 62303 | 11 | Level 24 | WIR - 02328 | Housekeeping | opening |  |  | 0.26 | 0.28 | 0.0728 | 0.0328 | 1 | 50 | 1 | 50 | FS702/FB750 | Sheet 62303 | Hotel | 1
25 | Sheet 62303 | 19 | Level 24 | WIR - 02328 | Housekeeping | opening |  |  | 0.2 | 0.3 | 0.06 | 0.039602 | 2 | 50 | 1 | 100 | FS702/FB750 | Sheet 62303 | Hotel | 2
28 | Sheet 62303 | 22 | Level 24 | WIR - 02328 | Housekeeping | cable trunking |  |  | 0.1 | 0.12 | 0.012 |  | 2 | 50 | 1 | 100 | FS702/FB750 | Sheet 62303 | Hotel | 2
18 | Sheet 62304 | 14 | Level 25 | WIR - 02328 | Housekeeping | opening |  |  | 0.2 | 0.3 | 0.06 | 0.04 | 2 | 50 | 1 | 100 | FS702/FB750 | Sheet 62304 | Hotel | 2
24 | Sheet 62304 | 18 | Level 25 | WIR - 02328 | Housekeeping | opening |  |  | 0.18 | 0.3 | 0.054 | 0.033469 | 2 | 50 | 1 | 100 | FS702/FB750 | Sheet 62304 | Hotel | 2
14 | Sheet 62305 | 10 | Level 26 | WIR - 02328 | Housekeeping | opening |  |  | 0.28 | 0.3 | 0.084 | 0.044 | 1 | 50 | 1 | 50 | FS702/FB750 | Sheet 62305 | Hotel | 1
4 | Sheet 62320 | 3 | Level 09 | WIR - 02558 | Room Service | opening |  |  | 0.2 | 0.3 | 0.06 | 0.05215 | 2 | 50 | 1 | 100 | FS702/FB750 | Sheet 62320 | Hotel | 2
[12 empty] | Subtotal 0.05 m |  |  |  | 5400 |  |  |  | 108
4 | Sheet 61907 | 3 | Level 29 | WIR - 01160 | Electrical Room | opening |  |  | 0.3 | 0.4 | 0.12 | 0.099509 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
16 | Sheet 61907 | 12 | Level 29 | WIR - 01160 | Telephone Room | opening |  |  | 0.3 | 0.6 | 0.18 | 0.089509 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
24 | Sheet 61907 | 18 | Level 29 | WIR - 01160 | Male Toilet | opening |  |  | 0.3 | 0.48 | 0.144 | 0.064 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
26 | Sheet 61907 | 19 | Level 29 | WIR - 01160 | Male Toilet | opening |  |  | 0.3 | 0.48 | 0.144 | 0.064 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
10 | Sheet 61910 | 8 | Basement 01 | WIR - 0977 | Corridor, Entry D. | opening |  |  | 0.45 | 0.45 | 0.2025 | 0.08 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
2 | Sheet 61026 |  | Level 06 | MEP-AX-WR-L6-00532 | Entry door | opening |  |  | 0.35 | 0.2 | 0.07 | 0.06215 | 2 | 95 | 1 | 190 |  |  | Residence | 2
8 | Sheet 61026 |  | Level 06 | MEP-AX-WR-L6-00532 | Passanger Lift lobby | opening |  |  | 0.2 | 0.35 | 0.07 | 0.056753 | 2 | 95 | 1 | 190 |  |  | Residence | 2
12 | Sheet 61027 |  | Level 06 | MEP-AX-WR-L6-00532 | Staircase 03 | opening |  |  | 0.3 | 0.3 | 0.09 | 0.085584 | 2 | 95 | 1 | 190 |  |  | Residence | 2
15 | Sheet 61027 |  | Level 06 | MEP-AX-WR-L6-00532 | FF Lobby | opening |  |  | 0.4 | 0.25 | 0.1 | 0.098037 | 2 | 95 | 1 | 190 |  |  | Residence | 2
3 | Sheet 61038 |  | Level 04 | MEP-AX-WR-L4-00531 | FF Lobby | opening |  |  | 0.3 | 0.25 | 0.075 | 0.065187 | 2 | 95 | 1 | 190 |  |  | Residence | 2
11 | Sheet 61038 |  | Level 04 | MEP-AX-WR-L4-00531 | Passanger Lobby | opening |  |  | 0.35 | 0.25 | 0.0875 | 0.072926 | 2 | 95 | 1 | 190 |  |  | Residence | 2
10 | Sheet 61863 |  | Level 26 | MEP-AX-WR-L26-00686 | Housekeeping | opening |  |  | 0.3 | 0.3 | 0.09 | 0.086075 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
12 | Sheet 61863 |  | Level 26 | MEP-AX-WR-L26-00686 | Housekeeping | opening |  |  | 0.3 | 0.3 | 0.09 | 0.085584 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
30 | Sheet 61864 |  | Level 26 | MEP-AX-WR-L26-00686 | Staircase | opening |  |  | 0.3 | 0.3 | 0.09 | 0.08215 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
10 | Sheet 61854 |  | Level 25 | MEP-AX-WR-L25-00608 | Housekeeping | opening |  |  | 0.3 | 0.3 | 0.09 | 0.086075 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
12 | Sheet 61854 |  | Level 25 | MEP-AX-WR-L25-00608 | Housekeeping | opening |  |  | 0.3 | 0.3 | 0.09 | 0.072337 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
30 | Sheet 61855 |  | Level 25 | MEP-AX-WR-L25-00608 | Room Service | opening |  |  | 0.3 | 0.3 | 0.09 | 0.072337 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
10 | Sheet 61859 |  | Level 24 | MEP-AX-WR-L24-00588 | Housekeeping | opening |  |  | 0.3 | 0.3 | 0.09 | 0.084112 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
12 | Sheet 61860 |  | Level 24 | MEP-AX-WR-L24-00588 | Housekeeping | opening |  |  | 0.3 | 0.3 | 0.09 | 0.072337 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
28 | Sheet 61860 |  | Level 24 | MEP-AX-WR-L24-00588 | Staircase | opening |  |  | 0.3 | 0.3 | 0.09 | 0.072337 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
9 | Sheet 61869 |  | Level 19 | WIR - 0731 | Housekeeping | opening |  |  | 0.3 | 0.3 | 0.09 | 0.086075 | 2 | 95 | 1 | 190 |  |  | Hotel | 2
12 | Sheet 61869 |  | Level 19 | WIR - 0731 | Staircase 08 | opening |  |  | 0.3 | 0.3 | 0.09 | 0.085584 | 2 | 95 | 1 | 190 |  |  | Hotel | 2
30 | Sheet 61870 |  | Level 19 | WIR - 0731 | Shaft | opening |  |  | 0.3 | 0.3 | 0.09 | 0.085584 | 2 | 95 | 1 | 190 |  |  | Hotel | 2
33 | Sheet 61871 |  | Level 19 | WIR - 0168 | Outer sleeve | opening |  |  | 0.2 | 0.4 | 0.08 | 0.064791 | 1 | 95 | 1 | 95 |  |  | Hotel | 1
35 | Sheet 61871 |  | Level 19 | WIR - 0168 | Outer sleeve | opening |  |  | 0.2 | 0.4 | 0.08 | 0.066753 | 1 | 95 | 1 | 95 |  |  | Hotel | 1
12 | Sheet 61879 |  | Level 27 | WIR - 0786 | Staircase | opening |  |  | 0.3 | 0.3 | 0.09 | 0.085584 | 2 | 95 | 1 | 190 |  |  | Hotel | 2
16 | Sheet 61879 |  | Level 27 | WIR - 0786 | Lift Lobby | opening |  |  | 0.2 | 0.5 | 0.1 | 0.087734 | 2 | 95 | 1 | 190 |  |  | Hotel | 2
23 | Sheet 61879 |  | Level 27 | WIR - 0786 | Lobby | opening |  |  | 0.3 | 0.3 | 0.09 | 0.072337 | 2 | 95 | 1 | 190 |  |  | Hotel | 2
32 | Sheet 61880 |  | Level 27 | WIR - 0786 | Service Lobby | opening |  |  | 0.3 | 0.3 | 0.09 | 0.08215 | 2 | 95 | 1 | 190 |  |  | Hotel | 2
16 | Sheet 61918 | 14 | Ground Level | WIR - 01192 | Ball Room | opening |  |  | 0.2 | 0.5 | 0.1 | 0.07 | 1 | 95 | 1 | 95 | FS702/FB750 |  | Hotel | 1
21 | Sheet 61927 | 47 | Level 22 | WIR - 01254 | Housekeeping | opening |  |  | 0.3 | 0.3 | 0.09 | 0.084112 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
23 | Sheet 61927 | 48 | Level 22 | WIR - 01254 | Staircase | opening |  |  | 0.3 | 0.3 | 0.09 | 0.085584 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
10 | Sheet 61928 | 62 | Level 22 | WIR - 01254 | Corridor MEP | opening |  |  | 0.3 | 0.3 | 0.09 | 0.085584 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
12 | Sheet 61923 | 37 | Level 23 | WIR - 01253 | Housekeeping | opening |  |  | 0.3 | 0.3 | 0.09 | 0.084112 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
14 | Sheet 61923 | 38 | Level 23 | WIR - 01253 | Staircase | opening |  |  | 0.3 | 0.3 | 0.09 | 0.085584 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
29 | Sheet 61923 | 49 | Level 23 | WIR - 01253 | Lobby | opening |  |  | 0.3 | 0.3 | 0.09 | 0.085584 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
4 | Sheet 62251 |  | Level 24 |  | Outer Sleeve | opening |  |  | 0.3 | 0.3 | 0.09 | 0.085584 | 1 | 95 | 1 | 95 |  |  | Hotel | 1
1 | Sheet 62263 |  | Level 17 | WIR - 00179 | Plant Room | civil opening |  |  | 0.2 | 0.35 | 0.07 | 0.07 | 1 | 95 | 1 | 95 | FS702/FB750 | Sheet 62263 | Hotel | 1
18 | Sheet 62269 | 13 | Level 18 | WIR - 01698 | AHU Room | opening |  |  | 0.2 | 0.45 | 0.09 | 0.081169 | 1 | 95 | 1 | 95 | FS702/FB750 |  | Hotel | 1
20 | Sheet 62269 | 18 | Level 18 | WIR - 01698 | AHU Room | opening |  |  | 0.26 | 0.48 | 0.1248 | 0.0896 | 1 | 95 | 2 | 190 | FS702/FB750 |  | Hotel | 2
2 | Sheet 62253 | 9 | Level 21 | WIR - 01466 | Room 05, Corridor | opening |  |  | 0.45 | 0.5 | 0.225 | 0.065 | 1 | 95 | 1 | 95 | FS702/FB750 |  | Hotel | 1
6 | Sheet 62265 | 17 | Ground Level | WIR - 01634 | Female Toilet | opening |  |  | 0.25 | 0.3 | 0.075 | 0.075 | 2 | 95 | 3 | 570 | FS702/FB750 |  | Hotel | 6
6 | Sheet 62260 | 4 | Level 19 | WIR - 00178 | Outer Sleeve | opening |  |  | 0.25 | 0.3 | 0.075 | 0.066169 | 1 | 95 | 1 | 95 |  |  | Hotel | 1
8 | Sheet 62260 | 5 | Level 19 | WIR - 00178 | Outer Sleeve | opening |  |  | 0.2 | 0.5 | 0.1 | 0.086753 | 1 | 95 | 1 | 95 |  |  | Hotel | 1
33 | Sheet 62260 | 22 | Level 19 | WIR - 00178 | Outer Sleeve | opening |  |  | 0.2 | 0.35 | 0.07 | 0.06215 | 1 | 95 | 1 | 95 |  |  | Hotel | 1
24 | Sheet 62274 | 23 | Level 29 | WIR - 01839 | Wall | opening |  |  | 0.2 | 0.3 | 0.06 | 0.059509 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Residence | 2
14 | Sheet 62275 | 39 | Level 29 | WIR - 01839 | Corridor Entry Dr. | opening |  |  | 0.25 | 0.3 | 0.075 | 0.07 | 2 | 95 | 2 | 380 | FS702/FB750 |  | Residence | 4
23 | Sheet 62275 | 46 | Level 29 | WIR - 01839 | Lobby | opening |  |  | 0.3 | 0.3 | 0.09 | 0.085014 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Residence | 2
2 | Sheet 62280 | 1 | Ground Level | WIR - 01955 | BOH Corridor | opening |  |  | 0.38 | 0.58 | 0.2204 | 0.0704 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
6 | Sheet 62280 | 3 | Ground Level | WIR - 01955 | BOH Corridor | opening |  |  | 0.32 | 0.7 | 0.224 | 0.074 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
13 | Sheet 62281 | 35 | Ground Level | WIR - 01955 | Kitchen | opening |  |  | 0.4 | 0.6 | 0.24 | 0.09 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
4 | Sheet 62282 | 55 | Ground Level | WIR - 01955 | Window High | opening |  |  | 0.25 | 1.06 | 0.265 | 0.065 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
26 | Sheet 62282 | 75 | Ground Level | WIR - 01955 | Food Storage Rm | opening |  |  | 0.08 | 1 | 0.08 | 0.079735 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
13 | Sheet 62291 | 10 | Ground Level | WIR - 02185 | Male Toilet | opening |  |  | 0.28 | 0.6 | 0.168 | 0.068 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
13 | Sheet 62292 | 34 | Ground Level | WIR - 02185 | Male Toilet | opening |  |  | 0.3 | 0.3 | 0.09 | 0.080373 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
18 | Sheet 62292 | 37 | Ground Level | WIR - 02185 | Corridor | opening |  |  | 0.35 | 0.65 | 0.2275 | 0.1025 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
31 | Sheet 62292 | 47 | Ground Level | WIR - 02185 | Corridor | opening |  |  | 0.4 | 0.6 | 0.24 | 0.09 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
33 | Sheet 62292 | 48 | Ground Level | WIR - 02185 | Corridor | opening |  |  | 0.2 | 0.4 | 0.08 | 0.075584 | 1 | 95 | 1 | 95 | FS702/FB750 |  | Hotel | 1
10 | Sheet 62293 | 56 | Ground Level | WIR - 02185 | Male Toilet | opening |  |  | 0.2 | 0.45 | 0.09 | 0.0743 | 1 | 95 | 1 | 95 | FS702/FB750 |  | Hotel | 1
34 | Sheet 62294 | 99 | Ground Level | WIR - 02185 | Ball Room | opening |  |  | 0.25 | 0.5 | 0.125 | 0.095 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
38 | Sheet 62294 | 102 | Ground Level | WIR - 02185 | Ball Room | opening |  |  | 0.2 | 0.4 | 0.08 | 0.07215 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
5 | Sheet 62295 | 105 | Ground Level | WIR - 02185 | Ball Room | opening |  |  | 0.25 | 0.45 | 0.1125 | 0.10073 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
26 | Sheet 62295 | 121 | Ground Level | WIR - 02185 | Ball Room | opening |  |  | 0.56 | 0.76 | 0.4256 | 0.0756 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
29 | Sheet 62297 | 179 | Ground Level | WIR - 02185 | Housekeeping | opening |  |  | 0.25 | 0.3 | 0.075 | 0.055 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
32 | Sheet 62297 | 181 | Ground Level | WIR - 02185 | Housekeeping | opening |  |  | 0.3 | 0.4 | 0.12 | 0.1 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
5 | Sheet 62298 | 184 | Ground Level | WIR - 02185 | Housekeeping | opening |  |  | 0.4 | 0.5 | 0.2 | 0.08 | 1 | 95 | 1 | 95 | FS702/FB750 |  | Hotel | 1
2 | Sheet 61939 | 1 | Level 18 | WIR - 02249 | Fire Pump Room | opening |  |  | 0.3 | 0.3 | 0.09 | 0.072337 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
10 | Sheet 61939 | 8 | Level 18 | WIR - 02249 | Fire Pump Room | opening |  |  | 0.25 | 0.4 | 0.1 | 0.0843 | 1 | 95 | 1 | 95 | FS702/FB750 |  | Hotel | 1
17 | Sheet 61939 | 13 | Level 18 | WIR - 02249 | Wall | opening |  |  | 0.3 | 0.55 | 0.165 | 0.085 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
28 | Sheet 61940 | 49 | Level 18 | WIR - 02249 | Corridor | opening |  |  | 0.4 | 0.4 | 0.16 | 0.09 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
13 | Sheet 61941 | 65 | Level 18 | WIR - 02249 | Housekeeping | opening |  |  | 0.3 | 0.3 | 0.09 | 0.086075 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
3 | Sheet 61942 | 84 | Level 18 | WIR - 02249 | Stair 08 | opening |  |  | 0.3 | 0.3 | 0.09 | 0.072337 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
6 | Sheet 62289 | 5 | Level 01 | WIR - 02088 | Lift lobby | opening |  |  | 0.28 | 0.5 | 0.14 | 0.1 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
6 | Sheet 62290 | 31 | Level 01 | WIR - 02088 | MEP Work | opening |  |  | 0.23 | 0.5 | 0.115 | 0.0725 | 1 | 95 | 1 | 95 | FS702/FB750 |  | Hotel | 1
1 | Sheet 62323 |  | Level 23 | WIR - 00203/00199 | Pantry Room | civil opening |  |  | 0.08 | 1.09 | 0.0872 | 0.0872 | 2 | 95 | 1 | 190 | FS702/FB750 | Sheet 62323 | Residence | 2
24 | Sheet 62310 | 77 | Level 01 | WIR - 02537 | Corridor, Entry Dr | opening |  |  | 0.2 | 0.4 | 0.08 | 0.06 | 2 | 95 | 1 | 190 | FS702/FB750 | Sheet 62310 | Hotel | 2
28 | Sheet 62311 | 105 | Level 01 | WIR - 02537 | Entry Door | opening |  |  | 0.25 | 0.38 | 0.095 | 0.065 | 2 | 95 | 1 | 190 | FS702/FB750 | Sheet 62311 | Hotel | 2
23 | Sheet 62312 | 129 | Level 01 | WIR - 02537 | Lobby, Wall | opening |  |  | 0.3 | 0.3 | 0.09 | 0.06 | 2 | 95 | 1 | 190 | FS702/FB750 | Sheet 62312 | Hotel | 2
24 | Sheet 62312 | 130 | Level 01 | WIR - 02537 | Lobby, Wall | cable tray |  |  | 0.2 | 0.3 | 0.06 |  | 2 | 95 | 1 | 190 | FS702/FB750 | Sheet 62312 | Hotel | 2
13 | Sheet 62313 | 147 | Level 01 | WIR - 02537 | Corridor, Wall | opening |  |  | 0.2 | 0.4 | 0.08 | 0.079469 | 2 | 95 | 1 | 190 | FS702/FB750 | Sheet 62313 | Hotel | 2
9 | Sheet 62314 | 8 | Level 23 | WIR - 02536 | Female Change Rm | opening |  |  | 0.3 | 0.5 | 0.15 | 0.0943 | 2 | 95 | 1 | 190 | FS702/FB750 | Sheet 62314 | Residence | 2
11 | Sheet 62314 | 9 | Level 23 | WIR - 02536 | Female Change Rm | opening |  |  | 0.36 | 1.08 | 0.3888 | 0.0888 | 1 | 95 | 1 | 95 | FS702/FB750 | Sheet 62314 | Residence | 1
3 | Sheet 61947 | 2 | Level 12 | WIR - 02330 | Housekeeping | opening |  |  | 0.3 | 0.3 | 0.09 | 0.084112 | 1 | 95 | 1 | 95 | FS702/FB750 | Sheet 61947 | Hotel | 1
17 | Sheet 61947 | 14 | Level 12 | WIR - 02330 | Housekeeping | opening |  |  | 0.2 | 0.5 | 0.1 | 0.075 | 2 | 95 | 1 | 190 | FS702/FB750 | Sheet 61947 | Hotel | 2
22 | Sheet 61947 | 18 | Level 12 | WIR - 02330 | Housekeeping | opening |  |  | 0.2 | 0.5 | 0.1 | 0.079602 | 2 | 95 | 1 | 190 | FS702/FB750 | Sheet 61947 | Hotel | 2
3 | Sheet 61948 | 2 | Level 19 | WIR - 02329 | Housekeeping | opening |  |  | 0.3 | 0.3 | 0.09 | 0.084112 | 1 | 95 | 1 | 95 | FS702/FB750 | Sheet 61948 | Hotel | 1
16 | Sheet 61948 | 13 | Level 19 | WIR - 02329 | Housekeeping | opening |  |  | 0.25 | 0.45 | 0.1125 | 0.0775 | 2 | 95 | 1 | 190 | FS702/FB750 | Sheet 61948 | Hotel | 2
22 | Sheet 61948 | 19 | Level 19 | WIR - 02329 | Housekeeping | opening |  |  | 0.25 | 0.4 | 0.1 | 0.069602 | 2 | 95 | 1 | 190 | FS702/FB750 | Sheet 61948 | Hotel | 2
3 | Sheet 61949 | 2 | Level 20 | WIR - 02329 | Housekeeping | opening |  |  | 0.3 | 0.3 | 0.09 | 0.084112 | 1 | 95 | 1 | 95 | FS702/FB750 | Sheet 61949 | Hotel | 1
13 | Sheet 61949 | 10 | Level 20 | WIR - 02329 | Housekeeping | opening |  |  | 0.25 | 0.45 | 0.1125 | 0.0775 | 2 | 95 | 1 | 190 | FS702/FB750 | Sheet 61949 | Hotel | 2
3 | Sheet 61950 | 2 | Level 21 | WIR - 02329 | Housekeeping | opening |  |  | 0.3 | 0.3 | 0.09 | 0.084112 | 1 | 95 | 1 | 95 | FS702/FB750 | Sheet 61950 | Hotel | 1
16 | Sheet 61950 | 13 | Level 21 | WIR - 02329 | Housekeeping | opening |  |  | 0.25 | 0.45 | 0.1125 | 0.0775 | 2 | 95 | 1 | 190 | FS702/FB750 | Sheet 61950 | Hotel | 2
21 | Sheet 61950 | 17 | Level 21 | WIR - 02329 | Housekeeping | opening |  |  | 0.25 | 0.4 | 0.1 | 0.069469 | 2 | 95 | 1 | 190 | FS702/FB750 | Sheet 61950 | Hotel | 2
3 | Sheet 62301 | 2 | Level 22 | WIR - 02329 | Housekeeping | opening |  |  | 0.3 | 0.3 | 0.09 | 0.084112 | 1 | 95 | 1 | 95 | FS702/FB750 | Sheet 62301 | Hotel | 1
16 | Sheet 62301 | 13 | Level 22 | WIR - 02329 | Housekeeping | opening |  |  | 0.25 | 0.4 | 0.1 | 0.065 | 2 | 95 | 1 | 190 | FS702/FB750 | Sheet 62301 | Hotel | 2
21 | Sheet 62301 | 17 | Level 22 | WIR - 02329 | Housekeeping | opening |  |  | 0.25 | 0.4 | 0.1 | 0.069204 | 2 | 95 | 1 | 190 | FS702/FB750 | Sheet 62301 | Hotel | 2
3 | Sheet 62302 | 2 | Level 23 | WIR - 02329 | Housekeeping | opening |  |  | 0.3 | 0.3 | 0.09 | 0.084112 | 1 | 95 | 1 | 95 | FS702/FB750 | Sheet 62302 | Hotel | 1
2 | Sheet 62303 | 1 | Level 24 | WIR - 02328 | Housekeeping | opening |  |  | 0.3 | 0.3 | 0.09 | 0.086075 | 1 | 95 | 1 | 95 | FS702/FB750 | Sheet 62303 | Hotel | 1
4 | Sheet 62304 | 3 | Level 25 | WIR - 02328 | Housekeeping | opening |  |  | 0.3 | 0.3 | 0.09 | 0.083847 | 1 | 95 | 1 | 95 | FS702/FB750 | Sheet 62304 | Hotel | 1
2 | Sheet 62305 | 1 | Level 26 | WIR - 02328 | Housekeeping | opening |  |  | 0.3 | 0.3 | 0.09 | 0.086075 | 1 | 95 | 1 | 95 | FS702/FB750 | Sheet 62305 | Hotel | 1
18 | Sheet 62305 | 13 | Level 26 | WIR - 02328 | Housekeeping | opening |  |  | 0.2 | 0.5 | 0.1 | 0.075 | 2 | 95 | 1 | 190 | FS702/FB750 | Sheet 62305 | Hotel | 2
21 | Sheet 62305 | 15 | Level 26 | WIR - 02328 | Housekeeping | opening |  |  | 0.2 | 0.4 | 0.08 | 0.06 | 2 | 95 | 1 | 190 | FS702/FB750 | Sheet 62305 | Hotel | 2
3 | Sheet 62306 | 2 | Level 27 | WIR - 02328 | Housekeeping | opening |  |  | 0.3 | 0.3 | 0.09 | 0.085942 | 1 | 95 | 1 | 95 | FS702/FB750 | Sheet 62306 | Hotel | 1
20 | Sheet 62306 | 15 | Level 27 | WIR - 02328 | Housekeeping | opening |  |  | 0.2 | 0.4 | 0.08 | 0.06 | 2 | 95 | 1 | 190 | FS702/FB750 | Sheet 62306 | Hotel | 2
24 | Sheet 62306 | 18 | Level 27 | WIR - 02328 | Housekeeping | opening |  |  | 0.2 | 0.4 | 0.08 | 0.059204 | 2 | 95 | 1 | 190 | FS702/FB750 | Sheet 62306 | Hotel | 2
28 | Sheet 62306 | 21 | Level 27 | WIR - 02328 | Housekeeping | opening |  |  | 0.26 | 0.7 | 0.182 | 0.062 | 2 | 95 | 1 | 190 | FS702/FB750 | Sheet 62306 | Hotel | 2
[12 empty] | Subtotal 0.10 m |  |  |  | 18240 |  |  |  | 192
4 | Sheet 61021 |  | Level 05 | MEP-AX-WR-L5-00227 | Passanger Lift Lobby | opening |  |  | 0.75 | 0.2 | 0.15 | 0.13943 | 2 | 150 | 1 | 300 |  |  | Hotel | 2
10 | Sheet 61027 |  | Level 06 | MEP-AX-WR-L6-00532 | Entry door | opening |  |  | 0.6 | 0.2 | 0.12 | 0.11951 | 2 | 150 | 1 | 300 |  |  | Residence | 2
16 | Sheet 61864 |  | Level 26 | MEP-AX-WR-L26-00686 | Lift lobby | opening |  |  | 0.25 | 0.6 | 0.15 | 0.1397 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
17 | Sheet 61854 |  | Level 25 | MEP-AX-WR-L25-00608 | Passanger Lift | opening |  |  | 0.2 | 0.6 | 0.12 | 0.11509 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
17 | Sheet 61860 |  | Level 24 | MEP-AX-WR-L24-00588 | Lift lobby | opening |  |  | 0.2 | 0.6 | 0.12 | 0.11068 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
16 | Sheet 61861 |  | Basement 01 | MEP-AX-WR-B1-00849 | CEF Room | opening |  |  | 0.25 | 0.5 | 0.125 | 0.11715 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Residence | 2
17 | Sheet 61869 |  | Level 19 | WIR - 0731 | Lift Lobby | opening |  |  | 0.25 | 0.6 | 0.15 | 0.1397 | 2 | 150 | 1 | 300 |  |  | Hotel | 2
10 | Sheet 61879 |  | Level 27 | WIR - 0786 | Housekeeping | opening |  |  | 0.3 | 0.4 | 0.12 | 0.11509 | 2 | 150 | 1 | 300 |  |  | Hotel | 2
21 | Sheet 61879 |  | Level 27 | WIR - 0786 | Water Meter Room | opening |  |  | 0.3 | 0.6 | 0.18 | 0.15007 | 2 | 150 | 1 | 300 |  |  | Hotel | 2
6 | Sheet 61920 | 5 | Level 01 | WIR - 01191 | Plant Room | opening |  |  | 0.4 | 0.4 | 0.16 | 0.12 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
9 | Sheet 61920 | 5 | Level 01 | WIR - 01191 | Plant Room | opening |  |  | 0.3 | 0.5 | 0.15 | 0.14117 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
18 | Sheet 61918 | 16 | Ground Level | WIR - 01192 | Ball Room | opening |  |  | 0.4 | 0.4 | 0.16 | 0.14234 | 1 | 150 | 1 | 150 | FS702/FB750 |  | Hotel | 1
29 | Sheet 61918 | 26 | Ground Level | WIR - 01192 | Ball Room | opening |  |  | 0.25 | 0.8 | 0.2 | 0.15 | 1 | 150 | 1 | 150 | FS702/FB750 |  | Hotel | 1
17 | Sheet 61919 | 42 | Ground Level | WIR - 01192 | Ball Room | opening |  |  | 0.25 | 0.7 | 0.175 | 0.135 | 1 | 150 | 1 | 150 | FS702/FB750 |  | Hotel | 1
5 | Sheet 61933 | 3 | Level 09 | WIR - 01416 | Corridor | opening |  |  | 0.3 | 0.6 | 0.18 | 0.13683 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Residence | 2
26 | Sheet 61927 | 51 | Level 22 | WIR - 01254 | Lobby | opening |  |  | 0.2 | 0.6 | 0.12 | 0.11117 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
4 | Sheet 61928 | 57 | Level 22 | WIR - 01254 | Corridor MEP | opening |  |  | 0.35 | 0.4 | 0.14 | 0.12528 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
17 | Sheet 61923 | 40 | Level 23 | WIR - 01253 | Lobby | opening |  |  | 0.2 | 0.6 | 0.12 | 0.11166 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
6 | Sheet 62251 |  | Level 24 |  | Outer Sleeve | opening |  |  | 0.3 | 0.4 | 0.12 | 0.11951 | 1 | 150 | 1 | 150 |  |  | Hotel | 1
14 | Sheet 61930 | 13 | Level 22 | WIR - 00175 | Corridor Out. Sleeve | opening |  |  | 0.1 | 1.7 | 0.17 | 0.14645 | 1 | 150 | 1 | 150 | FS702/FB750 |  | Hotel | 1
17 | Sheet 61925 | 16 | Level 23 | WIR - 00176 | Corridor Out. Sleeve | opening |  |  | 0.2 | 0.7 | 0.14 | 0.11449 | 1 | 150 | 1 | 150 | FS702/FB750 |  | Hotel | 1
13 | Sheet 62261 | 21 | Level 17 | WIR - 01579 | Plant Room | opening |  |  | 0.4 | 0.4 | 0.16 | 0.14234 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
16 | Sheet 62269 | 12 | Level 18 | WIR - 01698 | AHU Room | opening |  |  | 0.2 | 0.6 | 0.12 | 0.11117 | 1 | 150 | 1 | 150 | FS702/FB750 |  | Hotel | 1
9 | Sheet 62256 | 7 | Level 21 | WIR - 00177 | Shaft | opening |  |  | 0.3 | 0.4 | 0.12 | 0.11558 | 1 | 150 | 1 | 150 |  |  | Hotel | 1
21 | Sheet 62260 | 15 | Level 19 | WIR - 00178 | Outer Sleeve | opening |  |  | 0.4 | 0.4 | 0.16 | 0.1443 | 1 | 150 | 1 | 150 |  |  | Hotel | 1
27 | Sheet 62274 | 25 | Level 29 | WIR - 01839 | FTR work | opening |  |  | 0.2 | 0.75 | 0.15 | 0.13 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Residence | 2
30 | Sheet 62275 | 52 | Level 29 | WIR - 01839 | Corridor Entry Dr. | opening |  |  | 0.26 | 0.3 | 0.078 | 0.114 | 2 | 150 | 3 | 900 | FS702/FB750 |  | Residence | 6
9 | Sheet 62276 | 62 | Level 29 | WIR - 01839 | Water Meter Rm | opening |  |  | 0.25 | 0.6 | 0.15 | 0.14545 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Residence | 2
2 | Sheet 62281 | 26 | Ground Level | WIR - 01955 | Kitchen | opening |  |  | 0.4 | 0.4 | 0.16 | 0.12765 | 1 | 150 | 1 | 150 | FS702/FB750 |  | Hotel | 1
2 | Sheet 62282 | 54 | Ground Level | WIR - 01955 | Window High | opening |  |  | 0.3 | 1.15 | 0.345 | 0.145 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
15 | Sheet 62282 | 65 | Ground Level | WIR - 01955 | Window High | opening |  |  | 0.35 | 1.08 | 0.378 | 0.128 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
24 | Sheet 62282 | 74 | Ground Level | WIR - 01955 | Food Storage Rm | opening |  |  | 0.3 | 0.6 | 0.18 | 0.15 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
6 | Sheet 62292 | 29 | Ground Level | WIR - 02185 | Male Toilet | opening |  |  | 0.4 | 0.4 | 0.16 | 0.13519 | 1 | 150 | 1 | 150 | FS702/FB750 |  | Hotel | 1
22 | Sheet 62292 | 40 | Ground Level | WIR - 02185 | Corridor | opening |  |  | 0.3 | 0.8 | 0.24 | 0.12 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
12 | Sheet 62293 | 57 | Ground Level | WIR - 02185 | Male Toilet | opening |  |  | 0.3 | 0.45 | 0.135 | 0.1193 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
25 | Sheet 62293 | 68 | Ground Level | WIR - 02185 | Corridor | opening |  |  | 0.35 | 1.18 | 0.413 | 0.138 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
31 | Sheet 62293 | 73 | Ground Level | WIR - 02185 | Corridor | opening |  |  | 0.25 | 0.5 | 0.125 | 0.105 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
5 | Sheet 62294 | 78 | Ground Level | WIR - 02185 | Ball Room | opening |  |  | 0.25 | 0.5 | 0.125 | 0.105 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
17 | Sheet 62294 | 86 | Ground Level | WIR - 02185 | Ball Room | opening |  |  | 0.46 | 1.5 | 0.69 | 0.13 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
27 | Sheet 62294 | 93 | Ground Level | WIR - 02185 | Ball Room | opening |  |  | 0.25 | 0.8 | 0.2 | 0.1125 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
2 | Sheet 62295 | 103 | Ground Level | WIR - 02185 | Ball Room | opening |  |  | 0.3 | 0.5 | 0.15 | 0.14215 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
17 | Sheet 62295 | 115 | Ground Level | WIR - 02185 | Ball Room | opening |  |  | 0.3 | 0.45 | 0.135 | 0.10949 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
6 | Sheet 62296 | 134 | Ground Level | WIR - 02185 | Ball Room | opening |  |  | 0.15 | 1 | 0.15 | 0.14828 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
8 | Sheet 62296 | 135 | Ground Level | WIR - 02185 | Ball Room | opening |  |  | 0.42 | 1.1 | 0.462 | 0.112 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
23 | Sheet 62297 | 174 | Ground Level | WIR - 02185 | Housekeeping | opening |  |  | 0.3 | 0.5 | 0.15 | 0.11 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
8 | Sheet 62298 | 186 | Ground Level | WIR - 02185 | Housekeeping | opening |  |  | 0.5 | 0.7 | 0.35 | 0.11 | 1 | 150 | 1 | 150 | FS702/FB750 |  | Hotel | 1
15 | Sheet 62298 | 190 | Ground Level | WIR - 02185 | Corridor | opening |  |  | 0.4 | 1.08 | 0.432 | 0.132 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
30 | Sheet 61941 | 78 | Level 18 | WIR - 02249 | Housekeeping | opening |  |  | 0.3 | 0.6 | 0.18 | 0.13 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
9 | Sheet 62308 | 8 | Level 01 | WIR - 02537 | Entry Door | opening |  |  | 0.3 | 0.4 | 0.12 | 0.11117 | 2 | 150 | 1 | 300 | FS702/FB750 | Sheet 62308 | Hotel | 2
16 | Sheet 62308 | 14 | Level 01 | WIR - 02537 | Entry Door | opening |  |  | 0.2 | 0.9 | 0.18 | 0.14175 | 2 | 150 | 1 | 300 | FS702/FB750 | Sheet 62308 | Hotel | 2
10 | Sheet 62311 | 91 | Level 01 | WIR - 02537 | Water Meter Rm | opening |  |  | 0.3 | 0.4 | 0.12 | 0.11411 | 2 | 150 | 1 | 300 | FS702/FB750 | Sheet 62311 | Hotel | 2
33 | Sheet 62311 | 109 | Level 01 | WIR - 02537 | Entry Door | opening |  |  | 0.25 | 0.5 | 0.125 | 0.105 | 2 | 150 | 1 | 300 | FS702/FB750 | Sheet 62311 | Hotel | 2
11 | Sheet 62312 | 119 | Level 01 | WIR - 02537 | Lobby, Wall | opening |  |  | 0.2 | 0.8 | 0.16 | 0.115 | 1 | 150 | 1 | 150 | FS702/FB750 | Sheet 62312 | Hotel | 1
32 | Sheet 62312 | 137 | Level 01 | WIR - 02537 | Plant room | opening |  |  | 0.24 | 0.6 | 0.144 | 0.10867 | 2 | 150 | 1 | 300 | FS702/FB750 | Sheet 62312 | Hotel | 2
10 | Sheet 61944 | 9 | Level 23 | WIR - 02411 | Pantry Room | opening |  |  | 0.3 | 0.5 | 0.15 | 0.13283 | 2 | 150 | 1 | 300 | FS702/FB750 | Sheet 61944 | Residence | 2
20 | Sheet 61944 | 17 | Level 23 | WIR - 02411 | Pantry Room | opening |  |  | 0.25 | 0.6 | 0.15 | 0.13 | 2 | 150 | 1 | 300 | FS702/FB750 | Sheet 61944 | Residence | 2
28 | Sheet 62314 | 22 | Level 23 | WIR - 02536 | Male Change Rm | opening |  |  | 0.35 | 0.74 | 0.259 | 0.1533 | 2 | 150 | 1 | 300 | FS702/FB750 | Sheet 62314 | Residence | 2
9 | Sheet 62316 | 8 | Level 28 | WIR - 02557 | Gym Room | opening |  |  | 0.48 | 0.6 | 0.288 | 0.128 | 1 | 150 | 1 | 150 | FS702/FB750 | Sheet 62316 | Hotel | 1
11 | Sheet 62316 | 9 | Level 28 | WIR - 02557 | Gym Room | opening |  |  | 0.48 | 0.6 | 0.288 | 0.128 | 1 | 150 | 1 | 150 | FS702/FB750 | Sheet 62316 | Hotel | 1
15 | Sheet 62316 | 11 | Level 28 | WIR - 02557 | Gym Room | opening |  |  | 0.68 | 0.88 | 0.5984 | 0.1184 | 1 | 150 | 1 | 150 | FS702/FB750 | Sheet 62316 | Hotel | 1
19 | Sheet 62316 | 13 | Level 28 | WIR - 02557 | Gym Room | opening |  |  | 0.7 | 0.7 | 0.49 | 0.13 | 2 | 150 | 1 | 300 | FS702/FB750 | Sheet 62316 | Hotel | 2
25 | Sheet 62316 | 18 | Level 28 | WIR - 02557 | Gym Room | opening |  |  | 0.48 | 0.6 | 0.288 | 0.128 | 2 | 150 | 1 | 300 | FS702/FB750 | Sheet 62316 | Hotel | 2
27 | Sheet 62316 | 19 | Level 28 | WIR - 02557 | Gym Room | opening |  |  | 0.46 | 1 | 0.46 | 0.14 | 2 | 150 | 1 | 300 | FS702/FB750 | Sheet 62316 | Hotel | 2
17 | Sheet 62302 | 14 | Level 23 | WIR - 02329 | Housekeeping | opening |  |  | 0.4 | 0.4 | 0.16 | 0.125 | 2 | 150 | 1 | 300 | FS702/FB750 | Sheet 62302 | Hotel | 2
20 | Sheet 62304 | 15 | Level 25 | WIR - 02328 | Housekeeping | opening |  |  | 0.25 | 0.5 | 0.125 | 0.105 | 2 | 150 | 1 | 300 | FS702/FB750 | Sheet 62304 | Hotel | 2
36 | Sheet 62306 | 28 | Level 27 | WIR - 02328 | Housekeeping | opening |  |  | 0.3 | 0.9 | 0.27 | 0.11 | 1 | 150 | 1 | 150 | FS702/FB750 | Sheet 62306 | Hotel | 1
[12 empty] | Subtotal 0.15 m |  |  |  | 17850 |  |  |  | 119
32 | Sheet 61907 | 24 | Level 29 | WIR - 01160 | Male Toilet | opening |  |  | 0.2 | 0.8 | 0.16 | 0.15951 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2
20 | Sheet 61910 | 16 | Basement 01 | WIR - 0977 | Corridor, Entry D. | opening |  |  | 0.35 | 0.6 | 0.21 | 0.19009 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2
19 | Sheet 61031 |  | Level 06 | MEP-AX-WR-L6-00532 | Entry door | opening |  |  | 0.8 | 0.3 | 0.24 | 0.21298 | 2 | 180 | 1 | 360 |  |  | Residence | 2
7 | Sheet 61038 |  | Level 04 | MEP-AX-WR-L4-00531 | Chill Room | opening |  |  | 0.6 | 0.35 | 0.21 | 0.19992 | 2 | 180 | 1 | 360 |  |  | Residence | 2
20 | Sheet 61864 |  | Level 26 | MEP-AX-WR-L26-00686 | Water M. Room | opening |  |  | 0.3 | 0.8 | 0.24 | 0.21007 | 1 | 180 | 1 | 180 | FS702/FB750 |  | Hotel | 1
25 | Sheet 61864 |  | Level 26 | MEP-AX-WR-L26-00686 | Room Service | opening |  |  | 0.4 | 0.6 | 0.24 | 0.21252 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2
21 | Sheet 61855 |  | Level 25 | MEP-AX-WR-L25-00608 | Water M. Room | opening |  |  | 0.3 | 0.8 | 0.24 | 0.21007 | 1 | 180 | 1 | 180 | FS702/FB750 |  | Hotel | 1
26 | Sheet 61855 |  | Level 25 | MEP-AX-WR-L25-00608 | Lift lobby | opening |  |  | 0.4 | 0.6 | 0.24 | 0.21792 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2
21 | Sheet 61860 |  | Level 24 | MEP-AX-WR-L24-00588 | Water M. Room | opening |  |  | 0.3 | 0.8 | 0.24 | 0.21007 | 1 | 180 | 1 | 180 | FS702/FB750 |  | Hotel | 1
26 | Sheet 61860 |  | Level 24 | MEP-AX-WR-L24-00588 | Room Service | opening |  |  | 0.4 | 0.6 | 0.24 | 0.214 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2
23 | Sheet 61861 |  | Basement 01 | MEP-AX-WR-B1-00849 | CEF Room | opening |  |  | 0.4 | 0.5 | 0.2 | 0.175 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Residence | 2
19 | Sheet 61869 |  | Level 19 | WIR - 0731 | Water Meter Room | opening |  |  | 0.3 | 0.8 | 0.24 | 0.22675 | 2 | 180 | 1 | 360 |  |  | Hotel | 2
28 | Sheet 61879 |  | Level 27 | WIR - 0786 | Lobby | opening |  |  | 0.4 | 0.6 | 0.24 | 0.21154 | 2 | 180 | 1 | 360 |  |  | Hotel | 2
4 | Sheet 61918 | 3 | Ground Level | WIR - 01192 | Ball Room | opening |  |  | 0.86 | 0.95 | 0.817 | 0.177 | 1 | 180 | 1 | 180 | FS702/FB750 |  | Hotel | 1
31 | Sheet 61927 | 54 | Level 22 | WIR - 01254 | Water M. Room | opening |  |  | 0.3 | 0.8 | 0.24 | 0.22234 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2
21 | Sheet 61923 | 43 | Level 23 | WIR - 01253 | Water M. Room | opening |  |  | 0.3 | 0.8 | 0.24 | 0.22332 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2
25 | Sheet 61923 | 46 | Level 23 | WIR - 01253 | Lobby | opening |  |  | 0.4 | 0.55 | 0.22 | 0.20283 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2
3 | Sheet 62252 |  | Level 08 |  | Outer Sleeve | opening |  |  | 0.3 | 0.7 | 0.21 | 0.18105 | 1 | 180 | 1 | 180 |  |  | Hotel | 1
17 | Sheet 61930 | 15 | Level 22 | WIR - 00175 | Corridor Out. Sleeve | opening |  |  | 0.4 | 0.8 | 0.32 | 0.22755 | 1 | 180 | 1 | 180 | FS702/FB750 |  | Hotel | 1
7 | Sheet 62269 | 5 | Level 18 | WIR - 01698 | AHU Room | opening |  |  | 0.5 | 0.85 | 0.425 | 0.185 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2
8 | Sheet 62253 | 21 | Level 21 | WIR - 01466 | Room 05, Corridor | opening |  |  | 0.5 | 0.5 | 0.25 | 0.21676 | 1 | 180 | 1 | 180 | FS702/FB750 |  | Hotel | 1
2 | Sheet 62266 | 33 | Ground Level | WIR - 01634 | Female Toilet | opening |  |  | 0.4 | 0.4 | 0.16 | 0.21 | 2 | 180 | 3 | 1080 | FS702/FB750 |  | Hotel | 6
6 | Sheet 62256 | 5 | Level 21 | WIR - 00177 | Entry Door | opening |  |  | 0.25 | 1 | 0.25 | 0.23675 | 1 | 180 | 1 | 180 |  |  | Hotel | 1
14 | Sheet 62256 | 11 | Level 21 | WIR - 00177 | Room Entry Door | opening |  |  | 0.38 | 0.65 | 0.247 | 0.22247 | 2 | 180 | 1 | 360 |  |  | Hotel | 2
18 | Sheet 62256 | 14 | Level 21 | WIR - 00177 | Room Entry Door | opening |  |  | 0.2 | 1 | 0.2 | 0.18613 | 2 | 180 | 1 | 360 |  |  | Hotel | 2
4 | Sheet 62260 | 3 | Level 19 | WIR - 00178 | Outer Sleeve | opening |  |  | 0.3 | 0.8 | 0.24 | 0.21449 | 1 | 180 | 1 | 180 |  |  | Hotel | 1
20 | Sheet 62280 | 15 | Ground Level | WIR - 01955 | BOH Corridor | opening |  |  | 0.25 | 1.2 | 0.3 | 0.2075 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2
24 | Sheet 62280 | 18 | Ground Level | WIR - 01955 | BOH Corridor | opening |  |  | 0.25 | 1 | 0.25 | 0.195 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2
31 | Sheet 62280 | 24 | Ground Level | WIR - 01955 | BOH Corridor | opening |  |  | 0.4 | 0.8 | 0.32 | 0.15916 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2
19 | Sheet 62281 | 40 | Ground Level | WIR - 01955 | Kitchen | opening |  |  | 0.3 | 1.4 | 0.42 | 0.24 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2
2 | Sheet 62294 | 76 | Ground Level | WIR - 02185 | Ball Room | opening |  |  | 0.6 | 1.5 | 0.9 | 0.2 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2
22 | Sheet 62295 | 119 | Ground Level | WIR - 02185 | Ball Room | opening |  |  | 0.75 | 1.1 | 0.825 | 0.175 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2
7 | Sheet 62297 | 161 | Ground Level | WIR - 02185 | Housekeeping | opening |  |  | 0.5 | 0.8 | 0.4 | 0.22911 | 1 | 180 | 1 | 180 | FS702/FB750 |  | Hotel | 1
11 | Sheet 62297 | 164 | Ground Level | WIR - 02185 | Housekeeping | opening |  |  | 0.25 | 0.9 | 0.225 | 0.17451 | 1 | 180 | 1 | 180 | FS702/FB750 |  | Hotel | 1
10 | Sheet 62298 | 187 | Ground Level | WIR - 02185 | Housekeeping | opening |  |  | 0.6 | 0.8 | 0.48 | 0.24 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2
3 | Sheet 61941 | 56 | Level 18 | WIR - 02249 | Corridor | opening |  |  | 0.4 | 0.5 | 0.2 | 0.17 | 1 | 180 | 1 | 180 | FS702/FB750 |  | Hotel | 1
27 | Sheet 61941 | 76 | Level 18 | WIR - 02249 | Housekeeping | opening |  |  | 0.5 | 0.5 | 0.25 | 0.195 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2
8 | Sheet 61942 | 88 | Level 18 | WIR - 02249 | Lift lobby | opening |  |  | 0.25 | 0.8 | 0.2 | 0.19452 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2
11 | Sheet 61942 | 90 | Level 18 | WIR - 02249 | Water M. Room | opening |  |  | 0.3 | 0.6 | 0.18 | 0.16921 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2
8 | Sheet 62310 | 61 | Level 01 | WIR - 02537 | Housekeeping | opening |  |  | 0.4 | 0.5 | 0.2 | 0.16 | 2 | 180 | 1 | 360 | FS702/FB750 | Sheet 62310 | Hotel | 2
30 | Sheet 62310 | 82 | Level 01 | WIR - 02537 | Corridor, Entry Dr | opening |  |  | 0.25 | 0.8 | 0.2 | 0.165 | 2 | 180 | 1 | 360 | FS702/FB750 | Sheet 62310 | Hotel | 2
15 | Sheet 61944 | 13 | Level 23 | WIR - 02411 | Pantry Room | opening |  |  | 0.4 | 0.7 | 0.28 | 0.23682 | 2 | 180 | 1 | 360 | FS702/FB750 | Sheet 61944 | Residence | 2
17 | Sheet 62314 | 13 | Level 23 | WIR - 02536 | Female Change Rm | opening |  |  | 0.4 | 0.4 | 0.16 | 0.15554 | 2 | 180 | 1 | 360 | FS702/FB750 | Sheet 62314 | Residence | 2
22 | Sheet 62314 | 17 | Level 23 | WIR - 02536 | Male Change Rm | opening |  |  | 0.3 | 0.7 | 0.21 | 0.16683 | 2 | 180 | 1 | 360 | FS702/FB750 | Sheet 62314 | Residence | 2
33 | Sheet 62314 | 25 | Level 23 | WIR - 02536 | Male Change Rm | opening |  |  | 0.4 | 0.5 | 0.2 | 0.16 | 2 | 180 | 1 | 360 | FS702/FB750 | Sheet 62314 | Residence | 2
23 | Sheet 62315 | 49 | Level 23 | WIR - 02536 | Meeting Room | opening |  |  | 0.25 | 0.7 | 0.175 | 0.16322 | 2 | 180 | 1 | 360 | FS702/FB750 | Sheet 62315 | Residence | 2
10 | Sheet 61945 |  | Level 23 | WIR - 02390 | Corridor, Entry Dr | opening |  |  | 0.5 | 1.08 | 0.54 | 0.23019 | 1 | 180 | 1 | 180 | FS702/FB750 | Sheet 61945 | Hotel | 1
21 | Sheet 62303 | 16 | Level 24 | WIR - 02328 | Housekeeping | opening |  |  | 0.4 | 0.6 | 0.24 | 0.16973 | 2 | 180 | 1 | 360 | FS702/FB750 | Sheet 62303 | Hotel | 2
12 | Sheet 62305 | 9 | Level 26 | WIR - 02328 | Housekeeping | opening |  |  | 0.4 | 0.6 | 0.24 | 0.23 | 2 | 180 | 1 | 360 | FS702/FB750 | Sheet 62305 | Hotel | 2
18 | Sheet 62306 | 14 | Level 27 | WIR - 02328 | Housekeeping | opening |  |  | 0.4 | 0.5 | 0.2 | 0.185 | 2 | 180 | 1 | 360 | FS702/FB750 | Sheet 62306 | Hotel | 2
10 | Sheet 62325 | 9 | Level 12 | WIR - 02579 | Room Service | opening |  |  | 0.4 | 0.6 | 0.24 | 0.21762 | 1 | 180 | 1 | 180 | FS702/FB750 | Sheet 62325 | Hotel | 1
18 | Sheet 62325 | 16 | Level 12 | WIR - 02579 | Water Meter Rm | opening |  |  | 0.3 | 0.8 | 0.24 | 0.22234 | 1 | 180 | 1 | 180 | FS702/FB750 | Sheet 62325 | Hotel | 1
14 | Sheet 62326 | 13 | Level 08 | WIR - 02579 | Room Service | opening |  |  | 0.4 | 0.5 | 0.2 | 0.16754 | 1 | 180 | 1 | 180 | FS702/FB750 | Sheet 62326 | Hotel | 1
22 | Sheet 62326 | 20 | Level 08 | WIR - 02579 | Water Meter Rm | opening |  |  | 0.3 | 0.8 | 0.24 | 0.22234 | 1 | 180 | 1 | 180 | FS702/FB750 | Sheet 62326 | Hotel | 1
10 | Sheet 62327 | 9 | Level 07 | WIR - 02579 | Room Service | opening |  |  | 0.4 | 0.6 | 0.24 | 0.21762 | 1 | 180 | 1 | 180 | FS702/FB750 | Sheet 62327 | Hotel | 1
18 | Sheet 62327 | 16 | Level 07 | WIR - 02579 | Water Meter Rm | opening |  |  | 0.3 | 0.8 | 0.24 | 0.22234 | 1 | 180 | 1 | 180 | FS702/FB750 | Sheet 62327 | Hotel | 1
12 | Sheet 62320 | 10 | Level 09 | WIR - 02558 | Room Service | opening |  |  | 0.4 | 0.5 | 0.2 | 0.18703 | 1 | 180 | 1 | 180 | FS702/FB750 | Sheet 62320 | Hotel | 1
[12 empty] | Subtotal 0.25 m |  |  |  | 17640 |  |  |  | 98
12 | Sheet 61861 |  | Basement 01 | MEP-AX-WR-B1-00849 | CEF Room | opening |  |  | 1.6 | 1.7 | 2.72 | 0.32 | 1 | 245 | 1 | 245 | FS702/FB750 |  | Residence | 1
25 | Sheet 61869 | 25 | Level 19 | WIR - 0731 | Lobby | opening |  |  | 0.4 | 0.8 | 0.32 | 0.30528 | 2 | 245 | 1 | 490 |  |  | Hotel | 2
7 | Sheet 62261 | 14 | Level 17 | WIR - 01579 | Plant Room | opening |  |  | 0.88 | 0.88 | 0.7744 | 0.3144 | 2 | 245 | 1 | 490 | FS702/FB750 |  | Hotel | 2
16 | Sheet 62261 | 25 | Level 17 | WIR - 01579 | Plant Room | opening |  |  | 0.7 | 1.85 | 1.295 | 0.32435 | 2 | 245 | 1 | 490 | FS702/FB750 |  | Hotel | 2
5 | Sheet 62275 | 31 | Level 29 | WIR - 01839 | Housekeeping | opening |  |  | 0.4 | 0.8 | 0.32 | 0.31113 | 2 | 245 | 1 | 490 | FS702/FB750 |  | Residence | 2
33 | Sheet 62281 | 53 | Ground Level | WIR - 01955 | Kitchen | opening |  |  | 0.4 | 0.8 | 0.32 | 0.28532 | 1 | 245 | 1 | 245 | FS702/FB750 |  | Hotel | 1
27 | Sheet 62292 | 44 | Ground Level | WIR - 02185 | Corridor | opening |  |  | 0.5 | 0.6 | 0.3 | 0.2675 | 2 | 245 | 1 | 490 | FS702/FB750 |  | Hotel | 2
33 | Sheet 62293 | 74 | Ground Level | WIR - 02185 | Corridor | opening |  |  | 0.55 | 1.7 | 0.935 | 0.335 | 2 | 245 | 1 | 490 | FS702/FB750 |  | Hotel | 2
7 | Sheet 62294 | 79 | Ground Level | WIR - 02185 | Ball Room | opening |  |  | 0.55 | 1.7 | 0.935 | 0.335 | 2 | 245 | 1 | 490 | FS702/FB750 |  | Hotel | 2
21 | Sheet 62294 | 88 | Ground Level | WIR - 02185 | Ball Room | opening |  |  | 0.55 | 0.6 | 0.33 | 0.31234 | 2 | 245 | 1 | 490 | FS702/FB750 |  | Hotel | 2
24 | Sheet 62295 | 120 | Ground Level | WIR - 02185 | Ball Room | opening |  |  | 0.6 | 0.75 | 0.45 | 0.3206 | 2 | 245 | 1 | 490 | FS702/FB750 |  | Hotel | 2
7 | Sheet 61940 | 33 | Level 18 | WIR - 02249 | Fire Pump Room | opening |  |  | 0.4 | 0.8 | 0.32 | 0.28468 | 2 | 245 | 1 | 490 | FS702/FB750 |  | Hotel | 2
13 | Sheet 62316 | 10 | Level 28 | WIR - 02557 | Gym Room | opening |  |  | 0.85 | 0.88 | 0.748 | 0.268 | 1 | 245 | 1 | 245 | FS702/FB750 | Sheet 62316 | Hotel | 1
19 | Sheet 62320 | 16 | Level 09 | WIR - 02558 | Water Meter Rm | opening |  |  | 0.35 | 0.8 | 0.28 | 0.26921 | 1 | 245 | 1 | 245 | FS702/FB750 | Sheet 62320 | Hotel | 1
[12 empty] | Subtotal 0.35 m |  |  |  | 5880 |  |  |  | 24
7 | Sheet 61906 |  | Level 23 | WIR - 00892 | Water Meter Room | opening |  |  | 0.35 | 1.65 | 0.5775 | 0.49952 | 2 | 310 | 1 | 620 | FS702/FB750/FP302/FS709 |  | Residence | 2
5 | Sheet 61908 | 29 | Level 29 | WIR - 01160 | Male Toilet | opening |  |  | 0.25 | 1.5 | 0.375 | 0.36206 | 2 | 310 | 1 | 620 | FS702/FB750/FS709 |  | Hotel | 2
4 | Sheet 61910 | 3 | Basement 01 | WIR - 0977 | Corridor, Entry D. | opening |  |  | 0.6 | 0.8 | 0.48 | 0.44 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Hotel | 2
7 | Sheet 61912 |  | Level 13 |  | Water Meter Room | opening |  |  | 0.35 | 1.65 | 0.5775 | 0.49952 | 2 | 310 | 1 | 620 | FS702/FB750/FP302/FS709 |  | Residence | 2
18 | Sheet 61039 |  | Level 04 | MEP-AX-WR-L4-00531 | FTR Room | opening |  |  | 1.1 | 0.4 | 0.44 | 0.39528 | 2 | 310 | 1 | 620 |  |  | Residence | 2
8 | Sheet 61863 |  | Level 26 | MEP-AX-WR-L26-00686 | Housekeeping | opening |  |  | 0.6 | 0.9 | 0.54 | 0.47764 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Hotel | 2
7 | Sheet 61854 |  | Level 25 | MEP-AX-WR-L25-00608 | Housekeeping | opening |  |  | 0.6 | 0.9 | 0.54 | 0.50402 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Hotel | 2
7 | Sheet 61859 |  | Level 24 | MEP-AX-WR-L24-00588 | Housekeeping | opening |  |  | 0.6 | 0.9 | 0.54 | 0.48058 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Hotel | 2
8 | Sheet 61861 |  | Basement 01 | MEP-AX-WR-B1-00849 | Fresh Air plenum | opening |  |  | 0.9 | 2.1 | 1.89 | 0.39 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Residence | 2
10 | Sheet 61861 |  | Basement 01 | MEP-AX-WR-B1-00849 | Fresh Air plenum | opening |  |  | 0.9 | 2.15 | 1.935 | 0.435 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Residence | 2
14 | Sheet 61861 |  | Basement 01 | MEP-AX-WR-B1-00849 | CEF Room | opening |  |  | 1.6 | 1.8 | 2.88 | 0.48 | 1 | 310 | 1 | 310 | FS702/FB750 |  | Residence | 1
7 | Sheet 61879 |  | Level 27 | WIR - 0786 | Housekeeping | opening |  |  | 0.6 | 0.9 | 0.54 | 0.47862 | 2 | 310 | 1 | 620 |  |  | Hotel | 2
18 | Sheet 61927 | 45 | Level 22 | WIR - 01254 | Housekeeping | opening |  |  | 0.6 | 0.9 | 0.54 | 0.48255 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Hotel | 2
9 | Sheet 61923 | 35 | Level 23 | WIR - 01253 | Housekeeping | opening |  |  | 0.6 | 0.9 | 0.54 | 0.48251 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Hotel | 2
9 | Sheet 62261 | 15 | Level 17 | WIR - 01579 | Plant Room | opening |  |  | 1.05 | 1.45 | 1.5225 | 0.4425 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Hotel | 2
11 | Sheet 62261 | 20 | Level 17 | WIR - 01579 | Plant Room | opening |  |  | 1 | 2.5 | 2.5 | 0.43 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Hotel | 2
4 | Sheet 62253 | 18 | Level 21 | WIR - 01466 | Room 05, Corridor | opening |  |  | 0.4 | 1.7 | 0.68 | 0.36 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Hotel | 2
9 | Sheet 62278 |  | Level 27 | WIR - 00187 | Corridor Shaft 03 | opening |  |  | 0.55 | 1.15 | 0.6325 | 0.48605 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Residence | 2
14 | Sheet 62278 |  | Level 22 | WIR - 00186 | Corridor Shaft 03 | opening |  |  | 0.7 | 0.9 | 0.63 | 0.48329 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Residence | 2
26 | Sheet 62278 |  | Level 06 | WIR - 00183 | Corridor Shaft 03 | opening |  |  | 0.65 | 1 | 0.65 | 0.50329 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Residence | 2
13 | Sheet 62294 | 84 | Ground Level | WIR - 02185 | Ball Room | opening |  |  | 0.6 | 1.5 | 0.9 | 0.5 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Hotel | 2
19 | Sheet 62294 | 87 | Ground Level | WIR - 02185 | Ball Room | opening |  |  | 1 | 1.5 | 1.5 | 0.38 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Hotel | 2
9 | Sheet 62295 | 108 | Ground Level | WIR - 02185 | Ball Room | opening |  |  | 0.41 | 0.98 | 0.4018 | 0.39395 | 1 | 310 | 1 | 310 | FS702/FB750 |  | Hotel | 1
18 | Sheet 62296 | 144 | Ground Level | WIR - 02185 | Lobby | opening |  |  | 0.6 | 0.9 | 0.54 | 0.45807 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Hotel | 2
3 | Sheet 62298 | 183 | Ground Level | WIR - 02185 | Housekeeping | opening |  |  | 0.5 | 1.3 | 0.65 | 0.4 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Hotel | 2
31 | Sheet 61939 | 24 | Level 18 | WIR - 02249 | Wall | opening |  |  | 0.58 | 4.6 | 2.668 | 0.418 | 1 | 310 | 1 | 310 | FS702/FB750 |  | Hotel | 1
34 | Sheet 61939 | 26 | Level 18 | WIR - 02249 | Entry door | opening |  |  | 0.4 | 2 | 0.8 | 0.47 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Hotel | 2
11 | Sheet 61940 | 35 | Level 18 | WIR - 02249 | Wall | opening |  |  | 0.4 | 1.7 | 0.68 | 0.44 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Hotel | 2
22 | Sheet 61941 | 72 | Level 18 | WIR - 02249 | Housekeeping | opening |  |  | 0.6 | 0.9 | 0.54 | 0.44255 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Hotel | 2
4 | Sheet 62288 | 29 | Ground Level | WIR - 0194 | Staircase 04 | opening |  |  | 0.45 | 1.3 | 0.585 | 0.5 | 1 | 310 | 1 | 310 | FS702 |  | Residence | 1
8 | Sheet 62288 | 33 | Ground Level | WIR - 0194 | Staircase 04 | opening |  |  | 0.34 | 1.38 | 0.4692 | 0.3838 | 1 | 310 | 1 | 310 | FS702 |  | Residence | 1
4 | Sheet 62324 |  | Basement 01 | WIR - 00198 | FTR Room | opening |  |  | 0.4 | 1.2 | 0.48 | 0.42 | 1 | 310 | 1 | 310 | FS702/FB750 | Sheet 62324 | Residence | 1
22 | Sheet 62309 | 48 | Level 01 | WIR - 02537 | Housekeeping | opening |  |  | 0.6 | 0.9 | 0.54 | 0.45288 | 2 | 310 | 1 | 620 | FS702/FB750 | Sheet 62309 | Hotel | 2
30 | Sheet 62312 | 136 | Level 01 | WIR - 02537 | Plant room | opening |  |  | 0.24 | 2.3 | 0.552 | 0.42198 | 2 | 310 | 1 | 620 | FS702/FB750 | Sheet 62312 | Hotel | 2
11 | Sheet 61947 | 9 | Level 12 | WIR - 02330 | Housekeeping | opening |  |  | 0.6 | 0.9 | 0.54 | 0.47385 | 1 | 310 | 1 | 310 | FS702/FB750 | Sheet 61947 | Hotel | 1
10 | Sheet 61948 | 8 | Level 19 | WIR - 02329 | Housekeeping | opening |  |  | 0.6 | 0.9 | 0.54 | 0.47371 | 1 | 310 | 1 | 310 | FS702/FB750 | Sheet 61948 | Hotel | 1
9 | Sheet 61949 | 7 | Level 20 | WIR - 02329 | Housekeeping | opening |  |  | 0.6 | 0.9 | 0.54 | 0.47371 | 1 | 310 | 1 | 310 | FS702/FB750 | Sheet 61949 | Hotel | 1
10 | Sheet 61950 | 8 | Level 21 | WIR - 02329 | Housekeeping | opening |  |  | 0.6 | 0.9 | 0.54 | 0.48385 | 1 | 310 | 1 | 310 | FS702/FB750 | Sheet 61950 | Hotel | 1
10 | Sheet 62301 | 8 | Level 22 | WIR - 02329 | Housekeeping | opening |  |  | 0.6 | 0.9 | 0.54 | 0.47385 | 1 | 310 | 1 | 310 | FS702/FB750 | Sheet 62301 | Hotel | 1
10 | Sheet 62302 | 8 | Level 23 | WIR - 02329 | Housekeeping | opening |  |  | 0.6 | 0.9 | 0.54 | 0.47398 | 1 | 310 | 1 | 310 | FS702/FB750 | Sheet 62302 | Hotel | 1
10 | Sheet 62303 | 8 | Level 24 | WIR - 02328 | Housekeeping | opening |  |  | 0.6 | 0.9 | 0.54 | 0.48162 | 1 | 310 | 1 | 310 | FS702/FB750 | Sheet 62303 | Hotel | 1
13 | Sheet 62303 | 10 | Level 24 | WIR - 02328 | Housekeeping | opening |  |  | 0.6 | 0.65 | 0.39 | 0.37 | 2 | 310 | 1 | 620 | FS702/FB750 | Sheet 62303 | Hotel | 2
30 | Sheet 62303 | 23 | Level 24 | WIR - 02328 | Housekeeping | opening |  |  | 0.45 | 1 | 0.45 | 0.44558 | 2 | 310 | 1 | 620 | FS702/FB750 | Sheet 62303 | Hotel | 2
11 | Sheet 62304 | 9 | Level 25 | WIR - 02328 | Housekeeping | opening |  |  | 0.6 | 0.9 | 0.54 | 0.48332 | 1 | 310 | 1 | 310 | FS702/FB750 | Sheet 62304 | Hotel | 1
29 | Sheet 62304 | 22 | Level 25 | WIR - 02328 | Housekeeping | opening |  |  | 0.6 | 0.75 | 0.45 | 0.40911 | 2 | 310 | 1 | 620 | FS702/FB750 | Sheet 62304 | Hotel | 2
10 | Sheet 62305 | 8 | Level 26 | WIR - 02328 | Housekeeping | opening |  |  | 0.6 | 0.9 | 0.54 | 0.48162 | 1 | 310 | 1 | 310 | FS702/FB750 | Sheet 62305 | Hotel | 1
9 | Sheet 62306 | 7 | Level 27 | WIR - 02328 | Housekeeping | opening |  |  | 0.6 | 0.9 | 0.54 | 0.48318 | 1 | 310 | 1 | 310 | FS702/FB750 | Sheet 62306 | Hotel | 1
[12 empty] | Subtotal 0.50 m |  |  |  | 24180 |  |  |  | 78
7 | Sheet 61020 |  | Level 08 | MEP-AX-WR-L8-00271 | Apart. no. 4A | opening |  |  | 1.2 | 0.52 | 0.624 | 0.56094 | 1 | 340 | 1 | 340 |  |  | Residence | 1
7 | Sheet 61869 |  | Level 19 | WIR - 0731 | Housekeeping | opening |  |  | 0.6 | 0.9 | 0.54 | 0.53773 | 2 | 340 | 1 | 680 |  |  | Hotel | 2
20 | Sheet 61930 | 17 | Level 22 | WIR - 00175 | Corridor Out. Sleeve | opening |  |  | 0.7 | 1 | 0.7 | 0.60853 | 1 | 340 | 1 | 340 | FS702/FB750 |  | Hotel | 1
11 | Sheet 62278 |  | Level 26 | WIR - 00187 | Corridor Shaft 03 | opening |  |  | 0.68 | 1.04 | 0.7072 | 0.56115 | 2 | 340 | 1 | 680 | FS702/FB750 |  | Residence | 2
17 | Sheet 62278 |  | Level 21 | WIR - 00186 | Corridor Shaft 03 | opening |  |  | 0.7 | 0.95 | 0.665 | 0.51815 | 2 | 340 | 1 | 680 | FS702/FB750 |  | Residence | 2
20 | Sheet 62278 |  | Level 09 | WIR - 00183 | Corridor Shaft 03 | opening |  |  | 0.72 | 0.98 | 0.7056 | 0.55875 | 2 | 340 | 1 | 680 | FS702/FB750 |  | Residence | 2
5 | Sheet 61941 | 58 | Level 18 | WIR - 02249 | Corridor | blank opening |  |  | 0.22 | 2.7 | 0.594 | 0.594 | 2 | 340 | 2 | 1360 | FS702/FB750 |  | Hotel | 4
12 | Sheet 62288 | 37 | Ground Level | WIR - 0194 | Staircase 04 | opening |  |  | 0.18 | 3.2 | 0.576 | 0.56959 | 1 | 340 | 1 | 340 | FS702 |  | Residence | 1
5 | Sheet 62324 |  | Basement 01 | WIR - 00198 | FTR Room | blank opening |  |  | 0.4 | 1.6 | 0.64 | 0.64 | 1 | 340 | 1 | 340 | FS702/FB750 | Sheet 62324 | Residence | 1
10 | Sheet 62313 | 145 | Level 01 | WIR - 02537 | Plant room | opening |  |  | 0.35 | 1.5 | 0.525 | 0.51322 | 2 | 340 | 1 | 680 | FS702/FB750 | Sheet 62313 | Hotel | 2
14 | Sheet 62304 | 11 | Level 25 | WIR - 02328 | Housekeeping | opening |  |  | 0.75 | 0.9 | 0.675 | 0.645 | 2 | 340 | 1 | 680 | FS702/FB750 | Sheet 62304 | Hotel | 2
13 | Sheet 62306 | 10 | Level 27 | WIR - 02328 | Housekeeping | opening |  |  | 0.7 | 0.8 | 0.56 | 0.52 | 2 | 340 | 1 | 680 | FS702/FB750 | Sheet 62306 | Hotel | 2
[12 empty] | Subtotal 0.65 m |  |  |  | 7480 |  |  |  | 22
1 | Sheet 61910 | 13 | Basement 01 | WIR - 0977 | Corridor, Entry D. | opening |  |  | 0.55 | 1.5 | 0.825 | 0.78304 | 2 | 400 | 1 | 800 | FS702/FB750 |  | Hotel | 2
1 | Sheet 61861 |  | Basement 01 | MEP-AX-WR-B1-00849 | Fresh Air plenum | opening |  |  | 1.9 | 2.15 | 4.085 | 0.69 | 2 | 400 | 1 | 800 | FS702/FB750 |  | Residence | 2
7 | Sheet 62281 | 30 | Ground Level | WIR - 01955 | Kitchen | opening |  |  | 0.85 | 0.9 | 0.765 | 0.73773 | 1 | 400 | 1 | 400 | FS702/FB750 |  | Hotel | 1
23 | Sheet 62278 |  | Level 07 | WIR - 00183 | Corridor Shaft 03 | opening |  |  | 0.7 | 1.2 | 0.84 | 0.69329 | 2 | 400 | 1 | 800 | FS702/FB750 |  | Residence | 2
1 | Sheet 62298 | 192 | Ground Level | WIR - 02185 | Housekeeping | opening |  |  | 0.75 | 0.95 | 0.7125 | 0.69 | 2 | 400 | 1 | 800 | FS702/FB750 |  | Hotel | 2
1 | Sheet 62311 | 100 | Level 01 | WIR - 02537 | Service lobby | opening |  |  | 0.8 | 1 | 0.8 | 0.69303 | 2 | 400 | 1 | 800 | FS702/FB750 | Sheet 62311 | Hotel | 2
[12 empty] | Subtotal 0.80 m |  |  |  | 4400 |  |  |  | 11
1 | Sheet 61911 | 29 | Basement 01 | WIR - 0977 | Corridor, Entry D. | opening |  |  | 0.85 | 3.25 | 2.7625 | 2.6958 | 2 | 450 | 1 | 2426.2369 | FS702/FB750 |  | Hotel | 5.3916
2 | Sheet 61861 |  | Basement 01 | MEP-AX-WR-B1-00849 | Fresh Air plenum | opening |  |  | 2.2 | 2.7 | 5.94 | 2.54 | 2 | 450 | 1 | 2286 | FS702/FB750 |  | Residence | 5.08
4 | Sheet 61861 |  | Basement 01 | MEP-AX-WR-B1-00849 | Fresh Air plenum | opening |  |  | 2.15 | 2.8 | 6.02 | 2.62 | 2 | 450 | 1 | 2358 | FS702/FB750 |  | Residence | 5.24
4 | Sheet 62261 | 12 | Level 17 | WIR - 01579 | Plant Room | opening |  |  | 0.88 | 2.46 | 2.1648 | 1.5621 | 2 | 450 | 1 | 1405.9237 | FS702/FB750 |  | Hotel | 3.1243
4 | Sheet 62262 | 29 | Level 17 | WIR - 01579 | Plant Room | opening |  |  | 0.65 | 1.7 | 1.105 | 1.0815 | 2 | 450 | 1 | 973.305 | FS702/FB750 |  | Hotel | 2.1629
4 | Sheet 62269 | 3 | Level 18 | WIR - 01698 | AHU Room | opening |  |  | 0.86 | 2.6 | 2.236 | 2.183 | 2 | 450 | 1 | 1964.7113 | FS702/FB750 |  | Hotel | 4.366
13 | Sheet 62269 | 10 | Level 18 | WIR - 01698 | AHU Room | opening |  |  | 1.05 | 1.7 | 1.785 | 1.3618 | 2 | 450 | 1 | 1225.6592 | FS702/FB750 |  | Hotel | 2.7237
2 | Sheet 62271 | 1 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | opening |  |  | 1.3 | 11.425 | 14.8525 | 5.0657 | 1 | 450 | 1 | 2279.565 | FS702/FB750 |  | Hotel | 5.0657
4 | Sheet 62271 | 1 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | opening |  |  | 1.3 | 11.425 | 14.8525 | 5.0657 | 1 | 450 | 1 | 2279.565 | FS702/FB750 |  | Hotel | 5.0657
26 | Sheet 62271 | 21 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | opening |  |  | 0.76 | 1.9 | 1.444 | 1.2409 | 1 | 450 | 1 | 558.4222 | FS702/FB750 |  | Hotel | 1.2409
29 | Sheet 62271 | 23 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | opening |  |  | 1.6 | 1.75 | 2.8 | 1.0553 | 1 | 450 | 1 | 474.8858 | FS702/FB750 |  | Hotel | 1.0553
3 | Sheet 62272 | 2 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | opening |  |  | 0.47 | 2.7 | 1.269 | 1.218 | 2 | 450 | 1 | 1096.1775 | FS702/FB750 |  | Hotel | 2.4359
7 | Sheet 62272 | 5 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | opening |  |  | 0.85 | 2.7 | 2.295 | 2.242 | 2 | 450 | 1 | 2017.8113 | FS702/FB750 |  | Hotel | 4.484
11 | Sheet 62272 | 9 | Level 18 | WIR - 01768 | AHU for F-B- NX Rm | opening |  |  | 0.85 | 2.7 | 2.295 | 2.242 | 2 | 450 | 1 | 2017.8113 | FS702/FB750 |  | Hotel | 4.484
16 | Sheet 62280 | 12 | Ground Level | WIR - 01955 | BOH Corridor | opening |  |  | 0.8 | 1.9 | 1.52 | 1.3697 | 2 | 450 | 1 | 1232.6962 | FS702/FB750 |  | Hotel | 2.7393
4 | Sheet 62279 | 1 | Level 28 | WIR - 00188 | Shaft Opening 01 | opening |  |  | 0.85 | 2.65 | 2.2525 | 1.6918 | 2 | 450 | 1 | 1522.62 | FS702/FB750 |  | Hotel | 3.3836
9 | Sheet 62279 | 2 | Level 28 | WIR - 00188 | Shaft Opening 02 | opening |  |  | 0.85 | 2.65 | 2.2525 | 1.684 | 2 | 450 | 1 | 1515.555 | FS702/FB750 |  | Hotel | 3.3679
12 | Sheet 62279 | 3 | Level 28 | WIR - 00188 | Shaft Opening 03 | opening |  |  | 1.15 | 1.4 | 1.61 | 1.4456 | 2 | 450 | 1 | 1301.0259 | FS702/FB750 |  | Hotel | 2.8912
16 | Sheet 62279 | 3 | Level 28 | WIR - 00188 | Shaft Opening 03 | opening |  |  | 1.02 | 1.25 | 1.275 | 0.8743 | 2 | 450 | 1 | 900 | FS702/FB750 |  | Hotel | 2
22 | Sheet 62279 | 4 | Level 28 | WIR - 00188 | Shaft Opening 04 | opening |  |  | 0.85 | 2.65 | 2.2525 | 1.6697 | 2 | 450 | 1 | 1502.7497 | FS702/FB750 |  | Hotel | 3.3394
3 | Sheet 62278 |  | Level 30 | WIR - 00184 | Corridor Shaft 03 | opening |  |  | 0.7 | 2.6 | 1.82 | 1.6732 | 2 | 450 | 1 | 1505.8393 | FS702/FB750 |  | Residence | 3.3463
6 | Sheet 62278 |  | Level 29 | WIR - 00184 | Corridor Shaft 03 | opening |  |  | 0.7 | 2.6 | 1.82 | 1.6733 | 2 | 450 | 1 | 1505.9587 | FS702/FB750 |  | Residence | 3.3466
25 | Sheet 62291 | 21 | Ground Level | WIR - 02185 | FF Lobby | opening |  |  | 0.88 | 1.35 | 1.188 | 1.0771 | 2 | 450 | 1 | 969.3816 | FS702/FB750 |  | Hotel | 2.1542
8 | Sheet 62293 | 55 | Ground Level | WIR - 02185 | Male Toilet | opening |  |  | 0.58 | 1.95 | 1.131 | 1.0163 | 1 | 450 | 1 | 457.3486 | FS702/FB750 |  | Hotel | 1.0163
22 | Sheet 62293 | 66 | Ground Level | WIR - 02185 | Corridor | opening |  |  | 0.6 | 1.95 | 1.17 | 1.0156 | 2 | 450 | 1 | 914.0411 | FS702/FB750 |  | Hotel | 2.0312
26 | Sheet 62296 | 151 | Ground Level | WIR - 02185 | Lobby Shaft | opening |  |  | 0.4 | 3.38 | 1.352 | 1.3343 | 1 | 450 | 1 | 600.4519 | FS702/FB750 |  | Hotel | 1.3343
14 | Sheet 61939 | 11 | Level 18 | WIR - 02249 | High Level | opening |  |  | 0.48 | 2.7 | 1.296 | 1.243 | 2 | 450 | 1 | 1118.7112 | FS702/FB750 |  | Hotel | 2.486
25 | Sheet 61939 | 20 | Level 18 | WIR - 02249 | Wall | opening |  |  | 0.6 | 2 | 1.2 | 1.0048 | 2 | 450 | 1 | 900 | FS702/FB750 |  | Hotel | 2
28 | Sheet 61939 | 22 | Level 18 | WIR - 02249 | Wall | opening |  |  | 1.6 | 1.85 | 2.96 | 1.265 | 2 | 450 | 1 | 1138.5 | FS702/FB750 |  | Hotel | 2.53
9 | Sheet 61940 | 34 | Level 18 | WIR - 02249 | High Level | opening |  |  | 0.48 | 2.7 | 1.296 | 1.2607 | 2 | 450 | 1 | 1134.6075 | FS702/FB750 |  | Hotel | 2.5213
21 | Sheet 61940 | 44 | Level 18 | WIR - 02249 | Wall | opening |  |  | 0.76 | 1.9 | 1.444 | 1.2649 | 1 | 450 | 1 | 569.1825 | FS702/FB750 |  | Hotel | 1.2649
24 | Sheet 61940 | 46 | Level 18 | WIR - 02249 | Wall | opening |  |  | 1.6 | 1.75 | 2.8 | 1.0847 | 1 | 450 | 1 | 488.1038 | FS702/FB750 |  | Hotel | 1.0847
23 | Sheet 61942 | 101 | Level 18 | WIR - 02249 | SU Lobby | opening |  |  | 1.3 | 2.1 | 2.73 | 2.448 | 2 | 450 | 1 | 2203.1998 | FS702/FB750 |  | Hotel | 4.896
9 | Sheet 62288 | 34 | Ground Level | WIR - 0194 | Staircase 04 | blank opening |  |  | 0.97 | 1.3 | 1.261 | 1.261 | 2 | 450 | 1 | 1134.9 | FS702 |  | Residence | 2.522
6 | Sheet 62328 |  | Level 12 | WIR - 00207 | Room Service | civil opening |  |  | 0.35 | 4.1 | 1.435 | 1.435 | 1 | 450 | 1 | 645.75 | FS702/FB750 | Sheet 62328 | Hotel | 1.435
7 | Sheet 62328 |  | Level 12 | WIR - 00207 | Room Service | civil opening |  |  | 0.3 | 4.1 | 1.23 | 1.23 | 1 | 450 | 1 | 553.5 | FS702/FB750 | Sheet 62328 | Hotel | 1.23
15 | Sheet 62328 |  | Level 08 | WIR - 00207 | Room Service | civil opening |  |  | 0.35 | 4.1 | 1.435 | 1.435 | 1 | 450 | 1 | 645.75 | FS702/FB750 | Sheet 62328 | Hotel | 1.435
16 | Sheet 62328 |  | Level 08 | WIR - 00207 | Room Service | civil opening |  |  | 0.3 | 4.1 | 1.23 | 1.23 | 1 | 450 | 1 | 553.5 | FS702/FB750 | Sheet 62328 | Hotel | 1.23
22 | Sheet 62328 |  | Level 07 | WIR - 00207 | Room Service | civil opening |  |  | 0.35 | 4.1 | 1.435 | 1.435 | 1 | 450 | 1 | 645.75 | FS702/FB750 | Sheet 62328 | Hotel | 1.435
23 | Sheet 62328 |  | Level 07 | WIR - 00207 | Room Service | civil opening |  |  | 0.3 | 4.1 | 1.23 | 1.23 | 1 | 450 | 1 | 553.5 | FS702/FB750 | Sheet 62328 | Hotel | 1.23
1 | Sheet 62321 |  | Level 09 | WIR - 00204 | Room Service | civil opening |  |  | 0.35 | 4.1 | 1.435 | 1.435 | 1 | 450 | 1 | 645.75 | FS702/FB750 | Sheet 62321 | Hotel | 1.435
2 | Sheet 62321 |  | Level 09 | WIR - 00204 | Room Service | civil opening |  |  | 0.3 | 4.1 | 1.23 | 1.23 | 1 | 450 | 1 | 553.5 | FS702/FB750 | Sheet 62321 | Hotel | 1.23
6 | Sheet 62314 | 6 | Level 23 | WIR - 02536 | Female Change Rm | opening |  |  | 1.15 | 2.2 | 2.53 | 1.8544 | 2 | 450 | 1 | 1668.9687 | FS702/FB750 | Sheet 62314 | Residence | 3.7088
31 | Sheet 62314 | 24 | Level 23 | WIR - 02536 | Male Change Rm | opening |  |  | 1.2 | 1.45 | 1.74 | 1.205 | 2 | 450 | 1 | 1084.5 | FS702/FB750 | Sheet 62314 | Residence | 2.41
38 | Sheet 62314 | 28 | Level 23 | WIR - 02536 | Male Change Rm | opening |  |  | 2 | 2.2 | 4.4 | 3.76 | 2 | 450 | 1 | 3384 | FS702/FB750 | Sheet 62314 | Residence | 7.52
7 | Sheet 62315 | 34 | Level 23 | WIR - 02536 | Housekeeping | opening |  |  | 0.7 | 2.4 | 1.68 | 1.3991 | 1 | 450 | 1 | 629.6024 | FS702/FB750 | Sheet 62315 | Residence | 1.3991
[12 empty] | Subtotal 1.00 m |  |  |  | 57543.0178 |  |  |  | 127.8734
[14 empty] | Grand Total |  | 158613.0178 |  |  | Total qty | 779.8734

## duct
Project: |  |  |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  |  |  | Khansaheb Civil Engineering
Period of Completed Works: |  |  |  |  | up to July 2022
Summary of Completed Firestopping Works
No. | Sos Number | Serial No | Level | WIR No. | Location | Penetrant Type | Penetrant Size (in meter) |  | SquareMeters | Opening Size (in meter) |  | SquareMeters | Diffirence | Sides | Rate (AED) | Nos | Total (AED) |  |  | Hotel / Residence | QTY
1 | Sheet 61938 | 37 | Ground Level | WIR - 0194 | Ball Room | duct | 10" |  |  | 12" |  |  |  | 2 | 32 | 6 | 384 | FS702 |  | Hotel | 12
[13 empty] | Subtotal 0.05 m |  |  |  | 0 |  |  |  | 12
47 | Sheet 61884 | 15 | Level 27 | WIR - 0169 | Outer sleeve | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 |  | 1 | 46 | 1 | 46 |  |  | Hotel | 1
70 | Sheet 61885 | 38 | Level 27 | WIR - 0169 | Outer sleeve | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 |  | 2 | 46 | 1 | 92 |  |  | Hotel | 2
105 | Sheet 61886 | 73 | Level 27 | WIR - 0169 | Outer sleeve | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 |  | 1 | 46 | 1 | 46 |  |  | Hotel | 1
1 | Sheet 62267 | 7 | Ground Level | WIR - 00180 | BOH 03 | duct (flexible) | 8" |  |  | 10" |  |  |  | 2 | 46 | 6 | 552 |  |  | Hotel | 12
[13 empty] | Subtotal 0.10 m |  |  |  | 736 |  |  |  | 16
1 | Sheet 61885 | 39 | Level 27 | WIR - 0169 | Outer sleeve | duct | 0.3 | 0.3 | 0.09 | 0.35 | 0.35 | 0.1225 |  | 1 | 51 | 1 | 51 |  |  | Hotel | 1
1 | Sheet 62256 | 1 | Level 21 | WIR - 00177 | Entry Door | duct | 0.3 | 0.3 | 0.09 | 0.35 | 0.5 | 0.175 |  | 2 | 51 | 1 | 102 |  | Sheet 62256 | Hotel | 2
4 | Sheet 62256 | 4 | Level 21 | WIR - 00177 | Entry Door | duct | 0.3 | 0.3 | 0.09 | 0.35 | 0.5 | 0.175 |  | 1 | 51 | 1 | 51 |  |  | Hotel | 1
1 | Sheet 61937 | 2 | Ground Level | WIR - 0194 | Male Toilet | duct | 0.25 | 0.3 | 0.075 | 0.32 | 0.36 | 0.1152 |  | 2 | 51 | 2 | 204 | FS702 |  | Hotel | 4
2 | Sheet 61937 | 3 | Ground Level | WIR - 0194 | Male Toilet | duct | 0.3 | 0.35 | 0.105 | 0.36 | 0.41 | 0.1476 |  | 2 | 51 | 2 | 204 | FS702 |  | Hotel | 4
[13 empty] | Subtotal 0.20 m |  |  |  | 612 |  |  |  | 12
7 | Sheet 62256 | 6 | Level 21 | WIR - 00177 | Shaft | duct | 0.4 | 0.4 | 0.16 | 0.45 | 0.5 | 0.225 |  | 1 | 64 | 1 | 64 |  |  | Hotel | 1
23 | Sheet 62260 | 17 | Level 19 | WIR - 00178 | Outer Sleeve | duct | 0.25 | 0.3 | 0.075 | 0.4 | 0.6 | 0.24 |  | 1 | 64 | 1 | 64 |  |  | Hotel | 1
[13 empty] | Subtotal 0.30 m |  |  |  | 128 |  |  |  | 2
[13 empty] | Subtotal 0.40 m |  |  |  | 0 |  |  |  | 0
[13 empty] | Subtotal 0.50 m |  |  |  | 0 |  |  |  | 0
[13 empty] | Subtotal 0.60 m |  |  |  | 0 |  |  |  | 0
[13 empty] | Subtotal 0.70 m |  |  |  | 0 |  |  |  | 0
[13 empty] | Subtotal 0.80 m |  |  |  | 0 |  |  |  | 0
[13 empty] | Subtotal 0.90 m |  |  |  | 0 |  |  |  | 0
[13 empty] | Subtotal 1.00 m |  |  |  | 0 |  |  |  | 0
[13 empty] | Grand Total |  |  |  | 1476 |  |  | Total qty | 42

## civil opening (FR 230)
Project: |  |  |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  |  |  | Khansaheb Civil Engineering
Period of Completed Works: |  |  |  |  | up to July 2022
Summary of Completed Firestopping Works
No. | Sos Number | Serial No | Level | WIR No. | Location | Penetrant Type | Penetrant Size (in meter) | SquareMeters | Opening Size (in meter) |  | SquareMeters | Diffirence | Sides | Rate (AED) | Nos | Total (AED) |  | Hotel / Residence | QTY
6 | Sheet 61916 | 5 | Level 22 | WIR - 01153 | FTR Room | opening Mortar |  |  | 0.35 | 1.8 | 0.63 | 0.5475 | 1 | 680 | 1 | 372.3 | FR230 | Hotel | 0.5475
12 | Sheet 61916 | 6 | Level 23 | WIR - 01154 | FTR Room | opening Mortar |  |  | 0.35 | 1.8 | 0.63 | 0.5475 | 1 | 680 | 1 | 372.3 | FR230 | Hotel | 0.5475
18 | Sheet 61916 | 7 | Level 24 | WIR - 01155 | FTR Room | opening Mortar |  |  | 0.35 | 1.8 | 0.63 | 0.5475 | 1 | 680 | 1 | 372.3 | FR230 | Hotel | 0.5475
24 | Sheet 61916 | 8 | Level 25 | WIR - 01156 | FTR Room | opening Mortar |  |  | 0.35 | 1.8 | 0.63 | 0.5475 | 1 | 680 | 1 | 372.3 | FR230 | Hotel | 0.5475
6 | Sheet 61915 | 1 | Level 18 | WIR - 01149 | FTR Room | opening Mortar |  |  | 0.35 | 1.8 | 0.63 | 0.5475 | 1 | 680 | 1 | 372.3 | FR230 | Hotel | 0.5475
12 | Sheet 61915 | 2 | Level 19 | WIR - 01150 | FTR Room | opening Mortar |  |  | 0.35 | 1.8 | 0.63 | 0.5475 | 1 | 680 | 1 | 372.3 | FR230 | Hotel | 0.5475
18 | Sheet 61915 | 3 | Level 20 | WIR - 01151 | FTR Room | opening Mortar |  |  | 0.35 | 1.8 | 0.63 | 0.5475 | 1 | 680 | 1 | 372.3 | FR230 | Hotel | 0.5475
24 | Sheet 61915 | 4 | Level 21 | WIR - 01152 | FTR Room | opening Mortar |  |  | 0.35 | 1.8 | 0.63 | 0.5475 | 1 | 680 | 1 | 372.3 | FR230 | Hotel | 0.5475
6 | Sheet 61917 | 9 | Level 26 | WIR - 01157 | FTR Room | opening Mortar |  |  | 0.35 | 1.8 | 0.63 | 0.5475 | 1 | 680 | 1 | 372.3 | FR230 | Hotel | 0.5475
12 | Sheet 61917 | 10 | Level 27 | WIR - 01158 | FTR Room | opening Mortar |  |  | 0.35 | 1.8 | 0.63 | 0.5475 | 1 | 680 | 1 | 372.3 | FR230 | Hotel | 0.5475
18 | Sheet 61917 | 11 | Level 28 | WIR - 01159 | FTR Room | opening Mortar |  |  | 0.35 | 1.8 | 0.63 | 0.5475 | 1 | 680 | 1 | 372.3 | FR230 | Hotel | 0.5475
24 | Sheet 61917 | 12 | Level 29 | WIR - 01160 | FTR Room | opening Mortar |  |  | 0.35 | 1.8 | 0.63 | 0.5475 | 1 | 680 | 1 | 372.3 | FR230 | Hotel | 0.5475
3 | Sheet 61873 | 2 | Level 17 | WIR - 0739 | Electrical Rm, slab | opening Mortar |  |  | 0.5 | 2.4 | 1.2 | 1.135 | 1 | 680 | 1 | 771.8 |  | Hotel | 1.135
7 | Sheet 61873 | 5 | Level 17 | WIR - 0739 | Electrical Rm, slab | opening Mortar |  |  | 0.25 | 1.63 | 0.4075 | 0.3075 | 1 | 680 | 1 | 209.1 |  | Hotel | 0.3075
10 | Sheet 61873 | 2 | Level 18 | WIR - 0733 | Electrical Rm, slab | opening Mortar |  |  | 0.5 | 2.4 | 1.2 | 1.135 | 1 | 680 | 1 | 771.8 |  | Hotel | 1.135
14 | Sheet 61873 | 5 | Level 18 | WIR - 0733 | Electrical Rm, slab | opening Mortar |  |  | 0.25 | 1.63 | 0.4075 | 0.3075 | 1 | 680 | 1 | 209.1 |  | Hotel | 0.3075
17 | Sheet 61873 | 2 | Level 19 | WIR - 0734 | Electrical Rm, slab | opening Mortar |  |  | 0.5 | 2.4 | 1.2 | 1.155 | 1 | 680 | 1 | 785.4 |  | Hotel | 1.155
21 | Sheet 61873 | 5 | Level 19 | WIR - 0734 | Electrical Rm, slab | opening Mortar |  |  | 0.25 | 1.63 | 0.4075 | 0.3075 | 1 | 680 | 1 | 209.1 |  | Hotel | 0.3075
24 | Sheet 61874 | 2 | Level 20 | WIR - 0735 | Electrical Rm, slab | opening Mortar |  |  | 0.5 | 2.4 | 1.2 | 1.155 | 1 | 680 | 1 | 785.4 |  | Hotel | 1.155
28 | Sheet 61874 | 5 | Level 20 | WIR - 0735 | Electrical Rm, slab | opening Mortar |  |  | 0.25 | 1.63 | 0.4075 | 0.3075 | 1 | 680 | 1 | 209.1 |  | Hotel | 0.3075
31 | Sheet 61874 | 2 | Level 21 | WIR - 0736 | Electrical Rm, slab | opening Mortar |  |  | 0.5 | 2.4 | 1.2 | 1.155 | 1 | 680 | 1 | 785.4 |  | Hotel | 1.155
35 | Sheet 61874 | 5 | Level 21 | WIR - 0736 | Electrical Rm, slab | opening Mortar |  |  | 0.25 | 1.63 | 0.4075 | 0.3075 | 1 | 680 | 1 | 209.1 |  | Hotel | 0.3075
38 | Sheet 61874 | 2 | Level 22 | WIR - 0737 | Electrical Rm, slab | opening Mortar |  |  | 0.5 | 2.4 | 1.2 | 1.155 | 1 | 680 | 1 | 785.4 |  | Hotel | 1.155
42 | Sheet 61874 | 5 | Level 22 | WIR - 0737 | Electrical Rm, slab | opening Mortar |  |  | 0.25 | 1.63 | 0.4075 | 0.3175 | 1 | 680 | 1 | 215.9 |  | Hotel | 0.3175
45 | Sheet 61874 | 2 | Level 23 | WIR - 0738 | Electrical Rm, slab | opening Mortar |  |  | 0.5 | 2.4 | 1.2 | 1.155 | 1 | 680 | 1 | 785.4 |  | Hotel | 1.155
49 | Sheet 61874 | 5 | Level 23 | WIR - 0738 | Electrical Rm, slab | opening Mortar |  |  | 0.25 | 1.63 | 0.4075 | 0.3175 | 1 | 680 | 1 | 215.9 |  | Hotel | 0.3175
52 | Sheet 61875 | 2 | Level 24 | WIR - 0762 | Electrical Rm, slab | opening Mortar |  |  | 0.5 | 2.4 | 1.2 | 1.155 | 1 | 680 | 1 | 785.4 |  | Hotel | 1.155
56 | Sheet 61875 | 5 | Level 24 | WIR - 0762 | Electrical Rm, slab | opening Mortar |  |  | 0.25 | 1.63 | 0.4075 | 0.3175 | 1 | 680 | 1 | 215.9 |  | Hotel | 0.3175
59 | Sheet 61875 | 2 | Level 25 | WIR - 0763 | Electrical Rm, slab | opening Mortar |  |  | 0.5 | 2.4 | 1.2 | 1.155 | 1 | 680 | 1 | 785.4 |  | Hotel | 1.155
63 | Sheet 61875 | 5 | Level 25 | WIR - 0763 | Electrical Rm, slab | opening Mortar |  |  | 0.25 | 1.63 | 0.4075 | 0.3175 | 1 | 680 | 1 | 215.9 |  | Hotel | 0.3175
66 | Sheet 61875 | 2 | Level 26 | WIR - 0764 | Electrical Rm, slab | opening Mortar |  |  | 0.5 | 2.4 | 1.2 | 1.155 | 1 | 680 | 1 | 785.4 |  | Hotel | 1.155
70 | Sheet 61875 | 5 | Level 26 | WIR - 0764 | Electrical Rm, slab | opening Mortar |  |  | 0.25 | 1.63 | 0.4075 | 0.3175 | 1 | 680 | 1 | 215.9 |  | Hotel | 0.3175
73 | Sheet 61875 | 2 | Level 27 | WIR - 0765 | Electrical Rm, slab | opening Mortar |  |  | 0.5 | 2.4 | 1.2 | 1.155 | 1 | 680 | 1 | 785.4 |  | Hotel | 1.155
77 | Sheet 61875 | 5 | Level 27 | WIR - 0765 | Electrical Rm, slab | opening Mortar |  |  | 0.25 | 1.63 | 0.4075 | 0.3175 | 1 | 680 | 1 | 215.9 |  | Hotel | 0.3175
80 | Sheet 61876 | 2 | Level 28 | WIR - 0766 | Electrical Rm, slab | opening Mortar |  |  | 0.5 | 2.4 | 1.2 | 1.155 | 1 | 680 | 1 | 785.4 |  | Hotel | 1.155
84 | Sheet 61876 | 5 | Level 28 | WIR - 0766 | Electrical Rm, slab | opening Mortar |  |  | 0.25 | 1.63 | 0.4075 | 0.3175 | 1 | 680 | 1 | 215.9 |  | Hotel | 0.3175
86 | Sheet 61876 | 1 | Level 29 | WIR - 0767 | Electrical Rm, slab | opening Mortar |  |  | 0.5 | 1.4 | 0.7 | 0.68 | 1 | 680 | 1 | 462.4 |  | Hotel | 0.68
90 | Sheet 61876 | 4 | Level 29 | WIR - 0767 | Electrical Rm, slab | opening Mortar |  |  | 0.4 | 1.5 | 0.6 | 0.525 | 1 | 680 | 1 | 357 |  | Hotel | 0.525
4 | Sheet 62286 |  | Level 30 | WIR - 00191 | Electrical Room | opening Mortar |  |  | 0.54 | 1.37 | 0.7398 | 0.6548 | 1 | 680 | 1 | 445.264 | FR230 | Residence | 0.6548
6 | Sheet 62286 |  | Level 30 | WIR - 00191 | Electrical Room | opening Mortar |  |  | 0.25 | 0.3 | 0.075 | 0.055 | 1 | 680 | 1 | 37.4 | FR230 | Residence | 0.055
10 | Sheet 62286 |  | Level 29 | WIR - 00191 | Electrical Room | opening Mortar |  |  | 0.5 | 1.35 | 0.675 | 0.59 | 1 | 680 | 1 | 401.2 | FR230 | Residence | 0.59
12 | Sheet 62286 |  | Level 29 | WIR - 00191 | Electrical Room | opening Mortar |  |  | 0.25 | 0.3 | 0.075 | 0.055 | 1 | 680 | 1 | 37.4 | FR230 | Residence | 0.055
16 | Sheet 62286 |  | Level 28 | WIR - 00191 | Electrical Room | opening Mortar |  |  | 0.48 | 1.35 | 0.648 | 0.563 | 1 | 680 | 1 | 382.84 | FR230 | Residence | 0.563
18 | Sheet 62286 |  | Level 28 | WIR - 00191 | Electrical Room | opening Mortar |  |  | 0.25 | 0.3 | 0.075 | 0.055 | 1 | 680 | 1 | 37.4 | FR230 | Residence | 0.055
4 | Sheet 62285 |  | Level 06 | WIR - 00190 | Electrical Room | opening Mortar |  |  | 0.5 | 1.3 | 0.65 | 0.575 | 1 | 680 | 1 | 391 | FR230 | Residence | 0.575
6 | Sheet 62285 |  | Level 06 | WIR - 00190 | Electrical Room | opening Mortar |  |  | 0.75 | 1 | 0.75 | 0.73 | 1 | 680 | 1 | 496.4 | FR230 | Residence | 0.73
8 | Sheet 62285 |  | Level 06 | WIR - 00190 | Electrical Room | opening Mortar |  |  | 0.25 | 0.3 | 0.075 | 0.055 | 1 | 680 | 1 | 37.4 | FR230 | Residence | 0.055
12 | Sheet 62285 |  | Level 07 | WIR - 00190 | Electrical Room | opening Mortar |  |  | 0.5 | 1.3 | 0.65 | 0.575 | 1 | 680 | 1 | 391 | FR230 | Residence | 0.575
14 | Sheet 62285 |  | Level 07 | WIR - 00190 | Electrical Room | opening Mortar |  |  | 0.75 | 1 | 0.75 | 0.73 | 1 | 680 | 1 | 496.4 | FR230 | Residence | 0.73
16 | Sheet 62285 |  | Level 07 | WIR - 00190 | Electrical Room | opening Mortar |  |  | 0.25 | 0.3 | 0.075 | 0.055 | 1 | 680 | 1 | 37.4 | FR230 | Residence | 0.055
20 | Sheet 62285 |  | Level 08 | WIR - 00190 | Electrical Room | opening Mortar |  |  | 0.5 | 1.3 | 0.65 | 0.575 | 1 | 680 | 1 | 391 | FR230 | Residence | 0.575
22 | Sheet 62285 |  | Level 08 | WIR - 00190 | Electrical Room | opening Mortar |  |  | 0.75 | 1 | 0.75 | 0.73 | 1 | 680 | 1 | 496.4 | FR230 | Residence | 0.73
24 | Sheet 62285 |  | Level 08 | WIR - 00190 | Electrical Room | opening Mortar |  |  | 0.25 | 0.3 | 0.075 | 0.055 | 1 | 680 | 1 | 37.4 | FR230 | Residence | 0.055
4 | Sheet 62284 |  | Level 02 | WIR - 00189 | Electrical Room | opening Mortar |  |  | 0.5 | 1.3 | 0.65 | 0.575 | 1 | 680 | 1 | 391 | FR230 | Residence | 0.575
7 | Sheet 62284 |  | Level 02 | WIR - 00189 | Electrical Room | opening Mortar |  |  | 0.75 | 1 | 0.75 | 0.72 | 1 | 680 | 1 | 489.6 | FR230 | Residence | 0.72
9 | Sheet 62284 |  | Level 02 | WIR - 00189 | Electrical Room | opening Mortar |  |  | 0.25 | 0.3 | 0.075 | 0.055 | 1 | 680 | 1 | 37.4 | FR230 | Residence | 0.055
13 | Sheet 62284 |  | Level 04 | WIR - 00189 | Electrical Room | opening Mortar |  |  | 0.5 | 1.3 | 0.65 | 0.575 | 1 | 680 | 1 | 391 | FR230 | Residence | 0.575
16 | Sheet 62284 |  | Level 04 | WIR - 00189 | Electrical Room | opening Mortar |  |  | 0.75 | 1 | 0.75 | 0.72 | 1 | 680 | 1 | 489.6 | FR230 | Residence | 0.72
18 | Sheet 62284 |  | Level 04 | WIR - 00189 | Electrical Room | opening Mortar |  |  | 0.25 | 0.3 | 0.075 | 0.055 | 1 | 680 | 1 | 37.4 | FR230 | Residence | 0.055
22 | Sheet 62284 |  | Level 05 | WIR - 00189 | Electrical Room | opening Mortar |  |  | 0.5 | 1.3 | 0.65 | 0.575 | 1 | 680 | 1 | 391 | FR230 | Residence | 0.575
24 | Sheet 62284 |  | Level 05 | WIR - 00189 | Electrical Room | opening Mortar |  |  | 0.75 | 1 | 0.75 | 0.73 | 1 | 680 | 1 | 496.4 | FR230 | Residence | 0.73
26 | Sheet 62284 |  | Level 05 | WIR - 00189 | Electrical Room | opening Mortar |  |  | 0.25 | 0.3 | 0.075 | 0.055 | 1 | 680 | 1 | 37.4 | FR230 | Residence | 0.055
[14 empty] | Grand Total |  | 24118.104 |  | Total qty | 35.4678