## Contract
FIRE STOP WORKS ON MEP PENETRATIONS AND JOINTS | [11 empty] | FIRE STOP |  | Certified Amount
[6 empty] | Quantity |  |  | Progress Amount (AED) |  |  |  |  | Quantity |  |  | Progress Amount (AED)
S.Nr | Description | Qty | Unit | Rate | Amount | Previous | Current | Cumulative | Previous | Current | Cumulative | WIR Ref./ Remarks |  | Previous | Current | Cumulative | Previous | Current | Cumulative
G | Supply and installation of firestop sealant and mineral wool to Head of wall / Wall to wall joints (Single Sided)
G1 | Upto 20mm joint width | 500 | m | 14 | 7000 | 3131.37 | 732.6 | 3863.97 | 43839.18 | 10256.4 | 54095.58 |  | 0 | 3131.37 | 732.6 | 3863.97 | 43839.18 | 10256.4 | 54095.58
G2 | Upto 30mm joint width | 500 | m | 20 | 10000 | 39 |  | 39 | 780 | 0 | 780 |  | 0 | 39 |  | 39 | 780 | 0 | 780
G3 | Upto 35mm joint width | 150 | m | 27 | 4050 |  |  |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
H | Supply and installation of Sealant and mineral wool non-fire rated Head of wall / Wall to wall joints (Single Sided) | [12 empty] | 0 |  | 0 | 0 |  | 0
H1 | Upto 20mm joint width | 250 | m | 10 | 2500 |  |  |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
[14 empty] | 0 |  | 0 | 0 |  | 0
[14 empty] | 0 |  | 0 | 0 |  | 0
A | Supply and apply firestop sealant and mineral wool backing to non-insulated metallic/ non-combustible pipes (Single Sided) | [12 empty] | 0 |  | 0 | 0 |  | 0
A1 | Upto and including 2"ɸ | 100 | No. | 14 | 1400 | 37 | 18 | 55 | 518 | 252 | 770 |  | 0 | 37 | 18 | 55 | 518 | 252 | 770
A2 | Upto and including 3"ɸ | 100 | No. | 16 | 1600 | 34 | 8 | 42 | 544 | 128 | 672 |  | 0 | 34 | 8 | 42 | 544 | 128 | 672
A3 | Upto and including 4"ɸ | 100 | No. | 21 | 2100 |  | 8 | 8 | 0 | 168 | 168 |  | 0 | 0 | 8 | 8 | 0 | 168 | 168
A4 | Upto and including 6"ɸ | 100 | No. | 27 | 2700 | 2 | 4 | 6 | 54 | 108 | 162 |  | 0 | 2 | 4 | 6 | 54 | 108 | 162
A5 | Upto and including 8"ɸ | 50 | No. | 46 | 2300 |  | 2 | 2 | 0 | 92 | 92 |  | 0 | 0 | 2 | 2 | 0 | 92 | 92
A6 | Upto and including 24"ɸ | 10 | No. | 141 | 1410 |  |  |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
B | Supply and apply firestop sealant and mineral wool backing to insulated metallic/ non-combustible pipes (Single Sided) | [12 empty] | 0 |  | 0 | 0 |  | 0
B1 | Upto and including 2"ɸ | 200 | No. | 20 | 4000 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
B2 | Upto and including 3"ɸ | 200 | No. | 23 | 4600 | 65 |  | 65 | 1495 | 0 | 1495 |  | 0 | 65 | 0 | 65 | 1495 | 0 | 1495
B3 | Upto and including 4"ɸ | 200 | No. | 29 | 5800 | 4 | 6 | 10 | 116 | 174 | 290 |  | 0 | 4 | 6 | 10 | 116 | 174 | 290
B4 | Upto and including 6"ɸ | 200 | No. | 35 | 7000 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
B5 | Upto and including 8"ɸ | 100 | No. | 47 | 4700 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
B6 | Upto and including 16"ɸ | 50 | No. | 170 | 8500 |  | 4 | 4 | 0 | 680 | 680 |  | 0 | 0 | 4 | 4 | 0 | 680 | 680
C | Supply and apply firestop sealant and mineral wool backing to PVC conduits & cable pipes | [12 empty] | 0 | 0 | 0 | 0 |  | 0
C1 | Upto and including 2"ɸ |  |  | 18 |  | 2 | 15 | 17 | 36 | 270 | 306 |  | 0 | 2 | 15 | 17 | 36 | 270 | 306
C | Supply and apply firestop sealant and mineral wool backing to PVC/ combustible pipes (Single Sided) | [12 empty] | 0 | 0 | 0 | 0 |  | 0
C1 | Upto and including 2"ɸ | 400 | No. | 28 | 11200 | 5 | 8 | 13 | 140 | 224 | 364 |  | 0 | 5 | 8 | 13 | 140 | 224 | 364
C2 | Upto and including 3"ɸ | 400 | No. | 30 | 12000 | 162 | 11 | 173 | 4860 | 330 | 5190 |  | 0 | 162 | 11 | 173 | 4860 | 330 | 5190
C3 | Upto and including 4"ɸ | 400 | No. | 65 | 26000 | 19 | 10 | 29 | 1235 | 650 | 1885 |  | 0 | 19 | 10 | 29 | 1235 | 650 | 1885
C4 | Upto and including 6"ɸ | 250 | No. | 125 | 31250 | 21 | 18 | 39 | 2625 | 2250 | 4875 |  | 0 | 21 | 18 | 39 | 2625 | 2250 | 4875
C5 | Upto and including 8"ɸ | 250 | No. | 250 | 62500 | 3 | 34 | 37 | 750 | 8500 | 9250 |  | 0 | 3 | 34 | 37 | 750 | 8500 | 9250
D | Supply and apply firestop board material to cable tray openings, shaft openings and openings (Single Board) | [12 empty] | 0 |  | 0 | 0 |  | 0
D1 | For an area upto 0.05 m2 | 100 | No. | 50 | 5000 | 52 | 17 | 69 | 2600 | 850 | 3450 |  | 0 | 52 | 17 | 69 | 2600 | 850 | 3450 | 850
D2 | For an area upto 0.10 m2 | 100 | No. | 95 | 9500 | 102 | 37 | 139 | 9690 | 3515 | 13205 |  | 0 | 102 | 37 | 139 | 9690 | 3515 | 13205 | 3515
D3 | For an area upto 0.15 m2 | 100 | No. | 150 | 15000 | 58 | 30 | 88 | 8700 | 4500 | 13200 |  | 0 | 58 | 30 | 88 | 8700 | 4500 | 13200 | 4500
D4 | For an area upto 0.25 m2 | 100 | No. | 180 | 18000 | 55 | 15 | 70 | 9900 | 2700 | 12600 |  | 0 | 54 | 15 | 69 | 9720 | 2700 | 12420 | 2700
D5 | For an area upto 0.35 m2 | 100 | No. | 245 | 24500 | 10 | 12 | 22 | 2450 | 2940 | 5390 |  | 0 | 10 | 12 | 22 | 2450 | 2940 | 5390 | 2940
D6 | For an area upto 0.50 m2 | 50 | No. | 310 | 15500 | 39 | 18 | 57 | 12090 | 5580 | 17670 |  | 0 | 39 | 16 | 55 | 12090 | 4960 | 17050 | 4960
D7 | For an area upto 0.65 m2 | 50 | No. | 340 | 17000 | 10 | 5 | 15 | 3400 | 1700 | 5100 |  | 0 | 10 | 4 | 14 | 3400 | 1360 | 4760 | 1360
D8 | For an area upto 0.80 m2 | 50 | No. | 400 | 20000 | 7 | 2 | 9 | 2800 | 800 | 3600 |  | 0 | 7 | 2 | 9 | 2800 | 800 | 3600 | 800
D9 | For an area upto 1.00 m2 | 25 | m2 | 450 | 11250 | 76.3345 | 25.841 | 102.1754 | 34350.5188 | 11628.4278 | 45978.9466 |  | 0 | 76.3345 | 23.319 | 99.6534 | 34350.5188 | 10493.5278 | 44844.0466 | 10493.5278
E | Supply and apply firestopping materials to Metallic Duct with Fire Damper and L-angle (Single Sided) | [12 empty] | 0 |  | 0 | 0 |  | 0
E1 | For an area upto 0.05 m2 | 100 | No. | 32 | 3200 | 0 | 12 | 12 | 0 | 384 | 384 |  | 0 | 0 | 12 | 12 | 0 | 384 | 384
E2 | For an area upto 0.10 m2 | 100 | No. | 46 | 4600 | 16 |  | 16 | 736 | 0 | 736 |  | 0 | 16 |  | 16 | 736 |  | 736
E3 | For an area upto 0.20 m2 | 100 | No. | 51 | 5100 | 4 | 8 | 12 | 204 | 408 | 612 |  | 0 | 4 | 8 | 12 | 204 | 408 | 612
E4 | For an area upto 0.30 m2 | 100 | No. | 64 | 6400 | 2 |  | 2 | 128 | 0 | 128 |  | 0 | 2 | 0 | 2 | 128 |  | 128
E5 | For an area upto 0.40 m2 | 100 | No. | 74 | 7400 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
E6 | For an area upto 0.50 m2 | 100 | No. | 82 | 8200 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
E7 | For an area upto 0.60 m2 | 100 | No. | 88 | 8800 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
E8 | For an area upto 0.70 m2 | 50 | No. | 98 | 4900 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
E9 | For an area upto 0.80 m2 | 50 | No. | 103 | 5150 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
E10 | For an area upto 0.90 m2 | 25 | No. | 110 | 2750 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
E11 | For an area upto 1.00 m2 | 25 | m2 | 116 | 2900 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
[14 empty] | 0 |  | 0 | 0 |  | 0
F | Supply and installation of Nullfire FR 230 firestop mortar material (100mm thickness) to Electrical Openings (Single Sided) | [12 empty] | 0 |  | 0 | 0 |  | 0
F1 | For an area upto 1.00 m2 | 50 | m2 | 680 | 34000 | 35.4678 |  | 35.4678 | 24118.104 | 0 | 24118.104 |  | 0 | 34.9878 |  | 34.9878 | 23791.704 |  | 23791.704
| TOTAL AMOUNT OF CONSTRUCTION JOINTS |  |  |  | 441760 | 3991.1723 | 1060.441 | 5051.6132 | 168158.8028 | 59087.8278 | 227246.6306 |  |  | 3989.6923 | 1054.919 | 5044.6112 | 167652.4028 | 56992.9278 | 224645.3306
[9 empty] | 168158.8028 | 59087.8278 | 227246.6306
[9 empty] | 0 | 0 | 0

## Joints
Project: |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  | Khansaheb Civil Engineering - Construction Division
Period of Completed Works: |  |  | January 2023
Summary of Completed Firestopping Works (Construction Joints)
No. | Sos Number | Level | WIR No. | Location | Type | Joint Size (in meter) |  |  | Sides | Rate (AED) | Nos | Total (AED) |  |  | Hotel / Residence | QTY | Remarks
Hotel
January 2023 - Hotel | [14 empty] | Hotel
1 | Sheet 62300 | Gorund Level | WIR - 00195/00196 | Male Toilet | Horizontal joint | 0.02 | 32 | @ | 2 | 14 | 1 | 896 | 20 | Sheet 62300 | Hotel | 64
2 | Sheet 62300 | Gorund Level | WIR - 00195/00196 | Male Toilet | Horizontal joint | 0.02 | 7 | @ | 1 | 14 | 1 | 98 | 20 |  | Hotel | 7
3 | Sheet 62300 | Gorund Level | WIR - 00195/00196 | Male Toilet | Vertical joint | 0.02 | 4 | @ | 2 | 14 | 2 | 224 | 20 |  | Hotel | 16
4 | Sheet 62300 | Gorund Level | WIR - 00195/00196 | Male Toilet | Vertical joint | 0.02 | 3.6 | @ | 1 | 14 | 1 | 50.4 | 20 |  | Hotel | 3.6
5 | Sheet 62300 | Gorund Level | WIR - 00195/00196 | Ball Room | Horizontal joint | 0.02 | 15.3 | @ | 2 | 14 | 1 | 428.4 | 20 |  | Hotel | 30.6
6 | Sheet 62300 | Gorund Level | WIR - 00195/00196 | Ball Room | Horizontal joint | 0.02 | 24 | @ | 2 | 14 | 1 | 672 | 20 |  | Hotel | 48
7 | Sheet 62300 | Gorund Level | WIR - 00195/00196 | Ball Room | Horizontal joint | 0.02 | 7 | @ | 1 | 14 | 1 | 98 | 20 |  | Hotel | 7
8 | Sheet 62300 | Gorund Level | WIR - 00195/00196 | Ball Room | Horizontal joint | 0.02 | 8 | @ | 2 | 14 | 1 | 224 | 20 |  | Hotel | 16
9 | Sheet 62300 | Gorund Level | WIR - 00195/00196 | Ball Room | Horizontal joint | 0.02 | 61.5 | @ | 2 | 14 | 1 | 1722 | 20 |  | Hotel | 123
10 | Sheet 62300 | Gorund Level | WIR - 00195/00196 | Lobby | Horizontal joint | 0.02 | 9.95 | @ | 2 | 14 | 1 | 278.6 | 20 |  | Hotel | 19.9
11 | Sheet 62300 | Gorund Level | WIR - 00195/00196 | Lobby | Vertical joint | 0.02 | 3.8 | @ | 2 | 14 | 3 | 319.2 | 20 |  | Hotel | 22.8
12 | Sheet 62300 | Gorund Level | WIR - 00195/00196 | Housekeeping | Horizontal joint | 0.02 | 13.7 | @ | 2 | 14 | 1 | 383.6 | 20 |  | Hotel | 27.4
13 | Sheet 62300 | Gorund Level | WIR - 00195/00196 | Housekeeping | Vertical joint | 0.02 | 3.6 | @ | 2 | 14 | 3 | 302.4 | 20 |  | Hotel | 21.6
Hotel
January 2023 - Hotel | [14 empty] | Hotel
1 | Sheet 61943 | Level 18 | WIR - 00197 | Fire Pump Room | Horizontal joint | 0.02 | 27.5 | @ | 1 | 14 | 1 | 385 | 20 | Sheet 61943 | Hotel | 27.5
2 | Sheet 61943 | Level 18 | WIR - 00197 | Fire Pump Room | Horizontal joint | 0.02 | 17.4 | @ | 2 | 14 | 1 | 487.2 | 20 |  | Hotel | 34.8
3 | Sheet 61943 | Level 18 | WIR - 00197 | Corridor | Horizontal joint | 0.02 | 11.2 | @ | 1 | 14 | 1 | 156.8 | 20 |  | Hotel | 11.2
4 | Sheet 61943 | Level 18 | WIR - 00197 | Corridor | Vertical joint | 0.02 | 4 | @ | 1 | 14 | 2 | 112 | 20 |  | Hotel | 8
5 | Sheet 61943 | Level 18 | WIR - 00197 | Housekeeping | Horizontal joint | 0.02 | 15.5 | @ | 2 | 14 | 1 | 434 | 20 |  | Hotel | 31
6 | Sheet 61943 | Level 18 | WIR - 00197 | Housekeeping | Vertical joint | 0.02 | 4.5 | @ | 2 | 14 | 4 | 504 | 20 |  | Hotel | 36
7 | Sheet 61943 | Level 18 | WIR - 00197 | Lift Lobby | Horizontal joint | 0.02 | 15.4 | @ | 2 | 14 | 1 | 431.2 | 20 |  | Hotel | 30.8
8 | Sheet 61943 | Level 18 | WIR - 00197 | Lift Lobby | Vertical joint | 0.02 | 4.6 | @ | 2 | 14 | 4 | 515.2 | 20 |  | Hotel | 36.8
9 | Sheet 61943 | Level 18 | WIR - 00197 | Room Service | Horizontal joint | 0.02 | 7.6 | @ | 2 | 14 | 1 | 212.8 | 20 |  | Hotel | 15.2
10 | Sheet 61943 | Level 18 | WIR - 00197 | Room Service | Vertical joint | 0.02 | 2.4 | @ | 2 | 14 | 2 | 134.4 | 20 |  | Hotel | 9.6
11 | Sheet 61943 | Level 18 | WIR - 00197 | FF lobby | Horizontal joint | 0.02 | 1.65 | @ | 2 | 14 | 1 | 46.2 | 20 |  | Hotel | 3.3
12 | Sheet 61943 | Level 18 | WIR - 00197 | FF lobby | Vertical joint | 0.02 | 5.4 | @ | 2 | 14 | 2 | 302.4 | 20 |  | Hotel | 21.6
Hotel
January 2023 - Hotel | [14 empty] | Hotel
1 | Sheet 62299 | Level 01 | WIR - 00193 | Lift Lobby | Horizontal joint | 0.02 | 8.5 | @ | 1 | 14 | 1 | 119 | 20 | Sheet 62299 | Hotel | 8.5
2 | Sheet 62299 | Level 01 | WIR - 00193 | Equpment Room | Horizontal joint | 0.02 | 12.6 | @ | 2 | 14 | 1 | 352.8 | 20 |  | Hotel | 25.2
3 | Sheet 62299 | Level 01 | WIR - 00193 | Equpment Room | Horizontal joint | 0.02 | 26.2 | @ | 1 | 14 | 1 | 366.8 | 20 |  | Hotel | 26.2
732.6
[10 empty] | Grand Total |  | 10256.4
[10 empty] | Joints |  | 10256.4
[10 empty] | Outside Sleeve (Civil) |  | 16712.9
[10 empty] | MEP Opening (Civil) |  | 32118.5278 | 48831.4278
[10 empty] | Civil Total |  | 59087.8278
WIR List as per SOS
|  |  |  | Gorund Level | WIR - 00195/00196
|  |  |  | Level 18 | WIR - 00197
|  |  |  | Level 01 | WIR - 00193

## MEP opening (Civil)
Project: |  |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  |  | Khansaheb Civil Engineering - Construction Division
Period of Completed Works: |  |  |  | January 2023 | [14 empty] | all mortar openings priced by sqm diff
Summary of Completed Firestopping Works
No. | Sos Number | Serial No | Level | WIR No. | Location | Penetrant Type | Penetrant Size (in meter) |  | SquareMeters | Opening Size (in meter) |  | SquareMeters | Diffirence | Sides | Rate (AED) | Nos | Total (AED) |  |  | Hotel / Residence | QTY
Hotel
January 2023 - Hotel | [19 empty] | Hotel
1 | Sheet 62291 | 1 | Ground Level | WIR - 02185 | Male Toilet | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 4 | 0 | FS709 | Sheet 62291 | Hotel | 8
2 | Sheet 62291 | 2 | Ground Level | WIR - 02185 | Male Toilet | fire fighting pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 2 | 0 | FS702 |  | Hotel | 4
3 | Sheet 62291 | 2 | Ground Level | WIR - 02185 | Male Toilet | opening |  |  |  | 4" |  | 0.00785 | 0.0068688 | 2 | 50 | 1 | 100 | FS702 |  | Hotel | 2
4 | Sheet 62291 | 3 | Ground Level | WIR - 02185 | Male Toilet | duct | 0.2 | 0.25 | 0.05 | 0.26 | 0.31 | 0.0806 |  | 2 |  | 2 | 0 | FS709 |  | Hotel | 4
5 | Sheet 62291 | 4 | Ground Level | WIR - 02185 | Male Toilet | duct | 0.25 | 0.3 | 0.075 | 0.3 | 0.35 | 0.105 |  | 2 |  | 2 | 0 | FS709 |  | Hotel | 4
6 | Sheet 62291 | 5 | Ground Level | WIR - 02185 | Male Toilet | cable trunking | 0.05 | 0.05 | 0.0025 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750 |  | Hotel | 4
7 | Sheet 62291 | 5 | Ground Level | WIR - 02185 | Male Toilet | opening |  |  |  | 0.1 | 0.1 | 0.01 | 0.005 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
8 | Sheet 62291 | 6 | Ground Level | WIR - 02185 | Male Toilet | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 15 | 0 | FS709 |  | Hotel | 30
9 | Sheet 62291 | 7 | Ground Level | WIR - 02185 | Male Toilet | PVC pipe | 2" |  |  | 4" |  |  |  | 2 |  | 2 | 0 | FS702/FP302 |  | Hotel | 4
10 | Sheet 62291 | 8 | Ground Level | WIR - 02185 | Male Toilet | fire fighting pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
11 | Sheet 62291 | 9 | Ground Level | WIR - 02185 | Male Toilet | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 13 | 0 | FS709 |  | Hotel | 26
12 | Sheet 62291 | 10 | Ground Level | WIR - 02185 | Male Toilet | duct | 0.2 | 0.25 | 0.05 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Hotel | 4
13 | Sheet 62291 | 10 | Ground Level | WIR - 02185 | Male Toilet | opening |  |  |  | 0.28 | 0.6 | 0.168 | 0.068 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
14 | Sheet 62291 | 11 | Ground Level | WIR - 02185 | Male Toilet | CHW pipe | 3" |  |  | 5" |  |  |  | 2 |  | 2 | 0 | FS709 |  | Hotel | 4
15 | Sheet 62291 | 12 | Ground Level | WIR - 02185 | Male Toilet | CDP pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
16 | Sheet 62291 | 13 | Ground Level | WIR - 02185 | Male Toilet | PVC pipe | 3" |  |  | 5" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
17 | Sheet 62291 | 14 | Ground Level | WIR - 02185 | Male Toilet | PPR pipe | 3" |  |  | 5" |  |  |  | 2 |  | 3 | 0 | FS702/FP302 |  | Hotel | 6
18 | Sheet 62291 | 15 | Ground Level | WIR - 02185 | Male Toilet | fire fighting pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
19 | Sheet 62291 | 16 | Ground Level | WIR - 02185 | Male Toilet | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 7 | 0 | FS709 |  | Hotel | 14
20 | Sheet 62291 | 17 | Ground Level | WIR - 02185 | Male Toilet | duct | 0.2 | 0.2 | 0.04 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Hotel | 4
21 | Sheet 62291 | 18 | Ground Level | WIR - 02185 | Male Toilet | CHW pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Hotel | 4
22 | Sheet 62291 | 19 | Ground Level | WIR - 02185 | Male Toilet | PPR pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 3 | 0 | FS702/FP302/FB750 |  | Hotel | 6
23 | Sheet 62291 | 20 | Ground Level | WIR - 02185 | Male Toilet | fire fighting pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
24 | Sheet 62291 | 21 | Ground Level | WIR - 02185 | Male Toilet | CDP pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 1 | 0 | FS702/FP302/FB750 |  | Hotel | 2
25 | Sheet 62291 | 21 | Ground Level | WIR - 02185 | FF Lobby | opening |  |  |  | 0.88 | 1.35 | 1.188 | 1.0771 | 2 | 450 | 1 | 969.3816 | FS702/FB750 |  | Hotel | 2.1542
26 | Sheet 62291 | 22 | Ground Level | WIR - 02185 | FF Lobby | fire fighting pipe | 1" |  |  | 2" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
27 | Sheet 62291 | 23 | Ground Level | WIR - 02185 | FF Lobby | fire fighting pipe | 3" |  |  | 5" |  |  |  | 2 |  | 2 | 0 | FS702 |  | Hotel | 4
28 | Sheet 62291 | 24 | Ground Level | WIR - 02185 | FF Lobby | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 6 | 0 | FS709 |  | Hotel | 12
Hotel
January 2023 - Hotel | [19 empty] | Hotel
1 | Sheet 62292 | 25 | Ground Level | WIR - 02185 | Male Toilet | CDP pipe | 3" |  |  | 5" |  |  |  | 1 |  | 1 | 0 | FS702/FP302 | Sheet 62292 | Hotel | 1
2 | Sheet 62292 | 26 | Ground Level | WIR - 02185 | Male Toilet | CHW pipe | 3" |  |  | 5" |  |  |  | 1 |  | 1 | 0 | FS709 |  | Hotel | 1
3 | Sheet 62292 | 27 | Ground Level | WIR - 02185 | Male Toilet | CHW pipe | 3" |  | 0.0044156 |  |  |  |  | 1 |  | 1 | 0 | FS709 |  | Hotel | 1
4 | Sheet 62292 | 28 | Ground Level | WIR - 02185 | Male Toilet | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FS702/FB750 |  | Hotel | 2
5 | Sheet 62292 | 29 | Ground Level | WIR - 02185 | Male Toilet | conduit pipe | 0.5" |  | 0.00013266 |  |  |  |  | 1 |  | 3 | 0 | FS709/FB750 |  | Hotel | 3
6 | Sheet 62292 | 29 | Ground Level | WIR - 02185 | Male Toilet | opening |  |  |  | 0.4 | 0.4 | 0.16 | 0.13519 | 1 | 150 | 1 | 150 | FS702/FB750 |  | Hotel | 1
7 | Sheet 62292 | 30 | Ground Level | WIR - 02185 | Male Toilet | duct | 0.25 | 0.25 | 0.0625 |  |  |  |  | 1 |  | 1 | 0 | FS709/FB750 |  | Hotel | 1
8 | Sheet 62292 | 30 | Ground Level | WIR - 02185 | Male Toilet | opening |  |  |  | 0.3 | 0.38 | 0.114 | 0.0515 | 1 | 50 | 1 | 50 | FS702/FB750 |  | Hotel | 1
9 | Sheet 62292 | 31 | Ground Level | WIR - 02185 | Male Toilet | PPR pipe | 2" |  |  | 4" |  |  |  | 1 |  | 3 | 0 | FS702/FP302 |  | Hotel | 3
10 | Sheet 62292 | 32 | Ground Level | WIR - 02185 | Male Toilet | PVC pipe | 6" |  |  | 8" |  |  |  | 1 |  | 1 | 0 | FS702/FP302 |  | Hotel | 1
11 | Sheet 62292 | 33 | Ground Level | WIR - 02185 | Male Toilet | CHW pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Hotel | 4
12 | Sheet 62292 | 34 | Ground Level | WIR - 02185 | Male Toilet | conduit pipe | 0.5" |  | 0.00013266 |  |  |  |  | 2 |  | 6 | 0 | FS709/FB750 |  | Hotel | 12
13 | Sheet 62292 | 34 | Ground Level | WIR - 02185 | Male Toilet | opening |  |  |  | 0.3 | 0.3 | 0.09 | 0.080373 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
14 | Sheet 62292 | 35 | Ground Level | WIR - 02185 | Male Toilet | duct | 0.25 | 0.4 | 0.1 |  |  |  |  | 2 |  | 1 | 0 | FS709/FB750 |  | Hotel | 2
15 | Sheet 62292 | 35 | Ground Level | WIR - 02185 | Male Toilet | opening |  |  |  | 0.3 | 0.46 | 0.138 | 0.038 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
16 | Sheet 62292 | 36 | Ground Level | WIR - 02185 | Corridor | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 2 | 0 | FS709 |  | Hotel | 4
17 | Sheet 62292 | 37 | Ground Level | WIR - 02185 | Corridor | duct | 0.25 | 0.5 | 0.125 |  |  |  |  | 2 |  | 1 | 0 | FS709/FB750 |  | Hotel | 2
18 | Sheet 62292 | 37 | Ground Level | WIR - 02185 | Corridor | opening |  |  |  | 0.35 | 0.65 | 0.2275 | 0.1025 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
19 | Sheet 62292 | 38 | Ground Level | WIR - 02185 | Corridor | PVC pipe | 6" |  |  | 8" |  |  |  | 2 |  | 2 | 0 | FS702/FP302 |  | Hotel | 4
20 | Sheet 62292 | 39 | Ground Level | WIR - 02185 | Corridor | fire fighting pipe | 6" |  |  | 8" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
21 | Sheet 62292 | 40 | Ground Level | WIR - 02185 | Corridor | duct | 0.2 | 0.6 | 0.12 |  |  |  |  | 2 |  | 1 | 0 | FS709/FB750 |  | Hotel | 2
22 | Sheet 62292 | 40 | Ground Level | WIR - 02185 | Corridor | opening |  |  |  | 0.3 | 0.8 | 0.24 | 0.12 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
23 | Sheet 62292 | 41 | Ground Level | WIR - 02185 | Corridor | CHW pipe | 10" |  |  | 12" |  |  |  | 2 |  | 2 | 0 | FS709 |  | Hotel | 4
24 | Sheet 62292 | 42 | Ground Level | WIR - 02185 | Corridor | PVC pipe | 6" |  |  | 8" |  |  |  | 2 |  | 5 | 0 | FS702/FP302 |  | Hotel | 10
25 | Sheet 62292 | 43 | Ground Level | WIR - 02185 | Corridor | cable trunking | 0.15 | 0.15 | 0.0225 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
26 | Sheet 62292 | 44 | Ground Level | WIR - 02185 | Corridor | cable trunking | 0.07 | 0.07 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
27 | Sheet 62292 | 44 | Ground Level | WIR - 02185 | Corridor | opening |  |  |  | 0.5 | 0.6 | 0.3 | 0.2675 | 2 | 245 | 1 | 490 | FS702/FB750 |  | Hotel | 2
28 | Sheet 62292 | 45 | Ground Level | WIR - 02185 | Corridor | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 9 | 0 | FS709 |  | Hotel | 18
29 | Sheet 62292 | 46 | Ground Level | WIR - 02185 | Corridor | duct | 0.25 | 0.5 | 0.125 | 0.3 | 0.56 | 0.168 |  | 2 |  | 1 | 0 | FS709 |  | Hotel | 2
30 | Sheet 62292 | 47 | Ground Level | WIR - 02185 | Corridor | duct | 0.3 | 0.5 | 0.15 |  |  |  |  | 2 |  | 1 | 0 | FS709/FB750 |  | Hotel | 2
31 | Sheet 62292 | 47 | Ground Level | WIR - 02185 | Corridor | opening |  |  |  | 0.4 | 0.6 | 0.24 | 0.09 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
32 | Sheet 62292 | 48 | Ground Level | WIR - 02185 | Corridor | CDP pipe | 3" |  | 0.0044156 |  |  |  |  | 1 |  | 1 | 0 | FS702/FP302/FB750 |  | Hotel | 1
33 | Sheet 62292 | 48 | Ground Level | WIR - 02185 | Corridor | opening |  |  |  | 0.2 | 0.4 | 0.08 | 0.075584 | 1 | 95 | 1 | 95 | FS702/FB750 |  | Hotel | 1
Hotel
January 2023 - Hotel | [19 empty] | Hotel
1 | Sheet 62293 | 49 | Ground Level | WIR - 02185 | Male Toilet | PVC pipe | 6" |  | 0.017662 |  |  |  |  | 1 |  | 2 | 0 | FS702/FP302/FB750 | Sheet 62293 | Hotel | 2
2 | Sheet 62293 | 50 | Ground Level | WIR - 02185 | Male Toilet | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FS702/FB750 |  | Hotel | 2
3 | Sheet 62293 | 51 | Ground Level | WIR - 02185 | Male Toilet | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 1 |  | 3 | 0 | FS702/FB750 |  | Hotel | 3
4 | Sheet 62293 | 52 | Ground Level | WIR - 02185 | Male Toilet | PVC pipe | 4" |  | 0.00785 |  |  |  |  | 1 |  | 1 | 0 | FS702/FP302/FB750 |  | Hotel | 1
5 | Sheet 62293 | 53 | Ground Level | WIR - 02185 | Male Toilet | fire fighting pipe | 4" |  | 0.00785 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
6 | Sheet 62293 | 54 | Ground Level | WIR - 02185 | Male Toilet | PPR pipe | 3" |  | 0.0044156 |  |  |  |  | 1 |  | 3 | 0 | FS702/FP302/FB750 |  | Hotel | 3
7 | Sheet 62293 | 55 | Ground Level | WIR - 02185 | Male Toilet | conduit pipe | 0.5" |  | 0.00013266 |  |  |  |  | 1 |  | 3 | 0 | FS709/FB750 |  | Hotel | 3
8 | Sheet 62293 | 55 | Ground Level | WIR - 02185 | Male Toilet | opening |  |  |  | 0.58 | 1.95 | 1.131 | 1.0163 | 1 | 450 | 1 | 457.3486 | FS702/FB750 |  | Hotel | 1.0163
9 | Sheet 62293 | 56 | Ground Level | WIR - 02185 | Male Toilet | CHW pipe | 4" |  | 0.00785 |  |  |  |  | 1 |  | 2 | 0 | FS709/FB750 |  | Hotel | 2
10 | Sheet 62293 | 56 | Ground Level | WIR - 02185 | Male Toilet | opening |  |  |  | 0.2 | 0.45 | 0.09 | 0.0743 | 1 | 95 | 1 | 95 | FS702/FB750 |  | Hotel | 1
11 | Sheet 62293 | 57 | Ground Level | WIR - 02185 | Male Toilet | CHW pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Hotel | 4
12 | Sheet 62293 | 57 | Ground Level | WIR - 02185 | Male Toilet | opening |  |  |  | 0.3 | 0.45 | 0.135 | 0.1193 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
13 | Sheet 62293 | 58 | Ground Level | WIR - 02185 | Male Toilet | PPR pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 3 | 0 | FS702/FP302/FB750 |  | Hotel | 6
14 | Sheet 62293 | 59 | Ground Level | WIR - 02185 | Male Toilet | fire fighting pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
15 | Sheet 62293 | 60 | Ground Level | WIR - 02185 | Male Toilet | PVC pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 1 | 0 | FS702/FP302/FB750 |  | Hotel | 2
16 | Sheet 62293 | 61 | Ground Level | WIR - 02185 | Corridor | PVC pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 2 | 0 | FS702/FP302/FB750 |  | Hotel | 4
17 | Sheet 62293 | 62 | Ground Level | WIR - 02185 | Corridor | cable trunking | 0.15 | 0.15 | 0.0225 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
18 | Sheet 62293 | 63 | Ground Level | WIR - 02185 | Corridor | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 2 |  | 3 | 0 | FS702/FB750 |  | Hotel | 6
19 | Sheet 62293 | 64 | Ground Level | WIR - 02185 | Corridor | cable tray | 0.05 | 0.2 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
20 | Sheet 62293 | 65 | Ground Level | WIR - 02185 | Corridor | conduit pipe | 0.5" |  | 0.00013266 |  |  |  |  | 2 |  | 8 | 0 | FS709/FB750 |  | Hotel | 16
21 | Sheet 62293 | 66 | Ground Level | WIR - 02185 | Corridor | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 2 |  | 3 | 0 | FS702/FB750 |  | Hotel | 6
22 | Sheet 62293 | 66 | Ground Level | WIR - 02185 | Corridor | opening |  |  |  | 0.6 | 1.95 | 1.17 | 1.0156 | 2 | 450 | 1 | 914.0411 | FS702/FB750 |  | Hotel | 2.0312
23 | Sheet 62293 | 67 | Ground Level | WIR - 02185 | Corridor | duct | 0.3 | 0.5 | 0.15 |  |  |  |  | 2 |  | 1 | 0 | FS709/FB750 |  | Hotel | 2
24 | Sheet 62293 | 68 | Ground Level | WIR - 02185 | Corridor | duct | 0.25 | 0.5 | 0.125 |  |  |  |  | 2 |  | 1 | 0 | FS709/FB750 |  | Hotel | 2
25 | Sheet 62293 | 68 | Ground Level | WIR - 02185 | Corridor | opening |  |  |  | 0.35 | 1.18 | 0.413 | 0.138 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
26 | Sheet 62293 | 69 | Ground Level | WIR - 02185 | Corridor | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 7 | 0 | FS709 |  | Hotel | 14
27 | Sheet 62293 | 70 | Ground Level | WIR - 02185 | Corridor | PVC pipe | 6" |  |  | 8" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
28 | Sheet 62293 | 71 | Ground Level | WIR - 02185 | Corridor | duct | 0.5 | 1.4 | 0.7 | 0.6 | 1.5 | 0.9 |  | 2 |  | 3 | 0 | FS709 |  | Hotel | 6
29 | Sheet 62293 | 72 | Ground Level | WIR - 02185 | Corridor | fire fighting pipe | 1" |  |  | 2" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
30 | Sheet 62293 | 73 | Ground Level | WIR - 02185 | Corridor | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750 |  | Hotel | 4
31 | Sheet 62293 | 73 | Ground Level | WIR - 02185 | Corridor | opening |  |  |  | 0.25 | 0.5 | 0.125 | 0.105 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
32 | Sheet 62293 | 74 | Ground Level | WIR - 02185 | Corridor | duct | 0.4 | 1.5 | 0.6 |  |  |  |  | 2 |  | 1 | 0 | FS709/FB750 |  | Hotel | 2
33 | Sheet 62293 | 74 | Ground Level | WIR - 02185 | Corridor | opening |  |  |  | 0.55 | 1.7 | 0.935 | 0.335 | 2 | 245 | 1 | 490 | FS702/FB750 |  | Hotel | 2
34 | Sheet 62293 | 75 | Ground Level | WIR - 02185 | Corridor | fire fighting pipe | 1" |  |  | 2" |  |  |  | 2 |  | 3 | 0 | FS702 |  | Hotel | 6
Hotel
January 2023 - Hotel | [19 empty] | Hotel
1 | Sheet 62294 | 76 | Ground Level | WIR - 02185 | Ball Room | duct | 0.5 | 1.4 | 0.7 |  |  |  |  | 2 |  | 3 | 0 | FS709/FB750 | Sheet 62294 | Hotel | 6
2 | Sheet 62294 | 76 | Ground Level | WIR - 02185 | Ball Room | opening |  |  |  | 0.6 | 1.5 | 0.9 | 0.2 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2
3 | Sheet 62294 | 77 | Ground Level | WIR - 02185 | Ball Room | fire fighting pipe | 1" |  |  | 2" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
4 | Sheet 62294 | 78 | Ground Level | WIR - 02185 | Ball Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750 |  | Hotel | 4
5 | Sheet 62294 | 78 | Ground Level | WIR - 02185 | Ball Room | opening |  |  |  | 0.25 | 0.5 | 0.125 | 0.105 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
6 | Sheet 62294 | 79 | Ground Level | WIR - 02185 | Ball Room | duct | 0.4 | 1.5 | 0.6 |  |  |  |  | 2 |  | 1 | 0 | FS709/FB750 |  | Hotel | 2
7 | Sheet 62294 | 79 | Ground Level | WIR - 02185 | Ball Room | opening |  |  |  | 0.55 | 1.7 | 0.935 | 0.335 | 2 | 245 | 1 | 490 | FS702/FB750 |  | Hotel | 2
8 | Sheet 62294 | 80 | Ground Level | WIR - 02185 | Ball Room | fire fighting pipe | 1" |  |  | 2" |  |  |  | 2 |  | 3 | 0 | FS702 |  | Hotel | 6
9 | Sheet 62294 | 81 | Ground Level | WIR - 02185 | Ball Room | fire fighting pipe | 3" |  |  | 5" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
10 | Sheet 62294 | 82 | Ground Level | WIR - 02185 | Ball Room | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 13 | 0 | FS709 |  | Hotel | 26
11 | Sheet 62294 | 83 | Ground Level | WIR - 02185 | Ball Room | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 10 | 0 | FS709 |  | Hotel | 20
12 | Sheet 62294 | 84 | Ground Level | WIR - 02185 | Ball Room | duct | 0.4 | 1 | 0.4 |  |  |  |  | 2 |  | 1 | 0 | FS709/FB750 |  | Hotel | 2
13 | Sheet 62294 | 84 | Ground Level | WIR - 02185 | Ball Room | opening |  |  |  | 0.6 | 1.5 | 0.9 | 0.5 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Hotel | 2
14 | Sheet 62294 | 85 | Ground Level | WIR - 02185 | Ball Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750 |  | Hotel | 4
15 | Sheet 62294 | 85 | Ground Level | WIR - 02185 | Ball Room | opening |  |  |  | 0.15 | 0.25 | 0.0375 | 0.0175 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
16 | Sheet 62294 | 86 | Ground Level | WIR - 02185 | Ball Room | duct | 0.4 | 1.4 | 0.56 |  |  |  |  | 2 |  | 1 | 0 | FS709/FB750 |  | Hotel | 2
17 | Sheet 62294 | 86 | Ground Level | WIR - 02185 | Ball Room | opening |  |  |  | 0.46 | 1.5 | 0.69 | 0.13 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
18 | Sheet 62294 | 87 | Ground Level | WIR - 02185 | Ball Room | duct | 0.4 | 1.4 | 0.56 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Hotel | 4
19 | Sheet 62294 | 87 | Ground Level | WIR - 02185 | Ball Room | opening |  |  |  | 1 | 1.5 | 1.5 | 0.38 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Hotel | 2
20 | Sheet 62294 | 88 | Ground Level | WIR - 02185 | Ball Room | PVC pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 1 | 0 | FS702/FP302/FB750 |  | Hotel | 2
21 | Sheet 62294 | 88 | Ground Level | WIR - 02185 | Ball Room | opening |  |  |  | 0.55 | 0.6 | 0.33 | 0.31234 | 2 | 245 | 1 | 490 | FS702/FB750 |  | Hotel | 2
22 | Sheet 62294 | 89 | Ground Level | WIR - 02185 | Ball Room | PVC pipe | 6" |  |  | 8" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
23 | Sheet 62294 | 90 | Ground Level | WIR - 02185 | Ball Room | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 14 | 0 | FS709 |  | Hotel | 28
24 | Sheet 62294 | 91 | Ground Level | WIR - 02185 | Ball Room | fire fighting pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
25 | Sheet 62294 | 92 | Ground Level | WIR - 02185 | Ball Room | cable trunking | 0.15 | 0.15 | 0.0225 |  |  |  |  | 2 |  | 3 | 0 | FS702/FB750 |  | Hotel | 6
26 | Sheet 62294 | 93 | Ground Level | WIR - 02185 | Ball Room | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750 |  | Hotel | 4
27 | Sheet 62294 | 93 | Ground Level | WIR - 02185 | Ball Room | opening |  |  |  | 0.25 | 0.8 | 0.2 | 0.1125 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
28 | Sheet 62294 | 94 | Ground Level | WIR - 02185 | Ball Room | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 11 | 0 | FS709 |  | Hotel | 22
29 | Sheet 62294 | 95 | Ground Level | WIR - 02185 | Ball Room | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 13 | 0 | FS709 |  | Hotel | 26
30 | Sheet 62294 | 96 | Ground Level | WIR - 02185 | Ball Room | PVC pipe | 4" |  |  | 6" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
31 | Sheet 62294 | 97 | Ground Level | WIR - 02185 | Ball Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
32 | Sheet 62294 | 98 | Ground Level | WIR - 02185 | Ball Room | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
33 | Sheet 62294 | 99 | Ground Level | WIR - 02185 | Ball Room | cable tray | 0.05 | 0.2 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
34 | Sheet 62294 | 99 | Ground Level | WIR - 02185 | Ball Room | opening |  |  |  | 0.25 | 0.5 | 0.125 | 0.095 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
35 | Sheet 62294 | 100 | Ground Level | WIR - 02185 | Ball Room | PVC pipe | 6" |  |  | 8" |  |  |  | 2 |  | 2 | 0 | FS702/FP302 |  | Hotel | 4
36 | Sheet 62294 | 101 | Ground Level | WIR - 02185 | Ball Room | PVC pipe | 4" |  |  | 6" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
37 | Sheet 62294 | 102 | Ground Level | WIR - 02185 | Ball Room | PVC pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 1 | 0 | FS702/FP302/FB750 |  | Hotel | 2
38 | Sheet 62294 | 102 | Ground Level | WIR - 02185 | Ball Room | opening |  |  |  | 0.2 | 0.4 | 0.08 | 0.07215 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
Hotel
January 2023 - Hotel | [19 empty] | Hotel
1 | Sheet 62295 | 103 | Ground Level | WIR - 02185 | Ball Room | PVC pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 1 | 0 | FS702/FP302/FB750 | Sheet 62295 | Hotel | 2
2 | Sheet 62295 | 103 | Ground Level | WIR - 02185 | Ball Room | opening |  |  |  | 0.3 | 0.5 | 0.15 | 0.14215 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
3 | Sheet 62295 | 104 | Ground Level | WIR - 02185 | Ball Room | PVC pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 1 | 0 | FS702/FP302/FB750 |  | Hotel | 2
4 | Sheet 62295 | 105 | Ground Level | WIR - 02185 | Ball Room | PVC pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 2 | 0 | FS702/FP302/FB750 |  | Hotel | 4
5 | Sheet 62295 | 105 | Ground Level | WIR - 02185 | Ball Room | opening |  |  |  | 0.25 | 0.45 | 0.1125 | 0.10073 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
6 | Sheet 62295 | 106 | Ground Level | WIR - 02185 | Ball Room | fire fighting pipe | 1" |  |  | 2" |  |  |  | 2 |  | 2 | 0 | FS702 |  | Hotel | 4
7 | Sheet 62295 | 107 | Ground Level | WIR - 02185 | Ball Room | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 15 | 0 | FS709 |  | Hotel | 30
8 | Sheet 62295 | 108 | Ground Level | WIR - 02185 | Ball Room | PVC pipe | 4" |  | 0.00785 |  |  |  |  | 1 |  | 1 | 0 | FS702/FP302/FB750 |  | Hotel | 1
9 | Sheet 62295 | 108 | Ground Level | WIR - 02185 | Ball Room | opening |  |  |  | 0.41 | 0.98 | 0.4018 | 0.39395 | 1 | 310 | 1 | 310 | FS702/FB750 |  | Hotel | 1
10 | Sheet 62295 | 109 | Ground Level | WIR - 02185 | Ball Room | PVC pipe | 4" |  |  | 6" |  |  |  | 2 |  | 4 | 0 | FS702/FP302 |  | Hotel | 8
11 | Sheet 62295 | 110 | Ground Level | WIR - 02185 | Ball Room | fire fighting pipe | 3" |  |  | 5" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
12 | Sheet 62295 | 111 | Ground Level | WIR - 02185 | Ball Room | PVC pipe | 1" |  |  | 2" |  |  |  | 2 |  | 4 | 0 | FS702/FP302 |  | Hotel | 8
13 | Sheet 62295 | 112 | Ground Level | WIR - 02185 | Ball Room | PVC pipe | 4" |  |  | 6" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
14 | Sheet 62295 | 113 | Ground Level | WIR - 02185 | Ball Room | PVC pipe | 6" |  |  | 8" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
15 | Sheet 62295 | 114 | Ground Level | WIR - 02185 | Ball Room | PVC pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 1 | 0 | FS702/FP302/FB750 |  | Hotel | 2
16 | Sheet 62295 | 115 | Ground Level | WIR - 02185 | Ball Room | PVC pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 1 | 0 | FS702/FP302/FB750 |  | Hotel | 2
17 | Sheet 62295 | 115 | Ground Level | WIR - 02185 | Ball Room | opening |  |  |  | 0.3 | 0.45 | 0.135 | 0.10949 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
18 | Sheet 62295 | 116 | Ground Level | WIR - 02185 | Ball Room | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 9 | 0 | FS709 |  | Hotel | 18
19 | Sheet 62295 | 117 | Ground Level | WIR - 02185 | Ball Room | PVC pipe | 4" |  |  | 6" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
20 | Sheet 62295 | 118 | Ground Level | WIR - 02185 | Ball Room | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 22 | 0 | FS709 |  | Hotel | 44
21 | Sheet 62295 | 119 | Ground Level | WIR - 02185 | Ball Room | duct | 0.65 | 1 | 0.65 |  |  |  |  | 2 |  | 1 | 0 | FS709/FB750 |  | Hotel | 2
22 | Sheet 62295 | 119 | Ground Level | WIR - 02185 | Ball Room | opening |  |  |  | 0.75 | 1.1 | 0.825 | 0.175 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2
23 | Sheet 62295 | 120 | Ground Level | WIR - 02185 | Ball Room | duct | 8" |  | 0.032349 |  |  |  |  | 2 |  | 4 | 0 | FS709 |  | Hotel | 8
24 | Sheet 62295 | 120 | Ground Level | WIR - 02185 | Ball Room | opening |  |  |  | 0.6 | 0.75 | 0.45 | 0.3206 | 2 | 245 | 1 | 490 | FS702/FB750 |  | Hotel | 2
25 | Sheet 62295 | 121 | Ground Level | WIR - 02185 | Ball Room | duct | 0.5 | 0.7 | 0.35 |  |  |  |  | 2 |  | 1 | 0 | FS709/FB750 |  | Hotel | 2
26 | Sheet 62295 | 121 | Ground Level | WIR - 02185 | Ball Room | opening |  |  |  | 0.56 | 0.76 | 0.4256 | 0.0756 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
27 | Sheet 62295 | 122 | Ground Level | WIR - 02185 | Ball Room | duct | 8" |  | 0.032349 |  |  |  |  | 2 |  | 4 | 0 | FS709 |  | Hotel | 8
28 | Sheet 62295 | 122 | Ground Level | WIR - 02185 | Ball Room | opening |  |  |  | 0.35 | 0.4 | 0.14 | 0.010604 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
29 | Sheet 62295 | 123 | Ground Level | WIR - 02185 | Ball Room | PVC pipe | 4" |  |  | 6" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
30 | Sheet 62295 | 124 | Ground Level | WIR - 02185 | Ball Room | fire fighting pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
31 | Sheet 62295 | 125 | Ground Level | WIR - 02185 | Ball Room | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 10 | 0 | FS709 |  | Hotel | 20
32 | Sheet 62295 | 126 | Ground Level | WIR - 02185 | Ball Room | PVC pipe | 4" |  |  | 6" |  |  |  | 2 |  | 2 | 0 | FS702/FP302 |  | Hotel | 4
33 | Sheet 62295 | 127 | Ground Level | WIR - 02185 | Ball Room | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 2 | 0 | FS709 |  | Hotel | 4
34 | Sheet 62295 | 128 | Ground Level | WIR - 02185 | Ball Room | duct | 8" |  |  | 10" |  | 0.050645 |  | 2 |  | 6 | 0 | FS709 |  | Hotel | 12
35 | Sheet 62295 | 129 | Ground Level | WIR - 02185 | Ball Room | fire fighting pipe | 4" |  |  | 6" |  |  |  | 2 |  | 2 | 0 | FS702 |  | Hotel | 4
Hotel
January 2023 - Hotel | [19 empty] | Hotel
1 | Sheet 62296 | 130 | Ground Level | WIR - 02185 | Ball Room | fire fighting pipe | 3" |  |  | 5" |  |  |  | 2 |  | 2 | 0 | FS702 | Sheet 62296 | Hotel | 4
2 | Sheet 62296 | 131 | Ground Level | WIR - 02185 | Ball Room | duct | 0.2 | 0.3 | 0.06 | 0.26 | 0.36 | 0.0936 |  | 2 |  | 1 | 0 | FS709 |  | Hotel | 2
3 | Sheet 62296 | 132 | Ground Level | WIR - 02185 | Ball Room | fire fighting pipe | 1" |  |  | 2" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
4 | Sheet 62296 | 133 | Ground Level | WIR - 02185 | Ball Room | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 20 | 0 | FS709 |  | Hotel | 40
5 | Sheet 62296 | 134 | Ground Level | WIR - 02185 | Ball Room | conduit pipe | 0.5" |  | 0.00013266 |  |  |  |  | 2 |  | 13 | 0 | FS709/FB750 |  | Hotel | 26
6 | Sheet 62296 | 134 | Ground Level | WIR - 02185 | Ball Room | opening |  |  |  | 0.15 | 1 | 0.15 | 0.14828 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
7 | Sheet 62296 | 135 | Ground Level | WIR - 02185 | Ball Room | duct | 0.35 | 1 | 0.35 |  |  |  |  | 2 |  | 1 | 0 | FS709/FB750 |  | Hotel | 2
8 | Sheet 62296 | 135 | Ground Level | WIR - 02185 | Ball Room | opening |  |  |  | 0.42 | 1.1 | 0.462 | 0.112 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
9 | Sheet 62296 | 136 | Ground Level | WIR - 02185 | Ball Room | PVC pipe | 6" |  |  | 8" |  |  |  | 2 |  | 4 | 0 | FS702/FP302 |  | Hotel | 8
10 | Sheet 62296 | 137 | Ground Level | WIR - 02185 | Ball Room | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.3 | 0.075 |  | 2 |  | 1 | 0 | FS709 |  | Hotel | 2
11 | Sheet 62296 | 138 | Ground Level | WIR - 02185 | Lobby | PVC pipe | 6" |  |  | 8" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
12 | Sheet 62296 | 139 | Ground Level | WIR - 02185 | Lobby | CHW pipe | 4" |  |  | 6" |  |  |  | 2 |  | 2 | 0 | FS709 |  | Hotel | 4
13 | Sheet 62296 | 140 | Ground Level | WIR - 02185 | Lobby | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 6 | 0 | FS709 |  | Hotel | 12
14 | Sheet 62296 | 141 | Ground Level | WIR - 02185 | Lobby | fire fighting pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
15 | Sheet 62296 | 142 | Ground Level | WIR - 02185 | Lobby | PVC pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 2 | 0 | FS702/FP302/FB750 |  | Hotel | 4
16 | Sheet 62296 | 143 | Ground Level | WIR - 02185 | Lobby | PPR pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 3 | 0 | FS702/FP302/FB750 |  | Hotel | 6
17 | Sheet 62296 | 144 | Ground Level | WIR - 02185 | Lobby | PVC pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 2 | 0 | FS702/FP302/FB750 |  | Hotel | 4
18 | Sheet 62296 | 144 | Ground Level | WIR - 02185 | Lobby | opening |  |  |  | 0.6 | 0.9 | 0.54 | 0.45807 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Hotel | 2
19 | Sheet 62296 | 145 | Ground Level | WIR - 02185 | Lobby | duct | 0.2 | 0.4 | 0.08 | 0.25 | 0.45 | 0.1125 |  | 2 |  | 1 | 0 | FS709 |  | Hotel | 2
20 | Sheet 62296 | 146 | Ground Level | WIR - 02185 | Lobby Shaft | PPR pipe | 3" |  |  | 5" |  |  |  | 2 |  | 2 | 0 | FS702/FP302 |  | Hotel | 4
21 | Sheet 62296 | 147 | Ground Level | WIR - 02185 | Lobby Shaft | fire fighting pipe | 6" |  |  | 8" |  |  |  | 2 |  | 2 | 0 | FS702 |  | Hotel | 4
22 | Sheet 62296 | 148 | Ground Level | WIR - 02185 | Lobby Shaft | PVC pipe | 6" |  |  | 8" |  |  |  | 2 |  | 2 | 0 | FS702/FP302 |  | Hotel | 4
23 | Sheet 62296 | 149 | Ground Level | WIR - 02185 | Lobby Shaft | CDP pipe | 3" |  |  | 5" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
24 | Sheet 62296 | 150 | Ground Level | WIR - 02185 | Lobby Shaft | fire fighting pipe | 1" |  |  | 2" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
25 | Sheet 62296 | 151 | Ground Level | WIR - 02185 | Lobby Shaft | PVC pipe | 6" |  | 0.017662 |  |  |  |  | 1 |  | 1 | 0 | FS702/FP302/FB750 |  | Hotel | 1
26 | Sheet 62296 | 151 | Ground Level | WIR - 02185 | Lobby Shaft | opening |  |  |  | 0.4 | 3.38 | 1.352 | 1.3343 | 1 | 450 | 1 | 600.4519 | FS702/FB750 |  | Hotel | 1.3343
27 | Sheet 62296 | 152 | Ground Level | WIR - 02185 | Lobby Shaft | PPR pipe | 4" |  |  | 6" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
28 | Sheet 62296 | 153 | Ground Level | WIR - 02185 | Lobby Shaft | PPR pipe | 3" |  |  | 5" |  |  |  | 2 |  | 2 | 0 | FS702/FP302 |  | Hotel | 4
29 | Sheet 62296 | 154 | Ground Level | WIR - 02185 | Lobby Shaft | fire fighting pipe | 1" |  |  | 2" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
30 | Sheet 62296 | 155 | Ground Level | WIR - 02185 | Lobby Shaft | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 2 | 0 | FS709 |  | Hotel | 4
Hotel
January 2023 - Hotel | [19 empty] | Hotel
1 | Sheet 62297 | 156 | Ground Level | WIR - 02185 | Housekeeping | CDP pipe | 2" |  | 0.0019625 |  |  |  |  | 1 |  | 1 | 0 | FS702/FP302/FB750 | Sheet 62297 | Hotel | 1
2 | Sheet 62297 | 157 | Ground Level | WIR - 02185 | Housekeeping | CHW pipe | 2" |  | 0.0019625 |  |  |  |  | 1 |  | 2 | 0 | FS709/FB750 |  | Hotel | 2
3 | Sheet 62297 | 158 | Ground Level | WIR - 02185 | Housekeeping | duct | 0.25 | 0.4 | 0.1 |  |  |  |  | 1 |  | 1 | 0 | FS709/FB750 |  | Hotel | 1
4 | Sheet 62297 | 159 | Ground Level | WIR - 02185 | Housekeeping | cable trunking | 0.15 | 0.15 | 0.0225 |  |  |  |  | 1 |  | 2 | 0 | FS702/FB750 |  | Hotel | 2
5 | Sheet 62297 | 160 | Ground Level | WIR - 02185 | Housekeeping | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
6 | Sheet 62297 | 161 | Ground Level | WIR - 02185 | Housekeeping | cable tray | 0.05 | 0.2 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
7 | Sheet 62297 | 161 | Ground Level | WIR - 02185 | Housekeeping | opening |  |  |  | 0.5 | 0.8 | 0.4 | 0.22911 | 1 | 180 | 1 | 180 | FS702/FB750 |  | Hotel | 1
8 | Sheet 62297 | 162 | Ground Level | WIR - 02185 | Housekeeping | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 3 | 0 | FS702/FB750 |  | Hotel | 3
9 | Sheet 62297 | 163 | Ground Level | WIR - 02185 | Housekeeping | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FS702/FB750 |  | Hotel | 2
10 | Sheet 62297 | 164 | Ground Level | WIR - 02185 | Housekeeping | fire fighting pipe | 1" |  | 0.00049063 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
11 | Sheet 62297 | 164 | Ground Level | WIR - 02185 | Housekeeping | opening |  |  |  | 0.25 | 0.9 | 0.225 | 0.17451 | 1 | 180 | 1 | 180 | FS702/FB750 |  | Hotel | 1
12 | Sheet 62297 | 165 | Ground Level | WIR - 02185 | Housekeeping | PVC pipe | 3" |  |  | 5" |  |  |  | 1 |  | 1 | 0 | FS702/FP302 |  | Hotel | 1
13 | Sheet 62297 | 166 | Ground Level | WIR - 02185 | Housekeeping | cable trunking | 0.15 | 0.15 | 0.0225 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750 |  | Hotel | 4
14 | Sheet 62297 | 167 | Ground Level | WIR - 02185 | Housekeeping | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
15 | Sheet 62297 | 167 | Ground Level | WIR - 02185 | Housekeeping | opening |  |  |  | 0.2 | 0.5 | 0.1 | 0.045 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
16 | Sheet 62297 | 168 | Ground Level | WIR - 02185 | Housekeeping | CDP pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
17 | Sheet 62297 | 169 | Ground Level | WIR - 02185 | Housekeeping | duct | 0.2 | 0.2 | 0.04 | 0.26 | 0.26 | 0.0676 |  | 1 |  | 1 | 0 | FS709 |  | Hotel | 1
18 | Sheet 62297 | 170 | Ground Level | WIR - 02185 | Housekeeping | cable tray |  |  |  | 0.15 | 0.4 | 0.06 |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
19 | Sheet 62297 | 171 | Ground Level | WIR - 02185 | Housekeeping | duct | 0.2 | 0.2 | 0.04 | 0.26 | 0.26 | 0.0676 |  | 1 |  | 3 | 0 | FS709 |  | Hotel | 3
20 | Sheet 62297 | 172 | Ground Level | WIR - 02185 | Housekeeping | fire fighting pipe | 1" |  |  | 2" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
21 | Sheet 62297 | 173 | Ground Level | WIR - 02185 | Housekeeping | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 2 |  | 3 | 0 | FS702/FB750 |  | Hotel | 6
22 | Sheet 62297 | 174 | Ground Level | WIR - 02185 | Housekeeping | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
23 | Sheet 62297 | 174 | Ground Level | WIR - 02185 | Housekeeping | opening |  |  |  | 0.3 | 0.5 | 0.15 | 0.11 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
24 | Sheet 62297 | 175 | Ground Level | WIR - 02185 | Housekeeping | cable tray |  |  |  | 0.2 | 0.3 | 0.06 |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
25 | Sheet 62297 | 176 | Ground Level | WIR - 02185 | Housekeeping | cable trunking |  |  |  | 0.08 | 0.08 | 0.0064 |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
26 | Sheet 62297 | 177 | Ground Level | WIR - 02185 | Housekeeping | duct | 0.2 | 0.2 | 0.04 | 0.26 | 0.26 | 0.0676 |  | 1 |  | 2 | 0 | FS709 |  | Hotel | 2
27 | Sheet 62297 | 178 | Ground Level | WIR - 02185 | Housekeeping | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 15 | 0 | FS709 |  | Hotel | 30
28 | Sheet 62297 | 179 | Ground Level | WIR - 02185 | Housekeeping | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750 |  | Hotel | 4
29 | Sheet 62297 | 179 | Ground Level | WIR - 02185 | Housekeeping | opening |  |  |  | 0.25 | 0.3 | 0.075 | 0.055 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
30 | Sheet 62297 | 180 | Ground Level | WIR - 02185 | Housekeeping | cable trunking |  |  |  | 0.08 | 0.1 | 0.008 |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
31 | Sheet 62297 | 181 | Ground Level | WIR - 02185 | Housekeeping | cable tray | 0.05 | 0.2 | 0.01 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750 |  | Hotel | 4
32 | Sheet 62297 | 181 | Ground Level | WIR - 02185 | Housekeeping | opening |  |  |  | 0.3 | 0.4 | 0.12 | 0.1 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
Hotel
January 2023 - Hotel | [19 empty] | Hotel
1 | Sheet 62298 | 182 | Ground Level | WIR - 02185 | Housekeeping | duct | 0.3 | 0.5 | 0.15 |  |  |  |  | 2 |  | 1 | 0 | FS709/FB750 | Sheet 62298 | Hotel | 2
2 | Sheet 62298 | 183 | Ground Level | WIR - 02185 | Housekeeping | duct | 0.25 | 0.4 | 0.1 |  |  |  |  | 2 |  | 1 | 0 | FS709/FB750 |  | Hotel | 2
3 | Sheet 62298 | 183 | Ground Level | WIR - 02185 | Housekeeping | opening |  |  |  | 0.5 | 1.3 | 0.65 | 0.4 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Hotel | 2
4 | Sheet 62298 | 184 | Ground Level | WIR - 02185 | Housekeeping | duct | 0.3 | 0.4 | 0.12 |  |  |  |  | 1 |  | 1 | 0 | FS709/FB750 |  | Hotel | 1
5 | Sheet 62298 | 184 | Ground Level | WIR - 02185 | Housekeeping | opening |  |  |  | 0.4 | 0.5 | 0.2 | 0.08 | 1 | 95 | 1 | 95 | FS702/FB750 |  | Hotel | 1
6 | Sheet 62298 | 185 | Ground Level | WIR - 02185 | Housekeeping | PVC pipe | 2" |  |  | 4" |  |  |  | 1 |  | 1 | 0 | FS702/FP302 |  | Hotel | 1
7 | Sheet 62298 | 186 | Ground Level | WIR - 02185 | Housekeeping | duct | 0.4 | 0.6 | 0.24 |  |  |  |  | 1 |  | 1 | 0 | FS709/FB750 |  | Hotel | 1
8 | Sheet 62298 | 186 | Ground Level | WIR - 02185 | Housekeeping | opening |  |  |  | 0.5 | 0.7 | 0.35 | 0.11 | 1 | 150 | 1 | 150 | FS702/FB750 |  | Hotel | 1
9 | Sheet 62298 | 187 | Ground Level | WIR - 02185 | Housekeeping | duct | 0.4 | 0.6 | 0.24 |  |  |  |  | 2 |  | 1 | 0 | FS709/FB750 |  | Hotel | 2
10 | Sheet 62298 | 187 | Ground Level | WIR - 02185 | Housekeeping | opening |  |  |  | 0.6 | 0.8 | 0.48 | 0.24 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2
11 | Sheet 62298 | 188 | Ground Level | WIR - 02185 | Housekeeping | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 1 |  | 1 | 0 | FS709 |  | Hotel | 1
12 | Sheet 62298 | 189 | Ground Level | WIR - 02185 | Kitchen | duct | 0.25 | 0.25 | 0.0625 |  |  |  |  | 2 |  | 3 | 0 | FS709/FB750 |  | Hotel | 6
13 | Sheet 62298 | 189 | Ground Level | WIR - 02185 | Kitchen | opening |  |  |  | 0.3 | 0.33 | 0.099 | 0.0365 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
14 | Sheet 62298 | 190 | Ground Level | WIR - 02185 | Corridor | duct | 0.3 | 1 | 0.3 |  |  |  |  | 2 |  | 1 | 0 | FS709/FB750 |  | Hotel | 2
15 | Sheet 62298 | 190 | Ground Level | WIR - 02185 | Corridor | opening |  |  |  | 0.4 | 1.08 | 0.432 | 0.132 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
16 | Sheet 62298 | 191 | Ground Level | WIR - 02185 | Housekeeping | PVC pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 3 | 0 | FS702/FP302/FB750 |  | Hotel | 6
17 | Sheet 62298 | 192 | Ground Level | WIR - 02185 | Housekeeping | PVC pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 | FS702/FP302/FB750 |  | Hotel | 2
18 | Sheet 62298 | 192 | Ground Level | WIR - 02185 | Housekeeping | opening |  |  |  | 0.75 | 0.95 | 0.7125 | 0.68699 | 2 | 400 | 1 | 800 | FS702/FB750 |  | Hotel | 2
Hotel
January 2023 - Hotel | [19 empty] | Hotel
1 | Sheet 61939 | 1 | Level 18 | WIR - 02249 | Fire Pump Room | metal pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 | Sheet 61939 | Hotel | 2
2 | Sheet 61939 | 1 | Level 18 | WIR - 02249 | Fire Pump Room | opening |  |  |  | 0.3 | 0.3 | 0.09 | 0.072337 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
3 | Sheet 61939 | 2 | Level 18 | WIR - 02249 | Fire Pump Room | duct | 0.5 | 4.5 | 2.25 | 0.6 | 4.6 | 2.76 |  | 1 |  | 1 | 0 | FS709 |  | Hotel | 1
4 | Sheet 61939 | 3 | Level 18 | WIR - 02249 | Fire Pump Room | duct | 0.2 | 0.4 | 0.08 | 0.25 | 0.45 | 0.1125 |  | 1 |  | 2 | 0 | FS709 |  | Hotel | 2
5 | Sheet 61939 | 4 | Level 18 | WIR - 02249 | Fire Pump Room | PVC pipe | 4" |  |  | 6" |  |  |  | 1 |  | 2 | 0 | FS702/FP302 |  | Hotel | 2
6 | Sheet 61939 | 5 | Level 18 | WIR - 02249 | Fire Pump Room | fire fighting pipe | 6" |  |  | 8" |  |  |  | 1 |  | 3 | 0 | FS702 |  | Hotel | 3
7 | Sheet 61939 | 6 | Level 18 | WIR - 02249 | Fire Pump Room | CDP pipe | 3" |  |  | 5" |  |  |  | 1 |  | 1 | 0 | FS702/FP302 |  | Hotel | 1
8 | Sheet 61939 | 7 | Level 18 | WIR - 02249 | Fire Pump Room | CHW pipe | 3" |  |  | 5" |  |  |  | 1 |  | 2 | 0 | FS709 |  | Hotel | 2
9 | Sheet 61939 | 8 | Level 18 | WIR - 02249 | Fire Pump Room | PVC pipe | 4" |  | 0.00785 |  |  |  |  | 1 |  | 2 | 0 | FS702/FP302/FB750 |  | Hotel | 2
10 | Sheet 61939 | 8 | Level 18 | WIR - 02249 | Fire Pump Room | opening |  |  |  | 0.25 | 0.4 | 0.1 | 0.0843 | 1 | 95 | 1 | 95 | FS702/FB750 |  | Hotel | 1
11 | Sheet 61939 | 9 | Level 18 | WIR - 02249 | High Level | PVC pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 2 | 0 | FS702/FP302/FB750 |  | Hotel | 4
12 | Sheet 61939 | 10 | Level 18 | WIR - 02249 | High Level | CHW pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Hotel | 4
13 | Sheet 61939 | 11 | Level 18 | WIR - 02249 | High Level | PVC pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 | FS702/FP302/FB750 |  | Hotel | 2
14 | Sheet 61939 | 11 | Level 18 | WIR - 02249 | High Level | opening |  |  |  | 0.48 | 2.7 | 1.296 | 1.243 | 2 | 450 | 1 | 1118.7112 | FS702/FB750 |  | Hotel | 2.486
15 | Sheet 61939 | 12 | Level 18 | WIR - 02249 | Wall | fire fighting pipe | 6" |  |  | 8" |  |  |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
16 | Sheet 61939 | 13 | Level 18 | WIR - 02249 | Wall | duct | 0.2 | 0.4 | 0.08 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Hotel | 4
17 | Sheet 61939 | 13 | Level 18 | WIR - 02249 | Wall | opening |  |  |  | 0.3 | 0.55 | 0.165 | 0.085 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
18 | Sheet 61939 | 14 | Level 18 | WIR - 02249 | Wall | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 2 | 0 | FS709 |  | Hotel | 4
19 | Sheet 61939 | 15 | Level 18 | WIR - 02249 | Wall | cable trunking |  |  |  | 0.08 | 0.1 | 0.008 |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
20 | Sheet 61939 | 16 | Level 18 | WIR - 02249 | Wall | fire fighting pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
21 | Sheet 61939 | 17 | Level 18 | WIR - 02249 | Wall | PVC pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 3 | 0 | FS702/FP302/FB750 |  | Hotel | 6
22 | Sheet 61939 | 18 | Level 18 | WIR - 02249 | Wall | PVC pipe | 8" |  | 0.032349 |  |  |  |  | 2 |  | 2 | 0 | FS702/FP302/FB750 |  | Hotel | 4
23 | Sheet 61939 | 19 | Level 18 | WIR - 02249 | Wall | CHW pipe | 5" |  | 0.012266 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Hotel | 4
24 | Sheet 61939 | 20 | Level 18 | WIR - 02249 | Wall | fire fighting pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 3 | 0 | FS702/FB750 |  | Hotel | 6
25 | Sheet 61939 | 20 | Level 18 | WIR - 02249 | Wall | opening |  |  |  | 0.6 | 2 | 1.2 | 1.0048 | 2 | 450 | 1 | 900 | FS702/FB750 |  | Hotel | 2
26 | Sheet 61939 | 21 | Level 18 | WIR - 02249 | Wall | duct | 1.05 | 1.6 | 1.68 |  |  |  |  | 2 |  | 1 | 0 | FS709/FB750 |  | Hotel | 3.36
27 | Sheet 61939 | 22 | Level 18 | WIR - 02249 | Wall | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
28 | Sheet 61939 | 22 | Level 18 | WIR - 02249 | Wall | opening |  |  |  | 1.6 | 1.85 | 2.96 | 1.265 | 2 | 450 | 1 | 1138.5 | FS702/FB750 |  | Hotel | 2.53
29 | Sheet 61939 | 23 | Level 18 | WIR - 02249 | Wall | fire fighting pipe | 8" |  |  | 10" |  |  |  | 2 |  | 2 | 0 | FS702 |  | Hotel | 4
30 | Sheet 61939 | 24 | Level 18 | WIR - 02249 | Wall | duct | 0.5 | 4.5 | 2.25 |  |  |  |  | 1 |  | 1 | 0 | FS709/FB750 |  | Hotel | 2.25
31 | Sheet 61939 | 24 | Level 18 | WIR - 02249 | Wall | opening |  |  |  | 0.58 | 4.6 | 2.668 | 0.418 | 1 | 310 | 1 | 310 | FS702/FB750 |  | Hotel | 1
32 | Sheet 61939 | 25 | Level 18 | WIR - 02249 | Entry door | duct | 0.2 | 0.4 | 0.08 |  |  |  |  | 2 |  | 4 | 0 | FS709/FB750 |  | Hotel | 8
33 | Sheet 61939 | 26 | Level 18 | WIR - 02249 | Entry door | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
34 | Sheet 61939 | 26 | Level 18 | WIR - 02249 | Entry door | opening |  |  |  | 0.4 | 2 | 0.8 | 0.47 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Hotel | 2
35 | Sheet 61939 | 27 | Level 18 | WIR - 02249 | Staircase 07 | duct | 0.5 | 0.5 | 0.25 | 0.55 | 0.55 | 0.3025 |  | 2 |  | 1 | 0 | FS709 |  | Hotel | 2
Hotel
January 2023 - Hotel | [19 empty] | Hotel
1 | Sheet 61940 | 28 | Level 18 | WIR - 02249 | Fire Pump Room | PPR pipe | 0.5" |  |  | 2" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 | Sheet 61940 | Hotel | 2
2 | Sheet 61940 | 29 | Level 18 | WIR - 02249 | Fire Pump Room | PVC pipe | 6" |  |  | 8" |  |  |  | 2 |  | 7 | 0 | FS702/FP302 |  | Hotel | 14
3 | Sheet 61940 | 30 | Level 18 | WIR - 02249 | Fire Pump Room | PPR pipe | 6" |  |  | 8" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
4 | Sheet 61940 | 31 | Level 18 | WIR - 02249 | Fire Pump Room | fire fighting pipe | 6" |  |  | 8" |  |  |  | 2 |  | 3 | 0 | FS702 |  | Hotel | 6
5 | Sheet 61940 | 32 | Level 18 | WIR - 02249 | Fire Pump Room | fire fighting pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
6 | Sheet 61940 | 33 | Level 18 | WIR - 02249 | Fire Pump Room | CHW pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Hotel | 4
7 | Sheet 61940 | 33 | Level 18 | WIR - 02249 | Fire Pump Room | opening |  |  |  | 0.4 | 0.8 | 0.32 | 0.28468 | 2 | 245 | 1 | 490 | FS702/FB750 |  | Hotel | 2
8 | Sheet 61940 | 34 | Level 18 | WIR - 02249 | High Level | PVC pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 2 | 0 | FS702/FP302/FB750 |  | Hotel | 4
9 | Sheet 61940 | 34 | Level 18 | WIR - 02249 | High Level | opening |  |  |  | 0.48 | 2.7 | 1.296 | 1.2607 | 2 | 450 | 1 | 1134.6075 | FS702/FB750 |  | Hotel | 2.5213
10 | Sheet 61940 | 35 | Level 18 | WIR - 02249 | Wall | duct | 0.2 | 0.4 | 0.08 |  |  |  |  | 2 |  | 3 | 0 | FS709/FB750 |  | Hotel | 6
11 | Sheet 61940 | 35 | Level 18 | WIR - 02249 | Wall | opening |  |  |  | 0.4 | 1.7 | 0.68 | 0.44 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Hotel | 2
12 | Sheet 61940 | 36 | Level 18 | WIR - 02249 | Wall | fire fighting pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
13 | Sheet 61940 | 37 | Level 18 | WIR - 02249 | Wall | CHW pipe | 6" |  |  | 8" |  |  |  | 2 |  | 2 | 0 | FS709 |  | Hotel | 4
14 | Sheet 61940 | 38 | Level 18 | WIR - 02249 | Wall | PVC pipe | 6" |  |  | 8" |  |  |  | 2 |  | 2 | 0 | FS702/FP302 |  | Hotel | 4
15 | Sheet 61940 | 39 | Level 18 | WIR - 02249 | Wall | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 2 | 0 | FS709 |  | Hotel | 4
16 | Sheet 61940 | 40 | Level 18 | WIR - 02249 | Wall | PVC pipe | 6" |  | 0.017662 |  |  |  |  | 1 |  | 4 | 0 | FS702/FP302/FB750 |  | Hotel | 4
17 | Sheet 61940 | 41 | Level 18 | WIR - 02249 | Wall | PVC pipe | 4" |  | 0.00785 |  |  |  |  | 1 |  | 1 | 0 | FS702/FP302/FB750 |  | Hotel | 1
18 | Sheet 61940 | 42 | Level 18 | WIR - 02249 | Wall | CHW pipe | 6" |  | 0.017662 |  |  |  |  | 1 |  | 2 | 0 | FS709/FB750 |  | Hotel | 2
19 | Sheet 61940 | 43 | Level 18 | WIR - 02249 | Wall | metal pipe | 6" |  | 0.017662 |  |  |  |  | 1 |  | 2 | 0 | FS702/FB750 |  | Hotel | 2
20 | Sheet 61940 | 44 | Level 18 | WIR - 02249 | Wall | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 2 | 0 | FS702/FB750 |  | Hotel | 2
21 | Sheet 61940 | 44 | Level 18 | WIR - 02249 | Wall | opening |  |  |  | 0.76 | 1.9 | 1.444 | 1.2649 | 1 | 450 | 1 | 569.1825 | FS702/FB750 |  | Hotel | 1.2649
22 | Sheet 61940 | 45 | Level 18 | WIR - 02249 | Wall | duct | 1.05 | 1.6 | 1.68 |  |  |  |  | 1 |  | 1 | 0 | FS709/FB750 |  | Hotel | 1.68
23 | Sheet 61940 | 46 | Level 18 | WIR - 02249 | Wall | CHW pipe | 6" |  | 0.017662 |  |  |  |  | 1 |  | 2 | 0 | FS709/FB750 |  | Hotel | 2
24 | Sheet 61940 | 46 | Level 18 | WIR - 02249 | Wall | opening |  |  |  | 1.6 | 1.75 | 2.8 | 1.0847 | 1 | 450 | 1 | 488.1038 | FS702/FB750 |  | Hotel | 1.0847
25 | Sheet 61940 | 47 | Level 18 | WIR - 02249 | Corridor | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
26 | Sheet 61940 | 48 | Level 18 | WIR - 02249 | Corridor | cable trunking | 0.15 | 0.15 | 0.0225 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750 |  | Hotel | 4
27 | Sheet 61940 | 49 | Level 18 | WIR - 02249 | Corridor | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
28 | Sheet 61940 | 49 | Level 18 | WIR - 02249 | Corridor | opening |  |  |  | 0.4 | 0.4 | 0.16 | 0.09 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
29 | Sheet 61940 | 50 | Level 18 | WIR - 02249 | Corridor | fire fighting pipe | 6" |  |  | 8" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
30 | Sheet 61940 | 51 | Level 18 | WIR - 02249 | Corridor | fire fighting pipe | 3" |  |  | 5" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
31 | Sheet 61940 | 52 | Level 18 | WIR - 02249 | Corridor | fire fighting pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
32 | Sheet 61940 | 53 | Level 18 | WIR - 02249 | Corridor | PPR pipe | 1" |  |  | 2" |  |  |  | 1 |  | 1 | 0 | FS702/FP302 |  | Hotel | 1
33 | Sheet 61940 | 54 | Level 18 | WIR - 02249 | Corridor | CHW pipe | 6" |  |  | 8" |  |  |  | 1 |  | 2 | 0 | FS709 |  | Hotel | 2
Hotel
January 2023 - Hotel | [19 empty] | Hotel
1 | Sheet 61941 | 55 | Level 18 | WIR - 02249 | Corridor | CHW pipe | 3" |  |  | 5" |  |  |  | 1 |  | 2 | 0 | FS709 | Sheet 61941 | Hotel | 2
2 | Sheet 61941 | 56 | Level 18 | WIR - 02249 | Corridor | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 2 | 0 | FS702/FB750 |  | Hotel | 2
3 | Sheet 61941 | 56 | Level 18 | WIR - 02249 | Corridor | opening |  |  |  | 0.4 | 0.5 | 0.2 | 0.17 | 1 | 180 | 1 | 180 | FS702/FB750 |  | Hotel | 1
4 | Sheet 61941 | 57 | Level 18 | WIR - 02249 | Corridor | fire fighting pipe | 2" |  |  | 4" |  |  |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
5 | Sheet 61941 | 58 | Level 18 | WIR - 02249 | Corridor | blank opening |  |  |  | 0.22 | 2.7 | 0.594 | 0.594 | 2 | 340 | 2 | 1360 | FS702/FB750 |  | Hotel | 4
6 | Sheet 61941 | 59 | Level 18 | WIR - 02249 | Corridor | CHW pipe | 2" |  |  | 4" |  |  |  | 1 |  | 2 | 0 | FS709 |  | Hotel | 2
7 | Sheet 61941 | 60 | Level 18 | WIR - 02249 | Corridor | CDP pipe | 2" |  |  | 4" |  |  |  | 1 |  | 1 | 0 | FS702/FP302 |  | Hotel | 1
8 | Sheet 61941 | 61 | Level 18 | WIR - 02249 | Corridor | CHW pipe | 6" |  |  | 8" |  |  |  | 1 |  | 2 | 0 | FS709 |  | Hotel | 2
9 | Sheet 61941 | 62 | Level 18 | WIR - 02249 | Corridor | fire fighting pipe | 2" |  |  | 4" |  |  |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
10 | Sheet 61941 | 63 | Level 18 | WIR - 02249 | Corridor | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 1 |  | 5 | 0 | FS709 |  | Hotel | 5
11 | Sheet 61941 | 64 | Level 18 | WIR - 02249 | Corridor | PPR pipe | 2" |  |  | 4" |  |  |  | 1 |  | 1 | 0 | FS702/FP302 |  | Hotel | 1
12 | Sheet 61941 | 65 | Level 18 | WIR - 02249 | Housekeeping | CHW pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Hotel | 4
13 | Sheet 61941 | 65 | Level 18 | WIR - 02249 | Housekeeping | opening |  |  |  | 0.3 | 0.3 | 0.09 | 0.086075 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
14 | Sheet 61941 | 66 | Level 18 | WIR - 02249 | Housekeeping | fire fighting pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
15 | Sheet 61941 | 66 | Level 18 | WIR - 02249 | Housekeeping | opening |  |  |  | 6" |  | 0.017662 | 0.0157 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
16 | Sheet 61941 | 67 | Level 18 | WIR - 02249 | Housekeeping | fire fighting pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
17 | Sheet 61941 | 68 | Level 18 | WIR - 02249 | Housekeeping | CDP pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 | FS702/FP302/FB750 |  | Hotel | 2
18 | Sheet 61941 | 69 | Level 18 | WIR - 02249 | Housekeeping | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750 |  | Hotel | 4
19 | Sheet 61941 | 70 | Level 18 | WIR - 02249 | Housekeeping | cable tray | 0.05 | 0.2 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
20 | Sheet 61941 | 71 | Level 18 | WIR - 02249 | Housekeeping | cable trunking | 0.15 | 0.15 | 0.0225 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750 |  | Hotel | 4
21 | Sheet 61941 | 72 | Level 18 | WIR - 02249 | Housekeeping | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
22 | Sheet 61941 | 72 | Level 18 | WIR - 02249 | Housekeeping | opening |  |  |  | 0.6 | 0.9 | 0.54 | 0.44255 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Hotel | 2
23 | Sheet 61941 | 73 | Level 18 | WIR - 02249 | Housekeeping | PPR pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
24 | Sheet 61941 | 74 | Level 18 | WIR - 02249 | Housekeeping | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 |  | 1 |  | 5 | 0 | FS709 |  | Hotel | 5
25 | Sheet 61941 | 75 | Level 18 | WIR - 02249 | Housekeeping | cable tray | 0.05 | 0.2 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
26 | Sheet 61941 | 76 | Level 18 | WIR - 02249 | Housekeeping | cable trunking | 0.15 | 0.15 | 0.0225 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750 |  | Hotel | 4
27 | Sheet 61941 | 76 | Level 18 | WIR - 02249 | Housekeeping | opening |  |  |  | 0.5 | 0.5 | 0.25 | 0.195 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2
28 | Sheet 61941 | 77 | Level 18 | WIR - 02249 | Housekeeping | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750 |  | Hotel | 4
29 | Sheet 61941 | 78 | Level 18 | WIR - 02249 | Housekeeping | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750 |  | Hotel | 4
30 | Sheet 61941 | 78 | Level 18 | WIR - 02249 | Housekeeping | opening |  |  |  | 0.3 | 0.6 | 0.18 | 0.13 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
31 | Sheet 61941 | 79 | Level 18 | WIR - 02249 | Housekeeping | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 6 | 0 | FS709 |  | Hotel | 12
32 | Sheet 61941 | 80 | Level 18 | WIR - 02249 | Shaft | PVC pipe | 4" |  |  | 6" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
33 | Sheet 61941 | 81 | Level 18 | WIR - 02249 | Shaft | PVC pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
34 | Sheet 61941 | 82 | Level 18 | WIR - 02249 | Shaft | CDP pipe | 2" |  |  | 4" |  |  |  | 2 |  | 2 | 0 | FS702/FP302 |  | Hotel | 4
Hotel
January 2023 - Hotel | [19 empty] | Hotel
1 | Sheet 61942 | 83 | Level 18 | WIR - 02249 | Stair 08 | duct | 0.4 | 0.4 | 0.16 | 0.45 | 0.45 | 0.2025 |  | 1 |  | 2 | 0 | FS709 | Sheet 61942 | Hotel | 2
2 | Sheet 61942 | 84 | Level 18 | WIR - 02249 | Stair 08 | fire fighting pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
3 | Sheet 61942 | 84 | Level 18 | WIR - 02249 | Stair 08 | opening |  |  |  | 0.3 | 0.3 | 0.09 | 0.072337 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
4 | Sheet 61942 | 85 | Level 18 | WIR - 02249 | Lift lobby | CDP pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
5 | Sheet 61942 | 86 | Level 18 | WIR - 02249 | Lift lobby | CHW pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Hotel | 4
6 | Sheet 61942 | 87 | Level 18 | WIR - 02249 | Lift lobby | fire fighting pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
7 | Sheet 61942 | 88 | Level 18 | WIR - 02249 | Lift lobby | conduit pipe | 0.5" |  | 0.00013266 |  |  |  |  | 2 |  | 8 | 0 | FS709/FB750 |  | Hotel | 16
8 | Sheet 61942 | 88 | Level 18 | WIR - 02249 | Lift lobby | opening |  |  |  | 0.25 | 0.8 | 0.2 | 0.19452 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2
9 | Sheet 61942 | 89 | Level 18 | WIR - 02249 | Water M. Room | PPR pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 2 | 0 | FS702/FP302/FB750 |  | Hotel | 4
10 | Sheet 61942 | 90 | Level 18 | WIR - 02249 | Water M. Room | PPR pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 | FS702/FP302/FB750 |  | Hotel | 2
11 | Sheet 61942 | 90 | Level 18 | WIR - 02249 | Water M. Room | opening |  |  |  | 0.3 | 0.6 | 0.18 | 0.16921 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2
12 | Sheet 61942 | 91 | Level 18 | WIR - 02249 | Water M. Room | PVC pipe | 4" |  |  | 6" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
13 | Sheet 61942 | 92 | Level 18 | WIR - 02249 | Water M. Room | fire fighting pipe | 1" |  |  | 2" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
14 | Sheet 61942 | 93 | Level 18 | WIR - 02249 | SU Lobby | CHW pipe | 8" |  | 0.032349 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Hotel | 4
15 | Sheet 61942 | 94 | Level 18 | WIR - 02249 | SU Lobby | PPR pipe | 8" |  | 0.032349 |  |  |  |  | 2 |  | 1 | 0 | FS702/FP302/FB750 |  | Hotel | 2
16 | Sheet 61942 | 95 | Level 18 | WIR - 02249 | SU Lobby | metal pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750 |  | Hotel | 4
17 | Sheet 61942 | 96 | Level 18 | WIR - 02249 | SU Lobby | PVC pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 5 | 0 | FS702/FP302/FB750 |  | Hotel | 10
18 | Sheet 61942 | 97 | Level 18 | WIR - 02249 | SU Lobby | fire fighting pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 3 | 0 | FS702/FB750 |  | Hotel | 6
19 | Sheet 61942 | 98 | Level 18 | WIR - 02249 | SU Lobby | fire fighting pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
20 | Sheet 61942 | 99 | Level 18 | WIR - 02249 | SU Lobby | fire fighting pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
21 | Sheet 61942 | 100 | Level 18 | WIR - 02249 | SU Lobby | fire fighting pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
22 | Sheet 61942 | 101 | Level 18 | WIR - 02249 | SU Lobby | conduit pipe | 0.5" |  | 0.00013266 |  |  |  |  | 2 |  | 11 | 0 | FS709/FB750 |  | Hotel | 22
23 | Sheet 61942 | 101 | Level 18 | WIR - 02249 | SU Lobby | opening |  |  |  | 1.3 | 2.1 | 2.73 | 2.448 | 2 | 450 | 1 | 2203.1998 | FS702/FB750 |  | Hotel | 4.896
24 | Sheet 61942 | 102 | Level 18 | WIR - 02249 | FF Lobby | fire fighting pipe | 1" |  |  | 2" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
25 | Sheet 61942 | 103 | Level 18 | WIR - 02249 | FF Lobby | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 3 | 0 | FS709 |  | Hotel | 6
Hotel
January 2023 - Hotel | [19 empty] | Hotel
1 | Sheet 62289 | 1 | Level 01 | WIR - 02088 | Lift lobby | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 |  | 2 |  | 1 | 0 | FS709 | Sheet 62289 | Hotel | 2
2 | Sheet 62289 | 2 | Level 01 | WIR - 02088 | Lift lobby | metal pipe | 2" |  |  | 4" |  |  |  | 2 |  | 4 | 0 | FS702 |  | Hotel | 8
3 | Sheet 62289 | 3 | Level 01 | WIR - 02088 | Lift lobby | fire fighting pipe | 1" |  |  | 2" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
4 | Sheet 62289 | 4 | Level 01 | WIR - 02088 | Lift lobby | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 11 | 0 | FS709 |  | Hotel | 22
5 | Sheet 62289 | 5 | Level 01 | WIR - 02088 | Lift lobby | duct | 0.2 | 0.2 | 0.04 |  |  |  |  | 2 |  | 1 | 0 | FS709/FB750 |  | Hotel | 2
6 | Sheet 62289 | 5 | Level 01 | WIR - 02088 | Lift lobby | opening |  |  |  | 0.28 | 0.5 | 0.14 | 0.1 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
7 | Sheet 62289 | 6 | Level 01 | WIR - 02088 | Lift lobby | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 |  | 1 |  | 1 | 0 | FS709 |  | Hotel | 1
8 | Sheet 62289 | 7 | Level 01 | WIR - 02088 | Lift lobby | duct | 0.3 | 0.3 | 0.09 | 0.35 | 0.35 | 0.1225 |  | 1 |  | 1 | 0 | FS709 |  | Hotel | 1
9 | Sheet 62289 | 8 | Level 01 | WIR - 02088 | Pump room | cable tray |  |  |  | 0.1 | 0.16 | 0.016 |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
10 | Sheet 62289 | 9 | Level 01 | WIR - 02088 | Pump room | cable tray |  |  |  | 0.1 | 0.26 | 0.026 |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
11 | Sheet 62289 | 10 | Level 01 | WIR - 02088 | Pump room | cable trunking |  |  |  | 0.16 | 0.16 | 0.0256 |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
12 | Sheet 62289 | 11 | Level 01 | WIR - 02088 | Pump room | PVC pipe | 2" |  |  | 4" |  |  |  | 2 |  | 3 | 0 | FS702/FP302 |  | Hotel | 6
13 | Sheet 62289 | 12 | Level 01 | WIR - 02088 | Pump room | CHW pipe | 3" |  |  | 5" |  |  |  | 2 |  | 2 | 0 | FS709 |  | Hotel | 4
14 | Sheet 62289 | 13 | Level 01 | WIR - 02088 | Pump room | PVC pipe | 4" |  |  | 6" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
15 | Sheet 62289 | 14 | Level 01 | WIR - 02088 | Pump room | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 15 | 0 | FS709 |  | Hotel | 30
16 | Sheet 62289 | 15 | Level 01 | WIR - 02088 | Pump room | CDP pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
17 | Sheet 62289 | 16 | Level 01 | WIR - 02088 | Pump room | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 3 | 0 | FS709 |  | Hotel | 6
18 | Sheet 62289 | 17 | Level 01 | WIR - 02088 | Pump room | PVC pipe | 4" |  |  | 6" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
19 | Sheet 62289 | 18 | Level 01 | WIR - 02088 | Pump room | duct | 0.2 | 0.2 | 0.04 | 0.26 | 0.26 | 0.0676 |  | 2 |  | 1 | 0 | FS709 |  | Hotel | 2
20 | Sheet 62289 | 19 | Level 01 | WIR - 02088 | Pump room | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 5 | 0 | FS709 |  | Hotel | 10
21 | Sheet 62289 | 20 | Level 01 | WIR - 02088 | Pump room | fire fighting pipe | 1" |  |  | 2" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
22 | Sheet 62289 | 21 | Level 01 | WIR - 02088 | Pump room | duct | 0.4 | 0.5 | 0.2 | 0.45 | 0.55 | 0.2475 |  | 2 |  | 2 | 0 | FS709 |  | Hotel | 4
23 | Sheet 62289 | 22 | Level 01 | WIR - 02088 | Pump room | fire fighting pipe | 1" |  |  | 2" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
24 | Sheet 62289 | 23 | Level 01 | WIR - 02088 | Pump room | PVC pipe | 4" |  |  | 6" |  |  |  | 2 |  | 4 | 0 | FS702/FP302 |  | Hotel | 8
25 | Sheet 62289 | 24 | Level 01 | WIR - 02088 | Pump room | PVC pipe | 2" |  |  | 4" |  |  |  | 2 |  | 2 | 0 | FS702/FP302 |  | Hotel | 4
26 | Sheet 62289 | 25 | Level 01 | WIR - 02088 | Pump room | cable trunking |  |  |  | 0.1 | 0.1 | 0.01 |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
27 | Sheet 62289 | 26 | Level 01 | WIR - 02088 | Pump room | cable trunking |  |  |  | 0.2 | 0.25 | 0.05 |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
Hotel
January 2023 - Hotel | [19 empty] | Hotel
1 | Sheet 62290 | 27 | Level 01 | WIR - 02088 | MEP Work | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 13 | 0 | FS709 | Sheet 62290 | Hotel | 26
2 | Sheet 62290 | 28 | Level 01 | WIR - 02088 | MEP Work | duct | 0.2 | 0.2 | 0.04 | 0.26 | 0.26 | 0.0676 |  | 2 |  | 2 | 0 | FS709 |  | Hotel | 4
3 | Sheet 62290 | 29 | Level 01 | WIR - 02088 | MEP Work | cable tray | 0.05 | 0.2 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
4 | Sheet 62290 | 30 | Level 01 | WIR - 02088 | MEP Work | cable trunking | 0.15 | 0.15 | 0.0225 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
5 | Sheet 62290 | 31 | Level 01 | WIR - 02088 | MEP Work | cable trunking | 0.052 | 0.05 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
6 | Sheet 62290 | 31 | Level 01 | WIR - 02088 | MEP Work | opening |  |  |  | 0.23 | 0.5 | 0.115 | 0.0725 | 1 | 95 | 1 | 95 | FS702/FB750 |  | Hotel | 1
7 | Sheet 62290 | 32 | Level 01 | WIR - 02088 | MEP Work | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 1 |  | 3 | 0 | FS709 |  | Hotel | 3
[15 empty] | Grand Total |  | 32118.5278 |  |  |  | 1671.609
WIR List as per SOS
[5 empty] | Ground Level | WIR - 02185
[5 empty] | Level 18 | WIR - 02249
[5 empty] | Level 01 | WIR - 02088

## Outside Sleeve (Civil)
Project: |  |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  |  | Khansaheb Civil Engineering - Construction Division
Period of Completed Works: |  |  |  | January 2023 | [14 empty] | all mortar openings priced by sqm diff
Summary of Completed Firestopping Works
No. | Sos Number | Serial No | Level | WIR No. | Location | Penetrant Type | Penetrant Size (in meter) |  | SquareMeters | Opening Size (in meter) |  | SquareMeters | Diffirence | Sides | Rate (AED) | Nos | Total (AED) |  |  | Hotel / Residence | QTY
Hotel
January 2023 - Hotel - Outer Sleeve | [19 empty] | Hotel
1 | Sheet 61937 | 1 | Ground Level | WIR - 0194 | Male Toilet | fire fighting pipe | 2" |  |  | 4" |  |  |  | 2 | 14 | 2 | 56 | FS702 | Sheet 61937 | Hotel | 4
2 | Sheet 61937 | 2 | Ground Level | WIR - 0194 | Male Toilet | duct | 0.25 | 0.3 | 0.075 | 0.32 | 0.36 | 0.1152 |  | 2 | 51 | 2 | 204 | FS702 |  | Hotel | 4
3 | Sheet 61937 | 3 | Ground Level | WIR - 0194 | Male Toilet | duct | 0.3 | 0.35 | 0.105 | 0.36 | 0.41 | 0.1476 |  | 2 | 51 | 2 | 204 | FS702 |  | Hotel | 4
4 | Sheet 61937 | 4 | Ground Level | WIR - 0194 | Male Toilet | PVC pipe | 3" |  |  | 5" |  |  |  | 2 | 30 | 1 | 60 | FS702 |  | Hotel | 2
5 | Sheet 61937 | 5 | Ground Level | WIR - 0194 | Male Toilet | fire fighting pipe | 3" |  |  | 5" |  |  |  | 2 | 16 | 1 | 32 | FS702 |  | Hotel | 2
6 | Sheet 61937 | 6 | Ground Level | WIR - 0194 | Male Toilet | CHW pipe | 4" |  |  | 6" |  |  |  | 2 | 29 | 2 | 116 | FS702 |  | Hotel | 4
7 | Sheet 61937 | 7 | Ground Level | WIR - 0194 | Male Toilet | CDP pipe | 3" |  |  | 5" |  |  |  | 2 | 30 | 1 | 60 | FS702 |  | Hotel | 2
8 | Sheet 61937 | 8 | Ground Level | WIR - 0194 | Male Toilet | PVC pipe | 4" |  |  | 6" |  |  |  | 2 | 65 | 1 | 130 | FS702 |  | Hotel | 2
9 | Sheet 61937 | 9 | Ground Level | WIR - 0194 | Male Toilet | PPR pipe | 4" |  |  | 6" |  |  |  | 2 | 65 | 3 | 390 | FS702 |  | Hotel | 6
10 | Sheet 61937 | 10 | Ground Level | WIR - 0194 | Male Toilet | fire fighting pipe | 3" |  |  | 5" |  |  |  | 2 | 16 | 1 | 32 | FS702 |  | Hotel | 2
11 | Sheet 61937 | 11 | Ground Level | WIR - 0194 | Male Toilet | CDP pipe | 4" |  |  | 6" |  |  |  | 2 | 65 | 1 | 130 | FS702 |  | Hotel | 2
12 | Sheet 61937 | 12 | Ground Level | WIR - 0194 | Male Toilet | CHW pipe | 4" |  |  | 6" |  |  |  | 2 | 29 | 1 | 58 | FS702 |  | Hotel | 2
13 | Sheet 61937 | 13 | Ground Level | WIR - 0194 | Male Toilet | PPR pipe | 3" |  |  | 5" |  |  |  | 2 | 30 | 3 | 180 | FS702 |  | Hotel | 6
14 | Sheet 61937 | 14 | Ground Level | WIR - 0194 | Male Toilet | PVC pipe | 8" |  |  | 10" |  |  |  | 2 | 250 | 1 | 500 | FS702 |  | Hotel | 2
15 | Sheet 61937 | 15 | Ground Level | WIR - 0194 | Male Toilet | PVC pipe | 8" |  |  | 10" |  |  |  | 2 | 250 | 2 | 1000 | FS702 |  | Hotel | 4
16 | Sheet 61937 | 16 | Ground Level | WIR - 0194 | Male Toilet | fire fighting pipe | 8" |  |  | 10" |  |  |  | 2 | 46 | 1 | 92 | FS702 |  | Hotel | 2
17 | Sheet 61937 | 17 | Ground Level | WIR - 0194 | Male Toilet | CHW pipe | 12" |  |  | 14" |  |  |  | 2 | 170 | 2 | 680 | FS702 |  | Hotel | 4
18 | Sheet 61937 | 18 | Ground Level | WIR - 0194 | Male Toilet | PVC pipe | 8" |  |  | 10" |  |  |  | 2 | 250 | 5 | 2500 | FS702 |  | Hotel | 10
19 | Sheet 61937 | 19 | Ground Level | WIR - 0194 | Male Toilet | PVC pipe | 8" |  |  | 10" |  |  |  | 2 | 250 | 1 | 500 | FS702 |  | Hotel | 2
20 | Sheet 61937 | 20 | Ground Level | WIR - 0194 | Ball Room | fire fighting pipe | 2" |  |  | 4" |  |  |  | 2 | 14 | 1 | 28 | FS702 |  | Hotel | 2
21 | Sheet 61937 | 21 | Ground Level | WIR - 0194 | Ball Room | fire fighting pipe | 2" |  |  | 4" |  |  |  | 2 | 14 | 3 | 84 | FS702 |  | Hotel | 6
22 | Sheet 61937 | 22 | Ground Level | WIR - 0194 | Ball Room | fire fighting pipe | 4" |  |  | 6" |  |  |  | 2 | 21 | 1 | 42 | FS702 |  | Hotel | 2
23 | Sheet 61937 | 23 | Ground Level | WIR - 0194 | Ball Room | PVC pipe | 8" |  |  | 10" |  |  |  | 2 | 250 | 1 | 500 | FS702 |  | Hotel | 2
24 | Sheet 61937 | 24 | Ground Level | WIR - 0194 | Ball Room | fire fighting pipe | 3" |  |  | 5" |  |  |  | 2 | 16 | 1 | 32 | FS702 |  | Hotel | 2
25 | Sheet 61937 | 25 | Ground Level | WIR - 0194 | Ball Room | PVC pipe | 6" |  |  | 8" |  |  |  | 2 | 125 | 1 | 250 | FS702 |  | Hotel | 2
Hotel
January 2023 - Hotel - Outer Sleeve | [19 empty] | Hotel
1 | Sheet 61938 | 26 | Ground Level | WIR - 0194 | Ball Room | PVC pipe | 8" |  |  | 10" |  |  |  | 2 | 250 | 2 | 1000 | FS702 | Sheet 61938 | Hotel | 4
2 | Sheet 61938 | 27 | Ground Level | WIR - 0194 | Ball Room | PVC pipe | 6" |  |  | 8" |  |  |  | 2 | 125 | 1 | 250 | FS702 |  | Hotel | 2
3 | Sheet 61938 | 28 | Ground Level | WIR - 0194 | Ball Room | fire fighting pipe | 2" |  |  | 4" |  |  |  | 2 | 14 | 2 | 56 | FS702 |  | Hotel | 4
4 | Sheet 61938 | 29 | Ground Level | WIR - 0194 | Ball Room | PVC pipe | 6" |  |  | 8" |  |  |  | 2 | 125 | 4 | 1000 | FS702 |  | Hotel | 8
5 | Sheet 61938 | 30 | Ground Level | WIR - 0194 | Ball Room | fire fighting pipe | 4" |  |  | 6" |  |  |  | 2 | 21 | 1 | 42 | FS702 |  | Hotel | 2
6 | Sheet 61938 | 31 | Ground Level | WIR - 0194 | Ball Room | PVC pipe | 2" |  |  | 4" |  |  |  | 2 | 28 | 4 | 224 | FS702 |  | Hotel | 8
7 | Sheet 61938 | 32 | Ground Level | WIR - 0194 | Ball Room | PVC pipe | 6" |  |  | 8" |  |  |  | 2 | 125 | 1 | 250 | FS702 |  | Hotel | 2
8 | Sheet 61938 | 33 | Ground Level | WIR - 0194 | Ball Room | PVC pipe | 8" |  |  | 10" |  |  |  | 2 | 250 | 1 | 500 | FS702 |  | Hotel | 2
9 | Sheet 61938 | 34 | Ground Level | WIR - 0194 | Ball Room | PVC pipe | 6" |  |  | 8" |  |  |  | 2 | 125 | 1 | 250 | FS702 |  | Hotel | 2
10 | Sheet 61938 | 35 | Ground Level | WIR - 0194 | Ball Room | PVC pipe | 6" |  |  | 8" |  |  |  | 2 | 125 | 1 | 250 | FS702 |  | Hotel | 2
11 | Sheet 61938 | 36 | Ground Level | WIR - 0194 | Ball Room | fire fighting pipe | 3" |  |  | 5" |  |  |  | 2 | 16 | 1 | 32 | FS702 |  | Hotel | 2
12 | Sheet 61938 | 37 | Ground Level | WIR - 0194 | Ball Room | duct | 10" |  |  | 12" |  |  |  | 2 | 32 | 6 | 384 | FS702 |  | Hotel | 12
13 | Sheet 61938 | 38 | Ground Level | WIR - 0194 | Ball Room | fire fighting pipe | 6" |  |  | 8" |  |  |  | 2 | 27 | 2 | 108 | FS702 |  | Hotel | 4
14 | Sheet 61938 | 39 | Ground Level | WIR - 0194 | Ball Room | fire fighting pipe | 4" |  |  | 6" |  |  |  | 2 | 21 | 2 | 84 | FS702 |  | Hotel | 4
15 | Sheet 61938 | 40 | Ground Level | WIR - 0194 | Ball Room | fire fighting pipe | 2" |  |  | 4" |  |  |  | 2 | 14 | 1 | 28 | FS702 |  | Hotel | 2
16 | Sheet 61938 | 41 | Ground Level | WIR - 0194 | Ball Room | PVC pipe | 8" |  |  | 10" |  |  |  | 2 | 250 | 4 | 2000 | FS702 |  | Hotel | 8
Residence
January 2023 - Residence | [19 empty] | Residence
1 | Sheet 62288 | 26 | Ground Level | WIR - 0194 | Staircase 04 | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 3 | 0 | FS702 | Sheet 62288 | Residence | 3
2 | Sheet 62288 | 27 | Ground Level | WIR - 0194 | Staircase 04 | cable tray | 0.05 | 0.2 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FS702 |  | Residence | 1
3 | Sheet 62288 | 28 | Ground Level | WIR - 0194 | Staircase 04 | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 3 | 0 | FS702 |  | Residence | 3
4 | Sheet 62288 | 29 | Ground Level | WIR - 0194 | Staircase 04 | opening |  |  |  | 0.45 | 1.3 | 0.585 | 0.5 | 1 | 310 | 1 | 310 | FS702 |  | Residence | 1
5 | Sheet 62288 | 30 | Ground Level | WIR - 0194 | Staircase 04 | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 3 | 0 | FS702 |  | Residence | 3
6 | Sheet 62288 | 31 | Ground Level | WIR - 0194 | Staircase 04 | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 3 | 0 | FS702 |  | Residence | 3
7 | Sheet 62288 | 32 | Ground Level | WIR - 0194 | Staircase 04 | cable tray | 0.052 | 0.2 | 0.0104 |  |  |  |  | 1 |  | 1 | 0 | FS702 |  | Residence | 1
8 | Sheet 62288 | 33 | Ground Level | WIR - 0194 | Staircase 04 | opening |  |  |  | 0.34 | 1.38 | 0.4692 | 0.3838 | 1 | 310 | 1 | 310 | FS702 |  | Residence | 1
9 | Sheet 62288 | 34 | Ground Level | WIR - 0194 | Staircase 04 | blank opening |  |  |  | 0.97 | 1.3 | 1.261 | 1.261 | 2 | 450 | 1 | 1134.9 | FS702 |  | Residence | 2
10 | Sheet 62288 | 35 | Ground Level | WIR - 0194 | Staircase 04 | conduit pipe | 0.5" |  | 0.00013266 |  |  |  |  | 1 | 18 | 15 | 270 | FS702 |  | Residence | 15
11 | Sheet 62288 | 36 | Ground Level | WIR - 0194 | Staircase 04 | CDP pipe | 3" |  | 0.0044156 |  |  |  |  | 1 | 30 | 1 | 30 | FS702 |  | Residence | 1
12 | Sheet 62288 | 37 | Ground Level | WIR - 0194 | Staircase 04 | opening |  |  |  | 0.18 | 3.2 | 0.576 | 0.56959 | 1 | 340 | 1 | 340 | FS702 |  | Residence | 1
[15 empty] | Grand Total |  | 16712.9 |  |  |  | 185
WIR List as per SOS
[5 empty] | Ground Level | WIR - 0194