## Contract
FIRE STOP WORKS ON MEP PENETRATIONS AND JOINTS | [11 empty] | FIRE STOP
[6 empty] | Quantity |  |  | Progress Amount (AED) |  |  |  |  | Certified
S.Nr | Description | Qty | Unit | Rate | Amount | Previous | Current | Cumulative | Previous | Current | Cumulative | WIR Ref./ Remarks |  | Previous | Current | Cumulative
G | Supply and installation of firestop sealant and mineral wool to Head of wall / Wall to wall joints (Single Sided)
G1 | Upto 20mm joint width | 500 | m | 14 | 7000 | 2233.65 | 106 | 2339.65 | 31271.1 | 1484 | 32755.1 |  | 0 | 31271.1 | 1484 | 32755.1
G2 | Upto 30mm joint width | 500 | m | 20 | 10000 | 39 |  | 39 | 780 | 0 | 780 |  | 0 | 780 | 0 | 780
G3 | Upto 35mm joint width | 150 | m | 27 | 4050 |  |  |  | 0 | 0 | 0 |  | 0
H | Supply and installation of Sealant and mineral wool non-fire rated Head of wall / Wall to wall joints (Single Sided)
H1 | Upto 20mm joint width | 250 | m | 10 | 2500 |  |  |  | 0 | 0 | 0 |  | 0
A | Supply and apply firestop sealant and mineral wool backing to non-insulated metallic/ non-combustible pipes (Single Sided)
A1 | Upto and including 2"ɸ | 100 | No. | 14 | 1400 |  | 8 | 8 | 0 | 112 | 112 |  | 0 | 0 | 112 | 112
A2 | Upto and including 3"ɸ | 100 | No. | 16 | 1600 |  | 19 | 19 | 0 | 304 | 304 |  | 0 | 0 | 304 | 304
A3 | Upto and including 4"ɸ | 100 | No. | 21 | 2100 |  |  |  | 0 | 0 | 0 |  | 0
A4 | Upto and including 6"ɸ | 100 | No. | 27 | 2700 |  |  |  | 0 | 0 | 0 |  | 0
A5 | Upto and including 8"ɸ | 50 | No. | 46 | 2300 |  |  |  | 0 | 0 | 0 |  | 0
A6 | Upto and including 24"ɸ | 10 | No. | 141 | 1410 |  |  |  | 0 | 0 | 0 |  | 0
B | Supply and apply firestop sealant and mineral wool backing to insulated metallic/ non-combustible pipes (Single Sided)
B1 | Upto and including 2"ɸ | 200 | No. | 20 | 4000 |  |  |  | 0 | 0 | 0 |  | 0
B2 | Upto and including 3"ɸ | 200 | No. | 23 | 4600 |  | 37 | 37 | 0 | 851 | 851 |  | 0 | 0 | 851 | 851
B3 | Upto and including 4"ɸ | 200 | No. | 29 | 5800 |  |  |  | 0 | 0 | 0 |  | 0
B4 | Upto and including 6"ɸ | 200 | No. | 35 | 7000 |  |  |  | 0 | 0 | 0 |  | 0
B5 | Upto and including 8"ɸ | 100 | No. | 47 | 4700 |  |  |  | 0 | 0 | 0 |  | 0
B6 | Upto and including 16"ɸ | 50 | No. | 170 | 8500 |  |  |  | 0 | 0 | 0 |  | 0
C | Supply and apply firestop sealant and mineral wool backing to PVC/ combustible pipes (Single Sided)
C1 | Upto and including 2"ɸ | 400 | No. | 28 | 11200 |  |  |  | 0 | 0 | 0 |  | 0
C2 | Upto and including 3"ɸ | 400 | No. | 30 | 12000 |  | 65 | 65 | 0 | 1950 | 1950 |  | 0 | 0 | 1950 | 1950
C3 | Upto and including 4"ɸ | 400 | No. | 65 | 26000 |  | 1 | 1 | 0 | 65 | 65 |  | 0 | 0 | 65 | 65
C4 | Upto and including 6"ɸ | 250 | No. | 125 | 31250 |  | 17 | 17 | 0 | 2125 | 2125 |  | 0 | 0 | 2125 | 2125
C5 | Upto and including 8"ɸ | 250 | No. | 250 | 62500 |  | 3 | 3 | 0 | 750 | 750 |  | 0 | 0 | 750 | 750
D | Supply and apply firestop board material to cable tray openings, shaft openings and openings (Single Board)
D1 | For an area upto 0.05 m2 | 100 | No. | 50 | 5000 | 20 | 12 | 32 | 1000 | 600 | 1600 |  | 0 | 1000 | 600 | 1600
D2 | For an area upto 0.10 m2 | 100 | No. | 95 | 9500 | 10 | 60 | 70 | 950 | 5700 | 6650 |  | 0 | 950 | 5700 | 6650
D3 | For an area upto 0.15 m2 | 100 | No. | 150 | 15000 | 0 | 36 | 36 | 0 | 5400 | 5400 |  | 0 |  | 5400 | 5400
D4 | For an area upto 0.25 m2 | 100 | No. | 180 | 18000 | 4 | 28 | 32 | 720 | 5040 | 5760 |  | 0 | 720 | 4860 | 5580
D5 | For an area upto 0.35 m2 | 100 | No. | 245 | 24500 | 0 | 3 | 3 | 0 | 735 | 735 |  | 0 |  | 735 | 735
D6 | For an area upto 0.50 m2 | 50 | No. | 310 | 15500 | 8 | 19 | 27 | 2480 | 5890 | 8370 |  | 0 | 2480 | 5890 | 8370
D7 | For an area upto 0.65 m2 | 50 | No. | 340 | 17000 | 0 | 4 | 4 | 0 | 1360 | 1360 |  | 0 |  | 1360 | 1360
D8 | For an area upto 0.80 m2 | 50 | No. | 400 | 20000 | 2 | 2 | 4 | 800 | 800 | 1600 |  | 0 | 800 | 800 | 1600
D9 | For an area upto 1.00 m2 | 25 | m2 | 450 | 11250 | 5.3916 | 10.32 | 15.7116 | 2426.2369 | 4644 | 7070.2369 |  | 0 | 2426.2369 | 4644 | 7070.2369
E | Supply and apply firestopping materials to Metallic Duct with Fire Damper and L-angle (Single Sided)
E1 | For an area upto 0.05 m2 | 100 | No. | 32 | 3200 |  |  | 0 | 0 | 0 | 0 |  | 0
E2 | For an area upto 0.10 m2 | 100 | No. | 46 | 4600 |  | 4 | 4 | 0 | 184 | 184 |  | 0 | 0 | 184 | 184
E3 | For an area upto 0.20 m2 | 100 | No. | 51 | 5100 |  | 1 | 1 | 0 | 51 | 51 |  | 0 | 0 | 51 | 51
E4 | For an area upto 0.30 m2 | 100 | No. | 64 | 6400 |  |  | 0 | 0 | 0 | 0 |  | 0
E5 | For an area upto 0.40 m2 | 100 | No. | 74 | 7400 |  |  | 0 | 0 | 0 | 0 |  | 0
E6 | For an area upto 0.50 m2 | 100 | No. | 82 | 8200 |  |  | 0 | 0 | 0 | 0 |  | 0
E7 | For an area upto 0.60 m2 | 100 | No. | 88 | 8800 |  |  | 0 | 0 | 0 | 0 |  | 0
E8 | For an area upto 0.70 m2 | 50 | No. | 98 | 4900 |  |  | 0 | 0 | 0 | 0 |  | 0
E9 | For an area upto 0.80 m2 | 50 | No. | 103 | 5150 |  |  | 0 | 0 | 0 | 0 |  | 0
E10 | For an area upto 0.90 m2 | 25 | No. | 110 | 2750 |  |  | 0 | 0 | 0 | 0 |  | 0
E11 | For an area upto 1.00 m2 | 25 | m2 | 116 | 2900 |  |  | 0 | 0 | 0 | 0 |  | 0
F | Supply and installation of Nullfire FR 230 firestop mortar material (100mm thickness) to Electrical Openings (Single Sided)
F1 | For an area upto 1.00 m2 | 50 | m2 | 680 | 34000 | 6.57 | 18.785 | 25.355 | 4467.6 | 12773.8 | 17241.4 |  | 0 | 3451 | 13464 | 16915
| TOTAL AMOUNT OF CONSTRUCTION JOINTS |  |  |  | 441760 | 2328.6116 | 454.105 | 2782.7166 | 44894.9369 | 50818.8 | 95713.7369 |  |  | 43878.3369 | 51329 | 95207.3369 | -510.2

## MEP (Civil)
Project: |  |  |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  |  |  | Khansaheb Civil Engineering
Period of Completed Works: |  |  |  |  | October 2022 | [13 empty] | all mortar openings priced by sqm diff
Summary of Completed Firestopping Works
No. | Sos Number | Serial No | Level | WIR No. | Location | Penetrant Type | Penetrant Size (in meter) |  | SquareMeters | Opening Size (in meter) |  | SquareMeters | Diffirence | Sides | Rate (AED) | Nos | Total (AED) |  |  | Hotel / Residence | QTY
Hotel
June 2022 - Residence
1 | Sheet 61020 |  | Level 08 | MEP-AX-WR-L8-00271 | Apart. no. 4A | CHW pipe | 3" |  | 0.0044156 |  |  |  |  | 1 |  | 2 | 0 |  |  | Residence |  | PC 01 discrepancies |  | 3.1416 | 25.4 | 3 | 38.1 | 0.0091207
2 | Sheet 61020 |  | Level 08 | MEP-AX-WR-L8-00271 | Apart. no. 4A | fire fighting pipe | 3" |  | 0.0044156 |  |  |  |  | 1 |  | 1 | 0 |  |  | Residence |  | PC 01 discrepancies |  | 3.1416 | 25.4 | 3 | 38.1 | 0.0045604
3 | Sheet 61020 |  | Level 08 | MEP-AX-WR-L8-00271 | Apart. no. 4A | fire fighting pipe | 2" |  | 0.0019625 |  |  |  |  | 1 |  | 1 | 0 |  |  | Residence |  | PC 01 discrepancies |  | 3.1416 | 25.4 | 2 | 25.4 | 0.0020268
4 | Sheet 61020 |  | Level 08 | MEP-AX-WR-L8-00271 | Apart. no. 4A | duct | 0.2 | 0.2 | 0.04 |  |  |  |  | 1 |  | 1 | 0 |  |  | Residence |  | PC 01 discrepancies | [5 empty] | 0.04
5 | Sheet 61020 |  | Level 08 | MEP-AX-WR-L8-00271 | Apart. no. 4A | PVC pipe | 2" |  | 0.0019625 |  |  |  |  | 1 |  | 2 | 0 |  |  | Residence |  | PC 01 discrepancies |  | 3.1416 | 25.4 | 2 | 25.4 | 0.0040537
6 | Sheet 61020 |  | Level 08 | MEP-AX-WR-L8-00271 | Apart. no. 4A | PPR pipe | 2" |  | 0.0019625 |  |  |  |  | 1 |  | 2 | 0 |  |  | Residence |  | PC 01 discrepancies |  | 3.1416 | 25.4 | 2 | 25.4 | 0.0040537
7 | Sheet 61020 |  | Level 08 | MEP-AX-WR-L8-00271 | Apart. no. 4A | opening |  |  |  | 1.2 | 0.52 | 0.624 | 0.56094 | 1 | 340 | 1 | 340 |  |  | Residence | 1 | PC 01 discrepancies | [5 empty] | 0.063815 | 0.56018
[20 empty] | Hotel |  | PC 01 discrepancies
June 2022 - Hotel | [19 empty] | Hotel |  | PC 01 discrepancies
1 | Sheet 61021 |  | Level 05 | MEP-AX-WR-L5-00227 | Passanger Lift Lobby | CHW pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 3 | 0 |  |  | Hotel |  | PC 01 discrepancies |  | 3.1416 | 25.4 | 2 | 25.4 | 0.0060805
2 | Sheet 61021 |  | Level 05 | MEP-AX-WR-L5-00227 | Passanger Lift Lobby | fire fighting pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 1 | 0 |  |  | Hotel |  | PC 01 discrepancies |  | 3.1416 | 25.4 | 3 | 38.1 | 0.0045604
3 | Sheet 61021 |  | Level 05 | MEP-AX-WR-L5-00227 | Passanger Lift Lobby | conduit pipe | 0.5" |  | 0.00013266 |  |  |  |  | 2 |  | 2 | 0 |  |  | Hotel |  | PC 01 discrepancies |  | 3.1416 | 25.4 | 0.5 | 6.35 | 0.00025335
4 | Sheet 61021 |  | Level 05 | MEP-AX-WR-L5-00227 | Passanger Lift Lobby | opening |  |  |  | 0.75 | 0.2 | 0.15 | 0.13943 | 2 | 150 | 1 | 300 |  |  | Hotel | 2 | PC 01 discrepancies | [5 empty] | 0.010894 | 0.13911
[20 empty] | Residence |  | PC 01 discrepancies
June 2022 - Residence | [19 empty] | Residence |  | PC 01 discrepancies
1 | Sheet 61022 |  | Level 24 | MEP-AX-WR-L24-00333 | Corridor | blank opening |  |  |  | 0.15 | 0.15 | 0.0225 | 0.0225 | 2 | 50 | 1 | 100 |  |  | Residence | 2 | PC 01 discrepancies
2 | Sheet 61022 |  | Level 24 | MEP-AX-WR-L24-00333 | Corridor | blank opening |  |  |  | 0.3 | 0.15 | 0.045 | 0.045 | 2 | 50 | 1 | 100 |  |  | Residence | 2 | PC 01 discrepancies
[20 empty] | Residence |  | PC 01 discrepancies
June 2022 - Residence | [19 empty] | Residence |  | PC 01 discrepancies
1 | Sheet 61026 |  | Level 06 | MEP-AX-WR-L6-00532 | Entry door | fire fighting pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 1 | 0 |  |  | Residence |  | PC 01 discrepancies |  | 3.1416 | 25.4 | 4 | 50.8 | 0.0081073
2 | Sheet 61026 |  | Level 06 | MEP-AX-WR-L6-00532 | Entry door | opening |  |  |  | 0.35 | 0.2 | 0.07 | 0.061893 | 2 | 95 | 1 | 190 |  |  | Residence | 2 | PC 01 discrepancies | [5 empty] | 0.0081073 | 0.061893
3 | Sheet 61026 |  | Level 06 | MEP-AX-WR-L6-00532 | Passanger Lift lobby | fire fighting pipe | 1.5" |  | 0.00080384 |  |  |  |  | 2 |  | 1 | 0 |  |  | Residence |  | PC 01 discrepancies
4 | Sheet 61026 |  | Level 06 | MEP-AX-WR-L6-00532 | Passanger Lift lobby | conduit pipe | 0.5" |  | 0.00013266 |  |  |  |  | 2 |  | 3 | 0 |  |  | Residence |  | PC 01 discrepancies
5 | Sheet 61026 |  | Level 06 | MEP-AX-WR-L6-00532 | Passanger Lift lobby | opening |  |  |  | 6" |  | 0.017663 | 0.016461 | 2 | 50 | 1 | 100 |  |  | Residence | 2 | PC 01 discrepancies
6 | Sheet 61026 |  | Level 06 | MEP-AX-WR-L6-00532 | Passanger Lift lobby | CDP pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 1 | 0 |  |  | Residence |  | PC 01 discrepancies |  | 3.1416 | 25.4 | 3 | 38.1 | 0.0045604
7 | Sheet 61026 |  | Level 06 | MEP-AX-WR-L6-00532 | Passanger Lift lobby | CHW pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 2 | 0 |  |  | Residence |  | PC 01 discrepancies |  | 3.1416 | 25.4 | 3 | 38.1 | 0.0091207
8 | Sheet 61026 |  | Level 06 | MEP-AX-WR-L6-00532 | Passanger Lift lobby | opening |  |  |  | 0.2 | 0.35 | 0.07 | 0.056753 | 2 | 95 | 1 | 190 |  |  | Residence | 2 | PC 01 discrepancies | [5 empty] | 0.013681 | 0.056319
9 | Sheet 61027 |  | Level 06 | MEP-AX-WR-L6-00532 | Entry door | fire fighting pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 1 | 0 |  |  | Residence |  | PC 01 discrepancies |  | 3.1416 | 25.4 | 1 | 12.7 | 0.00050671
10 | Sheet 61027 |  | Level 06 | MEP-AX-WR-L6-00532 | Entry door | opening |  |  |  | 0.6 | 0.2 | 0.12 | 0.11951 | 2 | 150 | 1 | 300 |  |  | Residence | 2 | PC 01 discrepancies | [5 empty] | 0.00050671 | 0.11949
11 | Sheet 61027 |  | Level 06 | MEP-AX-WR-L6-00532 | Staircase 03 | fire fighting pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 1 | 0 |  |  | Residence |  | PC 01 discrepancies |  | 3.1416 | 25.4 | 3 | 38.1 | 0.0045604
12 | Sheet 61027 |  | Level 06 | MEP-AX-WR-L6-00532 | Staircase 03 | opening |  |  |  | 0.3 | 0.3 | 0.09 | 0.085584 | 2 | 95 | 1 | 190 |  |  | Residence | 2 | PC 01 discrepancies | [5 empty] | 0.0045604 | 0.08544
13 | Sheet 61027 |  | Level 06 | MEP-AX-WR-L6-00533 | FF Lobby | PVC conduit pipe | 0.5" |  |  | 1" |  |  |  | 2 |  | 4 | 0 | FS702/FB750/FP302 |  | Residence |  | PC 01 discrepancies
14 | Sheet 61027 |  | Level 06 | MEP-AX-WR-L6-00532 | FF Lobby | fire fighting pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 |  |  | Residence |  | PC 01 discrepancies |  | 3.1416 | 25.4 | 2 | 25.4 | 0.0020268
15 | Sheet 61027 |  | Level 06 | MEP-AX-WR-L6-00532 | FF Lobby | opening |  |  |  | 0.4 | 0.25 | 0.1 | 0.098037 | 2 | 95 | 1 | 190 |  |  | Residence | 2 | PC 01 discrepancies | [5 empty] | 0.0020268 | 0.097973
16 | Sheet 61031 |  | Level 06 | MEP-AX-WR-L6-00532 | Entry door | fire fighting pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 1 | 0 |  |  | Residence |  | PC 01 discrepancies |  | 3.1416 | 25.4 | 6 | 76.2 | 0.018241
17 | Sheet 61031 |  | Level 06 | MEP-AX-WR-L6-00532 | Entry door | CHW pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 2 | 0 |  |  | Residence |  | PC 01 discrepancies |  | 3.1416 | 25.4 | 3 | 38.1 | 0.0091207
18 | Sheet 61031 |  | Level 06 | MEP-AX-WR-L6-00532 | Entry door | conduit pipe | 0.5" |  | 0.00013266 |  |  |  |  | 2 |  | 4 | 0 |  |  | Residence |  | PC 01 discrepancies |  | 3.1416 | 25.4 | 0.5 | 6.35 | 0.00050671
19 | Sheet 61031 |  | Level 06 | MEP-AX-WR-L6-00532 | Entry door | opening |  |  |  | 0.8 | 0.3 | 0.24 | 0.21298 | 2 | 180 | 1 | 360 |  |  | Residence | 2 | PC 01 discrepancies | [5 empty] | 0.027869 | 0.21213
[20 empty] | Residence |  | PC 01 discrepancies
July 2022 - Residence - Level 04 | [19 empty] | Residence |  | PC 01 discrepancies
1 | Sheet 61038 |  | Level 04 | MEP-AX-WR-L4-00531 | FF Lobby | PVC pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 1 | 0 |  |  | Residence |  | PC 01 discrepancies |  | 3.1416 | 25.4 | 4 | 50.8 | 0.0081073
2 | Sheet 61038 |  | Level 04 | MEP-AX-WR-L4-00531 | FF Lobby | fire fighting pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 |  |  | Residence |  | PC 01 discrepancies |  | 3.1416 | 25.4 | 2 | 25.4 | 0.0020268
3 | Sheet 61038 |  | Level 04 | MEP-AX-WR-L4-00531 | FF Lobby | opening |  |  |  | 0.3 | 0.25 | 0.075 | 0.065187 | 2 | 95 | 1 | 190 |  |  | Residence | 2 | PC 01 discrepancies | [5 empty] | 0.010134 | 0.064866
4 | Sheet 61038 |  | Level 04 | MEP-AX-WR-L4-00531 | Chill Room | PPR pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 1 | 0 |  |  | Residence |  | PC 01 discrepancies |  | 3.1416 | 25.4 | 4 | 50.8 | 0.0081073
5 | Sheet 61038 |  | Level 04 | MEP-AX-WR-L4-00531 | Chill Room | fire fighting pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 |  |  | Residence |  | PC 01 discrepancies |  | 3.1416 | 25.4 | 2 | 25.4 | 0.0020268
6 | Sheet 61038 |  | Level 04 | MEP-AX-WR-L4-00531 | Chill Room | PVC conduit pipe | 0.5" |  | 0.00013266 |  |  |  |  | 2 |  | 2 | 0 |  |  | Residence |  | PC 01 discrepancies |  | 3.1416 | 25.4 | 0.5 | 6.35 | 0.00025335
7 | Sheet 61038 |  | Level 04 | MEP-AX-WR-L4-00531 | Chill Room | opening |  |  |  | 0.6 | 0.35 | 0.21 | 0.19992 | 2 | 180 | 1 | 360 |  |  | Residence | 2 | PC 01 discrepancies | [5 empty] | 0.010388 | 0.19961
8 | Sheet 61038 |  | Level 04 | MEP-AX-WR-L4-00531 | Passanger Lobby | CDP pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 2 | 0 |  |  | Residence |  | PC 01 discrepancies |  | 3.1416 | 25.4 | 3 | 38.1 | 0.0091207
9 | Sheet 61038 |  | Level 04 | MEP-AX-WR-L4-00531 | Passanger Lobby | CHW pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 1 | 0 |  |  | Residence |  | PC 01 discrepancies |  | 3.1416 | 25.4 | 3 | 38.1 | 0.0045604
10 | Sheet 61038 |  | Level 04 | MEP-AX-WR-L4-00531 | Passanger Lobby | PVC conduit pipe | 0.5" |  | 0.00013266 |  |  |  |  | 2 |  | 10 | 0 |  |  | Residence |  | PC 01 discrepancies |  | 3.1416 | 25.4 | 0.5 | 6.35 | 0.0012668
11 | Sheet 61038 |  | Level 04 | MEP-AX-WR-L4-00531 | Passanger Lobby | opening |  |  |  | 0.35 | 0.25 | 0.0875 | 0.072926 | 2 | 95 | 1 | 190 |  |  | Residence | 2 | PC 01 discrepancies | [5 empty] | 0.014948 | 0.072552
12 | Sheet 61039 |  | Level 04 | MEP-AX-WR-L4-00531 | FTR Room | fire fighting pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 1 | 0 |  |  | Residence |  | PC 01 discrepancies |  | 3.1416 | 25.4 | 3 | 38.1 | 0.0045604
13 | Sheet 61039 |  | Level 04 | MEP-AX-WR-L4-00531 | FTR Room | CHW pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 2 | 0 |  |  | Residence |  | PC 01 discrepancies
14 | Sheet 61039 |  | Level 04 | MEP-AX-WR-L4-00531 | FTR Room | cable tray | 0.1 | 0.1 | 0.01 |  |  |  |  | 2 |  | 1 | 0 |  |  | Residence |  | PC 01 discrepancies
15 | Sheet 61039 |  | Level 04 | MEP-AX-WR-L4-00531 | FTR Room | cable tray | 0.05 | 0.05 | 0.01 |  |  |  |  | 2 |  | 1 | 0 |  |  | Residence |  | PC 01 discrepancies
16 | Sheet 61039 |  | Level 04 | MEP-AX-WR-L4-00531 | FTR Room | cable tray | 0.3 | 0.05 | 0.015 |  |  |  |  | 2 |  | 1 | 0 |  |  | Residence |  | PC 01 discrepancies
17 | Sheet 61039 |  | Level 04 | MEP-AX-WR-L4-00531 | FTR Room | PVC conduit pipe | 0.5" |  | 0.00013266 |  |  |  |  | 2 |  | 3 | 0 |  |  | Residence |  | PC 01 discrepancies
18 | Sheet 61039 |  | Level 04 | MEP-AX-WR-L4-00531 | FTR Room | opening |  |  |  | 1.1 | 0.4 | 0.44 | 0.39528 | 2 | 310 | 1 | 620 |  |  | Residence | 2 | PC 01 discrepancies
July 2022 - Hotel - Level 26
1 | Sheet 61863 |  | Level 26 | MEP-AX-WR-L26-00686 | Housekeeping | cable tray | 0.05 | 0.2 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
2 | Sheet 61863 |  | Level 26 | MEP-AX-WR-L26-00686 | Housekeeping | cable tray | 0.05 | 0.1 | 0.005 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
3 | Sheet 61863 |  | Level 26 | MEP-AX-WR-L26-00686 | Housekeeping | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 2 |  | 3 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
4 | Sheet 61863 |  | Level 26 | MEP-AX-WR-L26-00686 | Housekeeping | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
5 | Sheet 61863 |  | Level 26 | MEP-AX-WR-L26-00686 | Housekeeping | CDP pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
6 | Sheet 61863 |  | Level 26 | MEP-AX-WR-L26-00686 | Housekeeping | fire fighting pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
7 | Sheet 61863 |  | Level 26 | MEP-AX-WR-L26-00686 | Housekeeping | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 10 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
8 | Sheet 61863 |  | Level 26 | MEP-AX-WR-L26-00686 | Housekeeping | opening |  |  |  | 0.6 | 0.9 | 0.54 | 0.47764 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
9 | Sheet 61863 |  | Level 26 | MEP-AX-WR-L26-00686 | Housekeeping | CHW pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
10 | Sheet 61863 |  | Level 26 | MEP-AX-WR-L26-00686 | Housekeeping | opening |  |  |  | 0.3 | 0.3 | 0.09 | 0.086075 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
11 | Sheet 61863 |  | Level 26 | MEP-AX-WR-L26-00686 | Housekeeping | fire fighting pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
12 | Sheet 61863 |  | Level 26 | MEP-AX-WR-L26-00686 | Housekeeping | opening |  |  |  | 0.3 | 0.3 | 0.09 | 0.085584 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
13 | Sheet 61864 |  | Level 26 | MEP-AX-WR-L26-00686 | Lift lobby | CHW pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 2 | 0 | FS709 |  | Hotel |  | PC 01 discrepancies
14 | Sheet 61864 |  | Level 26 | MEP-AX-WR-L26-00686 | Lift lobby | CDP pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 | FS709 |  | Hotel |  | PC 01 discrepancies
15 | Sheet 61864 |  | Level 26 | MEP-AX-WR-L26-00686 | Lift lobby | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 9 | 0 | FS709 |  | Hotel |  | PC 01 discrepancies
16 | Sheet 61864 |  | Level 26 | MEP-AX-WR-L26-00686 | Lift lobby | opening |  |  |  | 0.25 | 0.6 | 0.15 | 0.1397 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
17 | Sheet 61864 |  | Level 26 | MEP-AX-WR-L26-00686 | Water M. Room | PPR pipe | 6" |  | 0.017662 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
18 | Sheet 61864 |  | Level 26 | MEP-AX-WR-L26-00686 | Water M. Room | PPR pipe | 4" |  | 0.00785 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
19 | Sheet 61864 |  | Level 26 | MEP-AX-WR-L26-00686 | Water M. Room | PPR pipe | 3" |  | 0.0044156 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
20 | Sheet 61864 |  | Level 26 | MEP-AX-WR-L26-00686 | Water M. Room | opening |  |  |  | 0.3 | 0.8 | 0.24 | 0.21007 | 1 | 180 | 1 | 180 | FS702/FB750 |  | Hotel | 1 | PC 01 discrepancies
21 | Sheet 61864 |  | Level 26 | MEP-AX-WR-L26-00686 | Room Service | fire fighting pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
22 | Sheet 61864 |  | Level 26 | MEP-AX-WR-L26-00686 | Room Service | CDP pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 | FS709 |  | Hotel |  | PC 01 discrepancies
23 | Sheet 61864 |  | Level 26 | MEP-AX-WR-L26-00686 | Room Service | CHW pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 2 | 0 | FS709 |  | Hotel |  | PC 01 discrepancies
24 | Sheet 61864 |  | Level 26 | MEP-AX-WR-L26-00686 | Room Service | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 8 | 0 | FS709 |  | Hotel |  | PC 01 discrepancies
25 | Sheet 61864 |  | Level 26 | MEP-AX-WR-L26-00686 | Room Service | opening |  |  |  | 0.4 | 0.6 | 0.24 | 0.21252 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
26 | Sheet 61864 |  | Level 26 | MEP-AX-WR-L26-00686 | FF Lobby | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 1 | 0 | FS709 |  | Hotel |  | PC 01 discrepancies
27 | Sheet 61864 |  | Level 26 | MEP-AX-WR-L26-00686 | FF Lobby | fire fighting pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
28 | Sheet 61864 |  | Level 26 | MEP-AX-WR-L26-00686 | FF Lobby | opening |  |  |  | 6" |  | 0.017662 | 0.016681 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
29 | Sheet 61864 |  | Level 26 | MEP-AX-WR-L26-00686 | Staircase | fire fighting pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
30 | Sheet 61864 |  | Level 26 | MEP-AX-WR-L26-00686 | Staircase | opening |  |  |  | 0.3 | 0.3 | 0.09 | 0.08215 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
July 2022 - Hotel - Level 25
1 | Sheet 61854 |  | Level 25 | MEP-AX-WR-L25-00608 | Housekeeping | cable tray | 0.05 | 0.2 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
2 | Sheet 61854 |  | Level 25 | MEP-AX-WR-L25-00608 | Housekeeping | cable tray | 0.05 | 0.1 | 0.005 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
3 | Sheet 61854 |  | Level 25 | MEP-AX-WR-L25-00608 | Housekeeping | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
4 | Sheet 61854 |  | Level 25 | MEP-AX-WR-L25-00608 | Housekeeping | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
5 | Sheet 61854 |  | Level 25 | MEP-AX-WR-L25-00608 | Housekeeping | fire fighting pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
6 | Sheet 61854 |  | Level 25 | MEP-AX-WR-L25-00608 | Housekeeping | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 1 | 0 | FS709 |  | Hotel |  | PC 01 discrepancies
7 | Sheet 61854 |  | Level 25 | MEP-AX-WR-L25-00608 | Housekeeping | opening |  |  |  | 0.6 | 0.9 | 0.54 | 0.50402 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
8 | Sheet 61854 |  | Level 25 | MEP-AX-WR-L25-00608 | Housekeeping | CHW pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 | FS709 |  | Hotel |  | PC 01 discrepancies
9 | Sheet 61854 |  | Level 25 | MEP-AX-WR-L25-00608 | Housekeeping | CDP pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 | FS709 |  | Hotel |  | PC 01 discrepancies
10 | Sheet 61854 |  | Level 25 | MEP-AX-WR-L25-00608 | Housekeeping | opening |  |  |  | 0.3 | 0.3 | 0.09 | 0.086075 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
11 | Sheet 61854 |  | Level 25 | MEP-AX-WR-L25-00608 | Housekeeping | fire fighting pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
12 | Sheet 61854 |  | Level 25 | MEP-AX-WR-L25-00608 | Housekeeping | opening |  |  |  | 0.3 | 0.3 | 0.09 | 0.072337 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
13 | Sheet 61854 |  | Level 25 | MEP-AX-WR-L25-00608 | Passanger Lift | fire fighting pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
14 | Sheet 61854 |  | Level 25 | MEP-AX-WR-L25-00608 | Passanger Lift | CDP pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 | FS709 |  | Hotel |  | PC 01 discrepancies
15 | Sheet 61854 |  | Level 25 | MEP-AX-WR-L25-00608 | Passanger Lift | CHW pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 | FS709 |  | Hotel |  | PC 01 discrepancies
16 | Sheet 61854 |  | Level 25 | MEP-AX-WR-L25-00608 | Passanger Lift | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 1 | 0 | FS709 |  | Hotel |  | PC 01 discrepancies
17 | Sheet 61854 |  | Level 25 | MEP-AX-WR-L25-00608 | Passanger Lift | opening |  |  |  | 0.2 | 0.6 | 0.12 | 0.11509 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
18 | Sheet 61855 |  | Level 25 | MEP-AX-WR-L25-00608 | Water M. Room | PPR pipe | 6" |  | 0.017662 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
19 | Sheet 61855 |  | Level 25 | MEP-AX-WR-L25-00608 | Water M. Room | PPR pipe | 4" |  | 0.00785 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
20 | Sheet 61855 |  | Level 25 | MEP-AX-WR-L25-00608 | Water M. Room | PPR pipe | 3" |  | 0.0044156 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
21 | Sheet 61855 |  | Level 25 | MEP-AX-WR-L25-00608 | Water M. Room | opening |  |  |  | 0.3 | 0.8 | 0.24 | 0.21007 | 1 | 180 | 1 | 180 | FS702/FB750 |  | Hotel | 1 | PC 01 discrepancies
22 | Sheet 61855 |  | Level 25 | MEP-AX-WR-L25-00608 | Lift lobby | CHW pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 | FS709 |  | Hotel |  | PC 01 discrepancies
23 | Sheet 61855 |  | Level 25 | MEP-AX-WR-L25-00608 | Lift lobby | CDP pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 | FS709 |  | Hotel |  | PC 01 discrepancies
24 | Sheet 61855 |  | Level 25 | MEP-AX-WR-L25-00608 | Lift lobby | fire fighting pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
25 | Sheet 61855 |  | Level 25 | MEP-AX-WR-L25-00608 | Lift lobby | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 1 | 0 | FS709 |  | Hotel |  | PC 01 discrepancies
26 | Sheet 61855 |  | Level 25 | MEP-AX-WR-L25-00608 | Lift lobby | opening |  |  |  | 0.4 | 0.6 | 0.24 | 0.21792 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
27 | Sheet 61855 |  | Level 25 | MEP-AX-WR-L25-00608 | Room Service | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 2 | 0 | FS709 |  | Hotel |  | PC 01 discrepancies
28 | Sheet 61855 |  | Level 25 | MEP-AX-WR-L25-00608 | Room Service | opening |  |  |  | 4" |  | 0.00785 | 0.0068688 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
29 | Sheet 61855 |  | Level 25 | MEP-AX-WR-L25-00608 | Room Service | fire fighting pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
30 | Sheet 61855 |  | Level 25 | MEP-AX-WR-L25-00608 | Room Service | opening |  |  |  | 0.3 | 0.3 | 0.09 | 0.072337 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
July 2022 - Hotel - Level 24
1 | Sheet 61859 |  | Level 24 | MEP-AX-WR-L24-00588 | Housekeeping | cable tray | 0.05 | 0.2 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
2 | Sheet 61859 |  | Level 24 | MEP-AX-WR-L24-00588 | Housekeeping | cable tray | 0.05 | 0.1 | 0.005 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
3 | Sheet 61859 |  | Level 24 | MEP-AX-WR-L24-00588 | Housekeeping | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 2 |  | 3 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
4 | Sheet 61859 |  | Level 24 | MEP-AX-WR-L24-00588 | Housekeeping | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
5 | Sheet 61859 |  | Level 24 | MEP-AX-WR-L24-00588 | Housekeeping | fire fighting pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
6 | Sheet 61859 |  | Level 24 | MEP-AX-WR-L24-00588 | Housekeeping | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 8 | 0 | FS709 |  | Hotel |  | PC 01 discrepancies
7 | Sheet 61859 |  | Level 24 | MEP-AX-WR-L24-00588 | Housekeeping | opening |  |  |  | 0.6 | 0.9 | 0.54 | 0.48058 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
8 | Sheet 61859 |  | Level 24 | MEP-AX-WR-L24-00588 | Housekeeping | CHW pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 2 | 0 | FS709 |  | Hotel |  | PC 01 discrepancies
9 | Sheet 61859 |  | Level 24 | MEP-AX-WR-L24-00588 | Housekeeping | CDP pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 | FS709 |  | Hotel |  | PC 01 discrepancies
10 | Sheet 61859 |  | Level 24 | MEP-AX-WR-L24-00588 | Housekeeping | opening |  |  |  | 0.3 | 0.3 | 0.09 | 0.084112 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
11 | Sheet 61860 |  | Level 24 | MEP-AX-WR-L24-00588 | Housekeeping | fire fighting pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
12 | Sheet 61860 |  | Level 24 | MEP-AX-WR-L24-00588 | Housekeeping | opening |  |  |  | 0.3 | 0.3 | 0.09 | 0.072337 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
13 | Sheet 61860 |  | Level 24 | MEP-AX-WR-L24-00588 | Lift lobby | fire fighting pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
14 | Sheet 61860 |  | Level 24 | MEP-AX-WR-L24-00588 | Lift lobby | CDP pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 | FS709 |  | Hotel |  | PC 01 discrepancies
15 | Sheet 61860 |  | Level 24 | MEP-AX-WR-L24-00588 | Lift lobby | CHW pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 2 | 0 | FS709 |  | Hotel |  | PC 01 discrepancies
16 | Sheet 61860 |  | Level 24 | MEP-AX-WR-L24-00588 | Lift lobby | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 6 | 0 | FS709 |  | Hotel |  | PC 01 discrepancies
17 | Sheet 61860 |  | Level 24 | MEP-AX-WR-L24-00588 | Lift lobby | opening |  |  |  | 0.2 | 0.6 | 0.12 | 0.11068 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
18 | Sheet 61860 |  | Level 24 | MEP-AX-WR-L24-00588 | Water M. Room | PPR pipe | 6" |  | 0.017662 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
19 | Sheet 61860 |  | Level 24 | MEP-AX-WR-L24-00588 | Water M. Room | PPR pipe | 4" |  | 0.00785 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
20 | Sheet 61860 |  | Level 24 | MEP-AX-WR-L24-00588 | Water M. Room | PPR pipe | 3" |  | 0.0044156 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
21 | Sheet 61860 |  | Level 24 | MEP-AX-WR-L24-00588 | Water M. Room | opening |  |  |  | 0.3 | 0.8 | 0.24 | 0.21007 | 1 | 180 | 1 | 180 | FS702/FB750 |  | Hotel | 1 | PC 01 discrepancies
22 | Sheet 61860 |  | Level 24 | MEP-AX-WR-L24-00588 | Room Service | CHW pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 2 | 0 | FS709 |  | Hotel |  | PC 01 discrepancies
23 | Sheet 61860 |  | Level 24 | MEP-AX-WR-L24-00588 | Room Service | CDP pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 | FS709 |  | Hotel |  | PC 01 discrepancies
24 | Sheet 61860 |  | Level 24 | MEP-AX-WR-L24-00588 | Room Service | fire fighting pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
25 | Sheet 61860 |  | Level 24 | MEP-AX-WR-L24-00588 | Room Service | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 5 | 0 | FS709 |  | Hotel |  | PC 01 discrepancies
26 | Sheet 61860 |  | Level 24 | MEP-AX-WR-L24-00588 | Room Service | opening |  |  |  | 0.4 | 0.6 | 0.24 | 0.214 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
27 | Sheet 61860 |  | Level 24 | MEP-AX-WR-L24-00588 | Staircase | fire fighting pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel |  | PC 01 discrepancies
28 | Sheet 61860 |  | Level 24 | MEP-AX-WR-L24-00588 | Staircase | opening |  |  |  | 0.3 | 0.3 | 0.09 | 0.072337 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
July 2022 - Residence - Basement 01
1 | Sheet 61861 |  | Basement 01 | MEP-AX-WR-B1-00849 | Fresh Air plenum | duct | 1.7 | 2 | 3.4 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Residence |  | PC 01 discrepancies
2 | Sheet 61861 |  | Basement 01 | MEP-AX-WR-B1-00849 | Fresh Air plenum | opening |  |  |  | 2.2 | 2.7 | 5.94 | 2.54 | 2 | 450 | 1 | 2286 | FS702/FB750 |  | Residence | 5.08 | PC 01 discrepancies
3 | Sheet 61861 |  | Basement 01 | MEP-AX-WR-B1-00849 | Fresh Air plenum | duct | 1.7 | 2 | 3.4 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Residence |  | PC 01 discrepancies
4 | Sheet 61861 |  | Basement 01 | MEP-AX-WR-B1-00849 | Fresh Air plenum | opening |  |  |  | 2.15 | 2.8 | 6.02 | 2.62 | 2 | 450 | 1 | 2358 | FS702/FB750 |  | Residence | 5.24 | PC 01 discrepancies | [7 empty] | 4644
5 | Sheet 61861 |  | Basement 01 | MEP-AX-WR-B1-00849 | Fresh Air plenum | duct | 1.7 | 2 | 3.4 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Residence |  | PC 01 discrepancies
6 | Sheet 61861 |  | Basement 01 | MEP-AX-WR-B1-00849 | Fresh Air plenum | opening |  |  |  | 1.9 | 2.15 | 4.085 | 0.685 | 2 | 400 | 1 | 800 | FS702/FB750 |  | Residence | 2 | PC 01 discrepancies
7 | Sheet 61861 |  | Basement 01 | MEP-AX-WR-B1-00849 | Fresh Air plenum | duct | 0.75 | 2 | 1.5 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Residence |  | PC 01 discrepancies
8 | Sheet 61861 |  | Basement 01 | MEP-AX-WR-B1-00849 | Fresh Air plenum | opening |  |  |  | 0.9 | 2.1 | 1.89 | 0.39 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Residence | 2 | PC 01 discrepancies
9 | Sheet 61861 |  | Basement 01 | MEP-AX-WR-B1-00849 | Fresh Air plenum | duct | 0.75 | 2 | 1.5 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Residence |  | PC 01 discrepancies
10 | Sheet 61861 |  | Basement 01 | MEP-AX-WR-B1-00849 | Fresh Air plenum | opening |  |  |  | 0.9 | 2.15 | 1.935 | 0.435 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Residence | 2 | PC 01 discrepancies
11 | Sheet 61861 |  | Basement 01 | MEP-AX-WR-B1-00849 | CEF Room | duct | 1.5 | 1.6 | 2.4 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Residence |  | PC 01 discrepancies
12 | Sheet 61861 |  | Basement 01 | MEP-AX-WR-B1-00849 | CEF Room | opening |  |  |  | 1.6 | 1.7 | 2.72 | 0.32 | 1 | 245 | 1 | 245 | FS702/FB750 |  | Residence | 1 | PC 01 discrepancies
13 | Sheet 61861 |  | Basement 01 | MEP-AX-WR-B1-00849 | CEF Room | duct | 1.5 | 1.6 | 2.4 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Residence |  | PC 01 discrepancies
14 | Sheet 61861 |  | Basement 01 | MEP-AX-WR-B1-00849 | CEF Room | opening |  |  |  | 1.6 | 1.8 | 2.88 | 0.48 | 1 | 310 | 1 | 310 | FS702/FB750 |  | Residence | 1 | PC 01 discrepancies
15 | Sheet 61861 |  | Basement 01 | MEP-AX-WR-B1-00849 | CEF Room | PVC pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Residence |  | PC 01 discrepancies
16 | Sheet 61861 |  | Basement 01 | MEP-AX-WR-B1-00849 | CEF Room | opening |  |  |  | 0.25 | 0.5 | 0.125 | 0.11715 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Residence | 2 | PC 01 discrepancies
17 | Sheet 61861 |  | Basement 01 | MEP-AX-WR-B1-00849 | CEF Room | PVC pipe | 4" |  |  | 6" |  |  |  | 2 |  | 5 | 0 | FS702/FP302 |  | Residence |  | PC 01 discrepancies
18 | Sheet 61861 |  | Basement 01 | MEP-AX-WR-B1-00849 | CEF Room | fire fighting pipe | 2" |  |  | 3" |  |  |  | 2 |  | 2 | 0 | FS702 |  | Residence |  | PC 01 discrepancies
19 | Sheet 61861 |  | Basement 01 | MEP-AX-WR-B1-00849 | CEF Room | fire fighting pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Residence |  | PC 01 discrepancies
20 | Sheet 61861 |  | Basement 01 | MEP-AX-WR-B1-00849 | CEF Room | opening |  |  |  | 0.15 | 0.2 | 0.03 | 0.028037 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Residence | 2 | PC 01 discrepancies
21 | Sheet 61861 |  | Basement 01 | MEP-AX-WR-B1-00849 | CEF Room | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Residence |  | PC 01 discrepancies
22 | Sheet 61861 |  | Basement 01 | MEP-AX-WR-B1-00849 | CEF Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Residence |  | PC 01 discrepancies
23 | Sheet 61861 |  | Basement 01 | MEP-AX-WR-B1-00849 | CEF Room | opening |  |  |  | 0.4 | 0.5 | 0.2 | 0.175 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Residence | 2 | PC 01 discrepancies
[20 empty] | Hotel |  | PC 01 discrepancies
August 2022 - Hotel | [19 empty] | Hotel |  | PC 01 discrepancies
1 | Sheet 61869 |  | Level 19 | WIR - 0731 | Housekeeping | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 2 |  | 3 | 0 |  |  | Hotel |  | PC 01 discrepancies
2 | Sheet 61869 |  | Level 19 | WIR - 0731 | Housekeeping | cable trunking | 0.05 | 0.2 | 0.01 |  |  |  |  | 2 |  | 2 | 0 |  |  | Hotel |  | PC 01 discrepancies
3 | Sheet 61869 |  | Level 19 | WIR - 0731 | Housekeeping | cable tray | 0.05 | 0.2 | 0.01 |  |  |  |  | 2 |  | 2 | 0 |  |  | Hotel |  | PC 01 discrepancies
4 | Sheet 61869 |  | Level 19 | WIR - 0731 | Housekeeping | fire fighting pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 1 | 0 |  |  | Hotel |  | PC 01 discrepancies
5 | Sheet 61869 |  | Level 19 | WIR - 0731 | Housekeeping | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 3 | 0 |  |  | Hotel |  | PC 01 discrepancies
6 | Sheet 61869 |  | Level 19 | WIR - 0731 | Housekeeping | cable pipe | 0.5" |  | 0.00013266 |  |  |  |  | 2 |  | 6 | 0 |  |  | Hotel |  | PC 01 discrepancies
7 | Sheet 61869 |  | Level 19 | WIR - 0731 | Housekeeping | opening |  |  |  | 0.6 | 0.9 | 0.54 | 0.53773 | 2 | 340 | 1 | 680 |  |  | Hotel | 2 | PC 01 discrepancies | [8 empty] | 18689
8 | Sheet 61869 |  | Level 19 | WIR - 0731 | Housekeeping | CHW pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 2 | 0 |  |  | Hotel |  | PC 01 discrepancies
9 | Sheet 61869 |  | Level 19 | WIR - 0731 | Housekeeping | opening |  |  |  | 0.3 | 0.3 | 0.09 | 0.086075 | 2 | 95 | 1 | 190 |  |  | Hotel | 2 | PC 01 discrepancies
10 | Sheet 61869 |  | Level 19 | WIR - 0731 | Housekeeping | CDP pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 |  |  | Hotel |  | PC 01 discrepancies
11 | Sheet 61869 |  | Level 19 | WIR - 0731 | Staircase 08 | fire fighting pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 1 | 0 |  |  | Hotel |  | PC 01 discrepancies
12 | Sheet 61869 |  | Level 19 | WIR - 0731 | Staircase 08 | opening |  |  |  | 0.3 | 0.3 | 0.09 | 0.085584 | 2 | 95 | 1 | 190 |  |  | Hotel | 2 | PC 01 discrepancies
13 | Sheet 61869 |  | Level 19 | WIR - 0731 | Lift Lobby | fire fighting pipe | 1" |  |  | 3" |  |  |  | 2 |  | 1 | 0 |  |  | Hotel |  | PC 01 discrepancies
14 | Sheet 61869 |  | Level 19 | WIR - 0731 | Lift Lobby | CDP pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 |  |  | Hotel |  | PC 01 discrepancies
15 | Sheet 61869 |  | Level 19 | WIR - 0731 | Lift Lobby | CHW pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 2 | 0 |  |  | Hotel |  | PC 01 discrepancies
16 | Sheet 61869 |  | Level 19 | WIR - 0731 | Lift Lobby | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 13 | 0 |  |  | Hotel |  | PC 01 discrepancies
17 | Sheet 61869 |  | Level 19 | WIR - 0731 | Lift Lobby | opening |  |  |  | 0.25 | 0.6 | 0.15 | 0.1397 | 2 | 150 | 1 | 300 |  |  | Hotel | 2 | PC 01 discrepancies
18 | Sheet 61869 |  | Level 19 | WIR - 0731 | Water Meter Room | PPR pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 3 | 0 |  |  | Hotel |  | PC 01 discrepancies
19 | Sheet 61869 |  | Level 19 | WIR - 0731 | Water Meter Room | opening |  |  |  | 0.3 | 0.8 | 0.24 | 0.22675 | 2 | 180 | 1 | 360 |  |  | Hotel | 2 | PC 01 discrepancies
20 | Sheet 61869 |  | Level 19 | WIR - 0731 | Water Meter Room | CDP pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 |  |  | Hotel |  | PC 01 discrepancies
21 | Sheet 61869 |  | Level 19 | WIR - 0731 | Lobby | conduit pipe | 1" |  |  | 2" |  |  |  | 2 |  | 1 | 0 |  |  | Hotel |  | PC 01 discrepancies
22 | Sheet 61869 |  | Level 19 | WIR - 0731 | Lobby | fire fighting pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 1 | 0 |  |  | Hotel |  | PC 01 discrepancies
23 | Sheet 61869 |  | Level 19 | WIR - 0731 | Lobby | CHW pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 2 | 0 |  |  | Hotel |  | PC 01 discrepancies
24 | Sheet 61869 |  | Level 19 | WIR - 0731 | Lobby | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 6 | 0 |  |  | Hotel |  | PC 01 discrepancies
25 | Sheet 61869 |  | Level 19 | WIR - 0731 | Lobby | opening |  |  |  | 0.4 | 0.8 | 0.32 | 0.30528 | 2 | 245 | 1 | 490 |  |  | Hotel | 2 | PC 01 discrepancies | [7 empty] | 3525
26 | Sheet 61869 |  | Level 19 | WIR - 0731 | Service Lobby | fire fighting pipe | 1" |  |  | 3" |  |  |  | 2 |  | 1 | 0 |  |  | Hotel |  | PC 01 discrepancies
27 | Sheet 61869 |  | Level 19 | WIR - 0731 | Service Lobby | conduit pipe | 1" |  |  | 2" |  |  |  | 2 |  | 1 | 0 |  |  | Hotel |  | PC 01 discrepancies
28 | Sheet 61869 |  | Level 19 | WIR - 0731 | Service Lobby | conduit pipe | 1" |  |  | 2" |  |  |  | 2 |  | 1 | 0 |  |  | Hotel |  | PC 01 discrepancies
29 | Sheet 61870 |  | Level 19 | WIR - 0731 | Staircase 07 | fire fighting pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 1 | 0 |  |  | Hotel |  | PC 01 discrepancies
30 | Sheet 61870 |  | Level 19 | WIR - 0731 | Shaft | opening |  |  |  | 0.3 | 0.3 | 0.09 | 0.085584 | 2 | 95 | 1 | 190 |  |  | Hotel | 2 | PC 01 discrepancies
31 | Sheet 61871 |  | Level 19 | MEP-AX-WR-L19-00731 | Outer sleeve | PPR pipe | 3" |  | 0.0044156 |  |  |  |  | 1 | 30 | 3 | 90 |  |  | Hotel | 3 | PC 01 discrepancies
32 | Sheet 61871 |  | Level 19 | MEP-AX-WR-L19-00731 | Outer sleeve | fire fighting pipe | 2" |  | 0.0019625 |  |  |  |  | 1 | 14 | 1 | 14 |  |  | Hotel | 1 | PC 01 discrepancies
33 | Sheet 61871 |  | Level 19 | MEP-AX-WR-L19-00731 | Outer sleeve | opening |  |  |  | 0.2 | 0.4 | 0.08 | 0.064791 | 1 | 95 | 1 | 95 |  |  | Hotel | 1 | PC 01 discrepancies
34 | Sheet 61871 |  | Level 19 | MEP-AX-WR-L19-00731 | Outer sleeve | PPR pipe | 3" |  | 0.0044156 |  |  |  |  | 1 | 30 | 3 | 90 |  |  | Hotel | 3 | PC 01 discrepancies
35 | Sheet 61871 |  | Level 19 | MEP-AX-WR-L19-00731 | Outer sleeve | opening |  |  |  | 0.2 | 0.4 | 0.08 | 0.066753 | 1 | 95 | 1 | 95 |  |  | Hotel | 1 | PC 01 discrepancies
36 | Sheet 61871 |  | Level 19 | MEP-AX-WR-L19-00731 | Outer sleeve | fire fighting pipe | 2" |  |  | 4" |  |  |  | 1 | 14 | 1 | 14 | FS702/FB750 |  | Hotel | 1 | PC 01 discrepancies
37 | Sheet 61871 |  | Level 19 | MEP-AX-WR-L19-00731 | Outer sleeve | fire fighting pipe | 2" |  |  | 4" |  |  |  | 1 | 14 | 1 | 14 | FS702/FB750 |  | Hotel | 1 | PC 01 discrepancies
38 | Sheet 61871 |  | Level 19 | MEP-AX-WR-L19-00731 | Outer sleeve | PPR pipe | 3" |  |  | 5" |  |  |  | 1 | 30 | 3 | 90 | FS702/FB750/FP302 |  | Hotel | 3 | PC 01 discrepancies
39 | Sheet 61871 |  | Level 19 | MEP-AX-WR-L19-00731 | Outer sleeve | fire fighting pipe | 3" |  |  | 5" |  |  |  | 1 | 16 | 1 | 16 | FS702/FB750 |  | Hotel | 1 | PC 01 discrepancies
40 | Sheet 61871 |  | Level 19 | MEP-AX-WR-L19-00731 | Outer sleeve | CHW pipe | 3" |  |  | 5" |  |  |  | 1 | 23 | 2 | 46 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
41 | Sheet 61871 |  | Level 19 | MEP-AX-WR-L19-00731 | Outer sleeve | PPR pipe | 3" |  |  | 5" |  |  |  | 1 | 30 | 3 | 90 | FS702/FB750/FP302 |  | Hotel | 3 | PC 01 discrepancies
42 | Sheet 61871 |  | Level 19 | MEP-AX-WR-L19-00731 | Outer sleeve | fire fighting pipe | 2" |  |  | 4" |  |  |  | 1 | 14 | 1 | 14 | FS702/FB750 |  | Hotel | 1 | PC 01 discrepancies
43 | Sheet 61871 |  | Level 19 | MEP-AX-WR-L19-00731 | Outer sleeve | CHW pipe | 3" |  |  | 5" |  |  |  | 1 | 23 | 1 | 23 | FS702/FB750 |  | Hotel | 1 | PC 01 discrepancies
44 | Sheet 61871 |  | Level 19 | MEP-AX-WR-L19-00731 | Outer sleeve | fire fighting pipe | 3" |  |  | 5" |  |  |  | 1 | 16 | 1 | 16 | FS702/FB750 |  | Hotel | 1 | PC 01 discrepancies
[20 empty] | Hotel |  | PC 01 discrepancies
August 2022 - Hotel | [19 empty] | Hotel |  | PC 01 discrepancies
1 | Sheet 61873 |  | Level 17 | WIR - 0739 | Electrical Rm, slab | busbar | 0.05 | 0.06 | 0.01 |  |  |  |  | 1 |  | 4 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
2 | Sheet 61873 |  | Level 17 | WIR - 0739 | Electrical Rm, slab | cable tray | 0.05 | 0.5 | 0.025 |  |  |  |  | 1 |  | 1 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
3 | Sheet 61873 |  | Level 17 | WIR - 0739 | Electrical Rm, slab | opening Mortar |  |  |  | 0.5 | 2.4 | 1.2 | 1.135 | 1 | 680 | 1 | 771.8 | FR 230 |  | Hotel | 1.135 | PC 01 discrepancies
4 | Sheet 61873 |  | Level 17 | WIR - 0739 | Electrical Rm, slab | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 2 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
5 | Sheet 61873 |  | Level 17 | WIR - 0739 | Electrical Rm, slab | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 6 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
6 | Sheet 61873 |  | Level 17 | WIR - 0739 | Electrical Rm, slab | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
7 | Sheet 61873 |  | Level 17 | WIR - 0739 | Electrical Rm, slab | opening Mortar |  |  |  | 0.25 | 1.63 | 0.4075 | 0.3075 | 1 | 680 | 1 | 209.1 | FR 230 |  | Hotel | 0.3075 | PC 01 discrepancies
8 | Sheet 61873 |  | Level 18 | WIR - 0733 | Electrical Rm, slab | busbar | 0.05 | 0.06 | 0.01 |  |  |  |  | 1 |  | 4 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
9 | Sheet 61873 |  | Level 18 | WIR - 0733 | Electrical Rm, slab | cable tray | 0.05 | 0.5 | 0.025 |  |  |  |  | 1 |  | 1 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
10 | Sheet 61873 |  | Level 18 | WIR - 0733 | Electrical Rm, slab | opening Mortar |  |  |  | 0.5 | 2.4 | 1.2 | 1.135 | 1 | 680 | 1 | 771.8 | FR 230 |  | Hotel | 1.135 | PC 01 discrepancies
11 | Sheet 61873 |  | Level 18 | WIR - 0733 | Electrical Rm, slab | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 2 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
12 | Sheet 61873 |  | Level 18 | WIR - 0733 | Electrical Rm, slab | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 6 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
13 | Sheet 61873 |  | Level 18 | WIR - 0733 | Electrical Rm, slab | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
14 | Sheet 61873 |  | Level 18 | WIR - 0733 | Electrical Rm, slab | opening Mortar |  |  |  | 0.25 | 1.63 | 0.4075 | 0.3075 | 1 | 680 | 1 | 209.1 | FR 230 |  | Hotel | 0.3075 | PC 01 discrepancies
15 | Sheet 61873 |  | Level 19 | WIR - 0734 | Electrical Rm, slab | busbar | 0.05 | 0.06 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
16 | Sheet 61873 |  | Level 19 | WIR - 0734 | Electrical Rm, slab | cable tray | 0.05 | 0.5 | 0.025 |  |  |  |  | 1 |  | 1 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
17 | Sheet 61873 |  | Level 19 | WIR - 0734 | Electrical Rm, slab | opening Mortar |  |  |  | 0.5 | 2.4 | 1.2 | 1.155 | 1 | 680 | 1 | 785.4 | FR 230 |  | Hotel | 1.155 | PC 01 discrepancies
18 | Sheet 61873 |  | Level 19 | WIR - 0734 | Electrical Rm, slab | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 2 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
19 | Sheet 61873 |  | Level 19 | WIR - 0734 | Electrical Rm, slab | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 6 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
20 | Sheet 61873 |  | Level 19 | WIR - 0734 | Electrical Rm, slab | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
21 | Sheet 61873 |  | Level 19 | WIR - 0734 | Electrical Rm, slab | opening Mortar |  |  |  | 0.25 | 1.63 | 0.4075 | 0.3075 | 1 | 680 | 1 | 209.1 | FR 230 |  | Hotel | 0.3075 | PC 01 discrepancies
22 | Sheet 61874 |  | Level 20 | WIR - 0735 | Electrical Rm, slab | busbar | 0.05 | 0.06 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
23 | Sheet 61874 |  | Level 20 | WIR - 0735 | Electrical Rm, slab | cable tray | 0.05 | 0.5 | 0.025 |  |  |  |  | 1 |  | 1 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
24 | Sheet 61874 |  | Level 20 | WIR - 0735 | Electrical Rm, slab | opening Mortar |  |  |  | 0.5 | 2.4 | 1.2 | 1.155 | 1 | 680 | 1 | 785.4 | FR 230 |  | Hotel | 1.155 | PC 01 discrepancies
25 | Sheet 61874 |  | Level 20 | WIR - 0735 | Electrical Rm, slab | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 2 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
26 | Sheet 61874 |  | Level 20 | WIR - 0735 | Electrical Rm, slab | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 6 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
27 | Sheet 61874 |  | Level 20 | WIR - 0735 | Electrical Rm, slab | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
28 | Sheet 61874 |  | Level 20 | WIR - 0735 | Electrical Rm, slab | opening Mortar |  |  |  | 0.25 | 1.63 | 0.4075 | 0.3075 | 1 | 680 | 1 | 209.1 | FR 230 |  | Hotel | 0.3075 | PC 01 discrepancies
29 | Sheet 61874 |  | Level 21 | WIR - 0736 | Electrical Rm, slab | busbar | 0.05 | 0.06 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
30 | Sheet 61874 |  | Level 21 | WIR - 0736 | Electrical Rm, slab | cable tray | 0.05 | 0.5 | 0.025 |  |  |  |  | 1 |  | 1 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
31 | Sheet 61874 |  | Level 21 | WIR - 0736 | Electrical Rm, slab | opening Mortar |  |  |  | 0.5 | 2.4 | 1.2 | 1.155 | 1 | 680 | 1 | 785.4 | FR 230 |  | Hotel | 1.155 | PC 01 discrepancies
32 | Sheet 61874 |  | Level 21 | WIR - 0736 | Electrical Rm, slab | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 2 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
33 | Sheet 61874 |  | Level 21 | WIR - 0736 | Electrical Rm, slab | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 6 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
34 | Sheet 61874 |  | Level 21 | WIR - 0736 | Electrical Rm, slab | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
35 | Sheet 61874 |  | Level 21 | WIR - 0736 | Electrical Rm, slab | opening Mortar |  |  |  | 0.25 | 1.63 | 0.4075 | 0.3075 | 1 | 680 | 1 | 209.1 | FR 230 |  | Hotel | 0.3075 | PC 01 discrepancies
36 | Sheet 61874 |  | Level 22 | WIR - 0737 | Electrical Rm, slab | busbar | 0.05 | 0.06 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
37 | Sheet 61874 |  | Level 22 | WIR - 0737 | Electrical Rm, slab | cable tray | 0.05 | 0.5 | 0.025 |  |  |  |  | 1 |  | 1 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
38 | Sheet 61874 |  | Level 22 | WIR - 0737 | Electrical Rm, slab | opening Mortar |  |  |  | 0.5 | 2.4 | 1.2 | 1.155 | 1 | 680 | 1 | 785.4 | FR 230 |  | Hotel | 1.155 | PC 01 discrepancies
39 | Sheet 61874 |  | Level 22 | WIR - 0737 | Electrical Rm, slab | cable tray | 0.05 | 0.2 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
40 | Sheet 61874 |  | Level 22 | WIR - 0737 | Electrical Rm, slab | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 6 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
41 | Sheet 61874 |  | Level 22 | WIR - 0737 | Electrical Rm, slab | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
42 | Sheet 61874 |  | Level 22 | WIR - 0737 | Electrical Rm, slab | opening Mortar |  |  |  | 0.25 | 1.63 | 0.4075 | 0.3175 | 1 | 680 | 1 | 215.9 | FR 230 |  | Hotel | 0.3175 | PC 01 discrepancies
43 | Sheet 61874 |  | Level 23 | WIR - 0738 | Electrical Rm, slab | busbar | 0.05 | 0.06 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
44 | Sheet 61874 |  | Level 23 | WIR - 0738 | Electrical Rm, slab | cable tray | 0.05 | 0.5 | 0.025 |  |  |  |  | 1 |  | 1 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
45 | Sheet 61874 |  | Level 23 | WIR - 0738 | Electrical Rm, slab | opening Mortar |  |  |  | 0.5 | 2.4 | 1.2 | 1.155 | 1 | 680 | 1 | 785.4 | FR 230 |  | Hotel | 1.155 | PC 01 discrepancies
46 | Sheet 61874 |  | Level 23 | WIR - 0738 | Electrical Rm, slab | cable tray | 0.05 | 0.2 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
47 | Sheet 61874 |  | Level 23 | WIR - 0738 | Electrical Rm, slab | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 6 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
48 | Sheet 61874 |  | Level 23 | WIR - 0738 | Electrical Rm, slab | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
49 | Sheet 61874 |  | Level 23 | WIR - 0738 | Electrical Rm, slab | opening Mortar |  |  |  | 0.25 | 1.63 | 0.4075 | 0.3175 | 1 | 680 | 1 | 215.9 | FR 230 |  | Hotel | 0.3175 | PC 01 discrepancies
50 | Sheet 61875 |  | Level 24 | WIR - 0762 | Electrical Rm, slab | busbar | 0.05 | 0.06 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
51 | Sheet 61875 |  | Level 24 | WIR - 0762 | Electrical Rm, slab | cable tray | 0.05 | 0.5 | 0.025 |  |  |  |  | 1 |  | 1 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
52 | Sheet 61875 |  | Level 24 | WIR - 0762 | Electrical Rm, slab | opening Mortar |  |  |  | 0.5 | 2.4 | 1.2 | 1.155 | 1 | 680 | 1 | 785.4 | FR 230 |  | Hotel | 1.155 | PC 01 discrepancies
53 | Sheet 61875 |  | Level 24 | WIR - 0762 | Electrical Rm, slab | cable tray | 0.05 | 0.2 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
54 | Sheet 61875 |  | Level 24 | WIR - 0762 | Electrical Rm, slab | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 6 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
55 | Sheet 61875 |  | Level 24 | WIR - 0762 | Electrical Rm, slab | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
56 | Sheet 61875 |  | Level 24 | WIR - 0762 | Electrical Rm, slab | opening Mortar |  |  |  | 0.25 | 1.63 | 0.4075 | 0.3175 | 1 | 680 | 1 | 215.9 | FR 230 |  | Hotel | 0.3175 | PC 01 discrepancies
57 | Sheet 61875 |  | Level 25 | WIR - 0763 | Electrical Rm, slab | busbar | 0.05 | 0.06 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
58 | Sheet 61875 |  | Level 25 | WIR - 0763 | Electrical Rm, slab | cable tray | 0.05 | 0.5 | 0.025 |  |  |  |  | 1 |  | 1 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
59 | Sheet 61875 |  | Level 25 | WIR - 0763 | Electrical Rm, slab | opening Mortar |  |  |  | 0.5 | 2.4 | 1.2 | 1.155 | 1 | 680 | 1 | 785.4 | FR 230 |  | Hotel | 1.155 | PC 01 discrepancies
60 | Sheet 61875 |  | Level 25 | WIR - 0763 | Electrical Rm, slab | cable tray | 0.05 | 0.2 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
61 | Sheet 61875 |  | Level 25 | WIR - 0763 | Electrical Rm, slab | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 6 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
62 | Sheet 61875 |  | Level 25 | WIR - 0763 | Electrical Rm, slab | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
63 | Sheet 61875 |  | Level 25 | WIR - 0763 | Electrical Rm, slab | opening Mortar |  |  |  | 0.25 | 1.63 | 0.4075 | 0.3175 | 1 | 680 | 1 | 215.9 | FR 230 |  | Hotel | 0.3175 | PC 01 discrepancies
64 | Sheet 61875 |  | Level 26 | WIR - 0764 | Electrical Rm, slab | busbar | 0.05 | 0.06 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
65 | Sheet 61875 |  | Level 26 | WIR - 0764 | Electrical Rm, slab | cable tray | 0.05 | 0.5 | 0.025 |  |  |  |  | 1 |  | 1 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
66 | Sheet 61875 |  | Level 26 | WIR - 0764 | Electrical Rm, slab | opening Mortar |  |  |  | 0.5 | 2.4 | 1.2 | 1.155 | 1 | 680 | 1 | 785.4 | FR 230 |  | Hotel | 1.155 | PC 01 discrepancies
67 | Sheet 61875 |  | Level 26 | WIR - 0764 | Electrical Rm, slab | cable tray | 0.05 | 0.2 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
68 | Sheet 61875 |  | Level 26 | WIR - 0764 | Electrical Rm, slab | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 6 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
69 | Sheet 61875 |  | Level 26 | WIR - 0764 | Electrical Rm, slab | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
70 | Sheet 61875 |  | Level 26 | WIR - 0764 | Electrical Rm, slab | opening Mortar |  |  |  | 0.25 | 1.63 | 0.4075 | 0.3175 | 1 | 680 | 1 | 215.9 | FR 230 |  | Hotel | 0.3175 | PC 01 discrepancies
71 | Sheet 61875 |  | Level 27 | WIR - 0765 | Electrical Rm, slab | busbar | 0.05 | 0.06 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
72 | Sheet 61875 |  | Level 27 | WIR - 0765 | Electrical Rm, slab | cable tray | 0.05 | 0.5 | 0.025 |  |  |  |  | 1 |  | 1 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
73 | Sheet 61875 |  | Level 27 | WIR - 0765 | Electrical Rm, slab | opening Mortar |  |  |  | 0.5 | 2.4 | 1.2 | 1.155 | 1 | 680 | 1 | 785.4 | FR 230 |  | Hotel | 1.155 | PC 01 discrepancies
74 | Sheet 61875 |  | Level 27 | WIR - 0765 | Electrical Rm, slab | cable tray | 0.05 | 0.2 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
75 | Sheet 61875 |  | Level 27 | WIR - 0765 | Electrical Rm, slab | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 6 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
76 | Sheet 61875 |  | Level 27 | WIR - 0765 | Electrical Rm, slab | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
77 | Sheet 61875 |  | Level 27 | WIR - 0765 | Electrical Rm, slab | opening Mortar |  |  |  | 0.25 | 1.63 | 0.4075 | 0.3175 | 1 | 680 | 1 | 215.9 | FR 230 |  | Hotel | 0.3175 | PC 01 discrepancies
78 | Sheet 61876 |  | Level 28 | WIR - 0766 | Electrical Rm, slab | busbar | 0.05 | 0.06 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
79 | Sheet 61876 |  | Level 28 | WIR - 0766 | Electrical Rm, slab | cable tray | 0.05 | 0.5 | 0.025 |  |  |  |  | 1 |  | 1 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
80 | Sheet 61876 |  | Level 28 | WIR - 0766 | Electrical Rm, slab | opening Mortar |  |  |  | 0.5 | 2.4 | 1.2 | 1.155 | 1 | 680 | 1 | 785.4 | FR 230 |  | Hotel | 1.155 | PC 01 discrepancies
81 | Sheet 61876 |  | Level 28 | WIR - 0766 | Electrical Rm, slab | cable tray | 0.05 | 0.2 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
82 | Sheet 61876 |  | Level 28 | WIR - 0766 | Electrical Rm, slab | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 6 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
83 | Sheet 61876 |  | Level 28 | WIR - 0766 | Electrical Rm, slab | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
84 | Sheet 61876 |  | Level 28 | WIR - 0766 | Electrical Rm, slab | opening Mortar |  |  |  | 0.25 | 1.63 | 0.4075 | 0.3175 | 1 | 680 | 1 | 215.9 | FR 230 |  | Hotel | 0.3175 | PC 01 discrepancies
85 | Sheet 61876 |  | Level 29 | WIR - 0767 | Electrical Rm, slab | busbar | 0.05 | 0.06 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
86 | Sheet 61876 |  | Level 29 | WIR - 0767 | Electrical Rm, slab | opening Mortar |  |  |  | 0.5 | 1.4 | 0.7 | 0.68 | 1 | 680 | 1 | 462.4 | FR 230 |  | Hotel | 0.68 | PC 01 discrepancies | [7 empty] | 12773.8
87 | Sheet 61876 |  | Level 29 | WIR - 0767 | Electrical Rm, slab | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 1 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
88 | Sheet 61876 |  | Level 29 | WIR - 0767 | Electrical Rm, slab | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 5 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
89 | Sheet 61876 |  | Level 29 | WIR - 0767 | Electrical Rm, slab | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR 230 |  | Hotel |  | PC 01 discrepancies
90 | Sheet 61876 |  | Level 29 | WIR - 0767 | Electrical Rm, slab | opening Mortar |  |  |  | 0.4 | 1.5 | 0.6 | 0.525 | 1 | 680 | 1 | 357 | FR 230 |  | Hotel | 0.525 | PC 01 discrepancies
[20 empty] | Hotel |  | PC 01 discrepancies
August 2022 - Hotel | [19 empty] | Hotel |  | PC 01 discrepancies
1 | Sheet 61879 |  | Level 27 | WIR - 0786 | Housekeeping | cable tray | 0.05 | 0.2 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FB 750 |  | Hotel |  | PC 01 discrepancies
2 | Sheet 61879 |  | Level 27 | WIR - 0786 | Housekeeping | cable tray | 0.05 | 0.1 | 0.005 |  |  |  |  | 2 |  | 1 | 0 | FB 750 |  | Hotel |  | PC 01 discrepancies
3 | Sheet 61879 |  | Level 27 | WIR - 0786 | Housekeeping | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 2 |  | 4 | 0 | FB 750 |  | Hotel |  | PC 01 discrepancies
4 | Sheet 61879 |  | Level 27 | WIR - 0786 | Housekeeping | fire fighting pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 | FB 750 |  | Hotel |  | PC 01 discrepancies
5 | Sheet 61879 |  | Level 27 | WIR - 0786 | Housekeeping | CDP pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 | FB 750 |  | Hotel |  | PC 01 discrepancies
6 | Sheet 61879 |  | Level 27 | WIR - 0786 | Housekeeping | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 5 | 0 | FB 750 |  | Hotel |  | PC 01 discrepancies
7 | Sheet 61879 |  | Level 27 | WIR - 0786 | Housekeeping | opening |  |  |  | 0.6 | 0.9 | 0.54 | 0.47862 | 2 | 310 | 1 | 620 | FB 750 |  | Hotel | 2 | PC 01 discrepancies
8 | Sheet 61879 |  | Level 27 | WIR - 0786 | Housekeeping | CHW pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 2 | 0 | FB 750 |  | Hotel |  | PC 01 discrepancies
9 | Sheet 61879 |  | Level 27 | WIR - 0786 | Housekeeping | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 2 | 0 | FB 750 |  | Hotel |  | PC 01 discrepancies
10 | Sheet 61879 |  | Level 27 | WIR - 0786 | Housekeeping | opening |  |  |  | 0.3 | 0.4 | 0.12 | 0.11509 | 2 | 150 | 1 | 300 | FB 750 |  | Hotel | 2 | PC 01 discrepancies
11 | Sheet 61879 |  | Level 27 | WIR - 0786 | Staircase | fire fighting pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 1 | 0 | FB 750 |  | Hotel |  | PC 01 discrepancies
12 | Sheet 61879 |  | Level 27 | WIR - 0786 | Staircase | opening |  |  |  | 0.3 | 0.3 | 0.09 | 0.085584 | 2 | 95 | 1 | 190 | FB 750 |  | Hotel | 2 | PC 01 discrepancies
13 | Sheet 61879 |  | Level 27 | WIR - 0786 | Lift Lobby | CHW pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 2 | 0 | FB 750 |  | Hotel |  | PC 01 discrepancies
14 | Sheet 61879 |  | Level 27 | WIR - 0786 | Lift Lobby | CDP pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 4 | 0 | FB 750 |  | Hotel |  | PC 01 discrepancies
15 | Sheet 61879 |  | Level 27 | WIR - 0786 | Lift Lobby | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 13 | 0 | FB 750 |  | Hotel |  | PC 01 discrepancies
16 | Sheet 61879 |  | Level 27 | WIR - 0786 | Lift Lobby | opening |  |  |  | 0.2 | 0.5 | 0.1 | 0.081847 | 2 | 95 | 1 | 190 | FB 750 |  | Hotel | 2 | PC 01 discrepancies
17 | Sheet 61879 |  | Level 27 | WIR - 0786 | Lift Lobby | fire fighting pipe | 1" |  |  | 3" |  |  |  | 2 |  | 1 | 0 | FB 750 |  | Hotel |  | PC 01 discrepancies
18 | Sheet 61879 |  | Level 27 | WIR - 0786 | Water Meter Room | PPR pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 1 | 0 | FB 750 |  | Hotel |  | PC 01 discrepancies
19 | Sheet 61879 |  | Level 27 | WIR - 0786 | Water Meter Room | PPR pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 1 | 0 | FB 750 |  | Hotel |  | PC 01 discrepancies
20 | Sheet 61879 |  | Level 27 | WIR - 0786 | Water Meter Room | PPR pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 1 | 0 | FB 750 |  | Hotel |  | PC 01 discrepancies
21 | Sheet 61879 |  | Level 27 | WIR - 0786 | Water Meter Room | opening |  |  |  | 0.3 | 0.6 | 0.18 | 0.15007 | 2 | 150 | 1 | 300 | FB 750 |  | Hotel | 2 | PC 01 discrepancies
22 | Sheet 61879 |  | Level 27 | WIR - 0786 | Lobby | PVC pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 1 | 0 | FB 750 |  | Hotel |  | PC 01 discrepancies
23 | Sheet 61879 |  | Level 27 | WIR - 0786 | Lobby | opening |  |  |  | 0.3 | 0.3 | 0.09 | 0.072337 | 2 | 95 | 1 | 190 | FB 750 |  | Hotel | 2 | PC 01 discrepancies
24 | Sheet 61879 |  | Level 27 | WIR - 0786 | Lobby | fire fighting pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 1 | 0 | FB 750 |  | Hotel |  | PC 01 discrepancies
25 | Sheet 61879 |  | Level 27 | WIR - 0786 | Lobby | CHW pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 2 | 0 | FB 750 |  | Hotel |  | PC 01 discrepancies
26 | Sheet 61879 |  | Level 27 | WIR - 0786 | Lobby | CDP pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 | FB 750 |  | Hotel |  | PC 01 discrepancies
27 | Sheet 61879 |  | Level 27 | WIR - 0786 | Lobby | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 10 | 0 | FB 750 |  | Hotel |  | PC 01 discrepancies
28 | Sheet 61879 |  | Level 27 | WIR - 0786 | Lobby | opening |  |  |  | 0.4 | 0.6 | 0.24 | 0.21154 | 2 | 180 | 1 | 360 | FB 750 |  | Hotel | 2 | PC 01 discrepancies
29 | Sheet 61880 |  | Level 27 | WIR - 0786 | Service Lobby | fire fighting pipe | 1" |  |  | 3" |  |  |  | 2 |  | 1 | 0 |  |  | Hotel |  | PC 01 discrepancies
30 | Sheet 61880 |  | Level 27 | WIR - 0786 | Service Lobby | conduit pipe | 1" |  |  | 2" |  |  |  | 2 |  | 2 | 0 |  |  | Hotel |  | PC 01 discrepancies
31 | Sheet 61880 |  | Level 27 | WIR - 0786 | Service Lobby | fire fighting pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 1 | 0 |  |  | Hotel |  | PC 01 discrepancies
32 | Sheet 61880 |  | Level 27 | WIR - 0786 | Service Lobby | opening |  |  |  | 0.3 | 0.3 | 0.09 | 0.08215 | 2 | 95 | 1 | 190 |  |  | Hotel | 2 | PC 01 discrepancies
33 | Sheet 61884 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PPR pipe | 3" |  |  | 5" |  |  |  | 1 | 30 | 3 | 90 | FS702/FB750/FP302 |  | Hotel | 3 | PC 01 discrepancies
34 | Sheet 61884 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | fire fighting pipe | 2" |  |  | 4" |  |  |  | 1 | 14 | 1 | 14 | FS702/FB750 |  | Hotel | 1 | PC 01 discrepancies
35 | Sheet 61884 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | fire fighting pipe | 3" |  |  | 5" |  |  |  | 1 | 16 | 1 | 16 | FS702/FB750 |  | Hotel | 1 | PC 01 discrepancies
36 | Sheet 61884 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PVC pipe | 6" |  |  | 8" |  |  |  | 1 | 125 | 1 | 125 | FS702/FB750/FP302 |  | Hotel | 1 | PC 01 discrepancies
37 | Sheet 61884 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PVC pipe | 5" |  |  | 7" |  |  |  | 1 | 125 | 1 | 125 | FS702/FB750/FP302 |  | Hotel | 1 | PC 01 discrepancies
38 | Sheet 61884 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PVC pipe | 6" |  |  | 8" |  |  |  | 1 | 125 | 1 | 125 | FS702/FB750/FP302 |  | Hotel | 1 | PC 01 discrepancies
39 | Sheet 61884 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PPR pipe | 3" |  |  | 5" |  |  |  | 1 | 30 | 3 | 90 | FS702/FB750/FP302 |  | Hotel | 3 | PC 01 discrepancies
40 | Sheet 61884 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | fire fighting pipe | 3" |  |  | 5" |  |  |  | 1 | 16 | 1 | 16 | FS702/FB750 |  | Hotel | 1 | PC 01 discrepancies
41 | Sheet 61884 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PPR pipe | 3" |  |  | 5" |  |  |  | 1 | 30 | 3 | 90 | FS702/FB750/FP302 |  | Hotel | 3 | PC 01 discrepancies
42 | Sheet 61884 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | fire fighting pipe | 3" |  |  | 5" |  |  |  | 1 | 16 | 1 | 16 | FS702/FB750 |  | Hotel | 1 | PC 01 discrepancies
43 | Sheet 61884 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | CHW pipe | 3" |  |  | 5" |  |  |  | 1 | 23 | 2 | 46 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
44 | Sheet 61884 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PVC pipe | 6" |  |  | 8" |  |  |  | 1 | 125 | 1 | 125 | FS702/FB750/FP302 |  | Hotel | 1 | PC 01 discrepancies
45 | Sheet 61884 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PVC pipe | 4" |  |  | 6" |  |  |  | 1 | 65 | 1 | 65 | FS702/FB750/FP302 |  | Hotel | 1 | PC 01 discrepancies
46 | Sheet 61884 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | CHW pipe | 3" |  |  | 5" |  |  |  | 1 | 23 | 2 | 46 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
47 | Sheet 61884 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 |  | 1 | 46 | 1 | 46 | FS702/FB750 |  | Hotel | 1 | PC 01 discrepancies
48 | Sheet 61884 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | CHW pipe | 3" |  |  | 5" |  |  |  | 1 | 23 | 2 | 46 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
49 | Sheet 61884 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | fire fighting pipe | 3" |  |  | 5" |  |  |  | 1 | 16 | 1 | 16 | FS702/FB750 |  | Hotel | 1 | PC 01 discrepancies
50 | Sheet 61884 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PPR pipe | 3" |  |  | 5" |  |  |  | 1 | 30 | 3 | 90 | FS702/FB750/FP302 |  | Hotel | 3 | PC 01 discrepancies
51 | Sheet 61884 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | CHW pipe | 3" |  |  | 5" |  |  |  | 1 | 23 | 2 | 46 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
52 | Sheet 61884 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PVC pipe | 6" |  |  | 8" |  |  |  | 1 | 125 | 1 | 125 | FS702/FB750/FP302 |  | Hotel | 1 | PC 01 discrepancies
53 | Sheet 61884 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PPR pipe | 3" |  |  | 5" |  |  |  | 1 | 30 | 3 | 90 | FS702/FB750/FP302 |  | Hotel | 3 | PC 01 discrepancies
54 | Sheet 61884 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | CHW pipe | 3" |  |  | 5" |  |  |  | 1 | 23 | 2 | 46 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
55 | Sheet 61884 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | fire fighting pipe | 3" |  |  | 5" |  |  |  | 1 | 16 | 1 | 16 | FS702/FB750 |  | Hotel | 1 | PC 01 discrepancies
56 | Sheet 61884 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | fire fighting pipe | 3" |  |  | 5" |  |  |  | 1 | 16 | 1 | 16 | FS702/FB750 |  | Hotel | 1 | PC 01 discrepancies
57 | Sheet 61884 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PPR pipe | 3" |  |  | 5" |  |  |  | 1 | 30 | 3 | 90 | FS702/FB750/FP302 |  | Hotel | 3 | PC 01 discrepancies
58 | Sheet 61884 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | fire fighting pipe | 3" |  |  | 5" |  |  |  | 1 | 16 | 1 | 16 | FS702/FB750 |  | Hotel | 1 | PC 01 discrepancies
59 | Sheet 61884 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | CHW pipe | 3" |  |  | 5" |  |  |  | 1 | 23 | 2 | 46 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
60 | Sheet 61885 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PVC pipe | 6" |  |  | 8" |  |  |  | 1 | 125 | 1 | 125 | FS702/FB750/FP302 |  | Hotel | 1 | PC 01 discrepancies
61 | Sheet 61885 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | CHW pipe | 3" |  |  | 5" |  |  |  | 1 | 23 | 2 | 46 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
62 | Sheet 61885 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | CHW pipe | 3" |  |  | 5" |  |  |  | 1 | 23 | 2 | 46 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
63 | Sheet 61885 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PPR pipe | 3" |  |  | 5" |  |  |  | 1 | 30 | 3 | 90 | FS702/FB750/FP302 |  | Hotel | 3 | PC 01 discrepancies
64 | Sheet 61885 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | fire fighting pipe | 3" |  |  | 5" |  |  |  | 1 | 16 | 1 | 16 | FS702/FB750 |  | Hotel | 1 | PC 01 discrepancies
65 | Sheet 61885 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | fire fighting pipe | 3" |  |  | 5" |  |  |  | 1 | 16 | 1 | 16 | FS702/FB750 |  | Hotel | 1 | PC 01 discrepancies
66 | Sheet 61885 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PVC pipe | 6" |  |  | 8" |  |  |  | 1 | 125 | 1 | 125 | FS702/FB750/FP302 |  | Hotel | 1 | PC 01 discrepancies
67 | Sheet 61885 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PPR pipe | 3" |  |  | 5" |  |  |  | 1 | 30 | 3 | 90 | FS702/FB750/FP302 |  | Hotel | 3 | PC 01 discrepancies
68 | Sheet 61885 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | fire fighting pipe | 3" |  |  | 5" |  |  |  | 1 | 16 | 1 | 16 | FS702/FB750 |  | Hotel | 1 | PC 01 discrepancies
69 | Sheet 61885 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | fire fighting pipe | 3" |  |  | 5" |  |  |  | 1 | 16 | 1 | 16 | FS702/FB750 |  | Hotel | 1 | PC 01 discrepancies
70 | Sheet 61885 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 |  | 2 | 46 | 1 | 92 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
71 | Sheet 61885 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | duct | 0.3 | 0.3 | 0.09 | 0.35 | 0.35 | 0.1225 |  | 1 | 51 | 1 | 51 | FS702/FB750 |  | Hotel | 1 | PC 01 discrepancies
72 | Sheet 61885 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PPR pipe | 3" |  |  | 5" |  |  |  | 2 | 30 | 3 | 180 | FS702/FB750/FP302 |  | Hotel | 6 | PC 01 discrepancies
73 | Sheet 61885 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PVC pipe | 8" |  |  | 10" |  |  |  | 2 | 250 | 1 | 500 | FS702/FB750/FP302 |  | Hotel | 2 | PC 01 discrepancies
74 | Sheet 61885 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | fire fighting pipe | 3" |  |  | 5" |  |  |  | 2 | 16 | 1 | 32 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
75 | Sheet 61885 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PVC pipe | 6" |  |  | 8" |  |  |  | 1 | 125 | 1 | 125 | FS702/FB750/FP302 |  | Hotel | 1 | PC 01 discrepancies
76 | Sheet 61885 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | fire fighting pipe | 3" |  |  | 5" |  |  |  | 1 | 16 | 1 | 16 | FS702/FB750 |  | Hotel | 1 | PC 01 discrepancies
77 | Sheet 61885 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PVC pipe | 6" |  |  | 8" |  |  |  | 1 | 125 | 1 | 125 | FS702/FB750/FP302 |  | Hotel | 1 | PC 01 discrepancies
78 | Sheet 61885 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PVC pipe | 6" |  |  | 8" |  |  |  | 1 | 125 | 1 | 125 | FS702/FB750/FP302 |  | Hotel | 1 | PC 01 discrepancies
79 | Sheet 61885 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PPR pipe | 3" |  |  | 5" |  |  |  | 1 | 30 | 3 | 90 | FS702/FB750/FP302 |  | Hotel | 3 | PC 01 discrepancies
80 | Sheet 61885 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | fire fighting pipe | 3" |  |  | 5" |  |  |  | 1 | 16 | 1 | 16 | FS702/FB750 |  | Hotel | 1 | PC 01 discrepancies
81 | Sheet 61885 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PPR pipe | 3" |  |  | 5" |  |  |  | 1 | 30 | 3 | 90 | FS702/FB750/FP302 |  | Hotel | 3 | PC 01 discrepancies
82 | Sheet 61885 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | CHW pipe | 3" |  |  | 5" |  |  |  | 1 | 23 | 2 | 46 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
83 | Sheet 61885 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | fire fighting pipe | 3" |  |  | 5" |  |  |  | 1 | 16 | 1 | 16 | FS702/FB750 |  | Hotel | 1 | PC 01 discrepancies
84 | Sheet 61885 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PVC pipe | 5" |  |  | 7" |  |  |  | 1 | 125 | 1 | 125 | FS702/FB750/FP302 |  | Hotel | 1 | PC 01 discrepancies
85 | Sheet 61886 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | CHW pipe | 3" |  |  | 5" |  |  |  | 1 | 23 | 2 | 46 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
86 | Sheet 61886 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PVC pipe | 6" |  |  | 8" |  |  |  | 1 | 125 | 1 | 125 | FS702/FB750/FP302 |  | Hotel | 1 | PC 01 discrepancies
87 | Sheet 61886 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PVC pipe | 8" |  |  | 10" |  |  |  | 1 | 250 | 1 | 250 | FS702/FB750/FP302 |  | Hotel | 1 | PC 01 discrepancies
88 | Sheet 61886 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PVC pipe | 5" |  |  | 7" |  |  |  | 1 | 125 | 1 | 125 | FS702/FB750/FP302 |  | Hotel | 1 | PC 01 discrepancies
89 | Sheet 61886 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PPR pipe | 3" |  |  | 5" |  |  |  | 1 | 30 | 3 | 90 | FS702/FB750/FP302 |  | Hotel | 3 | PC 01 discrepancies
90 | Sheet 61886 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | CHW pipe | 3" |  |  | 5" |  |  |  | 1 | 23 | 2 | 46 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
91 | Sheet 61886 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PPR pipe | 3" |  |  | 5" |  |  |  | 1 | 30 | 3 | 90 | FS702/FB750/FP302 |  | Hotel | 3 | PC 01 discrepancies
92 | Sheet 61886 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | fire fighting pipe | 3" |  |  | 5" |  |  |  | 1 | 16 | 1 | 16 | FS702/FB750 |  | Hotel | 1 | PC 01 discrepancies
93 | Sheet 61886 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | CHW pipe | 3" |  |  | 5" |  |  |  | 1 | 23 | 2 | 46 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
94 | Sheet 61886 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | CDP pipe | 3" |  |  | 5" |  |  |  | 1 | 30 | 1 | 30 | FS702/FB750/FP302 |  | Hotel | 1 | PC 01 discrepancies
95 | Sheet 61886 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | CHW pipe | 3" |  |  | 5" |  |  |  | 1 | 23 | 2 | 46 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
96 | Sheet 61886 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PVC pipe | 6" |  |  | 8" |  |  |  | 1 | 125 | 1 | 125 | FS702/FB750/FP302 |  | Hotel | 1 | PC 01 discrepancies
97 | Sheet 61886 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | CHW pipe | 3" |  |  | 5" |  |  |  | 1 | 23 | 2 | 46 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
98 | Sheet 61886 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | CDP pipe | 3" |  |  | 5" |  |  |  | 1 | 30 | 1 | 30 | FS702/FB750/FP302 |  | Hotel | 1 | PC 01 discrepancies
99 | Sheet 61886 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PPR pipe | 3" |  |  | 5" |  |  |  | 1 | 30 | 3 | 90 | FS702/FB750/FP302 |  | Hotel | 3 | PC 01 discrepancies
100 | Sheet 61886 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | fire fighting pipe | 2" |  |  | 4" |  |  |  | 1 | 14 | 1 | 14 | FS702/FB750 |  | Hotel | 1 | PC 01 discrepancies
101 | Sheet 61886 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PPR pipe | 3" |  |  | 5" |  |  |  | 1 | 30 | 3 | 90 | FS702/FB750/FP302 |  | Hotel | 3 | PC 01 discrepancies
102 | Sheet 61886 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | CHW pipe | 3" |  |  | 5" |  |  |  | 1 | 23 | 2 | 46 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
103 | Sheet 61886 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | fire fighting pipe | 2" |  |  | 4" |  |  |  | 1 | 14 | 1 | 14 | FS702/FB750 |  | Hotel | 1 | PC 01 discrepancies
104 | Sheet 61886 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | CHW pipe | 3" |  |  | 5" |  |  |  | 1 | 23 | 2 | 46 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
105 | Sheet 61886 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 |  | 1 | 46 | 1 | 46 | FS702/FB750 |  | Hotel | 1 | PC 01 discrepancies
106 | Sheet 61886 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PVC pipe | 6" |  |  | 8" |  |  |  | 1 | 125 | 1 | 125 | FS702/FB750/FP302 |  | Hotel | 1 | PC 01 discrepancies
107 | Sheet 61886 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PVC pipe | 5" |  |  | 7" |  |  |  | 1 | 125 | 1 | 125 | FS702/FB750/FP302 |  | Hotel | 1 | PC 01 discrepancies
108 | Sheet 61886 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PVC pipe | 5" |  |  | 7" |  |  |  | 1 | 125 | 1 | 125 | FS702/FB750/FP302 |  | Hotel | 1 | PC 01 discrepancies
109 | Sheet 61886 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | CHW pipe | 3" |  |  | 5" |  |  |  | 1 | 23 | 2 | 46 | FS702/FB750 |  | Hotel | 2 | PC 01 discrepancies
110 | Sheet 61886 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | PPR pipe | 3" |  |  | 5" |  |  |  | 1 | 30 | 3 | 90 | FS702/FB750/FP302 |  | Hotel | 3 | PC 01 discrepancies
111 | Sheet 61886 |  | Level 27 | MEP-AX-WR-L27-00786 | Outer sleeve | fire fighting pipe | 2" |  |  | 4" |  |  |  | 1 | 14 | 1 | 14 | FS702/FB750 |  | Hotel | 1 | PC 01 discrepancies
October 2022 - Hotel | [19 empty] | Hotel
1 | Sheet 61920 | 1 | Level 01 | WIR - 01191 | Plant Room | PVC pipe | 4" |  |  | 6" |  |  |  | 1 |  | 6 | 0 | FS702/FP302 | Sheet 61920 | Hotel | 6
2 | Sheet 61920 | 2 | Level 01 | WIR - 01191 | Plant Room | CHW pipe | 3" |  |  | 5" |  |  |  | 1 |  | 2 | 0 | FS709 |  | Hotel | 2
3 | Sheet 61920 | 3 | Level 01 | WIR - 01191 | Plant Room | fire fighting pipe | 3" |  |  | 5" |  |  |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
4 | Sheet 61920 | 4 | Level 01 | WIR - 01191 | Plant Room | PPR pipe | 2" |  |  | 4" |  |  |  | 1 |  | 2 | 0 | FS702/FP302 |  | Hotel | 2
5 | Sheet 61920 | 5 | Level 01 | WIR - 01191 | Plant Room | duct | 0.2 | 0.2 | 0.04 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
6 | Sheet 61920 | 5 | Level 01 | WIR - 01191 | Plant Room | opening |  |  |  | 0.4 | 0.4 | 0.16 | 0.12 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
7 | Sheet 61920 | 6 | Level 01 | WIR - 01191 | Plant Room | PVC pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
8 | Sheet 61920 | 7 | Level 01 | WIR - 01191 | Plant Room | CHW pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Hotel | 4
9 | Sheet 61920 | 5 | Level 01 | WIR - 01191 | Plant Room | opening |  |  |  | 0.3 | 0.5 | 0.15 | 0.14117 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
Hotel
October 2022 - Hotel | [19 empty] | Hotel
1 | Sheet 61918 | 1 | Ground Level | WIR - 01192 | Ball Room | cable trunking |  |  |  | 0.08 | 0.08 | 0.0064 |  | 1 |  | 1 | 0 | FS702/FB750 | Sheet 61918 | Hotel | 1
2 | Sheet 61918 | 2 | Ground Level | WIR - 01192 | Ball Room | duct | 0.9 | 0.9 | 0.81 | 0.96 | 0.96 | 0.9216 |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
3 | Sheet 61918 | 3 | Ground Level | WIR - 01192 | Ball Room | duct | 0.8 | 0.8 | 0.64 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
4 | Sheet 61918 | 3 | Ground Level | WIR - 01192 | Ball Room | opening |  |  |  | 0.86 | 0.95 | 0.817 | 0.177 | 1 | 180 | 1 | 180 | FS702/FB750 |  | Hotel | 1
5 | Sheet 61918 | 4 | Ground Level | WIR - 01192 | Ball Room | duct | 0.3 | 0.8 | 0.24 | 0.36 | 0.86 | 0.3096 |  | 1 |  | 2 | 0 | FS702 |  | Hotel | 2
6 | Sheet 61918 | 5 | Ground Level | WIR - 01192 | Ball Room | PVC pipe | 2" |  |  | 4" |  |  |  | 1 |  | 1 | 0 | FS702/FP302 |  | Hotel | 1
7 | Sheet 61918 | 6 | Ground Level | WIR - 01192 | Ball Room | PVC pipe | 4" |  |  | 6" |  |  |  | 1 |  | 1 | 0 | FS702/FP302 |  | Hotel | 1
8 | Sheet 61918 | 7 | Ground Level | WIR - 01192 | Ball Room | conduit pipe | 1" |  |  | 2" |  |  |  | 1 |  | 2 | 0 | FS709 |  | Hotel | 2
9 | Sheet 61918 | 8 | Ground Level | WIR - 01192 | Ball Room | duct | 0.4 | 0.85 | 0.34 | 0.46 | 0.9 | 0.414 |  | 1 |  | 5 | 0 | FS702 |  | Hotel | 5
10 | Sheet 61918 | 9 | Ground Level | WIR - 01192 | Ball Room | PVC pipe | 4" |  |  | 6" |  |  |  | 1 |  | 9 | 0 | FS702/FP302 |  | Hotel | 9
11 | Sheet 61918 | 10 | Ground Level | WIR - 01192 | Ball Room | PVC pipe | 6" |  |  | 8" |  |  |  | 1 |  | 2 | 0 | FS702/FP302 |  | Hotel | 2
12 | Sheet 61918 | 11 | Ground Level | WIR - 01192 | Ball Room | PVC pipe | 2" |  |  | 4" |  |  |  | 1 |  | 2 | 0 | FS702/FP302 |  | Hotel | 2
13 | Sheet 61918 | 12 | Ground Level | WIR - 01192 | Ball Room | conduit pipe | 1" |  |  | 2" |  |  |  | 1 |  | 3 | 0 | FS709 |  | Hotel | 3
14 | Sheet 61918 | 13 | Ground Level | WIR - 01192 | Ball Room | cable tray | 0.05 | 0.2 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
15 | Sheet 61918 | 14 | Ground Level | WIR - 01192 | Ball Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FS702/FB750 |  | Hotel | 2
16 | Sheet 61918 | 14 | Ground Level | WIR - 01192 | Ball Room | opening |  |  |  | 0.2 | 0.5 | 0.1 | 0.07 | 1 | 95 | 1 | 95 | FS702/FB750 |  | Hotel | 1
17 | Sheet 61918 | 15 | Ground Level | WIR - 01192 | Ball Room | PVC pipe | 6" |  | 0.017662 |  |  |  |  | 1 |  | 1 | 0 | FS702/FP302/FB750 |  | Hotel | 1
18 | Sheet 61918 | 16 | Ground Level | WIR - 01192 | Ball Room | opening |  |  |  | 0.4 | 0.4 | 0.16 | 0.14234 | 1 | 150 | 1 | 150 | FS702/FB750 |  | Hotel | 1
19 | Sheet 61918 | 17 | Ground Level | WIR - 01192 | Ball Room | PVC pipe | 4" |  |  | 6" |  |  |  | 1 |  | 9 | 0 | FS702/FP302 |  | Hotel | 9
20 | Sheet 61918 | 18 | Ground Level | WIR - 01192 | Ball Room | PVC pipe | 2" |  |  | 4" |  |  |  | 1 |  | 4 | 0 | FS702/FP302 |  | Hotel | 4
21 | Sheet 61918 | 19 | Ground Level | WIR - 01192 | Ball Room | CDP pipe | 2" |  |  | 4" |  |  |  | 1 |  | 1 | 0 | FS702/FP302 |  | Hotel | 1
22 | Sheet 61918 | 20 | Ground Level | WIR - 01192 | Ball Room | conduit pipe | 1" |  |  | 2" |  |  |  | 1 |  | 8 | 0 | FS709 |  | Hotel | 8
23 | Sheet 61918 | 21 | Ground Level | WIR - 01192 | Ball Room | fire fighting pipe | 6" |  |  | 8" |  |  |  | 1 |  | 2 | 0 | FS702 |  | Hotel | 2
24 | Sheet 61918 | 22 | Ground Level | WIR - 01192 | Ball Room | CHW pipe | 8" |  |  | 10" |  |  |  | 1 |  | 2 | 0 | FS709 |  | Hotel | 2
25 | Sheet 61918 | 23 | Ground Level | WIR - 01192 | Ball Room | PPR pipe | 3" |  |  | 5" |  |  |  | 1 |  | 3 | 0 | FS702/FP302 |  | Hotel | 3
26 | Sheet 61918 | 24 | Ground Level | WIR - 01192 | Ball Room | duct | 0.3 | 0.3 | 0.09 | 0.36 | 0.36 | 0.1296 |  | 1 |  | 2 | 0 | FS702 |  | Hotel | 2
27 | Sheet 61918 | 25 | Ground Level | WIR - 01192 | Ball Room | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 1 |  | 3 | 0 | FS702/FB750 |  | Hotel | 3
28 | Sheet 61918 | 26 | Ground Level | WIR - 01192 | Ball Room | cable tray | 0.05 | 0.4 | 0.02 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
29 | Sheet 61918 | 26 | Ground Level | WIR - 01192 | Ball Room | opening |  |  |  | 0.25 | 0.8 | 0.2 | 0.15 | 1 | 150 | 1 | 150 | FS702/FB750 |  | Hotel | 1
30 | Sheet 61918 | 27 | Ground Level | WIR - 01192 | Ball Room | cable tray |  |  |  | 0.1 | 0.3 | 0.03 |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
Hotel
October 2022 - Hotel | [19 empty] | Hotel
1 | Sheet 61919 | 27 | Ground Level | WIR - 01192 | Ball Room | PVC pipe | 2" |  |  | 4" |  |  |  | 1 |  | 1 | 0 | FS702/FP302 | Sheet 61919 | Hotel | 1
2 | Sheet 61919 | 28 | Ground Level | WIR - 01192 | Ball Room | PVC pipe | 3" |  |  | 5" |  |  |  | 1 |  | 1 | 0 | FS702/FP302 |  | Hotel | 1
3 | Sheet 61919 | 29 | Ground Level | WIR - 01192 | Ball Room | PVC pipe | 6" |  |  | 8" |  |  |  | 1 |  | 9 | 0 | FS702/FP302 |  | Hotel | 9
4 | Sheet 61919 | 30 | Ground Level | WIR - 01192 | Ball Room | PVC pipe | 4" |  |  | 6" |  |  |  | 1 |  | 2 | 0 | FS702/FP302 |  | Hotel | 2
5 | Sheet 61919 | 31 | Ground Level | WIR - 01192 | Ball Room | PVC pipe | 6" |  |  | 8" |  |  |  | 1 |  | 2 | 0 | FS702/FP302 |  | Hotel | 2
6 | Sheet 61919 | 32 | Ground Level | WIR - 01192 | Ball Room | fire fighting pipe | 1" |  |  | 2" |  |  |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
7 | Sheet 61919 | 33 | Ground Level | WIR - 01192 | Ball Room | duct | 0.3 | 0.5 | 0.15 | 0.36 | 0.56 | 0.2016 |  | 2 |  | 4 | 0 | FS702 |  | Hotel | 8
8 | Sheet 61919 | 34 | Ground Level | WIR - 01192 | Ball Room | conduit pipe | 1" |  |  | 2" |  |  |  | 1 |  | 4 | 0 | FS709 |  | Hotel | 4
9 | Sheet 61919 | 35 | Ground Level | WIR - 01192 | Ball Room | fire fighting pipe | 4" |  |  | 6" |  |  |  | 1 |  | 2 | 0 | FS702 |  | Hotel | 2
10 | Sheet 61919 | 36 | Ground Level | WIR - 01192 | Ball Room | duct | 0.65 | 1.15 | 0.7475 | 0.7 | 1.2 | 0.84 |  | 1 |  | 5 | 0 | FS702 |  | Hotel | 5
11 | Sheet 61919 | 37 | Ground Level | WIR - 01192 | Ball Room | CHW pipe | 8" |  |  | 10" |  |  |  | 1 |  | 2 | 0 | FS709 |  | Hotel | 2
12 | Sheet 61919 | 38 | Ground Level | WIR - 01192 | Ball Room | duct | 0.3 | 0.6 | 0.18 | 0.36 | 0.66 | 0.2376 |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
13 | Sheet 61919 | 39 | Ground Level | WIR - 01192 | Ball Room | duct | 0.3 | 0.5 | 0.15 | 0.36 | 0.56 | 0.2016 |  | 1 |  | 3 | 0 | FS702 |  | Hotel | 3
14 | Sheet 61919 | 40 | Ground Level | WIR - 01192 | Ball Room | cable trunking |  |  |  | 0.08 | 0.08 | 0.0064 |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
15 | Sheet 61919 | 41 | Ground Level | WIR - 01192 | Ball Room | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FS702/FB750 |  | Hotel | 2
16 | Sheet 61919 | 42 | Ground Level | WIR - 01192 | Ball Room | cable tray | 0.05 | 0.4 | 0.02 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
17 | Sheet 61919 | 42 | Ground Level | WIR - 01192 | Ball Room | opening |  |  |  | 0.25 | 0.7 | 0.175 | 0.135 | 1 | 150 | 1 | 150 | FS702/FB750 |  | Hotel | 1
18 | Sheet 61919 | 43 | Ground Level | WIR - 01192 | Ball Room | duct | 0.3 | 0.4 | 0.12 | 0.36 | 0.46 | 0.1656 |  | 1 |  | 3 | 0 | FS702 |  | Hotel | 3
19 | Sheet 61919 | 44 | Ground Level | WIR - 01192 | Ball Room | PPR pipe | 3" |  |  | 5" |  |  |  | 1 |  | 3 | 0 | FS702/FP302 |  | Hotel | 3
20 | Sheet 61919 | 45 | Ground Level | WIR - 01192 | Ball Room | duct | 0.3 | 0.9 | 0.27 | 0.36 | 0.96 | 0.3456 |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
21 | Sheet 61919 | 46 | Ground Level | WIR - 01192 | Ball Room | CHW pipe | 3" |  |  | 5" |  |  |  | 1 |  | 2 | 0 | FS709 |  | Hotel | 2
22 | Sheet 61919 | 47 | Ground Level | WIR - 01192 | Ball Room | duct | 0.3 | 1 | 0.3 | 0.36 | 1.06 | 0.3816 |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
23 | Sheet 61919 | 48 | Ground Level | WIR - 01192 | Ball Room | duct | 0.8 | 0.8 | 0.64 | 0.86 | 0.86 | 0.7396 |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
Residence
October 2022 - Residence | [19 empty] | Residence
1 | Sheet 61933 | 1 | Level 09 | MEP-AX-WR-L9-01416 | Staircase | PVC pipe | 4" |  |  | 6" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 | Sheet 61933 | Residence | 2
2 | Sheet 61933 | 2 | Level 09 | MEP-AX-WR-L9-01416 | Staircase | PVC pipe | 6" |  |  | 8" |  |  |  | 2 |  | 2 | 0 | FS702/FP302 |  | Residence | 4
3 | Sheet 61933 | 3 | Level 09 | MEP-AX-WR-L9-01416 | Corridor | PVC pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 2 | 0 | FS702/FP302/FB750 |  | Residence | 4
4 | Sheet 61933 | 3 | Level 09 | MEP-AX-WR-L9-01416 | Corridor | PVC pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 1 | 0 | FS702/FP302/FB750 |  | Residence | 2
5 | Sheet 61933 | 3 | Level 09 | MEP-AX-WR-L9-01416 | Corridor | opening |  |  |  | 0.3 | 0.6 | 0.18 | 0.13683 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Residence | 2
6 | Sheet 61933 | 4 | Level 09 | MEP-AX-WR-L9-01416 | Staircase | PPR pipe | 2" |  |  | 4" |  |  |  | 2 |  | 3 | 0 | FS702/FP302 |  | Residence | 6
7 | Sheet 61933 | 5 | Level 09 | MEP-AX-WR-L9-01416 | Staircase | CHW pipe | 3" |  |  | 5" |  |  |  | 2 |  | 2 | 0 | FS709 |  | Residence | 4
8 | Sheet 61933 | 6 | Level 09 | MEP-AX-WR-L9-01416 | Staircase | fire fighting pipe | 1.5" |  |  | 3" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Residence | 2
9 | Sheet 61933 | 7 | Level 09 | MEP-AX-WR-L9-01416 | High level | fire fighting pipe | 1.5" |  |  | 3" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Residence | 2
10 | Sheet 61933 | 8 | Level 09 | MEP-AX-WR-L9-01416 | High level | CHW pipe | 3" |  |  | 5" |  |  |  | 2 |  | 2 | 0 | FS709 |  | Residence | 4
11 | Sheet 61933 | 9 | Level 09 | MEP-AX-WR-L9-01416 | High level | PPR pipe | 2" |  |  | 4" |  |  |  | 2 |  | 3 | 0 | FS702/FP302 |  | Residence | 6
Hotel
October 2022 - Hotel | [19 empty] | Hotel
1 | Sheet 61926 | 1 | Level 22 | WIR - 01254 | Corridor MEP | PPR pipe | 3" |  |  | 5" |  |  |  | 1 |  | 3 | 0 | FS702/FP302 | Sheet 61926 | Hotel | 3
2 | Sheet 61926 | 2 | Level 22 | WIR - 01254 | Corridor MEP | fire fighting pipe | 2" |  |  | 4" |  |  |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
3 | Sheet 61926 | 3 | Level 22 | WIR - 01254 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  |  | 1 |  | 9 | 0 | FS709 |  | Hotel | 9
4 | Sheet 61926 | 4 | Level 22 | WIR - 01254 | Corridor MEP | cable pipe | 0.5" |  |  | 1.5" |  |  |  | 1 |  | 2 | 0 | FS709 |  | Hotel | 2
5 | Sheet 61926 | 5 | Level 22 | WIR - 01254 | Corridor MEP | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
6 | Sheet 61926 | 6 | Level 22 | WIR - 01254 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  |  | 1 |  | 3 | 0 | FS709 |  | Hotel | 3
7 | Sheet 61926 | 7 | Level 22 | WIR - 01254 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  |  | 1 |  | 2 | 0 | FS709 |  | Hotel | 2
8 | Sheet 61926 | 8 | Level 22 | WIR - 01254 | Corridor MEP | PPR pipe | 3" |  |  | 5" |  |  |  | 1 |  | 3 | 0 | FS702/FP302 |  | Hotel | 3
9 | Sheet 61926 | 9 | Level 22 | WIR - 01254 | Corridor MEP | fire fighting pipe | 2" |  |  | 4" |  |  |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
10 | Sheet 61926 | 10 | Level 22 | WIR - 01254 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  |  | 1 |  | 4 | 0 | FS709 |  | Hotel | 4
11 | Sheet 61926 | 11 | Level 22 | WIR - 01254 | Corridor MEP | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
12 | Sheet 61926 | 12 | Level 22 | WIR - 01254 | Corridor MEP | PPR pipe | 3" |  |  | 5" |  |  |  | 1 |  | 3 | 0 | FS702/FP302 |  | Hotel | 3
13 | Sheet 61926 | 13 | Level 22 | WIR - 01254 | Corridor MEP | CHW pipe | 2" |  |  | 4" |  |  |  | 1 |  | 2 | 0 | FS709 |  | Hotel | 2
14 | Sheet 61926 | 14 | Level 22 | WIR - 01254 | Corridor MEP | fire fighting pipe | 2" |  |  | 4" |  |  |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
15 | Sheet 61926 | 15 | Level 22 | WIR - 01254 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  |  | 1 |  | 6 | 0 | FS709 |  | Hotel | 6
16 | Sheet 61926 | 16 | Level 22 | WIR - 01254 | Corridor MEP | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
17 | Sheet 61926 | 17 | Level 22 | WIR - 01254 | Corridor MEP | CHW pipe | 2" |  |  | 4" |  |  |  | 1 |  | 2 | 0 | FS709 |  | Hotel | 2
18 | Sheet 61926 | 18 | Level 22 | WIR - 01254 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  |  | 1 |  | 2 | 0 | FS709 |  | Hotel | 2
19 | Sheet 61926 | 19 | Level 22 | WIR - 01254 | Corridor MEP | fire fighting pipe | 3" |  |  | 5" |  |  |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
20 | Sheet 61926 | 20 | Level 22 | WIR - 01254 | Corridor MEP | CHW pipe | 2" |  |  | 4" |  |  |  | 1 |  | 2 | 0 | FS709 |  | Hotel | 2
21 | Sheet 61926 | 21 | Level 22 | WIR - 01254 | Corridor MEP | PPR pipe | 3" |  |  | 5" |  |  |  | 1 |  | 3 | 0 | FS702/FP302 |  | Hotel | 3
22 | Sheet 61926 | 22 | Level 22 | WIR - 01254 | Corridor MEP | fire fighting pipe | 2" |  |  | 4" |  |  |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
23 | Sheet 61926 | 23 | Level 22 | WIR - 01254 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  |  | 1 |  | 4 | 0 | FS709 |  | Hotel | 4
24 | Sheet 61926 | 24 | Level 22 | WIR - 01254 | Entry door | PPR pipe | 3" |  |  | 5" |  |  |  | 2 |  | 3 | 0 | FS702/FP302 |  | Hotel | 6
25 | Sheet 61926 | 25 | Level 22 | WIR - 01254 | Entry door | conduit pipe | 1" |  |  | 2" |  |  |  | 2 |  | 9 | 0 | FS709 |  | Hotel | 18
26 | Sheet 61926 | 26 | Level 22 | WIR - 01254 | Entry door | fire fighting pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
27 | Sheet 61926 | 27 | Level 22 | WIR - 01254 | Entry door | duct | 0.3 | 0.3 | 0.09 | 0.36 | 0.36 | 0.1296 |  | 2 |  | 2 | 0 | FS702 |  | Hotel | 4
28 | Sheet 61926 | 28 | Level 22 | WIR - 01254 | Entry door | cable pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 4 | 0 | FS709 |  | Hotel | 8
Hotel
October 2022 - Hotel | [19 empty] | Hotel
1 | Sheet 61927 | 29 | Level 22 | WIR - 01254 | Corridor MEP | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 |  | 1 |  | 1 | 0 | FS702 | Sheet 61927 | Hotel | 1
2 | Sheet 61927 | 30 | Level 22 | WIR - 01254 | Corridor MEP | CHW pipe | 2" |  |  | 4" |  |  |  | 1 |  | 2 | 0 | FS709 |  | Hotel | 2
3 | Sheet 61927 | 31 | Level 22 | WIR - 01254 | Corridor MEP | CDP pipe | 2" |  |  | 4" |  |  |  | 1 |  | 1 | 0 | FS702/FP302 |  | Hotel | 1
4 | Sheet 61927 | 32 | Level 22 | WIR - 01254 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  |  | 1 |  | 7 | 0 | FS709 |  | Hotel | 7
5 | Sheet 61927 | 33 | Level 22 | WIR - 01254 | Corridor MEP | PPR pipe | 3" |  |  | 5" |  |  |  | 2 |  | 3 | 0 | FS702/FP302 |  | Hotel | 6
6 | Sheet 61927 | 34 | Level 22 | WIR - 01254 | Corridor MEP | fire fighting pipe | 1" |  |  | 2" |  |  |  | 2 |  | 3 | 0 | FS702 |  | Hotel | 6
7 | Sheet 61927 | 35 | Level 22 | WIR - 01254 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  |  | 2 |  | 9 | 0 | FS709 |  | Hotel | 18
8 | Sheet 61927 | 36 | Level 22 | WIR - 01254 | Corridor MEP | duct | 0.2 | 0.2 | 0.04 | 0.26 | 0.26 | 0.0676 |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
9 | Sheet 61927 | 37 | Level 22 | WIR - 01254 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  |  | 2 |  | 5 | 0 | FS709 |  | Hotel | 10
10 | Sheet 61927 | 38 | Level 22 | WIR - 01254 | Corridor MEP | fire fighting pipe | 3" |  |  | 5" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
11 | Sheet 61927 | 39 | Level 22 | WIR - 01254 | Corridor MEP | fire fighting pipe | 1" |  |  | 2" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
12 | Sheet 61927 | 40 | Level 22 | WIR - 01254 | Corridor MEP | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
13 | Sheet 61927 | 41 | Level 22 | WIR - 01254 | Housekeeping | cable tray | 0.05 | 0.1 | 0.005 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
14 | Sheet 61927 | 42 | Level 22 | WIR - 01254 | Housekeeping | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 2 |  | 3 | 0 | FS702/FB750 |  | Hotel | 6
15 | Sheet 61927 | 43 | Level 22 | WIR - 01254 | Housekeeping | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750 |  | Hotel | 4
16 | Sheet 61927 | 44 | Level 22 | WIR - 01254 | Housekeeping | fire fighting pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
17 | Sheet 61927 | 45 | Level 22 | WIR - 01254 | Housekeeping | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 4 | 0 | FS709/FB750 |  | Hotel | 8
18 | Sheet 61927 | 45 | Level 22 | WIR - 01254 | Housekeeping | opening |  |  |  | 0.6 | 0.9 | 0.54 | 0.48255 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Hotel | 2
19 | Sheet 61927 | 46 | Level 22 | WIR - 01254 | Housekeeping | CHW pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Hotel | 4
20 | Sheet 61927 | 47 | Level 22 | WIR - 01254 | Housekeeping | CDP pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 | FS702/FP302/FB750 |  | Hotel | 2
21 | Sheet 61927 | 47 | Level 22 | WIR - 01254 | Housekeeping | opening |  |  |  | 0.3 | 0.3 | 0.09 | 0.084112 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
22 | Sheet 61927 | 48 | Level 22 | WIR - 01254 | Staircase | fire fighting pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
23 | Sheet 61927 | 48 | Level 22 | WIR - 01254 | Staircase | opening |  |  |  | 0.3 | 0.3 | 0.09 | 0.085584 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
24 | Sheet 61927 | 49 | Level 22 | WIR - 01254 | Lobby | CHW pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Hotel | 4
25 | Sheet 61927 | 50 | Level 22 | WIR - 01254 | Lobby | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 10 | 0 | FS709/FB750 |  | Hotel | 20
26 | Sheet 61927 | 51 | Level 22 | WIR - 01254 | Lobby | opening |  |  |  | 0.2 | 0.6 | 0.12 | 0.11117 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
27 | Sheet 61927 | 51 | Level 22 | WIR - 01254 | Lobby | fire fighting pipe | 1" |  |  | 2" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
28 | Sheet 61927 | 52 | Level 22 | WIR - 01254 | Water M. Room | PPR pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 1 | 0 | FS702/FP302/FB750 |  | Hotel | 2
29 | Sheet 61927 | 53 | Level 22 | WIR - 01254 | Water M. Room | PPR pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 2 | 0 | FS702/FP302/FB750 |  | Hotel | 4
30 | Sheet 61927 | 54 | Level 22 | WIR - 01254 | Water M. Room | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Hotel | 4
31 | Sheet 61927 | 54 | Level 22 | WIR - 01254 | Water M. Room | opening |  |  |  | 0.3 | 0.8 | 0.24 | 0.22234 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2
Hotel
October 2022 - Hotel | [19 empty] | Hotel
1 | Sheet 61928 | 55 | Level 22 | WIR - 01254 | Corridor MEP | CHW pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 | Sheet 61928 | Hotel | 4
2 | Sheet 61928 | 56 | Level 22 | WIR - 01254 | Corridor MEP | fire fighting pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
3 | Sheet 61928 | 57 | Level 22 | WIR - 01254 | Corridor MEP | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 6 | 0 | FS709/FB750 |  | Hotel | 12
4 | Sheet 61928 | 57 | Level 22 | WIR - 01254 | Corridor MEP | opening |  |  |  | 0.35 | 0.4 | 0.14 | 0.12528 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2
5 | Sheet 61928 | 58 | Level 22 | WIR - 01254 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  |  | 2 |  | 2 | 0 | FS709 |  | Hotel | 4
6 | Sheet 61928 | 59 | Level 22 | WIR - 01254 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  |  | 2 |  | 3 | 0 | FS709 |  | Hotel | 6
7 | Sheet 61928 | 60 | Level 22 | WIR - 01254 | Corridor MEP | fire fighting pipe | 1" |  |  | 2" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
8 | Sheet 61928 | 61 | Level 22 | WIR - 01254 | Corridor MEP | cable pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 2 | 0 | FS709 |  | Hotel | 4
9 | Sheet 61928 | 62 | Level 22 | WIR - 01254 | Corridor MEP | fire fighting pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
10 | Sheet 61928 | 62 | Level 22 | WIR - 01254 | Corridor MEP | opening |  |  |  | 0.3 | 0.3 | 0.09 | 0.085584 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
11 | Sheet 61928 | 63 | Level 22 | WIR - 01254 | Corridor MEP | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
12 | Sheet 61928 | 64 | Level 22 | WIR - 01254 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  |  | 1 |  | 2 | 0 | FS709 |  | Hotel | 2
13 | Sheet 61928 | 65 | Level 22 | WIR - 01254 | Corridor MEP | PPR pipe | 3" |  |  | 5" |  |  |  | 1 |  | 3 | 0 | FS702/FP302 |  | Hotel | 3
14 | Sheet 61928 | 66 | Level 22 | WIR - 01254 | Corridor MEP | fire fighting pipe | 2" |  |  | 4" |  |  |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
15 | Sheet 61928 | 67 | Level 22 | WIR - 01254 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  |  | 1 |  | 7 | 0 | FS709 |  | Hotel | 7
Hotel
October 2022 - Hotel | [19 empty] | Hotel
1 | Sheet 61922 | 1 | Level 23 | WIR - 01253 | Corridor MEP | PPR pipe | 3" |  |  | 5" |  |  |  | 1 |  | 3 | 0 | FS702/FP302 | Sheet 61922 | Hotel | 3
2 | Sheet 61922 | 2 | Level 23 | WIR - 01253 | Corridor MEP | fire fighting pipe | 2" |  |  | 4" |  |  |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
3 | Sheet 61922 | 3 | Level 23 | WIR - 01253 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  |  | 1 |  | 5 | 0 | FS709 |  | Hotel | 5
4 | Sheet 61922 | 4 | Level 23 | WIR - 01253 | Corridor MEP | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
5 | Sheet 61922 | 5 | Level 23 | WIR - 01253 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  |  | 1 |  | 3 | 0 | FS709 |  | Hotel | 3
6 | Sheet 61922 | 6 | Level 23 | WIR - 01253 | Corridor MEP | PPR pipe | 3" |  |  | 5" |  |  |  | 1 |  | 3 | 0 | FS702/FP302 |  | Hotel | 3
7 | Sheet 61922 | 7 | Level 23 | WIR - 01253 | Corridor MEP | fire fighting pipe | 2" |  |  | 4" |  |  |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
8 | Sheet 61922 | 8 | Level 23 | WIR - 01253 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  |  | 1 |  | 4 | 0 | FS709 |  | Hotel | 4
9 | Sheet 61922 | 9 | Level 23 | WIR - 01253 | Corridor MEP | CHW pipe | 2" |  |  | 4" |  |  |  | 1 |  | 2 | 0 | FS709 |  | Hotel | 2
10 | Sheet 61922 | 10 | Level 23 | WIR - 01253 | Corridor MEP | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
11 | Sheet 61922 | 11 | Level 23 | WIR - 01253 | Corridor MEP | CHW pipe | 2" |  |  | 4" |  |  |  | 1 |  | 2 | 0 | FS709 |  | Hotel | 2
12 | Sheet 61922 | 12 | Level 23 | WIR - 01253 | Corridor MEP | CHW pipe | 2" |  |  | 4" |  |  |  | 1 |  | 2 | 0 | FS709 |  | Hotel | 2
13 | Sheet 61922 | 13 | Level 23 | WIR - 01253 | Corridor MEP | PPR pipe | 3" |  |  | 5" |  |  |  | 1 |  | 3 | 0 | FS702/FP302 |  | Hotel | 3
14 | Sheet 61922 | 14 | Level 23 | WIR - 01253 | Corridor MEP | fire fighting pipe | 2" |  |  | 4" |  |  |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
15 | Sheet 61922 | 15 | Level 23 | WIR - 01253 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  |  | 1 |  | 5 | 0 | FS709 |  | Hotel | 5
16 | Sheet 61922 | 16 | Level 23 | WIR - 01253 | Corridor MEP | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
17 | Sheet 61922 | 17 | Level 23 | WIR - 01253 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  |  | 1 |  | 2 | 0 | FS709 |  | Hotel | 2
18 | Sheet 61922 | 18 | Level 23 | WIR - 01253 | Corridor MEP | PPR pipe | 3" |  |  | 5" |  |  |  | 1 |  | 3 | 0 | FS702/FP302 |  | Hotel | 3
19 | Sheet 61922 | 19 | Level 23 | WIR - 01253 | Corridor MEP | fire fighting pipe | 2" |  |  | 4" |  |  |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
20 | Sheet 61922 | 20 | Level 23 | WIR - 01253 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  |  | 1 |  | 6 | 0 | FS709 |  | Hotel | 6
21 | Sheet 61922 | 21 | Level 23 | WIR - 01253 | Corridor MEP | fire fighting pipe | 3" |  |  | 5" |  |  |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
22 | Sheet 61922 | 22 | Level 23 | WIR - 01253 | Corridor MEP | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
23 | Sheet 61922 | 23 | Level 23 | WIR - 01253 | Corridor MEP | CDP pipe | 3" |  |  | 5" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
24 | Sheet 61922 | 24 | Level 23 | WIR - 01253 | Corridor MEP | fire fighting pipe | 1" |  |  | 2" |  |  |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
25 | Sheet 61922 | 25 | Level 23 | WIR - 01253 | Corridor MEP | PPR pipe | 3" |  |  | 5" |  |  |  | 1 |  | 3 | 0 | FS702/FP302 |  | Hotel | 3
26 | Sheet 61922 | 26 | Level 23 | WIR - 01253 | Corridor MEP | fire fighting pipe | 2" |  |  | 4" |  |  |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
27 | Sheet 61922 | 27 | Level 23 | WIR - 01253 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  |  | 1 |  | 22 | 0 | FS709 |  | Hotel | 22
Hotel
October 2022 - Hotel | [19 empty] | Hotel
1 | Sheet 61923 | 28 | Level 23 | WIR - 01253 | Corridor MEP | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 |  | 1 |  | 1 | 0 | FS702 | Sheet 61923 | Hotel | 1
2 | Sheet 61923 | 29 | Level 23 | WIR - 01253 | Corridor MEP | cable pipe | 0.5" |  |  | 1.5" |  |  |  | 1 |  | 4 | 0 | FS709 |  | Hotel | 4
3 | Sheet 61923 | 30 | Level 23 | WIR - 01253 | Housekeeping | cable tray | 0.05 | 0.1 | 0.005 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
4 | Sheet 61923 | 31 | Level 23 | WIR - 01253 | Housekeeping | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 2 |  | 3 | 0 | FS702/FB750 |  | Hotel | 6
5 | Sheet 61923 | 32 | Level 23 | WIR - 01253 | Housekeeping | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750 |  | Hotel | 4
6 | Sheet 61923 | 33 | Level 23 | WIR - 01253 | Housekeeping | fire fighting pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
7 | Sheet 61923 | 34 | Level 23 | WIR - 01253 | Housekeeping | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 3 | 0 | FS709/FB750 |  | Hotel | 6
8 | Sheet 61923 | 35 | Level 23 | WIR - 01253 | Housekeeping | cable pipe | 0.5" |  | 0.00013266 |  |  |  |  | 2 |  | 4 | 0 | FS709/FB750 |  | Hotel | 8
9 | Sheet 61923 | 35 | Level 23 | WIR - 01253 | Housekeeping | opening |  |  |  | 0.6 | 0.9 | 0.54 | 0.48251 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Hotel | 2 | [9 empty] | 43399.8
10 | Sheet 61923 | 36 | Level 23 | WIR - 01253 | Housekeeping | CHW pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Hotel | 4
11 | Sheet 61923 | 37 | Level 23 | WIR - 01253 | Housekeeping | CDP pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 | FS702/FP302/FB750 |  | Hotel | 2
12 | Sheet 61923 | 37 | Level 23 | WIR - 01253 | Housekeeping | opening |  |  |  | 0.3 | 0.3 | 0.09 | 0.084112 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
13 | Sheet 61923 | 38 | Level 23 | WIR - 01253 | Staircase | fire fighting pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
14 | Sheet 61923 | 38 | Level 23 | WIR - 01253 | Staircase | opening |  |  |  | 0.3 | 0.3 | 0.09 | 0.085584 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
15 | Sheet 61923 | 39 | Level 23 | WIR - 01253 | Lobby | CHW pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Hotel | 4
16 | Sheet 61923 | 40 | Level 23 | WIR - 01253 | Lobby | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 9 | 0 | FS709/FB750 |  | Hotel | 18
17 | Sheet 61923 | 40 | Level 23 | WIR - 01253 | Lobby | opening |  |  |  | 0.2 | 0.6 | 0.12 | 0.11166 | 2 | 150 | 1 | 300 | FS702/FB750 |  | Hotel | 2 | [8 empty] | 46839.8
18 | Sheet 61923 | 41 | Level 23 | WIR - 01253 | Lobby | fire fighting pipe | 1" |  |  | 2" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
19 | Sheet 61923 | 42 | Level 23 | WIR - 01253 | Water M. Room | PPR pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 1 | 0 | FS702/FP302/FB750 |  | Hotel | 2
20 | Sheet 61923 | 43 | Level 23 | WIR - 01253 | Water M. Room | PPR pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 2 | 0 | FS702/FP302/FB750 |  | Hotel | 4
21 | Sheet 61923 | 43 | Level 23 | WIR - 01253 | Water M. Room | opening |  |  |  | 0.3 | 0.8 | 0.24 | 0.22332 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2
22 | Sheet 61923 | 44 | Level 23 | WIR - 01253 | Lobby | CHW pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 2 | 0 | FS709/FB750 |  | Hotel | 4
23 | Sheet 61923 | 45 | Level 23 | WIR - 01253 | Lobby | fire fighting pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
24 | Sheet 61923 | 46 | Level 23 | WIR - 01253 | Lobby | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 11 | 0 | FS709/FB750 |  | Hotel | 22
25 | Sheet 61923 | 46 | Level 23 | WIR - 01253 | Lobby | opening |  |  |  | 0.4 | 0.55 | 0.22 | 0.20283 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2 | [8 empty] | 45899.8
26 | Sheet 61923 | 47 | Level 23 | WIR - 01253 | Lobby | conduit pipe | 1" |  |  | 2" |  |  |  | 2 |  | 3 | 0 | FS709 |  | Hotel | 6
27 | Sheet 61923 | 48 | Level 23 | WIR - 01253 | Lobby | fire fighting pipe | 1" |  |  | 2" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
28 | Sheet 61923 | 49 | Level 23 | WIR - 01253 | Lobby | fire fighting pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
29 | Sheet 61923 | 49 | Level 23 | WIR - 01253 | Lobby | opening |  |  |  | 0.3 | 0.3 | 0.09 | 0.085584 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
30 | Sheet 61923 | 50 | Level 23 | WIR - 01253 | Corridor MEP | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
31 | Sheet 61923 | 51 | Level 23 | WIR - 01253 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  |  | 1 |  | 1 | 0 | FS709 |  | Hotel | 1
32 | Sheet 61923 | 52 | Level 23 | WIR - 01253 | Corridor MEP | PPR pipe | 3" |  |  | 5" |  |  |  | 1 |  | 3 | 0 | FS702/FP302 |  | Hotel | 3
33 | Sheet 61923 | 53 | Level 23 | WIR - 01253 | Corridor MEP | fire fighting pipe | 2" |  |  | 4" |  |  |  | 1 |  | 1 | 0 | FS702 |  | Hotel | 1
34 | Sheet 61923 | 54 | Level 23 | WIR - 01253 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  |  | 1 |  | 7 | 0 | FS709 |  | Hotel | 7
Hotel
October 2022 - Hotel - Outer Sleeve | [19 empty] | Hotel
1 | Sheet 62251 |  | Level 24 | WIR - 00588 (B) | Outer Sleeve | fire fighting pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 | FS702/FB750 | Sheet 62251 | Hotel | 2
2 | Sheet 62251 |  | Level 24 | WIR - 00588 (B) | Outer Sleeve | PVC pipe | 4" |  |  | 6" |  |  |  | 2 |  | 1 | 0 | FS702/FB750/FP302 |  | Hotel | 2
3 | Sheet 62251 |  | Level 24 | WIR - 00588 (B) | Outer Sleeve | fire fighting pipe | 3" |  | 0.0044156 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
4 | Sheet 62251 |  | Level 24 | WIR - 00588 (B) | Outer Sleeve | opening |  |  |  | 0.3 | 0.3 | 0.09 | 0.085584 | 1 | 95 | 1 | 95 | FS702/FB750 |  | Hotel | 1
5 | Sheet 62251 |  | Level 24 | WIR - 00588 (B) | Outer Sleeve | fire fighting pipe | 1" |  | 0.00049063 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
6 | Sheet 62251 |  | Level 24 | WIR - 00588 (B) | Outer Sleeve | opening |  |  |  | 0.3 | 0.4 | 0.12 | 0.11951 | 1 | 150 | 1 | 150 | FS702/FB750 |  | Hotel | 1
7 | Sheet 62251 |  | Level 24 | WIR - 00588 (B) | Outer Sleeve | fire fighting pipe | 1" |  |  | 2" |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
8 | Sheet 62251 |  | Level 24 | WIR - 00588 (B) | Outer Sleeve | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
Hotel
October 2022 - Hotel - Outer Sleeve | [19 empty] | Hotel
1 | Sheet 62252 |  | Level 08 |  | Outer Sleeve | PPR pipe | 3" |  | 0.0044156 |  |  |  |  | 1 |  | 3 | 0 | FS702/FB750/FP302 | Sheet 62252 | Hotel | 3
2 | Sheet 62252 |  | Level 08 |  | Outer Sleeve | PVC pipe | 4" |  | 0.00785 |  |  |  |  | 1 |  | 2 | 0 | FS702/FB750/FP302 |  | Hotel | 2
3 | Sheet 62252 |  | Level 08 |  | Outer Sleeve | opening |  |  |  | 0.3 | 0.7 | 0.21 | 0.18105 | 1 | 180 | 1 | 0 | FS702/FB750 |  | Hotel | 1
4 | Sheet 62252 |  | Level 08 |  | Outer Sleeve | cable trunking |  |  |  | 0.15 | 0.2 | 0.03 |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
5 | Sheet 62252 |  | Level 08 |  | Outer Sleeve | PVC pipe | 6" |  |  | 8" |  |  |  | 1 |  | 1 | 0 | FS702/FB750/FP302 |  | Hotel | 1
6 | Sheet 62252 |  | Level 08 |  | Outer Sleeve | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
7 | Sheet 62252 |  | Level 08 |  | Outer Sleeve | CHW pipe | 3" |  |  | 5" |  |  |  | 1 |  | 2 | 0 | FS702/FB750 |  | Hotel | 2
8 | Sheet 62252 |  | Level 08 |  | Outer Sleeve | fire fighting pipe | 2" |  |  | 4" |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
9 | Sheet 62252 |  | Level 08 |  | Outer Sleeve | conduit pipe | 0.5" |  |  | 1.5" |  |  |  | 1 |  | 2 | 0 | FS702/FB750 |  | Hotel | 2
Hotel
October 2022 - Hotel - Outer Sleeve | [19 empty] | Hotel
1 | Sheet 61930 | 1 | Level 22 | WIR - 01254 (B) | Corridor Out. Sleeve | PPR pipe | 4" |  |  | 6" |  |  |  | 1 |  | 3 | 0 | FS702/FB750/FP302 | Sheet 61930 | Hotel | 3
2 | Sheet 61930 | 2 | Level 22 | WIR - 01254 (B) | Corridor Out. Sleeve | fire fighting pipe | 3" |  |  | 5" |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
3 | Sheet 61930 | 3 | Level 22 | WIR - 01254 (B) | Corridor Out. Sleeve | fire fighting pipe | 3" |  |  | 5" |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
4 | Sheet 61930 | 4 | Level 22 | WIR - 01254 (B) | Corridor Out. Sleeve | PPR pipe | 4" |  |  | 6" |  |  |  | 1 |  | 3 | 0 | FS702/FB750/FP302 |  | Hotel | 3
5 | Sheet 61930 | 5 | Level 22 | WIR - 01254 (B) | Corridor Out. Sleeve | PPR pipe | 4" |  |  | 6" |  |  |  | 1 |  | 3 | 0 | FS702/FB750/FP302 |  | Hotel | 3
6 | Sheet 61930 | 6 | Level 22 | WIR - 01254 (B) | Corridor Out. Sleeve | CHW pipe | 3" |  |  | 5" |  |  |  | 1 |  | 2 | 0 | FS702/FB750 |  | Hotel | 2
7 | Sheet 61930 | 7 | Level 22 | WIR - 01254 (B) | Corridor Out. Sleeve | fire fighting pipe | 3" |  |  | 5" |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
8 | Sheet 61930 | 8 | Level 22 | WIR - 01254 (B) | Corridor Out. Sleeve | CHW pipe | 3" |  |  | 5" |  |  |  | 1 |  | 2 | 0 | FS702/FB750 |  | Hotel | 2
9 | Sheet 61930 | 9 | Level 22 | WIR - 01254 (B) | Corridor Out. Sleeve | fire fighting pipe | 3" |  |  | 5" |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
10 | Sheet 61930 | 10 | Level 22 | WIR - 01254 (B) | Corridor Out. Sleeve | CHW pipe | 3" |  |  | 5" |  |  |  | 1 |  | 2 | 0 | FS702/FB750 |  | Hotel | 2
11 | Sheet 61930 | 11 | Level 22 | WIR - 01254 (B) | Corridor Out. Sleeve | PPR pipe | 4" |  |  | 6" |  |  |  | 1 |  | 3 | 0 | FS702/FB750/FP302 |  | Hotel | 3
12 | Sheet 61930 | 12 | Level 22 | WIR - 01254 (B) | Corridor Out. Sleeve | fire fighting pipe | 3" |  |  | 5" |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
13 | Sheet 61930 | 13 | Level 22 | WIR - 01254 (B) | Corridor Out. Sleeve | PPR pipe | 4" |  | 0.00785 |  |  |  |  | 1 |  | 3 | 0 | FS702/FB750/FP302 |  | Hotel | 3
14 | Sheet 61930 | 13 | Level 22 | WIR - 01254 (B) | Corridor Out. Sleeve | opening |  |  |  | 0.1 | 1.7 | 0.17 | 0.14645 | 1 | 150 | 1 | 150 | FS702/FB750 |  | Hotel | 1
15 | Sheet 61930 | 14 | Level 22 | WIR - 01254 (B) | Corridor Out. Sleeve | duct | 0.3 | 0.3 | 0.09 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
16 | Sheet 61930 | 15 | Level 22 | WIR - 01254 (B) | Corridor Out. Sleeve | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 1 |  | 5 | 0 | FS702/FB750 |  | Hotel | 5
17 | Sheet 61930 | 15 | Level 22 | WIR - 01254 (B) | Corridor Out. Sleeve | opening |  |  |  | 0.4 | 0.8 | 0.32 | 0.22755 | 1 | 180 | 1 | 180 | FS702/FB750 |  | Hotel | 1
18 | Sheet 61930 | 16 | Level 22 | WIR - 01254 (B) | Corridor Out. Sleeve | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 1 |  | 3 | 0 | FS702/FB750 |  | Hotel | 3
19 | Sheet 61930 | 17 | Level 22 | WIR - 01254 (B) | Corridor Out. Sleeve | duct | 0.3 | 0.3 | 0.09 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
20 | Sheet 61930 | 17 | Level 22 | WIR - 01254 (B) | Corridor Out. Sleeve | opening |  |  |  | 0.7 | 1 | 0.7 | 0.60853 | 1 | 340 | 1 | 340 | FS702/FB750 |  | Hotel | 1
21 | Sheet 61930 | 18 | Level 22 | WIR - 01254 (B) | Corridor Out. Sleeve | CHW pipe | 3" |  |  | 5" |  |  |  | 1 |  | 2 | 0 | FS702/FB750 |  | Hotel | 2
22 | Sheet 61930 | 19 | Level 22 | WIR - 01254 (B) | Corridor Out. Sleeve | CDP pipe | 3" |  |  | 5" |  |  |  | 1 |  | 1 | 0 | FS702/FB750/FP302 |  | Hotel | 1
23 | Sheet 61930 | 20 | Level 22 | WIR - 01254 (B) | Corridor Out. Sleeve | PPR pipe | 4" |  |  | 6" |  |  |  | 2 |  | 3 | 0 | FS702/FB750/FP302 |  | Hotel | 6
24 | Sheet 61930 | 21 | Level 22 | WIR - 01254 (B) | Corridor Out. Sleeve | fire fighting pipe | 1" |  |  | 3" |  |  |  | 2 |  | 3 | 0 | FS702/FB750 |  | Hotel | 6
25 | Sheet 61930 | 22 | Level 22 | WIR - 01254 (B) | Corridor Out. Sleeve | fire fighting pipe | 4" |  |  | 6" |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
26 | Sheet 61930 | 23 | Level 22 | WIR - 01254 (B) | Corridor Out. Sleeve | fire fighting pipe | 1" |  |  | 2" |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
27 | Sheet 61930 | 24 | Level 22 | WIR - 01254 (B) | Corridor Out. Sleeve | PPR pipe | 4" |  |  | 6" |  |  |  | 1 |  | 3 | 0 | FS702/FB750/FP302 |  | Hotel | 3
28 | Sheet 61930 | 25 | Level 22 | WIR - 01254 (B) | Corridor Out. Sleeve | fire fighting pipe | 3" |  |  | 5" |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
Hotel
October 2022 - Hotel - Outer Sleeve | [19 empty] | Hotel
1 | Sheet 61925 | 1 | Level 23 | WIR - 01253 (B) | Corridor Out. Sleeve | PPR pipe | 4" |  |  | 6" |  |  |  | 1 |  | 3 | 0 | FS702/FB750/FP302 | Sheet 61925 | Hotel | 3
2 | Sheet 61925 | 2 | Level 23 | WIR - 01253 (B) | Corridor Out. Sleeve | fire fighting pipe | 3" |  |  | 5" |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
3 | Sheet 61925 | 3 | Level 23 | WIR - 01253 (B) | Corridor Out. Sleeve | PPR pipe | 4" |  |  | 6" |  |  |  | 1 |  | 3 | 0 | FS702/FB750/FP302 |  | Hotel | 3
4 | Sheet 61925 | 4 | Level 23 | WIR - 01253 (B) | Corridor Out. Sleeve | fire fighting pipe | 3" |  |  | 5" |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
5 | Sheet 61925 | 5 | Level 23 | WIR - 01253 (B) | Corridor Out. Sleeve | CHW pipe | 3" |  |  | 5" |  |  |  | 1 |  | 2 | 0 | FS702/FB750 |  | Hotel | 2
6 | Sheet 61925 | 6 | Level 23 | WIR - 01253 (B) | Corridor Out. Sleeve | CHW pipe | 3" |  |  | 5" |  |  |  | 1 |  | 2 | 0 | FS702/FB750 |  | Hotel | 2
7 | Sheet 61925 | 7 | Level 23 | WIR - 01253 (B) | Corridor Out. Sleeve | CHW pipe | 3" |  |  | 5" |  |  |  | 1 |  | 2 | 0 | FS702/FB750 |  | Hotel | 2
8 | Sheet 61925 | 8 | Level 23 | WIR - 01253 (B) | Corridor Out. Sleeve | PPR pipe | 4" |  |  | 6" |  |  |  | 1 |  | 3 | 0 | FS702/FB750/FP302 |  | Hotel | 3
9 | Sheet 61925 | 9 | Level 23 | WIR - 01253 (B) | Corridor Out. Sleeve | fire fighting pipe | 3" |  |  | 5" |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
10 | Sheet 61925 | 10 | Level 23 | WIR - 01253 (B) | Corridor Out. Sleeve | PPR pipe | 4" |  |  | 6" |  |  |  | 1 |  | 3 | 0 | FS702/FB750/FP302 |  | Hotel | 3
11 | Sheet 61925 | 11 | Level 23 | WIR - 01253 (B) | Corridor Out. Sleeve | fire fighting pipe | 3" |  |  | 5" |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
12 | Sheet 61925 | 12 | Level 23 | WIR - 01253 (B) | Corridor Out. Sleeve | fire fighting pipe | 5" |  |  | 7" |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
13 | Sheet 61925 | 13 | Level 23 | WIR - 01253 (B) | Corridor Out. Sleeve | CDP pipe | 4" |  |  | 6" |  |  |  | 1 |  | 1 | 0 | FS702/FB750/FP302 |  | Hotel | 1
14 | Sheet 61925 | 14 | Level 23 | WIR - 01253 (B) | Corridor Out. Sleeve | fire fighting pipe | 2" |  |  | 4" |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
15 | Sheet 61925 | 15 | Level 23 | WIR - 01253 (B) | Corridor Out. Sleeve | PPR pipe | 4" |  | 0.00785 |  |  |  |  | 1 |  | 3 | 0 | FS702/FB750/FP302 |  | Hotel | 3
16 | Sheet 61925 | 16 | Level 23 | WIR - 01253 (B) | Corridor Out. Sleeve | fire fighting pipe | 2" |  | 0.0019625 |  |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
17 | Sheet 61925 | 16 | Level 23 | WIR - 01253 (B) | Corridor Out. Sleeve | opening |  |  |  | 0.2 | 0.7 | 0.14 | 0.11449 | 1 | 150 | 1 | 150 | FS702/FB750 |  | Hotel | 1
18 | Sheet 61925 | 17 | Level 23 | WIR - 01253 (B) | Corridor Out. Sleeve | PPR pipe | 4" |  |  | 6" |  |  |  | 1 |  | 3 | 0 | FS702/FB750/FP302 |  | Hotel | 3
19 | Sheet 61925 | 18 | Level 23 | WIR - 01253 (B) | Corridor Out. Sleeve | fire fighting pipe | 3" |  |  | 5" |  |  |  | 1 |  | 1 | 0 | FS702/FB750 |  | Hotel | 1
September 2022 - Hotel | [19 empty] | Hotel
1 | Sheet 61915 | 1 | Level 18 | WIR - 01149 | FTR Room | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 3 | 0 | FR230 | Sheet 61915 | Hotel | 3 |  | 0.015 | 3 | 0.045
2 | Sheet 61915 | 1 | Level 18 | WIR - 01149 | FTR Room | cable tray | 0.05 | 0.5 | 0.025 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  | 0.025 | 1 | 0.025
3 | Sheet 61915 | 1 | Level 18 | WIR - 01149 | FTR Room | cable trunking | 0.15 | 0.15 | 0.0225 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  | 0.0225 | 1 | 0.0225
4 | Sheet 61915 | 1 | Level 18 | WIR - 01149 | FTR Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  | 0.01 | 1 | 0.01
5 | Sheet 61915 | 1 | Level 18 | WIR - 01149 | FTR Room | cable trunking | 0.05 | 0.07 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR230 |  | Hotel | 2 |  | 0.01 | 2 | 0.02 | 0.1225
6 | Sheet 61915 | 1 | Level 18 | WIR - 01149 | FTR Room | opening Mortar |  |  |  | 0.35 | 1.8 | 0.63 | 0.5075 | 1 | 680 | 1 | 345.1 | FR230 |  | Hotel | 0.5075
7 | Sheet 61915 | 2 | Level 19 | WIR - 01150 | FTR Room | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 3 | 0 | FR230 |  | Hotel | 3 |  | 0.015 | 3 | 0.045
8 | Sheet 61915 | 2 | Level 19 | WIR - 01150 | FTR Room | cable tray | 0.05 | 0.5 | 0.025 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  | 0.025 | 1 | 0.025
9 | Sheet 61915 | 2 | Level 19 | WIR - 01150 | FTR Room | cable trunking | 0.15 | 0.15 | 0.0225 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  | 0.0225 | 1 | 0.0225
10 | Sheet 61915 | 2 | Level 19 | WIR - 01150 | FTR Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  | 0.01 | 1 | 0.01
11 | Sheet 61915 | 2 | Level 19 | WIR - 01150 | FTR Room | cable trunking | 0.05 | 0.07 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR230 |  | Hotel | 2 |  | 0.01 | 2 | 0.02 | 0.1225
12 | Sheet 61915 | 2 | Level 19 | WIR - 01150 | FTR Room | opening Mortar |  |  |  | 0.35 | 1.8 | 0.63 | 0.5075 | 1 | 680 | 1 | 345.1 | FR230 |  | Hotel | 0.5075
[15 empty] | Grand Total |  | 49845 |  |  |  | 1131.12
WIR List as per SOS
[5 empty] | Level 01 | WIR - 01191
[5 empty] | Ground Level | WIR - 01192 | [8 empty] | MEP |  | 49845
[5 empty] | Level 09 | WIR - 01416 | [8 empty] | Joints |  | 1484
[5 empty] | Level 22 | WIR - 01254
[5 empty] | Level 23 | WIR - 01253 | [8 empty] | Total |  | 51329
[5 empty] | Level 22 | WIR - 00175
[5 empty] | Level 23 | WIR - 00176
[16 empty] | 14 | 112
[16 empty] | 16 | 304
[16 empty] | 23 | 851
[16 empty] | 30 | 1950
[16 empty] | 46 | 184
[16 empty] | 50 | 600
[16 empty] | 51 | 51
[16 empty] | 65 | 65
[16 empty] | 95 | 5700
[16 empty] | 125 | 2125
[16 empty] | 150 | 5400
[16 empty] | 180 | 4860
[16 empty] | 245 | 735
[16 empty] | 250 | 750
[16 empty] | 310 | 5890
[16 empty] | 340 | 1360
[16 empty] | 400 | 800
[16 empty] | 450 | 4644
[16 empty] | 680 | 13464
49845
Note on S236: Himal Kosala: Check this material

## Joints
Project: |  |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  |  | Khansaheb Civil Engineering
Period of Completed Works: |  |  |  | October 2022
Summary of Completed Firestopping Works (Construction Joints)
No. | Sos Number | Level | WIR No. | Location | Type | Joint Size (in meter) |  |  | Sides | Rate (AED) | Nos | Total (AED) |  |  | Hotel / Residence | QTY | Remarks
Hotel
October 2022 - Hotel | [14 empty] | Hotel
1 | Sheet 61924 | Level 23 | WIR - 00176 | Corridor | Head of wall joint | 0.02 | 50.5 | @ | 1 | 14 | 1 | 707 | 20 | Sheet 61924 | Hotel | 50.5
Hotel
October 2022 - Hotel | [14 empty] | Hotel
1 | Sheet 61929 | Level 22 | WIR - 00175 | Corridor | Head of wall joint | 0.02 | 55.5 | @ | 1 | 14 | 1 | 777 | 20 | Sheet 61929 | Hotel | 55.5
[10 empty] | Grand Total |  | 1484 |  |  |  | 106 | 1484
WIR List as per SOS
|  |  |  | Level 23 | WIR - 00176
|  |  |  | Level 22 | WIR - 00175