## IPC-6 (hidden)
PROJECT |  | DORCHESTER HOTEL AND RESIDENCES | [6 empty] | IPC-06
EMPLOYER |  | SKY PALACES REAL ESTATE DEVELOPMENT LLC
EMPLOYER'S REP |  | OMNIYAT CONCEPT INVESTMENTS LLC
ENGINEER |  | BREWER SMITH BREWER GULG ( BSBG )
MAIN CONTRACTOR |  | KHANSAHEB CIVIL ENGINEERING
FOR THE PERIOD ENDING |  | 2022-07-31
FIRE STOP WORKS ON MEP PENETRATIONS AND JOINTS
Item | Description | Contract Amount (AED) | Progress Completion (%) |  |  | Work Done (AED) |  |  | Remarks
|  |  | Previous | This Month | Cumulative | Previous | This Month | Cumulative
FIRESTOP MIDDLE EAST INVOICE REF.FME-INV-2022-0147
A | Firestop to MEP Penetrations | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
B | Firestop to Construction Joints | 193300 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Total MEP Amount | #REF! |  |  |  | #REF! | #REF! | #REF!

## Contract
FIRE STOP WORKS ON MEP PENETRATIONS AND JOINTS | [11 empty] | FIRE STOP
[6 empty] | Quantity |  |  | Progress Amount (AED)
S.Nr | Description | Qty | Unit | Rate | Amount | Previous | Current | Cumulative | Previous | Current | Cumulative | WIR Ref./ Remarks | Certified Qty (This month) | Certified Qty (Cumulative) | Certified Amount (This month) | Certified Amount (Cumulative)
G | Supply and installation of firestop sealant and mineral wool to Head of wall / Wall to wall joints (Single Sided)
G1 | Upto 20mm joint width | 500 | m | 14 | 7000 | 1841.6 | 392.05 | 2233.65 | 25782.4 | 5488.7 | 31271.1 |  |  |  | 5488.7 | 31271.1
G2 | Upto 30mm joint width | 500 | m | 20 | 10000 | 39 |  | 39 | 780 | 0 | 780 |  |  |  |  | 780
G3 | Upto 35mm joint width | 150 | m | 27 | 4050 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0
H | Supply and installation of Sealant and mineral wool non-fire rated Head of wall / Wall to wall joints (Single Sided)
H1 | Upto 20mm joint width | 250 | m | 10 | 2500 |  |  |  | 0 | 0 | 0
D | Supply and apply firestop board material to cable tray openings, shaft openings and openings (Single Board)
D1 | For an area upto 0.05 m2 | 100 | No. | 50 | 5000 |  | 20 | 20 | 0 | 1000 | 1000 |  | 20 | 20 | 1000 | 1000
D2 | For an area upto 0.10 m2 | 100 | No. | 95 | 9500 |  | 10 | 10 | 0 | 950 | 950 |  | 10 | 10 | 950 | 950
D3 | For an area upto 0.15 m2 | 100 | No. | 150 | 15000 |  |  | 0 | 0 | 0 | 0
D4 | For an area upto 0.25 m2 | 100 | No. | 180 | 18000 |  | 4 | 4 | 0 | 720 | 720 |  | 4 | 4 | 720 | 720
D5 | For an area upto 0.35 m2 | 100 | No. | 245 | 24500 |  |  | 0 | 0 | 0 | 0
D6 | For an area upto 0.50 m2 | 50 | No. | 310 | 15500 |  | 8 | 8 | 0 | 2480 | 2480 |  | 8 | 8 | 2480 | 2480
D7 | For an area upto 0.65 m2 | 50 | No. | 340 | 17000 |  |  | 0 | 0 | 0 | 0
D8 | For an area upto 0.80 m2 | 50 | No. | 400 | 20000 |  | 2 | 2 | 0 | 800 | 800 |  | 2 | 2 | 800 | 800
D9 | For an area upto 1.00 m2 | 25 | m2 | 450 | 11250 |  | 5.3916 | 5.3916 | 0 | 2426.2369 | 2426.2369 |  | 5.3916 | 5.3916 | 2426.2369 | 2426.2369
F | Supply and installation of Nullfire FR 230 firestop mortar material (100mm thickness) to Electrical Openings (Single Sided)
F1 | For an area upto 1.00 m2 | 50 | m2 | 680 | 34000 |  | 6.57 | 6.57 | 0 | 4467.6 | 4467.6 |  | 5.075 | 5.075 | 3451 | 3451
| TOTAL AMOUNT OF CONSTRUCTION JOINTS |  |  |  | 193300 | 1880.6 | 448.0116 | 2328.6116 | 26562.4 | 18332.5369 | 44894.9369 |  |  |  | 17315.9369 | 43878.3369
[9 empty] | 26562.4 | 18332.5369 | 44894.9369
[9 empty] | 0 | 0 | 0

## Joints
Project: |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  | Khansaheb Civil Engineering - Construction Division
Period of Completed Works: |  |  | September 2022
Summary of Completed Firestopping Works (Construction Joints)
No. | Sos Number | Level | WIR No. | Location | Type | Joint Size (in meter) |  |  | Sides | Rate (AED) | Nos | Total (AED) |  |  | Hotel / Residence | QTY | Remarks | Certified Amount for September 2022
September 2022 - Hotel
1 | Sheet 61909 | Level 29 | WIR - 0172 | Electrical Room | Head of wall joint | 0.02 | 10.3 | @ | 2 | 14 | 1 | 288.4 | 20 | Sheet 61909 | Hotel | 20.6 |  | 288.4
2 | Sheet 61909 | Level 29 | WIR - 0172 | Electrical Room | Head of wall joint | 0.02 | 8.15 | @ | 2 | 14 | 1 | 228.2 | 20 |  | Hotel | 16.3 |  | 228.2
3 | Sheet 61909 | Level 29 | WIR - 0172 | Electrical Room | Vertical joint | 0.02 | 2.55 | @ | 1 | 14 | 1 | 35.7 | 20 |  | Hotel | 2.55 |  | 35.7
0
September 2022 - Hotel | [17 empty] | 0
1 | Sheet 61913 | Ground Level | WIR - 0173 | Ball Room | Horizontal joint | 0.02 | 19.7 | @ | 1 | 14 | 1 | 275.8 | 20 | Sheet 61913 | Hotel | 19.7 |  | 275.8
2 | Sheet 61913 | Ground Level | WIR - 0173 | Ball Room | Vertical joint | 0.02 | 8 | @ | 1 | 14 | 2 | 224 | 20 |  | Hotel | 16 |  | 224
3 | Sheet 61913 | Ground Level | WIR - 0173 | Ball Room | Horizontal joint | 0.02 | 10.5 | @ | 1 | 14 | 1 | 147 | 20 |  | Hotel | 10.5 |  | 147
4 | Sheet 61913 | Ground Level | WIR - 0173 | Ball Room | Horizontal joint | 0.02 | 17 | @ | 1 | 14 | 1 | 238 | 20 |  | Hotel | 17 |  | 238
5 | Sheet 61913 | Ground Level | WIR - 0173 | Lobby | Horizontal joint | 0.02 | 16.8 | @ | 2 | 14 | 1 | 470.4 | 20 |  | Hotel | 33.6 |  | 470.4
6 | Sheet 61913 | Ground Level | WIR - 0173 | Lobby | Vertical joint | 0.02 | 3.5 | @ | 2 | 14 | 4 | 392 | 20 |  | Hotel | 28 |  | 392
7 | Sheet 61913 | Ground Level | WIR - 0173 | Lobby | Horizontal joint | 0.02 | 35.2 | @ | 1 | 14 | 1 | 492.8 | 20 |  | Hotel | 35.2 |  | 492.8
8 | Sheet 61913 | Ground Level | WIR - 0173 | Lobby | Vertical joint | 0.02 | 3.6 | @ | 1 | 14 | 6 | 302.4 | 20 |  | Hotel | 21.6 |  | 302.4
0
September 2022 - Hotel | [17 empty] | 0
1 | Sheet 61914 | Level 01 | WIR - 0171 | Wall | Horizontal joint | 0.02 | 95 | @ | 1 | 14 | 1 | 1330 | 20 | Sheet 61914 | Hotel | 95 |  | 1330
2 | Sheet 61914 | Level 01 | WIR - 0171 | Wall | Vertical joint | 0.02 | 4 | @ | 1 | 14 | 5 | 280 | 20 |  | Hotel | 20 |  | 280
3 | Sheet 61914 | Level 01 | WIR - 0171 | Wall | Vertical joint | 0.02 | 8 | @ | 1 | 14 | 3 | 336 | 20 |  | Hotel | 24 |  | 336
4 | Sheet 61914 | Level 01 | WIR - 0171 | Wall | Horizontal joint | 0.02 | 32 | @ | 1 | 14 | 1 | 448 | 20 |  | Hotel | 32 |  | 448
[10 empty] | Grand Total |  | 5488.7 | 300 | 0 | 0 | 392.05 | 0 | 5488.7
WIR List as per SOS
|  |  |  | Ground Level | WIR - 0173
|  |  |  | Level 01 | WIR - 0171
|  |  |  | Level 29 | WIR - 0172

## Joints 20mm
Project: |  |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  |  | Khansaheb Civil Engineering
Period of Completed Works: |  |  |  | up to July 2022
Summary of Completed Firestopping Works (Construction Joints)
No. | Sos Number | Level | WIR No. | Location | Type | Joint Size (in meter) |  |  | Sides | Rate (AED) | Nos | Total (AED) |  |  | Hotel / Residence | QTY | Remarks
1 | Sheet 61023 | Level 25 | FSM-AX-WR-L25-00161 | Corridor | Head of wall joint | 0.02 | 35 | @ | 2 | 14 | 1 | 980 | 20 | Sheet 61023 | Residence | 70
2 | Sheet 61023 | Level 25 | FSM-AX-WR-L25-00161 | Corridor | Head of wall joint | 0.02 | 4 | @ | 2 | 14 | 3 | 336 | 20 |  | Residence | 24
3 | Sheet 61023 | Level 25 | FSM-AX-WR-L25-00161 | FF Lobby | Head of wall joint | 0.02 | 18 | @ | 2 | 14 | 1 | 504 | 20 |  | Residence | 36
4 | Sheet 61023 | Level 25 | FSM-AX-WR-L25-00161 | Housekeeping | Head of wall joint | 0.02 | 10 | @ | 2 | 14 | 1 | 280 | 20 |  | Residence | 20
5 | Sheet 61023 | Level 25 | FSM-AX-WR-L25-00161 | Garbage Room | Head of wall joint | 0.02 | 13 | @ | 2 | 14 | 1 | 364 | 20 |  | Residence | 26
6 | Sheet 61023 | Level 25 | FSM-AX-WR-L25-00161 | Passanger Lift lobby | Head of wall joint | 0.02 | 25 | @ | 2 | 14 | 1 | 700 | 20 |  | Residence | 50
7 | Sheet 61023 | Level 25 | FSM-AX-WR-L25-00161 | Water meter Rm | Head of wall joint | 0.02 | 12 | @ | 2 | 14 | 1 | 336 | 20 |  | Residence | 24
8 | Sheet 61023 | Level 25 | FSM-AX-WR-L25-00161 | Apartment, Shaft | Head of wall joint | 0.02 | 3.5 | @ | 2 | 14 | 3 | 294 | 20 |  | Residence | 21
9 | Sheet 61023 | Level 25 | FSM-AX-WR-L25-00161 | Apartment, Shaft | Head of wall joint | 0.02 | 5.1 | @ | 2 | 14 | 1 | 142.8 | 20 |  | Residence | 10.2
1 | Sheet 61024 | Level 24 | FSM-AX-WR-L24-00162 | Corridor | Head of wall joint | 0.02 | 35 | @ | 2 | 14 | 1 | 980 | 20 | Sheet 61024 | Residence | 70
2 | Sheet 61024 | Level 24 | FSM-AX-WR-L24-00162 | Corridor | Head of wall joint | 0.02 | 4 | @ | 2 | 14 | 3 | 336 | 20 |  | Residence | 24
3 | Sheet 61024 | Level 24 | FSM-AX-WR-L24-00162 | FF Lobby | Head of wall joint | 0.02 | 18 | @ | 2 | 14 | 1 | 504 | 20 |  | Residence | 36
4 | Sheet 61024 | Level 24 | FSM-AX-WR-L24-00162 | Housekeeping | Head of wall joint | 0.02 | 10 | @ | 2 | 14 | 1 | 280 | 20 |  | Residence | 20
5 | Sheet 61024 | Level 24 | FSM-AX-WR-L24-00162 | Garbage Room | Head of wall joint | 0.02 | 13 | @ | 2 | 14 | 1 | 364 | 20 |  | Residence | 26
6 | Sheet 61024 | Level 24 | FSM-AX-WR-L24-00162 | Passanger Lift lobby | Head of wall joint | 0.02 | 25 | @ | 2 | 14 | 1 | 700 | 20 |  | Residence | 50
7 | Sheet 61024 | Level 24 | FSM-AX-WR-L24-00162 | Water meter Rm | Head of wall joint | 0.02 | 12 | @ | 2 | 14 | 1 | 336 | 20 |  | Residence | 24
8 | Sheet 61024 | Level 24 | FSM-AX-WR-L24-00162 | Apartment, Shaft | Head of wall joint | 0.02 | 3.5 | @ | 2 | 14 | 3 | 294 | 20 |  | Residence | 21
9 | Sheet 61024 | Level 24 | FSM-AX-WR-L24-00162 | Apartment, Shaft | Head of wall joint | 0.02 | 5.1 | @ | 2 | 14 | 1 | 142.8 | 20 |  | Residence | 10.2
1 | Sheet 61032 | Level 06 | FSM-AX-WR-L6-00163 | Apart. no. 4A | Head of wall joint | 0.02 | 37 | @ | 2 | 14 | 1 | 1036 | 20 | Sheet 61032 | Residence | 74
2 | Sheet 61032 | Level 06 | FSM-AX-WR-L6-00163 | Apart. no. 4A | Head of wall joint | 0.02 | 3.5 | @ | 2 | 14 | 5 | 490 | 20 |  | Residence | 35
3 | Sheet 61032 | Level 06 | FSM-AX-WR-L6-00163 | Apart. no. 3B | Head of wall joint | 0.02 | 9 | @ | 2 | 14 | 1 | 252 | 20 |  | Residence | 18
4 | Sheet 61032 | Level 06 | FSM-AX-WR-L6-00163 | Apart. no. 3B | Head of wall joint | 0.02 | 2.45 | @ | 2 | 14 | 1 | 68.6 | 20 |  | Residence | 4.9
5 | Sheet 61032 | Level 06 | FSM-AX-WR-L6-00163 | Apart. no. 3B | Head of wall joint | 0.02 | 3.5 | @ | 2 | 14 | 2 | 196 | 20 |  | Residence | 14
6 | Sheet 61032 | Level 06 | FSM-AX-WR-L6-00163 | Apart. no. 2A | Head of wall joint | 0.02 | 3.5 | @ | 2 | 14 | 1 | 98 | 20 |  | Residence | 7
7 | Sheet 61032 | Level 06 | FSM-AX-WR-L6-00163 | Apart. no. 2A | Head of wall joint | 0.02 | 7.5 | @ | 2 | 14 | 1 | 210 | 20 |  | Residence | 15
8 | Sheet 61032 | Level 06 | FSM-AX-WR-L6-00163 | Apart. no. 2A | Head of wall joint | 0.02 | 10 | @ | 2 | 14 | 1 | 280 | 20 |  | Residence | 20
9 | Sheet 61032 | Level 06 | FSM-AX-WR-L6-00163 | Apart. no. 2A | Head of wall joint | 0.02 | 7.8 | @ | 2 | 14 | 1 | 218.4 | 20 |  | Residence | 15.6
10 | Sheet 61032 | Level 06 | FSM-AX-WR-L6-00163 | Corridor | Head of wall joint | 0.02 | 26 | @ | 2 | 14 | 1 | 728 | 20 |  | Residence | 52
11 | Sheet 61032 | Level 06 | FSM-AX-WR-L6-00163 | Corridor | Head of wall joint | 0.02 | 3.5 | @ | 2 | 14 | 1 | 98 | 20 |  | Residence | 7
12 | Sheet 61033 | Level 06 | FSM-AX-WR-L6-00163 | Garbage Room | Head of wall joint | 0.02 | 4 | @ | 2 | 14 | 1 | 112 | 20 | Sheet 61033 | Residence | 8
13 | Sheet 61033 | Level 06 | FSM-AX-WR-L6-00163 | Garbage Room | Head of wall joint | 0.02 | 3.5 | @ | 2 | 14 | 2 | 196 | 20 |  | Residence | 14
14 | Sheet 61033 | Level 06 | FSM-AX-WR-L6-00163 | Housekeeping | Head of wall joint | 0.02 | 3.5 | @ | 2 | 14 | 1 | 98 | 20 |  | Residence | 7
15 | Sheet 61033 | Level 06 | FSM-AX-WR-L6-00163 | Housekeeping | Head of wall joint | 0.02 | 3.5 | @ | 2 | 14 | 2 | 196 | 20 |  | Residence | 14
16 | Sheet 61033 | Level 06 | FSM-AX-WR-L6-00163 | Lift lobby | Head of wall joint | 0.02 | 4 | @ | 2 | 14 | 2 | 224 | 20 |  | Residence | 16
17 | Sheet 61033 | Level 06 | FSM-AX-WR-L6-00163 | Lift lobby | Head of wall joint | 0.02 | 2.5 | @ | 2 | 14 | 2 | 140 | 20 |  | Residence | 10
18 | Sheet 61033 | Level 06 | FSM-AX-WR-L6-00163 | FF Lobby | Head of wall joint | 0.02 | 8.5 | @ | 2 | 14 | 1 | 238 | 20 |  | Residence | 17
19 | Sheet 61033 | Level 06 | FSM-AX-WR-L6-00163 | Staircase 3&4 | Head of wall joint | 0.02 | 2.5 | @ | 2 | 14 | 2 | 140 | 20 |  | Residence | 10
20 | Sheet 61033 | Level 06 | FSM-AX-WR-L6-00163 | Staircase 3&4 | Head of wall joint | 0.02 | 3.5 | @ | 2 | 14 | 4 | 392 | 20 |  | Residence | 28
1 | Sheet 61041 | Level 04 | FSM-AX-WR-L4-00164 | FF Lobby | Head of wall joint | 0.02 | 9 | @ | 2 | 14 | 1 | 252 | 20 | Sheet 61041 | Residence | 18
2 | Sheet 61041 | Level 04 | FSM-AX-WR-L4-00164 | FF Lobby | Head of wall joint | 0.02 | 4 | @ | 2 | 14 | 2 | 224 | 20 |  | Residence | 16
3 | Sheet 61041 | Level 04 | FSM-AX-WR-L4-00164 | Chilled Room | Head of wall joint | 0.02 | 3 | @ | 2 | 14 | 1 | 84 | 20 |  | Residence | 6
4 | Sheet 61041 | Level 04 | FSM-AX-WR-L4-00164 | Chilled Room | Head of wall joint | 0.02 | 4 | @ | 2 | 14 | 2 | 224 | 20 |  | Residence | 16
5 | Sheet 61041 | Level 04 | FSM-AX-WR-L4-00164 | Passanger Lift lobby | Head of wall joint | 0.02 | 8.3 | @ | 2 | 14 | 2 | 464.8 | 20 |  | Residence | 33.2
6 | Sheet 61041 | Level 04 | FSM-AX-WR-L4-00164 | Passanger Lift lobby | Head of wall joint | 0.02 | 2.8 | @ | 2 | 14 | 4 | 313.6 | 20 |  | Residence | 22.4
7 | Sheet 61041 | Level 04 | FSM-AX-WR-L4-00164 | housekeeping | Head of wall joint | 0.02 | 5.5 | @ | 2 | 14 | 1 | 154 | 20 |  | Residence | 11
8 | Sheet 61041 | Level 04 | FSM-AX-WR-L4-00164 | housekeeping | Head of wall joint | 0.02 | 4 | @ | 2 | 14 | 1 | 112 | 20 |  | Residence | 8
9 | Sheet 61041 | Level 04 | FSM-AX-WR-L4-00164 | Garbage Room | Head of wall joint | 0.02 | 2.8 | @ | 2 | 14 | 1 | 78.4 | 20 |  | Residence | 5.6
10 | Sheet 61041 | Level 04 | FSM-AX-WR-L4-00164 | Garbage Room | Head of wall joint | 0.02 | 4 | @ | 2 | 14 | 1 | 112 | 20 |  | Residence | 8
11 | Sheet 61041 | Level 04 | FSM-AX-WR-L4-00164 | Staircase | Head of wall joint | 0.02 | 2.5 | @ | 2 | 14 | 2 | 140 | 20 |  | Residence | 10
12 | Sheet 61041 | Level 04 | FSM-AX-WR-L4-00164 | Staircase | Head of wall joint | 0.02 | 4 | @ | 2 | 14 | 4 | 448 | 20 |  | Residence | 32
1 | Sheet 61868 | Level 26 | FSM-AX-WR-L26-00167 | Lift Lobby | Head of wall joint | 0.02 | 9.8 | @ | 1 | 14 | 1 | 137.2 | 20 | Sheet 61868 | Hotel | 9.8
2 | Sheet 61868 | Level 26 | FSM-AX-WR-L26-00167 | Lift Lobby | Head of wall joint | 0.02 | 2.6 | @ | 1 | 14 | 4 | 145.6 | 20 |  | Hotel | 10.4
3 | Sheet 61868 | Level 26 | FSM-AX-WR-L26-00167 | Lift Lobby | Head of wall joint | 0.02 | 7.8 | @ | 1 | 14 | 1 | 109.2 | 20 |  | Hotel | 7.8
4 | Sheet 61868 | Level 26 | FSM-AX-WR-L26-00167 | Corridor | Head of wall joint | 0.02 | 112.7 | @ | 1 | 14 | 1 | 1577.8 | 20 |  | Hotel | 112.7
5 | Sheet 61868 | Level 26 | FSM-AX-WR-L26-00167 | Corridor | Head of wall joint | 0.02 | 3.2 | @ | 1 | 14 | 3 | 134.4 | 20 |  | Hotel | 9.6
1 | Sheet 61853 | Level 25 | FSM-AX-WR-L25-00166 | Lift Lobby | Head of wall joint | 0.02 | 9.8 | @ | 1 | 14 | 1 | 137.2 | 20 | Sheet 61853 | Hotel | 9.8
2 | Sheet 61853 | Level 25 | FSM-AX-WR-L25-00166 | Lift Lobby | Head of wall joint | 0.02 | 2.6 | @ | 1 | 14 | 4 | 145.6 | 20 |  | Hotel | 10.4
3 | Sheet 61853 | Level 25 | FSM-AX-WR-L25-00166 | Corridor | Head of wall joint | 0.02 | 127.5 | @ | 1 | 14 | 1 | 1785 | 20 |  | Hotel | 127.5
4 | Sheet 61853 | Level 25 | FSM-AX-WR-L25-00166 | Corridor | Head of wall joint | 0.02 | 3.2 | @ | 1 | 14 | 6 | 268.8 | 20 |  | Hotel | 19.2
1 | Sheet 61858 | Level 24 | FSM-AX-WR-L24-00165 | Lift Lobby | Head of wall joint | 0.02 | 9.8 | @ | 1 | 14 | 1 | 137.2 | 20 | Sheet 61858 | Hotel | 9.8
2 | Sheet 61858 | Level 24 | FSM-AX-WR-L24-00165 | Lift Lobby | Head of wall joint | 0.02 | 2.6 | @ | 1 | 14 | 4 | 145.6 | 20 |  | Hotel | 10.4
3 | Sheet 61858 | Level 24 | FSM-AX-WR-L24-00165 | Corridor | Head of wall joint | 0.02 | 7.8 | @ | 1 | 14 | 1 | 109.2 | 20 |  | Hotel | 7.8
4 | Sheet 61858 | Level 24 | FSM-AX-WR-L24-00165 | Corridor | Head of wall joint | 0.02 | 139 | @ | 1 | 14 | 1 | 1946 | 20 |  | Hotel | 139
[10 empty] | Cumulative Joints total |  | #REF!
1 | Sheet 61872 | Level 19 | WIR - 0168 | Corridor | Head of wall joint | 0.02 | 55.7 | @ | 1 | 14 | 1 | 779.8 | 20 | Sheet 61872 | Hotel | 55.7
2 | Sheet 61872 | Level 19 | WIR - 0168 | Corridor | Vertical joint | 0.02 | 3.3 | @ | 1 | 14 | 2 | 92.4 | 20 | Sheet 61872 | Hotel | 6.6
1 | Sheet 61883 | Level 27 | WIR - 0169 | Corridor | Head of wall joint | 0.02 | 122 | @ | 1 | 14 | 1 | 1708 | 20 | Sheet 61883 | Hotel | 122
2 | Sheet 61883 | Level 27 | WIR - 0169 | Corridor | Vertical joint | 0.02 | 3.5 | @ | 1 | 14 | 6 | 294 | 20 | Sheet 61883 | Hotel | 21
3 | Sheet 61883 | Level 27 | WIR - 0169 | Corridor | Head of wall joint | 0.02 | 7 | @ | 1 | 14 | 1 | 98 | 20 | Sheet 61883 | Hotel | 7
4 | Sheet 61883 | Level 27 | WIR - 0169 | Corridor | Vertical joint | 0.02 | 2.5 | @ | 1 | 14 | 4 | 140 | 20 | Sheet 61883 | Hotel | 10
1 | Sheet 61909 | Level 29 | WIR - 0172 | Electrical Room | Head of wall joint | 0.02 | 10.3 | @ | 2 | 14 | 1 | 288.4 | 20 | Sheet 61909 | Hotel | 20.6
2 | Sheet 61909 | Level 29 | WIR - 0172 | Electrical Room | Head of wall joint | 0.02 | 8.15 | @ | 2 | 14 | 1 | 228.2 | 20 |  | Hotel | 16.3
3 | Sheet 61909 | Level 29 | WIR - 0172 | Electrical Room | Vertical joint | 0.02 | 2.55 | @ | 1 | 14 | 1 | 35.7 | 20 |  | Hotel | 2.55
1 | Sheet 61913 | Ground Level | WIR - 0173 | Ball Room | Horizontal joint | 0.02 | 19.7 | @ | 1 | 14 | 1 | 275.8 | 20 | Sheet 61913 | Hotel | 19.7
2 | Sheet 61913 | Ground Level | WIR - 0173 | Ball Room | Vertical joint | 0.02 | 8 | @ | 1 | 14 | 2 | 224 | 20 |  | Hotel | 16
3 | Sheet 61913 | Ground Level | WIR - 0173 | Ball Room | Horizontal joint | 0.02 | 10.5 | @ | 1 | 14 | 1 | 147 | 20 |  | Hotel | 10.5
4 | Sheet 61913 | Ground Level | WIR - 0173 | Ball Room | Horizontal joint | 0.02 | 17 | @ | 1 | 14 | 1 | 238 | 20 |  | Hotel | 17
5 | Sheet 61913 | Ground Level | WIR - 0173 | Lobby | Horizontal joint | 0.02 | 16.8 | @ | 2 | 14 | 1 | 470.4 | 20 |  | Hotel | 33.6
6 | Sheet 61913 | Ground Level | WIR - 0173 | Lobby | Vertical joint | 0.02 | 3.5 | @ | 2 | 14 | 4 | 392 | 20 |  | Hotel | 28
7 | Sheet 61913 | Ground Level | WIR - 0173 | Lobby | Horizontal joint | 0.02 | 35.2 | @ | 1 | 14 | 1 | 492.8 | 20 |  | Hotel | 35.2
8 | Sheet 61913 | Ground Level | WIR - 0173 | Lobby | Vertical joint | 0.02 | 3.6 | @ | 1 | 14 | 6 | 302.4 | 20 |  | Hotel | 21.6
1 | Sheet 61914 | Level 01 | WIR - 0171 | Wall | Horizontal joint | 0.02 | 95 | @ | 1 | 14 | 1 | 1330 | 20 | Sheet 61914 | Hotel | 95
2 | Sheet 61914 | Level 01 | WIR - 0171 | Wall | Vertical joint | 0.02 | 4 | @ | 1 | 14 | 5 | 280 | 20 |  | Hotel | 20
3 | Sheet 61914 | Level 01 | WIR - 0171 | Wall | Vertical joint | 0.02 | 8 | @ | 1 | 14 | 3 | 336 | 20 |  | Hotel | 24
4 | Sheet 61914 | Level 01 | WIR - 0171 | Wall | Horizontal joint | 0.02 | 32 | @ | 1 | 14 | 1 | 448 | 20 |  | Hotel | 32
[10 empty] | Grand Total |  | #REF! |  |  | Total qty | 2233.65
[10 empty] | Joints Total |  | #REF!

## Joints 30mm
Project: |  |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  |  | Khansaheb Civil Engineering
Period of Completed Works: |  |  |  | up to July 2022
Summary of Completed Firestopping Works (Construction Joints)
No. | Sos Number | Level | WIR No. | Location | Type | Joint Size (in meter) |  |  | Sides | Rate (AED) | Nos | Total (AED) |  |  | Hotel / Residence | QTY | Remarks
1 | Sheet 61862 | Basement 01 | FSM-AX-WR-LB1-00170 | CEF Room | Head of wall joint | 0.03 | 20 | @ | 1 | 20 | 1 | 400 | 30 | Sheet 61862 | Residence | 20
2 | Sheet 61862 | Basement 01 | FSM-AX-WR-LB1-00170 | CEF Room | Head of wall joint | 0.03 | 6.5 | @ | 1 | 20 | 2 | 260 | 30 |  | Residence | 13
3 | Sheet 61862 | Basement 01 | FSM-AX-WR-LB1-00170 | Electrical Cabinet | Head of wall joint | 0.03 | 3 | @ | 2 | 20 | 1 | 120 | 30 |  | Residence | 6
[10 empty] | Grand Total |  | 780 |  |  | Total qty | 39

## MEP (Civil opening)
Project: |  |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  |  | Khansaheb Civil Engineering - MEP Division
Period of Completed Works: |  |  |  | September 2022 | [14 empty] | all mortar openings priced by sqm diff
Summary of Completed Firestopping Works
No. | Sos Number | Serial No | Level | WIR No. | Location | Penetrant Type | Penetrant Size (in meter) |  | SquareMeters | Opening Size (in meter) |  | SquareMeters | Diffirence | Sides | Rate (AED) | Nos | Total (AED) |  |  | Hotel / Residence | QTY
Residence
September 2022 - Residence | [19 empty] | Residence
1 | Sheet 61906 |  | Level 23 | WIR - 00892 | Water Meter Room | PPR pipe | 8" |  | 0.032349 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750/FP302/FS709 | Sheet 61906 | Residence | 2 | 8 | 25.4 | 203.2 | 0.032442 | 1 | 0.032442
2 | Sheet 61906 |  | Level 23 | WIR - 00892 | Water Meter Room | PVC pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750/FP302/FS709 |  | Residence | 2 | 6 | 25.4 | 152.4 | 0.018249 | 1 | 0.018249
3 | Sheet 61906 |  | Level 23 | WIR - 00892 | Water Meter Room | CDP pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750/FP302/FS709 |  | Residence | 2 | 2 | 25.4 | 50.8 | 0.0020276 | 1 | 0.0020276
4 | Sheet 61906 |  | Level 23 | WIR - 00892 | Water Meter Room | metal pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750/FP302/FS709 |  | Residence | 4 | 6 | 25.4 | 152.4 | 0.018249 | 2 | 0.036498
5 | Sheet 61906 |  | Level 23 | WIR - 00892 | Water Meter Room | metal pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750/FP302/FS709 |  | Residence | 4 | 4 | 25.4 | 101.6 | 0.0081106 | 2 | 0.016221
6 | Sheet 61906 |  | Level 23 | WIR - 00892 | Water Meter Room | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 3 | 0 | FS702/FB750/FP302/FS709 |  | Residence | 6 | 1 | 25.4 | 25.4 | 0.00050691 | 3 | 0.0015207 | 0.10696
7 | Sheet 61906 |  | Level 23 | WIR - 00892 | Water Meter Room | opening |  |  |  | 0.35 | 1.65 | 0.5775 | 0.47054 | 2 | 310 | 1 | 620 | FS702/FB750/FP302/FS709 |  | Residence | 2
Hotel
September 2022 - Hotel | [19 empty] | Hotel
1 | Sheet 61907 | 1 | Level 29 | WIR - 00950 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750 | Sheet 61907 | Hotel | 4 |  |  |  | 0.01 | 2 | 0.02
2 | Sheet 61907 | 2 | Level 29 | WIR - 00950 | Electrical Room | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2 |  |  |  | 0.01 | 1 | 0.01
3 | Sheet 61907 | 3 | Level 29 | WIR - 00950 | Electrical Room | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750/FS709 |  | Hotel | 4 | 1 | 25.4 | 25.4 | 0.00050691 | 2 | 0.0010138 | 0.031014
4 | Sheet 61907 | 3 | Level 29 | WIR - 00950 | Electrical Room | opening |  |  |  | 0.3 | 0.4 | 0.12 | 0.088986 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
5 | Sheet 61907 | 4 | Level 29 | WIR - 00950 | Electrical Room | duct | 0.2 | 0.4 | 0.08 | 0.3 | 0.46 | 0.138 |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
6 | Sheet 61907 | 5 | Level 29 | WIR - 00950 | Electrical Room | cable trunking | 0.05 | 0.05 | 0.0025 | 0.15 | 0.15 | 0.0225 | 0.0225 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
7 | Sheet 61907 | 6 | Level 29 | WIR - 00950 | Electrical Room | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
8 | Sheet 61907 | 7 | Level 29 | WIR - 00950 | Electrical Room | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750/FS709 |  | Hotel | 2
9 | Sheet 61907 | 7 | Level 29 | WIR - 00950 | Electrical Room | opening |  |  |  | 0.2 | 0.2 | 0.04 | 0.027009 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
10 | Sheet 61907 | 8 | Level 29 | WIR - 00950 | Telephone Room | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
11 | Sheet 61907 | 9 | Level 29 | WIR - 00950 | Telephone Room | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750/FS709 |  | Hotel | 4
12 | Sheet 61907 | 9 | Level 29 | WIR - 00950 | Telephone Room | opening |  |  |  | 0.2 | 0.2 | 0.04 | 0.029509 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
13 | Sheet 61907 | 10 | Level 29 | WIR - 00950 | Telephone Room | cable trunking | 0.07 | 0.07 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
14 | Sheet 61907 | 11 | Level 29 | WIR - 00950 | Telephone Room | duct | 0.2 | 0.4 | 0.08 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
15 | Sheet 61907 | 12 | Level 29 | WIR - 00950 | Telephone Room | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750/FS709 |  | Hotel | 4
16 | Sheet 61907 | 12 | Level 29 | WIR - 00950 | Telephone Room | opening |  |  |  | 0.3 | 0.6 | 0.18 | 0.089509 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
17 | Sheet 61907 | 13 | Level 29 | WIR - 00950 | Telephone Room | cable trunking | 0.1 | 0.1 | 0.01 | 0.15 | 0.17 | 0.0255 | 0.0255 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
18 | Sheet 61907 | 14 | Level 29 | WIR - 00950 | Telephone Room | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
19 | Sheet 61907 | 15 | Level 29 | WIR - 00950 | Telephone Room | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 3 | 0 | FS702/FB750/FS709 |  | Hotel | 6
20 | Sheet 61907 | 15 | Level 29 | WIR - 00950 | Telephone Room | opening |  |  |  | 0.2 | 0.25 | 0.05 | 0.039509 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
21 | Sheet 61907 | 16 | Level 29 | WIR - 00950 | Telephone Room | conduit pipe | 1" |  |  | 2" |  |  |  | 2 |  | 6 | 0 | FS709 |  | Hotel | 12
22 | Sheet 61907 | 17 | Level 29 | WIR - 00950 | Telephone Room | GSM pipe | 0.5" |  |  | 1.5" |  |  |  | 2 |  | 2 | 0 | FS709 |  | Hotel | 4
23 | Sheet 61907 | 18 | Level 29 | WIR - 00950 | Male Toilet | duct | 0.2 | 0.4 | 0.08 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
24 | Sheet 61907 | 18 | Level 29 | WIR - 00950 | Male Toilet | opening |  |  |  | 0.3 | 0.48 | 0.144 | 0.064 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
25 | Sheet 61907 | 19 | Level 29 | WIR - 00950 | Male Toilet | duct | 0.2 | 0.4 | 0.08 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
26 | Sheet 61907 | 19 | Level 29 | WIR - 00950 | Male Toilet | opening |  |  |  | 0.3 | 0.48 | 0.144 | 0.064 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
27 | Sheet 61907 | 20 | Level 29 | WIR - 00950 | Male Toilet | CHW pipe | 3" |  |  | 5" |  |  |  | 2 |  | 2 | 0 | FS709 |  | Hotel | 4 | 1 | 25.4 | 25.4 | 0.00050691 | 2 | 0.0010138
28 | Sheet 61907 | 21 | Level 29 | WIR - 00950 | Male Toilet | PVC pipe | 4" |  |  | 6" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
29 | Sheet 61907 | 22 | Level 29 | WIR - 00950 | Male Toilet | cable trunking | 0.07 | 0.07 | 0.0049 | 0.15 | 0.2 | 0.03 | 0.03 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
30 | Sheet 61907 | 23 | Level 29 | WIR - 00950 | Male Toilet | PPR pipe | 2" |  |  | 4" |  |  |  | 2 |  | 3 | 0 | FS702/FP302 |  | Hotel | 6
31 | Sheet 61907 | 24 | Level 29 | WIR - 00950 | Male Toilet | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 3 | 0 | FS702/FB750/FS709 |  | Hotel | 6 | 1 | 25.4 | 25.4 | 0.00050691 | 3 | 0.0015207
32 | Sheet 61907 | 24 | Level 29 | WIR - 00950 | Male Toilet | opening |  |  |  | 0.2 | 0.8 | 0.16 | 0.15848 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2
33 | Sheet 61907 | 25 | Level 29 | WIR - 00950 | Male Toilet | conduit pipe | 1" |  |  | 2" |  |  |  | 2 |  | 3 | 0 | FS709 |  | Hotel | 6
Hotel
September 2022 - Hotel | [19 empty] | Hotel
1 | Sheet 61908 | 26 | Level 29 | WIR - 00950 | Male Toilet | CHW pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750/FS709 | Sheet 61908 | Hotel | 4 | 1 | 25.4 | 25.4 | 0.00050691 | 2 | 0.0010138
2 | Sheet 61908 | 27 | Level 29 | WIR - 00950 | Male Toilet | fire fighting pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750/FS709 |  | Hotel | 2 |  |  |  | 0.00049063 | 1 | 0.00049063
3 | Sheet 61908 | 28 | Level 29 | WIR - 00950 | Male Toilet | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750/FS709 |  | Hotel | 2 | 1 | 25.4 | 25.4 | 0.00050691 | 1 | 0.00050691 | 0.0020114
4 | Sheet 61908 | 29 | Level 29 | WIR - 00950 | Male Toilet | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 8 | 0 | FS702/FB750/FS709 |  | Hotel | 16
5 | Sheet 61908 | 29 | Level 29 | WIR - 00950 | Male Toilet | opening |  |  |  | 0.25 | 1.5 | 0.375 | 0.37299 | 2 | 310 | 1 | 620 | FS702/FB750/FS709 |  | Hotel | 2
Hotel
September 2022 - Hotel | [19 empty] | Hotel
1 | Sheet 61910 | 1 | Basement 01 | WIR - 0977 | Corridor, Entry D. | cable tray | 0.05 | 0.15 | 0.0075 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 | Sheet 61910 | Hotel | 2
2 | Sheet 61910 | 2 | Basement 01 | WIR - 0977 | Corridor, Entry D. | cable trunking | 0.15 | 0.15 | 0.0225 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
3 | Sheet 61910 | 3 | Basement 01 | WIR - 0977 | Corridor, Entry D. | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
4 | Sheet 61910 | 3 | Basement 01 | WIR - 0977 | Corridor, Entry D. | opening |  |  |  | 0.6 | 0.8 | 0.48 | 0.44 | 2 | 310 | 1 | 620 | FS702/FB750 |  | Hotel | 2
5 | Sheet 61910 | 4 | Basement 01 | WIR - 0977 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  |  | 2 |  | 2 | 0 | FS702/FP302 |  | Hotel | 4
6 | Sheet 61910 | 5 | Basement 01 | WIR - 0977 | Corridor, Entry D. | PPR pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
7 | Sheet 61910 | 6 | Basement 01 | WIR - 0977 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  |  | 2 |  | 2 | 0 | FS709 |  | Hotel | 4
8 | Sheet 61910 | 7 | Basement 01 | WIR - 0977 | Corridor, Entry D. | CDP pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
9 | Sheet 61910 | 8 | Basement 01 | WIR - 0977 | Corridor, Entry D. | duct | 0.35 | 0.35 | 0.1225 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
10 | Sheet 61910 | 8 | Basement 01 | WIR - 0977 | Corridor, Entry D. | opening |  |  |  | 0.45 | 0.45 | 0.2025 | 0.08 | 2 | 95 | 1 | 190 | FS702/FB750 |  | Hotel | 2
11 | Sheet 61910 | 9 | Basement 01 | WIR - 0977 | Corridor, Entry D. | conduit pipe | 1" |  |  | 2" |  |  |  | 2 |  | 4 | 0 | FS709 |  | Hotel | 8
12 | Sheet 61910 | 10 | Basement 01 | WIR - 0977 | Corridor, Entry D. | cable tray | 0.05 | 0.15 | 0.0075 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
13 | Sheet 61910 | 11 | Basement 01 | WIR - 0977 | Corridor, Entry D. | cable trunking | 0.15 | 0.15 | 0.0225 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
14 | Sheet 61910 | 12 | Basement 01 | WIR - 0977 | Corridor, Entry D. | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
15 | Sheet 61910 | 13 | Basement 01 | WIR - 0977 | Corridor, Entry D. | PPR pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750/FP302/FS709 |  | Hotel | 2
16 | Sheet 61910 | 13 | Basement 01 | WIR - 0977 | Corridor, Entry D. | opening |  |  |  | 0.55 | 1.5 | 0.825 | 0.78304 | 2 | 400 | 1 | 800 | FS702/FB750 |  | Hotel | 2
17 | Sheet 61910 | 14 | Basement 01 | WIR - 0977 | Corridor, Entry D. | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
18 | Sheet 61910 | 15 | Basement 01 | WIR - 0977 | Corridor, Entry D. | CHW pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750/FS709 |  | Hotel | 4
19 | Sheet 61910 | 16 | Basement 01 | WIR - 0977 | Corridor, Entry D. | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750/FS709 |  | Hotel | 2
20 | Sheet 61910 | 16 | Basement 01 | WIR - 0977 | Corridor, Entry D. | opening |  |  |  | 0.35 | 0.6 | 0.21 | 0.19009 | 2 | 180 | 1 | 360 | FS702/FB750 |  | Hotel | 2
21 | Sheet 61910 | 17 | Basement 01 | WIR - 0977 | Corridor, Entry D. | cable tray | 0.05 | 0.3 | 0.015 | 0.1 | 0.4 | 0.04 | 0.025 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
22 | Sheet 61910 | 18 | Basement 01 | WIR - 0977 | Corridor, Entry D. | duct | 0.2 | 0.4 | 0.08 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2
23 | Sheet 61910 | 18 | Basement 01 | WIR - 0977 | Corridor, Entry D. | opening |  |  |  | 0.25 | 0.5 | 0.125 | 0.045 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
24 | Sheet 61910 | 19 | Basement 01 | WIR - 0977 | Corridor, Entry D. | fire fighting pipe | 4" |  |  | 6" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
25 | Sheet 61910 | 20 | Basement 01 | WIR - 0977 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  |  | 2 |  | 2 | 0 | FS702/FP302 |  | Hotel | 4
26 | Sheet 61910 | 21 | Basement 01 | WIR - 0977 | Corridor, Entry D. | conduit pipe | 1" |  |  | 2" |  |  |  | 2 |  | 8 | 0 | FS709 |  | Hotel | 16
Hotel
September 2022 - Hotel | [19 empty] | Hotel
1 | Sheet 61911 | 22 | Basement 01 | WIR - 0977 | Corridor, Entry D. | CHW pipe | 3" |  | 0.0044156 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750/FS709 | Sheet 61911 | Hotel | 4 | 1 | 25.4 | 25.4 | 0.00050691 | 2 | 0.0010138
2 | Sheet 61911 | 23 | Basement 01 | WIR - 0977 | Corridor, Entry D. | PVC pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 4 | 0 | FS702/FB750/FP302/FS709 |  | Hotel | 8 | 1 | 25.4 | 25.4 | 0.00050691 | 4 | 0.0020276
3 | Sheet 61911 | 24 | Basement 01 | WIR - 0977 | Corridor, Entry D. | fire fighting pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2 | 1 | 25.4 | 25.4 | 0.00050691 | 1 | 0.00050691
4 | Sheet 61911 | 25 | Basement 01 | WIR - 0977 | Corridor, Entry D. | PPR pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750/FP302/FS709 |  | Hotel | 2 | 1 | 25.4 | 25.4 | 0.00050691 | 1 | 0.00050691
5 | Sheet 61911 | 26 | Basement 01 | WIR - 0977 | Corridor, Entry D. | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2 |  |  |  | 0.01 | 1 | 0.01
6 | Sheet 61911 | 27 | Basement 01 | WIR - 0977 | Corridor, Entry D. | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 6 | 0 | FS702/FB750/FS709 |  | Hotel | 12 | 1 | 25.4 | 25.4 | 0.00050691 | 6 | 0.0030415
7 | Sheet 61911 | 28 | Basement 01 | WIR - 0977 | Corridor, Entry D. | duct | 0.2 | 0.2 | 0.04 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750 |  | Hotel | 2 |  |  |  | 0.04 | 1 | 0.04 | 0.057097
8 | Sheet 61911 | 29 | Basement 01 | WIR - 0977 | Corridor, Entry D. | opening |  |  |  | 0.85 | 3.25 | 2.7625 | 2.7054 | 2 | 450 | 1 | 2434.8629 | FS702/FB750 |  | Hotel | 5.4108
9 | Sheet 61911 | 30 | Basement 01 | WIR - 0977 | Corridor, Entry D. | duct | 0.2 | 0.4 | 0.08 | 0.26 | 0.46 | 0.1196 |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
10 | Sheet 61911 | 31 | Basement 01 | WIR - 0977 | Corridor, Entry D. | duct | 0.2 | 0.5 | 0.1 | 0.26 | 0.56 | 0.1456 |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
11 | Sheet 61911 | 32 | Basement 01 | WIR - 0977 | Corridor, Entry D. | CHW pipe | 2" |  |  | 4" |  |  |  | 2 |  | 2 | 0 | FS709 |  | Hotel | 4
12 | Sheet 61911 | 33 | Basement 01 | WIR - 0977 | Corridor, Entry D. | conduit pipe | 1" |  |  | 2" |  |  |  | 2 |  | 5 | 0 | FS709 |  | Hotel | 10
13 | Sheet 61911 | 34 | Basement 01 | WIR - 0977 | Corridor, Entry D. | CDP pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 | FS702/FP302 |  | Hotel | 2
14 | Sheet 61911 | 35 | Basement 01 | WIR - 0977 | Corridor, Entry D. | PPR pipe | 2" |  |  | 4" |  |  |  | 2 |  | 3 | 0 | FS702/FP302 |  | Hotel | 6
15 | Sheet 61911 | 36 | Basement 01 | WIR - 0977 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  |  | 2 |  | 1 | 0 | FS702 |  | Hotel | 2
16 | Sheet 61911 | 37 | Basement 01 | WIR - 0977 | Corridor, Entry D. | cable tray | 0.05 | 0.1 | 0.005 | 0.09 | 0.16 | 0.0144 | 0.0094 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
17 | Sheet 61911 | 38 | Basement 01 | WIR - 0977 | Corridor, Entry D. | cable trunking | 0.1 | 0.1 | 0.01 | 0.15 | 0.15 | 0.0225 | 0.0125 | 2 | 50 | 1 | 100 | FS702/FB750 |  | Hotel | 2
Residence
September 2022 - Residence | [19 empty] | Residence
1 | Sheet 61912 |  | Level 13 | WIR - 01133 | Water Meter Room | PPR pipe | 8" |  | 0.032349 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750/FP302/FS709 | Sheet 61912 | Residence | 2 | 1 | 25.4 | 25.4 | 0.00050691 | 1 | 0.00050691
2 | Sheet 61912 |  | Level 13 | WIR - 01133 | Water Meter Room | PVC pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750/FP302/FS709 |  | Residence | 2 | 1 | 25.4 | 25.4 | 0.00050691 | 1 | 0.00050691
3 | Sheet 61912 |  | Level 13 | WIR - 01133 | Water Meter Room | CDP pipe | 2" |  | 0.0019625 |  |  |  |  | 2 |  | 1 | 0 | FS702/FB750/FP302/FS709 |  | Residence | 2 | 1 | 25.4 | 25.4 | 0.00050691 | 1 | 0.00050691
4 | Sheet 61912 |  | Level 13 | WIR - 01133 | Water Meter Room | insulated metal pipe | 6" |  | 0.017662 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750/FP302/FS709 |  | Residence | 4 | 1 | 25.4 | 25.4 | 0.00050691 | 2 | 0.0010138
5 | Sheet 61912 |  | Level 13 | WIR - 01133 | Water Meter Room | insulated metal pipe | 4" |  | 0.00785 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750/FP302/FS709 |  | Residence | 4 | 1 | 25.4 | 25.4 | 0.00050691 | 2 | 0.0010138
6 | Sheet 61912 |  | Level 13 | WIR - 01133 | Water Meter Room | conduit pipe | 1" |  | 0.00049063 |  |  |  |  | 2 |  | 2 | 0 | FS702/FB750/FP302/FS709 |  | Residence | 4 | 1 | 25.4 | 25.4 | 0.00050691 | 2 | 0.0010138 | 0.0045622
7 | Sheet 61912 |  | Level 13 | WIR - 01133 | Water Meter Room | opening |  |  |  | 0.35 | 1.65 | 0.5775 | 0.57294 | 2 | 310 | 1 | 620 | FS702/FB750/FP302/FS709 |  | Residence | 2
Hotel
September 2022 - Hotel | [19 empty] | Hotel
1 | Sheet 61916 | 5 | Level 22 | WIR - 01153 | FTR Room | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 3 | 0 | FR230 | Sheet 61916 | Hotel | 3 |  |  |  | 0.015 | 3 | 0.045
2 | Sheet 61916 | 5 | Level 22 | WIR - 01153 | FTR Room | cable tray | 0.05 | 0.5 | 0.025 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.025 | 1 | 0.025
3 | Sheet 61916 | 5 | Level 22 | WIR - 01153 | FTR Room | cable trunking | 0.15 | 0.15 | 0.0225 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.0225 | 1 | 0.0225
4 | Sheet 61916 | 5 | Level 22 | WIR - 01153 | FTR Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.01 | 1 | 0.01
5 | Sheet 61916 | 5 | Level 22 | WIR - 01153 | FTR Room | cable trunking | 0.05 | 0.07 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR230 |  | Hotel | 2 |  |  |  | 0.01 | 2 | 0.02 | 0.1225
6 | Sheet 61916 | 5 | Level 22 | WIR - 01153 | FTR Room | opening Mortar |  |  |  | 0.35 | 1.8 | 0.63 | 0.5075 | 1 | 680 | 1 | 345.1 | FR230 |  | Hotel | 0.5075
7 | Sheet 61916 | 6 | Level 23 | WIR - 01154 | FTR Room | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 3 | 0 | FR230 |  | Hotel | 3 |  |  |  | 0.015 | 3 | 0.045
8 | Sheet 61916 | 6 | Level 23 | WIR - 01154 | FTR Room | cable tray | 0.05 | 0.5 | 0.025 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.025 | 1 | 0.025
9 | Sheet 61916 | 6 | Level 23 | WIR - 01154 | FTR Room | cable trunking | 0.15 | 0.15 | 0.0225 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.0225 | 1 | 0.0225
10 | Sheet 61916 | 6 | Level 23 | WIR - 01154 | FTR Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.01 | 1 | 0.01
11 | Sheet 61916 | 6 | Level 23 | WIR - 01154 | FTR Room | cable trunking | 0.05 | 0.07 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR230 |  | Hotel | 2 |  |  |  | 0.01 | 2 | 0.02 | 0.1225
12 | Sheet 61916 | 6 | Level 23 | WIR - 01154 | FTR Room | opening Mortar |  |  |  | 0.35 | 1.8 | 0.63 | 0.5075 | 1 | 680 | 1 | 345.1 | FR230 |  | Hotel | 0.5075
13 | Sheet 61916 | 7 | Level 24 | WIR - 01155 | FTR Room | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 3 | 0 | FR230 |  | Hotel | 3 |  |  |  | 0.015 | 3 | 0.045
14 | Sheet 61916 | 7 | Level 24 | WIR - 01155 | FTR Room | cable tray | 0.05 | 0.5 | 0.025 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.025 | 1 | 0.025
15 | Sheet 61916 | 7 | Level 24 | WIR - 01155 | FTR Room | cable trunking | 0.15 | 0.15 | 0.0225 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.0225 | 1 | 0.0225
16 | Sheet 61916 | 7 | Level 24 | WIR - 01155 | FTR Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.01 | 1 | 0.01
17 | Sheet 61916 | 7 | Level 24 | WIR - 01155 | FTR Room | cable trunking | 0.05 | 0.07 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR230 |  | Hotel | 2 |  |  |  | 0.01 | 2 | 0.02 | 0.1225
18 | Sheet 61916 | 7 | Level 24 | WIR - 01155 | FTR Room | opening Mortar |  |  |  | 0.35 | 1.8 | 0.63 | 0.5075 | 1 | 680 | 1 | 345.1 | FR230 |  | Hotel | 0.5075
19 | Sheet 61916 | 8 | Level 25 | WIR - 01156 | FTR Room | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 3 | 0 | FR230 |  | Hotel | 3 |  |  |  | 0.015 | 3 | 0.045
20 | Sheet 61916 | 8 | Level 25 | WIR - 01156 | FTR Room | cable tray | 0.05 | 0.5 | 0.025 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.025 | 1 | 0.025
21 | Sheet 61916 | 8 | Level 25 | WIR - 01156 | FTR Room | cable trunking | 0.15 | 0.15 | 0.0225 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.0225 | 1 | 0.0225
22 | Sheet 61916 | 8 | Level 25 | WIR - 01156 | FTR Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.01 | 1 | 0.01
23 | Sheet 61916 | 8 | Level 25 | WIR - 01156 | FTR Room | cable trunking | 0.05 | 0.07 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR230 |  | Hotel | 2 |  |  |  | 0.01 | 2 | 0.02 | 0.1225
24 | Sheet 61916 | 8 | Level 25 | WIR - 01156 | FTR Room | opening Mortar |  |  |  | 0.35 | 1.8 | 0.63 | 0.5075 | 1 | 680 | 1 | 345.1 | FR230 |  | Hotel | 0.5075
Hotel
September 2022 - Hotel | [19 empty] | Hotel
1 | Sheet 61915 | 1 | Level 18 | WIR - 01149 | FTR Room | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 3 | 0 | FR230 | Sheet 61915 | Hotel | 3 |  |  |  | 0.015 | 3 | 0.045
2 | Sheet 61915 | 1 | Level 18 | WIR - 01149 | FTR Room | cable tray | 0.05 | 0.5 | 0.025 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.025 | 1 | 0.025
3 | Sheet 61915 | 1 | Level 18 | WIR - 01149 | FTR Room | cable trunking | 0.15 | 0.15 | 0.0225 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.0225 | 1 | 0.0225
4 | Sheet 61915 | 1 | Level 18 | WIR - 01149 | FTR Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.01 | 1 | 0.01
5 | Sheet 61915 | 1 | Level 18 | WIR - 01149 | FTR Room | cable trunking | 0.05 | 0.07 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR230 |  | Hotel | 2 |  |  |  | 0.01 | 2 | 0.02 | 0.1225
6 | Sheet 61915 | 1 | Level 18 | WIR - 01149 | FTR Room | opening Mortar |  |  |  | 0.35 | 1.8 | 0.63 | 0 | 1 | 680 | 1 | 0 | FR230 |  | Hotel | 0
7 | Sheet 61915 | 2 | Level 19 | WIR - 01150 | FTR Room | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 3 | 0 | FR230 |  | Hotel | 3 |  |  |  | 0.015 | 3 | 0.045
8 | Sheet 61915 | 2 | Level 19 | WIR - 01150 | FTR Room | cable tray | 0.05 | 0.5 | 0.025 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.025 | 1 | 0.025
9 | Sheet 61915 | 2 | Level 19 | WIR - 01150 | FTR Room | cable trunking | 0.15 | 0.15 | 0.0225 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.0225 | 1 | 0.0225
10 | Sheet 61915 | 2 | Level 19 | WIR - 01150 | FTR Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.01 | 1 | 0.01
11 | Sheet 61915 | 2 | Level 19 | WIR - 01150 | FTR Room | cable trunking | 0.05 | 0.07 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR230 |  | Hotel | 2 |  |  |  | 0.01 | 2 | 0.02 | 0.1225
12 | Sheet 61915 | 2 | Level 19 | WIR - 01150 | FTR Room | opening Mortar |  |  |  | 0.35 | 1.8 | 0.63 | 0 | 1 | 680 | 1 | 0 | FR230 |  | Hotel | 0
13 | Sheet 61915 | 3 | Level 20 | WIR - 01151 | FTR Room | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 3 | 0 | FR230 |  | Hotel | 3 |  |  |  | 0.015 | 3 | 0.045
14 | Sheet 61915 | 3 | Level 20 | WIR - 01151 | FTR Room | cable tray | 0.05 | 0.5 | 0.025 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.025 | 1 | 0.025
15 | Sheet 61915 | 3 | Level 20 | WIR - 01151 | FTR Room | cable trunking | 0.15 | 0.15 | 0.0225 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.0225 | 1 | 0.0225
16 | Sheet 61915 | 3 | Level 20 | WIR - 01151 | FTR Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.01 | 1 | 0.01
17 | Sheet 61915 | 3 | Level 20 | WIR - 01151 | FTR Room | cable trunking | 0.05 | 0.07 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR230 |  | Hotel | 2 |  |  |  | 0.01 | 2 | 0.02 | 0.1225
18 | Sheet 61915 | 3 | Level 20 | WIR - 01151 | FTR Room | opening Mortar |  |  |  | 0.35 | 1.8 | 0.63 | 0.5075 | 1 | 680 | 1 | 345.1 | FR230 |  | Hotel | 0.5075
19 | Sheet 61915 | 4 | Level 21 | WIR - 01152 | FTR Room | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 3 | 0 | FR230 |  | Hotel | 3 |  |  |  | 0.015 | 3 | 0.045
20 | Sheet 61915 | 4 | Level 21 | WIR - 01152 | FTR Room | cable tray | 0.05 | 0.5 | 0.025 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.025 | 1 | 0.025
21 | Sheet 61915 | 4 | Level 21 | WIR - 01152 | FTR Room | cable trunking | 0.15 | 0.15 | 0.0225 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.0225 | 1 | 0.0225
22 | Sheet 61915 | 4 | Level 21 | WIR - 01152 | FTR Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.01 | 1 | 0.01
23 | Sheet 61915 | 4 | Level 21 | WIR - 01152 | FTR Room | cable trunking | 0.05 | 0.07 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR230 |  | Hotel | 2 |  |  |  | 0.01 | 2 | 0.02 | 0.1225
24 | Sheet 61915 | 4 | Level 21 | WIR - 01152 | FTR Room | opening Mortar |  |  |  | 0.35 | 1.8 | 0.63 | 0.5075 | 1 | 680 | 1 | 345.1 | FR230 |  | Hotel | 0.5075
Hotel
September 2022 - Hotel | [19 empty] | Hotel
1 | Sheet 61917 | 9 | Level 26 | WIR - 01157 | FTR Room | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 3 | 0 | FR230 | Sheet 61917 | Hotel | 3 |  |  |  | 0.015 | 3 | 0.045
2 | Sheet 61917 | 9 | Level 26 | WIR - 01157 | FTR Room | cable tray | 0.05 | 0.5 | 0.025 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.025 | 1 | 0.025
3 | Sheet 61917 | 9 | Level 26 | WIR - 01157 | FTR Room | cable trunking | 0.15 | 0.15 | 0.0225 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.0225 | 1 | 0.0225
4 | Sheet 61917 | 9 | Level 26 | WIR - 01157 | FTR Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.01 | 1 | 0.01
5 | Sheet 61917 | 9 | Level 26 | WIR - 01157 | FTR Room | cable trunking | 0.05 | 0.07 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR230 |  | Hotel | 2 |  |  |  | 0.01 | 2 | 0.02 | 0.1225
6 | Sheet 61917 | 9 | Level 26 | WIR - 01157 | FTR Room | opening Mortar |  |  |  | 0.35 | 1.8 | 0.63 | 0.5075 | 1 | 680 | 1 | 345.1 | FR230 |  | Hotel | 0.5075
7 | Sheet 61917 | 10 | Level 27 | WIR - 01158 | FTR Room | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 3 | 0 | FR230 |  | Hotel | 3 |  |  |  | 0.015 | 3 | 0.045
8 | Sheet 61917 | 10 | Level 27 | WIR - 01158 | FTR Room | cable tray | 0.05 | 0.5 | 0.025 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.025 | 1 | 0.025
9 | Sheet 61917 | 10 | Level 27 | WIR - 01158 | FTR Room | cable trunking | 0.15 | 0.15 | 0.0225 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.0225 | 1 | 0.0225
10 | Sheet 61917 | 10 | Level 27 | WIR - 01158 | FTR Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.01 | 1 | 0.01
11 | Sheet 61917 | 10 | Level 27 | WIR - 01158 | FTR Room | cable trunking | 0.05 | 0.07 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR230 |  | Hotel | 2 |  |  |  | 0.01 | 2 | 0.02 | 0.1225
12 | Sheet 61917 | 10 | Level 27 | WIR - 01158 | FTR Room | opening Mortar |  |  |  | 0.35 | 1.8 | 0.63 | 0.5075 | 1 | 680 | 1 | 345.1 | FR230 |  | Hotel | 0.5075
13 | Sheet 61917 | 11 | Level 28 | WIR - 01159 | FTR Room | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 3 | 0 | FR230 |  | Hotel | 3 |  |  |  | 0.015 | 3 | 0.045
14 | Sheet 61917 | 11 | Level 28 | WIR - 01159 | FTR Room | cable tray | 0.05 | 0.5 | 0.025 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.025 | 1 | 0.025
15 | Sheet 61917 | 11 | Level 28 | WIR - 01159 | FTR Room | cable trunking | 0.15 | 0.15 | 0.0225 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.0225 | 1 | 0.0225
16 | Sheet 61917 | 11 | Level 28 | WIR - 01159 | FTR Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.01 | 1 | 0.01
17 | Sheet 61917 | 11 | Level 28 | WIR - 01159 | FTR Room | cable trunking | 0.05 | 0.07 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR230 |  | Hotel | 2 |  |  |  | 0.01 | 2 | 0.02 | 0.1225
18 | Sheet 61917 | 11 | Level 28 | WIR - 01159 | FTR Room | opening Mortar |  |  |  | 0.35 | 1.8 | 0.63 | 0.5075 | 1 | 680 | 1 | 345.1 | FR230 |  | Hotel | 0.5075
19 | Sheet 61917 | 12 | Level 29 | WIR - 01160 | FTR Room | cable tray | 0.05 | 0.3 | 0.015 |  |  |  |  | 1 |  | 3 | 0 | FR230 |  | Hotel | 3 |  |  |  | 0.015 | 3 | 0.045
20 | Sheet 61917 | 12 | Level 29 | WIR - 01160 | FTR Room | cable tray | 0.05 | 0.5 | 0.025 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.025 | 1 | 0.025
21 | Sheet 61917 | 12 | Level 29 | WIR - 01160 | FTR Room | cable trunking | 0.15 | 0.15 | 0.0225 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.0225 | 1 | 0.0225
22 | Sheet 61917 | 12 | Level 29 | WIR - 01160 | FTR Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  |  | 1 |  | 1 | 0 | FR230 |  | Hotel | 1 |  |  |  | 0.01 | 1 | 0.01
23 | Sheet 61917 | 12 | Level 29 | WIR - 01160 | FTR Room | cable trunking | 0.05 | 0.07 | 0.01 |  |  |  |  | 1 |  | 2 | 0 | FR230 |  | Hotel | 2 |  |  |  | 0.01 | 2 | 0.02 | 0.1225
24 | Sheet 61917 | 12 | Level 29 | WIR - 01160 | FTR Room | opening Mortar |  |  |  | 0.35 | 1.8 | 0.63 | 0.5075 | 1 | 680 | 1 | 345.1 | FR230 |  | Hotel | 0.5075
[15 empty] | Grand Total |  | 11835.8629 | 12843.8369 | -1007.974 |  | 422.4858
WIR List as per SOS
[5 empty] | Level 23 | WIR - 00892
[5 empty] | Basement 01 | WIR - 0977 | [8 empty] | MEP |  | 11835.8629
[5 empty] | Level 22 | WIR - 01153
[5 empty] | Level 23 | WIR - 01154
[5 empty] | Level 24 | WIR - 01155
[5 empty] | Level 25 | WIR - 01156
[5 empty] | Level 18 | WIR - 01149 | No WIR
[5 empty] | Level 19 | WIR - 01150 | No WIR
[5 empty] | Level 20 | WIR - 01151
[5 empty] | Level 21 | WIR - 01152
[5 empty] | Level 26 | WIR - 01157
[5 empty] | Level 27 | WIR - 01158
[5 empty] | Level 28 | WIR - 01159
[5 empty] | Level 29 | WIR - 01160
[5 empty] | Level 29 | WIR - 00950
[5 empty] | Level 13 | WIR - 01133
Note on N149: Himal Kosala: No WIR
Note on N155: Himal Kosala: No WIR

## civil opening (hidden)
Project: |  |  |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  |  |  | Khansaheb Civil Engineering
Period of Completed Works: |  |  |  |  | up to July 2022
Summary of Completed Firestopping Works
No. | Sos Number | Serial No | Level | WIR No. | Location | Penetrant Type | Penetrant Size (in meter) | SquareMeters | Opening Size (in meter) |  | SquareMeters | Diffirence | Sides | Rate (AED) | Nos | Total (AED) |  | Hotel / Residence | QTY
6 | Sheet 61907 | 5 | Level 29 | WIR - 01160 | Electrical Room | cable trunking |  |  | 0.15 | 0.15 | 0.0225 |  | 2 | 50 | 1 | 100 | FS702/FB750 | Hotel | 2
9 | Sheet 61907 | 7 | Level 29 | WIR - 01160 | Electrical Room | opening |  |  | 0.2 | 0.2 | 0.04 | 0.029509 | 2 | 50 | 1 | 100 | FS702/FB750 | Hotel | 2
12 | Sheet 61907 | 9 | Level 29 | WIR - 01160 | Telephone Room | opening |  |  | 0.2 | 0.2 | 0.04 | 0.029509 | 2 | 50 | 1 | 100 | FS702/FB750 | Hotel | 2
17 | Sheet 61907 | 13 | Level 29 | WIR - 01160 | Telephone Room | cable trunking |  |  | 0.15 | 0.17 | 0.0255 |  | 2 | 50 | 1 | 100 | FS702/FB750 | Hotel | 2
20 | Sheet 61907 | 15 | Level 29 | WIR - 01160 | Telephone Room | opening |  |  | 0.2 | 0.25 | 0.05 | 0.039509 | 2 | 50 | 1 | 100 | FS702/FB750 | Hotel | 2
29 | Sheet 61907 | 22 | Level 29 | WIR - 01160 | Male Toilet | cable trunking |  |  | 0.15 | 0.2 | 0.03 |  | 2 | 50 | 1 | 100 | FS702/FB750 | Hotel | 2
21 | Sheet 61910 | 17 | Basement 01 | WIR - 0977 | Corridor, Entry D. | cable tray |  |  | 0.1 | 0.4 | 0.04 |  | 2 | 50 | 1 | 100 | FS702/FB750 | Hotel | 2
23 | Sheet 61910 | 18 | Basement 01 | WIR - 0977 | Corridor, Entry D. | opening |  |  | 0.25 | 0.5 | 0.125 | 0.045 | 2 | 50 | 1 | 100 | FS702/FB750 | Hotel | 2
16 | Sheet 61911 | 37 | Basement 01 | WIR - 0977 | Corridor, Entry D. | cable tray |  |  | 0.09 | 0.16 | 0.0144 |  | 2 | 50 | 1 | 100 | FS702/FB750 | Hotel | 2
17 | Sheet 61911 | 38 | Basement 01 | WIR - 0977 | Corridor, Entry D. | cable trunking |  |  | 0.15 | 0.15 | 0.0225 |  | 2 | 50 | 1 | 100 | FS702/FB750 | Hotel | 2
[12 empty] | Subtotal 0.05 m |  |  |  | 1000 |  |  | 20
4 | Sheet 61907 | 3 | Level 29 | WIR - 01160 | Electrical Room | opening |  |  | 0.3 | 0.4 | 0.12 | 0.099509 | 2 | 95 | 1 | 190 | FS702/FB750 | Hotel | 2
16 | Sheet 61907 | 12 | Level 29 | WIR - 01160 | Telephone Room | opening |  |  | 0.3 | 0.6 | 0.18 | 0.089509 | 2 | 95 | 1 | 190 | FS702/FB750 | Hotel | 2
24 | Sheet 61907 | 18 | Level 29 | WIR - 01160 | Male Toilet | opening |  |  | 0.3 | 0.48 | 0.144 | 0.064 | 2 | 95 | 1 | 190 | FS702/FB750 | Hotel | 2
26 | Sheet 61907 | 19 | Level 29 | WIR - 01160 | Male Toilet | opening |  |  | 0.3 | 0.48 | 0.144 | 0.064 | 2 | 95 | 1 | 190 | FS702/FB750 | Hotel | 2
10 | Sheet 61910 | 8 | Basement 01 | WIR - 0977 | Corridor, Entry D. | opening |  |  | 0.45 | 0.45 | 0.2025 | 0.08 | 2 | 95 | 1 | 190 | FS702/FB750 | Hotel | 2
[12 empty] | Subtotal 0.10 m |  |  |  | 950 |  |  | 10
[12 empty] | Subtotal 0.15 m |  |  |  | 0 |  |  | 0
32 | Sheet 61907 | 24 | Level 29 | WIR - 01160 | Male Toilet | opening |  |  | 0.2 | 0.8 | 0.16 | 0.15951 | 2 | 180 | 1 | 360 | FS702/FB750 | Hotel | 2
20 | Sheet 61910 | 16 | Basement 01 | WIR - 0977 | Corridor, Entry D. | opening |  |  | 0.35 | 0.6 | 0.21 | 0.19009 | 2 | 180 | 1 | 360 | FS702/FB750 | Hotel | 2
[12 empty] | Subtotal 0.25 m |  |  |  | 720 |  |  | 4
[12 empty] | Subtotal 0.35 m |  |  |  | 0 |  |  | 0
7 | Sheet 61906 |  | Level 23 | WIR - 00892 | Water Meter Room | opening |  |  | 0.35 | 1.65 | 0.5775 | 0.49952 | 2 | 310 | 1 | 620 | FS702/FB750/FP302/FS709 | Residence | 2
5 | Sheet 61908 | 29 | Level 29 | WIR - 01160 | Male Toilet | opening |  |  | 0.25 | 1.5 | 0.375 | 0.36206 | 2 | 310 | 1 | 620 | FS702/FB750/FS709 | Hotel | 2
4 | Sheet 61910 | 3 | Basement 01 | WIR - 0977 | Corridor, Entry D. | opening |  |  | 0.6 | 0.8 | 0.48 | 0.44 | 2 | 310 | 1 | 620 | FS702/FB750 | Hotel | 2
7 | Sheet 61912 |  | Level 13 |  | Water Meter Room | opening |  |  | 0.35 | 1.65 | 0.5775 | 0.49952 | 2 | 310 | 1 | 620 | FS702/FB750/FP302/FS709 | Residence | 2
[12 empty] | Subtotal 0.50 m |  |  |  | 2480 |  |  | 8
[12 empty] | Subtotal 0.65 m |  |  |  | 0 |  |  | 0
1 | Sheet 61910 | 13 | Basement 01 | WIR - 0977 | Corridor, Entry D. | opening |  |  | 0.55 | 1.5 | 0.825 | 0.78304 | 2 | 400 | 1 | 800 | FS702/FB750 | Hotel | 2
[12 empty] | Subtotal 0.80 m |  |  |  | 800 |  |  | 2
1 | Sheet 61911 | 29 | Basement 01 | WIR - 0977 | Corridor, Entry D. | opening |  |  | 0.85 | 3.25 | 2.7625 | 2.6958 | 2 | 450 | 1 | 2426.2369 | FS702/FB750 | Hotel | 5.3916
[12 empty] | Subtotal 1.00 m |  |  |  | 2426.2369 |  |  | 5.3916
[14 empty] | Grand Total |  | 8376.2369 |  | Total qty | 49.3916

## civil opening (FR 230) (hidden)
Project: |  |  |  |  | Dorchester Collection Dubai - Hotel & Residences ¦ OMNIYAT
Client: |  |  |  |  | Khansaheb Civil Engineering
Period of Completed Works: |  |  |  |  | up to July 2022
Summary of Completed Firestopping Works
No. | Sos Number | Serial No | Level | WIR No. | Location | Penetrant Type | Penetrant Size (in meter) | SquareMeters | Opening Size (in meter) |  | SquareMeters | Diffirence | Sides | Rate (AED) | Nos | Total (AED) |  | Hotel / Residence | QTY
6 | Sheet 61916 | 5 | Level 22 | WIR - 01153 | FTR Room | opening Mortar |  |  | 0.35 | 1.8 | 0.63 | 0.5475 | 1 | 680 | 1 | 372.3 | FR230 | Hotel | 0.5475
12 | Sheet 61916 | 6 | Level 23 | WIR - 01154 | FTR Room | opening Mortar |  |  | 0.35 | 1.8 | 0.63 | 0.5475 | 1 | 680 | 1 | 372.3 | FR230 | Hotel | 0.5475
18 | Sheet 61916 | 7 | Level 24 | WIR - 01155 | FTR Room | opening Mortar |  |  | 0.35 | 1.8 | 0.63 | 0.5475 | 1 | 680 | 1 | 372.3 | FR230 | Hotel | 0.5475
24 | Sheet 61916 | 8 | Level 25 | WIR - 01156 | FTR Room | opening Mortar |  |  | 0.35 | 1.8 | 0.63 | 0.5475 | 1 | 680 | 1 | 372.3 | FR230 | Hotel | 0.5475
6 | Sheet 61915 | 1 | Level 18 | WIR - 01149 | FTR Room | opening Mortar |  |  | 0.35 | 1.8 | 0.63 | 0.5475 | 1 | 680 | 1 | 372.3 | FR230 | Hotel | 0.5475
12 | Sheet 61915 | 2 | Level 19 | WIR - 01150 | FTR Room | opening Mortar |  |  | 0.35 | 1.8 | 0.63 | 0.5475 | 1 | 680 | 1 | 372.3 | FR230 | Hotel | 0.5475
18 | Sheet 61915 | 3 | Level 20 | WIR - 01151 | FTR Room | opening Mortar |  |  | 0.35 | 1.8 | 0.63 | 0.5475 | 1 | 680 | 1 | 372.3 | FR230 | Hotel | 0.5475
24 | Sheet 61915 | 4 | Level 21 | WIR - 01152 | FTR Room | opening Mortar |  |  | 0.35 | 1.8 | 0.63 | 0.5475 | 1 | 680 | 1 | 372.3 | FR230 | Hotel | 0.5475
6 | Sheet 61917 | 9 | Level 26 | WIR - 01157 | FTR Room | opening Mortar |  |  | 0.35 | 1.8 | 0.63 | 0.5475 | 1 | 680 | 1 | 372.3 | FR230 | Hotel | 0.5475
12 | Sheet 61917 | 10 | Level 27 | WIR - 01158 | FTR Room | opening Mortar |  |  | 0.35 | 1.8 | 0.63 | 0.5475 | 1 | 680 | 1 | 372.3 | FR230 | Hotel | 0.5475
18 | Sheet 61917 | 11 | Level 28 | WIR - 01159 | FTR Room | opening Mortar |  |  | 0.35 | 1.8 | 0.63 | 0.5475 | 1 | 680 | 1 | 372.3 | FR230 | Hotel | 0.5475
24 | Sheet 61917 | 12 | Level 29 | WIR - 01160 | FTR Room | opening Mortar |  |  | 0.35 | 1.8 | 0.63 | 0.5475 | 1 | 680 | 1 | 372.3 | FR230 | Hotel | 0.5475
[14 empty] | Grand Total |  | 4467.6 |  | Total qty | 6.57