## Sheet1
No | Description | Qty | Unit | Rate | Amount | Previous | This Month | % | Cumulative | Remark
Carpet Works - Khansaheb - Dorchester Hotel
Supply & Installation Customized Tufted Printed Carpet
| Area: RES-FA-05 - Meeting Room | 35.2 | m2 | 265 | 9328 | 7928.8 | 466.4 | 90% | 8395.2 | 90% until WIR raised and approved
| Area: RES-FA-05 - Multifunction Room | 43.8 | m2 | 265 | 11607 | 9865.95 | 580.35 | 90% | 10446.3 | 90% until WIR raised and approved
Wooden Flooring Works - Khansaheb - Dorchester Hotel
Supply & Installation Engineered Wooden Flooring - Chevron
| Area: RES-WD-01 - Ground Floor Lobby Corridor | 62 | L Sum | 283 | 17546 | 15791.4 | 0 | 90% | 15791.4 | 90% until WIR approval
| Area: RES-WD-01 - Ground Floor Lift Lobby | 14 | L Sum | 293 | 4102 | 3691.8 | 0 | 90% | 3691.8 | 90% until WIR approval
| Area: RES-WD-01 - Level 2 Corridor | 25 | L Sum | 283 | 7075 | 6013.75 | 0 | 85% | 6013.75 | 85% until MIR raised and approved
| Area: RES-WD-01 - Level 2 Lift Lobby | 12 | L Sum | 293 | 3516 | 2988.6 | 0 | 85% | 2988.6 | 85% until MIR raised and approved
| Area: RES-WD-01 - Level 4 Fitness & Yoga | 160 | L Sum | 267 | 42720 | 38448 | 0 | 90% | 38448 | 90% until WIR approval
| Area: RES-WD-01 - Level 4 Lift Lobby | 12 | L Sum | 283 | 3396 | 2886.6 | 0 | 85% | 2886.6 | 85% until MIR raised and approved
| Area: RES-WD-01 - Level 23 Corridor | 37 | L Sum | 283 | 10471 | 8900.35 | 523.55 | 90% | 9423.9 | 90% until WIR raised and approved
| Area: RES-WD-01 - Level 23 Lift Lobby | 19 | L Sum | 283 | 5377 | 4570.45 | 268.85 | 90% | 4839.3 | 90% until WIR raised and approved
| Storage Charges - from 18.03.2022 (189Days) | 1 | L Sum | 18522 | 18522 | 18522 | 0 | 100% | 18522
[6 empty] | 119607.7 | 1839.15 |  | 121446.85
Variation
| Storage Charges - from 01.11.2022 (61Days) | 1 | L Sum | 5978 | 5978 | 5978 | 0 | 100% | 5978
[5 empty] | 5978 | 125585.7 | 1839.15 |  | 127424.85
| Discount |  |  |  | -203 | -190.7369 | -4136.3364 |  | -4327.0734
[5 empty] | 5775 | 125394.9631 | -2297.1864 |  | 123097.7766
| Advance Payment |  |  |  |  | 34477.2 | 0 |  | 34477.2
| Advance Payment Recovery |  |  |  |  | -30268.4889 | 689.1559 | 30% | -29579.333
[6 empty] | 129603.6742 | -1608.0305 |  | 127995.6436
[5 empty] | KCE Claim | 134374.65 | 6425.45 |  | 166537.97
[5 empty] | Difference | -4770.9758 | -8033.4805 | 0 | -38542.3264