## Summary Contract
PLOT 18
ESTIMATED COST TO COMPLETE WITH NEW CONTRACTOR BY PACKAGES
25 FEBRUARY 2022
Package | Current Contractor | Total Value of Package |  | Gross value of Works executed to 31-Nov-2021 [Note 1] | Gross Certification (Assessed up to Jan 2022) | % Complete | Estimated value of Works remaining to complete | Forecast cost to complete with new contractor | Cost uplift |  | Basis of calculation
A. Main Contractor Works (Roberts Pizzarotti JV)
Preliminaries | Roberts Pizzarotti JV | 69999375 |  | 63022928.4021 | 63705272.6331 | 91.01% | 6294102.3669 | 16425000 | 10130897.6331 | 161% | Orig Contract Prelims at 2.4m per month for 28months. Khansaheb prelims at 1.46 per month for 10 months; plus 12.5%
Novated Design Fees | Various (see org chart) | 17133642.5 |  | 16714931.5227 | 16742681.5227 | 97.72% | 390960.9773 |  | -390960.9773 | -100% | Monthly rates in novated Contract for Consultants (BSBG/WME/BRIMAXX/LMS/Light-Touch) to be carried forward separately by Omniyat
Completed Works (Structure Fee / PC ADJ etc) | Roberts Pizzarotti JV | 196378058.15 |  | 196378058.15 | 196378058 | 100% | 0.15 | 0 | -0.15 | - | N/A
Civil and BOH Works | Roberts Pizzarotti JV | 35034040.53 |  | 28393526.1823 | 28661071.9709 | 81.81% | 6372968.5591 | 7328913.843 | 955945.2839 | 15% | Assumed 15% mark-up fpr New Contractors prices to undertake works
PS/PC Rate Adjustment | Roberts Pizzarotti JV |  |  |  |  | #DIV/0! | 0 |  | 0 | #DIV/0!
Variations (Agreed Under Addendum 2) | Roberts Pizzarotti JV | 33848923.8674 |  | 36587076.9811 | 32290700.0617 | 95.4% | 1558223.8057 | 3116447.6114 | 1558223.8057 | 0% | Variations not agreed downstream with subs post addendum 2 considered under Psums
New Variations (Post Addendum 2) | Roberts Pizzarotti JV | 931101.6741 |  | 342895.3104 | 90890.8804 | 9.762% | 840210.7936 | 1419550.95 | 579340.1564 | 68.95% | RPJV claimed variations for MEP and Civils (Psum Variations Considered below)
EOT Costs Awarded to Oct 2020 | Roberts Pizzarotti JV |  |  |  |  | #DIV/0! | 0 |  | 0 | #DIV/0!
Authaurity Payments Agreed | Roberts Pizzarotti JV |  |  |  |  | #DIV/0! | 0 |  | 0 | #DIV/0!
(incl. Overhead, Profit and Attendance Fee for PS Packages) | Roberts Pizzarotti JV | 13343972 |  | 9114071.0174 | 9128947.7589 | 68.41% | 4215024.2411 | 12304742.5964 | 8089718.3553 | 191.9% | Change from 6% OH&P to 12.5% OH&P
Materials on-site | Various (see schedule) |  |  | 11808683.3552 | 6882912.8603 |  | -6882912.8603 | -6882912.8603 | 0 | 0% | CHECK BALANCE TAKEN OFF PSUMS BELOW!
MEP Main Works | RP Services | 116046969.42 |  | 98313488.8273 | 100476553.9053 | 86.58% | 15570415.5147 | 20241540.1691 | 4671124.6544 | 30% | Assumed a 30% premium / up-lift added for RISK
Sub-Total of A (Main Contractor Works) | 55299988.82 | 482716083.1414 |  | 460675659.7486 | 454357089.5933 | 94.13% | 28358993.5481 | 53953282.3096 | 25594288.7615 | 90.25%
B. Provisional Sum (Sub-Contractor Packages)
MEP WORKS (FOH) | [6 empty] | 10521008.9002 | 12048677.3702
Electrical Works & Wiring | Silicon Vega & SKMA | 9986424.922 |  | 9270455.5317 | 9530219.7929 | 188.3% | 456205.1291 | 456205.1291 | 0 | -2.552e-14% | Additional cost assumed for final T&C etc
ELV (incl Access Control) | SIS | 5659163.54 |  | 3970785.5925 | 3993499.2789 | 140.7% | 1665664.2611 | 2078880.9611 | 413216.7 | 24.81% | SIS increase (BGM speakers/tablets etc) & Creation Gulf
Sanitary-ware | Sanipex | 4335707.25 |  | 3547406.0975 | 3548564.159 | 163.7% | 787143.091 | 787143.091 | 0 | 2.958e-14%
Supply of Light Fittings | Projects & Supplies | 6183623.2 |  | 512308 | 1914900.142 | 39.25% | 4268723.058 | 4307892.178 | 39169.12 | 0.9176%
Elevators | Kone Middle East | 14429641.04 |  | 13275588.8268 | 13515270.0989 | 185.7% | 914370.9411 | 1780711.6911 | 866340.75 | 94.75% | Additional CTU cost (AED 8k/mth *6lifts for 12months)
FOH MEP (MISC. guest rooom lights and alarm cord) | HS Energy & SIS | 2154228 |  | 1948435.5802 | 1948435.5802 | 180.9% | 205792.4198 | 205792.4198 | 0 | 0%
Kitchens | TSSC | 2223110 |  | 0 | 0 | 0% | 2223110 | 2432051.9 | 208941.9 | 9.399% | Potential price up-lift as RPJV did not pay advance paid last July - supplier may enforce 2021-2022 price increases
Facade Works | [6 empty] | 19459348.398 | 22257403.298
Aluminium and Glazing Works | Glassline Aluminium LLC | 62798782.8 |  | 49627038.8325 | 50138851.994 | 158.9% | 12659930.806 | 15017414.206 | 2357483.4 | 18.62% | Glassline have a side agreement with RPJV covering EOT costs till Oct-2020 plus variations
GRC | Arabian Profiles LLC | 21709321.67 |  | 17096638.2579 | 17867870.2246 | 161.1% | 3841451.4454 | 4160822.9454 | 319371.5 | 8.314% | Joyz overseas (EIFS VO)
Balustrade | Al Rawaa Glass | 9116353 |  | 7956481.3071 | 7794226.9624 | 172.8% | 1322126.0376 | 1443326.0376 | 121200 | 9.167% | Variaiton regarding welded channel with RPJV - agreed under Addendum 2
BMU | EW Cox | 1750793 |  | 816514.6305 | 921931.9305 | 99.29% | 828861.0695 | 828861.0695 | 0 | 0%
External Ceilings | Al Rawda | 3480715 |  | 2560516.9721 | 2673735.9605 | 150.4% | 806979.0395 | 806979.0395 | 0 | 0%
Interior Finishes | [6 empty] | 38336361.1053 | 39085096.3603
Guestrooms | Rawda / DAR / Momentum / Joseph Glass | 32624669.96 |  | 22190196.8897 | 23225027.2244 | 139.2% | 9399642.7356 | 9376718.1156 | -22924.62 | -0.2439%
Corridor | Rawda / DAR / Momentum / ASI / AHK | 4516769.82 |  | 1516200.9875 | 1584966.2881 | 68.66% | 2931803.5319 | 2931803.5319 | 0 | -1.588e-14%
Rooms - Joinery | ASI | 16209692.3826 |  | 9648441.6399 | 10037571.1909 | 121.4% | 6172121.1917 | 6172121.1917 | 0 | 0% | RPJV Variaitons under Addendum 2 not agreed with ASI
Public Areas (Turn-Key) | Bond Interiors | 11346891 |  | 5905019.6809 | 7368393.2515 | 117% | 3978497.7485 | 4207880.2035 | 229382.455 | 5.766%
ID Ballroom (Turn-Key) | AHK (Rattan House/DAR/Golden Oasis/SIS/Kone) | 6594439 |  | 95000 | 579611.9383 | 10.23% | 6014827.0617 | 6014827.0617 | 0 | -1.548e-14% | Increment represents next lowest price received at tender stage to replace AHK
ID Various - L28 Gym/ L1 Corridor / L29 changing rooms and lobby / Royal & Pres (Turn-Key) | AHK (Decolab/SIS/gldn oasis/DAR) | 6617805.03 |  | 187197.1226 | 390947.394 | 8.736% | 6226857.636 | 6226857.636 | 0 | 0% | Increment represents next lowest price received at tender stage to replace AHK
Residential (Turn-Key) | AHK (Rattan House/DAR/Golden Oasis/SIS) | 4000000 |  | 2203550.4 | 2387388.8 | 114.8% | 1612611.2 | 2154888.62 | 542277.42 | 33.63%
Signage (Rooms, Public Areas and External) | Joseph Signs | 2000000 |  | 0 | 0 | 0% | 2000000 | 2000000 | 0 | 0% | Actual saving of tender awarded value
External Works | [6 empty] | 23195451.2277 | 25046763.7427
Secondary Structure | RPJV | 12000000 |  | 8068729.0375 | 8619009.4644 | 139.1% | 3380990.5356 | 3380990.5356 | 0 | 0%
Soft Landscaping and Irrigation | RPJV (Fiona Landscape) | 5110819.99 |  | 0 | 9014.04 | 0.1764% | 5101805.95 | 5701805.95 | 600000 | 11.76% | PC adjustment for landscape metal works and softscape
Hard Landscape | RPJV (Fiona and Al Reem) | 9234342 |  | 0 | 125561.6053 | 1.36% | 9108780.3947 | 10360092.9097 | 1251312.515 | 13.74% | Pc adjustment for granite and replacement of cobble stone with solid granite in zones (strips). E/O for L29 cabanas
Landscape MEP | RPJV (Watermasters) | 4893506 |  | 1189121.9701 | 1824402.0666 | 61.58% | 3069103.9334 | 3069103.9334 | 0 | 0%
Landscape Pool and W/features | RPJV (IKK/ Watermaters/ Reem &Mosaic ?) | 3414995.97 |  | 820985.56 | 880225.556 | 49.82% | 2534770.414 | 2534770.414 | 0 | 0%
|  | 262391794.5747 |  |  | 170879624.9435 |  | 91512169.6312 | 98437940.7712
-3644944.8235
-4412593.5376
Sub-Total of B (PSUM Packages) |  | 262391794.5747 |  | 154349074.556 | 170879624.9435 | 123.9% | 91512169.6312 | 98437940.7712 | 6925771.14 | 7.568%
Internal Partitions | Sharif Carpentry | 12800000 |  | 12800000 | 0 | 100% | 0
Display Apt Fitout 301 | BW Interiors | 10400000 |  | 10400000 | 0 | 100% | 0
BOH Tiling | Al Reem Marble & Granite | 1600000 |  | 1600000 | 0 | 100% | 0
Display Apt Fitout 105 | Bond Interiors | 1300000 |  | 1300000 | 0 | 100% | 0
ADD : MOS | [6 empty] | 1493173.9032
GRAND TOTAL A.+B (MAIN & PSUM PACKAGES) |  | 745107877.7161 | 0 | 615024734.3046 | 625236714.5368 | 166.5% | 121364337.0825 | 152391223.0808 | 32520059.9015 | 25.57%
125.6%
0
Notes: | [8 empty] | 6925771.14
[1] Including MOS and variations on-account , excl. advance payments and retention.
SUMMARY & CHECK:
TOTAL WORKS |  | 488064970.2923 |  | 460675659.7486 | 1475449.3337 | 94.69% | 25913861.21 | 53953282.3096 | 25594288.7615 | 90.25%
Total (with Psums Value |  | 256861805.75 |  | 154349074.556 | 8464132.6193 | 63.39% | 94048598.5747 | 98437940.7712 | 6925771.14 | 7.568%
TOTAL CHECK |  | 744926776.0423 | 0 | 615024734.3046 | 9939581.953 | 83.9% | 119962459.7847 | 152391223.0808 | 32520059.9015 | 25.57%

## PS FUTURE WORKS 91m
PLOT 18
VALUE OF WORKS TO COMPLETE - PROVISONAL SUM PACKAGES
AS AT 25-FEB-2022
[19 empty] | Oct | Nov | Dec
Item No. | Package | Contractor | Category | ADDENDUM -2 INSTRUCTED AMOUNT | AWRDED AFTER ADDENDUM-2 | NEW CONTRACT AMOUNT | VARIATIONS (POST ADDENDUM 2) |  |  | RISK UP-LIFT | FINAL ESTIMATED PACKAGE SUM | Hotel Component | Residence Component | Retail Component | Hotel | Resident | Retail |  | Gross certification to Nov-21 (incl. MOS excl. advance payments, recovery and retention) IPC 46 | Gross certification to Nov-21 (incl. MOS excl. advance payments, recovery and retention) IPC 47 | Gross certification to Dec-21 (incl. MOS excl. advance payments, recovery and retention) IPC 48 | Amount remaining to be paid at the end of IPC 46 | Retention to be released | Net Paid Amount (incl. MOS, advance payments, recovery and retention) IPC 47 |  | Amount remaining to be paid at the end of IPC 47 | Retention to be released | Net Paid Amount (incl. MOS, advance payments, recovery and retention) IPC 48 |  | Amount remaining to be paid at the end of IPC 48 | Retention to be released | Net Paid Amount upto (incl. MOS, advance payments, recovery and retention) IPC 49 |  | Amount remaining to be paid at the end of IPC 49 | Retention to be released | Preliminaries | Podium | Terraces | MEP | Apartments | Other
Awarded Provisional Sums
1 | Electrical works Hotel Public areas | BOND INTERIORS | ID - Pareas | 751671 | 0 | 237871.59 |  |  |  | 0 | 237871.59 | 100% | 0% | 0% | 237871.59 | 0 | 0 |  | 388302.6 | 461484.39 | 483592.6 | #REF! | 23787.159 | 502391.934 | 211.2% | -288307.503 | 23787.159 | 515656.86 | 216.8% | -301572.429 | 23787.159 | 545163.921 | 229.2% | -331079.49 | 23787.159
2 | Fit out Hotel Public areas | BOND INTERIORS | ID-Pareas | 10595220 | 0 | 3740626.1585 | 229382.455 |  |  | 0 | 3970008.6135 | 100% | 0% | 0% | 3970008.6135 | 0 | 0 |  | 4439325.6741 | 5443535.2909 | 6171043.2805 | #REF! | 397000.8613 | 6444687.1745 | 162.3% | -2871679.4224 | 397000.8613 | 6881191.9683 | 173.3% | -3308184.2162 | 397000.8613 | 7291322.3049 | 183.7% | -3718314.5528 | 397000.8613
3 | Electrical works Hotel 19-27 | SILICON VEGA | MEP Electrical | 2090511 | 0 | 177534.0176 |  |  |  | 0 | 177534.0176 | 100% | 0% | 0% | 177534.0176 | 0 | 0 |  | 1912976.9824 | 1912976.9824 | 1912976.9824 | #REF! | 17753.4018 | 1748309.7368 | 984.8% | -1588529.121 | 17753.4018 | 1748309.7368 | 984.8% | -1588529.121 | 17753.4018 | 1748309.7368 | 984.8% | -1588529.121 | 17753.4018
4 | Supply Wiring accessories Hotel | SMKA | MEP Electrical | 516116 | 0 | 8333.81 |  |  |  | 0 | 8333.81 | 100% | 0% | 0% | 8333.81 | 0 | 0 |  | 286780.07 | 286780.07 | 507782.19 | #REF! | 833.381 | 487437.843 | 5849% | -479937.414 | 833.381 | 465337.631 | 5584% | -457837.202 | 833.381 | 465337.631 | 5584% | -457837.202 | 833.381
5 | ELV hotel 19 & 27 | SIS | MEP ELV | 371106 | 0 | 65611.5408 |  |  |  | 0 | 65611.5408 | 100% | 0% | 0% | 65611.5408 | 0 | 0 |  | 300929.8554 | 305494.4592 | 305494.4592 | #REF! | 6561.1541 | 284786.8444 | 434% | -225736.4577 | 6561.1541 | 284786.8444 | 434% | -225736.4577 | 6561.1541 | 284786.8444 | 434% | -225736.4577 | 6561.1541
6 | Void Column light fittings | Bayt Al Tawreed Trading LLC | MEP Lights | 512308 | 0 | 0 |  |  |  | 0 | 0 | 51.62% | 44.76% | 3.62% | 0 | 0 | 0 |  | 512308 | 512308 | 512308 | #REF! | 0 | 461077.2 |  | -461077.2 | 0 | 461077.2 |  | -461077.2 | 0 | 461077.2 |  | -461077.2 | 0
7 | BMU | E W Cox Middle East LLC | BMU | 2111400 | 0 | 828861.0695 |  |  |  | 0 | 828861.0695 | 51.62% | 44.76% | 3.62% | 427875.1335 | 370981.0579 | 30004.8781 |  | 816514.6305 | 816514.6305 | 921931.9305 | #REF! | 82886.107 | 848263.2136 | 102.3% | -102288.2511 | 82886.107 | 929961.6211 | 112.2% | -183986.6586 | 82886.107 | 925637.2461 | 111.7% | -179662.2836 | 82886.107
8 | Hotel Ceiling and partition | Al Rawda General Maintenance and Decoration Co LLC | Hotel ID | 8101444.13 | 0 | 47336.9806 |  |  |  | 0 | 47336.9806 | 100% | 0% | 0% | 47336.9806 | 0 | 0 |  | 8025361.6534 | 8025361.6534 | 8054107.1494 | #REF! | 4733.6981 | 7222825.488 | 15258% | -7180222.2055 | 4733.6981 | 7248696.4345 | 15313% | -7206093.152 | 4733.6981 | 7248696.4345 | 15313% | -7206093.152 | 4733.6981
9 | Sanitary ware | Sanipex LLC | MEP Sanitary | 4023939.06 | 0 | 431509.101 |  |  |  | 0 | 431509.101 | 100% | 0% | 0% | 431509.101 | 0 | 0 |  | 3289873.173 | 3291780.8975 | 3292938.959 | #REF! | 43150.9101 | 2962602.8077 | 686.6% | -2574244.6168 | 43150.9101 | 2963645.0631 | 686.8% | -2575286.8722 | 43150.9101 | 2963645.0631 | 686.8% | -2575286.8722 | 43150.9101
10a | Hotel guestroom Sanitary ware descope from Sanipex in lieu of Al Futtaim | Al Futtaim Engineering LLC | MEP Sanitary | 220263 | 0 | 220263 |  |  |  | 0 | 220263 | 100% | 0% | 0% | 220263 | 0 | 0 |  | 0 | 0 | 0 | #REF! | 22026.3 | 220263 | 100% | -22026.3 | 22026.3 | 220263 | 100% | -22026.3 | 22026.3 | 220263 | 100% | -22026.3 | 22026.3
10b | Hotel guestroom Sanitary ware descope from sanipex (Already in PS VO-154) | Bette GmbH & Co. KG | MEP Sanitary | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | #REF! | 0 | 78608 |  | -78608 | 0 | 78608 |  | -78608 | 0 | 78608 |  | -78608 | 0
|  | Taps&More | MEP Sanitary | 99000 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 |  | 99000 | 99000 | 99000 | #REF! | 0 | 89100 |  | -89100 | 0 | 89100 |  | -89100 | 0 | 89100 |  | -89100 | 0
11 | Hotel guestroom Sanitary ware descope from sanipex | Taps&More | MEP Sanitary | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | #REF! | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
12 | Access control system Hotel Gust room | Creation Gulf Trading LLC | MEP ELV | 3684009 | 0 | 679401.1248 | 113829.32 |  |  | 0 | 793230.4448 | 100% | 0% | 0% | 793230.4448 | 0 | 0 |  | 3412812.4752 | 3412812.4752 | 3411810.1752 | #REF! | 79323.0445 | 3071531.2277 | 387.2% | -2357623.8274 | 79323.0445 | 3070629.1577 | 387.1% | -2356721.7574 | 79323.0445 | 3070629.1577 | 387.1% | -2356721.7574 | 79323.0445
| Stone works | Dar Al Rokham LLC | Hotel ID | 14192643.2 | 0 | 2614074.9234 |  |  |  | 0 | 2614074.9234 | 100% | 0% | 0% | 2614074.9234 | 0 | 0 |  | 10669855.6027 | 10910208.9411 | 11095280.4567 | #REF! | 261407.4923 | 10039130.0925 | 384% | -7686462.6615 | 261407.4923 | 10173306.9413 | 389.2% | -7820639.5103 | 261407.4923 | 10467777.0573 | 400.4% | -8115109.6262 | 261407.4923
| Ironmongery supply | Momentum Fireguard LLC | Hotel ID | 1177018 | 0 | 215927.4038 | -22924.62 |  |  | 0 | 193002.7838 | 100% | 0% | 0% | 193002.7838 | 0 | 0 |  | 988555.1162 | 988555.1162 | 988555.1162 | #REF! | 19300.2784 | 891331.2151 | 461.8% | -717628.7097 | 19300.2784 | 891331.2151 | 461.8% | -717628.7097 | 19300.2784 | 918981.5366 | 476.1% | -745279.0312 | 19300.2784
13 | Joinery works | Alshafar Interiors Co LLC | Rooms Joinery | 11437852 | 0 | 6172121.1917 |  |  |  | 0 | 6172121.1917 | 100% | 0% | 0% | 6172121.1917 | 0 | 0 |  | 5118170.1309 | 5420169.6399 | 5695727.9627 | #REF! | 617212.1192 | 5739489.9209 | 92.99% | -184580.8483 | 617212.1192 | 5939269.7049 | 96.23% | -384360.6324 | 617212.1192 | 5927418.9134 | 96.04% | -372509.8408 | 617212.1192
14 | Internal Glazing | Joseph Decorative Glass | Hotel ID | 2072163 | 0 | 1172280.69 |  |  |  | 0 | 1172280.69 | 100% | 0% | 0% | 1172280.69 | 0 | 0 |  | 717106.3476 | 802711.1502 | 820658.8241 | #REF! | 117228.069 | 892789.5839 | 76.16% | 162263.0371 | 117228.069 | 905801.6475 | 77.27% | 149250.9736 | 117228.069 | 963238.6747 | 82.17% | 91813.9463 | 117228.069
| External Ceiling | Al Rawda General Maintenance and Decoration Co LLC | Façade Ceiling | 3480715 | 0 | 806979.0395 |  |  |  | 0 | 806979.0395 | 51.62% | 44.76% | 3.62% | 416579.1795 | 361187.1142 | 29212.7458 |  | 2555487.0413 | 2560516.9721 | 2602165.9584 | #REF! | 80697.904 | 2304465.2749 | 285.6% | -1578184.1393 | 80697.904 | 2341949.3625 | 290.2% | -1615668.227 | 80697.904 | 2406362.3644 | 298.2% | -1680081.2288 | 80697.904
| Internal & external painting | Al Rawda General Maintenance and Decoration Co LLC | Hotel ID | 1339194 | 0 | 214017.9065 |  |  |  | 0 | 214017.9065 | 51.62% | 44.76% | 3.62% | 110480.4456 | 95789.9849 | 7747.4759 |  | 1075377.2713 | 1084102.8595 | 1105437.5992 | #REF! | 21401.7906 | 975692.5735 | 455.9% | -783076.4577 | 21401.7906 | 994893.8393 | 464.9% | -802277.7234 | 21401.7906 | 1012658.4842 | 473.2% | -820042.3683 | 21401.7906
15 | GRC claddiing -Edge Profile | Arabian Profile Co Limited | GRC | 18300000 | 0 | 1485633.3566 |  |  |  | 148923.5 | 1634556.8566 | 51.62% | 44.76% | 3.62% | 843791.8716 | 731593.8149 | 59171.17 |  | 16051121.3017 | 16331411.7463 | 16817093.7001 | #REF! | 163455.6857 | 15264129.3971 | 933.8% | -13793028.2262 | 163455.6857 | 15652674.96 | 957.6% | -14181573.7891 | 163455.6857 | 15440578.6823 | 944.6% | -13969477.5114 | 163455.6857
16 | Glass façade (Towers and Preliminaries) | Glassline Aluminum LLC | FAÇADE | 58250000 | 0 | 12659930.806 | 996483.4 |  |  | 1361000 | 15017414.206 | 51.62% | 44.76% | 3.62% | 7752298.1162 | 6721483.7496 | 543632.3401 |  | 41342303.5181 | 41578355.7099 | 41766543.4977 | #REF! | 1501741.4206 | 37980703.818 | 252.9% | -32211224.4184 | 1501741.4206 | 38140862.0328 | 254% | -32389602.3011 | 1501741.4206 | 38235970.4427 | 254.6% | -32510784.3456 | 1501741.4206
| Glass façade (Podium) | Glassline Aluminum LLC | FAÇADE | 0 | 0 | 0 |  |  |  | 0 | 0 | 51.62% | 44.76% | 3.62% | 0 | 0 | 0 |  | 7896077.5964 | 8048683.1226 | 8074711.2195 | 0 | 0 | 7746193.3858 |  | 0 | 0 | 7764413.0537 |  | 0 | 0 | 7790486.6883 |  | 0 | 0
17 | Vertical Transport | Kone Middle East LLC | MEP - LIFT | 13988719 | 0 | 914370.9411 | 576000 |  |  | 290340.75 | 1780711.6911 | 51.62% | 44.76% | 3.62% | 919240.0036 | 797009.6936 | 64461.994 |  | 13211055.6976 | 13275588.8268 | 13498736.7656 | #REF! | 178071.1691 | 12121137.7761 | 680.7% | -10518497.2541 | 178071.1691 | 12288498.7302 | 690.1% | -10685858.2082 | 178071.1691 | 12261410.1258 | 688.6% | -10658769.6039 | 178071.1691
18 | Glass balustrade | Al Rawaa Glass Mirror Factory LLC | Balustrade | 9063400 | 0 | 1322126.0376 |  |  |  | 121200 | 1443326.0376 | 51.62% | 44.76% | 3.62% | 745074.5893 | 646002.8587 | 52248.5896 |  | 7934080.6062 | 7956481.3071 | 8083920.889 | #REF! | 144332.6038 | 7660833.1764 | 530.8% | -6361839.7426 | 144332.6038 | 7675528.8001 | 531.8% | -6376535.3663 | 144332.6038 | 7156815.9736 | 495.9% | -5857822.5398 | 144332.6038
19 | L8 fit out | Alshafar Interiors Co LLC | Rooms Joinery | 4228272 | 0 | 0 |  |  |  | 0 | 0 | 0% | 100% | 0% | 0 | 0 | 0 |  | 4228272 | 4228272 | 4228272 | #REF! | 0 | 3805444.8 |  | -3805444.8 | 0 | 3805444.8 |  | -3805444.8 | 0 | 3805444.8 |  | -3805444.8 | 0
20 | Hotel guest room light fittings | HS Energy Solutions FZCO | FOHMEP | 1980228 | 0 | 163792.4198 |  |  |  | 0 | 163792.4198 | 100% | 0% | 0% | 163792.4198 | 0 | 0 |  | 1870435.5802 | 1870435.5802 | 1870435.5802 | #REF! | 16379.242 | 1683392.0222 | 1028% | -1535978.8444 | 16379.242 | 1683392.0222 | 1028% | -1535978.8444 | 16379.242 | 1683392.0222 | 1028% | -1535978.8444 | 16379.242
21 | Medical alarm system (panic alarm & disabled toilet alarm) | SIS | FOHMEP | 120000 | 0 | 42000 |  |  |  | 0 | 42000 | 100% | 0% | 0% | 42000 | 0 | 0 |  | 78000 | 78000 | 78000 | #REF! | 4200 | 70200 | 167.1% | -32400 | 4200 | 70200 | 167.1% | -32400 | 4200 | 70200 | 167.1% | -32400 | 4200
22 | Landscape secondary structure | RPJV | L'SCAPE (Struct) | 12000000 | 0 | 3380990.5356 |  |  |  | 0 | 3380990.5356 | 51.62% | 44.76% | 3.62% | 1745336.8603 | 1513261.3798 | 122392.2955 |  | 7135159.7115 | 8068729.0375 | 8291345.398 | #REF! | 338099.0536 | 8451546.7781 | 250% | -5408655.2961 | 338099.0536 | 8618509.0485 | 254.9% | -5575617.5665 | 338099.0536 | 8864257.0983 | 262.2% | -5821365.6163 | 338099.0536
23 | ELV specialistic works Hotel Public Areas (2, 4, 28) | SIS | MEP ELV | 500000 | 0 | 400000 | 299387.38 |  |  | 0 | 699387.38 | 100% | 0% | 0% | 699387.38 | 0 | 0 |  | 100000 | 100000 | 100000 | #REF! | 69938.738 | 170000 | 24.31% | 459448.642 | 69938.738 | 170000 | 24.31% | 459448.642 | 69938.738 | 170000 | 24.31% | 459448.642 | 69938.738
24 | Lighting control System Hotel&resi Public Areas | RPJV (CREATION GULF) | MEP ELV | 221365.24 | 0 | 134013.3367 |  |  |  | 0 | 134013.3367 | 51.62% | 44.76% | 3.62% | 69180.441 | 59981.5956 | 4851.3002 |  | 87351.9033 | 87351.9033 | 87351.9033 | #REF! | 13401.3337 | 105419.3823 | 78.66% | 15192.6208 | 13401.3337 | 105419.3823 | 78.66% | 15192.6208 | 13401.3337 | 105419.3823 | 78.66% | 15192.6208 | 13401.3337
25 | Balcony Tiles installation | RPJV | Hotel ID | 577960 | 0 | 276665.2754 |  |  |  | 0 | 276665.2754 | 51.62% | 44.76% | 3.62% | 142820.3061 | 123829.6505 | 10015.3188 |  | 63030.0223 | 163648.1293 | 248295.5343 | #REF! | 27666.5275 | 147283.3164 | 53.24% | 101715.4315 | 27666.5275 | 223465.9809 | 80.77% | 25532.767 | 27666.5275 | 271165.2521 | 98.01% | -22166.5043 | 27666.5275
26 | Supply balcony tiles | RPJV (PORCELLAN) | Hotel ID | 610000 | 0 | 108790.96 |  |  |  | 0 | 108790.96 | 51.62% | 44.76% | 3.62% | 56160.1313 | 48692.5818 | 3938.2468 |  | 137400 | 215609.04 | 423209.04 | #REF! | 10879.096 | 588439.096 | 540.9% | -490527.232 | 10879.096 | 567679.096 | 521.8% | -469767.232 | 10879.096 | 559879.096 | 514.6% | -461967.232 | 10879.096
27 | Fit out Corridors Level 7 to 16 & 19 to 27: wall covering, stones, painting | Existing Guestrooms Subcon (ASI, Al Rawda, Dar al Rokham) | ID - Corridor | 2910913 | 0 | 1461242.069 |  |  |  | 0 | 1461242.069 | 100% | 0% | 0% | 1461242.069 | 0 | 0 |  | 1313063.964 | 1399551.8388 | 1409268.948 | #REF! | 146124.2069 | 1561868.7671 | 106.9% | -246750.905 | 146124.2069 | 1568670.7436 | 107.4% | -253552.8815 | 146124.2069 | 1596952.1317 | 109.3% | -281834.2696 | 146124.2069
28 | Fit out Corridors Level 7 to 16 & 19 to 27: metalworks | RPJV (AHK) | ID - Corridor | 900000 | 0 | 787216.6429 |  |  |  | 0 | 787216.6429 | 100% | 0% | 0% | 787216.6429 | 0 | 0 |  | 94137.1488 | 94137.1488 | 112783.3571 | #REF! | 78721.6643 | 245896.0041 | 31.24% | 462598.9744 | 78721.6643 | 258948.35 | 32.89% | 449546.6286 | 78721.6643 | 258948.35 | 32.89% | 449546.6286 | 78721.6643
29 | External wall cladding instread of GRC (Terraco) | RPJV (Joyz Overseas) | GRC | 1650000 | 0 | 1152066.5827 |  |  |  | 0 | 1152066.5827 | 51.62% | 44.76% | 3.62% | 594720.4676 | 515641.1555 | 41704.9596 |  | 342004.2576 | 388133.4804 | 494277.0175 | #REF! | 115206.6583 | 601693.4363 | 52.23% | 435166.4881 | 115206.6583 | 675993.9122 | 58.68% | 360866.0122 | 115206.6583 | 678553.3921 | 58.9% | 358306.5323 | 115206.6583
30 | Front door ironmongery supply - Guestrooms Hotel | RPJV (Mobility General Trading) | Hotel ID | 105000 | 0 | 105000 |  |  |  | 0 | 105000 | 100% | 0% | 0% | 105000 | 0 | 0 |  | 0 | 0 | 0 | #REF! | 10500 | 0 | 0% | 94500 | 10500 | 0 | 0% | 94500 | 10500 | 0 | 0% | 94500 | 10500
31 | ELV Box in Hotel Guest Rooms | RPJV (ASI) | Hotel ID | 46035 | 0 | 46035 |  |  |  | 0 | 46035 | 100% | 0% | 0% | 46035 | 0 | 0 |  | 0 | 0 | 0 | #REF! | 4603.5 | 0 | 0% | 41431.5 | 4603.5 | 0 | 0% | 41431.5 | 4603.5 | 0 | 0% | 41431.5 | 4603.5
32 | Landscape - Softscape package | RPJV (Fiona Landscape) | L'SCAPE - SOFT | 5110819.99 | 0 | 5101805.95 | 600000 |  |  | 0 | 5701805.95 | 51.62% | 44.76% | 3.62% | 2943389.5156 | 2552010.3202 | 206406.1142 |  | 0 | 0 | 0 | #REF! | 570180.595 | 1022163.798 | 17.93% | 4109461.557 | 570180.595 | 2363750.278 | 41.46% | 2767875.077 | 570180.595 | 2370060.106 | 41.57% | 2761565.249 | 570180.595
| Landscape - Hardscape package | RPJV (Fiona and Al Reem) | L'Scape - HARD | 9234342 | 0 | 9108780.3947 | 828312.515 |  |  | 0 | 9937092.9097 | 51.62% | 44.76% | 3.62% | 5129731.7626 | 4447637.0962 | 359724.0509 |  | 0 | 0 | 125561.6053 | #REF! | 993709.291 | 1846868.352 | 18.59% | 7096515.2667 | 993709.291 | 1934761.4757 | 19.47% | 7008622.143 | 993709.291 | 1934761.4757 | 19.47% | 7008622.143 | 993709.291
| Landscape - MEP package | RPJV (Watermasters) | L'Scape MEP | 4893506 | 0 | 3069103.9334 |  |  |  | 0 | 3069103.9334 | 51.62% | 44.76% | 3.62% | 1584334.5809 | 1373667.3925 | 111101.9601 |  | 1047230.9395 | 1189121.9701 | 1808370.2961 | #REF! | 306910.3933 | 1811086.5891 | 59.01% | 951106.951 | 306910.3933 | 2244560.4173 | 73.13% | 517633.1228 | 306910.3933 | 2255782.6566 | 73.5% | 506410.8835 | 306910.3933
| Landscape - Swimming pool and water features package | RPJV (IKK/ Watermaters/ Reem &Mosaic ?) | L'Scape Pool/WF | 3414995.97 | 0 | 2534770.414 |  |  |  | 0 | 2534770.414 | 51.62% | 44.76% | 3.62% | 1308500.6271 | 1134510.7695 | 91759.0174 |  | 787533.4741 | 820985.56 | 845135.556 | #REF! | 253477.0414 | 1257689.282 | 49.62% | 1023604.0906 | 253477.0414 | 1274594.2792 | 50.28% | 1006699.0934 | 253477.0414 | 1299157.2792 | 51.25% | 982136.0934 | 253477.0414
33 | GRC claddiing to Stair Plaza&retail | RPJV (Arabian Profile Co Limited) | GRC | 581910.664 | 0 | 347256.2464 |  |  |  | 0 | 347256.2464 | 51.62% | 44.76% | 3.62% | 179260.8174 | 155424.708 | 12570.7211 |  | 124510.5073 | 215498.9549 | 215498.9549 | #REF! | 34725.6246 | 261843.9946 | 75.4% | 50686.6272 | 34725.6246 | 261843.9946 | 75.4% | 50686.6272 | 34725.6246 | 274773.9319 | 79.13% | 37756.6899 | 34725.6246
| GRC Fluted Entrances (Hotel Podium) | RPJV (Arabian Profile Co Limited) | GRC | 363022.1242 | 0 | 344871.0242 |  |  |  | 0 | 344871.0242 | 100% | 0% | 0% | 344871.0242 | 0 | 0 |  | 18151.1 | 18151.1 | 18151.1 | #REF! | 34487.1024 | 84856.3925 | 24.61% | 225527.5293 | 34487.1024 | 84856.3925 | 24.61% | 225527.5293 | 34487.1024 | 84856.3925 | 24.61% | 225527.5293 | 34487.1024
| GRP Cladding to underside of Pool view deck at L29 | RPJV (EIFS? Joyz Overseas) | GRC | 74015.3487 | 0 | 0 |  |  |  | 0 | 0 | 100% | 0% | 0% | 0 | 0 | 0 |  | 74015.3487 | 74015.3487 | 74015.3487 | #REF! | 0 | 66613.8138 |  | -66613.8138 | 0 | 66613.8138 |  | -66613.8138 | 0 | 66613.8138 |  | -66613.8138 | 0
| EIFS Cladding at back side and GRC Cladding at front side at Hotel Rooftop Pool Area - Level 29 | RPJV (EIFS & GRCS: Joyz Overseas and APL) | GRC | 485306.76 | 0 | 461041.41 | 170448 |  |  | 0 | 631489.41 | 100% | 0% | 0% | 631489.41 | 0 | 0 |  | 24265.35 | 24265.35 | 24265.35 | #REF! | 63148.941 | 113440.5112 | 17.96% | 454899.9577 | 63148.941 | 113440.5112 | 17.96% | 454899.9577 | 63148.941 | 113440.5112 | 17.96% | 454899.9577 | 63148.941
| GRC Wall Cladding at Hotel Levels 8,11,14,16,21,23,25&27 | RPJV (Arabian Profile Co Limited) | GRC | 95745.1031 | 0 | 50582.8255 |  |  |  | 0 | 50582.8255 | 100% | 0% | 0% | 50582.8255 | 0 | 0 |  | 40850.4312 | 45162.2776 | 45162.2776 | #REF! | 5058.2826 | 49633.5374 | 98.12% | -4108.9944 | 5058.2826 | 49633.5374 | 98.12% | -4108.9944 | 5058.2826 | 49633.5374 | 98.12% | -4108.9944 | 5058.2826
34 | Timber Ceiling and flooring, skirting to match timber flooring | RPJV | Hotel ID | 850000 | 0 | 850000 |  |  |  | 0 | 850000 | 100% | 0% | 0% | 850000 | 0 | 0 |  | 0 | 0 | 0 | #REF! | 85000 | 170000 | 20% | 595000 | 85000 | 170000 | 20% | 595000 | 85000 | 170000 | 20% | 595000 | 85000
| Painted Timber Skirting Hotel Rooms | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 100% | 0% | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 | #REF! | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
35 | Hotel Guestrooms media hub | RPJV | MEP ELV | 103965 | 0 | 103965 |  |  |  | 0 | 103965 | 100% | 0% | 0% | 103965 | 0 | 0 |  | 0 | 0 | 0 | #REF! | 10396.5 | 30000 | 28.86% | 63568.5 | 10396.5 | 30000 | 28.86% | 63568.5 | 10396.5 | 30000 | 28.86% | 63568.5 | 10396.5
36 | Fire Hose Cabinet Doors to Hotel Corridors | RPJV (ASI) | ID - Corridor | 85856.82 | 0 | 85856.82 |  |  |  | 0 | 85856.82 | 100% | 0% | 0% | 85856.82 | 0 | 0 |  | 0 | 0 | 0 | #REF! | 8585.682 | 17171.364 | 20% | 60099.774 | 8585.682 | 17171.364 | 20% | 60099.774 | 8585.682 | 17171.364 | 20% | 60099.774 | 8585.682
| Light fittings Supply for Hotel Corridors | RPJV (Project & Supplies) | MEP Lights | 498657 | 0 | 70025 |  |  |  | 0 | 70025 | 100% | 0% | 0% | 70025 | 0 | 0 |  | 0 | 0 | 0 | #REF! | 7002.5 | 249328.5 | 356.1% | -186306 | 7002.5 | 249328.5 | 356.1% | -186306 | 7002.5 | 635097.3 | 907% | -572074.8 | 7002.5
37 | Light fittings Supply for Hotel Public Areas (LV2,4, 28) excluding L4 | RPJV (Project & Supplies) | MEP Lights | 779967 | 0 | 703598.2 |  |  |  | 0 | 703598.2 | 100% | 0% | 0% | 703598.2 | 0 | 0 |  | 0 | 0 | 0 | #REF! | 70359.82 | 389983.25 | 55.43% | 243255.13 | 70359.82 | 389983.25 | 55.43% | 243255.13 | 70359.82 | 458715.17 | 65.2% | 174523.21 | 70359.82
38 | Light fittings Supply for Residential Public Areas (GF, LV2, LV4, LV23) | RPJV (Project & Supplies) | MEP Lights | 394865.2 | 0 | 222912.798 |  |  |  | 0 | 222912.798 | 51.62% | 44.76% | 3.62% | 115072.1716 | 99771.1543 | 8069.4722 |  | 0 | 0 | 0 | #REF! | 22291.2798 | 197432.6 | 88.57% | 3188.9182 | 22291.2798 | 197432.6 | 88.57% | 3188.9182 | 22291.2798 | 352189.7618 | 158% | -151568.2436 | 22291.2798
39 | Light fittings Supply for Balconies and Tower Façade | RPJV (Project & Supplies) | MEP Lights | 644724 | 0 | 5544 |  |  |  | 0 | 5544 | 51.62% | 44.76% | 3.62% | 2861.9268 | 2481.3796 | 200.6935 |  | 0 | 0 | 0 | #REF! | 554.4 | 322362 | 5815% | -317372.4 | 554.4 | 322362 | 5815% | -317372.4 | 554.4 | 897624 | 16191% | -892634.4 | 554.4
40 | Hotel Ground Floor Light fittings (ballroom&meeting rooms) | RPJV (Project & Supplies) | MEP Lights | 588000 | 0 | 531707.1 |  |  |  | 0 | 531707.1 | 100% | 0% | 0% | 531707.1 | 0 | 0 |  | 0 | 0 | 0 | #REF! | 53170.71 | 294000 | 55.29% | 184536.39 | 53170.71 | 294000 | 55.29% | 184536.39 | 53170.71 | 344663.61 | 64.82% | 133872.78 | 53170.71
41 | Electrical FOH at Level-07 to 11 Hotel | RPJV (Future Metro) | MEP Electrical | 2008965.2212 | 0 | 7579.0509 |  |  |  | 0 | 7579.0509 | 100% | 0% | 0% | 7579.0509 | 0 | 0 |  | 1990433.5789 | 2000527.5672 | 2001386.1702 | #REF! | 757.9051 | 1800474.8105 | 23756% | -1793653.6647 | 757.9051 | 1801247.5532 | 23766% | -1794426.4074 | 757.9051 | 1801247.5532 | 23766% | -1794426.4074 | 757.9051
42 | Electrical FOH at Level-8 Residential | RPJV (Future Metro) | MEP Electrical | 497164.17 | 0 | -0.0017358 |  |  |  | 0 | -0.0017358 | 0% | 100% | 0% | 0 | -0.0017358 | 0 |  | 497164.1717 | 497164.1717 | 497164.1717 | #REF! | -0.00017358 | 447447.7546 | -25777456949% | -447447.7561 | -0.00017358 | 447447.7546 | -25777456949% | -447447.7561 | -0.00017358 | 447447.7546 | -25777456949% | -447447.7561 | -0.00017358
43 | Electrical FOH at Level-12 to 16 Hotel | RPJV (Future Metro) | MEP Electrical | 3876246.9258 | 0 | 36981.5662 |  |  |  | 0 | 36981.5662 | 100% | 0% | 0% | 36981.5662 | 0 | 0 |  | 3800719.9921 | 3835383.5307 | 3839265.3596 | #REF! | 3698.1566 | 3451845.1777 | 9334% | -3418561.768 | 3698.1566 | 3455338.8236 | 9343% | -3422055.414 | 3698.1566 | 3455338.8236 | 9343% | -3422055.414 | 3698.1566
44 | External facade lighting provisions (balcony and void areas) | RPJV (Project & Supplies) | MEP Electrical | 353378.6051 | 0 | 81793.8572 |  |  |  | 0 | 81793.8572 | 51.62% | 44.76% | 3.62% | 42223.6716 | 36609.2374 | 2960.9482 |  | 233676.3344 | 237563.0384 | 249817.3084 | #REF! | 8179.3857 | 213806.7346 | 261.4% | -140192.2631 | 8179.3857 | 224835.5775 | 274.9% | -151221.106 | 8179.3857 | 244426.2731 | 298.8% | -170811.8016 | 8179.3857
45 | Electrical Works Hotel Corridors MEP/ELV | RPJV | MEP Electrical | 300000 | 0 | 102870 |  |  |  | 0 | 102870 | 100% | 0% | 0% | 102870 | 0 | 0 |  | 197130 | 197130 | 197130 | #REF! | 10287 | 197991 | 192.5% | -105408 | 10287 | 197991 | 192.5% | -105408 | 10287 | 197991 | 192.5% | -105408 | 10287
46 | Light fittings for Hotel Public areas (Level 4) | RPJV (Project & Supplies) | MEP Lights | 236349 | 0 | 206182.96 |  |  |  | 0 | 206182.96 | 100% | 0% | 0% | 206182.96 | 0 | 0 |  | 0 | 0 | 0 | #REF! | 20618.296 | 118174.55 | 57.32% | 67390.114 | 20618.296 | 118174.55 | 57.32% | 67390.114 | 20618.296 | 145323.986 | 70.48% | 40240.678 | 20618.296
47,48 | Light fittings Supply for Podium Façade - landscape | RPJV (Project & Supplies) | MEP Lights | 2528753 | 0 | 2528753 | 39169.12 |  |  | 0 | 2567922.12 | 51.62% | 44.76% | 3.62% | 1325614.2196 | 1149348.7869 | 92959.1135 |  | 0 | 0 | 0 | #REF! | 256792.212 | 1264376.5 | 49.24% | 1046753.408 | 256792.212 | 1264376.5 | 49.24% | 1046753.408 | 256792.212 | 1264376.5 | 49.24% | 1046753.408 | 256792.212
49 | Void area lighting Control Cable | RPJV | MEP Electrical | 21500 | 0 | 4891.25 |  |  |  | 0 | 4891.25 | 51.62% | 44.76% | 3.62% | 2524.9639 | 2189.2223 | 177.0639 |  | 16608.75 | 16608.75 | 16608.75 | #REF! | 489.125 | 14947.875 | 305.6% | -10545.75 | 489.125 | 14947.875 | 305.6% | -10545.75 | 489.125 | 14947.875 | 305.6% | -10545.75 | 489.125
50 | Balance Joinery,ironmongery in Hotel Corridors | Momentum Fireguard LLC | ID - Corridor | 620000 | 0 | 597488 |  |  |  | 0 | 597488 | 100% | 0% | 0% | 597488 | 0 | 0 |  | 22512 | 22512 | 22512 | #REF! | 59748.8 | 138587.2 | 23.19% | 399152 | 59748.8 | 138587.2 | 23.19% | 399152 | 59748.8 | 138587.2 | 23.19% | 399152 | 59748.8
51 | Sanitaryware for hotel guestrooms 7A and 15A | RPJV | MEP Sanitary | 216996.19 | 0 | 60370.99 |  |  |  | 0 | 60370.99 | 100% | 0% | 0% | 60370.99 | 0 | 0 |  | 0 | 156625.2 | 156625.2 | #REF! | 6037.099 | 153036.878 | 253.5% | -98702.987 | 6037.099 | 153036.878 | 253.5% | -98702.987 | 6037.099 | 153036.878 | 253.5% | -98702.987 | 6037.099
52 | Ommission Provisional Sum Sanipex (9 rooms 7A,15A,Royal and Presidential Suites | 0 | Hotel ID | -222939 | 0 | -43301.4041 |  |  |  | 0 | -43301.4041 | 100% | 0% | 0% | -43301.4041 | 0 | 0 |  | 0 | 0 | 0 | #REF! | -4330.1404 | 0 | 0% | -38971.2637 | -4330.1404 | 0 | 0% | -38971.2637 | -4330.1404 | -161673.8363 | 373.4% | 122702.5726 | -4330.1404
|  | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | #REF! | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| Provisional Sums to be Awarded | [8 empty] | 0 | 0 |  |  |  | 0 | 0 | 0 | [17 empty] | 0
53 | Signages and wayfinding | Joseph Advertising LLC | ID- Signage | 2000000 | 0 | 2000000 |  |  |  | 0 | 2000000 | 51.62% | 44.76% | 3.62% | 1032441.1393 | 895158.6015 | 72400.2591 |  | 0 | 0 | 0 | #REF! | 200000 | 400000 | 20% | 1400000 | 200000 | 400000 | 20% | 1400000 | 200000 | 400000 | 20% | 1400000 | 200000
54 | Sanitaryware to hotel guestrooms Royal and presidential suites | RPJV (AHK) | MEP Sanitary | 75000 | 0 | 75000 |  |  |  | 0 | 75000 | 100% | 0% | 0% | 75000 | 0 | 0 |  | 0 | 0 | 0 | #REF! | 7500 | 0 | 0% | 67500 | 7500 | 0 | 0% | 67500 | 7500 | 0 | 0% | 67500 | 7500
55 | Additional Fit-out items in guestroom suites (ie. Balustrades) | RPJV (Al Raada) | Hotel ID | 200000 | 0 | 200000 |  |  |  | 0 | 200000 | 100% | 0% | 0% | 200000 | 0 | 0 |  | 0 | 0 | 0 | #REF! | 20000 | 40000 | 20% | 140000 | 20000 | 40000 | 20% | 140000 | 20000 | 40000 | 20% | 140000 | 20000
| Descoped packages to be rescoped and Instructed | [8 empty] | 0 | 0 |  |  |  | 0 | 0 | 0 | [17 empty] | 0
|  | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | #REF! | 0 | 0 |  | 0 | 0 |  |  |  | #REF! |  |  | 0 | 0
56 | Fitout residence public area | AHK | ID - RESI | 4000000 | 0 | 1612611.2 | 542277.42 |  |  | 0 | 2154888.62 | 0% | 100% | 0% | 0 | 2154888.62 | 0 |  | 1997171.7333 | 2203550.4 | 2350230.4 | #REF! | 215488.862 | 2252662.8 | 104.5% | -313263.042 | 215488.862 | 2362672.8 | 109.6% | -423273.042 | 215488.862 | 2390541.6 | 110.9% | -451141.842 | 215488.862
57 | ELV specialistic works Resi Public Areas (G,2, 4, 23) | RPJV | MEP ELV | 371516 | 0 | 282673.2588 |  |  |  | 0 | 282673.2588 | 0% | 100% | 0% | 0 | 282673.2588 | 0 |  | 59851.2276 | 65126.7548 | 88842.7412 | #REF! | 28267.3259 | 58614.0793 | 20.74% | 195791.8536 | 28267.3259 | 79958.4671 | 28.29% | 174447.4658 | 28267.3259 | 79958.4671 | 28.29% | 174447.4658 | 28267.3259
58 | Electrical works resi FOH public areas (GF,2,4,23) | RPJV -Silicon Vega | MEP Electrical | 322543 | 0 | 36221.5789 |  |  |  | 0 | 36221.5789 | 0% | 100% | 0% | 0 | 36221.5789 | 0 |  | 286321.4211 | 286321.4211 | 286321.4211 | #REF! | 3622.1579 | 264933.5948 | 731.4% | -232334.1738 | 3622.1579 | 264933.5948 | 731.4% | -232334.1738 | 3622.1579 | 264933.5948 | 731.4% | -232334.1738 | 3622.1579
| Extra packages required for completion of the project | [8 empty] | 0 | 0 |  |  |  | 0 | 0 | 0 | [17 empty] | 0
|  | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | #REF! | 0 | 0 |  | 0 | 0 |  |  |  | #REF! |  |  |  | 0
59 | Headboards | AHK | Hotel ID | 712815 | 0 | 712815 |  |  |  | 0 | 712815 | 51.62% | 44.76% | 3.62% | 367969.7654 | 319041.2393 | 25803.9954 |  | 0 | 0 | 0 | #REF! | 71281.5 | 169959.2 | 23.84% | 471574.3 | 71281.5 | 169959.2 | 23.84% | 471574.3 | 71281.5 | 169959.2 | 23.84% | 471574.3 | 71281.5
60 | Hotel Kitchen equipment works (Hoods and Cold Rooms only) | TSSC | Kitchens | 1735122 | 487988 | 2223110 | 208941.9 |  |  | 0 | 2432051.9 | 100% | 0% | 0% | 2432051.9 | 0 | 0 |  | 0 | 0 | 0 | #REF! | 243205.19 | 670398 | 27.57% | 1518448.71 | 243205.19 | 670398 | 27.57% | 1518448.71 | 243205.19 | 670398 | 27.57% | 1518448.71 | 243205.19
61 | Kitchens and BOH Areas - GF,L2, L28 (Fitout) | RPJV | Hotel ID | 580000 | 0 | 580000 |  |  |  | 0 | 580000 | 51.62% | 44.76% | 3.62% | 299407.9304 | 259595.9944 | 20996.0752 |  | 0 | 0 | 0 | #REF! | 58000 | 116000 | 20% | 406000 | 58000 | 116000 | 20% | 406000 | 58000 | 116000 | 20% | 406000 | 58000
62 | 2 No. Penthouse lifts and 2 No. Retail Lobby Lifts (Coring only by RPJV, Lifts by OM) | RPJV | Hotel ID | 300000 | 0 | 300000 |  |  |  | 0 | 300000 | 51.62% | 44.76% | 3.62% | 154866.1709 | 134273.7902 | 10860.0389 |  | 0 | 0 | 0 | #REF! | 30000 | 60000 | 20% | 210000 | 30000 | 60000 | 20% | 210000 | 30000 | 60000 | 20% | 210000 | 30000
63 | Carpet and Wallpaper for Hotel | Goodrich and CSI | Hotel ID | 2000000 | 0 | 2000000 |  |  |  | 0 | 2000000 | 100% | 0% | 0% | 2000000 | 0 | 0 |  | 0 | 0 | 0 | #REF! | 200000 | 1188454.595 | 59.42% | 611545.405 | 200000 | 1188454.595 | 59.42% | 611545.405 | 200000 | 1188454.595 | 59.42% | 611545.405 | 200000
| Descoped Packages to be Rescoped | [8 empty] | 0 | 0 |  |  |  | 0 | 0 | 0 | [17 empty] | 0
|  | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | #REF! | 0 | 0 |  | 0 | 0 |  |  |  | #REF! |  |  |  | 0
64 | Turn Key Fitout -Ball Room L0 | AHK (Rattan House/DAR) | ID Ballroom | 5000000 | 0 | 4742695.1879 |  |  |  | 0 | 4742695.1879 | 100% | 0% | 0% | 4742695.1879 | 0 | 0 |  | 95000 | 95000 | 125000 | #REF! | 474269.5188 | 1385387.8 | 29.21% | 2883037.8691 | 474269.5188 | 1373112.9603 | 28.95% | 2895312.7088 | 474269.5188 | 1434539.7432 | 30.25% | 2833885.9259 | 474269.5188
65 | MEP and ELV - Ball room L0+Additional lift | AHK (Golden Oasis/SIS/Kone) | ID Ballroom | 1000000 | 594439 | 1272131.8738 |  |  |  | 0 | 1272131.8738 | 100% | 0% | 0% | 1272131.8738 | 0 | 0 |  | 0 | 0 | 166374.1985 | #REF! | 127213.1874 | 0 | 0% | 1144918.6864 | 127213.1874 | 149736.7786 | 11.77% | 995181.9078 | 127213.1874 | 290076.4136 | 22.8% | 854842.2728 | 127213.1874
65 | Royalsuits fitout works | AHK (Decolab/SIS/gldn oasis/DAR) | ID Various | 1718372.7909 | 0 | 1664536.4694 |  |  |  | 0 | 1664536.4694 | 100% | 0% | 0% | 1664536.4694 | 0 | 0 |  | 17269.4876 | 0 | 0 | #REF! | 166453.6469 | 343674.5582 | 20.65% | 1154408.2643 | 166453.6469 | 343674.5582 | 20.65% | 1154408.2643 | 166453.6469 | 381359.9833 | 22.91% | 1116722.8392 | 166453.6469
65 | Presidential suites fitout works | AHK (Decolab/SIS/gldn oasis/DAR) | ID Various | 1829208.4191 | 0 | 1765759.694 |  |  |  | 0 | 1765759.694 | 100% | 0% | 0% | 1765759.694 | 0 | 0 |  | 6951.0591 | 0 | 0 | #REF! | 176575.9694 | 365841.6838 | 20.72% | 1223342.0408 | 176575.9694 | 365841.6838 | 20.72% | 1223342.0408 | 176575.9694 | 410255.7914 | 23.23% | 1178927.9332 | 176575.9694
65 | Royal and Presidential Suites MEP Works | AHK (Golden Oasis) | ID Various | 412877.79 | 0 | 264151.4119 |  |  |  | 0 | 264151.4119 | 100% | 0% | 0% | 264151.4119 | 0 | 0 |  | 0 | 106216.9403 | 106216.9403 | #REF! | 26415.1412 | 156927.4162 | 59.41% | 80808.8545 | 26415.1412 | 156927.4162 | 59.41% | 80808.8545 | 26415.1412 | 186684.0227 | 70.67% | 51052.248 | 26415.1412
65 | LV 28 Gym fitout works | AHK (Decolab/SIS/gldn oasis/DAR) | ID Various | 413000 | 1466 | 383761.3313 |  |  |  | 0 | 383761.3313 | 100% | 0% | 0% | 383761.3313 | 0 | 0 |  | 0 | 0 | 0 | #REF! | 38376.1331 | 82600 | 21.52% | 262785.1982 | 38376.1331 | 82600 | 21.52% | 262785.1982 | 38376.1331 | 110234.2018 | 28.72% | 235150.9963 | 38376.1331
65 | LV 28 Gym MEP (electrical, ELV and lighting) | AHK (Golden Oasis/SIS) | ID Various | 150000 | 0 | 112750.7058 |  |  |  | 0 | 112750.7058 | 100% | 0% | 0% | 112750.7058 | 0 | 0 |  | 0 | 28575.5842 | 30033.0342 | #REF! | 11275.0706 | 50002.909 | 44.35% | 51472.7262 | 11275.0706 | 51023.124 | 45.25% | 50452.5112 | 11275.0706 | 56074.506 | 49.73% | 45401.1292 | 11275.0706
65 | Turn Key Fitout - GF and Level 1 Ablution | AHK (Decolab/SIS/gldn oasis/DAR) | ID Various | 358982.5595 | 392324.8705 | 751307.43 |  |  |  | 0 | 751307.43 | 100% | 0% | 0% | 751307.43 | 0 | 0 |  | 0 | 0 | 0 | #REF! | 75130.743 | 150261.486 | 20% | 525915.201 | 75130.743 | 150261.486 | 20% | 525915.201 | 75130.743 | 150261.486 | 20% | 525915.201 | 75130.743
65 | Turn Key Fitout - Rooftop LV 29 (amenties) | AHK (Decolab/SIS/gldn oasis/DAR) | ID Various | 513931.25 | 561665.2 | 1075596.45 |  |  |  | 0 | 1075596.45 | 100% | 0% | 0% | 1075596.45 | 0 | 0 |  | 0 | 0 | 0 | #REF! | 107559.645 | 215119.29 | 20% | 752917.515 | 107559.645 | 215119.29 | 20% | 752917.515 | 107559.645 | 215119.29 | 20% | 752917.515 | 107559.645
65 | MEP Works - GF,Level 1 Ablution room and Roof Top L29 | AHK (Golden Oasis) | ID Various | 127086.1904 | 138889.9596 | 208994.1436 |  |  |  | 0 | 208994.1436 | 100% | 0% | 0% | 208994.1436 | 0 | 0 |  | 0 | 52404.5981 | 54272.6245 | #REF! | 20899.4144 | 47164.1383 | 22.57% | 140930.591 | 20899.4144 | 48845.362 | 23.37% | 139249.3672 | 20899.4144 | 51283.8057 | 24.54% | 136810.9236 | 20899.4144
65 | Turnkey fitout - Signature resturant LV 17 | 0 | 0 | Excluded | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | #REF! | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
65 | Electrical Works Hotel FOH Public area - LV17, LV29 including ELV | 0 | 0 | Excluded | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | #REF! | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
65 | Lighting fitting supply (L29, L17 | 0 | 0 | Excluded | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | #REF! | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
65 | Carpet - Guest rooms Hotel | 0 | 0 | Excluded | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | #REF! | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
65 | Decorative Wall Covering - Guest room Hotels | 0 | 0 | Excluded | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | #REF! | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
65 | Light fittings (Inc. point wiring, switches and sockets) - Residence Corridor | 0 | 0 | Excluded | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | #REF! | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
66 | Psum Steel Cabana Level 29 (e/over) | [5 empty] | 423000 |  |  | 0 | 423000 | 100% | 0% | 0% | 423000 | 0 | 0 | [11 empty] | 0% |  |  |  | 0% |  | 42300
| Total |  |  | 254685032.722 | 2176773.03 | 91512169.6312 | 5004306.89 | 0 | 0 | 1921464.25 | 98437940.7712 |  |  |  | 69431612.1478 | 27020957.7854 | 1985370.838 |  | 157829596.8383 | 162406612.9171 | 166909017.3021 | #REF! | 9801494.0771 | 167472128.3021 |  | -79258681.608 | 9801494.0771 | 171643352.5816 |  | -83429905.8875 | #REF! | 173760212.6254 |  | -85546765.9313 | 9843794.0771 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | KEY: | [5 empty] | reconcile with Contract Sum | [10 empty] | NOTE: Reconciled to MATCH with MOS & VARIATIONS ADDED - refer to Contract Sum Sheet for Reconciliation
|  | MEP | MEP Electrical | 9986424.922 | 0 | 456205.1291 | 0 | #REF! | #REF! |  | 456205.1291 | [6 empty] | 0 | 9221811.3007 | 9270455.5317 | 9508452.3534
|  |  | MEP - ELV | 5251961.24 | 0 | 1665664.2611 | 413216.7 | #REF! | #REF! |  | 2078880.9611 | [6 empty] | 0 | 3960945.4614 | 3970785.5925 | 3993499.2789
|  |  | MEP Sanitary | 4635198.25 | 0 | 787143.091 | 0 | #REF! | #REF! |  | 787143.091 | [6 empty] | 0 | 3388873.173 | 3547406.0975 | 3548564.159
|  |  | MEP Lights | 6183623.2 | 0 | 4268723.058 | 39169.12 | #REF! | #REF! |  | 4307892.178 | [6 empty] | 0 | 512308 | 512308 | 512308
|  |  | MEP - LIFT | 13988719 | 0 | 914370.9411 | 576000 | #REF! | #REF! |  | 1780711.6911 | [6 empty] | 0 | 13211055.6976 | 13275588.8268 | 13498736.7656
|  |  | FOHMEP | 2100228 | 0 | 205792.4198 | 0 | #REF! | #REF! |  | 205792.4198 | [6 empty] | 0 | 1948435.5802 | 1948435.5802 | 1948435.5802
|  |  | Kitchens | 1735122 | 487988 | 2223110 | 208941.9 | #REF! | #REF! |  | 2432051.9 | [6 empty] | 0 | 0 | 0 | 0
|  | Façade | FAÇADE | 58250000 | 0 | 12659930.806 | 996483.4 | #REF! | #REF! |  | 15017414.206 | [6 empty] | 0 | 49238381.1145 | 49627038.8325 | 49841254.7173
|  |  | GRC | 21550000 | 0 | 3841451.4454 | 170448 | #REF! | #REF! |  | 4160822.9454 | [6 empty] | 0 | 16674918.2965 | 17096638.2579 | 17688463.7487
|  |  | Balustrade | 9063400 | 0 | 1322126.0376 | 0 | #REF! | #REF! |  | 1443326.0376 | [6 empty] | 0 | 7934080.6062 | 7956481.3071 | 8083920.889
|  |  | BMU | 2111400 | 0 | 828861.0695 | 0 | #REF! | #REF! |  | 828861.0695 | [6 empty] | 0 | 816514.6305 | 816514.6305 | 921931.9305
|  |  | Façade Ceiling | 3480715 | 0 | 806979.0395 | 0 | #REF! | #REF! |  | 806979.0395 | [6 empty] | 0 | 2555487.0413 | 2560516.9721 | 2602165.9584
|  | Fit-Out | Hotel ID | 32641333.33 | 0 | 9399642.7356 | -22924.62 | #REF! | #REF! |  | 9376718.1156 | [6 empty] | 0 | 21676686.0134 | 22190196.8897 | 22735543.72
|  |  | ID - Corridor | 4516769.82 | 0 | 2931803.5319 | 0 | #REF! | #REF! |  | 2931803.5319 | [6 empty] | 0 | 1429713.1128 | 1516200.9875 | 1544564.3051
|  |  | Rooms Joinery | 15666124 | 0 | 6172121.1917 | 0 | #REF! | #REF! |  | 6172121.1917 | [6 empty] | 0 | 9346442.1309 | 9648441.6399 | 9923999.9627
|  |  | ID - Pareas | 11346891 | 0 | 3978497.7485 | 229382.455 | #REF! | #REF! |  | 4207880.2035 | [6 empty] | 0 | 4827628.2741 | 5905019.6809 | 6654635.8805
|  |  | ID Ballroom | 6000000 | 594439 | 6014827.0617 | 0 | #REF! | #REF! |  | 6014827.0617 | [6 empty] | 0 | 95000 | 95000 | 291374.1985
|  |  | ID Various | 5523459 | 1094346.03 | 6226857.636 | 0 | #REF! | #REF! |  | 6226857.636 | [6 empty] | 0 | 24220.5466 | 187197.1226 | 190522.599
|  |  | ID - RESI | 4000000 | 0 | 1612611.2 | 542277.42 | #REF! | #REF! |  | 2154888.62 | [6 empty] | 0 | 1997171.7333 | 2203550.4 | 2350230.4
|  |  | ID- Signage | 2000000 | 0 | 2000000 | 0 | #REF! | #REF! |  | 2000000 | [6 empty] | 0 | 0 | 0 | 0
|  | External | L'SCAPE (Struct) | 12000000 | 0 | 3380990.5356 | 0 | #REF! | #REF! |  | 3380990.5356 | [6 empty] | 0 | 7135159.7115 | 8068729.0375 | 8291345.398
|  |  | L'SCAPE - SOFT | 5110819.99 | 0 | 5101805.95 | 600000 | #REF! | #REF! |  | 5701805.95 | [6 empty] | 0 | 0 | 0 | 0
|  |  | L'Scape - HARD | 9234342 | 0 | 9108780.3947 | 828312.515 | #REF! | #REF! |  | 9937092.9097 | [6 empty] | 0 | 0 | 0 | 125561.6053
|  |  | L'Scape MEP | 4893506 | 0 | 3069103.9334 | 0 | #REF! | #REF! |  | 3069103.9334 | [6 empty] | 0 | 1047230.9395 | 1189121.9701 | 1808370.2961
|  |  | L'Scape Pool/WF | 3414995.97 | 0 | 2534770.414 | 0 | #REF! | #REF! |  | 2534770.414 | [6 empty] | 0 | 787533.4741 | 820985.56 | 845135.556
|  |  |  | 254685032.722 | 2176773.03 | 91512169.6312 | 4581306.89 | #REF! | #REF! |  | 98014940.7712 | [6 empty] | 0 | 157829596.8383 | 162406612.9171 | 166909017.3021
|  |  | check | 0 | 0 | 0 | 423000 | #REF! | #REF! |  | 423000 | [6 empty] | 0 | 0 | 0 | 0

## PS COMPLETED WORKS 171m (2)
PLOT 18
|  | VALUE OF WORKS TO COMPLETE - PROVISONAL SUM PACKAGES | [6 empty] | Does Not RECONCILE with Contract Sum (5. Psums and 9 VO's)
|  | AS AT 25-FEB-2022 | [6 empty] | AGREED UNDER ADDENDUM 2 | [50 empty] | DEBT OWED
[9 empty] | Nil value items in Addendum 2 | [9 empty] | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan
No | Item No. | Package | Contractor | Category | FINAL ESTIMATED PACKAGE SUM | ADDENDUM -2 INSTRUCTED AMOUNT | AWRDED AFTER ADDENDUM-2 | REVISED CONTRACT AMOUNT | VARIATIONS (Addendum 2) | Hotel Component | Residence Component | Retail Component | FINAL ESTIMATED PACKAGE SUM | FINAL ESTIMATED PACKAGE SUM | Hotel | Resident | Retail |  | Gross certification to Nov-21 (incl. MOS excl. advance payments, recovery and retention) IPC 46 | Hotel | Resident | Retail | Gross certification to Nov-21 (incl. MOS excl. advance payments, recovery and retention) IPC 47 | Hotel | Resident | Retail | Gross certification to Dec-21 (incl. MOS excl. advance payments, recovery and retention) IPC 48 | Hotel | Resident | Retail | Gross Certification upto January 2022 (incl. MOS excl. advance payments, recovery and retention) IPC 49 |  | Value of Works remaining to be certified | Hotel | Resident | Retail |  | Net Paid Amount (incl. MOS, advance payments, recovery and retention) IPC 46 |  | Amount remaining to be paid at the end of IPC 46 | Retention to be released | Net Paid Amount (incl. MOS, advance payments, recovery and retention) IPC 47 |  | Amount remaining to be paid at the end of IPC 47 | Retention to be released | Net Paid Amount (incl. MOS, advance payments, recovery and retention) IPC 48 |  | Amount remaining to be paid at the end of IPC 48 | Retention to be released | Net Paid Amount upto (incl. MOS, advance payments, recovery and retention) IPC 49 |  | Amount remaining to be paid at the end of IPC 49 | Retention to be released | Preliminaries | Podium | Terraces | MEP | Apartments | Other | PDC's (Feb & Mar-22) | SOA Delta (up to Oct-22) | Nov Owed | Dec Owed | Jan Owed
Awarded Provisional Sums
1 | 1 | Electrical works Hotel Public areas | BOND INTERIORS | ID - Pareas | 237871.59 | 751671 | 0 | 751671 | 0 | 100% | 0% | 0% | 237871.59 | 751671 | 237871.59 | 0 | 0 |  | 388302.6 | 388302.6 | 0 | 0 | 461484.39 | 461484.39 | 0 | 0 | 483592.6 | 483592.6 | 0 | 0 | 513799.41 | 68.35% | 237871.59 | 513799.41 | 0 | 0 | 0 | 458482.86 | 61% | 218021.04 | 75167.1 | 502391.934 | 66.84% | 174111.966 | 75167.1 | 515656.86 | 68.6% | 160847.04 | 75167.1 | 545163.921 | 72.53% | 151990.6869 | 54516.3921 | [8 empty] | 43909.074 | 13264.926 | 29507.061
2 | 2 | Fit out Hotel Public areas | BOND INTERIORS | ID-Pareas | 3970008.61 | 10595220 | 0 | 10595220 | 0 | 100% | 0% | 0% | 3970008.61 | 10595220 | 3970008.61 | 0 | 0 |  | 4439325.6741 | 4439325.6741 | 0 | 0 | 5443535.2909 | 5443535.2909 | 0 | 0 | 6171043.2805 | 6171043.2805 | 0 | 0 | 6854593.8415 | 64.7% | 3740626.1585 | 6854593.8415 | 0 | 0 | 229382.4515 | 5842161.4045 | 55.14% | 3693536.5955 | 1059522 | 6444687.1745 | 60.83% | 3091010.8255 | 1059522 | 6881191.9683 | 64.95% | 2654506.0317 | 1059522 | 7291322.3049 | 68.82% | 2574765.4646 | 729132.2305 | [7 empty] | 2996.31 | 602525.7701 | 436504.7938 | 410130.3366
3 | 3 | Electrical works Hotel 19-27 | SILICON VEGA | MEP Electrical | 0 | 2090511 | 0 | 2090511 | 0 | 100% | 0% | 0% | 0 | 2090511 | 0 | 0 | 0 |  | 1912976.9824 | 1912976.9824 | 0 | 0 | 1912976.9824 | 1912976.9824 | 0 | 0 | 1912976.9824 | 1912976.9824 | 0 | 0 | 1912976.9824 | 91.51% | 177534.0176 | 1912976.9824 | 0 | 0 | -177534.0176 | 1748309.7368 | 83.63% | 133150.1632 | 209051.1 | 1748309.7368 | 83.63% | 133150.1632 | 209051.1 | 1748309.7368 | 83.63% | 133150.1632 | 209051.1 | 1748309.7368 | 83.63% | 167370.2895 | 174830.9737 | [8 empty] | 0 | 0 | 0
4 | 4 | Supply Wiring accessories Hotel | SMKA | MEP Electrical | 0 | 516116 | 0 | 516116 | 0 | 100% | 0% | 0% | 0 | 516116 | 0 | 0 | 0 |  | 286780.07 | 286780.07 | 0 | 0 | 286780.07 | 286780.07 | 0 | 0 | 507782.19 | 507782.19 | 0 | 0 | 507782.19 | 98.39% | 8333.81 | 507782.19 | 0 | 0 | -8333.81 | 487437.843 | 94.44% | -22933.443 | 51611.6 | 487437.843 | 94.44% | -22933.443 | 51611.6 | 465337.631 | 90.16% | -833.231 | 51611.6 | 465337.631 | 90.16% | 4244.6059 | 46533.7631 | [8 empty] | 0 | -22100.212 | 0
5 | 5 | ELV hotel 19 & 27 | SIS | MEP ELV | 90611.54 | 371106 | 0 | 371106 | 0 | 100% | 0% | 0% | 90611.54 | 371106 | 90611.54 | 0 | 0 |  | 300929.8554 | 300929.8554 | 0 | 0 | 305494.4592 | 305494.4592 | 0 | 0 | 305494.4592 | 305494.4592 | 0 | 0 | 305494.4592 | 82.32% | 65611.5408 | 305494.4592 | 0 | 0 | 24999.9992 | 281363.3916 | 75.82% | 52632.0085 | 37110.6 | 284786.8444 | 76.74% | 49208.5556 | 37110.6 | 284786.8444 | 76.74% | 49208.5556 | 37110.6 | 284786.8444 | 76.74% | 57840.4712 | 28478.6844 | [8 empty] | 3423.4529 | 0 | 0
6 | 6 | Void Column light fittings | Bayt Al Tawreed Trading LLC | MEP Lights | 0 | 512308 | 0 | 512308 | 0 | 51.62% | 44.76% | 3.62% | 0 | 512308 | 0 | 0 | 0 |  | 512308 | 264463.9276 | 229298.4564 | 18545.616 | 512308 | 264463.9276 | 229298.4564 | 18545.616 | 512308 | 264463.9276 | 229298.4564 | 18545.616 | 512308 | 100% | 0 | 264463.9276 | 229298.4564 | 18545.616 | 0 | 461077.2 | 90% | 0 | 51230.8 | 461077.2 | 90% | 0 | 51230.8 | 461077.2 | 90% | 0 | 51230.8 | 461077.2 | 90% | 5123.08 | 46107.72 | [8 empty] | 0 | 0 | 0
7 | 7 | BMU | E W Cox Middle East LLC | BMU | 828861.07 | 2111400 | 0 | 2111400 | -360607 | 51.62% | 44.76% | 3.62% | 828861.07 | 1750793 | 427875.1337 | 370981.0581 | 30004.8781 |  | 816514.6305 | 421501.6477 | 365455.0474 | 29557.9354 | 816514.6305 | 421501.6477 | 365455.0474 | 29557.9354 | 921931.9305 | 475920.2263 | 412637.6488 | 33374.0553 | 921931.9305 | 52.66% | 828861.0695 | 475920.2263 | 412637.6488 | 33374.0553 | 0.0005 | 843938.8386 | 48.2% | 731774.8614 | 175079.3 | 848263.2136 | 48.45% | 727450.4864 | 175079.3 | 929961.6211 | 53.12% | 645752.0789 | 175079.3 | 925637.2461 | 52.87% | 732592.0292 | 92563.7246 | [7 empty] | 34796.88 | 4324.375 | 81698.4075 | -4324.375
8 | 8 | Hotel Ceiling and partition | Al Rawda General Maintenance and Decoration Co LLC | Hotel ID | 47336.98 | 8101444.13 | 0 | 8101444.13 | 0 | 100% | 0% | 0% | 47336.98 | 8101444.13 | 47336.98 | 0 | 0 |  | 8025361.6534 | 8025361.6534 | 0 | 0 | 8025361.6534 | 8025361.6534 | 0 | 0 | 8054107.1494 | 8054107.1494 | 0 | 0 | 8054107.1494 | 99.42% | 47336.9806 | 8054107.1494 | 0 | 0 | -0.00055556 | 7222825.488 | 89.15% | 68474.229 | 810144.413 | 7222825.488 | 89.15% | 68474.229 | 810144.413 | 7248696.4345 | 89.47% | 42603.2825 | 810144.413 | 7248696.4345 | 89.47% | 127878.0521 | 724869.6434 | [6 empty] | 810000 |  | 0 | 25870.9465 | 0
9 | 9 | Sanitary ware | Sanipex LLC | MEP Sanitary | 652670.1 | 4023939.06 | 0 | 4023939.06 | -299491 | 100% | 0% | 0% | 652670.1 | 3724448.06 | 652670.1 | 0 | 0 |  | 3289873.173 | 3289873.173 | 0 | 0 | 3291780.8975 | 3291780.8975 | 0 | 0 | 3292938.959 | 3292938.959 | 0 | 0 | 3292938.959 | 88.41% | 431509.101 | 3292938.959 | 0 | 0 | 221160.999 | 2960885.8557 | 79.5% | 391117.3983 | 372444.806 | 2962602.8077 | 79.54% | 389400.4463 | 372444.806 | 2963645.0631 | 79.57% | 388358.1909 | 372444.806 | 2963645.0631 | 79.57% | 464438.4906 | 296364.5063 | [6 empty] | 135000 | -295250.03 | 1716.9521 | 1042.2554 | 0
10 | 10a | Hotel guestroom Sanitary ware descope from Sanipex in lieu of Al Futtaim | Al Futtaim Engineering LLC | MEP Sanitary | 220263 | 220263 | 0 | 220263 | 0 | 100% | 0% | 0% | 220263 | 220263 | 220263 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 220263 | 0 | 0 | 0 | 0 | 220263 | 100% | -22026.3 | 22026.3 | 220263 | 100% | -22026.3 | 22026.3 | 220263 | 100% | -22026.3 | 22026.3 | 220263 | 100% | -22026.3 | 22026.3 | [8 empty] | 0 | 0 | 0
11 | 10b | Hotel guestroom Sanitary ware descope from sanipex (Already in PS VO-154) | Bette GmbH & Co. KG | MEP Sanitary | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 78608 |  | -78608 | 0 | 78608 |  | -78608 | 0 | 78608 |  | -78608 | 0 | 78608 |  | -86468.8 | 7860.8 | [8 empty] | 0 | 0 | 0
|  |  | Taps&More | MEP Sanitary | 0 | 99000 | 0 | 99000 | 0 | 100% | 0% | 0% | 0 | 99000 | 0 | 0 | 0 |  | 99000 | 99000 | 0 | 0 | 99000 | 99000 | 0 | 0 | 99000 | 99000 | 0 | 0 | 99000 | 100% | 0 | 99000 | 0 | 0 | 0 | 89100 | 90% | 0 | 9900 | 89100 | 90% | 0 | 9900 | 89100 | 90% | 0 | 9900 | 89100 | 90% | 990 | 8910 | [8 empty] | 0 | 0 | 0
12 | 11 | Hotel guestroom Sanitary ware descope from sanipex | Taps&More | MEP Sanitary | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | [8 empty] | 0 | 0 | 0
13 | 12 | Access control system Hotel Gust room | Creation Gulf Trading LLC | MEP ELV | 793230.44 | 3684009 | 0 | 3684009 | 407202.3 | 100% | 0% | 0% | 793230.44 | 4091211.3 | 793230.44 | 0 | 0 |  | 3412812.4752 | 3412812.4752 | 0 | 0 | 3412812.4752 | 3412812.4752 | 0 | 0 | 3411810.1752 | 3411810.1752 | 0 | 0 | 3411810.1752 | 83.39% | 679401.1248 | 3411810.1752 | 0 | 0 | 113829.3152 | 3071531.2277 | 75.08% | 610558.9423 | 409121.13 | 3071531.2277 | 75.08% | 610558.9423 | 409121.13 | 3070629.1577 | 75.05% | 611461.0123 | 409121.13 | 3070629.1577 | 75.05% | 713519.2266 | 307062.9158 | [7 empty] | 97896.53 | 0 | -902.07 | 0
14 |  | Stone works | Dar Al Rokham LLC | Hotel ID | 2614074.92 | 14192643.2 | 0 | 14192643.2 | -76663.37 | 100% | 0% | 0% | 2614074.92 | 14115979.83 | 2614074.92 | 0 | 0 |  | 10669855.6027 | 10669855.6027 | 0 | 0 | 10910208.9411 | 10910208.9411 | 0 | 0 | 11095280.4567 | 11095280.4567 | 0 | 0 | 11501904.9066 | 81.48% | 2614074.9234 | 11501904.9066 | 0 | 0 | -0.0033955 | 9864541.312 | 69.88% | 2839840.535 | 1411597.983 | 10039130.0925 | 71.12% | 2665251.7545 | 1411597.983 | 10173306.9413 | 72.07% | 2531074.9057 | 1411597.983 | 10467777.0573 | 74.16% | 2601425.067 | 1046777.7057 | [6 empty] | 660000 | 176391.94 | 174588.7806 | 134176.8488 | 294470.1159
15 |  | Ironmongery supply | Momentum Fireguard LLC | Hotel ID | 193002.78 | 1177018 | 0 | 1177018 | 60000 | 100% | 0% | 0% | 193002.78 | 1237018 | 193002.78 | 0 | 0 |  | 988555.1162 | 988555.1162 | 0 | 0 | 988555.1162 | 988555.1162 | 0 | 0 | 988555.1162 | 988555.1162 | 0 | 0 | 1021090.5962 | 82.54% | 215927.4038 | 1021090.5962 | 0 | 0 | -22924.6238 | 889699.6046 | 71.92% | 223616.5954 | 123701.8 | 891331.2151 | 72.05% | 221984.9849 | 123701.8 | 891331.2151 | 72.05% | 221984.9849 | 123701.8 | 918981.5366 | 74.29% | 226138.3098 | 91898.1537 | [7 empty] | 74005.9 | 1631.6105 | 0 | 27650.3215
16 | 13 | Joinery works | Alshafar Interiors Co LLC | Rooms Joinery | 6172121.19 | 11437852 | 0 | 11437852 | 543568.3826 | 100% | 0% | 0% | 6172121.19 | 11981420.3826 | 6172121.19 | 0 | 0 |  | 5118170.1309 | 5118170.1309 | 0 | 0 | 5420169.6399 | 5420169.6399 | 0 | 0 | 5695727.9627 | 5695727.9627 | 0 | 0 | 5809299.1909 | 48.49% | 6172121.1917 | 5809299.1909 | 0 | 0 | -0.0017361 | 5426350.3449 | 45.29% | 5356927.9995 | 1198142.0383 | 5739489.9209 | 47.9% | 5043788.4235 | 1198142.0383 | 5939269.7049 | 49.57% | 4844008.6395 | 1198142.0383 | 5927418.9134 | 49.47% | 5461259.5779 | 592741.8913 | [7 empty] | 634296.58 | 313139.576 | 199779.784 | -11850.7915
17 | 14 | Internal Glazing | Joseph Decorative Glass | Hotel ID | 1172280.69 | 2072163 | 0 | 2072163 | 0 | 100% | 0% | 0% | 1172280.69 | 2072163 | 1172280.69 | 0 | 0 |  | 717106.3476 | 717106.3476 | 0 | 0 | 802711.1502 | 802711.1502 | 0 | 0 | 820658.8241 | 820658.8241 | 0 | 0 | 899882.31 | 43.43% | 1172280.69 | 899882.31 | 0 | 0 | -2.9164e-05 | 830726.102 | 40.09% | 1034220.598 | 207216.3 | 892789.5839 | 43.08% | 972157.1161 | 207216.3 | 905801.6475 | 43.71% | 959145.0525 | 207216.3 | 963238.6747 | 46.48% | 1012600.4578 | 96323.8675 | [7 empty] | 4572.04 | 62063.4819 | 13012.0636 | 57437.0273
18 |  | External Ceiling | Al Rawda General Maintenance and Decoration Co LLC | Façade Ceiling | 806979.04 | 3480715 | 0 | 3480715 | 0 | 51.62% | 44.76% | 3.62% | 806979.04 | 3480715 | 416579.1797 | 361187.1145 | 29212.7458 |  | 2555487.0413 | 1319194.9762 | 1143783.1031 | 92508.962 | 2560516.9721 | 1321791.53 | 1146034.396 | 92691.0462 | 2602165.9584 | 1343291.5934 | 1164675.6201 | 94198.7449 | 2673735.9605 | 76.82% | 806979.0395 | 1380237.5006 | 1196708.8716 | 96789.5882 | 0.00047008 | 2299938.3372 | 66.08% | 832705.1628 | 348071.5 | 2304465.2749 | 66.21% | 828178.2251 | 348071.5 | 2341949.3625 | 67.28% | 790694.1375 | 348071.5 | 2406362.3644 | 69.13% | 833716.3991 | 240636.2364 | [7 empty] | -307788.35 | 4526.9377 | 37484.0876 | 64413.0019
19 |  | Internal & external painting | Al Rawda General Maintenance and Decoration Co LLC | Hotel ID | 214017.91 | 1339194 | 0 | 1339194 | 0 | 51.62% | 44.76% | 3.62% | 214017.91 | 1339194 | 110480.4474 | 95789.9865 | 7747.4761 |  | 1075377.2713 | 555131.8676 | 481316.6071 | 38928.7966 | 1084102.8595 | 559636.1957 | 485221.9998 | 39244.664 | 1105437.5992 | 570649.6272 | 494770.9877 | 40016.9843 | 1125176.0935 | 84.02% | 214017.9065 | 580839.044 | 503605.5292 | 40731.5204 | 0.0035212 | 967839.5441 | 72.27% | 237435.0559 | 133919.4 | 975692.5735 | 72.86% | 229582.0265 | 133919.4 | 994893.8393 | 74.29% | 210380.7607 | 133919.4 | 1012658.4842 | 75.62% | 225269.6674 | 101265.8484 | [8 empty] | 7853.0294 | 19201.2657 | 17764.6449
20 | 15 | GRC claddiing -Edge Profile | Arabian Profile Co Limited | GRC | 1634556.86 | 18300000 | 0 | 18300000 | 159321.67 | 51.62% | 44.76% | 3.62% | 1634556.86 | 18459321.67 | 843791.8734 | 731593.8165 | 59171.1701 |  | 16051121.3017 | 8285918.982 | 7184149.6488 | 581052.6709 | 16331411.7463 | 8430610.675 | 7309601.85 | 591199.2214 | 16817093.7001 | 8681329.6898 | 7526983.0392 | 608780.971 | 16973688.3134 | 91.95% | 1485633.3566 | 8762167.0504 | 7597071.5468 | 614449.7163 | 148923.5034 | 15272427.617 | 82.74% | 1340961.886 | 1845932.167 | 15264129.3971 | 82.69% | 1349260.1059 | 1845932.167 | 15652674.96 | 84.8% | 960714.543 | 1845932.167 | 15440578.6823 | 83.65% | 1474685.1194 | 1544057.8682 | [7 empty] | 90888.66 | -8298.2199 | 388545.563 | -212096.2777
21 | 16 | Glass façade (Towers and Preliminaries) | Glassline Aluminum LLC | FAÇADE | 15193414.21 | 58250000 | 0 | 58250000 | 4548782.8 | 51.62% | 44.76% | 3.62% | 15193414.21 | 62798782.8 | 7843152.9385 | 6800257.7084 | 550003.5631 |  | 41342303.5181 | 21341747.4731 | 18503959.3007 | 1496596.7443 | 41578355.7099 | 21463602.4701 | 18609611.3757 | 1505141.8642 | 41766543.4977 | 21560748.8771 | 18693840.3342 | 1511954.2865 | 42026892.725 | 66.92% | 12659930.806 | 21695146.5035 | 18810367.2593 | 1521378.9623 | 2533483.404 | 38075057.274 | 60.63% | 10804477.7285 | 6279878.28 | 37980703.818 | 60.48% | 10792007.3162 | 6279878.28 | 38140862.0328 | 60.74% | 10613629.4336 | 6279878.28 | 38235970.4427 | 60.89% | 12948728.6247 | 3823597.0443 | [7 empty] | 1878371.92 | -94353.456 | 160158.2148 | 95108.4099
22 |  | Glass façade (Podium) | Glassline Aluminum LLC | FAÇADE | 375000 | 0 | 0 | 0 | 0 | 51.62% | 44.76% | 3.62% | 375000 | 0 | 193582.7136 | 167842.2378 | 13575.0486 |  | 7896077.5964 | 4076117.6749 | 3534120.8894 | 285839.0321 | 8048683.1226 | 4154895.7865 | 3602423.9641 | 291363.3719 | 8074711.2195 | 4168332.0256 | 3614073.6015 | 292305.5924 | 8111959.269 |  | 0 | 4187560.2349 | 3630745.0575 | 293653.9766 | 375000 | 7639369.5175 |  | 0 | 0 | 7746193.3858 |  | 0 | 0 | 7764413.0537 |  | 0 | 0 | 7790486.6883 |  | 0 | 779048.6688 | [8 empty] | 106823.8684 | 18219.6679 | 26073.6346
23 | 17 | Vertical Transport | Kone Middle East LLC | MEP - LIFT | 1780711.69 | 13988719 | 0 | 13988719 | 440922.04 | 51.62% | 44.76% | 3.62% | 1780711.69 | 14429641.04 | 919240.003 | 797009.6931 | 64461.9939 |  | 13211055.6976 | 6819818.698 | 5912995.0715 | 478241.9281 | 13275588.8268 | 6853132.0267 | 5941878.7644 | 480578.0357 | 13498736.7656 | 6968325.5828 | 6041755.1628 | 488656.02 | 13515270.0989 | 93.66% | 914370.9411 | 6976860.4296 | 6049155.1406 | 489254.5288 | 866340.7489 | 12144661.6744 | 84.16% | 842015.2616 | 1442964.104 | 12121137.7761 | 84% | 865539.1599 | 1442964.104 | 12288498.7302 | 85.16% | 698178.2058 | 1442964.104 | 12261410.1258 | 84.97% | 942089.9016 | 1226141.0126 | [7 empty] | 695153.26 | -23523.8983 | 167360.9541 | -27088.6043
24 | 18 | Glass balustrade | Al Rawaa Glass Mirror Factory LLC | Balustrade | 2943326.04 | 9063400 | 0 | 9063400 | 52953 | 51.62% | 44.76% | 3.62% | 2943326.04 | 9116353 | 1519405.4451 | 1317371.8109 | 106548.784 |  | 7934080.6062 | 4095735.6103 | 3551130.25 | 287214.746 | 7956481.3071 | 4107299.3128 | 3561156.34 | 288025.6543 | 8083920.889 | 4173086.2464 | 3618195.659 | 292638.9837 | 7794226.9624 | 85.5% | 1322126.0376 | 4023540.2826 | 3488534.6539 | 282152.026 | 1621200.0024 | 7976665.6864 | 87.5% | 228052.0136 | 911635.3 | 7660833.1764 | 84.03% | 543884.5236 | 911635.3 | 7675528.8001 | 84.2% | 529188.8999 | 911635.3 | 7156815.9736 | 78.51% | 1243855.429 | 715681.5974 | [7 empty] | 228227 | -315832.51 | 14695.6237 | -518712.8265
25 | 19 | L8 fit out | Alshafar Interiors Co LLC | Rooms Joinery | 0 | 4228272 | 0 | 4228272 | 0 | 0% | 100% | 0% | 0 | 4228272 | 0 | 0 | 0 |  | 4228272 | 0 | 4228272 | 0 | 4228272 | 0 | 4228272 | 0 | 4228272 | 0 | 4228272 | 0 | 4228272 | 100% | 0 | 0 | 4228272 | 0 | 0 | 3805444.8 | 90% | 0 | 422827.2 | 3805444.8 | 90% | 0 | 422827.2 | 3805444.8 | 90% | 0 | 422827.2 | 3805444.8 | 90% | 42282.72 | 380544.48 | [6 empty] | 569000 | 592612.19 | 0 | 0 | 0
26 | 20 | Hotel guest room light fittings | HS Energy Solutions FZCO | FOHMEP | 163792.42 | 1980228 | 0 | 1980228 | 54000 | 100% | 0% | 0% | 163792.42 | 2034228 | 163792.42 | 0 | 0 |  | 1870435.5802 | 1870435.5802 | 0 | 0 | 1870435.5802 | 1870435.5802 | 0 | 0 | 1870435.5802 | 1870435.5802 | 0 | 0 | 1870435.5802 | 91.95% | 163792.4198 | 1870435.5802 | 0 | 0 | 0.00020839 | 1683392.0222 | 82.75% | 147413.1778 | 203422.8 | 1683392.0222 | 82.75% | 147413.1778 | 203422.8 | 1683392.0222 | 82.75% | 147413.1778 | 203422.8 | 1683392.0222 | 82.75% | 182496.7756 | 168339.2022 | [7 empty] | -172067.68 | 0 | 0 | 0
27 | 21 | Medical alarm system (panic alarm & disabled toilet alarm) | SIS | FOHMEP | 42000 | 120000 | 0 | 120000 | 0 | 100% | 0% | 0% | 42000 | 120000 | 42000 | 0 | 0 |  | 78000 | 78000 | 0 | 0 | 78000 | 78000 | 0 | 0 | 78000 | 78000 | 0 | 0 | 78000 | 65% | 42000 | 78000 | 0 | 0 | 0 | 70200 | 58.5% | 37800 | 12000 | 70200 | 58.5% | 37800 | 12000 | 70200 | 58.5% | 37800 | 12000 | 70200 | 58.5% | 42780 | 7020 | [8 empty] | 0 | 0 | 0
28 | 22 | Landscape secondary structure | RPJV | L'SCAPE (Struct) | 3380990.54 | 12000000 | 0 | 12000000 | 0 | 51.62% | 44.76% | 3.62% | 3380990.54 | 12000000 | 1745336.8626 | 1513261.3818 | 122392.2956 |  | 7135159.7115 | 3683316.2109 | 3193549.7945 | 258293.7061 | 8068729.0375 | 4165243.9001 | 3611396.1007 | 292089.0367 | 8291345.398 | 4280163.0446 | 3711034.5757 | 300147.7778 | 8619009.4644 | 71.83% | 3380990.5356 | 4449309.9756 | 3857690.2294 | 312009.2594 | 0.0044017 | 7751369.7836 | 64.59% | 3048630.2164 | 1200000 | 8451546.7781 | 70.43% | 2348453.2219 | 1200000 | 8618509.0485 | 71.82% | 2181490.9515 | 1200000 | 8864257.0983 | 73.87% | 2249317.1919 | 886425.7098 | [8 empty] | 700176.9945 | 166962.2704 | 245748.0498
29 | 23 | ELV specialistic works Hotel Public Areas (2, 4, 28) | RPJV (SIS) | MEP ELV | 699387.38 | 500000 | 0 | 500000 | 0 | 100% | 0% | 0% | 699387.38 | 500000 | 699387.38 | 0 | 0 |  | 100000 | 100000 | 0 | 0 | 100000 | 100000 | 0 | 0 | 100000 | 100000 | 0 | 0 | 100000 | 20% | 400000 | 100000 | 0 | 0 | 299387.38 | 170000 | 34% | 280000 | 50000 | 170000 | 34% | 280000 | 50000 | 170000 | 34% | 280000 | 50000 | 170000 | 34% | 313000 | 17000 | [8 empty] | 0 | 0 | 0
30 | 24 | Lighting control System Hotel&resi Public Areas | RPJV (CREATION GULF) | MEP ELV | 134013.34 | 221365.24 | 0 | 221365.24 | 0 | 51.62% | 44.76% | 3.62% | 134013.34 | 221365.24 | 69180.4427 | 59981.597 | 4851.3003 |  | 87351.9033 | 45092.8493 | 39096.9038 | 3162.1502 | 87351.9033 | 45092.8493 | 39096.9038 | 3162.1502 | 87351.9033 | 45092.8493 | 39096.9038 | 3162.1502 | 87351.9033 | 39.46% | 134013.3367 | 45092.8493 | 39096.9038 | 3162.1502 | 0.00325 | 105419.3823 | 47.62% | 93809.3337 | 22136.524 | 105419.3823 | 47.62% | 93809.3337 | 22136.524 | 105419.3823 | 47.62% | 93809.3337 | 22136.524 | 105419.3823 | 47.62% | 105403.9195 | 10541.9382 | [8 empty] | 0 | 0 | 0
31 | 25 | Balcony Tiles installation | RPJV | Hotel ID | 276665.28 | 577960 | 0 | 577960 | 0 | 51.62% | 44.76% | 3.62% | 276665.28 | 577960 | 142820.3084 | 123829.6526 | 10015.319 |  | 63030.0223 | 32537.394 | 28210.9333 | 2281.695 | 163648.1293 | 84478.5305 | 73245.5153 | 5924.0835 | 248295.5343 | 128175.2622 | 111131.9416 | 8988.3305 | 301294.7246 | 52.13% | 276665.2754 | 155534.5344 | 134853.2822 | 10906.9081 | 0.0046 | 56727.02 | 9.815% | 463436.98 | 57796 | 147283.3164 | 25.48% | 372880.6836 | 57796 | 223465.9809 | 38.66% | 296698.0191 | 57796 | 271165.2521 | 46.92% | 279678.2226 | 27116.5252 | [8 empty] | 90556.2964 | 76182.6645 | 47699.2712
32 | 26 | Supply balcony tiles | RPJV (PORCELLAN) | Hotel ID | 108790.96 | 610000 | 0 | 610000 | 0 | 51.62% | 44.76% | 3.62% | 108790.96 | 610000 | 56160.1313 | 48692.5818 | 3938.2468 |  | 137400 | 70928.7063 | 61497.3959 | 4973.8978 | 215609.04 | 111301.8215 | 96502.1434 | 7805.0752 | 423209.04 | 218469.2117 | 189419.6062 | 15320.2221 | 501209.04 | 82.17% | 108790.96 | 258734.4161 | 224330.7917 | 18143.8322 | 0 | 596260 | 97.75% | -47260 | 61000 | 588439.096 | 96.47% | -39439.096 | 61000 | 567679.096 | 93.06% | -18679.096 | 61000 | 559879.096 | 91.78% | -5867.0056 | 55987.9096 | [8 empty] | -7820.904 | -20760 | -7800
33 | 27 | Fit out Corridors Level 7 to 16 & 19 to 27: wall covering, stones, painting | Existing Guestrooms Subcon (ASI, Al Rawda, Dar al Rokham) | ID - Corridor | 1461242.07 | 2910913 | 0 | 2910913 | 0 | 100% | 0% | 0% | 1461242.07 | 2910913 | 1461242.07 | 0 | 0 |  | 1313063.964 | 1313063.964 | 0 | 0 | 1399551.8388 | 1399551.8388 | 0 | 0 | 1409268.948 | 1409268.948 | 0 | 0 | 1449670.931 | 49.8% | 1461242.069 | 1449670.931 | 0 | 0 | 0.0010079 | 1501327.2548 | 51.58% | 1118494.4452 | 291091.3 | 1561868.7671 | 53.66% | 1057952.9329 | 291091.3 | 1568670.7436 | 53.89% | 1051150.9564 | 291091.3 | 1596952.1317 | 54.86% | 1154265.6551 | 159695.2132 | [8 empty] | 60541.5123 | 6801.9764 | 28281.3881
34 | 28 | Fit out Corridors Level 7 to 16 & 19 to 27: metalworks | RPJV (AHK) | ID - Corridor | 787216.64 | 900000 | 0 | 900000 | 0 | 100% | 0% | 0% | 787216.64 | 900000 | 787216.64 | 0 | 0 |  | 94137.1488 | 94137.1488 | 0 | 0 | 94137.1488 | 94137.1488 | 0 | 0 | 112783.3571 | 112783.3571 | 0 | 0 | 112783.3571 | 12.53% | 787216.6429 | 112783.3571 | 0 | 0 | -0.0028635 | 245896.0041 | 27.32% | 564103.9959 | 90000 | 245896.0041 | 27.32% | 564103.9959 | 90000 | 258948.35 | 28.77% | 551051.65 | 90000 | 258948.35 | 28.77% | 615156.815 | 25894.835 | [8 empty] | 0 | 13052.3459 | 0
35 | 29 | External wall cladding instread of GRC (Terraco) | RPJV (Joyz Overseas) | GRC | 1152066.58 | 1650000 | 0 | 1650000 | 0 | 51.62% | 44.76% | 3.62% | 1152066.58 | 1650000 | 594720.4662 | 515641.1543 | 41704.9595 |  | 342004.2576 | 176549.6327 | 153074.0265 | 12380.5984 | 388133.4804 | 200362.4864 | 173720.5118 | 14050.4823 | 494277.0175 | 255155.9635 | 221228.1619 | 17892.8921 | 497933.4173 | 30.18% | 1152066.5827 | 257043.4723 | 222864.6907 | 18025.2542 | -0.0026962 | 569402.9803 | 34.51% | 915597.0197 | 165000 | 601693.4363 | 36.47% | 883306.5637 | 165000 | 675993.9122 | 40.97% | 809006.0878 | 165000 | 678553.3921 | 41.12% | 903591.2687 | 67855.3392 | [8 empty] | 32290.456 | 74300.4759 | 2559.4799
36 | 30 | Front door ironmongery supply - Guestrooms Hotel | RPJV (Mobility General Trading) | Hotel ID | 105000 | 105000 | 0 | 105000 | 0 | 100% | 0% | 0% | 105000 | 105000 | 105000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 105000 | 0 | 0 | 0 | 0 | 0 | 0% | 94500 | 10500 | 0 | 0% | 94500 | 10500 | 0 | 0% | 94500 | 10500 | 0 | 0% | 105000 | 0 | [8 empty] | 0 | 0 | 0
37 | 31 | ELV Box in Hotel Guest Rooms | RPJV (ASI) | Hotel ID | 46035 | 46035 | 0 | 46035 | 0 | 100% | 0% | 0% | 46035 | 46035 | 46035 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 46035 | 0 | 0 | 0 | 0 | 0 | 0% | 41431.5 | 4603.5 | 0 | 0% | 41431.5 | 4603.5 | 0 | 0% | 41431.5 | 4603.5 | 0 | 0% | 46035 | 0 | [8 empty] | 0 | 0 | 0
38 | 32 | Landscape - Softscape package | RPJV (Fiona Landscape) | L'SCAPE - SOFT | 5701805.95 | 5110819.99 | 0 | 5110819.99 | 0 | 51.62% | 44.76% | 3.62% | 5701805.95 | 5110819.99 | 2943389.5156 | 2552010.3202 | 206406.1142 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9014.04 | 0.1764% | 5101805.95 | 4653.2329 | 4034.4977 | 326.3094 | 600000 | 1022163.798 | 20% | 3577574.193 | 511081.999 | 1022163.798 | 20% | 3577574.193 | 511081.999 | 2363750.278 | 46.25% | 2235987.713 | 511081.999 | 2370060.106 | 46.37% | 2503753.8734 | 237006.0106 | [8 empty] | 0 | 1341586.48 | 6309.828
39 |  | Landscape - Hardscape package | RPJV (Fiona and Al Reem) | L'Scape - HARD | 9937092.91 | 9234342 | 0 | 9234342 | 0 | 51.62% | 44.76% | 3.62% | 9937092.91 | 9234342 | 5129731.7627 | 4447637.0963 | 359724.0509 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125561.6053 | 64817.4834 | 56198.7755 | 4545.3464 | 125561.6053 | 1.36% | 9108780.3947 | 64817.4834 | 56198.7755 | 4545.3464 | 828312.5153 | 1846868.352 | 20% | 6464039.448 | 923434.2 | 1846868.352 | 20% | 6464039.448 | 923434.2 | 1934761.4757 | 20.95% | 6376146.3243 | 923434.2 | 1934761.4757 | 20.95% | 7106104.3767 | 193476.1476 | [8 empty] | 0 | 87893.1237 | 0
40 |  | Landscape - MEP package | RPJV (Watermasters) | L'Scape MEP | 3069103.93 | 4893506 | 0 | 4893506 | 0 | 51.62% | 44.76% | 3.62% | 3069103.93 | 4893506 | 1584334.5791 | 1373667.391 | 111101.9599 |  | 1047230.9395 | 540602.1522 | 468718.8916 | 37909.8957 | 1189121.9701 | 613849.2208 | 532226.3799 | 43046.3694 | 1808370.2961 | 933517.9444 | 809389.1127 | 65463.239 | 1824402.0666 | 37.28% | 3069103.9334 | 941793.8741 | 816564.6013 | 66043.5912 | -0.0034336 | 1711762.8677 | 34.98% | 2692392.5323 | 489350.6 | 1811086.5891 | 37.01% | 2593068.8109 | 489350.6 | 2244560.4173 | 45.87% | 2159594.9827 | 489350.6 | 2255782.6566 | 46.1% | 2412145.0777 | 225578.2657 | [8 empty] | 99323.7215 | 433473.8282 | 11222.2393
41 |  | Landscape - Swimming pool and water features package | RPJV (IKK/ Watermaters/ Reem &Mosaic ?) | L'Scape Pool/WF | 2534770.41 | 3414995.97 | 0 | 3414995.97 | 0 | 51.62% | 44.76% | 3.62% | 2534770.41 | 3414995.97 | 1308500.625 | 1134510.7677 | 91759.0173 |  | 787533.4741 | 406540.9786 | 352483.6817 | 28508.8138 | 820985.56 | 423809.6335 | 367456.1429 | 29719.7837 | 845135.556 | 436276.3582 | 378265.1812 | 30594.0166 | 880225.556 | 25.78% | 2534770.414 | 454390.5379 | 393970.7389 | 31864.2792 | -0.004 | 1234272.8218 | 36.14% | 1839223.5512 | 341499.597 | 1257689.282 | 36.83% | 1815807.091 | 341499.597 | 1274594.2792 | 37.32% | 1798902.0938 | 341499.597 | 1299157.2792 | 38.04% | 1985922.9629 | 129915.7279 | [7 empty] | 307710.48 | 23416.4602 | 16904.9972 | 24563
42 | 33 | GRC claddiing to Stair Plaza&retail | RPJV (Arabian Profile Co Limited) | GRC | 347256.25 | 581910.664 | 0 | 581910.664 | 0 | 51.62% | 44.76% | 3.62% | 347256.25 | 581910.664 | 179260.8192 | 155424.7096 | 12570.7212 |  | 124510.5073 | 64274.885 | 55728.3258 | 4507.2965 | 215498.9549 | 111244.9933 | 96452.8716 | 7801.0901 | 215498.9549 | 111244.9933 | 96452.8716 | 7801.0901 | 234654.4176 | 40.32% | 347256.2464 | 121133.4371 | 105026.4601 | 8494.5203 | 0.0035519 | 200426.7924 | 34.44% | 323292.8052 | 58191.0664 | 261843.9946 | 45% | 261875.6031 | 58191.0664 | 261843.9946 | 45% | 261875.6031 | 58191.0664 | 274773.9319 | 47.22% | 279659.339 | 27477.3932 | [8 empty] | 61417.2021 | 0 | 12929.9373
43 |  | GRC Fluted Entrances (Hotel Podium) | RPJV (Arabian Profile Co Limited) | GRC | 344871.02 | 363022.1242 | 0 | 363022.1242 | 0 | 100% | 0% | 0% | 344871.02 | 363022.1242 | 344871.02 | 0 | 0 |  | 18151.1 | 18151.1 | 0 | 0 | 18151.1 | 18151.1 | 0 | 0 | 18151.1 | 18151.1 | 0 | 0 | 18151.1 | 5% | 344871.0242 | 18151.1 | 0 | 0 | -0.0042279 | 84856.3925 | 23.37% | 241863.5193 | 36302.2124 | 84856.3925 | 23.37% | 241863.5193 | 36302.2124 | 84856.3925 | 23.37% | 241863.5193 | 36302.2124 | 84856.3925 | 23.37% | 269680.0925 | 8485.6393 | [8 empty] | 0 | 0 | 0
39 |  | GRP Cladding to underside of Pool view deck at L29 | RPJV (EIFS? Joyz Overseas) | GRC | 0 | 74015.3487 | 0 | 74015.3487 | 0 | 100% | 0% | 0% | 0 | 74015.3487 | 0 | 0 | 0 |  | 74015.3487 | 74015.3487 | 0 | 0 | 74015.3487 | 74015.3487 | 0 | 0 | 74015.3487 | 74015.3487 | 0 | 0 | 74015.3487 | 100% | 0 | 74015.3487 | 0 | 0 | 0 | 66613.8138 | 90% | 0 | 7401.5349 | 66613.8138 | 90% | 0 | 7401.5349 | 66613.8138 | 90% | 0 | 7401.5349 | 66613.8138 | 90% | 740.1535 | 6661.3814 | [8 empty] | 0 | 0 | 0
40 |  | EIFS Cladding at back side and GRC Cladding at front side at Hotel Rooftop Pool Area - Level 29 | RPJV (EIFS & GRCS: Joyz Overseas and APL) | GRC | 631489.41 | 485306.76 | 0 | 485306.76 | 0 | 100% | 0% | 0% | 631489.41 | 485306.76 | 631489.41 | 0 | 0 |  | 24265.35 | 24265.35 | 0 | 0 | 24265.35 | 24265.35 | 0 | 0 | 24265.35 | 24265.35 | 0 | 0 | 24265.35 | 5% | 461041.41 | 24265.35 | 0 | 0 | 170448 | 113440.5112 | 23.38% | 323335.5727 | 48530.676 | 113440.5112 | 23.38% | 323335.5727 | 48530.676 | 113440.5112 | 23.38% | 323335.5727 | 48530.676 | 113440.5112 | 23.38% | 360522.1976 | 11344.0511 | [8 empty] | 0 | 0 | 0
41 |  | GRC Wall Cladding at Hotel Levels 8,11,14,16,21,23,25&27 | RPJV (Arabian Profile Co Limited) | GRC | 50582.83 | 95745.1031 | 0 | 95745.1031 | 0 | 100% | 0% | 0% | 50582.83 | 95745.1031 | 50582.83 | 0 | 0 |  | 40850.4312 | 40850.4312 | 0 | 0 | 45162.2776 | 45162.2776 | 0 | 0 | 45162.2776 | 45162.2776 | 0 | 0 | 45162.2776 | 47.17% | 50582.8255 | 45162.2776 | 0 | 0 | 0.0044893 | 46723.041 | 48.8% | 39447.5518 | 9574.5103 | 49633.5374 | 51.84% | 36537.0554 | 9574.5103 | 49633.5374 | 51.84% | 36537.0554 | 9574.5103 | 49633.5374 | 51.84% | 41148.212 | 4963.3537 | [8 empty] | 2910.4964 | 0 | 0
42 | 34 | Timber Ceiling and flooring, skirting to match timber flooring | RPJV | Hotel ID | 850000 | 850000 | 0 | 850000 | 0 | 100% | 0% | 0% | 850000 | 850000 | 850000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 850000 | 0 | 0 | 0 | 0 | 170000 | 20% | 595000 | 85000 | 170000 | 20% | 595000 | 85000 | 170000 | 20% | 595000 | 85000 | 170000 | 20% | 663000 | 17000 | [8 empty] | 0 | 0 | 0
43 |  | Painted Timber Skirting Hotel Rooms | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | [8 empty] | 0 | 0 | 0
39 | 35 | Hotel Guestrooms media hub | RPJV | MEP ELV | 103965 | 103965 | 0 | 103965 | 0 | 100% | 0% | 0% | 103965 | 103965 | 103965 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 103965 | 0 | 0 | 0 | 0 | 30000 | 28.86% | 63568.5 | 10396.5 | 30000 | 28.86% | 63568.5 | 10396.5 | 30000 | 28.86% | 63568.5 | 10396.5 | 30000 | 28.86% | 70965 | 3000 | [8 empty] | 0 | 0 | 0
40 | 36 | Fire Hose Cabinet Doors to Hotel Corridors | RPJV (ASI) | ID - Corridor | 85856.82 | 85856.82 | 0 | 85856.82 | 0 | 100% | 0% | 0% | 85856.82 | 85856.82 | 85856.82 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 85856.82 | 0 | 0 | 0 | 0 | 17171.364 | 20% | 60099.774 | 8585.682 | 17171.364 | 20% | 60099.774 | 8585.682 | 17171.364 | 20% | 60099.774 | 8585.682 | 17171.364 | 20% | 66968.3196 | 1717.1364 | [8 empty] | 0 | 0 | 0
41 |  | Light fittings Supply for Hotel Corridors | RPJV (Project & Supplies) | MEP Lights | 70025 | 498657 | 0 | 498657 | 0 | 100% | 0% | 0% | 70025 | 498657 | 70025 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 428632 | 85.96% | 70025 | 428632 | 0 | 0 | 0 | 249328.5 | 50% | 199462.8 | 49865.7 | 249328.5 | 50% | 199462.8 | 49865.7 | 249328.5 | 50% | 199462.8 | 49865.7 | 635097.3 | 127.4% | -199950.03 | 63509.73 | [8 empty] | 0 | 0 | 385768.8
42 | 37 | Light fittings Supply for Hotel Public Areas (LV2,4, 28) excluding L4 | RPJV (Project & Supplies) | MEP Lights | 703598.2 | 779967 | 0 | 779967 | 0 | 100% | 0% | 0% | 703598.2 | 779967 | 703598.2 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76368.8 | 9.791% | 703598.2 | 76368.8 | 0 | 0 | 0 | 389983.25 | 50% | 311987.05 | 77996.7 | 389983.25 | 50% | 311987.05 | 77996.7 | 389983.25 | 50% | 311987.05 | 77996.7 | 458715.17 | 58.81% | 275380.313 | 45871.517 | [8 empty] | 0 | 0 | 68731.92
43 | 38 | Light fittings Supply for Residential Public Areas (GF, LV2, LV4, LV23) | RPJV (Project & Supplies) | MEP Lights | 222912.8 | 394865.2 | 0 | 394865.2 | 0 | 51.62% | 44.76% | 3.62% | 222912.8 | 394865.2 | 115072.1726 | 99771.1552 | 8069.4722 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171952.402 | 43.55% | 222912.798 | 88765.3669 | 76962.3359 | 6224.6992 | 0.002 | 197432.6 | 50% | 157946.08 | 39486.52 | 197432.6 | 50% | 157946.08 | 39486.52 | 197432.6 | 50% | 157946.08 | 39486.52 | 352189.7618 | 89.19% | 7456.462 | 35218.9762 | [8 empty] | 0 | 0 | 154757.1618
44 | 39 | Light fittings Supply for Balconies and Tower Façade | RPJV (Project & Supplies) | MEP Lights | 5544 | 644724 | 0 | 644724 | 0 | 51.62% | 44.76% | 3.62% | 5544 | 644724 | 2861.9268 | 2481.3796 | 200.6935 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 639180 | 99.14% | 5544 | 329957.8637 | 286083.7375 | 23138.3988 | 0 | 322362 | 50% | 257889.6 | 64472.4 | 322362 | 50% | 257889.6 | 64472.4 | 322362 | 50% | 257889.6 | 64472.4 | 897624 | 139.2% | -342662.4 | 89762.4 | [8 empty] | 0 | 0 | 575262
45 | 40 | Hotel Ground Floor Light fittings (ballroom&meeting rooms) | RPJV (Project & Supplies) | MEP Lights | 531707.1 | 588000 | 0 | 588000 | 0 | 100% | 0% | 0% | 531707.1 | 588000 | 531707.1 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56292.9 | 9.574% | 531707.1 | 56292.9 | 0 | 0 | 0 | 294000 | 50% | 235200 | 58800 | 294000 | 50% | 235200 | 58800 | 294000 | 50% | 235200 | 58800 | 344663.61 | 58.62% | 208870.029 | 34466.361 | [8 empty] | 0 | 0 | 50663.61
46 | 41 | Electrical FOH at Level-07 to 11 Hotel | RPJV (Future Metro) | MEP Electrical | 0 | 2008965.2212 | 0 | 2008965.2212 | 0 | 100% | 0% | 0% | 0 | 2008965.2212 | 0 | 0 | 0 |  | 1990433.5789 | 1990433.5789 | 0 | 0 | 2000527.5672 | 2000527.5672 | 0 | 0 | 2001386.1702 | 2001386.1702 | 0 | 0 | 2001386.1702 | 99.62% | 7579.0509 | 2001386.1702 | 0 | 0 | -7579.0509 | 1791390.221 | 89.17% | 16678.478 | 200896.5221 | 1800474.8105 | 89.62% | 7593.8885 | 200896.5221 | 1801247.5532 | 89.66% | 6821.1458 | 200896.5221 | 1801247.5532 | 89.66% | 27592.9126 | 180124.7553 | [8 empty] | 9084.5895 | 772.7427 | 0
47 | 42 | Electrical FOH at Level-8 Residential | RPJV (Future Metro) | MEP Electrical | 0 | 497164.17 | 0 | 497164.17 | 0 | 0% | 100% | 0% | 0 | 497164.17 | 0 | 0 | 0 |  | 497164.1717 | 0 | 497164.1717 | 0 | 497164.1717 | 0 | 497164.1717 | 0 | 497164.1717 | 0 | 497164.1717 | 0 | 497164.1717 | 100% | -0.0017358 | 0 | 497164.1717 | 0 | 0.0017358 | 447447.7546 | 90% | -0.0015622 | 49716.417 | 447447.7546 | 90% | -0.0015622 | 49716.417 | 447447.7546 | 90% | -0.0015622 | 49716.417 | 447447.7546 | 90% | 4971.64 | 44744.7755 | [8 empty] | 0 | 0 | 0
48 | 43 | Electrical FOH at Level-12 to 16 Hotel | RPJV (Future Metro) | MEP Electrical | 0 | 3876246.9258 | 0 | 3876246.9258 | 0 | 100% | 0% | 0% | 0 | 3876246.9258 | 0 | 0 | 0 |  | 3800719.9921 | 3800719.9921 | 0 | 0 | 3835383.5307 | 3835383.5307 | 0 | 0 | 3839265.3596 | 3839265.3596 | 0 | 0 | 3839265.3596 | 99.05% | 36981.5662 | 3839265.3596 | 0 | 0 | -36981.5662 | 3420647.9929 | 88.25% | 67974.2403 | 387624.6926 | 3451845.1777 | 89.05% | 36777.0556 | 387624.6926 | 3455338.8236 | 89.14% | 33283.4096 | 387624.6926 | 3455338.8236 | 89.14% | 75374.2198 | 345533.8824 | [8 empty] | 31197.1847 | 3493.646 | 0
49 | 44 | External facade lighting provisions (balcony and void areas) | RPJV (Project & Supplies) | MEP Electrical | 0 | 353378.6051 | 0 | 353378.6051 | 0 | 51.62% | 44.76% | 3.62% | 0 | 353378.6051 | 0 | 0 | 0 |  | 233676.3344 | 120628.5305 | 104588.6904 | 8459.1136 | 237563.0384 | 122634.927 | 106328.2986 | 8599.8128 | 249817.3084 | 128960.8332 | 111813.0562 | 9043.4189 | 271584.7478 | 76.85% | 81793.8572 | 140197.6332 | 121555.7115 | 9831.4031 | -81793.8572 | 210308.701 | 59.51% | 107732.0436 | 35337.8605 | 213806.7346 | 60.5% | 104234.01 | 35337.8605 | 224835.5775 | 63.62% | 93205.167 | 35337.8605 | 244426.2731 | 69.17% | 84509.7047 | 24442.6273 | [8 empty] | 3498.0336 | 11028.8429 | 19590.6955
50 | 45 | Electrical Works Hotel Corridors MEP/ELV | RPJV | MEP Electrical | 0 | 300000 | 0 | 300000 | 0 | 100% | 0% | 0% | 0 | 300000 | 0 | 0 | 0 |  | 197130 | 197130 | 0 | 0 | 197130 | 197130 | 0 | 0 | 197130 | 197130 | 0 | 0 | 197130 | 65.71% | 102870 | 197130 | 0 | 0 | -102870 | 197991 | 66% | 72009 | 30000 | 197991 | 66% | 72009 | 30000 | 197991 | 66% | 72009 | 30000 | 197991 | 66% | 82209.9 | 19799.1 | [8 empty] | 0 | 0 | 0
51 | 46 | Light fittings for Hotel Public areas (Level 4) | RPJV (Project & Supplies) | MEP Lights | 206182.96 | 236349 | 0 | 236349 | 0 | 100% | 0% | 0% | 206182.96 | 236349 | 206182.96 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30166.04 | 12.76% | 206182.96 | 30166.04 | 0 | 0 | 0 | 118174.55 | 50% | 94539.55 | 23634.9 | 118174.55 | 50% | 94539.55 | 23634.9 | 118174.55 | 50% | 94539.55 | 23634.9 | 145323.986 | 61.49% | 76492.6154 | 14532.3986 | [8 empty] | 0 | 0 | 27149.436
52 | 47,48 | Light fittings Supply for Podium Façade - landscape | RPJV (Project & Supplies) | MEP Lights | 2567922.12 | 2528753 | 0 | 2528753 | 0 | 51.62% | 44.76% | 3.62% | 2567922.12 | 2528753 | 1325614.2196 | 1149348.7869 | 92959.1135 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2528753 | 0 | 0 | 0 | 39169.12 | 1264376.5 | 50% | 1011501.2 | 252875.3 | 1264376.5 | 50% | 1011501.2 | 252875.3 | 1264376.5 | 50% | 1011501.2 | 252875.3 | 1264376.5 | 50% | 1137938.85 | 126437.65 | [8 empty] | 0 | 0 | 0
53 | 49 | Void area lighting Control Cable | RPJV | MEP Electrical | 0 | 21500 | 0 | 21500 | 0 | 51.62% | 44.76% | 3.62% | 0 | 21500 | 0 | 0 | 0 |  | 16608.75 | 8573.7784 | 7433.7327 | 601.2389 | 16608.75 | 8573.7784 | 7433.7327 | 601.2389 | 16608.75 | 8573.7784 | 7433.7327 | 601.2389 | 16608.75 | 77.25% | 4891.25 | 8573.7784 | 7433.7327 | 601.2389 | -4891.25 | 14947.875 | 69.53% | 4402.125 | 2150 | 14947.875 | 69.53% | 4402.125 | 2150 | 14947.875 | 69.53% | 4402.125 | 2150 | 14947.875 | 69.53% | 5057.3375 | 1494.7875 | [8 empty] | 0 | 0 | 0
54 | 50 | Balance Joinery,ironmongery in Hotel Corridors | Momentum Fireguard LLC | ID - Corridor | 597488 | 620000 | 0 | 620000 | 0 | 100% | 0% | 0% | 597488 | 620000 | 597488 | 0 | 0 |  | 22512 | 22512 | 0 | 0 | 22512 | 22512 | 0 | 0 | 22512 | 22512 | 0 | 0 | 22512 | 3.631% | 597488 | 22512 | 0 | 0 | 0 | 138587.2 | 22.35% | 419412.8 | 62000 | 138587.2 | 22.35% | 419412.8 | 62000 | 138587.2 | 22.35% | 419412.8 | 62000 | 138587.2 | 22.35% | 467554.08 | 13858.72 | [8 empty] | 0 | 0 | 0
55 | 51 | Sanitaryware for hotel guestrooms 7A and 15A | RPJV | MEP Sanitary | 60370.99 | 216996.19 | 0 | 216996.19 | 0 | 100% | 0% | 0% | 60370.99 | 216996.19 | 60370.99 | 0 | 0 |  | 0 | 0 | 0 | 0 | 156625.2 | 156625.2 | 0 | 0 | 156625.2 | 156625.2 | 0 | 0 | 156625.2 | 72.18% | 60370.99 | 156625.2 | 0 | 0 | 0 | 43399.238 | 20% | 151897.333 | 21699.619 | 153036.878 | 70.53% | 42259.693 | 21699.619 | 153036.878 | 70.53% | 42259.693 | 21699.619 | 153036.878 | 70.53% | 48655.6242 | 15303.6878 | [8 empty] | 109637.64 | 0 | 0
56 | 52 | Ommission Provisional Sum Sanipex (9 rooms 7A,15A,Royal and Presidential Suites | 0 | Hotel ID | -43301.4 | -222939 | 0 | -222939 | 0 | 100% | 0% | 0% | -43301.4 | -222939 | -43301.4 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -179637.5959 | 80.58% | -43301.4041 | -179637.5959 | 0 | 0 | 0.0040951 | 0 | 0% | -200645.1 | -22293.9 | 0 | 0% | -200645.1 | -22293.9 | 0 | 0% | -200645.1 | -22293.9 | -161673.8363 | 72.52% | -45097.7801 | -16167.3836 | [8 empty] | 0 | 0 | -161673.8363
57 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | [8 empty] | 0 | 0 | 0
58 |  | Provisional Sums to be Awarded | [11 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | [15 empty] | 0
59 | 53 | Signages and wayfinding | Joseph Advertising LLC | ID- Signage | 2000000 | 2000000 | 0 | 2000000 | 0 | 51.62% | 44.76% | 3.62% | 2000000 | 2000000 | 1032441.1393 | 895158.6015 | 72400.2591 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2000000 | 0 | 0 | 0 | 0 | 400000 | 20% | 1400000 | 200000 | 400000 | 20% | 1400000 | 200000 | 400000 | 20% | 1400000 | 200000 | 400000 | 20% | 1560000 | 40000 | [8 empty] | 0 | 0 | 0
60 | 54 | Sanitaryware to hotel guestrooms Royal and presidential suites | RPJV (AHK) | MEP Sanitary | 75000 | 75000 | 0 | 75000 | 0 | 100% | 0% | 0% | 75000 | 75000 | 75000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 75000 | 0 | 0 | 0 | 0 | 0 | 0% | 67500 | 7500 | 0 | 0% | 67500 | 7500 | 0 | 0% | 67500 | 7500 | 0 | 0% | 75000 | 0 | [8 empty] | 0 | 0 | 0
61 | 55 | Additional Fit-out items in guestroom suites (ie. Balustrades) | RPJV (Al Raada) | Hotel ID | 200000 | 200000 | 0 | 200000 | 0 | 100% | 0% | 0% | 200000 | 200000 | 200000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 200000 | 0 | 0 | 0 | 0 | 40000 | 20% | 140000 | 20000 | 40000 | 20% | 140000 | 20000 | 40000 | 20% | 140000 | 20000 | 40000 | 20% | 156000 | 4000 | [8 empty] | 0 | 0 | 0
62 |  | Descoped packages to be rescoped and Instructed | [11 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | [15 empty] | 0
63 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  |  | 0 | 0
64 | 56 | Fitout residence public area | AHK | ID - RESI | 2154888.82 | 4000000 | 0 | 4000000 | 0 | 0% | 100% | 0% | 2154888.82 | 4000000 | 0 | 2154888.82 | 0 |  | 1997171.7333 | 0 | 1997171.7333 | 0 | 2203550.4 | 0 | 2203550.4 | 0 | 2350230.4 | 0 | 2350230.4 | 0 | 2387388.8 | 59.68% | 1612611.2 | 0 | 2387388.8 | 0 | 542277.62 | 2097878.8 | 52.45% | 1502121.2 | 400000 | 2252662.8 | 56.32% | 1347337.2 | 400000 | 2362672.8 | 59.07% | 1237327.2 | 400000 | 2390541.6 | 59.76% | 1370404.24 | 239054.16 | [8 empty] | 154784 | 110010 | 27868.8
65 | 57 | ELV specialistic works Resi Public Areas (G,2, 4, 23) | RPJV | MEP ELV | 282673.26 | 371516 | 0 | 371516 | 0 | 0% | 100% | 0% | 282673.26 | 371516 | 0 | 282673.26 | 0 |  | 59851.2276 | 0 | 59851.2276 | 0 | 65126.7548 | 0 | 65126.7548 | 0 | 88842.7412 | 0 | 88842.7412 | 0 | 88842.7412 | 23.91% | 282673.2588 | 0 | 88842.7412 | 0 | 0.0012 | 53866.1048 | 14.5% | 280498.2952 | 37151.6 | 58614.0793 | 15.78% | 275750.3207 | 37151.6 | 79958.4671 | 21.52% | 254405.9329 | 37151.6 | 79958.4671 | 21.52% | 283561.6862 | 7995.8467 | [8 empty] | 4747.9745 | 21344.3878 | 0
66 | 58 | Electrical works resi FOH public areas (GF,2,4,23) | RPJV -Silicon Vega | MEP Electrical | 0 | 322543 | 0 | 322543 | 0 | 0% | 100% | 0% | 0 | 322543 | 0 | 0 | 0 |  | 286321.4211 | 0 | 286321.4211 | 0 | 286321.4211 | 0 | 286321.4211 | 0 | 286321.4211 | 0 | 286321.4211 | 0 | 286321.4211 | 88.77% | 36221.5789 | 0 | 286321.4211 | 0 | -36221.5789 | 264933.5948 | 82.14% | 25355.1052 | 32254.3 | 264933.5948 | 82.14% | 25355.1052 | 32254.3 | 264933.5948 | 82.14% | 25355.1052 | 32254.3 | 264933.5948 | 82.14% | 31116.0458 | 26493.3595 | [8 empty] | 0 | 0 | 0
67 |  | Extra packages required for completion of the project | [11 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | [15 empty] | 0
68 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  |  |  | 0
69 | 59 | Headboards | AHK | Hotel ID | 712815 | 712815 | 0 | 712815 | 0 | 100% | 0% | 0% | 712815 | 712815 | 712815 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 712815 | 0 | 0 | 0 | 0 | 169959.2 | 23.84% | 471574.3 | 71281.5 | 169959.2 | 23.84% | 471574.3 | 71281.5 | 169959.2 | 23.84% | 471574.3 | 71281.5 | 169959.2 | 23.84% | 525859.88 | 16995.92 | [8 empty] | 0 | 0 | 0
70 | 60 | Hotel Kitchen equipment works (Hoods and Cold Rooms only) | TSSC | Kitchens | 2765518.9 | 1735122 | 487988 | 2223110 | 0 | 100% | 0% | 0% | 2765518.9 | 2223110 | 2765518.9 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2223110 | 0 | 0 | 0 | 542408.9 | 670398 | 30.16% | 1330401 | 222311 | 670398 | 30.16% | 1330401 | 222311 | 670398 | 30.16% | 1330401 | 222311 | 670398 | 30.16% | 1485672.2 | 67039.8 | [7 empty] | 670398 | 0 | 0 | 0
71 | 61 | Kitchens and BOH Areas - GF,L2, L28 (Fitout) | RPJV | Hotel ID | 580000 | 580000 | 0 | 580000 | 0 | 100% | 0% | 0% | 580000 | 580000 | 580000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 580000 | 0 | 0 | 0 | 0 | 116000 | 20% | 406000 | 58000 | 116000 | 20% | 406000 | 58000 | 116000 | 20% | 406000 | 58000 | 116000 | 20% | 452400 | 11600 | [8 empty] | 0 | 0 | 0
72 | 62 | 2 No. Penthouse lifts and 2 No. Retail Lobby Lifts (Coring only by RPJV, Lifts by OM) | RPJV | Hotel ID | 300000 | 300000 | 0 | 300000 | 0 | 100% | 0% | 0% | 300000 | 300000 | 300000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 300000 | 0 | 0 | 0 | 0 | 60000 | 20% | 210000 | 30000 | 60000 | 20% | 210000 | 30000 | 60000 | 20% | 210000 | 30000 | 60000 | 20% | 234000 | 6000 | [8 empty] | 0 | 0 | 0
73 | 63 | Carpet and Wallpaper for Hotel | Goodrich and CSI | Hotel ID | 2000000 | 2000000 | 0 | 2000000 | 0 | 100% | 0% | 0% | 2000000 | 2000000 | 2000000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 2000000 | 0 | 0 | 0 | 0 | 1188454.595 | 59.42% | 611545.405 | 200000 | 1188454.595 | 59.42% | 611545.405 | 200000 | 1188454.595 | 59.42% | 611545.405 | 200000 | 1188454.595 | 59.42% | 692699.9455 | 118845.4595 | [7 empty] | 365800.73 | 0 | 0 | 0
74 |  | Descoped Packages to be Rescoped | [11 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | [15 empty] | 0
75 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  |  |  | 0
76 | 64 | Turn Key Fitout -Ball Room L0 | AHK (Rattan House/DAR) | ID Ballroom | 4742695.19 | 5000000 | 0 | 5000000 | 0 | 100% | 0% | 0% | 4742695.19 | 5000000 | 4742695.19 | 0 | 0 |  | 95000 | 95000 | 0 | 0 | 95000 | 95000 | 0 | 0 | 125000 | 125000 | 0 | 0 | 257304.8121 | 5.146% | 4742695.1879 | 257304.8121 | 0 | 0 | 0.0020979 | 1385387.8 | 27.71% | 3114612.2 | 500000 | 1385387.8 | 27.71% | 3114612.2 | 500000 | 1373112.9603 | 27.46% | 3126887.0397 | 500000 | 1434539.7432 | 28.69% | 3422006.2825 | 143453.9743 | [8 empty] | 0 | -12274.8397 | 61426.7829
77 | 64 | MEP and ELV - Ball room L0+Additional lift | AHK (Golden Oasis/SIS/Kone) | ID Ballroom | 1272131.87 | 1000000 | 594439 | 1594439 | 0 | 100% | 0% | 0% | 1272131.87 | 1594439 | 1272131.87 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 166374.1985 | 166374.1985 | 0 | 0 | 322307.1262 | 20.21% | 1272131.8738 | 322307.1262 | 0 | 0 | -0.0037753 | 0 | 0% | 1434995.1 | 159443.9 | 0 | 0% | 1434995.1 | 159443.9 | 149736.7786 | 9.391% | 1285258.3214 | 159443.9 | 290076.4136 | 18.19% | 1275354.945 | 29007.6414 | [7 empty] | 460008 | 0 | 149736.7786 | 140339.635
78 | 64 | Royalsuits fitout works | AHK (Decolab/SIS/gldn oasis/DAR) | ID Various | 3764536.47 | 1718372.7909 | 0 | 1718372.7909 | 0 | 100% | 0% | 0% | 3764536.47 | 1718372.7909 | 3764536.47 | 0 | 0 |  | 17269.4876 | 17269.4876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53836.3215 | 3.133% | 1664536.4694 | 53836.3215 | 0 | 0 | 2100000.0006 | 395761.0413 | 23.03% | 1150774.4705 | 171837.2791 | 343674.5582 | 20% | 1202860.9536 | 171837.2791 | 343674.5582 | 20% | 1202860.9536 | 171837.2791 | 381359.9833 | 22.19% | 1298876.8093 | 38135.9983 | [8 empty] | -52086.4831 | 0 | 37685.4251
79 | 64 | Presidential suites fitout works | AHK (Decolab/SIS/gldn oasis/DAR) | ID Various | 1765759.69 | 1829208.4191 | 0 | 1829208.4191 | 0 | 100% | 0% | 0% | 1765759.69 | 1829208.4191 | 1765759.69 | 0 | 0 |  | 6951.0591 | 6951.0591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63448.7251 | 3.469% | 1765759.694 | 63448.7251 | 0 | 0 | -0.0040014 | 413285.1413 | 22.59% | 1233002.4358 | 182920.8419 | 365841.6838 | 20% | 1280445.8934 | 182920.8419 | 365841.6838 | 20% | 1280445.8934 | 182920.8419 | 410255.7914 | 22.43% | 1377927.0486 | 41025.5791 | [8 empty] | -47443.4575 | 0 | 44414.1076
80 | 64 | Royal and Presidential Suites MEP Works | AHK (Golden Oasis) | ID Various | 264151.41 | 412877.79 | 0 | 412877.79 | 0 | 100% | 0% | 0% | 264151.41 | 412877.79 | 264151.41 | 0 | 0 |  | 0 | 0 | 0 | 0 | 106216.9403 | 106216.9403 | 0 | 0 | 106216.9403 | 106216.9403 | 0 | 0 | 148726.3781 | 36.02% | 264151.4119 | 148726.3781 | 0 | 0 | -0.001896 |  | 0% | 371590.011 | 41287.779 | 156927.4162 | 38.01% | 214662.5948 | 41287.779 | 156927.4162 | 38.01% | 214662.5948 | 41287.779 | 186684.0227 | 45.22% | 207525.3651 | 18668.4023 | [8 empty] | 156927.4162 | 0 | 29756.6065
81 | 64 | LV 28 Gym fitout works | AHK (Decolab/SIS/gldn oasis/DAR) | ID Various | 383761.33 | 413000 | 1466 | 414466 | 0 | 100% | 0% | 0% | 383761.33 | 414466 | 383761.33 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30704.6687 | 7.408% | 383761.3313 | 30704.6687 | 0 | 0 | -0.0012952 | 82600 | 19.93% | 290419.4 | 41446.6 | 82600 | 19.93% | 290419.4 | 41446.6 | 82600 | 19.93% | 290419.4 | 41446.6 | 110234.2018 | 26.6% | 293208.378 | 11023.4202 | [8 empty] | 0 | 0 | 27634.2018
82 | 64 | LV 28 Gym MEP (electrical, ELV and lighting) | AHK (Golden Oasis/SIS) | ID Various | 112750.71 | 150000 | 0 | 150000 | 0 | 100% | 0% | 0% | 112750.71 | 150000 | 112750.71 | 0 | 0 |  | 0 | 0 | 0 | 0 | 28575.5842 | 28575.5842 | 0 | 0 | 30033.0342 | 30033.0342 | 0 | 0 | 37249.2942 | 24.83% | 112750.7058 | 37249.2942 | 0 | 0 | 0.004234 | 30000 | 20% | 105000 | 15000 | 50002.909 | 33.34% | 84997.091 | 15000 | 51023.124 | 34.02% | 83976.876 | 15000 | 56074.506 | 37.38% | 88318.0434 | 5607.4506 | [8 empty] | 20002.909 | 1020.215 | 5051.382
83 | 64 | Turn Key Fitout - GF and Level 1 Ablution | AHK (Decolab/SIS/gldn oasis/DAR) | ID Various | 751307.43 | 358982.5595 | 392324.8705 | 751307.43 | 0 | 100% | 0% | 0% | 751307.43 | 751307.43 | 751307.43 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 751307.43 | 0 | 0 | 0 | 0 | 365380.776 | 48.63% | 310795.911 | 75130.743 | 150261.486 | 20% | 525915.201 | 75130.743 | 150261.486 | 20% | 525915.201 | 75130.743 | 150261.486 | 20% | 586019.7954 | 15026.1486 | [8 empty] | -215119.29 | 0 | 0
84 | 64 | Turn Key Fitout - Rooftop LV 29 (amenties) | AHK (Decolab/SIS/gldn oasis/DAR) | ID Various | 1075596.45 | 513931.25 | 561665.2 | 1075596.45 | 0 | 100% | 0% | 0% | 1075596.45 | 1075596.45 | 1075596.45 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 1075596.45 | 0 | 0 | 0 | 0 | 0 | 0% | 968036.805 | 107559.645 | 215119.29 | 20% | 752917.515 | 107559.645 | 215119.29 | 20% | 752917.515 | 107559.645 | 215119.29 | 20% | 838965.231 | 21511.929 | [8 empty] | 215119.29 | 0 | 0
85 | 64 | MEP Works - GF,Level 1 Ablution room and Roof Top L29 | AHK (Golden Oasis) | ID Various | 208994.14 | 127086.1904 | 138889.9596 | 265976.15 | 0 | 100% | 0% | 0% | 208994.14 | 265976.15 | 208994.14 | 0 | 0 |  | 0 | 0 | 0 | 0 | 52404.5981 | 52404.5981 | 0 | 0 | 54272.6245 | 54272.6245 | 0 | 0 | 56982.0064 | 21.42% | 208994.1436 | 56982.0064 | 0 | 0 | -0.0036427 | 0 | 0% | 239378.535 | 26597.615 | 47164.1383 | 17.73% | 192214.3967 | 26597.615 | 48845.362 | 18.36% | 190533.173 | 26597.615 | 51283.8057 | 19.28% | 209563.9637 | 5128.3806 | [8 empty] | 47164.1383 | 1681.2238 | 2438.4437
86 | 64 | Turnkey fitout - Signature resturant LV 17 | 0 | 0 | 0 | Excluded | 0 | 0 | 0 | 0% | 100% | 0% | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | [8 empty] | 0 | 0 | 0
87 | 64 | Electrical Works Hotel FOH Public area - LV17, LV29 including ELV | 0 | 0 | 0 | Excluded | 0 | 0 | 0 | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | [8 empty] | 0 | 0 | 0
88 | 64 | Lighting fitting supply (L29, L17 | 0 | 0 | 0 | Excluded | 0 | 0 | 0 | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | [8 empty] | 0 | 0 | 0
89 | 64 | Carpet - Guest rooms Hotel | 0 | 0 | 0 | Excluded | 0 | 0 | 0 | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | [8 empty] | 0 | 0 | 0
90 | 64 | Decorative Wall Covering - Guest room Hotels | 0 | 0 | 0 | Excluded | 0 | 0 | 0 | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | [8 empty] | 0 | 0 | 0
91 | 65 | Light fittings (Inc. point wiring, switches and sockets) - Residence Corridor | 0 | 0 | 0 | Excluded | 0 | 0 | 0 | 0% | 100% | 0% | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | [8 empty] | 0 | 0 | 0
92 | 66 | Psum Steel Cabana Level 29 (e/over) |  |  | 423000 |  |  |  |  | 100% | 0% | 0% | 423000 | 0 | 423000 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 423000
|  | Total |  |  | 102712363.84 | 254685032.722 | 2176773.03 | 256861805.752 | 5529988.8226 |  |  |  | 102712363.84 | 262391794.5747 | 73562532.5758 | 27151012.0812 | 1998819.183 |  | 157829596.8383 | 101720660.6965 | 52439371.3043 | 3669564.8374 | 162406612.9171 | 105022490.8434 | 53634975.542 | 3749146.5317 | 166909017.3021 | 108086461.1627 | 54978525.1627 | 3844030.9767 | 170879624.9435 |  | 91512169.6312 | 111223197.9762 | 55752779.7868 | 3903647.1806 | 11200194.2088 | 165087283.2976 |  | 71065331.8196 | 26239179.4575 | 167472128.3021 |  | 68680486.8152 | 26239179.4575 | 171643352.5816 |  | 64509262.5356 | 26239179.4575 | 173760212.6254 |  | 72034609.3556 | 17376021.2625 | 0 | 0 | 0 | 0 | 0 | 0 | 2174000 | 5539020.36 | 2384845.0044 | 4171224.2796 | 2116860.0438
|  | Less: MOS | [16 empty] | -3987117.9423 |  |  |  | -3644944.8235 |  |  |  | -2652058.5277 |  |  |  | -1493173.9032 |  | 1493173.9032
|  | Less: Variations | [16 empty] | -4107086.9265 |  |  |  | -4412593.5376 |  |  |  | -4443751.5991 |  |  |  | -4443751.5991 |  | -1086237.2235
|  | The Amounts to be checked with the Summary | [16 empty] | 149735391.9695 |  |  |  | 154349074.556 |  |  |  | 159813207.1753 |  |  |  | 164942699.4412 |  | 91919106.3109 | [30 empty] | 16385949.6878
|  |  |  | KEY: | [7 empty] | reconcile with Contract Sum | [10 empty] | NOTE: Reconciled to MATCH with MOS & VARIATIONS ADDED - refer to Contract Sum Sheet for Reconciliation
|  |  | MEP | MEP Electrical |  | 9986424.922 | 0 | 9986424.922 | 0 | 0% |  | 0% |  | 9986424.922 |  |  |  | 0 | 9221811.3007 |  |  |  | 9270455.5317 |  |  |  | 9508452.3534 |  |  |  | 9530219.7929 | 7.9715 | 456205.1291
|  |  |  | MEP - ELV |  | 5251961.24 | 0 | 5251961.24 | 407202.3 | 0% |  | 9789653% |  | 5659163.54 |  |  |  | 0 | 3960945.4614 |  |  |  | 3970785.5925 |  |  |  | 3993499.2789 |  |  |  | 3993499.2789 | 2.4909 | 1665664.2611
|  |  |  | MEP Sanitary |  | 4635198.25 | 0 | 4635198.25 | -299491 | 13500000% |  | -29525003% |  | 4335707.25 |  |  |  | 0 | 3388873.173 |  |  |  | 3547406.0975 |  |  |  | 3548564.159 |  |  |  | 3548564.159 | #VALUE! | 787143.091
|  |  |  | MEP Lights |  | 6183623.2 | 0 | 6183623.2 | 0 | 0% |  | 0% |  | 6183623.2 |  |  |  | 0 | 512308 |  |  |  | 512308 |  |  |  | 512308 |  |  |  | 1914900.142 | 3.6077 | 4268723.058
|  |  |  | MEP - LIFT |  | 13988719 | 0 | 13988719 | 440922.04 | 0% |  | 69515326% |  | 14429641.04 |  |  |  | 0 | 13211055.6976 |  |  |  | 13275588.8268 |  |  |  | 13498736.7656 |  |  |  | 13515270.0989 | 0.93663 | 914370.9411
|  |  |  | FOHMEP |  | 2100228 | 0 | 2100228 | 54000 | 0% |  | -17206768% |  | 2154228 |  |  |  | 0 | 1948435.5802 |  |  |  | 1948435.5802 |  |  |  | 1948435.5802 |  |  |  | 1948435.5802 | 1.5695 | 205792.4198
|  |  |  | Kitchens |  | 1735122 | 487988 | 2223110 | 0 | 0% |  | 67039800% |  | 2223110 |  |  |  | 0 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 2223110
|  |  | Façade | FAÇADE |  | 58250000 | 0 | 58250000 | 4548782.8 | 0% |  | 187837192% |  | 62798782.8 |  |  |  | 0 | 49238381.1145 |  |  |  | 49627038.8325 |  |  |  | 49841254.7173 |  |  |  | 50138851.994 | #VALUE! | 12659930.806
|  |  |  | GRC |  | 21550000 | 0 | 21550000 | 159321.67 | 0% |  | 9088866% |  | 21709321.67 |  |  |  | 0 | 16674918.2965 |  |  |  | 17096638.2579 |  |  |  | 17688463.7487 |  |  |  | 17867870.2246 | 3.1962 | 3841451.4454
|  |  |  | Balustrade |  | 9063400 | 0 | 9063400 | 52953 | 0% |  | 22822700% |  | 9116353 |  |  |  | 0 | 7934080.6062 |  |  |  | 7956481.3071 |  |  |  | 8083920.889 |  |  |  | 7794226.9624 | 0.85497 | 1322126.0376
|  |  |  | BMU |  | 2111400 | 0 | 2111400 | -360607 | 0% |  | 3479688% |  | 1750793 |  |  |  | 0 | 816514.6305 |  |  |  | 816514.6305 |  |  |  | 921931.9305 |  |  |  | 921931.9305 | 0.52658 | 828861.0695
|  |  |  | Façade Ceiling |  | 3480715 | 0 | 3480715 | 0 | 0% |  | -30778835% |  | 3480715 |  |  |  | 0 | 2555487.0413 |  |  |  | 2560516.9721 |  |  |  | 2602165.9584 |  |  |  | 2673735.9605 | 0.76816 | 806979.0395
|  |  | Fit-Out | Hotel ID |  | 32641333.33 | 0 | 32641333.33 | -16663.37 | 147000000% |  | 62077061% |  | 32624669.96 |  |  |  | 0 | 21676686.0134 |  |  |  | 22190196.8897 |  |  |  | 22735543.72 |  |  |  | 23225027.2244 | 6.0576 | 9399642.7356
|  |  |  | ID - Corridor |  | 4516769.82 | 0 | 4516769.82 | 0 | 0% |  | 0% |  | 4516769.82 |  |  |  | 0 | 1429713.1128 |  |  |  | 1516200.9875 |  |  |  | 1544564.3051 |  |  |  | 1584966.2881 | 0.65964 | 2931803.5319
|  |  |  | Rooms Joinery |  | 15666124 | 0 | 15666124 | 543568.3826 | 56900000% |  | 122690877% |  | 16209692.3826 |  |  |  | 0 | 9346442.1309 |  |  |  | 9648441.6399 |  |  |  | 9923999.9627 |  |  |  | 10037571.1909 | 1.4849 | 6172121.1917
|  |  |  | ID - Pareas |  | 11346891 | 0 | 11346891 | 0 | 0% |  | 299631% |  | 11346891 |  |  |  | 0 | 4827628.2741 |  |  |  | 5905019.6809 |  |  |  | 6654635.8805 |  |  |  | 7368393.2515 | 1.3305 | 3978497.7485
|  |  |  | ID Ballroom |  | 6000000 | 594439 | 6594439 | 0 | 0% |  | 46000800% |  | 6594439 |  |  |  | 0 | 95000 |  |  |  | 95000 |  |  |  | 291374.1985 |  |  |  | 579611.9383 | 0.25361 | 6014827.0617
|  |  |  | ID Various |  | 5523459 | 1094346.03 | 6617805.03 | 0 | 0% |  | 0% |  | 6617805.03 |  |  |  | 0 | 24220.5466 |  |  |  | 187197.1226 |  |  |  | 190522.599 |  |  |  | 390947.394 | 0.96288 | 6226857.636
|  |  |  | ID - RESI |  | 4000000 | 0 | 4000000 | 0 | 0% |  | 0% |  | 4000000 |  |  |  | 0 | 1997171.7333 |  |  |  | 2203550.4 |  |  |  | 2350230.4 |  |  |  | 2387388.8 | 0.59685 | 1612611.2
|  |  |  | ID- Signage |  | 2000000 | 0 | 2000000 | 0 | 0% |  | 0% |  | 2000000 |  |  |  | 0 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 2000000
|  |  | External | L'SCAPE (Struct) |  | 12000000 | 0 | 12000000 | 0 | 0% |  | 0% |  | 12000000 |  |  |  | 0 | 7135159.7115 |  |  |  | 8068729.0375 |  |  |  | 8291345.398 |  |  |  | 8619009.4644 | 0.71825 | 3380990.5356
|  |  |  | L'SCAPE - SOFT |  | 5110819.99 | 0 | 5110819.99 | 0 | 0% |  | 0% |  | 5110819.99 |  |  |  | 0 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 9014.04 | 0.0017637 | 5101805.95
|  |  |  | L'Scape - HARD |  | 9234342 | 0 | 9234342 | 0 | 0% |  | 0% |  | 9234342 |  |  |  | 0 | 0 |  |  |  | 0 |  |  |  | 125561.6053 |  |  |  | 125561.6053 | 0.013597 | 9108780.3947
|  |  |  | L'Scape MEP |  | 4893506 | 0 | 4893506 | 0 | 0% |  | 0% |  | 4893506 |  |  |  | 0 | 1047230.9395 |  |  |  | 1189121.9701 |  |  |  | 1808370.2961 |  |  |  | 1824402.0666 | 0.37282 | 3069103.9334
|  |  |  | L'Scape Pool/WF |  | 3414995.97 | 0 | 3414995.97 | 0 | 0% |  | 30771048% |  | 3414995.97 |  |  |  | 0 | 787533.4741 |  |  |  | 820985.56 |  |  |  | 845135.556 |  |  |  | 880225.556 | 0.25775 | 2534770.414
[6 empty] | 254685032.722 | 2176773.03 | 256861805.752 | 5529988.8226 | 217400000% |  | 553902036% |  | 262391794.5747 |  |  |  | 0 | 157829596.8383 |  |  |  | 162406612.9171 |  |  |  | 166909017.3021 |  |  |  | 170879624.9435 | #VALUE! | 91512169.6312
|  |  |  | check |  | 0 | 0 | 0 | 0 | 0% |  | 0% |  | 0 |  |  |  | 0 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 0

## Cost to Complete- Contract
Plot 18 | [7 empty] | 3000000 |  | -2129492.2659
Cost to Complete as of 4th February 2022 - AS PER CONTRACT | [5 empty] | DL |  | DL | 5129492.2659 |  | ESTIMATED VALUE OF WORK REMAINING TO COMPLETE
Ref. | Contract Bill Breakdown | Contract Amount | Contract Amount- With Awarded Provisional sums | Paid Amount in the PC-47 (Nov) | Certified Amount in the PC-48 (Dec) | Var 47-48 | Estimated value of Works completed in January 2022 (PC 49) | Var 48-49 | Remaining Amount-Based on Paid(PC-47- Nov) Amount | Remaining Amount-Based on Certified (PC-48 - Dec) Amount | Remaining Amount-Based on Estimated value of Works completed in Jan 2022 (PC49)
1 | Preliminaries | 69999375 | 69999375 | 63022928.4021 | 63411911.6108 | 388983.2087 | 63705272.6331 | 293361.0224 | 6976446.5979 | 6587463.3892 | 6294102.3669
2 | Design Fee | 17133642.5 | 17133642.5 | 16714931.5227 | 16742681.5227 | 27750 | 16742681.5227 | 0 | 418710.9773 | 390960.9773 | 390960.9773
3 | Base Build works -Structure | 146698856.68 | 146698856.68 | 146698856.68 | 146698856.68 | 0 | 146698856.68 | 0 | 0 | 0 | 0
4 | Other Base build Works (Civil/Finishes) | 35034040.53 | 35034040.53 | 28393526.1823 | 28484582.391 | 91056.2088 | 28661071.9709 | 176489.5799 | 6640514.3477 | 6549458.139 | 6372968.5591
5 | Provisional Sum | 254685030.3425 | 256861805.75 | 154349074.556 | 159813207.1753 | 5464132.6193 | 164942699.4412 | 5129492.2659 | 102512731.194 | 97048598.5747 | 91919106.3088
6 | Attendance Fee, OH&P on PS | 13343972 | 13343972 | 9114071.0174 | 9441459.0083 | 327387.9909 | 9128947.7589 | -312511.2494 | 4229900.9826 | 3902512.9917 | 4215024.2411
7 | MEP Works | 116046969.42 | 116046969.42 | 98313488.8273 | 99552006.2721 | 1238517.4448 | 100476553.9053 | 924547.6332 | 17733480.5927 | 16494963.1479 | 15570415.5147
8 | PS and PC Rate agreements | 30430613.47 | 30430613.47 | 30430613.47 | 30430613.47 | 0 | 30430613.47 | 0 | 0 | 0 | 0
9 | Variations | 39378912.6923 | 39378912.6923 | 36587076.9811 | 36701271.8437 | 114194.8626 | 36734451.6608 | 33179.8171 | 2791835.7111 | 2677640.8486 | 2644461.0315
10 | EOT Costs Awarded to October 2020 | 5000000 | 5000000 | 5000000 | 5000000 | 0 | 5000000 | 0 |  | 0 | 0
11 | Authority Payments Agreed | 14248588 | 14248588 | 14248588 | 14248588 | 0 | 14248588 | 0 |  | 0 | 0
12 |  | 742000000.6348 | 744176776.0423 | 602873155.6389 | 610525177.9739 | 7652022.335 | 616769737.0429 | 6244559.069 | 141303620.4034 | 133651598.0683 | 127407038.9994
13 | Material on site-Annexure 5 |  |  | 11808683.3552 | 10639399.0867 | -1169284.2686 | 6882912.8603 | -3756486.2264 | -11808683.3552 | -10639399.0867 | -6882912.8603
14 | Post Addendum 2 VOs |  | 931101.6741 | 342895.3104 | 428998.8804 | 86103.57 | 90890.8804 | -338108 | 588206.3636 | 502102.7936 | 840210.7936
15 | Total | 742000000.6348 | 745107877.7163 | 615024734.3046 | 621593575.941 | 6568841.6365 | 623743540.7836 | 2149964.8426 | 130083143.4118 | 123514301.7753 | 121364336.9327
|  | check | 3107877.0815 |  | check | 621593575.941 | check | 623743540.7836 | AGAINST BUDGET |  | AGAINST FINAL ACOUNT
| 100% works lumped together on Summary Page |  | 2176775.4075 | [5 empty] | 616769737.0391
|  |  | 931101.6741 | [5 empty] | -0.0037771
|  | variance from add 2 | 3107877.0815
|  | Presented Figure less EOT & Auth Payments | 725859289.7163 | NO
| CHECK MAIN CONTRATOR WORKS |  | 488246071.9663
| Psum Package Works |  | 256861805.75
|  | CHECK | 745107877.7163
[7 empty] | 32334451.6608 |  |  | 1544461.0315
33878912.6923

## SOA Nov 21
Plot-18
Sub-Contractor's Payments
Payments for the Works executed September (IPC-45) &October (IPC-46) & November (IPC-47) 2021
[5 empty] | 2021-09-01 | [6 empty] | 2022-10-01 | [5 empty] | 2022-11-01
| Ref. No | Sub-Contractor |  |  | PC-45 Month Payment (Sept) |  |  |  | PC-45 Cumulative Payment (Sept) |  |  | PC-46 Month Payment (Oct) |  |  | PC-46 Cumulative Payment (Oct) |  |  | PC-47 Month Payment (Nov) |  |  | PC-47 Cumulative Payment (Nov)
Item No |  |  | Payment made to Sub-Contractors in PC No.44 | Cumulative Payment made to Sub-Contractor up to PC No.44 | Amount Paid by OME in PC No.45 | Amount Paid by RPJV (In Sep 21) -Refer to the RPJV Payment Summary | Variance | Note | Cumulative OME Payment up to PC No.45 | Cumulative RPJV Payments (up to Sep 21) | Variance | Amount Paid by OME in PC No.46 | Amount Paid by RPJV (In Oct 21) -Refer to the RPJV Payment Summary | Variance | Cumulative OME Payment up to PC No.46 | Cumulative RPJV Payments (up to Oct 21) | Variance | Amount Paid by OME in PC No.47 | Amount Paid by RPJV (In Nov 21) -Refer to the RPJV Payment Summary | Variance | Cumulative OME Payment up to PC No.47 | Cumulative RPJV Payments (up to Nov 21) | Variance
| 1 | AHK Worldwide Interiors LLC | 506750.148 | 4029962.022 | 436744.112 | 984010.78 | 547266.668 | 458k PDC Jan-22 | 4466706.134 | 4024948.59 | -441757.544 | 414783.0739 | 396532.57 | -18250.5039 | 4881489.2079 | 4421481.16 | -460008.0479 | 135784 | 161954.9 | 26170.9 | 5017273.2079 | 4583436.06 | -433837.1479
| 2 | Al Rawaa Glass Mirror Factory LLC | 201044.0817 | 7068746.4817 | 29722.0478 | No information Submitted | -29722.0478 |  | 7098468.5294 | 6895445.42 | -203023.1094 | 42204.0162 | 17000 | -25204.0162 | 7140672.5456 | 6912445.42 | -228227.1256 | 20160.6308 | 12600 | -7560.6308 | 7160833.1764 | 6925045.42 | -235787.7564
| 3 | Al Rawda General Maintenance and Decoration Co LLC | 437612.8598 | 10624760.6175 | 338650.9747 | 1788348.1885 | 1449697.2138 | 810k PDCFeb-22 | 10963411.5922 | 11200875.54 | 237463.9478 | 110023.2561 | 174347.66 | 64324.4039 | 11073434.8484 | 11375223.2 | 301788.3516 | 13344.3398 | 168000 | 154655.6602 | 11086779.1882 | 11543223.2 | 456444.0118
| 4 | Al Reem Marble & Granite LLC |  |  | 0 | 0 | 0 |  |  | RPJV's Domestic Sub-Contractor |  | 0 |  | 0 |  |  | 0 | 0 |  | 0 |  | 0 | 0
| 5 | Alshafar Interiors Co LLC (L8) |  | 3805444.8 | 0 | 569719 | 569719 | 569k PDC Mar-22 | 3805444.8 | 3212832.61 | -592612.19 | 0 |  | 0 | 3805444.8 | 3212832.61 | -592612.19 | 0 |  | 0 | 3805444.8 | 3212832.61 | -592612.19
| 6 | Alshafar Interiors Co LLC |  | 5865303.4135 | 504749.7265 | 991824.72 | 487074.9935 |  | 6370053.14 | 5477362.3 | -892690.84 | -58938.5892 | 199455.67 | 258394.2592 | 6311114.5508 | 5676817.97 | -634296.5808 | 226629.7789 | 237961.27 | 11331.4911 | 6537744.3297 | 5914779.24 | -622965.0897
| 7 | Arabian Profile Co Limited | 462657.2263 | 13854993.9578 | 754722.005 | 2337351.65 | 1582629.645 | 1.57m PDC Jan-22 | 14609715.9628 | 15124118.54 | 514402.5772 | 1229800.195 | 624508.96 | -605291.235 | 15839516.1578 | 15748627.5 | -90888.6578 | 303572.7511 | 399016.21 | 95443.4589 | 16143088.9089 | 16147643.71 | 4554.8011
| 8 | Arcadia Metal Industries LLC |  |  | 0 | 0 | 0 |  |  | RPJV's Domestic Sub-Contractor |  | 0 |  | 0 |  |  | 0 | 0 |  | 0 |  | 0 | 0
| 9 | Bond Interior Design LLC | 469357.6629 | 5165795.4988 | 348273.0546 | 908174.6 | 559901.5454 |  | 5514068.5535 | 5490233.73 | -23834.8235 | 786575.711 | 807414.22 | 20838.509 | 6300644.2645 | 6297647.95 | -2996.3145 | 646434.8441 | 632652 | -13782.8441 | 6947079.1085 | 6930299.95 | -16779.1585
| 10 | Creation Gulf Trading LLC |  | 3064781.2277 | 0 | 103654.42 | 103654.42 |  | 3064781.2277 | 2966884.7 | -97896.5277 | 0 |  | 0 | 3064781.2277 | 2966884.7 | -97896.5277 | 6749.9962 |  | -6749.9962 | 3071531.2239 | 2966884.7 | -104646.5239
| 11 | Dar Al Rokham LLC | 916290.4168 | 9740239.7996 | 593544.2593 | 1791112.1 | 1197567.8407 | 660k PDC Feb-22 | 10333784.0589 | 10268297.44 | -65486.6189 | 446021.3771 | 335116.06 | -110905.3171 | 10779805.436 | 10603413.5 | -176391.936 | 153181.6968 | 235692.54 | 82510.8432 | 10932987.1327 | 10839106.04 | -93881.0927
| 12 | E W Cox Middle East LLC |  | 848263.2136 | 0 | No information Submitted |  |  | 848263.2136 | 813466.33 | -34796.8836 | 0 |  | 0 | 848263.2136 | 813466.33 | -34796.8836 | 0 |  | 0 | 848263.2136 | 813466.33 | -34796.8836
| 13 | Fiona Environs UAE |  |  | 0 | 0 | 0 |  |  | RPJV's Domestic Sub-Contractor |  | 0 | 349920 | 349920 |  |  | 0 | 0 |  | 0 |  | 0 | 0
| 14 | Glassline Aluminum LLC | 121236.9049 | 46486453.2339 | -989748.9295 | No information Submitted | 989748.9295 |  | 45496704.3044 | 43533507.38 | -1963196.9244 | -84825 |  | 84825 | 45411879.3044 | 43533507.38 | -1878371.9244 | 315017.8965 | 270900 | -44117.8965 | 45726897.2009 | 43804407.38 | -1922489.8209
| 15 | Goodrich Global Trading LLC |  | 395141.2 | 0 | No information Submitted |  |  | 395141.2 | 148177.95 | -246963.25 | 0 |  | 0 | 395141.2 | 148177.95 | -246963.25 | 0 |  | 0 | 395141.2 | 148177.95 | -246963.25
| 15B | CSI Luxury Floorings |  | 118837.475 | 0 | No information Submitted |  |  | 118837.475 | 0 | -118837.475 | 0 |  | 0 | 118837.475 | 0 | -118837.475 | 0 |  | 0 | 118837.475 | 0 | -118837.475
| 16 | HS Energy Solutions FZCO |  | 1683392.0222 | 0 | 397687.22 | 397687.22 |  | 1683392.0222 | 1855459.7 | 172067.6778 | 0 |  | 0 | 1683392.0222 | 1855459.7 | 172067.6778 | 0 |  | 0 | 1683392.0222 | 1855459.7 | 172067.6778
| 17 | Isam Kabbani and Partners for Constructions and Maintenance Co. LLC |  |  | 0 | 0 | 0 |  |  | RPJV's Domestic Sub-Contractor |  | 0 |  | 0 |  |  | 0 | 0 | 206255.83 | 206255.83 |  |  | 0
| 18 | Joseph Decorative Glass |  | 726983.724 | 0 | 62521.84 | 62521.84 |  | 726983.724 | 739293.99 | 12310.266 | 103742.378 | 96004.15 | -7738.228 | 830726.102 | 835298.14 | 4572.038 | 62063.4819 | 65166.65 | 3103.1681 | 892789.5839 | 900464.79 | 7675.2061
| 19 | Kone Middle East LLC | 116595.9214 | 11807598.836 | 147597.8431 | No information Submitted | -147597.8431 |  | 11955196.6791 | 11298098.35 | -657098.3291 | 117541.2501 | 79486.32 | -38054.9301 | 12072737.9292 | 11377584.67 | -695153.2592 | 48399.8469 | 50820.17 | 2420.3231 | 12121137.7761 | 11428404.84 | -692732.9361
| 20 | Momentum Fireguard LLC |  | 835549.9701 | 55781.245 | 163320.33 | 107539.085 |  | 891331.2151 | 965337.12 | 74005.9049 | 0 |  | 0 | 891331.2151 | 965337.12 | 74005.9049 | 0 |  | 0 | 891331.2151 | 965337.12 | 74005.9049
| 21 | Projects & Supplies |  |  | 0 | 0 | 0 |  |  | RPJV's Domestic Sub-Contractor |  | 0 | 1256998.17 | 1256998.17 |  |  | 0 | 0 | 1214301.66 | 1214301.66 |  |  | 0
| 22 | Sanipex LLC |  | 2945660.985 | 1459.044 | 135502.5 | 134043.456 | 135k PDC Mar-22 | 2947120.029 | 3242370.06 | 295250.031 | 0 |  | 0 | 2947120.029 | 3242370.06 | 295250.031 | 15482.781 |  | -15482.781 | 2962602.81 | 3242370.06 | 279767.25
| 23 | TSSC Kitchen |  | 670398 | 0 | No information Submitted |  |  | 670398 | No information Submitted | -670398 | 0 |  | 0 | 670398 |  | -670398 | 0 |  | 0 | 670398 | 0 | -670398
| 24 | Walltracts LLC |  | 499240.5 | 0 | No information Submitted |  |  | 499240.5 | 305217.3 | -194023.2 | 0 |  | 0 | 499240.5 | 305217.3 | -194023.2 | 0 |  | 0 | 499240.5 | 305217.3 | -194023.2
| 24B | Watts of Westminster |  | 175235.42 | 0 | No information Submitted |  |  | 175235.42 | No information Submitted | -175235.42 | 0 |  | 0 | 175235.42 |  | -175235.42 | 0 |  | 0 | 175235.42 | 0 | -175235.42
| 25 | Water Master | 516295.5126 | 1343890.4829 | 199797.3656 | No information Submitted | -199797.3656 |  | 1543687.8485 | 1262495.59 | -281192.2585 | 26518.2206 |  | -26518.2206 | 1570206.0691 | 1262495.59 | -307710.4791 | -16688.0527 |  | 16688.0527 | 1553518.0165 | 1262495.59 | -291022.4265
| Total |  | 754128.3389 | 131756672.8811 | 2421292.7482 | 10233227.3485 | 7811934.6003 |  | 134177965.6293 | 128824422.64 | -5353542.9893 | 3133445.8888 | 4336783.78 | 1203337.8912 | 137311411.5181 | 131554288.25 | -5757123.2681 | 1930133.9914 | 3655321.23 | 1725187.2386 | 139241545.5095 | 133789051.99 | -5452493.5195
[6 empty] | 4220384.77 | PDC's to be paid up to Mar-22 |  |  | ASI | -1485303.03 | Domestic Subs | 1606918.17 |  |  | ASI | -1226908.7708 | Domestic Subs | 1420557.49 |  |  | ASI | -1215577.2797
[10 empty] | Glassline | -1963196.9244 |  |  |  |  | Glassline | -1878371.9244 |  |  |  |  | Glassline | -1922489.8209
[7 empty] | PDC feb-Mar | 2174000 |  | AHK | -441757.544 | Total w/o Domestic | 2729865.61 | -403580.2788 |  | AHK TSSC | -670398 | Total w/o Domestic | 2234763.74 | 304629.7486 |  | AHK | -433837.1479
[10 empty] | TSSC | -670398 |  |  |  |  | Kone | -695153.2592 |  |  |  |  | TSSC | -670398
[22 empty] | Kone | -692732.9361

## Annex 9 - IPC 49
Plot-18 | Plot-18 |  |  |  | Annexure 9 - Provisional Sum Packages as per the Addendum 2
Progress of Provisional Sums -Addendum 2 Break Down | Progress of Provisional Sums -Addendum 2 Break Down
Payment Certificate No. 49
Payment Certificate No. 41 | Item No | SCOPE OF WORKS | SUPPLIER/SUBCONTRACTOR | CATOGERY | ADDENDUM 2 INSTRUCTED AMOUNT | AWARDED AFTER ADDENDUM 2 | REVISED CONTRACT AMOUNT | VARIATIONS ADDENDUM 2 | FINAL ESTIMATED PACKAGE SUM | WORKDONE |  |  | MOS | VARIATIONS | ADVANCES |  |  |  |  | Retention | Net Paid | Categeory | Advance Payment Reference (Annexure -8)
Item No | [9 empty] | Previous | Current | Cumulative | Cumulative | Cumulative | Advance Paid | Additional Advances | Recovery Percentage | Recovery of Advance | Advance Remaining
[10 empty] | Amount | Amount | Amount to Date | Amount to Date | Amount to Date | [5 empty] | 10%
1 | 1 | Electrical works Hotel Public areas | BOND INTERIORS | FOHMEP | 751671 |  | 751671 | 0 | 751671 | 483592.6 | -7736.44 | 475856.16 | 37943.25 |  | 225501.3 |  | 30% | 142756.848 | 82744.452 | 51379.941 | 545163.921 | H | AP - 38
2 | 2 | Fit out Hotel Public areas | BOND INTERIORS | ID | 10595220 |  | 10595220 | 0 | 10595220 | 6171043.2805 | 683550.561 | 6854593.8415 |  |  | 3178566 |  | 30% | 2056378.1525 | 1122187.8475 | 685459.3842 | 7291322.3049 | AA | AP - 19
3 | 3 | Electrical works Hotel 19-27 | SILICON VEGA | FOHMEP | 2090511 |  | 2090511 | 0 | 2090511 | 1912976.9824 | 0 | 1912976.9824 |  |  | 313577 |  | 15% | 286946.5474 | 26630.4526 | 191297.6982 | 1748309.7368 | C | AP - 20
4 | 4 | Supply Wiring accessories Hotel | SMKA | FOHMEP | 516116 |  | 516116 | 0 | 516116 | 507782.19 | 0 | 507782.19 |  |  | 516115.85 |  | 100% | 507782.19 | 8333.66 | 50778.219 | 465337.631 | C | AP - 22
5 | 5 | ELV hotel 19 & 27 | SIS | FOHMEP | 371106 |  | 371106 | 0 | 371106 | 305494.4592 | 0 | 305494.4592 |  |  | 55666 |  | 15% | 45824.1689 | 9841.8311 | 30549.4459 | 284786.8444 | E | AP - 21
6 | 6 | Void Column light fittings | Bayt Al Tawreed Trading LLC | FOHMEP | 512308 |  | 512308 | 0 | 512308 | 512308 | 0 | 512308 |  |  | 0 |  |  | 0 | 0 | 51230.8 | 461077.2 | D
7 | 7 | BMU | E W Cox Middle East LLC | BMU | 2111400 |  | 2111400 | -360607 | 1750793 | 887336.9305 | 0 | 887336.9305 |  | 34595 | 211140 |  | 12.5% | 115241.4913 | 95898.5087 | 92193.1931 | 925637.2461 | N | AP - 12
8 | 8 | Hotel Ceiling and partition | Al Rawda General Maintenance and Decoration Co LLC | ID | 8101444.13 |  | 8101444.13 | 0 | 8101444.13 | 8054107.1494 | 0 | 8054107.1494 |  |  | 0 |  |  | 0 | 0 | 805410.7149 | 7248696.4345 | P
9 | 9 | Sanitary ware | Sanipex LLC | FOHMEP | 4023939.06 |  | 4023939.06 | -299491 | 3724448.06 | 3242370.06 | 0 | 3242370.06 |  | 50568.899 | 0 |  |  | 0 | 0 | 329293.8959 | 2963645.0631 | B
10 | 10a | Hotel guestroom Sanitary ware descope from Sanipex in lieu of Al Futtaim | Al Futtaim Engineering LLC | FOHMEP | 220263 |  | 220263 | 0 | 220263 |  | 0 | 0 |  |  | 220263 |  |  | 0 | 220263 | 0 | 220263 | B | AP - 18
| 10b | Hotel guestroom Sanitary ware descope from sanipex (Already in PS VO-154) | Bette GmbH & Co. KG | FOHMEP | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 78608 |  |  | 0 | 78608 | 0 | 78608 | B | AP - 23
|  |  | Taps&More | FOHMEP | 99000 |  | 99000 | 0 | 99000 | 99000 | 0 | 99000 |  |  | 0 |  |  | 0 | 0 | 9900 | 89100 | B
11 | 11 | Hotel guestroom Sanitary ware descope from sanipex | Taps&More | FOHMEP | 0 |  | 0 | 0 | 0 |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | B
12 | 12 | Access control system Hotel Gust room | Creation Gulf Trading LLC | FOHMEP | 3684009 |  | 3684009 | 407202.3 | 4091211.3 | 3031938.741 | 0 | 3031938.741 |  | 379871.4342 | 368400 |  | 12.5% | 368400 | 0 | 341181.0175 | 3070629.1577 | A | AP - 11
|  | Stone works | Dar Al Rokham LLC | ID | 14192643.2 |  | 14192643.2 | -76663.37 | 14115979.83 | 11093379.8267 | 406624.4499 | 11500004.2766 |  | 1900.63 | 2128896 |  | 17.5% | 2012833.3587 | 116062.6413 | 1150190.4907 | 10467777.0573 | Q | AP - 7
|  | Ironmongery supply | Momentum Fireguard LLC | ID | 1177018 |  | 1177018 | 60000 | 1237018 | 928555.1162 | 32535.48 | 961090.5962 |  | 60000 | 117701 |  | 12.5% | 117701 | 0 | 102109.0596 | 918981.5366 | Y | AP - 14
13 | 13 | Joinery works | Alshafar Interiors Co LLC | ID | 11437852 |  | 11437852 | 543568.3826 | 11981420.3826 | 5157499.7801 | 113571.2282 | 5271071.0083 |  | 538228.1826 | 1715677 |  | 17.5% | 1016627.3584 | 699049.6416 | 580929.9191 | 5927418.9134 | R | AP - 13
14 | 14 | Internal Glazing | Joseph Decorative Glass | ID | 2072163 |  | 2072163 | 0 | 2072163 | 820658.8241 | 79223.4859 | 899882.31 |  |  | 310824 |  | 17.5% | 157479.4042 | 153344.5958 | 89988.231 | 963238.6747 | X | AP - 16
|  | External Ceiling | Al Rawda General Maintenance and Decoration Co LLC | FAÇADE | 3480715 |  | 3480715 | 0 | 3480715 | 2602165.9584 | 71570.0021 | 2673735.9605 | [6 empty] | 0 | 267373.596 | 2406362.3644 | O
|  | Internal & external painting | Al Rawda General Maintenance and Decoration Co LLC | ID & Façade | 1339194 |  | 1339194 | 0 | 1339194 | 1105437.5992 | 19738.4943 | 1125176.0935 | [6 empty] | 0 | 112517.6094 | 1012658.4842 | S
15 | 15 | GRC claddiing -Edge Profile | Arabian Profile Co Limited | GRC | 18300000 |  | 18300000 | 159321.67 | 18459321.67 | 16215188.2101 | 252219.7876 | 16467407.9976 | 316280.3158 | 190000 | 1830000 | 600000 | 10% | 2265740.7998 | 164259.2002 | 1697368.8313 | 15440578.6823 | U | AP - 5, AP - 9
16 | 16 | Glass façade (Towers and Preliminaries) | Glassline Aluminum LLC | FAÇADE | 58250000 |  | 58250000 | 4548782.8 | 62798782.8 | 39155831.0845 | 136157.4298 | 39291988.5143 | 124191.7975 | 2610712.4133 | 2912500 |  | 5% | 2500733.0098 | 411766.9902 | 4202689.2725 | 38235970.4427 | M | AP - 2, AP - 3
|  | Glass façade (Podium) | Glassline Aluminum LLC | FAÇADE | 0 |  | 0 | 0 | 0 | 8074711.2195 | 37248.0495 | 8111959.269 |  |  | 2112115.2 |  | 20% | 1622391.8538 | 489723.3462 | 811195.9269 | 7790486.6883 | K | AP - 34
17 | 17 | Vertical Transport | Kone Middle East LLC | LIFT | 13988719 |  | 13988719 | 440922.04 | 14429641.04 | 12880150.0478 | 16533.3333 | 12896683.3812 | 177664.6777 | 440922.04 | 2098307.85 |  | 15% | 2000640.8132 | 97667.0368 | 1351527.0099 | 12261410.1258 | K | AP - 4
18 | 18 | Glass balustrade | Al Rawaa Glass Mirror Factory LLC | Balustrade | 9063400 |  | 9063400 | 52953 | 9116353 | 5938479.529 | 935700.5712 | 6874180.1002 | 837093.8622 | 82953 | 1359510 | 500000 | 17.5% | 1717498.2925 | 142011.7075 | 779422.6962 | 7156815.9736 | J | AP - 8
19 | 19 | L8 fit out | Alshafar Interiors Co LLC | ID | 4228272 |  | 4228272 | 0 | 4228272 | 4228272 | 0 | 4228272 |  |  | 1057068 |  | 25% | 1057068 | 0 | 422827.2 | 3805444.8 | L | AP - 6
20 | 20 | Hotel guest room light fittings | HS Energy Solutions FZCO | FOHMEP | 1980228 |  | 1980228 | 54000 | 2034228 | 1816435.5802 | 0 | 1816435.5802 |  | 54000 | 495056.985 |  | 27.5% | 495056.985 | 0 | 187043.558 | 1683392.0222 | AB | AP - 15
25 | 21 | Medical alarm system (panic alarm & disabled toilet alarm) | SIS | FOHMEP | 120000 |  | 120000 | 0 | 120000 | 78000 | 0 | 78000 | [6 empty] | 0 | 7800 | 70200 | D
26 | 22 | Landscape secondary structure | RPJV | LANDSCAPE | 12000000 |  | 12000000 | 0 | 12000000 | 8291345.398 | 327664.0664 | 8619009.4644 |  |  | 2400000 |  | 15% | 1292851.4197 | 1107148.5803 | 861900.9464 | 8864257.0983 | G | AP - 27
27 | 23 | ELV specialistic works Hotel Public Areas (2, 4, 28) | RPJV (SIS) | FOHMEP | 500000 |  | 500000 | 0 | 500000 | 100000 | 0 | 100000 |  |  | 100000 |  | 20% | 20000 | 80000 | 10000 | 170000 | AC | AP - 30
28 | 24 | Lighting control System Hotel&resi Public Areas | RPJV (CREATION GULF) | FOHMEP | 221365.24 |  | 221365.24 | 0 | 221365.24 | 87351.9033 | 0 | 87351.9033 |  |  | 44273.05 |  | 20% | 17470.3807 | 26802.6694 | 8735.1903 | 105419.3823 | H | AP - 31
29 | 25 | Balcony Tiles installation | RPJV | FAÇADE | 577960 |  | 577960 | 0 | 577960 | 248295.5343 | 52999.1903 | 301294.7246 | [6 empty] | 0 | 30129.4725 | 271165.2521 | D
30 | 26 | Supply balcony tiles | RPJV (PORCELLAN) | FAÇADE | 610000 |  | 610000 | 0 | 610000 | 423209.04 | 78000 | 501209.04 |  |  | 610000 |  | 100% | 501209.04 | 108790.96 | 50120.904 | 559879.096 | Q | AP - 26
31 | 27 | Fit out Corridors Level 7 to 16 & 19 to 27: wall covering, stones, painting | Existing Guestrooms Subcon (ASI, Al Rawda, Dar al Rokham) | ID | 2910913 |  | 2910913 | 0 | 2910913 | 1409268.948 | 40401.983 | 1449670.931 |  |  | 582182.48 |  | 20% | 289934.1862 | 292248.2938 | 144967.0931 | 1596952.1317 | Q | AP - 29
32 | 28 | Fit out Corridors Level 7 to 16 & 19 to 27: metalworks | RPJV (AHK) | ID | 900000 |  | 900000 | 0 | 900000 | 112783.3571 | 0 | 112783.3571 |  |  | 180000 |  | 20% | 22556.6714 | 157443.3286 | 11278.3357 | 258948.35 | T | AP - 33
33 | 29 | External wall cladding instread of GRC (Terraco) | RPJV | GRC | 1650000 |  | 1650000 | 0 | 1650000 | 494277.0175 | 3656.3998 | 497933.4173 |  |  | 330000 |  | 20% | 99586.6835 | 230413.3165 | 49793.3417 | 678553.3921 | T | AP - 28
34 | 30 | Front door ironmongery supply - Guestrooms Hotel | RPJV (Mobility General Trading) | ID | 105000 |  | 105000 | 0 | 105000 |  | 0 | 0 | [6 empty] | 0 | 0 | 0 | M
35 | 31 | ELV Box in Hotel Guest Rooms | RPJV (ASI) | ID | 46035 |  | 46035 | 0 | 46035 |  | 0 | 0 | [6 empty] | 0 | 0 | 0 | Y
1a | 32 | Landscape - Softscape package | RPJV | LANDSCAPE | 5110819.99 |  | 5110819.99 | 0 | 5110819.99 |  | 9014.04 | 9014.04 |  |  | 1022163.798 | 1341586.48 | 20% | 1802.808 | 2361947.47 | 901.404 | 2370060.106 | C | AP - 37
1b |  | Landscape - Hardscape package | RPJV | LANDSCAPE | 9234342 |  | 9234342 | 0 | 9234342 | 125561.6053 | 3.638e-10 | 125561.6053 |  |  | 1846868.352 |  | 20% | 25112.3211 | 1821756.0309 | 12556.1605 | 1934761.4757 | AC | AP - 37
1c |  | Landscape - MEP package | RPJV | LANDSCAPE | 4893506 |  | 4893506 | 0 | 4893506 | 1808370.2961 | 16031.7704 | 1824402.0666 |  |  | 978701.21 |  | 20% | 364880.4133 | 613820.7967 | 182440.2067 | 2255782.6566 | AC | AP - 37
1d |  | Landscape - Swimming pool and water features package | RPJV | LANDSCAPE | 3414995.97 |  | 3414995.97 | 0 | 3414995.97 | 845135.556 | 35090 | 880225.556 |  |  | 682999.39 |  | 20% | 176045.1112 | 506954.2788 | 88022.5556 | 1299157.2792 | AC | AP - 37
17a | 33 | GRC claddiing to Stair Plaza&retail | Arabian Profile Co Limited | GRC | 581910.664 |  | 581910.664 | 0 | 581910.664 | 215498.9549 | 19155.4627 | 234654.4176 |  |  | 116382.2 |  | 22.5% | 52797.244 | 63584.956 | 23465.4418 | 274773.9319 | AC | AP - 39
17b |  | GRC Fluted Entrances (Hotel Podium) | Arabian Profile Co Limited | GRC | 363022.1242 |  | 363022.1242 | 0 | 363022.1242 | 18151.1 | 0 | 18151.1 |  |  | 72604.4 |  | 22.5% | 4083.9975 | 68520.4025 | 1815.11 | 84856.3925 | M | AP - 39
17c |  | GRP Cladding to underside of Pool view deck at L29 | Arabian Profile Co Limited | GRC | 74015.3487 |  | 74015.3487 | 0 | 74015.3487 | 74015.3487 | 0 | 74015.3487 |  |  | 14803 |  | 22.5% | 14803 | 0 | 7401.5349 | 66613.8138 | M | AP - 39
17d |  | EIFS Cladding at back side and GRC Cladding at front side at Hotel Rooftop Pool Area - Level 29 | Arabian Profile Co Limited | GRC | 485306.76 |  | 485306.76 | 0 | 485306.76 | 24265.35 | 0 | 24265.35 |  |  | 97061.4 |  | 22.5% | 5459.7037 | 91601.6962 | 2426.535 | 113440.5112 | M | AP - 39
17e |  | GRC Wall Cladding at Hotel Levels 8,11,14,16,21,23,25&27 | Arabian Profile Co Limited | GRC | 95745.1031 |  | 95745.1031 | 0 | 95745.1031 | 45162.2776 | 0 | 45162.2776 |  |  | 19149 |  | 22.5% | 10161.5125 | 8987.4875 | 4516.2278 | 49633.5374 | M | AP - 39
15 | 34 | Timber Ceiling and flooring, skirting to match timber flooring | RPJV | ID | 850000 |  | 850000 | 0 | 850000 |  | 0 | 0 |  |  | 170000 |  |  |  | 170000 | 0 | 170000 | M | AP - 39
16 |  | Painted Timber Skirting Hotel Rooms |  |  | 0 |  | 0 | 0 | 0 |  | 0 | [7 empty] | 0 | 0 | 0 | V
28 | 35 | Hotel Guestrooms media hub | RPJV | FOHMEP | 103965 |  | 103965 | 0 | 103965 |  | 0 | 0 |  |  | 30000 |  |  |  | 30000 | 0 | 30000 | V | AP - 39
22 | 36 | Fire Hose Cabinet Doors to Hotel Corridors | RPJV | ID | 85856.82 |  | 85856.82 | 0 | 85856.82 |  | 0 | 0 |  |  | 17171.364 |  |  |  | 17171.364 | 0 | 17171.364 | F | AP - 39
4 |  | Light fittings Supply for Hotel Corridors | Project Supplies | FOHMEP | 498657 |  | 498657 | 0 | 498657 |  | 428632 | 428632 |  |  | 249328.5 |  |  |  | 249328.5 | 42863.2 | 635097.3 | W | AP - 35
5 | 37 | Light fittings Supply for Hotel Public Areas (LV2,4, 28) excluding L4 | Project Supplies | FOHMEP | 779967 |  | 779967 | 0 | 779967 |  | 76368.8 | 76368.8 |  |  | 389983.25 |  |  |  | 389983.25 | 7636.88 | 458715.17 | D | AP - 35
6 | 38 | Light fittings Supply for Residential Public Areas (GF, LV2, LV4, LV23) | Project Supplies | FOHMEP | 394865.2 |  | 394865.2 | 0 | 394865.2 |  | 171952.402 | 171952.402 |  |  | 197432.6 |  |  |  | 197432.6 | 17195.2402 | 352189.7618 | D | AP - 35
7 | 39 | Light fittings Supply for Balconies and Tower Façade | Project Supplies | FOHMEP | 644724 |  | 644724 | 0 | 644724 |  | 639180 | 639180 |  |  | 322362 |  |  |  | 322362 | 63918 | 897624 | D | AP - 35
11 | 40 | Hotel Ground Floor Light fittings (ballroom&meeting rooms) | Project Supplies | FOHMEP | 588000 |  | 588000 | 0 | 588000 |  | 56292.9 | 56292.9 |  |  | 294000 |  |  |  | 294000 | 5629.29 | 344663.61 | D | AP - 35
29 | 41 | Electrical FOH at Level-07 to 11 Hotel | RPJV (Future Metro) | FOHMEP | 2008965.2212 |  | 2008965.2212 | 0 | 2008965.2212 | 2001386.1702 | 0 | 2001386.1702 | [6 empty] | 0 | 200138.617 | 1801247.5532 | D
30 | 42 | Electrical FOH at Level-8 Residential | RPJV (Future Metro) | FOHMEP | 497164.17 |  | 497164.17 | 0 | 497164.17 | 497164.1717 | 0 | 497164.1717 | [6 empty] | 0 | 49716.4172 | 447447.7546 | C
31 | 43 | Electrical FOH at Level-12 to 16 Hotel | RPJV (Future Metro) | FOHMEP | 3876246.9258 |  | 3876246.9258 | 0 | 3876246.9258 | 3839265.3596 | 0 | 3839265.3596 | [6 empty] | 0 | 383926.536 | 3455338.8236 | I
32 | 44 | External facade lighting provisions (balcony and void areas) | RPJV | FOHMEP | 353378.6051 |  | 353378.6051 | 0 | 353378.6051 | 249817.3084 | 21767.4395 | 271584.7478 | [6 empty] | 0 | 27158.4748 | 244426.2731 | C
2 | 45 | Electrical Works Hotel Corridors MEP/ELV | RPJV | FOHMEP | 300000 |  | 300000 | 0 | 300000 | 197130 | 0 | 197130 |  |  | 60000 |  | 20% | 39426 | 20574 | 19713 | 197991 | D | AP - 36
10 | 46 | Light fittings for Hotel Public areas (Level 4) | Project Supplies | FOHMEP | 236349 |  | 236349 | 0 | 236349 |  | 30166.04 | 30166.04 |  |  | 118174.55 |  |  |  | 118174.55 | 3016.604 | 145323.986 | C | AP - 35
8 | 47,48 | Light fittings Supply for Podium Façade - landscape | Project Supplies | FOHMEP | 2528753 |  | 2528753 | 0 | 2528753 |  | 0 | 0 |  |  | 1264376.5 |  |  |  | 1264376.5 | 0 | 1264376.5 | D | AP - 35
9 | 49 | Void area lighting Control Cable | RPJV | FOHMEP | 21500 |  | 21500 | 0 | 21500 | 16608.75 | 0 | 16608.75 |  |  | 1560 |  | 20% | 1560 | 0 | 1660.875 | 14947.875 | D | AP - 39
23 | 50 | Balance Joinery,ironmongery in Hotel Corridors |  | ID | 620000 |  | 620000 | 0 | 620000 | 22512 | 0 | 22512 |  |  | 122828.8 |  | 20% | 4502.4 | 118326.4 | 2251.2 | 138587.2 | D | AP - 39
24 | 51 | Sanitaryware for hotel guestrooms 7A and 15A | RPJV | FOHMEP | 216996.19 |  | 216996.19 | 0 | 216996.19 | 156625.2 | 0 | 156625.2 |  |  | 43399.238 |  | 20% | 31325.04 | 12074.198 | 15662.52 | 153036.878 | T | AP - 39
| 52 | Ommission Provisional Sum Sanipex (9 rooms 7A,15A,Royal and Presidential Suites |  | ID | -222939 |  | -222939 | 0 | -222939 | 0 | -179637.5959 | -179637.5959 | [7 empty] | -17963.7596 | -161673.8363 | B
[20 empty] | 0 | 0
| A |  | Sub Total for Awarded Provisional Sums |  | 230864577.722 | 0 | 230864577.722 | 5529988.8226 | 236394566.5447 | 156605915.8155 | 4603671.331 | 161209587.1466 | 1493173.9032 | 4443751.5991 | 33683298.267 | 2441586.48 |  | 21462668.2061 | 14662216.5409 | 16714651.2649 | 165094077.9249
19 | 19 | Signages and wayfinding |  | ID | 2000000 |  | 2000000 | 0 | 2000000 |  |  | 0 |  |  | 400000 |  |  |  | 400000 | 0 | 400000 | AA | AP - 39 | Provisional Sum
21 | 21 | Sanitaryware to hotel guestrooms Royal and presidential suites |  | FOHMEP | 75000 |  | 75000 | 0 | 75000 |  |  | 0 | [6 empty] | 0 | 0 | 0 | B
25 | 25 | Additional Fit-out items in guestroom suites (ie. Balustrades) |  | ID | 200000 |  | 200000 | 0 | 200000 |  |  | 0 |  |  | 40000 |  |  |  | 40000 | 0 | 40000 | Z | AP - 39 | Provisional Sum (OME estimate figure)
D |  |  | Sub Total To be Awarded PS |  | 2275000 | 0 | 2275000 | 0 | 2275000 | 0 | 0 | 0 | 0 | 0 | 440000 | 0 |  | 0 | 440000 | 0 | 440000
|  | Descoped packages to be rescoped and Instructed |  |  |  |  | 0 | 0 | 0 | [10 empty] | 0 | 0
| 1 | Fitout residence public area | AHK | ID | 4000000 |  | 4000000 | 0 | 4000000 | 2350230.4 | 37158.4 | 2387388.8 |  |  | 600000 |  | 15% | 358108.32 | 241891.68 | 238738.88 | 2390541.6 | AB | AP - 24
| 2 | ELV specialistic works Resi Public Areas (G,2, 4, 23) | RPJV | FOHMEP | 371516 |  | 371516 | 0 | 371516 | 88842.7412 | 0 | 88842.7412 | [5 empty] | 0 | 0 | 8884.2741 | 79958.4671 | I
| 3 | Electrical works resi FOH public areas (GF,2,4,23) | RPJV -Silicon Vega | FOHMEP | 322543 |  | 322543 | 0 | 322543 | 286321.4211 | 0 | 286321.4211 |  |  | 64508.6 |  | 20% | 57264.2842 | 7244.3158 | 28632.1421 | 264933.5948 | I | AP - 32
| E |  | Sub Total for Descoped packages to be rescoped and Instructed |  | 4694059 | 0 | 4694059 | 0 | 4694059 | 2725394.5623 | 37158.4 | 2762552.9623 | 0 | 0 | 664508.6 | 0 |  | 415372.6042 | 249135.9958 | 276255.2962 | 2735433.6619
|  | Extra packages required for completion of the project |  |  |  |  | 0 | 0 | 0 | [10 empty] | 0 | 0
| 1 | Headboards |  | ID | 712815 |  | 712815 | 0 | 712815 |  |  | 0 |  |  | 169959.2 |  |  |  | 169959.2 | 0 | 169959.2 | AA | AP - 39
| 2 | Hotel Kitchen equipment works (Hoods and Cold Rooms only) |  |  | 1735122 | 487988 | 2223110 | 0 | 2223110 |  |  | 0 |  |  | 670398 |  |  |  | 670398 | 0 | 670398 |  | AP - 39, AP - 41
| 3 | Kitchens and BOH Areas - GF,L2, L28 (Fitout) |  |  | 580000 |  | 580000 | 0 | 580000 |  |  | 0 |  |  | 116000 |  |  |  | 116000 | 0 | 116000 | AA | AP - 39
| 4 | 2 No. Penthouse lifts and 2 No. Retail Lobby Lifts (Coring only by RPJV, Lifts by OM) |  | LIFT | 300000 |  | 300000 | 0 | 300000 |  |  | 0 |  |  | 60000 |  |  |  | 60000 | 0 | 60000 | AA | AP - 39
| 5 | Carpet and Wallpaper for Hotel |  | ID | 2000000 |  | 2000000 | 0 | 2000000 |  |  | 0 |  |  | 1188454.595 |  |  |  | 1188454.595 | 0 | 1188454.595 | AA | AP - 40
|  |  | Sub Total for Extra packages required for completion of the project |  | 5327937 | 487988 | 5815925 | 0 | 5815925 | 0 | 0 | 0 | 0 | 0 | 2204811.795 |  |  | 0 | 2204811.795 | 0 | 2204811.795
|  | Descoped Packages to be Rescoped |  |  |  |  | 0 | 0 | 0 | [10 empty] | 0 | 0
| 1a | Turn Key Fitout -Ball Room L0 |  | ID | 5000000 | 0 | 5000000 | 0 | 5000000 | 125000 | 132304.8121 | 257304.8121 |  |  | 1318887.8 |  | 20% | 115922.3877 | 1202965.4123 | 25730.4812 | 1434539.7432 | AA | AP - 39
| 1b | MEP and ELV - Ball room L0+Additional lift |  | FOHMEP | 1000000 | 594439 | 1594439 | 0 | 1594439 | 166374.1985 | 155932.9277 | 322307.1262 | [6 empty] | 0 | 32230.7126 | 290076.4136 |  | AP - 39
| 2a | Royalsuits fitout works |  | FOHMEP | 1718372.7909 | 0 | 1718372.7909 | 0 | 1718372.7909 | 0 | 53836.3215 | 53836.3215 |  |  | 343674.5582 |  | 20% | 10767.2643 | 332907.2939 | 5383.6322 | 381359.9833 | AA | AP - 39
| 2b | Presidential suites fitout works |  | FOHMEP | 1829208.4191 | 0 | 1829208.4191 | 0 | 1829208.4191 | 0 | 63448.7251 | 63448.7251 |  |  | 365841.6838 |  | 20% | 12689.745 | 353151.9388 | 6344.8725 | 410255.7914 | AA | AP - 39
| 2c | Royal and Presidential Suites MEP Works |  | FOHMEP | 412877.79 | 0 | 412877.79 | 0 | 412877.79 | 106216.9403 |  | 148726.3781 |  |  | 82575.558 |  | 20% | 29745.2756 | 52830.2824 | 14872.6378 | 186684.0227 | C | AP - 39
| 4a | LV 28 Gym fitout works |  | ID | 413000 | 1466 | 414466 | 0 | 414466 |  |  | 30704.6687 |  |  | 82600 |  |  |  | 82600 | 3070.4669 | 110234.2018 | AA | AP - 39
| 4b | LV 28 Gym MEP (electrical, ELV and lighting) |  | FOHMEP | 150000 | 0 | 150000 | 0 | 150000 | 30033.0342 | 7216.26 | 37249.2942 |  |  | 30000 |  | 20% | 7449.8588 | 22550.1412 | 3724.9294 | 56074.506 | C | AP - 39
| 5 | Turn Key Fitout - GF and Level 1 Ablution |  | ID | 358982.5595 | 392324.8705 | 751307.43 | 0 | 751307.43 |  |  | 0 |  |  | 150261.486 |  | 20% | 0 | 150261.486 | 0 | 150261.486 | AA | AP - 39
| 6 | Turn Key Fitout - Rooftop LV 29 (amenties) |  | ID | 513931.25 | 561665.2 | 1075596.45 | 0 | 1075596.45 |  |  | 0 |  |  | 215119.29 |  | 20% | 0 | 215119.29 | 0 | 215119.29 | AA | AP - 39
| 6a | MEP Works - GF,Level 1 Ablution room and Roof Top L29 |  | FOHMEP | 127086.1904 | 138889.9596 | 265976.15 | 0 | 265976.15 | 54272.6245 | 2709.3819 | 56982.0064 |  |  | 0 |  | 20% | 0 | 0 | 5698.2006 | 51283.8057 | AA
| 7 | Turnkey fitout - Signature resturant LV 17 |  |  | Excluded | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
| 8 | Electrical Works Hotel FOH Public area - LV17, LV29 including ELV |  |  | Excluded | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
| 9 | Lighting fitting supply (L29, L17 |  |  | Excluded | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
| 10 | Carpet - Guest rooms Hotel |  |  | Excluded | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0
| 11 | Decorative Wall Covering - Guest room Hotels |  |  | Excluded | [14 empty] | 0 | 0
| 12 | Light fittings (Inc. point wiring, switches and sockets) - Residence Corridor |  |  | Excluded | [14 empty] | 0 | 0
| D |  | Sub Total for Descoped Packages to be Rescoped |  | 11523459 | 1688785.03 | 13212244.03 | 0 | 13212244.03 | 481896.7975 | 488662.5348 | 970559.3323 | 0 | 0 | 2588960.376 | 0 |  | 176574.5315 | 2412385.8445 | 97055.9332 | 3285889.2436
|  |  |  | Adjustments | [5 empty] | 0 | 0 | 0 | [8 empty] | 0
|  |  |  | Attendence,profit and margin | [16 empty] | 0
TOTAL | TOTAL |  |  |  | 254685032.722 | 2176773.03 | 256861805.752 | 5529988.8226 | 262391794.5747 | 159813207.1753 | 5129492.2659 | 164942699.4412 | 1493173.9032 | 4443751.5991 | 39581579.038 | 2441586.48 |  | 22054615.3417 | 19968550.1763 | 17087962.4943 | 173760212.6254
[10 empty] | 8663448.5718 | -321984.8367 | 8341463.7351
[10 empty] | 168476655.7471 | 4807507.4292 | 173284163.1762
[10 empty] | 168476655.7471 | 4807507.4292 | 173284163.1762 | 1493173.9032 |  | 52923164.916 | 42023165.518
9119474.1716
|  | MEP FRONT OF HOUSE | FOHMEP |  | 28215047.612 | [6 empty] | 20551870.6175
|  | LIFTS | LIFT |  | 13988719 | [6 empty] | 12896683.3812
|  | FAÇADE | FAÇADE |  | 62918675 | [6 empty] | 50880187.5084
|  | BALLUSTRADES | Balustrade |  | 9063400 | [6 empty] | 6874180.1002
|  | GRC | GRC |  | 21550000 | [6 empty] | 17361589.9088
|  | BMU | BMU |  | 2111400 | [6 empty] | 887336.9305
|  | ID AND FITOUT | ID |  | 59299478.15 | [6 empty] | 39174349.8743
|  |  | LANDSCAPE |  | 34653663.96 | [6 empty] | 11458212.7323
|  |  | AHK |  | 0 | [6 empty] | 2387388.8
Adjustments on FOH MEP
162471799.853
[12 empty] | Addendum 2 advances |  |  | 1144959.402 |  | 1144959
Note on Q56: Author: As per Appendix F1 Addendum 2
Note on Q70: Author: As per Appendix F1 Addendum 2
Note on Q71: Author: As per Appendix F1 Addendum 2
Note on Q93: Author: 1.2 Mn as per add 2, increased to 1.3 mn

## Summary-VOs after ADD 2
Schedule of Variations Submitted After Addendum-2
Ref | Sub-Contractor/Consultant | OCI Estaimated Amount | RPJV Submitted Amount | OCI Estaimated Amount-Excluding Consultants and Main Contractor works
1 | AHK Worldwide Interiors LLC | 965277.42 | 433220.03 | 965277.42
2 | TSSC Kitchen | 208941.9 | 208941.9 | 208941.9
3 | Bond Interior Design LLC | 229382.455 | 536744.39 | 229382.455
4 | Glassline Aluminum LLC | 996483.4 | 2320011.02 | 996483.4
5 | Creation Gulf Trading LLC | 113829.32 | 113829.32 | 113829.32
6 | Momentum Fireguard LLC | -22924.62 | 91798.01 | -22924.62
7 | SIS | 299387.38 | 299387.38 | 299387.38
8 | Kone Middle East LLC | 576000 | 230147.2 | 576000
9 | LMS | 219420 | 219420
10 | Arcadia Metal Industries LLC | 275000 | 329488.99 | 275000
11 | DESIGN | 106000 | 106000 |  |  | Consultants
12 | Light Touch | 21215.9 | 21215.9
13 | MEDIATECH | 84969.6 | 84969.6 |  |  | Main Contractor
14 | DESIGN | 127690.78 | 127690.78
15 | Al Reem Marble & Granite LLC | 553312.515 | 687750.02 | 553312.515
16 | Fiona Environs UAE | 600000 | 600317.48 | 600000
17 | Fondue | 158152 | 158152
18 | JOYZ OVERCIS LLC | 170448 | 170448 | 170448
19 | BSBG | 1355475 | 1355475
20 | MEINHARDT | 108946.8 | 108946.8
21 | Light Touch | 21215.9 | 44439
22 | BG&E | 294220 | 294220
23 | Timelaps | 31800 | 31800
24 | CEC | 209880 | 209880
25 | PROJECT SUPPLIES | 39169.12 | 39169.12 | 39169.12
26 | Al Rawaa |  | 636000
27 | MEP | 1174399.5741 | 1324740.85
28 | CIVIL | 45000 | 45000
29 | FINISHES | 49810.1 | 49810.1 |  | 931101.6741
-338108
| Total | 9012502.5441 | 10879012.89 | 5004306.89

## ADD2-VO-REGISTER - R1
EMPLOYER VARIATION LOG AFTER ADDENDUM 2
VARITATION DETAILS |  |  | CLIENT INSTRUCTION |  | RPJV's VARIATION NOTIFICATIONS |  | RPJV's VARIATION SUBMISSIONS |  | RPJV | OCI | CLIENT EVALUATIONS / RESPONSES |  |  |  | VARIATION APPROVAL STATUS |  |  | Sub-Contractor
Sl. No. | RC-ADD2-VO Reference | Descriptions | Letter Ref. | Date | Letter Ref. | Date | Letter Ref. | Date | Submitted Amount (AED) | Estimated Amount (AED) | Letter Ref. | Date | VO Amount (AED) | Date to be Responded | Status | VO Status / Remarks | Action By
1 | VO-001 | Provisional Sum Adjustment for Lift Car Finishes - Hotel Lobby | OMERED-RTRFI-000215 / OMERED-LETTER-001169 | 2-Feb-2020, 14-July-2020 | - | - | ROBERTS-VAR-000292 | 2021-07-07 | 64289 | -9612 | OMERED-GNC-002059, OMERED-GNC-002151 | 9-Aug-2021 , 07-Oct-2021 | -9612 | Responded | OME Assessment issued and RPJV to agree | OME Assement issued and RPJV to respond. | RPJV | Bond Interior Design LLC | 6 LIFTS IN HOTEL | N
2 | VO-002 | Provisional Sum Adjustment for Ironmongeries | OMERED-LETTER-001169 | 2021-07-14 | - | - | ROBERTS-VAR-000294, ROBERTS-VAR-000310, ROBERTS-VAR-000338 | 11-Jul-2021 , 26-Oct-2021, 17-Jan-2022 | 91798.01 | -22924.62 | OMERED-GNC-002062, OMERED-GNC-002189, OCI-LETTER-002245 | 15-Aug-2021, 17-Nov-2021, 04-Feb-2022 | -22924.62 | Responded | OME Assessment issued and RPJV to agree | OME Assement issued and RPJV to respond. | RPJV | Momentum Fireguard LLC | BOND scop doors | N
3 | VO-004 | Change in Guestroom Access control panel (changing existing touch panel) | Material sample submission ref. CGT-EX-SA-HT-00004 | 2021-06-28 | ROBERTS-VR-000194 | 2021-07-19 | - | - | 91427.54 | 91427.54 | OMERED-LETTER-001819 | 2021-07-26 | 0 | Responded | Submitted and Rejected | 1. OME advised that the cost is already included in Addendum 2 - Refer Appendix A2 – page 2 of 3 – Ref VO-0227. 2. OME rejected and RPJV to respond to close this VO. | RPJV | Creation Gulf Trading LLC | All 225 rooms
4 | VO-005 | Additional scope to provide power & control provisions for motorized curtain & louvres at Hotel & Residential lobbies | OMERED-LETTER-001762 | 2021-06-23 | ROBERTS-VR-000197, ROBERTS-RFI-000803, OMERED-RTRFI-000262 | 1-Aug-2021 , 21-June-2021, 22-June-2021. | ROBERTS-VAR-000351 | 2022-01-31 | 49337.98 | 27251.0641 |  |  |  |  | Submitted and Under Review | Under OME review | OME | MEP | Ground floor Resi & Hotel lobies | N
5 | VO-007 | Undertaking Kitchen Equipment package engineering works for hotels. | OMERED-LETTER-001796 | 2021-07-08 | ROBERTS-VR-000196 | 2021-08-01 | ROBERTS-VAR-000358 | 2022-02-09 | 100952.28 | 100952.28 | OMERED-LETTER-001796 | 2021-07-08 | 95000 | Responded | OME Assessment issued and RPJV to agree | OME issued Assessment and RPJV to review and confirm. | RPJV | TSSC Kitchen | Additional to 2.223M agreement
6 | VO-008 | Undertaking refrigeration lines,supply,installation including associated civil works to the hotels. | OMERED-LETTER-001796 | 2021-07-08 | ROBERTS-VR-000195, | 2021-07-31 | ROBERTS-VAR-000357 | 2022-02-08 | 107989.62 | 107989.62 |  |  |  |  | Submitted and Under Review | Under OME review | OME | TSSC Kitchen | Additional to 2.223M agreement
7 | VO-009 | Review and endorsement of Landscape, Irrigation & Façade Lighting packages for drainage , power and lighting services | OMERED-LETTER-001888 | 2021-09-05 | ROBERTS-VR-000199 | 2021-08-04 | ROBERTS-VAR-000317 | 2021-11-24 | 106000 | 106000 | OMERED-LETTER-001888 | 2021-09-05 | 100000 | Responded | OME Assessment issued and RPJV to agree | OME issued Assessment and RPJV to review and confirm. | RPJV | DESIGN
8 | VO-010.1 | MEP Design development & coordination for residential retail lobby level 1 & 2 (Light Touch) | OMERED-LETTER-001732 OMERED-LETTER-001785 | 9-June-2021, 04-July-2020 | ROBERTS-VR-000200 | 2021-08-01 | ROBERTS-VAR-000303 | 2021-08-31 | 21215.9 | 21215.9 | OMERED-LETTER-001888 | 2021-09-05 | 20015 | Responded | OME Assessment issued and RPJV to agree | OME issued Assessment and RPJV to review and confirm. | RPJV | Light Touch
9 | VO-010.2 | MEP Design development & coordination for residential retail lobby level 1 & 2 (Mediatech) | OMERED-LETTER-001732 OMERED-LETTER-001785 | 9-June-2021, 04-July-2020 | ROBERTS-VR-000200 | 2021-08-01 | ROBERTS-VAR-000302 | 2021-08-28 | 8649.6 | 8649.6 | OMERED-LETTER-001888 | 2021-09-05 | 8160 | Responded | OME Assessment issued and RPJV to agree | OME issued Assessment and RPJV to review and confirm. | RPJV | MEDIATECH |  |  | Submitted and Under Review | 1. OME responded with requirement of additional two Quotations and Marked up drawings. 2. RPJV to respond. | RPJV | Arcadia Metal Industries LLC
10 | VO-012 | Thermal & Moisture protection to All day Dining, Level 28 Spa & Level 2 Hotel Main Lobby | OMERED-LETTER-001169 | 2020-07-14 | - | - | ROBERTS-VAR-000296 | 2021-08-02 | 49810.1 | 49810.1 | OMERED-LETTER-001835 | 2021-08-09 | 0 | Responded | Submitted and Rejected | 1. OME rejected since it is included in Add-02. 2. RPJV to respond to close this VO. | RPJV | FINISHES
11 | VO-013 | Addition of disabled regulations to Level 28 Spa Treatment No.5 Bathrooms | OMERED-RTRFI-000245 | 2021-05-20 | - | - | ROBERTS-VAR-000298 | 2021-08-07 | 13852.06 | 10528.2168 | OMERED-GNC-002191 | 2021-11-21 |  | Responded | Submitted and Under Review | OME requesting detailed submission and RPJV to respond. | RPJV | Bond Interior Design LLC |  | N
12 | VO-014 | Supply & Installation Baby changing stations to Disabled toilets | OMERED-RTRFI-000180, OMERED-RTRFI-000182 | 16-Nov-2020, 16-Nov-2020 | - | - | ROBERTS-VAR-000299 | 2021-08-07 | 4415.75 | 4415.75 | OMERED-GNC-002180 | 2021-11-08 | 4415.75 | Responded | OME Assessment issued and RPJV to agree | OME issued assessment and RPJV to confirm. | RPJV | Bond Interior Design LLC |  | N
13 | VO-015 | Additional grab bars to disabled toilets Hotel Lobby & All Day Dining | To be Updated |  | To be Updated |  | ROBERTS-VAR-000297 ROBERTS-VAR-000305 | 16/9/2021, 23/09/2021 | 20383.16 | 10757.94 | OMERED-LETTER-001867 | 2021-08-25 |  | 2021-10-05 | Submitted and Under Review | RPJV resubmitted the VO vide ROBERTS-VAR-000305 and awaiting OME response. | OME | Bond Interior Design LLC |  | N
14 | VO-020 | Wooden flooring change to stone flooring Residence Basement 1&2 Lobby | OMERED-GNC-001616 | 2021-11-08 | - | - | ROBERTS-VAR-000360 | 2022-02-09 | 15002.82 | 15002.82 |  |  |  |  | Submitted and Under Review | Under OME review | OME | AHK Worldwide Interiors LLC
15 | VO-021 | Redesigning of the detailed design Level 17 (Fuego Restaurant) | OMERED-WTRAN-005996 | 2021-07-06 |  |  | ROBERTS-VAR-000304 | 2021-09-05 | 21690.78 | 21690.78 |  |  |  | 2021-09-19 | Submitted and Under Review | Under OME review | OME | DESIGN
16 | VO-022 | Pantry at level 23 - Provisional sum adjustment. | OMERED-LETTER-001309 |  |  |  | ROBERTS-VAR-000312 | 2021-10-24 | 57760.11 | 50000 | OMERED-GNC-002163 | 2021-10-26 | 0 | Responded | Submitted and Under Review | 1. OME responded and RPJV to reply. | RPJV | AHK Worldwide Interiors LLC |  | N
17 | VO-023 | Design of Secret Terrace Bar at Level 2 | OMERED-LETTER-001499 | 2021-01-07 |  |  | ROBERTS-VAR-000306, ROBERTS-LETTER-001558 | 21-Sep-2021, 27-Jan-2022 | 38160 | 38160 | OMERED-LETTER-001934, OCI-LETTER-002201 | 23-Sep-2021, 21-Jan-2022 | 0 | Responded | Submitted and Rejected | 1. OME rejected and RPJV to respond. | RPJV | LMS
18 | VO-024 | Residence Drainage Piping for Level 06 & 24 Apartments | ROBERTS-WTRAN-078763, OMERED-LETTER-001783 | 20-Oct-2020, 4-July-2021 | ROBERTS-VR-000193 | 2021-06-13 | ROBERTS-VAR-000309, ROBERTS-LETTER-001592 | 20-Oct-2021, 09-Feb-2022 | 97205.58 | 97205.58 |  |  |  |  | Submitted and Under Review | Under OME review. | OME | MEP
19 | VO-026 | Replacement Chiller for Level 8 Residence Apartments, DX Units Level 8 Corridor, DX Unit Sales Centre Corridor | OMERED-LETTER-001663 OMERED-LETTER-001714 | 27-Apr-2021, 31-May-2021 | - | - | ROBERTS-VAR-000315, ROBERTS-VAR-000319. ROBERTS-VAR-000346, ROBERTS-LETTER-001593 | 15-Nov-2021, 28-Nov-2021, 26-Jan-2022, 09-Feb-2022 | 606154.36 | 477900 |  |  |  |  | Submitted and Under Review | Under OME review. | OME | MEP
20 | VO-027 | Dismantling Costs for Ecology Units | To be Updated | [5 empty] | 30000 | 30000 |  |  |  |  | Estimated | RPJV to submit the cost. | RPJV | MEP
21 | VO-030 | Royal and Presidential Suites Increased Electrical Load | ROBERTS-RFI-000815, OMERED-RTRFI-000272 | 01-Aug-2021, 03-Aug-2021 | - | - | ROBERTS-VAR-000314 | 2021-11-09 | 29712.67 | 29712.67 |  |  |  | 2021-11-23 | Submitted and Under Review | Under OME review. | OME | MEP
22 | VO-031 | Hotel Level 17 & 29 IT+AV Layout | OMERED-LETTER-001751, OMERED-LETTER-001772 | 17-June-2021, 28-June-2021 | ROBERTS-LETTER-001326 ROBERTS-LETTER-001342 | 03-June-2021, 21-June-2021 | ROBERTS-VAR-000321 | 2021-11-30 | 51522.13 | 51522.13 | OCI-LETTER-002154, OCI-LETTER-002216 | 05-Jan-2022, 26-Jan-2022 | 0 |  | Submitted and Rejected | 1. OME rejected with comments of its already included in Landscpae works Provisional sum award. 2. RPJV responded and issued dispute notice through letter ref. ROBERTS-LETTER-001594, dated 09 February 2022. | OME | SIS
23 | VO-036 | Kitchen Hoods and Cold Rooms | To be Updated | [6 empty] | 0 |  |  |  |  | Estimated | RPJV to submit the cost. | RPJV | TSSC Kitchen
24 | VO-037 | Additional Tablet in Spa Treatment Rooms | OMERED-LETTER-001943 | 2021-09-28 | ROBERTS-VR-000203 | 2021-09-27 | ROBERTS-VAR-000313 | 2021-11-09 | 146032.93 | 146032.93 |  |  |  | 2021-11-23 | Submitted and Under Review | OME responded and RPJV to rspond. | RPJV | SIS
25 | VO-038 | Platform for Ecology Units | To be Updated | [5 empty] | 45000 | 45000 |  |  |  |  | Estimated | RPJV to submit the cost. | RPJV | CIVIL
26 | VO-039 | PC Rate Adjustment for Acoustic Underlay | To be Updated |  |  |  | ROBERTS-VAR-000307 | 2021-10-04 | 31520.96 | 31520.96 | OMERED-GNC-002166 | 2021-11-01 | 0 | Responded | OME Assessment issued and RPJV to agree | 1. OME responded and RPJV to close this VO. | RPJV | AHK Worldwide Interiors LLC
27 | VO-040 | PC Rate Adjustment for Landscape Stoneworks | To be Updated | [5 empty] | 150000 | 150000 |  |  |  |  | Estimated | RPJV to submit the cost. | RPJV | Al Reem Marble & Granite LLC
28 | VO-041 | PC Rate Adjustment for Landscape Metal Works | OMERED-LETTER-001499 | 2021-01-07 | ROBERTS-LETTER-001106 | 2020-10-04 | ROBERTS-VAR-000330 | 2021-12-23 | 329488.99 | 275000 | OMERED-GNC-002217 | 2021-12-28 |  |  | Submitted and Under Review | 1. OME responded with requirement of additional two Quotations and Marked up drawings. 2. RPJV to respond. | RPJV | Arcadia Metal Industries LLC |  | N
29 | VO-042 | PC Rate Adjustment for Landscape Softscape Works | OMERED-LETTER-001499 | 2021-01-07 | ROBERTS-LETTER-001106 | 2020-10-04 | ROBERTS-VAR-000328 | 2021-12-09 | 600317.48 | 600000 | OMERED-GNC-002216 | 2021-12-28 |  |  | Submitted and Under Review | 1. OME responded with requirement of additional two Quotations and Marked up drawings. 2. RPJV to respond. | RPJV | Fiona Environs UAE |  | N
30 | VO-043 | PVC Grooves for EIFS | To be Updated |  | To be Updated |  | ROBERTS-VAR-000306 | 2021-07-15 | 170448 | 170448 | OMERED-WTRAN-006626 | 2021-09-15 | 0 | Responded | Submitted and Rejected | OME rejected and RPJV to respond. | RPJV | JOYZ OVERCIS LLC
31 | VO-044 | Electrical Works for Additional Water Feature in Residential Ground Floor Zone 3A | OMERED-LETTER-001984 |  | ROBERTS-VR-000204 |  |  |  | 10000 | 10000 |  |  |  |  | Estimated | RPJV to submit the cost. | RPJV | MEP
32 | VO-045 | Additional Socket in the 4B-Duplex Apartment Balcony | OMERED-LETTER-002071 |  | ROBERTS-VR-000206 | 2021-11-09 | ROBERTS-VAR-000356 | 2022-02-08 | 16813.33 | 16813.33 |  |  |  |  | Submitted and Under Review | Under OME review. | OME | MEP
33 | VO-046 | Residences Units 602 and 603 Drainage Modification | OMERED-LETTER-001935, OMERED-LETTER-002088 | 27-Sep-2021, 25-Nov-2021 | ROBERTS-NOD-000108, ROBERTS-NOD-000121 | 16-Oct-2021, 21-Nov-2021 | ROBERTS-VAR-000355 | 2022-02-03 | 118553.28 | 118553.28 |  |  |  |  | Estimated | RPJV to submit the cost. | RPJV | MEP
34 | VO-047 | Timelapse Camera | OMERED-LETTER-000466 | 2019-02-19 | - | - | ROBERTS-VAR-000344 | 2022-01-24 | 31800 | 31800 |  |  |  |  | Submitted and Under Review | Under OME review. | OME
35 | VO-048 | Extension of consultant's site supervision services - Close out support (Fondue) | OMERED-LETTER-001573 | 2021-03-02 |  |  | ROBERTS-VAR-000316 ROBERTS-VAR-000326, ROBERTS-LETTER-001556, ROBERTS-LETTER-001590, ROBERTS-LETTER-001596 | 22/11/2021 08/12/2021, 19/01/2022, 07/02/2022, 09/02/2022 | 158152 | 158152 | OMERED-LETTER-002096 | 2021-11-30 | 0 | 2022-03-26 | Submitted and Under Review | 1. OME rejected and saying included in Addendum 2. Resubmitted via ROBERTS-VAR-000326 (08/12/2021) and ROBERTS-LETTER-001556, dated 19/01/2022. 3. RPJV responded and issued dispute notice through letter ref. ROBERTS-LETTER-001596, dated 09 February 2022. | OME | FONDUE
36 | VO-049 | Provisional Sum Adjustment of Ironmongeries at Residence lobby & Ameneties | [6 empty] | 15000 | 15000 |  |  |  |  | Estimated | RPJV to submit the cost. | RPJV | AHK Worldwide Interiors LLC
37 | VO-050 | BP8 Amendment (BSBG) | OMERED-LETTER-001944 | 2021-09-28 | ROBERTS-VR-000207 | 2021-11-16 | ROBERTS-VAR-000326 | 2021-12-08 | 94552 | 94552 | OMERED-GNC-002203 | 2021-12-09 |  | Responded | Submitted and Under Review | 1. OME requested additional informations. 2. RPJV to respond. | OME | BSBG
38 | VO-051 | Extension of consultant's site supervision services (LMS) - Landscape works |  |  | ROBERTS-VR-000214 | 2021-12-06 | ROBERTS-VAR-000322 | 2021-12-08 | 181260 | 181260 | OCI-LETTER-002217 | 2022-01-26 | 0 |  | Submitted and Rejected | 1. OME rejected. 2. RPJV to respond. | RPJV | LMS
39 | VO-051.1 | Extension of consultant's site supervision services (BSBG) - Nov 2021 to Apr 2022 |  |  | ROBERTS-VR-000215 | 2021-12-06 | ROBERTS-VAR-000323 | 2021-12-08 | 1081200 | 1081200 | OCI-LETTER-002217 | 2022-01-26 | 0 | Responded | Submitted and Rejected | 1. OME rejected. 2. RPJV responded and issued dispute notice through letter ref. ROBERTS-LETTER-001598, dated 09 February 2022. | OME | BSBG
40 | VO-051.2 | Extension of consultant's main certification stamping (BSBG-NEA) - Sep 2021 to Apr 2022 |  |  | ROBERTS-VR-000213 | 2021-12-06 | ROBERTS-VAR-000324 | 2021-12-08 | 93280 | 93280 | OCI-LETTER-002217 | 2022-01-26 | 0 | Responded | Submitted and Rejected | 1. OME rejected. 2. RPJV responded and issued dispute notice through letter ref. ROBERTS-LETTER-001597, dated 09 February 2022. | OME | BSBG
41 | VO-051.3 | Extension of consultant's site supervision services (Mediatech) |  |  | ROBERTS-VR-000212 | 2021-12-06 | ROBERTS-VAR-000325 | 2021-12-08 | 76320 | 76320 | OCI-LETTER-002217 | 2022-01-26 | 0 | Responded | Submitted and Rejected | 1. OME rejected. 2. RPJV responded and issued dispute notice through letter ref. ROBERTS-LETTER-001599, dated 09 February 2022. | OME | MEDIATECH
42 | VO-051.4 | Extension of consultant's site supervision services (Meinhardt) |  |  | ROBERTS-VR-000220 | 2022-01-14 | ROBERTS-VAR-000339 | 2022-01-17 | 108946.8 | 108946.8 |  |  |  | 2022-01-31 | Submitted and Under Review | Under OME review. | OME | MEINHARDT
43 | VO-051.5 | Extension of consultant's services (BG&E) |  |  | ROBERTS-VR-000226 | 2022-02-10 |  |  | 255000 | 255000 |  |  |  |  | Estimated | RPJV to submit the cost. | RPJV | BG&E
44 | VO-052 | Hotel Gym – 100% Detail Design | OMERED-LETTER-002041 | 2021-11-03 | ROBERTS-NOD-000115 | 2021-11-10 |  |  | 50000 | 50000 | OMERED-LETTER-002062 | 2021-11-14 |  |  | Estimated | Under Resubmission by RP Services. | RPJV | AHK Worldwide Interiors LLC
45 | VO-053 | Change in BGM System Volume Controller | OMERED-LETTER-002069 | 2021-11-15 | ROBERTS-VR-000205 | 2021-11-09 | ROBERTS-VAR-000318 | 2021-11-25 | 22401.78 | 22401.78 |  |  |  | 2021-12-09 | Submitted and Under Review | Under OME review. | OME | Creation Gulf Trading LLC
46 | VO-054 | Additional Telephone and Data Points in Hotel Level 2 Offices | Workflow Transmittal ref. BSBG-WTRAN-006794 | 2021-09-28 | ROBERTS-VR-000211, ROBERTS-LETTER-001538 | 30-Sep-2021, 11-Jan-2022 | ROBERTS-VAR-000329 | 2021-12-23 | 61832.32 | 61832.32 | OCI-LETTER-002148, OCI-LETTER-002211 | 05-Jan-2022, 26-Jan-2022 | 0 | Responded | Submitted and Rejected | 1. OME rejected. 2. RPJV to respond. | RPJV | SIS
47 | VO-055 | Additional Requirements for the FFE Equipment in Coffee Bar |  |  | ROBERTS-VR-000208 |  |  |  | 25000 | 25000 |  |  |  |  | Estimated | RPJV to submit the cost. | RPJV | FF&E
48 | VO-056 | Ball Room LV Panels Relocation | [6 empty] | 10000 | 10000 |  |  |  |  | Estimated | RPJV to submit the cost. | RPJV | MEP
49 | VO-057 | External BGM Speaker Type Change | [6 empty] | 50000 | 50000 |  |  |  |  | Estimated | RPJV to submit the cost. | RPJV | SIS
50 | VO-058 | Modification of Power Requirements in Landscape Area | OMERED-WTRAN-006784, OMERED-WTRAN-006785, OMERED-WTRAN-006788 | 2021-09-27 | ROBERTS-LETTER-001484 | 2021-11-24 | ROBERTS-VAR-000336 | 2022-01-07 | 246963.65 | 246963.65 |  |  |  |  | Submitted and Under Review | Under OME review. | OME | MEP
51 | VO-059 | Additional Scope of acoustics requirements to glass partion & screed works to receive floor finishes at Hotel Ballroom regions | OMERED-LETTER 001809 | 2021-07-15 | ROBERTS-VR-000210 | 2021-11-28 |  |  | 25000 | 25000 | OMERED-LETTER-002137 | 2021-12-16 |  |  | Estimated | 1. RPJV issued notification and OME rejected. 2. RPJV to respond. 3. RPJV to respond. | RPJV | AHK Worldwide Interiors LLC
52 | VO-059.1 | Screed to Ballroom Areas | OMERED-LETTER 001809 | 2021-07-15 | ROBERTS-VR-000210 | 2021-11-28 |  |  | 25000 | 25000 | OMERED-LETTER-002137 | 2021-12-16 |  |  | Estimated | RPJV to submit the cost. | RPJV | AHK Worldwide Interiors LLC
53 | VO-060 | BSBG Instruction to Proceed under Clause 8.1(b) with LOD for Retail Units | OMERED-LETTER-002070 | 2021-11-15 | ROBERTS-VR-000221 | 2022-01-25 | ROBERTS-VAR-000352 | 2022-02-01 | 86443 | 86443 |  |  |  |  | Submitted and Under Review | Under OME review. | RPJV | BSBG
54 | VO-060.1 | CEC Instruction to Proceed under Clause 8.1(b) with LOD for Retail Units | OMERED-LETTER-002070 | 2021-11-15 | ROBERTS-VR-000222 | 2022-01-26 | ROBERTS-VAR-000354 | 2022-02-01 | 209880 | 209880 |  |  |  |  | Submitted and Under Review | Under OME review. | OME | CEC
55 | VO-060.2 | BG&E Instruction to Proceed under Clause 8.1(b) with LOD for Retail Units | OMERED-LETTER-002070 | 2021-11-15 | ROBERTS-VR-000223 | 2022-01-31 | ROBERTS-VAR-000353 | 2022-02-01 | 39220 | 39220 |  |  |  |  | Submitted and Under Review | Under OME review. | OME | BG&E
56 | VO-061 | Welding of Top U Channels to Glassbalustrade | Workflow Transmittal ref. BSBG-WTRAN-015802 | 2021-06-20 | - | - | ROBERTS-VAR-000331 | 2021-12-23 | 636000 | 0 | OCI-LETTER-002236 | 2022-02-04 | 0 | Responded | Submitted and Rejected | 1. OME rejected this VO. 2. RPJV to respond. | RPJV | AL RAWAA
57 | VO-062 | Additional cost for Replacing Broken façade Glasses due to NiS inclusion |  |  |  |  | ROBERTS-VAR-000334 | 2021-12-27 | 180292.22 | 180292.22 | OCI-LETTER-002193 | 2022-01-19 | 0 |  | Submitted and Under Review | 1. OME requested additional informations. 2. RPJV to respond. | RPJV & RP Services | Glassline Aluminum LLC
58 | VO-062.1 | Additional cost for Replacing Broken façade Glasses due to NiS inclusion(Till 19th September 2021) |  |  |  |  | ROBERTS-VAR-000348 | 2022-01-28 | 54395.76 | 54395.76 |  |  |  |  | Submitted and Under Review | Under OME review. | OME | Glassline Aluminum LLC
59 | VO-063 | Modifications as per DEWA Comments on Load Schedules/Single Line Diagrams | [6 empty] | 100000 | 100000 |  |  |  |  | Estimated | RPJV to submit the cost. | RPJV | MEP
60 | VO-064 | Light Fixtures in Landscape and Podium Area | OMERED-LETTER-001644 | 2021-04-13 | - | - | OMERED-LETTER-001644, ROBERTS-LETTER-001601 | 27-Dec-2021, 10-Feb-2022 | 39169.12 | 39169.12 | OCI-GNC-002229 | 2022-01-26 |  | Responded | Submitted and Under Review | 1. OME responded with requirement of additional two Quotations and Quantity Calculations. 2. RPJV responded. 3. VO is under OME review. | OME | PROJECT SUPPLIES
61 | VO-065 | Basement 1 & 2 lift lobby doors change in specifications | OMERED-WTRAN-006136 | 2021-07-27 | - | - | ROBERTS-VAR-000335 | 2022-01-03 | 125550.64 | 125550.64 | OCI-LETTER-002196 | 2022-01-19 | 0 |  | Submitted and Under Review | 1. OME responded that RPJV to resubmit this Variation in consideration of comments provided in OMERED-GNC-001745, dated 20 January 2021. 2. RPJV to respond. | RPJV | AHK Worldwide Interiors LLC
62 | VO-066 | Cabana on Level 20 - Hotel | OMERED-LETTER-001613 | 2022-01-08 | - | - | ROBERTS-VAR-000337, ROBERTS-LETTER-001600 | 08-Jan-2022, 10-Feb-2022 | 424795 | 424795 | OCI-GNC-002236 | 2022-01-31 |  | Responded | Submitted and Under Review | 1. OME responded with requirement of additional two Quotations, Quantity Calculations and Markup drawings. 2. RPJV responded. 3. VO is under OME review. | OME | AHK Worldwide Interiors LLC |  | N
63 | VO-067 | Provisional Sum Adjustment - GRMS - 15A, 171 & 18A | OMERED-LETTER 000695 | 2019-10-01 | - | - | ROBERTS-VAR-000332 | 2021-12-27 | 76944.35 | 76944.35 | OCI-GNC-002235 | 2022-01-31 |  | Responded | Submitted and Under Review | 1. OME responded with requirement of Quantity Calculations and Markup drawings. 2. RPJV to respond. | RPJV | CREATION GULF |  | N
64 | VO-068 | Modification to Toilet & Shower Room in Hotel Level 29 | [6 empty] | 35000 | 35000 |  |  |  |  | Estimated | RPJV to submit the cost. | RPJV | AHK Worldwide Interiors LLC
65 | VO-069 | Additional DX Stand-by Unit in the UPS Room | MEP Meeting No. 38 |  | ROBERTS-VR-000219, ROBERTS-LETTER-001543 | 03-Jan-2022, 11-Jan-2022 | - | - | 10000 | 10000 | OCI-LETTER-002172, OCI-LETTER-002191 | 11-Jan-2022, 19-Jan-2022 | - | - | Estimated | 1. Notification issued and OME rejected. 2. RPJV to respond. | RPJV | MEP
66 | VO-070 | Additional Requirements for Sky Hooks in Ball Room | FM-EX-RFI-ML-002163 | 2021-10-27 | ROBERTS-VR-000218, ROBERTS-LETTER-001544 | 03-Jan-2022, 13-Jan-2022 | - | - | 10000 | 10000 | OCI-LETTER-002166, OCI-LETTER-002209 | 11-Jan-2022, 26-Jan-2022 | - | - | Estimated | 1. Notification issued and OME advised to submit the Variations. 2. RPJV to respond. | RPJV | AHK Worldwide Interiors LLC
67 | VO-071 | Additional Light Fixtures in Hotel Level 02 | [6 empty] | 5000 | 5000 |  |  |  |  | Estimated | RPJV to submit the cost. | RPJV | Bond Interior Design LLC
68 | VO-072 | Omission of the Hotel L17 and L29 External Areas BGM Installations | OMERED-LETTER-002132 | 2021-12-14 |  |  |  |  | -10000 | -10000 |  |  |  |  | Estimated | RPJV to submit the cost. | RPJV | SIS
69 | VO-073 | Panic Bar & Pull Handle to Facade Doors | OMERED-LETTER-000348 | 2018-10-11 | - | - | ROBERTS-VAR-000345 | 2022-01-25 | 850133.28 | 200000 |  |  |  |  | Submitted and Under Review | Under OME review. | OME | Glassline Aluminum LLC
70 | VO-074 | Level 28 Gym ADA Toilet - Fitout Works | OMERED-LETTER-002062 | 2021-11-14 | - | - | ROBERTS-VAR-000340 | 2022-01-19 | 256669.08 | 100000 | OCI-GNC-002237 | 2022-02-01 |  | Responded | Submitted and Under Review | 1. OME responded with requirement of Quantity Calculations, Quotations and Markup drawings. 2. RPJV to respond. | RPJV | Bond Interior Design LLC |  | N
71 | VO-075 | PS Adjustment - Hotel Guest Room Headboard Works | OMERED-LETTER-001776 | 2021-06-29 |  |  | ROBERTS-VAR-000341 | 2022-01-19 | 122756.48 | 115808 | OCI-LETTER-002246 | 2022-02-04 | 115808 | Responded | Submitted and Under Review | 1. OME instructed the VO amount and informed that RPJV not entitled for OH&P. 2. RPJV to respond. | OME |  |  | N
72 | VO-076 | Paver Changed from Cobble Granite to Black Absolute Granite | OMERED-LETTER-001613 | 2021-04-01 | - | - | ROBERTS-VAR-000349 | 2022-01-28 | 537750.02 | 403312.515 |  |  |  |  | Submitted and Under Review | Under OME review. | OME | Al Reem Marble & Granite LLC
73 | VO-077 | Increase in Area of Canopy at Hotel Tower | OMERED-GNC-001773 | 2021-02-10 |  |  | ROBERTS-VAR-000342 | 2022-01-21 | 146483.52 | 146483.52 |  |  |  |  | Submitted and Under Review | Under OME review. | OME | Glassline Aluminum LLC
74 | VO-078 | Lighting Cove Requirement Throughout the EIFS Region | Against Original contract drawings |  |  |  | ROBERTS-VAR-000343 | 2022-01-21 | 683707.8 | 341853.9 |  |  |  |  | Submitted and Under Review | Under OME review. | OME | Glassline Aluminum LLC
75 | VO-079 | Change in Hardware & Automatic sliding Glass Doors | OMERED-RTRFI-000091 | 2021-04-15 |  |  | ROBERTS-VAR-000350 | 2022-01-28 | 73458 | 73458 | OCI-LETTER-002244 | 2022-02-04 | 0 | Responded | Submitted and Rejected | 1. OME rejected and RPJV to respond. | RPJV | Glassline Aluminum LLC
77 | VO-081 | Change or introduction of canopy at L30 & L29 | OMERED-RTRFI-000340 & 000349 |  |  |  | ROBERTS-VAR-000347 | 2022-01-27 | 331540.44 | 0 |  |  |  |  | Submitted and Under Review | Under OME review. | OME | Glassline Aluminum LLC
82 | VO-086 | Extension of Lift CTU | OMERED-LETTER-000333 | 2018-10-03 |  |  | ROBERTS-VAR-000361 | 2022-02-10 | 230147.2 | 576000 |  |  |  |  | Submitted and Under Review | Under OME review. | OME | Kone Middle East LLC
83 | VO-087 | Additional Scope of Works for L2 & L28 | OMERED-LETTER-001169 | 2022-02-09 | - | - | ROBERTS-VAR-000359 | 2022-02-09 | 172135.34 | 108292.5482 |  |  |  |  | Submitted and Under Review | Under OME review. | OME | Bond Interior Design LLC |  | N
84 | VO-088 | Site Observation no. 075 - 27 January 2022 - Stone lift surround buttons | OCI-SIOBS-000075 | 2022-01-27 | ROBERTS-RTSO-000073 | 2022-02-01 |  |  | 27600 | 27600 | OCI-LETTER-002241 | 2022-02-04 | 0 | Responded | Estimated | 1. OME rejected based on the notification. 2. RPJV to respond. | RPJV | AHK Worldwide Interiors LLC
85 | VO-089 | Supply and Installation of Fire Rated Sliding Door at GF Lobby | OMERED-WTRAN-002435 | 2020-01-14 |  |  | ROBERTS-VAR-000362 | 2022-02-10 | 10785.5 | 10000 |  |  |  |  | Submitted and Under Review | Under OME review. | OME | AHK Worldwide Interiors LLC |  | N
87 | VO-091 | RC-ADD2-VO-091 - Additional Shutter Fold & Slide System for Ballroom Bar Cabinet | ROBERTS-VAR-000367 | [5 empty] | 5000 | 5000 | [7 empty] | AHK Worldwide Interiors LLC
|  | TOTAL | [6 empty] | 11378069.72 | 8987230.9941
Formulas:
Date to be Responded = [Date]+14