## IPC
PROJECT |  | DORCHESTER HOTEL AND RESIDENCES | [6 empty] | IPC-14
EMPLOYER |  | SKY PALACES REAL ESTATE DEVELOPMENT LLC
EMPLOYER'S REP |  | OMNIYAT CONCEPT INVESTMENTS LLC
ENGINEER |  | BREWER SMITH BREWER GROUP (BSBG)
MAIN CONTRACTOR |  | KHANSAHEB CIVIL ENGINEERING
FOR THE PERIOD ENDING |  | 2023-03-31
TEMPORARY MAINTENANCE WORKS (BLUE SKY) SUMMARY
Item | Description | Contract Amount (AED) | Progress Completion (%) |  |  | Work Done (AED) |  |  | Remarks
|  |  | Previous | This Month | Cumulative | Previous | This Month | Cumulative
BLUE SKY PROFORMA INVOICE REF.5731
A | Temporary Maintenance Manpower | 396000 | 109.4% | 10.68% | 120.1% | 433200 | 42300 | 475500
B | Additional material & works | 426097.549 | 100% | 0% | 100% | 426097.549 | 0 | 426097.549
| Total MEP Amount | 822097.549 |  |  |  | 859297.549 | 42300 | 901597.549

## Contract
TEMPORARY MAINTENANCE (BLUE SKY) | [9 empty] | MANPOWER
S.Nr | Month | Designation | Man power | No. of Days | Rate | Amount | Previous Amount (AED) | Current Amount (AED) | Cumulative Amount (AED) | Remarks
| April'22 | [5 empty] | 19200 | 0 | 19200
1 | April'22 | Supervisor | 1 | 20 | 230 | 4600 | 4600 | 0 | 4600 | Day Shift
2 | April'22 | Electrician | 3 | 20 | 150 | 9000 | 9000 | 0 | 9000 | Day Shift
3 | April'22 | Plumber | 1 | 20 | 150 | 3000 | 3000 | 0 | 3000 | Day Shift
4 | April'22 | Helper | 1 | 20 | 130 | 2600 | 2600 | 0 | 2600 | Day Shift
| May'22 | [5 empty] | 33300 | 0 | 33300
5 | May'22 | Supervisor | 1 | 30 | 230 | 6900 | 6900 | 0 | 6900 | Day Shift
6 | May'22 | Electrician | 3 | 30 | 150 | 13500 | 13500 | 0 | 13500 | Day Shift
7 | May'22 | Plumber | 2 | 30 | 150 | 9000 | 9000 | 0 | 9000 | Day Shift
8 | May'22 | Helper | 1 | 30 | 130 | 3900 | 3900 | 0 | 3900 | Day Shift
| June'22 | [5 empty] | 42300 | 0 | 42300
9 | June'22 | Supervisor | 1 | 30 | 230 | 6900 | 6900 | 0 | 6900 | Day Shift
10 | June'22 | Electrician | 3 | 30 | 150 | 13500 | 13500 | 0 | 13500 | Day Shift
11 | June'22 | Plumber | 2 | 30 | 150 | 9000 | 9000 | 0 | 9000 | Day Shift
12 | June'22 | Helper | 1 | 30 | 130 | 3900 | 3900 | 0 | 3900 | Day Shift
13 | June'22 | Electrician | 2 | 30 | 150 | 9000 | 9000 | 0 | 9000 | Night Shift
| July'22 | [5 empty] | 42300 | 0 | 42300
14 | July'22 | Supervisor | 1 | 30 | 230 | 6900 | 6900 | 0 | 6900 | Day Shift
15 | July'22 | Electrician | 3 | 30 | 150 | 13500 | 13500 | 0 | 13500 | Day Shift
16 | July'22 | Plumber | 2 | 30 | 150 | 9000 | 9000 | 0 | 9000 | Day Shift
17 | July'22 | Helper | 1 | 30 | 130 | 3900 | 3900 | 0 | 3900 | Day Shift
18 | July'22 | Electrician | 2 | 30 | 150 | 9000 | 9000 | 0 | 9000 | Night Shift
| Aug'22 | [5 empty] | 42300 | 0 | 42300
19 | Aug'22 | Supervisor | 1 | 30 | 230 | 6900 | 6900 | 0 | 6900 | Day Shift
20 | Aug'22 | Electrician | 3 | 30 | 150 | 13500 | 13500 | 0 | 13500 | Day Shift
21 | Aug'22 | Plumber | 2 | 30 | 150 | 9000 | 9000 | 0 | 9000 | Day Shift
22 | Aug'22 | Helper | 1 | 30 | 130 | 3900 | 3900 | 0 | 3900 | Day Shift
23 | Aug'22 | Electrician | 2 | 30 | 150 | 9000 | 9000 | 0 | 9000 | Night Shift
| Sep'22 | [5 empty] | 42300 | 0 | 42300
24 | Sep'22 | Supervisor | 1 | 30 | 230 | 6900 | 6900 | 0 | 6900 | Day Shift
25 | Sep'22 | Electrician | 3 | 30 | 150 | 13500 | 13500 | 0 | 13500 | Day Shift
26 | Sep'22 | Plumber | 2 | 30 | 150 | 9000 | 9000 | 0 | 9000 | Day Shift
27 | Sep'22 | Helper | 1 | 30 | 130 | 3900 | 3900 | 0 | 3900 | Day Shift
28 | Sep'22 | Electrician | 2 | 30 | 150 | 9000 | 9000 | 0 | 9000 | Night Shift
| Oct'22 | [5 empty] | 42300 | 0 | 42300
29 | Oct'22 | Supervisor | 1 | 30 | 230 | 6900 | 6900 | 0 | 6900 | Day Shift
30 | Oct'22 | Electrician | 3 | 30 | 150 | 13500 | 13500 | 0 | 13500 | Day Shift
31 | Oct'22 | Plumber | 2 | 30 | 150 | 9000 | 9000 | 0 | 9000 | Day Shift
32 | Oct'22 | Helper | 1 | 30 | 130 | 3900 | 3900 | 0 | 3900 | Day Shift
33 | Oct'22 | Electrician | 2 | 30 | 150 | 9000 | 9000 | 0 | 9000 | Night Shift
| Nov'22 | [5 empty] | 42300 | 0 | 42300
34 | Nov'22 | Supervisor | 1 | 30 | 230 | 6900 | 6900 | 0 | 6900 | Day Shift
35 | Nov'22 | Electrician | 3 | 30 | 150 | 13500 | 13500 | 0 | 13500 | Day Shift
36 | Nov'22 | Plumber | 2 | 30 | 150 | 9000 | 9000 | 0 | 9000 | Day Shift
37 | Nov'22 | Helper | 1 | 30 | 130 | 3900 | 3900 | 0 | 3900 | Day Shift
38 | Nov'22 | Electrician | 2 | 30 | 150 | 9000 | 9000 | 0 | 9000 | Night Shift
| Dec'22 | [5 empty] | 42300 | 0 | 42300
39 | Dec'22 | Supervisor | 1 | 30 | 230 | 6900 | 6900 | 0 | 6900 | Day Shift
40 | Dec'22 | Electrician | 3 | 30 | 150 | 13500 | 13500 | 0 | 13500 | Day Shift
41 | Dec'22 | Plumber | 2 | 30 | 150 | 9000 | 9000 | 0 | 9000 | Day Shift
42 | Dec'22 | Helper | 1 | 30 | 130 | 3900 | 3900 | 0 | 3900 | Day Shift
43 | Dec'22 | Electrician | 2 | 30 | 150 | 9000 | 9000 | 0 | 9000 | Night Shift
| Jan'23 | [5 empty] | 42300 | 0 | 42300
44 | Jan'23 | Supervisor | 1 | 30 | 230 | 6900 | 6900 | 0 | 6900 | Day Shift
45 | Jan'23 | Electrician | 3 | 30 | 150 | 13500 | 13500 | 0 | 13500 | Day Shift
46 | Jan'23 | Plumber | 2 | 30 | 150 | 9000 | 9000 | 0 | 9000 | Day Shift
47 | Jan'23 | Helper | 1 | 30 | 130 | 3900 | 3900 | 0 | 3900 | Day Shift
48 | Jan'23 | Electrician | 2 | 30 | 150 | 9000 | 9000 | 0 | 9000 | Night Shift
| Feb'23 | [5 empty] | 42300 | 0 | 42300
49 | Feb'23 | Supervisor | 1 | 28 | 230 | 6440 | 6900 | 0 | 6900 | Day Shift
50 | Feb'23 | Electrician | 3 | 28 | 150 | 12600 | 13500 | 0 | 13500 | Day Shift
51 | Feb'23 | Plumber | 2 | 28 | 150 | 8400 | 9000 | 0 | 9000 | Day Shift
52 | Feb'23 | Helper | 1 | 28 | 130 | 3640 | 3900 | 0 | 3900 | Day Shift
53 | Feb'23 | Electrician | 2 | 28 | 150 | 8400 | 9000 | 0 | 9000 | Night Shift
| Mar'23 | [5 empty] | 0 | 42300 | 42300
54 | Mar'23 | Supervisor | 1 | 28 | 230 | 6440 |  | 6900 | 6900 | Day Shift
55 | Mar'23 | Electrician | 3 | 28 | 150 | 12600 |  | 13500 | 13500 | Day Shift
56 | Mar'23 | Plumber | 2 | 28 | 150 | 8400 |  | 9000 | 9000 | Day Shift
57 | Mar'23 | Helper | 1 | 28 | 130 | 3640 |  | 3900 | 3900 | Day Shift
58 | Mar'23 | Electrician | 2 | 28 | 150 | 8400 |  | 9000 | 9000 | Night Shift
|  | TOTAL AMOUNT |  |  |  |  | 433200 | 42300 | 475500

## Additional
TEMPORARY MAINTENANCE (BLUE SKY) | [9 empty] | ADDITIONAL WORKS
S.Nr | Description | Month | Unit | Qty | Rate | Amount | Previous IPC (AED) | Current (AED) | Cumulative (AED) | Remarks
1 | KCE Office Temporary Maintenance - BS/Q/KCE/04/22/V01_April'22
Electrical Materials
| 600c600 LED Lights | April'22 | Nr | 31 | 55 | 1705 | 1705 | 0 | 1705
| 13A Twin Switch Socket Outlet | April'22 | Nr | 6 | 15 | 90 | 90 | 0 | 90
| PVC Trunking | April'22 | Lot | 1 | 47 | 47 | 47 | 0 | 47
Plumbing Materials
| Washbasin + Pedestal | April'22 | Nr | 2 | 120 | 240 | 240 | 0 | 240
| Washbasin mixture | April'22 | Nr | 2 | 75 | 150 | 150 | 0 | 150
| Western type WC | April'22 | Nr | 6 | 450 | 2700 | 2700 | 0 | 2700
| Urinal Pot | April'22 | Nr | 3 | 245 | 735 | 735 | 0 | 735
| Angle valve and Shattaf | April'22 | Lot | 1 | 294 | 294 | 294 | 0 | 294
| Hose, WC Connector, tape | April'22 | Lot | 1 | 272 | 272 | 272 | 0 | 272
| Manpower | April'22 | Lot | 1 |  | 0 | 0 | 0 | 0
| Electrician | April'22 | Hr | 40 | 15 | 600 | 600 | 0 | 600 | 2 Days 2 labour
| Electrician Helper | April'22 | Hr | 40 | 13 | 520 | 520 | 0 | 520 | 2 Days 2 labour
| Plumber | April'22 | Hr | 40 | 15 | 600 | 600 | 0 | 600 | 2 Days 2 labour
| Plumbing Helper | April'22 | Hr | 40 | 13 | 520 | 520 | 0 | 520 | 2 Days 2 labour
| OHP (10%) | April'22 | Lot | 1 | 875 | 875 | 623.3 | 0 | 623.3
| TOTAL AMOUNT |  |  |  |  | 9348 | 9096.3 | 0 | 9096.3
2 | Mess area and Toilet water supply and food storage AC works - BS/Q/KCE/04/22/V03_May'22
L2 Mess Area Water Supply
| 165 Gallon Water cooler with filter set | May'22 | Nr | 6 | 3500 | 21000 | 21000 | 0 | 21000
| Garden Tap, Angle valve and conn. hose | May'22 | Lot | 1 | 234 | 234 | 234 | 0 | 234
| HPVC Pipe with Elbow | May'22 | Lot | 1 | 27 | 27 | 27 | 0 | 27
| 1x18W LED Tube Rod | May'22 | Nr | 20 | 8 | 160 | 160 | 0 | 160
Food Storage AC Works
| Supply and installation of 2ton Split AC with copper piping and wiring | May'22 | Nr | 1 | 2850 | 2850 | 2850 | 0 | 2850
Hotel L17 Mess area & Level 18 Toilet area Water supply works
| 165 Gallon Water cooler with filter set | May'22 | Nr | 2 | 3500 | 7000 | 7000 | 0 | 7000
| Washbasin + Pedestrial | May'22 | Nr | 1 | 120 | 120 | 120 | 0 | 120
| Urinal | May'22 | Nr | 4 | 180 | 720 | 720 | 0 | 720
| Tap, Angle valve and Connection hose | May'22 | Lot | 1 | 156 | 156 | 156 | 0 | 156
| 1x18W LED Tube Rod | May'22 | Nr | 20 | 8 | 160 | 160 | 0 | 160
Food Storage AC Works
| Supply and installation of 2ton Split AC with copper piping and wiring | May'22 | Nr | 1 | 2850 | 2850 | 2850 | 0 | 2850
| Manpower | May'22 | Lot | 1 |  | 0 | 0 | 0 | 0
| Electrician | May'22 | Hr | 40 | 15 | 600 | 600 | 0 | 600 | 2 Days 2 labour
| Electrician Helper | May'22 | Hr | 40 | 13 | 520 | 520 | 0 | 520 | 2 Days 2 labour
| Plumber | May'22 | Hr | 40 | 15 | 600 | 600 | 0 | 600 | 2 Days 2 labour
| Plumbing Helper | May'22 | Hr | 40 | 13 | 520 | 520 | 0 | 520 | 2 Days 2 labour
| OHP (10%) | May'22 | Lot | 1 | 3767 | 3767 | 3527.7 | 0 | 3527.7
| TOTAL AMOUNT |  |  |  |  | 41284 | 41044.7 | 0 | 41044.7
3 | Foreman Office Power Supply Works - BS/Q/KCE/04/22/V06_May'22
Electrical Materials
| 63A Floor Distribution with Stand | May'22 | Nr | 1 | 1200 | 1200 | 1200 | 0 | 1200
| 4C x 16mm2 Cable | May'22 | m | 40 | 38.5 | 1540 | 1540 | 0 | 1540
| 20A Isolator | May'22 | Nr | 4 | 50 | 200 | 200 | 0 | 200
| 13A Twin Switch Socket Outlet | May'22 | Nr | 8 | 15 | 120 | 120 | 0 | 120
| 1x18W LED Light fittings | May'22 | Nr | 8 | 50 | 400 | 400 | 0 | 400
| Wiring for above | May'22 | Lot | 1 | 689 | 689 | 689 | 0 | 689
| Cable gland and PVC Trunking | May'22 | Lot | 1 | 73 | 73 | 73 | 0 | 73
KCE Office Works
| 6" Exhaust Fan | May'22 | Nr | 5 | 20 | 100 | 100 | 0 | 100
| Manpower | May'22 | Lot | 1 |  | 0 | 0 | 0 | 0
| Electrician | May'22 | Hr | 60 | 15 | 900 | 900 | 0 | 900 | 2 Days 3 labour
| Material buy back amount | May'22 | Lot | 1 | -822 | -822 | -822 | 0 | -822
| OHP (10%) | May'22 | Lot | 1 | 522 | 522 | 350 | 0 | 350
| TOTAL AMOUNT |  |  |  |  | 4922 | 4750 | 0 | 4750
4 | Mirage Office Sanitary ware replacement works - BS/Q/KCE/04/22/V07_May'22
Plumbing Materials
| Western type WC | May'22 | Nr | 5 | 450 | 2250 | 2250 | 0 | 2250
| Kitchen Sink with Mixture | May'22 | Nr | 1 | 160 | 160 | 160 | 0 | 160
| Tissue Holder (Big) | May'22 | Nr | 3 | 58 | 174 | 174 | 0 | 174
| Tissue Holder (Small) | May'22 | Nr | 5 | 40 | 200 | 200 | 0 | 200
| Hose, WC Connector, tape | May'22 | Lot | 1 | 119 | 119 | 119 | 0 | 119
| Manpower | May'22 | Lot | 1 |  | 0 | 0 | 0 | 0
| Electrician | May'22 | Hr | 60 | 15 | 900 | 900 | 0 | 900 | 3 Days 2 labour
| OHP (10%) | May'22 | Lot | 1 | 380 | 380 | 290.3 | 0 | 290.3
| TOTAL AMOUNT |  |  |  |  | 4183 | 4093.3 | 0 | 4093.3
5 | Derrick Crane Power supply - BS/Q/KCE/04/22/V08_May'22
Electrical Materials
| 200A Tower Crane Panel with Earth leakage protection | May'22 | Nr | 1 | 2650 | 2650 | 2650 | 0 | 2650
| 4Cx95mm2 Armoured Cable | May'22 | m | 100 | 180 | 18000 | 18000 | 0 | 18000
| Cable gland, Cable lug, tie and insulation tape | May'22 | Lot | 1 | 109 | 109 | 109 | 0 | 109
| Manpower | May'22 | Lot | 1 |  | 0 | 0 | 0 | 0
| Electrician | May'22 | Hr | 60 | 15 | 900 | 900 | 0 | 900 | 2 Days 3 labour
| Electrician Helper | May'22 | Hr | 60 | 13 | 780 | 780 | 0 | 780 | 2 Days 3 labour
| Material buy back amount | May'22 | Lot | 1 | -6195 | -6195 | -6195 | 0 | -6195
| OHP (10%) | May'22 | Lot | 1 | 2243 | 2243 | 1456.4 | 0 | 1456.4
| TOTAL AMOUNT |  |  |  |  | 18487 | 17700.4 | 0 | 17700.4
6 | Installation of Additional New Light fittings - BS/Q/KCE/04/22/V09_June'22
Electrical Materials
| 1x18W LED Tube Light fittings | June'22 | Nr | 180 | 50 | 9000 | 9000 | 0 | 9000
| 1x200W LED Flood Light fittings | June'22 | Nr | 80 | 220 | 17600 | 17600 | 0 | 17600
| 1x18W LED Tube Rod | June'22 | Nr | 275 | 8.75 | 2406.25 | 2406.25 | 0 | 2406.25
| Wiring Accessories for the above | June'22 | Lot | 1 | 12600 | 12600 | 12600 | 0 | 12600
| Male & Female Industrial Socket, Cable tie, insulation tape and other accessories | June'22 | Lot | 1 | 1652.5 | 1652.5 | 1652.5 | 0 | 1652.5
| Manpower | June'22 | Lot |  |  | 0 | 0 | 0 | 0
| OHP (10%) | June'22 | Lot | 1 | 4325.875 | 4325.875 | 4325.875 | 0 | 4325.875
| TOTAL AMOUNT |  |  |  |  | 47584.625 | 47584.625 | 0 | 47584.625
7 | Additional Manpower Requirement - BS/Q/KCE/04/22/V10_June'22
Manpower Details
Removal and Replacement of Light fittings and fixing hanging cables
| Electrician (6nr x 1month) | June'22 | Hr | 180 | 150 | 27000 | 27000 | 0 | 27000
| Helper (4nr x 1month) | June'22 | Hr | 120 | 130 | 15600 | 15600 | 0 | 15600
DB Dressing and testing in all Levels
| Electrician (2nr x 1month) | June'22 | Hr | 60 | 150 | 9000 | 9000 | 0 | 9000
| Helper (2nr x 1month) | June'22 | Hr | 60 | 130 | 7800 | 7800 | 0 | 7800
FHR Maintenance work in all Levels
| Plumber (2nr x 10 days) | June'22 | Hr | 20 | 150 | 3000 | 3000 | 0 | 3000
| Helper (2nr x 10 days) | June'22 | Hr | 20 | 130 | 2600 | 2600 | 0 | 2600
Electrical Material details
| Wire coil, Male & Female Industrial Socket | June'22 | Lot | 1 | 1104.15 | 1104.15 | 1104.15 | 0 | 1104.15
Plumbing Material details
| Hanging Clamp, Threaded Rod, Nut, Washer and Unifix | June'22 | Lot | 1 | 919.5 | 919.5 | 919.5 | 0 | 919.5
| Manpower | June'22 | Lot |  |  | 0 | 0 | 0 | 0
| OHP (10%) | June'22 | Lot | 1 | 6702.365 | 6702.365 | 6702.365 | 0 | 6702.365
| TOTAL AMOUNT |  |  |  |  | 73726.015 | 73726.015 | 0 | 73726.015
8 | New Labour Toilet at Gate No.1 - BS/Q/KCE/04/22/V11_June'22
Plumbing Materials
| 2" UPVC Pipe with accessories | June'22 | Lot | 1 | 571.1 | 571.1 | 571.1 | 0 | 571.1
| 4" UPVC Tee, Elbow, Floor Trap, Vent cowl, UPVC Reducer Push | June'22 | Lot | 1 | 1255 | 1255 | 1255 | 0 | 1255
| CP Hex nipple, Flexible Hose, WC Connector, Glue and Lubricant | June'22 | Lot | 1 | 377 | 377 | 377 | 0 | 377
Electrical Materials
| 3Cx 6mm2 and 3C 4mm2 Cable | June'22 | Lot | 1 | 1163 | 1163 | 1163 | 0 | 1163
| Manpower | June'22 | Lot | 1 |  | 0 | 0 | 0 | 0
| Electrician | June'22 | Hr | 10 | 15 | 150 | 150 | 0 | 150 | 1 Day 1 labour
| Plumber | June'22 | Hr | 30 | 15 | 450 | 450 | 0 | 450 | 3 Days 1 labour
| Plumbing Helper | June'22 | Hr | 30 | 13 | 390 | 390 | 0 | 390 | 3 Days 1 labour
| Material buy back amount | June'22 | Lot |  |  | 0 | 0 | 0 | 0
| OHP (10%) | June'22 | Lot | 1 | 435.61 | 435.61 | 336.61 | 0 | 336.61
| TOTAL AMOUNT |  |  |  |  | 4791.71 | 4692.71 | 0 | 4692.71
9 | L2 Client Office AC Drain works - BS/Q/KCE/04/22/V13_July'22
Plumbing Materials
| 1" HPVC Pipe with accessories | July'22 | Lot | 1 | 734 | 734 | 734 | 0 | 734
| 3/4" HPVC Pipe with accessories | July'22 | Lot | 1 | 387.5 | 387.5 | 387.5 | 0 | 387.5
| Fisher, unifix, nut, washer , glue and insulation tape | July'22 | Lot | 1 | 106.5 | 106.5 | 106.5 | 0 | 106.5
| Manpower | July'22 | Lot | 1 | 0 |  | 0 | 0 | 0
| OHP (10%) | July'22 | Lot | 1 | 122 | 122 | 122 | 0 | 122
| TOTAL AMOUNT |  |  |  |  | 1350 | 1350 | 0 | 1350
10 | L2 New Mess/ Rest area, Canteen Power supply, AC Drain - BS/Q/KCE/04/22/V14_July'22
Mess and Rest area Power Supply works
| SMDB with Stand, 125A | July'22 | Nr | 1 | 2850 | 2850 | 2850 | 0 | 2850
| DB with Stand, 80A | July'22 | Nr | 2 | 3900 | 7800 | 7800 | 0 | 7800
| 4Cx 50mm2 Armoured Cable + Earth Cable | July'22 | m | 45 | 88 | 3960 | 3960 | 0 | 3960
| 4Cx 16mm2 Armoured Cable + Earth Cable | July'22 | m | 80 | 38.5 | 3080 | 3080 | 0 | 3080
| Cable Gland, lug and insulation tape for above | July'22 | Lot | 1 | 76.8 | 76.8 | 76.8 | 0 | 76.8
| 200W/ 220V LED Light fittings | July'22 | Nr | 15 | 220 | 3300 | 3300 | 0 | 3300
| MCCB, 125A | July'22 | Nr | 1 | 360 | 360 | 360 | 0 | 360
| 32A Isolator | July'22 | Nr | 16 | 65 | 1040 | 1040 | 0 | 1040
| Wiring and accessories for above | July'22 | Lot | 1 | 5645 | 5645 | 5645 | 0 | 5645
| Femal, male socket, PVC Gland and Junctiuon Box | July'22 | Lot | 1 | 558.5 | 558.5 | 558.5 | 0 | 558.5
| Cable ties, Fishers, Hook and accessories | July'22 | Lot | 1 | 237.7 | 237.7 | 237.7 | 0 | 237.7
Canteen Power Supply works
| DB, 40A | July'22 | Nr | 1 | 1200 | 1200 | 1200 | 0 | 1200
| 4Cx 10mm2 Armoured Cable + Earth Cable | July'22 | m | 60 | 27.5 | 1650 | 1650 | 0 | 1650
| 15A Socket with Back box | July'22 | Nr | 2 | 12 | 24 | 24 | 0 | 24
| 13A Twin Socket with Back box | July'22 | Nr | 5 | 15 | 75 | 75 | 0 | 75
| 10A Switch outlet with Back box | July'22 | Nr | 2 | 7 | 14 | 14 | 0 | 14
| 1x18W LED Light fittings | July'22 | Nr | 7 | 50 | 350 | 350 | 0 | 350
| PVC Trunking and accessories | July'22 | Lot | 1 | 32 | 32 | 32 | 0 | 32
AC Drain Pipe works
| 1" HPVC Pipe | July'22 | Lot | 1 | 734 | 734 | 734 | 0 | 734
| Threaded rod, Nut and Wahser, Glue | July'22 | Lot | 1 | 66 | 66 | 66 | 0 | 66
| Manpower | July'22 | Lot | 1 | 0 | 0 | 0 | 0 | 0
| Material buy back amount | July'22 | Lot | 1 | -6162 | -6162 | -6162 | 0 | -6162
| OHP (10%) | July'22 | Lot | 1 | 3305 | 3305 | 2689.1 | 0 | 2689.1
| TOTAL AMOUNT |  |  |  |  | 30196 | 29580.1 | 0 | 29580.1
11 | Power Supply for GF Glass line office - BS/Q/KCE/04/22/V15_July'22
Electrical Materials
| DB, 40A | July'22 | Nr | 1 | 1200 | 1200 | 1200 | 0 | 1200
| 4Cx 16mm2 Armoured Cable + Earth Cable | July'22 | m | 80 | 38.5 | 3080 | 3080 | 0 | 3080
| 1x18W LED Light fittings | July'22 | Nr | 10 | 50 | 500 | 500 | 0 | 500
| 32A Isolator | July'22 | Nr | 2 | 65 | 130 | 130 | 0 | 130
| 13A Twin Socket with Back box | July'22 | Nr | 5 | 15 | 75 | 75 | 0 | 75
| 10A Switch outlet with Back box | July'22 | Nr | 2 | 7 | 14 | 14 | 0 | 14
| Wiring and accessories for above | July'22 | Lot | 1 | 870 | 870 | 870 | 0 | 870
| Cable Gland, Tie, Hook, Chain and Fisher | July'22 | Lot | 1 | 79 | 79 | 79 | 0 | 79
| Manpower | July'22 | Lot | 1 | 0 | 0 | 0 | 0 | 0
| Material buy back amount | July'22 | Lot | 1 | -1284 | -1284 | -1284 | 0 | -1284
| OHP (10%) | July'22 | Lot | 1 | 594 | 594 | 466.4 | 0 | 466.4
| TOTAL AMOUNT |  |  |  |  | 5258 | 5130.4 | 0 | 5130.4
12 | 110V Transformer - BS/Q/KCE/04/22/V16_July'22
Electrical Materials
| 7.5KvA/ 6 Outlet, 110V Transformer | July'22 | Nr | 10 | 3100 | 31000 | 31000 | 0 | 31000
| 4Cx 6mm2 Armoured Cable + Earth Cable | July'22 | m | 84 | 15 | 1260 | 1260 | 0 | 1260
| Cable Gland, Lug, Tie and Insulation tape | July'22 | Lot | 1 | 151 | 151 | 151 | 0 | 151
| Manpower | July'22 | Lot | 1 | 0 | 0 | 0 | 0 | 0
| Material buy back amount | July'22 | Lot | 1 | -9678 | -9678 | -9678 | 0 | -9678
| OHP (10%) | July'22 | Lot | 1 | 3241 | 3241 | 2273.3 | 0 | 2273.3
| TOTAL AMOUNT |  |  |  |  | 25974 | 25006.3 | 0 | 25006.3
13 | Power Socket for Basement Offices - BS/Q/KCE/04/22/V18_July'22
Electrical Materials
| 13A Twin Socket with Back box | July'22 | Nr | 35 | 15 | 525 | 525 | 0 | 525
| Wiring and accessories for above | July'22 | Lot | 1 | 1125 | 1125 | 1125 | 0 | 1125
| PVC Gland, Fisher, Hook, Cable Tie and insulation tape | July'22 | Lot | 1 | 196 | 196 | 196 | 0 | 196
| Manpower | July'22 | Lot | 1 | 0 | 0 | 0 | 0 | 0
| Material buy back amount | July'22 | Lot |  |  | 0 | 0 | 0 | 0
| OHP (10%) | July'22 | Lot | 1 | 184 | 184 | 184 | 0 | 184
| TOTAL AMOUNT |  |  |  |  | 2030 | 2030 | 0 | 2030
14 | Monthly Maintenance Materials - BS/Q/KCE/04/22/V05_July'22
Electrical Materials
| 1x18W LED Tube Rod | July'22 | Nr | 39 | 8.7436 | 341 | 341 | 0 | 341
| 1x18W LED Light fittings | July'22 | Nr | 4 | 50 | 200 | 200 | 0 | 200
| 16A SP MCB | July'22 | Nr | 2 | 16 | 32 | 32 | 0 | 32
| 20A SP MCB | July'22 | Nr | 2 | 93 | 186 | 186 | 0 | 186
| ELCB, 3P, 30mA, 40A | July'22 | Nr | 1 | 145 | 145 | 145 | 0 | 145
| ELCB, 3P, 30mA, 100A | July'22 | Nr | 1 | 150 | 150 | 150 | 0 | 150
| 220V, 16A Male Industrial Plug | July'22 | Nr | 4 | 4.95 | 19.8 | 19.8 | 0 | 19.8
| 220V, 16A Female Ind. Socket | July'22 | Nr | 4 | 3.75 | 15 | 15 | 0 | 15
| 380V, 32A Male Ind. Plug | July'22 | Nr | 1 | 14.75 | 14.75 | 14.75 | 0 | 14.75
| 380V, 32A Female Ind. Socket | July'22 | Nr | 1 | 16.95 | 16.95 | 16.95 | 0 | 16.95
| 3Cx2.5mm2 Flexible wire coil | July'22 | Rolls | 2 | 315 | 630 | 630 | 0 | 630
| Insulation Tape | July'22 | Nr | 15 | 1.1 | 16.5 | 16.5 | 0 | 16.5
| Cable Tie | July'22 | Nr | 20 | 6.75 | 135 | 135 | 0 | 135
Plumbing Materials
| 1" LDPE Pipe | July'22 | m | 30 | 4.4 | 132 | 132 | 0 | 132
| 1" LDPE M/ Adaptor | July'22 | Nr | 3 | 13.2 | 39.6 | 39.6 | 0 | 39.6
| 1" LDPE Socket | July'22 | Nr | 3 | 7.6 | 22.8 | 22.8 | 0 | 22.8
| 1" Ball Valve | July'22 | Nr | 3 | 33 | 99 | 99 | 0 | 99
| 2" LDPE Socket | July'22 | Nr | 2 | 30.95 | 61.9 | 61.9 | 0 | 61.9
| 1" GI Hanging Clamp | July'22 | Nr | 10 | 1.1 | 11 | 11 | 0 | 11
| 4" UPVC Pipe | July'22 | Length | 1 | 63 | 63 | 63 | 0 | 63
| Booster Pump Bladder | July'22 | Nr | 1 | 825 | 825 | 825 | 0 | 825
| Filter Candle | July'22 | Nr | 40 | 7.43 | 297.2 | 297.2 | 0 | 297.2
| Teflon Tape | July'22 | Nr | 5 | 1.1 | 5.5 | 5.5 | 0 | 5.5
| TOTAL AMOUNT |  |  |  |  | 3459 | 3459 | 0 | 3459
15 | Labour Toilet Refurbishment Works - BS/Q/KCE/05/22/V05_July'22
Electrical Materials
| 36W/220V Tube Rod | Aug'22 | Nr | 10 | 2.5 | 25 | 25 | 0 | 25
| 6" Exhaust Fan | Aug'22 | Nr | 5 | 20 | 100 | 100 | 0 | 100
Plumbing Materials
| Western Type WC | Aug'22 | m | 9 | 450 | 4050 | 4050 | 0 | 4050
| Hand Spray | Aug'22 | Nr | 9 | 30 | 270 | 270 | 0 | 270
| Urinal Push tap | Aug'22 | Nr | 3 | 260 | 780 | 780 | 0 | 780
| Angle valve, hose, BTp and WC connec | Aug'22 | Lot | 1 | 567 | 567 | 567 | 0 | 567
| 1" PPR Pipe | Aug'22 | Nr | 12 | 565 | 565 | 565 | 0 | 565
| PPR Elbow, Tee, Socket and Clamp | Aug'22 | Lot | 1
| 3/4" PPR Pipe | Aug'22 | Length | 12 | 377 | 377 | 377 | 0 | 377
| PPR Elbow, Tee, Socket and Clamp | Aug'22 | Lot | 1
| Teflon Tape | Aug'22 | Lot | 1 | 51 | 51 | 51 | 0 | 51
| Manpower | Aug'22 | Lot | 1 | 0 | 0 | 0 | 0 | 0
| Electrician | Aug'22 | Hr | 20 | 15 | 300 | 300 | 0 | 300 | 2 Days 1 labour
| Plumber | Aug'22 | Hr | 120 | 15 | 1800 | 1800 | 0 | 1800 | 3 Days 4 labour
| Material buy back amount | Aug'22 | Lot |  |  | 0 | 0 | 0 | 0
| OHP (10%) | Aug'22 | Lot | 1 | 678.5 | 678.5 | 678.5 | 0 | 678.5
| TOTAL AMOUNT |  |  |  |  | 9563.5 | 9563.5 | 0 | 9563.5
16 | Power Supply works on L3 & B1 Subcontractor offices - BS/Q/KCE/07/22/V17_Aug'22
Electrical Materials
L3:-
| 13A Twin Socket with Back box | Aug'22 | Nr | 8 | 15 | 120 | 120 | 0 | 120
| Wiring of A/C and power socket outlet | Aug'22 | Lot | 1 | 495 | 495 | 495 | 0 | 495
| Cable Gland, Tie, Hook, Chain and Fisher | Aug'22 | Lot | 1 | 120.4 | 120.4 | 120.4 | 0 | 120.4
B1:-
| 1x18W LED Light fittings | Aug'22 | Nr | 10 | 50 | 500 | 500 | 0 | 500
| Wiring of A/C, Cooler and Lights | Aug'22 | Lot | 1 | 1168 | 1168 | 1168 | 0 | 1168
| Fisher, screw, cable tie and tapes | Aug'22 | Lot | 1 | 66.4 | 66.4 | 66.4 | 0 | 66.4
| Material buy back amount | Aug'22 | Lot |  |  | 0 | 0 | 0 | 0
| OHP (10%) | Aug'22 | Lot | 1 | 246.98 | 246.98 | 246.98 | 0 | 246.98
| TOTAL AMOUNT |  |  |  |  | 2716.78 | 2716.78 | 0 | 2716.78
17 | B2, GF KCE office, L2 FM office A/C, Lighting and power works - BS/Q/KCE/07/22/V19_Aug'22
Electrical Materials
B2:-
| 32A Isolator | Aug'22 | Nr | 2 | 65 | 130 | 130 | 0 | 130
| Wiring of above | Aug'22 | Lot | 1 | 180 | 180 | 180 | 0 | 180
| Gypsum screw, fisher, tie and tapes | Aug'22 | Lot | 1 | 16.75 | 16.75 | 16.75 | 0 | 16.75
GF:-
| 32A Isolator | Aug'22 | Nr | 1 | 65 | 65 | 65 | 0 | 65
| Wiring of above | Aug'22 | Lot | 1 | 90 | 90 | 90 | 0 | 90
| Gypsum screw, fisher, tie and tapes | Aug'22 | Lot | 1 | 13.4 | 13.4 | 13.4 | 0 | 13.4
L2:-
| 13A Twin Socket with Back box | Aug'22 | Nr | 13 | 15 | 195 | 195 | 0 | 195
| 1x18W LED Light fittings | Aug'22 | Lot | 8 | 50 | 400 | 400 | 0 | 400
| 32A Isolator | Aug'22 | Nr | 4 | 65 | 260 | 260 | 0 | 260
| Wiring of above | Aug'22 | Lot | 1 | 870 | 870 | 870 | 0 | 870
| Gypsum screw, fisher, tie and tapes | Aug'22 | Lot | 1 | 35.75 | 35.75 | 35.75 | 0 | 35.75
| Material buy back amount | Aug'22 | Lot |  |  | 0 | 0 | 0 | 0
| OHP (10%) | Aug'22 | Lot | 1 | 225.59 | 225.59 | 225.59 | 0 | 225.59
| TOTAL AMOUNT |  |  |  |  | 2481.49 | 2481.49 | 0 | 2481.49
18 | L2 Relocation of Hand wash and drinking station at labour area - BS/Q/KCE/07/22/V20_Aug'22
Plumbing Materials
| 4" UPVC Pipe | Aug'22 | m | 12 | 272.5 | 272.5 | 272.5 | 0 | 272.5
| Bends, Cap, P-trap and grating | Aug'22 | Lot | 1 |  |  | 0 | 0 | 0
| 1" PPR Pipe | Aug'22 | m | 16 | 498 | 498 | 498 | 0 | 498
| PPE Socket, Adaptor, Elbow, Cap, Clamp and etc., | Aug'22 | Lot | 1 |  |  | 0 | 0 | 0
| 2" UPVC Pipe | Aug'22 | Nr | 10 | 117.6 | 117.6 | 117.6 | 0 | 117.6
| Tee, Elbow and clip | Aug'22 | Nr | 1 |  |  | 0 | 0 | 0
| Nut, Wahser and Lubricant | Aug'22 | Length | 1 | 120 | 120 | 120 | 0 | 120
| Material buy back amount | Aug'22 | Lot |  |  | 0 | 0 | 0 | 0
| OHP (10%) | Aug'22 | Lot | 1 | 100.81 | 100.81 | 100.81 | 0 | 100.81
| TOTAL AMOUNT |  |  |  |  | 1108.91 | 1108.91 | 0 | 1108.91
19 | Booster pump relocation and Tank replacement from L17-L18 - BS/Q/KCE/08/22/V21_Aug'22
Plumbing Materials
| 500 Gallon Water tank | Aug'22 | Nr | 1 | 600 | 600 | 600 | 0 | 600
| 1" GI Pipe | Aug'22 | m | 24 | 795.34 | 795.34 | 795.34 | 0 | 795.34
| Elbow, 45, Tee, Socket, Reducer, Nipple, Union and Plug | Aug'22 | Lot | 1 |  |  | 0 | 0 | 0
| 1" GI Ball valve | Aug'22 | Nr | 4 | 33 | 132 | 132 | 0 | 132
| Rod, nut, Washer, Clamp and tapes | Aug'22 | Lot | 1 | 187.02 | 187.02 | 187.02 | 0 | 187.02
| Material buy back amount | Aug'22 | Lot |  |  | 0 | 0 | 0 | 0
| OHP (10%) | Aug'22 | Lot | 1 | 171.436 | 171.436 | 171.436 | 0 | 171.436
| TOTAL AMOUNT |  |  |  |  | 1885.796 | 1885.796 | 0 | 1885.796
20 | Labour welfare area relocation from L17 to B1 - BS/Q/KCE/08/22/V22_Aug'22
Plumbing Materials
| 4" UPVC Pipe | Aug'22 | m | 12 | 272.5 | 272.5 | 272.5 | 0 | 272.5
| Bends, Cap, P-trap and grating | Aug'22 | Lot | 1
| 1" PPR Pipe | Aug'22 | m | 16 | 498 | 498 | 498 | 0 | 498
| PPE Socket, Adaptor, Elbow, Cap, Clamp and etc., | Aug'22 | Lot | 1 |  |  | 0 | 0 | 0
| 1" GI Ball valve | Aug'22 | Nr | 3 | 33 | 99 | 99 | 0 | 99
| Rod, nut, Washer, PVC cement and Lubricant | Aug'22 | Lot | 1 | 107.46 | 107.46 | 107.46 | 0 | 107.46
| Material buy back amount | Aug'22 | Lot |  |  | 0 | 0 | 0 | 0
| OHP (10%) | Aug'22 | Lot | 1 | 97.696 | 97.696 | 97.696 | 0 | 97.696
| TOTAL AMOUNT |  |  |  |  | 1074.656 | 1074.656 | 0 | 1074.656
21 | Temporary Power supply for Lift 17 & 18 in L28 Hotel - BS/Q/KCE/08/22/V24_Sep'22
Electrical Materials
| 63A TPN Isolator panel with 300mA ELCB protection | Sep'22 | Nr | 2 | 1200 | 2400 | 2400 | 0 | 2400
| 4C 16mm2 Armoured + Earth cable | Sep'22 | m | 80 |  |  | 0 | 0 | 0
| Cable gland, lug and insulation tapes | Sep'22 | Lot | 1 | 55.75 | 55.75 | 55.75 | 0 | 55.75
| Material buy back amount | Sep'22 | Lot | 1 | -720 | -720 | -720 | 0 | -720
| OHP (10%) | Sep'22 | Lot | 1 | 245.575 | 245.575 | 245.575 | 0 | 245.575
| TOTAL AMOUNT |  |  |  |  | 1981.325 | 1981.325 | 0 | 1981.325
22 | Temporary Water supply for Male and Female Toilets in B1 - BS/Q/KCE/08/22/V25_Sep'22
Plumbing Materials
| 1" LDPE Pipe | Sep'22 | m | 50 | 351.5 | 351.5 | 351.5 | 0 | 351.5
| Adaptors, Hex Nipple, GI clamp | Sep'22 | Lot | 1
| 1" GI Ball valve | Sep'22 | Nr | 4 | 33 | 132 | 132 | 0 | 132
| 1" PRV | Sep'22 | m | 1 | 124 | 124 | 124 | 0 | 124
| Material buy back amount | Sep'22 | Lot |  |  | 0 | 0 | 0 | 0
| OHP (10%) | Sep'22 | Lot | 1 | 60.75 | 60.75 | 60.75 | 0 | 60.75
| TOTAL AMOUNT |  |  |  |  | 668.25 | 668.25 | 0 | 668.25
23 | Temporary power supply for lift no.13 in Hotel Ball Room - BS/Q/KCE/09/22/V27_Oct'22
Electrical Materials
| 63A Isolator | Oct'22 | Nr | 1 | 1200 | 1200 | 1200 | 0 | 1200
| 4C 16mm2 Armoured Cable | Oct'22 | m | 25 | 38.5 | 962.5 | 962.5 | 0 | 962.5
| Cable gland, lugs, ite, insulation tape | Oct'22 | Lot | 1 | 33.25 | 33.25 | 33.25 | 0 | 33.25
| Material buy back amount | Oct'22 | Lot | 1 | -648 | -648 | -648 | 0 | -648
| OHP (10%) | Oct'22 | Lot | 1 | 219.575 | 219.575 | 219.575 | 0 | 219.575
| TOTAL AMOUNT |  |  |  |  | 1767.325 | 1767.325 | 0 | 1767.325
24 | Temporary power supply for cradle in L7 Hotel - BS/Q/KCE/09/22/V28_Oct'22
Electrical Materials
| 63A Isolator | Oct'22 | Nr | 1 | 1200 | 1200 | 1200 | 0 | 1200
| 4C 16mm2 Armoured Cable | Oct'22 | m | 40 | 38.5 | 1540 | 1540 | 0 | 1540
| Cable gland, lugs, ite, insulation tape | Oct'22 | Lot | 1 | 38.05 | 38.05 | 38.05 | 0 | 38.05
| Material buy back amount | Oct'22 | Lot | 1 | -822 | -822 | -822 | 0 | -822
| OHP (10%) | Oct'22 | Lot | 1 | 277.805 | 277.805 | 277.805 | 0 | 277.805
| TOTAL AMOUNT |  |  |  |  | 2233.855 | 2233.855 | 0 | 2233.855
25 | Emergency light and detector in B2 & B1 Ofice area - BS/Q/KCE/10/22/V29_Oct'22
Electrical Materials
| Emergeny Exit light - Supply + Install | Oct'22 | Nr | 30 | 50 | 1500 | 1500 | 0 | 1500
| Smoke Detector - Supply + Install | Oct'22 | m | 22 | 45 | 990 | 990 | 0 | 990
| Wiring for above | Oct'22 | Lot | 1 | 1575 | 1575 | 1575 | 0 | 1575
| PVC Connector, Cable tie and insulation tape | Oct'22 | Lot | 1 | 53.9 | 53.9 | 53.9 | 0 | 53.9
| Material buy back amount | Oct'22 | Lot | 1 | 0 | 0 | 0 | 0 | 0
| OHP (10%) | Oct'22 | Lot | 1 | 411.89 | 411.89 | 411.89 | 0 | 411.89
| TOTAL AMOUNT |  |  |  |  | 4530.79 | 4530.79 | 0 | 4530.79
26 | Wall cutting machine power supply at Hotel Level-29 - BS/Q/KCE/09/22/V33_Oct'22
Electrical Materials
| 63A Isolator | Oct'22 | Nr | 2 | 1200 | 2400 | 2400 | 0 | 2400
| 4C 16mm2 Armoured Cable | Oct'22 | m | 160 | 38.5 | 6160 | 6160 | 0 | 6160
| Cable gland, lugs, ite, insulation tape | Oct'22 | Lot | 1 | 63.5 | 63.5 | 63.5 | 0 | 63.5
| Material buy back amount | Oct'22 | Lot | 1 | -2568 | -2568 | -2568 | 0 | -2568
| OHP (10%) | Oct'22 | Lot | 1 | 862.35 | 862.35 | 862.35 | 0 | 862.35
| TOTAL AMOUNT |  |  |  |  | 6917.85 | 6917.85 | 0 | 6917.85
27 | Electrical and Plumbing works for proposed Labour Toilet at B1- BS/Q/KCE/10/22/V34_Nov'22
Electrical Materials
| 40A SP Distribution Panel | Nov'22 | Nr | 1 | 750 | 750 | 750 | 0 | 750
| 3C x 10mm2 Amoured Cable | Nov'22 | m | 50 | 14 | 700 | 700 | 0 | 700
| 1 x 18W LED Tube Light Fittings | Nov'22 | Nr | 24 | 50 | 1200 | 1200 | 0 | 1200
| 1 x 8W Exit Light Fittings with Battery Back-up | Nov'22 | Nr | 4 | 50 | 200 | 200 | 0 | 200
| 6" Exhaust Fan | Nov'22 | Nr | 20 | 20 | 400 | 400 | 0 | 400
| 1G Switch with back box | Nov'22 | Nr | 4 | 7 | 28 | 28 | 0 | 28
| Wiring for the above | Nov'22 | Lot | 1 | 1260 | 1260 | 1260 | 0 | 1260
| Cable Gland, Lug, Tie and Insulation Tape | Nov'22 | Lot | 1 | 44.7 | 44.7 | 44.7 | 0 | 44.7
| Butterfly fisher, Screw, Clip | Nov'22 | Lot | 1 | 60 | 60 | 60 | 0 | 60
Drainage Materials
| 4" UPVC Pipe | Nov'22 | m | 100 |  | 0 | 0 | 0 | 0
| 4" UPVC Tee, Elbow, Socket, Y, Access Cap, | Nov'22 | Lot | 1 | 2938.75 | 2938.75 | 2938.75 | 0 | 2938.75
| 4" UPVC P Trap,Floor Trap, Reducer Bushes | Nov'22 | Lot | 1 | 948 | 948 | 948 | 0 | 948
| 3" UPVC Pipe | Nov'22 | m | 20 |  | 0 | 0 | 0 | 0
| 3" UPVC Socket,WC Coonector | Nov'22 | Lot | 1 | 366 | 366 | 366 | 0 | 366
| 2" UPVC Pipe | Nov'22 | m | 70 |  | 0 | 0 | 0 | 0
| 2" UPVC Elbow, Socket, Y, Access Cap, 45 | Nov'22 | Lot | 1 | 1130 | 1130 | 1130 | 0 | 1130
| 4", 2", 1" G.I Hanging Clamp | Nov'22 | Lot | 1 | 608 | 608 | 608 | 0 | 608
| 4", 2", 1" G.I U Clip | Nov'22 | Lot | 1 | 157.5 | 157.5 | 157.5 | 0 | 157.5
| WC Asian Tpe including High level Flushing Tank | Nov'22 | Nr | 14 | 195 | 2730 | 2730 | 0 | 2730
| Wash Basin + Pedestrial | Nov'22 | Nr | 10 | 120 | 1200 | 1200 | 0 | 1200
| Wash Basin Mixture | Nov'22 | Nr | 10 | 75 | 750 | 750 | 0 | 750
| Wash Basin Bottle Trap,Waste Cup | Nov'22 | Nr | 10 | 22 | 220 | 220 | 0 | 220
| Urinals including Fittings | Nov'22 | Nr | 19 | 260 | 4940 | 4940 | 0 | 4940
| Shattaff and Connection Hose | Nov'22 | Lot | 1 | 525 | 525 | 525 | 0 | 525
| Angle Valve | Nov'22 | Nr | 50 | 12 | 600 | 600 | 0 | 600
| 4" G.I Grating | Nov'22 | Nr | 8 | 58 | 464 | 464 | 0 | 464
| Threaded Rod, Nut, Washer, Silicon White, Unifix | Nov'22 | Lot | 1 | 358.4 | 358.4 | 358.4 | 0 | 358.4
| Connector, Screw and Fisher | Nov'22 | Lot | 1 | 296 | 296 | 296 | 0 | 296
Water Supply Materials
| 1" PPR Pipe | Nov'22 | m | 80 |  | 0 | 0 | 0 | 0
| PPR Elbow, Socket, Tee, End Cap, Clip, Male & Female Adaptor, Female Tee, Female Elbow | Nov'22 | Lot | 1 | 1846.75 | 1846.75 | 1846.75 | 0 | 1846.75
| 1" Ball Valve | Nov'22 | Nr | 5 | 33 | 165 | 165 | 0 | 165
| 1" LDPE Pipe | Nov'22 | m | 100 |  | 0 | 0 | 0 | 0
| LDPE Male, Female Adaptor, Tee, Socket | Nov'22 | Lot | 1 | 738.15 | 738.15 | 738.15 | 0 | 738.15
| Taflon Tape, PVC Cement, Lubricant, Shellac | Nov'22 | Lot | 1 | 429 | 429 | 429 | 0 | 429
Tank and Pump Material Details
| Submersible Pump with Control Panel(Duty+Stand By) | Nov'22 | Set | 1 | 9500 | 9500 | 9500 | 0 | 9500
| 2000 Gallon GRP Septic Tank | Nov'22 | Nr | 1 | 2800 | 2800 | 2800 | 0 | 2800
| 2" NRV | Nov'22 | Nr | 2 | 170 | 340 | 340 | 0 | 340
| 2" Gate Valve | Nov'22 | Nr | 3 | 118 | 354 | 354 | 0 | 354
| Float Switch | Nov'22 | Nr | 3 | 230 | 690 | 690 | 0 | 690
| 2" G.I Pipe | Nov'22 | m | 10 |  | 0 | 0 | 0 | 0
| G.I Tee, Union, Elbow, Hex Nipple | Nov'22 | Lot | 1 | 449.58 | 449.58 | 449.58 | 0 | 449.58
| 2" LDPE Pipe | Nov'22 | m | 100 |  | 0 | 0 | 0 | 0
| LDPE Male, Female Adaptor, Socket | Nov'22 | Nr | 1 | 1652 | 1652 | 1652 | 0 | 1652
| Booster Pump(Duty+Stand By) | Nov'22 | Set | 1 | 4500 | 4500 | 4500 | 0 | 4500
| 2000 Gallon GRP Water Tank | Nov'22 | Nr | 1 | 2400 | 2400 | 2400 | 0 | 2400
| 2" Gate Valve | Nov'22 | Nr | 3 | 118 | 354 | 354 | 0 | 354
| 2" Stainer | Nov'22 | Nr | 1 | 285 | 285 | 285 | 0 | 285
| Float Switch | Nov'22 | Nr | 1 | 230 | 230 | 230 | 0 | 230
| 1" Ball Valve | Nov'22 | Nr | 5 | 33 | 165 | 165 | 0 | 165
| G.I Union, G.I Tee, Hex Nipple, G.I Reducer Bush | Nov'22 | Lot | 1 | 146.88 | 146.88 | 146.88 | 0 | 146.88
Electrical Manpower Details
| Electrician | Nov'22 | Hr | 60 | 15 | 900 |  | 0
| Helper | Nov'22 | Hr | 60 | 13 | 780 |  | 0
Plumbing Manpower Details
| Plumber | Nov'22 | Hr | 240 | 15 | 3600 |  | 0
| Helper | Nov'22 | Hr | 240 | 13 | 3120 |  | 0
| Material buy back amount | Nov'22 | Lot | 1 | -2505 | -2505 | -2505 | 0 | -2505
| OHP (10%) | Nov'22 | Lot | 1 | 4991.97 | 4991.97 | 4991.97 | 0 | 4991.97
| TOTAL AMOUNT |  |  |  |  | 60806.68 | 52406.68 | 0 | 52406.68
28 | Temporary Drainage Line Extension Work - BS/Q/KCE/10/22/V35_Nov'22
Materials
| 2" LDPE Pipe | Nov'22 | m | 100 | 13.75 | 1375 | 1375 | 0 | 1375
| LDPE Socket and Taflon Tape | Nov'22 | Lot | 1 | 153.8 | 153.8 | 153.8 | 0 | 153.8
| Material buy back amount | Nov'22 | Lot | 1 |  | 0 | 0 | 0 | 0
| OHP (10%) | Nov'22 | Lot | 1 | 152.88 | 152.88 | 152.88 | 0 | 152.88
| TOTAL AMOUNT |  |  |  |  | 1681.68 | 1681.68 | 0 | 1681.68
29 | B1 & B2 AC Power Supply for Offices - BS/Q/KCE/10/22/V36_Nov'22
Electrical Materials
| 63A DB with Timer Control | Nov'22 | Nr | 2 | 2500 | 5000 | 5000 | 0 | 5000
| 40A DB with Timer Control | Nov'22 | Nr | 1 | 2000 | 2000 | 2000 | 0 | 2000
| 32A Isolator | Nov'22 | Nr | 17 | 65 | 1105 | 1105 | 0 | 1105
| 4cx16mm² Armoured +Earth Cable | Nov'22 | m | 180 | 38.5 | 6930 | 6930 | 0 | 6930
| 4cx10mm² Armoured +Earth Cable | Nov'22 | m | 50 | 27.5 | 1375 | 1375 | 0 | 1375
| Wiring for the Isolator | Nov'22 | Lot | 1 | 1875 | 1875 | 1875 | 0 | 1875
| Cable Gland, Cable Lug, Adaptor, Tie, Insulation Tape | Nov'22 | Lot | 1 | 125.7 | 125.7 | 125.7 | 0 | 125.7
| Material buy back amount | Nov'22 | Lot | 1 | -4923 | -4923 | -4923 | 0 | -4923
| OHP (10%) | Nov'22 | Lot | 1 | 1841.07 | 1841.07 | 1841.07 | 0 | 1841.07
| TOTAL AMOUNT |  |  |  |  | 15328.77 | 15328.77 | 0 | 15328.77
30 | Water provision for irrigation tank - BS/Q/KCE/12/22/V38_Jan'23
| 2" LDPE Pipe | Jan'23 | m | 50 | 13.75 | 687.5 | 687.5 | 0 | 687.5
| LDPE Socket and Taflon Tape | Jan'23 | Lot | 1 | 92.5 | 92.5 | 92.5 | 0 | 92.5
| 2" Gate Valve | Jan'23 | Nr | 1 | 118 | 118 | 118 | 0 | 118
| Material buy back amount | Jan'23 | Lot | 1 |  | 0 | 0 | 0 | 0
| OHP (10%) | Jan'23 | Lot | 1 | 89.8 | 89.8 | 89.8 | 0 | 89.8
| TOTAL AMOUNT |  |  |  |  | 987.8 | 987.8 | 0 | 987.8
31 | New Labor toilet and rest area - BS/Q/KCE/12/22/V39_Jan'23
Electrical Materials
| 40A SP Distribution Panel | Jan'23 | Nr | 1 | 750 | 750 | 750 | 0 | 750
| 4C x 10mm2 Amoured Cable | Jan'23 | m | 60 | 27.5 | 1650 | 1650 | 0 | 1650
| 3C x 10mm2 Amoured Cable | Jan'23 | m | 30 | 14 | 420 | 420 | 0 | 420
| 1 x 18W LED Tube Light Fittings | Jan'23 | Nr | 30 | 50 | 1500 | 1500 | 0 | 1500
| 1 x 8W Exit Light Fittings with Battery Back-up | Jan'23 | Nr | 8 | 50 | 400 | 400 | 0 | 400
| 6" Exhaust Fan | Jan'23 | Nr | 22 | 20 | 440 | 440 | 0 | 440
| 1G Switch with back box | Jan'23 | Nr | 4 | 7 | 28 | 28 | 0 | 28
| Wiring for the above | Jan'23 | Lot | 1 | 1575 | 1575 | 1575 | 0 | 1575
| Cable Gland, Lug, Tie and Insulation Tape | Jan'23 | Lot | 1 | 248.3 | 248.3 | 248.3 | 0 | 248.3
| Butterfly fisher, Screw, Clip | Jan'23 | Lot | 1 | 80 | 80 | 80 | 0 | 80
Drainage Materials
| 4" UPVC Pipe | Jan'23 | m | 100 |  | 0 | 0 | 0 | 0
| 4" UPVC Tee, Elbow, Socket, Y, Access Cap, | Jan'23 | Lot | 1 | 3305 | 3305 | 3305 | 0 | 3305
| 4" UPVC P Trap,Floor Trap, Reducer Bushes | Jan'23 | Lot | 1 | 1175.5 | 1175.5 | 1175.5 | 0 | 1175.5
| 3" UPVC Pipe | Jan'23 | m | 20 |  | 0 | 0 | 0 | 0
| 3" UPVC Socket,WC Coonector | Jan'23 | Lot | 1 | 89.5 | 89.5 | 89.5 | 0 | 89.5
| 2" UPVC Pipe | Jan'23 | m | 70 |  | 0 | 0 | 0 | 0
| 2" UPVC Elbow, Socket, Y, Access Cap, 45 | Jan'23 | Lot | 1 | 1868.5 | 1868.5 | 1868.5 | 0 | 1868.5
| 4", 2", 1" G.I Hanging Clamp | Jan'23 | Lot | 1 | 705 | 705 | 705 | 0 | 705
| 4", 2", 1" G.I U Clip | Jan'23 | Lot | 1 | 130 | 130 | 130 | 0 | 130
| WC Asian Tpe including High level Flushing Tank | Jan'23 | Nr | 18 | 195 | 3510 | 3510 | 0 | 3510
| Wash Basin + Pedestrial | Jan'23 | Nr | 17 | 120 | 2040 | 2040 | 0 | 2040
| Wash Basin Mixture | Jan'23 | Nr | 17 | 75 | 1275 | 1275 | 0 | 1275
| Wash Basin Bottle Trap,Waste Cup | Jan'23 | Nr | 18 | 22 | 396 | 396 | 0 | 396
| Urinals including Fittings | Jan'23 | Nr | 30 | 260 | 7800 | 7800 | 0 | 7800
| Shattaff and Connection Hose | Jan'23 | Lot | 1 | 900 | 900 | 900 | 0 | 900
| Angle Valve | Jan'23 | Nr | 60 | 12 | 720 | 720 | 0 | 720
| 4" G.I Grating | Jan'23 | Nr | 9 | 58 | 522 | 522 | 0 | 522
| Threaded Rod, Nut, Washer, Silicon White, Unifix | Jan'23 | Lot | 1 | 440 | 440 | 440 | 0 | 440
| Connector, Screw and Fisher | Jan'23 | Lot | 1 | 177 | 177 | 177 | 0 | 177
Water Supply Materials
| 1" PPR Pipe | Jan'23 | m | 100 |  | 0 | 0 | 0 | 0
| PPR Elbow, Socket, Tee, End Cap, Clip, Male & Female Adaptor, Female Tee, Female Elbow | Jan'23 | Lot | 1 | 2366 | 2366 | 2366 | 0 | 2366
| 1" Ball Valve | Jan'23 | Nr | 15 | 33 | 495 | 495 | 0 | 495
| 1" LDPE Pipe | Jan'23 | m | 100 |  | 0 | 0 | 0 | 0
| 1" GI Hex Nipple, Tee & Elbow | Jan'23 | Lot | 1 | 120.18 | 120.18 | 120.18 | 0 | 120.18
| LDPE Male, Female Adaptor, Tee, Socket | Jan'23 | Lot | 1 | 755.75 | 755.75 | 755.75 | 0 | 755.75
| Taflon Tape, PVC Cement, Lubricant, Shellac | Jan'23 | Lot | 1 | 475 | 475 | 475 | 0 | 475
Tank and Pump Material Details
| Submersible Pump with Control Panel(Duty+Stand By) | Jan'23 | Set | 1 |  | 0 | 0 | 0 | 0
| 2000 Gallon GRP Septic Tank | Jan'23 | Nr | 1 |  | 0 | 0 | 0 | 0
| 2" NRV | Jan'23 | Nr | 2 | 170 | 340 | 340 | 0 | 340
| 2" Gate Valve | Jan'23 | Nr | 5 | 118 | 590 | 590 | 0 | 590
| Float Switch | Jan'23 | Nr | 4 | 230 | 920 | 920 | 0 | 920
| 2" G.I Pipe | Jan'23 | m | 12 |  | 0 | 0 | 0 | 0
| G.I Tee, Union, Elbow, Hex Nipple | Jan'23 | Lot | 1 | 444.72 | 444.72 | 444.72 | 0 | 444.72
| 2" LDPE Pipe | Jan'23 | m | 100 |  | 0 | 0 | 0 | 0
| LDPE Male, Female Adaptor, Socket | Jan'23 | Nr | 1 | 1116 | 1116 | 1116 | 0 | 1116
| Booster Pump(Duty+Stand By) | Jan'23 | Set | 1 |  | 0 | 0 | 0 | 0
| 2000 Gallon GRP Water Tank | Jan'23 | Nr | 1 | 2400 | 2400 | 2400 | 0 | 2400
| 2" Gate Valve | Jan'23 | Nr | 3 | 118 | 354 | 354 | 0 | 354
| 2" Stainer | Jan'23 | Nr | 1 | 285 | 285 | 285 | 0 | 285
| Float Switch | Jan'23 | Nr | 1 | 230 | 230 | 230 | 0 | 230
| 1" Ball Valve | Jan'23 | Nr | 4 | 33 | 132 | 132 | 0 | 132
| G.I Union, G.I Tee, Hex Nipple, G.I Reducer Bush | Jan'23 | Lot | 1 | 180.35 | 180.35 | 180.35 | 0 | 180.35
| Jute and Shellac | Jan'23 | Nr | 1 | 61.21 | 61.21 | 61.21 | 0 | 61.21
| Material buy back amount | Jan'23 | Lot | 1 | -1566 | -1566 | -1566 | 0 | -1566
| OHP (10%) | Jan'23 | Lot | 1 | 4341 | 4341 | 4341.001 | 0 | 4341.001
| TOTAL AMOUNT |  |  |  |  | 46185.01 | 46185.011 | 0 | 46185.011
32 | L3 Client office temporary water supply - BS/Q/KCE/12/23/V42_Jan'23
| 1" LDPE Pipe | Jan'23 | m | 50
| 1" GI Hex Nipple, Tee & Elbow | Jan'23 | Lot | 1 | 337.16 | 337.16 | 337.16 | 0 | 337.16
| 1" Ball valve | Jan'23 | Nr | 1 | 33 | 33 | 33 | 0 | 33
| 1" PRV | Jan'23 | Nr | 1 | 124 | 124 | 124 | 0 | 124
| Shattaf | Jan'23 | Nr | 1 | 15 | 15 | 15 | 0 | 15
| Threaded rod, Nut and Wahser, Glue | Jan'23 | Lot | 1 | 62.36 | 62.36 | 62.36 | 0 | 62.36
| Material buy back amount | Jan'23 | Lot | 1 |  | 0 | 0 | 0 | 0
| OHP (10%) | Jan'23 | Lot | 1 | 57.152 | 57.152 | 57.152 | 0 | 57.152
| TOTAL AMOUNT |  |  |  |  | 628.672 | 628.672 | 0 | 628.672
33 | Plumbing re-routing works from B2 to L2 near lift lobby - BS/Q/KCE/02/23/V45_Feb'23
L2 to GF
| 4" UPVC Pipe | Feb'23 | m | 30 |  | Included | Included |  | Included
| 4" UPVC Tee, Elbow, Socket, Y, Access Cap, | Feb'23 | Lot | 1 | 664.5 | 664.5 | 664.5 | 0 | 664.5
| 1" LDPE Pipe | Feb'23 | m | 100 |  | Included | Included |  | Included
| LDPE Socket, PPR End cap | Feb'23 | Lot | 1 | 450.1 | 450.1 | 450.1 | 0 | 450.1
| Unifix, threaded rod, nut and wahser, Taflon Tape and PVC Cement | Feb'23 | Lot | 1 | 123.8 | 123.8 | 123.8 | 0 | 123.8
B2 to B1
| 4" UPVC Pipe | Feb'23 | m | 4 |  | Included | Included |  | Included
| 4" UPVC Tee, Elbow, Socket, Y, Access Cap, | Feb'23 | Lot | 1 | 179.25 | 179.25 | 179.25 | 0 | 179.25
| Material buy back amount | Feb'23 | Lot |  |  | 0 | 0 | 0 | 0
| OHP (10%) | Feb'23 | Lot | 1 | 141.77 | 141.77 | 141.765 | 0 | 141.765
| TOTAL AMOUNT |  |  |  |  | 1559.42 | 1559.415 | 0 | 1559.415
34 | Removal and relocation works at B1 hand wash area - BS/Q/KCE/02/23/V46_Feb'23
Water Supply Materials
| 1" PPR Pipe | Feb'23 | m | 20 |  | Included | Included |  | Included
| PPR Elbow, Socket, Tee, End Cap, Clip, Male & Female Adaptor, Female Tee, Female Elbow | Feb'23 | Lot | 1 | 503.7 | 503.7 | 503.7 | 0 | 503.7
| Angle valve and garden tape | Feb'23 | Lot | 1 | 264 | 264 | 264 | 0 | 264
| 4" GI Steel grating | Feb'23 | Nr | 1 | 58 | 58 | 58 | 0 | 58
| 1" Ball Valve | Feb'23 | Nr | 2 | 33 | 66 | 66 | 0 | 66
| LDPE Male, Female Adaptor, Tee, Socket | Feb'23 | Lot | 1 | 71.2 | 71.2 | 71.2 | 0 | 71.2
| Unifix, threaded rod, nut and wahser, Taflon Tape and PVC Cement | Feb'23 | Lot | 1 | 78.14 | 78.14 | 78.14 | 0 | 78.14
| Material buy back amount | Feb'23 | Lot | 1 |  | 0
| OHP (10%) | Feb'23 | Lot | 1 | 104.104 | 104.104 | 104.104 | 0 | 104.104
| TOTAL AMOUNT |  |  |  |  | 1145.144 | 1145.144 | 0 | 1145.144
| Month | Previous | Current | Cumulative
| April'22 | 9096.3 | 0 | 9096.3
| May'22 | 67588.4 | 0 | 67588.4
| June'22 | 126003.35 | 0 | 126003.35
| July'22 | 66555.8 | 0 | 66555.8
| Aug'22 | 18831.132 | 0 | 18831.132
| Sep'22 | 2649.575 | 0 | 2649.575
| Oct'22 | 15449.82 | 0 | 15449.82
| Nov'22 | 69417.13 | 0 | 69417.13
| Jan'23 | 47801.483 | 0 | 47801.483
| Feb'23 | 2704.559 | 0 | 2704.559
| TOTAL | 426097.549 | 0 | 426097.549