## SUMMARY
Cumulative Certificate Summary |  |  |  |  | Certificate Amount for
ITEM NO | DESCRIPTION | KCE Certificate ( January ) | Cumulative Claim | Claim Amount for FEB | Work Done for December | Certified (Cumulative)
1 | SCAFFOLDING WORK AS PER CONTRACT NO 201A22002/20 | 353366.5533 | 364896.0509 | 11529.4975 | 6979.6778 | 360346.2312
2 | Miscellaneous Scaffoldings | 1826062.6721 | 2000408.0996 | 174345.4274 | 170609.3024 | 1996671.9746
3 | Manpower - scaffolder | 476768 | 551520 | 74752 | 74752 | 551520
4 | Manpower - Foreman | 6500 | 6500 | 0 | 0 | 6500
5 | Inspection scaffolding with scaftag - max 500m3/tag | 18150 | 18150 | 0 | 0 | 18150
6 | HIRE CHARGES FOR SCFFOLD MATERIAL | 24307.18 | 25722.3549 | 1415.1749 | 1415.1749 | 25722.3549
7 | THIRD PARTY CERTIFICATE 2ND FLOOR BIRDCAGE SCAFFOLD | 28000 | 29600 | 1600 | 1600 | 29600
8 | RE - Inspection scaffolding with scaftag - max 500m3/tag | 27800 | 27800 | 0 | 0 | 27800
9 | Sale Material Tube & Coupler End Cap | 450 | 450 | 0 | 0 | 450
| Deductions |  |  | 0
| Client's Materials usage | -29000 | -29000 | 0 | -3500 | -32500
0
| Client's Materials ( Hire ) |  |  | 0
| TOTAL AMOUNT | 2732404.4054 | 2996046.5053 | 263642.0998 | 251856.1551 | 2984260.5606
| VAT AMOUNT 5% | 136620.2203 | 149802.3253 | 13182.105 | 12592.8078 | 149213.028
| GRAND TOTAL | 2869024.6257 | 3145848.8305 | 276824.2048 | 264448.9629 | 3133473.5886
|  |  | KCE Claim | 2808527.48 | 134602.08 | 2943129.56
|  |  | Difference | -76123.0746 | 117254.0751 | 41131.0006
Note on G15: Himal Kosala: Due to the fact that no new scaffoldings were built using KCE material, only 3500 will be deduct

## Sc Shedule
Customer Name: |  |  | Khansaheb Civil Engineering L.L.C
Site |  |  | DORCHESTER HOTEL | [7 empty] | Supporting are attached |  | Text Color | Input Data is correct |  |  |  | Problematic items (please refer the comment)
Quote Reference: | [10 empty] | No supporting | [12 empty] | 2.45 | 3.5
Contract No: |  |  | 201A22002/20
As Of |  | 2023-02-28
Billing Reference | number | Tag No. | HOC | OHC | Ref | Section of Work | Description | Section | Scaffold Type | Length | Width | Height | Handrail | Measure H | Board Lift | Re-measure | Quantity | Unit of Measure | Hire Status | HOC Date | OHC Date | Percent Dismantle | Hire Charge After WEEKS | Weeks On Hire | E&D Rate per unit | Hire Rate per wk | Labour Cost | Weekly hire charge | Erect Cost | Dismantle Cost | Hire Cost | Total Cost | Previous Billed | Net Payment | Remarks
| 1 |  | 12095 | 7598 |  | Basement 1 Residence Pump Room | Access Scaffold |  | INDEPENDENT | 2.5 | 1.3 | 6 | 1 | 5 |  |  | 12.5 | m2-LxH | OFF HIRED | 2022-05-20 | 2022-07-04 | 100% |  | 6.5714 | 14 |  | 175 | 0 | 122.5 | 52.5 | 0 | 175 | 175 | 0
| 1 |  | 12093 | 7569 |  | Basement -1 Residence | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 6 | 1 | 5 |  |  | 25 | m2-LxH | OFF HIRED | 2022-05-22 | 2022-06-06 | 100% |  | 2.2857 | 14 |  | 350 | 0 | 245 | 105 | 0 | 350 | 350 | 0
| 1 |  | 12097 | 7569 |  | Basment 2 Hotel Ramp Area | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 5 | 1 | 4 |  |  | 20 | m2-LxH | OFF HIRED | 2022-05-22 | 2022-06-06 | 100% |  | 2.2857 | 14 |  | 280 | 0 | 196 | 84 | 0 | 280 | 280 | 0
| 1 |  | 12098 | 7552 |  | Basment 1ramp Hotel | Access Scaffold |  | INDEPENDENT | 2.5 | 1.3 | 6 | 1 | 5 |  |  | 12.5 | m2-LxH | OFF HIRED | 2022-05-23 | 2022-05-28 | 100% |  | 0.85714 | 14 |  | 175 | 0 | 122.5 | 52.5 | 0 | 175 | 175 | 0
| 1 |  | 12096 | 7553 |  | Basement -1 Hotel | Access Scaffold |  | INDEPENDENT | 2.5 | 1.3 | 3 | 1 | 2 |  |  | 5 | m2-LxH | OFF HIRED | 2022-05-23 | 2022-05-31 | 100% |  | 1.2857 | 14 |  | 70 | 0 | 49 | 21 | 0 | 70 | 70 | 0
| 1 |  | 12094 | 7569 |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 4 | 1 | 3 |  |  | 12 | m2-LxH | OFF HIRED | 2022-05-23 | 2022-06-06 | 100% |  | 2.1429 | 14 |  | 168 | 0 | 117.6 | 50.4 | 0 | 168 | 168 | 0
| 1 |  | 12099 | 7551 |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 1.8 | 1.3 | 5 | 1 | 4 |  |  | 7.2 | m2-LxH | OFF HIRED | 2022-05-23 | 2022-05-30 | 100% |  | 1.1429 | 14 |  | 100.8 | 0 | 70.56 | 30.24 | 0 | 100.8 | 100.8 | 0
| 1 |  | 12101 | 7551 |  | Basment 1 Hotel | Access Scaffold |  | INDEPENDENT | 2.5 | 1.3 | 4 | 1 | 3 |  |  | 7.5 | m2-LxH | OFF HIRED | 2022-05-27 | 2022-05-30 | 100% |  | 0.57143 | 14 |  | 105 | 0 | 73.5 | 31.5 | 0 | 105 | 105 | 0
| 1 |  | 12102 | 7569 |  | Basment1 Ramp Area Residence | Access Scaffold |  | INDEPENDENT | 2.5 | 1.3 | 4 | 1 | 3 |  |  | 7.5 | m2-LxH | OFF HIRED | 2022-05-27 | 2022-06-06 | 100% |  | 1.5714 | 14 |  | 105 | 0 | 73.5 | 31.5 | 0 | 105 | 105 | 0
| 1 |  | 12120 | 7554 |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 17.5 | 1.3 | 5 | 1 | 4 |  |  | 70 | m2-LxH | OFF HIRED | 2022-05-29 | 2022-06-01 | 100% |  | 0.57143 | 14 |  | 980 | 0 | 686 | 294 | 0 | 980 | 980 | 0
| 1 |  | 12131 | 7557 |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 16 | 1.3 | 4 | 1 | 3 |  |  | 48 | m2-LxH | OFF HIRED | 2022-05-30 | 2022-06-08 | 100% |  | 1.4286 | 14 |  | 672 | 0 | 470.4 | 201.6 | 0 | 672 | 672 | 0
| 1 |  | 12105 | 7551 |  | Basement 1 Ramp Residence | Access Scaffold |  | INDEPENDENT | 2.5 | 1.8 | 4 | 1 | 3 |  |  | 7.5 | m2-LxH | OFF HIRED | 2022-05-27 | 2022-05-30 | 100% |  | 0.57143 | 18 |  | 135 | 0 | 94.5 | 40.5 | 0 | 135 | 135 | 0
| 1 |  | 12103 | 7572 |  | Basment 1 pump room Residence | Birdcage Scaffold |  | Birdcage | 13 | 5 | 6 | 1 | 5 |  |  | 325 | m3 | OFF HIRED | 2022-05-27 | 2022-06-15 | 100% |  | 2.8571 | 7.5 |  | 2437.5 | 0 | 1706.25 | 731.25 | 0 | 2437.5 | 2437.5 | 0
| 1 |  | 12104 | 7598 |  | Basment 1 pump room Residence | Birdcage Scaffold |  | Birdcage | 5 | 2.5 | 4 | 1 | 3 |  |  | 37.5 | m3 | OFF HIRED | 2022-05-27 | 2022-07-04 | 100% |  | 5.5714 | 7.5 |  | 281.25 | 0 | 196.875 | 84.375 | 0 | 281.25 | 281.25 | 0
| 1 |  | 12121 | 7598 |  | Basment 1 pump room Residence | Birdcage Scaffold |  | Birdcage | 3.8 | 2.5 | 3 | 1 | 2 |  |  | 19 | m3 | OFF HIRED | 2022-05-29 | 2022-07-04 | 100% |  | 5.2857 | 7.5 |  | 142.5 | 0 | 99.75 | 42.75 | 0 | 142.5 | 142.5 | 0
| 1 | 258 | 12372 | 7711 |  | Basement 1 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-06-16 | 2022-07-14 | 100% |  | 4.1429 | 135 | 12.25 | 540 | 49 | 378 | 162 | 203 | 743 | 743 | 0
| 1 | 257 | 12371 | 7705 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-06-16 | 2022-07-07 | 100% |  | 3.1429 | 135 | 12.25 | 540 | 49 | 378 | 162 | 154 | 694 | 694 | 0
| 1 | 257 | 12371 | 7705 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 4 | 1.3 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-06-16 | 2022-07-07 | 100% |  | 3.1429 | 135 | 12.25 | 540 | 49 | 378 | 162 | 154 | 694 | 694 | 0
| 1 | 260 | 12374 | 7578 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 2.5 | 6 | 1 | 5 |  |  | 5 | rm | OFF HIRED | 2022-06-16 | 2022-06-22 | 100% |  | 1 | 135 | 12.25 | 675 | 61.25 | 472.5 | 202.5 | 61.25 | 736.25 | 736.25 | 0
| 1 | 273 | 12387 | 6732 |  | Basment 1 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 6 | 1 | 5 |  |  | 5 | rm | OFF HIRED | 2022-06-17 | 2022-09-28 | 100% |  | 14.8571 | 135 | 12.25 | 675 | 61.25 | 472.5 | 202.5 | 910 | 1585 | 1585 | 0
| 1 | 286 | 12394 | 7705 |  | Basment 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 6 | 1 | 5 |  |  | 5 | rm | OFF HIRED | 2022-06-19 | 2022-07-07 | 100% |  | 2.7143 | 135 | 12.25 | 675 | 61.25 | 472.5 | 202.5 | 166.25 | 841.25 | 841.25 | 0
| 1 | 287 | 12394 | 7705 |  | Basment 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 6 | 1 | 5 |  |  | 5 | rm | OFF HIRED | 2022-06-19 | 2022-07-07 | 100% |  | 2.7143 | 135 | 12.25 | 675 | 61.25 | 472.5 | 202.5 | 166.25 | 841.25 | 841.25 | 0
| 1 | 299 | 12406 | 7702 |  | Basement 1 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-06-19 | 2022-07-06 | 100% |  | 2.5714 | 135 | 12.25 | 540 | 49 | 378 | 162 | 126 | 666 | 666 | 0
| 1 | 306 | 12410 | 7721 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 6 | 1 | 5 |  |  | 5 | rm | OFF HIRED | 2022-06-20 | 2022-07-17 | 100% |  | 4 | 135 | 12.25 | 675 | 61.25 | 472.5 | 202.5 | 245 | 920 | 920 | 0
| 1 | 373 | 12530 | 7836 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 3.5 | 2.5 | 6 | 1 | 5 |  |  | 5 | rm | OFF HIRED | 2022-06-27 | 2022-08-18 | 100% |  | 7.5714 | 135 | 12.25 | 675 | 61.25 | 472.5 | 202.5 | 463.75 | 1138.75 | 1138.75 | 0
| 1 | 119 | 12142 | 7569 |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 4 | 1 | 3 |  |  | 12 | m2-LxH | OFF HIRED | 2022-06-01 | 2022-06-06 | 100% |  | 0.85714 | 14 |  | 168 | 0 | 117.6 | 50.4 | 0 | 168 | 168 | 0
| 1 | 88 | 12206 | 7572 |  | Basement 1 KCE Store Residence | Access Scaffold |  | INDEPENDENT | 22.5 | 1.3 | 3 | 1 | 2 |  |  | 45 | m2-LxH | OFF HIRED | 2022-06-02 | 2022-06-15 | 100% |  | 2 | 14 |  | 630 | 0 | 441 | 189 | 0 | 630 | 630 | 0
| 1 | 52 | 12207 | 7572 |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 10 | 1.3 | 4 | 1 | 3 |  |  | 30 | m2-LxH | OFF HIRED | 2022-06-02 | 2022-06-15 | 100% |  | 2 | 14 |  | 420 | 0 | 294 | 126 | 0 | 420 | 420 | 0
| 1 | 222 | 12319 | 7578 |  | Besement lift lobby Residence | Access Scaffold |  | INDEPENDENT | 1.3 | 1.3 | 5 | 1 | 4 |  |  | 5.2 | m2-LxH | OFF HIRED | 2022-06-12 | 2022-06-22 | 100% |  | 1.5714 | 14 |  | 72.8 | 0 | 50.96 | 21.84 | 0 | 72.8 | 72.8 | 0
| 1 | 227 | 12324 | 7820 |  | Besement 1 Hotel | Access Scaffold |  | INDEPENDENT | 2.5 | 1.3 | 4 | 1 | 3 |  |  | 7.5 | m2-LxH | OFF HIRED | 2022-06-13 | 2022-08-12 | 100% |  | 8.7143 | 14 |  | 105 | 0 | 73.5 | 31.5 | 0 | 105 | 105 | 0
| 1 | 88 | 12238 | 7573 |  | Basement 1 KCE Store Residence | Access Scaffold |  | INDEPENDENT | 8 | 1.3 | 4 | 1 | 3 |  |  | 24 | m2-LxH | OFF HIRED | 2022-06-03 | 2022-06-14 | 100% |  | 1.7143 | 14 | 0.84 | 336 | 20.16 | 235.2 | 100.8 | 34.56 | 370.56 | 370.56 | 0
| 1 | 140 | 12241 | 7589 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 7.5 | 1.3 | 5 | 1 | 4 |  |  | 30 | m2-LxH | OFF HIRED | 2022-06-05 | 2022-06-28 | 100% |  | 3.4286 | 14 | 0.84 | 420 | 25.2 | 294 | 126 | 86.4 | 506.4 | 506.4 | 0
| 1 | 113 | 12229 | 7711 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 7 | 1.3 | 5 | 1 | 4 |  |  | 28 | m2-LxH | OFF HIRED | 2022-06-05 | 2022-07-14 | 100% |  | 5.7143 | 14 | 0.84 | 392 | 23.52 | 274.4 | 117.6 | 134.4 | 526.4 | 526.4 | 0
| 1 |  | 12230 | 7812 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 2.5 | 1.3 | 5 | 1 | 4 |  |  | 10 | m2-LxH | OFF HIRED | 2022-06-05 | 2022-08-09 | 100% |  | 9.4286 | 14 | 0.84 | 140 | 8.4 | 98 | 42 | 79.2 | 219.2 | 219.2 | 0
| 1 | 168 | 12164 | 7573 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 2.5 | 1.3 | 5 | 1 | 4 |  |  | 10 | m2-LxH | OFF HIRED | 2022-06-07 | 2022-06-14 | 100% |  | 1.1429 | 14 | 0.84 | 140 | 8.4 | 98 | 42 | 9.6 | 149.6 | 149.6 | 0
| 1 | 169 | 12165 | 7573 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 2.5 | 1.3 | 5 | 1 | 4 |  |  | 10 | m2-LxH | OFF HIRED | 2022-06-07 | 2022-06-14 | 100% |  | 1.1429 | 14 | 0.84 | 140 | 8.4 | 98 | 42 | 9.6 | 149.6 | 149.6 | 0
| 1 | 204 | 12301 | 7573 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 15 | 1.3 | 5 | 1 | 4 |  |  | 60 | m2-LxH | OFF HIRED | 2022-06-10 | 2022-06-14 | 100% |  | 0.71429 | 14 | 0.84 | 840 | 50.4 | 588 | 252 | 36 | 876 | 876 | 0
| 1 | 207 | 12303 | 7574 |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 10 | 1.3 | 5 | 1 | 4 |  |  | 40 | m2-LxH | OFF HIRED | 2022-06-10 | 2022-06-19 | 100% |  | 1.4286 | 14 | 0.84 | 560 | 33.6 | 392 | 168 | 48 | 608 | 608 | 0
| 1 | 209 | 12306 | 7574 |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 10 | 1.3 | 6 | 1 | 5 |  |  | 50 | m2-LxH | OFF HIRED | 2022-06-12 | 2022-06-19 | 100% |  | 1.1429 | 14 | 0.84 | 700 | 42 | 490 | 210 | 48 | 748 | 748 | 0
| 1 | 228 | 12325 | 7578 |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 4 | 1 | 3 |  |  | 15 | m2-LxH | OFF HIRED | 2022-06-13 | 2022-06-22 | 100% |  | 1.4286 | 14 | 0.84 | 210 | 12.6 | 147 | 63 | 18 | 228 | 228 | 0
| 1 | 248 | 12363 | 7704 |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 5 | 1 | 4 |  |  | 20 | m2-LxH | OFF HIRED | 2022-06-15 | 2022-07-06 | 100% |  | 3.1429 | 14 | 0.84 | 280 | 16.8 | 196 | 84 | 52.8 | 332.8 | 332.8 | 0
| 1 | 247 | 12362 | 7704 |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 5 | 1 | 4 |  |  | 16 | m2-LxH | OFF HIRED | 2022-06-15 | 2022-07-06 | 100% |  | 3.1429 | 14 | 0.84 | 224 | 13.44 | 156.8 | 67.2 | 42.24 | 266.24 | 266.24 | 0
| 1 | 240 | 12355 | 7827 |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 5 | 1 | 4 |  |  | 20 | m2-LxH | OFF HIRED | 2022-06-15 | 2022-08-16 | 100% |  | 9 | 14 | 0.84 | 280 | 16.8 | 196 | 84 | 151.2 | 431.2 | 431.2 | 0
| 1 | 239 | 12354 | 7704 |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 10 | 1.3 | 4 | 1 | 3 |  |  | 30 | m2-LxH | OFF HIRED | 2022-06-15 | 2022-07-06 | 100% |  | 3.1429 | 14 | 0.84 | 420 | 25.2 | 294 | 126 | 79.2 | 499.2 | 499.2 | 0
| 1 | A242 | 12405 | 7703 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 6 | 1.3 | 4.5 | 1 | 3.5 |  |  | 21 | m2-LxH | OFF HIRED | 2022-06-19 | 2022-07-07 | 100% |  | 2.7143 | 14 | 0.84 | 294 | 17.64 | 205.8 | 88.2 | 47.88 | 341.88 | 341.88 | 0
| 1 | 300 | 12407 | 7579 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 5 | 1 | 4 |  |  | 20 | m2-LxH | OFF HIRED | 2022-06-19 | 2022-06-23 | 100% |  | 0.71429 | 14 | 0.84 | 280 | 16.8 | 196 | 84 | 12 | 292 | 292 | 0
| 1 | 288 | 12394 | 7578 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 10 | 1.3 | 6 | 1 | 5 |  |  | 50 | m2-LxH | OFF HIRED | 2022-06-19 | 2022-06-22 | 100% |  | 0.57143 | 14 | 0.84 | 700 | 42 | 490 | 210 | 24 | 724 | 724 | 0
| 1 |  | 12411 | 7703 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 10 | 1.3 | 3 | 1 | 2 |  |  | 20 | m2-LxH | OFF HIRED | 2022-06-16 | 2022-07-07 | 100% |  | 3.1429 | 14 | 0.84 | 280 | 16.8 | 196 | 84 | 52.8 | 332.8 | 332.8 | 0
| 1 | 274 | 12388 | 7589 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 5 | 1 | 4 |  |  | 20 | m2-LxH | OFF HIRED | 2022-06-17 | 2022-06-28 | 100% |  | 1.7143 | 14 | 0.84 | 280 | 16.8 | 196 | 84 | 28.8 | 308.8 | 308.8 | 0
| 1 | 319 | 12420 | 7579 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 26 | 1.3 | 4 | 1 | 3 |  |  | 78 | m2-LxH | OFF HIRED | 2022-06-21 | 2022-06-23 | 100% |  | 0.42857 | 14 | 0.84 | 1092 | 65.52 | 764.4 | 327.6 | 28.08 | 1120.08 | 1120.08 | 0
| 1 |  | 12501 | 7812 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 5 | 1 | 4 |  |  | 16 | m2-LxH | OFF HIRED | 2022-06-24 | 2022-08-09 | 100% |  | 6.7143 | 14 | 0.84 | 224 | 13.44 | 156.8 | 67.2 | 90.24 | 314.24 | 314.24 | 0
| 1 | 256 | 12370 | 7722 |  | Bsement 1 Hotel | Access Scaffold |  | INDEPENDENT | 4 | 1.8 | 5 | 1 | 4 |  |  | 16 | m2-LxH | OFF HIRED | 2022-06-16 | 2022-07-17 | 100% |  | 4.5714 | 18 | 1.05 | 288 | 16.8 | 201.6 | 86.4 | 76.8 | 364.8 | 364.8 | 0
| 1 | 210 | 12307 | 7579 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 7.5 | 3.5 | 6 | 1 | 5 |  |  | 131.25 | m3 | OFF HIRED | 2022-06-12 | 2022-06-23 | 100% |  | 1.7143 | 7.5 | 0.7 | 984.375 | 91.875 | 689.0625 | 295.3125 | 157.5 | 1141.875 | 1141.875 | 0
| 1 | 285 | 12393 | 7734 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 7.5 | 2.5 | 5 | 1 | 4 |  |  | 75 | m3 | OFF HIRED | 2022-06-19 | 2022-07-25 | 100% |  | 5.2857 | 7.5 | 0.7 | 562.5 | 52.5 | 393.75 | 168.75 | 277.5 | 840 | 840 | 0
| 1 | 381 | 12544 | 8118 |  | Basment 1 Residence | Birdcage Scaffold |  | Birdcage | 5 | 5 | 3 | 1 | 2 |  |  | 50 | m3 | OFF HIRED | 2022-06-26 | 2022-10-18 | 100% |  | 16.4286 | 7.5 | 0.7 | 375 | 35 | 262.5 | 112.5 | 575 | 950 | 950 | 0
| 1 | 429 | 12589 | 7820 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 6 | 1 | 5 |  |  | 5 | rm | OFF HIRED | 2022-07-03 | 2022-08-12 | 100% |  | 5.8571 | 135 | 12.25 | 675 | 61.25 | 472.5 | 202.5 | 358.75 | 1033.75 | 1033.75 | 0
| 1 | 438 | 12596 | 7727 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 6 | 1 | 5 |  |  | 5 | rm | OFF HIRED | 2022-07-04 | 2022-07-18 | 100% |  | 2.1429 | 135 | 12.25 | 675 | 61.25 | 472.5 | 202.5 | 131.25 | 806.25 | 806.25 | 0
| 1 |  | 12638 | 8116 |  | Basement 1 Hotel | HEAVY DUTY TOWER |  | Tower | 6 | 2.5 | 7 | 1 | 6 |  |  | 6 | rm | OFF HIRED | 2022-07-06 | 2022-10-18 | 100% |  | 15 | 135 | 12.25 | 810 | 73.5 | 567 | 243 | 1102.5 | 1912.5 | 1912.5 | 0
| 1 | 503 | 12708 | 7708 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 2.5 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-07 | 2022-07-13 | 100% |  | 1 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 24.5 | 294.5 | 294.5 | 0
| 1 | 503 | 12708 | 7708 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 2.5 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-07 | 2022-07-13 | 100% |  | 1 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 24.5 | 294.5 | 294.5 | 0
| 1 | 498 | 12702 | 7731 |  | Basement 1 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 6 | 1 | 5 |  |  | 5 | rm | OFF HIRED | 2022-07-12 | 2022-07-20 | 100% |  | 1.2857 | 135 | 12.25 | 675 | 61.25 | 472.5 | 202.5 | 78.75 | 753.75 | 753.75 | 0
| 1 | 540 | 12750 | 8118 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-07-18 | 2022-10-18 | 100% |  | 13.2857 | 135 | 12.25 | 540 | 49 | 378 | 162 | 651 | 1191 | 1191 | 0
| 1 | 564 | 12777 | 7741 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-07-21 | 2022-07-29 | 100% |  | 1.2857 | 135 | 12.25 | 540 | 49 | 378 | 162 | 63 | 603 | 603 | 0
| 1 | 568 | 12787 | 7863 |  | Basment 1 Lift Hotel | Access Scaffold |  | INDEPENDENT | 6.5 | 1.3 | 4.5 | 1 | 3.5 |  |  | 22.75 | m2-LxH | OFF HIRED | 2022-07-21 | 2022-09-01 | 100% |  | 6.1429 | 14 |  | 318.5 | 0 | 222.95 | 95.55 | 0 | 318.5 | 318.5 | 0
| 1 | 406 | 12567 | 8116 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 12 | 1.3 | 3 | 1 | 2 |  |  | 24 | m2-LxH | OFF HIRED | 2022-06-30 | 2022-10-18 | 100% |  | 15.8571 | 14 | 0.84 | 336 | 20.16 | 235.2 | 100.8 | 319.68 | 655.68 | 655.68 | 0
| 1 | 405 | 12566 | 7721 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 4.2 | 1.3 | 5.5 | 1 | 4.5 |  |  | 18.9 | m2-LxH | OFF HIRED | 2022-06-30 | 2022-07-17 | 100% |  | 2.5714 | 14 | 0.84 | 264.6 | 15.876 | 185.22 | 79.38 | 40.824 | 305.424 | 305.424 | 0
| 1 | 469 | 12624 | 6746 |  | Basment 2 Hotel | Access Scaffold |  | INDEPENDENT | 15 | 1.3 | 9 | 1 | 8 |  |  | 120 | m2-LxH | OFF HIRED | 2022-07-07 | 2022-09-29 | 100% |  | 12.1429 | 14 | 0.84 | 1680 | 100.8 | 1176 | 504 | 1224 | 2904 | 2904 | 0
| 1 | 485 | 12636 | 7809 |  | Basement 1 Ramp Residence | Access Scaffold |  | INDEPENDENT | 56 | 1.3 | 4.5 | 1 | 3.5 |  |  | 196 | m2-LxH | OFF HIRED | 2022-07-07 | 2022-07-26 | 100% |  | 2.8571 | 14 | 0.84 | 2744 | 164.64 | 1920.8 | 823.2 | 470.4 | 3214.4 | 3214.4 | 0
| 1 | 512 | 12717 | 7737 |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 3 | 1 | 2 |  |  | 8 | m2-LxH | OFF HIRED | 2022-07-14 | 2022-07-26 | 100% |  | 1.8571 | 14 |  | 112 | 0 | 78.4 | 33.6 | 0 | 112 | 112 | 0
| 1 | 523 | 12731 | 7731 |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 3 | 1 | 2 |  |  | 8 | m2-LxH | OFF HIRED | 2022-07-15 | 2022-07-20 | 100% |  | 0.85714 | 14 | 0.84 | 112 | 6.72 | 78.4 | 33.6 | 5.76 | 117.76 | 117.76 | 0
| 1 | 532 | 12743 | 7731 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 3 | 1 | 2 |  |  | 8 | m2-LxH | OFF HIRED | 2022-07-17 | 2022-07-20 | 100% |  | 0.57143 | 14 | 0.84 | 112 | 6.72 | 78.4 | 33.6 | 3.84 | 115.84 | 115.84 | 0
| 1 | 531 | 12742 | 7734 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 8 | 0.6 | 5 | 1 | 4 |  |  | 32 | m2-LxH | OFF HIRED | 2022-07-17 | 2022-07-25 | 100% |  | 1.2857 | 14 | 0.84 | 448 | 26.88 | 313.6 | 134.4 | 34.56 | 482.56 | 482.56 | 0
| 1 | 541 | 12751 | 8118 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 7.5 | 1.3 | 5.5 | 1 | 4.5 |  |  | 33.75 | m2-LxH | OFF HIRED | 2022-07-17 | 2022-10-18 | 100% |  | 13.4286 | 14 | 0.84 | 472.5 | 28.35 | 330.75 | 141.75 | 380.7 | 853.2 | 853.2 | 0
| 1 | 546 | 12757 | 6746 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 6 | 1 | 5 |  |  | 25 | m2-LxH | OFF HIRED | 2022-07-19 | 2022-09-29 | 100% |  | 10.4286 | 14 | 0.84 | 350 | 21 | 245 | 105 | 219 | 569 | 569 | 0
| 1 | 548 | 12759 | 7737 |  | Basement 1 Ramp Residence | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 4 | 1 | 3 |  |  | 12 | m2-LxH | OFF HIRED | 2022-07-19 | 2022-07-26 | 100% |  | 1.1429 | 14 | 0.84 | 168 | 10.08 | 117.6 | 50.4 | 11.52 | 179.52 | 179.52 | 0
| 1 | 467 | 12623 | 7742 |  | Basement 1 Near MEP Hotel | Birdcage Scaffold |  | INDEPENDENT | 5 | 1.8 | 4.5 | 1 | 3.5 |  |  | 17.5 | m2-LxH | OFF HIRED | 2022-07-07 | 2022-07-27 | 100% |  | 3 | 18 | 1.05 | 315 | 18.375 | 220.5 | 94.5 | 55.125 | 370.125 | 370.125 | 0
| 1 | 565 | 12788 | 8416 |  | Basement 1 Hotel | Birdcage Scaffold |  | INDEPENDENT | 5 | 1.8 | 5 | 1 | 4 |  |  | 20 | m2-LxH | OFF HIRED | 2022-07-21 | 2023-01-12 | 100% |  | 25.1429 | 18 | 1.05 | 360 | 21 | 252 | 108 | 528 | 888 | 888 | 0
| 1 | 580 | 12795 | 7833 |  | Basement 1 Residence | Birdcage Scaffold |  | INDEPENDENT | 10 | 1.8 | 5 | 1 | 4 |  |  | 40 | m2-LxH | OFF HIRED | 2022-07-24 | 2022-08-19 | 100% |  | 3.8571 | 18 | 1.05 | 720 | 42 | 504 | 216 | 162 | 882 | 882 | 0
| 1 | 587 | 12804 | 6712 |  | Basement 1 Residence | Birdcage Scaffold |  | INDEPENDENT | 10 | 1.8 | 5 | 1 | 4 |  |  | 40 | m2-LxH | OFF HIRED | 2022-07-25 | 2022-09-24 | 100% |  | 8.8571 | 18 | 1.05 | 720 | 42 | 504 | 216 | 372 | 1092 | 1092 | 0
| 1 | 578 | 12794 | 6701 |  | Level 15 Hotel | Birdcage Scaffold |  | INDEPENDENT | 12 | 1.8 | 6 | 1 | 5 |  |  | 60 | m2-LxH | OFF HIRED | 2022-07-24 | 2022-09-19 | 100% |  | 8.2857 | 18 | 1.05 | 1080 | 63 | 756 | 324 | 522 | 1602 | 1602 | 0
| 1 | 577 | 12793 | 7839 |  | Baseent 1 Residence | Birdcage Scaffold |  | Birdcage | 7.5 | 4 | 5 | 1 | 4 |  |  | 120 | m3 | OFF HIRED | 2022-07-24 | 2022-08-23 | 100% |  | 4.4286 | 7.5 |  | 900 | 0 | 630 | 270 | 0 | 900 | 900 | 0
| 1 | 381 | 12553 | 8161 |  | Baseent 1 Residence | Birdcage Scaffold |  | Birdcage | 5 | 5 | 3 | 1 | 2 |  |  | 50 | m3 | OFF HIRED | 2022-06-28 | 2022-10-28 | 100% |  | 17.5714 | 7.5 | 0.7 | 375 | 35 | 262.5 | 112.5 | 615 | 990 | 990 | 0
| 1 | 389 | 12555 | 7722 |  | Baseent 1 Residence | Birdcage Scaffold |  | Birdcage | 7 | 3 | 4 | 1 | 3 |  |  | 63 | m3 | OFF HIRED | 2022-06-29 | 2022-07-17 | 100% |  | 2.7143 | 7.5 | 0.7 | 472.5 | 44.1 | 330.75 | 141.75 | 119.7 | 592.2 | 592.2 | 0
| 1 | 400 | 12561 | 7721 |  | Baseent 1 Residence | Birdcage Scaffold |  | Birdcage | 5 | 5 | 4 | 1 | 3 |  |  | 75 | m3 | OFF HIRED | 2022-06-29 | 2022-07-17 | 100% |  | 2.7143 | 7.5 | 0.7 | 562.5 | 52.5 | 393.75 | 168.75 | 142.5 | 705 | 705 | 0
| 1 | 407 | 12568 |  |  | Baseent 1 Residence | Birdcage Scaffold |  | Birdcage | 5 | 5 | 3.5 | 1 | 2.5 |  |  | 62.5 | m3 | ON HIRE | 2022-06-30 |  | 100% |  | 34.8571 | 7.5 | 0.7 | 468.75 | 43.75 | 328.125 | 0 | 1525 | 1853.125 | 1678.125 | 175 |  |  | #VALUE! | 328.125 | #VALUE! | #VALUE!
| 1 | 468 | 12625 | 7801 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 8.5 | 3 | 4 | 1 | 3 |  |  | 76.5 | m3 | OFF HIRED | 2022-07-07 | 2022-08-03 | 100% |  | 4 | 7.5 | 0.7 | 573.75 | 53.55 | 401.625 | 172.125 | 214.2 | 787.95 | 787.95 | 0
| 1 | 545 | 12756 | 7820 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 6 | 4 | 5 | 1 | 4 |  |  | 96 | m3 | OFF HIRED | 2022-07-18 | 2022-08-12 | 100% |  | 3.7143 | 7.5 | 0.7 | 720 | 67.2 | 504 | 216 | 249.6 | 969.6 | 969.6 | 0
| 1 | 550 | 12760 | 7742 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 5.5 | 1 | 4.5 |  |  | 28.125 | m3 | OFF HIRED | 2022-07-19 | 2022-07-27 | 100% |  | 1.2857 | 7.5 | 0.7 | 210.9375 | 19.6875 | 147.6562 | 63.2812 | 25.3125 | 236.25 | 236.25 | 0
| 1 | 559 | 12772 | 7734 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 3 | 3 | 5.5 | 1 | 4.5 |  |  | 40.5 | m3 | OFF HIRED | 2022-07-20 | 2022-07-25 | 100% |  | 0.85714 | 7.5 | 0.7 | 303.75 | 28.35 | 212.625 | 12.38 | 24.3 | 249.305 | 249.305 | 0
| 1 | 486 | 12768 | 6712 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 5 | 3 | 6 | 1 | 5 |  |  | 75 | m3 | OFF HIRED | 2022-07-20 | 2022-09-24 | 100% |  | 9.5714 | 7.5 | 0.7 | 562.5 | 52.5 | 393.75 | 168.75 | 502.5 | 1065 | 1065 | 0
| 1 | 575 | 12791 | 7742 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 3.5 | 2.5 | 6 | 1 | 5 |  |  | 43.75 | m3 | OFF HIRED | 2022-07-24 | 2022-07-27 | 100% |  | 0.57143 | 7.5 | 0.7 | 328.125 | 30.625 | 229.6875 | 98.4375 | 17.5 | 345.625 | 345.625 | 0
| 1 | 576 | 12792 | 7801 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 10 | 9 | 5 | 1 | 4 |  |  | 360 | m3 | OFF HIRED | 2022-07-24 | 2022-08-03 | 100% |  | 1.5714 | 7.5 | 0.7 | 2700 | 252 | 1890 | 810 | 396 | 3096 | 3096 | 0
| 1 | 590 | 12808 | 7836 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 8 | 5 | 5 | 1 | 4 |  |  | 160 | m3 | OFF HIRED | 2022-07-25 | 2022-08-18 | 100% |  | 3.5714 | 7.5 | 0.7 | 1200 | 112 | 840 | 360 | 400 | 1600 | 1600 | 0
| 1 | 728 | 12984 | 7839 |  | Basement 1 Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-12 | 2022-08-23 | 100% |  | 1.7143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 42 | 312 | 312 | 0
| 1 | 760 | 13025 | 7863 |  | Basement 1 Residence | Access Scaffold |  | Tower | 2.5 | 1.3 | 2.5 | 1 | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2022-08-17 | 2022-09-01 | 100% |  | 2.2857 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 60.75 | 42 | 244.5 | 244.5 | 0
| 1 | 768 | 13030 | 7873 |  | Basement 1 Residence | Access Scaffold |  | Tower | 2.5 | 1.8 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-08-19 | 2022-09-06 | 100% |  | 2.7143 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 99.75 | 504.75 | 504.75 | 0
| 1 | 803 | 13064 | 7845 |  | Basement 1 Hotel | Access Scaffold |  | Tower | 2.5 | 1.8 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-08-23 | 2022-08-29 | 100% |  | 1 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 30.625 | 368.125 | 368.125 | 0
| 1 | 806 | 13068 | 7845 |  | Basement 1 Hotel | Access Scaffold |  | Tower | 1.8 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-08-24 | 2022-08-29 | 100% |  | 0.85714 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 26.25 | 363.75 | 363.75 | 0
| 1 | 816 | 13079 | 7845 |  | Basement 1 Hotel | Access Scaffold |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-08-25 | 2022-08-29 | 100% |  | 0.71429 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 21.875 | 359.375 | 359.375 | 0
| 1 | 817 | 13080 | 7845 |  | Basement 1 Hotel | Access Scaffold |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-08-25 | 2022-08-29 | 100% |  | 0.71429 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 21.875 | 359.375 | 359.375 | 0
| 1 | 632 | 12854 | 7801 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 5 | 1.3 | 4 | 1 | 3 |  |  | 15 | m2-LxH | OFF HIRED | 2022-07-31 | 2022-08-03 | 100% |  | 0.57143 | 14 | 0 | 210 | 0 | 147 | 63 | 0 | 210 | 210 | 0
| 1 | 612 | 12832 | 6748 |  | Basement 1 Residence | Access Scaffold |  | Independent | 7.5 | 1.3 | 5 | 1 | 4 |  |  | 30 | m2-LxH | OFF HIRED | 2022-07-28 | 2022-09-29 | 100% |  | 9.1429 | 14 | 0.84 | 420 | 25.2 | 294 | 126 | 230.4 | 650.4 | 650.4 | 0
| 1 | 648 | 12871 | 7805 |  | Basement 1 Residence | Access Scaffold |  | Independent | 21.5 | 1.3 | 3 | 1 | 2 |  |  | 43 | m2-LxH | OFF HIRED | 2022-08-02 | 2022-08-04 | 100% |  | 0.42857 | 14 | 0.84 | 602 | 36.12 | 421.4 | 180.6 | 15.48 | 617.48 | 617.48 | 0
| 1 | 647 | 12870 | 7812 |  | Basement 1 Residence | Access Scaffold |  | Independent | 9.5 | 1.3 | 4 | 1 | 3 |  |  | 28.5 | m2-LxH | OFF HIRED | 2022-08-03 | 2022-08-09 | 100% |  | 1 | 14 | 0.84 | 399 | 23.94 | 279.3 | 119.7 | 23.94 | 422.94 | 422.94 | 0
| 1 | 689 | 12897 | 7812 |  | Basement 1 Residence | Access Scaffold |  | Independent | 10 | 1.3 | 5.5 | 1 | 4.5 |  |  | 45 | m2-LxH | OFF HIRED | 2022-08-06 | 2022-08-09 | 100% |  | 0.57143 | 14 | 0.84 | 630 | 37.8 | 441 | 189 | 21.6 | 651.6 | 651.6 | 0
| 1 | 676 | 12894 | 7867 |  | Basement 1 Residence | Access Scaffold |  | Independent | 10 | 1.3 | 5 | 1 | 4 |  |  | 40 | m2-LxH | OFF HIRED | 2022-08-07 | 2022-09-02 | 100% |  | 3.8571 | 14 | 0.84 | 560 | 33.6 | 392 | 168 | 129.6 | 689.6 | 689.6 | 0
| 1 | 700 | 12963 | 7834 |  | Basement 1 Residence | Access Scaffold |  | Independent | 7.5 | 1.3 | 4.5 | 1 | 3.5 |  |  | 26.25 | m2-LxH | OFF HIRED | 2022-08-08 | 2022-08-19 | 100% |  | 1.7143 | 14 | 0.84 | 367.5 | 22.05 | 257.25 | 110.25 | 37.8 | 405.3 | 405.3 | 0
| 1 | 701 | 12964 | 7820 |  | Basement 1 Residence | Access Scaffold |  | Independent | 7 | 1.3 | 4 | 1 | 3 |  |  | 21 | m2-LxH | OFF HIRED | 2022-08-08 | 2022-08-12 | 100% |  | 0.71429 | 14 | 0.84 | 294 | 17.64 | 205.8 | 88.2 | 12.6 | 306.6 | 306.6 | 0
| 1 | 704 | 12966 | 7836 |  | Basement 1 Residence | Access Scaffold |  | Independent | 5 | 1.3 | 5 | 1 | 4 |  |  | 20 | m2-LxH | OFF HIRED | 2022-08-08 | 2022-08-18 | 100% |  | 1.5714 | 14 | 0.84 | 280 | 16.8 | 196 | 84 | 26.4 | 306.4 | 306.4 | 0
| 1 | 717 | 12982 | 7834 |  | Basement 1 Residence | Access Scaffold |  | Independent | 10 | 1.3 | 5 | 1 | 4 |  |  | 40 | m2-LxH | OFF HIRED | 2022-08-12 | 2022-08-19 | 100% |  | 1.1429 | 14 | 0.84 | 560 | 33.6 | 392 | 168 | 38.4 | 598.4 | 598.4 | 0
| 1 | 727 | 12983 | 7836 |  | Basement 1 Residence | Access Scaffold |  | Independent | 11 | 1.3 | 5 | 1 | 4 |  |  | 44 | m2-LxH | OFF HIRED | 2022-08-12 | 2022-08-18 | 100% |  | 1 | 14 | 0.84 | 616 | 36.96 | 431.2 | 184.8 | 36.96 | 652.96 | 652.96 | 0
| 1 | 739 | 12997 | 7850 |  | Basement 1 Residence | Access Scaffold |  | Independent | 7.5 | 1.3 | 4.5 | 1 | 3.5 |  |  | 26.25 | m2-LxH | OFF HIRED | 2022-08-15 | 2022-08-29 | 100% |  | 2.1429 | 14 | 0.84 | 367.5 | 22.05 | 257.25 | 110.25 | 47.25 | 414.75 | 414.75 | 0
| 1 | 780 | 13040 | 7867 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 4 | 1.3 | 5 | 1 | 4 |  |  | 16 | m2-LxH | OFF HIRED | 2022-08-19 | 2022-09-02 | 100% |  | 2.1429 | 14 | 0.84 | 224 | 13.44 | 156.8 | 67.2 | 28.8 | 252.8 | 252.8 | 0
| 1 | 789 | 13049 | 7850 |  | Basement 1 Residence | Access Scaffold |  | Independent | 25 | 1.3 | 4.5 |  | 4.5 |  |  | 112.5 | m2-LxH | OFF HIRED | 2022-08-22 | 2022-08-29 | 100% |  | 1.1429 | 14 | 0.84 | 1575 | 94.5 | 1102.5 | 472.5 | 108 | 1683 | 1683 | 0
| 1 | 798 | 13058 | 6702 |  | Basement 1 Residence | Access Scaffold |  | Independent | 10 | 1.3 | 4 |  | 4 |  |  | 40 | m2-LxH | OFF HIRED | 2022-08-23 | 2022-09-20 | 100% |  | 4.1429 | 14 | 0.84 | 560 | 33.6 | 392 | 168 | 139.2 | 699.2 | 699.2 | 0
| 1 | 805 | 13067 | 7898 |  | Basement 2 Hotel | Access Scaffold |  | Independent | 5 | 1 | 3 |  | 3 |  |  | 15 | m2-LxH | OFF HIRED | 2022-08-24 | 2022-09-16 | 100% |  | 3.4286 | 14 | 0.84 | 210 | 12.6 | 147 | 63 | 43.2 | 253.2 | 253.2 | 0
| 1 | 577 | 12895 | 7827 |  | Basement 1 Residence | Access Scaffold |  | Independent | 8 | 1.8 | 5 | 1 | 4 |  |  | 32 | m2-LxH | OFF HIRED | 2022-08-06 | 2022-08-16 | 100% |  | 1.5714 | 18 | 1.05 | 576 | 33.6 | 403.2 | 172.8 | 52.8 | 628.8 | 628.8 | 0
| 1 | 633 | 12856 |  |  | Basement 1 Residence | Access Scaffold |  | Independent | 7.5 | 1.8 | 10 | 1 | 9 |  |  | 67.5 | m2-LxH | ON HIRE | 2022-07-31 |  | 100% |  | 30.4286 | 18 | 1.05 | 1215 | 70.875 | 850.5 | 0 | 2156.625 | 3007.125 | 2723.625 | 283.5 |  |  | #VALUE! | 850.5 | #VALUE! | #VALUE!
| 1 | 689 | 12897 | 8284 |  | Basement 1 Residence | Access Scaffold |  | Independent | 15 | 1.8 | 5.5 | 1 | 4.5 |  |  | 67.5 | m2-LxH | OFF HIRED | 2022-08-06 | 2022-11-27 | 100% |  | 16.2857 | 18 | 1.05 | 1215 | 70.875 | 850.5 | 364.5 | 1154.25 | 2369.25 | 2369.25 | 0
| 1 | 791 | 13051 | 7878 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 5 | 1.8 | 4 |  | 4 |  |  | 20 | m2-LxH | OFF HIRED | 2022-08-22 | 2022-09-12 | 100% |  | 3.1429 | 18 | 1.05 | 360 | 21 | 252 | 108 | 66 | 426 | 426 | 0
| 1 | 673 | 12890 | 8119 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 7 | 2.5 | 5 | 1 | 4 |  |  | 70 | m3 | OFF HIRED | 2022-08-06 | 2022-10-14 | 100% |  | 10 | 7.5 | 0.7 | 525 | 49 | 367.5 | 157.5 | 490 | 1015 | 1015 | 0
| 1 | 689 | 12897 | 8284 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 20 | 2.5 | 5.5 | 1 | 4.5 |  |  | 225 | m3 | OFF HIRED | 2022-08-06 | 2022-11-27 | 100% |  | 16.2857 | 7.5 | 0.7 | 1687.5 | 157.5 | 1181.25 | 506.25 | 2565 | 4252.5 | 4252.5 | 0
| 1 | 688 | 12899 | 6732 |  | Basement 2 Residence | Birdcage Scaffold |  | Birdcage | 5 | 2.5 | 5 | 1 | 4 |  |  | 50 | m3 | OFF HIRED | 2022-08-07 | 2022-09-28 | 100% |  | 7.5714 | 7.5 | 0.7 | 375 | 35 | 262.5 | 112.5 | 265 | 640 | 640 | 0
| 1 | 710 | 12975 | 7867 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 7.5 | 6 | 5.5 | 1 | 4.5 |  |  | 202.5 | m3 | OFF HIRED | 2022-08-11 | 2022-09-02 | 100% |  | 3.2857 | 7.5 | 0.7 | 1518.75 | 141.75 | 1063.125 | 455.625 | 465.75 | 1984.5 | 1984.5 | 0
| 1 | 740 | 12998 | 8446 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 7.5 | 7.5 | 3 | 1 | 2 |  |  | 112.5 | m3 | OFF HIRED | 2022-08-15 | 2023-01-22 | 100% |  | 23 | 7.5 | 0.7 | 843.75 | 78.75 | 590.625 | 253.125 | 1811.25 | 2655 | 2655 | 0
| 1 | 486 | 12881 | 6746 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 9 | 2.5 | 3 | 1 | 2 |  |  | 45 | m3 | OFF HIRED | 2022-08-03 | 2022-09-29 | 100% |  | 8.2857 | 7.5 | 0.7 | 337.5 | 31.5 | 236.25 | 101.25 | 261 | 598.5 | 598.5 | 0
| 1 | 656 | 12880 | 7833 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 5 | 2.5 | 3 | 1 | 2 |  |  | 25 | m3 | OFF HIRED | 2022-08-03 | 2022-08-19 | 100% |  | 2.4286 | 7.5 | 0.7 | 187.5 | 17.5 | 131.25 | 56.25 | 42.5 | 230 | 230 | 0
| 1 | 651 | 12875 | 7834 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 3 | 1 | 2 |  |  | 20 | m3 | OFF HIRED | 2022-08-03 | 2022-08-19 | 100% |  | 2.4286 | 7.5 | 0.7 | 150 | 14 | 105 | 45 | 34 | 184 | 184 | 0
| 1 | 639 | 12862 | 8096 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 9 | 2.5 | 5 | 1 | 4 |  |  | 90 | m3 | OFF HIRED | 2022-08-01 | 2022-10-12 | 100% |  | 10.4286 | 7.5 | 0.7 | 675 | 63 | 472.5 | 202.5 | 657 | 1332 | 1332 | 0
| 1 | 925 | 13297 | 8140 |  | Basement 1 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 3.5 |  | 3.5 |  |  | 3.5 | rm | OFF HIRED | 2022-09-09 | 2022-10-23 | 100% |  | 6.4286 | 135 |  | 472.5 | 0 | 330.75 | 141.75 | 0 | 472.5 | 472.5 | 0
| 1 | 833 | 13102 | 7863 |  | Basement 1 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-08-26 | 2022-09-01 | 100% |  | 1 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 30.625 | 368.125 | 368.125 | 0
| 1 | 829 | 13097 | 7884 |  | Basement 1 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-08-26 | 2022-09-13 | 100% |  | 2.7143 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 83.125 | 420.625 | 420.625 | 0
| 1 | 752 | 13132 | 7878 |  | Basement 1 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-08-30 | 2022-09-12 | 100% |  | 2 | 135 | 12.25 | 540 | 49 | 378 | 162 | 98 | 638 | 638 | 0
| 1 | 858 | 13129 | 7898 |  | Basement 2 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-08-30 | 2022-09-16 | 100% |  | 2.5714 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 78.75 | 416.25 | 416.25 | 0
| 1 | 884 | 13255 | 7875 |  | Basement 1 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-09-03 | 2022-09-06 | 100% |  | 0.57143 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 21 | 426 | 426 | 0
| 1 | 927 | 13299 | 8058 |  | Basement 1 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-09-09 | 2022-10-03 | 100% |  | 3.5714 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 109.375 | 446.875 | 446.875 | 0
| 1 | 935 | 13306 | 7898 |  | Basement 1 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-09-10 | 2022-09-16 | 100% |  | 1 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 30.625 | 368.125 | 368.125 | 0
| 1 | 823 | 13118 | 7878 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 9 | 1.3 | 4 |  | 4 |  |  | 36 | m2-LxH | OFF HIRED | 2022-08-27 | 2022-09-12 | 100% |  | 2.4286 | 14 | 0.84 | 504 | 30.24 | 352.8 | 151.2 | 73.44 | 577.44 | 577.44 | 0
| 1 | 847 | 13116 | 7868 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 4 | 1.3 | 2.5 |  | 2.5 |  |  | 10 | m2-LxH | OFF HIRED | 2022-08-29 | 2022-09-03 | 100% |  | 0.85714 | 14 | 0.84 | 140 | 8.4 | 98 | 42 | 7.2 | 147.2 | 147.2 | 0
| 1 | 841 | 13110 | 7884 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 10 | 1.3 | 4 |  | 4 |  |  | 40 | m2-LxH | OFF HIRED | 2022-08-27 | 2022-09-13 | 100% |  | 2.5714 | 14 | 0.84 | 560 | 33.6 | 392 | 168 | 86.4 | 646.4 | 646.4 | 0
| 1 | 930 | 13301 | 8119 |  | Basement 1 Residence | Access Scaffold |  | Independent | 5 | 1.3 | 4 |  | 4 |  |  | 20 | m2-LxH | OFF HIRED | 2022-09-10 | 2022-10-14 | 100% |  | 5 | 14 | 0.84 | 280 | 16.8 | 196 | 84 | 84 | 364 | 364 | 0
| 1 | 925 | 13317 | 8316 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 4 | 1.3 | 2.5 |  | 2.5 |  |  | 10 | m2-LxH | OFF HIRED | 2022-09-12 | 2022-12-09 | 100% |  | 12.7143 | 14 | 0.84 | 140 | 8.4 | 98 | 42 | 106.8 | 246.8 | 246.8 | 0
| 1 | 958 | 13334 | 6712 |  | Basement 1 Residence | Access Scaffold |  | Independent | 11.5 | 1.3 | 5 |  | 5 |  |  | 57.5 | m2-LxH | OFF HIRED | 2022-09-14 | 2022-09-24 | 100% |  | 1.5714 | 14 | 0.84 | 805 | 48.3 | 563.5 | 241.5 | 75.9 | 880.9 | 880.9 | 0
| 1 | 970 | 13345 | 6712 |  | Basement 1 Residence | Access Scaffold |  | Independent | 9.5 | 1.3 | 4.5 |  | 4.5 |  |  | 42.75 | m2-LxH | OFF HIRED | 2022-09-15 | 2022-09-24 | 100% |  | 1.4286 | 14 | 0.84 | 598.5 | 35.91 | 418.95 | 179.55 | 51.3 | 649.8 | 649.8 | 0
| 1 | 969 | 13344 | 6712 |  | Basement 1 Residence | Access Scaffold |  | Independent | 7.5 | 1.3 | 4.5 |  | 4.5 |  |  | 33.75 | m2-LxH | OFF HIRED | 2022-09-15 | 2022-09-24 | 100% |  | 1.4286 | 14 | 0.84 | 472.5 | 28.35 | 330.75 | 141.75 | 40.5 | 513 | 513 | 0
| 1 | 968 | 13343 | 8076 |  | Basement 1 Residence | Access Scaffold |  | Independent | 7.5 | 1.3 | 4.5 |  | 4.5 |  |  | 33.75 | m2-LxH | OFF HIRED | 2022-09-15 | 2022-10-03 | 100% |  | 2.7143 | 14 | 0.84 | 472.5 | 28.35 | 330.75 | 141.75 | 76.95 | 549.45 | 549.45 | 0
| 1 | 851 | 13123 | 7868 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 3.8 | 1.8 | 2.5 |  | 2.5 |  |  | 9.5 | m2-LxH | OFF HIRED | 2022-08-29 | 2022-09-03 | 100% |  | 0.85714 | 18 | 1.05 | 171 | 9.975 | 119.7 | 51.3 | 8.55 | 179.55 | 179.55 | 0
| 1 | 871 | 13142 | 7868 |  | Basement 1 Residence | Access Scaffold |  | Independent | 4 | 1.8 | 4 |  | 4 |  |  | 16 | m2-LxH | OFF HIRED | 2022-09-01 | 2022-09-03 | 100% |  | 0.42857 | 18 | 1.05 | 288 | 16.8 | 201.6 | 86.4 | 7.2 | 295.2 | 295.2 | 0
| 1 | 335 | 12436 | 7727 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-06-23 | 2022-07-18 | 100% |  | 3.7143 | 135 | 12.25 | 540 | 49 | 378 | 162 | 182 | 722 | 722 | 0
| 1 | 547 | 12770 | 6746 |  | Basement 1 Residance | Access Scaffold |  | INDEPENDENT | 9 | 1.3 | 6 | 1 | 5 |  |  | 45 | m2-LxH | OFF HIRED | 2022-07-20 | 2022-09-29 | 100% |  | 10.2857 | 14 | 0.84 | 630 | 37.8 | 441 | 189 | 388.8 | 1018.8 | 1018.8 | 0
| 1 | 733 | 12989 | 7827 |  | Basement Residence | Access Scaffold |  | Tower | 1.8 | 1.3 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-08-13 | 2022-08-16 | 100% |  | 0.57143 | 135 | 12.25 | 540 | 49 | 378 | 162 | 28 | 568 | 568 | 0
| 1 | 734 | 12990 | 8291 |  | Basement 1 Residence | Access Scaffold |  | Independent | 7.5 | 1.3 | 2 | 0 | 2 |  |  | 15 | m2-LxH | OFF HIRED | 2022-08-13 | 2022-11-29 | 100% |  | 15.5714 | 14 | 0.84 | 210 | 12.6 | 147 | 63 | 196.2 | 406.2 | 406.2 | 0
| 1 | 734 | 12990 | 8291 |  | Basement 1 Residence | Access Scaffold |  | Independent | 4 | 1.3 | 2 | 0 | 2 |  |  | 8 | m2-LxH | OFF HIRED | 2022-08-13 | 2022-11-29 | 100% |  | 15.5714 | 14 | 0.84 | 112 | 6.72 | 78.4 | 33.6 | 104.64 | 216.64 | 216.64 | 0
| 1 | 751 | 13017 | 7875 |  | Basement 1 Residence | Access Scaffold |  | Independent | 7.5 | 1.3 | 5.5 | 1 | 4.5 |  |  | 33.75 | m2-LxH | OFF HIRED | 2022-08-17 | 2022-09-06 | 100% |  | 3 | 14 | 0.84 | 472.5 | 28.35 | 330.75 | 141.75 | 85.05 | 557.55 | 557.55 | 0
| 1 | 752 | 13017 | 7875 |  | Basement 1 Residence | Access Scaffold |  | Independent | 7.5 | 1.3 | 5.5 | 1 | 4.5 |  |  | 33.75 | m2-LxH | OFF HIRED | 2022-08-17 | 2022-09-06 | 100% |  | 3 | 14 | 0.84 | 472.5 | 28.35 | 330.75 | 141.75 | 85.05 | 557.55 | 557.55 | 0
| 1 | 752A | 13017 | 7875 |  | Basement 1 Residence | Access Scaffold |  | Independent | 7.5 | 1.3 | 5.5 | 1 | 4.5 |  |  | 33.75 | m2-LxH | OFF HIRED | 2022-08-17 | 2022-09-06 | 100% |  | 3 | 14 | 0.84 | 472.5 | 28.35 | 330.75 | 141.75 | 85.05 | 557.55 | 557.55 | 0
| 1 | 752B | 13065 | 6748 |  | Basement 1 Residence | Access Scaffold |  | Independent | 10 | 1.3 | 4.5 |  | 4.5 |  |  | 45 | m2-LxH | OFF HIRED | 2022-08-23 | 2022-09-29 | 100% |  | 5.4286 | 14 | 0.84 | 630 | 37.8 | 441 | 189 | 205.2 | 835.2 | 835.2 | 0
| 1 | 811 | 13074 | 7850 |  | Basement 1 Residence | Access Scaffold |  | Independent | 13 | 1.3 | 4 |  | 4 |  |  | 52 | m2-LxH | OFF HIRED | 2022-08-24 | 2022-08-29 | 100% |  | 0.85714 | 14 | 0.84 | 728 | 43.68 | 509.6 | 218.4 | 37.44 | 765.44 | 765.44 | 0
| 1 | 639 | 12974 | 6748 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 6 | 2.5 | 5 | 1 | 4 |  |  | 60 | m3 | OFF HIRED | 2022-08-11 | 2022-09-29 | 100% |  | 7.1429 | 7.5 | 0.7 | 450 | 42 | 315 | 135 | 300 | 750 | 750 | 0
| 1 | 857 | 13128 | 7863 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3.5 |  | 3.5 |  |  | 3.5 | rm | OFF HIRED | 2022-08-30 | 2022-09-01 | 100% |  | 0.42857 | 135 | 12.25 | 472.5 | 42.875 | 330.75 | 141.75 | 18.375 | 490.875 | 490.875 | 0
| 1 | 882 | 13252 | 7875 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 2.5 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-09-03 | 2022-09-06 | 100% |  | 0.57143 | 135 | 12.25 | 540 | 49 | 378 | 162 | 28 | 568 | 568 | 0
| 1 | 768 | 13254 | 7873 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-09-03 | 2022-09-06 | 100% |  | 0.57143 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 21 | 426 | 426 | 0
| 1 | 798 | 13098 | 8076 |  | Basement 1 Residence | Access Scaffold |  | Independent | 5 | 1.3 | 4 |  | 4 |  |  | 20 | m2-LxH | OFF HIRED | 2022-08-26 | 2022-10-03 | 100% |  | 5.5714 | 14 | 0.84 | 280 | 16.8 | 196 | 84 | 93.6 | 373.6 | 373.6 | 0
| 1 | 893 | 13264 | 6712 |  | Basement 1 Residence | Access Scaffold |  | Independent | 14 | 1.3 | 4 |  | 4 |  |  | 56 | m2-LxH | OFF HIRED | 2022-09-05 | 2022-09-24 | 100% |  | 2.8571 | 14 | 0.84 | 784 | 47.04 | 548.8 | 235.2 | 134.4 | 918.4 | 918.4 | 0
| 1 | 905 | 13279 | 8076 |  | Basement 1 Residence | Access Scaffold |  | Independent | 13.5 | 1.3 | 4 |  | 4 |  |  | 54 | m2-LxH | OFF HIRED | 2022-09-07 | 2022-10-03 | 100% |  | 3.8571 | 14 | 0.84 | 756 | 45.36 | 529.2 | 226.8 | 174.96 | 930.96 | 930.96 | 0
| 1 | 956 | 13331 | 8075 |  | Basement 1 Residence | Access Scaffold |  | Independent | 12.5 | 1.3 | 4 |  | 4 |  |  | 50 | m2-LxH | OFF HIRED | 2022-09-14 | 2022-10-05 | 100% |  | 3.1429 | 14 | 0.84 | 700 | 42 | 490 | 210 | 132 | 832 | 832 | 0
| 1 | 885 | 13256 | 7881 |  | Besement 1 Residence | Birdcage Scaffold |  | Birdcage | 7 | 2.5 | 4 |  | 4 |  |  | 70 | m3 | OFF HIRED | 2022-09-03 | 2022-09-10 | 100% |  | 1.1429 | 7.5 | 0.7 | 525 | 49 | 367.5 | 157.5 | 56 | 581 | 581 | 0
| 1 | 1031 | 13468 | 8087 |  | Basement 1 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-09-23 | 2022-10-07 | 100% |  | 2.1429 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 65.625 | 403.125 | 403.125 | 0
| 1 | 1050 | 13489 | 8098 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-26 | 2022-10-12 | 100% |  | 2.4286 | 135 | 12.25 | 270 | 24.5 | 189 | 0 | 59.5 | 248.5 | 248.5 | 0
| 1 | 1052 | 13491 | 6715 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-09-24 | 2022-09-25 | 100% |  | 0.28571 | 135 | 12.25 | 540 | 49 | 378 | 162 | 14 | 554 | 554 | 0
| 1 | 1020 | 13455 | 8059 |  | Basement 1 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-09-22 | 2022-10-03 | 100% |  | 1.7143 | 135 | 12.25 | 540 | 49 | 378 | 162 | 84 | 624 | 624 | 0
| 1 | 406 | 13460 | 8156 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-09-22 | 2022-10-27 | 100% |  | 5.1429 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 189 | 594 | 594 | 0
| 1 | 406 | 13460 | 8156 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-09-22 | 2022-10-27 | 100% |  | 5.1429 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 189 | 594 | 594 | 0
| 1 | 956 | 13372 | 8075 |  | Basement 1 Residence | Access Scaffold |  | Independent | 17.5 | 1.3 | 3.5 |  | 3.5 |  |  | 61.25 | m2-LxH | OFF HIRED | 2022-09-17 | 2022-10-05 | 100% |  | 2.7143 | 14 | 0.84 | 857.5 | 51.45 | 600.25 | 257.25 | 139.65 | 997.15 | 997.15 | 0
| 1 | 968 | 13373 | 8156 |  | Basement 1 Residence | Access Scaffold |  | Independent | 11.5 | 1.3 | 4.5 |  | 4.5 |  |  | 51.75 | m2-LxH | OFF HIRED | 2022-09-17 | 2022-10-27 | 100% |  | 5.8571 | 14 | 0.84 | 724.5 | 43.47 | 507.15 | 217.35 | 254.61 | 979.11 | 979.11 | 0
| 1 | 1000 | 13384 | 8075 |  | Basement 1Hotel | Access Scaffold |  | Independent | 7 | 1.3 | 2.5 |  | 2.5 |  |  | 17.5 | m2-LxH | OFF HIRED | 2022-09-20 | 2022-10-05 | 100% |  | 2.2857 | 14 | 0.84 | 245 | 14.7 | 171.5 | 73.5 | 33.6 | 278.6 | 278.6 | 0
| 1 | 1002 | 13386 | 8261 |  | Basement 1 Residence | Access Scaffold |  | Independent | 14.5 | 1.3 | 4.5 |  | 4.5 |  |  | 65.25 | m2-LxH | OFF HIRED | 2022-09-20 | 2022-11-20 | 100% |  | 8.8571 | 14 | 0.84 | 913.5 | 54.81 | 639.45 | 274.05 | 485.46 | 1398.96 | 1398.96 | 0
| 1 | 969 | 13363 | 8059 |  | Basement 1 Residence | Access Scaffold |  | Independent | 13.5 | 1.3 | 4.5 |  | 4.5 |  |  | 60.75 | m2-LxH | OFF HIRED | 2022-09-17 | 2022-10-03 | 100% |  | 2.4286 | 14 | 0.84 | 850.5 | 51.03 | 595.35 | 255.15 | 123.93 | 974.43 | 974.43 | 0
| 1 | 985 | 13364 | 8087 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 20 | 1.3 | 4.5 |  | 4.5 |  |  | 90 | m2-LxH | OFF HIRED | 2022-09-17 | 2022-10-07 | 100% |  | 3 | 14 | 0.84 | 1260 | 75.6 | 882 | 378 | 226.8 | 1486.8 | 1486.8 | 0
| 1 | 989 | 13369 | 8308 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 5.5 | 1.8 | 4.5 |  | 4.5 |  |  | 24.75 | m2-LxH | OFF HIRED | 2022-09-17 | 2022-12-06 | 100% |  | 11.5714 | 18 | 1.05 | 445.5 | 25.9875 | 311.85 | 133.65 | 300.7125 | 746.2125 | 746.2125 | 0
| 1 | 1000 | 13384 | 8075 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 5 | 2.5 | 2.5 |  | 2.5 |  |  | 31.25 | m3 | OFF HIRED | 2022-09-20 | 2022-10-05 | 100% |  | 2.2857 | 7.5 | 0.7 | 234.375 | 21.875 | 164.0625 | 70.3125 | 50 | 284.375 | 284.375 | 0
| 1 | 946 | 13321 | 6702 |  | Basement 2 To Ground Floor Residence | Access Scaffold |  | Independent | 44.5 | 1 | 2.5 |  | 2.5 |  |  | 111.25 | m2-LxH | OFF HIRED | 2022-09-12 | 2022-09-20 | 100% |  | 1.2857 | 14 | 0.84 | 1557.5 | 93.45 | 1090.25 | 467.25 | 120.15 | 1677.65 | 1677.65 | 0
| 1 | 1102 | 13535 | 8058 |  | Basment 1 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-10-01 | 2022-10-03 | 100% |  | 0.42857 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 13.125 | 350.625 | 350.625 | 0
| 1 | 1110 | 13544 | 8301 |  | Basment 1 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-10-03 | 2022-12-04 | 100% |  | 9 | 135 | 12.25 | 540 | 49 | 378 | 162 | 441 | 981 | 981 | 0
| 1 | 1252 | 13790 | 8131 |  | Basment 1 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 4.5 |  | 4.5 |  |  | 4.5 | rm | OFF HIRED | 2022-10-19 | 2022-10-20 | 100% |  | 0.28571 | 135 | 12.25 | 607.5 | 55.125 | 425.25 | 182.25 | 15.75 | 623.25 | 623.25 | 0
| 1 | 1182 | 13667 | 8493 |  | Basement 1 Residence | Access Scaffold |  | Independent | 9 | 1.3 | 4 |  | 4 |  |  | 36 | m2-LxH | OFF HIRED | 2022-10-11 | 2023-01-05 | 100% |  | 12.4286 | 14 | 0.84 | 504 | 30.24 | 352.8 | 151.2 | 375.84 | 879.84 | 879.84 | 0
| 1 | 1180 | 13665 | 8186 |  | Basement 1 Residence | Access Scaffold |  | Independent | 13 | 1 | 4 |  | 4 |  |  | 52 | m2-LxH | OFF HIRED | 2022-10-11 | 2022-11-02 | 100% |  | 3.2857 | 14 | 0.84 | 728 | 43.68 | 509.6 | 218.4 | 143.52 | 871.52 | 871.52 | 0
| 1 | 1125 | 13609 | 8184 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 10 | 1.3 | 3 |  | 3 |  |  | 30 | m2-LxH | OFF HIRED | 2022-10-04 | 2022-11-02 | 100% |  | 4.2857 | 14 | 0.84 | 420 | 25.2 | 294 | 126 | 108 | 528 | 528 | 0
| 1 | 1120 | 13604 | 8247 |  | Basement 1 Residence | Access Scaffold |  | Independent | 37.5 | 1.3 | 4.5 |  | 4.5 |  |  | 168.75 | m2-LxH | OFF HIRED | 2022-10-04 | 2022-11-17 | 100% |  | 6.4286 | 14 | 0.84 | 2362.5 | 141.75 | 1653.75 | 708.75 | 911.25 | 3273.75 | 3273.75 | 0
| 1 | 1185 | 13670 | 8225 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 7.5 | 1.3 | 2.5 |  | 2.5 |  |  | 18.75 | m2-LxH | OFF HIRED | 2022-10-12 | 2022-11-11 | 100% |  | 4.4286 | 14 | 0.84 | 262.5 | 15.75 | 183.75 | 78.75 | 69.75 | 332.25 | 332.25 | 0
| 1 | 1206 | 13692 | 8131 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 2.5 | 1 | 1 |  | 1 |  |  | 2.5 | m2-LxH | OFF HIRED | 2022-10-14 | 2022-10-20 | 100% |  | 1 | 14 | 0.84 | 35 | 2.1 | 24.5 | 10.5 | 2.1 | 37.1 | 37.1 | 0
| 1 | 1113 | 13547 | 8078 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 13 | 0.6 | 2 |  | 2 |  |  | 26 | m2-LxH | OFF HIRED | 2022-10-03 | 2022-10-07 | 100% |  | 0.71429 | 14 | 0.84 | 364 | 21.84 | 254.8 | 109.2 | 15.6 | 379.6 | 379.6 | 0
| 1 | 1112 | 13546 | 8119 |  | Bsement 1 Resedence | Access Scaffold |  | Independent | 5 | 1.3 | 4 |  | 4 |  |  | 20 | m2-LxH | OFF HIRED | 2022-10-03 | 2022-10-14 | 100% |  | 1.7143 | 14 | 0.84 | 280 | 16.8 | 196 | 84 | 28.8 | 308.8 | 308.8 | 0
| 1 | 1115 | 13549 | 8314 |  | Basement 2 to Level 4 Residence | Access Scaffold |  | Independent | 90 | 0.6 | 2 |  | 2 |  |  | 180 | m2-LxH | OFF HIRED | 2022-10-03 | 2022-12-09 | 100% |  | 9.7143 | 14 | 0.84 | 2520 | 151.2 | 1764 | 756 | 1468.8 | 3988.8 | 3988.8 | 0
| 1 | 1147 | 13632 | 8087 |  | Basement 1 Residence | Access Scaffold |  | Independent | 27 | 1.3 | 3.5 |  | 3.5 |  |  | 94.5 | m2-LxH | OFF HIRED | 2022-10-07 | 2022-10-07 | 100% |  | 0.14286 | 14 | 0.84 | 1323 | 79.38 | 926.1 | 396.9 | 11.34 | 1334.34 | 1334.34 | 0
| 1 | 1152 | 13637 | 8137 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 5.6 | 1.3 | 2 |  | 2 |  |  | 11.2 | m2-LxH | OFF HIRED | 2022-10-07 | 2022-10-24 | 100% |  | 2.5714 | 14 | 0.84 | 156.8 | 9.408 | 109.76 | 47.04 | 24.192 | 180.992 | 180.992 | 0
| 1 | 1148 | 13636 | 8266 |  | Basement 1 Residence | Access Scaffold |  | Independent | 7.8 | 1.3 | 2 |  | 2 |  |  | 15.6 | m2-LxH | OFF HIRED | 2022-10-07 | 2022-11-22 | 100% |  | 6.7143 | 14 | 0.84 | 218.4 | 13.104 | 152.88 | 65.52 | 87.984 | 306.384 | 306.384 | 0
| 1 | 1157 | 13642 | 8094 |  | Basement 2 Residence | Access Scaffold |  | Independent | 23.5 | 1.3 | 3.5 |  | 3.5 |  |  | 82.25 | m2-LxH | OFF HIRED | 2022-10-07 | 2022-10-10 | 100% |  | 0.57143 | 14 | 0.84 | 1151.5 | 69.09 | 806.05 | 345.45 | 39.48 | 1190.98 | 1190.98 | 0
| 1 | 1164 | 13649 | 8096 |  | Basement 1 Residence | Access Scaffold |  | Independent | 6.5 | 1.3 | 4 |  | 4 |  |  | 26 | m2-LxH | OFF HIRED | 2022-10-10 | 2022-10-12 | 100% |  | 0.42857 | 14 | 0.84 | 364 | 21.84 | 254.8 | 109.2 | 9.36 | 373.36 | 373.36 | 0
| 1 | 1059 | 13496 | 8075 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 25 | 1.3 | 2.5 |  | 2.5 |  |  | 62.5 | m2-LxH | OFF HIRED | 2022-09-26 | 2022-10-05 | 100% |  | 1.4286 | 14 | 0.84 | 875 | 52.5 | 612.5 | 262.5 | 75 | 950 | 950 | 0
| 1 | 1073 | 13509 | 8245 |  | Basement 1 Residence | Access Scaffold |  | Independent | 20 | 1.3 | 3 |  | 3 |  |  | 60 | m2-LxH | OFF HIRED | 2022-09-28 | 2022-11-16 | 100% |  | 7.1429 | 14 | 0.84 | 840 | 50.4 | 588 | 252 | 360 | 1200 | 1200 | 0
| 1 | 1084 | 13517 | 8214 |  | Basement 1 Residence | Access Scaffold |  | Independent | 15 | 1.3 | 3 |  | 3 |  |  | 45 | m2-LxH | OFF HIRED | 2022-09-29 | 2022-11-09 | 100% |  | 6 | 14 | 0.84 | 630 | 37.8 | 441 | 189 | 226.8 | 856.8 | 856.8 | 0
| 1 | 1085 | 13518 | 8102 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 29 | 1.3 | 4 |  | 4 |  |  | 116 | m2-LxH | OFF HIRED | 2022-09-29 | 2022-10-13 | 100% |  | 2.1429 | 14 | 0.84 | 1624 | 97.44 | 1136.8 | 487.2 | 208.8 | 1832.8 | 1832.8 | 0
| 1 | 1088 | 13521 | 8078 |  | Basement 1 To Ground Floor Residence | Access Scaffold |  | Independent | 25 | 1 | 2 |  | 2 |  |  | 50 | m2-LxH | OFF HIRED | 2022-09-29 | 2022-10-07 | 100% |  | 1.2857 | 14 | 0.84 | 700 | 42 | 490 | 210 | 54 | 754 | 754 | 0
| 1 | 1103 | 13536 | 8059 |  | Basement 2 Residence | Access Scaffold |  | Independent | 30 | 1.3 | 3 |  | 3 |  |  | 90 | m2-LxH | OFF HIRED | 2022-10-01 | 2022-10-03 | 100% |  | 0.42857 | 14 | 0.84 | 1260 | 75.6 | 882 | 378 | 32.4 | 1292.4 | 1292.4 | 0
| 1 | 1126 | 13610 | 8099 |  | Basement 1 Residence | Access Scaffold |  | Independent | 7.5 | 1.3 | 2.5 |  | 2.5 |  |  | 18.75 | m2-LxH | OFF HIRED | 2022-10-04 | 2022-10-12 | 100% |  | 1.2857 | 14 | 0.84 | 262.5 | 15.75 | 183.75 | 78.75 | 20.25 | 282.75 | 282.75 | 0
| 1 | 1217 | 13753 | 8574 |  | Basement 1 Residence | Access Scaffold |  | Independent | 12 | 1.3 | 5 |  | 5 |  |  | 60 | m2-LxH | OFF HIRED | 2022-10-15 | 2023-02-18 | 100% |  | 18.1429 | 14 | 0.84 | 840 | 50.4 | 588 | 252 | 914.4 | 1754.4 | 1372.8 | 381.6 |  |  | #VALUE! | 588 | #VALUE! | #VALUE!
| 1 | 1223 | 13760 | 8475 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 16 | 1.3 | 2.5 |  | 2.5 |  |  | 40 | m2-LxH | OFF HIRED | 2022-10-15 | 2022-12-30 | 100% |  | 11 | 14 | 0.84 | 560 | 33.6 | 392 | 168 | 369.6 | 929.6 | 929.6 | 0
| 1 | 1237 | 13775 | 8487 |  | Basement 1 Residence | Access Scaffold |  | Independent | 13 | 1.3 | 3.5 |  | 3.5 |  |  | 45.5 | m2-LxH | OFF HIRED | 2022-10-17 | 2023-01-03 | 100% |  | 11.2857 | 14 | 0.84 | 637 | 38.22 | 445.9 | 191.1 | 431.34 | 1068.34 | 1068.34 | 0
| 1 | 1175 | 13660 | 8475 |  | Basement 1 Residence | Access Scaffold |  | Independent | 20 | 1.3 | 3.5 |  | 3.5 |  |  | 70 | m2-LxH | OFF HIRED | 2022-10-10 | 2022-12-30 | 100% |  | 11.7143 | 14 | 0.84 | 980 | 58.8 | 686 | 294 | 688.8 | 1668.8 | 1668.8 | 0
| 1 | 1238 | 13776 | 8184 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 8 | 1 | 2.5 |  | 2.5 |  |  | 20 | m2-LxH | OFF HIRED | 2022-10-17 | 2022-11-02 | 100% |  | 2.4286 | 14 | 0.84 | 280 | 16.8 | 196 | 84 | 40.8 | 320.8 | 320.8 | 0
| 1 | 1292 | 13731 | 8195 |  | Basement 1 To Ground Floor Residence | Access Scaffold |  | Independent | 6 | 1.3 | 1.5 |  | 1.5 |  |  | 9 | m2-LxH | OFF HIRED | 2022-10-25 | 2022-11-05 | 100% |  | 1.7143 | 14 | 0.84 | 126 | 7.56 | 88.2 | 37.8 | 12.96 | 138.96 | 138.96 | 0
| 1 | 1107 | 13541 | 8217 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 8 | 1.3 | 3.5 |  | 3.5 |  |  | 28 | m2-LxH | OFF HIRED | 2022-10-01 | 2022-11-09 | 100% |  | 5.7143 | 14 | 0.84 | 392 | 23.52 | 274.4 | 117.6 | 134.4 | 526.4 | 526.4 | 0
| 1 | 1179 | 13664 | 8116 |  | Basement 1 Residence | Access Scaffold |  | Independent | 23.5 | 1.3 | 4 |  | 4 |  |  | 94 | m2-LxH | OFF HIRED | 2022-10-11 | 2022-10-18 | 100% |  | 1.1429 | 14 | 0.84 | 1316 | 78.96 | 921.2 | 394.8 | 90.24 | 1406.24 | 1406.24 | 0
| 1 | 1112 | 13546 | 8119 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 7.5 | 1.3 | 2 |  | 2 |  |  | 15 | m2-LxH | OFF HIRED | 2022-10-03 | 2022-10-14 | 100% |  | 1.7143 | 14 | 0.84 | 210 | 12.6 | 147 | 63 | 21.6 | 231.6 | 231.6 | 0
| 1 | 1220 | 13756 | 8110 |  | Basement 1 Residence | Access Scaffold |  | Independent | 12.5 | 1.3 | 2.5 |  | 2.5 |  |  | 31.25 | m2-LxH | OFF HIRED | 2022-10-15 | 2022-10-16 | 100% |  | 0.28571 | 14 | 0.84 | 437.5 | 26.25 | 306.25 | 131.25 | 7.5 | 445 | 445 | 0
| 1 | 1186 | 13671 | 8110 |  | Basement 1 Residence | Access Scaffold |  | Independent | 6.3 | 1 | 4 |  | 4 |  |  | 25.2 | m2-LxH | OFF HIRED | 2022-10-12 | 2022-10-16 | 100% |  | 0.71429 | 14 | 0.84 | 352.8 | 21.168 | 246.96 | 105.84 | 15.12 | 367.92 | 367.92 | 0
| 1 | 1264 | 13702 | 8406 |  | Basement 1 Residence | Access Scaffold |  | Independent | 12 | 1.3 | 3 |  | 3 |  |  | 36 | m2-LxH | OFF HIRED | 2022-10-21 | 2023-01-09 | 100% |  | 11.5714 | 14 | 0.84 | 504 | 30.24 | 352.8 | 151.2 | 349.92 | 853.92 | 853.92 | 0
| 1 | 1265 | 13703 | 8589 |  | Basement 1 Residence | Access Scaffold |  | Independent | 22 | 1.3 | 4 |  | 4 |  |  | 88 | m2-LxH | OFF HIRED | 2022-10-21 | 2023-02-21 | 100% |  | 17.7143 | 14 | 0.84 | 1232 | 73.92 | 862.4 | 369.6 | 1309.44 | 2541.44 | 1950.08 | 591.36 |  |  | #VALUE! | 862.4 | #VALUE! | #VALUE!
| 1 | 1270 | 13708 | 8252 |  | Basement 1 Residence | Access Scaffold |  | Independent | 12.5 | 1.3 | 4 |  | 4 |  |  | 50 | m2-LxH | OFF HIRED | 2022-10-21 | 2022-11-18 | 100% |  | 4.1429 | 14 | 0.84 | 700 | 42 | 490 | 210 | 174 | 874 | 874 | 0
| 1 | 1275 | 13713 | 8137 |  | Basement 2 Residence | Access Scaffold |  | Independent | 23 | 1.3 | 2 |  | 2 |  |  | 46 | m2-LxH | OFF HIRED | 2022-10-21 | 2022-10-24 | 100% |  | 0.57143 | 14 | 0.84 | 644 | 38.64 | 450.8 | 193.2 | 22.08 | 666.08 | 666.08 | 0
| 1 | 1280 | 13719 | 8458 |  | Basement 1 Residence | Access Scaffold |  | Independent | 7.5 | 1.3 | 4 |  | 4 |  |  | 30 | m2-LxH | OFF HIRED | 2022-10-24 | 2022-12-23 | 100% |  | 8.7143 | 14 | 0.84 | 420 | 25.2 | 294 | 126 | 219.6 | 639.6 | 639.6 | 0
| 1 | 1293 | 13732 | 8186 |  | Basement 1 To Ground Floor Residence | Access Scaffold |  | Independent | 11 | 1 | 1.5 |  | 1.5 |  |  | 16.5 | m2-LxH | OFF HIRED | 2022-10-25 | 2022-11-02 | 100% |  | 1.2857 | 14 | 0.84 | 231 | 13.86 | 161.7 | 69.3 | 17.82 | 248.82 | 248.82 | 0
| 1 | 1082 | 13515 | 8140 |  | Basement 1 To Ground Floor Hotel | Access Scaffold |  | Independent | 32 | 0.6 | 2 |  | 2 |  |  | 64 | m2-LxH | OFF HIRED | 2022-09-29 | 2022-10-23 | 100% |  | 3.5714 | 14 | 0.84 | 896 | 53.76 | 627.2 | 268.8 | 192 | 1088 | 1088 | 0
| 1 | 1186 | 13671 | 8110 |  | Basement 1 Residence | Access Scaffold |  | Independent | 4 | 1.8 | 4 |  | 4 |  |  | 16 | m2-LxH | OFF HIRED | 2022-10-12 | 2022-10-16 | 100% |  | 0.71429 | 18 | 1.05 | 288 | 16.8 | 201.6 | 86.4 | 12 | 300 | 300 | 0
| 1 | 1205 | 13691 | 8225 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 5 | 1.8 | 3 |  | 3 |  |  | 15 | m2-LxH | OFF HIRED | 2022-10-14 | 2022-11-01 | 100% |  | 2.7143 | 18 | 1.05 | 270 | 15.75 | 189 | 81 | 42.75 | 312.75 | 312.75 | 0
| 1 | 1196 | 13676 | 8332 |  | Basement 1 Residence | Access Scaffold |  | Independent | 7.5 | 1.8 | 2.5 |  | 2.5 |  |  | 18.75 | m2-LxH | OFF HIRED | 2022-10-12 | 2022-12-15 | 100% |  | 9.2857 | 18 | 1.05 | 337.5 | 19.6875 | 236.25 | 101.25 | 182.8125 | 520.3125 | 520.3125 | 0
| 1 | 1262 | 13800 | 8347 |  | Basement 2 Hotel | Access Scaffold |  | Independent | 11.3 | 1.8 | 2.5 |  | 2.5 |  |  | 28.25 | m2-LxH | OFF HIRED | 2022-10-21 | 2022-12-20 | 100% |  | 8.7143 | 18 | 1.05 | 508.5 | 29.6625 | 355.95 | 152.55 | 258.4875 | 766.9875 | 766.9875 | 0
| 1 | 1184 | 13669 | 8493 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 4 | 4 | 2.5 |  | 2.5 |  |  | 40 | m3 | OFF HIRED | 2022-10-12 | 2023-01-05 | 100% |  | 12.2857 | 7.5 | 0.7 | 300 | 28 | 210 | 90 | 344 | 644 | 644 | 0
| 1 | 1202 | 13688 | 8137 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 4.3 | 2.5 | 3.5 |  | 3.5 |  |  | 37.625 | m3 | OFF HIRED | 2022-10-13 | 2022-10-24 | 100% |  | 1.7143 | 7.5 | 0.7 | 282.1875 | 26.3375 | 197.5312 | 84.6562 | 45.15 | 327.3375 | 327.3375 | 0
| 1 | 1114 | 13548 | 8309 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 2 |  | 2 |  |  | 20 | m3 | OFF HIRED | 2022-10-03 | 2022-12-06 | 100% |  | 9.2857 | 7.5 | 0.7 | 150 | 14 | 105 | 45 | 130 | 280 | 280 | 0
| 1 | 1161 | 13646 | 8185 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 4.3 | 2.5 | 3.5 |  | 3.5 |  |  | 37.625 | m3 | OFF HIRED | 2022-10-10 | 2022-11-02 | 100% |  | 3.4286 | 7.5 | 0.7 | 282.1875 | 26.3375 | 197.5312 | 84.6562 | 90.3 | 372.4875 | 372.4875 | 0
| 1 | 1060 | 13497 | 8102 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 3.5 |  | 3.5 |  |  | 35 | m3 | OFF HIRED | 2022-09-26 | 2022-10-13 | 100% |  | 2.5714 | 7.5 | 0.7 | 262.5 | 24.5 | 183.75 | 78.75 | 63 | 325.5 | 325.5 | 0
| 1 | `1087 | 13520 | 8225 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 2.6 | 2.5 | 3 |  | 3 |  |  | 19.5 | m3 | OFF HIRED | 2022-09-29 | 2022-11-11 | 100% |  | 6.2857 | 7.5 | 0.7 | 146.25 | 13.65 | 102.375 | 43.875 | 85.8 | 232.05 | 232.05 | 0
| 1 | 1107 | 13541 | 8217 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 2.5 |  | 2.5 |  |  | 25 | m3 | OFF HIRED | 2022-10-01 | 2022-11-09 | 100% |  | 5.7143 | 7.5 | 0.7 | 187.5 | 17.5 | 131.25 | 56.25 | 100 | 287.5 | 287.5 | 0
| 1 | 1131 | 13615 | 8131 |  | Bsement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 2 |  | 2 |  |  | 12.5 | m3 | OFF HIRED | 2022-10-04 | 2022-10-20 | 100% |  | 2.4286 | 7.5 | 0.7 | 93.75 | 8.75 | 65.625 | 28.125 | 21.25 | 115 | 115 | 0
| 1 | 1132 | 13616 | 8242 |  | Bsement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 4 |  | 4 |  |  | 25 | m3 | OFF HIRED | 2022-10-04 | 2022-11-16 | 100% |  | 6.2857 | 7.5 | 0.7 | 187.5 | 17.5 | 131.25 | 56.25 | 110 | 297.5 | 297.5 | 0
| 1 | 1216 | 13752 | 8308 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 5 | 2.5 | 2.5 |  | 2.5 |  |  | 31.25 | m3 | OFF HIRED | 2022-10-15 | 2022-12-06 | 100% |  | 7.5714 | 7.5 | 0.7 | 234.375 | 21.875 | 164.0625 | 70.3125 | 165.625 | 400 | 400 | 0
| 1 | 1219 | 13755 | 8242 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 2.5 |  | 2.5 |  |  | 25 | m3 | OFF HIRED | 2022-10-15 | 2022-11-16 | 100% |  | 4.7143 | 7.5 | 0.7 | 187.5 | 17.5 | 131.25 | 56.25 | 82.5 | 270 | 270 | 0
| 1 | 1232 | 13769 | 8185 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 3 |  | 3 |  |  | 30 | m3 | OFF HIRED | 2022-10-16 | 2022-11-02 | 100% |  | 2.5714 | 7.5 | 0.7 | 225 | 21 | 157.5 | 67.5 | 54 | 279 | 279 | 0
| 1 | 1196A | 13681 | 8232 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 2 |  | 2 |  |  | 20 | m3 | OFF HIRED | 2022-10-12 | 2022-11-13 | 100% |  | 4.7143 | 7.5 | 0.7 | 150 | 14 | 105 | 45 | 66 | 216 | 216 | 0
| 1 | 1263 | 13714 | 8472 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 12 | 8 | 3 |  | 3 |  |  | 288 | m3 | OFF HIRED | 2022-10-21 | 2022-12-27 | 100% |  | 9.7143 | 7.5 | 0.7 | 2160 | 201.6 | 1512 | 648 | 1958.4 | 4118.4 | 4118.4 | 0
| 1 | 1082 | 13515 | 8140 |  | Basement To Ground Floor Hotel | Boarded Lift |  | Board Lift | 4 | 2.5 |  |  |  | 1 |  | 10 | m2-LxW | OFF HIRED | 2022-09-29 | 2022-10-23 | 100% |  | 3.5714 | 7.5 | 1.05 | 75 | 10.5 | 52.5 | 22.5 | 37.5 | 112.5 | 112.5 | 0
| 1 | 1085 | 13518 | 8102 |  | Basement 1 Hotel | Cantiliver |  | Cantiliver | 14 | 1.2 |  |  |  | 1 |  | 16.8 | m2-LxW | OFF HIRED | 2022-09-29 | 2022-10-13 | 100% |  | 2.1429 | 36.5 | 3.15 | 613.2 | 52.92 | 429.24 | 183.96 | 113.4 | 726.6 | 726.6 | 0
| 1 | 1322 | 13810 | 8177 |  | Basement 2 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-10-30 | 2022-10-31 | 100% |  | 0.28571 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 10.5 | 415.5 | 415.5 | 0
| 1 | 1305 | 13743 | 8156 |  | Basement 1 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.8 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-10-27 | 2022-10-27 | 100% |  | 0.14286 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 3.5 | 273.5 | 273.5 | 0
| 1 | 1309 | 13747 | 8206 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-10-28 | 2022-11-07 | 100% |  | 1.5714 | 135 | 12.25 | 540 | 49 | 378 | 162 | 77 | 617 | 617 | 0
| 1 | 1308 | 13746 |  |  | Basement 2 Residence | HEAVY DUTY TOWER |  | Tower | 1 | 1 | 8 |  | 8 |  |  | 8 | rm | ON HIRE | 2022-10-28 |  | 100% |  | 17.7143 | 135 | 12.25 | 1080 | 98 | 756 | 0 | 1736 | 2492 | 2100 | 392 |  |  | #VALUE! | 756 | #VALUE! | #VALUE!
| 1 | 1296 | 13735 | 8161 |  | Basement 1 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-10-26 | 2022-10-28 | 100% |  | 0.42857 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 15.75 | 420.75 | 420.75 | 0
| 1 | 1428 | 13916 | 8332 |  | Basement 1 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.8 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-11-12 | 2022-12-15 | 100% |  | 4.8571 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 119 | 389 | 389 | 0
| 1 | 1379 | 13867 | 8471 |  | Basement 2 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-11-06 | 2022-12-26 | 100% |  | 7.2857 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 223.125 | 560.625 | 560.625 | 0
| 1 | 1455 | 13943 | 8267 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 3.5 |  | 3.5 |  |  | 3.5 | rm | OFF HIRED | 2022-11-18 | 2022-11-23 | 100% |  | 0.85714 | 135 | 12.25 | 472.5 | 42.875 | 330.75 | 141.75 | 36.75 | 509.25 | 509.25 | 0
| 1 | 1325 | 13813 | 8456 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 2.5 |  | 2.5 |  |  | 12.5 | m2-LxH | OFF HIRED | 2022-10-31 | 2022-12-22 | 100% |  | 7.5714 | 14 | 0.84 | 175 | 10.5 | 122.5 | 52.5 | 79.5 | 254.5 | 254.5 | 0
| 1 | 1338 | 13826 | 8326 |  | Basement 2 To Ground Floor Residence | Access Scaffold |  | INDEPENDENT | 35 | 1 | 2.5 |  | 2.5 |  |  | 87.5 | m2-LxH | OFF HIRED | 2022-11-01 | 2022-12-13 | 100% |  | 6.1429 | 14 | 0.84 | 1225 | 73.5 | 857.5 | 367.5 | 451.5 | 1676.5 | 1676.5 | 0
| 1 | 1346 | 13834 | 8278 |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 8.5 | 1.3 | 3.7 |  | 3.7 |  |  | 31.45 | m2-LxH | OFF HIRED | 2022-11-02 | 2022-11-26 | 100% |  | 3.5714 | 14 | 0.84 | 440.3 | 26.418 | 308.21 | 132.09 | 94.35 | 534.65 | 534.65 | 0
| 1 | 1345 | 13833 | 8288 |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 12.5 | 1.3 | 2.5 |  | 2.5 |  |  | 31.25 | m2-LxH | OFF HIRED | 2022-11-02 | 2022-11-28 | 100% |  | 3.8571 | 14 | 0.84 | 437.5 | 26.25 | 306.25 | 131.25 | 101.25 | 538.75 | 538.75 | 0
| 1 | 1342 | 13830 | 8347 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 6.8 | 1.3 | 3.5 |  | 3.5 |  |  | 23.8 | m2-LxH | OFF HIRED | 2022-11-01 | 2022-12-20 | 100% |  | 7.1429 | 14 | 0.84 | 333.2 | 19.992 | 233.24 | 99.96 | 142.8 | 476 | 476 | 0
| 1 | 1350 | 13838 | 8235 |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 10.5 | 1.3 | 2 |  | 2 |  |  | 21 | m2-LxH | OFF HIRED | 2022-11-02 | 2022-11-15 | 100% |  | 2 | 14 | 0.84 | 294 | 17.64 | 205.8 | 88.2 | 35.28 | 329.28 | 329.28 | 0
| 1 | 1357 | 13845 | 8186 |  | Basement 1 To Basement 2 Residence | Access Scaffold |  | INDEPENDENT | 13 | 1 | 1.5 |  | 1.5 |  |  | 19.5 | m2-LxH | OFF HIRED | 2022-11-03 | 2022-11-04 | 100% |  | 0.28571 | 14 | 0.84 | 273 | 16.38 | 191.1 | 81.9 | 4.68 | 277.68 | 277.68 | 0
| 1 | 1374 | 13862 | 8232 |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 6.3 | 0.6 | 2.5 |  | 2.5 |  |  | 15.75 | m2-LxH | OFF HIRED | 2022-11-05 | 2022-11-13 | 100% |  | 1.2857 | 14 | 0.84 | 220.5 | 13.23 | 154.35 | 66.15 | 17.01 | 237.51 | 237.51 | 0
| 1 | 1373 | 13861 | 8407 |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 4.3 | 1.3 | 2 |  | 2 |  |  | 8.6 | m2-LxH | OFF HIRED | 2022-11-05 | 2023-01-09 | 100% |  | 9.4286 | 14 | 0.84 | 120.4 | 7.224 | 84.28 | 36.12 | 68.112 | 188.512 | 188.512 | 0
| 1 | 1381 | 13869 | 8235 |  | Basement 2 Residence | Access Scaffold |  | INDEPENDENT | 21.3 | 1 | 3.5 |  | 3.5 |  |  | 74.55 | m2-LxH | OFF HIRED | 2022-11-07 | 2022-11-15 | 100% |  | 1.2857 | 14 | 0.84 | 1043.7 | 62.622 | 730.59 | 313.11 | 80.514 | 1124.214 | 1124.214 | 0
| 1 | 1371 | 13859 | 8331 |  | Basement 1 To Ground Floor Hotel | Access Scaffold |  | INDEPENDENT | 16.5 | 1 | 2 |  | 2 |  |  | 33 | m2-LxH | OFF HIRED | 2022-11-05 | 2022-12-15 | 100% |  | 5.8571 | 14 | 0.84 | 462 | 27.72 | 323.4 | 138.6 | 162.36 | 624.36 | 624.36 | 0
| 1 | 1369 | 13857 | 8236 |  | Basement 2 Residence | Access Scaffold |  | INDEPENDENT | 20 | 1 | 3.5 |  | 3.5 |  |  | 70 | m2-LxH | OFF HIRED | 2022-11-04 | 2022-11-15 | 100% |  | 1.7143 | 14 | 0.84 | 980 | 58.8 | 686 | 294 | 100.8 | 1080.8 | 1080.8 | 0
| 1 | 1368 | 13856 | 8206 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 11.3 | 1 | 2 |  | 2 |  |  | 22.6 | m2-LxH | OFF HIRED | 2022-11-04 | 2022-11-07 | 100% |  | 0.57143 | 14 | 0.84 | 316.4 | 18.984 | 221.48 | 94.92 | 10.848 | 327.248 | 327.248 | 0
| 1 | 1367 | 13855 | 8221 |  | Basement 1 | Access Scaffold |  | INDEPENDENT | 6.1 | 1.3 | 4.5 |  | 4.5 |  |  | 27.45 | m2-LxH | OFF HIRED | 2022-11-04 | 2022-11-10 | 100% |  | 1 | 14 | 0.84 | 384.3 | 23.058 | 269.01 | 115.29 | 23.058 | 407.358 | 407.358 | 0
| 1 | 1297 | 13736 | 8166 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 13.5 | 1 | 1.5 |  | 1.5 |  |  | 20.25 | m2-LxH | OFF HIRED | 2022-10-26 | 2022-10-28 | 100% |  | 0.42857 | 14 | 0.84 | 283.5 | 17.01 | 198.45 | 85.05 | 7.29 | 290.79 | 290.79 | 0
| 1 | 1316 | 13804 | 8347 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 2.5 |  | 2.5 |  |  | 10 | m2-LxH | OFF HIRED | 2022-10-29 | 2022-12-20 | 100% |  | 7.5714 | 14 | 0.84 | 140 | 8.4 | 98 | 42 | 63.6 | 203.6 | 203.6 | 0
| 1 | 1318 | 13803 | 8175 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 6.8 | 1.3 | 3 |  | 3 |  |  | 20.4 | m2-LxH | OFF HIRED | 2022-10-29 | 2022-10-30 | 100% |  | 0.28571 | 14 | 0.84 | 285.6 | 17.136 | 199.92 | 85.68 | 4.896 | 290.496 | 290.496 | 0
| 1 | 1318 | 13806 | 8174 |  | Basement 2 Residence | Access Scaffold |  | INDEPENDENT | 37.5 | 1.3 | 3.5 |  | 3.5 |  |  | 131.25 | m2-LxH | OFF HIRED | 2022-10-29 | 2022-10-30 | 100% |  | 0.28571 | 14 | 0.84 | 1837.5 | 110.25 | 1286.25 | 551.25 | 31.5 | 1869 | 1869 | 0
| 1 | 1415 | 13903 | 8471 |  | Basement 2 Residence | Access Scaffold |  | INDEPENDENT | 29 | 1 | 2 |  | 2 |  |  | 58 | m2-LxH | OFF HIRED | 2022-11-11 | 2022-12-26 | 100% |  | 6.5714 | 14 | 0.84 | 812 | 48.72 | 568.4 | 243.6 | 320.16 | 1132.16 | 1132.16 | 0
| 1 | 1414 | 13902 | 8317 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 36 | 1.3 | 4 |  | 4 |  |  | 144 | m2-LxH | OFF HIRED | 2022-11-11 | 2022-12-09 | 100% |  | 4.1429 | 14 | 0.84 | 2016 | 120.96 | 1411.2 | 604.8 | 501.12 | 2517.12 | 2517.12 | 0
| 1 | 1413 | 13901 | 8309 |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 10 | 1.3 | 1.5 |  | 1.5 |  |  | 15 | m2-LxH | OFF HIRED | 2022-11-11 | 2022-12-06 | 100% |  | 3.7143 | 14 | 0.84 | 210 | 12.6 | 147 | 63 | 46.8 | 256.8 | 256.8 | 0
| 1 | 1416 | 13904 | 8314 |  | Basement 1 To 2 Hotel | Access Scaffold |  | INDEPENDENT | 15 | 1 | 2 |  | 2 |  |  | 30 | m2-LxH | OFF HIRED | 2022-11-11 | 2022-12-09 | 100% |  | 4.1429 | 14 | 0.84 | 420 | 25.2 | 294 | 126 | 104.4 | 524.4 | 524.4 | 0
| 1 | 1418 | 13906 | 8238 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 17.5 | 1 | 2 |  | 2 |  |  | 35 | m2-LxH | OFF HIRED | 2022-11-12 | 2022-11-15 | 100% |  | 0.57143 | 14 | 0.84 | 490 | 29.4 | 343 | 147 | 16.8 | 506.8 | 506.8 | 0
| 1 | 1420 | 13908 | 8252 |  | Basement 1 To Ground Floor Residence | Access Scaffold |  | INDEPENDENT | 10 | 0.6 | 2 |  | 2 |  |  | 20 | m2-LxH | OFF HIRED | 2022-11-12 | 2022-11-18 | 100% |  | 1 | 14 | 0.84 | 280 | 16.8 | 196 | 84 | 16.8 | 296.8 | 296.8 | 0
| 1 | 1424 | 13912 | 8350 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 8 | 1.3 | 4 |  | 4 |  |  | 32 | m2-LxH | OFF HIRED | 2022-11-12 | 2022-12-21 | 100% |  | 5.7143 | 14 | 0.84 | 448 | 26.88 | 313.6 | 134.4 | 153.6 | 601.6 | 601.6 | 0
| 1 | 1423 | 13911 | 8231 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 8.3 | 1.3 | 3.5 |  | 3.5 |  |  | 29.05 | m2-LxH | OFF HIRED | 2022-11-12 | 2022-11-13 | 100% |  | 0.28571 | 14 | 0.84 | 406.7 | 24.402 | 284.69 | 122.01 | 6.972 | 413.672 | 413.672 | 0
| 1 | 1439 | 13927 | 8244 |  | Basement 2 Hotel | Access Scaffold |  | INDEPENDENT | 13.5 | 1 | 1.5 |  | 1.5 |  |  | 20.25 | m2-LxH | OFF HIRED | 2022-11-16 | 2022-11-16 | 100% |  | 0.14286 | 14 | 0.84 | 283.5 | 17.01 | 198.45 | 85.05 | 2.43 | 285.93 | 285.93 | 0
| 1 | 1433 | 13921 | 8242 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 27.5 | 1 | 3.5 |  | 3.5 |  |  | 96.25 | m2-LxH | OFF HIRED | 2022-11-15 | 2022-11-16 | 100% |  | 0.28571 | 14 | 0.84 | 1347.5 | 80.85 | 943.25 | 404.25 | 23.1 | 1370.6 | 1370.6 | 0
| 1 | 1431 | 13919 | 8301 |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 11.3 | 1.3 | 2.5 |  | 2.5 |  |  | 28.25 | m2-LxH | OFF HIRED | 2022-11-12 | 2022-12-04 | 100% |  | 3.2857 | 14 | 0.84 | 395.5 | 23.73 | 276.85 | 118.65 | 77.97 | 473.47 | 473.47 | 0
| 1 | 1388 | 13876 | 8231 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 22.5 | 0.6 | 2 |  | 2 |  |  | 45 | m2-LxH | OFF HIRED | 2022-11-08 | 2022-11-13 | 100% |  | 0.85714 | 14 | 0.84 | 630 | 37.8 | 441 | 189 | 32.4 | 662.4 | 662.4 | 0
| 1 | 1393 | 13881 | 8471 |  | Basement 2 Hotel | Access Scaffold |  | INDEPENDENT | 20 | 1 | 2 |  | 2 |  |  | 40 | m2-LxH | OFF HIRED | 2022-11-08 | 2022-12-26 | 100% |  | 7 | 14 | 0.84 | 560 | 33.6 | 392 | 168 | 235.2 | 795.2 | 795.2 | 0
| 1 | 1394 | 13882 | 8466 |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 14 | 1 | 4 |  | 4 |  |  | 56 | m2-LxH | OFF HIRED | 2022-11-08 | 2022-12-24 | 100% |  | 6.7143 | 14 | 0.84 | 784 | 47.04 | 548.8 | 235.2 | 315.84 | 1099.84 | 1099.84 | 0
| 1 | 1398 | 13886 | 8304 |  | Basement 2 Residence | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 2 |  | 2 |  |  | 10 | m2-LxH | OFF HIRED | 2022-11-09 | 2022-12-06 | 100% |  | 4 | 14 | 0.84 | 140 | 8.4 | 98 | 42 | 33.6 | 173.6 | 173.6 | 0
| 1 | 1405 | 13893 | 8469 |  | Basement 2 Hotel | Access Scaffold |  | INDEPENDENT | 5 | 0.6 | 2 |  | 2 |  |  | 10 | m2-LxH | OFF HIRED | 2022-11-10 | 2022-12-26 | 100% |  | 6.7143 | 14 | 0.84 | 140 | 8.4 | 98 | 42 | 56.4 | 196.4 | 196.4 | 0
| 1 | 1452 | 13940 | 8496 |  | Basement 2 Hotel | Access Scaffold |  | INDEPENDENT | 4 | 1 | 1.5 |  | 1.5 |  |  | 6 | m2-LxH | OFF HIRED | 2022-11-17 | 2023-01-06 | 100% |  | 7.2857 | 14 | 0.84 | 84 | 5.04 | 58.8 | 25.2 | 36.72 | 120.72 | 120.72 | 0
| 1 | 1444 | 13932 | 8252 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 14.3 | 1 | 4.5 |  | 4.5 |  |  | 64.35 | m2-LxH | OFF HIRED | 2022-11-16 | 2022-11-18 | 100% |  | 0.42857 | 14 | 0.84 | 900.9 | 54.054 | 630.63 | 270.27 | 23.166 | 924.066 | 924.066 | 0
| 1 | 1445 | 13933 | 8260 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 7.5 | 0.6 | 2 |  | 2 |  |  | 15 | m2-LxH | OFF HIRED | 2022-11-16 | 2022-11-21 | 100% |  | 0.85714 | 14 | 0.84 | 210 | 12.6 | 147 | 63 | 10.8 | 220.8 | 220.8 | 0
| 1 | 1443 | 13931 | 8555 |  | Basement 2 Hotel | Access Scaffold |  | INDEPENDENT | 7.5 | 1.3 | 7.5 |  | 7.5 |  |  | 56.25 | m2-LxH | OFF HIRED | 2022-11-16 | 2023-02-10 | 100% |  | 12.4286 | 14 | 0.84 | 787.5 | 47.25 | 551.25 | 236.25 | 587.25 | 1374.75 | 1071 | 303.75 |  |  | #VALUE! | 551.25 | #VALUE! | #VALUE!
| 1 | 1432 | 13920 | 8340 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 7.5 | 1.3 | 3 |  | 3 |  |  | 22.5 | m2-LxH | OFF HIRED | 2022-11-14 | 2022-12-17 | 100% |  | 4.8571 | 14 | 0.84 | 315 | 18.9 | 220.5 | 94.5 | 91.8 | 406.8 | 406.8 | 0
| 1 | 1430 | 13918 | 8232 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 16 | 1.3 | 3.5 |  | 3.5 |  |  | 56 | m2-LxH | OFF HIRED | 2022-11-12 | 2022-11-13 | 100% |  | 0.28571 | 14 | 0.84 | 784 | 47.04 | 548.8 | 235.2 | 13.44 | 797.44 | 797.44 | 0
| 1 | 1454 | 13942 | 8317 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 6.3 | 1.3 | 4 |  | 4 |  |  | 25.2 | m2-LxH | OFF HIRED | 2022-11-18 | 2022-12-09 | 100% |  | 3.1429 | 14 | 0.84 | 352.8 | 21.168 | 246.96 | 105.84 | 66.528 | 419.328 | 419.328 | 0
| 1 | 1463 | 13951 | 8259 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 15 | 1 | 3.5 |  | 3.5 |  |  | 52.5 | m2-LxH | OFF HIRED | 2022-11-19 | 2022-11-20 | 100% |  | 0.28571 | 14 | 0.84 | 735 | 44.1 | 514.5 | 220.5 | 12.6 | 747.6 | 747.6 | 0
| 1 | 1462 | 13950 | 8310 |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 19.3 | 1.3 | 2 |  | 2 |  |  | 38.6 | m2-LxH | OFF HIRED | 2022-11-19 | 2022-12-07 | 100% |  | 2.7143 | 14 | 0.84 | 540.4 | 32.424 | 378.28 | 162.12 | 88.008 | 628.408 | 628.408 | 0
| 1 | 1469 | 13957 | 8260 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 7 | 1 | 3.5 |  | 3.5 |  |  | 24.5 | m2-LxH | OFF HIRED | 2022-11-19 | 2022-11-21 | 100% |  | 0.42857 | 14 | 0.84 | 343 | 20.58 | 240.1 | 102.9 | 8.82 | 351.82 | 351.82 | 0
| 1 | 1466 | 13954 | 8261 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 5 | 1 | 3.5 |  | 3.5 |  |  | 17.5 | m2-LxH | OFF HIRED | 2022-11-19 | 2022-11-20 | 100% |  | 0.28571 | 14 | 0.84 | 245 | 14.7 | 171.5 | 73.5 | 4.2 | 249.2 | 249.2 | 0
| 1 | 1465 | 13953 | 8257 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 9.3 | 1 | 3.5 |  | 3.5 |  |  | 32.55 | m2-LxH | OFF HIRED | 2022-11-19 | 2022-11-20 | 100% |  | 0.28571 | 14 | 0.84 | 455.7 | 27.342 | 318.99 | 136.71 | 7.812 | 463.512 | 463.512 | 0
| 1 | 1474 | 13962 | 8267 |  | Basment 2 Residence | Access Scaffold |  | INDEPENDENT | 11 | 1 | 3.5 |  | 3.5 |  |  | 38.5 | m2-LxH | OFF HIRED | 2022-11-21 | 2022-11-23 | 100% |  | 0.42857 | 14 | 0.84 | 539 | 32.34 | 377.3 | 161.7 | 13.86 | 552.86 | 552.86 | 0
| 1 | 1493 | 13980 | 8282 |  | Basement 2 Residence | Access Scaffold |  | INDEPENDENT | 7.5 | 1.3 | 3 |  | 3 |  |  | 22.5 | m2-LxH | OFF HIRED | 2022-11-24 | 2022-11-27 | 100% |  | 0.57143 | 14 | 0.84 | 315 | 18.9 | 220.5 | 94.5 | 10.8 | 325.8 | 325.8 | 0
| 1 | 1479 | 13967 | 8273 |  | Basement 2 Residence | Access Scaffold |  | INDEPENDENT | 11 | 1 | 2.5 |  | 2.5 |  |  | 27.5 | m2-LxH | OFF HIRED | 2022-11-23 | 2022-11-26 | 100% |  | 0.57143 | 14 | 0.84 | 385 | 23.1 | 269.5 | 115.5 | 13.2 | 398.2 | 398.2 | 0
| 1 | 1482 | 13970 | 8273 |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 1.8 | 1.3 | 2.5 |  | 2.5 |  |  | 4.5 | m2-LxH | OFF HIRED | 2022-11-23 | 2022-11-26 | 100% |  | 0.57143 | 14 | 0.84 | 63 | 3.78 | 44.1 | 18.9 | 2.16 | 65.16 | 65.16 | 0
| 1 | 1481 | 13969 |  |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 4 |  | 4 |  |  | 20 | m2-LxH | ON HIRE | 2022-11-23 |  | 100% |  | 14 | 14 | 0.84 | 280 | 16.8 | 196 | 0 | 235.2 | 431.2 | 364 | 67.2 |  |  | #VALUE! | 196 | #VALUE! | #VALUE!
| 1 | 1457 | 13945 |  |  | Basement 1 Hotel | Access Scaffold |  | Independent | 6.5 | 1.8 | 2 |  | 2 |  |  | 13 | m2-LxH | ON HIRE | 2022-11-18 |  | 100% |  | 14.7143 | 18 | 1.05 | 234 | 13.65 | 163.8 | 0 | 200.85 | 364.65 | 310.05 | 54.6 |  |  | #VALUE! | 163.8 | #VALUE! | #VALUE!
| 1 | 1489 | 13976 | 8413 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 11.6 | 1.8 | 3 |  | 3 |  |  | 34.8 | m2-LxH | OFF HIRED | 2022-11-24 | 2023-01-11 | 100% |  | 7 | 18 | 1.05 | 626.4 | 36.54 | 438.48 | 187.92 | 255.78 | 882.18 | 882.18 | 0
| 1 | 1494 | 13981 | 8326 |  | Basement 1 Residence | Access Scaffold |  | Independent | 3.8 | 1.8 | 2 |  | 2 |  |  | 7.6 | m2-LxH | OFF HIRED | 2022-11-24 | 2022-12-13 | 100% |  | 2.8571 | 18 | 1.05 | 136.8 | 7.98 | 95.76 | 41.04 | 22.8 | 159.6 | 159.6 | 0
| 1 | 1488 | 13975 | 8278 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 3.6 | 1.8 | 3.5 |  | 3.5 |  |  | 12.6 | m2-LxH | OFF HIRED | 2022-11-24 | 2022-11-26 | 100% |  | 0.42857 | 18 | 1.05 | 226.8 | 13.23 | 158.76 | 68.04 | 5.67 | 232.47 | 232.47 | 0
| 1 | 1484 | 13972 | 8274 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 5 | 1.8 | 3 |  | 3 |  |  | 15 | m2-LxH | OFF HIRED | 2022-11-23 | 2022-11-26 | 100% |  | 0.57143 | 18 | 1.05 | 270 | 15.75 | 189 | 81 | 9 | 279 | 279 | 0
| 1 | 1347 | 13835 | 8456 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 3 |  | 3 |  |  | 30 | m3 | OFF HIRED | 2022-11-02 | 2022-12-22 | 100% |  | 7.2857 | 7.5 | 0.7 | 225 | 21 | 157.5 | 67.5 | 153 | 378 | 378 | 0
| 1 | 1429 | 13917 | 8316 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 6.8 | 2.5 | 3 |  | 3 |  |  | 51 | m3 | OFF HIRED | 2022-11-12 | 2022-12-09 | 100% |  | 4 | 7.5 | 0.7 | 382.5 | 35.7 | 267.75 | 114.75 | 142.8 | 525.3 | 525.3 | 0
| 1 | 1464 | 13952 |  |  | Basement 2 Hotel | Birdcage Scaffold |  | Birdcage | 3 | 2.5 | 2 |  | 2 |  |  | 15 | m3 | ON HIRE | 2022-11-19 |  | 100% |  | 14.5714 | 7.5 | 0.7 | 112.5 | 10.5 | 78.75 | 0 | 153 | 231.75 | 189.75 | 42 |  |  | #VALUE! | 78.75 | #VALUE! | #VALUE!
| 1 | 1473 | 13961 | 8269 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 2 |  | 2 |  |  | 12.5 | m3 | OFF HIRED | 2022-11-20 | 2022-11-21 | 100% |  | 0.28571 | 7.5 | 0.7 | 93.75 | 8.75 | 65.625 | 28.125 | 2.5 | 96.25 | 96.25 | 0
| 1 | 1451 | 13939 | 8473 |  | Basement 2 Residence | Birdcage Scaffold |  | Birdcage | 3.5 | 3.5 | 1.2 |  | 1.2 |  |  | 14.7 | m3 | OFF HIRED | 2022-11-17 | 2022-12-27 | 100% |  | 5.8571 | 7.5 | 0.7 | 110.25 | 10.29 | 77.175 | 33.075 | 60.27 | 170.52 | 170.52 | 0
| 1 | 1450 | 13938 | 8425 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 10 | 2.5 | 3.5 |  | 3.5 |  |  | 87.5 | m3 | OFF HIRED | 2022-11-17 | 2023-01-14 | 100% |  | 8.4286 | 7.5 | 0.7 | 656.25 | 61.25 | 459.375 | 196.875 | 516.25 | 1172.5 | 1172.5 | 0
| 1 | 1436 | 13924 | 8449 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 5.8 | 2.5 | 1.5 |  | 1.5 |  |  | 21.75 | m3 | OFF HIRED | 2022-11-15 | 2023-01-23 | 100% |  | 10 | 7.5 | 0.7 | 163.125 | 15.225 | 114.1875 | 48.9375 | 152.25 | 315.375 | 315.375 | 0
| 1 | 1482 | 13970 | 8273 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 6 | 2.5 | 3 |  | 3 |  |  | 45 | m3 | OFF HIRED | 2022-11-23 | 2022-11-26 | 100% |  | 0.57143 | 7.5 | 0.7 | 337.5 | 31.5 | 236.25 | 101.25 | 18 | 355.5 | 355.5 | 0
| 1 | 1455 | 13943 | 8267 |  | Basement1 Residence | Cantiliver |  | Cantiliver | 2.5 | 1 |  |  |  | 1 |  | 2.5 | m2-LxW | OFF HIRED | 2022-11-18 | 2022-11-23 | 100% |  | 0.85714 | 36.5 | 3.15 | 91.25 | 7.875 | 63.875 | 27.375 | 6.75 | 98 | 98 | 0
| 1 | 1450 | 13938 | 8425 |  | Basement1 Residence | Cantiliver |  | Cantiliver | 2 | 1 |  |  |  | 1 |  | 2 | m2-LxW | OFF HIRED | 2022-11-17 | 2023-01-14 | 100% |  | 8.4286 | 36.5 | 3.15 | 73 | 6.3 | 51.1 | 21.9 | 53.1 | 126.1 | 126.1 | 0
| 1 | 1494 | 13981 | 8326 |  | Basement1 Residence | Cantiliver |  | Cantiliver | 1 | 1.8 |  |  |  | 1 |  | 1.8 | m2-LxW | OFF HIRED | 2022-11-24 | 2022-12-13 | 100% |  | 2.8571 | 36.5 | 3.15 | 65.7 | 5.67 | 45.99 | 19.71 | 16.2 | 81.9 | 81.9 | 0
| 1 | 1616 | 14156 | 8407 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 4.5 |  | 4.5 |  |  | 4.5 | rm | OFF HIRED | 2022-12-17 | 2023-01-09 | 100% |  | 3.4286 | 135 | 12.25 | 607.5 | 55.125 | 425.25 | 182.25 | 189 | 796.5 | 796.5 | 0
| 1 | 1617 | 14157 | 8406 |  | Basement 1 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 1.5 |  | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2022-12-17 | 2023-01-09 | 100% |  | 3.4286 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 60.75 | 63 | 265.5 | 265.5 | 0
| 1 | 1622 | 14159 | 8464 |  | Basement 2 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 1.5 |  | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2022-12-17 | 2022-12-24 | 100% |  | 1.1429 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 60.75 | 21 | 223.5 | 223.5 | 0
| 1 | 1566 | 14100 | 8327 |  | Basement 2 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-12-10 | 2022-12-13 | 100% |  | 0.57143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 14 | 284 | 284 | 0
| 1 | 1566 | 14100 | 8327 |  | Basement 2 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-12-10 | 2022-12-13 | 100% |  | 0.57143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 14 | 284 | 284 | 0
| 1 | 1578 | 14110 | 8327 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-12-10 | 2022-12-13 | 100% |  | 0.57143 | 135 | 12.25 | 540 | 49 | 378 | 162 | 28 | 568 | 568 | 0
| 1 | 1526 | 14064 |  |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 1.5 | 1.3 | 1 |  | 1 |  |  | 1 | rm | ON HIRE | 2022-12-05 |  | 100% |  | 12.2857 | 135 | 12.25 | 135 | 12.25 | 94.5 | 0 | 150.5 | 245 | 196 | 49 |  |  | #VALUE! | 94.5 | #VALUE! | #VALUE!
| 1 | 1527 | 14065 | 8452 |  | Basement 1 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3.5 |  | 3.5 |  |  | 3.5 | rm | OFF HIRED | 2022-12-05 | 2022-12-21 | 100% |  | 2.4286 | 135 | 12.25 | 472.5 | 42.875 | 330.75 | 141.75 | 104.125 | 576.625 | 576.625 | 0
| 1 | 1590 | 14123 | 8414 |  | Basement 1 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 6 |  | 6 |  |  | 6 | rm | OFF HIRED | 2022-12-14 | 2023-01-11 | 100% |  | 4.1429 | 135 | 12.25 | 810 | 73.5 | 567 | 243 | 304.5 | 1114.5 | 1114.5 | 0
| 1 | 1632 | 14169 | 8449 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 4.5 |  | 4.5 |  |  | 4.5 | rm | OFF HIRED | 2022-12-20 | 2023-01-23 | 100% |  | 5 | 135 | 12.25 | 607.5 | 55.125 | 425.25 | 182.25 | 275.625 | 883.125 | 883.125 | 0
| 1 | 1536 | 14073 | 8312 |  | Basment 1 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 7.5 |  | 7.5 |  |  | 7.5 | rm | OFF HIRED | 2022-12-06 | 2022-12-07 | 100% |  | 0.28571 | 135 | 12.25 | 1012.5 | 91.875 | 708.75 | 303.75 | 26.25 | 1038.75 | 1038.75 | 0
| 1 | 1534 | 14072 | 8442 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-12-06 | 2023-01-19 | 100% |  | 6.4286 | 135 | 12.25 | 540 | 49 | 378 | 162 | 315 | 855 | 855 | 0
| 1 | 1532 | 14069 | 8563 |  | Basement 1 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-12-06 | 2023-02-13 | 100% |  | 10 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 367.5 | 772.5 | 582.75 | 189.75 |  |  | #VALUE! | 339.6333 | #VALUE! | #VALUE!
| 1 | 1496 | 13983 | 8453 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-11-26 | 2022-12-21 | 100% |  | 3.7143 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 136.5 | 541.5 | 541.5 | 0
| 1 | 1644 | 14180 | 8487 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-12-21 | 2023-01-03 | 100% |  | 2 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 49 | 319 | 319 | 0
| 1 | 1671 | 14256 | 8606 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3.5 |  | 3.5 |  |  | 3.5 | rm | OFF HIRED | 2022-12-27 | 2023-01-25 | 100% |  | 4.2857 | 135 | 12.25 | 472.5 | 42.875 | 330.75 | 141.75 | 183.75 | 656.25 | 656.25 | 0
| 1 | 1608 | 14143 | 8345 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 26.3 | 1 | 4 |  | 4 |  |  | 105.2 | m2-LxH | OFF HIRED | 2022-12-16 | 2022-12-20 | 100% |  | 0.71429 | 14 | 0.84 | 1472.8 | 88.368 | 1030.96 | 441.84 | 63.12 | 1535.92 | 1535.92 | 0
| 1 | 1615 | 14150 | 8466 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 6.8 | 1.3 | 4 |  | 4 |  |  | 27.2 | m2-LxH | OFF HIRED | 2022-12-17 | 2022-12-24 | 100% |  | 1.1429 | 14 | 0.84 | 380.8 | 22.848 | 266.56 | 114.24 | 26.112 | 406.912 | 406.912 | 0
| 1 | 1619 | 14154 | 8345 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 12 | 1 | 4 |  | 4 |  |  | 48 | m2-LxH | OFF HIRED | 2022-12-17 | 2022-12-20 | 100% |  | 0.57143 | 14 | 0.84 | 672 | 40.32 | 470.4 | 201.6 | 23.04 | 695.04 | 695.04 | 0
| 1 | 1625 | 14162 | 8486 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 3.5 | 1 | 3.5 |  | 3.5 |  |  | 12.25 | m2-LxH | OFF HIRED | 2022-12-19 | 2023-01-02 | 100% |  | 2.1429 | 14 | 0.84 | 171.5 | 10.29 | 120.05 | 51.45 | 22.05 | 193.55 | 193.55 | 0
| 1 | 1629 | 14165 |  |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 8.8 | 1.3 | 3.5 |  | 3.5 |  |  | 30.8 | m2-LxH | ON HIRE | 2022-12-19 |  | 100% |  | 10.2857 | 14 | 0.84 | 431.2 | 25.872 | 301.84 | 0 | 266.112 | 567.952 | 464.464 | 103.488 |  |  | #VALUE! | 301.84 | #VALUE! | #VALUE!
| 1 | 1628 | 14166 | 8466 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 12.5 | 1.3 | 4 |  | 4 |  |  | 50 | m2-LxH | OFF HIRED | 2022-12-19 | 2022-12-24 | 100% |  | 0.85714 | 14 | 0.84 | 700 | 42 | 490 | 210 | 36 | 736 | 736 | 0
| 1 | 1495 | 13982 | 8282 |  | Basement 2 Residence | Access Scaffold |  | INDEPENDENT | 13.8 | 0.6 | 2.5 |  | 2.5 |  |  | 34.5 | m2-LxH | OFF HIRED | 2022-11-26 | 2022-11-27 | 100% |  | 0.28571 | 14 | 0.84 | 483 | 28.98 | 338.1 | 144.9 | 8.28 | 491.28 | 491.28 | 0
| 1 | 1499 | 13986 | 8284 |  | Basement 2 Residence | Access Scaffold |  | INDEPENDENT | 11 | 1 | 3.5 |  | 3.5 |  |  | 38.5 | m2-LxH | OFF HIRED | 2022-11-26 | 2022-11-27 | 100% |  | 0.28571 | 14 | 0.84 | 539 | 32.34 | 377.3 | 161.7 | 9.24 | 548.24 | 548.24 | 0
| 1 | 1509 | 13996 | 8496 |  | Basement 2 Residence | Access Scaffold |  | INDEPENDENT | 5 | 0.6 | 2.5 |  | 2.5 |  |  | 12.5 | m2-LxH | OFF HIRED | 2022-11-28 | 2023-01-06 | 100% |  | 5.7143 | 14 | 0.84 | 175 | 10.5 | 122.5 | 52.5 | 60 | 235 | 235 | 0
| 1 | 1508 | 13995 | 8338 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 20 | 1.3 | 4.5 |  | 4.5 |  |  | 90 | m2-LxH | OFF HIRED | 2022-11-28 | 2022-12-16 | 100% |  | 2.7143 | 14 | 0.84 | 1260 | 75.6 | 882 | 378 | 205.2 | 1465.2 | 1465.2 | 0
| 1 | 1507 | 13994 | 8288 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 6 | 0.6 | 2.5 |  | 2.5 |  |  | 15 | m2-LxH | OFF HIRED | 2022-11-28 | 2022-11-28 | 100% |  | 0.14286 | 14 | 0.84 | 210 | 12.6 | 147 | 63 | 1.8 | 211.8 | 211.8 | 0
| 1 | 1565 | 14099 | 8327 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 7.5 | 1 | 3.5 |  | 3.5 |  |  | 26.25 | m2-LxH | OFF HIRED | 2022-12-10 | 2022-12-13 | 100% |  | 0.57143 | 14 | 0.84 | 367.5 | 22.05 | 257.25 | 110.25 | 12.6 | 380.1 | 380.1 | 0
| 1 | 1565 | 14099 | 8327 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 6 | 1 | 4 |  | 4 |  |  | 24 | m2-LxH | OFF HIRED | 2022-12-10 | 2022-12-13 | 100% |  | 0.57143 | 14 | 0.84 | 336 | 20.16 | 235.2 | 100.8 | 11.52 | 347.52 | 347.52 | 0
| 1 | 1571 | 14103 |  |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 19 | 1.3 | 4 |  | 4 |  |  | 76 | m2-LxH | ON HIRE | 2022-12-10 |  | 100% |  | 11.5714 | 14 | 0.84 | 1064 | 63.84 | 744.8 | 0 | 738.72 | 1483.52 | 1228.16 | 255.36 |  |  | #VALUE! | 744.8 | #VALUE! | #VALUE!
| 1 | 1519 | 14057 | 8307 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 9.3 | 1 | 4 |  | 4 |  |  | 37.2 | m2-LxH | OFF HIRED | 2022-11-30 | 2022-12-06 | 100% |  | 1 | 14 | 0.84 | 520.8 | 31.248 | 364.56 | 156.24 | 31.248 | 552.048 | 552.048 | 0
| 1 | 1543 | 14079 | 8336 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 12.5 | 1.3 | 4 |  | 4 |  |  | 50 | m2-LxH | OFF HIRED | 2022-12-07 | 2022-12-15 | 100% |  | 1.2857 | 14 | 0.84 | 700 | 42 | 490 | 210 | 54 | 754 | 754 | 0
| 1 | 1547 | 14082 |  |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 9.3 | 1.3 | 4 |  | 4 |  |  | 37.2 | m2-LxH | ON HIRE | 2022-12-08 |  | 100% |  | 11.8571 | 14 | 0.84 | 520.8 | 31.248 | 364.56 | 0 | 370.512 | 735.072 | 610.08 | 124.992 |  |  | #VALUE! | 364.56 | #VALUE! | #VALUE!
| 1 | 1601 | 14136 | 8454 |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 10 | 1.3 | 2 |  | 2 |  |  | 20 | m2-LxH | OFF HIRED | 2022-12-15 | 2022-12-22 | 100% |  | 1.1429 | 14 | 0.84 | 280 | 16.8 | 196 | 84 | 19.2 | 299.2 | 299.2 | 0
| 1 | 1600 | 14135 | 8350 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 3.5 |  | 3.5 |  |  | 14 | m2-LxH | OFF HIRED | 2022-12-15 | 2022-12-21 | 100% |  | 1 | 14 | 0.84 | 196 | 11.76 | 137.2 | 58.8 | 11.76 | 207.76 | 207.76 | 0
| 1 | 1593 | 14128 | 8342 |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 35 | 0.6 | 2 |  | 2 |  |  | 70 | m2-LxH | OFF HIRED | 2022-12-14 | 2022-12-19 | 100% |  | 0.85714 | 14 | 0.84 | 980 | 58.8 | 686 | 294 | 50.4 | 1030.4 | 1030.4 | 0
| 1 | 1591 | 14124 | 8453 |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 13.1 | 1.3 | 4 |  | 4 |  |  | 52.4 | m2-LxH | OFF HIRED | 2022-12-14 | 2022-12-21 | 100% |  | 1.1429 | 14 | 0.84 | 733.6 | 44.016 | 513.52 | 220.08 | 50.304 | 783.904 | 783.904 | 0
| 1 | 1591 | 14124 | 8453 |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 6.5 | 1.3 | 2.5 |  | 2.5 |  |  | 16.25 | m2-LxH | OFF HIRED | 2022-12-14 | 2022-12-21 | 100% |  | 1.1429 | 14 | 0.84 | 227.5 | 13.65 | 159.25 | 68.25 | 15.6 | 243.1 | 243.1 | 0
| 1 | 1611 | 14146 | 8446 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 4.5 |  | 4.5 |  |  | 22.5 | m2-LxH | OFF HIRED | 2022-12-16 | 2023-01-22 | 100% |  | 5.4286 | 14 | 0.84 | 315 | 18.9 | 220.5 | 94.5 | 102.6 | 417.6 | 417.6 | 0
| 1 | 1613 | 14148 | 8495 |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 8.8 | 1.3 | 2 |  | 2 |  |  | 17.6 | m2-LxH | OFF HIRED | 2022-12-16 | 2023-01-05 | 100% |  | 3 | 14 | 0.84 | 246.4 | 14.784 | 172.48 | 73.92 | 44.352 | 290.752 | 290.752 | 0
| 1 | 1515 | 14052 | 8442 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 13 | 1.3 | 4.5 |  | 4.5 |  |  | 58.5 | m2-LxH | OFF HIRED | 2022-11-29 | 2023-01-19 | 100% |  | 7.4286 | 14 | 0.84 | 819 | 49.14 | 573.3 | 245.7 | 365.04 | 1184.04 | 1184.04 | 0
| 1 | 1523 | 14061 | 8301 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 9.5 | 1.3 | 3 |  | 3 |  |  | 28.5 | m2-LxH | OFF HIRED | 2022-12-03 | 2022-12-04 | 100% |  | 0.28571 | 14 | 0.84 | 399 | 23.94 | 279.3 | 119.7 | 6.84 | 405.84 | 405.84 | 0
| 1 | 1592 | 14127 | 8454 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 4 |  | 4 |  |  | 16 | m2-LxH | OFF HIRED | 2022-12-14 | 2022-12-22 | 100% |  | 1.2857 | 14 | 0.84 | 224 | 13.44 | 156.8 | 67.2 | 17.28 | 241.28 | 241.28 | 0
| 1 | 1644 | 14180 | 8487 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 7.5 | 1.3 | 2 |  | 2 |  |  | 15 | m2-LxH | OFF HIRED | 2022-12-21 | 2023-01-03 | 100% |  | 2 | 14 | 0.84 | 210 | 12.6 | 147 | 63 | 25.2 | 235.2 | 235.2 | 0
| 1 | 1638 | 14174 | 8614 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 7.5 | 1.3 | 4 |  | 4 |  |  | 30 | m2-LxH | OFF HIRED | 2022-12-20 | 2023-01-27 | 100% |  | 5.5714 | 14 | 0.84 | 420 | 25.2 | 294 | 126 | 140.4 | 560.4 | 560.4 | 0
| 1 | 1639 | 14175 | 8481 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 9 | 1.3 | 4 |  | 4 |  |  | 36 | m2-LxH | OFF HIRED | 2022-12-20 | 2023-01-02 | 100% |  | 2 | 14 | 0.84 | 504 | 30.24 | 352.8 | 151.2 | 60.48 | 564.48 | 564.48 | 0
| 1 | 1639 | 14175 | 8481 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 13.9 | 1.3 | 2 |  | 2 |  |  | 27.8 | m2-LxH | OFF HIRED | 2022-12-20 | 2023-01-02 | 100% |  | 2 | 14 | 0.84 | 389.2 | 23.352 | 272.44 | 116.76 | 46.704 | 435.904 | 435.904 | 0
| 1 | 1639 | 14175 | 8481 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 4 | 1 | 2 |  | 2 |  |  | 8 | m2-LxH | OFF HIRED | 2022-12-20 | 2023-01-02 | 100% |  | 2 | 14 | 0.84 | 112 | ` | 78.4 | 33.6 | 13.44 | 125.44 | 125.44 | 0
| 1 | 1641 | 14177 | 8473 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 3.5 | 1 | 3.5 |  | 3.5 |  |  | 12.25 | m2-LxH | OFF HIRED | 2022-12-21 | 2022-12-27 | 100% |  | 1 | 14 | 0.84 | 171.5 | 10.29 | 120.05 | 51.45 | 10.29 | 181.79 | 181.79 | 0
| 1 | 1649 | 14184 | 8485 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 6.3 | 1.3 | 3.5 |  | 3.5 |  |  | 22.05 | m2-LxH | OFF HIRED | 2022-12-22 | 2023-01-02 | 100% |  | 1.7143 | 14 | 0.84 | 308.7 | 18.522 | 216.09 | 92.61 | 31.752 | 340.452 | 340.452 | 0
| 1 | 1647 | 14183 | 8623 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 3.5 |  | 3.5 |  |  | 17.5 | m2-LxH | OFF HIRED | 2022-12-22 | 2023-02-01 | 100% |  | 6 | 14 | 0.84 | 245 | 14.7 | 171.5 | 73.5 | 88.2 | 333.2 | 257.6 | 75.6 |  |  | #VALUE! | 651.7 | #VALUE! | #VALUE!
| 1 | 1648 | 14183 | 8623 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 14 | 1 | 3.5 |  | 3.5 |  |  | 49 | m2-LxH | OFF HIRED | 2022-12-22 | 2023-02-01 | 100% |  | 6 | 14 | 0.84 | 686 | 41.16 | 480.2 | 205.8 | 246.96 | 932.96 | 721.28 | 211.68 |  |  | #VALUE! | 651.7 | #VALUE! | #VALUE!
| 1 | 1645 | 14181 | 8486 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 2 |  | 2 |  |  | 10 | m2-LxH | OFF HIRED | 2022-12-22 | 2023-01-02 | 100% |  | 1.7143 | 14 | 0.84 | 140 | 8.4 | 98 | 42 | 14.4 | 154.4 | 154.4 | 0
| 1 | 1645 | 14181 | 8486 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 2.5 | 1.3 | 4 |  | 4 |  |  | 10 | m2-LxH | OFF HIRED | 2022-12-22 | 2023-01-02 | 100% |  | 1.7143 | 14 | 0.84 | 140 | 8.4 | 98 | 42 | 14.4 | 154.4 | 154.4 | 0
| 1 | 1652 | 14187 | 8500 |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 3 | 1.3 | 2 |  | 2 |  |  | 6 | m2-LxH | OFF HIRED | 2022-12-22 | 2023-01-07 | 100% |  | 2.4286 | 14 | 0.84 | 84 | 5.04 | 58.8 | 25.2 | 12.24 | 96.24 | 96.24 | 0
| 1 | 1657 | 14192 | 8408 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 18 | 1.3 | 4 |  | 4 |  |  | 72 | m2-LxH | OFF HIRED | 2022-12-23 | 2023-01-10 | 100% |  | 2.7143 | 14 | 0.84 | 1008 | 60.48 | 705.6 | 302.4 | 164.16 | 1172.16 | 1172.16 | 0
| 1 | 1655 | 14190 | 8500 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 7.5 | 1.3 | 4 |  | 4 |  |  | 30 | m2-LxH | OFF HIRED | 2022-12-23 | 2023-01-07 | 100% |  | 2.2857 | 14 | 0.84 | 420 | 25.2 | 294 | 126 | 57.6 | 477.6 | 477.6 | 0
| 1 | 1660 | 14195 | 8481 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 24 | 1.3 | 4 |  | 4 |  |  | 96 | m2-LxH | OFF HIRED | 2022-12-24 | 2023-01-02 | 100% |  | 1.4286 | 14 | 0.84 | 1344 | 80.64 | 940.8 | 403.2 | 115.2 | 1459.2 | 1459.2 | 0
| 1 | 1661 | 14196 | 8485 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 18.5 | 1.3 | 3.5 |  | 3.5 |  |  | 64.75 | m2-LxH | OFF HIRED | 2022-12-24 | 2023-01-02 | 100% |  | 1.4286 | 14 | 0.84 | 906.5 | 54.39 | 634.55 | 271.95 | 77.7 | 984.2 | 984.2 | 0
| 1 | 1663 | 14197 | 8464 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 7.5 | 0.6 | 2.5 |  | 2.5 |  |  | 18.75 | m2-LxH | OFF HIRED | 2022-12-24 | 2022-12-24 | 100% |  | 0.14286 | 14 | 0.84 | 262.5 | 15.75 | 183.75 | 78.75 | 2.25 | 264.75 | 264.75 | 0
| 1 | 1662 | 14198 | 8464 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 6.3 | 0.6 | 3 |  | 3 |  |  | 18.9 | m2-LxH | OFF HIRED | 2022-12-24 | 2022-12-24 | 100% |  | 0.14286 | 14 | 0.84 | 264.6 | 15.876 | 185.22 | 79.38 | 2.268 | 266.868 | 266.868 | 0
| 1 | 1667 | 14251 | 8465 |  | Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 4 | 1 | 1.5 |  | 1.5 |  |  | 6 | m2-LxH | OFF HIRED | 2022-12-24 | 2022-12-24 | 100% |  | 0.14286 | 14 | 0.84 | 84 | 5.04 | 58.8 | 25.2 | 0.72 | 84.72 | 84.72 | 0
| 1 | 1674 | 14259 | 8496 |  | Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 19.3 | 1.3 | 3 |  | 3 |  |  | 57.9 | m2-LxH | OFF HIRED | 2022-12-27 | 2023-01-06 | 100% |  | 1.5714 | 14 | 0.84 | 810.6 | 48.636 | 567.42 | 243.18 | 76.428 | 887.028 | 887.028 | 0
| 1 | 1560 | 14093 | 8338 |  | Basement 1 Residence | Access Scaffold |  | Independent | 16 | 1.8 | 2.5 |  | 2.5 |  |  | 40 | m2-LxH | OFF HIRED | 2022-12-09 | 2022-12-16 | 100% |  | 1.1429 | 18 | 1.05 | 720 | 42 | 504 | 216 | 48 | 768 | 768 | 0
| 1 | 1520 | 14058 | 8413 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 9.3 | 1.8 | 4 |  | 4 |  |  | 37.2 | m2-LxH | OFF HIRED | 2022-11-30 | 2023-01-11 | 100% |  | 6.1429 | 18 | 1.05 | 669.6 | 39.06 | 468.72 | 200.88 | 239.94 | 909.54 | 909.54 | 0
| 1 | 1585 | 14117 |  |  | Basement 1 Hotel | Access Scaffold |  | Independent | 9.3 | 1.8 | 4.5 |  | 4.5 |  |  | 41.85 | m2-LxH | ON HIRE | 2022-12-12 |  | 100% |  | 11.2857 | 18 | 1.05 | 753.3 | 43.9425 | 527.31 | 0 | 495.9225 | 1023.2325 | 847.4625 | 175.77 |  |  | #VALUE! | 527.31 | #VALUE! | #VALUE!
| 1 | 1624 | 14161 | 8453 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 2.5 | 1.8 | 2 |  | 2 |  |  | 5 | m2-LxH | OFF HIRED | 2022-12-19 | 2022-12-21 | 100% |  | 0.42857 | 18 | 1.05 | 90 | 5.25 | 63 | 27 | 2.25 | 92.25 | 92.25 | 0
| 1 | 1646 | 14182 | 8425 |  | Basement 1 Residence | Access Scaffold |  | Independent | 4.3 | 1..8 | 3 |  | 3 |  |  | 12.9 | m2-LxH | OFF HIRED | 2022-12-22 | 2023-01-14 | 100% |  | 3.4286 | 18 | 1.05 | 232.2 | 13.545 | 162.54 | 69.66 | 46.44 | 278.64 | 278.64 | 0
| 1 | 1665 | 14200 | 8465 |  | Basement 1 Residence | Access Scaffold |  | Independent | 9.5 | 1.8 | 4.5 |  | 4.5 |  |  | 42.75 | m2-LxH | OFF HIRED | 2022-12-24 | 2022-12-24 | 100% |  | 0.14286 | 18 | 1.05 | 769.5 | 44.8875 | 538.65 | 230.85 | 6.4125 | 775.9125 | 775.9125 | 0
| 1 | 1609 | 14144 | 8454 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 3.6 | 2.5 | 4 |  | 4 |  |  | 36 | m3 | OFF HIRED | 2022-12-15 | 2022-12-22 | 100% |  | 1.1429 | 7.5 | 0.7 | 270 | 25.2 | 189 | 81 | 28.8 | 298.8 | 298.8 | 0
| 1 | 1624 | 14161 | 8453 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 2 |  | 2 |  |  | 12.5 | m3 | OFF HIRED | 2022-12-19 | 2022-12-21 | 100% |  | 0.42857 | 7.5 | 0.7 | 93.75 | 8.75 | 65.625 | 28.125 | 3.75 | 97.5 | 97.5 | 0
| 1 | 1626 | 14163 | 8500 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 7 | 3 | 2 |  | 2 |  |  | 42 | m3 | OFF HIRED | 2022-12-19 | 2023-01-07 | 100% |  | 2.8571 | 7.5 | 0.7 | 315 | 29.4 | 220.5 | 94.5 | 84 | 399 | 399 | 0
| 1 | 1506 | 13993 | 8304 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 3.5 |  | 3.5 |  |  | 21.875 | m3 | OFF HIRED | 2022-11-28 | 2022-12-06 | 100% |  | 1.2857 | 7.5 | 0.7 | 164.0625 | 15.3125 | 114.8437 | 49.2188 | 19.6875 | 183.75 | 183.75 | 0
| 1 | 1572 | 14105 | 8458 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 25 | 4.3 | 4 |  | 4 |  |  | 430 | m3 | OFF HIRED | 2022-12-10 | 2022-12-23 | 100% |  | 2 | 7.5 | 0.7 | 3225 | 301 | 2257.5 | 967.5 | 602 | 3827 | 3827 | 0
| 1 | 1523 | 14061 | 8301 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 17.1 | 2.5 | 4 |  | 4 |  |  | 171 | m3 | OFF HIRED | 2022-12-03 | 2022-12-04 | 100% |  | 0.28571 | 7.5 | 0.7 | 1282.5 | 119.7 | 897.75 | 384.75 | 34.2 | 1316.7 | 1316.7 | 0
| 1 | 1602 | 14137 | 8495 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 24.3 | 2.5 | 3.5 |  | 3.5 |  |  | 212.625 | m3 | OFF HIRED | 2022-12-15 | 2023-01-05 | 100% |  | 3.1429 | 7.5 | 0.7 | 1594.6875 | 148.8375 | 1116.2812 | 478.4062 | 467.775 | 2062.4625 | 2062.4625 | 0
| 1 | 1592 | 14127 | 8454 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 13.3 | 2.5 | 4 |  | 4 |  |  | 133 | m3 | OFF HIRED | 2022-12-14 | 2022-12-22 | 100% |  | 1.2857 | 7.5 | 0.7 | 997.5 | 93.1 | 698.25 | 299.25 | 119.7 | 1117.2 | 1117.2 | 0
| 1 | 1586 | 14118 | 8404 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 4 |  | 4 |  |  | 25 | m3 | OFF HIRED | 2022-12-13 | 2023-01-02 | 100% |  | 3 | 7.5 | 0.7 | 187.5 | 17.5 | 131.25 | 56.25 | 52.5 | 240 | 240 | 0
| 1 | 1537 | 14073 | 8312 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 6 | 2.5 | 3 |  | 3 |  |  | 45 | m3 | OFF HIRED | 2022-12-06 | 2022-12-07 | 100% |  | 0.28571 | 7.5 | 0.7 | 337.5 | 31.5 | 236.25 | 101.25 | 9 | 346.5 | 346.5 | 0
| 1 | 1515 | 14052 | 8442 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 4 |  | 4 |  |  | 25 | m3 | OFF HIRED | 2022-11-29 | 2023-01-19 | 100% |  | 7.4286 | 7.5 | 0.7 | 187.5 | 17.5 | 131.25 | 56.25 | 130 | 317.5 | 317.5 | 0
| 1 | 1613 | 14148 | 8495 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 3.5 | 2.5 | 2 |  | 2 |  |  | 17.5 | m3 | OFF HIRED | 2022-12-16 | 2023-01-05 | 100% |  | 3 | 7.5 | 0.7 | 131.25 | 12.25 | 91.875 | 39.375 | 36.75 | 168 | 168 | 0
| 1 | 1611 | 14146 | 8446 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 4.5 |  | 4.5 |  |  | 45 | m3 | OFF HIRED | 2022-12-16 | 2023-01-22 | 100% |  | 5.4286 | 7.5 | 0.7 | 337.5 | 31.5 | 236.25 | 101.25 | 171 | 508.5 | 508.5 | 0
| 1 | 1496 | 13983 | 8453 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 4.8 | 2.5 | 3 |  | 3 |  |  | 36 | m3 | OFF HIRED | 2022-11-26 | 2022-12-21 | 100% |  | 3.7143 | 7.5 | 0.7 | 270 | 25.2 | 189 | 81 | 93.6 | 363.6 | 363.6 | 0
| 1 | 1505 | 13992 | 8282 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 2 |  | 2 |  |  | 12.5 | m3 | OFF HIRED | 2022-11-27 | 2022-11-27 | 100% |  | 0.14286 | 7.5 | 0.7 | 93.75 | 8.75 | 65.625 | 28.125 | 1.25 | 95 | 95 | 0
| 1 | 1640 | 14176 | 8486 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 6.3 | 2.5 | 2 |  | 2 |  |  | 31.5 | m3 | OFF HIRED | 2022-12-20 | 2023-01-02 | 100% |  | 2 | 7.5 | 0.7 | 236.25 | 22.05 | 165.375 | 70.875 | 44.1 | 280.35 | 280.35 | 0
| 1 | 1643 | 14179 | 8483 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 3.5 | 2.5 | 4 |  | 4 |  |  | 35 | m3 | OFF HIRED | 2022-12-21 | 2023-01-02 | 100% |  | 1.8571 | 7.5 | 0.7 | 262.5 | 24.5 | 183.75 | 78.75 | 45.5 | 308 | 308 | 0
| 1 | 1642 | 14178 | 8483 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 4 |  | 4 |  |  | 25 | m3 | OFF HIRED | 2022-12-21 | 2023-01-02 | 100% |  | 1.8571 | 7.5 | 0.7 | 187.5 | 17.5 | 131.25 | 56.25 | 32.5 | 220 | 220 | 0
| 1 | 1637 | 14173 | 8458 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 18 | 2.5 | 4 |  | 4 |  |  | 180 | m3 | OFF HIRED | 2022-12-20 | 2022-12-23 | 100% |  | 0.57143 | 7.5 | 0.7 | 1350 | 126 | 945 | 405 | 72 | 1422 | 1422 | 0
| 1 | 1654 | 14189 | 8473 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 3.5 | 2.5 | 2 |  | 2 |  |  | 17.5 | m3 | OFF HIRED | 2022-12-23 | 2022-12-27 | 100% |  | 0.71429 | 7.5 | 0.7 | 131.25 | 12.25 | 91.875 | 39.375 | 8.75 | 140 | 140 | 0
| 1 | 1653 | 14188 | 8485 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 4 |  | 4 |  |  | 25 | m3 | OFF HIRED | 2022-12-23 | 2023-01-02 | 100% |  | 1.5714 | 7.5 | 0.7 | 187.5 | 17.5 | 131.25 | 56.25 | 27.5 | 215 | 215 | 0
| 1 | 1669 | 14254 | 8490 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 4.3 | 2.5 | 3.5 |  | 3.5 |  |  | 37.625 | m3 | OFF HIRED | 2022-12-26 | 2023-01-03 | 100% |  | 1.2857 | 7.5 | 0.7 | 282.1875 | 26.3375 | 197.5312 | 84.6562 | 33.8625 | 316.05 | 316.05 | 0
| 1 | 1505 | 13992 | 8282 |  | Basement 1 Hotel | Cantiliver |  | Cantiliver | 1.8 | 1 |  |  |  | 1 |  | 1.8 | m2-LxW | OFF HIRED | 2022-11-27 | 2022-11-27 | 100% |  | 0.14286 | 36.5 | 3.15 | 65.7 | 5.67 | 45.99 | 19.71 | 0.81 | 66.51 | 66.51 | 0
| 1 | 1537 | 14069 | 8563 |  | Basement 1 Hotel | Cantiliver |  | Cantiliver | 1.3 | 1.3 |  |  |  | 1.3 |  | 2.197 | m2-LxW | OFF HIRED | 2022-12-06 | 2023-02-13 | 100% |  | 10 | 36.5 | 3.15 | 80.1905 | 6.9206 | 56.1334 | 24.0572 | 69.2055 | 149.396 | 112.4864 | 36.9096 |  |  | #VALUE! | 339.6333 | #VALUE! | #VALUE!
| 1 | 1534 | 14072 | 8442 |  | Basement 1 Residence | Cantiliver |  | Cantiliver | 2 | 0.6 |  |  |  | 1 |  | 1.2 | m2-LxW | OFF HIRED | 2022-12-06 | 2023-01-19 | 100% |  | 6.4286 | 36.5 | 3.15 | 43.8 | 3.78 | 30.66 | 13.14 | 24.3 | 68.1 | 68.1 | 0
| 1 | 1632 | 14169 | 8449 |  | Basement 1 Residence | Cantiliver |  | Cantiliver | 1.5 | 1 |  |  |  | 1 |  | 1.5 | m2-LxW | OFF HIRED | 2022-12-20 | 2023-01-23 | 100% |  | 5 | 36.5 | 3.15 | 54.75 | 4.725 | 38.325 | 16.425 | 23.625 | 78.375 | 78.375 | 0
| 1 | 1520 | 14058 | 8413 |  | Basement 1 Hotel | Cantiliver |  | Cantiliver | 1.8 | 1 |  |  |  | 1 |  | 1.8 | m2-LxW | OFF HIRED | 2022-11-30 | 2023-01-11 | 100% |  | 6.1429 | 36.5 | 3.15 | 65.7 | 5.67 | 45.99 | 19.71 | 34.83 | 100.53 | 100.53 | 0
| 1 | 1638 | 14174 |  |  | Basement 1 Residence | Cantiliver |  | Cantiliver | 7.5 | 1.3 |  |  |  | 1.3 |  | 12.675 | m2-LxW | ON HIRE | 2022-12-20 |  | 100% |  | 10.1429 | 36.5 | 3.15 | 462.6375 | 39.9263 | 323.8462 | 0 | 404.9663 | 728.8125 | 569.1075 | 159.705 |  |  | #VALUE! | 617.8463 | #VALUE! | #VALUE!
| 1 | 1636 | 14172 |  |  | Basement 1 Residence | Cantiliver |  | Cantiliver | 5 | 0.6 |  |  |  | 0.6 |  | 1.8 | m2-LxW | ON HIRE | 2022-12-20 |  | 100% |  | 10.1429 | 36.5 | 3.15 | 65.7 | 5.67 | 45.99 | 0 | 57.51 | 103.5 | 80.82 | 22.68 |  |  | #VALUE! | 134.19 | #VALUE! | #VALUE!
| 2 | 328 | 12425 | 7594 |  | Ground Floor Residence | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 3 | 1 | 2 |  |  | 10 | m2-LxH | OFF HIRED | 2022-06-22 | 2022-06-30 | 100% |  | 1.2857 | 14 | 0.84 | 140 | 8.4 | 98 | 42 | 10.8 | 150.8 | 150.8 | 0
| 2 |  | 12106 | 7555 |  | Ground Floor Residance | Access Scaffold |  | INDEPENDENT | 10 | 1.3 | 3 | 1 | 2 |  |  | 20 | m2-LxH | OFF HIRED | 2022-05-25 | 2022-06-01 | 100% |  | 1.1429 | 14 |  | 280 | 0 | 196 | 84 | 0 | 280 | 280 | 0
| 2 |  | 12107 | 7555 |  | Ground Floor Residance | Access Scaffold |  | INDEPENDENT | 8 | 1.3 | 4 | 1 | 3 |  |  | 24 | m2-LxH | OFF HIRED | 2022-05-26 | 2022-06-01 | 100% |  | 1 | 14 |  | 336 | 0 | 235.2 | 100.8 | 0 | 336 | 336 | 0
| 2 |  | 12108 | 7555 |  | Ground Floor Residance | Access Scaffold |  | INDEPENDENT | 10 | 1.3 | 4 | 1 | 3 |  |  | 30 | m2-LxH | OFF HIRED | 2022-05-26 | 2022-06-01 | 100% |  | 1 | 14 |  | 420 | 0 | 294 | 126 | 0 | 420 | 420 | 0
| 2 |  | 12116 | 6702 |  | Ground Floor Residance | Access Scaffold |  | INDEPENDENT | 13 | 1.3 | 1.5 | 1 | 0.5 |  |  | 6.5 | m2-LxH | OFF HIRED | 2022-05-29 | 2022-09-20 | 100% |  | 16.4286 | 14 |  | 91 | 0 | 63.7 | 27.3 | 0 | 91 | 91 | 0
| 2 |  | 12115 | 6741 |  | Ground Floor Residance | Access Scaffold |  | INDEPENDENT | 12.5 | 1.3 | 3 | 1 | 2 |  |  | 25 | m2-LxH | OFF HIRED | 2022-05-29 | 2022-09-30 | 100% |  | 17.8571 | 14 |  | 350 | 0 | 245 | 105 | 0 | 350 | 350 | 0
| 2 |  | 12117 | 7713 |  | Ground Floor Residance | Access Scaffold |  | INDEPENDENT | 1.8 | 1.3 | 5 | 1 | 4 |  |  | 7.2 | m2-LxH | OFF HIRED | 2022-05-29 | 2022-07-14 | 100% |  | 6.7143 | 14 |  | 100.8 | 0 | 70.56 | 30.24 | 0 | 100.8 | 100.8 | 0
| 2 |  | 12117 | 7713 |  | Ground Floor Residance | Access Scaffold |  | INDEPENDENT | 1.8 | 1.3 | 5 | 1 | 4 |  |  | 7.2 | m2-LxH | OFF HIRED | 2022-05-29 | 2022-07-14 | 100% |  | 6.7143 | 14 |  | 100.8 | 0 | 70.56 | 30.24 | 0 | 100.8 | 100.8 | 0
| 2 |  | 12117 | 7713 |  | Ground Floor Residance | Access Scaffold |  | INDEPENDENT | 1.8 | 1.3 | 5 | 1 | 4 |  |  | 7.2 | m2-LxH | OFF HIRED | 2022-05-29 | 2022-07-14 | 100% |  | 6.7143 | 14 |  | 100.8 | 0 | 70.56 | 30.24 | 0 | 100.8 | 100.8 | 0
| 2 |  | 12116 | 6702 |  | Ground Floor Gate 1 Residence | Edge Prorection |  | Edge Prorection | 35 | [6 empty] | 35 | lm |  | 2022-05-29 |  | 100% |  | 0 | 24 |  | 840 | 0 | 588 | 0 | 0 | 588 | 588 | 0
| 2 | 243 | 12358 | 7849 |  | Ground Floor Gate 1 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-06-15 | 2022-08-27 | 100% |  | 10.5714 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 259 | 529 | 529 | 0
| 2 | 261 | 12375 | 7586 |  | Grround Level Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-06-16 | 2022-06-27 | 100% |  | 1.7143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 42 | 312 | 312 | 0
| 2 | 301 | 12408 | 7710 |  | Ground Floor Gate 1 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-06-19 | 2022-07-14 | 100% |  | 3.7143 | 135 | 12.25 | 540 | 49 | 378 | 162 | 182 | 722 | 722 | 0
| 2 | 302 | 12409 | 8180 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-06-20 | 2022-11-01 | 100% |  | 19.2857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 472.5 | 742.5 | 742.5 | 0
| 2 | 303 | 12409 | 8180 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-06-20 | 2022-11-01 | 100% |  | 19.2857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 472.5 | 742.5 | 742.5 | 0
| 2 | 304 | 12409 | 8180 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-06-20 | 2022-11-01 | 100% |  | 19.2857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 472.5 | 742.5 | 742.5 | 0
| 2 | 305 | 12409 | 8180 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-06-20 | 2022-11-01 | 100% |  | 19.2857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 472.5 | 742.5 | 742.5 | 0
| 2 | 316 | 12417 | 7736 |  | Ground Floor Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-06-20 | 2022-07-26 | 100% |  | 5.2857 | 135 | 12.25 | 540 | 49 | 378 | 162 | 259 | 799 | 799 | 0
| 2 | 320 | 12421 | 7714 |  | Ground Floor Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-06-21 | 2022-07-15 | 100% |  | 3.5714 | 135 | 12.25 | 540 | 49 | 378 | 162 | 175 | 715 | 715 | 0
| 2 | 329 | 12426 | 7726 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-06-22 | 2022-07-18 | 100% |  | 3.8571 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 141.75 | 546.75 | 546.75 | 0
| 2 | 338 | 12439 | 7584 |  | Ground Floor Gate 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-06-23 | 2022-06-27 | 100% |  | 0.71429 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 26.25 | 431.25 | 431.25 | 0
| 2 | 314 | 12311 | 7900 |  | Ground Floor Gate 2 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 2.5 | 6 | 1 | 5 |  |  | 5 | rm | OFF HIRED | 2022-06-12 | 2022-09-20 | 100% |  | 14.4286 | 135 | 12.25 | 675 | 61.25 | 472.5 | 202.5 | 883.75 | 1558.75 | 1558.75 | 0
| 2 | 387 | 12546 | 7830 |  | Ground Floor Office Area Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-06-28 | 2022-08-18 | 100% |  | 7.4286 | 135 | 12.25 | 540 | 49 | 378 | 162 | 364 | 904 | 904 | 0
| 2 | 98 | 12140 | 7563 |  | Ground Floor Hotel | Access Scaffold |  | INDEPENDENT | 2.5 | 1.3 | 4 | 1 | 3 |  |  | 7.5 | m2-LxH | OFF HIRED | 2022-06-01 | 2022-06-10 | 100% |  | 1.4286 | 14 |  | 105 | 0 | 73.5 | 31.5 | 0 | 105 | 105 | 0
| 2 |  | 12231 | 8115 |  | Ground Floor Mep Store Residence | Access Scaffold |  | INDEPENDENT | 2.5 | 1.3 | 3 | 1 | 2 |  |  | 5 | m2-LxH | OFF HIRED | 2022-06-05 | 2022-10-18 | 100% |  | 19.4286 | 14 |  | 70 | 0 | 49 | 21 | 0 | 70 | 70 | 0
| 2 | A16 | 12233 | 7558 |  | Ground Floor Wash Room Residence | Access Scaffold |  | INDEPENDENT | 2.5 | 1.3 | 5 | 1 | 4 |  |  | 10 | m2-LxH | OFF HIRED | 2022-06-05 | 2022-06-08 | 100% |  | 0.57143 | 14 |  | 140 | 0 | 98 | 42 | 0 | 140 | 140 | 0
| 2 | 173 | 12170 | 7600 |  | Ground Floor Hotel | Access Scaffold |  | INDEPENDENT | 2.5 | 1.2 | 4 | 1 | 3 |  |  | 7.5 | m2-LxH | OFF HIRED | 2022-06-07 | 2022-07-05 | 100% |  | 4.1429 | 14 |  | 105 | 0 | 73.5 | 31.5 | 0 | 105 | 105 | 0
| 2 | 163 | 12160 | 8139 |  | Ground Floor Hotel | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 5 | 1 | 4 |  |  | 20 | m2-LxH | OFF HIRED | 2022-06-07 | 2022-10-24 | 100% |  | 20 | 14 |  | 280 | 0 | 196 | 84 | 0 | 280 | 280 | 0
| 2 | 175 | 12172 | 6702 |  | Ground Floor Hotel | Access Scaffold |  | INDEPENDENT | 4 | 1 | 3 | 1 | 2 |  |  | 8 | m2-LxH | OFF HIRED | 2022-06-08 | 2022-09-20 | 100% |  | 15 | 14 |  | 112 | 0 | 78.4 | 33.6 | 0 | 112 | 112 | 0
| 2 | 202 | 12198 | 7568 |  | Ground Floor Hotel | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 4 | 1 | 3 |  |  | 12 | m2-LxH | OFF HIRED | 2022-06-09 | 2022-06-20 | 100% |  | 1.7143 | 14 |  | 168 | 0 | 117.6 | 50.4 | 0 | 168 | 168 | 0
| 2 | 187 | 12185 | 7567 |  | Ground Floor Hotel | Access Scaffold |  | INDEPENDENT | 2.5 | 1.3 | 3 | 1 | 2 |  |  | 5 | m2-LxH | OFF HIRED | 2022-06-09 | 2022-06-20 | 100% |  | 1.7143 | 14 |  | 70 | 0 | 49 | 21 | 0 | 70 | 70 | 0
| 2 | 188 | 12185 | 7567 |  | Ground Floor Hotel | Access Scaffold |  | INDEPENDENT | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 3.6 | m2-LxH | OFF HIRED | 2022-06-09 | 2022-06-20 | 100% |  | 1.7143 | 14 |  | 50.4 | 0 | 35.28 | 15.12 | 0 | 50.4 | 50.4 | 0
| 2 | 130 | 12227 | 6718 |  | ground Floor Pump Room Residence | Access Scaffold |  | INDEPENDENT | 2.5 | 1.3 | 6 | 1 | 5 |  |  | 12.5 | m2-LxH | OFF HIRED | 2022-06-05 | 2022-09-24 | 100% |  | 16 | 14 | 0.84 | 175 | 10.5 | 122.5 | 52.5 | 168 | 343 | 343 | 0
| 2 | 132 | 12227 | 6718 |  | ground Floor Pump Room Residence | Access Scaffold |  | INDEPENDENT | 2.5 | 1.3 | 6 | 1 | 5 |  |  | 12.5 | m2-LxH | OFF HIRED | 2022-06-05 | 2022-09-24 | 100% |  | 16 | 14 | 0.84 | 175 | 10.5 | 122.5 | 52.5 | 168 | 343 | 343 | 0
| 2 | 174 | 12171 | 6716 |  | Ground Floor Hotel | Access Scaffold |  | INDEPENDENT | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 3.6 | m2-LxH | OFF HIRED | 2022-06-08 | 2022-09-24 | 100% |  | 15.5714 | 14 | 0.84 | 50.4 | 3.024 | 35.28 | 15.12 | 47.088 | 97.488 | 97.488 | 0
| 2 | 174 | 12171 | 6716 |  | Ground Floor Hotel | Access Scaffold |  | INDEPENDENT | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 3.6 | m2-LxH | OFF HIRED | 2022-06-08 | 2022-09-24 | 100% |  | 15.5714 | 14 | 0.84 | 50.4 | 3.024 | 35.28 | 15.12 | 47.088 | 97.488 | 97.488 | 0
| 2 | 369 | 12524 | 6718 |  | Ground Floor Hotel | Access Scaffold |  | INDEPENDENT | 2.5 | 1.8 | 7 | 1 | 6 |  |  | 15 | m2-LxH | OFF HIRED | 2022-06-27 | 2022-09-24 | 100% |  | 12.8571 | 14 | 0.84 | 210 | 12.6 | 147 | 63 | 162 | 372 | 372 | 0
| 2 | 369 | 12524 | 6718 |  | Ground Floor Hotel | Access Scaffold |  | INDEPENDENT | 5 | 1.8 | 7 | 1 | 6 |  |  | 30 | m2-LxH | OFF HIRED | 2022-06-27 | 2022-09-24 | 100% |  | 12.8571 | 14 | 0.84 | 420 | 25.2 | 294 | 126 | 324 | 744 | 744 | 0
| 2 | 369 | 12524 | 6718 |  | Ground Floor Hotel | Access Scaffold |  | INDEPENDENT | 2.5 | 1.8 | 7 | 1 | 6 |  |  | 15 | m2-LxH | OFF HIRED | 2022-06-27 | 2022-09-24 | 100% |  | 12.8571 | 14 | 0.84 | 210 | 12.6 | 147 | 63 | 162 | 372 | 372 | 0
| 2 | 369 | 12524 | 6718 |  | Ground Floor Hotel | Access Scaffold |  | INDEPENDENT | 3.1 | 1.8 | 5 | 1 | 4 |  |  | 12.4 | m2-LxH | OFF HIRED | 2022-06-27 | 2022-09-24 | 100% |  | 12.8571 | 14 | 0.84 | 173.6 | 10.416 | 121.52 | 52.08 | 133.92 | 307.52 | 307.52 | 0
| 2 | 385 | 12547 | 6708 |  | Ground Floor Residence | Access Scaffold |  | INDEPENDENT | 7.5 | 1.3 | 5 | 1 | 4 |  |  | 30 | m2-LxH | OFF HIRED | 2022-06-28 | 2022-09-19 | 100% |  | 12 | 14 | 0.84 | 420 | 25.2 | 294 | 126 | 302.4 | 722.4 | 722.4 | 0
| 2 | 118 | 12141 | 7715 |  | Ground Floor Residance | Access Scaffold |  | INDEPENDENT | 1.8 | 1.8 | 6 | 1 | 5 |  |  | 9 | m2-LxH | OFF HIRED | 2022-06-01 |  | 100% |  | -6387.4286 | 18 |  | 162 | 0 | 113.4 | 48.6 | 0 | 162 | 162 | 0
| 2 | 182 | 12179 | 7566 |  | Ground Floor Residance | Access Scaffold |  | INDEPENDENT | 2.5 | 1.8 | 4 | 1 | 3 |  |  | 7.5 | m2-LxH | OFF HIRED | 2022-06-08 | 2022-06-19 | 100% |  | 1.7143 | 18 |  | 135 | 0 | 94.5 | 40.5 | 0 | 135 | 135 | 0
| 2 | 196 | 12192 | 7568 |  | Ground Floor Residance | Access Scaffold |  | INDEPENDENT | 2.5 | 1.8 | 5 | 1 | 4 |  |  | 10 | m2-LxH | OFF HIRED | 2022-06-09 | 2022-06-20 | 100% |  | 1.7143 | 18 |  | 180 | 0 | 126 | 54 | 0 | 180 | 180 | 0
| 2 | 196 | 12192 | 6704 |  | Ground Floor Residance | Access Scaffold |  | INDEPENDENT | 2.5 | 1.8 | 5 | 1 | 4 |  |  | 10 | m2-LxH | OFF HIRED | 2022-06-09 | 2022-09-21 | 100% |  | 15 | 18 |  | 180 | 0 | 126 | 54 | 0 | 180 | 180 | 0
| 2 | 197 | 12193 | 7899 |  | Ground Level Residence | Access Scaffold |  | INDEPENDENT | 1.8 | 1.8 | 4 | 1 | 3 |  |  | 5.4 | m2-LxH | OFF HIRED | 2022-06-09 | 2022-09-14 | 100% |  | 14 | 18 |  | 97.2 | 0 | 68.04 | 29.16 | 0 | 97.2 | 97.2 | 0
| 2 | 332 | 12432 | 6715 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 15 | 14 | 5 | 1 | 4 |  |  | 840 | m3 | OFF HIRED | 2022-06-22 | 2022-09-25 | 100% |  | 13.7143 | 7.5 | 0.7 | 6300 | 588 | 4410 | 1890 | 8064 | 14364 | 14364 | 0
| 2 | 332 | 12432 | 6715 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 16 | 5 | 5 | 1 | 4 |  |  | 320 | m3 | OFF HIRED | 2022-06-22 | 2022-09-25 | 100% |  | 13.7143 | 7.5 | 0.7 | 2400 | 224 | 1680 | 720 | 3072 | 5472 | 5472 | 0
| 2 | 332 | 12432 | 6715 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 14 | 8.5 | 5 | 1 | 4 |  |  | 476 | m3 | OFF HIRED | 2022-06-22 | 2022-09-25 | 100% |  | 13.7143 | 7.5 | 0.7 | 3570 | 333.2 | 2499 | 1071 | 4569.6 | 8139.6 | 8139.6 | 0
| 2 | 332 | 12432 | 6715 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 7.5 | 2.5 | 5 | 1 | 4 |  |  | 75 | m3 | OFF HIRED | 2022-06-22 | 2022-09-25 | 100% |  | 13.7143 | 7.5 | 0.7 | 562.5 | 52.5 | 393.75 | 168.75 | 720 | 1282.5 | 1282.5 | 0
| 2 | 162 | 12159 | 8142 |  | Ground Floor Ball Room Hotel | Birdcage Scaffold |  | Birdcage | 30 | 3.1 | 5.5 | 1 | 4.5 |  |  | 418.5 | m3 | OFF HIRED | 2022-06-07 | 2022-10-28 | 100% |  | 20.5714 | 7.5 | 0.7 | 3138.75 | 292.95 | 2197.125 | 941.625 | 6026.4 | 9165.15 | 9165.15 | 0
| 2 | 131 | 12228 | 8430 |  | Ground Floor Ball Room Hotel | Birdcage Scaffold |  | Birdcage | 10 | 2.5 | 3 | 1 | 2 |  |  | 50 | m3 | OFF HIRED | 2022-06-05 | 2023-01-17 | 100% |  | 32.4286 | 7.5 | 0.7 | 375 | 35 | 262.5 | 112.5 | 1135 | 1510 | 1510 | 0
| 2 | 332 | 12523 | 8068 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 10 | 5 | 5 | 1 | 4 |  |  | 200 | m3 | OFF HIRED | 2022-06-27 | 2022-10-01 | 100% |  | 13.8571 | 7.5 | 0.7 | 1500 | 140 | 1050 | 450 | 1940 | 3440 | 3440 | 0
| 2 | 332 | 12523 | 8068 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 8 | 4 | 5 | 1 | 4 |  |  | 128 | m3 | OFF HIRED | 2022-06-27 | 2022-10-01 | 100% |  | 13.8571 | 7.5 | 0.7 | 960 | 89.6 | 672 | 288 | 1241.6 | 2201.6 | 2201.6 | 0
| 2 | 415 | 12574 | 8117 |  | Ground Floor Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-07-01 | 2022-10-18 | 100% |  | 15.7143 | 135 |  | 540 | 0 | 378 | 162 | 0 | 540 | 540 | 0
| 2 | 427 | 12587 | 7715 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 2.5 | 3.5 | 1 | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-07-03 | 2022-07-15 | 100% |  | 1.8571 | 135 |  | 337.5 | 0 | 236.25 | 101.25 | 0 | 337.5 | 337.5 | 0
| 2 | 448 | 12605 | 8070 |  | Ground Floor Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-07-07 | 2022-10-06 | 100% |  | 13.1429 | 135 |  | 405 | 0 | 283.5 | 121.5 | 0 | 405 | 405 | 0
| 2 | 530 | 12739 | 8142 |  | Ground Floor Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-07-17 | 2022-10-28 | 100% |  | 14.8571 | 135 |  | 540 | 0 | 378 | 162 | 0 | 540 | 540 | 0
| 2 | 554 | 12765 | 6731 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-20 | 2022-09-27 | 100% |  | 10 | 135 |  | 270 | 0 | 189 | 81 | 0 | 270 | 270 | 0
| 2 | 390 | 12556 | 6715 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-06-29 | 2022-09-25 | 100% |  | 12.7143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 311.5 | 581.5 | 581.5 | 0
| 2 | 449 | 12606 | 7855 |  | Ground Floor Residance | HEAVY DUTY TOWER |  | Tower | 1.8 | 0.6 | 6 | 1 | 5 |  |  | 5 | rm | OFF HIRED | 2022-07-07 | 2022-08-29 | 100% |  | 7.7143 | 135 | 12.25 | 675 | 61.25 | 472.5 | 202.5 | 472.5 | 1147.5 | 1147.5 | 0
| 2 | 465 | 12622 | 6715 |  | Ground Floor Residance | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-07 | 2022-09-25 | 100% |  | 11.5714 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 283.5 | 553.5 | 553.5 | 0
| 2 | 465 | 12622 | 6715 |  | Ground Floor Residance | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-07 | 2022-09-25 | 100% |  | 11.5714 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 283.5 | 553.5 | 553.5 | 0
| 2 | 526 | 12734 | 6734 |  | Ground Floor Residance | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-07-15 | 2022-09-28 | 100% |  | 10.8571 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 399 | 804 | 804 | 0
| 2 | 506 | 12711 | 7890 |  | Ground Floor | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-13 | 2022-09-15 | 100% |  | 9.2857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 227.5 | 497.5 | 497.5 | 0
| 2 | 506 | 12711 | 7890 |  | Ground Floor | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-13 | 2022-09-15 | 100% |  | 9.2857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 227.5 | 497.5 | 497.5 | 0
| 2 | 555 | 12766 | 7749 |  | Ground Floor Residance | HEAVY DUTY TOWER |  | Tower | 1.3 | 0.6 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-07-20 | 2022-08-03 | 100% |  | 2.1429 | 135 | 12.25 | 540 | 49 | 378 | 162 | 105 | 645 | 645 | 0
| 2 | 558 | 12769 | 7890 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3.5 | 1 | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-07-20 | 2022-09-15 | 100% |  | 8.2857 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 253.75 | 591.25 | 591.25 | 0
| 2 | 398 | 12559 | 8141 |  | Ground Floor Hotel | Access Scaffold |  | INDEPENDENT | 20 | 1 | 7 | 1 | 6 |  |  | 120 | m2-LxH | OFF HIRED | 2022-06-29 | 2022-10-25 | 100% |  | 17 | 14 |  | 1680 | 0 | 1176 | 504 | 0 | 1680 | 1680 | 0
| 2 | 399 | 12560 | 6718 |  | Ground Floor Hotel | Access Scaffold |  | INDEPENDENT | 10 | 1.3 | 3 | 1 | 2 |  |  | 20 | m2-LxH | OFF HIRED | 2022-06-29 | 2022-09-24 | 100% |  | 12.5714 | 14 |  | 280 | 0 | 196 | 84 | 0 | 280 | 280 | 0
| 2 | 557 | 12797 | 7858 |  | Ground Floor Ramp Hotel | Access Scaffold |  | INDEPENDENT | 6 | 1.3 | 3.5 | 1 | 2.5 |  |  | 15 | m2-LxH | OFF HIRED | 2022-07-24 | 2022-08-26 | 100% |  | 4.8571 | 14 |  | 210 | 0 | 147 | 63 | 0 | 210 | 210 | 0
| 2 | 440 | 12598 | 8067 |  | Ground Floor Ramp Residence | Access Scaffold |  | INDEPENDENT | 24 | 1.3 | 2 | 1 | 1 |  |  | 24 | m2-LxH | OFF HIRED | 2022-07-04 | 2022-09-30 | 100% |  | 12.7143 | 14 | 0.84 | 336 | 20.16 | 235.2 | 100.8 | 256.32 | 592.32 | 592.32 | 0
| 2 | 416 | 12576 | 7843 |  | Ground Floor Residence Stair Case | Access Scaffold |  | INDEPENDENT | 9.5 | 1.3 | 4 | 1 | 3 |  |  | 28.5 | m2-LxH | OFF HIRED | 2022-07-01 | 2022-08-25 | 100% |  | 8 | 14 | 0.84 | 399 | 23.94 | 279.3 | 119.7 | 191.52 | 590.52 | 590.52 | 0
| 2 | 482 | 12634 | 7720 |  | Ground Floor Ramp Residence | Access Scaffold |  | INDEPENDENT | 27 | 1.3 | 3.5 | 1 | 2.5 |  |  | 67.5 | m2-LxH | OFF HIRED | 2022-07-07 | 2022-07-17 | 100% |  | 1.5714 | 14 | 0.84 | 945 | 56.7 | 661.5 | 283.5 | 89.1 | 1034.1 | 1034.1 | 0
| 2 | 494 | 12646 | 7900 |  | GF Hotel Staircase | Access Scaffold |  | INDEPENDENT | 6.5 | 1.3 | 5 | 1 | 4 |  |  | 26 | m2-LxH | OFF HIRED | 2022-07-07 | 2022-09-20 | 100% |  | 10.8571 | 14 | 0.84 | 364 | 21.84 | 254.8 | 109.2 | 237.12 | 601.12 | 601.12 | 0
| 2 | 553 | 12763 |  |  | Ground Floor Corridoor Residence | Access Scaffold |  | INDEPENDENT | 60 | 1.3 | 5 | 1 | 4 |  |  | 240 | m2-LxH | OFF HIRED | 2022-07-19 | 2022-11-30 | 100% |  | 19.2857 | 14 | 0.84 | 3360 | 201.6 | 2352 |  | 3888 | 6240 | 6240 | 0
| 2 | 553 | 12763 | 8192 |  | PARTIAL DISMANTEL |  |  |  | 30 | 1.3 | 5 | 1 | 4 |  |  | 120 | m2-LxH | OFF HIRED | 2022-11-03 | 2022-11-30 | 100% |  | -4 | 14 | 0.84 | 1680 | 100.8 |  | 504 | -403.2 | 100.8 | 100.8 | 0
| 2 | 553 | 12763 | 8223 |  | PARTIAL DISMANTEL |  |  |  | 30 | 1.3 | 5 | 1 | 4 |  |  | 120 | m2-LxH | OFF HIRED | 2022-11-11 | 2022-11-30 | 100% |  | -2.8571 | 14 | 0.84 | 1680 | 100.8 |  | 504 | -288 | 216 | 216 | 0
| 2 | 557 | 12771 | 7858 |  | Ground Floor Ramp Hotel | Access Scaffold |  | INDEPENDENT | 9 | 1.3 | 3.5 | 1 | 2.5 |  |  | 22.5 | m2-LxH | OFF HIRED | 2022-07-20 | 2022-08-26 | 100% |  | 5.4286 | 14 | 0.84 | 315 | 18.9 | 220.5 | 94.5 | 102.6 | 417.6 | 417.6 | 0
| 2 | 552 | 12762 | 8154 |  | Ground Floor Office Residence | Access Scaffold |  | INDEPENDENT | 15 | 1.3 | 5.5 | 1 | 4.5 |  |  | 67.5 | m2-LxH | OFF HIRED | 2022-07-20 | 2022-10-27 | 100% |  | 14.2857 | 14 | 0.84 | 945 | 56.7 | 661.5 | 283.5 | 810 | 1755 | 1755 | 0
| 2 | 428 | 12588 | 7843 |  | Ground Floor Office Residence | Birdcage Scaffold |  | INDEPENDENT | 10 | 1.8 | 5 | 1 | 4 |  |  | 40 | m2-LxH | OFF HIRED | 2022-07-03 | 2022-08-25 | 100% |  | 7.7143 | 18 | 1.05 | 720 | 42 | 504 | 216 | 324 | 1044 | 1044 | 0
| 2 | 551 | 12761 | 8154 |  | Ground Floor Hotel | Birdcage Scaffold |  | INDEPENDENT | 5 | 1.8 | 5.5 | 1 | 4.5 |  |  | 22.5 | m2-LxH | OFF HIRED | 2022-07-20 | 2022-10-27 | 100% |  | 14.2857 | 18 | 1.05 | 405 | 23.625 | 283.5 | 121.5 | 337.5 | 742.5 | 742.5 | 0
| 2 | 443 | 12602 | 8115 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 8 | 4 | 5.5 | 1 | 4.5 |  |  | 144 | m3 | OFF HIRED | 2022-07-04 | 2022-10-18 | 100% |  | 15.2857 | 7.5 | 0.7 | 1080 | 100.8 | 756 | 324 | 1540.8 | 2620.8 | 2620.8 | 0
| 2 | 444 | 12602 | 8115 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 8 | 4.4 | 5.5 | 1 | 4.5 |  |  | 158.4 | m3 | OFF HIRED | 2022-07-04 | 2022-10-18 | 100% |  | 15.2857 | 7.5 | 0.7 | 1188 | 110.88 | 831.6 | 356.4 | 1694.88 | 2882.88 | 2882.88 | 0
| 2 | 432 | 12592 | 6708 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 15 | 6 | 5.5 | 1 | 4.5 |  |  | 405 | m3 | OFF HIRED | 2022-07-03 | 2022-09-19 | 100% |  | 11.2857 | 7.5 | 0.7 | 3037.5 | 283.5 | 2126.25 | 911.25 | 3199.5 | 6237 | 6237 | 0
| 2 | 445 | 12599 | 8066 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 22 | 3 | 5.5 | 1 | 4.5 |  |  | 297 | m3 | OFF HIRED | 2022-07-04 | 2022-10-04 | 100% |  | 13.2857 | 7.5 | 0.7 | 2227.5 | 207.9 | 1559.25 | 668.25 | 2762.1 | 4989.6 | 4989.6 | 0
| 2 | 497 | 12632 | 6715 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 7.5 | 7.5 | 5 | 1 | 4 |  |  | 225 | m3 | OFF HIRED | 2022-07-06 | 2022-09-25 | 100% |  | 11.7143 | 7.5 | 0.7 | 1687.5 | 157.5 | 1181.25 | 506.25 | 1845 | 3532.5 | 3532.5 | 0
| 2 | 497 | 12632 | 6715 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 32.5 | 4.5 | 5.5 | 1 | 4.5 |  |  | 658.125 | m3 | OFF HIRED | 2022-07-06 | 2022-09-25 | 100% |  | 11.7143 | 7.5 | 0.7 | 4935.9375 | 460.6875 | 3455.1562 | 1480.7812 | 5396.625 | 10332.5625 | 10332.5625 | 0
| 2 | 497 | 12632 | 6715 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 35 | 4.5 | 7 | 1 | 6 |  |  | 945 | m3 | OFF HIRED | 2022-07-06 | 2022-09-25 | 100% |  | 11.7143 | 7.5 | 0.7 | 7087.5 | 661.5 | 4961.25 | 2126.25 | 7749 | 14836.5 | 14836.5 | 0
| 2 | 431 | 12591 | 6745 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 18 | 2.5 | 5.5 | 1 | 4.5 |  |  | 202.5 | m3 | OFF HIRED | 2022-07-03 | 2022-09-30 | 100% |  | 12.8571 | 7.5 | 0.7 | 1518.75 | 141.75 | 1063.125 | 455.625 | 1822.5 | 3341.25 | 3341.25 | 0
| 2 | 522 | 12730 | 7843 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 7.5 | 2.5 | 4.5 | 1 | 3.5 |  |  | 65.625 | m3 | OFF HIRED | 2022-07-15 | 2022-08-25 | 100% |  | 6 | 7.5 | 0.7 | 492.1875 | 45.9375 | 344.5312 | 147.6562 | 275.625 | 767.8125 | 767.8125 | 0
| 2 | 703 | 12967 | 6711 |  | Ground Floor Hotel | Access Scaffold |  | Tower | 1.3 | 1 | 3.5 | 1 | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-08-09 | 2022-09-23 | 100% |  | 6.5714 | 135 |  | 337.5 | 0 | 236.25 | 101.25 | 0 | 337.5 | 337.5 | 0
| 2 | 747 | 13014 | 6718 |  | Ground Floor Hotel | Access Scaffold |  | Tower | 1.8 | 1.8 | 3.5 | 1 | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-08-16 | 2022-09-24 | 100% |  | 5.7143 | 135 |  | 337.5 | 0 | 236.25 | 101.25 | 0 | 337.5 | 337.5 | 0
| 2 | 748 | 13014 | 6718 |  | Ground Floor Hotel | Access Scaffold |  | Tower | 1.8 | 1.8 | 3.5 | 1 | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-08-16 | 2022-09-24 | 100% |  | 5.7143 | 135 |  | 337.5 | 0 | 236.25 | 101.25 | 0 | 337.5 | 337.5 | 0
| 2 | 749 | 13015 | 7857 |  | Ground Floor Hotel | Access Scaffold |  | Tower | 2.6 | 1.3 | 8 | 1 | 7 |  |  | 7 | rm | OFF HIRED | 2022-08-16 | 2022-08-27 | 100% |  | 1.7143 | 135 |  | 945 | 0 | 661.5 | 283.5 | 0 | 945 | 945 | 0
| 2 | 607 | 12827 | 7840 |  | Ground Floor Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-27 | 2022-08-22 | 100% |  | 3.8571 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 94.5 | 364.5 | 364.5 | 0
| 2 | 607 | 12827 | 8281 |  | Ground Floor Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-27 | 2022-11-27 | 100% |  | 17.7143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 434 | 704 | 704 | 0
| 2 | 767 | 13029 | 8170 |  | Ground Floor Hotel | Access Scaffold |  | Tower | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-18 | 2022-10-29 | 100% |  | 14.8571 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 364 | 634 | 634 | 0
| 2 | 792 | 13052 | 7847 |  | Ground Floor Hotel | Access Scaffold |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-08-22 | 2022-08-26 | 100% |  | 0.71429 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 21.875 | 359.375 | 359.375 | 0
| 2 | 794 | 13054 | 7854 |  | Ground Floor Hotel | Access Scaffold |  | Tower | 1.8 | 1.8 | 6 |  | 6 |  |  | 6 | rm | OFF HIRED | 2022-08-22 | 2022-08-29 | 100% |  | 1.1429 | 135 | 12.25 | 810 | 73.5 | 567 | 243 | 84 | 894 | 894 | 0
| 2 | 795 | 13055 | 7857 |  | Ground Floor Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 5 |  | 5 |  |  | 5 | rm | OFF HIRED | 2022-08-22 | 2022-08-27 | 100% |  | 0.85714 | 135 | 12.25 | 675 | 61.25 | 472.5 | 202.5 | 52.5 | 727.5 | 727.5 | 0
| 2 | 797 | 13057 | 7876 |  | Ground Floor Hotel | Access Scaffold |  | Tower | 2.5 | 1.3 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-08-22 | 2022-09-06 | 100% |  | 2.2857 | 135 | 12.25 | 540 | 49 | 378 | 162 | 112 | 652 | 652 | 0
| 2 | 797 | 13057 | 7876 |  | Ground Floor Hotel | Access Scaffold |  | Tower | 2.5 | 1.3 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-08-23 | 2022-09-06 | 100% |  | 2.1429 | 135 | 12.25 | 540 | 49 | 378 | 162 | 105 | 645 | 645 | 0
| 2 | 804 | 13066 | 8065 |  | Ground Floor Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-08-24 | 2022-09-30 | 100% |  | 5.4286 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 166.25 | 503.75 | 503.75 | 0
| 2 | 815 | 13078 | 8237 |  | Ground Floor Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 5 |  | 5 |  |  | 5 | rm | OFF HIRED | 2022-08-25 | 2022-11-15 | 100% |  | 11.8571 | 135 | 12.25 | 675 | 61.25 | 472.5 | 202.5 | 726.25 | 1401.25 | 1401.25 | 0
| 2 | 824 | 13092 | 7882 |  | Ground Floor Hotel | Access Scaffold |  | Tower | 2.5 | 1.3 | 5 |  | 5 |  |  | 5 | rm | OFF HIRED | 2022-08-26 | 2022-09-10 | 100% |  | 2.2857 | 135 | 12.25 | 675 | 61.25 | 472.5 | 202.5 | 140 | 815 | 815 | 0
| 2 | 652 | 12876 | 8141 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 12.5 | 1 | 5 | 1 | 4 |  |  | 50 | m2-LxH | OFF HIRED | 2022-08-03 | 2022-10-25 | 100% |  | 12 | 14 | 0 | 700 | 0 | 490 | 210 | 0 | 700 | 700 | 0
| 2 | 605 | 12822 | 7823 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 20 | 1.3 | 3 | 1 | 2 |  |  | 40 | m2-LxH | OFF HIRED | 2022-07-27 | 2022-08-12 | 100% |  | 2.4286 | 14 | 0.84 | 560 | 33.6 | 392 | 168 | 81.6 | 641.6 | 641.6 | 0
| 2 | 709 | 12973 | 8144 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 5 | 1 | 4 | 1 | 3 |  |  | 15 | m2-LxH | OFF HIRED | 2022-08-11 | 2022-10-25 | 100% |  | 10.8571 | 14 | 0.84 | 210 | 12.6 | 147 | 63 | 136.8 | 346.8 | 346.8 | 0
| 2 | 754 | 13019 | 6740 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 27.5 | 1 | 4 | 1 | 3 |  |  | 82.5 | m2-LxH | OFF HIRED | 2022-08-17 | 2022-09-30 | 100% |  | 6.4286 | 14 | 0.84 | 1155 | 69.3 | 808.5 | 346.5 | 445.5 | 1600.5 | 1600.5 | 0
| 2 | 686 | 12896 | 7840 |  | Ground Floor Residence | Access Scaffold |  | Independent | 12.5 | 1.8 | 7 | 1 | 6 |  |  | 75 | m2-LxH | OFF HIRED | 2022-08-08 | 2022-08-22 | 100% |  | 2.1429 | 18 | 1.05 | 1350 | 78.75 | 945 | 405 | 168.75 | 1518.75 | 1518.75 | 0
| 2 | 631 | 12992 | 8066 |  | Ground Floor Residence | Access Scaffold |  | Independent | 13 | 1.8 | 5 | 1 | 4 |  |  | 52 | m2-LxH | OFF HIRED | 2022-08-13 | 2022-10-04 | 100% |  | 7.5714 | 18 | 1.05 | 936 | 54.6 | 655.2 | 280.8 | 413.4 | 1349.4 | 1349.4 | 0
| 2 | 631 | 12992 | 8066 |  | Ground Floor Residence | Birdcage Scaffold |  | Birdcage | 10 | 6 | 5 | 1 | 4 |  |  | 240 | m3 | OFF HIRED | 2022-08-13 | 2022-10-04 | 100% |  | 7.5714 | 7.5 | 0.7 | 1800 | 168 | 1260 | 540 | 1272 | 3072 | 3072 | 0
| 2 | 711 | 12980 | 6703 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 13 | 2.5 | 4 | 1 | 3 |  |  | 97.5 | m3 | OFF HIRED | 2022-08-12 | 2022-09-23 | 100% |  | 6.1429 | 7.5 | 0.7 | 731.25 | 68.25 | 511.875 | 219.375 | 419.25 | 1150.5 | 1150.5 | 0
| 2 | 332 | 13070 | 8061 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 10 | 8 | 4 |  | 4 |  |  | 320 | m3 | OFF HIRED | 2022-08-24 | 2022-10-03 | 100% |  | 5.8571 | 7.5 | 0.7 | 2400 | 224 | 1680 | 720 | 1312 | 3712 | 3712 | 0
| 2 | 162 | 12855 | 8280 |  | Ground Floor Hotel | Cantiliver |  | Cantiliver | 46 | 0.6 |  |  |  | 1 |  | 27.6 | m2-LxW | OFF HIRED | 2022-07-31 | 2022-11-26 | 100% |  | 17 | 36.5 | 3.15 | 1007.4 | 86.94 | 705.18 | 302.22 | 1477.98 | 2485.38 | 2485.38 | 0
| 2 | 879 | 13149 | 8556 |  | Ground Floor Residence | Mobile Tower |  | Mobile Tower | 1.8 | 1.8 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-09-03 | 2023-02-10 | 100% |  | 23 | 100 | 10.15 | 400 | 40.6 | 280 | 120 | 933.8 | 1333.8 | 1155.8 | 178 |  |  | #VALUE! | 1120 | #VALUE! | #VALUE!
| 2 | 879 | 13149 | 8556 |  | Ground Floor Residence | Mobile Tower |  | Mobile Tower | 1.8 | 1.8 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-09-03 | 2023-02-10 | 100% |  | 23 | 100 | 10.15 | 400 | 40.6 | 280 | 120 | 933.8 | 1333.8 | 1155.8 | 178 |  |  | #VALUE! | 1120 | #VALUE! | #VALUE!
| 2 | 879 | 13149 | 8556 |  | Ground Floor Residence | Mobile Tower |  | Mobile Tower | 1.8 | 1.8 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-09-03 | 2023-02-10 | 100% |  | 23 | 100 | 10.15 | 400 | 40.6 | 280 | 120 | 933.8 | 1333.8 | 1155.8 | 178 |  |  | #VALUE! | 1120 | #VALUE! | #VALUE!
| 2 | 879 | 13149 | 8556 |  | Ground Floor Residence | Mobile Tower |  | Mobile Tower | 1.8 | 1.8 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-09-03 | 2023-02-10 | 100% |  | 23 | 100 | 10.15 | 400 | 40.6 | 280 | 120 | 933.8 | 1333.8 | 1155.8 | 178 |  |  | #VALUE! | 1120 | #VALUE! | #VALUE!
| 2 | 913 | 13286 | 8455 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 5 |  | 5 |  |  | 5 | rm | OFF HIRED | 2022-09-08 | 2022-12-22 | 100% |  | 15.1429 | 135 |  | 675 | 0 | 472.5 | 202.5 | 0 | 675 | 675 | 0
| 2 | 838 | 13106 | 7857 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 5 |  | 5 |  |  | 5 | rm | OFF HIRED | 2022-08-26 | 2022-08-27 | 100% |  | 0.28571 | 135 | 12.25 | 675 | 61.25 | 472.5 | 202.5 | 17.5 | 692.5 | 692.5 | 0
| 2 | 834 | 13103 |  |  | Ground Floor Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 3 |  | 3 |  |  | 3 | rm | ON HIRE | 2022-08-26 |  | 100% |  | 26.7143 | 135 | 12.25 | 405 | 36.75 | 283.5 | 0 | 981.75 | 1265.25 | 1118.25 | 147 |  |  | #VALUE! | 283.5 | #VALUE! | #VALUE!
| 2 | 840 | 13109 | 8064 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-08-26 | 2022-10-01 | 100% |  | 5.2857 | 135 | 12.25 | 540 | 49 | 378 | 162 | 259 | 799 | 799 | 0
| 2 | 840 | 13109 | 8064 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-08-26 | 2022-10-01 | 100% |  | 5.2857 | 135 | 12.25 | 540 | 49 | 378 | 162 | 259 | 799 | 799 | 0
| 2 | 825 | 13093 | 8090 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 6 |  | 6 |  |  | 6 | rm | OFF HIRED | 2022-08-26 | 2022-10-10 | 100% |  | 6.5714 | 135 | 12.25 | 810 | 73.5 | 567 | 243 | 483 | 1293 | 1293 | 0
| 2 | 828 | 13096 | 7876 |  | Ground Floor Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-08-26 | 2022-09-06 | 100% |  | 1.7143 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 52.5 | 390 | 390 | 0
| 2 | 828 | 13096 | 7876 |  | Ground Floor Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-08-26 | 2022-09-06 | 100% |  | 1.7143 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 52.5 | 390 | 390 | 0
| 2 | 631 | 13119 | 8070 |  | Ground Floor Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 2.5 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-08-29 | 2022-10-06 | 100% |  | 5.5714 | 135 | 12.25 | 540 | 49 | 378 | 162 | 273 | 813 | 813 | 0
| 2 | 846 | 13115 | 8093 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-29 | 2022-10-11 | 100% |  | 6.2857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 154 | 424 | 424 | 0
| 2 | 870 | 13141 | 8302 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-09-01 | 2022-12-05 | 100% |  | 13.7143 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 504 | 909 | 909 | 0
| 2 | 895 | 13266 | 8071 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 0.6 | 6 |  | 6 |  |  | 6 | rm | OFF HIRED | 2022-09-06 | 2022-10-06 | 100% |  | 4.4286 | 135 | 12.25 | 810 | 73.5 | 567 | 243 | 325.5 | 1135.5 | 1135.5 | 0
| 2 | 943 | 13316 | 8064 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 6 |  | 6 |  |  | 6 | rm | OFF HIRED | 2022-09-12 | 2022-10-01 | 100% |  | 2.8571 | 135 | 12.25 | 810 | 73.5 | 567 | 243 | 210 | 1020 | 1020 | 0
| 2 | 953 | 13328 | 6716 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-14 | 2022-09-24 | 100% |  | 1.5714 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 38.5 | 308.5 | 308.5 | 0
| 2 | 962 | 13337 | 8430 |  | Ground Floor Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 0.6 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-09-15 | 2023-01-17 | 100% |  | 17.8571 | 135 | 12.25 | 540 | 49 | 378 | 162 | 875 | 1415 | 1415 | 0
| 2 | 962 | 13337 | 8430 |  | Ground Floor Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 0.6 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-09-15 | 2023-01-17 | 100% |  | 17.8571 | 135 | 12.25 | 540 | 49 | 378 | 162 | 875 | 1415 | 1415 | 0
| 2 | 845 | 13114 | 8144 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 19 | 1 | 2.5 |  | 2.5 |  |  | 47.5 | m2-LxH | OFF HIRED | 2022-08-27 | 2022-10-25 | 100% |  | 8.5714 | 14 | 0.84 | 665 | 39.9 | 465.5 | 199.5 | 342 | 1007 | 1007 | 0
| 2 | 839 | 13108 | 8470 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 3.5 | 1.3 | 4 |  | 4 |  |  | 14 | m2-LxH | OFF HIRED | 2022-08-26 | 2022-12-26 | 100% |  | 17.5714 | 14 | 0.84 | 196 | 11.76 | 137.2 | 58.8 | 206.64 | 402.64 | 402.64 | 0
| 2 | 832 | 13101 | 8064 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 5 | 1.3 | 4 |  | 4 |  |  | 20 | m2-LxH | OFF HIRED | 2022-08-26 | 2022-10-01 | 100% |  | 5.2857 | 14 | 0.84 | 280 | 16.8 | 196 | 84 | 88.8 | 368.8 | 368.8 | 0
| 2 | 881 | 13251 | 8063 |  | Ground Floor Residence | Access Scaffold |  | Independent | 18 | 1 | 2.5 |  | 2.5 |  |  | 45 | m2-LxH | OFF HIRED | 2022-09-03 | 2022-10-02 | 100% |  | 4.2857 | 14 | 0.84 | 630 | 37.8 | 441 | 189 | 162 | 792 | 792 | 0
| 2 | 553 | 13258 | 8168 |  | Ground Floor Residence | Access Scaffold |  | Independent | 5 | 1.3 | 5 |  | 5 |  |  | 25 | m2-LxH | OFF HIRED | 2022-09-03 | 2022-10-28 | 100% |  | 8 | 14 | 0.84 | 350 | 21 | 245 | 105 | 168 | 518 | 518 | 0
| 2 | 916 | 13289 | 7890 |  | Ground Floor Residence | Access Scaffold |  | Independent | 6 | 1.3 | 3 |  | 3 |  |  | 18 | m2-LxH | OFF HIRED | 2022-09-08 | 2022-09-15 | 100% |  | 1.1429 | 14 | 0.84 | 252 | 15.12 | 176.4 | 75.6 | 17.28 | 269.28 | 269.28 | 0
| 2 | 875 | 13146 | 8302 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 18 | 1 | 7 |  | 7 |  |  | 126 | m2-LxH | OFF HIRED | 2022-09-01 | 2022-12-05 | 100% |  | 13.7143 | 14 | 0.84 | 1764 | 105.84 | 1234.8 | 0 | 1451.52 | 2686.32 | 2686.32 | 0
| 2 | 867 | 13310 | 8061 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 11.3 | 4 | 4 |  | 4 |  |  | 180.8 | m3 | OFF HIRED | 2022-09-12 | 2022-10-03 | 100% |  | 3.1429 | 7.5 | 0.7 | 1356 | 126.56 | 949.2 | 406.8 | 397.76 | 1753.76 | 1753.76 | 0
| 2 | 327 | 12424 | 7580 |  | G F Residance office front lobby | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-06-22 | 2022-06-23 | 100% |  | 0.28571 | 135 | 12.25 | 540 | 49 | 378 | 162 | 14 | 554 | 554 | 0
| 2 | 333 | 12429 | 7588 |  | Ground Floor Residence | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 3 | 1 | 2 |  |  | 10 | m2-LxH | OFF HIRED | 2022-06-22 | 2022-06-28 | 100% |  | 1 | 14 | 0.84 | 140 | 8.4 | 98 | 42 | 8.4 | 148.4 | 148.4 | 0
| 2 | 183 | 12180 | 7566 |  | Ground Floor Residence | Access Scaffold |  | INDEPENDENT | 2.5 | 1.8 | 4 | 1 | 3 |  |  | 7.5 | m2-LxH | OFF HIRED | 2022-06-08 | 2022-06-19 | 100% |  | 1.7143 | 18 | 1.05 | 135 | 7.875 | 94.5 | 40.5 | 13.5 | 148.5 | 148.5 | 0
| 2 | 616 | 12836 | 8196 |  | Ground Floor Residence | Access Scaffold |  | Tower | 1.8 | 1.3 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-07-28 | 2022-11-05 | 100% |  | 14.4286 | 135 |  | 540 | 0 | 378 | 162 | 0 | 540 | 540 | 0
| 2 | 625 | 12845 | 7891 |  | Ground Floor Residence | Access Scaffold |  | Tower | 2.5 | 2.5 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-07-29 | 2022-09-15 | 100% |  | 7 | 135 |  | 540 | 0 | 378 | 162 | 0 | 540 | 540 | 0
| 2 | 623 | 12842 | 8294 |  | Ground Floor Residence | Access Scaffold |  | Tower | 1.8 | 1.3 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-07-29 | 2022-11-30 | 100% |  | 17.8571 | 135 | 12.25 | 540 | 49 | 378 | 162 | 875 | 1415 | 1415 | 0
| 2 | A625 | 12846 | 7894 |  | Ground Floor Residence | Access Scaffold |  | Tower | 1.8 | 1.3 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-07-29 | 2022-09-15 | 100% |  | 7 | 135 | 12.25 | 540 | 49 | 378 | 162 | 343 | 883 | 883 | 0
| 2 | 655 | 12879 | 8317 |  | Ground Floor Residence | Access Scaffold |  | Tower | 1.3 | 0.6 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-08-03 | 2022-12-09 | 100% |  | 18.4286 | 135 | 12.25 | 540 | 49 | 378 | 162 | 903 | 1443 | 1443 | 0
| 2 | 732 | 12988 | 8290 |  | Ground Floor Residence | Access Scaffold |  | Tower | 1.8 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-08-13 | 2022-11-29 | 100% |  | 15.5714 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 572.25 | 977.25 | 977.25 | 0
| 2 | 736 | 12993 | 7844 |  | Ground Floor Residence | Access Scaffold |  | Tower | 1.8 | 0.6 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-08-14 | 2022-08-25 | 100% |  | 1.7143 | 135 | 12.25 | 540 | 49 | 378 | 162 | 84 | 624 | 624 | 0
| 2 | 774 | 13036 | 8253 |  | Ground Floor Residence | Access Scaffold |  | Tower | 1.3 | 1.3 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-08-19 | 2022-11-18 | 100% |  | 13.1429 | 135 | 12.25 | 540 | 49 | 378 | 162 | 644 | 1184 | 1184 | 0
| 2 | 822 | 13091 | 7876 |  | Ground Floor Residence | Access Scaffold |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-08-25 | 2022-09-06 | 100% |  | 1.8571 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 56.875 | 394.375 | 394.375 | 0
| 2 | 822 | 13091 | 7876 |  | Ground Floor Residence | Access Scaffold |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-08-25 | 2022-09-06 | 100% |  | 1.8571 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 56.875 | 394.375 | 394.375 | 0
| 2 | 822 | 13091 | 7876 |  | Ground Floor Residence | Access Scaffold |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-08-25 | 2022-09-06 | 100% |  | 1.8571 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 56.875 | 394.375 | 394.375 | 0
| 2 | 601 | 12821 | 7891 |  | Ground Floor Residence | Access Scaffold |  | Independent | 14 | 1.3 | 5 | 1 | 4 |  |  | 56 | m2-LxH | OFF HIRED | 2022-07-27 | 2022-09-15 | 100% |  | 7.2857 | 14 | 0.84 | 784 | 47.04 | 548.8 | 235.2 | 342.72 | 1126.72 | 1126.72 | 0
| 2 | 595 | 12815 | 8412 |  | Ground Floor Residence | Access Scaffold |  | Independent | 6 | 1.3 | 4 | 1 | 3 |  |  | 18 | m2-LxH | OFF HIRED | 2022-07-26 | 2023-01-11 | 100% |  | 24.2857 | 14 | 0.84 | 252 | 15.12 | 176.4 | 75.6 | 367.2 | 619.2 | 619.2 | 0
| 2 | 630 | 12851 | 7888 |  | Ground Floor Residence | Access Scaffold |  | Independent | 10 | 1.8 | 4 | 1 | 3 |  |  | 30 | m2-LxH | OFF HIRED | 2022-07-31 | 2022-09-14 | 100% |  | 6.5714 | 18 | 1.05 | 540 | 31.5 | 378 | 162 | 207 | 747 | 747 | 0
| 2 | 653 | 12877 | 7889 |  | Ground Floor Residence | Access Scaffold |  | Independent | 5 | 1.8 | 4 | 1 | 3 |  |  | 15 | m2-LxH | OFF HIRED | 2022-08-03 | 2022-09-14 | 100% |  | 6.1429 | 18 | 1.05 | 270 | 15.75 | 189 | 81 | 96.75 | 366.75 | 366.75 | 0
| 2 | 735 | 12991 | 6747 |  | Ground Floor Residence | Birdcage Scaffold |  | Birdcage | 17.5 | 2.5 | 5 | 1 | 4 |  |  | 175 | m3 | OFF HIRED | 2022-08-13 | 2022-09-30 | 100% |  | 7 | 7.5 | 0.7 | 1312.5 | 122.5 | 918.75 | 393.75 | 857.5 | 2170 | 2170 | 0
| 2 | 653 | 12877 | 7889 |  | Ground Floor Residence | Birdcage Scaffold |  | Birdcage | 12 | 5 | 4 | 1 | 3 |  |  | 180 | m3 | OFF HIRED | 2022-08-03 | 2022-09-14 | 100% |  | 6.1429 | 7.5 | 0.7 | 1350 | 126 | 945 | 405 | 774 | 2124 | 2124 | 0
| 2 | 617 | 12837 | 7806 |  | Ground Floor Residence | Birdcage Scaffold |  | Birdcage | 16.5 | 2.5 | 5 | 1 | 4 |  |  | 165 | m3 | OFF HIRED | 2022-07-28 | 2022-08-05 | 100% |  | 1.2857 | 7.5 | 0.7 | 1237.5 | 115.5 | 866.25 | 371.25 | 148.5 | 1386 | 1386 | 0
| 2 | 629 | 12852 | 7888 |  | Ground Floor Residence | Birdcage Scaffold |  | Birdcage | 7.5 | 2.5 | 4 | 1 | 3 |  |  | 56.25 | m3 | OFF HIRED | 2022-07-31 | 2022-09-14 | 100% |  | 6.5714 | 7.5 | 0.7 | 421.875 | 39.375 | 295.3125 | 126.5625 | 258.75 | 680.625 | 680.625 | 0
| 2 | 631 | 12853 |  |  | Ground Floor Residence | Birdcage Scaffold |  | Birdcage | 6.5 | 4 | 5 | 1 | 4 |  |  | 104 | m3 | ON HIRE | 2022-07-31 |  | 100% |  | 30.4286 | 7.5 | 0.7 | 780 | 72.8 | 546 | 0 | 2215.2 | 2761.2 | 2470 | 291.2 |  |  | #VALUE! | 546 | #VALUE! | #VALUE!
| 2 | 601 | 12821 | 7891 |  | Ground Floor Residence | Cantiliver |  | Cantiliver | 14 | 0.6 |  |  |  | 1 |  | 8.4 | m2-LxW | OFF HIRED | 2022-07-27 | 2022-09-15 | 100% |  | 7.2857 | 36.5 | 3.15 | 306.6 | 26.46 | 214.62 | 91.98 | 192.78 | 499.38 | 499.38 | 0
| 2 | 859 | 13130 | 8065 |  | Ground Floor Residence | Access Scaffold |  | Independent | 10 | 1.3 | 4 |  | 4 |  |  | 40 | m2-LxH | OFF HIRED | 2022-08-30 | 2022-09-30 | 100% |  | 4.5714 | 14 | 0.84 | 560 | 33.6 | 392 | 168 | 153.6 | 713.6 | 713.6 | 0
| 2 | 927 | 13298 | 8063 |  | Ground Floor Residence | Access Scaffold |  | Independent | 4 | 1.3 | 2.5 |  | 2.5 |  |  | 10 | m2-LxH | OFF HIRED | 2022-09-09 | 2022-10-02 | 100% |  | 3.4286 | 14 | 0.84 | 140 | 8.4 | 98 | 42 | 28.8 | 168.8 | 168.8 | 0
| 2 | 947 | 13322 | 8191 |  | Ground Floor Residence | Access Scaffold |  | Independent | 9 | 1.3 | 4 |  | 4 |  |  | 36 | m2-LxH | OFF HIRED | 2022-09-12 | 2022-11-04 | 100% |  | 7.7143 | 14 | 0.84 | 504 | 30.24 | 352.8 | 151.2 | 233.28 | 737.28 | 737.28 | 0
| 2 | 856 | 13127 | 6734 |  | Ground Floor Residence | Access Scaffold |  | Independent | 5 | 1.8 | 4 |  | 4 |  |  | 20 | m2-LxH | OFF HIRED | 2022-08-30 | 2022-09-28 | 100% |  | 4.2857 | 18 | 1.05 | 360 | 21 | 252 | 108 | 90 | 450 | 450 | 0
| 2 | 887 | 13257 | 8093 |  | Ground Floor Residence | Access Scaffold |  | Independent | 4 | 1.8 | 4 |  | 4 |  |  | 16 | m2-LxH | OFF HIRED | 2022-09-03 | 2022-10-11 | 100% |  | 5.5714 | 18 | 1.05 | 288 | 16.8 | 201.6 | 86.4 | 93.6 | 381.6 | 381.6 | 0
| 2 | 866 | 13138 | 8061 |  | Ground Floor Residence | Birdcage Scaffold |  | Birdcage | 12 | 3.1 | 3.5 |  | 3.5 |  |  | 130.2 | m3 | OFF HIRED | 2022-08-31 | 2022-10-03 | 100% |  | 4.8571 | 7.5 | 0.7 | 976.5 | 91.14 | 683.55 | 292.95 | 442.68 | 1419.18 | 1419.18 | 0
| 2 | 866 | 13138 | 8061 |  | Ground Floor Residence | Birdcage Scaffold |  | Birdcage | 17.5 | 4 | 3.5 |  | 3.5 |  |  | 245 | m3 | OFF HIRED | 2022-08-31 | 2022-10-03 | 100% |  | 4.8571 | 7.5 | 0.7 | 1837.5 | 171.5 | 1286.25 | 551.25 | 833 | 2670.5 | 2670.5 | 0
| 2 | 867 | 13138 | 8061 |  | Ground Floor Residence | Birdcage Scaffold |  | Birdcage | 20 | 5 | 3.5 |  | 3.5 |  |  | 350 | m3 | OFF HIRED | 2022-08-31 | 2022-10-03 | 100% |  | 4.8571 | 7.5 | 0.7 | 2625 | 245 | 1837.5 | 787.5 | 1190 | 3815 | 3815 | 0
| 2 | 889 | 13260 | 7887 |  | Ground Floor Residence | Birdcage Scaffold |  | Birdcage | 14.5 | 4 | 4 |  | 4 |  |  | 232 | m3 | OFF HIRED | 2022-09-03 | 2022-09-14 | 100% |  | 1.7143 | 7.5 | 0.7 | 1740 | 162.4 | 1218 | 522 | 278.4 | 2018.4 | 2018.4 | 0
| 2 | 889 | 13318 | 7302 |  | Ground Floor Residence | Birdcage Scaffold |  | Birdcage | 15 | 4 | 4 |  | 4 |  |  | 240 | m3 | OFF HIRED | 2022-09-10 | 2022-12-05 | 100% |  | 12.4286 | 7.5 | 0.7 | 1800 | 168 | 1260 | 540 | 2088 | 3888 | 3888 | 0
| 2 | 1023 | 13458 | 8287 |  | Ground Floor Residence | Mobile Tower |  | Mobile Tower | 1.8 | 1.8 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-09-22 | 2022-11-28 | 100% |  | 9.7143 | 100 | 10.15 | 400 | 40.6 | 280 | 120 | 394.4 | 794.4 | 794.4 | 0
| 2 | 1024 | 13459 | 8188 |  | Ground Floor Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 3.5 |  | 3.5 |  |  | 3.5 | rm | OFF HIRED | 2022-09-22 | 2022-11-03 | 100% |  | 6.1429 | 135 | 12.25 | 472.5 | 42.875 | 330.75 | 141.75 | 263.375 | 735.875 | 735.875 | 0
| 2 | 1028 | 13463 | 8432 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-09-23 | 2023-01-17 | 100% |  | 16.7143 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 511.875 | 849.375 | 849.375 | 0
| 2 | 1028 | 13463 | 8432 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 3.3 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-09-23 | 2023-01-17 | 100% |  | 16.7143 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 511.875 | 849.375 | 849.375 | 0
| 2 | 1039 | 13476 | 8079 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-09-23 | 2022-10-07 | 100% |  | 2.1429 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 65.625 | 403.125 | 403.125 | 0
| 2 | 1039 | 13476 | 8079 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-09-23 | 2022-10-07 | 100% |  | 2.1429 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 65.625 | 403.125 | 403.125 | 0
| 2 | 975 | 13351 | 8071 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 7 |  | 7 |  |  | 7 | rm | OFF HIRED | 2022-09-16 | 2022-10-06 | 100% |  | 3 | 135 | 12.25 | 945 | 85.75 | 661.5 | 283.5 | 257.25 | 1202.25 | 1202.25 | 0
| 2 | 998 | 13382 | 8243 |  | Ground Floor Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.8 | 3.5 |  | 3.5 |  |  | 3.5 | rm | OFF HIRED | 2022-09-20 | 2022-11-16 | 100% |  | 8.2857 | 135 | 12.25 | 472.5 | 42.875 | 330.75 | 141.75 | 355.25 | 827.75 | 827.75 | 0
| 2 | 980 | 13358 | 8063 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 5 | 1.3 | 3 |  | 3 |  |  | 15 | m2-LxH | OFF HIRED | 2022-09-16 | 2022-10-02 | 100% |  | 2.4286 | 14 |  | 210 | 0 | 147 | 63 | 0 | 210 | 210 | 0
| 2 | 1032 | 13469 | 8237 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 5 | 1 | 2.5 |  | 2.5 |  |  | 12.5 | m2-LxH | OFF HIRED | 2022-09-23 | 2022-11-15 | 100% |  | 7.7143 | 14 | 0.84 | 175 | 10.5 | 122.5 | 52.5 | 81 | 256 | 256 | 0
| 2 | 1040 | 13477 | 8240 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 4 | 1.3 | 4 |  | 4 |  |  | 16 | m2-LxH | OFF HIRED | 2022-09-23 | 2022-11-15 | 100% |  | 7.7143 | 14 | 0.84 | 224 | 13.44 | 156.8 | 67.2 | 103.68 | 327.68 | 327.68 | 0
| 2 | 631 | 13486 | 8063 |  | Ground Floor Residence | Access Scaffold |  | Independent | 16 | 1.8 | 4 |  | 4 |  |  | 64 | m2-LxH | OFF HIRED | 2022-09-26 | 2022-10-02 | 100% |  | 1 | 14 | 0.84 | 896 | 53.76 | 627.2 | 268.8 | 53.76 | 949.76 | 949.76 | 0
| 2 | 976 | 13352 | 8643 |  | Ground Floor Residence | Access Scaffold |  | Independent | 6.3 | 1 | 4 |  | 4 |  |  | 25.2 | m2-LxH | OFF HIRED | 2022-09-16 | 2023-02-07 | 100% |  | 20.7143 | 14 | 0.84 | 352.8 | 21.168 | 246.96 | 105.84 | 438.48 | 791.28 | 664.272 | 127.008 |  |  | #VALUE! | 246.96 | #VALUE! | #VALUE!
| 2 | 978 | 13354 | 8209 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 4 | 1.3 | 6.5 |  | 6.5 |  |  | 26 | m2-LxH | OFF HIRED | 2022-09-16 | 2022-11-07 | 100% |  | 7.5714 | 14 | 0.84 | 364 | 21.84 | 254.8 | 109.2 | 165.36 | 529.36 | 529.36 | 0
| 2 | 983 | 13361 | 8164 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 4 | 1.3 | 3.5 |  | 3.5 |  |  | 14 | m2-LxH | OFF HIRED | 2022-09-17 | 2022-10-28 | 100% |  | 6 | 14 | 0.84 | 196 | 11.76 | 137.2 | 58.8 | 70.56 | 266.56 | 266.56 | 0
| 2 | 984 | 13362 | 8193 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 17.5 | 1.3 | 3 |  | 3 |  |  | 52.5 | m2-LxH | OFF HIRED | 2022-09-17 | 2022-11-05 | 100% |  | 7.1429 | 14 | 0.84 | 735 | 44.1 | 514.5 | 220.5 | 315 | 1050 | 1050 | 0
| 2 | 988 | 13368 | 8123 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 7.5 | 1.3 | 3 |  | 3 |  |  | 22.5 | m2-LxH | OFF HIRED | 2022-09-17 | 2022-10-19 | 100% |  | 4.7143 | 14 | 0.84 | 315 | 18.9 | 220.5 | 94.5 | 89.1 | 404.1 | 404.1 | 0
| 2 | 974 | 13350 | 8056 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 8 | 1.3 | 3.5 |  | 3.5 |  |  | 28 | m2-LxH | OFF HIRED | 2022-09-16 | 2022-10-02 | 100% |  | 2.4286 | 14 | 0.84 | 392 | 23.52 | 274.4 | 117.6 | 57.12 | 449.12 | 449.12 | 0
| 2 | 1033 | 13470 |  |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 2.5 |  | 2.5 |  |  | 25 | m3 | ON HIRE | 2022-09-23 |  | 100% |  | 22.7143 | 7.5 | 0.7 | 187.5 | 17.5 | 131.25 | 0 | 397.5 | 528.75 | 458.75 | 70 |  |  | #VALUE! | 131.25 | #VALUE! | #VALUE!
| 2 | 998 | 13382 | 8243 |  | Ground Floor Residence | Birdcage Scaffold |  | Birdcage | 3 | 2.5 | 3.5 |  | 3.5 |  |  | 26.25 | m3 | OFF HIRED | 2022-09-20 | 2022-11-16 | 100% |  | 8.2857 | 7.5 | 0.7 | 196.875 | 18.375 | 137.8125 | 59.0625 | 152.25 | 349.125 | 349.125 | 0
| 2 | 162 | 13355 | 8264 |  | Ground Floor Hotel | Cantiliver |  | Cantiliver | 10 | 1 |  |  |  | 1 |  | 10 | m2-LxW | OFF HIRED | 2022-09-16 | 2022-11-22 | 100% |  | 9.7143 | 36.5 | 3.15 | 365 | 31.5 | 255.5 | 109.5 | 306 | 671 | 671 | 0
| 2 | 162 | 13355 | 8264 |  | Ground Floor Hotel | Cantiliver |  | Cantiliver | 10 | 1 |  |  |  | 1 |  | 10 | m2-LxW | OFF HIRED | 2022-09-16 | 2022-11-22 | 100% |  | 9.7143 | 36.5 | 3.15 | 365 | 31.5 | 255.5 | 109.5 | 306 | 671 | 671 | 0
| 2 | 162 | 13355 | 8264 |  | Ground Floor Hotel | Cantiliver |  | Cantiliver | 10 | 1 |  |  |  | 1 |  | 10 | m2-LxW | OFF HIRED | 2022-09-16 | 2022-11-22 | 100% |  | 9.7143 | 36.5 | 3.15 | 365 | 31.5 | 255.5 | 109.5 | 306 | 671 | 671 | 0
| 2 | 1041 | 13485 |  |  | Ground to Lev 6 Zone 10-11 Residence | Chain Pully With Ladder Beam |  | Independent | 4 | 14 |  |  |  | 1 |  | 56 | m2-LxW | ON HIRE | 2022-09-26 |  | 100% |  | 22.2857 | 81 | 1.82 | 4536 | 101.92 | 3175.2 | 0 | 2271.36 | 5446.56 | 5038.88 | 407.68 |  |  | #VALUE! | 4876.2 | #VALUE! | #VALUE!
| 2 | 1041 | 13485 | 8160 |  | PARTIAL DISMANTEL |  |  |  | 4 | 7 |  |  | 0 | 1 |  | 28 | m2-LxW | OFF HIRED | 2022-10-27 | 2023-02-28 | 100% |  | -17.8571 | 81 | 1.82 | 2268 | 50.96 |  | 680.4 | -910 | -229.6 | -25.76 | -203.84 |  |  | #VALUE! | 4876.2 | #VALUE! | #VALUE!
| 2 | 1041 | 13485 |  |  | Ground to Lev 6 Zone 10-11 Residence | Chain Pully With Ladder Beam |  | Independent | 6 | 5 |  |  |  | 1 |  | 30 | m2-LxW | ON HIRE | 2022-09-26 |  | 100% |  | 22.2857 | 81 | 1.82 | 2430 | 54.6 | 1701 | 0 | 1216.8 | 2917.8 | 2699.4 | 218.4 |  |  | #VALUE! | 4876.2 | #VALUE! | #VALUE!
| 2 | 1041 | 13485 | 8160 |  | PARTIAL DISMANTEL |  |  |  | 3 | 6 |  |  | 0 | 1 |  | 18 | m2-LxW | OFF HIRED | 2022-10-27 | 2023-02-28 | 100% |  | -17.8571 | 81 | 1.82 | 1458 | 32.76 |  | 437.4 | -585 | -147.6 | -16.56 | -131.04 |  |  | #VALUE! | 4876.2 | #VALUE! | #VALUE!
| 2 | 1041 | 13484 | 8159 |  | Ground to Lev 6 Zone 10-11 Residence | HEAVY DUTY Cradle Landing |  | Birdcage | 15 | 5 |  |  |  | 1 |  | 75 | m2-LxW | OFF HIRED | 2022-09-26 | 2022-10-27 | 100% |  | 4.5714 | 12 | 3.15 | 900 | 236.25 | 630 | 270 | 1080 | 1980 | 1980 | 0
| 2 | 1041 | 13483 |  |  | Ground to Lev 6 Zone 10-11 Residence | Chain Pully |  | Independent | 32.5 | 1 | 16 |  | 16 |  |  | 520 | m2-LxH | ON HIRE | 2022-09-26 |  | 100% |  | 22.2857 | 14 | 0.84 | 7280 | 436.8 | 5096 | 0 | 9734.4 | 14830.4 | 13083.2 | 1747.2 |  |  | #VALUE! | 18900.2188 | #VALUE! | #VALUE!
| 2 | 1041 | 13483 | 8158 |  | PARTIAL DISMANTEL |  |  |  | 17.5 | 1 | 16 |  | 16 | 1 |  | 280 | m2-LxH | OFF HIRED | 2022-10-27 | 2023-02-28 | 100% |  | -17.8571 | 14 | 0.84 | 3920 | 235.2 |  | 1176 | -4200 | -3024 | -2083.2 | -940.8 |  |  | #VALUE! | 18900.2188 | #VALUE! | #VALUE!
| 2 | 1041 | 13483 | 8158 |  | Ground to Lev 6 Zone 10-11 Residence | Chain Pully |  | Buttress | 32.5 | 2.5 | 25 |  | 25 |  |  | 2031.25 | m3 | OFF HIRED | 2022-09-26 | 2022-10-27 | 100% |  | 4.5714 | 5.25 | 0.35 | 10664.0625 | 710.9375 | 7464.8438 | 3199.2188 | 3250 | 13914.0625 | 13914.0625 | 0
| 2 | 1041 | 13483 |  |  | Ground to Lev 6 Zone 10-11 Residence | Chain Pully |  | Buttress | 17.5 | 2.5 | 18 |  | 18 |  |  | 787.5 | m3 | ON HIRE | 2022-09-26 |  | 100% |  | 22.2857 | 5.25 | 0.35 | 4134.375 | 275.625 | 2894.0625 | 0 | 6142.5 | 9036.5625 | 7934.0625 | 1102.5 |  |  | #VALUE! | 18900.2188 | #VALUE! | #VALUE!
| 2 | 1041 | 13483 |  |  | Ground to Lev 6 Zone 10-11 Residence | Chain Pully |  | Buttress | 15 | 2.5 | 25 |  | 25 |  |  | 937.5 | m3 | ON HIRE | 2022-09-26 |  | 100% |  | 22.2857 | 5.25 | 0.35 | 4921.875 | 328.125 | 3445.3125 | 0 | 7312.5 | 10757.8125 | 9445.3125 | 1312.5 |  |  | #VALUE! | 18900.2188 | #VALUE! | #VALUE!
| 2 | 1041 | 13483 | 8158 |  | PARTIAL DISMANTEL |  |  |  | 2.5 | 2.5 | 25 |  | 25 | 1 |  | 156.25 | m3 | OFF HIRED | 2022-10-27 | 2023-02-28 | 100% |  | -17.8571 | 5.25 | 0.35 | 820.3125 | 54.6875 |  | 246.0938 | -976.5625 | -730.4688 | -511.7188 | -218.75 |  |  | #VALUE! | 18900.2188 | #VALUE! | #VALUE!
| 2 |  | 12083 | 7561 |  | Gorund Floor Ball Room Hotel Tower | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 3 | 1 | 2 |  |  | 10 | m2-LxH | OFF HIRED | 2022-05-18 | 2022-06-05 | 100% |  | 2.7143 | 14 |  | 140 | 0 | 98 | 42 | 0 | 140 | 140 | 0
| 2 |  | 12804 | 7562 |  | Gorund Floor Ball Room Hotel Tower | Access Scaffold |  | INDEPENDENT | 2.5 | 1.3 | 3 | 1 | 2 |  |  | 5 | m2-LxH | OFF HIRED | 2022-05-18 | 2022-06-05 | 100% |  | 2.7143 | 14 |  | 70 | 0 | 49 | 21 | 0 | 70 | 70 | 0
| 2 |  | 12085 | 7561 |  | Gorund Floor Ball Room Hotel Tower | Access Scaffold |  | INDEPENDENT | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2.6 | m2-LxH | OFF HIRED | 2022-05-18 | 2022-06-05 | 100% |  | 2.7143 | 14 |  | 36.4 | 0 | 25.48 | 10.92 | 0 | 36.4 | 36.4 | 0
| 2 | 1201 | 13687 | 8211 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 6 |  | 6 |  |  | 6 | rm | OFF HIRED | 2022-10-13 | 2022-11-09 | 100% |  | 4 | 135 | 12.25 | 810 | 73.5 | 567 | 243 | 294 | 1104 | 1104 | 0
| 2 | 1154 | 13639 | 8216 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-10-07 | 2022-11-09 | 100% |  | 4.8571 | 135 | 12.25 | 540 | 49 | 378 | 162 | 238 | 778 | 778 | 0
| 2 | 1160 | 13645 | 8304 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-10-10 | 2022-12-06 | 100% |  | 8.2857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 203 | 473 | 473 | 0
| 2 | 1072 | 13508 | 8180 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-09-27 | 2022-11-01 | 100% |  | 5.1429 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 157.5 | 495 | 495 | 0
| 2 | 1176 | 13661 | 8104 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-10-10 | 2022-10-14 | 100% |  | 0.71429 | 135 | 12.25 | 540 | 49 | 378 | 162 | 35 | 575 | 575 | 0
| 2 | 1101 | 13534 | 8212 |  | Ground Floor Residence | HEAVY DUTY TOWER |  | Tower | 1 | 1 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-10-01 | 2022-11-09 | 100% |  | 5.7143 | 135 | 12.25 | 540 | 49 | 378 | 162 | 280 | 820 | 820 | 0
| 2 | 1134 | 13618 | 8216 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-10-04 | 2022-11-09 | 100% |  | 5.2857 | 135 | 12.25 | 540 | 49 | 378 | 162 | 259 | 799 | 799 | 0
| 2 | 1134 | 13618 | 8216 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-10-04 | 2022-11-09 | 100% |  | 5.2857 | 135 | 12.25 | 540 | 49 | 378 | 162 | 259 | 799 | 799 | 0
| 2 | 1127 | 13611 | 8099 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-10-04 | 2022-10-12 | 100% |  | 1.2857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 31.5 | 301.5 | 301.5 | 0
| 2 | 1155 | 13640 | 8153 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1 | 6 |  | 6 |  |  | 6 | rm | OFF HIRED | 2022-10-07 | 2022-10-27 | 100% |  | 3 | 135 |  | 810 | 0 | 567 | 243 | 0 | 810 | 810 | 0
| 2 | 1245 | 13783 | 8280 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 6 |  | 6 |  |  | 6 | rm | OFF HIRED | 2022-10-18 | 2022-11-26 | 100% |  | 5.7143 | 135 | 12.25 | 810 | 73.5 | 567 | 243 | 420 | 1230 | 1230 | 0
| 2 | 1245 | 13783 | 8280 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 1 | 1 | 6 |  | 6 |  |  | 6 | rm | OFF HIRED | 2022-10-18 | 2022-11-26 | 100% |  | 5.7143 | 135 | 12.25 | 810 | 73.5 | 567 | 243 | 420 | 1230 | 1230 | 0
| 2 | 1254 | 13792 | 8164 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 0.6 | 6 |  | 6 |  |  | 6 | rm | OFF HIRED | 2022-10-20 | 2022-10-28 | 100% |  | 1.2857 | 135 | 12.25 | 810 | 73.5 | 567 | 243 | 94.5 | 904.5 | 904.5 | 0
| 2 | 1258 | 13796 | 8211 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 0.6 | 6 |  | 6 |  |  | 6 | rm | OFF HIRED | 2022-10-20 | 2022-11-09 | 100% |  | 3 | 135 | 12.25 | 810 | 73.5 | 567 | 243 | 220.5 | 1030.5 | 1030.5 | 0
| 2 | 1257 | 13795 | 8280 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1 | 6 |  | 6 |  |  | 6 | rm | OFF HIRED | 2022-10-20 | 2022-11-26 | 100% |  | 5.4286 | 135 | 12.25 | 810 | 73.5 | 567 | 243 | 399 | 1209 | 1209 | 0
| 2 | 1277 | 13716 | 8144 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.2 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-10-22 | 2022-10-25 | 100% |  | 0.57143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 14 | 284 | 284 | 0
| 2 | 1192 | 13677 | 8142 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 3.5 | 1.3 | 2 |  | 2 |  |  | 7 | m2-LxH | OFF HIRED | 2022-10-12 | 2022-10-25 | 100% |  | 2 | 14 | 0.84 | 98 | 5.88 | 68.6 | 29.4 | 11.76 | 109.76 | 109.76 | 0
| 2 | 1207 | 13693 | 8193 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 4 | 1.3 | 3.5 |  | 3.5 |  |  | 14 | m2-LxH | OFF HIRED | 2022-10-14 | 2022-11-05 | 100% |  | 3.2857 | 14 | 0.84 | 196 | 11.76 | 137.2 | 58.8 | 38.64 | 234.64 | 234.64 | 0
| 2 | 1166 | 13651 | 8164 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 13 | 1.3 | 6 |  | 6 |  |  | 78 | m2-LxH | OFF HIRED | 2022-10-10 | 2022-10-28 | 100% |  | 2.7143 | 14 | 0.84 | 1092 | 65.52 | 764.4 | 327.6 | 177.84 | 1269.84 | 1269.84 | 0
| 2 | 1174 | 13659 | 8113 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 6 | 0.6 | 6 |  | 6 |  |  | 36 | m2-LxH | OFF HIRED | 2022-10-10 | 2022-10-17 | 100% |  | 1.1429 | 14 | 0.84 | 504 | 30.24 | 352.8 | 151.2 | 34.56 | 538.56 | 538.56 | 0
| 2 | 1128 | 13612 | 8224 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 5 | 1.3 | 2 |  | 2 |  |  | 10 | m2-LxH | OFF HIRED | 2022-10-04 | 2022-11-11 | 100% |  | 5.5714 | 14 | 0.84 | 140 | 8.4 | 98 | 42 | 46.8 | 186.8 | 186.8 | 0
| 2 | 1244 | 13782 | 8455 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 12.5 | 1.3 | 6 |  | 6 |  |  | 75 | m2-LxH | OFF HIRED | 2022-10-18 | 2022-12-22 | 100% |  | 9.4286 | 14 | 0.84 | 1050 | 63 | 735 | 315 | 594 | 1644 | 1644 | 0
| 2 | 1233 | 13771 | 8182 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 3 | 1.3 | 2 |  | 2 |  |  | 6 | m2-LxH | OFF HIRED | 2022-10-17 | 2022-10-31 | 100% |  | 2.1429 | 14 | 0.84 | 84 | 5.04 | 58.8 | 25.2 | 10.8 | 94.8 | 94.8 | 0
| 2 | 1135 | 13619 | 8192 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 5 | 1.3 | 4 |  | 4 |  |  | 20 | m2-LxH | OFF HIRED | 2022-10-05 | 2022-11-03 | 100% |  | 4.2857 | 14 | 0.84 | 280 | 16.8 | 196 | 84 | 72 | 352 | 352 | 0
| 2 | 1210 | 13696 | 8110 |  | Ground Floor To Basement 1 Residence | Access Scaffold |  | Independent | 19.5 | 1.3 | 2.5 |  | 2.5 |  |  | 48.75 | m2-LxH | OFF HIRED | 2022-10-14 | 2022-10-16 | 100% |  | 0.42857 | 14 | 0.84 | 682.5 | 40.95 | 477.75 | 204.75 | 17.55 | 700.05 | 700.05 | 0
| 2 | 1281 | 13720 | 8226 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 23 | 1 | 6 |  | 6 |  |  | 138 | m2-LxH | OFF HIRED | 2022-10-24 | 2022-11-12 | 100% |  | 2.8571 | 14 | 0.84 | 1932 | 115.92 | 1352.4 | 579.6 | 331.2 | 2263.2 | 2263.2 | 0
| 2 | 1283 | 13722 | 8215 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 3.9 | 0.6 | 4 |  | 4 |  |  | 15.6 | m2-LxH | OFF HIRED | 2022-10-24 | 2022-11-09 | 100% |  | 2.4286 | 14 | 0.84 | 218.4 | 13.104 | 152.88 | 65.52 | 31.824 | 250.224 | 250.224 | 0
| 2 | 1290 | 13729 | 8205 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 23 | 1 | 6 |  | 6 |  |  | 138 | m2-LxH | OFF HIRED | 2022-10-24 | 2022-11-07 | 100% |  | 2.1429 | 14 | 0.84 | 1932 | 115.92 | 1352.4 | 579.6 | 248.4 | 2180.4 | 2180.4 | 0
| 2 | 1158 | 13643 | 8123 |  | Ground Floor Residence | Access Scaffold |  | Independent | 6 | 1.8 | 2 |  | 2 |  |  | 12 | m2-LxH | OFF HIRED | 2022-10-10 | 2022-10-19 | 100% |  | 1.4286 | 18 | 1.05 | 216 | 12.6 | 151.2 | 64.8 | 18 | 234 | 234 | 0
| 2 | 1069 | 13505 | 8315 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 8 | 1.8 | 6 |  | 6 |  |  | 48 | m2-LxH | OFF HIRED | 2022-09-27 | 2022-12-09 | 100% |  | 10.5714 | 18 | 1.05 | 864 | 50.4 | 604.8 | 259.2 | 532.8 | 1396.8 | 1396.8 | 0
| 2 | 1255 | 13793 | 8311 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 2.8 | 1.8 | 6 |  | 6 |  |  | 16.8 | m2-LxH | OFF HIRED | 2022-10-20 | 2022-12-07 | 100% |  | 7 | 18 | 1.05 | 302.4 | 17.64 | 211.68 | 90.72 | 123.48 | 425.88 | 425.88 | 0
| 2 | 1261 | 13799 | 8139 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 30 | 1.8 | 2 |  | 2 |  |  | 60 | m2-LxH | OFF HIRED | 2022-10-20 | 2022-10-24 | 100% |  | 0.71429 | 18 | 1.05 | 1080 | 63 | 756 | 324 | 45 | 1125 | 1125 | 0
| 2 | 1111 | 13545 |  |  | Ground Floor Residence | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 4 |  | 4 |  |  | 40 | m3 | ON HIRE | 2022-10-03 |  | 100% |  | 21.2857 | 7.5 | 0.7 | 300 | 28 | 210 | 0 | 596 | 806 | 694 | 112 |  |  | #VALUE! | 210 | #VALUE! | #VALUE!
| 2 | 1141 | 13631 | 8117 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 2 |  | 2 |  |  | 12.5 | m3 | OFF HIRED | 2022-10-06 | 2022-10-18 | 100% |  | 1.8571 | 7.5 | 0.7 | 93.75 | 8.75 | 65.625 | 28.125 | 16.25 | 110 | 110 | 0
| 2 | 1141 | 13631 | 8117 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 2 |  | 2 |  |  | 12.5 | m3 | OFF HIRED | 2022-10-06 | 2022-10-18 | 100% |  | 1.8571 | 7.5 | 0.7 | 93.75 | 8.75 | 65.625 | 28.125 | 16.25 | 110 | 110 | 0
| 2 | 1141 | 13631 | 8117 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 2 |  | 2 |  |  | 12.5 | m3 | OFF HIRED | 2022-10-06 | 2022-10-18 | 100% |  | 1.8571 | 7.5 | 0.7 | 93.75 | 8.75 | 65.625 | 28.125 | 16.25 | 110 | 110 | 0
| 2 | 1141 | 13631 | 8117 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 2 |  | 2 |  |  | 12.5 | m3 | OFF HIRED | 2022-10-06 | 2022-10-18 | 100% |  | 1.8571 | 7.5 | 0.7 | 93.75 | 8.75 | 65.625 | 28.125 | 16.25 | 110 | 110 | 0
| 2 | 1141 | 13631 | 8117 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 2 |  | 2 |  |  | 12.5 | m3 | OFF HIRED | 2022-10-06 | 2022-10-18 | 100% |  | 1.8571 | 7.5 | 0.7 | 93.75 | 8.75 | 65.625 | 28.125 | 16.25 | 110 | 110 | 0
| 2 | 1153 | 13638 | 8089 |  | Ground Floor Residence | Birdcage Scaffold |  | Birdcage | 4.5 | 2.6 | 4 |  | 4 |  |  | 46.8 | m3 | OFF HIRED | 2022-10-07 | 2022-10-10 | 100% |  | 0.57143 | 7.5 | 0.7 | 351 | 32.76 | 245.7 | 105.3 | 18.72 | 369.72 | 369.72 | 0
| 2 | 1074 | 13510 | 8061 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 4 |  | 4 |  |  | 25 | m3 | OFF HIRED | 2022-09-28 | 2022-10-03 | 100% |  | 0.85714 | 7.5 | 0.7 | 187.5 | 17.5 | 131.25 | 56.25 | 15 | 202.5 | 202.5 | 0
| 2 | 1074 | 13510 | 8061 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 4 |  | 4 |  |  | 25 | m3 | OFF HIRED | 2022-09-28 | 2022-10-03 | 100% |  | 0.85714 | 7.5 | 0.7 | 187.5 | 17.5 | 131.25 | 56.25 | 15 | 202.5 | 202.5 | 0
| 2 | 1074 | 13510 | 8061 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 4 |  | 4 |  |  | 25 | m3 | OFF HIRED | 2022-09-28 | 2022-10-03 | 100% |  | 0.85714 | 7.5 | 0.7 | 187.5 | 17.5 | 131.25 | 56.25 | 15 | 202.5 | 202.5 | 0
| 2 | 1074 | 13510 | 8061 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 4 |  | 4 |  |  | 25 | m3 | OFF HIRED | 2022-09-28 | 2022-10-03 | 100% |  | 0.85714 | 7.5 | 0.7 | 187.5 | 17.5 | 131.25 | 56.25 | 15 | 202.5 | 202.5 | 0
| 2 | 1074 | 13510 | 8061 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 4 |  | 4 |  |  | 25 | m3 | OFF HIRED | 2022-09-28 | 2022-10-03 | 100% |  | 0.85714 | 7.5 | 0.7 | 187.5 | 17.5 | 131.25 | 56.25 | 15 | 202.5 | 202.5 | 0
| 2 | 1070 | 13506 |  |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 6.5 | 3 | 4 |  | 4 |  |  | 78 | m3 | ON HIRE | 2022-09-27 |  | 100% |  | 22.1429 | 7.5 | 0.7 | 585 | 54.6 | 409.5 | 0 | 1209 | 1618.5 | 1400.1 | 218.4 |  |  | #VALUE! | 409.5 | #VALUE! | #VALUE!
| 2 | 1081 | 13514 | 8061 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 4 |  | 4 |  |  | 25 | m3 | OFF HIRED | 2022-09-29 | 2022-10-03 | 100% |  | 0.71429 | 7.5 | 0.7 | 187.5 | 17.5 | 131.25 | 56.25 | 12.5 | 200 | 200 | 0
| 2 | 1081 | 13514 | 8061 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 4 |  | 4 |  |  | 25 | m3 | OFF HIRED | 2022-09-29 | 2022-10-03 | 100% |  | 0.71429 | 7.5 | 0.7 | 187.5 | 17.5 | 131.25 | 56.25 | 12.5 | 200 | 200 | 0
| 2 | 1081 | 13514 | 8061 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 4 |  | 4 |  |  | 25 | m3 | OFF HIRED | 2022-09-29 | 2022-10-03 | 100% |  | 0.71429 | 7.5 | 0.7 | 187.5 | 17.5 | 131.25 | 56.25 | 12.5 | 200 | 200 | 0
| 2 | 1081 | 13514 | 8061 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 4 |  | 4 |  |  | 25 | m3 | OFF HIRED | 2022-09-29 | 2022-10-03 | 100% |  | 0.71429 | 7.5 | 0.7 | 187.5 | 17.5 | 131.25 | 56.25 | 12.5 | 200 | 200 | 0
| 2 | 1089 | 13522 | 8097 |  | Ground Floor Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 2 |  | 2 |  |  | 12.5 | m3 | OFF HIRED | 2022-09-30 | 2022-10-12 | 100% |  | 1.8571 | 7.5 | 0.7 | 93.75 | 8.75 | 65.625 | 28.125 | 16.25 | 110 | 110 | 0
| 2 | 1089 | 13522 | 8097 |  | Ground Floor Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 2 |  | 2 |  |  | 12.5 | m3 | OFF HIRED | 2022-09-30 | 2022-10-12 | 100% |  | 1.8571 | 7.5 | 0.7 | 93.75 | 8.75 | 65.625 | 28.125 | 16.25 | 110 | 110 | 0
| 2 | 1089 | 13522 | 8097 |  | Ground Floor Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 2 |  | 2 |  |  | 12.5 | m3 | OFF HIRED | 2022-09-30 | 2022-10-12 | 100% |  | 1.8571 | 7.5 | 0.7 | 93.75 | 8.75 | 65.625 | 28.125 | 16.25 | 110 | 110 | 0
| 2 | 1089 | 13522 | 8097 |  | Ground Floor Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 2 |  | 2 |  |  | 12.5 | m3 | OFF HIRED | 2022-09-30 | 2022-10-12 | 100% |  | 1.8571 | 7.5 | 0.7 | 93.75 | 8.75 | 65.625 | 28.125 | 16.25 | 110 | 110 | 0
| 2 | 1089 | 13522 | 8097 |  | Ground Floor Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 2 |  | 2 |  |  | 12.5 | m3 | OFF HIRED | 2022-09-30 | 2022-10-12 | 100% |  | 1.8571 | 7.5 | 0.7 | 93.75 | 8.75 | 65.625 | 28.125 | 16.25 | 110 | 110 | 0
| 2 | 1100 | 13533 | 8229 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 4 |  | 4 |  |  | 25 | m3 | OFF HIRED | 2022-10-01 | 2022-11-04 | 100% |  | 5 | 7.5 | 0.7 | 187.5 | 17.5 | 131.25 | 56.25 | 87.5 | 275 | 275 | 0
| 2 | 1133 | 13617 | 8117 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 4 |  | 4 |  |  | 25 | m3 | OFF HIRED | 2022-10-04 | 2022-10-18 | 100% |  | 2.1429 | 7.5 | 0.7 | 187.5 | 17.5 | 131.25 | 56.25 | 37.5 | 225 | 225 | 0
| 2 | 1129 | 13613 | 8117 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 2 |  | 2 |  |  | 12.5 | m3 | OFF HIRED | 2022-10-04 | 2022-10-18 | 100% |  | 2.1429 | 7.5 | 0.7 | 93.75 | 8.75 | 65.625 | 28.125 | 18.75 | 112.5 | 112.5 | 0
| 2 | 1129 | 13613 | 8117 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 2 |  | 2 |  |  | 12.5 | m3 | OFF HIRED | 2022-10-04 | 2022-10-18 | 100% |  | 2.1429 | 7.5 | 0.7 | 93.75 | 8.75 | 65.625 | 28.125 | 18.75 | 112.5 | 112.5 | 0
| 2 | 1228 | 13766 | 8120 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 4 |  | 4 |  |  | 25 | m3 | OFF HIRED | 2022-10-16 | 2022-10-18 | 100% |  | 0.42857 | 7.5 | 0.7 | 187.5 | 17.5 | 131.25 | 56.25 | 7.5 | 195 | 195 | 0
| 2 | 1167 | 13652 | 8163 |  | Ground Floor Hotel | Boarded Lift |  | Board Lift | 11 | 1.3 |  |  |  | 1 |  | 14.3 | m2-LxW | OFF HIRED | 2022-10-10 | 2022-10-28 | 100% |  | 2.7143 | 7.5 | 1.05 | 107.25 | 15.015 | 75.075 | 32.175 | 40.755 | 148.005 | 148.005 | 0
| 2 | 1168 | 13653 | 8163 |  | Ground Floor Hotel | Boarded Lift |  | Board Lift | 7 | 1.3 |  |  |  | 1 |  | 9.1 | m2-LxW | OFF HIRED | 2022-10-10 | 2022-10-28 | 100% |  | 2.7143 | 7.5 | 1.05 | 68.25 | 9.555 | 47.775 | 20.475 | 25.935 | 94.185 | 94.185 | 0
| 2 | 1324 | 13812 | 8205 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 2 | 0.6 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-10-31 | 2022-11-07 | 100% |  | 1.1429 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 28 | 298 | 298 | 0
| 2 | 1339 | 13827 | 8211 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 0.6 | 5 |  | 5 |  |  | 5 | rm | OFF HIRED | 2022-11-01 | 2022-11-09 | 100% |  | 1.2857 | 135 | 12.25 | 675 | 61.25 | 472.5 | 202.5 | 78.75 | 753.75 | 753.75 | 0
| 2 | 1349 | 13837 | 8602 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 1.5 |  | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2022-11-02 | 2023-01-23 | 100% |  | 11.8571 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 60.75 | 217.875 | 420.375 | 420.375 | 0
| 2 | 1276 | 13715 | 8223 |  | Ground Floor Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-10-28 | 2022-11-11 | 100% |  | 2.1429 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 65.625 | 403.125 | 403.125 | 0
| 2 | 1421 | 13909 | 8236 |  | Ground Floor Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 3.5 |  | 3.5 |  |  | 3.5 | rm | OFF HIRED | 2022-11-12 | 2022-11-15 | 100% |  | 0.57143 | 135 | 12.25 | 472.5 | 42.875 | 330.75 | 141.75 | 24.5 | 497 | 497 | 0
| 2 | 1375 | 13863 | 8224 |  | Ground Floor Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-11-05 | 2022-11-11 | 100% |  | 1 | 135 | 12.25 | 540 | 49 | 378 | 162 | 49 | 589 | 589 | 0
| 2 | 1442 | 13930 | 8439 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 0.6 | 6 |  | 6 |  |  | 6 | rm | OFF HIRED | 2022-11-15 | 2023-01-18 | 100% |  | 9.2857 | 135 | 12.25 | 810 | 73.5 | 567 | 243 | 682.5 | 1492.5 | 1492.5 | 0
| 2 | 1442 | 13930 | 8439 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 0.6 | 6 |  | 6 |  |  | 6 | rm | OFF HIRED | 2022-11-15 | 2023-01-18 | 100% |  | 9.2857 | 135 | 12.25 | 810 | 73.5 | 567 | 243 | 682.5 | 1492.5 | 1492.5 | 0
| 2 | 1442 | 13930 | 8439 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 0.6 | 6 |  | 6 |  |  | 6 | rm | OFF HIRED | 2022-11-15 | 2023-01-18 | 100% |  | 9.2857 | 135 | 12.25 | 810 | 73.5 | 567 | 243 | 682.5 | 1492.5 | 1492.5 | 0
| 2 | 1477 | 13965 | 8295 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-11-22 | 2022-11-30 | 100% |  | 1.2857 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 47.25 | 452.25 | 452.25 | 0
| 2 | 1485 | 13973 | 8438 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 1.6 | 1 | 6 |  | 6 |  |  | 6 | rm | OFF HIRED | 2022-11-24 | 2023-01-18 | 100% |  | 8 | 135 | 12.25 | 810 | 73.5 | 567 | 243 | 588 | 1398 | 1398 | 0
| 2 | 1486 | 13973 | 8438 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 0.6 | 6 |  | 6 |  |  | 6 | rm | OFF HIRED | 2022-11-24 | 2023-01-18 | 100% |  | 8 | 135 | 12.25 | 810 | 73.5 | 567 | 243 | 588 | 1398 | 1398 | 0
| 2 | 1331 | 13819 | 8245 |  | Ground Floor To Basement Hotel | Access Scaffold |  | INDEPENDENT | 56 | 1.3 | 2 |  | 2 |  |  | 112 | m2-LxH | OFF HIRED | 2022-10-31 | 2022-11-16 | 100% |  | 2.4286 | 14 | 0.84 | 1568 | 94.08 | 1097.6 | 470.4 | 228.48 | 1796.48 | 1796.48 | 0
| 2 | 1343 | 13831 | 8236 |  | Ground floor To Level 3 Residence | Access Scaffold |  | INDEPENDENT | 35 | 1 | 1.5 |  | 1.5 |  |  | 52.5 | m2-LxH | OFF HIRED | 2022-11-01 | 2022-11-15 | 100% |  | 2.1429 | 14 | 0.84 | 735 | 44.1 | 514.5 | 220.5 | 94.5 | 829.5 | 829.5 | 0
| 2 | 1348 | 13836 | 8329 |  | Ground Floor To Level 2 Residence | Access Scaffold |  | INDEPENDENT | 24 | 1 | 2 |  | 2 |  |  | 48 | m2-LxH | OFF HIRED | 2022-11-02 | 2022-12-14 | 100% |  | 6.1429 | 14 | 0.84 | 672 | 40.32 | 470.4 | 201.6 | 247.68 | 919.68 | 919.68 | 0
| 2 | 1378 | 13866 | 8207 |  | Ground Floor To Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 26 | 1.3 | 1.5 |  | 1.5 |  |  | 39 | m2-LxH | OFF HIRED | 2022-11-06 | 2022-11-07 | 100% |  | 0.28571 | 14 | 0.84 | 546 | 32.76 | 382.2 | 163.8 | 9.36 | 555.36 | 555.36 | 0
| 2 | 1299 | 13738 | 8153 |  | Ground Floor Hotel | Access Scaffold |  | INDEPENDENT | 25 | 1.3 | 6 |  | 6 |  |  | 150 | m2-LxH | OFF HIRED | 2022-10-27 | 2022-10-27 | 100% |  | 0.14286 | 14 | 0.84 | 2100 | 126 | 1470 | 630 | 18 | 2118 | 2118 | 0
| 2 | 1319 | 13807 | 8226 |  | Ground Floor Hotel | Access Scaffold |  | INDEPENDENT | 15 | 1.3 | 6 |  | 6 |  |  | 90 | m2-LxH | OFF HIRED | 2022-10-29 | 2022-11-12 | 100% |  | 2.1429 | 14 | 0.84 | 1260 | 75.6 | 882 | 378 | 162 | 1422 | 1422 | 0
| 2 | 1217 | 13805 | 8221 |  | Ground Floor To Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 17.5 | 1.3 | 1.5 |  | 1.5 |  |  | 26.25 | m2-LxH | OFF HIRED | 2022-10-29 | 2022-11-10 | 100% |  | 1.8571 | 14 | 0.84 | 367.5 | 22.05 | 257.25 | 110.25 | 40.95 | 408.45 | 408.45 | 0
| 2 | 1314 | 13802 | 8174 |  | Ground Floor To Basement 1 Residence | Access Scaffold |  | INDEPENDENT | 75 | 1.3 | 2 |  | 2 |  |  | 150 | m2-LxH | OFF HIRED | 2022-10-29 | 2022-10-30 | 100% |  | 0.28571 | 14 | 0.84 | 2100 | 126 | 1470 | 630 | 36 | 2136 | 2136 | 0
| 2 | 1422 | 13910 | 8238 |  | Ground Floor Residence | Access Scaffold |  | INDEPENDENT | 5 | 0.6 | 1.5 |  | 1.5 |  |  | 7.5 | m2-LxH | OFF HIRED | 2022-11-12 | 2022-11-15 | 100% |  | 0.57143 | 14 | 0.84 | 105 | 6.3 | 73.5 | 31.5 | 3.6 | 108.6 | 108.6 | 0
| 2 | 1389 | 13877 | 8639 |  | Ground Floor Residence | Access Scaffold |  | INDEPENDENT | 5 | 1 | 1.5 |  | 1.5 |  |  | 7.5 | m2-LxH | OFF HIRED | 2022-11-08 | 2023-02-07 | 100% |  | 13.1429 | 14 | 0.84 | 105 | 6.3 | 73.5 | 31.5 | 82.8 | 187.8 | 150 | 37.8 |  |  | #VALUE! | 73.5 | #VALUE! | #VALUE!
| 2 | 1387 | 13875 | 8328 |  | Ground floor To Level 7 Hotel | Access Scaffold |  | INDEPENDENT | 78 | 1 | 2 |  | 2 |  |  | 156 | m2-LxH | OFF HIRED | 2022-11-08 | 2022-12-13 | 100% |  | 5.1429 | 14 | 0.84 | 2184 | 131.04 | 1528.8 | 655.2 | 673.92 | 2857.92 | 2857.92 | 0
| 2 | 1403 | 13891 | 8622 |  | Ground Floor Hotel | Access Scaffold |  | INDEPENDENT | 3.9 | 1.3 | 4 |  | 4 |  |  | 15.6 | m2-LxH | OFF HIRED | 2022-11-10 | 2023-02-01 | 100% |  | 12 | 14 | 0.84 | 218.4 | 13.104 | 152.88 | 65.52 | 157.248 | 375.648 | 308.256 | 67.392 |  |  | #VALUE! | 152.88 | #VALUE! | #VALUE!
| 2 | 1459 | 13947 | 8295 |  | Ground Floor Hotel | Access Scaffold |  | INDEPENDENT | 17 | 1.3 | 6 |  | 6 |  |  | 102 | m2-LxH | OFF HIRED | 2022-11-18 | 2022-11-30 | 100% |  | 1.8571 | 14 |  | 1428 | 0 | 999.6 | 428.4 | 0 | 1428 | 1428 | 0
| 2 | 1458 | 13946 | 8629 |  | Ground Floor Hotel | Access Scaffold |  | INDEPENDENT | 15 | 1.3 | 6 |  | 6 |  |  | 90 | m2-LxH | OFF HIRED | 2022-11-18 | 2023-02-02 | 100% |  | 11 | 14 | 0.84 | 1260 | 75.6 | 882 | 378 | 831.6 | 2091.6 | 1692 | 399.6 |  |  | #VALUE! | 882 | #VALUE! | #VALUE!
| 2 | 1453 | 13941 | 8324 |  | Ground Floor Hotel | Access Scaffold |  | INDEPENDENT | 3.5 | 1.3 | 4 |  | 4 |  |  | 14 | m2-LxH | OFF HIRED | 2022-11-17 | 2022-12-13 | 100% |  | 3.8571 | 14 | 0.84 | 196 | 11.76 | 137.2 | 58.8 | 45.36 | 241.36 | 241.36 | 0
| 2 | 1284 | 13872 |  |  | Ground Floor Hotel | Access Scaffold |  | INDEPENDENT | 3.5 | 0.6 | 1.5 |  | 1.5 |  |  | 5.25 | m2-LxH | ON HIRE | 2022-11-08 |  | 100% |  | 16.1429 | 14 | 0.84 | 73.5 | 4.41 | 51.45 | 0 | 71.19 | 122.64 | 105 | 17.64 |  |  | #VALUE! | 51.45 | #VALUE! | #VALUE!
| 2 | 1447 | 13935 | 8310 |  | Ground Floor Hotel | Access Scaffold |  | INDEPENDENT | 35 | 1.3 | 2.5 |  | 2.5 |  |  | 87.5 | m2-LxH | OFF HIRED | 2022-11-17 | 2022-12-07 | 100% |  | 3 | 14 | 0.84 | 1225 | 73.5 | 857.5 | 367.5 | 220.5 | 1445.5 | 1445.5 | 0
| 2 | 1441 | 13929 | 8272 |  | GroundFloor Hotel | Access Scaffold |  | INDEPENDENT | 9.3 | 1.3 | 6 |  | 6 |  |  | 55.8 | m2-LxH | OFF HIRED | 2022-11-15 | 2022-11-24 | 100% |  | 1.4286 | 14 | 0.84 | 781.2 | 46.872 | 546.84 | 234.36 | 66.96 | 848.16 | 848.16 | 0
| 2 | 1437 | 13925 | 8436 |  | Ground Floor Hotel | Access Scaffold |  | INDEPENDENT | 7.5 | 0.6 | 6 |  | 6 |  |  | 45 | m2-LxH | OFF HIRED | 2022-11-15 | 2023-01-17 | 100% |  | 9.1429 | 14 | 0.84 | 630 | 37.8 | 441 | 189 | 345.6 | 975.6 | 975.6 | 0
| 2 | 1471 | 13959 | 8440 |  | Ground Floor Hotel | Access Scaffold |  | INDEPENDENT | 6 | 1 | 2 |  | 2 |  |  | 12 | m2-LxH | OFF HIRED | 2022-11-20 | 2023-01-18 | 100% |  | 8.5714 | 14 | 0.84 | 168 | 10.08 | 117.6 | 50.4 | 86.4 | 254.4 | 254.4 | 0
| 2 | 1472 | 13960 |  |  | Ground Floor Hotel | Access Scaffold |  | INDEPENDENT | 3.9 | 1.3 | 2 |  | 2 |  |  | 7.8 | m2-LxH | ON HIRE | 2022-11-20 |  | 100% |  | 14.4286 | 14 | 0.84 | 109.2 | 6.552 | 76.44 | 0 | 94.536 | 170.976 | 144.768 | 26.208 |  |  | #VALUE! | 76.44 | #VALUE! | #VALUE!
| 2 | 1335 | 13823 | 8603 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 2.5 | 1.8 | 6 |  | 6 |  |  | 15 | m2-LxH | OFF HIRED | 2022-11-01 | 2023-01-23 | 100% |  | 12 | 18 |  | 270 | 0 | 189 | 81 | 0 | 270 | 270 | 0
| 2 | 1337 | 13825 | 8219 |  | Ground Floor Residence | Access Scaffold |  | Independent | 2.5 | 1.8 | 2.5 |  | 2.5 |  |  | 6.25 | m2-LxH | OFF HIRED | 2022-11-01 | 2022-11-10 | 100% |  | 1.4286 | 18 | 1.05 | 112.5 | 6.5625 | 78.75 | 33.75 | 9.375 | 121.875 | 121.875 | 0
| 2 | 1360 | 13848 | 8412 |  | Ground Floor Residence | Access Scaffold |  | Independent | 6 | 1.8 | 2 |  | 2 |  |  | 12 | m2-LxH | OFF HIRED | 2022-11-03 | 2023-01-11 | 100% |  | 10 | 18 | 1.05 | 216 | 12.6 | 151.2 | 64.8 | 126 | 342 | 342 | 0
| 2 | 1358 | 13846 | 8215 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 22.5 | 3.5 | 3 |  | 3 |  |  | 236.25 | m3 | OFF HIRED | 2022-11-03 | 2022-11-09 | 100% |  | 1 | 7.5 | 0.7 | 1771.875 | 165.375 | 1240.3125 | 531.5625 | 165.375 | 1937.25 | 1937.25 | 0
| 2 | 1427 | 13915 | 8472 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 3.5 | 2.5 | 2 |  | 2 |  |  | 17.5 | m3 | OFF HIRED | 2022-11-12 | 2022-12-27 | 100% |  | 6.5714 | 7.5 | 0.7 | 131.25 | 12.25 | 91.875 | 39.375 | 80.5 | 211.75 | 211.75 | 0
| 2 | 1380 | 13868 | 8244 |  | Ground Floor Residence | Birdcage Scaffold |  | Birdcage | 1.8 | 2.5 | 3.5 |  | 3.5 |  |  | 15.75 | m3 | OFF HIRED | 2022-11-06 | 2022-11-16 | 100% |  | 1.5714 | 7.5 | 0.7 | 118.125 | 11.025 | 82.6875 | 35.4375 | 17.325 | 135.45 | 135.45 | 0
| 2 | 1392 | 13880 | 8328 |  | Ground Floor Residence | Birdcage Scaffold |  | Birdcage | 6 | 2.5 | 3.5 |  | 3.5 |  |  | 52.5 | m3 | OFF HIRED | 2022-11-08 | 2022-12-13 | 100% |  | 5.1429 | 7.5 | 0.7 | 393.75 | 36.75 | 275.625 | 118.125 | 0 | 393.75 | 393.75 | 0
| 2 | 1396 | 13884 | 8459 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 4.5 |  | 4.5 |  |  | 28.125 | m3 | OFF HIRED | 2022-11-08 | 2022-12-23 | 100% |  | 6.5714 | 7.5 |  | 210.9375 | 0 | 147.6562 | 63.2812 | 0 | 210.9375 | 210.9375 | 0
| 2 | 1396 | 13884 | 8459 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 8 | 5 | 1 |  | 1 |  |  | 40 | m3 | OFF HIRED | 2022-11-08 | 2022-12-23 | 100% |  | 6.5714 | 7.5 |  | 300 | 0 | 210 | 90 | 0 | 300 | 300 | 0
| 2 | 1399 | 13887 | 8603 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 2.5 |  | 2.5 |  |  | 25 | m3 | OFF HIRED | 2022-11-09 | 2023-01-23 | 100% |  | 10.8571 | 7.5 |  | 187.5 | 0 | 131.25 | 56.25 | 0 | 187.5 | 187.5 | 0
| 2 | 1399 | 13887 | 8603 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 2.5 |  | 2.5 |  |  | 15.625 | m3 | OFF HIRED | 2022-11-09 | 2023-01-23 | 100% |  | 10.8571 | 7.5 |  | 117.1875 | 0 | 82.0312 | 35.1562 | 0 | 117.1875 | 117.1875 | 0
| 2 | 1409 | 13897 | 8461 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 10.5 | 2.5 | 0.5 |  | 0.5 |  |  | 13.125 | m3 | OFF HIRED | 2022-11-10 | 2022-12-24 | 100% |  | 6.4286 | 7.5 | 0.7 | 98.4375 | 9.1875 | 68.9062 | 29.5312 | 59.0625 | 157.5 | 157.5 | 0
| 2 | 1335 | 13823 | 8603 |  | Ground Floor Hotel | Cantiliver |  | Cantiliver | 6 | 0.9 |  |  |  | 1 |  | 5.4 | m2-LxW | OFF HIRED | 2022-11-01 | 2023-01-23 | 100% |  | 12 | 36.5 | 3.15 | 197.1 | 17.01 | 137.97 | 59.13 | 0 | 197.1 | 197.1 | 0
| 2 | 1459 | 13947 | 8295 |  | Ground Floor Hotel | Cantiliver |  | Cantiliver | 8 | 0.6 |  |  |  | 1 |  | 4.8 | m2-LxW | OFF HIRED | 2022-11-18 | 2022-11-30 | 100% |  | 1.8571 | 36.5 | 3.15 | 175.2 | 15.12 | 122.64 | 52.56 | 0 | 175.2 | 175.2 | 0
| 2 | 1610 | 14145 | 8346 |  | Ground Floor Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 6.5 |  | 6.5 |  |  | 6.5 | rm | OFF HIRED | 2022-12-16 | 2022-12-20 | 100% |  | 0.71429 | 135 | 12.25 | 877.5 | 79.625 | 614.25 | 263.25 | 56.875 | 934.375 | 934.375 | 0
| 2 | 1497 | 13984 | 8439 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 0.6 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-11-26 | 2023-01-18 | 100% |  | 7.7143 | 135 | 12.25 | 540 | 49 | 378 | 162 | 378 | 918 | 918 | 0
| 2 | 1518 | 14056 | 8440 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 0.6 | 6 |  | 6 |  |  | 6 | rm | OFF HIRED | 2022-11-30 | 2023-01-18 | 100% |  | 7.1429 | 135 | 12.25 | 810 | 73.5 | 567 | 243 | 525 | 1335 | 1335 | 0
| 2 | 1594 | 14129 | 8335 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.8 | 3.5 |  | 3.5 |  |  | 3.5 | rm | OFF HIRED | 2022-12-14 | 2022-12-15 | 100% |  | 0.28571 | 135 | 12.25 | 472.5 | 42.875 | 330.75 | 141.75 | 12.25 | 484.75 | 484.75 | 0
| 2 | 1587 | 14119 | 8329 |  | Ground Floor Residence | HEAVY DUTY TOWER |  | Tower | 2.6 | 1 | 1 |  | 1 |  |  | 1 | rm | OFF HIRED | 2022-12-13 | 2022-12-14 | 100% |  | 0.28571 | 135 | 12.25 | 135 | 12.25 | 94.5 | 40.5 | 3.5 | 138.5 | 138.5 | 0
| 2 | 1664 | 14199 | 8463 |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-12-24 | 2022-12-24 | 100% |  | 0.14286 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 3.5 | 273.5 | 273.5 | 0
| 2 | 1633 | 14170 | 8445 |  | Ground Floor Residence | Access Scaffold |  | INDEPENDENT | 2.5 | 1.3 | 7 |  | 7 |  |  | 17.5 | m2-LxH | OFF HIRED | 2022-12-20 | 2023-01-20 | 100% |  | 4.5714 | 14 | 0.84 | 245 | 14.7 | 171.5 | 73.5 | 67.2 | 312.2 | 312.2 | 0
| 2 | 1633 | 14170 | 8445 |  | Ground Floor Residence | Access Scaffold |  | INDEPENDENT | 1 | 1.3 | 7 |  | 7 |  |  | 7 | m2-LxH | OFF HIRED | 2022-12-20 | 2023-01-20 | 100% |  | 4.5714 | 14 | 0.84 | 98 | 5.88 | 68.6 | 29.4 | 26.88 | 124.88 | 124.88 | 0
| 2 | 1554 | 14086 | 8326 |  | Ground Floor Residence | Access Scaffold |  | INDEPENDENT | 14 | 0.6 | 2 |  | 2 |  |  | 28 | m2-LxH | OFF HIRED | 2022-12-08 | 2022-12-13 | 100% |  | 0.85714 | 14 | 0.84 | 392 | 23.52 | 274.4 | 117.6 | 20.16 | 412.16 | 412.16 | 0
| 2 | 1564 | 14098 | 8463 |  | Ground Floor Hotel | Access Scaffold |  | INDEPENDENT | 7.5 | 1 | 1 |  | 1 |  |  | 7.5 | m2-LxH | OFF HIRED | 2022-12-10 | 2022-12-24 | 100% |  | 2.1429 | 14 | 0.84 | 105 | 6.3 | 73.5 | 31.5 | 13.5 | 118.5 | 118.5 | 0
| 2 | 1598 | 14133 | 8342 |  | Ground floor To Basement 1 Hotel | Access Scaffold |  | INDEPENDENT | 21 | 0.6 | 2 |  | 2 |  |  | 42 | m2-LxH | OFF HIRED | 2022-12-15 | 2022-12-19 | 100% |  | 0.71429 | 14 | 0.84 | 588 | 35.28 | 411.6 | 176.4 | 25.2 | 613.2 | 613.2 | 0
| 2 | 1658 | 14193 | 8599 |  | Ground Floor Hotel | Access Scaffold |  | INDEPENDENT | 6 | 1.3 | 1.3 |  | 1.3 |  |  | 7.8 | m2-LxH | OFF HIRED | 2022-12-23 | 2023-02-24 | 100% |  | 9.1429 | 14 | 0.84 | 109.2 | 6.552 | 76.44 | 32.76 | 59.904 | 169.104 | 113.88 | 55.224 |  |  | #VALUE! | 76.44 | #VALUE! | #VALUE!
| 2 | 1670 | 14255 |  |  | Ground Floor Hotel | Access Scaffold |  | INDEPENDENT | 9.9 | 1 | 4 |  | 4 |  |  | 39.6 | m2-LxH | ON HIRE | 2022-12-27 |  | 100% |  | 9.1429 | 14 | 0.84 | 554.4 | 33.264 | 388.08 | 0 | 304.128 | 692.208 | 559.152 | 133.056 |  |  | #VALUE! | 458.64 | #VALUE! | #VALUE!
| 2 | 1670 | 14255 |  |  | Ground Floor Hotel | Access Scaffold |  | INDEPENDENT | 1.8 | 1 | 4 |  | 4 |  |  | 7.2 | m2-LxH | ON HIRE | 2022-12-27 |  | 100% |  | 9.1429 | 14 | 0.84 | 100.8 | 6.048 | 70.56 | 0 | 55.296 | 125.856 | 101.664 | 24.192 |  |  | #VALUE! | 458.64 | #VALUE! | #VALUE!
| 2 | 1607 | 14142 | 8576 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 8 | 3.5 | 3.5 |  | 3.5 |  |  | 98 | m3 | OFF HIRED | 2022-12-16 | 2023-02-19 | 100% |  | 9.4286 | 7.5 | 0.7 | 735 | 68.6 | 514.5 | 220.5 | 646.8 | 1381.8 | 975.1 | 406.7 |  |  | #VALUE! | 514.5 | #VALUE! | #VALUE!
| 2 | 1584 | 14116 | 8576 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 9 | 3.5 | 3.5 |  | 3.5 |  |  | 110.25 | m3 | OFF HIRED | 2022-12-12 | 2023-02-19 | 100% |  | 10 | 7.5 | 0.7 | 826.875 | 77.175 | 578.8125 | 248.0625 | 771.75 | 1598.625 | 1141.0875 | 457.5375 |  |  | #VALUE! | 578.8125 | #VALUE! | #VALUE!
| 2 | 1664 | 14199 | 8463 |  | Ground Floor Hotel | Cantiliver |  | Cantiliver | 2.5 | 0.6 |  |  |  | 0.6 |  | 0.9 | m2-LxW | OFF HIRED | 2022-12-24 | 2022-12-24 | 100% |  | 0.14286 | 36.5 | 3.15 | 32.85 | 2.835 | 22.995 | 9.855 | 0.405 | 33.255 | 33.255 | 0
| 2 | 1528 | 14066 | 8462 |  | Ground Floor Hotel | Chain Pully With Ladder Beam |  | Independent | 3 | 20 |  |  |  | 1 |  | 60 | m2-LxW | OFF HIRED | 2022-12-06 | 2022-12-24 | 100% |  | 2.7143 | 81 | 1.82 | 4860 | 109.2 | 3402 | 1458 | 296.4 | 5156.4 | 5156.4 | 0
| 2 | 1589 A` | 14122 |  |  | Ground Floor Residence | Chain Pully With Ladder Beam |  | Independent | 4 | 4 |  |  |  | 1 |  | 16 | m2-LxW | ON HIRE | 2022-12-14 |  | 100% |  | 11 | 81 | 1.82 | 1296 | 29.12 | 907.2 | 0 | 320.32 | 1227.52 | 1111.04 | 116.48 |  |  | #VALUE! | 907.2 | #VALUE! | #VALUE!
| 2 | 1590 A` | 14123 | 8414 |  | Ground Floor Residence | Chain Pully With Ladder Beam |  | Independent | 4 | 2 |  |  |  | 1 |  | 8 | m2-LxW | OFF HIRED | 2022-12-14 | 2023-01-11 | 100% |  | 4.1429 | 81 | 1.82 | 648 | 14.56 | 453.6 | 194.4 | 60.32 | 708.32 | 708.32 | 0
| 2 | 1589 | 14121 |  |  | Ground Floor To Level 5 Residence | Chain Pully |  | Independent | 7.5 | 1 | 16 |  | 16 |  |  | 120 | m2-LxH | ON HIRE | 2022-12-14 |  | 100% |  | 11 | 14 | 0.84 | 1680 | 100.8 | 1176 | 0 | 1108.8 | 2284.8 | 1881.6 | 403.2 |  |  | #VALUE! | 3449.9062 | #VALUE! | #VALUE!
| 2 | 1589 | 14121 |  |  | Ground Floor To Level 5 Residence | Chain Pully |  | Buttress | 7.5 | 2.5 | 16 |  | 16 |  |  | 300 | m3 | ON HIRE | 2022-12-14 |  | 100% |  | 11 | 5.25 | 0.35 | 1575 | 105 | 1102.5 | 0 | 1155 | 2257.5 | 1837.5 | 420 |  |  | #VALUE! | 3449.9062 | #VALUE! | #VALUE!
| 2 | 1589 | 14121 |  |  | Ground Floor To Level 5 Residence | Chain Pully |  | Buttress | 7.5 | 2.5 | 17 |  | 17 |  |  | 318.75 | m3 | ON HIRE | 2022-12-14 |  | 100% |  | 11 | 5.25 | 0.35 | 1673.4375 | 111.5625 | 1171.4062 | 0 | 1227.1875 | 2398.5938 | 1952.3438 | 446.25 |  |  | #VALUE! | 3449.9062 | #VALUE! | #VALUE!
| 3 | 167 | 12163 | 7723 |  | Level 2 Hotel | Access Scaffold |  | INDEPENDENT | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 3.6 | m2-LxH | OFF HIRED | 2022-06-07 | 2022-07-17 | 100% |  | 5.8571 | 14 |  | 50.4 | 0 | 35.28 | 15.12 | 0 | 50.4 | 50.4 | 0
| 3 | 172 | 12169 | 7709 |  | Level 2 Hotel | Access Scaffold |  | 2.5 | 2.5 | 1 | 3 | 1 | 2 |  |  | 5 | m2-LxH | OFF HIRED | 2022-06-08 | 2022-07-13 | 100% |  | 5.1429 | 14 |  | 70 | 0 | 49 | 21 | 0 | 70 | 70 | 0
| 3 | 157 | 12154 | 7565 |  | Level 2 Hotel | Access Scaffold |  | INDEPENDENT | 1.8 | 1.3 | 4 | 1 | 3 |  |  | 5.4 | m2-LxH | OFF HIRED | 2022-06-06 | 2022-06-16 | 100% |  | 1.5714 | 14 | 0.84 | 75.6 | 4.536 | 52.92 | 22.68 | 7.128 | 82.728 | 82.728 | 0
| 3 | 151 | 12248 | 7564 |  | Level 2 Hotel | Access Scaffold |  | INDEPENDENT | 1.8 | 1.3 | 4 | 1 | 3 |  |  | 5.4 | m2-LxH | OFF HIRED | 2022-06-06 | 2022-06-17 | 100% |  | 1.7143 | 14 | 0.84 | 75.6 | 4.536 | 52.92 | 22.68 | 7.776 | 83.376 | 83.376 | 0
| 3 | 152 | 12248 | 7564 |  | Level 2 Hotel | Access Scaffold |  | INDEPENDENT | 1.8 | 1.3 | 4 | 1 | 3 |  |  | 5.4 | m2-LxH | OFF HIRED | 2022-06-06 | 2022-06-17 | 100% |  | 1.7143 | 14 | 0.84 | 75.6 | 4.536 | 52.92 | 22.68 | 7.776 | 83.376 | 83.376 | 0
| 3 | 290 | 12396 | 6708 |  | Level 2 Hotel | Access Scaffold |  | INDEPENDENT | 6 | 1 | 3 | 1 | 2 |  |  | 12 | m2-LxH | OFF HIRED | 2022-06-19 | 2022-09-19 | 100% |  | 13.2857 | 14 | 0.84 | 168 | 10.08 | 117.6 | 50.4 | 133.92 | 301.92 | 301.92 | 0
| 3 | 292 | 12398 | 7581 |  | Level 2 Hotel | Access Scaffold |  | INDEPENDENT | 1.8 | 1.3 | 3.5 | 1 | 2.5 |  |  | 4.5 | m2-LxH | OFF HIRED | 2022-06-19 | 2022-06-23 | 100% |  | 0.71429 | 14 | 0.84 | 63 | 3.78 | 44.1 | 18.9 | 2.7 | 65.7 | 65.7 | 0
| 3 | 315 | 12416 | 7581 |  | Level 2 Hotel | Access Scaffold |  | INDEPENDENT | 7 | 1.3 | 4 | 1 | 3 |  |  | 21 | m2-LxH | OFF HIRED | 2022-06-20 | 2022-06-23 | 100% |  | 0.57143 | 14 | 0.84 | 294 | 17.64 | 205.8 | 88.2 | 10.08 | 304.08 | 304.08 | 0
| 3 | 331 | 12428 | 8139 |  | Level 2 Hotel | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 3 | 1 | 2 |  |  | 8 | m2-LxH | OFF HIRED | 2022-06-22 | 2022-10-24 | 100% |  | 17.8571 | 14 | 0.84 | 112 | 6.72 | 78.4 | 33.6 | 120 | 232 | 232 | 0
| 3 | 166 | 12162 | 6711 |  | Level 2 Hotel | Access Scaffold |  | INDEPENDENT | 1.8 | 1.8 | 3 | 1 | 2 |  |  | 3.6 | m2-LxH | OFF HIRED | 2022-06-07 | 2022-09-23 | 100% |  | 15.5714 | 18 |  | 64.8 | 0 | 45.36 | 19.44 | 0 | 64.8 | 64.8 | 0
| 3 | 496 | 12701 | 6722 |  | Level 2 Hotel | Mobile Tower |  | Mobile Tower | 2.5 | 1.8 | 6 | 1 | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-09-23 | 2022-10-31 | 100% |  | -5.5714 | 100 | 10.15 | 250 | 25.375 |  | 75 | -141.375 | -66.375 | -66.375 | 0
| 3 | 496 | 12701 | 6722 |  | Level 2 Hotel | Mobile Tower |  | Mobile Tower | 2.5 | 1.8 | 6 | 1 | 5 |  |  | 5 | rm | OFF HIRED | 2022-07-12 | 2022-09-23 | 100% |  | 10.5714 | 100 | 10.15 | 500 | 50.75 | 350 | 150 | 536.5 | 1036.5 | 1036.5 | 0
| 3 | 525 | 12733 | 8241 |  | Level 2 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-15 | 2022-11-15 | 100% |  | 17.7143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 434 | 704 | 704 | 0
| 3 | 529 | 12738 | 7900 |  | Level 2 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-17 | 2022-09-20 | 100% |  | 9.4286 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 231 | 501 | 501 | 0
| 3 | 331 | 12740 | 8197 |  | Level 2 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 2.5 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-17 | 2022-10-31 | 100% |  | 15.2857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 374.5 | 644.5 | 644.5 | 0
| 3 | 519 | 12580 | 8191 |  | Level 2 Residence | Access Scaffold |  | INDEPENDENT | 12 | 1.3 | 7 | 1 | 6 |  |  | 72 | m2-LxH | OFF HIRED | 2022-07-01 | 2022-11-04 | 100% |  | 18.1429 | 14 |  | 1008 | 0 | 705.6 | 302.4 | 0 | 1008 | 1008 | 0
| 3 | 426 | 12586 | 7729 |  | Level 2 Residence | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 4 | 1 | 3 |  |  | 15 | m2-LxH | OFF HIRED | 2022-07-03 | 2022-07-27 | 100% |  | 3.5714 | 14 |  | 210 | 0 | 147 | 63 | 0 | 210 | 210 | 0
| 3 | 527 | 12741 | 7736 |  | Level 2 Hotel | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 6 | 1 | 5 |  |  | 20 | m2-LxH | OFF HIRED | 2022-07-17 | 2022-07-26 | 100% |  | 1.4286 | 14 |  | 280 | 0 | 196 | 84 | 0 | 280 | 280 | 0
| 3 | 451 | 12617 | 7824 |  | Level 2 Hotel | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 3 | 1 | 2 |  |  | 8 | m2-LxH | OFF HIRED | 2022-07-07 | 2022-08-16 | 100% |  | 5.8571 | 14 | 0.84 | 112 | 6.72 | 78.4 | 33.6 | 39.36 | 151.36 | 151.36 | 0
| 3 | 461 | 12616 | 6740 |  | Level 2 Hotel | Access Scaffold |  | INDEPENDENT | 8 | 1.3 | 3.5 | 1 | 2.5 |  |  | 20 | m2-LxH | OFF HIRED | 2022-07-07 | 2022-09-30 | 100% |  | 12.2857 | 14 | 0.84 | 280 | 16.8 | 196 | 84 | 206.4 | 486.4 | 486.4 | 0
| 3 | 581 | 12788 | 7738 |  | Level 2 Residance | Access Scaffold |  | INDEPENDENT | 7.5 | 1.3 | 7 | 1 | 6 |  |  | 45 | m2-LxH | OFF HIRED | 2022-07-21 | 2022-07-26 | 100% |  | 0.85714 | 14 | 0.84 | 630 | 37.8 | 441 | 189 | 32.4 | 662.4 | 662.4 | 0
| 3 | 495 | 12649 |  |  | Level 2 Residence | Birdcage Scaffold |  | Birdcage | 13 | 6 | 7.5 | 1 | 6.5 |  |  | 507 | m3 | ON HIRE | 2022-07-07 |  | 100% |  | 33.8571 | 7.5 | 0.7 | 3802.5 | 354.9 | 2661.75 | 0 | 12015.9 | 14677.65 | 13258.05 | 1419.6 |  |  | #VALUE! | 2661.75 | #VALUE! | #VALUE!
| 3 | 81 | 12707 | 7738 |  | Level 2 Hotel | Boarded Lift |  | Board Lift | 28 | 1.3 |  |  |  | 1 |  | 36.4 | m2-LxW | OFF HIRED | 2022-07-12 | 2022-07-26 | 100% |  | 2.1429 | 7.5 | 1.05 | 273 | 38.22 | 191.1 | 81.9 | 81.9 | 354.9 | 354.9 | 0
| 3 | 81 | 12640 | 8241 |  | Level 2 Hotel | Cantiliver |  | Cantiliver | 40 | 0.6 |  |  |  | 1 |  | 24 | m2-LxW | OFF HIRED | 2022-07-06 | 2022-11-15 | 100% |  | 19 | 36.5 | 3.15 | 876 | 75.6 | 613.2 | 262.8 | 1436.4 | 2312.4 | 2312.4 | 0
| 3 | 81 | 12640 | 8241 |  | Level 2 Hotel | Cantiliver |  | Cantiliver | 40 | 0.6 |  |  |  | 1 |  | 24 | m2-LxW | OFF HIRED | 2022-07-06 | 2022-11-15 | 100% |  | 19 | 36.5 | 3.15 | 876 | 75.6 | 613.2 | 262.8 | 1436.4 | 2312.4 | 2312.4 | 0
| 3 | 81 | 12640 | 8241 |  | Level 2 Hotel | Cantiliver |  | Cantiliver | 40 | 0.6 |  |  |  | 1 |  | 24 | m2-LxW | OFF HIRED | 2022-07-06 | 2022-11-15 | 100% |  | 19 | 36.5 | 3.15 | 876 | 75.6 | 613.2 | 262.8 | 1436.4 | 2312.4 | 2312.4 | 0
| 3 | 81 | 12640 | 8241 |  | Level 2 Hotel | Cantiliver |  | Cantiliver | 40 | 0.6 |  |  |  | 1 |  | 24 | m2-LxW | OFF HIRED | 2022-07-06 | 2022-11-15 | 100% |  | 19 | 36.5 | 3.15 | 876 | 75.6 | 613.2 | 262.8 | 1436.4 | 2312.4 | 2312.4 | 0
| 3 | 81 | 12707 | 7738 |  | Level 2 Hotel | Cantiliver |  | Cantiliver | 28 | 0.6 |  |  |  | 1 |  | 16.8 | m2-LxW | OFF HIRED | 2022-07-12 | 2022-07-26 | 100% |  | 2.1429 | 36.5 | 3.15 | 613.2 | 52.92 | 429.24 | 183.96 | 113.4 | 726.6 | 726.6 | 0
| 3 | 677 | 12953 | 8148 |  | Level 2 Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-08 | 2022-10-25 | 100% |  | 11.2857 | 135 |  | 270 | 0 | 189 | 81 | 0 | 270 | 270 | 0
| 3 | 671 | 12888 | 7860 |  | Level 2 Residance | Access Scaffold |  | Tower | 1.8 | 1.3 | 3.5 | 1 | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-08-06 | 2022-08-31 | 100% |  | 3.7143 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 113.75 | 451.25 | 451.25 | 0
| 3 | 608 | 12828 | 7740 |  | Level 2 Residance | Access Scaffold |  | Independent | 7.5 | 1.3 | 7 | 1 | 6 |  |  | 45 | m2-LxH | OFF HIRED | 2022-07-27 | 2022-07-29 | 100% |  | 0.42857 | 14 | 0.84 | 630 | 37.8 | 441 | 189 | 16.2 | 646.2 | 646.2 | 0
| 3 | 608 | 12828 | 7740 |  | Level 2 Residance | Access Scaffold |  | Independent | 7.5 | 1.3 | 7 | 1 | 6 |  |  | 45 | m2-LxH | OFF HIRED | 2022-07-27 | 2022-07-29 | 100% |  | 0.42857 | 14 | 0.84 | 630 | 37.8 | 441 | 189 | 16.2 | 646.2 | 646.2 | 0
| 3 | 796 | 13056 | 8338 |  | Level 2 Hotel | Access Scaffold |  | Independent | 7.5 | 1.3 | 6 |  | 6 |  |  | 45 | m2-LxH | OFF HIRED | 2022-08-23 | 2022-12-16 | 100% |  | 16.5714 | 14 | 0.84 | 630 | 37.8 | 441 | 189 | 626.4 | 1256.4 | 1256.4 | 0
| 3 | 766 | 13028 | 8256 |  | Level 2 Residance | Birdcage Scaffold |  | Birdcage | 24 | 4 | 7.5 | 1 | 6.5 |  |  | 624 | m3 | OFF HIRED | 2022-08-18 | 2022-11-19 | 100% |  | 13.4286 | 7.5 | 0.7 | 4680 | 436.8 | 3276 | 1404 | 5865.6 | 10545.6 | 10545.6 | 0
| 3 | 900 | 13273 | 6744 |  | Level 2 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-09-06 | 2022-09-30 | 100% |  | 3.5714 | 135 |  | 540 | 0 | 378 | 162 | 0 | 540 | 540 | 0
| 3 | 901 | 13273 | 6744 |  | Level 2 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-09-06 | 2022-09-30 | 100% |  | 3.5714 | 135 |  | 540 | 0 | 378 | 162 | 0 | 540 | 540 | 0
| 3 | 903 | 13274 | 8150 |  | Level 2 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-09-07 | 2022-10-25 | 100% |  | 7 | 135 |  | 540 | 0 | 378 | 162 | 0 | 540 | 540 | 0
| 3 | 849 | 13120 | 8151 |  | Level 2 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-08-29 | 2022-10-27 | 100% |  | 8.5714 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 262.5 | 600 | 600 | 0
| 3 | 849 | 13120 | 8151 |  | Level 2 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-08-29 | 2022-10-27 | 100% |  | 8.5714 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 262.5 | 600 | 600 | 0
| 3 | 864 | 13136 | 8051 |  | Level 2 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-08-31 | 2022-10-01 | 100% |  | 4.5714 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 140 | 477.5 | 477.5 | 0
| 3 | 849 | 13326 | 8308 |  | Level 2 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-13 | 2022-12-06 | 100% |  | 12.1429 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 297.5 | 567.5 | 567.5 | 0
| 3 | 964 | 13339 | 8488 |  | Level 2 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 5 |  | 5 |  |  | 5 | rm | OFF HIRED | 2022-09-15 | 2023-01-03 | 100% |  | 15.8571 | 135 | 12.25 | 675 | 61.25 | 472.5 | 202.5 | 971.25 | 1646.25 | 1646.25 | 0
| 3 | 865 | 13137 | 8104 |  | Level 2 Hotel | Access Scaffold |  | Independent | 5 | 1.3 | 2.5 |  | 2.5 |  |  | 12.5 | m2-LxH | OFF HIRED | 2022-08-31 | 2022-10-14 | 100% |  | 6.4286 | 14 | 0.84 | 175 | 10.5 | 122.5 | 52.5 | 67.5 | 242.5 | 242.5 | 0
| 3 | 899 | 13272 | 8417 |  | Level 2 Hotel | Access Scaffold |  | Independent | 7 | 1.3 | 4 |  | 4 |  |  | 28 | m2-LxH | OFF HIRED | 2022-09-06 | 2023-01-11 | 100% |  | 18.2857 | 14 | 0.84 | 392 | 23.52 | 274.4 | 117.6 | 430.08 | 822.08 | 822.08 | 0
| 3 | 920 | 13293 |  |  | Level 2 Hotel | Access Scaffold |  | Independent | 4 | 1.3 | 7 |  | 7 |  |  | 28 | m2-LxH | ON HIRE | 2022-09-08 |  | 100% |  | 24.8571 | 14 | 0.84 | 392 | 23.52 | 274.4 | 0 | 584.64 | 859.04 | 764.96 | 94.08 |  |  | #VALUE! | 274.4 | #VALUE! | #VALUE!
| 3 | 971 | 13346 | 8478 |  | Level 2 Hotel | Access Scaffold |  | Independent | 22.5 | 1.3 | 6 |  | 6 |  |  | 135 | m2-LxH | OFF HIRED | 2022-09-14 | 2022-12-31 | 100% |  | 15.5714 | 14 | 0.84 | 1890 | 113.4 | 1323 | 567 | 1765.8 | 3655.8 | 3655.8 | 0
| 3 | 910 | 13284 | 8271 |  | Level 2 hotel | Access Scaffold |  | Independent | 6.5 | 1.8 | 4 |  | 4 |  |  | 26 | m2-LxH | OFF HIRED | 2022-09-08 | 2022-11-24 | 100% |  | 11.1429 | 18 | 1.05 | 468 | 27.3 | 327.6 | 140.4 | 304.2 | 772.2 | 772.2 | 0
| 3 | 160 | 12157 | 7559 |  | Level 2 Residence | Access Scaffold |  | INDEPENDENT | 6 | 1.3 | 5 | 1 | 4 |  |  | 24 | m2-LxH | OFF HIRED | 2022-06-07 | 2022-06-08 | 100% |  | 0.28571 | 14 |  | 336 | 0 | 235.2 | 100.8 | 0 | 336 | 336 | 0
| 3 | 180 | 12176 | 7595 |  | Level 2 Residence | Access Scaffold |  | INDEPENDENT | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2.6 | m2-LxH | OFF HIRED | 2022-06-08 | 2022-06-30 | 100% |  | 3.2857 | 14 | 0.84 | 36.4 | 2.184 | 25.48 | 10.92 | 7.176 | 43.576 | 43.576 | 0
| 3 | 153 | 12249 | 7564 |  | Level 2 Residence | Access Scaffold |  | INDEPENDENT | 5 | 1.8 | 3.5 | 1 | 2.5 |  |  | 12.5 | m2-LxH | OFF HIRED | 2022-06-06 | 2022-06-17 | 100% |  | 1.7143 | 18 | 1.05 | 225 | 13.125 | 157.5 | 67.5 | 22.5 | 247.5 | 247.5 | 0
| 3 | 189 | 12186 | 7567 |  | Level 2 Residence | Access Scaffold |  | INDEPENDENT | 2.5 | 1.8 | 7.5 | 1 | 6.5 |  |  | 16.25 | m2-LxH | OFF HIRED | 2022-06-09 | 2022-06-20 | 100% |  | 1.7143 | 18 | 1.05 | 292.5 | 17.0625 | 204.75 | 87.75 | 29.25 | 321.75 | 321.75 | 0
| 3 | 190 | 12187 | 7567 |  | Level 2 Residence | Access Scaffold |  | INDEPENDENT | 4 | 1.8 | 7.5 | 1 | 6.5 |  |  | 26 | m2-LxH | OFF HIRED | 2022-06-09 | 2022-06-20 | 100% |  | 1.7143 | 18 | 1.05 | 468 | 27.3 | 327.6 | 140.4 | 46.8 | 514.8 | 514.8 | 0
| 3 | 190 | 12187 | 7567 |  | Level 2 Residence | Access Scaffold |  | INDEPENDENT | 4 | 1.8 | 7.5 | 1 | 6.5 |  |  | 26 | m2-LxH | OFF HIRED | 2022-06-09 | 2022-06-20 | 100% |  | 1.7143 | 18 | 1.05 | 468 | 27.3 | 327.6 | 140.4 | 46.8 | 514.8 | 514.8 | 0
| 3 | 424 | 12584 | 8028 |  | Level 2 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-07-03 | 2022-10-10 | 100% |  | 14.2857 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 525 | 930 | 930 | 0
| 3 | 525 | 12733 | 8241 |  | Level 2 Residence | HEAVY DUTY TOWER |  | Tower | 1 | 0.6 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-15 | 2022-11-15 | 100% |  | 17.7143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 434 | 704 | 704 | 0
| 3 | 569A | 12789 | 7738 |  | Level 2 Residance | Access Scaffold |  | INDEPENDENT | 7.5 | 1.3 | 7 | 1 | 6 |  |  | 45 | m2-LxH | OFF HIRED | 2022-07-21 | 2022-07-26 | 100% |  | 0.85714 | 14 |  | 630 | 0 | 441 | 189 | 0 | 630 | 630 | 0
| 3 | 483 | 12643 | 8051 |  | Level 2 Residance | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 3 | 1 | 2 |  |  | 8 | m2-LxH | OFF HIRED | 2022-07-06 | 2022-10-01 | 100% |  | 12.5714 | 14 | 0.84 | 112 | 6.72 | 78.4 | 33.6 | 84.48 | 196.48 | 196.48 | 0
| 3 | 418 | 12578 | 8192 |  | Level 2 Residence | Cantiliver |  | Cantiliver | 60 | 0.6 |  |  |  | 1 |  | 36 | m2-LxW | OFF HIRED | 2022-07-01 | 2022-11-03 | 100% |  | 18 | 36.5 |  | 1314 | 0 | 919.8 | 394.2 | 0 | 1314 | 1314 | 0
| 3 | 658 | 12885 | 8590 |  | Level 2 Residence | Access Scaffold |  | Tower | 2.5 | 1.3 | 8 | 1 | 7 |  |  | 7 | rm | OFF HIRED | 2022-08-05 | 2023-02-21 | 100% |  | 28.7143 | 135 |  | 945 | 0 | 661.5 | 283.5 | 0 | 945 | 661.5 | 283.5 |  |  | #VALUE! | 1323 | #VALUE! | #VALUE!
| 3 | 658 | 12885 | 8590 |  | Level 2 Residence | Access Scaffold |  | Tower | 2.5 | 1.3 | 8 | 1 | 7 |  |  | 7 | rm | OFF HIRED | 2022-08-05 | 2023-02-21 | 100% |  | 28.7143 | 135 |  | 945 | 0 | 661.5 | 283.5 | 0 | 945 | 661.5 | 283.5 |  |  | #VALUE! | 1323 | #VALUE! | #VALUE!
| 3 | 890 | 13261 |  |  | Level 2 Residence | Mobile Tower |  | Mobile Tower | 2.5 | 1.8 | 7 |  | 7 |  |  | 7 | rm | ON HIRE | 2022-09-05 |  | 100% |  | 25.2857 | 100 | 10.15 | 700 | 71.05 | 490 | 0 | 1796.55 | 2286.55 | 2002.35 | 284.2 |  |  | #VALUE! | 1470 | #VALUE! | #VALUE!
| 3 | 890 | 13261 |  |  | Level 2 Residence | Mobile Tower |  | Mobile Tower | 2.5 | 1.8 | 7 |  | 7 |  |  | 7 | rm | ON HIRE | 2022-09-05 |  | 100% |  | 25.2857 | 100 | 10.15 | 700 | 71.05 | 490 | 0 | 1796.55 | 2286.55 | 2002.35 | 284.2 |  |  | #VALUE! | 1470 | #VALUE! | #VALUE!
| 3 | 890 | 13261 |  |  | Level 2 Residence | Mobile Tower |  | Mobile Tower | 2.5 | 1.8 | 7 |  | 7 |  |  | 7 | rm | ON HIRE | 2022-09-05 |  | 100% |  | 25.2857 | 100 | 10.15 | 700 | 71.05 | 490 | 0 | 1796.55 | 2286.55 | 2002.35 | 284.2 |  |  | #VALUE! | 1470 | #VALUE! | #VALUE!
| 3 | 830 | 13099 | 8150 |  | Level 2 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 8 |  | 8 |  |  | 8 | rm | OFF HIRED | 2022-08-26 | 2022-10-25 | 100% |  | 8.7143 | 135 |  | 1080 | 0 | 756 | 324 | 0 | 1080 | 1080 | 0
| 3 | 876 | 13147 | 8107 |  | Level 2 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-09-01 | 2022-10-14 | 100% |  | 6.2857 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 192.5 | 530 | 530 | 0
| 3 | 844 | 13112 | 7882 |  | Level 2 Residence | Access Scaffold |  | Independent | 7 | 1.3 | 2.5 |  | 2.5 |  |  | 17.5 | m2-LxH | OFF HIRED | 2022-08-27 | 2022-09-10 | 100% |  | 2.1429 | 14 | 0.84 | 245 | 14.7 | 171.5 | 73.5 | 31.5 | 276.5 | 276.5 | 0
| 3 | 347 | 13275 | 8203 |  | Level 2 to 4 Residence | Birdcage Scaffold |  | Birdcage | 4 | 4 | 16 |  | 16 |  |  | 256 | m3 | OFF HIRED | 2022-09-07 | 2022-11-05 | 100% |  | 8.5714 | 7.5 | 0.7 | 1920 | 179.2 | 1344 | 576 | 1536 | 3456 | 3456 | 0
| 3 | 941 | 13314 | 8612 |  | Level 2 Residence | Birdcage Scaffold |  | Birdcage | 4 | 3 | 5.5 |  | 5.5 |  |  | 66 | m3 | OFF HIRED | 2022-09-10 | 2023-01-26 | 100% |  | 19.8571 | 7.5 | 0.7 | 495 | 46.2 | 346.5 | 148.5 | 917.4 | 1412.4 | 1412.4 | 0
| 3 | 410 | 12571 | 8148 |  | Level 2 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 2.5 | 6 | 1 | 5 |  |  | 5 | rm | OFF HIRED | 2022-06-30 | 2022-10-25 | 100% |  | 16.8571 | 135 |  | 675 | 0 | 472.5 | 202.5 | 0 | 675 | 675 | 0
| 3 | 1021 | 13456 | 8290 |  | Level 2 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-09-20 | 2022-11-29 | 100% |  | 10.1429 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 310.625 | 648.125 | 648.125 | 0
| 3 | 1034 | 13471 | 8165 |  | Level 2 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 5 |  | 5 |  |  | 5 | rm | OFF HIRED | 2022-09-23 | 2022-10-28 | 100% |  | 5.1429 | 135 | 12.25 | 675 | 61.25 | 472.5 | 202.5 | 315 | 990 | 990 | 0
| 3 | 1034 | 13471 | 8165 |  | Level 2 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 2.5 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-09-23 | 2022-10-28 | 100% |  | 5.1429 | 135 | 12.25 | 540 | 49 | 378 | 162 | 252 | 792 | 792 | 0
| 3 | 1022 | 13457 | 8165 |  | Level 2 Hotel | Access Scaffold |  | Independent | 35 | 1.3 | 4 |  | 4 |  |  | 140 | m2-LxH | OFF HIRED | 2022-09-22 | 2022-10-28 | 100% |  | 5.2857 | 14 | 0.84 | 1960 | 117.6 | 1372 | 588 | 621.6 | 2581.6 | 2581.6 | 0
| 3 | 886 | 13133 | 7890 |  | Level 2 Hotel | Boarded Lift |  | Board Lift | 20 | 1 |  |  |  | 1 |  | 20 | m2-LxW | OFF HIRED | 2022-08-30 | 2022-09-15 | 100% |  | 2.4286 | 7.5 | 1.05 | 150 | 21 | 105 | 45 | 51 | 201 | 201 | 0
| 3 | 886 | 13133 | 7890 |  | Level 2 Hotel | Boarded Lift |  | Board Lift | 20 | 1 |  |  |  | 1 |  | 20 | m2-LxW | OFF HIRED | 2022-08-30 | 2022-09-15 | 100% |  | 2.4286 | 7.5 | 1.05 | 150 | 21 | 105 | 45 | 51 | 201 | 201 | 0
| 3 | 1118 | 13602 | 8204 |  | Leevel 2 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-10-03 | 2022-11-05 | 100% |  | 4.8571 | 135 | 12.25 | 540 | 49 | 378 | 162 | 238 | 778 | 778 | 0
| 3 | 1118 | 13602 | 8204 |  | Leevel 2 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-10-03 | 2022-11-05 | 100% |  | 4.8571 | 135 | 12.25 | 540 | 49 | 378 | 162 | 238 | 778 | 778 | 0
| 3 | 1173 | 13658 | 8093 |  | Level 2 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 6 |  | 6 |  |  | 6 | rm | OFF HIRED | 2022-10-10 | 2022-10-11 | 100% |  | 0.28571 | 135 | 12.25 | 810 | 73.5 | 567 | 243 | 21 | 831 | 831 | 0
| 3 | 1221 | 13757 | 8240 |  | Level 2 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 6 |  | 6 |  |  | 6 | rm | OFF HIRED | 2022-10-15 | 2022-11-15 | 100% |  | 4.5714 | 135 | 12.25 | 810 | 73.5 | 567 | 243 | 336 | 1146 | 1146 | 0
| 3 | 1239 | 13777 | 8219 |  | Level 2 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4.5 |  | 4.5 |  |  | 4.5 | rm | OFF HIRED | 2022-10-17 | 2022-11-10 | 100% |  | 3.5714 | 135 | 12.25 | 607.5 | 55.125 | 425.25 | 182.25 | 196.875 | 804.375 | 804.375 | 0
| 3 | 1267 | 13705 | 8613 |  | Level 2 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 5.5 |  | 5.5 |  |  | 5.5 | rm | OFF HIRED | 2022-10-21 | 2023-01-27 | 100% |  | 14.1429 | 135 | 12.25 | 742.5 | 67.375 | 519.75 | 222.75 | 952.875 | 1695.375 | 1695.375 | 0
| 3 | 1278 | 13717 | 8204 |  | Leevel 2 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-10-22 | 2022-11-05 | 100% |  | 2.1429 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 52.5 | 322.5 | 322.5 | 0
| 3 | 1187 | 13672 | 8166 |  | Level 2 Hotel | Access Scaffold |  | Independent | 1.3 | 1.3 | 2 |  | 2 |  |  | 2.6 | m2-LxH | OFF HIRED | 2022-10-12 | 2022-10-28 | 100% |  | 2.4286 | 14 | 0.84 | 36.4 | 2.184 | 25.48 | 10.92 | 5.304 | 41.704 | 41.704 | 0
| 3 | 1204 | 13690 | 8249 |  | Level 2 Residence | Access Scaffold |  | Independent | 13.5 | 1.3 | 5.5 |  | 5.5 |  |  | 74.25 | m2-LxH | OFF HIRED | 2022-10-13 | 2022-11-17 | 100% |  | 5.1429 | 14 | 0.84 | 1039.5 | 62.37 | 727.65 | 311.85 | 320.76 | 1360.26 | 1360.26 | 0
| 3 | 1116 | 13550 | 8165 |  | Level 2 Hotel | Access Scaffold |  | Independent | 5 | 1.3 | 4 |  | 4 |  |  | 20 | m2-LxH | OFF HIRED | 2022-10-03 | 2022-10-28 | 100% |  | 3.7143 | 14 | 0.84 | 280 | 16.8 | 196 | 84 | 62.4 | 342.4 | 342.4 | 0
| 3 | 1061 | 13498 | 8228 |  | Level 2 Residence | Access Scaffold |  | Independent | 7.3 | 1.3 | 6 |  | 6 |  |  | 43.8 | m2-LxH | OFF HIRED | 2022-09-26 | 2022-11-13 | 100% |  | 7 | 14 | 0.84 | 613.2 | 36.792 | 429.24 | 183.96 | 257.544 | 870.744 | 870.744 | 0
| 3 | 658 | 13761 | 8590 |  | Level 2 Residence | Access Scaffold |  | Independent | 13 | 1.3 | 6 |  | 6 |  |  | 78 | m2-LxH | OFF HIRED | 2022-10-15 | 2023-02-21 | 100% |  | 18.5714 | 14 | 0.84 | 1092 | 65.52 | 764.4 | 327.6 | 1216.8 | 2308.8 | 1784.64 | 524.16 |  |  | #VALUE! | 764.4 | #VALUE! | #VALUE!
| 3 | 1227 | 13765 | 8111 |  | Level 2 To 5 Residence | Access Scaffold |  | Independent | 2.5 | 1.3 | 4 |  | 4 |  |  | 10 | m2-LxH | OFF HIRED | 2022-10-16 | 2022-10-17 | 100% |  | 0.28571 | 14 | 0.84 | 140 | 8.4 | 98 | 42 | 2.4 | 142.4 | 142.4 | 0
| 3 | 1286 | 13725 | 8229 |  | Level 2 Residence | Access Scaffold |  | Independent | 13 | 1.3 | 6 |  | 6 |  |  | 78 | m2-LxH | OFF HIRED | 2022-10-24 | 2022-11-04 | 100% |  | 1.7143 | 14 | 0.84 | 1092 | 65.52 | 764.4 | 327.6 | 112.32 | 1204.32 | 1204.32 | 0
| 3 | 1071 | 13507 | 8298 |  | Level 2 Hotel | Access Scaffold |  | Independent | 6 | 1.8 | 4 |  | 4 |  |  | 24 | m2-LxH | OFF HIRED | 2022-09-27 | 2022-12-04 | 100% |  | 9.8571 | 18 | 1.05 | 432 | 25.2 | 302.4 | 129.6 | 248.4 | 680.4 | 680.4 | 0
| 3 | 1061 | 13498 | 8228 |  | Level 2 Residence | Birdcage Scaffold |  | Birdcage | 18 | 8 | 6 |  | 6 |  |  | 864 | m3 | OFF HIRED | 2022-09-26 | 2022-11-13 | 100% |  | 7 | 7.5 | 0.7 | 6480 | 604.8 | 4536 | 1944 | 4233.6 | 10713.6 | 10713.6 | 0
| 3 | 1061 | 13498 | 8288 |  | Level 2 Residence | Birdcage Scaffold |  | Birdcage | 11 | 7 | 6 |  | 6 |  |  | 462 | m3 | OFF HIRED | 2022-09-26 | 2022-11-13 | 100% |  | 7 | 7.5 | 0.7 | 3465 | 323.4 | 2425.5 | 1039.5 | 2263.8 | 5728.8 | 5728.8 | 0
| 3 | 1222 | 13758 |  |  | Level 2 Residence | Birdcage Scaffold |  | Birdcage | 3 | 2.5 | 6 |  | 6 |  |  | 45 | m3 | ON HIRE | 2022-10-15 |  | 100% |  | 19.5714 | 7.5 | 0.7 | 337.5 | 31.5 | 236.25 | 0 | 616.5 | 852.75 | 726.75 | 126 |  |  | #VALUE! | 236.25 | #VALUE! | #VALUE!
| 3 | 1119 | 13603 | 8170 |  | Level 2 Hotel | Boarded Lift |  | Board Lift | 20 | 5 |  |  |  | 1 |  | 100 | m2-LxW | OFF HIRED | 2022-10-03 | 2022-10-29 | 100% |  | 3.8571 | 7.5 | 1.05 | 750 | 105 | 525 | 225 | 405 | 1155 | 1155 | 0
| 3 | 1041 | 13759 | 8474 |  | Level 2 Residence | Cantiliver |  | Cantiliver | 30 | 0.6 |  |  |  | 1 |  | 18 | m2-LxW | OFF HIRED | 2022-10-15 | 2022-12-27 | 100% |  | 10.5714 | 36.5 | 3.15 | 657 | 56.7 | 459.9 | 197.1 | 599.4 | 1256.4 | 1256.4 | 0
| 3 | 1041 | 13759 | 8474 |  | Level 2 Residence | Cantiliver |  | Cantiliver | 30 | 0.6 |  |  |  | 1 |  | 18 | m2-LxW | OFF HIRED | 2022-10-15 | 2022-12-27 | 100% |  | 10.5714 | 36.5 | 3.15 | 657 | 56.7 | 459.9 | 197.1 | 599.4 | 1256.4 | 1256.4 | 0
| 3 | 1041 | 13759 | 8474 |  | Level 2 Residence | Cantiliver |  | Cantiliver | 30 | 0.6 |  |  |  | 1 |  | 18 | m2-LxW | OFF HIRED | 2022-10-15 | 2022-12-27 | 100% |  | 10.5714 | 36.5 | 3.15 | 657 | 56.7 | 459.9 | 197.1 | 599.4 | 1256.4 | 1256.4 | 0
| 3 | 1267 | 13705 | 8613 |  | Level 2 Residence | Cantiliver |  | Cantiliver | 1.8 | 1 |  |  |  | 1 |  | 1.8 | m2-LxW | OFF HIRED | 2022-10-21 | 2023-01-27 | 100% |  | 14.1429 | 36.5 | 3.15 | 65.7 | 5.67 | 45.99 | 19.71 | 80.19 | 145.89 | 145.89 | 0
| 3 | 1377 | 13865 | 8266 |  | Level 2 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-11-05 | 2022-11-22 | 100% |  | 2.5714 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 63 | 333 | 333 | 0
| 3 | 1376 | 13864 | 8266 |  | Level 2 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-11-05 | 2022-11-22 | 100% |  | 2.5714 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 63 | 333 | 333 | 0
| 3 | 1382 | 13870 | 8328 |  | Level 3 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-11-07 | 2022-12-13 | 100% |  | 5.2857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 129.5 | 399.5 | 399.5 | 0
| 3 | 1386 | 13874 | 8431 |  | Level 2 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 6 |  | 6 |  |  | 6 | rm | OFF HIRED | 2022-11-08 | 2023-01-17 | 100% |  | 10.1429 | 135 | 12.25 | 810 | 73.5 | 567 | 243 | 745.5 | 1555.5 | 1555.5 | 0
| 3 | 1406 | 13894 | 8224 |  | Level 2 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 5.5 |  | 5.5 |  |  | 5.5 | rm | OFF HIRED | 2022-11-10 | 2022-11-11 | 100% |  | 0.28571 | 135 | 12.25 | 742.5 | 67.375 | 519.75 | 222.75 | 19.25 | 761.75 | 761.75 | 0
| 3 | 1406 | 13894 | 8224 |  | Level 2 Residence | Buttress |  | Tower | 2.5 | 2.5 | 2.5 |  | 2.5 |  |  | 15.625 | m3 | OFF HIRED | 2022-11-10 | 2022-11-11 | 100% |  | 0.28571 | 5.25 | 0.35 | 82.0312 | 5.4688 | 57.4219 | 24.6094 | 1.5625 | 83.5938 | 83.5938 | 0
| 3 | 1411 | 13899 | 8625 |  | Level 2 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 5 |  | 5 |  |  | 5 | rm | OFF HIRED | 2022-11-10 | 2023-02-01 | 100% |  | 12 | 135 | 12.25 | 675 | 61.25 | 472.5 | 202.5 | 735 | 1410 | 1198.75 | 211.25 |  |  | #VALUE! | 472.5 | #VALUE! | #VALUE!
| 3 | 1323 | 13811 | 8478 |  | Level 2 Hotel | Mobile Tower |  | Tower | 1.8 | 1.8 | 6 |  | 6 |  |  | 6 | rm | OFF HIRED | 2022-10-31 | 2022-12-31 | 100% |  | 8.8571 | 100 | 10.15 | 600 | 60.9 | 420 | 180 | 539.4 | 1139.4 | 1139.4 | 0
| 3 | 1344 | 13832 | 8586 |  | Level 3 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-11-01 | 2023-02-21 | 100% |  | 16.1429 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 395.5 | 665.5 | 511 | 154.5 |  |  | #VALUE! | 189 | #VALUE! | #VALUE!
| 3 | 1468 | 13956 | 8451 |  | Level 2 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 1.5 |  | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2022-11-19 | 2022-12-21 | 100% |  | 4.7143 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 60.75 | 86.625 | 289.125 | 289.125 | 0
| 3 | 1320 | 13808 | 8287 |  | Level 2 Residence | Access Scaffold |  | INDEPENDENT | 7.5 | 1.3 | 5.5 |  | 5.5 |  |  | 41.25 | m2-LxH | OFF HIRED | 2022-10-29 | 2022-11-28 | 100% |  | 4.4286 | 14 |  | 577.5 | 0 | 404.25 | 173.25 | 0 | 577.5 | 577.5 | 0
| 3 | 1426 | 13914 | 8329 |  | Level 2 To 5 Residence | Access Scaffold |  | INDEPENDENT | 30 | 1 | 2 |  | 2 |  |  | 60 | m2-LxH | OFF HIRED | 2022-11-12 | 2022-12-14 | 100% |  | 4.7143 | 14 | 0.84 | 840 | 50.4 | 588 | 252 | 237.6 | 1077.6 | 1077.6 | 0
| 3 | 1490 | 13977 | 8303 |  | Level 2 Hotel | Access Scaffold |  | INDEPENDENT | 3.8 | 1.3 | 1.5 |  | 1.5 |  |  | 5.7 | m2-LxH | OFF HIRED | 2022-11-24 | 2022-12-05 | 100% |  | 1.7143 | 14 | 0.84 | 79.8 | 4.788 | 55.86 | 23.94 | 8.208 | 88.008 | 88.008 | 0
| 3 | 1332 | 13820 | 8275 |  | Level 2 To Level 5 Hotel | Access Scaffold |  | Independent | 5 | 1.8 | 14.5 |  | 14.5 |  |  | 72.5 | m2-LxH | OFF HIRED | 2022-10-31 | 2022-11-26 | 100% |  | 3.8571 | 18 | 1.05 | 1305 | 76.125 | 913.5 | 391.5 | 293.625 | 1598.625 | 1598.625 | 0
| 3 | 1336 | 13824 | 8585 |  | Level 2 Hotel | Access Scaffold |  | Independent | 1.8 | 1.8 | 6 |  | 6 |  |  | 10.8 | m2-LxH | OFF HIRED | 2022-11-01 | 2023-02-21 | 100% |  | 16.1429 | 18 | 1.05 | 194.4 | 11.34 | 136.08 | 58.32 | 183.06 | 377.46 | 285.12 | 92.34 |  |  | #VALUE! | 136.08 | #VALUE! | #VALUE!
| 3 | 1359 | 13847 | 8228 |  | Level 2 Residence | Birdcage Scaffold |  | Birdcage | 2.6 | 2.6 | 4 |  | 4 |  |  | 27.04 | m3 | OFF HIRED | 2022-11-03 | 2022-11-13 | 100% |  | 1.5714 | 7.5 | 0.7 | 202.8 | 18.928 | 141.96 | 60.84 | 29.744 | 232.544 | 232.544 | 0
| 3 | 1361 | 13850 | 8213 |  | Level 2 Hotel | Birdcage Scaffold |  | Birdcage | 6.3 | 3.9 | 6 |  | 6 |  |  | 147.42 | m3 | OFF HIRED | 2022-11-03 | 2022-11-09 | 100% |  | 1 | 7.5 | 0.7 | 1105.65 | 103.194 | 773.955 | 331.695 | 103.194 | 1208.844 | 1208.844 | 0
| 3 | 1517 | 14055 | 8477 |  | Level 2 Hotel | Mobile Tower |  | Tower | 1.8 | 1.8 | 5 |  | 5 |  |  | 5 | rm | OFF HIRED | 2022-11-30 | 2022-12-31 | 100% |  | 4.5714 | 100 | 10.15 | 500 | 50.75 | 350 | 150 | 232 | 732 | 732 | 0
| 3 | 1651 | 14186 | 8488 |  | Level 2 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 4.5 |  | 4.5 |  |  | 4.5 | rm | OFF HIRED | 2022-12-22 | 2023-01-03 | 100% |  | 1.8571 | 135 | 12.25 | 607.5 | 55.125 | 425.25 | 182.25 | 102.375 | 709.875 | 709.875 | 0
| 3 | 1618 | 14153 | 8482 |  | Level 2 Hotel | Access Scaffold |  | INDEPENDENT | 8.1 | 1 | 2 |  | 2 |  |  | 16.2 | m2-LxH | OFF HIRED | 2022-12-17 | 2023-01-02 | 100% |  | 2.4286 | 14 | 0.84 | 226.8 | 13.608 | 158.76 | 68.04 | 33.048 | 259.848 | 259.848 | 0
| 3 | 1558 | 14095 | 8494 |  | Level 2 Hotel | Access Scaffold |  | INDEPENDENT | 11.3 | 1.3 | 1.5 |  | 1.5 |  |  | 16.95 | m2-LxH | OFF HIRED | 2022-12-09 | 2023-01-05 | 100% |  | 4 | 14 | 0.84 | 237.3 | 14.238 | 166.11 | 71.19 | 56.952 | 294.252 | 294.252 | 0
| 3 | 1540 | 14076 | 8640 |  | Level 2 Hotel | Access Scaffold |  | INDEPENDENT | 4.5 | 1.3 | 6 |  | 6 |  |  | 27 | m2-LxH | OFF HIRED | 2022-12-07 | 2023-02-07 | 100% |  | 9 | 14 | 0 | 378 | 0 | 264.6 | 113.4 | 0 | 378 | 264.6 | 113.4 |  |  | #VALUE! | 264.6 | #VALUE! | #VALUE!
| 3 | 1542 | 14078 | 8451 |  | Level 2 Hotel | Access Scaffold |  | INDEPENDENT | 8.8 | 1.3 | 5 |  | 5 |  |  | 44 | m2-LxH | OFF HIRED | 2022-12-07 | 2022-12-21 | 100% |  | 2.1429 | 14 | 0.84 | 616 | 36.96 | 431.2 | 184.8 | 79.2 | 695.2 | 695.2 | 0
| 3 | 1521 | 14059 | 8307 |  | Level 2 Residence | Access Scaffold |  | INDEPENDENT | 7.9 | 1 | 6 |  | 6 |  |  | 47.4 | m2-LxH | OFF HIRED | 2022-12-03 | 2022-12-06 | 100% |  | 0.57143 | 14 | 0.84 | 663.6 | 39.816 | 464.52 | 199.08 | 22.752 | 686.352 | 686.352 | 0
| 3 | 1557 | 14089 | 8451 |  | Level 2 Hotel | Access Scaffold |  | INDEPENDENT | 11.1 | 1.3 | 5 |  | 5 |  |  | 55.5 | m2-LxH | OFF HIRED | 2022-12-09 | 2022-12-21 | 100% |  | 1.8571 | 14 | 0.84 | 777 | 46.62 | 543.9 | 233.1 | 86.58 | 863.58 | 863.58 | 0
| 3 | 1621 | 14158 | 8463 |  | Level 2 Hotel | Access Scaffold |  | Independent | 6.3 | 1.8 | 4.3 |  | 4.3 |  |  | 27.09 | m2-LxH | OFF HIRED | 2022-12-19 | 2022-12-24 | 100% |  | 0.85714 | 18 | 1.05 | 487.62 | 28.4445 | 341.334 | 146.286 | 24.381 | 512.001 | 512.001 | 0
| 3 | 1512 | 13999 | 8307 |  | Level 2 Residence | Birdcage Scaffold |  | Birdcage | 7.9 | 2.5 | 6 |  | 6 |  |  | 118.5 | m3 | OFF HIRED | 2022-11-29 | 2022-12-06 | 100% |  | 1.1429 | 7.5 | 0.7 | 888.75 | 82.95 | 622.125 | 266.625 | 94.8 | 983.55 | 983.55 | 0
| 3 | 1521 | 14059 | 8307 |  | Level 2 Residence | Cantiliver |  | Cantiliver | 1.8 | 1 |  |  |  | 1 |  | 1.8 | m2-LxW | OFF HIRED | 2022-12-03 | 2022-12-06 | 100% |  | 0.57143 | 36.5 | 3.15 | 65.7 | 5.67 | 45.99 | 19.71 | 3.24 | 68.94 | 68.94 | 0
| 3 | 1557 | 14089 | 8451 |  | Level 2 Hotel | Boarded Lift |  | Board Lift | 1.5 | 1 |  |  |  | 1 |  | 1.5 | m2-LxW | OFF HIRED | 2022-12-09 | 2022-12-21 | 100% |  | 1.8571 | 7.5 | 1.05 | 11.25 | 1.575 | 7.875 | 3.375 | 2.925 | 14.175 | 14.175 | 0
| 3 | 1557 | 14089 | 8451 |  | Level 2 Hotel | Boarded Lift |  | Board Lift | 1.5 | 1 |  |  |  | 1 |  | 1.5 | m2-LxW | OFF HIRED | 2022-12-09 | 2022-12-21 | 100% |  | 1.8571 | 7.5 | 1.05 | 11.25 | 1.575 | 7.875 | 3.375 | 2.925 | 14.175 | 14.175 | 0
| 3 | 1557 | 14089 | 8451 |  | Level 2 Hotel | Boarded Lift |  | Board Lift | 1.5 | 1 |  |  |  | 1 |  | 1.5 | m2-LxW | OFF HIRED | 2022-12-09 | 2022-12-21 | 100% |  | 1.8571 | 7.5 | 1.05 | 11.25 | 1.575 | 7.875 | 3.375 | 2.925 | 14.175 | 14.175 | 0
| 3 | 1557 | 14089 | 8451 |  | Level 2 Hotel | Boarded Lift |  | Board Lift | 1.5 | 1 |  |  |  | 1 |  | 1.5 | m2-LxW | OFF HIRED | 2022-12-09 | 2022-12-21 | 100% |  | 1.8571 | 7.5 | 1.05 | 11.25 | 1.575 | 7.875 | 3.375 | 2.925 | 14.175 | 14.175 | 0
| 3 | 1557 | 14089 | 8451 |  | Level 2 Hotel | Boarded Lift |  | Board Lift | 1.5 | 1 |  |  |  | 1 |  | 1.5 | m2-LxW | OFF HIRED | 2022-12-09 | 2022-12-21 | 100% |  | 1.8571 | 7.5 | 1.05 | 11.25 | 1.575 | 7.875 | 3.375 | 2.925 | 14.175 | 14.175 | 0
| 3 | 1557 | 14089 | 8451 |  | Level 2 Hotel | Boarded Lift |  | Board Lift | 1.5 | 1 |  |  |  | 1 |  | 1.5 | m2-LxW | OFF HIRED | 2022-12-09 | 2022-12-21 | 100% |  | 1.8571 | 7.5 | 1.05 | 11.25 | 1.575 | 7.875 | 3.375 | 2.925 | 14.175 | 14.175 | 0
| 3 | 1557 | 14089 | 8451 |  | Level 2 Hotel | Boarded Lift |  | Board Lift | 1.5 | 1 |  |  |  | 1 |  | 1.5 | m2-LxW | OFF HIRED | 2022-12-09 | 2022-12-21 | 100% |  | 1.8571 | 7.5 | 1.05 | 11.25 | 1.575 | 7.875 | 3.375 | 2.925 | 14.175 | 14.175 | 0
| 3 | 1557 | 14089 | 8451 |  | Level 2 Hotel | Boarded Lift |  | Board Lift | 1.5 | 1 |  |  |  | 1 |  | 1.5 | m2-LxW | OFF HIRED | 2022-12-09 | 2022-12-21 | 100% |  | 1.8571 | 7.5 | 1.05 | 11.25 | 1.575 | 7.875 | 3.375 | 2.925 | 14.175 | 14.175 | 0
| 3 | 1557 | 14089 | 8451 |  | Level 2 Hotel | Boarded Lift |  | Board Lift | 1.5 | 1 |  |  |  | 1 |  | 1.5 | m2-LxW | OFF HIRED | 2022-12-09 | 2022-12-21 | 100% |  | 1.8571 | 7.5 | 1.05 | 11.25 | 1.575 | 7.875 | 3.375 | 2.925 | 14.175 | 14.175 | 0
| 4 |  | 12081 | 7597 |  | Level -3 Hotel | Access Scaffold |  | INDEPENDENT | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2.6 | m2-LxH | OFF HIRED | 2022-05-19 | 2022-07-06 | 100% |  | 7 | 14 |  | 36.4 | 0 | 25.48 | 10.92 | 0 | 36.4 | 36.4 | 0
| 4 |  | 12081 | 7597 |  | Level -3 Hotel | Access Scaffold |  | INDEPENDENT | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2.6 | m2-LxH | OFF HIRED | 2022-05-19 | 2022-07-06 | 100% |  | 7 | 14 |  | 36.4 | 0 | 25.48 | 10.92 | 0 | 36.4 | 36.4 | 0
| 4 |  | 12079 | 7580 |  | Level-3 Residence Studio Room | Access Scaffold |  | INDEPENDENT | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 3.6 | m2-LxH | OFF HIRED | 2022-05-19 | 2022-06-23 | 100% |  | 5.1429 | 14 |  | 50.4 | 0 | 35.28 | 15.12 | 0 | 50.4 | 50.4 | 0
| 4 |  | 12079 | 7580 |  | Level-3 Residence Studio Room | Access Scaffold |  | INDEPENDENT | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 3.6 | m2-LxH | OFF HIRED | 2022-05-19 | 2022-06-23 | 100% |  | 5.1429 | 14 |  | 50.4 | 0 | 35.28 | 15.12 | 0 | 50.4 | 50.4 | 0
| 4 |  | 12079 | 7580 |  | Level-3 Residence Studio Room | Access Scaffold |  | INDEPENDENT | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 3.6 | m2-LxH | OFF HIRED | 2022-05-19 | 2022-06-23 | 100% |  | 5.1429 | 14 |  | 50.4 | 0 | 35.28 | 15.12 | 0 | 50.4 | 50.4 | 0
| 4 |  | 12079 | 7580 |  | Level-3 Residence Studio Room | Access Scaffold |  | INDEPENDENT | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 3.6 | m2-LxH | OFF HIRED | 2022-05-19 | 2022-06-23 | 100% |  | 5.1429 | 14 |  | 50.4 | 0 | 35.28 | 15.12 | 0 | 50.4 | 50.4 | 0
| 4 |  | 12079 | 7580 |  | Level-3 Residence Studio Room | Access Scaffold |  | INDEPENDENT | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 3.6 | m2-LxH | OFF HIRED | 2022-05-19 | 2022-06-23 | 100% |  | 5.1429 | 14 |  | 50.4 | 0 | 35.28 | 15.12 | 0 | 50.4 | 50.4 | 0
| 4 |  | 12127 | 7561 |  | Level 3 Hotel Lift Front | Access Scaffold |  | INDEPENDENT | 1.6 | 1.3 | 3 | 1 | 2 |  |  | 3.2 | m2-LxH | OFF HIRED | 2022-05-30 | 2022-06-05 | 100% |  | 1 | 14 |  | 44.8 | 0 | 31.36 | 13.44 | 0 | 44.8 | 44.8 | 0
| 4 |  | 12119 | 7561 |  | Level 3 Residance | Access Scaffold |  | INDEPENDENT | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 3.6 | m2-LxH | OFF HIRED | 2022-05-29 | 2022-06-05 | 100% |  | 1.1429 | 14 |  | 50.4 | 0 | 35.28 | 15.12 | 0 | 50.4 | 50.4 | 0
| 4 |  | 12138 | 7570 |  | Level 3 Residance | Access Scaffold |  | INDEPENDENT | 2.5 | 1.3 | 3 | 1 | 2 |  |  | 5 | m2-LxH | OFF HIRED | 2022-05-30 | 2022-06-12 | 100% |  | 2 | 14 |  | 70 | 0 | 49 | 21 | 0 | 70 | 70 | 0
| 4 |  | 12138 | 7570 |  | Level 3 Residance | Access Scaffold |  | INDEPENDENT | 6 | 1.3 | 3 | 1 | 2 |  |  | 12 | m2-LxH | OFF HIRED | 2022-05-30 | 2022-06-12 | 100% |  | 2 | 14 |  | 168 | 0 | 117.6 | 50.4 | 0 | 168 | 168 | 0
| 4 | 334 | 12435 | 7585 |  | Level 3 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-06-23 | 2022-06-26 | 100% |  | 0.57143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 14 | 284 | 284 | 0
| 4 | 367 | 12516 | 7709 |  | Level 3 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-06-27 | 2022-07-13 | 100% |  | 2.4286 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 59.5 | 329.5 | 329.5 | 0
| 4 | 367 | 12516 | 7709 |  | Level 3 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-06-27 | 2022-07-13 | 100% |  | 2.4286 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 59.5 | 329.5 | 329.5 | 0
| 4 | 148 | 12246 | 7830 |  | Level 3 Hotel | Access Scaffold |  | INDEPENDENT | 1.8 | 1.3 | 3.5 | 1 | 2.5 |  |  | 4.5 | m2-LxH | OFF HIRED | 2022-06-06 | 2022-08-18 | 100% |  | 10.5714 | 14 |  | 63 | 0 | 44.1 | 18.9 | 0 | 63 | 63 | 0
| 4 | 156 | 12152 | 7559 |  | Level 3 Hotel | Access Scaffold |  | INDEPENDENT | 1.3 | 1.2 | 3.5 | 1 | 2.5 |  |  | 3.25 | m2-LxH | OFF HIRED | 2022-06-06 | 2022-07-03 | 100% |  | 4 | 14 |  | 45.5 | 0 | 31.85 | 13.65 | 0 | 45.5 | 45.5 | 0
| 4 | 184 | 12181 | 7701 |  | Level 3 Residence | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 6 | 1 | 5 |  |  | 25 | m2-LxH | OFF HIRED | 2022-06-08 | 2022-07-04 | 100% |  | 3.8571 | 14 |  | 350 | 0 | 245 | 105 | 0 | 350 | 350 | 0
| 4 | 154 | 12250 | 7896 |  | Level 3 Residence | Access Scaffold |  | INDEPENDENT | 2.5 | 1.3 | 4 | 1 | 3 |  |  | 7.5 | m2-LxH | OFF HIRED | 2022-06-06 | 2022-09-16 | 100% |  | 14.7143 | 14 | 0.84 | 105 | 6.3 | 73.5 | 31.5 | 92.7 | 197.7 | 197.7 | 0
| 4 | 144 | 12239 | 7900 |  | Level 3 Hotel | Access Scaffold |  | INDEPENDENT | 1.8 | 1.3 | 5 | 1 | 4 |  |  | 7.2 | m2-LxH | OFF HIRED | 2022-06-06 | 2022-09-20 | 100% |  | 15.2857 | 14 | 0.84 | 100.8 | 6.048 | 70.56 | 30.24 | 92.448 | 193.248 | 193.248 | 0
| 4 | 150 | 12247 | 7565 |  | Level 3 Hotel | Access Scaffold |  | INDEPENDENT | 1.8 | 1.8 | 3 | 1 | 2 |  |  | 3.6 | m2-LxH | OFF HIRED | 2022-06-06 | 2022-06-16 | 100% |  | 1.5714 | 18 |  | 64.8 | 0 | 45.36 | 19.44 | 0 | 64.8 | 64.8 | 0
| 4 | 155 | 12151 | 7599 |  | Level 3 Residence | Access Scaffold |  | INDEPENDENT | 5 | 1.8 | 3.5 | 1 | 2.5 |  |  | 12.5 | m2-LxH | OFF HIRED | 2022-06-06 | 2022-07-03 | 100% |  | 4 | 18 | 1.05 | 225 | 13.125 | 157.5 | 67.5 | 52.5 | 277.5 | 277.5 | 0
| 4 | 409 | 12570 | 7896 |  | Level 3 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-06-30 | 2022-09-16 | 100% |  | 11.2857 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 414.75 | 819.75 | 819.75 | 0
| 4 | 430 | 12590 | 7724 |  | Level 3 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2.5 | 1 | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2022-07-03 | 2022-07-15 | 100% |  | 1.8571 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 60.75 | 34.125 | 236.625 | 236.625 | 0
| 4 | 441 | 12600 | 8298 |  | Level 3 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-04 | 2022-12-04 | 100% |  | 22 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 539 | 809 | 809 | 0
| 4 | 447 | 12604 | 6733 |  | Level 3 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-07-06 | 2022-09-28 | 100% |  | 12.1429 | 135 | 12.25 | 540 | 49 | 378 | 162 | 595 | 1135 | 1135 | 0
| 4 | 489 | 12641 | 8126 |  | Level 3 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-07 | 2022-10-19 | 100% |  | 15 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 367.5 | 637.5 | 637.5 | 0
| 4 | 489 | 12641 | 8126 |  | Level 3 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-07 | 2022-10-19 | 100% |  | 15 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 367.5 | 637.5 | 637.5 | 0
| 4 | 473 | 12629 | 8222 |  | Level 3 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-07 | 2022-11-10 | 100% |  | 18.1429 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 444.5 | 714.5 | 714.5 | 0
| 4 | 521 | 12779 | 6739 |  | Level 3 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-15 | 2022-09-28 | 100% |  | 10.8571 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 266 | 536 | 536 | 0
| 4 | 520 | 12728 | 8136 |  | Level 3 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3.5 | 1 | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-07-15 | 2022-10-21 | 100% |  | 14.1429 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 433.125 | 770.625 | 770.625 | 0
| 4 | 442 | 12601 | 7855 |  | Level 3 Hotel | Access Scaffold |  | INDEPENDENT | 8 | 1.3 | 4.5 | 1 | 3.5 |  |  | 28 | m2-LxH | OFF HIRED | 2022-07-05 | 2022-08-29 | 100% |  | 8 | 14 | 0.84 | 392 | 23.52 | 274.4 | 117.6 | 188.16 | 580.16 | 580.16 | 0
| 4 | 439 | 12597 | 7709 |  | Level 3 Hotel | Access Scaffold |  | INDEPENDENT | 6.5 | 1.3 | 3 | 1 | 2 |  |  | 13 | m2-LxH | OFF HIRED | 2022-07-04 | 2022-07-13 | 100% |  | 1.4286 | 14 | 0.84 | 182 | 10.92 | 127.4 | 54.6 | 15.6 | 197.6 | 197.6 | 0
| 4 | 472 | 12628 | 8126 |  | Level 3 Hotel | Access Scaffold |  | INDEPENDENT | 4.3 | 1.3 | 3 | 1 | 2 |  |  | 8.6 | m2-LxH | OFF HIRED | 2022-07-07 | 2022-10-19 | 100% |  | 15 | 14 | 0.84 | 120.4 | 7.224 | 84.28 | 36.12 | 108.36 | 228.76 | 228.76 | 0
| 4 | 475 | 12631 | 8135 |  | Level 3 Hotel | Access Scaffold |  | INDEPENDENT | 4.3 | 1.3 | 3 | 1 | 2 |  |  | 8.6 | m2-LxH | OFF HIRED | 2022-07-07 | 2022-10-21 | 100% |  | 15.2857 | 14 | 0.84 | 120.4 | 7.224 | 84.28 | 36.12 | 110.424 | 230.824 | 230.824 | 0
| 4 |  | 12630 | 8135 |  | Level 3 Hotel | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 3 | 1 | 2 |  |  | 10 | m2-LxH | OFF HIRED | 2022-07-07 | 2022-10-21 | 100% |  | 15.2857 | 14 | 0.84 | 140 | 8.4 | 98 | 42 | 128.4 | 268.4 | 268.4 | 0
| 4 | 507 | 12712 | 8081 |  | Level 3 Hotel | Access Scaffold |  | INDEPENDENT | 10 | 1.3 | 3 | 1 | 2 |  |  | 20 | m2-LxH | OFF HIRED | 2022-07-13 | 2022-10-07 | 100% |  | 12.4286 | 14 | 0.84 | 280 | 16.8 | 196 | 84 | 208.8 | 488.8 | 488.8 | 0
| 4 | 508 | 12715 | 8136 |  | Level 3 Hotel | Access Scaffold |  | INDEPENDENT | 7.5 | 1.3 | 3 | 1 | 2 |  |  | 15 | m2-LxH | OFF HIRED | 2022-07-14 | 2022-10-21 | 100% |  | 14.2857 | 14 | 0.84 | 210 | 12.6 | 147 | 63 | 180 | 390 | 390 | 0
| 4 | 620 | 12838 | 7740 |  | Level 3 Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-24 | 2022-07-29 | 100% |  | 0.85714 | 135 |  | 270 | 0 | 189 | 81 | 0 | 270 | 270 | 0
| 4 | 699 | 12962 | 7896 |  | Level 3 Hotel | Access Scaffold |  | Tower | 2.5 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-06 | 2022-09-16 | 100% |  | 6 | 135 |  | 270 | 0 | 189 | 81 | 0 | 270 | 270 | 0
| 4 | 678 | 12954 | 6731 |  | Level 3 Hotel | Access Scaffold |  | Tower | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-08 | 2022-09-27 | 100% |  | 7.2857 | 135 |  | 270 | 0 | 189 | 81 | 0 | 270 | 270 | 0
| 4 | 696 | 12900 | 7891 |  | Level 3 Hotel | Access Scaffold |  | Tower | 2.5 | 2.5 | 9 | 1 | 8 |  |  | 8 | rm | OFF HIRED | 2022-08-09 | 2022-09-15 | 100% |  | 5.4286 | 135 |  | 1080 | 0 | 756 | 324 | 0 | 1080 | 1080 | 0
| 4 | 773 | 13035 | 7841 |  | Level 3 Residence | Access Scaffold |  | Tower | 1.8 | 1.3 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-08-19 | 2022-08-22 | 100% |  | 0.57143 | 135 |  | 540 | 0 | 378 | 162 | 0 | 540 | 540 | 0
| 4 | 598 | 12818 | 8170 |  | Level 3 Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-26 | 2022-10-29 | 100% |  | 13.7143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 336 | 606 | 606 | 0
| 4 | 807 | 13069 | 7894 |  | Level 3 Residence | Access Scaffold |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-24 | 2022-09-15 | 100% |  | 3.2857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 80.5 | 350.5 | 350.5 | 0
| 4 | 787 | 13048 | 7894 |  | Level 3 Residence | Access Scaffold |  | Independent | 4 | 1.3 | 2 |  | 2 |  |  | 8 | m2-LxH | OFF HIRED | 2022-08-22 | 2022-09-15 | 100% |  | 3.5714 | 14 | 0.84 | 112 | 6.72 | 78.4 | 33.6 | 24 | 136 | 136 | 0
| 4 | 788 | 13048 | 7894 |  | Level 3 Residence | Access Scaffold |  | Independent | 7 | 1.3 | 2 |  | 2 |  |  | 14 | m2-LxH | OFF HIRED | 2022-08-22 | 2022-09-15 | 100% |  | 3.5714 | 14 | 0.84 | 196 | 11.76 | 137.2 | 58.8 | 42 | 238 | 238 | 0
| 4 |  | 12080 | 7597 |  | Level 3 Residence | Access Scaffold |  | INDEPENDENT | 2.5 | 1.3 | 3 | 1 | 2 |  |  | 5 | m2-LxH | OFF HIRED | 2022-05-18 | 2022-07-06 | 100% |  | 7.1429 | 14 |  | 70 | 0 | 49 | 21 | 0 | 70 | 70 | 0
| 4 |  | 12080 | 7597 |  | Level 3 Residence | Access Scaffold |  | INDEPENDENT | 2.5 | 1.3 | 2 | 1 | 1 |  |  | 2.5 | m2-LxH | OFF HIRED | 2022-05-18 | 2022-07-06 | 100% |  | 7.1429 | 14 |  | 35 | 0 | 24.5 | 10.5 | 0 | 35 | 35 | 0
| 4 | 181 | 12182 | 7566 |  | Leevl 3 Residence | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 3 | 1 | 2 |  |  | 8 | m2-LxH | OFF HIRED | 2022-06-08 | 2022-06-19 | 100% |  | 1.7143 | 14 |  | 112 | 0 | 78.4 | 33.6 | 0 | 112 | 112 | 0
| 4 | 519 | 12727 | 7887 |  | Level 3 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3.5 | 1 | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-07-14 | 2022-09-14 | 100% |  | 9 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 275.625 | 613.125 | 613.125 | 0
| 4 | 589 | 12807 | 6745 |  | Level 3 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-25 | 2022-09-30 | 100% |  | 9.7143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 238 | 508 | 508 | 0
| 4 | 1005 | 13389 | 8470 |  | Level 3 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 2.5 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-20 | 2022-12-26 | 100% |  | 14 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 343 | 613 | 613 | 0
| 4 | 1030 | 13467 |  |  | Level 3 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 2 |  | 2 |  |  | 12.5 | m3 | ON HIRE | 2022-09-23 |  | 100% |  | 22.7143 | 7.5 | 0.7 | 93.75 | 8.75 | 65.625 | 0 | 198.75 | 264.375 | 229.375 | 35 |  |  | #VALUE! | 65.625 | #VALUE! | #VALUE!
| 4 | 1200 | 13686 | 8132 |  | Level 3 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-10-13 | 2022-10-20 | 100% |  | 1.1429 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 28 | 298 | 298 | 0
| 4 | 1199 | 13685 | 8126 |  | Level 3 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-10-13 | 2022-10-19 | 100% |  | 1 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 24.5 | 294.5 | 294.5 | 0
| 4 | 1171 | 13656 | 8135 |  | Level 3 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-10-10 | 2022-10-21 | 100% |  | 1.7143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 42 | 312 | 312 | 0
| 4 | 1098 | 13531 | 8081 |  | Level 3 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-30 | 2022-10-07 | 100% |  | 1.1429 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 28 | 298 | 298 | 0
| 4 | 1224 | 13762 | 8222 |  | Level 3 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-10-15 | 2022-11-10 | 100% |  | 3.8571 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 94.5 | 364.5 | 364.5 | 0
| 4 | 1169 | 13654 | 8256 |  | Level 3 Hotel | Access Scaffold |  | Independent | 5 | 1.3 | 2 |  | 2 |  |  | 10 | m2-LxH | OFF HIRED | 2022-10-10 | 2022-11-19 | 100% |  | 5.8571 | 14 | 0.84 | 140 | 8.4 | 98 | 42 | 49.2 | 189.2 | 189.2 | 0
| 4 | 1212 | 13698 | 8126 |  | Level 3 Hotel | Access Scaffold |  | Independent | 6.3 | 1.3 | 2 |  | 2 |  |  | 12.6 | m2-LxH | OFF HIRED | 2022-10-15 | 2022-10-19 | 100% |  | 0.71429 | 14 | 0.84 | 176.4 | 10.584 | 123.48 | 52.92 | 7.56 | 183.96 | 183.96 | 0
| 4 | 1170 | 13655 | 8136 |  | Level 3 Hotel | Access Scaffold |  | Independent | 10 | 1.3 | 2 |  | 2 |  |  | 20 | m2-LxH | OFF HIRED | 2022-10-10 | 2022-10-21 | 100% |  | 1.7143 | 14 | 0.84 | 280 | 16.8 | 196 | 84 | 28.8 | 308.8 | 308.8 | 0
| 4 | 1225 | 13763 | 8222 |  | Level 3 Residence | Birdcage Scaffold |  | Birdcage | 9.3 | 2.5 | 2.5 |  | 2.5 |  |  | 58.125 | m3 | OFF HIRED | 2022-10-16 | 2022-11-10 | 100% |  | 3.7143 | 7.5 | 0.7 | 435.9375 | 40.6875 | 305.1562 | 130.7812 | 151.125 | 587.0625 | 587.0625 | 0
| 4 | 1247 | 13785 | 8223 |  | Level 3 Residence | Birdcage Scaffold |  | Birdcage | 6.8 | 2.5 | 2 |  | 2 |  |  | 34 | m3 | OFF HIRED | 2022-10-19 | 2022-11-11 | 100% |  | 3.4286 | 7.5 | 0.7 | 255 | 23.8 | 178.5 | 76.5 | 81.6 | 336.6 | 336.6 | 0
| 4 | 1425 | 13913 | 8445 |  | Level 3 Residence | HEAVY DUTY TOWER |  | Tower | 1 | 0.6 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-11-12 | 2023-01-20 | 100% |  | 10 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 245 | 515 | 515 | 0
| 4 | 1491 | 13978 | 8281 |  | Level 3 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1 | 1 |  | 1 |  |  | 1 | rm | OFF HIRED | 2022-11-24 | 2022-11-27 | 100% |  | 0.57143 | 135 | 12.25 | 135 | 12.25 | 94.5 | 40.5 | 7 | 142 | 142 | 0
| 5 | 356 | 12512 | 8148 |  | Level 1 Hotel | Access Scaffold |  | INDEPENDENT | 7.5 | 1.3 | 3 | 1 | 2 |  |  | 15 | m2-LxH | OFF HIRED | 2022-06-24 | 2022-10-25 | 100% |  | 17.7143 | 14 |  | 210 | 0 | 147 | 63 | 0 | 210 | 210 | 0
| 5 | 171 | 12168 | 7600 |  | Level 1 Hotel | Access Scaffold |  | INDEPENDENT | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 3.6 | m2-LxH | OFF HIRED | 2022-06-08 | 2022-07-05 | 100% |  | 4 | 14 | 0.84 | 50.4 | 3.024 | 35.28 | 15.12 | 12.096 | 62.496 | 62.496 | 0
| 5 | 170 | 12167 | 6720 |  | Level 1 Hotel | Access Scaffold |  | INDEPENDENT | 1.8 | 1.8 | 3 | 1 | 2 |  |  | 3.6 | m2-LxH | OFF HIRED | 2022-06-08 | 2022-09-26 | 100% |  | 15.8571 | 18 | 1.05 | 64.8 | 3.78 | 45.36 | 19.44 | 59.94 | 124.74 | 124.74 | 0
| 5 | 593 | 12811 | 8126 |  | Level 1 Hotel | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 3 | 1 | 2 |  |  | 8 | m2-LxH | OFF HIRED | 2022-07-26 | 2022-10-19 | 100% |  | 12.2857 | 14 | 0.84 | 112 | 6.72 | 78.4 | 33.6 | 82.56 | 194.56 | 194.56 | 0
| 5 | 596 | 12816 | 7749 |  | Level 1 Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-26 | 2022-08-03 | 100% |  | 1.2857 | 135 |  | 270 | 0 | 189 | 81 | 0 | 270 | 270 | 0
| 5 | 596 | 12816 | 7749 |  | Level 1 Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-26 | 2022-08-03 | 100% |  | 1.2857 | 135 |  | 270 | 0 | 189 | 81 | 0 | 270 | 270 | 0
| 5 | 781 | 13041 | 7900 |  | Level 1 Hotel | Access Scaffold |  | Tower | 2.5 | 1.3 | 2 | 0 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-20 | 2022-09-20 | 100% |  | 4.5714 | 135 |  | 270 | 0 | 189 | 81 | 0 | 270 | 270 | 0
| 5 | 597 | 12817 | 8182 |  | Level 1 Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-26 | 2022-10-31 | 100% |  | 14 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 343 | 613 | 613 | 0
| 5 | 810 | 13073 | 6711 |  | Level 1 Hotel | Access Scaffold |  | Tower | 1.8 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-24 | 2022-09-23 | 100% |  | 4.4286 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 108.5 | 378.5 | 378.5 | 0
| 5 | 821 | 13090 | 7900 |  | Level 1 Hotel | Access Scaffold |  | Independent | 4 | 1.3 | 3.5 |  | 3.5 |  |  | 14 | m2-LxH | OFF HIRED | 2022-08-25 | 2022-09-20 | 100% |  | 3.8571 | 14 | 0.84 | 196 | 11.76 | 137.2 | 58.8 | 45.36 | 241.36 | 241.36 | 0
| 5 | 963 | 13338 | 6733 |  | Level 1 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-15 | 2022-09-28 | 100% |  | 2 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 49 | 319 | 319 | 0
| 5 | 1284 | 13723 | 8155 |  | Level 1 Hotel | HEAVY DUTY TOWER |  | Tower | 2 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-10-24 | 2022-10-27 | 100% |  | 0.57143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 14 | 284 | 284 | 0
| 5 | 1302 | 13740 | 8203 |  | Level 1Hotel | Access Scaffold |  | INDEPENDENT | 9.5 | 1.3 | 2 |  | 2 |  |  | 19 | m2-LxH | OFF HIRED | 2022-10-27 | 2022-11-05 | 100% |  | 1.4286 | 14 | 0.84 | 266 | 15.96 | 186.2 | 79.8 | 22.8 | 288.8 | 288.8 | 0
| 6 | 384 | 12543 | 6725 |  | Level 4 Hotel | Access Scaffold |  | INDEPENDENT | 27 | 1.3 | 3.5 | 1 | 2.5 |  |  | 67.5 | m2-LxH |  | 2022-06-28 |  | 100% |  | 0 | 14 |  | 945 | 0 | 661.5 | 0 | 0 | 661.5 | 661.5 | 0
| 6 |  | 12132 | 7821 |  | Level 4 Hotel | Access Scaffold |  | INDEPENDENT | 3 | 1.3 | 3 | 1 | 2 |  |  | 6 | m2-LxH | OFF HIRED | 2022-05-30 | 2022-08-10 | 100% |  | 10.4286 | 14 |  | 84 | 0 | 58.8 | 25.2 | 0 | 84 | 84 | 0
| 6 |  | 12130 | 7562 |  | Level 4 Hotel | Access Scaffold |  | INDEPENDENT | 1.6 | 1.3 | 3 | 1 | 2 |  |  | 3.2 | m2-LxH | OFF HIRED | 2022-05-30 | 2022-06-05 | 100% |  | 1 | 14 |  | 44.8 | 0 | 31.36 | 13.44 | 0 | 44.8 | 44.8 | 0
| 6 | A08 | 12219 | 7811 |  | Level 4 Hotel | Access Scaffold |  | INDEPENDENT | 1.8 | 1.3 | 4 | 1 | 3 |  |  | 5.4 | m2-LxH | OFF HIRED | 2022-06-03 | 2022-08-06 | 100% |  | 9.2857 | 14 |  | 75.6 | 0 | 52.92 | 22.68 | 0 | 75.6 | 75.6 | 0
| 6 | A09 | 12219 | 7811 |  | Level 4 Hotel | Access Scaffold |  | INDEPENDENT | 1.8 | 1.3 | 4 | 1 | 3 |  |  | 5.4 | m2-LxH | OFF HIRED | 2022-06-03 | 2022-08-06 | 100% |  | 9.2857 | 14 |  | 75.6 | 0 | 52.92 | 22.68 | 0 | 75.6 | 75.6 | 0
| 6 | A09 | 12220 | 7596 |  | Level 4 Hotel | Access Scaffold |  | INDEPENDENT | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2.6 | m2-LxH | OFF HIRED | 2022-06-03 | 2022-07-03 | 100% |  | 4.4286 | 14 |  | 36.4 | 0 | 25.48 | 10.92 | 0 | 36.4 | 36.4 | 0
| 6 | A17 | 12234 | 7565 |  | Level 4 Hotel | Access Scaffold |  | INDEPENDENT | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 3.6 | m2-LxH | OFF HIRED | 2022-06-05 | 2022-06-16 | 100% |  | 1.7143 | 14 | 0.84 | 50.4 | 3.024 | 35.28 | 15.12 | 5.184 | 55.584 | 55.584 | 0
| 6 | 255 | 12369 | 7593 |  | Level 4 Hotel | Access Scaffold |  | INDEPENDENT | 25 | 1.3 | 4 | 1 | 3 |  |  | 75 | m2-LxH | OFF HIRED | 2022-06-16 | 2022-06-29 | 100% |  | 2 | 14 | 0.84 | 1050 | 63 | 735 | 315 | 126 | 1176 | 1176 | 0
| 6 | 376 | 12533 | 7719 |  | Level 4 Hotel | Access Scaffold |  | INDEPENDENT | 12 | 1.3 | 3 | 1 | 2 |  |  | 24 | m2-LxH | OFF HIRED | 2022-06-28 | 2022-07-15 | 100% |  | 2.5714 | 14 | 0.84 | 336 | 20.16 | 235.2 | 100.8 | 51.84 | 387.84 | 387.84 | 0
| 6 | 145 | 12240 | 7713 |  | Level 4 Hotel | Access Scaffold |  | INDEPENDENT | 7 | 1.8 | 3 | 1 | 2 |  |  | 14 | m2-LxH | OFF HIRED | 2022-06-06 | 2022-07-14 | 100% |  | 5.5714 | 18 |  | 252 | 0 | 176.4 | 75.6 | 0 | 252 | 252 | 0
| 6 | 408 | 12569 | 7738 |  | Level 4 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-06-30 | 2022-07-26 | 100% |  | 3.8571 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 94.5 | 364.5 | 364.5 | 0
| 6 | 408 | 12614 | 7824 |  | Level 4 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-07 | 2022-08-16 | 100% |  | 5.8571 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 143.5 | 413.5 | 413.5 | 0
| 6 | 446 | 12603 | 8234 |  | Level 4 Hotel | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 6 | 1 | 5 |  |  | 20 | m2-LxH | OFF HIRED | 2022-07-04 | 2022-11-09 | 100% |  | 18.4286 | 14 | 0.84 | 280 | 16.8 | 196 | 84 | 309.6 | 589.6 | 589.6 | 0
| 6 | 81 | 12579 | 8151 |  | Level 4 Hotel | Cantiliver |  | Cantiliver | 24.5 | 0.6 |  |  |  | 1 |  | 14.7 | m2-LxW | OFF HIRED | 2022-07-01 | 2022-10-27 | 100% |  | 17 | 36.5 | 3.15 | 536.55 | 46.305 | 375.585 | 160.965 | 787.185 | 1323.735 | 1323.735 | 0
| 6 | 81 | 12737 | 8196 |  | Level 4 Hotel | Cantiliver |  | Cantiliver | 28 | 1 |  |  |  | 1 |  | 28 | m2-LxW | OFF HIRED | 2022-07-12 | 2022-11-05 | 100% |  | 16.7143 | 36.5 | 3.15 | 1022 | 88.2 | 715.4 | 306.6 | 1474.2 | 2496.2 | 2496.2 | 0
| 6 | 674 | 12891 | 8155 |  | Level 4 Hotel | Access Scaffold |  | Tower | 1.3 | 1 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-06 | 2022-10-27 | 100% |  | 11.8571 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 290.5 | 560.5 | 560.5 | 0
| 6 | 237 | 12352 | 7577 |  | Level 4 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-06-15 | 2022-06-24 | 100% |  | 1.4286 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 35 | 305 | 305 | 0
| 6 | 272 | 12386 | 6710 |  | Level 4 Residance | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-06-17 | 2022-09-15 | 100% |  | 13 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 477.75 | 882.75 | 882.75 | 0
| 6 | 158 | 12155 | 7599 |  | Level 4 Residence | Access Scaffold |  | INDEPENDENT | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 3.6 | m2-LxH | OFF HIRED | 2022-06-07 | 2022-07-03 | 100% |  | 3.8571 | 14 | 0.84 | 50.4 | 3.024 | 35.28 | 15.12 | 11.664 | 62.064 | 62.064 | 0
| 6 | 289 | 12395 | 7595 |  | Level 4 residence | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 4 | 1 | 3 |  |  | 15 | m2-LxH | OFF HIRED | 2022-06-19 | 2022-06-30 | 100% |  | 1.7143 | 14 | 0.84 | 210 | 12.6 | 147 | 63 | 21.6 | 231.6 | 231.6 | 0
| 6 | 141 | 12153 | 7564 |  | Level 4 Residence | Access Scaffold |  | INDEPENDENT | 5 | 1.8 | 3.5 | 1 | 2.5 |  |  | 12.5 | m2-LxH | OFF HIRED | 2022-06-06 | 2022-06-17 | 100% |  | 1.7143 | 18 |  | 225 | 0 | 157.5 | 67.5 | 0 | 225 | 225 | 0
| 6 | 326 | 12423 |  |  | Level 4 residence | Birdcage Scaffold |  | Birdcage | 9 | 6 | 9 | 1 | 8 |  |  | 432 | m3 | ON HIRE | 2022-06-22 |  | 100% |  | 36 | 7.5 | 0.7 | 3240 | 302.4 | 2268 | 0 | 10886.4 | 6631.2 | 6631.2 | 0
| 6 |  | 12423 | 7819 |  | PARTIAL DISMANTEL | Birdcage Scaffold |  | Birdcage | 9 | 3.5 | 9 | 1 | 8 |  |  | 252 | m3 | OFF HIRED | 2022-08-25 | 2022-09-30 | 100% |  | -5.2857 | 7.5 | 0.7 | 1890 | 176.4 |  | 567 | -932.4 | -365.4 | -365.4 | 0
| 6 |  | 12423 | 8234 |  | PARTIAL off Hire From HOC12423 (Balance M3 To Charge ) |  |  |  | 9 | 2.5 | 9 | 1 | 8 |  |  | 180 | m3 | OFF HIRED | 2022-10-01 | 2022-11-09 | 100% |  | 5.7143 | 7.5 | 0.7 | 1350 | 126 |  | 405 | 720 | 1125 | 1125 | 0
| 6 | 347 | 12526 | 7817 |  | Level 4 residence | Birdcage Scaffold |  | Birdcage | 18.1 | 6.5 | 9 | 1 | 8 |  |  | 941.2 | m3 | ON HIRE | 2022-06-26 |  | 100% |  | 35.4286 | 7.5 | 0.7 | 7059 | 658.84 | 4941.3 | 0 | 23341.76 | 14070.94 | 14070.94 | 0
| 6 |  | 12526 | 7817 |  | PARTIAL DISMANTEL | Birdcage Scaffold |  | Birdcage | 18.1 | 4 | 9 | 1 | 8 |  |  | 579.2 | m3 | OFF HIRED | 2022-08-26 | 2022-09-30 | 100% |  | -5.1429 | 7.5 | 0.7 | 4344 | 405.44 |  | 1303.2 | -2085.12 | -781.92 | -781.92 | 0
| 6 |  | 12526 | 8190 |  | PARTIAL off Hire From HOC12526(Balance M3 To Charge ) |  |  |  | 18.1 | 2.5 | 9 | 1 | 8 |  |  | 362 | m3 | OFF HIRED | 2022-10-01 | 2022-11-03 | 100% |  | 4.8571 | 7.5 | 0.7 | 2715 | 253.4 |  | 814.5 | 1230.8 | 2045.3 | 2045.3 | 0
| 6 | 346 | 12525 | 6710 |  | Level 4 residence | Birdcage Scaffold |  | Birdcage | 17.5 | 7.5 | 9 | 1 | 8 |  |  | 1050 | m3 | OFF HIRED | 2022-06-26 | 2022-09-15 | 100% |  | 11.7143 | 7.5 | 0.7 | 7875 | 735 | 5512.5 | 2362.5 | 8610 | 16485 | 16485 | 0
| 6 | 208 | 12305 | 7824 |  | Level 4 Residence | Boarded Lift |  | Board Lift | 13 | 1.3 |  |  |  | 1 |  | 16.9 | m2-LxW | OFF HIRED | 2022-06-10 | 2022-08-16 | 100% |  | 9.7143 | 7.5 | 1.05 | 126.75 | 17.745 | 88.725 | 38.025 | 172.38 | 299.13 | 299.13 | 0
| 6 |  | 12305 | 7824 |  | Level 4 Residence | Boarded Lift |  | Board Lift | 13 | 1.3 |  |  |  | 1 |  | 16.9 | m2-LxW | OFF HIRED | 2022-06-10 | 2022-08-16 | 100% |  | 9.7143 | 7.5 | 1.05 | 126.75 | 17.745 | 88.725 | 38.025 | 172.38 | 299.13 | 299.13 | 0
| 6 |  | 12305 | 7824 |  | Level 4 Residence | Boarded Lift |  | Board Lift | 16 | 1.3 |  |  |  | 1 |  | 20.8 | m2-LxW | OFF HIRED | 2022-06-10 | 2022-08-16 | 100% |  | 9.7143 | 7.5 | 1.05 | 156 | 21.84 | 109.2 | 46.8 | 212.16 | 368.16 | 368.16 | 0
| 6 |  | 12305 | 7824 |  | Level 4 Residence | Boarded Lift |  | Board Lift | 16 | 1.3 |  |  |  | 1 |  | 20.8 | m2-LxW | OFF HIRED | 2022-06-10 | 2022-08-16 | 100% |  | 9.7143 | 7.5 | 1.05 | 156 | 21.84 | 109.2 | 46.8 | 212.16 | 368.16 | 368.16 | 0
| 6 |  | 12305 | 7824 |  | Level 4 Residence | Boarded Lift |  | Board Lift | 16 | 1.3 |  |  |  | 1 |  | 20.8 | m2-LxW | OFF HIRED | 2022-06-10 | 2022-08-16 | 100% |  | 9.7143 | 7.5 | 1.05 | 156 | 21.84 | 109.2 | 46.8 | 212.16 | 368.16 | 368.16 | 0
| 6 |  | 12305 | 7824 |  | Level 4 Residence | Boarded Lift |  | Board Lift | 16 | 1.3 |  |  |  | 1 |  | 20.8 | m2-LxW | OFF HIRED | 2022-06-10 | 2022-08-16 | 100% |  | 9.7143 | 7.5 | 1.05 | 156 | 21.84 | 109.2 | 46.8 | 212.16 | 368.16 | 368.16 | 0
| 6 | 403 | 12564 | 6733 |  | Level 4 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-06-30 | 2022-09-28 | 100% |  | 13 | 135 | 12.25 | 540 | 49 | 378 | 162 | 637 | 1177 | 1177 | 0
| 6 | 423 | 12583 | 7723 |  | Level 4 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 0.6 | 6 | 1 | 5 |  |  | 5 | rm | OFF HIRED | 2022-07-03 | 2022-07-17 | 100% |  | 2.1429 | 135 | 12.25 | 675 | 61.25 | 472.5 | 202.5 | 131.25 | 806.25 | 806.25 | 0
| 6 | 560 | 12773 | 7855 |  | Level 4 to 5 Residance | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-21 | 2022-08-29 | 100% |  | 5.7143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 140 | 410 | 410 | 0
| 6 | 560 | 12773 | 7855 |  | Level 4 to 5 Residance | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-21 | 2022-08-29 | 100% |  | 5.7143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 140 | 410 | 410 | 0
| 6 | 460 | 12615 | 7887 |  | Level 4 Residance | Access Scaffold |  | INDEPENDENT | 6 | 1 | 2 | 1 | 1 |  |  | 6 | m2-LxH | OFF HIRED | 2022-07-07 | 2022-09-14 | 100% |  | 10 | 14 | 0.84 | 84 | 5.04 | 58.8 | 25.2 | 50.4 | 134.4 | 134.4 | 0
| 6 | 480 | 12633 | 7890 |  | Level 4 Residence | Boarded Lift |  | Board Lift | 10 | 1.3 |  |  |  | 1 |  | 13 | m2-LxW | OFF HIRED | 2022-07-04 | 2022-09-15 | 100% |  | 10.5714 | 7.5 | 1.05 | 97.5 | 13.65 | 68.25 | 29.25 | 144.3 | 241.8 | 241.8 | 0
| 6 | 480 | 12633 | 7890 |  | Level 4 Residence | Boarded Lift |  | Board Lift | 10 | 1.3 |  |  |  | 1 |  | 13 | m2-LxW | OFF HIRED | 2022-07-04 | 2022-09-15 | 100% |  | 10.5714 | 7.5 | 1.05 | 97.5 | 13.65 | 68.25 | 29.25 | 144.3 | 241.8 | 241.8 | 0
| 6 | 480 | 12633 | 7890 |  | Level 4 Residence | Boarded Lift |  | Board Lift | 10 | 1.3 |  |  |  | 1 |  | 13 | m2-LxW | OFF HIRED | 2022-07-04 | 2022-09-15 | 100% |  | 10.5714 | 7.5 | 1.05 | 97.5 | 13.65 | 68.25 | 29.25 | 144.3 | 241.8 | 241.8 | 0
| 6 | 480 | 12633 | 7890 |  | Level 4 Residence | Boarded Lift |  | Board Lift | 10 | 1.3 |  |  |  | 1 |  | 13 | m2-LxW | OFF HIRED | 2022-07-04 | 2022-09-15 | 100% |  | 10.5714 | 7.5 | 1.05 | 97.5 | 13.65 | 68.25 | 29.25 | 144.3 | 241.8 | 241.8 | 0
| 6 | 480 | 12633 | 7890 |  | Level 4 Residence | Boarded Lift |  | Board Lift | 10 | 1.3 |  |  |  | 1 |  | 13 | m2-LxW | OFF HIRED | 2022-07-04 | 2022-09-15 | 100% |  | 10.5714 | 7.5 | 1.05 | 97.5 | 13.65 | 68.25 | 29.25 | 144.3 | 241.8 | 241.8 | 0
| 6 | 480 | 12633 | 7890 |  | Level 4 Residence | Boarded Lift |  | Board Lift | 10 | 1.3 |  |  |  | 1 |  | 13 | m2-LxW | OFF HIRED | 2022-07-04 | 2022-09-15 | 100% |  | 10.5714 | 7.5 | 1.05 | 97.5 | 13.65 | 68.25 | 29.25 | 144.3 | 241.8 | 241.8 | 0
| 6 | 480 | 12633 | 7890 |  | Level 4 Residence | Boarded Lift |  | Board Lift | 10 | 1.3 |  |  |  | 1 |  | 13 | m2-LxW | OFF HIRED | 2022-07-04 | 2022-09-15 | 100% |  | 10.5714 | 7.5 | 1.05 | 97.5 | 13.65 | 68.25 | 29.25 | 144.3 | 241.8 | 241.8 | 0
| 6 | 347 | 12839 | 8263 |  | Level 4 Residence | Birdcage Scaffold |  | Birdcage | 6.5 | 6 | 7 | 1 | 6 |  |  | 234 | m3 | ON HIRE | 2022-07-26 |  | 100% |  | 31.1429 | 7.5 | 0.7 | 1755 | 163.8 | 1228.5 | 0 | 5101.2 | 2796.3 | 2796.3 | 0
| 6 |  | 12839 | 7818 |  | PARTIAL DISMANTEL | Birdcage Scaffold |  | Birdcage | 6.5 | 3.5 | 7 | 1 | 6 |  |  | 136.5 | m3 | OFF HIRED | 2022-08-25 | 2022-09-30 | 100% |  | -5.2857 | 7.5 | 0.7 | 1023.75 | 95.55 |  | 307.125 | -505.05 | -197.925 | -197.925 | 0
| 6 |  | 12839 | 8263 |  | PARTIAL off Hire From HOC12839(Balance M3 To Charge ) |  |  |  | 6.5 | 2.5 | 7 | 1 | 6 |  |  | 97.5 | m3 | OFF HIRED | 2022-10-01 | 2022-11-22 | 100% |  | 7.5714 | 7.5 | 0.7 | 731.25 | 68.25 |  | 219.375 | 516.75 | 736.125 | 736.125 | 0
| 6 | 954 | 13329 | 4749 |  | Level 4 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.8 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-14 | 2022-10-01 | 100% |  | 2.5714 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 63 | 333 | 333 | 0
| 6 | 723 | 13006 | 8628 |  | Zone 12 Level 4 Residence | Chain Pully |  | Independent | 13 | 1.3 | 9 | 1 | 8 |  |  | 104 | m2-LxH | OFF HIRED | 2022-08-09 | 2023-02-02 | 100% |  | 25.4286 | 14 | 0.84 | 1456 | 87.36 | 1019.2 | 436.8 | 2221.44 | 3677.44 | 3215.68 | 461.76 |  |  | #VALUE! | 1974.7 | #VALUE! | #VALUE!
| 6 |  |  | 8421 |  | PARTIAL DISMANTEL |  |  |  | 7 | 1.3 | 9 | 1 | 8 |  |  | 56 | m2-LxH | OFF HIRED | 2023-01-11 | 2023-02-02 | 100% |  | -3.2857 | 14 | 0.84 | 784 | 47.04 |  | 0 | -154.56 | -154.56 | 94.08 | -248.64 |  |  | #VALUE! | 0 | #VALUE! | #VALUE!
| 6 | 723 | 13006 | 8628 |  | Zone 12 Level 4 Residence | Chain Pully |  | Buttress | 13 | 2.5 | 9 | 1 | 8 |  |  | 260 | m3 | OFF HIRED | 2022-08-09 | 2023-02-02 | 100% |  | 25.4286 | 5.25 | 0.35 | 1365 | 91 | 955.5 | 409.5 | 2314 | 3679 | 3243.5 | 435.5 |  |  | #VALUE! | 1974.7 | #VALUE! | #VALUE!
| 6 |  |  | 8421 |  | PARTIAL DISMANTEL |  |  |  | 7 | 2.5 | 9 | 1 | 8 |  |  | 140 | m3 | OFF HIRED | 2023-01-11 | 2023-02-02 | 100% |  | -3.2857 | 5.25 | 0.35 | 735 | 49 |  | 0 | -161 | -161 | 73.5 | -234.5 |  |  | #VALUE! | 0 | #VALUE! | #VALUE!
| 6 | 723 | 13010 | 8612 |  | Zone 9 Level 4 Residence | Chain Pully |  | Independent | 6 | 1.3 | 9 | 1 | 8 |  |  | 48 | m2-LxH | OFF HIRED | 2022-08-10 | 2023-01-26 | 100% |  | 24.2857 | 14 | 0.84 | 672 | 40.32 | 470.4 | 201.6 | 979.2 | 1651.2 | 1651.2 | 0
| 6 | 723 | 13010 | 8612 |  | Zone 9 Level 4 Residence | Chain Pully |  | Buttress | 6 | 2.5 | 9 | 1 | 8 |  |  | 120 | m3 | OFF HIRED | 2022-08-10 | 2023-01-26 | 100% |  | 24.2857 | 5.25 | 0.35 | 630 | 42 | 441 | 189 | 1020 | 1650 | 1650 | 0
| 6 | 724 | 13008 | 8596 |  | Zone 9 Level 4 Residence | Chain Pully |  | Independent | 45 | 1.3 | 9 | 1 | 8 |  |  | 360 | m2-LxH | OFF HIRED | 2022-08-11 | 2023-02-24 | 100% |  | 28.2857 | 14 | 0.84 | 5040 | 302.4 | 3528 | 1512 | 8553.6 | 13593.6 | 11044.8 | 2548.8 |  |  | #VALUE! | 6835.5 | #VALUE! | #VALUE!
| 6 |  |  | 8467 |  | PARTIAL DISMANTEL |  |  |  | 13 | 1.3 | 9 | 1 | 8 |  |  | 104 | m2-LxH | OFF HIRED | 2022-12-26 | 2023-02-24 | 100% |  | -8.7143 | 14 | 0.84 | 1456 | 87.36 |  | 0 | -761.28 | -761.28 | -24.96 | -736.32 |  |  | #VALUE! | 0 | #VALUE! | #VALUE!
| 6 |  |  | 8402 |  | PARTIAL DISMANTEL |  |  |  | 14.5 | 1.3 | 9 | 1 | 8 |  |  | 116 | m2-LxH | OFF HIRED | 2023-01-02 | 2023-02-24 | 100% |  | -7.7143 | 14 | 0.84 | 1624 | 97.44 |  | 0 | -751.68 | -751.68 | 69.6 | -821.28 |  |  | #VALUE! | 0 | #VALUE! | #VALUE!
| 6 | 724 | 13008 | 8596 |  | Zone 9 Level 4 Residence | Chain Pully |  | Buttress | 45 | 2.5 | 9 | 1 | 8 |  |  | 900 | m3 | OFF HIRED | 2022-08-11 | 2023-02-24 | 100% |  | 28.2857 | 5.25 | 0.35 | 4725 | 315 | 3307.5 | 1417.5 | 8910 | 13635 | 11137.5 | 2497.5 |  |  | #VALUE! | 6835.5 | #VALUE! | #VALUE!
| 6 |  |  | 8467 |  | PARTIAL DISMANTEL |  |  |  | 13 | 2.5 | 9 | 1 | 8 |  |  | 260 | m3 | OFF HIRED | 2022-12-26 | 2023-02-24 | 100% |  | -8.7143 | 5.25 | 0.35 | 1365 | 91 |  | 0 | -793 | -793 | -71.5 | -721.5 |  |  | #VALUE! | 0 | #VALUE! | #VALUE!
| 6 |  |  | 8402 |  | PARTIAL DISMANTEL |  |  |  | 14.5 | 2.5 | 9 | 1 | 8 |  |  | 290 | m3 | OFF HIRED | 2023-01-02 | 2023-02-24 | 100% |  | -7.7143 | 5.25 | 0.35 | 1522.5 | 101.5 |  | 0 | -783 | -783 | 21.75 | -804.75 |  |  | #VALUE! | 0 | #VALUE! | #VALUE!
| 6 | 724A | 13009 | 8405 |  | Level 4 Zone 7 Residence | Chain Pully With Ladder Beam |  | Independent | 3 | 24 |  |  |  | 1 |  | 72 | m2-LxW | OFF HIRED | 2022-08-11 | 2023-01-02 | 100% |  | 20.7143 | 81 | 1.82 | 5832 | 131.04 | 4082.4 | 1749.6 | 2714.4 | 8546.4 | 7339.68 | 1206.72 |  |  | #VALUE! | 6804 | #VALUE! | #VALUE!
| 6 |  |  | 8468 |  | PARTIAL DISMANTEL |  |  |  | 3 | 6 |  |  | 0 | 1 |  | 18 | m2-LxW | OFF HIRED | 2022-12-26 | 2023-01-02 | 100% |  | -1.1429 | 81 | 1.82 | 1458 | 32.76 |  | 0 | -37.44 | -37.44 | 264.24 | -301.68 |  |  | #VALUE! | 0 | #VALUE! | #VALUE!
| 6 | 724A | 13009 | 8405 |  | Level 4 Zone 7 Residence | Chain Pully With Ladder Beam |  | Independent | 6 | 8 |  |  |  | 1 |  | 48 | m2-LxW | OFF HIRED | 2022-08-11 | 2023-01-02 | 100% |  | 20.7143 | 81 | 1.82 | 3888 | 87.36 | 2721.6 | 1166.4 | 1809.6 | 5697.6 | 4893.12 | 804.48 |  |  | #VALUE! | 6804 | #VALUE! | #VALUE!
| 6 |  |  | 8468 |  | PARTIAL DISMANTEL |  |  |  | 6 | 2 |  |  | 0 | 1 |  | 12 | m2-LxW | OFF HIRED | 2022-12-26 | 2023-01-02 | 100% |  | -1.1429 | 81 | 1.82 | 972 | 21.84 |  | 0 | -24.96 | -24.96 | 176.16 | -201.12 |  |  | #VALUE! | 0 | #VALUE! | #VALUE!
| 6 | 725 A | 13011 | 8437 |  | Level 4 Zone 9 Residence | Chain Pully With Ladder Beam |  | Independent | 3 | 6 |  |  |  | 1 |  | 18 | m2-LxW | OFF HIRED | 2022-08-10 | 2023-01-18 | 100% |  | 23.1429 | 81 | 1.82 | 1458 | 32.76 | 1020.6 | 437.4 | 758.16 | 2216.16 | 2216.16 | 0
| 6 | 725 A | 13011 | 8437 |  | Level 4 Zone 9 Residence | Chain Pully With Ladder Beam |  | Independent | 6 | 2 |  |  |  | 1 |  | 12 | m2-LxW | OFF HIRED | 2022-08-10 | 2023-01-18 | 100% |  | 23.1429 | 81 | 1.82 | 972 | 21.84 | 680.4 | 291.6 | 505.44 | 1477.44 | 1477.44 | 0
| 6 | 723A | 13007 | 8422 |  | Level 4 Zone 12 Residence | Chain Pully With Ladder Beam |  | Independent | 3 | 6 |  |  |  | 1 |  | 18 | m2-LxW | OFF HIRED | 2022-08-09 | 2023-01-11 | 100% |  | 22.2857 | 81 | 1.82 | 1458 | 32.76 | 1020.6 | 437.4 | 730.08 | 2188.08 | 2188.08 | 0
| 6 | 723 A | 13007 | 8422 |  | Level 4 Zone 9 Residence | Chain Pully With Ladder Beam |  | Independent | 6 | 2 |  |  |  | 1 |  | 12 | m2-LxW | OFF HIRED | 2022-08-09 | 2023-01-11 | 100% |  | 22.2857 | 81 | 1.82 | 972 | 21.84 | 680.4 | 291.6 | 486.72 | 1458.72 | 1458.72 | 0
| 6 | 1054 | 13493 | 8089 |  | Level 4 Hotel | Mobile Tower |  | Mobile Tower | 1.8 | 1 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-26 | 2022-10-10 | 100% |  | 2.1429 | 100 | 10.15 | 200 | 20.3 | 140 | 60 | 43.5 | 243.5 | 243.5 | 0
| 6 | 1013 | 13396 | 8172 |  | Level 4 Hotel | Mobile Tower |  | Mobile Tower | 1.8 | 1 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-02 | 2022-10-29 | 100% |  | 8.2857 | 100 | 10.15 | 200 | 20.3 | 140 | 60 | 168.2 | 368.2 | 368.2 | 0
| 6 | 1017 | 13452 | 6749 |  | Level 4 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-09-21 | 2022-10-01 | 100% |  | 1.5714 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 48.125 | 385.625 | 385.625 | 0
| 6 | 1018 | 13453 | 6744 |  | Level 4 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.8 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-09-22 | 2022-09-30 | 100% |  | 1.2857 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 39.375 | 376.875 | 376.875 | 0
| 6 | 256 | 13356 | 6747 |  | Level 04 Residence | Cantiliver |  | Cantiliver | 3 | 1 |  |  |  | 1 |  | 3 | m2-LxW | OFF HIRED | 2022-09-16 | 2022-09-30 | 100% |  | 2.1429 | 36.5 | 3.15 | 109.5 | 9.45 | 76.65 | 32.85 | 20.25 | 129.75 | 129.75 | 0
| 6 | 256 | 13356 | 6747 |  | Level 04 Residence | Cantiliver |  | Cantiliver | 3 | 1 |  |  |  | 1 |  | 3 | m2-LxW | OFF HIRED | 2022-09-16 | 2022-09-30 | 100% |  | 2.1429 | 36.5 | 3.15 | 109.5 | 9.45 | 76.65 | 32.85 | 20.25 | 129.75 | 129.75 | 0
| 6 | 256 | 13356 | 6747 |  | Level 04 Residence | Cantiliver |  | Cantiliver | 3 | 1 |  |  |  | 1 |  | 3 | m2-LxW | OFF HIRED | 2022-09-16 | 2022-09-30 | 100% |  | 2.1429 | 36.5 | 3.15 | 109.5 | 9.45 | 76.65 | 32.85 | 20.25 | 129.75 | 129.75 | 0
| 6 | 1194 | 13679 | 8494 |  | Level 4 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-10-12 | 2023-01-05 | 100% |  | 12.2857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 301 | 571 | 571 | 0
| 6 | 1230 | 13768 | 8234 |  | Level 4 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 2 |  | 2 |  |  | 2.6 | m2-LxH | OFF HIRED | 2022-10-16 | 2022-11-09 | 100% |  | 3.5714 | 14 | 0.84 | 36.4 | 2.184 | 25.48 | 10.92 | 7.8 | 44.2 | 44.2 | 0
| 6 | 1282 | 13721 | 8155 |  | Level 4 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.8 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-10-24 | 2022-10-27 | 100% |  | 0.57143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 14 | 284 | 284 | 0
| 6 | 1062 | 13499 | 8237 |  | Level 4 Residence | Access Scaffold |  | Independent | 5 | 0.6 | 3 |  | 3 |  |  | 15 | m2-LxH | OFF HIRED | 2022-09-26 | 2022-11-15 | 100% |  | 7.2857 | 14 | 0.84 | 210 | 12.6 | 147 | 63 | 91.8 | 301.8 | 301.8 | 0
| 6 | 1067 | 13504 | 8099 |  | Level 4 Hotel | Access Scaffold |  | Independent | 4 | 1 | 2 |  | 2 |  |  | 8 | m2-LxH | OFF HIRED | 2022-09-27 | 2022-10-12 | 100% |  | 2.2857 | 14 | 0.84 | 112 | 6.72 | 78.4 | 33.6 | 15.36 | 127.36 | 127.36 | 0
| 6 | 1067 | 13504 | 8099 |  | Level 4 Hotel | Access Scaffold |  | Independent | 4 | 1 | 2 |  | 2 |  |  | 8 | m2-LxH | OFF HIRED | 2022-09-27 | 2022-10-12 | 100% |  | 2.2857 | 14 | 0.84 | 112 | 6.72 | 78.4 | 33.6 | 15.36 | 127.36 | 127.36 | 0
| 6 | 1067 | 13504 | 8099 |  | Level 4 Hotel | Access Scaffold |  | Independent | 4 | 1 | 2 |  | 2 |  |  | 8 | m2-LxH | OFF HIRED | 2022-09-27 | 2022-10-12 | 100% |  | 2.2857 | 14 | 0.84 | 112 | 6.72 | 78.4 | 33.6 | 15.36 | 127.36 | 127.36 | 0
| 6 | 1178 | 13663 | 8635 |  | Level 4 Hotel | Access Scaffold |  | Independent | 4 | 1 | 2.5 |  | 2.5 |  |  | 10 | m2-LxH | OFF HIRED | 2022-10-10 | 2023-02-05 | 100% |  | 17 | 14 | 0.84 | 140 | 8.4 | 98 | 42 | 142.8 | 282.8 | 234.8 | 48 |  |  | #VALUE! | 98 | #VALUE! | #VALUE!
| 6 | 1177 | 13662 | 8253 |  | Level 4 Hotel | Access Scaffold |  | Independent | 7.5 | 1.3 | 2.5 |  | 2.5 |  |  | 18.75 | m2-LxH | OFF HIRED | 2022-10-10 | 2022-11-18 | 100% |  | 5.7143 | 14 | 0.84 | 262.5 | 15.75 | 183.75 | 78.75 | 90 | 352.5 | 352.5 | 0
| 6 | 1269 | 13707 | 8490 |  | Level 4 To 6 Residence | Access Scaffold |  | Independent | 27 | 1.3 | 1.5 |  | 1.5 |  |  | 40.5 | m2-LxH | OFF HIRED | 2022-10-21 | 2023-01-03 | 100% |  | 10.7143 | 14 | 0.84 | 567 | 34.02 | 396.9 | 170.1 | 364.5 | 931.5 | 931.5 | 0
| 6 | 1401 | 13889 | 8277 |  | Level 4 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-11-10 | 2022-11-26 | 100% |  | 2.4286 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 89.25 | 494.25 | 494.25 | 0
| 6 | 1400 | 13888 | 8277 |  | Level 4 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-11-10 | 2022-11-26 | 100% |  | 2.4286 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 89.25 | 494.25 | 494.25 | 0
| 6 | 1492 | 13979 | 8275 |  | Level 4 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-11-24 | 2022-11-26 | 100% |  | 0.42857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 10.5 | 280.5 | 280.5 | 0
| 6 | 1475 | 13963 | 8612 |  | Level 4 Residence | Access Scaffold |  | INDEPENDENT | 2 | 1.3 | 6 |  | 6 |  |  | 12 | m2-LxH | OFF HIRED | 2022-11-21 | 2023-01-26 | 100% |  | 9.5714 | 14 | 0.84 | 168 | 10.08 | 117.6 | 50.4 | 96.48 | 264.48 | 264.48 | 0
| 6 | 1333 | 13821 | 8244 |  | Level 4 Hotel | Access Scaffold |  | Independent | 3 | 1.8 | 1.75 |  | 1.75 |  |  | 5.25 | m2-LxH | OFF HIRED | 2022-10-31 | 2022-11-16 | 100% |  | 2.4286 | 18 | 1.05 | 94.5 | 5.5125 | 66.15 | 28.35 | 13.3875 | 107.8875 | 107.8875 | 0
| 6 | 1370 | 13858 | 8404 |  | Level 4 Residence | Cantiliver |  | Cantiliver | 56 | 0.6 |  |  |  | 1 |  | 33.6 | m2-LxW | OFF HIRED | 2022-11-04 | 2023-01-02 | 100% |  | 8.5714 | 36.5 | 3.15 | 1226.4 | 105.84 | 858.48 | 367.92 | 907.2 | 2133.6 | 2133.6 | 0
| 6 | 1475 | 13963 | 8612 |  | Level 4 Residence | Cantiliver |  | Cantiliver | 15 | 0.6 |  |  |  | 1 |  | 9 | m2-LxW | OFF HIRED | 2022-11-21 | 2023-01-26 | 100% |  | 9.5714 | 36.5 | 3.15 | 328.5 | 28.35 | 229.95 | 98.55 | 271.35 | 599.85 | 599.85 | 0
| 6 | 1475 | 13963 | 8612 |  | Level 4 Residence | Cantiliver |  | Cantiliver | 15 | 0.6 |  |  |  | 1 |  | 9 | m2-LxW | OFF HIRED | 2022-11-21 | 2023-01-26 | 100% |  | 9.5714 | 36.5 | 3.15 | 328.5 | 28.35 | 229.95 | 98.55 | 271.35 | 599.85 | 599.85 | 0
| 6 | 1583 | 14115 |  |  | Level 4 Hotel | Access Scaffold |  | INDEPENDENT | 4 | 1 | 2 |  | 2 |  |  | 8 | m2-LxH | ON HIRE | 2022-12-12 |  | 100% |  | 11.2857 | 14 | 0.84 | 112 | 6.72 | 78.4 | 0 | 75.84 | 154.24 | 127.36 | 26.88 |  |  | #VALUE! | 78.4 | #VALUE! | #VALUE!
| 6 | 1656 | 14191 |  |  | Level 4 Residence | Access Scaffold |  | INDEPENDENT | 16.5 | 1 | 1 |  | 1 |  |  | 16.5 | m2-LxH | ON HIRE | 2022-12-23 |  | 100% |  | 9.7143 | 14 | 0.84 | 231 | 13.86 | 161.7 | 0 | 134.64 | 296.34 | 240.9 | 55.44 |  |  | #VALUE! | 161.7 | #VALUE! | #VALUE!
| 6 | 1522 | 14060 | 8559 |  | Level 4 Residence | Birdcage Scaffold |  | Birdcage | 12 | 2.6 | 5 |  | 5 |  |  | 156 | m3 | OFF HIRED | 2022-12-03 | 2023-02-11 | 100% |  | 10.1429 | 7.5 | 0.7 | 1170 | 109.2 | 819 | 351 | 1107.6 | 2277.6 | 1755 | 522.6 |  |  | #VALUE! | 819 | #VALUE! | #VALUE!
| 6 | 1676 | 14261 | 8417 |  | Level 4 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 8 |  | 8 |  |  | 50 | m3 | OFF HIRED | 2022-12-27 | 2023-01-11 | 100% |  | 2.2857 | 7.5 | 0.7 | 375 | 35 | 262.5 | 112.5 | 80 | 455 | 455 | 0
| 6 | 1597 | 14132 | 8621 |  | Level 4 To 5 Hotel | Chain Pully |  | Independent | 10 | 2.6 | 6 |  | 6 |  |  | 60 | m2-LxH | OFF HIRED | 2022-12-14 | 2023-02-01 | 100% |  | 7.1429 | 26 | 2.1 | 1560 | 126 | 1092 | 468 | 900 | 2460 | 1974 | 486 |  |  | #VALUE! | 1166.529 | #VALUE! | #VALUE!
| 6 | 1597 | 14132 | 8621 |  | Level 4 To 5 Hotel | Chain Pully |  | Buttress | 2.6 | 1.3 | 3 |  | 3 |  |  | 10.14 | m3 | OFF HIRED | 2022-12-14 | 2023-02-01 | 100% |  | 7.1429 | 5.25 | 0.35 | 53.235 | 3.549 | 37.2645 | 15.9705 | 25.35 | 78.585 | 62.1075 | 16.4775 |  |  | #VALUE! | 1166.529 | #VALUE! | #VALUE!
| 6 | 1597 | 14132 | 8621 |  | Level 4 To 5 Hotel | Chain Pully |  | Buttress | 2.6 | 1.3 | 3 |  | 3 |  |  | 10.14 | m3 | OFF HIRED | 2022-12-14 | 2023-02-01 | 100% |  | 7.1429 | 5.25 | 0.35 | 53.235 | 3.549 | 37.2645 | 15.9705 | 25.35 | 78.585 | 62.1075 | 16.4775 |  |  | #VALUE! | 1166.529 | #VALUE! | #VALUE!
| 7 |  | 12082 | 7821 |  | Level -5 Residance Pump Room | Access Scaffold |  | INDEPENDENT | 14 | 1.3 | 5 | 1 | 4 |  |  | 56 | m2-LxH | OFF HIRED | 2022-05-19 | 2022-08-10 | 100% |  | 12 | 14 |  | 784 | 0 | 548.8 | 235.2 | 0 | 784 | 784 | 0
| 7 |  | 12091 | 7597 |  | Level 5 Hotel Stair Case Area | Access Scaffold |  | INDEPENDENT | 1.3 | 1.3 | 4 | 1 | 3 |  |  | 3.9 | m2-LxH | OFF HIRED | 2022-05-22 | 2022-07-06 | 100% |  | 6.5714 | 14 |  | 54.6 | 0 | 38.22 | 16.38 | 0 | 54.6 | 54.6 | 0
| 7 |  | 12090 | 7824 |  | Level-5 Hotel Tower | Access Scaffold |  | INDEPENDENT | 7.5 | 1.3 | 4 | 1 | 3 |  |  | 22.5 | m2-LxH | OFF HIRED | 2022-05-23 | 2022-08-16 | 100% |  | 12.2857 | 14 |  | 315 | 0 | 220.5 | 94.5 | 0 | 315 | 315 | 0
| 7 |  | 12089 | 6720 |  | Level -5 Hotel Tower | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 4 | 1 | 3 |  |  | 15 | m2-LxH | OFF HIRED | 2022-05-23 | 2022-09-26 | 100% |  | 18.1429 | 14 |  | 210 | 0 | 147 | 63 | 0 | 210 | 210 | 0
| 7 |  | 12113 | 7740 |  | Level 5 - Hotel | Access Scaffold |  | INDEPENDENT | 1.3 | 1 | 8 | 1 | 7 |  |  | 9.1 | m2-LxH | OFF HIRED | 2022-05-27 | 2022-07-29 | 100% |  | 9.1429 | 14 |  | 127.4 | 0 | 89.18 | 38.22 | 0 | 127.4 | 127.4 | 0
| 7 |  | 12114 | 7563 |  | Level 5 Hotel Stair Case Area | Access Scaffold |  | INDEPENDENT | 1.3 | 1.3 | 4 | 1 | 3 |  |  | 3.9 | m2-LxH | OFF HIRED | 2022-05-27 | 2022-06-10 | 100% |  | 2.1429 | 14 |  | 54.6 | 0 | 38.22 | 16.38 | 0 | 54.6 | 54.6 | 0
| 7 |  | 12129 | 7726 |  | Level 5 Hotel | Access Scaffold |  | INDEPENDENT | 1.6 | 1.3 | 8 | 1 | 7 |  |  | 11.2 | m2-LxH | OFF HIRED | 2022-05-30 | 2022-07-18 | 100% |  | 7.1429 | 14 |  | 156.8 | 0 | 109.76 | 47.04 | 0 | 156.8 | 156.8 | 0
| 7 |  | 12092 | 7811 |  | Level 5 Hotel | Access Scaffold |  | INDEPENDENT | 5 | 1.8 | 6 | 1 | 5 |  |  | 25 | m2-LxH | OFF HIRED | 2022-05-22 | 2022-08-06 | 100% |  | 11 | 18 |  | 450 | 0 | 315 | 135 | 0 | 450 | 450 | 0
| 7 |  | 12112 | 7745 |  | Level 5 Hotel | Birdcage Scaffold |  | Birdcage | 7.5 | 2.5 | 8 | 1 | 7 |  |  | 131.25 | m3 | OFF HIRED | 2022-05-27 | 2022-07-28 | 100% |  | 9 | 7.5 |  | 984.375 | 0 | 689.0625 | 295.3125 | 0 | 984.375 | 984.375 | 0
| 7 | a03 | 12210 | 7821 |  | Level 5 Hotel | Access Scaffold |  | INDEPENDENT | 1.8 | 1.3 | 4.5 | 1 | 3.5 |  |  | 6.3 | m2-LxH | OFF HIRED | 2022-06-02 | 2022-08-10 | 100% |  | 10 | 14 |  | 88.2 | 0 | 61.74 | 26.46 | 0 | 88.2 | 88.2 | 0
| 7 | A12 | 12224 | 7596 |  | Level 5 Hotel | Access Scaffold |  | INDEPENDENT | 1.8 | 1.3 | 6 | 1 | 5 |  |  | 9 | m2-LxH | OFF HIRED | 2022-06-05 | 2022-07-03 | 100% |  | 4.1429 | 14 |  | 126 | 0 | 88.2 | 37.8 | 0 | 126 | 126 | 0
| 7 | 378 | 12534 | 7830 |  | Level 5 Hotel | Access Scaffold |  | INDEPENDENT | 7.5 | 1 | 7 | 1 | 6 |  |  | 45 | m2-LxH | OFF HIRED | 2022-06-28 | 2022-08-18 | 100% |  | 7.4286 | 14 | 0.84 | 630 | 37.8 | 441 | 189 | 280.8 | 910.8 | 910.8 | 0
| 7 | A02 | 12209 | 6709 |  | Level 5 Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 4.5 | 1 | 3.5 |  |  | 21.875 | m3 | OFF HIRED | 2022-06-02 | 2022-09-20 | 100% |  | 15.8571 | 7.5 |  | 164.0625 | 0 | 114.8437 | 49.2188 | 0 | 164.0625 | 164.0625 | 0
| 7 |  | 12401 | 8430 |  | Zone 3 Level 5 Hotel | Chain Pully |  | INDEPENDENT | 15 | 1.3 | 7 | 1 | 6 |  |  | 90 | m2-LxH | OFF HIRED | 2022-06-17 | 2023-01-17 | 100% |  | 30.7143 | 14 | 0.84 | 1260 | 75.6 | 882 | 378 | 2322 | 3582 | 3582 | 0
| 7 |  | 12401 | 8430 |  | Zone 3 Level 5 Hotel | Chain Pully |  | INDEPENDENT | 15 | 1.8 | 7 | 1 | 6 |  |  | 90 | m2-LxH | OFF HIRED | 2022-06-17 | 2023-01-17 | 100% |  | 30.7143 | 18 | 1.05 | 1620 | 94.5 | 1134 | 486 | 2902.5 | 4522.5 | 4522.5 | 0
| 7 |  | 12401 | 8430 |  | Zone 3 Level 5 Hotel | Chain Pully |  | Buttress | 11 | 2.5 | 3 | 1 | 2 |  |  | 55 | m3 | OFF HIRED | 2022-06-17 | 2023-01-17 | 100% |  | 30.7143 | 5.25 | 0.35 | 288.75 | 19.25 | 202.125 | 86.625 | 591.25 | 880 | 880 | 0
| 7 |  | 12449 |  |  | Zone 6 Level 5 Hotel | Chain Pully |  | INDEPENDENT | 15 | 2.5 | 9 | 1 | 8 |  |  | 120 | m2-LxH | ON HIRE | 2022-06-17 |  | 100% |  | 36.7143 | 26 | 2.1 | 3120 | 252 | 2184 | 0 | 9252 | 11436 | 10428 | 1008 |  |  | #VALUE! | 3010.875 | #VALUE! | #VALUE!
| 7 |  | 12449 |  |  | Zone 6 Level 5 Hotel | Chain Pully |  | Buttress | 15 | 2.5 | 7 | 1 | 6 |  |  | 225 | m3 | ON HIRE | 2022-06-17 |  | 100% |  | 36.7143 | 5.25 | 0.35 | 1181.25 | 78.75 | 826.875 | 0 | 2891.25 | 3718.125 | 3403.125 | 315 |  |  | #VALUE! | 3010.875 | #VALUE! | #VALUE!
| 7 | 491 | 12721 | 6744 |  | Level 5 Hotel | Access Scaffold |  | INDEPENDENT | 7.5 | 1 | 7 | 1 | 6 |  |  | 45 | m2-LxH | OFF HIRED | 2022-07-11 | 2022-09-30 | 100% |  | 11.7143 | 14 | 0.84 | 630 | 37.8 | 441 | 189 | 442.8 | 1072.8 | 1072.8 | 0
| 7 | A492 | 12720 | 6744 |  | Level 5 Hotel | Load Bearing Speacial Scaffold |  | Load Bearing | 5 | 1.2 | 8 | 1 | 7 |  | 1 | 1 | unit | OFF HIRED | 2022-07-11 | 2022-09-30 | 100% |  | 11.7143 | 3000 | 175 | 3000 | 175 | 2100 | 900 | 2050 | 5050 | 5050 | 0
| 7 | 624 | 12844 | 7749 |  | Level 5 Hotel | Access Scaffold |  | Tower | 2.5 | 1.8 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-07-26 | 2022-08-03 | 100% |  | 1.2857 | 135 |  | 540 | 0 | 378 | 162 | 0 | 540 | 540 | 0
| 7 | 758 | 13023 | 6745 |  | level 5 Hotel | Access Scaffold |  | Tower | 2.5 | 2.5 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-08-17 | 2022-09-30 | 100% |  | 6.4286 | 135 |  | 540 | 0 | 378 | 162 | 0 | 540 | 540 | 0
| 7 | 707 | 12971 | 6745 |  | Level 5 Hotel | Access Scaffold |  | Tower | 2.5 | 1.3 | 7 | 1 | 6 |  |  | 6 | rm | OFF HIRED | 2022-08-11 | 2022-09-30 | 100% |  | 7.2857 | 135 | 12.25 | 810 | 73.5 | 567 | 243 | 535.5 | 1345.5 | 1345.5 | 0
| 7 | 712 | 12976 | 6747 |  | Level 5 Hotel | Access Scaffold |  | Tower | 2.5 | 1.8 | 9 | 1 | 8 |  |  | 8 | rm | OFF HIRED | 2022-08-12 | 2022-09-30 | 100% |  | 7.1429 | 135 | 12.25 | 1080 | 98 | 756 | 324 | 700 | 1780 | 1780 | 0
| 7 | 713 | 12977 | 6720 |  | Level 5 Hotel | Access Scaffold |  | Tower | 2.5 | 1.8 | 9 | 1 | 8 |  |  | 8 | rm | OFF HIRED | 2022-08-12 | 2022-09-26 | 100% |  | 6.5714 | 135 | 12.25 | 1080 | 98 | 756 | 324 | 644 | 1724 | 1724 | 0
| 7 | 731 | 12987 | 6725 |  | Level 5/6 Hotel | Access Scaffold |  | Tower | 2.5 | 1.8 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-08-13 | 2022-09-26 | 100% |  | 6.4286 | 135 | 12.25 | 540 | 49 | 378 | 162 | 315 | 855 | 855 | 0
| 7 | 730 | 12986 | 6740 |  | Level 5 Hotel | Access Scaffold |  | Tower | 2.5 | 2.5 | 9 | 1 | 8 |  |  | 8 | rm | OFF HIRED | 2022-08-13 | 2022-09-30 | 100% |  | 7 | 135 | 12.25 | 1080 | 98 | 756 | 324 | 686 | 1766 | 1766 | 0
| 7 | 750 | 13016 | 6709 |  | Level 5 Hotel | Access Scaffold |  | Tower | 2.5 | 2.5 | 9 | 1 | 8 |  |  | 8 | rm | OFF HIRED | 2022-08-16 | 2022-09-20 | 100% |  | 5.1429 | 135 | 12.25 | 1080 | 98 | 756 | 324 | 504 | 1584 | 1584 | 0
| 7 | 750 | 13016 | 6709 |  | Level 5 Hotel | Access Scaffold |  | Tower | 2.5 | 2.5 | 9 | 1 | 8 |  |  | 8 | rm | OFF HIRED | 2022-08-16 | 2022-09-20 | 100% |  | 5.1429 | 135 | 12.25 | 1080 | 98 | 756 | 324 | 504 | 1584 | 1584 | 0
| 7 | 705 | 12969 | 6733 |  | Level 5 To 6 Hotel | Access Scaffold |  | Independent | 4 | 1.3 | 5 | 1 | 4 |  |  | 16 | m2-LxH | OFF HIRED | 2022-08-10 | 2022-09-28 | 100% |  | 7.1429 | 14 | 0.84 | 224 | 13.44 | 156.8 | 67.2 | 96 | 320 | 320 | 0
| 7 | 721 | 13003 | 8592 |  | Zone 1 , 2 Level 5 Hotel | Chain Pully |  | Independent | 51 | 1 | 7 | 1 | 6 |  |  | 306 | m2-LxH | OFF HIRED | 2022-08-11 | 2023-02-21 | 100% |  | 27.8571 | 14 | 0.84 | 4284 | 257.04 | 2998.8 | 1285.2 | 7160.4 | 11444.4 | 9388.08 | 2056.32 |  |  | #VALUE! | 5810.175 | #VALUE! | #VALUE!
|  |  | 13003 | 8637 |  | PARTIAL DISMANTEL |  |  |  | 31 | 1 | 7 | 1 | 6 |  |  | 186 | m2-LxH | OFF HIRED | 2023-02-02 | 2023-02-21 | 100% |  | -2.8571 | 14 | 0.84 | 2604 | 156.24 |  | 0 | -446.4 | -446.4 |  | -446.4 |  |  | #VALUE! | 5810.175 | #VALUE! | #VALUE!
| 7 | 721 | 13003 | 8592 |  | Zone 1 , 2 Level 5 Hotel | Chain Pully |  | Buttress | 51 | 2.5 | 7 | 1 | 6 |  |  | 765 | m3 | OFF HIRED | 2022-08-11 | 2023-02-21 | 100% |  | 27.8571 | 5.25 | 0.35 | 4016.25 | 267.75 | 2811.375 | 1204.875 | 7458.75 | 11475 | 9466.875 | 2008.125 |  |  | #VALUE! | 5810.175 | #VALUE! | #VALUE!
|  |  |  | 8637 |  | PARTIAL DISMANTEL |  |  |  | 31 | 2.5 | 7 | 1 | 6 |  |  | 465 | m3 | OFF HIRED | 2023-02-02 | 2023-02-21 | 100% |  | -2.8571 | 5.25 | 0.35 | 2441.25 | 162.75 |  | 0 | -465 | -465 |  | -465 |  |  | #VALUE! | 0 | #VALUE! | #VALUE!
| 7 | 972 | 13347 | 6725 |  | Level 5 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 7 |  | 7 |  |  | 7 | rm | OFF HIRED | 2022-09-15 | 2022-09-26 | 100% |  | 1.7143 | 135 |  | 945 | 0 | 661.5 | 283.5 | 0 | 945 | 945 | 0
| 7 | 972 | 13347 | 6725 |  | Level 5 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 7 |  | 7 |  |  | 7 | rm | OFF HIRED | 2022-09-15 | 2022-09-26 | 100% |  | 1.7143 | 135 |  | 945 | 0 | 661.5 | 283.5 | 0 | 945 | 945 | 0
| 7 | 972 | 13347 | 6725 |  | Level 5 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 7 |  | 7 |  |  | 7 | rm | OFF HIRED | 2022-09-15 | 2022-09-26 | 100% |  | 1.7143 | 135 |  | 945 | 0 | 661.5 | 283.5 | 0 | 945 | 945 | 0
| 7 | 972 | 13347 | 6725 |  | Level 5 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 7 |  | 7 |  |  | 7 | rm | OFF HIRED | 2022-09-15 | 2022-09-26 | 100% |  | 1.7143 | 135 |  | 945 | 0 | 661.5 | 283.5 | 0 | 945 | 945 | 0
| 7 | 972 | 13347 | 6725 |  | Level 5 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 7 |  | 7 |  |  | 7 | rm | OFF HIRED | 2022-09-15 | 2022-09-26 | 100% |  | 1.7143 | 135 |  | 945 | 0 | 661.5 | 283.5 | 0 | 945 | 945 | 0
| 7 | 972 | 13347 | 6725 |  | Level 5 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 7 |  | 7 |  |  | 7 | rm | OFF HIRED | 2022-09-15 | 2022-09-26 | 100% |  | 1.7143 | 135 |  | 945 | 0 | 661.5 | 283.5 | 0 | 945 | 945 | 0
| 7 | 972 | 13347 | 6725 |  | Level 5 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 7 |  | 7 |  |  | 7 | rm | OFF HIRED | 2022-09-15 | 2022-09-26 | 100% |  | 1.7143 | 135 |  | 945 | 0 | 661.5 | 283.5 | 0 | 945 | 945 | 0
| 7 | 940 | 13313 | 8298 |  | Level 5 Hotel | Access Scaffold |  | Independent | 8 | 1 | 4 |  | 4 |  |  | 32 | m2-LxH | OFF HIRED | 2022-09-10 | 2022-12-04 | 100% |  | 12.2857 | 14 | 0.84 | 448 | 26.88 | 313.6 | 134.4 | 330.24 | 778.24 | 778.24 | 0
| 7 | 238 | 12353 | 7577 |  | Level 5 Residance | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 6 | 1 | 5 |  |  | 5 | rm | OFF HIRED | 2022-06-15 | 2022-06-24 | 100% |  | 1.4286 | 135 | 12.25 | 675 | 61.25 | 472.5 | 202.5 | 87.5 | 762.5 | 762.5 | 0
| 7 | 259 | 12373 | 7701 |  | Level 5 Residance | HEAVY DUTY TOWER |  | Tower | 2.5 | 2.5 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-06-16 | 2022-07-04 | 100% |  | 2.7143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 66.5 | 336.5 | 336.5 | 0
| 7 | 271 | 12385 | 7577 |  | Level 5 Pump Room Residance | HEAVY DUTY TOWER |  | Tower | 2.5 | 2.5 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-06-17 | 2022-06-24 | 100% |  | 1.1429 | 135 | 12.25 | 540 | 49 | 378 | 162 | 56 | 596 | 596 | 0
| 7 | 351 | 12506 | 6709 |  | Level 5 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 2.5 | 6 | 1 | 5 |  |  | 5 | rm | OFF HIRED | 2022-06-24 | 2022-09-20 | 100% |  | 12.7143 | 135 | 12.25 | 675 | 61.25 | 472.5 | 202.5 | 778.75 | 1453.75 | 1453.75 | 0
| 7 | 178 | 12174 | 7596 |  | Level 5 Residence | Access Scaffold |  | INDEPENDENT | 1.8 | 1 | 5 | 1 | 4 |  |  | 7.2 | m2-LxH | OFF HIRED | 2022-06-08 | 2022-07-03 | 100% |  | 3.7143 | 14 |  | 100.8 | 0 | 70.56 | 30.24 | 0 | 100.8 | 100.8 | 0
| 7 | 297 | 12403 | 7714 |  | Level 5 Residence | Access Scaffold |  | INDEPENDENT | 13 | 1.3 | 9 | 1 | 8 |  |  | 104 | m2-LxH | OFF HIRED | 2022-06-17 | 2022-07-15 | 100% |  | 4.1429 | 14 | 0.84 | 1456 | 87.36 | 1019.2 | 436.8 | 361.92 | 1817.92 | 1817.92 | 0
| 7 | 270 | 12502 | 8193 |  | Level 5 Residence | Access Scaffold |  | INDEPENDENT | 20 | 1.3 | 4 | 1 | 3 |  |  | 60 | m2-LxH | OFF HIRED | 2022-06-24 | 2022-11-05 | 100% |  | 19.2857 | 14 | 0.84 | 840 | 50.4 | 588 | 252 | 972 | 1812 | 1812 | 0
| 7 | 198 | 12194 | 6731 |  | Level 5 Residence | Access Scaffold |  | INDEPENDENT | 1.8 | 1.8 | 6 | 1 | 5 |  |  | 9 | m2-LxH | OFF HIRED | 2022-06-09 | 2022-09-27 | 100% |  | 15.8571 | 18 |  | 162 | 0 | 113.4 | 48.6 | 0 | 162 | 162 | 0
| 7 | 199 | 12195 | 7568 |  | Level 5 Residence | Access Scaffold |  | INDEPENDENT | 5 | 1.8 | 6 | 1 | 5 |  |  | 25 | m2-LxH | OFF HIRED | 2022-06-09 | 2022-06-20 | 100% |  | 1.7143 | 18 | 1.05 | 450 | 26.25 | 315 | 135 | 45 | 495 | 495 | 0
| 7 | 177 | 12173 | 7724 |  | Level 5 Residence | Birdcage Scaffold |  | Birdcage | 7.5 | 2.5 | 6 | 1 | 5 |  |  | 93.75 | m3 | OFF HIRED | 2022-06-08 | 2022-07-15 | 100% |  | 5.4286 | 7.5 |  | 703.125 | 0 | 492.1875 | 210.9375 | 0 | 703.125 | 703.125 | 0
| 7 | 226 | 12347 | 6749 |  | Level 5 Residence | Birdcage Scaffold |  | Birdcage | 11 | 6 | 5 | 1 | 4 |  |  | 264 | m3 | OFF HIRED | 2022-06-14 | 2022-10-01 | 100% |  | 15.7143 | 7.5 | 0.7 | 1980 | 184.8 | 1386 | 594 | 2904 | 4884 | 4884 | 0
| 7 | 233 | 12336 | 8190 |  | Level 5 Residence | Birdcage Scaffold |  | Birdcage | 12 | 10 | 4 | 1 | 3 |  |  | 360 | m3 | OFF HIRED | 2022-06-14 | 2022-11-03 | 100% |  | 20.4286 | 7.5 | 0.7 | 2700 | 252 | 1890 | 810 | 5148 | 7848 | 7848 | 0
| 7 | 226 | 12337 | 7878 |  | Level 5 Residence | Birdcage Scaffold |  | Birdcage | 11 | 6 | 6 | 1 | 5 |  |  | 330 | m3 | OFF HIRED | 2022-06-13 | 2022-09-12 | 100% |  | 13.1429 | 7.5 | 0.7 | 2475 | 231 | 1732.5 | 742.5 | 3036 | 5511 | 5511 | 0
| 7 | 402 | 12563 | 7723 |  | Level 5 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-06-29 | 2022-07-17 | 100% |  | 2.7143 | 135 | 12.25 | 540 | 49 | 378 | 162 | 133 | 673 | 673 | 0
| 7 | 404 | 12565 | 6731 |  | Level 5 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-06-30 | 2022-09-27 | 100% |  | 12.8571 | 135 | 12.25 | 540 | 49 | 378 | 162 | 630 | 1170 | 1170 | 0
| 7 | 490 | 12648 | 7713 |  | Level 5 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-07 | 2022-07-14 | 100% |  | 1.1429 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 28 | 298 | 298 | 0
| 7 | 615 | 12835 | 7860 |  | Level 5 Residence | Access Scaffold |  | Tower | 1.8 | 1.3 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-07-27 | 2022-08-31 | 100% |  | 5.1429 | 135 | 12.25 | 540 | 49 | 378 | 162 | 252 | 792 | 792 | 0
| 7 | 689 | 12898 | 7811 |  | Level 5 Residence | Access Scaffold |  | Tower | 2.5 | 2.5 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-08-08 | 2022-08-06 | 100% |  | -0.14286 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 0 | 405 | 405 | 0
| 7 | 270 | 12384 | 6725 |  | Level -5 Residance | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 3 | 1 | 2 |  |  | 10 | m2-LxH | OFF HIRED | 2022-06-16 | 2022-09-26 | 100% |  | 14.7143 | 14 | 0.84 | 140 | 8.4 | 98 | 42 | 123.6 | 263.6 | 263.6 | 0
| 7 |  | 12448 |  |  | Level 5 Hotel Zone 3,4 and 5 | Chain Pully With Ladder Beam |  | INDEPENDENT | 3 | 23 |  |  |  | 1 |  | 69 | m2-LxW | ON HIRE | 2022-06-17 |  | 100% |  | 36.7143 | 81 | 1.82 | 5589 | 125.58 | 3912.3 | 0 | 4610.58 | 8522.88 | 8020.56 | 502.32 |  |  | #VALUE! | 5953.5 | #VALUE! | #VALUE!
| 7 |  | 12448 | 8270 |  | PARTIAL DISMANTEL |  |  |  | 3 | 6 |  |  | 0 | 1 |  | 18 | m2-LxW | OFF HIRED | 2022-11-21 | 2023-01-31 | 100% |  | -10.2857 | 81 | 1.82 | 1458 | 32.76 |  | 437.4 | -336.96 | 100.44 | 100.44 | 0
| 7 |  | 12448 |  |  | Level 5 Hotel Zone 3,4 and 6 | Chain Pully With Ladder Beam |  | INDEPENDENT | 6 | 6 |  |  |  | 1 |  | 36 | m2-LxW | ON HIRE | 2022-06-17 |  | 100% |  | 36.7143 | 81 | 1.82 | 2916 | 65.52 | 2041.2 | 0 | 2405.52 | 4446.72 | 4184.64 | 262.08 |  |  | #VALUE! | 5953.5 | #VALUE! | #VALUE!
| 7 |  | 12448 | 8270 |  | PARTIAL DISMANTEL |  |  |  | 6 | 1 |  |  | 0 | 1 |  | 6 | m2-LxW | OFF HIRED | 2022-11-21 | 2023-01-31 | 100% |  | -10.2857 | 81 | 1.82 | 486 | 10.92 |  | 145.8 | -112.32 | 33.48 | 33.48 | 0
| 7 |  | 12450 |  |  | Level 5 Hotel Zone 5 Road Side | Chain Pully |  | INDEPENDENT | 20 | 1.3 | 24 | 1 | 23 |  |  | 460 | m2-LxH | ON HIRE | 2022-06-17 |  | 100% |  | 36.7143 | 26 | 2.1 | 11960 | 966 | 8372 | 0 | 35466 | 43838 | 39974 | 3864 |  |  | #VALUE! | 17472 | #VALUE! | #VALUE!
| 7 |  |  | 8478 |  | PARTIAL DISMANTEL |  |  |  | 10 | 1.3 | 24 | 1 | 23 |  |  | 230 | m2-LxH | OFF HIRED | 2022-12-31 | 2023-01-31 | 100% |  | -4.5714 | 26 | 2.1 | 5980 | 483 |  | 1794 | -2208 | -414 | -414 | 0
| 7 |  | 12450 |  |  | Level 5 Hotel Zone 5 Road Side | Chain Pully |  | INDEPENDENT | 20 | 1.3 | 26 | 1 | 25 |  |  | 500 | m2-LxH | ON HIRE | 2022-06-17 |  | 100% |  | 36.7143 | 26 | 2.1 | 13000 | 1050 | 9100 | 0 | 38550 | 47650 | 43450 | 4200 |  |  | #VALUE! | 17472 | #VALUE! | #VALUE!
| 7 |  |  | 8478 |  | PARTIAL DISMANTEL |  |  |  | 10 | 1.3 | 26 | 1 | 25 |  |  | 250 | m2-LxH | OFF HIRED | 2022-12-31 | 2023-01-31 | 100% |  | -4.5714 | 26 | 2.1 | 6500 | 525 |  | 1950 | -2400 | -450 | -450 | 0
| 7 | 722 A | 13005 | 8437 |  | Level 5 Zone 6 Hotel | Chain Pully With Ladder Beam |  | Independent | 3 | 5 |  |  |  | 1 |  | 15 | m2-LxW | OFF HIRED | 2022-08-08 | 2023-01-18 | 100% |  | 23.4286 | 81 | 1.82 | 1215 | 27.3 | 850.5 | 364.5 | 639.6 | 1854.6 | 1854.6 | 0
| 7 | 722 A | 13005 | 8437 |  | Level 5 Zone 6 Hotel | Chain Pully With Ladder Beam |  | Independent | 6 | 2 |  |  |  | 1 |  | 12 | m2-LxW | OFF HIRED | 2022-08-08 | 2023-01-18 | 100% |  | 23.4286 | 81 | 1.82 | 972 | 21.84 | 680.4 | 291.6 | 511.68 | 1483.68 | 1483.68 | 0
| 7 | 721 A | 13004 | 8437 |  | Level 5 Zone 1 , 2 Hotel | Chain Pully With Ladder Beam |  | Independent | 3 | 20 |  |  |  | 1 |  | 60 | m2-LxW | OFF HIRED | 2022-08-11 | 2023-01-18 | 100% |  | 23 | 81 | 1.82 | 4860 | 109.2 | 3402 | 1458 | 2511.6 | 7371.6 | 7371.6 | 0
| 7 | 721 A | 13004 | 8437 |  | Level 5 Zone 1 , 2 Hotel | Chain Pully With Ladder Beam |  | Independent | 6 | 8 |  |  |  | 1 |  | 48 | m2-LxW | OFF HIRED | 2022-08-11 | 2023-01-18 | 100% |  | 23 | 81 | 1.82 | 3888 | 87.36 | 2721.6 | 1166.4 | 2009.28 | 5897.28 | 5897.28 | 0
| 7 |  | 12402 | 8299 |  | Level 5 Zone 4 Hotel | Chain Pully |  | Birdcage | 9.5 | 2.5 | 21 | 1 | 20 |  |  | 190 | m2-LxH | OFF HIRED | 2022-06-17 | 2022-12-05 | 100% |  | 24.5714 | 26 | 2.1 | 4940 | 399 | 3458 | 1482 | 9804 | 14744 | 14744 | 0
| 7 |  | 12402 | 8299 |  | Level 5 Zone 4 Hotel | Chain Pully |  | Buttress | 9.5 | 2.5 | 18 | 1 | 17 |  |  | 403.75 | m3 | OFF HIRED | 2022-06-17 | 2022-12-05 | 100% |  | 24.5714 | 5.25 | 0.35 | 2119.6875 | 141.3125 | 1483.7812 | 635.9062 | 3472.25 | 5591.9375 | 5591.9375 | 0
| 7 | 1047 | 13478 | 6747 |  | Level 5 Hotel | Access Scaffold |  | Independent | 15 | 1.3 | 2.5 |  | 2.5 |  |  | 37.5 | m2-LxH | OFF HIRED | 2022-09-26 | 2022-09-30 | 100% |  | 0.71429 | 14 | 0.84 | 525 | 31.5 | 367.5 | 157.5 | 22.5 | 547.5 | 547.5 | 0
| 7 | 1047 | 13482 | 6747 |  | Level 5 Hotel | Access Scaffold |  | Independent | 15 | 1.3 | 2.5 |  | 2.5 |  |  | 37.5 | m2-LxH | OFF HIRED | 2022-09-24 | 2022-09-30 | 100% |  | 1 | 14 | 0.84 | 525 | 31.5 | 367.5 | 157.5 | 31.5 | 556.5 | 556.5 | 0
| 7 | 1183 | 13668 | 8154 |  | Level 5 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-10-12 | 2022-10-27 | 100% |  | 2.2857 | 135 | 12.25 | 540 | 49 | 378 | 162 | 112 | 652 | 652 | 0
| 7 | 1250 | 13788 | 8172 |  | Level 5 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 6 |  | 6 |  |  | 6 | rm | OFF HIRED | 2022-10-19 | 2022-10-29 | 100% |  | 1.5714 | 135 | 12.25 | 810 | 73.5 | 567 | 243 | 0 | 810 | 810 | 0
| 7 | 1211 | 13697 | 8182 |  | Level 5 Hotel | Access Scaffold |  | Independent | 3.6 | 1.3 | 4.5 |  | 4.5 |  |  | 16.2 | m2-LxH | OFF HIRED | 2022-10-15 | 2022-10-31 | 100% |  | 2.4286 | 14 | 0.84 | 226.8 | 13.608 | 158.76 | 68.04 | 33.048 | 259.848 | 259.848 | 0
| 7 | 1256 | 13794 | 8212 |  | Level 5 Residence | Access Scaffold |  | Independent | 5 | 1.3 | 2 |  | 2 |  |  | 10 | m2-LxH | OFF HIRED | 2022-10-20 | 2022-11-09 | 100% |  | 3 | 14 | 0.84 | 140 | 8.4 | 98 | 42 | 25.2 | 165.2 | 165.2 | 0
| 7 | 1279 | 13718 | 8324 |  | Level 5 Hotel | Access Scaffold |  | Independent | 5 | 1.3 | 2.5 |  | 2.5 |  |  | 12.5 | m2-LxH | OFF HIRED | 2022-10-22 | 2022-12-13 | 100% |  | 7.5714 | 14 | 0.84 | 175 | 10.5 | 122.5 | 52.5 | 79.5 | 254.5 | 254.5 | 0
| 7 | 1229 | 13767 | 8216 |  | Level 5 Hotel | Birdcage Scaffold |  | Birdcage | 6 | 2.5 | 5 |  | 5 |  |  | 75 | m3 | OFF HIRED | 2022-10-16 | 2022-11-09 | 100% |  | 3.5714 | 7.5 | 0.7 | 562.5 | 52.5 | 393.75 | 168.75 | 187.5 | 750 | 750 | 0
| 7 | 1303 | 13741 | 8162 |  | Level 7 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 1.5 |  | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2022-10-27 | 2022-10-28 | 100% |  | 0.28571 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 60.75 | 5.25 | 207.75 | 207.75 | 0
| 7 | 1365 | 13853 | 8452 |  | Level 5 Hotel | Access Scaffold |  | INDEPENDENT | 8 | 1 | 1.5 |  | 1.5 |  |  | 12 | m2-LxH | OFF HIRED | 2022-11-04 | 2022-12-21 | 100% |  | 6.8571 | 14 | 0.84 | 168 | 10.08 | 117.6 | 50.4 | 69.12 | 237.12 | 237.12 | 0
| 7 | 1383 | 13871 | 8331 |  | Level 5 Residence | Access Scaffold |  | INDEPENDENT | 11.3 | 1 | 4 |  | 4 |  |  | 45.2 | m2-LxH | OFF HIRED | 2022-11-07 | 2022-12-15 | 100% |  | 5.5714 | 14 |  | 632.8 | 0 | 442.96 | 189.84 | 0 | 632.8 | 632.8 | 0
| 7 | 1383 | 13871 | 8331 |  | Level 5 Residence | Access Scaffold |  | INDEPENDENT | 8.8 | 1.3 | 2 |  | 2 |  |  | 17.6 | m2-LxH | OFF HIRED | 2022-11-07 | 2022-12-15 | 100% |  | 5.5714 | 14 |  | 246.4 | 0 | 172.48 | 73.92 | 0 | 246.4 | 246.4 | 0
| 7 | 1295 | 13734 |  |  | Level 5 Residence | Access Scaffold |  | INDEPENDENT | 3.9 | 1 | 1.5 |  | 1.5 |  |  | 5.85 | m2-LxH | ON HIRE | 2022-10-26 |  | 100% |  | 18 | 14 | 0.84 | 81.9 | 4.914 | 57.33 | 0 | 88.452 | 145.782 | 126.126 | 19.656 |  |  | #VALUE! | 57.33 | #VALUE! | #VALUE!
| 7 | 1417 | 13905 | 8251 |  | Level 5 To 6 Hotel | Chain Pully With Ladder Beam |  | Independent | 6 | 3 |  |  |  | 1 |  | 18 | m2-LxW | OFF HIRED | 2022-11-11 | 2022-11-17 | 100% |  | 1 | 81 | 1.82 | 1458 | 32.76 | 1020.6 | 437.4 | 32.76 | 1490.76 | 1490.76 | 0
| 7 | 1417 | 13905 | 8251 |  | Level 5 To 6 Hotel | Chain Pully With Ladder Beam |  | Independent | 4 | 17 |  |  |  | 1 |  | 68 | m2-LxW | OFF HIRED | 2022-11-11 | 2022-11-17 | 100% |  | 1 | 81 | 1.82 | 5508 | 123.76 | 3855.6 | 1652.4 | 123.76 | 5631.76 | 5631.76 | 0
| 7 | 1603 | 14138 | 8619 |  | Level 5 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-12-15 | 2023-02-01 | 100% |  | 7 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 171.5 | 441.5 | 357 | 84.5 |  |  | #VALUE! | 378 | #VALUE! | #VALUE!
| 7 | 1603 | 14138 | 8619 |  | Level 5 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-12-15 | 2023-02-01 | 100% |  | 7 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 171.5 | 441.5 | 357 | 84.5 |  |  | #VALUE! | 378 | #VALUE! | #VALUE!
| 7 | 1604 | 14139 | 8477 |  | Level 5 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 5 |  | 5 |  |  | 5 | rm | OFF HIRED | 2022-12-15 | 2022-12-31 | 100% |  | 2.4286 | 135 | 12.25 | 675 | 61.25 | 472.5 | 202.5 | 148.75 | 823.75 | 823.75 | 0
| 7 | 1606 | 14141 | 8619 |  | Level 5 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-12-16 | 2023-02-01 | 100% |  | 6.8571 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 168 | 438 | 353.5 | 84.5 |  |  | #VALUE! | 378 | #VALUE! | #VALUE!
| 7 | 1606 | 14141 | 8619 |  | Level 5 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-12-16 | 2023-02-01 | 100% |  | 6.8571 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 168 | 438 | 353.5 | 84.5 |  |  | #VALUE! | 378 | #VALUE! | #VALUE!
| 7 | 1627 | 14164 | 8616 |  | Level 5 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-12-19 | 2023-01-28 | 100% |  | 5.8571 | 135 | 12.25 | 540 | 49 | 378 | 162 | 287 | 827 | 827 | 0
| 7 | 1631 | 14168 | 8613 |  | Level 5 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-12-20 | 2023-01-27 | 100% |  | 5.5714 | 135 | 12.25 | 540 | 49 | 378 | 162 | 273 | 813 | 813 | 0
| 7 | 1510 | 13997 | 8303 |  | Level 5 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3.5 |  | 3.5 |  |  | 3.5 | rm | OFF HIRED | 2022-11-28 | 2022-12-05 | 100% |  | 1.1429 | 135 | 12.25 | 472.5 | 42.875 | 330.75 | 141.75 | 49 | 521.5 | 521.5 | 0
| 7 | 1588 | 14120 |  |  | Level 5 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.8 | 6 |  | 6 |  |  | 6 | rm | ON HIRE | 2022-12-13 |  | 100% |  | 11.1429 | 135 | 12.25 | 810 | 73.5 | 567 | 0 | 819 | 1386 | 1092 | 294 |  |  | #VALUE! | 567 | #VALUE! | #VALUE!
| 7 | 1579 | 14112 | 8494 |  | Level 5 Hotel | Access Scaffold |  | INDEPENDENT | 5 | 1 | 4 |  | 4 |  |  | 20 | m2-LxH | OFF HIRED | 2022-12-10 | 2023-01-05 | 100% |  | 3.8571 | 14 | 0.84 | 280 | 16.8 | 196 | 84 | 64.8 | 344.8 | 344.8 | 0
| 7 | 1498 | 13985 |  |  | Level 5 Hotel | Cantiliver |  | Cantiliver | 70 | 0.3 |  |  |  | 0.3 |  | 6.3 | m2-LxW | ON HIRE | 2022-11-26 |  | 100% |  | 13.5714 | 36.5 | 3.15 | 229.95 | 19.845 | 160.965 | 0 | 269.325 | 430.29 | 350.91 | 79.38 |  |  | #VALUE! | 160.965 | #VALUE! | #VALUE!
| 8 |  | 12236 | 8121 |  | Level 6 to 25 Residence | Edge Prorection |  | Edge Prorection | 318 | [6 empty] | 318 | lm | OFF HIRED | 2022-06-15 | 2022-10-19 | 100% |  | 18.1429 | 24 |  | 7632 | 0 | 5342.4 | 2289.6 | 0 | 7632 | 7632 | 0
| 8 | 296 | 13309 | 8428 |  | Level 6 to 7 Hotel | Access Scaffold |  | Independent | 18 | 1.3 | 3 |  | 3 |  |  | 54 | m2-LxH | OFF HIRED | 2022-09-10 | 2023-01-16 | 100% |  | 18.4286 | 14 | 0.84 | 756 | 45.36 | 529.2 | 0 | 835.92 | 1365.12 | 1365.12 | 0
| 8 |  | 12713 | 6729 |  | Level 6,7,10,23 Residence | Netting Instalation |  | Netting | 7 |  | 4 | 1 | 3 |  |  | 21 | m2-LxH | OFF HIRED | 2022-07-07 | 2022-09-27 | 100% |  | 11.8571 | 4.5 |  | 94.5 | 0 | 66.15 | 28.35 | 0 | 94.5 | 94.5 | 0
| 8 |  | 12713 | 6729 |  | Level 6,7,10,23 Residence | Netting Instalation |  | Netting | 7 |  | 4 | 1 | 3 |  |  | 21 | m2-LxH | OFF HIRED | 2022-07-07 | 2022-09-27 | 100% |  | 11.8571 | 4.5 |  | 94.5 | 0 | 66.15 | 28.35 | 0 | 94.5 | 94.5 | 0
| 8 |  | 12713 | 6729 |  | Level 6,7,10,23 Residence | Netting Instalation |  | Netting | 7 |  | 4 | 1 | 3 |  |  | 21 | m2-LxH | OFF HIRED | 2022-07-07 | 2022-09-27 | 100% |  | 11.8571 | 4.5 |  | 94.5 | 0 | 66.15 | 28.35 | 0 | 94.5 | 94.5 | 0
| 8 |  | 12713 | 6729 |  | Level 6,7,10,23 Residence | Netting Instalation |  | Netting | 7 |  | 4 | 1 | 3 |  |  | 21 | m2-LxH | OFF HIRED | 2022-07-07 | 2022-09-27 | 100% |  | 11.8571 | 4.5 |  | 94.5 | 0 | 66.15 | 28.35 | 0 | 94.5 | 94.5 | 0
| 8 |  | 12713 | 6729 |  | Level 6,7,10,23 Residence | Netting Instalation |  | Netting | 7 |  | 4 | 1 | 3 |  |  | 21 | m2-LxH | OFF HIRED | 2022-07-07 | 2022-09-27 | 100% |  | 11.8571 | 4.5 |  | 94.5 | 0 | 66.15 | 28.35 | 0 | 94.5 | 94.5 | 0
| 8 |  | 12713 | 6729 |  | Level 6,7,10,23 Residence | Netting Instalation |  | Netting | 7 |  | 4 | 1 | 3 |  |  | 21 | m2-LxH | OFF HIRED | 2022-07-07 | 2022-09-27 | 100% |  | 11.8571 | 4.5 |  | 94.5 | 0 | 66.15 | 28.35 | 0 | 94.5 | 94.5 | 0
| 8 | 753 | 13018 |  |  | Level 6 Residence | Access Scaffold |  | Tower | 2.5 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | ON HIRE | 2022-08-17 |  | 100% |  | 28 | 135 | 12.25 | 270 | 24.5 | 189 | 0 | 686 | 875 | 777 | 98 |  |  | #VALUE! | 189 | #VALUE! | #VALUE!
| 8 | 1274 | 13712 | 8288 |  | Level 6 To 10 Residence | Access Scaffold |  | Independent | 52 | 1 | 2 |  | 2 |  |  | 104 | m2-LxH | OFF HIRED | 2022-10-21 | 2022-11-28 | 100% |  | 5.5714 | 14 | 0.84 | 1456 | 87.36 | 1019.2 | 436.8 | 486.72 | 1942.72 | 1942.72 | 0
| 9 | 518 | 12726 | 8428 |  | Level 7 Hotel | Access Scaffold |  | INDEPENDENT | 7.5 | 1.3 | 6 | 1 | 5 |  |  | 37.5 | m2-LxH | OFF HIRED | 2022-07-14 | 2023-01-16 | 100% |  | 26.7143 | 14 | 0.84 | 525 | 31.5 | 367.5 | 157.5 | 841.5 | 1366.5 | 1366.5 | 0
| 9 | 502 | 12706 | 7735 |  | Level 7 Hotel | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 6 | 1 | 5 |  |  | 50 | m3 | OFF HIRED | 2022-07-13 | 2022-07-25 | 100% |  | 1.8571 | 7.5 |  | 375 | 0 | 262.5 | 112.5 | 0 | 375 | 375 | 0
| 9 | 517 | 12725 | 6717 |  | Level 7 Hotel | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 6 | 1 | 5 |  |  | 50 | m3 | OFF HIRED | 2022-07-14 | 2022-09-24 | 100% |  | 10.4286 | 7.5 | 0.7 | 375 | 35 | 262.5 | 112.5 | 365 | 740 | 740 | 0
| 9 | 517 | 12725 | 6717 |  | Level 7 Hotel | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 6 | 1 | 5 |  |  | 50 | m3 | OFF HIRED | 2022-07-14 | 2022-09-24 | 100% |  | 10.4286 | 7.5 | 0.7 | 375 | 35 | 262.5 | 112.5 | 365 | 740 | 740 | 0
| 9 | 778 | 13038 | 8147 |  | Level 7/13 Hotel | Access Scaffold |  | Tower | 2.5 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-19 | 2022-10-25 | 100% |  | 9.7143 | 135 |  | 270 | 0 | 189 | 81 | 0 | 270 | 270 | 0
| 9 | 763 | 13027 | 8069 |  | Level 7,8,9 Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-18 | 2022-10-04 | 100% |  | 6.8571 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 168 | 438 | 438 | 0
| 9 | 763 | 13027 | 8069 |  | Level 7,8,9 Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-18 | 2022-10-04 | 100% |  | 6.8571 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 168 | 438 | 438 | 0
| 9 | 763 | 13027 | 8069 |  | Level 7,8,9 Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-18 | 2022-10-04 | 100% |  | 6.8571 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 168 | 438 | 438 | 0
| 9 | 827 | 13095 | 8077 |  | Level 7 Hotel | Access Scaffold |  | Independent | 7.5 | 1.3 | 2.5 |  | 2.5 |  |  | 18.75 | m2-LxH | OFF HIRED | 2022-08-26 | 2022-10-06 | 100% |  | 6 | 14 | 0.84 | 262.5 | 15.75 | 183.75 | 78.75 | 94.5 | 357 | 357 | 0
| 9 | 939 | 13312 | 8296 |  | Level 7 & 8 hotel | Access Scaffold |  | Independent | 16 | 1 | 3 |  | 3 |  |  | 48 | m2-LxH | OFF HIRED | 2022-09-12 | 2022-11-30 | 100% |  | 11.4286 | 14 | 0.84 | 672 | 40.32 | 470.4 | 201.6 | 460.8 | 1132.8 | 1132.8 | 0
| 9 | 759 | 13024 | 7861 |  | Level 7 Residence | Access Scaffold |  | Tower | 2.5 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-17 | 2022-08-31 | 100% |  | 2.1429 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 52.5 | 322.5 | 322.5 | 0
| 9 | 945 | 13348 | 8566 |  | Level 7 to 23 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-14 | 2023-02-15 | 100% |  | 22.1429 | 135 |  | 270 | 0 | 189 | 81 | 0 | 270 | 189 | 81 |  |  | #VALUE! | 2457 | #VALUE! | #VALUE!
| 9 | 945 | 13348 | 8566 |  | Level 7 to 23 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-14 | 2023-02-15 | 100% |  | 22.1429 | 135 |  | 270 | 0 | 189 | 81 | 0 | 270 | 189 | 81 |  |  | #VALUE! | 2457 | #VALUE! | #VALUE!
| 9 | 945 | 13348 | 8566 |  | Level 7 to 23 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-14 | 2023-02-15 | 100% |  | 22.1429 | 135 |  | 270 | 0 | 189 | 81 | 0 | 270 | 189 | 81 |  |  | #VALUE! | 2457 | #VALUE! | #VALUE!
| 9 | 945 | 13348 | 8566 |  | Level 7 to 23 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-14 | 2023-02-15 | 100% |  | 22.1429 | 135 |  | 270 | 0 | 189 | 81 | 0 | 270 | 189 | 81 |  |  | #VALUE! | 2457 | #VALUE! | #VALUE!
| 9 | 945 | 13348 | 8566 |  | Level 7 to 23 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-14 | 2023-02-15 | 100% |  | 22.1429 | 135 |  | 270 | 0 | 189 | 81 | 0 | 270 | 189 | 81 |  |  | #VALUE! | 2457 | #VALUE! | #VALUE!
| 9 | 945 | 13348 | 8566 |  | Level 7 to 23 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-14 | 2023-02-15 | 100% |  | 22.1429 | 135 |  | 270 | 0 | 189 | 81 | 0 | 270 | 189 | 81 |  |  | #VALUE! | 2457 | #VALUE! | #VALUE!
| 9 | 945 | 13348 | 8566 |  | Level 7 to 23 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-14 | 2023-02-15 | 100% |  | 22.1429 | 135 |  | 270 | 0 | 189 | 81 | 0 | 270 | 189 | 81 |  |  | #VALUE! | 2457 | #VALUE! | #VALUE!
| 9 | 945 | 13348 | 8566 |  | Level 7 to 23 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-14 | 2023-02-15 | 100% |  | 22.1429 | 135 |  | 270 | 0 | 189 | 81 | 0 | 270 | 189 | 81 |  |  | #VALUE! | 2457 | #VALUE! | #VALUE!
| 9 | 945 | 13348 | 8566 |  | Level 7 to 23 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-14 | 2023-02-15 | 100% |  | 22.1429 | 135 |  | 270 | 0 | 189 | 81 | 0 | 270 | 189 | 81 |  |  | #VALUE! | 2457 | #VALUE! | #VALUE!
| 9 | 945 | 13348 | 8566 |  | Level 7 to 23 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-14 | 2023-02-15 | 100% |  | 22.1429 | 135 |  | 270 | 0 | 189 | 81 | 0 | 270 | 189 | 81 |  |  | #VALUE! | 2457 | #VALUE! | #VALUE!
| 9 | 945 | 13348 | 8566 |  | Level 7 to 23 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-14 | 2023-02-15 | 100% |  | 22.1429 | 135 |  | 270 | 0 | 189 | 81 | 0 | 270 | 189 | 81 |  |  | #VALUE! | 2457 | #VALUE! | #VALUE!
| 9 | 945 | 13348 | 8566 |  | Level 7 to 23 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-14 | 2023-02-15 | 100% |  | 22.1429 | 135 |  | 270 | 0 | 189 | 81 | 0 | 270 | 189 | 81 |  |  | #VALUE! | 2457 | #VALUE! | #VALUE!
| 9 | 945 | 13348 | 8566 |  | Level 7 to 23 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-14 | 2023-02-15 | 100% |  | 22.1429 | 135 |  | 270 | 0 | 189 | 81 | 0 | 270 | 189 | 81 |  |  | #VALUE! | 2457 | #VALUE! | #VALUE!
| 9 | 1053 | 13492 |  |  | Level 7 Hotel | Access Scaffold |  | Independent | 5.8 | 1.3 | 3 |  | 3 |  |  | 17.4 | m2-LxH | ON HIRE | 2022-09-26 |  | 100% |  | 22.2857 | 14 | 0.84 | 243.6 | 14.616 | 170.52 | 0 | 325.728 | 496.248 | 437.784 | 58.464 |  |  | #VALUE! | 170.52 | #VALUE! | #VALUE!
| 9 | 928 | 13300 | 8103 |  | Level 7 Hotel | Access Scaffold |  | Independent | 4.3 | 1.8 | 3 |  | 3 |  |  | 12.9 | m2-LxH | OFF HIRED | 2022-09-30 | 2022-10-14 | 100% |  | 2.1429 | 18 | 1.05 | 232.2 | 13.545 | 162.54 | 69.66 | 29.025 | 261.225 | 261.225 | 0
| 9 | 929 | 13300 | 8103 |  | Level 7 Hotel | Access Scaffold |  | Independent | 7.5 | 1.8 | 3 |  | 3 |  |  | 22.5 | m2-LxH | OFF HIRED | 2022-09-30 | 2022-10-14 | 100% |  | 2.1429 | 18 | 1.05 | 405 | 23.625 | 283.5 | 121.5 | 50.625 | 455.625 | 455.625 | 0
| 9 | 1181 | 13666 | 8276 |  | Level 7 Hotel | Birdcage Scaffold |  | Birdcage | 7.8 | 4 | 8 |  | 8 |  |  | 249.6 | m3 | OFF HIRED | 2022-10-11 | 2022-11-26 | 100% |  | 6.7143 | 7.5 | 0.7 | 1872 | 174.72 | 1310.4 | 561.6 | 1173.12 | 3045.12 | 3045.12 | 0
| 9 | 1402 | 13890 | 8484 |  | Level 7 Hotel | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 2 |  | 2 |  |  | 10 | m2-LxH | OFF HIRED | 2022-11-10 | 2023-01-02 | 100% |  | 7.7143 | 14 | 0.84 | 140 | 8.4 | 98 | 42 | 64.8 | 204.8 | 204.8 | 0
| 9 | 1402 | 13890 | 8484 |  | Level 7 Hotel | Cantiliver |  | Cantiliver | 5 | 0.6 |  |  |  | 1 |  | 3 | m2-LxW | OFF HIRED | 2022-11-10 | 2023-01-02 | 100% |  | 7.7143 | 36.5 | 3.15 | 109.5 | 9.45 | 76.65 | 32.85 | 72.9 | 182.4 | 182.4 | 0
| 9 | 1614 | 14149 |  |  | Level 7 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 2 |  | 2 |  |  | 2 | rm | ON HIRE | 2022-12-17 |  | 100% |  | 10.5714 | 135 | 12.25 | 270 | 24.5 | 189 | 0 | 259 | 448 | 350 | 98 |  |  | #VALUE! | 189 | #VALUE! | #VALUE!
| 9 | 1650 | 14185 | 8461 |  | Level 7 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 1.5 |  | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2022-12-22 | 2022-12-24 | 100% |  | 0.42857 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 60.75 | 7.875 | 210.375 | 210.375 | 0
| 9 | 1650 | 14185 | 8461 |  | Level 7 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 1.5 |  | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2022-12-22 | 2022-12-24 | 100% |  | 0.42857 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 60.75 | 7.875 | 210.375 | 210.375 | 0
| 9 | 1659 | 14194 | 8558 |  | Level 7 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 1 |  | 1 |  |  | 1 | rm | OFF HIRED | 2022-12-23 | 2023-02-11 | 100% |  | 7.2857 | 135 | 12.25 | 135 | 12.25 | 94.5 | 40.5 | 89.25 | 224.25 | 164.5 | 59.75 |  |  | #VALUE! | 189 | #VALUE! | #VALUE!
| 9 | 1659 | 14194 | 8558 |  | Level 7 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 1 |  | 1 |  |  | 1 | rm | OFF HIRED | 2022-12-23 | 2023-02-11 | 100% |  | 7.2857 | 135 | 12.25 | 135 | 12.25 | 94.5 | 40.5 | 89.25 | 224.25 | 164.5 | 59.75 |  |  | #VALUE! | 189 | #VALUE! | #VALUE!
| 9 | 1563 | 14097 | 8431 |  | Level 7 To 20 Hotel | Access Scaffold |  | INDEPENDENT | 155 | 1 | 2 |  | 2 |  |  | 310 | m2-LxH | OFF HIRED | 2022-12-09 | 2023-01-17 | 100% |  | 5.7143 | 14 | 0.84 | 4340 | 260.4 | 3038 | 1302 | 1488 | 5828 | 5828 | 0
| 10 |  | 12109 | 8117 |  | Level 8 To Ground | Edge Prorection |  | Edge Prorection | 200 | [6 empty] | 200 | lm | OFF HIRED | 2022-05-27 | 2022-10-18 | 100% |  | 20.7143 | 24 |  | 4800 | 0 | 3360 | 1440 | 0 | 4800 | 4800 | 0
| 10 |  | 12100 |  |  | Level 8 To 28 Hotel Tower | Edge Prorection | Edge Prorection | Edge Prorection | 150 | [6 empty] | 150 | lm |  | 2022-05-20 |  | 100% |  | 0 | 24 |  | 3600 | 0 | 2520 | 0 | 0 | 2520 | 2520 | 0
| 10 | 1553 | 14090 | 8558 |  | Level 8 Hotel | Access Scaffold |  | INDEPENDENT | 5 | 1 | 1.8 |  | 1.8 |  |  | 9 | m2-LxH | OFF HIRED | 2022-12-08 | 2023-02-11 | 100% |  | 9.4286 | 14 | 0.84 | 126 | 7.56 | 88.2 | 37.8 | 71.28 | 197.28 | 147.6 | 49.68 |  |  | #VALUE! | 88.2 | #VALUE! | #VALUE!
| 11 | 563 | 12776 | 7832 |  | Level 9 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-21 | 2022-08-17 | 100% |  | 4 | 135 |  | 270 | 0 | 189 | 81 | 0 | 270 | 270 | 0
| 11 | 562 | 12775 | 7832 |  | Level 9 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-21 | 2022-08-17 | 100% |  | 4 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 98 | 368 | 368 | 0
| 11 | 1272 | 13710 | 8173 |  | Level 9 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-10-21 | 2022-10-28 | 100% |  | 1.1429 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 28 | 298 | 298 | 0
| 11 | 1246 | 13784 | 8479 |  | Level 9 Hotel | Access Scaffold |  | Independent | 10 | 1.3 | 2 |  | 2 |  |  | 20 | m2-LxH | OFF HIRED | 2022-10-18 | 2022-12-31 | 100% |  | 10.7143 | 14 | 0.84 | 280 | 16.8 | 196 | 84 | 180 | 460 | 460 | 0
| 11 | 1146 | 13630 | 8109 |  | Level 9 Residence | Access Scaffold |  | Birdcage | 2.5 | 1.8 | 5 |  | 5 |  |  | 22.5 | m3 | OFF HIRED | 2022-10-06 | 2022-10-15 | 100% |  | 1.4286 | 7.5 | 0.7 | 168.75 | 15.75 | 118.125 | 50.625 | 22.5 | 191.25 | 191.25 | 0
| 11 | 1556 | 14088 | 8556 |  | Level 9 Hotel | Access Scaffold |  | INDEPENDENT | 5 | 1 | 1.8 |  | 1.8 |  |  | 9 | m2-LxH | OFF HIRED | 2022-12-08 | 2023-02-10 | 100% |  | 9.2857 | 14 | 0.84 | 126 | 7.56 | 88.2 | 37.8 | 70.2 | 196.2 | 147.6 | 48.6 |  |  | #VALUE! | 134.19 | #VALUE! | #VALUE!
| 11 | 1556 | 14088 | 8556 |  | Level 9 Hotel | Cantiliver |  | Cantiliver | 5 | 0.6 |  |  |  | 0.6 |  | 1.8 | m2-LxW | OFF HIRED | 2022-12-08 | 2023-02-10 | 100% |  | 9.2857 | 36.5 | 3.15 | 65.7 | 5.67 | 45.99 | 19.71 | 52.65 | 118.35 | 90.54 | 27.81 |  |  | #VALUE! | 134.19 | #VALUE! | #VALUE!
| 12 | 819 | 13088 | 8497 |  | Level 10 Hotel | Mobile Tower |  | Mobile Tower | 2.5 | 1.8 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-07-01 | 2023-01-06 | 100% |  | 27.1429 | 100 |  | 400 | 0 | 280 | 120 | 0 | 400 | 400 | 0
| 12 | 683 | 12892 | 8069 |  | Level 10,11,12,13,14,15,16,17, Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-08 | 2022-10-04 | 100% |  | 8.2857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 203 | 473 | 473 | 0
| 12 | 683 | 12892 | 8069 |  | Level 10,11,12,13,14,15,16,17, Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-08 | 2022-10-04 | 100% |  | 8.2857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 203 | 473 | 473 | 0
| 12 | 683 | 12892 | 8069 |  | Level 10,11,12,13,14,15,16,17, Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-08 | 2022-10-04 | 100% |  | 8.2857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 203 | 473 | 473 | 0
| 12 | 683 | 12892 | 8069 |  | Level 10,11,12,13,14,15,16,17, Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-08 | 2022-10-04 | 100% |  | 8.2857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 203 | 473 | 473 | 0
| 12 | 683 | 12892 | 8069 |  | Level 10,11,12,13,14,15,16,17, Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-08 | 2022-10-04 | 100% |  | 8.2857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 203 | 473 | 473 | 0
| 12 | 683 | 12892 | 8069 |  | Level 10,11,12,13,14,15,16,17, Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-08 | 2022-10-04 | 100% |  | 8.2857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 203 | 473 | 473 | 0
| 12 | 683 | 12892 | 8069 |  | Level 10,11,12,13,14,15,16,17, Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-08 | 2022-10-04 | 100% |  | 8.2857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 203 | 473 | 473 | 0
| 12 | 683 | 12892 | 8069 |  | Level 10,11,12,13,14,15,16,17, Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-08 | 2022-10-04 | 100% |  | 8.2857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 203 | 473 | 473 | 0
| 12 | 915 | 13288 | 8566 |  | Level 10 to 17 Hotel | Birdcage Scaffold |  | Birdcage | 7.5 | 6 | 28 |  | 28 |  |  | 1260 | m3 | OFF HIRED | 2022-09-08 | 2023-02-15 | 100% |  | 23 | 7.5 | 0.7 | 9450 | 882 | 6615 | 2835 | 20286 | 29736 | 25011 | 4725 |  |  | #VALUE! | 6615 | #VALUE! | #VALUE!
| 12 | 253 | 12367 | 6723 |  | Level 10 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-06-16 | 2022-09-26 | 100% |  | 14.7143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 360.5 | 630.5 | 630.5 | 0
| 12 | 492 | 12644 | 6736 |  | Level 10 Residance | Access Scaffold |  | INDEPENDENT | 3 | 1.3 | 5 | 1 | 4 |  |  | 12 | m2-LxH | OFF HIRED | 2022-07-07 | 2022-09-29 | 100% |  | 12.1429 | 14 | 0.84 | 168 | 10.08 | 117.6 | 50.4 | 122.4 | 290.4 | 290.4 | 0
| 12 | 536 | 12746 | 8498 |  | Level 10 Residance | Access Scaffold |  | INDEPENDENT | 18 | 0.6 | 5 | 1 | 4 |  |  | 72 | m2-LxH | OFF HIRED | 2022-07-17 | 2023-01-06 | 100% |  | 24.8571 | 14 | 0.84 | 1008 | 60.48 | 705.6 | 302.4 | 1503.36 | 2511.36 | 2511.36 | 0
| 12 | 770 | 13032 | 7870 |  | Level 10 Residence | Access Scaffold |  | Tower | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-19 | 2022-09-03 | 100% |  | 2.2857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 56 | 326 | 326 | 0
| 12 | 863 | 13135 | 7885 |  | Level 10 to 17 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-08-31 | 2022-09-13 | 100% |  | 2 | 135 |  | 337.5 | 0 | 236.25 | 101.25 | 0 | 337.5 | 337.5 | 0
| 12 | 1014 | 13397 | 8498 |  | Level 10 Residence | Birdcage Scaffold |  | Birdcage | 8 | 2.5 | 3.5 |  | 3.5 |  |  | 70 | m3 | OFF HIRED | 2022-09-22 | 2023-01-06 | 100% |  | 15.2857 | 7.5 | 0.7 | 525 | 49 | 367.5 | 157.5 | 749 | 1274 | 1274 | 0
| 12 | 863 | 13135 | 7885 |  | Level 10 to 17 Hotel | Cantiliver |  | Cantiliver | 1.5 | 1 |  |  |  | 1 |  | 1.5 | m2-LxW | OFF HIRED | 2022-08-31 | 2022-09-13 | 100% |  | 2 | 36.5 |  | 54.75 | 0 | 38.325 | 16.425 | 0 | 54.75 | 54.75 | 0
| 12 | 863 | 13135 | 7885 |  | Level 10 to 17 Hotel | Cantiliver |  | Cantiliver | 1.5 | 1 |  |  |  | 1 |  | 1.5 | m2-LxW | OFF HIRED | 2022-08-31 | 2022-09-13 | 100% |  | 2 | 36.5 |  | 54.75 | 0 | 38.325 | 16.425 | 0 | 54.75 | 54.75 | 0
| 12 | 863 | 13135 | 7885 |  | Level 10 to 17 Hotel | Cantiliver |  | Cantiliver | 1.5 | 1 |  |  |  | 1 |  | 1.5 | m2-LxW | OFF HIRED | 2022-08-31 | 2022-09-13 | 100% |  | 2 | 36.5 |  | 54.75 | 0 | 38.325 | 16.425 | 0 | 54.75 | 54.75 | 0
| 12 | 863 | 13135 | 7885 |  | Level 10 to 17 Hotel | Cantiliver |  | Cantiliver | 1.5 | 1 |  |  |  | 1 |  | 1.5 | m2-LxW | OFF HIRED | 2022-08-31 | 2022-09-13 | 100% |  | 2 | 36.5 |  | 54.75 | 0 | 38.325 | 16.425 | 0 | 54.75 | 54.75 | 0
| 12 | 863 | 13135 | 7885 |  | Level 10 to 17 Hotel | Cantiliver |  | Cantiliver | 1.5 | 1 |  |  |  | 1 |  | 1.5 | m2-LxW | OFF HIRED | 2022-08-31 | 2022-09-13 | 100% |  | 2 | 36.5 |  | 54.75 | 0 | 38.325 | 16.425 | 0 | 54.75 | 54.75 | 0
| 12 | 863 | 13135 | 7885 |  | Level 10 to 17 Hotel | Cantiliver |  | Cantiliver | 1.5 | 1 |  |  |  | 1 |  | 1.5 | m2-LxW | OFF HIRED | 2022-08-31 | 2022-09-13 | 100% |  | 2 | 36.5 |  | 54.75 | 0 | 38.325 | 16.425 | 0 | 54.75 | 54.75 | 0
| 12 | 863 | 13135 | 7885 |  | Level 10 to 17 Hotel | Cantiliver |  | Cantiliver | 1.5 | 1 |  |  |  | 1 |  | 1.5 | m2-LxW | OFF HIRED | 2022-08-31 | 2022-09-13 | 100% |  | 2 | 36.5 |  | 54.75 | 0 | 38.325 | 16.425 | 0 | 54.75 | 54.75 | 0
| 12 | 863 | 13135 | 7885 |  | Level 10 to 17 Hotel | Cantiliver |  | Cantiliver | 1.5 | 1 |  |  |  | 1 |  | 1.5 | m2-LxW | OFF HIRED | 2022-08-31 | 2022-09-13 | 100% |  | 2 | 36.5 |  | 54.75 | 0 | 38.325 | 16.425 | 0 | 54.75 | 54.75 | 0
| 12 | 1063 | 13500 | 8179 |  | Level 10 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-26 | 2022-11-01 | 100% |  | 5.2857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 129.5 | 399.5 | 399.5 | 0
| 12 | 1271 | 13709 | 8157 |  | Level 10 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-10-21 | 2022-10-27 | 100% |  | 1 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 24.5 | 294.5 | 294.5 | 0
| 12 | 1226 | 13764 | 8480 |  | Level 10 To 15 Residence | Access Scaffold |  | Independent | 66 | 0.6 | 2 |  | 2 |  |  | 132 | m2-LxH | OFF HIRED | 2022-10-16 | 2022-12-31 | 100% |  | 11 | 14 | 0.84 | 1848 | 110.88 | 1293.6 | 554.4 | 1219.68 | 3067.68 | 3067.68 | 0
| 12 | 1240 | 13778 | 8321 |  | Level 10 Hotel | Access Scaffold |  | Independent | 7.5 | 1.3 | 2 |  | 2 |  |  | 15 | m2-LxH | OFF HIRED | 2022-10-17 | 2022-12-11 | 100% |  | 8 | 14 | 0.84 | 210 | 12.6 | 147 | 63 | 100.8 | 310.8 | 310.8 | 0
| 12 | 1149 | 13633 | 8566 |  | Level 10 To 17 Hotel | Boarded Lift |  | Board Lift | 3.8 | 2.5 |  |  |  | 1 |  | 9.5 | m2-LxW | OFF HIRED | 2022-10-07 | 2023-02-15 | 100% |  | 18.8571 | 7.5 | 1.05 | 71.25 | 9.975 | 49.875 | 21.375 | 188.1 | 259.35 | 216.6 | 42.75 |  |  | #VALUE! | 1097.25 | #VALUE! | #VALUE!
| 12 | 1149 | 13633 | 8566 |  | Level 10 To 17 Hotel | Boarded Lift |  | Board Lift | 3.8 | 2.5 |  |  |  | 1 |  | 9.5 | m2-LxW | OFF HIRED | 2022-10-07 | 2023-02-15 | 100% |  | 18.8571 | 7.5 | 1.05 | 71.25 | 9.975 | 49.875 | 21.375 | 188.1 | 259.35 | 216.6 | 42.75 |  |  | #VALUE! | 1097.25 | #VALUE! | #VALUE!
| 12 | 1149 | 13633 | 8566 |  | Level 10 To 17 Hotel | Boarded Lift |  | Board Lift | 3.8 | 2.5 |  |  |  | 1 |  | 9.5 | m2-LxW | OFF HIRED | 2022-10-07 | 2023-02-15 | 100% |  | 18.8571 | 7.5 | 1.05 | 71.25 | 9.975 | 49.875 | 21.375 | 188.1 | 259.35 | 216.6 | 42.75 |  |  | #VALUE! | 1097.25 | #VALUE! | #VALUE!
| 12 | 1149 | 13633 | 8566 |  | Level 10 To 17 Hotel | Boarded Lift |  | Board Lift | 3.8 | 2.5 |  |  |  | 1 |  | 9.5 | m2-LxW | OFF HIRED | 2022-10-07 | 2023-02-15 | 100% |  | 18.8571 | 7.5 | 1.05 | 71.25 | 9.975 | 49.875 | 21.375 | 188.1 | 259.35 | 216.6 | 42.75 |  |  | #VALUE! | 1097.25 | #VALUE! | #VALUE!
| 12 | 1149 | 13633 | 8566 |  | Level 10 To 17 Hotel | Boarded Lift |  | Board Lift | 3.8 | 2.5 |  |  |  | 1 |  | 9.5 | m2-LxW | OFF HIRED | 2022-10-07 | 2023-02-15 | 100% |  | 18.8571 | 7.5 | 1.05 | 71.25 | 9.975 | 49.875 | 21.375 | 188.1 | 259.35 | 216.6 | 42.75 |  |  | #VALUE! | 1097.25 | #VALUE! | #VALUE!
| 12 | 1149 | 13633 | 8566 |  | Level 10 To 17 Hotel | Boarded Lift |  | Board Lift | 3.8 | 2.5 |  |  |  | 1 |  | 9.5 | m2-LxW | OFF HIRED | 2022-10-07 | 2023-02-15 | 100% |  | 18.8571 | 7.5 | 1.05 | 71.25 | 9.975 | 49.875 | 21.375 | 188.1 | 259.35 | 216.6 | 42.75 |  |  | #VALUE! | 1097.25 | #VALUE! | #VALUE!
| 12 | 1149 | 13633 | 8566 |  | Level 10 To 17 Hotel | Boarded Lift |  | Board Lift | 3.8 | 2.5 |  |  |  | 1 |  | 9.5 | m2-LxW | OFF HIRED | 2022-10-07 | 2023-02-15 | 100% |  | 18.8571 | 7.5 | 1.05 | 71.25 | 9.975 | 49.875 | 21.375 | 188.1 | 259.35 | 216.6 | 42.75 |  |  | #VALUE! | 1097.25 | #VALUE! | #VALUE!
| 12 | 1149 | 13633 | 8566 |  | Level 10 To 17 Hotel | Boarded Lift |  | Board Lift | 3.8 | 2.5 |  |  |  | 1 |  | 9.5 | m2-LxW | OFF HIRED | 2022-10-07 | 2023-02-15 | 100% |  | 18.8571 | 7.5 | 1.05 | 71.25 | 9.975 | 49.875 | 21.375 | 188.1 | 259.35 | 216.6 | 42.75 |  |  | #VALUE! | 1097.25 | #VALUE! | #VALUE!
| 12 | 1149 | 13633 | 8566 |  | Level 10 To 17 Hotel | Boarded Lift |  | Board Lift | 3.8 | 2.5 |  |  |  | 1 |  | 9.5 | m2-LxW | OFF HIRED | 2022-10-07 | 2023-02-15 | 100% |  | 18.8571 | 7.5 | 1.05 | 71.25 | 9.975 | 49.875 | 21.375 | 188.1 | 259.35 | 216.6 | 42.75 |  |  | #VALUE! | 1097.25 | #VALUE! | #VALUE!
| 12 | 1149 | 13633 | 8566 |  | Level 10 To 17 Hotel | Boarded Lift |  | Board Lift | 3.8 | 2.5 |  |  |  | 1 |  | 9.5 | m2-LxW | OFF HIRED | 2022-10-07 | 2023-02-15 | 100% |  | 18.8571 | 7.5 | 1.05 | 71.25 | 9.975 | 49.875 | 21.375 | 188.1 | 259.35 | 216.6 | 42.75 |  |  | #VALUE! | 1097.25 | #VALUE! | #VALUE!
| 12 | 1149 | 13633 | 8566 |  | Level 10 To 17 Hotel | Boarded Lift |  | Board Lift | 3.8 | 2.5 |  |  |  | 1 |  | 9.5 | m2-LxW | OFF HIRED | 2022-10-07 | 2023-02-15 | 100% |  | 18.8571 | 7.5 | 1.05 | 71.25 | 9.975 | 49.875 | 21.375 | 188.1 | 259.35 | 216.6 | 42.75 |  |  | #VALUE! | 1097.25 | #VALUE! | #VALUE!
| 12 | 1149 | 13633 | 8566 |  | Level 10 To 17 Hotel | Boarded Lift |  | Board Lift | 3.8 | 2.5 |  |  |  | 1 |  | 9.5 | m2-LxW | OFF HIRED | 2022-10-07 | 2023-02-15 | 100% |  | 18.8571 | 7.5 | 1.05 | 71.25 | 9.975 | 49.875 | 21.375 | 188.1 | 259.35 | 216.6 | 42.75 |  |  | #VALUE! | 1097.25 | #VALUE! | #VALUE!
| 12 | 1149 | 13633 | 8566 |  | Level 10 To 17 Hotel | Boarded Lift |  | Board Lift | 3.8 | 2.5 |  |  |  | 1 |  | 9.5 | m2-LxW | OFF HIRED | 2022-10-07 | 2023-02-15 | 100% |  | 18.8571 | 7.5 | 1.05 | 71.25 | 9.975 | 49.875 | 21.375 | 188.1 | 259.35 | 216.6 | 42.75 |  |  | #VALUE! | 1097.25 | #VALUE! | #VALUE!
| 12 | 1149 | 13633 | 8566 |  | Level 10 To 17 Hotel | Boarded Lift |  | Board Lift | 3.8 | 2.5 |  |  |  | 1 |  | 9.5 | m2-LxW | OFF HIRED | 2022-10-07 | 2023-02-15 | 100% |  | 18.8571 | 7.5 | 1.05 | 71.25 | 9.975 | 49.875 | 21.375 | 188.1 | 259.35 | 216.6 | 42.75 |  |  | #VALUE! | 1097.25 | #VALUE! | #VALUE!
| 12 | 1149 | 13633 | 8566 |  | Level 10 To 17 Hotel | Boarded Lift |  | Board Lift | 3.8 | 2.5 |  |  |  | 1 |  | 9.5 | m2-LxW | OFF HIRED | 2022-10-07 | 2023-02-15 | 100% |  | 18.8571 | 7.5 | 1.05 | 71.25 | 9.975 | 49.875 | 21.375 | 188.1 | 259.35 | 216.6 | 42.75 |  |  | #VALUE! | 1097.25 | #VALUE! | #VALUE!
| 12 | 1149 | 13633 | 8566 |  | Level 10 To 17 Hotel | Boarded Lift |  | Board Lift | 3.8 | 2.5 |  |  |  | 1 |  | 9.5 | m2-LxW | OFF HIRED | 2022-10-07 | 2023-02-15 | 100% |  | 18.8571 | 7.5 | 1.05 | 71.25 | 9.975 | 49.875 | 21.375 | 188.1 | 259.35 | 216.6 | 42.75 |  |  | #VALUE! | 1097.25 | #VALUE! | #VALUE!
| 12 | 1149 | 13633 | 8566 |  | Level 10 To 17 Hotel | Boarded Lift |  | Board Lift | 3.8 | 2.5 |  |  |  | 1 |  | 9.5 | m2-LxW | OFF HIRED | 2022-10-07 | 2023-02-15 | 100% |  | 18.8571 | 7.5 | 1.05 | 71.25 | 9.975 | 49.875 | 21.375 | 188.1 | 259.35 | 216.6 | 42.75 |  |  | #VALUE! | 1097.25 | #VALUE! | #VALUE!
| 12 | 1149 | 13633 | 8566 |  | Level 10 To 17 Hotel | Boarded Lift |  | Board Lift | 3.8 | 2.5 |  |  |  | 1 |  | 9.5 | m2-LxW | OFF HIRED | 2022-10-07 | 2023-02-15 | 100% |  | 18.8571 | 7.5 | 1.05 | 71.25 | 9.975 | 49.875 | 21.375 | 188.1 | 259.35 | 216.6 | 42.75 |  |  | #VALUE! | 1097.25 | #VALUE! | #VALUE!
| 12 | 1149 | 13633 | 8566 |  | Level 10 To 17 Hotel | Boarded Lift |  | Board Lift | 3.8 | 2.5 |  |  |  | 1 |  | 9.5 | m2-LxW | OFF HIRED | 2022-10-07 | 2023-02-15 | 100% |  | 18.8571 | 7.5 | 1.05 | 71.25 | 9.975 | 49.875 | 21.375 | 188.1 | 259.35 | 216.6 | 42.75 |  |  | #VALUE! | 1097.25 | #VALUE! | #VALUE!
| 12 | 1149 | 13633 | 8566 |  | Level 10 To 17 Hotel | Boarded Lift |  | Board Lift | 3.8 | 2.5 |  |  |  | 1 |  | 9.5 | m2-LxW | OFF HIRED | 2022-10-07 | 2023-02-15 | 100% |  | 18.8571 | 7.5 | 1.05 | 71.25 | 9.975 | 49.875 | 21.375 | 188.1 | 259.35 | 216.6 | 42.75 |  |  | #VALUE! | 1097.25 | #VALUE! | #VALUE!
| 12 | 1149 | 13633 | 8566 |  | Level 10 To 17 Hotel | Boarded Lift |  | Board Lift | 3.8 | 2.5 |  |  |  | 1 |  | 9.5 | m2-LxW | OFF HIRED | 2022-10-07 | 2023-02-15 | 100% |  | 18.8571 | 7.5 | 1.05 | 71.25 | 9.975 | 49.875 | 21.375 | 188.1 | 259.35 | 216.6 | 42.75 |  |  | #VALUE! | 1097.25 | #VALUE! | #VALUE!
| 12 | 1149 | 13633 | 8566 |  | Level 10 To 17 Hotel | Boarded Lift |  | Board Lift | 3.8 | 2.5 |  |  |  | 1 |  | 9.5 | m2-LxW | OFF HIRED | 2022-10-07 | 2023-02-15 | 100% |  | 18.8571 | 7.5 | 1.05 | 71.25 | 9.975 | 49.875 | 21.375 | 188.1 | 259.35 | 216.6 | 42.75 |  |  | #VALUE! | 1097.25 | #VALUE! | #VALUE!
| 12 | 1531 | 14068 | 8313 |  | Level 10 & 11 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 1.5 |  | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2022-12-06 | 2022-12-08 | 100% |  | 0.42857 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 60.75 | 7.875 | 210.375 | 210.375 | 0
| 12 | 1530 | 14068 | 8313 |  | Level 10 & 11 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 1.5 |  | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2022-12-06 | 2022-12-08 | 100% |  | 0.42857 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 60.75 | 7.875 | 210.375 | 210.375 | 0
| 12 | 1636 | 14172 |  |  | Level 10 Hotel | Access Scaffold |  | INDEPENDENT | 5 | 1 | 1.8 |  | 1.8 |  |  | 9 | m2-LxH | ON HIRE | 2022-12-20 |  | 100% |  | 10.1429 | 14 | 0.84 | 126 | 7.56 | 88.2 | 0 | 76.68 | 164.88 | 134.64 | 30.24 |  |  | #VALUE! | 134.19 | #VALUE! | #VALUE!
| 12 | 1530 | 14068 | 8313 |  | Level 10 & 11 Hotel | Cantiliver |  | Cantiliver | 1.3 | 0.6 |  |  |  | 0.6 |  | 0.468 | m2-LxW | OFF HIRED | 2022-12-06 | 2022-12-08 | 100% |  | 0.42857 | 36.5 | 3.15 | 17.082 | 1.4742 | 11.9574 | 5.1246 | 0.6318 | 17.7138 | 17.7138 | 0
| 12 | 1531 | 14068 | 8313 |  | Level 10 & 11 Hotel | Cantiliver |  | Cantiliver | 1.3 | 0.6 |  |  |  | 0.6 |  | 0.468 | m2-LxW | OFF HIRED | 2022-12-06 | 2022-12-08 | 100% |  | 0.42857 | 36.5 | 3.15 | 17.082 | 1.4742 | 11.9574 | 5.1246 | 0.6318 | 17.7138 | 17.7138 | 0
| 13 | 501 | 12705 | 7733 |  | Level 13 Hotel | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 6 | 1 | 5 |  |  | 50 | m3 | OFF HIRED | 2022-07-12 | 2022-07-21 | 100% |  | 1.4286 | 7.5 | 0.7 | 375 | 35 | 262.5 | 112.5 | 50 | 425 | 425 | 0
| 13 | 501 | 12705 | 7733 |  | Level 13 Hotel | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 6 | 1 | 5 |  |  | 50 | m3 | OFF HIRED | 2022-07-12 | 2022-07-21 | 100% |  | 1.4286 | 7.5 | 0.7 | 375 | 35 | 262.5 | 112.5 | 50 | 425 | 425 | 0
| 13 | 501 | 12705 | 7733 |  | Level 13 Hotel | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 6 | 1 | 5 |  |  | 50 | m3 | OFF HIRED | 2022-07-12 | 2022-07-21 | 100% |  | 1.4286 | 7.5 | 0.7 | 375 | 35 | 262.5 | 112.5 | 50 | 425 | 425 | 0
| 13 | 516 | 12724 | 7735 |  | Level 13 Hotel | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 6 | 1 | 5 |  |  | 50 | m3 | OFF HIRED | 2022-07-14 | 2022-07-25 | 100% |  | 1.7143 | 7.5 | 0.7 | 375 | 35 | 262.5 | 112.5 | 60 | 435 | 435 | 0
| 13 | 516 | 12724 | 7735 |  | Level 13 Hotel | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 6 | 1 | 5 |  |  | 50 | m3 | OFF HIRED | 2022-07-14 | 2022-07-25 | 100% |  | 1.7143 | 7.5 | 0.7 | 375 | 35 | 262.5 | 112.5 | 60 | 435 | 435 | 0
| 13 | 516 | 12724 | 7735 |  | Level 13 Hotel | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 6 | 1 | 5 |  |  | 50 | m3 | OFF HIRED | 2022-07-14 | 2022-07-25 | 100% |  | 1.7143 | 7.5 | 0.7 | 375 | 35 | 262.5 | 112.5 | 60 | 435 | 435 | 0
| 13 |  | 12883 | 6739 |  | Level 13,16,18 Hotel | Netting Instalation |  | Netting | 24 |  | 7 | 1 | 6 |  |  | 144 | m2-LxH | OFF HIRED | 2022-07-31 | 2022-09-28 | 100% |  | 8.5714 | 4.5 |  | 648 | 0 | 453.6 | 194.4 | 0 | 648 | 648 | 0
| 13 |  | 12883 | 6739 |  | Level 13,16,18 Hotel | Netting Instalation |  | Netting | 6.5 |  | 6 | 1 | 5 |  |  | 32.5 | m2-LxH | OFF HIRED | 2022-07-31 | 2022-09-28 | 100% |  | 8.5714 | 4.5 |  | 146.25 | 0 | 102.375 | 43.875 | 0 | 146.25 | 146.25 | 0
| 13 |  | 12883 | 6739 |  | Level 13,16,18 Hotel | Netting Instalation |  | Netting | 8 |  | 2 |  | 2 |  |  | 16 | m2-LxH | OFF HIRED | 2022-07-31 | 2022-09-28 | 100% |  | 8.5714 | 4.5 |  | 72 | 0 | 50.4 | 21.6 | 0 | 72 | 72 | 0
| 13 | 843 | 13113 | 8057 |  | Level 13 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-08-27 | 2022-10-03 | 100% |  | 5.4286 | 135 |  | 337.5 | 0 | 236.25 | 101.25 | 0 | 337.5 | 337.5 | 0
| 13 | 951 | 13327 | 8053 |  | Level 13/14 Hotel | Access Scaffold |  | Independent | 5 | 1.3 | 5 |  | 5 |  |  | 25 | m2-LxH | OFF HIRED | 2022-09-14 | 2022-10-02 | 100% |  | 2.7143 | 14 | 0.84 | 350 | 21 | 245 | 105 | 57 | 407 | 407 | 0
| 13 | 869 | 13140 | 7883 |  | Level 13 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 0.6 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-09-01 | 2022-09-12 | 100% |  | 1.7143 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 52.5 | 390 | 390 | 0
| 13 | 1012 | 13395 | 6717 |  | Level 13/10 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-21 | 2022-09-24 | 100% |  | 0.57143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 14 | 284 | 284 | 0
| 13 | 1012 | 13395 | 6717 |  | Level 13/10 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-21 | 2022-09-24 | 100% |  | 0.57143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 14 | 284 | 284 | 0
| 13 | 1109 | 13543 |  |  | Level 13 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 4 |  | 4 |  |  | 4 | rm | ON HIRE | 2022-10-03 |  | 100% |  | 21.2857 | 135 | 12.25 | 540 | 49 | 378 | 0 | 1043 | 1421 | 1225 | 196 |  |  | #VALUE! | 378 | #VALUE! | #VALUE!
| 13 | 1188 | 13673 | 8300 |  | Level 13 To 14 Hotel | Access Scaffold |  | Independent | 5 | 1.3 | 2.5 |  | 2.5 |  |  | 12.5 | m2-LxH | OFF HIRED | 2022-10-12 | 2022-12-05 | 100% |  | 7.8571 | 14 | 0.84 | 175 | 10.5 | 122.5 | 52.5 | 82.5 | 257.5 | 257.5 | 0
| 13 | 1190 | 13675 | 8572 |  | Level 13 Hotel | Access Scaffold |  | Independent | 5 | 1 | 2 |  | 2 |  |  | 10 | m2-LxH | OFF HIRED | 2022-10-12 | 2023-02-17 | 100% |  | 18.4286 | 14 | 0.84 | 140 | 8.4 | 98 | 42 | 154.8 | 294.8 | 232.4 | 62.4 |  |  | #VALUE! | 98 | #VALUE! | #VALUE!
| 13 | 1304 | 13742 | 8286 |  | Level 13 Residence | HEAVY DUTY TOWER |  | Tower | 1 | 0.6 | 1.5 |  | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2022-10-27 | 2022-11-28 | 100% |  | 4.7143 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 60.75 | 86.625 | 289.125 | 289.125 | 0
| 13 | 1372 | 13860 |  |  | Level 13 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 1.5 |  | 1.5 |  |  | 1.5 | rm | ON HIRE | 2022-11-05 |  | 100% |  | 16.5714 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 0 | 304.5 | 446.25 | 372.75 | 73.5 |  |  | #VALUE! | 180.075 | #VALUE! | #VALUE!
| 13 | 1372 | 13860 |  |  | Level 13 Hotel | Cantiliver |  | Cantiliver | 2.5 | 0.6 |  |  |  | 1 |  | 1.5 | m2-LxW | ON HIRE | 2022-11-05 |  | 100% |  | 16.5714 | 36.5 | 3.15 | 54.75 | 4.725 | 38.325 | 0 | 78.3 | 116.625 | 97.725 | 18.9 |  |  | #VALUE! | 180.075 | #VALUE! | #VALUE!
| 13 | 1559 | 14092 | 8436 |  | Level 13 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1 | 1.5 |  | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2022-12-09 | 2023-01-17 | 100% |  | 5.7143 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 60.75 | 105 | 307.5 | 307.5 | 0
| 13 | 1635 | 14171 | 8609 |  | Level 13 & 16 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-12-20 | 2023-01-26 | 100% |  | 5.4286 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 133 | 403 | 403 | 0
| 13 | 1634 | 14171 | 8609 |  | Level 13 & 16 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-12-20 | 2023-01-26 | 100% |  | 5.4286 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 133 | 403 | 403 | 0
| 13 | 1634 | 14171 | 8609 |  | Level 13 & 16 Hotel | Cantiliver |  | Cantiliver | 2.5 | 0.6 |  |  |  | 0.6 |  | 0.9 | m2-LxW | OFF HIRED | 2022-12-20 | 2023-01-26 | 100% |  | 5.4286 | 36.5 | 3.15 | 32.85 | 2.835 | 22.995 | 9.855 | 15.39 | 48.24 | 48.24 | 0
| 14 | 769 | 13031 | 6735 |  | Level 14 Residence | Access Scaffold |  | Tower | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-19 | 2022-09-28 | 100% |  | 5.8571 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 143.5 | 413.5 | 413.5 | 0
| 14 | 1259 | 13797 | 8313 |  | Level 14 Hotel | Access Scaffold |  | Independent | 2.5 | 1.8 | 2 |  | 2 |  |  | 5 | m2-LxH | OFF HIRED | 2022-10-20 | 2022-12-08 | 100% |  | 7.1429 | 18 | 1.05 | 90 | 5.25 | 63 | 27 | 37.5 | 127.5 | 127.5 | 0
| 14 | 1573 | 14106 | 8409 |  | Level 14 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 1.5 |  | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2022-12-10 | 2023-01-10 | 100% |  | 4.5714 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 60.75 | 84 | 286.5 | 286.5 | 0
| 15 | 578 | 12794 | 6701 |  | Level 15 Hotel | Access Scaffold |  | INDEPENDENT | 7 | 1 | 6 | 1 | 5 |  |  | 35 | m2-LxH | OFF HIRED | 2022-07-24 | 2022-09-19 | 100% |  | 8.2857 | 14 | 0.84 | 490 | 29.4 | 343 | 147 | 243.6 | 733.6 | 733.6 | 0
| 15 | 471 | 12627 | 6701 |  | Level 15 Hotel | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 6.5 | 1 | 5.5 |  |  | 55 | m3 | OFF HIRED | 2022-07-07 | 2022-09-19 | 100% |  | 10.7143 | 7.5 | 0.7 | 412.5 | 38.5 | 288.75 | 123.75 | 412.5 | 825 | 825 | 0
| 15 | 493 | 12645 | 6717 |  | Level 15 Hotel | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 6 | 1 | 5 |  |  | 50 | m3 | OFF HIRED | 2022-07-11 | 2022-09-24 | 100% |  | 10.8571 | 7.5 | 0.7 | 375 | 35 | 262.5 | 112.5 | 380 | 755 | 755 | 0
| 15 | 493 | 12645 | 6717 |  | Level 15 Hotel | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 6 | 1 | 5 |  |  | 50 | m3 | OFF HIRED | 2022-07-11 | 2022-09-24 | 100% |  | 10.8571 | 7.5 | 0.7 | 375 | 35 | 262.5 | 112.5 | 380 | 755 | 755 | 0
| 15 | 950 | 13325 | 8072 |  | Level 15/16 Hotel | Access Scaffold |  | Independent | 5 | 1.3 | 5 |  | 5 |  |  | 25 | m2-LxH | OFF HIRED | 2022-09-13 | 2022-10-05 | 100% |  | 3.2857 | 14 | 0.84 | 350 | 21 | 245 | 105 | 69 | 419 | 419 | 0
| 15 | 979 | 13357 | 6717 |  | Level 15 To 16 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 7 |  | 7 |  |  | 7 | rm | OFF HIRED | 2022-09-16 | 2022-09-24 | 100% |  | 1.2857 | 135 | 12.25 | 945 | 85.75 | 661.5 | 283.5 | 110.25 | 1055.25 | 1055.25 | 0
| 15 | 1130 | 13614 |  |  | Level 15/16 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3.5 |  | 3.5 |  |  | 3.5 | rm | ON HIRE | 2022-10-04 |  | 100% |  | 21.1429 | 135 | 12.25 | 472.5 | 42.875 | 330.75 | 0 | 906.5 | 1237.25 | 1065.75 | 171.5 |  |  | #VALUE! | 330.75 | #VALUE! | #VALUE!
| 15 | 1083 | 13540 | 8125 |  | Level 15 to 23 Residence | Access Scaffold |  | Independent | 27 | 0.6 | 2 |  | 2 |  |  | 54 | m2-LxH | OFF HIRED | 2022-10-01 | 2022-10-19 | 100% |  | 2.7143 | 14 | 0.84 | 756 | 45.36 | 529.2 | 226.8 | 123.12 | 879.12 | 879.12 | 0
| 15 | 1215 | 13751 |  |  | Level 15 Hotel | Access Scaffold |  | Independent | 5 | 1.3 | 4 |  | 4 |  |  | 20 | m2-LxH | ON HIRE | 2022-10-15 |  | 100% |  | 19.5714 | 14 | 0.84 | 280 | 16.8 | 196 | 0 | 328.8 | 524.8 | 457.6 | 67.2 |  |  | #VALUE! | 196 | #VALUE! | #VALUE!
| 15 | 1214 | 13700 |  |  | Level 15 Hotel | Access Scaffold |  | Independent | 5 | 1 | 2 |  | 2 |  |  | 10 | m2-LxH | ON HIRE | 2022-10-15 |  | 100% |  | 19.5714 | 14 | 0.84 | 140 | 8.4 | 98 | 0 | 164.4 | 262.4 | 228.8 | 33.6 |  |  | #VALUE! | 98 | #VALUE! | #VALUE!
| 15 | 1260 | 13798 | 8171 |  | Level 15 Hotel | Access Scaffold |  | Independent | 2.5 | 1.8 | 2 |  | 2 |  |  | 5 | m2-LxH | OFF HIRED | 2022-10-20 | 2022-10-29 | 100% |  | 1.4286 | 18 | 1.05 | 90 | 5.25 | 63 | 27 | 7.5 | 97.5 | 97.5 | 0
| 15 | 1413 | 14051 | 8313 |  | Level 15 & 16 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 1.5 |  | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2022-11-29 | 2022-12-08 | 100% |  | 1.4286 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 60.75 | 26.25 | 228.75 | 228.75 | 0
| 15 | 1514 | 14051 | 8313 |  | Level 15 & 16 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 1.5 |  | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2022-11-29 | 2022-12-08 | 100% |  | 1.4286 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 60.75 | 26.25 | 228.75 | 228.75 | 0
| 15 | 1545 | 14080 | 8484 |  | Level 15 Hotel | Access Scaffold |  | INDEPENDENT | 6.3 | 1.3 | 2 |  | 2 |  |  | 12.6 | m2-LxH | OFF HIRED | 2022-12-07 | 2023-01-02 | 100% |  | 3.8571 | 14 | 0.84 | 176.4 | 10.584 | 123.48 | 52.92 | 40.824 | 217.224 | 217.224 | 0
| 15 | 1544 | 14080 | 8484 |  | Level 15 Hotel | Access Scaffold |  | INDEPENDENT | 6.3 | 1.3 | 2 |  | 2 |  |  | 12.6 | m2-LxH | OFF HIRED | 2022-12-07 | 2023-01-02 | 100% |  | 3.8571 | 14 | 0.84 | 176.4 | 10.584 | 123.48 | 52.92 | 40.824 | 217.224 | 217.224 | 0
| 15 | 1544 | 14080 | 8484 |  | Level 15 Hotel | Cantiliver |  | Cantiliver | 6 | 0.6 |  |  |  | 0.6 |  | 2.16 | m2-LxW | ON HIRE | 2022-12-07 | 2023-01-02 | 100% |  | 12 | 36.5 | 3.15 | 78.84 | 6.804 | 55.188 | 0 | 81.648 | 136.836 | 109.62 | 27.216 |  |  | #VALUE! | 357.336 | #VALUE! | #VALUE!
| 15 | 1545 | 14080 | 8484 |  | Level 15 Hotel | Cantiliver |  | Cantiliver | 6 | 0.6 |  |  |  | 0.6 |  | 2.16 | m2-LxW | ON HIRE | 2022-12-07 | 2023-01-02 | 100% |  | 12 | 36.5 | 3.15 | 78.84 | 6.804 | 55.188 | 0 | 81.648 | 136.836 | 109.62 | 27.216 |  |  | #VALUE! | 357.336 | #VALUE! | #VALUE!
| 16 | 561 | 12774 | 6701 |  | Level 16 Hotel | Access Scaffold |  | INDEPENDENT | 26.5 | 1 | 3 | 1 | 2 |  |  | 53 | m2-LxH | OFF HIRED | 2022-07-20 | 2022-09-19 | 100% |  | 8.8571 | 14 | 0.84 | 742 | 44.52 | 519.4 | 222.6 | 394.32 | 1136.32 | 1136.32 | 0
| 16 | 584 | 12801 | 6737 |  | Level 16 Hotel | Access Scaffold |  | INDEPENDENT | 3 | 1.3 | 5 | 1 | 4 |  |  | 12 | m2-LxH | OFF HIRED | 2022-07-25 | 2022-09-26 | 100% |  | 9.1429 | 14 | 0.84 | 168 | 10.08 | 117.6 | 50.4 | 92.16 | 260.16 | 260.16 | 0
| 16 | 786 | 13047 | 8053 |  | Level 16 Hotel | Access Scaffold |  | Tower | 2.5 | 1.3 | 2.5 | 1 | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2022-08-17 | 2022-10-02 | 100% |  | 6.7143 | 135 |  | 202.5 | 0 | 141.75 | 60.75 | 0 | 202.5 | 202.5 | 0
| 16 | 775 | 13037 | 7874 |  | Level 16,17,18 Residence | Access Scaffold |  | Tower | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-19 | 2022-09-06 | 100% |  | 2.7143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 66.5 | 336.5 | 336.5 | 0
| 16 | 775 | 13037 | 7874 |  | Level 16,17,18 Residence | Access Scaffold |  | Tower | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-19 | 2022-09-06 | 100% |  | 2.7143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 66.5 | 336.5 | 336.5 | 0
| 16 | 775 | 13037 | 7874 |  | Level 16,17,18 Residence | Access Scaffold |  | Tower | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-19 | 2022-09-06 | 100% |  | 2.7143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 66.5 | 336.5 | 336.5 | 0
| 16 | 484 | 12635 | 7856 |  | Level 16 to 18 Residance | Access Scaffold |  | INDEPENDENT | 143 | 1.3 | 3.5 |  | 3.5 |  |  | 500.5 | m2-LxH | OFF HIRED | 2022-07-05 | 2022-08-26 | 100% |  | 7.5714 | 14 | 0.84 | 7007 | 420.42 | 4904.9 | 2102.1 | 3183.18 | 10190.18 | 10190.18 | 0
| 16 | 993 | 13375 | 8178 |  | Level 16 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-17 | 2022-11-01 | 100% |  | 6.5714 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 161 | 431 | 431 | 0
| 16 | 1051 | 13490 | 8296 |  | Level 16 To 18 Hotel | Access Scaffold |  | Independent | 20 | 1 | 2.5 |  | 2.5 |  |  | 50 | m2-LxH | OFF HIRED | 2022-09-26 | 2022-11-30 | 100% |  | 9.4286 | 14 | 0.84 | 700 | 42 | 490 | 210 | 396 | 1096 | 1096 | 0
| 16 | 1550 | 14083 | 8479 |  | Level 16 To 19 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 1.8 |  | 1.8 |  |  | 1.8 | rm | OFF HIRED | 2022-12-08 | 2022-12-31 | 100% |  | 3.4286 | 135 | 12.25 | 243 | 22.05 | 170.1 | 72.9 | 75.6 | 318.6 | 318.6 | 0
| 16 | 1548 | 14083 | 8479 |  | Level 16 To 19 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-12-08 | 2022-12-31 | 100% |  | 3.4286 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 84 | 354 | 354 | 0
| 16 | 1550 | 14083 | 8479 |  | Level 16 & 19 Hotel | Cantiliver |  | Cantiliver | 2.5 | 0.6 |  |  |  | 0.6 |  | 0.9 | m2-LxW | OFF HIRED | 2022-12-08 | 2022-12-31 | 100% |  | 3.4286 | 36.5 | 3.15 | 32.85 | 2.835 | 22.995 | 9.855 | 9.72 | 42.57 | 42.57 | 0
| 17 | 391 | 12549 | 7728 |  | Level 17 Hotel | Access Scaffold |  | INDEPENDENT | 6 | 1.3 | 4 | 1 | 3 |  |  | 18 | m2-LxH | OFF HIRED | 2022-06-28 | 2022-07-18 | 100% |  | 3 | 14 | 0.84 | 252 | 15.12 | 176.4 | 75.6 | 45.36 | 297.36 | 297.36 | 0
| 17 | 392 | 12549 | 7728 |  | Level 17 Hotel | Access Scaffold |  | INDEPENDENT | 4.5 | 1.3 | 4 | 1 | 3 |  |  | 13.5 | m2-LxH | OFF HIRED | 2022-06-28 | 2022-07-18 | 100% |  | 3 | 14 | 0.84 | 189 | 11.34 | 132.3 | 56.7 | 34.02 | 223.02 | 223.02 | 0
| 17 | 454 | 12611 | 7829 |  | Level 17 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 3.5 | 1 | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-07-07 | 2022-08-18 | 100% |  | 6.1429 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 188.125 | 525.625 | 525.625 | 0
| 17 | 455 | 12611 | 7829 |  | Level 17 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 3.5 | 1 | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-07-07 | 2022-08-18 | 100% |  | 6.1429 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 188.125 | 525.625 | 525.625 | 0
| 17 | 456 | 12611 | 7829 |  | Level 17 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 3.5 | 1 | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-07-07 | 2022-08-18 | 100% |  | 6.1429 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 188.125 | 525.625 | 525.625 | 0
| 17 | 458 | 12613 | 7829 |  | Level 17 Hotel | Access Scaffold |  | INDEPENDENT | 10 | 1.3 | 4 | 1 | 3 |  |  | 30 | m2-LxH | OFF HIRED | 2022-07-07 | 2022-08-18 | 100% |  | 6.1429 | 14 | 0.84 | 420 | 25.2 | 294 | 126 | 154.8 | 574.8 | 574.8 | 0
| 17 | 457 | 12612 | 7829 |  | Level 17 Hotel | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 3.5 | 1 | 2.5 |  |  | 12.5 | m2-LxH | OFF HIRED | 2022-07-07 | 2022-08-18 | 100% |  | 6.1429 | 14 | 0.84 | 175 | 10.5 | 122.5 | 52.5 | 64.5 | 239.5 | 239.5 | 0
| 17 | 603 | 12825 |  |  | Level 17 Hotel | Access Scaffold |  | Tower | 1.8 | 1.8 | 3.5 | 1 | 2.5 |  |  | 2.5 | rm | ON HIRE | 2022-07-27 |  | 100% |  | 31 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 0 | 949.375 | 1185.625 | 1063.125 | 122.5 |  |  | #VALUE! | 236.25 | #VALUE! | #VALUE!
| 17 | 695 | 12960 | 8293 |  | Level 17 Hotel | Access Scaffold |  | Tower | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-06 | 2022-11-29 | 100% |  | 16.5714 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 406 | 676 | 676 | 0
| 17 | 820 | 13089 | 7885 |  | Level 17 Hotel | Access Scaffold |  | Independent | 4 | 1.3 | 4 |  | 4 |  |  | 16 | m2-LxH | OFF HIRED | 2022-08-25 | 2022-09-13 | 100% |  | 2.8571 | 14 | 0 | 224 | 0 | 156.8 | 67.2 | 0 | 224 | 224 | 0
| 17 | 649 | 12872 | 7808 |  | Level 17 Hotel | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 3.5 | 1 | 2.5 |  |  | 25 | m3 | OFF HIRED | 2022-08-02 | 2022-08-05 | 100% |  | 0.57143 | 7.5 |  | 187.5 | 0 | 131.25 | 56.25 | 0 | 187.5 | 187.5 | 0
| 17 | 649 | 12872 | 7808 |  | Level 17 Hotel | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 3.5 | 1 | 2.5 |  |  | 25 | m3 | OFF HIRED | 2022-08-02 | 2022-08-05 | 100% |  | 0.57143 | 7.5 |  | 187.5 | 0 | 131.25 | 56.25 | 0 | 187.5 | 187.5 | 0
| 17 | 649 | 12872 | 7808 |  | Level 17 Hotel | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 3.5 | 1 | 2.5 |  |  | 25 | m3 | OFF HIRED | 2022-08-02 | 2022-08-05 | 100% |  | 0.57143 | 7.5 |  | 187.5 | 0 | 131.25 | 56.25 | 0 | 187.5 | 187.5 | 0
| 17 | 744 | 13002 | 8069 |  | Level 17 Hotel | Birdcage Scaffold |  | Birdcage | 9 | 6 | 4 | 1 | 3 |  |  | 162 | m3 | OFF HIRED | 2022-08-07 | 2022-10-04 | 100% |  | 8.4286 | 7.5 | 0.7 | 1215 | 113.4 | 850.5 | 364.5 | 955.8 | 2170.8 | 2170.8 | 0
| 17 | 726 | 12994 | 6706 |  | Level 17 Residence | Birdcage Scaffold |  | Birdcage | 7.5 | 2.5 | 4 | 1 | 3 |  |  | 56.25 | m3 | OFF HIRED | 2022-08-15 | 2022-09-21 | 100% |  | 5.4286 | 7.5 | 0.7 | 421.875 | 39.375 | 295.3125 | 126.5625 | 213.75 | 635.625 | 635.625 | 0
| 17 | 932 | 13303 | 8077 |  | Level 17 Hotel | Access Scaffold |  | Independent | 6 | 1.3 | 2.5 |  | 2.5 |  |  | 15 | m2-LxH | OFF HIRED | 2022-09-10 | 2022-10-06 | 100% |  | 3.8571 | 14 | 0.84 | 210 | 12.6 | 147 | 63 | 48.6 | 258.6 | 258.6 | 0
| 17 | 604 | 12826 | 6701 |  | Level 17 Hotel | Access Scaffold |  | Independent | 4 | 1.3 | 3 | 1 | 2 |  |  | 8 | m2-LxH | OFF HIRED | 2022-07-27 | 2022-09-19 | 100% |  | 7.8571 | 14 | 0.84 | 112 | 6.72 | 78.4 | 33.6 | 52.8 | 164.8 | 164.8 | 0
| 17 | 1010 | 13394 | 8072 |  | Level 17/16 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-21 | 2022-10-05 | 100% |  | 2.1429 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 52.5 | 322.5 | 322.5 | 0
| 17 | 1011 | 13394 | 8072 |  | Level 17/16 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-21 | 2022-10-05 | 100% |  | 2.1429 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 52.5 | 322.5 | 322.5 | 0
| 17 | 987 | 13367 | 6717 |  | Level 17 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-17 | 2022-09-24 | 100% |  | 1.1429 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 28 | 298 | 298 | 0
| 17 | 1 | 13277 | 8636 |  | Level 17 Residence | Boarded Lift |  | Board Lift | 20 | 1.3 |  |  |  | 1 |  | 26 | m2-LxW | OFF HIRED | 2022-09-07 | 2023-02-06 | 100% |  | 21.8571 | 7.5 | 1.05 | 195 | 27.3 | 136.5 | 58.5 | 596.7 | 791.7 | 709.8 | 81.9 |  |  | #VALUE! | 2658.6 | #VALUE! | #VALUE!
| 17 | 1 | 13277 | 8636 |  | Level 17 Residence | Boarded Lift |  | Board Lift | 20 | 1.3 |  |  |  | 1 |  | 26 | m2-LxW | OFF HIRED | 2022-09-07 | 2023-02-06 | 100% |  | 21.8571 | 7.5 | 1.05 | 195 | 27.3 | 136.5 | 58.5 | 596.7 | 791.7 | 709.8 | 81.9 |  |  | #VALUE! | 2658.6 | #VALUE! | #VALUE!
| 17 | 1 | 13277 | 8636 |  | Level 17 Residence | Boarded Lift |  | Board Lift | 20 | 1.3 |  |  |  | 1 |  | 26 | m2-LxW | OFF HIRED | 2022-09-07 | 2023-02-06 | 100% |  | 21.8571 | 7.5 | 1.05 | 195 | 27.3 | 136.5 | 58.5 | 596.7 | 791.7 | 709.8 | 81.9 |  |  | #VALUE! | 2658.6 | #VALUE! | #VALUE!
| 17 | 1 | 13277 | 8636 |  | Level 17 Residence | Boarded Lift |  | Board Lift | 20 | 1.3 |  |  |  | 1 |  | 26 | m2-LxW | OFF HIRED | 2022-09-07 | 2023-02-06 | 100% |  | 21.8571 | 7.5 | 1.05 | 195 | 27.3 | 136.5 | 58.5 | 596.7 | 791.7 | 709.8 | 81.9 |  |  | #VALUE! | 2658.6 | #VALUE! | #VALUE!
| 17 | 1 | 13277 | 8636 |  | Level 17 Residence | Boarded Lift |  | Board Lift | 20 | 1.3 |  |  |  | 1 |  | 26 | m2-LxW | OFF HIRED | 2022-09-07 | 2023-02-06 | 100% |  | 21.8571 | 7.5 | 1.05 | 195 | 27.3 | 136.5 | 58.5 | 596.7 | 791.7 | 709.8 | 81.9 |  |  | #VALUE! | 2658.6 | #VALUE! | #VALUE!
| 17 | 1 | 13277 | 8636 |  | Level 17 Residence | Boarded Lift |  | Board Lift | 20 | 1.3 |  |  |  | 1 |  | 26 | m2-LxW | OFF HIRED | 2022-09-07 | 2023-02-06 | 100% |  | 21.8571 | 7.5 | 1.05 | 195 | 27.3 | 136.5 | 58.5 | 596.7 | 791.7 | 709.8 | 81.9 |  |  | #VALUE! | 2658.6 | #VALUE! | #VALUE!
| 17 | 1 | 13277 | 8636 |  | Level 17 Residence | Cantiliver |  | Cantiliver | 20 | 0.6 |  |  |  | 1 |  | 12 | m2-LxW | OFF HIRED | 2022-09-07 | 2023-02-06 | 100% |  | 21.8571 | 36.5 | 3.15 | 438 | 37.8 | 306.6 | 131.4 | 826.2 | 1264.2 | 1100.4 | 163.8 |  |  | #VALUE! | 2658.6 | #VALUE! | #VALUE!
| 17 | 1 | 13277 | 8636 |  | Level 17 Residence | Cantiliver |  | Cantiliver | 20 | 0.6 |  |  |  | 1 |  | 12 | m2-LxW | OFF HIRED | 2022-09-07 | 2023-02-06 | 100% |  | 21.8571 | 36.5 | 3.15 | 438 | 37.8 | 306.6 | 131.4 | 826.2 | 1264.2 | 1100.4 | 163.8 |  |  | #VALUE! | 2658.6 | #VALUE! | #VALUE!
| 17 | 1 | 13277 | 8636 |  | Level 17 Residence | Cantiliver |  | Cantiliver | 20 | 0.6 |  |  |  | 1 |  | 12 | m2-LxW | OFF HIRED | 2022-09-07 | 2023-02-06 | 100% |  | 21.8571 | 36.5 | 3.15 | 438 | 37.8 | 306.6 | 131.4 | 826.2 | 1264.2 | 1100.4 | 163.8 |  |  | #VALUE! | 2658.6 | #VALUE! | #VALUE!
| 17 | 1 | 13277 | 8636 |  | Level 17 Residence | Cantiliver |  | Cantiliver | 20 | 0.6 |  |  |  | 1 |  | 12 | m2-LxW | OFF HIRED | 2022-09-07 | 2023-02-06 | 100% |  | 21.8571 | 36.5 | 3.15 | 438 | 37.8 | 306.6 | 131.4 | 826.2 | 1264.2 | 1100.4 | 163.8 |  |  | #VALUE! | 2658.6 | #VALUE! | #VALUE!
| 17 | 1 | 13277 | 8636 |  | Level 17 Residence | Cantiliver |  | Cantiliver | 20 | 0.6 |  |  |  | 1 |  | 12 | m2-LxW | OFF HIRED | 2022-09-07 | 2023-02-06 | 100% |  | 21.8571 | 36.5 | 3.15 | 438 | 37.8 | 306.6 | 131.4 | 826.2 | 1264.2 | 1100.4 | 163.8 |  |  | #VALUE! | 2658.6 | #VALUE! | #VALUE!
| 17 | 1 | 13277 | 8636 |  | Level 17 Residence | Cantiliver |  | Cantiliver | 20 | 0.6 |  |  |  | 1 |  | 12 | m2-LxW | OFF HIRED | 2022-09-07 | 2023-02-06 | 100% |  | 21.8571 | 36.5 | 3.15 | 438 | 37.8 | 306.6 | 131.4 | 826.2 | 1264.2 | 1100.4 | 163.8 |  |  | #VALUE! | 2658.6 | #VALUE! | #VALUE!
| 17 | 1251 | 13789 | 8171 |  | Level 17 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-10-19 | 2022-10-29 | 100% |  | 1.5714 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 48.125 | 385.625 | 385.625 | 0
| 17 | 1196 | 13682 | 8254 |  | Level 17 Hotel | Access Scaffold |  | Independent | 7 | 1 | 2 |  | 2 |  |  | 14 | m2-LxH | OFF HIRED | 2022-10-13 | 2022-11-18 | 100% |  | 5.2857 | 14 | 0.84 | 196 | 11.76 | 137.2 | 58.8 | 62.16 | 258.16 | 258.16 | 0
| 17 | 1268 | 13706 | 8157 |  | Level 17 Hotel | Access Scaffold |  | Independent | 5 | 1.3 | 2 |  | 2 |  |  | 10 | m2-LxH | OFF HIRED | 2022-10-21 | 2022-10-27 | 100% |  | 1 | 14 | 0.84 | 140 | 8.4 | 98 | 42 | 8.4 | 148.4 | 148.4 | 0
| 17 | 1181 | 13666 | 8276 |  | Level 7 Hotel | Boarded Lift |  | Board Lift | 7.8 | 4 |  |  |  | 1 |  | 31.2 | m2-LxW | OFF HIRED | 2022-10-11 | 2022-11-26 | 100% |  | 6.7143 | 7.5 | 1.05 | 234 | 32.76 | 163.8 | 70.2 | 219.96 | 453.96 | 453.96 | 0
| 17 | 1251 | 13789 | 8171 |  | Level 17 Hotel | Cantiliver |  | Cantiliver | 2.5 | 0.6 |  |  |  | 1 |  | 1.5 | m2-LxW | OFF HIRED | 2022-10-19 | 2022-10-29 | 100% |  | 1.5714 | 36.5 | 3.15 | 54.75 | 4.725 | 38.325 | 16.425 | 7.425 | 62.175 | 62.175 | 0
| 17 | 1483 | 13971 | 8293 |  | Level 17 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 1.5 |  | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2022-11-23 | 2022-11-29 | 100% |  | 1 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 60.75 | 18.375 | 220.875 | 220.875 | 0
| 17 | 1363 | 13851 |  |  | Level 17 Hotel | Access Scaffold |  | Independent | 6 | 1.8 | 2 |  | 2 |  |  | 12 | m2-LxH | ON HIRE | 2022-11-04 |  | 100% |  | 16.7143 | 18 | 1.05 | 216 | 12.6 | 151.2 | 0 | 210.6 | 361.8 | 311.4 | 50.4 |  |  | #VALUE! | 304.5 | #VALUE! | #VALUE!
| 17 | 1363 | 13851 |  |  | Level 17 Hotel | Cantiliver |  | Cantiliver | 6 | 1 |  |  |  | 1 |  | 6 | m2-LxW | ON HIRE | 2022-11-04 |  | 100% |  | 16.7143 | 36.5 | 3.15 | 219 | 18.9 | 153.3 | 0 | 315.9 | 469.2 | 393.6 | 75.6 |  |  | #VALUE! | 304.5 | #VALUE! | #VALUE!
| 17 | 1504 | 13991 | 8428 |  | Level 17 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-11-28 | 2023-01-16 | 100% |  | 7.1429 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 175 | 445 | 445 | 0
| 17 | 1525 | 14063 | 8457 |  | Level 17 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.8 | 5 |  | 5 |  |  | 5 | rm | OFF HIRED | 2022-12-05 | 2022-12-22 | 100% |  | 2.5714 | 135 | 12.25 | 675 | 61.25 | 472.5 | 202.5 | 157.5 | 832.5 | 832.5 | 0
| 17 | 1546 | 14081 |  |  | Level 17 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.8 | 1.5 |  | 1.5 |  |  | 1.5 | rm | ON HIRE | 2022-12-07 |  | 100% |  | 12 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 0 | 220.5 | 362.25 | 288.75 | 73.5 |  |  | #VALUE! | 141.75 | #VALUE! | #VALUE!
| 17 | 1668 | 14253 | 8418 |  | Level 17 Hotel | Access Scaffold |  | INDEPENDENT | 9.1 | 1.3 | 3 |  | 3 |  |  | 27.3 | m2-LxH | OFF HIRED | 2022-12-24 | 2023-01-12 | 100% |  | 2.8571 | 14 | 0.84 | 382.2 | 22.932 | 267.54 | 114.66 | 65.52 | 447.72 | 447.72 | 0
| 17 | 1538 | 14074 | 8608 |  | Level 17 Hotel | Birdcage Scaffold |  | Birdcage | 7 | 2.5 | 1.8 |  | 1.8 |  |  | 31.5 | m3 | OFF HIRED | 2022-12-06 | 2023-01-25 | 100% |  | 7.2857 | 7.5 | 0.7 | 236.25 | 22.05 | 165.375 | 70.875 | 160.65 | 396.9 | 396.9 | 0
| 18 | 362 | 12515 | 8296 |  | Level 18 Hotel | Access Scaffold |  | INDEPENDENT | 7.5 | 1.3 | 5 | 1 | 4 |  |  | 30 | m2-LxH | OFF HIRED | 2022-06-26 | 2022-11-30 | 100% |  | 22.5714 | 14 |  | 420 | 0 | 294 | 126 | 0 | 420 | 420 | 0
| 18 | 363 | 12515 | 8296 |  | Level 18 Hotel | Access Scaffold |  | INDEPENDENT | 7.5 | 1.3 | 5 | 1 | 4 |  |  | 30 | m2-LxH | OFF HIRED | 2022-06-26 | 2022-11-30 | 100% |  | 22.5714 | 14 |  | 420 | 0 | 294 | 126 | 0 | 420 | 420 | 0
| 18 | 382 | 12540 | 6739 |  | Level 18 Hotel | Access Scaffold |  | INDEPENDENT | 10 | 1.3 | 5 | 1 | 4 |  |  | 40 | m2-LxH | OFF HIRED | 2022-06-28 | 2022-09-28 | 100% |  | 13.2857 | 14 |  | 560 | 0 | 392 | 168 | 0 | 560 | 560 | 0
| 18 | 382 | 12540 | 6739 |  | Level 18 Hotel | Access Scaffold |  | INDEPENDENT | 8 | 6 | 5 | 1 | 4 |  |  | 32 | m2-LxH | OFF HIRED | 2022-06-28 | 2022-09-28 | 100% |  | 13.2857 | 14 |  | 448 | 0 | 313.6 | 134.4 | 0 | 448 | 448 | 0
| 18 | 383 | 12542 | 7743 |  | Level 18 To 22 Hotel | Access Scaffold |  | INDEPENDENT | 65 | 1.3 | 3.5 | 1 | 2.5 |  |  | 162.5 | m2-LxH | OFF HIRED | 2022-06-28 | 2022-07-29 | 100% |  | 4.5714 | 14 | 0.84 | 2275 | 136.5 | 1592.5 | 682.5 | 624 | 2899 | 2899 | 0
| 18 | 337 | 12438 | 7717 |  | Level 18 Hotel | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 9 | 1 | 8 |  |  | 80 | m3 | OFF HIRED | 2022-06-23 | 2022-07-11 | 100% |  | 2.7143 | 7.5 | 0.7 | 600 | 56 | 420 | 180 | 152 | 752 | 752 | 0
| 18 | 359 | 12513 | 7717 |  | Level 18 Hotel | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 9 | 1 | 8 |  |  | 80 | m3 | OFF HIRED | 2022-06-26 | 2022-07-11 | 100% |  | 2.2857 | 7.5 | 0.7 | 600 | 56 | 420 | 180 | 128 | 728 | 728 | 0
| 18 | 359 | 12513 | 7717 |  | Level 18 Hotel | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 9 | 1 | 8 |  |  | 80 | m3 | OFF HIRED | 2022-06-26 | 2022-07-11 | 100% |  | 2.2857 | 7.5 | 0.7 | 600 | 56 | 420 | 180 | 128 | 728 | 728 | 0
| 18 | 421 | 12582 | 7842 |  | Level 18 Hotel | Mobile Tower |  | Mobile Tower | 2.5 | 1.3 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-07-01 | 2022-08-25 | 100% |  | 8 | 100 | 10.15 | 400 | 40.6 | 280 | 120 | 324.8 | 724.8 | 724.8 | 0
| 18 | 422 | 12582 | 7842 |  | Level 18 Hotel | Mobile Tower |  | Mobile Tower | 2.5 | 1.3 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-07-01 | 2022-08-25 | 100% |  | 8 | 100 | 10.15 | 400 | 40.6 | 280 | 120 | 324.8 | 724.8 | 724.8 | 0
| 18 | 567 | 12780 | 6739 |  | Level 18 Hotel | Access Scaffold |  | INDEPENDENT | 6.5 | 1.3 | 4.5 | 1 | 3.5 |  |  | 22.75 | m2-LxH | OFF HIRED | 2022-07-21 | 2022-09-28 | 100% |  | 10 | 14 |  | 318.5 | 0 | 222.95 | 95.55 | 0 | 318.5 | 318.5 | 0
| 18 | 413 | 12572 | 7826 |  | Level 18 Hotel | Access Scaffold |  | INDEPENDENT | 6.5 | 1.3 | 4 | 1 | 3 |  |  | 19.5 | m2-LxH | OFF HIRED | 2022-07-01 | 2022-08-18 | 100% |  | 7 | 14 | 0.84 | 273 | 16.38 | 191.1 | 81.9 | 114.66 | 387.66 | 387.66 | 0
| 18 | 515 | 12723 | 8138 |  | Level 18 Hotel | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 5 | 1 | 4 |  |  | 16 | m2-LxH | OFF HIRED | 2022-07-14 | 2022-10-24 | 100% |  | 14.7143 | 14 | 0.84 | 224 | 13.44 | 156.8 | 67.2 | 197.76 | 421.76 | 421.76 | 0
| 18 | 578 | 12805 | 6701 |  | Level 18 Hotel | Access Scaffold |  | INDEPENDENT | 14 | 1.3 | 3 | 1 | 2 |  |  | 28 | m2-LxH | OFF HIRED | 2022-07-25 | 2022-09-19 | 100% |  | 8.1429 | 14 | 0.84 | 392 | 23.52 | 274.4 | 117.6 | 191.52 | 583.52 | 583.52 | 0
| 18 | 566 | 12779 | 6739 |  | Level 18 Hotel | Birdcage Scaffold |  | Birdcage | 10 | 6 | 4.5 | 1 | 3.5 |  |  | 210 | m3 | OFF HIRED | 2022-07-21 | 2022-09-28 | 100% |  | 10 | 7.5 | 0.7 | 1575 | 147 | 1102.5 | 472.5 | 1470 | 3045 | 3045 | 0
| 18 | 515 | 12723 | 8138 |  | Level 18 Hotel | Cantiliver |  | Cantiliver | 4 | 1 |  |  |  | 1 |  | 4 | m2-LxW | OFF HIRED | 2022-07-14 | 2022-10-24 | 100% |  | 14.7143 | 36.5 | 3.15 | 146 | 12.6 | 102.2 | 43.8 | 185.4 | 331.4 | 331.4 | 0
| 18 | 669 | 12893 | 8092 |  | Level 18 Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-08-08 | 2022-10-10 | 100% |  | 9.1429 | 135 |  | 540 | 0 | 378 | 162 | 0 | 540 | 540 | 0
| 18 | 729 | 12985 | 8053 |  | Level 18 Hotel | Access Scaffold |  | Tower | 1.8 | 1.8 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-08-12 | 2022-10-02 | 100% |  | 7.4286 | 135 | 12.25 | 540 | 49 | 378 | 162 | 364 | 904 | 904 | 0
| 18 | 802 | 13063 | 8279 |  | Level 18 Hotel | Birdcage Scaffold |  | Birdcage | 19.5 | 6.3 | 4 |  | 4 |  |  | 491.4 | m3 | OFF HIRED | 2022-08-23 | 2022-11-26 | 100% |  | 13.7143 | 7.5 | 0.7 | 3685.5 | 343.98 | 2579.85 | 1105.65 | 4717.44 | 8402.94 | 8402.94 | 0
| 18 |  | 13062 | 8146 |  | Level 18 Hotel | Birdcage Scaffold |  | Birdcage | 10 | 8 | 4 |  | 4 |  |  | 320 | m3 | OFF HIRED | 2022-08-23 | 2022-10-25 | 100% |  | 9.1429 | 7.5 | 0.7 | 2400 | 224 | 1680 | 720 | 2048 | 4448 | 4448 | 0
| 18 | 413 | 13107 | 8350 |  | Level 18 Hotel | Birdcage Scaffold |  | Birdcage | 14 | 2.5 | 4 |  | 4 |  |  | 140 | m3 | OFF HIRED | 2022-08-26 | 2022-12-21 | 100% |  | 16.8571 | 7.5 | 0.7 | 1050 | 98 | 735 | 315 | 1652 | 2702 | 2702 | 0
| 18 | 360 | 12514 | 6739 |  | Level 18 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.8 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-06-26 | 2022-09-28 | 100% |  | 13.5714 | 135 |  | 540 | 0 | 378 | 162 | 0 | 540 | 540 | 0
| 18 | 361 | 12514 | 6739 |  | Level 18 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.8 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-06-26 | 2022-09-28 | 100% |  | 13.5714 | 135 |  | 540 | 0 | 378 | 162 | 0 | 540 | 540 | 0
| 18 | 364 | 12514 | 6739 |  | Level 18 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2.5 | 1 | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2022-06-26 | 2022-09-28 | 100% |  | 13.5714 | 135 |  | 202.5 | 0 | 141.75 | 60.75 | 0 | 202.5 | 202.5 | 0
| 18 | 1042 | 13479 | 8072 |  | Level 18 To 19 Hotel | Access Scaffold |  | Independent | 4 | 1.3 | 8 |  | 8 |  |  | 32 | m2-LxH | OFF HIRED | 2022-09-24 | 2022-10-05 | 100% |  | 1.7143 | 14 | 0.84 | 448 | 26.88 | 313.6 | 134.4 | 46.08 | 494.08 | 494.08 | 0
| 18 | 992 | 13374 | 8457 |  | Level 18 Hotel | Access Scaffold |  | Independent | 10 | 0.6 | 4 |  | 4 |  |  | 40 | m2-LxH | OFF HIRED | 2022-09-17 | 2022-12-22 | 100% |  | 13.8571 | 14 | 0.84 | 560 | 33.6 | 392 | 168 | 465.6 | 1025.6 | 1025.6 | 0
| 18 | 1163 | 13648 | 8100 |  | Level 18 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-10-10 | 2022-10-04 | 100% |  | -0.71429 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 0 | 270 | 270 | 0
| 18 | 1124 | 13608 | 8296 |  | Level 18 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-10-04 | 2022-11-30 | 100% |  | 8.2857 | 135 | 12.25 | 540 | 49 | 378 | 162 | 406 | 946 | 946 | 0
| 18 | 1189 | 13674 | 8472 |  | Level 18 To 30 Hotel | Access Scaffold |  | Independent | 151 | 1 | 1.5 |  | 1.5 |  |  | 226.5 | m2-LxH | OFF HIRED | 2022-10-13 | 2022-12-27 | 100% |  | 10.8571 | 14 | 0.84 | 3171 | 190.26 | 2219.7 | 951.3 | 2065.68 | 5236.68 | 5236.68 | 0
| 18 | 1094 | 13527 | 8457 |  | Level 18 Hotel | Access Scaffold |  | Independent | 7.5 | 0.6 | 4 |  | 4 |  |  | 30 | m2-LxH | OFF HIRED | 2022-09-30 | 2022-12-22 | 100% |  | 12 | 14 | 0.84 | 420 | 25.2 | 294 | 126 | 302.4 | 722.4 | 722.4 | 0
| 18 | 1094 | 13527 | 8457 |  | Level 18 Hotel | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 4 |  | 4 |  |  | 40 | m3 | OFF HIRED | 2022-09-30 | 2022-12-22 | 100% |  | 12 | 7.5 | 0.7 | 300 | 28 | 210 | 90 | 336 | 636 | 636 | 0
| 18 | 1247 | 13785 | 8223 |  | Level 18 Hotel | Cantiliver |  | Cantiliver | 4.2 | 0.6 |  |  |  | 1 |  | 2.52 | m2-LxW | OFF HIRED | 2022-10-19 | 2022-11-11 | 100% |  | 3.4286 | 36.5 | 3.15 | 91.98 | 7.938 | 64.386 | 27.594 | 27.216 | 119.196 | 119.196 | 0
| 18 | 1329 | 13817 | 8337 |  | Level 18 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 1.75 |  | 1.75 |  |  | 1.75 | rm | OFF HIRED | 2022-10-31 | 2022-12-16 | 100% |  | 6.7143 | 135 | 12.25 | 236.25 | 21.4375 | 165.375 | 70.875 | 143.9375 | 380.1875 | 380.1875 | 0
| 18 | 1419 | 13907 | 8323 |  | Level 18 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-11-12 | 2022-12-12 | 100% |  | 4.4286 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 162.75 | 567.75 | 567.75 | 0
| 18 | 1605 | 14140 |  |  | Level 18 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 4 |  | 4 |  |  | 4 | rm | ON HIRE | 2022-12-15 |  | 100% |  | 10.8571 | 135 | 12.25 | 540 | 49 | 378 | 0 | 532 | 910 | 714 | 196 |  |  | #VALUE! | 378 | #VALUE! | #VALUE!
| 18 | 1577 | 14109 | 8647 |  | Level 18 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 1.5 |  | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2022-12-10 | 2023-02-08 | 100% |  | 8.7143 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 60.75 | 160.125 | 362.625 | 280.875 | 81.75 |  |  | #VALUE! | 141.75 | #VALUE! | #VALUE!
| 19 | 662 | 12952 | 8080 |  | Level 19,20,21 Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-08 | 2022-10-07 | 100% |  | 8.7143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 213.5 | 483.5 | 483.5 | 0
| 19 | 662 | 12952 | 8080 |  | Level 19,20,21 Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-08 | 2022-10-07 | 100% |  | 8.7143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 213.5 | 483.5 | 483.5 | 0
| 19 | 662 | 12952 | 8080 |  | Level 19,20,21 Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-08 | 2022-10-07 | 100% |  | 8.7143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 213.5 | 483.5 | 483.5 | 0
| 19 | 761 | 13026 | 7859 |  | Level 19,20,21,22 Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-18 | 2022-08-31 | 100% |  | 2 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 49 | 319 | 319 | 0
| 19 | 762 | 13026 | 7859 |  | Level 19,20,21,22 Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-18 | 2022-08-31 | 100% |  | 2 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 49 | 319 | 319 | 0
| 19 | 764 | 13026 | 7859 |  | Level 19,20,21,22 Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-18 | 2022-08-31 | 100% |  | 2 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 49 | 319 | 319 | 0
| 19 | 765 | 13026 | 7859 |  | Level 19,20,21,22 Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-18 | 2022-08-31 | 100% |  | 2 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 49 | 319 | 319 | 0
| 19 | 926 | 13296 | 8060 |  | Level 19 to 20 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 6 |  | 6 |  |  | 6 | rm | OFF HIRED | 2022-09-09 | 2022-10-03 | 100% |  | 3.5714 | 135 | 12.25 | 810 | 73.5 | 567 | 243 | 262.5 | 1072.5 | 1072.5 | 0
| 19 | 1461 | 13949 | 8580 |  | Level 19 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-11-19 | 2023-02-18 | 100% |  | 13.1429 | 135 |  | 270 | 0 | 189 | 81 | 0 | 270 | 189 | 81 |  |  | #VALUE! | 227.325 | #VALUE! | #VALUE!
| 19 | 1461 | 13949 | 8580 |  | Level 19 Hotel | Cantiliver |  | Cantiliver | 2.5 | 0.6 |  |  |  | 1 |  | 1.5 | m2-LxW | OFF HIRED | 2022-11-19 | 2023-02-18 | 100% |  | 13.1429 | 36.5 | 0 | 54.75 | 0 | 38.325 | 16.425 | 0 | 54.75 | 38.325 | 16.425 |  |  | #VALUE! | 227.325 | #VALUE! | #VALUE!
| 19 | 1620 | 14155 | 8447 |  | Level 19 to 20 Hotel | Access Scaffold |  | INDEPENDENT | 18 | 1 | 2 |  | 2 |  |  | 36 | m2-LxH | OFF HIRED | 2022-12-17 | 2023-01-21 | 100% |  | 5.1429 | 14 | 0.84 | 504 | 30.24 | 352.8 | 151.2 | 155.52 | 659.52 | 659.52 | 0
| 20 | 478 | 12642 | 7716 |  | Level 20 Hotel | Birdcage Scaffold |  | Birdcage | 13 | 2.5 | 6 | 1 | 5 |  |  | 162.5 | m3 | OFF HIRED | 2022-07-07 | 2022-07-15 | 100% |  | 1.2857 | 7.5 | 0.7 | 1218.75 | 113.75 | 853.125 | 365.625 | 146.25 | 1365 | 1365 | 0
| 20 | 470 | 12626 | 7716 |  | Level 20 Hotel | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 6 | 1 | 5 |  |  | 50 | m3 | OFF HIRED | 2022-07-07 | 2022-07-15 | 100% |  | 1.2857 | 7.5 | 0.7 | 375 | 35 | 262.5 | 112.5 | 45 | 420 | 420 | 0
| 20 | 1288 | 13727 |  |  | Level 20 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 |  | 4 |  |  | 4 | rm | ON HIRE | 2022-10-24 |  | 100% |  | 18.2857 | 135 | 12.25 | 540 | 49 | 378 | 0 | 896 | 1274 | 1078 | 196 |  |  | #VALUE! | 378 | #VALUE! | #VALUE!
| 20 | 1289 | 13728 |  |  | Level 20 Hotel | Access Scaffold |  | Independent | 5 | 1.3 | 2 |  | 2 |  |  | 10 | m2-LxH | ON HIRE | 2022-10-24 |  | 100% |  | 18.2857 | 14 | 0.84 | 140 | 8.4 | 98 | 0 | 153.6 | 251.6 | 218 | 33.6 |  |  | #VALUE! | 98 | #VALUE! | #VALUE!
| 20 | 1351 | 13839 | 8337 |  | Level 20 Hotel | HEAVY DUTY TOWER |  | Tower | 2 | 2 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-11-03 | 2022-12-16 | 100% |  | 6.2857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 154 | 424 | 424 | 0
| 20 | 1434 | 13922 | 8441 |  | Level 20 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 1.5 |  | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2022-11-15 | 2023-01-17 | 100% |  | 9.1429 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 60.75 | 168 | 370.5 | 370.5 | 0
| 20 | 1328 | 13816 | 8337 |  | Level 20 Hotel | Access Scaffold |  | INDEPENDENT | 7.5 | 1.3 | 1.75 |  | 1.75 |  |  | 13.125 | m2-LxH | OFF HIRED | 2022-10-31 | 2022-12-16 | 100% |  | 6.7143 | 14 | 0.84 | 183.75 | 11.025 | 128.625 | 55.125 | 0 | 183.75 | 183.75 | 0
| 20 | 1440 | 13928 | 8330 |  | Level 20 Hotel | Access Scaffold |  | INDEPENDENT | 3.9 | 1.3 | 4 |  | 4 |  |  | 15.6 | m2-LxH | OFF HIRED | 2022-11-15 | 2022-12-14 | 100% |  | 4.2857 | 14 | 0.84 | 218.4 | 13.104 | 152.88 | 65.52 | 56.16 | 274.56 | 274.56 | 0
| 20 | 1440 | 13928 | 8330 |  | Level 20 Hotel | Access Scaffold |  | INDEPENDENT | 2.5 | 1 | 1.5 |  | 1.5 |  |  | 3.75 | m2-LxH | OFF HIRED | 2022-11-15 | 2022-12-14 | 100% |  | 4.2857 | 14 | 0.84 | 52.5 | 3.15 | 36.75 | 15.75 | 13.5 | 66 | 66 | 0
| 20 | 1569 | 14102 | 8479 |  | Level 20 To 27 Hotel | Access Scaffold |  | INDEPENDENT | 86 | 1 | 2 |  | 2 |  |  | 172 | m2-LxH | OFF HIRED | 2022-12-10 | 2022-12-31 | 100% |  | 3.1429 | 14 | 0.84 | 2408 | 144.48 | 1685.6 | 722.4 | 454.08 | 2862.08 | 2862.08 | 0
| 20 | 1562 | 14096 |  |  | Level 20 Hotel | Access Scaffold |  | INDEPENDENT | 5 | 1 | 2 |  | 2 |  |  | 10 | m2-LxH | ON HIRE | 2022-12-09 |  | 100% |  | 11.7143 | 14 | 0.84 | 140 | 8.4 | 98 | 0 | 98.4 | 196.4 | 162.8 | 33.6 |  |  | #VALUE! | 153.188 | #VALUE! | #VALUE!
| 20 | 1562 | 14096 |  |  | Level 20 Hotel | Cantiliver |  | Cantiliver | 6 | 0.6 |  |  |  | 0.6 |  | 2.16 | m2-LxW | ON HIRE | 2022-12-09 |  | 100% |  | 11.7143 | 36.5 | 3.15 | 78.84 | 6.804 | 55.188 | 0 | 79.704 | 134.892 | 107.676 | 27.216 |  |  | #VALUE! | 153.188 | #VALUE! | #VALUE!
| 21 | 504 | 12709 |  |  | Level 21 Residance | Access Scaffold |  | INDEPENDENT | 6 | 1 | 3 | 1 | 2 |  |  | 12 | m2-LxH | OFF HIRED | 2022-07-11 | 2022-07-13 | 100% |  | 0.42857 | 14 | 0.84 | 168 | 10.08 | 117.6 | 50.4 | 4.32 | 172.32 | 172.32 | 0
| 21 | 1165 | 13650 | 8101 |  | Level 21 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 1.5 |  | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2022-10-10 | 2022-10-13 | 100% |  | 0.57143 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 60.75 | 10.5 | 213 | 213 | 0
| 21 | 1231 | 13770 | 8297 |  | Level 21 Hotel | Access Scaffold |  | Independent | 6 | 1 | 2 |  | 2 |  |  | 12 | m2-LxH | OFF HIRED | 2022-10-16 | 2022-11-30 | 100% |  | 6.5714 | 14 | 0.84 | 168 | 10.08 | 117.6 | 50.4 | 66.24 | 234.24 | 234.24 | 0
| 21 | 1287 | 13726 |  |  | Level 21 Hotel | Access Scaffold |  | Independent | 5 | 1 | 3 |  | 3 |  |  | 15 | m2-LxH | ON HIRE | 2022-10-24 |  | 100% |  | 18.2857 | 14 | 0.84 | 210 | 12.6 | 147 | 0 | 230.4 | 377.4 | 327 | 50.4 |  |  | #VALUE! | 147 | #VALUE! | #VALUE!
| 21 | 1352 | 13840 | 8319 |  | Level 21 Hotel | Access Scaffold |  | INDEPENDENT | 2.5 | 1.3 | 1.5 |  | 1.5 |  |  | 3.75 | m2-LxH | OFF HIRED | 2022-11-03 | 2022-12-09 | 100% |  | 5.2857 | 14 | 0.84 | 52.5 | 3.15 | 36.75 | 15.75 | 16.65 | 69.15 | 69.15 | 0
| 21 | 1352 | 13840 | 8319 |  | Level 21 Hotel | Cantiliver |  | Cantiliver | 2.5 | 0.6 |  |  |  | 1 |  | 1.5 | m2-LxW | OFF HIRED | 2022-11-03 | 2022-12-09 | 100% |  | 5.2857 | 36.5 | 3.15 | 54.75 | 4.725 | 38.325 | 16.425 | 24.975 | 79.725 | 79.725 | 0
| 21 | 1576 | 14108 |  |  | Level 21 Hotel | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 2 |  | 2 |  |  | 10 | m2-LxH | ON HIRE | 2022-12-10 |  | 100% |  | 11.5714 | 14 | 0.84 | 140 | 8.4 | 98 | 0 | 97.2 | 195.2 | 161.6 | 33.6 |  |  | #VALUE! | 143.99 | #VALUE! | #VALUE!
| 21 | 1576 | 14108 |  |  | Level 21 Hotel | Cantiliver |  | Cantiliver | 5 | 0.6 |  |  |  | 0.6 |  | 1.8 | m2-LxW | ON HIRE | 2022-12-10 |  | 100% |  | 11.5714 | 36.5 | 3.15 | 65.7 | 5.67 | 45.99 | 0 | 65.61 | 111.6 | 88.92 | 22.68 |  |  | #VALUE! | 143.99 | #VALUE! | #VALUE!
| 22 | 646 | 12869 | 8101 |  | Level 22 Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-02 | 2022-10-13 | 100% |  | 10.4286 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 255.5 | 525.5 | 525.5 | 0
| 22 | 938 | 13311 | 8334 |  | Level 22 Hotel | Access Scaffold |  | Independent | 12.5 | 1.3 | 2.5 |  | 2.5 |  |  | 31.25 | m2-LxH | OFF HIRED | 2022-09-10 | 2022-12-15 | 100% |  | 13.8571 | 14 | 0.84 | 437.5 | 26.25 | 306.25 | 131.25 | 363.75 | 801.25 | 801.25 | 0
| 22 | 330 | 12427 | 7582 |  | Level 22 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-06-22 | 2022-06-24 | 100% |  | 0.42857 | 135 | 12.25 | 540 | 49 | 378 | 162 | 21 | 561 | 561 | 0
| 22 | 504 | 12709 |  |  | Level 22 Residance | Access Scaffold |  | INDEPENDENT | 6 | 1 | 3 | 1 | 2 |  |  | 12 | m2-LxH | OFF HIRED | 2022-07-11 | 2022-07-13 | 100% |  | 0.42857 | 14 | 0.84 | 168 | 10.08 | 117.6 | 50.4 | 4.32 | 172.32 | 172.32 | 0
| 22 | 694 | 12959 | 7853 |  | Level 22 Residence | Access Scaffold |  | Tower | 1.8 | 1.8 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-08-06 | 2022-08-29 | 100% |  | 3.4286 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 126 | 531 | 531 | 0
| 22 | 697 | 12959 | 7853 |  | Level 22 Residence | Access Scaffold |  | Tower | 1.8 | 1.8 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-08-06 | 2022-08-29 | 100% |  | 3.4286 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 126 | 531 | 531 | 0
| 22 | 698 | 12961 | 7865 |  | Level 22 Residence | Access Scaffold |  | Tower | 2.5 | 1.8 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-08-06 | 2022-09-03 | 100% |  | 4.1429 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 152.25 | 557.25 | 557.25 | 0
| 22 | 706 | 12970 | 6742 |  | Level 22 Residence | Access Scaffold |  | Tower | 1.3 | 0.6 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-08-09 | 2022-09-29 | 100% |  | 7.4286 | 135 | 12.25 | 540 | 49 | 378 | 162 | 364 | 904 | 904 | 0
| 22 | 868 | 13139 | 8201 |  | Level 22 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-01 | 2022-11-05 | 100% |  | 9.4286 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 231 | 501 | 501 | 0
| 22 | 911 | 13285 | 8210 |  | Level 22 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-08 | 2022-11-07 | 100% |  | 8.7143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 213.5 | 483.5 | 483.5 | 0
| 22 | 912 | 13285 | 8210 |  | Level 22 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-08 | 2022-11-07 | 100% |  | 8.7143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 213.5 | 483.5 | 483.5 | 0
| 22 | 921 | 13294 | 8210 |  | Level 22 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-08 | 2022-11-07 | 100% |  | 8.7143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 213.5 | 483.5 | 483.5 | 0
| 22 | 922 | 13294 | 8210 |  | Level 22 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-08 | 2022-11-07 | 100% |  | 8.7143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 213.5 | 483.5 | 483.5 | 0
| 22 | 923 | 13294 | 8210 |  | Level 22 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-08 | 2022-11-07 | 100% |  | 8.7143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 213.5 | 483.5 | 483.5 | 0
| 22 | 1162 | 13647 | 8286 |  | Level 22 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 0.6 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-10-10 | 2022-11-28 | 100% |  | 7.1429 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 175 | 445 | 445 | 0
| 22 | 1097 | 13530 | 8100 |  | Level 22 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-30 | 2022-10-04 | 100% |  | 0.71429 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 17.5 | 287.5 | 287.5 | 0
| 22 | 1096 | 13529 | 8100 |  | Level 22 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-30 | 2022-10-04 | 100% |  | 0.71429 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 17.5 | 287.5 | 287.5 | 0
| 22 | 1108 | 13542 | 8210 |  | Level 22 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-10-03 | 2022-11-07 | 100% |  | 5.1429 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 126 | 396 | 396 | 0
| 22 | 1083 | 13516 | 8125 |  | Level 22 To 24 Residence | Access Scaffold |  | Independent | 25 | 0.6 | 2 |  | 2 |  |  | 50 | m2-LxH | OFF HIRED | 2022-09-29 | 2022-10-19 | 100% |  | 3 | 14 | 0.84 | 700 | 42 | 490 | 210 | 126 | 826 | 826 | 0
| 22 | 1326 | 13814 | 8325 |  | Level 22 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 1.75 |  | 1.75 |  |  | 1.75 | rm | OFF HIRED | 2022-10-31 | 2022-12-13 | 100% |  | 6.2857 | 135 | 12.25 | 236.25 | 21.4375 | 165.375 | 70.875 | 134.75 | 371 | 371 | 0
| 22 | 1307 | 13745 |  |  | Level 22 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 4 |  | 4 |  |  | 4 | rm | ON HIRE | 2022-10-27 |  | 100% |  | 17.8571 | 135 | 12.25 | 540 | 49 | 378 | 0 | 875 | 1253 | 1057 | 196 |  |  | #VALUE! | 378 | #VALUE! | #VALUE!
| 22 | 1470 | 13958 | 8474 |  | Level 22 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1 | 3.5 |  | 3.5 |  |  | 3.5 | rm | OFF HIRED | 2022-11-19 | 2022-12-27 | 100% |  | 5.5714 | 135 | 12.25 | 472.5 | 42.875 | 330.75 | 141.75 | 238.875 | 711.375 | 711.375 | 0
| 22 | 1467 | 13955 | 8343 |  | Level 22 To 23 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 5 |  | 5 |  |  | 5 | rm | OFF HIRED | 2022-11-19 | 2022-12-19 | 100% |  | 4.4286 | 135 | 12.25 | 675 | 61.25 | 472.5 | 202.5 | 271.25 | 946.25 | 946.25 | 0
| 22 | 1581 | 14113 |  |  | Level 22 Hotel | Access Scaffold |  | INDEPENDENT | 6 | 1 | 2 |  | 2 |  |  | 12 | m2-LxH | ON HIRE | 2022-12-11 |  | 100% |  | 11.4286 | 14 | 0.84 | 168 | 10.08 | 117.6 | 0 | 115.2 | 232.8 | 192.48 | 40.32 |  |  | #VALUE! | 172.788 | #VALUE! | #VALUE!
| 22 | 1581 | 14113 |  |  | Level 22 Hotel | Cantiliver |  | Cantiliver | 6 | 0.6 |  |  |  | 0.6 |  | 2.16 | m2-LxW | ON HIRE | 2022-12-11 |  | 100% |  | 11.4286 | 36.5 | 3.15 | 78.84 | 6.804 | 55.188 | 0 | 77.76 | 132.948 | 105.732 | 27.216 |  |  | #VALUE! | 172.788 | #VALUE! | #VALUE!
| 23 | 554 | 12647 | 8230 |  | Level 23 Hotel | Support Tower With Ladder Beam |  | INDEPENDENT | 20 | 1 | 3 | 1 | 2 |  |  | 40 | m2-LxH | OFF HIRED | 2022-07-05 | 2022-11-14 | 100% |  | 19 | 14 | 0.84 | 560 | 33.6 | 392 | 168 | 638.4 | 1198.4 | 1198.4 | 0
| 23 | 554 | 12647 | 8230 |  | Level 23 Hotel | Support Tower With Ladder Beam |  | INDEPENDENT | 20 | 1 | 3 | 1 | 2 |  |  | 40 | m2-LxH | OFF HIRED | 2022-07-05 | 2022-11-14 | 100% |  | 19 | 14 | 0.84 | 560 | 33.6 | 392 | 168 | 638.4 | 1198.4 | 1198.4 | 0
| 23 | 554 | 12647 | 8230 |  | Level 23 Hotel | Support Tower With Ladder Beam |  | Buttress | 20 | 2.5 | 6 | 1 | 5 |  |  | 250 | m3 | OFF HIRED | 2022-07-05 | 2022-11-14 | 100% |  | 19 | 5.25 | 0.35 | 1312.5 | 87.5 | 918.75 | 393.75 | 1662.5 | 2975 | 2975 | 0
| 23 | 554 | 12647 | 8230 |  | Level 23 Hotel | Support Tower With Ladder Beam |  | HD Chainpully | 16 | 3 |  |  |  | 1 |  | 48 | m2-LxW | OFF HIRED | 2022-07-05 | 2022-11-14 | 100% |  | 19 | 81 | 1.82 | 3888 | 87.36 | 2721.6 | 1166.4 | 1659.84 | 5547.84 | 5547.84 | 0
| 23 | 657 | 12886 | 8556 |  | Level 23 to 28 Hotel | Access Scaffold |  | Tower | 2.5 | 1.3 | 3.5 | 1 | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-08-05 | 2023-02-10 | 100% |  | 27.1429 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 831.25 | 1168.75 | 1023.75 | 145 |  |  | #VALUE! | 427.875 | #VALUE! | #VALUE!
| 23 | 738 | 12996 | 7859 |  | Level 23 Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-15 | 2022-08-31 | 100% |  | 2.4286 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 59.5 | 329.5 | 329.5 | 0
| 23 | 657 | 12886 | 8556 |  | Level 23 to 28 Hotel | Cantiliver |  | Cantiliver | 1.5 | 1 |  |  |  | 1 |  | 1.5 | m2-LxW | OFF HIRED | 2022-08-05 | 2023-02-10 | 100% |  | 27.1429 | 36.5 | 3.15 | 54.75 | 4.725 | 38.325 | 16.425 | 128.25 | 183 | 159.825 | 23.175 |  |  | #VALUE! | 427.875 | #VALUE! | #VALUE!
| 23 | 657 | 12886 | 8556 |  | Level 23 to 28 Hotel | Cantiliver |  | Cantiliver | 1.5 | 1 |  |  |  | 1 |  | 1.5 | m2-LxW | OFF HIRED | 2022-08-05 | 2023-02-10 | 100% |  | 27.1429 | 36.5 | 3.15 | 54.75 | 4.725 | 38.325 | 16.425 | 128.25 | 183 | 159.825 | 23.175 |  |  | #VALUE! | 427.875 | #VALUE! | #VALUE!
| 23 | 657 | 12886 | 8556 |  | Level 23 to 28 Hotel | Cantiliver |  | Cantiliver | 1.5 | 1 |  |  |  | 1 |  | 1.5 | m2-LxW | OFF HIRED | 2022-08-05 | 2023-02-10 | 100% |  | 27.1429 | 36.5 | 3.15 | 54.75 | 4.725 | 38.325 | 16.425 | 128.25 | 183 | 159.825 | 23.175 |  |  | #VALUE! | 427.875 | #VALUE! | #VALUE!
| 23 | 657 | 12886 | 8556 |  | Level 23 to 28 Hotel | Cantiliver |  | Cantiliver | 1.5 | 1 |  |  |  | 1 |  | 1.5 | m2-LxW | OFF HIRED | 2022-08-05 | 2023-02-10 | 100% |  | 27.1429 | 36.5 | 3.15 | 54.75 | 4.725 | 38.325 | 16.425 | 128.25 | 183 | 159.825 | 23.175 |  |  | #VALUE! | 427.875 | #VALUE! | #VALUE!
| 23 | 657 | 12886 | 8556 |  | Level 23 to 28 Hotel | Cantiliver |  | Cantiliver | 1.5 | 1 |  |  |  | 1 |  | 1.5 | m2-LxW | OFF HIRED | 2022-08-05 | 2023-02-10 | 100% |  | 27.1429 | 36.5 | 3.15 | 54.75 | 4.725 | 38.325 | 16.425 | 128.25 | 183 | 159.825 | 23.175 |  |  | #VALUE! | 427.875 | #VALUE! | #VALUE!
| 23 | 293 | 12399 | 7706 |  | Level 23 Residance | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 5.5 | 1 | 4.5 |  |  | 4.5 | rm | OFF HIRED | 2022-06-19 | 2022-07-05 | 100% |  | 2.4286 | 135 | 12.25 | 607.5 | 55.125 | 425.25 | 182.25 | 133.875 | 741.375 | 741.375 | 0
| 23 | 126 | 12211 | 7560 |  | Level 23 Residence | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 5 | 1 | 4 |  |  | 20 | m2-LxH | OFF HIRED | 2022-06-02 | 2022-06-09 | 100% |  | 1.1429 | 14 |  | 280 | 0 | 196 | 84 | 0 | 280 | 280 | 0
| 23 | 146 | 12242 | 7576 |  | Level 23 Residence | Access Scaffold |  | INDEPENDENT | 1.3 | 1 | 3 | 1 | 2 |  |  | 2.6 | m2-LxH | OFF HIRED | 2022-06-06 | 2022-06-22 | 100% |  | 2.4286 | 14 |  | 36.4 | 0 | 25.48 | 10.92 | 0 | 36.4 | 36.4 | 0
| 23 | 142 | 12243 | 7560 |  | Level 23 Residence | Access Scaffold |  | INDEPENDENT | 10 | 1.3 | 5 | 1 | 4 |  |  | 40 | m2-LxH | OFF HIRED | 2022-06-06 | 2022-06-09 | 100% |  | 0.57143 | 14 |  | 560 | 0 | 392 | 168 | 0 | 560 | 560 | 0
| 23 | 165 | 12166 | 8563 |  | Level 23 Residence | Access Scaffold |  | INDEPENDENT | 6 | 1.3 | 5 | 1 | 4 |  |  | 24 | m2-LxH | OFF HIRED | 2022-06-08 | 2023-02-13 | 100% |  | 35.8571 | 14 |  | 336 | 0 | 235.2 | 100.8 | 0 | 336 | 235.2 | 100.8 |  |  | #VALUE! | 739.2 | #VALUE! | #VALUE!
| 23 | 220 | 12317 | 7585 |  | Level 23 Residence | Access Scaffold |  | INDEPENDENT | 2.5 | 1.3 | 3 | 1 | 2 |  |  | 5 | m2-LxH | OFF HIRED | 2022-06-12 | 2022-06-26 | 100% |  | 2.1429 | 14 |  | 70 | 0 | 49 | 21 | 0 | 70 | 70 | 0
| 23 | 218 | 12315 | 6724 |  | Level 23 Residence | Access Scaffold |  | INDEPENDENT | 2.5 | 1.3 | 3 | 1 | 2 |  |  | 5 | m2-LxH | OFF HIRED | 2022-06-12 | 2022-09-26 | 100% |  | 15.2857 | 14 |  | 70 | 0 | 49 | 21 | 0 | 70 | 70 | 0
| 23 | A219 | 12511 | 7583 |  | Level 23 Residence | Access Scaffold |  | INDEPENDENT | 7.5 | 1.3 | 3 | 1 | 2 |  |  | 15 | m2-LxH | OFF HIRED | 2022-06-24 | 2022-06-26 | 100% |  | 0.42857 | 14 |  | 210 | 0 | 147 | 63 | 0 | 210 | 210 | 0
| 23 | 358 | 12519 | 7718 |  | Level 23 Residence | Access Scaffold |  | INDEPENDENT | 8 | 1.3 | 4 | 1 | 3 |  |  | 24 | m2-LxH | OFF HIRED | 2022-06-27 | 2022-07-15 | 100% |  | 2.7143 | 14 | 0.84 | 336 | 20.16 | 235.2 | 100.8 | 54.72 | 390.72 | 390.72 | 0
| 23 | 165 | 12166 | 7587 |  | Level 23 Residence | Access Scaffold |  | INDEPENDENT | 10 | 1.8 | 5 | 1 | 4 |  |  | 40 | m2-LxH | OFF HIRED | 2022-06-08 | 2022-06-27 | 100% |  | 2.8571 | 18 |  | 720 | 0 | 504 | 216 | 0 | 720 | 720 | 0
| 23 | 217 | 12314 | 6707 |  | Level 23 Residence | Birdcage Scaffold |  | Birdcage | 15 | 11 | 5 | 1 | 4 |  |  | 660 | m3 | OFF HIRED | 2022-06-12 | 2022-09-21 | 100% |  | 14.5714 | 7.5 | 0.7 | 4950 | 462 | 3465 | 1485 | 6732 | 11682 | 11682 | 0
| 23 | 206 | 12304 | 6719 |  | Level 23 Residence | Birdcage Scaffold |  | Birdcage | 16 | 8 | 4 | 1 | 3 |  |  | 384 | m3 | OFF HIRED | 2022-06-12 | 2022-09-24 | 100% |  | 15 | 7.5 | 0.7 | 2880 | 268.8 | 2016 | 864 | 4032 | 6912 | 6912 | 0
| 23 | A217 | 12575 | 7718 |  | Level 23Residence | Birdcage Scaffold |  | Birdcage | 10 | 8 | 4 | 1 | 3 |  |  | 240 | m3 | OFF HIRED | 2022-07-01 | 2022-07-15 | 100% |  | 2.1429 | 7.5 | 0.7 | 1800 | 168 | 1260 | 540 | 360 | 2160 | 2160 | 0
| 23 | 217 | 12764 | 6729 |  | Level 23 Residance | Birdcage Scaffold |  | Birdcage | 8 | 8 | 4 | 1 | 3 |  |  | 192 | m3 | OFF HIRED | 2022-07-19 | 2022-09-27 | 100% |  | 10.1429 | 7.5 | 0.7 | 1440 | 134.4 | 1008 | 432 | 1363.2 | 2803.2 | 2803.2 | 0
| 23 | 558 | 12719 | 7880 |  | Level 23 Residence | Load Bearing Back Proping |  | Load Bearing | 6.5 | 1 | 3.3 | 1 | 2.3 |  | 2 | 2 | unit | OFF HIRED | 2022-07-12 | 2022-09-09 | 100% |  | 8.5714 | 500 | 70 | 1000 | 140 | 700 | 300 | 1200 | 2200 | 2200 | 0
| 23 | 672 | 12889 | 7835 |  | Level 23 Residence | Access Scaffold |  | Tower | 2.5 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-08-05 | 2022-08-19 | 100% |  | 2.1429 | 135 |  | 405 | 0 | 283.5 | 121.5 | 0 | 405 | 405 | 0
| 23 | 672 | 12889 | 7835 |  | Level 23 Residence | Access Scaffold |  | Tower | 2.5 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-08-05 | 2022-08-19 | 100% |  | 2.1429 | 135 |  | 405 | 0 | 283.5 | 121.5 | 0 | 405 | 405 | 0
| 23 | 594 | 12819 | 7822 |  | Level 23 Residence | Access Scaffold |  | Tower | 1.3 | 1 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-27 | 2022-08-08 | 100% |  | 1.8571 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 45.5 | 315.5 | 315.5 | 0
| 23 | 609 | 12830 | 7746 |  | Level 23 Residence | Access Scaffold |  | Tower | 1.3 | 0.6 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-07-27 | 2022-07-31 | 100% |  | 0.71429 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 26.25 | 431.25 | 431.25 | 0
| 23 | 746 | 13013 | 7880 |  | Level 23 Residence | Access Scaffold |  | Independent | 19 | 1.3 | 5 | 1 | 4 |  |  | 76 | m2-LxH | OFF HIRED | 2022-08-16 | 2022-09-09 | 100% |  | 3.5714 | 14 | 0 | 1064 | 0 | 744.8 | 319.2 | 0 | 1064 | 1064 | 0
| 23 | 918 | 13291 | 7897 |  | Level 23 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 0.6 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-09-08 | 2022-09-16 | 100% |  | 1.2857 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 47.25 | 452.25 | 452.25 | 0
| 23 | 826 | 13094 | 7883 |  | Level 23 Residence | Access Scaffold |  | Independent | 4 | 1.3 | 3 |  | 3 |  |  | 12 | m2-LxH | OFF HIRED | 2022-08-26 | 2022-09-12 | 100% |  | 2.5714 | 14 | 0.84 | 168 | 10.08 | 117.6 | 0 | 25.92 | 143.52 | 143.52 | 0
| 23 | 897 | 13268 | 7895 |  | Level 23 Residence | Access Scaffold |  | Independent | 3.5 | 1.3 | 3 |  | 3 |  |  | 10.5 | m2-LxH | OFF HIRED | 2022-09-06 | 2022-09-15 | 100% |  | 1.4286 | 14 | 0.84 | 147 | 8.82 | 102.9 | 44.1 | 12.6 | 159.6 | 159.6 | 0
| 23 | 944 | 13320 | 6719 |  | Level 23 Residence | Access Scaffold |  | Independent | 4 | 1.8 | 4 |  | 4 |  |  | 16 | m2-LxH | OFF HIRED | 2022-09-13 | 2022-09-24 | 100% |  | 1.7143 | 18 | 1.05 | 288 | 16.8 | 201.6 | 86.4 | 28.8 | 316.8 | 316.8 | 0
| 23 | 952 | 13320 | 6719 |  | Level 23 Residence | Access Scaffold |  | Independent | 4 | 1.8 | 4 |  | 4 |  |  | 16 | m2-LxH | OFF HIRED | 2022-09-13 | 2022-09-24 | 100% |  | 1.7143 | 18 | 1.05 | 288 | 16.8 | 201.6 | 86.4 | 28.8 | 316.8 | 316.8 | 0
| 23 | 726 | 13269 | 6706 |  | Level 23 Residence | Birdcage Scaffold |  | Birdcage | 8 | 5 | 3 |  | 3 |  |  | 120 | m3 | OFF HIRED | 2022-09-06 | 2022-09-21 | 100% |  | 2.2857 | 7.5 | 0.7 | 900 | 84 | 630 | 270 | 192 | 1092 | 1092 | 0
| 23 | 903 | 13276 | 7800 |  | Level 23 Residence | Birdcage Scaffold |  | Birdcage | 3 | 2.5 | 4 |  | 4 |  |  | 30 | m3 | OFF HIRED | 2022-09-07 | 2022-09-09 | 100% |  | 0.42857 | 7.5 | 0.7 | 225 | 21 | 157.5 | 67.5 | 9 | 234 | 234 | 0
| 23 | 645 | 12868 | 8084 |  | Level 23 Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-02 | 2022-10-07 | 100% |  | 9.5714 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 234.5 | 504.5 | 504.5 | 0
| 23 | 1024 | 13461 | 6742 |  | Level 23 , 26 , 27 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 0.6 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-09-23 | 2022-09-29 | 100% |  | 1 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 36.75 | 441.75 | 441.75 | 0
| 23 | 1025 | 13461 | 6742 |  | Level 23 , 26 , 27 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 0.6 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-09-23 | 2022-09-29 | 100% |  | 1 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 36.75 | 441.75 | 441.75 | 0
| 23 | 1026 | 13461 | 6742 |  | Level 23 , 26 , 27 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 0.6 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-09-23 | 2022-09-29 | 100% |  | 1 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 36.75 | 441.75 | 441.75 | 0
| 23 | 1043 | 13480 | 8055 |  | Level 23 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4.5 |  | 4.5 |  |  | 4.5 | rm | OFF HIRED | 2022-09-24 | 2022-10-01 | 100% |  | 1.1429 | 135 | 12.25 | 607.5 | 55.125 | 425.25 | 182.25 | 63 | 670.5 | 670.5 | 0
| 23 | 957 | 13333 | 6719 |  | Level 23 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 2.5 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-14 | 2022-09-24 | 100% |  | 1.5714 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 38.5 | 308.5 | 308.5 | 0
| 23 | 957 | 13333 | 6719 |  | Level 23 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 2.5 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-14 | 2022-09-24 | 100% |  | 1.5714 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 38.5 | 308.5 | 308.5 | 0
| 23 | 897 | 13319 | 8129 |  | Level 23 to 25 Residence | GRC -GLASS LINE WORK |  | Cantiliver spl | 8 |  | 12 |  |  |  | 1 | 1 | unit | OFF HIRED | 2022-09-06 | 2022-10-20 | 100% |  | 6.4286 | 17000 | 1050 | 17000 | 1050 | 11900 | 5100 | 6750 | 23750 | 23750 | 0
| 23 | 1172 | 13657 | 8492 |  | Level 23 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-10-10 | 2023-01-05 | 100% |  | 12.5714 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 308 | 578 | 578 | 0
| 23 | 1106 | 13539 | 8202 |  | Level 23 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-10-01 | 2022-11-05 | 100% |  | 5.1429 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 157.5 | 495 | 495 | 0
| 23 | 1243 | 13781 | 8476 |  | Level 23 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-10-18 | 2022-12-29 | 100% |  | 10.4286 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 255.5 | 525.5 | 525.5 | 0
| 23 | 1144 | 13628 | 8286 |  | Level 23 Residence | Access Scaffold |  | Independent | 13 | 1.3 | 3 |  | 3 |  |  | 39 | m2-LxH | OFF HIRED | 2022-10-06 | 2022-11-28 | 100% |  | 7.7143 | 14 | 0.84 | 546 | 32.76 | 382.2 | 163.8 | 252.72 | 798.72 | 798.72 | 0
| 23 | 1234 | 13772 | 8343 |  | Level 23 Hotel | Access Scaffold |  | Independent | 6.5 | 1.3 | 2 |  | 2 |  |  | 13 | m2-LxH | OFF HIRED | 2022-10-17 | 2022-12-17 | 100% |  | 8.8571 | 14 | 0.84 | 182 | 10.92 | 127.4 | 54.6 | 96.72 | 278.72 | 278.72 | 0
| 23 | 1143 | 13627 | 8125 |  | Level 23 to 25 Residence | Access Scaffold |  | Independent | 32 | 0.6 | 2 |  | 2 |  |  | 64 | m2-LxH | OFF HIRED | 2022-10-06 | 2022-10-19 | 100% |  | 2 | 14 | 0.84 | 896 | 53.76 | 627.2 | 268.8 | 107.52 | 1003.52 | 1003.52 | 0
| 23 | 1145 | 13629 | 8341 |  | Level 23 Residence | Access Scaffold |  | Independent | 11 | 1.3 | 3 |  | 3 |  |  | 33 | m2-LxH | OFF HIRED | 2022-10-06 | 2022-12-17 | 100% |  | 10.4286 | 14 | 0.84 | 462 | 27.72 | 323.4 | 138.6 | 289.08 | 751.08 | 751.08 | 0
| 23 | 1193 | 13678 | 8476 |  | Level 23 Residence | Access Scaffold |  | Independent | 5 | 1.8 | 4 |  | 4 |  |  | 36 | m3 | OFF HIRED | 2022-10-12 | 2022-12-29 | 100% |  | 11.2857 | 7.5 | 0.7 | 270 | 25.2 | 189 | 81 | 284.4 | 554.4 | 554.4 | 0
| 23 | 1208 | 13694 | 8214 |  | Level 23 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 4 |  | 4 |  |  | 25 | m3 | OFF HIRED | 2022-10-14 | 2022-11-09 | 100% |  | 3.8571 | 7.5 | 0.7 | 187.5 | 17.5 | 131.25 | 56.25 | 67.5 | 255 | 255 | 0
| 23 | 1353 | 13841 | 8321 |  | Level 23 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-11-03 | 2022-12-11 | 100% |  | 5.5714 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 136.5 | 406.5 | 406.5 | 0
| 23 | 1487 | 13974 |  |  | Level 23 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 1.5 |  | 1.5 |  |  | 1.5 | rm | ON HIRE | 2022-11-24 |  | 100% |  | 13.8571 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 0 | 254.625 | 396.375 | 322.875 | 73.5 |  |  | #VALUE! | 141.75 | #VALUE! | #VALUE!
| 23 | 1330 | 13818 | 8257 |  | Level 23 To 24 Residence | Access Scaffold |  | INDEPENDENT | 10 | 1.3 | 2.5 |  | 2.5 |  |  | 25 | m2-LxH | OFF HIRED | 2022-10-31 | 2022-11-20 | 100% |  | 3 | 14 | 0.84 | 350 | 21 | 245 | 105 | 63 | 413 | 413 | 0
| 23 | 1435 | 13923 | 8306 |  | Level 23 Residence | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 3.5 |  | 3.5 |  |  | 17.5 | m2-LxH | OFF HIRED | 2022-11-15 | 2022-12-06 | 100% |  | 3.1429 | 14 | 0.84 | 245 | 14.7 | 171.5 | 73.5 | 46.2 | 291.2 | 291.2 | 0
| 23 | 1391 | 13879 | 8214 |  | Level 23 Residence | Access Scaffold |  | INDEPENDENT | 7.5 | 1 | 4 |  | 4 |  |  | 30 | m2-LxH | OFF HIRED | 2022-11-08 | 2022-11-09 | 100% |  | 0.28571 | 14 | 0.84 | 420 | 25.2 | 294 | 126 | 7.2 | 427.2 | 427.2 | 0
| 23 | 1476 | 13964 | 8285 |  | Level 23 Residence | Access Scaffold |  | INDEPENDENT | 3 | 1.3 | 1.5 |  | 1.5 |  |  | 4.5 | m2-LxH | OFF HIRED | 2022-11-21 | 2022-11-28 | 100% |  | 1.1429 | 14 | 0.84 | 63 | 3.78 | 44.1 | 18.9 | 4.32 | 67.32 | 67.32 | 0
| 23 | 1390 | 13878 | 8246 |  | Level 23 Residence | Birdcage Scaffold |  | Birdcage | 6.8 | 2.5 | 2.5 |  | 2.5 |  |  | 42.5 | m3 | OFF HIRED | 2022-11-08 | 2022-11-16 | 100% |  | 1.2857 | 7.5 | 0.7 | 318.75 | 29.75 | 223.125 | 95.625 | 38.25 | 357 | 357 | 0
| 23 | 1549 | 14084 | 8443 |  | Level 23 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-12-08 | 2023-01-19 | 100% |  | 6.1429 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 150.5 | 420.5 | 420.5 | 0
| 23 | 1570 | 14104 |  |  | Level 23 Hotel | Access Scaffold |  | INDEPENDENT | 6 | 1 | 2 |  | 2 |  |  | 12 | m2-LxH | ON HIRE | 2022-12-10 |  | 100% |  | 11.5714 | 14 | 0.84 | 168 | 10.08 | 117.6 | 0 | 116.64 | 234.24 | 193.92 | 40.32 |  |  | #VALUE! | 172.788 | #VALUE! | #VALUE!
| 23 | 1541 | 14077 | 8480 |  | Level 23 Residence | Access Scaffold |  | Independent | 5 | 1.8 | 3 |  | 3 |  |  | 15 | m2-LxH | OFF HIRED | 2022-12-07 | 2022-12-31 | 100% |  | 3.5714 | 18 | 1.05 | 270 | 15.75 | 189 | 81 | 56.25 | 326.25 | 326.25 | 0
| 23 | 1570 | 14104 |  |  | Level 23 Hotel | Cantiliver |  | Cantiliver | 6 | 0.6 |  |  |  | 0.6 |  | 2.16 | m2-LxW | ON HIRE | 2022-12-10 |  | 100% |  | 11.5714 | 36.5 | 3.15 | 78.84 | 6.804 | 55.188 | 0 | 78.732 | 133.92 | 106.704 | 27.216 |  |  | #VALUE! | 172.788 | #VALUE! | #VALUE!
| 24 | 386 | 12545 | 6725 |  | Level 24 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 3.5 | 1 | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-06-27 | 2022-09-26 | 100% |  | 13.1429 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 402.5 | 740 | 740 | 0
| 24 | 908 | 13282 | 7893 |  | Level 24 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 6 |  | 6 |  |  | 6 | rm | OFF HIRED | 2022-09-08 | 2022-09-16 | 100% |  | 1.2857 | 135 | 12.25 | 810 | 73.5 | 567 | 243 | 94.5 | 904.5 | 904.5 | 0
| 24 | 862 | 13134 | 8435 |  | Level 24/25 Hotel | Access Scaffold |  | Independent | 8 | 1.3 | 5 |  | 5 |  |  | 40 | m2-LxH | OFF HIRED | 2022-08-31 | 2023-01-17 | 100% |  | 20 | 14 |  | 560 | 0 | 392 | 168 | 0 | 560 | 560 | 0
| 24 | 919 | 13292 | 8343 |  | Level 24 Hotel | Access Scaffold |  | Independent | 11.3 | 1.3 | 2 |  | 2 |  |  | 22.6 | m2-LxH | OFF HIRED | 2022-09-18 | 2022-12-19 | 100% |  | 13.2857 | 14 | 0.84 | 316.4 | 18.984 | 221.48 | 94.92 | 252.216 | 568.616 | 568.616 | 0
| 24 | 245 | 12360 | 7581 |  | Level 24 Residance | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-06-15 | 2022-06-23 | 100% |  | 1.2857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 31.5 | 301.5 | 301.5 | 0
| 24 | A14 | 12226 | 7559 |  | Level 24 Residence | Access Scaffold |  | INDEPENDENT | 8 | 1.3 | 5 | 1 | 4 |  |  | 32 | m2-LxH | OFF HIRED | 2022-06-05 | 2022-06-08 | 100% |  | 0.57143 | 14 |  | 448 | 0 | 313.6 | 134.4 | 0 | 448 | 448 | 0
| 24 | 244 | 12359 | 7585 |  | Level 24 Residence | Access Scaffold |  | INDEPENDENT | 1.3 | 1.3 | 4 | 1 | 3 |  |  | 3.9 | m2-LxH | OFF HIRED | 2022-06-15 | 2022-06-26 | 100% |  | 1.7143 | 14 | 0.84 | 54.6 | 3.276 | 38.22 | 16.38 | 5.616 | 60.216 | 60.216 | 0
| 24 | 397 | 12558 | 7732 |  | Level 24 to 31 Residance | Access Scaffold |  | INDEPENDENT | 12 | 1.3 | 6 | 1 | 5 |  |  | 60 | m2-LxH | OFF HIRED | 2022-06-29 | 2022-07-19 | 100% |  | 3 | 14 | 0.84 | 840 | 50.4 | 588 | 252 | 151.2 | 991.2 | 991.2 | 0
| 24 | 745 | 13012 | 7870 |  | Level 24 Residence | Access Scaffold |  | Tower | 2.5 | 2.5 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-08-16 | 2022-09-03 | 100% |  | 2.7143 | 135 |  | 405 | 0 | 283.5 | 121.5 | 0 | 405 | 405 | 0
| 24 | 745 | 13012 | 7870 |  | Level 24 Residence | Access Scaffold |  | Tower | 2.5 | 2.5 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-08-16 | 2022-09-03 | 100% |  | 2.7143 | 135 |  | 405 | 0 | 283.5 | 121.5 | 0 | 405 | 405 | 0
| 24 | 745 | 13012 | 7870 |  | Level 24 Residence | Access Scaffold |  | Tower | 2.5 | 2.5 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-08-16 | 2022-09-03 | 100% |  | 2.7143 | 135 |  | 405 | 0 | 283.5 | 121.5 | 0 | 405 | 405 | 0
| 24 | 693 | 12958 | 6730 |  | Level 24 Residence | Access Scaffold |  | Tower | 6 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-08-08 | 2022-09-28 | 100% |  | 7.4286 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 273 | 678 | 678 | 0
| 24 | 742 | 13000 | 7841 |  | Level 24 Residence | Access Scaffold |  | Tower | 1.8 | 1.8 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-08-15 | 2022-08-22 | 100% |  | 1.1429 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 42 | 447 | 447 | 0
| 24 | 793 | 13053 | 6713 |  | Level 24 Residence | Birdcage Scaffold |  | Birdcage | 8.8 | 6.3 | 2 |  | 2 |  |  | 110.88 | m3 | OFF HIRED | 2022-08-23 | 2022-09-24 | 100% |  | 4.7143 | 7.5 | 0.7 | 831.6 | 77.616 | 582.12 | 249.48 | 365.904 | 1197.504 | 1197.504 | 0
| 24 | 873 | 13144 | 7895 |  | Level 24 25 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 0.6 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-09-01 | 2022-09-15 | 100% |  | 2.1429 | 135 | 12.25 | 540 | 49 | 378 | 162 | 105 | 645 | 645 | 0
| 24 | 877 | 13144 | 7895 |  | Level 24 25 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 0.6 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-09-01 | 2022-09-15 | 100% |  | 2.1429 | 135 | 12.25 | 540 | 49 | 378 | 162 | 105 | 645 | 645 | 0
| 24 | 874 | 13145 | 7862 |  | Level 24 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-09-01 | 2022-09-02 | 100% |  | 0.28571 | 135 | 12.25 | 540 | 49 | 378 | 162 | 14 | 554 | 554 | 0
| 24 | 906 | 13280 | 6704 |  | Level 24 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-08 | 2022-09-21 | 100% |  | 2 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 49 | 319 | 319 | 0
| 24 | 936 | 13307 | 8083 |  | Level 24 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-10 | 2022-10-07 | 100% |  | 4 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 98 | 368 | 368 | 0
| 24 | 848 | 13117 | 8073 |  | Level 24 Residence | Access Scaffold |  | Independent | 5 | 1.3 | 3 |  | 3 |  |  | 15 | m2-LxH | OFF HIRED | 2022-08-29 | 2022-10-05 | 100% |  | 5.4286 | 14 | 0.84 | 210 | 12.6 | 147 | 63 | 68.4 | 278.4 | 278.4 | 0
| 24 | 644 | 12867 | 8084 |  | Level 24 Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-02 | 2022-10-07 | 100% |  | 9.5714 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 234.5 | 504.5 | 504.5 | 0
| 24 | 1006 | 13390 | 6703 |  | Level 24 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-09-20 | 2022-09-23 | 100% |  | 0.57143 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 17.5 | 355 | 355 | 0
| 24 | 1044 | 13481 | 6719 |  | Level 24 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 2 |  | 2 |  |  | 12.5 | m3 | OFF HIRED | 2022-09-24 | 2022-09-24 | 100% |  | 0.14286 | 7.5 | 0.7 | 93.75 | 8.75 | 65.625 | 28.125 | 1.25 | 95 | 95 | 0
| 24 | 1045 | 13481 | 6719 |  | Level 24 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 2 |  | 2 |  |  | 12.5 | m3 | OFF HIRED | 2022-09-24 | 2022-09-24 | 100% |  | 0.14286 | 7.5 | 0.7 | 93.75 | 8.75 | 65.625 | 28.125 | 1.25 | 95 | 95 | 0
| 24 | 1046 | 13481 | 6719 |  | Level 24 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 2 |  | 2 |  |  | 12.5 | m3 | OFF HIRED | 2022-09-24 | 2022-09-24 | 100% |  | 0.14286 | 7.5 | 0.7 | 93.75 | 8.75 | 65.625 | 28.125 | 1.25 | 95 | 95 | 0
| 24 | 1086 | 13519 | 8214 |  | Level 24 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-29 | 2022-11-09 | 100% |  | 6 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 147 | 417 | 417 | 0
| 24 | 1095 | 13528 | 8060 |  | Level 24 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-30 | 2022-10-03 | 100% |  | 0.57143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 14 | 284 | 284 | 0
| 24 | 1321 | 13809 | 8255 |  | Level 24 To 26 Residence | Access Scaffold |  | INDEPENDENT | 17.5 | 1 | 2.5 |  | 2.5 |  |  | 43.75 | m2-LxH | OFF HIRED | 2022-10-29 | 2022-11-19 | 100% |  | 3.1429 | 14 | 0.84 | 612.5 | 36.75 | 428.75 | 183.75 | 115.5 | 728 | 728 | 0
| 24 | 1410 | 13898 | 8585 |  | Level 24 Hotel | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 2 |  | 2 |  |  | 10 | m2-LxH | OFF HIRED | 2022-11-10 | 2023-02-21 | 100% |  | 14.8571 | 14 |  | 140 | 0 | 98 | 42 | 0 | 140 | 98 | 42 |  |  | #VALUE! | 98 | #VALUE! | #VALUE!
| 24 | 1561 | 14094 | 8480 |  | Level 24 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 2.6 |  | 2.6 |  |  | 2.6 | rm | OFF HIRED | 2022-12-09 | 2022-12-31 | 100% |  | 3.2857 | 135 | 12.25 | 351 | 31.85 | 245.7 | 105.3 | 104.65 | 455.65 | 455.65 | 0
| 24 | 1516 | 14053 | 8303 |  | Level 24 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-11-29 | 2022-12-05 | 100% |  | 1 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 24.5 | 294.5 | 294.5 | 0
| 24 | 1516 | 14053 | 8303 |  | Level 24 Hotel | Cantiliver |  | Cantiliver | 1 | 0.6 |  |  |  | 0.6 |  | 0.36 | m2-LxW | OFF HIRED | 2022-11-29 | 2022-12-05 | 100% |  | 1 | 36.5 | 3.15 | 13.14 | 1.134 | 9.198 | 3.942 | 1.134 | 14.274 | 14.274 | 0
| 25 | 510 | 12722 | 8080 |  | Level 25 to 26 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-14 | 2022-10-07 | 100% |  | 12.2857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 301 | 571 | 571 | 0
| 25 | 514 | 12722 | 8080 |  | Level 25 to 26 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-14 | 2022-10-07 | 100% |  | 12.2857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 301 | 571 | 571 | 0
| 25 | 937 | 13308 | 8181 |  | Level 25 Hotel | Access Scaffold |  | Independent | 5 | 1 | 2.5 |  | 2.5 |  |  | 12.5 | m2-LxH | OFF HIRED | 2022-09-10 | 2022-10-31 | 100% |  | 7.4286 | 14 | 0.84 | 175 | 10.5 | 122.5 | 52.5 | 78 | 253 | 253 | 0
| 25 | 907 | 13281 | 8181 |  | Level 25 Hotel | Access Scaffold |  | Independent | 6.5 | 1 | 3 |  | 3 |  |  | 19.5 | m2-LxH | OFF HIRED | 2022-09-08 | 2022-10-31 | 100% |  | 7.7143 | 14 | 0.84 | 273 | 16.38 | 191.1 | 81.9 | 126.36 | 399.36 | 399.36 | 0
| 25 | 949 | 13324 | 8080 |  | Level 25 Hotel | Access Scaffold |  | Independent | 6 | 1 | 2 |  | 2 |  |  | 12 | m2-LxH | OFF HIRED | 2022-09-13 | 2022-10-07 | 100% |  | 3.5714 | 14 | 0.84 | 168 | 10.08 | 117.6 | 50.4 | 36 | 204 | 204 | 0
| 25 | 353 | 12508 | 7732 |  | Level 25 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-06-26 | 2022-07-19 | 100% |  | 3.4286 | 135 |  | 405 | 0 | 283.5 | 121.5 | 0 | 405 | 405 | 0
| 25 | 143 | 12244 | 7570 |  | Level 25 Residence | Access Scaffold |  | INDEPENDENT | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 3.6 | m2-LxH | OFF HIRED | 2022-06-06 | 2022-06-12 | 100% |  | 1 | 14 |  | 50.4 | 0 | 35.28 | 15.12 | 0 | 50.4 | 50.4 | 0
| 25 | 193 | 12189 | 7575 |  | Level 25 Residence | Access Scaffold |  | INDEPENDENT | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2.6 | m2-LxH | OFF HIRED | 2022-06-09 | 2022-06-19 | 100% |  | 1.5714 | 14 |  | 36.4 | 0 | 25.48 | 10.92 | 0 | 36.4 | 36.4 | 0
| 25 | 542 | 12754 | 7802 |  | Level 25 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-07-18 | 2022-08-03 | 100% |  | 2.4286 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 89.25 | 494.25 | 494.25 | 0
| 25 | 556 | 12767 | 6724 |  | Level 25 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 3.5 | 1 | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-07-20 | 2022-09-26 | 100% |  | 9.8571 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 301.875 | 639.375 | 639.375 | 0
| 25 | 755 | 13020 | 8121 |  | Level 25 To 28 Residence | Access Scaffold |  | Independent | 40 | 1.3 | 4 | 1 | 3 |  |  | 120 | m2-LxH | OFF HIRED | 2022-08-16 | 2022-10-19 | 100% |  | 9.2857 | 14 | 0.84 | 1680 | 100.8 | 1176 | 504 | 936 | 2616 | 2616 | 0
| 25 | 883 | 13253 | 8054 |  | Level 25 Residence | Birdcage Scaffold |  | Birdcage | 9 | 6.5 | 6 |  | 6 |  |  | 351 | m3 | OFF HIRED | 2022-09-03 | 2022-10-01 | 100% |  | 4.1429 | 7.5 | 0.7 | 2632.5 | 245.7 | 1842.75 | 789.75 | 1017.9 | 3650.4 | 3650.4 | 0
| 25 | 977 | 13353 | 8082 |  | Level 25 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 2.5 | 7 |  | 7 |  |  | 7 | rm | OFF HIRED | 2022-09-16 | 2022-10-07 | 100% |  | 3.1429 | 135 | 12.25 | 945 | 85.75 | 661.5 | 283.5 | 269.5 | 1214.5 | 1214.5 | 0
| 25 | 982 | 13360 | 8083 |  | Level 25 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 2.5 | 7 |  | 7 |  |  | 7 | rm | OFF HIRED | 2022-09-16 | 2022-10-07 | 100% |  | 3.1429 | 135 | 12.25 | 945 | 85.75 | 661.5 | 283.5 | 269.5 | 1214.5 | 1214.5 | 0
| 25 | 960 | 13335 | 8073 |  | Level 25 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 2.5 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-14 | 2022-10-05 | 100% |  | 3.1429 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 77 | 347 | 347 | 0
| 25 | 891 | 13262 | 8085 |  | Level 25 Residence | Access Scaffold |  | Independent | 4 | 1.3 | 4 |  | 4 |  |  | 16 | m2-LxH | OFF HIRED | 2022-09-06 | 2022-10-07 | 100% |  | 4.5714 | 14 | 0.84 | 224 | 13.44 | 156.8 | 67.2 | 61.44 | 285.44 | 285.44 | 0
| 25 | 961 | 13336 | 6721 |  | Level 25 Residence | Access Scaffold |  | Independent | 4 | 1.3 | 3 |  | 3 |  |  | 12 | m2-LxH | OFF HIRED | 2022-09-14 | 2022-09-24 | 100% |  | 1.5714 | 14 | 0.84 | 168 | 10.08 | 117.6 | 50.4 | 15.84 | 183.84 | 183.84 | 0
| 25 | 891 | 13262 | 8085 |  | Level 25 Residence | Cantiliver |  | Cantiliver | 4 | 1.2 |  |  |  | 1 |  | 4.8 | m2-LxW | OFF HIRED | 2022-09-06 | 2022-10-07 | 100% |  | 4.5714 | 36.5 | 3.15 | 175.2 | 15.12 | 122.64 | 52.56 | 69.12 | 244.32 | 244.32 | 0
| 25 | 1156 | 13641 | 8341 |  | Level 25 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 6 |  | 6 |  |  | 6 | rm | OFF HIRED | 2022-10-07 | 2022-12-17 | 100% |  | 10.2857 | 135 | 12.25 | 810 | 73.5 | 567 | 243 | 756 | 1566 | 1566 | 0
| 25 | 1075 | 13511 | 8143 |  | Level 25 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-09-28 | 2022-10-25 | 100% |  | 4 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 147 | 552 | 552 | 0
| 25 | 1076 | 13511 | 8143 |  | Level 25 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-09-28 | 2022-10-25 | 100% |  | 4 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 147 | 552 | 552 | 0
| 25 | 1077 | 13511 | 8143 |  | Level 25 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-09-28 | 2022-10-25 | 100% |  | 4 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 147 | 552 | 552 | 0
| 25 | 1078 | 13511 | 8143 |  | Level 25 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-09-28 | 2022-10-25 | 100% |  | 4 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 147 | 552 | 552 | 0
| 25 | 1105 | 13538 | 8201 |  | Level 25 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-10-01 | 2022-11-05 | 100% |  | 5.1429 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 157.5 | 495 | 495 | 0
| 25 | 1104 | 13537 | 8082 |  | Level 29 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-10-01 | 2022-10-07 | 100% |  | 1 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 36.75 | 441.75 | 441.75 | 0
| 25 | 1066 | 13503 | 8083 |  | Level 25 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 6 |  | 6 |  |  | 6 | rm | OFF HIRED | 2022-09-27 | 2022-10-07 | 100% |  | 1.5714 | 135 | 12.25 | 810 | 73.5 | 567 | 243 | 115.5 | 925.5 | 925.5 | 0
| 25 | 1142 | 13626 | 8474 |  | Level 25 Hotel | Access Scaffold |  | Independent | 6.3 | 1.3 | 2.5 |  | 2.5 |  |  | 15.75 | m2-LxH | OFF HIRED | 2022-10-06 | 2022-12-27 | 100% |  | 11.8571 | 14 | 0.84 | 220.5 | 13.23 | 154.35 | 66.15 | 156.87 | 377.37 | 377.37 | 0
| 25 | 1056 | 13495 | 8227 |  | Level 25 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 2 |  | 2 |  |  | 12.5 | m3 | OFF HIRED | 2022-09-26 | 2022-11-01 | 100% |  | 5.2857 | 7.5 | 0.7 | 93.75 | 8.75 | 65.625 | 28.125 | 46.25 | 140 | 140 | 0
| 25 | 1057 | 13495 | 8227 |  | Level 25 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 2 |  | 2 |  |  | 12.5 | m3 | OFF HIRED | 2022-09-26 | 2022-11-01 | 100% |  | 5.2857 | 7.5 | 0.7 | 93.75 | 8.75 | 65.625 | 28.125 | 46.25 | 140 | 140 | 0
| 25 | 1058 | 13495 | 8227 |  | Level 25 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 2 |  | 2 |  |  | 12.5 | m3 | OFF HIRED | 2022-09-26 | 2022-11-01 | 100% |  | 5.2857 | 7.5 | 0.7 | 93.75 | 8.75 | 65.625 | 28.125 | 46.25 | 140 | 140 | 0
| 25 | 1140 | 13624 | 8194 |  | Level 25 Residence | Birdcage Scaffold |  | Birdcage | 7.5 | 2.5 | 2 |  | 2 |  |  | 37.5 | m3 | OFF HIRED | 2022-10-05 | 2022-11-05 | 100% |  | 4.5714 | 7.5 | 0.7 | 281.25 | 26.25 | 196.875 | 84.375 | 120 | 401.25 | 401.25 | 0
| 25 | 1408 | 13896 | 8492 |  | Level 25 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 1.5 |  | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2022-11-10 | 2023-01-05 | 100% |  | 8.1429 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 60.75 | 149.625 | 352.125 | 352.125 | 0
| 25 | 1407 | 13895 |  |  | Level 25 Hotel | Access Scaffold |  | INDEPENDENT | 8.8 | 1.3 | 3 |  | 3 |  |  | 26.4 | m2-LxH | ON HIRE | 2022-11-10 |  | 100% |  | 15.8571 | 14 |  | 369.6 | 0 | 258.72 | 0 | 0 | 258.72 | 258.72 | 0
| 25 | 1407 | 13895 |  |  | Level 25 Hotel | Birdcage Scaffold |  | Support Tower | 2.5 | 2.5 | 2 |  | 2 |  |  | 12.5 | m3 | ON HIRE | 2022-11-10 |  | 100% |  | 15.8571 | 7.5 |  | 93.75 | 0 | 65.625 | 0 | 0 | 65.625 | 65.625 | 0
| 25 | 1503 | 13990 | 8321 |  | Level 25 Hotel | HEAVY DUTY TOWER |  | Tower | 2 | 1.3 | 1.5 |  | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2022-11-26 | 2022-12-11 | 100% |  | 2.2857 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 60.75 | 42 | 244.5 | 244.5 | 0
| 25 | 1582 | 14114 | 8476 |  | Level 25 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.5 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-12-12 | 2022-12-29 | 100% |  | 2.5714 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 63 | 333 | 333 | 0
| 25 | 1511 | 14000 | 8422 |  | Level 25 To 26 Residence | Access Scaffold |  | INDEPENDENT | 17 | 1 | 2 |  | 2 |  |  | 34 | m2-LxH | OFF HIRED | 2022-11-29 | 2023-01-11 | 100% |  | 6.2857 | 14 | 0.84 | 476 | 28.56 | 333.2 | 142.8 | 179.52 | 655.52 | 655.52 | 0
| 25 | 1580 | 14111 |  |  | Level 25 Hotel | Access Scaffold |  | INDEPENDENT | 5 | 1 | 1.8 |  | 1.8 |  |  | 9 | m2-LxH | ON HIRE | 2022-12-10 |  | 100% |  | 11.5714 | 14 | 0.84 | 126 | 7.56 | 88.2 | 0 | 87.48 | 175.68 | 145.44 | 30.24 |  |  | #VALUE! | 268.38 | #VALUE! | #VALUE!
| 25 | 1580 | 14111 |  |  | Level 25 Hotel | Access Scaffold |  | INDEPENDENT | 5 | 1 | 1.8 |  | 1.8 |  |  | 9 | m2-LxH | ON HIRE | 2022-12-10 |  | 100% |  | 11.5714 | 14 | 0.84 | 126 | 7.56 | 88.2 | 0 | 87.48 | 175.68 | 145.44 | 30.24 |  |  | #VALUE! | 268.38 | #VALUE! | #VALUE!
| 25 | 1580 | 14111 |  |  | Level 25 Hotel | Cantiliver |  | Cantiliver | 5 | 0.6 |  |  |  | 0.6 |  | 1.8 | m2-LxW | ON HIRE | 2022-12-10 |  | 100% |  | 11.5714 | 36.5 | 3.15 | 65.7 | 5.67 | 45.99 | 0 | 65.61 | 111.6 | 88.92 | 22.68 |  |  | #VALUE! | 268.38 | #VALUE! | #VALUE!
| 25 | 1575 | 14111 |  |  | Level 25 Hotel | Cantiliver |  | Cantiliver | 5 | 0.6 |  |  |  | 0.6 |  | 1.8 | m2-LxW | ON HIRE | 2022-12-10 |  | 100% |  | 11.5714 | 36.5 | 3.15 | 65.7 | 5.67 | 45.99 | 0 | 65.61 | 111.6 | 88.92 | 22.68 |  |  | #VALUE! | 268.38 | #VALUE! | #VALUE!
| 26 | 350 | 12505 | 7591 |  | Level 26 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-06-24 | 2022-06-29 | 100% |  | 0.85714 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 31.5 | 436.5 | 436.5 | 0
| 26 |  | 12236 | 8121 |  | Level 26 to Roof | Edge Prorection |  | Edge Prorection | 644 | [6 empty] | 644 | lm | OFF HIRED | 2022-06-15 | 2022-10-19 | 100% |  | 18.1429 | 24 |  | 15456 | 0 | 10819.2 | 4636.8 | 0 | 15456 | 15456 | 0
| 26 | 513 | 12718 | 7877 |  | Level 26 & 27 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.8 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-07-14 | 2022-09-09 | 100% |  | 8.2857 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 304.5 | 709.5 | 709.5 | 0
| 26 | 534 | 12745 | 7725 |  | Level 26 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.8 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-17 | 2022-07-18 | 100% |  | 0.28571 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 7 | 277 | 277 | 0
| 26 | 500 | 12704 | 6701 |  | Level 26 Hotel | Birdcage Scaffold |  | INDEPENDENT | 12 | 1.8 | 6 | 1 | 5 |  |  | 60 | m2-LxH | OFF HIRED | 2022-07-13 | 2022-09-19 | 100% |  | 9.8571 | 18 | 1.05 | 1080 | 63 | 756 | 324 | 621 | 1701 | 1701 | 0
| 26 | 737 | 12995 | 7852 |  | Level 26 Hotel | Access Scaffold |  | Independent | 5 | 1.3 | 5 | 1 | 4 |  |  | 20 | m2-LxH | OFF HIRED | 2022-08-15 | 2022-08-29 | 100% |  | 2.1429 | 14 | 0 | 280 | 0 | 196 | 84 | 0 | 280 | 280 | 0
| 26 | 352 | 12507 | 7732 |  | Level 26 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-06-26 | 2022-07-19 | 100% |  | 3.4286 | 135 |  | 405 | 0 | 283.5 | 121.5 | 0 | 405 | 405 | 0
| 26 | 267 | 12381 | 7590 |  | Level 26 Residance | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-06-17 | 2022-06-28 | 100% |  | 1.7143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 42 | 312 | 312 | 0
| 26 | 269 | 12383 | 6723 |  | Level 26 Residance | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-06-17 | 2022-09-26 | 100% |  | 14.5714 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 357 | 627 | 627 | 0
| 26 | 317 | 12418 | 7582 |  | Level 26 Residance | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-06-21 | 2022-06-24 | 100% |  | 0.57143 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 21 | 426 | 426 | 0
| 26 | 200 | 12196 | 7585 |  | Level 26 Residence | Access Scaffold |  | INDEPENDENT | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 3.6 | m2-LxH | OFF HIRED | 2022-06-09 | 2022-06-26 | 100% |  | 2.5714 | 14 | 0.84 | 50.4 | 3.024 | 35.28 | 15.12 | 7.776 | 58.176 | 58.176 | 0
| 26 | 186 | 12184 | 7582 |  | Level 26 Residence | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 13 | 1 | 12 |  |  | 48 | m2-LxH | OFF HIRED | 2022-06-09 | 2022-06-24 | 100% |  | 2.2857 | 14 | 0.84 | 672 | 40.32 | 470.4 | 201.6 | 92.16 | 764.16 | 764.16 | 0
| 26 | 388 | 12554 | 7802 |  | Level 26 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-06-28 | 2022-08-03 | 100% |  | 5.2857 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 194.25 | 599.25 | 599.25 | 0
| 26 | 544 | 12755 | 7802 |  | Level 26 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-07-18 | 2022-08-03 | 100% |  | 2.4286 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 89.25 | 494.25 | 494.25 | 0
| 26 | 425 | 12585 | 7814 |  | Level 26 Residance | Access Scaffold |  | INDEPENDENT | 12 | 1.3 | 4 | 1 | 3 |  |  | 36 | m2-LxH | OFF HIRED | 2022-07-03 | 2022-08-08 | 100% |  | 5.2857 | 14 | 0.84 | 504 | 30.24 | 352.8 | 151.2 | 159.84 | 663.84 | 663.84 | 0
| 26 | 606 | 12823 | 6730 |  | Level 26 To 28 Residence | Access Scaffold |  | Tower | 2.5 | 1.3 | 11 | 1 | 10 |  |  | 10 | rm | OFF HIRED | 2022-07-27 | 2022-09-28 | 100% |  | 9.1429 | 135 | 12.25 | 1350 | 122.5 | 945 | 405 | 1120 | 2470 | 2470 | 0
| 26 | 880 | 13150 | 7897 |  | Level 26 27 28 29 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 0.6 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-09-03 | 2022-09-16 | 100% |  | 2 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 73.5 | 478.5 | 478.5 | 0
| 26 | 880 | 13150 | 7897 |  | Level 26 27 28 29 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 0.6 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-09-03 | 2022-09-16 | 100% |  | 2 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 73.5 | 478.5 | 478.5 | 0
| 26 | 881 | 13150 | 7897 |  | Level 26 27 28 29 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 0.6 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-09-03 | 2022-09-16 | 100% |  | 2 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 73.5 | 478.5 | 478.5 | 0
| 26 | 881 | 13150 | 7897 |  | Level 26 27 28 29 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 0.6 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-09-03 | 2022-09-16 | 100% |  | 2 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 73.5 | 478.5 | 478.5 | 0
| 26 | 934 | 13305 | 8060 |  | Level 26 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-09-10 | 2022-10-03 | 100% |  | 3.4286 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 105 | 442.5 | 442.5 | 0
| 26 | 513 | 12718 | 7877 |  | Level 26 & 27 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.8 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-07-14 | 2022-09-09 | 100% |  | 8.2857 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 304.5 | 709.5 | 709.5 | 0
| 26 | 708 | 12972 | 7835 |  | Level 26 Residence | Access Scaffold |  | Tower | 2.5 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-08-11 | 2022-08-19 | 100% |  | 1.2857 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 47.25 | 452.25 | 452.25 | 0
| 26 | 948 | 13323 | 8062 |  | Level 26 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-13 | 2022-10-03 | 100% |  | 3 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 73.5 | 343.5 | 343.5 | 0
| 26 | 1027 | 13462 | 8055 |  | Level 26 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-09-23 | 2022-10-01 | 100% |  | 1.2857 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 39.375 | 376.875 | 376.875 | 0
| 26 | 966 | 13341 | 6714 |  | Level 26 Hotel | Access Scaffold |  | Independent | 20.5 | 1.3 | 2 |  | 2 |  |  | 41 | m2-LxH | OFF HIRED | 2022-09-15 | 2022-09-24 | 100% |  | 1.4286 | 14 | 0.84 | 574 | 34.44 | 401.8 | 172.2 | 49.2 | 623.2 | 623.2 | 0
| 26 | 995 | 13379 | 8112 |  | Level 26 Residence | Access Scaffold |  | Independent | 13.5 | 1.8 | 2.5 |  | 2.5 |  |  | 33.75 | m2-LxH | OFF HIRED | 2022-09-19 | 2022-10-17 | 100% |  | 4.1429 | 18 | 1.05 | 607.5 | 35.4375 | 425.25 | 0 | 146.8125 | 572.0625 | 572.0625 | 0
| 26 | 1090 | 13523 | 8227 |  | Level 26 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-09-30 | 2022-11-01 | 100% |  | 4.7143 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 144.375 | 481.875 | 481.875 | 0
| 26 | 1266 | 13704 | 8167 |  | Level 26 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-10-21 | 2022-10-28 | 100% |  | 1.1429 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 42 | 447 | 447 | 0
| 26 | 1273 | 13711 | 8167 |  | Level 26 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-10-21 | 2022-10-28 | 100% |  | 1.1429 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 42 | 447 | 447 | 0
| 26 | 1341 | 13829 | 8349 |  | Level 26 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-11-01 | 2022-12-21 | 100% |  | 7.2857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 178.5 | 448.5 | 448.5 | 0
| 26 | 1412 | 13900 | 8443 |  | Level 26 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 1.5 |  | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2022-11-10 | 2023-01-19 | 100% |  | 10.1429 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 60.75 | 186.375 | 388.875 | 388.875 | 0
| 26 | 1355 | 13843 | 8348 |  | Level 26 Residence | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 2 |  | 2 |  |  | 8 | m2-LxH | OFF HIRED | 2022-11-03 | 2022-12-20 | 100% |  | 6.8571 | 14 | 0.84 | 112 | 6.72 | 78.4 | 33.6 | 46.08 | 158.08 | 158.08 | 0
| 26 | 1306 | 13744 | 8247 |  | Level 26 To 29 Residence | Access Scaffold |  | INDEPENDENT | 39 | 1 | 2.5 |  | 2.5 |  |  | 97.5 | m2-LxH | OFF HIRED | 2022-10-27 | 2022-11-17 | 100% |  | 3.1429 | 14 | 0.84 | 1365 | 81.9 | 955.5 | 409.5 | 257.4 | 1622.4 | 1622.4 | 0
| 26 | 1311 | 13749 | 8348 |  | Level 26 Residence | Access Scaffold |  | INDEPENDENT | 8 | 1.3 | 2.5 |  | 2.5 |  |  | 20 | m2-LxH | OFF HIRED | 2022-10-28 | 2022-12-20 | 100% |  | 7.7143 | 14 | 0.84 | 280 | 16.8 | 196 | 84 | 129.6 | 409.6 | 409.6 | 0
| 26 | 1478 | 13966 | 8284 |  | Level 26 To 27 Residence | Access Scaffold |  | INDEPENDENT | 17.8 | 1 | 2 |  | 2 |  |  | 35.6 | m2-LxH | OFF HIRED | 2022-11-23 | 2022-11-27 | 100% |  | 0.71429 | 14 | 0.84 | 498.4 | 29.904 | 348.88 | 149.52 | 21.36 | 519.76 | 519.76 | 0
| 26 | 1412 | 13900 | 8443 |  | Level 26 Residence | Cantiliver |  | Cantiliver | 2.5 | 0.6 |  |  |  | 1 |  | 1.5 | m2-LxW | OFF HIRED | 2022-11-10 | 2023-01-19 | 100% |  | 10.1429 | 36.5 | 3.15 | 54.75 | 4.725 | 38.325 | 16.425 | 47.925 | 102.675 | 102.675 | 0
| 26 | 1502 | 13989 |  |  | Level 26 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 1.5 |  | 1.5 |  |  | 1.5 | rm | ON HIRE | 2022-11-26 |  | 100% |  | 13.5714 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 0 | 249.375 | 391.125 | 317.625 | 73.5 |  |  | #VALUE! | 184.9295 | #VALUE! | #VALUE!
| 26 | 1535 | 14071 |  |  | Level 26 Hotel | Birdcage Scaffold |  | Birdcage | 6.8 | 4.3 | 5 |  | 5 |  |  | 146.2 | m3 | ON HIRE | 2022-12-06 |  | 100% |  | 12.1429 | 7.5 | 0.7 | 1096.5 | 102.34 | 767.55 | 0 | 1242.7 | 2010.25 | 1600.89 | 409.36 |  |  | #VALUE! | 1037.7412 | #VALUE! | #VALUE!
| 26 | 1535 | 14071 |  |  | Level 26 Hotel | Cantiliver |  | Cantiliver | 4.3 | 1.5 |  |  |  | 1.5 |  | 9.675 | m2-LxW | ON HIRE | 2022-12-06 |  | 100% |  | 12.1429 | 36.5 | 3.15 | 353.1375 | 30.4762 | 247.1962 | 0 | 370.0687 | 617.265 | 495.36 | 121.905 |  |  | #VALUE! | 1037.7412 | #VALUE! | #VALUE!
| 26 | 1535 | 14071 |  |  | Level 26 Hotel | Cantiliver |  | Cantiliver | 2.5 | 0.6 |  |  |  | 0.6 |  | 0.9 | m2-LxW | ON HIRE | 2022-12-06 |  | 100% |  | 12.1429 | 36.5 | 3.15 | 32.85 | 2.835 | 22.995 | 0 | 34.425 | 57.42 | 46.08 | 11.34 |  |  | #VALUE! | 1037.7412 | #VALUE! | #VALUE!
| 26 | 1502 | 13989 |  |  | Level 26 Hotel | Cantiliver |  | Cantiliver | 1 | 1.3 |  |  |  | 1.3 |  | 1.69 | m2-LxW | ON HIRE | 2022-11-26 |  | 100% |  | 13.5714 | 36.5 | 3.15 | 61.685 | 5.3235 | 43.1795 | 0 | 72.2475 | 115.427 | 94.133 | 21.294 |  |  | #VALUE! | 184.9295 | #VALUE! | #VALUE!
| 27 | 99 | 12145 | 7571 |  | Level 27 Hotel | Access Scaffold |  | INDEPENDENT | 4 | 1 | 2.5 | 1 | 1.5 |  |  | 6 | m2-LxH | OFF HIRED | 2022-06-01 | 2022-06-12 | 100% |  | 1.7143 | 14 |  | 84 | 0 | 58.8 | 25.2 | 0 | 84 | 84 | 0
| 27 | 311 | 12440 | 7743 |  | Level 27 to 23 Hotel | Access Scaffold |  | INDEPENDENT | 65 | 1.3 | 3.5 | 1 | 2.5 |  |  | 162.5 | m2-LxH | OFF HIRED | 2022-06-23 | 2022-07-29 | 100% |  | 5.2857 | 14 | 0.84 | 2275 | 136.5 | 1592.5 | 682.5 | 721.5 | 2996.5 | 2996.5 | 0
| 27 | 464 | 12621 | 7712 |  | Level 27 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 9 | 1 | 8 |  |  | 8 | rm | OFF HIRED | 2022-07-07 | 2022-07-14 | 100% |  | 1.1429 | 135 | 12.25 | 1080 | 98 | 756 | 324 | 112 | 1192 | 1192 | 0
| 27 | 464 | 12621 | 7712 |  | Level 27 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 6 | 1 | 5 |  |  | 5 | rm | OFF HIRED | 2022-07-07 | 2022-07-14 | 100% |  | 1.1429 | 135 | 12.25 | 675 | 61.25 | 472.5 | 202.5 | 70 | 745 | 745 | 0
| 27 | 499 | 12703 | 8239 |  | Level 27 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-13 | 2022-11-15 | 100% |  | 18 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 441 | 711 | 711 | 0
| 27 | 539 | 12749 | 6726 |  | Level 27 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.8 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-18 | 2022-09-26 | 100% |  | 10.1429 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 248.5 | 518.5 | 518.5 | 0
| 27 | 668 | 12951 | 6738 |  | Level 27 To 28 Hotel | Access Scaffold |  | Independent | 7.5 | 1.3 | 4 | 1 | 3 |  |  | 22.5 | m2-LxH | OFF HIRED | 2022-08-08 | 2022-09-27 | 100% |  | 7.2857 | 14 | 0.84 | 315 | 18.9 | 220.5 | 94.5 | 137.7 | 452.7 | 452.7 | 0
| 27 | 878 | 13148 | 8095 |  | Level 27 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-09-02 | 2022-10-11 | 100% |  | 5.7143 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 210 | 615 | 615 | 0
| 27 | 924 | 13295 | 8062 |  | Level 27 Hotel | Access Scaffold |  | Independent | 37 | 1 | 2 |  | 2 |  |  | 74 | m2-LxH | OFF HIRED | 2022-09-09 | 2022-10-03 | 100% |  | 3.5714 | 14 | 0.84 | 1036 | 62.16 | 725.2 | 310.8 | 222 | 1258 | 1258 | 0
| 27 | 231 | 12348 | 7581 |  | Level 27 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-06-14 | 2022-06-23 | 100% |  | 1.4286 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 52.5 | 457.5 | 457.5 | 0
| 27 | 365 | 12520 | 7802 |  | Level 27 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-06-27 | 2022-08-03 | 100% |  | 5.4286 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 199.5 | 604.5 | 604.5 | 0
| 27 | 433 | 12593 | 7814 |  | Level 27 Residance | Access Scaffold |  | INDEPENDENT | 12 | 1 | 4 | 1 | 3 |  |  | 36 | m2-LxH | OFF HIRED | 2022-07-04 | 2022-08-08 | 100% |  | 5.1429 | 14 | 0.84 | 504 | 30.24 | 352.8 | 151.2 | 155.52 | 659.52 | 659.52 | 0
| 27 | 637 | 12860 | 7865 |  | Level 27 Residence | Access Scaffold |  | Tower | 2.5 | 1.3 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-08-01 | 2022-09-03 | 100% |  | 4.8571 | 135 |  | 540 | 0 | 378 | 162 | 0 | 540 | 540 | 0
| 27 | 654 | 12878 | 7814 |  | Level 27 Residence | Access Scaffold |  | Tower | 1.3 | 0.6 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-08-03 | 2022-08-08 | 100% |  | 0.85714 | 135 |  | 405 | 0 | 283.5 | 121.5 | 0 | 405 | 405 | 0
| 27 | 756 | 13021 | 7846 |  | Level 27 Residence | Access Scaffold |  | Tower | 1.8 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-08-17 | 2022-08-27 | 100% |  | 1.5714 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 57.75 | 462.75 | 462.75 | 0
| 27 | 914 | 13287 | 6706 |  | Level 27 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-08 | 2022-09-21 | 100% |  | 2 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 49 | 319 | 319 | 0
| 27 | 917 | 13290 | 6706 |  | Level 27 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-09-08 | 2022-09-21 | 100% |  | 2 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 73.5 | 478.5 | 478.5 | 0
| 27 | 931 | 13302 | 7895 |  | Level 27 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-09-10 | 2022-09-15 | 100% |  | 0.85714 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 26.25 | 363.75 | 363.75 | 0
| 27 | 898 | 13271 | 8086 |  | Level 27 Residence | Birdcage Scaffold |  | Birdcage | 8 | 6.5 | 6 |  | 6 |  |  | 312 | m3 | OFF HIRED | 2022-09-06 | 2022-10-07 | 100% |  | 4.5714 | 7.5 | 0.7 | 2340 | 218.4 | 1638 | 702 | 998.4 | 3338.4 | 3338.4 | 0
| 27 | 737 | 13046 | 7852 |  | Level 27 Hotel | Access Scaffold |  | Independent | 10 | 1.3 | 2 |  | 2 |  |  | 20 | m2-LxH | OFF HIRED | 2022-08-20 | 2022-08-29 | 100% |  | 1.4286 | 14 | 0.84 | 280 | 16.8 | 196 | 84 | 24 | 304 | 304 | 0
| 27 | 997 | 13381 | 6703 |  | Level 27 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 2.5 | 3.5 |  | 3.5 |  |  | 3.5 | rm | OFF HIRED | 2022-09-19 | 2022-09-23 | 100% |  | 0.71429 | 135 | 12.25 | 472.5 | 42.875 | 330.75 | 141.75 | 30.625 | 503.125 | 503.125 | 0
| 27 | 990 | 13370 | 8143 |  | Level 27 Residence | Access Scaffold |  | Independent | 16 | 1.8 | 2.5 |  | 2.5 |  |  | 40 | m2-LxH | OFF HIRED | 2022-09-17 | 2022-10-25 | 100% |  | 5.5714 | 18 | 1.05 | 720 | 42 | 504 | 216 | 234 | 954 | 954 | 0
| 27 | 1091 | 13524 | 8227 |  | Level 27 Residence | Access Scaffold |  | Independent | 1.8 | 1.8 | 2.5 |  | 2.5 |  |  | 4.5 | m2-LxH | OFF HIRED | 2022-09-30 | 2022-11-01 | 100% |  | 4.7143 | 18 | 1.05 | 81 | 4.725 | 56.7 | 24.3 | 22.275 | 103.275 | 103.275 | 0
| 27 | 1356 | 13844 | 8349 |  | Level 27 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-11-03 | 2022-12-21 | 100% |  | 7 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 171.5 | 441.5 | 441.5 | 0
| 27 | 1300 | 13739 | 8349 |  | Level 27 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-10-27 | 2022-12-21 | 100% |  | 8 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 196 | 466 | 466 | 0
| 27 | 1301 | 13739 | 8349 |  | Level 27 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-10-27 | 2022-12-21 | 100% |  | 8 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 196 | 466 | 466 | 0
| 27 | 1312 | 13750 | 8319 |  | Level 27 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-10-28 | 2022-12-09 | 100% |  | 6.1429 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 150.5 | 420.5 | 420.5 | 0
| 27 | 1366 | 13854 | 8443 |  | Level 27 Residence | Access Scaffold |  | INDEPENDENT | 3.5 | 1 | 2 |  | 2 |  |  | 7 | m2-LxH | OFF HIRED | 2022-11-04 | 2023-01-19 | 100% |  | 11 | 14 | 0.84 | 98 | 5.88 | 68.6 | 29.4 | 64.68 | 162.68 | 162.68 | 0
| 27 | 1460 | 13948 | 8291 |  | Level 27 To 29 Residence | Access Scaffold |  | INDEPENDENT | 17 | 1 | 2 |  | 2 |  |  | 34 | m2-LxH | OFF HIRED | 2022-11-19 | 2022-11-29 | 100% |  | 1.5714 | 14 | 0.84 | 476 | 28.56 | 333.2 | 142.8 | 44.88 | 520.88 | 520.88 | 0
| 27 | 1327 | 13815 | 8258 |  | Level 27 Residence | Access Scaffold |  | Independent | 5 | 1.8 | 6 |  | 6 |  |  | 30 | m2-LxH | OFF HIRED | 2022-10-31 | 2022-11-19 | 100% |  | 2.8571 | 18 | 1.05 | 540 | 31.5 | 378 | 162 | 90 | 630 | 630 | 0
| 27 | 1623 | 14160 | 8447 |  | Level 27 To 28 Hotel | Access Scaffold |  | INDEPENDENT | 12 | 1 | 2 |  | 2 |  |  | 24 | m2-LxH | OFF HIRED | 2022-12-17 | 2023-01-21 | 100% |  | 5.1429 | 14 | 0.84 | 336 | 20.16 | 235.2 | 100.8 | 103.68 | 439.68 | 439.68 | 0
| 27 | 1567 | 14101 |  |  | Level 27 Hotel | Access Scaffold |  | INDEPENDENT | 6.3 | 1.3 | 1.8 |  | 1.8 |  |  | 11.34 | m2-LxH | ON HIRE | 2022-12-10 |  | 100% |  | 11.5714 | 14 | 0.84 | 158.76 | 9.5256 | 111.132 | 0 | 110.2248 | 221.3568 | 183.2544 | 38.1024 |  |  | #VALUE! | 314.244 | #VALUE! | #VALUE!
| 27 | 1568 | 14101 |  |  | Level 27 Hotel | Access Scaffold |  | INDEPENDENT | 6.3 | 1.3 | 1.8 |  | 1.8 |  |  | 11.34 | m2-LxH | ON HIRE | 2022-12-10 |  | 100% |  | 11.5714 | 14 | 0.84 | 158.76 | 9.5256 | 111.132 | 0 | 110.2248 | 221.3568 | 183.2544 | 38.1024 |  |  | #VALUE! | 314.244 | #VALUE! | #VALUE!
| 27 | 1567 | 14101 |  |  | Level 27 Hotel | Cantiliver |  | Cantiliver | 5 | 0.6 |  |  |  | 0.6 |  | 1.8 | m2-LxW | ON HIRE | 2022-12-10 |  | 100% |  | 11.5714 | 36.5 | 3.15 | 65.7 | 5.67 | 45.99 | 0 | 65.61 | 111.6 | 88.92 | 22.68 |  |  | #VALUE! | 314.244 | #VALUE! | #VALUE!
| 27 | 1568 | 14101 |  |  | Level 27 Hotel | Cantiliver |  | Cantiliver | 5 | 0.6 |  |  |  | 0.6 |  | 1.8 | m2-LxW | ON HIRE | 2022-12-10 |  | 100% |  | 11.5714 | 36.5 | 3.15 | 65.7 | 5.67 | 45.99 | 0 | 65.61 | 111.6 | 88.92 | 22.68 |  |  | #VALUE! | 314.244 | #VALUE! | #VALUE!
| 28 |  | 12128 | 7571 |  | Level 28 Hotel | Access Scaffold |  | INDEPENDENT | 2.5 | 1.3 | 3 | 1 | 2 |  |  | 5 | m2-LxH | OFF HIRED | 2022-05-30 | 2022-06-12 | 100% |  | 2 | 14 |  | 70 | 0 | 49 | 21 | 0 | 70 | 70 | 0
| 28 |  | 12118 | 7558 |  | Level 28 Hotel | Access Scaffold |  | INDEPENDENT | 2.5 | 1.8 | 4 | 1 | 3 |  |  | 7.5 | m2-LxH | OFF HIRED | 2022-05-29 | 2022-06-08 | 100% |  | 1.5714 | 18 |  | 135 | 0 | 94.5 | 40.5 | 0 | 135 | 135 | 0
| 28 | 309 | 12413 | 7825 |  | Level 28 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-06-20 | 2022-08-16 | 100% |  | 8.2857 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 304.5 | 709.5 | 709.5 | 0
| 28 | 325 | 12431 | 8183 |  | Level 28 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-06-22 | 2022-11-01 | 100% |  | 19 | 135 | 12.25 | 540 | 49 | 378 | 162 | 931 | 1471 | 1471 | 0
| 28 | 324 | 12430 | 7810 |  | Level 28 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-06-22 | 2022-08-06 | 100% |  | 6.5714 | 135 | 12.25 | 540 | 49 | 378 | 162 | 322 | 862 | 862 | 0
| 28 | 129 | 12215 | 7813 |  | Level 28 Hotel | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 5 | 1 | 4 |  |  | 20 | m2-LxH | OFF HIRED | 2022-06-03 | 2022-08-09 | 100% |  | 9.7143 | 14 |  | 280 | 0 | 196 | 84 | 0 | 280 | 280 | 0
| 28 | 130 | 12216 | 7825 |  | Level 28 Hotel | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 5 | 1 | 4 |  |  | 20 | m2-LxH | OFF HIRED | 2022-06-03 | 2022-08-16 | 100% |  | 10.7143 | 14 |  | 280 | 0 | 196 | 84 | 0 | 280 | 280 | 0
| 28 | 191 | 12188 | 7810 |  | Level 28 Hotel | Access Scaffold |  | INDEPENDENT | 6 | 1.3 | 5 | 1 | 4 |  |  | 24 | m2-LxH | OFF HIRED | 2022-06-09 | 2022-08-06 | 100% |  | 8.4286 | 14 | 0.84 | 336 | 20.16 | 235.2 | 100.8 | 169.92 | 505.92 | 505.92 | 0
| 28 | 192 | 12188 | 7810 |  | Level 28 Hotel | Access Scaffold |  | INDEPENDENT | 2.5 | 1.3 | 5 | 1 | 4 |  |  | 10 | m2-LxH | OFF HIRED | 2022-06-09 | 2022-08-06 | 100% |  | 8.4286 | 14 | 0.84 | 140 | 8.4 | 98 | 42 | 70.8 | 210.8 | 210.8 | 0
| 28 | 211 | 12308 | 7739 |  | Level 28 Hotel | Access Scaffold |  | INDEPENDENT | 13 | 1.3 | 5 | 1 | 4 |  |  | 52 | m2-LxH | OFF HIRED | 2022-06-12 | 2022-07-26 | 100% |  | 6.4286 | 14 | 0.84 | 728 | 43.68 | 509.6 | 218.4 | 280.8 | 1008.8 | 1008.8 | 0
| 28 | 211 | 12308 | 7739 |  | Level 28 Hotel | Access Scaffold |  | INDEPENDENT | 10 | 1.3 | 5 | 1 | 4 |  |  | 40 | m2-LxH | OFF HIRED | 2022-06-12 | 2022-07-26 | 100% |  | 6.4286 | 14 | 0.84 | 560 | 33.6 | 392 | 168 | 216 | 776 | 776 | 0
| 28 | 246 | 12361 | 7859 |  | Level 28 Hotel | Access Scaffold |  | INDEPENDENT | 26 | 1.3 | 4.5 | 1 | 3.5 |  |  | 91 | m2-LxH | OFF HIRED | 2022-06-15 | 2022-08-31 | 100% |  | 11.1429 | 14 | 0.84 | 1274 | 76.44 | 891.8 | 382.2 | 851.76 | 2125.76 | 2125.76 | 0
| 28 | 368 | 12517 | 7893 |  | Level 28 Hotel | Access Scaffold |  | INDEPENDENT | 24 | 1.3 | 4 | 1 | 3 |  |  | 72 | m2-LxH | OFF HIRED | 2022-06-27 | 2022-09-16 | 100% |  | 11.7143 | 14 | 0.84 | 1008 | 60.48 | 705.6 | 302.4 | 708.48 | 1716.48 | 1716.48 | 0
| 28 | 344 | 12446 | 7807 |  | Level 28 Hotel | Access Scaffold |  | INDEPENDENT | 26 | 1.3 | 5 | 1 | 4 |  |  | 104 | m2-LxH | OFF HIRED | 2022-06-24 | 2022-08-04 | 100% |  | 6 | 14 | 0.84 | 1456 | 87.36 | 1019.2 | 436.8 | 524.16 | 1980.16 | 1980.16 | 0
| 28 | 128 | 12214 | 7813 |  | Level 28 Hotel | Birdcage Scaffold |  | Birdcage | 5 | 2.5 | 5 | 1 | 4 |  |  | 50 | m3 | OFF HIRED | 2022-06-03 | 2022-08-09 | 100% |  | 9.7143 | 7.5 |  | 375 | 0 | 262.5 | 112.5 | 0 | 375 | 375 | 0
| 28 |  | 12221 | 6705 |  | Level 28 Hotel | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 5 | 1 | 4 |  |  | 40 | m3 | OFF HIRED | 2022-06-03 | 2022-09-21 | 100% |  | 15.8571 | 7.5 |  | 300 | 0 | 210 | 90 | 0 | 300 | 300 | 0
| 28 | 212 | 12309 | 8289 |  | Level 28 Hotel | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 5 | 1 | 4 |  |  | 40 | m3 | OFF HIRED | 2022-06-12 | 2022-11-29 | 100% |  | 24.4286 | 7.5 |  | 300 | 0 | 210 | 90 | 0 | 300 | 300 | 0
| 28 | 263 | 12377 | 7837 |  | Level 28 Hotel | Birdcage Scaffold |  | Birdcage | 9 | 7 | 5 | 1 | 4 |  |  | 252 | m3 | OFF HIRED | 2022-06-17 | 2022-08-23 | 100% |  | 9.7143 | 7.5 | 0.7 | 1890 | 176.4 | 1323 | 567 | 1713.6 | 3603.6 | 3603.6 | 0
| 28 | 310 | 12414 | 7739 |  | Level 28 Hotel | Birdcage Scaffold |  | Birdcage | 6.3 | 2.5 | 5 | 1 | 4 |  |  | 63 | m3 | OFF HIRED | 2022-06-20 | 2022-07-26 | 100% |  | 5.2857 | 7.5 | 0.7 | 472.5 | 44.1 | 330.75 | 141.75 | 233.1 | 705.6 | 705.6 | 0
| 28 | 583 | 12800 | 7816 |  | Level 28 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-07-25 | 2022-08-12 | 100% |  | 2.7143 | 135 |  | 540 | 0 | 378 | 162 | 0 | 540 | 540 | 0
| 28 | 591 | 12809 | 7825 |  | Level 28 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-07-25 | 2022-08-16 | 100% |  | 3.2857 | 135 | 12.25 | 540 | 49 | 378 | 162 | 161 | 701 | 701 | 0
| 28 | 344 | 12608 | 7828 |  | Level 28 Hotel | Access Scaffold |  | INDEPENDENT | 6 | 0.6 | 5 | 1 | 4 |  |  | 24 | m2-LxH | OFF HIRED | 2022-07-06 | 2022-08-16 | 100% |  | 6 | 14 | 0.84 | 336 | 20.16 | 235.2 | 100.8 | 120.96 | 456.96 | 456.96 | 0
| 28 | 450 | 12607 | 7815 |  | Level 28 Hotel | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 5 | 1 | 4 |  |  | 16 | m2-LxH | OFF HIRED | 2022-07-06 | 2022-08-08 | 100% |  | 4.8571 | 14 | 0.84 | 224 | 13.44 | 156.8 | 67.2 | 65.28 | 289.28 | 289.28 | 0
| 28 | 420 | 12581 | 8239 |  | Level 28 Hotel | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 5 | 1 | 4 |  |  | 16 | m2-LxH | OFF HIRED | 2022-07-01 | 2022-11-15 | 100% |  | 19.7143 | 14 | 0.84 | 224 | 13.44 | 156.8 | 67.2 | 264.96 | 488.96 | 488.96 | 0
| 28 | 585 | 12802 | 6737 |  | Level 28 Hotel | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 5 | 1 | 4 |  |  | 20 | m2-LxH | OFF HIRED | 2022-07-25 | 2022-09-26 | 100% |  | 9.1429 | 14 | 0.84 | 280 | 16.8 | 196 | 84 | 153.6 | 433.6 | 433.6 | 0
| 28 | 582 | 12799 | 7810 |  | Level 28 Hotel | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 5 | 1 | 4 |  |  | 16 | m2-LxH | OFF HIRED | 2022-07-25 | 2022-08-06 | 100% |  | 1.8571 | 14 | 0.84 | 224 | 13.44 | 156.8 | 67.2 | 24.96 | 248.96 | 248.96 | 0
| 28 | 511 | 12716 | 7877 |  | Level 28 Hotel | Birdcage Scaffold |  | INDEPENDENT | 1.8 | 1.8 | 3.5 | 1 | 2.5 |  |  | 4.5 | m2-LxH | OFF HIRED | 2022-07-14 | 2022-09-09 | 100% |  | 8.2857 | 18 | 1.05 | 81 | 4.725 | 56.7 | 24.3 | 39.15 | 120.15 | 120.15 | 0
| 28 | 127 | 12609 | 7828 |  | Level 28 Hotel | Boarded Lift |  | Board Lift | 25 | 1.3 |  |  |  | 1 |  | 32.5 | m2-LxW | OFF HIRED | 2022-07-06 | 2022-08-16 | 100% |  | 6 | 7.5 | 1.05 | 243.75 | 34.125 | 170.625 | 73.125 | 204.75 | 448.5 | 448.5 | 0
| 28 | 614 | 12834 | 6737 |  | Level 28 Hotel | Access Scaffold |  | Tower | 1.3 | 1 | 6 | 1 | 5 |  |  | 5 | rm | OFF HIRED | 2022-07-27 | 2022-09-26 | 100% |  | 8.8571 | 135 |  | 675 | 0 | 472.5 | 202.5 | 0 | 675 | 675 | 0
| 28 | 613 | 12833 | 7852 |  | Level 28 Hotel | Access Scaffold |  | Tower | 2.5 | 1.8 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-07-28 | 2022-08-29 | 100% |  | 4.7143 | 135 | 12.25 | 540 | 49 | 378 | 162 | 231 | 771 | 771 | 0
| 28 | 642 | 12865 | 8220 |  | Level 28 Hotel | Access Scaffold |  | Tower | 1.3 | 1.3 | 7 | 1 | 6 |  |  | 6 | rm | OFF HIRED | 2022-08-02 | 2022-11-10 | 100% |  | 14.4286 | 135 | 12.25 | 810 | 73.5 | 567 | 243 | 1060.5 | 1870.5 | 1870.5 | 0
| 28 | 743 | 13001 | 7825 |  | Level 28 Hotel | Access Scaffold |  | Tower | 2.5 | 1.3 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-08-16 | 2022-08-16 | 100% |  | 0.14286 | 135 | 12.25 | 540 | 49 | 378 | 162 | 7 | 547 | 547 | 0
| 28 | 743 | 13001 | 7825 |  | Level 28 Hotel | Access Scaffold |  | Tower | 2.5 | 1.3 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-08-16 | 2022-08-16 | 100% |  | 0.14286 | 135 | 12.25 | 540 | 49 | 378 | 162 | 7 | 547 | 547 | 0
| 28 | 799 | 13059 | 7892 |  | Level 28 Hotel | Access Scaffold |  | Tower | 1.8 | 1.3 | 6 |  | 6 |  |  | 6 | rm | OFF HIRED | 2022-08-23 | 2022-09-16 | 100% |  | 3.5714 | 135 | 12.25 | 810 | 73.5 | 567 | 243 | 262.5 | 1072.5 | 1072.5 | 0
| 28 | 783 | 13043 |  |  | Level 28 Hotel | Access Scaffold |  | Tower | 2.5 | 1.3 | 4 |  | 4 |  |  | 4 | rm | ON HIRE | 2022-08-20 |  | 100% |  | 27.5714 | 135 | 12.25 | 540 | 49 | 378 | 0 | 1351 | 1729 | 1533 | 196 |  |  | #VALUE! | 534.8 | #VALUE! | #VALUE!
| 28 | 628 | 12850 | 7828 |  | Level 28 Hotel | Access Scaffold |  | Independent | 8 | 1.3 | 5 | 1 | 4 |  |  | 32 | m2-LxH | OFF HIRED | 2022-07-29 | 2022-08-16 | 100% |  | 2.7143 | 14 | 0 | 448 | 0 | 313.6 | 134.4 | 0 | 448 | 448 | 0
| 28 | 790 | 13050 | 7851 |  | Level 28 Hotel | Access Scaffold |  | Independent | 5 | 1.3 | 4 |  | 4 |  |  | 20 | m2-LxH | OFF HIRED | 2022-08-22 | 2022-08-29 | 100% |  | 1.1429 | 14 | 0 | 280 | 0 | 196 | 84 | 0 | 280 | 280 | 0
| 28 | 610 | 12829 | 7747 |  | Level 28 Hotel | Access Scaffold |  | Independent | 5 | 1.3 | 5 | 1 | 4 |  |  | 20 | m2-LxH | OFF HIRED | 2022-07-27 | 2022-07-31 | 100% |  | 0.71429 | 14 | 0.84 | 280 | 16.8 | 196 | 84 | 12 | 292 | 292 | 0
| 28 | 602 | 12824 | 7886 |  | Level 28 Hotel | Access Scaffold |  | Independent | 13 | 1.3 | 4 | 1 | 3 |  |  | 39 | m2-LxH | OFF HIRED | 2022-07-27 | 2022-09-13 | 100% |  | 7 | 14 | 0.84 | 546 | 32.76 | 382.2 | 163.8 | 229.32 | 775.32 | 775.32 | 0
| 28 | 643 | 12866 | 7825 |  | Level 28 Hotel | Access Scaffold |  | Independent | 17.5 | 1.3 | 4 | 1 | 3 |  |  | 52.5 | m2-LxH | OFF HIRED | 2022-08-02 | 2022-08-16 | 100% |  | 2.1429 | 14 | 0.84 | 735 | 44.1 | 514.5 | 220.5 | 94.5 | 829.5 | 829.5 | 0
| 28 | 685 | 12956 | 6738 |  | Level 28 Hotel | Access Scaffold |  | Independent | 35 | 1.3 | 4.5 | 1 | 3.5 |  |  | 122.5 | m2-LxH | OFF HIRED | 2022-08-08 | 2022-09-27 | 100% |  | 7.2857 | 14 | 0.84 | 1715 | 102.9 | 1200.5 | 514.5 | 749.7 | 2464.7 | 2464.7 | 0
| 28 | 783 | 13043 | 7851 |  | Level 28 Hotel | Access Scaffold |  | Independent | 4 | 1.3 | 4 |  | 4 |  |  | 16 | m2-LxH | OFF HIRED | 2022-08-20 | 2022-08-29 | 100% |  | 1.4286 | 14 | 0.84 | 224 | 13.44 | 156.8 | 67.2 | 19.2 | 243.2 | 243.2 | 0
| 28 | 784 | 13045 | 7851 |  | Level 28 Hotel | Access Scaffold |  | Independent | 4 | 1.3 | 4 |  | 4 |  |  | 16 | m2-LxH | OFF HIRED | 2022-08-20 | 2022-08-29 | 100% |  | 1.4286 | 14 | 0.84 | 224 | 13.44 | 156.8 | 67.2 | 19.2 | 243.2 | 243.2 | 0
| 28 | 801 | 13061 | 7872 |  | Level 28 Hotel | Access Scaffold |  | Independent | 4 | 1.3 | 2.5 |  | 2.5 |  |  | 10 | m2-LxH | OFF HIRED | 2022-08-23 | 2022-09-05 | 100% |  | 2 | 14 | 0.84 | 140 | 8.4 | 98 | 42 | 16.8 | 156.8 | 156.8 | 0
| 28 | 835 | 13104 | 7866 |  | Level 28 Hotel | Access Scaffold |  | Independent | 8 | 1.3 | 3.5 |  | 3.5 |  |  | 28 | m2-LxH | OFF HIRED | 2022-08-26 | 2022-09-03 | 100% |  | 1.2857 | 14 | 0.84 | 392 | 23.52 | 274.4 | 117.6 | 30.24 | 422.24 | 422.24 | 0
| 28 | 849 | 13121 | 7872 |  | Level 28 Hotel | Birdcage Scaffold |  | Birdcage | 4 | 4 | 4 |  | 4 |  |  | 64 | m3 | OFF HIRED | 2022-08-29 | 2022-09-05 | 100% |  | 1.1429 | 7.5 | 0.7 | 480 | 44.8 | 336 | 144 | 51.2 | 531.2 | 531.2 | 0
| 28 | 348 | 12503 | 7744 |  | Level 28 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-06-24 | 2022-07-29 | 100% |  | 5.1429 | 135 |  | 405 | 0 | 283.5 | 121.5 | 0 | 405 | 405 | 0
| 28 | 339 | 12441 | 7744 |  | Level 28 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-06-23 | 2022-07-29 | 100% |  | 5.2857 | 135 |  | 405 | 0 | 283.5 | 121.5 | 0 | 405 | 405 | 0
| 28 | 340 | 12442 | 7712 |  | Level 28 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-06-23 | 2022-07-14 | 100% |  | 3.1429 | 135 |  | 405 | 0 | 283.5 | 121.5 | 0 | 405 | 405 | 0
| 28 | 370 | 12527 | 7803 |  | Level 28 Residence | Access Scaffold |  | INDEPENDENT | 7.5 | 1.3 | 4 | 1 | 3 |  |  | 22.5 | m2-LxH | OFF HIRED | 2022-06-27 | 2022-08-03 | 100% |  | 5.4286 | 14 | 0.84 | 315 | 18.9 | 220.5 | 94.5 | 102.6 | 417.6 | 417.6 | 0
| 28 | 379 | 12551 | 7897 |  | Level 28 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-06-28 | 2022-09-16 | 100% |  | 11.5714 | 135 |  | 405 | 0 | 283.5 | 121.5 | 0 | 405 | 405 | 0
| 28 | 549 | 12758 | 7804 |  | Level 28 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-07-19 | 2022-08-03 | 100% |  | 2.2857 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 84 | 489 | 489 | 0
| 28 | 436 | 12595 | 7822 |  | Level 28 Residance | Access Scaffold |  | INDEPENDENT | 12 | 1 | 4 | 1 | 3 |  |  | 36 | m2-LxH | OFF HIRED | 2022-07-04 | 2022-08-08 | 100% |  | 5.1429 | 14 | 0.84 | 504 | 30.24 | 352.8 | 151.2 | 155.52 | 659.52 | 659.52 | 0
| 28 | 434 | 12594 | 8281 |  | Level 28 Residance | Access Scaffold |  | INDEPENDENT | 12.5 | 1.3 | 3 | 1 | 2 |  |  | 25 | m2-LxH | OFF HIRED | 2022-07-04 | 2022-11-27 | 100% |  | 21 | 14 | 0.84 | 350 | 21 | 245 | 105 | 441 | 791 | 791 | 0
| 28 | 692 | 12957 | 7838 |  | Level 28 Residence | Access Scaffold |  | Tower | 2.5 | 1.8 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-08 | 2022-08-23 | 100% |  | 2.2857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 56 | 326 | 326 | 0
| 28 | 812 | 13075 | 6735 |  | Level 28 Residence | Access Scaffold |  | Tower | 2.5 | 1.8 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-08-24 | 2022-09-28 | 100% |  | 5.1429 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 189 | 594 | 594 | 0
| 28 | 785 | 13044 | 7869 |  | Level 28 Residence | Cantiliver |  | Cantiliver | 3 | 1.2 |  |  |  | 1 |  | 3.6 | m2-LxW | OFF HIRED | 2022-08-20 | 2022-09-03 | 100% |  | 2.1429 | 36.5 | 3.15 | 131.4 | 11.34 | 91.98 | 39.42 | 24.3 | 155.7 | 155.7 | 0
| 28 | 892 | 13263 | 7874 |  | Level 28 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-09-05 | 2022-09-06 | 100% |  | 0.28571 | 135 | 12.25 | 405 | 36.75 | 283.5 | 0 | 10.5 | 294 | 294 | 0
| 28 | 664 | 12887 | 7813 |  | Level 28 Hotel | Access Scaffold |  | Tower | 2.5 | 1.3 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-08-05 | 2022-08-09 | 100% |  | 0.71429 | 135 | 12.25 | 540 | 49 | 378 | 162 | 35 | 575 | 575 | 0
| 28 | 650 | 12873 | 7816 |  | Level 28 Hotel | Access Scaffold |  | Independent | 5 | 1.3 | 5 | 1 | 4 |  |  | 20 | m2-LxH | OFF HIRED | 2022-08-03 | 2022-08-12 | 100% |  | 1.4286 | 14 | 0.84 | 280 | 16.8 | 196 | 84 | 24 | 304 | 304 | 0
| 28 | 785 | 13044 | 7869 |  | Level 28 Residence | Access Scaffold |  | Independent | 2.6 | 1.3 | 4 |  | 4 |  |  | 10.4 | m2-LxH | OFF HIRED | 2022-08-20 | 2022-09-03 | 100% |  | 2.1429 | 14 | 0.84 | 145.6 | 8.736 | 101.92 | 43.68 | 18.72 | 164.32 | 164.32 | 0
| 28 | 818 | 13081 |  |  | Level 28 Hotel | Access Scaffold |  | Independent | 35 | 1.3 | 3.5 |  | 3.5 |  |  | 122.5 | m2-LxH | ON HIRE | 2022-08-25 |  | 100% |  | 26.8571 | 14 | 0.84 | 1715 | 102.9 | 1200.5 | 0 | 2763.6 | 3964.1 | 3552.5 | 411.6 |  |  | #VALUE! | 1200.5 | #VALUE! | #VALUE!
| 28 | 1016 | 13451 | 8208 |  | Level 28 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-09-20 | 2022-11-07 | 100% |  | 7 | 135 | 12.25 | 540 | 49 | 378 | 162 | 343 | 883 | 883 | 0
| 28 | 1019 | 13454 | 8074 |  | Level 28 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-22 | 2022-10-05 | 100% |  | 2 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 49 | 319 | 319 | 0
| 28 | 1035 | 13472 |  |  | Level 28 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 |  | 4 |  |  | 4 | rm | ON HIRE | 2022-09-23 |  | 100% |  | 22.7143 | 135 | 12.25 | 540 | 49 | 378 | 0 | 1113 | 434 | 434 | 0
| 28 | 1036 | 13473 | 8084 |  | Level 28 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-09-23 | 2022-10-07 | 100% |  | 2.1429 | 135 | 12.25 | 540 | 49 | 378 | 162 | 105 | 645 | 645 | 0
| 28 | 1049 | 13488 | 8052 |  | Level 28 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-26 | 2022-10-01 | 100% |  | 0.85714 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 21 | 291 | 291 | 0
| 28 | 994 | 13378 | 8208 |  | Level 28 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4.5 |  | 4.5 |  |  | 4.5 | rm | OFF HIRED | 2022-09-19 | 2022-11-07 | 100% |  | 7.1429 | 135 | 12.25 | 607.5 | 55.125 | 425.25 | 182.25 | 393.75 | 1001.25 | 1001.25 | 0
| 28 | 999 | 13383 | 6703 |  | Level 28 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-09-20 | 2022-09-23 | 100% |  | 0.57143 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 21 | 426 | 426 | 0
| 28 | 986 | 13366 | 8176 |  | Level 28 Hotel | Access Scaffold |  | Independent | 4 | 1.3 | 4 |  | 4 |  |  | 16 | m2-LxH | OFF HIRED | 2022-09-17 | 2022-10-31 | 100% |  | 6.4286 | 14 |  | 224 | 0 | 156.8 | 67.2 | 0 | 224 | 224 | 0
| 28 | 827 | 13095 | 8007 |  | Level 28 Hotel | Access Scaffold |  | Independent | 17.5 | 1.3 | 4 |  | 4 |  |  | 70 | m2-LxH | OFF HIRED | 2022-09-08 | 2022-10-06 | 100% |  | 4.1429 | 14 | 0.84 | 980 | 58.8 | 686 | 294 | 243.6 | [5 empty] | #VALUE! | 869.75 | #VALUE! | #VALUE!
| 28 | 1048 | 13487 | 6743 |  | Level 28 Hotel | Access Scaffold |  | Independent | 10 | 1.3 | 3 |  | 3 |  |  | 30 | m2-LxH | OFF HIRED | 2022-09-26 | 2022-09-29 | 100% |  | 0.57143 | 14 | 0.84 | 420 | 25.2 | 294 | 126 | 14.4 | 434.4 | 434.4 | 0
| 28 | 992 A | 13376 | 6705 |  | Level 28 Hotel | Access Scaffold |  | Independent | 5 | 1 | 3.5 |  | 3.5 |  |  | 17.5 | m2-LxH | OFF HIRED | 2022-09-19 | 2022-09-21 | 100% |  | 0.42857 | 14 | 0.84 | 245 | 14.7 | 171.5 | 73.5 | 6.3 | 251.3 | 251.3 | 0
| 28 | 1001 | 13385 | 8086 |  | Level 28 Residence | Access Scaffold |  | Independent | 8 | 1 | 3 |  | 3 |  |  | 24 | m2-LxH | OFF HIRED | 2022-09-20 | 2022-10-07 | 100% |  | 2.5714 | 14 | 0.84 | 336 | 20.16 | 235.2 | 100.8 | 51.84 | 387.84 | 387.84 | 0
| 28 | 981 | 13359 | 8101 |  | Level 28 Hotel | Access Scaffold |  | Independent | 5 | 1.3 | 4 |  | 4 |  |  | 20 | m2-LxH | OFF HIRED | 2022-09-16 | 2022-10-13 | 100% |  | 4 | 14 | 0.84 | 280 | 16.8 | 196 | 84 | 67.2 | 347.2 | 347.2 | 0
| 28 | 986 | 13366 | 8176 |  | Level 28 Hotel | Access Scaffold |  | Independent | 4 | 1.8 | 4 |  | 4 |  |  | 16 | m2-LxH | OFF HIRED | 2022-09-17 | 2022-10-31 | 100% |  | 6.4286 | 18 |  | 288 | 0 | 201.6 | 86.4 | 0 | 288 | 288 | 0
| 28 | 1009 | 13393 | 8091 |  | Level 28 Hotel | Birdcage Scaffold |  | Birdcage | 24 | 2.5 | 3 |  | 3 |  |  | 180 | m3 | OFF HIRED | 2022-09-21 | 2022-10-10 | 100% |  | 2.8571 | 7.5 | 0.7 | 1350 | 126 | 945 | 405 | 360 | 1710 | 1710 | 0
| 28 | 909 | 13283 | 7886 |  | Level 28 Hotel | Cantiliver |  | Cantiliver | 10 | 1 |  |  |  | 1 |  | 10 | m2-LxW | OFF HIRED | 2022-09-08 | 2022-09-13 | 100% |  | 0.85714 | 36.5 | 3.15 | 365 | 31.5 | 255.5 | 109.5 | 27 | 392 | 392 | 0
| 28 | 909 | 13283 | 7866 |  | Level 28 Hotel | Cantiliver |  | Cantiliver | 10 | 1 |  |  |  | 1 |  | 10 | m2-LxW | OFF HIRED | 2022-09-08 | 2022-09-13 | 100% |  | 0.85714 | 36.5 | 3.15 | 365 | 31.5 | 255.5 | 109.5 | 27 | 392 | 392 | 0
| 28 | 1123 | 13607 | 8095 |  | Level 28 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-10-04 | 2022-10-11 | 100% |  | 1.1429 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 28 | 298 | 298 | 0
| 28 | 1203 | 13689 | 8108 |  | Level 28 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-10-13 | 2022-10-15 | 100% |  | 0.42857 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 15.75 | 420.75 | 420.75 | 0
| 28 | 1209 | 13695 | 8593 |  | Level 23 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-10-14 | 2023-02-21 | 100% |  | 18.7143 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 687.75 | 1092.75 | 861 | 231.75 |  |  | #VALUE! | 283.5 | #VALUE! | #VALUE!
| 28 | 1249 | 13787 | 8187 |  | Level 28 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-10-19 | 2022-11-03 | 100% |  | 2.2857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 56 | 326 | 326 | 0
| 28 | 1197 | 13683 | 8114 |  | Level 28 Hotel | Access Scaffold |  | Independent | 7 | 1 | 3.5 |  | 3.5 |  |  | 24.5 | m2-LxH | OFF HIRED | 2022-10-13 | 2022-10-17 | 100% |  | 0.71429 | 14 | 0.84 | 343 | 20.58 | 240.1 | 102.9 | 14.7 | 357.7 | 357.7 | 0
| 28 | 1151 | 13635 | 8297 |  | Level 28 Hotel | Access Scaffold |  | Independent | 5 | 0.6 | 3 |  | 3 |  |  | 15 | m2-LxH | OFF HIRED | 2022-10-07 | 2022-11-30 | 100% |  | 7.8571 | 14 | 0.84 | 210 | 12.6 | 147 | 63 | 99 | 309 | 309 | 0
| 28 | 1093 | 13526 | 8551 |  | Level 28 Hotel | Access Scaffold |  | Independent | 15 | 1.3 | 4 |  | 4 |  |  | 60 | m2-LxH | OFF HIRED | 2022-09-30 | 2023-02-09 | 100% |  | 19 | 14 | 0.84 | 840 | 50.4 | 588 | 252 | 957.6 | 1797.6 | 1480.8 | 316.8 |  |  | #VALUE! | 588 | #VALUE! | #VALUE!
| 28 | 1092 | 13525 | 8594 |  | Level 28 Hotel | Access Scaffold |  | Independent | 17.5 | 1.3 | 4 |  | 4 |  |  | 70 | m2-LxH | OFF HIRED | 2022-09-30 | 2023-02-21 | 100% |  | 20.7143 | 14 | 0.84 | 980 | 58.8 | 686 | 294 | 1218 | 2198 | 1727.6 | 470.4 |  |  | #VALUE! | 686 | #VALUE! | #VALUE!
| 28 | 1235 | 13773 |  |  | Level 28 Hotel | Access Scaffold |  | Independent | 25 | 1.3 | 4 |  | 4 |  |  | 100 | m2-LxH | ON HIRE | 2022-10-17 |  | 100% |  | 19.2857 | 14 | 0.84 | 1400 | 84 | 980 | 0 | 1620 | 2600 | 2264 | 336 |  |  | #VALUE! | 980 | #VALUE! | #VALUE!
| 28 | 1285 | 13724 | 8179 |  | Level 28 Hotel | Access Scaffold |  | Independent | 3.9 | 1.3 | 4 |  | 4 |  |  | 15.6 | m2-LxH | OFF HIRED | 2022-10-24 | 2022-11-01 | 100% |  | 1.2857 | 14 | 0.84 | 218.4 | 13.104 | 152.88 | 65.52 | 16.848 | 235.248 | 235.248 | 0
| 28 | 1191 | 13676 | 8332 |  | Level 28 Hotel | Access Scaffold |  | Independent | 4 | 1.8 | 1.5 |  | 1.5 |  |  | 6 | m2-LxH | OFF HIRED | 2022-10-18 | 2022-12-15 | 100% |  | 8.4286 | 18 | 1.05 | 108 | 6.3 | 75.6 | 32.4 | 53.1 | 161.1 | 161.1 | 0
| 28 | 1242 | 13780 | 8127 |  | Level 28 Hotel | Access Scaffold |  | Independent | 1.8 | 1.8 | 4 |  | 4 |  |  | 7.2 | m2-LxH | OFF HIRED | 2022-10-18 | 2022-10-19 | 100% |  | 0.28571 | 18 | 1.05 | 129.6 | 7.56 | 90.72 | 38.88 | 2.16 | 131.76 | 131.76 | 0
| 28 | 1213 | 13699 | 8276 |  | Level 28 Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 3.5 |  | 3.5 |  |  | 21.875 | m3 | OFF HIRED | 2022-10-15 | 2022-11-26 | 100% |  | 6.1429 | 7.5 | 0.7 | 164.0625 | 15.3125 | 114.8437 | 49.2188 | 94.0625 | 258.125 | 258.125 | 0
| 28 | 1064 | 13501 | 8091 |  | Level 28 Hotel | Birdcage Scaffold |  | Birdcage | 7.5 | 2.5 | 4 |  | 4 |  |  | 75 | m3 | OFF HIRED | 2022-09-26 | 2022-10-10 | 100% |  | 2.1429 | 7.5 | 0.7 | 562.5 | 52.5 | 393.75 | 168.75 | 112.5 | 675 | 675 | 0
| 28 | 1139 | 13623 | 8202 |  | Level 28 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.8 | 2.5 |  | 2.5 |  |  | 17.5 | m3 | OFF HIRED | 2022-10-05 | 2022-11-05 | 100% |  | 4.5714 | 7.5 | 0.7 | 131.25 | 12.25 | 91.875 | 39.375 | 56 | 187.25 | 187.25 | 0
| 28 | 1121 | 13605 | 8609 |  | Level 28 Hotel | Boarded Lift |  | Board Lift | 4 | 2 |  |  |  | 1 |  | 8 | m2-LxW | OFF HIRED | 2022-10-04 | 2023-01-26 | 100% |  | 16.4286 | 7.5 | 1.05 | 60 | 8.4 | 42 | 18 | 138 | 198 | 198 | 0
| 28 | 1121 | 13605 | 8609 |  | Level 28 Hotel | Boarded Lift |  | Board Lift | 4 | 2 |  |  |  | 1 |  | 8 | m2-LxW | OFF HIRED | 2022-10-04 | 2023-01-26 | 100% |  | 16.4286 | 7.5 | 1.05 | 60 | 8.4 | 42 | 18 | 138 | 198 | 198 | 0
| 28 | 1121 | 13605 | 8609 |  | Level 28 Hotel | Boarded Lift |  | Board Lift | 4 | 2 |  |  |  | 1 |  | 8 | m2-LxW | OFF HIRED | 2022-10-04 | 2023-01-26 | 100% |  | 16.4286 | 7.5 | 1.05 | 60 | 8.4 | 42 | 18 | 138 | 198 | 198 | 0
| 28 | 1395 | 13883 | 8445 |  | Level 28 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-11-08 | 2023-01-20 | 100% |  | 10.5714 | 135 |  | 540 | 0 | 378 | 162 | 0 | 540 | 540 | 0
| 28 | 1354 | 13842 | 8325 |  | Level 28 Hotel | Access Scaffold |  | INDEPENDENT | 3 | 1 | 3 |  | 3 |  |  | 9 | m2-LxH | OFF HIRED | 2022-11-03 | 2022-12-13 | 100% |  | 5.8571 | 14 | 0.84 | 126 | 7.56 | 88.2 | 37.8 | 44.28 | 170.28 | 170.28 | 0
| 28 | 1438 | 13926 | 8318 |  | Level 28 Hotel | Access Scaffold |  | INDEPENDENT | 12.5 | 1.3 | 3.5 |  | 3.5 |  |  | 43.75 | m2-LxH | OFF HIRED | 2022-11-15 | 2022-12-09 | 100% |  | 3.5714 | 14 | 0.84 | 612.5 | 36.75 | 428.75 | 183.75 | 131.25 | 743.75 | 743.75 | 0
| 28 | 1446 | 13934 | 8262 |  | Level 28 Hotel | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 3.5 |  | 3.5 |  |  | 17.5 | m2-LxH | OFF HIRED | 2022-11-17 | 2022-11-22 | 100% |  | 0.85714 | 14 | 0.84 | 245 | 14.7 | 171.5 | 73.5 | 12.6 | 257.6 | 257.6 | 0
| 28 | 1408 | 13896 | 8492 |  | Level 28 Residence | Cantiliver |  | Cantiliver | 2.5 | 0.6 |  |  |  | 1 |  | 1.5 | m2-LxW | OFF HIRED | 2022-11-10 | 2023-01-05 | 100% |  | 8.1429 | 36.5 | 3.15 | 54.75 | 4.725 | 38.325 | 16.425 | 38.475 | 93.225 | 93.225 | 0
| 28 | 1596 | 14131 | 8551 |  | Level 28 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-12-14 | 2023-02-09 | 100% |  | 8.2857 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 253.75 | 591.25 | 450.625 | 140.625 |  |  | #VALUE! | 236.25 | #VALUE! | #VALUE!
| 28 | 1599 | 14134 | 8551 |  | Level 28 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 2.5 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-12-15 | 2023-02-09 | 100% |  | 8.1429 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 199.5 | 469.5 | 357 | 112.5 |  |  | #VALUE! | 189 | #VALUE! | #VALUE!
| 28 | 1612 | 14147 | 8631 |  | Level 28 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-12-16 | 2023-02-03 | 100% |  | 7.1429 | 135 | 12.25 | 540 | 49 | 378 | 162 | 350 | 890 | 707 | 183 |  |  | #VALUE! | 378 | #VALUE! | #VALUE!
| 28 | 1672 | 14257 | 8631 |  | Level 28 Hotel | HEAVY DUTY TOWER |  | Tower | 4 | 1.3 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-12-27 | 2023-02-03 | 100% |  | 5.5714 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 204.75 | 609.75 | 472.5 | 137.25 |  |  | #VALUE! | 577.6312 | #VALUE! | #VALUE!
| 28 | 1555 | 14087 | 8573 |  | Level 28 Hotel | Access Scaffold |  | INDEPENDENT | 4.3 | 1.3 | 2 |  | 2 |  |  | 8.6 | m2-LxH | OFF HIRED | 2022-12-08 | 2023-02-17 | 100% |  | 10.2857 | 14 | 0.84 | 120.4 | 7.224 | 84.28 | 36.12 | 74.304 | 194.704 | 141.04 | 53.664 |  |  | #VALUE! | 887.67 | #VALUE! | #VALUE!
| 28 | 1555 | 14087 | 8573 |  | Level 28 Hotel | Access Scaffold |  | INDEPENDENT | 7 | 0.6 | 4 |  | 4 |  |  | 28 | m2-LxH | OFF HIRED | 2022-12-08 | 2023-02-17 | 100% |  | 10.2857 | 14 | 0.84 | 392 | 23.52 | 274.4 | 117.6 | 241.92 | 633.92 | 459.2 | 174.72 |  |  | #VALUE! | 887.67 | #VALUE! | #VALUE!
| 28 | 1672 | 14257 |  |  | Level 28 Hotel | Access Scaffold |  | Independent | 5.5 | 1.8 | 3 |  | 3 |  |  | 16.5 | m2-LxH | ON HIRE | 2022-12-27 |  | 100% |  | 9.1429 | 18 | 1.05 | 297 | 17.325 | 207.9 | 0 | 158.4 | 366.3 | 297 | 69.3 |  |  | #VALUE! | 577.6312 | #VALUE! | #VALUE!
| 28 | 1555 | 14087 | 8573 |  | Level 28 Hotel | Birdcage Scaffold |  | Birdcage | 9.2 | 2.5 | 4 |  | 4 |  |  | 92 | m3 | OFF HIRED | 2022-12-08 | 2023-02-17 | 100% |  | 10.2857 | 7.5 | 0.7 | 690 | 64.4 | 483 | 207 | 662.4 | 1352.4 | 989 | 363.4 |  |  | #VALUE! | 887.67 | #VALUE! | #VALUE!
| 28 | 1574 | 14107 |  |  | Level 28 Hotel | Birdcage Scaffold |  | Birdcage | 3.5 | 3.5 | 3 |  | 3 |  |  | 36.75 | m3 | ON HIRE | 2022-12-10 |  | 100% |  | 11.5714 | 7.5 | 0.7 | 275.625 | 25.725 | 192.9375 | 0 | 297.675 | 490.6125 | 387.7125 | 102.9 |  |  | #VALUE! | 192.9375 | #VALUE! | #VALUE!
| 28 | 1672 | 14257 |  |  | Level 28 Hotel | Cantiliver |  | Cantiliver | 1.5 | 1.5 |  |  |  | 1.5 |  | 3.375 | m2-LxW | ON HIRE | 2022-12-27 |  | 100% |  | 9.1429 | 36.5 | 3.15 | 123.1875 | 10.6312 | 86.2312 | 0 | 97.2 | 183.4312 | 140.9062 | 42.525 |  |  | #VALUE! | 577.6312 | #VALUE! | #VALUE!
| 29 | 323 | 12422 | 7591 |  | Level 29 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-06-21 | 2022-06-29 | 100% |  | 1.2857 | 135 | 12.25 | 540 | 49 | 378 | 162 | 63 | 603 | 603 | 0
| 29 | 349 | 12504 | 7591 |  | Level 29 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-06-24 | 2022-06-29 | 100% |  | 0.85714 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 31.5 | 436.5 | 436.5 | 0
| 29 | 341 | 12443 | 7592 |  | Level 29 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-06-24 | 2022-06-29 | 100% |  | 0.85714 | 135 | 12.25 | 540 | 49 | 378 | 162 | 42 | 582 | 582 | 0
| 29 | 136 | 12212 | 6705 |  | Level 29 Hotel | Access Scaffold |  | INDEPENDENT | 15 | 1.3 | 5 | 1 | 4 |  |  | 60 | m2-LxH | OFF HIRED | 2022-06-03 | 2022-09-21 | 100% |  | 15.8571 | 14 |  | 840 | 0 | 588 | 252 | 0 | 840 | 840 | 0
| 29 | 127 | 12213 | 7810 |  | Level 29 Hotel | Access Scaffold |  | INDEPENDENT | 25 | 1.3 | 4.5 | 1 | 3.5 |  |  | 87.5 | m2-LxH | OFF HIRED | 2022-06-03 | 2022-08-06 | 100% |  | 9.2857 | 14 |  | 1225 | 0 | 857.5 | 367.5 | 0 | 1225 | 1225 | 0
| 29 | 135 | 12146 | 6737 |  | Level 29 Hotel | Access Scaffold |  | INDEPENDENT | 17 | 1.3 | 9 | 1 | 8 |  |  | 136 | m2-LxH | OFF HIRED | 2022-06-01 | 2022-09-26 | 100% |  | 16.8571 | 14 | 0.84 | 1904 | 114.24 | 1332.8 | 571.2 | 1925.76 | 3829.76 | 3829.76 | 0
| 29 | 308 | 12412 | 7592 |  | Level 29 Hotel | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 4 | 1 | 3 |  |  | 12 | m2-LxH | OFF HIRED | 2022-06-20 | 2022-06-29 | 100% |  | 1.4286 | 14 | 0.84 | 168 | 10.08 | 117.6 | 50.4 | 14.4 | 182.4 | 182.4 | 0
| 29 | 314 | 12415 | 7581 |  | Level 29 Hotel | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 4 | 1 | 3 |  |  | 12 | m2-LxH | OFF HIRED | 2022-06-20 | 2022-06-23 | 100% |  | 0.57143 | 14 | 0.84 | 168 | 10.08 | 117.6 | 50.4 | 5.76 | 173.76 | 173.76 | 0
| 29 | 374 | 12531 | 7730 |  | Level 29 Hotel | Access Scaffold |  | INDEPENDENT | 6 | 4 | 3.5 | 1 | 2.5 |  |  | 15 | m2-LxH | OFF HIRED | 2022-06-28 | 2022-07-19 | 100% |  | 3.1429 | 14 | 0.84 | 210 | 12.6 | 147 | 63 | 39.6 | 249.6 | 249.6 | 0
| 29 | 393 | 12550 | 7730 |  | Level 29 Hotel | Access Scaffold |  | INDEPENDENT | 8 | 1.3 | 6 | 1 | 5 |  |  | 40 | m2-LxH | OFF HIRED | 2022-06-29 | 2022-07-19 | 100% |  | 3 | 14 | 0.84 | 560 | 33.6 | 392 | 168 | 100.8 | 660.8 | 660.8 | 0
| 29 | 135 | 12146 | 6737 |  | Level 29 Hotel | BUTTRESS |  | Birdcage | 2.5 | 2.5 | 5 | 1 | 4 |  |  | 25 | m3 | OFF HIRED | 2022-06-01 | 2022-09-26 | 100% |  | 16.8571 | 5.25 | 0.35 | 131.25 | 8.75 | 91.875 | 39.375 | 147.5 | 278.75 | 278.75 | 0
| 29 | 135 | 12146 | 6737 |  | Level 29 Hotel | BUTTRESS |  | Birdcage | 2.5 | 2.5 | 5 | 1 | 4 |  |  | 25 | m3 | OFF HIRED | 2022-06-01 | 2022-09-26 | 100% |  | 16.8571 | 5.25 | 0.35 | 131.25 | 8.75 | 91.875 | 39.375 | 147.5 | 278.75 | 278.75 | 0
| 29 | 537 | 12747 | 7807 |  | Level 29 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-17 | 2022-08-04 | 100% |  | 2.7143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 66.5 | 336.5 | 336.5 | 0
| 29 | 476 | 12637 | 8127 |  | Level 29 Hotel | Access Scaffold |  | INDEPENDENT | 12 | 1.3 | 3.5 | 1 | 2.5 |  |  | 30 | m2-LxH | OFF HIRED | 2022-07-07 | 2022-10-19 | 100% |  | 15 | 14 |  | 420 | 0 | 294 | 126 | 0 | 420 | 420 | 0
| 29 | 414 | 12573 | 7739 |  | Level 29 Hotel | Access Scaffold |  | INDEPENDENT | 4.5 | 1.3 | 3.5 | 1 | 2.5 |  |  | 11.25 | m2-LxH | OFF HIRED | 2022-07-01 | 2022-07-26 | 100% |  | 3.7143 | 14 | 0.84 | 157.5 | 9.45 | 110.25 | 47.25 | 35.1 | 192.6 | 192.6 | 0
| 29 | a136 | 12650 | 6705 |  | Level 29 Hotel Glass Work | Access Scaffold |  | INDEPENDENT | 15 | 1.3 | 5 | 1 | 4 |  |  | 60 | m2-LxH | OFF HIRED | 2022-07-07 | 2022-09-21 | 100% |  | 11 | 14 | 0.84 | 840 | 50.4 | 588 | 252 | 554.4 | 1394.4 | 1394.4 | 0
| 29 | 528 | 12736 | 7837 |  | Level 29 Hotel | Birdcage Scaffold |  | Birdcage | 18 | 6 | 3.5 | 1 | 2.5 |  |  | 270 | m3 | OFF HIRED | 2022-07-15 | 2022-08-23 | 100% |  | 5.7143 | 7.5 | 0.7 | 2025 | 189 | 1417.5 | 607.5 | 1080 | 3105 | 3105 | 0
| 29 | 619 | 12841 | 7893 |  | Level 29 Hotel | Access Scaffold |  | Tower | 1.8 | 1.8 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-27 | 2022-09-16 | 100% |  | 7.4286 | 135 |  | 270 | 0 | 189 | 81 | 0 | 270 | 270 | 0
| 29 | 626 | 12848 | 7982 |  | Level 29 Hotel | Access Scaffold |  | Tower | 2.5 | 1.3 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-07-29 | 2022-09-16 | 100% |  | 7.1429 | 135 |  | 540 | 0 | 378 | 162 | 0 | 540 | 540 | 0
| 29 | 809 | 13072 | 7866 |  | Level 29 Hotel | Access Scaffold |  | Tower | 2.5 | 2.5 | 2.5 | 1 | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2022-08-17 | 2022-09-03 | 100% |  | 2.5714 | 135 |  | 202.5 | 0 | 141.75 | 60.75 | 0 | 202.5 | 202.5 | 0
| 29 | 800 | 13060 | 6738 |  | Level 29 Hotel | Access Scaffold |  | Independent | 9 | 1.3 | 4 |  | 4 |  |  | 36 | m2-LxH | OFF HIRED | 2022-08-23 | 2022-08-27 | 100% |  | 0.71429 | 14 | 0 | 504 | 0 | 352.8 | 151.2 | 0 | 504 | 504 | 0
| 29 | 782 | 13042 | 8457 |  | Level 29 Hotel | Access Scaffold |  | Independent | 10 | 1.3 | 4 |  | 4 |  |  | 40 | m2-LxH | OFF HIRED | 2022-08-20 | 2022-12-22 | 100% |  | 17.8571 | 14 | 0 | 560 | 0 | 392 | 168 | 0 | 560 | 560 | 0
| 29 | 618 | 12840 | 7747 |  | Level 29 Hotel | Access Scaffold |  | Independent | 7.5 | 1.3 | 4.5 | 1 | 3.5 |  |  | 26.25 | m2-LxH | OFF HIRED | 2022-07-29 | 2022-07-31 | 100% |  | 0.42857 | 14 | 0.84 | 367.5 | 22.05 | 257.25 | 110.25 | 9.45 | 376.95 | 376.95 | 0
| 29 | 627 | 12849 | 8138 |  | Level 29 Hotel | Access Scaffold |  | Independent | 10 | 1.3 | 5 | 1 | 4 |  |  | 40 | m2-LxH | OFF HIRED | 2022-07-29 | 2022-10-24 | 100% |  | 12.5714 | 14 | 0.84 | 560 | 33.6 | 392 | 168 | 422.4 | 982.4 | 982.4 | 0
| 29 | 651 | 12874 | 7815 |  | Level 29 Hotel | Access Scaffold |  | Independent | 4 | 1.3 | 3.5 | 1 | 2.5 |  |  | 10 | m2-LxH | OFF HIRED | 2022-08-03 | 2022-08-08 | 100% |  | 0.85714 | 14 | 0.84 | 140 | 8.4 | 98 | 42 | 7.2 | 147.2 | 147.2 | 0
| 29 | 634 | 12857 | 7892 |  | Level 29 Hoel | Birdcage Scaffold |  | Birdcage | 7.5 | 2.5 | 5.5 | 1 | 4.5 |  |  | 84.375 | m3 | OFF HIRED | 2022-07-31 | 2022-09-16 | 100% |  | 6.8571 | 7.5 | 0.7 | 632.8125 | 59.0625 | 442.9687 | 189.8438 | 405 | 1037.8125 | 1037.8125 | 0
| 29 | 136 | 12968 | 6738 |  | Level 29 Hotel | Cantiliver |  | Cantiliver | 18 | 0.6 |  |  |  | 1 |  | 10.8 | m2-LxW | OFF HIRED | 2022-08-09 | 2022-09-27 | 100% |  | 7.1429 | 36.5 | 3.15 | 394.2 | 34.02 | 275.94 | 118.26 | 243 | 637.2 | 637.2 | 0
| 29 | 888 | 13259 | 8146 |  | Level 29 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-09-03 | 2022-10-25 | 100% |  | 7.5714 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 231.875 | 569.375 | 569.375 | 0
| 29 | 898 | 13270 | 8146 |  | Level 29 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-09-06 | 2022-10-25 | 100% |  | 7.1429 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 262.5 | 667.5 | 667.5 | 0
| 29 | 933 | 13304 | 8095 |  | Level 29 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-09-10 | 2022-10-11 | 100% |  | 4.5714 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 168 | 573 | 573 | 0
| 29 | 342 | 12444 | 7591 |  | Level 29 Residance | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 5 | 1 | 4 |  |  | 4 | rm | OFF HIRED | 2022-06-24 | 2022-06-29 | 100% |  | 0.85714 | 135 | 12.25 | 540 | 49 | 378 | 162 | 42 | 582 | 582 | 0
| 29 | 572 | 12812 | 6727 |  | Level 29 Residance | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-07-26 | 2022-09-27 | 100% |  | 9.1429 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 336 | 741 | 741 | 0
| 29 | 573 | 12813 | 6727 |  | Level 29 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-07-26 | 2022-09-27 | 100% |  | 9.1429 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 336 | 741 | 741 | 0
| 29 | 462 | 12618 | 7750 |  | Level 29 to 31 Residance | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 15 | 1 | 14 |  |  | 56 | m2-LxH | OFF HIRED | 2022-07-06 | 2022-08-01 | 100% |  | 3.8571 | 14 | 0.84 | 784 | 47.04 | 548.8 | 235.2 | 181.44 | 965.44 | 965.44 | 0
| 29 |  | 12753 | 6726 |  | Level 29 Residance | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 4 | 1 | 3 |  |  | 12 | m2-LxH | OFF HIRED | 2022-07-12 | 2022-09-26 | 100% |  | 11 | 14 | 0.84 | 168 | 10.08 | 117.6 | 50.4 | 110.88 | 278.88 | 278.88 | 0
| 29 | 574 | 12814 | 7804 |  | Level 29 Residance | Access Scaffold |  | INDEPENDENT | 7.5 | 1 | 4 | 1 | 3 |  |  | 22.5 | m2-LxH | OFF HIRED | 2022-07-26 | 2022-08-03 | 100% |  | 1.2857 | 14 | 0.84 | 315 | 18.9 | 220.5 | 94.5 | 24.3 | 339.3 | 339.3 | 0
| 29 | 569 | 12798 | 7839 |  | Level 29 Residance | Access Scaffold |  | INDEPENDENT | 8 | 1.3 | 5.5 | 1 | 4.5 |  |  | 36 | m2-LxH | OFF HIRED | 2022-07-24 | 2022-08-23 | 100% |  | 4.4286 | 14 | 0.84 | 504 | 30.24 | 352.8 | 151.2 | 133.92 | 637.92 | 637.92 | 0
| 29 | 741 | 12999 | 7869 |  | Level 29 Residence | Access Scaffold |  | Tower | 1.3 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-08-15 | 2022-09-03 | 100% |  | 2.8571 | 135 |  | 405 | 0 | 283.5 | 121.5 | 0 | 405 | 405 | 0
| 29 | 599 | 12820 | 7744 |  | Level 29 Residence | Access Scaffold |  | Tower | 2.5 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-07-27 | 2022-07-29 | 100% |  | 0.42857 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 15.75 | 420.75 | 420.75 | 0
| 29 | 600 | 12820 | 7744 |  | Level 29 Residence | Access Scaffold |  | Tower | 2.5 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-07-27 | 2022-07-29 | 100% |  | 0.42857 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 15.75 | 420.75 | 420.75 | 0
| 29 | 636 | 12859 | 7804 |  | Level 29 Residence | Access Scaffold |  | Tower | 1.8 | 1.8 | 3.5 | 1 | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-08-01 | 2022-08-03 | 100% |  | 0.42857 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 13.125 | 350.625 | 350.625 | 0
| 29 | 715 | 12979 | 7869 |  | Level 29 Residence | Access Scaffold |  | Tower | 2.5 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-08-12 | 2022-09-03 | 100% |  | 3.2857 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 120.75 | 525.75 | 525.75 | 0
| 29 | 757 | 13022 | 7866 |  | Level 29 Residence | Access Scaffold |  | Tower | 1.8 | 1.3 | 3.5 | 1 | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-08-17 | 2022-09-03 | 100% |  | 2.5714 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 78.75 | 416.25 | 416.25 | 0
| 29 | 771 | 13033 | 7871 |  | Level 29 Residence | Access Scaffold |  | Tower | 2.5 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-19 | 2022-09-05 | 100% |  | 2.5714 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 63 | 333 | 333 | 0
| 29 | 716 | 12981 | 7841 |  | Level 29 Residence | Access Scaffold |  | Tower | 2.5 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-08-22 | 2022-08-22 | 100% |  | 0.14286 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 5.25 | 410.25 | 410.25 | 0
| 29 | 836 | 13105 | 7853 |  | Level 29 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-08-26 | 2022-08-29 | 100% |  | 0.57143 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 17.5 | 355 | 355 | 0
| 29 | 837 | 13105 | 7853 |  | Level 29 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-08-26 | 2022-08-29 | 100% |  | 0.57143 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 17.5 | 355 | 355 | 0
| 29 | 860 | 13131 | 7874 |  | Level 29 Residence | Access Scaffold |  | Independent | 10 | 1.3 | 3.5 |  | 3.5 |  |  | 35 | m2-LxH | OFF HIRED | 2022-08-30 | 2022-09-06 | 100% |  | 1.1429 | 14 | 0.84 | 490 | 29.4 | 343 | 147 | 33.6 | 523.6 | 523.6 | 0
| 29 | 855 | 13126 | 8147 |  | Level 29 Residence | Access Scaffold |  | Independent | 3 | 1 | 2 |  | 2 |  |  | 6 | m2-LxH | OFF HIRED | 2022-08-30 | 2022-10-25 | 100% |  | 8.1429 | 14 | 0.84 | 84 | 5.04 | 58.8 | 25.2 | 41.04 | 125.04 | 125.04 | 0
| 29 | 904 | 13278 | 8189 |  | Level 29 Residence | Access Scaffold |  | Independent | 3 | 1.8 | 3 |  | 3 |  |  | 9 | m2-LxH | OFF HIRED | 2022-09-07 | 2022-11-03 | 100% |  | 8.2857 | 18 | 1.05 | 162 | 9.45 | 113.4 | 48.6 | 78.3 | 240.3 | 240.3 | 0
| 29 | 1029 | 13466 | 8052 |  | Level 29 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-09-23 | 2022-10-01 | 100% |  | 1.2857 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 39.375 | 376.875 | 376.875 | 0
| 29 | 1037 | 13474 | 6714 |  | Level 29 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-09-23 | 2022-09-24 | 100% |  | 0.28571 | 135 | 12.25 | 540 | 49 | 378 | 162 | 14 | 554 | 554 | 0
| 29 | 1038 | 13475 | 8079 |  | Level 29 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-09-23 | 2022-10-07 | 100% |  | 2.1429 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 65.625 | 403.125 | 403.125 | 0
| 29 | 991 | 13371 | 6704 |  | Level 29 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.8 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-09-17 | 2022-09-21 | 100% |  | 0.71429 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 26.25 | 431.25 | 431.25 | 0
| 29 | 1007 | 13391 | 6707 |  | Level 29 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 0.6 | 3.5 |  | 3.5 |  |  | 3.5 | rm | OFF HIRED | 2022-09-21 | 2022-09-21 | 100% |  | 0.14286 | 135 | 12.25 | 472.5 | 42.875 | 330.75 | 141.75 | 6.125 | 478.625 | 478.625 | 0
| 29 | 956 | 13332 | 8306 |  | Level 29 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-09-14 | 2022-12-06 | 100% |  | 12 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 441 | 846 | 846 | 0
| 29 | 1008 | 13392 | 6726 |  | Level 29 Hotel | Access Scaffold |  | Independent | 7 | 1.3 | 5 |  | 5 |  |  | 35 | m2-LxH | OFF HIRED | 2022-09-21 | 2022-09-26 | 100% |  | 0.85714 | 14 | 0.84 | 490 | 29.4 | 343 | 147 | 25.2 | 515.2 | 515.2 | 0
| 29 | 627 | 13365 | 8265 |  | Level 29 Hotel | Access Scaffold |  | Independent | 25 | 1.3 | 2 |  | 2 |  |  | 50 | m2-LxH | OFF HIRED | 2022-09-17 | 2022-11-22 | 100% |  | 9.5714 | 14 | 0.84 | 700 | 42 | 490 | 210 | 402 | 1102 | 1102 | 0
| 29 | 1195 | 13680 | 8112 |  | Level 29 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-10-12 | 2022-10-17 | 100% |  | 0.85714 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 31.5 | 436.5 | 436.5 | 0
| 29 | 1159 | 13644 | 8106 |  | Level 29 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-10-10 | 2022-10-14 | 100% |  | 0.71429 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 21.875 | 359.375 | 359.375 | 0
| 29 | 1079 | 13512 | 8054 |  | Level 29 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-09-28 | 2022-10-01 | 100% |  | 0.57143 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 14 | 284 | 284 | 0
| 29 | 1099 | 13532 | 8073 |  | Level 29 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-09-30 | 2022-10-05 | 100% |  | 0.85714 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 31.5 | 436.5 | 436.5 | 0
| 29 | 1218 | 13754 | 8138 |  | Level 29 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 5 |  | 5 |  |  | 5 | rm | OFF HIRED | 2022-10-15 | 2022-10-24 | 100% |  | 1.4286 | 135 | 12.25 | 675 | 61.25 | 472.5 | 202.5 | 87.5 | 762.5 | 762.5 | 0
| 29 | 1198 | 13684 | 8499 |  | Level 29 Hotel | Access Scaffold |  | Independent | 15.5 | 1.3 | 3.5 |  | 3.5 |  |  | 54.25 | m2-LxH | OFF HIRED | 2022-10-13 | 2023-01-06 | 100% |  | 12.2857 | 14 | 0.84 | 759.5 | 45.57 | 531.65 | 227.85 | 559.86 | 1319.36 | 1319.36 | 0
| 29 | 1253 | 13791 | 8420 |  | Level 29 To 31 Residence | Access Scaffold |  | Independent | 17 | 1.3 | 2 |  | 2 |  |  | 34 | m2-LxH | OFF HIRED | 2022-10-19 | 2023-01-13 | 100% |  | 12.4286 | 14 | 0.84 | 476 | 28.56 | 333.2 | 142.8 | 354.96 | 830.96 | 830.96 | 0
| 29 | 1310 | 13748 | 8183 |  | Level 29 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-10-28 | 2022-11-01 | 100% |  | 0.71429 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 21.875 | 359.375 | 359.375 | 0
| 29 | 1449 | 13937 | 8265 |  | Level 29 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-11-17 | 2022-11-22 | 100% |  | 0.85714 | 135 | 12.25 | 540 | 49 | 378 | 162 | 42 | 582 | 582 | 0
| 29 | 1364 | 13852 | 8401 |  | Levl 29 Hotel | Access Scaffold |  | INDEPENDENT | 31.5 | 1.3 | 4 |  | 4 |  |  | 126 | m2-LxH | OFF HIRED | 2022-11-04 | 2023-01-07 | 100% |  | 9.2857 | 14 | 0.84 | 1764 | 105.84 | 1234.8 | 529.2 | 982.8 | 2746.8 | 2746.8 | 0
| 29 | 1404 | 13892 | 8279 |  | Level 29 Hotel | Access Scaffold |  | INDEPENDENT | 11.8 | 1.3 | 3 |  | 3 |  |  | 35.4 | m2-LxH | OFF HIRED | 2022-11-10 | 2022-11-26 | 100% |  | 2.4286 | 14 | 0.84 | 495.6 | 29.736 | 346.92 | 148.68 | 72.216 | 567.816 | 567.816 | 0
| 29 | 1448 | 13936 | 8401 |  | Level 29 Hotel | Access Scaffold |  | INDEPENDENT | 11.8 | 1.3 | 3.5 |  | 3.5 |  |  | 41.3 | m2-LxH | OFF HIRED | 2022-11-17 | 2023-01-07 | 100% |  | 7.4286 | 14 | 0.84 | 578.2 | 34.692 | 404.74 | 173.46 | 257.712 | 835.912 | 835.912 | 0
| 29 | 1500 | 13987 | 8305 |  | Level 29 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-11-26 | 2022-12-06 | 100% |  | 1.5714 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 38.5 | 308.5 | 308.5 | 0
| 29 | 1595 | 14130 | 8489 |  | Level 29 Hotel | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 2 |  | 2 |  |  | 10 | m2-LxH | OFF HIRED | 2022-12-14 | 2023-01-03 | 100% |  | 3 | 14 | 0.84 | 140 | 8.4 | 98 | 42 | 25.2 | 165.2 | 165.2 | 0
| 29 | 1666 | 14252 |  |  | Level 29 Hotel | Access Scaffold |  | INDEPENDENT | 7.3 | 1 | 1 |  | 1 |  |  | 7.3 | m2-LxH | ON HIRE | 2022-12-24 |  | 100% |  | 9.5714 | 14 | 0.84 | 102.2 | 6.132 | 71.54 | 0 | 58.692 | 130.232 | 105.704 | 24.528 |  |  | #VALUE! | 71.54 | #VALUE! | #VALUE!
| 29 | 1500 | 13987 | 8305 |  | Level 29 Hotel | Cantiliver |  | Cantiliver | 1.3 | 1 |  |  |  | 1 |  | 1.3 | m2-LxW | OFF HIRED | 2022-11-26 | 2022-12-06 | 100% |  | 1.5714 | 36.5 | 3.15 | 47.45 | 4.095 | 33.215 | 14.235 | 6.435 | 53.885 | 53.885 | 0
| 30 | 533 | 12744 | 8262 |  | Level 30 Hotel | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 3 | 1 | 2 |  |  | 8 | m2-LxH | OFF HIRED | 2022-07-17 | 2022-11-22 | 100% |  | 18.4286 | 14 | 0.84 | 112 | 6.72 | 78.4 | 33.6 | 123.84 | 235.84 | 235.84 | 0
| 30 | 254 | 12368 | 6723 |  | Level 30 Residance | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-06-16 | 2022-09-26 | 100% |  | 14.7143 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 540.75 | 945.75 | 945.75 | 0
| 30 | 262 | 12376 | 7746 |  | Level 30 Residance | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-06-17 | 2022-07-31 | 100% |  | 6.4286 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 236.25 | 641.25 | 641.25 | 0
| 30 | 357 | 12518 | 6723 |  | Level 30 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-06-27 | 2022-09-26 | 100% |  | 13.1429 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 483 | 888 | 888 | 0
| 30 | 366 | 12521 | 7822 |  | Level 30 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-06-27 | 2022-08-08 | 100% |  | 6.1429 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 225.75 | 630.75 | 630.75 | 0
| 30 | A262 | 12522 | 7822 |  | Level 30 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-06-27 | 2022-08-08 | 100% |  | 6.1429 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 225.75 | 630.75 | 630.75 | 0
| 30 | 345 | 12447 | 7590 |  | Level 30 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-06-24 | 2022-06-28 | 100% |  | 0.71429 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 26.25 | 431.25 | 431.25 | 0
| 30 | 117 | 12148 | 6724 |  | Level 30 Residence | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 4 | 1 | 3 |  |  | 12 | m2-LxH | OFF HIRED | 2022-06-02 | 2022-09-26 | 100% |  | 16.7143 | 14 |  | 168 | 0 | 117.6 | 50.4 | 0 | 168 | 168 | 0
| 30 | 179 | 12175 | 7575 |  | Level 30 Residaence | Access Scaffold |  | INDEPENDENT | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 3.6 | m2-LxH | OFF HIRED | 2022-06-08 | 2022-06-19 | 100% |  | 1.7143 | 14 |  | 50.4 | 0 | 35.28 | 15.12 | 0 | 50.4 | 50.4 | 0
| 30 | 215 | 12312 | 7575 |  | Level 30 Residence | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 2.5 | 1 | 1.5 |  |  | 6 | m2-LxH | OFF HIRED | 2022-06-12 | 2022-06-19 | 100% |  | 1.1429 | 14 |  | 84 | 0 | 58.8 | 25.2 | 0 | 84 | 84 | 0
| 30 | 216 | 12313 | 7575 |  | Level 30 Residence | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 3 | 1 | 2 |  |  | 10 | m2-LxH | OFF HIRED | 2022-06-12 | 2022-06-19 | 100% |  | 1.1429 | 14 |  | 140 | 0 | 98 | 42 | 0 | 140 | 140 | 0
| 30 | 343 | 12445 | 7835 |  | Level 30 Residence | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 4 | 1 | 3 |  |  | 12 | m2-LxH | OFF HIRED | 2022-06-24 | 2022-08-19 | 100% |  | 8.1429 | 14 |  | 168 | 0 | 117.6 | 50.4 | 0 | 168 | 168 | 0
| 30 | 230 | 12334 | 7587 |  | Level 30 Residence | Access Scaffold |  | INDEPENDENT | 7.5 | 1.3 | 3 | 1 | 2 |  |  | 15 | m2-LxH | OFF HIRED | 2022-06-14 | 2022-06-27 | 100% |  | 2 | 14 | 0.84 | 210 | 12.6 | 147 | 63 | 25.2 | 235.2 | 235.2 | 0
| 30 | 318 | 12419 | 7590 |  | Level 30 Residence | Access Scaffold |  | INDEPENDENT | 3 | 1.3 | 4 | 1 | 3 |  |  | 9 | m2-LxH | OFF HIRED | 2022-06-21 | 2022-06-28 | 100% |  | 1.1429 | 14 | 0.84 | 126 | 7.56 | 88.2 | 37.8 | 8.64 | 134.64 | 134.64 | 0
| 30 | 401 | 12562 | 7899 |  | Level 30 Receidence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-06-29 | 2022-09-19 | 100% |  | 11.8571 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 435.75 | 840.75 | 840.75 | 0
| 30 | 487 | 12639 | 6724 |  | Level 30 Receidence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-07-06 | 2022-09-26 | 100% |  | 11.8571 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 435.75 | 840.75 | 840.75 | 0
| 30 | 463 | 12620 | 7803 |  | Level 30 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-07-07 | 2022-08-03 | 100% |  | 4 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 147 | 552 | 552 | 0
| 30 | 538 | 12748 | 7869 |  | Level 30 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-07-17 | 2022-09-03 | 100% |  | 7 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 257.25 | 662.25 | 662.25 | 0
| 30 | 417 | 12577 | 6727 |  | Level 30 Residance | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 4 | 1 | 3 |  |  | 12 | m2-LxH | OFF HIRED | 2022-07-01 | 2022-09-27 | 100% |  | 12.7143 | 14 | 0.84 | 168 | 10.08 | 117.6 | 50.4 | 128.16 | 296.16 | 296.16 | 0
| 30 | 505 | 12710 | 6729 |  | Level 30 Residance | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 4 | 1 | 3 |  |  | 12 | m2-LxH | OFF HIRED | 2022-07-13 | 2022-09-27 | 100% |  | 11 | 14 | 0.84 | 168 | 10.08 | 117.6 | 50.4 | 110.88 | 278.88 | 278.88 | 0
| 30 | 527 | 12735 | 7864 |  | Level 30 Residance | Access Scaffold |  | INDEPENDENT | 20 | 1.3 | 9 | 1 | 8 |  |  | 160 | m2-LxH | OFF HIRED | 2022-07-15 | 2022-08-27 | 100% |  | 6.2857 | 14 | 0.84 | 2240 | 134.4 | 1568 | 672 | 844.8 | 3084.8 | 3084.8 | 0
| 30 | 527 | 12735 | 7864 |  | Level 30 Residence | Cantiliver |  | Cantiliver | 20 | 0.6 |  |  |  | 1 |  | 12 | m2-LxW | OFF HIRED | 2022-07-15 | 2022-08-27 | 100% |  | 6.2857 | 36.5 | 3.15 | 438 | 37.8 | 306.6 | 131.4 | 237.6 | 675.6 | 675.6 | 0
| 30 |  | 12714 | 6729 |  | Level 30 Residence | Netting Instalation |  | Netting | 6 |  | 3 | 1 | 2 |  |  | 12 | m2-LxH | OFF HIRED | 2022-07-11 | 2022-09-27 | 100% |  | 11.2857 | 4.5 |  | 54 | 0 | 37.8 | 16.2 | 0 | 54 | 54 | 0
| 30 |  | 12714 | 6729 |  | Level 30 Residence | Netting Instalation |  | Netting | 15 |  | 3 | 1 | 2 |  |  | 30 | m2-LxH | OFF HIRED | 2022-07-11 | 2022-09-27 | 100% |  | 11.2857 | 4.5 |  | 135 | 0 | 94.5 | 40.5 | 0 | 135 | 135 | 0
| 30 |  | 12714 | 6729 |  | Level 30 Residence | Netting Instalation |  | Netting | 18 |  | 2 | 1 | 1 |  |  | 18 | m2-LxH | OFF HIRED | 2022-07-11 | 2022-09-27 | 100% |  | 11.2857 | 4.5 |  | 81 | 0 | 56.7 | 24.3 | 0 | 81 | 81 | 0
| 30 | 621 | 12843 | 7874 |  | Level 30 Residance | Access Scaffold |  | Tower | 2.5 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-29 | 2022-09-06 | 100% |  | 5.7143 | 135 |  | 270 | 0 | 189 | 81 | 0 | 270 | 270 | 0
| 30 | 813 | 13076 | 7879 |  | Level 30 Residence | Access Scaffold |  | Tower | 1.3 | 0.6 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-08-24 | 2022-09-10 | 100% |  | 2.5714 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 78.75 | 416.25 | 416.25 | 0
| 30 | 772 | 13034 | 6736 |  | Level 30 Residence | Access Scaffold |  | Independent | 4 | 1.3 | 4 | 1 | 3 |  |  | 12 | m2-LxH | OFF HIRED | 2022-08-19 | 2022-09-29 | 100% |  | 6 | 14 | 0.84 | 168 | 10.08 | 117.6 | 50.4 | 60.48 | 228.48 | 228.48 | 0
| 30 |  | 12882 | 6730 |  | Level 30 Residence | Netting Instalation |  | Netting | 10 |  | 4 | 1 | 3 |  |  | 30 | m2-LxH | OFF HIRED | 2022-07-31 | 2022-09-28 | 100% |  | 8.5714 | 4.5 |  | 135 | 0 | 94.5 | 40.5 | 0 | 135 | 135 | 0
| 30 |  | 12882 | 6730 |  | Level 30 Residence | Netting Instalation |  | Netting | 10 |  | 4 | 1 | 3 |  |  | 30 | m2-LxH | OFF HIRED | 2022-07-31 | 2022-09-28 | 100% |  | 8.5714 | 4.5 |  | 135 | 0 | 94.5 | 40.5 | 0 | 135 | 135 | 0
| 30 | 854 | 13125 | 7870 |  | Level 30 Residence | HEAVY DUTY TOWER |  | Tower | 1.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-08-29 | 2022-09-03 | 100% |  | 0.85714 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 26.25 | 363.75 | 363.75 | 0
| 30 | 852 | 13124 | 7865 |  | Level 30 Residence | HEAVY DUTY TOWER |  | Tower | 2 | 1.3 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-08-29 | 2022-09-03 | 100% |  | 0.85714 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 31.5 | 436.5 | 436.5 | 0
| 30 | 850 | 13122 | 7865 |  | Level 30 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-08-29 | 2022-09-03 | 100% |  | 0.85714 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 31.5 | 436.5 | 436.5 | 0
| 30 | 872 | 13143 | 8187 |  | Level 30Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-09-01 | 2022-11-03 | 100% |  | 9.1429 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 280 | 617.5 | 617.5 | 0
| 30 | 896 | 13267 | 7899 |  | Level 30 Residence | HEAVY DUTY TOWER |  | Tower | 4 | 1.3 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-09-06 | 2022-09-19 | 100% |  | 2 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 73.5 | 478.5 | 478.5 | 0
| 30 | 896 | 13267 | 7899 |  | Level 30 Residence | HEAVY DUTY TOWER |  | Tower | 4 | 1.3 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-09-06 | 2022-09-19 | 100% |  | 2 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 73.5 | 478.5 | 478.5 | 0
| 30 | 896 | 13267 | 7899 |  | Level 30 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-09-06 | 2022-09-19 | 100% |  | 2 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 73.5 | 478.5 | 478.5 | 0
| 30 | 942 | 13315 | 6713 |  | Level 30 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-09-12 | 2022-09-24 | 100% |  | 1.8571 | 135 | 12.25 | 540 | 49 | 378 | 162 | 91 | 631 | 631 | 0
| 30 | 993 | 13377 | 8435 |  | Level 30 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 6 |  | 6 |  |  | 6 | rm | OFF HIRED | 2022-09-19 | 2023-01-17 | 100% |  | 17.2857 | 135 | 12.25 | 810 | 73.5 | 567 | 243 | 1270.5 | 2080.5 | 2080.5 | 0
| 30 | 965 | 13340 | 7899 |  | Level 30 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-09-15 | 2022-09-19 | 100% |  | 0.71429 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 26.25 | 431.25 | 431.25 | 0
| 30 | 973 | 13349 | 8178 |  | Level 30 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-09-16 | 2022-11-01 | 100% |  | 6.7143 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 246.75 | 651.75 | 651.75 | 0
| 30 | 1122 | 13606 | 8098 |  | Level 30 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-10-04 | 2022-10-12 | 100% |  | 1.2857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 31.5 | 301.5 | 301.5 | 0
| 30 | 1065 | 13502 | 8052 |  | Level 30 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-09-27 | 2022-10-01 | 100% |  | 0.71429 | 135 | 12.25 | 540 | 49 | 378 | 162 | 35 | 575 | 575 | 0
| 30 | 1080 | 13513 | 8054 |  | Level 30 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-09-28 | 2022-10-01 | 100% |  | 0.57143 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 21 | 426 | 426 | 0
| 30 | 1138 | 13622 | 8106 |  | Level 30 Residence | HEAVY DUTY TOWER |  | Tower | 2 | 1 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-10-06 | 2022-10-14 | 100% |  | 1.2857 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 47.25 | 452.25 | 452.25 | 0
| 30 | 1136 | 13620 | 8121 |  | Level 30 Residence | HEAVY DUTY TOWER |  | Tower | 2 | 2 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-10-06 | 2022-10-19 | 100% |  | 2 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 61.25 | 398.75 | 398.75 | 0
| 30 | 1294 | 13733 | 8178 |  | Level 30 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 0.6 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-10-25 | 2022-11-01 | 100% |  | 1.1429 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 28 | 298 | 298 | 0
| 30 | 1137 | 13621 | 8082 |  | Level 30 Residence | Access Scaffold |  | Independent | 2 | 0.6 | 2.5 |  | 2.5 |  |  | 5 | m2-LxH | OFF HIRED | 2022-10-06 | 2022-10-07 | 100% |  | 0.28571 | 14 | 0.84 | 70 | 4.2 | 49 | 21 | 1.2 | 71.2 | 71.2 | 0
| 30 | 1150 | 13634 | 8091 |  | Level 30 Hotel | Access Scaffold |  | Independent | 3 | 1.8 | 2 |  | 2 |  |  | 6 | m2-LxH | OFF HIRED | 2022-10-07 | 2022-10-10 | 100% |  | 0.57143 | 18 | 1.05 | 108 | 6.3 | 75.6 | 32.4 | 3.6 | 111.6 | 111.6 | 0
| 30 | 1055 | 13494 | 8306 |  | Level 30 Residence | Access Scaffold |  | Cantiliver | 6 | 2 | 6 |  |  |  | 1 | 1 | unit | OFF HIRED | 2022-09-26 | 2022-12-06 | 100% |  | 10.2857 | 3000 | 350 | 3000 | 350 | 2100 | 900 | 3600 | 6600 | 6600 | 0
| 30 | 1334 | 13822 | 8333 |  | Level 30 Residence | HEAVY DUTY TOWER |  | Tower | 2.3 | 1 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-11-01 | 2022-12-15 | 100% |  | 6.4286 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 157.5 | 427.5 | 427.5 | 0
| 30 | 1480 | 13968 |  |  | Level 30 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | ON HIRE | 2022-11-23 |  | 100% |  | 14 | 135 | 12.25 | 270 | 24.5 | 189 | 0 | 343 | 532 | 434 | 98 |  |  | #VALUE! | 425.25 | #VALUE! | #VALUE!
| 30 | 1480 | 13968 |  |  | Level 30 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 2.5 |  | 2.5 |  |  | 2.5 | rm | ON HIRE | 2022-11-23 |  | 100% |  | 14 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 0 | 428.75 | 665 | 542.5 | 122.5 |  |  | #VALUE! | 425.25 | #VALUE! | #VALUE!
| 30 | 1385 | 13873 | 8448 |  | Level 30 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 0.6 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2022-11-08 | 2023-01-23 | 100% |  | 11 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 269.5 | 539.5 | 539.5 | 0
| 30 | 1630 | 14167 | 8568 |  | Level 30 Residence | Access Scaffold |  | Independent | 5 | 1.8 | 2 |  | 2 |  |  | 10 | m2-LxH | OFF HIRED | 2022-12-19 | 2023-02-15 | 100% |  | 8.4286 | 18 | 1.05 | 180 | 10.5 | 126 | 54 | 88.5 | 268.5 | 192 | 76.5 |  |  | #VALUE! | 126 | #VALUE! | #VALUE!
| 30 | 1501 | 13988 | 8577 |  | Level 30 Hotel | Access Scaffold |  | Independent | 5 | 1.8 | 2.5 |  | 2.5 |  |  | 12.5 | m2-LxH | OFF HIRED | 2022-11-26 | 2023-02-20 | 100% |  | 12.4286 | 18 | 1.05 | 225 | 13.125 | 157.5 | 67.5 | 163.125 | 388.125 | 283.125 | 105 |  |  | #VALUE! | 157.5 | #VALUE! | #VALUE!
| 31 | 322 | 12434 | 8133 |  | Level 31 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-06-21 | 2022-10-20 | 100% |  | 17.4286 | 135 |  | 270 | 0 | 189 | 81 | 0 | 270 | 270 | 0
| 31 | 321 | 12433 | 7585 |  | Level 31 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-06-21 | 2022-06-26 | 100% |  | 0.85714 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 31.5 | 436.5 | 436.5 | 0
| 31 | A11 | 12223 | 7570 |  | Level 31 Residence | Access Scaffold |  | INDEPENDENT | 25 | 1.3 | 6 | 1 | 5 |  |  | 125 | m2-LxH | OFF HIRED | 2022-06-05 | 2022-06-12 | 100% |  | 1.1429 | 14 | 0.84 | 1750 | 105 | 1225 | 525 | 120 | 1870 | 1870 | 0
| 31 | A 13 | 12225 | 7576 |  | Level 31 Residence | Access Scaffold |  | INDEPENDENT | 8 | 1.3 | 3 | 1 | 2 |  |  | 16 | m2-LxH | OFF HIRED | 2022-06-05 | 2022-06-22 | 100% |  | 2.5714 | 14 | 0.84 | 224 | 13.44 | 156.8 | 67.2 | 34.56 | 258.56 | 258.56 | 0
| 31 | 371 | 12528 | 6727 |  | Level 31 Residence | Access Scaffold |  | INDEPENDENT | 4 | 1.3 | 2 | 1 | 1 |  |  | 4 | m2-LxH | OFF HIRED | 2022-06-27 | 2022-09-27 | 100% |  | 13.2857 | 14 | 0.84 | 56 | 3.36 | 39.2 | 16.8 | 44.64 | 100.64 | 100.64 | 0
| 31 | 524 | 12732 | 8122 |  | Level 31 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-07-15 | 2022-10-15 | 100% |  | 13.2857 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 488.25 | 893.25 | 893.25 | 0
| 31 | 452 | 12619 | 8152 |  | Level 31 Residence | Birdcage Scaffold |  | Birdcage | 9 | 9 | 5 | 1 | 4 |  |  | 324 | m3 | OFF HIRED | 2022-07-06 | 2022-10-27 | 100% |  | 16.2857 | 7.5 | 0.7 | 2430 | 226.8 | 1701 | 729 | 3693.6 | 6123.6 | 6123.6 | 0
| 31 | 641 | 12864 | 6730 |  | Level 31 Residence | Access Scaffold |  | Tower | 2.5 | 2 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-08-01 | 2022-09-28 | 100% |  | 8.4286 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 206.5 | 476.5 | 476.5 | 0
| 31 | 622 | 12847 | 6707 |  | Level 31 Residence | Access Scaffold |  | Independent | 4 | 1.3 | 4 | 1 | 3 |  |  | 12 | m2-LxH | OFF HIRED | 2022-07-29 | 2022-09-21 | 100% |  | 7.8571 | 14 | 0.84 | 168 | 10.08 | 117.6 | 50.4 | 79.2 | 247.2 | 247.2 | 0
| 31 | 452 | 13039 | 8433 |  | Level 31 Residence | Birdcage Scaffold |  | Birdcage | 7.5 | 5 | 4 | 1 | 3 |  |  | 112.5 | m3 | OFF HIRED | 2022-08-18 | 2023-01-16 | 100% |  | 21.7143 | 7.5 | 0.7 | 843.75 | 78.75 | 590.625 | 253.125 | 1710 | 2553.75 | 2553.75 | 0
| 31 | 831 | 13100 | 7853 |  | Level 31 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2022-08-26 | 2022-08-29 | 100% |  | 0.57143 | 135 |  | 540 | 0 | 378 | 162 | 0 | 540 | 540 | 0
| 31 | 894 | 13265 | 7879 |  | Level 31 Residence | Access Scaffold |  | Independent | 9 | 1.3 | 3 |  | 3 |  |  | 27 | m2-LxH | OFF HIRED | 2022-09-06 | 2022-09-10 | 100% |  | 0.71429 | 14 | 0.84 | 378 | 22.68 | 264.6 | 113.4 | 16.2 | 394.2 | 394.2 | 0
| 31 | 592 | 12810 | 6736 |  | Level 31 Residence | Access Scaffold |  | INDEPENDENT | 5 | 1.3 | 5 | 1 | 4 |  |  | 20 | m2-LxH | OFF HIRED | 2022-07-26 | 2022-09-29 | 100% |  | 9.4286 | 14 | 0.84 | 280 | 16.8 | 196 | 84 | 158.4 | 438.4 | 438.4 | 0
| 31 | 714 | 12978 | 6735 |  | Level 31 Residence | Access Scaffold |  | Tower | 2.5 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-08-12 | 2022-09-28 | 100% |  | 6.8571 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 252 | 657 | 657 | 0
| 31 | 1003 | 13387 | 8230 |  | Level 31 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2022-09-20 | 2022-11-14 | 100% |  | 8 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 294 | 699 | 699 | 0
| 31 | 996 | 13380 | 8086 |  | Level 31 Residence | Access Scaffold |  | Independent | 5 | 1.3 | 7 |  | 7 |  |  | 35 | m2-LxH | OFF HIRED | 2022-09-19 | 2022-10-07 | 100% |  | 2.7143 | 14 | 0.84 | 490 | 29.4 | 343 | 147 | 79.8 | 569.8 | 569.8 | 0
| 31 | 1015 | 13398 |  |  | Level 31 Residence | Access Scaffold |  | Independent | 8 | 1.3 | 4 |  | 4 |  |  | 32 | m2-LxH | ON HIRE | 2022-09-21 |  | 100% |  | 23 | 14 | 0.84 | 448 | 26.88 | 313.6 | 0 | 618.24 | 352 | 352 | 0
| 31 | 1004 | 13388 | 8333 |  | Level 31 Residence | Birdcage Scaffold |  | Birdcage | 7 | 3 | 4 |  | 4 |  |  | 84 | m3 | OFF HIRED | 2022-09-20 | 2022-12-15 | 100% |  | 12.4286 | 7.5 | 0.7 | 630 | 58.8 | 441 | 189 | 730.8 | 1360.8 | 1360.8 | 0
| 31 | 1291 | 13730 | 8492 |  | Level 31 Residence | Birdcage Scaffold |  | Birdcage | 4.4 | 2.5 | 4 |  | 4 |  |  | 44 | m3 | OFF HIRED | 2022-10-25 | 2023-01-05 | 100% |  | 10.4286 | 7.5 | 0.7 | 330 | 30.8 | 231 | 99 | 321.2 | 651.2 | 651.2 | 0
| 31 | 1340 | 13828 | 8194 |  | Level 31 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 0.6 | 1.5 |  | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2022-11-01 | 2022-11-05 | 100% |  | 0.71429 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 60.75 | 13.125 | 215.625 | 215.625 | 0
| 31 | 1313 | 13801 | 8344 |  | Level 31 Residence | Access Scaffold |  | INDEPENDENT | 3.5 | 1 | 4.5 |  | 4.5 |  |  | 15.75 | m2-LxH | OFF HIRED | 2022-10-29 | 2022-12-20 | 100% |  | 7.5714 | 14 | 0.84 | 220.5 | 13.23 | 154.35 | 66.15 | 100.17 | 320.67 | 320.67 | 0
| 31 | 1533 | 14070 |  |  | Level 31 Residence | HEAVY DUTY TOWER |  | Tower | 2.8 | 1 | 4 |  | 4 |  |  | 4 | rm | ON HIRE | 2022-12-06 |  | 100% |  | 12.1429 | 135 | 12.25 | 540 | 49 | 378 | 0 | 595 | 973 | 777 | 196 |  |  | #VALUE! | 378 | #VALUE! | #VALUE!
| 31 | 1539 | 14075 | 8344 |  | Level 31 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-12-07 | 2022-12-20 | 100% |  | 2 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 61.25 | 398.75 | 398.75 | 0
| 31 | 1542 | 14062 |  |  | Level 31 Residence | Access Scaffold |  | INDEPENDENT | 4 | 1 | 4 |  | 4 |  |  | 16 | m2-LxH | ON HIRE | 2022-12-05 |  | 100% |  | 12.2857 | 14 | 0.84 | 224 | 13.44 | 156.8 | 0 | 165.12 | 321.92 | 268.16 | 53.76 |  |  | #VALUE! | 156.8 | #VALUE! | #VALUE!
| 32 | 967 | 13342 | 8088 |  | Level 12 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 0.6 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2022-09-15 | 2022-10-10 | 100% |  | 3.7143 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 113.75 | 451.25 | 451.25 | 0
| 32 | 1529 | 14067 | 8313 |  | Level 12 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 1.5 |  | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2022-12-06 | 2022-12-08 | 100% |  | 0.42857 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 60.75 | 7.875 | 210.375 | 210.375 | 0
| 32 | 1551 | 14085 | 8484 |  | Level 11 To 12 Hotel | Access Scaffold |  | INDEPENDENT | 5 | 1 | 1.8 |  | 1.8 |  |  | 9 | m2-LxH | OFF HIRED | 2022-12-08 | 2023-01-02 | 100% |  | 3.7143 | 14 | 0.84 | 126 | 7.56 | 88.2 | 37.8 | 28.08 | 154.08 | 154.08 | 0
| 32 | 1552 | 14086 |  |  | Level 11 To 12 Hotel | Access Scaffold |  | INDEPENDENT | 5 | 1 | 1.8 |  | 1.8 |  |  | 9 | m2-LxH | ON HIRE | 2022-12-08 |  | 100% |  | 11.8571 | 14 | 0.84 | 126 | 7.56 | 88.2 | 0 | 89.64 | 177.84 | 147.6 | 30.24 |  |  | #VALUE! | 362.6 | #VALUE! | #VALUE!
| 32 | 1551 | 14085 | 8484 |  | Level 11 & 12 Hotel | Cantiliver |  | Cantiliver | 5 | 0.6 |  |  |  | 0.6 |  | 1.8 | m2-LxW | OFF HIRED | 2022-12-08 | 2023-01-02 | 100% |  | 3.7143 | 36.5 | 3.15 | 65.7 | 5.67 | 45.99 | 19.71 | 21.06 | 86.76 | 86.76 | 0
| 32 | 1552 | 14087 | 8573 |  | Level 11 & 12 Hotel | Cantiliver |  | Cantiliver | 5 | 0.6 |  |  |  | 0.6 |  | 1.8 | m2-LxW | OFF HIRED | 2022-12-08 | 2023-02-17 | 100% |  | 10.2857 | 36.5 | 3.15 | 65.7 | 5.67 | 45.99 | 19.71 | 58.32 | 124.02 | 90.54 | 33.48 |  |  | #VALUE! | 887.67 | #VALUE! | #VALUE!
| 32 | 1529 | 14067 | 8313 |  | Level 12 Hotel | Cantiliver |  | Cantiliver | 1.3 | 0.6 |  |  |  | 0.6 |  | 0.468 | m2-LxW | OFF HIRED | 2022-12-06 | 2022-12-08 | 100% |  | 0.42857 | 36.5 | 3.15 | 17.082 | 1.4742 | 11.9574 | 5.1246 | 0.6318 | 17.7138 | 17.7138 | 0
|  | 298 | 12404 | 8189 |  | Roof Level Residence | Access Scaffold |  | INDEPENDENT | 4.5 | 1.3 | 3 | 1 | 2 |  |  | 9 | m2-LxH | OFF HIRED | 2022-06-19 | 2022-11-03 | 100% |  | 19.7143 | 14 | 0.84 | 126 | 7.56 | 88.2 | 37.8 | 149.04 | 275.04 | 275.04 | 0
|  | 453 | 12610 | 8248 |  | Roof Level Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 | 1 | 3 |  |  | 3 | rm | OFF HIRED | 2022-07-06 | 2022-11-15 | 100% |  | 19 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 698.25 | 1103.25 | 1103.25 | 0
|  | 635 | 12858 | 7815 |  | Roof Level Hotel | Access Scaffold |  | Tower | 1.8 | 0.6 | 3 | 1 | 2 |  |  | 2 | rm | OFF HIRED | 2022-07-31 | 2022-08-08 | 100% |  | 1.2857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 31.5 | 301.5 | 301.5 | 0
| 1 | 1689 | 14274 |  |  | Basement 1 Hotel | Mobile Tower |  | Mobile Tower | 2.5 | 1.3 | 4 |  | 4 |  |  | 4 | rm | ON HIRE | 2022-12-31 |  | 100% |  | 8.5714 | 100 | 10.15 | 400 | 40.6 | 280 | 0 | 348 | 628 | 465.6 | 162.4 |  |  | #VALUE! | 280 | #VALUE! | #VALUE!
| 28 | 1683 | 14268 | 8631 |  | Level 28 Hotel | Mobile Tower |  | Mobile Tower | 1.8 | 1.8 | 3.5 |  | 3.5 |  |  | 3.5 | rm | OFF HIRED | 2022-12-29 | 2023-02-03 | 100% |  | 5.2857 | 100 | 10.15 | 350 | 35.525 | 245 | 105 | 187.775 | 537.775 | 417.55 | 120.225 |  |  | #VALUE! | 245 | #VALUE! | #VALUE!
| 9 | 1805 | 14394 | 8591 |  | Level 7 Hotel | Mobile Tower |  | Mobile Tower | 1.8 | 1.8 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2023-01-27 | 2023-02-21 | 100% |  | 3.7143 | 100 | 10.15 | 400 | 40.6 | 280 | 120 | 150.8 | 550.8 | 309 | 241.8 |  |  | #VALUE! | 280 | #VALUE! | #VALUE!
| 17 | 1721 | 14306 | 8418 |  | Level 17 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2023-01-10 | 2023-01-12 | 100% |  | 0.42857 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 15.75 | 420.75 | 420.75 | 0
| 1 | 1749 | 14335 | 8620 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2023-01-16 | 2023-02-01 | 100% |  | 2.4286 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 59.5 | 329.5 | 245 | 84.5 |  |  | #VALUE! | 189 | #VALUE! | #VALUE!
| 7 | 1747 | 14333 | 8613 |  | Level 5 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.8 | 3.5 |  | 3.5 |  |  | 3.5 | rm | OFF HIRED | 2023-01-16 | 2023-01-27 | 100% |  | 1.7143 | 135 | 12.25 | 472.5 | 42.875 | 330.75 | 141.75 | 73.5 | 546 | 546 | 0
| 18 | 1701 | 14286 | 8497 |  | Level 18 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2023-01-04 | 2023-01-06 | 100% |  | 0.42857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 10.5 | 280.5 | 280.5 | 0
| 18 | 1701 | 14286 | 8497 |  | Level 18 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2023-01-04 | 2023-01-06 | 100% |  | 0.42857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 10.5 | 280.5 | 280.5 | 0
| 1 | 1711 | 14296 | 8419 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2023-01-07 | 2023-01-13 | 100% |  | 1 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 24.5 | 294.5 | 294.5 | 0
| 1 | 1714 | 14299 | 8411 |  | Basement 1 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 0.6 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2023-01-09 | 2023-01-10 | 100% |  | 0.28571 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 7 | 277 | 277 | 0
| 23 | 1715 | 14300 | 8581 |  | Level 23 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2023-01-09 | 2023-02-20 | 100% |  | 6.1429 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 188.125 | 525.625 | 336.875 | 188.75 |  |  | #VALUE! | 236.25 | #VALUE! | #VALUE!
| 1 | 1688 | 14273 |  |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 3 |  | 3 |  |  | 3 | rm | ON HIRE | 2022-12-31 |  | 100% |  | 8.5714 | 135 | 12.25 | 405 | 36.75 | 283.5 | 0 | 315 | 598.5 | 451.5 | 147 |  |  | #VALUE! | 283.5 | #VALUE! | #VALUE!
| 18 | 1724 | 14309 | 8441 |  | Levlel 18 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3.5 |  | 3.5 |  |  | 3.5 | rm | OFF HIRED | 2023-01-10 | 2023-01-17 | 100% |  | 1.1429 | 135 | 12.25 | 472.5 | 42.875 | 330.75 | 141.75 | 49 | 521.5 | 521.5 | 0
| 17 | 1729 | 14314 | 8624 |  | Level 17 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 1.5 |  | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2023-01-11 | 2023-02-01 | 100% |  | 3.1429 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 60.75 | 57.75 | 260.25 | 196.875 | 63.375 |  |  | #VALUE! | 141.75 | #VALUE! | #VALUE!
| 18 | 1728 | 14313 | 8447 |  | Level 18 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3.5 |  | 3.5 |  |  | 3.5 | rm | OFF HIRED | 2023-01-11 | 2023-01-21 | 100% |  | 1.5714 | 135 | 12.25 | 472.5 | 42.875 | 330.75 | 141.75 | 67.375 | 539.875 | 539.875 | 0
| 1 | 1737 | 14321 | 8645 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 1.5 |  | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2023-01-14 | 2023-02-08 | 100% |  | 3.7143 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 60.75 | 68.25 | 270.75 | 189 | 81.75 |  |  | #VALUE! | 141.75 | #VALUE! | #VALUE!
| 1 | 1738 | 14322 | 8604 |  | Basement 1 | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4.5 |  | 4.5 |  |  | 4.5 | rm | OFF HIRED | 2023-01-14 | 2023-01-25 | 100% |  | 1.7143 | 135 | 12.25 | 607.5 | 55.125 | 425.25 | 182.25 | 94.5 | 702 | 702 | 0
| 9 | 1745 | 14331 | 8450 |  | Level 7 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 3 |  | 3 |  |  | 3 | rm | OFF HIRED | 2023-01-16 | 2023-01-23 | 100% |  | 1.1429 | 135 | 12.25 | 405 | 36.75 | 283.5 | 121.5 | 42 | 447 | 447 | 0
| 28 | 1768 | 14355 |  |  | Level 28 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 3.5 |  | 3.5 |  |  | 3.5 | rm | ON HIRE | 2023-01-20 |  | 100% |  | 5.7143 | 135 | 12.25 | 472.5 | 42.875 | 330.75 | 0 | 245 | 575.75 | 404.25 | 171.5 |  |  | #VALUE! | 330.75 | #VALUE! | #VALUE!
| 1 | 1775 | 14363 |  |  | Basement 2 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 4 |  | 4 |  |  | 4 | rm | ON HIRE | 2023-01-21 |  | 100% |  | 5.5714 | 135 | 12.25 | 540 | 49 | 378 | 0 | 273 | 651 | 455 | 196 |  |  | #VALUE! | 378 | #VALUE! | #VALUE!
| 2 | 1776 | 14364 |  |  | Ground Floor Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 4 |  | 4 |  |  | 4 | rm | ON HIRE | 2023-01-21 |  | 100% |  | 5.5714 | 135 | 12.25 | 540 | 49 | 378 | 0 | 273 | 651 | 455 | 196 |  |  | #VALUE! | 756 | #VALUE! | #VALUE!
| 2 | 1776 | 14364 |  |  | Ground Floor Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 4 |  | 4 |  |  | 4 | rm | ON HIRE | 2023-01-21 |  | 100% |  | 5.5714 | 135 | 12.25 | 540 | 49 | 378 | 0 | 273 | 651 | 455 | 196 |  |  | #VALUE! | 756 | #VALUE! | #VALUE!
| 1 | 1778 | 14366 |  |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | ON HIRE | 2023-01-21 |  | 100% |  | 5.5714 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 0 | 170.625 | 406.875 | 284.375 | 122.5 |  |  | #VALUE! | 236.25 | #VALUE! | #VALUE!
| 6 | 1779 | 14367 | 8618 |  | Level 4 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 1.5 |  | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2023-01-21 | 2023-01-30 | 100% |  | 1.4286 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 60.75 | 26.25 | 228.75 | 170.625 | 58.125 |  |  | #VALUE! | 141.75 | #VALUE! | #VALUE!
| 1 | 1789 | 14378 | 8571 |  | Basement 1 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2023-01-24 | 2023-02-17 | 100% |  | 3.5714 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 109.375 | 446.875 | 271.25 | 175.625 |  |  | #VALUE! | 236.25 | #VALUE! | #VALUE!
| 2 | 1790 | 14379 |  |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 2 |  | 2 |  |  | 2 | rm | ON HIRE | 2023-01-24 |  | 100% |  | 5.1429 | 135 | 12.25 | 270 | 24.5 | 189 | 0 | 126 | 315 | 217 | 98 |  |  | #VALUE! | 189 | #VALUE! | #VALUE!
| 1 | 1783 | 14371 | 8642 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2023-01-21 | 2023-02-07 | 100% |  | 2.5714 | 135 | 12.25 | 540 | 49 | 378 | 162 | 126 | 666 | 455 | 211 |  |  | #VALUE! | 378 | #VALUE! | #VALUE!
| 3 | 1795 | 14384 |  |  | Level 2 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 5.5 |  | 5.5 |  |  | 5.5 | rm | ON HIRE | 2023-01-25 |  | 100% |  | 5 | 135 | 12.25 | 742.5 | 67.375 | 519.75 | 0 | 336.875 | 856.625 | 587.125 | 269.5 |  |  | #VALUE! | 519.75 | #VALUE! | #VALUE!
| 31 | 1767 | 14354 |  |  | Level 31 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 2.5 |  | 2.5 |  |  | 2.5 | rm | ON HIRE | 2023-01-19 |  | 100% |  | 5.8571 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 0 | 179.375 | 415.625 | 293.125 | 122.5 |  |  | #VALUE! | 299.46 | #VALUE! | #VALUE!
| 3 | 1788 | 14377 | 8621 |  | Level 2 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 0.6 | 1.5 |  | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2023-01-23 | 2023-02-01 | 100% |  | 1.4286 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 60.75 | 26.25 | 228.75 | 165.375 | 63.375 |  |  | #VALUE! | 164.745 | #VALUE! | #VALUE!
| 1 | 1678 | 14263 |  |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1 | 4 |  | 4 |  |  | 4 | rm | ON HIRE | 2022-12-28 |  | 100% |  | 9 | 135 | 12.25 | 540 | 49 | 378 | 0 | 441 | 819 | 623 | 196 |  |  | #VALUE! | 394.5564 | #VALUE! | #VALUE!
| 3 | 1692 | 14277 |  |  | Level 2 Hotel | HEAVY DUTY TOWER |  | Tower | 2.8 | 1.3 | 6 |  | 6 |  |  | 6 | rm | ON HIRE | 2022-12-31 |  | 100% |  | 8.5714 | 135 | 12.25 | 810 | 73.5 | 567 | 0 | 630 | 1197 | 903 | 294 |  |  | #VALUE! | 589.995 | #VALUE! | #VALUE!
| 28 | 1708 | 14293 | 8444 |  | Level 28 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3.5 |  | 3.5 |  |  | 3.5 | rm | OFF HIRED | 2023-01-06 | 2023-01-20 | 100% |  | 2.1429 | 135 | 12.25 | 472.5 | 42.875 | 330.75 | 141.75 | 91.875 | 564.375 | 564.375 | 0
| 6 | 1733 | 14318 | 8597 |  | Level 4 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 1.5 |  | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2023-01-13 | 2023-02-24 | 100% |  | 6.1429 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 60.75 | 112.875 | 315.375 | 191.625 | 123.75 |  |  | #VALUE! | 167.3 | #VALUE! | #VALUE!
| 1 | 1750 | 14336 |  |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 |  | 4 |  |  | 4 | rm | ON HIRE | 2023-01-16 |  | 100% |  | 6.2857 | 135 | 12.25 | 540 | 49 | 378 | 0 | 308 | 686 | 490 | 196 |  |  | #VALUE! | 534.8 | #VALUE! | #VALUE!
| 1 | 1803 | 14392 | 8555 |  | Basement 1 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.8 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2023-01-26 | 2023-02-10 | 100% |  | 2.2857 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 56 | 326 | 210 | 116 |  |  | #VALUE! | 189 | #VALUE! | #VALUE!
| 1 | 1810 | 14399 | 8633 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2023-01-27 | 2023-02-03 | 100% |  | 1.1429 | 135 | 12.25 | 540 | 49 | 378 | 162 | 56 | 596 | 413 | 183 |  |  | #VALUE! | 400.995 | #VALUE! | #VALUE!
| 31 | 1812 | 14401 | 8641 |  | Level 31 Residence |  |  | Independent | 2.5 | 1 | 2.5 |  | 2.5 |  |  | 6.25 | m2-LxH | OFF HIRED | 2023-01-28 | 2023-02-06 | 100% |  | 1.4286 | 14 | 0.84 | 87.5 | 5.25 | 61.25 | 26.25 | 7.5 | 95 | 64.25 | 30.75 |  |  | #VALUE! | 61.25 | #VALUE! | #VALUE!
| 1 | 1815 | 14404 | 8564 |  | Basement 2 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 1.5 |  | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2023-01-28 | 2023-02-15 | 100% |  | 2.7143 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 60.75 | 49.875 | 252.375 | 152.25 | 100.125 |  |  | #VALUE! | 141.75 | #VALUE! | #VALUE!
| 31 | 1819 | 14407 |  |  | Level 31 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 1.5 |  | 1.5 |  |  | 1.5 | rm | ON HIRE | 2023-01-29 |  | 100% |  | 4.4286 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 0 | 81.375 | 223.125 | 149.625 | 73.5 |  |  | #VALUE! | 141.75 | #VALUE! | #VALUE!
| 1 | 1801 | 14390 |  |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.8 | 3.5 |  | 3.5 |  |  | 3.5 | rm | ON HIRE | 2023-01-26 |  | 100% |  | 4.8571 | 135 | 12.25 | 472.5 | 42.875 | 330.75 | 0 | 208.25 | 539 | 367.5 | 171.5 |  |  | #VALUE! | 537.5737 | #VALUE! | #VALUE!
| 1 | 1748 | 14334 | 8620 |  | Basement 1 Residence | Access Scaffold |  | Independent | 10 | 1.3 | 2 |  | 2 |  |  | 20 | m2-LxH | OFF HIRED | 2023-01-16 | 2023-02-01 | 100% |  | 2.4286 | 14 | 0.84 | 280 | 16.8 | 196 | 84 | 40.8 | 320.8 | 234.4 | 86.4 |  |  | #VALUE! | 823.2 | #VALUE! | #VALUE!
| 1 | 1748 | 14334 | 8620 |  | Basement 1 Residence | Access Scaffold |  | Independent | 16 | 0.6 | 4 |  | 4 |  |  | 64 | m2-LxH | OFF HIRED | 2023-01-16 | 2023-02-01 | 100% |  | 2.4286 | 14 | 0.84 | 896 | 53.76 | 627.2 | 268.8 | 130.56 | 1026.56 | 750.08 | 276.48 |  |  | #VALUE! | 823.2 | #VALUE! | #VALUE!
| 32 | 1732 | 14317 | 8558 |  | Level 12 Hotel | Access Scaffold |  | Independent | 6 | 1.3 | 1.5 |  | 1.5 |  |  | 9 | m2-LxH | OFF HIRED | 2023-01-12 | 2023-02-11 | 100% |  | 4.4286 | 14 | 0.84 | 126 | 7.56 | 88.2 | 37.8 | 33.48 | 159.48 | 109.8 | 49.68 |  |  | #VALUE! | 88.2 | #VALUE! | #VALUE!
| 2 | 1744 | 14330 | 8432 |  | Ground floor Hotel | Access Scaffold |  | Independent | 8.1 | 1.3 | 4.5 |  | 4.5 |  |  | 36.45 | m2-LxH | OFF HIRED | 2023-01-16 | 2023-01-17 | 100% |  | 0.28571 | 14 | 0.84 | 510.3 | 30.618 | 357.21 | 153.09 | 8.748 | 519.048 | 519.048 | 0
| 1 | 1710 | 14295 | 8419 |  | Basement 1 Residence | Access Scaffold |  | Independent | 26 | 0.6 | 1.5 |  | 1.5 |  |  | 39 | m2-LxH | OFF HIRED | 2023-01-07 | 2023-01-13 | 100% |  | 1 | 14 | 0.84 | 546 | 32.76 | 382.2 | 163.8 | 32.76 | 578.76 | 578.76 | 0
| 2 | 1673 | 14258 | 8454 |  | Ground floor Hotel | Access Scaffold |  | Independent | 3.1 | 1.3 | 7 |  | 7 |  |  | 21.7 | m2-LxH | OFF HIRED | 2022-12-27 | 2023-02-10 | 100% |  | 6.5714 | 14 | 0.84 | 303.8 | 18.228 | 212.66 | 91.14 | 119.784 | 423.584 | 306.404 | 117.18 |  |  | #VALUE! | 359.66 | #VALUE! | #VALUE!
| 2 | 1673 | 14258 | 8554 |  | Ground floor Hotel | Access Scaffold |  | Independent | 2.5 | 1.3 | 4 |  | 4 |  |  | 10 | m2-LxH | OFF HIRED | 2022-12-27 | 2023-02-10 | 100% |  | 6.5714 | 14 | 0.84 | 140 | 8.4 | 98 | 42 | 55.2 | 195.2 | 141.2 | 54 |  |  | #VALUE! | 359.66 | #VALUE! | #VALUE!
| 2 | 1673 | 14258 | 8554 |  | Ground floor Hotel | Access Scaffold |  | Independent | 2.5 | 1.3 | 2 |  | 2 |  |  | 5 | m2-LxH | OFF HIRED | 2022-12-27 | 2023-02-10 | 100% |  | 6.5714 | 14 | 0.84 | 70 | 4.2 | 49 | 21 | 27.6 | 97.6 | 70.6 | 27 |  |  | #VALUE! | 359.66 | #VALUE! | #VALUE!
| 6 | 1680 | 14265 | 8640 |  | Level 4 Hotel | Access Scaffold |  | Independent | 5.6 | 1.3 | 2 |  | 2 |  |  | 11.2 | m2-LxH | OFF HIRED | 2022-12-28 | 2023-02-07 | 100% |  | 6 | 14 | 0.84 | 156.8 | 9.408 | 109.76 | 47.04 | 56.448 | 213.248 | 156.8 | 56.448 |  |  | #VALUE! | 109.76 | #VALUE! | #VALUE!
| 3 | 1679 | 14264 | 8488 |  | Level 2 Hotel | Access Scaffold |  | Independent | 6.8 | 1 | 2 |  | 2 |  |  | 13.6 | m2-LxH | OFF HIRED | 2022-12-28 | 2023-01-03 | 100% |  | 1 | 14 | 0.84 | 190.4 | 11.424 | 133.28 | 57.12 | 11.424 | 201.824 | 201.824 | 0
| 2 | 1682 | 14267 | 8491 |  | Ground Floor Residence | Access Scaffold |  | Independent | 12.5 | 1 | 2 |  | 2 |  |  | 25 | m2-LxH | OFF HIRED | 2022-12-29 | 2023-01-04 | 100% |  | 1 | 14 | 0.84 | 350 | 21 | 245 | 105 | 21 | 371 | 371 | 0
| 28 | 1685 | 14270 | 8435 |  | Level 28 to 30 Hotel | Access Scaffold |  | Independent | 25 | 1 | 2 |  | 2 |  |  | 50 | m2-LxH | OFF HIRED | 2022-12-30 | 2023-01-17 | 100% |  | 2.7143 | 14 | 0.84 | 700 | 42 | 490 | 210 | 114 | 814 | 814 | 0
| 28 | 1685 | 14270 | 8435 |  | Level 28 to 30 Hotel | Access Scaffold |  | Independent | 6 | 0.6 | 6 |  | 6 |  |  | 36 | m2-LxH | OFF HIRED | 2022-12-30 | 2023-01-17 | 100% |  | 2.7143 | 14 | 0.84 | 504 | 30.24 | 352.8 | 151.2 | 82.08 | 586.08 | 586.08 | 0
| 28 | 1685 | 14270 | 8435 |  | Level 28 to 30 Hotel | Access Scaffold |  | Independent | 7.5 | 1 | 4 |  | 4 |  |  | 30 | m2-LxH | OFF HIRED | 2022-12-30 | 2023-01-17 | 100% |  | 2.7143 | 14 | 0.84 | 420 | 25.2 | 294 | 126 | 68.4 | 488.4 | 488.4 | 0
| 2 | 1687 | 14272 | 8495 |  | Ground Floor Residence | Access Scaffold |  | Independent | 26.5 | 0.6 | 1.5 |  | 1.5 |  |  | 39.75 | m2-LxH | OFF HIRED | 2022-12-31 | 2023-01-05 | 100% |  | 0.85714 | 14 | 0.84 | 556.5 | 33.39 | 389.55 | 166.95 | 28.62 | 585.12 | 585.12 | 0
| 1 | 1690 | 14275 |  |  | Basement 1 Residence | Access Scaffold |  | Independent | 6.3 | 1.3 | 4 |  | 4 |  |  | 25.2 | m2-LxH | ON HIRE | 2022-12-31 |  | 100% |  | 8.5714 | 14 | 0.84 | 352.8 | 21.168 | 246.96 | 0 | 181.44 | 428.4 | 343.728 | 84.672 |  |  | #VALUE! | 246.96 | #VALUE! | #VALUE!
| 1 | 1691 | 14276 | 8426 |  | Basement 1 Residence | Access Scaffold |  | Independent | 15 | 1.3 | 4 |  | 4 |  |  | 60 | m2-LxH | OFF HIRED | 2022-12-31 | 2023-01-14 | 100% |  | 2.1429 | 14 | 0.84 | 840 | 50.4 | 588 | 252 | 108 | 948 | 948 | 0
| 1 | 1705 | 14290 | 8611 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 4 | 1.3 | 3 |  | 3 |  |  | 12 | m2-LxH | OFF HIRED | 2023-01-05 | 2023-01-27 | 100% |  | 3.2857 | 14 | 0.84 | 168 | 10.08 | 117.6 | 50.4 | 33.12 | 201.12 | 201.12 | 0
| 1 | 1707 | 14292 | 8415 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 3.8 | 1.3 | 3 |  | 3 |  |  | 11.4 | m2-LxH | OFF HIRED | 2023-01-06 | 2023-01-11 | 100% |  | 0.85714 | 14 | 0.84 | 159.6 | 9.576 | 111.72 | 47.88 | 8.208 | 167.808 | 167.808 | 0
| 1 | 1704 | 14289 | 8574 |  | Basement 1 Residence | Access Scaffold |  | Independent | 4 | 1 | 5 |  | 5 |  |  | 20 | m2-LxH | OFF HIRED | 2023-01-05 | 2023-02-18 | 100% |  | 6.4286 | 14 | 0.84 | 280 | 16.8 | 196 | 84 | 108 | 388 | 260.8 | 127.2 |  |  | #VALUE! | 196 | #VALUE! | #VALUE!
| 1 | 1702 | 14287 | 8644 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 11 | 1.3 | 3 |  | 3 |  |  | 33 | m2-LxH | OFF HIRED | 2023-01-04 | 2023-02-07 | 100% |  | 5 | 14 | 0.84 | 462 | 27.72 | 323.4 | 138.6 | 138.6 | 600.6 | 434.28 | 166.32 |  |  | #VALUE! | 323.4 | #VALUE! | #VALUE!
| 1 | 1696 | 14281 | 8429 |  | Basement 1 Residence | Access Scaffold |  | Independent | 6.8 | 1.3 | 3.5 |  | 3.5 |  |  | 23.8 | m2-LxH | OFF HIRED | 2023-01-03 | 2023-01-16 | 100% |  | 2 | 14 | 0.84 | 333.2 | 19.992 | 233.24 | 99.96 | 39.984 | 373.184 | 373.184 | 0
| 6 | 1695 | 14280 |  |  | Leevl 4 Hotel | Access Scaffold |  | Independent | 6.8 | 1.3 | 2 |  | 2 |  |  | 13.6 | m2-LxH | ON HIRE | 2023-01-02 |  | 100% |  | 8.2857 | 14 | 0.84 | 190.4 | 11.424 | 133.28 | 0 | 94.656 | 227.936 | 182.24 | 45.696 |  |  | #VALUE! | 133.28 | #VALUE! | #VALUE!
| 28 | 1686 | 14271 | 8587 |  | Level 28 Hotel | Access Scaffold |  | Independent | 6 | 1 | 3.5 |  | 3.5 |  |  | 21 | m2-LxH | OFF HIRED | 2022-12-30 | 2023-02-21 | 100% |  | 7.7143 | 14 | 0.84 | 294 | 17.64 | 205.8 | 88.2 | 136.08 | 430.08 | 288.96 | 141.12 |  |  | #VALUE! | 205.8 | #VALUE! | #VALUE!
| 1 | 1698 | 14283 | 8408 |  | Basement 1 Residence | Access Scaffold |  | Independent | 14.5 | 1 | 4 |  | 4 |  |  | 58 | m2-LxH | OFF HIRED | 2023-01-03 | 2023-01-10 | 100% |  | 1.1429 | 14 | 0.84 | 812 | 48.72 | 568.4 | 243.6 | 55.68 | 867.68 | 867.68 | 0
| 3 | 1712 | 14297 |  |  | Level 2 Hotel | Access Scaffold |  | Independent | 4.6 | 1.3 | 6 |  | 6 |  |  | 27.6 | m2-LxH | ON HIRE | 2023-01-07 |  | 100% |  | 7.5714 | 14 | 0.84 | 386.4 | 23.184 | 270.48 | 0 | 175.536 | 446.016 | 353.28 | 92.736 |  |  | #VALUE! | 270.48 | #VALUE! | #VALUE!
| 1 | 1700 | 14285 | 8632 |  | Basement 2 Hotel | Access Scaffold |  | Independent | 5 | 1 | 1.5 |  | 1.5 |  |  | 7.5 | m2-LxH | OFF HIRED | 2023-01-03 | 2023-02-04 | 100% |  | 4.7143 | 14 | 0.84 | 105 | 6.3 | 73.5 | 31.5 | 29.7 | 134.7 | 99.6 | 35.1 |  |  | #VALUE! | 73.5 | #VALUE! | #VALUE!
| 2 | 1716 | 14301 | 8627 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 5 | 1.3 | 1.5 |  | 1.5 |  |  | 7.5 | m2-LxH | OFF HIRED | 2023-01-09 | 2023-02-02 | 100% |  | 3.5714 | 14 | 0.84 | 105 | 6.3 | 73.5 | 31.5 | 22.5 | 127.5 | 94.2 | 33.3 |  |  | #VALUE! | 73.5 | #VALUE! | #VALUE!
| 31 | 1717 | 14304 | 8448 |  | Level 31 Residence | Access Scaffold |  | Independent | 4 | 1.3 | 4 |  | 4 |  |  | 16 | m2-LxH | OFF HIRED | 2023-01-09 | 2023-01-23 | 100% |  | 2.1429 | 14 | 0.84 | 224 | 13.44 | 156.8 | 67.2 | 28.8 | 252.8 | 252.8 | 0
| 1 | 1719 | 14303 |  |  | Basement 1 Hotel | Access Scaffold |  | Independent | 4 | 1.3 | 2 |  | 2 |  |  | 8 | m2-LxH | ON HIRE | 2023-01-09 |  | 100% |  | 7.2857 | 14 | 0.84 | 112 | 6.72 | 78.4 | 0 | 48.96 | 127.36 | 100.48 | 26.88 |  |  | #VALUE! | 78.4 | #VALUE! | #VALUE!
| 1 | 1723 | 14308 | 8571 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 7.3 | 1 | 3.5 |  | 3.5 |  |  | 25.55 | m2-LxH | OFF HIRED | 2023-01-10 | 2023-02-17 | 100% |  | 5.5714 | 14 | 0.84 | 357.7 | 21.462 | 250.39 | 107.31 | 119.574 | 477.274 | 317.842 | 159.432 |  |  | #VALUE! | 432.67 | #VALUE! | #VALUE!
| 1 | 1723 | 14308 | 8571 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 9.3 | 1 | 2 |  | 2 |  |  | 18.6 | m2-LxH | OFF HIRED | 2023-01-10 | 2023-02-17 | 100% |  | 5.5714 | 14 | 0.84 | 260.4 | 15.624 | 182.28 | 78.12 | 87.048 | 347.448 | 231.384 | 116.064 |  |  | #VALUE! | 432.67 | #VALUE! | #VALUE!
| 1 | 1726 | 14311 | 8606 |  | Basement 1 Residence | Access Scaffold |  | Independent | 15 | 1 | 2 |  | 2 |  |  | 30 | m2-LxH | OFF HIRED | 2023-01-11 | 2023-01-25 | 100% |  | 2.1429 | 14 | 0.84 | 420 | 25.2 | 294 | 126 | 54 | 474 | 474 | 0
| 1 | 1726 | 14311 | 8606 |  | Basement 1 Residence | Access Scaffold |  | Independent | 4 | 1.3 | 2 |  | 2 |  |  | 8 | m2-LxH | OFF HIRED | 2023-01-11 | 2023-01-25 | 100% |  | 2.1429 | 14 | 0.84 | 112 | 6.72 | 78.4 | 33.6 | 14.4 | 126.4 | 126.4 | 0
| 1 | 1730 | 14315 |  |  | Basement 1 Hotel | Access Scaffold |  | Independent | 20 | 1.3 | 2 |  | 2 |  |  | 40 | m2-LxH | ON HIRE | 2023-01-12 |  | 100% |  | 6.8571 | 14 | 0.84 | 560 | 33.6 | 392 | 0 | 230.4 | 622.4 | 488 | 134.4 |  |  | #VALUE! | 943.25 | #VALUE! | #VALUE!
| 1 | 1734 | 14319 | 8571 |  | Basement 1 Residence | Access Scaffold |  | Independent | 6.5 | 1.3 | 2 |  | 2 |  |  | 13 | m2-LxH | OFF HIRED | 2023-01-13 | 2023-02-17 | 100% |  | 5.1429 | 14 | 0.84 | 182 | 10.92 | 127.4 | 54.6 | 56.16 | 238.16 | 157.04 | 81.12 |  |  | #VALUE! | 127.4 | #VALUE! | #VALUE!
| 1 | 1741 | 14326 | 8427 |  | Basement 1 Residence | Access Scaffold |  | Independent | 4.3 | 1.3 | 4 |  | 4 |  |  | 17.2 | m2-LxH | OFF HIRED | 2023-01-14 | 2023-01-16 | 100% |  | 0.42857 | 14 | 0.84 | 240.8 | 14.448 | 168.56 | 72.24 | 6.192 | 246.992 | 246.992 | 0
| 1 | 1739 | 14324 | 8581 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 4.3 | 1 | 3 |  | 3 |  |  | 12.9 | m2-LxH | OFF HIRED | 2023-01-14 | 2023-02-20 | 100% |  | 5.4286 | 14 | 0.84 | 180.6 | 10.836 | 126.42 | 54.18 | 58.824 | 239.424 | 154.284 | 85.14 |  |  | #VALUE! | 126.42 | #VALUE! | #VALUE!
| 1 | 1740 | 14327 | 8600 |  | Basement 2 Hotel | Access Scaffold |  | Independent | 4.3 | 1.3 | 3 |  | 3 |  |  | 12.9 | m2-LxH | OFF HIRED | 2023-01-14 | 2023-02-25 | 100% |  | 6.1429 | 14 | 0.84 | 180.6 | 10.836 | 126.42 | 54.18 | 66.564 | 247.164 | 154.284 | 92.88 |  |  | #VALUE! | 236.285 | #VALUE! | #VALUE!
| 1 | 1742 | 14328 | 8427 |  | Basement 1 Residence | Access Scaffold |  | Independent | 4.3 | 1.3 | 1.5 |  | 1.5 |  |  | 6.45 | m2-LxH | OFF HIRED | 2023-01-14 | 2023-01-16 | 100% |  | 0.42857 | 14 | 0.84 | 90.3 | 5.418 | 63.21 | 27.09 | 2.322 | 92.622 | 92.622 | 0
| 1 | 1742 | 14328 | 8427 |  | Basement 1 Residence | Access Scaffold |  | Independent | 4.3 | 0.6 | 4 |  | 4 |  |  | 17.2 | m2-LxH | OFF HIRED | 2023-01-14 | 2023-01-16 | 100% |  | 0.42857 | 14 | 0.84 | 240.8 | 14.448 | 168.56 | 72.24 | 6.192 | 246.992 | 246.992 | 0
| 1 | 1752 | 14338 | 8639 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 16.3 | 1.3 | 2 |  | 2 |  |  | 32.6 | m2-LxH | OFF HIRED | 2023-01-17 | 2023-02-07 | 100% |  | 3.1429 | 14 | 0.84 | 456.4 | 27.384 | 319.48 | 136.92 | 86.064 | 542.464 | 378.16 | 164.304 |  |  | #VALUE! | 319.48 | #VALUE! | #VALUE!
| 1 | 1758 | 14344 | 8561 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 14 | 1.3 | 2 |  | 2 |  |  | 28 | m2-LxH | OFF HIRED | 2023-01-18 | 2023-02-14 | 100% |  | 4 | 14 | 0.84 | 392 | 23.52 | 274.4 | 117.6 | 94.08 | 486.08 | 321.44 | 164.64 |  |  | #VALUE! | 274.4 | #VALUE! | #VALUE!
| 1 | 1761 | 14347 |  |  | Basement 1 Hotel | Access Scaffold |  | Independent | 7.5 | 1.3 | 2.5 |  | 2.5 |  |  | 18.75 | m2-LxH | ON HIRE | 2023-01-19 |  | 100% |  | 5.8571 | 14 | 0.84 | 262.5 | 15.75 | 183.75 | 0 | 92.25 | 276 | 213 | 63 |  |  | #VALUE! | 183.75 | #VALUE! | #VALUE!
| 8 | 1763 | 14349 | 8641 |  | Level 6 To 8 Residence | Access Scaffold |  | Independent | 20 | 1 | 2 |  | 2 |  |  | 40 | m2-LxH | OFF HIRED | 2023-01-19 | 2023-02-06 | 100% |  | 2.7143 | 14 | 0.84 | 560 | 33.6 | 392 | 168 | 91.2 | 651.2 | 454.4 | 196.8 |  |  | #VALUE! | 392 | #VALUE! | #VALUE!
| 1 | 1766 | 14352 |  |  | Basement 1 Hotel | Access Scaffold |  | Independent | 22 | 1.3 | 4 |  | 4 |  |  | 88 | m2-LxH | ON HIRE | 2023-01-19 |  | 100% |  | 5.8571 | 14 | 0.84 | 1232 | 73.92 | 862.4 | 0 | 432.96 | 1295.36 | 999.68 | 295.68 |  |  | #VALUE! | 862.4 | #VALUE! | #VALUE!
| 2 | 1769 | 14356 | 8627 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 5 | 1.3 | 2 |  | 2 |  |  | 10 | m2-LxH | OFF HIRED | 2023-01-20 | 2023-02-02 | 100% |  | 2 | 14 | 0.84 | 140 | 8.4 | 98 | 42 | 16.8 | 156.8 | 112.4 | 44.4 |  |  | #VALUE! | 98 | #VALUE! | #VALUE!
| 2 | 1770 | 14357 | 8622 |  | Ground floor Hotel | Access Scaffold |  | Independent | 16.8 | 1 | 2 |  | 2 |  |  | 33.6 | m2-LxH | OFF HIRED | 2023-01-20 | 2023-02-01 | 100% |  | 1.8571 | 14 | 0.84 | 470.4 | 28.224 | 329.28 | 141.12 | 52.416 | 522.816 | 377.664 | 145.152 |  |  | #VALUE! | 329.28 | #VALUE! | #VALUE!
| 1 | 1774 | 14362 | 8620 |  | Basement 1 Residence | Access Scaffold |  | Independent | 10 | 1.3 | 4 |  | 4 |  |  | 40 | m2-LxH | OFF HIRED | 2023-01-21 | 2023-02-01 | 100% |  | 1.7143 | 14 | 0.84 | 560 | 33.6 | 392 | 168 | 57.6 | 617.6 | 444.8 | 172.8 |  |  | #VALUE! | 392 | #VALUE! | #VALUE!
| 1 | 1785 | 14373 | 8567 |  | Basement 1 Residence | Access Scaffold |  | Independent | 9.5 | 1.3 | 3 |  | 3 |  |  | 28.5 | m2-LxH | OFF HIRED | 2023-01-22 | 2023-02-15 | 100% |  | 3.5714 | 14 | 0.84 | 399 | 23.94 | 279.3 | 119.7 | 85.5 | 484.5 | 313.5 | 171 |  |  | #VALUE! | 279.3 | #VALUE! | #VALUE!
| 10 | 1763A | 14374 | 8567 |  | Leevel 8 To 9 Residence | Access Scaffold |  | Independent | 26 | 1 | 2 |  | 2 |  |  | 52 | m2-LxH | OFF HIRED | 2023-01-22 | 2023-02-15 | 100% |  | 3.5714 | 14 | 0.84 | 728 | 43.68 | 509.6 | 218.4 | 156 | 884 | 572 | 312 |  |  | #VALUE! | 509.6 | #VALUE! | #VALUE!
| 1 | 1793 | 14382 |  |  | Basement 1 Residence | Access Scaffold |  | Independent | 5 | 1 | 3 |  | 3 |  |  | 15 | m2-LxH | ON HIRE | 2023-01-25 |  | 100% |  | 5 | 14 | 0.84 | 210 | 12.6 | 147 | 0 | 63 | 210 | 159.6 | 50.4 |  |  | #VALUE! | 147 | #VALUE! | #VALUE!
| 1 | 1751 | 14337 |  |  | Basement 1 Residence | Access Scaffold |  | Independent | 4 | 1.3 | 1.5 |  | 1.5 |  |  | 6 | m2-LxH | ON HIRE | 2023-01-16 |  | 100% |  | 6.2857 | 14 | 0.84 | 84 | 5.04 | 58.8 | 0 | 31.68 | 90.48 | 70.32 | 20.16 |  |  | #VALUE! | 113.988 | #VALUE! | #VALUE!
| 3 | 1777 | 14365 |  |  | Level 2 Hotel | Access Scaffold |  | Independent | 7.5 | 1.3 | 5.6 |  | 5.6 |  |  | 42 | m2-LxH | ON HIRE | 2023-01-21 |  | 100% |  | 5.5714 | 14 | 0.84 | 588 | 35.28 | 411.6 | 0 | 196.56 | 608.16 | 467.04 | 141.12 |  |  | #VALUE! | 457.5375 | #VALUE! | #VALUE!
| 6 | 1784 | 14368 | 8607 |  | Level 4 Hotel | Access Scaffold |  | Independent | 3 | 1 | 1 |  | 1 |  |  | 3 | m2-LxH | OFF HIRED | 2023-01-21 | 2023-01-25 | 100% |  | 0.71429 | 14 | 0.84 | 42 | 2.52 | 29.4 | 12.6 | 1.8 | 43.8 | 43.8 | 0
| 6 | 1784 | 14368 | 8607 |  | Level 4 Hotel | Access Scaffold |  | Independent | 3 | 1 | 1 |  | 1 |  |  | 3 | m2-LxH | OFF HIRED | 2023-01-21 | 2023-01-25 | 100% |  | 0.71429 | 14 | 0.84 | 42 | 2.52 | 29.4 | 12.6 | 1.8 | 43.8 | 43.8 | 0
| 1 | 1713 | 14298 | 8426 |  | Basement 1 Residence | Access Scaffold |  | Independent | 12 | 1.3 | 4 |  | 4 |  |  | 48 | m2-LxH | OFF HIRED | 2023-01-08 | 2023-01-14 | 100% |  | 1 | 14 | 0.84 | 672 | 40.32 | 470.4 | 201.6 | 40.32 | 712.32 | 712.32 | 0
| 1 | 1681 | 14266 | 8644 |  | Basement 1 Residence | Access Scaffold |  | Independent | 4 | 1.3 | 3 |  | 3 |  |  | 12 | m2-LxH | OFF HIRED | 2022-12-29 | 2023-02-07 | 100% |  | 5.8571 | 14 | 0.84 | 168 | 10.08 | 117.6 | 50.4 | 59.04 | 227.04 | 166.56 | 60.48 |  |  | #VALUE! | 264.6 | #VALUE! | #VALUE!
| 1 | 1684 | 14269 | 8491 |  | Basement 1 Residence | Access Scaffold |  | Independent | 7 | 1 | 4 |  | 4 |  |  | 28 | m2-LxH | OFF HIRED | 2022-12-30 | 2023-01-04 | 100% |  | 0.85714 | 14 | 0.84 | 392 | 23.52 | 274.4 | 117.6 | 20.16 | 412.16 | 412.16 | 0
| 1 | 1699 | 14284 | 8425 |  | Basement 1 Residence | Access Scaffold |  | Independent | 2.5 | 1.3 | 3.5 |  | 3.5 |  |  | 8.75 | m2-LxH | OFF HIRED | 2023-01-03 | 2023-01-14 | 100% |  | 1.7143 | 14 | 0.84 | 122.5 | 7.35 | 85.75 | 36.75 | 12.6 | 135.1 | 135.1 | 0
| 1 | 1725 | 14310 | 8429 |  | Basement 1 Residence | Access Scaffold |  | Independent | 13 | 1.3 | 3.5 |  | 3.5 |  |  | 45.5 | m2-LxH | OFF HIRED | 2023-01-11 | 2023-01-16 | 100% |  | 0.85714 | 14 | 0.84 | 637 | 38.22 | 445.9 | 191.1 | 32.76 | 669.76 | 669.76 | 0
| 31 | 1767 | 14354 |  |  | Levl 31 Residence | Access Scaffold |  | Independent | 4.3 | 1 | 1.5 |  | 1.5 |  |  | 6.45 | m2-LxH | ON HIRE | 2023-01-19 |  | 100% |  | 5.8571 | 14 | 0.84 | 90.3 | 5.418 | 63.21 | 0 | 31.734 | 94.944 | 73.272 | 21.672 |  |  | #VALUE! | 299.46 | #VALUE! | #VALUE!
| 1 | 1797 | 14386 | 8643 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 13.8 | 1 | 2 |  | 2 |  |  | 27.6 | m2-LxH | OFF HIRED | 2023-01-26 | 2023-02-07 | 100% |  | 1.8571 | 14 | 0.84 | 386.4 | 23.184 | 270.48 | 115.92 | 43.056 | 429.456 | 290.352 | 139.104 |  |  | #VALUE! | 439.53 | #VALUE! | #VALUE!
| 30 | 1798 | 14387 | 8626 |  | Level 30 Residence | Access Scaffold |  | Independent | 5 | 1 | 2 |  | 2 |  |  | 10 | m2-LxH | OFF HIRED | 2023-01-26 | 2023-02-02 | 100% |  | 1.1429 | 14 | 0.84 | 140 | 8.4 | 98 | 42 | 9.6 | 149.6 | 105.2 | 44.4 |  |  | #VALUE! | 98 | #VALUE! | #VALUE!
| 6 | 1796 | 14385 | 8625 |  | Leevel 4 Hotel | Access Scaffold |  | Independent | 4 | 1.3 | 1.5 |  | 1.5 |  |  | 6 | m2-LxH | OFF HIRED | 2023-01-26 | 2023-02-01 | 100% |  | 1 | 14 | 0.84 | 84 | 5.04 | 58.8 | 25.2 | 5.04 | 89.04 | 63.12 | 25.92 |  |  | #VALUE! | 58.8 | #VALUE! | #VALUE!
| 7 | 1800 | 14388 | 8625 |  | Level 5 Residence | Access Scaffold |  | Independent | 7.5 | 1.3 | 2 |  | 2 |  |  | 15 | m2-LxH | OFF HIRED | 2023-01-26 | 2023-02-01 | 100% |  | 1 | 14 | 0.84 | 210 | 12.6 | 147 | 63 | 12.6 | 222.6 | 157.8 | 64.8 |  |  | #VALUE! | 294 | #VALUE! | #VALUE!
| 7 | 1800 | 14388 | 8625 |  | Level 5 Residence | Access Scaffold |  | Independent | 7.5 | 1.3 | 2 |  | 2 |  |  | 15 | m2-LxH | OFF HIRED | 2023-01-26 | 2023-02-01 | 100% |  | 1 | 14 | 0.84 | 210 | 12.6 | 147 | 63 | 12.6 | 222.6 | 157.8 | 64.8 |  |  | #VALUE! | 294 | #VALUE! | #VALUE!
| 1 | 1799 | 14389 |  |  | Basement 1 Hotel | Access Scaffold |  | Independent | 14 | 1.3 | 2 |  | 2 |  |  | 28 | m2-LxH | ON HIRE | 2023-01-26 |  | 100% |  | 4.8571 | 14 | 0.84 | 392 | 23.52 | 274.4 | 0 | 114.24 | 388.64 | 294.56 | 94.08 |  |  | #VALUE! | 274.4 | #VALUE! | #VALUE!
| 9 | 1804 | 14393 | 8591 |  | Leevel 7 Hotel | Access Scaffold |  | Independent | 5 | 1.3 | 2 |  | 2 |  |  | 10 | m2-LxH | OFF HIRED | 2023-01-27 | 2023-02-21 | 100% |  | 3.7143 | 14 | 0.84 | 140 | 8.4 | 98 | 42 | 31.2 | 171.2 | 104 | 67.2 |  |  | #VALUE! | 98 | #VALUE! | #VALUE!
| 7 | 1806 | 14395 | 8553 |  | Level 5 Residence | Access Scaffold |  | Independent | 22 | 1.3 | 4 |  | 4 |  |  | 88 | m2-LxH | OFF HIRED | 2023-01-27 | 2023-02-10 | 100% |  | 2.1429 | 14 | 0.84 | 1232 | 73.92 | 862.4 | 369.6 | 158.4 | 1390.4 | 915.2 | 475.2 |  |  | #VALUE! | 1996.4 | #VALUE! | #VALUE!
| 2 | 1807 | 14396 | 8578 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 13 | 1.3 | 1 |  | 1 |  |  | 13 | m2-LxH | OFF HIRED | 2023-01-27 | 2023-02-20 | 100% |  | 3.5714 | 14 | 0.84 | 182 | 10.92 | 127.4 | 54.6 | 39 | 221 | 135.2 | 85.8 |  |  | #VALUE! | 127.4 | #VALUE! | #VALUE!
| 12 | 1808 | 14397 |  |  | Level 10 To 11 Residence | Access Scaffold |  | Independent | 21 | 1 | 2 |  | 2 |  |  | 42 | m2-LxH | ON HIRE | 2023-01-27 |  | 100% |  | 4.7143 | 14 | 0.84 | 588 | 35.28 | 411.6 | 0 | 166.32 | 577.92 | 436.8 | 141.12 |  |  | #VALUE! | 411.6 | #VALUE! | #VALUE!
| 1 | 1809 | 14398 | 8633 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 9.6 | 1.3 | 2.5 |  | 2.5 |  |  | 24 | m2-LxH | OFF HIRED | 2023-01-27 | 2023-02-03 | 100% |  | 1.1429 | 14 | 0.84 | 336 | 20.16 | 235.2 | 100.8 | 23.04 | 359.04 | 249.6 | 109.44 |  |  | #VALUE! | 235.2 | #VALUE! | #VALUE!
| 6 | 1813 | 14402 | 8618 |  | Level 4 Residence | Access Scaffold |  | Independent | 13 | 1.3 | 1 |  | 1 |  |  | 13 | m2-LxH | OFF HIRED | 2023-01-28 | 2023-01-30 | 100% |  | 0.42857 | 14 | 0.84 | 182 | 10.92 | 127.4 | 54.6 | 4.68 | 186.68 | 133.64 | 53.04 |  |  | #VALUE! | 127.4 | #VALUE! | #VALUE!
| 2 | 1811 | 14400 |  |  | Ground floor Hotel | Access Scaffold |  | Independent | 5 | 1.3 | 2 |  | 2 |  |  | 10 | m2-LxH | ON HIRE | 2023-01-27 |  | 100% |  | 4.7143 | 14 | 0.84 | 140 | 8.4 | 98 | 0 | 39.6 | 137.6 | 104 | 33.6 |  |  | #VALUE! | 98 | #VALUE! | #VALUE!
| 28 | 1814 | 14403 | 8594 |  | Level 28 Hotel | Access Scaffold |  | Independent | 4 | 1 | 2.5 |  | 2.5 |  |  | 10 | m2-LxH | OFF HIRED | 2023-01-28 | 2023-02-21 | 100% |  | 3.5714 | 14 | 0.84 | 140 | 8.4 | 98 | 42 | 30 | 170 | 102.8 | 67.2 |  |  | #VALUE! | 98 | #VALUE! | #VALUE!
| 1 | 1817 | 14405 |  |  | Basement 1 Residence | Access Scaffold |  | Independent | 19.5 | 1.3 | 2 |  | 2 |  |  | 39 | m2-LxH | ON HIRE | 2023-01-28 |  | 100% |  | 4.5714 | 14 | 0.84 | 546 | 32.76 | 382.2 | 0 | 149.76 | 531.96 | 400.92 | 131.04 |  |  | #VALUE! | 382.2 | #VALUE! | #VALUE!
| 7 | 1818 | 14406 | 8584 |  | Level 5 Residence | Access Scaffold |  | Independent | 26 | 1 | 4 |  | 4 |  |  | 104 | m2-LxH | OFF HIRED | 2023-01-28 | 2023-02-20 | 100% |  | 3.4286 | 14 | 0.84 | 1456 | 87.36 | 1019.2 | 436.8 | 299.52 | 1755.52 | 1069.12 | 686.4 |  |  | #VALUE! | 1019.2 | #VALUE! | #VALUE!
| 2 | 1820 | 14408 | 8617 |  | Ground Floor to Basement 1 Residence | Access Scaffold |  | Independent | 17 | 1.3 | 2.5 |  | 2.5 |  |  | 42.5 | m2-LxH | OFF HIRED | 2023-01-29 | 2023-01-30 | 100% |  | 0.28571 | 14 | 0.84 | 595 | 35.7 | 416.5 | 178.5 | 10.2 | 605.2 | 431.8 | 173.4 |  |  | #VALUE! | 416.5 | #VALUE! | #VALUE!
| 1 | 1802 | 14391 | 8645 |  | Basement 1 Residence | Access Scaffold |  | Independent | 12.3 | 1.3 | 4.5 |  | 4.5 |  |  | 55.35 | m2-LxH | OFF HIRED | 2023-01-26 | 2023-02-08 | 100% |  | 2 | 14 | 0.84 | 774.9 | 46.494 | 542.43 | 232.47 | 92.988 | 867.888 | 582.282 | 285.606 |  |  | #VALUE! | 719.8201 | #VALUE! | #VALUE!
| 1 | 1743 | 14329 | 8560 |  | Basement 1 Residence | Access Scaffold |  | Independent | 10 | 1.8 | 3.5 |  | 3.5 |  |  | 35 | m2-LxH | OFF HIRED | 2023-01-14 | 2023-02-14 | 100% |  | 4.5714 | 18 | 1.05 | 630 | 36.75 | 441 | 189 | 168 | 798 | 535.5 | 262.5 |  |  | #VALUE! | 1053.5 | #VALUE! | #VALUE!
| 1 | 1743 | 14329 | 8560 |  | Basement 1 Residence | Access Scaffold |  | Independent | 12.5 | 1.8 | 5 |  | 5 |  |  | 62.5 | m2-LxH | OFF HIRED | 2023-01-14 | 2023-02-14 | 100% |  | 4.5714 | 14 | 0.84 | 875 | 52.5 | 612.5 | 262.5 | 240 | 1115 | 747.5 | 367.5 |  |  | #VALUE! | 1053.5 | #VALUE! | #VALUE!
| 1 | 1727 | 14312 |  |  | Basement 1 Hotel | Access Scaffold |  | Independent | 4 | 1.8 | 6.5 |  | 6.5 |  |  | 26 | m2-LxH | ON HIRE | 2023-01-11 |  | 100% |  | 7 | 14 | 0.84 | 364 | 21.84 | 254.8 | 0 | 152.88 | 407.68 | 320.32 | 87.36 |  |  | #VALUE! | 254.8 | #VALUE! | #VALUE!
| 1 | 1718 | 14302 |  |  | Basement 1 Hotel | Access Scaffold |  | Independent | 5.6 | 1.8 | 2.5 |  | 2.5 |  |  | 14 | m2-LxH | ON HIRE | 2023-01-09 |  | 100% |  | 7.2857 | 14 | 0.84 | 196 | 11.76 | 137.2 | 0 | 85.68 | 222.88 | 175.84 | 47.04 |  |  | #VALUE! | 137.2 | #VALUE! | #VALUE!
| 1 | 1756 | 14342 | 8605 |  | Basement 1 Residence | Access Scaffold |  | Independent | 3.1 | 1.8 | 4 |  | 4 |  |  | 12.4 | m2-LxH | OFF HIRED | 2023-01-18 | 2023-01-25 | 100% |  | 1.1429 | 14 | 0.84 | 173.6 | 10.416 | 121.52 | 52.08 | 11.904 | 185.504 | 185.504 | 0
| 1 | 1757 | 14343 | 8604 |  | Basement 1 Residence | Access Scaffold |  | Independent | 6.8 | 1.8 | 5 |  | 5 |  |  | 34 | m2-LxH | OFF HIRED | 2023-01-18 | 2023-01-25 | 100% |  | 1.1429 | 14 | 0.84 | 476 | 28.56 | 333.2 | 142.8 | 32.64 | 508.64 | 508.64 | 0
| 1 | 1764 | 14350 | 8560 |  | Basement 1 Residence | Access Scaffold |  | Independent | 25 | 1.8 | 3.5 |  | 3.5 |  |  | 87.5 | m2-LxH | OFF HIRED | 2023-01-19 | 2023-02-14 | 100% |  | 3.8571 | 14 | 0.84 | 1225 | 73.5 | 857.5 | 367.5 | 283.5 | 1508.5 | 994 | 514.5 |  |  | #VALUE! | 857.5 | #VALUE! | #VALUE!
| 1 | 1786 | 14375 | 8615 |  | Basement 1 Residence | Access Scaffold |  | Independent | 9.3 | 1.8 | 3.5 |  | 3.5 |  |  | 32.55 | m2-LxH | OFF HIRED | 2023-01-23 | 2023-01-27 | 100% |  | 0.71429 | 14 | 0.84 | 455.7 | 27.342 | 318.99 | 136.71 | 19.53 | 475.23 | 475.23 | 0
| 27 | 1782 | 14370 | 8634 |  | Level 27 Residence | Access Scaffold |  | Independent | 3.6 | 1.8 | 2 |  | 2 |  |  | 7.2 | m2-LxH | OFF HIRED | 2023-01-21 | 2023-02-03 | 100% |  | 2 | 14 | 0.84 | 100.8 | 6.048 | 70.56 | 30.24 | 12.096 | 112.896 | 80.064 | 32.832 |  |  | #VALUE! | 70.56 | #VALUE! | #VALUE!
| 1 | 1750 | 14336 |  |  | Basement 1 Residence | Access Scaffold |  | Independent | 4 | 1.8 | 4 |  | 4 |  |  | 16 | m2-LxH | ON HIRE | 2023-01-16 |  | 100% |  | 6.2857 | 14 | 0.84 | 224 | 13.44 | 156.8 | 0 | 84.48 | 241.28 | 187.52 | 53.76 |  |  | #VALUE! | 534.8 | #VALUE! | #VALUE!
| 6 | 1780 | 14368 | 8607 |  | Level 4 Hotel | Access Scaffold |  | Independent | 4 | 1.8 | 2 |  | 2 |  |  | 8 | m2-LxH | OFF HIRED | 2023-01-21 | 2023-01-25 | 100% |  | 0.71429 | 14 | 0.84 | 112 | 6.72 | 78.4 | 33.6 | 4.8 | 116.8 | 116.8 | 0
| 1 | 1735 | 14320 |  |  | Basement 1 Hotel | Access Scaffold |  | Independent | 3.6 | 1.8 | 7 |  | 7 |  |  | 25.2 | m2-LxH | ON HIRE | 2023-01-13 |  | 100% |  | 6.7143 | 14 | 0.84 | 352.8 | 21.168 | 246.96 | 0 | 142.128 | 389.088 | 304.416 | 84.672 |  |  | #VALUE! | 280.0728 | #VALUE! | #VALUE!
| 1 | 1713 | 14298 | 8426 |  | Basedment 1 Residence | Access Scaffold |  | Independent | 5.5 | 1.8 | 4 |  | 4 |  |  | 22 | m2-LxH | OFF HIRED | 2023-01-08 | 2023-01-14 | 100% |  | 1 | 14 | 0.84 | 308 | 18.48 | 215.6 | 92.4 | 18.48 | 326.48 | 326.48 | 0
| 1 | 1681 | 14266 | 8644 |  | Basedment 1 Residence | Access Scaffold |  | Independent | 5 | 1.8 | 3 |  | 3 |  |  | 15 | m2-LxH | OFF HIRED | 2022-12-29 | 2023-02-07 | 100% |  | 5.8571 | 14 | 0.84 | 210 | 12.6 | 147 | 63 | 73.8 | 283.8 | 208.2 | 75.6 |  |  | #VALUE! | 264.6 | #VALUE! | #VALUE!
| 1 | 1699 | 14284 | 8425 |  | Basedment 1 Residence | Access Scaffold |  | Independent | 5 | 1.8 | 3 |  | 3 |  |  | 15 | m2-LxH | OFF HIRED | 2023-01-03 | 2023-01-14 | 100% |  | 1.7143 | 14 | 0.84 | 210 | 12.6 | 147 | 63 | 21.6 | 231.6 | 231.6 | 0
| 1 | 1746 | 14332 | 8614 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 3.1 | 2.5 | 4 |  | 4 |  |  | 31 | m3 | OFF HIRED | 2023-01-16 | 2023-01-27 | 100% |  | 1.7143 | 7.5 | 0.7 | 232.5 | 21.7 | 162.75 | 69.75 | 37.2 | 269.7 | 269.7 | 0
| 1 | 1675 | 14260 | 8414 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 3.5 | 3.1 | 4 |  | 4 |  |  | 43.4 | m3 | OFF HIRED | 2022-12-27 | 2023-01-11 | 100% |  | 2.2857 | 7.5 | 0.7 | 325.5 | 30.38 | 227.85 | 97.65 | 69.44 | 394.94 | 394.94 | 0
| 1 | 1709 | 14294 | 8410 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 3.5 |  | 3.5 |  |  | 21.875 | m3 | OFF HIRED | 2023-01-06 | 2023-01-10 | 100% |  | 0.71429 | 7.5 | 0.7 | 164.0625 | 15.3125 | 114.8437 | 49.2188 | 10.9375 | 175 | 175 | 0
| 1 | 1677 | 14262 | 8416 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 3.5 | 3.1 | 4 |  | 4 |  |  | 43.4 | m3 | OFF HIRED | 2022-12-28 | 2023-01-12 | 100% |  | 2.2857 | 7.5 | 0.7 | 325.5 | 30.38 | 227.85 | 97.65 | 69.44 | 394.94 | 394.94 | 0
| 1 | 1693 | 14278 | 8410 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 3.5 |  | 3.5 |  |  | 21.875 | m3 | OFF HIRED | 2023-01-02 | 2023-01-10 | 100% |  | 1.2857 | 7.5 | 0.7 | 164.0625 | 15.3125 | 114.8437 | 49.2188 | 19.6875 | 183.75 | 183.75 | 0
| 1 | 1706 | 14291 | 8415 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 4 |  | 4 |  |  | 25 | m3 | OFF HIRED | 2023-01-05 | 2023-01-11 | 100% |  | 1 | 7.5 | 0.7 | 187.5 | 17.5 | 131.25 | 56.25 | 17.5 | 205 | 205 | 0
| 1 | 1706 | 14291 | 8415 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 4 |  | 4 |  |  | 25 | m3 | OFF HIRED | 2023-01-05 | 2023-01-11 | 100% |  | 1 | 7.5 | 0.7 | 187.5 | 17.5 | 131.25 | 56.25 | 17.5 | 205 | 205 | 0
| 1 | 1703 | 14288 | 8589 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 5.8 | 4 | 1.5 |  | 1.5 |  |  | 34.8 | m3 | OFF HIRED | 2023-01-04 | 2023-02-21 | 100% |  | 7 | 7.5 | 0.7 | 261 | 24.36 | 182.7 | 78.3 | 170.52 | 431.52 | 280.14 | 151.38 |  |  | #VALUE! | 182.7 | #VALUE! | #VALUE!
| 1 | 1697 | 14282 | 8557 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 3.5 |  | 3.5 |  |  | 21.875 | m3 | OFF HIRED | 2023-01-03 | 2023-02-11 | 100% |  | 5.7143 | 7.5 | 0.7 | 164.0625 | 15.3125 | 114.8437 | 49.2188 | 87.5 | 251.5625 | 178.2812 | 73.2812 |  |  | #VALUE! | 114.8437 | #VALUE! | #VALUE!
| 1 | 1694 | 14279 | 8410 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 3.5 |  | 3.5 |  |  | 21.875 | m3 | OFF HIRED | 2023-01-02 | 2023-01-10 | 100% |  | 1.2857 | 7.5 | 0.7 | 164.0625 | 15.3125 | 114.8437 | 49.2188 | 19.6875 | 183.75 | 183.75 | 0
| 1 | 1720 | 14305 | 8645 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 4 |  | 4 |  |  | 25 | m3 | OFF HIRED | 2023-01-10 | 2023-02-08 | 100% |  | 4.2857 | 7.5 | 0.7 | 187.5 | 17.5 | 131.25 | 56.25 | 75 | 262.5 | 186.25 | 76.25 |  |  | #VALUE! | 131.25 | #VALUE! | #VALUE!
| 1 | 1722 | 14307 | 8649 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 3.1 | 2.5 | 4 |  | 4 |  |  | 31 | m3 | OFF HIRED | 2023-01-10 | 2023-02-09 | 100% |  | 4.4286 | 7.5 | 0.7 | 232.5 | 21.7 | 162.75 | 69.75 | 96.1 | 328.6 | 230.95 | 97.65 |  |  | #VALUE! | 162.75 | #VALUE! | #VALUE!
| 1 | 1731 | 14316 | 8427 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 4.5 |  | 4.5 |  |  | 28.125 | m3 | OFF HIRED | 2023-01-12 | 2023-01-16 | 100% |  | 0.71429 | 7.5 | 0.7 | 210.9375 | 19.6875 | 147.6562 | 63.2812 | 14.0625 | 225 | 225 | 0
| 1 | 1736 | 14323 | 8615 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 4.1 | 3.5 | 4 |  | 4 |  |  | 57.4 | m3 | OFF HIRED | 2023-01-14 | 2023-01-27 | 100% |  | 2 | 7.5 | 0.7 | 430.5 | 40.18 | 301.35 | 129.15 | 80.36 | 510.86 | 510.86 | 0
| 17 | 1753 | 14339 |  |  | Level 17 Hotel | Birdcage Scaffold |  | Birdcage | 9 | 6 | 2 |  | 2 |  |  | 108 | m3 | ON HIRE | 2023-01-17 |  | 100% |  | 6.1429 | 7.5 | 0.7 | 810 | 75.6 | 567 | 0 | 464.4 | 1031.4 | 729 | 302.4 |  |  | #VALUE! | 567 | #VALUE! | #VALUE!
| 1 | 1754 | 14340 | 8605 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 4 |  | 4 |  |  | 25 | m3 | OFF HIRED | 2023-01-17 | 2023-01-25 | 100% |  | 1.2857 | 7.5 | 0.7 | 187.5 | 17.5 | 131.25 | 56.25 | 22.5 | 210 | 210 | 0
| 2 | 1755 | 14341 |  |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 4.5 | 3 | 1 |  | 1 |  |  | 13.5 | m3 | ON HIRE | 2023-01-17 |  | 100% |  | 6.1429 | 7.5 | 0.7 | 101.25 | 9.45 | 70.875 | 0 | 58.05 | 128.925 | 91.125 | 37.8 |  |  | #VALUE! | 70.875 | #VALUE! | #VALUE!
| 1 | 1759 | 14346 | 8623 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 3.5 |  | 3.5 |  |  | 21.875 | m3 | OFF HIRED | 2023-01-19 | 2023-02-01 | 100% |  | 2 | 7.5 | 0.7 | 164.0625 | 15.3125 | 114.8437 | 49.2188 | 30.625 | 194.6875 | 143.2812 | 51.4063 |  |  | #VALUE! | 229.6875 | #VALUE! | #VALUE!
| 1 | 1759 | 14346 | 8623 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 3.5 |  | 3.5 |  |  | 21.875 | m3 | OFF HIRED | 2023-01-19 | 2023-02-01 | 100% |  | 2 | 7.5 | 0.7 | 164.0625 | 15.3125 | 114.8437 | 49.2188 | 30.625 | 194.6875 | 143.2812 | 51.4063 |  |  | #VALUE! | 229.6875 | #VALUE! | #VALUE!
| 2 | 1760 | 14345 | 8565 |  | Ground Floor Residence | Birdcage Scaffold |  | Birdcage | 10 | 4 | 3.5 |  | 3.5 |  |  | 140 | m3 | OFF HIRED | 2023-01-18 | 2023-02-15 | 100% |  | 4.1429 | 7.5 | 0.7 | 1050 | 98 | 735 | 315 | 406 | 1456 | 931 | 525 |  |  | #VALUE! | 735 | #VALUE! | #VALUE!
| 23 | 1762 | 14348 |  |  | Level 23 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 2.5 |  | 2.5 |  |  | 15.625 | m3 | ON HIRE | 2023-01-19 |  | 100% |  | 5.8571 | 7.5 | 0.7 | 117.1875 | 10.9375 | 82.0312 | 0 | 64.0625 | 146.0938 | 102.3438 | 43.75 |  |  | #VALUE! | 164.0625 | #VALUE! | #VALUE!
| 23 | 1762 | 14348 |  |  | Level 23 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 2.5 |  | 2.5 |  |  | 15.625 | m3 | ON HIRE | 2023-01-19 |  | 100% |  | 5.8571 | 7.5 | 0.7 | 117.1875 | 10.9375 | 82.0312 | 0 | 64.0625 | 146.0938 | 102.3438 | 43.75 |  |  | #VALUE! | 164.0625 | #VALUE! | #VALUE!
| 2 | 1771 | 14360 |  |  | Ground Floor Residence | Birdcage Scaffold |  | Birdcage | 6.8 | 3.1 | 3.5 |  | 3.5 |  |  | 73.78 | m3 | ON HIRE | 2023-01-20 |  | 100% |  | 5.7143 | 7.5 | 0.7 | 553.35 | 51.646 | 387.345 | 0 | 295.12 | 682.465 | 475.881 | 206.584 |  |  | #VALUE! | 387.345 | #VALUE! | #VALUE!
| 1 | 1773 | 14361 | 8638 |  | Basement 2 Residence | Birdcage Scaffold |  | Birdcage | 11.8 | 6.3 | 1.5 |  | 1.5 |  |  | 111.51 | m3 | OFF HIRED | 2023-01-20 | 2023-02-07 | 100% |  | 2.7143 | 7.5 | 0.7 | 836.325 | 78.057 | 585.4275 | 250.8975 | 211.869 | 1048.194 | 719.2395 | 328.9545 |  |  | #VALUE! | 585.4275 | #VALUE! | #VALUE!
| 1 | 1791 | 14380 | 8642 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 3.5 |  | 3.5 |  |  | 35 | m3 | OFF HIRED | 2023-01-24 | 2023-02-07 | 100% |  | 2.1429 | 7.5 | 0.7 | 262.5 | 24.5 | 183.75 | 78.75 | 52.5 | 315 | 211.75 | 103.25 |  |  | #VALUE! | 183.75 | #VALUE! | #VALUE!
| 1 | 1781 | 14369 |  |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 3.5 | 2.5 | 2 |  | 2 |  |  | 17.5 | m3 | ON HIRE | 2023-01-21 |  | 100% |  | 5.5714 | 7.5 | 0.7 | 131.25 | 12.25 | 91.875 | 0 | 68.25 | 160.125 | 111.125 | 49 |  |  | #VALUE! | 91.875 | #VALUE! | #VALUE!
| 1 | 1730 | 14315 |  |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 5 | 7 | 3 |  | 3 |  |  | 105 | m3 | ON HIRE | 2023-01-12 |  | 100% |  | 6.8571 | 7.5 | 0.7 | 787.5 | 73.5 | 551.25 | 0 | 504 | 1055.25 | 761.25 | 294 |  |  | #VALUE! | 943.25 | #VALUE! | #VALUE!
| 1 | 1792 | 14381 | 8633 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 6.3 | 2.5 | 4 |  | 4 |  |  | 63 | m3 | OFF HIRED | 2023-01-25 | 2023-02-03 | 100% |  | 1.4286 | 7.5 | 0.7 | 472.5 | 44.1 | 330.75 | 141.75 | 63 | 535.5 | 374.85 | 160.65 |  |  | #VALUE! | 330.75 | #VALUE! | #VALUE!
| 3 | 1794 | 14383 | 8559 |  | Level 2 Hotel | Birdcage Scaffold |  | Birdcage | 11 | 5 | 5 |  | 5 |  |  | 275 | m3 | OFF HIRED | 2023-01-25 | 2023-02-11 | 100% |  | 2.5714 | 7.5 | 0.7 | 2062.5 | 192.5 | 1443.75 | 618.75 | 495 | 2557.5 | 1636.25 | 921.25 |  |  | #VALUE! | 1673.7 | #VALUE! | #VALUE!
| 1 | 1787 | 14376 |  |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 3.5 |  | 3.5 |  |  | 21.875 | m3 | ON HIRE | 2023-01-23 |  | 100% |  | 5.2857 | 7.5 | 0.7 | 164.0625 | 15.3125 | 114.8437 | 0 | 80.9375 | 195.7812 | 134.5312 | 61.25 |  |  | #VALUE! | 142.4377 | #VALUE! | #VALUE!
| 1 | 1713 | 14298 | 8426 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 6.8 | 2.5 | 2.5 |  | 2.5 |  |  | 42.5 | m3 | OFF HIRED | 2023-01-08 | 2023-01-14 | 100% |  | 1 | 7.5 | 0.7 | 318.75 | 29.75 | 223.125 | 95.625 | 29.75 | 348.5 | 348.5 | 0
| 1 | 1725 | 14310 | 8429 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 3.5 |  | 3.5 |  |  | 21.875 | m3 | OFF HIRED | 2023-01-11 | 2023-01-16 | 100% |  | 0.85714 | 7.5 | 0.7 | 164.0625 | 15.3125 | 114.8437 | 49.2188 | 13.125 | 177.1875 | 177.1875 | 0
| 1 | 1797 | 14386 | 8643 |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 4 | 2.3 | 2 |  | 2 |  |  | 18.4 | m3 | OFF HIRED | 2023-01-26 | 2023-02-07 | 100% |  | 1.8571 | 7.5 | 0.7 | 138 | 12.88 | 96.6 | 41.4 | 23.92 | 161.92 | 107.64 | 54.28 |  |  | #VALUE! | 439.53 | #VALUE! | #VALUE!
| 7 | 1806 | 14395 | 8553 |  | Leevel 5 Residence | Birdcage Scaffold |  | Birdcage | 8 | 6 | 4.5 |  | 4.5 |  |  | 216 | m3 | OFF HIRED | 2023-01-27 | 2023-02-10 | 100% |  | 2.1429 | 7.5 | 0.7 | 1620 | 151.2 | 1134 | 486 | 324 | 1944 | 1242 | 702 |  |  | #VALUE! | 1996.4 | #VALUE! | #VALUE!
| 1 | 1802 | 14391 | 8645 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 3.5 |  | 3.5 |  |  | 21.875 | m3 | OFF HIRED | 2023-01-26 | 2023-02-08 | 100% |  | 2 | 7.5 | 0.7 | 164.0625 | 15.3125 | 114.8437 | 49.2188 | 30.625 | 194.6875 | 127.9687 | 66.7188 |  |  | #VALUE! | 719.8201 | #VALUE! | #VALUE!
| 1 | 1801 | 14390 |  |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 3.5 |  | 3.5 |  |  | 21.875 | m3 | ON HIRE | 2023-01-26 |  | 100% |  | 4.8571 | 7.5 | 0.7 | 164.0625 | 15.3125 | 114.8437 | 0 | 74.375 | 189.2187 | 127.9687 | 61.25 |  |  | #VALUE! | 537.5737 | #VALUE! | #VALUE!
| 1 | 1735 | 14320 |  |  | Basement 1 Hotel | Cantiliver |  | Cantiliver | 1.8 | 0.6 |  |  |  | 0.6 |  | 0.648 | m2-LxW | ON HIRE | 2023-01-13 |  | 100% |  | 6.7143 | 36.5 | 3.15 | 23.652 | 2.0412 | 16.5564 | 0 | 13.7052 | 30.2616 | 22.0968 | 8.1648 |  |  | #VALUE! | 280.0728 | #VALUE! | #VALUE!
| 1 | 1740 | 14327 | 8600 |  | Basement 2 Hotel | Cantiliver |  | Cantiliver | 4.3 | 1 |  |  |  | 1 |  | 4.3 | m2-LxW | OFF HIRED | 2023-01-14 | 2023-02-25 | 100% |  | 6.1429 | 36.5 | 3.15 | 156.95 | 13.545 | 109.865 | 47.085 | 83.205 | 240.155 | 144.695 | 95.46 |  |  | #VALUE! | 236.285 | #VALUE! | #VALUE!
| 6 | 1733 | 14318 | 8597 |  | Level 4 Residence | Cantiliver |  | Cantiliver | 1 | 1 |  |  |  | 1 |  | 1 | m2-LxW | OFF HIRED | 2023-01-13 | 2023-02-24 | 100% |  | 6.1429 | 36.5 | 3.15 | 36.5 | 3.15 | 25.55 | 10.95 | 19.35 | 55.85 | 34.1 | 21.75 |  |  | #VALUE! | 167.3 | #VALUE! | #VALUE!
| 28 | 1708 | 14293 | 8444 |  | Level 28 Hotel | Cantiliver |  | Cantiliver | 1 | 0.6 |  |  |  | 0.6 |  | 0.36 | m2-LxW | OFF HIRED | 2023-01-06 | 2023-01-20 | 100% |  | 2.1429 | 36.5 | 3.15 | 13.14 | 1.134 | 9.198 | 3.942 | 2.43 | 15.57 | 15.57 | 0
| 3 | 1692 | 14277 |  |  | Level 2 Hotel | Cantiliver |  | Cantiliver | 2.5 | 0.6 |  |  |  | 0.6 |  | 0.9 | m2-LxW | ON HIRE | 2022-12-31 |  | 100% |  | 8.5714 | 36.5 | 3.15 | 32.85 | 2.835 | 22.995 | 0 | 24.3 | 47.295 | 35.955 | 11.34 |  |  | #VALUE! | 589.995 | #VALUE! | #VALUE!
| 1 | 1684 | 14269 | 8491 |  | Basement 1 Residence | Cantiliver |  | Cantiliver | 1 | 1 |  |  |  | 1 |  | 1 | m2-LxW | OFF HIRED | 2022-12-30 | 2023-01-04 | 100% |  | 0.85714 | 36.5 | 3.15 | 36.5 | 3.15 | 25.55 | 10.95 | 2.7 | 39.2 | 39.2 | 0
| 1 | 1678 | 14263 |  |  | Basement 1Residence | Cantiliver |  | Cantiliver | 1.8 | 0.6 |  |  |  | 0.6 |  | 0.648 | m2-LxW | ON HIRE | 2022-12-28 |  | 100% |  | 9 | 36.5 | 3.15 | 23.652 | 2.0412 | 16.5564 | 0 | 18.3708 | 34.9272 | 26.7624 | 8.1648 |  |  | #VALUE! | 394.5564 | #VALUE! | #VALUE!
| 1 | 1784 | 14372 | 8605 |  | Basement 1Residence | Cantiliver |  | Cantiliver | 7.5 | 0.3 |  |  |  | 0.6 |  | 1.35 | m2-LxW | OFF HIRED | 2023-01-21 | 2023-01-25 | 100% |  | 0.71429 | 36.5 | 3.15 | 49.275 | 4.2525 | 34.4925 | 14.7825 | 3.0375 | 52.3125 | 52.3125 | 0
| 3 | 1788 | 14377 | 8621 |  | Level 2 Hotel | Cantiliver |  | Cantiliver | 2.5 | 0.6 |  |  |  | 0.6 |  | 0.9 | m2-LxW | OFF HIRED | 2023-01-23 | 2023-02-01 | 100% |  | 1.4286 | 36.5 | 3.15 | 32.85 | 2.835 | 22.995 | 9.855 | 4.05 | 36.9 | 26.64 | 10.26 |  |  | #VALUE! | 164.745 | #VALUE! | #VALUE!
| 1 | 1787 | 14376 |  |  | Basement 1 Residence | Cantiliver |  | Cantiliver | 3 | 0.6 |  |  |  | 0.6 |  | 1.08 | m2-LxW | ON HIRE | 2023-01-23 |  | 100% |  | 5.2857 | 36.5 | 3.15 | 39.42 | 3.402 | 27.594 | 0 | 17.982 | 45.576 | 31.968 | 13.608 |  |  | #VALUE! | 142.4377 | #VALUE! | #VALUE!
| 16 | 1751 | 14337 |  |  | Level 16 Hotel | Cantiliver |  | Cantiliver | 6 | 0.6 |  |  |  | 0.6 |  | 2.16 | m2-LxW | ON HIRE | 2023-01-16 |  | 100% |  | 6.2857 | 36.5 | 3.15 | 78.84 | 6.804 | 55.188 | 0 | 42.768 | 97.956 | 70.74 | 27.216 |  |  | #VALUE! | 113.988 | #VALUE! | #VALUE!
| 1 | 1735 | 14320 |  |  | Basement 1 Hotel | Cantiliver |  | Cantiliver | 1.8 | 0.6 |  |  |  | 0.6 |  | 0.648 | m2-LxW | ON HIRE | 2023-01-13 |  | 100% |  | 6.7143 | 36.5 | 3.15 | 23.652 | 2.0412 | 16.5564 | 0 | 13.7052 | 30.2616 | 22.0968 | 8.1648 |  |  | #VALUE! | 280.0728 | #VALUE! | #VALUE!
| 3 | 1794 | 14383 | 8559 |  | Level 2 Hotel | Cantiliver |  | Cantiliver | 4 | 1.5 |  |  |  | 1.5 |  | 9 | m2-LxW | OFF HIRED | 2023-01-25 | 2023-02-11 | 100% |  | 2.5714 | 36.5 | 3.15 | 328.5 | 28.35 | 229.95 | 98.55 | 72.9 | 401.4 | 258.3 | 143.1 |  |  | #VALUE! | 1673.7 | #VALUE! | #VALUE!
| 1 | 1810 | 14399 | 8633 |  | Basement 1 Residence | Cantiliver |  | Cantiliver | 2.5 | 0.6 |  |  |  | 0.6 |  | 0.9 | m2-LxW | OFF HIRED | 2023-01-27 | 2023-02-03 | 100% |  | 1.1429 | 36.5 | 3.15 | 32.85 | 2.835 | 22.995 | 9.855 | 3.24 | 36.09 | 25.02 | 11.07 |  |  | #VALUE! | 400.995 | #VALUE! | #VALUE!
| 1 | 1797 | 14386 | 8643 |  | Basement 1 Hotel | Cantiliver |  | Boardlift | 13.8 | 1 |  |  |  | 1 |  | 13.8 | m2-LxW | OFF HIRED | 2023-01-26 | 2023-02-07 | 100% |  | 1.8571 | 7.5 | 1.05 | 103.5 | 14.49 | 72.45 | 31.05 | 26.91 | 130.41 | 84.87 | 45.54 |  |  | #VALUE! | 439.53 | #VALUE! | #VALUE!
| 1 | 1802 | 14391 | 8645 |  | Basement 1 Residence | Cantiliver |  | Cantiliver | 6.8 | 0.6 |  |  |  | 0.6 |  | 2.448 | m2-LxW | OFF HIRED | 2023-01-26 | 2023-02-08 | 100% |  | 2 | 36.5 | 3.15 | 89.352 | 7.7112 | 62.5464 | 26.8056 | 15.4224 | 104.7744 | 69.156 | 35.6184 |  |  | #VALUE! | 719.8201 | #VALUE! | #VALUE!
| 1 | 1801 | 14390 |  |  | Basement 1 Residence | Cantiliver |  | Cantiliver | 2.5 | 1.2 |  |  |  | 1.2 |  | 3.6 | m2-LxW | ON HIRE | 2023-01-26 |  | 100% |  | 4.8571 | 36.5 | 3.15 | 131.4 | 11.34 | 91.98 | 0 | 55.08 | 147.06 | 101.7 | 45.36 |  |  | #VALUE! | 537.5737 | #VALUE! | #VALUE!
| 3 | 1777 | 14365 |  |  | Level 2 Hotel | Support Tower |  | Buttress | 2.5 | 2.5 | 2 |  | 2 |  |  | 12.5 | m3 | ON HIRE | 2023-01-21 |  | 100% |  | 5.5714 | 5.25 | 0.35 | 65.625 | 4.375 | 45.9375 | 0 | 24.375 | 70.3125 | 52.8125 | 17.5 |  |  | #VALUE! | 457.5375 | #VALUE! | #VALUE!
| 3 | 1772 | 14358 |  |  | Level 2 to Level 6 Zone 4 Hotel | Chain Pully |  | Independent | 10 | 1.3 | 17 |  | 17 |  |  | 170 | m2-LxH | ON HIRE | 2023-01-20 |  | 100% |  | 5.7143 | 14 | 0.84 | 2380 | 142.8 | 1666 | 0 | 816 | 2482 | 1910.8 | 571.2 |  |  | #VALUE! | 3411.625 | #VALUE! | #VALUE!
| 3 | 1772 | 14358 |  |  | Level 2 to Level 6 Zone 4 Hotel | Chain Pully |  | Buttress | 10 | 2.5 | 4.5 |  | 4.5 |  |  | 112.5 | m3 | ON HIRE | 2023-01-20 |  | 100% |  | 5.7143 | 5.25 | 0.35 | 590.625 | 39.375 | 413.4375 | 0 | 225 | 638.4375 | 480.9375 | 157.5 |  |  | #VALUE! | 3411.625 | #VALUE! | #VALUE!
| 3 | 1772 | 14358 |  |  | Level 2 to Level 6 Zone 4 Hotel | Chain Pully |  | Buttress | 10 | 2.5 | 14.5 |  | 14.5 |  |  | 362.5 | m3 | ON HIRE | 2023-01-20 |  | 100% |  | 5.7143 | 5.25 | 0.35 | 1903.125 | 126.875 | 1332.1875 | 0 | 725 | 2057.1875 | 1549.6875 | 507.5 |  |  | #VALUE! | 3411.625 | #VALUE! | #VALUE!
| 3 | 1772 A | 14359 |  |  | Level 2 to Level 6 Zone 4 Hotel | Chain Pully With Ladder Beam |  | Independent | 3 | 5 |  |  |  | 1 |  | 15 | m2-LxW | ON HIRE | 2023-01-20 |  | 100% |  | 5.7143 | 81 | 1.82 | 1215 | 27.3 | 850.5 | 0 | 156 | 1006.5 | 897.3 | 109.2 |  |  | #VALUE! | 1530.9 | #VALUE! | #VALUE!
| 3 | 1772 A | 14359 |  |  | Level 2 to Level 6 Zone 4 Hotel | Chain Pully With Ladder Beam |  | Independent | 6 | 2 |  |  |  | 1 |  | 12 | m2-LxW | ON HIRE | 2023-01-20 |  | 100% |  | 5.7143 | 81 | 1.82 | 972 | 21.84 | 680.4 | 0 | 124.8 | 805.2 | 717.84 | 87.36 |  |  | #VALUE! | 1530.9 | #VALUE! | #VALUE!
|  | 1765 |  |  |  |  | SHAFT SCAFFOLDING |  | Shaft |  |  | 10 |  | 10 |  |  | 10 | rm | ON HIRE | 2023-01-19 |  | 100% |  | 5.8571 | 63 | 7.14 | 630 | 71.4 | 441 | 0 | 418.2 | 859.2 | 573.6 | 285.6 |  |  | #VALUE! | 0 | #VALUE! | #VALUE!
[37 empty] | #VALUE! | 0 | #VALUE! | #VALUE!
|  | 1961 | 14549 |  |  | Level 13 Hotel | Mobile Tower |  | Mobile Tower | 2.5 | 1.3 | 4.5 |  | 4.5 |  |  | 4.5 | rm | ON HIRE | 2023-02-23 |  | 100% |  | 0.85714 | 100 | 10.15 | 450 | 45.675 | 315 | 0 | 39.15 | 354.15 |  | 354.15 |  |  | #VALUE! | 315 | #VALUE! | #VALUE!
|  | 1831 | 14418 | 8632 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 4.5 |  | 4.5 |  |  | 4.5 | rm | OFF HIRED | 2023-01-31 | 2023-02-04 | 100% |  | 0.71429 | 135 | 12.25 | 607.5 | 55.125 | 425.25 | 182.25 | 39.375 | 646.875 |  | 646.875 |  |  | #VALUE! | 425.25 | #VALUE! | #VALUE!
|  | 1833 | 14420 | 8630 |  | Level 18 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2023-02-01 | 2023-02-02 | 100% |  | 0.28571 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 8.75 | 346.25 |  | 346.25 |  |  | #VALUE! | 708.75 | #VALUE! | #VALUE!
|  | 1833 A | 14420 | 8630 |  | Level 18 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2023-02-01 | 2023-02-02 | 100% |  | 0.28571 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 8.75 | 346.25 |  | 346.25 |  |  | #VALUE! | 708.75 | #VALUE! | #VALUE!
|  | 1834 | 14420 | 8630 |  | Level 18 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2023-02-01 | 2023-02-02 | 100% |  | 0.28571 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 8.75 | 346.25 |  | 346.25 |  |  | #VALUE! | 708.75 | #VALUE! | #VALUE!
|  | 1845 | 14431 |  |  | Level 18 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | ON HIRE | 2023-02-02 |  | 100% |  | 3.8571 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 0 | 118.125 | 354.375 |  | 354.375 |  |  | #VALUE! | 236.25 | #VALUE! | #VALUE!
|  | 1846 | 14432 |  |  | Level 18 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | ON HIRE | 2023-02-02 |  | 100% |  | 3.8571 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 0 | 118.125 | 354.375 |  | 354.375 |  |  | #VALUE! | 236.25 | #VALUE! | #VALUE!
|  | 1842 | 14428 |  |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.8 | 3 |  | 3 |  |  | 3 | rm | ON HIRE | 2023-02-02 |  | 100% |  | 3.8571 | 135 | 12.25 | 405 | 36.75 | 283.5 | 0 | 141.75 | 425.25 |  | 425.25 |  |  | #VALUE! | 283.5 | #VALUE! | #VALUE!
|  | 1848 | 14434 |  |  | Ground Floor Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 5.5 |  | 5.5 |  |  | 5.5 | rm | ON HIRE | 2023-02-02 |  | 100% |  | 3.8571 | 135 | 12.25 | 742.5 | 67.375 | 519.75 | 0 | 259.875 | 779.625 |  | 779.625 |  |  | #VALUE! | 519.75 | #VALUE! | #VALUE!
|  | 1859 | 14444 | 8577 |  | Level 28 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 2 |  | 2 |  |  | 2 | rm | OFF HIRED | 2023-02-04 | 2023-02-20 | 100% |  | 2.4286 | 135 | 12.25 | 270 | 24.5 | 189 | 81 | 59.5 | 329.5 |  | 329.5 |  |  | #VALUE! | 189 | #VALUE! | #VALUE!
|  | 1862 | 14446 |  |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3.5 |  | 3.5 |  |  | 3.5 | rm | ON HIRE | 2023-02-04 |  | 100% |  | 3.5714 | 135 | 12.25 | 472.5 | 42.875 | 330.75 | 0 | 153.125 | 483.875 |  | 483.875 |  |  | #VALUE! | 330.75 | #VALUE! | #VALUE!
|  | 1865 | 14450 | 8587 |  | Level 18 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2023-02-04 | 2023-02-21 | 100% |  | 2.5714 | 135 | 12.25 | 540 | 49 | 378 | 162 | 126 | 666 |  | 666 |  |  | #VALUE! | 378 | #VALUE! | #VALUE!
|  | 1887 | 14472 |  |  | Level 3 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 0.6 | 1.5 |  | 1.5 |  |  | 1.5 | rm | ON HIRE | 2023-02-09 |  | 100% |  | 2.8571 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 0 | 52.5 | 194.25 |  | 194.25 |  |  | #VALUE! | 141.75 | #VALUE! | #VALUE!
|  | 1908 | 14493 | 8563 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | OFF HIRED | 2023-02-11 | 2023-02-13 | 100% |  | 0.42857 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 101.25 | 13.125 | 350.625 |  | 350.625 |  |  | #VALUE! | 236.25 | #VALUE! | #VALUE!
|  | 1907 | 14492 |  |  | Level 17 Hotel | HEAVY DUTY TOWER |  | Tower | 1.8 | 1 | 1.5 |  | 1.5 |  |  | 1.5 | rm | ON HIRE | 2023-02-11 |  | 100% |  | 2.5714 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 0 | 47.25 | 189 |  | 189 |  |  | #VALUE! | 141.75 | #VALUE! | #VALUE!
|  | 1915 | 14500 | 8570 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 1.5 |  | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2023-02-11 | 2023-02-17 | 100% |  | 1 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 60.75 | 18.375 | 220.875 |  | 220.875 |  |  | #VALUE! | 141.75 | #VALUE! | #VALUE!
|  | 1864 | 14449 | 8562 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 5.5 |  | 5.5 |  |  | 5.5 | rm | OFF HIRED | 2023-02-04 | 2023-02-13 | 100% |  | 1.4286 | 135 | 12.25 | 742.5 | 67.375 | 519.75 | 222.75 | 96.25 | 838.75 |  | 838.75 |  |  | #VALUE! | 519.75 | #VALUE! | #VALUE!
|  | 1890 | 14473 |  |  | Basement 1 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 2.5 | 3 |  | 3 |  |  | 3 | rm | ON HIRE | 2023-02-09 |  | 100% |  | 2.8571 | 135 | 12.25 | 405 | 36.75 | 283.5 | 0 | 105 | 388.5 |  | 388.5 |  |  | #VALUE! | 342.3 | #VALUE! | #VALUE!
|  | 1869 | 14454 | 8587 |  | Level 18 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 3.5 |  | 3.5 |  |  | 3.5 | rm | OFF HIRED | 2023-02-06 | 2023-02-21 | 100% |  | 2.2857 | 135 | 12.25 | 472.5 | 42.875 | 330.75 | 141.75 | 98 | 570.5 |  | 570.5 |  |  | #VALUE! | 369.075 | #VALUE! | #VALUE!
|  | 1954 | 14542 |  |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 3.5 |  | 3.5 |  |  | 3.5 | rm | ON HIRE | 2023-02-22 |  | 100% |  | 1 | 135 | 12.25 | 472.5 | 42.875 | 330.75 | 0 | 42.875 | 373.625 |  | 373.625 |  |  | #VALUE! | 330.75 | #VALUE! | #VALUE!
|  | 1949 | 14537 |  |  | Basement 2 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 1.5 |  | 1.5 |  |  | 1.5 | rm | ON HIRE | 2023-02-21 |  | 100% |  | 1.1429 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 0 | 21 | 162.75 |  | 162.75 |  |  | #VALUE! | 141.75 | #VALUE! | #VALUE!
|  | 1948 | 14536 |  |  | Ground Floor Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 4 |  | 4 |  |  | 4 | rm | ON HIRE | 2023-02-21 |  | 100% |  | 1.1429 | 135 | 12.25 | 540 | 49 | 378 | 0 | 56 | 434 |  | 434 |  |  | #VALUE! | 378 | #VALUE! | #VALUE!
|  | 1947 | 14535 |  |  | Ground Floor Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 4 |  | 4 |  |  | 4 | rm | ON HIRE | 2023-02-21 |  | 100% |  | 1.1429 | 135 | 12.25 | 540 | 49 | 378 | 0 | 56 | 434 |  | 434 |  |  | #VALUE! | 378 | #VALUE! | #VALUE!
|  | 1936 | 14524 | 8582 |  | Ground Floor Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3.5 |  | 3.5 |  |  | 3.5 | rm | OFF HIRED | 2023-02-18 | 2023-02-20 | 100% |  | 0.42857 | 135 | 12.25 | 472.5 | 42.875 | 330.75 | 141.75 | 18.375 | 490.875 |  | 490.875 |  |  | #VALUE! | 330.75 | #VALUE! | #VALUE!
|  | 1935 | 14523 | 8581 |  | Ground Floor Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 4 |  | 4 |  |  | 4 | rm | OFF HIRED | 2023-02-18 | 2023-02-20 | 100% |  | 0.42857 | 135 | 12.25 | 540 | 49 | 378 | 162 | 21 | 561 |  | 561 |  |  | #VALUE! | 378 | #VALUE! | #VALUE!
|  | 1937 | 14525 | 8582 |  | Ground Floor Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3.5 |  | 3.5 |  |  | 3.5 | rm | OFF HIRED | 2023-02-18 | 2023-02-20 | 100% |  | 0.42857 | 135 | 12.25 | 472.5 | 42.875 | 330.75 | 141.75 | 18.375 | 490.875 |  | 490.875 |  |  | #VALUE! | 330.75 | #VALUE! | #VALUE!
|  | 1893 | 14478 |  |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 4 |  | 4 |  |  | 4 | rm | ON HIRE | 2023-02-09 |  | 100% |  | 2.8571 | 135 | 12.25 | 540 | 49 | 378 | 0 | 140 | 518 |  | 518 |  |  | #VALUE! | 378 | #VALUE! | #VALUE!
|  | 1911 | 14496 | 8583 |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 1.5 |  | 1.5 |  |  | 1.5 | rm | OFF HIRED | 2023-02-11 | 2023-02-20 | 100% |  | 1.4286 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 60.75 | 26.25 | 228.75 |  | 228.75 |  |  | #VALUE! | 141.75 | #VALUE! | #VALUE!
|  | 1921 | 14509 |  |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 2.5 | rm | ON HIRE | 2023-02-13 |  | 100% |  | 2.2857 | 135 | 12.25 | 337.5 | 30.625 | 236.25 | 0 | 70 | 306.25 |  | 306.25 |  |  | #VALUE! | 236.25 | #VALUE! | #VALUE!
|  | 1920 | 14508 |  |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4 |  | 4 |  |  | 4 | rm | ON HIRE | 2023-02-13 |  | 100% |  | 2.2857 | 135 | 12.25 | 540 | 49 | 378 | 0 | 112 | 490 |  | 490 |  |  | #VALUE! | 378 | #VALUE! | #VALUE!
|  | 1928 | 14516 |  |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 4.5 |  | 4.5 |  |  | 4.5 | rm | ON HIRE | 2023-02-16 |  | 100% |  | 1.8571 | 135 | 12.25 | 607.5 | 55.125 | 425.25 | 0 | 102.375 | 527.625 |  | 527.625 |  |  | #VALUE! | 425.25 | #VALUE! | #VALUE!
|  | 1930 | 14518 |  |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 1.5 |  | 1.5 |  |  | 1.5 | rm | ON HIRE | 2023-02-16 |  | 100% |  | 1.8571 | 135 | 12.25 | 202.5 | 18.375 | 141.75 | 0 | 34.125 | 175.875 |  | 175.875 |  |  | #VALUE! | 141.75 | #VALUE! | #VALUE!
|  | 1931 | 14519 |  |  | Basement 1 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 3 |  | 3 |  |  | 3 | rm | ON HIRE | 2023-02-16 |  | 100% |  | 1.8571 | 135 | 12.25 | 405 | 36.75 | 283.5 | 0 | 68.25 | 351.75 |  | 351.75 |  |  | #VALUE! | 283.5 | #VALUE! | #VALUE!
|  | 1962 | 14550 |  |  | Level 28 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 4 |  | 4 |  |  | 4 | rm | ON HIRE | 2023-02-23 |  | 100% |  | 0.85714 | 135 | 12.25 | 540 | 49 | 378 | 0 | 42 | 420 |  | 420 |  |  | #VALUE! | 509.25 | #VALUE! | #VALUE!
|  | 1951 | 14539 |  |  | Level 2 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 6 |  | 6 |  |  | 6 | rm | ON HIRE | 2023-02-21 |  | 100% |  | 1.1429 | 135 | 12.25 | 810 | 73.5 | 567 | 0 | 84 | 651 |  | 651 |  |  | #VALUE! | 586.929 | #VALUE! | #VALUE!
|  | 1980 | 14618 |  |  | Level 28 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 3.5 |  | 3.5 |  |  | 3.5 | rm | ON HIRE | 2023-02-25 |  | 100% |  | 0.57143 | 135 | 12.25 | 472.5 | 42.875 | 330.75 | 0 | 24.5 | 355.25 |  | 355.25 |  |  | #VALUE! | 330.75 | #VALUE! | #VALUE!
|  | 1982 | 14620 |  |  | Basement 1 Hotel | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.8 | 2 |  | 2 |  |  | 2 | rm | ON HIRE | 2023-02-25 |  | 100% |  | 0.57143 | 135 | 12.25 | 270 | 24.5 | 189 | 0 | 14 | 203 |  | 203 |  |  | #VALUE! | 189 | #VALUE! | #VALUE!
|  | 1983 | 14621 |  |  | Basement 1 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1 | 3 |  | 3 |  |  | 3 | rm | ON HIRE | 2023-02-25 |  | 100% |  | 0.57143 | 135 | 12.25 | 405 | 36.75 | 283.5 | 0 | 21 | 304.5 |  | 304.5 |  |  | #VALUE! | 550.06 | #VALUE! | #VALUE!
|  | 1992 | 14630 |  |  | Ground Floor Residence | HEAVY DUTY TOWER |  | Tower | 1.8 | 1.3 | 4 |  | 4 |  |  | 4 | rm | ON HIRE | 2023-02-27 |  | 100% |  | 0.28571 | 135 | 12.25 | 540 | 49 | 378 | 0 | 14 | 392 |  | 392 |  |  | #VALUE! | 378 | #VALUE! | #VALUE!
|  | 1986 | 14624 |  |  | Level 28 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1.3 | 2 |  | 2 |  |  | 2 | rm | ON HIRE | 2023-02-26 |  | 100% |  | 0.42857 | 135 | 12.25 | 270 | 24.5 | 189 | 0 | 10.5 | 199.5 |  | 199.5 |  |  | #VALUE! | 567 | #VALUE! | #VALUE!
|  | 1986 | 14624 |  |  | Level 28 Hotel | HEAVY DUTY TOWER |  | Tower | 1.3 | 1 | 4 |  | 4 |  |  | 4 | rm | ON HIRE | 2023-02-26 |  | 100% |  | 0.42857 | 135 | 12.25 | 540 | 49 | 378 | 0 | 21 | 399 |  | 399 |  |  | #VALUE! | 567 | #VALUE! | #VALUE!
|  | 1997 | 14635 |  |  | Level 3 Residence | HEAVY DUTY TOWER |  | Tower | 2.5 | 1.3 | 1 |  | 1 |  |  | 1 | rm | ON HIRE | 2023-02-28 |  | 100% |  | 0.14286 | 135 | 12.25 | 135 | 12.25 | 94.5 | 0 | 1.75 | 96.25 |  | 96.25 |  |  | #VALUE! | 94.5 | #VALUE! | #VALUE!
|  | 1829 | 14416 | 8552 |  | Level 28 Hotel | Access Scaffold |  | Independent | 6.5 | 1.3 | 3.5 |  | 3.5 |  |  | 22.75 | m2-LxH | OFF HIRED | 2023-01-31 | 2023-02-10 | 100% |  | 1.5714 | 14 | 0.84 | 318.5 | 19.11 | 222.95 | 95.55 | 30.03 | 348.53 |  | 348.53 |  |  | #VALUE! | 222.95 | #VALUE! | #VALUE!
|  | 1827 | 14415 |  |  | Level 18 Hotel | Access Scaffold |  | Independent | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 6.25 | m2-LxH | ON HIRE | 2023-01-31 |  | 100% |  | 4.1429 | 14 | 0.84 | 87.5 | 5.25 | 61.25 | 0 | 21.75 | 83 |  | 83 |  |  | #VALUE! | 183.75 | #VALUE! | #VALUE!
|  | 1827 | 14415 |  |  | Level 18 Hotel | Access Scaffold |  | Independent | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 6.25 | m2-LxH | ON HIRE | 2023-01-31 |  | 100% |  | 4.1429 | 14 | 0.84 | 87.5 | 5.25 | 61.25 | 0 | 21.75 | 83 |  | 83 |  |  | #VALUE! | 183.75 | #VALUE! | #VALUE!
|  | 1828 | 14415 |  |  | Level 18 Hotel | Access Scaffold |  | Independent | 2.5 | 1.3 | 2.5 |  | 2.5 |  |  | 6.25 | m2-LxH | ON HIRE | 2023-01-31 |  | 100% |  | 4.1429 | 14 | 0.84 | 87.5 | 5.25 | 61.25 | 0 | 21.75 | 83 |  | 83 |  |  | #VALUE! | 183.75 | #VALUE! | #VALUE!
|  | 1826 | 14414 |  |  | Level 17 To 21 Hotel | Access Scaffold |  | Independent | 50 | 1 | 1.5 |  | 1.5 |  |  | 75 | m2-LxH | ON HIRE | 2023-01-31 |  | 100% |  | 4.1429 | 14 | 0.84 | 1050 | 63 | 735 | 0 | 261 | 996 |  | 996 |  |  | #VALUE! | 735 | #VALUE! | #VALUE!
|  | 1825 | 14413 |  |  | Leevel 7 To 9 Hotel | Access Scaffold |  | Independent | 28 | 1 | 1.5 |  | 1.5 |  |  | 42 | m2-LxH | ON HIRE | 2023-01-31 |  | 100% |  | 4.1429 | 14 | 0.84 | 588 | 35.28 | 411.6 | 0 | 146.16 | 557.76 |  | 557.76 |  |  | #VALUE! | 411.6 | #VALUE! | #VALUE!
|  | 1824 | 14412 | 8627 |  | Ground Floor Residence | Access Scaffold |  | Independent | 21.5 | 1 | 1.5 |  | 1.5 |  |  | 32.25 | m2-LxH | OFF HIRED | 2023-01-31 | 2023-02-02 | 100% |  | 0.42857 | 14 | 0.84 | 451.5 | 27.09 | 316.05 | 135.45 | 11.61 | 463.11 |  | 463.11 |  |  | #VALUE! | 316.05 | #VALUE! | #VALUE!
|  | 1823 | 14411 |  |  | Level 7 Hotel | Access Scaffold |  | Independent | 5 | 1 | 1.5 |  | 1.5 |  |  | 7.5 | m2-LxH | ON HIRE | 2023-01-31 |  | 100% |  | 4.1429 | 14 | 0.84 | 105 | 6.3 | 73.5 | 0 | 26.1 | 99.6 |  | 99.6 |  |  | #VALUE! | 73.5 | #VALUE! | #VALUE!
|  | 1830 | 14417 |  |  | Level 29 Hoel | Access Scaffold |  | Independent | 7.5 | 1.3 | 1.5 |  | 1.5 |  |  | 11.25 | m2-LxH | ON HIRE | 2023-01-31 |  | 100% |  | 4.1429 | 14 | 0.84 | 157.5 | 9.45 | 110.25 | 0 | 39.15 | 149.4 |  | 149.4 |  |  | #VALUE! | 110.25 | #VALUE! | #VALUE!
|  | 1891 | 14476 | 8570 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 5 | 0.6 | 2.5 |  | 2.5 |  |  | 12.5 | m2-LxH | OFF HIRED | 2023-02-09 | 2023-02-17 | 100% |  | 1.2857 | 14 | 0.84 | 175 | 10.5 | 122.5 | 52.5 | 13.5 | 188.5 |  | 188.5 |  |  | #VALUE! | 122.5 | #VALUE! | #VALUE!
|  | 1902 | 14487 |  |  | Level 4 Residence | Access Scaffold |  | Independent | 4.3 | 1 | 2 |  | 2 |  |  | 8.6 | m2-LxH | ON HIRE | 2023-02-10 |  | 100% |  | 2.7143 | 14 | 0.84 | 120.4 | 7.224 | 84.28 | 0 | 19.608 | 103.888 |  | 103.888 |  |  | #VALUE! | 84.28 | #VALUE! | #VALUE!
|  | 1914 | 14499 |  |  | Basement 1 Residence | Access Scaffold |  | Independent | 8 | 1.3 | 1.5 |  | 1.5 |  |  | 12 | m2-LxH | ON HIRE | 2023-02-11 |  | 100% |  | 2.5714 | 14 | 0.84 | 168 | 10.08 | 117.6 | 0 | 25.92 | 143.52 |  | 143.52 |  |  | #VALUE! | 117.6 | #VALUE! | #VALUE!
|  | 1901 | 14486 |  |  | Level 5 Hotel | Access Scaffold |  | Independent | 9.6 | 1.3 | 2 |  | 2 |  |  | 19.2 | m2-LxH | ON HIRE | 2023-02-10 |  | 100% |  | 2.7143 | 14 | 0.84 | 268.8 | 16.128 | 188.16 | 0 | 43.776 | 231.936 |  | 231.936 |  |  | #VALUE! | 188.16 | #VALUE! | #VALUE!
|  | 1905 | 14490 |  |  | Level 28 Hotel | Access Scaffold |  | Independent | 7.4 | 1.3 | 2 |  | 2 |  |  | 14.8 | m2-LxH | ON HIRE | 2023-02-11 |  | 100% |  | 2.5714 | 14 | 0.84 | 207.2 | 12.432 | 145.04 | 0 | 31.968 | 177.008 |  | 177.008 |  |  | #VALUE! | 145.04 | #VALUE! | #VALUE!
|  | 1904 | 14489 |  |  | Level 3 Residence | Access Scaffold |  | Independent | 7.8 | 1.3 | 1.5 |  | 1.5 |  |  | 11.7 | m2-LxH | ON HIRE | 2023-02-11 |  | 100% |  | 2.5714 | 14 | 0.84 | 163.8 | 9.828 | 114.66 | 0 | 25.272 | 139.932 |  | 139.932 |  |  | #VALUE! | 114.66 | #VALUE! | #VALUE!
|  | 1900 | 14485 |  |  | Level 17 Hotel | Access Scaffold |  | Independent | 8.3 | 1.3 | 2 |  | 2 |  |  | 16.6 | m2-LxH | ON HIRE | 2023-02-10 |  | 100% |  | 2.7143 | 14 | 0.84 | 232.4 | 13.944 | 162.68 | 0 | 37.848 | 200.528 |  | 200.528 |  |  | #VALUE! | 162.68 | #VALUE! | #VALUE!
|  | 1898 | 14483 |  |  | Level 28 Hotel | Access Scaffold |  | Independent | 27.5 | 1 | 2 |  | 2 |  |  | 55 | m2-LxH | ON HIRE | 2023-02-10 |  | 100% |  | 2.7143 | 14 | 0.84 | 770 | 46.2 | 539 | 0 | 125.4 | 664.4 |  | 664.4 |  |  | #VALUE! | 539 | #VALUE! | #VALUE!
|  | 1895 | 14480 | 8559 |  | Level 2 Hotel | Access Scaffold |  | Independent | 4 | 1 | 6 |  | 6 |  |  | 24 | m2-LxH | OFF HIRED | 2023-02-10 | 2023-02-11 | 100% |  | 0.28571 | 14 | 0.84 | 336 | 20.16 | 235.2 | 100.8 | 5.76 | 341.76 |  | 341.76 |  |  | #VALUE! | 235.2 | #VALUE! | #VALUE!
|  | 1892 | 14477 |  |  | Level 5 Hotel | Access Scaffold |  | Independent | 10.8 | 1.3 | 7 |  | 7 |  |  | 75.6 | m2-LxH | ON HIRE | 2023-02-09 |  | 100% |  | 2.8571 | 14 | 0.84 | 1058.4 | 63.504 | 740.88 | 0 | 181.44 | 922.32 |  | 922.32 |  |  | #VALUE! | 912.38 | #VALUE! | #VALUE!
|  | 1892 | 14477 |  |  | Level 5 Hotel | Access Scaffold |  | Independent | 2.5 | 1.3 | 7 |  | 7 |  |  | 17.5 | m2-LxH | ON HIRE | 2023-02-09 |  | 100% |  | 2.8571 | 14 | 0.84 | 245 | 14.7 | 171.5 | 0 | 42 | 213.5 |  | 213.5 |  |  | #VALUE! | 912.38 | #VALUE! | #VALUE!
|  | 1894 | 14479 |  |  | Level 3 Residence | Access Scaffold |  | Independent | 8 | 1 | 1.5 |  | 1.5 |  |  | 12 | m2-LxH | ON HIRE | 2023-02-09 |  | 100% |  | 2.8571 | 14 | 0.84 | 168 | 10.08 | 117.6 | 0 | 28.8 | 146.4 |  | 146.4 |  |  | #VALUE! | 117.6 | #VALUE! | #VALUE!
|  | 1906 | 14491 |  |  | Level 28 Hotel | Access Scaffold |  | Independent | 14.1 | 1.3 | 2 |  | 2 |  |  | 28.2 | m2-LxH | ON HIRE | 2023-02-11 |  | 100% |  | 2.5714 | 14 | 0.84 | 394.8 | 23.688 | 276.36 | 0 | 60.912 | 337.272 |  | 337.272 |  |  | #VALUE! | 276.36 | #VALUE! | #VALUE!
|  | 1863 | 14448 | 8638 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 5 | 1.3 | 1 |  | 1 |  |  | 5 | m2-LxH | OFF HIRED | 2023-02-04 | 2023-02-07 | 100% |  | 0.57143 | 14 | 0.84 | 70 | 4.2 | 49 | 21 | 2.4 | 72.4 |  | 72.4 |  |  | #VALUE! | 49 | #VALUE! | #VALUE!
|  | 1860 | 14445 | 8594 |  | Level 28 Hotel | Access Scaffold |  | Independent | 9 | 1 | 2 |  | 2 |  |  | 18 | m2-LxH | OFF HIRED | 2023-02-04 | 2023-02-21 | 100% |  | 2.5714 | 14 | 0.84 | 252 | 15.12 | 176.4 | 75.6 | 38.88 | 290.88 |  | 290.88 |  |  | #VALUE! | 176.4 | #VALUE! | #VALUE!
|  | 1851 | 14437 | 8640 |  | Level 3 Residence | Access Scaffold |  | Independent | 6.3 | 1.3 | 1.4 |  | 1.4 |  |  | 8.82 | m2-LxH | OFF HIRED | 2023-02-03 | 2023-02-07 | 100% |  | 0.71429 | 14 | 0.84 | 123.48 | 7.4088 | 86.436 | 37.044 | 5.292 | 128.772 |  | 128.772 |  |  | #VALUE! | 86.436 | #VALUE! | #VALUE!
|  | 1861 | 14447 | 8595 |  | Basement 2 Residence | Access Scaffold |  | Independent | 31.3 | 1.3 | 1.5 |  | 1.5 |  |  | 46.95 | m2-LxH | OFF HIRED | 2023-02-04 | 2023-02-24 | 100% |  | 3 | 14 | 0.84 | 657.3 | 39.438 | 460.11 | 197.19 | 118.314 | 775.614 |  | 775.614 |  |  | #VALUE! | 460.11 | #VALUE! | #VALUE!
|  | 1858 | 14443 | 8551 |  | Level 28 Hotel | Access Scaffold |  | Independent | 5 | 1.3 | 3.5 |  | 3.5 |  |  | 17.5 | m2-LxH | OFF HIRED | 2023-02-04 | 2023-02-09 | 100% |  | 0.85714 | 14 | 0.84 | 245 | 14.7 | 171.5 | 73.5 | 12.6 | 257.6 |  | 257.6 |  |  | #VALUE! | 171.5 | #VALUE! | #VALUE!
|  | 1854 | 14439 | 8575 |  | Leevel 1 Hotel | Access Scaffold |  | Independent | 8.3 | 1.3 | 2 |  | 2 |  |  | 16.6 | m2-LxH | OFF HIRED | 2023-02-03 | 2023-02-20 | 100% |  | 2.5714 | 14 | 0.84 | 232.4 | 13.944 | 162.68 | 69.72 | 35.856 | 268.256 |  | 268.256 |  |  | #VALUE! | 162.68 | #VALUE! | #VALUE!
|  | 1850 | 14436 |  |  | Level 10 To 12 Hotel | Access Scaffold |  | Independent | 30 | 1 | 1.5 |  | 1.5 |  |  | 45 | m2-LxH | ON HIRE | 2023-02-02 |  | 100% |  | 3.8571 | 14 | 0.84 | 630 | 37.8 | 441 | 0 | 145.8 | 586.8 |  | 586.8 |  |  | #VALUE! | 441 | #VALUE! | #VALUE!
|  | 1836 | 14422 |  |  | Level 3 Residence | Access Scaffold |  | Independent | 9.3 | 1.3 | 2 |  | 2 |  |  | 18.6 | m2-LxH | ON HIRE | 2023-02-01 |  | 100% |  | 4 | 14 | 0.84 | 260.4 | 15.624 | 182.28 | 0 | 62.496 | 244.776 |  | 244.776 |  |  | #VALUE! | 182.28 | #VALUE! | #VALUE!
|  | 1835 | 14421 | 8648 |  | Level 4 Hotel | Access Scaffold |  | Independent | 29 | 1 | 1 |  | 1 |  |  | 29 | m2-LxH | OFF HIRED | 2023-02-01 | 2023-02-08 | 100% |  | 1.1429 | 14 | 0.84 | 406 | 24.36 | 284.2 | 121.8 | 27.84 | 433.84 |  | 433.84 |  |  | #VALUE! | 284.2 | #VALUE! | #VALUE!
|  | 1841 | 14427 |  |  | Besement 1 Residence | Access Scaffold |  | Independent | 5 | 1.3 | 3 |  | 3 |  |  | 15 | m2-LxH | ON HIRE | 2023-02-02 |  | 100% |  | 3.8571 | 14 | 0.84 | 210 | 12.6 | 147 | 0 | 48.6 | 195.6 |  | 195.6 |  |  | #VALUE! | 147 | #VALUE! | #VALUE!
|  | 1840 | 14426 | 8579 |  | Level 5 Residence | Access Scaffold |  | Independent | 20.8 | 1.3 | 2 |  | 2 |  |  | 41.6 | m2-LxH | OFF HIRED | 2023-02-02 | 2023-02-20 | 100% |  | 2.7143 | 14 | 0.84 | 582.4 | 34.944 | 407.68 | 174.72 | 94.848 | 677.248 |  | 677.248 |  |  | #VALUE! | 995.68 | #VALUE! | #VALUE!
|  | 1840 | 14426 | 8579 |  | Level 5 Residence | Access Scaffold |  | Independent | 15 | 1.3 | 4 |  | 4 |  |  | 60 | m2-LxH | OFF HIRED | 2023-02-02 | 2023-02-20 | 100% |  | 2.7143 | 14 | 0.84 | 840 | 50.4 | 588 | 252 | 136.8 | 976.8 |  | 976.8 |  |  | #VALUE! | 995.68 | #VALUE! | #VALUE!
|  | 1844 | 14430 |  |  | Level 5 Hotel | Access Scaffold |  | Independent | 19 | 1.3 | 2 |  | 2 |  |  | 38 | m2-LxH | ON HIRE | 2023-02-02 |  | 100% |  | 3.8571 | 14 | 0.84 | 532 | 31.92 | 372.4 | 0 | 123.12 | 495.52 |  | 495.52 |  |  | #VALUE! | 372.4 | #VALUE! | #VALUE!
|  | 1843 | 14429 | 8642 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 4 | 1 | 2 |  | 2 |  |  | 8 | m2-LxH | OFF HIRED | 2023-02-02 | 2023-02-07 | 100% |  | 0.85714 | 14 | 0.84 | 112 | 6.72 | 78.4 | 33.6 | 5.76 | 117.76 |  | 117.76 |  |  | #VALUE! | 78.4 | #VALUE! | #VALUE!
|  | 1847 | 14433 | 8557 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 3.9 | 1.8 | 2.5 |  | 2.5 |  |  | 9.75 | m2-LxH | OFF HIRED | 2023-02-02 | 2023-02-11 | 100% |  | 1.4286 | 14 | 0.84 | 136.5 | 8.19 | 95.55 | 40.95 | 11.7 | 148.2 |  | 148.2 |  |  | #VALUE! | 108.29 | #VALUE! | #VALUE!
|  | 1847 | 14433 | 8557 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 1.3 | 1.3 | 1 |  | 1 |  |  | 1.3 | m2-LxH | OFF HIRED | 2023-02-02 | 2023-02-11 | 100% |  | 1.4286 | 14 | 0.84 | 18.2 | 1.092 | 12.74 | 5.46 | 1.56 | 19.76 |  | 19.76 |  |  | #VALUE! | 108.29 | #VALUE! | #VALUE!
|  | 1855 | 14440 | 8597 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 4 | 1.3 | 3 |  | 3 |  |  | 12 | m2-LxH | OFF HIRED | 2023-02-03 | 2023-02-24 | 100% |  | 3.1429 | 14 | 0.84 | 168 | 10.08 | 117.6 | 50.4 | 31.68 | 199.68 |  | 199.68 |  |  | #VALUE! | 117.6 | #VALUE! | #VALUE!
|  | 1877 | 14462 |  |  | Level 23 Residence | Access Scaffold |  | Independent | 5 | 1.3 | 2.5 |  | 2.5 |  |  | 12.5 | m2-LxH | ON HIRE | 2023-02-07 |  | 100% |  | 3.1429 | 14 | 0.84 | 175 | 10.5 | 122.5 | 0 | 33 | 155.5 |  | 155.5 |  |  | #VALUE! | 122.5 | #VALUE! | #VALUE!
|  | 1822 | 14410 | 8617 |  | Basement 1 Residence | Access Scaffold |  | Independent | 10 | 1.3 | 2.5 |  | 2.5 |  |  | 25 | m2-LxH | OFF HIRED | 2023-01-30 | 2023-01-30 | 100% |  | 0.14286 | 14 | 0.84 | 350 | 21 | 245 | 105 | 3 | 353 |  | 353 |  |  | #VALUE! | 428.75 | #VALUE! | #VALUE!
|  | 1822 | 14410 | 8617 |  | Basement 1 Residence | Access Scaffold |  | Independent | 7.5 | 1 | 2.5 |  | 2.5 |  |  | 18.75 | m2-LxH | OFF HIRED | 2023-01-30 | 2023-01-30 | 100% |  | 0.14286 | 14 | 0.84 | 262.5 | 15.75 | 183.75 | 78.75 | 2.25 | 264.75 |  | 264.75 |  |  | #VALUE! | 428.75 | #VALUE! | #VALUE!
|  | 1867 | 14452 |  |  | Ground Floor Hotel | Access Scaffold |  | Independent | 27 | 1 | 1.5 |  | 1.5 |  |  | 40.5 | m2-LxH | ON HIRE | 2023-02-05 |  | 100% |  | 3.4286 | 14 | 0.84 | 567 | 34.02 | 396.9 | 0 | 116.64 | 513.54 |  | 513.54 |  |  | #VALUE! | 396.9 | #VALUE! | #VALUE!
|  | 1872 | 14457 | 8646 |  | Level 3 Residence | Access Scaffold |  | Independent | 3.1 | 1.3 | 1.5 |  | 1.5 |  |  | 4.65 | m2-LxH | OFF HIRED | 2023-02-06 | 2023-02-08 | 100% |  | 0.42857 | 14 | 0.84 | 65.1 | 3.906 | 45.57 | 19.53 | 1.674 | 66.774 |  | 66.774 |  |  | #VALUE! | 45.57 | #VALUE! | #VALUE!
|  | 1871 | 14456 |  |  | Ground Floor Hotel | Access Scaffold |  | Independent | 4.5 | 1.3 | 2 |  | 2 |  |  | 9 | m2-LxH | ON HIRE | 2023-02-06 |  | 100% |  | 3.2857 | 14 | 0.84 | 126 | 7.56 | 88.2 | 0 | 24.84 | 113.04 |  | 113.04 |  |  | #VALUE! | 88.2 | #VALUE! | #VALUE!
|  | 1873 | 14458 |  |  | Level 23 Residence | Access Scaffold |  | Independent | 5 | 1.3 | 2.5 |  | 2.5 |  |  | 12.5 | m2-LxH | ON HIRE | 2023-02-06 |  | 100% |  | 3.2857 | 14 | 0.84 | 175 | 10.5 | 122.5 | 0 | 34.5 | 157 |  | 157 |  |  | #VALUE! | 122.5 | #VALUE! | #VALUE!
|  | 1876 | 14461 |  |  | Basement 2 Residence | Access Scaffold |  | Independent | 17.4 | 1.3 | 1.5 |  | 1.5 |  |  | 26.1 | m2-LxH | ON HIRE | 2023-02-07 |  | 100% |  | 3.1429 | 14 | 0.84 | 365.4 | 21.924 | 255.78 | 0 | 68.904 | 324.684 |  | 324.684 |  |  | #VALUE! | 255.78 | #VALUE! | #VALUE!
|  | 1875 | 14460 |  |  | Level 5 Hotel | Access Scaffold |  | Independent | 22 | 1.3 | 6 |  | 6 |  |  | 132 | m2-LxH | ON HIRE | 2023-02-06 |  | 100% |  | 3.2857 | 14 | 0.84 | 1848 | 110.88 | 1293.6 | 0 | 364.32 | 1657.92 |  | 1657.92 |  |  | #VALUE! | 1293.6 | #VALUE! | #VALUE!
|  | 1886 | 14471 | 8553 |  | Level 3 Residence | Access Scaffold |  | Independent | 6.6 | 1 | 1 |  | 1 |  |  | 6.6 | m2-LxH | OFF HIRED | 2023-02-08 |  | 100% |  | -6423.4286 | 14 | 0.84 | 92.4 | 5.544 | 64.68 | 27.72 | 0 | 92.4 |  | 92.4 |  |  | #VALUE! | 64.68 | #VALUE! | #VALUE!
|  | 1885 | 14470 | 8580 |  | Level 15 Hotel | Access Scaffold |  | Independent | 5 | 1 | 1.5 |  | 1.5 |  |  | 7.5 | m2-LxH | OFF HIRED | 2023-02-08 | 2023-02-18 | 100% |  | 1.5714 | 14 | 0.84 | 105 | 6.3 | 73.5 | 31.5 | 9.9 | 114.9 |  | 114.9 |  |  | #VALUE! | 73.5 | #VALUE! | #VALUE!
|  | 1882 | 14466 |  |  | Level 17 Hotel | Access Scaffold |  | Independent | 8.8 | 1.3 | 2 |  | 2 |  |  | 17.6 | m2-LxH | ON HIRE | 2023-02-08 |  | 100% |  | 3 | 14 | 0.84 | 246.4 | 14.784 | 172.48 | 0 | 44.352 | 216.832 |  | 216.832 |  |  | #VALUE! | 172.48 | #VALUE! | #VALUE!
|  | 1881 | 14465 |  |  | Level 3 Residence | Access Scaffold |  | Independent | 7.5 | 1.3 | 1.5 |  | 1.5 |  |  | 11.25 | m2-LxH | ON HIRE | 2023-02-08 |  | 100% |  | 3 | 14 | 0.84 | 157.5 | 9.45 | 110.25 | 0 | 28.35 | 138.6 |  | 138.6 |  |  | #VALUE! | 155.82 | #VALUE! | #VALUE!
|  | 1880 | 14465 |  |  | Level 3 Residence | Access Scaffold |  | Independent | 3.1 | 1.3 | 1.5 |  | 1.5 |  |  | 4.65 | m2-LxH | ON HIRE | 2023-02-08 |  | 100% |  | 3 | 14 | 0.84 | 65.1 | 3.906 | 45.57 | 0 | 11.718 | 57.288 |  | 57.288 |  |  | #VALUE! | 155.82 | #VALUE! | #VALUE!
|  | 1879 | 14464 |  |  | Level 17 Hotel | Access Scaffold |  | Independent | 9.9 | 1.3 | 1.5 |  | 1.5 |  |  | 14.85 | m2-LxH | ON HIRE | 2023-02-08 |  | 100% |  | 3 | 14 | 0.84 | 207.9 | 12.474 | 145.53 | 0 | 37.422 | 182.952 |  | 182.952 |  |  | #VALUE! | 145.53 | #VALUE! | #VALUE!
|  | 1884 | 14469 |  |  | Level 5 Hotel | Access Scaffold |  | Independent | 5 | 1.3 | 3.5 |  | 3.5 |  |  | 17.5 | m2-LxH | ON HIRE | 2023-02-08 |  | 100% |  | 3 | 14 | 0.84 | 245 | 14.7 | 171.5 | 0 | 44.1 | 215.6 |  | 215.6 |  |  | #VALUE! | 306.25 | #VALUE! | #VALUE!
|  | 1884 | 14469 |  |  | Level 5 Hotel | Access Scaffold |  | Independent | 2.5 | 1.3 | 5.5 |  | 5.5 |  |  | 13.75 | m2-LxH | ON HIRE | 2023-02-08 |  | 100% |  | 3 | 14 | 0.84 | 192.5 | 11.55 | 134.75 | 0 | 34.65 | 169.4 |  | 169.4 |  |  | #VALUE! | 306.25 | #VALUE! | #VALUE!
|  | 1878 | 14463 | 8565 |  | Ground Floor Residence | Access Scaffold |  | Independent | 9 | 1.3 | 3.5 |  | 3.5 |  |  | 31.5 | m2-LxH | OFF HIRED | 2023-02-08 | 2023-02-15 | 100% |  | 1.1429 | 14 | 0.84 | 441 | 26.46 | 308.7 | 132.3 | 30.24 | 471.24 |  | 471.24 |  |  | #VALUE! | 308.7 | #VALUE! | #VALUE!
|  | 1874 | 14459 | 8579 |  | Level 5 Residence | Access Scaffold |  | Independent | 5 | 1.3 | 4 |  | 4 |  |  | 20 | m2-LxH | OFF HIRED | 2023-02-06 | 2023-02-20 | 100% |  | 2.1429 | 14 | 0.84 | 280 | 16.8 | 196 | 84 | 36 | 316 |  | 316 |  |  | #VALUE! | 406 | #VALUE! | #VALUE!
|  | 1853 | 14438 | 8635 |  | Level 3 Residence | Access Scaffold |  | Independent | 3.1 | 1 | 1 |  | 1 |  |  | 3.1 | m2-LxH | OFF HIRED | 2023-02-03 | 2023-02-05 | 100% |  | 0.42857 | 14 | 0.84 | 43.4 | 2.604 | 30.38 | 13.02 | 1.116 | 44.516 |  | 44.516 |  |  | #VALUE! | 108.29 | #VALUE! | #VALUE!
|  | 1853 | 14438 | 8635 |  | Level 3 Residence | Access Scaffold |  | Independent | 4 | 1.3 | 1.5 |  | 1.5 |  |  | 6 | m2-LxH | OFF HIRED | 2023-02-03 | 2023-02-05 | 100% |  | 0.42857 | 14 | 0.84 | 84 | 5.04 | 58.8 | 25.2 | 2.16 | 86.16 |  | 86.16 |  |  | #VALUE! | 108.29 | #VALUE! | #VALUE!
|  | 1852 | 14438 |  |  | Level 3 Residence | Access Scaffold |  | Independent | 1.3 | 1 | 1.5 |  | 1.5 |  |  | 1.95 | m2-LxH | ON HIRE | 2023-02-03 |  | 100% |  | 3.7143 | 14 | 0.84 | 27.3 | 1.638 | 19.11 | 0 | 6.084 | 25.194 |  | 25.194 |  |  | #VALUE! | 108.29 | #VALUE! | #VALUE!
|  | 1890 | 14473 |  |  | Basement 1 Hotel | Access Scaffold |  | Independent | 2 | 1.3 | 3 |  | 3 |  |  | 6 | m2-LxH | ON HIRE | 2023-02-09 |  | 100% |  | 2.8571 | 14 | 0.84 | 84 | 5.04 | 58.8 | 0 | 14.4 | 73.2 |  | 73.2 |  |  | #VALUE! | 342.3 | #VALUE! | #VALUE!
|  | 1939 | 14527 |  |  | Level 28 Hotel | Access Scaffold |  | Independent | 12 | 1 | 2.5 |  | 2.5 |  |  | 30 | m2-LxH | ON HIRE | 2023-02-18 |  | 100% |  | 1.5714 | 14 | 0.84 | 420 | 25.2 | 294 | 0 | 39.6 | 333.6 |  | 333.6 |  |  | #VALUE! | 294 | #VALUE! | #VALUE!
|  | 1938 | 14526 |  |  | Level 17 Hotel | Access Scaffold |  | Independent | 8.5 | 1 | 2 |  | 2 |  |  | 17 | m2-LxH | ON HIRE | 2023-02-18 |  | 100% |  | 1.5714 | 14 | 0.84 | 238 | 14.28 | 166.6 | 0 | 22.44 | 189.04 |  | 189.04 |  |  | #VALUE! | 166.6 | #VALUE! | #VALUE!
|  | 1941 | 14529 | 8593 |  | Level 23 Residence | Access Scaffold |  | Independent | 6.8 | 1.3 | 3 |  | 3 |  |  | 20.4 | m2-LxH | ON HIRE | 2023-02-18 | 2023-02-21 | 100% |  | 1.5714 | 14 | 0.84 | 285.6 | 17.136 | 199.92 | 0 | 26.928 | 226.848 |  | 226.848 |  |  | #VALUE! | 199.92 | #VALUE! | #VALUE!
|  | 1958 | 14546 | 8595 |  | Basement 1 Residence | Access Scaffold |  | Independent | 4 | 0.6 | 1.5 |  | 1.5 |  |  | 6 | m2-LxH | OFF HIRED | 2023-02-22 | 2023-02-24 | 100% |  | 0.42857 | 14 | 0.84 | 84 | 5.04 | 58.8 | 25.2 | 2.16 | 86.16 |  | 86.16 |  |  | #VALUE! | 58.8 | #VALUE! | #VALUE!
|  | 1963 | 14601 |  |  | Level 28 Hotel | Access Scaffold |  | Independent | 6.8 | 1.3 | 3.5 |  | 3.5 |  |  | 23.8 | m2-LxH | ON HIRE | 2023-02-23 |  | 100% |  | 0.85714 | 14 | 0.84 | 333.2 | 19.992 | 233.24 | 0 | 17.136 | 250.376 |  | 250.376 |  |  | #VALUE! | 233.24 | #VALUE! | #VALUE!
|  | 1969 | 14607 |  |  | Basement 1 Residence | Access Scaffold |  | Independent | 20.1 | 1.3 | 4.5 |  | 4.5 |  |  | 90.45 | m2-LxH | ON HIRE | 2023-02-23 |  | 100% |  | 0.85714 | 14 | 0.84 | 1266.3 | 75.978 | 886.41 | 0 | 65.124 | 951.534 |  | 951.534 |  |  | #VALUE! | 886.41 | #VALUE! | #VALUE!
|  | 1945 | 14533 |  |  | Basement 1 Residence | Access Scaffold |  | Independent | 6.3 | 1.3 | 3.5 |  | 3.5 |  |  | 22.05 | m2-LxH | ON HIRE | 2023-02-21 |  | 100% |  | 1.1429 | 14 | 0.84 | 308.7 | 18.522 | 216.09 | 0 | 21.168 | 237.258 |  | 237.258 |  |  | #VALUE! | 216.09 | #VALUE! | #VALUE!
|  | 1950 | 14538 |  |  | Level 17 Hotel | Access Scaffold |  | Independent | 5 | 1.3 | 2 |  | 2 |  |  | 10 | m2-LxH | ON HIRE | 2023-02-21 |  | 100% |  | 1.1429 | 14 | 0.84 | 140 | 8.4 | 98 | 0 | 9.6 | 107.6 |  | 107.6 |  |  | #VALUE! | 98 | #VALUE! | #VALUE!
|  | 1934 | 14521 |  |  | Hotel | Access Scaffold |  | Independent | 5.8 | 1.3 | 5 |  | 5 |  |  | 29 | m2-LxH | ON HIRE | 2023-02-17 |  | 100% |  | 1.7143 | 14 | 0.84 | 406 | 24.36 | 284.2 | 0 | 41.76 | 325.96 |  | 325.96 |  |  | #VALUE! | 284.2 | #VALUE! | #VALUE!
|  | 1942 | 14530 |  |  | Level 25 To 26 Residence | Access Scaffold |  | Independent | 6.8 | 1.3 | 2 |  | 2 |  |  | 13.6 | m2-LxH | ON HIRE | 2023-02-18 |  | 100% |  | 1.5714 | 14 | 0.84 | 190.4 | 11.424 | 133.28 | 0 | 17.952 | 151.232 |  | 151.232 |  |  | #VALUE! | 133.28 | #VALUE! | #VALUE!
|  | 1919 | 14507 | 8569 |  | Ground Floor Residence | Access Scaffold |  | Independent | 6.5 | 1.3 | 3.5 |  | 3.5 |  |  | 22.75 | m2-LxH | OFF HIRED | 2023-02-13 | 2023-02-17 | 100% |  | 0.71429 | 14 | 0.84 | 318.5 | 19.11 | 222.95 | 95.55 | 13.65 | 332.15 |  | 332.15 |  |  | #VALUE! | 222.95 | #VALUE! | #VALUE!
|  | 1924 | 14512 |  |  | Level 21 To 24 Hotel | Access Scaffold |  | Independent | 51.5 | 1.3 | 1.5 |  | 1.5 |  |  | 77.25 | m2-LxH | ON HIRE | 2023-02-13 |  | 100% |  | 2.2857 | 14 | 0.84 | 1081.5 | 64.89 | 757.05 | 0 | 148.32 | 905.37 |  | 905.37 |  |  | #VALUE! | 757.05 | #VALUE! | #VALUE!
|  | 1929 | 14517 | 8595 |  | Ground Floor Residence | Access Scaffold |  | Independent | 14 | 0.6 | 2 |  | 2 |  |  | 28 | m2-LxH | OFF HIRED | 2023-02-16 | 2023-02-24 | 100% |  | 1.2857 | 14 | 0.84 | 392 | 23.52 | 274.4 | 117.6 | 30.24 | 422.24 |  | 422.24 |  |  | #VALUE! | 274.4 | #VALUE! | #VALUE!
|  | 1922 | 14510 |  |  | Ground Floor Hotel | Access Scaffold |  | Independent | 12.5 | 1.3 | 5.5 |  | 5.5 |  |  | 68.75 | m2-LxH | ON HIRE | 2023-02-13 |  | 100% |  | 2.2857 | 14 | 0.84 | 962.5 | 57.75 | 673.75 | 0 | 132 | 805.75 |  | 805.75 |  |  | #VALUE! | 980.35 | #VALUE! | #VALUE!
|  | 1984 | 14622 |  |  | Level 23 Residence | Access Scaffold |  | Independent | 9.8 | 1 | 2 |  | 2 |  |  | 19.6 | m2-LxH | ON HIRE | 2023-02-25 |  | 100% |  | 0.57143 | 14 | 0.84 | 274.4 | 16.464 | 192.08 | 0 | 9.408 | 201.488 |  | 201.488 |  |  | #VALUE! | 192.08 | #VALUE! | #VALUE!
|  | 1966 | 14604 |  |  | Level 23 Residence | Access Scaffold |  | Independent | 4 | 1.3 | 2 |  | 2 |  |  | 8 | m2-LxH | ON HIRE | 2023-02-23 |  | 100% |  | 0.85714 | 14 | 0.84 | 112 | 6.72 | 78.4 | 0 | 5.76 | 84.16 |  | 84.16 |  |  | #VALUE! | 254.485 | #VALUE! | #VALUE!
|  | 1983 | 14621 |  |  | Basement 1 Residence | Access Scaffold |  | Independent | 6.8 | 1.3 | 4 |  | 4 |  |  | 27.2 | m2-LxH | ON HIRE | 2023-02-25 |  | 100% |  | 0.57143 | 14 | 0.84 | 380.8 | 22.848 | 266.56 | 0 | 13.056 | 279.616 |  | 279.616 |  |  | #VALUE! | 550.06 | #VALUE! | #VALUE!
|  | 1952 | 14540 |  |  | Level 7 Residence | Access Scaffold |  | Independent | 8.5 | 1 | 1.5 |  | 1.5 |  |  | 12.75 | m2-LxH | ON HIRE | 2023-02-22 |  | 100% |  | 1 | 14 | 0.84 | 178.5 | 10.71 | 124.95 | 0 | 10.71 | 135.66 |  | 135.66 |  |  | #VALUE! | 124.95 | #VALUE! | #VALUE!
|  | 1985 | 14623 |  |  | Level 28 Hotel | Access Scaffold |  | Independent | 4.1 | 0.6 | 2 |  | 2 |  |  | 8.2 | m2-LxH | ON HIRE | 2023-02-26 |  | 100% |  | 0.42857 | 14 | 0.84 | 114.8 | 6.888 | 80.36 | 0 | 2.952 | 83.312 |  | 83.312 |  |  | #VALUE! | 178.36 | #VALUE! | #VALUE!
|  | 1985 | 14623 |  |  | Level 28 Hotel | Access Scaffold |  | Independent | 4 | 1.3 | 2.5 |  | 2.5 |  |  | 10 | m2-LxH | ON HIRE | 2023-02-26 |  | 100% |  | 0.42857 | 14 | 0.84 | 140 | 8.4 | 98 | 0 | 3.6 | 101.6 |  | 101.6 |  |  | #VALUE! | 178.36 | #VALUE! | #VALUE!
|  | 1996 | 14634 |  |  | Level 3 Residence | Access Scaffold |  | Independent | 5.6 | 1.3 | 1 |  | 1 |  |  | 5.6 | m2-LxH | ON HIRE | 2023-02-27 |  | 100% |  | 0.28571 | 14 | 0.84 | 78.4 | 4.704 | 54.88 | 0 | 1.344 | 56.224 |  | 56.224 |  |  | #VALUE! | 54.88 | #VALUE! | #VALUE!
|  | 1821 | 14409 |  |  | Ground Floor Residence | Access Scaffold |  | Independent | 6 | 1.8 | 6 |  | 6 |  |  | 36 | m2-LxH | ON HIRE | 2023-01-30 |  | 100% |  | 4.2857 | 18 | 1.05 | 648 | 37.8 | 453.6 | 0 | 162 | 615.6 |  | 615.6 |  |  | #VALUE! | 453.6 | #VALUE! | #VALUE!
|  | 1883 | 14468 |  |  | Basement 1 Residence | Access Scaffold |  | Independent | 1.8 | 1.8 | 3.5 |  | 3.5 |  |  | 6.3 | m2-LxH | ON HIRE | 2023-02-08 |  | 100% |  | 3 | 18 | 1.05 | 113.4 | 6.615 | 79.38 | 0 | 19.845 | 99.225 |  | 99.225 |  |  | #VALUE! | 79.38 | #VALUE! | #VALUE!
|  | 1888 | 14474 |  |  | Basement 1 Hotel | Access Scaffold |  | Independent | 23.3 | 1.8 | 4 |  | 4 |  |  | 93.2 | m2-LxH | ON HIRE | 2023-02-09 |  | 100% |  | 2.8571 | 18 | 1.05 | 1677.6 | 97.86 | 1174.32 | 0 | 279.6 | 1453.92 |  | 1453.92 |  |  | #VALUE! | 1174.32 | #VALUE! | #VALUE!
|  | 1889 | 14475 |  |  | Basement 1 Hotel | Access Scaffold |  | Independent | 6.8 | 1.8 | 4.5 |  | 4.5 |  |  | 30.6 | m2-LxH | ON HIRE | 2023-02-09 |  | 100% |  | 2.8571 | 18 | 1.05 | 550.8 | 32.13 | 385.56 | 0 | 91.8 | 477.36 |  | 477.36 |  |  | #VALUE! | 385.56 | #VALUE! | #VALUE!
|  | 1909 | 14494 | 8560 |  | Basement 1 Residence | Access Scaffold |  | Independent | 11.5 | 1.8 | 2 |  | 2 |  |  | 23 | m2-LxH | OFF HIRED | 2023-02-11 | 2023-02-14 | 100% |  | 0.57143 | 18 | 1.05 | 414 | 24.15 | 289.8 | 124.2 | 13.8 | 427.8 |  | 427.8 |  |  | #VALUE! | 289.8 | #VALUE! | #VALUE!
|  | 1916 | 14501 |  |  | Basement 1 Hotel | Access Scaffold |  | Independent | 1.8 | 1.8 | 2 |  | 2 |  |  | 3.6 | m2-LxH | ON HIRE | 2023-02-11 |  | 100% |  | 2.5714 | 18 | 1.05 | 64.8 | 3.78 | 45.36 | 0 | 9.72 | 55.08 |  | 55.08 |  |  | #VALUE! | 45.36 | #VALUE! | #VALUE!
|  | 1910 | 14495 |  |  | Basement 1 Residence | Access Scaffold |  | Independent | 4.1 | 1.8 | 3.5 |  | 3.5 |  |  | 14.35 | m2-LxH | ON HIRE | 2023-02-11 |  | 100% |  | 2.5714 | 18 | 1.05 | 258.3 | 15.0675 | 180.81 | 0 | 38.745 | 219.555 |  | 219.555 |  |  | #VALUE! | 180.81 | #VALUE! | #VALUE!
|  | 1912 | 14497 |  |  | Basement 1 Residence | Access Scaffold |  | Independent | 11.5 | 1.8 | 2 |  | 2 |  |  | 23 | m2-LxH | ON HIRE | 2023-02-11 |  | 100% |  | 2.5714 | 18 | 1.05 | 414 | 24.15 | 289.8 | 0 | 62.1 | 351.9 |  | 351.9 |  |  | #VALUE! | 289.8 | #VALUE! | #VALUE!
|  | 1897 | 14482 |  |  | Basement 1 Residence | Access Scaffold |  | Independent | 4 | 1.8 | 3 |  | 3 |  |  | 12 | m2-LxH | ON HIRE | 2023-02-10 |  | 100% |  | 2.7143 | 18 | 1.05 | 216 | 12.6 | 151.2 | 0 | 34.2 | 185.4 |  | 185.4 |  |  | #VALUE! | 151.2 | #VALUE! | #VALUE!
|  | 1940 | 14528 | 8578 |  | Ground Floor Hotel | Access Scaffold |  | Independent | 5 | 1.8 | 3.5 |  | 3.5 |  |  | 17.5 | m2-LxH | OFF HIRED | 2023-02-18 | 2023-02-20 | 100% |  | 0.42857 | 18 | 1.05 | 315 | 18.375 | 220.5 | 94.5 | 7.875 | 322.875 |  | 322.875 |  |  | #VALUE! | 220.5 | #VALUE! | #VALUE!
|  | 1926 | 14514 | 8592 |  | Level 5 Residence | Access Scaffold |  | Independent | 7.5 | 1.8 | 2.5 |  | 2.5 |  |  | 18.75 | m2-LxH | OFF HIRED | 2023-02-14 | 2023-02-21 | 100% |  | 1.1429 | 18 | 1.05 | 337.5 | 19.6875 | 236.25 | 101.25 | 22.5 | 360 |  | 360 |  |  | #VALUE! | 236.25 | #VALUE! | #VALUE!
|  | 1927 | 14515 | 8589 |  | Basement 1 Hotel | Access Scaffold |  | Independent | 4 | 1.8 | 2.5 |  | 2.5 |  |  | 10 | m2-LxH | OFF HIRED | 2023-02-15 | 2023-02-21 | 100% |  | 1 | 18 | 1.05 | 180 | 10.5 | 126 | 54 | 10.5 | 190.5 |  | 190.5 |  |  | #VALUE! | 126 | #VALUE! | #VALUE!
|  | 1972 | 14610 |  |  | Basement 1 Hotel | Access Scaffold |  | Independent | 4 | 1.8 | 2.5 |  | 2.5 |  |  | 10 | m2-LxH | ON HIRE | 2023-02-23 |  | 100% |  | 0.85714 | 18 | 1.05 | 180 | 10.5 | 126 | 0 | 9 | 135 |  | 135 |  |  | #VALUE! | 126 | #VALUE! | #VALUE!
|  | 1976 | 14614 |  |  | Basement 1 Residence | Access Scaffold |  | Independent | 2.5 | 1.8 | 2 |  | 2 |  |  | 5 | m2-LxH | ON HIRE | 2023-02-24 |  | 100% |  | 0.71429 | 18 | 1.05 | 90 | 5.25 | 63 | 0 | 3.75 | 66.75 |  | 66.75 |  |  | #VALUE! | 63 | #VALUE! | #VALUE!
|  | 1896 | 14481 |  |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 6 | 2.5 | 3 |  | 3 |  |  | 45 | m3 | ON HIRE | 2023-02-10 |  | 100% |  | 2.7143 | 7.5 | 0.7 | 337.5 | 31.5 | 236.25 | 0 | 85.5 | 321.75 |  | 321.75 |  |  | #VALUE! | 236.25 | #VALUE! | #VALUE!
|  | 1899 | 14484 |  |  | Level 28 Hotel | Birdcage Scaffold |  | Birdcage | 3 | 2.5 | 3.5 |  | 3.5 |  |  | 26.25 | m3 | ON HIRE | 2023-02-10 |  | 100% |  | 2.7143 | 7.5 | 0.7 | 196.875 | 18.375 | 137.8125 | 0 | 49.875 | 187.6875 |  | 187.6875 |  |  | #VALUE! | 137.8125 | #VALUE! | #VALUE!
|  | 1856 | 14441 | 8561 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 10 | 2.5 | 4 |  | 4 |  |  | 100 | m3 | OFF HIRED | 2023-02-03 | 2023-02-14 | 100% |  | 1.7143 | 7.5 | 0.7 | 750 | 70 | 525 | 225 | 120 | 870 |  | 870 |  |  | #VALUE! | 525 | #VALUE! | #VALUE!
|  | 1849 | 14435 | 8554 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 5.5 |  | 5.5 |  |  | 34.375 | m3 | OFF HIRED | 2023-02-02 | 2023-02-10 | 100% |  | 1.2857 | 7.5 | 0.7 | 257.8125 | 24.0625 | 180.4688 | 77.3438 | 30.9375 | 288.75 |  | 288.75 |  |  | #VALUE! | 180.4688 | #VALUE! | #VALUE!
|  | 1832 | 14419 | 8576 |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 5.1 | 4 | 3.5 |  | 3.5 |  |  | 71.4 | m3 | OFF HIRED | 2023-02-01 | 2023-02-19 | 100% |  | 2.7143 | 7.5 | 0.7 | 535.5 | 49.98 | 374.85 | 160.65 | 135.66 | 671.16 |  | 671.16 |  |  | #VALUE! | 374.85 | #VALUE! | #VALUE!
|  | 1838 | 14424 | 8564 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 4 |  | 4 |  |  | 25 | m3 | OFF HIRED | 2023-02-02 | 2023-02-15 | 100% |  | 2 | 7.5 | 0.7 | 187.5 | 17.5 | 131.25 | 56.25 | 35 | 222.5 |  | 222.5 |  |  | #VALUE! | 131.25 | #VALUE! | #VALUE!
|  | 1839 | 14425 |  |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 8.8 | 7.3 | 3 |  | 3 |  |  | 192.72 | m3 | ON HIRE | 2023-02-02 |  | 100% |  | 3.8571 | 7.5 | 0.7 | 1445.4 | 134.904 | 1011.78 | 0 | 520.344 | 1532.124 |  | 1532.124 |  |  | #VALUE! | 1011.78 | #VALUE! | #VALUE!
|  | 1837 | 14423 | 8638 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 4 |  | 4 |  |  | 25 | m3 | OFF HIRED | 2023-02-02 | 2023-02-07 | 100% |  | 0.85714 | 7.5 | 0.7 | 187.5 | 17.5 | 131.25 | 56.25 | 15 | 202.5 |  | 202.5 |  |  | #VALUE! | 131.25 | #VALUE! | #VALUE!
|  | 1857 | 14442 |  |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 8.6 | 2.5 | 4 |  | 4 |  |  | 86 | m3 | ON HIRE | 2023-02-03 |  | 100% |  | 3.7143 | 7.5 | 0.7 | 645 | 60.2 | 451.5 | 0 | 223.6 | 675.1 |  | 675.1 |  |  | #VALUE! | 451.5 | #VALUE! | #VALUE!
|  | 1866 | 14451 | 8564 |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 4.5 |  | 4.5 |  |  | 28.125 | m3 | OFF HIRED | 2023-02-04 | 2023-02-15 | 100% |  | 1.7143 | 7.5 | 0.7 | 210.9375 | 19.6875 | 147.6562 | 63.2812 | 33.75 | 244.6875 |  | 244.6875 |  |  | #VALUE! | 147.6562 | #VALUE! | #VALUE!
|  | 1868 | 14453 |  |  | Level 23 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 4 |  | 4 |  |  | 25 | m3 | ON HIRE | 2023-02-05 |  | 100% |  | 3.4286 | 7.5 | 0.7 | 187.5 | 17.5 | 131.25 | 0 | 60 | 191.25 |  | 191.25 |  |  | #VALUE! | 131.25 | #VALUE! | #VALUE!
|  | 1870 | 14455 |  |  | Basement 2 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 2 |  | 2 |  |  | 12.5 | m3 | ON HIRE | 2023-02-06 |  | 100% |  | 3.2857 | 7.5 | 0.7 | 93.75 | 8.75 | 65.625 | 0 | 28.75 | 94.375 |  | 94.375 |  |  | #VALUE! | 65.625 | #VALUE! | #VALUE!
|  | 1903 | 14488 | 8579 |  | Level 5 Residence | Birdcage Scaffold |  | Birdcage | 8 | 8 | 4.5 |  | 4.5 |  |  | 288 | m3 | OFF HIRED | 2023-02-10 | 2023-02-20 | 100% |  | 1.5714 | 7.5 | 0.7 | 2160 | 201.6 | 1512 | 648 | 316.8 | 2476.8 |  | 2476.8 |  |  | #VALUE! | 1544.8125 | #VALUE! | #VALUE!
|  | 1874 | 14459 | 8579 |  | Level 5 Residence | Birdcage Scaffold |  | Birdcage | 4 | 2.5 | 4 |  | 4 |  |  | 40 | m3 | OFF HIRED | 2023-02-06 | 2023-02-20 | 100% |  | 2.1429 | 7.5 | 0.7 | 300 | 28 | 210 | 90 | 60 | 360 |  | 360 |  |  | #VALUE! | 406 | #VALUE! | #VALUE!
|  | 1953 | 14541 |  |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 2 |  | 2 |  |  | 12.5 | m3 | ON HIRE | 2023-02-22 |  | 100% |  | 1 | 7.5 | 0.7 | 93.75 | 8.75 | 65.625 | 0 | 8.75 | 74.375 |  | 74.375 |  |  | #VALUE! | 65.625 | #VALUE! | #VALUE!
|  | 1943 | 14531 |  |  | Level 28 Hotel | Birdcage Scaffold |  | Birdcage | 6.3 | 6 | 3 |  | 3 |  |  | 113.4 | m3 | ON HIRE | 2023-02-18 |  | 100% |  | 1.5714 | 7.5 | 0.7 | 850.5 | 79.38 | 595.35 | 0 | 124.74 | 720.09 |  | 720.09 |  |  | #VALUE! | 595.35 | #VALUE! | #VALUE!
|  | 1957 | 14545 |  |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 3.5 |  | 3.5 |  |  | 21.875 | m3 | ON HIRE | 2023-02-22 |  | 100% |  | 1 | 7.5 | 0.7 | 164.0625 | 15.3125 | 114.8437 | 0 | 15.3125 | 130.1562 |  | 130.1562 |  |  | #VALUE! | 114.8437 | #VALUE! | #VALUE!
|  | 1956 | 14544 |  |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 3.5 |  | 3.5 |  |  | 21.875 | m3 | ON HIRE | 2023-02-22 |  | 100% |  | 1 | 7.5 | 0.7 | 164.0625 | 15.3125 | 114.8437 | 0 | 15.3125 | 130.1562 |  | 130.1562 |  |  | #VALUE! | 114.8437 | #VALUE! | #VALUE!
|  | 1955 | 14543 |  |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 3.5 |  | 3.5 |  |  | 21.875 | m3 | ON HIRE | 2023-02-22 |  | 100% |  | 1 | 7.5 | 0.7 | 164.0625 | 15.3125 | 114.8437 | 0 | 15.3125 | 130.1562 |  | 130.1562 |  |  | #VALUE! | 114.8437 | #VALUE! | #VALUE!
|  | 1960 | 14548 |  |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 3.5 |  | 3.5 |  |  | 21.875 | m3 | ON HIRE | 2023-02-23 |  | 100% |  | 0.85714 | 7.5 | 0.7 | 164.0625 | 15.3125 | 114.8437 | 0 | 13.125 | 127.9687 |  | 127.9687 |  |  | #VALUE! | 114.8437 | #VALUE! | #VALUE!
|  | 1959 | 14547 |  |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 3.5 |  | 3.5 |  |  | 21.875 | m3 | ON HIRE | 2023-02-22 |  | 100% |  | 1 | 7.5 | 0.7 | 164.0625 | 15.3125 | 114.8437 | 0 | 15.3125 | 130.1562 |  | 130.1562 |  |  | #VALUE! | 114.8437 | #VALUE! | #VALUE!
|  | 1964 | 14602 |  |  | Level 28 Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 3.5 |  | 3.5 |  |  | 21.875 | m3 | ON HIRE | 2023-02-23 |  | 100% |  | 0.85714 | 7.5 | 0.7 | 164.0625 | 15.3125 | 114.8437 | 0 | 13.125 | 127.9687 |  | 127.9687 |  |  | #VALUE! | 114.8437 | #VALUE! | #VALUE!
|  | 1968 | 14606 |  |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 3.5 |  | 3.5 |  |  | 21.875 | m3 | ON HIRE | 2023-02-23 |  | 100% |  | 0.85714 | 7.5 | 0.7 | 164.0625 | 15.3125 | 114.8437 | 0 | 13.125 | 127.9687 |  | 127.9687 |  |  | #VALUE! | 114.8437 | #VALUE! | #VALUE!
|  | 1967 | 14605 |  |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 3.5 |  | 3.5 |  |  | 21.875 | m3 | ON HIRE | 2023-02-23 |  | 100% |  | 0.85714 | 7.5 | 0.7 | 164.0625 | 15.3125 | 114.8437 | 0 | 13.125 | 127.9687 |  | 127.9687 |  |  | #VALUE! | 114.8437 | #VALUE! | #VALUE!
|  | 1944 | 14532 |  |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 4 | 3 | 4 |  | 4 |  |  | 48 | m3 | ON HIRE | 2023-02-21 |  | 100% |  | 1.1429 | 7.5 | 0.7 | 360 | 33.6 | 252 | 0 | 38.4 | 290.4 |  | 290.4 |  |  | #VALUE! | 252 | #VALUE! | #VALUE!
|  | 1970 | 14608 |  |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 3.5 |  | 3.5 |  |  | 21.875 | m3 | ON HIRE | 2023-02-23 |  | 100% |  | 0.85714 | 7.5 | 0.7 | 164.0625 | 15.3125 | 114.8437 | 0 | 13.125 | 127.9687 |  | 127.9687 |  |  | #VALUE! | 114.8437 | #VALUE! | #VALUE!
|  | 1946 | 14534 |  |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 5 | 2.5 | 2 |  | 2 |  |  | 25 | m3 | ON HIRE | 2023-02-17 |  | 100% |  | 1.7143 | 7.5 | 0.7 | 187.5 | 17.5 | 131.25 | 0 | 30 | 161.25 |  | 161.25 |  |  | #VALUE! | 557.8125 | #VALUE! | #VALUE!
|  | 1933 | 14520 |  |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 4 | 3.5 | 2.5 |  | 2.5 |  |  | 35 | m3 | ON HIRE | 2023-02-13 |  | 100% |  | 2.2857 | 7.5 | 0.7 | 262.5 | 24.5 | 183.75 | 0 | 56 | 239.75 |  | 239.75 |  |  | #VALUE! | 183.75 | #VALUE! | #VALUE!
|  | 1923 | 14511 |  |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 7.5 | 2.5 | 7.5 |  | 7.5 |  |  | 140.625 | m3 | ON HIRE | 2023-02-13 |  | 100% |  | 2.2857 | 7.5 | 0.7 | 1054.6875 | 98.4375 | 738.2812 | 0 | 225 | 963.2812 |  | 963.2812 |  |  | #VALUE! | 895.7812 | #VALUE! | #VALUE!
|  | 1925 | 14513 |  |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 11.8 | 4 | 5.6 |  | 5.6 |  |  | 264.32 | m3 | ON HIRE | 2023-02-14 |  | 100% |  | 2.1429 | 7.5 | 0.7 | 1982.4 | 185.024 | 1387.68 | 0 | 396.48 | 1784.16 |  | 1784.16 |  |  | #VALUE! | 1387.68 | #VALUE! | #VALUE!
|  | 1946 | 14534 |  |  | Ground Floor Residence | Birdcage Scaffold |  | Birdcage | 5 | 2.5 | 6.5 |  | 6.5 |  |  | 81.25 | m3 | ON HIRE | 2023-02-21 |  | 100% |  | 1.1429 | 7.5 | 0.7 | 609.375 | 56.875 | 426.5625 | 0 | 65 | 491.5625 |  | 491.5625 |  |  | #VALUE! | 557.8125 | #VALUE! | #VALUE!
|  | 1962 | 14550 |  |  | Level 28 Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 4 |  | 4 |  |  | 25 | m3 | ON HIRE | 2023-02-23 |  | 100% |  | 0.85714 | 7.5 | 0.7 | 187.5 | 17.5 | 131.25 | 0 | 15 | 146.25 |  | 146.25 |  |  | #VALUE! | 509.25 | #VALUE! | #VALUE!
|  | 1965 | 14603 | 8598 |  | Level 28 Hotel | Birdcage Scaffold |  | Birdcage | 3.5 | 2.5 | 3.5 |  | 3.5 |  |  | 30.625 | m3 | OFF HIRED | 2023-02-23 | 2023-02-24 | 100% |  | 0.28571 | 7.5 | 0.7 | 229.6875 | 21.4375 | 160.7812 | 68.9062 | 6.125 | 235.8125 |  | 235.8125 |  |  | #VALUE! | 180.7103 | #VALUE! | #VALUE!
|  | 1971 | 14609 |  |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 3.5 |  | 3.5 |  |  | 21.875 | m3 | ON HIRE | 2023-02-23 |  | 100% |  | 0.85714 | 7.5 | 0.7 | 164.0625 | 15.3125 | 114.8437 | 0 | 13.125 | 127.9687 |  | 127.9687 |  |  | #VALUE! | 114.8437 | #VALUE! | #VALUE!
|  | 1974 | 14612 |  |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 3.5 |  | 3.5 |  |  | 21.875 | m3 | ON HIRE | 2023-02-23 |  | 100% |  | 0.85714 | 7.5 | 0.7 | 164.0625 | 15.3125 | 114.8437 | 0 | 13.125 | 127.9687 |  | 127.9687 |  |  | #VALUE! | 114.8437 | #VALUE! | #VALUE!
|  | 1973 | 14611 |  |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 2 |  | 2 |  |  | 12.5 | m3 | ON HIRE | 2023-02-23 |  | 100% |  | 0.85714 | 7.5 | 0.7 | 93.75 | 8.75 | 65.625 | 0 | 7.5 | 73.125 |  | 73.125 |  |  | #VALUE! | 65.625 | #VALUE! | #VALUE!
|  | 1975 | 14613 |  |  | Basement 1 Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 2 |  | 2 |  |  | 12.5 | m3 | ON HIRE | 2023-02-24 |  | 100% |  | 0.71429 | 7.5 | 0.7 | 93.75 | 8.75 | 65.625 | 0 | 6.25 | 71.875 |  | 71.875 |  |  | #VALUE! | 65.625 | #VALUE! | #VALUE!
|  | 1978 | 14616 |  |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 3.5 |  | 3.5 |  |  | 21.875 | m3 | ON HIRE | 2023-02-24 |  | 100% |  | 0.71429 | 7.5 | 0.7 | 164.0625 | 15.3125 | 114.8437 | 0 | 10.9375 | 125.7812 |  | 125.7812 |  |  | #VALUE! | 114.8437 | #VALUE! | #VALUE!
|  | 1977 | 14615 |  |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 4 |  | 4 |  |  | 25 | m3 | ON HIRE | 2023-02-24 |  | 100% |  | 0.71429 | 7.5 | 0.7 | 187.5 | 17.5 | 131.25 | 0 | 12.5 | 143.75 |  | 143.75 |  |  | #VALUE! | 131.25 | #VALUE! | #VALUE!
|  | 1981 | 14619 |  |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 6.3 | 2.5 | 2 |  | 2 |  |  | 31.5 | m3 | ON HIRE | 2023-02-25 |  | 100% |  | 0.57143 | 7.5 | 0.7 | 236.25 | 22.05 | 165.375 | 0 | 12.6 | 177.975 |  | 177.975 |  |  | #VALUE! | 165.375 | #VALUE! | #VALUE!
|  | 1966 | 14604 |  |  | Level 23 Residence | Birdcage Scaffold |  | Birdcage | 4.3 | 2.6 | 3 |  | 3 |  |  | 33.54 | m3 | ON HIRE | 2023-02-23 |  | 100% |  | 0.85714 | 7.5 | 0.7 | 251.55 | 23.478 | 176.085 | 0 | 20.124 | 196.209 |  | 196.209 |  |  | #VALUE! | 254.485 | #VALUE! | #VALUE!
|  | 1979 | 14617 |  |  | Level 28 Hotel | Birdcage Scaffold |  | Birdcage | 3.5 | 2.5 | 3.5 |  | 3.5 |  |  | 30.625 | m3 | ON HIRE | 2023-02-25 |  | 100% |  | 0.57143 | 7.5 | 0.7 | 229.6875 | 21.4375 | 160.7812 | 0 | 12.25 | 173.0312 |  | 173.0312 |  |  | #VALUE! | 199.1062 | #VALUE! | #VALUE!
|  | 1995 | 14633 |  |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 4.5 |  | 4.5 |  |  | 28.125 | m3 | ON HIRE | 2023-02-27 |  | 100% |  | 0.28571 | 7.5 | 0.7 | 210.9375 | 19.6875 | 147.6562 | 0 | 5.625 | 153.2812 |  | 153.2812 |  |  | #VALUE! | 147.6562 | #VALUE! | #VALUE!
|  | 1994 | 14632 |  |  | Ground Floor Hotel | Birdcage Scaffold |  | Birdcage | 11.5 | 3 | 3.5 |  | 3.5 |  |  | 120.75 | m3 | ON HIRE | 2023-02-27 |  | 100% |  | 0.28571 | 7.5 | 0.7 | 905.625 | 84.525 | 633.9375 | 0 | 24.15 | 658.0875 |  | 658.0875 |  |  | #VALUE! | 633.9375 | #VALUE! | #VALUE!
|  | 1993 | 14631 |  |  | Basement 1 Residence | Birdcage Scaffold |  | Birdcage | 2.5 | 2.5 | 5 |  | 5 |  |  | 31.25 | m3 | ON HIRE | 2023-02-27 |  | 100% |  | 0.28571 | 7.5 | 0.7 | 234.375 | 21.875 | 164.0625 | 0 | 6.25 | 170.3125 |  | 170.3125 |  |  | #VALUE! | 164.0625 | #VALUE! | #VALUE!
|  | 1869 | 14454 | 8587 |  | Level 18 Hotel | Cantiliver |  | Cantiliver | 1.5 | 1 |  |  |  | 1 |  | 1.5 | m2-LxW | OFF HIRED | 2023-02-06 | 2023-02-21 | 100% |  | 2.2857 | 36.5 | 3.15 | 54.75 | 4.725 | 38.325 | 16.425 | 10.8 | 65.55 |  | 65.55 |  |  | #VALUE! | 369.075 | #VALUE! | #VALUE!
|  | 1917A | 14506 |  |  | Ground Floor Residence | Cantiliver |  | Cantiliver | 18.6 | 2 |  |  |  | 1 |  | 37.2 | m2-LxW | ON HIRE | 2023-02-13 |  | 100% |  | 2.2857 | 36.5 | 3.15 | 1357.8 | 117.18 | 950.46 | 0 | 267.84 | 1218.3 |  | 1218.3 |  |  | #VALUE! | 950.46 | #VALUE! | #VALUE!
|  | 1965 | 14603 | 8598 |  | Level 28 Hotel | Cantiliver |  | Cantiliver | 1.3 | 0.6 |  |  |  | 1 |  | 0.78 | m2-LxW | OFF HIRED | 2023-02-23 | 2023-02-24 | 100% |  | 0.28571 | 36.5 | 3.15 | 28.47 | 2.457 | 19.929 | 8.541 | 0.702 | 29.172 |  | 29.172 |  |  | #VALUE! | 180.7103 | #VALUE! | #VALUE!
|  | 1951 | 14539 |  |  | Level 2 Hotel | Cantiliver |  | Cantiliver | 1.3 | 0.6 |  |  |  | 1 |  | 0.78 | m2-LxW | ON HIRE | 2023-02-21 |  | 100% |  | 1.1429 | 36.5 | 3.15 | 28.47 | 2.457 | 19.929 | 0 | 2.808 | 22.737 |  | 22.737 |  |  | #VALUE! | 586.929 | #VALUE! | #VALUE!
|  | 1922 | 14510 |  |  | Ground FloorHotel | Cantiliver |  | Cantiliver | 10 | 1.2 |  |  |  | 1 |  | 12 | m2-LxW | ON HIRE | 2023-02-13 |  | 100% |  | 2.2857 | 36.5 | 3.15 | 438 | 37.8 | 306.6 | 0 | 86.4 | 393 |  | 393 |  |  | #VALUE! | 980.35 | #VALUE! | #VALUE!
|  | 1979 | 14617 |  |  | Level 28 Hotel | Cantiliver |  | Cantiliver | 2.5 | 0.6 |  |  |  | 1 |  | 1.5 | m2-LxW | ON HIRE | 2023-02-25 |  | 100% |  | 0.57143 | 36.5 | 3.15 | 54.75 | 4.725 | 38.325 | 0 | 2.7 | 41.025 |  | 41.025 |  |  | #VALUE! | 199.1062 | #VALUE! | #VALUE!
|  | 1903 | 14488 | 8579 |  | Level 5 Residece | Boarded Lift |  | Board Lift | 2.5 | 2.5 |  |  |  | 1 |  | 6.25 | m2-LxW | OFF HIRED | 2023-02-10 | 2023-02-20 | 100% |  | 1.5714 | 7.5 | 1.05 | 46.875 | 6.5625 | 32.8125 | 14.0625 | 10.3125 | 57.1875 |  | 57.1875 |  |  | #VALUE! | 1544.8125 | #VALUE! | #VALUE!
|  | 1923 | 14511 |  |  | Ground Floor Hotel | Boarded Lift |  | Board Lift | 7.5 | 4 |  |  |  | 1 |  | 30 | m2-LxW | ON HIRE | 2023-02-13 |  | 100% |  | 2.2857 | 7.5 | 1.05 | 225 | 31.5 | 157.5 | 0 | 72 | 229.5 |  | 229.5 |  |  | #VALUE! | 895.7812 | #VALUE! | #VALUE!
|  | 1917 | 14502 |  |  | Ground Floor To Level 5 Residence | Chain Pully |  | Independent | 18.6 | 1 | 16.5 |  | 16.5 |  |  | 306.9 | m2-LxH | ON HIRE | 2023-02-13 |  | 100% |  | 2.2857 | 14 | 0.84 | 4296.6 | 257.796 | 3007.62 | 0 | 589.248 | 3596.868 |  | 3596.868 |  |  | #VALUE! | 10868.445 | #VALUE! | #VALUE!
|  | 1917 | 14502 |  |  | Ground Floor To Level 5 Residence | Chain Pully |  | Buttress | 18.6 | 2.5 | 23 |  | 23 |  |  | 1069.5 | m3 | ON HIRE | 2023-02-13 |  | 100% |  | 2.2857 | 5.25 | 0.35 | 5614.875 | 374.325 | 3930.4125 | 0 | 855.6 | 4786.0125 |  | 4786.0125 |  |  | #VALUE! | 10868.445 | #VALUE! | #VALUE!
|  | 1917 | 14502 |  |  | Ground Floor To Level 5 Residence | Chain Pully |  | Buttress | 18.6 | 2.5 | 23 |  | 23 |  |  | 1069.5 | m3 | ON HIRE | 2023-02-13 |  | 100% |  | 2.2857 | 5.25 | 0.35 | 5614.875 | 374.325 | 3930.4125 | 0 | 855.6 | 4786.0125 |  | 4786.0125 |  |  | #VALUE! | 10868.445 | #VALUE! | #VALUE!
|  | 1918 | 14504 |  |  | Ground Floor To Level 5 hotel | Chain Pully |  | Independent | 30 | 2.5 | 6 |  | 6 |  |  | 180 | m2-LxH | ON HIRE | 2023-02-13 |  | 100% |  | 2.2857 | 14 | 2.1 | 2520 | 378 | 1764 | 0 | 864 | 2628 |  | 2628 |  |  | #VALUE! | 11466 | #VALUE! | #VALUE!
|  | 1918 | 14504 |  |  | Ground Floor To Level 5 hotel | Chain Pully |  | Buttress | 30 | 4 | 22 |  | 22 |  |  | 2640 | m3 | ON HIRE | 2023-02-13 |  | 100% |  | 2.2857 | 5.25 | 0.35 | 13860 | 924 | 9702 | 0 | 2112 | 11814 |  | 11814 |  |  | #VALUE! | 11466 | #VALUE! | #VALUE!
|  | 1917 | 14503 |  |  | Ground Floor To Level 5 Residence | Chain Pully With Ladder Beam |  | Independent | 4 | 9 |  |  |  | 1 |  | 36 | m2-LxW | ON HIRE | 2023-02-13 |  | 100% |  | 2.2857 | 81 | 1.82 | 2916 | 65.52 | 2041.2 | 0 | 149.76 | 2190.96 |  | 2190.96 |  |  | #VALUE! | 3061.8 | #VALUE! | #VALUE!
|  | 1917 | 14503 |  |  | Ground Floor To Level 5 Residence | Chain Pully With Ladder Beam |  | Independent | 6 | 3 |  |  |  | 1 |  | 18 | m2-LxW | ON HIRE | 2023-02-13 |  | 100% |  | 2.2857 | 81 | 1.82 | 1458 | 32.76 | 1020.6 | 0 | 74.88 | 1095.48 |  | 1095.48 |  |  | #VALUE! | 3061.8 | #VALUE! | #VALUE!
|  | 1918 | 14505 |  |  | Ground Floor To Level 5 hotel | Chain Pully With Ladder Beam |  | Independent | 4 | 14 |  |  |  | 1 |  | 56 | m2-LxW | ON HIRE | 2023-02-13 |  | 100% |  | 2.2857 | 81 | 1.82 | 4536 | 101.92 | 3175.2 | 0 | 232.96 | 3408.16 |  | 3408.16 |  |  | #VALUE! | 4876.2 | #VALUE! | #VALUE!
|  | 1917 | 14505 |  |  | Ground Floor To Level 5 hotel | Chain Pully With Ladder Beam |  | Independent | 6 | 5 |  |  |  | 1 |  | 30 | m2-LxW | ON HIRE | 2023-02-13 |  | 100% |  | 2.2857 | 81 | 1.82 | 2430 | 54.6 | 1701 | 0 | 124.8 | 1825.8 |  | 1825.8 |  |  | #VALUE! | 4876.2 | #VALUE! | #VALUE!
0
[26 empty] | Total Amount |  |  | 923999.9025 | 333857.9359 | 765943.2961
[30 empty] | GRAND TOTAL |  | 1996671.9746 | 1826079.6221 | 172077.3525
RPJ EXISTING SCAFFOLDING
Billing Reference |  | Tag No. | HOC | OHC | Ref | Section of Work | Description | Section | Scaffold Type | Length | Width | Height |  | Height | Board Lift | Re-measure | Quantity | Unit of Measure | Hire Status | HOC Date | OHC Date | Percent Dismantle | Hire Charge After WEEKS | Weeks On Hire | E&D Rate per unit | Hire Rate per wk | Labour Cost | Weekly hire charge | Erect Cost | Dismantle Cost | Hire Cost | Total Cost | Previous Billed | Net Payment | Remarks
|  |  | 10947 | 8636 |  | Level 17-23 Residence | Birdcage Scaffold |  | Birdcage | 25 |  | 33 |  | 33 |  |  | 3612 | m3 | OFF HIRED | 2022-05-01 | 2023-02-06 | 100% |  | 40.2857 | 3.6 | 1.4 | 13003.2 | 5056.8 | 0 | 13003.2 | 203716.8 | 216720 | 199382.4 | 17337.6
|  |  |  | 8424 |  | PARTIAL DISMANTEL |  |  |  | 25 |  | 17.5 |  | 17.5 |  |  | 1806 | m3 | OFF HIRED | 2023-01-12 | 2023-02-06 | 100% |  | -3.7143 | 3.6 | 1.4 | 6501.6 | 2528.4 |  | 0 | -9391.2 | -9391.2 | -722.4 | -8668.8 |  | -24
|  |  | 10947 | 8636 |  | Level 17-23 Residence | Birdcage Scaffold |  | Birdcage | 3.9 | 1.3 | 33 |  | 33 |  |  | 167.31 | m3 | OFF HIRED | 2022-05-01 | 2023-02-06 | 100% |  | 40.2857 | 6 | 2.1 | 1003.86 | 351.351 | 0 | 1003.86 | 14154.426 | 15158.286 | 13853.268 | 1305.018
|  |  | 11152 | 8263 |  | Level 4-6 | podium cantliver |  | Cantiliver | 33 | 1.3 | 7 |  | 7 |  |  | 300.3 | m3 | OFF HIRED | 2022-05-01 | 2022-11-22 | 100% |  | 29.4286 | 6 | 2.1 | 1801.8 | 630.63 | 0 | 1801.8 | 18558.54 | 20360.34 | 20360.34 | 0
|  |  | 11152 | 8263 |  | Level 4-6 | podium cantliver |  | Cantiliver | 33 | 2.5 | 7 |  | 7 |  |  | 577.5 | m3 | OFF HIRED | 2022-05-01 | 2022-11-22 | 100% |  | 29.4286 | 6 | 2.1 | 3465 | 1212.75 | 0 | 3465 | 35689.5 | 39154.5 | 39154.5 | 0
|  |  | 11160 | 8263 |  | Level 4-6 | podium cantliver |  | Cantiliver | 24 | 9 | 11.5 |  | 11.5 |  | 1 | 2484 | m3 | OFF HIRED | 2022-05-01 | 2022-11-22 | 100% |  | 29.4286 | 3.6 | 1.4 | 8942.4 | 3477.6 | 0 | 8942.4 | 102340.8 | 111283.2 | 111283.2 | 0
[26 empty] | Total Amount |  |  |  |  | 365068.866 | 393285.126 | 383311.308 | 9973.818
[30 empty] | Less Discount 30.02% |  |  |  | 2994.1402
[30 empty] | GRAND TOTAL |  | -118064.1948 |  | 6979.6778
RPJ EXISTING SCAFFOLDING
Billing Reference |  | Tag No. | HOC | OHC | Ref | Section of Work | Description | Section | Scaffold Type | Length | Width | Height |  | Height | Board Lift | Re-measure | Quantity | Unit of Measure | Hire Status | HOC Date | OHC Date | Percent Dismantle | Hire Charge After WEEKS | Weeks On Hire | E&D Rate per unit | Hire Rate per wk | Labour Cost | Weekly hire charge | Erect Cost | Dismantle Cost | Hire Cost | Total Cost | Previous Billed | Net Payment | Remarks
|  |  | 11183 | 8277 |  | Grc Installation | Access Scaffold |  | INDEPENDENT | 14.6 | 1.3 | 30 |  | 30 |  |  | 569.4 | m3 | OFF HIRED | 2022-05-01 | 2022-11-26 | 100% |  | 30 | 6 | 2.1 | 3416.4 | 1195.74 | 0 | 3416.4 | 35872.2 | 39288.6 | 39288.6 | 0
|  |  | 11183 | 8277 |  | Landing platfrom | Access Scaffold |  | INDEPENDENT | 14.6 | 1.3 | 35 |  | 35 |  |  | 664.3 | m3 | OFF HIRED | 2022-05-01 | 2022-11-26 | 100% |  | 30 | 6 | 2.1 | 3985.8 | 1395.03 | 0 | 3985.8 | 41850.9 | 45836.7 | 45836.7 | 0
[26 empty] | Total Amount |  |  |  |  | 77723.1 | 85125.3 | 85125.3 | 0
[30 empty] | GRAND TOTAL |  |  |  | 0
[31 empty] | TOTAL FOR RPJ OLD JOB |  |  | 6979.6778
[28 empty] | Total Amount (AED) |  |  | 2357018.2057
Note on Z767: Himal Kosala: 26 rate for heavy duty cradle landing platform with full level access platform to the existing scaffolding of CHS - refer WA-C002-R1
Note on O780: Himal Kosala: 50% only
Note on Y780: Himal Kosala: Half Dismantal item
Note on H873: Himal Kosala: Please check the type
Note on H875: Himal Kosala: This is a mobile tower
Note on H885: Himal Kosala: Check this
Note on AE1034: Himal Kosala: Full Dismantle Cost cover under original item
Note on AE1036: Himal Kosala: Full Dismantle Cost cover under original item
Note on AE1040: Himal Kosala: Full Dismantle Cost cover under original item
Note on AE1041: Himal Kosala: Full Dismantle Cost cover under original item
Note on AE1043: Himal Kosala: Full Dismantle Cost cover under original item
Note on AE1044: Himal Kosala: Full Dismantle Cost cover under original item
Note on AE1046: Himal Kosala: Full Dismantle Cost cover under original item
Note on AE1048: Himal Kosala: Full Dismantle Cost cover under original item
Note on AE1116: Himal Kosala: Full Dismantle Cost cover under original item
Note on AE1118: Himal Kosala: Full Dismantle Cost cover under original item
Note on D2379: Himal Kosala: Correct No 14505
Note on AE2390: Himal Kosala: Full Dismantle Cost cover under original item

## DW - Scaffolder
ITEM NO -22 DORCHESTER HOTEL - DAY WORK SHEET - FOR SCAFFOLDER CONTRACT NO - 201A2202
Variation no. | Date | Description | No of Scaffolder | Hours | Total Hours | Rate | Total Amount
6402 | 2022-05-05 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
6403 | 2022-05-06 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
6404 | 2022-05-08 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
6405 | 2022-05-09 | Modification Of Scaffolding | 11 | 10 | 110 | 16 | 1760
6408 | 2022-05-10 | Modification Of Scaffolding | 12 | 10 | 120 | 16 | 1920
6406 | 2022-05-11 | Modification Of Scaffolding | 12 | 10 | 120 | 16 | 1920
6410 | 2022-05-12 | Modification Of Scaffolding | 12 | 10 | 120 | 16 | 1920
6411 | 2022-05-13 | Modification Of Scaffolding | 12 | 10 | 120 | 16 | 1920
6412 | 2022-05-17 | Modification Of Scaffolding | 15 | 14 | 210 | 16 | 3360
6413 | 2022-05-18 | Modification Of Scaffolding | 8 | 10 | 80 | 16 | 1280
6423 | 2022-05-18 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
6417 | 2022-05-19 | Modification Of Scaffolding | 8 | 10 | 80 | 16 | 1280
6418 | 2022-05-19 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
6416 | 2022-05-19 | Modification Of Scaffolding | 10 | 10 | 100 | 16 | 1600
6420 | 2022-05-19 | Modification Of Scaffolding | 10 | 10 | 100 | 16 | 1600
6424 | 2022-05-20 | Modification Of Scaffolding | 9 | 10 | 90 | 16 | 1440
6425 | 2022-05-20 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
6427 | 2022-05-20 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
6428 | 2022-05-22 | Modification Of Scaffolding | 9 | 10 | 90 | 16 | 1440
6429 | 2022-05-22 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
6433 | 2022-05-23 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
6432 | 2022-05-23 | Modification Of Scaffolding | 9 | 10 | 90 | 16 | 1440
6434 | 2022-05-23 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
6435 | 2022-05-24 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
6438 | 2022-05-24 | Modification Of Scaffolding | 8 | 10 | 80 | 16 | 1280
6439 | 2022-05-24 | Modification Of Scaffolding | 8 | 10 | 80 | 16 | 1280
6440 | 2022-05-25 | Modification Of Scaffolding | 10 | 10 | 100 | 16 | 1600
6441 | 2022-05-25 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
6442 | 2022-05-25 | Modification Of Scaffolding | 8 | 10 | 80 | 16 | 1280
6443 | 2022-05-25 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
6444 | 2022-05-26 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
6446 | 2022-05-26 | Modification Of Scaffolding | 13 | 10 | 130 | 16 | 2080
6447 | 2022-05-26 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
6488 | 2022-05-27 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
6449 | 2022-05-27 | Modification Of Scaffolding | 12 | 10 | 120 | 16 | 1920
6450 | 2022-05-27 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
6953 | 2022-05-29 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
6952 | 2022-05-29 | Modification Of Scaffolding | 5 | 6 | 30 | 16 | 480
6951 | 2022-05-29 | Modification Of Scaffolding | 10 | 10 | 100 | 16 | 1600
6958 | 2022-05-30 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
6954 | 2022-05-30 | Modification Of Scaffolding | 4 | 5 | 20 | 16 | 320
6957 | 2022-05-31 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
6956 | 2022-05-31 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
6959 | 2022-06-01 | Modification Of Scaffolding | 12 | 10 | 120 | 16 | 1920
6960 | 2022-06-01 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
6961 | 2022-06-01 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
6962 | 2022-06-02 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
6963 | 2022-06-02 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
6964 | 2022-06-03 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
6965 | 2022-06-03 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
6966 | 2022-06-03 | Modification Of Scaffolding | 2 | 3 | 6 | 16 | 96
6967 | 2022-06-05 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
6968 | 2022-06-05 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
6969 | 2022-06-05 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
6970 | 2022-06-05 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
6971 | 2022-06-06 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
6972 | 2022-06-06 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
6973 | 2022-06-07 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
6974 | 2022-06-07 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
6975 | 2022-06-07 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
6976 | 2022-06-07 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
6977 | 2022-06-08 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
6978 | 2022-06-08 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
6979 | 2022-06-08 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
6980 | 2022-06-09 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
6981 | 2022-06-09 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
6982 | 2022-06-09 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
6983 | 2022-06-09 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
6984 | 2022-06-10 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
6985 | 2022-06-10 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
6986 | 2022-06-10 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
6987 | 2022-06-10 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
6988 | 2022-06-12 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
6989 | 2022-06-12 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
6990 | 2022-06-12 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
6991 | 2022-06-13 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
6992 | 2022-06-13 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
6993 | 2022-06-13 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
6994 | 2022-06-14 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
6995 | 2022-06-14 | Modification Of Scaffolding | 7 | 10 | 70 | 16 | 1120
6996 | 2022-06-14 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
6997 | 2022-06-14 | Modification Of Scaffolding | 2 | 6 | 12 | 16 | 192
6998 | 2022-06-15 | Modification Of Scaffolding | 7 | 10 | 70 | 16 | 1120
6999 | 2022-06-15 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7000 | 2022-06-14 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
3760 | 2022-06-15 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
3761 | 2022-06-16 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
3762 | 2022-06-16 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
3764 | 2022-06-17 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
3765 | 2022-06-17 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
3766 | 2022-06-17 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
3767 | 2022-06-19 | Modification Of Scaffolding | 8 | 10 | 80 | 16 | 1280
3768 | 2022-06-19 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
3769 | 2022-06-19 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
3770 | 2022-06-19 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
3771 | 2022-06-20 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
3772 | 2022-06-20 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
3773 | 2022-06-20 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
3774 | 2022-06-21 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
3775 | 2022-06-21 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
3776 | 2022-06-22 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
3777 | 2022-06-22 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
3778 | 2022-06-22 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
3779 | 2022-06-22 | Modification Of Scaffolding | 8 | 10 | 80 | 16 | 1280
3780 | 2022-06-23 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
3781 | 2022-06-23 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
3782 | 2022-06-23 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
3783 | 2022-06-23 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
3784 | 2022-06-23 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
3785 | 2022-06-24 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
3786 | 2022-06-24 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
3787 | 2022-06-24 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
3788 | 2022-06-24 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
3789 | 2022-06-26 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
3790 | 2022-06-25 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
3791 | 2022-06-26 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
3792 | 2022-06-26 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
3794 | 2022-06-27 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
3793 | 2022-06-26 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
3795 | 2022-06-28 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
3796 | 2022-06-27 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
3798 | 2022-06-28 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
3799 | 2022-06-28 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
3800 | 2022-06-29 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7101 | 2022-06-29 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7102 | 2022-06-29 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7103 | 2022-06-30 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7104 | 2022-07-01 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7105 | 2022-07-01 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7106 | 2022-07-03 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7111 | 2022-07-04 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7110 | 2022-07-04 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7109 | 2022-07-04 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7108 | 2022-07-04 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7107 | 2022-07-04 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7112 | 2022-07-07 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7113 | 2022-07-07 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7114 | 2022-07-11 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7115 | 2022-07-12 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7116 | 2022-07-13 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7117 | 2022-07-14 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7120 | 2022-07-14 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7118 | 2022-07-15 | Modification Of Scaffolding | 8 | 10 | 80 | 16 | 1280
7119 | 2022-07-15 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7121 | 2022-07-17 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7122 | 2022-07-17 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
7123 | 2022-07-18 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7124 | 2022-07-19 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7125 | 2022-07-19 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7126 | 2022-07-19 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7127 | 2022-07-18 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7128 | 2022-07-19 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7129 | 2022-07-20 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7130 | 2022-07-20 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7131 | 2022-07-20 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7132 | 2022-07-21 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
7133 | 2022-07-22 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7134 | 2022-07-22 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7135 | 2022-07-22 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
7136 | 2022-07-23 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7138 | 2022-07-23 | Modification Of Scaffolding | 4 | 6 | 24 | 16 | 384
7139 | 2022-07-24 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7141 | 2022-07-25 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7142 | 2022-07-25 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7143 | 2022-07-26 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7140 | 2022-07-26 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7144 | 2022-07-26 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7145 | 2022-07-27 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7147 | 2022-07-27 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7146 | 2022-07-28 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7137 | 2022-07-28 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7148 | 2022-07-29 | Modification Of Scaffolding | 8 | 10 | 80 | 16 | 1280
7149 | 2022-07-30 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7152 | 2022-07-31 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7157 | 2022-08-01 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7151 | 2022-08-02 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7153 | 2022-08-02 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7155 | 2022-08-03 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7154 | 2022-08-03 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7160 | 2022-08-03 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7162 | 2022-08-04 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7161 | 2022-08-04 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7159 | 2022-08-04 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7158 | 2022-08-04 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7163 | 2022-08-05 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7164 | 2022-08-06 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7165 | 2022-08-06 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7173 | 2022-08-07 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7156 | 2022-08-09 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7166 | 2022-08-09 | Modification Of Scaffolding | 8 | 10 | 80 | 16 | 1280
7168 | 2022-08-09 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7169 | 2022-08-09 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7170 | 2022-08-09 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7172 | 2022-08-10 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7171 | 2022-08-10 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7167 | 2022-08-10 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
7175 | 2022-08-11 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7174 | 2022-08-11 | Modification Of Scaffolding | 9 | 10 | 90 | 16 | 1440
7176 | 2022-08-11 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7179 | 2022-08-12 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7177 | 2022-08-12 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7180 | 2022-08-13 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7182 | 2022-08-13 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7196 | 2022-08-13 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7181 | 2022-08-13 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7183 | 2022-08-13 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7186 | 2022-08-15 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7184 | 2022-08-15 | Modification Of Scaffolding | 15 | 10 | 150 | 16 | 2400
7185 | 2022-08-15 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
7187 | 2022-08-15 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7197 | 2022-08-16 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7188 | 2022-08-16 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7189 | 2022-08-16 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7191 | 2022-08-17 | Modification Of Scaffolding | 8 | 10 | 80 | 16 | 1280
7192 | 2022-08-17 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7193 | 2022-08-17 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7194 | 2022-08-18 | Modification Of Scaffolding | 10 | 10 | 100 | 16 | 1600
7195 | 2022-08-18 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7198 | 2022-08-18 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7199 | 2022-08-19 | Modification Of Scaffolding | 10 | 10 | 100 | 16 | 1600
7200 | 2022-08-19 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7202 | 2022-08-19 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7201 | 2022-08-19 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7206 | 2022-08-19 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7205 | 2022-08-20 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
7204 | 2022-08-20 | Modification Of Scaffolding | 10 | 10 | 100 | 16 | 1600
7203 | 2022-08-20 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7207 | 2022-08-22 | Modification Of Scaffolding | 11 | 10 | 110 | 16 | 1760
7208 | 2022-08-22 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7209 | 2022-08-22 | Modification Of Scaffolding | 9 | 10 | 90 | 16 | 1440
7210 | 2022-08-23 | Modification Of Scaffolding | 10 | 10 | 100 | 16 | 1600
7211 | 2022-08-23 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7212 | 2022-08-23 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
7213 | 2022-08-24 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7214 | 2022-08-24 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7216 | 2022-08-24 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7215 | 2022-08-24 | Modification Of Scaffolding | 8 | 10 | 80 | 16 | 1280
7217 | 2022-08-24 | Modification Of Scaffolding | 9 | 10 | 90 | 16 | 1440
7220 | 2022-08-25 | Modification Of Scaffolding | 8 | 10 | 80 | 16 | 1280
7218 | 2022-08-25 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7221 | 2022-08-25 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7219 | 2022-08-25 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7222 | 2022-08-26 | Modification Of Scaffolding | 8 | 10 | 80 | 16 | 1280
7223 | 2022-08-26 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7224 | 2022-08-26 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
7225 | 2022-08-26 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7226 | 2022-08-27 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
7227 | 2022-08-27 | Modification Of Scaffolding | 8 | 10 | 80 | 16 | 1280
7228 | 2022-08-27 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7229 | 2022-08-27 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7230 | 2022-08-29 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7231 | 2022-08-29 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7232 | 2022-08-29 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7233 | 2022-08-29 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7234 | 2022-08-30 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7235 | 2022-08-30 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
7236 | 2022-08-30 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7237 | 2022-08-30 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
7238 | 2022-08-30 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7240 | 2022-08-31 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7241 | 2022-08-31 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7242 | 2022-08-31 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7243 | 2022-08-31 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7244 | 2022-08-31 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
7247 | 2022-09-01 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7246 | 2022-09-01 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7248 | 2022-09-01 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
7249 | 2022-09-01 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
7250 | 2022-09-02 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
6151 | 2022-09-02 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
6152 | 2022-09-02 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
6153 | 2022-09-02 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
6154 | 2022-09-03 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
6155 | 2022-09-03 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
6156 | 2022-09-03 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
6157 | 2022-09-03 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
6158 | 2022-09-03 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
6159 | 2022-09-05 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
6160 | 2022-09-05 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
6161 | 2022-09-05 | Modification Of Scaffolding | 8 | 10 | 80 | 16 | 1280
6162 | 2022-09-05 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
6163 | 2022-09-06 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
6164 | 2022-09-06 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
6165 | 2022-09-06 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
6166 | 2022-09-07 | Modification Of Scaffolding | 10 | 10 | 100 | 16 | 1600
6167 | 2022-09-07 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
6168 | 2022-09-07 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
6169 | 2022-09-07 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
6170 | 2022-09-08 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
6171 | 2022-09-08 | Modification Of Scaffolding | 7 | 10 | 70 | 16 | 1120
6172 | 2022-09-08 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
6173 | 2022-09-08 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
6174 | 2022-09-08 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
6175 | 2022-09-08 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
6176 | 2022-09-09 | Modification Of Scaffolding | 8 | 10 | 80 | 16 | 1280
6177 | 2022-09-09 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
6178 | 2022-09-08 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
6179 | 2022-09-09 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
6180 | 2022-09-09 | Modification Of Scaffolding | 10 | 10 | 100 | 16 | 1600
6181 | 2022-09-10 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
6182 | 2022-09-10 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
6183 | 2022-09-10 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
6184 | 2022-09-10 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
6185 | 2022-09-10 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
6187 | 2022-09-11 | Modification Of Scaffolding | 7 | 10 | 70 | 16 | 1120
6188 | 2022-09-12 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
6190 | 2022-09-12 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
6189 | 2022-09-11 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
6191 | 2022-09-12 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
6193 | 2022-09-12 | Modification Of Scaffolding | 7 | 10 | 70 | 16 | 1120
6195 | 2022-09-12 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
6192 | 2022-09-13 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
6194 | 2022-09-13 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
6198 | 2022-09-14 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
6200 | 2022-09-14 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7252 | 2022-09-15 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7251 | 2022-09-15 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
6196 | 2022-09-13 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
6197 | 2022-09-14 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
6199 | 2022-09-14 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7253 | 2022-09-15 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7254 | 2022-09-15 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7255 | 2022-09-15 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7256 | 2022-09-16 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7257 | 2022-09-16 | Modification Of Scaffolding | 3 | 5 | 15 | 16 | 240
7257 | 2022-09-16 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7258 | 2022-09-16 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7260 | 2022-09-16 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7261 | 2022-09-17 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7262 | 2022-09-17 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7263 | 2022-09-17 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7264 | 2022-09-17 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
7269 | 2022-09-18 | Modification Of Scaffolding | 10 | 10 | 100 | 16 | 1600
7267 | 2022-09-19 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7268 | 2022-09-19 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7259 | 2022-09-19 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7270 | 2022-09-19 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7273 | 2022-09-19 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7274 | 2022-09-19 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7280 | 2022-09-20 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7271 | 2022-09-20 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7272 | 2022-09-20 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7275 | 2022-09-20 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7276 | 2022-09-21 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7277 | 2022-09-21 | Modification Of Scaffolding | 9 | 10 | 90 | 16 | 1440
7278 | 2022-09-21 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7279 | 2022-09-21 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7282 | 2022-09-21 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
7281 | 2022-09-22 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7283 | 2022-09-22 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7284 | 2022-09-22 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7285 | 2022-09-22 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7286 | 2022-09-22 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7295 | 2022-09-22 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7287 | 2022-09-23 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7288 | 2022-09-24 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7290 | 2022-09-24 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
7291 | 2022-09-26 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7292 | 2022-09-26 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7293 | 2022-09-25 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7294 | 2022-09-27 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7289 | 2022-09-24 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7301 | 2022-09-26 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7296 | 2022-09-27 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7299 | 2022-09-27 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7298 | 2022-09-28 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7297 | 2022-09-28 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7304 | 2022-09-28 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7302 | 2022-09-29 | Modification Of Scaffolding | 0 | 10 | 0 | 16 | 0
7303 | 2022-09-29 | Modification Of Scaffolding | 8 | 10 | 80 | 16 | 1280
7305 | 2022-09-29 | Modification Of Scaffolding | 8 | 10 | 80 | 16 | 1280
7308 | 2022-09-30 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7307 | 2022-09-30 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
7306 | 2022-09-30 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7309 | 2022-10-01 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7311 | 2022-10-03 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7310 | 2022-10-03 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
7312 | 2022-10-03 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7313 | 2022-10-04 | Modification Of Scaffolding | 7 | 10 | 70 | 16 | 1120
7314 | 2022-10-04 | Modification Of Scaffolding | 7 | 10 | 70 | 16 | 1120
7315 | 2022-10-04 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7316 | 2022-10-05 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7317 | 2022-10-05 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7319 | 2022-10-05 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7322 | 2022-10-06 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7318 | 2022-10-06 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7320 | 2022-10-07 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7321 | 2022-10-07 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7266 | 2022-10-08 | Modification Of Scaffolding | 10 | 10 | 100 | 16 | 1600
7265 | 2022-10-08 | Modification Of Scaffolding | 10 | 10 | 100 | 16 | 1600
7323 | 2022-10-10 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7343 | 2022-10-10 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7325 | 2022-10-10 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7324 | 2022-10-10 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
7326 | 2022-10-10 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
7327 | 2022-10-11 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7328 | 2022-10-11 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7329 | 2022-10-11 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7331 | 2022-10-11 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7333 | 2022-10-12 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7332 | 2022-10-12 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7330 | 2022-10-12 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7334 | 2022-10-13 | Modification Of Scaffolding | 7 | 10 | 70 | 16 | 1120
7338 | 2022-10-13 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7337 | 2022-10-14 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7335 | 2022-10-14 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7339 | 2022-10-15 | Modification Of Scaffolding | 8 | 10 | 80 | 16 | 1280
7341 | 2022-10-15 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7336 | 2022-10-14 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7345 | 2022-10-16 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
7342 | 2022-10-17 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7340 | 2022-10-17 | Modification Of Scaffolding | 7 | 10 | 70 | 16 | 1120
7344 | 2022-10-18 | Modification Of Scaffolding | 7 | 10 | 70 | 16 | 1120
7346 | 2022-10-18 | Modification Of Scaffolding | 8 | 10 | 80 | 16 | 1280
7347 | 2022-10-18 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7358 | 2022-10-19 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7357 | 2022-10-19 | Modification Of Scaffolding | 8 | 10 | 80 | 16 | 1280
7348 | 2022-10-19 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7349 | 2022-10-19 | Modification Of Scaffolding | 8 | 10 | 80 | 16 | 1280
7350 | 2022-10-19 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7354 | 2022-10-19 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7356 | 2022-10-20 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7355 | 2022-10-20 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7353 | 2022-10-20 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7351 | 2022-10-20 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
7352 | 2022-10-20 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7363 | 2022-10-20 | Modification Of Scaffolding | 7 | 10 | 70 | 16 | 1120
7362 | 2022-10-21 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7361 | 2022-10-21 | Modification Of Scaffolding | 7 | 10 | 70 | 16 | 1120
7359 | 2022-10-21 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7360 | 2022-10-21 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7366 | 2022-10-22 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7365 | 2022-10-22 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
7364 | 2022-10-22 | Modification Of Scaffolding | 8 | 10 | 80 | 16 | 1280
7367 | 2022-10-24 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7369 | 2022-10-24 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7370 | 2022-10-24 | Modification Of Scaffolding | 7 | 10 | 70 | 16 | 1120
7371 | 2022-10-25 | Modification Of Scaffolding | 11 | 10 | 110 | 16 | 1760
7373 | 2022-10-25 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7374 | 2022-10-25 | Modification Of Scaffolding | 10 | 10 | 100 | 16 | 1600
7368 | 2022-10-25 | Modification Of Scaffolding | 8 | 10 | 80 | 16 | 1280
7375 | 2022-10-26 | Modification Of Scaffolding | 12 | 10 | 120 | 16 | 1920
7376 | 2022-10-26 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
7377 | 2022-10-26 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7378 | 2022-10-26 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7379 | 2022-10-27 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7380 | 2022-10-27 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7381 | 2022-10-27 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7382 | 2022-10-27 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7383 | 2022-10-28 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7384 | 2022-10-27 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7385 | 2022-10-28 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7386 | 2022-10-28 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7387 | 2022-10-28 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7427 | 2022-10-28 | Modification Of Scaffolding | 17 | 10 | 170 | 16 | 2720
7388 | 2022-10-28 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7389 | 2022-10-29 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7390 | 2022-10-29 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7393 | 2022-10-29 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7428 | 2022-10-29 | Modification Of Scaffolding | 10 | 10 | 100 | 16 | 1600
7392 | 2022-10-31 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7391 | 2022-10-31 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7398 | 2022-10-31 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
7394 | 2022-11-01 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7395 | 2022-11-11 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7396 | 2022-11-01 | Modification Of Scaffolding | 10 | 10 | 100 | 16 | 1600
7397 | 2022-11-01 | Modification Of Scaffolding | 3 | 8 | 24 | 16 | 384
7399 | 2022-11-02 | Modification Of Scaffolding | 4 | 9 | 36 | 16 | 576
7401 | 2022-11-02 | Modification Of Scaffolding | 10 | 9 | 90 | 16 | 1440
7402 | 2022-11-02 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7404 | 2022-11-02 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7405 | 2022-11-02 | Modification Of Scaffolding | 2 | 8 | 16 | 16 | 256
7406 | 2022-11-02 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7407 | 2022-11-02 | Modification Of Scaffolding | 2 | 8 | 16 | 16 | 256
7408 | 2022-11-03 | Modification Of Scaffolding | 12 | 10 | 120 | 16 | 1920
7409 | 2022-11-03 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7410 | 2022-11-03 | Modification Of Scaffolding | 4 | 9 | 36 | 16 | 576
7411 | 2022-11-03 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7412 | 2022-11-04 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7413 | 2022-11-04 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7414 | 2022-11-04 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7415 | 2022-11-04 | Modification Of Scaffolding | 13 | 9 | 117 | 16 | 1872
7416 | 2022-11-05 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7417 | 2022-11-05 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7420 | 2022-11-05 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7419 | 2022-11-05 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7418 | 2022-11-05 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7422 | 2022-11-07 | Modification Of Scaffolding | 8 | 10 | 80 | 16 | 1280
7423 | 2022-11-07 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7421 | 2022-11-07 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7426 | 2022-11-08 | Modification Of Scaffolding | 2 | 9 | 18 | 16 | 288
7425 | 2022-11-08 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7424 | 2022-11-08 | Modification Of Scaffolding | 9 | 9 | 81 | 16 | 1296
7430 | 2022-11-08 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7431 | 2022-11-08 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7429 | 2022-11-09 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7432 | 2022-11-09 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7433 | 2022-11-09 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
7434 | 2022-11-09 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7435 | 2022-11-10 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7437 | 2022-11-10 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7438 | 2022-11-10 | Modification Of Scaffolding | 2 | 8 | 16 | 16 | 256
7440 | 2022-11-10 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7441 | 2022-11-11 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7439 | 2022-11-11 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7442 | 2022-11-11 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7443 | 2022-11-12 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7445 | 2022-11-12 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7446 | 2022-11-12 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7447 | 2022-11-12 | Modification Of Scaffolding | 2 | 9 | 18 | 16 | 288
7450 | 2022-11-12 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7448 | 2022-11-12 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7501 | 2022-11-14 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
7502 | 2022-11-14 | Modification Of Scaffolding | 1 | 5 | 5 | 16 | 80
7503 | 2022-11-14 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7504 | 2022-11-15 | Modification Of Scaffolding | 2 | 4 | 8 | 16 | 128
7508 | 2022-11-15 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7507 | 2022-11-16 | Modification Of Scaffolding | 2 | 6 | 12 | 16 | 192
7506 | 2022-11-16 | Modification Of Scaffolding | 4 | 8 | 32 | 16 | 512
7509 | 2022-11-16 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7505 | 2022-11-16 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7512 | 2022-11-17 | Modification Of Scaffolding | 4 | 8 | 32 | 16 | 512
7513 | 2022-11-17 | Modification Of Scaffolding | 2 | 8 | 16 | 16 | 256
7510 | 2022-11-17 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7511 | 2022-11-17 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7514 | 2022-11-18 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7515 | 2022-11-18 | Modification Of Scaffolding | 3 | 8 | 24 | 16 | 384
7517 | 2022-11-18 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7519 | 2022-11-19 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7516 | 2022-11-19 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7518 | 2022-11-19 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7521 | 2022-11-21 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7526 | 2022-11-22 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7523 | 2022-11-21 | Modification Of Scaffolding | 1 | 9 | 9 | 16 | 144
7522 | 2022-11-21 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7520 | 2022-11-21 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7525 | 2022-11-22 | Modification Of Scaffolding | 8 | 10 | 80 | 16 | 1280
7524 | 2022-11-22 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7527 | 2022-11-23 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7528 | 2022-11-23 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7529 | 2022-11-23 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
7531 | 2022-11-23 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7532 | 2022-11-24 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
7533 | 2022-11-24 | Modification Of Scaffolding | 10 | 10 | 100 | 16 | 1600
7530 | 2022-11-24 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7534 | 2022-11-25 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7537 | 2022-11-25 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7536 | 2022-11-25 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7535 | 2022-11-25 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
7538 | 2022-11-26 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7539 | 2022-11-26 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7540 | 2022-11-26 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7541 | 2022-11-28 | Modification Of Scaffolding | 2 | 9 | 18 | 16 | 288
7542 | 2022-11-28 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7543 | 2022-11-28 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7544 | 2022-11-28 | Modification Of Scaffolding | 3 | 4 | 12 | 16 | 192
7547 | 2022-11-28 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7551 | 2022-11-29 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7545 | 2022-11-29 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7548 | 2022-11-29 | Modification Of Scaffolding | 2 | 9 | 18 | 16 | 288
7549 | 2022-11-29 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7550 | 2022-11-29 | Modification Of Scaffolding | 10 | 10 | 100 | 16 | 1600
7552 | 2022-11-29 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7553 | 2022-11-29 | Modification Of Scaffolding | 5 | 4 | 20 | 16 | 320
7554 | 2022-11-30 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7555 | 2022-11-30 | Modification Of Scaffolding | 2 | 9 | 18 | 16 | 288
7556 | 2022-11-30 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7557 | 2022-11-30 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7558 | 2022-11-30 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7559 | 2022-11-30 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7560 | 2022-12-03 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7564 | 2022-12-05 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7563 | 2022-12-05 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7562 | 2022-12-05 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7561 | 2022-12-05 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7565 | 2022-12-05 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7567 | 2022-12-06 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7568 | 2022-12-06 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7569 | 2022-12-06 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7572 | 2022-12-07 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7570 | 2022-12-07 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7571 | 2022-12-07 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7573 | 2022-12-07 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7574 | 2022-12-08 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7575 | 2022-12-08 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7581 | 2022-12-09 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7576 | 2022-12-09 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7577 | 2022-12-09 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7579 | 2022-12-09 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7588 | 2022-12-09 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7578 | 2022-12-09 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7585 | 2022-12-09 | Modification Of Scaffolding | 4 | 4 | 16 | 16 | 256
7586 | 2022-12-10 | Modification Of Scaffolding | 7 | 10 | 70 | 16 | 1120
7593 | 2022-12-10 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7583 | 2022-12-10 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7583 | 2022-12-10 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7594 | 2022-12-12 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
7595 | 2022-12-12 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7592 | 2022-12-12 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7590 | 2022-12-12 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7591 | 2022-12-12 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7566 | 2022-12-13 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7599 | 2022-12-13 | Modification Of Scaffolding | 2 | 4 | 8 | 16 | 128
7596 | 2022-12-13 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7597 | 2022-12-13 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7598 | 2022-12-13 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7708 | 2022-12-14 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
7707 | 2022-12-14 | Modification Of Scaffolding | 8 | 10 | 80 | 16 | 1280
7705 | 2022-12-14 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7704 | 2022-12-14 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7709 | 2022-12-15 | Modification Of Scaffolding | 11 | 10 | 110 | 16 | 1760
7718 | 2022-12-15 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7712 | 2022-12-15 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7711 | 2022-12-15 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
7710 | 2022-12-15 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7717 | 2022-12-16 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7716 | 2022-12-16 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7714 | 2022-12-16 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7715 | 2022-12-16 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7713 | 2022-12-16 | Modification Of Scaffolding | 9 | 10 | 90 | 16 | 1440
7720 | 2022-12-17 | Modification Of Scaffolding | 10 | 10 | 100 | 16 | 1600
7719 | 2022-12-17 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7723 | 2022-12-17 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7722 | 2022-12-17 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7721 | 2022-12-17 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7724 | 2022-12-19 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7725 | 2022-12-19 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7726 | 2022-12-19 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
7727 | 2022-12-19 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7728 | 2022-12-19 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7732 | 2022-12-19 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7731 | 2022-12-20 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7729 | 2022-12-20 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7730 | 2022-12-20 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7733 | 2022-12-21 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7734 | 2022-12-21 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7734 | 2022-12-21 | Modification Of Scaffolding | 1 | 5 | 5 | 16 | 80
7735 | 2022-12-22 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7736 | 2022-12-22 | Modification Of Scaffolding | 11 | 10 | 110 | 16 | 1760
7737 | 2022-12-23 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7738 | 2022-12-24 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7739 | 2022-12-24 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7740 | 2022-12-24 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7741 | 2022-12-24 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7742 | 2022-12-24 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7743 | 2022-12-26 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7744 | 2022-12-26 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7745 | 2022-12-26 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7746 | 2022-12-26 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7605 | 2022-12-26 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7750 | 2022-12-27 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7749 | 2022-10-27 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7748 | 2022-12-27 | Modification Of Scaffolding | 11 | 10 | 110 | 16 | 1760
7603 | 2022-12-27 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7602 | 2022-12-27 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7747 | 2022-12-26 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7604 | 2022-12-27 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7609 | 2022-12-28 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7608 | 2023-12-28 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7607 | 2023-12-28 | Modification Of Scaffolding | 10 | 10 | 100 | 16 | 1600
7606 | 2022-12-28 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7611 | 2022-12-29 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7610 | 2022-12-29 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7612 | 2022-12-29 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7614 | 2022-12-30 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7613 | 2022-12-30 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7616 | 2022-12-31 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7623 | 2022-12-31 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7617 | 2022-12-31 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7618 | 2022-12-31 | Modification Of Scaffolding | 2 | 8 | 16 | 16 | 256
7615 | 2022-12-31 | Modification Of Scaffolding | 4 | 8 | 32 | 16 | 512
7621 | 2023-01-02 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7619 | 2023-01-02 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7620 | 2023-01-02 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7622 | 2023-01-02 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7626 | 2023-01-03 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7624 | 2023-01-03 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7627 | 2023-01-03 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7625 | 2023-01-03 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7634 | 2023-01-04 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7632 | 2023-01-04 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7631 | 2023-01-04 | Modification Of Scaffolding | 2 | 8 | 16 | 16 | 256
7630 | 2023-01-04 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7629 | 2023-01-04 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7637 | 2023-01-05 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7635 | 2023-01-05 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7640 | 2023-01-06 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7638 | 2023-01-05 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7636 | 2023-01-05 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7644 | 2023-01-06 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7643 | 2023-01-06 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7642 | 2023-01-06 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7641 | 2023-01-06 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7639 | 2023-01-06 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7646 | 2023-01-07 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7645 | 2023-01-07 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7647 | 2023-01-07 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7649 | 2023-01-07 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7657 | 2023-01-07 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7656 | 2023-01-07 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
7652 | 2023-01-08 | Modification Of Scaffolding | 2 | 8 | 16 | 16 | 256
7650 | 2023-01-08 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7655 | 2023-01-09 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7654 | 2023-01-09 | Modification Of Scaffolding | 2 | 6 | 12 | 16 | 192
7663 | 2023-01-09 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7653 | 2023-01-09 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
7659 | 2023-01-10 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7660 | 2023-01-10 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7661 | 2023-01-10 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7662 | 2023-01-10 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
7664 | 2023-01-10 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7668 | 2023-01-11 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7665 | 2023-01-11 | Modification Of Scaffolding | 8 | 10 | 80 | 16 | 1280
7666 | 2023-01-11 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7670 | 2023-01-11 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7669 | 2023-01-11 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7667 | 2023-01-11 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7671 | 2023-01-12 | Modification Of Scaffolding | 8 | 10 | 80 | 16 | 1280
7673 | 2023-01-12 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7672 | 2023-01-12 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
7674 | 2023-01-12 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7675 | 2023-01-12 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7680 | 2023-01-13 | Modification Of Scaffolding | 12 | 6 | 72 | 16 | 1152
7678 | 2023-01-13 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7677 | 2023-01-13 | Modification Of Scaffolding | 8 | 10 | 80 | 16 | 1280
7676 | 2023-01-13 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7679 | 2023-01-13 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7687 | 2023-01-14 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7686 | 2023-01-14 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
7685 | 2023-01-14 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
7684 | 2023-01-14 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7682 | 2023-01-14 | Modification Of Scaffolding | 2 | 8 | 16 | 16 | 256
7683 | 2023-01-14 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7681 | 2023-01-14 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7688 | 2023-01-15 | Modification Of Scaffolding | 10 | 10 | 100 | 16 | 1600
7690 | 2023-01-16 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7691 | 2023-01-16 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7692 | 2023-01-16 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7689 | 2023-01-16 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7693 | 2023-01-17 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7694 | 2023-01-17 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7695 | 2023-01-17 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7696 | 2023-01-17 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7700 | 2023-01-18 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7801 | 2023-01-18 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7698 | 2023-01-18 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7697 | 2023-01-18 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7699 | 2023-01-18 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7802 | 2023-01-19 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7806 | 2023-01-19 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7804 | 2023-01-19 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7803 | 2023-01-19 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7811 | 2023-01-20 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7807 | 2023-01-20 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7810 | 2023-01-20 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7808 | 2023-01-20 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7809 | 2023-01-20 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7816 | 2023-01-21 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7815 | 2023-01-21 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
7814 | 2023-01-21 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7813 | 2023-01-21 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7812 | 2023-01-21 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7820 | 2023-01-23 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7817 | 2023-01-23 | Modification Of Scaffolding | 8 | 10 | 80 | 16 | 1280
7818 | 2023-01-23 | Modification Of Scaffolding | 7 | 10 | 70 | 16 | 1120
7819 | 2023-01-23 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7821 | 2023-01-23 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7822 | 2023-01-24 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7825 | 2023-01-24 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7824 | 2023-01-24 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7823 | 2023-01-24 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7831 | 2023-01-25 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
7830 | 2023-01-25 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
7829 | 2023-01-25 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7828 | 2023-01-25 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7827 | 2023-01-25 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7826 | 2023-01-25 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7835 | 2023-01-26 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7836 | 2023-01-26 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7834 | 2023-01-26 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7833 | 2023-01-26 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7832 | 2023-01-26 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7837 | 2023-01-27 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7839 | 2023-01-27 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7838 | 2023-01-27 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7842 | 2023-01-28 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7849 | 2023-01-28 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
7848 | 2023-01-28 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7847 | 2023-01-28 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7844 | 2023-01-28 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7841 | 2023-01-27 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
7840 | 2023-01-27 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
7845 | 2023-01-28 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7846 | 2023-01-28 | Modification Of Scaffolding | 6 | 10 | 60 | 16 | 960
7843 | 2023-01-28 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7853 | 2023-01-30 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
7851 | 2023-01-30 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7851 | 2023-01-30 | Modification Of Scaffolding | 1 | 5 | 5 | 16 | 80
7854 | 2023-01-30 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7852 | 2023-01-30 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7857 | 2023-01-31 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7856 | 2023-01-31 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7855 | 2023-01-31 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7859 | 2023-01-31 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7858 | 2023-01-31 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7860 | 2023-02-01 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7861 | 2023-02-01 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7862 | 2023-02-01 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7863 | 2023-02-01 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7864 | 2023-02-02 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7867 | 2023-02-02 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7873 | 2023-02-02 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7868 | 2023-02-02 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
7866 | 2023-02-02 | Modification Of Scaffolding | 7 | 10 | 70 | 16 | 1120
7865 | 2023-02-02 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7875 | 2023-02-02 | Modification Of Scaffolding | 6 | 6 | 36 | 16 | 576
7872 | 2023-02-03 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7871 | 2023-02-03 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
7870 | 2023-02-03 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7869 | 2023-02-03 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7876 | 2023-02-03 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7877 | 2023-02-03 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7884 | 2023-02-03 | Modification Of Scaffolding | 5 | 3 | 15 | 16 | 240
7883 | 2023-02-03 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7882 | 2023-02-04 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7881 | 2023-02-04 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7879 | 2023-02-04 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7878 | 2023-02-04 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7880 | 2023-02-04 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7887 | 2023-02-06 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7890 | 2023-02-06 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7889 | 2023-02-06 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7886 | 2023-02-06 | Modification Of Scaffolding | 5 | 8 | 40 | 16 | 640
7885 | 2023-02-06 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7898 | 2023-02-07 | Modification Of Scaffolding | 4 | 5 | 20 | 16 | 320
7897 | 2023-02-07 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7896 | 2023-02-07 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7893 | 2023-02-07 | Modification Of Scaffolding | 4 | 4 | 16 | 16 | 256
7895 | 2023-02-07 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
7894 | 2023-02-07 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7891 | 2023-02-07 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7892 | 2023-02-07 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7901 | 2023-02-08 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7903 | 2023-02-08 | Modification Of Scaffolding | 4 | 5 | 20 | 16 | 320
7904 | 2023-02-08 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7900 | 2023-02-08 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7899 | 2023-02-08 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7905 | 2023-02-08 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7906 | 2023-02-08 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7917 | 2023-02-09 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7907 | 2023-02-09 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7908 | 2023-02-09 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7909 | 2023-02-09 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7911 | 2023-02-09 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
7913 | 2023-02-10 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7914 | 2023-02-10 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7915 | 2023-02-10 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
7916 | 2023-02-10 | Modification Of Scaffolding | 4 | 5 | 20 | 16 | 320
7918 | 2023-02-10 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7922 | 2023-02-11 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7923 | 2023-02-11 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
7927 | 2023-02-11 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
7921 | 2023-02-11 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7920 | 2023-02-11 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7925 | 2023-02-12 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7932 | 2023-02-13 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7902 | 2023-02-08 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7912 | 2023-02-10 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7926 | 2023-02-11 | Modification Of Scaffolding | 7 | 10 | 70 | 16 | 1120
7919 | 2023-02-11 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7933 | 2023-02-13 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7931 | 2023-02-13 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7930 | 2023-02-13 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7929 | 2023-02-13 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7928 | 2023-02-13 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7942 | 2023-02-14 | Modification Of Scaffolding | 4 | 6 | 24 | 16 | 384
7940 | 2023-02-14 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7935 | 2023-02-14 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7938 | 2023-02-14 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7941 | 2023-02-14 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7937 | 2023-02-14 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7936 | 2023-02-14 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7934 | 2023-02-14 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7949 | 2023-02-15 | Modification Of Scaffolding | 4 | 8 | 32 | 16 | 512
7947 | 2023-02-15 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7945 | 2023-02-15 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7950 | 2023-02-15 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7948 | 2023-02-15 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7946 | 2023-02-15 | Modification Of Scaffolding | 4 | 10 | 10 | 16 | 160
7944 | 2023-02-15 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7952 | 2023-02-15 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7951 | 2023-02-15 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7953 | 2023-02-15 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7943 | 2023-02-15 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7954 | 2023-02-15 | Modification Of Scaffolding | 4 | 8 | 32 | 16 | 512
7955 | 2023-02-16 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7961 | 2023-02-16 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
7960 | 2023-02-16 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7959 | 2023-02-16 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7958 | 2023-02-16 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7957 | 2023-02-16 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7956 | 2023-02-16 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7967 | 2023-02-17 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7965 | 2023-02-17 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7974 | 2023-02-17 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7968 | 2023-02-17 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7966 | 2023-02-17 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7962 | 2023-02-17 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7972 | 2023-02-18 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7969 | 2023-02-18 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7970 | 2023-02-18 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7971 | 2023-02-18 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7975 | 2023-02-18 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7978 | 2023-02-19 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7978 | 2023-02-19 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7977 | 2023-02-19 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7976 | 2023-02-19 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7982 | 2023-02-20 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7980 | 2023-02-20 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7989 | 2023-12-21 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7984 | 2023-02-20 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7983 | 2023-02-20 | Modification Of Scaffolding | 4 | 8 | 32 | 16 | 512
7979 | 2023-02-20 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7985 | 2023-02-20 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7986 | 2023-02-21 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7987 | 2023-02-21 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7988 | 2023-02-21 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7990 | 2023-02-21 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7995 | 2023-02-22 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7994 | 2023-02-22 | Modification Of Scaffolding | 4 | 6 | 24 | 16 | 384
7992 | 2023-02-22 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
7939 | 2023-02-14 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
7964 | 2023-02-17 | Modification Of Scaffolding | 1 | 10 | 10 | 16 | 160
7963 | 2023-02-17 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7973 | 2023-02-18 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7981 | 2023-02-20 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7991 | 2023-02-21 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7998 | 2023-02-22 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7997 | 2023-02-22 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7996 | 2023-02-22 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
8005 | 2023-02-23 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
8004 | 2023-02-23 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
8003 | 2023-02-23 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
8002 | 2023-02-23 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
8001 | 2023-02-23 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
8019 | 2023-02-23 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
8000 | 2023-02-23 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
7999 | 2023-02-23 | Modification Of Scaffolding | 5 | 10 | 50 | 16 | 800
8010 | 2023-02-24 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
8008 | 2023-02-24 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
8007 | 2023-02-24 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
8006 | 2023-02-24 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
8018 | 2023-02-25 | Modification Of Scaffolding | 6 | 6 | 36 | 16 | 576
8016 | 2023-02-25 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
8015 | 2023-02-25 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
8012 | 2023-02-25 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
7993 | 2023-02-22 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
8020 | 2023-02-25 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
8017 | 2023-02-25 | Modification Of Scaffolding | 3 | 10 | 30 | 16 | 480
8013 | 2023-02-25 | Modification Of Scaffolding | 4 | 10 | 40 | 16 | 640
8011 | 2023-02-24 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
8009 | 2023-02-24 | Modification Of Scaffolding | 2 | 10 | 20 | 16 | 320
[5 empty] | 0 |  | 0
|  | Total Amount |  |  | 34470 | 16 | 551520
551520
Note on H374: Himal Kosala: Please get a detaill description for dayworks from KCE

## DW - Forman
ITEM NO - 23 DORCHESTER HOTEL - DAY WORK SHEET - FOR FOREMAN CONTRACT NO - 201A2202
Variation no | Date | Description | No of Foreman | Hours | Total Hours | Rate | Total Amount
6402 | 2022-05-05 | Modification Of Scaffolding | 1 | 10 | 10 | 25 | 250
6403 | 2022-05-06 | Modification Of Scaffolding | 1 | 10 | 10 | 25 | 250
6404 | 2022-05-08 | Modification Of Scaffolding | 1 | 10 | 10 | 25 | 250
6405 | 2022-05-09 | Modification Of Scaffolding | 1 | 10 | 10 | 25 | 250
6408 | 2022-05-10 | Modification Of Scaffolding | 1 | 10 | 10 | 25 | 250
6406 | 2022-05-11 | Modification Of Scaffolding | 1 | 10 | 10 | 25 | 250
6410 | 2022-05-12 | Modification Of Scaffolding | 1 | 10 | 10 | 25 | 250
6411 | 2022-05-13 | Modification Of Scaffolding | 1 | 10 | 10 | 25 | 250
6412 | 2022-05-17 | Modification Of Scaffolding | 1 | 10 | 10 | 25 | 250
6413 | 2022-05-18 | Modification Of Scaffolding | 1 | 10 | 10 | 25 | 250
6423 | 2022-05-18 | Modification Of Scaffolding | 1 | 10 | 10 | 25 | 250
6417 | 2022-05-19 | Modification Of Scaffolding | 1 | 10 | 10 | 25 | 250
6416 | 2022-05-19 | Modification Of Scaffolding | 1 | 10 | 10 | 25 | 250
6420 | 2022-05-19 | Modification Of Scaffolding | 1 | 10 | 10 | 25 | 250
6424 | 2022-05-20 | Modification Of Scaffolding | 1 | 10 | 10 | 25 | 250
6428 | 2022-05-22 | Modification Of Scaffolding | 1 | 10 | 10 | 25 | 250
6432 | 2022-05-23 | Modification Of Scaffolding | 1 | 10 | 10 | 25 | 250
6438 | 2022-05-24 | Modification Of Scaffolding | 1 | 10 | 10 | 25 | 250
6439 | 2022-05-24 | Modification Of Scaffolding | 1 | 10 | 10 | 25 | 250
6440 | 2022-05-25 | Modification Of Scaffolding | 1 | 10 | 10 | 25 | 250
6442 | 2022-05-25 | Modification Of Scaffolding | 1 | 10 | 10 | 25 | 250
6443 | 2022-05-25 | Modification Of Scaffolding | 1 | 10 | 10 | 25 | 250
6446 | 2022-05-26 | Modification Of Scaffolding | 1 | 10 | 10 | 25 | 250
6449 | 2022-05-27 | Modification Of Scaffolding | 1 | 10 | 10 | 25 | 250
6951 | 2022-05-29 | Modification Of Scaffolding | 1 | 10 | 10 | 25 | 250
6959 | 2022-06-01 | Modification Of Scaffolding | 1 | 10 | 10 | 25 | 250
|  | Modification Of Scaffolding |  | 10 | 0 | 25 | 0
[5 empty] | 0 | 25 | 0
|  | Total Amount |  |  | 0 | 25 | 6500

## Ins and tagging
ITEM NO : 24 SCAFFOLDING INSPECTION AND TAGING CONTRACTNO : 201A22002 -E11/K107/SK/DM/008
Item No | Description | L | W | H | m2/m3 | no of tag | Tag nomber | Inspection charges /tag | HandOver Certicate No | Inspection date | Total amount
1 | Scaffolding inspaction and taging | 4 | 1.3 | 5 | 20 | 1 | 1 | 150 | 12051 | 2022-05-05 | 150
|  | 2.5 | 1.3 | 6 | 15
2 | Scaffolding inspaction and taging | 2.5 | 1.3 | 3 | 7.5 | 1 | 2 | 150 | 12502 | 2022-05-05 | 150
Grid 3-4 - H-I ( GF )
3 | Scaffolding inspaction and taging | 2.5 | 1.3 | 5 | 12.5 | 1 | 4 | 150 | 12053 | 2022-05-06 | 150
Level -5 MEP Plant Room
4 | Scaffolding inspaction and taging | 10 | 1.3 | 3 | 30 | 1 | 5 | 150 | 12054 | 2022-05-08 | 150
South East RC Wall
5 | Scaffolding inspaction and taging | 2.5 | 1.3 | 3 | 7.5 | 1 | 7 | 150 | 12055 | 2022-05-08 | 150
Ground Level Toilet area (G17-20)
6 | Scaffolding inspaction and taging | 2.5 | 1.3 | 3 | 7.5 | 1 | 8 | 150 | 12056 | 2022-05-08 | 150
Ground Level Toilet area (G17-20)
7 | Scaffolding inspaction and taging | 12 | 1.3 | 4 | 48 | 1 | 9 | 150 | 12057 | 2022-05-10 | 150
South East Corner RC Wall
8 | Scaffolding inspaction and taging | 2.5 | 1.3 | 5 | 12.5 | 1 | 10 | 150 | 12058 | 2022-05-11 | 150
Level -05 MEP Plant Room
9 | Scaffolding inspaction and taging | 4 | 1.3 | 5 | 20 | 1 | 11 | 150 | 12059 | 2022-05-11 | 150
Level -05 MEP Plant Room
10 | Scaffolding inspaction and taging | 4 | 2.5 | 5.5 | 55 | 1 | 12 | 150 | 12060 | 2021-05-12 | 150
Level -02 Grid B-V 11-19
11 | Scaffolding inspaction and taging | 4 | 1.3 | 4 | 16 | 1 | 13 | 150 | 12061 | 2021-05-12 | 150
Level -05 Residence Tower
12 | Scaffolding inspaction and taging | 12 | 5 | 4 | 240 | 1 | 16 | 150 | 12062 | 2022-05-13 | 150
G Level Back Side First Aid Room
13 | Scaffolding inspaction and taging | 10 | 3 | 4 | 120 | 1 | 17 | 150 | 12063 | 2022-05-13 | 150
G Level Near First Aid Room
14 | Scaffolding inspaction and taging | 8 | 1.3 | 3 | 24 | 1 | 18 | 150 | 12064 | 2022-05-17 | 150
Level -5 Residance Tower MEP Plant Room
15 | Scaffolding inspaction and taging | 6 | 1.3 | 5 | 30 | 1 | 19 | 150 | 12065 | 2022-05-17 | 150
Level -5 Residance Tower MEP Plant Room
16 | Scaffolding inspaction and taging | 4 | 1 | 4 | 16 | 1 | 28 | 150 | 12088 | 2022-05-12 | 150
Residance Tower inside Room Level - 30
17 | Scaffolding inspaction and taging | 6 | 1 | 4 | 24 | 1 | 24 | 150 | 12087 | 2022-05-12 | 150
Residance Tower Level - 31
18 | Scaffolding inspaction and taging | 2.5 | 1.3 | 3 | 7.5 | 1 | 21 | 150 | 12067 | 2022-05-13 | 150
Level -5 Hotel Tower Plan Room
19 | Scaffolding inspaction and taging | 45 | 1.3 | 5 | 225 | 1 | 22 | 150 | 12068 | 2022-05-17 | 150
Basement -1 Residence Tower
20 | Scaffolding inspaction and taging | 1.8 | 1.3 | 3 | 5.4 | 1 | 25 | 150 | 12070 | 2022-05-17 | 150
Level 3
21 | Scaffolding inspaction and taging | 12 | 4 | 3 | 144 | 1 | 27 | 150 | 12071 | 2022-05-17 | 150
Ground Level Back Side Office
22 | Scaffolding inspaction and taging | 4 | 1.3 | 3 | 12 | 1 | 29 | 150 | 12072 | 2022-05-18 | 150
Level -5 Residence Tower Plan Room
23 | Scaffolding inspaction and taging | 10 | 1.3 | 6 | 60 | 1 | 30 | 150 | 12073 | 2022-05-18 | 150
Level -5 Residence Tower House Keeping
24 | Scaffolding inspaction and taging | 2.5 | 1.3 | 4 | 10 | 1 | 31 | 150 | 12074 | 2022-05-18 | 150
Level -5 Hotel Tower Plan Room
25 | Scaffolding inspaction and taging | 2.5 | 1.3 | 4 | 10 | 1 | 32 | 150 | 12075 | 2022-05-18 | 150
Level -5 Hotel Tower Plan Room
26 | Scaffolding inspaction and taging | 4 | 1.3 | 3 | 12 | 1 | 34 | 150 | 12076 | 2022-05-19 | 150
Level -23 Residance Tower
27 | Scaffolding inspaction and taging | 40 | 1.3 | 6 | 240 | 1 | 36 | 150 | 12077 | 2022-05-19 | 150
Level -23 Out side balcony
28 | Scaffolding inspaction and taging | 12 | 1.3 | 4 | 48 | 1 | 37 | 150 | 12078 | 2022-05-19 | 150
Level -23 Residance Tower
29 | Scaffolding inspaction and taging | 1.8 | 1.3 | 3 | 5.4 | 1 | 71 | 150 | 12110 | 2022-05-26 | 150
Level -2 HotelSide
30 | Scaffolding inspaction and taging | 1.8 | 1.3 | 3 | 5.4 | 1 | 77 | 150 | 12111 | 2022-05-27 | 150
Level -4 Water Meter Room
31 | Scaffolding inspaction and taging | 8 | 8 | 6 | 384 | 1 | 101 | 150 | 12122 | 2022-05-27 | 150
Level -24
32 | Scaffolding inspaction and taging | 8 | 8 | 6 | 384 | 1 | 103 | 150 | 12124 | 2022-05-29 | 150
Level -22
33 | Scaffolding inspaction and taging | 8 | 8 | 6 | 384 | 1 | 102 | 150 | 12123 | 2022-05-29 | 150
Level -22 Hotel side
34 | Scaffolding inspaction and taging | 7.5 | 6 | 5 | 225 | 1 | 84 | 150 | 12125 | 2022-05-30 | 150
Level -7
35 | Scaffolding inspaction and taging | 2.5 | 1.8 | 7 | 17.5 | 1 | 83 | 150 | 12126 | 2022-05-30 | 150
Mobile Tower
36 | Scaffolding inspaction and taging | 2.5 | 1.8 | 3 | 7.5 | 1 | 83 | 150 | 12135 | 2022-05-31 | 150
Basment 1 Hotel Side
37 | Scaffolding inspaction and taging | 8 | 3 | 3 | 72 | 1 | 90 | 150 | 12134 | 2022-05-31 | 150
Basment 1 Hotel Side
38 | Scaffolding inspaction and taging | 7 | 1.3 | 3 | 21 | 3 | 87,88,89 | 150 | 12133 | 2022-05-31 | 450
Basment 1 Hotel Side
39 | Scaffolding inspaction and taging | 6 | 2.6 | 3 | 46.8 | 1 | 92 | 150 | 12136 | 2022-05-31 | 150
Basment 1 Hotel Side
40 | Scaffolding inspaction and taging | 2.5 | 1.8 | 6 | 15 | 1 | 93 | 150 | 12137 | 2022-05-31 | 150
Level 2 Mobile tower
41 | Scaffolding inspaction and taging | 6.5 | 6.5 | 6 | 253.5 | 1 | 94 | 150 | 12139 | 2022-05-31 | 150
Level 16 hotel side
1 | Scaffolding inspaction and taging | 19 | 10 | 6 | 1140 | 1 | 122 | 150 | 12201 | 2022-06-01 | 150
Ground Floor Ball Room Hotel
2 | Scaffolding inspaction and taging | 19 | 10 | 6 | 1140 | 1 | 123 | 150 | 12202 | 2022-06-01 | 150
Ground Floor Ball Room Hotel
3 | Scaffolding inspaction and taging | 19 | 10 | 6 | 1140 | 1 | 124 | 150 | 12203 | 2022-06-01 | 150
Ground Floor Ball Room Hotel
4 | Scaffolding inspaction and taging | 4 | 1.3 | 5 | 20 | 1 | 96 | 150 | 12144 | 2022-06-01 | 150
Leevel 2 Hotel Lift Lobby
5 | Scaffolding inspaction and taging | 19 | 10 | 6 | 1140 | 1 | 121 | 150 | 12150 | 2022-06-01 | 150
Ground Floor Ball Area
6 | Scaffolding inspaction and taging | 19 | 10 | 6 | 1140 | 1 | 120 | 150 | 12149 | 2022-06-01 | 150
Ground Floor Ball Area
7 | Scaffolding inspaction and taging | 10 | 1.3 | 7 | 70 | 1 | 100 | 150 | 12204 | 2022-06-02 | 150
ground Floor Ball Area
8 | Scaffolding inspaction and taging | 8 | 1.3 | 5 | 40 | 1 | AD 4 | 150 | 12205 | 2022-06-02 | 150
Level 26 Hotel Side
9 | Scaffolding inspaction and taging | 6 | 1.3 | 5 | 30 | 1 | A01 | 150 | 12208 | 2022-06-02 | 150
Ground Floor Hotel
10 | Scaffolding inspaction and taging | 10 | 1.3 | 5 | 50 | 1 | A05 | 150 | 12217 | 2022-06-03 | 150
LEVEL 18 HOTEL SIDE
11 | Scaffolding inspaction and taging | 2.5 | 2.5 | 8 | 50 | 1 | A06 | 150 | 12218 | 2022-06-03 | 150
LEVEL - 22 Residence
12 | Scaffolding inspaction and taging | 8 | 1.3 | 4 | 32 | 1 | A10 | 150 | 12222 | 2022-06-05 | 150
LEVEL 23 RESIDANCE
13 | Scaffolding inspaction and taging | 7.5 | 1.3 | 5 | 37.5 | 1 | A15 | 150 | 12232 | 2022-06-05 | 150
BASMENT -01
14 | Scaffolding inspaction and taging | 5 | 1.3 | 2.5 | 12.5 | 1 | A18 | 150 | 12235 | 2022-06-06 | 150
Level 24 Hotel Back Side
15 | Scaffolding inspaction and taging | 4 | 1.3 | 5 | 20 | 1 | 147 | 150 | 12245 | 2022-06-06 | 150
Level 23 pmv staircase
16 | Scaffolding inspaction and taging | 15 | 1.3 | 3 | 45 | 1 | 159 | 150 | 12156 | 2022-06-07 | 150
Level 2 Hotel Outside
17 | Scaffolding inspaction and taging | 5 | 1.3 | 5 | 25 | 1 | 164 | 150 | 12161 | 2022-06-07 | 150
Level 23 Residance
18 | Scaffolding inspaction and taging | 4 | 1.3 | 5 | 20 | 1 | 161 | 150 | 12158 | 2022-06-07 | 150
Level -23 Residance BMV Room
19 | Scaffolding inspaction and taging | 1.8 | 1.3 | 2.5 | 4.5 | 1 | 185 | 150 | 12177 | 2022-06-08 | 150
Level -6 Residance Mobile Tower
20 | Scaffolding inspaction and taging | 1.8 | 1.3 | 3 | 5.4 | 1 | 176 | 150 | 12178 | 2002-06-08 | 150
Level 23- Residance Staircase
21 | Scaffolding inspaction and taging | 2.5 | 1.3 | 3 | 7.5 | 1 | 195 | 150 | 12191 | 2022-06-09 | 150
Ground Floor Access Way
22 | Scaffolding inspaction and taging | 15 | 1.3 | 5 | 75 | 1 | 194 | 150 | 12190 | 2022-06-09 | 150
Level - 18 Hotel
23 | Scaffolding inspaction and taging | 5 | 1.3 | 4 | 20 | 1 | 201 | 150 | 12197 | 2022-06-09 | 150
Ground Floor Hotel Walk Way
24 | Scaffolding inspaction and taging | 8 | 5 | 6 | 240 | 1 | 203 | 150 | 12199 | 2022-06-10 | 150
Level 14 Hotel
25 | Scaffolding inspaction and taging | 2.5 | 1.8 | 3 | 7.5 | 1 | 205 | 150 | 12302 | 2022-06-10 | 150
G F Ball Area Mobile Tower
26 | Scaffolding inspaction and taging | 2 | 1.3 | 2 | 4 | 1 | 219 | 150 | 12316 | 2022-06-12 | 150
Level -23
27 | Scaffolding inspaction and taging | 2 | 2 | 1.5 | 6 | 1 | 221 | 150 | 12318 | 2022-06-12 | 150
Level -23 Residence Tower
28 | Scaffolding inspaction and taging | 2.5 | 1.3 | 5 | 12.5 | 1 | 223 | 150 | 12320 | 2022-06-13 | 150
Level -18 Hotel
29 | Scaffolding inspaction and taging | 2.5 | 1.3 | 5 | 12.5 | 1 | 224 | 150 | 12321 | 2022-06-13 | 150
Level -18 Hotel
30 | Scaffolding inspaction and taging | 2 | 1 | 3 | 6 | 1 | 225 | 150 | 12322 | 2022-06-13 | 150
Groud Floor Hotel
31 | Scaffolding inspaction and taging | 2.5 | 1.3 | 5 | 12.5 | 1 | 235 | 150 | 12350 | 2022-06-15 | 150
Level -23 Residance
| Scaffolding inspaction and taging | 2.5 | 1.3 | 5 | 12.5 | 1 | 264 | 150 | 12378 | 2022-06-17 | 150
Level -18 Hotel
29 | Scaffolding inspaction and taging | 1.3 | 1.3 | 2 | 2.6 | 1 | 265 | 150 | 12379 | 2022-06-17 | 150
Level -24 Residance
30 | Scaffolding inspaction and taging | 1.3 | 1.3 | 2 | 2.6 | 1 | 266 | 150 | 12380 | 2022-06-17 | 150
Level -25 Residance
31 | Scaffolding inspaction and taging | 6 | 1.3 | 2 | 12 | 1 | 268 | 150 | 12382 | 2022-06-17 | 150
Level -26
32 | Scaffolding inspaction and taging | 7 | 1 | 1.5 | 10.5 | 2 | 278 - 275 | 150 | 12389 | 2022-06-19 | 300
Level -29-27
33 | Scaffolding inspaction and taging | 7 | 1 | 1.5 | 10.5 | 2 | 279-280 | 150 | 12390 | 2022-06-19 | 300
Level -25-26
34 | Scaffolding inspaction and taging | 7 | 1 | 1.5 | 10.5 | 2 | 281-282 | 150 | 12391 | 2022-06-19 | 300
Level -23 - 24
35 | Scaffolding inspaction and taging | 7 | 1 | 1.5 | 10.5 | 2 | 283-284 | 150 | 12392 | 2022-06-19 | 300
Level 21-22
36 | Scaffolding inspaction and taging | 1.3 | 1.3 | 2 | 2.6 | 1 | 291 | 150 | 12397 | 2022-06-19 | 150
Level 29
37 | Scaffolding inspaction and taging | 6 | 2.5 | 5 | 30 | 1 | 336 | 150 | 12437 | 2022-06-23 | 150
Level 30
38 | Scaffolding inspaction and taging | 1.8 | 1.3 | 3 | 5.4 | 1 | 241 | 150 | 12356 | 2022-06-15 | 150
GF Office Area
39 | Scaffolding inspaction and taging | 2 | 1 | 2 | 4 | 1 | 242 | 150 | 12357 | 2022-06-15 | 150
GF North
40 | Scaffolding inspaction and taging | 4 | 2 | 2 | 8 | 1 | 236 | 150 | 12351 | 2022-06-15 | 150
Level 23
41 | Scaffolding inspaction and taging | 2.5 | 1.8 | 6 | 15 | 1 | 234 | 150 | 12349 | 2022-06-15 | 150
Level 18
42 | Scaffolding inspaction and taging | 5 | 2 | 5 | 25 | 1 | 232 | 150 | 12335 | 2022-06-14 | 150
Level 1 Hotel
43 | Scaffolding inspaction and taging | 5 | 1.3 | 5 | 25 | 1 | 229 | 150 | 12323 | 2022-06-13 | 150
GF Gate no 2
44 | Scaffolding inspaction and taging | 5 | 1 | 5 | 25 | 1 | 213 | 150 | 12310 | 2022-06-12 | 150
level 18 hotel
45 | Scaffolding inspaction and taging | 2.5 | 2.5 | 5 | 12.5 | 1 | 249 | 150 | 12364 | 2022-06-15 | 150
| level 18 hotel | 2.5 | 2.5 | 4 | 10 | 1 | 250 | 150 | 12364 | 2022-06-15 | 150
46 | Scaffolding inspaction and taging | 6 | 6 | 5 | 30 | 1 | 251 | 150 | 12365 | 2022-06-15 | 150
level 18 hotel
47 | Scaffolding inspaction and taging | 2 | 1.3 | 3 | 6 | 1 | 252 | 150 | 12366 | 2022-06-16 | 150
Level 10 Residance
48 | Scaffolding inspaction and taging | 15 | 1.3 | 4 | 60 | 1 | 354 | 150 | 12509 | 2022-06-24 | 150
Level 29 Hotel
49 | Scaffolding inspaction and taging | 2.5 | 2.5 | 5 | 12.5 | 1 | 355 | 150 | 12510 | 2022-06-24 | 150
Basement 1
50 | Scaffolding inspaction and taging | 1.8 | 1.3 | 4 | 7.2 | 1 | 114 | 150 | 12147 | 2022-06-01 | 150
Level 30 Residance
51 | Scaffolding inspaction and taging | 1.3 | 1.3 | 6 | 7.8 | 1 | 95 | 150 | 12143 | 2022-06-01 | 150
Level 2 Hotel
52 | Scaffolding inspaction and taging | 2.5 | 1.3 | 5 | 12.5 | 1 | 372 | 150 | 12529 | 2022-06-27 | 150
Level 30 Residance
53 | Scaffolding inspaction and taging | 10 | 1.8 | 5 | 50 | 1 | 375 | 150 | 12532 | 2022-06-28 | 150
Level 24 Hotel
54 | Scaffolding inspaction and taging | 12 | 1.3 | 4 | 48 | 1 | 380 | 150 | 12552 | 2022-06-28 | 150
Level 22 Residance
55 | Scaffolding inspaction and taging | 7 | 1 | 2 | 14 | 3 | 394 / 395 / 396 | 150 | 12557 | 2022-06-29 | 450
Level 7 / 9 / 10 hotel Shaft
56 | Scaffolding inspaction and taging | 4 | 1.3 | 5 | 20 | 2 | 586 , 579 | 150 | 12803 | 2022-07-25 | 300
Level 15 / 18 Hotel
57 | Scaffolding inspaction and taging | 6 | 1.3 | 6 | 36 | 1 | 588 | 150 | 12806 | 2022-07-25 | 150
Level 13 Hotel
58 | Scaffolding inspaction and taging | 2.5 | 1.3 | 3 | 7.5 | 2 | 570 - 571 | 150 | 12790 | 2022-07-24 | 300
Level 6 Residance
59 | Scaffolding inspaction and taging | 9 | 1.3 | 6 | 54 | 1 | 702 | 150 | 12965 | 2022-08-08 | 150
Level 28 Hotel
60 | Scaffolding inspaction and taging | 2.5 | 2.5 | 5 | 12.5 | 1 | 638 | 150 | 12861 | 2022-08-01 | 150
Level 26 Residence
61 | Scaffolding inspaction and taging | 6 | 1.3 | 5 | 30 | 1 | 640 | 150 | 12831 | 2022-08-01 | 150
Level 10 Residence
62 | Scaffolding inspaction and taging | 20 | 1.8 | 5 | 100 | 1 | 611 | 150 | 12863 | 2022-08-01 | 150
Level 28 Hotel
63 | Scaffolding inspaction and taging | 5 | 1.3 | 5 | 25 | 1 | 814 | 150 | 13077 | 2022-08-24 | 150
Level 25
64 | Scaffolding inspaction and taging | 10 | 1 | 5 | 50 | 1 | 808 | 150 | 13071 | 2022-08-24 | 150
Level 25 Hotel
65 | Scaffolding inspaction and taging | 12 | 1.3 | 7 | 84 | 1 | 842 | 150 | 13111 | 2022-08-27 | 150
G F Hotel
[8 empty] | TOTAL AMOUNT |  |  | 18150

## Hire
HIRE CHARGES FOR SCFFOLD MATERIAL - CONTRACT NO : 201A220022 - E11/K107/SK/DM/015
sn | Deceription | QTY | DO No | HRN 6230 Date1/9/22 | UNIT RATE/WEEK | Hire charges from | Hire Charges up to | NO OF DAYS | Rent /Day | Total amount | Invoiced till last month | Inv For Month OF August
1 | BRC Coupler | 600 | 8162 |  | 0.22 | 2022-05-26 | 2023-02-28 | 279 | 18.8571 | 5261.1429 | 4733.1429 | 528
| BRC Coupler | -7 |  | 6537 | -0.22 | 2022-11-16 | 2023-02-28 | 105 | -0.22 | -23.1 | -16.94 | -6.16
| BRC Coupler | -5 |  | 6546 | -0.22 | 2022-11-22 | 2023-02-28 | 99 | -0.15714 | -15.5571 | -11.1571 | -4.4
| BRC Coupler | -5 |  | 6562 | -0.22 | 2022-11-24 | 2023-02-28 | 97 | -0.15714 | -15.2429 | -10.8429 | -4.4
| BRC Coupler | -128 |  | 6636 | -0.22 | 2022-12-06 | 2023-02-28 | 85 | -4.0229 | -341.9429 | -229.3029 | -112.64
| BRC Coupler | -83 |  | 6726 | -0.22 | 2023-01-02 | 2023-02-28 | 58 | -2.6086 | -151.2971 | -78.2571 | -73.04
| BRC Coupler | -26 |  | 6796 | -0.22 | 2023-01-07 | 2023-02-28 | 53 | -0.81714 | -43.3086 | -20.4286 | -22.88
| BRC Coupler | -5 |  | 6798 | -0.22 | 2023-01-18 | 2023-02-28 | 42 | -0.15714 | -6.6 | -2.2 | -4.4
| BRC Coupler | -77 |  | 6876 | -0.22 | 2023-02-17 | 2023-02-28 | 12 | -2.42 | -29.04 |  | -29.04
| BRC Coupler | -29 |  | 6878 | -0.22 | 2023-02-21 | 2023-02-28 | 8 | -0.91143 | -7.2914 |  | -7.2914
2 | Double Coupler | 300 | 8162 |  | 0.36 | 2022-05-26 | 2023-02-28 | 279 | 15.4286 | 4304.5714 | 3872.5714 | 432
| Double Coupler | -4 |  | 6537 | -0.36 | 2022-11-16 | 2023-02-28 | 105 | -0.20571 | -21.6 | -15.84 | -5.76
| Double Coupler | -2 |  | 6546 | -0.36 | 2022-11-22 | 2023-02-28 | 99 | -0.10286 | -10.1829 | -7.3029 | -2.88
| Double Coupler | -13 |  | 6562 | -0.36 | 2022-11-24 | 2023-02-28 | 97 | -0.66857 | -64.8514 | -46.1314 | -18.72
| Double Coupler | -12 |  | 6636 | -0.36 | 2022-12-06 | 2023-02-28 | 85 | -0.61714 | -52.4571 | -35.1771 | -17.28
| Double Coupler | -16 |  | 6726 | -0.36 | 2023-01-02 | 2023-02-28 | 58 | -0.82286 | -47.7257 | -24.6857 | -23.04
| Double Coupler | -6 |  | 6796 | -0.36 | 2023-01-07 | 2023-02-28 | 53 | -0.30857 | -16.3543 | -7.7143 | -8.64
| Double Coupler | -3 |  | 6798 | -0.36 | 2023-01-18 | 2023-02-28 | 42 | -0.15429 | -6.48 | -2.16 | -4.32
| Double Coupler | -15 |  | 6876 | -0.36 | 2023-02-17 | 2023-02-28 | 12 | -0.77143 | -9.2571 |  | -9.2571
| Double Coupler | -11 |  | 6878 | -0.36 | 2023-02-21 | 2023-02-28 | 8 | -0.56571 | -4.5257 |  | -4.5257
3 | KS - Spigot Connector | 300 | 8162 |  | 0.19 | 2022-05-26 | 2023-02-28 | 279 | 8.1429 | 2271.8571 | 2043.8571 | 228
| KS - Spigot Connector | -12 |  | 6537 | -0.19 | 2022-11-16 | 2023-02-28 | 105 | -0.32571 | -34.2 | -25.08 | -9.12
| KS - Spigot Connector | -5 |  | 6546 | -0.19 | 2022-11-22 | 2023-02-28 | 99 | -0.13571 | -13.4357 | -9.6357 | -3.8
| KS - Spigot Connector | -28 |  | 6562 | -0.19 | 2022-11-24 | 2023-02-28 | 97 | -0.76 | -73.72 | -52.44 | -21.28
| KS - Spigot Connector | -27 |  | 6636 | -0.19 | 2022-12-06 | 2023-02-28 | 85 | -0.73286 | -62.2929 | -41.7729 | -20.52
| KS - Spigot Connector | -21 |  | 6726 | -0.19 | 2023-01-02 | 2023-02-28 | 58 | -0.57 | -33.06 | -17.1 | -15.96
| KS - Spigot Connector | -3 |  | 6796 | -0.19 | 2023-01-07 | 2023-02-28 | 53 | -0.081429 | -4.3157 | -2.0357 | -2.28
| KS - Spigot Connector | -4 |  | 6798 | -0.19 | 2023-01-18 | 2023-02-28 | 42 | -0.10857 | -4.56 | -1.52 | -3.04
| KS - Spigot Connector | -17 |  | 6876 | -0.19 | 2023-02-17 | 2023-02-28 | 12 | -0.46143 | -5.5371 |  | -5.5371
| KS - Spigot Connector | -13 |  | 6878 | -0.19 | 2023-02-21 | 2023-02-28 | 8 | -0.35286 | -2.8229 |  | -2.8229
4 | Ladder Clamp | 400 | 8162 |  | 0.31 | 2022-05-26 | 2023-02-28 | 279 | 17.7143 | 4942.2857 | 4446.2857 | 496
| Ladder Clamp | -1 |  | 6537 | -0.31 | 2022-11-16 | 2023-02-28 | 105 | -0.044286 | -4.65 | -3.41 | -1.24
| Ladder Clamp | -6 |  | 6546 | -0.31 | 2022-11-22 | 2023-02-28 | 99 | -0.26571 | -26.3057 | -18.8657 | -7.44
| Ladder Clamp | -3 |  | 6562 | -0.31 | 2022-11-24 | 2023-02-28 | 97 | -0.13286 | -12.8871 | -9.1671 | -3.72
| Ladder Clamp | -45 |  | 6636 | -0.31 | 2022-12-06 | 2023-02-28 | 85 | -1.9929 | -169.3929 | -113.5929 | -55.8
| Ladder Clamp | -67 |  | 6726 | -0.31 | 2023-01-02 | 2023-02-28 | 58 | -2.9671 | -172.0943 | -89.0143 | -83.08
| Ladder Clamp | -15 |  | 6796 | -0.31 | 2023-01-07 | 2023-02-28 | 53 | -0.66429 | -35.2071 | -16.6071 | -18.6
| Ladder Clamp | -77 |  | 6876 | -0.31 | 2023-02-17 | 2023-02-28 | 12 | -3.41 | -40.92 |  | -40.92
| Ladder Clamp | -13 |  | 6878 | -0.31 | 2023-02-21 | 2023-02-28 | 8 | -0.57571 | -4.6057 |  | -4.6057
5 | Ladder Trap | 60 | 8162 | 59 | 26 | 2022-05-26 | 2022-09-01 | 99 | 222.8571 | 22062.8571 | 22062.8571 | 0
6 | Ladder Trap | 1 |  | 6546 | 26 | 2022-09-02 | 2022-11-22 | 82 | 3.7143 | 304.5714 | 304.5714 | 0
7 | Single Coupler | 400 | 8162 |  | 0.25 | 2022-05-26 | 2023-02-28 | 279 | 14.2857 | 3985.7143 | 3585.7143 | 400
| Single Coupler | -10 |  | 6537 | -0.25 | 2022-11-16 | 2023-02-28 | 105 | -0.35714 | -37.5 | -27.5 | -10
| Single Coupler | -1 |  | 6546 | -0.25 | 2022-11-22 | 2023-02-28 | 99 | -0.035714 | -3.5357 | -2.5357 | -1
| Single Coupler | -1 |  | 6562 | -0.25 | 2022-11-24 | 2023-02-28 | 97 | -0.035714 | -3.4643 | -2.4643 | -1
| Single Coupler | -15 |  | 6636 | -0.25 | 2022-12-06 | 2023-02-28 | 85 | -0.53571 | -45.5357 | -30.5357 | -15
| Single Coupler | -35 |  | 6726 | -0.25 | 2023-01-02 | 2023-02-28 | 58 | -1.25 | -72.5 | -37.5 | -35
| Single Coupler | -22 |  | 6796 | -0.25 | 2023-01-07 | 2023-02-28 | 53 | -0.78571 | -41.6429 | -19.6429 | -22
| Single Coupler | -28 |  | 6876 | -0.25 | 2023-02-17 | 2023-02-28 | 12 | -1 | -12 |  | -12
| Single Coupler | -22 |  | 6878 | -0.25 | 2023-02-21 | 2023-02-28 | 8 | -0.78571 | -6.2857 |  | -6.2857
8 | Sleeve Coupler | 300 | 8162 |  | 0.33 | 2022-05-26 | 2023-02-28 | 279 | 14.1429 | 3945.8571 | 3549.8571 | 396
| Sleeve Coupler | -5 |  | 6537 | -0.33 | 2022-11-16 | 2023-02-28 | 105 | -0.23571 | -24.75 | -18.15 | -6.6
| Sleeve Coupler | -1 |  | 6546 | -0.33 | 2022-11-22 | 2023-02-28 | 99 | -0.047143 | -4.6671 | -3.3471 | -1.32
| Sleeve Coupler | -3 |  | 6562 | -0.33 | 2022-11-24 | 2023-02-28 | 97 | -0.14143 | -13.7186 | -9.7586 | -3.96
| Sleeve Coupler | -27 |  | 6636 | -0.33 | 2022-12-06 | 2023-02-28 | 85 | -1.2729 | -108.1929 | -72.5529 | -35.64
| Sleeve Coupler | -11 |  | 6726 | -0.33 | 2023-01-02 | 2023-02-28 | 58 | -0.51857 | -30.0771 | -15.5571 | -14.52
| Sleeve Coupler | -2 |  | 6796 | -0.33 | 2023-01-07 | 2023-02-28 | 53 | -0.094286 | -4.9971 | -2.3571 | -2.64
| Sleeve Coupler | -1 |  | 6798 | -0.33 | 2023-01-18 | 2023-02-28 | 42 | -0.047143 | -1.98 | -0.66 | -1.32
| Sleeve Coupler | -7 |  | 6876 | -0.33 | 2023-02-17 | 2023-02-28 | 12 | -0.33 | -3.96 |  | -3.96
| Sleeve Coupler | -1 |  | 6878 | -0.33 | 2023-02-21 | 2023-02-28 | 8 | -0.047143 | -0.37714 |  | -0.37714
9 | Steel Ladder 3.0 mtr | 40 | 8162 |  | 7.25 | 2022-05-26 | 2023-02-28 | 279 | 41.4286 | 11558.5714 | 10398.5714 | 1160
| Steel Ladder 3.0 mtr | -2 |  | 6546 | -7.25 | 2022-11-22 | 2023-02-28 | 99 | -2.0714 | -205.0714 | -147.0714 | -58
| Steel Ladder 3.0 mtr | -1 |  | 6562 | -7.25 | 2022-11-24 | 2023-02-28 | 97 | -1.0357 | -100.4643 | -71.4643 | -29
10 | BRC Coupler | 500 | 8174 |  | 0.22 | 2022-06-01 | 2023-02-28 | 273 | 15.7143 | 4290 | 3850 | 440
11 | KS - Spigot Connector | 100 | 8174 |  | 0.19 | 2022-06-01 | 2023-02-28 | 273 | 2.7143 | 741 | 665 | 76
12 | Single Coupler | 300 | 8174 |  | 0.25 | 2022-06-01 | 2023-02-28 | 273 | 10.7143 | 2925 | 2625 | 300
[8 empty] | TOTAL |  | 64305.8871 | 60767.95 | 3537.9371
[8 empty] | Disount 60% |  | 38583.5323 | 36460.77 | 2122.7623
[8 empty] | TOTAL AMOUNT |  | 25722.3549 | 24307.18 | 1415.1749

## RE Insp & Taging
ITEM NO : RE INSPECTION Of MODIFIED SCAFFOLD AND TAGING CONTRACTNO : 201A22002 -E11/K107/SK/DM/008
Item No | Description | Tag nomber | no of tag | Inspection charges /tag | HandOver Certicate No | Inspection date | Total amount
1 | Re inspaction of Scaffold TAG | A15,87,88,89,90,91,92 | 7 | 50 | 12340 | 2022-06-07 | 350
| Basement |  | 7 | 50 | 12340 | 2022-06-14 | 350
2 | Re inspaction of Scaffold TAG | 94 , A05 | 2 | 50 | 12338 | 2022-06-07 | 100
| Lelel 16 & 18 Hotel |  | 2 | 50 | 12338 | 2022-06-14 | 100
3 | Re inspaction of Scaffold TAG | 16 | 1 | 50 | 12326 | 2022-05-20 | 50
|  |  | 1 | 50 | 12326 | 2022-05-27 | 50
|  |  | 1 | 50 | 12326 | 2022-06-05 | 50
|  |  | 1 | 50 | 12326 | 2022-06-12 | 50
4 | Re inspaction of Scaffold TAG | 17 | 1 | 50 | 12327 | 2022-05-20 | 50
| G F HOTEL |  | 1 | 50 | 12327 | 2022-05-27 | 50
|  |  | 1 | 50 | 12327 | 2022-06-05 | 50
|  |  | 1 | 50 | 12327 | 2022-06-12 | 50
5 | Re inspaction of Scaffold TAG | 27 | 1 | 50 | 12328 | 2022-05-27 | 50
| GROUND LEVEL OFFICE |  | 1 | 50 | 12328 | 2022-06-05 | 50
|  |  | 1 | 50 | 12328 | 2022-06-12 | 50
6 | Re inspaction of Scaffold TAG | 83 , 71 | 2 | 50 | 12331 | 2022-06-05 | 100
| Level 2 Hotel |  | 2 | 50 | 12331 | 2022-06-12 | 100
7 | Re inspaction of Scaffold TAG | 12 | 1 | 50 | 12332 | 2022-05-18 | 50
| Level 2 Hotel |  | 1 | 50 | 12332 | 2022-05-27 | 50
|  |  | 1 | 50 | 12332 | 2022-06-05 | 50
|  |  | 1 | 50 | 12332 | 2022-06-12 | 50
8 | Re inspaction of Scaffold TAG | 29 , 31 , 32 , 30 | 4 | 50 | 12333 | 2022-05-22 | 200
| Level 5 Hotel |  | 4 | 50 | 12332 | 2022-06-01 | 200
|  |  | 4 | 50 | 12332 | 2022-06-07 | 200
|  |  | 4 | 50 | 12332 | 2022-06-14 | 200
9 | Re inspaction of Scaffold TAG | 24 , 28 | 2 | 50 | 12329 | 2022-05-23 | 100
| Level 30 & 31 Residance |  | 2 | 50 | 12332 | 2022-05-29 | 100
|  |  | 2 | 50 | 12332 | 2022-06-05 | 100
|  |  | 2 | 50 | 12332 | 2022-06-12 | 100
10 | Re inspaction of Scaffold TAG | 93 , 19 , 96 , 95 | 4 | 50 | 12330 | 2022-06-07 | 200
| Level 02 Hotel |  | 4 | 50 | 12330 | 2022-06-14 | 200
11 | Re inspaction of Scaffold TAG | 159 | 1 | 50 | 12346 | 2022-06-14 | 50
Level 02 Hotel
12 | Re inspaction of Scaffold TAG | A01 | 1 | 50 | 12344 | 2022-06-08 | 50
| Level G F Hotel |  | 1 | 50 | 12344 | 2022-06-15 | 50
13 | Re inspaction of Scaffold TAG | 84 | 1 | 50 | 12343 | 2022-06-07 | 50
| Level 7 Hotel |  | 1 | 50 | 12343 | 2022-06-14 | 50
14 | Re inspaction of Scaffold TAG | 100, 120, 121 ,122 ,123 ,124 | 6 | 50 | 12341 | 2022-06-07 | 300
| G F Hotel Ball Area |  | 6 | 50 | 12341 | 2022-06-14 | 300
15 | Re inspaction of Scaffold TAG | 114, A10, A06, 147 , A04 | 5 | 50 | 12342 | 2022-06-07 | 250
| Level 23 ,22,30,26 Residance |  | 5 | 50 | 12342 | 2022-06-14 | 250
16 | Re inspaction of Scaffold TAG | 101 , 102 , 103 | 3 | 50 | 12339 | 2022-06-07 | 150
| Level 10 - 22 - 24 Hotel |  | 3 | 50 | 12339 | 2022-06-14 | 150
17 | Re inspaction of Scaffold TAG | 13,30 , 31, 32 ,232 ,19 | 6 | 50 | 12538 | 2022-06-21 | 300
| Level 05 |  | 6 | 50 | 12538 | 2022-06-28 | 300
18 | Re inspaction of Scaffold TAG | 12 , 83 , 159, 93, 96, 95 , 190 ,231 | 8 | 50 | 12537 | 2022-06-21 | 400
| Level 02 |  | 8 | 50 | 12537 | 2022-06-28 | 400
19 | Re inspaction of Scaffold TAG | 16, 17, 27, 100, 120, 121,122, 123, 124, A01 | 10 | 50 | 12536 | 2022-06-21 | 500
| GF |  | 10 | 50 | 12536 | 2022-06-28 | 500
20 | Re inspaction of Scaffold TAG | 87, 88,89, 90, 91 ,92 | 6 | 50 | 12535 | 2022-06-21 | 300
| Besment 01 |  | 6 | 50 | 12535 | 2022-06-28 | 300
21 | Re inspaction of Scaffold TAG | 234 , 84, 94, 224, 223 | 5 | 50 | 12539 | 2022-06-21 | 250
| Level 7 / 18 Hotel |  | 5 | 50 | 12539 | 2022-06-28 | 250
22 | Re inspaction of Scaffold TAG | 114, 24, 291, 268, 266, 235, 236, 221, 252 | 9 | 50 | 12548 | 2022-06-21 | 450
| Level 10 to 30 Residance |  | 9 | 50 | 12548 | 2022-06-28 | 450
23 | Modified Scaffold Re inspaction & Taging | 28, 281,282,283,284,278,101,102,103,275,278,279 | 12 | 50 | 12541 | 2022-06-21 | 600
| Level 20 To 29 Hotel |  | 12 | 50 | 12541 | 2022-06-28 | 600
24 | Modified Scaffold Re inspaction & Taging | 87 , 88, 89, 90, 91, 92 | 6 | 50 | 12781 | 2022-07-11 | 300
| Basement 1 |  | 6 | 50 | 12781 | 2022-07-17 | 300
|  |  | 6 | 50 | 12781 | 2022-07-24 | 300
25 | Modified Scaffold Re inspaction & Taging | 24, 372, 291, 266, 265, 221, 236, 380 | 8 | 50 | 12784 | 2022-07-11 | 400
| Level 22 to 30 Residance |  | 8 | 50 | 12784 | 2022-07-17 | 400
|  |  | 8 | 50 | 12784 | 2022-07-24 | 400
26 | Modified Scaffold Re inspaction & Taging | 264, 194, 251, 94, 203, 396, 395, 394 | 8 | 50 | 12785 | 2022-07-11 | 400
| Level 7 to 18 Hotel |  | 8 | 50 | 12785 | 2022-07-17 | 400
|  |  | 8 | 50 | 12785 | 2022-07-24 | 400
27 | Modified Scaffold Re inspaction & Taging | 284, 138, 102, 283, 282, 281, 137, 279, 278, 275 | 10 | 50 | 12786 | 2022-07-11 | 500
| Level 22 to 29 hotel |  | 10 | 50 | 12786 | 2022-07-17 | 500
|  |  | 10 | 50 | 12786 | 2022-07-24 | 500
28 | Modified Scaffold Re inspaction & Taging | 12, 93 ,96, 159, 31, 32 | 6 | 50 | 12783 | 2022-07-24 | 300
| Level 2 Hotel |  | 6 | 50 | 12783 | 2022-07-24 | 300
|  |  | 6 | 50 | 12783 | 2022-07-24 | 300
29 | Modified Scaffold Re inspaction & Taging | 16, 17, 27, 100, 120, 121, 122, 123, 124, A01, 23 | 11 | 50 | 12782 | 2022-07-11 | 550
| Ground Floor |  | 11 | 50 | 12782 | 2022-07-17 | 550
|  |  | 11 | 50 | 12782 | 2022-07-24 | 550
0
30 | Modified Scaffold Re inspaction & Taging | 12 , 93 , 96 , 159 | 4 | 50 | 13087 | 2022-08-01 | 200
|  |  | 4 | 50 | 13087 | 2022-08-08 | 200
|  |  | 4 | 50 | 13087 | 2022-08-15 | 200
|  |  | 4 | 50 | 13087 | 2022-08-22 | 200
|  |  | 4 | 50 | 13087 | 2022-08-29 | 200
31 | Modified Scaffold Re inspaction & Taging | 87 , 88 , 89 , 90, 91 92 | 6 | 50 | 13085 | 2022-08-01 | 300
|  |  | 6 | 50 | 13085 | 2022-08-08 | 300
|  |  | 6 | 50 | 13085 | 2022-08-15 | 300
|  |  | 6 | 50 | 13085 | 2022-08-22 | 300
|  |  | 6 | 50 | 13085 | 2022-08-29 | 300
32 | Modified Scaffold Re inspaction & Taging | 275, 278, 279 , 280 , 281 , 281 , 282 , 283 , 284 | 8 | 50 | 13084 | 2022-08-01 | 400
|  |  | 8 | 50 | 13084 | 2022-08-08 | 400
|  |  | 8 | 50 | 13084 | 2022-08-15 | 400
|  |  | 8 | 50 | 13084 | 2022-08-22 | 400
|  |  | 8 | 50 | 13084 | 2022-08-29 | 400
33 | Modified Scaffold Re inspaction & Taging | 24 , 266 , 265 , 380, 640 , 638 | 6 | 50 | 13083 | 2022-08-01 | 300
|  |  | 6 | 50 | 13083 | 2022-08-08 | 300
|  |  | 6 | 50 | 13083 | 2022-08-15 | 300
|  |  | 6 | 50 | 13083 | 2022-08-22 | 300
|  |  | 6 | 50 | 13083 | 2022-08-29 | 300
34 | Modified Scaffold Re inspaction & Taging | 194, 251, 394, 395, 396 | 5 | 50 | 13082 | 2022-08-01 | 250
|  |  | 5 | 50 | 13082 | 2022-08-08 | 250
|  |  | 5 | 50 | 13082 | 2022-08-15 | 250
|  |  | 5 | 50 | 13082 | 2022-08-22 | 250
|  |  | 5 | 50 | 13082 | 2022-08-29 | 250
35 | Modified Scaffold Re inspaction & Taging | 16, 17, 100, 120, 121, 122, 123, 124, A01, 23 | 10 | 50 | 13086 | 2022-08-01 | 500
|  |  | 10 | 50 | 13086 | 2022-08-08 | 500
|  |  | 10 | 50 | 13086 | 2022-08-15 | 500
|  |  | 10 | 50 | 13086 | 2022-08-22 | 500
|  |  | 10 | 50 | 13086 | 2022-08-29 | 500
|  |  |  | TOTAL AMOUNT |  |  | 27800

## Sale
SALE MATERIAL AS PER QUOTE # CHS/NS/126/0203622-R5
sn | Deceription | QTY | DO No | UNIT PRICE | Delivery Date | Total Amount
1 | TUBE END CAP | 100 | 15611 | 3 | 2022-06-14 | 300
2 | CLAMP PROTECTION CAP | 100 | 15611 | 1.5 | 2022-06-14 | 150
|  |  |  | Grand Total |  | 450

## Third Party Insp
THIRD PARTY INSPECTION
sn | Deceription | Date | QTY | UNIT PRICE | Total Amount
1 | Third party inspection |  | 1 | 800 | 800
1 | Third party inspection | 2022-06-03 | 1 | 800 | 800
2 | Third party inspection | 2022-06-16 | 1 | 800 | 800
3 | Third party inspection | 2022-07-06 | 9 | 800 | 7200
4 | Third party inspection | 2022-07-21 | 1 | 800 | 800
5 | Third party inspection | 2022-09-06 | 1 | 800 | 800
6 | Third party inspection | 2022-09-06 | 1 | 800 | 800
7 | Third party inspection | 2022-09-24 | 1 | 800 | 800
8 | Third party inspection | 2022-09-24 | 1 | 800 | 800
9 | Third party inspection | 2022-09-27 | 1 | 800 | 800
10 | Third party inspection | 2022-10-07 | 1 | 800 | 800
11 | Third party inspection | 2022-10-10 | 1 | 800 | 800
12 | Third party inspection | 2022-10-12 | 1 | 800 | 800
13 | Third party inspection | 2022-10-19 | 7 | 800 | 5600
14 | Third party inspection | 2022-10-21 | 1 | 800 | 800
15 | Third party inspection | 2022-12-13 | 5 | 800 | 4000
16 | Third party inspection | 2023-01-24 | 1 | 800 | 800
17 | Third party inspection | 2023-02-14 | 1 | 800 | 800
18 | Third party inspection | 2023-02-14 | 1 | 800 | 800
|  |  |  | Grand Total | 29600