## Hotel & BB
CONSULTANCY FEES - HOTEL PROJECT
|  |  | Amt Certified | Period | Contract Amount | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | Cumulative Upto date
Monthly Fee Consultancy Services
1 | PROJECT MANAGEMENT | MIRAGE | 6261284.45 | 2022-09-01 |  | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 |  |  |  | 8061284.45
2 | DESIGN ARCHITECT - SUPERVISION | FOSTERS & PARTNERS | 24037180.342 | 2022-09-01 |  | 96250 | 96250 | 96250 | 96250 | 96250 | 96250 |  |  |  | 24614680.342 | No written approvel -Estimated
3 | ARCHITECT OF RECORD - SUPERVISION | BSBG | 1547194 | 2022-10-01 |  | 2022-11-01: 215750; 2022-12-01: 215750; 2023-01-01: 215750; 2023-02-01: 215750; 2023-03-01: 215750 | 2625944
4 | STRUCTURAL ENGINEER - SUPERVISION | BG&E | 194800 | 2022-09-01 |  | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 |  |  |  | 404800
5 | MEP ENGINEER - SUPERVISION | WME | 610064.52 | 2022-10-01 |  | 2022-11-01: 136000; 2022-12-01: 136000; 2023-01-01: 136000; 2023-02-01: 136000; 2023-03-01: 136000 | 1290064.52
6 | LIGHTING ENGINEER - SUPERVISION | LIGHT TOUCH | 266380 | 2022-09-01 |  | 48010 | 89320 | 106856 | 54320 | 52980 | 63380 |  |  |  | 681246
7 | LANDSCAPE ARCHITECT - SUPERVISION | U+A | 150000 | 2022-09-01 |  | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 |  |  |  | 330000
8 | INTERIOR DESIGN - SUPERVISION | G&B | 12342198.11 | 2022-10-01 |  | 2022-11-01: 141473.64; 2022-12-01: 141473.64; 2023-01-01: 141473.64; 2023-02-01: 141473.64; 2023-03-01: 150573.64 | 13058666.31
9 | INTERIOR DESIGN - SUPERVISION | GAJ | 1036223.001 | 2022-10-01 |  | 230740 | 230740 | 219560 | 225080 | 225080 | 251760 |  |  |  | 2419183.001
10 | QUANTITY SURVEYING | EXCOM | 794247.91 | 2022-09-01 |  | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 |  |  |  | 857247.91
11 | QUANTITY SURVEYING | ECON | 4600 | 2022-09-01 |  | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 |  |  |  | 67600
12 | PROJECT MONITOR | CONIN | 2112328.13 | 2022-09-01 |  | 37968.75 | 37968.75 | 37968.75 | 37968.75 | 37968.75 | 37968.75 |  |  |  | 2340140.63
13 | KITCHEN AND BACK OF HOUSE | Fondue Consultancy | 180000 | 2022-10-01 |  | 2022-11-01: 29490; 2022-12-01: 29490; 2023-01-01: 29490; 2023-02-01: 29490; 2023-03-01: 29490 | 327450
14 | HOSPITALITY ADVISORY SERVICES | Roya | 1100000 | 2022-09-01 |  | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 |  |  |  | 1340000
15 | MEP MANAGER | Ian Banham & Associates | 674066.6667 | 2022-10-01 |  | 2022-11-01: 102000; 2022-12-01: 102000; 2023-01-01: 102000; 2023-02-01: 102000; 2023-03-01: 93933.33 | 1175999.9967
16 | Planning consultant | Critical Path | 146480 |  |  | 2022-11-01: 20000; 2022-12-01: 13904; 2023-01-01: 13904; 2023-02-01: 13904; 2023-03-01: 7808 | 216000
Fixed Fee Consulancy Services
17 | TRAFFIC ACCESS STUDY | AL TURATH | 257620 | 2022-10-01 |  | 2022-11-01: 5000 | 262620
18 | SIGNAGE AND WAYWARD FINDING | BRIMAX | 0 | July-22 |  | 2022-11-01: 20000; 2022-12-01: 20000; 2023-01-01: 10000 | 50000
19 | SURVEY SERVICES, OQOOD SUBMISSION | PRD | 151110 |  |  | 2023-02-01: 47080 | 198190
20 | FAÇADE ENGINEERING / BMU DESIGN | MEINHARDT | 44250 | 2022-10-01 |  | 2022-11-01: 20000; 2022-12-01: 20000; 2023-01-01: 20000; 2023-02-01: 12220 | 116470
21 | L17 & L29 RESTAURANTS | MITCHELL & EADES | 287600 | 2022-10-01 |  | 2022-11-01: 131400; 2022-12-01: 50000; 2023-01-01: 50000; 2023-02-01: 50000; 2023-03-01: 45000 | 614000
22 | IT CONSULTANT | MEDIA TECH | 78072 | 2022-09-01 |  | 2022-11-01: 12500; 2022-12-01: 12500; 2023-01-01: 12500; 2023-02-01: 12500; 2023-03-01: 12500 | 140572 | Exchange Rates
23 | FIRE SAFETY CONSULTANCY | VORTEX | 27275 | 2022-10-01 |  | 2022-11-01: 36560; 2022-12-01: 36560; 2023-01-01: 36560; 2023-02-01: 36560; 2023-03-01: 36560 | 210075 | GBP | 4.45
24 | FOH MEP | CEC | 375000 | 2022-10-01 |  | 2022-11-01: 81250; 2022-12-01: 162500; 2023-01-01: 162500 | 781250 | EUR | 3.85
25 | Acoustic | Acoustic Middle East | 18600 | 2022-09-01 |  | 2022-11-01: 13950; 2023-01-01: 13950 | 46500 | USD | 3.676
26 | Art Consultant | Amelie Maison D’Art | 169400 | 2022-10-01 |  | 2022-12-01: 84700; 2023-02-01: 84700 | 338800 |  | 1
27 | RERA Valuation | Land Sterling | 17414.25 | 2022-10-01 |  | 2022-12-01: 15755.75 | 33170
28 | TRAVEL COST | Various Traval Companies | 1648076.5 | 2022-10-01 |  | 2022-11-01: 50000; 2022-12-01: 50000; 2023-01-01: 50000; 2023-02-01: 50000; 2023-03-01: 50000 | 1898076.5
29 | HOTEL OPERATOR | DORCHESTER | 1594892.92 | 2022-09-01 |  | 42460 | 42460 | 42460 | 42460 | 42460 | 345730 | 750090 |  | 207880 | 3110892.92
30 | ELV Consultancy | EM-TEC |  |  |  | 2022-12-01: 27500; 2023-02-01: 27500 | 55000
31 | RECRUITMENTS | Daniel Turner | 228600 | 2022-10-01 |  | 2023-01-01: 55000; 2023-03-01: 55000 | 338600
32 | BRANDING CONSULTANT | Construct | 450034.0625 | 2022-10-01 |  | 2022-11-01: 237843.2262; 2022-12-01: 237843.2262; 2023-01-01: 237843.2262; 2023-02-01: 237843.2262; 2023-03-01: 237843.2262 | 1639250.1935
33 | FF&E PROCUREMNT | Furnish Hospitality | 20000 | 2022-10-01 |  | 0 | 20000 | 0 | 0 | 0 | 0 |  |  |  | 40000
Marketing Payments
34 | PROCUREMENT & STOCK CONTROL PLATFORM | Fourth Limited | 20218 | 2022-10-01 |  | 2022-11-01: 42274; 2023-01-01: 42274; 2023-03-01: 42274 | 147040
35 | SERVICES | Elitser Technologies | 35415 | 2022-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 35415
36 | IT SERVICES | IGME InformationTechnology | 31758 | 2022-10-01 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 31758
69897986.7731
CONSULTANCY FEES - RESIDNCE FIT OUT PROJECT
| Consultant Name | Description | Amt Certified | Period |  | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | Cumulative Upto date
Monthly Fee Consultancy Services
| GAJ | ID supervision | 839142.581 | 2022-09-22 |  | 125720 | 125720 | 106720 | 106720 | 106720 | 133400 |  |  |  | 1544142.581
| Ian Banham & Associates | MEP supervision | 674066.6667 | 2022-09-22 |  | 102000 | 102000 | 102000 | 102000 | 102000 | 93933.33 |  |  |  | 1277999.9967
| Light Touch - RESIDENCES | Lighting | 171730 | 2022-09-22 |  | 21660 | 21660 | 21660 | 21660 | 20320 | 30720 |  |  |  | 309410
| Critical Path | Planning consultant | 146480 | 2022-09-22 |  | 2022-10-01: 20000; 2022-11-01: 13904; 2022-12-01: 13904; 2023-01-01: 13904; 2023-02-01: 7808 | 216000
| CEC | 2701 MEP design | 50000 | 2022-09-22 |  | 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0 | 50000
| STG Innovations | 2701 Images | 18166.5 | May-22 |  | 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0 | 18166.5
| Gilles & Boissier | 2701 ID design | 257400 | Oct-22 |  | 2023-03-01: 9100 | 266500
3682219.0776

## Sheet1
Plot-18
Calculation of
Ref. | Description | Amount
1 | G&B Balance Consultancy Fee | 716468.2
2 | ADD : G&B for unit 10-01 design Fee | 300000
3 | ADD : Increse travel Expenses + Contingencies | 150000
1166468.2

## RESI
DORCHESTER HOTEL & RESIDENCIES
Consultant Name | Description | Approved amount(AED) | Amt Certified | Period | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01
GAJ | ID supervision | 1544143
Ian Banham & Associates | MEP supervision | 1278000
Light Touch - RESIDENCES | Lighting | 309410
Critical Path | Planning consultant | 216000
CEC | 2701 MEP design | 50000
STG Innovations | 2701 Images | 18166.5
Gilles & Boissier | 2701 ID design | 266500

## DOCHESTER
550000
60Daays
[7 empty] | 15% | 35% |  | 10%
|  | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01
DORCHESTER | NEW TSA | 36760 | 36760 | 36760 | 36760 | 36760 | 36760 | 36760
| TSA | 2023-03-01: 303270; 2023-04-01: 707630; 2023-06-01: 202180
| EXPENSES | 5700 | 5700 | 5700 | 5700 | 5700 | 5700 | 5700 | 5700 | 5700
| TOTAL | 42460 | 42460 | 42460 | 42460 | 42460 | 345730 | 750090 | 5700 | 207880