## 1C. FCR
|  | Project Name | Plot 18
|  | Plot Number | Plot 18
|  | FCR for Month ending | December 2022 | [22 empty] | 4399300.81
|  | Previous Month | October 2022 | [31 empty] | 50% |  | 50%
|  | Approved Business Plan | December 2017 | [31 empty] | TOC RESI |  | TOC KCE
[22 empty] | 2022 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023
Cost Code |  | Scope of Work | Consultant / Regulatory Authority / Contractor | Approved Business Plan Dec 2017 (Superseded) | TARGET BUDGET | Previous month Forecast Cost October 2022 | Current month Forecast Cost November 2022 | % of Total Cost | Variance with Budget | Variance with last month | Current month Forecast Cost December 2022 | Total Budget (Upto June 23) | Payments Certified by QS December 2022 | Payments Certified by QS December 2022 | % of works Certified | Balance to Certify | Actual amount paid by Finance (as at the end of December 2022) | Actual amount paid as % of Certified | Balance to pay |  |  | 2022-12-11 | 2023-01-11 | 2023-02-11 | 2023-03-11 | 2023-04-11 | 2023-05-11 | 2023-06-11 | 2023-07-11 | 2023-08-11 | 2023-09-11 | 2023-10-11 | 2023-11-11 | 2023-12-11 | 2024-01-11 | 2024-02-11 | 2024-03-11 | 2024-04-11 | 2024-05-11 | 2024-06-11 | Total future cash flow | Variance | Check | Check
1 | bar: 2024-01-11; 2024-03-11
| A | CONSULTANCY FEES |  | 1 | 2 | bar: 2023-01-11; 2023-03-11; 2024-01-11 to 2024-03-11
|  | ONGOING CONSULTANCY AGREEMENTS |  | 31984813.8 | 43379967.62 | 68387796.7862 | 68705296.7862 | 5.189% | 36720482.9862 | 317500 | 68705296.7862 |  | 64348579.9816 | 56553225.412 | 93.66% | 4356716.8046 | 59718557.8261 | 92.8% | 8986738.9601 | bar: 2024-01-11; 2024-03-11
| 1 | ARCHITECT DESIGN - LEAD (FC BTP @4.8) | FOSTERS & PARTNERS | 18822918 | 18822918 | 18822918 | 18822918 | 1.652% | 0 | 0 | 18822918 | 25038430.342 | 18822918 | 24370930.342 | 100% | 0 | 18822918 | 100% | 0 | [21 empty] | 0 | 0 | TRUE | TRUE | bar: 2024-01-11; 2024-03-11
| 2 | ARCHITECT - SUPERVISION LEAD (FC @4.8) | FOSTERS & PARTNERS | 5856000 | 5856000 | 8802472.9062 | 8802472.9062 | 0.7724% | 2946472.9062 | 0 | 8802472.9062 |  | 8629887.7916 |  | 98.04% | 172585.1146 | 8629887.7916 | 100% | 172585.1146 |  | 0 |  | 49553.333 | 49553.333 | 49553.333 | 23925.1156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 172585.1146 | 0 | TRUE | TRUE
| 3 | INTERIOR DESIGNER | G&B | 3789345.8 | 11600000 | 13413557.68 | 13413557.68 | 1.177% | 9624211.88 | 0 | 13413557.68 | 7464339.729 | 12032894.14 | 7362361.16 | 89.71% | 1380663.54 | 12032894.14 | 100% | 1380663.54 |  | 0 |  | 300000 | 298057.68 | 300000 | 282605.86 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1380663.54 | 0 | TRUE | TRUE
| 6 | TRAFFIC ACCESS STUDY | AL TURATH | 125000 | 213000 | 262620 | 262620 | 0.02304% | 137620 | 0 | 262620 | 105000 | 257620 | 100000 | 98.1% | 5000 | 257620 | 100% | 5000 |  | 0 |  | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | TRUE | TRUE
| 7 | PROJECT MONITOR | CONIN | 0 | 1350000 | 2378109.38 | 2378109.38 | 0.2087% | 2378109.38 | 0 | 2378109.38 | 2434218.75 | 2188265.63 | 2188265.63 | 92.02% | 189843.75 | 2188265.63 | 100% | 189843.75 |  | 0 |  | 75937.5 | 37968.75 | 37968.75 | 37968.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189843.75 | 0 | TRUE | TRUE
| 8 | Q.S FEES | HQS - EXCOMM-ECON-DUMEEQS-EBN | 100000 | 100000 | 1224043.68 | 1224043.68 | 0.1074% | 1124043.68 | 0 | 1224043.68 | 945447.91 | 1158817.77 | 861447.91 | 94.67% | 65225.91 | 1158817.77 | 100% | 65225.91 |  | 0 |  | 21000 | 11500 | 11500 | 11500 | 9725.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65225.91 | 0 | TRUE | TRUE
| 10 | SURVEY SERVICES, OQOOD SUBMISSION | PRD | 191300 | 351300 | 198190 | 198190 | 0.01739% | 6890 | 0 | 198190 |  | 151110 | 151110 | 76.25% | 47080 | 151110 | 100% | 47080 |  | 0 |  | 0 | 0 | 0 | 47080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47080 | 0 | TRUE | TRUE
| 11 | TRAVEL COST | VARIOUS | 113500 | 2099999.62 | 1898076.5 | 1898076.5 | 0.1665% | 1784576.5 | 0 | 1898076.5 |  | 1818076.5 | 1818076.5 | 95.79% | 80000 | 1818076.5 | 100% | 80000 |  | 0 |  | 15000 | 15000 | 15000 | 15000 | 15000 | 5000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 0 | TRUE | TRUE
| 12 | F&B CONSULTANT | FONDUE |  |  | 327450 | 327450 |  |  | 0 | 327450 | 347675 | 305450 | 305450 | 93.28% | 22000 | 248600 | 81.39% | 78850 |  | 0 | 2023-01-11: 50000; 2023-02-11: 28850 | 78850 | 0 | TRUE | TRUE
| 13 | HOTEL OPENING | ROYA |  |  | 1340000 | 1340000 |  |  | 0 | 1340000 | 1460000 | 1220000 | 1220000 | 91.04% | 120000 | 1180000 | 96.72% | 160000 |  | 0 | 2023-01-11: 40000; 2023-02-11: 40000; 2023-03-11: 40000; 2023-04-11: 40000 | 160000 | 0 | TRUE | TRUE
| 15 | HOTEL OPERATOR | DORCHESTER | 2026750 | 2026750 | 2767000 | 2767000 | 0.2428% | 740250 | 0 | 2767000 |  | 2298345.82 | 2298345.82 | 83.06% | 468654.18 | 1479865.2045 | 64.39% | 1287134.7955 |  | 0 |  | 55000 | 55000 | 55000 | 303270 | 358270 | 312420 | 148174.7955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1287134.7955 | 0 | TRUE | TRUE
| 18 | NEW LANDSCAPE | LMS, U+A | 0 |  | 436940 | 436940 | 0.03834% | 436940 | 0 | 436940 | 420000 | 240000 | 240000 | 54.93% | 196940 | 210000 | 87.5% | 226940 |  | 0 |  | 40000 | 40000 | 40000 | 40000 | 36940 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226940 | 0 | TRUE | TRUE
| 19 | EXTERIOR AND INTERIOR LIGHTING DESIGN | LIGHT TOUCH | 725000 | 725000 | 485660.22 | 485660.22 | 0.04261% | -239339.78 | 0 | 485660.22 | 388590 | 198970 | 198970 | 40.97% | 286690.22 | 159970 | 80.4% | 325690.22 |  | 0 |  | 125000 | 100000 | 50350 | 50340.22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325690.22 | 0 | TRUE | TRUE
| 20 | SIGNAGE AND WAYWARD FINDING | BRIMAX | 235000 | 235000 | 161000 | 161000 | 0.01413% | -74000 | 0 | 161000 | 235000 | 111000 | 74000 | 68.94% | 50000 | 111000 | 100% | 50000 |  | 0 |  | 14571.4286 | 17714.2857 | 17714.2857 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | TRUE | TRUE
| 21 | MIRAGE RESOURCES - PROJECT MANAGERS | MIRAGE |  |  | 8281242 | 8281242 | 0.7266% | 8281242 | 0 | 8281242 | 8953029 | 7116501.19 | 7116501.19 | 85.94% | 1164740.81 | 6850932.51 | 96.27% | 1430309.49 |  | 0 |  | 479159.5637 | 479159.5637 | 239434.2288 | 232556.1338 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1430309.49 | 0 | TRUE | TRUE
| 22 | MEP CONSULTANT | WME |  |  | 1632000 | 1632000 |  |  | 0 | 1632000 | 2207397.85 | 1327397.85 | 1327397.85 | 81.34% | 304602.15 | 826064.52 | 62.23% | 805935.48 |  | 0 |  | 233142.8571 | 233142.8571 | 214506.9086 | 125142.8571 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 805935.48 | 0 | TRUE | TRUE
| 23 | FAÇADE ENGINEERING / BMU DESIGN | MEINHARDT |  |  | 152470 | 152470 |  |  | 0 | 152470 | 156790 | 119420 | 119420 | 78.32% | 33050 | 58190 | 48.73% | 94280 |  | 0 |  | 18960 | 18960 | 18960 | 18960 | 18440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94280 | 0 | TRUE | TRUE
| 24 | STRUCTURAL CONSULTANT | BG&E |  |  | 414800 | 732300 |  |  | 317500 | 732300 | 732300 | 550580 | 550580 | 75.19% | 181720 | 334800 | 60.81% | 397500 |  | 0 |  | 122500 | 80000 | 90000 | 35000 | 35000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 397500 | 0 | TRUE | TRUE
| 25 | L17 & L29 RESTAURANTS | MITCHELL & EADES |  |  | 614000 | 614000 |  |  | 0 | 614000 | 525200 | 430037.5 | 422100 | 70.04% | 183962.5 | 430037.5 | 100% | 183962.5 |  | 0 |  | 50000 | 50000 | 50000 | 33962.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183962.5 | 0 | TRUE | TRUE
| 26 | IT CONSULTANT | MEDIA TECH |  |  | 147600 | 147600 |  |  | 0 | 147600 | 190572 | 103072 | 103072 | 69.83% | 44528 | 62500 | 60.64% | 85100 |  | 0 | 2023-01-11: 25100; 2023-02-11: 20000; 2023-03-11: 20000; 2023-04-11: 20000 | 85100 | 0 | TRUE | TRUE
| 27 | FIRE SAFETY CONSULTANCY | VORTEX |  |  | 170000 | 170000 |  |  | 0 | 170000 | 206500 | 143350 | 143350 | 84.32% | 26650 | 64775 | 45.19% | 105225 |  | 0 | 2023-01-11: 20000; 2023-02-11: 20000; 2023-03-11: 20000; 2023-04-11: 24175; 2023-05-11: 21050 | 105225 | 0 | TRUE | TRUE
| 28 | SUPERVISION SERVICES - BSBG | BSBG |  |  | 2444736 | 2444736 |  |  | 0 | 2444736 | 3419895 | 3117694 | 3117694 | 127.5% | -672958 | 1752944 | 56.23% | 691792 |  | 0 |  | 220805.875 | 273227.75 | 197758.375 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 691792 | 0 | TRUE | TRUE
| 30 | ID Supervision-Hotel | GAJ |  |  | 875040.42 | 875040.42 |  |  | 0 | 875040.42 | 1125100.41 | 397704.42 | 397704.42 | 45.45% | 477336 | 288554.26 | 72.55% | 586486.16 |  | 0 |  | 150000 | 150000 | 150000 | 136486.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 586486.16 | 0 | TRUE | TRUE
| 31 | FOH MEP | CEC |  |  | 320000 | 320000 |  |  | 0 | 320000 | 781981.22 | 243750 | 700731.22 | 76.17% | 76250 | 243750 | 100% | 76250 |  | 0 |  | 50000 | 26250 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76250 | 0 | TRUE | TRUE
| 32 | Acoustic | Acoustic Middle East |  |  | 46500 | 46500 |  |  | 0 | 46500 | 46500 | 18600 | 18600 | 40% | 27900 | 18600 | 100% | 27900 |  | 0 |  | 18600 | 9300 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27900 | 0 | TRUE | TRUE
| 33 | Cleaning Mock-ups (Level 8) | Magnum Plus |  |  | 70800 | 70800 |  |  | 0 | 70800 | 77152.52 | 41752.52 | 41752.52 | 58.97% | 29047.48 | 35400 | 84.79% | 35400 |  | 0 |  | 6000 | 8800 | 10000 | 10600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35400 | 0 | TRUE | TRUE
| 34 | Recrutment | Daniel Turne |  |  | 328600 | 328600 |  |  | 0 | 328600 | 228600 | 228600 | 228600 | 69.57% | 100000 | 117000 | 51.18% | 211600 |  | 0 |  | 60000 | 60000 | 91600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211600 | 0 | TRUE | TRUE
| 35 | Art Consultant | Amelie Maison D’Art |  |  | 338800 | 338800 |  |  | 0 | 338800 | 3559806.25 | 1059350.6 | 1059350.6 | 312.7% | -720550.6 | 169400 | 15.99% | 169400 |  | 0 |  | 50000 | 50000 | 50000 | 19400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169400 | 0 | TRUE | TRUE
| 36 | RERA Valuation | Land Sterling |  |  | 33170 | 33170 |  |  | 0 | 33170 |  | 17414.25 | 17414.25 | 52.5% | 15755.75 | 16585 | 95.24% | 16585 |  | 0 |  | 16585 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16585 | 0 | TRUE | TRUE
| 37 | INACTIVE CONSULTANCY AGREEMENTS |  | 14528816.2 | 14282191.19 | 25127809.84 | 25127809.84 | 1.287% | -238062.55 | 0 | 25127809.84 |  | 25127809.84 | 25127809.84 | 100% | 0 | 25127809.84 | 100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
|  | TOTAL CONSULTANCY FEES |  | 46513630 | 57662158.81 | 93515606.6262 | 93833106.6262 | 6.475% | 47319476.6262 | 317500 | 93833106.6262 |  | 89476389.8216 | 81681035.252 | 95.36% | 4356716.8046 | 84846367.6661 | 94.83% | 8986738.9601 |  | 0 | 0 | 2311915.5574 | 2172484.2196 | 1769345.881 | 1507972.5965 | 694425.91 | 382420 | 148174.7955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8986738.9601 | 0 | TRUE | TRUE
0 | bar: 2024-01-11; 2024-03-11
| B | LOCAL AUTHORITY FEES | [18 empty] | 0 | bar: 2023-01-11; 2023-03-11; 2024-01-11; 2024-03-11
| 1 | POWER CONNECTION (TCL 7MW) | DEWA | 5739077 | 6465200 | 8087188 | 8087188 | 0.7096% | 2348111 | 0 | 8087188 |  | 8087188 | 8087188 | 100% | 0 | 8087188 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 2 | POWER CONNECTION (TCL INCREASE BY 3.5MW) | DEWA | 0 | 3500000 | 75019.9 | 75019.9 | 0.006583% | 75019.9 | 0 | 75019.9 |  | 75019.9 | 75019.9 | 100% | 0 | 75019.9 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 3 | WATER CONNECTION/CHARGERS | DEWA | 150000 | 150000 | 958457 | 958457 | 0.0841% | 808457 | 0 | 958457 |  | 343175.94 | 343175.94 | 35.81% | 615281.06 | 277251.94 | 80.79% | 681205.06 |  | 0 |  | 247000 | 100000 | 100000 | 100000 | 68281.06 | 65924 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 681205.06 | 0 | TRUE | TRUE
| 4 | SUBSTATION FEES | DEWA | 1577000 | 1577000 | 1577000 | 1577000 | 0.1384% | 0 | 0 | 1577000 |  | 1577000 | 1577000 | 100% | 0 | 1577000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 5 | DUBAI CIVIL DEFENSE | DCD | 213649 | 213649 | 28920 | 28920 | 0.002538% | -184729 | 0 | 28920 |  | 28920 | 28920 | 100% | 0 | 28920 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 6 | CIVIL AVIATION |  | 5000 | 5000 | 5000 | 5000 | 0.0004387% | 0 | 0 | 5000 |  | 0 | 0 | 0% | 5000 | 0 | 0% | 5000 |  | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | TRUE | TRUE
| 7 | PERMIT/ NOC CHARGES | DUBAI MUNICIPALITY / DP | 894554 | 894554 | 727472 | 727472 | 0.06383% | -167082 | 0 | 727472 |  | 727472 | 727472 | 100% | 0 | 727472 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 8 | ADDITIONAL GFA COSTS (80/FT2) | DUBAI MUNICIPALITY | 2071852 | 2017852 | 0 | 0 | 0% | -2071852 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 9 | BUILDING PERMIT EXCEPTION FEES | DUBAI MUNICIPALITY | 1500000 | 70331 | 1406619 | 1406619 | 0.1234% | -93381 | 0 | 1406619 |  | 1406619 | 1406619 | 100% | 0 | 1406619 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 10 | INCREASED POWER (SUBSTATION CONTRIBUTION) | DP | 4080000 | 277449 | 5548976 | 5548976 | 0.4869% | 1468976 | 0 | 5548976 |  | 5548976 | 5548976 | 100% | 0 | 5548976 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 11 | ADDITIONAL HEIGHT | DP | 6710000 | 6710000 | 6710000 | 6710000 | 0.5888% | 0 | 0 | 6710000 |  | 6710000 | 6710000 | 100% | 0 | 6710000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 12 | ANNUAL MASTER-COMM CHARGES (2016-2020) | DP | 4662471 | 4962471 | 1619005.54 | 2734726.83 | 0.24% | -1927744.17 | 1115721.29 | 2734726.83 |  | 2734726.83 | 2734726.83 | 100% | 0 | 2734726.83 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 13 | DPG ADDITIONAL GFA COSTS (190/FT2) | DP | 4830000 | 4830000 | 10300000 | 10300000 | 0.9038% | 5470000 | 0 | 10300000 |  | 10300000 | 10300000 | 100% | 0 | 10300000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 14 | CONNECTION CHARGE+Deposit | EMPOWER | 6413181 | 6419181 | 6161400 | 6161400 | 0.5406% | -251781 | 0 | 6161400 |  | 6161400 | 6161400 | 100% | 0 | 6161400 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 15 | DEMAND CHARGERS/SECURITY | EMPOWER | 855000 | 855000 | 5568314 | 5568314 | 0.4886% | 4713314 | 0 | 5568314 |  | 2790796.14 | 2790796.14 | 50.12% | 2777517.86 | 2790796.14 | 100% | 2777517.86 |  | 0 | 0 | 379099.4 | 125000 | 350000 | 650000 | 150000 | 150000 | 650000 | 323418.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2777517.86 | 0 | TRUE | TRUE
| 16 | LEED CERTIFICATION FEES | USGBC | 133216 | 35000 | 4411 | 4411 | 0.000387% | -128805 | 0 | 4411 |  | 4411 | 4411 | 100% | 0 | 4411 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 17 | LEGAL FEES AND FINANCE CHARGES | VARIOUS | 1820000 | 1650000 | 1546782 | 1546782 | 0.1357% | -273218 | 0 | 1546782 |  | 1546782 | 1546782 | 100% | 0 | 1546782 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 18 | RTA & DLD | RTA & DLD | 25000 | 2500 | 5681 | 5681 | 0.0004985% | -19319 | 0 | 5681 |  | 5681 | 5681 | 100% | 0 | 5681 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 19 | TECOM | TECOM | 50000 | 50000 | 18700 | 18700 | 0.001641% | -31300 | 0 | 18700 |  | 18700 | 18700 | 100% | 0 | 18700 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
|  | TOTAL LOCAL AUTHORITY FEES |  | 41730000 | 40685187 | 50348945.44 | 51464666.73 | 4.516% | 9734666.73 | 1115721.29 | 51464666.73 |  | 48066867.81 | 48066867.81 | 93.4% | 3397798.92 | 48000943.81 | 99.86% | 3463722.92 |  |  | 0 | 626099.4 | 230000 | 450000 | 750000 | 218281.06 | 215924 | 650000 | 323418.46 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 3463722.92 | 5.5879e-09 | FALSE | TRUE
| C | CAPITAL WORKS | bar: 2023-01-11; 2023-03-11; 2024-01-11; 2024-03-11
| 1 | FACILITATING WORKS |  | 40000000 | 40587829.04 | 40587829.04 | 40587829.04 | 3.561% | 587829.04 | 0 | 40587829.04 |  | 40587828.83 | 40587828.83 | 100% | 0.21 | 40587828.83 | 100% | 0.21 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | -0.21 | FALSE | FALSE
| 1.1 | PILING, SHORING & ENABLING WORKS | NSCC | 40000000 | 40559649.04 | 40559649.04 | 40559649.04 | 3.559% | 559649.04 | 0 | 40559649.04 |  | 40559648.83 | 40559648.83 | 100% | 0.21 | 40559648.83 | 100% | 0.21 | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | -0.21 | FALSE | FALSE
| 1.2 | OME SITE ESTABLISHMENT | VARIOUS | 0 | 28180 | 28180 | 28180 | 0.002473% | 28180 | 0 | 28180 |  | 28180 | 28180 | 100% | 0 | 28180 | 100% | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 2+3+4+5 | RP TOTAL - MAIN WORKS & PROVISIONAL SUMS & CONTRACT FEES NOVATED |  | 730862422 | 753126225.04 | 507541746.9409 | 507541746.9409 |  |  | 0 | 507541746.9409 |  | 583165175.8896 | 583165175.8896 |  | -75623428.9487 | 507541746.9409 |  | 0 |  |  | 2023-12-11: 0; 2024-03-11: 0 | 0 | 0 | TRUE | TRUE
[7 empty] | 0 | [14 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6 | LOOSE FF&E | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6.1 | LOOSE FF&E FOR RESIDENTIAL AND HOTEL | TBA | 40269400 | 32000000 | 26300000 | 26300000 | 2.797% | -12269400 | 0 | 26300000 |  | 9173382.3781 | 9173382.3781 | 34.88% | 17126617.6219 | 5625903.5 | 61.33% | 20674096.5 |  | 0 | 0 | 1945720.36 | 2378317.8143 | 2808487.27 | 3600855.75 | 5177374.1795 | 3217034.7862 | 1546306.34 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20674096.5 | 0 | TRUE | TRUE
| 6.2 | BOH EQUIPMENT-Commercial Kitchen and Laundry | TBA | 13000000 | 11077300 | 7162178 | 7162178 | 1.199% | -1002700 | 0 | 7162178 |  | 2608796.1 | 2608796.1 | 36.42% | 4553381.9 | 2608796.1 | 100% | 4553381.9 |  | 0 |  | 852343.236 | 1741752.844 | 744451.12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1214834.7 | 0 | 0 | 0 | 4553381.9 | 0 | TRUE | TRUE
| 6.2.1 | Commercial Kitchen and Laundry | [6 empty] | 0 | [9 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 6.2.2 | Gym Equipment | [6 empty] | 0 | [9 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE | Moved to Hotel public
[9 empty] | 0 | [9 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE | Moved to Hotel public
| 6 | LOOSE FF&E |  | 53269400 | 43077300 | 33462178 | 33462178 | 2.936% | -19807222 | 0 | 33462178 |  | 11782178.4781 | 11782178.4781 | 35.21% | 21679999.5219 | 8234699.6 | 69.89% | 25227478.4 |  |  | 0 | 2798063.596 | 4120070.6583 | 3552938.39 | 3600855.75 | 5177374.1795 | 3217034.7862 | 1546306.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1214834.7 | 0 | 0 | 0 | 25227478.4 | 0 | TRUE | TRUE
[22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7 | RESIDENCES FIT-OUT | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7.1 | Residences - Fit out Package |  | 0 | 18445000 | 95159810.83 | 95159810.83 | 8.35% | 95159810.83 | 0 | 95159810.83 |  | 71836657.91 | 71836657.91 | 75.49% | 23323152.92 | 69094809.3224 | 96.18% | 26065001.5076 |  | 0 |  | 9600000 | 9700467.6849 | 2528864.9812 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4235668.8415 |  | 0 | 0 | 0 | 0 | 26065001.5076 | 0 | TRUE | TRUE
| 7.2 | Residential Kitchen appliances |  |  |  | 3100000 | 3100000 |  |  |  | 3100000 |  |  |  |  | 3100000 |  |  | 3100000 |  | 0 |  | 1729800 | 446400 | 334800 | 279000 | 155000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155000 | 0 | 0 | 0 | 0 | 0 | 3100000 | 0 | TRUE | TRUE
| 7.3 | Residences - Fit out Package Consultancy Fee |  | 0 | 18445000 | 3682219.5 | 3682219.5 | 0.3231% | 3682219.5 | 0 | 3682219.5 |  | 3026717.62 | 3026717.62 | 82.2% | 655501.88 | 3237931.08 | 107% | 444288.42 |  | 0 |  | 150000 | 150000 | 144288.42 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 444288.42 | 0 | TRUE | TRUE
| 7.4 | Purchaser Customizations |  | 0 | 644645 | 644645 | 644645 | 0.05656% | 644645 | 0 | 644645 |  | 0 | 0 | 0% | 644645 | 0 | 0% | 644645 |  | 0 |  | 359711.91 | 92828.88 | 69621.66 | 58018.05 | 32232.25 | 32232.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 644645 | 0 | TRUE | TRUE
| 7 | RESIDENCES FIT-OUT |  | 0 | 37534645 | 102586675.33 | 102586675.33 | 9.002% | 102586675.33 | 0 | 102586675.33 |  | 74863375.53 | 74863375.53 | 72.98% | 27723299.8 | 72332740.4024 | 96.62% | 30253934.9176 |  |  | 0 | 11839511.91 | 10389696.5649 | 3077575.0612 | 337018.05 | 187232.25 | 32232.25 | 0 | 0 | 0 | 0 | 0 | 0 | 4390668.8415 | 0 | 0 | 0 | 0 | 0 | 30253934.9276 | 0.01 | FALSE | TRUE
[22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8 | Residences - Furniture Package |  | 0 | 56015000 | 53828987.2 | 53828987.2 | 4.723% | 53828987.2 | 0 | 53828987.2 |  | 4525180.49 | 4525180.49 | 8.407% | 49303806.71 | 4521008.3471 | 99.91% | 49307978.8529 |  | 0 | 0 | 1072292.21 | 378210 | 8202932 | 7218408 | 9059761 | 12678710 | 6907530.97 | 3790134.6729 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49307978.8529 | 0 | TRUE | TRUE
[21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 19982204.03 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9 | NEW CONTRACTOR - KHANSAHEB |  | 0 | 56015000 | 194951733.75 | 194951733.75 | 17.11% | 194951733.75 | 0 | 194951734 |  | 104356336.266 | 104356336.266 | 53.53% | 90595397.484 | 84551414.399 | 81.02% | 110400319.601 |  | 0 |  | 20000000 | 20000000 | 15000000 | 15000000 | 15000000 | 18880319.601 |  | 0 |  | 0 | 0 | 0 | 0 |  | 6520000 | 0 | 0 | 0 | 110400319.601 | 0 | TRUE | FALSE
[21 empty] | 0 | [19 empty] | 0 | 0 | TRUE | TRUE | bar: 2024-01-11; 2024-03-11
| 9.1 | Fit Out Package - F&B Hotel | [7 empty] | 23000000 | 23000000 |  | 962551.45 | 962551.45 | 4.185% | 22037448.55 | 559353.9 | 58.11% | 22440646.1 |  | 0 | 2023-01-11: 1000000; 2023-02-11: 1440646.1; 2023-03-11: 5000000; 2023-04-11: 5000000; 2023-05-11: 5000000; 2023-06-11: 5000000 | 22440646.1 | 0 | TRUE | FALSE
[41 empty] | 0 | 0 | TRUE | TRUE
| 9.2 | Facility Management / Operational Costs-Operational Supplies and Equipment | [7 empty] | 5000000 | 5000000 |  | 1397466.38 | 1397466.38 | 27.95% | 3602533.62 | 1011754.18 | 72.4% | 3988245.82 |  |  | 2023-01-11: 664707.6367; 2023-02-11: 664707.6367; 2023-03-11: 664707.6367; 2023-04-11: 664707.6367; 2023-05-11: 664707.6367; 2023-06-11: 664707.6367 | 3988245.82 |  | TRUE | FALSE
[21 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10 | PAYMENTS TO RPJV SUBCONTRACTORS / SUPPLIERS | [18 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10.1 | Direct Payments (RPJV Historical Debt) |  | 40269400 | 32000000 | 25000000 | 25000000 | 2.194% | -12269400 | 0 | 25000000 |  | 25000000 | 25000000 | 100% | 0 | 25000000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 10.2 | Accrued retention payable to continuing SCs |  | 13000000 | 11077300 | 24000000 | 24000000 | 2.106% | -1002700 | 0 | 24000000 |  |  |  |  | 24000000 | 0 | 0% | 24000000 | [5 empty] | 0 | 0 | 12000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12000000 | 0 | 0 | 0 | 24000000 | 0 | TRUE | TRUE
| 10.3 | Advance payment credit (direct) |  |  |  | -4000000 | -4000000 | -0.351% | -4000000 | 0 | -4000000 |  | -4000000 | -4000000 | 100% | 0 | -4000000 |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 10.4 | Advance payment credit (PS) |  |  |  | -11600000 | -11600000 | -1.018% | -11600000 | 0 | -11600000 |  | -11600000 | -11600000 | 100% | 0 | -11600000 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE | Moved to Hotel public
[9 empty] | 0 | [9 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE | Moved to Hotel public
| 10 | PAYMENTS TO RPJV SUBCONTRACTORS / SUPPLIERS |  | 53269400 | 43077300 | 33400000 | 33400000 | 2.931% | -19869400 | 0 | 33400000 |  | 9400000 | 9400000 | 28.14% | 24000000 | 9400000 | 100% | 24000000 |  |  | 0 | 0 | 0 | 0 | 0 | 12000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000000 | 0 | 0 | 0 | 24000000 | 0 | TRUE | TRUE
[22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | TOTAL CAPITAL WORKS |  | 730862422 | 753126225.04 | 966359150.2609 | 966359150.2609 | 87.25% | 235496728.2609 | 28000000 | 994359150.5109 |  | 831040093.3136 | 831040093.3136 | 83.58% | 163319056.9472 | 728740546.5994 | 87.69% | 265618603.9015 |  |  | 0 | 37374575.3527 | 36993330.9599 | 35498153.0878 | 31820989.4367 | 47089075.0662 | 40473004.2739 | 8453837.31 | 3790134.6729 | 0 | 0 | 0 | 0 | 4390668.8415 | 0 | 19734834.7 | 0 | 0 | 0 | 265618603.7015 | -0.2 | FALSE | FALSE
0 | bar: 2024-01-11; 2024-03-11
| D | CONTINGENCIES | bar: 2023-01-11; 2023-03-11; 2024-01-11; 2024-03-11
| 1 | CONSULTANT AND AUTHORITY FEES |  | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 2 | PRE-CONTRACT AND CAPITAL WORKS |  | 35504278.85 | 19902701 | 0.2 | 0.2 | 1.755e-08% | -35504278.65 | 0 | 0.2 |  |  |  | 0% | 0.2 |  | 0% | 0.2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.2 | FALSE | FALSE
|  | TOTAL CONTINGENCIES |  | 35504278.85 | 19902701 | 0.2 | 0.2 | 1.755e-08% | -35504278.65 | 0 | 0.2 |  | 0 | 0 | 0% | 0.2 | 0 | 0% | 0.2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | -0.2 | FALSE | FALSE
|  | TOTAL COST FOR THE PROJECT (A + B + C + D - E) |  | 854610330.85 | 871376271.85 | 1110223702.3271 | 1111656923.8171 | 100% | 257046592.9671 | 29433221.29 | 1139656924.0671 |  | 968583350.9452 | 960787996.3756 | 84.99% | 171073572.8718 | 861587858.0755 | 88.95% | 278069065.9816 |  |  | 0 | 40312590.3101 | 39395815.1795 | 37717498.9689 | 34078962.0332 | 48001782.0362 | 41071348.2739 | 9252012.1055 | 4113553.1329 | 0 | 0 | 0 | 0 | 4390668.8415 | 0 | 19734834.7 | 0 |  | 0 | 278069065.5816 | -0.4 | TRUE | TRUE
[16 empty] | 1139656923.8171 |  |  | 1139656924.0571

## Cash Flow
CONSULTANCY FEES - HOTEL
| Consultant Name | Description | Final Contract Sum | Amt Certified | Period | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | Variations After November 2022 | Cumulative Upto Date
1 | DESIGN ARCHITECT - SUPERVISION | F+P | 25038430.342 | 24370930.342 | 2022-12-25 |  |  |  | 111250 | 111250 | 111250 | 111250 | 111250 | 111250 |  | 25038430.342 | 667500 | 0 | 158 | 6 | 111250
2 | INTERIOR DESIGN - SUPERVISION | G&B - Hotel | 7464339.729 | 7362361.16 | 2022-10-23 |  |  |  | 16996.4282 | 16996.4282 | 16996.4282 | 16996.4282 | 16996.4282 | 16996.4282 |  | 7464339.729 | 101978.569 | 0 | 221 | 8 | 16996.4282
3 | TRAFFIC ACCESS STUDY | ALTHURATH | 105000 | 100000 | 2022-10-23 |  |  |  | 5000 | [6 empty] | 105000 | 5000 | 0 | 221 | 8 | 833.3333
4 | PROJECT MONITOR | Conin | 2434218.75 | 2188265.63 | 2022-11-24 |  |  | 35136.16 | 35136.16 | 35136.16 | 35136.16 | 35136.16 | 35136.16 | 35136.16 |  | 2434218.75 | 245953.12 | 0 | 189 | 7 | 35136.16
5 | QUANTITY SURVEYING | Excom | 846747.91 | 825747.91 | 2022-12-25 |  |  |  | 10500 | 10500 | [5 empty] | 846747.91 | 21000 | 0 | 158 | 6 | 3500
6 | QUANTITY SURVEYING | ECON | 98700 | 35700 | 2022-12-25 |  |  |  | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 |  | 98700 | 63000 | 0 | 158 | 6 | 10500
7 | SURVEY SERVICES, OQOOD SUBMISSION | PRD |  | 151110 | [5 empty] | 47080 | [5 empty] | 198190 |  |  | 45078 | 6 | 0
8 | TRAVEL COST | Various Travel Companies |  | 1648076.5 | [11 empty] | 1648076.5 |  |  | 45078 | 6 | 0
9 | KITCHEN AND BACK OF HOUSE | Fondue | 347675 | 305450 | 2022-12-25 |  |  |  | 7037.5 | 7037.5 | 7037.5 | 7037.5 | 7037.5 | 7037.5 |  | 347675 | 42225 | 0 | 158 | 6 | 7037.5
10 | HOSPITALITY ADVISORY SERVICES | Roya | 1460000 | 1220000 | 2022-12-25 |  |  |  | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 |  | 1460000 | 240000 | 0 | 158 | 6 | 40000
11 | HOTEL OPERATOR | Dorchester | 0 | 2298345.82 | 2023-01-26 | [10 empty] | 2298345.82 |  |  | 126 | 5 | 0
12 | LANDSCAPE ARCHITECT - SUPERVISION | U+A | 420000 | 240000 | 2022-12-25 |  |  |  | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 |  | 420000 | 180000 | 0 | 158 | 6 | 30000
13 | LIGHTING ENGINEER - SUPERVISION | Light Touch | 388590 | 198970 | 2022-12-25 |  |  |  | 31603.3333 | 31603.3333 | 31603.3333 | 31603.3333 | 31603.3333 | 31603.3333 |  | 388590 | 189620 | 0 | 158 | 6 | 31603.3333
14 | SIGNAGE AND WAYWARD FINDING | Brimax | 235000 | 74000 | 2022-09-22 |  |  |  | 26833.3333 | 26833.3333 | 26833.3333 | 26833.3333 | 26833.3333 | 26833.3333 |  | 235000 | 161000 | 0 | 252 | 9 | 26833.3333
15 | PROJECT MANAGEMENT | Mirage | 8953029 | 7116501.19 | 2022-12-25 |  |  |  | 306087.9683 | 306087.9683 | 306087.9683 | 306087.9683 | 306087.9683 | 306087.9683 |  | 8953029 | 1836527.81 | 0 | 158 | 6 | 306087.9683
16 | MEP ENGINEER - SUPERVISION | WME | 2207397.85 | 1327397.85 | 2022-12-25 |  |  |  | 146666.6667 | 146666.6667 | 146666.6667 | 146666.6667 | 146666.6667 | 146666.6667 |  | 2207397.85 | 880000 | 0 | 158 | 6 | 146666.6667
17 | FAÇADE ENGINEERING / BMU DESIGN | Meinhardt | 156790 | 119420 | 2022-12-25 |  |  |  | 6228.3333 | 6228.3333 | 6228.3333 | 6228.3333 | 6228.3333 | 6228.3333 |  | 156790 | 37370 | 0 | 158 | 6 | 6228.3333
18 | STRUCTURAL ENGINEER - SUPERVISION | BGE | 732300 | 550580 | 2023-01-26 |  |  |  | 0 | 36344 | 36344 | 36344 | 36344 | 36344 |  | 732300 | 181720 | 0 | 126 | 5 | 36344
19 | L17 & L29 RESTAURANTS | Mitchell & Eades (L17 & L29) | 525200 | 389100 | 2023-01-26 |  |  |  | 0 | 27220 | 27220 | 27220 | 27220 | 27220 |  | 525200 | 136100 | 0 | 126 | 5 | 27220
20 | MUSA CAFÉ | Mitchell & Eades (Musa Café) |  | 33000 | 2022-10-23 | [10 empty] | 33000 |  |  | 221 | 8 | 0
21 | IT CONSULTANT | Mediatech | 190572 | 103072 | 2022-11-24 |  |  | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 |  | 190572 | 87500 | 0 | 189 | 7 | 12500
22 | FIRE SAFETY CONSULTANCY | Vortex | 206500 | 143350 | 2022-12-25 |  |  |  | 10525 | 10525 | 10525 | 10525 | 10525 | 10525 |  | 206500 | 63150 | 0 | 158 | 6 | 10525
23 | ARCHITECT OF RECORD - SUPERVISION | BSBG | 3419895 | 3117694 | 2022-12-25 |  |  |  | 50366.8333 | 50366.8333 | 50366.8333 | 50366.8333 | 50366.8333 | 50366.8333 |  | 3419895 | 302201 | 0 | 158 | 6 | 50366.8333
24 | INTERIOR DESIGN - SUPERVISION | GAJ | 1125100.41 | 397704.42 | 2022-12-25 |  |  |  | 121232.665 | 121232.665 | 121232.665 | 121232.665 | 121232.665 | 121232.665 |  | 1125100.41 | 727395.99 | 0 | 158 | 6 | 121232.665
25 | FOH MEP | CEC | 781981.22 | 700731.22 | 2022-12-25 |  |  |  | 13541.6667 | 13541.6667 | 13541.6667 | 13541.6667 | 13541.6667 | 13541.6667 |  | 781981.22 | 81250 | 0 | 158 | 6 | 13541.6667
26 | Acoustic | AME | 46500 | 18600 | 2022-09-22 |  |  |  | 13950 | 13950 | [5 empty] | 46500 | 27900 | 0 | 252 | 9 | 4650
27 | CLEANING SERVICES | Magnum Plus | 77152.52 | 41752.52 | 2022-12-25 |  |  |  | 5900 | 5900 | 5900 | 5900 | 5900 | 5900 |  | 77152.52 | 35400 | 0 | 158 | 6 | 5900
28 | RECRUITMENTS | Danial Turner | 228600 | 228600 | 2022-10-23 | [10 empty] | 228600 | 0 | 0 | 221 | 8 | 0
29 | Art Consultant | AMELIA | 3559806.25 | 1059350.6 | 2023-01-26 |  |  |  | 0 | 500091.13 | 500091.13 | 500091.13 | 500091.13 | 500091.13 |  | 3559806.25 | 2500455.65 | 0 | 126 | 5 | 500091.13
30 | RERA Valuation | Land Sterling |  | 17414.25 | [11 empty] | 17414.25 |  |  | 45078 | 6 | 0
31 | Planning consultant | Critical Path |  | 146480 | [11 empty] | 146480 |  |  | 45078 | 6 | 0
32 | ELV Consultancy | EMTEC | 55000 | 33000 | 2022-12-25 |  |  |  | 22000 | [6 empty] | 55000 | 22000 | 0 | 158 | 6 | 3666.6667
33 | BRANDING CONSULTANT | Construct | 1639250.1935 | 450034.0625 | 2022-10-23 |  |  |  | 198202.6885 | 198202.6885 | 198202.6885 | 198202.6885 | 198202.6885 | 198202.6885 |  | 1639250.1935 | 1189216.131 | 0 | 221 | 8 | 198202.6885
34 | FF&E PROCUREMNT | Furnish Hospitality Trading | 180000 | 40000 | 2022-11-24 |  |  | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 |  | 180000 | 140000 | 0 | 189 | 7 | 20000
35 | DESIGN REVIEW | Salama | 340000 | 340000 | 2022-11-24 | [10 empty] | 340000 | 0 | 0 | 189 | 7 | 0
[17 empty] | 0 | 0 | 45078 | 6 | 0
36 | PROCUREMENT & STOCK CONTROL PLATFORM | FOURTH | 147040 | 20218 | 2022-10-23 |  |  |  | 21137 | 21137 | 21137 | 21137 | 21137 | 21137 |  | 147040 | 126822 | 0 | 221 | 8 | 21137
37 | SERVICES | Elitser Technologies | 35415 | 35415 | 2022-10-23 | [10 empty] | 35415 | 0 | 0 | 221 | 8 | 0
38 | IT SERVICES | IGME | 83758 | 83758 | 2022-11-24 | [10 empty] | 83758 | 0 | 0 | 189 | 7 | 0
39 | FF&E PROCUREMNT | Elite Document Solutions Ltd | 159899.6 | 159899.6 | 2022-12-25 | [10 empty] | 159899.6 | 0 | 0 | 158 | 6 | 0
40 | IT SERVICES | Infrateq | 128500 | 107500 | 2023-01-26 |  |  |  |  | 21000 | [5 empty] | 128500 | 21000 | 0 | 126 | 5 | 4200
41 | IT SERVICES | Samsotech LLC | 81480 | 81480 | 2022-12-25 | [10 empty] | 81480 | 0 | 0 | 158 | 6 | 0
42 | IT SERVICES | Budgeting Solutions Ltd | 38544 | 38544 | 2023-01-26 | [10 empty] | 38544 | 0 | 0 | 126 | 5 | 0
43 | IT SERVICES | Key Information Technology | 94696 | 56817.6 | 2023-01-26 |  |  |  |  | 37878.4 | [5 empty] | 94696 | 37878.4 | 0 | 126 | 5 | 7575.68
44 | IT SERVICES | Al Suwaidi | 11000 | 11000 | 2023-01-26 | [10 empty] | 11000 | 0 | 0 | 126 | 5 | 0
45 | Art Consultant | Ayyam Gallery | 183064.8 | 182890.5 | 2023-01-26 | [10 empty] | 182890.5 | 174.3 | -174.3 | 126 | 5 | 34.86
46 | IT SERVICES | m-hance | 89345.34 | 3933 | 2023-01-26 |  |  |  |  | 17082.468 | 17082.468 | 17082.468 | 17082.468 | 17082.468 |  | 89345.34 | 85412.34 | 0 | 126 | 5 | 17082.468
47 | IT SERVICES | Salt TS | 146000 | 71000 | 2023-01-26 |  |  |  |  | 15000 | 15000 | 15000 | 15000 | 15000 |  | 146000 | 75000 | 0 | 126 | 5 | 15000
48 | IT SERVICES | SevenRooms | 84410 | 5138 | 2023-01-26 |  |  |  |  | 15854.4 | 15854.4 | 15854.4 | 15854.4 | 15854.4 |  | 84410 | 79272 | 0 | 126 | 5 | 15854.4
49 | IT SERVICES | Spire Solutions DMCC |  | 164132.68 | 2022-09-22 | [10 empty] | 164132.68 |  |  | 252 | 9 | 0
50 | IT SERVICES | Oasys | 335091 | 202505.5 | 2022-11-24 |  |  |  | 22097.5833 | 22097.5833 | 22097.5833 | 22097.5833 | 22097.5833 | 22097.5833 |  | 335091 | 132585.5 | 0 | 189 | 7 | 22097.5833
51 | IT SERVICES | Intelity Inc. | 367000 | 169096 | 2022-12-25 |  |  |  | 32984 | 32984 | 32984 | 32984 | 32984 | 32984 |  | 367000 | 197904 | 0 | 158 | 6 | 32984
0
52 | GOVERNMENT FEE | Empower |  | 2657537 | 2023-01-26 | [10 empty] | 2657537 | -2657537
53 | GOVERNMENT FEE | DEWA |  | 285755.52 | 2023-01-26 | [10 empty] | 285755.52 | -285755.52
54 | GOVERNMENT FEE | Business Bay LLC |  | 17657358.29 | 2022-09-22 | [10 empty] | 17657358.29 | -17657358.29
55 | GOVERNMENT FEE | Dubai Civil Defence |  | 8020 | 2022-12-25 | [10 empty] | 8020 | -8020
0
0
CONSULTANCY FEES - RESIDENCE | [16 empty] | 0
0
| Consultant Name | Description |  | Amt Certified | Period | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 |  | Cumulative Upto date
Monthly Fee Consultancy Services
1 | GAJ | ID supervision |  | 839142.581 | Sep-22 | 125720 | 125720 | 106720 | 106720 | 106720 | 133400 |  |  |  |  | 1544142.581
2 | Ian Banham & Associates | MEP supervision |  | 674066.6667 | Sep-22 | 102000 | 102000 | 102000 | 102000 | 102000 | 93933.33 |  |  |  |  | 1277999.9967
3 | Light Touch - RESIDENCES | Lighting |  | 171730 | Sep-22 | 21660 | 21660 | 21660 | 21660 | 20320 | 30720 |  |  |  |  | 309410
4 | Critical Path | Planning consultant |  | 146480 | Sep-22 | 20000 | 13904 | 13904 | 13904 | 7808 | [5 empty] | 216000
5 | CEC | 2701 MEP design |  | 50000 | Sep-22 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 50000
6 | STG Innovations | 2701 Images |  | 18166.5 | May-22 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 18166.5
7 | Gilles & Boissier | 2701 ID design |  | 257400 | Oct-22 | [5 empty] | 9100 |  |  |  |  | 266500
3682219.0776

## QS Certified
|  | 2022-09-22 | 2022-10-23 | 2022-11-24 | 2022-12-25 | 2023-01-26 | Latest Cumilative | Month
1 | F+P | 24037180.342 | 24148430.342 | 24259680.342 | 24370930.342 |  | 24370930.342 | 2022-12-25
2 | G&B - Hotel | 7212211.16 | 7362361.16 |  |  |  | 7362361.16 | 2022-10-23
3 | ALTHURATH | 20000 | 100000 |  |  |  | 100000 | 2022-10-23
4 | Conin | 2112328.13 | 2150296.88 | 2188265.63 |  |  | 2188265.63 | 2022-11-24
5 | Excom | 794247.91 | 804747.91 | 815247.91 | 825747.91 |  | 825747.91 | 2022-12-25
6 | ECON | 4200 | 14700 | 25200 | 35700 |  | 35700 | 2022-12-25
7 | Fondue | 156000 | 180000 | 272600 | 305450 |  | 305450 | 2022-12-25
8 | Roya | 1100000 | 1140000 | 1180000 | 1220000 |  | 1220000 | 2022-12-25
9 | Dorchester | 1561988.12 | 1594892.92 | 1715466.11 | 2004716.11 | 2298345.82 | 2298345.82 | 2023-01-26
10 | U+A | 150000 | 180000 | 210000 | 240000 |  | 240000 | 2022-12-25
11 | Light Touch | 94650 | 127310 | 159970 | 198970 |  | 198970 | 2022-12-25
12 | Brimax | 74000 |  |  |  |  | 74000 | 2022-09-22
13 | Mirage | 6261284.45 | 6547316.84 | 6850932.51 | 7116501.19 |  | 7116501.19 | 2022-12-25
14 | WME | 950064.52 | 1058064.52 | 1166064.52 | 1327397.85 |  | 1327397.85 | 2022-12-25
15 | Meinhardt | 84750 | 98510 | 113620 | 119420 |  | 119420 | 2022-12-25
16 | BGE | 305580 | 375580 | 463080 | 498080 | 550580 | 550580 | 2023-01-26
17 | Mitchell & Eades (L17 & L29) | 254600 | 275600 | 338400 | 372600 | 389100 | 389100 | 2023-01-26
18 | Mitchell & Eades (Musa Café) | 0 | 33000 |  |  |  | 33000 | 2022-10-23
19 | Mediatech | 78072 | 90572 | 103072 |  |  | 103072 | 2022-11-24
20 | Vortex | 51275 | 62775 | 88775 | 143350 |  | 143350 | 2022-12-25
21 | BSBG | 2454736 | 2706194 | 2911944 | 3117694 |  | 3117694 | 2022-12-25
22 | GAJ | 105606 | 197080.42 | 297925.13 | 397704.42 |  | 397704.42 | 2022-12-25
23 | CEC | 456981.22 | 538231.22 | 538231.22 | 700731.22 |  | 700731.22 | 2022-12-25
24 | AME | 18600 |  |  |  |  | 18600 | 2022-09-22
25 | Magnum Plus | 23600 | 29952.52 | 35852.52 | 41752.52 |  | 41752.52 | 2022-12-25
26 | Danial Turner | 54000 | 228600 |  |  |  | 228600 | 2022-10-23
27 | AMELIA | 84700 | 169400 |  |  | 1059350.6 | 1059350.6 | 2023-01-26
28 | Construct | 248004.0625 | 450034.0625 |  |  |  | 450034.0625 | 2022-10-23
29 | Salama | 300000 | 300000 | 340000 |  |  | 340000 | 2022-11-24
30 | EMTEC |  |  |  | 33000 |  | 33000 | 2022-12-25
31 | Furnish Hospitality Trading |  | 20000 | 40000 |  |  | 40000 | 2022-11-24
b. Authorities
1 | Empower | 1917786 | 2060781 | 2147939 | 2656236 | 2657537 | 2657537 | 2023-01-26
2 | DEWA | 109829.94 | 191207.8429 | 191207.8429 | 241013.44 | 285755.52 | 285755.52 | 2023-01-26
3 | Business Bay LLC | 17657358.29 |  |  |  |  | 17657358.29 | 2022-09-22
4 | Dubai Civil Defence |  |  |  | 8020 |  | 8020 | 2022-12-25
c. OSE/IT | [6 empty] | 0 | 0
1 | Elitser Technologies |  | 35415 |  |  |  | 35415 | 2022-10-23
2 | IGME |  | 31758 | 83758 |  |  | 83758 | 2022-11-24
3 | FOURTH |  | 20218 |  |  |  | 20218 | 2022-10-23
4 | Infrateq |  |  | 84000 |  | 107500 | 107500 | 2023-01-26
5 | Oasys |  |  | 202505.5 |  |  | 202505.5 | 2022-11-24
6 | Elite Document Solutions Ltd |  |  |  | 159899.6 |  | 159899.6 | 2022-12-25
7 | Intelity Inc. |  |  |  | 169096 |  | 169096 | 2022-12-25
8 | Samsotech LLC |  |  |  | 81480 |  | 81480 | 2022-12-25
9 | Budgeting Solutions Ltd |  |  |  |  | 38544 | 38544 | 2023-01-26
10 | Key Information Technology |  |  |  |  | 56817.6 | 56817.6 | 2023-01-26
11 | Al Suwaidi |  |  |  |  | 11000 | 11000 | 2023-01-26
12 | Ayyam Gallery |  |  |  |  | 182890.5 | 182890.5 | 2023-01-26
13 | m-hance |  |  |  |  | 3933 | 3933 | 2023-01-26
14 | Salt TS |  |  |  |  | 71000 | 71000 | 2023-01-26
15 | SevenRooms |  |  |  |  | 5138 | 5138 | 2023-01-26
16 | Spire Solutions DMCC | 164132.68 |  |  |  |  | 164132.68 | 2022-09-22
| BSBG | 1159000
| BGE | 110780
| WME | 448000
| Vortex | 24000
| U+A (in lie of LMS) | 0
| Brimax | 74000
Jensen Hughes / Shrimer
| Meinhardt | 40320
| Mediatech | 40572
| CEC | 554892
Fondue
| Light Touch | 5610
2457174

## Final Contract Sums
Consultant Tracker
Item | Consultant | Scope of Works | Contact | Invoice by Consultant | PC Issuence | Historical Debt | Service Agreement | VOs | [6 empty] | Final Contract Sum
[8 empty] | BP-09 | BP Phasing |  | VO-1 |  | VO-2 | EOT
1 | BSBG | Lead Architect | Richard Round |  | Paid | 1159000 | 1729736 | 380444 | 33915 | BP-09-Additional | 41300 |  |  | 1234500 | 3419895
2 | BGE | Structural | Jack Stevenson |  | Paid | 110780 | 449800 | 35000 |  | Canopy | 37500 |  |  | 210000 | 732300
3 | WME | MEP | Ammar Al Sukar |  | Paid | 448000 | 1632000 | [7 empty] | 1632000
4 | Vortex |  | Ashhad Siddiqui |  | Paid | 24000 | 35000 | 26000 | 40500 | Additional works | 75000 | Variation - Units L2-03/04 | 6300 |  | 182800
5 | U+A (in lie of LMS) | Landscape | Brett Ross | No Invoice | Paid | 0 | 300000 | [7 empty] | 300000
6 | Brimax | Signage & Wayfinding | Christian Berglehner |  | Paid | 74000 | 50000 | [7 empty] | 50000
7 | Jensen Hughes / Shrimer |  | Rashid Siddig | No Invoice |  |  | 0 | [7 empty] | 0
8 | Meinhardt | Façade | Paul Grove |  | Paid | 40320 | 116470 | [7 empty] | 116470
9 | Mediatech | ELV | Ged King | No Invoice | Paid | 40572 | 100800 | [7 empty] | 100800
10 | CEC | MEP | Sagr Kulkarni | No Invoice |  | 554892 | 0 | 325000 | [6 empty] | 325000
11 | Fondue | Kitchen Equipment | Mark Burns |  | Paid |  | 96000 |  |  |  | 156000 | Variations | 77450 | 18225 | 347675
12 | Light Touch | Lighting | Paul Miles |  | Paid | 5610 | 123160 |  |  |  | 108000 |  | 60000 |  | 291160
13 | salama | [11 empty] | 40000 |  | 40000
| Mirage |  |  |  |  | 0 | [8 empty] | 0
AME
| GAJ | [5 empty] | 228400 | 896700.42 | [6 empty] | 1125100.42
Hospitality Trading
AL TURATH
EM-TEC
Note on M6: Nayana WJK Weeraman: VO-03 ?
Note on J7: Nayana WJK Weeraman: BP-08A

## Consultant Summary
Consultant | Currency | Amount | Total Amount until June 23 | Conversion factor | Amount in AED
Mirage | AED |  | 8953029 |  | 8953029
| Original Contract Amount | 4441242
| Payment for the Extended Period | 2711787
| EOT (Approximately) | 1800000
F+P | GBP |  | 5626613.56 | 4.45 | 25038430.342
| Original Contract Value | 4620000
| Variations Approved to Date | 271613.56
| LPO ref Plot-18/1989/2020 | 180000
| LPO ref Plot-18/2247/2021 | 126000
| LPO ref Plot-18/2621/2021 | 84000
| LPO ref Plot-18/2779/2021 | 45000
| LPO ref Plot-18/2968/2022 | 45000
| LPO ref Plot-18/3307/2022 | 30000
| LPO ref Plot-18/3397/2022 | 45000
| LPO ref Plot-18/3534/2022 | 30000
| EOT (Approximately) | 150000
BSBG | AED |  | 3419895 |  | 3419895
| Original Contract Value | 1729736
| Variations approved to Date | 455659
| EOT | 1234500
BGE | AED |  | 732300 |  | 732300
| Original Contract Value | 449800
| Variations approved to Date | 72500
| EOT | 210000
WME | AED |  | 2207397.85 |  | 2207397.85
| Original Contract Value | 1632000
Variations approved to Date
| EOT (Approximately) | 575397.85
Light Touch | AED |  | 388590 |  | 388590
| New Contract Amount | 123160
| Settlement Payment | 5610
| Variations Agreed | 96520
| EOT (Approximately) | 163300
U+A | AED |  | 420000 |  | 420000
| Original Contract Value | 300000
Variations approved to Date
| EOT | 120000
G&B - Hotel | EUR |  | 1938789.54 | 3.85 | 7464339.729
| Original Contract Value | 1580000
| Variations approved to Date | 358789.54
EOT
GAJ | AED |  | 1125100.41 |  | 1125100.41
| LPO ref Proj/PLOT18/3324/2022 | 228400
| LPO ref Proj/PLOT18/3647/2022 | 896700.41
Excom | AED |  | 846747.91 |  | 846747.91
| LPO ref Plot-18/1294/2018 | 66000
| LPO ref Plot-18/1380/2019 | 90000
| LPO ref Plot-18/1439/2019 | 72000
| LPO ref Plot-18/1575/2019 | 90000
| LPO ref Plot-18/1926/2020 | 79686.83
| LPO ref Plot-18/2105/2020 | 100999.8
| LPO ref Plot-18/2465/2021 | 252561.28
| LPO ref Plot-18/3165/2022 | 95500
ECON | AED |  | 98700 |  | 98700
| Original Contract Value | 77700
Variations approved to Date
| EOT | 21000
Conin | AED |  | 2434218.75 |  | 2434218.75
| Original Contract Value | 1350000
| Variations approved to Date | 1084218.75
Fondue | AED |  | 347675 |  | 347675
| Contract Amount | 96000
| Variations approved to Date | 251675
Roya | AED |  | 1460000 |  | 1460000
| Original Contract Value | 1220000
Variations approved to Date
| EOT (Approximately) | 240000
IBA | AED |  | 2734401.39 |  | 2734401.39
| LPO ref Plot-18/1400/2019 | 180000
| LPO ref Plot-18/1500/2019 | 492000
| LPO ref Plot-18/1788/2020 | 492000
| LPO ref Plot-18/1924/2020 | 228000
| LPO ref Plot-18/2453/2021 | 472612.89
| LPO ref Plot-18/2920/2021 | 115200
| LPO ref Plot-18/3031/2022 | 396974
| LPO ref Plot-18/3164/2022 | 150000
| LPO ref Plot-18/3318/2022 | 207614.5
ALTHURATH | AED |  | 105000 |  | 105000
| Original Contract Value | 25000
| LPO ref Proj/PLOT18/3467/2022 | 80000
Meinhardt | AED |  | 156790 |  | 156790
| Settlement Payment | 40320
| New Agreement | 116470
Mitchell & Eades (L17 & L29) | AED |  | 525200 |  | 525200
| LPO ref. PROJ/PLOT18/3266/2022 | 386000
| LPO ref. PROJ/PLOT18/3645/2022 | 13200
| EOT (Approximately) | 126000
Mediatech | AED |  | 190572 |  | 190572
| Contract Amount | 140572
| EOT (Approximately) | 50000
Vortex | AED |  | 206500 |  | 206500
| Outstanding Amount | 24000
| Fee for the Remaining Services | 35000
| Variations | 147500
CEC | AED |  | 781981.22 |  | 781981.22
| Residual Payment | 456981.22
| New Agreement | 325000
AME | AED |  | 46500 |  | 46500
| Original Contract Value | 46500
| Variations approved to Date | 0
AMELIA | EUR |  | 924625 | 3.85 | 3559806.25
| Contract Amount | 88000
| Variations | 836625
Dorchester |  |  |  |  | 0
EMTEC | AED |  | 55000 |  | 55000
| LPO ref Proj/PLOT18/3503/2022 | 55000
Danial Turner | AED |  | 228600 |  | 228600
| LPO ref Plot-18/3048/2022 | 54000
| LPO ref Plot-18/3049/2022 | 117000
| LPO ref Plot-18/3486/2022 | 57600
Construct | GBP |  | 368370.83 | 4.45 | 1639250.1935
| Original Contract Amount | 368370.83
Furnish Hospitality Trading | AED |  | 180000 |  | 180000
| LPO Ref: PROJ/PLOT18/3410/2022 | 40000
| EOT (Approximately) | 140000
FOURTH | USD |  | 40000 | 3.676 | 147040
| Original Contract Value | 40000
Elitser Technologies | AED |  | 35415 |  | 35415
| Original Contract Value | 35415
IGME | AED |  | 83758 |  | 83758
| LPO ref: PROJ/PLOT18/3435/2022 | 31758
| LPO ref: PROJ/PLOT18/3434/2022 | 52000
Infrateq | AED |  | 128500 |  | 128500
| LPO ref: PROJ/PLOT18/3608/2022 | 105000
| LPO ref: PROJ/PLOT18/3687/2022 | 23500
Oasys | AED |  | 335091 |  | 335091
| LPO ref: PROJ/PLOT18/3565/2022 | 335091
Elite Document Solutions Ltd | AED |  | 159899.6 |  | 159899.6
| LPO ref PROJ/PLOT18/3629/2022 | 159899.6
Intelity Inc. | AED |  | 367000 |  | 367000
| LPO ref: PROJ/PLOT18/3606/2022 | 367000
Samsotech LLC | AED |  | 81480 |  | 81480
| LPO ref: PROJ/PLOT18/3601/2022 | 81480
Budgeting Solutions Ltd | AED |  | 38544 |  | 38544
| LPO ref PROJ/PLOT18/3602/2022 | 38544
Key Information Technology | AED |  | 94696 |  | 94696
| LPO ref PROJ/PLOT18/3604/2022 | 94696
Al Suwaidi | AED |  | 11000 |  | 11000
| LPO ref PROJ/PLOT18/3678/2022 | 11000
Ayyam Gallery | USD |  | 49800 | 3.676 | 183064.8
| LPO ref PROJ/PLOT18/3681/2022 | 49800
m-hance | AED |  | 89345.34 |  | 89345.34
| LPO ref PROJ/PLOT18/3433/2022 | 89345.34
Salt TS | AED |  | 146000 |  | 146000
| Original Contract Value | 146000
SevenRooms | AED |  | 84410 |  | 84410
| LPO ref PROJ/PLOT18/3605/2022 | 84410
TSSC | AED |  | 3383682 |  | 3383682
| Contract Amount | 1023695
| Variation | 2359987
Magnum Plus | AED |  | 77152.52 |  | 77152.52
| Contract Amount | 70800
| EOT (Approximately) | 6352.52
Brimax | AED |  | 235000 |  | 235000
| Original Contract Value | 235000
Salama | AED |  | 340000 |  | 340000
| Original Contract Value | 300000
| LPO ref: PLOT18/3535/2022 | 40000
[5 empty] | AED | 1
[5 empty] | GBP | 4.45
[5 empty] | EUR | 3.85
[5 empty] | USD | 3.676

## December Payments
Company Name | PC No | Certified | PC No | Paid |  | 243750
Al Turath |  |  | 2 | 80000 | F+P | 222500
Amelie Maison D'Art |  |  | 2 | 84700 | G&B | 0
BG&E | 9 | 87500 | 8 | 70000 | Al Turath | 80000
BSBG | 13 | 205750 | BSBG-12 | 205750 | Conin | 37968.75
CEC | 7 | 162500 | 5 | 81250 | Excom | 21000
Conin | 58 | 37968.75 | 57 | 37968.75 | PRD | 0
Construct Branding |  |  | 2 | 202030 | Travel | 170025
Dorchester |  |  | 29 | 3835.601 | Fondue | 92600
Econ | 3 | 10500 | 2 | 10500 | Roya | 40000
Em Tec | 1 | 33000 |  |  | Dorchester | 3835.601
Excom | 50 | 10500 | 49 | 10500 | U+A | 30000
F+P |  | 333750 |  | 222500 | Light Touch | 32660
Fondue |  | 92600 |  | 92600 | BRIMAX | 0
GAJ | 15 | 100844.71 | 13 | 91473.84 | Mirage | 286032.39
Light Touch | 16 | 32660 | 14 | 32660 | WME | 108000
Magnum Plus | 6 | 5900 | 5 | 5900 | Meinhardt | 13940
Mediatech | 6 | 12500 | 5 | 12500 | BG&E | 70000
Meinhardt | 7 | 15110 | MEINH-06 | 13940 | Mitchell & Eades | 90437.5
Mirage | 22 | 303615.67 | 21 | 286032.39 | Mediatech | 12500
Mitchell & Eades |  | 121750 |  | 90437.5 | Vortex | 11500
Travel |  | 0 |  | 72765 | BSBG | 205750
Roya | 34 | 40000 | 33 | 40000 |  | 0
Salama Structural | 3 | 40000 | 3 | 40000 | GAJ | 91473.84
Travel |  | 0 |  | 97260 | CEC | 81250
U+A |  |  | 5 | 30000 | Acoustic Middle East | 0
Vortex | 6 | 26000 | 5 | 11500 | Magnum Plus | 5900
WME | WME-09 | 108000 | WME-08 | 108000 | Daniel Turne | 0
[5 empty] | Amelie Maison D'Art | 84700
[5 empty] | Land Sterling | 0
|  |  |  | 2034103.081 |  | 1792073.081
242030
Residence
Bond Interiors-RESIDENCES | 11 | 6037621.65 | 11 | 6037621.65
CEC - Residences | 6 | 42750 | 6 | 42750
GAJ |  | 126329.63 |  | 252635.06
IB&A - RESIDENCES |  | 121266.67 |  | 223266.67
Light Touch - RESIDENCES |  | 21660 |  | 43320
Critical Path |  | 24000 |  | 44000
|  | 336006.3 |  | 605971.73
Elitser Technologies |  |  | ELS-1 | 35415
Elite Document Solutions | 1 | 159899.6
Samsotech | 1 | 81480 | 1 | 81480
Spire Solutions | 1 | 164132.68 | 1 | 164132.68
Fourth Limited |  |  | 1 | 20218
OASYS | 1 | 202505.5 | 1 | 202505.5
IGME Information Technology |  | 52000 |  | 83758
IGME Information Technology | 2 | 52000 | 1 | 31758
IGME Information Technology |  |  | 2 | 52000
Infrateq | 1 | 84000 | 1 | 84000
Intelity | 1 | 169096 | 1 | 169096
|  | 965113.78 |  | 924363.18
Al Shafar Interiors |  |  | ASI-WFA-02 | 441498.44
EW Cox | WFA-01 | 80486.9
Empower DCS |  | 595455 |  | 142995
Business Bay LLC |  |  | 6 | 152820.82
DEWA |  |  | 4 | 35576

## FF&E Payments
| Certified | Paid
HOTEL
Pre-Opening | 86400 | 86400
OS&E Payment Tracker | 1190801.525 | 438393.581
CCM Fees | 117600 | 112800
FF&E Payment Tracker | 9173382.3781 | 5625903.5
IT | 1397466.38 | 1011754.18
| 11965650.2831 | 7275251.261
RESI
FF&E Payment Tracker | 4510065.49 | 4510065.49
FF&E Miscellaneous | 15115 | 10942.8571
| 4525180.49 | 4521008.3471

## Consultat & Hard Cost
Plot -18 Payments -November 2022
| SN | Company Name | Certified | Paid |  | As per PC | Month | Paid | Total Contract | Paid
1 | 50 | Acoustic Middle East |  | 18600
2 | 1 | Al Ain Ahlia Insurance |  | 808013.48
4 | 48 | Al Turath | 80000 | 100000
5 | 63 | Amelie Maison D'Art |  | 84700
6 | 30 | BG&E | 35000 | 70000
7 | 27 | BSBG | 239665 | 272033
8 | 47 | Business Bay LLC | 152820.82 | 152820.82
9 | 84 | CEC | 81250 | 81250
10 | 20 | Conin | 37968.75 | 75937.5 |  | 2188265.63 | nov | 2217944.67 | 2340140.63 | updated
11 | 8 | Construct Branding | 202030 |  | not entered
13 | 43 | Daniel Turner |  | 57600 |  | 228600 |  | 117000
15 | 34 | Dorchester |  | 223471.0255 |  | 1379981.56 |  |  | 3110892.92 | NOT UPDATED
16 | 17 | DSGN |  | 24700 | not entered | Closed
17 | 67 | Econ QS | 10500 | 10500 |  |  |  |  | NOT UPDATED
20 | 16 | Excom | 10500 | 21000 |  |  |  |  | NOT UPDATED
| 5 | Nasser Air Travel | 27535 | 97190 |  | 1648076.5 |  | 1922496.5 | 1898076.5
| 3 | U Travel | 72510 | 177230
21 | 26 | Fondue | 24000 | 48000 |  | 180000 | Oct | 156000 | 327450
| 14 | Roya | 40000 | 80000 |  | 1180000 |  | 1140000 | 1340000
|  | Maison D’Art |  |  |  | 169400 |  | 84700 | 338800
23 | 44 | G&B |  | 331100 |  | 12032894.14 |  | 12032894.14 | 13058666.31
25 | 18 | GAJ - Hotel | 91473.84 | 91473.84
29 | 49 | Land Sterling |  | 16585
30 | 22 | Light Touch | 32660 | 54920
32 | 25 | Mediatech | 12500 | 25000
33 | 24 | Meinhardt | 13940 | 33770
34 | 21 | Mirage | 286032.39 | 579849.57
35 | 9 | Mitchell & Eades | 21000 | 204600
40 | 19 | U+A | 30000 | 60000
41 | 23 | Vortex | 11500 | 19550
42 | 31 | WME | 108000 | 216000
31 | 54 | Magnum Plus Cleaning | 5900 | 17700
43 | 51 | NSCC |  | 269239.5
44 | 33 | Khansaheb | 19804921.87 | 15491078.95
45 | 85 | Al Shafar Interiors | 441498.44 | 441498.44
46 | 52 | DEWA | 35576 | 140175.94 | [5 empty] | Tracker | not in Tracker
47 | 56 | Empower DCS | 2449 | 142995 | [5 empty] | 2560643.14 | 230153 | 2790796.14
48 | 58 | Elitser Technologies | 35415 | 35415 | [7 empty] | 2790796.14
49 | 60 | Fourth Limited | 20218 | 20218
50 | 59 | IGME Information Technology | 31758 | 31758
|  |  | 87391 | 87391
53 | 26 | Bond Interiors-RESIDENCES | 11005574.21 | 11005574.21
51 | 10 | Ian Banham - RESIDENCES | 102000
52 | 17 | Critical Path – Residences | 20000
54 | 65 | IBA - RESIDENCES |  | 102000
55 | 76 | Light Touch - RESIDENCES | 21660 | 21660
56 | 68 | GAJ | 126305.43 | 126305.43
57 | 15 | IBA |  | 82000
| 72 | Critical Path |  | 20000
|  |  | 269965.43 | 351965.43