## 1C. FCR
|  | Project Name | Plot 18
|  | Plot Number | Plot 18
|  | FCR for Month ending | January 2022 | [22 empty] | 4399300.81
|  | Previous Month | December 2022 | [31 empty] | 50% |  | 50%
|  | Approved Business Plan | December 2017 | [31 empty] | TOC RESI |  | TOC KCE
[22 empty] | 2022 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023
Cost Code |  | Scope of Work | Consultant / Regulatory Authority / Contractor | Approved Business Plan Dec 2017 (Superseded) | TARGET BUDGET | Previous month Forecast Cost December 2022 | Current month Forecast Cost November 2022 | % of Total Cost | Variance with Budget | Variance with last month | Current month Forecast Cost January 2023 | Total Budget | Payments Certified by QS December 2022 | Payments Certified by QS December 2022 | % of works Certified | Balance to Certify | Actual amount paid by Finance (as at the end of December 2022) | Actual amount paid as % of Certified | Balance to pay |  |  | 2022-12-11 | 2023-01-11 | 2023-02-11 | 2023-03-11 | 2023-04-11 | 2023-05-11 | 2023-06-11 | 2023-07-11 | 2023-08-11 | 2023-09-11 | 2023-10-11 | 2023-11-11 | 2023-12-11 | 2024-01-11 | 2024-02-11 | 2024-03-11 | 2024-04-11 | 2024-05-11 | 2024-06-11 | Total future cash flow | Variance | Check | Check
1 | bar: 2024-01-11; 2024-03-11
| A | CONSULTANCY FEES |  | 1 | 2 | bar: 2023-01-11; 2023-03-11; 2024-01-11 to 2024-03-11
|  | ONGOING CONSULTANCY AGREEMENTS |  | 31984813.8 | 43379967.62 | 68705296.7862 | 72844399.5907 | 5.09% | 40859585.7907 | 4139102.8045 | 72844399.5907 | 98206589.4307 | 57445562.51 | 59157532.911 | 78.86% | 15614689.6007 | 56441836.3445 | 98.25% | 16402563.2462 | bar: 2024-01-11; 2024-03-11
| 2 | ARCHITECT - SUPERVISION LEAD (FC @4.8) | FOSTERS & PARTNERS | 24678918 | 24678918 | 27625390.9062 | 25038430.342 | 2.189% | 359512.342 | -2586960.5642 | 25038430.342 | 25038430.342 | 24259680.34 | 24259680.34 | 96.89% | 778750.002 | 24259680.34 | 100% | 778750.002 |  | -606164.8874 |  | 49553.333 | 49553.333 | 49553.333 | 23925.1156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 172585.1146 | -606164.8874 | FALSE | FALSE
| 3 | INTERIOR DESIGNER | G&B | 3789345.8 | 11600000 | 13413557.68 | 13434176.679 | 1.175% | 9644830.879 | 20618.999 | 13434176.679 | 13434176.679 | 11984698.11 | 11984698.11 | 89.21% | 1449478.569 | 11984698.11 | 100% | 1449478.569 |  | -68815.029 |  | 300000 | 298057.68 | 300000 | 282605.86 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1380663.54 | -68815.029 | FALSE | FALSE
| 6 | TRAFFIC ACCESS STUDY | AL TURATH | 125000 | 213000 | 262620 | 262620 | 0.02296% | 137620 | 0 | 262620 | 262000 | 257620 | 257620 | 98.1% | 5000 | 257620 | 100% | 5000 |  | 0 |  | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | TRUE | TRUE
| 7 | PROJECT MONITOR | CONIN | 0 | 1350000 | 2378109.38 | 2454046.88 | 0.2146% | 2454046.88 | 75937.5 | 2454046.88 | 2454046.88 | 2188265.63 | 2188265.63 | 89.17% | 265781.25 | 2188265.63 | 100% | 265781.25 |  | -75937.5 |  | 75937.5 | 37968.75 | 37968.75 | 37968.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189843.75 | -75937.5 | FALSE | FALSE
| 8 | Q.S FEES | HQS - EXCOMM-ECON-DUMEEQS-EBN | 100000 | 100000 | 1224043.68 | 1152223.68 | 0.1007% | 1052223.68 | -71820 | 1152223.68 | 1152223.68 | 1158817.77 | 1186272.85 | 100.6% | -6594.09 | 1158817.77 | 100% | -6594.09 |  | 71820 |  | 21000 | 11500 | 11500 | 11500 | 9725.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65225.91 | 71820 | FALSE | FALSE
| 10 | SURVEY SERVICES, OQOOD SUBMISSION | PRD | 191300 | 351300 | 198190 | 198190 | 0.01733% | 6890 | 0 | 198190 | 198190 | 151110 | 151110 | 76.25% | 47080 | 151110 | 100% | 47080 |  | 0 |  | 0 | 0 | 0 | 47080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47080 | 0 | TRUE | TRUE
| 11 | TRAVEL COST | Various Vendors | 113500 | 2099999.62 | 1898076.5 | 1848076.5 | 0.1616% | 1734576.5 | -50000 | 1848076.5 | 1848076.5 | 1818076.5 | 1818076.5 | 98.38% | 30000 | 1818076.5 | 100% | 30000 |  | 50000 |  | 15000 | 15000 | 15000 | 15000 | 15000 | 5000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 50000 | FALSE | FALSE
| 12 | F&B CONSULTANT | FONDUE |  |  | 327450 | 347675 |  |  | 20225 | 347675 | 347675 | 296600 | 305450 | 85.31% | 51075 | 248600 | 83.82% | 99075 |  | -20225 | 2023-01-11: 50000; 2023-02-11: 28850 | 78850 | -20225 | FALSE | FALSE
| 13 | HOTEL OPENING | ROYA |  |  | 1340000 | 1460000 |  |  | 120000 | 1460000 | 1460000 | 1180000 | 1220000 | 80.82% | 280000 | 1180000 | 100% | 280000 |  | -120000 | 2023-01-11: 40000; 2023-02-11: 40000; 2023-03-11: 40000; 2023-04-11: 40000 | 160000 | -120000 | FALSE | FALSE
| 15 | HOTEL OPERATOR | DORCHESTER | 2026750 | 2026750 | 2767000 | 3798019.4997 | 0.3321% | 1771269.4997 | 1031019.4997 | 3798019.4997 | 3798019.4997 | 2004716.11 | 2329037.951 | 52.78% | 1793303.3897 | 1479865.2045 | 73.82% | 2318154.2952 |  | -1031019.4997 |  | 55000 | 55000 | 55000 | 303270 | 358270 | 312420 | 148174.7955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1287134.7955 | -1031019.4997 | FALSE | FALSE
| 18 | LANDSCAPE | U+A | 0 |  | 436940 | 486122.5 | 0.0425% | 486122.5 | 49182.5 | 486122.5 | 486122.5 | 210000 | 240000 | 43.2% | 276122.5 | 210000 | 100% | 276122.5 |  | -49182.5 |  | 40000 | 40000 | 40000 | 40000 | 36940 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226940 | -49182.5 | FALSE | FALSE
| 19 | EXTERIOR AND INTERIOR LIGHTING DESIGN | LIGHT TOUCH | 725000 | 725000 | 485660.22 | 494980 | 0.04328% | -230020 | 9319.78 | 494980 | 494980 | 159970 | 193370 | 32.32% | 335010 | 159970 | 100% | 335010 |  | -9319.78 |  | 125000 | 100000 | 50350 | 50340.22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325690.22 | -9319.78 | FALSE | FALSE
| 20 | SIGNAGE AND WAYWARD FINDING | BRIMAX | 235000 | 235000 | 161000 | 105000 | 0.00918% | -130000 | -56000 | 105000 | 105000 | 111000 | 55000 | 105.7% | -6000 | 111000 | 100% | -6000 |  | 56000 |  | 14571.4286 | 17714.2857 | 17714.2857 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 56000 | FALSE | FALSE
| 21 | MIRAGE RESOURCES - PROJECT MANAGERS | MIRAGE |  |  | 8281242 | 8953029 | 0.7827% | 8953029 | 671787 | 8953029 | 8953029 | 6850932.51 | 7116501.19 | 76.52% | 2102096.49 | 6850932.51 | 100% | 2102096.49 |  | -671787 |  | 479159.5637 | 479159.5637 | 239434.2288 | 232556.1338 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1430309.49 | -671787 | FALSE | FALSE
| 22 | MEP CONSULTANT | WME |  |  | 1632000 | 2207397.85 |  |  | 575397.85 | 2207397.85 | 2207397.85 | 879397.85 | 879397.85 | 39.84% | 1328000 | 826064.52 | 93.94% | 1381333.33 |  | -575397.85 |  | 233142.8571 | 233142.8571 | 214506.9086 | 125142.8571 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 805935.48 | -575397.85 | FALSE | FALSE
| 23 | FAÇADE ENGINEERING / BMU DESIGN | MEINHARDT |  |  | 152470 | 116470 |  |  | -36000 | 116470 | 116470 | 73300 | 79100 | 62.93% | 43170 | 58190 | 79.39% | 58280 |  | 36000 |  | 18960 | 18960 | 18960 | 18960 | 18440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94280 | 36000 | FALSE | FALSE
| 24 | STRUCTURAL CONSULTANT | BG&E |  |  | 732300 | 837300 |  |  | 105000 | 837300 | 837300 | 439800 | 439800 | 52.53% | 397500 | 334800 | 76.13% | 502500 |  | -105000 |  | 122500 | 80000 | 90000 | 35000 | 35000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 397500 | -105000 | FALSE | FALSE
| 25 | L17 & L29 RESTAURANTS | MITCHELL & EADES |  |  | 614000 | 642600 |  |  | 28600 | 642600 | 642600 | 430037.5 | 422100 | 66.92% | 212562.5 | 430037.5 | 100% | 212562.5 |  | -28600 |  | 50000 | 50000 | 50000 | 33962.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183962.5 | -28600 | FALSE | FALSE
| 26 | IT CONSULTANT | MEDIA TECH |  |  | 147600 | 100800 |  |  | -46800 | 100800 | 100800 | 62500 | 62500 | 62% | 38300 | 62500 | 100% | 38300 |  | 46800 | 2023-01-11: 25100; 2023-02-11: 20000; 2023-03-11: 20000; 2023-04-11: 20000 | 85100 | 46800 | FALSE | FALSE
| 27 | FIRE SAFETY CONSULTANCY | VORTEX |  |  | 170000 | 182500 |  |  | 12500 | 182500 | 182500 | 64775 | 143350 | 35.49% | 117725 | 64775 | 100% | 117725 |  | -12500 | 2023-01-11: 20000; 2023-02-11: 20000; 2023-03-11: 20000; 2023-04-11: 24175; 2023-05-11: 21050 | 105225 | -12500 | FALSE | FALSE
| 28 | SUPERVISION SERVICES - BSBG | BSBG |  |  | 2444736 | 3419895 |  |  | 975159 | 3419895 | 3419895 | 1752944 | 1958694 | 51.26% | 1666951 | 1752944 | 100% | 1666951 |  | -975159 |  | 220805.875 | 273227.75 | 197758.375 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 691792 | -975159 | FALSE | FALSE
| 30 | ID Supervision-Hotel | GAJ |  |  | 875040.42 | 1125100.41 |  |  | 250059.99 | 1125100.41 | 1125100.41 | 397704.42 | 397704.42 | 35.35% | 727395.99 | 288554.26 | 72.55% | 836546.15 |  | -250059.99 |  | 150000 | 150000 | 150000 | 136486.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 586486.16 | -250059.99 | FALSE | FALSE
| 31 | FOH MEP | CEC |  |  | 320000 | 325000 |  |  | 5000 | 325000 | 325000 | 243750 | 145839.22 | 75% | 81250 | 243750 | 100% | 81250 |  | -5000 |  | 50000 | 26250 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76250 | -5000 | FALSE | FALSE
| 32 | Acoustic | Acoustic Middle East -AME |  |  | 46500 | 33170 |  |  | -13330 | 33170 | 33170 | 18600 | 18600 | 56.07% | 14570 | 18600 | 100% | 14570 |  | 13330 |  | 18600 | 9300 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27900 | 13330 | FALSE | FALSE
[6 empty] | 70800 |  |  |  | -70800 |  |  | 35852.52 | bar: 2024-01-11; 2024-03-11
| 34 | Recrutment | Daniel Turne |  |  | 328600 | 228600 |  |  | -100000 | 228600 | 228600 | 228600 | 228600 | 100% | 0 | 117000 | 51.18% | 111600 |  | 100000 |  | 60000 | 60000 | 91600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211600 | 100000 | FALSE | FALSE
| 35 | Art Consultant | Amelie Maison D’Art |  |  | 338800 | 3559806.25 |  |  | 3221006.25 | 3559806.25 | 3559806.25 | 169400 | 1059350.6 | 4.759% | 3390406.25 | 169400 | 100% | 3390406.25 |  | -3221006.25 |  | 50000 | 50000 | 50000 | 19400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169400 | -3221006.25 | FALSE | FALSE
| 36 | RERA Valuation | Land Sterling |  |  | 33170 | 33170 |  |  | 0 | 33170 | 33170 | 17414.25 | 17414.25 | 52.5% | 15755.75 | 16585 | 95.24% | 16585 |  | 0 |  | 16585 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16585 | 0 | TRUE | TRUE
|  | FF&E Consultancy | Furnish Hospitality Trading | [6 empty] | 180000 | 180000 | 180000 | 0 | 40000 |  | 180000 | bar: 2024-01-11; 2024-03-11
|  | ELV Consultancy | EM-TEC | [6 empty] | 55000 | 55000 | 55000 |  | 33000 | bar: 2024-01-11; 2024-03-11
| 37 | INACTIVE CONSULTANCY AGREEMENTS |  | 14528816.2 | 14282191.19 | 25127809.84 | 25127809.84 | 1.287% | -238062.55 | 0 | 25127809.84 | 25127809.84 | 25127809.84 | 25127809.84 | 100% | 0 | 25127809.84 | 100% | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
|  | TOTAL CONSULTANCY FEES |  | 46513630 | 57662158.81 | 93833106.6262 | 97972209.4307 | 6.377% | 51458579.4307 | 4139102.8045 | 97972209.4307 | 123334399.2707 | 82573372.35 | 84285342.751 | 84.28% | 15614689.6007 | 81569646.1845 | 98.78% | 16402563.2462 |  | -7451224.2861 | 0 | 2305915.5574 | 2163684.2196 | 1759345.881 | 1497372.5965 | 694425.91 | 382420 | 148174.7955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8951338.9601 | -7451224.2861 | FALSE | FALSE
0 | bar: 2024-01-11; 2024-03-11
| B | LOCAL AUTHORITY FEES | [18 empty] | 0 | bar: 2023-01-11; 2023-03-11; 2024-01-11; 2024-03-11
| 1 | POWER CONNECTION (TCL 7MW) | DEWA | 5739077 | 6465200 | 8087188 | 8087188 | 0.707% | 2348111 | 0 | 8087188 |  | 8087188 | 8087188 | 100% | 0 | 8087188 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 2 | POWER CONNECTION (TCL INCREASE BY 3.5MW) | DEWA | 0 | 3500000 | 75019.9 | 75019.9 | 0.006559% | 75019.9 | 0 | 75019.9 |  | 75019.9 | 75019.9 | 100% | 0 | 75019.9 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 3 | WATER CONNECTION/CHARGERS | DEWA | 150000 | 150000 | 958457 | 958457 | 0.0838% | 808457 | 0 | 958457 |  | 343175.94 | 343175.94 | 35.81% | 615281.06 | 277251.94 | 80.79% | 681205.06 |  | 0 |  | 247000 | 100000 | 100000 | 100000 | 68281.06 | 65924 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 681205.06 | 0 | TRUE | TRUE
| 4 | SUBSTATION FEES | DEWA | 1577000 | 1577000 | 1577000 | 1577000 | 0.1379% | 0 | 0 | 1577000 |  | 1577000 | 1577000 | 100% | 0 | 1577000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 5 | DUBAI CIVIL DEFENSE | DCD | 213649 | 213649 | 28920 | 28920 | 0.002528% | -184729 | 0 | 28920 |  | 28920 | 28920 | 100% | 0 | 28920 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 6 | CIVIL AVIATION |  | 5000 | 5000 | 5000 | 5000 | 0.0004371% | 0 | 0 | 5000 |  | 0 | 0 | 0% | 5000 | 0 | 0% | 5000 |  | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | TRUE | TRUE
| 7 | PERMIT/ NOC CHARGES | DUBAI MUNICIPALITY / DP | 894554 | 894554 | 727472 | 727472 | 0.0636% | -167082 | 0 | 727472 |  | 727472 | 727472 | 100% | 0 | 727472 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 8 | ADDITIONAL GFA COSTS (80/FT2) | DUBAI MUNICIPALITY | 2071852 | 2017852 | 0 | 0 | 0% | -2071852 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 9 | BUILDING PERMIT EXCEPTION FEES | DUBAI MUNICIPALITY | 1500000 | 70331 | 1406619 | 1406619 | 0.123% | -93381 | 0 | 1406619 |  | 1406619 | 1406619 | 100% | 0 | 1406619 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 10 | INCREASED POWER (SUBSTATION CONTRIBUTION) | DP | 4080000 | 277449 | 5548976 | 5548976 | 0.4851% | 1468976 | 0 | 5548976 |  | 5548976 | 5548976 | 100% | 0 | 5548976 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 11 | ADDITIONAL HEIGHT | DP | 6710000 | 6710000 | 6710000 | 6710000 | 0.5866% | 0 | 0 | 6710000 |  | 6710000 | 6710000 | 100% | 0 | 6710000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 12 | ANNUAL MASTER-COMM CHARGES (2016-2020) | DP | 4662471 | 4962471 | 1619005.54 | 2734726.83 | 0.2391% | -1927744.17 | 1115721.29 | 2734726.83 |  | 2734726.83 | 2734726.83 | 100% | 0 | 2734726.83 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 13 | DPG ADDITIONAL GFA COSTS (190/FT2) | DP | 4830000 | 4830000 | 10300000 | 10300000 | 0.9005% | 5470000 | 0 | 10300000 |  | 10300000 | 10300000 | 100% | 0 | 10300000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 14 | CONNECTION CHARGE+Deposit | EMPOWER | 6413181 | 6419181 | 6161400 | 6161400 | 0.5387% | -251781 | 0 | 6161400 |  | 6161400 | 6161400 | 100% | 0 | 6161400 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 15 | DEMAND CHARGERS/SECURITY | EMPOWER | 855000 | 855000 | 5568314 | 5568314 | 0.4868% | 4713314 | 0 | 5568314 |  | 2790796.14 | 2790796.14 | 50.12% | 2777517.86 | 2790796.14 | 100% | 2777517.86 |  | 0 | 0 | 379099.4 | 125000 | 350000 | 650000 | 150000 | 150000 | 650000 | 323418.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2777517.86 | 0 | TRUE | TRUE
| 16 | LEED CERTIFICATION FEES | USGBC | 133216 | 35000 | 4411 | 4411 | 0.0003856% | -128805 | 0 | 4411 |  | 4411 | 4411 | 100% | 0 | 4411 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 17 | LEGAL FEES AND FINANCE CHARGES | VARIOUS | 1820000 | 1650000 | 1546782 | 1546782 | 0.1352% | -273218 | 0 | 1546782 |  | 1546782 | 1546782 | 100% | 0 | 1546782 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 18 | RTA & DLD | RTA & DLD | 25000 | 2500 | 5681 | 5681 | 0.0004967% | -19319 | 0 | 5681 |  | 5681 | 5681 | 100% | 0 | 5681 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 19 | TECOM | TECOM | 50000 | 50000 | 18700 | 18700 | 0.001635% | -31300 | 0 | 18700 |  | 18700 | 18700 | 100% | 0 | 18700 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
|  | TOTAL LOCAL AUTHORITY FEES |  | 41730000 | 40685187 | 50348945.44 | 51464666.73 | 4.499% | 9734666.73 | 1115721.29 | 51464666.73 |  | 48066867.81 | 48066867.81 | 93.4% | 3397798.92 | 48000943.81 | 99.86% | 3463722.92 |  |  | 0 | 626099.4 | 230000 | 450000 | 750000 | 218281.06 | 215924 | 650000 | 323418.46 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 3463722.92 | 5.5879e-09 | FALSE | TRUE
| C | CAPITAL WORKS | bar: 2023-01-11; 2023-03-11; 2024-01-11; 2024-03-11
| 1 | FACILITATING WORKS |  | 40000000 | 40587829.04 | 40587829.04 | 40587829.04 | 3.549% | 587829.04 | 0 | 40587829.04 |  | 40587828.83 | 40587828.83 | 100% | 0.21 | 40587828.83 | 100% | 0.21 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | -0.21 | FALSE | FALSE
| 1.1 | PILING, SHORING & ENABLING WORKS | NSCC | 40000000 | 40559649.04 | 40559649.04 | 40559649.04 | 3.546% | 559649.04 | 0 | 40559649.04 |  | 40559648.83 | 40559648.83 | 100% | 0.21 | 40559648.83 | 100% | 0.21 | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | -0.21 | FALSE | FALSE
| 1.2 | OME SITE ESTABLISHMENT | VARIOUS | 0 | 28180 | 28180 | 28180 | 0.002464% | 28180 | 0 | 28180 |  | 28180 | 28180 | 100% | 0 | 28180 | 100% | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 2+3+4+5 | RP TOTAL - MAIN WORKS & PROVISIONAL SUMS & CONTRACT FEES NOVATED |  | 730862422 | 753126225.04 | 507541746.9409 | 507541746.9409 |  |  | 0 | 507541746.9409 |  | 583165175.8896 | 583165175.8896 |  | -75623428.9487 | 507541746.9409 |  | 0 |  |  | 2023-12-11: 0; 2024-03-11: 0 | 0 | 0 | TRUE | TRUE
[7 empty] | 0 | [14 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6 | LOOSE FF&E | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6.1 | LOOSE FF&E FOR RESIDENTIAL AND HOTEL | TBA | 40269400 | 32000000 | 26300000 | 26300000 | 2.797% | -12269400 | 0 | 26300000 |  | 9173382.3781 | 9173382.3781 | 34.88% | 17126617.6219 | 5625903.5 | 61.33% | 20674096.5 |  | 0 | 0 | 1945720.36 | 2378317.8143 | 2808487.27 | 3600855.75 | 5177374.1795 | 3217034.7862 | 1546306.34 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20674096.5 | 0 | TRUE | TRUE
| 6.2 | BOH EQUIPMENT-Commercial Kitchen and Laundry | TBA | 13000000 | 11077300 | 7162178 | 7162178 | 1.199% | -1002700 | 0 | 7162178 |  | 2608796.1 | 2608796.1 | 36.42% | 4553381.9 | 2608796.1 | 100% | 4553381.9 |  | 0 |  | 852343.236 | 1741752.844 | 744451.12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1214834.7 | 0 | 0 | 0 | 4553381.9 | 0 | TRUE | TRUE
| 6.2.1 | Commercial Kitchen and Laundry | [6 empty] | 0 | [9 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 6.2.2 | Gym Equipment | [6 empty] | 0 | [9 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE | Moved to Hotel public
[9 empty] | 0 | [9 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE | Moved to Hotel public
| 6 | LOOSE FF&E |  | 53269400 | 43077300 | 33462178 | 33462178 | 2.926% | -19807222 | 0 | 33462178 |  | 11782178.4781 | 11782178.4781 | 35.21% | 21679999.5219 | 8234699.6 | 69.89% | 25227478.4 |  |  | 0 | 2798063.596 | 4120070.6583 | 3552938.39 | 3600855.75 | 5177374.1795 | 3217034.7862 | 1546306.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1214834.7 | 0 | 0 | 0 | 25227478.4 | 0 | TRUE | TRUE
[22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7 | RESIDENCES FIT-OUT | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7.1 | Residences - Fit out Package |  | 0 | 18445000 | 95159810.83 | 95159810.83 | 8.32% | 95159810.83 | 0 | 95159810.83 |  | 71836657.91 | 71836657.91 | 75.49% | 23323152.92 | 69094809.3224 | 96.18% | 26065001.5076 |  | 0 |  | 9600000 | 9700467.6849 | 2528864.9812 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4235668.8415 |  | 0 | 0 | 0 | 0 | 26065001.5076 | 0 | TRUE | TRUE
| 7.2 | Residential Kitchen appliances |  |  |  | 3100000 | 3100000 |  |  |  | 3100000 |  |  |  |  | 3100000 |  |  | 3100000 |  | 0 |  | 1729800 | 446400 | 334800 | 279000 | 155000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155000 | 0 | 0 | 0 | 0 | 0 | 3100000 | 0 | TRUE | TRUE
| 7.3 | Residences - Fit out Package Consultancy Fee |  | 0 | 18445000 | 3682219.5 | 3682219.5 | 0.3219% | 3682219.5 | 0 | 3682219.5 |  | 3026717.62 | 3026717.62 | 82.2% | 655501.88 | 3237931.08 | 107% | 444288.42 |  | 0 |  | 150000 | 150000 | 144288.42 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 444288.42 | 0 | TRUE | TRUE
| 7.4 | Purchaser Customizations |  | 0 | 644645 | 644645 | 644645 | 0.05636% | 644645 | 0 | 644645 |  | 0 | 0 | 0% | 644645 | 0 | 0% | 644645 |  | 0 |  | 359711.91 | 92828.88 | 69621.66 | 58018.05 | 32232.25 | 32232.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 644645 | 0 | TRUE | TRUE
| 7 | RESIDENCES FIT-OUT |  | 0 | 37534645 | 102586675.33 | 102586675.33 | 8.969% | 102586675.33 | 0 | 102586675.33 |  | 74863375.53 | 74863375.53 | 72.98% | 27723299.8 | 72332740.4024 | 96.62% | 30253934.9176 |  |  | 0 | 11839511.91 | 10389696.5649 | 3077575.0612 | 337018.05 | 187232.25 | 32232.25 | 0 | 0 | 0 | 0 | 0 | 0 | 4390668.8415 | 0 | 0 | 0 | 0 | 0 | 30253934.9276 | 0.01 | FALSE | TRUE
[22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8 | Residences - Furniture Package |  | 0 | 56015000 | 53828987.2 | 53828987.2 | 4.706% | 53828987.2 | 0 | 53828987.2 |  | 4525180.49 | 4525180.49 | 8.407% | 49303806.71 | 4521008.3471 | 99.91% | 49307978.8529 |  | 0 | 0 | 1072292.21 | 378210 | 8202932 | 7218408 | 9059761 | 12678710 | 6907530.97 | 3790134.6729 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49307978.8529 | 0 | TRUE | TRUE
[21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 19982204.03 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9 | NEW CONTRACTOR - KHANSAHEB |  | 0 | 56015000 | 194951733.75 | 194951733.75 | 17.04% | 194951733.75 | 0 | 194951734 |  | 104356336.266 | 104356336.266 | 53.53% | 90595397.484 | 84551414.399 | 81.02% | 110400319.601 |  | 0 |  | 20000000 | 20000000 | 15000000 | 15000000 | 15000000 | 18880319.601 |  | 0 |  | 0 | 0 | 0 | 0 |  | 6520000 | 0 | 0 | 0 | 110400319.601 | 0 | TRUE | FALSE
[21 empty] | 0 | [19 empty] | 0 | 0 | TRUE | TRUE | bar: 2024-01-11; 2024-03-11
| 9.1 | Fit Out Package - F&B Hotel | [7 empty] | 23000000 | 23000000 |  | 962551.45 | 962551.45 | 4.185% | 22037448.55 | 559353.9 | 58.11% | 22440646.1 |  | 0 | 2023-01-11: 1000000; 2023-02-11: 1440646.1; 2023-03-11: 5000000; 2023-04-11: 5000000; 2023-05-11: 5000000; 2023-06-11: 5000000 | 22440646.1 | 0 | TRUE | FALSE
[41 empty] | 0 | 0 | TRUE | TRUE
| 9.2 | Facility Management / Operational Costs-Operational Supplies and Equipment | [7 empty] | 5000000 | 5000000 |  | 1397466.38 | 1397466.38 | 27.95% | 3602533.62 | 1011754.18 | 72.4% | 3988245.82 |  |  | 2023-01-11: 664707.6367; 2023-02-11: 664707.6367; 2023-03-11: 664707.6367; 2023-04-11: 664707.6367; 2023-05-11: 664707.6367; 2023-06-11: 664707.6367 | 3988245.82 |  | TRUE | FALSE
[21 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10 | PAYMENTS TO RPJV SUBCONTRACTORS / SUPPLIERS | [18 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10.1 | Direct Payments (RPJV Historical Debt) |  | 40269400 | 32000000 | 25000000 | 25000000 | 2.186% | -12269400 | 0 | 25000000 |  | 25000000 | 25000000 | 100% | 0 | 25000000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 10.2 | Accrued retention payable to continuing SCs |  | 13000000 | 11077300 | 24000000 | 24000000 | 2.098% | -1002700 | 0 | 24000000 |  |  |  |  | 24000000 | 0 | 0% | 24000000 | [5 empty] | 0 | 0 | 12000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12000000 | 0 | 0 | 0 | 24000000 | 0 | TRUE | TRUE
| 10.3 | Advance payment credit (direct) |  |  |  | -4000000 | -4000000 | -0.3497% | -4000000 | 0 | -4000000 |  | -4000000 | -4000000 | 100% | 0 | -4000000 |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 10.4 | Advance payment credit (PS) |  |  |  | -11600000 | -11600000 | -1.014% | -11600000 | 0 | -11600000 |  | -11600000 | -11600000 | 100% | 0 | -11600000 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE | Moved to Hotel public
[9 empty] | 0 | [9 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE | Moved to Hotel public
| 10 | PAYMENTS TO RPJV SUBCONTRACTORS / SUPPLIERS |  | 53269400 | 43077300 | 33400000 | 33400000 | 2.92% | -19869400 | 0 | 33400000 |  | 9400000 | 9400000 | 28.14% | 24000000 | 9400000 | 100% | 24000000 |  |  | 0 | 0 | 0 | 0 | 0 | 12000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000000 | 0 | 0 | 0 | 24000000 | 0 | TRUE | TRUE
[22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | TOTAL CAPITAL WORKS |  | 730862422 | 753126225.04 | 966359150.2609 | 966359150.2609 | 86.94% | 235496728.2609 | 28000000 | 994359150.5109 |  | 831040093.3136 | 831040093.3136 | 83.58% | 163319056.9472 | 728740546.5994 | 87.69% | 265618603.9015 |  |  | 0 | 37374575.3527 | 36993330.9599 | 35498153.0878 | 31820989.4367 | 47089075.0662 | 40473004.2739 | 8453837.31 | 3790134.6729 | 0 | 0 | 0 | 0 | 4390668.8415 | 0 | 19734834.7 | 0 | 0 | 0 | 265618603.7015 | -0.2 | FALSE | FALSE
0 | bar: 2024-01-11; 2024-03-11
| D | CONTINGENCIES | bar: 2023-01-11; 2023-03-11; 2024-01-11; 2024-03-11
| 1 | CONSULTANT AND AUTHORITY FEES |  | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 2 | PRE-CONTRACT AND CAPITAL WORKS |  | 35504278.85 | 19902701 | 0.2 | 0.2 | 1.749e-08% | -35504278.65 | 0 | 0.2 |  |  |  | 0% | 0.2 |  | 0% | 0.2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.2 | FALSE | FALSE
|  | TOTAL CONTINGENCIES |  | 35504278.85 | 19902701 | 0.2 | 0.2 | 1.749e-08% | -35504278.65 | 0 | 0.2 |  | 0 | 0 | 0% | 0.2 | 0 | 0% | 0.2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | -0.2 | FALSE | FALSE
|  | TOTAL COST FOR THE PROJECT (A + B + C + D - E) |  | 854610330.85 | 871376271.85 | 1110541202.3271 | 1115796026.6216 | 100% | 261185695.7716 | 33254824.0945 | 1143796026.8716 |  | 961680333.4736 | 963392303.8746 | 84.08% | 182331545.6679 | 858311136.5939 | 89.25% | 285484890.2677 |  |  | 0 | 40306590.3101 | 39387015.1795 | 37707498.9689 | 34068362.0332 | 48001782.0362 | 41071348.2739 | 9252012.1055 | 4113553.1329 | 0 | 0 | 0 | 0 | 4390668.8415 | 0 | 19734834.7 | 0 |  | 0 | 278033665.5816 | -7451224.6861 | TRUE | TRUE
[16 empty] | 1144011879.1416 |  |  | 1143796026.8616

## Cash Flow
CONSULTANCY FEES - HOTEL
| Consultant Name | Description | Final Contract Sum | Amt Certified | Period | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | Variations After November 2022 | Cumulative Upto Date
1 | DESIGN ARCHITECT - SUPERVISION | F+P | 25038430.342 | 24370930.342 | 2022-12-25 |  |  |  | 111250 | 111250 | 111250 | 111250 | 111250 | 111250 |  | 25038430.342 | 667500 | 0
2 | INTERIOR DESIGN - SUPERVISION | G&B - Hotel | 13434176.679 | 11984698.11 | 2022-10-23 |  |  |  | 241600 | 241600 | 241600 | 241600 | 241600 | 241600 |  | 13434298.11 | 1449478.569 | 121.431
3 | TRAFFIC ACCESS STUDY | ALTHURATH | 262000 | 100000 | 2022-10-23 |  |  |  | 5000 | [6 empty] | 105000 | 162000 | -157000
4 | PROJECT MONITOR | Conin | 2454046.88 | 2188265.63 | 2022-11-24 |  |  | 38000 | 38000 | 38000 | 38000 | 38000 | 38000 | 38000 |  | 2454265.63 | 265781.25 | 218.75
5 | QUANTITY SURVEYING | Excom | 846747.91 | 825747.91 | 2022-12-25 |  |  |  | 10500 | 10500 | [5 empty] | 846747.91 | 21000 | 0
6 | QUANTITY SURVEYING | ECON | 98700 | 35700 | 2022-12-25 |  |  |  | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 |  | 98700 | 63000 | 0
7 | SURVEY SERVICES, OQOOD SUBMISSION | PRD | 198190 | 151110 | [5 empty] | 47080 | [5 empty] | 198190
8 | TRAVEL COST | Various Travel Companies | 1848076.5 | 1648076.5 | [11 empty] | 1648076.5
9 | KITCHEN AND BACK OF HOUSE | Fondue | 347675 | 305450 | 2022-12-25 |  |  |  | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 |  | 347450 | 42225 | -225
10 | HOSPITALITY ADVISORY SERVICES | Roya | 1460000 | 1220000 | 2022-12-25 |  |  |  | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 |  | 1460000 | 240000 | 0
11 | HOTEL OPERATOR | Dorchester | 3798019.4997 | 2329037.951 | 2023-01-26 | [8 empty] | 207880 |  | 2536917.951
12 | LANDSCAPE ARCHITECT - SUPERVISION | U+A | 486122.5 | 240000 | 2022-12-25 |  |  |  | 41020.4167 | 41020.4167 | 41020.4167 | 41020.4167 | 41020.4167 | 41020.4167 |  | 486122.5 | 246122.5 | 0
13 | LIGHTING ENGINEER - SUPERVISION | Light Touch | 494980 | 193370 | 2022-12-25 |  |  |  | 50300 | 50300 | 50300 | 50300 | 50300 | 50300 |  | 495170 | 301610 | 190
14 | SIGNAGE AND WAYWARD FINDING | Brimax | 105000 | 55000 | 2022-09-22 |  |  |  | 8300 | 8300 | 8300 | 8300 | 8300 | 8300 |  | 104800 | 50000 | -200
15 | PROJECT MANAGEMENT | Mirage | 8953029 | 7116501.19 | 2022-12-25 |  |  |  | 306000 | 306000 | 306000 | 306000 | 306000 | 306000 |  | 8952501.19 | 1836527.81 | -527.81
16 | MEP ENGINEER - SUPERVISION | WME | 2207397.85 | 879397.85 | 2022-12-25 |  |  |  | 221300 | 221300 | 221300 | 221300 | 221300 | 221300 |  | 2207197.85 | 1328000 | -200
17 | FAÇADE ENGINEERING / BMU DESIGN | Meinhardt | 116470 | 79100 | 2022-12-25 |  |  |  | 18685 | 18685 | [5 empty] | 116470 | 37370 | 0
18 | STRUCTURAL ENGINEER - SUPERVISION | BGE | 837300 | 439800 | 2023-01-26 |  |  |  |  | 79500 | 79500 | 79500 | 79500 | 79500 |  | 837300 | 397500 | 0
19 | L17 & L29 RESTAURANTS | Mitchell & Eades (L17 & L29) | 642600 | 389100 | 2023-01-26 |  |  |  |  | 84500 | 84500 | 84500 |  |  |  | 642600 | 253500 | 0
20 | MUSA CAFÉ | Mitchell & Eades (Musa Café) |  | 33000 | 2022-10-23 | [10 empty] | 33000
21 | IT CONSULTANT | Mediatech | 100800 | 62500 | 2022-11-24 |  |  | 5471.4286 | 5471.4286 | 5471.4286 | 5471.4286 | 5471.4286 | 5471.4286 | 5471.4286 |  | 100800 | 38300 | 0
22 | FIRE SAFETY CONSULTANCY | Vortex | 182500 | 143350 | 2022-12-25 |  |  |  | 6525 | 6525 | 6525 | 6525 | 6525 | 6525 |  | 182500 | 39150 | 0
23 | ARCHITECT OF RECORD - SUPERVISION | BSBG | 3419895 | 1958694 | 2022-12-25 |  |  |  | 243500 | 243500 | 243500 | 243500 | 243500 | 243500 |  | 3419694 | 1461201 | -201
24 | INTERIOR DESIGN - SUPERVISION | GAJ | 1125100.41 | 397704.42 | 2022-12-25 |  |  |  | 121200 | 121200 | 121200 | 121200 | 121200 | 121200 |  | 1124904.42 | 727395.99 | -195.99
25 | FOH MEP | CEC | 325000 | 145839.22 | 2022-12-25 |  |  |  | 60000 | 60000 | 60000 |  |  |  |  | 325839.22 | 179160.78 | 839.22
26 | Acoustic | AME | 46500 | 18600 | 2022-09-22 |  |  |  | 13950 | 13950 | [5 empty] | 46500 | 27900 | 0
27 | CLEANING SERVICES | Magnum Plus | 77152.52 | 41752.52 | 2022-12-25 |  |  |  | 5900 | 5900 | 5900 | 5900 | 5900 | 5900 |  | 77152.52 | 35400 | 0
28 | RECRUITMENTS | Danial Turner | 228600 | 228600 | 2022-10-23 | [10 empty] | 228600 | 0 | 0
29 | Art Consultant | Amelie Maison D’Art | 3559806.25 | 1059350.6 | 2023-01-26 |  |  |  | 416700 | 416700 | 416700 | 416700 | 416700 | 416700 |  | 3559550.6 | 2500455.65 | -255.65
30 | RERA Valuation | Land Sterling | 33170 | 17414.25 | [11 empty] | 17414.25
31 | Planning consultant | Critical Path |  | 146480 | [11 empty] | 146480
32 | ELV Consultancy | EMTEC | 55000 | 33000 | 2022-12-25 |  |  |  | 22000 | [6 empty] | 55000 | 22000 | 0
33 | BRANDING CONSULTANT | Construct | 1639250.1935 | 450034.0625 | 2022-10-23 |  |  |  | 198200 | 198200 | 198200 | 198200 | 198200 | 198200 |  | 1639234.0625 | 1189216.131 | -16.131
34 | FF&E PROCUREMNT | Furnish Hospitality Trading | 180000 | 40000 | 2022-11-24 |  |  | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 |  | 180000 | 140000 | 0
35 | DESIGN REVIEW | Salama | 340000 | 340000 | 2022-11-24 | [10 empty] | 340000 | 0 | 0
[17 empty] | 0 | 0
36 | PROCUREMENT & STOCK CONTROL PLATFORM | FOURTH | 147040 | 20218 | 2022-10-23 |  |  |  | 21137 | 21137 | 21137 | 21137 | 21137 | 21137 |  | 147040 | 126822 | 0
37 | SERVICES | Elitser Technologies | 35415 | 35415 | 2022-10-23 | [10 empty] | 35415 | 0 | 0
38 | IT SERVICES | IGME | 83758 | 83758 | 2022-11-24 | [10 empty] | 83758 | 0 | 0
39 | FF&E PROCUREMNT | Elite Document Solutions Ltd | 159899.6 | 159899.6 | 2022-12-25 | [10 empty] | 159899.6 | 0 | 0
40 | IT SERVICES | Infrateq | 128500 | 107500 | 2023-01-26 | [10 empty] | 107500 | 21000 | -21000
41 | IT SERVICES | Samsotech LLC | 81480 | 81480 | 2022-12-25 | [10 empty] | 81480 | 0 | 0
42 | IT SERVICES | Budgeting Solutions Ltd | 38544 | 38544 | 2023-01-26 | [10 empty] | 38544 | 0 | 0
43 | IT SERVICES | Key Information Technology | 94696 | 56817.6 | 2023-01-26 |  |  |  |  | 37878.4 | [5 empty] | 94696 | 37878.4 | 0
44 | IT SERVICES | Al Suwaidi | 11000 | 11000 | 2023-01-26 | [10 empty] | 11000 | 0 | 0
45 | Art Consultant | Ayyam Gallery | 183064.8 | 182890.5 | 2023-01-26 | [10 empty] | 182890.5 | 174.3 | -174.3
46 | IT SERVICES | m-hance | 89345.34 | 3933 | 2023-01-26 |  |  |  |  | 17100 | 17000 | 17000 | 17000 | 17000 |  | 89033 | 85412.34 | -312.34
47 | IT SERVICES | Salt TS | 146000 | 71000 | 2023-01-26 |  |  |  |  | 15000 | 15000 | 15000 | 15000 | 15000 |  | 146000 | 75000 | 0
48 | IT SERVICES | SevenRooms | 84410 | 5138 | 2023-01-26 |  |  |  |  | 16000 | 16000 | 16000 | 16000 | 16000 |  | 85138 | 79272 | 728
49 | IT SERVICES | Spire Solutions DMCC |  | 164132.68 | 2022-09-22 | [10 empty] | 164132.68
50 | IT SERVICES | Oasys | 335091 | 202505.5 | 2022-11-24 |  |  |  |  | 26500 | 26500 | 26500 | 26500 | 26500 |  | 335005.5 | 132585.5 | -85.5
51 | IT SERVICES | Intelity Inc. | 367000 | 169096 | 2022-12-25 |  |  |  |  | 39600 | 39600 | 39600 | 39600 | 39600 |  | 367096 | 197904 | 96
0
52 | GOVERNMENT FEE | Empower |  | 2657537 | 2023-01-26 | [10 empty] | 2657537 | -2657537
53 | GOVERNMENT FEE | DEWA |  | 285755.52 | 2023-01-26 | [10 empty] | 285755.52 | -285755.52
54 | GOVERNMENT FEE | Business Bay LLC |  | 17657358.29 | 2022-09-22 | [10 empty] | 17657358.29 | -17657358.29
55 | GOVERNMENT FEE | Dubai Civil Defence |  | 8020 | 2022-12-25 | [10 empty] | 8020 | -8020
0
0
CONSULTANCY FEES - RESIDENCE | [16 empty] | 0
0
| Consultant Name | Description |  | Amt Certified | Period | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 |  | Cumulative Upto date
Monthly Fee Consultancy Services
1 | GAJ | ID supervision |  | 839142.581 | Sep-22 | 125720 | 125720 | 106720 | 106720 | 106720 | 133400 |  |  |  |  | 1544142.581
2 | Ian Banham & Associates | MEP supervision |  | 674066.6667 | Sep-22 | 102000 | 102000 | 102000 | 102000 | 102000 | 93933.33 |  |  |  |  | 1277999.9967
3 | Light Touch - RESIDENCES | Lighting |  | 171730 | Sep-22 | 21660 | 21660 | 21660 | 21660 | 20320 | 30720 |  |  |  |  | 309410
4 | Critical Path | Planning consultant |  | 146480 | Sep-22 | 20000 | 13904 | 13904 | 13904 | 7808 | [5 empty] | 216000
5 | CEC | 2701 MEP design |  | 50000 | Sep-22 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 50000
6 | STG Innovations | 2701 Images |  | 18166.5 | May-22 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 18166.5
7 | Gilles & Boissier | 2701 ID design |  | 257400 | Oct-22 | [5 empty] | 9100 |  |  |  |  | 266500
3682219.0776

## QS Certified
|  | 2022-09-22 | 2022-10-23 | 2022-11-24 | 2022-12-25 | 2023-01-26 | Latest Cumilative | Month
1 | F+P | 24037180.342 | 24148430.342 | 24259680.342 | 24370930.342 |  | 24370930.342 | 2022-12-25
2 | G&B - Hotel | 11834548.11 | 11984698.11 |  |  |  | 11984698.11 | 2022-10-23
3 | ALTHURATH | 20000 | 100000 |  |  |  | 100000 | 2022-10-23
4 | Conin | 2112328.13 | 2150296.88 | 2188265.63 |  |  | 2188265.63 | 2022-11-24
5 | Excom | 794247.91 | 804747.91 | 815247.91 | 825747.91 |  | 825747.91 | 2022-12-25
6 | ECON | 4200 | 14700 | 25200 | 35700 |  | 35700 | 2022-12-25
7 | Fondue | 156000 | 180000 | 272600 | 305450 |  | 305450 | 2022-12-25
8 | Roya | 1100000 | 1140000 | 1180000 | 1220000 |  | 1220000 | 2022-12-25
9 | Dorchester | 1561988.12 | 1594892.92 | 1715466.11 | 2004716.11 | 2329037.951 | 2329037.951 | 2023-01-26
10 | U+A | 150000 | 180000 | 210000 | 240000 |  | 240000 | 2022-12-25
11 | Light Touch | 89050 | 121710 | 154370 | 193370 |  | 193370 | 2022-12-25
12 | Brimax | 55000 |  |  |  |  | 55000 | 2022-09-22
13 | Mirage | 6261284.45 | 6547316.84 | 6850932.51 | 7116501.19 |  | 7116501.19 | 2022-12-25
14 | WME | 502064.52 | 610064.52 | 718064.52 | 879397.85 |  | 879397.85 | 2022-12-25
15 | Meinhardt | 44430 | 58190 | 73300 | 79100 |  | 79100 | 2022-12-25
16 | BGE | 194800 | 264800 | 352300 | 387300 | 439800 | 439800 | 2023-01-26
17 | Mitchell & Eades (L17 & L29) | 254600 | 275600 | 338400 | 372600 | 389100 | 389100 | 2023-01-26
18 | Mitchell & Eades (Musa Café) | 0 | 33000 |  |  |  | 33000 | 2022-10-23
19 | Mediatech | 37500 | 50000 | 62500 |  |  | 62500 | 2022-11-24
20 | Vortex | 51275 | 62775 | 88775 | 143350 |  | 143350 | 2022-12-25
21 | BSBG | 1295736 | 1547194 | 1752944 | 1958694 |  | 1958694 | 2022-12-25
22 | GAJ | 105606 | 197080.42 | 297925.13 | 397704.42 |  | 397704.42 | 2022-12-25
23 | CEC | 0 | 81250 | 0 | 145839.22 |  | 145839.22 | 2022-12-25
24 | AME | 18600 |  |  |  |  | 18600 | 2022-09-22
25 | Magnum Plus | 23600 | 29952.52 | 35852.52 | 41752.52 |  | 41752.52 | 2022-12-25
26 | Danial Turner | 54000 | 228600 |  |  |  | 228600 | 2022-10-23
27 | Amelie Maison D’Art | 84700 | 169400 |  |  | 1059350.6 | 1059350.6 | 2023-01-26
28 | Construct | 248004.0625 | 450034.0625 |  |  |  | 450034.0625 | 2022-10-23
29 | Salama | 300000 | 300000 | 340000 |  |  | 340000 | 2022-11-24
30 | EMTEC |  |  |  | 33000 |  | 33000 | 2022-12-25
31 | Furnish Hospitality Trading |  | 20000 | 40000 |  |  | 40000 | 2022-11-24
b. Authorities
1 | Empower | 1917786 | 2060781 | 2147939 | 2656236 | 2657537 | 2657537 | 2023-01-26
2 | DEWA | 109829.94 | 191207.8429 | 191207.8429 | 241013.44 | 285755.52 | 285755.52 | 2023-01-26
3 | Business Bay LLC | 17657358.29 |  |  |  |  | 17657358.29 | 2022-09-22
4 | Dubai Civil Defence |  |  |  | 8020 |  | 8020 | 2022-12-25
c. OSE/IT | [6 empty] | 0 | 0
1 | Elitser Technologies |  | 35415 |  |  |  | 35415 | 2022-10-23
2 | IGME |  | 31758 | 83758 |  |  | 83758 | 2022-11-24
3 | FOURTH |  | 20218 |  |  |  | 20218 | 2022-10-23
4 | Infrateq |  |  | 84000 |  | 107500 | 107500 | 2023-01-26
5 | Oasys |  |  | 202505.5 |  |  | 202505.5 | 2022-11-24
6 | Elite Document Solutions Ltd |  |  |  | 159899.6 |  | 159899.6 | 2022-12-25
7 | Intelity Inc. |  |  |  | 169096 |  | 169096 | 2022-12-25
8 | Samsotech LLC |  |  |  | 81480 |  | 81480 | 2022-12-25
9 | Budgeting Solutions Ltd |  |  |  |  | 38544 | 38544 | 2023-01-26
10 | Key Information Technology |  |  |  |  | 56817.6 | 56817.6 | 2023-01-26
11 | Al Suwaidi |  |  |  |  | 11000 | 11000 | 2023-01-26
12 | Ayyam Gallery |  |  |  |  | 182890.5 | 182890.5 | 2023-01-26
13 | m-hance |  |  |  |  | 3933 | 3933 | 2023-01-26
14 | Salt TS |  |  |  |  | 71000 | 71000 | 2023-01-26
15 | SevenRooms |  |  |  |  | 5138 | 5138 | 2023-01-26
16 | Spire Solutions DMCC | 164132.68 |  |  |  |  | 164132.68 | 2022-09-22
| BSBG | 1159000
| BGE | 110780
| WME | 448000
| Vortex | 24000
| U+A (in lie of LMS) | 0
| Brimax | 74000
Jensen Hughes / Shrimer
| Meinhardt | 40320
| Mediatech | 40572
| CEC | 554892
Fondue
| Light Touch | 5600
2457164

## Contract Sums BD
Consultant Tracker
Item | Consultant | Scope of Works | Contact | Invoice by Consultant | PC Issuence | Historical Debt | Service Agreement |  | VOs | [6 empty] | Final Contract Sum
[9 empty] | BP-09 | BP Phasing |  | VO-1 |  | VO-2 | EOT
1 | BSBG | Lead Architect | Richard Round |  | Paid | 1159000 | 1729736 |  | 380444 | 33915 | BP-09-Additional | 41300 |  |  | 1234500 | 3419895
2 | BGE | Structural | Jack Stevenson |  | Paid | 110780 | 414800 | May 22-Feb-23 | 35000 |  | Canopy | 37500 | Revised Fee Oct, Nov, Dec 22 | 210000 | 140000 | 837300
3 | WME | MEP | Ammar Al Sukar |  | Paid | 448000 | 1632000 | [8 empty] | 1632000
4 | Vortex |  | Ashhad Siddiqui |  | Paid | 24000 | 35000 |  | 26000 | 40500 | Additional works | 75000 | Variation - Units L2-03/04 | 6300 |  | 182800
5 | U+A | Landscape | Brett Ross | No Invoice | Paid | 0 | 300000 | Rate |  |  | Secret Garden | 43122.5 | Landscape changes | 23000 | 120000 | 486122.5
6 | Brimax | Signage & Wayfinding | Christian Berglehner |  | Paid | 74000 | 50000 | [8 empty] | 50000
7 | Jensen Hughes / Shrimer |  | Rashid Siddig | No Invoice |  |  | 0 | [8 empty] | 0
8 | Meinhardt | Façade | Paul Grove |  | Paid | 40320 | 116470 | [8 empty] | 116470
9 | Mediatech | ELV | Ged King | No Invoice | Paid | 40572 | 100800 | [8 empty] | 100800
10 | CEC | MEP | Sagr Kulkarni | No Invoice |  | 554892 | 0 |  | 325000 | [6 empty] | 325000
11 | Fondue | Kitchen Equipment | Mark Burns |  | Paid |  | 96000 |  |  |  |  | 156000 | Variations | 95675 |  | 347675
12 | Light Touch | Lighting | Paul Miles |  | Paid | 5610 | 123160 | May-22 |  |  |  |  | Secret Garden/Butterfly Bar | 60000 | 311820 | 494980
U+A
LIGHT TOUCH
BRIMAX
MIRAGE
WME
MEINHARDT
BG&E
MITCHELL & EADES
MEDIA TECH
VORTEX
BSBG
GAJ
CEC
Note on N6: Nayana WJK Weeraman: VO-03 ?
Note on K7: Nayana WJK Weeraman: BP-08A

## Contract Sum
Consultant | Currency | Amount | Total Amount until June 23 | Conversion factor | Amount in AED
Mirage | AED |  | 8953029 |  | 8953029
| Original Contract Amount | 4441242
| Payment for the Extended Period | 2711787
| EXTENSION (April -June 23) | 1800000
F+P | GBP |  | 5626613.56 | 4.45 | 25038430.342
| Original Contract Value | 4620000
| Variations Approved to Date | 271613.56
| LPO ref Plot-18/1989/2020 | 180000
| LPO ref Plot-18/2247/2021 | 126000
| LPO ref Plot-18/2621/2021 | 84000
| LPO ref Plot-18/2779/2021 | 45000
| LPO ref Plot-18/2968/2022 | 45000
| LPO ref Plot-18/3307/2022 | 30000
| LPO ref Plot-18/3397/2022 | 45000
| LPO ref Plot-18/3534/2022 | 30000
| EXTENSION (April) | 150000
PRD | AED |  | 198190 |  | 198190
| Original Contract Value | 191300
| Variations approved to Date | 6890
Traval Cost | AED |  | 1848076.5 |  | 1848076.5
| Trackecr total up to Oct-22 | 1648076.5
| Allow for (Nov, Dec 22 +Jan-June 23) 8months @25,000.00 | 200000
BSBG | AED |  | 3419895 |  | 3419895
| Original Contract Value | 1729736
| Variations approved to Date | 455659
| EXTENSION (April -June 23) | 1234500
BGE | AED |  | 837300 |  | 837300
| Original Contract Value | 414800
| Variations approved to Date | 282500
| EXTENSION (April -June 23) | 140000
WME | AED |  | 2207397.85 |  | 2207397.85
| Original Contract Value | 1632000
| Variations approved to Date | 427397.85
| EXTENSION (April -June 23) | 148000
Light Touch | AED |  | 494980 |  | 494980
| New Contract Amount | 123160
| Variations Agreed | 60000
| EXTENSION (April -June 23) | 311820
U+A | AED |  | 486122.5 |  | 486122.5
| Original Contract Value | 300000
| Variations approved to Date | 66122.5
| EXTENSION (April -June 23) | 120000
G&B | EUR |  | 3489396.54 | 3.85 | 13434176.679
| Original Contract Value | 1580000
| Variations approved to Date | 358789.54
| Apatrmnent DD | 1200607
| Apartment VO(Tim)+ Additional Site Visits | 350000
GAJ | AED |  | 1125100.41 |  | 1125100.41
| LPO ref Proj/PLOT18/3324/2022 | 228400
| LPO ref Proj/PLOT18/3647/2022 | 896700.41
Excom | AED |  | 846747.91 |  | 846747.91
| LPO ref Plot-18/1294/2018 | 66000
| LPO ref Plot-18/1380/2019 | 90000
| LPO ref Plot-18/1439/2019 | 72000
| LPO ref Plot-18/1575/2019 | 90000
| LPO ref Plot-18/1926/2020 | 79686.83
| LPO ref Plot-18/2105/2020 | 100999.8
| LPO ref Plot-18/2465/2021 | 252561.28
| LPO ref Plot-18/3165/2022 | 95500
QS | AED |  | 305475.77 |  | 305475.77
| LPO ref Plot-18/3395/2022 | 77700
| Dumeeqs | 154150
| EBEN | 73625.77
Conin | AED |  | 2454046.88 |  | 2454046.88
| Original Contract Value | 1350000
| Variations approved to Date | 1104046.88
Fondue | AED |  | 347675 |  | 347675
| Contract Amount | 96000
| Variations approved to Date | 251675
Roya | AED |  | 1460000 |  | 1460000
| Paid upto December 22 | 1220000
| Extension Jan-June 23 6th months @40,000.00 | 240000
ALTHURATH | AED |  | 262000 |  | 262000
| Original Contract Value | 95000
| PLOT18/1154/2021 | 30000
| Additional Services | 32000
| PLOT18/3466/2021 | 25000
| PLOT18/3467/2022 | 80000
Dochester | AED |  | 3798019.4997 |  | 3798019.4997
| NEW TSA | 845480
| TSA | 2021800
| STAFF | 471299.3665
| EXPENSES | 459440.1332
Meinhardt | AED |  | 116470 |  | 116470
| Original Contract Value | 116470
| Variations | 0
Mediatech | AED |  | 100800 |  | 100800
| Original Contract Value | 100800
| Variations | 0
Mitchell & Eades (L17 & L29) | AED |  | 642600 |  | 642600
| LPO ref. PROJ/PLOT18/3266/2022 | 386000
| LPO ref. PROJ/PLOT18/3424/2022 | 228000
| LPO ref. PROJ/PLOT18/3645/2022 | 13200
| LPO to be issued | 15400
Brimaxx | AED |  | 105000 |  | 105000
| Contract Amount | 50000
| Pre-Novation | 55000
Vortex | AED |  | 182500 |  | 182500
| Original Contract Value | 35000
| Variations approved to Date | 147500
| EXTENSION (April -June 23) | 0
CEC | AED |  | 325000 |  | 325000
| Original Contract Value | 0
| Variations | 325000
EOT
Land Sterling | AED |  | 33170 |  | 33170
| LPO ref Plot-18/3411/2022 | 33170
| Variations | 0
Amelie Maison D’Art | EUR |  | 924625 | 3.85 | 3559806.25
| Contract Amount | 88000
| Variations | 836625
EMTEC | AED |  | 55000 |  | 55000
| LPO ref Proj/PLOT18/3503/2022 | 55000
Danial Turner | AED |  | 228600 |  | 228600
| LPO ref Plot-18/3048/2022 | 54000
| LPO ref Plot-18/3049/2022 | 117000
| LPO ref Plot-18/3486/2022 | 57600
Furnish Hospitality Trading | AED |  | 180000 |  | 180000
| LPO Ref: PROJ/PLOT18/3410/2022 | 40000
| EXTENSION (April -June 23) | 140000
[5 empty] | AED | 1
[5 empty] | GBP | 4.45
[5 empty] | EUR | 3.85
[5 empty] | USD | 3.676

## December Payments
Company Name | PC No | Certified | PC No | Paid |  | 243750
Al Turath |  |  | 2 | 80000 | F+P | 222500
Amelie Maison D'Art |  |  | 2 | 84700 | G&B | 0
BG&E | 9 | 87500 | 8 | 70000 | Al Turath | 80000
BSBG | 13 | 205750 | BSBG-12 | 205750 | Conin | 37968.75
CEC | 7 | 162500 | 5 | 81250 | Excom | 21000
Conin | 58 | 37968.75 | 57 | 37968.75 | PRD | 0
Construct Branding |  |  | 2 | 202030 | Travel | 170025
Dorchester |  |  | 29 | 3835.601 | Fondue | 92600
Econ | 3 | 10500 | 2 | 10500 | Roya | 40000
Em Tec | 1 | 33000 |  |  | Dorchester | 3835.601
Excom | 50 | 10500 | 49 | 10500 | U+A | 30000
F+P |  | 333750 |  | 222500 | Light Touch | 32660
Fondue |  | 92600 |  | 92600 | BRIMAX | 0
GAJ | 15 | 100844.71 | 13 | 91473.84 | Mirage | 286032.39
Light Touch | 16 | 32660 | 14 | 32660 | WME | 108000
Magnum Plus | 6 | 5900 | 5 | 5900 | Meinhardt | 13940
Mediatech | 6 | 12500 | 5 | 12500 | BG&E | 70000
Meinhardt | 7 | 15110 | MEINH-06 | 13940 | Mitchell & Eades | 90437.5
Mirage | 22 | 303615.67 | 21 | 286032.39 | Mediatech | 12500
Mitchell & Eades |  | 121750 |  | 90437.5 | Vortex | 11500
Travel |  | 0 |  | 72765 | BSBG | 205750
Roya | 34 | 40000 | 33 | 40000 |  | 0
Salama Structural | 3 | 40000 | 3 | 40000 | GAJ | 91473.84
Travel |  | 0 |  | 97260 | CEC | 81250
U+A |  |  | 5 | 30000 | Acoustic Middle East | 0
Vortex | 6 | 26000 | 5 | 11500 | Magnum Plus | 5900
WME | WME-09 | 108000 | WME-08 | 108000 | Daniel Turne | 0
[5 empty] | Amelie Maison D'Art | 84700
[5 empty] | Land Sterling | 0
|  |  |  | 2034103.081 |  | 1792073.081
242030
Residence
Bond Interiors-RESIDENCES | 11 | 6037621.65 | 11 | 6037621.65
CEC - Residences | 6 | 42750 | 6 | 42750
GAJ |  | 126329.63 |  | 252635.06
IB&A - RESIDENCES |  | 121266.67 |  | 223266.67
Light Touch - RESIDENCES |  | 21660 |  | 43320
Critical Path |  | 24000 |  | 44000
|  | 336006.3 |  | 605971.73
Elitser Technologies |  |  | ELS-1 | 35415
Elite Document Solutions | 1 | 159899.6
Samsotech | 1 | 81480 | 1 | 81480
Spire Solutions | 1 | 164132.68 | 1 | 164132.68
Fourth Limited |  |  | 1 | 20218
OASYS | 1 | 202505.5 | 1 | 202505.5
IGME Information Technology |  | 52000 |  | 83758
IGME Information Technology | 2 | 52000 | 1 | 31758
IGME Information Technology |  |  | 2 | 52000
Infrateq | 1 | 84000 | 1 | 84000
Intelity | 1 | 169096 | 1 | 169096
|  | 965113.78 |  | 924363.18
Al Shafar Interiors |  |  | ASI-WFA-02 | 441498.44
EW Cox | WFA-01 | 80486.9
Empower DCS |  | 595455 |  | 142995
Business Bay LLC |  |  | 6 | 152820.82
DEWA |  |  | 4 | 35576

## FF&E Payments
| Certified | Paid
HOTEL
Pre-Opening | 86400 | 86400
OS&E Payment Tracker | 1190801.525 | 438393.581
CCM Fees | 117600 | 112800
FF&E Payment Tracker | 9173382.3781 | 5625903.5
IT | 1397466.38 | 1011754.18
| 11965650.2831 | 7275251.261
RESI
FF&E Payment Tracker | 4510065.49 | 4510065.49
FF&E Miscellaneous | 15115 | 10942.8571
| 4525180.49 | 4521008.3471

## Consultat & Hard Cost
Plot -18 Payments -November 2022
| SN | Company Name | Certified | Paid |  | As per PC | Month | Paid | Total Contract | Paid
1 | 50 | Acoustic Middle East |  | 18600
2 | 1 | Al Ain Ahlia Insurance |  | 808013.48
4 | 48 | Al Turath | 80000 | 100000
5 | 63 | Amelie Maison D'Art |  | 84700
6 | 30 | BG&E | 35000 | 70000
7 | 27 | BSBG | 239665 | 272033
8 | 47 | Business Bay LLC | 152820.82 | 152820.82
9 | 84 | CEC | 81250 | 81250
10 | 20 | Conin | 37968.75 | 75937.5 |  | 2188265.63 | nov | 2217944.67 | 2340140.63 | updated
11 | 8 | Construct Branding | 202030 |  | not entered
13 | 43 | Daniel Turner |  | 57600 |  | 228600 |  | 117000
15 | 34 | Dorchester |  | 223471.0255 |  | 1379981.56 |  |  | 3110892.92 | NOT UPDATED
16 | 17 | DSGN |  | 24700 | not entered | Closed
17 | 67 | Econ QS | 10500 | 10500 |  |  |  |  | NOT UPDATED
20 | 16 | Excom | 10500 | 21000 |  |  |  |  | NOT UPDATED
| 5 | Nasser Air Travel | 27535 | 97190 |  | 1648076.5 |  | 1922496.5 | 1898076.5
| 3 | U Travel | 72510 | 177230
21 | 26 | Fondue | 24000 | 48000 |  | 180000 | Oct | 156000 | 327450
| 14 | Roya | 40000 | 80000 |  | 1180000 |  | 1140000 | 1340000
|  | Maison D’Art |  |  |  | 169400 |  | 84700 | 338800
23 | 44 | G&B |  | 331100 |  | 12032894.14 |  | 12032894.14 | 13058666.31
25 | 18 | GAJ - Hotel | 91473.84 | 91473.84
29 | 49 | Land Sterling |  | 16585
30 | 22 | Light Touch | 32660 | 54920
32 | 25 | Mediatech | 12500 | 25000
33 | 24 | Meinhardt | 13940 | 33770
34 | 21 | Mirage | 286032.39 | 579849.57
35 | 9 | Mitchell & Eades | 21000 | 204600
40 | 19 | U+A | 30000 | 60000
41 | 23 | Vortex | 11500 | 19550
42 | 31 | WME | 108000 | 216000
31 | 54 | Magnum Plus Cleaning | 5900 | 17700
43 | 51 | NSCC |  | 269239.5
44 | 33 | Khansaheb | 19804921.87 | 15491078.95
45 | 85 | Al Shafar Interiors | 441498.44 | 441498.44
46 | 52 | DEWA | 35576 | 140175.94 | [5 empty] | Tracker | not in Tracker
47 | 56 | Empower DCS | 2449 | 142995 | [5 empty] | 2560643.14 | 230153 | 2790796.14
48 | 58 | Elitser Technologies | 35415 | 35415 | [7 empty] | 2790796.14
49 | 60 | Fourth Limited | 20218 | 20218
50 | 59 | IGME Information Technology | 31758 | 31758
|  |  | 87391 | 87391
53 | 26 | Bond Interiors-RESIDENCES | 11005574.21 | 11005574.21
51 | 10 | Ian Banham - RESIDENCES | 102000
52 | 17 | Critical Path – Residences | 20000
54 | 65 | IBA - RESIDENCES |  | 102000
55 | 76 | Light Touch - RESIDENCES | 21660 | 21660
56 | 68 | GAJ | 126305.43 | 126305.43
57 | 15 | IBA |  | 82000
| 72 | Critical Path |  | 20000
|  |  | 269965.43 | 351965.43