## 1C. FCR
|  | Project Name | Plot 18
|  | Plot Number | Plot 18
|  | FCR for Month ending | November 2022 | [23 empty] | 4399300.81
|  | Previous Month | October 2022 | [32 empty] | 50% |  | 50%
|  | Approved Business Plan | December 2017 | [32 empty] | TOC RESI |  | TOC KCE
[23 empty] | 2022 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023
Cost Code |  | Scope of Work | Consultant / Regulatory Authority / Contractor | Approved Business Plan Dec 2017 (Superseded) | TARGET BUDGET | Previous month Forecast Cost October 2022 | Current month Forecast Cost November 2022 | Figures from Budget Breakdown | % of Total Cost | Variance with Budget | Variance with last month | Current month Forecast Cost November 2022 | Payments Certified by QS November 2022 | Payments Certified by QS November 2022 (Original Value in FCR) | % of works Certified | Balance to Certify | Actual amount paid by Finance (as at the end of November 2022) | Actual amount paid as % of Certified | Balance to pay |  |  |  | 2022-12-11 | 2023-01-11 | 2023-02-11 | 2023-03-11 | 2023-04-11 | 2023-05-11 | 2023-06-11 | 2023-07-11 | 2023-08-11 | 2023-09-11 | 2023-10-11 | 2023-11-11 | 2023-12-11 | 2024-01-11 | 2024-02-11 | 2024-03-11 | 2024-04-11 | 2024-05-11 | 2024-06-11 | Total future cash flow | Variance | Check | Check
1 | bar: 2024-01-11; 2024-03-11
| A | CONSULTANCY FEES |  | 1 | 2 | bar: 2023-01-11; 2023-03-11; 2024-01-11 to 2024-03-11
|  | ONGOING CONSULTANCY AGREEMENTS |  | 33809813.8 | 51544617.62 | 76538485.6462 | 79625311.7962 |  | 6.306% | 45815497.9962 | 3086826.15 | 79625311.7962 | 67212675.96 | 70100121.4621 | 84.41% | 12960483.2062 | 69131923.6361 | 102.9% | 10493388.1601 | bar: 2024-01-11; 2024-03-11
| 1 | ARCHITECT DESIGN - LEAD (FC BTP @4.8) | FOSTERS & PARTNERS | 18822918 | 18822918 | 18822918 | 18822918 | 24659680.342 | 1.695% | 0 | 0 | 18822918 | 16338680.34 | 18822918 | 86.8% | 2484237.66 | 18822918 | 115.2% | 0 | [22 empty] | 0 | 0 | TRUE | TRUE | bar: 2024-01-11; 2024-03-11
| 2 | ARCHITECT - SUPERVISION LEAD (FC @4.8) | FOSTERS & PARTNERS | 5856000 | 5856000 | 8802472.9062 | 8802472.9062 |  | 0.7926% | 2946472.9062 | 0 | 8802472.9062 | 8032250 | 8629887.7916 | 91.25% | 770222.9062 | 8629887.7916 | 107.4% | 172585.1146 |  |  | 0 | 49553.333 | 49553.333 | 49553.333 | 23925.1156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 172585.1146 | 0 | TRUE | TRUE
| 3 | INTERIOR DESIGNER | G&B | 3789345.8 | 11600000 | 13413557.68 | 13413557.68 | 8078829.36 | 1.208% | 9624211.88 | 0 | 13413557.68 | 7362361.16 | 12032894.14 | 54.89% | 6051196.52 | 12032894.14 | 163.4% | 1380663.54 |  |  | 0 | 200000 | 300000 | 298057.68 | 300000 | 282605.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1380663.54 | 0 | TRUE | TRUE
| 4 | INTERIOR DESIGNER | DSGN | 0 | 3500000 | 3857039.16 | 3857039.16 |  | 0.3473% | 3857039.16 | 0 | 3857039.16 | 3851739.16 | 3827039.16 | 99.86% | 5300 | 3827039.16 | 99.36% | 30000 |  |  | 0 | 30000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | TRUE | TRUE
| 5 | PLANNING RESOURCES | PETER EVANS & Critical Path | 0 | 1000000 | 1897446.62 | 1897446.62 | 196000 | 0.1708% | 1897446.62 | 0 | 1897446.62 | 1897446.62 | 1897446.62 | 100% | 0 | 1897446.62 | 100% | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 6 | TRAFFIC ACCESS STUDY | AL TURATH | 125000 | 213000 | 213000 | 262620 | 105000 | 0.02365% | 137620 | 49620 | 262620 | 100000 | 257620 | 38.08% | 162620 | 257620 | 257.6% | 5000 |  |  | 0 |  | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | TRUE | TRUE
| 7 | PROJECT MONITOR | CONIN | 0 | 1350000 | 2150296.88 | 2378109.38 | 2340140.63 | 0.2141% | 2378109.38 | 227812.5 | 2378109.38 | 2188265.63 | 2188265.63 | 92.02% | 189843.75 | 2188265.63 | 100% | 189843.75 |  |  | 0 | 55000 | 55000 | 55000 | 24843.75 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189843.75 | 0 | TRUE | TRUE
| 8 | Q.S FEES | HQS - EXCOMM-ECON-DUMEEQS-EBN | 100000 | 100000 | 1224043.68 | 1224043.68 | 945447.91 | 0.1102% | 1124043.68 | 0 | 1224043.68 | 861447.91 | 1142017.87 | 70.38% | 362595.77 | 1137817.77 | 132.1% | 86225.91 |  |  | 0 | 21000 | 21000 | 21000 | 23225.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86225.91 | 0 | TRUE | TRUE
| 9 | MEP MANAGER | IAN BANHAM & ASSOCIATES | 0 |  | 2734401.39 | 2734401.39 | 3134334.72 | 0.2462% | 2734401.39 | 0 | 2734401.39 | 2734401.39 | 2734401.39 | 100% | 0 | 2652401.38 | 97% | 82000.01 |  |  | 0 |  |  |  |  | 82000.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82000.01 | 0 | TRUE | TRUE
| 10 | SURVEY SERVICES, OQOOD SUBMISSION | PRD | 191300 | 351300 | 198190 | 198190 | 198190 | 0.01784% | 6890 | 0 | 198190 | 151110 | 151110 | 76.25% | 47080 | 151110 | 100% | 47080 |  |  | 0 | 47080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47080 | 0 | TRUE | TRUE
| 11 | TRAVEL COST | VARIOUS | 113500 | 2099999.62 | 2205158.27 | 1898076.5 | 1898076.5 | 0.1709% | 1784576.5 | -307081.77 | 1898076.5 | 1648076.5 | 1648076.5 | 86.83% | 250000 | 1648076.5 | 100% | 250000 |  |  | 0 | 2022-12-11: 120000; 2023-01-11: 130000; 2023-11-11: 0; 2023-12-11: 0; 2024-01-11: 0; 2024-02-11: 0; 2024-03-11: 0; 2024-04-11: 0; 2024-05-11: 0; 2024-06-11: 0 | 250000 | 0 | TRUE | TRUE
| 12 | Fondue |  |  |  |  | 327450 | 423410 |  |  | 327450 | 327450 | 305450 | 180000 | 93.28% | 22000 | 156000 | 51.07% | 171450 |  |  | 0 | 2022-12-11: 24000; 2023-01-11: 50000; 2023-02-11: 50000; 2023-03-11: 47450 | 171450 | 0 | TRUE | TRUE
| 13 | Roya |  |  |  |  | 1340000 | 1380000 |  |  | 1340000 | 1340000 | 1220000 | 1180000 | 91.04% | 120000 | 1140000 | 93.44% | 200000 |  |  | 0 | 2022-12-11: 40000; 2023-01-11: 40000; 2023-02-11: 40000; 2023-03-11: 40000; 2023-04-11: 40000 | 200000 | 0 | TRUE | TRUE
| 14 | Maison D’Art |  |  |  |  | 338800 |  |  |  | 338800 | 338800 |  | 169400 | 0% | 338800 | 84700 | 0% | 254100 |  |  | 0 | 2023-02-11: 75000; 2023-03-11: 104100; 2023-04-11: 75000 | 254100 | 0 | TRUE | TRUE
| 15 | HOTEL OPERATOR | DORCHESTER | 2026750 | 2026750 | 2767000 | 2767000 | 3845040.18 | 0.2491% | 740250 | 0 | 2767000 | 2329040.18 | 1594881.3705 | 84.17% | 437959.82 | 1476029.6045 | 63.38% | 1290970.3955 |  |  | 0 | 55000 | 55000 | 55000 | 55000 | 303270 | 358270 | 312420 | 97010.3955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1290970.3955 | 0 | TRUE | TRUE
| 16 | MEP CONSULTANT | CSA - PRE NOVATION | 1825000 | 1850000 | 1732373.48 | 1732373.48 |  | 0.156% | -92626.52 | 0 | 1732373.48 | 1732373.48 | 1732373.48 | 100% | 0 | 1732373.48 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 17 | LANDSCAPE | 40 NORTH |  | 1814650 | 615795.54 | 615795.54 |  | 0.05545% | 615795.54 | 0 | 615795.54 | 615795.54 | 615795.54 | 100% | 0 | 615795.54 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 18 | NEW LANDSCAPE | LMS, U+A | 0 |  | 436940 | 436940 | 390000 | 0.03934% | 436940 | 0 | 436940 | 240000 | 210000 | 54.93% | 196940 | 180000 | 75% | 256940 |  |  | 0 | 60000 | 40000 | 40000 | 40000 | 40000 | 36940 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256940 | 0 | TRUE | TRUE
| 19 | EXTERIOR AND INTERIOR LIGHTING DESIGN | LIGHT TOUCH | 725000 | 725000 | 485660.22 | 485660.22 | 476506 | 0.04373% | -239339.78 | 0 | 485660.22 | 198970 | 159970 | 40.97% | 286690.22 | 127310 | 63.98% | 358350.22 |  |  | 0 | 33000 | 125000 | 100000 | 50000 | 50350.22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 358350.22 | 0 | TRUE | TRUE
| 20 | SIGNAGE AND WAYWARD FINDING | BRIMAX | 235000 | 235000 | 161000 | 161000 | 124000 | 0.0145% | -74000 | 0 | 161000 | 74000 | 111000 | 45.96% | 87000 | 111000 | 150% | 50000 |  |  | 0 | 17714.2857 | 14571.4286 | 17714.2857 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | TRUE | TRUE
| 21 | MIRAGE RESOURCES - PROJECT MANAGERS | MIRAGE |  |  | 8281242 | 8281242 | 8316501.19 | 0.7456% | 8281242 | 0 | 8281242 | 7116501.19 | 6850932.51 | 85.94% | 1164740.81 | 6604329.08 | 92.8% | 1676912.92 |  |  | 0 | 479159.5637 | 479159.5637 | 479159.5637 | 239434.2288 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1676912.92 | 0 | TRUE | TRUE
| 22 | MEP CONSULTANT | WME |  |  | 1632000 | 1632000 | 1871397.85 |  |  | 0 | 1632000 | 1327397.85 | 718064.52 | 81.34% | 304602.15 | 718064.52 | 54.1% | 913935.48 |  |  | 0 | 233142.8571 | 233142.8571 | 233142.8571 | 214506.9086 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 913935.48 | 0 | TRUE | TRUE
| 23 | FAÇADE ENGINEERING / BMU DESIGN | MEINHARDT |  |  | 152470 | 152470 | 191640 |  |  | 0 | 152470 | 119420 | 98510 | 78.32% | 33050 | 98510 | 82.49% | 53960 |  |  | 0 | 35000 | 18960 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53960 | 0 | TRUE | TRUE
| 24 | STRUCTURAL CONSULTANT | BG&E |  |  | 414800 | 414800 | 655580 |  |  | 0 | 414800 | 550580 | 340580 | 132.7% | -135780 | 264800 | 48.09% | 150000 |  |  | 0 | 40000 | 35000 | 35000 | 40000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | TRUE | TRUE
| 25 | L17 & L29 RESTAURANTS | MITCHELL & EADES |  |  | 386000 | 614000 | 715500 |  |  | 228000 | 614000 | 389100 | 375150 | 63.37% | 224900 | 339600 | 87.28% | 274400 |  |  | 0 | 150000 | 50000 | 50000 | 24400 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 274400 | 0 | TRUE | TRUE
| 26 | IT CONSULTANT | MEDIA TECH |  |  | 147600 | 147600 | 165572 |  |  | 0 | 147600 | 103072 | 62500 | 69.83% | 44528 | 62500 | 60.64% | 85100 |  |  | 0 | 2022-12-11: 20000; 2023-01-11: 20100; 2023-02-11: 15000; 2023-03-11: 15000; 2023-04-11: 15000 | 85100 | 0 | TRUE | TRUE
| 27 | FIRE SAFETY CONSULTANCY | VORTEX |  |  | 170000 | 170000 | 326150 |  |  | 0 | 170000 | 143350 | 70825 | 84.32% | 26650 | 70825 | 49.41% | 99175 |  |  | 0 | 2022-12-11: 15000; 2023-01-11: 20000; 2023-02-11: 20000; 2023-03-11: 20000; 2023-04-11: 24175 | 99175 | 0 | TRUE | TRUE
| 28 | SUPERVISION SERVICES - BSBG | BSBG |  |  | 2444736 | 2444736 | 3980694 |  |  | 0 | 2444736 | 3117694 | 1547194 | 127.5% | -672958 | 1547194 | 49.63% | 897542 |  |  | 0 | 403508.375 | 220805.875 | 273227.75 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 897542 | 0 | TRUE | TRUE
| 29 | Consultant Over-run (DL DEPLOYMENT SCHEDULE) |  | 0 |  | 61658.82 | 61658.82 |  | 0.005552% | 61658.82 | 0 | 61658.82 | 0 | 0 | 0% | 61658.82 | 0 | 0% | 61658.82 |  | 0 | 0 | 61658.82 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61658.82 | 0 | TRUE | TRUE
| 30 | ID Supervision-Hotel | GAJ |  |  | 228400 | 875040.42 | 1319184.42 |  |  | 646640.42 | 875040.42 | 397704.42 | 197080.42 | 45.45% | 477336 | 197080.42 | 49.55% | 677960 |  |  | 0 | 150000 | 125000 | 152960 | 125000 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 677960 | 0 | TRUE | TRUE
| 31 | FOH MEP | CEC |  |  | 320000 | 320000 | 1106981.22 |  |  | 0 | 320000 | 700731.22 | 81250 | 219% | -380731.22 | 81250 | 11.6% | 238750 |  |  | 0 | 50000 | 50000 | 50000 | 50000 | 38750 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238750 | 0 | TRUE | TRUE
| 32 | Acoustic | Acoustic Middle East |  |  | 46500 | 46500 | 46500 |  |  | 0 | 46500 | 18600 | 37200 | 40% | 27900 | 37200 | 200% | 9300 |  |  | 0 | 9300 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9300 | 0 | TRUE | TRUE
| 33 | Cleaning Mock-ups (Level 8) | Magnum Plus |  |  | 70800 | 70800 |  |  |  | 0 | 70800 | 41752.52 | 29952.52 | 58.97% | 29047.48 | 23600 | 56.52% | 47200 |  |  | 0 | 6000 | 6000 | 8800 | 10000 | 10000 | 6400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47200 | 0 | TRUE | TRUE
| 34 | Recrutment | Daniel Turne |  |  | 93015 | 328600 | 338600 |  |  | 235585 | 328600 | 228600 | 228600 | 69.57% | 100000 | 117000 | 51.18% | 211600 |  |  | 0 | 0 | 60000 | 60000 | 91600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211600 | 0 | TRUE | TRUE
| 35 | Art Consultant | Amelie Maison D’Art |  |  | 338800 | 338800 | 1228750.6 |  |  | 0 | 338800 | 1059350.6 | 160600 | 312.7% | -720550.6 | 84700 | 7.995% | 254100 |  |  | 0 | 35000 | 50000 | 50000 | 50000 | 50000 | 19100 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254100 | 0 | TRUE | TRUE
| 36 | RERA Valuation | Land Sterling |  |  | 33170 | 33170 | 33170 |  |  | 0 | 33170 | 17414.25 | 16585 | 52.5% | 15755.75 | 16585 | 95.24% | 16585 |  |  | 0 | 16585 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16585 | 0 | TRUE | TRUE
[44 empty] | TRUE | TRUE
| 37 | INACTIVE CONSULTANCY AGREEMENTS |  | 14528816.2 | 14282191.19 | 14290753.65 | 14290753.65 |  | 1.287% | -238062.55 | 0 | 14290753.65 | 14290753.65 | 14290753.65 | 100% | 0 | 14290753.65 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
[44 empty] | TRUE | TRUE | bar: 2024-01-11; 2024-03-11
|  | TOTAL CONSULTANCY FEES |  | 48338630 | 65826808.81 | 90829239.2962 | 93916065.4462 |  | 7.592% | 45577435.4462 | 3086826.15 | 93916065.4462 | 81503429.61 | 84390875.1121 | 86.78% | 12960483.2062 | 83422677.2861 | 102.4% | 10493388.1601 |  |  | 0 | 2456702.2346 | 2253293.0574 | 2228615.4696 | 1588485.913 | 1136151.09 | 420710 | 312420 | 97010.3955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10493388.1601 | 0 | TRUE | TRUE
0 | bar: 2024-01-11; 2024-03-11
| B | LOCAL AUTHORITY FEES | [19 empty] | 0 | bar: 2023-01-11; 2023-03-11; 2024-01-11; 2024-03-11
| 1 | POWER CONNECTION (TCL 7MW) | DEWA | 5739077 | 6465200 | 8087188 | 8087188 |  | 0.7282% | 2348111 | 0 | 8087188 | 8087188 | 8087188 | 100% | 0 | 8087188 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 2 | POWER CONNECTION (TCL INCREASE BY 3.5MW) | DEWA | 0 | 3500000 | 75019.9 | 75019.9 |  | 0.006755% | 75019.9 | 0 | 75019.9 | 75019.9 | 75019.9 | 100% | 0 | 75019.9 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 3 | WATER CONNECTION/CHARGERS | DEWA | 150000 | 150000 | 958457 | 958457 |  | 0.0863% | 808457 | 0 | 958457 | 343175.94 | 343175.94 | 35.81% | 615281.06 | 241675.94 | 70.42% | 716781.06 |  |  | 0 | 101500 | 247000 | 100000 | 100000 | 100000 | 68281.06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 716781.06 | 0 | TRUE | TRUE
| 4 | SUBSTATION FEES | DEWA | 1577000 | 1577000 | 1577000 | 1577000 |  | 0.142% | 0 | 0 | 1577000 | 1577000 | 1577000 | 100% | 0 | 1577000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 5 | DUBAI CIVIL DEFENSE | DCD | 213649 | 213649 | 28920 | 28920 |  | 0.002604% | -184729 | 0 | 28920 | 28920 | 28920 | 100% | 0 | 28920 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 6 | CIVIL AVIATION |  | 5000 | 5000 | 5000 | 5000 |  | 0.0004502% | 0 | 0 | 5000 | 0 | 0 | 0% | 5000 | 0 | 0% | 5000 |  |  | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | TRUE | TRUE
| 7 | PERMIT/ NOC CHARGES | DUBAI MUNICIPALITY / DP | 894554 | 894554 | 727472 | 727472 |  | 0.0655% | -167082 | 0 | 727472 | 727472 | 727472 | 100% | 0 | 727472 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 8 | ADDITIONAL GFA COSTS (80/FT2) | DUBAI MUNICIPALITY | 2071852 | 2017852 | 0 | 0 |  | 0% | -2071852 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 9 | BUILDING PERMIT EXCEPTION FEES | DUBAI MUNICIPALITY | 1500000 | 70331 | 1406619 | 1406619 |  | 0.1267% | -93381 | 0 | 1406619 | 1406619 | 1406619 | 100% | 0 | 1406619 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 10 | INCREASED POWER (SUBSTATION CONTRIBUTION) | DP | 4080000 | 277449 | 5548976 | 5548976 |  | 0.4996% | 1468976 | 0 | 5548976 | 5548976 | 5548976 | 100% | 0 | 5548976 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 11 | ADDITIONAL HEIGHT | DP | 6710000 | 6710000 | 6710000 | 6710000 |  | 0.6042% | 0 | 0 | 6710000 | 6710000 | 6710000 | 100% | 0 | 6710000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 12 | ANNUAL MASTER-COMM CHARGES (2016-2020) | DP | 4662471 | 4962471 | 1619005.54 | 1619005.54 |  | 0.1458% | -3043465.46 | 0 | 1619005.54 | 1619005.54 | 1619005.54 | 100% | 0 | 1619005.54 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 13 | DPG ADDITIONAL GFA COSTS (190/FT2) | DP | 4830000 | 4830000 | 10300000 | 10300000 |  | 0.9274% | 5470000 | 0 | 10300000 | 10300000 | 10300000 | 100% | 0 | 10300000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 14 | CONNECTION CHARGE+Deposit | EMPOWER | 6413181 | 6419181 | 6161400 | 6161400 |  | 0.5548% | -251781 | 0 | 6161400 | 6161400 | 6161400 | 100% | 0 | 6161400 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 15 | DEMAND CHARGERS/SECURITY | EMPOWER | 855000 | 855000 | 5568314 | 5568314 |  | 0.5014% | 4713314 | 0 | 5568314 | 2790796.14 | 2790796.14 | 50.12% | 2777517.86 | 2790796.14 | 100% | 2777517.86 |  |  | 0 | 379099.4 | 125000 | 350000 | 650000 | 150000 | 150000 | 650000 | 323418.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2777517.86 | 0 | TRUE | TRUE
| 16 | LEED CERTIFICATION FEES | USGBC | 133216 | 35000 | 4411 | 4411 |  | 0.0003972% | -128805 | 0 | 4411 | 4411 | 4411 | 100% | 0 | 4411 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 17 | LEGAL FEES AND FINANCE CHARGES | VARIOUS | 1820000 | 1650000 | 1546782 | 1546782 |  | 0.1393% | -273218 | 0 | 1546782 | 1546782 | 1546782 | 100% | 0 | 1546782 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 18 | RTA & DLD | RTA & DLD | 25000 | 2500 | 5681 | 5681 |  | 0.0005115% | -19319 | 0 | 5681 | 5681 | 5681 | 100% | 0 | 5681 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 19 | TECOM | TECOM | 50000 | 50000 | 18700 | 18700 |  | 0.001684% | -31300 | 0 | 18700 | 18700 | 18700 | 100% | 0 | 18700 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
|  | TOTAL LOCAL AUTHORITY FEES |  | 41730000 | 40685187 | 50348945.44 | 50348945.44 |  | 4.533% | 8618945.44 | 0 | 50348945.44 | 46951146.52 | 46951146.52 | 93.25% | 3397798.92 | 46849646.52 | 99.78% | 3499298.92 |  |  |  | 485599.4 | 372000 | 450000 | 750000 | 250000 | 218281.06 | 650000 | 323418.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 3499298.92 | 0 | TRUE | TRUE
| C | CAPITAL WORKS | bar: 2023-01-11; 2023-03-11; 2024-01-11; 2024-03-11
| 1 | FACILITATING WORKS |  | 40000000 | 40587829.04 | 40587829.04 | 40587829.04 |  | 3.655% | 587829.04 | 0 | 40587829.04 | 40587828.83 | 40587828.83 | 100% | 0.21 | 40587828.83 | 100% | 0.21 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | -0.21 | FALSE | FALSE
| 1.1 | PILING, SHORING & ENABLING WORKS | NSCC | 40000000 | 40559649.04 | 40559649.04 | 40559649.04 |  | 3.652% | 559649.04 | 0 | 40559649.04 | 40559648.83 | 40559648.83 | 100% | 0.21 | 40559648.83 | 100% | 0.21 | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | -0.21 | FALSE | FALSE
| 1.2 | OME SITE ESTABLISHMENT | VARIOUS | 0 | 28180 | 28180 | 28180 |  | 0.002537% | 28180 | 0 | 28180 | 28180 | 28180 | 100% | 0 | 28180 | 100% | 0 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 2+3+4+5 | RP TOTAL - MAIN WORKS & PROVISIONAL SUMS & CONTRACT FEES NOVATED |  | 730862422 | 753126225.04 | 507541746.9409 | 507541746.9409 |  |  |  | 0 | 507541746.9409 | 583165175.8896 | 583165175.8896 |  | -75623428.9487 | 507541746.9409 |  | 0 |  | 0 |  | 2023-12-11: 0; 2024-03-11: 0 | 0 | 0 | TRUE | TRUE
[7 empty] | 0 | [13 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6 | LOOSE FF&E | [18 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6.1 | LOOSE FF&E FOR RESIDENTIAL AND HOTEL | TBA | 40269400 | 32000000 | 26300000 | 26300000 |  | 2.797% | -12269400 | 0 | 26300000 | 11954795.4471 | 11954795.4471 | 45.46% | 14345204.5529 | 4521008.3471 | 37.82% | 21778991.6529 |  |  | 0 | 1945720.36 | 2378317.8143 | 2808487.27 | 1546306.34 | 3600855.75 | 3217034.7862 | 6282269.3324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21778991.6529 | 0 | TRUE | TRUE
| 6.2 | BOH EQUIPMENT-Commercial Kitchen and Laundry | TBA | 13000000 | 11077300 | 7162178 | 7162178 |  | 1.199% | -1002700 | 0 | 7162178 | 2608796.1 | 2608796.1 | 36.42% | 4553381.9 | 2608796.1 | 100% | 4553381.9 |  |  | 0 |  | 852343.236 | 1741752.844 | 744451.12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1214834.7 | 0 | 0 | 0 | 4553381.9 | 0 | TRUE | TRUE
| 6.2.1 | Commercial Kitchen and Laundry | [7 empty] | 0 | [8 empty] | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 6.2.2 | Gym Equipment | [7 empty] | 0 | [8 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE | Moved to Hotel public
[10 empty] | 0 | [8 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE | Moved to Hotel public
| 6 | LOOSE FF&E |  | 53269400 | 43077300 | 33462178 | 33462178 |  | 3.013% | -19807222 | 0 | 33462178 | 14563591.5471 | 14563591.5471 | 43.52% | 18898586.4529 | 7129804.4471 | 48.96% | 26332373.5529 |  |  |  | 1945720.36 | 3230661.0503 | 4550240.114 | 2290757.46 | 3600855.75 | 3217034.7862 | 6282269.3324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1214834.7 | 0 | 0 | 0 | 26332373.5529 | 0 | TRUE | TRUE
[23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7 | RESIDENCES FIT-OUT | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7.1 | Preliminaries |  |  |  | 3800000 | 3800000 |  |  |  |  | 3800000 |  |  |  | 3800000 |  |  | 3800000 |  |  | 0 | 2120400 | 547200 | 410400 | 342000 | 190000 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800000 | 0 | TRUE | TRUE
| 7.2 | Residences - Fit out Package |  | 0 | 18445000 | 91359810.83 | 91359810.83 |  | 8.226% | 91359810.83 | 0 | 91359810.83 | 65799036.26 | 65799036.26 | 72.02% | 25560774.57 | 63057187.6724 | 95.83% | 28302623.1576 |  |  | 0 | 9600000 | 9700467.6849 | 4766486.6312 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4235668.8415 |  | 0 | 0 | 0 | 0 | 28302623.1576 | 0 | TRUE | TRUE
| 7.3 | Residential Kitchen appliances |  |  |  | 3100000 | 3100000 |  |  |  |  | 3100000 |  |  |  | 3100000 |  |  | 3100000 |  | 0 | 0 | 1729800 | 446400 | 334800 | 279000 | 155000 | 155000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3100000 | 0 | TRUE | TRUE
| 7.4 | Residences - Fit out Package Consultancy Fee |  | 0 | 18445000 | 2500000 | 3682219.5 | 3682219.0776 | 0.3315% | 3682219.5 | 1182219.5 | 3682219.5 | 2690711.32 | 2690711.32 | 73.07% | 991508.18 | 2631959.35 | 97.82% | 1050260.15 |  |  | 0 | 300000 | 300000 | 300000 | 150260.15 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1050260.15 | 0 | TRUE | TRUE
| 7.5 | Purchaser Customizations |  | 0 | 644645 | 644645 | 644645 |  | 0.05804% | 644645 | 0 | 644645 | 0 | 0 | 0% | 644645 | 0 | 0% | 644645 |  |  | 0 | 359711.91 | 92828.88 | 69621.66 | 58018.05 | 32232.25 | 32232.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 644645 | 0 | TRUE | TRUE
| 7 | RESIDENCES FIT-OUT |  | 0 | 37534645 | 101404455.83 | 102586675.33 |  | 9.237% | 102586675.33 | 1182219.5 | 102586675.33 | 68489747.58 | 68489747.58 | 66.76% | 34096927.75 | 65689147.0224 | 95.91% | 36897528.2976 |  |  |  | 14109911.91 | 11086896.5649 | 5881308.2912 | 829278.2 | 377232.25 | 377232.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4235668.8415 | 0 | 0 | 0 | 0 | 0 | 36897528.3076 | 0.01 | FALSE | TRUE
[23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8 | Residences - Furniture Package |  | 0 | 56015000 | 53828987.2 | 53828987.2 |  | 4.847% | 53828987.2 | 0 | 53828987.2 | 4525180.49 | 4525180.49 | 8.407% | 49303806.71 | 4521008.3471 | 99.91% | 49307978.8529 |  |  | 0 | 1072292.21 | 378210 | 8202932 | 7218408 | 9059761 | 12678710 | 6907530.97 | 3790134.6729 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49307978.8529 | 0 | TRUE | TRUE
[22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 19982204.03 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9 | NEW CONTRACTOR - KHANSAHEB |  | 0 | 56015000 | 194951733.75 | 194951733.75 |  | 17.55% | 194951733.75 | 0 | 194951734 | 104356336.266 | 104356336.266 | 53.53% | 90595397.484 | 84551414.399 | 81.02% | 110400319.601 |  |  | 0 | 20000000 | 20000000 | 15000000 | 15000000 | 15000000 | 18880319.601 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 6520000 | 0 | 0 | 0 | 110400319.601 | 0 | TRUE | FALSE
[22 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10 | PAYMENTS TO RPJV SUBCONTRACTORS / SUPPLIERS | [19 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10.1 | Direct Payments (RPJV Historical Debt) |  | 40269400 | 32000000 | 25000000 | 25000000 |  | 2.251% | -12269400 | 0 | 25000000 | 25000000 | 25000000 | 100% | 0 | 25000000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 10.2 | Accrued retention payable to continuing SCs |  | 13000000 | 11077300 | 24000000 | 24000000 |  | 2.161% | -1002700 | 0 | 24000000 |  |  |  | 24000000 | 0 | 0% | 24000000 | [6 empty] | 0 | 0 | 12000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12000000 | 0 | 0 | 0 | 24000000 | 0 | TRUE | TRUE
| 10.3 | Advance payment credit (direct) |  |  |  | -4000000 | -4000000 |  | -0.3602% | -4000000 | 0 | -4000000 | -4000000 | -4000000 | 100% | 0 | -4000000 |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 10.4 | Advance payment credit (PS) |  |  |  | -11600000 | -11600000 |  | -1.044% | -11600000 | 0 | -11600000 | -11600000 | -11600000 | 100% | 0 | -11600000 |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE | Moved to Hotel public
[10 empty] | 0 | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE | Moved to Hotel public
| 10 | PAYMENTS TO RPJV SUBCONTRACTORS / SUPPLIERS |  | 53269400 | 43077300 | 33400000 | 33400000 |  | 3.007% | -19869400 | 0 | 33400000 | 9400000 | 9400000 | 28.14% | 24000000 | 9400000 | 100% | 24000000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 12000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000000 | 0 | 0 | 0 | 24000000 | 0 | TRUE | TRUE
[23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | TOTAL CAPITAL WORKS |  | 730862422 | 753126225.04 | 965176930.7609 | 966359150.2609 |  | 87.01% | 235496728.2609 | 1182219.5 | 966359150.5109 | 825087860.6026 | 825087860.6026 | 85.38% | 141271289.6582 | 719420949.9865 | 87.19% | 246938200.5144 |  |  |  | 37127924.48 | 34695767.6152 | 33634480.4052 | 25338443.66 | 28037849 | 47153296.6372 | 13189800.3024 | 3790134.6729 | 0 | 0 | 0 | 0 | 0 | 4235668.8415 | 0 | 19734834.7 | 0 | 0 | 0 | 246938200.3144 | -0.2 | FALSE | FALSE
0 | bar: 2024-01-11; 2024-03-11
| D | CONTINGENCIES | bar: 2023-01-11; 2023-03-11; 2024-01-11; 2024-03-11
| 1 | CONSULTANT AND AUTHORITY FEES |  | 0 |  | 0 | 0 |  | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0% | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE | TRUE
| 2 | PRE-CONTRACT AND CAPITAL WORKS |  | 35504278.85 | 19902701 | 0.2 | 0.2 |  | 1.801e-08% | -35504278.65 | 0 | 0.2 |  |  | 0% | 0.2 |  | 0% | 0.2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.2 | FALSE | FALSE
|  | TOTAL CONTINGENCIES |  | 35504278.85 | 19902701 | 0.2 | 0.2 |  | 1.801e-08% | -35504278.65 | 0 | 0.2 | 0 | 0 | 0% | 0.2 | 0 | 0% | 0.2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | -0.2 | FALSE | FALSE
|  | TOTAL COST FOR THE PROJECT (A + B + C + D - E) |  | 856435330.85 | 879540921.85 | 1106355115.4971 | 1110624161.3471 |  | 100% | 254188830.4971 | 4269045.65 | 1110624161.5971 | 953542436.7326 | 956429882.2347 | 85.86% | 157629571.9844 | 849693273.7926 | 89.11% | 260930887.7945 |  |  |  | 40070226.1146 | 37321060.6727 | 36313095.8748 | 27676929.573 | 29424000.09 | 47792287.6972 | 14152220.3024 | 4210563.5284 | 0 | 0 | 0 | 0 | 0 | 4235668.8415 | 0 | 19734834.7 | 0 |  | 0 | 260930887.3945 | -0.4 | TRUE | TRUE
VARIANCE from 28/2 to 30/3
[5 empty] | 10280175 |  | consultant prolongation |  |  |  | 12700000 | [9 empty] | PC 43
[7 empty] | 2701 FFE |  |  |  | 8632321.46 | [9 empty] | 557747692.3966
[5 empty] | 8458000 |  | Changeover |  |  |  | 11661395
[7 empty] | Add 02? |  |  |  | 1791018
[7 empty] | Total |  |  |  | 34784734.46
0
562268700.7438
562268700.7438
65323813.0574
[12 empty] | 57607014.1276 | 65323813.0574 |  |  | -7716798.9298 | 67353984.5945 | 1.0311 | -9746970.4669
67353984.5945

## Consultat & Hard Cost
Plot -18 Payments -November 2022
| SN | Company Name | Certified | Paid |  | As per PC | Month | Paid | Total Contract | Paid
1 | 50 | Acoustic Middle East |  | 18600
2 | 1 | Al Ain Ahlia Insurance |  | 808013.48
4 | 48 | Al Turath | 80000 | 100000
5 | 63 | Amelie Maison D'Art |  | 84700
6 | 30 | BG&E | 35000 | 70000
7 | 27 | BSBG | 239665 | 272033
8 | 47 | Business Bay LLC | 152820.82 | 152820.82
9 | 84 | CEC | 81250 | 81250
10 | 20 | Conin | 37968.75 | 75937.5 |  | 2188265.63 | nov | 2217944.67 | 2340140.63 | updated
11 | 8 | Construct Branding | 202030 |  | not entered
13 | 43 | Daniel Turner |  | 57600 |  | 228600 |  | 117000
15 | 34 | Dorchester |  | 223471.0255 |  | 1379981.56 |  |  | 3110892.92 | NOT UPDATED
16 | 17 | DSGN |  | 24700 | not entered | Closed
17 | 67 | Econ QS | 10500 | 10500 |  |  |  |  | NOT UPDATED
20 | 16 | Excom | 10500 | 21000 |  |  |  |  | NOT UPDATED
| 5 | Nasser Air Travel | 27535 | 97190 |  | 1648076.5 |  | 1922496.5 | 1898076.5
| 3 | U Travel | 72510 | 177230
21 | 26 | Fondue | 24000 | 48000 |  | 180000 | Oct | 156000 | 327450
| 14 | Roya | 40000 | 80000 |  | 1180000 |  | 1140000 | 1340000
|  | Maison D’Art |  |  |  | 169400 |  | 84700 | 338800
23 | 44 | G&B |  | 331100 |  | 12032894.14 |  | 12032894.14 | 13058666.31
25 | 18 | GAJ - Hotel | 91473.84 | 91473.84
29 | 49 | Land Sterling |  | 16585
30 | 22 | Light Touch | 32660 | 54920
32 | 25 | Mediatech | 12500 | 25000
33 | 24 | Meinhardt | 13940 | 33770
34 | 21 | Mirage | 286032.39 | 579849.57
35 | 9 | Mitchell & Eades | 21000 | 204600
40 | 19 | U+A | 30000 | 60000
41 | 23 | Vortex | 11500 | 19550
42 | 31 | WME | 108000 | 216000
31 | 54 | Magnum Plus Cleaning | 5900 | 17700
43 | 51 | NSCC |  | 269239.5
44 | 33 | Khansaheb | 19804921.87 | 15491078.95
45 | 85 | Al Shafar Interiors | 441498.44 | 441498.44
46 | 52 | DEWA | 35576 | 140175.94 | [5 empty] | Tracker | not in Tracker
47 | 56 | Empower DCS | 2449 | 142995 | [5 empty] | 2560643.14 | 230153 | 2790796.14
48 | 58 | Elitser Technologies | 35415 | 35415 | [7 empty] | 2790796.14
49 | 60 | Fourth Limited | 20218 | 20218
50 | 59 | IGME Information Technology | 31758 | 31758
|  |  | 87391 | 87391
53 | 26 | Bond Interiors-RESIDENCES | 11005574.21 | 11005574.21
51 | 10 | Ian Banham - RESIDENCES | 102000
52 | 17 | Critical Path – Residences | 20000
54 | 65 | IBA - RESIDENCES |  | 102000
55 | 76 | Light Touch - RESIDENCES | 21660 | 21660
56 | 68 | GAJ | 126305.43 | 126305.43
57 | 15 | IBA |  | 82000
| 72 | Critical Path |  | 20000
|  |  | 269965.43 | 351965.43

## FF&E Payments
| Certified | Paid
HOTEL
Pre-Opening | 86400 | 82285.7143
OS&E Payment Tracker | 1171166.525 | 418758.581
CCM Fees | 112800 | 107942.8571
FF&E Payment Tracker | 10497037.9221 | 5353365.4524
IT | 87391 | 87391
| 11954795.4471 | 6049743.6048
RESI
FF&E Payment Tracker | 4510065.49 | 4510065.49
FF&E Miscellaneous | 15115 | 10942.8571
| 4525180.49 | 4521008.3471

## Bduget Breakdown
CONSULTANCY FEES - HOTEL
| Consultant Name | Description | Amt Certified | Period | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | Variations After November 2022 | Cumulative Upto Date | Final Contract Sum
Monthly Fee Consultancy Services
1 | PROJECT MANAGEMENT | Mirage | 7116501.19 | 2022-12-25 |  |  | 300000 | 300000 | 300000 | 300000 |  |  |  |  | 8316501.19
2 | DESIGN ARCHITECT - SUPERVISION | F+P | 24370930.342 | 2022-12-25 |  |  |  | 96250 | 96250 | 96250 |  |  |  |  | 24659680.342
3 | ARCHITECT OF RECORD - SUPERVISION | BSBG | 3117694 | 2022-12-25 |  |  | 215750 | 215750 | 215750 | 215750 |  |  |  |  | 3980694 | 3350580
4 | STRUCTURAL ENGINEER - SUPERVISION | BGE | 550580 | 2023-01-26 |  |  |  | 35000 | 35000 | 35000 |  |  |  |  | 655580 | 449800
5 | MEP ENGINEER - SUPERVISION | WME | 1327397.85 | 2022-12-25 |  |  | 136000 | 136000 | 136000 | 136000 |  |  |  |  | 1871397.85 | 1632000
6 | LIGHTING ENGINEER - SUPERVISION | Light Touch | 198970 | 2022-12-25 |  |  | 106856 | 54320 | 52980 | 63380 |  |  |  |  | 476506 | 291160
7 | LANDSCAPE ARCHITECT - SUPERVISION | U+A (in lie of LMS) | 240000 | 2022-12-25 |  | 30000 | 30000 | 30000 | 30000 | 30000 |  |  |  |  | 390000 | 300000
8 | INTERIOR DESIGN - SUPERVISION | G&B - Hotel | 7362361.16 | 2022-10-23 |  | 141473.64 | 141473.64 | 141473.64 | 141473.64 | 150573.64 |  |  |  |  | 8078829.36
9 | INTERIOR DESIGN - SUPERVISION | GAJ | 397704.42 | 2022-12-25 |  |  | 219560 | 225080 | 225080 | 251760 |  |  |  |  | 1319184.42 | 1125100.42
10 | QUANTITY SURVEYING | Excom | 825747.91 | 2022-12-25 |  |  | 10500 | 10500 | 10500 | 10500 |  |  |  |  | 867747.91
11 | QUANTITY SURVEYING | ECON | 35700 | 2022-12-25 |  |  | 10500 | 10500 | 10500 | 10500 |  |  |  |  | 77700
12 | PROJECT MONITOR | Conin | 2188265.63 | 2022-11-24 |  |  | 37968.75 | 37968.75 | 37968.75 | 37968.75 |  |  |  |  | 2340140.63
13 | KITCHEN AND BACK OF HOUSE | Fondue | 305450 | 2022-12-25 |  |  | 29490 | 29490 | 29490 | 29490 |  |  |  |  | 423410 | 347675
14 | HOSPITALITY ADVISORY SERVICES | Roya | 1220000 | 2022-12-25 |  |  | 40000 | 40000 | 40000 | 40000 |  |  |  |  | 1380000
15 | MEP MANAGER | IBA | 2734401.39 | 2022-09-22 |  |  | 102000 | 102000 | 102000 | 93933.33 |  |  |  |  | 3134334.72
16 | Planning consultant | Critical Path | 146480 |  |  |  | 13904 | 13904 | 13904 | 7808 |  |  |  |  | 196000
Fixed Fee Consulancy Services
17 | TRAFFIC ACCESS STUDY | ALTHURATH | 100000 | 2022-10-23 |  | 5000 | [8 empty] | 105000
18 | SIGNAGE AND WAYWARD FINDING | Brimax | 74000 | 2022-09-22 |  | 20000 | 20000 | 10000 | [6 empty] | 124000 | 50000
19 | SURVEY SERVICES, OQOOD SUBMISSION | PRD | 151110 | [5 empty] | 47080 | [5 empty] | 198190
20 | FAÇADE ENGINEERING / BMU DESIGN | Meinhardt | 119420 | 2022-12-25 |  | 20000 | 20000 | 20000 | 12220 | [5 empty] | 191640 | 116470
21 | L17 & L29 RESTAURANTS | Mitchell & Eades (L17 & L29) | 389100 | 2023-01-26 |  | 131400 | 50000 | 50000 | 50000 | 45000 |  |  |  |  | 715500
22 | IT CONSULTANT | Mediatech | 103072 | 2022-11-24 |  | 12500 | 12500 | 12500 | 12500 | 12500 |  |  |  |  | 165572 | 100800 | Exchange Rates
23 | FIRE SAFETY CONSULTANCY | Vortex | 143350 | 2022-12-25 |  | 36560 | 36560 | 36560 | 36560 | 36560 |  |  |  |  | 326150 | 182800 | GBP | 4.45
24 | FOH MEP | CEC | 700731.22 | 2022-12-25 |  | 81250 | 162500 | 162500 | [6 empty] | 1106981.22 | 325000 | EUR | 3.85
25 | Acoustic | AME | 18600 | 2022-09-22 |  | 13950 |  | 13950 | [6 empty] | 46500 |  | USD | 3.676
26 | Art Consultant | AMELIA | 1059350.6 | 2023-01-26 |  |  | 84700 |  | 84700 | [5 empty] | 1228750.6 |  |  | 1
27 | RERA Valuation | Land Sterling | 17414.25 |  |  |  | 15755.75 | [7 empty] | 33170
28 | TRAVEL COST | Various Travel Companies | 1648076.5 |  |  | 50000 | 50000 | 50000 | 50000 | 50000 |  |  |  |  | 1898076.5
29 | HOTEL OPERATOR | Dorchester | 2329040.18 | 2023-01-26 | 42460 | 42460 | 42460 | 42460 | 42460 | 345730 | 750090 |  | 207880 |  | 3845040.18
30 | ELV Consultancy | EMTEC | 33000 | 2022-12-25 |  |  | 27500 |  | 27500 | [5 empty] | 88000
31 | RECRUITMENTS | Danial Turner | 228600 | 2022-10-23 |  |  |  | 55000 |  | 55000 |  |  |  |  | 338600
32 | BRANDING CONSULTANT | Construct | 450034.0625 | 2022-10-23 |  | 237843.2262 | 237843.2262 | 237843.2262 | 237843.2262 | 237843.2262 |  |  |  |  | 1639250.1935
33 | FF&E PROCUREMNT | Furnish Hospitality Trading | 40000 | 2022-11-24 | 0 | 20000 | 0 | 0 | 0 | 0 |  |  |  |  | 60000
Marketing Payments
34 | PROCUREMENT & STOCK CONTROL PLATFORM | FOURTH | 20218 | 2022-10-23 |  | 42274 |  | 42274 |  | 42274 |  |  |  |  | 147040
35 | SERVICES | Elitser Technologies | 35415 | 2022-10-23 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 35415
36 | IT SERVICES | IGME | 83758 | 2022-11-24 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 83758
[15 empty] | 70544340.1155 | 8271385.42
37 | FF&E PROCUREMNT | Elite Document Solutions Ltd | 159899.6 | 2022-12-25
38 | GOVERNMENT FEE | Empower | 2657537 | 2023-01-26
39 | IT SERVICES | Intelity Inc. | 169096 | 2022-12-25
40 | IT SERVICES | Samsotech LLC | 81480 | 2022-12-25
41 | GOVERNMENT FEE | DEWA | 285755.52 | 2023-01-26
42 | IT SERVICES | Infrateq | 107500 | 2023-01-26
43 | CLEANING SERVICES | Magnum Plus | 41752.52 | 2022-12-25
44 | IT SERVICES | Oasys | 202505.5 | 2022-11-24
45 | DESIGN REVIEW | Salama | 340000 | 2022-11-24
|  | Spire Solutions DMCC | 164132.68 | 2022-09-22
|  | Business Bay LLC | 17657358.29 | 2022-09-22
|  | DSGN | 3851739.16 | 2022-09-22
|  | Budgeting Solutions Ltd | 38544 | 2023-01-26
|  | Key Information Technology | 56817.6 | 2023-01-26
|  | Al Suwaidi | 11000 | 2023-01-26
|  | Ayyam Gallery | 182890.5 | 2023-01-26
|  | m-hance | 3933 | 2023-01-26
|  | Salt TS | 71000 | 2023-01-26
|  | SevenRooms | 5138 | 2023-01-26
CONSULTANCY FEES - RESIDENCE
| Consultant Name | Description | Amt Certified | Period | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 |  | Cumulative Upto date | Cumulative Upto date
Monthly Fee Consultancy Services
1 | GAJ | ID supervision | 839142.581 | 2022-09-22 | 125720 | 125720 | 106720 | 106720 | 106720 | 133400 |  |  |  |  | 1544142.581
2 | Ian Banham & Associates | MEP supervision | 674066.6667 | 2022-09-22 | 102000 | 102000 | 102000 | 102000 | 102000 | 93933.33 |  |  |  |  | 1277999.9967
3 | Light Touch - RESIDENCES | Lighting | 171730 | 2022-09-22 | 21660 | 21660 | 21660 | 21660 | 20320 | 30720 |  |  |  |  | 309410
4 | Critical Path | Planning consultant | 146480 | 2022-09-22 | 20000 | 13904 | 13904 | 13904 | 7808 | [5 empty] | 216000
5 | CEC | 2701 MEP design | 50000 | 2022-09-22 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 50000
6 | STG Innovations | 2701 Images | 18166.5 | May-22 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 18166.5
7 | Gilles & Boissier | 2701 ID design | 257400 | Oct-22 | [5 empty] | 9100 |  |  |  |  | 266500
[15 empty] | 3682219.0776 | 0

## sum
Consultant Tracker
Item | Consultant | Scope of Works | Contact | Invoice by Consultant | PC Issuence | Historical Debt | Service Agreement | VOs |  |  |  | Final Contract Sum
BP-09
1 | BSBG | Lead Architect | Richard Round |  | Paid | 1159000 | 1729736 | 380444 | 35000 | 5400 | 1200000 | 3350580 | ADJ
2 | BGE | Structural | Jack Stevenson |  | Paid | 110780 | 449800 |  |  |  |  | 449800 | ADJ
3 | WME | MEP | Ammar Al Sukar |  | Paid | 448000 | 1632000 |  |  |  |  | 1632000 | adj
4 | Vortex |  | Ashhad Siddiqui |  | Paid | 24000 | 35000 | 26000 | 75000 | 40500 | 6300 | 182800 | fucking complicated small just ignored
5 | U+A (in lie of LMS) | Landscape | Brett Ross | No Invoice | Paid | 0 | 300000 |  |  |  |  | 300000
6 | Brimax | Signage & Wayfinding | Christian Berglehner |  | Paid | 74000 | 50000 |  |  |  |  | 50000 | adj
7 | Jensen Hughes / Shrimer |  | Rashid Siddig | No Invoice |  |  | 0 |  |  |  |  | 0
8 | Meinhardt | Façade | Paul Grove |  | Paid | 40320 | 116470 |  |  |  |  | 116470 | adj | 1125100.42
9 | Mediatech | ELV | Ged King | No Invoice | Paid | 40572 | 100800 |  |  |  |  | 100800 | adj
10 | CEC | MEP | Sagr Kulkarni | No Invoice |  | 554892 | 0 | 325000 |  |  |  | 325000
11 | Fondue | Kitchen Equipment | Mark Burns |  | Paid |  | 96000 |  | 156000 | 77450 | 18225 | 347675
12 | Light Touch | Lighting | Paul Miles |  | Paid | 5610 | 123160 |  | 108000 | 60000 |  | 291160
13 | salama | [8 empty] | 40000 |  | 40000
[6 empty] | 2457174 | 4632966
| Mirage |  |  |  |  | 0 | 4441242 | 2711787 |  |  |  | 7153029
AME
| GAJ | [5 empty] | 228400 | 896700.42 |  |  |  | 1125100.42
Hospitality Trading
| TOTAL | [5 empty] | 4669642
AL TURATH
EM-TEC
|  | 2022-09-22 | 2022-10-23 | 2022-11-24 | 2022-12-25 | 2023-01-26
1 | BSBG | 2454736 | 2706194 | 2911944 | 3117694 |  | 3117694 | 2022-12-25
2 | BGE | 305580 | 375580 | 463080 | 498080 | 550580 | 550580 | 2023-01-26
3 | WME | 950064.52 | 1058064.52 | 1166064.52 | 1327397.85 |  | 1327397.85 | 2022-12-25
4 | Light Touch | 94650 | 127310 | 159970 | 198970 |  | 198970 | 2022-12-25
5 | Meinhardt | 84750 | 98510 | 113620 | 119420 |  | 119420 | 2022-12-25
6 | Mediatech | 78072 | 90572 | 103072 |  |  | 103072 | 2022-11-24
7 | Vortex | 51275 | 62775 | 88775 | 143350 |  | 143350 | 2022-12-25
8 | U+A (in lie of LMS) | 150000 | 180000 | 210000 | 240000 |  | 240000 | 2022-12-25
9 | Brimax | 74000 |  |  |  |  | 74000 | 2022-09-22
10 | Construct | 248004.0625 | 450034.0625 |  |  |  | 450034.0625 | 2022-10-23
11 | Fondue | 156000 | 180000 | 272600 | 305450 |  | 305450 | 2022-12-25
[7 empty] | 0 | #N/A
12 | Mirage | 6261284.45 | 6547316.84 | 6850932.51 | 7116501.19 |  | 7116501.19 | 2022-12-25
13 | IBA | 2734401.39 | Discontinued |  |  |  | 2734401.39 | 2022-09-22
14 | Conin | 2112328.13 | 2150296.88 | 2188265.63 |  |  | 2188265.63 | 2022-11-24
15 | Excom | 794247.91 | 804747.91 | 815247.91 | 825747.91 |  | 825747.91 | 2022-12-25
16 | ECON | 4200 | 14700 | 25200 | 35700 |  | 35700 | 2022-12-25
17 | CEC | 456981.22 | 538231.22 | 538231.22 | 700731.22 |  | 700731.22 | 2022-12-25
18 | Salama | 300000 | 300000 | 340000 |  |  | 340000 | 2022-11-24
19 | Roya | 1100000 | 1140000 | 1180000 | 1220000 |  | 1220000 | 2022-12-25
20 | GAJ | 105606 | 197080.42 | 297925.13 | 397704.42 |  | 397704.42 | 2022-12-25
21 | Dorchester | 1561988.12 | 1594892.92 | 1715466.11 | 2004716.11 | 2329040.18 | 2329040.18 | 2023-01-26
22 | Spire Solutions DMCC | 164132.68 |  |  |  |  | 164132.68 | 2022-09-22 | Spire Solutions Oct (215,510.92) and Nov (262,564.11) removed, no PC found
23 | Business Bay LLC | 17657358.29 |  |  |  |  | 17657358.29 | 2022-09-22 | Business Bay Oct (52,174.85) and Nov (52,174.85) removed, no PC found
24 | DSGN | 3851739.16 | Discontinued |  |  |  | 3851739.16 | 2022-09-22
25 | Mitchell & Eades (L17 & L29) | 254600 | 275600 | 338400 | 372600 | 389100 | 389100 | 2023-01-26
26 | Mitchell & Eades (Musa Café) | 0 | 33000 |  |  |  | 33000 | 2022-10-23
27 | Magnum Plus | 23600 | 29952.52 | 35852.52 | 41752.52 |  | 41752.52 | 2022-12-25
28 | ALTHURATH | 20000 | 100000 |  |  |  | 100000 | 2022-10-23
29 | G&B - Hotel | 7212211.16 | 7362361.16 |  |  |  | 7362361.16 | 2022-10-23
30 | F+P | 24037180.342 | 24148430.342 | 24259680.342 | 24370930.342 |  | 24370930.342 | 2022-12-25
31 | EMTEC |  |  |  | 33000 |  | 33000 | 2022-12-25
32 | AME | 18600 |  |  |  |  | 18600 | 2022-09-22
33 | AMELIA | 84700 | 169400 |  |  | 1059350.6 | 1059350.6 | 2023-01-26
[7 empty] | 0 | #N/A
34 | Empower | 1917786 | 2060781 | 2147939 | 2656236 | 2657537 | 2657537 | 2023-01-26
35 | DEWA | 109829.94 | 191207.8429 | 191207.8429 | 241013.44 | 285755.52 | 285755.52 | 2023-01-26
[7 empty] | 0 | #N/A
36 | Elitser Technologies |  | 35415 |  |  |  | 35415 | 2022-10-23
37 | Furnish Hospitality Trading |  | 20000 | 40000 |  |  | 40000 | 2022-11-24
[7 empty] | 0 | #N/A
38 | Danial Turner | 54000 | 228600 |  |  |  | 228600 | 2022-10-23
39 | IGME |  | 31758 | 83758 |  |  | 83758 | 2022-11-24
40 | FOURTH |  | 20218 |  |  |  | 20218 | 2022-10-23
41 | Infrateq |  |  | 84000 |  | 107500 | 107500 | 2023-01-26
42 | Oasys |  |  | 202505.5 |  |  | 202505.5 | 2022-11-24
[7 empty] | 0 | #N/A
43 | Elite Document Solutions Ltd |  |  |  | 159899.6 |  | 159899.6 | 2022-12-25
44 | Intelity Inc. |  |  |  | 169096 |  | 169096 | 2022-12-25
45 | Samsotech LLC |  |  |  | 81480 |  | 81480 | 2022-12-25
46 | Budgeting Solutions Ltd |  |  |  |  | 38544 | 38544 | 2023-01-26
47 | Key Information Technology |  |  |  |  | 56817.6 | 56817.6 | 2023-01-26
48 | Al Suwaidi |  |  |  |  | 11000 | 11000 | 2023-01-26
49 | Ayyam Gallery |  |  |  |  | 182890.5 | 182890.5 | 2023-01-26
50 | m-hance |  |  |  |  | 3933 | 3933 | 2023-01-26
51 | Salt TS |  |  |  |  | 71000 | 71000 | 2023-01-26
52 | SevenRooms |  |  |  |  | 5138 | 5138 | 2023-01-26
[7 empty] | 0 | #N/A
| BSBG | 1159000
| BGE | 110780
| WME | 448000
| Vortex | 24000
| U+A (in lie of LMS) | 0
| Brimax | 74000
Jensen Hughes / Shrimer
| Meinhardt | 40320
| Mediatech | 40572
| CEC | 554892
Fondue
| Light Touch | 5600
2457164
Formulas:
VOs = LOOKUP([Service Agreement],[Scope of Works]:[Historical Debt],D31:H31)

## Sheet1
Mirage Leisure and Developments
Currency | AED
Original Contract Amount | 4441242
Payment for the Extended Period | 2711787
Variations approved to Date | 0
Current Final Contract Value | 7153029
Foster + Partners Ltd.
Currency | GBP
Original Contract Value | 4620000
Variations Approved to Date | 271613.56
LPO ref Plot-18/1989/2020 | 180000
LPO ref Plot-18/2247/2021 | 126000 |  |  |  |  | 1125100.42
LPO ref Plot-18/2621/2021 | 84000
LPO ref Plot-18/2779/2021 | 45000
LPO ref Plot-18/2968/2022 | 45000
LPO ref Plot-18/3307/2022 | 30000
LPO ref Plot-18/3397/2022 | 45000
LPO ref Plot-18/3534/2022 | 30000
Total Agreed Value | 5476613.56
|  |  |  | 4441242 | 2711787
Brewer Smith & Brewer Gulf
Currency | AED |  | 0 | 228400 | 896700.42
Original Contract Value | 3228067
Variations approved to Date | 0 |  |  | 4669642
Current Final Contract Value | 3228067
BGE International Consulting Engineers
Currency | AED
Outstanding Amount | 110780
New Agreement | 414800
Estimated Contract Value | 525580
WME Engineering Consultants
Currency | AED
Contract Amount | 1632000
Variations | 0
Estimated Contract Value | 1632000
Light Touch PLD LLC
Currency | AED
New Contract Amount | 123160
Settlement Payment | 5610
Variations Agreed | 96520
Estimated Contract Value | 225290
U Plus A FZ LLC
Currency | AED
Original Contract Value | 300000
Variations approved to Date | 0
Current Final Contract Value | 300000
Gilles & Boissier SARL
Currency | Euro | Spire Solutions DMCC | 164132.68
Original Contract Value | 1580000 | Business Bay LLC | 17657358.29
|  | DSGN Architectural Prospective Drawing Services | 3851739.16
Variations approved to Date | 358789.54
Current Final Contract Value | 1938789.54
Godwin Austen Johnson (Dubai Branch)
Currency | AED
LPO ref Proj/PLOT18/3324/2022 | 228400
LPO ref Proj/PLOT18/3647/2022 | 896700.41
Current Final Value | 1125100.41
EXCOM Project Development Consultants
Currency | AED
LPO ref Plot-18/1294/2018 | 66000
LPO ref Plot-18/1380/2019 | 90000
LPO ref Plot-18/1439/2019 | 72000
LPO ref Plot-18/1575/2019 | 90000
LPO ref Plot-18/1926/2020 | 79686.83
LPO ref Plot-18/2105/2020 | 100999.8
LPO ref Plot-18/2465/2021 | 252561.28
LPO ref Plot-18/3165/2022 | 95500
Current Final Contract Value | 846747.91
ECON Project Development Consultant
Currency | AED
Original Contract Value | 77700
Variations approved to Date | 0
Current Final Contract Value | 77700
Incorporated Consultant (Conin)
Currency | AED
Original Contract Value | 1350000
Variations approved to Date | 1084218.75
Current Final Contract Value | 2434218.75
Fondue Consultants
Currency | AED
Contract Amount | 96000
Variations approved to Date | 233450
Current Final Contract Value | 329450
Roya International Hospitality & Leisure Consultants LLC
Currency | AED
Original Contract Value | 1220000
Variations approved to Date | 0
Current Final Contract Value | 1220000
Ian Banham & Associates
Currency | AED
LPO ref Plot-18/1400/2019 | 180000
LPO ref Plot-18/1500/2019 | 492000
LPO ref Plot-18/1788/2020 | 492000
LPO ref Plot-18/1924/2020 | 228000
LPO ref Plot-18/2453/2021 | 472612.89
LPO ref Plot-18/2920/2021 | 115200
LPO ref Plot-18/3031/2022 | 396974
LPO ref Plot-18/3164/2022 | 150000
LPO ref Plot-18/3318/2022 | 207614.5
Variations approved to Date | 0
Current Final Contract Value | 2734401.39
Al Turath Engineering Consultants
Currency | AED
Original Contract Value | 25000
LPO ref Proj/PLOT18/3467/2022 | 80000
Variations approved to Date | 0
Current Final Contract Value | 105000
Meinhardt Façade Technology
Currency | AED
Settlement Payment | 40320
New Agreement | 116470
Estimated Contract Value | 156790
Mitchell & Eades PTY Ltd
Currency | AED
LPO ref. PROJ/PLOT18/3266/2022 | 386000
LPO ref. PROJ/PLOT18/3645/2022 | 13200
Adjustments | 0
Agreed total Value | 399200
Mediatech FZ LLC
Currency | AED
Contract Amount | 140572
Variations | 0
Estimated Contract Value | 140572
Vortex Fire Safety Consultancy LLC
Currency | AED
Outstanding Amount | 24000
Fee for the Remaining Services | 35000
Variations | 147500
Current Final Contract Value | 206500
Consistent Engineering Consultants
Currency | AED
Residual Payment | 456981.22
New Agreement | 325000
Estimated Contract Value | 781981.22
Acoustics Middle East & Technical Services FZE
Currency | AED
Original Contract Value | 46500
Variations approved to Date | 0
Current Final Contract Value | 46500
Amelie, Maison d'art
Currency | Euro
Contract Amount | 88000
Variations | 0
Estimated Contract Value | 88000
Dorchester Services Ltd
Original Contract Value: | Fee US$ 550,000+ Expenses
Variations Approved to Date: | 0
AdjustedContract Value: | Fee US$ 550,000+ Expenses
EM-TEC FZ LLC
Currency | AED
LPO ref Proj/PLOT18/3503/2022 | 55000
Current Final Value | 55000
Daniel Turner Search Ltd
Currency | AED
LPO ref Plot-18/3048/2022 | 54000
LPO ref Plot-18/3049/2022 | 117000
LPO ref Plot-18/3486/2022 | 57600
Total | 228600
CONSTRUCT
Currency | GBP
Original Contract Amount | 368370.83
Current Final Contract Value | 368370.83
Furnish Hospitality General Trading LLC
Currency | AED
LPO Ref: PROJ/PLOT18/3410/2022 | 40000
Current Final Value | 40000
Fourth Limited
Currency | USD
Original Contract Value | 40000
Variations approved to Date | 0
Current Final Contract Value | 40000
Elitser Technologies LLC
Currency | AED
Original Contract Value | 35415
Variations approved to Date | 0
Current Final Contract Value | 35415
IGME Information Technoloy
Currency | AED
LPO ref: PROJ/PLOT18/3435/2022 | 31758
LPO ref: PROJ/PLOT18/3434/2022 | 52000
Total Agreed Value | 83758