## IPA
| EMPLOYER |  | : | SKY PALACES REAL ESTATE DEVELOPMENT LLC
| EMPLOYER'S REPRESENTATIVE |  | : | OMNIYAT CONCEPT INVESTMENTS LLC
| ENGINEER |  | : | BREWER SMITH BREWER GULF ( BSBG )
| MAIN CONTRACTOR |  | : | KHANSAHEB CIVIL ENGINEERING - CONSTRUCTION DIVISION
| PROJECT |  | : | DORCHESTER HOTEL AND RESIDENCES
| KHANSAHEB JOB REF. NO. |  | : | 201A22002
| APPLICATION FOR PAYMENT NO. 13 | [6 empty] | FOR THE PERIOD ENDING: 28TH FEBRUARY 2023
|  | Description |  | Original Contract Value Amount (AED) | Previous (AED) | This (AED) | Cumulative (AED)
|  | Total Value of Workdone |  | 194951734.5 | 170828486.4092 | 24527852.5664 | 195356338.9756
|  |  |  | 0 | 0 | 0 | 0
|  | Total |  | 194951734.5 | 170828486.4092 | 24527852.5664 | 195356338.9756
SUMMARY
| (i) | Total Value of Workdone |  |  |  |  | 195356338.9756 |  |  | 56294044.2448 | -139062294.7308
|  | Sub Total 01 |  |  |  |  | 195356338.9756
0
| (ii) | Add Mobilisation Payment 01 & 02 |  |  |  |  | 12000000
|  | Sub Total 2 |  |  |  |  | 207356338.9756 |  |  | 68294044.2448 | -139062294.7308
| (iii) | Less Retention @ 10% on Provisional Sums & MEP (Except prelims & OHP ) |  |  |  |  | -9093109.6871 |  | KCE retention | 50558846.001 | -5055884.6001
| (iv) | Less Amount Certified Previously |  |  |  |  | -169665945.7183 |  | KMEP retention | 40372250.87 | -4037225.087
[10 empty] | 90931096.871 | -9093109.6871
| (v) | Amount due for Payment |  |  |  |  | 28597283.5702
207356338.9756
-3191697.0765
-397333
07.03.23
| Signature | [5 empty] | Date
Note: |  | Mobilisation payments (AED 12 million) to be recovered from subsequent payments as LOA clause 30. | [7 empty] | -448628.7596
203318680.1396
130255895.9809
-73062784.1586
86791925.909
-120564413.0666

## Summary
APPLICATION FOR PAYMENT - SUMMARY
| PROJECT | DORCHESTER HOTEL AND RESIDENCES | [5 empty] | FOR THE PERIOD ENDING: 28TH FEBRUARY 2023
| EMPLOYER | SKY PALACES REAL ESTATE DEVELOPMENT LLC
| EMPLOYER'S REPRESENTATIVE | OMNIYAT CONCEPT INVESTMENTS LLC
| ENGINEER | BREWER SMITH BREWER GULF ( BSBG )
| MAIN CONTRACTOR | KHANSAHEB CIVIL ENGINEERING - CONSTRUCTION DIVISION
| CONTRACT NO. | 201A22002
| Item | Contract Amount | Percentage Complete |  |  | Value Complete |  |  |  | 461823.5938
|  |  | Previous Certificate | This Month | To Date | Previous Valuation | This Month | To Date |  |  |  | Total Certified |  | Variance
| Main Contract Value | 194951734.5 | [6 empty] | 6053836.2575 | 1013274.3962
1 | Civil Works
1.1 | Contract Cost - Direct Work |  |  |  |  | 102597474.4943 | 16039406.7427 | 118636881.237 | 48430690.06 | 8106195.17 |  | 56536885.23 |  | -62099996.007
1.2 | Cost Adjustments |  |  |  |  | -131070.889 | -19197 | -150267.889 | -1208 |  |  |  |  | 150267.889
1.3 | Main Contractor OH & Profit (12.5%) |  |  |  |  | 11976467.9937 | 1870322.8968 | 13846790.8905 | 6445740.61 |  |  | 6445740.61 |  | -7401050.2805
( Exc. KID Value )
| Sub Total 1 |  |  |  |  | 114442871.5989 | 17890532.6395 | 132333404.2384 |  |  |  | 62982625.84 | 0 | -69350778.3984
2 | Provisional Sums (excl MEP)
2.1 | Subcontract Cost
2.2 | Main Contractor OH & Profit (12.5%)
| Sub Total 2 |  |  |  |  | 0 | 0 | 0
3 | MEP Works
3.1 | Subcontract Cost (incl KMEP oh&p of 12.5%) |  |  |  |  | 51259649.8275 | 6033927.2062 | 57293577.0337 | 50927624.03 |  | Correction: Apply retention only on KMEP SC works | 30299794.5825 |  | -26993782.4512
3.2 | Main Contractor OH & Profit on MEP (10%) |  |  |  |  | 5125964.9828 | 603392.7206 | 5729357.7034 | 5208507.0031 |  |  | 2797241.92 |  | -2932115.7834
| Sub Total 3 |  |  |  |  | 56385614.8103 | 6637319.9269 | 63022934.7371 |  |  |  | 33097036.5025 | 0 | -29925898.2346
|  | 194951734.5 |  |  |  | 170828486.4092 | 24527852.5664 | 195356338.9756 |  |  |  | 96079662.3425 |  | -99276676.6331
175930458.2707
85904689.09
8106195.17
96079662.3497
0.0072381

## Pre Cert
APPLICATION FOR PAYMENT NO. 13
PREVIOUSLY CERTIFIED AMOUNTS
Certificate No. | Description | Certified Amount (AED)
1 | Payment Certificate 01 | 6000000
2 | Payment Certificate 02 | 6000000
3 | Payment Certificate 03 | 2104452.12
4 | Payment Certificate 04 | 11118319.2
5 | Payment Certificate 05 | 11047382.21
6 | Payment Certificate 06 | 12807977.89
7 | Payment Certificate 07 | 19982204.03
8 | Payment Certificate 08 | 15491078.95
9 | Payment Certificate 09 | 19804921.87
10 | Payment Certificate 10 | 21126467.6392
11 | Payment Certificate 11 | 19971554.879
12 | Payment Certificate 12 | 24211586.93
13
14
15
16
17
18
19
20
21
22
| TOTAL AMOUNT | 169665945.7183

## Cover
201A22002 - DORCHESTER HOTEL AND RESIDENCES
CONTRACTOR
KHANSAHEB CIVIL ENGINEERING L.L.C.
APPLICATION FOR PAYMENT NO. 13
201A22002 - DORCHESTER HOTEL AND RESIDENCES
APPLICATION FOR PAYMENT NO. 13
| Section 1 | Certificate / Summary
| Section 2 | Cost breakdown Summary
| Section 3 | Labour Cost & Backup
| Section 4 | Material Cost & Backup
| Section 5 | Plant Cost & Backup
| Section 6 | Subcontractor Cost & Backup
| Section 7 | Prelim & General Cost & Backup
| Section 8 | Salary Cost & Backup
| Section 9 | Committed Orders
| Section 10 | MEP Payment Application
| Section 11 | Cost Adjustments
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 1
Certificate / Summary
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 2
Cost breakdown Summary
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 3
Labour Cost & Backup
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 4
Material Cost & Backup
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 5
Plant Cost & Backup
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 6
Subcontractor Cost & Backup
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 7
Prelim & General Cost & Backup
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 8
Salary Cost & Backup
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 9
Committed Orders
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 10
MEP Payment Application
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 11
Cost Adjustments

## SC Summary
SUBCONTRACTOR PAYMENT APPLICATION (CIVIL WORKS) - SUMMARY
PROJECT : DORCHESTER HOTEL AND RESIDENCES | [6 empty] | 2023-02-28
EMPLOYER : SKY PALACES REAL ESTATE DEVELOPMENT LLC
MAIN CONTRACTOR : KHANSAHEB CIVIL ENGINEERING - CONSTRUCTION DIVISION
CONTRACT NO : 201A22002
Sl No | Item | Scope of work | Work Approval Amount | Work Approval Reference | Value Complete |  |  | WD inc. Ad R. | Recovery | Advance P |  | Certified- Jan 23 |  | Variance in certifications
[5 empty] | Previous Valuation | This Month | To Date
| Subcontractors ( PS ) | [6 empty] | 0 |  | 0
1 | Watermaster Technical Services LLC | Swimming Pool & Water Feature works | 2128651 |  | 1650462.71 | 195138.99 | 1845601.7 | 1845601.7 |  |  | 0 | 1604579.94 |  | -241021.76
2 | Arcadia Metal Industries | External Metal works | 3330440 |  | 5079695.46 | 804588.71 | 5884284.17 | 5884284.17 | 499566 | 499566 | 0 | 4776873.4 |  | -1107410.77
3 | Dar Al Rokham LLC | Internal Stone works | 4111821 |  | 4520429.78 | 91096.64 | 4611526.42 | 4611526.42 |  | 0 | 0 | 3650150.6857 |  | -961375.7343
4 | Al Shirawi Contracting Co LLC | Waterproofing works | 1391469 |  | 820138 | 130693 | 950831 | 950831 |  |  | 0 | 745737 |  | -205094
5 | Alshafar Interiors Co LLC | Joinery to Guest Rooms | 5919164.28 |  | 3775358.4645 | 503018.3975 | 4278376.862 | 4114778.56 | 724276.448 | 887874.75 | 163598.302 | 3714462.4673 |  | -563914.3947
6 | Isam Kabbani & Partners | Guniting & Waterproofing works | 1155933 |  | 440809.82 | 0 | 440809.82 | 440809.82 |  |  | 0 | 435538.7332 |  | -5271.0868
7 | Fiona Environs UAE | Soft Landscaping & Irrigation works | 3313028.6 |  | 2293957.75 | 1330561.877 | 3624519.627 | 3545356.71 | 83043.883 | 162206.8 | 79162.917 | 2027557.55 |  | -1596962.077
8 | Al Reem Marble & Granite LLC | External Stoneworks | 4556481 |  | 4266533.93 | 486912.826 | 4753446.756 | 4483411.93 | 73109.324 | 343144.15 | 270034.826 | 4188087.0406 |  | -565359.7154
9 | Joyz Overseas Technical Services LLC | EIFS works | 1538156.94 |  | 1496789.264 | 7772.562 | 1504561.826 | 1499965.426 | 149219.29 | 153815.69 | 4596.4 | 1305109.3472 |  | -199452.4788
10 | Bond Interiors Design LLC | Fitout of Hotel Lobby, All Day Dining & Spa Works | 4325954.46 |  | 2874494.52 | 333825.33 | 3208319.85 | 3208319.85 |  |  | 0 | 2792023.53 |  | -416296.32
11 | Al Rawda General Maint. & Decoration Co LLC | Partition & Ceiling works | 1954843 |  | 3462423.68 | 693038.08 | 4155461.76 | 4155461.76 |  |  |  | 3134189.6889 |  | -1021272.0711
12 | Joseph Advertisers LLC | Signage works | 999150 |  | 199830 | 0 | 199830 | 0 |  | 199830 | 199830 | 199830 |  | 0
13 | Joseph Decorative Glass | Internal Glazing works | 1262387 |  | 735873.824 | 22955.528 | 758829.352 | 632939.94 | 126587.988 | 252477.4 | 125889.412 | 636429.304 |  | -122400.048
14 | Walltracts | Wall Coverings | 712173.7 |  | 689333.335 | 0 | 689333.335 | 406956.395 | 0 | 282376.94 | 282376.94 | 689333.34 |  | 0.005
15 | Goodrich Global Trading LLC | Carpets to Guest Rooms | 839675.05 |  | 617321.71 | 87720.72 | 705042.43 | 705042.43 |  |  |  | 555878.32 |  | -149164.11
16 | Arabian Profile Company Ltd | GRC Works | 4155655 |  | 1444023 | 460067 | 1904090 | 1904090 |  |  |  | 1444023 |  | -460067
17 | Glass Line Aluminium LLC | Aluminium & Glazing Façade works | 10273402 |  | 6919274.23 | 634874.53 | 7554148.76 | 7554148.76 |  |  |  | 5456646.61 |  | -2097502.15
18 | EW COX Middle East LLC | BMU System | 628861 |  | 204605.8 | 0 | 204605.8 | 204605.8 |  |  |  | 204605.8 |  | 0
19 | Mohammed Tayyeb Khoory & Sons | Garbage & Linen Chutes | 287122 |  | 163261.6 | 0 | 163261.6 | 163261.6 |  |  |  | 140609.4 |  | -22652.2
20 | HTS Carpets Trading LLC | Carpets to lift lobbies & Corridors | 356512.42 |  |  | 261442.45 | 261442.45 | 261442.45 |  |  |  | 0 |  | -261442.45
21 | Khansaheb Interior DIvision ( KID ) | Restaurant Works |  |  | 6654659.656 | 1057626.568 | 7712286.224 | 3986011.28 | 797202.256 | 4523477.2 | 3726274.944 | 6349499.176 |  | -1362787.048
| Subcontractors ( PS ) |  |  |  | 48309276.5335 | 7101333.2085 | 55410609.742 | 50558846.001 | 2453005.189 | 7304768.93 | 4851763.741 | 44051164.3328 | 0 | -11359445.4092
| Subcontractors (Domestic) | [8 empty] | 2781291.73
1 | Blue Sky LLC | Supply of MEP Maintenance team | 1071950 | P-006 | 826548.52 | 45004.56 | 871553.08 |  |  |  |  | 814292.99 |  | -57260.09
2 | Data Link Technical Services LLC | Wild Air Partitions | 241882.91 | C-006 | 485569.89 | 29036.11 | 514606 |  |  |  |  | 485569.8915 |  | -29036.1085
3 | Al Rawda General Maint. & Decoration Co LLC | Ceiling & Partition repairs, painting works | 26960 | P-001 | 45698.1 | 0 | 45698.1 |  |  |  |  | 45448 |  | -250.1
4 | Firestop Middle East | Firestopping works | 441760 | C-001, 002 R1 | 227246.63 | 51791.03 | 279037.66 |  |  |  |  | 224645.3306 |  | -54392.3294
5 | Creative House Scaffolding | Scaffolding | 1931942.08 | C-01 & 02 | 2808527.48 | 134602.08 | 2943129.56 |  |  |  |  | 2732404.4054 |  | -210725.1546
6 | Corecut Engineering LLC | Coring & Scanning | 383133 | C-015, 016 | 542776.45 | 52304 | 595080.45 |  |  |  |  | 477692.45 |  | -117388
7 | Inventure Façade Contracting LLC | Glass Balustrade works | 2703097 | C-011 | 2198186.87 | 209794.85 | 2407981.72 |  |  |  |  | 2132695.105 |  | -275286.615
8 | TWIC Insulation Materials Supply LLC | Epoxy Coating & Dust Sealer works | 778544.8 | C-015, 16 R1 | 428574.99 | 124804.39 | 553379.38 |  |  |  |  | 419173.1468 |  | -134206.2332
9 | Al Maraya Marble & Granite Factory LLC | Tile Installation | 514481.6 | C-017 | 257226.99 | 0 | 257226.99 |  |  |  |  | 250361.08 |  | -6865.91
10 | German Concrete Works & Building Contracting LLC | Screed & Insulation works | 796114.2 | C-018 R1 | 660995.32 | 121688.89 | 782684.21 |  |  |  |  | 620302.5396 |  | -162381.6704
11 | Greenwood General Trading LLC | Wooden Flooring | 353975.01 | C-005 | 285597.82 | 30400 | 315997.82 |  |  |  |  | 285597.815 |  | -30400.005
12 | Al Hayat Fiberglass Ind LLC | GRP Lining works | 313333.4 | C-027 | 131172 | 0 | 131172 |  |  |  |  | 131172 |  | 0
13 | Vulcan Industries LLC | Steel Doors | 685405 | C-032 | 200380.69 | 0 | 200380.69 |  |  |  |  | 194166.7524 |  | -6213.9376
14 | Polaris International Industries LLC | Timber Doors | 1008983.76 | C-029 | 797551.2928 | 86784.8172 | 884336.11 |  |  |  |  | 722946.6695 |  | -161389.4405
15 | Center Core Professional Technical Services LLC | Slab cutting & strengthening works | 88900 | C-033 | 88900 | 0 | 88900 |  |  |  |  | 88900 |  | 0
16 | Weserve Technical Services LLC | Miscellaneous Steel works | 1147041.3 | C-052 | 631288.2 | 291765.33 | 923053.53 |  |  |  |  | 631288.2 |  | -291765.33
17 | Venus Engineering LLC | RC column removal & strengthening works | 110965 | C-039 | 244465 | 170885.4 | 415350.4 |  |  |  |  | 396452.15 |  | -18898.25
18 | Global Composites Solutions LLC | GRP Cladding to Planter Wall | 225683 | C-053 | 45136.6 | 0 | 45136.6 |  |  |  |  | 45136.6 |  | 0
19 | Indiga Tech Trading LLC | Steel Doors | 154496.05 | C-047 | 77105.922 | 92383.178 | 169489.1 |  |  |  |  | 76532.8402 |  | -92956.2598
20 | Monrac LLC | Ceiling & Partition repairs, painting works | 918183.61 | PS-021 | 880323.37 | 86619.68 | 966943.05 |  |  |  |  | 880323.368 |  | -86619.682
21 | Hygenic Solutions LLC | MMA Flooring | 474794 | C-016 | 274196.05 | 75401.5 | 349597.55 |  |  |  |  | 274195.05 |  | -75402.5
22 | Technical Access Services (L.L.C.) | Scaffolding Works | 1580356.14 | C-065 | 1396036.15 | 302628.25 | 1698664.4 |  |  |  |  | 1346549.53 |  | -352114.87
23 | Progress Fabrication | Metal Cladding Works and Misc Metal Works | 1264100.14 | C-078 | 432387.85 | 641731.13 | 1074118.98 |  |  |  |  | 503360.2939 |  | -570758.6861
24 | Ferco Shutters LLC | Fire Curtains | 33685 | P-027 | 26948 | 0 | 26948 |  |  |  |  | 24590.05 |  | -2357.95
25 | Jeel Alfan Technical Services | Decorative Paint | 128266 | P-015 | 32066.5 | 0 | 32066.5 |  |  |  |  | 32066.5 |  | 0
26 | Technoserve Technical works LLC | Painting works | 73379.6 | P-012 | 28045.136 | 12054.512 | 40099.648 |  |  |  |  | 27980.7406 |  | -12118.9074
27 | Dormakaba Middle East | Movable Partition Works- AHK Balance | 366250 | PS-025 | 314975 | 0 | 314975 | 205100 |  | 109875 |  | 314975 |  | 0
28 | Khansaheb Joinery DIvision ( KJD ) | Joinery Works- AHK Balance | 2105729.87 | PS-023 | 946285.19 | 663218.464 | 1609503.654 | 1188357.684 |  | 421145.97 |  | 917426.9245 |  | -692076.7295
29 | Al Burhani General Trading LLC | Wooden Flooring & Carpet works- AHK | 133457 | PS-032 | 127949.2 | 6425.45 | 134374.65 | 81372.15 |  | 53002.5 |  | 123336.8617 |  | -11037.7883
30 | Rattan House Factory for Furniture and Decoration | Res Lobbies, Joinery works- AHK Balance | 279759 | PS-044 | 153597.4 | 32059.28 | 185656.68 | 185656.68 |  |  |  | 150072.32 |  | -35584.36
31 | International Foundation Group LLC | Waterproofing Concrete works | 450000 | C-061 R4 | 450000 | 0 | 450000 |  |  |  |  | 450000 |  | 0
32 | X-Calibur Emirates LLC | Stair nosing works | 221889 | C-064 | 173913 | 0 | 173913 |  |  |  |  | 173913 |  | 0
33 | Master Rubber Manufacturing | Wall & Corner Guard works | 169068.5 | C-062 | 50720.55 | 0 | 50720.55 |  |  |  |  | 50720.55 |  | 0
34 | DNK Engineering Equipment Trading LLC | Rolling Shutter works | 75530 | C-026 | 60817 | 29163 | 89980 |  |  |  |  | 60817 |  | -29163
35 | Vijayraj Contracting Co LLC | Plastering works | 206250 | C-019 | 181750.15 | 29649.95 | 211400.1 |  |  |  |  | 181750.15 |  | -29649.95
36 | Doormax Building Material Trading LLC | Glass Door works | 128000 | C-090 | 89600 | 12000 | 101600 |  |  |  |  | 99200 |  | -2400
37 | KTC International Cont LLC | RTA works | 1043942 | C-091 | 208788.4 | 84150 | 292938.4 |  |  |  |  | 208788.4 |  | -84150
38 | Urban Science Building Contracting LLC | Joinery- Cupboards | 533125 | C-097 | 106625 | 0 | 106625 |  |  |  |  | 106625 |  | 0
39 | Berkeley | Final Cleaning | 993456 | C-067 | 16070 | 13400 | 29470 |  |  |  |  | 16070 |  | -13400
40 | Elite Skills Technical Services LLC | Steel Door Repainting Works | 75430 | C-087 | 55860 | 95456 | 151316 |  |  |  |  | 50274 |  | -101042
| Subcontractors (Domestic) |  |  |  | 16989902.7108 | 3525201.8512 | 20515104.562 |  |  |  |  | 16767812.7048 |  | -3747291.8572
| Subcontractors (Domestic & PS ) |  |  |  | 65299179.2443 | 10626535.0597 | 75925714.304 |  |  |  |  | 60818977.0376 |  | -15106737.2664
Subcontractors ( Labour Only )
1 | Al Qannati Electromechanical LLC | Labour Supply ( Block Works ) |  |  | 972720 | 11400 | 984120 |  |  |  |  | 972720 |  | -11400
2 | Focus Power Security Services LLC | Supply of Site Security Service | 252000 | P-004 | 207516.12 | 24500 | 232016.12 |  |  |  |  | 207516.12 |  | -24500
3 | Service plus Technical Services LLC | Cleaning Service | 162400 | P-005 | 130187.96 | 16800 | 146987.96 |  |  |  |  | 130187.96 |  | -16800
4 | Pinewood StarTechnical Services LLC | Labour Supply ( ASI Recovery ) | 74400 |  |  | 23944 | 23944
| Subcontractors (Labour Only) |  |  |  | 1310424.08 | 76644 | 1387068.08 |  |  |  |  | 1310424.08 |  | -52700
[7 empty] | 77312782.384 |  |  |  |  | 62129401.1176

## Staff Cost
FOR THE PERIOD ENDING: 28TH FEBRUARY 2023
SALARY COST & BACKUPS
Certificate No. | Description | Applied Amount (AED)
1 | 2022-03-01 | 16639.13 | 16639.13 | 0
2 | 2022-04-01 | 438092.619 | 438092.619 | 0
3 | 2022-05-01 | 772560.2273 | 772560.2273 | 0
4 | 2022-06-01 | 991945.4545 | 981763.6364 | -10181.8182
5 | July-22 | 1042220 | 1030430.5263 | -11789.4737
6 | August-22 | 1160798.7391 | 1137101.7391 | -23697
7 | September-22 | 1257377 | 1228858.1818 | -28518.8182
8 | October-22 | 1266237 | 1236938.0952 | -29298.9048
9 | November-22 | 1303682.27
10 | December-22 | 1299435.18
11 | January-23 | 1372949.59
12 | February-23 | 1403820.5
13
14
15
16
17
18
19
| TOTAL AMOUNT | 12325757.71 | 6842384.1552 | -103486.0148

## Cost Adust't
FOR THE PERIOD ENDING: 28TH FEBRUARY 2023
Cost Adjustments
Certificate No. | Description | Applied Amount (AED)
1 | Petty Cash Gifts to Arjun | -1208
2 | TXM Manpower cost adjustment from material transaction- August 22 | -9071.54
3 | TXM Manpower cost adjustment from material transaction- September 22 | -9384.76
4 | TXM Manpower cost adjustment from material transaction- October 22 | -9051.18
5 | TXM Manpower cost adjustment from material transaction- November 22 | -9951.73
6 | TXM Manpower cost adjustment from material transaction- November 22 | -1583.52
7 | TXM Manpower cost adjustment from material transaction- December 22 | -19197
8 | TXM Manpower cost adjustment from material transaction- January 23 | -18884.76
8 | IT costs adjustment from Overhead transaction for June 22 | -10220
9 | IT costs adjustment from Overhead transaction July 22 | -11760
10 | IT costs adjustment from Overhead transaction August 22 | -12180
11 | IT costs adjustment from Overhead transaction September 22 | -14000
12 | Visa Cost of labours | -2797.41
13 | Visa Cost of labours | -1259.8
14 | Included VAT adjustment | -521.189
15 | TXM Manpower cost adjustment from material transaction- February 23 | -19197
16
17
18
19
20
| TOTAL AMOUNT | -150267.889

## Com or's
APPLICATION FOR PAYMENT NO. 13
COMMITTED ORDERS
Certificate No. | Description | Total Amount (AED ) | Applied Amount (AED)
1 | Kone (LPO HM-201A22002/0002) - CTU use Lifts (2 Nos)- Feb. 23 | 160000 | 16000
2 | IT infra-strucure set up to Offices | 10000 | 10000
3 | Kone (LPO HM-201A22002/0048)- CTU use Lifts no 10 & 21 (2 Nos)- Feb 23 | 128000 | 16000
4 | Al Ihsan Building Materials Trading (LPO HM-201A22002/0056)- Balcony Tiles | 154032 | 30240
5 | Schirmer Safety Consultants (LPO HM-201A22002/0065)- Façade Inspection Services | 11500 | 5750
6 | Dosteen Doors & Shutters LLC (LPO HM-201A22002/0069)- Scissor Lift | 72900 | 72900
7 | High Glass Decor & Curtain Works LLC (LPO HM-201A22002/0080)- Turkish Acrylic carpet | 19435 | 19435
8 | Kone (LPO HM-201A22002/0086) - CTU Lifts (1 Nos)- for Feb 23 | 64000 | 8000
9 | Indigatech (LPO HM-201A22002/0095)- Fire rated Windows | 91817 | 0
10 | New Era Construction (LPO HM-201A22002/00113)- Cobiax Permanent Formwork | 67371.21 | 51376.14
11 | Dosteen Doors & Shutters LLC (LPO HM-201A22002/0117)- Scissor Lift | 72900 | 36450
12 | Spider Access (LPO HM-201A22002/0130)- Column rectification & paint Mock up | 15300 | 0
13 | Carpet Land LLC (LPO HM-201A22002/0151) - Carpet | 13790 | 0
14 | Dutco LLC (LPO HM-201A22002/0155) - Modular Seal | 7600 | 0
15 | Master Builders Solutions LLC (LPO HM-201A22002/0159) - Emaco | 8400 | 0
16 | Jabel Ali Tra. LLC (LPO HM-201A22002/0161 ) -Dune Sand | 11110 | 0
17 | Al Najar LLC (LPO HM-201A22002/0162 ) - DC Furniture | 4900 | 0
18 | Osler Access LLC (LPO HM-201A22002/0166 ) - Cradle Works | 12760 | 0
19 | Al Majid LLC (LPO HM-201A22002/0167 ) - GRP Tank | 6500 | 6500
20 | Inter Metal LLC (LPO HM-201A22002/0168 ) - DC Furniture | 5350 | 0
21 | Smart Office LLC (LPO HM-201A22002/169 ) - DC Furnitire | 9742 | 0
22 | Master Builders Solutions LLC (LPO HM-201A22002/0170) - Mater top | 18000 | 0
23 | Consent (LPO HM-201A22002/0172) - Tile & Coping | 166700 | 55632.42
24 | Momentum (LPO HM-201A22002/0179)- Ironmongery | 62299.3 | 4574.5 | Part cost booked.
25 | Indigatech (LPO HM-201A22002/0132)- Window Glass | 42920 | 0
26 | Laidlaw (LPO HM-201A22002/0176)- Ironmongery | 240812.4 | 0
27 | Kone (LPO HM-201A22002/0138) - CTU Lifts (2 Nos)- for Feb 23 | 96000 | 16000
28 | Fluid Codes Testing- (LPO HM-201A22002/0149) | 28207 | 0
29 | AST Digital Print Centre (LPO HM-201A22002/0037)- Printer charges | 15000 | 3438.16 | Registered Invoice
30 | Golden Ready Mix LLC (LPO HM-201A22002/0023 R1)- Concrete supply | 587200 | 92366.5 | Registered Invoice
31 | High Class Decor & Curtains Works LLC ( HM-201A22002/0080 ) | 19435 | 9717.5 | Registered Invoice
32 | AHK Works- Alternatives SC's | 528371.34 | 83360
33 | Ostermeier- Supply of manhole covers ( HM-201A22002/0277) | 420090 | 95735
34 | Hilti RE 500V4 ( HM-201A22002/0183) | 18900 | 0
35 | Mobility General- Ironmongery ( HM-201A22002/0185) | 150516 | 11129
36 | Osler- Cradle ( HM-201A22002/0188) | 137000 | 0
37 | Momentum- Ironmongery ( HM-201A22002/0192) | 12202 | 4680
38 | Master Emaco ( HM-201A22002/0195) | 9000 | 0
39 | Door Controls Glass Trading( HM-201A22002/0206) | 57018
40 | Osler- Cradle Maintenance ( HM-201A22002/0207) | 14928.57 | 11428.57
41 | Amalgam- Traffic Signs ( HM-201A22002/0210) | 3003 | 0
42 | Al Areej AC- Temp AC's ( HM-201A22002/0216) | 26500 | 0
43 | Mobility General- Ironmongery ( HM-201A22002/0222) | 13640 | 13640
44 | Schirmer- Façade Testing( HM-201A22002/0224) | 5000 | 0
45 | Neotech Engineering ( HM-201A22002/0228) | 8518 | 0
46 | Neotech Engineering ( HM-201A22002/0229) | 2770 | 0
47 | Hilti RE 500V4 ( HM-201A22002/0231) | 31500 | 12600
48 | Styro polystyrene ( HM-201A22002/0234) | 6875 | 3079.99
49 | Arabuild Tiles ( HM-201A22002/0237) | 480000 | 274713.6
50 | Smart Office Furnitures ( HM-201A22002/0240) | 1439 | 0
51 | Doormax Ironmongery (HM-201A22002/0252) | 223860.28 | 77978.28
52 | Betec CAD Louvers (HM-201A22002/0267) | 90586.4 | 0
53 | Mobility General Trading (HM-201A22002/0273) | 17100 | 17100
54 | Doormax Ironmongery (HM-201A22002/0280) | 13148 | 13148
55 | Styro Polystyrene (HM-201A22002/0281) | 46000 | 6125.13
56 | Carpets BSH Trading (HM-201A22002/0116) | 98548.1 | 19709.45
57 | Wow Factor- Barrisol (HM-201A22002/0118) | 40786 | 28550.2
58 | Consent (LPO HM-201A22002/0213) - Benches | 237500 | 109238.5
59 | Consent (LPO HM-201A22002/0242) - Kerbstone | 138000 | 95220
60 | Jebel Ali Transport(LPO HM-201A22002/0244) - Roadbase | 126000 | 59981.6
61 | Fireproof(LPO HM-201A22002/0289) - Palgan | 19000 | 0
62 | Laidlaw (LPO HM-201A22002/0286)- Ironmongery | 13984.5 | 0
63 | Master Builders ( HM-201A22002/0316) | 63900 | 36780
64 | Laidlaw (LPO HM-201A22002/0325)- Ironmongery | 35406.19 | 24969
65 | Hilti RE 500V4 ( HM-201A22002/0330) | 19800 | 6600
66 | Laidlaw (LPO HM-201A22002/0331)- Ironmongery | 93046.22 | 69784.665
67 | Consent (LPO HM-201A22002/0345) - Precast | 24996.5 | 24996.5
68 | Mobility General Trading (HM-201A22002/0353) | 25564 | 25564
69 | Laidlaw (LPO HM-201A22002/0355)- Ironmongery | 19038 | 19038
70 | Mobility General Trading (HM-201A22002/0359) | 25040 | 25040
71 | DIgilock (HM-201A22002/0362) | 5403.708 | 5403.708
72 | Fischer Fixing (HM-201A22002/0319) | 2324.1 | 2324.1
| TOTAL AMOUNT | 5530283.818 | 1632297.513

## K Summary
COINS - FINANCE
Contract Cost Breakdown 201A22002 Dorchester Hotel & Residences
Period February 2023
|  |  | Previous Cum | Current Month
Ledger | Current Period | Total to Date |  |  | Certified
Labour | 1841741.49 | 12911119.45 | 11069377.96 | -1841741.49 | 7628037.26 | -5283082.19
Payroll | 1765097.49 | 11522626.37 | 9757528.88 | -1765097.49 | 6696259.3
Manual Journal |  |  |  | 0
Purchase Orders |  |  |  | 0
Direct Invoices |  |  |  | 0
Petty Cash Charges |  | 1425 | 1425 | 0 | 1425
Subcontractor Costs | 76644 | 1387068.08 | 1310424.08 | -76644 | 930352.96
Material | 1235525.57 | 10732950.13 | 9058810.56 | -1674139.57 | 6311690.05 | -4421260.08
Purchase Orders | 1259395.73 | 6456544.89 | 5197149.16 | -1259395.73
Stock Issues | 395061.83 | 4096616.6 | 3701554.77 | -395061.83
Manual Journals | -438614 | 4371 | 4371 | 0
Petty Cash Charges | 2965.39 | 14611.42 | 11646.03 | -2965.39
Plant Charges | 16450 | 160160 | 143710 | -16450
Direct Invoices | 266.62 | 646.22 | 379.6 | -266.62
Plant | 524192.86 | 3700074.42 | 3175881.56 | -524192.86 | 2300533.63 | -1399540.79
Plant Charges | 509056.25 | 3505544.74 | 2996488.49 | -509056.25
Manual Journals | 14134.91 | 185009.98 | 170875.07 | -14134.91
Petty Cash Charges |  |  |  | 0
Direct Invoices | 1001.7 | 9519.7 | 8518 | -1001.7
Subcontractor | 10628035.0597 | 75934834.304 | 65308299.2443 | -10626535.0597 | 41412331.2124 | -34522503.0916
Subcontract Costs | 10626535.0597 | 75925714.304 | 65299179.2443 | -10626535.0597 | 41405911.2124 | -34519803.0916
CVR Items |  | 0 | 0 | 0
Purchase Orders | 1500 | 9120 | 9120 | 0 | 6420 | -2700
Direct Invoices | 0 | 0 | 0 | 0
Manual Journals |  |  |  | 0
Overhead | 109893.16 | 1398117.19 | 1288084.03 | -110033.16 | 973013.62 | -425103.57
CVR Items |  | 0 | 0 | 0
Purchase Orders | 27692.11 | 694166.95 | 666474.84 | -27692.11
Direct Invoices | 16727.68 | 133692.83 | 116965.15 | -16727.68
Petty Cash Charges | 32560.5 | 150549.63 | 117989.13 | -32560.5
Manual Journals | 1166.33 | 165674.86 | 164368.53 | -1306.33
Plant Charges | 1148 | 11060 | 9912 | -1148
Stock Issues | 30598.54 | 242972.92 | 212374.38 | -30598.54
Salaries | 1403820.5 | 12327488.23 | 10923667.73 | -1403820.5 | 8251283.44 | -4076204.79
Payroll Charges | 1403820.5 | 12325757.71 | 10921937.21 | -1403820.5 | 8249552.44
Manual Journals |  | 1730.52 | 1730.52 | 0 | 1731
Direct Invoices |  |  |  | 0
Commited Orders | -141056 | 1632297.513 | 1773353.41 | 141055.897
Commited Orders | -141056 | 1632297.513 | 1773353.41 | 141055.897 | 2225356.19 | 593058.677
0
0
Total | 15602152.6397 | 118636881.237 | 102597474.4943 | -16039406.7427 | 69102245.4024 | -49534635.8346
|  |  |  | -437254.103 |  | -6191829.4793
-55726465.3139

## Labour
COINS - FINANCE
Labour Cost 201A22002 Dorchester Hotel & Residences
Period February 2023
Payroll
Cost Head | Description |  | Normal Hours | OT Hours | EOT Hours | Current | TTD
10100 | Unskilled labour costs - internal |  | 31298 | 3623 | 5190 | 403679.24 | 2880606.56
10200 | Skilled labour costs - internal |  | 28728 | 3355 | 4742 | 413782.14 | 2503751.41
10300 | Operators costs - internal |  | 6159 | 636.5 | 1216 | 114710.76 | 758328.97
10400 | Tradesmen costs - internal |  | 56102 | 6577 | 9535.5 | 797138.78 | 5119252.7
10500 | Charge hand labour costs - internal |  | 2216 | 275 | 469 | 35786.57 | 260686.73
Total |  |  | 124503 | 14466.5 | 21152.5 | 1765097.49 | 11522626.37
Manual Journals
Cost Head | Description |  |  | Type | Int Ref | Current | TTD
Total
Purchase Orders
Commodity | Description |  |  | Invoiced | Accrual / Rev | Current | TTD
Total | [5 empty] | 0
Direct Invoices
Cost Head | Description |  |  | Type | Int Ref | Current | TTD
Total
Petty Cash Charges
Cost Head | Description |  |  | Type | Int Ref | Current | TTD
10200 | Skilled labour costs - internal | [5 empty] | 1425
Total | [6 empty] | 1425
Subcontract Costs
Cost Head | Description |  |  | Int Ref | Ext Ref | Current | TTD
11400 | Tradesmen costs - external |  |  |  |  | 250685 | 2127571.59
| ALQA002 | Al Qannati Electromechanical and Plumbing Co LLC |  |  |  | 167085 | 1065676
1065676
| BLUE008 | Blue Sky Middle East Contracting (LLC) |  |  |  | 42300 | 724191.51
724191.51
| FOCU003 | Focus Power Security Services (LLC) |  |  |  | 24500 | 207516.12
207516.12
| SERV004 | Service Plus Technical Services LLC |  |  |  | 16800 | 130187.96
130187.96
| ALQA002 | Al Qannati Electromechanical and Plumbing Co LLC |  |  |  | 250685 | 2127571.59
2127571.59
Total | [5 empty] | 250685 | 2127571.59

## Material
COINS - FINANCE
Material Cost 201A22002 Dorchester Hotel & Residences
Period February 2023
Purchase Orders
Commodity | Description |  | Invoiced | Accrual / Rev | Current | TTD
21110A01 | Reinforcement - Bars Mesh Bending Sched |  | 49757.4 | -29003.06 | 20754.34 | 226559.34
| CICO001 | Cicon Building Materials | 49757.4 | -29003.06 | 20754.34 | 226559.34
21110A02 | Reinforcing Sundries |  | 7620 | -720 | 6900 | 12660
| ALAB003 | Al Abbasi Fasteners and Hardware | 2500 |  | 2500 | 7250
| MODE002 | Modern Building Materials Trad | 720 | -720 | 0 | 1010
| SALA001 | Salam Enterprises LLC | 4400 |  | 4400 | 4400
21111A01 | Aggregates |  |  | 0 | 0 | 8999.1
| JABE002 | Jabel Ali General Transport En |  | 0 | 0 | 8999.1
21112A01 | Timber/Plywood/Nails |  | 8500 | 34150 | 42650 | 106150
| ABUA004 | Abu Al Hassan Building Material Co. (ABCO) LLC - Foreign Direct Investment |  | 23250 | 23250 | 48750
| ACME001 | Acme Building Materials Trading LLC | 7150 | 10900 | 18050 | 51050
| SRRB001 | SRR Building Material Trading LLC | 1350 |  | 1350 | 6350
22317A01 | Vehicle Plant and Spares |  | 56000 | -56000 | 0 | 410933.64
| KONE001 | Kone Middle East LLC | 56000 | -56000 | 0 | 410933.64
22324A01 | Metalwork/Steelwork/Misc Metalwork Items |  |  | 295180 | 295180 | 324355
| OSTE001 | Ostermeier FZE |  | 295180 | 295180 | 324355
22711A01 | Consumable Tooling |  | 41787.08 | -15858.89 | 25928.19 | 106484.88
| ALAB003 | Al Abbasi Fasteners and Hardware | 604 | -318 | 286 | 4519
| DIAM005 | Diamond Tools Trading FZC | 1400 |  | 1400 | 1400
| DUTI001 | Dutest Industrial Est |  |  | 0 | 600
| GULF019 | Gulf Metal Wires Industry LLC |  |  | 0 | 820
| HILT001 | Hilti Emirates LLC | 39783.08 | -15540.89 | 24242.19 | 92465.88
| NASE001 | Naser Al Sayer and Co LLC |  |  | 0 | 6680
23011A01 | Blockwork/Masonry/Mortar |  | 8496 | -2470.4 | 6025.6 | 81190
| ARKA003 | Arkan Building Materials Co Arkan PJSC - Dubai Bramch | 7360 | -3680 | 3680 | 45310
| MAST005 | Master Builders Solutions Construction Chemicals LLC |  |  | 0 | 8400
| UNIM005 | Uni Mix Block Industry (LLC) | 1136 | 1209.6 | 2345.6 | 27480
23011A02 | Blockwork Sundry Material |  | 3702.4 | -460.8 | 3241.6 | 164205
| ALAB003 | Al Abbasi Fasteners and Hardware |  |  | 0 | 1600
| CORE004 | Core Metallic Ind LLC |  |  | 0 | 23379
| HILT001 | Hilti Emirates LLC |  |  | 0 | 69300
| MODE002 | Modern Building Materials Trad |  |  | 0 | 720
| PALL001 | Palletco LLC |  |  | 0 | 26000
| UNIM005 | Uni Mix Block Industry (LLC) | 3702.4 | -460.8 | 3241.6 | 43206
23011A03 | Concrete |  | 40045 | 98259 | 138304 | 352042.5
| GOLD026 | Golden Ready Mix LLC | 40045 | 98259 | 138304 | 352042.5
23011A04 | Concrete Sundries |  | 87397.62 | 90891.18 | 178288.8 | 437770.84
| ALAB003 | Al Abbasi Fasteners and Hardware |  | 5160 | 5160 | 13760
| KING003 | Kingspan Insulation (LLC) |  | 0 | 0 | 12000
| MAPE001 | Mapei Construction Chemicals LLC |  |  | 0 | 460
| MAST005 | Master Builders Solutions Construction Chemicals LLC | 64612 | 97124 | 161736 | 367881
| STYR002 | Styro Insulation Materials Trading LLC | 22785.62 | -11392.82 | 11392.8 | 43669.84
23011A05 | Plaster Screed Rush Coat |  | 4960 | 1000 | 5960 | 47760
| CONM001 | Conmix Ltd | 4960 | 1000 | 5960 | 47760
23011A06 | Plaster Sundries |  | 786 | 0 | 786 | 5103
| CONM001 | Conmix Ltd | 786 |  | 786 | 2706
| CORE004 | Core Metallic Ind LLC |  | 0 | 0 | 2397
23011A07 | Precast Concrete |  | 127978.5 | -117906 | 10072.5 | 273492.5
| ALSE002 | Al Serkal and Assarain Concret | 117906 | -117906 | 0 | 254470
| CONS001 | Consent LLC | 10072.5 |  | 10072.5 | 19022.5
23012A01 | Road Base |  | 8520.4 | 0 | 8520.4 | 66018.4
| JABE002 | Jabel Ali General Transport En | 8520.4 | 0 | 8520.4 | 66018.4
23012A04 | Kerb Stones |  | 21620 | -13340 | 8280 | 42780
| CONS001 | Consent LLC | 21620 | -13340 | 8280 | 42780
23016A01 | Tiling Material |  | 86905.8 | 3402.54 | 90308.34 | 535977.88
| ALIH002 | Al Ihsan Building Materials Trading |  | 0 | 0 | 123792
| ARAB017 | Arabuild LLC | 83980.8 |  | 83980.8 | 216266.4
| CONS001 | Consent LLC |  | 3015.54 | 3015.54 | 188394.48
| MAPE001 | Mapei Construction Chemicals LLC |  | 3312 | 3312 | 4600
| MATE005 | Matex Construction Chemicals Manufacturing LLC | 2000 | -2000 | 0 | 2000
| SODA001 | Sodamco Sal Abu Dhabi | 925 | -925 | 0 | 925
23019A01 | Formwork/Falsework |  | 1065.12 | 2324.1 | 3389.22 | 25695.8
| ALQU003 | Al Quebeisi SGB LLC |  |  | 0 | 111.51
| FISC002 | Fischer Fixing LLC |  | 2324.1 | 2324.1 | 5024.1
| NEXT004 | Next Era Construction Materials Trading One Person Company LLC |  |  | 0 | 15995.07
| RMDK001 | RMD Kwikform Middle East LLC | 1065.12 |  | 1065.12 | 1065.12
| TRAD004 | Tradex LLC |  |  | 0 | 3500
23019A02 | Formwork Sundries |  | 31200 | -18019.48 | 13180.52 | 59715.52
| ABUA004 | Abu Al Hassan Building Material Co. (ABCO) LLC - Foreign Direct Investment | 15000 | -15000 | 0 | 19125
| ACME001 | Acme Building Materials Trading LLC | 16200 | -16200 | 0 | 23890
| ASCE001 | Ascend Access System Scaffoldi |  | 13180.52 | 13180.52 | 16700.52
23121A01 | Painting & Decorating Materials/Sealants |  |  | 22047 | 22047 | 32100
| DUTC004 | Dutco Tennant LLC |  |  | 0 | 7600
| PALG001 | Palgan Insulation Co LLC |  | 19000 | 19000 | 19000
| QCON001 | Q Con General Trading LLC |  | 3047 | 3047 | 5500
23123A01 | Ironmongery |  | 263032.18 | -95811.91 | 167220.27 | 1390572.79
| ALAB003 | Al Abbasi Fasteners and Hardware | 3750 | -3750 | 0 | 5320
| BETE001 | Betec Cad Industries FZC | 90586.4 |  | 90586.4 | 90586.4
| DOOR001 | Doormax Building Material Trading (LLC) |  | 18698 | 18698 | 159030
| DOOR002 | Door Controls Glass Trading LL | 57018.18 | -57018 | 0.18 | 57018.18
| FINE001 | Fine Tools Trading LLC |  |  | 0 | 840
| LAID001 | Laidlaw Gulf LLC | 111677.6 | -55285.51 | 56392.09 | 733591.63
| MOBI002 | Mobility General Trading LLC |  | 0 | 0 | 139387
| MOME001 | Momentum Fireguard LLC |  | 1543.6 | 1543.6 | 198599.58
| QUAL010 | Quality Metal Works Manufacturing LLC |  |  | 0 | 6200
23912A02 | Electrical Items |  |  |  | 0 | 16635
| ALBA003 | Al Bajaa Lighting Equipment Trading LLC |  |  | 0 | 6835
| FAIS001 | Faisal Ali Juma Trading LLC |  |  | 0 | 9800
24713A01 | Cleaning Materials |  | 600 | -600 | 0 | 600
| ALBA009 | Al Bariq Equipment LLC | 600 | -600 | 0 | 600
29901A02 | Other Consumables |  | 96898.05 | -46737.8 | 50160.25 | 277899.49
| AJIH001 | AJI Heavy Equipment Rental LLC | 1560.5 |  | 1560.5 | 1560.5
| ALAB003 | Al Abbasi Fasteners and Hardware | 93637.55 | -45037.8 | 48599.75 | 233467.09
| ALBA009 | Al Bariq Equipment LLC | 1700 | -1700 | 0 | 1700
| ALSH004 | Al Sham Star Trading LLC |  |  | 0 | 945
| ASCE001 | Ascend Access System Scaffoldi |  |  | 0 | 17582
| CHEM001 | Chemex Hygiene Concepts LLC |  |  | 0 | 4642.5
| CRES002 | Crescent Scaffolding Industrie |  |  | 0 | 6600
| FAIS001 | Faisal Ali Juma Trading LLC |  |  | 0 | 5903.5
| HEPW001 | Corys Piping Systems LLC |  |  | 0 | 2016
| NEXT004 | Next Era Construction Materials Trading One Person Company LLC |  | 0 | 0 | 1542.9
| SALE001 | Saleem Jacobson Trading |  |  | 0 | 1940
41540A01 | External Works through LPO's |  | 138624.7 | 23574 | 162198.7 | 1450844.21
| ALNA007 | Al Najah Furnishings LLC |  |  | 0 | 4900
| BSHT001 | BSH Trading (LLC) |  |  | 0 | 78838.74
| CARP001 | Carpet Land LLC |  |  | 0 | 13790
| CULL001 | Culligan International Emirate |  |  | 0 | 218423.22
| DANA002 | Danat Alkhaleej for Safety Consultancy |  |  | 0 | 5550
| DOST001 | Dosteen Doors and Shutters LLC |  | 36450 | 36450 | 36450
| FLUI002 | Fluid Codes DMCC |  |  | 0 | 28207
| GULF019 | Gulf Metal Wires Industry LLC |  |  | 0 | 1225
| INDI003 | Indiga Tech Trading (LLC) | 107191.9 | -12876 | 94315.9 | 134737
| INTE009 | Intermetal (LLC) Dubai Br |  | 0 | 0 | 7350
| KCEJ001 | KCE (LLC) - Joinery Division |  |  | 0 | 1248.54
| NATI010 | National Services for Carpet a |  |  | 0 | 2686.2
| OSLE001 | Osler Access Equipment LLC |  |  | 0 | 753260.09
| OSTE001 | Ostermeier FZE |  |  | 0 | 13357
| SANI001 | Sanipex LLC |  |  | 0 | 20401.74
| SCHI004 | Schirmer Safety Consultants |  |  | 0 | 10750
| SMAR015 | Smart Space Office Furniture Trading |  |  | 0 | 11112.39
| TXML001 | TXM Labour Supply LLC | 19197 |  | 19197 | 96321.49
| WOWF001 | Wow Factor Building Material T | 12235.8 |  | 12235.8 | 12235.8
Total |  |  | 1085496.25 | 173899.48 | 1259395.73 | 6456544.89
Stock Issues
Cost Head | Description |  | Type | Int Ref | Current | TTD
21112 | Wood Products |  |  |  |  | 38201.65
| 11121609-A03989 | Plywood - Film Faced - 18Mm - Fsc - Popalr Core |  |  |  | 38201.65
21510 | Fuels |  |  |  | 335262.76 | 3782843.65
| 15101501-A18400 | Fuel - Petrol |  |  |  | 1234.12
| 15101501-A18401 | Fuel - Diesel | ISS |  | 335262.76 | 3781609.53
22210 | Heavy construction machinery and equipment |  |  |  | 43200 | 104400
| 22101701-A04048 | Floor Protection Sheet Polypro Corrugated 4Mm |  |  | 43200 | 104400
22711 | Hand tools |  |  |  | 2700 | 116222
| 22711H02-010001 | Floor Cleaning Machine |  |  |  | 4440
| 27112702-A20393 | Angle Grinder |  |  |  | 27722
| 27112702-A20412 | Concrete Mixer |  |  |  | 2350
| 27112702-A20424 | Drill |  |  |  | 9510
| 27112702-A20470 | Paddle Mixer |  |  | 2700 | 2700
| 27112702-A20504 | Stepdown Transformer |  |  |  | 34875
| 27112702-A20516 | Vacuum Cleaner |  |  |  | 11125
| 27112702-A20520 | Wall Chasing Machine |  |  |  | 23500
24325 | Project IT Infrastructure |  |  |  | 13255.5 | 16051.5
| 24325V01-010001 | Firewall SonicWall TZ400 - New |  |  | 3275 | 3275
| 24325V01-010002 | Access Point Aruba AP 515 - New |  |  |  | 2598
| 24325V01-010004 | Mounting Kit Aruba AP 515 - New |  |  |  | 198
| 24325V01-010012 | Aruba Central AP Foundation 1y Subscription - New |  |  | 2350.8 | 2350.8
| 24325V01-010026 | Ray L2+ Cloud Managed Switch 8 Port - New |  |  | 1077 | 1077
| 24325V01-010029 | Advanced Gateway Security Suite Bundle for TZ400 Series - 1 Yr |  |  | 5445.64 | 5445.64
| 24325V01-010030 | Sonicwall Network Security Manager Essential with Management and 7-Day R |  |  | 1107.06 | 1107.06
| 24325V01-020001 | Firewall SonicWall TZ400 - Used |  |  |  | 0
| 24325V01-020002 | Access Point Aruba AP 515 - Used |  |  |  | 0
| 24325V01-020005 | Network Switch Cisco SG350 28 Port - Used |  |  |  | 0
| 24325V01-020007 | Wireless Router D-Link 4G - Used |  |  |  | 0
24618 | Personal safety and protection |  |  |  | 453.32 | 14801.05
| 46181507-A04452 | Safety Vest 90 Gsm Florescent Green - Large (Rigger) |  |  |  | 102.93
| 46181507-A04459 | Safety Vest 90 Gsm M Green - Staff Vest - 2XL |  |  |  | 105.56
| 46181507-A04460 | Safety Vest 90 Gsm M Green - 2Xl |  |  |  | 387.51
| 46181507-A04461 | Safety Vest 90 Gsm M Green - Staff Vest - 3XL |  |  |  | 9
| 46181507-A04462 | Safety Vest 90 Gsm M Green - Large |  |  |  | 1236.68
| 46181507-A04463 | Safety Vest 90 Gsm M Green - Staff Vest - M |  |  |  | 226.47
| 46181507-A04464 | Safety Vest 90 Gsm M Green - Staff Vest - L |  |  |  | 316.66
| 46181507-A04465 | Safety Vest 90 Gsm M Green - Medium |  |  |  | 914.5
| 46181507-A04466 | Safety Vest 90 Gsm M Green - Staff Vest - XL |  |  |  | 364.27
| 46181507-A04467 | Safety Vest 90 Gsm M Green - Xl |  |  |  | 1006.81
| 46181507-A20681 | Traffic Marshall Safety Jacket Size- XL |  |  |  | 75
| 46181507-A20695 | Rigger Safety Jacket Size - XL |  |  |  | 37.5
| 46181507-A20696 | Rigger Safety Jacket Size - 2XL |  |  |  | 37.5
| 46181701-A04400 | Safety Helmet For Staff Mk7 |  |  |  | 3395
| 46181701-A04402 | Safety Helmet High Ev Yellow - 6 Point Textile Tapes System. Slip Ratche |  |  | 364 | 5941
| 46181701-A04404 | Safety Helmet High Ev Red - 6 Point Textile Tapes System. Slip Ratchet T |  |  | 89.32 | 558.66
| 46181701-A04405 | Safety Helmet High Ev White - 6 Point Textile Tapes System. Slip Ratchet |  |  |  | 26
| 46181701-A20074 | Safety Helmet High Ev Green - 6 Point Textile Tapes System. Slip Ratchet |  |  |  | 60
25213 | Window treatments |  |  |  |  | 13724.91
| 52131602-A18941 | Shade Net - 100% new HDPE with UV protection - 285 GSM - 3.66X100Mtr - |  |  |  | 13724.91
25310 | Clothing |  |  |  | 190.25 | 8526.42
| 53101602-A04981 | Shirt Cotton Full Sleeve White - 2Xl |  |  |  | 380.04
| 53101602-A04984 | Shirt Cotton Full Sleeve White - Large |  |  |  | 1200
| 53101602-A04985 | Shirt Cotton Full Sleeve White - Medium |  |  |  | 912
| 53101602-A04986 | Shirt Cotton Full Sleeve White - Small |  |  | 190.25 | 1322.96
| 53101602-A04987 | Shirt Cotton Full Sleeve White - Xl |  |  |  | 376.09
| 53101602-A04988 | Shirt Formal Half Sleeve White - 2Xl |  |  |  | 105.56
| 53101602-A04989 | Shirt Formal Half Sleeve White - 3Xl |  |  |  | 360
| 53101602-A04991 | Shirt Formal Half Sleeve White - Large |  |  |  | 298.42
| 53101602-A04992 | Shirt Formal Half Sleeve White - Medium |  |  |  | 106.7
| 53101602-A04993 | Shirt Formal Half Sleeve White - Small |  |  |  | 120.71
| 53101602-A04994 | Shirt Formal Half Sleeve White - Xl |  |  |  | 383.29
| 53103001-A05701 | T-Shirt 220 Gsm Half Sleeve White - 2Xl |  |  |  | 361.16
| 53103001-A05702 | T-Shirt 220 Gsm Half Sleeve White - 3Xl |  |  |  | 52
| 53103001-A05704 | T-Shirt 220 Gsm Half Sleeve White - Large |  |  |  | 208
| 53103001-A05705 | T-Shirt 220 Gsm Half Sleeve White - Medium |  |  |  | 1326
| 53103001-A05706 | T-Shirt 220 Gsm Half Sleeve White - Small |  |  |  | 312
| 53103001-A05707 | T-Shirt 220 Gsm Half Sleeve White - Xl |  |  |  | 701.49
60905 | Computers & Accessories |  |  |  |  | 1845.42
| 60905V01-010006 | Keyboard & Mouse Logitec Wireless Black - New |  |  |  | 125
| 60905V01-010013 | Cable HDMI 5m - New |  |  |  | 55
| 60905V01-010032 | Microsoft Display Adapter 1080p - New |  |  |  | 330
| 60905V01-010038 | Monitor HP E22 G4 FHD - New |  |  |  | 652.42
| 60905V01-010043 | Laptop Bag HP - New |  |  |  | 198
| 60905V01-010050 | USB A Wi-Fi adapter - New |  |  |  | 485
Total |  |  |  |  | 395061.83 | 4096616.6
Manual Journals
Cost Head | Description |  | Type | Int Ref | Current | TTD
29910 | Internal division - material costs |  |  |  |  | 4371
29951 | Materials cost accruals - CVR |  |  |  | -438614 | 0
|  | CVR Item Cost Code Manual Accruals Material | JCV | 159877 | -438614
Total |  |  |  |  | -438614 | 4371
Petty Cash Charges
Cost Head | Description |  | Type | Int Ref | Current | TTD
23116 | Hardware |  |  |  | 2965.39 | 14611.42
|  | 27743-CHRIS McCANN-201A22002 | PCP | FEB/11999/13 | 2683.94
|  | 27743-CHRIS McCANN-201A22002 | PCP | FEB/12016/15 | 281.45
Total |  |  |  |  | 2965.39 | 14611.42
Plant Charges
Cost Head | Description |  | Type | Int Ref | Current | TTD
22711 | Hand tools |  |  |  |  | 2850
| 27112217-A19363 | LT 53/2-Block Cutter |  |  |  | 2850
24619 | Fire protection |  |  |  |  | 3975
| PTLT150045 | PTLT150045 Building Dryer Machine |  |  |  | 150
| PTLT150092 | PTLT150092 Ventilation Fan 18" |  |  |  | 315
| PTLT150096 | PTLT150096 Ventilation Fan-20" |  |  |  | 387
| PTLT150097 | PTLT150097 Ventilation Fan 18" |  |  |  | 315
| PTLT150098 | PTLT150098 Ventilation Fan 18" |  |  |  | 387
| PTLT150108 | PTLT150108 Ventilation Fan 18" |  |  |  | 387
| PTLT150113 | PTLT150113 Ventilation Fan 18" |  |  |  | 702
| PTLT150115 | PTLT150115 Ventilation Fan-20" |  |  |  | 387
| PTLT150142 | PTLT150142 Ventilation Fan 18" |  |  |  | 315
| PTLT150143 | PTLT150143 Ventilation Fan 18" |  |  |  | 315
| PTLT150144 | PTLT150144 Ventilation Fan 18" |  |  |  | 315
29900 | EHD Materials |  |  |  | 16450 | 153335
| 99000101-A18468 | Pedestrian Barrier Steel Branded (2.5 x 1.2mtr) |  |  | 10000 | 51000
| 99000101-A18474 | Rebar Access mat |  |  | 1800 | 1800
| 99000101-A20672 | Expandable PVC Barrier - 2.5m x 0.960m |  |  |  | 1750
| 99000201-A18478 | Metal Hordings (2.2 x 2 mtr) K standard |  |  |  | 5775
| 99000601-A18491 | TYPE 1 - 3 Cooler Stand |  |  |  | 8612.5
| 99000701-A18494 | Cable Management Stand |  |  |  | 21937.5
| 99000701-A18496 | Cable Management Hooks-double hooks ( type 2) |  |  |  | 3375
| 99000701-A18497 | Cable Management Hooks three hooks ( type 3) |  |  |  | 1600
| 99000801-A18499 | Aluminium Podium Tower 1.00m x 1.30m |  |  | 1350 | 1350
| 99000901-A18510 | Man Basket |  |  |  | 7575
| 99001001-A18505 | Concrete Bucket - 1m3 |  |  |  | 960
| 99001001-A18668 | 1.5 CBM (3T) Tipping skip |  |  | 3300 | 3300
| 99001001-A18669 | 1.5 CBM (3T) Self Dumping Skip |  |  |  | 5500
| 99001101-A18509 | Tripod |  |  |  | 2800
| 99001201-A18840 | EHD Security Cabin |  |  |  | 2600
| 99001401-A18842 | EHD Gas Monitor |  |  |  | 5400
| 99001601-A19775 | Large Industrial Evaporative Outdoor Air Cooler |  |  |  | 28000
Total |  |  |  |  | 16450 | 160160
Direct Invoices
Cost Head | Description |  | Type | Int Ref | Current | TTD
21510 | Fuels |  |  |  | 266.62 | 646.22
| ALFU013 | Al Futtaim Transport and Renta |  |  | 266.62 | 646.22
|  | Fuel-3/3100 | PINN | 2302PL001200 | 266.62
Total |  |  |  |  | 266.62 | 646.22
[5 empty] | 1235525.57 | 10732950.13

## Plant
COINS - FINANCE
Plant Cost 201A22002 Dorchester Hotel & Residences
Period February 2023
Plant Charges
Cost Head | Description |  | Type | Int Ref | Current | TTD
30010 | I-Earth moving machinery |  |  |  | 11474.62 | 92853.8
| 2210150902 | Backhoe Loader (3CX) With Operator-Working |  |  |  | 4147
| 2210152614 | Mini Excavator 3 Ton with Breaker-Working |  |  |  | 4950
| P000220110 | P000220110 Case Sr150 Skid Steer Loader |  |  | 1308.46 | 1308.46
| P000220111 | P000220111 Case Sr150 Skid Steer Loader |  |  |  | 560.77
| P000220115 | P000220115 Case Sr150 Skid Steer Loader |  |  |  | 93.46
| P000220119 | P000220119 Case Sr150 Skid Steer Loader |  |  |  | 2710.39
| P000220120 | P000220120 Case Sr200 Skid Steer Loader |  |  | 1461.54 | 33176.94
| P000220123 | P000220123 Case Sr150 Skid Steer Loader |  |  | 2243.08 | 16916.55
| P000230121 | P000230121 Avant Compact Loader -Dxb62067 |  |  | 3507.69 | 5992.31
| P000500132 | P000500132 Bomag Plate Compactor Bpr25/50 |  |  | 1661.54 | 12946.15
| P000500133 | P000500133 Bomag Plate Compactor Bpr25/50 |  |  |  | 553.85
| P000610012 | P000610012 Sb Hopper Broom Attachment |  |  | 1292.31 | 6084.62
| P000610041 | P000610041 Hydraulic Breaker CB 37S for Skid Steer Loader |  |  |  | 3413.3
30020 | I-Aerial lifts |  |  |  | 22262.33 | 61037.33
| 2210180513 | Operator for Spider Boom Lift - 36 Mtr-Working |  |  | 22262.33 | 61037.33
30030 | I-Building construction machinery and accessories |  |  |  | 15529 | 200135.48
| KSFT000027 | KSFT000027 Diesel Storage Tank 1800 Ltrs(Original) |  |  |  | 138.48
| P000090078 | P000090078 Diesel Tanker- Dorchester Hotel & Residences (Completion Works) Scania Fuel Tanker |  |  |  | 1044
| P000490100 | P000490100 Livers Hf 4Kva Converter |  |  | 972 | 10692
| W000020068 | W000020068 Diesel Tanker 9/68 Mercedes Fuel Tanker - DXB64273 |  |  | 1044 | 12006
| W000020069 | W000020069 Diesel Tanker - 9/69 - Dorchester Hotel & Residences (Completion Works) Mercedes Fuel Tanker - DXB63219 |  |  | 12006 | 61596
| W000020070 | W000020070 9/70 Diesel Tanker Dorchester Hotel & Residences (Completion Works) Mercedes Fuel Tanker - DXB65028 |  |  | 1044 | 91872
| W000020071 | W000020071 Mercdes Water Tanker - DXB64272 |  |  |  | 6945
| W000020072 | W000020072 9/72 Sweet Water Tanker 1-Trip Mercdes Water Tanker - DXB62723 |  |  |  | 10674.5
| W000020073 | W000020073 9/73 Sweet Water Tanker 1-Trip Mercedes Water Tanker-DXB62979 |  |  | 463 | 5167.5
30100 | I-Lifting equipment and accessories |  |  |  | 248063.77 | 1457260.77
| 2410160302 | Forklift - 5 Ton With Operator-Working |  |  |  | 20460
| 2410160315 | Forklift 3 Ton With Long Fork-Working |  |  | 18954.32 | 133357.18
| 2410160401 | Monorail - 20 Mtr with Special Clamp & 2nos.Winches-Working |  |  | 22846.25 | 22846.25
| 2410160402 | Mast Climber (Model: MSM SUPER)-Working |  |  | 47384.96 | 122693.38
| 2410161705 | Electric Scissor Lift - 5.9 Mtr-Working |  |  | 8690 | 10890
| 2410161727 | Power Tower Duo - 5.1 Mtr-Working |  |  | 3511.92 | 10088.26
| 2410162301 | Operator for Derrick Crane - 2 Ton-Working |  |  | 761.55 | 761.55
| 2410162302 | Derrick Crane 2 Ton-Working |  |  | 2538.49 | 2538.49
| 2410162303 | Derrick Crane - 5 Ton Capacity-Working |  |  | 26061.72 | 425405.76
| 2410162304 | Derrick Crane - 12 Ton-Working |  |  | 29615.76 | 246444.04
| 2410162402 | Mobile Crane - 50 Ton-Working |  |  |  | 2640
| 2410162404 | Mobile Crane - 70 Ton With Fly Jib & Skidding |  |  |  | 21450
| 2410162405 | Mobile Crane - 100 Ton-Working |  |  | 6050 | 12650
| 2410162406 | Mobile Crane - 100 Ton-Working |  |  |  | 3850
| 2410162414 | Mini Crane (JEKKO SPX532) - 3.2 Ton With Operator-Working |  |  | 44000.88 | 140899.67
| 2410162415 | Jekko Mini Picker-1000kg-Working |  |  | 8038.47 | 27838.52
| MOB001 | Calculation For Special Bracket with 3rd Party Approval |  |  | 9240 | 134860
| P000210110 | P000210110 Manitou Mt-X 1840 Telehandler |  |  | 2503.85 | 3576.93
| P000210112 | P000210112 Manitou Mt-X 1840 Telehandler |  |  | 6080.77 | 6080.77
| P000250049 | P000250049 Liebherr Mobile Crane-55 Ton(1055-32) |  |  |  | 1246.15
| P000260029 | P000260029 Skyjack 8841Rt Scissor Lift |  |  |  | 211.54
| P000260049 | P000260049 Scissor Lift Electric- 8m |  |  | 2200 | 19118.9
| P000260050 | P000260050 Scissor Lift - 8m |  |  | 2030.88 | 9392.82
| P000260081 | P000260081 Scissor Lift Electric- 8m |  |  | 2030.88 | 19885.7
| P000260082 | P000260082 Scissor Lift Electric- 8m |  |  | 2200 | 18684.93
| P000260087 | P000260087 Nano Lift 4.5 Meter |  |  | 1107.69 | 10430.76
| P000260088 | P000260088 Nano Lift 4.5 Meter-Holiday |  |  | 1107.69 | 9738.45
| P000260092 | P000260092 Nano Lift 4.5 Meter |  |  | 1107.69 | 10199.99
| W000180010 | W000180010 Moffett Forklift M4 - DXB43955 |  |  |  | 654.23
| W000180014 | W000180014 TCM Forklift - DXB 41076-Working |  |  |  | 8366.5
30110 | I-Passenger motor vehicles |  |  |  | 56404.88 | 447407.47
| 2510150704 | Pick Up - 3 Ton Double CabinWithout Driver-Working |  |  | 5330.88 | 53499.1
| 2510150705 | Recovery Vehicle 3 Ton |  |  |  | 3850
| P000080658 | P000080658 Ashok Leyland Bus - Dxb 73025P |  |  | 1680 | 1680
| P000080660 | P000080660 Ashok Leyland Bus - Dxb 92791Q With IVMS |  |  |  | 840
| P000080661 | P000080661 Ashok Leyland Bus - Dxb 36303H |  |  |  | 1512
| P000080664 | P000080664 Ashok Leyland Bus - Dxb 52753J |  |  | 5110 | 33614
| P000080666 | P000080666 Ashok Leyland Bus - Dxb 53795I |  |  |  | 168
| P000080667 | P000080667 Ashok Leyland Bus - Dxb 51596J |  |  | 5110 | 8134
| P000080681 | P000080681 Ashok Leyland Bus - DXB 86848H |  |  | 5110 | 39396
| P000080682 | P000080682 Ashok Leyland Bus - DXB 87476H |  |  |  | 840
| P000080683 | P000080683 Ashok Leyland Bus - DXB 15614M |  |  |  | 1176
| P000080684 | P000080684 Ashok Leyland Bus - DXB 15497M |  |  | 840 | 1680
| P000080685 | P000080685 Ashok Leyland Bus - DXB 86783H With IVMS |  |  | 2184 | 26586
| P000080686 | P000080686 Ashok Leyland Bus - DXB 15496M |  |  |  | 1848
| P000080687 | P000080687 Ashok Leyland Bus - DXB 85148H |  |  | 5110 | 48202
| P000080690 | P000080690 Ashok Leyland Bus - DXB 15611M |  |  | 5110 | 50988
| P000080692 | P000080692 Ashok Leyland 59 Seat Bus-DXB 72359 W |  |  |  | 184.44
| P000080696 | P000080696 Ashok Leyland 59 Seat Bus-DXB 72353 W |  |  | 5610 | 37379.51
| P000080701 | P000080701 Ashok Leyland 71 Seat Bus |  |  | 5850 | 51031.23
| TA00033100 | TA00033100 TOYOTA COASTER HI ROOF 23STR 4.0D MANUAL |  |  | 4680 | 9142.03
| TA00033109 | TA00033109 TOYOTA COASTER HI ROOF 23STR 4.0D MANUAL |  |  | 4680 | 49107.95
| TA00043000 | TA00043000 TOYOTA HIACE 13 SEAT BUS |  |  |  | 26549.21
30120 | I-Product and material transport vehicles |  |  |  |  | 16019.78
| P000320042 | P000320042 Thwaites Dumper - P 22157 |  |  |  | 16019.78
30130 | I-Specialized and recreational vehicles |  |  |  | 28220 | 236157.08
| P000100022 | P000100022 Nissan Truck With Hiab Crane With IVMS |  |  |  | 1540
| P000100023 | P000100023 Mercedes Truck With Crane With IVMS |  |  |  | 2480
| P000100025 | P000100025 Mercedes Truck With Crane With IVMS |  |  |  | 2480
| P000120019 | P000120019 12/19 Skip Truck 1-Trip ( 57202 ) Isuzu 12Ton Truck - Dxb 83254O |  |  | 10603 | 83450
| P000120020 | P000120020 1 Trip 12/20 Skip Truck ( 60136 ) Hino 13.5 Ton Skip Truck |  |  | 3276 | 17754
| W000030018 | W000030018 Nissan Truck with Hiab Crane With IVMS |  |  |  | 9497.08
| W000030019 | W000030019 Nissan Truck with Hiab Crane With IVMS |  |  | -385 | 3465
| W000030020 | W000030020 Nissan Truck with Hiab Crane With IVMS |  |  | 3850 | 7700
| W000050017 | W000050017 12/17 Skip Truck 1-Trip ( 59984 ) Isuzu with Hiab Skip Loader - Dxb 70086 D |  |  | 10876 | 107791
30140 | I-Truck tractors |  |  |  | 1206 | 5628
| P000170028 | P000170028 Machinery Shifting Man Tractor Head - Dxb 25990-Low Bed |  |  | 402 | 804
| P000170029 | P000170029 Machinery Shifting Man Tractor Head - Dxb 25988-Low Bed |  |  | 804 | 804
| W000070021 | W000070021 MAN Tractor Unit - DXB 66748 |  |  |  | 2010
| W000070022 | W000070022 MAN Tractor Unit - DXB 66768 |  |  |  | 2010
30160 | I-Product and material trailers |  |  |  | 744 | 2272
| W000320031 | W000320031 Machinery Shifting Low Bed Semi Trailer 65Ton |  |  | 496 | 496
| W000320032 | W000320032 Machinery Shifting Low Bed Semi Trailer 65Ton |  |  | 248 | 496
| W000320035 | W000320035 Flat Bed Semi Trailer - 55Ton |  |  |  | 640
| W000320037 | W000320037 Flat Bed Semi Trailer - 55Ton |  |  |  | 640
30170 | I-Power generators |  |  |  | 60981.43 | 760075.27
| 2611160108 | Generator - 350 KVA-Working |  |  |  | 17769.86
| 2611160109 | Cables - (1C 240mm2 40Mtr x 30 Runs =1200Mtrs)-Working |  |  | 19385.2 | 232179.9
| 2611160110 | Distribution Board - 2500Ams-Working |  |  | 41596.23 | 510125.51
30230 | I-Compressors |  |  |  |  | 11894.43
| P000330091 | P000330091 Atlas Copco Air Compressor |  |  |  | 11682.9
| PTLT250022 | PTLT250022 Electric Compressor |  |  |  | 211.53
30510 | I-Plant repair & maintenance |  |  |  | 64170.22 | 214803.33
| K000010027 | K000010027 Eco Cabin Type 1 - Ablution |  |  |  | 6292.17
| KA00010006 | KA00010006 Eco Cabin Type 1 - Ablution |  |  |  | 7625.61
| KVS0010004 | KVS0010004 CAT & Ginny Cable Locator M/Kit |  |  | 432 | 4374
| PTLT260006 | PTLT260006 Floor Polishing Machine |  |  |  | 4440
| PTLT530006 | PTLT530006 Block Cutter |  |  |  | 2850
| S3131298 | S3131298-Fuel RFID Tag Installation |  |  |  | 161
| S3131331 | S3131331-Fuel RFID Tag Installation |  |  |  | 322
| S3131479 | S3131479-Fuel RFID Tag Installation / Metal Jerry Can |  |  |  | 472
| S3131494 | S3131494-Third party inspection & Certification |  |  |  | 100
| S3131597 | S3131597-PAT Test |  |  |  | 1850
| S3131609 | S3131609-Fabrication of Steel Ramp Dorchester Hotel |  |  |  | 7374
| S3131631 | S3131631-Electrical Repairs |  |  |  | 500
| S3131666 | S3131666-Dorchester Hotel -Third party inspection & Certification |  |  |  | 770
| S3131668 | S3131668-Electrical Repairs |  |  |  | 400
| S3131730 | S3131730-Electrical Repairs |  |  |  | 25
| S3131828 | S3131828-Electrical Repairs |  |  |  | 2225
| S3131868 | S3131868-DORCHESTER Hotel - Third party inspection & Certification |  |  |  | 860
| S3131933 | S3131933-Fuel RFID Tag Installation |  |  |  | 161
| S3131942 | S3131942-Electrical Repairs |  |  |  | 1431.19
| S3131975 | S3131975-PAT Test and Plugs |  |  |  | 1020
| S3132009 | S3132009-PAT Test |  |  |  | 350
| S3132054 | S3132054-Electrical Repairs |  |  |  | 1255.29
| S3132108 | S3132108-DORCHESTER Hotel- Water pump Replaced |  |  |  | 581
| S3132186 | S3132186-Electrical Repairs |  |  |  | 2619.96
| S3132199 | S3132199-DORCHESTER HOTEL Third party inspection & Certification |  |  |  | 200
| S3132235 | S3132235-Fuel RFID Tag Installation |  |  |  | 161
| S3132242 | S3132242-Electrical Repairs |  |  |  | 1694.02
| S3132281 | S3132281-Electrical Repairs |  |  |  | 175
| S3132299 | S3132299-DORCHESTER Hotel- Beam Cutting |  |  |  | 5510
| S3132316 | S3132316-Electrical Repairs |  |  |  | 666.32
| S3132327 | S3132327-Electrical Repairs |  |  |  | 1082.53
| S3132436 | S3132436-DORCHESTER Hotel Third party inspection & Certification |  |  |  | 2100
| S3132513 | S3132513-Refurbishment of KA1/6 & KA1/27 Ablution units |  |  |  | 418.8
| S3132579 | S3132579-Electrical Repairs |  |  |  | 1569.31
| S3132712 | S3132712-Electrical Repairs |  |  |  | 421
| S3132715 | S3132715-Electrical Repairs |  |  |  | 183.1
| S3132769 | S3132769-Electrical Repairs |  |  |  | 286.67
| S3132770 | S3132770-Electrical Repairs |  |  |  | 504.57
| S3132873 | S3132873-Electrical Repairs |  |  |  | 199.97
| S3132874 | S3132874-Electrical Repairs |  |  |  | 269.22
| S3132898 | S3132898-Electrical Repairs |  |  |  | 400
| S3132899 | S3132899-Electrical Repairs |  |  |  | 504.57
| S3132900 | S3132900-Electrical Repairs |  |  |  | 1158.48
| S3132901 | S3132901-Electrical Repairs |  |  |  | 1169.59
| S3132903 | S3132903-Electrical Repairs |  |  |  | 1189.12
| S3133002 | S3133002-Signboard Cutting Remove |  |  |  | 640.67
| S3133036 | S3133036-Electrical Repairs |  |  |  | 30.6
| S3133037 | S3133037-Electrical Repairs |  |  |  | 357
| S3133131 | S3133131-Electrical Repairs |  |  |  | 131.81
| S3133139 | S3133139-Electrical Repairs |  |  |  | 400
| S3133140 | S3133140-Electrical Repairs |  |  |  | 268.05
| S3133143 | S3133143-Electrical Repairs |  |  |  | 1346.55
| S3133145 | S3133145-Electrical Repairs |  |  |  | 836.5
| S3133262 | S3133262-Electrical Repairs |  |  |  | 400
| S3133263 | S3133263-Electrical Repairs |  |  |  | 434.9
| S3133265 | S3133265-Electrical Repairs |  |  |  | 354.19
| S3133266 | S3133266-Electrical Repairs |  |  |  | 1293.47
| S3133267 | S3133267-Electrical Repairs |  |  |  | 566.71
| S3133473 | S3133473-Electrical Repairs |  |  |  | 172
| S3133475 | S3133475-Electrical Repairs |  |  |  | 162
| S3133481 | S3133481-Electrical Repairs |  |  |  | 822.69
| S3133483 | S3133483-Electrical Repairs |  |  |  | 362.82
| S3133486 | S3133486-Electrical Repairs |  |  |  | 196
| S3133536 | S3133536-Electrical Repairs |  |  |  | 393.04
| S3133537 | S3133537-Electrical Repairs |  |  |  | 180.55
| S3133538 | S3133538-Electrical Repairs |  |  |  | 530.48
| S3133539 | S3133539-Electrical Repairs |  |  |  | 1486.78
| S3133581 | S3133581-Electrical Repairs |  |  |  | 155
| S3133592 | S3133592-Electrical Repairs |  |  |  | 100
| S3133645 | S3133645-Electrical Repairs |  |  |  | 62.53
| S3133646 | S3133646-Electrical Repairs |  |  |  | 400
| S3133685 | S3133685-Fuel RFID Tag Installation |  |  |  | 161
| S3133755 | S3133755-Electrical Repairs |  |  |  | 50
| S3133756 | S3133756-Electrical Repairs |  |  |  | 65
| S3133757 | S3133757-Electrical Repairs |  |  |  | 325
| S3133780 | S3133780-Light Tool Repair |  |  |  | 655.63
| S3133781 | S3133781-Light Tool Repair |  |  |  | 643.47
| S3133782 | S3133782-Light Tool Repair |  |  |  | 295.49
| S3133827 | S3133827-Electrical Repairs |  |  |  | 65
| S3133858 | S3133858-Light Tool Repair |  |  |  | 55
| S3133859 | S3133859-Light Tool Repair |  |  |  | 55
| S3133903 | S3133903-Light Tool Repair |  |  |  | 132.38
| S3133911 | S3133911-Light Tool Repair |  |  |  | 320
| S3133976 | S3133976-Light Tool Repair |  |  |  | 2095.73
| S3133979 | S3133979-Light Tool Repair |  |  |  | 172.85
| S3134028 | S3134028-Light Tool Repair |  |  |  | 269.31
| S3134029 | S3134029-Light Tool Repair |  |  |  | 201
| S3134080 | S3134080-Light Tool Repair |  |  |  | 492.04
| S3134115 | S3134115-Light Tool Repair |  |  | 210.02 | 210.02
| S3134116 | S3134116-Light Tool Repair |  |  |  | 467.97
| S3134118 | S3134118-Light Tool Repair |  |  |  | 504.5
| S3134136 | S3134136-Light Tool Repair |  |  |  | 177.38
| S3134137 | S3134137-Light Tool Repair |  |  |  | 177.38
| S3134138 | S3134138-Light Tool Repair |  |  |  | 177.38
| S3134139 | S3134139-Light Tool Repair |  |  |  | 177.38
| S3134167 | S3134167-Light Tool Repair |  |  |  | 177.38
| S3134168 | S3134168-Light Tool Repair |  |  |  | 77.38
| S3134177 | S3134177-Fuel RFID Tag Installation |  |  |  | 161
| S3134245 | S3134245-Fuel RFID Tag Installation |  |  |  | 161
| S3134274 | S3134274-Light Tool Repair |  |  |  | 214.3
| S3134275 | S3134275-Light Tool Repair / Installation |  |  |  | 525
| S3134278 | S3134278-Light Tool Repair |  |  |  | 174.2
| S3134279 | S3134279-Light Tool Repair |  |  | 1166.92 | 1166.92
| S3134280 | S3134280-Light Tool Repair |  |  | 254.13 | 254.13
| S3134283 | S3134283-Light Tool Repair |  |  | 1202.63 | 1202.63
| S3134284 | S3134284-Light Tool Repair |  |  | 957.33 | 957.33
| S3134320 | S3134320-Light Tool Repair |  |  |  | 386
| S3134352 | S3134352-Fuel RFID Tag Installation |  |  |  | 161
| S3134368 | S3134368-Supply of Safety Net |  |  |  | 800
| S3134413 | S3134413-Third party inspection & Certification |  |  |  | 50
| S3134435 | S3134435-Light Tool Repair |  |  |  | 310
| S3134492 | S3134492-Gas Cutting Work |  |  |  | 2185
| S3134583 | S3134583-Light Tool Repair |  |  |  | 191.79
| S3134585 | S3134585-Light Tool Repair |  |  |  | 465.95
| S3134588 | S3134588-Light Tool Repair |  |  |  | 264.28
| S3134606 | S3134606-Light Tool Repair |  |  |  | 1360.96
| S3134607 | S3134607-Light Tool Repair |  |  |  | 12.92
| S3134608 | S3134608-Light Tool Repair |  |  |  | 324.33
| S3134609 | S3134609-Light Tool Repair |  |  |  | 570.66
| S3134653 | S3134653-Light Tool Repair / Pat Test |  |  |  | 5625
| S3134654 | S3134654-Light Tool Repair / Pat Test |  |  |  | 1140
| S3134669 | S3134669-Light Tool Repair |  |  |  | 166.63
| S3134681 | S3134681-Light Tool Repair |  |  |  | 336.41
| S3134682 | S3134682-Light Tool Repair |  |  |  | 236.41
| S3134762 | S3134762-Light Tool Repair |  |  |  | 495
| S3134763 | S3134763-Light Tool Repair |  |  |  | 178.92
| S3134764 | S3134764-Light Tool Repair |  |  |  | 495
| S3134771 | S3134771-Light Tool Repair |  |  |  | 187
| S3134772 | S3134772-Light Tool Repair |  |  |  | 135.52
| S3134773 | S3134773-Light Tool Repair |  |  |  | 187
| S3134774 | S3134774-Light Tool Repair |  |  |  | 377.77
| S3134775 | S3134775-Light Tool Repair |  |  |  | 400
| S3134788 | S3134788-Light Tool Repair |  |  |  | 173
| S3134789 | S3134789-Light Tool Repair |  |  |  | 248.5
| S3134899 | S3134899-Fuel RFID Tag Installation |  |  | 161 | 161
| S3134958 | S3134958-Third party inspection & Certification |  |  |  | 50
| S3135092 | S3135092-Third party inspection & Certification |  |  |  | 800
| S3135127 | S3135127-Gas Cutting Works |  |  |  | 1045
| S3135282 | S3135282-Light Tool Repair |  |  | 489.18 | 489.18
| S3135283 | S3135283-Light Tool Repair |  |  | 1058.16 | 1058.16
| S3135284 | S3135284-Light Tool Repair |  |  | 187 | 187
| S3135285 | S3135285-Light Tool Repair |  |  | 187 | 187
| S3135286 | S3135286-Light Tool Repair |  |  | 187 | 187
| S3135287 | S3135287-Light Tool Repair |  |  | 430.5 | 430.5
| S3135289 | S3135289-Light Tool Repair |  |  | 1070.09 | 1070.09
| S3135377 | S3135377-Light Tool Repair |  |  | 332.82 | 332.82
| S3135378 | S3135378-Light Tool Repair |  |  | 1179.47 | 1179.47
| S3135379 | S3135379-Light Tool Repair |  |  | 1114.97 | 1114.97
| S3304180 | S3304180-Ac Service & Repair |  |  |  | 5580
| S3304218 | S3304218-Additional Paint Requirement for the New Project - Dorchester |  |  |  | 946
| S3304220 | S3304220-Ac Repairs & Service |  |  |  | 4490
| S3304230 | S3304230-Ac Repair & Service - Client Room |  |  |  | 2220
| S3304236 | S3304236-Third Party Certificate for Concrete Bucket (KCB010) |  |  |  | 50
| S3304239 | S3304239-Ac Repairs & Service |  |  |  | 4400
| S3304272 | S3304272-Ac Repair & Service (Non KCE Asset) |  |  |  | 1830
| S3304302 | S3304302-Ac Repairs & Service (Non KCE Asset) |  |  |  | 1980
| S3304317 | S3304317-Replacement of Asian Ablution ? Bottom and Top (KA1/27) |  |  |  | 834.25
| S3304379 | S3304379-Ac Repairs & Service for client office & KCE office |  |  |  | 1120
| S3304387 | S3304387-AC Repair & Service for client office & KCE office |  |  |  | 2490
| S3304411 | S3304411-AC Repair & Service for Site office. |  |  |  | 8280
| S3304437 | S3304437-Inspection & Servicing of Fire Extinguishers |  |  |  | 6000
| S3304438 | S3304438-AC Units relocation - Sr. Staff office |  |  | 16160 | 16160
| S3304479 | S3304479-Shifting of AC units within offices |  |  | 5770 | 5770
| S3304504 | S3304504-AC Units Shifting from one office |  |  | 6270 | 6270
| S3304536 | S3304536-Forklift Charges - Material Offloading |  |  |  | 65
| S3304579 | S3304579-Forklift Charges |  |  |  | 65
| S3304589 | S3304589-Forklift Charge |  |  |  | 65
| S3304597 | S3304597-Forklift Charge |  |  |  | 65
| S3304599 | S3304599-AC Units Shifting and Repairs |  |  | 8260 | 8260
| S3304601 | S3304601-Forklift Charge |  |  |  | 65
| S3304666 | S3304666-Cubicle Door Locks |  |  |  | 424.08
| S3304667 | S3304667-Urinal Push Tap Leak Rectification |  |  |  | 977.48
| S3304758 | S3304758-Forklift Charge |  |  |  | 65
| S3304849 | S3304849-AC Relocating |  |  | 16090 | 16090
| T039101439 | T039101439 Grab Prefabricated Concrete |  |  | 1000 | 1460.27
Total |  |  |  |  | 509056.25 | 3505544.74
Manual Journals
Cost Head | Description |  | Type | Int Ref | Current | TTD
30295 | I-Waste skip |  |  |  | 10795.91 | 157096.58
|  | Timber-February 2023 | JNL | 160830 | 2921.87
|  | Mixed Waste -February 2023 | JNL | 160828 | 2850
|  | Mixed Waste -February 2023 | JNL | 160828 | 5630
|  | Demolition Waste -February 2023 | JNL | 160828 | 2920
|  | Demolition Waste -February 2023 | JNL | 160828 | 5310
|  | Demolition Waste -February 2023 | JNL | 160828 | 264.04
|  | Waste Management Fine Reversal-February 2023 | JNL | 160873 | -9100
30951 | Plant cost accruals - CVR |  |  |  |  | 0
34110 | E-Passenger motor vehicles |  |  |  | 2268 | 17300
|  | P000080687-KCE Salik Month Of February 2023 | JNL | 160438 | 296
|  | P000080685-KCE Salik Month Of February 2023 | JNL | 160438 | 104
|  | P000080690-KCE Salik Month Of February 2023 | JNL | 160438 | 252
|  | P000080681-KCE Salik Month Of February 2023 | JNL | 160438 | 328
|  | P000080684-KCE Salik Month Of February 2023 | JNL | 160438 | 40
|  | P000080696-KCE Salik Month Of February 2023 | JNL | 160438 | 272
|  | P000080701-KCE Salik Month Of February 2023 | JNL | 160438 | 368
|  | P000080667-KCE Salik Month Of February 2023 | JNL | 160438 | 280
|  | P000080664-KCE Salik Month Of February 2023 | JNL | 160438 | 224
|  | P000080658-KCE Salik Month Of February 2023 | JNL | 160438 | 104
34120 | E-Product and material transport vehicles |  |  |  | 1071 | 10613.4
|  | TA00033100-Salik For January 2023 | JNL | 160436 | 344.4
|  | TA00033109-Salik For January 2023 | JNL | 160436 | 672
|  | TA00043000-Salik For January 2023 | JNL | 160436 | 54.6
Total |  |  |  |  | 14134.91 | 185009.98
Petty Cash Charges
Cost Head | Description |  | Type | Int Ref | Current | TTD
Total
Direct Invoices
Cost Head | Description |  | Type | Int Ref | Current | TTD
30100 | I-Lifting equipment and accessories |  |  |  |  | 400
| KCEE004 | KCE (LLC) - Equipment Hire Div |  |  |  | 400
34110 | E-Passenger motor vehicles |  |  |  |  | 616.5
| GOLD010 | Golden Palace Heavy and Light |  |  |  | 616.5
34120 | E-Product and material transport vehicles |  |  |  | 1001.7 | 8503.2
| GOLD010 | Golden Palace Heavy and Light |  |  | 1001.7 | 8503.2
|  | Hire 3 Ton Pick Up-Salik January 2023 | PINN | 2302PL001593 | 1001.7
Total |  |  |  |  | 1001.7 | 9519.7
[5 empty] | 524192.86 | 3700074.42

## Subcontractor
COINS - FINANCE
Subcontract Cost 201A22002 Dorchester Hotel & Residences
Period February 2023
Subcontract Costs
Cost Head |  | Description |  |  | Int Ref |  | Ext Ref |  | Current |  | TTD
Manual Journals
| Cost Head |  | Description |  |  | Type |  | Int Ref |  | Current |  | TTD
Total
CVR Items
Cost Head |  | Description |  |  | Type |  | Int Ref |  | Current |  | TTD
Purchase Orders
Commodity |  | Description |  |  | Invoiced |  | Accrual / Rev |  | Current |  | TTD
62001A01 |  | Pest control |  |  | 1500 |  |  |  | 1500 |  | 9120
|  | CITY003 |  | City Pest Control and Building | 1500 |  |  |  | 1500 |  | 9120
Total |  |  |  |  | 1500 |  |  |  | 1500 |  | 9120
Direct Invoices
Cost Head |  | Description |  |  | Type |  | Int Ref |  | Current |  | TTD

## Overhead
COINS - FINANCE
Overhead Cost 201A22002 Dorchester Hotel & Residences
Period February 2023
CVR Items
Purchase Orders
Commodity | Description |  | Invoiced | Accrual / Rev | Current | TTD
25512A01 | Project Sign Boards |  |  | 0 | 0 | 8303
| ABDU011 | Abdulrahman Al Abdooli Advertising LLC |  | 0 | 0 | 890
| AMAL002 | Amalgam Ind. LLC |  |  | 0 | 3003
| KCEJ001 | KCE (LLC) - Joinery Division |  |  | 0 | 3660
| SALE001 | Saleem Jacobson Trading |  |  | 0 | 750
29901A01 | Small Tools/Equipment |  |  |  | 0 | 9035
| ALJA007 | Al Jas Technical Services LLC |  |  | 0 | 9035
60803A01 | Water and Electricity Charges |  |  |  | 0 | 24200
| DANL001 | Danlesco Gulf LLC |  |  | 0 | 24200
60905V02 | IT Equipment Printer Cameras etc |  | 26593.5 | -22130.5 | 4463 | 76506.2
| ASTD001 | AST Digital Print Centre |  |  | 0 | 11561.84
| NEOT001 | Neo Tech Engineering LLC | 14293.5 | -9830.5 | 4463 | 38801.5
| SCRE002 | Screencheck Technology Trading |  |  | 0 | 11300
| SHAR005 | Sharaf DG LLC |  |  | 0 | 2542.86
| ZENE003 | Zener Marine Services LLC | 12300 | -12300 | 0 | 12300
61001A01 | Safety Clothing and Equipment / PPE |  | 4771 | -1518 | 3253 | 65324
| AGSO001 | AGS Office Supplies and Trading LLC |  |  | 0 | 250
| ALAB003 | Al Abbasi Fasteners and Hardware |  |  | 0 | 14750
| ALJA007 | Al Jas Technical Services LLC | 4563 | -3018 | 1545 | 17490
| GULF019 | Gulf Metal Wires Industry LLC |  |  | 0 | 800
| KENT002 | Kent Star General Trading LLC |  |  | 0 | 2000
| SALE001 | Saleem Jacobson Trading | 208 | 1500 | 1708 | 17234
| TULI001 | Tulip Trading LLC |  |  | 0 | 12800
61003A01 | Health and Safety expenses |  |  |  | 0 | 41245.93
| ALAM004 | Al Ameen Pharmacy LLC |  |  | 0 | 8825.93
| ASGC002 | ASGC Trading Building Machines & Equipment Rental LLC |  |  | 0 | 8000
| DANA002 | Danat Alkhaleej for Safety Consultancy |  |  | 0 | 600
| SALE001 | Saleem Jacobson Trading |  |  | 0 | 23820
61111A01 | Refreshments (snacks tea coffee etc.) |  | 5924 | 269.4 | 6193.4 | 77950.15
| ALSH022 | Al Shalal Pure Drinking Water LLC | 1568 | -492 | 1076 | 15024
| CHOI001 | T Choithram and Sons LLC | 4356 | 761.4 | 5117.4 | 59111.15
| CLEA003 | Clear Ice LLC |  |  | 0 | 750
| FIND001 | Find General Trading LLC |  |  | 0 | 785
| JACK001 | Jackys Electronics LLC |  |  | 0 | 2280
61441A01 | Site Office Consumables |  | 3832 | -1582 | 2250 | 53492
| ALAB003 | Al Abbasi Fasteners and Hardware |  |  | 0 | 30960
| ALBA009 | Al Bariq Equipment LLC | 3832 | -3832 | 0 | 3832
| MANG001 | Mangal Trading Co LLC |  | 2250 | 2250 | 18700
61511A01 | Laboratory Testing & Calibaration Charges |  | 357.75 |  | 357.75 | 8487.75
| ALFA021 | Al Fajer Trading LLC |  |  | 0 | 330
| DANA002 | Danat Alkhaleej for Safety Consultancy |  |  | 0 | 6850
| GLOB007 | G Global Technologies LLC |  |  | 0 | 500
| WIMP001 | Wimpey Laboratories LLC | 357.75 |  | 357.75 | 807.75
61521A01 | Rubbish Removal |  | 43424.96 | -38000 | 5424.96 | 172728.96
| GREE044 | Green Earth Waste Collection & Transportation Services | 5424.96 |  | 5424.96 | 58728.96
| STUR001 | Sturdy Products UAE Limited | 38000 | -38000 | 0 | 114000
61531A01 | Office & Site Furniture - Including ACs |  |  | 5750 | 5750 | 88240
| ALAR007 | Al Areej AC Units Fix Cont |  |  | 0 | 31625
| ALNA007 | Al Najah Furnishings LLC |  | 5750 | 5750 | 11250
| SABI001 | Sabi Air Conditioning Trading |  |  | 0 | 45365
61531A02 | Site Est (Offices Ablutions Stores Etc) |  |  |  | 0 | 22930.5
| ALME003 | Al Mesmar Trading Co LLC |  |  | 0 | 5025
| NATI010 | National Services for Carpet a |  |  | 0 | 10368.5
| SALE001 | Saleem Jacobson Trading |  |  | 0 | 6705
| TULI001 | Tulip Trading LLC |  |  | 0 | 832
61701A01 | Printing and Stationery |  |  | -1.1369e-13 | -1.1369e-13 | 45723.46
| AGSO001 | AGS Office Supplies and Trading LLC |  | -1.1369e-13 | -1.1369e-13 | 17129.06
| ALWA002 | Al Waha Stamps LLC |  |  | 0 | 670
| ASTD001 | AST Digital Print Centre |  |  | 0 | 27009.4
| SILV004 | Silver Screen Advertising Gift |  |  | 0 | 915
Total |  |  | 84903.21 | -57211.1 | 27692.11 | 694166.95
Direct Invoices
Cost Head | Description |  | Type | Int Ref | Current | TTD
29955 | Profit Abatement-CVR |  |  |  |  | 0
| ACC | Accruals |  |  |  | -22492843
60624 | Penalties & Violations-Costed to Company |  |  |  |  | 1872
| GOLD010 | Golden Palace Heavy and Light |  |  |  | 1872
60701 | Communication expense - landline and fax usage |  |  |  | 4600 | 55432.05
| EMIR032 | Emirates Integrated Telecommun |  |  | 4600 | 52984.76
|  | DU BILL FOR JAN 2023 | PINN | 2302PL000985 | 4600
| ETIS001 | Emirates Telecommunications Gr |  |  |  | 2447.29
60703 | Communication expense - internet and data |  |  |  |  | 3750
| EMIR032 | Emirates Integrated Telecommun |  |  |  | 3750
60803 | Utilities - water external supply |  |  |  | 7700 | 13750
| DUBA003 | Dubai Aluminium PJSC |  |  | 7700 | 13750
|  | SWEET WATER SUPPLIES - JAN'2023 | PINN | 2302PL000419 | 7700
60901 | Printers & Photocopiers |  |  |  | 4427.68 | 54613.78
| NEWS001 | New Smart Office Automation LL |  |  | 4427.68 | 54613.78
|  | B/W AND COLOR COPY CHGS - DEC'2022 | PINN | 2302PL001906 | 1891.79
|  | B/W AND COLOR COPY CHGS - DEC'2022 | PINN | 2302PL001906 | 2535.89
61003 | First-aid and medical expenses |  |  |  |  | 1445
| YORK004 | York Diagnostic Laboratories D |  |  |  | 1445
61201 | Recruitment expenses |  |  |  |  | 2830
| EISA001 | Eisa Travels Agency LLC |  |  |  | 2830
Total |  |  |  |  | 16727.68 | 133692.83
Petty Cash Charges
Cost Head | Description |  | Type | Int Ref | Current | TTD
60621 | Other fee - charges |  |  |  | 20640 | 55742.52
|  | 04193-MURALI N-NOC CHARGES | PCP | FEB/11992/10 | 5250
|  | 04193-MURALI N-201A22002-RTA FINE | PCP | FEB/12016/06 | 5000
|  | 04193-MURALI-201A22002-RTA INSPECTION | PCP | FEB/12016/08 | 10040
|  | 27743-CHRIS McCANN-201A22002 | PCP | FEB/12016/15 | 350
60811 | Utilities - office and factory electricity and water |  |  |  |  | 46680
61003 | First-aid and medical expenses |  |  |  | 11070 | 11070
|  | 29076-RAJESH ROY_MEIDCAL EXPENSES | PDD | 29076-RAJESH ROY_MEIDCAL EXPENSES | 10500
|  | 29076-RAJESH ROY-201A22002 | PCP | FEB/12016/05 | 570
61111 | Refreshments (snacks, tea, coffee etc.) |  |  |  | 850.5 | 32043.55
|  | 27743-CHRIS McCANN-201A22002 | PCP | FEB/12016/15 | 850.5
61131 | COS Staff welfare expense |  |  |  |  | 4313.56
62001 | Miscellaneous expenses |  |  |  |  | 700
Total |  |  |  |  | 32560.5 | 150549.63
Manual Journals
Cost Head | Description |  | Type | Int Ref | Current | TTD
60621 | Other fee - charges |  |  |  | 120 | 82788.81
|  | Credit Card transactions_9134-DM - Fees for temporary BCC-202300105905-24/02/2023 (FEB-2023) | JNL |  | 120
60701 | Communication expense - landline and fax usage |  |  |  | 352.04 | 25555.04
|  | Tel Cost-0565456086-HIRED--SANEESH MOHAN-100 (JAN-2023) | JNL |  | 194.54
|  | Tel Cost-0509394368- FACE STATION (JAN-2023) | JNL |  | 105
|  | Tel Cost-0501894373-FACE STATION (JAN-2023) | JNL |  | 52.5
60703 | Communication expense - internet and data |  |  |  |  | 1079.17
60811 | Utilities - office and factory electricity and water |  |  |  |  | 5064.85
60902 | Specialist Software |  |  |  | 280 | 49700
|  | MAIL BOX SERVICES - FEB 23 | JNL |  | 280
61001 | Health and safety - material items |  |  |  |  | 1490
61111 | Refreshments (snacks, tea, coffee etc.) |  |  |  |  | 2193.67
61201 | Recruitment expenses |  |  |  |  | -2830
61311 | Rent - accommodation |  |  |  | 414.29 | 533.32
|  | Sub contract employees accomodation | JNL |  | 414.29
62001 | Miscellaneous expenses |  |  |  |  | 100
Total |  |  |  |  | 1166.33 | 165674.86
Plant Charges
Cost Head | Description |  | Type | Int Ref | Current | TTD
60905 | Computers & Accessories |  |  |  | 1148 | 11060
| ITA0002036 | ITA0002036 Samsung Galaxy Tab Active Pro |  |  | 0 | 0
| ITA0002123 | ITA0002123 Samsung Galaxy Tab Active Pro |  |  | 0 | 0
| ITA0002186 | ITA0002186 Samsung Galaxy Tab Active Pro |  |  | 168 | 168
| ITA0003005 | ITA0003005 Face Station 2 - Identification Device |  |  | 196 | 2303
| ITA0003060 | ITA0003060 Face Station 2 - Identification Device |  |  | 196 | 2198
| ITA0003063 | ITA0003063 Face Station 2 - Identification Device |  |  | 196 | 1995
| ITA0003075 | ITA0003075 Face Station 2 - Identification Device |  |  | 196 | 2198
| ITA0003084 | ITA0003084 Face Station 2 - Identification Device |  |  | 196 | 2198
Total |  |  |  |  | 1148 | 11060
Stock Issues
Cost Head | Description |  | Type | Int Ref | Current | TTD
60902 | Specialist Software |  |  |  |  | 2399
| 60906V01-010017 | Bluebeam Revu Extreme Perpetual License Windows OS |  |  |  | 2399
60905 | Computers & Accessories |  |  |  | 1229.69 | 26281.17
| 24325V01-010002 | Access Point Aruba AP 515 - New |  |  |  | 3897
| 24325V01-010004 | Mounting Kit Aruba AP 515 - New |  |  |  | 66
| 24325V01-020002 | Access Point Aruba AP 515 - Used |  |  |  | 0
| 60905V01-010006 | Keyboard & Mouse Logitec Wireless Black - New |  |  |  | 1375
| 60905V01-010008 | Mouse Logitec Wireless Black - New |  |  | 50 | 1250
| 60905V01-010011 | Cable HDMI 2m - New |  |  |  | 72.5
| 60905V01-010013 | Cable HDMI 5m - New |  |  |  | 110
| 60905V01-010019 | Cable Cat6 5m - New |  |  |  | 70.44
| 60905V01-010020 | Cable Roll 305m - New |  |  | 414.92 | 2250.82
| 60905V01-010031 | RJ45 connector - New |  |  |  | 8.26
| 60905V01-010037 | Monitor 24" 1080p E Series - New | ISS |  | 672.48 | 5560.23
| 60905V01-010038 | Monitor HP E22 G4 FHD - New |  |  |  | 4566.94
| 60905V01-010041 | Samsung Tablet Case Cover - New |  |  |  | 380
| 60905V01-010043 | Laptop Bag HP - New |  |  | 92.29 | 2817.25
| 60905V01-010045 | EVOLIS-YMCKO Color Ribbon - New |  |  |  | 660
| 60905V01-010046 | EVOLIS Smart Cards - Mifare 1K - New |  |  |  | 1120.02
| 60905V01-010050 | USB A Wi-Fi adapter - New |  |  |  | 582
| 60905V01-010052 | Crucial SSD Hard disk - New |  |  |  | 786.28
| 60905V01-010053 | Bracket for Crucial SSD Hard disk - New |  |  |  | 17.5
| 60905V01-010054 | New Onsite installation of new SSD with OS |  |  |  | 95
| 60909V01-010018 | Mobile Handset Samsung A13 Black ? New |  |  |  | 595.93
60906 | Standard Software |  |  |  |  | 8847
| 60906V01-010017 | Bluebeam Revu Extreme Perpetual License Windows OS |  |  |  | 7197
| 60906V01-010018 | Bluebeam Revu Extreme Annual Maintenance & Support Windows OS |  |  |  | 1650
60909 | Telecomunication Services |  |  |  | 1756.65 | 37918.51
| 24325V01-010002 | Access Point Aruba AP 515 - New |  |  |  | 3897
| 24325V01-010004 | Mounting Kit Aruba AP 515 - New |  |  |  | 66
| 24325V01-010012 | Aruba Central AP Foundation 1y Subscription - New |  |  |  | 3651.91
| 24325V01-020005 | Network Switch Cisco SG350 28 Port - Used |  |  |  | 0
| 60909V01-010008 | Sim Card Etisalat Standard - New |  |  |  | 0
| 60909V01-010012 | Mobile Handset Samsung A12 Black - New |  |  |  | 4910.1
| 60909V01-010014 | Mobile Handset Samsung A52 Black - New |  |  |  | 1255.24
| 60909V01-010015 | Mobile Handset Nokia 225 - New |  |  |  | 340
| 60909V01-010018 | Mobile Handset Samsung A13 Black ? New | ISS |  | 1756.65 | 22563.26
| 60909V01-010019 | Mobile Handset Samsung A53 ? New |  |  |  | 1235
61001 | Health and safety - material items |  |  |  | 27612.2 | 154670.42
| 46181503-A01361 | Blue Pant/Shirt 180 Gsm Full Sleeve -2XL | ISS |  | 1474.05 | 5475.02
| 46181503-A01362 | Blue Pant/Shirt 180 Gsm Full Sleeve -3XL | ISS |  | 564.48 | 1834.56
| 46181503-A01363 | Blue Pant/Shirt 180 Gsm Full Sleeve -4XL | ISS |  | 77.49 | 387.45
| 46181503-A01364 | Blue Pant/Shirt 180 Gsm Full Sleeve -Large | ISS |  | 3650.02 | 11535
| 46181503-A01365 | Blue Pant/Shirt 180 Gsm Full Sleeve -Medium | ISS |  | 6164.51 | 26325.93
| 46181503-A01366 | Blue Pant/Shirt 180 Gsm Full Sleeve - Small | ISS |  | 5382 | 14188.75
| 46181503-A01367 | Blue Pant/Shirt 180 Gsm Full Sleeve -XL | ISS |  | 2243.79 | 8250.65
| 46181503-A01383 | Beige Pant/Shirt 180 Gsm Full Sleeve for Chargehand - 2XL | ISS |  | 114 | 570
| 46181503-A01384 | Beige Pant/Shirt 180 Gsm Full Sleeve for Chargehand - 3XL | ISS |  | 114 | 114
| 46181503-A01386 | Beige Pant/Shirt 180 Gsm Full Sleeve for Chargehand - Large | ISS |  | 342 | 1026
| 46181503-A01387 | Beige Pant/Shirt 180 Gsm Full Sleeve for Chargehand - Medium | ISS |  | 114 | 1596
| 46181503-A01388 | Beige Pant/Shirt 180 Gsm Full Sleeve for Chargehand - Small |  |  |  | 114
| 46181503-A01389 | Beige Pant/Shirt 180 Gsm Full Sleeve for Chargehand - XL |  |  |  | 342
| 46181504-A20645 | Hand Gloves 15g Nylon + Spandex with Washed Micro Foam Size 8 | ISS |  | 790 | 6262.26
| 46181504-A20646 | Hand Gloves 15g Nylon + Spandex with Washed Micro Foam Size 9 | ISS |  | 3947.65 | 23574.04
| 46181504-A20647 | Hand Gloves 15g Nylon + Spandex with Washed Micro Foam Size 10 |  |  | 394.21 | 8713.17
| 46181504-A20648 | Hand Gloves 15g Nylon + Spandex with Washed Micro Foam Size 11 |  |  |  | 375
| 46181605-A04415 | Safety Shoe For Staff 59351 Size 38 |  |  |  | 240
| 46181605-A04416 | Safety Shoe For Staff 59351 Size 39 |  |  |  | 80
| 46181605-A04418 | Safety Shoe For Staff 59351 Size 41 |  |  |  | 640
| 46181605-A04419 | Safety Shoe For Staff 59351 Size 42 |  |  |  | 1120
| 46181605-A04420 | Safety Shoe For Staff 59351 Size 43 | ISS |  | 80 | 1120
| 46181605-A04421 | Safety Shoe For Staff 59351 Size 44 |  |  |  | 560
| 46181605-A04422 | Safety Shoe For Staff 59351 Size 45 |  |  | 80 | 240
| 46181605-A04423 | Safety Shoe For Staff 59351 Size 46 |  |  |  | 80
| 46181605-A18968 | Safety Shoe For Staff 59351 Size 40 |  |  |  | 560
| 46181605-A18970 | Safety Shoe for workers Saudi 59102 SIZE 38 |  |  | 65 | 455
| 46181605-A18971 | Safety Shoe for workers Saudi 59102 SIZE 39 | ISS |  | 130 | 2015
| 46181605-A18972 | Safety Shoe for workers Saudi 59102 SIZE 40 | ISS |  | 325 | 5460
| 46181605-A18973 | Safety Shoe for workers Saudi 59102 SIZE 41 |  |  | 325 | 4030
| 46181605-A18974 | Safety Shoe for workers Saudi 59102 SIZE 42 | ISS |  | 715 | 10530
| 46181605-A18975 | Safety Shoe for workers Saudi 59102 SIZE 43 |  |  | 325 | 4940
| 46181605-A18976 | Safety Shoe for workers Saudi 59102 SIZE 44 |  |  | 130 | 2275
| 46181605-A18977 | Safety Shoe for workers Saudi 59102 SIZE 45 | ISS |  | 65 | 715
| 46181605-A18978 | Safety Shoe for workers Saudi 59102 SIZE 46 |  |  |  | 195
| 46181701-A04402 | Safety Helmet High Ev Yellow - 6 Point Textile Tapes System. Slip Ratche |  |  |  | 26
| 46181804-A04397 | Safety Goggles - Clear - Globus - Riley - Bm08 |  |  |  | 2870.98
| 46181804-A04398 | Safety Goggles - Grey - Globus - Riley - Bm08 |  |  |  | 65.56
| 46181804-A19383 | Safety Goggles - Clear - Bm10 |  |  |  | 51.47
| 46181804-A19384 | Safety Goggles - Clear - Riley - Pn-RLY00071 |  |  |  | 760.21
| 46181804-A19385 | Safety Goggles - Grey - Riley - Pn-RLY00072 |  |  |  | 509.49
| 46182001-A20175 | Disposable Face Mask Blue 3 Ply (1x50) Local |  |  |  | 4107.88
| 71001Z01-010011 | Fire Extinguisher Inspection Tag |  |  |  | 340
61131 | COS Staff welfare expense |  |  |  |  | 12314.32
| 51211706-A00348 | Aqualyte Solution 80Grmx100Satchets/Ct |  |  |  | 230.35
| 51211706-A00349 | Aqualyte Solution 800Grmx10Satchets/Ct |  |  |  | 12083.97
61701 | Stationary |  |  |  |  | 542.5
| 14111509-A19706 | Business Cards |  |  |  | 120
| 71701Z01-01005 | Khansaheb Note Pad A5 |  |  |  | 275
| 71701Z01-01006 | Khansaheb Note Pad A4 |  |  |  | 147.5
Total |  |  |  |  | 30598.54 | 242972.92
[5 empty] | 109893.16 | 1398117.19