## Summary
No | Description | Previous | This Month | Cumulative
| Original Scope | 552871.22 | 145362.2954 | 698233.5154
| Variations | 281196 | 7464 | 288660
|  | 834067.22 | 152826.2954 | 986893.5154
| Advance Payment | 133278.25 |  | 133278.25
| Advance Payment Recovery | -83406.722 | -15282.6295 | -98689.3515
|  | 883938.748 | 137543.6659 | 1021482.4139

## Breakdown
No | Description | Qty | Unit | Rate | Amount | Previous % | This Month % | Cumulative % | Previous Amount | This Month Amount | Cumulative Amount | Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8
| WA: PS-025 | [10 empty] | Column8: #DIV/0!
1 | Metal Architrave cladding for TB-21 Door ME-01 340mm width 2400mm H x 1920mm (10mm thick) | 25 | LS | 4144 | 103600 |  | 0% |  | 0 | 0 | 0 | Column8: 0
2 | Metal Architrave cladding for TB-22 ME-03 50mm Width 2250mm Hx 1100mm (10mm thickness) | 95 | LS | 479 | 45505 |  | 0% |  | 0 | 0 | 0 | Column8: 0
3 | Metal cladding around the wooden panel ME-01 85mm Width 2405mm Hx 1244mm (10mm thickness) | 9 | LS | 777 | 6993 |  | 0% |  | 0 | 0 | 0 | Column8: 0
4 | Metal cladding around the wooden panel ME-01 85mm Width 2405mm Hx 940mm (10mm thickness) | 2 | LS | 752 | 1504 |  | 0% |  | 0 | 0 | 0 | Column8: 0
5 | Metal cladding around the wooden panel ME-01 85mm width 2510mm Hx750mm (10mm thickness) | 126 | LS | 741 | 93366 |  | 0% |  | 0 | 0 | 0 | Column8: 0
6 | Metal cladding around the Ceiling wooden panel ME-01 85mm width 2200m Lx750mm (10mm thickness) | 268 | LS | 174 | 46632 |  | 0% |  | 0 | 0 | 0 | Column8: 0
7 | Metal cladding around the Wall Paper/Stone fature ME-01 108/126mm width 2510mm H | 2665 | LS | 176 | 469040 | 70% | 20% | 90% | 328328 | 93808 | 422136 | Column8: 0
8 | Metal Architraves in the Room Entrance Doors ME-01 130mm Width 2440mm Hx1100mm | 225 | LS | 975 | 219375 | 70% | 0% | 70% | 153562.5 | 0 | 153562.5 | Column8: 0
| WA: PS-028 | [10 empty] | Column8: #DIV/0!
| Supply and installation of Metal Wall Cladding including all necessary framing, fitting, fixing, backing framing support, finishes, decoration, provision of the Niche etc and the like all in accordance with drawings and specifications. | [10 empty] | Column8: #DIV/0!
7 | Metal Wall Cladding around lift entrance to L1 Corridor; Type HTL-ME-06, Gun Metal Patina, Satin varnish( ref drg. P18-IDR-H-L1-101B-12A- rev. A), Material : SS sht. grade 304, Thickness considered max. 1. 5 mm thk | 21 | m2 | 1508.4105 | 31676.62 |  | 0 |  | 0 | 0 | 0 | Column8: 0
8 | Metal Wall Cladding around doors to L1 Corridor; Type HTL-ME-01; Brass, Brushed bronze patina. Material : SS sht grade 304, Thickness considered max. 1. 5 mm thk. | 4 | m2 | 1570.495 | 6281.98 |  | 0 |  | 0 | 0 | 0 | Column8: 0
[9 empty] | 0 | 0 | 0 | Column8: #DIV/0!
| Metal Finishes Package | [7 empty] | 0 | 0 | 0 | Column8: #DIV/0!
| Floor finishes | [7 empty] | 0 | 0 | 0 | Column8: #DIV/0!
| Metal finish supplied and installed complete | [7 empty] | 0 | 0 | 0 | Column8: #DIV/0!
A | 7mm thick metal joint HTL-ME-04 ref, L28-GYM-DD-300 detail 1 (Supply only) | 2 | m | 117 | 234 |  | 0 |  | 0 | 0 | 0 | Column8: 0
| Addional Work | [7 empty] | 0 | 0 | 0 | Column8: #DIV/0!
A | 7mm thick metal joint HTL-ME-04 ref, L28-GYM-DD-300 detail 1 to Jib door (Supply only) | 1 | m | 117 | 117 |  | 0 |  | 0 | 0 | 0 | Column8: 0
[9 empty] | 0 | 0 | 0 | Column8: #DIV/0!
4 | Supply and fixing of metal skirting Type baseboard HTL-ME-01: 150mm High | 16.61 | m | 300 | 4983 |  | 0 |  | 0 | 0 | 0 | Column8: 0
| Wall finish including preparation of substrate, render, filler, primer, undercoat(s), finish coats, all necessary fittings, fixings accessories to complete all in accordance with the drawings and specifications | [7 empty] | 0 | 0 | 0 | Column8: #DIV/0!
| Level 1 | [7 empty] | 0 | 0 | 0 | Column8: #DIV/0!
| Ball Room | [7 empty] | 0 | 0 | 0 | Column8: #DIV/0!
D | Metal Beam 150 x 100 mm; type HTL-ME-06 | 24 | m | 842.02 | 20208.48 |  | 0 |  | 0 | 0 | 0 | Column8: 0
E | Metal frame beam -150 mm width | 28 | m | 711.86 | 19932.08 |  | 0 |  | 0 | 0 | 0 | Column8: 0
F | Metal Beam 700 x 100 mm; type HTL-ME-06 | 20 | m | 2230.17 | 44603.4 |  | 0 |  | 0 | 0 | 0 | Column8: 0
G | Metal Beam 700 x 200 mm; type HTL-ME-06 | 24 | m | 2509.54 | 60228.96 |  | 0 |  | 0 | 0 | 0 | Column8: 0
H | Metal " L" Beam 130 x 130 mm; type HTL-ME-06 | 47 | m | 487.84 | 22928.48 |  | 6.685 | 6.685 | 0 | 3261.209 | 3261.209 | Column1: 70% is paid since MOS; Column7: 4658.87; Column8: 9.55
#DIV/0!
| Wall finish including preparation of substrate, (Cont'd) | [10 empty] | Column8: #DIV/0!
| Meeting Room -01 | [10 empty] | Column8: #DIV/0!
A | Metal" C" Beam 100 x 200 mm; type HTL-ME-06 | 12 | m | 881.92 | 10583.04 |  | 0 |  |  |  |  | Column8: 0
B | Metal " L" Beam 130 x 130 mm; type HTL-ME-06 | 32 | m | 487.84 | 15610.88 | 24 | 7.32 | 31.32 | 11708.16 | 3570.9888 | 15279.1488 | Column1: no approved WIR; Column8: 0
#DIV/0!
| Meeting Room -02 | [10 empty] | Column8: #DIV/0!
K | Metal" L" Beam 130 x 130 mm; type HTL-ME-06 | 54 | m | 487.84 | 26343.36 | 40.5 | 11.7 | 52.2 | 19757.52 | 5707.728 | 25465.248 | Column8: 0
L | Metal "U" Beam 100 x 200 mm; type HTL-ME-06 | 42 | m | 881.92 | 37040.64 | [6 empty] | Column8: 0
#DIV/0!
| Corridor | [10 empty] | Column8: #DIV/0!
S | Lit skirting 100 mm high; type HTL-ME-03 | 95 | m | 132 | 12540 |  | 79.87 | 79.87 | 0 | 10542.84 | 10542.84 | Column8: 0
T | Stringer at staircase side; type HTL-ME-04 | 1 | m2 | 970 | 970 |  | 0 |  |  |  |  | Column8: 0
#DIV/0!
| Hall | [10 empty] | Column8: #DIV/0!
C | Metal" L" Beam 130 x 130 mm; type HTL-ME-06 | 71 | m | 487.84 | 34636.64 | 53.25 | 10.47 | 63.72 | 25977.48 | 5107.6848 | 31085.1648 | Column8: 0
#DIV/0!
| Prefunction | [10 empty] | Column8: #DIV/0!
P | Metal" L" Beam 130 x 130 mm; type HTL-ME-06 | 69 | m | 487.84 | 33660.96 |  | 43.4 | 43.4 | 0 | 21172.256 | 21172.256 | Column8: 0
#DIV/0!
| Break out space | [10 empty] | Column8: #DIV/0!
A | Metal " L" Beam 130 x 130 mm; type HTL-ME-06 | 37 | m | 487.84 | 18050.08 | 27.75 | 3.57 | 31.32 | 13537.56 | 1741.5888 | 15279.1488 | Column8: 0
[7 empty] | 0 |  | 0 | 0 | 0 | Column8: #DIV/0!
| Ballroom male toilet | [5 empty] | 0 |  | 0 | 0 | 0 | Column8: #DIV/0!
K | Metal frame ; type in HTL-ME-04 | 3 | m2 | 1550 | 4650 |  | 0 |  | 0 | 0 | 0 | Column8: 0
[7 empty] | 0 |  | 0 | 0 | 0 | Column8: #DIV/0!
P | Metal baseboard; type HTL-MT-04, 150 mm H | 2 | m | 525 | 1050 |  | 0 |  | 0 | 0 | 0 | Column8: 0
[7 empty] | 0 |  | 0 | 0 | 0 | Column8: #DIV/0!
| Ballroom female toilet | [5 empty] | 0 |  | 0 | 0 | 0 | Column8: #DIV/0!
I | 7 mm brass strip ; type HTL-ME-04 | 15 | m | 301 | 4515 |  | 0 |  | 0 | 0 | 0 | Column8: 0
[7 empty] | 0 |  | 0 | 0 | 0 | Column8: #DIV/0!
| Handrail | [5 empty] | 0 |  | 0 | 0 | 0 | Column8: #DIV/0!
J | Handrail, wallmounted, in HTL-ME-03 | 2 | m | 375 | 750 |  | 0 |  | 0 | 0 | 0 | Column8: 0
K | Handrail, floor mounted, in HTL-ME-03 | 3 | m | 900 | 2700 |  | 0 |  | 0 | 0 | 0 | Column8: 0
[7 empty] | 0 |  | 0 | 0 | 0 | Column8: #DIV/0!
| Wall Finishes | [5 empty] | 0 |  | 0 | 0 | 0 | Column8: #DIV/0!
| Ballroom female toilet | [5 empty] | 0 |  | 0 | 0 | 0 | Column8: #DIV/0!
O | Metal baseboard; HTL -ME -04 | 10 | m | 529 | 5290 |  | 0 |  | 0 | 0 | 0 | Column8: 0
Q | Backlit recessed metal baseboard; type HTL-ME-04 overall size 430x1930x740mm (490mm wide,150mmH) 5mm thick SS 304 | 1 | nos | 4750 | 4750 |  | 0 |  | 0 | 0 | 0 | Column8: 0
[7 empty] | 0 |  | 0 | 0 | 0 | Column8: #DIV/0!
C | Lit skirting 100 mm high; type HTL-ME-03 | 3 | m | 250 | 750 |  | 1.8 | 1.8 | 0 | 450 | 450 | Column8: 0
[9 empty] | 552871.22 | 145362.2954 | 698233.5154 | Column8: #DIV/0!
#DIV/0!
| Variations | [10 empty] | Column8: #DIV/0!
| WA: PS-035 | [10 empty] | Column8: #DIV/0!
| Supply and Installation of Secondary Steel Supports for Stone Claddings as per the highlighted drawings at ball room | 1 | LS | 300000 | 300000 | 90% | 0% | 90% | 270000 | 0 | 270000 | Column7: No approved WIR; Column8: #VALUE!
#DIV/0!
| Supply and Installation of Metal Work as per the highlighted drawings - (RESIDENTIAL AMENITIES, LOBBIES AND LIFT LOBBIES (B1, B2, GF, L2, L4 and L23)) | 1 | LS | 200114.69 | 200114.69 |  | 0% |  | 0 | 0 | 0 | Column8: 0
#DIV/0!
| Supply and Installation of Automatic Glass sliding Door as per the highlighted drawings (RESIDENTIAL AMENITIES - GROUND FLOOR) | 1 | LS | 24880 | 24880 | 45% | 30% | 75% | 11196 | 7464 | 18660 | Column7: No approved WIR; Column8: #VALUE!
#DIV/0!
| Variations (no WA) | [10 empty] | Column8: #DIV/0!
| Ceiling Cladding : L 185 x 200 x 1.0 mm thk x 31.27 m | 12.04 | m | 1630 | 19625.2 |  | 0% |  | 0 | 0 | 0 | Column8: 0
| Ceiling Cladding : L 350 x 200 x 1.0 mm thk x 15.64 m | 8.6 | m | 1630 | 14018 |  | 0% |  | 0 | 0 | 0 | Column8: 0
| Ceiling Cladding : L 325 x 100 x 1.0 mm thk x 52.69 m | 22.39 | m | 1630 | 36495.7 |  | 0% |  | 0 | 0 | 0 | Column8: 0
| Ceiling Cladding : L 300 x 100 x 1.0 mm thk x 15.64 | 6.26 | m | 1630 | 10203.8 |  | 0% |  | 0 | 0 | 0 | Column8: 0
| L - Profile in HTL-ME-03 : 202 x 45 x 67 x 1.2 mm, (HTL-ME-03, SS grade 304 in Mirror finish)) | 19.21 | m2 | 1475 | 28334.75 |  | 0% |  | 0 | 0 | 0 | Column8: 0
#DIV/0!
| Fabrication and supply of floor trim based on enclosed drawing. Material, SS grade 304 Finish: ME-06, Thickness Considered 8 mm thk. | [10 empty] | Column8: #DIV/0!
#DIV/0!
| Floor trim @ Meeting Room 1 | 21 | m | 150 | 3150 |  | 14.7 | 14.7 | 0 | 2205 | 2205 | Column1: No WIR; Column8: 0
| Floor Trim @ Break-out Space | 79 | m | 150 | 11850 |  | 55.3 | 55.3 | 0 | 8295 | 8295 | Column1: No WIR; Column8: 0
| Floor Trim @ Meeting Room 2 | 54 | m | 150 | 8100 |  | 37.8 | 37.8 | 0 | 5670 | 5670 | Column1: No WIR; Column8: 0
| Floor Trim @ Hall | 30 | m | 150 | 4500 |  | 21 | 21 | 0 | 3150 | 3150 | Column1: No WIR; Column8: 0
| Floor Trim @ Prefunction | 29 | m | 150 | 4350 |  | 20.3 | 20.3 | 0 | 3045 | 3045 | Column1: No WIR; Column8: 0
| Floor Trim @ ball Room | 31 | m | 151 | 4681 |  | 21.7 | 21.7 | 0 | 3276.7 | 3276.7 | Column1: No WIR; Column8: 0
| Floor Trim @ Lift Lobby | 30 | m | 152 | 4560 |  | 21 | 21 | 0 | 3192 | 3192 | Column1: No WIR; Column8: 0
[9 empty] | 281196 | 7464 | 288660 | Column8: #DIV/0!
| Total | [7 empty] | 834067.22 | 181659.9954 | 1015727.2154 | Column8: #DIV/0!
Note on I9: Himal Kosala: No WIR found, Only Approve upto 70%
Note on I10: Himal Kosala: No WIR found, Only Approve upto 70%
Note on I77: Himal Kosala: Until OME rate approval