## Summary
SN | Description | Total Scope | Balance Scope | Valuation at WFA | Previous | This Month | Cumulative
01 | Contract Works | 1600000 | 0 | 533925 | 283571.5314 | 250314.5484 | 533886.0798 | 1067811.0798
02 | Variations (old) | 485255 | 472082 | 13173 | 60270.7675 | 65003.0503 | 125273.8178 | 138446.8178
| Total Value of Work Done |  | 472082 | 547098 | 343842.299 | 315317.5986 | 659159.8976 | 1206257.8976
03 | New Variations | 1152852.8325 | 1152852.8325 | 0 | 390276.4829 | 22658.6837 | 412935.1666
| Total Value of Work Done |  | 1624934.8325 | 547098 | 734118.7819 | 337976.2823 | 1072095.0642 |  | 1619193.0642
04 | Advance Payment |  | 10% |  | 153815.69 | 0 | 153815.69
05 | Advance Payment Recovery |  | 10% |  | -73411.8782 | -33797.6282 | -107209.5064
| TOTAL |  |  |  | 814522.5937 | 304178.6541 | 1118701.2477

## Progress Bill
PROGRESS BOQ
Item | Description | Qty. | Unit | Rate | Amount | OCI - Certified |  | Balance Works |  |  | Pervious Work Certified |  |  | Balance Works |  |  | This Month Workdone |  |  | Cumulative |  |  | Balance Works
|  |  |  | Rate | Amount | Progress % | Amount | Progress % | Qty | Amount | Pervious % | Pervious Qty | Amount | Progress % | Qty | Amount | Progress % | Qty | Amount | Progress % | Qty | Amount | Progress % | Qty | Amount
DESIGN AND BUILD OF TERRACO SYSTEM
[8 empty] | 100% | [5 empty] | 100% | [8 empty] | 100%
EIFS WITH TERRACO RENDER SYSTEM
EIFS with TERRACO System, mineral wool, Adhesive, groove requirement,including all necessary framing, fitting, fixing, backing framing support, decoration, Primer, Basecoat and Final coat etc and the like all in accordance with drawings and specifications.
ON BLOCKWORK / CONCRETE WALL
A | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 75mm | 876 | m2 | 295 | 258420 |  |  | 100% | 876 | 258420 | 4.65% | 40.7312 | 12015.7187 | 95.35% | 835.2688 | 246404.2813 | 3.734% | 32.7067 | 9648.486 | 8.383% | 73.438 | 21664.2047 | 91.62% | 802.562 | 236755.7953
B | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 100mm | 692 | m2 | 319 | 220748 | 89.8% | 198241.4271 | 10.2% | 70.5535 | 22506.5729 | 89.43% | 618.8872 | 197425.0167 | 10.57% | 73.1128 | 23322.9833 | -15.35% | -106.2372 | -33889.6713 | 74.08% | 512.65 | 163535.3453 | 25.92% | 179.35 | 57212.6547
C | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 150mm | 266 | m2 | 347 | 92302 |  |  | 100% | 266 | 92302 |  | 0 | 0 | 100% | 266 | 92302 | 0% | 0 | 0 |  | 0 | 0 | 100% | 266 | 92302
D | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 200mm | 682 | m2 | 380 | 259160 | 95.74% | 248117.6104 | 4.261% | 29.0589 | 11042.3896 | 99.13% | 676.0951 | 256916.1456 | 0.8658% | 5.9049 | 2243.8544 | 0% | 0 | 0 | 99.13% | 676.0951 | 256916.1456 | 0.8658% | 5.9049 | 2243.8544
E | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 275mm | 176 | m2 | 415 | 73040 |  |  | 100% | 176 | 73040 |  | 0 | 0 | 100% | 176 | 73040 | 0% | 0 | 0 |  | 0 | 0 | 100% | 176 | 73040
F | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 300mm | 854 | m2 | 435 | 371490 | 20.26% | 75252.564 | 79.74% | 681.0056 | 296237.436 | 33.99% | 290.3156 | 126287.2825 | 66.01% | 563.6844 | 245202.7175 | 53.1% | 453.4329 | 197243.2976 | 87.09% | 743.7485 | 323530.5801 | 12.91% | 110.2515 | 47959.4199
G | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 400mm | 422 | m2 | 500 | 211000 | 31.07% | 65567.88 | 68.93% | 290.8642 | 145432.12 | 32% | 135.04 | 67520 | 68% | 286.96 | 143480 | 34.21% | 144.3649 | 72182.4362 | 66.21% | 279.4049 | 139702.4362 | 33.79% | 142.5951 | 71297.5638
STAND ALONE EIFS SYSTEM WITH NECESSARY BACK FRAMING SUPPORT
H | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 75mm | 88 | m2 | 400 | 35200 |  |  | 100% | 88 | 35200 |  | 0 | 0 | 100% | 88 | 35200 | 0% | 0 | 0 |  | 0 | 0 | 100% | 88 | 35200
J | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 300mm | 86 | m2 | 450 | 38700 |  |  | 100% | 86 | 38700 | 90% | 77.4 | 34830 | 10% | 8.6 | 3870 | 10% | 8.6 | 3870 | 100% | 86 | 38700 | 0% | 0 | 0
K | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 400mm | 24 | m2 | 525 | 12600 |  |  | 100% | 24 | 12600 | 90% | 21.6 | 11340 | 10% | 2.4 | 1260 | 10% | 2.4 | 1260 | 100% | 24 | 12600 | 0% | 0 | 0
TERRACO RENDER SYSTEM
TERRACO Render System, Adhesive, groove requirement, including all necessary framing, fitting, fixing, backing framing support, Primer, Basecoat and Final coat decoration, etc and the like all in accordance with drawings and specifications.
ON BLOCKWORK / CONCRETE WALL
A | TERRACO RENDER System (TERRACO acid wash finishes) | 1298 | m2 | 175 | 227150 | 5.909% | 13423.2 | 94.09% | 1221.296 | 213726.8 | 78.29% | 1016.225 | 177839.3679 | 21.71% | 281.775 | 49310.6321 | 0% | 0 | 0 | 78.29% | 1016.225 | 177839.3679 | 21.71% | 281.775 | 49310.6321
| Discount |  |  |  | -199810 | 33.37% | -66677.2725 | 66.63% | 0 | -133132.7275 | 33.37% | 0 | -66677 | 66.63% | 0 | -133133.403 | 0% | 0 | 0 | 33.37% | 0 | -66677 | 66.63% | 0 | -133133
| TOTAL |  |  |  | 1600000 |  | 0 |  |  | 0 |  |  | 817496.5314 |  |  | 0 |  |  | 250314.5484 |  | 66.74% | 1067811.0798 |  |  | 0
Note on AA15: Himal Kosala: Robarts Qty 217.79, need to check
Note on AA23: Himal Kosala: 195.53 m2 WA-PS005 R2 Completed qty
Note on AA25: Himal Kosala: 141.46 m2 WA-PS005 R2 Completed qty

## 75MM-EIFS
DETAILED STATUS REPORT
Client Name |  | : | Omniyat Investments & Management LLC
Project Name |  | : | Dorchester Hotel (PLOT 18)
Main Contractor |  | : | Khansaheb civil engineering llc
Scope of works |  | : | External Insulation Finishing System (EPS)
WORK BREAKDOWN : 70% UPTO EPS BOARDS, 20% UPTO BASECOAT, 10% PAINT
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
75MM -EIFS | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | LEVEL-23,Elevation-0, | JOT-AX-SD-L23-00009_02 | C-E/10-11 | WALL INS. | a | 1 | 12.25 | 4.75 | 58.1875 |  | 0 | 0 | 0 | 0 | 58.1875 | 80% | 46.55 | 40.7312 | 5.8188
JOT-AX-WR-L23-000121
2 | L 31,RESIDENTIAL | JOT-AX-SD-L31-00011_00 | F-G/4-6 | WALL INS. |  | 1 | 12.423 | 3.261 | 40.5114 | Door | 1 | 1 | 2.1 | 2.1 | 38.4114 | 70% | 26.888 | 0 | 26.888
JOT-AX-WR-L31-000153
[14 empty] | TOTAL | 96.5989 |  | 73.438 | 40.7312 | 32.7067
Note on C15: Himal Kosala: This WIR for proceed with Basecoat
Note on I17: Himal Kosala: 1.5m work is not completed
Note on M17: Himal Kosala: Door Deducted

## 100MM-EIFS
DETAILED STATUS REPORT
Client Name |  | : | Omniyat Investments & Management LLC
Project Name |  | : | Dorchester Hotel (PLOT 18)
Main Contractor |  | : | Khansaheb civil engineering llc
Scope of works |  | : | External Insulation Finishing System (EPS)
EIFS BUILDUP FOR PARAPET (ROBERTS-VOR-01 for Level 4 & 29, ROBERTS VOR-05 for level 2)- WORKS UNDER ROBERTS
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PROGRESS % | WORK DONE TO DATE | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS | REMARKS
RATE BREAKDOWN: 70%-EPS BOARDS,20%-BASECOAT,10%-PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
2 | ELEVATION 06 ( LIFT AREA) | JOT-AX-SD-ML-00003_00_E | G-H/3-7 | WALL-L2L3 | BO5 | 1 | 2.9 | 7.6 | 22.04 | LIFT LOBBY OPENING L2,L3 | 0 | 0 | 0 | 0 | 22.04 | 90% | 19.836 | 19.836 | 0 | upto basecoat done under roberts
| CORE WALL AREA | [18 empty] | paint done under KCE
JOT-AX-WR-ML-00014
3 | (HOUSEKEEPING LOBBY) | JOT-AX-SD-GF-00001_00_E | D-F/7-8 | WALL GF | B10 | 1 | 4 | 3.82 | 15.28 |  | 0 | 0 | 0 | 0 | 15.28 | 90% | 13.752 | 13.752 | 0 | upto basecoat done under roberts
| JOT-AX-WR-GF-00017 |  |  |  |  | 1 | 1.7 | 4.87 | 8.279 |  | 0 | 0 | 0 | 0 | 8.279 | 90% | 7.4511 | 7.4511 | 0 | paint done under KCE
13 | GF BALL ROOM WALL | JOT-AX-SD-GF-00002_02 | A-U/23-25 | WALL GF | BO22 | 1 | 21.23 | 7.275 | 154.4483 |  | 0 | 0 | 0 | 0 | 196.3882 | 90% | 176.7494 | 176.7494 | -5e-06 | upto basecoat done under roberts
| JOT-AX-WR-L29-00052 |  |  |  |  | 1 | 9.32 | 4.5 | 41.94 | [10 empty] | paint done under KCE
[14 empty] | TOTAL | 241.9873 |  | 217.7885 | 217.7885 | -5e-06
WORK BREAKDOWN : 70% UPTO EPS BOARDS, 20% UPTO BASECOAT, 10% PAINT -WORKS UNDER KCE
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
100MM -EIFS | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | STAIR 6 WALL,Elevation-07, | JOT-AX-SD-ML-00003_01 | L2,G/10-11 | WALL-L2 |  | 1 | 4.62 | 7.442 | 34.382 |  | 0 | 0 | 0 | 0 | 34.382 | 100% | 34.382 | 34.382 | 0
JOT-AX-WR-ML-00074_01
| JOT-AX-WR-ML-00110,116 |  | L2,T-W/10-12
2 | Hotel Ramp area ,Elevation-12 | JOT-AX-SD-ML-00003_01 | GF-L2-W/22-23 | WALL,GF-L3 |  | 1 | 13 | 9.98 | 129.74 |  | 0 | 0 | 0 | 0 | 129.74 | 95% | 123.253 | 76.3919 | 46.8611
JOT-AX-WR-ML-00107,118
3 | Hotel, near Ball room ,Elevation-14 | JOT-AX-SD-GF-00002_02 | GF-A-U/25 | WALL-GF |  | 1 | 7.859 | 4.5 | 35.3655 |  | 0 | 0 | 0 | 0 | 168.1088 | 10% | 16.8109 | 16.8109 | 0
| JOT-AX-WR-ML-00116 |  |  |  |  | 1 | 18.244 | 7.276 | 132.7433
4 | Hotel ,Damac side ,podium level-2 | JOT-AX-SD-ML-00004_02 | T-W/22-23 | WALL-L2 |  | 1 | 18.557 | 7.242 | 134.3898 | LOUVER-1 | 1 | 2.5 | 1 | 2.5 | 114.7224 | 95% | 108.9863 | 0 | 108.9863
| JOT-AX-WR-ML-00136.140,147 | [8 empty] | LOUVER-2 | 1 | 0.6 | 0.5 | 0.3
[10 empty] | WINDOW-1 | 1 | 3.299 | 2.267 | 7.4788
[10 empty] | WINDOW-2 | 1 | 2.168 | 1.197 | 2.5951
[10 empty] | WINDOW-3 | 1 | 2.168 | 1.473 | 3.1935
[10 empty] | DOOR-1 | 1 | 1.5 | 2.4 | 3.6
5 | L 23 RESIDENTIAL,ELEVATION-20 | JOT-AX-SD-L23-00009_02 | E-D/11 | WALL-L23 |  | 1 | 4.732 | 3.45 | 16.3254 |  | 0 | 0 | 0 | 0 | 16.3254 | 70% | 11.4278 | 0 | 11.4278
JOT-AX-WR-L23-00152
[14 empty] | TOTAL | 463.2787 |  | 294.86 | 127.5848 | 167.2752
[17 empty] | 512.6485 | 345.3734 | 167.2751
512.65
0.001475
Note on R38: Himal Kosala: Send Approved WIR
Note on C39: Himal Kosala: WIR for proceed with the paint, please send the approved WIR for painting
Note on R44: Himal Kosala: Send Approved WIR
Note on C45: Himal Kosala: WIR approved for proceed with final paint

## 200MM-EIFS
DETAILED STATUS REPORT
Client Name |  | : | Omniyat Investments & Management LLC
Project Name |  | : | Dorchester Hotel (PLOT 18)
Main Contractor |  | : | Khansaheb civil engineering llc
Scope of works |  | : | External Insulation Finishing System (EPS)
WORK BREAKDOWN : 70% UPTO EPS BOARDS, 20% UPTO BASECOAT, 10% PAINT
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
200MM -EIFS | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | LEVEL-4 to 5,STAIR 6 WALL,Elevation-10 | JOT-AX-SD-L4-00005_02 | E-H/10-12 | WALL L4 |  | 1 | 21.97 | 9.92 | 217.9424 |  | 0 | 0 | 0 | 0 | 217.9424 | 10% | 21.7942 | 21.7942 | 0
JOT-AX-WR-L4-00071,JOT-AX-WR-ML-00098_0
2 | LEVEL- GF to 1 ,STAIR-6 WALL,ELEVATION-7 | JOT-AX-SD-GF-00002_02 | T-W/10-14 | WALL GF-1 |  | 1 | 4.613 | 5.275 | 24.3336 |  | 1 | 0.9 | 1.8 | 1.62 | 22.7136 | 100% | 22.7136 | 22.7136 | 0
JOT-AX-WR-ML-00083_00,110,116
2.1 | LEVEL- GF to 1 ,STAIR-6 WALL,ELEVATION-9 | JOT-AX-SD-GF-00002_02 | T-W/10-14 | WALL GF-1 |  | 1 | 5.312 | 5.275 | 28.0208 |  | 1 | 1.1 | 1.8 | 1.98 | 26.0408 | 100% | 26.0408 | 26.0408 | 0
JOT-AX-WR-ML-00083_00
3 | LEVEL-GROUND FLOOR ,NEAR LOBBY | JOT-AX-SD-GF-00001_02 | E-D/6-8 | WALL GF |  | 1 | 5.58 | 5.275 | 29.4345 |  | 0 | 0 | 0 | 0 | 29.4345 | 70% | 20.6042 | 20.6042 | 0
JOT-AX-WR-ML-00077_00
[14 empty] | TOTAL | 296.1313 |  | 91.1528 | 91.1528 | 0
676.0951
584.9424

## EIFS -STAND ALONE (300MM)
DETAILED STATUS REPORT
Client Name |  | : | Omniyat Investments & Management LLC
Project Name |  | : | Dorchester Hotel (PLOT 18)
Main Contractor |  | : | Khansaheb civil engineering llc
Scope of works |  | : | External Insulation Finishing System (EPS)
EIFS SYSTEM+BUILT UP(300MM)
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 35%-FRAMING,35%-EPS BOARDS,20%-BASECOAT,10%-PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | STAIR 6 WALL,LEVEL-02 to 3 | JOT-AX-SD-ML-00003_02 | E-H/10-11 | WALL L2 |  | 1 | 4 | 7.275 | 29.1 |  | 0 | 0 | 0 | 0 | 29.1 | 100% | 29.1 | 29.1 | 0
JOT-AX-WR-ML-00085,100,108,104,110
2 | Residential,Stair-6,L4-5 | JOT-AX-SD-L4-00005_02 | T-W/13-14 | WALL L4-5 |  | 1 | 4 | 9.92 | 39.68 |  | 0 | 0 | 0 | 0 | 39.68 | 100% | 39.68 | 39.68 | 0
JOT-AX-WR-ML-00076,81,90,98
[14 empty] | TOTAL | 68.78 |  | 68.78 | 68.78 | 0

## EIFS -STAND ALONE (400MM)
DETAILED STATUS REPORT
Client Name |  | : | Omniyat Investments & Management LLC
Project Name |  | : | Dorchester Hotel (PLOT 18)
Main Contractor |  | : | Khansaheb civil engineering llc
Scope of works |  | : | External Insulation Finishing System (EPS)
EIFS SYSTEM+BUILT UP(400MM)
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 35%-FRAMING,35%-EPS BOARDS,20%-BASECOAT,10%-PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | Stair-6,GF to 1 st floor | JOT-AX-SD-GF-00002_02 | Grid-E-H/10-12 | WALL GF |  | 1 | 3.22 | 7.275 | 23.4255 |  | 0 | 0 | 0 | 0 | 23.4255 | 100% | 23.4255 | 23.4255 | 0
JOT-AX-WR-GF-00086,99
JOT-AX-WR-ML-00110
[14 empty] | TOTAL | 23.4255 |  | 23.4255 | 23.4255 | 0

## EIFS RENDER
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  | (Sqm)
1 | L4 ZONE 3, GATE 2 FRONT | JOT-AX-SD-L04-00005_00_E | A-I/Y1-4 |  |  | 1 | 79.9 | 1.2 | 95.88 |  | 0 | 0 | 0 | 0 | 95.88 | 95.88 | 0
AREA
JOT-AX-WR-L4-00009
[14 empty] | TOTAL | 95.88 | 95.88 | 0

## VARIATIONS
DORCHESTER HOTEL & RESIDENCIES
JOYZ OVERSEAS - VARIATION SCHEDULE
SN | Variations | Total Work Scope |  |  | Progress as per WFA |  |  | Remaining Work |  | Previous |  | This Month | This Month | Cumulative |  |  | Balance Work
|  | QTY | Rate | Amount | % | QTY | Amount | QTY | Amount | QTY | Amount | QTY | Amount | % | QTY | Amount | % | QTY | Amount
1 | Additional EFIS to parapets at L4, L29 | 256.9673 | 319 | 81973 | 13.7% | 35.21 | 11232 | 221.7573 | 70741 | 212.4213 | 67762.3819 | 45.36 | 14469.84 | 86.99% | 257.7813 | 82232.2219 | -0.3167% | -0.81394 | -259.6459
2 | Additional EFIS to non-accessible balconies | 766.0026 | 380 | 291081 | 0% |  | 0 | 766.0026 | 291081 |  | 0 |  | 0 |  |  | 0 | 100% | 766.0026 | 291081
3 | PVC grooved to EFIS system | 823.01 | 32.16 | 26468 | 7.333% | 60.3545 | 1941 | 762.6555 | 24527 | 176.66 | 5681.3856 | 33.5293 | 1078.3023 | 25.54% | 210.1893 | 6759.6879 | 74.46% | 612.8207 | 19708.3121
4 | Additional EFIS to entrance at L2 | 169.4702 | 319 | 54061 | 0% |  | 0 | 169.4702 | 54061 | 0 | 0 | 55.7411 | 17781.398 | 32.89% | 55.7411 | 17781.398 | 67.11% | 113.7292 | 36279.602
5 | Additional EFIS to parapets at L2 | 99.2853 | 319 | 31672 | 0% |  | 0 | 99.2853 | 31672 |  | 0 | 99.29 | 31673.51 | 100% | 99.29 | 31673.51 | -0.004768% | -0.0047335 | -1.51
Sub-Totals |  |  |  | 485255 | 2.715% |  | 13173 |  | 472082 |  | 73443.7675 |  | 65003.0503 | 28.53% |  | 138446.8178 | 71.47% |  | 346807.7582
NEW VARIATIONS
WA PS-005
Additions
6 | Installation of stud frame + 200mm EIFS system to replace 300mm EIFS system (PS-005) | 854 | 450 | 384300 | [5 empty] | 340.3437 | 153154.6506 | 79.5783 | 35810.2544 | 49.17% | 419.922 | 188964.905 | 50.83% | 434.078 | 195335.095
7 | Installation of stud frame + 200mm EIFS system to replace 400mm EIFS system (PS-005) | 422 | 525 | 221550 | [5 empty] | 397.8524 | 208872.5044 | -46.5104 | -24417.9357 | 83.26% | 351.342 | 184454.5686
8 | Installation of stud frame + 200mm EIFS system to replace 275mm EIFS system (PS-005) | 176 | 415 | 73040
9 | Removal of framing in areas where the works are completed (PS-005 R1) | 1 | 25250 | 25250 | [5 empty] | 1 | 25250 | 0 | 0 | 100% | 1 | 25250
Omission
10 | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 400mm (PS-005 R2) | 280.54 | 500 | -140270 | [6 empty] | -13975.4117 | 137.9449 | -54997.0245 | 49.17% | 137.9449 | -68972.4362
11 | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 300mm (PS-005 R2) | 658.47 | 435 | -286434.45 | [6 empty] | -67510.9309 | 548.2185 | -170964.0992 | 83.26% | 548.2185 | -238475.0301
12 | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 275mm (PS-005 R2) | 176 | 415 | -73040 | [9 empty] | 0% | 0 | 0
WA PS-019
13 | Removal & reinstatement of EIFS for waterproofing termination at ground floor as per the attached Joyz Variation ref. KCE-JOT-VOR-00002 Rev 01 dated 15.08.22 (PS-019 R0) | 1 | 7860.45 | 7860.45 | [6 empty] | 0 | 0 | 0 | 0% |  | 0
14 | Supply & installation of 100mm thick EIFS on stair wall at Residence level 23 as per the attached Joyz Variation ref. KCE-JOT-VOR-00003 Rev 0 dated 01.09.22 (PS-019 R1) | 10 | 319 | 3190 | [5 empty] | 0 | 0 | 9 | 2871 | 90% | 9 | 2871
15 | Additional scope of EIFS 50mm,75mm,100mm thick system and EIFS 20mm render as per the attached Joyz Variation ref. KCE- JOT-VOR-00004 dated 14.09.22. (PS-019 R3)
15.1 | Render on Planter Wall | 1799.35 | 175 | 314886.25 | [5 empty] | 141.1501 | 24701.2762 | 911.0554 | 159434.6968 | 58.48% | 1052.2056 | 184135.973
15.2 | Render on Parapet Coping & Internal Face | 638 | 175 | 111650 | [7 empty] | 0 | 0 | 0% |  | 0
15.3 | 50mm EIFS Build-up on top of the Level-02 Parapet Wall | 11.75 | 270 | 3172.5 | [7 empty] | 0 | 0 | 0% |  | 0
15.4 | 100mm EIFS at Level-01 AV Rooms External | 25.8075 | 319 | 8232.5925 | [5 empty] | 18.0652 | 5762.8147 | 2.5808 | 823.2593 | 80% | 20.646 | 6586.074
15.5 | 75mm EIFS at Basement-01 External Seating Area | 47.92 | 295 | 14136.4 | [5 empty] | 33.5431 | 9895.2219 | 7.3158 | 2158.1462 | 85.26% | 40.8589 | 12053.3681
15.6 | Render on Basement-01 to Level-01A | 176.05 | 175 | 30808.75 | [5 empty] | 158.4398 | 27726.9576 | 8.8022 | 1540.3865 | 95% | 167.242 | 29267.3441
15.7 | Render near AV Room External Area | 47.2 | 175 | 8260 | [5 empty] | 0 | 0 | 42.48 | 7434 | 90% | 42.48 | 7434
16 | Cutting of existing 100mm thick EIFS and reinstatement of EIFS system after the cutting at L 29 parapet (PS-019 R4) | 1 | 34345 | 34345 | [5 empty] | 0.2 | 6869 | 0.8 | 27476 | 100% | 1 | 34345
17 | Supply & installation of insulation behind the gabion wall as per the response to KCE-AX-RFI-GF-00072 dt 15.07.22 & Joyz variation submission ref JOT-KCE-DOR-202209-005 dated 26.10.22. (PS-019 R4) | 115 | 120 | 13800 | [6 empty] | 0 | 0 | 0 | 0% |  | 0
18 | Supply & installation of 200mm fluted EIFS on Level 29 as per the response to KCE-AX-RFI-GF-00072 date 15.07.22 & Joyz variation submission ref JOT-KCE-DOR-202209-005 dated 26.10.22 (PS-019 R4) | 120.404 | 660 | 79466.64
19 | Supply & installation of 400mm fluted EIFS (200mm built up + 200mm EIFS) on level 28 as per the Joyz variation submission JOT-KCE-DOR-202209-005 dated 26.10.22 and mockup approval. (PS-019 R4) | 67.404 | 750 | 50553 | [5 empty] | 0 | 0 | 47.32 | 35490 | 70.2% | 47.32 | 35490
20 | External door jamb finishes due to changes in finishing details & as per Joyz variation submission ref JOT-KCE-VOR-00006 dated 17.11.22. (PS-019 R5) | 16 | 2800 | 44800 | [6 empty] | 0 | 0 | 0 | 0% |  | 0
21 | Paint finish to match with GRC colour in place of GRC coping at Residence tower level 32 as per Joyz variation submission ref JOT-KCE-VOR-00007 dated 17.11.22. (PS-019 R5) | 67 | 40 | 2680 | [6 empty] | 0 | 0 | 0 | 0% |  | 0
22 | Additional EIFS works as per the shop drawing ref GLA-AX-SD-L31-66195 comments & Joyz variation submission ref JOT-KCE-VOR-00007 dated 17.11.22. (PS-019 R5) | 68 | 295 | 20060 | [6 empty] | 0 | 0 | 0 | 0% |  | 0
23 | Removal & reinstatement of 200m thick with 400mm thick EIFS and framing as per the response to KCE-AX-RFI-GF-00254 dt 22.10.22 & & Joyz variation submission ref JOT-KCE-VOR-00007 dated 17.11.22. (PS-019 R5) | 33.44 | 380 | 12707.2 | [5 empty] | 25.08 | 9530.4 | 0 | 0 | 75% | 25.08 | 9530.4
24 | Additional scope of EIFS 20mmm render as per the attached Joyz variation ref. KCE-JOT-VOR-00004 rev 1 dated 29.11.22. (PS-019 R6) | 1073.42 | 175 | 187848.5
Sub-Totals |  |  |  | 1152852.8325 | [6 empty] | 390276.4829 |  | 22658.6837 | 35.82% |  | 412935.1666 | 16.94% |  | 195335.095

## RPJV Variation
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PROGRESS % | WORK DONE TO DATE | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS BUILDUP FOR L29 PARAPET, EPS BOARD | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | L4, PARAPET | JOT-AX-SD-L4-00005_02 | W-X/13-16 | WALL L4 | BO23 | 1 | 25.15 | 1.4 | 35.21 |  | 0 | 0 | 0 | 0 | 35.21 | 100% | 35.21 | 35.21 | 0
JOT-AX-WR-L4-00036
2 | L4, PARAPET | JOT-AX-SD-L4-00005_02 | X-Q/23-24 | PARAPET L4 |  | 1 | 28.9 | 1.4 | 40.46 |  | 0 | 0 | 0 | 0 | 40.46 | 100% | 40.46 | 40.46 | 0
JOT-AX-WR-L4-00073
3 | L2 PARAPET, ROADSIDE | JOT-AX-SD-L2-00004_03 | U-Z/13-22 | PARAPET L2, INSULATION |  | 1 | 86.03 | 1.4 | 120.44 |  | 0 | 0 | 0 | 0 | 120.4378 | 100% | 120.4378 | 120.4378 | 0
JOT-AX-WR-L2-00078_00
JOT-AX-WR-L2-00084_00
JOT-AX-WR-L2-00078,82,84,92,96,109
4 | L2 PARAPET, ROADSIDE | JOT-AX-SD-L2-00004_03 | U-Z/13-22 | PARAPET L2, BASE COAT |  | 1 | 25 | 1.4 | 35 |  | 0 | 0 | 0 | 0 | 35 | 20% | 7 | 7 | 0
JOT-AX-WR-L2-00082_00
4 | L4 PARAPET, ROADSIDE | JOT-AX-SD-L4-00005_02 | G-X / 11-16 | PARAPET L4, PAINT |  | 1 | 23.19 | 1.4 | 32.47 |  | 0 | 0 | 0 | 0 | 32.47 | 20% | 6.494 | 6.494 | 0
JOT-AX-WR-L2-00075_00
4 | L4 PARAPET,RESIDENTIAL | JOT-AX-SD-L4-00005_02 | W-X/15-17 | WALL,L4 |  | 1 | 2.877 | 1.4 | 4.0278 |  | 0 | 0 | 0 | 0 | 4.0278 | 70% | 2.8195 | 2.8195 | 0
JOT-AX-WR-L4-00089,97
2 | L2 parapet,Damac side,Hotel | JOT-AX-SD-L2-00004_03 | Y-X/23-25 | L2 |  | 1 | 36 | 1.4 | 50.4 |  | 0 | 0 | 0 | 0 | 50.4 | 90% | 45.36 | 0 | 45.36
JOT-AX-WR-L2-00144,156
[14 empty] | TOTAL | 318.0056 |  | 257.7813 | 212.4213 | 45.36
RPJV-VOR-4,ADDITIONAL EIFS FOR LEVEL 2 AND GF
NO | BUILDING | DRAWING REF. NO/INSTRUCTION REF./RFI REF. | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 70%-INSULATION,20%-BASECOAT,10%-PAINTING | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | HOTEL ENTRANCE | JOT-AX-SD-ML-00004_02 | L2,GRID-T-W/18-19 |  |  | 1 | 18.937 | 4.205 | 79.6301 |  | 0 | 0 | 0 | 0 | 79.6301 | 70% | 55.7411 | 0 | 55.7411
JOT-AX-WR-L2-00144,150
[14 empty] | TOTAL | 79.6301 |  | 55.7411 | 0 | 55.7411
EIFS BUILDUP FOR PARAPET (ROBERTS-VOR-01 for Level 4 & 29, ROBERTS VOR-05 for level 2) | [17 empty] | MONTH: | December 2022
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PROGRESS % | WORK DONE TO DATE | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS | REMARKS
RATE BREAKDOWN: 70%-EPS BOARDS,20%-BASECOAT,10%-PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | L2 PARAPET, ROADSIDE | JOT-AX-SD-L2-00004_03 | U-Z/13-22 | WALL L2 |  | 1 | 86.03 | 1.4 | 120.44 |  | 0 | 0 | 0 | 0 | 120.44 | 100% | 120.44 | 120.44 | 0
JOT-AX-WR-L2-00078,82,84,92,96,109
2 | L2 parapet,Damac side,Hotel | JOT-AX-SD-L2-00004_03 | Y-X/23-25 | L2 |  | 1 | 36 | 1.4 | 50.4 |  | 0 | 0 | 0 | 0 | 50.4 | 90% | 45.36 | 0 | 45.36
JOT-AX-WR-L2-00144,156
[14 empty] | TOTAL | 170.84 |  | 165.8 | 120.44 | 45.36
Note on C32: Himal Kosala: Please send the approval for basecoat (150)

## PVC GROOVE
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
PVC Groove | [5 empty] | NO | LENGTH | AREA |  | NO | LENGTH | AREA |  |  |  |  | (Sqm)
1 | STAIR 6 WALL,Elevation-10 | JOT-AX-SD-L4-00005_02 | E-H/10-12 | WALL L4 |  | 2 | 9.92 | 19.84 |  | 0 | 0 | 0 | 19.84 | 100% | 19.84 | 19.84 | 0
JOT-AX-WR-L4-00071
2 | LEVEL-2 PARAPET-BASECOAT | JOT-AX-SD-L4-00004_03 | U-Z/13-15 | WALL L2 |  | 6 | 1.4 | 8.4 |  | 0 | 0 | 0 | 8.4 | 100% | 8.4 | 8.4 | 0
JOT-AX-WR-L2-00082_00
3 | LEVEL-4,STAIR 6 WALL,Elevation-08 | JOT-AX-SD-L4-00005_02 | E-H/10-12 | WALL L4 |  | 2 | 9.92 | 19.84 |  | 0 | 0 | 0 | 19.84 | 100% | 19.84 | 19.84 | 0
JOT-AX-WR-L4-00070_01
4 | GF Ballroom Wall | JOT-AX-SD-GF-00002_02 | A-U/23-25 | WALL GF |  | 4 | 7.28 | 29.12 |  | 0 | 0 | 0 | 29.12 | 100% | 29.12 | 29.12 | 0
JOT-AX-WR-ML-00093_00
5 | Residential,stair-6,L2 | JOT-AX-SD-ML-00003_02 | E-H/10-11 | WALL L2 |  | 4 | 7.28 | 29.12 |  | 0 | 0 | 0 | 29.12 | 100% | 29.12 | 29.12 | 0
JOT-AX-WR-ML-00110_00
6 | LEVEL-2 PARAPET-BASECOAT | JOT-AX-SD-L4-00004_03 | U-Z/18-22 | WALL L2 |  | 6 | 1.4 | 8.4 |  | 0 | 0 | 0 | 8.4 | 100% | 8.4 | 8.4 | 0
JOT-AX-WR-L2-00096_00
7 | LEVEL-2 Hotel Ramp | JOT-AX-SD-ML-00004_03 | W/18-23 | WALL GF to L3 |  | 4 | 9.98 | 39.92 |  | 0 | 0 | 0 | 71.92 | 95% | 68.324 | 61.94 | 9.98
| JOT-AX-WR-ML-00118,119,140 |  |  |  |  | 4 | 8 | 32
8 | Hotel,Damac side, | JOT-AX-SD-ML-00004_03 | W-T/23 | level-2 to 4 |  | 3 | 7.242 | 21.726 |  | 0 | 0 | 0 | 28.574 | 95% | 27.1453 | 0 | 28.574
| JOT-AX-WR-ML-00140 |  |  |  |  | 1 | 4.873 | 4.873
[6 empty] | 1 | 1.975 | 1.975
[12 empty] | TOTAL | 215.214 |  | 210.1893 | 176.66 | 38.554
Note on C23: Himal Kosala: send the WIR for final paint approval
Note on C26: Himal Kosala: send the WIR for final paint approval

## EIFS + BUILTUP (300MM)
DETAILED STATUS REPORT
Client Name |  | : | Omniyat Investments & Management LLC
Project Name |  | : | Dorchester Hotel (PLOT 18)
Main Contractor |  | : | Khansaheb civil engineering llc
Scope of works |  | : | External Insulation Finishing System (EPS)
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
EIFS SYSTEM+BUILT UP(300MM)- 35% framing, 35% ESP Boards, 20% Basecoat, 10% Paint | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | STAIR 6 WALL,LEVEL-02 to 3 | JOT-AX-SD-ML-00003_02 | E-H/10-11 | WALL L2 |  | 1 | 9.275 | 7.442 | 69.0246 |  | 0 | 0 | 0 | 0 | 69.0246 | 100% | 69.0246 | 69.0246 | 0
JOT-AX-WR-ML-00085,100,104,116
2 | Hotel ramp area,Level-1 to lvl-3 | JOT-AX-SD-ML-00004_03 | W/18-22 | WALL L2-3 |  | 0.5 | 26.051 | 2.599 | 33.8533 |  | 0 | 0 | 0 | 0 | 244.9024 | 95% | 232.6573 | 220.4122 | 12.2451
| JOT-AX-WR-ML-00107_00,117,118,119 |  |  |  |  | 1 | 4.01 | 9.98 | 40.0198 |  | 0 | 0 | 0 | 0
[6 empty] | 1 | 26.05 | 7.38 | 192.249 |  | 1 | 2.795 | 7.592 | 21.2196
3 | Residential area,lvl-2 to lvl-3 | JOT-AX-SD-ML-00003_02 | G/4-7 | WALL L2-3 |  | 1 | 25.135 | 7.037 | 176.875 |  | 0 | 0 | 0 | 0 | 176.875 | 35% | 61.9062 | 61.9062 | 0
JOT-AX-WR-ML-00103_00
4 | Residential & Hotel entrance lvl-23,Elevation-20 | JOT-AX-SD-L23-00009_02 | D-G/10-11 | WALL L23 |  | 1 | 14.46 | 3.45 | 49.887 | D-03b | 1 | 1.2 | 2.1 | 2.52 | 47.367 | 70% | 33.1569 | 34.9209 | -1.764
JOT-AX-WR-ML-00120
5 | Hotel Level-17,Elevation-24 | JOT-AX-SD-L17-00008_02 | E-H/10-11 | WALL L17 |  | 1 | 8.6 | 3.85 | 33.11 |  | 0 | 0 | 0 | 0 | 33.11 | 70% | 23.177 | 11.5885 | 11.5885
JOT-AX-WR-ML-00120
[14 empty] | TOTAL | 571.279 |  | 419.922 | 397.8524 | 22.0696
Note on R17: Himal Kosala: Additionally Termination Points are not done
Note on C18: Himal Kosala: send the approval for final paint

## EIFS + BUILTUP (400MM)
DETAILED STATUS REPORT
Client Name |  | : | Omniyat Investments & Management LLC
Project Name |  | : | Dorchester Hotel (PLOT 18)
Main Contractor |  | : | Khansaheb civil engineering llc
Scope of works |  | : | External Insulation Finishing System (EPS)
WORK BREAKDOWN : 70% UPTO EPS BOARDS, 20% UPTO BASECOAT, 10% PAINT
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
EIFS SYSTEM+BUILT UP(400MM)- 35% framing, 35% ESP Boards, 20% Basecoat, 10% Paint | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | Stair-6,GF to 1 st floor | JOT-AX-SD-GF-00002_02 | E-H/10-12 | WALL GF-L1 |  | 1 | 8.477 | 7.275 | 61.6702 |  | 0 | 0 | 0 | 0 | 61.6702 | 100% | 61.6702 | 61.6702 | 0
JOT-AX-WR-GF-00086,99,116
2 | Residential ,road side,GF to 1 st floor | JOT-AX-SD-ML-00001_02 | G-H/3-8 | WALL GF-L1 |  | 1 | 24.817 | 7.275 | 180.5437 | D-03b | 4 | 1.2 | 2.1 | 10.08 | 170.4637 | 70% | 119.3246 | 108.3262 | 10.9984
JOT-AX-WR-ML-00095,106,107
3 | Residential ,Lobby,GF to 1 st floor | JOT-AX-SD-ML-00001_02 | E-F/6-7 | WALL GF-L1 |  | 1 | 6.694 | 7.28 | 48.7323 |  | 1 | 1 | 1.8 | 1.8 | 46.9323 | 90% | 42.2391 | 42.2391 | 0
JOT-AX-WR-ML-00106_00,115,128
4 | RESIDENTIAL,RAMP AREA,GF to Level-3 | JOT-AX-SD-ML-00001_02 | G-D/Y1 | WALL GF-L3 |  | 1 | 11.32 | 11.635 | 131.7082 |  | 2 | 1 | 1.8 | 3.6 | 128.1082 | 100% | 128.1082 | 128.1082 | 0
JOT-AX-WR-ML-00111_00,112,113,114
[14 empty] | TOTAL | 407.1744 |  | 351.342 | 340.3437 | 10.9984

## KCE Variation
DETAILED STATUS REPORT
Client Name |  | : | Omniyat Investments & Management LLC
Project Name |  | : | Dorchester Hotel (PLOT 18)
Main Contractor |  | : | Khansaheb civil engineering llc
Scope of works |  | : | External Insulation Finishing System (EPS)
KCE-VOR-04, ITEMS-04, 20MM PLASTERING FOR LEVEL 01
NO | BUILDING | DRAWING REF. NO/INSTRUCTION REF./RFI REF. | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 90%-PLASTERING,10%-PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | 20MM PLASTER AT LEVEL-1,AV ROOMS EXTERNAL | E11/K116/SN/dm/281, KCE-AX-RFI-L1-00232 | 25/T-U | WALL-LVL-1 AV ROOMS |  | 1 | 16 | 2.95 | 47.2 |  | 0 | 0 | 0 | 0 | 47.2 | 90% | 42.48 | 0 | 42.48
JOT-AX-WR-L1-00149
[14 empty] | TOTAL | 47.2 |  | 42.48 | 0 | 42.48
KCE-VOR-04, ITEMS-04, 100MM EIFS FOR LEVEL 01
NO | BUILDING | DRAWING REF. NO/INSTRUCTION REF./RFI REF. | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 70%-EPS BOARDS,20%-BASECOAT,10%-PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | 100MM EIFS AT LEVEL-1,AV ROOMS EXTERNAL | E11/K116/SN/dm/281, KCE-AX-RFI-L1-00232 | 25/T-U | WALL-LVL-1 AV ROOMS |  | 1 | 9.3 | 2.775 | 25.8075 |  | 0 | 0 | 0 | 0 | 25.8075 | 80% | 20.646 | 18.0652 | 2.5808
JOT-AX-WR-L1-122_00
[14 empty] | TOTAL | 25.8075 |  | 20.646 | 18.0652 | 2.5808
VOR-4, ITEM -5,75 MM EIFS
NO | BUILDING | DRAWING REF. NO/INSTRUCTION REF./RFI REF. | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 70%-EPS BOARDS,20%-BASECOAT,10%-PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | 75MM EIFS AT B-1, EXTERNAL SEATING AREA | E11/K116/SN/dm/281, KCE-AX-RFI-L1-00232 | EXTERNAL SEATING AREA | WALL-B-1 EXTERNAL |  | 1 | 10.25 | 4.675 | 47.9187 | D-03e | 1 | 1.2 | 2.1 | 2.52 | 45.3987 | 90% | 40.8589 | 33.5431 | 7.3158
JOT-AX-WR-B1-123_00
[14 empty] | TOTAL | 45.3987 |  | 40.8589 | 33.5431 | 7.3158
KCE-VOR-04, ITEM 06, PLASTER ON WALL SEATING AREA @BASEMENT
NO | BUILDING | DRAWING REF. NO/INSTRUCTION REF./RFI REF. | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 90%-20MM PLASTERING,10%-PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | 20mm PLASTER AT B-1, EXTERNAL SEATING AREA | E11/K116/SN//, KCE-AX-RFI-B1-00186 | EXTERNAL SEATING AREA | WALL-B-1 EXTERNAL |  | 1 | 11.285 | 4.675 | 52.7574 |  | 0 | 0 | 0 | 0 | 52.7574 | 95% | 167.242 | 158.4398 | 8.8022
| JOT-AX-WR-B1-00124_00 |  | ABOVE GF |  |  | 1 | 31.612 | 3.9 | 123.2868 |  | 0 | 0 | 0 | 0 | 123.2868
[14 empty] | TOTAL | 176.0442 |  | 167.242 | 158.4398 | 8.8022
KCE-VOR-04, ITEM 01, RENDER ON PLANTER WALLS AREA @
NO | BUILDING | DRAWING REF. NO/INSTRUCTION REF./RFI REF. | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 90%-20MM PLASTERING,10%-PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | Ground floor Planter wall EIFS render plaster | FE-LX-SD-GL-00006_00 | GF Planter wall |  |  | 1 | 11.5 | 1.38 | 15.87 |  | 0 | 0 | 0 | 0 | 156.8335 | 90% | 141.1501 | 141.1501 | 0
[6 empty] | 1 | 21.8 | 0.9 | 19.62
[6 empty] | 1 | 29.25 | 0.9 | 26.325
[6 empty] | 1 | 14.2 | 1.115 | 15.833
[6 empty] | 1 | 27.75 | 1.45 | 40.2375
[6 empty] | 1 | 29.96 | 1.3 | 38.948
| PLANTER WALL,NEAR KCE OFFICE | WIR: JOT-AX-WR-GF-00131 | GRID-A/3-5 | WALL |  | 1 | 23.216 | 1.3 | 30.1808 |  | 0 | 0 | 0 | 0 | 347.9294 | 90% | 313.1365 | 0 | 313.1365
| LPG TANK ,ROAD SIDE | WIR: JOT-AX-WR-GF-00134 | GRID-K/Y1 | LPG TANK INSIDE |  | 1 | 34.253 | 2.9 | 99.3337
| CANAL SIDE WALL | WIR: JOT-AX-WR-GF-00131 | GRID-17-21/A | WALL |  | 1 | 32.951 | 1 | 32.951
| CANAL SIDE WALL | WIR: JOT-AX-WR-GF-00131 | GRID-20-24/A | SIDES+TOP |  | 1 | 37.411 | 1.35 | 50.5049
| CANAL SIDE WALL | WIR: JOT-AX-WR-GF-00131 | GRID-23-24/A | WALL |  | 1 | 28.011 | 1.4 | 39.2154
| CANAL SIDE WALL | WIR: JOT-AX-WR-GF-00131 | GRID-18-21/A | COPING |  | 4 | 3.848 | 0.45 | 6.9264
| CANAL SIDE WALL | WIR: JOT-AX-WR-GF-00131 | GRID-21/A | WALL |  | 1 | 3.85 | 0.75 | 2.8875
| NEAR ENTRANCE OF HOTEL | WIR: JOT-AX-WR-GF-00131 | GRID-15-16/B-C | WALL |  | 1 | 33.73 | 1.2 | 40.476
| NEAR ENTRANCE OF HOTEL | WIR: JOT-AX-WR-GF-00131 | GRID-15-16/V-Z | WALL |  | 1 | 32.467 | 1.4 | 45.4538
2 | SECOND FLOOR PLANTER WALL/ECO1A
a | NEAR CLIENT OFFICE |  | GRID-1-3/F | WALL |  | 1 | 8.605 | 1.35 | 11.6168 |  | 0 | 0 | 0 | 0 | 101.5889 | 50% | 50.7944 | 0 | 50.7944
b | NEAR CLIENT OFFICE |  | GRID-1-3/F | WALL |  | 1 | 13.84 | 1.35 | 18.684
c | DAMAC BUILDING SIDE |  | GRID-22-24/V-A | WALL |  | 1 | 52.806 | 1.35 | 71.2881
3 | FOURTH FLOOR PLANTER WALL/ECO1A
a | CAMNAL SIDE | WIR: JOT-AX-WR-GF-00133 | GRID-3-9/B-C |  |  | 1 | 85.382 | 0.8 | 68.3056 | [5 empty] | 683.9056 | 80% | 547.1245 | 0 | 547.1245
b | CAMNAL SIDE | WIR: JOT-AX-WR-GF-00133 | GRID-3-9/D |  |  | 1 | 684 | 0.9 | 615.6
[14 empty] | TOTAL | 1290.2574 |  | 1052.2056 | 141.1501 | 911.0554
KCE-VOR-05, ITEM 01, 50mm CUTTING OF PARAPET & REINSTATEMENT
NO | BUILDING | DRAWING REF. NO/INSTRUCTION REF./RFI REF. | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 20%-50MM CUTTING OF PARAPET,70%-REINSTATEMENT OF BASECOAT,10%-REINSTATEMENT OF PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | CUTTING OF PARAPET AND REINSTATEMENT | E11-K116-JA-dm-273 | L29 PARAPET |  |  | 1 | 82.218 | 1 | 82.218 |  | 0 | 0 | 0 | 0 | 82.218 | 100% | 82.218 | 0 | 82.218
| JOT-AX-WR-L29-00127,135,160 |  |  |  |  | 1 | 77.782 | 1 | 77.782 |  | 0 | 0 | 0 | 0 | 77.782 | 100% | 77.782 | 0 | 77.782
N
[14 empty] | TOTAL | 160 |  | 160 | 0 | 160
KCE-VOR-05, ITEM 04,400MM FLUTED EIFS
NO | BUILDING | DRAWING REF. NO/INSTRUCTION REF./RFI REF. | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 35%-BUILT UP,35%-INSULATION,20%-BASECOAT,10%-PAINTING | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | ROAD SIDE,FLUTED EIFS | JOT-AX-SD-ML-00006_03 | L29 ,GRID-X-W/16-19 |  |  | 1 | 16.9 | 4 | 67.6 |  | 0 | 0 | 0 | 0 | 67.6 | 70% | 47.32 | 0 | 47.32
JOT-AX-WR-L29-145,154
[14 empty] | TOTAL | 67.6 |  | 47.32 | 0 | 47.32
KCE-VOR-03-100MM EIFS ON STAIRWALL
NO | BUILDING | DRAWING REF. NO/INSTRUCTION REF./RFI REF. | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 70%-INSULATION,20%-BASECOAT,10%-PAINTING | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | L 23 HOTEL ENTRANCE ,STAIRWALL | E11-K116-MS-dm-135 ,lvl-23 | L23 |  |  | 1 | 5 | 2 | 10 |  | 0 | 0 | 0 | 0 | 10 | 90% | 9 | 0 | 9
JOT-AX-WR-L23-00130,159
[14 empty] | TOTAL | 10 |  | 9 | 0 | 9
Note on C35: Himal Kosala: No WIR
Note on C78: Himal Kosala: This WIR for approval of the render, please send the final paint approval
Note on C115: Himal Kosala: No WIR for below
Note on R121: Himal Kosala: Full Area not completed
Note on B133: Himal Kosala: This Lump-sum is now 100% complete

## EIFS 400mm EPS BOARDS (hidden)
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS 400mm EPS BOARDS | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  | (Sqm)
1 | ELEVATION 01 (BASEMENT RAMP SIDE) | JOT-AX-SD-GF-00001_00_E | D-G/Y1 | WALL-GF |  | 1 | 11.32 | 4.6 | 52.072 | DOOR | 2 | 1.2 | 1.78 | 4.272 | 47.8 | 47.8 | 0
JOT-AX-WR-GF-00003
2 | ELEVATION 01 (BASEMENT RAMP SIDE) | JOT-AX-SD-ML-00003_00_E | D-G/Y1 | WALL-L2L3 |  | 1 | 11.32 | 7.4 | 83.768 |  | 0 | 0 | 0 | 0 | 83.768 | 83.768 | 0
JOT-AX-WR-ML-00007
[14 empty] | TOTAL | 131.568 | 131.568 | 0

## EIFS 400mm BASECOAT (hidden)
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS 400mm BASECOAT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  | (Sqm)
1 | ELEVATION 01 (BASEMENT RAMP SIDE) | JOT-AX-SD-GF-00001_00_E | D-G/Y1 | WALL-GF |  | 1 | 11.32 | 4.6 | 52.072 | DOOR | 2 | 1.2 | 1.78 | 4.272 | 47.8 | 47.8 | 0
JOT-AX-WR-GF-00006
2 | ELEVATION 01 (BASEMENT RAMP SIDE) | JOT-AX-SD-ML-00003_00_E | D-G/Y1 | WALL-L2L3 |  | 1 | 11.32 | 7.4 | 83.768 |  | 0 | 0 | 0 | 0 | 83.768 | 83.768 | 0
JOT-AX-WR-L4-00011
[14 empty] | TOTAL | 131.568 | 131.568 | 0

## EIFS 400mm PAINT (hidden)
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS 400mm PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  | (Sqm)
1 | RAMPSIDE | JOT-AX-SD-ML-00003_00_E | D-H/Y1 | L2-WALL | PA9 | 1 | 11.61 | 6.36 | 73.8396 |  | 0 | 0 | 0 | 0 | 73.8396 | 73.8396 | 0
JOT-AX-WR-ML-00054
[14 empty] | TOTAL | 73.8396 | 73.8396 | 0

## EIFS 300mm EPS BOARDS (hidden)
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PROGRESS % | WORK DONE TO DATE | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS 300mm EPS BOARDS | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
4 | ELEVATION 06 ( LIFT AREA) | JOT-AX-SD-ML-00003_00_E | G-H/3-7 | WALL-L2L3 |  | 1 | 27.3 | 7.6 | 207.48 | LIFT LOBBY OPENING L2,L3 | 2 | 3.18 | 2.4 | 15.264 | 192.216 | 100% | 192.216 | 192.216 | 0
| CORE WALL AREA | JOT-AX-WR-ML-00014
[14 empty] | TOTAL | 192.216 |  | 192.216 | 192.216 | 0

## EIFS 300mm BASECOAT (hidden)
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS 300mm BASECOAT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  | (Sqm)
4 | ELEVATION 06 ( LIFT AREA) | JOT-AX-SD-ML-00003_00_E | G-H/3-7 | WALL-L2L3 |  | 1 | 27.3 | 7.6 | 207.48 | LIFT LOBBY OPENING L2,L3 | 2 | 3.18 | 2.4 | 15.264 | 192.216 | 192.216 | 0
CORE WALL AREA
JOT-AX-WR-ML-00016
[14 empty] | TOTAL | 192.216 | 192.216 | 0