## Summary
SN | Description | Total Scope | Valuation at WFA | Previous | This Month | Cumulative
01 | Contract Works | 1600000 | 533925 | 533886.0798 | 93707.6667 | 627593.7465 | 1161518.7465
02 | Variations (old) | 485254.936 | 13173 | 125273.8178 | -6970.7026 | 118303.1152 | 131476.1152
| Total Value of Work Done |  | 547098 | 659159.8976 | 86736.9641 | 745896.8617 | 1292994.8617
03 | New Variations | 1207502.395 | 0 | 412935.1666 | 120383.1464 | 533318.313
| Total Value of Work Done |  | 547098 | 1072095.0642 | 207120.1105 | 1279215.1747 |  | 1826313.1747
04 | Advance Payment |  |  | 153815.69 | 0 | 153815.69
05 | Advance Payment Recovery | 10% |  | -107209.5064 | -20712.0111 | -127921.5175
| TOTAL |  |  | 1118701.2477 | 186408.0995 | 1305109.3472

## Progress Bill
PROGRESS BOQ
Item | Description | Qty. | Unit | Rate | Amount | OCI - Certified |  | Pervious Work Certified |  |  | This Month Workdone |  |  | Cumulative
|  |  |  | Rate | Amount | Progress % | Amount | Pervious % | Pervious Qty | Amount | Progress % | Qty | Amount | Progress % | Qty | Amount
DESIGN AND BUILD OF TERRACO SYSTEM
EIFS WITH TERRACO RENDER SYSTEM
EIFS with TERRACO System, mineral wool, Adhesive, groove requirement,including all necessary framing, fitting, fixing, backing framing support, decoration, Primer, Basecoat and Final coat etc and the like all in accordance with drawings and specifications.
ON BLOCKWORK / CONCRETE WALL
A | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 75mm | 876 | m2 | 295 | 258420 |  |  | 8.383% | 73.438 | 21664.2047 | 2.004% | 17.558 | 5179.5982 | 10.39% | 90.9959 | 26843.8029
B | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 100mm | 692 | m2 | 319 | 220748 | 89.8% | 198241.4271 | 74.08% | 512.65 | 163535.3453 | 15.72% | 108.7965 | 34706.0818 | 89.8% | 621.4465 | 198241.4271
C | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 150mm | 266 | m2 | 347 | 92302 |  |  |  | 0 | 0 | 30.5% | 81.1298 | 28152.0371 | 30.5% | 81.1298 | 28152.0371
D | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 200mm | 682 | m2 | 380 | 259160 | 95.74% | 248117.6104 | 99.13% | 676.0951 | 256916.1456 | 0.8658% | 5.9049 | 2243.8544 | 100% | 682 | 259160
E | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 275mm | 176 | m2 | 415 | 73040 |  |  |  | 0 | 0 | 0% | 0 | 0 |  | 0 | 0
F | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 300mm | 854 | m2 | 435 | 371490 | 20.26% | 75252.564 | 87.09% | 743.7485 | 323530.5801 | 5.354% | 45.7241 | 19890.0042 | 92.44% | 789.4726 | 343420.5843
G | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 400mm | 422 | m2 | 500 | 211000 | 31.07% | 65567.88 | 66.21% | 279.4049 | 139702.4362 | 0.9218% | 3.89 | 1945.0144 | 67.13% | 283.2949 | 141647.4505
STAND ALONE EIFS SYSTEM WITH NECESSARY BACK FRAMING SUPPORT
H | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 75mm | 88 | m2 | 400 | 35200 |  |  |  | 0 | 0 | 0% | 0 | 0 |  | 0 | 0
J | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 300mm | 86 | m2 | 450 | 38700 |  |  | 100% | 86 | 38700 | 0% | 0 | 0 | 100% | 86 | 38700
K | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 400mm | 24 | m2 | 525 | 12600 |  |  | 100% | 24 | 12600 | 0% | 0 | 0 | 100% | 24 | 12600
TERRACO RENDER SYSTEM
TERRACO Render System, Adhesive, groove requirement, including all necessary framing, fitting, fixing, backing framing support, Primer, Basecoat and Final coat decoration, etc and the like all in accordance with drawings and specifications.
ON BLOCKWORK / CONCRETE WALL
A | TERRACO RENDER System (TERRACO acid wash finishes) | 1298 | m2 | 175 | 227150 | 5.909% | 13423.2 | 78.29% | 1016.225 | 177839.3679 | 0.7005% | 9.0919 | 1591.0767 | 78.99% | 1025.3168 | 179430.4446
| Discount |  |  |  | -199810 | 33.37% | -66677.2725 | 33.37% | 0 | -66677 | 0% | 0 | 0 | 33.37% | 0 | -66677
| TOTAL |  |  |  | 1600000 |  | 533925.409 |  |  | 1067811.0798 |  |  | 93707.6667 |  | 72.59% | 1161518.7465
Note on S15: Himal Kosala: WFA Certified qty
Note on S23: Himal Kosala: 195.53 m2 WA-PS005 R2 Completed qty
Note on S25: Himal Kosala: 141.46 m2 WA-PS005 R2 Completed qty
Note on S42: Himal Kosala: WFA Certified Qty (6%) = 77.88m2 Extra Paid 244.28 qty from Nov bill

## 75MM-EIFS
DETAILED STATUS REPORT
Client Name |  | : | Omniyat Investments & Management LLC
Project Name |  | : | Dorchester Hotel (PLOT 18)
Main Contractor |  | : | Khansaheb civil engineering llc
Scope of works |  | : | External Insulation Finishing System (EPS)
EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 75mm
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
RATE BREAKDOWN: 70%-EPS BOARDS,20%-BASECOAT,10%-PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | LEVEL-23,Elevation-0, | JOT-AX-SD-L23-00009_02 | C-E/10-11 | WALL INS. | a | 1 | 12.25 | 4.75 | 58.1875 |  | 0 | 0 | 0 | 0 | 58.1875 | 90% | 52.3687 | 46.55 | 5.8187
JOT-AX-WR-L23-000121, 159
2 | L 31,RESIDENTIAL | JOT-AX-SD-L31-00011_00 | F-G/4-6 | WALL INS. |  | 1 | 12.423 | 3.261 | 40.5114 | Door | 1 | 1 | 2.1 | 2.1 | 38.4114 | 70% | 26.888 | 26.888 | 0
JOT-AX-WR-L31-000153
3 | Hotel Level-30 | JOT-AX-SD-L29-0006_04 | U-X/21-22 | WALL INS |  | 1 | 6.507 | 2.9 | 18.8703 |  | 1 | 1 | 2.1 | 2.1 | 16.7703 | 70% | 11.7392 | 0 | 11.7392
JOT-AX-WR-L30-000187
[14 empty] | TOTAL | 113.3692 |  | 90.9959 | 73.438 | 17.558

## 100MM-EIFS
DETAILED STATUS REPORT
Client Name |  | : | Omniyat Investments & Management LLC
Project Name |  | : | Dorchester Hotel (PLOT 18)
Main Contractor |  | : | Khansaheb civil engineering llc
Scope of works |  | : | External Insulation Finishing System (EPS)
EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 100mm
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PROGRESS % | WORK DONE TO DATE | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS | REMARKS
RATE BREAKDOWN: 70%-EPS BOARDS,20%-BASECOAT,10%-PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
2 | ELEVATION 06 ( LIFT AREA) | JOT-AX-SD-ML-00003_00_E | G-H/3-7 | WALL-L2L3 | BO5 | 1 | 2.9 | 7.6 | 22.04 | LIFT LOBBY OPENING L2,L3 | 0 | 0 | 0 | 0 | 22.04 | 90% | 19.836 | 19.836 | 0 | upto basecoat done under roberts
| CORE WALL AREA | [18 empty] | paint done under KCE
JOT-AX-WR-ML-00014
3 | (HOUSEKEEPING LOBBY) | JOT-AX-SD-GF-00001_00_E | D-F/7-8 | WALL GF | B10 | 1 | 4 | 3.82 | 15.28 |  | 0 | 0 | 0 | 0 | 15.28 | 90% | 13.752 | 13.752 | 0 | upto basecoat done under roberts
| JOT-AX-WR-GF-00017 |  |  |  |  | 1 | 1.7 | 4.87 | 8.279 |  | 0 | 0 | 0 | 0 | 8.279 | 90% | 7.4511 | 7.4511 | 0 | paint done under KCE
13 | GF BALL ROOM WALL | JOT-AX-SD-GF-00002_02 | A-U/23-25 | WALL GF | BO22 | 1 | 21.23 | 7.275 | 154.4483 |  | 0 | 0 | 0 | 0 | 196.3882 | 90% | 176.7494 | 176.7494 | -5e-06 | upto basecoat done under roberts
| JOT-AX-WR-L29-00052 |  |  |  |  | 1 | 9.32 | 4.5 | 41.94 | [10 empty] | paint done under KCE
[14 empty] | TOTAL | 241.9873 |  | 217.7885 | 217.7885 | -5e-06
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
RATE BREAKDOWN: 70%-EPS BOARDS,20%-BASECOAT,10%-PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | STAIR 6 WALL,Elevation-07, | JOT-AX-SD-ML-00003_01 | L2,G/10-11 | WALL-L2 |  | 1 | 4.62 | 7.442 | 34.382 |  | 0 | 0 | 0 | 0 | 34.382 | 100% | 34.382 | 34.382 | 0
JOT-AX-WR-ML-00074_01
| JOT-AX-WR-ML-00110,116 |  | L2,T-W/10-12
2 | Hotel Ramp area ,Elevation-12 | JOT-AX-SD-ML-00003_01 | GF-L2-W/22-23 | WALL,GF-L3 |  | 1 | 13 | 9.98 | 129.74 |  | 0 | 0 | 0 | 0 | 129.74 | 95% | 123.253 | 123.253 | 0
JOT-AX-WR-ML-00107,118
3 | Hotel, near Ball room ,Elevation-14 | JOT-AX-SD-GF-00002_02 | GF-A-U/25 | WALL-GF |  | 1 | 7.859 | 4.5 | 35.3655 |  | 0 | 0 | 0 | 0 | 168.1088 | 10% | 16.8109 | 16.8109 | 0
| JOT-AX-WR-ML-00116 |  |  |  |  | 1 | 18.244 | 7.276 | 132.7433
4 | Hotel ,Damac side ,podium level-2 | JOT-AX-SD-ML-00004_02 | T-W/22-23 | WALL-L2 |  | 1 | 18.557 | 7.242 | 134.3898 | LOUVER-1 | 1 | 2.5 | 1 | 2.5 | 114.7224 | 100% | 114.7224 | 108.9863 | 5.7361
| JOT-AX-WR-ML-00136.140,147 | [8 empty] | LOUVER-2 | 1 | 0.6 | 0.5 | 0.3
[10 empty] | WINDOW-1 | 1 | 3.299 | 2.267 | 7.4788
[10 empty] | WINDOW-2 | 1 | 2.168 | 1.197 | 2.5951
[10 empty] | WINDOW-3 | 1 | 2.168 | 1.473 | 3.1935
[10 empty] | DOOR-1 | 1 | 1.5 | 2.4 | 3.6
5 | L 23 RESIDENTIAL,ELEVATION-20 | JOT-AX-SD-L23-00009_02 | E-D/11 | WALL-L23 |  | 1 | 4.732 | 3.45 | 16.3254 |  | 0 | 0 | 0 | 0 | 16.3254 | 90% | 14.6929 | 11.4278 | 3.2651
JOT-AX-WR-L23-00152,173
6 | L 10 ,RESIDENTIAL | KCE-AX-RFI-L10-00365 | G-D/10-11 |  |  | 1 | 18.313 | 5.45 | 99.8058 |  | 0 | 0 | 0 | 0 | 99.8058 | 70% | 69.8641 | 0 | 69.8641
WR-180
[14 empty] | TOTAL | 563.0845 |  | 373.7253 | 294.86 | 78.8653
[15 empty] | Total qty claimed by sc |  | 591.5138
[15 empty] | WFA approved qty |  | 621.4465
[16 empty] | Difference | 29.9327
Note on R38: Himal Kosala: WIR

## 150MM-EIFS
DETAILED STATUS REPORT
Client Name |  | : | Omniyat Investments & Management LLC
Project Name |  | : | Dorchester Hotel (PLOT 18)
Main Contractor |  | : | Khansaheb civil engineering llc
Scope of works |  | : | External Insulation Finishing System (EPS)
WORK BREAKDOWN : 70% UPTO EPS BOARDS, 20% UPTO BASECOAT, 10% PAINT | [17 empty] | MONTH: | January 2023
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
150MM -EIFS | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | L-10 EIFS | KCE-RFI-L10-00365 | G-D/10-11,L10 | WALL |  | 1 | 21.266 | 5.45 | 115.8997 |  | 0 | 0 | 0 | 0 | 115.8997 | 70% | 81.1298 | 0 | 81.1298
WR-180
[14 empty] | TOTAL | 115.8997 |  | 81.1298 | 0 | 81.1298

## 200MM-EIFS
DETAILED STATUS REPORT
Client Name |  | : | Omniyat Investments & Management LLC
Project Name |  | : | Dorchester Hotel (PLOT 18)
Main Contractor |  | : | Khansaheb civil engineering llc
Scope of works |  | : | External Insulation Finishing System (EPS)
EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 200mm
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
RATE BREAKDOWN: 70%-EPS BOARDS,20%-BASECOAT,10%-PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | LEVEL-4 to 5,STAIR 6 WALL,Elevation-10 | JOT-AX-SD-L4-00005_02 | E-H/10-12 | WALL L4 |  | 1 | 21.97 | 9.92 | 217.9424 |  | 0 | 0 | 0 | 0 | 217.9424 | 10% | 21.7942 | 21.7942 | 0
JOT-AX-WR-L4-00071,JOT-AX-WR-ML-00098_0
2 | LEVEL- GF to 1 ,STAIR-6 WALL,ELEVATION-7 | JOT-AX-SD-GF-00002_02 | T-W/10-14 | WALL GF-1 |  | 1 | 4.613 | 5.275 | 24.3336 |  | 1 | 0.9 | 1.8 | 1.62 | 22.7136 | 100% | 22.7136 | 22.7136 | 0
JOT-AX-WR-ML-00083_00,110,116
2.1 | LEVEL- GF to 1 ,STAIR-6 WALL,ELEVATION-9 | JOT-AX-SD-GF-00002_02 | T-W/10-14 | WALL GF-1 |  | 1 | 5.312 | 5.275 | 28.0208 |  | 1 | 1.1 | 1.8 | 1.98 | 26.0408 | 100% | 26.0408 | 26.0408 | 0
JOT-AX-WR-ML-00083_00
3 | LEVEL-GROUND FLOOR ,NEAR LOBBY | JOT-AX-SD-GF-00001_02 | E-D/6-8 | WALL GF |  | 1 | 5.58 | 5.275 | 29.4345 |  | 0 | 0 | 0 | 0 | 29.4345 | 70% | 20.6042 | 20.6042 | 0
JOT-AX-WR-ML-00077_00
[14 empty] | TOTAL | 296.1313 |  | 91.1528 | 91.1528 | 0
[15 empty] | WFA Amount |  | 248117.6104
[15 empty] | Rate |  | 380
[15 empty] | Approved qty from WFA |  | 652.9411
[16 empty] | Total qty | 744.0938
[16 empty] | BOQ qty | 682
[16 empty] | Extra qty | 62.0938

## EIFS -STAND ALONE (300MM)
DETAILED STATUS REPORT
Client Name |  | : | Omniyat Investments & Management LLC
Project Name |  | : | Dorchester Hotel (PLOT 18)
Main Contractor |  | : | Khansaheb civil engineering llc
Scope of works |  | : | External Insulation Finishing System (EPS)
EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 300mm
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 35%-FRAMING,35%-EPS BOARDS,20%-BASECOAT,10%-PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | STAIR 6 WALL,LEVEL-02 to 3 | JOT-AX-SD-ML-00003_02 | E-H/10-11 | WALL L2 |  | 1 | 4 | 7.275 | 29.1 |  | 0 | 0 | 0 | 0 | 29.1 | 100% | 29.1 | 29.1 | 0
JOT-AX-WR-ML-00085,100,108,104,110
2 | Residential,Stair-6,L4-5 | JOT-AX-SD-L4-00005_02 | T-W/13-14 | WALL L4-5 |  | 1 | 4 | 9.92 | 39.68 |  | 0 | 0 | 0 | 0 | 39.68 | 100% | 39.68 | 39.68 | 0
JOT-AX-WR-ML-00076,81,90,98
[14 empty] | TOTAL | 68.78 |  | 68.78 | 68.78 | 0
Work is 100% completed
[16 empty] | BOQ qty | 86
[15 empty] | Extra qty from BOQ |  | 17.22

## EIFS -STAND ALONE (400MM)
DETAILED STATUS REPORT
Client Name |  | : | Omniyat Investments & Management LLC
Project Name |  | : | Dorchester Hotel (PLOT 18)
Main Contractor |  | : | Khansaheb civil engineering llc
Scope of works |  | : | External Insulation Finishing System (EPS)
EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 400mm
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 35%-FRAMING,35%-EPS BOARDS,20%-BASECOAT,10%-PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | Stair-6,GF to 1 st floor | JOT-AX-SD-GF-00002_02 | Grid-E-H/10-12 | WALL GF |  | 1 | 3.22 | 7.275 | 23.4255 |  | 0 | 0 | 0 | 0 | 23.4255 | 100% | 23.4255 | 23.4255 | 0
JOT-AX-WR-GF-00086,99
JOT-AX-WR-ML-00110
[14 empty] | TOTAL | 23.4255 |  | 23.4255 | 23.4255 | 0
Work is 100% completed
[16 empty] | BOQ qty | 24
[15 empty] | Extra qty from BOQ |  | 0.5745

## EIFS RENDER
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
TERRACO RENDER System (TERRACO acid wash finishes) | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  | (Sqm)
1 | L4 ZONE 3, GATE 2 FRONT | JOT-AX-SD-L04-00005_00_E | A-I/Y1-4 |  |  | 1 | 79.9 | 1.2 | 95.88 |  | 0 | 0 | 0 | 0 | 95.88 | 95.88 | 0
AREA
JOT-AX-WR-L4-00009
[14 empty] | TOTAL | 95.88 | 95.88 | 0
[12 empty] | Total qty from BOQ |  |  | 1298
[14 empty] | Omission from V01 | -569.254
[14 empty] | Omission from V05 | -219.95
[14 empty] | New qty need to be completed | 508.796
[14 empty] | Completed qty upto now | 95.88
[14 empty] | Balance rendering qty | 412.916

## VARIATIONS
DORCHESTER HOTEL & RESIDENCIES
JOYZ OVERSEAS - VARIATION SCHEDULE
SN | Variations | Total Work Scope |  |  | Previous |  | This Month | This Month | Cumulative
|  | QTY | Rate | Amount | QTY | Amount | QTY | Amount | % | QTY | Amount
1 | RPJV-JOT-VOR-001 Rev00
| Additional EIFS for the parapets at level 04 and level 29 | 629.95 | 319 | 200954.05 | 257.7813 | 82232.2219 | 225.1901 | 71835.6419 | 76.67% | 482.9714 | 154067.8638
| DDT: L29 Parapet Hight error | -60.696 | 319 | -19362.024 | 0 | 0 | 0 | 0 | 0% | 0 | 0
| DDT: Contract scope (EIFS Render) | -569.254 | 175 | -99619.45 | 0 | 0 | -436.4368 | -76376.4446 | 76.67% | -436.4368 | -76376.4446
2 | RPJV-JOT-VOR-002 Rev00
| Additional EIFS for the non accessible balconies at various floor levels | 838.85 | 380 | 318763 | 0 | 0 | 0 | 0 | 0% | 0 | 0
| DDT: Rate error. Use 150mm Build up Rate | 838.85 | -33 | -27682.05 | 0 | 0 | 0 | 0 | 0% | 0 | 0
3 | RPJV-JOT-VOR-003 Rev00 | 823 | 32.16 | 26467.68 | 210.1893 | 6759.6879 | 65.3747 | 2102.4504 | 33.48% | 275.564 | 8862.1382
| PVC Grooves for EIFS | 5000 | 32.16
| DDT: Quantity Error. Lump Sum Contract | -4177 | 32.16
4 | RPJV-JOT-VOR-004 Rev00
| Additional EIFS at level 02 entrance | 169.47 | 319 | 54060.93 | 55.7411 | 17781.398 | 7.963 | 2540.1997 | 37.59% | 63.7041 | 20321.5977
5 | RPJV-JOT-VOR-005 Rev00
| Additional EIFS for the parapets at level 02 floor | 219.95 | 319 | 70164.05 | 99.29 | 31673.51 | 71.55 | 22824.45 | 77.67% | 170.84 | 54497.96
| DDT: Contract scope (EIFS Render) | -219.95 | 175 | -38491.25 | 0 | 0 | -170.84 | -29897 | 77.67% | -170.84 | -29897
Sub-Totals |  |  |  | 485254.936 |  | 138446.8178 |  | -6970.7026 | 27.09% |  | 131476.1152
NEW VARIATIONS
WA PS-005
Additions
6 | Installation of stud frame + 200mm EIFS system to replace 300mm EIFS system (PS-005) | 854 | 450 | 384300 | 419.922 | 188964.905 | 11.8417 | 5328.7875 | 50.56% | 431.7638 | 194293.6925
7 | Installation of stud frame + 200mm EIFS system to replace 400mm EIFS system (PS-005) | 422 | 525 | 221550 | 351.342 | 184454.5686 | 19.393 | 10181.3163 | 87.85% | 370.735 | 194635.885
8 | Installation of stud frame + 200mm EIFS system to replace 275mm EIFS system (PS-005) | 176 | 415 | 73040 | 0 | 0 | 0 | 0 | 0% |  | 0
9 | Removal of framing in areas where the works are completed (PS-005 R1) | 1 | 25250 | 25250 | 1 | 25250 | 0 | 0 | 100% | 1 | 25250
Omission
10 | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 300mm (PS-005 R2) | 658.47 | 435 | -286434.45 | 548.2185 | -238475.0301 | 30.2599 | -13163.0772 | 87.85% | 578.4784 | -251638.1073
11 | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 400mm (PS-005 R2) | 280.54 | 500 | -140270 | 137.9449 | -68972.4362 | 3.89 | -1945.0144 | 50.56% | 141.8349 | -70917.4505
12 | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 275mm (PS-005 R2) | 176 | 415 | -73040 | 0 | 0 | 0 | 0 | 0% | 0 | 0
WA PS-019
13 | Removal & reinstatement of EIFS for waterproofing termination at ground floor as per the attached Joyz Variation ref. KCE-JOT-VOR-00002 Rev 01 dated 15.08.22 (PS-019 R0) | 1 | 7860.45 | 7860.45 | 0 | 0 | 0 | 0 | 0% |  | 0
14 | Supply & installation of 100mm thick EIFS on stair wall at Residence level 23 as per the attached Joyz Variation ref. KCE-JOT-VOR-00003 Rev 0 dated 01.09.22 (PS-019 R1) | 10 | 319 | 3190 | 9 | 2871 | 0 | 0 | 90% | 9 | 2871
15 | Additional scope of EIFS 50mm,75mm,100mm thick system and EIFS 20mm render as per the attached Joyz Variation ref. KCE- JOT-VOR-00004 dated 14.09.22. (PS-019 R3)
15.1 | Render on Planter Wall | 1799.35 | 175 | 314886.25 | 1052.2056 | 184135.973 | 330.459 | 57830.3171 | 76.84% | 1382.6645 | 241966.2901
15.2 | Render on Parapet Coping & Internal Face | 638 | 175 | 111650 | 0 | 0 | 0 | 0 | 0% |  | 0
15.3 | 50mm EIFS Build-up on top of the Level-02 Parapet Wall | 11.75 | 270 | 3172.5 | 0 | 0 | 0 | 0 | 0% |  | 0
15.4 | 100mm EIFS at Level-01 AV Rooms External | 25.8075 | 319 | 8232.5925 | 20.646 | 6586.074 | 2.5808 | 823.2593 | 90% | 23.2268 | 7409.3333
15.5 | 75mm EIFS at Basement-01 External Seating Area | 47.92 | 295 | 14136.4 | 40.8589 | 12053.3681 | 4.5399 | 1339.2631 | 94.74% | 45.3987 | 13392.6312
15.6 | Render on Basement-01 to Level-01A | 176.05 | 175 | 30808.75 | 167.242 | 29267.3441 | 0 | 0 | 95% | 167.242 | 29267.3441
15.7 | Render near AV Room External Area | 47.2 | 175 | 8260 | 42.48 | 7434 | 0 | 0 | 90% | 42.48 | 7434
16 | Cutting of existing 100mm thick EIFS and reinstatement of EIFS system after the cutting at L 29 parapet (PS-019 R4) | 160 | Rate Only | 34345 | 1 | 34345 | 159 | 0 | 100% | 160 | 34345
17 | Supply & installation of insulation behind the gabion wall as per the response to KCE-AX-RFI-GF-00072 dt 15.07.22 & Joyz variation submission ref JOT-KCE-DOR-202209-005 dated 26.10.22. (PS-019 R4) | 115 | 120 | 13800 | 0 | 0 | 0 | 0 | 0% |  | 0
18 | Supply & installation of 200mm fluted EIFS on Level 29 as per the response to KCE-AX-RFI-GF-00072 date 15.07.22 & Joyz variation submission ref JOT-KCE-DOR-202209-005 dated 26.10.22 (PS-019 R4) | 120.404 | 660 | 79466.64 | 0 | 0 | 0 | 0 | 0% |  | 0
19 | Supply & installation of 400mm fluted EIFS (200mm built up + 200mm EIFS) on level 28 as per the Joyz variation submission JOT-KCE-DOR-202209-005 dated 26.10.22 and mockup approval. (PS-019 R4) | 67.404 | 750 | 50553 | 47.32 | 35490 | 20.28 | 15210 | 100.3% | 67.6 | 50700
20 | External door jamb finishes due to changes in finishing details & as per Joyz variation submission ref JOT-KCE-VOR-00006 dated 17.11.22. (PS-019 R5) | 16 | 2800 | 44800 | 0 | 0 | 0 | 0 | 0% |  | 0
21 | Paint finish to match with GRC colour in place of GRC coping at Residence tower level 32 as per Joyz variation submission ref JOT-KCE-VOR-00007 dated 17.11.22. (PS-019 R5) | 67 | 40 | 2680 | 0 | 0 | 0 | 0 | 0% |  | 0
22 | Additional EIFS works as per the shop drawing ref GLA-AX-SD-L31-66195 comments & Joyz variation submission ref JOT-KCE-VOR-00007 dated 17.11.22. (PS-019 R5) | 68 | 295 | 20060 | 0 | 0 | 48.678 | 14360.01 | 71.59% | 48.678 | 14360.01
23 | Removal & reinstatement of 200m thick with 400mm thick EIFS and framing as per the response to KCE-AX-RFI-GF-00254 dt 22.10.22 & & Joyz variation submission ref JOT-KCE-VOR-00007 dated 17.11.22. (PS-019 R5) | 33.44 | 380 | 12707.2 | 25.08 | 9530.4 | 0 | 0 | 75% | 25.08 | 9530.4
24 | Additional scope of EIFS 20mmm render as per the attached Joyz variation ref. KCE-JOT-VOR-00004 rev 1 dated 29.11.22. (PS-019 R6) | 1073.42 | 175 | 187848.5 | 0 | 0 | 0 | 0 | 0% |  | 0
[10 empty] | 90% | only until WA
| Additional area of 200mm EIFS in L30(L29 in Instruction) | 12.868 | 380 | 4889.84 | 0 | 0 | 12.8674 | 4400.6508 | 100% | 12.8674 | 4400.6508
| Additional area of 75mm EIFS in L30(L29 in Instruction) | 58.353 | 295 | 17214.135 | 0 | 0 | 28.313 | 7517.1015 | 48.52% | 28.313 | 7517.1015
| Additional area of 20mm Plastering + Paint finish in L30(L29 in Instruction) | 30.86 | 175 | 5400.5 | 0 | 0 | 0 | 0 | 0% |  | 0
Additional area in which 300mm EIFS change to 300mm built-up+200mm EIFS (500mm thick) in L29.
| 300mm builtup+ 200mm EIFS (500mm thick) | 98.31 | 600 | 58986 | 0 | 0 | 15.4642 | 8350.668 | 15.73% | 15.4642 | 8350.668
| Omission of 300mm EIFS | 98.31 | 435 | -42764.85 | 0 | 0 | 15.4642 | 6054.2343 | 15.73% | 15.4642 | 6054.2343
| 100 mm Built-up + Rendering + Trustone paint finish in L29 | 29.1305 | 375 | 10923.9375 | 0 | 0 | 12.1352 | 4095.63 | 41.66% | 12.1352 | 4095.63
Sub-Totals |  |  |  | 1207502.395 |  | 412935.1666 |  | 120383.1464 | 44.17% |  | 533318.313
Note on K7: Himal Kosala: This qty include WFA qty 35.21 (see the measurements)
Note on K9: Himal Kosala: As per WFA, this deduction already paid in EIFS render in main bill
Note on K15: Himal Kosala: WFA qty 60.35
Note on K23: Himal Kosala: qtys were mistakenly add in wrong variation (please see the measurement sheets)
Note on K24: Himal Kosala: As per WFA, this deduction already paid in EIFS render in main bill

## RPJV Variation
| NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PROGRESS % | WORK DONE TO DATE | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
| RPJV-JOT-VOR-001 Rev00 | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
| 1 | L4, PARAPET | JOT-AX-SD-L4-00005_02 | W-X/13-16 | WALL L4 | BO23 | 1 | 25.15 | 1.4 | 35.21 |  | 0 | 0 | 0 | 0 | 35.21 | 100% | 35.21 | 35.21 | 0
JOT-AX-WR-L4-00036
| 2 | L4, PARAPET | JOT-AX-SD-L4-00005_02 | X-Q/23-24 | PARAPET L4 |  | 1 | 28.9 | 1.4 | 40.46 |  | 0 | 0 | 0 | 0 | 40.46 | 100% | 40.46 | 40.46 | 0
JOT-AX-WR-L4-00073
| 3 | L4 PARAPET, ROADSIDE | JOT-AX-SD-L4-00005_02 | G-X / 11-16 | PARAPET L4, PAINT |  | 1 | 23.19 | 1.4 | 32.47 |  | 0 | 0 | 0 | 0 | 32.47 | 20% | 6.494 | 6.494 | 0
JOT-AX-WR-L2-00075_00
| 4 | L4 PARAPET,RESIDENTIAL | JOT-AX-SD-L4-00005_02 | W-X/15-17 | WALL,L4 |  | 1 | 2.877 | 1.4 | 4.0278 |  | 0 | 0 | 0 | 0 | 4.0278 | 70% | 2.8195 | 2.8195 | 0
JOT-AX-WR-L4-00089,97
| 6 | L4, PARAPET | JOT-AX-SD-L4-00005_02 | B-G/Y1 | WALL L4 | BO15 | 1 | 30.7 | 1.1 | 33.77 |  | 0 | 0 | 0 | 0 | 33.77 | 100% | 33.77 | 33.77 | 0
JOT-AX-WR-L4-00031
| 10 | L4, PARAPET | JOT-AX-SD-L4-00005_02 | F-H/Y1-4 | WALL L4 | BO19 | 1 | 49.2 | 1.1 | 54.12 |  | 0 | 0 | 0 | 0 | 54.12 | 100% | 54.12 | 54.12 | 0
JOT-AX-WR-L4-00036
| 14 | L4-DAMAC SIDE | JOT-AX-SD-L4-00005_02 | B-X/23-24 | WALL-L4 | B024 | 1 | 34.92 | 1.4 | 48.888 |  | 0 | 0 | 0 | 0 | 48.888 | 90% | 43.9992 | 43.9992 | 0 | paint done under khansaheb
|  | JOT-AX-WR-L4-00062_00 | [18 empty] | in no:01
| 1 | L29, PARAPET | RP-LX-SD-L29-1856 | S-T/16-18 | WALL L29 | BO11 | 1 | 9 | 1.4 | 12.6 |  | 0 | 0 | 0 | 0 | 12.6 | 100% | 12.6 | 12.6 | 0
JOT-AX-WR-GF-00005
| 4 | L29, PARAPET | JOT-AX-SD-ML-00006_01 | S-W/13-14 | WALL L29 | BO13 | 1 | 16.5 | 1.4 | 23.1 |  | 0 | 0 | 0 | 0 | 23.1 | 100% | 23.1 | 23.1 | 0
JOT-AX-WR-L29-00020
| 5 | L29, PARAPET | JOT-AX-SD-ML-00006_01 | S-T/18-24 | WALL L29 | BO14 | 1 | 45 | 1.4 | 63 |  | 0 | 0 | 0 | 0 | 63 | 100% | 63 | 63 | 0
JOT-AX-WR-L29-00030
| 7 | L29, PARAPET | JOT-AX-SD-ML-00006_01 | S-T/14-18 | WALL L29 | BO16 | 1 | 28.31 | 1.4 | 39.634 |  | 0 | 0 | 0 | 0 | 39.634 | 100% | 39.634 | 39.634 | 0
JOT-AX-WR-L29-00037
| 8 | L29, PARAPET | JOT-AX-SD-ML-00006_01 | S-X/23-24 | WALL L29 | BO17 | 1 | 24.08 | 1.4 | 33.712 |  | 0 | 0 | 0 | 0 | 33.712 | 100% | 33.712 | 33.712 | 0
JOT-AX-WR-L29-00040
| 9 | L29, PARAPET | JOT-AX-SD-ML-00006_01 | W-X/13-18 | WALL L29 | BO18 | 1 | 7.5 | 1.4 | 10.5 |  | 0 | 0 | 0 | 0 | 10.5 | 90% | 9.45 | 9.45 | 0 | Paint balance to do
|  | JOT-AX-WR-L29-00043 |  |  |  |  | 1 | 4.07 | 1.6 | 6.512 |  | 0 | 0 | 0 | 0 | 6.512 | 90% | 5.8608 | 5.8608 | 0 | Paint balance to do
[7 empty] | 1 | 21.58 | 1.65 | 35.607 |  | 0 | 0 | 0 | 0 | 35.607 | 90% | 32.0463 | 32.0463 | 0 | Paint balance to do
1 | 11 | L29, PARAPET | JOT-AX-SD-ML-00006_02 | S-T/13-15 | PARAPET WALL L29 | BO20 | 1 | 6.43 | 1.4 | 9.002 |  | 0 | 0 | 0 | 0 | 9.002 | 100% | 9.002 | 9.002 | 0
JOT-AX-WR-L29-00048
| 12 | L29, PARAPET | JOT-AX-SD-ML-00006_02 | V-X/13-14 | PARAPET WALL L29 | BO21 | 1 | 9.92 | 1.4 | 13.888 |  | 0 | 0 | 0 | 0 | 13.888 | 90% | 12.4992 | 12.4992 | 0 | paint balance to do
JOT-AX-WR-L29-00051
| 15 | L29 ROAD SIDE | JOT-AX-SD-ML-00006_02 | B-X/23-24 | L29 WALL | B025 | 1 | 18.63 | 1.4 | 26.082 |  | 0 | 0 | 0 | 0 | 26.082 | 70% | 18.2574 | 18.2574 | 0 | paint done under khansaheb
JOT-AX-WR-L4-00068_00
| 16 | L29 PARAPET | JOT-AX-SD-ML-00006_02 | V-X/13-14 | L29 WALL | PA10 | 1 | 17.55 | 1.4 | 24.57 |  | 0 | 0 | 0 | 0 | 24.57 | 10% | 2.457 | 2.457 | 0
JOT-AX-WR-L4-00055_00
| 17 | L29 PARAPET,HOTEL | JOT-AX-SD-L29-00006_04 | W-X/15-17 |  |  | 1 | 4 | 1.4 | 5.6 |  | 0 | 0 | 0 | 0 | 5.6 | 80% | 4.48 | 0 | 4.48
WIR-169,192
[15 empty] | TOTAL | 552.7528 |  | 482.9714 | 478.4914 | 4.48
RPJV-JOT-VOR-004 Rev00
| NO | BUILDING | DRAWING REF. NO/INSTRUCTION REF./RFI REF. | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
| WORK BREAKDOWN: 70%-INSULATION,20%-BASECOAT,10%-PAINTING | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
| 1 | HOTEL ENTRANCE | JOT-AX-SD-ML-00004_02 | L2,GRID-T-W/18-19 |  |  | 1 | 18.937 | 4.205 | 79.6301 |  | 0 | 0 | 0 | 0 | 79.6301 | 80% | 63.7041 | 55.7411 | 7.963
JOT-AX-WR-L2-00144,150
[15 empty] | TOTAL | 79.6301 |  | 63.7041 | 55.7411 | 7.963
RPJV-JOT-VOR-005 Rev00
| NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PROGRESS % | WORK DONE TO DATE | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS | REMARKS
| RATE BREAKDOWN: 70%-EPS BOARDS,20%-BASECOAT,10%-PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
| 1 | L2 PARAPET, ROADSIDE | JOT-AX-SD-L2-00004_03 | U-Z/13-22 | WALL L2 |  | 1 | 86.03 | 1.4 | 120.44 |  | 0 | 0 | 0 | 0 | 120.44 | 100% | 120.44 | 120.44 | 0
JOT-AX-WR-L2-00078,82,84,92,96,109
| 2 | L2 parapet,Damac side,Hotel | JOT-AX-SD-L2-00004_03 | Y-X/23-25 | L2 |  | 1 | 36 | 1.4 | 50.4 |  | 0 | 0 | 0 | 0 | 50.4 | 100% | 50.4 | 45.36 | 5.04
JOT-AX-WR-L2-00144,156,164,163,161
[15 empty] | TOTAL | 170.84 |  | 170.84 | 165.8 | 5.04
Note on S4: Himal Kosala: This is the WFA qty
Note on R55: Himal Kosala: WIR for EIFS only, no WIR for basecoat approval

## PVC GROOVE
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
RPJV-JOT-VOR-003 Rev00 | [5 empty] | NO | LENGTH | AREA |  | NO | LENGTH | AREA |  |  |  |  | (Sqm)
1 | STAIR 6 WALL,Elevation-10 | JOT-AX-SD-L4-00005_02 | E-H/10-12 | WALL L4 |  | 2 | 9.92 | 19.84 |  | 0 | 0 | 0 | 19.84 | 100% | 19.84 | 19.84 | 0
JOT-AX-WR-L4-00071
2 | LEVEL-2 PARAPET-BASECOAT | JOT-AX-SD-L4-00004_03 | U-Z/13-15 | WALL L2 |  | 6 | 1.4 | 8.4 |  | 0 | 0 | 0 | 8.4 | 100% | 8.4 | 8.4 | 0
JOT-AX-WR-L2-00082_00
3 | LEVEL-4,STAIR 6 WALL,Elevation-08 | JOT-AX-SD-L4-00005_02 | E-H/10-12 | WALL L4 |  | 2 | 9.92 | 19.84 |  | 0 | 0 | 0 | 19.84 | 100% | 19.84 | 19.84 | 0
JOT-AX-WR-L4-00070_01
4 | GF Ballroom Wall | JOT-AX-SD-GF-00002_02 | A-U/23-25 | WALL GF |  | 4 | 7.28 | 29.12 |  | 0 | 0 | 0 | 29.12 | 100% | 29.12 | 29.12 | 0
JOT-AX-WR-ML-00093_00
5 | Residential,stair-6,L2 | JOT-AX-SD-ML-00003_02 | E-H/10-11 | WALL L2 |  | 4 | 7.28 | 29.12 |  | 0 | 0 | 0 | 29.12 | 100% | 29.12 | 29.12 | 0
JOT-AX-WR-ML-00110_00
6 | LEVEL-2 PARAPET-BASECOAT | JOT-AX-SD-L4-00004_03 | U-Z/18-22 | WALL L2 |  | 6 | 1.4 | 8.4 |  | 0 | 0 | 0 | 8.4 | 100% | 8.4 | 8.4 | 0
JOT-AX-WR-L2-00096_00
7 | LEVEL-2 Hotel Ramp | JOT-AX-SD-ML-00004_03 | W/18-23 | WALL GF to L3 |  | 4 | 9.98 | 39.92 |  | 0 | 0 | 0 | 71.92 | 100% | 71.92 | 68.324 | 3.596
| JOT-AX-WR-ML-00118,119,140 |  |  |  |  | 4 | 8 | 32
8 | Hotel,Damac side, | JOT-AX-SD-ML-00004_03 | W-T/23 | level-2 to 4 |  | 3 | 7.242 | 21.726 |  | 0 | 0 | 0 | 28.574 | 100% | 28.574 | 27.1453 | 1.4287
| JOT-AX-WR-ML-00140 |  |  |  |  | 1 | 4.873 | 4.873
[6 empty] | 1 | 1.975 | 1.975
[12 empty] | TOTAL | 215.214 |  | 215.214 | 210.1893 | 5.0247

## EIFS + BUILTUP (300MM)
DETAILED STATUS REPORT
Client Name |  | : | Omniyat Investments & Management LLC
Project Name |  | : | Dorchester Hotel (PLOT 18)
Main Contractor |  | : | Khansaheb civil engineering llc
Scope of works |  | : | External Insulation Finishing System (EPS)
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
EIFS SYSTEM+BUILT UP(300MM)- 35% framing, 35% ESP Boards, 20% Basecoat, 10% Paint | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | STAIR 6 WALL,LEVEL-02 to 3 | JOT-AX-SD-ML-00003_02 | E-H/10-11 | WALL L2 |  | 1 | 9.275 | 7.442 | 69.0246 |  | 0 | 0 | 0 | 0 | 69.0246 | 100% | 69.0246 | 69.0246 | 0
JOT-AX-WR-ML-00085,100,104,116
2 | Hotel ramp area,Level-1 to lvl-3 | JOT-AX-SD-ML-00004_03 | W/18-22 | WALL L2-3 |  | 0.5 | 26.051 | 2.599 | 33.8533 |  | 0 | 0 | 0 | 0 | 244.9024 | 95% | 232.6573 | 232.6573 | 0
| JOT-AX-WR-ML-00107_00,117,118,119 |  |  |  |  | 1 | 4.01 | 9.98 | 40.0198 |  | 0 | 0 | 0 | 0
[6 empty] | 1 | 26.05 | 7.38 | 192.249 |  | 1 | 2.795 | 7.592 | 21.2196
3 | Residential area,lvl-2 to lvl-3 | JOT-AX-SD-ML-00003_02 | G/4-7 | WALL L2-3 |  | 1 | 25.135 | 7.037 | 176.875 |  | 0 | 0 | 0 | 0 | 176.875 | 35% | 61.9062 | 61.9062 | 0
JOT-AX-WR-ML-00103_00
4 | Residential & Hotel entrance lvl-23,Elevation-20 | JOT-AX-SD-L23-00009_02 | D-G/10-11 | WALL L23 |  | 1 | 14.46 | 3.45 | 49.887 | D-03b | 1 | 1.2 | 2.1 | 2.52 | 47.367 | 95% | 44.9987 | 33.1569 | 11.8418
JOT-AX-WR-ML-00120, JOT-AX-WR-L23-00159,191.
5 | Hotel Level-17,Elevation-24 | JOT-AX-SD-L17-00008_02 | E-H/10-11 | WALL L17 |  | 1 | 8.6 | 3.85 | 33.11 |  | 0 | 0 | 0 | 0 | 33.11 | 70% | 23.177 | 23.177 | 0
JOT-AX-WR-ML-00120
[14 empty] | TOTAL | 571.279 |  | 431.7638 | 419.922 | 11.8418

## EIFS + BUILTUP (400MM)
DETAILED STATUS REPORT
Client Name |  | : | Omniyat Investments & Management LLC
Project Name |  | : | Dorchester Hotel (PLOT 18)
Main Contractor |  | : | Khansaheb civil engineering llc
Scope of works |  | : | External Insulation Finishing System (EPS)
WORK BREAKDOWN : 70% UPTO EPS BOARDS, 20% UPTO BASECOAT, 10% PAINT
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
EIFS SYSTEM+BUILT UP(400MM)- 35% framing, 35% ESP Boards, 20% Basecoat, 10% Paint | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | Stair-6,GF to 1 st floor | JOT-AX-SD-GF-00002_02 | E-H/10-12 | WALL GF-L1 |  | 1 | 8.477 | 7.275 | 61.6702 |  | 0 | 0 | 0 | 0 | 61.6702 | 100% | 61.6702 | 61.6702 | 0
JOT-AX-WR-GF-00086,99,116
2 | Residential ,road side,GF to 1 st floor | JOT-AX-SD-ML-00001_02 | G-H/3-8 | WALL GF-L1 |  | 1 | 24.817 | 7.275 | 180.5437 | D-03b | 4 | 1.2 | 2.1 | 10.08 | 170.4637 | 80% | 136.3709 | 119.3246 | 17.0464
JOT-AX-WR-ML-00095,106,107,157,158,189
3 | Residential ,Lobby,GF to 1 st floor | JOT-AX-SD-ML-00001_02 | E-F/6-7 | WALL GF-L1 |  | 1 | 6.694 | 7.28 | 48.7323 |  | 1 | 1 | 1.8 | 1.8 | 46.9323 | 95% | 44.5857 | 42.2391 | 2.3466
JOT-AX-WR-ML-00106_00,115,128,190
4 | RESIDENTIAL,RAMP AREA,GF to Level-3 | JOT-AX-SD-ML-00001_02 | G-D/Y1 | WALL GF-L3 |  | 1 | 11.32 | 11.635 | 131.7082 |  | 2 | 1 | 1.8 | 3.6 | 128.1082 | 100% | 128.1082 | 128.1082 | 0
JOT-AX-WR-ML-00111_00,112,113,114
[14 empty] | TOTAL | 407.1744 |  | 370.735 | 351.342 | 19.393

## KCE Variation
DETAILED STATUS REPORT
Client Name |  | : | Omniyat Investments & Management LLC
Project Name |  | : | Dorchester Hotel (PLOT 18)
Main Contractor |  | : | Khansaheb civil engineering llc
Scope of works |  | : | External Insulation Finishing System (EPS)
KCE-VOR-04, ITEMS-04, 20MM PLASTERING FOR LEVEL 01
NO | BUILDING | DRAWING REF. NO/INSTRUCTION REF./RFI REF. | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 90%-PLASTERING,10%-PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | 20MM PLASTER AT LEVEL-1,AV ROOMS EXTERNAL | E11/K116/SN/dm/281, KCE-AX-RFI-L1-00232 | 25/T-U | WALL-LVL-1 AV ROOMS |  | 1 | 16 | 2.95 | 47.2 |  | 0 | 0 | 0 | 0 | 47.2 | 90% | 42.48 | 42.48 | 0
JOT-AX-WR-L1-00149
[14 empty] | TOTAL | 47.2 |  | 42.48 | 42.48 | 0
KCE-VOR-04, ITEMS-04, 100MM EIFS FOR LEVEL 01
NO | BUILDING | DRAWING REF. NO/INSTRUCTION REF./RFI REF. | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 70%-EPS BOARDS,20%-BASECOAT,10%-PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | 100MM EIFS AT LEVEL-1,AV ROOMS EXTERNAL | E11/K116/SN/dm/281, KCE-AX-RFI-L1-00232 | 25/T-U | WALL-LVL-1 AV ROOMS |  | 1 | 9.3 | 2.775 | 25.8075 |  | 0 | 0 | 0 | 0 | 25.8075 | 90% | 23.2268 | 20.646 | 2.5808
JOT-AX-WR-L1-122_00,146
[14 empty] | TOTAL | 25.8075 |  | 23.2268 | 20.646 | 2.5808
VOR-4, ITEM -5,75 MM EIFS
NO | BUILDING | DRAWING REF. NO/INSTRUCTION REF./RFI REF. | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 70%-EPS BOARDS,20%-BASECOAT,10%-PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | 75MM EIFS AT B-1, EXTERNAL SEATING AREA | E11/K116/SN/dm/281, KCE-AX-RFI-L1-00232 | EXTERNAL SEATING AREA | WALL-B-1 EXTERNAL |  | 1 | 10.25 | 4.675 | 47.9187 | D-03e | 1 | 1.2 | 2.1 | 2.52 | 45.3987 | 100% | 45.3987 | 40.8589 | 4.5399
JOT-AX-WR-B1-123_00,137,148
[14 empty] | TOTAL | 45.3987 |  | 45.3987 | 40.8589 | 4.5399
KCE-VOR-04, ITEM 06, PLASTER ON WALL SEATING AREA @BASEMENT
NO | BUILDING | DRAWING REF. NO/INSTRUCTION REF./RFI REF. | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 90%-20MM PLASTERING,10%-PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | 20mm PLASTER AT B-1, EXTERNAL SEATING AREA | E11/K116/SN//, KCE-AX-RFI-B1-00186 | EXTERNAL SEATING AREA | WALL-B-1 EXTERNAL |  | 1 | 11.285 | 4.675 | 52.7574 |  | 0 | 0 | 0 | 0 | 52.7574 | 95% | 167.242 | 167.242 | 0
| JOT-AX-WR-B1-00124_00,138 |  | ABOVE GF |  |  | 1 | 31.612 | 3.9 | 123.2868 |  | 0 | 0 | 0 | 0 | 123.2868
[14 empty] | TOTAL | 176.0442 |  | 167.242 | 167.242 | 0
KCE-VOR-04, ITEM 01, RENDER ON PLANTER WALLS AREA @
NO | BUILDING | DRAWING REF. NO/INSTRUCTION REF./RFI REF. | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 90%-20MM PLASTERING,10%-PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | Ground floor Planter wall EIFS render plaster | FE-LX-SD-GL-00006_00 | GF Planter wall |  |  | 1 | 11.5 | 1.38 | 15.87 |  | 0 | 0 | 0 | 0 | 156.8335 | 90% | 141.1501 | 141.1501 | 0
[6 empty] | 1 | 21.8 | 0.9 | 19.62
[6 empty] | 1 | 29.25 | 0.9 | 26.325
[6 empty] | 1 | 14.2 | 1.115 | 15.833
[6 empty] | 1 | 27.75 | 1.45 | 40.2375
[6 empty] | 1 | 29.96 | 1.3 | 38.948
| PLANTER WALL,NEAR KCE OFFICE | WIR: JOT-AX-WR-GF-00131 | GRID-A/3-5 | WALL |  | 1 | 23.216 | 1.3 | 30.1808 |  | 0 | 0 | 0 | 0 | 347.9294 | 90% | 313.1365 | 313.1365 | 0
| LPG TANK ,ROAD SIDE | WIR: JOT-AX-WR-GF-00134 | GRID-K/Y1 | LPG TANK INSIDE |  | 1 | 34.253 | 2.9 | 99.3337
| CANAL SIDE WALL | WIR: JOT-AX-WR-GF-00131 | GRID-17-21/A | WALL |  | 1 | 32.951 | 1 | 32.951
| CANAL SIDE WALL | WIR: JOT-AX-WR-GF-00131 | GRID-20-24/A | SIDES+TOP |  | 1 | 37.411 | 1.35 | 50.5049
| CANAL SIDE WALL | WIR: JOT-AX-WR-GF-00131 | GRID-23-24/A | WALL |  | 1 | 28.011 | 1.4 | 39.2154
| CANAL SIDE WALL | WIR: JOT-AX-WR-GF-00131 | GRID-18-21/A | COPING |  | 4 | 3.848 | 0.45 | 6.9264
| CANAL SIDE WALL | WIR: JOT-AX-WR-GF-00131 | GRID-21/A | WALL |  | 1 | 3.85 | 0.75 | 2.8875
| NEAR ENTRANCE OF HOTEL | WIR: JOT-AX-WR-GF-00131 | GRID-15-16/B-C | WALL |  | 1 | 33.73 | 1.2 | 40.476
| NEAR ENTRANCE OF HOTEL | WIR: JOT-AX-WR-GF-00131 | GRID-15-16/V-Z | WALL |  | 1 | 32.467 | 1.4 | 45.4538
| Damac side |  | GRID-24/T | WALL |  | 1 | 4.429 | 5 | 22.145 |  | 0 | 0 | 0 | 0 | 156.7621 | 50% | 78.3811 | 0 | 78.3811
|  |  | GRID-24/T | WALL |  | 1 | 3.37 | 8.55 | 28.8135
|  |  | GRID-24/T | WALL |  | 1 | 2.054 | 3.2 | 6.5728
|  |  | GRID-24/B | WALL |  | 1 | 4.466 | 3 | 13.398
|  |  | GRID-24/B | Block wall |  | 1 | 17.714 | 1.4 | 24.7996
|  |  | GRID-24/B | External wall of stair |  | 1 | 7.152 | 1.1 | 7.8672
|  |  | GRID-24/A | Stair wall ,and outer wall |  | 1 | 22.44 | 1.3 | 29.172
|  |  | GRID-24/A | Wall of planter side |  | 1 | 13.33 | 1.8 | 23.994
2 | SECOND FLOOR PLANTER WALL/ECO1A
a | NEAR CLIENT OFFICE |  | GRID-1-3/F | WALL |  | 1 | 8.605 | 1.35 | 11.6168 |  | 0 | 0 | 0 | 0 | 101.5889 | 50% | 50.7944 | 50.7944 | 0
b | NEAR CLIENT OFFICE |  | GRID-1-3/F | WALL |  | 1 | 13.84 | 1.35 | 18.684
c | DAMAC BUILDING SIDE |  | GRID-22-24/V-A | WALL |  | 1 | 52.806 | 1.35 | 71.2881
d | N-E CORNER (DAMAC-ROAD SIDE) |  | GRID-23-24/T-Z |  |  | 1 | 130.206 | 1.35 | 175.7781 |  | 0 | 0 | 0 | 0 | 175.7781 | 50% | 87.889 | 0 | 87.889
3 | FOURTH FLOOR PLANTER WALL/ECO1A
a | CAMNAL SIDE | WIR: JOT-AX-WR-GF-00133 | GRID-3-9/B-C |  |  | 1 | 85.382 | 0.8 | 68.3056 | [5 empty] | 683.9056 | 85% | 581.3198 | 547.1245 | 34.1953
b | CAMNAL SIDE | WIR: JOT-AX-WR-GF-00133 | GRID-3-9/D |  |  | 1 | 684 | 0.9 | 615.6
c | Residential Road |  |  |  |  | 1 | 26.928 | 1.35 | 36.3528 | [5 empty] | 259.9871 | 50% | 129.9936 | 0 | 129.9936
[6 empty] | 1 | 25.42 | 1.35 | 34.317
[6 empty] | 1 | 7.888 | 1.35 | 10.6488
d | Near stair-06 |  |  |  |  | 1 | 16.98 | 1.35 | 22.923
[6 empty] | 1 | 41.501 | 1.35 | 56.0264
[6 empty] | 1 | 1.79 | 0.35 | 0.6265
[6 empty] | 1 | 41.114 | 1.35 | 55.5039
e | Canal side ,Hotel |  |  |  |  | 1 | 12.602 | 1.35 | 17.0127
| Damac side |  | GRID-24/Q-U |  |  | 1 | 19.686 | 1.35 | 26.5761
[14 empty] | TOTAL | 1882.7847 |  | 1382.6645 | 1052.2056 | 330.459
KCE-VOR-05, ITEM 01, 50mm CUTTING OF PARAPET & REINSTATEMENT
NO | BUILDING | DRAWING REF. NO/INSTRUCTION REF./RFI REF. | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 20%-50MM CUTTING OF PARAPET,70%-REINSTATEMENT OF BASECOAT,10%-REINSTATEMENT OF PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | CUTTING OF PARAPET AND REINSTATEMENT | E11-K116-JA-dm-273 | L29 PARAPET |  |  | 1 | 82.218 | 1 | 82.218 |  | 0 | 0 | 0 | 0 | 82.218 | 100% | 82.218 | 82.218 | 0
| JOT-AX-WR-L29-00127,135,160 |  |  |  |  | 1 | 77.782 | 1 | 77.782 |  | 0 | 0 | 0 | 0 | 77.782 | 100% | 77.782 | 77.782 | 0
[14 empty] | TOTAL | 160 |  | 160 | 160 | 0
KCE-VOR-05, ITEM 04,400MM FLUTED EIFS
NO | BUILDING | DRAWING REF. NO/INSTRUCTION REF./RFI REF. | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 35%-BUILT UP,35%-INSULATION,20%-BASECOAT,10%-PAINTING | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | ROAD SIDE,FLUTED EIFS | JOT-AX-SD-ML-00006_03 | L29 ,GRID-X-W/16-19 |  |  | 1 | 16.9 | 4 | 67.6 |  | 0 | 0 | 0 | 0 | 67.6 | 100% | 67.6 | 47.32 | 20.28
JOT-AX-WR-L29-145,154,181,170
[14 empty] | TOTAL | 67.6 |  | 67.6 | 47.32 | 20.28
KCE-VOR-03-100MM EIFS ON STAIRWALL
NO | BUILDING | DRAWING REF. NO/INSTRUCTION REF./RFI REF. | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 70%-INSULATION,20%-BASECOAT,10%-PAINTING | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | L 23 HOTEL ENTRANCE ,STAIRWALL | E11-K116-MS-dm-135 ,lvl-23 | L23 |  |  | 1 | 5 | 2 | 10 |  | 0 | 0 | 0 | 0 | 10 | 90% | 9 | 9 | 0
JOT-AX-WR-L23-00130,159
[14 empty] | TOTAL | 10 |  | 9 | 9 | 0
KCE-VOR-08-ITEM-1 | [17 empty] | MONTH: | December 2022
NO | BUILDING | DRAWING REF. NO/INSTRUCTION REF./RFI REF. | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 70%-INSULATION,20%-BASECOAT,10%-PAINTING | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | Additional 200mm | E11-K116-JA-dm-607 ,lvl-30 | U/20-22,L30 |  |  | 1 | 9.191 | 1.4 | 12.8674 |  | 0 | 0 | 0 | 0 | 12.8674 | 100% | 12.8674 | 0 | 12.8674
WIR-165,171,182
[14 empty] | TOTAL | 12.8674 |  | 12.8674 | 0 | 12.8674
KCE-VOR-08-ITEM-2 | [17 empty] | MONTH: | December 2022
NO | BUILDING | DRAWING REF. NO/INSTRUCTION REF./RFI REF. | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 70%-INSULATION,20%-BASECOAT,10%-PAINTING | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | Additional 75mm EIFS | E11-K116-JA-dm-607 ,lvl-30 | U-X/22,L30 |  |  | 1 | 7.984 | 1.4 | 11.1776 |  | 0 | 0 | 0 | 0 | 28.313 | 100% | 28.313 | 0 | 28.313
| WIR-162,171,182 |  |  |  |  | 1 | 85.677 | 0.2 | 17.1354
[14 empty] | TOTAL | 28.313 |  | 28.313 | 0 | 28.313
KCE-VOR-08-ITEM-4(300MM BUILT-UP+200MM EIFS) | [17 empty] | MONTH: | December 2022
NO | BUILDING | DRAWING REF. NO/INSTRUCTION REF./RFI REF. | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 70%-INSULATION,20%-BASECOAT,10%-PAINTING | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | 500mm thick(300mm built-upo+200mm EIFS) | E11-K116-JA-dm-607 ,lvl-29 | 17-19/X,L29 |  |  | 1 | 16.7 | 0.926 | 15.4642 |  | 0 | 0 | 0 | 0 | 15.4642 | 100% | 15.4642 | 0 | 15.4642
WIR-174,175,176,183
[14 empty] | TOTAL | 15.4642 |  | 15.4642 | 0 | 15.4642
KCE-VOR-08-ITEM-5(100MM BUILT-UP+RENDERING+TRUSTONE PAINT | [17 empty] | MONTH: | December 2022
NO | BUILDING | DRAWING REF. NO/INSTRUCTION REF./RFI REF. | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 70%-INSULATION,20%-BASECOAT,10%-PAINTING | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | 100MM BUILT-UP+RENDERING+TRUSTONE FINISH | E11-K116-JA-dm-607 ,lvl-29 | L29 |  |  | 1 | 17.336 | 0.7 | 12.1352 |  | 0 | 0 | 0 | 0 | 12.1352 | 100% | 12.1352 | 0 | 12.1352
WIR-174,178,182
[14 empty] | TOTAL | 12.1352 |  | 12.1352 | 0 | 12.1352
KCE-VOR-07-ITEM-2 | [17 empty] | MONTH: | December 2022
NO | BUILDING | DRAWING REF. NO/INSTRUCTION REF./RFI REF. | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 70%-INSULATION,20%-BASECOAT,10%-PAINTING | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | 75MM EIFS at L31 residential |  | 5-4/F-D,L31 |  |  | 1 | 11.4 | 6.1 | 69.54 |  | 0 | 0 | 0 | 0 | 69.54 | 70% | 48.678 | 0 | 48.678
JOT-AX-SD-L31-00153
[14 empty] | TOTAL | 69.54 |  | 48.678 | 0 | 48.678
Note on R115: Himal Kosala: What is the WIR for this
Note on C124: Himal Kosala: No WIR for below
Note on R125: Himal Kosala: What is the WIR for this
Note on R129: Himal Kosala: What is the WIR for this
Note on R132: Himal Kosala: WIR ?
Note on R135: Himal Kosala: What is the WIR for this
Note on B153: Himal Kosala: This Lump-sum is now 100% complete

## EIFS 400mm EPS BOARDS (hidden)
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS 400mm EPS BOARDS | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  | (Sqm)
1 | ELEVATION 01 (BASEMENT RAMP SIDE) | JOT-AX-SD-GF-00001_00_E | D-G/Y1 | WALL-GF |  | 1 | 11.32 | 4.6 | 52.072 | DOOR | 2 | 1.2 | 1.78 | 4.272 | 47.8 | 47.8 | 0
JOT-AX-WR-GF-00003
2 | ELEVATION 01 (BASEMENT RAMP SIDE) | JOT-AX-SD-ML-00003_00_E | D-G/Y1 | WALL-L2L3 |  | 1 | 11.32 | 7.4 | 83.768 |  | 0 | 0 | 0 | 0 | 83.768 | 83.768 | 0
JOT-AX-WR-ML-00007
[14 empty] | TOTAL | 131.568 | 131.568 | 0

## EIFS 400mm BASECOAT (hidden)
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS 400mm BASECOAT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  | (Sqm)
1 | ELEVATION 01 (BASEMENT RAMP SIDE) | JOT-AX-SD-GF-00001_00_E | D-G/Y1 | WALL-GF |  | 1 | 11.32 | 4.6 | 52.072 | DOOR | 2 | 1.2 | 1.78 | 4.272 | 47.8 | 47.8 | 0
JOT-AX-WR-GF-00006
2 | ELEVATION 01 (BASEMENT RAMP SIDE) | JOT-AX-SD-ML-00003_00_E | D-G/Y1 | WALL-L2L3 |  | 1 | 11.32 | 7.4 | 83.768 |  | 0 | 0 | 0 | 0 | 83.768 | 83.768 | 0
JOT-AX-WR-L4-00011
[14 empty] | TOTAL | 131.568 | 131.568 | 0

## EIFS 400mm PAINT (hidden)
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS 400mm PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  | (Sqm)
1 | RAMPSIDE | JOT-AX-SD-ML-00003_00_E | D-H/Y1 | L2-WALL | PA9 | 1 | 11.61 | 6.36 | 73.8396 |  | 0 | 0 | 0 | 0 | 73.8396 | 73.8396 | 0
JOT-AX-WR-ML-00054
[14 empty] | TOTAL | 73.8396 | 73.8396 | 0

## EIFS 300mm EPS BOARDS (hidden)
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PROGRESS % | WORK DONE TO DATE | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS 300mm EPS BOARDS | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
4 | ELEVATION 06 ( LIFT AREA) | JOT-AX-SD-ML-00003_00_E | G-H/3-7 | WALL-L2L3 |  | 1 | 27.3 | 7.6 | 207.48 | LIFT LOBBY OPENING L2,L3 | 2 | 3.18 | 2.4 | 15.264 | 192.216 | 100% | 192.216 | 192.216 | 0
| CORE WALL AREA | JOT-AX-WR-ML-00014
[14 empty] | TOTAL | 192.216 |  | 192.216 | 192.216 | 0

## EIFS 300mm BASECOAT (hidden)
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS 300mm BASECOAT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  | (Sqm)
4 | ELEVATION 06 ( LIFT AREA) | JOT-AX-SD-ML-00003_00_E | G-H/3-7 | WALL-L2L3 |  | 1 | 27.3 | 7.6 | 207.48 | LIFT LOBBY OPENING L2,L3 | 2 | 3.18 | 2.4 | 15.264 | 192.216 | 192.216 | 0
CORE WALL AREA
JOT-AX-WR-ML-00016
[14 empty] | TOTAL | 192.216 | 192.216 | 0