## Summary
SN | Description | Total Scope | Balance Scope | Valuation at WFA | Previous | This Month | Cumulative
01 | Contract Works | 1600000 | 0 | 533925 | 101679.6935 | 181891.8379 | 283571.5314 | 817496.5314
02 | Variations (old) | 485255 | 472082 | 13173 | 60130.8072 | 139.9603 | 60270.7675 | 73443.7675
| Total Value of Work Done |  | 472082 | 547098 | 161810.5008 | 182031.7982 | 343842.299 | 890940.299
03 | New Variations | 742594.6925 | 742594.6925 | 0 | 237796.8754 | 152479.6075 | 390276.4829
| Total Value of Work Done |  | 1214676.6925 | 547098 | 399607.3761 | 334511.4057 | 734118.7819 |  | 1281216.7819
04 | Advance Payment |  | 10% |  | 153815.69 | 0 | 153815.69
05 | Advance Payment Recovery |  | 10% |  | -39960.7376 | -33451.1406 | -73411.8782
| TOTAL |  |  |  | 513462.3285 | 301060.2652 | 814522.5937

## Progress Bill
PROGRESS BOQ
Item | Description | Qty. | Unit | Rate | Amount | OCI - Certified |  | Balance Works |  |  | Pervious Work Certified |  |  | Balance Works |  |  | This Month Workdone |  |  | Cumulative |  |  | Balance Works
|  |  |  | Rate | Amount | Progress % | Amount | Progress % | Qty | Amount | Pervious % | Pervious Qty | Amount | Progress % | Qty | Amount | Progress % | Qty | Amount | Progress % | Qty | Amount | Progress % | Qty | Amount
DESIGN AND BUILD OF TERRACO SYSTEM
[8 empty] | 100% | [5 empty] | 100% | [8 empty] | 100%
EIFS WITH TERRACO RENDER SYSTEM
EIFS with TERRACO System, mineral wool, Adhesive, groove requirement,including all necessary framing, fitting, fixing, backing framing support, decoration, Primer, Basecoat and Final coat etc and the like all in accordance with drawings and specifications.
ON BLOCKWORK / CONCRETE WALL
A | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 75mm | 876 | m2 | 295 | 258420 |  |  | 100% | 876 | 258420 |  | 0 | 0 | 100% | 876 | 258420 | 4.65% | 40.7312 | 12015.7187 | 4.65% | 40.7312 | 12015.7187 | 95.35% | 835.2687 | 246404.2812
B | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 100mm | 692 | m2 | 319 | 220748 | 89.8% | 198241.4271 | 10.2% | 70.5535 | 22506.5729 | 89.43% | 618.8872 | 197425.0167 | 10.57% | 73.1128 | 23322.9833 | 0% | 0 | 0 | 89.43% | 618.8872 | 197425.0167 | 10.57% | 73.1128 | 23322.9833
C | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 150mm | 266 | m2 | 347 | 92302 |  |  | 100% | 266 | 92302 |  | 0 | 0 | 100% | 266 | 92302 | 0% | 0 | 0 |  | 0 | 0 | 100% | 266 | 92302
D | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 200mm | 682 | m2 | 380 | 259160 | 95.74% | 248117.6104 | 4.261% | 29.0589 | 11042.3896 | 99.13% | 676.0951 | 256916.1456 | 0.8658% | 5.9049 | 2243.8544 | 0% | 0 | 0 | 99.13% | 676.0951 | 256916.1456 | 0.8658% | 5.9049 | 2243.8544
E | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 275mm | 176 | m2 | 415 | 73040 |  |  | 100% | 176 | 73040 |  | 0 | 0 | 100% | 176 | 73040 | 0% | 0 | 0 |  | 0 | 0 | 100% | 176 | 73040
F | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 300mm | 854 | m2 | 435 | 371490 | 20.26% | 75252.564 | 79.74% | 681.0056 | 296237.436 | 33.99% | 290.3156 | 126287.2825 | 66.01% | 563.6844 | 245202.7175 | 0% | 0 | 0 | 33.99% | 290.3156 | 126287.2825 | 66.01% | 563.6844 | 245202.7175
G | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 400mm | 422 | m2 | 500 | 211000 | 31.07% | 65567.88 | 68.93% | 290.8642 | 145432.12 | 32% | 135.04 | 67520 | 68% | 286.96 | 143480 | 0% | 0 | 0 | 32% | 135.04 | 67520 | 68% | 286.96 | 143480
STAND ALONE EIFS SYSTEM WITH NECESSARY BACK FRAMING SUPPORT
H | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 75mm | 88 | m2 | 400 | 35200 |  |  | 100% | 88 | 35200 |  | 0 | 0 | 100% | 88 | 35200 | 0% | 0 | 0 |  | 0 | 0 | 100% | 88 | 35200
J | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 300mm | 86 | m2 | 450 | 38700 |  |  | 100% | 86 | 38700 | 76.59% | 65.87 | 29641.5 | 23.41% | 20.13 | 9058.5 | 13.41% | 11.53 | 5188.5 | 90% | 77.4 | 34830 | 10% | 8.6 | 3870
K | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 400mm | 24 | m2 | 525 | 12600 |  |  | 100% | 24 | 12600 | 87.85% | 21.083 | 11068.5488 | 12.15% | 2.917 | 1531.4512 | 2.154% | 0.51705 | 271.4512 | 90% | 21.6 | 11340 | 10% | 2.4 | 1260
TERRACO RENDER SYSTEM
TERRACO Render System, Adhesive, groove requirement, including all necessary framing, fitting, fixing, backing framing support, Primer, Basecoat and Final coat decoration, etc and the like all in accordance with drawings and specifications.
ON BLOCKWORK / CONCRETE WALL
A | TERRACO RENDER System (TERRACO acid wash finishes) | 1298 | m2 | 175 | 227150 | 5.909% | 13423.2 | 94.09% | 1221.296 | 213726.8 | 5.909% | 76.704 | 13423.2 | 94.09% | 1221.296 | 213726.8 | 72.38% | 939.521 | 164416.1679 | 78.29% | 1016.225 | 177839.3679 | 21.71% | 281.775 | 49310.6321
| Discount |  |  |  | -199810 | 33.37% | -66677.2725 | 66.63% | 0 | -133132.7275 | 33.37% | 0 | -66677 | 66.63% | 0 | -133133.403 | 0% | 0 | 0 | 33.37% | 0 | -66677 | 66.63% | 0 | -133133
| TOTAL |  |  |  | 1600000 |  | 0 |  |  | 0 |  |  | 635604.6935 |  |  | 0 |  |  | 181891.8379 |  | 51.09% | 817496.5314 |  |  | 0

## VARIATIONS
DORCHESTER HOTEL & RESIDENCIES | [15 empty] | KCE PC 10
JOYZ OVERSEAS - VARIATION SCHEDULE | [15 empty] | 2022-11-01
SN | Variations | Total Work Scope |  |  | Progress as per WFA |  |  | Remaining Work |  | Previous |  | This Month | This Month | Cumulative |  |  | Balance Work
|  | QTY | Rate | Amount | % | QTY | Amount | QTY | Amount | QTY | Amount | QTY | Amount | % | QTY | Amount | % | QTY | Amount
01 | Additional EFIS to parapets at L4, L29 | 256.9673 | 319 | 81973 | 13.7% | 35.21 | 11232 | 221.7573 | 70741 | 212.4213 | 67762.3819 | 0 | 0 | 86.99% | 212.4213 | 67762.3819 | 17.34% | 44.5461 | 14210.1941
02 | Additional EFIS to non-accessible balconies | 766.0026 | 380 | 291081 | 0% |  | 0 | 766.0026 | 291081 |  | 0 |  | 0 |  |  | 0 | 100% | 766.0026 | 291081
03 | PVC grooved to EFIS system | 823.01 | 32.16 | 26468 | 7.333% | 60.3545 | 1941 | 762.6555 | 24527 | 172.308 | 5541.4253 | 4.352 | 139.9603 | 21.47% | 176.66 | 5681.3856 | 78.53% | 646.35 | 20786.6144
04 | Additional EFIS to entrance at L2 | 169.4702 | 319 | 54061 | 0% |  | 0 | 169.4702 | 54061 |  | 0 |  | 0 |  |  | 0 | 100% | 169.4702 | 54061
05 | Additional EFIS to parapets at L2 | 99.2853 | 319 | 31672 | 0% |  | 0 | 99.2853 | 31672 |  | 0 |  | 0 |  |  | 0 | 100% | 99.2853 | 31672
Sub-Totals |  |  |  | 485255 | 2.715% |  | 13173 |  | 472082 |  | 73303.8072 |  | 139.9603 | 15.14% |  | 73443.7675 | 84.86% |  | 411810.8085
NEW VARIATIONS
Additions
06 | EIFS WITH BUILTUP 300mm | 854 | 450 | 384300 | [5 empty] | 209.7173 | 94372.7645 | 130.6264 | 58781.8861 | 39.85% | 340.3437 | 153154.6506 | 60.15% | 513.6563 | 231145.3494
07 | EIFS WITH BUILTUP 400mm | 422 | 525 | 221550 | [5 empty] | 225.0935 | 118174.1109 | 172.7588 | 90698.3935 | 94.28% | 397.8524 | 208872.5044
08 | EIFS WITH BUILTUP 275mm |  |  | 73040
09 | EIFS Removal | 1 | 25250 | 25250 | [5 empty] | 1 | 25250 | 0 | 0 | 100% | 1 | 25250
10 | Cutting of existing 100mm thick EIFS and reinstatement of EIFS system after the cutting at L 29 parapet | 1 | 34345 | 34345 | [7 empty] | 0.2 | 6869 | 20% | 0.2 | 6869
11 | RENDER ON PLANTER WALL | 1799.35 | 175 | 314886.25 | [7 empty] | 141.1501 | 24701.2762 | 7.845% | 141.1501 | 24701.2762
12 | RENDER ON PARAPET COPING AND INTERNAL FACE | 638 | 175 | 111650 | [7 empty] | 0 | 0 | 0% |  | 0
13 | 50mm EIFS BUILD UP ON TOP OF THE LEVEL-2 PARAPET WALL | 11.75 | 270 | 3172.5 | [7 empty] | 0 | 0 | 0% |  | 0
14 | 100MM EIFS AT LEVEL-1 AV ROOMS EXTERNAL | 25.8075 | 319 | 8232.5925 | [7 empty] | 18.0652 | 5762.8147 | 70% | 18.0652 | 5762.8147
15 | 75 MM EIFS AT BASEMENT-1 EXTERNAL SEATING AREA | 47.92 | 295 | 14136.4 | [7 empty] | 33.5431 | 9895.2219 | 70% | 33.5431 | 9895.2219
16 | RENDER ON BASEMENT -1 TO LEVEL-O1A | 176.05 | 175 | 30808.75 | [7 empty] | 158.4398 | 27726.9576 | 90% | 158.4398 | 27726.9576
17 | RENDER AT LEVEL-1 AV ROOMS EXTERNAL | 47.2 | 175 | 8260 | [7 empty] | 0 | 0 | 0% | 0 | 0
18 | Removal & reinstatement of 200m thick with 400mm thick EIFS and framing as per the response to KCE-AX-RFI-GF-00254 dt 22.10.22 & & Joyz variation submission ref JOT-KCE-VOR-00007 dated 17.11.22. | 33.44 | 380 | 12707.2 | [9 empty] | 75% | 25.08 | 9530.4
Omission
19 | EIFS WITH BUILTUP 300mm | 1 | -140270 | -140270 | [7 empty] | 0 | -13975.4117 | 9.963% |  | -13975.4117
20 | EIFS WITH BUILTUP 400mm | 1 | -286434 | -286434 | [7 empty] | 0 | -67510.9309 | 23.57% |  | -67510.9309
21 | EIFS WITH BUILTUP 275mm | 1 | -73040 | -73040 | [7 empty] | 0 | 0 | 0% |  | 0
Sub-Totals |  |  |  | 742594.6925 | [6 empty] | 237796.8754 |  | 152479.6075 | 52.56% |  | 390276.4829 | 31.13% |  | 231145.3494
| Installation of stud frame + 200mm EIFS system to replace 400mm EIFS system | 422 | 525 | 221550
| Installation of stud frame + 200mm EIFS system to replace 300mm EIFS system | 854 | 450 | 384300
| Installation of stud frame + 200mm EIFS system to replace 275mm EIFS system | 176 | 415 | 73040
| Break up existing 400/300mm EIFS system | 1 | 12819 | 12819
Cutting of existing 100mm thick EIFS and reinstatement of EIFS system after the cutting at L 29 parapet

## VO 04
DETAILED STATUS REPORT
Client Name |  | : | Omniyat Investments & Management LLC
Project Name |  | : | Dorchester Hotel (PLOT 18)
Main Contractor |  | : | Khansaheb civil engineering llc
Scope of works |  | : | External Insulation Finishing System (EPS)
KCE-VOR-04, ITEMS-04, 100MM EIFS FOR LEVEL 01 | [17 empty] | MONTH: | November 2022
NO | BUILDING | DRAWING REF. NO/INSTRUCTION REF./RFI REF. | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 70%-EPS BOARDS,20%-BASECOAT,10%-PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | 100MM EIFS AT LEVEL-1,AV ROOMS EXTERNAL | E11/K116/SN/dm/281, KCE-AX-RFI-L1-00232 | 25/T-U | WALL-LVL-1 AV ROOMS |  | 1 | 9.3 | 2.775 | 25.8075 |  | 0 | 0 | 0 | 0 | 25.8075 | 70% | 18.0652 | 0 | 18.0652
JOT-AX-WR-L1-122_00
[14 empty] | TOTAL | 25.8075 |  | 18.0652 | 0 | 18.0652
EIFS -STAND ALONE(400MM) | [17 empty] | MONTH: | November 2022
NO | BUILDING | DRAWING REF. NO/INSTRUCTION REF./RFI REF. | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 70%-EPS BOARDS,20%-BASECOAT,10%-PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | 75MM EIFS AT B-1, EXTERNAL SEATING AREA | E11/K116/SN/dm/281, KCE-AX-RFI-L1-00232 | EXTERNAL SEATING AREA | WALL-B-1 EXTERNAL |  | 1 | 10.25 | 4.675 | 47.9187 |  | 0 | 0 | 0 | 0 | 47.9187 | 70% | 33.5431 | 0 | 33.5431
JOT-AX-WR-B1-123_00
[14 empty] | TOTAL | 47.9187 |  | 33.5431 | 0 | 33.5431
KCE-VOR-04, ITEM 06, PLASTER ON WALL SEATING AREA @BASEMENT | [17 empty] | MONTH: | November 2022
NO | BUILDING | DRAWING REF. NO/INSTRUCTION REF./RFI REF. | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 90%-20MM PLASTERING,10%-PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | 20mm PLASTER AT B-1, EXTERNAL SEATING AREA | E11/K116/SN//, KCE-AX-RFI-B1-00186 | EXTERNAL SEATING AREA | WALL-B-1 EXTERNAL |  | 1 | 11.285 | 4.675 | 52.7574 |  | 0 | 0 | 0 | 0 | 52.7574 | 90% | 158.4398 | 0 | 158.4398
| JOT-AX-WR-B1-00124_00 |  | ABOVE GF |  |  | 1 | 31.612 | 3.9 | 123.2868 |  | 0 | 0 | 0 | 0 | 123.2868
[14 empty] | TOTAL | 176.0442 |  | 158.4398 | 0 | 158.4398
KCE-VOR-04, ITEM 01, RENDER ON PLANTER WALLS AREA @ | [17 empty] | MONTH: | November 2022
NO | BUILDING | DRAWING REF. NO/INSTRUCTION REF./RFI REF. | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 90%-20MM PLASTERING,10%-PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | Ground floor Planter wall EIFS render plaster | FE-LX-SD-GL-00006_00 | GF Planter wall |  |  | 1 | 11.5 | 1.38 | 15.87 |  | 0 | 0 | 0 | 0 | 156.8335 | 90% | 141.1501 | 0 | 141.1501
[6 empty] | 1 | 21.8 | 0.9 | 19.62
[6 empty] | 1 | 29.25 | 0.9 | 26.325
[6 empty] | 1 | 14.2 | 1.115 | 15.833
[6 empty] | 1 | 27.75 | 1.45 | 40.2375
[6 empty] | 1 | 29.96 | 1.3 | 38.948
[14 empty] | TOTAL | 156.8335 |  | 141.1501 | 0 | 141.1501

## PERCENTAGE SUMMARY
REQUEST FOR PAYMENT APPLICATION
SUMMARY REPORT
Main Contractor : Roberts-Pizzarotti JV
Scope of works : External Insulation and Finishing Systems (EPS)
Site : Dorchester Hotel (Plot 18)
S.No. |  | ITEM OF WORKS | UNIT | RATE | Weightage |  |  | % Completion |  |  |  | Overall progress % | PROGRESS QUANTITY
| BOQ REF. |  |  |  |  | QTY | AMOUNT
|  |  |  | (AED) |  |  |  | PREVIOUS | CURRENT | CUMULATIVE |  |  | PREVIOUS | CURRENT | CUMULATIVE
MAIN WORKS
EIFS WITH TERRACO RENDER SYSTEM
1 | ITEM G | EIFS 400MM | Sqm | 500 |  | 422 | 211000
|  | EPS BOARDS-70% |  |  | 70% |  |  | 31.18% | 0% | 31.18% | 21.82% | 29.81% | 131.568 | 0 | 131.568 | 32% | 2.191%
|  | BASEOCAT-20% |  |  | 20% |  |  | 31.18% | 0% | 31.18% | 6.235% |  | 131.568 | 0 | 131.568
|  | PAINT-10% |  |  | 10% |  |  | 17.5% | 0% | 17.5% | 1.75% |  | 73.8396 | 0 | 73.8396
2 | ITEM F | EIFS 300MM | Sqm | 435 |  | 854 | 371490
|  | EPS BOARDS-70% |  |  | 70% |  |  | 22.51% | 0% | 22.51% | 15.76% | 20.26% | 192.216 | 0 | 192.216 | 33.99% | 13.74%
|  | BASEOCAT-20% |  |  | 20% |  |  | 22.51% | 0% | 22.51% | 4.502% |  | 192.216 | 0 | 192.216
|  | PAINT-10% |  |  | 10% |  |  | 0% | 0% | 0% | 0% |  | 0 | 0 | 0
3 | ITEM D | EIFS 200MM | Sqm | 380 |  | 682 | 259160
|  | EPS BOARDS-70% |  |  | 70% |  |  | 105.4% | 0% | 105.4% | 73.81% | 94.04% | 719.1192 | 0 | 719.1192 | 99.13% | 5.095%
|  | BASEOCAT-20% |  |  | 20% |  |  | 88.57% | 0% | 88.57% | 17.71% |  | 604.0448 | 0 | 604.0448
|  | PAINT-10% |  |  | 10% |  |  | 25.15% | 0% | 25.15% | 2.515% |  | 171.5176 | 0 | 171.5176
4 | ITEM B | EIFS 100MM | Sqm | 319 |  | 692 | 220748
|  | EPS BOARDS-70% |  |  | 70% |  |  | 86.94% | 0% | 86.94% | 60.86% | 81.79% | 601.6058 | 0 | 601.6058 | 89.43% | 7.645%
|  | BASEOCAT-20% |  |  | 20% |  |  | 83.46% | 0% | 83.46% | 16.69% |  | 577.5384 | 0 | 577.5384
|  | PAINT-10% |  |  | 10% |  |  | 42.41% | 0% | 42.41% | 4.241% |  | 293.508 | 0 | 293.508
TERRACO RENDER SYSTEM
5 | ITEM B | EIFS RENDER | Sqm | 175 |  | 1298 | 227150
|  | EPS BOARDS-80% |  |  | 80% |  |  | 7.387% | 0% | 7.387% | 5.909% | 5.909% | 95.88 | 0 | 95.88 | 78.29% | 72.38%
|  | BASEOCAT-20% |  |  | 20% |  |  | 0% | 0% | 0% | 0% |  | 0 | 0 | 0
6 | ITEM J | 300mm Stand Alone | Sqm | 450 | 100% | 86 | 38700 | 0% | 76.59% | 76.59% |  |  | 0 | 65.87 | 65.87
7 | ITEM K | 400mm Stand Alone | Sqm | 525 | 100% | 24 | 12600 | 0% | 87.85% | 87.85% |  |  | 0 | 21.083 | 21.083
VARIATIONS
8 |  | PVC GROOVE | Lm | 32.16 |  | 823.01 | 26468 | 13.19% | 7.743% | 20.94% |  | 20.94% | 108.58 | 63.728 | 172.308 | 21.47% | 0.5288%
9 | ITEM B | EIFS 100MM PARAPET WALL | Sqm | 319 |  | 256.9673 | 81972.576 | [8 empty] | 86.99% | 4.326%
|  | EPS BOARDS | [5 empty] | 67.51% | 15.16% | 82.66% |  | 82.66% | 173.4705 | 38.9508 | 212.4213
10 | KCE-VOR-1_04 | EIFS WITH BUILTUP 300mm | Sqm | 450 |  | 854 | 384300 | 2.829% | 21.73% | 24.56% |  | 24.56% | 24.1586 | 185.5587 | 209.7173 | 39.85% | 15.3%
|  | EIFS WITH BUILTUP 400mm | Sqm | 525 |  | 422 | 384300 | 0% | 26.36% | 26.36% |  | 26.36% | 0 | 225.0935 | 225.0935
TOTAL
13.7%

## EIFS 400mm EPS BOARDS (hidden)
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS 400mm EPS BOARDS | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  | (Sqm)
1 | ELEVATION 01 (BASEMENT RAMP SIDE) | JOT-AX-SD-GF-00001_00_E | D-G/Y1 | WALL-GF |  | 1 | 11.32 | 4.6 | 52.072 | DOOR | 2 | 1.2 | 1.78 | 4.272 | 47.8 | 47.8 | 0
JOT-AX-WR-GF-00003
2 | ELEVATION 01 (BASEMENT RAMP SIDE) | JOT-AX-SD-ML-00003_00_E | D-G/Y1 | WALL-L2L3 |  | 1 | 11.32 | 7.4 | 83.768 |  | 0 | 0 | 0 | 0 | 83.768 | 83.768 | 0
JOT-AX-WR-ML-00007
[14 empty] | TOTAL | 131.568 | 131.568 | 0

## EIFS 400mm BASECOAT (hidden)
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS 400mm BASECOAT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  | (Sqm)
1 | ELEVATION 01 (BASEMENT RAMP SIDE) | JOT-AX-SD-GF-00001_00_E | D-G/Y1 | WALL-GF |  | 1 | 11.32 | 4.6 | 52.072 | DOOR | 2 | 1.2 | 1.78 | 4.272 | 47.8 | 47.8 | 0
JOT-AX-WR-GF-00006
2 | ELEVATION 01 (BASEMENT RAMP SIDE) | JOT-AX-SD-ML-00003_00_E | D-G/Y1 | WALL-L2L3 |  | 1 | 11.32 | 7.4 | 83.768 |  | 0 | 0 | 0 | 0 | 83.768 | 83.768 | 0
JOT-AX-WR-L4-00011
[14 empty] | TOTAL | 131.568 | 131.568 | 0

## EIFS 400mm PAINT (hidden)
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS 400mm PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  | (Sqm)
1 | RAMPSIDE | JOT-AX-SD-ML-00003_00_E | D-H/Y1 | L2-WALL | PA9 | 1 | 11.61 | 6.36 | 73.8396 |  | 0 | 0 | 0 | 0 | 73.8396 | 73.8396 | 0
JOT-AX-WR-ML-00054
[14 empty] | TOTAL | 73.8396 | 73.8396 | 0

## EIFS 300mm EPS BOARDS (hidden)
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PROGRESS % | WORK DONE TO DATE | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS 300mm EPS BOARDS | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
4 | ELEVATION 06 ( LIFT AREA) | JOT-AX-SD-ML-00003_00_E | G-H/3-7 | WALL-L2L3 |  | 1 | 27.3 | 7.6 | 207.48 | LIFT LOBBY OPENING L2,L3 | 2 | 3.18 | 2.4 | 15.264 | 192.216 | 100% | 192.216 | 192.216 | 0
| CORE WALL AREA | JOT-AX-WR-ML-00014
[14 empty] | TOTAL | 192.216 |  | 192.216 | 192.216 | 0

## EIFS 300mm BASECOAT (hidden)
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS 300mm BASECOAT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  | (Sqm)
4 | ELEVATION 06 ( LIFT AREA) | JOT-AX-SD-ML-00003_00_E | G-H/3-7 | WALL-L2L3 |  | 1 | 27.3 | 7.6 | 207.48 | LIFT LOBBY OPENING L2,L3 | 2 | 3.18 | 2.4 | 15.264 | 192.216 | 192.216 | 0
CORE WALL AREA
JOT-AX-WR-ML-00016
[14 empty] | TOTAL | 192.216 | 192.216 | 0

## EIFS 200mm EPS BOARDS
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PROGRESS % | WORK DONE TO DATE | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS 200mm EPS BOARDS | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | ELEVATION 01-03 (BOH-ETS ROOMS) | JOT-AX-SD-GF-00001_00_E | D-I/Y1-Y3 | WALL-GF |  | 1 | 38.37 | 4.6 | 176.502 | DOOR | 1 | 1.4 | 2 | 2.8 | 157.9976 |  | 157.9976 | 157.9976 | 0
| JOT-AX-WR-GF-00003 | [8 empty] | DOOR | 1 | 1.1 | 2 | 2.2
| JOT-AX-WR-GF-00002 | [8 empty] | WINDOW | 1 | 0.76 | 1.19 | 0.9044
| JOT-AX-WR-GF-000015 | [8 empty] | DOOR | 2 | 2.1 | 3 | 12.6
2 | ELEVATION 01-03 (BOH-ETS ROOMS) | JOT-AX-SD-ML-00003_00_E | D-I/Y1-Y3 | WALL-L2L3 |  | 1 | 38.37 | 7.4 | 283.938 | DOOR | 1 | 1.2 | 1.73 | 2.076 | 281.862 |  | 281.862 | 281.862 | 0
JOT-AX-WR-ML-00007
3 | (HOUSEKEEPING LOBBY) | JOT-AX-SD-GF-00001_00_E | D-F/7-8 | WALL GF |  | 1 | 4 | 3.82 | 15.28 | DOOR | 1 | 1.2 | 2 | 2.4 | 17.263 |  | 17.263 | 17.263 | 0
| JOT-AX-WR-GF-00017 |  |  |  |  | 1 | 0.9 | 4.87 | 4.383
4 | (HOUSEKEEPING LOBBY) | JOT-AX-SD-GF-00001 | E-F/6-7 | WALL GF |  | 1 | 11.53 | 4.22 | 48.6566 | Door | 1 | 1.2 | 1.7 | 2.04 | 44.0566 |  | 44.0566 | 44.0566 | 0
| JOT-AX-WR-GF-00024 | [9 empty] | 2 | 0.8 | 1.6 | 2.56
5 | STAIR 6 WALL | JOT-AX-SD-L4-00005_02 | E-H/10-12 | WALL L4 |  | 1 | 21.97 | 9.92 | 217.94 |  | 0 | 0 | 0 | 0 | 217.94 |  | 217.94 | 217.94 | 0
JOT-AX-WR-L4-00056
[14 empty] | TOTAL | 719.1192 |  | 719.1192 | 719.1192 | 0

## EIFS 200mm BASECOAT
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PROGRESS % | WORK DONE TO DATE | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS 200mm BASECOAT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | ELEVATION 01-03 (BOH-ETS ROOMS) | JOT-AX-SD-GF-00001_00_E | D-I/Y1-Y3 | WALL-GF |  | 1 | 38.37 | 4.6 | 176.502 | DOOR | 1 | 1.4 | 2 | 2.8 | 157.9976 |  | 157.9976 | 157.9976 | 0
| JOT-AX-WR-GF-00006 | [8 empty] | DOOR | 1 | 1.1 | 2 | 2.2
| JOT-AX-WR-GF-00019 | [8 empty] | WINDOW | 1 | 0.76 | 1.19 | 0.9044
[10 empty] | DOOR | 2 | 2.1 | 3 | 12.6
2 | ELEVATION 01-03 (BOH-ETS ROOMS) | JOT-AX-SD-ML-00003_00_E | D-I/Y1-Y3 | WALL-L2L3 |  | 1 | 38.37 | 7.4 | 283.938 | DOOR | 1 | 1.2 | 1.73 | 2.076 | 281.862 |  | 281.862 | 281.862 | 0
JOT-AX-WR-L4-00011
3 | (HOUSEKEEPING LOBBY) | JOT-AX-SD-GF-00001_00_E | D-F/7-8 | WALL GF |  | 1 | 4 | 3.82 | 15.28 | DOOR | 1 | 1.2 | 2 | 2.4 | 17.263 |  | 17.263 | 17.263 | 0
[6 empty] | 1 | 0.9 | 4.87 | 4.383
4 | (HOUSEKEEPING LOBBY) | JOT-AX-SD-GF-00001 | E-F/6-7 | WALL GF |  | 1 | 11.53 | 4.22 | 48.6566 | Door | 1 | 1.2 | 1.7 | 2.04 | 44.0566 |  | 44.0566 | 44.0566 | 0
| JOT-AX-WR-GF-00024 | [9 empty] | 2 | 0.8 | 1.6 | 2.56
5 | STAIR 6 WALL,Elevation-10 | JOT-AX-SD-L4-00005_02 | E-H/10-12 | WALL L4 |  | 2 | 8.1895 | 9.92 | 81.24 | [5 empty] | 81.24 |  | 81.24 | 81.24 | 0
JOT-AX-WR-L4-00071
6 | LEVEL-4 to 5,STAIR 6 WALL,Elevation-08 | JOT-AX-SD-L4-00005_02 | E-H/10-12 | WALL L4,Basecoat |  | 1 | 9.1 | 9.92 | 90.272 |  | 0 | 0 | 0 | 0 | 90.272 | 20% | 18.0544 | 18.0544 | 0
JOT-AX-WR-L4-00070_01
7 | LEVEL-4 to 5,STAIR 6 WALL,Elevation-07 | JOT-AX-SD-L4-00005_02 | E-H/10-12 | WALL L4,Basecoat |  | 1 | 1.8 | 9.92 | 17.856 |  | 0 | 0 | 0 | 0 | 17.856 | 20% | 3.5712 | 3.5712 | 0
JOT-AX-WR-L4-00070_01
[14 empty] | TOTAL | 690.5472 |  | 604.0448 | 604.0448 | 0

## EIFS 200mm PAINT
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS 200mm PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  | (Sqm)
1 | RAMPSIDE | JOT-AX-WR-ML-00003_00_E | D-H/Y1 | L2 WALL | PA9 | 1 | 4.36 | 6.36 | 27.7296 | [5 empty] | 27.7296 | 27.7296 | 0
| JOT-AX-WR-ML-00054 |  |  |  |  | 1 | 3.55 | 6.36 | 22.578 | [5 empty] | 22.578 | 22.578 | 0
2 | Gate 2 Front | JOT-AX-WR-ML-00003_01_E | Y1-Y3/G-H | L2 WALL | PA11 | 1 | 19.06 | 6.36 | 121.21 | [5 empty] | 121.21 | 121.21 | 0
[14 empty] | TOTAL | 171.5176 | 171.5176 | 0

## EIFS 100mm EPS BOARDS
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS 100mm EPS BOARDS | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | L29, PARAPET | RP-LX-SD-L29-1856 | S-T/16-18 | WALL L29 |  | 1 | 9 | 1.4 | 12.6 |  | 0 | 0 | 0 | 0 | 12.6 |  | 12.6 | 12.6 | 0
OT-AX-WR-GF-00005
4 | ELEVATION 06 ( LIFT AREA) | JOT-AX-SD-ML-00003_00_E | G-H/3-7 | WALL-L2L3 |  | 1 | 2.9 | 7.6 | 22.04 | LIFT LOBBY OPENING L2,L3 | 0 | 0 | 0 | 0 | 22.04 |  | 22.04 | 22.04 | 0
CORE WALL AREA
JOT-AX-WR-ML-00014
3 | (HOUSEKEEPING LOBBY) | JOT-AX-SD-GF-00001_00_E | D-F/7-8 | WALL GF |  | 1 | 4 | 3.82 | 15.28 |  | 0 | 0 | 0 | 0 | 15.28 |  | 15.28 | 15.28 | 0
| JOT-AX-WR-GF-00017 |  |  |  |  | 1 | 1.7 | 4.87 | 8.279 |  | 0 | 0 | 0 | 0 | 8.279 |  | 8.279 | 8.279 | 0
4 | L29 Parapet | JOT-AX-SD-GF-00006_01 | S-W/13-14 | WALL 29 |  | 1 | 16.5 | 1.4 | 23.1 |  | 0 | 0 | 0 | 0 | 23.1 |  | 23.1 | 23.1 | 0
JOT-AX-WR-L29-00020
5 | L29 Parapet | JOT-AX-SD-GF-00006_01 | S-T/18-24 | WALL 29 | BO14 | 1 | 45 | 1.4 | 63 | [5 empty] | 63 |  | 63 | 63 | 0
JOT-AX-WR-L29-00030
6 | L4 PARAPET | JOT-AX-SD-GF-00005_02 | B-G/Y1 | WALL 14 | BO15 | 1 | 30.7 | 1.1 | 33.77 | [5 empty] | 33.77 |  | 33.77 | 33.77 | 0
JOT-AX-WR-L4-00031
7 | L29 Parapet | JOT-AX-SD-ML-00006_01 | S-T/14-18 | WALL L29 | BO16 | 1 | 28.31 | 1.4 | 39.634 | [5 empty] | 39.634 |  | 39.634 | 39.634 | 0
JOT-AX-WR-L29-00037
8 | L29 Parapet | JOT-AX-SD-ML-00006_01 | S-X/23-24 | WALL L29 | BO17 | 1 | 24.08 | 1.4 | 33.712 | [5 empty] | 33.712 |  | 33.712 | 33.712 | 0
JOT-AX-WR-L29-00040
9 | L29 Parapet | JOT-AX-SD-ML-00006_01 | W-X/13-18 | WALL L29 | BO18 | 1 | 7.5 | 1.4 | 10.5 | [5 empty] | 10.5 |  | 10.5 | 10.5 | 0
| JOT-AX-WR-L29-00043 |  |  |  |  | 1 | 4.07 | 1.6 | 6.512 | [5 empty] | 6.512 |  | 6.512 | 6.512 | 0
[6 empty] | 1 | 21.58 | 1.65 | 35.607 | [5 empty] | 35.607 |  | 35.607 | 35.607 | 0
10 | L4 Parapet | JOT-AX-SD-L4-00005_02 | F-H/Y1-4 | WALL L4 | BO19 | 1 | 49.2 | 1.1 | 54.12 | [5 empty] | 54.12 |  | 54.12 | 54.12 | 0
JOT-AX-WR-L4-00036
11 | L29 Parapet | 2JOT-AX-SD-ML-00006_02 | S-T/13-15 | PARAPET WALL L29 | BO20 | 1 | 6.43 | 1.4 | 9.002 | [5 empty] | 9.002 |  | 9.002 | 9.002 | 0
JOT-AX-WR-L29-00048
12 | L29 Parapet | 2JOT-AX-SD-ML-00006_02 | V-X/13-15 | PARAPET WALL L29 | BO21 | 1 | 9.92 | 1.4 | 13.888 | [5 empty] | 13.888 |  | 13.888 | 13.888 | 0
JOT-AX-WR-L29-00051
13 | GF BALLROOM WALL | 2JOT-AX-SD-GF-00002_02 | A-U/23-25 | WALL GF | BO22 | 1 | 21.23 | 7.28 | 154.5544 | [5 empty] | 154.5544 |  | 154.5544 | 154.5544 | 0
| JOT-AX-WR-L29-00052 |  |  |  |  | 1 | 9.32 | 4.5 | 41.94 | [5 empty] | 41.94 |  | 41.94 | 41.94 | 0
14 | STAIR 6 WALL,Elevation-07, | JOT-AX-SD-ML-00003_01 | G/10-11 | WALL, L2,Insulation |  | 1 | 4.62 | 7.442 | 34.382 |  | 0 | 0 | 0 | 0 | 34.382 | 70% | 24.0674 | 24.0674 | 0
JOT-AX-WR-ML-00074_01
[14 empty] | TOTAL | 611.9204 |  | 601.6058 | 601.6058 | 0

## EIFS 100mm BASECOAT
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS 100mm BASECOAT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  | (Sqm)
3 | L29, PARAPET | RP-LX-SD-L29-1856 | S-T/16-18 | WALL L29 |  | 1 | 9 | 1.4 | 12.6 |  | 0 | 0 | 0 | 0 | 12.6 | 12.6 | 0
JOT-AX-WR-L29-00008
4 | ELEVATION 06 ( LIFT AREA) | JOT-AX-SD-ML-00003_00_E | G-H/3-7 | WALL-L2L3 |  | 1 | 2.9 | 7.6 | 22.04 | LIFT LOBBY OPENING L2,L3 | 0 | 0 | 0 | 0 | 22.04 | 22.04 | 0
CORE WALL AREA
JOT-AX-WR-ML-00016
3 | (HOUSEKEEPING LOBBY) | JOT-AX-SD-GF-00001_00_E | D-F/7-8 | WALL GF |  | 1 | 4 | 3.82 | 15.28 |  | 0 | 0 | 0 | 0 | 15.28 | 15.28 | 0
[6 empty] | 1 | 1.7 | 4.87 | 8.279 |  | 0 | 0 | 0 | 0 | 8.279 | 8.279 | 0
4 | L29 Parapet | JOT-AX-SD-GF-00006_01 | S-W/13-14 | WALL 29 |  | 1 | 16.5 | 1.4 | 23.1 |  | 0 | 0 | 0 | 0 | 23.1 | 23.1 | 0
JOT-AX-WR-L29-00020
5 | L29 Parapet | JOT-AX-SD-GF-00006_01 | S-T/18-24 | WALL 29 | BO14 | 1 | 45 | 1.4 | 63 | [5 empty] | 63 | 63 | 0
JOT-AX-WR-L29-00030
6 | L4 PARAPET | JOT-AX-SD-GF-00005_02 | B-G/Y1 | WALL L4 | BO15 | 1 | 30.7 | 1.1 | 33.77 | [5 empty] | 33.77 | 33.77 | 0
JOT-AX-WR-L4-00033
7 | L29 PARAPET | JOT-AX-SD-ML-00006_01 | S-T/14-18 | WALL L29 | BA16 | 1 | 28.31 | 1.4 | 39.634 | [5 empty] | 39.634 | 39.634 | 0
JOT-AX-WR-L29-00038
8 | L29 PARAPET | JOT-AX-SD-ML-00006_01 | S-X/23-24 | WALL L29 | BA17 | 1 | 24.08 | 1.4 | 33.712 | [5 empty] | 33.712 | 33.712 | 0
JOT-AX-WR-L29-00038
9 | L4 PARAPET | JOT-AX-SD-L4-00005_02 | F-H/Y1-4 | WALL L4 | BA15 | 1 | 49.2 | 1.1 | 54.12 | [5 empty] | 54.12 | 54.12 | 0
JOT-AX-WR-L4-00044
10 | L29 Parapet | 2JOT-AX-SD-ML-00006_01 | W-X/13-18 | WALL L29 | BA18 | 1 | 7.5 | 1.4 | 10.5 | [5 empty] | 10.5 | 10.5 | 0
| JOT-AX-WR-L29-00046 |  |  |  |  | 1 | 4.07 | 1.6 | 6.512 | [5 empty] | 6.512 | 6.512 | 0
[6 empty] | 1 | 21.58 | 1.65 | 35.607 | [5 empty] | 35.607 | 35.607 | 0
11 | L29 Parapet | 2JOT-AX-SD-ML-00006_02 | S-T/13-15 | PARAPET WALL L29 | BA19 | 1 | 6.43 | 1.4 | 9.002 | [5 empty] | 9.002 | 9.002 | 0
JOT-AX-WR-L29-00049
12 | L29 Parapet | 2JOT-AX-SD-ML-00006_02 | V-X/13-14 | PARAPET WALL L29 | BA20 | 1 | 9.92 | 1.4 | 13.888 | [5 empty] | 13.888 | 13.888 | 0
JOT-AX-WR-L29-00053
12 | GF Ballroom Wall | 2JOT-AX-SD-GF-00002_02 | A-U/23-25 | WALL GF | BA21 | 1 | 21.23 | 7.28 | 154.5544 | [5 empty] | 154.5544 | 154.5544 | 0
| JOT-AX-WR-L29-00058 |  |  |  |  | 1 | 9.32 | 4.5 | 41.94 | [5 empty] | 41.94 | 41.94 | 0
[14 empty] | TOTAL | 577.5384 | 577.5384 | 0

## EIFS 100mm PAINT
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  | (Sqm)
1 | L29, PARAPET | RP-LX-SD-L29-1856 | S-T/16-18 |  | PA1 | 1 | 9 | 1.4 | 12.6 |  | 0 | 0 | 0 | 0 | 12.6 | 12.6 | 0
JOT-AX-WR-L29-00013_01
2 | L29 Parapet | JOT-AX-SD-ML-00006_01 | S-W/13-14 | WALL L29 | PA2 | 1 | 16.5 | 1.4 | 23.1 |  | 0 | 0 | 0 | 0 | 23.1 | 23.1 | 0
JOT-AX-WR-L29-00025
3 | L29 Parapet | JOT-AX-SD-ML-00006_01 | S-T/18-24 | WALL L29 | PA3 | 1 | 45 | 1.4 | 63 | [5 empty] | 63 | 63 | 0
JOT-AX-WR-L29-00034
4 | L4 Parapet | JOT-AX-SD-L4-00005_02 | B-G/Y1 | WALL L4 | PA4 | 1 | 30.7 | 1.1 | 33.77 | [5 empty] | 33.77 | 33.77 | 0
JOT-AX-WR-L4-00035
5 | L29 Parapet | JOT-AX-SD-ML-00006_01 | S-T/14-18 | WALL L29 | PA5 | 1 | 28.31 | 1.4 | 39.634 | [5 empty] | 39.634 | 39.634 | 0
JOT-AX-WR-L29-00041
6 | L29 Parapet | 2JOT-AX-SD-ML-00006_02 | S-X/23-24 | WALL L29 | PA6 | 1 | 24.08 | 1.4 | 33.712 | [5 empty] | 33.712 | 33.712 | 0
JOT-AX-WR-L29-00045
7 | L4 Parapet | JOT-AX-SD-L4-00005_02 | F-H/Y1-4 | WALL L4 | PA7 | 1 | 49.2 | 1.1 | 54.12 | [5 empty] | 54.12 | 54.12 | 0
JOT-AX-WR-L4-00047
8 | L29 Parapet | JOT-AX-SD-ML-00006_02 | S-T/13-15 | PARAPET WALL L29 | PA8 | 1 | 6.43 | 1.4 | 9.002 | [5 empty] | 9.002 | 9.002 | 0
JOT-AX-WR-L29-00050
9 | L29 Parapet | JOT-AX-SD-ML-00006_02 | V-X/13-14 | PARAPET WALL L29 | PA10 | 1 | 17.55 | 1.4 | 24.57 | [5 empty] | 24.57 | 24.57 | 0
JOT-AX-WR-L29-00055
[14 empty] | TOTAL | 293.508 | 293.508 | 0

## EIFS RENDER
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  | (Sqm)
1 | L4 ZONE 3, GATE 2 FRONT | JOT-AX-SD-L04-00005_00_E | A-I/Y1-4 |  |  | 1 | 79.9 | 1.2 | 95.88 |  | 0 | 0 | 0 | 0 | 95.88 | 95.88 | 0
AREA
JOT-AX-WR-L4-00009
[14 empty] | TOTAL | 95.88 | 95.88 | 0

## EIFS -STAND ALONE (300MM)
DETAILED STATUS REPORT
Client Name |  | : | Omniyat Investments & Management LLC
Project Name |  | : | Dorchester Hotel (PLOT 18)
Main Contractor |  | : | Khansaheb civil engineering llc
Scope of works |  | : | External Insulation Finishing System (EPS)
EIFS SYSTEM+BUILT UP(300MM) | [17 empty] | MONTH: | October 2022
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 35%-FRAMING,35%-EPS BOARDS,20%-BASECOAT,10%-PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | STAIR 6 WALL,LEVEL-02 to 3 | JOT-AX-SD-ML-00003_02 | E-H/10-11 | WALL L2 |  | 1 | 4 | 7.275 | 29.1 |  | 0 | 0 | 0 | 0 | 29.1 | 90% | 26.19 | 0 | 26.19
JOT-AX-WR-ML-00085,100,108,104,110
2 | Residential,Stair-6,L4-5 | JOT-AX-SD-L4-00005_02 | T-W/13-14 | WALL L4-5 |  | 1 | 4 | 9.92 | 39.68 |  | 0 | 0 | 0 | 0 | 39.68 | 100% | 39.68 | 0 | 39.68
JOT-AX-WR-ML-00076,81,90,98
[14 empty] | TOTAL | 68.78 |  | 65.87 | 0 | 65.87

## EIFS -STAND ALONE (400MM)
DETAILED STATUS REPORT
Client Name |  | : | Omniyat Investments & Management LLC
Project Name |  | : | Dorchester Hotel (PLOT 18)
Main Contractor |  | : | Khansaheb civil engineering llc
Scope of works |  | : | External Insulation Finishing System (EPS)
EIFS SYSTEM+BUILT UP(400MM) | [17 empty] | MONTH: | October 2022
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 35%-FRAMING,35%-EPS BOARDS,20%-BASECOAT,10%-PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | Stair-6,GF to 1 st floor | JOT-AX-SD-GF-00002_02 | Grid-E-H/10-12 | WALL GF |  | 1 | 3.22 | 7.275 | 23.4255 |  | 0 | 0 | 0 | 0 | 23.4255 | 90% | 21.083 | 0 | 21.083
JOT-AX-WR-GF-00086,99
JOT-AX-WR-ML-00110
[14 empty] | TOTAL | 23.4255 |  | 21.083 | 0 | 21.083

## PVC GROOVE
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
PVC Groove | [5 empty] | NO | LENGTH | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | L2 RAMP TO ETS ROOM | JOT-AX-WR-ML-00201_02 | ELEVATION 1 | PVC GROOVE |  | 11 | 3.56 | 39.16 |  | 0 | 0 | 0 | 0 | 60.5 | 100% | 60.5 | 60.5 | 0
| JOT-AX-WR-ML-00054 |  | ELEVATION 2
| JOT-AX-WR-ML-00057 |  | ELEVATION 3
2 | STAIR 6 WALL,Elevation-10 | JOT-AX-SD-L4-00005_02 | E-H/10-12 | WALL L4 |  | 2 | 9.92 | 19.84 | [5 empty] | 19.84 | 100% | 19.84 | 19.84 | 0
JOT-AX-WR-L4-00071
2 | LEVEL-2 PARAPET-BASECOAT | JOT-AX-SD-L4-00004_03 | U-Z/13-15 | PARAPET L2 |  | 6 | 1.4 | 8.4 | [5 empty] | 8.4 | 100% | 8.4 | 8.4 | 0
JOT-AX-WR-L2-00082_00
3 | LEVEL-4,STAIR 6 WALL,Elevation-08 | JOT-AX-SD-L4-00005_02 | E-H/10-12 | WALL L4 |  | 2 | 9.92 | 19.84 | [5 empty] | 19.84 | 100% | 19.84 | 19.84 | 0
JOT-AX-WR-L4-00070_01
4 | GF Ballroom Wall | JOT-AX-SD-GF-00002_02 | A-U/23-25 | WALL GF |  | 4 | 7.28 | 29.12 |  | 0 | 0 | 0 |  | 29.12 | 100% | 29.12 | 0 | 29.12
JOT-AX-WR-ML-00093_00
5 | Residential,stair-6,L2 | JOT-AX-SD-ML-00003_02 | E-H/10-11 | WALL L2 |  | 4 | 7.28 | 29.12 |  | 0 | 0 | 0 |  | 29.12 | 90% | 26.208 | 0 | 26.208
JOT-AX-WR-ML-00110_00
6 | LEVEL-2 PARAPET-BASECOAT | JOT-AX-SD-L4-00004_03 | U-Z/18-22 | WALL L2 |  | 6 | 1.4 | 8.4 |  | 0 | 0 | 0 |  | 8.4 | 100% | 8.4 | 0 | 8.4
JOT-AX-WR-L2-00096_00
[13 empty] | TOTAL | 175.22 |  | 172.308 | 108.58 | 63.728

## EIFS + BUILTUP (300MM)
DETAILED STATUS REPORT
Client Name |  | : | Omniyat Investments & Management LLC
Project Name |  | : | Dorchester Hotel (PLOT 18)
Main Contractor |  | : | Khansaheb civil engineering llc
Scope of works |  | : | External Insulation Finishing System (EPS)
[18 empty] | MONTH: | October 2022
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
EIFS SYSTEM+BUILT UP(300MM)- 35% framing, 35% ESP Boards, 20% Basecoat, 10% Paint | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | STAIR 6 WALL,LEVEL-02 to 3 | JOT-AX-SD-ML-00003_02 | E-H/10-11 | WALL L2 |  | 1 | 9.275 | 7.442 | 69.0246 |  | 0 | 0 | 0 | 0 | 69.0246 | 90% | 62.1221 | 24.1586 | 37.9635
JOT-AX-WR-ML-00085,100,104
2 | Hotel ramp area,Level-1 to lvl-3 | JOT-AX-SD-ML-00004_03 | W/18-22 | WALL L2-3 |  | 0.5 | 26.051 | 2.599 | 33.8533 |  | 0 | 0 | 0 | 0 | 244.8255 | 35% | 85.6889 | 0 | 85.6889
| JOT-AX-WR-ML-00107_00 |  |  |  |  | 1 | 9.975 | 4.014 | 40.0397 |  | 0 | 0 | 0 | 0
[6 empty] | 1 | 7.376 | 26.051 | 192.1522 |  | 1 | 2.795 | 7.592 | 21.2196
3 | Residential area,lvl-2 to lvl-3 | JOT-AX-SD-ML-00003_02 | G/4-7 | WALL L2-3 |  | 1 | 25.135 | 7.037 | 176.875 |  | 0 | 0 | 0 | 0 | 176.875 | 35% | 61.9062 | 0 | 61.9062
JOT-AX-WR-ML-00103_00
[14 empty] | TOTAL | 490.725 |  | 209.7173 | 24.1586 | 185.5587

## EIFS + BUILTUP (400MM)
DETAILED STATUS REPORT
Client Name |  | : | Omniyat Investments & Management LLC
Project Name |  | : | Dorchester Hotel (PLOT 18)
Main Contractor |  | : | Khansaheb civil engineering llc
Scope of works |  | : | External Insulation Finishing System (EPS)
WORK BREAKDOWN : 70% UPTO EPS BOARDS, 20% UPTO BASECOAT, 10% PAINT | [17 empty] | MONTH: | October 2022
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
EIFS SYSTEM+BUILT UP(400MM)- 35% framing, 35% ESP Boards, 20% Basecoat, 10% Paint | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | Stair-6,GF to 1 st floor | JOT-AX-SD-GF-00002_02 | E-H/10-12 | WALL GF-L1 |  | 1 | 8.477 | 7.275 | 61.6702 |  | 0 | 0 | 0 | 0 | 61.6702 | 90% | 55.5032 | 0 | 55.5032
JOT-AX-WR-GF-00086,99, 110
2 | Residential ,road side,GF to 1 st floor | JOT-AX-SD-ML-00001_02 | G-H/3-8 | WALL GF-L1 |  | 1 | 24.817 | 7.275 | 180.5437 |  | 0 | 0 | 0 | 0 | 180.5437 | 60% | 108.3262 | 0 | 108.3262
JOT-AX-WR-ML-00095,106,105
3 | Residential ,Lobby,GF to 1 st floor | JOT-AX-SD-ML-00001_02 | E-F/6-7 | WALL GF-L1 |  | 1 | 6.694 | 7.28 | 48.7323 |  | 1 | 1 | 1.8 | 1.8 | 46.9323 | 35% | 16.4263 | 0 | 16.4263
JOT-AX-WR-ML-00106_00
4 | RESIDENTIAL,RAMP AREA,GF to Level-3 | JOT-AX-SD-ML-00001_02 | G-D/Y1 | WALL GF-L3 |  | 1 | 11.32 | 11.635 | 131.7082 |  | 2 | 1 | 1.8 | 3.6 | 128.1082 | 35% | 44.8379 | 0 | 44.8379
JOT-AX-WR-ML-00111_00
[14 empty] | TOTAL | 417.2544 |  | 225.0935 | 0 | 225.0935

## EIFS - PARAPET
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PROGRESS % | WORK DONE TO DATE | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS BUILDUP FOR L29 PARAPET, EPS BOARD | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | L4, PARAPET | JOT-AX-SD-L4-00005_02 | W-X/13-16 | WALL L4 | BO23 | 1 | 25.15 | 1.4 | 35.21 |  | 0 | 0 | 0 | 0 | 35.21 | 100% | 35.21 | 35.21 | 0
JOT-AX-WR-L4-00036
2 | L4, PARAPET | JOT-AX-SD-L4-00005_02 | X-Q/23-24 | PARAPET L4 |  | 1 | 28.9 | 1.4 | 40.46 |  | 0 | 0 | 0 | 0 | 40.46 | 100% | 40.46 | 40.46 | 0
JOT-AX-WR-L4-00073
3 | L2 PARAPET, ROADSIDE | JOT-AX-SD-L2-00004_03 | U-Z/13-22 | PARAPET L2, INSULATION |  | 1 | 86.03 | 1.4 | 120.44 |  | 0 | 0 | 0 | 0 | 120.4378 | 100% | 120.4378 | 84.3065 | 36.1313
JOT-AX-WR-L2-00078_00
JOT-AX-WR-L2-00084_00
JOT-AX-WR-L2-00078,82,84,92,96,109
4 | L2 PARAPET, ROADSIDE | JOT-AX-SD-L2-00004_03 | U-Z/13-22 | PARAPET L2, BASE COAT |  | 1 | 25 | 1.4 | 35 |  | 0 | 0 | 0 | 0 | 35 | 20% | 7 | 7 | 0
JOT-AX-WR-L2-00082_00
4 | L4 PARAPET, ROADSIDE | JOT-AX-SD-L4-00005_02 | G-X / 11-16 | PARAPET L4, PAINT |  | 1 | 23.19 | 1.4 | 32.47 |  | 0 | 0 | 0 | 0 | 32.47 | 20% | 6.494 | 6.494 | 0
JOT-AX-WR-L2-00075_00
4 | L4 PARAPET,RESIDENTIAL | JOT-AX-SD-L4-00005_02 | W-X/15-17 | WALL,L4 |  | 1 | 2.877 | 1.4 | 4.0278 |  | 0 | 0 | 0 | 0 | 4.0278 | 70% | 2.8195 | 0 | 2.8195
JOT-AX-WR-L4-00089,97
[14 empty] | TOTAL | 267.6056 |  | 212.4213 | 173.4705 | 38.9508