## Summary
SN | Description | Total Scope | Balance Scope | Already Claim Amount | Previous | This Month | Cumulative
01 | Contract Works | 1600000 | 1066075 | 533925.409 | 60969.2358 | 40710.0487 | 101679.2845
02 | Variations (old) | 485255 | 472082 | 13173 | 45656.0095 | 14474.7977 | 60130.8072
| Total Value of Work Done |  | 1538157 |  | 106625.2453 | 55184.8464 | 161810.0917
03 | New Variations | 631100 | 631100 | 0 | 10871.3666 | 226925.5087 | 237796.8754
| Total Value of Work Done |  | 2169257 |  | 117496.6119 | 282110.3552 | 399606.9671
04 | Advance Payment |  | 10% |  | 153815.7 | 0 | 153815.7
05 | Advance Payment Recovery |  | 10% |  | -11749.6612 | -28211.0355 | -39960.6967
| TOTAL |  |  |  | 259562.6507 | 253899.3196 | 513461.9704

## Progress Bill
PROGRESS BOQ
Item | Description | Qty. | Unit | Rate | Amount | OCI - Certified |  | Balance Works |  |  | Pervious Work Certified |  |  | Balance Works |  |  | This Month Workdone |  |  | Cumulative |  |  | Balance Works
|  |  |  | Rate | Amount | Progress % | Amount | Progress % | Qty | Amount | Pervious % | Pervious Qty | Amount | Progress % | Qty | Amount | Progress % | Qty | Amount | Progress % | Qty | Amount | Progress % | Qty | Amount
DESIGN AND BUILD OF TERRACO SYSTEM
[8 empty] | 100% | [5 empty] | 100% | [8 empty] | 100%
EIFS WITH TERRACO RENDER SYSTEM
EIFS with TERRACO System, mineral wool, Adhesive, groove requirement,including all necessary framing, fitting, fixing, backing framing support, decoration, Primer, Basecoat and Final coat etc and the like all in accordance with drawings and specifications.
ON BLOCKWORK / CONCRETE WALL
A | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 75mm | 876 | m2 | 295 | 258420 |  |  | 100% | 876 | 258420 |  |  |  | 100% | 876 | 258420 | 0% | 0 | 0 |  | 0 | 0 | 100% | 876 | 258420
B | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 100mm | 692 | m2 | 319 | 220748 | 89.8% | 198241.4271 | 10.2% | 70.5535 | 22506.5729 | 89.43% | 618.8872 | 197425.0167 | 10.57% | 73.1128 | 23322.9833 | 0% | 0 | 0 | 89.43% | 618.8872 | 197425.0167 | 10.57% | 73.1128 | 23322.9833
C | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 150mm | 266 | m2 | 347 | 92302 |  |  | 100% | 266 | 92302 |  |  |  | 100% | 266 | 92302 | 0% | 0 | 0 |  | 0 | 0 | 100% | 266 | 92302
D | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 200mm | 682 | m2 | 380 | 259160 | 95.74% | 248117.6104 | 4.261% | 29.0589 | 11042.3896 | 99.13% | 676.0951 | 256916.1456 | 0.8658% | 5.9049 | 2243.8544 | 0% | 0 | 0 | 99.13% | 676.0951 | 256916.1456 | 0.8658% | 5.9049 | 2243.8544
E | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 275mm | 176 | m2 | 415 | 73040 |  |  | 100% | 176 | 73040 |  |  |  | 100% | 176 | 73040 | 0% | 0 | 0 |  | 0 | 0 | 100% | 176 | 73040
F | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 300mm | 854 | m2 | 435 | 371490 | 20.26% | 75252.564 | 79.74% | 681.0056 | 296237.436 | 33.99% | 290.3156 | 126287.2825 | 66.01% | 563.6844 | 245202.7175 | 0% | 0 | 0 | 33.99% | 290.3156 | 126287.2825 | 66.01% | 563.6844 | 245202.7175
G | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 400mm | 422 | m2 | 500 | 211000 | 31.07% | 65567.88 | 68.93% | 290.8642 | 145432.12 | 32% | 135.04 | 67520 | 68% | 286.96 | 143480 | 0% | 0 | 0 | 32% | 135.04 | 67520 | 68% | 286.96 | 143480
STAND ALONE EIFS SYSTEM WITH NECESSARY BACK FRAMING SUPPORT
H | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 75mm | 88 | m2 | 400 | 35200 |  |  | 100% | 88 | 35200 | 0% | 0 | 0 | 100% | 88 | 35200 | 0% | 0 | 0 |  | 0 | 0 | 100% | 88 | 35200
J | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 300mm | 86 | m2 | 450 | 38700 |  |  | 100% | 86 | 38700 | 0% | 0 | 0 | 100% | 86 | 38700 | 76.59% | 65.87 | 29641.5 | 76.59% | 65.87 | 29641.5 | 23.41% | 20.13 | 9058.5
K | EIFS System with TERRACO finishes (TERRACO acid wash finishes) with Built-up 400mm | 24 | m2 | 525 | 12600 |  |  | 100% | 24 | 12600 | 0% | 0 | 0 | 100% | 24 | 12600 | 87.85% | 21.083 | 11068.5488 | 87.85% | 21.083 | 11068.5488 | 12.15% | 2.917 | 1531.4512
TERRACO RENDER SYSTEM
TERRACO Render System, Adhesive, groove requirement, including all necessary framing, fitting, fixing, backing framing support, Primer, Basecoat and Final coat decoration, etc and the like all in accordance with drawings and specifications.
ON BLOCKWORK / CONCRETE WALL
A | TERRACO RENDER System (TERRACO acid wash finishes) | 1298 | m2 | 175 | 227150 | 5.909% | 13423.2 | 94.09% | 1221.296 | 213726.8 | 5.909% |  | 13423.2 | 94.09% | 1221.296 | 213726.8 | 0% | 76.704 | 0 | 5.909% | 76.704 | 13423.2 | 94.09% | 1221.296 | 213726.8
| Discount |  |  |  | -199810 | 33.37% | -66677.2725 | 66.63% | 0 | -133132.7275 | 33.37% |  | -66677 | 66.63% | 0 | -133132.7275 | -0.0003381% | 0 | 0 | 33.37% | 0 | -66677 | 66.63% | 0 | -133133
| Sub Total -1 |  |  |  | 1600000 | 33.37% | 533925.409 |  | 0 | 1066074.591 |  |  | 594894.6448 |  | 0 | 1005105.6277 |  | 0 | 40710.0487 |  | 0 | 635604.6935 |  | 0 | 964395.3065
| TOTAL |  |  |  | 1600000 |  | 533925.409 |  |  | 1066074.591 |  |  | 594894.6448 |  |  | 1005105.6277 |  |  | 40710.0487 |  |  | 635604.6935 |  |  | 964395.3065

## VARIATIONS
SN | Variations | Total Work Scope |  |  | Progress as per WFA |  |  | Remaining Work |  | Previous |  | This Month | This Month | Cumulative |  |  | Cumulative
|  | QTY | Rate | Amount | % | QTY | Amount | QTY | Amount | QTY | Amount | QTY | Amount | % | QTY | Amount | % | QTY | Amount
01 | Additional EFIS to parapets at L4, L29 | 256.9673 | 319 | 81973 | 13.7% | 35.21 | 11232 | 221.7573 | 70741 | 173.4705 | 55337.0767 | 38.9508 | 12425.3052 | 82.66% | 212.4213 | 67762.3819 | 17.34% | 44.5461 | 14210.1941
02 | Additional EFIS to non-accessible balconies | 766.0026 | 380 | 291081 | 0% |  | 0 | 766.0026 | 291081 |  | 0 |  | 0 |  |  | 0 | 100% | 766.0026 | 291081
03 | PVC grooved to EFIS system | 823.01 | 32.16 | 26468 | 7.333% | 60.3545 | 1941 | 762.6555 | 24527 | 108.58 | 3491.9328 | 63.728 | 2049.4925 | 20.94% | 172.308 | 5541.4253 | 79.06% | 650.702 | 20926.5747
04 | Additional EFIS to entrance at L2 | 169.4702 | 319 | 54061 | 0% |  | 0 | 169.4702 | 54061 |  | 0 |  | 0 |  |  | 0 | 100% | 169.4702 | 54061
05 | Additional EFIS to parapets at L2 | 99.2853 | 319 | 31672 | 0% |  | 0 | 99.2853 | 31672 |  | 0 |  | 0 |  |  | 0 | 100% | 99.2853 | 31672
Sub-Totals |  |  |  | 485255 | 2.715% |  | 13173 |  | 472082 |  | 58829.0095 |  | 14474.7977 | 15.11% |  | 73303.8072 | 84.89% |  | 411950.7688
NEW VARIATIONS
06 | EIFS WITH BUILTUP 300mm | 854 | 450 | 384300 | [5 empty] | 24.1586 | 10871.3666 | 185.5587 | 83501.3979 | 24.56% | 209.7173 | 94372.7645 | 75.44% | 644.2827 | 289927.2355
07 | EIFS WITH BUILTUP 400mm | 422 | 525 | 221550 | [5 empty] | 0 | 0 | 225.0935 | 118174.1109 | 53.34% | 225.0935 | 118174.1109
08 | 300 & 400mm EIFS Removal | 1 | 25250 | 25250 | [5 empty] | 0 | 0 | 1 | 25250 | 100% | 1 | 25250
Sub-Totals |  |  |  | 631100 | [6 empty] | 10871.3666 |  | 226925.5087 | 37.68% |  | 237796.8754 | 45.94% |  | 289927.2355
| Installation of stud frame + 200mm EIFS system to replace 400mm EIFS system | 422 | 525 | 221550
| Installation of stud frame + 200mm EIFS system to replace 300mm EIFS system | 854 | 450 | 384300
| Installation of stud frame + 200mm EIFS system to replace 275mm EIFS system | 176 | 415 | 73040
| Break up existing 400/300mm EIFS system | 1 | 12819 | 12819

## PERCENTAGE SUMMARY
REQUEST FOR PAYMENT APPLICATION
SUMMARY REPORT
Main Contractor : Roberts-Pizzarotti JV
Scope of works : External Insulation and Finishing Systems (EPS)
Site : Dorchester Hotel (Plot 18)
S.No. |  | ITEM OF WORKS | UNIT | RATE | Weightage |  |  | % Completion |  |  |  | Overall progress % | PROGRESS QUANTITY
| BOQ REF. |  |  |  |  | QTY | AMOUNT
|  |  |  | (AED) |  |  |  | PREVIOUS | CURRENT | CUMULATIVE |  |  | PREVIOUS | CURRENT | CUMULATIVE
MAIN WORKS
EIFS WITH TERRACO RENDER SYSTEM
1 | ITEM G | EIFS 400MM | Sqm | 500 |  | 422 | 211000
|  | EPS BOARDS-70% |  |  | 70% |  |  | 31.18% | 0% | 31.18% | 21.82% | 29.81% | 131.568 | 0 | 131.568 | 32% | 2.191%
|  | BASEOCAT-20% |  |  | 20% |  |  | 31.18% | 0% | 31.18% | 6.235% |  | 131.568 | 0 | 131.568
|  | PAINT-10% |  |  | 10% |  |  | 17.5% | 0% | 17.5% | 1.75% |  | 73.8396 | 0 | 73.8396
2 | ITEM F | EIFS 300MM | Sqm | 435 |  | 854 | 371490
|  | EPS BOARDS-70% |  |  | 70% |  |  | 22.51% | 0% | 22.51% | 15.76% | 20.26% | 192.216 | 0 | 192.216 | 33.99% | 13.74%
|  | BASEOCAT-20% |  |  | 20% |  |  | 22.51% | 0% | 22.51% | 4.502% |  | 192.216 | 0 | 192.216
|  | PAINT-10% |  |  | 10% |  |  | 0% | 0% | 0% | 0% |  | 0 | 0 | 0
3 | ITEM D | EIFS 200MM | Sqm | 380 |  | 682 | 259160
|  | EPS BOARDS-70% |  |  | 70% |  |  | 105.4% | 0% | 105.4% | 73.81% | 94.04% | 719.1192 | 0 | 719.1192 | 99.13% | 5.095%
|  | BASEOCAT-20% |  |  | 20% |  |  | 88.57% | 0% | 88.57% | 17.71% |  | 604.0448 | 0 | 604.0448
|  | PAINT-10% |  |  | 10% |  |  | 25.15% | 0% | 25.15% | 2.515% |  | 171.5176 | 0 | 171.5176
4 | ITEM B | EIFS 100MM | Sqm | 319 |  | 692 | 220748
|  | EPS BOARDS-70% |  |  | 70% |  |  | 86.94% | 0% | 86.94% | 60.86% | 81.79% | 601.6058 | 0 | 601.6058 | 89.43% | 7.645%
|  | BASEOCAT-20% |  |  | 20% |  |  | 83.46% | 0% | 83.46% | 16.69% |  | 577.5384 | 0 | 577.5384
|  | PAINT-10% |  |  | 10% |  |  | 42.41% | 0% | 42.41% | 4.241% |  | 293.508 | 0 | 293.508
TERRACO RENDER SYSTEM
5 | ITEM B | EIFS RENDER | Sqm | 175 |  | 1298 | 227150
|  | EPS BOARDS-80% |  |  | 80% |  |  | 7.387% | 0% | 7.387% | 5.909% | 5.909% | 95.88 | 0 | 95.88 | 5.909% | 0%
|  | BASEOCAT-20% |  |  | 20% |  |  | 0% | 0% | 0% | 0% |  | 0 | 0 | 0
6 | ITEM J | 300mm Stand Alone | Sqm | 450 | 100% | 86 | 38700 | 0% | 76.59% | 76.59% |  |  | 0 | 65.87 | 65.87
7 | ITEM K | 400mm Stand Alone | Sqm | 525 | 100% | 24 | 12600 | 0% | 87.85% | 87.85% |  |  | 0 | 21.083 | 21.083
VARIATIONS
8 |  | PVC GROOVE | Lm | 32.16 |  | 823.01 | 26468 | 13.19% | 7.743% | 20.94% |  | 20.94% | 108.58 | 63.728 | 172.308 | 20.94% | 0%
9 | ITEM B | EIFS 100MM PARAPET WALL | Sqm | 319 |  | 256.9673 | 81972.576 | [8 empty] | 82.66% | 0%
|  | EPS BOARDS | [5 empty] | 67.51% | 15.16% | 82.66% |  | 82.66% | 173.4705 | 38.9508 | 212.4213
10 | KCE-VOR-1_04 | EIFS WITH BUILTUP 300mm | Sqm | 450 |  | 854 | 384300 | 2.829% | 21.73% | 24.56% |  | 24.56% | 24.1586 | 185.5587 | 209.7173 | 24.56% | 0%
|  | EIFS WITH BUILTUP 400mm | Sqm | 525 |  | 422 | 384300 | 0% | 26.36% | 26.36% |  | 26.36% | 0 | 225.0935 | 225.0935
TOTAL
13.7%

## EIFS 400mm EPS BOARDS (hidden)
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS 400mm EPS BOARDS | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  | (Sqm)
1 | ELEVATION 01 (BASEMENT RAMP SIDE) | JOT-AX-SD-GF-00001_00_E | D-G/Y1 | WALL-GF |  | 1 | 11.32 | 4.6 | 52.072 | DOOR | 2 | 1.2 | 1.78 | 4.272 | 47.8 | 47.8 | 0
JOT-AX-WR-GF-00003
2 | ELEVATION 01 (BASEMENT RAMP SIDE) | JOT-AX-SD-ML-00003_00_E | D-G/Y1 | WALL-L2L3 |  | 1 | 11.32 | 7.4 | 83.768 |  | 0 | 0 | 0 | 0 | 83.768 | 83.768 | 0
JOT-AX-WR-ML-00007
[14 empty] | TOTAL | 131.568 | 131.568 | 0

## EIFS 400mm BASECOAT (hidden)
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS 400mm BASECOAT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  | (Sqm)
1 | ELEVATION 01 (BASEMENT RAMP SIDE) | JOT-AX-SD-GF-00001_00_E | D-G/Y1 | WALL-GF |  | 1 | 11.32 | 4.6 | 52.072 | DOOR | 2 | 1.2 | 1.78 | 4.272 | 47.8 | 47.8 | 0
JOT-AX-WR-GF-00006
2 | ELEVATION 01 (BASEMENT RAMP SIDE) | JOT-AX-SD-ML-00003_00_E | D-G/Y1 | WALL-L2L3 |  | 1 | 11.32 | 7.4 | 83.768 |  | 0 | 0 | 0 | 0 | 83.768 | 83.768 | 0
JOT-AX-WR-L4-00011
[14 empty] | TOTAL | 131.568 | 131.568 | 0

## EIFS 400mm PAINT (hidden)
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS 400mm PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  | (Sqm)
1 | RAMPSIDE | JOT-AX-SD-ML-00003_00_E | D-H/Y1 | L2-WALL | PA9 | 1 | 11.61 | 6.36 | 73.8396 |  | 0 | 0 | 0 | 0 | 73.8396 | 73.8396 | 0
JOT-AX-WR-ML-00054
[14 empty] | TOTAL | 73.8396 | 73.8396 | 0

## EIFS 300mm EPS BOARDS (hidden)
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PROGRESS % | WORK DONE TO DATE | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS 300mm EPS BOARDS | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
4 | ELEVATION 06 ( LIFT AREA) | JOT-AX-SD-ML-00003_00_E | G-H/3-7 | WALL-L2L3 |  | 1 | 27.3 | 7.6 | 207.48 | LIFT LOBBY OPENING L2,L3 | 2 | 3.18 | 2.4 | 15.264 | 192.216 | 100% | 192.216 | 192.216 | 0
| CORE WALL AREA | JOT-AX-WR-ML-00014
[14 empty] | TOTAL | 192.216 |  | 192.216 | 192.216 | 0

## EIFS 300mm BASECOAT (hidden)
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS 300mm BASECOAT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  | (Sqm)
4 | ELEVATION 06 ( LIFT AREA) | JOT-AX-SD-ML-00003_00_E | G-H/3-7 | WALL-L2L3 |  | 1 | 27.3 | 7.6 | 207.48 | LIFT LOBBY OPENING L2,L3 | 2 | 3.18 | 2.4 | 15.264 | 192.216 | 192.216 | 0
CORE WALL AREA
JOT-AX-WR-ML-00016
[14 empty] | TOTAL | 192.216 | 192.216 | 0

## EIFS 200mm EPS BOARDS
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PROGRESS % | WORK DONE TO DATE | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS 200mm EPS BOARDS | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | ELEVATION 01-03 (BOH-ETS ROOMS) | JOT-AX-SD-GF-00001_00_E | D-I/Y1-Y3 | WALL-GF |  | 1 | 38.37 | 4.6 | 176.502 | DOOR | 1 | 1.4 | 2 | 2.8 | 157.9976 |  | 157.9976 | 157.9976 | 0
| JOT-AX-WR-GF-00003 | [8 empty] | DOOR | 1 | 1.1 | 2 | 2.2
| JOT-AX-WR-GF-00002 | [8 empty] | WINDOW | 1 | 0.76 | 1.19 | 0.9044
| JOT-AX-WR-GF-000015 | [8 empty] | DOOR | 2 | 2.1 | 3 | 12.6
2 | ELEVATION 01-03 (BOH-ETS ROOMS) | JOT-AX-SD-ML-00003_00_E | D-I/Y1-Y3 | WALL-L2L3 |  | 1 | 38.37 | 7.4 | 283.938 | DOOR | 1 | 1.2 | 1.73 | 2.076 | 281.862 |  | 281.862 | 281.862 | 0
JOT-AX-WR-ML-00007
3 | (HOUSEKEEPING LOBBY) | JOT-AX-SD-GF-00001_00_E | D-F/7-8 | WALL GF |  | 1 | 4 | 3.82 | 15.28 | DOOR | 1 | 1.2 | 2 | 2.4 | 17.263 |  | 17.263 | 17.263 | 0
| JOT-AX-WR-GF-00017 |  |  |  |  | 1 | 0.9 | 4.87 | 4.383
4 | (HOUSEKEEPING LOBBY) | JOT-AX-SD-GF-00001 | E-F/6-7 | WALL GF |  | 1 | 11.53 | 4.22 | 48.6566 | Door | 1 | 1.2 | 1.7 | 2.04 | 44.0566 |  | 44.0566 | 44.0566 | 0
| JOT-AX-WR-GF-00024 | [9 empty] | 2 | 0.8 | 1.6 | 2.56
5 | STAIR 6 WALL | JOT-AX-SD-L4-00005_02 | E-H/10-12 | WALL L4 |  | 1 | 21.97 | 9.92 | 217.94 |  | 0 | 0 | 0 | 0 | 217.94 |  | 217.94 | 217.94 | 0
JOT-AX-WR-L4-00056
[14 empty] | TOTAL | 719.1192 |  | 719.1192 | 719.1192 | 0

## EIFS 200mm BASECOAT
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PROGRESS % | WORK DONE TO DATE | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS 200mm BASECOAT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | ELEVATION 01-03 (BOH-ETS ROOMS) | JOT-AX-SD-GF-00001_00_E | D-I/Y1-Y3 | WALL-GF |  | 1 | 38.37 | 4.6 | 176.502 | DOOR | 1 | 1.4 | 2 | 2.8 | 157.9976 |  | 157.9976 | 157.9976 | 0
| JOT-AX-WR-GF-00006 | [8 empty] | DOOR | 1 | 1.1 | 2 | 2.2
| JOT-AX-WR-GF-00019 | [8 empty] | WINDOW | 1 | 0.76 | 1.19 | 0.9044
[10 empty] | DOOR | 2 | 2.1 | 3 | 12.6
2 | ELEVATION 01-03 (BOH-ETS ROOMS) | JOT-AX-SD-ML-00003_00_E | D-I/Y1-Y3 | WALL-L2L3 |  | 1 | 38.37 | 7.4 | 283.938 | DOOR | 1 | 1.2 | 1.73 | 2.076 | 281.862 |  | 281.862 | 281.862 | 0
JOT-AX-WR-L4-00011
3 | (HOUSEKEEPING LOBBY) | JOT-AX-SD-GF-00001_00_E | D-F/7-8 | WALL GF |  | 1 | 4 | 3.82 | 15.28 | DOOR | 1 | 1.2 | 2 | 2.4 | 17.263 |  | 17.263 | 17.263 | 0
[6 empty] | 1 | 0.9 | 4.87 | 4.383
4 | (HOUSEKEEPING LOBBY) | JOT-AX-SD-GF-00001 | E-F/6-7 | WALL GF |  | 1 | 11.53 | 4.22 | 48.6566 | Door | 1 | 1.2 | 1.7 | 2.04 | 44.0566 |  | 44.0566 | 44.0566 | 0
| JOT-AX-WR-GF-00024 | [9 empty] | 2 | 0.8 | 1.6 | 2.56
5 | STAIR 6 WALL,Elevation-10 | JOT-AX-SD-L4-00005_02 | E-H/10-12 | WALL L4 |  | 2 | 8.1895 | 9.92 | 81.24 | [5 empty] | 81.24 |  | 81.24 | 81.24 | 0
JOT-AX-WR-L4-00071
6 | LEVEL-4 to 5,STAIR 6 WALL,Elevation-08 | JOT-AX-SD-L4-00005_02 | E-H/10-12 | WALL L4,Basecoat |  | 1 | 9.1 | 9.92 | 90.272 |  | 0 | 0 | 0 | 0 | 90.272 | 20% | 18.0544 | 18.0544 | 0
JOT-AX-WR-L4-00070_01
7 | LEVEL-4 to 5,STAIR 6 WALL,Elevation-07 | JOT-AX-SD-L4-00005_02 | E-H/10-12 | WALL L4,Basecoat |  | 1 | 1.8 | 9.92 | 17.856 |  | 0 | 0 | 0 | 0 | 17.856 | 20% | 3.5712 | 3.5712 | 0
JOT-AX-WR-L4-00070_01
[14 empty] | TOTAL | 690.5472 |  | 604.0448 | 604.0448 | 0

## EIFS 200mm PAINT
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS 200mm PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  | (Sqm)
1 | RAMPSIDE | JOT-AX-WR-ML-00003_00_E | D-H/Y1 | L2 WALL | PA9 | 1 | 4.36 | 6.36 | 27.7296 | [5 empty] | 27.7296 | 27.7296 | 0
| JOT-AX-WR-ML-00054 |  |  |  |  | 1 | 3.55 | 6.36 | 22.578 | [5 empty] | 22.578 | 22.578 | 0
2 | Gate 2 Front | JOT-AX-WR-ML-00003_01_E | Y1-Y3/G-H | L2 WALL | PA11 | 1 | 19.06 | 6.36 | 121.21 | [5 empty] | 121.21 | 121.21 | 0
[14 empty] | TOTAL | 171.5176 | 171.5176 | 0

## EIFS 100mm EPS BOARDS
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS 100mm EPS BOARDS | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | L29, PARAPET | RP-LX-SD-L29-1856 | S-T/16-18 | WALL L29 |  | 1 | 9 | 1.4 | 12.6 |  | 0 | 0 | 0 | 0 | 12.6 |  | 12.6 | 12.6 | 0
OT-AX-WR-GF-00005
4 | ELEVATION 06 ( LIFT AREA) | JOT-AX-SD-ML-00003_00_E | G-H/3-7 | WALL-L2L3 |  | 1 | 2.9 | 7.6 | 22.04 | LIFT LOBBY OPENING L2,L3 | 0 | 0 | 0 | 0 | 22.04 |  | 22.04 | 22.04 | 0
CORE WALL AREA
JOT-AX-WR-ML-00014
3 | (HOUSEKEEPING LOBBY) | JOT-AX-SD-GF-00001_00_E | D-F/7-8 | WALL GF |  | 1 | 4 | 3.82 | 15.28 |  | 0 | 0 | 0 | 0 | 15.28 |  | 15.28 | 15.28 | 0
| JOT-AX-WR-GF-00017 |  |  |  |  | 1 | 1.7 | 4.87 | 8.279 |  | 0 | 0 | 0 | 0 | 8.279 |  | 8.279 | 8.279 | 0
4 | L29 Parapet | JOT-AX-SD-GF-00006_01 | S-W/13-14 | WALL 29 |  | 1 | 16.5 | 1.4 | 23.1 |  | 0 | 0 | 0 | 0 | 23.1 |  | 23.1 | 23.1 | 0
JOT-AX-WR-L29-00020
5 | L29 Parapet | JOT-AX-SD-GF-00006_01 | S-T/18-24 | WALL 29 | BO14 | 1 | 45 | 1.4 | 63 | [5 empty] | 63 |  | 63 | 63 | 0
JOT-AX-WR-L29-00030
6 | L4 PARAPET | JOT-AX-SD-GF-00005_02 | B-G/Y1 | WALL 14 | BO15 | 1 | 30.7 | 1.1 | 33.77 | [5 empty] | 33.77 |  | 33.77 | 33.77 | 0
JOT-AX-WR-L4-00031
7 | L29 Parapet | JOT-AX-SD-ML-00006_01 | S-T/14-18 | WALL L29 | BO16 | 1 | 28.31 | 1.4 | 39.634 | [5 empty] | 39.634 |  | 39.634 | 39.634 | 0
JOT-AX-WR-L29-00037
8 | L29 Parapet | JOT-AX-SD-ML-00006_01 | S-X/23-24 | WALL L29 | BO17 | 1 | 24.08 | 1.4 | 33.712 | [5 empty] | 33.712 |  | 33.712 | 33.712 | 0
JOT-AX-WR-L29-00040
9 | L29 Parapet | JOT-AX-SD-ML-00006_01 | W-X/13-18 | WALL L29 | BO18 | 1 | 7.5 | 1.4 | 10.5 | [5 empty] | 10.5 |  | 10.5 | 10.5 | 0
| JOT-AX-WR-L29-00043 |  |  |  |  | 1 | 4.07 | 1.6 | 6.512 | [5 empty] | 6.512 |  | 6.512 | 6.512 | 0
[6 empty] | 1 | 21.58 | 1.65 | 35.607 | [5 empty] | 35.607 |  | 35.607 | 35.607 | 0
10 | L4 Parapet | JOT-AX-SD-L4-00005_02 | F-H/Y1-4 | WALL L4 | BO19 | 1 | 49.2 | 1.1 | 54.12 | [5 empty] | 54.12 |  | 54.12 | 54.12 | 0
JOT-AX-WR-L4-00036
11 | L29 Parapet | 2JOT-AX-SD-ML-00006_02 | S-T/13-15 | PARAPET WALL L29 | BO20 | 1 | 6.43 | 1.4 | 9.002 | [5 empty] | 9.002 |  | 9.002 | 9.002 | 0
JOT-AX-WR-L29-00048
12 | L29 Parapet | 2JOT-AX-SD-ML-00006_02 | V-X/13-15 | PARAPET WALL L29 | BO21 | 1 | 9.92 | 1.4 | 13.888 | [5 empty] | 13.888 |  | 13.888 | 13.888 | 0
JOT-AX-WR-L29-00051
13 | GF BALLROOM WALL | 2JOT-AX-SD-GF-00002_02 | A-U/23-25 | WALL GF | BO22 | 1 | 21.23 | 7.28 | 154.5544 | [5 empty] | 154.5544 |  | 154.5544 | 154.5544 | 0
| JOT-AX-WR-L29-00052 |  |  |  |  | 1 | 9.32 | 4.5 | 41.94 | [5 empty] | 41.94 |  | 41.94 | 41.94 | 0
14 | STAIR 6 WALL,Elevation-07, | JOT-AX-SD-ML-00003_01 | G/10-11 | WALL, L2,Insulation |  | 1 | 4.62 | 7.442 | 34.382 |  | 0 | 0 | 0 | 0 | 34.382 | 70% | 24.0674 | 24.0674 | 0
JOT-AX-WR-ML-00074_01
[14 empty] | TOTAL | 611.9204 |  | 601.6058 | 601.6058 | 0

## EIFS 100mm BASECOAT
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS 100mm BASECOAT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  | (Sqm)
3 | L29, PARAPET | RP-LX-SD-L29-1856 | S-T/16-18 | WALL L29 |  | 1 | 9 | 1.4 | 12.6 |  | 0 | 0 | 0 | 0 | 12.6 | 12.6 | 0
JOT-AX-WR-L29-00008
4 | ELEVATION 06 ( LIFT AREA) | JOT-AX-SD-ML-00003_00_E | G-H/3-7 | WALL-L2L3 |  | 1 | 2.9 | 7.6 | 22.04 | LIFT LOBBY OPENING L2,L3 | 0 | 0 | 0 | 0 | 22.04 | 22.04 | 0
CORE WALL AREA
JOT-AX-WR-ML-00016
3 | (HOUSEKEEPING LOBBY) | JOT-AX-SD-GF-00001_00_E | D-F/7-8 | WALL GF |  | 1 | 4 | 3.82 | 15.28 |  | 0 | 0 | 0 | 0 | 15.28 | 15.28 | 0
[6 empty] | 1 | 1.7 | 4.87 | 8.279 |  | 0 | 0 | 0 | 0 | 8.279 | 8.279 | 0
4 | L29 Parapet | JOT-AX-SD-GF-00006_01 | S-W/13-14 | WALL 29 |  | 1 | 16.5 | 1.4 | 23.1 |  | 0 | 0 | 0 | 0 | 23.1 | 23.1 | 0
JOT-AX-WR-L29-00020
5 | L29 Parapet | JOT-AX-SD-GF-00006_01 | S-T/18-24 | WALL 29 | BO14 | 1 | 45 | 1.4 | 63 | [5 empty] | 63 | 63 | 0
JOT-AX-WR-L29-00030
6 | L4 PARAPET | JOT-AX-SD-GF-00005_02 | B-G/Y1 | WALL L4 | BO15 | 1 | 30.7 | 1.1 | 33.77 | [5 empty] | 33.77 | 33.77 | 0
JOT-AX-WR-L4-00033
7 | L29 PARAPET | JOT-AX-SD-ML-00006_01 | S-T/14-18 | WALL L29 | BA16 | 1 | 28.31 | 1.4 | 39.634 | [5 empty] | 39.634 | 39.634 | 0
JOT-AX-WR-L29-00038
8 | L29 PARAPET | JOT-AX-SD-ML-00006_01 | S-X/23-24 | WALL L29 | BA17 | 1 | 24.08 | 1.4 | 33.712 | [5 empty] | 33.712 | 33.712 | 0
JOT-AX-WR-L29-00038
9 | L4 PARAPET | JOT-AX-SD-L4-00005_02 | F-H/Y1-4 | WALL L4 | BA15 | 1 | 49.2 | 1.1 | 54.12 | [5 empty] | 54.12 | 54.12 | 0
JOT-AX-WR-L4-00044
10 | L29 Parapet | 2JOT-AX-SD-ML-00006_01 | W-X/13-18 | WALL L29 | BA18 | 1 | 7.5 | 1.4 | 10.5 | [5 empty] | 10.5 | 10.5 | 0
| JOT-AX-WR-L29-00046 |  |  |  |  | 1 | 4.07 | 1.6 | 6.512 | [5 empty] | 6.512 | 6.512 | 0
[6 empty] | 1 | 21.58 | 1.65 | 35.607 | [5 empty] | 35.607 | 35.607 | 0
11 | L29 Parapet | 2JOT-AX-SD-ML-00006_02 | S-T/13-15 | PARAPET WALL L29 | BA19 | 1 | 6.43 | 1.4 | 9.002 | [5 empty] | 9.002 | 9.002 | 0
JOT-AX-WR-L29-00049
12 | L29 Parapet | 2JOT-AX-SD-ML-00006_02 | V-X/13-14 | PARAPET WALL L29 | BA20 | 1 | 9.92 | 1.4 | 13.888 | [5 empty] | 13.888 | 13.888 | 0
JOT-AX-WR-L29-00053
12 | GF Ballroom Wall | 2JOT-AX-SD-GF-00002_02 | A-U/23-25 | WALL GF | BA21 | 1 | 21.23 | 7.28 | 154.5544 | [5 empty] | 154.5544 | 154.5544 | 0
| JOT-AX-WR-L29-00058 |  |  |  |  | 1 | 9.32 | 4.5 | 41.94 | [5 empty] | 41.94 | 41.94 | 0
[14 empty] | TOTAL | 577.5384 | 577.5384 | 0

## EIFS 100mm PAINT
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  | (Sqm)
1 | L29, PARAPET | RP-LX-SD-L29-1856 | S-T/16-18 |  | PA1 | 1 | 9 | 1.4 | 12.6 |  | 0 | 0 | 0 | 0 | 12.6 | 12.6 | 0
JOT-AX-WR-L29-00013_01
2 | L29 Parapet | JOT-AX-SD-ML-00006_01 | S-W/13-14 | WALL L29 | PA2 | 1 | 16.5 | 1.4 | 23.1 |  | 0 | 0 | 0 | 0 | 23.1 | 23.1 | 0
JOT-AX-WR-L29-00025
3 | L29 Parapet | JOT-AX-SD-ML-00006_01 | S-T/18-24 | WALL L29 | PA3 | 1 | 45 | 1.4 | 63 | [5 empty] | 63 | 63 | 0
JOT-AX-WR-L29-00034
4 | L4 Parapet | JOT-AX-SD-L4-00005_02 | B-G/Y1 | WALL L4 | PA4 | 1 | 30.7 | 1.1 | 33.77 | [5 empty] | 33.77 | 33.77 | 0
JOT-AX-WR-L4-00035
5 | L29 Parapet | JOT-AX-SD-ML-00006_01 | S-T/14-18 | WALL L29 | PA5 | 1 | 28.31 | 1.4 | 39.634 | [5 empty] | 39.634 | 39.634 | 0
JOT-AX-WR-L29-00041
6 | L29 Parapet | 2JOT-AX-SD-ML-00006_02 | S-X/23-24 | WALL L29 | PA6 | 1 | 24.08 | 1.4 | 33.712 | [5 empty] | 33.712 | 33.712 | 0
JOT-AX-WR-L29-00045
7 | L4 Parapet | JOT-AX-SD-L4-00005_02 | F-H/Y1-4 | WALL L4 | PA7 | 1 | 49.2 | 1.1 | 54.12 | [5 empty] | 54.12 | 54.12 | 0
JOT-AX-WR-L4-00047
8 | L29 Parapet | JOT-AX-SD-ML-00006_02 | S-T/13-15 | PARAPET WALL L29 | PA8 | 1 | 6.43 | 1.4 | 9.002 | [5 empty] | 9.002 | 9.002 | 0
JOT-AX-WR-L29-00050
9 | L29 Parapet | JOT-AX-SD-ML-00006_02 | V-X/13-14 | PARAPET WALL L29 | PA10 | 1 | 17.55 | 1.4 | 24.57 | [5 empty] | 24.57 | 24.57 | 0
JOT-AX-WR-L29-00055
[14 empty] | TOTAL | 293.508 | 293.508 | 0

## EIFS RENDER
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  | (Sqm)
1 | L4 ZONE 3, GATE 2 FRONT | JOT-AX-SD-L04-00005_00_E | A-I/Y1-4 |  |  | 1 | 79.9 | 1.2 | 95.88 |  | 0 | 0 | 0 | 0 | 95.88 | 95.88 | 0
AREA
JOT-AX-WR-L4-00009
[14 empty] | TOTAL | 95.88 | 95.88 | 0

## EIFS -STAND ALONE (300MM)
DETAILED STATUS REPORT
Client Name |  | : | Omniyat Investments & Management LLC
Project Name |  | : | Dorchester Hotel (PLOT 18)
Main Contractor |  | : | Khansaheb civil engineering llc
Scope of works |  | : | External Insulation Finishing System (EPS)
EIFS SYSTEM+BUILT UP(300MM) | [17 empty] | MONTH: | October 2022
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 35%-FRAMING,35%-EPS BOARDS,20%-BASECOAT,10%-PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | STAIR 6 WALL,LEVEL-02 to 3 | JOT-AX-SD-ML-00003_02 | E-H/10-11 | WALL L2 |  | 1 | 4 | 7.275 | 29.1 |  | 0 | 0 | 0 | 0 | 29.1 | 90% | 26.19 | 0 | 26.19
JOT-AX-WR-ML-00085,100,108,104,110
2 | Residential,Stair-6,L4-5 | JOT-AX-SD-L4-00005_02 | T-W/13-14 | WALL L4-5 |  | 1 | 4 | 9.92 | 39.68 |  | 0 | 0 | 0 | 0 | 39.68 | 100% | 39.68 | 0 | 39.68
JOT-AX-WR-ML-00076,81,90,98
[14 empty] | TOTAL | 68.78 |  | 65.87 | 0 | 65.87

## EIFS -STAND ALONE (400MM)
DETAILED STATUS REPORT
Client Name |  | : | Omniyat Investments & Management LLC
Project Name |  | : | Dorchester Hotel (PLOT 18)
Main Contractor |  | : | Khansaheb civil engineering llc
Scope of works |  | : | External Insulation Finishing System (EPS)
EIFS SYSTEM+BUILT UP(400MM) | [17 empty] | MONTH: | October 2022
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
WORK BREAKDOWN: 35%-FRAMING,35%-EPS BOARDS,20%-BASECOAT,10%-PAINT | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | Stair-6,GF to 1 st floor | JOT-AX-SD-GF-00002_02 | Grid-E-H/10-12 | WALL GF |  | 1 | 3.22 | 7.275 | 23.4255 |  | 0 | 0 | 0 | 0 | 23.4255 | 90% | 21.083 | 0 | 21.083
JOT-AX-WR-GF-00086,99
JOT-AX-WR-ML-00110
[14 empty] | TOTAL | 23.4255 |  | 21.083 | 0 | 21.083

## PVC GROOVE
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
PVC Groove | [5 empty] | NO | LENGTH | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | L2 RAMP TO ETS ROOM | JOT-AX-WR-ML-00201_02 | ELEVATION 1 | PVC GROOVE |  | 11 | 3.56 | 39.16 |  | 0 | 0 | 0 | 0 | 60.5 | 100% | 60.5 | 60.5 | 0
| JOT-AX-WR-ML-00054 |  | ELEVATION 2
| JOT-AX-WR-ML-00057 |  | ELEVATION 3
2 | STAIR 6 WALL,Elevation-10 | JOT-AX-SD-L4-00005_02 | E-H/10-12 | WALL L4 |  | 2 | 9.92 | 19.84 | [5 empty] | 19.84 | 100% | 19.84 | 19.84 | 0
JOT-AX-WR-L4-00071
2 | LEVEL-2 PARAPET-BASECOAT | JOT-AX-SD-L4-00004_03 | U-Z/13-15 | PARAPET L2 |  | 6 | 1.4 | 8.4 | [5 empty] | 8.4 | 100% | 8.4 | 8.4 | 0
JOT-AX-WR-L2-00082_00
3 | LEVEL-4,STAIR 6 WALL,Elevation-08 | JOT-AX-SD-L4-00005_02 | E-H/10-12 | WALL L4 |  | 2 | 9.92 | 19.84 | [5 empty] | 19.84 | 100% | 19.84 | 19.84 | 0
JOT-AX-WR-L4-00070_01
4 | GF Ballroom Wall | JOT-AX-SD-GF-00002_02 | A-U/23-25 | WALL GF |  | 4 | 7.28 | 29.12 |  | 0 | 0 | 0 |  | 29.12 | 100% | 29.12 | 0 | 29.12
JOT-AX-WR-ML-00093_00
5 | Residential,stair-6,L2 | JOT-AX-SD-ML-00003_02 | E-H/10-11 | WALL L2 |  | 4 | 7.28 | 29.12 |  | 0 | 0 | 0 |  | 29.12 | 90% | 26.208 | 0 | 26.208
JOT-AX-WR-ML-00110_00
6 | LEVEL-2 PARAPET-BASECOAT | JOT-AX-SD-L4-00004_03 | U-Z/18-22 | WALL L2 |  | 6 | 1.4 | 8.4 |  | 0 | 0 | 0 |  | 8.4 | 100% | 8.4 | 0 | 8.4
JOT-AX-WR-L2-00096_00
[13 empty] | TOTAL | 175.22 |  | 172.308 | 108.58 | 63.728

## EIFS + BUILTUP (300MM)
DETAILED STATUS REPORT
Client Name |  | : | Omniyat Investments & Management LLC
Project Name |  | : | Dorchester Hotel (PLOT 18)
Main Contractor |  | : | Khansaheb civil engineering llc
Scope of works |  | : | External Insulation Finishing System (EPS)
[18 empty] | MONTH: | October 2022
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
EIFS SYSTEM+BUILT UP(300MM)- 35% framing, 35% ESP Boards, 20% Basecoat, 10% Paint | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | STAIR 6 WALL,LEVEL-02 to 3 | JOT-AX-SD-ML-00003_02 | E-H/10-11 | WALL L2 |  | 1 | 9.275 | 7.442 | 69.0246 |  | 0 | 0 | 0 | 0 | 69.0246 | 90% | 62.1221 | 24.1586 | 37.9635
JOT-AX-WR-ML-00085,100,104
2 | Hotel ramp area,Level-1 to lvl-3 | JOT-AX-SD-ML-00004_03 | W/18-22 | WALL L2-3 |  | 0.5 | 26.051 | 2.599 | 33.8533 |  | 0 | 0 | 0 | 0 | 244.8255 | 35% | 85.6889 | 0 | 85.6889
| JOT-AX-WR-ML-00107_00 |  |  |  |  | 1 | 9.975 | 4.014 | 40.0397 |  | 0 | 0 | 0 | 0
[6 empty] | 1 | 7.376 | 26.051 | 192.1522 |  | 1 | 2.795 | 7.592 | 21.2196
3 | Residential area,lvl-2 to lvl-3 | JOT-AX-SD-ML-00003_02 | G/4-7 | WALL L2-3 |  | 1 | 25.135 | 7.037 | 176.875 |  | 0 | 0 | 0 | 0 | 176.875 | 35% | 61.9062 | 0 | 61.9062
JOT-AX-WR-ML-00103_00
[14 empty] | TOTAL | 490.725 |  | 209.7173 | 24.1586 | 185.5587

## EIFS + BUILTUP (400MM)
DETAILED STATUS REPORT
Client Name |  | : | Omniyat Investments & Management LLC
Project Name |  | : | Dorchester Hotel (PLOT 18)
Main Contractor |  | : | Khansaheb civil engineering llc
Scope of works |  | : | External Insulation Finishing System (EPS)
WORK BREAKDOWN : 70% UPTO EPS BOARDS, 20% UPTO BASECOAT, 10% PAINT | [17 empty] | MONTH: | October 2022
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | Progress of work (%) | Workdone (to date) | Workdone (Previous) | Workdone (this month) | REMARKS
EIFS SYSTEM+BUILT UP(400MM)- 35% framing, 35% ESP Boards, 20% Basecoat, 10% Paint | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | Stair-6,GF to 1 st floor | JOT-AX-SD-GF-00002_02 | E-H/10-12 | WALL GF-L1 |  | 1 | 8.477 | 7.275 | 61.6702 |  | 0 | 0 | 0 | 0 | 61.6702 | 90% | 55.5032 | 0 | 55.5032
JOT-AX-WR-GF-00086,99, 110
2 | Residential ,road side,GF to 1 st floor | JOT-AX-SD-ML-00001_02 | G-H/3-8 | WALL GF-L1 |  | 1 | 24.817 | 7.275 | 180.5437 |  | 0 | 0 | 0 | 0 | 180.5437 | 60% | 108.3262 | 0 | 108.3262
JOT-AX-WR-ML-00095,106,105
3 | Residential ,Lobby,GF to 1 st floor | JOT-AX-SD-ML-00001_02 | E-F/6-7 | WALL GF-L1 |  | 1 | 6.694 | 7.28 | 48.7323 |  | 1 | 1 | 1.8 | 1.8 | 46.9323 | 35% | 16.4263 | 0 | 16.4263
JOT-AX-WR-ML-00106_00
4 | RESIDENTIAL,RAMP AREA,GF to Level-3 | JOT-AX-SD-ML-00001_02 | G-D/Y1 | WALL GF-L3 |  | 1 | 11.32 | 11.635 | 131.7082 |  | 2 | 1 | 1.8 | 3.6 | 128.1082 | 35% | 44.8379 | 0 | 44.8379
JOT-AX-WR-ML-00111_00
[14 empty] | TOTAL | 417.2544 |  | 225.0935 | 0 | 225.0935

## EIFS - PARAPET
NO | BUILDING | DRAWING REF. NO | LOCATION | ITEM NAMES | ID NO. (In the Drawing) | GROSS AREA (Sqm) |  |  |  | DEDUCTION ITEM NAME | DEDUCTIONS (Sqm) |  |  |  | NET AREA / TOTAL AREA TO DATE (SqM) | PROGRESS % | WORK DONE TO DATE | PREVIOUS MONTH PROGRESS | CURRENT MONTH PROGRESS
EIFS BUILDUP FOR L29 PARAPET, EPS BOARD | [5 empty] | NO | LENGTH | HEIGHT | AREA |  | NO | LENGTH | HEIGHT | AREA |  |  |  |  | (Sqm)
1 | L4, PARAPET | JOT-AX-SD-L4-00005_02 | W-X/13-16 | WALL L4 | BO23 | 1 | 25.15 | 1.4 | 35.21 |  | 0 | 0 | 0 | 0 | 35.21 | 100% | 35.21 | 35.21 | 0
JOT-AX-WR-L4-00036
2 | L4, PARAPET | JOT-AX-SD-L4-00005_02 | X-Q/23-24 | PARAPET L4 |  | 1 | 28.9 | 1.4 | 40.46 |  | 0 | 0 | 0 | 0 | 40.46 | 100% | 40.46 | 40.46 | 0
JOT-AX-WR-L4-00073
3 | L2 PARAPET, ROADSIDE | JOT-AX-SD-L2-00004_03 | U-Z/13-22 | PARAPET L2, INSULATION |  | 1 | 86.03 | 1.4 | 120.44 |  | 0 | 0 | 0 | 0 | 120.4378 | 100% | 120.4378 | 84.3065 | 36.1313
JOT-AX-WR-L2-00078_00
JOT-AX-WR-L2-00084_00
JOT-AX-WR-L2-00078,82,84,92,96,109
4 | L2 PARAPET, ROADSIDE | JOT-AX-SD-L2-00004_03 | U-Z/13-22 | PARAPET L2, BASE COAT |  | 1 | 25 | 1.4 | 35 |  | 0 | 0 | 0 | 0 | 35 | 20% | 7 | 7 | 0
JOT-AX-WR-L2-00082_00
4 | L4 PARAPET, ROADSIDE | JOT-AX-SD-L4-00005_02 | G-X / 11-16 | PARAPET L4, PAINT |  | 1 | 23.19 | 1.4 | 32.47 |  | 0 | 0 | 0 | 0 | 32.47 | 20% | 6.494 | 6.494 | 0
JOT-AX-WR-L2-00075_00
4 | L4 PARAPET,RESIDENTIAL | JOT-AX-SD-L4-00005_02 | W-X/15-17 | WALL,L4 |  | 1 | 2.877 | 1.4 | 4.0278 |  | 0 | 0 | 0 | 0 | 4.0278 | 70% | 2.8195 | 0 | 2.8195
JOT-AX-WR-L4-00089,97
[14 empty] | TOTAL | 267.6056 |  | 212.4213 | 173.4705 | 38.9508