## TAX_INVOICE (hidden)
TWIC
INSULATION MATERIALS SUPPLY
M/s TWIC INSULATION MATERIALS SUPPLY LLC
PROGRESS CLAIM - PROFORMA INVOICE
To, |  |  |  |  | Invoice # | 391
M/s KHANSAHEB CIVIL ENGINEERING L.L.C. |  |  |  |  | Invoice Date | 2023-01-30
AL RASHIDIYA |  |  |  |  | Due Date | 2023-03-30
P.O. BOX 2716, Dubai |  |  |  |  | Certificate #
UNITED ARAB EMIRATES |  |  |  |  | Valuation Month | 2023-01-01
Phone : +9714-6057200 |  |  |  |  | Contract | LOI 201A22002/SW/ARM/163
VAT TRN | '100240059400003 |  |  |  | CLIENT (KCE) VAT TRN | 100240059400003
[5 empty] | TWIC VAT TRN | '100315259000003
[5 empty] | Nature of Work | Epoxy Resin and Dust Sealer
Particulars |  |  |  | Contract Amount | Certified Previous AED | Claimed Current AED (December 2022) | Total Claimed AED
Value of Work Done - Dorchester Hotel & Residences at Plot 18
Work Done To Date (A) |  |  |  | 1183329.41 | 307520.1196 | 111653.0272 | 419173.1468
Less: Advance Recovery
Total (Net of Advances Recovery)
Less : Retention |  | Rate | 10% |  | 30752.012 | 11165.3027 | 41917.3147
Net Certified (Excl. VAT) |  |  |  |  | 276768.1077 | 100487.7245 | 377255.8322
VAT Amount |  | Rate | 5% |  | 13838.4054 | 5024.3862 | 18862.7916
Payment Due (Incl. VAT) |  |  |  |  | 290606.513 | 105512.1107 | 396118.6238
Total Previously released | [6 empty] | 290606.513
Total Payable (AED) Inclusive of VAT | [6 empty] | 105512.1107
UAE Dirhams One Hundred Eight Thousand Four Hundred Fifty and Sixteen fils
TWIC Insulation Materials Supply LLC
PO BOX 20496, Dubai , United Arab Emirates, Phone : +971-4-5807877
Email : projects@triconconstruction.ae / twic@eim.ae
[5 empty] | Cheque Payable to: | TWIC INSULATION MATERIALS SUPPLY LLC
[5 empty] | Bank Transfer to: | Bank Name : RAKBANK
Bank address : MAKTOUM STREET, DUBAI
Account Currency :AED
Account No. 0024 529591 001
Swift Address: NRAKAEAK
IBAN : AE81 0400 0002 4296 2063 001
For: TWIC INSULATION MATERIALS SUPPLY LLC

## Summary
No | Description | Previous Amount | This Month Amount | Cumulative Amount
| Work done | 299037.05 | 120136.0968 | 419173.1468

## BOQ January 2023
PROJECT : DORCHESTER PLOT BB.B03.018, BUSINESS BAY, DUBAI - UAE
Main Contractor : KHANSAHEB
Sub Contractor : TWIC INSULATION
Subject : EPOXY, RESIN AND DUST SEALER FLOORING SYSTEM
PERIOD : JANUARY 2023
PROJECT BOQ SUMMARY SHEET
Item | ITEM DESCRIPTION | SUBCONTRACT SUM |  |  |  | TWIC INVOICE
[6 empty] | TOTAL QUANTITY |  |  | work done (%) | AMOUNT (AED)
|  | BOQ QTY | Unit | Cost Rate (AED) | Amount (AED) | Previous | Current | Total |  | Previous | Current (January 2023) | Total
EPOXY, RESIN AND DUST SEALER FLOORING SYSTEM
GROUND LEVEL TO ROOF LEVEL
2A | Anti Static Epoxy floor paint, in Electrical rooms (PA06) | 65 | M² | 36 | 2340 |  | 0 | 0 | 0% | 0 | 0 | 0
|  | 310 | 1 COAT | 18 | 5580
2B | Heavy duty solvent free Dust Sealer floor paint directly on concrete finish, in IT/Telecom rooms (PA03) | 10 | M² | 14 | 0 |  |  | 0 | 0% | 0 | 0 | 0
2C | Heavy duty solvent free Dust Sealer floor paint directly on concrete finish, in Plant rooms & Store (PA03) | 6677 | M² | 14 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0
D | Skirting
2D | Anti Static Epoxy Skirting, in Electrical rooms (PA06) | 84 | Mtr. | 14 | 1176 | 0 | 0 | 0 | 0% | 0 | 0 | 0
|  | 447 | 1 COAT | 7 | 3129
2E | Heavy duty solvent free Dust Sealer Skirting, in IT/Telecom rooms (PA03) | 12 | Mtr. | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
2F | Heavy duty solvent free Dust Sealer Skirting, in Plant rooms & Store (PA03) | 3651 | Mtr. | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0
EPOXY, RESIN AND DUST SEALER FLOORING (CONT'D)
Staircase Finishes
3A | Heavy duty solvent free Dust Sealer floor paint directly on concrete finish, in all Staircase (PA.03) | 5846 | M² | 14 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0
Car Parking Finishes
3B | Dust sealer applied direct to power float concrete floor finish within all car park areas (PA.01) | 6000 | M² | 14 | 84000 | 0 | 0 | 0 | 0% | 0 | 0 | 0
0
Car Park Markings
3C | Hot applied Rommco thermosetting plastic traffic coating system in car parking lines to engineer and authority approval | 500 | Mtr. | 10 | 5000 | 0 | 0 | 0 | 0% | 0 | 0 | 0
0
3D | Ditto, in single head directional arrows | 34 | Nos | 50 | 1700 | 0 | 0 | 0 | 0% | 0 | 0 | 0
0
3E | Ditto, in double head directional arrows | 3 | Nos | 50 | 150 | 0 | 0 | 0 | 0% | 0 | 0 | 0
3F | Ditto, in car park numbering comprising up to 3 digits painted on floors | 245 | Nos | 55 | 13475 |  | 0 | 0 | 0% | 0 | 0 | 0
3G | Ditto, in handicap sign to floor | 9 | Nos | 75 | 675 |  |  | 0 | 0% | 0 | 0 | 0
3H | Ditto, in road marking stripe (buffer zones) Curb Paint | 500 | Mtr. | 20 | 10000 | 0 | 0 | 0 | 0% | 0 | 0 | 0
Curb Paint
3J | Curb paint (M60/182) | 640 | Mtr. | 8 | 5120 | 0 | 0 | 0 | 0% | 0 | 0 | 0
Total Amount for Original Scope of Works in AED |  |  |  |  | 132345 |  |  |  |  | 0 | 0 | 0
VARIATION ITEMS
EPOXY, RESIN AND DUST SEALER FLOORING SYSTEM (CONT'D)
B2 TO ROOF LEVEL
6B | Supply and application of Mastertop 1205 epoxy floor coating at Plant rooms & Store Based on SI-000243 | 5035 | M² | 36 | 181260 | 1559.0435 | 336.6584 | 1895.7019 | 37.65% | 56125.5664 | 12119.7025 | 68245.269
| ONE COAT | 1989 | M² | 18 | 35802 | 0 | 0 | 0 | 0% | 0 | 0 | 0
D | Skirting
6D | Supply and application of Mastertop 1205 epoxy floor coating at Plant rooms & Store Based on SI-000243 | 3506 | Mtr. | 12 | 42072 | 1151.5039 | 106.0712 | 1257.5751 | 35.87% | 13818.0463 | 1272.8547 | 15090.901
| ONE COAT | 1480 | Mtr. | 6 | 8880 | 0 | 0 | 0 | 0% | 0 | 0 | 0
EPOXY, RESIN AND DUST SEALER FLOORING (CONT'D)
Staircase Finishes
7A | Supply and application of Mastertop 1205 epoxy floor coating to concrete finish, in all Staircase Based on SI-000145 | 1361 | M² | 36 | 48996 | 91.45 | 869.62 | 961.07 | 70.61% | 3292.2 | 31306.32 | 34598.52
| ONE COAT | 3170 | M² | 18 | 57060 | 96.37 | 0 | 96.37 | 3.04% | 1734.66 | 0 | 1734.66
| RETOUCH | 675 | M² | 18 | 12150
SubTotal Amount for VARIATION Scope of Works in AED |  |  |  |  | 386220 |  |  |  |  | 74970.4727 | 44698.8772 | 119669.35
ADDITIONAL WORKS: EI 11 K129 SK dm 204 from 201A22002 Kitchen Scope Floor Finishes
EPOXY, RESIN AND DUST SEALER FLOORING (CONT'D)
RESIN FLOORING
Fondue Scope (KITCHEN AREAS)
8B | Fully sealed, seamless self - levelling resin system; including 100mm seamless cove to all surrounding wall faces. (UCRETE MF 4MM THICK) | 1681.05 | M² | 155 | 260562.75 | 866.0226 | 12.29 | 878.3126 | 52.25% | 134233.5064 | 1904.95 | 136138.4564
8C | Supply and application of Nitocote HT120 epoxy floor coating to floor areas | 160 | M² | 45 | 7200 | 191.06 | 25.21 | 241.48 | 150.9% | 8597.7 | 1134.45 | 9732.15
Skirting
8D | Supply and application of 100mm high skirting at areas where Ucrete flooring is applied at floor areas (UCRETE RG 4MM THICK) | 1775.48 | Mtr. | 46 | 81672.08 | 759.6026 | 13.55 | 773.1526 | 43.55% | 34941.7204 | 623.3 | 35565.0204
8E | Supply and application of Nitocote HT120 skirting to 100mm high where Nitocote HT120 used at floor areas | 150 | Mtr. | 14 | 2100 | 202.28 | 27.225 | 256.73 | 171.2% | 2831.92 | 381.15 | 3213.07
Total Amount for Kitchen related flooring Works in AED |  |  |  |  | 351534.83 |  |  |  |  | 180604.8469 | 4043.85 | 184648.6969
ADDITIONAL WORKS: E11-K129-SK-AK-575 - Carpark Traffic Deck Coating & Floor Marking
9 | Carpark Traffic Coating & Floor Marking
9A | Carpark floor grinding & filling works | 12000 | M² | 3 | 36000 | 0 | 2097.01 | 2097.01 | 17.48% | 0 | 6291.03 | 6291.03
9B | Levelling works using heavy duty grinder and partial filling to remove undulations and provides mooth level surface | 1530 | M² | 12 | 18360 | 0 | 0 | 0 | 0% | 0 | 0 | 0
9C | Internal Driveways: Supply & Application of Flowcoat SF150 Epoxy colour RAL 7042 Rough to driveways | 8000 | M² | 30 | 240000 | 0 | 1160.76 | 1160.76 | 14.51% | 0 | 34822.8 | 34822.8
9D | Internal Parking Bays: Supply & Application of Flowcoat SF150 Epoxy colour RAL 7012 Rough to parking bays | 10000 | M² | 30 | 300000 |  | 936.25 | 936.25 | 9.363% |  | 28087.5 | 28087.5
9E | Internal Ramps: Supply & Application of Flowcoat SF150 Epoxy colour RAL 7042 Rough to internal ramps | 532 | M² | 30 | 15960 | 0 | 0 | 0 | 0% | 0 | 0 | 0
9F | Exposed ramps: Supply & Application of DECKSHIELD ED Polyurethane colour RAL 7042 Rough to external / exposed to sunlight ramps | 1050 | M² | 95 | 99750 | 0 | 0 | 0 | 0% | 0 | 0 | 0
9G | Supply and application of Parking space line marking & numbering, driveway arrows, hatching, all in white colour | 1 | LS | 54000 | 54000 | 0 | 0.1 |  | 10%
Total Amount for Carpark Traffic Coating Works in AED |  |  |  |  | 764070 |  |  |  |  | 0 | 62910.3 | 62910.3
| Historical debts from Roberts JV as agreed with OMNIYAT | 1 | LS | 51944.8 | 51944.8 |  |  |  |  | 51944.8 |  | 51944.8
Combined Total Amount in AED |  |  |  |  | 1686114.63 |  |  |  |  | 307520.1196 | 111653.0272 | 419173.1468
Note on H87: Himal Kosala: only 50%, no supporting or measurement sheet
Note on H93: Himal Kosala: only 50%, no supporting or measurement sheets

## CUMULATIVE EPOXY TO BOH ROOMS
PROJECT NAME: DORCHESTER COLLECTION AT Plot 18, Plot BB. B03.018, Dubai
Head Contractor : KHANSAHEB CIVIL ENGINEERING
Sub Contractor : TWIC INSULATION | [6 empty] | FINAL COAT DONE UNDER KCE
Scope : EPOXY FLOOR COATING AT BOH ROOMS - JANUARY 2023
HOTEL EPOXY FLOOR COATING TO BOH ROOMS | [5 empty] | TOTAL |  | PREVIOUSLY COMPLETED |  | JAN. 2023 Current month |  | CUMULATIVE COMPLETION
SI. | LEVEL | ROOM | NAME |  |  | AREA (m2) | SKIRTING (m) | AREA | SKIRTING | AREA | SKIRTING | AREA | SKIRTING
1 | B2 | P-B2-032 | ROOM SERVICE SUPPORT AREA | 24254999.6065 | 21699.9998 | 24.255 | 21.7 | 24.255 | 21.7 |  |  | 24.255 | 21.7
2 | B2 |  | STAIR-1 CORRIDOR | 29463664.1439 | 42592.8862 | 29.4637 | 42.5929 | 29.4637 | 42.5929 |  |  | 29.4637 | 42.5929
3 | B1 | P-B1-007 | GREASE TRAP | 29155832.3261 | 27385.1045 | 28.89 | 26.94 | 28.89 | 26.94
4 | B1 | P-B1-008 | LIFT LOBBY | 23333521.5575 | 23106.7783 | 23.3335 | 23.1068 | 23.3335 | 23.1068 |  |  | 23.3335 | 23.1068
5 | B1 | P-B1-010 | CEFROOM 5 | 43788711.7798 | 24683.6416 | 43.7887 | 24.6836 | 43.7887 | 24.6836
6 | B1 | P-B1-012 | FRESH AIR PLENUM | 38430767.7395 | 24628.3941 | 38.4308 | 24.6284 | 38.4308 | 24.6284
7 | B1 | P-B1-013 | WATER FILTRATION PUMP ROOM | 112051849.3025 | 53833.1453 | 112.0518 | 53.8331 | 112.0518 | 53.8331
8 | B1 | P-B1-011 | VENTILATION SHAFT | 50017842.5049 | 44991.186 | 50.0178 | 44.9912 |  |  |  |  | 0 | 0
9 | B1 | P-B1-088 | FF LOBBY | 5020519.5497 | 9450.3442 | 5.0205 | 9.4503 | 5.0205 | 9.4503 |  |  | 5.0205 | 9.4503
10 | B1 | P-B1-090 | MECH ROOM | 3231223.4512 | 7450.5061 | 3.2312 | 7.4505 | 3.2312 | 7.4505 |  |  | 3.2312 | 7.4505
11 | B1 | P-B1-093 | ELECTRICAL ROOM | 7368812.9668 | 8602.1434 | 7.3688 | 8.6021 | 0 | 0 |  |  | 0 | 0
12 | B1 | P-B1-094 | FTR | 6118018.37 | 7250.2417 | 6.118 | 7.2502 | 6.118 | 7.2502 |  |  | 6.118 | 7.2502
13 | B1 |  | LOADING BAY | 84987884.9848 | 23002.2147 | 84.9879 | 23.0022 | 84.9879 | 23.0022 |  |  | 84.9879 | 23.0022
14 | B1 | P-B1-098 | GENERATOR ROOM | 62919541.7183 | 43342.8115 | 62.9195 | 43.3428 | 0 | 0 |  |  | 0 | 0
15 | B1 | P-B1-099 | EA PLENUM ROOM | 35046604.683 | 26916.9756 | 35.0466 | 26.917 | 0 | 0
16 | B1 | P-B1-100 | FAN PUMP ROOM | 33898473.7331 | 26672.5773 | 33.8985 | 26.6726 | 33.8985 | 26.6726 |  |  | 33.8985 | 26.6726
17 | B1 | P-B1-101 | FUEL TANK | 12300000 | 14200 | 12.3 | 14.2 | 0 | 0 |  |  | 0 | 0
18 | B1 | P-B1-104 | BOILER ROOM | 78035296.4167 | 33158.6237 | 78.0353 | 33.1586 |  |  |  |  | 0 | 0
19 | B1 | P-B1-106 | CEF ROOM 6 | 44553589.8513 | 25429.8405 | 44.5536 | 25.4298 | 0 | 0 |  |  | 0 | 0
20 | B1 | P-B1-110 | PUMB ROOM W.F | 45319904.0561 | 30511.0663 | 45.3199 | 30.5111 | 0 | 0 |  |  | 0 | 0
21 | B1 | P-B1-113 | IRRIGATION TANK & PUMP ROOM | 38884864.4047 | 20634.1883 | 38.8849 | 20.6342 | 0 | 0 |  |  | 0 | 0
22 | B1 | P-B1-115 | CEF ROOM 4 | 58220892.6724 | 31075.2044 | 58.2209 | 31.0752 | 0 | 0 |  |  | 0 | 0
23 | B1 | P-B1-116 | EA PLENUM ROOM 3 | 20369225.8877 | 19706.5936 | 20.3692 | 19.7066 | 0 | 0 |  |  | 0 | 0
24 | B1 | P-B1-120 | WM | 2625832.207 | 5503.7846 | 2.6258 | 5.5038 |  |  |  |  | 0 | 0
25 | B1 | P-B1-123 | STAIR-1 CORRIDOR | 19128717.1295 | 28281.0637 | 19.1287 | 28.2811 | 19.1287 | 28.2811 |  |  | 19.1287 | 28.2811
26 | B1 | P-B1-135 | ELECTRICAL ROOM | 4536000.0031 | 4980 | 4.536 | 4.98 |  |  |  |  | 0 | 0
27 | B1 | P-B1-138 | FTR | 18270000.0003 | 16411.3789 | 18.27 | 16.4114 |  |  |  |  | 0 | 0
28 | B1 | P-B1-143 | BALANCING TANK | 12669053.9773 | 14326.1768 | 12.6691 | 14.3262 |  |  | 12.6691 | 14.3262 | 12.6691 | 14.3262
29 | B1 |  | STAIR 2 CORRIDOR AND RAMP | 11871441.4807 | 4539.2052 | 11.92 | 3.92 | 11.92 | 3.92 |  |  | 11.92 | 3.92
30 | B1 |  | RECYCLING CORRIDOR AND RAMP | 36539471.0754 | 17758.2418 | 36.5395 | 17.7582
31 | B1 |  | STAIR 5 CORRIDOR AND RAMP | 25921643.2425 | 12932.8297 | 25.9216 | 12.9328 |  |  |  |  | 0 | 0
32 | B1 |  | STAIR 6 CORRIDOR AND RAMP | 8912926.2246 | 2527.9953 | 8.9129 | 2.528 |  |  |  |  | 0 | 0
33 | B1 |  | FAN ROOM CORRIDOR AND RAMP | 25290335.2506 | 13050.5984 | 25.2903 | 13.0506
34 | B1 |  | RECEVING RAMP | 3594373.8115 | 1786.0432 | 3.5944 | 1.786
35 | B1 |  | WASTE ROUTE CORRIDOR AND RAMP | 30477637.9851 | 8661.2097 | 30.4776 | 8.6612 |  |  |  |  | 0 | 0
36 | G | P-GF-001 | SECURITY & EQUIPMENT ROOM | 11346490.8131 | 13183.3232 | 11.3465 | 13.1833 |  |  |  |  | 0 | 0
37 | G | P-GF-002 | CORRIDR | 28263999.4805 | 34769.9994 | 28.264 | 34.77 |  |  |  |  | 0 | 0
38 | G | P-GF-003 | ETS ROOM | 151337912.238 | 52843.8496 | 151.3379 | 52.8438 |  |  |  |  | 0 | 0
39 | G | P-GF-004 | BOH CIRCULATION | 16799576.8371 | 19100.0006 | 16.7996 | 19.1 |  |  |  |  | 0 | 0
40 | G | P-GF-005 | ETS CONTROL | 4000000 | 8000 | 4 | 8 |  |  |  |  | 0 | 0
41 | G | P-GF-006 | PRESSURE | 13440866.6322 | 14767.8638 | 13.4409 | 14.7679 |  |  |  |  | 0 | 0
42 | G | P-GF-014 | WM ROOM | 3579271.5543 | 7591.7836 | 3.5793 | 7.5918 |  |  |  |  | 0 | 0
43 | G | P-GF-015 | FF LOBBY | 13074160.9455 | 16209.8108 | 13.98 | 11.82 | 13.98 | 11.82 |  |  | 13.98 | 11.82
44 | G | P-GF-017 | SERVICE CORR / HOUSEKEEPING LOBBY | 9657686.9822 | 15084.0106 | 9.6577 | 15.084 |  |  |  |  | 0 | 0
45 | G | P-GF-021 | GSM / KITCHEN EXTRACT | 6619368.9513 | 10307.7727 | 6.6194 | 10.3078 |  |  |  |  | 0 | 0
46 | G | P-GF-022 | FF LOBBY | 5102444.2757 | 9499.9998 | 5.1024 | 9.5 |  |  |  |  | 0 | 0
47 | G | P-GF-037 | SUBSTATION | 237449293.6728 | 62637.8114 | 237.4493 | 62.6378
48 | G | P-GF-041 | EGRESS CIRCULATION | 17817294.5883 | 18139.0358 | 17.8173 | 18.139 |  |  |  |  | 0 | 0
49 | G | P-GF-042 | LV ROOM APARTMENT | 118464630.6696 | 44758.6402 | 118.4646 | 44.7586 | 0 | 0 |  |  | 0 | 0
50 | G | P-GF-054 | LV ROOM HOTEL | 121929367.8543 | 47325.3875 | 121.9294 | 47.3254 | 0 | 0 |  |  | 0 | 0
51 | G | P-GF-055 | EGRESS CIRCULATION | 27686517.9252 | 42240.1706 | 27.6865 | 42.2402 |  |  |  |  | 0 | 0
52 | G | P-GF-071 | BREECHING INLET | 1105369.0361 | 4300.5677 | 1.5 | 5.23 | 1.5 | 5.23
53 | G | P-GF-056 | FTR ROOM | 17603747.2268 | 20163.3119 | 17.6037 | 20.1633 |  |  |  |  | 0 | 0
54 | G | P-GF-072 | FIRE COMMAND CENTER | 19164999.9989 | 19700 | 19.165 | 18.8 | 19.165 | 18.8 |  |  | 19.165 | 18.8
55 | G | P-GF-080 | FTR | 2117200.1861 | 5840.0002 | 2.1172 | 5.84 |  |  |  |  | 0 | 0
56 | L1 | P-01-002 | PLANT | 19979431.8111 | 23537.3429 | 19.9794 | 23.5373 | 19.9794 | 23.5373
57 | L1 | P-01-003 | PLANT | 9261769.1815 | 13666.8222 | 9.2618 | 13.6668 | 9.2618 | 13.6668
58 | L1 | P-01-006 | MECH ROOM | 3289999.9994 | 7500 | 3.29 | 7.5 | 0 | 0 |  |  | 0 | 0
59 | L1 | P-01-010 | LIFT LOBBY | 12305071.9048 | 15303.7261 | 12.3051 | 15.3037 | 0 | 0 |  |  | 0 | 0
60 | L1 | P-01-013 | PR CORRIDOR | 15784809.9721 | 20603.4618 | 15.7848 | 20.6035 |  |  |  |  | 0 | 0
61 | L1 |  | FF LOBBY | 5019944.0644 | 6118.7779 | 5.0199 | 6.1188 |  |  |  |  | 0 | 0
62 | L1 | P-01-016 | DIMMER ROOM | 4751738.9017 | 9923.7233 | 2.47 | 4.65 | 2.47 | 4.65 |  |  | 2.47 | 4.65
63 | L1 | P-01-018 | PLANT ROOM | 305063148.0445 | 89992.7027 | 305.0631 | 89.9927 | 0 | 0 |  |  | 0 | 0
64 | L1 | P-01-021 | FTR | 6120000.0001 | 6354.4817 | 6.12 | 6.3545 |  |  |  |  | 0 | 0
65 | L1 | P-01-022 | ELECTRICAL ROOM | 6126472.9587 | 5296.4044 | 6.1265 | 5.2964 |  |  |  |  | 0 | 0
66 | L1 | P-01-024 | STORE | 3289999.9994 | 7500 | 3.29 | 7.5 |  |  |  |  | 0 | 0
67 | L2 | P-02-004 | FF LOBBY | 13092924.908 | 16229.3021 | 13.99 | 10.71 | 13.99 | 10.71 |  |  | 13.99 | 10.71
68 | L2 | P-02-005 | WM ROOM | 2977242.159 | 6902.6399 | 1.9 | 3.04 | 1.9 | 3.04 |  |  | 1.9 | 3.04
69 | L2 | P-02-006 | HOUSEKEEPING LOBBY | 9624999.9987 | 15060 | 9.91 | 12.25 | 9.91 | 12.25
70 | L2 | P-02-066 | TELECOM ROOM | 1349660.064 | 2250.8486 | 1.3497 | 2.2508 |  |  |  |  | 0 | 0
71 | L2 | P-02-009 | ELECTRICAL ROOM | 4895085.4354 | 5784.8543 | 4.8951 | 5.7849 |  |  |  |  | 0 | 0
72 | L2 | P-02-013 | FF ROOM | 4988689.9152 | 9475.1258 | 4.9887 | 9.4751 |  |  |  |  | 0 | 0
73 | L2 | P-02-016 | MECH ROOM | 3289999.9994 | 7500 | 2.47 | 4.65 | 2.47 | 4.65 |  |  | 2.47 | 4.65
74 | L2 | P-02-039 | ELECTRICAL ROOM | 6126472.9587 | 5296.4044 | 6.1265 | 5.2964 | 6.1265 | 5.2964 |  |  | 6.1265 | 5.2964
75 | L2 | P-02-043 | FTR | 6120047.6896 | 7250.106 | 6.12 | 7.2501 | 6.12 | 7.2501 |  |  | 6.12 | 7.2501
76 | L2 | P-02-027 | CORRIDOR | 22437810.2279 | 27859.9571 | 22.4378 | 27.86 |  |  |  |  | 0 | 0
77 | L3 | P-03-001 | MEP CORRIDOR | 23133189.5442 | 32572.1955 | 23.1332 | 32.5722 |  |  |  |  | 0 | 0
78 | L3 | P-03-002 | POOL PLANT | 104633062.6532 | 49129.3405 | 104.6331 | 49.1293 |  |  |  |  | 0 | 0
79 | L3 | P-03-006 | AHU FOR RETAIL / F&B UNITS & ADJACENT ROOM | 126772510.7479 | 43586.3417 | 126.7725 | 43.5863 | 0 | 0 |  |  | 0 | 0
80 | L3 | P-03-008 | WM ROOM | 3586702.4134 | 7599.0218 | 1.9 | 3.04 | 1.9 | 3.04
81 | L3 | P-03-009 | FF LOBBY | 13109250.0008 | 16229.8108 | 13.99 | 10.71 | 13.99 | 10.71
82 | L3 | P-03-023 | ELECTRICAL ROOM | 6068417.8914 | 5203.3494 | 6.0684 | 5.2033 | 6.0684 | 5.2033 |  |  | 6.0684 | 5.2033
83 | L3 | P-03-024 | FTR | 6445247.8916 | 8610.8049 | 6.4452 | 8.6108 | 6.4452 | 8.6108 |  |  | 6.4452 | 8.6108
84 | L3 | P-03-027 | PLANT SPACE | 82279384.1144 | 57085.6922 | 82.2794 | 57.0857 |  |  |  |  | 0 | 0
85 | L3 | P-03-028 | CORRIDOR | 23133216.2309 | 32572.2762 | 23.1332 | 32.5723 |  |  |  |  | 0 | 0
86 | L3 | P-03-030 | MEP | 16586363.6961 | 25134.6428 | 16.5864 | 25.1346 |  |  |  |  | 0 | 0
87 | L3 | P-03-115 | FF LOBBY | 5006197.9279 | 9452.359 | 5.0062 | 9.4524 |  |  |  |  | 0 | 0
88 | L4 | P-04-003 | FF LOBBY | 13990386.9671 | 16210.0159 | 13.9904 | 10.71 | 0 | 0 |  |  | 0 | 0
89 | L4 | P-04-005 | WM ROOM | 2474976.0996 | 6299.9681 | 1.9 | 3.04 | 1.9 | 3.04 |  |  | 1.9 | 3.04
90 | L4 | P-04-007 | FTR | 1835432.0926 | 5422.3097 | 1.82 | 4.3 | 1.82 | 4.3 |  |  | 1.82 | 4.3
91 | L4 | P-04-011 | STO. | 17711951.005 | 18060.0249 | 18.81 | 17.67 | 18.81 | 17.67 |  |  | 18.81 | 17.67
92 | L4 | P-04-039 | HOUSEKEEPING LOBBY | 9914313.0115 | 15120.1349 | 9.9143 | 12.24 | 9.9143 | 12.24 |  |  | 9.9143 | 12.24
93 | L5 | P-05-007 | PLANT | 394489769.5712 | 133616.905 | 394.4898 | 133.6169 | 266.7 | 77.47 |  |  | 266.7 | 77.47
94 | L5 | P-05-008 | PLANT | 375788026.3847 | 132285.384 | 375.788 | 132.2854 | 220.98 | 68.14 |  |  | 220.98 | 68.14
95 | L5 | P-05-001 | FF LOBBY | 13990386.9671 | 16210.0159 | 13.9904 | 10.81 | 13.9904 | 10.81 |  |  | 13.9904 | 10.81
96 | L5 | P-05-011 | LIFT LOBBY (INSIDE RT CORE) | 27838817.1635 | 23799.8484 | 27.8388 | 17.4 | 27.8388 | 17.4 |  |  | 27.8388 | 17.4
97 | L5 | P-05-002 | WM ROOM | 2474970.5229 | 6299.9614 | 1.9 | 3.04 | 1.9 | 3.04 |  |  | 1.9 | 3.04
98 | L5 | P-05-019 | HOUSEKEEPING LOBBY | 9914313.0115 | 15120.1349 | 9.34 | 9.72 | 9.34 | 9.72 |  |  | 9.34 | 9.72
99 | L5 | P-05-017 | SERVICE CORR. | 9934937.2852 | 15124.3663 | 9.91 | 12.15 | 9.91 | 12.15 |  |  | 9.91 | 12.15
100 | L5 | P-05-020 | FF LOBBY | 5544827.8423 | 10441.5788 | 5.6 | 6.97 | 5.6 | 6.97 |  |  | 5.6 | 6.97
101 | L7 |  | FF LOBBY | 5019975.2718 | 5901.4583 | 5.02 | 5.9015 |  |  |  |  | 0 | 0
102 | L7 |  | FTR | 6099550.8363 | 7235.8856 | 6.0996 | 7.2359 | 0 | 0 |  |  | 0 | 0
103 | L7 |  | ELECTRICAL ROOM | 7700810.0179 | 10314.0693 | 7.7008 | 10.3141 | 0 | 0 |  |  | 0 | 0
104 | L8 | H-08-003 | MECH ROOM | 2572540.5687 | 4777.1234 | 2.5725 | 4.7771 | 2.5725 | 4.7771 |  |  | 2.5725 | 4.7771
105 | L8 |  | FF LOBBY | 5019975.2718 | 5901.4583 | 5.02 | 5.9015 | 5.02 | 5.9015 |  |  | 5.02 | 5.9015
106 | L8 |  | FTR | 6099550.8363 | 7235.8856 | 6.0996 | 7.2359 | 0 | 0 |  |  | 0 | 0
107 | L8 |  | ELECTRICAL ROOM | 7700810.0179 | 10314.0693 | 7.7008 | 10.3141 | 0 | 0 |  |  | 0 | 0
108 | L9 | H-09-003 | MECH ROOM | 2572540.5687 | 4777.1234 | 2.5725 | 4.7771 | 2.5725 | 4.7771 |  |  | 2.5725 | 4.7771
109 | L9 |  | FF LOBBY | 5019975.2718 | 5901.4583 | 5.02 | 5.9015 | 5.02 | 5.9015 |  |  | 5.02 | 5.9015
110 | L9 |  | FTR | 6099550.8363 | 7235.8856 | 6.0996 | 7.2359 | 0 | 0 |  |  | 0 | 0
111 | L9 |  | ELECTRICAL ROOM | 7700810.0179 | 10314.0693 | 7.7008 | 10.3141 | 0 | 0 |  |  | 0 | 0
112 | L10 | H-10-003 | MECH ROOM | 2572540.5687 | 4777.1234 | 2.5725 | 4.7771 | 2.5725 | 4.7771 |  |  | 2.5725 | 4.7771
113 | L10 |  | FF LOBBY | 5019975.2718 | 5901.4583 | 5.02 | 5.9015 | 5.02 | 5.9015 |  |  | 5.02 | 5.9015
114 | L10 |  | FTR | 6099550.8363 | 7235.8856 | 6.0996 | 7.2359 | 0 | 0 |  |  | 0 | 0
115 | L10 |  | ELECTRICAL ROOM | 7700810.0179 | 10314.0693 | 7.7008 | 10.3141 | 0 | 0 |  |  | 0 | 0
116 | L11 | H-11-003 | MECH ROOM | 2572540.5687 | 4777.1234 | 2.5725 | 4.7771 | 2.5725 | 4.7771 |  |  | 2.5725 | 4.7771
117 | L11 |  | FF LOBBY | 5019975.2718 | 5901.4583 | 5.02 | 5.9015 | 5.02 | 5.9015 |  |  | 5.02 | 5.9015
118 | L11 |  | FTR | 6099550.8363 | 7235.8856 | 6.0996 | 7.2359 | 0 | 0 |  |  | 0 | 0
119 | L11 |  | ELECTRICAL ROOM | 7700810.0179 | 10314.0693 | 7.7008 | 10.3141 | 0 | 0 |  |  | 0 | 0
120 | L12 | H-12-003 | MECH ROOM | 2572540.5687 | 4777.1234 | 2.5725 | 4.7771 | 2.5725 | 4.7771 |  |  | 2.5725 | 4.7771
121 | L12 |  | FF LOBBY | 5019975.2718 | 5901.4583 | 5.02 | 5.9015 | 5.02 | 5.9015 |  |  | 5.02 | 5.9015
122 | L12 |  | FTR | 6099550.8363 | 7235.8856 | 6.0996 | 7.2359 | 0 | 0 |  |  | 0 | 0
123 | L12 |  | ELECTRICAL ROOM | 7700810.0179 | 10314.0693 | 7.7008 | 10.3141 | 0 | 0 |  |  | 0 | 0
124 | L13 | H-13-003 | MECH ROOM | 2572540.5687 | 4777.1234 | 2.5725 | 4.7771 | 2.5725 | 4.7771 |  |  | 2.5725 | 4.7771
125 | L13 |  | FF LOBBY | 5019975.2718 | 5901.4583 | 5.02 | 5.9015 | 5.02 | 5.9015 |  |  | 5.02 | 5.9015
126 | L13 |  | FTR | 6099550.8363 | 7235.8856 | 6.0996 | 7.2359 | 0 | 0 |  |  | 0 | 0
127 | L13 |  | ELECTRICAL ROOM | 7700810.0179 | 10314.0693 | 7.7008 | 10.3141 | 0 | 0 |  |  | 0 | 0
128 | L14 | H-14-003 | MECH ROOM | 2572540.5687 | 4777.1234 | 2.5725 | 4.7771 | 2.5725 | 4.7771 |  |  | 2.5725 | 4.7771
129 | L14 |  | FF LOBBY | 5019975.2718 | 5901.4583 | 5.02 | 5.9015 | 5.02 | 5.9015 |  |  | 5.02 | 5.9015
130 | L14 |  | FTR | 6099550.8363 | 7235.8856 | 6.0996 | 7.2359 | 0 | 0 |  |  | 0 | 0
131 | L14 |  | ELECTRICAL ROOM | 7700810.0179 | 10314.0693 | 7.7008 | 10.3141 | 0 | 0 |  |  | 0 | 0
132 | L15 | H-15-003 | MECH ROOM | 2572540.5687 | 4777.1234 | 2.5725 | 4.7771 | 2.5725 | 4.7771 |  |  | 2.5725 | 4.7771
133 | L15 |  | FF LOBBY | 5019975.2718 | 5901.4583 | 5.02 | 5.9015 | 5.02 | 5.9015 |  |  | 5.02 | 5.9015
134 | L15 |  | FTR | 6099550.8363 | 7235.8856 | 6.0996 | 7.2359 | 0 | 0 |  |  | 0 | 0
135 | L15 |  | ELECTRICAL ROOM | 7700810.0179 | 10314.0693 | 7.7008 | 10.3141 | 0 | 0 |  |  | 0 | 0
136 | L16 | H-16-003 | MECH ROOM | 2572540.5687 | 4777.1234 | 2.5725 | 4.7771 | 2.5725 | 4.7771 |  |  | 2.5725 | 4.7771
137 | L16 |  | FF LOBBY | 5019975.2718 | 5901.4583 | 5.02 | 5.9015 | 5.02 | 5.9015 |  |  | 5.02 | 5.9015
138 | L16 |  | FTR | 6099550.8363 | 7235.8856 | 6.0996 | 7.2359 | 0 | 0 |  |  | 0 | 0
139 | L16 |  | ELECTRICAL ROOM | 7700810.0179 | 10314.0693 | 7.7008 | 10.3141 | 0 | 0 |  |  | 0 | 0
140 | L17 (OME L18) | H-17-001 | FF LOBBY | 5020003.4936 | 5917.044 | 5.02 | 5.917 | 0 | 0 |  |  | 0 | 0
141 | L17 (OME L18) | H-17-003 | MECH ROOM | 2539992.6288 | 4753.3163 | 2.54 | 4.7533 | 0 | 0 |  |  | 0 | 0
142 | L17 (OME L18) | H-17-007 | FTR | 6132531.2107 | 7271.039 | 6.1325 | 7.271 | 0 | 0 |  |  | 0 | 0
143 | L17 (OME L18) | H-17-008 | ELECTRICAL ROOM | 6121505.4154 | 5288.3694 | 6.1215 | 5.2884 | 0 | 0 |  |  | 0 | 0
144 | L17 (OME L18) | H-17-021 | MEP PLANT ROOM | 67548602.606 | 33158.3903 | 67.5486 | 33.1584 |  | 0 |  |  | 0 | 0
145 | L17 (OME L18) | H-17-025 | MEP PLANT ROOM | 58865659.0126 | 30855.8979 | 58.8657 | 30.8559 | 0 | 0 |  |  | 0 | 0
146 | L18 (OME L19) | H-18-001 | FF LOBBY | 5019978.5688 | 5922.4716 | 5.02 | 5.9225 | 0 | 0 |  |  | 0 | 0
147 | L18 (OME L19) | H-18-003 | MECH ROOM | 2539868.2457 | 4756.5758 | 2.5399 | 4.7566 | 0 | 0 |  |  | 0 | 0
148 | L18 (OME L19) | H-18-006 | ELECTRICAL ROOM | 6121501.011 | 5292.3855 | 6.1215 | 5.2924 | 0 | 0 |  |  | 0 | 0
149 | L18 (OME L19) | H-18-007 | FTR | 6132486.1461 | 7273.0498 | 6.1325 | 7.273 | 0 | 0 |  |  | 0 | 0
150 | L18 (OME L19) | H-18-010 | AHU FOR F&B HX ROOM | 215282748.0624 | 71710.0034 | 215.2827 | 71.71 | 0 | 0 |  |  | 0 | 0
151 | L18 (OME L19) | H-18-011 | FIRE PUMP ROOM | 68848024.74 | 33199.5305 | 68.848 | 33.1995 | 0 | 0 |  |  | 0 | 0
152 | L18 (OME L19) | H-18-012 | FIRE PUMP TANK | 68849646.5303 | 33199.9225 | 68.8496 | 33.1999 | 0 | 0 |  |  | 0 | 0
153 | L18 (OME L19) | H-18-013 | FIRE PUMP ROOM | 89010372.982 | 37327.0637 | 89.0104 | 37.3271 | 0 | 0 |  |  | 0 | 0
154 | L18 (OME L19) | H-18-014 | AUH ROOM-BAR | 82068247.7105 | 36369.5225 | 82.0682 | 36.3695 | 0 | 0 |  |  | 0 | 0
155 | L19 | H-19-003 | MECH ROOM | 2572540.5687 | 4777.1234 | 2.5725 | 4.7771 | 0 | 0 |  |  | 0 | 0
156 | L19 | H-19-001 | FF LOBBY | 5019975.2718 | 5901.4583 | 5.02 | 5.9015 | 0 | 0 |  |  | 0 | 0
157 | L19 | H-19-007 | FTR | 6099550.8363 | 7235.8856 | 6.0996 | 7.2359 | 0 | 0 |  |  | 0 | 0
158 | L19 | H-19-006 | ELECTRICAL ROOM | 7700810.0179 | 10314.0693 | 7.7008 | 10.3141 | 0 | 0 |  |  | 0 | 0
159 | L20 | H-20-001 | FF LOBBY | 5624914.1752 | 5901.4583 | 5.6249 | 5.9015 | 0 | 0 |  |  | 0 | 0
160 | L20 | H-20-003 | MECH ROOM | 2572540.5687 | 4777.1234 | 2.5725 | 4.7771 | 0 | 0 |  |  | 0 | 0
161 | L20 | H-20-007 | FTR | 6099550.8363 | 7235.8856 | 6.0996 | 7.2359 | 0 | 0 |  |  | 0 | 0
162 | L20 | H-20-006 | ELECTRICAL ROOM | 7700810.0179 | 10314.0693 | 7.7008 | 10.3141 | 0 | 0 |  |  | 0 | 0
163 | L21 | H-21-001 | FF LOBBY | 5624914.1752 | 5901.4583 | 5.6249 | 5.9015 | 0 | 0 |  |  | 0 | 0
164 | L21 | H-21-003 | MECH ROOM | 2572540.5687 | 4777.1234 | 2.5725 | 4.7771 | 0 | 0 |  |  | 0 | 0
165 | L21 | H-21-007 | FTR | 6099550.8363 | 7235.8856 | 6.0996 | 7.2359 | 0 | 0 |  |  | 0 | 0
166 | L21 | H-21-006 | ELECTRICAL ROOM | 7700810.0179 | 10314.0693 | 7.7008 | 10.3141 | 0 | 0 |  |  | 0 | 0
167 | L22 | H-22-001 | FF LOBBY | 5624914.1752 | 5901.4583 | 5.6249 | 5.9015 | 0 | 0 |  |  | 0 | 0
168 | L22 | H-22-003 | MECH ROOM | 2572540.5687 | 4777.1234 | 2.5725 | 4.7771 | 0 | 0 |  |  | 0 | 0
169 | L22 | H-22-007 | FTR | 6099550.8363 | 7235.8856 | 6.0996 | 7.2359 | 0 | 0 |  |  | 0 | 0
170 | L22 | H-22-006 | ELECTRICAL ROOM | 7700810.0179 | 10314.0693 | 7.7008 | 10.3141 | 0 | 0 |  |  | 0 | 0
171 | L23 | H-23-003 | MECH ROOM | 2572540.5687 | 4777.1234 | 2.5725 | 4.7771 | 0 | 0 |  |  | 0 | 0
172 | L23 | H-23-001 | FF LOBBY | 5019975.2718 | 5901.4583 | 5.02 | 5.9015 | 0 | 0 |  |  | 0 | 0
173 | L23 | H-23-007 | FTR | 6099550.8363 | 7235.8856 | 6.0996 | 7.2359 | 0 | 0 |  |  | 0 | 0
174 | L23 | H-23-006 | ELECTRICAL ROOM | 7700810.0179 | 10314.0693 | 7.7008 | 10.3141 | 0 | 0 |  |  | 0 | 0
175 | L24 | H-24-003 | MECH ROOM | 2572540.5687 | 4777.1234 | 2.5725 | 4.7771 | 0 | 0 |  |  | 0 | 0
176 | L24 | H-24-001 | FF LOBBY | 5019975.2718 | 5901.4583 | 5.02 | 5.9015 | 0 | 0 |  |  | 0 | 0
177 | L24 | H-24-007 | FTR | 6099550.8363 | 7235.8856 | 6.0996 | 7.2359 | 0 | 0 |  |  | 0 | 0
178 | L24 | H-24-006 | ELECTRICAL ROOM | 7700810.0179 | 10314.0693 | 7.7008 | 10.3141 | 0 | 0 |  |  | 0 | 0
179 | L25 | H-25-003 | MECH ROOM | 2572540.5687 | 4777.1234 | 2.5725 | 4.7771 | 0 | 0 |  |  | 0 | 0
180 | L25 | H-25-001 | FF LOBBY | 5019975.2718 | 5901.4583 | 5.02 | 5.9015 | 0 | 0 |  |  | 0 | 0
181 | L25 | H-25-007 | FTR | 6099550.8363 | 7235.8856 | 6.0996 | 7.2359 | 0 | 0 |  |  | 0 | 0
182 | L25 | H-25-006 | ELECTRICAL ROOM | 7700810.0179 | 10314.0693 | 7.7008 | 10.3141 | 0 | 0 |  |  | 0 | 0
183 | L26 | H-26-003 | MECH ROOM | 2572540.5687 | 4777.1234 | 2.5725 | 4.7771 | 0 | 0 |  |  | 0 | 0
184 | L26 | H-26-001 | FF LOBBY | 5019975.2718 | 5901.4583 | 5.02 | 5.9015 | 0 | 0 |  |  | 0 | 0
185 | L26 | H-26-007 | FTR | 6099550.8363 | 7235.8856 | 6.0996 | 7.2359 | 0 | 0 |  |  | 0 | 0
186 | L26 | H-26-006 | ELECTRICAL ROOM | 7700810.0179 | 10314.0693 | 7.7008 | 10.3141 | 0 | 0 |  |  | 0 | 0
187 | L27 | H-27-003 | MECH ROOM | 2572540.5687 | 4777.1234 | 2.5725 | 4.7771 | 0 | 0 |  |  | 0 | 0
188 | L27 | H-27-001 | FF LOBBY | 5019975.2718 | 5901.4583 | 5.02 | 5.9015 | 0 | 0 |  |  | 0 | 0
189 | L27 | H-27-007 | FTR | 6099550.8363 | 7235.8856 | 6.0996 | 7.2359 | 0 | 0 |  |  | 0 | 0
190 | L27 | H-27-006 | ELECTRICAL ROOM | 7700810.0179 | 10314.0693 | 7.7008 | 10.3141 | 0 | 0 |  |  | 0 | 0
191 | L28 (OME L29) | H-29-003 | MECH ROOM | 3356141.2155 | 6402.3858 | 3.3561 | 6.4024 | 0 | 0 |  |  | 0 | 0
192 | L28 (OME L29) | H-29-001 | FF LOBBY | 5019875.13 | 5901.4583 | 5.0199 | 5.9015 | 0 | 0 |  |  | 0 | 0
193 | L28 (OME L29) | H-29-006 | ELECTRICAL ROOM | 6121141.5901 | 5289.4525 | 6.1211 | 5.2895 | 0 | 0 |  |  | 0 | 0
194 | L28 (OME L29) | H-29-007 | FTR ROOM | 6132502.1845 | 6360.4829 | 6.1325 | 6.3605 | 0 | 0 |  |  | 0 | 0
195 | L28 (OME L29) | H-29-011 | MECH PLANT FOR GYM&SPA | 68180120.146 | 40000.2107 | 68.1801 | 40.0002 | 0 | 0 |  |  | 0 | 0
196 | L28 (OME L29) | H-29-012 | POOL PLANT | 89719295.3 | 46969.9921 | 89.7193 | 46.97 | 0 | 0 |  |  | 0 | 0
197 | L28 (OME L29) | H-29-039 | ESCAPE CORRIDOR (STAIR 6 -CORRIDOR ) | 48003934.9355 | 51172.5012 | 48.0039 | 51.1725 | 0 | 0 |  |  | 0 | 0
198 | L28 (OME L29) |  | STAIR 8 - CORRIDOR | 15347181.1251 | 14595.2376 | 15.3472 | 14.5952 | 0 | 0 |  |  | 0 | 0
199 | L28 (OME L29) | H-29-040 | GSM | 9487485.7666 | 11404.1704 | 9.4875 | 11.4042 | 0 | 0 |  |  | 0 | 0
200 | L28 (OME L29) | H-29-041 | MEP PLANT ROOM | 415560574.9206 | 142870.028 | 415.5606 | 142.87 | 0 | 0 |  |  | 0 | 0
201 | L 29 (OME L30) | H-30-001 | FF LOBBY | 5576693.672 | 6401.9794 | 5.5767 | 6.402 | 0 | 0 |  |  | 0 | 0
202 | L 29 (OME L30) | H-30-006 | ELECTRICAL ROOM | 11336466.8815 | 13040.0005 | 11.3365 | 13.04 | 0 | 0 |  |  | 0 | 0
203 | L 29 (OME L30) | H-30-013 | GSM | 5803975.5083 | 10308.8837 | 5.804 | 10.3089 | 0 | 0 |  |  | 0 | 0
204 | L 30 (OME L31) | H-31-001 | MEP ROOF PLANT | 31560521.178 | 22232.1 | 31.5605 | 22.2321 | 0 | 0 |  |  | 0 | 0
205 | L 31(OME L32) | H-32-001 | LIFT MACHINE ROOM | 12874987.3601 | 15299.9967 | 12.875 | 15.3 | 0 | 0 |  |  | 0 | 0
206 | L 31(OME L32) | H-32-002 | LIFT MACHINE ROOM | 11115134.8015 | 15300.0509 | 11.1151 | 15.3001 | 0 | 0 |  |  | 0 | 0
207 | L 31(OME L32) | H-32-003 | LIFT MACHINE ROOM | 66219926.0652 | 32599.9808 | 66.2199 | 32.6 | 0 | 0 |  |  | 0 | 0
208 | L31(OME L32) | H-32-003 | MEP ROOF PLANT | 44478379.3798 | 26188.2054 | 44.4784 | 26.1882 | 0 | 0 |  |  | 0 | 0
HOTEL EPOXY FLOOR COATING TO BOH ROOMS | [5 empty] | 5599.838 | 3426.7587 | 1256.8309 | 811.0339 | 12.6691 | 14.3262 | 965.5424 | 605.1407
RESIDENCE SERVICED APARTMENTS EPOXY FLOOR COATING TO BOH ROOMS | [5 empty] | TOTAL |  | PREVIOUSLY COMPLETED |  | 2023-01-01 |  | CUMULATIVE COMPLETION
SI | LEVEL | ROOM | NAME | AREA (MM2) | SKIRTING (MM) | AREA (M²) | SKIRTING (M) | AREA | SKIRTING | AREA | SKIRTING | AREA | SKIRTING
1 | L 6 | R-06-002 | WM ROOM | 2473788.4399 | 6298.5687 | 2.4738 | 6.2986
2 | L 6 | R-06-008 | HOUSE KEEPING LOBBY | 9554394.6376 | 15103.0056 | 9.61 | 12.24 | 9.61 | 12.24 |  |  | 9.61 | 12.24
3 | L 6 | R-06-013 | EMPOWER METER | 1625000 | 6450 | 1.625 | 6.45 | 0 | 0
4 | L 7 | R-07-002 | WM ROOM | 2473788.4399 | 6298.5687 | 2.4738 | 6.2986
5 | L 7 | R-07-013 | EMPOWER METER | 1625000 | 6450 | 1.625 | 6.45 | 0 | 0
6 | L 8 | R-08-002 | WM ROOM | 2473788.4399 | 6298.5687 | 2.4738 | 6.2986
7 | L 8 | R-08-013 | EMPOWER METER | 1625000 | 6450 | 1.625 | 6.45
8 | L 9 | R-09-002 | WM ROOM | 2473788.4399 | 6298.5687 | 2.4738 | 6.2986
9 | L 9 | R-09-013 | EMPOWER METER | 1625000 | 6450 | 1.625 | 6.45 | 0 | 0
10 | L 10 | R-10-002 | WM ROOM | 2473788.4399 | 6298.5687 | 2.4738 | 6.2986
11 | L 10 | R-10-013 | EMPOWER METER | 1625000 | 6450 | 1.625 | 6.45 | 0 | 0
12 | L10 | R-10-014 | BMU EXTERNAL STORAGE | 28565725.4395 | 24376.6376 | 28.5657 | 24.3766
13 | L 11 | R-11-002 | WM ROOM | 2473788.4399 | 6298.5687 | 2.4738 | 6.2986
14 | L 11 | R-11-013 | EMPOWER METER | 1625000 | 6450 | 1.625 | 6.45 | 0 | 0
15 | L 12 | R-12-002 | WM ROOM | 2473788.4399 | 6298.5687 | 2.4738 | 6.2986
16 | L 12 | R-12-013 | EMPOWER METER | 1625000 | 6450 | 1.625 | 6.45
17 | L 13 | R-13-002 | WM ROOM | 2473788.4399 | 6298.5687 | 2.4738 | 6.2986
18 | L 13 | R-13-013 | EMPOWER METER | 1625000 | 6450 | 1.625 | 6.45
19 | L 14 | R-14-002 | WM ROOM | 2473788.4399 | 6298.5687 | 2.4738 | 6.2986
20 | L 14 | R-14-013 | EMPOWER METER | 1625000 | 6450 | 1.625 | 6.45
21 | L 15 | R-15-002 | WM ROOM | 2473788.4399 | 6298.5687 | 2.4738 | 6.2986
22 | L 15 | R-15-013 | EMPOWER METER | 1625000 | 6450 | 1.625 | 6.45
23 | L 16 | R-16-002 | WM ROOM | 2473788.4399 | 6298.5687 | 2.4738 | 6.2986
24 | L 16 | R-16-013 | EMPOWER METER | 1625000 | 6450 | 1.625 | 6.45
25 | L 17 | R-17-002 | WM ROOM | 2473788.4399 | 6298.5687 | 2.4738 | 6.2986
26 | L 17 | R-17-013 | EMPOWER METER | 1625000 | 6450 | 1.625 | 6.45
27 | L 18 | R-18-002 | WM ROOM | 2473788.4399 | 6298.5687 | 2.4738 | 6.2986
28 | L 18 | R-18-013 | EMPOWER METER | 1625000 | 6450 | 1.625 | 6.45
29 | L 19 | R-19-002 | WM ROOM | 2473788.4399 | 6298.5687 | 2.4738 | 6.2986
30 | L 19 | R-19-013 | EMPOWER METER | 1625000 | 6450 | 1.625 | 6.45 | 0 | 0
31 | L 20 | R-20-002 | WM ROOM | 2473788.4399 | 6298.5687 | 2.4738 | 6.2986
32 | L 20 | R-20-013 | EMPOWER METER | 1625000 | 6450 | 1.625 | 6.45
33 | L 21 | R-21-002 | WM ROOM | 2473788.4399 | 6298.5687 | 2.4738 | 6.2986
34 | L 21 | R-21-013 | EMPOWER METER | 1625000 | 6450 | 1.625 | 6.45
35 | L 22 | R-22-002 | WM ROOM | 2473788.4399 | 6298.5687 | 2.4738 | 6.2986
36 | L 22 | R-22-013 | EMPOWER METER | 1625000 | 6450 | 1.625 | 6.45
37 | L23(OME L24) | R-23-001 | FF LOBBY | 13992613.9931 | 16210 | 13.9926 | 12.11 | 13.9926 | 12.11 |  |  | 13.9926 | 12.11
38 | L23(OME L24) | R-23-002 | WM ROOM | 2473381.8353 | 6298.0581 | 2.4734 | 6.2981
39 | L23(OME L24) | R-23-008 | HOUSE KEEPING LOBBY | 11672732.7882 | 15934.8407 | 11.61 | 13.03 | 11.61 | 13.03 |  |  | 11.61 | 13.03
40 | L23(OME L24) | R-23-009 | MEP CORRIDOR | 19267410.6211 | 21648.3171 | 19.2674 | 21.6483
41 | L23(OME L24) | R-23-010 | TELECOM | 3480370.3772 | 7856.1043 | 3.4804 | 7.8561
42 | L23(OME L24) | R-23-015 | PLANT ROOM | 141430649.4559 | 50527.2617 | 141.4306 | 50.5273
43 | L23(OME L24) | R-23-016 | PLANT ROOM | 303409349.1242 | 70045.0488 | 303.4093 | 70.045 | 0 | 0 | 303.4093 | 70.045 | 303.4093 | 70.045
44 | L23(OME L24) |  | EMPOWER METER | 1625000 | 6450 | 1.625 | 6.45
45 | L23(OME L24) | R-23-034 | LIFT 27 CORRIDOR | 8180522.0311 | 11891.5093 | 8.1805 | 11.8915
46 | L23(OME L24) | R-23-035 | BMU STORAGE | 30723584.1087 | 22071.609 | 30.23 | 20.21 | 30.23 | 20.21 |  |  | 30.23 | 20.21
47 | L24 | R-24-001 | FF LOBBY | 13992613.9931 | 16210 | 14.99 | 17.21 | 14.99 | 17.21 |  |  | 14.99 | 17.21
48 | L24 | R-24-002 | WM ROOM | 1907793.882 | 5612.1026 | 1.9078 | 5.6121
49 | L24 | R-24-008 | HOUSE KEEPING LOBBY | 11672732.7882 | 15934.8407 | 9.55 | 15.1 | 9.55 | 15.1 |  |  | 9.55 | 15.1
50 | L24 | R-24-013 | EMPOWER METER | 1625000 | 6450 | 1.625 | 6.45
51 | L25 | R-25-001 | FF LOBBY | 13992613.9931 | 16210 | 14.99 | 17.21 | 14.99 | 17.21 |  |  | 14.99 | 17.21
52 | L25 | R-25-002 | WM ROOM | 1907793.882 | 5612.1026 | 1.9078 | 5.6121
53 | L25 | R-25-008 | HOUSE KEEPING LOBBY | 11672732.7882 | 15934.8407 | 9.55 | 15.1 | 9.55 | 15.1 |  |  | 9.55 | 15.1
54 | L25 | R-25-013 | EMPOWER METER | 1625000 | 6450 | 1 | 2.23 | 1 | 2.23 |  |  | 1 | 2.23
55 | L26 | R-26-001 | FF LOBBY | 13992613.9931 | 16210 | 14.99 | 17.21 | 14.99 | 17.21 |  |  | 14.99 | 17.21
56 | L26 | R-26-002 | WM ROOM | 1907793.882 | 5612.1026 | 1.9078 | 5.6121 | 0 | 0 |  |  | 0 | 0
57 | L26 | R-26-010 | TELECOM | 3480370.3772 | 7856.1043 | 1.28 | 2.15 | 1.28 | 2.15 |  |  | 1.28 | 2.15
58 | L26 | R-26-013 | EMPOWER METER | 1625000 | 6450 | 1 | 2.23 | 1 | 2.23 |  |  | 1 | 2.23
59 | L27 | R-27-001 | FF LOBBY | 13992613.9931 | 16210 | 14.99 | 17.21 | 14.99 | 17.21 |  |  | 14.99 | 17.21
60 | L27 | R-27-002 | WM ROOM | 1907793.882 | 5612.1026 | 1.9078 | 5.6121 | 0 | 0 |  |  | 0 | 0
61 | L27 | R-27-008 | HOUSE KEEPING LOBBY | 11672732.7882 | 15934.8407 | 9.55 | 15.1 | 9.55 | 15.1 |  |  | 9.55 | 15.1
62 | L27 | R-27-010 | TELECOM | 3480370.3772 | 7856.1043 | 1.28 | 2.15 | 1.28 | 2.15 |  |  | 1.28 | 2.15
63 | L27 | R-27-013 | EMPOWER METER | 1625000 | 6450 | 1 | 2.23 | 1 | 2.23 |  |  | 1 | 2.23
64 | L28 | R-28-001 | FF LOBBY | 13992613.9931 | 16210 | 14.99 | 17.21 | 14.99 | 17.21 |  |  | 14.99 | 17.21
65 | L28 | R-28-002 | WM ROOM | 1907793.882 | 5612.1026 | 1.9078 | 5.6121 | 0 | 0 |  |  | 0 | 0
66 | L28 | R-28-008 | HOUSE KEEPING LOBBY | 11672732.7882 | 15934.8407 | 9.55 | 15.1 | 9.55 | 15.1 |  |  | 9.55 | 15.1
67 | L28 | R-28-010 | TELECOM | 3480370.3772 | 7856.1043 | 1.28 | 2.15 | 1.28 | 2.15 |  |  | 1.28 | 2.15
68 | L28 | R-28-013 | EMPOWER METER | 1625000 | 6450 | 1 | 2.23 | 1 | 2.23 |  |  | 1 | 2.23
69 | L29 | R-29-001 | FF LOBBY | 13992613.9931 | 16210 | 14.99 | 17.21 | 14.99 | 17.21 |  |  | 14.99 | 17.21
70 | L29 | R-29-002 | WM ROOM | 1907793.882 | 5612.1026 | 1.9078 | 5.6121 | 0 | 0 |  |  | 0 | 0
71 | L29 | R-29-008 | HOUSE KEEPING LOBBY | 11672732.7882 | 15934.8407 | 9.55 | 15.1 | 9.55 | 15.1 |  |  | 9.55 | 15.1
72 | L29 | R-29-013 | EMPOWER METER | 1625000 | 6450 | 1.625 | 6.45 | 0 | 0 |  |  | 0 | 0
73 | L30(OME L31) | R-31-002 | WM ROOM | 1907793.882 | 5612.1026 | 1.9078 | 5.6121 | 0 | 0 |  |  | 0 | 0
74 | L30(OME L31) | R-31-008 | HOUSE KEEPING LOBBY | 11672732.7882 | 15934.8407 | 9.61 | 12.23 | 9.61 | 12.23 |  |  | 9.61 | 12.23
75 | L30(OME L31) | R-31-013 | LIFT MACHINE ROOM | 1625000 | 6450 | 44.11 | 26.92 | 44.11 | 26.92 |  |  | 44.11 | 26.92
76 | L30(OME L31) | R-31-015 | EMPOWER METER | 1625000 | 6450 | 1.625 | 6.45 | 0 | 0 |  |  | 0 | 0
77 | L31(OME L32) | R-32-006 | FIRE EXIT LOBBY | 4262500 | 8600 | 4.2625 | 8.6 | 0 | 0 |  |  | 0 | 0
78 | L31(OME L32) | R-32-007 | FIRE EXIT LOBBY | 4809445.1646 | 8996.5088 | 4.8094 | 8.9965 | 0 | 0 |  |  | 0 | 0
79 | L31(OME L32) | R-32-008 | MEP PLANT ROOM | 20580000.0001 | 21700 | 20.58 | 21.7 | 0 | 0 | 20.58 | 21.7 | 20.58 | 21.7
80 | L31(OME L32) | R-32-009 | LIFT MACHINE ROOM | 11332750.1798 | 13645.0001 | 11.44 | 12.82 | 11.44 | 12.82 |  |  | 11.44 | 12.82
81 | L31(OME L32) | R-32-012 | GSM | 8308000 | 11560 | 8.308 | 10.56 | 8.308 | 10.56 |  |  | 8.308 | 10.56
82 | L31(OME L32) | R-32-013 | FTR | 6732000 | 11860 | 6.732 | 10.86 | 6.732 | 10.86 |  |  | 6.732 | 10.86
83 | L31(OME L32) | R-32-016 | MEP SERVICE CORRIDOR | 11040000 | 20960 | 11.04 | 15.36 | 11.04 | 15.36 |  |  | 11.04 | 15.36
RESIDENCE SERVICED APARTMENTS TOTAL EPOXY FLOOR COATING TO BOH ROOMS | [5 empty] | 928.2059 | 854.2198 | 302.2126 | 340.47 | 323.9893 | 91.745 | 626.202 | 432.215
COMBINED HOTEL & RESIDENCE SERVICED APARTMENTS TOTAL EPOXY FLOOR COATING TO BOH ROOMS | [5 empty] | 6528.0439 | 4280.9786 | 1559.0435 | 1151.5039 | 336.6584 | 106.0712 | 1895.7019 | 1257.5751

## Cumulative UCRETE Flooring
PROJECT NAME: Dorchester Collection, Plot BB. B03.018, Dubai
Head Contractor : Khansaheb Civil Engineering LLC
Sub Contractor : TWIC Insulation
Scope : UCRETE MF - FONDUE BOH Kitchen flooring system (January 2023)
ALL LEVELS BOH KITCHEN FLOORING - UCRETE MF & RG SKIRTING | [7 empty] | 4mm thick UCRETE MF at BOH kitchen areas | 4mm thick UCRETE RG skirting | PREVIOUSLY COMPLETED |  | 2022-06-01 |  | 2022-07-01 |  | 2022-08-01 |  | 2022-09-01 |  | 2022-10-01 |  | 2022-11-01 |  | Dec. 2022 |  | CURRENT MONTH (Jan. 2023) |  | CUMULATIVE COMPLETION
SI. | LEVEL | ROOM | NAME |  |  |  |  | AREA | SKIRTING | AREA | SKIRTING | AREA | SKIRTING | AREA | SKIRTING | AREA | SKIRTING | AREA | SKIRTING | AREA | SKIRTING | AREA | SKIRTING | AREA | SKIRTING | AREA | SKIRTING | AREA | SKIRTING
1 | B2 | P-B2-048 | LAUNDRY COLLECTION | 40765873.3973 | 30962.3765 |  |  | 40.7659 | 30.9624 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
2 | B1 | 18-24/S-T | CORRIDOR NEAR FOOD PREPARATION |  |  | 237668543.177 | 162482.9527 | 116.42 | 90.04 | 116.42 | 90.04 | [6 empty] | 116.42 | 90.04 |  |  |  |  | 0 | 0 | 0 | 0 | 116.42 | 90.04
3 | B1 | 17-24/U-V | CORRIDOR NEAR LIFT CORE | 129231308.4237 | 125907.8772 |  |  | 145.23 | 103.31 | 145.23 | 103.31 | [6 empty] | 145.23 | 103.31 |  |  |  |  | 0 | 0 | 0 | 0 | 145.23 | 103.31
4 | B1 | 18-19/Q-T | CORRIDOR NEAR RAW WASH ROOM | 129231308.4237 | 125907.8772 |  |  | 16.06 | 12.51 | 16.06 | 12.51 | [6 empty] | 16.06 | 12.51 | [8 empty] | 16.06 | 12.51
5 | B1 | 22-23/Q-V | CORRIDOR NEAR EXEC. CHEF OFFICE | 43519603.9886 | 34572.1786 |  |  | 45.52 | 34.57 | 45.52 | 34.57 | [6 empty] | 45.52 | 34.57 | [8 empty] | 45.52 | 34.57
6 | B1 | 23-24/U-T | PANTRY ROOM NEAR STAFF DINNING | 14991477.2601 | 17198.0588 |  |  | 14.9915 | 17.1981 | 14.9915 | 17.1981 | [12 empty] | 14.9915 | 17.1981 | 0 | 0 | 14.9915 | 17.1981
7 | B1 | P-B1-064 | HOUSEKEEPING & GUEST VALET | 112532276.8962 | 64912.1889 |  |  | 112.5323 | 64.9122 | 112.5323 | 64.9122 | [9 empty] | 64.9122 | 112.5323 |  |  | 0 |  | 0 | 112.5323 | 64.9122
8 | B1 | P-B1-075 | STORE CONTROL OFFICE | 9028115.4691 | 12880.9333 |  |  | 9.03 | 11.04 | 9.03 | 11.04 | [8 empty] | 9.03 | 11.04 |  |  | 0 | 0 | 0 | 0 | 9.03 | 11.04
9 | B1 | P-B1-077 | UNIFORM DISTRIBUTION | 47940254.579 | 27003.1721 |  |  | 47.9403 | 27.0032 | 47.9403 | 27.0032 | [8 empty] | 47.9403 | 27.0032 |  |  | 0 | 0 | 0 | 0 | 47.9403 | 27.0032
10 | B1 | P-B1-089 | ROOM SERVICE SUPPORT AREA | 18276880.3578 | 15211.9663 |  |  | 18.2769 | 15.212 | 18.2769 | 15.212 | [6 empty] | 18.2769 | 15.212 |  |  |  |  | 0 | 0 | 0 | 0 | 18.2769 | 15.212
11 | B1 | P-B1-091 | WASTE ROUTE | 24634561.2625 | 16601.8267 | 24256884.4921 | 20701.1628 | 24.63 | 16.6 | 24.63 | 16.6 | [12 empty] | 24.63 | 16.6 | 0 | 0 | 24.63 | 16.6
12 | B1 | P-B1-092 | BOH Store | 1920000.0009 | 4663.2002 |  |  | 1.92 | 4.6632 | 1.92 | 4.6632 | [12 empty] | 1.92 | 4.6632 | 0 | 0 | 1.92 | 4.6632
13 | B1 | P-B1-095 | HOUSEKEEPING LOBBY | 14697808.778 | 14017.4087 |  |  | 14.6978 | 14.0174 | 14.6978 | 14.0174 | [12 empty] | 14.6978 | 14.0174 | 0 | 0 | 14.6978 | 14.0174
14 | B1 | P-B1-117 | BIN STORE | 23884961.5108 | 22108.1768 |  |  | 23.885 | 22.1082 | 23.885 | 22.1082 | [10 empty] | 23.885 | 22.1082 |  |  |  |  | 23.885 | 22.1082
15 | B1 | P-B1-144 | COMPRESSOR & LOCAL STEAM BOILER | 3419068.9706 | 6610.843 |  |  | 3.4191 | 6.6108 | 3.4191 | 6.6108 | [9 empty] | 6.6108 | 3.4191 |  |  | 0 |  | 0 | 3.4191 | 6.6108
16 | B1 | P-03-055 | FLOWER ROOM | 12579503.7663 | 13293.6957 |  |  | 12.5795 | 13.2937 | 12.5795 | 13.2937 | [12 empty] | 12.5795 | 13.2937 | 0 | 0 | 12.5795 | 13.2937
17 | G | P-GF-043 | ROOM SERVICE SUPPORT AREA | 17676500.9563 | 20511.1645 |  |  | 17.67 | 20.5112 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
18 | G | P-GF-053 | HOUSE KEEPING LOBBY | 12292522.3494 | 17565.9946 |  |  | 12.29 | 13.55 | 0 | 0 | [12 empty] | 0 | 0 | 12.29 | 13.55 | 12.29 | 13.55
19 | G | P-GF-058 | BOH STORE | 1915337.5511 | 4659.3277 |  |  | 1.9153 | 4.6593 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
20 | G |  | NEAR FOOD STORAGE ROOM | 4008361.7449 | 7852.8335 |  |  | 4.0084 | 7.8528 | 0 | 0 | [16 empty] | 0 | 0
21 | L1 | P-01-004 | ROOM SERVICE SUPPORT AREA | 24253394.98 | 14861.0696 |  |  | 17.67 | 14.8611 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
22 | L1 | P-01-020 | HOUSE KEEPING LOBBY | 9344005.7288 | 10012.6413 |  |  | 9.34 | 10 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
23 | L2 | P-02-015 | ROOM SERVICE SUPPORT AREA | 24253394.98 | 14641.3675 |  |  | 17.67 | 14.6414 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
24 | L2 | P-02-040 | HOUSE KEEPING LOBBY | 9348260.5719 | 14458.4031 |  |  | 9.34 | 9.79 | 9.34 | 9.79 | [12 empty] | 9.34 | 9.79 | 0 | 0 | 9.34 | 9.79
25 | L2 | P-02-041 | BOH STORE | 1915337.5511 | 4654.1541 |  |  | 1.9153 | 4.6542 | 1.9153 | 4.6542 | [12 empty] | 1.9153 | 4.6542 | 0 | 0 | 1.9153 | 4.6542
26 | L2 | P-02-098 | BOH CORRIDOR | 38209714.9831 | 44057.9699 |  |  | 38.2097 | 44.058 | 38.2097 | 44.058 | [12 empty] | 38.2097 | 44.058 | 0 | 0 | 38.2097 | 44.058
27 | L3 | P-03-025 | STORAGE SUPPORT ROOM | 9803593.49 | 9821.3642 |  |  | 9.8 | 9.8214 | 9.8 | 9.8214 | [12 empty] | 9.8 | 9.8214 | 0 | 0 | 9.8 | 9.8214
28 | L4 | P-04-004 | BOH STORE | 1915337.5511 | 4660.4193 |  |  | 1.9153 | 4.6604 | 1.9153 | 4.6604 | [12 empty] | 1.9153 | 4.6604 | 0 | 0 | 1.9153 | 4.6604
29 | L4 | P-04-018 | HOUSE KEEPING LOBBY | 9344005.958 | 14458.4031 |  |  | 9.34 | 9.79 | 9.34 | 9.79 | [12 empty] | 9.34 | 9.79 | 0 | 0 | 9.34 | 9.79
30 | L4 |  | ROOM SERVICE SUPPORT AREA | 24253394.98 | 13613.8402 |  |  | 17.67 | 13.6138 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
31 | L5 |  | BOH STORE | 1915337.5511 | 4654.1541 |  |  | 1.9153 | 4.6542 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
32 | L5 |  | HOUSE KEEPING LOBBY & LINEN ROOM | 9385473.1556 | 14458.4031 |  |  | 9.5 | 10.09 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
33 | L5 |  | ROOM SERVICE SUPPORT AREA | 24253394.98 | 20777.1548 |  |  | 20 | 15.1 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
34 | L6 |  | HOUSE KEEPING LOBBY & LINEN ROOM | 9385473.1556 | 14458.4031 |  |  | 9.5 | 10.09 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
35 | L6 |  | ROOM SERVICE SUPPORT AREA | 24253394.98 | 20777.1548 |  |  | 20 | 15.1 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
36 | L7 |  | HOUSE KEEPING LOBBY & LINEN ROOM | 9385473.1556 | 14458.4031 |  |  | 9.5 | 10.09 | 9.5 | 10.09 | [8 empty] | 9.5 | 10.09 |  |  | 0 | 0 | 0 | 0 | 9.5 | 10.09
37 | L7 |  | ROOM SERVICE SUPPORT AREA | 24253394.98 | 20777.1548 |  |  | 20 | 15.1 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
38 | L7 |  | JANITOR | 1915615.5716 | 4553.9687 |  |  | 1.93 | 4.68 | 1.93 | 4.68 | [8 empty] | 1.93 | 4.68 |  |  | 0 | 0 | 0 | 0 | 1.93 | 4.68
39 | L8 |  | HOUSE KEEPING LOBBY & LINEN ROOM | 9385473.1556 | 14458.4031 |  |  | 9.5 | 10.09 | 9.5 | 10.09 | [8 empty] | 9.5 | 10.09 |  |  | 0 | 0 | 0 | 0 | 9.5 | 10.09
40 | L8 |  | ROOM SERVICE SUPPORT AREA | 24253394.98 | 20777.1548 |  |  | 20 | 15.1 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
41 | L9 |  | HOUSE KEEPING LOBBY & LINEN ROOM | 9385473.1556 | 14458.4031 |  |  | 9.5 | 10.09 | 9.5 | 10.09 | [8 empty] | 9.5 | 10.09 |  |  | 0 | 0 | 0 | 0 | 9.5 | 10.09
42 | L9 |  | ROOM SERVICE SUPPORT AREA | 24253394.98 | 20777.1548 |  |  | 20 | 15.1 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
43 | L9 |  | JANITOR | 1915615.5716 | 4553.9687 |  |  | 1.93 | 4.68 | 1.93 | 4.68 | [8 empty] | 1.93 | 4.68 |  |  | 0 | 0 | 0 | 0 | 1.93 | 4.68
44 | L10 |  | HOUSE KEEPING LOBBY & LINEN ROOM | 9385473.1556 | 14458.4031 |  |  | 9.5 | 10.09 | 9.5 | 10.09 | [9 empty] | 10.09 | 9.5 |  |  | 0 |  | 0 | 9.5 | 10.09
45 | L10 |  | ROOM SERVICE SUPPORT AREA | 24253394.98 | 20777.1548 |  |  | 20 | 15.1 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
46 | L11 |  | HOUSE KEEPING LOBBY & LINEN ROOM | 9385473.1556 | 14458.4031 |  |  | 9.5 | 10.09 | 9.5 | 10.09 | [9 empty] | 10.09 | 9.5 |  |  | 0 |  | 0 | 9.5 | 10.09
47 | L11 |  | ROOM SERVICE SUPPORT AREA | 24253394.98 | 20777.1548 |  |  | 20 | 15.1 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
48 | L12 |  | HOUSE KEEPING LOBBY & LINEN ROOM | 9385473.1556 | 14458.4031 |  |  | 9.5 | 10.09 | 9.5 | 10.09 | [9 empty] | 10.09 | 9.5 |  |  | 0 |  | 0 | 9.5 | 10.09
49 | L12 |  | ROOM SERVICE SUPPORT AREA | 24253394.98 | 20777.1548 |  |  | 20 | 15.1 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
50 | L12 |  | JANITOR | 1915615.5716 | 4553.9687 |  |  | 1.93 | 4.68 | 1.93 | 4.68 | [9 empty] | 4.68 | 1.93 |  |  | 0 |  | 0 | 1.93 | 4.68
51 | L13 |  | HOUSE KEEPING LOBBY & LINEN ROOM | 9385473.1556 | 14458.4031 |  |  | 9.5 | 10.09 | 9.5 | 10.09 | [9 empty] | 10.09 | 9.5 |  |  | 0 |  | 0 | 9.5 | 10.09
52 | L13 |  | ROOM SERVICE SUPPORT AREA | 24253394.98 | 20777.1548 |  |  | 20 | 15.1 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
53 | L13 |  | JANITOR | 1915615.5716 | 4553.9687 |  |  | 1.93 | 4.68 | 1.93 | 4.68 | [9 empty] | 4.68 | 1.93 |  |  | 0 |  | 0 | 1.93 | 4.68
54 | L14 |  | HOUSE KEEPING LOBBY & LINEN ROOM | 9385473.1556 | 14458.4031 |  |  | 9.5 | 10.09 | 9.5 | 10.09 | [9 empty] | 10.09 | 9.5 |  |  | 0 |  | 0 | 9.5 | 10.09
55 | L14 |  | ROOM SERVICE SUPPORT AREA | 24253394.98 | 20777.1548 |  |  | 20 | 15.1 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
56 | L15 |  | HOUSE KEEPING LOBBY & LINEN ROOM | 9385473.1556 | 14458.4031 |  |  | 9.5 | 10.09 | 9.5 | 10.09 | [9 empty] | 10.09 | 9.5 |  |  | 0 |  | 0 | 9.5 | 10.09
57 | L15 |  | ROOM SERVICE SUPPORT AREA | 24253394.98 | 20777.1548 |  |  | 20 | 15.1 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
58 | L15 |  | JANITOR | 1915615.5716 | 4553.9687 |  |  | 1.93 | 4.68 | 1.93 | 4.68 | [9 empty] | 4.68 | 1.93 |  |  | 0 |  | 0 | 1.93 | 4.68
59 | L16 |  | HOUSE KEEPING LOBBY & LINEN ROOM | 9385473.1556 | 14458.4031 |  |  | 9.5 | 10.09 | 9.5 | 10.09 | [9 empty] | 10.09 | 9.5 |  |  | 0 |  | 0 | 9.5 | 10.09
60 | L16 |  | ROOM SERVICE SUPPORT AREA | 24253394.98 | 20777.1548 |  |  | 20 | 15.1 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
61 | L17 |  | HOUSE KEEPING LOBBY & LINEN ROOM | 9385473.1556 | 14458.4031 |  |  | 9.5 | 10.09 | 9.5 | 10.09 | [10 empty] | 9.5 | 10.09 |  |  |  |  | 9.5 | 10.09
62 | L17 |  | ROOM SERVICE SUPPORT AREA | 24253394.98 | 20777.1548 |  |  | 20 | 15.1 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
63 | L18 |  | HOUSE KEEPING LOBBY & LINEN ROOM | 9385473.1556 | 14458.4031 |  |  | 9.5 | 10.09 | 9.5 | 10.09 | [10 empty] | 9.5 | 10.09 |  |  |  |  | 9.5 | 10.09
64 | L18 |  | ROOM SERVICE SUPPORT AREA | 24253394.98 | 20777.1548 |  |  | 20 | 15.1 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
65 | L18 |  | JANITOR | 1915615.5716 | 4553.9687 |  |  | 1.93 | 4.68 | 1.93 | 4.68 | [10 empty] | 1.93 | 4.68 |  |  |  |  | 1.93 | 4.68
66 | L19 |  | HOUSE KEEPING LOBBY & LINEN ROOM | 9385473.1556 | 14458.4031 |  |  | 9.5 | 10.09 | 9.5 | 10.09 | [10 empty] | 9.5 | 10.09 |  |  |  |  | 9.5 | 10.09
67 | L19 |  | ROOM SERVICE SUPPORT AREA | 24253394.98 | 20777.1548 |  |  | 20 | 15.1 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
68 | L19 |  | JANITOR | 1915615.5716 | 4553.9687 |  |  | 1.93 | 4.68 | 1.93 | 4.68 | [10 empty] | 1.93 | 4.68 |  |  |  |  | 1.93 | 4.68
69 | L20 |  | HOUSE KEEPING LOBBY & LINEN ROOM | 9385473.1556 | 14458.4031 |  |  | 9.5 | 10.09 | 9.5 | 10.09 | [10 empty] | 9.5 | 10.09 |  |  |  |  | 9.5 | 10.09
70 | L20 |  | ROOM SERVICE SUPPORT AREA | 24253394.98 | 20777.1548 |  |  | 20 | 15.1 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
71 | L21 |  | HOUSE KEEPING LOBBY & LINEN ROOM | 9385473.1556 | 14458.4031 |  |  | 9.5 | 10.09 | 9.5 | 10.09 | [10 empty] | 9.5 | 10.09 |  |  |  |  | 9.5 | 10.09
72 | L21 |  | ROOM SERVICE SUPPORT AREA | 24253394.98 | 20777.1548 |  |  | 20 | 15.1 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
73 | L21 |  | JANITOR | 1915615.5716 | 4553.9687 |  |  | 1.93 | 4.68 | 1.93 | 4.68 | [10 empty] | 1.93 | 4.68 |  |  |  |  | 1.93 | 4.68
74 | L22 |  | HOUSE KEEPING LOBBY & LINEN ROOM | 9385473.1556 | 14458.4031 |  |  | 9.5 | 10.09 | 9.5 | 10.09 | [10 empty] | 9.5 | 10.09 |  |  |  |  | 9.5 | 10.09
75 | L22 |  | ROOM SERVICE SUPPORT AREA | 24253394.98 | 20777.1548 |  |  | 20 | 15.1 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
76 | L23 |  | HOUSE KEEPING LOBBY & LINEN ROOM | 9385473.1556 | 14458.4031 |  |  | 9.5 | 10.09 | 9.5 | 10.09 | [10 empty] | 9.5 | 10.09 |  |  |  |  | 9.5 | 10.09
77 | L23 |  | ROOM SERVICE SUPPORT AREA | 24253394.98 | 20777.1548 |  |  | 20 | 15.1 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
78 | L24 |  | HOUSE KEEPING LOBBY & LINEN ROOM | 9385473.1556 | 14458.4031 |  |  | 9.5 | 10.09 | 9.5 | 10.09 | [10 empty] | 9.5 | 10.09 |  |  |  |  | 9.5 | 10.09
79 | L24 |  | ROOM SERVICE SUPPORT AREA | 24253394.98 | 20777.1548 |  |  | 20 | 15.1 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
80 | L24 |  | JANITOR | 1915615.5716 | 4553.9687 |  |  | 1.93 | 4.68 | 1.93 | 4.68 | [10 empty] | 1.93 | 4.68 |  |  |  |  | 1.93 | 4.68
81 | L25 |  | HOUSE KEEPING LOBBY & LINEN ROOM | 9385473.1556 | 14458.4031 |  |  | 9.5 | 10.09 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
82 | L25 |  | ROOM SERVICE SUPPORT AREA | 24253394.98 | 20777.1548 |  |  | 20 | 15.1 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
83 | L25 |  | JANITOR | 1915615.5716 | 4553.9687 |  |  | 1.9156 | 4.554 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
84 | L26 |  | HOUSE KEEPING LOBBY & LINEN ROOM | 9385473.1556 | 14458.4031 |  |  | 9.5 | 10.09 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
85 | L26 |  | ROOM SERVICE SUPPORT AREA | 24253394.98 | 20777.1548 |  |  | 20 | 15.1 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
86 | L26 |  | JANITOR | 1915615.5716 | 4553.9687 |  |  | 1.9156 | 4.554 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
87 | L27 |  | HOUSE KEEPING LOBBY & LINEN ROOM | 9385473.1556 | 14458.4031 |  |  | 9.5 | 10.09 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
88 | L27 |  | ROOM SERVICE SUPPORT AREA | 24253394.98 | 20777.1548 |  |  | 20 | 15.1 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
89 | L28 |  | HOUSE KEEPING LOBBY & LINEN ROOM | 9385473.1556 | 14458.4031 |  |  | 9.5 | 10.09 | 0 | 0 | [16 empty] | 0 | 0
90 | L28 |  | ROOM SERVICE SUPPORT AREA | 24253394.98 | 20777.1548 |  |  | 20 | 15.1 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0
TOTAL QUANTITY UCRETE FLOORING | [7 empty] | 1547.7688 | 1326.9567 | 866.0226 | 759.6026 | 0 | 0 | 0 | 0 | 0 | 0 | 341.5069 | 255.642 | 89.3303 | 233.8662 | 295.8463 | 121.5482 | 139.3392 | 148.5463 | 12.29 | 13.55 | 878.3126 | 773.1526
463.0524

## Carpark coating
PROJECT NAME: Dorchester Collection, Plot BB. B03.018, Dubai
Head Contractor : Khansaheb Civil Engineering LLC
Sub Contractor : TWIC Insulation
Scope : E11-K129-SK-AK-575 - Carpark Traffic Deck Coating & Floor Marking (January 2023)
S/L | ITEM DESCRIPTION | SUBCONTRACT QUANTITY |  | TWIC PROGRESS CLAIM
QUANTITY
|  | QTY | Unit | Previous | 2023-01-30 | 2023-02-28 | 2023-03-31 | Cumulative Total
Carpark Traffic Coating & Floor Marking
1 | Carpark floor grinding & filling works | 12000 | m² | 0 | 2097.01 |  |  | 2097.01
2 | Levelling works using heavy duty grinder and partial filling to remove undulations and provides mooth level surface | 1530 | m² | 0 | 0 |  |  | 0
3 | Internal Driveways: Supply & Application of Flowcoat SF150 Epoxy colour RAL 7042 Rough to driveways | 8000 | m² | 0 | 1160.76 |  |  | 1160.76
4 | Internal Parking Bays: Supply & Application of Flowcoat SF150 Epoxy colour RAL 7012 Rough to parking bays | 10000 | m² | 0 | 936.25 |  |  | 936.25
5 | Internal Ramps: Supply & Application of Flowcoat SF150 Epoxy colour RAL 7042 Rough to internal ramps | 532 | m² | 0 | 0 |  |  | 0
6 | Exposed ramps: Supply & Application of DECKSHIELD ED Polyurethane colour RAL 7042 Rough to external / exposed to sunlight ramps | 1050 | m² | 0 | 0 |  |  | 0
7 | Supply and application of Parking space line marking & numbering, driveway arrows, hatching, all in white colour | 1 | LS | 0 | 0.1 |  |  | 0.1

## Carpark Detailed calculation
PROJECT NAME:- Plot 18 by Dorchester Collection plot 3466829 Dubai, UAE
Head Contractor : Khansaheb Civil Engineering LLC
Sub Contractor : TWIC Insulation
Scope : CARPARK TRAFFIC DECK COATING & FLOOR MARKING CALCULATION - JANUARY 2023
BASEMENT LEVEL CARPARK TRAFFIC DECK COATING & FLOOR MARKING CALCULATION - JANUARY 2023 | [5 empty] | Qty
SI | GRID LINE | LEVEL | NAME | AREA (MM2) | SKIRTING (MM) | AREA (M²)
1 | 21-24/A-Z | B2 | FLOWCOAT SF150 ROUGH RAL 7042 DRIVEWAYS |  |  | 611.89
2 | 21-24/A-Z | B2 | FLOWCOAT SF150 ROUGH RAL 7012 CARPARK BAYS |  |  | 537.5
3 | 21-24/A-Z | B2 | HATCHING |  |  |  | Lumpsum
4 | 21-24/A-Z | B2 | DECKSHIELD LINEMARKER (CARPARK BAYS) |  |  |  | Lumpsum
5 | 18-22/A-U | B2 | FLOWCOAT SF150 ROUGH RAL 7042 DRIVEWAYS |  |  | 548.87
6 | 18-22/A-U | B2 | FLOWCOAT SF150 ROUGH RAL 7012 CARPARK BAYS |  |  | 398.75
7 | 18-22/A-U | B2 | HATCHING |  |  |  | Lumpsum
8 | 18-22/A-U | B2 | DECKSHIELD LINEMARKER (CARPARK BAYS) |  |  |  | Lumpsum
JANUARY 2023 - TOTAL QUANTITY CARPARK TRAFFIC DECK COATING & FLOOR MARKING - BASEMENT LEVEL | [5 empty] | 2097.01

## Stairs
PROJECT NAME:- Plot 18 by Dorchester Collection plot 3466829 Dubai, UAE
Head Contractor : Khansaheb Civil Engineering LLC
Sub Contractor : TWIC Insulation
Scope : STAIRS - EPOXY FLOOR COATING - JANUARY 2023
Sn. No. | Level | Stair No. | JANUARY 2023 - Quantity |  |  | TOTAL QUANTITY (m²)
|  |  | RISER AREA | TREAD AREA | LANDING HORIZONTAL AREA (m²)
1 | LEVEL 7 | STAIR 7 | 5.19 | 7.5 | 12.66 | 25.35
2 | LEVEL 8 | STAIR 7 | 5.19 | 7.5 | 12.66 | 25.35
3 | LEVEL 9 | STAIR 7 | 5.19 | 7.5 | 12.66 | 25.35
4 | LEVEL 10 | STAIR 7 | 5.19 | 7.5 | 12.66 | 25.35
5 | LEVEL 11 | STAIR 7 | 5.19 | 7.5 | 12.66 | 25.35
6 | LEVEL 12 | STAIR 7 | 5.19 | 7.5 | 12.66 | 25.35
7 | LEVEL 13 | STAIR 7 | 5.19 | 7.5 | 12.66 | 25.35
8 | LEVEL 14 | STAIR 7 | 5.19 | 7.5 | 12.66 | 25.35
9 | LEVEL 15 | STAIR 7 | 5.19 | 7.5 | 12.66 | 25.35
10 | LEVEL 16 | STAIR 7 | 4.95 | 7.13 | 13.26 | 25.34
11 | LEVEL 17 | STAIR 7 | 5.9 | 8.63 | 11.66 | 26.19
12 | LEVEL 18 | STAIR 7 | 8.25 | 11.63 | 26.52 | 46.4
13 | LEVEL 19 | STAIR 7 | 5.19 | 7.5 | 12.66 | 25.35
14 | LEVEL 20 | STAIR 7 | 5.19 | 7.5 | 12.66 | 25.35
15 | LEVEL 21 | STAIR 7 | 5.19 | 7.5 | 12.66 | 25.35
16 | LEVEL 22 | STAIR 7 | 4.95 | 7.13 | 13.26 | 25.34
17 | LEVEL 23 | STAIR 7 | 4.95 | 7.13 | 13.26 | 25.34
18 | LEVEL 24 | STAIR 7 | 5.19 | 7.5 | 12.66 | 25.35
19 | LEVEL 25 | STAIR 3 | 5.66 | 8.25 | 12.66 | 26.57
20 | LEVEL 25 | STAIR 7 | 5.19 | 7.5 | 12.66 | 25.35
21 | LEVEL 26 | STAIR 3 | 5.66 | 8.25 | 12.66 | 26.57
22 | LEVEL 26 | STAIR 7 | 5.19 | 7.5 | 12.66 | 25.35
23 | LEVEL 27 | STAIR 3 | 5.66 | 8.25 | 12.66 | 26.57
24 | LEVEL 27 | STAIR 7 | 4.95 | 7.13 | 13.26 | 25.34
25 | LEVEL 28 | STAIR 3 | 5.66 | 8.25 | 12.66 | 26.57
26 | LEVEL 28 | STAIR 7 | 9.91 | 14.26 | 26.12 | 50.29
27 | LEVEL 29 | STAIR 3 | 12.03 | 17.26 | 25.52 | 54.81
28 | LEVEL 29 | STAIR 7 | 5.66 | 8.25 | 12.6 | 26.51
29 | LEVEL 30 | STAIR 3 | 4.72 | 6.75 | 13.46 | 24.93
30 | LEVEL 30 | STAIR 7 | 6.37 | 9.38 | 10.96 | 26.71
31 | LEVEL 31 | STAIR 3 | 6.13 | 9 | 10.76 | 25.89
JANUARY 2023 - Total Quantity - Mastertop 1205 Epoxy floor coating at Staircases | [5 empty] | 869.62