## Summary
No | Description | Remaining Value of Work | Previous | This Month | Cumulative
1 | Work Done for Joinery works - Level 8 | 0 | 0 | 0 | 0
2 | Work Done for Joinery works | 5973423.0233 | 3956735.8871 | 196130.1547 | 4152866.0418 | 5464428.9767
3 | Deductions for Rejected WIRs | 74482.59 | 74482.59 | 0 | 74482.59
4 | Variations against L8 subcontract as per subcontract addendum no. 01 | 0 | 0 | 0
5 | Variations against joinery subcontract as per subcontract addendum no. 01 | 145647.91 | 70679.9192 | 0 | 70679.9192 | 262728
6 | Final adjustment as per subcontract addendum no. 01 | -0.02 | -0.02 | 0 | -0.02 | 331080
7 | Frosted film for GD-03 glass | 25361 | 0 | 0
8 | Timber Frame for GD -08 Door | 9365 | 0 | 0
9 | TB-21 Door finish changes | 5135 | 0 | 0
10 | Rectification works due to damage by others | 0 | 0 | 0
11 | Wardrobe height change | 17770 | 0 | 0
12 | Vanity Carcase for 7A and 15A room |  | 0 | 0
13 | Additional preliminaries (for new subcontract period) | 750000 | 666666.6667 | 0 | 666666.6667
14 | MOS (75%) | -1082020.2218 | -721218.2514 | -35089.3031 | -756307.5545
15 | Variation with KCE - Modification/Damage Works | 68273.97 | -44172.6711 | 0 | -44172.6711
|  | 5987438.2515 | 4003174.1205 | 161040.8515 | 4164214.9721

## BOQ
No | Description | Qty | Unit | Rate | Amount | Progress % | Previous Amount | Current Amount | Cumulative Amount
PACKAGE 8 - TIMBER DOORS
LUMP SUM
Timber doors complete with frame, sub frames, transoms, stops,
insulation, protective and decorative coatings all in accordance with
drawings and specifications
1 | TYPE 02A (13 Nos)
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per door type : HO-TB-01 | 13 | No. | 3361 | 43693 | 97.51% | 41761.5708 | 844.0693 | 42605.6401
| Timber (HTL-WD-01) double panel door, size 914 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-04 | 13 | No. | 2286 | 29718 | 97.51% | 28404.3293 | 574.0977 | 28978.427
| Timber (HTL-WD-01) double panel door, size 1115 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-05 | 13 | No. | 2347 | 30511 | 97.51% | 29162.2751 | 589.417 | 29751.6922
2 | TYPE 02B (16 Nos)
| 60 minutes FR Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per as per door type : HO-TB-01 | 16 | No. | 3361 | 53776 | 97.31% | 52578.4881 | -248.963 | 52329.5252
| Timber (HTL-WD-01) double panel door, size 914 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-04 | 16 | No. | 2286 | 36576 | 97.31% | 35761.5067 | -169.3333 | 35592.1733
| Timber (HTL-WD-01) double panel door, size 1115 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-05 | 16 | No. | 2347 | 37552 | 97.31% | 36715.7726 | -173.8519 | 36541.9207
| Timber single leaf connecting door, size 942 x 2549mm (60 minutes fire rated) as per DRAWING DLR-703-309 | 16 | No. | 2745 | 43920 | 97.31% | 42941.9667 | -203.3333 | 42738.6333
3 | TYPE 02C (8 Nos)
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per door type : HO-TB-01 | 8 | No. | 3361 | 26888 | 87.84% | 24648.7337 | -1029.3063 | 23619.4275
| Timber (HTL-WD-01) double panel door, size 914 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-04 | 8 | No. | 2286 | 18288 | 87.84% | 16764.9525 | -700.0875 | 16064.865
| Timber (HTL-WD-01) double panel door, size 1115 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-05 | 8 | No. | 2347 | 18776 | 87.84% | 17212.3112 | -718.7687 | 16493.5425
| Timber single leaf connecting door, size 942 x 2549mm (60 minutes fire rated) as per DRAWING DLR-703-309 | 3 | No. | 2745 | 8235 | 87.84% | 7549.1789 | -315.2461 | 7233.9328
4 | TYPE 02D (7 Nos)
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per door type : HO-TB-01 | 7 | No. | 3361 | 23527 | 86.43% | 19661.85 | 672.2 | 20334.05
| Timber (HTL-WD-01) double panel door, size 914 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-04 | 7 | No. | 2286 | 16002 | 86.43% | 13373.1 | 457.2 | 13830.3
| Timber (HTL-WD-01) double panel door, size 1115 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-05 | 7 | No. | 2347 | 16429 | 86.43% | 13729.95 | 469.4 | 14199.35
5 | TYPE 02E (9 Nos)
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per door type : HO-TB-01 | 9 | No. | 3361 | 30249 | 89.56% | 29555.7938 | -2464.7333 | 27091.0604
| Timber (HTL-WD-01) double panel door, size 914 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-04 | 9 | No. | 2286 | 20574 | 89.56% | 20102.5125 | -1676.4 | 18426.1125
| Timber (HTL-WD-01) double panel door, size 1115 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-05 | 9 | No. | 2347 | 21123 | 89.56% | 20638.9312 | -1721.1333 | 18917.7979
| Timber single leaf connecting door, size 942 x 2549mm (60 minutes fire rated) as per Door type : HO-TB-02 | 9 | No. | 2745 | 24705 | 89.56% | 24138.8438 | -2013 | 22125.8437
6 | TYPE 02F (8 Nos)
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per door type : HO-TB-01 | 8 | No. | 3361 | 26888 | 87.77% | 24627.7275 | -1029.3062 | 23598.4212
| Timber (HTL-WD-01) double panel door, size 914 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-04 | 8 | No. | 2286 | 18288 | 87.77% | 16750.665 | -700.0875 | 16050.5775
| Timber (HTL-WD-01) double panel door, size 1115 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-05 | 8 | No. | 2347 | 18776 | 87.77% | 17197.6425 | -718.7687 | 16478.8737
| Timber single leaf connecting door, size 942 x 2549mm (60 minutes fire rated) as per Door type : HO-TB-02 | 8 | No. | 2745 | 21960 | 87.77% | 20113.9875 | -840.6562 | 19273.3312
7 | TYPE 02G (9 Nos)
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per door type : HO-TB-01 | 9 | No. | 3361 | 30249 | 88.18% | 23815.4858 | 2856.85 | 26672.3358
| Timber (HTL-WD-01) double panel door, size 914 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-04 | 9 | No. | 2286 | 20574 | 88.18% | 16198.215 | 1943.1 | 18141.315
| Timber (HTL-WD-01) double panel door, size 1115 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-05 | 9 | No. | 2347 | 21123 | 88.18% | 16630.4508 | 1994.95 | 18625.4008
8 | TYPE 03A (13 Nos)
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per Door type : HO-TB-01 | 13 | No. | 3361 | 43693 | 89.1% | 39112.5172 | -182.0542 | 38930.463
| Timber (HTL-WD-01) double panel door, size 1480 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-03 | 13 | No. | 2701 | 35113 | 89.1% | 31431.9872 | -146.3042 | 31285.683
9 | TYPE 03B (2 Nos) No Details
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per Door type : HO-TB-01 | 0 | No. | 0 |  |  |  | 0 | 0
| Timber (HTL-WD-01) double panel door, size 1450 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-03 | 0 | No. | 0 |  |  |  | 0 | 0
| Timber single leaf connecting door, size 942 x 2549mm (60 minutes fire rated) as per DRAWING DLR-703-309 | 0 | No. | 0 |  |  |  | 0 | 0
10 | TYPE 03C (9 Nos)
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per Door type : HO-TB-01 | 9 | No. | 3361 | 30249 | 92.24% | 29538.9887 | -1638.4875 | 27900.5012
| Timber (HTL-WD-01) double panel door, size 1480 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-03 | 9 | No. | 2701 | 24309 | 92.24% | 23738.4137 | -1316.7375 | 22421.6763
11 | TYPE 03D (18 Nos)
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per Door type : HO-TB-01 | 18 | No. | 3361 | 60498 | 97.69% | 59098.9837 | 0 | 59098.9837
| Timber (HTL-WD-01) double panel door, size 1480 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-03 | 18 | No. | 2701 | 48618 | 97.69% | 47493.7087 | 0 | 47493.7087
12 | TYPE 03E (2 Nos) No Details
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per DRAWING DLR-704-304 | 0 | No. | 0 |  |  |  | 0 | 0
| Timber (HTL-WD-01) double panel door, size 1450 x 2430mm (Non fire rated door) including frame as per DRAWING DLR-704-305 | 0 | No. | 0 |  |  |  | 0 | 0
| Timber single leaf connecting door, size 942 x 2549mm (60 minutes fire rated) as per DRAWING DLR-703-309 | 0 | No. | 0 |  |  |  | 0 | 0
13 | TYPE 03F (9 Nos)
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per Door type : HO-TB-01 | 9 | No. | 3361 | 30249 | 91.54% | 26260.6133 | 1428.425 | 27689.0383
| Timber (HTL-WD-01) double panel door, size 1480 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-03 | 9 | No. | 2701 | 24309 | 91.54% | 21103.8133 | 1147.925 | 22251.7383
14 | TYPE 01A (6 Nos)
| Entrance door, size 1170 x 2480mm (1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per Door type : HO-TB-01 | 6 | No. | 3361 | 20166 | 87.99% | 15601.3419 | 2142.6375 | 17743.9794
| Timber (HTL-WD-01) double panel door, size 914 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-04 | 6 | No. | 2286 | 13716 | 87.99% | 10611.3263 | 1457.325 | 12068.6512
| Timber (HTL-WD-01) double panel door, size 1115 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-05 | 6 | No. | 2347 | 14082 | 87.99% | 10894.4806 | 1496.2125 | 12390.6931
15 | TYPE 01B (6 Nos)
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per Door type : HO-TB-01 | 6 | No. | 3361 | 20166 | 97.77% | 19716.4663 | 0 | 19716.4663
| Timber (HTL-WD-01) double panel door, size 1054 x 2430mm (Non fire rated door) including frame as per DRAWING DLR-703-304 | 6 | No. | 0 |  |  |  | 0 | 0
| Timber (HTL-WD-01) double panel door, size 1054 x 2430mm (Non fire rated door) including frame as per DRAWING DLR-703-306 | 6 | No. | 0 |  |  |  | 0 | 0
16 | TYPE 01C (2 Nos)
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per Door type : HO-TB-01 | 2 | No. | 3361 | 6722 | 97.83% | 6576.3567 | 0 | 6576.3567
| Timber (HTL-WD-01) double panel door, size 914 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-04 | 2 | No. | 2286 | 4572 | 97.83% | 4472.94 | 0 | 4472.94
| Timber (HTL-WD-01) double panel door, size 1115 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-05 | 2 | No. | 2347 | 4694 | 97.83% | 4592.2967 | 0 | 4592.2967
| Timber single leaf connecting door, size 942 x 2549mm (60 minutes fire rated) as per Door type : HO-TB-02 | 1 | No. | 0 |  |  |  | 0 | 0
17 | TYPE 04A (4 Nos)
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per Door type : HO-TB-01 | 4 | No. | 3361 | 13444 | 97.83% | 13152.7133 | 0 | 13152.7133
| Timber (HTL-WD-01) double panel door, size 1054 x 2430mm (Non fire rated door) including frame as per DRAWING DLR-703-304 | 4 | No. | 0 |  |  |  | 0 | 0
| Timber (HTL-WD-01) double panel door, size 1054 x 2430mm (Non fire rated door) including frame as per DRAWING DLR-703-306 | 4 | No. | 0 |  |  |  | 0 | 0
Add | HO-TB-11; Guestroom Single leaf door; NFR S/O: 885mm x 2415mm | 4 | No. | 1538 | 6152 | 97.83% | 6018.7067 | 0 | 6018.7067
18 | TYPE 04B (1 No)
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per Door type : HO-TB-01 | 1 | No. | 3361 | 3361 | 97.75% | 3285.3775 | 0 | 3285.3775
| Timber (HTL-WD-01) double panel door, size 1054 x 2430mm (Non fire rated door) including frame as per DRAWING DLR-703-304 | 0 | No. | 0 |  |  |  | 0 | 0
| Timber (HTL-WD-01) double panel door, size 1054 x 2430mm (Non fire rated door) including frame as per DRAWING DLR-703-306 | 0 | No. | 0 |  |  |  | 0 | 0
Add | HO-TB-11; Guestroom Single leaf door; NFR S/O: 885mm x 2415mm | 1 | No. | 1538 | 1538 | 97.75% | 1503.395 | 0 | 1503.395
19 | TYPE 05A (9 Nos)
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per Door type : HO-TB-01 | 9 | No. | 3361 | 30249 | 89.81% | 25445.5708 | 1722.5125 | 27168.0833
| Timber (HTL-WD-01) double panel door, size 1054 x 2430mm (Non fire rated door) including frame as per DRAWING DLR-703-304 | 0 | No. | 0 |  |  |  | 0 | 0
| Timber (HTL-WD-01) double panel door, size 1054 x 2430mm (Non fire rated door) including frame as per DRAWING DLR-703-306 | 0 | No. | 0 |  |  |  | 0 | 0
| Timber single leaf connecting door, size 942 x 2549mm (60 minutes fire rated) as per DRAWING DLR-703-309 | 0 | No. | 0 |  |  |  | 0 | 0
20 | TYPE 06A (5 Nos)
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per Door type : HO-TB-01 | 5 | No. | 3361 | 16805 | 95% | 15292.55 | 672.2 | 15964.75
| Timber (HTL-WD-01) double panel door, size 1115 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-05 | 5 | No. | 2347 | 11735 | 95% | 10678.85 | 469.4 | 11148.25
| Timber (HTL-WD-01) double panel door, size 1054 x 2430mm (Non fire rated door) including frame as per DRAWING DLR-703-306 | 0 | No. | 0 |  |  |  | 0 | 0
21 | TYPE 07A (5 Nos)
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per Door type : HO-TB-01 | 5 | No | 0 |  |  |  | 0 | 0
22 | TYPE 07B (5 Nos)
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per DRAWING DLR-703-303 | 0 | No | 0 |  |  |  | 0 | 0
23 | TYPE 08A
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per Door type : HO-TB-01 | 5 | No. | 3361 | 16805 | 97.84% | 16442.2921 | 0 | 16442.2921
| Timber (HTL-WD-01) double panel door, size 1054 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-06 | 5 | No. | 2523 | 12615 | 97.84% | 12342.7262 | 0 | 12342.7262
| Timber (HTL-WD-01) double panel door, size 1054 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-11 | 10 | No. | 1538 | 15380 | 97.84% | 15048.0483 | 0 | 15048.0483
24 | TYPE 09A (02 No's)
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per Door type : HO-TB-01 | 2 | No. | 3361 | 6722 | 97.83% | 6576.3567 | 0 | 6576.3567
| Timber (HTL-WD-01) single panel door, size 1054 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-11 | 2 | No. | 1538 | 3076 | 97.83% | 3009.3533 | 0 | 3009.3533
| Timber (HTL-WD-01) double panel door, size 1115 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-05 | 2 | No. | 2347 | 4694 | 97.83% | 4592.2967 | 0 | 4592.2967
25 | TYPE 09B (02No's)
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per Door type : HO-TB-01 | 2 | No. | 3361 | 6722 | 97.75% | 6570.755 | 0 | 6570.755
| Timber (HTL-WD-01) single panel door, size 1054 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-11 | 2 | No. | 1538 | 3076 | 97.75% | 3006.79 | 0 | 3006.79
26 | TYPE 10A (05 No's)
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per Door type : HO-TB-01 | 5 | No. | 3361 | 16805 | 97.83% | 16440.8917 | 0 | 16440.8917
| Timber (HTL-WD-01) double panel door, size 1054 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-06 | 5 | No. | 2523 | 12615 | 97.83% | 12341.675 | 0 | 12341.675
| Timber (HTL-WD-01) single panel door, size 1054 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-11 | 5 | No. | 1538 | 7690 | 97.83% | 7523.3833 | 0 | 7523.3833
27 | TYPE 10B (03 No's)
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per Door type : HO-TB-01 | 3 | No. | 3361 | 10083 | 90.56% | 3276.975 | 5853.7417 | 9130.7167
| Timber (HTL-WD-01) double panel door, size 1480 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-03 | 3 | Nos | 2701 | 8103 | 90.56% | 2633.475 | 4704.2417 | 7337.7167
| Timber (HTL-WD-01) single panel door, size 1054 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-11 | 3 | No. | 1538 | 4614 | 90.56% | 1499.55 | 2678.6833 | 4178.2333
28 | TYPE 11A Non-interleading (1 No)
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per Door type : HO-TB-01, Ref: 1BS-1202-303 | 1 | No. | 3243 | 3243 | 97.5% | 3161.925 | 0 | 3161.925
| Timber (HTL-WD-01) double panel door, size 1054 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-12, Ref. 1BS-1202-308 | 1 | No. | 11725 | 11725 | 97.5% | 11431.875 | 0 | 11431.875
| Timber (HTL-WD-01) double single panel door, size 1054 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-XA, Ref: 1BS-1202-316 | 1 | No. | 7789 | 7789 | 97.5% | 7594.275 | 0 | 7594.275
29 | TYPE 11B Non-interleading (3 No's)
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per Door type : HO-TB-01, Ref: 1BS-1202-303 | 3 | No. | 3243 | 9729 | 91.25% | 4742.8875 | 4134.825 | 8877.7125
| Timber (HTL-WD-01) double panel door, size 1054 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-12, Ref. 1BS-1202-308 | 3 | No. | 11725 | 35175 | 91.25% | 17147.8125 | 14949.375 | 32097.1875
| Timber (HTL-WD-01) double single panel door, size 1054 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-XA, Ref: 1BS-1202-316 | 3 | No. | 7789 | 23367 | 91.25% | 11391.4125 | 9930.975 | 21322.3875
29 | TYPE 11C Interleading (11 No's)
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per Door type : HO-TB-01, Ref: 1BS-1202-303 | 11 | No. | 3243 | 35673 | 88.1% | 25130.5475 | 6296.825 | 31427.3725
| Timber (HTL-WD-01) double panel door, size 1054 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-12, Ref. 1BS-1202-308 | 11 | No. | 11725 | 128975 | 88.1% | 90858.9792 | 22766.0417 | 113625.0208
| Timber (HTL-WD-01) double single panel door, size 1054 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-XA, Ref: 1BS-1202-316 | 11 | No. | 7789 | 85679 | 88.1% | 60358.2592 | 15123.6417 | 75481.9008
29 | TYPE 11D Interleading (4 No's)
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per Door type : HO-TB-01, Ref: 1BS-1202-303 | 4 | No. | 3243 | 12972 | 60.94% | 7040.9133 | 864.8 | 7905.7133
| Timber (HTL-WD-01) double panel door, size 1054 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-12, Ref. 1BS-1202-308 | 4 | No. | 11725 | 46900 | 60.94% | 25456.2778 | 3126.6667 | 28582.9444
| Timber (HTL-WD-01) double single panel door, size 1054 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-XA, Ref: 1BS-1202-316 | 4 | No. | 7789 | 31156 | 60.94% | 16910.7844 | 2077.0667 | 18987.8511
30 | TYPE 12A (05 No's)
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per Door type : HO-TB-01 | 5 | No. | 3361 | 16805 | 97.37% | 16362.4683 | 0 | 16362.4683
| Timber (HTL-WD-01) double panel door, size 1054 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-06 | 5 | No. | 2523 | 12615 | 97.37% | 12282.805 | 0 | 12282.805
31 | TYPE 13A (01 No)
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per Door type : HO-TB-01 | 1 | No. | 3361 | 3361 | 97.5% | 3276.975 | 0 | 3276.975
| Timber (HTL-WD-01) double panel door, size 1480 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-03 | 1 | No. | 2701 | 2701 | 97.5% | 2633.475 | 0 | 2633.475
32 | TYPE 14A (04 No's)
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per Door type : HO-TB-01 | 4 | No. | 3361 | 13444 | 81.25% | 13107.9 | -2184.65 | 10923.25
| Timber (HTL-WD-01) double panel door, size 1480 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-03 | 4 | No. | 2701 | 10804 | 81.25% | 10533.9 | -1755.65 | 8778.25
2 BED SUITE ROOM
33 | TYPE 15A (2 Nos) No Drawings
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per DRAWING DLR-703-303 | 0 | No. | 0 |  |  |  | 0 | 0
JUNIOR SUITE ROOM
34 | TYPE 16A (03 No's)
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per Door type : HO-TB-01 | 3 | No. | 3361 | 10083 | 79.25% | 6562.3525 | 1428.425 | 7990.7775
| Timber (HTL-WD-01) double panel door, size 1115 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-05 | 3 | No. | 2347 | 7041 | 79.25% | 2464.35 | 3115.6425 | 5579.9925
PRESIDENTIAL SUITE ROOM
35 | TYPE 17A (01 No.) - No Drawings
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per DRAWING DLR-703-303 | 0 | No. | 0 |  |  |  | 0 | 0
ROYAL SUITE ROOM
36 | TYPE 18A (01 No's) - No Details
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per DRAWING DLR-703-303 | 0 | No. | 0 |  |  |  | 0 | 0
37 | TYPE 19A (06 No's)
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per Door type : HO-TB-01 | 6 | No. | 3361 | 20166 | 88.49% | 16415.6842 | 1428.425 | 17844.1092
| Timber (HTL-WD-01) double panel door, size 1480 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-03 | 6 | No. | 2701 | 16206 | 88.49% | 13192.1342 | 1147.925 | 14340.0592
PACKAGE 11 - TIMBER JOINERY (LUMPSUM)
DELUXE ROOM
TYPE -02A (13 No's)
DWG ref. P18-IDR-H-AL-T2A-001
1 | Wardrobe Type-2
Supply and install of Wardrobe consisting of HTL-WD-01 back panel, HTL-WD-02 shelf, frame, door, racks, shoe shelf, baseboard, drawer including all necessary fittings, fixing, accessories etc., complete as per Drg. No. P18-IDR-H-AL-BDR-072.1, Rev A, Dated 20-3-2019.
| Wardrobe with drawer unit; Size 1432 x 690 x 2400 mm | 13 | No. | 7426 | 96538 | 98% | 94607.24 | 0 | 94607.24
| Wardrobe with open shelf & hanger rail; Size 1432 x 690 x 2400 mm | 13 | No. | 7384 | 95992 | 98% | 94072.16 | 0 | 94072.16
Vanity cabinet consisting of Backlit washbasin counter (HTL-ST-12) invisible joint with stone veining continuity, Backlit niches, Cut moldings (HTL-PT-01), drawer, backlit tablet, skirting, including all necessary fittings, fixing, accessories, etc., complete as per Drg. No. DLR-704-312 (vanity top measured separately)
2 | Vanity counter Type 2 (Stoneworks by others)
| Size 1800 x 600 x 900mm | 13 | No. | 0 |  |  |  | 0 | 0
3 | Timber screen behind the minibar unit
Supply & installation of timber screen made of mdf panels in WD03 walnut high gloss finish as per given details.
| OAD : 610 + 1380mm L x 60mm THK x 2250mm H | 13 | No. | 2227 | 28951 | 98% | 28371.98 | 0 | 28371.98
4 | DB cabinets including shutter
Supply & installation of DB cabinets made with mdf carcass & shutter in painted finish HTL-PT-02 as per given drawing P18-IDR-H-AL-BDR-074.0, Rev A dated 20.03.2019.
| OAD : 700mm W x 250mm D x 2400mm H | 13 | No. | 1951 | 25363 | 98% | 24855.74 | 0 | 24855.74
TYPE -02B (16 Nos)
1 | Wardrobe Type-2
Supply and install of Wardrobe consisting of HTL-WD-01 back panel, HTL-WD-02 shelf, frame, door, racks, shoe shelf, baseboard, drawer including all necessary fittings, fixing, accessories etc., complete as per Drg. No. P18-IDR-H-AL-BDR-072.1, Rev A, Dated 20-3-2019.
| Wardrobe with drawer unit; Size 1432 x 690 x 2400 mm | 16 | No. | 7426 | 118816 | 97.33% | 115647.5733 | 0 | 115647.5733
| Wardrobe with open shelf & hanger rail; Size 1432 x 690 x 2400 mm | 16 | No. | 7384 | 118144 | 97.33% | 114993.4933 | 0 | 114993.4933
Vanity cabinet consisting of Backlit washbasin counter (HTL-ST-12) invisible joint with stone veining continuity, Backlit niches, Cut moldings (HTL-PT-01), drawer, backlit tablet, skirting, including all necessary fittings, fixing, accessories, etc., complete as per Drg. No. DLR-704-312 (vanity top measured separately)
2 | Vanity counter cabinet (Stoneworks by others)
| Size 1800 x 600 x 900mm | 16 | No. | 0 |  |  |  | 0 | 0
3 | Timber screen behind the minibar unit
Supply & installation of timber screen made of mdf panels in WD03 walnut high gloss finish as per given details.
| OAD : 610 + 1380mm L x 60mm THK x 2250mm H | 16 | No. | 2227 | 35632 | 95.86% | 32969.4978 | 1187.7333 | 34157.2311
4 | DB cabinets including shutter
Supply & installation of DB cabinets made with mdf carcass & shutter in painted finish HTL-PT-02 as per given drawing P18-IDR-H-AL-BDR-074.0, Rev A dated 20.03.2019.
| OAD : 700mm W x 250mm D x 2400mm H | 16 | No. | 1951 | 31216 | 86.78% | 18729.6 | 8358.9511 | 27088.5511
TYPE -02C (8 Nos)
1 | Wardrobe Type-2
Supply and install of Wardrobe consisting of HTL-WD-01 back panel, HTL-WD-02 shelf, frame, door, racks, shoe shelf, baseboard, drawer including all necessary fittings, fixing, accessories etc., complete as per Drg. No. P18-IDR-H-AL-BDR-072.1, Rev A, Dated 20-3-2019.
| Wardrobe with drawer unit; Size 1432 x 690 x 2400 mm | 8 | No. | 7426 | 59408 | 97.25% | 57774.28 | 0 | 57774.28
| Wardrobe with open shelf & hanger rail; Size 1432 x 690 x 2400 mm | 8 | No. | 7384 | 59072 | 97.25% | 57447.52 | 0 | 57447.52
Vanity cabinet consisting of Backlit washbasin counter (HTL-ST-12) invisible joint with stone veining continuity, Backlit niches, Cut moldings (HTL-PT-01), drawer, backlit tablet, skirting, including all necessary fittings, fixing, accessories, etc., complete as per Drg. No. DLR-704-312 (vanity top measured separately)
2 | Vanity counter cabinet (Stoneworks by others)
| Size 1800 x 600 x 900mm | 8 | No. | 0 |  |  |  | 0 | 0
3 | Timber screen behind the minibar unit
Supply & installation of timber screen made of mdf panels in WD03 walnut high gloss finish as per given details.
| OAD : 610 + 1380mm L x 60mm THK x 2250mm H | 8 | No. | 2227 | 17816 | 84.75% | 15099.06 | 0 | 15099.06
4 | DB cabinets including shutter
Supply & installation of DB cabinets made with mdf carcass & shutter in painted finish HTL-PT-02 as per given drawing P18-IDR-H-AL-BDR-074.0, Rev A dated 20.03.2019.
| OAD : 700mm W x 250mm D x 2400mm H | 8 | No. | 1951 | 15608 | 96% | 13325.33 | 1658.35 | 14983.68
TYPE -02D (7 Nos)
1 | Wardrobe Type-2
Supply and install of Wardrobe consisting of HTL-WD-01 back panel, HTL-WD-02 shelf, frame, door, racks, shoe shelf, baseboard, drawer including all necessary fittings, fixing, accessories etc., complete as per Drg. No. P18-IDR-H-AL-BDR-072.1, Rev A, Dated 20-3-2019.
| Wardrobe with drawer unit; Size 1432 x 690 x 2400 mm | 7 | No. | 7426 | 51982 | 95.86% | 49828.46 | 0 | 49828.46
| Wardrobe with open shelf & hanger rail; Size 1432 x 690 x 2400 mm | 7 | No. | 7384 | 51688 | 95.86% | 49546.64 | 0 | 49546.64
Vanity cabinet consisting of Backlit washbasin counter (HTL-ST-12) invisible joint with stone veining continuity, Backlit niches, Cut moldings (HTL-PT-01), drawer, backlit tablet, skirting, including all necessary fittings, fixing, accessories, etc., complete as per Drg. No. DLR-704-312 (vanity top measured separately)
2 | Vanity counter cabinet (Stoneworks by others)
| Size 1800 x 600 x 900mm | 7 | No. | 0 |  |  |  | 0 | 0
3 | Timber screen behind the minibar unit
Supply & installation of timber screen made of mdf panels in WD03 walnut high gloss finish as per given details.
| OAD : 610 + 1380mm L x 60mm THK x 2250mm H | 7 | No. | 2227 | 15589 | 95.64% | 14909.765 | 0 | 14909.765
4 | DB cabinets including shutter
Supply & installation of DB cabinets made with mdf carcass & shutter in painted finish HTL-PT-02 as per given drawing P18-IDR-H-AL-BDR-074.0, Rev A dated 20.03.2019.
| OAD : 700mm W x 250mm D x 2400mm H | 7 | No. | 1951 | 13657 | 80.86% | 9384.31 | 1658.35 | 11042.66
TYPE -02E (9 Nos)
1 | Wardrobe Type-2
Supply and install of Wardrobe consisting of HTL-WD-01 back panel, HTL-WD-02 shelf, frame, door, racks, shoe shelf, baseboard, drawer including all necessary fittings, fixing, accessories etc., complete as per Drg. No. P18-IDR-H-AL-BDR-072.1, Rev A, Dated 20-3-2019.
| Wardrobe with drawer unit; Size 1432 x 690 x 2400 mm | 9 | No. | 7426 | 66834 | 96.67% | 65302.3875 | -696.1875 | 64606.2
| Wardrobe with open shelf & hanger rail; Size 1432 x 690 x 2400 mm | 9 | No. | 7384 | 66456 | 96.67% | 64933.05 | -692.25 | 64240.8
Vanity cabinet consisting of Backlit washbasin counter (HTL-ST-12) invisible joint with stone veining continuity, Backlit niches, Cut moldings (HTL-PT-01), drawer, backlit tablet, skirting, including all necessary fittings, fixing, accessories, etc., complete as per Drg. No. DLR-704-312 (vanity top measured separately)
2 | Vanity counter cabinet (Stoneworks by others)
| Size 1800 x 600 x 900mm | 9 | No. | 0 |  |  |  | 0 | 0
3 | Timber screen behind the minibar unit
Supply & installation of timber screen made of mdf panels in WD03 walnut high gloss finish as per given details.
| OAD : 610 + 1380mm L x 60mm THK x 2250mm H | 9 | No. | 2227 | 20043 | 92% | 17103.36 | 1336.2 | 18439.56
4 | DB cabinets including shutter
Supply & installation of DB cabinets made with mdf carcass & shutter in painted finish HTL-PT-02 as per given drawing P18-IDR-H-AL-BDR-074.0, Rev A dated 20.03.2019.
| OAD : 700mm W x 250mm D x 2400mm H | 9 | No. | 1951 | 17559 | 86.11% | 15120.25 | 0 | 15120.25
TYPE -02F (8 Nos)
1 | Wardrobe Type-2C
Supply and install of Wardrobe consisting of HTL-WD-01 back panel, HTL-WD-02 shelf, frame, door, racks, shoe shelf, baseboard, drawer including all necessary fittings, fixing, accessories etc., complete as per Drg. No. P18-IDR-H-AL-BDR-072.4, Rev A, Dated 05-04-2019.
| Wardrobe with drawer unit; Size 800 x 755 x 2400 mm | 8 | No. | 4957 | 39656 | 96.5% | 38565.46 | -297.42 | 38268.04
| Wardrobe with open shelf & hanger rail; Size 2064 x 720 x 2400 mm | 8 | No. | 9776 | 78208 | 96.5% | 76057.28 | -586.56 | 75470.72
Vanity cabinet consisting of Backlit washbasin counter (HTL-ST-12) invisible joint with stone veining continuity, Backlit niches, Cut moldings (HTL-PT-01), drawer, backlit tablet, skirting, including all necessary fittings, fixing, accessories, etc., complete as per Drg. No. DLR-704-312 (vanity top measured separately)
2 | Vanity counter cabinet (Stoneworks by others)
| Size 900 1800 x 600 x 900mm | 8 | No. | 0 |  |  |  | 0 | 0
3 | Timber screen behind the minibar unit
Supply & installation of timber screen made of mdf panels in WD03 walnut high gloss finish as per given details.
| OAD : 610 + 1380mm L x 60mm THK x 2250mm H | 8 | No. | 2227 | 17816 | 91.25% | 15099.06 | 1158.04 | 16257.1
4 | DB cabinets including shutter
Supply & installation of DB cabinets made with mdf carcass & shutter in painted finish HTL-PT-02 as per given drawing P18-IDR-H-AL-BDR-074.0, Rev A dated 20.03.2019.
| OAD : 700mm W x 250mm D x 2400mm H | 8 | No. | 1951 | 15608 | 84.62% | 13325.33 | -117.06 | 13208.27
TYPE -02G (9 Nos)
1 | Wardrobe
Supply and install of Wardrobe consisting of HTL-WD-01 back panel, HTL-WD-02 shelf, frame, door, racks, shoe shelf, baseboard, drawer including all necessary fittings, fixing, accessories etc., complete as per Drg. No. P18-IDR-H-AL-BDR-072.1, Rev A, Dated 20-3-2019.
| Wardrobe with drawer unit; Size 1432 x 690 x 2400 mm | 9 | No. | 7426 | 66834 | 96.67% | 52619.3983 | 11986.8017 | 64606.2
| Wardrobe with open shelf & hanger rail; Size 1432 x 690 x 2400 mm | 9 | No. | 7384 | 66456 | 96.67% | 52321.7933 | 11919.0067 | 64240.8
Vanity cabinet consisting of Backlit washbasin counter (HTL-ST-12) invisible joint with stone veining continuity, Backlit niches, Cut moldings (HTL-PT-01), drawer, backlit tablet, skirting, including all necessary fittings, fixing, accessories, etc., complete as per Drg. No. DLR-704-312 (vanity top measured separately)
2 | Vanity counter cabinet (Stoneworks by others)
| Size 1500 x 600 x 900mm | 9 | No. | 0 |  |  |  | 0 | 0
3 | Timber screen behind the minibar unit
Supply & installation of timber screen made of mdf panels in WD03 walnut high gloss finish as per given details.
| OAD : 610 + 1380mm L x 60mm THK x 2250mm H | 9 | No. | 2227 | 20043 | 96.17% | 19274.685 | 0 | 19274.685
4 | DB cabinets including shutter
Supply & installation of DB cabinets made with mdf carcass & shutter in painted finish HTL-PT-02 as per given drawing P18-IDR-H-AL-BDR-074.0, Rev A dated 20.03.2019.
| OAD : 700mm W x 250mm D x 2400mm H | 9 | No. | 1951 | 17559 | 97% | 17032.23 | 0 | 17032.23
TYPE -02H (1 No)
1 | Wardrobe Type-2C
Supply and install of Wardrobe consisting of HTL-WD-01 back panel, HTL-WD-02 shelf, frame, door, racks, shoe shelf, baseboard, drawer including all necessary fittings, fixing, accessories etc., complete as per Drg. No. P18-IDR-H-AL-BDR-072.4, Rev A, Dated 05-04-2019.
| Wardrobe with drawer unit; Size 800 x 755 x 2400 mm | 1 | No. | 4957 | 4957 | 97.25% | 4820.6825 | 0 | 4820.6825
| Wardrobe with open shelf & hanger rail; Size 2064 x 720 x 2400 mm | 1 | No. | 9776 | 9776 | 97.25% | 9507.16 | 0 | 9507.16
Vanity cabinet consisting of Backlit washbasin counter (HTL-ST-12) invisible joint with stone veining continuity, Backlit niches, Cut moldings (HTL-PT-01), drawer, backlit tablet, skirting, including all necessary fittings, fixing, accessories, etc., complete as per Drg. No. DLR-704-312 (vanity top measured separately)
2 | Vanity counter cabinet (Stoneworks by others)
| Size 900 1800 x 600 x 900mm | 1 | No. | 0 |  |  |  | 0 | 0
3 | Timber screen behind the minibar unit
Supply & installation of timber screen made of mdf panels in WD03 walnut high gloss finish as per given details.
| OAD : 610 + 1380mm L x 60mm THK x 2250mm H | 1 | No. | 2227 | 2227 | 98% | 1887.3825 | 295.0775 | 2182.46
4 | DB cabinets including shutter
Supply & installation of DB cabinets made with mdf carcass & shutter in painted finish HTL-PT-02 as per given drawing P18-IDR-H-AL-BDR-074.0, Rev A dated 20.03.2019.
| OAD : 700mm W x 250mm D x 2400mm H | 1 | No. | 1951 | 1951 | 98% | 1665.6663 | 246.3137 | 1911.98
TYPE -03A (13 Nos)
1 | Wardrobe
Supply and install of Wardrobe consisting of HTL-WD-01 back panel, HTL-WD-02 shelf, frame, door, racks, shoe shelf, baseboard, drawer including all necessary fittings, fixing, accessories etc., complete as per Drg. No. P18-IDR-H-AL-BDR-072.0, Rev B, Dated 20-03-2019.
| Wardrobe with drawer units : Size 1190x 630 x 2400mm | 13 | No. | 6044 | 78572 | 96.6% | 75900.552 | 0 | 75900.552
| Wardrobe with open shelf & hanger rail; Size 1990 x 690 x 2400 mm | 13 | No. | 6444 | 83772 | 96.6% | 80923.752 | 0 | 80923.752
| Minibar unit; Size 740 x 610 x 2430 mm | 13 | No. | 4820 | 62660 | 93.67% | 58691.5333 | 0 | 58691.5333
Drawing Ref. P18-IDR-H-AL-BDR-073.0 Rev A, dated 20.03.2019.
Vanity cabinet consisting of Backlit washbasin counter (HTL-ST-12) invisible joint with stone veining continuity, Backlit niches, Cut moldings (HTL-PT-01), drawer, backlit tablet, skirting, including all necessary fittings, fixing, accessories, etc., complete as per Drg. No. DLR-704-312 (vanity top measured separately)
2 | Vanity counter cabinet (Stoneworks by others)
| Size 2800 x 600 x 900mm | 13 | No. | 0 |  |  |  | 0 | 0
4 | DB cabinets including shutter
Supply & installation of DB cabinets made with mdf carcass & shutter in painted finish HTL-PT-02 as per given drawing P18-IDR-H-AL-BDR-074.0, Rev A dated 20.03.2019.
| OAD : 780mm W x 280mm D x 2400mm H | 13 | No. | 1951 | 25363 | 90.47% | 15217.8 | 7727.2607 | 22945.0607
5 | Supply & installation of timber cladding near wardrobe 1B, HTL-WD01 timber finish as per given drawing & specification. Drawing ref. P18-IDR-H-AL-BDR-072.0, Dated 20.03.2019.
| OAD : 2550mm H x 965mm W | 13 | No. | 1076 | 13988 |  | 0 | 0 | 0
Electrical switches, HTL-PT-02 painted board finish skiritng etc are excluded as per per Technical clarification 02
3 | Timber screen behind the minibar unit
Supply & installation of timber screen made of mdf panels in WD03 walnut high gloss finish as per given details.
| OAD : 610 + 1380mm L x 60mm THK x 2250mm H | 13 | No. | 2227 | 28951 | 95.83% | 27744.7083 | 0 | 27744.7083
Type - 03B (2 Nos.) Layout not provided.
Details followed as per Mock up room 704
1 | Wardrobe
Supply and install of Wardrobe consisting of HTL-WD-01 back panel, HTL-WD-02 shelf, frame, door, racks, shoe shelf, baseboard, drawer including all necessary fittings, fixing, accessories etc., complete as per Drg. No. DLR-704-318 & 319.
| Wardrobe with drawer units : Size 1190x 630 x 2400mm | 0 | No. | 0 |  |  |  | 0 | 0
| Wardrobe with open shelf & hanger rail; Size 1990 x 690 x 2400 mm | 0 | No. | 0 |  |  |  | 0 | 0
| Minibar unit; Size 740 x 610 x 2430 mm | 0 | No. | 0 |  |  |  | 0 | 0
Vanity cabinet consisting of Backlit washbasin counter (HTL-ST-12) invisible joint with stone veining continuity, Backlit niches, Cut moldings (HTL-PT-01), drawer, backlit tablet, skirting, including all necessary fittings, fixing, accessories, etc., complete as per Drg. No. DLR-704-312 (vanity top measured separately)
2 | Vanity counter cabinet (Stoneworks by others)
| Size 2800 x 600 x 900mm | 0 | No. | 0 |  |  |  | 0 | 0
TYPE -03C (9 Nos)
1 | Wardrobe
Supply and install of Wardrobe consisting of HTL-WD-01 back panel, HTL-WD-02 shelf, frame, door, racks, shoe shelf, baseboard, drawer including all necessary fittings, fixing, accessories etc., complete as per Drg. No. P18-IDR-H-AL-BDR-072.0, Rev B, Dated 20-03-2019.
| Wardrobe with drawer units : Size 1190x 630 x 2400mm | 9 | No. | 6044 | 54396 | 96.67% | 52582.8 | 0 | 52582.8
| Wardrobe with open shelf & hanger rail; Size 1990 x 690 x 2400 mm | 9 | No. | 6444 | 57996 | 96.67% | 56062.8 | 0 | 56062.8
| Minibar unit; Size 740 x 610 x 2430 mm | 9 | No. | 4820 | 43380 | 93.89% | 40729 | 0 | 40729
Drawing Ref. P18-IDR-H-AL-BDR-073.0 Rev A, dated 20.03.2019.
Vanity cabinet consisting of Backlit washbasin counter (HTL-ST-12) invisible joint with stone veining continuity, Backlit niches, Cut moldings (HTL-PT-01), drawer, backlit tablet, skirting, including all necessary fittings, fixing, accessories, etc., complete as per Drg. No. DLR-704-312 (vanity top measured separately)
2 | Vanity counter cabinet (Stoneworks by others)
| Size 2800 x 600 x 900mm | 9 | No. | 0 |  |  |  | 0 | 0
3 | DB cabinets including shutter
Supply & installation of DB cabinets made with mdf carcass & shutter in painted finish HTL-PT-02 as per given drawing P18-IDR-H-AL-BDR-074.0, Rev A dated 20.03.2019.
| OAD : 780mm W x 280mm D x 2400mm H | 9 | No. | 1951 | 17559 | 86.11% | 15120.25 | 0 | 15120.25
4 | Supply & installation of timber cladding near wardrobe 1B, HTL-WD01 timber finish as per given drawing & specification. Drawing ref. P18-IDR-H-AL-BDR-072.0, Dated 20.03.2019.
| OAD : 2550mm H x 965mm W | 9 | No. | 1076 | 9684 | 96.67% | 9361.2 | 0 | 9361.2
Electrical switches, HTL-PT-02 painted board finish skiritng etc are excluded as per per Technical clarification 02
5 | Timber screen behind the minibar unit
Supply & installation of timber screen made of mdf panels in WD03 walnut high gloss finish as per given details.
| OAD : 610 + 1380mm L x 60mm THK x 2250mm H | 9 | No. | 2227 | 20043 | 96.17% | 19274.685 | 0 | 19274.685
TYPE -03D (18 Nos)
1 | Wardrobe
Supply and install of Wardrobe consisting of HTL-WD-01 back panel, HTL-WD-02 shelf, frame, door, racks, shoe shelf, baseboard, drawer including all necessary fittings, fixing, accessories etc., complete as per Drg. No. P18-IDR-H-AL-BDR-072.0, Rev B, Dated 20-03-2019.
| Wardrobe with drawer units : Size 1190x 630 x 2400mm | 18 | No. | 6044 | 108792 | 97.4% | 105963.408 | 0 | 105963.408
| Wardrobe with open shelf & hanger rail; Size 1990 x 690 x 2400 mm | 18 | No. | 6444 | 115992 | 97.4% | 112976.208 | 0 | 112976.208
| Minibar unit; Size 740 x 610 x 2430 mm | 18 | No. | 4820 | 86760 | 95% | 82422 | 0 | 82422
Drawing Ref. P18-IDR-H-AL-BDR-073.0 Rev A, dated 20.03.2019.
Vanity cabinet consisting of Backlit washbasin counter (HTL-ST-12) invisible joint with stone veining continuity, Backlit niches, Cut moldings (HTL-PT-01), drawer, backlit tablet, skirting, including all necessary fittings, fixing, accessories, etc., complete as per Drg. No. DLR-704-312 (vanity top measured separately)
2 | Vanity counter cabinet (Stoneworks by others)
| Size 2800 x 600 x 900mm | 18 | No. | 0 |  |  |  | 0 | 0
4 | DB cabinets including shutter
Supply & installation of DB cabinets made with mdf carcass & shutter in painted finish HTL-PT-02 as per given drawing P18-IDR-H-AL-BDR-074.0, Rev A dated 20.03.2019.
| OAD : 780mm W x 280mm D x 2400mm H | 18 | No. | 1951 | 35118 | 97.7% | 34310.286 | 0 | 34310.286
5 | Supply & installation of timber cladding near wardrobe 1B, HTL-WD01 timber finish as per given drawing & specification. Drawing ref. P18-IDR-H-AL-BDR-072.0, Dated 20.03.2019.
| OAD : 2550mm H x 965mm W | 18 | No. | 1076 | 19368 | 97.4% | 18922.536 | -58.104 | 18864.432
Electrical switches, HTL-PT-02 painted board finish skiritng etc are excluded as per per Technical clarification 02
3 | Timber screen behind the minibar unit
Supply & installation of timber screen made of mdf panels in WD03 walnut high gloss finish as per given details.
| OAD : 610 + 1380mm L x 60mm THK x 2250mm H | 18 | No. | 2227 | 40086 | 97.58% | 39113.9145 | 0 | 39113.9145
Type - 03E (2 Nos.) Updated layout not provided.
Details followed as per Mock up room 704
1 | Wardrobe
Supply and install of Wardrobe consisting of HTL-WD-01 back panel, HTL-WD-02 shelf, frame, door, racks, shoe shelf, baseboard, drawer including all necessary fittings, fixing, accessories etc., complete as per Drg. No. DLR-704-318 & 319.
| Wardrobe with drawer units : Size 1190x 630 x 2400mm | 0 | No. | 0 |  |  |  | 0 | 0
| Wardrobe with open shelf & hanger rail; Size 1990 x 690 x 2400 mm | 0 | No. | 0 |  |  |  | 0 | 0
| Minibar unit; Size 740 x 610 x 2430 mm | 0 | No. | 0 |  |  |  | 0 | 0
Vanity cabinet consisting of Backlit washbasin counter (HTL-ST-12) invisible joint with stone veining continuity, Backlit niches, Cut moldings (HTL-PT-01), drawer, backlit tablet, skirting, including all necessary fittings, fixing, accessories, etc., complete as per Drg. No. DLR-704-312 (vanity top measured separately)
2 | Vanity counter cabinet (Stoneworks by others)
| Size 2800 x 600 x 900mm | 0 | No. | 0 |  |  |  | 0 | 0
TYPE -03F (9 Nos)
1 | Wardrobe
Supply and install of Wardrobe consisting of HTL-WD-01 back panel, HTL-WD-02 shelf, frame, door, racks, shoe shelf, baseboard, drawer including all necessary fittings, fixing, accessories etc., complete as per Drg. No. P18-IDR-H-AL-BDR-072.0, Rev B, Dated 20-03-2019.
| Wardrobe with drawer units : Size 1190x 630 x 2400mm | 9 | No. | 6044 | 54396 | 96.67% | 52582.8 | 0 | 52582.8
| Wardrobe with open shelf & hanger rail; Size 1990 x 690 x 2400 mm | 9 | No. | 6444 | 57996 | 96.67% | 56062.8 | 0 | 56062.8
| Minibar unit; Size 740 x 610 x 2430 mm | 9 | No. | 4820 | 43380 | 93.89% | 41934 | -1205 | 40729
Drawing Ref. P18-IDR-H-AL-BDR-073.0 Rev A, dated 20.03.2019.
Vanity cabinet consisting of Backlit washbasin counter (HTL-ST-12) invisible joint with stone veining continuity, Backlit niches, Cut moldings (HTL-PT-01), drawer, backlit tablet, skirting, including all necessary fittings, fixing, accessories, etc., complete as per Drg. No. DLR-704-312 (vanity top measured separately)
2 | Vanity counter cabinet (Stoneworks by others)
| Size 2800 x 600 x 900mm | 9 | No. | 0 |  |  |  | 0 | 0
4 | DB cabinets including shutter
Supply & installation of DB cabinets made with mdf carcass & shutter in painted finish HTL-PT-02 as per given drawing P18-IDR-H-AL-BDR-074.0, Rev A dated 20.03.2019.
| OAD : 900mm W x 300mm D x 2400mm H | 9 | No. | 2234 | 20106 | 86.11% | 17313.5 | 0 | 17313.5
5 | Supply & installation of timber cladding near wardrobe 1B, HTL-WD01 timber finish as per given drawing & specification. Drawing ref. P18-IDR-H-AL-BDR-072.0, Dated 20.03.2019.
| OAD : 2550mm H x 965mm W | 9 | No. | 1076 | 9684 | 96.67% | 9361.2 | 0 | 9361.2
Electrical switches, HTL-PT-02 painted board finish skiritng etc are excluded as per per Technical clarification 02
5 | Timber screen behind the minibar unit
Supply & installation of timber screen made of mdf panels in WD03 walnut high gloss finish as per given details.
| OAD : 610 + 1380mm L x 60mm THK x 2250mm H | 9 | No. | 2227 | 20043 | 96.17% | 19274.685 | 0 | 19274.685
TYPE -01A (6 Nos)
1 | Wardrobe
Supply and install of Wardrobe consisting of HTL-WD-01 back panel, HTL-WD-02 shelf, frame, door, racks, shoe shelf, baseboard, drawer including all necessary fittings, fixing, accessories etc., complete as per Drg. No. P18-IDR-H-AL-BDR-072.11, Rev A, Dated 17-04-2019.
| Wardrobe with drawer unit; Size 1450 x 735 x 2465 mm | 6 | No. | 7176 | 43056 | 96.5% | 41549.04 | 0 | 41549.04
| Wardrobe with open shelf & hanger rail; Size 1400 x 700 x 2465 mm | 6 | No. | 5140 | 30840 | 96.5% | 29760.6 | 0 | 29760.6
Vanity cabinet consisting of Backlit washbasin counter (HTL-ST-12) invisible joint with stone veining continuity, Backlit niches, Cut moldings (HTL-PT-01), drawer, backlit tablet, skirting, including all necessary fittings, fixing, accessories, etc., complete as per Drg. No. DLR-704-312 (vanity top measured separately)
2 | Vanity counter cabinet (Stoneworks by others)
| Size: 1800 x 600 x 900mm | 6 | No. | 0 |  |  |  | 0 | 0
TYPE -01B (6 Nos)
1 | Wardrobe
Supply and install of Wardrobe consisting of HTL-WD-01 back panel, HTL-WD-02 shelf, frame, door, racks, shoe shelf, baseboard, drawer including all necessary fittings, fixing, accessories etc., complete as per Drg. No. P18-IDR-H-AL-BDR-072.9, Rev A, Dated 05-04-2019.
| Wardrobe with drawer unit; Size 2820 x 710 x 2515 mm | 6 | No. | 13880 | 83280 | 98% | 81614.4 | 0 | 81614.4
Vanity cabinet consisting of Backlit washbasin counter (HTL-ST-12) invisible joint with stone veining continuity, Backlit niches, Cut moldings (HTL-PT-01), drawer, backlit tablet, skirting, including all necessary fittings, fixing, accessories, etc., complete as per Drg. No. DLR-704-312 (vanity top measured separately)
2 | Vanity counter cabinet (Stoneworks by others)
| Size 2100 x 600 x 900mm | 6 | No. | 0 |  |  |  | 0 | 0
3 | DB cabinets including shutter
Supply & installation of DB cabinets made with mdf carcass & shutter in painted finish HTL-PT-02 as per given drawing P18-IDR-H-AL-BDR-074.0, Rev A dated 20.03.2019.
| OAD : 660mm W x 210mm D x 2400mm H | 6 | No. | 1951 | 11706 | 98% | 11471.88 | 0 | 11471.88
4 | Minibar unit; Size 740 x 610 x 2430 mm | 6 | No. | 4820 | 28920 | 95% | 27474 | 0 | 27474
Drawing Ref. P18-IDR-H-AL-BDR-073.0 Rev A, dated 20.03.2019.
TYPE -01C (2 Nos)
1 | Bedroom Wardrobe Type 5
Supply and install of Wardrobe consisting of HTL-WD-01 back panel, HTL-WD-02 shelf, frame, door, racks, shoe shelf, baseboard, drawer including all necessary fittings, fixing, accessories etc., complete as per Drg. No. P18-IDR-H-AL-BDR-072.11, Rev A, Dated 17-04-2019.
| Wardrobe with drawer unit; Size 1450 x 735 x 2465 mm | 2 | No. | 7176 | 14352 | 98% | 14064.96 | 0 | 14064.96
| Wardrobe with open shelf & hanger rail; Size 1400 x 700 x 2465 mm | 2 | No. | 5140 | 10280 | 98% | 10074.4 | 0 | 10074.4
Vanity cabinet consisting of Backlit washbasin counter (HTL-ST-12) invisible joint with stone veining continuity, Backlit niches, Cut moldings (HTL-PT-01), drawer, backlit tablet, skirting, including all necessary fittings, fixing, accessories, etc., complete as per Drg. No. DLR-704-312 (vanity top measured separately)
2 | Vanity counter cabinet (Stoneworks by others)
| Size: 1800 x 600 x 900mm | 2 | No. | 0 |  |  |  | 0 | 0
TYPE -04A (4 Nos)
1 | Wardrobe Type - 2
Supply and install of Wardrobe consisting of HTL-WD-01 back panel, HTL-WD-02 shelf, frame, door, racks, shoe shelf, baseboard, drawer including all necessary fittings, fixing, accessories etc., complete as per Drg. No. P18-IDR-H-AL-BDR-072.4, Rev A, Dated 05-04-2019.
| Wardrobe with drawer unit; Size 2864 x 720 x 2400 mm | 4 | No. | 14808 | 59232 | 98% | 58047.36 | 0 | 58047.36
Vanity cabinet consisting of Backlit washbasin counter (HTL-ST-12) invisible joint with stone veining continuity, Backlit niches, Cut moldings (HTL-PT-01), drawer, backlit tablet, skirting, including all necessary fittings, fixing, accessories, etc., complete as per Drg. No. DLR-704-312 (vanity top measured separately)
2 | Vanity counter cabinet (Stoneworks by others)
| Size 1800 x 600 x 900mm | 4 | No. | 0 |  |  |  | 0 | 0
| Size 2100 x 600 x 900mm | 4 | No. | 0 |  |  |  | 0 | 0
4 | DB cabinets including shutter
Supply & installation of DB cabinets made with mdf carcass & shutter in painted finish HTL-PT-02 as per given drawing P18-IDR-H-AL-BDR-074.0, Rev A dated 20.03.2019.
| OAD : 900mm W x 300mm D x 2400mm H | 4 | No. | 2234 | 8936 | 98% | 8757.28 | 0 | 8757.28
| Minibar unit; Size 740 x 610 x 2430 mm | 4 | No. | 4820 | 19280 | 95% | 18316 | 0 | 18316
Drawing Ref. P18-IDR-H-AL-BDR-073.0 Rev A, dated 20.03.2019.
TYPE -04B (1 No)
1 | Wardrobe Type - 2
Supply and install of Wardrobe consisting of HTL-WD-01 back panel, HTL-WD-02 shelf, frame, door, racks, shoe shelf, baseboard, drawer including all necessary fittings, fixing, accessories etc., complete as per Drg. No. P18-IDR-H-AL-BDR-072.4, Rev A, Dated 05-04-2019.
| Wardrobe with drawer unit; Size 2864 x 720 x 2400 mm | 1 | No. | 14808 | 14808 | 100% | 14808 | 0 | 14808
Vanity cabinet consisting of Backlit washbasin counter (HTL-ST-12) invisible joint with stone veining continuity, Backlit niches, Cut moldings (HTL-PT-01), drawer, backlit tablet, skirting, including all necessary fittings, fixing, accessories, etc., complete as per Drg. No. DLR-704-312 (vanity top measured separately)
2 | Vanity counter cabinet (Stoneworks by others)
| Size 1900 x 600 x 900mm | 1 | No. | 0 |  |  |  | 0 | 0
DB cabinets including shutter
4 | Supply & installation of DB cabinets made with mdf carcass & shutter in painted finish HTL-PT-02 as per given drawing P18-IDR-H-AL-BDR-074.0, Rev A dated 20.03.2019.
| OAD : 900mm W x 300mm D x 2400mm H | 1 | No. | 2234 | 2234 | 98% | 2189.32 | 0 | 2189.32
5 | Minibar unit; Size 740 x 610 x 2430 mm | 1 | No. | 4820 | 4820 | 95% | 4579 | 0 | 4579
Drawing Ref. P18-IDR-H-AL-BDR-073.0 Rev A, dated 20.03.2019.
TYPE -05A (9 Nos)
1 | Wardrobe
Supply and install of Wardrobe consisting of HTL-WD-01 back panel, HTL-WD-02 shelf, frame, door, racks, shoe shelf, baseboard, drawer including all necessary fittings, fixing, accessories etc., complete as per Drg. No. P18-IDR-H-AL-BDR-072.10, Rev A, Dated 05-04-2019.
| Wardrobe with drawer unit; Size 2801 x 750 x 2745 mm | 9 | No. | 14382 | 129438 | 96.67% | 125123.4 | 0 | 125123.4
Vanity cabinet consisting of Backlit washbasin counter (HTL-ST-12) invisible joint with stone veining continuity, Backlit niches, Cut moldings (HTL-PT-01), drawer, backlit tablet, skirting, including all necessary fittings, fixing, accessories, etc., complete as per Drg. No. DLR-704-312 (vanity top measured separately)
2 | Vanity counter cabinet (Stoneworks by others)
| Size 1900 x 600 x 900mm | 9 | No. | 0 |  |  |  | 0 | 0
4 | DB cabinets including shutter
Supply & installation of DB cabinets made with mdf carcass & shutter in painted finish HTL-PT-02 as per given drawing P18-IDR-H-AL-BDR-074.0, Rev A dated 20.03.2019.
| OAD : 900mm W x 300mm D x 2400mm H | 9 | No. | 2234 | 20106 | 86.11% | 17313.5 | 0 | 17313.5
5 | Minibar unit; Size 954 x 640 x 2430 | 9 | No. | 7416 | 66744 | 93.89% | 62665.2 | 0 | 62665.2
Drawing Ref. P18-IDR-H-AL-BDR-073.2, dated 20.03.2019.
TYPE -06A (5 Nos)
1 | Wardrobe
Supply and install of Wardrobe consisting of HTL-WD-01 back panel, HTL-WD-02 shelf, frame, door, racks, shoe shelf, baseboard, drawer including all necessary fittings, fixing, accessories etc., complete as per Drg. No. P18-IDR-H-AL-BDR-072.5, Rev A, Dated 05-04-2019.
| Wardrobe with drawer unit; Size 3682 x 720 x 2550 mm | 5 | No. | 13752 | 68760 | 97.4% | 66972.24 | 0 | 66972.24
4 | DB cabinets including shutter
Supply & installation of DB cabinets made with mdf carcass & shutter in painted finish HTL-PT-02 as per given drawing P18-IDR-H-AL-BDR-074.0, Rev A dated 20.03.2019.
| OAD : 900mm W x 300mm D x 2400mm H | 5 | No. | 2234 | 11170 | 95.4% | 8757.28 | 1898.9 | 10656.18
TYPE 07A (5 Nos) - 1 Bed Duplex Suite
Tenderers to list and price joinery items as per 100% DD issued for 1 bed duplex through Post Tender Addendum 06 dated 11 Jun 2019
1 | Entrance Closet
Supply and install of Wardrobe consisting of HTL-WD-12 back panel, HTL-WD-09 shelf, frame, door including all necessary fittings, fixing, accessories etc., complete as per Drg. No. D1BS-707-208, Rev A, Dated 29-04-2019. Marble finish to shutters is excluded
| Size 1160 x 600/460/215 x 2405 mm | 5 | No. | 2591 | 12955 | 81.6% | 10571.28 | 0 | 10571.28
2 | Bedroom Wardrobe
Supply and install of Wardrobe consisting of HTL-WD-01 back panel, HTL-WD-02 shelf, frame, door, racks, shoe shelf, baseboard, drawer including all necessary fittings, fixing, accessories etc., complete as per Drg. No. D1BS-707-319, Rev A, Dated 29-04-2019.
| Size 3430 x 710/860 x 2550 mm | 5 | No. | 13430 | 67150 | 81.6% | 54794.4 | 0 | 54794.4
| Size 1284 x 640 x 2550 mm | 5 | No. | 5853 | 29265 | 81.6% | 23880.24 | 0 | 23880.24
| Size 1134 x 640 x 2550 mm | 5 | No. | 2973 | 14865 | 81.6% | 12129.84 | 0 | 12129.84
3 | Vanity cabinet (Stoneworks by others)
Vanity cabinet consisting of HTL-WD-09 back panel, shelf, frame, door, including all necessary fittings, fixing, accessories etc., complete as per Drg. No. D1BS-707-330-332, Rev A, Dated 29-04-2019. (vanity top & metal legs measured separately)
| Master vanity cabinet size: 800 x 300 x 2550mm | 10 | No. | 1918 | 19180 | 20% | 0 | 3836 | 3836
4 | Minibar base unit
Minibar cabinet consisting of HTL-WD-09 shelf, frame, door, including all necessary fittings, fixing, accessories etc., complete as per Drg. No. D1BS-707-310-312 Rev A, dated 29.04.2019. Stone top, door finish, credenza, shelves & skirting are excluded
| Size 1530 x 680 | 5 | No. | 3044 | 15220 | 16% | 3044 | -608.8 | 2435.2
5 | Electrical Panel
Supply & installation of electrical cabinet made with mdf carcass & shutter in HTL-GL-01 mirror as per Drg. No. D1BS-707-307, Rev A dated 29.04.2019.
| Size 1240 x 295 x 2605mm | 5 | No. | 3282 | 16410 | 85.2% | 13981.32 | 0 | 13981.32
Supply & installation of electrical cabinet made with mdf carcass & shutter in HTL-WD-01 as per Drg. No. D1BS-707-307, Rev A dated 29.04.2019.
| Size 500 x 480/300 x 2060mm | 5 | No. | 1327 | 6635 | 85.2% | 5653.02 | 0 | 5653.02
6 | Vanity Table
Supply & installation of vanity table made with HTL-WD-09 mdf carcass & HTL-ST-10 drawer face as per Drg. No. D1BS-707-325-326, Rev A dated 29.04.2019. Stoneworks excluded
| Size 1542 x 610mm | 5 | No. | 1719 | 8595 | 16% | 1719 | -343.8 | 1375.2
| Wood niche architrave; OAD : 1600mm L x 610mm W x 2580mm H | 5 | No. | 2188 | 10940 |  | 0 | 0 | 0
Skirting - HTL WD-09
Supply & installation of timber skirting made of 18mm thk mdf in HTL WD09 finish as per given Dwg no. 1 bedroom Suite Sections
7 | OAD : 150mm H | 137 | m | 116 | 15892 | 20% | 0 | 3178.4 | 3178.4
Timber wall cladding
| Supply & installation of timber wall finishes made of mdf backing in HTL-WD-09 finish including all necessary timber supports as per given Dwg no. Duplex 1 bedroom Suite General Plan. | 310 | m2 | 487 | 150970 | 80% | 120776 | 0 | 120776
TYPE 11B (03 No's) - 1 Bed Suite
Wardrobe
Supply and install of Wardrobe consisting of HTL-WD-07 back panel, HTL-WD-02 shelf, frame, door, racks, shoe shelf, baseboard, drawer, including all necessary fittings, fixing, accessories etc., complete as per Drg. No. P18-IDR-H-AL-T11B&D-012, Elevation 29 & 30. 1BS-1202-322, 323, 324
Wardrobe with open shelf, drawer units & hanger rails.
| OAD : 3605mm L x 700mm W x 2500mm H | 3 | No. | 15517 | 46551 | 91.5% | 42594.165 | 0 | 42594.165
Mirror & fabric finishes are not shown in the elevation drawings & the same is not considered.
Vanity counter including wood niche. Location : Vestibule area.
Supply & install of vanity counter with drawer units consisting of HTL-WD-07 finish including wood niche in HTL WD-07 finish as per given details on Drg P18-IDR-H-AL-BDR-076.0 dated 20.03.2019, 1BS-1202-319, 320
| Vanity unit; OAD : 1300mm L x 550mm W x 100mm H | 3 | No. | 1584 | 4752 |  | 0 | 0 | 0
| Wood niche; OAD : 1300mm L x 620mm W x 2500mm H | 24 | m2 | 462 | 11088 |  | 0 | 0 | 0
Small cabinet + niche + light cove; Living room entrance area
Supply & install of wood niche with small cabinet in HTL WD-07 finish including light cove at living room entrance area as per given drawing Ref. P18-IDR-H-AL-BDR-075.0, dated 20.03.2019. 1BS-1202-310
| OAD : 500mm L x 485mm W x 2950mm H | 6 | No. | 1207 | 7242 |  | 0 | 0 | 0
Minibar Unit
Minibar base unit
Supply & install of mini bar base unit in HTl WD-07 finish with drawer unit as per given details on Drg P18-IDR-H-AL-BDR-073.1 including side shelf. 1BS-1202-311, 312, 313
| OAD : 2046mm L x 664mm W x 915mm H | 3 | No. | 5706 | 17118 | 12.5% | 15406.2 | -13266.45 | 2139.75
| Minibar wall cabinet in metal finish with mirror shutter | 3 | No. | 0 |  |  |  | 0 | 0
| Lit shelf in stone finish HTL-ST-16 to Minibar | 3 | No. | 0 |  |  |  | 0 | 0
| Credenza in metal finish HTL-ME03 to Minibar | 3 | No. | 0 |  |  |  | 0 | 0
Small cabinet + niche + light cove; Connecting jib door area
Supply & install wood light cove made of mdf in HTL-WD-07 including small cabinet as per given Drg no. P18-IDR-H-AL-BDR-075 dated 30.03.2019. 1BS-1202-314 - Lit shelf, counter top & credenza are excluded
| OAD : 727mm L x 546mm D x 2850mm H | 3 | No. | 2613 | 7839 |  | 0 | 0 | 0
Timber wall cladding
| Supply & installation of timber wall finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General Plan. | 156 | m2 | 316 | 49296 | 91.5% | 45105.84 | 0 | 45105.84
Timber Ceiling finish
| Supply & installation of timber ceiling finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General RCP. | 0 | m2 | 0 |  |  |  | 0 | 0
Timber Cove to ceiling at entrance area.
| Supply & installation of 200mm wide timber cove to ceiling finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General RCP. | 0 | m | 0 |  |  |  | 0 | 0
Skirting - HTL WD-07
Supply & installation of timber skirting made of 18mm thk mdf in HTL WD07 finish as per given Dwg no. 1 bedroom Suite Sections
| OAD : 150mm H | 150 | m | 116 | 17400 |  | 0 | 0 | 0
4 | DB cabinets including shutter
Supply & installation of DB cabinets made with mdf carcass shutter in painted finish HTL-PT-02 as per given drawing P18-IDR-H-AL-BDR-074.2, dated 05.04.2019.
| OAD : 1135mm W x 302mm D x2465mm H | 3 | No. | 3555 | 10665 | 82% | 10665 | -1919.7 | 8745.3
Bedroom Valet box
Supply & installation of bedroom valet box made with mdf carcass in walnut veneer finish , including shelf, shoe rack, hanger rod & shutter in extra clear mirror finish on external side as per given drawing P18-IDR-H-AL-BDR-074.1.
| OAD : 760mm L x 380mm W x 2650mm H. | 3 | No. | 1389 | 4167 | 82% | 4167 | -750.06 | 3416.94
TYPE 11A (01 No's) - 1 Bed Suite
Wardrobe
Supply and install of Wardrobe consisting of HTL-WD-07 back panel, HTL-WD-07 shelf, frame, door, racks, shoe shelf, baseboard, drawer including all necessary fittings, fixing, accessories etc., complete as per Drg. No. 1 Bedroom suite Sections JJ1.
Wardrobe with open shelf, drawer units & hanger rails.
| OAD : 3605mm L x 700mm W x 2500mm H | 1 | No. | 15517 | 15517 | 95% | 14741.15 | 0 | 14741.15
Mirror & fabric finishes are not shown in the elevation drawings & the same is not considered.
Vanity counter including wood niche. Location : Vestibule area.
Supply & install of vanity counter with drawer units consisting of HTL-WD-07 finish including wood niche in HTL WD-07 finish as per given details on Drg P18-IDR-H-AL-BDR-076.0 dated 20.03.2019, 1BS-1202-319, 320
| Vanity unit; OAD : 1300mm L x 550mm W x 100mm H | 1 | No. | 1584 | 1584 | 80% | 1267.2 | 0 | 1267.2
| Wood niche; OAD : 1300mm L x 620mm W x 2500mm H | 8 | m2 | 462 | 3696 | 80% | 2956.8 | 0 | 2956.8
Small cabinet + niche + light cove; Living room entrance area
Supply & install of wood niche with small cabinet in HTL WD-07 finish including light cove at living room entrance area as per given drawing Ref. P18-IDR-H-AL-BDR-075.0, dated 20.03.2019. 1BS-1202-310
| OAD : 500mm L x 485mm W x 2950mm H | 2 | No. | 1207 | 2414 | 80% | 1931.2 | 0 | 1931.2
Minibar Unit
Minibar base unit
Supply & install of mini bar base unit in HTl WD-07 finish with drawer unit as per given details on Drg P18-IDR-H-AL-BDR-073.1 including side shelf. 1BS-1202-311, 312, 313
| OAD : 2046mm L x 664mm W x 915mm H | 1 | No. | 5706 | 5706 | 90% | 5135.4 | 0 | 5135.4
| Minibar wall cabinet in metal finish with mirror shutter | 1 | No. | 0 |  |  |  | 0 | 0
| Lit shelf in stone finish HTL-ST-16 to Minibar | 1 | No. | 0 |  |  |  | 0 | 0
| Credenza in metal finish HTL-ME03 to Minibar | 1 | No. | 0 |  |  |  | 0 | 0
Small cabinet + niche + light cove; Connecting jib door area
Supply & install wood light cove made of mdf in HTL-WD-07 including small cabinet as per given Drg no. P18-IDR-H-AL-BDR-075 dated 30.03.2019. 1BS-1202-314 - Lit shelf, counter top & credenza are excluded
| OAD : 727mm L x 546mm D x 2850mm H | 1 | No. | 2613 | 2613 |  | 0 | 0 | 0
Timber wall cladding
| Supply & installation of timber wall finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General Plan. | 52 | m2 | 316 | 16432 | 95% | 15610.4 | 0 | 15610.4
Timber Ceiling finish
| Supply & installation of timber ceiling finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General RCP. | 0 | m2 | 0 |  |  |  | 0 | 0
Timber Cove to ceiling at entrance area.
| Supply & installation of 200mm wide timber cove to ceiling finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General RCP. | 0 | m | 0 |  |  |  | 0 | 0
Skirting - HTL WD-07
Supply & installation of timber skirting made of 18mm thk mdf in HTL WD07 finish as per given Dwg no. 1 bedroom Suite Sections
| OAD : 150mm H | 50 | m | 116 | 5800 | 95% | 5510 | 0 | 5510
4 | DB cabinets including shutter
Supply & installation of DB cabinets made with mdf carcass shutter in painted finish HTL-PT-02 as per given drawing P18-IDR-H-AL-BDR-074.2, dated 05.04.2019.
| OAD : 1135mm W x 302mm D x2465mm H | 1 | No. | 3555 | 3555 | 95% | 3377.25 | 0 | 3377.25
Bedroom Valet box
Supply & installation of bedroom valet box made with mdf carcass in walnut veneer finish , including shelf, shoe rack, hanger rod & shutter in extra clear mirror finish on external side as per given drawing P18-IDR-H-AL-BDR-074.1.
| OAD : 760mm L x 380mm W x 2650mm H. | 1 | No. | 1389 | 1389 | 95% | 1319.55 | 0 | 1319.55
TYPE 11C (11 No's) - 1 Bed Suite
Wardrobe
Supply and install of Wardrobe consisting of HTL-WD-07 back panel, HTL-WD-07 shelf, frame, door, racks, shoe shelf, baseboard, drawer including all necessary fittings, fixing, accessories etc., complete as per Drg. No. 1 Bedroom suite Sections JJ1.
Wardrobe with open shelf, drawer units & hanger rails.
| OAD : 3605mm L x 700mm W x 2500mm H | 11 | No. | 15517 | 170687 | 93.82% | 160135.44 | 0 | 160135.44
Mirror & fabric finishes are not shown in the elevation drawings & the same is not considered.
Vanity counter including wood niche. Location : Vestibule area.
Supply & install of vanity counter with drawer units consisting of HTL-WD-07 finish including wood niche in HTL WD-07 finish as per given details on Drg P18-IDR-H-AL-BDR-076.0 dated 20.03.2019, 1BS-1202-319, 320
| Vanity unit; OAD : 1300mm L x 550mm W x 100mm H | 11 | No. | 1584 | 17424 | 90% | 17424 | -1742.4 | 15681.6
| Wood niche; OAD : 1300mm L x 620mm W x 2500mm H | 88 | m2 | 462 | 40656 | 90% | 40656 | -4065.6 | 36590.4
Small cabinet + niche + light cove; Living room entrance area
Supply & install of wood niche with small cabinet in HTL WD-07 finish including light cove at living room entrance area as per given drawing Ref. P18-IDR-H-AL-BDR-075.0, dated 20.03.2019. 1BS-1202-310
| OAD : 500mm L x 485mm W x 2950mm H | 22 | No. | 1207 | 26554 | 90% | 26554 | -2655.4 | 23898.6
Minibar Unit
Minibar base unit
Supply & install of mini bar base unit in HTl WD-07 finish with drawer unit as per given details on Drg P18-IDR-H-AL-BDR-073.1 including side shelf. 1BS-1202-311, 312, 313
| OAD : 2046mm L x 664mm W x 915mm H | 11 | No. | 5706 | 62766 | 70% | 43936.2 | 0 | 43936.2
| Minibar wall cabinet in metal finish with mirror shutter | 11 | No. | 0 |  |  |  | 0 | 0
| Lit shelf in stone finish HTL-ST-16 to Minibar | 11 | No. | 0 |  |  |  | 0 | 0
| Credenza in metal finish HTL-ME03 to Minibar | 11 | No. | 0 |  |  |  | 0 | 0
Small cabinet + niche + light cove; Connecting jib door area
Supply & install wood light cove made of mdf in HTL-WD-07 including small cabinet as per given Drg no. P18-IDR-H-AL-BDR-075 dated 30.03.2019. 1BS-1202-314 - Lit shelf, counter top & credenza are excluded
| OAD : 727mm L x 546mm D x 2850mm H | 11 | No. | 2613 | 28743 | 35% | 0 | 10060.05 | 10060.05
Timber wall cladding
| Supply & installation of timber wall finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General Plan. | 572 | m2 | 316 | 180752 | 93.82% | 169578.24 | 0 | 169578.24
Timber Ceiling finish
| Supply & installation of timber ceiling finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General RCP. | 0 | m2 | 0 |  |  |  | 0 | 0
Timber Cove to ceiling at entrance area.
| Supply & installation of 200mm wide timber cove to ceiling finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General RCP. | 0 | m | 0 |  |  |  | 0 | 0
Skirting - HTL WD-07
Supply & installation of timber skirting made of 18mm thk mdf in HTL WD07 finish as per given Dwg no. 1 bedroom Suite Sections
| OAD : 150mm H | 550 | m | 116 | 63800 | 93.82% | 59856 | 0 | 59856
4 | DB cabinets including shutter
Supply & installation of DB cabinets made with mdf carcass shutter in painted finish HTL-PT-02 as per given drawing P18-IDR-H-AL-BDR-074.2, dated 05.04.2019.
| OAD : 1135mm W x 302mm D x2465mm H | 11 | No. | 3555 | 39105 | 88.82% | 34732.35 | 0 | 34732.35
Bedroom Valet box
Supply & installation of bedroom valet box made with mdf carcass in walnut veneer finish , including shelf, shoe rack, hanger rod & shutter in extra clear mirror finish on external side as per given drawing P18-IDR-H-AL-BDR-074.1.
| OAD : 760mm L x 380mm W x 2650mm H. | 11 | No. | 1389 | 15279 | 90% | 15279 | -1527.9 | 13751.1
TYPE 11D (4 No's) - 1 Bed Suite
Wardrobe
Supply and install of Wardrobe consisting of HTL-WD-07 back panel, HTL-WD-07 shelf, frame, door, racks, shoe shelf, baseboard, drawer including all necessary fittings, fixing, accessories etc., complete as per Drg. No. 1 Bedroom suite Sections JJ1.
Wardrobe with open shelf, drawer units & hanger rails.
| OAD : 3605mm L x 700mm W x 2500mm H | 4 | No. | 15517 | 62068 | 96% | 59585.28 | 0 | 59585.28
Mirror & fabric finishes are not shown in the elevation drawings & the same is not considered.
Vanity counter including wood niche. Location : Vestibule area.
Supply & install of vanity counter with drawer units consisting of HTL-WD-07 finish including wood niche in HTL WD-07 finish as per given details on Drg P18-IDR-H-AL-BDR-076.0 dated 20.03.2019, 1BS-1202-319, 320
| Vanity unit; OAD : 1300mm L x 550mm W x 100mm H | 4 | No. | 1584 | 6336 | 25% | 1584 | 0 | 1584
| Wood niche; OAD : 1300mm L x 620mm W x 2500mm H | 32 | m2 | 462 | 14784 | 25% | 3696 | 0 | 3696
Small cabinet + niche + light cove; Living room entrance area
Supply & install of wood niche with small cabinet in HTL WD-07 finish including light cove at living room entrance area as per given drawing Ref. P18-IDR-H-AL-BDR-075.0, dated 20.03.2019. 1BS-1202-310
| OAD : 500mm L x 485mm W x 2950mm H | 8 | No. | 1207 | 9656 | 100% | 9656 | 0 | 9656
Minibar Unit
Minibar base unit
Supply & install of mini bar base unit in HTl WD-07 finish with drawer unit as per given details on Drg P18-IDR-H-AL-BDR-073.1 including side shelf. 1BS-1202-311, 312, 313
| OAD : 2046mm L x 664mm W x 915mm H | 4 | No. | 5706 | 22824 | 70% | 15976.8 | 0 | 15976.8
| Minibar wall cabinet in metal finish with mirror shutter | 4 | No. | 0 |  |  |  | 0 | 0
| Lit shelf in stone finish HTL-ST-16 to Minibar | 4 | No. | 0 |  |  |  | 0 | 0
| Credenza in metal finish HTL-ME03 to Minibar | 4 | No. | 0 |  |  |  | 0 | 0
Small cabinet + niche + light cove; Connecting jib door area
Supply & install wood light cove made of mdf in HTL-WD-07 including small cabinet as per given Drg no. P18-IDR-H-AL-BDR-075 dated 30.03.2019. 1BS-1202-314 - Lit shelf, counter top & credenza are excluded
| OAD : 727mm L x 546mm D x 2850mm H | 4 | No. | 2613 | 10452 |  | 0 | 0 | 0
Timber wall cladding
| Supply & installation of timber wall finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General Plan. | 208 | m2 | 316 | 65728 | 96% | 63098.88 | 0 | 63098.88
Timber Ceiling finish
| Supply & installation of timber ceiling finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General RCP. | 0 | m2 | 0 |  |  |  | 0 | 0
Timber Cove to ceiling at entrance area.
| Supply & installation of 200mm wide timber cove to ceiling finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General RCP. | 0 | m | 0 |  |  |  | 0 | 0
Skirting - HTL WD-07
Supply & installation of timber skirting made of 18mm thk mdf in HTL WD07 finish as per given Dwg no. 1 bedroom Suite Sections
| OAD : 150mm H | 200 | m | 116 | 23200 | 96% | 22272 | 0 | 22272
4 | DB cabinets including shutter
Supply & installation of DB cabinets made with mdf carcass shutter in painted finish HTL-PT-02 as per given drawing P18-IDR-H-AL-BDR-074.2, dated 05.04.2019.
| OAD : 1135mm W x 302mm D x2465mm H | 4 | No. | 3555 | 14220 | 88.82% | 13177.2 | -547.2545 | 12629.9455
Bedroom Valet box
Supply & installation of bedroom valet box made with mdf carcass in walnut veneer finish , including shelf, shoe rack, hanger rod & shutter in extra clear mirror finish on external side as per given drawing P18-IDR-H-AL-BDR-074.1.
| OAD : 760mm L x 380mm W x 2650mm H. | 4 | No. | 1389 | 5556 | 88.82% | 5148.56 | -213.8218 | 4934.7382
TYPE 8A (5 No's) - 1 Bed Suite
Wardrobe
Supply and install of Wardrobe consisting of HTL-WD-07 back panel, HTL-WD-07 shelf, frame, door, racks, shoe shelf, baseboard, drawer including all necessary fittings, fixing, accessories etc., complete as per Drg. No. 1 Bedroom suite Sections JJ1.
Wardrobe with open shelf & hanger rails;
| OAD : 2920mm L x 720mm W x 2550mm H | 5 | No. | 11259 | 56295 | 98% | 55169.1 | 0 | 55169.1
Timber wall cladding
| Supply & installation of timber wall finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General Plan. | 260 | m2 | 316 | 82160 | 98% | 80516.8 | 0 | 80516.8
Timber Ceiling finish
| Supply & installation of timber ceiling finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General RCP. | 0 | m2 | 0 |  |  |  | 0 | 0
Timber Cove to ceiling at entrance area.
| Supply & installation of 200mm wide timber cove to ceiling finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General RCP. | 0 | m | 0 |  |  |  | 0 | 0
Skirting - HTL WD-07
Supply & installation of timber skirting made of 18mm thk mdf in HTL WD07 finish as per given Dwg no. 1 bedroom Suite Sections
| OAD : 150mm H | 250 | m | 116 | 29000 | 98% | 28420 | 0 | 28420
4 | DB cabinets including shutter
Supply & installation of DB cabinets made with mdf carcass shutter in painted finish HTL-PT-02 as per given drawing P18-IDR-H-AL-BDR-074.2, dated 05.04.2019.
| OAD : 900mm W x 300mm D x 2400mm H | 5 | No. | 2234 | 11170 | 98% | 10946.6 | 0 | 10946.6
TYPE 9A (2 No's) - 1 Bed Suite
Wardrobe
Supply and install of Wardrobe consisting of HTL-WD-07 back panel, HTL-WD-07 shelf, frame, door, racks, shoe shelf, baseboard, drawer including all necessary fittings, fixing, accessories etc., complete as per Drg. P18-IDR-H-AL-BDR-072.6, Dated 05.04.2019
Wardrobe with open shelf & hanger rails.
| OAD : 1480mm L x 720mm W x 2550mm H | 2 | No. | 4954 | 9908 | 98% | 9709.84 | 0 | 9709.84
Wardrobe with drawer units, shelf & hanger rails.
| OAD : 1460mm L x 720mm W x 2550mm H | 2 | No. | 7606 | 15212 | 98% | 14907.76 | 0 | 14907.76
Minibar Unit
Minibar base unit
Supply & installation of mini bar base unit in HTl WD-07 finish with drawer unit as per given details on Drg P18-IDR-H-AL-BDR-073.2
| OAD : 994mm L x 613mm W x 2430mm H | 2 | No. | 7416 | 14832 | 98% | 14090.4 | 444.96 | 14535.36
Timber wall cladding
| Supply & installation of timber wall finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General Plan. | 0 | m2 | 0 |  |  |  | 0 | 0
Timber Ceiling finish
| Supply & installation of timber ceiling finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General RCP. | 0 | m2 | 0 |  |  |  | 0 | 0
Timber Cove to ceiling at entrance area.
| Supply & installation of 200mm wide timber cove to ceiling finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General RCP. | 0 | m | 0 |  |  |  | 0 | 0
Skirting - HTL WD-07
Supply & installation of timber skirting made of 18mm thk mdf in HTL WD07 finish as per given Dwg no. 1 bedroom Suite Sections
0 | OAD : 150mm H | 0 | m | 0 |  |  |  | 0 | 0
4 | DB cabinets including shutter
Supply & installation of DB cabinets made with mdf carcass shutter in painted finish HTL-PT-02 as per given drawing P18-IDR-H-AL-BDR-074.2, dated 05.04.2019.
| OAD : 900mm W x 300mm D x 2400mm H | 2 | No. | 2234 | 4468 | 98% | 4378.64 | 0 | 4378.64
TYPE 09B (2 No's) - 1 Bed Suite
Wardrobe
Supply and install of Wardrobe consisting of HTL-WD-07 back panel, HTL-WD-07 shelf, frame, door, racks, shoe shelf, baseboard, drawer including all necessary fittings, fixing, accessories etc., complete as per Drg. P18-IDR-H-AL-BDR-072.6, Dated 05.04.2019
Wardrobe with open shelf & hanger rails.
| OAD : 1480mm L x 720mm W x 2550mm H | 2 | No. | 4954 | 9908 | 98% | 9709.84 | 0 | 9709.84
Wardrobe with drawer units, shelf & hanger rails.
| OAD : 1460mm L x 720mm W x 2550mm H | 2 | No. | 7606 | 15212 | 98% | 14907.76 | 0 | 14907.76
Wardrobe type 4c, drawing ref. P18-IDR-H-AL-BDR-072.10
| OAD : 829mm L x 720mm W x 2592mm H | 2 | No. | 5204 | 10408 | 98% | 10199.84 | 0 | 10199.84
Minibar Unit
Minibar base unit
Supply & installation of mini bar base unit in HTl WD-07 finish with drawer unit as per given details on Drg P18-IDR-H-AL-BDR-073.2
| OAD : 994mm L x 613mm W x 2430mm H | 2 | No. | 7416 | 14832 | 98% | 14090.4 | 444.96 | 14535.36
Timber wall cladding
| Supply & installation of timber wall finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General Plan. | 0 | m2 | 0 |  |  |  | 0 | 0
Timber Ceiling finish
| Supply & installation of timber ceiling finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General RCP. | 0 | m2 | 0 |  |  |  | 0 | 0
Timber Cove to ceiling at entrance area.
| Supply & installation of 200mm wide timber cove to ceiling finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General RCP. | 0 | m | 0 |  |  |  | 0 | 0
Skirting - HTL WD-07
Supply & installation of timber skirting made of 18mm thk mdf in HTL WD07 finish as per given Dwg no. 1 bedroom Suite Sections
| OAD : 150mm H | 0 | m | 0 |  |  |  | 0 | 0
4 | DB cabinets including shutter
Supply & installation of DB cabinets made with mdf carcass shutter in painted finish HTL-PT-02 as per given drawing P18-IDR-H-AL-BDR-074.2, dated 05.04.2019.
| OAD : 900mm W x 300mm D x 2400mm H | 2 | No. | 2234 | 4468 | 98% | 4378.64 | 0 | 4378.64
TYPE 10A (5 No's) - 1 Bed Suite
Wardrobe
Supply and install of Wardrobe consisting of HTL-WD-07 back panel, HTL-WD-07 shelf, frame, door, racks, shoe shelf, baseboard, drawer including all necessary fittings, fixing, accessories etc., complete as per Drg. P18-IDR-H-AL-BDR-072.6, Dated 05.04.2019
| Wardrobe with open shelf & hanger rails. | 5 | No. | 4954 | 24770 | 98.2% | 24324.14 | 0 | 24324.14
OAD : 1480mm L x 720mm W x 2550mm H
| Wardrobe with open shelf & hanger rails. | 5 | No. | 7606 | 38030 | 98.2% | 37345.46 | 0 | 37345.46
OAD : 1480mm L x 720mm W x 2550mm H
Wardrobe type 4c, drawing ref. P18-IDR-H-AL-BDR-072.10
| OAD : 785mm L x 720mm W x 2592mm H | 5 | No. | 5204 | 26020 | 98.2% | 25551.64 | 0 | 25551.64
Timber wall cladding
| Supply & installation of timber wall finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General Plan. | 0 | m2 | 0 |  |  |  | 0 | 0
Timber Ceiling finish
| Supply & installation of timber ceiling finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General RCP. | 0 | m2 | 0 |  |  |  | 0 | 0
Timber Cove to ceiling at entrance area.
| Supply & installation of 200mm wide timber cove to ceiling finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General RCP. | 0 | m | 0 |  |  |  | 0 | 0
Skirting - HTL WD-07
Supply & installation of timber skirting made of 18mm thk mdf in HTL WD07 finish as per given Dwg no. 1 bedroom Suite Sections
| OAD : 150mm H | 0 | m | 0 |  |  |  | 0 | 0
4 | DB cabinets including shutter
Supply & installation of DB cabinets made with mdf carcass shutter in painted finish HTL-PT-02 as per given drawing P18-IDR-H-AL-BDR-074.2, dated 05.04.2019.
| OAD : 800mm W x 300mm D x 2400mm H | 5 | No. | 2234 | 11170 | 98% | 10946.6 | 0 | 10946.6
3 | Timber screen behind the minibar unit
Supply & installation of timber screen made of mdf panels in WD03 walnut high gloss finish as per given details.
| OAD : 610 + 1380mm L x 60mm THK x 2250mm H | 5 | No. | 2227 | 11135 | 98% | 10912.3 | 0 | 10912.3
TYPE 10B (03 No's)
Wardrobe
Supply and install of Wardrobe consisting of HTL-WD-07 back panel, HTL-WD-07 shelf, frame, door, racks, shoe shelf, baseboard, drawer including all necessary fittings, fixing, accessories etc., complete as per Drg. P18-IDR-H-AL-BDR-072.6, Dated 05.04.2019
Wardrobe with open shelf & hanger rails.
| OAD : 1480mm L x 720mm W x 2550mm H | 3 | No. | 4954 | 14862 | 95% | 14118.9 | 0 | 14118.9
Wardrobe with drawer units, shelf & hanger rails.
| OAD : 1460mm L x 720mm W x 2550mm H | 3 | No. | 7606 | 22818 | 95% | 21677.1 | 0 | 21677.1
Timber wall cladding
| Supply & installation of timber wall finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General Plan. | 0 | m2 | 0 |  |  |  | 0 | 0
Timber Ceiling finish
| Supply & installation of timber ceiling finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General RCP. | 0 | m2 | 0 |  |  |  | 0 | 0
Timber Cove to ceiling at entrance area.
| Supply & installation of 200mm wide timber cove to ceiling finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General RCP. | 0 | m | 0 |  |  |  | 0 | 0
Skirting - HTL WD-07
Supply & installation of timber skirting made of 18mm thk mdf in HTL WD07 finish as per given Dwg no. 1 bedroom Suite Sections
| OAD : 150mm H | 0 | m | 0 |  |  |  | 0 | 0
4 | DB cabinets including shutter
Supply & installation of DB cabinets made with mdf carcass shutter in painted finish HTL-PT-02 as per given drawing P18-IDR-H-AL-BDR-074.2, dated 05.04.2019.
| OAD : 800mm W x 300mm D x 2400mm H | 3 | No. | 2234 | 6702 | 95% | 6366.9 | 0 | 6366.9
TYPE 12A (5 No's) - 1 Bed Suite
Wardrobe
Supply and install of Wardrobe consisting of HTL-WD-07 back panel, HTL-WD-07 shelf, frame, door, racks, shoe shelf, baseboard, drawer including all necessary fittings, fixing, accessories etc., complete as per Drg. No. 1 Bedroom suite Sections JJ1.
Wardrobe with open shelf & hanger rails.
| OAD : 3765mm L x 720mm W x 2550mm H | 5 | No. | 13929 | 69645 | 98% | 68252.1 | 0 | 68252.1
Vanity counter including wood niche. Location
Vanity counter including wood niche. Location : Vestibule area.
Supply & install of vanity counter with drawer units consisting of HTL-WD-07 finish including wood niche in HTL WD-07 finish as per given details on Drg P18-IDR-H-AL-BDR-076.0 dated 20.03.2019
| Vanity unit; OAD : 1300mm L x 550mm W x 100mm H | 5 | No. | 1584 | 7920 | 80% | 6336 | 0 | 6336
| Wood niche; OAD : 1300mm L x 620mm W x 2500mm H | 40 | m2 | 462 | 18480 | 80% | 14784 | 0 | 14784
Timber wall cladding
| Supply & installation of timber wall finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General Plan. | 0 | m2 | 0 |  |  |  | 0 | 0
Timber Ceiling finish
| Supply & installation of timber ceiling finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General RCP. | 0 | m2 | 0 |  |  |  | 0 | 0
Timber Cove to ceiling at entrance area.
| Supply & installation of 200mm wide timber cove to ceiling finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General RCP. | 0 | m | 0 |  |  |  | 0 | 0
Skirting - HTL WD-07
Supply & installation of timber skirting made of 18mm thk mdf in HTL WD07 finish as per given Dwg no. 1 bedroom Suite Sections
| OAD : 150mm H | 0 | m | 0 |  |  |  | 0 | 0
4 | DB cabinets including shutter
Supply & installation of DB cabinets made with mdf carcass shutter in painted finish HTL-PT-02 as per given drawing P18-IDR-H-AL-BDR-074.2, dated 05.04.2019.
| OAD : 800mm W x 300mm D x 2400mm H | 5 | No. | 2234 | 11170 | 95.4% | 8757.28 | 1898.9 | 10656.18
Minibar base unit
Supply & install of mini bar base unit in HTl WD-07 finish with drawer unit as per given details on Drg P18-IDR-H-AL-BDR-073.1 including side shelf.
| OAD : 2046mm L x 664mm W x 915mm H | 5 | No. | 5706 | 28530 | 95% | 27103.5 | 0 | 27103.5
| Minibar wall cabinet in metal finish with mirror shutter | 5 | No. | 0 |  |  |  | 0 | 0
| Lit shelf in stone finish HTL-ST-16 to Minibar | 5 | No. | 0 |  |  |  | 0 | 0
| Credenza in metal finish HTL-ME03 to Minibar | 5 | No. | 0 |  |  |  | 0 | 0
TYPE 13A (1 No) - 1 Bed Suite
Wardrobe
Supply and install of Wardrobe consisting of HTL-WD-07 back panel, HTL-WD-07 shelf, frame, door, racks, shoe shelf, baseboard, drawer including all necessary fittings, fixing, accessories etc., complete as per Drg. P18-IDR-H-AL-BDR-072.7, Dated 05.04.2019
| OAD : 4095mm L x 720mm W x 2550mm H | 1 | No. | 15514 | 15514 | 95% | 14738.3 | 0 | 14738.3
Timber wall cladding
| Supply & installation of timber wall finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General Plan. | 0 | m2 | 0 |  |  |  | 0 | 0
Timber Ceiling finish
| Supply & installation of timber ceiling finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General RCP. | 0 | m2 | 0 |  |  |  | 0 | 0
Skirting - HTL WD-07
Supply & installation of timber skirting made of 18mm thk mdf in HTL WD07 finish as per given Dwg no. 1 bedroom Suite Sections
| OAD : 150mm H | 0 | m | 0 |  |  |  | 0 | 0
4 | DB cabinets including shutter
Supply & installation of DB cabinets made with mdf carcass shutter in painted finish HTL-PT-02 as per given drawing P18-IDR-H-AL-BDR-074.0, dated 05.04.2019.
| OAD : 800mm W x 300mm D x 2400mm H | 1 | No. | 2234 | 2234 |  | 0 | 0 | 0
TYPE 14A (4 No's) - 1 Bed Suite
Wardrobe
Supply and install of Wardrobe consisting of HTL-WD-01 back panel, HTL-WD-02 shelf, frame, door, racks, shoe shelf, baseboard, draw including all necessary fittings, fixing, accessories etc., complete as per drawing details.
Wardrobe with open shelf, drawers & hanger rails as per given drawing P18-IDR-H-AL-BDR-072.7; Dated 05.04.2019.
| OAD : 5507mm L x 720mm W x 2550mm H | 4 | No. | 21067 | 84268 | 95% | 80054.6 | 0 | 80054.6
Timber wall cladding
| Supply & installation of timber wall finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General Plan. | 0 | m2 | 0 |  |  |  | 0 | 0
Timber Ceiling finish
| Supply & installation of timber ceiling finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General RCP. | 0 | m2 | 0 |  |  |  | 0 | 0
Timber Cove to ceiling at entrance area.
| Supply & installation of 200mm wide timber cove to ceiling finishes made of mdf backing in HTL-WD-07 finish including all necessary timber supports as per given Dwg no. 1 bedroom Suite General RCP. | 0 | m | 0 |  |  |  | 0 | 0
Skirting - HTL WD-07
Supply & installation of timber skirting made of 18mm thk mdf in HTL WD07 finish as per given Dwg no. 1 bedroom Suite Sections
| OAD : 150mm H | 0 | m | 0 |  |  |  | 0 | 0
Minibar base unit
Supply & install of mini bar base unit in HTl WD-07 finish with drawer unit as per given details on Drg P18-IDR-H-AL-BDR-073.1 including side shelf.
| OAD : 2046mm L x 664mm W x 915mm H | 4 | No. | 5706 | 22824 | 93.75% | 21397.5 | 0 | 21397.5
| Minibar wall cabinet in metal finish with mirror shutter | 4 | No. | 0 |  |  |  | 0 | 0
| Lit shelf in stone finish HTL-ST-16 to Minibar | 4 | No. | 0 |  |  |  | 0 | 0
| Credenza in metal finish HTL-ME03 to Minibar | 4 | No. | 0 |  |  |  | 0 | 0
4 | DB cabinets including shutter
Supply & installation of DB cabinets made with mdf carcass shutter in painted finish HTL-PT-02 as per given drawing P18-IDR-H-AL-BDR-074.0, dated 05.04.2019.
| OAD : 800mm W x 300mm D x 2400mm H | 4 | No. | 2234 | 8936 | 71.25% | 6366.9 | 0 | 6366.9
Timber screen behind the minibar unit
Supply & installation of timber screen made of mdf panels in WD03 walnut high gloss finish as per given details.
| OAD : 610 + 1380mm L x 60mm THK x 2250mm H | 4 | No. | 2227 | 8908 | 60% | 4008.6 | 1336.2 | 5344.8
TYPE 16A (3 No's) - 1 Bed Suite
Wardrobe
Supply and install of Wardrobe consisting of HTL-WD-01 back panel, HTL-WD-02 shelf, frame, door, racks, shoe shelf, baseboard, draw including all necessary fittings, fixing, accessories etc., complete as per drawing details.
Wardrobe with open shelf & hanger rails as per given drawing P18-IDR-H-AL-BDR-072.0; Dated 20.03.2019.
| Size: 1894 x 720 x 2550mm, ref. 072.0 | 3 | No. | 8096 | 24288 | 96% | 23316.48 | 0 | 23316.48
Wardrobe with open shelf & hanger rails as per given drawing P18-IDR-H-AL-BDR-072.3; Dated 05.04.2019.
| OAD : 800mm L x 720mm W x 2550mm H | 3 | No. | 4112 | 12336 | 96% | 11842.56 | 0 | 11842.56
4 | DB cabinets including shutter
Supply & installation of DB cabinets made with mdf carcass shutter in painted finish HTL-PT-02 as per given drawing P18-IDR-H-AL-BDR-074.0, dated 05.04.2019.
| OAD : 800mm W x 300mm D x 2400mm H | 3 | No. | 2234 | 6702 | 65.33% | 4378.64 | 0 | 4378.64
3 | Timber screen behind the minibar unit
Supply & installation of timber screen made of mdf panels in WD03 walnut high gloss finish as per given details.
| OAD : 610 + 1380mm L x 60mm THK x 2250mm H | 3 | No. | 2227 | 6681 | 52.67% | 2182.46 | 1336.2 | 3518.66
TYPE 19A (6 No's) - 1 Bed Suite
Wardrobe
Supply and install of Wardrobe consisting of HTL-WD-01 back panel, HTL-WD-02 shelf, frame, door, racks, shoe shelf, baseboard, draw including all necessary fittings, fixing, accessories etc., complete as per drawing details.
Wardrobe with open shelf & hanger rails as per given drawing P18-IDR-H-AL-BDR-072.0; Dated 20.03.2019.
| OAD : 1795mm L x 720mm W x 2550mm H | 6 | No. | 5690 | 34140 | 97.5% | 33286.5 | 0 | 33286.5
Wardrobe with open shelf & hanger rails as per given drawing P18-IDR-H-AL-BDR-072.0; Dated 20.03.2019.
| OAD : 1795mm L x 720mm W x 2550mm H | 6 | No. | 8736 | 52416 | 97.5% | 51105.6 | 0 | 51105.6
4 | DB cabinets including shutter
Supply & installation of DB cabinets made with mdf carcass shutter in painted finish HTL-PT-02 as per given drawing P18-IDR-H-AL-BDR-074.0, dated 05.04.2019.
| OAD : 800mm W x 300mm D x 2400mm H | 6 | No. | 2234 | 13404 | 79.5% | 8757.28 | 1898.9 | 10656.18
Minibar base unit
Supply & installation of mini bar base unit in HTl WD-07 finish with drawer unit as per given details on Drg P18-IDR-H-AL-BDR-073.2
| OAD : 994mm L x 613mm W x 2430mm H | 6 | No. | 7416 | 44496 | 92.5% | 34855.2 | 6303.6 | 41158.8
ADDITIONAL ITEMS
TYPE - 03B (2 No's)
TYPE - 03E (2 No's)
TYPE - 03G (4 No's)
TYPE - 07A (5 No's)
TYPE - 15A (2 No's) - 2 Bed Suite - No Drawings
TYPE - 17A (1 No's) - Presidential Suite
TYPE - 18A (1 No's) - Royal Suite
VANITY & CISTERN SUPPORT
TYPE - 02A (13 No's)
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom: Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitred with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding | 13 | No. | 1769 | 22997 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cictern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 950mm length, pencil edge finish (HTL-ST-03) | 13 | No. | 377 | 4901 | 100% | 4901 | 0 | 4901
TYPE - 02B (16 No's)
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom: Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitred with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding | 16 | No. | 1769 | 28304 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cictern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 950mm length, pencil edge finish (HTL-ST-03) | 16 | No. | 377 | 6032 | 100% | 6032 | 0 | 6032
TYPE - 02C (8 No's)
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom: Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitred with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding | 8 | No. | 1769 | 14152 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cictern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 950mm length, pencil edge finish (HTL-ST-03) | 8 | No. | 377 | 3016 | 100% | 3016 | 0 | 3016
TYPE - 02D (7 No's)
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom: Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitred with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding | 7 | No. | 1769 | 12383 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cictern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 950mm length, pencil edge finish (HTL-ST-03) | 7 | No. | 377 | 2639 | 100% | 2639 | 0 | 2639
TYPE - 02E (9 No's)
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom: Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitred with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding | 9 | No. | 1769 | 15921 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cictern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 950 1365mm length, pencil edge finish (HTL-ST-03) | 9 | No. | 543 | 4887 | 100% | 4887 | 0 | 4887
TYPE - 02F (8 No's)
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom: Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitred with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding | 8 | No. | 1769 | 14152 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cictern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 950 1075mm length, pencil edge finish (HTL-ST-03) | 8 | No. | 437 | 3496 | 100% | 3496 | 0 | 3496
TYPE - 02G (9 No's)
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom: Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835 1600mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitred with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding | 9 | No. | 1624 | 14616 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cictern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 950mm length, pencil edge finish (HTL-ST-03) | 9 | No. | 377 | 3393 | 100% | 3393 | 0 | 3393
TYPE - 03A (13 No's)
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 2867mm length, with 250mm high fascia. Including lower shelf top size of 428mm x 2867mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. (niche surround and shelf, elsewhere). | 13 | No. | 4780 | 62140 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 1020mm length, pencil edge finish (HTL-ST-12) | 13 | No. | 418 | 5434 | 100% | 5434 | 0 | 5434
TYPE - 03B (2 No's)
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 2867mm length, with 250mm high fascia. Including lower shelf top size of 428mm x 2867mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. (niche surround and shelf, elsewhere). |  | No.
Support to Cistern (Stone by others)
| Carcass to Cistern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 1020mm length, pencil edge finish (HTL-ST-12) |  | No.
TYPE - 03C (9 No's)
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 2867mm length, with 250mm high fascia. Including lower shelf top size of 428mm x 2867mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. (niche surround and shelf, elsewhere). | 9 | No. | 4780 | 43020 |  |  | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 1020mm length, pencil edge finish (HTL-ST-12) | 9 | No. | 418 | 3762 | 100% | 3762 | 0 | 3762
TYPE - 03D (18 No's)
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 2867mm length, with 250mm high fascia. Including lower shelf top size of 428mm x 2867mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. (niche surround and shelf, elsewhere). | 18 | No. | 4780 | 86040 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 1020mm length, pencil edge finish (HTL-ST-12) | 18 | No. | 418 | 7524 | 100% | 7524 | 0 | 7524
TYPE - 03E (18 No's)
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 2867mm length, with 250mm high fascia. Including lower shelf top size of 428mm x 2867mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. (niche surround and shelf, elsewhere). |  | No.
Support to Cistern (Stone by others)
| Carcass to Cistern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 1020mm length, pencil edge finish (HTL-ST-12) |  | No.
TYPE - 03F (9 No's)
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 2867mm length, with 250mm high fascia. Including lower shelf top size of 428mm x 2867mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. (niche surround and shelf, elsewhere). | 9 | No. | 4780 | 43020 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 1020mm length, pencil edge finish (HTL-ST-12) | 9 | No. | 418 | 3762 | 100% | 3762 | 0 | 3762
TYPE - 03G (4 No's)
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom: Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitred with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding |  | No.
Support to Cistern (Stone by others)
| Carcass to Cistern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 950mm length, pencil edge finish (HTL-ST-03) |  | No.
TYPE - 01C (2 No's)
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom: Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitred with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding | 2 | No. | 1769 | 3538 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 950mm length, pencil edge finish (HTL-ST-03) | 2 | No. | 377 | 754 | 100% | 754 | 0 | 754
TYPE - 04A (4 No's)
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom: Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitred with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding | 4 | No. | 3946 | 15784 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 950mm length, pencil edge finish (HTL-ST-03) | 4 | No. | 418 | 1672 | 100% | 1672 | 0 | 1672
TYPE - 04B (1 No's)
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom: Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitred with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding | 1 | No. | 3946 | 3946 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 950mm length, pencil edge finish (HTL-ST-03) | 1 | No. | 418 | 418 | 100% | 418 | 0 | 418
TYPE - 05A (9 No's)
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom: Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitred with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding | 9 | No. | 3946 | 35514 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 950mm length, pencil edge finish (HTL-ST-03) | 9 | No. | 418 | 3762 | 100% | 3762 | 0 | 3762
TYPE - 06A (5 No's)
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom: Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitred with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding | 5 | No. | 3946 | 19730 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 950mm length, pencil edge finish (HTL-ST-03) | 5 | No. | 418 | 2090 | 100% | 2090 | 0 | 2090
TYPE - 07A (5 No's)
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom: Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitred with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding | 5 | No. | 0 |  |  |  | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 950mm length, pencil edge finish (HTL-ST-03) | 5 | No. | 0 |  |  |  | 0 | 0
TYPE - 07B (5 No's)
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom: Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitred with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding | 5 | No. | 0 |  |  |  | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 950mm length, pencil edge finish (HTL-ST-03) | 5 | No. | 0 |  |  |  | 0 | 0
TYPE - 08A (5 No's)
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom: Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitred with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding | 5 | No. | 3946 | 19730 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 950 1090mm length, pencil edge finish (HTL-ST-03) | 5 | No. | 437 | 2185 | 100% | 2185 | 0 | 2185
TYPE - 09A (2 No's)
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom: Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835 2315mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitred with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding | 2 | No. | 2028 | 4056 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 950 1000mm length, pencil edge finish (HTL-ST-03) | 2 | No. | 418 | 836 | 100% | 836 | 0 | 836
TYPE - 09B (2 No's)
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom: Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835 2050mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitred with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding | 2 | No. | 1932 | 3864 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 950 1000mm length, pencil edge finish (HTL-ST-03) | 2 | No. | 418 | 836 | 100% | 836 | 0 | 836
TYPE - 10A (5 No's)
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom: Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitred with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding | 5 | No. | 1769 | 8845 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 950mm length, pencil edge finish (HTL-ST-03) | 5 | No. | 377 | 1885 | 100% | 1885 | 0 | 1885
TYPE - 10B (3 No's)
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom: Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitred with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding | 3 | No. | 1769 | 5307 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 950mm length, pencil edge finish (HTL-ST-03) | 3 | No. | 377 | 1131 | 100% | 1131 | 0 | 1131
TYPE - 11A (1 No's)
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom: Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitred with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding | 9 | No. | 0 |  |  |  | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 950mm length, pencil edge finish (HTL-ST-03) | 9 | No. | 0 |  |  |  | 0 | 0
TYPE - 11B (3 No's)
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom: Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitred with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding | 11 | No. | 0 |  |  |  | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 950mm length, pencil edge finish (HTL-ST-03) | 11 | No. | 0 |  |  |  | 0 | 0
TYPE - 12A (5 No's)
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom: Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitred with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding | 5 | No. | 0 |  |  |  | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 950mm length, pencil edge finish (HTL-ST-03) | 5 | No. | 0 |  |  |  | 0 | 0
TYPE - 13A (1 No's)
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom: Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitred with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding | 1 | No. | 1769 | 1769 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 950 1100mm length, pencil edge finish (HTL-ST-03) | 1 | No. | 437 | 437 | 100% | 437 | 0 | 437
TYPE - 14A (4 No's)
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom: Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835 2860mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitred with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding | 4 | No. | 4780 | 19120 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 950 1050mm length, pencil edge finish (HTL-ST-03) | 4 | No. | 418 | 1672 | 100% | 1672 | 0 | 1672
TYPE - 15A (2 No's) - No drawings
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom: Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitred with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding | 2 | No. | 0 |  |  |  | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 950mm length, pencil edge finish (HTL-ST-03) | 2 | No. | 0 |  |  |  | 0 | 0
TYPE - 16A (3 No's)
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom: Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835 1900mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitred with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding | 3 | No. | 1932 | 5796 |  |  | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 950mm length, pencil edge finish (HTL-ST-03) | 3 | No. | 377 | 1131 | 100% | 1131 | 0 | 1131
TYPE - 17A (1 No's) - No drawings
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom: Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitred with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding | 3 | No. | 0 |  |  |  | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 950mm length, pencil edge finish (HTL-ST-03) | 3 | No. | 0 |  |  |  | 0 | 0
Support to Vanity Counter (Stone by others)
| Carcass to Vanity Counter @ Bathroom: Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitred with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding | 17 | No. | 0 |  |  |  | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 950mm length, pencil edge finish (HTL-ST-03) | 17 | No. | 0 |  |  |  | 0 | 0
TYPE 02H (1 No)
| Entrance door, size 1170 x 2480mm ( 1 hour fire rated) including brass strip HTL-ME-01 and architrave and frame as per Door type : HO-TB-01 | 1 | No. | 3361 | 3361 | 97.83% | 3288.1783 | 0 | 3288.1783
| Timber (HTL-WD-01) double panel door, size 914 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-04 | 1 | No. | 2286 | 2286 | 97.83% | 2236.47 | 0 | 2236.47
| Timber (HTL-WD-01) double panel door, size 1115 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-05 | 1 | No. | 2347 | 2347 | 97.83% | 2296.1483 | 0 | 2296.1483
1 | Door type HO-GD-03; Non Fire rated Sliding Door.
Supply & installation of slingle leaf sliding door type HO-GD-03 made of HTL-GL-04 glass panels with HTL-TB-01 timber frame including metal pul handle as per given drawing P18-IDR-H-AL-BDR-121.
| OAD : 860mm W x 2430mm H | 119 | No. | 7424 | 883456 | 80% | 706764.8 | 0 | 706764.8
2 | Door Type HO-TB-06; Non Fire rated Swing Door.
Supply & installation of Double leaf door made of solid white oak timber jamb, shutter made with solid core with metal edge trim all around, both sides finished with HTL-FA10 fabric finish as per given drawing; P18-IDR-H-AL-BDR-103,Rev-A, dated 26.04.2019
| OAD : 1575mm W x 2650mm H | 10 | No.
ADDITIONAL - TIMBER DOOR
Door type HO-TB-02; Fire Rated 60 Minutes Interleading Door.
| Timber single leaf connecting door, size 942 x 2549mm (60 minutes fire rated) as per DRAWING DLR-703-309 | 30 | No. | 2745 | 82350 | 80% | 65880 | 0 | 65880
Door type HO-TB-03 at Unit TYPE - 5A
| Timber (HTL-WD-01) double panel door, size 1480 x 2430mm (Non fire rated door) including frame as per Door type : HO-TB-03 | 9 | No. | 2701 | 24309 | 89.81% | 20448.8208 | 1384.2625 | 21833.0833
TYPE 07A (5 No's)
| Entrance door, size 1410 x 2660mm (1 hour fire rated) including brass strip HTL-ME-01, architrave and frame. Dwg ref. D1BS-707-303 Rev.A dated 29-04-2019 | 5 | No. | 3950 | 19750 | 164% | 13140.3333 | 19256.25 | 32396.5833
| Powder room door, size 805 x 2420mm (non-fire rated) including frame & metal architrave. Dwg ref. D1BS-707-304 Rev.A dated 29-04-2019 | 5 | No. | 1487 | 7435 | 70% | 5204.5 | 0 | 5204.5
| Bedroom & vestibule door, size 900 x 3015mm (non-fire rated) including metal edge Dwg ref. D1BS-707-324 Rev.A dated 29-04-2019 | 10 | No. | 4397 | 43970 | 70% | 30779 | 0 | 30779
| Walk-in-closet door, size 900 x 2620mm (non-fire rated) Dwg ref. D1BS-707-323 Rev.A dated 29-04-2019 | 5 | No. | 4624 | 23120 | 70% | 16184 | 0 | 16184
| Bathroom door, size 1000 x 2620mm (non-fire rated) Dwg ref. D1BS-707-322 Rev.A dated 29-04-2019 | 5 | No. | 4768 | 23840 | 70% | 16688 | 0 | 16688
| Valet door from walk-in-closet, size 920 x 2425mm (non-fire rated) Dwg ref. D1BS-707-327 Rev.A dated 29-04-2019 | 5 | No. | 1508 | 7540 | 70% | 5278 | 0 | 5278
| Valet door to corridor, size 915 x 2435mm (60 minutes fire rated ) Dwg ref. D1BS-707-328 Rev.A dated 29-04-2019 | 5 | No. | 3117 | 15585 | 70% | 10909.5 | 0 | 10909.5
| WC door, size 858 x 2450mm (non-fire rated ) Dwg ref. D1BS-707-329 Rev.A dated 29-04-2019 | 5 | No. | 2052 | 10260 | 70% | 7182 | 0 | 7182
| Timber architrave (HTL-WD-09) to vestibule, size 1600 x 2580mm x 725mm | 5 | No. | 1875 | 9375 | 70% | 6562.5 | 0 | 6562.5
TYPE 11A to 11D (19 Nos)
| Timber architrave to powder room, size 1010 x 2435mm (non-fire rated) including frame. Dwg ref. 1BS-1202-304 | 19 | No. | 803 | 15257 | 52.63% | 8029.7591 | 0 | 8029.7591
TYPE 11C & 11D (15 Nos)
| Connecting jib door, size 980 x 2405mm (60 minutes fire rated) including frame. Dwg ref. 1BS-1202-315 | 15 | No. | 2850 | 42750 | 60% | 25650 | 0 | 25650
ADDITIONAL - JOINERY
TYPE 05A (09 No's)
Timber screen behind the minibar unit
Supply & installation of timber screen made of mdf panels in WD03 walnut high gloss finish as per given details.
Add | Size 670+1410 x 2200mm | 9 | No. | 2227 | 20043 | 87.78% | 14920.9 | 2672.4 | 17593.3
TYPE - 02H (1 No's)
Support to Vanity Counter (Stone by others)
Add | Carcass to Vanity Counter @ Bathroom: Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitred with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding | 1 | No. | 1769 | 1769 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
Add | Carcass to Cictern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 950mm length, pencil edge finish (HTL-ST-03) | 1 | No. | 437 | 437 | 100% | 437 | 0 | 437
TYPE - 01A (6 No's)
Support to Vanity Counter (Stone by others)
Add | Carcass to Vanity Counter @ Bathroom: Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitred with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding | 6 | No. | 1769 | 10614 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
Add | Carcass to Cistern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 950mm length, pencil edge finish (HTL-ST-03) | 6 | No. | 377 | 2262 | 100% | 2262 | 0 | 2262
TYPE - 01B (6 No's)
Support to Vanity Counter (Stone by others)
Add | Carcass to Vanity Counter @ Bathroom: Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835 2300mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitred with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding | 6 | No. | 1955 | 11730 |  | 0 | 0 | 0
TYPE - 07A (5 No's)
Support to Vanity Counter (Stone by others)
| Master Bath Vanity: Supply and installation of carcass to vanity inlcuding metal legs and wood shelves. Size: 3500mm length x 580mm | 5 | No. | 7772 | 38860 | 85% | 33031 | 0 | 33031
Support to Vanity Counter (Stone by others)
| Powder Room: Supply and installation of carcass to vanity; Size: 500 x 400 | 5 | No. | 644 | 3220 | 85% | 2737 | 0 | 2737
Support to Cistern (Stone by others)
| Carcass to Cistern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 1000mm length, pencil edge finish (HTL-ST-20) | 10 | No. | 398 | 3980 | 90% | 3980 | -398 | 3582
TYPE - 08A (5 No's)
| Powder Room; Vanity Type 5; Ref. 070.12 det. 1 | 5 | No. | 1397 | 6985 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top; 220mm w x 1500mm l x 1255mm h | 5 | No. | 597 | 2985 | 100% | 2985 | 0 | 2985
TYPE 9A (2 No's) - 1 Bed Suite
| Powder Room; Vanity Type 5; Ref: 070.12 det. 5 | 2 | No. | 679 | 1358 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top; 220mm w x 1000mm l x 1255mm h | 2 | No. | 418 | 836 | 100% | 836 | 0 | 836
TYPE 09B (2 No's) - 1 Bed Suite
Support to Vanity Counter
| Powder Room; Vanity Type 5; Ref: 070.12 det. 5 | 2 | No. | 679 | 1358 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top; 220mm w x 1000mm l x 1255mm h | 2 | No. | 418 | 836 | 100% | 836 | 0 | 836
TYPE 10A (5 No's) - 1 Bed Suite
Support to Vanity Counter
| Powder Room; Vanity Type 5; Ref: 070.12 det. 6 | 5 | No. | 1397 | 6985 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top; 220mm w x 1115mm l x 1255mm h | 5 | No. | 437 | 2185 | 100% | 2185 | 0 | 2185
TYPE 10B (03 No's)
Support to Vanity Counter
| Powder Room; Vanity Type 5; Ref: 070.12 det. 6 | 3 | No. | 1397 | 4191 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top; 220mm w x 1290mm l x 1255mm h | 3 | No. | 497 | 1491 | 100% | 1491 | 0 | 1491
TYPE 11A (01 No's) - 1 Bed Suite
Vanity counter cabinet (Stoneworks by others)
| Master Bath Vanity; Ref: 071.2 - under vanity drawers | 1 | No. | 1089 | 1089 | 100% | 1089 | 0 | 1089
Support to Vanity Counter
| Master Bath Vanity; Ref: 071.2 | 1 | No. | 3421 | 3421 | 100% | 3421 | 0 | 3421
| Powder Room; Vanity Type 4; Ref: 070.11 | 1 | No. | 1265 | 1265 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top; 220mm w x 1020mm l x 1255mm h | 1 | No. | 418 | 418 | 100% | 418 | 0 | 418
| Carcass to Cistern Top; 220mm w x 1460mm l x 1255mm h | 1 | No. | 597 | 597 | 100% | 597 | 0 | 597
Access Panel to Equipment (Provisional)
| Size 355 x 600mm | 1 | No. | 394 | 394 | 100% | 394 | 0 | 394
TYPE 11B (03 No's)
Vanity counter cabinet (Stoneworks by others)
| Master Bath Vanity; Ref: 071.2 - under vanity drawers | 3 | No. | 1089 | 3267 | 100% | 3267 | 0 | 3267
Support to Vanity Counter
| Master Bath Vanity; Ref: 071.2 | 3 | No. | 3421 | 10263 |  | 0 | 0 | 0
| Powder Room; Vanity Type 4; Ref: 070.11 | 3 | No. | 1265 | 3795 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top; 220mm w x 1020mm l x 1255mm h | 3 | No. | 418 | 1254 | 100% | 1254 | 0 | 1254
| Carcass to Cistern Top; 220mm w x 1460mm l x 1255mm h | 3 | No. | 597 | 1791 | 100% | 1791 | 0 | 1791
Access Panel to Equipment (Provisional)
| Size 355 x 600mm | 3 | No. | 394 | 1182 |  | 0 | 0 | 0
TYPE 11C (11 No's) - 1 Bed Suite
Vanity counter cabinet (Stoneworks by others)
| Master Bath Vanity; Ref: 071.2 - under vanity drawers | 11 | No. | 1089 | 11979 | 100% | 11979 | 0 | 11979
Support to Vanity Counter
| Master Bath Vanity; Ref: 071.2 | 11 | No. | 3421 | 37631 | 100% | 30104.8 | 7526.2 | 37631
| Powder Room; Vanity Type 4; Ref: 070.11 | 11 | No. | 1265 | 13915 | 100% | 11132 | 2783 | 13915
Support to Cistern (Stone by others)
| Carcass to Cistern Top; 220mm w x 1020mm l x 1255mm h | 11 | No. | 418 | 4598 | 100% | 4598 | 0 | 4598
| Carcass to Cistern Top; 220mm w x 1460mm l x 1255mm h | 11 | No. | 597 | 6567 | 100% | 6567 | 0 | 6567
Access Panel to Equipment (Provisional)
| Size 355 x 600mm | 11 | No. | 394 | 4334 |  | 0 | 0 | 0
TYPE 11D (4 No's)
Vanity counter cabinet (Stoneworks by others)
| Master Bath Vanity; Ref: 071.2 - under vanity drawers | 4 | No. | 1089 | 4356 |  | 0 | 0 | 0
Support to Vanity Counter
| Master Bath Vanity; Ref: 071.2 | 4 | No. | 3421 | 13684 |  | 0 | 0 | 0
| Powder Room; Vanity Type 4; Ref: 070.11 | 4 | No. | 1265 | 5060 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top; 220mm w x 1020mm l x 1255mm h | 4 | No. | 418 | 1672 | 100% | 1672 | 0 | 1672
| Carcass to Cistern Top; 220mm w x 1460mm l x 1255mm h | 4 | No. | 597 | 2388 | 100% | 2388 | 0 | 2388
Access Panel to Equipment (Provisional)
| Size 355 x 600mm | 4 | No. | 394 | 1576 |  | 0 | 0 | 0
TYPE 12A (5 No's) - 1 Bed Suite
Vanity counter cabinet (Stoneworks by others)
| Master Bath Vanity; Ref: 071.2 - under vanity drawers | 5 | No. | 1089 | 5445 |  | 0 | 0 | 0
Support to Vanity Counter
| Master Bath Vanity; Ref: 071.2 | 5 | No. | 3421 | 17105 |  | 0 | 0 | 0
| Powder Room; Vanity Type 5; Ref: 070.12 det. 9 | 5 | No. | 1619 | 8095 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top; 220mm w x 1000mm l x 1255mm h | 5 | No. | 418 | 2090 | 100% | 2090 | 0 | 2090
| Carcass to Cistern Top; 220mm w x 1400mm l x 1255mm h | 5 | No. | 597 | 2985 | 100% | 2985 | 0 | 2985
TYPE 13A (1 No) - 1 Bed Suite
Vanity counter cabinet (Stoneworks by others)
Support to Vanity Counter
| Powder Room; Vanity Type 5; Ref: 070.12 det. 7 | 1 | No. | 1593 | 1593 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top; 220mm w x 1290mm l x 1255mm h | 1 | No. | 497 | 497 | 100% | 497 | 0 | 497
TYPE 14A (4 No's) - 1 Bed Suite
Vanity counter cabinet (Stoneworks by others)
Support to Vanity Counter
| Powder Room; Vanity Type 5; Ref: 070.12 det. 8 | 4 | No. | 1120 | 4480 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top; 220mm w x 1165mm l x 1255mm h | 4 | No. | 497 | 1988 | 100% | 1988 | 0 | 1988
Support to Vanity Counter
TYPE 19A (6 No's) - 1 Bed Suite
| Vanity Type 1, Ref.070.0 | 6 | No. | 4780 | 28680 |  | 0 | 0 | 0
Support to Cistern (Stone by others)
| Carcass to Cistern Top; 220mm w x 1080mm l x 1255mm h | 6 | No. | 437 | 2622 | 100% | 2622 | 0 | 2622
Preliminaries
| Preliminaries (Mobilization - 10%) | 1 | item | 133516 | 133516 | 100% | 133516 | 0 | 133516
| Preliminaries (Time related - 30%) | 1 | item | 400548 | 400548 | 100% | 400548 | 0 | 400548
| Preliminaries Progress related - 60%) | 1 | item | 801096 | 801096 | 83.05% | 649879.7229 | 15412.2917 | 665292.0147
| Provisional Sum - Allow for 12 Numbers of Units (Standard Guest rooms, 1 Bed Double height rooms, presidential suite and Royal Suite) | 1 | item | 709387 | 709387 | 86.98% | 617012.7627 | 0 | 617012.7627
[7 empty] | 9421164.8638 | 196130.1547 | 9617295.0185

## Variation
VO No | Description | Amount | Previous | This Month | Progress % | Cumulative
1 | Damaged Items (by Roberts) | 371251.04 | 0 | 0 | 0% | 0
2 | Damages on Installed Joinery Items - Water Leakage at 1301 |  | 0 | 0 | 0% | 0
3 | Damages on Installed Joinery Items - Door Architrave, Wardrobe and Timber Panel (Location: Guestrooms at Level 08 – Rm. 08, Level 24 – Rm. 17 and Level 25 – Rm. 15) |  | 0 | 0 | 0% | 0
4 | DOOR VARIATION ORDER – OMISSION OF SCOPE Hotel - Corridor & Lift Lobby Timber Works (Level 7-16 & Level 19-27) (19 Levels) Adjustment of Corridor Doors | -65700 | -57144.744 | 0 | 86.98% | -57144.744
5 | Permanent Access Panel and Removable Shelf to Wardrobe in Level 7,708 | 1202.67 | 1202.67 | 0 | 100% | 1202.67
6 | Permanent access panel and removable shelf to Wardobe for 19A type suites | 9621.36 | 9621.36 | 0 | 100% | 9621.36
7 | Modification of Entrance Lounge Cabinet-Room Type 11 | 26041.02 | 26041.02 | 0 | 100% | 26041.02
8 | Increase to door jamb thickness | 9444.55 | 9444.55 | 0 | 100% | 9444.55
9 | Omission of corridor cladding and ceiling | -164860.58 | 0 | 0 |  | 0
10 | Provision of 25mm hole and groove for electrical conduits | 37723.28 | 37723.28 | 0 | 100% | 37723.28
11 | Omission of Corridor Doors (HO-TB-21 and HO-TB-23) | -241493 | -113394.0571 | 0 | 46.96% | -113394.0571
12 | Modification of Minibar works for 07A series in all apartments | 16203.28 | 0 | 0 | 0% | 0
14 | Modification to Minibar height in Apt 2401, 12A Series | 3597.17 | 3597.17 | 0 | 100% | 3597.17
15 | Modifications to hotel guest room 11 series (A, B, C & D) Mini bar cabinet to suit revised ceiling levels/MEP services | 53014.2 | 26507.1 | 0 | 50% | 26507.1
16 | Modification to Wardrobe, Type 13A, Walk-in Closet Type 1-6A & Type 1-C | 5024.84 | 5024.84 | 0 | 100% | 5024.84
17 | Permanent access panel and removable shelf to Wardrobe for 14A type suites (4 Rooms) | 7204.14 | 7204.14 | 0 | 100% | 7204.14
| Permanent access panel to Type 1A Rooms (2810, 2610, 2512) and 15A Rooms (1007, 2305) |  | 0 | 0 | 0% | 0
| Modifications to 7A type suites electrical cabinets | 0 | 0 | 0 | 0% | 0
| Supply and installation of allen key locks for ELV Boxes nd DB doors @ Guest Rooms |  | 0 | 0 | 0% | 0
| Provision of Wardrobe Access Panels for MEP Services in Type 13A |  | 0 | 0 | 0% | 0
| Modification of vanity drawr units in level 12-27 floors, 11 and 12A Series |  | 0 | 0 | 0% | 0
| Skirting extension for the back of beds |  | 0 | 0 | 0% | 0
| Provision of permanent access panels on cupboard for LV box access and ONU |  | 0 | 0 | 0% | 0
VO-0156 | Joinery - Additional Sofa bed for 7A Guestrooms The Employer’s representative issued comments on shop drawings via OMRED-WTRAN-002487 dated 16th of January 2020.As per the comments on the shop drawing of type 7A hotel guestrooms, additional item of sofa base is included to the scope of joinery work sub-contractor, which further contribute additional cost impact. | 10750 | 10750 | 0 | 100% | 10750
VO-0157 | Joinery - Change of material inside Minibar for typical Guestrooms As per the comments on the shop drawing typical minibar drawings, an additional item of fabric & metal to inside of minibar unit. Which further contribute an additional work to the joinery work subcontractor & thus incurred additional cost impact. | 92621.25 | 92621.25 | 0 | 100% | 92621.25
| Joinery - Change in Veneer to natural veneer | 0 |  | 0 |  | 0
| Painting Hotel - Change in moulding setout around the bed head | 0 |  | 0 |  | 0
| Painting - Change in paint colour | 0 |  | 0 |  | 0
| Joinery - Change minibar finish from stone to mirror | 0 |  | 0 |  | 0
| Joinery - Provide additional shoe rack & tie rack to hotel guestrooms Employer's representative confirmed to provide additional shoe rack & tie rack to hotel guestrooms | 132176.95 | 132176.95 | 0 | 100% | 132176.95
| Joinery - Change in Door Finish As per the comments on the shop drawing of type 7A hotel guestrooms, door finish has to be change in accordance with the pattern matching to corridor, which further contribute additional cost impact to ID subcontractor. | 1781.72 | 1781.72 | 0 | 100% | 1781.72
| Joinery - Increase in Vaneer to doors Employer's representative instructed vide OMERED-GNC-00144 to proceed with veneer on solid wood modlings to the door types TB-18,TB-19,TB-06,TB-07. | 16037.74 | 16037.74 | 0 | 100% | 16037.74
| Joinery - Extraover for PS timber works (PS adjustment for ASI acope) 15A & 7A | -293613.89 | -255380.3741 | 0 | 86.98% | -255380.3741
| Joinery - Brass materials to metal knob, grab handle and metal insert | 0 |  | 0 |  | 0
| Joinery - Additional metal plate to Guest room door Jamb | 0 |  | 0 |  | 0
| Joinery - Additional metal cabinet & metal backsplash to hotel guestroom minibar. This metal backsplash & metal cabinet was not included in the initial recommendation of hotel guestroom joinery package (ASI) | 169811.32 | 66396.2261 | 0 | 39.1% | 66396.2261
| Joinery - Timber access panel has to be provided to hotel guestroom as per shop drawing comments-ASI Cost | 28301.89 | 28301.89 | 0 | 100% | 28301.89
VO-0296 | Shop drawing comments, additional moulding to be provided on hotel guestroom wardrobe & DB units. ASI | 56603.77 | 56603.77 | 0 | 100% | 56603.77
VO-0298 | Joinery - MDF Support for Fabric Panel in 11A, 11B, 11C & 1D Hotel Guestrooms as per shop drawing comments | 8952.83 | 8236.6036 | 0 | 92% | 8236.6036
VO-0313 | Joinery - Addition of Library shelf to Room type 11 at Hotel guest rooms as per the instruction OMERED-INST-0000020 for alternative design for hotel guestroom | 47169.81 | 33018.867 | 0 | 70% | 33018.867
| Revision in interleading door, glass door to timber door provisional sum Adjustment 11 serious Guest room | 146698.64 | 146698.64 | 0 | 100% | 146698.64
| Hotel Corridor joinery | 460045.06 | 400139.3787 | 0 | 86.98% | 400139.3787
| Supply & Installation of Painted skirting | 332424 | 332424 | 0 | 100% | 332424
| Hotel Corridor Fire Hose Cabinet | 85856.82 | 51105.25 | 0 | 59.52% | 51105.25
| ELV Box to Hotel Guest Room | 46035 | 46035 | 0 | 100% | 46035
| Descope Stone support Frame works | -765937 | -666198.9921 | 0 | 86.98% | -666198.9921
| Bathtub Stone support | 0 |  | 0 |  | 0
VO-0152 | Joinery - Removal of Interconnecting Doors As per Employer's representative instruction vide OMERED-INST-0000003 , to proceed with the omission of interleading door in hotel guestroom type 1A & 1c, which deem to vary from original scope of work and incurred variation. | -67340 | -67340 | 0 | 100% | -67340
VO-0218 | Joinery - Cancenllation of Wooden Panelling for Painted Gypsum As per the Employer's Representative instruction ( OMERED-INST-000027) wall wooden panelling is cancelled & paint finish is introduced. ( Cost saving) | -100000 | -100000 | 0 | 100% | -100000
| Adjustment as per the Addendum Agreement | 331079.98 | 331079.98 | 0 | 100% | 331079.98
| ID level 8 full height mirror | 0 |  | 0 |  | 0
VO-0158 | Resi ID - Change from manually operated blinds to motorized The Employer’s representative commented on the RFI response ASI-ID-RFI-L8-0003623 via Aconex Ref: OMERED-WTRAN-001016 dated 25th July 2019 to provide motorized Venetian Shutter. This is deviating from the approved Venetian blinds which is working manually & deem to variation to the contract. | 29000 | 29000 | 0 | 100% | 29000
VO-0159 | Resi ID - Supply and install Fluted Glass for Master Bedroom The Employer’s representative commented on the RFI response ASI-ID-SD-L8-10305 via Aconex Ref: OMEREDWTRAN-002174 dated 23rd December 2019 to supply and install Fluted Glass for Master Bedroom. This deem to be additional to original scope & incurred variation | 8762 | 8762 | 0 | 100% | 8762
VO-0242 | Resi ID - New finishes to wall, floor & ceiling to the AV room As per the comments to the level – 8 room type 2A, 4A & 4B rack mark-up drawings, the Employer’s representative has recommended new finishes to wall, floor & ceiling to the AV room & also to increase the size of AV room door as per the MEP requirements. | 4593.1226 | 4593.1226 | 0 | 100% | 4593.1226
VO-0243 | Resi ID - Increase in Stone skirting As per the comments from the Employer representatives on level 8 4B snug room, the stone skirting shall extend along the facade spandrel, which is deviating from our original scope of work & thus contribute an additional cost impact. The variation cost proposal associated with the instruction is attached here. | 4290 | 4290 | 0 | 100% | 4290
VO-0244 | Resi ID - Maid Rooms Fitout The Employer’s representative instructed to proceed with the fit out works & timber doors to maid’s room in 2A,4A & 4B apartment. Maid's room was not included in the original scope to ID subcontractor & thus accumulate additional cost impact | 21172 | 21172 | 0 | 100% | 21172
VO-0297 | Resi ID - Addition of Steel Frame & Change in Stone Finish at Level 8 First Place | 35000 | 35000 | 0 | 100% | 35000
| New Design to 4B level 8 | 0 |  | 0 |  | 0
| Shifting loose furniture and installation of chandelier | 0 |  | 0 |  | 0
| Supply & installation of Wooden skirting in sales center | 7644 | 7644 | 0 | 100% | 7644
| Descoped Wall covering | -64458 | -64458 | 0 | 100% | -64458
| Descoped Fabrics | -101583 | -101583 | 0 | 100% | -101583
| Frosted film for GD-03 glass | 42268 |  | 0 |  | 0
| Timber Frame for GD -08 Door | 15608 |  | 0 |  | 0
| TB-21 Door finish changes | 8559 |  | 0 |  | 0
| Rectification works due to damage by others | 5000 |  | 0 |  | 0
| Wardrobe height change | 53848 |  | 0 |  | 0
| Vanity Carcase for 7A and 15A room | 0 |  | 0 |  | 0
| Additional preliminaries (for new subcontract period) | 750000 | 666666.6667 | 0 | 88.89% | 666666.6667 | Work is not full completed to pay 100%
|  | 1627432.9826 | 1231402.0175 | 0 |  | 1231402.0175

## Progress
[6 empty] | Wardrobe | [6 empty] | Door
SR No | Level | Room Name | Room Type | Room No | Room Category | Walk in | One sided | Walk in one sided | Total | Minibar | Timber Screen | DB | HO-TB-01 Entrance door | HO-TB-02 Connecting | HO-TB-03 Double door | HO-GD-04 | HO-TB-04 Double door | HO-TB-05 Double door | HO-TB-06 Double door | HO-TB-07 | HO-TB-09 single leaf | HO-TB-10 | HO-TB-11 Single leaf | Total % | HO-GD-03 Sliding door | WC metal frame
1 | 7 | 1 BEDROOM | 8A | 701 | 8A | 98% | N/A | N/A | 98% | 85% | 85% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | 98% | N/A | N/A | 97.83% | 98% | 100%
2 | 7 | STD. GUEST | 2B | 702 | 2A/2B/2C/2D | 98% | N/A | N/A | 98% | 85% | 98% | 98% | 97.5% | 98% | N/A | n/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.88% | N/A | 100%
3 | 7 | STD. GUEST | 2C | 703 | 2A/2B/2C/2D | 98% | N/A | N/A | 98% | 85% | 98% | 98% | 97.5% | 98% | N/A | n/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.88% | N/A | 100%
4 | 7 | STD. GUEST | 3A | 704 | 3A/3B/3D/3E/3G | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
5 | 7 | STD. GUEST | 3D | 705 | 3A/3B/3D/3E/3G | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
6 | 7 | STD. GUEST | 2A | 706 | 2A/2B/2C/2D | 98% | N/A | N/A | 98% | 85% | 98% | 98% | 97.5% | N/A | N/A | n/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.83% | N/A | 100%
7 | 7 | CORNER. GUEST | 19A | 708 | 19A | 98% | N/A | N/A | 98% | 95% | 85% | 98% | 97.5% | N/A | N/A | n/A | N/A | 98% | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
8 | 7 | STD. GUEST | 1C | 709 | 1B/1C | 98% | N/A | N/A | 98% | N/A | N/A | 85% | 97.5% | N/A | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.83% | N/A | 100%
9 | 7 | JUNIOR SUITE | 4B | 710 | 4A/4B | N/A | 100% | N/A | 100% | 95% | N/A | 98% | 97.5% | N/A | N/A | n/A | N/A | N/A | N/A | N/A | 98% | N/A | N/A | 97.75% | N/A | 100%
10 | 7 | CORNER. GUEST | 7A | 707 | PROV.SUM | 95% | N/A | N/A | 95% | 0% | N/A | 90% | 90% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 90% | N/A | 90% | N/A | 100%
11 | 8 | 1 BEDROOM | 8A | 801 | 8A | 98% | N/A | N/A | 98% | 95% | 85% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | 98% | N/A | N/A | 97.83% | 98% | 100%
12 | 8 | STD. GUEST | 2B | 802 | 2A/2B/2C/2D | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.83% | N/A | 100%
13 | 8 | STD. GUEST | 2C | 803 | 2A/2B/2C/2D | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | 98% | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.88% | N/A | 100%
14 | 8 | STD. GUEST | 3A | 804 | 3A/3B/3D/3E/3G | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
15 | 8 | STD. GUEST | 3D | 805 | 3A/3B/3D/3E/3G | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
16 | 8 | STD. GUEST | 2A | 806 | 2A/2B/2C/2D | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.83% | N/A | 100%
17 | 8 | STD. GUEST | 1B | 807 | 1B/1C | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | 98% | N/A | N/A | N/A | N/A | N/A | N/A | 98% | N/A | N/A | 97.83% | 98% | 100%
18 | 8 | JUNIOR SUITE | 4A | 808 | 4A/4B | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | 98% | N/A | N/A | N/A | N/A | N/A | N/A | 98% | N/A | N/A | 97.83% | N/A | 100%
19 | 9 | 1 BEDROOM | 8A | 901 | 8A | N/A | 98% | N/A | 98% | 95% | 98% | 98% | 97.5% | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 98% | N/A | N/A | 97.88% | 98% | 100%
20 | 9 | STD. GUEST | 2B | 902 | 2A/2B/2C/2D | N/A | 98% | N/A | 98% | 95% | 98% | 98% | 97.5% | 98% | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.88% | N/A | 100%
21 | 9 | STD. GUEST | 2C | 903 | 2A/2B/2C/2D | N/A | 98% | N/A | 98% | 95% | 98% | 98% | 97.5% | 98% | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.88% | N/A | 100%
22 | 9 | STD. GUEST | 3A | 904 | 3A/3B/3D/3E/3G | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
23 | 9 | STD. GUEST | 3D | 905 | 3A/3B/3D/3E/3G | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
24 | 9 | STD. GUEST | 2A | 906 | 2A/2B/2C/2D | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.83% | N/A | 100%
25 | 9 | 1 BEDROOM | 9A | 907 | 9A | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | 98% | N/A | N/A | 97.83% | 98% | 100%
26 | 9 | 1 BEDROOM | 9B | 908 | 9B | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 98% | N/A | N/A | 97.75% | 98% | 100%
27 | 9 | STD. GUEST | 1B | 909 | 1B/1C | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
28 | 9 | JUNIOR SUITE | 4A | 910 | 4A/4B | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | 98% | N/A | N/A | N/A | N/A | N/A | N/A | 98% | N/A | N/A | 97.83% | N/A | 100%
29 | 10 | 1 BEDROOM | 8A | 1001 | 8A | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | 98% | N/A | N/A | 97.83% | 98% | 100%
30 | 10 | STD. GUEST | 2B | 1002 | 2A/2B/2C/2D | N/A | 98% | N/A | 98% | 95% | 98% | 98% | 97.5% | 98% | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.88% | N/A | 100%
31 | 10 | STD. GUEST | 2C | 1003 | 2A/2B/2C/2D | N/A | 98% | N/A | 98% | 95% | 98% | 98% | 97.5% | 98% | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.88% | N/A | 100%
32 | 10 | STD. GUEST | 3A | 1004 | 3A/3B/3D/3E/3G | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
33 | 10 | STD. GUEST | 3D | 1005 | 3A/3B/3D/3E/3G | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
34 | 10 | STD. GUEST | 2A | 1006 | 2A/2B/2C/2D | N/A | 98% | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.83% | N/A | 100%
35 | 10 | STD. GUEST | 1B | 1008 | 1B/1C | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
36 | 10 | JUNIOR SUITE | 4A | 1009 | 4A/4B | N/A | 98% | N/A | 98% | 95% | 98% | 98% | 97.5% | 98% | N/A | N/A | N/A | N/A | N/A | N/A | 98% | N/A | N/A | 97.83% | N/A | 100%
37 | 10 | DOUBLE HT | 15A |  | PROV.SUM | 95% | N/A | N/A | 95% | 90% | 90% | 90% | 90% | N/A | N/A | n/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 90% | N/A | 100%
38 | 11 | 1 BEDROOM | 8A | 1101 | 8A | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | 98% | N/A | N/A | 97.83% | 98% | 100%
39 | 11 | STD. GUEST | 2B | 1102 | 2A/2B/2C/2D | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | 98% | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.88% | N/A | 100%
40 | 11 | STD. GUEST | 2C | 1103 | 2A/2B/2C/2D | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | 98% | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.88% | N/A | 100%
41 | 11 | STD. GUEST | 3A | 1104 | 3A/3B/3D/3E/3G | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
42 | 11 | STD. GUEST | 3D | 1105 | 3A/3B/3D/3E/3G | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
43 | 11 | STD. GUEST | 2A | 1106 | 2A/2B/2C/2D | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.83% | N/A | 100%
44 | 11 | CORNER. GUEST | 16A | 1107 | 16A | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | N/A | N/A | N/A | 98% | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
45 | 11 | STD. GUEST | 1B | 1108 | 1B/1C | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
46 | 11 | JUNIOR SUITE | 4A | 1109 | 4A/4B | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | 98% | N/A | N/A | N/A | N/A | N/A | N/A | 98% | N/A | N/A | 97.83% | N/A | 100%
47 | 12 | 1 BEDROOM | 10A | 1201 | 10A | 98% | 98% |  | 98% | N/A | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | 98% | N/A | N/A | 97.83% | 98% | 100%
48 | 12 | STD. GUEST | 3G | 1202 | 3A/3B/3D/3E/3G | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 0% | 100%
49 | 12 | STD. GUEST | 2B | 1203 | 2A/2B/2C/2D | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.83% | N/A | 100%
50 | 12 | DELUX SUITE | 11C | 1204 | 11A/11B/11C/11D | 90% | N/A | N/A | 90% | 85% | 85% | 98% | 85% | 98% | N/A | 97.5% | N/A | N/A | 85% | N/A | N/A | N/A | N/A | 91.38% | N/A | 100%
51 | 12 | STD. GUEST | 3D | 1205 | 3A/3B/3D/3E/3G | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
52 | 12 | STD. GUEST | 2B | 1206 | 2A/2B/2C/2D | 98% | 98% | N/A | 98% | 85% | 98% | 98% | 97.5% | 98% | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.88% | N/A | 100%
53 | 12 | DELUX SUITE | 11C | 1207 | 11A/11B/11C/11D | 90% | N/A | N/A | 90% | 85% | 85% | 98% | 85% | 98% | N/A | 97.5% | N/A | N/A | 85% | N/A | N/A | N/A | N/A | 91.38% | N/A | 100%
54 | 12 | STD. GUEST | 3D | 1208 | 3A/3B/3D/3E/3G | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
55 | 12 | STD. GUEST | 2A | 1209 | 2A/2B/2C/2D | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.83% | N/A | 100%
56 | 12 | 1 BEDROOM | 9A | 1210 | 9A | 98% | N/A | N/A | 98% | 95% | 85% | 98% | 97.5% | N/A | 98% | N/A | N/A | 98% | N/A | N/A | N/A | N/A | N/A | 97.83% | 98% | 100%
57 | 12 | 1 BEDROOM | 9B | 1211 | 9B | 98% | N/A | N/A | 98% | 95% | 85% | 98% | 97.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 98% | N/A | N/A | 97.75% | 98% | 100%
58 | 12 | STD. GUEST | 1A | 1212 | 1A | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | 98% | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.88% | N/A | 100%
59 | 12 | STD. GUEST | 2F | 1213 | 2E/2F/2G/2H | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | 98% | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.88% | N/A | 100%
60 | 12 | STD. GUEST | 3C | 1214 | 3C/3F | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
61 | 12 | STD. GUEST | 3F | 1215 | 3C/3F | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
62 | 12 | STD. GUEST | 2G | 1216 | 2E/2F/2G/2H | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | 98% | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.88% | N/A | 100%
63 | 12 | STD. GUEST | 2E | 1217 | 2E/2F/2G/2H | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | 98% | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.88% | N/A | 100%
64 | 12 | JUNIOR SUITE | 5A | 1218 | 5A | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | 98% | N/A | N/A | 97.83% | N/A | 100%
65 | 13 | 1 BEDROOM | 10A | 1301 | 10A | 98% |  |  | 98% | N/A | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | 98% | N/A | N/A | 97.83% | 98% | 100%
66 | 13 | STD. GUEST | 3G | 1302 | 3A/3B/3D/3E/3G | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
67 | 13 | STD. GUEST | 2B | 1303 | 2A/2B/2C/2D | 98% | 98% | N/A | 98% | 85% | 98% | 98% | 97.5% | 98% | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.88% | N/A | 100%
68 | 13 | DELUX SUITE | 11C | 1304 | 11A/11B/11C/11D | 98% | N/A | N/A | 98% | 85% | 85% | 98% | 85% | 98% | N/A | 97.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 93.5% | N/A | 100%
69 | 13 | STD. GUEST | 3D | 1305 | 3A/3B/3D/3E/3G | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
70 | 13 | STD. GUEST | 2B | 1306 | 2A/2B/2C/2D | 98% | N/A | N/A | 98% | 85% | 98% | 98% | 97.5% | 98% | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.88% | N/A | 100%
71 | 13 | DELUX SUITE | 11C | 1307 | 11A/11B/11C/11D | 95% | N/A | N/A | 95% | 85% | 85% | 98% | 85% | 98% | N/A | 97.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 93.5% | N/A | 100%
72 | 13 | STD. GUEST | 3D | 1308 | 3A/3B/3D/3E/3G | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
73 | 13 | STD. GUEST | 2A | 1309 | 2A/2B/2C/2D | N/A | 98% | N/A | 98% | 85% | 98% | 98% | 97.5% | N/A | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.83% | N/A | 100%
74 | 13 | CORNER. GUEST | 19A | 1311 | 19A | 98% | N/A | N/A | 98% | 95% | 85% | 98% | 97.5% | N/A | 98% | N/A | N/A | 98% | N/A | N/A | N/A | N/A | N/A | 97.83% | 0% | 100%
75 | 13 | STD. GUEST | 1A | 1312 | 1A | 98% | N/A | N/A | 98% | 85% | 98% | 98% | 97.5% | 98% | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.88% | N/A | 100%
76 | 13 | STD. GUEST | 2F | 1313 | 2E/2F/2G/2H | N/A | 98% | N/A | 98% | 85% | 98% | 98% | 97.5% | 98% | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.88% | N/A | 100%
77 | 13 | STD. GUEST | 3C | 1314 | 3C/3F | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
78 | 13 | STD. GUEST | 3F | 1315 | 3C/3F | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
79 | 13 | STD. GUEST | 2G | 1316 | 2E/2F/2G/2H | 98% | N/A | N/A | 98% | 85% | 98% | 98% | 97.5% | 98% | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.88% | N/A | 100%
80 | 13 | STD. GUEST | 2E | 1317 | 2E/2F/2G/2H | 98% | N/A | N/A | 98% | 85% | 98% | 98% | 97.5% | 98% | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.88% | N/A | 100%
81 | 13 | JUNIOR SUITE | 5A | 1318 | 5A | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | N/A | 100%
82 | 13 | DELUX SUITE | 7A |  | PROV.SUM | 95% | N/A | N/A | 95% | 20% | N/A | 90% | 90% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 90% | N/A | 90% | N/A | 100%
83 | 14 | 1 BEDROOM | 10A | 1401 | 10A | 98% |  |  | 98% | N/A | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | 98% | N/A | N/A | 97.83% | 98% | 100%
84 | 14 | STD. GUEST | 3G | 1402 | 3A/3B/3D/3E/3G | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | 97.83% | 98% | 100%
85 | 14 | STD. GUEST | 2B | 1403 | 2A/2B/2C/2D | 98% | N/A | N/A | 98% | 85% | 98% | 98% | 97.5% | N/A | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.83% | 98% | 100%
86 | 14 | DELUX SUITE | 11C | 1404 | 11A/11B/11C/11D | 98% | N/A | N/A | 98% | 85% | 95% | 98% | 85% | N/A | N/A | 97.5% | N/A | N/A | 85% | N/A | N/A | N/A | N/A | 89.17% | N/A | 100%
87 | 14 | STD. GUEST | 3D | 1405 | 3A/3B/3D/3E/3G | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
88 | 14 | STD. GUEST | 2B | 1406 | 2A/2B/2C/2D | 98% | N/A | N/A | 98% | 85% | 98% | 98% | 97.5% | N/A | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.83% | N/A | 100%
89 | 14 | DELUX SUITE | 11C | 1407 | 11A/11B/11C/11D | 90% | N/A | N/A | 90% | 85% | 85% | 98% | 85% | 98% | N/A | 85% | N/A | N/A | 85% | N/A | N/A | N/A | N/A | 88.25% | N/A | 100%
90 | 14 | STD. GUEST | 3D | 1408 | 3A/3B/3D/3E/3G | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
91 | 14 | STD. GUEST | 2A | 1409 | 2A/2B/2C/2D | 98% | 98% | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | 85% | 94.62% | N/A | 100%
92 | 14 | STD. GUEST | 1A | 1410 | 1A | 98% | N/A | N/A | 98% | 85% | 98% | 98% | 97.5% | N/A | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.83% | N/A | 100%
93 | 14 | STD. GUEST | 2F | 1411 | 2E/2F/2G/2H | N/A | 98% | N/A | 98% | 95% | 98% | 98% | 97.5% | 98% | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.88% | N/A | 100%
94 | 14 | STD. GUEST | 3C | 1412 | 3C/3F | N/A | 98% | N/A | 98% | 95% | 98% | 98% | 97.5% | 98% | 98% | N/A | N/A | N/A | 98% | N/A | N/A | N/A | N/A | 97.88% | N/A | 100%
95 | 14 | STD. GUEST | 3F | 1413 | 3C/3F | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
96 | 14 | STD. GUEST | 2G | 1414 | 2E/2F/2G/2H | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.83% | 98% | 100%
97 | 14 | STD. GUEST | 2E | 1415 | 2E/2F/2G/2H | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | 98% | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.88% | N/A | 100%
98 | 14 | JUNIOR SUITE | 5A | 1416 | 5A | N/A | 98% | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.88% | N/A | 100%
99 | 15 | 1 BEDROOM | 10A | 1501 | 10A | 98% |  | 100% | 99% | N/A | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | 98% | N/A | N/A | 97.83% | 98% | 100%
100 | 15 | STD. GUEST | 3G | 1502 | 3A/3B/3D/3E/3G | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
101 | 15 | STD. GUEST | 2B | 1503 | 2A/2B/2C/2D | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.83% | N/A | 100%
102 | 15 | DELUX SUITE | 11C | 1504 | 11A/11B/11C/11D | 95% | N/A | N/A | 95% | 85% | 85% | 98% | 97.5% | 98% | N/A | 97.5% | N/A | N/A | 85% | N/A | N/A | N/A | N/A | 94.5% | N/A | 100%
103 | 15 | STD. GUEST | 3D | 1505 | 3A/3B/3D/3E/3G | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
104 | 15 | STD. GUEST | 2B | 1506 | 2A/2B/2C/2D | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | 98% | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.88% | N/A | 100%
105 | 15 | DELUX SUITE | 11C | 1507 | 11A/11B/11C/11D | 98% | N/A | N/A | 98% | 85% | 85% | 98% | 97.5% | 98% | N/A | 97.5% | N/A | N/A | 85% | N/A | N/A | N/A | N/A | 94.5% | N/A | 100%
106 | 15 | STD. GUEST | 3D | 1508 | 3A/3B/3D/3E/3G | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
107 | 15 | STD. GUEST | 2A | 1509 | 2A/2B/2C/2D | 98% | N/A | N/A | 98% | 85% | 98% | 98% | 97.5% | N/A | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.83% | N/A | 100%
108 | 15 | CORNER. GUEST | 19A | 1510 | 19A | N/A | 98% | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.83% | 98% | 100%
109 | 15 | STD. GUEST | 1A | 1512 | 1A | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.83% | N/A | 100%
110 | 15 | STD. GUEST | 2F | 1513 | 2E/2F/2G/2H | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | 98% | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.88% | N/A | 100%
111 | 15 | STD. GUEST | 3C | 1514 | 3C/3F | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
112 | 15 | STD. GUEST | 3F | 1515 | 3C/3F | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.83% | 98% | 100%
113 | 15 | STD. GUEST | 2G | 1516 | 2E/2F/2G/2H | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | 98% | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.88% | N/A | 100%
114 | 15 | STD. GUEST | 2E | 1517 | 2E/2F/2G/2H | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.88% | N/A | 100%
115 | 15 | JUNIOR SUITE | 5A | 1518 | 5A | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | 98% | N/A | N/A | N/A | 85% | N/A | N/A | 94.62% | N/A | 100%
116 | 15 | DELUX SUITE | 7A |  | PROV.SUM | 95% | N/A | N/A | 95% | 20% | N/A | 82% | 0% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | 90% | N/A | 62.67% | N/A | 100%
117 | 16 | 1 BEDROOM | 10A | 1601 | 10A | 98% |  |  | 98% | N/A | 98% | 98% | 97.5% | N/A | N/A | N/A | 98% | N/A | N/A | N/A | 98% | N/A | N/A | 97.83% | 98% | 100%
118 | 16 | DELUX SUITE | 11D | 1602 | 11A/11B/11C/11D | 98% | N/A | N/A | 98% | 85% | 97.5% | 98% | 85% | N/A | N/A | 98% | N/A | N/A | 98% | N/A | N/A | N/A | N/A | 93.67% | N/A | 100%
119 | 16 | STD. GUEST | 2C | 1603 | 2A/2B/2C/2D | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | 97.5% | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.75% | N/A | 100%
120 | 16 | STD. GUEST | 3A | 1604 | 3A/3B/3D/3E/3G | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
121 | 16 | STD. GUEST | 3D | 1605 | 3A/3B/3D/3E/3G | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/AA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
122 | 16 | STD. GUEST | 2B | 1606 | 2A/2B/2C/2D | 98% | N/A | N/A | 98% | 85% | 98% | 98% | 97.5% | 97.5% | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.75% | N/A | 100%
123 | 16 | DELUX SUITE | 11C | 1607 | 11A/11B/11C/11D | 98% | N/A | N/A | 98% | 85% | 85% | 98% | 85% | 97.5% | N/A | 97.5% | N/A | N/A | 85% | N/A | N/A | N/A | N/A | 91.25% | N/A | 100%
124 | 16 | STD. GUEST | 3D | 1608 | 3A/3B/3D/3E/3G | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
125 | 16 | STD. GUEST | 2A | 1609 | 2A/2B/2C/2D | 98% | N/A | N/A | 98% | 85% | 98% | 98% | 97.5% | N/A | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.83% | N/A | 100%
126 | 16 | STD. GUEST | 1C | 1610 | 1B/1C | 98% | N/A | N/A | 98% | N/A | N/A | 98% | 97.5% | N/A | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.83% | N/A | 100%
127 | 16 | STD. GUEST | 2H | 1611 | 2E/2F/2G/2H | 98% | N/A | N/A | 98% | 85% | 98% | 98% | 97.5% | N/A | N/A | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.83% | N/A | 100%
128 | 16 | STD. GUEST | 3C | 1612 | 3C/3F | N/A | 98% | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
129 | 16 | STD. GUEST | 3F | 1613 | 3C/3F | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | 98% | 100%
130 | 16 | STD. GUEST | 2G | 1614 | 2E/2F/2G/2H | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | N/A | N/A | 98% | 85% | N/A | N/A | N/A | N/A | 98% | 94.62% | 98% | 100%
131 | 16 | STD. GUEST | 2E | 1615 | 2E/2F/2G/2H | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | 98% | 98% | N/A | N/A | N/A | N/A | N/A | 97.88% | 98% | 100%
132 | 16 | JUNIOR SUITE | 5A | 1616 | 5A | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.75% | N/A | 100%
135 | 19 | 1 BEDROOM | 12A | 1901 | 12A | 98% | N/A | N/A | 98% | 95% | 85% | 98% | 97.5% | N/A | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | N/A | 97.5% | 98% | 100%
136 | 19 | CORNER. GUEST | 19A | 1903 | 19A | 98% | N/A | N/A | 98% | 95% | 85% | 98% | 97.5% | N/A | N/A | N/A | 97.5% | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | 98% | 100%
137 | 19 | JUNIOR SUITE | 6A | 1904 | 6A | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | N/A | N/A | 97.5% | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | 98% | 100%
138 | 19 | PRESIDENTIAL | 17A | N/A | PROV.SUM | 0% | N/A | N/A | 0% | N/A | N/A | 85% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | N/A | 100%
139 | 20 | 1 BEDROOM | 12A | 2001 | 12A | 98% | N/A | N/A | 98% | 95% | 60% | 85% | 97.5% | N/A | N/A | N/A | 97.5% | N/A | N/A | N/A | 97.5% | N/A | N/A | 97.5% | 95.5% | 100%
140 | 20 | STD. GUEST | 2D | 2002 | 2A/2B/2C/2D | 98% | N/A | N/A | 98% | 95% | 98% | 85% | 97.5% | N/A | N/A | N/A | 97.5% | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | 100%
141 | 20 | STD. GUEST | 3A | 2003 | 3A/3B/3D/3E/3G | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | N/A | N/A | 97.5% | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | 95.5% | 100%
142 | 20 | DELUX SUITE | 11B | 2004 | 11A/11B/11C/11D | 98% | N/A | N/A | 98% | 0% | N/A | 98% | 97.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | 100%
143 | 20 | CORNER. GUEST | 19A | 2006 | 19A | 98% | N/A | N/A | 98% | 90% | 60% | 85% | 97.5% | N/A | N/A | N/A | N/A | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | 0% | 100%
144 | 20 | JUNIOR SUITE | 6A | 2007 | 6A | 98% | N/A | N/A | 98% | 95% | 98% | 85% | 97.5% | N/A | N/A | N/A | N/A | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | 95.5% | 100%
145 | 20 | DELUX SUITE | 7A |  | PROV.SUM | 98% | N/A | N/A | 98% | 20% | N/A | 82% | 85% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 985% | N/A | 535% | N/A | 80%
146 | 21 | 1 BEDROOM | 12A | 2101 | 12A | 98% | N/A | N/A | 98% | 95% | 0% | 98% | 97.5% | N/A | N/A | N/A | N/A | 97.5% | N/A | N/A | 97.5% | N/A | N/A | 97.5% | 95.5% | 100%
147 | 21 | STD. GUEST | 2D | 2102 | 2A/2B/2C/2D | 98% | N/A | N/A | 98% | 60% | 98% | 98% | 97.5% | N/A | N/A | N/A | 97.5% | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | 100%
148 | 21 | STD. GUEST | 3A | 2103 | 3A/3B/3D/3E/3G | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | N/A | 97.5% | 95.5% | 100%
149 | 21 | DELUX SUITE | 11B | 2104 | 11A/11B/11C/11D | 98% | N/A | N/A | 98% | 0% | N/A | 85% | 85% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 85% | N/A | 100%
150 | 21 | JUNIOR SUITE | 6A | 2105 | 6A | 98% | N/A | N/A | 98% | 60% | 60% | 98% | 97.5% | N/A | N/A | N/A | 85% | 97.5% | N/A | N/A | N/A | N/A | N/A | 93.33% | 47.75% | 100%
151 | 22 | 1 BEDROOM | 12A | 2201 | 12A | 98% | N/A | N/A | 98% | 95% | 60% | 98% | 97.5% | N/A | N/A | N/A | N/A | 97.5% | N/A | N/A | 97.5% | N/A | N/A | 97.5% | 71.63% | 100%
152 | 22 | DELUX SUITE | 11A | 2202 | 11A/11B/11C/11D | 95% | N/A | N/A | 95% | 50% | N/A | 85% | 97.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | 100%
153 | 22 | STD. GUEST | 3D | 2203 | 3A/3B/3D/3E/3G | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | N/A | 97.5% | 95.5% | 100%
154 | 22 | STD. GUEST | 2A | 2204 | 2A/2B/2C/2D | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | N/A | N/A | 97.5% | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | 100%
155 | 22 | JUNIOR SUITE | 6A | 2206 | 6A | 98% | N/A | N/A | 98% | 60% | 60% | 98% | 97.5% | N/A | N/A | N/A | 97.5% | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | 47.75% | 100%
156 | 22 | DOUBLE HT | 15A | 2205 | PROV.SUM | 95% | N/A | N/A | 95% | 50% | 25% | 85% | 97.5% | N/A | N/A | n/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | 100%
157 | 23 | 1 BEDROOM | 12A | 2301 | 12A | 98% | N/A | N/A | 98% | 95% | 98% | 98% | 97.5% | N/A | 97.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 95.5% | 96.83% | 71.63% | 100%
158 | 23 | STD. GUEST | 2D | 2302 | 2A/2B/2C/2D | 95% | N/A | N/A | 95% | 95% | 98% | 98% | 97.5% | N/A | N/A | N/A | 97.5% | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | 100%
159 | 23 | STD. GUEST | 3A | 2303 | 3A/3B/3D/3E/3G | 95% | N/A | N/A | 95% | 95% | 98% | 98% | 97.5% | N/A | 97.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.5% | 95.5% | 100%
160 | 23 | DELUX SUITE | 11B | 2304 | 11A/11B/11C/11D | 90% | N/A | N/A | 90% | 0% | N/A | 60% | 97.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | 100%
161 | 23 | CORNER. GUEST | 16A | 2305 | 16A | 95% | N/A | N/A | 95% | 95% | 60% | 98% | 97.5% | N/A | N/A | N/A | N/A | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | 95.5% | 100%
162 | 23 | JUNIOR SUITE | 6A | 2306 | 6A | 95% | N/A | N/A | 95% | 95% | 60% | 98% | 97.5% | N/A | N/A | N/A | 85% | 85% | N/A | N/A | N/A | N/A | N/A | 89.17% | 0% | 100%
163 | 24 | 1 BEDROOM | 13A | 2401 | 13A | 95% | N/A | N/A | 95% | N/A | 98% | N/A | 97.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | 100%
164 | 24 | 1 BEDROOM | 14A | 2402 | 14A | 95% | N/A | N/A | 95% | 95% | 60% | 0% | 97.5% | N/A | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | N/A | 97.5% | 0% | 100%
165 | 24 | STD. GUEST | 2D | 2403 | 2A/2B/2C/2D | 95% | N/A | N/A | 95% | 85% | 98% | 0% | 97.5% | N/A | N/A | N/A | 97.5% | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | 100%
166 | 24 | STD. GUEST | 3A | 2404 | 3A/3B/3D/3E/3G | 95% | N/A | N/A | 95% | 95% | 98% | 0% | 97.5% | N/A | 97.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.5% | 95.5% | 100%
167 | 24 | STD. GUEST | 3D | 2405 | 3A/3B/3D/3E/3G | 95% | N/A | N/A | 95% | 95% | 98% | 98% | 97.5% | N/A | N/A | N/A | 97.5% | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | 95.5% | 100%
168 | 24 | STD. GUEST | 2B | 2406 | 2A/2B/2C/2D | 95% | N/A | N/A | 95% | 85% | 98% | 0% | 97.5% | N/A | N/A | N/A | 97.5% | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | 100%
169 | 24 | DELUX SUITE | 11C | 2407 | 11A/11B/11C/11D | 90% | N/A | N/A | 90% | 0% | 0% | 0% | 0% | N/A | N/A | 85% | N/A | N/A | 85% | N/A | N/A | N/A | N/A | 56.67% | N/A | 100%
170 | 24 | STD. GUEST | 3D | 2408 | 3A/3B/3D/3E/3G | 95% | N/A | N/A | 95% | 95% | 98% | 98% | 97.5% | N/A | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | N/A | 97.5% | 95.5% | 100%
171 | 24 | STD. GUEST | 2B | 2409 | 2A/2B/2C/2D | 95% | N/A | N/A | 95% | 95% | 98% | 0% | 97.5% | 97.5% | N/A | N/A | 97.5% | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | 100%
172 | 24 | CORNER. GUEST | 19A | 2411 | 19A | 95% | N/A | N/A | 95% | 85% | 60% | 0% | 0% | N/A | N/A | N/A | N/A | 85% | N/A | N/A | N/A | N/A | N/A | 42.5% | 0% | 100%
173 | 24 | STD. GUEST | 1A | 2412 | 1A | 95% | N/A | N/A | 95% | 85% | 98% | 0% | 97.5% | N/A | N/A | N/A | 97.5% | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | 100%
174 | 24 | STD. GUEST | 2F | 2413 | 2E/2F/2G/2H | 95% | N/A | N/A | 95% | 85% | 98% | 0% | 97.5% | 97.5% | N/A | N/A | 97.5% | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | 100%
175 | 24 | STD. GUEST | 3C | 2414 | 3C/3F | 95% | N/A | N/A | 95% | 95% | 98% | 0% | 97.5% | N/A | 97.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.5% | 95.5% | 100%
176 | 24 | STD. GUEST | 3F | 2415 | 3C/3F | 95% | N/A | N/A | 95% | 95% | 98% | 0% | 97.5% | N/A | 97.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.5% | 95.5% | 100%
177 | 24 | STD. GUEST | 2G | 2416 | 2E/2F/2G/2H | 95% | N/A | N/A | 95% | 85% | 98% | 98% | 97.5% | 97.5% | N/A | N/A | 97.5% | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | 100%
178 | 24 | STD. GUEST | 2E | 2417 | 2E/2F/2G/2H | 95% | N/A | N/A | 95% | 85% | 98% | 0% | 97.5% | 97.5% | N/A | N/A | 97.5% | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | 100%
179 | 24 | JUNIOR SUITE | 5A | 2418 | 5A | 95% | N/A | N/A | 95% | 95% | 60% | 0% | 97.5% | N/A | 85% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 91.25% | N/A | 100%
180 | 24 | DELUX SUITE | 7A |  | PROV.SUM | 25% | N/A | N/A | 25% | 20% | N/A | 82% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 85% | N/A | 42.5% | N/A | 100%
181 | 25 | 1 BEDROOM | 10B | 2501 | 10B | 95% | N/A | N/A | 95% | 95% | 0% | 95% | 97.5% | N/A | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | N/A | 97.5% | 95.5% | 100%
182 | 25 | 1 BEDROOM | 14A | 2502 | 14A | 95% | N/A | N/A | 95% | 95% | 0% | 95% | 97.5% | N/A | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | N/A | 97.5% | 95.5% | 100%
183 | 25 | STD. GUEST | 2D | 2503 | 2A/2B/2C/2D | 95% | N/A | N/A | 95% | 95% | 97.5% | 95% | 97.5% | N/A | N/A | N/A | 97.5% | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | 100%
184 | 25 | STD. GUEST | 3A | 2504 | 3A/3B/3D/3E/3G | 95% | N/A | N/A | 95% | 95% | 97.5% | 95% | 97.5% | N/A | 97.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.5% | 95.5% | 100%
185 | 25 | STD. GUEST | 3D | 2505 | 3A/3B/3D/3E/3G | 95% | N/A | N/A | 95% | 95% | 97.5% | 95% | 97.5% | N/A | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | N/A | 97.5% | 95.5% | 100%
186 | 25 | STD. GUEST | 2B | 2506 | 2A/2B/2C/2D | 95% | N/A | N/A | 95% | 95% | 97.5% | 95% | 97.5% | 97.5% | N/A | N/A | 97.5% | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | 100%
187 | 25 | DELUX SUITE | 11C | 2507 | 11A/11B/11C/11D | 90% | N/A | N/A | 90% | 0% | 0% | 95% | 85% | N/A | N/A | 85% | N/A | N/A | 85% | N/A | N/A | N/A | N/A | 85% | N/A | 100%
188 | 25 | STD. GUEST | 3D | 2508 | 3A/3B/3D/3E/3G | 95% | N/A | N/A | 95% | 95% | 90% | 95% | 97.5% | N/A | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | N/A | 97.5% | 0% | 100%
189 | 25 | STD. GUEST | 2B | 2509 | 2A/2B/2C/2D | 95% | N/A | N/A | 95% | 95% | 60% | 95% | 97.5% | N/A | N/A | n/A | 85% | 85% | N/A | N/A | N/A | N/A | N/A | 89.17% | N/A | 100%
190 | 25 | STD. GUEST | 1A | 2510 | 1A | 95% | N/A | N/A | 95% | 95% | 60% | 95% | 97.5% | N/A | N/A | N/A | 97.5% | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | 100%
191 | 25 | STD. GUEST | 2F | 2511 | 2E/2F/2G/2H | 95% | N/A | N/A | 95% | 95% | 60% | 95% | 97.5% | 97.5% | N/A | N/A | 97.5% | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | 100%
192 | 25 | STD. GUEST | 3C | 2512 | 3C/3F | 95% | N/A | N/A | 95% | 95% | 97.5% | 95% | 97.5% | N/A | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | N/A | 97.5% | 95.5% | 100%
193 | 25 | STD. GUEST | 3F | 2513 | 3C/3F | 95% | N/A | N/A | 95% | 95% | 97.5% | 95% | 97.5% | N/A | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | N/A | 97.5% | 0% | 100%
194 | 25 | STD. GUEST | 2G | 2514 | 2E/2F/2G/2H | 95% | N/A | N/A | 95% | 95% | 97.5% | 95% | 97.5% | 97.5% | N/A | N/A | 97.5% | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | 100%
195 | 25 | STD. GUEST | 2E | 2515 | 2E/2F/2G/2H | N/A | 95% | N/A | 95% | 95% | 60% | 95% | 97.5% | 97.5% | N/A | N/A | 97.5% | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | 100%
196 | 25 | JUNIOR SUITE | 5A | 2516 | 5A | 95% | N/A | N/A | 95% | 95% | 60% | 95% | 97.5% | N/A | 85% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 91.25% | N/A | 100%
197 | 26 | 1 BEDROOM | 10B | 2601 | 10B | 95% | N/A | N/A | 95% | 95% | 90% | 95% | 97.5% | N/A | 85% | N/A | N/A | N/A | N/A | N/A | 85% | N/A | N/A | 89.17% | 0% | 100%
198 | 26 | 1 BEDROOM | 14A | 2602 | 14A | 95% | N/A | N/A | 95% | 95% | 90% | 95% | 97.5% | N/A | 97.5% | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | N/A | 97.5% | 0% | 100%
199 | 26 | STD. GUEST | 2D | 2603 | 2A/2B/2C/2D | 95% | N/A | N/A | 95% | 95% | 90% | 95% | 97.5% | N/A | N/A | n/A | 85% | 85% | N/A | N/A | N/A | N/A | N/A | 89.17% | N/A | 100%
200 | 26 | STD. GUEST | 3A | 2604 | 3A/3B/3D/3E/3G | 95% | N/A | N/A | 95% | 90% | 90% | 95% | 97.5% | N/A | 97.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.5% | 95.5% | 100%
201 | 26 | DELUX SUITE | 11D | 2605 | 11A/11B/11C/11D | 95% | N/A | N/A | 95% | 70% | 0% | 90% | 97.5% | N/A | N/A | 85% | N/A | N/A | 85% | N/A | N/A | N/A | N/A | 89.17% | N/A | 100%
202 | 26 | STD. GUEST | 2C | 2606 | 2A/2B/2C/2D | 95% | N/A | N/A | 95% | 90% | 90% | 95% | 97.5% | 85% | N/A | N/A | 97.5% | 85% | N/A | N/A | N/A | N/A | N/A | 91.25% | N/A | 100%
203 | 26 | STD. GUEST | 3A | 2607 | 3A/3B/3D/3E/3G | 95% | N/A | N/A | 95% | 90% | 90% | 95% | 50% | N/A | 97.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 73.75% | 95.5% | 100%
204 | 26 | STD. GUEST | 1A | 2609 | 1A | 95% | N/A | N/A | 95% | 90% | 90% | 95% | 97.5% | N/A | N/A | N/A | 85% | 85% | N/A | N/A | N/A | N/A | N/A | 89.17% | N/A | 100%
205 | 26 | STD. GUEST | 2F | 2610 | 2E/2F/2G/2H | 95% | N/A | N/A | 95% | 90% | 90% | 95% | 97.5% | 85% | N/A | N/A | 97.5% | 85% | N/A | N/A | N/A | N/A | N/A | 91.25% | N/A | 100%
206 | 26 | STD. GUEST | 3C | 2611 | 3C/3F | 95% | N/A | N/A | 95% | 90% | 90% | 95% | 97.5% | N/A | 97.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.5% | 0% | 100%
207 | 26 | STD. GUEST | 3F | 2612 | 3C/3F | 95% | N/A | N/A | 95% | 90% | 90% | 95% | 97.5% | N/A | 97.5% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.5% | 95.5% | 100%
208 | 26 | STD. GUEST | 2G | 2613 | 2E/2F/2G/2H | 95% | N/A | N/A | 95% | 90% | 90% | 95% | 97.5% | 85% | N/A | N/A | 97.5% | 85% | N/A | N/A | N/A | N/A | N/A | 91.25% | N/A | 100%
209 | 26 | STD. GUEST | 2E | 2614 | 2E/2F/2G/2H | 95% | N/A | N/A | 95% | 90% | 90% | 95% | 97.5% | N/A | N/A | n/A | 85% | 85% | N/A | N/A | N/A | N/A | N/A | 89.17% | N/A | 100%
210 | 26 | JUNIOR SUITE | 5A | 2615 | 5A | 95% | N/A | N/A | 95% | 90% | 90% | 95% | 97.5% | N/A | 85% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 91.25% | N/A | 100%
211 | 26 | ROYAL | 18A |  | PROV.SUM | 0% | N/A | N/A | 0% | N/A | N/A | N/A | 97.5% | N/A | N/A | n/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 97.5% | N/A | 100%
212 | 27 | 1 BEDROOM | 10B | 2701 | 10B | 95% | N/A | N/A | 95% | 90% | 90% | 95% | 85% | N/A | 85% | N/A | N/A | N/A | N/A | N/A | 85% | N/A | N/A | 85% | 0% | 100%
213 | 27 | 1 BEDROOM | 14A | 2702 | 14A | 95% | N/A | N/A | 95% | 90% | 90% | 95% | 97.5% | N/A | 0% | N/A | N/A | N/A | N/A | N/A | 0% | N/A | N/A | 32.5% | 0% | 100%
214 | 27 | STD. GUEST | 2D | 2703 | 2A/2B/2C/2D | 95% | N/A | N/A | 95% | 90% | 90% | 95% | 85% | N/A | N/A | n/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | 28.33% | N/A | 100%
215 | 27 | STD. GUEST | 3A | 2704 | 3A/3B/3D/3E/3G | 95% | N/A | N/A | 95% | 90% | 90% | 95% | 97.5% | N/A | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 48.75% | 0% | 100%
216 | 27 | DELUX SUITE | 11B | 2705 | 11A/11B/11C/11D | 80% | N/A | N/A | 80% | 50% | N/A | 85% | 85% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 85% | N/A | 100%
217 | 27 | STD. GUEST | 2C | 2706 | 2A/2B/2C/2D | 95% | N/A | N/A | 95% | 90% | 0% | 85% | 97.5% | 0% | N/A | n/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | 24.38% | N/A | 100%
218 | 27 | STD. GUEST | 3A | 2707 | 3A/3B/3D/3E/3G | 95% | N/A | N/A | 95% | 90% | 90% | 95% | 85% | N/A | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 42.5% | 0% | 100%
219 | 27 | DELUX SUITE | 11D | 2708 | 11A/11B/11C/11D | 95% | N/A | N/A | 95% | 70% | 0% | 90% | 0% | N/A | N/A | 0% | N/A | N/A | 0% | N/A | N/A | N/A | N/A | 0% | N/A | 100%
220 | 27 | CORNER. GUEST | 16A | 2709 | 16A | 95% | N/A | N/A | 95% | 90% | 0% | 0% | 85% | N/A | N/A | N/A | N/A | 0% | N/A | N/A | N/A | N/A | N/A | 42.5% | 0% | 100%
221 | 27 | STD. GUEST | 1A | 2710 | 1A | 95% | N/A | N/A | 95% | 90% | 90% | 95% | 85% | N/A | N/A | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | 28.33% | N/A | 100%
222 | 27 | STD. GUEST | 2F | 2711 | 2E/2F/2G/2H | 95% | N/A | N/A | 95% | 90% | 90% | 95% | 97.5% | 0% | N/A | n/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | 24.38% | N/A | 100%
223 | 27 | STD. GUEST | 3C | 2712 | 3C/3F | 95% | N/A | N/A | 95% | 90% | 90% | 95% | 97.5% | N/A | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 48.75% | 0% | 100%
224 | 27 | STD. GUEST | 3F | 2713 | 3C/3F | 95% | N/A | N/A | 95% | 90% | 90% | 95% | 85% | N/A | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 42.5% | 0% | 100%
225 | 27 | STD. GUEST | 2G | 2714 | 2E/2F/2G/2H | 95% | N/A | N/A | 95% | 90% | 90% | 95% | 85% | 0% | N/A | n/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | 21.25% | N/A | 100%
226 | 27 | STD. GUEST | 2E | 2715 | 2E/2F/2G/2H | 95% | N/A | N/A | 95% | 90% | 90% | 95% | 97.5% | N/A | N/A | n/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | 32.5% | N/A | 100%
227 | 27 | JUNIOR SUITE | 5A | 2716 | 5A | 95% | N/A | N/A | 95% | 90% | 90% | 95% | 97.5% | N/A | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 48.75% | N/A | 100%
Room Type | No of rooms | Wardrobe | MiniBar | Timber Screen | DB | Door | WC frame
1A | 8 | 96.5% | 90% | 91.25% | 84.62% | 87.99% | 100%
1B | 4 | 98% | 95% | 98% | 98% | 97.77% | 100%
1C | 2 | 98% | 0% | 0% | 91.5% | 97.83% | 100%
2A | 11 | 98% | 91.36% | 98% | 98% | 97.51% | 100%
2B | 18 | 97.33% | 90.56% | 95.86% | 86.78% | 97.31% | 100%
2C | 8 | 97.25% | 92.5% | 84.75% | 96% | 87.84% | 100%
2D | 7 | 95.86% | 87.86% | 95.64% | 80.86% | 86.43% | 100%
2E | 9 | 96.67% | 91.67% | 92% | 86.11% | 89.56% | 100%
2F | 8 | 96.5% | 91.25% | 91.25% | 84.62% | 87.77% | 100%
2G | 9 | 96.67% | 91.67% | 96.17% | 97% | 88.18% | 100%
2H | 1 | 98% | 85% | 98% | 98% | 97.83% | 100%
3A | 15 | 96.6% | 93.67% | 95.83% | 90.47% | 89.1% | 100%
3C | 9 | 96.67% | 93.89% | 96.17% | 86.11% | 92.24% | 100%
3D | 20 | 97.4% | 95% | 97.58% | 97.7% | 97.69% | 100%
3F | 9 | 96.67% | 93.89% | 96.17% | 86.11% | 91.54% | 100%
3G | 4 | 98% | 95% | 98% | 98% | 97.77% | 100%
4A | 4 | 98% | 95% | 98% | 98% | 97.83% | 100%
4B | 1 | 100% | 95% | 0% | 98% | 97.75% | 100%
5A | 9 | 96.67% | 93.89% | 87.78% | 86.11% | 89.81% | 100%
6A | 5 | 97.4% | 81% | 75.2% | 95.4% | 95% | 100%
7A | 5 | 81.6% | 16% | 0% | 85.2% | 164% | 96%
8A | 5 | 98% | 93% | 92.8% | 98% | 97.84% | 100%
9A | 2 | 98% | 95% | 91.5% | 98% | 97.83% | 100%
9B | 2 | 98% | 95% | 91.5% | 98% | 97.75% | 100%
10A | 5 | 98.2% | 0% | 98% | 98% | 97.83% | 100%
10B | 3 | 95% | 93.33% | 60% | 95% | 90.56% | 100%
11A | 1 | 95% | 50% | 0% | 85% | 97.5% | 100%
11B | 4 | 91.5% | 12.5% | 0% | 82% | 91.25% | 100%
11C | 11 | 93.82% | 69.55% | 70.45% | 88.82% | 88.1% | 100%
11D | 3 | 96% | 75% | 32.5% | 92.67% | 60.94% | 100%
12A | 5 | 98% | 95% | 60.6% | 95.4% | 97.37% | 100%
13A | 1 | 95% | 0% | 98% | 0% | 97.5% | 100%
14A | 4 | 95% | 93.75% | 60% | 71.25% | 81.25% | 100%
15A | 2 | 95% | 70% | 57.5% | 87.5% | 93.75% | 100%
16A | 3 | 96% | 93.33% | 52.67% | 65.33% | 79.25% | 100%
17A | 1 | 0% | 0% | 0% | 85% | 0% | 100%
18A | 1 | 0% | 0% | 0% | 0% | 97.5% | 100%
19A | 6 | 97.5% | 92.5% | 78.83% | 79.5% | 88.49% | 100%
|  | 91.26% | 73.35% | 69.21% | 85.32% | 91.67% | 99.89%
|  | 91.26% | 63.27% | 58.85% | 75.23% | 85.24% | 99.89%
|  | -0.002316% | 10.08% | 10.36% | 10.09% | 6.431% | 0.004737%