## IPA
| EMPLOYER |  | : | SKY PALACES REAL ESTATE DEVELOPMENT LLC
| EMPLOYER'S REPRESENTATIVE |  | : | OMNIYAT CONCEPT INVESTMENTS LLC
| ENGINEER |  | : | BREWER SMITH BREWER GULF ( BSBG )
| MAIN CONTRACTOR |  | : | KHANSAHEB CIVIL ENGINEERING - CONSTRUCTION DIVISION
| PROJECT |  | : | DORCHESTER HOTEL AND RESIDENCES
| KHANSAHEB JOB REF. NO. |  | : | 201A22002
| APPLICATION FOR PAYMENT NO. 12 | [6 empty] | FOR THE PERIOD ENDING: 31ST JANUARY 2022
|  | Description |  | Contract Value Amount (AED) | Previous (AED) | This (AED) | Cumulative (AED)
|  | Total Value of Workdone |  | 194951734.5 | 145289360.1978 | 25539126.2114 | 170828486.4092
|  |  |  | 0 | 0 | 0 | 0
|  | Total |  | 194951734.5 | 145289360.1978 | 25539126.2114 | 170828486.4092
SUMMARY
| (i) | Total Value of Workdone |  |  |  |  | 170828486.4092 |  |  | 56294044.2448 | -114534442.1644
|  | Sub Total 01 |  |  |  |  | 170828486.4092
0
| (ii) | Add Mobilisation Payment 01 & 02 |  |  |  |  | 12000000
|  | Sub Total 2 |  |  |  |  | 182828486.4092 |  |  | 68294044.2448 | -114534442.1644
| (iii) | Less Retention @ 10% on Provisional Sums & MEP (Except prelims & OHP ) |  |  |  |  | -7925267.9394 |  | KCE retention | 43258967.2135 | -4325896.7214
| (iv) | Less Amount Certified Previously |  |  |  |  | -146452936.5322 |  | KMEP retention | 35993712.18 | -3599371.218
[10 empty] | 79252679.3935 | -7925267.9394
| (v) | Amount due for Payment |  |  |  |  | 28450281.9376
182828486.4092
-3191697.0765
-397333
06.02.23
| Signature | [5 empty] | Date
Note: |  | Mobilisation payments (AED 12 million) to be recovered from subsequent payments as LOA clause 30. | [7 empty] | -448628.7596
178790827.5731
130255895.9809
-48534931.5922
86791925.909
-96036560.5002

## Summary
APPLICATION FOR PAYMENT - SUMMARY
| PROJECT | DORCHESTER HOTEL AND RESIDENCES | [5 empty] | FOR THE PERIOD ENDING: 31ST JANUARY 2022
| EMPLOYER | SKY PALACES REAL ESTATE DEVELOPMENT LLC
| EMPLOYER'S REPRESENTATIVE | OMNIYAT CONCEPT INVESTMENTS LLC
| ENGINEER | BREWER SMITH BREWER GULF ( BSBG )
| MAIN CONTRACTOR | KHANSAHEB CIVIL ENGINEERING - CONSTRUCTION DIVISION
| CONTRACT NO. | 201A22002
| Item | Contract Amount | Percentage Complete |  |  | Value Complete |  |  |  | 461823.5938
|  |  | Previous Certificate | This Month | To Date | Previous Valuation | This Month | To Date |  |  |  | Total Certified |  | Variance
| Main Contract Value | 194951734.5 | [6 empty] | 6053836.2575 | 1013274.3962
1 | Civil Works
1.1 | Contract Cost - Direct Work |  |  |  |  | 86532889.437 | 16064585.0573 | 102597474.4943 | 48430690.06 | 8106195.17 |  | 56536885.23 |  | -46060589.2643
1.2 | Cost Adjustments |  |  |  |  | -112186.129 | -18884.76 | -131070.889 | -1208 |  |  |  |  | 131070.889
1.3 | Main Contractor OH & Profit (12.5%) |  |  |  |  | 10090634.2655 | 1885833.7282 | 11976467.9937 | 6445740.61 |  |  | 6445740.61 |  | -5530727.3837
( Exc. KID Value )
| Sub Total 1 |  |  |  |  | 96511337.5734 | 17931534.0255 | 114442871.5989 |  |  |  | 62982625.84 | 0 | -51460245.7589
2 | Provisional Sums (excl MEP)
2.1 | Subcontract Cost
2.2 | Main Contractor OH & Profit (12.5%)
| Sub Total 2 |  |  |  |  | 0 | 0 | 0
3 | MEP Works
3.1 | Subcontract Cost (incl KMEP oh&p of 12.5%) |  |  |  |  | 44343656.9313 | 6915992.8962 | 51259649.8275 | 45564133.18 |  | Correction: Apply retention only on KMEP SC works | 30299794.5825 |  | -20959855.245
3.2 | Main Contractor OH & Profit on MEP (10%) |  |  |  |  | 4434365.6931 | 691599.2896 | 5125964.9828 | 4659968.1661 |  |  | 2797241.92 |  | -2328723.0628
| Sub Total 3 |  |  |  |  | 48778022.6244 | 7607592.1859 | 56385614.8103 |  |  |  | 33097036.5025 | 0 | -23288578.3078
|  | 194951734.5 |  |  |  | 145289360.1978 | 25539126.2114 | 170828486.4092 |  |  |  | 96079662.3425 |  | -74748824.0667
153857124.3218
85904689.09
8106195.17
96079662.3497
0.0072381

## Pre Cert
APPLICATION FOR PAYMENT NO. 12
PREVIOUSLY CERTIFIED AMOUNTS
Certificate No. | Description | Certified Amount (AED)
1 | Payment Certificate 01 | 6000000
2 | Payment Certificate 02 | 6000000
3 | Payment Certificate 03 | 2104452.12
4 | Payment Certificate 04 | 11118319.2
5 | Payment Certificate 05 | 11047382.21
6 | Payment Certificate 06 | 12807977.89
7 | Payment Certificate 07 | 19982204.03
8 | Payment Certificate 08 | 15491078.95
9 | Payment Certificate 09 | 19804921.87
10 | Payment Certificate 10 | 21126467.6392
11 | Payment Certificate 11 | 20970132.623
12 | Payment Certificate 12
13
14
15
16
17
18
19
20
21
22
| TOTAL AMOUNT | 146452936.5322

## Cover
201A22002 - DORCHESTER HOTEL AND RESIDENCES
CONTRACTOR
KHANSAHEB CIVIL ENGINEERING L.L.C.
APPLICATION FOR PAYMENT NO. 12
201A22002 - DORCHESTER HOTEL AND RESIDENCES
APPLICATION FOR PAYMENT NO. 12
| Section 1 | Certificate / Summary
| Section 2 | Cost breakdown Summary
| Section 3 | Labour Cost & Backup
| Section 4 | Material Cost & Backup
| Section 5 | Plant Cost & Backup
| Section 6 | Subcontractor Cost & Backup
| Section 7 | Prelim & General Cost & Backup
| Section 8 | Salary Cost & Backup
| Section 9 | Committed Orders
| Section 10 | MEP Payment Application
| Section 11 | Cost Adjustments
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 1
Certificate / Summary
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 2
Cost breakdown Summary
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 3
Labour Cost & Backup
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 4
Material Cost & Backup
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 5
Plant Cost & Backup
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 6
Subcontractor Cost & Backup
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 7
Prelim & General Cost & Backup
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 8
Salary Cost & Backup
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 9
Committed Orders
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 10
MEP Payment Application
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 11
Cost Adjustments

## SC Summary
SUBCONTRACTOR PAYMENT APPLICATION (CIVIL WORKS) - SUMMARY
PROJECT : DORCHESTER HOTEL AND RESIDENCES | [6 empty] | 2022-12-31
EMPLOYER : SKY PALACES REAL ESTATE DEVELOPMENT LLC
MAIN CONTRACTOR : KHANSAHEB CIVIL ENGINEERING - CONSTRUCTION DIVISION
CONTRACT NO : 201A22002
Sl No | Item | Scope of work | Work Approval Amount | Work Approval Reference | Value Complete |  |  | WD inc. Ad R. | Recovery | Advance P |  | Certified- Dec 22 |  | Variance in certifications
[5 empty] | Previous Valuation | This Month | To Date
| Subcontractors ( PS ) | [6 empty] | 0 |  | 0
1 | Watermaster Technical Services LLC | Swimming Pool & Water Feature works | 2128651 |  | 1650462.71 | 0 | 1650462.71 | 1650462.71 |  |  | 0 | 1523358.5042 |  | -127104.2058
2 | Arcadia Metal Industries | External Metal works | 3330440 |  | 3683043.92 | 1396651.54 | 5079695.46 | 5079695.46 | 499566 | 499566 | 0 | 2835026.0733 |  | -2244669.3867
3 | Dar Al Rokham LLC | Internal Stone works | 4111821 |  | 4021568.01 | 498861.77 | 4520429.78 | 4520429.78 |  | 0 | 0 | 3340377.3863 |  | -1180052.3937
4 | Al Shirawi Contracting Co LLC | Waterproofing works | 1391469 |  | 660688 | 159450 | 820138 | 820138 |  |  | 0 | 595446.9146 |  | -224691.0854
5 | Alshafar Interiors Co LLC | Joinery to Guest Rooms | 5919164.28 |  | 2818709.6423 | 956648.8222 | 3775358.4645 | 3499980.2645 | 612496.55 | 887874.75 | 275378.2 | 2673113.54 |  | -1102244.9245
6 | Isam Kabbani & Partners | Guniting & Waterproofing works | 1155933 |  | 440809.82 | 0 | 440809.82 | 440809.82 |  |  | 0 | 435538.7332 |  | -5271.0868
7 | Fiona Environs UAE | Soft Landscaping & Irrigation works | 3313028.6 |  | 1980098.46 | 313859.29 | 2293957.75 | 2293957.75 |  |  | 0 | 1890383.0379 |  | -403574.7121
8 | Al Reem Marble & Granite LLC | External Stoneworks | 4556481 |  | 3273837.72 | 992696.21 | 4266533.93 | 4100716.03 | 51137.25 | 216955.15 | 165817.9 | 3293717.13 |  | -972816.8
9 | Joyz Overseas Technical Services LLC | EIFS works | 1538156.94 |  | 1311674.861 | 185114.403 | 1496789.264 | 1492192.864 | 149219.29 | 153815.69 | 4596.4 | 1118701.0978 |  | -378088.1662
10 | Bond Interiors Design LLC | Fitout of Hotel Lobby, All Day Dining & Spa Works | 4325954.46 |  | 2447011.17 | 427483.35 | 2874494.52 | 2874494.52 |  |  | 0 | 2302353.34 |  | -572141.18
11 | Al Rawda General Maint. & Decoration Co LLC | Partition & Ceiling works | 1954843 |  | 2775812.47 | 686611.21 | 3462423.68 | 3462423.68 |  |  |  | 2712951.3745 |  | -749472.3055
12 | Joseph Advertisers LLC | Signage works | 999150 |  | 199830 | 0 | 199830 | 0 |  | 199830 | 199830 | 199830 |  | 0
13 | Joseph Decorative Glass | Internal Glazing works | 1262387 |  | 735873.824 | 0 | 735873.824 | 604245.534 | 120849.11 | 252477.4 | 131628.29 | 583334.8144 |  | -152539.0096
14 | Walltracts | Wall Coverings | 712173.7 |  | 664277.335 | 25056 | 689333.335 | 406956.395 | 0 | 282376.94 | 282376.94 | 664277.34 |  | -25055.995
15 | Goodrich Global Trading LLC | Carpets to Guest Rooms | 839675.05 |  | 617321.71 | 0 | 617321.71 | 617321.71 |  |  |  | 555878.32 |  | -61443.39
16 | Arabian Profile Company Ltd | GRC Works | 4155655 |  | 1286232.9 | 157790.1 | 1444023 | 1444023 |  |  |  | 1057914.9 |  | -386108.1
17 | Glass Line Aluminium LLC | Aluminium & Glazing Façade works | 10273402 |  | 6280090.49 | 639183.74 | 6919274.23 | 6919274.23 |  |  |  | 5026710.6015 |  | -1892563.6285
18 | EW COX Middle East LLC | BMU System | 628861 |  |  | 204605.8 | 204605.8 | 204605.8 |  |  |  | 0 |  | -204605.8
19 | Mohammed Tayyeb Khoory & Sons | Garbage & Linen Chutes | 287122 |  | 163261.6 | 0 | 163261.6 | 163261.6 |  |  |  | 140609.4 |  | -22652.2
20 | HTS Carpets Trading LLC | Carpets to lift lobbies & Corridors | 356512.42 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
21 | Khansaheb Interior DIvision ( KID ) | Restaurant Works |  |  | 5695629.184 | 959030.472 | 6654659.656 | 2663978.066 | 532795.61 | 4523477.2 |  | 5449938.7191 |  | -1204720.9369
| Subcontractors ( PS ) |  |  |  | 40706233.8263 | 7603042.7073 | 48309276.5335 | 43258967.2135 | 1966063.81 | 7016373.13 | 1059627.73 | 36399461.2267 | 0 | -11909815.3068
| Subcontractors (Domestic) | [8 empty] | 2492895.93
1 | Blue Sky LLC | Supply of MEP Maintenance team | 1071950 | P-006 | 736447.04 | 90101.48 | 826548.52 |  |  |  |  | 735847.04 |  | -90701.48
2 | Data Link Technical Services LLC | Wild Air Partitions | 241882.91 | C-006 | 401538 | 84031.89 | 485569.89 |  |  |  |  | 401126.93 |  | -84442.96
3 | Al Rawda General Maint. & Decoration Co LLC | Ceiling & Partition repairs, painting works | 26960 | P-001 | 45698.1 | 0 | 45698.1 |  |  |  |  | 45448 |  | -250.1
4 | Firestop Middle East | Firestopping works | 441760 | C-001, 002 R1 | 168158.8 | 59087.83 | 227246.63 |  |  |  |  | 167652.4 |  | -59594.23
5 | Creative House Scaffolding | Scaffolding | 1931942.08 | C-01 & 02 | 2565637.12 | 242890.36 | 2808527.48 |  |  |  |  | 2496617.12 |  | -311910.36
6 | Corecut Engineering LLC | Coring & Scanning | 383133 | C-015, 016 | 459191.45 | 83585 | 542776.45 |  |  |  |  | 454113.45 |  | -88663
7 | Inventure Façade Contracting LLC | Glass Balustrade works | 2703097 | C-011 | 1978898.88 | 219287.99 | 2198186.87 |  |  |  |  | 1968569.78 |  | -229617.09
8 | TWIC Insulation Materials Supply LLC | Epoxy Coating & Dust Sealer works | 778544.8 | C-015, 16 R1 | 312589.46 | 115985.53 | 428574.99 |  |  |  |  | 299037.05 |  | -129537.94
9 | Al Maraya Marble & Granite Factory LLC | Tile Installation | 514481.6 | C-017 | 257226.99 | 0 | 257226.99 |  |  |  |  | 250361.08 |  | -6865.91
10 | German Concrete Works & Building Contracting LLC | Screed & Insulation works | 796114.2 | C-018 R1 | 386401.77 | 274593.55 | 660995.32 |  |  |  |  | 378896.84 |  | -282098.48
11 | Greenwood General Trading LLC | Wooden Flooring | 353975.01 | C-005 | 176987.51 | 108610.31 | 285597.82 |  |  |  |  | 176987.51 |  | -108610.31
12 | Al Hayat Fiberglass Ind LLC | GRP Lining works | 313333.4 | C-027 | 118320 | 12852 | 131172 |  |  |  |  | 118320 |  | -12852
13 | Vulcan Industries LLC | Steel Doors | 685405 | C-032 | 200380.69 | 0 | 200380.69 |  |  |  |  | 194166.7524 |  | -6213.9376
14 | Polaris International Industries LLC | Timber Doors | 1008983.76 | C-029 | 695471.5128 | 102079.78 | 797551.2928 |  |  |  |  | 669790.8336 |  | -127760.4592
15 | Center Core Professional Technical Services LLC | Slab cutting & strengthening works | 88900 | C-033 | 88900 | 0 | 88900 |  |  |  |  | 88900 |  | 0
16 | Weserve Technical Services LLC | Miscellaneous Steel works | 1147041.3 | C-052 | 485457.3 | 145830.9 | 631288.2 |  |  |  |  | 485457.3 |  | -145830.9
17 | Venus Engineering LLC | RC column removal & strengthening works | 110965 | C-039 | 77965 | 166500 | 244465 |  |  |  |  | 77965 |  | -166500
18 | Global Composites Solutions LLC | GRP Cladding to Planter Wall | 225683 | C-053 | 45136.6 | 0 | 45136.6 |  |  |  |  | 45136.6 |  | 0
19 | Indiga Tech Trading LLC | Steel Doors | 154496.05 | C-047 | 42531.49 | 34574.432 | 77105.922 |  |  |  |  | 42531.49 |  | -34574.432
20 | Monrac LLC | Ceiling & Partition repairs, painting works | 918183.61 | PS-021 | 741677.8 | 138645.57 | 880323.37 |  |  |  |  | 710516.8605 |  | -169806.5095
21 | Hygenic Solutions LLC | MMA Flooring | 474794 | C-016 | 274196.05 | 0 | 274196.05 |  |  |  |  | 274195.05 |  | -1
22 | Technical Access Services (L.L.C.) | Scaffolding Works | 1580356.14 | C-065 | 1028070.06 | 367966.09 | 1396036.15 |  |  |  |  | 1024892.56 |  | -371143.59
23 | Progress Fabrication | Metal Cladding Works and Misc Metal Works | 1264100.14 | C-078 | 376278.25 | 56109.6 | 432387.85 |  |  |  |  | 376278.25 |  | -56109.6
24 | Ferco Shutters LLC | Fire Curtains | 33685 | P-027 | 3368.5 | 23579.5 | 26948 |  |  |  |  | 3368.5 |  | -23579.5
25 | Jeel Alfan Technical Services | Decorative Paint | 128266 | P-015 | 32066.5 | 0 | 32066.5 |  |  |  |  | 32066.5 |  | 0
26 | Technoserve Technical works LLC | Painting works | 73379.6 | P-012 | 17586.552 | 10458.584 | 28045.136 |  |  |  |  | 17586.552 |  | -10458.584
27 | Dormakaba Middle East | Movable Partition Works- AHK Balance | 366250 | PS-025 | 109875 | 205100 | 314975 | 205100 |  | 109875 |  | 109875 |  | -205100
28 | Khansaheb Joinery DIvision ( KJD ) | Joinery Works- AHK Balance | 2105729.87 | PS-023 | 677747.6459 | 268537.5441 | 946285.19 | 525139.22 |  | 421145.97 |  | 677747.642 |  | -268537.548
29 | Al Burhani General Trading LLC | Wooden Flooring & Carpet works- AHK | 133457 | PS-032 | 53002.5 | 74946.7 | 127949.2 | 74946.7 |  | 53002.5 |  | 53002.5 |  | -74946.7
30 | Rattan House Factory for Furniture and Decoration | Res Lobbies, Joinery works- AHK Balance | 279759 | PS-044 | 125018.56 | 28578.84 | 153597.4 | 153597.4 |  |  |  | 125018.56 |  | -28578.84
31 | International Foundation Group LLC | Waterproofing Concrete works | 450000 | C-061 R4 | 450000 | 0 | 450000 |  |  |  |  | 450000 |  | 0
32 | X-Calibur Emirates LLC | Stair nosing works | 221889 | C-064 | 173913 | 0 | 173913 |  |  |  |  | 173913 |  | 0
33 | Master Rubber Manufacturing | Wall & Corner Guard works | 169068.5 | C-062 | 50720.55 | 0 | 50720.55 |  |  |  |  | 50720.55 |  | 0
34 | DNK Engineering Equipment Trading LLC | Rolling Shutter works | 75530 | C-026 | 37765 | 23052 | 60817 |  |  |  |  | 37765 |  | -23052
35 | Vijayraj Contracting Co LLC | Plastering works | 206250 | C-019 | 159087.05 | 22663.1 | 181750.15 |  |  |  |  | 159087.05 |  | -22663.1
36 | Doormax Building Material Trading LLC | Glass Door works | 128000 | C-090 | 32000 | 57600 | 89600 |  |  |  |  | 32000
37 | KTC International Cont LLC | RTA works | 1043942 | C-091 | 208788.4 | 0 | 208788.4 |  |  |  |  | 208788.4
38 | Urban Science Building Contracting LLC | Joinery- Cupboards | 533125 | C-097 | 106625 | 0 | 106625 |  |  |  |  | 106625
39 | Berkeley | Final Cleaning | 993456 | C-067 |  | 16070 | 16070
40 | Elite Skills Technical Services LLC | Steel Door Repainting Works | 75430 | C-087 |  | 55860 | 55860
| Subcontractors (Domestic) |  |  |  | 13900724.1307 | 3089178.5801 | 16989902.7108 |  |  |  |  | 13720372.1505 |  | -3140000.5603
| Subcontractors (Domestic & PS ) |  |  |  | 54606957.957 | 10692221.2873 | 65299179.2443 |  |  |  |  | 50119833.3772 |  | -15049815.8671
Subcontractors ( Labour Only )
1 | Al Qannati Electromechanical LLC | Labour Supply ( Block Works ) |  |  | 830285 | 142435 | 972720 |  |  |  |  | 830285 |  | -142435
2 | Focus Power Security Services LLC | Supply of Site Security Service | 252000 | P-004 | 182000 | 25516.12 | 207516.12 |  |  |  |  | 182000 |  | -25516.12
3 | Service plus Technical Services LLC | Cleaning Service | 162400 | P-005 | 113387.96 | 16800 | 130187.96 |  |  |  |  | 113387.96 |  | -16800
| Subcontractors (Labour Only) |  |  |  | 1125672.96 | 184751.12 | 1310424.08 |  |  |  |  | 1125672.96 |  | -184751.12
[7 empty] | 66609603.3243 |  |  |  |  | 51245506.3372

## Staff Cost
FOR THE PERIOD ENDING: 31ST JANUARY 2022
SALARY COST & BACKUPS
Certificate No. | Description | Applied Amount (AED)
1 | 2022-03-01 | 16639.13 | 16639.13 | 0
2 | 2022-04-01 | 438092.619 | 438092.619 | 0
3 | 2022-05-01 | 772560.2273 | 772560.2273 | 0
4 | 2022-06-01 | 991945.4545 | 981763.6364 | -10181.8182
5 | July-22 | 1042220 | 1030430.5263 | -11789.4737
6 | August-22 | 1160798.7391 | 1137101.7391 | -23697
7 | September-22 | 1257377 | 1228858.1818 | -28518.8182
8 | October-22 | 1266237 | 1236938.0952 | -29298.9048
9 | November-22 | 1303682.27
10 | December-22 | 1299435.18
11 | January-23 | 1372949.59
12
13
14
15
16
17
18
19
| TOTAL AMOUNT | 10921937.21 | 6842384.1552 | -103486.0148

## Cost Adust't
FOR THE PERIOD ENDING: 31ST JANUARY 2022
Cost Adjustments
Certificate No. | Description | Applied Amount (AED)
1 | Petty Cash Gifts to Arjun | -1208
2 | TXM Manpower cost adjustment from material transaction- August 22 | -9071.54
3 | TXM Manpower cost adjustment from material transaction- September 22 | -9384.76
4 | TXM Manpower cost adjustment from material transaction- October 22 | -9051.18
5 | TXM Manpower cost adjustment from material transaction- November 22 | -9951.73
6 | TXM Manpower cost adjustment from material transaction- November 22 | -1583.52
7 | TXM Manpower cost adjustment from material transaction- December 22 | -19197
8 | TXM Manpower cost adjustment from material transaction- January 23 | -18884.76
8 | IT costs adjustment from Overhead transaction for June 22 | -10220
9 | IT costs adjustment from Overhead transaction July 22 | -11760
10 | IT costs adjustment from Overhead transaction August 22 | -12180
11 | IT costs adjustment from Overhead transaction September 22 | -14000
12 | Visa Cost of labours | -2797.41
13 | Visa Cost of labours | -1259.8
14 | Included VAT adjustment | -521.189
15
16
17
18
19
20
| TOTAL AMOUNT | -131070.889

## Com or's
APPLICATION FOR PAYMENT NO. 12
COMMITTED ORDERS
Certificate No. | Description | Total Amount (AED ) | Applied Amount (AED)
1 | Kone (LPO HM-201A22002/0002) - CTU use Lifts (2 Nos)- Jan. 23 | 160000 | 16000
2 | IT infra-strucure set up to Offices | 10000 | 10000
3 | Kone (LPO HM-201A22002/0048)- CTU use Lifts no 10 & 21 (2 Nos)- Jan 23 | 128000 | 16000
4 | Al Ihsan Building Materials Trading (LPO HM-201A22002/0056)- Balcony Tiles | 154032 | 30240
5 | Schirmer Safety Consultants (LPO HM-201A22002/0065)- Façade Inspection Services | 11500 | 5750
6 | Dosteen Doors & Shutters LLC (LPO HM-201A22002/0069)- Scissor Lift | 72900 | 72900
7 | High Glass Decor & Curtain Works LLC (LPO HM-201A22002/0080)- Turkish Acrylic carpet | 19435 | 19435
8 | Kone (LPO HM-201A22002/0086) - CTU Lifts (1 Nos)- for Oct 22 | 64000 | 16000
9 | Indigatech (LPO HM-201A22002/0095)- Fire rated Windows | 91817 | 64271.9
10 | New Era Construction (LPO HM-201A22002/00113)- Cobiax Permanent Formwork | 67371.21 | 51376.14
11 | Dosteen Doors & Shutters LLC (LPO HM-201A22002/0117)- Scissor Lift | 72900 | 72900
12 | Spider Access (LPO HM-201A22002/0130)- Column rectification & paint Mock up | 15300 | 0
13 | Carpet Land LLC (LPO HM-201A22002/0151) - Carpet | 13790 | 0
14 | Dutco LLC (LPO HM-201A22002/0155) - Modular Seal | 7600 | 0
15 | Master Builders Solutions LLC (LPO HM-201A22002/0159) - Emaco | 8400 | 0
16 | Jabel Ali Tra. LLC (LPO HM-201A22002/0161 ) -Dune Sand | 11110 | 2110.9
17 | Al Najar LLC (LPO HM-201A22002/0162 ) - DC Furniture | 4900 | 0
18 | Osler Access LLC (LPO HM-201A22002/0166 ) - Cradle Works | 12760 | 0
19 | Al Majid LLC (LPO HM-201A22002/0167 ) - GRP Tank | 6500 | 6500
20 | Inter Metal LLC (LPO HM-201A22002/0168 ) - DC Furniture | 5350 | 0
21 | Smart Office LLC (LPO HM-201A22002/169 ) - DC Furnitire | 9742 | 0
22 | Master Builders Solutions LLC (LPO HM-201A22002/0170) - Mater top | 18000 | 0
23 | Consent (LPO HM-201A22002/0172) - Tile & Coping | 166700 | 77893.56
24 | Momentum (LPO HM-201A22002/0179)- Ironmongery | 62299.3 | 32454.8 | Part cost booked.
25 | Indigatech (LPO HM-201A22002/0132)- Window Glass | 42920 | 30044
26 | Laidlaw (LPO HM-201A22002/0176)- Ironmongery | 240812.4 | 16566.5
27 | Kone (LPO HM-201A22002/0138) - CTU Lifts (2 Nos)- for Jan 23 | 96000 | 16000
28 | Fluid Codes Testing- (LPO HM-201A22002/0149) | 28207 | 0
29 | AST Digital Print Centre (LPO HM-201A22002/0037)- Printer charges | 15000 | 3438.16 | Registered Invoice
30 | Golden Ready Mix LLC (LPO HM-201A22002/0023 R1)- Concrete supply | 587200 | 78601 | Registered Invoice
31 | High Class Decor & Curtains Works LLC ( HM-201A22002/0080 ) | 19435 | 9717.5 | Registered Invoice
32 | AHK Works- Alternatives SC's | 528371.34 | 83360
33 | Ostermeier- Supply of manhole covers ( HM-201A22002/0277) | 420090
34 | Hilti RE 500V4 ( HM-201A22002/0183) | 18900 | 0
35 | Mobility General- Ironmongery ( HM-201A22002/0185) | 150516 | 11129
36 | Osler- Cradle ( HM-201A22002/0188) | 137000 | 0
37 | Momentum- Ironmongery ( HM-201A22002/0192) | 12202 | 11952
38 | Master Emaco ( HM-201A22002/0195) | 9000 | 0
39 | Door Controls Glass Trading( HM-201A22002/0206) | 57018
40 | Osler- Cradle Maintenance ( HM-201A22002/0207) | 14928.57 | 11428.57
41 | Amalgam- Traffic Signs ( HM-201A22002/0210) | 3003 | 0
42 | Al Areej AC- Temp AC's ( HM-201A22002/0216) | 26500 | 0
43 | Mobility General- Ironmongery ( HM-201A22002/0222) | 13640 | 13640
44 | Schirmer- Façade Testing( HM-201A22002/0224) | 5000 | 0
45 | Neotech Engineering ( HM-201A22002/0228) | 8518 | 0
46 | Neotech Engineering ( HM-201A22002/0229) | 2770 | 0
47 | Hilti RE 500V4 ( HM-201A22002/0231) | 31500 | 12600
48 | Styro polystyrene ( HM-201A22002/0234) | 6875 | 3079.99
49 | Arabuild Tiles ( HM-201A22002/0237) | 480000 | 358694.4
50 | Smart Office Furnitures ( HM-201A22002/0240) | 1439 | 0
51 | Doormax Ironmongery (HM-201A22002/0252) | 223860.28 | 83528.28
52 | Betec CAD Louvers (HM-201A22002/0267) | 90586.4 | 90586.4
53 | Mobility General Trading (HM-201A22002/0273) | 17100 | 17100
54 | Doormax Ironmongery (HM-201A22002/0280) | 13148 | 13148
55 | Styro Polystyrene (HM-201A22002/0281) | 46000 | 6125.13
56 | Carpets BSH Trading (HM-201A22002/0116) | 98548.1 | 78838.48
57 | Wow Factor- Barrisol (HM-201A22002/0118) | 40786 | 36707.4
58 | Consent (LPO HM-201A22002/0213) - Benches | 237500 | 57137.5
59 | Consent (LPO HM-201A22002/0242) - Kerbstone | 138000 | 103500
60 | Jebel Ali Transport(LPO HM-201A22002/0244) - Roadbase | 126000 | 68502
61 | Fireproof(LPO HM-201A22002/0289) - Palgan | 19000 | 19000
62 | Laidlaw (LPO HM-201A22002/0286)- Ironmongery | 13984.5 | 8316.8
63 | Master Builders ( HM-201A22002/0316) | 63900 | 36780
| TOTAL AMOUNT | 5279665.1 | 1773353.41

## K Summary
COINS - FINANCE
Contract Cost Breakdown 201A22002 Dorchester Hotel & Residences
Period January 2023
|  |  | Previous Cum | Current Month
Ledger | Current Period | Total to Date |  |  | Certified
Labour | 1800634.84 | 11069377.96 | 9268743.12 | -1800634.84 | 7628037.26 | -3441340.7
Payroll | 1615883.72 | 9757528.88 | 8141645.16 | -1615883.72 | 6696259.3
Manual Journal |  |  |  | 0
Purchase Orders |  |  |  | 0
Direct Invoices |  |  |  | 0
Petty Cash Charges |  | 1425 | 1425 | 0 | 1425
Subcontractor Costs | 184751.12 | 1310424.08 | 1125672.96 | -184751.12 | 930352.96
Material | 1515105.04 | 9058810.56 | 7543705.52 | -1515105.04 | 6311690.05 | -2747120.51
Purchase Orders | 1143781.77 | 5197149.16 | 4053367.39 | -1143781.77
Stock Issues | 359999.41 | 3701554.77 | 3341555.36 | -359999.41
Manual Journals |  | 4371 | 4371 | 0
Petty Cash Charges | 326.36 | 11646.03 | 11319.67 | -326.36
Plant Charges | 10997.5 | 143710 | 132712.5 | -10997.5
Direct Invoices |  | 379.6 | 379.6 | 0
Plant | 419648.87 | 3175881.56 | 2756232.69 | -419648.87 | 2300533.63 | -875347.93
Plant Charges | 400500.97 | 2996488.49 | 2595987.52 | -400500.97
Manual Journals | 18531.4 | 170875.07 | 152343.67 | -18531.4
Petty Cash Charges |  |  |  | 0
Direct Invoices | 616.5 | 8518 | 7901.5 | -616.5
Subcontractor | 10693721.2873 | 65308299.2443 | 54614577.957 | -10693721.2873 | 41412331.2124 | -23895968.0319
Subcontract Costs | 10692221.2873 | 65299179.2443 | 54606957.957 | -10692221.2873 | 41405911.2124 | -23893268.0319
CVR Items |  | 0 | 0 | 0
Purchase Orders | 1500 | 9120 | 7620 | -1500 | 6420 | -2700
Direct Invoices | 0 | 0 | 0 | 0
Manual Journals |  |  |  | 0
Overhead | 165516.26 | 1288084.03 | 1122567.77 | -165516.26 | 973013.62 | -315070.41
CVR Items |  | 0 | 0 | 0
Purchase Orders | 105327.79 | 666474.84 | 561147.05 | -105327.79
Direct Invoices | 8801.48 | 116965.15 | 108163.67 | -8801.48
Petty Cash Charges | 16291.44 | 117989.13 | 101697.69 | -16291.44
Manual Journals | 5957.08 | 164368.53 | 158411.45 | -5957.08
Plant Charges | 1085 | 9912 | 8827 | -1085
Stock Issues | 28053.47 | 212374.38 | 184320.91 | -28053.47
Salaries | 1372949.59 | 10923667.73 | 9550718.14 | -1372949.59 | 8251283.44 | -2672384.29
Payroll Charges | 1372949.59 | 10921937.21 | 9548987.62 | -1372949.59 | 8249552.44
Manual Journals |  | 1730.52 | 1730.52 | 0 | 1731
Direct Invoices |  |  |  | 0
Commited Orders | 97009.169 | 1773353.41 | 1676344.24 | -97009.17
Commited Orders | 97009.169 | 1773353.41 | 1676344.24 | -97009.17 | 2225356.19 | 452002.78
0
0
Total | 16064585.0563 | 102597474.4943 | 86532889.437 | -16064585.0573 | 69102245.4024 | -33495229.0919
|  |  |  | -0.001 |  | -4186903.6365
-37682132.7284

## Labour
COINS - FINANCE
Labour Cost 201A22002 Dorchester Hotel & Residences
Period January 2023
Payroll
Cost Head | Description |  | Normal Hours | OT Hours | EOT Hours | Current | TTD
10100 | Unskilled labour costs - internal |  | 33031.5 | 3791.5 | 4634.5 | 391520.22 | 2476927.32
10200 | Skilled labour costs - internal |  | 27580 | 3293.5 | 4199.5 | 368030.58 | 2089969.27
10300 | Operators costs - internal |  | 6236 | 645.5 | 1255.5 | 103445.37 | 643618.21
10400 | Tradesmen costs - internal |  | 54246 | 6407.5 | 8995 | 718785.41 | 4322113.92
10500 | Charge hand labour costs - internal |  | 2304 | 286 | 457.5 | 34102.14 | 224900.16
Total |  |  | 123397.5 | 14424 | 19542 | 1615883.72 | 9757528.88
Manual Journals
Cost Head | Description |  |  | Type | Int Ref | Current | TTD
Total
Purchase Orders
Commodity | Description |  |  | Invoiced | Accrual / Rev | Current | TTD
Total | [5 empty] | 0
Direct Invoices
Cost Head | Description |  |  | Type | Int Ref | Current | TTD
Total
Petty Cash Charges
Cost Head | Description |  |  | Type | Int Ref | Current | TTD
10200 | Skilled labour costs - internal | [5 empty] | 1425
Total | [6 empty] | 1425
Subcontract Costs
Cost Head | Description |  |  | Int Ref | Ext Ref | Current | TTD
11400 | Tradesmen costs - external |  |  |  |  | 327433.22 | 1876886.59
| ALQA002 | Al Qannati Electromechanical and Plumbing Co LLC |  |  |  | 176900 | 898591
898591
| BLUE008 | Blue Sky Middle East Contracting (LLC) |  |  |  | 111717.1 | 681891.51
681891.51
| FOCU003 | Focus Power Security Services (LLC) |  |  |  | 22016.12 | 183016.12
183016.12
| SERV004 | Service Plus Technical Services LLC |  |  |  | 16800 | 113387.96
113387.96
| ALQA002 | Al Qannati Electromechanical and Plumbing Co LLC |  |  |  | 327433.22 | 1876886.59
1876886.59
Total | [5 empty] | 327433.22 | 1876886.59

## Material
COINS - FINANCE
Material Cost 201A22002 Dorchester Hotel & Residences
Period January 2023
Purchase Orders
Commodity | Description |  | Invoiced | Accrual / Rev | Current | TTD
21110A01 | Reinforcement - Bars Mesh Bending Sched |  | 32919.3 | 29563.48 | 62482.78 | 205805
| CICO001 | Cicon Building Materials | 32919.3 | 29563.48 | 62482.78 | 205805
21110A02 | Reinforcing Sundries |  | 2250 | -1530 | 720 | 5760
| ALAB003 | Al Abbasi Fasteners and Hardware | 2250 | -2250 | 0 | 4750
| MODE002 | Modern Building Materials Trad |  | 720 | 720 | 1010
21111A01 | Aggregates |  |  | 0 | 0 | 8999.1
| JABE002 | Jabel Ali General Transport En |  | 0 | 0 | 8999.1
21112A01 | Timber/Plywood/Nails |  |  | 7150 | 7150 | 63500
| ABUA004 | Abu Al Hassan Building Material Co. (ABCO) LLC - Foreign Direct Investment |  |  | 0 | 25500
| ACME001 | Acme Building Materials Trading LLC |  | 7150 | 7150 | 33000
| SRRB001 | SRR Building Material Trading LLC |  |  | 0 | 5000
22317A01 | Vehicle Plant and Spares |  | 56000 | 20000 | 76000 | 410933.64
| KONE001 | Kone Middle East LLC | 56000 | 20000 | 76000 | 410933.64
22324A01 | Metalwork/Steelwork/Misc Metalwork Items |  |  | 29175 | 29175 | 29175
| OSTE001 | Ostermeier FZE |  | 29175 | 29175 | 29175
22711A01 | Consumable Tooling |  | 13323.3 | 26897.77 | 40221.07 | 80556.69
| ALAB003 | Al Abbasi Fasteners and Hardware | 440 | -122 | 318 | 4233
| DUTI001 | Dutest Industrial Est |  |  | 0 | 600
| GULF019 | Gulf Metal Wires Industry LLC | 120 |  | 120 | 820
| HILT001 | Hilti Emirates LLC | 12763.3 | 27019.77 | 39783.07 | 68223.69
| NASE001 | Naser Al Sayer and Co LLC |  |  | 0 | 6680
23011A01 | Blockwork/Masonry/Mortar |  | 10128 | -2768 | 7360 | 75164.4
| ARKA003 | Arkan Building Materials Co Arkan PJSC - Dubai Bramch | 5520 | 1840 | 7360 | 41630
| MAST005 | Master Builders Solutions Construction Chemicals LLC |  |  | 0 | 8400
| UNIM005 | Uni Mix Block Industry (LLC) | 4608 | -4608 | 0 | 25134.4
23011A02 | Blockwork Sundry Material |  | 33264 | -28080 | 5184 | 160963.4
| ALAB003 | Al Abbasi Fasteners and Hardware |  |  | 0 | 1600
| CORE004 | Core Metallic Ind LLC |  |  | 0 | 23379
| HILT001 | Hilti Emirates LLC | 25200 | -25200 | 0 | 69300
| MODE002 | Modern Building Materials Trad |  |  | 0 | 720
| PALL001 | Palletco LLC |  |  | 0 | 26000
| UNIM005 | Uni Mix Block Industry (LLC) | 8064 | -2880 | 5184 | 39964.4
23011A03 | Concrete |  | 46950 | -8394 | 38556 | 213738.5
| GOLD026 | Golden Ready Mix LLC | 46950 | -8394 | 38556 | 213738.5
23011A04 | Concrete Sundries |  | 56885.21 | 25316.82 | 82202.03 | 259482.04
| ALAB003 | Al Abbasi Fasteners and Hardware |  |  | 0 | 8600
| KING003 | Kingspan Insulation (LLC) |  | 0 | 0 | 12000
| MAPE001 | Mapei Construction Chemicals LLC |  |  | 0 | 460
| MAST005 | Master Builders Solutions Construction Chemicals LLC | 39796 | 13924 | 53720 | 206145
| STYR002 | Styro Insulation Materials Trading LLC | 17089.21 | 11392.82 | 28482.03 | 32277.04
23011A05 | Plaster Screed Rush Coat |  | 9600 | -4520 | 5080 | 41800
| CONM001 | Conmix Ltd | 9600 | -4520 | 5080 | 41800
23011A06 | Plaster Sundries |  |  | 0 | 0 | 4317
| CONM001 | Conmix Ltd |  |  | 0 | 1920
| CORE004 | Core Metallic Ind LLC |  | 0 | 0 | 2397
23011A07 | Precast Concrete |  | 43265 | 74641 | 117906 | 263420
| ALSE002 | Al Serkal and Assarain Concret | 43265 | 74641 | 117906 | 254470
| CONS001 | Consent LLC |  |  | 0 | 8950
23012A01 | Road Base |  | 24220 | 2496.2 | 26716.2 | 57498
| JABE002 | Jabel Ali General Transport En | 24220 | 2496.2 | 26716.2 | 57498
23012A04 | Kerb Stones |  | 21160 | 13340 | 34500 | 34500
| CONS001 | Consent LLC | 21160 | 13340 | 34500 | 34500
23016A01 | Tiling Material |  | 80628.86 | -57175.22 | 23453.64 | 445669.54
| ALIH002 | Al Ihsan Building Materials Trading |  | 0 | 0 | 123792
| ARAB017 | Arabuild LLC |  |  | 0 | 132285.6
| CONS001 | Consent LLC | 79708.86 | -59180.22 | 20528.64 | 185378.94
| MAPE001 | Mapei Construction Chemicals LLC | 920 | -920 | 0 | 1288
| MATE005 | Matex Construction Chemicals Manufacturing LLC |  | 2000 | 2000 | 2000
| SODA001 | Sodamco Sal Abu Dhabi |  | 925 | 925 | 925
23019A01 | Formwork/Falsework |  |  |  | 0 | 22306.58
| ALQU003 | Al Quebeisi SGB LLC |  |  | 0 | 111.51
| FISC002 | Fischer Fixing LLC |  |  | 0 | 2700
| NEXT004 | Next Era Construction Materials Trading One Person Company LLC |  |  | 0 | 15995.07
| TRAD004 | Tradex LLC |  |  | 0 | 3500
23019A02 | Formwork Sundries |  | 7690 | 38845 | 46535 | 46535
| ABUA004 | Abu Al Hassan Building Material Co. (ABCO) LLC - Foreign Direct Investment |  | 19125 | 19125 | 19125
| ACME001 | Acme Building Materials Trading LLC | 7690 | 16200 | 23890 | 23890
| ASCE001 | Ascend Access System Scaffoldi |  | 3520 | 3520 | 3520
23121A01 | Painting & Decorating Materials/Sealants |  |  | 0 | 0 | 10053
| DUTC004 | Dutco Tennant LLC |  |  | 0 | 7600
| QCON001 | Q Con General Trading LLC |  | 0 | 0 | 2453
23123A01 | Ironmongery |  | 4453 | 322899.2 | 327352.2 | 1223352.52
| ALAB003 | Al Abbasi Fasteners and Hardware |  | 3750 | 3750 | 5320
| DOOR001 | Doormax Building Material Trading (LLC) |  | 16100 | 16100 | 140332
| DOOR002 | Door Controls Glass Trading LL |  | 57018 | 57018 | 57018
| FINE001 | Fine Tools Trading LLC |  |  | 0 | 840
| LAID001 | Laidlaw Gulf LLC |  | 250484.2 | 250484.2 | 677199.54
| MOBI002 | Mobility General Trading LLC |  | 0 | 0 | 139387
| MOME001 | Momentum Fireguard LLC | 4453 | -4453 | 0 | 197055.98
| QUAL010 | Quality Metal Works Manufacturing LLC |  |  | 0 | 6200
23912A02 | Electrical Items |  |  |  | 0 | 16635
| ALBA003 | Al Bajaa Lighting Equipment Trading LLC |  |  | 0 | 6835
| FAIS001 | Faisal Ali Juma Trading LLC |  |  | 0 | 9800
24713A01 | Cleaning Materials |  |  | 0 | 0 | 600
| ALBA009 | Al Bariq Equipment LLC |  | 0 | 0 | 600
29901A02 | Other Consumables |  | 20651.26 | 30959.45 | 51610.71 | 227739.24
| ALAB003 | Al Abbasi Fasteners and Hardware | 20651.26 | 29416.55 | 50067.81 | 184867.34
| ALBA009 | Al Bariq Equipment LLC |  | 0 | 0 | 1700
| ALSH004 | Al Sham Star Trading LLC |  |  | 0 | 945
| ASCE001 | Ascend Access System Scaffoldi |  |  | 0 | 17582
| CHEM001 | Chemex Hygiene Concepts LLC |  |  | 0 | 4642.5
| CRES002 | Crescent Scaffolding Industrie |  |  | 0 | 6600
| FAIS001 | Faisal Ali Juma Trading LLC |  |  | 0 | 5903.5
| HEPW001 | Corys Piping Systems LLC |  |  | 0 | 2016
| NEXT004 | Next Era Construction Materials Trading One Person Company LLC |  | 1542.9 | 1542.9 | 1542.9
| SALE001 | Saleem Jacobson Trading |  |  | 0 | 1940
41540A01 | External Works through LPO's |  | 260125.24 | -98548.1 | 161577.14 | 1288645.51
| ALNA007 | Al Najah Furnishings LLC |  |  | 0 | 4900
| BSHT001 | BSH Trading (LLC) | 78838.74 | -98548.1 | -19709.36 | 78838.74
| CARP001 | Carpet Land LLC |  |  | 0 | 13790
| CULL001 | Culligan International Emirate |  |  | 0 | 218423.22
| DANA002 | Danat Alkhaleej for Safety Consultancy |  |  | 0 | 5550
| FLUI002 | Fluid Codes DMCC |  |  | 0 | 28207
| GULF019 | Gulf Metal Wires Industry LLC |  |  | 0 | 1225
| INDI003 | Indiga Tech Trading (LLC) |  | 0 | 0 | 40421.1
| INTE009 | Intermetal (LLC) Dubai Br |  | 0 | 0 | 7350
| KCEJ001 | KCE (LLC) - Joinery Division |  |  | 0 | 1248.54
| NATI010 | National Services for Carpet a |  |  | 0 | 2686.2
| OSLE001 | Osler Access Equipment LLC | 137000 |  | 137000 | 753260.09
| OSTE001 | Ostermeier FZE |  |  | 0 | 13357
| SANI001 | Sanipex LLC | 20401.74 |  | 20401.74 | 20401.74
| SCHI004 | Schirmer Safety Consultants | 5000 |  | 5000 | 10750
| SMAR015 | Smart Space Office Furniture Trading |  |  | 0 | 11112.39
| TXML001 | TXM Labour Supply LLC | 18884.76 |  | 18884.76 | 77124.49
Total |  |  | 723513.17 | 420268.6 | 1143781.77 | 5197149.16
Stock Issues
Cost Head | Description |  | Type | Int Ref | Current | TTD
21112 | Wood Products |  |  |  |  | 38201.65
| 11121609-A03989 | Plywood - Film Faced - 18Mm - Fsc - Popalr Core |  |  |  | 38201.65
21510 | Fuels |  |  |  | 340982.53 | 3447580.89
| 15101501-A18400 | Fuel - Petrol |  |  |  | 1234.12
| 15101501-A18401 | Fuel - Diesel | ISS |  | 340982.53 | 3446346.77
22210 | Heavy construction machinery and equipment |  |  |  | 16416 | 61200
| 22101701-A04048 | Floor Protection Sheet Polypro Corrugated 4Mm |  |  | 16416 | 61200
22711 | Hand tools |  |  |  |  | 113522
| 22711H02-010001 | Floor Cleaning Machine |  |  |  | 4440
| 27112702-A20393 | Angle Grinder |  |  |  | 27722
| 27112702-A20412 | Concrete Mixer |  |  |  | 2350
| 27112702-A20424 | Drill |  |  |  | 9510
| 27112702-A20504 | Stepdown Transformer |  |  |  | 34875
| 27112702-A20516 | Vacuum Cleaner |  |  |  | 11125
| 27112702-A20520 | Wall Chasing Machine |  |  |  | 23500
24325 | Project IT Infrastructure |  |  |  |  | 2796
| 24325V01-010002 | Access Point Aruba AP 515 - New |  |  |  | 2598
| 24325V01-010004 | Mounting Kit Aruba AP 515 - New |  |  |  | 198
| 24325V01-020001 | Firewall SonicWall TZ400 - Used |  |  |  | 0
| 24325V01-020002 | Access Point Aruba AP 515 - Used |  |  |  | 0
| 24325V01-020005 | Network Switch Cisco SG350 28 Port - Used |  |  |  | 0
| 24325V01-020007 | Wireless Router D-Link 4G - Used |  |  |  | 0
24618 | Personal safety and protection |  |  |  | 1869.02 | 14347.73
| 46181507-A04452 | Safety Vest 90 Gsm Florescent Green - Large (Rigger) |  |  |  | 102.93
| 46181507-A04459 | Safety Vest 90 Gsm M Green - Staff Vest - 2XL |  |  |  | 105.56
| 46181507-A04460 | Safety Vest 90 Gsm M Green - 2Xl |  |  |  | 387.51
| 46181507-A04461 | Safety Vest 90 Gsm M Green - Staff Vest - 3XL |  |  |  | 9
| 46181507-A04462 | Safety Vest 90 Gsm M Green - Large | ISS |  | 318.79 | 1236.68
| 46181507-A04463 | Safety Vest 90 Gsm M Green - Staff Vest - M |  |  |  | 226.47
| 46181507-A04464 | Safety Vest 90 Gsm M Green - Staff Vest - L |  |  |  | 316.66
| 46181507-A04465 | Safety Vest 90 Gsm M Green - Medium | ISS |  | 318.81 | 914.5
| 46181507-A04466 | Safety Vest 90 Gsm M Green - Staff Vest - XL |  |  |  | 364.27
| 46181507-A04467 | Safety Vest 90 Gsm M Green - Xl | ISS |  | 212.79 | 1006.81
| 46181507-A20681 | Traffic Marshall Safety Jacket Size- XL |  |  |  | 75
| 46181507-A20695 | Rigger Safety Jacket Size - XL |  |  |  | 37.5
| 46181507-A20696 | Rigger Safety Jacket Size - 2XL |  |  |  | 37.5
| 46181701-A04400 | Safety Helmet For Staff Mk7 | ISS |  | 70 | 3395
| 46181701-A04402 | Safety Helmet High Ev Yellow - 6 Point Textile Tapes System. Slip Ratche |  |  | 910 | 5577
| 46181701-A04404 | Safety Helmet High Ev Red - 6 Point Textile Tapes System. Slip Ratchet T |  |  | 12.63 | 469.34
| 46181701-A04405 | Safety Helmet High Ev White - 6 Point Textile Tapes System. Slip Ratchet |  |  | 26 | 26
| 46181701-A20074 | Safety Helmet High Ev Green - 6 Point Textile Tapes System. Slip Ratchet |  |  |  | 60
25213 | Window treatments |  |  |  |  | 13724.91
| 52131602-A18941 | Shade Net - 100% new HDPE with UV protection - 285 GSM - 3.66X100Mtr - |  |  |  | 13724.91
25310 | Clothing |  |  |  | 731.86 | 8336.17
| 53101602-A04981 | Shirt Cotton Full Sleeve White - 2Xl |  |  |  | 380.04
| 53101602-A04984 | Shirt Cotton Full Sleeve White - Large | ISS |  | 384 | 1200
| 53101602-A04985 | Shirt Cotton Full Sleeve White - Medium |  |  | 192 | 912
| 53101602-A04986 | Shirt Cotton Full Sleeve White - Small |  |  |  | 1132.71
| 53101602-A04987 | Shirt Cotton Full Sleeve White - Xl |  |  |  | 376.09
| 53101602-A04988 | Shirt Formal Half Sleeve White - 2Xl |  |  |  | 105.56
| 53101602-A04989 | Shirt Formal Half Sleeve White - 3Xl |  |  |  | 360
| 53101602-A04991 | Shirt Formal Half Sleeve White - Large |  |  |  | 298.42
| 53101602-A04992 | Shirt Formal Half Sleeve White - Medium |  |  |  | 106.7
| 53101602-A04993 | Shirt Formal Half Sleeve White - Small |  |  |  | 120.71
| 53101602-A04994 | Shirt Formal Half Sleeve White - Xl |  |  |  | 383.29
| 53103001-A05701 | T-Shirt 220 Gsm Half Sleeve White - 2Xl | ISS |  | 103.87 | 361.16
| 53103001-A05702 | T-Shirt 220 Gsm Half Sleeve White - 3Xl |  |  |  | 52
| 53103001-A05704 | T-Shirt 220 Gsm Half Sleeve White - Large |  |  |  | 208
| 53103001-A05705 | T-Shirt 220 Gsm Half Sleeve White - Medium |  |  |  | 1326
| 53103001-A05706 | T-Shirt 220 Gsm Half Sleeve White - Small |  |  |  | 312
| 53103001-A05707 | T-Shirt 220 Gsm Half Sleeve White - Xl | ISS |  | 51.99 | 701.49
60905 | Computers & Accessories |  |  |  |  | 1845.42
| 60905V01-010006 | Keyboard & Mouse Logitec Wireless Black - New |  |  |  | 125
| 60905V01-010013 | Cable HDMI 5m - New |  |  |  | 55
| 60905V01-010032 | Microsoft Display Adapter 1080p - New |  |  |  | 330
| 60905V01-010038 | Monitor HP E22 G4 FHD - New |  |  |  | 652.42
| 60905V01-010043 | Laptop Bag HP - New |  |  |  | 198
| 60905V01-010050 | USB A Wi-Fi adapter - New |  |  |  | 485
Total |  |  |  |  | 359999.41 | 3701554.77
Manual Journals
Cost Head | Description |  | Type | Int Ref | Current | TTD
29910 | Internal division - material costs |  |  |  |  | 4371
29951 | Materials cost accruals - CVR |  |  |  |  | 0
|  | CVR Item Cost Code Manual Accruals Material | JCV | 157356
Total | [5 empty] | 4371
Petty Cash Charges
Cost Head | Description |  | Type | Int Ref | Current | TTD
23116 | Hardware |  |  |  | 326.36 | 11646.03
|  | 27743-CHRIS McCANN-201A22002 | PCP | JAN/11832/16 | 179.56
|  | 27743-CHRIS McCANN-201A22002 | PCP | JAN/11836/21 | 146.8
Total |  |  |  |  | 326.36 | 11646.03
Plant Charges
Cost Head | Description |  | Type | Int Ref | Current | TTD
22711 | Hand tools |  |  |  |  | 2850
| 27112217-A19363 | LT 53/2-Block Cutter |  |  |  | 2850
24619 | Fire protection |  |  |  | 1935 | 3975
| PTLT150045 | PTLT150045 Building Dryer Machine |  |  |  | 150
| PTLT150092 | PTLT150092 Ventilation Fan 18" |  |  |  | 315
| PTLT150096 | PTLT150096 Ventilation Fan-20" |  |  | 387 | 387
| PTLT150097 | PTLT150097 Ventilation Fan 18" |  |  |  | 315
| PTLT150098 | PTLT150098 Ventilation Fan 18" |  |  | 387 | 387
| PTLT150108 | PTLT150108 Ventilation Fan 18" |  |  | 387 | 387
| PTLT150113 | PTLT150113 Ventilation Fan 18" |  |  | 387 | 702
| PTLT150115 | PTLT150115 Ventilation Fan-20" |  |  | 387 | 387
| PTLT150142 | PTLT150142 Ventilation Fan 18" |  |  |  | 315
| PTLT150143 | PTLT150143 Ventilation Fan 18" |  |  |  | 315
| PTLT150144 | PTLT150144 Ventilation Fan 18" |  |  |  | 315
29900 | EHD Materials |  |  |  | 9062.5 | 136885
| 99000101-A18468 | Pedestrian Barrier Steel Branded (2.5 x 1.2mtr) |  |  |  | 41000
| 99000101-A20672 | Expandable PVC Barrier - 2.5m x 0.960m |  |  | 1750 | 1750
| 99000201-A18478 | Metal Hordings (2.2 x 2 mtr) K standard |  |  |  | 5775
| 99000601-A18491 | TYPE 1 - 3 Cooler Stand |  |  |  | 8612.5
| 99000701-A18494 | Cable Management Stand |  |  | 7312.5 | 21937.5
| 99000701-A18496 | Cable Management Hooks-double hooks ( type 2) |  |  |  | 3375
| 99000701-A18497 | Cable Management Hooks three hooks ( type 3) |  |  |  | 1600
| 99000901-A18510 | Man Basket |  |  |  | 7575
| 99001001-A18505 | Concrete Bucket - 1m3 |  |  |  | 960
| 99001001-A18669 | 1.5 CBM (3T) Self Dumping Skip |  |  |  | 5500
| 99001101-A18509 | Tripod |  |  |  | 2800
| 99001201-A18840 | EHD Security Cabin |  |  |  | 2600
| 99001401-A18842 | EHD Gas Monitor |  |  |  | 5400
| 99001601-A19775 | Large Industrial Evaporative Outdoor Air Cooler |  |  |  | 28000
Total |  |  |  |  | 10997.5 | 143710
Direct Invoices
Cost Head | Description |  | Type | Int Ref | Current | TTD
21510 | Fuels |  |  |  |  | 379.6
| ALFU013 | Al Futtaim Transport and Renta |  |  |  | 379.6
Total | [5 empty] | 379.6
[5 empty] | 1515105.04 | 9058430.96

## Plant
COINS - FINANCE
Plant Cost 201A22002 Dorchester Hotel & Residences
Period January 2023
Plant Charges
Cost Head | Description |  | Type | Int Ref | Current | TTD
30010 | I-Earth moving machinery |  |  |  | 12904.65 | 81379.18
| 2210150902 | Backhoe Loader (3CX) With Operator-Working |  |  |  | 4147
| 2210152614 | Mini Excavator 3 Ton with Breaker-Working |  |  | 990 | 4950
| P000220111 | P000220111 Case Sr150 Skid Steer Loader |  |  |  | 560.77
| P000220115 | P000220115 Case Sr150 Skid Steer Loader |  |  |  | 93.46
| P000220119 | P000220119 Case Sr150 Skid Steer Loader |  |  |  | 2710.39
| P000220120 | P000220120 Case Sr200 Skid Steer Loader |  |  | 3800.02 | 31715.4
| P000220123 | P000220123 Case Sr150 Skid Steer Loader |  |  | 2430.01 | 14673.47
| P000230121 | P000230121 Avant Compact Loader -Dxb62067 |  |  | 2484.62 | 2484.62
| P000500132 | P000500132 Bomag Plate Compactor Bpr25/50 |  |  | 1800 | 11284.61
| P000500133 | P000500133 Bomag Plate Compactor Bpr25/50 |  |  |  | 553.85
| P000610012 | P000610012 Sb Hopper Broom Attachment |  |  | 1400 | 4792.31
| P000610041 | P000610041 Hydraulic Breaker CB 37S for Skid Steer Loader |  |  |  | 3413.3
30020 | I-Aerial lifts |  |  |  | 8250 | 38775
| 2210180513 | Spider Lift - 26 Mtr (X26J) with Sky Guard-Working |  |  | 8250 | 38775
30030 | I-Building construction machinery and accessories |  |  |  | 21924 | 184606.48
| KSFT000027 | KSFT000027 Diesel Storage Tank 1800 Ltrs(Original) |  |  |  | 138.48
| P000090078 | P000090078 Diesel Tanker- Dorchester Hotel & Residences (Completion Works) Scania Fuel Tanker |  |  |  | 1044
| P000490100 | P000490100 Livers Hf 4Kva Converter |  |  | 1053 | 9720
| W000020068 | W000020068 Diesel Tanker 9/68 Mercedes Fuel Tanker - DXB64273 |  |  | 2088 | 10962
| W000020069 | W000020069 Diesel Tanker - 9/69 - Dorchester Hotel & Residences (Completion Works) Mercedes Fuel Tanker - DXB63219 |  |  | 8352 | 49590
| W000020070 | W000020070 9/70 Diesel Tanker Dorchester Hotel & Residences (Completion Works) Mercedes Fuel Tanker - DXB65028 |  |  | 6264 | 90828
| W000020071 | W000020071 Mercdes Water Tanker - DXB64272 |  |  |  | 6945
| W000020072 | W000020072 9/72 Sweet Water Tanker 1-Trip Mercdes Water Tanker - DXB62723 |  |  |  | 10674.5
| W000020073 | W000020073 9/73 Sweet Water Tanker 1-Trip Mercedes Water Tanker-DXB62979 |  |  | 4167 | 4704.5
30100 | I-Lifting equipment and accessories |  |  |  | 206437.03 | 1209197
| 2410160302 | Forklift - 5 Ton With Operator-Working |  |  | 880 | 20460
| 2410160315 | Forklift 3 Ton With Long Fork-Working |  |  | 17938.91 | 114402.86
| 2410160402 | Mast Climber (Model: MSM SUPER)-Working |  |  | 45692.67 | 75308.42
| 2410161705 | Electric Scissor Lift - 7.8 Mtr-Working |  |  | 2200 | 2200
| 2410161727 | Power Tower Duo - 5.1 Mtr-Working |  |  | 1540.4 | 6576.34
| 2410162303 | Derrick Crane |  |  | 24200.19 | 399344.04
| 2410162304 | Derrick Crane - 12 Ton |  |  | 31731.17 | 216828.28
| 2410162402 | Mobile Crane - 50 Ton-Working |  |  |  | 2640
| 2410162404 | Mobile Crane - 70 Ton With Fly Jib & Skidding |  |  |  | 21450
| 2410162405 | Mobile Crane - 100 Ton-Working |  |  |  | 6600
| 2410162406 | Mobile Crane - 100 Ton-Working |  |  | 3850 | 3850
| 2410162414 | Mini Crane (JEKKO SPX532) - 3.2 Ton With Operator-Working |  |  | 49561.5 | 96898.79
| 2410162415 | Jekko Mini Picker-1000kg-Working |  |  | 12184.64 | 19800.05
| MOB001 | Calculation For Special Bracket with 3rd Party Approval |  |  | 2530 | 125620
| P000210110 | P000210110 Manitou Mt-X 1840 Telehandler |  |  | 1073.08 | 1073.08
| P000250049 | P000250049 Liebherr Mobile Crane-55 Ton(1055-32) |  |  |  | 1246.15
| P000260029 | P000260029 Skyjack 8841Rt Scissor Lift |  |  |  | 211.54
| P000260049 | P000260049 Scissor Lift Electric- 8m |  |  | 2200 | 16918.9
| P000260050 | P000260050 Scissor Lift - 8m |  |  | 2200.12 | 7361.94
| P000260081 | P000260081 Scissor Lift Electric- 8m |  |  | 2200.12 | 17854.82
| P000260082 | P000260082 Scissor Lift Electric- 8m |  |  | 2200 | 16484.93
| P000260087 | P000260087 Nano Lift 4.5 Meter |  |  | 1200 | 9323.07
| P000260088 | P000260088 Nano Lift 4.5 Meter |  |  | 1200 | 8630.76
| P000260092 | P000260092 Nano Lift 4.5 Meter |  |  | 1200 | 9092.3
| W000180010 | W000180010 Moffett Forklift M4 - DXB43955 |  |  | 654.23 | 654.23
| W000180014 | W000180014 TCM Forklift - DXB 41076-Working |  |  |  | 8366.5
30110 | I-Passenger motor vehicles |  |  |  | 55702.94 | 391002.59
| 2510150704 | Pick Up - 3 Ton Double CabinWithout Driver-Working |  |  | 5521.26 | 48168.22
| 2510150705 | Recovery Vehicle 3 Ton |  |  | 660 | 3850
| P000080660 | P000080660 Ashok Leyland Bus - Dxb 92791Q With IVMS |  |  | 840 | 840
| P000080661 | P000080661 Ashok Leyland Bus - Dxb 36303H |  |  |  | 1512
| P000080664 | P000080664 Ashok Leyland Bus - Dxb 52753J |  |  | 5110 | 28504
| P000080666 | P000080666 Ashok Leyland Bus - Dxb 53795I |  |  |  | 168
| P000080667 | P000080667 Ashok Leyland Bus - Dxb 51596J |  |  | 3024 | 3024
| P000080681 | P000080681 Ashok Leyland Bus - DXB 86848H |  |  | 5110 | 34286
| P000080682 | P000080682 Ashok Leyland Bus - DXB 87476H |  |  |  | 840
| P000080683 | P000080683 Ashok Leyland Bus - DXB 15614M |  |  |  | 1176
| P000080684 | P000080684 Ashok Leyland Bus - DXB 15497M |  |  | 840 | 840
| P000080685 | P000080685 Ashok Leyland Bus - DXB 86783H With IVMS |  |  | 4368 | 24402
| P000080686 | P000080686 Ashok Leyland Bus - DXB 15496M |  |  |  | 1848
| P000080687 | P000080687 Ashok Leyland Bus - DXB 85148H |  |  | 5110 | 43092
| P000080690 | P000080690 Ashok Leyland Bus - DXB 15611M |  |  | 5110 | 45878
| P000080692 | P000080692 Ashok Leyland 59 Seat Bus-DXB 72359 W |  |  |  | 184.44
| P000080696 | P000080696 Ashok Leyland 59 Seat Bus-DXB 72353 W |  |  | 4795.4 | 31769.51
| P000080701 | P000080701 Ashok Leyland 71 Seat Bus |  |  | 5850 | 45181.23
| TA00033100 | TA00033100 TOYOTA COASTER HI ROOF 23STR 4.0D MANUAL |  |  | 4462.03 | 4462.03
| TA00033109 | TA00033109 TOYOTA COASTER HI ROOF 23STR 4.0D MANUAL |  |  | 4680 | 44427.95
| TA00043000 | TA00043000 TOYOTA HIACE 13 SEAT BUS |  |  | 222.25 | 26549.21
30120 | I-Product and material transport vehicles |  |  |  |  | 16019.78
| P000320042 | P000320042 Thwaites Dumper - P 22157 |  |  |  | 16019.78
30130 | I-Specialized and recreational vehicles |  |  |  | 36758.64 | 207937.08
| P000100022 | P000100022 Nissan Truck With Hiab Crane With IVMS |  |  |  | 1540
| P000100023 | P000100023 Mercedes Truck With Crane With IVMS |  |  |  | 2480
| P000100025 | P000100025 Mercedes Truck With Crane With IVMS |  |  |  | 2480
| P000120019 | P000120019 12/19 Skip Truck 1-Trip ( 59151 ) Isuzu 12Ton Truck - Dxb 83254O |  |  | 12285 | 72847
| P000120020 | P000120020 1 Trip 12/20 Skip Truck ( 59844 ) Hino 13.5 Ton Skip Truck |  |  | 1092 | 14478
| W000030018 | W000030018 Nissan Truck with Hiab Crane With IVMS |  |  | 3473.64 | 9497.08
| W000030019 | W000030019 Nissan Truck with Hiab Crane With IVMS |  |  | 3850 | 3850
| W000030020 | W000030020 Nissan Truck with Hiab Crane With IVMS |  |  | 770 | 3850
| W000050017 | W000050017 12/17 Skip Truck 1-Trip ( 59984 ) Isuzu with Hiab Skip Loader - Dxb 70086 D |  |  | 15288 | 96915
30140 | I-Truck tractors |  |  |  | 402 | 4422
| P000170028 | P000170028 Machinery Shifting Man Tractor Head - Dxb 25990-Low Bed |  |  | 402 | 402
| W000070021 | W000070021 MAN Tractor Unit - DXB 66748 |  |  |  | 2010
| W000070022 | W000070022 MAN Tractor Unit - DXB 66768 |  |  |  | 2010
30160 | I-Product and material trailers |  |  |  | 248 | 1528
| W000320032 | W000320032 Machinery Shifting Low Bed Semi Trailer 65Ton |  |  | 248 | 248
| W000320035 | W000320035 Flat Bed Semi Trailer - 55Ton |  |  |  | 640
| W000320037 | W000320037 Flat Bed Semi Trailer - 55Ton |  |  |  | 640
30170 | I-Power generators |  |  |  | 45308.41 | 699093.84
| 2611160108 | Generator - 350 KVA-Working |  |  |  | 17769.86
| 2611160109 | Cables - (1C 240mm2 40Mtr x 30 Runs =1200Mtrs)-Working |  |  | 20769.86 | 212794.7
| 2611160110 | Generator - 650 KVA-Working |  |  | 24538.55 | 468529.28
30230 | I-Compressors |  |  |  |  | 11894.43
| P000330091 | P000330091 Atlas Copco Air Compressor |  |  |  | 11682.9
| PTLT250022 | PTLT250022 Electric Compressor |  |  |  | 211.53
30510 | I-Plant repair & maintenance |  |  |  | 12565.3 | 150633.11
| K000010027 | K000010027 Eco Cabin Type 1 - Ablution |  |  |  | 6292.17
| KA00010006 | KA00010006 Eco Cabin Type 1 - Ablution |  |  |  | 7625.61
| KVS0010004 | KVS0010004 CAT & Ginny Cable Locator M/Kit |  |  | 468 | 3942
| PTLT260006 | PTLT260006 Floor Polishing Machine |  |  |  | 4440
| PTLT530006 | PTLT530006 Block Cutter |  |  |  | 2850
| S3131298 | S3131298-Fuel RFID Tag Installation |  |  |  | 161
| S3131331 | S3131331-Fuel RFID Tag Installation |  |  |  | 322
| S3131479 | S3131479-Fuel RFID Tag Installation / Metal Jerry Can |  |  |  | 472
| S3131494 | S3131494-Third party inspection & Certification |  |  |  | 100
| S3131597 | S3131597-PAT Test |  |  |  | 1850
| S3131609 | S3131609-Fabrication of Steel Ramp Dorchester Hotel |  |  |  | 7374
| S3131631 | S3131631-Electrical Repairs |  |  |  | 500
| S3131666 | S3131666-Dorchester Hotel -Third party inspection & Certification |  |  |  | 770
| S3131668 | S3131668-Electrical Repairs |  |  |  | 400
| S3131730 | S3131730-Electrical Repairs |  |  |  | 25
| S3131828 | S3131828-Electrical Repairs |  |  |  | 2225
| S3131868 | S3131868-DORCHESTER Hotel - Third party inspection & Certification |  |  |  | 860
| S3131933 | S3131933-Fuel RFID Tag Installation |  |  |  | 161
| S3131942 | S3131942-Electrical Repairs |  |  |  | 1431.19
| S3131975 | S3131975-PAT Test and Plugs |  |  |  | 1020
| S3132009 | S3132009-PAT Test |  |  |  | 350
| S3132054 | S3132054-Electrical Repairs |  |  |  | 1255.29
| S3132108 | S3132108-DORCHESTER Hotel- Water pump Replaced |  |  |  | 581
| S3132186 | S3132186-Electrical Repairs |  |  |  | 2619.96
| S3132199 | S3132199-DORCHESTER HOTEL Third party inspection & Certification |  |  |  | 200
| S3132235 | S3132235-Fuel RFID Tag Installation |  |  |  | 161
| S3132242 | S3132242-Electrical Repairs |  |  |  | 1694.02
| S3132281 | S3132281-Electrical Repairs |  |  |  | 175
| S3132299 | S3132299-DORCHESTER Hotel- Beam Cutting |  |  |  | 5510
| S3132316 | S3132316-Electrical Repairs |  |  |  | 666.32
| S3132327 | S3132327-Electrical Repairs |  |  |  | 1082.53
| S3132436 | S3132436-DORCHESTER Hotel Third party inspection & Certification |  |  |  | 2100
| S3132513 | S3132513-Refurbishment of KA1/6 & KA1/27 Ablution units |  |  |  | 418.8
| S3132579 | S3132579-Electrical Repairs |  |  |  | 1569.31
| S3132712 | S3132712-Electrical Repairs |  |  |  | 421
| S3132715 | S3132715-Electrical Repairs |  |  |  | 183.1
| S3132769 | S3132769-Electrical Repairs |  |  |  | 286.67
| S3132770 | S3132770-Electrical Repairs |  |  |  | 504.57
| S3132873 | S3132873-Electrical Repairs |  |  |  | 199.97
| S3132874 | S3132874-Electrical Repairs |  |  |  | 269.22
| S3132898 | S3132898-Electrical Repairs |  |  |  | 400
| S3132899 | S3132899-Electrical Repairs |  |  |  | 504.57
| S3132900 | S3132900-Electrical Repairs |  |  |  | 1158.48
| S3132901 | S3132901-Electrical Repairs |  |  |  | 1169.59
| S3132903 | S3132903-Electrical Repairs |  |  |  | 1189.12
| S3133002 | S3133002-Signboard Cutting Remove |  |  |  | 640.67
| S3133036 | S3133036-Electrical Repairs |  |  |  | 30.6
| S3133037 | S3133037-Electrical Repairs |  |  |  | 357
| S3133131 | S3133131-Electrical Repairs |  |  |  | 131.81
| S3133139 | S3133139-Electrical Repairs |  |  |  | 400
| S3133140 | S3133140-Electrical Repairs |  |  |  | 268.05
| S3133143 | S3133143-Electrical Repairs |  |  |  | 1346.55
| S3133145 | S3133145-Electrical Repairs |  |  |  | 836.5
| S3133262 | S3133262-Electrical Repairs |  |  |  | 400
| S3133263 | S3133263-Electrical Repairs |  |  |  | 434.9
| S3133265 | S3133265-Electrical Repairs |  |  |  | 354.19
| S3133266 | S3133266-Electrical Repairs |  |  |  | 1293.47
| S3133267 | S3133267-Electrical Repairs |  |  |  | 566.71
| S3133473 | S3133473-Electrical Repairs |  |  |  | 172
| S3133475 | S3133475-Electrical Repairs |  |  |  | 162
| S3133481 | S3133481-Electrical Repairs |  |  |  | 822.69
| S3133483 | S3133483-Electrical Repairs |  |  |  | 362.82
| S3133486 | S3133486-Electrical Repairs |  |  |  | 196
| S3133536 | S3133536-Electrical Repairs |  |  |  | 393.04
| S3133537 | S3133537-Electrical Repairs |  |  |  | 180.55
| S3133538 | S3133538-Electrical Repairs |  |  |  | 530.48
| S3133539 | S3133539-Electrical Repairs |  |  |  | 1486.78
| S3133581 | S3133581-Electrical Repairs |  |  |  | 155
| S3133592 | S3133592-Electrical Repairs |  |  |  | 100
| S3133645 | S3133645-Electrical Repairs |  |  |  | 62.53
| S3133646 | S3133646-Electrical Repairs |  |  |  | 400
| S3133685 | S3133685-Fuel RFID Tag Installation |  |  |  | 161
| S3133755 | S3133755-Electrical Repairs |  |  |  | 50
| S3133756 | S3133756-Electrical Repairs |  |  |  | 65
| S3133757 | S3133757-Electrical Repairs |  |  |  | 325
| S3133780 | S3133780-Light Tool Repair |  |  |  | 655.63
| S3133781 | S3133781-Light Tool Repair |  |  |  | 643.47
| S3133782 | S3133782-Light Tool Repair |  |  |  | 295.49
| S3133827 | S3133827-Electrical Repairs |  |  |  | 65
| S3133858 | S3133858-Light Tool Repair |  |  |  | 55
| S3133859 | S3133859-Light Tool Repair |  |  |  | 55
| S3133903 | S3133903-Light Tool Repair |  |  | 132.38 | 132.38
| S3133911 | S3133911-Light Tool Repair |  |  |  | 320
| S3133976 | S3133976-Light Tool Repair |  |  |  | 2095.73
| S3133979 | S3133979-Light Tool Repair |  |  |  | 172.85
| S3134028 | S3134028-Light Tool Repair |  |  |  | 269.31
| S3134029 | S3134029-Light Tool Repair |  |  |  | 201
| S3134080 | S3134080-Light Tool Repair |  |  | 492.04 | 492.04
| S3134116 | S3134116-Light Tool Repair |  |  |  | 467.97
| S3134118 | S3134118-Light Tool Repair |  |  | 504.5 | 504.5
| S3134136 | S3134136-Light Tool Repair |  |  |  | 177.38
| S3134137 | S3134137-Light Tool Repair |  |  |  | 177.38
| S3134138 | S3134138-Light Tool Repair |  |  |  | 177.38
| S3134139 | S3134139-Light Tool Repair |  |  |  | 177.38
| S3134167 | S3134167-Light Tool Repair |  |  | 177.38 | 177.38
| S3134168 | S3134168-Light Tool Repair |  |  | 77.38 | 77.38
| S3134177 | S3134177-Fuel RFID Tag Installation |  |  |  | 161
| S3134245 | S3134245-Fuel RFID Tag Installation |  |  |  | 161
| S3134274 | S3134274-Light Tool Repair |  |  | 214.3 | 214.3
| S3134275 | S3134275-Light Tool Repair / Installation |  |  | 525 | 525
| S3134278 | S3134278-Light Tool Repair |  |  |  | 174.2
| S3134320 | S3134320-Light Tool Repair |  |  | 386 | 386
| S3134352 | S3134352-Fuel RFID Tag Installation |  |  |  | 161
| S3134368 | S3134368-Supply of Safety Net |  |  |  | 800
| S3134413 | S3134413-Third party inspection & Certification |  |  | 50 | 50
| S3134435 | S3134435-Light Tool Repair |  |  | 310 | 310
| S3134492 | S3134492-Gas Cutting Work |  |  |  | 2185
| S3134583 | S3134583-Light Tool Repair |  |  | 191.79 | 191.79
| S3134585 | S3134585-Light Tool Repair |  |  | 465.95 | 465.95
| S3134588 | S3134588-Light Tool Repair |  |  | 264.28 | 264.28
| S3134606 | S3134606-Light Tool Repair |  |  | 1360.96 | 1360.96
| S3134607 | S3134607-Light Tool Repair |  |  | 12.92 | 12.92
| S3134608 | S3134608-Light Tool Repair |  |  | 324.33 | 324.33
| S3134609 | S3134609-Light Tool Repair |  |  | 570.66 | 570.66
| S3134653 | S3134653-Light Tool Repair / Pat Test |  |  |  | 5625
| S3134654 | S3134654-Light Tool Repair / Pat Test |  |  |  | 1140
| S3134669 | S3134669-Light Tool Repair |  |  | 166.63 | 166.63
| S3134681 | S3134681-Light Tool Repair |  |  | 336.41 | 336.41
| S3134682 | S3134682-Light Tool Repair |  |  | 236.41 | 236.41
| S3134762 | S3134762-Light Tool Repair |  |  | 495 | 495
| S3134763 | S3134763-Light Tool Repair |  |  | 178.92 | 178.92
| S3134764 | S3134764-Light Tool Repair |  |  | 495 | 495
| S3134771 | S3134771-Light Tool Repair |  |  | 187 | 187
| S3134772 | S3134772-Light Tool Repair |  |  | 135.52 | 135.52
| S3134773 | S3134773-Light Tool Repair |  |  | 187 | 187
| S3134774 | S3134774-Light Tool Repair |  |  | 377.77 | 377.77
| S3134775 | S3134775-Light Tool Repair |  |  | 400 | 400
| S3134788 | S3134788-Light Tool Repair |  |  | 173 | 173
| S3134789 | S3134789-Light Tool Repair |  |  | 248.5 | 248.5
| S3134958 | S3134958-Third party inspection & Certification |  |  | 50 | 50
| S3135092 | S3135092-Third party inspection & Certification |  |  | 800 | 800
| S3135127 | S3135127-Gas Cutting Works |  |  | 1045 | 1045
| S3304180 | S3304180-Ac Service & Repair |  |  |  | 5580
| S3304218 | S3304218-Additional Paint Requirement for the New Project - Dorchester |  |  |  | 946
| S3304220 | S3304220-Ac Repairs & Service |  |  |  | 4490
| S3304230 | S3304230-Ac Repair & Service - Client Room |  |  |  | 2220
| S3304236 | S3304236-Third Party Certificate for Concrete Bucket (KCB010) |  |  |  | 50
| S3304239 | S3304239-Ac Repairs & Service |  |  |  | 4400
| S3304272 | S3304272-Ac Repair & Service (Non KCE Asset) |  |  |  | 1830
| S3304302 | S3304302-Ac Repairs & Service (Non KCE Asset) |  |  |  | 1980
| S3304317 | S3304317-Replacement of Asian Ablution ? Bottom and Top (KA1/27) |  |  |  | 834.25
| S3304379 | S3304379-Ac Repairs & Service for client office & KCE office |  |  |  | 1120
| S3304387 | S3304387-AC Repair & Service for client office & KCE office |  |  |  | 2490
| S3304411 | S3304411-AC Repair & Service for Site office. |  |  |  | 8280
| S3304437 | S3304437-Inspection & Servicing of Fire Extinguishers |  |  |  | 6000
| S3304536 | S3304536-Forklift Charges - Material Offloading |  |  |  | 65
| S3304579 | S3304579-Forklift Charges |  |  |  | 65
| S3304589 | S3304589-Forklift Charge |  |  |  | 65
| S3304597 | S3304597-Forklift Charge |  |  |  | 65
| S3304601 | S3304601-Forklift Charge |  |  |  | 65
| S3304666 | S3304666-Cubicle Door Locks |  |  |  | 424.08
| S3304667 | S3304667-Urinal Push Tap Leak Rectification |  |  |  | 977.48
| S3304758 | S3304758-Forklift Charge |  |  | 65 | 65
| T039101439 | T039101439 Grab Prefabricated Concrete |  |  | 460.27 | 460.27
Total |  |  |  |  | 400500.97 | 2996488.49
Manual Journals
Cost Head | Description |  | Type | Int Ref | Current | TTD
30295 | I-Waste skip |  |  |  | 15100 | 146300.67
|  | Mixed Waste-January 2023 | JNL | 158640 | 7280
|  | Demolition Waste-January 2023 | JNL | 158640 | 7820
30951 | Plant cost accruals - CVR |  |  |  |  | 0
34110 | E-Passenger motor vehicles |  |  |  | 2464 | 15032
|  | P000080664-KCE Salik Month Of January 2023 | JNL | 158485 | 320
|  | P000080660-KCE Salik Month Of January 2023 | JNL | 158485 | 64
|  | P000080701-KCE Salik Month Of January 2023 | JNL | 158485 | 368
|  | P000080667-KCE Salik Month Of January 2023 | JNL | 158485 | 144
|  | P000080687-KCE Salik Month Of January 2023 | JNL | 158485 | 260
|  | P000080685-KCE Salik Month Of January 2023 | JNL | 158485 | 272
|  | P000080690-KCE Salik Month Of January 2023 | JNL | 158485 | 324
|  | P000080681-KCE Salik Month Of January 2023 | JNL | 158485 | 300
|  | P000080684-KCE Salik Month Of January 2023 | JNL | 158485 | 72
|  | P000080696-KCE Salik Month Of January 2023 | JNL | 158485 | 340
34120 | E-Product and material transport vehicles |  |  |  | 967.4 | 9542.4
|  | TA00043000-Salik For December 2022 | JNL | 158482 | 247.8
|  | TA00033109-Salik For December 2022 | JNL | 158482 | 495.6
|  | W000020073-KCE Salik Month Of January 2023 | JNL | 158485 | 224
Total |  |  |  |  | 18531.4 | 170875.07
Petty Cash Charges
Cost Head | Description |  | Type | Int Ref | Current | TTD
Total
Direct Invoices
Cost Head | Description |  | Type | Int Ref | Current | TTD
30100 | I-Lifting equipment and accessories |  |  |  |  | 400
| KCEE004 | KCE (LLC) - Equipment Hire Div |  |  |  | 400
34110 | E-Passenger motor vehicles |  |  |  | 616.5 | 616.5
| GOLD010 | Golden Palace Heavy and Light |  |  | 616.5 | 616.5
|  | Hire-Pick Up 3 tonSalik -December 2022 | PINN | 2301PL001695 | 616.5
34120 | E-Product and material transport vehicles |  |  |  |  | 7501.5
| GOLD010 | Golden Palace Heavy and Light |  |  |  | 7501.5
Total |  |  |  |  | 616.5 | 8518
[5 empty] | 419648.87 | 3175881.56

## Subcontractor
COINS - FINANCE
Subcontract Cost 201A22002 Dorchester Hotel & Residences
Period January 2023
Subcontract Costs
Cost Head |  | Description |  |  | Int Ref |  | Ext Ref |  | Current |  | TTD
Manual Journals
| Cost Head |  | Description |  |  | Type |  | Int Ref |  | Current |  | TTD
Total
CVR Items
Cost Head |  | Description |  |  | Type |  | Int Ref |  | Current |  | TTD
Total | [10 empty] | 0
Purchase Orders
Commodity |  | Description |  |  | Invoiced |  | Accrual / Rev |  | Current |  | TTD
62001A01 |  | Pest control |  |  |  |  | 1500 |  | 1500 |  | 9120
|  | CITY003 |  | City Pest Control and Building |  |  | 1500 |  | 1500 |  | 9120
Total | [6 empty] | 1500 |  | 1500 |  | 9120
Direct Invoices
Cost Head |  | Description |  |  | Type |  | Int Ref |  | Current |  | TTD
Total

## Overhead
COINS - FINANCE
Overhead Cost 201A22002 Dorchester Hotel & Residences
Period January 2023
CVR Items
Purchase Orders
Commodity | Description |  | Invoiced | Accrual / Rev | Current | TTD
25512A01 | Project Sign Boards |  |  | 0 | 0 | 8303
| ABDU011 | Abdulrahman Al Abdooli Adverti |  | 0 | 0 | 890
| AMAL002 | Amalgam Ind. LLC |  |  | 0 | 3003
| KCEJ001 | KCE (LLC) - Joinery Division |  |  | 0 | 3660
| SALE001 | Saleem Jacobson Trading |  |  | 0 | 750
29901A01 | Small Tools/Equipment |  |  |  | 0 | 9035
| ALJA007 | Al Jas Technical Services LLC |  |  | 0 | 9035
60803A01 | Water and Electricity Charges |  |  |  | 0 | 24200
| DANL001 | Danlesco Gulf LLC |  |  | 0 | 24200
60905V02 | IT Equipment Printer Cameras etc |  |  | 22130.5 | 22130.5 | 72043.2
| ASTD001 | AST Digital Print Centre |  |  | 0 | 11561.84
| NEOT001 | Neo Tech Engineering LLC |  | 9830.5 | 9830.5 | 34338.5
| SCRE002 | Screencheck Technology Trading |  |  | 0 | 11300
| SHAR005 | Sharaf DG LLC |  |  | 0 | 2542.86
| ZENE003 | Zener Marine Services LLC |  | 12300 | 12300 | 12300
61001A01 | Safety Clothing and Equipment / PPE |  | 6936 | 3018 | 9954 | 62071
| AGSO001 | AGS Office Supplies and Tradin |  |  | 0 | 250
| ALAB003 | Al Abbasi Fasteners and Hardware |  |  | 0 | 14750
| ALJA007 | Al Jas Technical Services LLC | 3936 | 3018 | 6954 | 15945
| GULF019 | Gulf Metal Wires Industry LLC |  |  | 0 | 800
| KENT002 | Kent Star General Trading LLC |  |  | 0 | 2000
| SALE001 | Saleem Jacobson Trading | 3000 |  | 3000 | 15526
| TULI001 | Tulip Trading LLC |  |  | 0 | 12800
61003A01 | Health and Safety expenses |  | 1921.01 |  | 1921.01 | 41245.93
| ALAM004 | Al Ameen Pharmacy LLC | 1321.01 |  | 1321.01 | 8825.93
| ASGC002 | ASGC Trading Building Machines & Equipment Rental LLC |  |  | 0 | 8000
| DANA002 | Danat Alkhaleej for Safety Consultancy | 600 |  | 600 | 600
| SALE001 | Saleem Jacobson Trading |  |  | 0 | 23820
61111A01 | Refreshments (snacks tea coffee etc.) |  | 10035.9 | -2726.4 | 7309.5 | 71756.75
| ALSH022 | Al Shalal Pure Drinking Water LLC | 1516 | 504 | 2020 | 13948
| CHOI001 | T Choithram and Sons LLC | 8519.9 | -3230.4 | 5289.5 | 53993.75
| CLEA003 | Clear Ice LLC |  |  | 0 | 750
| FIND001 | Find General Trading LLC |  |  | 0 | 785
| JACK001 | Jackys Electronics LLC |  |  | 0 | 2280
61441A01 | Site Office Consumables |  | 16010 | -6880 | 9130 | 51242
| ALAB003 | Al Abbasi Fasteners and Hardware | 13760 | -6880 | 6880 | 30960
| ALBA009 | Al Bariq Equipment LLC |  | 0 | 0 | 3832
| MANG001 | Mangal Trading Co LLC | 2250 |  | 2250 | 16450
61511A01 | Laboratory Testing & Calibaration Charges |  | 4200 |  | 4200 | 8130
| ALFA021 | Al Fajer Trading LLC |  |  | 0 | 330
| DANA002 | Danat Alkhaleej for Safety Consultancy | 4200 |  | 4200 | 6850
| GLOB007 | G Global Technologies LLC |  |  | 0 | 500
| WIMP001 | Wimpey Laboratories LLC |  |  | 0 | 450
61521A01 | Rubbish Removal |  | 4068.72 | 38000 | 42068.72 | 167304
| GREE044 | Green Earth Waste Collection & Transportation Services | 4068.72 |  | 4068.72 | 53304
| STUR001 | Sturdy Products UAE Limited |  | 38000 | 38000 | 114000
61531A01 | Office & Site Furniture - Including ACs |  | 5500 |  | 5500 | 82490
| ALAR007 | Al Areej AC Units Fix Cont |  |  | 0 | 31625
| ALNA007 | Al Najah Furnishings LLC | 5500 |  | 5500 | 5500
| SABI001 | Sabi Air Conditioning Trading |  |  | 0 | 45365
61531A02 | Site Est (Offices Ablutions Stores Etc) |  |  |  | 0 | 22930.5
| ALME003 | Al Mesmar Trading Co LLC |  |  | 0 | 5025
| NATI010 | National Services for Carpet a |  |  | 0 | 10368.5
| SALE001 | Saleem Jacobson Trading |  |  | 0 | 6705
| TULI001 | Tulip Trading LLC |  |  | 0 | 832
61701A01 | Printing and Stationery |  | 2500 | 614.06 | 3114.06 | 45723.46
| AGSO001 | AGS Office Supplies and Tradin |  | 614.06 | 614.06 | 17129.06
| ALWA002 | Al Waha Stamps LLC |  |  | 0 | 670
| ASTD001 | AST Digital Print Centre | 2500 |  | 2500 | 27009.4
| SILV004 | Silver Screen Advertising Gift |  |  | 0 | 915
Total |  |  | 51171.63 | 54156.16 | 105327.79 | 666474.84
Direct Invoices
Cost Head | Description |  | Type | Int Ref | Current | TTD
29955 | Profit Abatement-CVR |  |  |  |  | 0
| ACC | Accruals |  |  |  | -22492843
60624 | Penalties & Violations-Costed to Company |  |  |  |  | 1872
| GOLD010 | Golden Palace Heavy and Light |  |  |  | 1872
60701 | Communication expense - landline and fax usage |  |  |  | 4881.48 | 50832.05
| EMIR032 | Emirates Integrated Telecommun |  |  | 4600 | 48384.76
|  | DU-DEC 2022 (Internet broad band-1) | PINN | 2301PL000425 | 3020
|  | DU-DEC 2022 (Internet broad band-2) | PINN | 2301PL000425 | 1580
| ETIS001 | Emirates Telecommunications Gr |  |  | 281.48 | 2447.29
|  | Tel Cost-0565456086-201A22002-DORCHESTER HOTEL-HIRED--SANEESH MOHAN (DEC-2022) | PINN | 2301PL000776 | 110.62
|  | Tel Cost-0509394368-201A22002-DORCHESTER HOTEL-DORCHESTER FACE STATION (DEC-2022) | PINN | 2301PL000776 | 105
|  | Tel Cost-0501894373-201A22002-DORCHESTER HOTEL-DORCHESTER FACE STATION (DEC-2022) | PINN | 2301PL000776 | 65.86
60703 | Communication expense - internet and data |  |  |  |  | 3750
| EMIR032 | Emirates Integrated Telecommun |  |  |  | 3750
60803 | Utilities - water external supply |  |  |  | 2475 | 6050
| DUBA003 | Dubai Aluminium PJSC |  |  | 2475 | 6050
|  | SWEET WATER CHGS - DEC'2022 | PINN | 2301PL000199 | 2475
60901 | Printers & Photocopiers |  |  |  |  | 50186.1
| NEWS001 | New Smart Office Automation LL |  |  |  | 50186.1
61003 | First-aid and medical expenses |  |  |  | 1445 | 1445
| YORK004 | York Diagnostic Laboratories D |  |  | 1445 | 1445
|  | PCR COVID TESTS (81 SAMPLES @ AED 85) (SEPT'2022 TO NOV'2022) | PINN | 2301PL000478 | 1445
61201 | Recruitment expenses |  |  |  |  | 2830
| EISA001 | Eisa Travels Agency LLC |  |  |  | 2830
Total |  |  |  |  | 8801.48 | 116965.15
Petty Cash Charges
Cost Head | Description |  | Type | Int Ref | Current | TTD
60621 | Other fee - charges |  |  |  | 5250 | 35102.52
|  | 04193-MURALI N-201A22002-NOC CHARGES | PCP | JAN/11817/10 | 5250
60811 | Utilities - office and factory electricity and water |  |  |  |  | 46680
61111 | Refreshments (snacks, tea, coffee etc.) |  |  |  | 9591 | 31193.05
|  | 27743-CHRIS McCANN-201A22002 | PCP | JAN/11832/16 | 7219
|  | 27743-CHRIS McCANN-201A22002 | PCP | JAN/11836/21 | 2372
61131 | COS Staff welfare expense |  |  |  | 1100.44 | 4313.56
|  | 27743-CHRIS McCANN-201A22002 | PCP | JAN/11832/16 | 1100.44
62001 | Miscellaneous expenses |  |  |  | 350 | 700
|  | 27743-CHRIS McCANN-201A22002 | PCP | JAN/11836/21 | 350
Total |  |  |  |  | 16291.44 | 117989.13
Manual Journals
Cost Head | Description |  | Type | Int Ref | Current | TTD
60621 | Other fee - charges |  |  |  | 5660 | 82668.81
|  | Credit card transactions_9134-DM - Fees to obtain a sand disposal permit-202300048472-26/01/2023-201A22002 (JAN-2023) | JNL |  | 230
|  | Credit card transactions_9134-RTA - Fees to obtain diversion NOC-1449951882-27/01/2023-201A22002 (JAN-2023) | JNL |  | 220
|  | Replacement Of Lost No Plate | JNL |  | 70
|  | Credit card transactions_9134-RTA - Fees to obtain access NOC-1432191555-04/01/2023-201A22002 (JAN-2023) | JNL |  | 120
|  | Credit card transactions_9134-DDA - fees to renew BCC-1434134628-06/01/2023-201A22002 (JAN-2023) | JNL |  | 5020
60701 | Communication expense - landline and fax usage |  |  |  |  | 25203
60703 | Communication expense - internet and data |  |  |  |  | 1079.17
60811 | Utilities - office and factory electricity and water |  |  |  |  | 5064.85
60902 | Specialist Software |  |  |  |  | 49280
61001 | Health and safety - material items |  |  |  |  | 1490
61111 | Refreshments (snacks, tea, coffee etc.) |  |  |  | 297.08 | 2193.67
|  | Unclaimed VAT Dec'22 W/Off | JNL |  | 21.75
|  | Unclaimed VAT Dec'22 W/Off | JNL |  | 84.66
|  | Unclaimed VAT Dec'22 W/Off | JNL |  | 190.67
61201 | Recruitment expenses |  |  |  |  | -2830
61311 | Rent - accommodation |  |  |  |  | 119.03
62001 | Miscellaneous expenses |  |  |  |  | 100
Total |  |  |  |  | 5957.08 | 164368.53
Plant Charges
Cost Head | Description |  | Type | Int Ref | Current | TTD
60905 | Computers & Accessories |  |  |  | 1085 | 9912
| ITA0002123 | ITA0002123 Samsung Galaxy Tab Active Pro |  |  | 0 | 0
| ITA0003005 | ITA0003005 Face Station 2 - Identification Device |  |  | 217 | 2107
| ITA0003060 | ITA0003060 Face Station 2 - Identification Device |  |  | 217 | 2002
| ITA0003063 | ITA0003063 Face Station 2 - Identification Device |  |  | 217 | 1799
| ITA0003075 | ITA0003075 Face Station 2 - Identification Device |  |  | 217 | 2002
| ITA0003084 | ITA0003084 Face Station 2 - Identification Device |  |  | 217 | 2002
Total |  |  |  |  | 1085 | 9912
Stock Issues
Cost Head | Description |  | Type | Int Ref | Current | TTD
60902 | Specialist Software |  |  |  |  | 2399
| 60906V01-010017 | Bluebeam Revu Extreme Perpetual License Windows OS |  |  |  | 2399
60905 | Computers & Accessories |  |  |  | 874.56 | 25051.48
| 24325V01-010002 | Access Point Aruba AP 515 - New |  |  |  | 3897
| 24325V01-010004 | Mounting Kit Aruba AP 515 - New |  |  |  | 66
| 24325V01-020002 | Access Point Aruba AP 515 - Used |  |  |  | 0
| 60905V01-010006 | Keyboard & Mouse Logitec Wireless Black - New |  |  |  | 1375
| 60905V01-010008 | Mouse Logitec Wireless Black - New |  |  | 250 | 1200
| 60905V01-010011 | Cable HDMI 2m - New |  |  |  | 72.5
| 60905V01-010013 | Cable HDMI 5m - New |  |  |  | 110
| 60905V01-010019 | Cable Cat6 5m - New |  |  |  | 70.44
| 60905V01-010020 | Cable Roll 305m - New |  |  |  | 1835.9
| 60905V01-010031 | RJ45 connector - New |  |  |  | 8.26
| 60905V01-010037 | Monitor 24" 1080p E Series - New |  |  |  | 4887.75
| 60905V01-010038 | Monitor HP E22 G4 FHD - New |  |  |  | 4566.94
| 60905V01-010041 | Samsung Tablet Case Cover - New |  |  |  | 380
| 60905V01-010043 | Laptop Bag HP - New |  |  | 184.56 | 2724.96
| 60905V01-010045 | EVOLIS-YMCKO Color Ribbon - New |  |  | 440 | 660
| 60905V01-010046 | EVOLIS Smart Cards - Mifare 1K - New |  |  |  | 1120.02
| 60905V01-010050 | USB A Wi-Fi adapter - New |  |  |  | 582
| 60905V01-010052 | Crucial SSD Hard disk - New |  |  |  | 786.28
| 60905V01-010053 | Bracket for Crucial SSD Hard disk - New |  |  |  | 17.5
| 60905V01-010054 | New Onsite installation of new SSD with OS |  |  |  | 95
| 60909V01-010018 | Mobile Handset Samsung A13 Black ? New |  |  |  | 595.93
60906 | Standard Software |  |  |  |  | 8847
| 60906V01-010017 | Bluebeam Revu Extreme Perpetual License Windows OS |  |  |  | 7197
| 60906V01-010018 | Bluebeam Revu Extreme Annual Maintenance & Support Windows OS |  |  |  | 1650
60909 | Telecomunication Services |  |  |  |  | 36161.86
| 24325V01-010002 | Access Point Aruba AP 515 - New |  |  |  | 3897
| 24325V01-010004 | Mounting Kit Aruba AP 515 - New |  |  |  | 66
| 24325V01-010012 | Aruba Central AP Foundation 1y Subscription - New |  |  |  | 3651.91
| 24325V01-020005 | Network Switch Cisco SG350 28 Port - Used |  |  |  | 0
| 60909V01-010008 | Sim Card Etisalat Standard - New |  |  |  | 0
| 60909V01-010012 | Mobile Handset Samsung A12 Black - New |  |  |  | 4910.1
| 60909V01-010014 | Mobile Handset Samsung A52 Black - New |  |  |  | 1255.24
| 60909V01-010015 | Mobile Handset Nokia 225 - New |  |  |  | 340
| 60909V01-010018 | Mobile Handset Samsung A13 Black ? New |  |  |  | 20806.61
| 60909V01-010019 | Mobile Handset Samsung A53 ? New |  |  |  | 1235
61001 | Health and safety - material items |  |  |  | 27178.91 | 127058.22
| 46181503-A01361 | Blue Pant/Shirt 180 Gsm Full Sleeve -2XL | ISS |  | 631.73 | 4000.97
| 46181503-A01362 | Blue Pant/Shirt 180 Gsm Full Sleeve -3XL | ISS |  | 141.12 | 1270.08
| 46181503-A01363 | Blue Pant/Shirt 180 Gsm Full Sleeve -4XL |  |  |  | 309.96
| 46181503-A01364 | Blue Pant/Shirt 180 Gsm Full Sleeve -Large |  |  | 1754.82 | 7884.98
| 46181503-A01365 | Blue Pant/Shirt 180 Gsm Full Sleeve -Medium | ISS |  | 6708.04 | 20161.42
| 46181503-A01366 | Blue Pant/Shirt 180 Gsm Full Sleeve - Small |  |  | 2898 | 8806.75
| 46181503-A01367 | Blue Pant/Shirt 180 Gsm Full Sleeve -XL |  |  | 1262.15 | 6006.86
| 46181503-A01383 | Beige Pant/Shirt 180 Gsm Full Sleeve for Chargehand - 2XL |  |  |  | 456
| 46181503-A01386 | Beige Pant/Shirt 180 Gsm Full Sleeve for Chargehand - Large | ISS |  | 342 | 684
| 46181503-A01387 | Beige Pant/Shirt 180 Gsm Full Sleeve for Chargehand - Medium | ISS |  | 114 | 1482
| 46181503-A01388 | Beige Pant/Shirt 180 Gsm Full Sleeve for Chargehand - Small |  |  |  | 114
| 46181503-A01389 | Beige Pant/Shirt 180 Gsm Full Sleeve for Chargehand - XL |  |  |  | 342
| 46181504-A20645 | Hand Gloves 15g Nylon + Spandex with Washed Micro Foam Size 8 |  |  | 1185 | 5472.26
| 46181504-A20646 | Hand Gloves 15g Nylon + Spandex with Washed Micro Foam Size 9 |  |  | 3946.53 | 19626.39
| 46181504-A20647 | Hand Gloves 15g Nylon + Spandex with Washed Micro Foam Size 10 |  |  | 1568.96 | 8318.96
| 46181504-A20648 | Hand Gloves 15g Nylon + Spandex with Washed Micro Foam Size 11 | ISS |  | 375 | 375
| 46181605-A04415 | Safety Shoe For Staff 59351 Size 38 |  |  |  | 240
| 46181605-A04416 | Safety Shoe For Staff 59351 Size 39 |  |  |  | 80
| 46181605-A04418 | Safety Shoe For Staff 59351 Size 41 |  |  |  | 640
| 46181605-A04419 | Safety Shoe For Staff 59351 Size 42 | ISS |  | 80 | 1120
| 46181605-A04420 | Safety Shoe For Staff 59351 Size 43 | ISS |  | 160 | 1040
| 46181605-A04421 | Safety Shoe For Staff 59351 Size 44 |  |  |  | 560
| 46181605-A04422 | Safety Shoe For Staff 59351 Size 45 |  |  |  | 160
| 46181605-A04423 | Safety Shoe For Staff 59351 Size 46 |  |  |  | 80
| 46181605-A18968 | Safety Shoe For Staff 59351 Size 40 |  |  |  | 560
| 46181605-A18970 | Safety Shoe for workers Saudi 59102 SIZE 38 |  |  |  | 390
| 46181605-A18971 | Safety Shoe for workers Saudi 59102 SIZE 39 | ISS |  | 130 | 1885
| 46181605-A18972 | Safety Shoe for workers Saudi 59102 SIZE 40 | ISS |  | 1105 | 5135
| 46181605-A18973 | Safety Shoe for workers Saudi 59102 SIZE 41 |  |  | 585 | 3705
| 46181605-A18974 | Safety Shoe for workers Saudi 59102 SIZE 42 | ISS |  | 1950 | 9815
| 46181605-A18975 | Safety Shoe for workers Saudi 59102 SIZE 43 |  |  | 585 | 4615
| 46181605-A18976 | Safety Shoe for workers Saudi 59102 SIZE 44 |  |  | 390 | 2145
| 46181605-A18977 | Safety Shoe for workers Saudi 59102 SIZE 45 |  |  | 195 | 650
| 46181605-A18978 | Safety Shoe for workers Saudi 59102 SIZE 46 |  |  |  | 195
| 46181701-A04402 | Safety Helmet High Ev Yellow - 6 Point Textile Tapes System. Slip Ratche |  |  |  | 26
| 46181804-A04397 | Safety Goggles - Clear - Globus - Riley - Bm08 |  |  | 660 | 2870.98
| 46181804-A04398 | Safety Goggles - Grey - Globus - Riley - Bm08 |  |  |  | 65.56
| 46181804-A19383 | Safety Goggles - Clear - Bm10 |  |  |  | 51.47
| 46181804-A19384 | Safety Goggles - Clear - Riley - Pn-RLY00071 |  |  |  | 760.21
| 46181804-A19385 | Safety Goggles - Grey - Riley - Pn-RLY00072 |  |  |  | 509.49
| 46182001-A20175 | Disposable Face Mask Blue 3 Ply (1x50) Local |  |  | 326.56 | 4107.88
| 71001Z01-010011 | Fire Extinguisher Inspection Tag |  |  | 85 | 340
61131 | COS Staff welfare expense |  |  |  |  | 12314.32
| 51211706-A00348 | Aqualyte Solution 80Grmx100Satchets/Ct |  |  |  | 230.35
| 51211706-A00349 | Aqualyte Solution 800Grmx10Satchets/Ct |  |  |  | 12083.97
61701 | Stationary |  |  |  |  | 542.5
| 14111509-A19706 | Business Cards |  |  |  | 120
| 71701Z01-01005 | Khansaheb Note Pad A5 |  |  |  | 275
| 71701Z01-01006 | Khansaheb Note Pad A4 |  |  |  | 147.5
Total |  |  |  |  | 28053.47 | 212374.38
[5 empty] | 165516.26 | 1288084.03