## PA Front Sheet
PAYMENT APPLICATION
Application # 4
Khansaheb Civil Engineering L.L.C. | Date | 2022-12-30 |  |  |  |  | HOTEL
PO Box - 2716 | Period As on | 2022-12-25 |  |  |  |  | RESIDENCE
Dubai | Type | Scaffolding Services
United Arab Emirates | Our Bankers | Bank Of Sharjah
Tel : 971 04 605 7200
Fax : 971 04 285 7539 | Account No. | 013 06 278065 01
Attn: Mr. Saman Kulasooriya
Dorchester Hotel & Residences (Completion Works) - 201A22002/49
Certified Amount
Description | Previous Invoiced (AED) | This Application Value (AED) | Total Invoiced Net To Date (AED) | Previous Invoiced (AED) | This Application Value (AED) | Total Invoiced Net To Date (AED)
Contract Ref 201A22002/49
Scope Of Work | 188189.03 | 218786.89 | 406975.92 | 188189.03 | 216776.42 | 404965.45
Varitaions | 411568.56 | 206348.08 | 617916.64 | 411568.56 | 183489.3415 | 595057.9015
Dayworks | 2870 | 307.5 | 3177.5 | 2870 | 307.5 | 3177.5
Total | 602627.59 | 425442.47 | 1028070.06 | 602627.59 | 400573.2615 | 1003200.8515
AED : Four Hundred Twenty-Five Thousand Four Hundred Forty-Two and Forty-Seven Fils Only
(for Client use only) | Authorised Signatory
Technical Access Services LLC
The above amount is not inclusive of VAT

## Evaluation
Invoice Schedule
Khansaheb Civil Engineering LLC
Application No.: | 4
Project Name: | Dorchester Hotel & Residences (Completion Works)
Order Reference: | 201A22002/49
As On Date: | 2022-12-25
Billing Reference | Location | Tag No. | HOC | OHC | Description | Founding Level | Scaffold Type | Number | Length | Width | Height | Board Lift | Unit of Measure | Quantity | HOC Date | OHC Date | Erection % | Hire % | Dismantle % | Hire Weeks | E&D Rate per unit | Hire Rate per week | Erect Charges | Hire Charges | Dismantle Charges | Until WA Approved Only Approved this % | Total Amount | Previous Amount | Net Amount | Remarks | Total Amount
E11/K149/SK/dm/257 | HOTEL | 1 | 74602 |  | Level-28/29 Block & Glass Work | Level 28-29 | Design-1399-02 rev-D | 1 |  |  |  |  | unit | 1 | 2022-09-26 |  | 100% | 100% | 0% | 13 | 50703.26 | 2807 | 35492.28 | 36491 | 0 | 100% | 71983.28 | 59953.28 | 12030 | Tas Quote-2439-4-3 rev1 | 71983.28 | 0 | 0%
E11/K149/SK/dm/216 | RESIDENCE |  |  |  | Hire of Aluminium Tower | NA | NA | 1 |  |  |  |  | unit | 1 | 2022-09-15 | 2022-10-01 | 0% | 100% | 0% | 2.4286 | 0 | 200 | 0 | 485.71 | 0 | 100% | 485.71 | 485.71 | 0 | TAS/HIRE/4969/SM | 485.71 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE |  |  |  | Contract Scope - Progressive Billing |  |  | 1 |  |  |  |  | unit | 1 | 2022-09-20 | 2022-11-25 | 95% | 95% | 0% | 9.5714 | 191160 | 6716 | 0 | 0 | 0 |  | 0 | 188189.03 | -188189.03 |  | 0 | 0
CONTRACT - 201A22002/49 | RESIDENCE |  |  |  | Contract Scope - Progressive Billing |  |  | 1 |  |  |  |  | unit | 1 | 2022-09-20 |  | 100% | 0% | 0% | 13.8571 | 256226.3674 |  | 179358.46 | 0 | 0 | 100% | 179358.46 |  | 179358.46 | Tas Quote -2439-2-2 rev1 | 179856 | 497.54 | 0.2766%
CONTRACT - 201A22002/49 | RESIDENCE |  |  |  | Item - 9,10,11,12 |  |  | 1 |  |  |  |  | unit | 1 | 2022-09-20 |  | 100% | 0% | 0% | 13.8571 | 80440 |  | 56308 | 0 | 0 | 100% | 56308 |  | 56308 | Tas Quote -2439-2-2 rev1 | 56308 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 1 | 74652 |  | Glass Work | 29 to 31 | Design-1399-01 rev-G | 1 | 34.2 | 1.3 | 5 | 1 | m2-LxH | 171 | 2022-09-20 |  | 0% | 100% | 0% | 13.8571 | 0 | 0.49 | 0 | 1161.09 | 0 | 100% | 1161.09 |  | 1161.09 | Tas Quote -2439-2-2 rev1 | 1161.09 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 1 | 74652 |  | Glass Work | 29 to 31 | Design-1399-01 rev-G | 1 | 25.2 | 1.8 | 10.5 | 5 | m2-LxH | 264.6 | 2022-09-20 |  | 0% | 100% | 0% | 13.8571 | 0 | 0.77 | 0 | 2823.28 | 0 | 100% | 2823.28 |  | 2823.28 | Tas Quote -2439-2-2 rev1 | 2823.28 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 1 | 74652 |  | Glass Work | 29 to 31 | Design-1399-01 rev-G | 4 | 25.2 | 1.8 | 1 | 4 | m2-LxW | 181.44 | 2022-09-20 |  | 0% | 100% | 0% | 13.8571 | 0 | 0.7 | 0 | 1759.97 | 0 | 100% | 1759.97 |  | 1759.97 | Tas Quote -2439-2-2 rev1 | 1759.97 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 1 | 74652 |  | Glass Work | 29 to 31 | Design-1399-01 rev-G | 1 | 7.2 | 1.8 | 15.5 | 1 | m2-LxH | 111.6 | 2022-09-20 |  | 0% | 100% | 0% | 13.8571 | 0 | 0.77 | 0 | 1190.77 | 0 | 100% | 1190.77 |  | 1190.77 | Tas Quote -2439-2-2 rev1 | 1190.77 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 1 | 74652 |  | Glass Work | 29 to 31 | Design-1399-01 rev-G | 1 | 14.4 | 1.8 | 4.2 | 1 | m2-LxH | 60.48 | 2022-09-20 |  | 0% | 100% | 0% | 13.8571 | 0 | 0.77 | 0 | 645.32 | 0 | 100% | 645.32 |  | 645.32 | Tas Quote -2439-2-2 rev1 | 645.32 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 1 | 74652 |  | Glass Work | 29 to 31 | Design-1399-01 rev-G | 1 | 14.4 | 1.8 | 6 | 2 | m2-LxH | 86.4 | 2022-09-20 |  | 0% | 100% | 0% | 13.8571 | 0 | 0.77 | 0 | 921.89 | 0 | 100% | 921.89 |  | 921.89 | Tas Quote -2439-2-2 rev1 | 921.89 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 1 | 74652 |  | Glass Work | 29 to 31 | Design-1399-01 rev-G | 1 | 14.4 | 1.8 | 1 | 1 | m2-LxW | 25.92 | 2022-09-20 |  | 0% | 100% | 0% | 13.8571 | 0 | 0.7 | 0 | 251.42 | 0 | 100% | 251.42 |  | 251.42 | Tas Quote -2439-2-2 rev1 | 251.42 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 1g | 74656 |  | Glass Work | 29 to 31 | Design-1399-01 rev-G | 1 | 9 | 1.8 | 10.5 | 1 | m2-LxH | 94.5 | 2022-09-21 |  | 0% | 100% | 0% | 13.7143 | 0 | 0.77 | 0 | 997.92 | 0 | 100% | 997.92 |  | 997.92 | Tas Quote -2439-2-2 rev1 | 997.92 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 1m | 74674 |  | Glass Work | 29 to 31 | Design-1399-01 rev-G | 1 | 23.4 | 2.75 | 1 | 1 | m2-LxW | 64.35 | 2022-10-01 |  | 0% | 100% | 0% | 12.2857 | 0 | 6.72 | 0 | 5312.74 | 0 | 100% | 5312.74 |  | 5312.74 | Tas Quote -2439-2-2 rev1 | 5312.74 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 1u | 79101 |  | Glass Work | 29 to 31 | Design-1399-01 rev-G | 1 | 20 | 2.75 | 1 | 1 | m2-LxW | 55 | 2022-12-06 |  | 0% | 100% | 0% | 2.8571 | 0 | 6.72 | 0 | 1056 | 0 | 100% | 1056 |  | 1056 | Tas Quote -2439-2-2 rev1 | 1056 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 8w | 79146 |  | Glass Work | 29 to 31 | Design-1399-01 rev-G | 1 | 6 | 2.5 | 1 | 1 | m2-LxW | 15 | 2022-12-15 |  | 0% | 100% | 0% | 1.5714 | 0 | 6.72 | 0 | 158.4 | 0 | 100% | 158.4 |  | 158.4 | Tas Quote -2439-2-2 rev1 | 158.4 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 1 | 74652 |  | Glass Work | 29 to 31 | H20 Beam - Bottom | 1 | 50.4 | 1.3 | 1 |  | m3 | 65.52 | 2022-09-20 |  | 0% | 100% | 0% | 13.8571 | 0 | 10.15 | 0 | 9215.39 | 0 | 100% | 9215.39 |  | 9215.39 | Tas Quote -2439-2-2 rev1 | 9215.39 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 1 | 74652 |  | Glass Work | 29 to 31 | Hilti | 1 | 224 | 1 | 1 |  | lm | 224 | 2022-09-20 |  | 0% | 100% | 0% | 13.8571 | 0 | 17.15 | 0 | 53233.6 | 0 | 100% | 53233.6 |  | 53233.6 | Tas Quote -2439-2-2 rev1 | 53233.6 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 3d | 79109 |  | Glass Work | 31to32 | Design-1399-03 | 1 | 20 | 2.75 | 1 | 1 | m2-LxW | 55 | 2022-12-07 |  | 0% | 100% | 0% | 2.7143 | 0 | 6.72 | 0 | 1003.2 | 0 | 100% | 1003.2 |  | 1003.2 | Tas Quote -2439-2-2 rev1 | 1003.2 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 2h | 79158 |  | Glass Work | 31 | Design-1399-03 | 1 | 5 | 2.75 | 1 | 1 | m2-LxW | 13.75 | 2022-12-16 |  | 0% | 100% | 0% | 1.4286 | 0 | 6.72 | 0 | 132 | 0 | 100% | 132 |  | 132 | Tas Quote -2439-2-2 rev1 | 132 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 3f | 79143 |  | Glass Work | 31 | Design-1399-03 | 1 | 12 | 2.75 | 1 | 1 | m2-LxW | 33 | 2022-12-14 |  | 0% | 100% | 0% | 1.7143 | 0 | 6.72 | 0 | 380.16 | 0 | 100% | 380.16 |  | 380.16 | Tas Quote -2439-2-2 rev1 | 380.16 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 3d | 79109 |  | Glass Work | 31to32 | Design-1399-03 | 1 | 12 | 5 | 1 | 1 | m2-LxW | 60 | 2022-12-07 |  | 0% | 100% | 0% | 2.7143 | 0 | 12.25 | 0 | 1995 | 0 | 100% | 1995 |  | 1995 | Tas Quote -2439-2-2 rev1 | 1995 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 3f | 79143 |  | Glass Work | 31 | Design-1399-03 | 1 | 12 | 2.75 | 1 | 1 | m2-LxW | 33 | 2022-12-14 |  | 0% | 100% | 0% | 1.7143 | 0 | 8.61 | 0 | 487.08 | 0 | 100% | 487.08 |  | 487.08 | Tas Quote -2439-2-2 rev1 | 568.26 | 81.18 | 14.29%
CONTRACT - 201A22002/49 | RESIDENCE |  |  |  | Glass Work | 31 | Sheeting-22 | 1 | 52 | 1 | 1 |  | m2-LxH | 52 | 2022-12-14 |  | 0% | 100% | 0% | 1.7143 | 0 | 0 | 0 | 0 | 0 | 100% | 0 |  | 0 | Tas Quote -2439-2-2 rev1 | 0 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 8 | 77651 |  | Glass Work | Level 26 | Design-1399-04 | 1 | 6.8 | 1.8 | 4 | 1 | m2-LxH | 27.2 | 2022-10-10 |  | 0% | 100% | 0% | 11 | 0 | 0.77 | 0 | 230.38 | 0 | 100% | 230.38 |  | 230.38 | Tas Quote -2439-2-2 rev1 | 230.38 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 8a | 77651 |  | Glass Work | Level 26 to 31 | Design-1399-04 | 1 | 23.4 | 3.6 | 24 | 1 | m3 | 2021.76 | 2022-10-10 |  | 0% | 100% | 0% | 11 | 0 | 0.49 | 0 | 10897.29 | 0 | 100% | 10897.29 |  | 10897.29 | Tas Quote -2439-2-2 rev1 | 10897.29 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 8b | 77651 |  | Glass Work | Level 26 | Design-1399-04 | 1 | 18.6 | 0.6 | 4 | 1 | m2-LxH | 74.4 | 2022-10-10 |  | 0% | 100% | 0% | 11 | 0 | 0.49 | 0 | 401.02 | 0 | 100% | 401.02 |  | 401.02 | Tas Quote -2439-2-2 rev1 | 401.02 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 8c | 77651 |  | Glass Work | Level 26 | Design-1399-04 | 1 | 10.8 | 0.6 | 4 | 1 | m2-LxH | 43.2 | 2022-10-10 |  | 0% | 100% | 0% | 11 | 0 | 0.49 | 0 | 232.85 | 0 | 100% | 232.85 |  | 232.85 | Tas Quote -2439-2-2 rev1 | 232.85 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 8d | 77651 |  | Glass Work | Level 26 | Design-1399-04 | 1 | 6.8 | 0.9 | 4 | 1 | m2-LxH | 27.2 | 2022-10-10 |  | 0% | 100% | 0% | 11 | 0 | 0.49 | 0 | 146.61 | 0 | 100% | 146.61 |  | 146.61 | Tas Quote -2439-2-2 rev1 | 146.61 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 8e | 77651 |  | Glass Work | Level 26 to 31 | Design-1399-04 | 6 | 23.4 | 0.5 | 1 | 6 | m2-LxW | 70.2 | 2022-10-10 |  | 0% | 100% | 0% | 11 | 0 | 1.05 | 0 | 810.81 | 0 | 100% | 810.81 |  | 810.81 | Tas Quote -2439-2-2 rev1 | 810.81 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 8f | 77651 |  | Glass Work | Level 26 to 31 | Design-1399-04 | 5 | 23.4 | 1.8 | 1 | 5 | m2-LxW | 210.6 | 2022-10-10 |  | 0% | 100% | 0% | 11 | 0 | 0.7 | 0 | 1621.62 | 0 | 100% | 1621.62 |  | 1621.62 | Tas Quote -2439-2-2 rev1 | 1621.62 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 8g | 77651 |  | Glass Work | Level 26 | Design-1399-04 | 1 | 22.5 | 2.5 | 9 |  | m3 | 506.25 | 2022-10-10 |  | 0% | 100% | 0% | 11 | 0 | 0.35 | 0 | 1949.06 | 0 | 100% | 1949.06 |  | 1949.06 | Tas Quote -2439-2-2 rev1 | 1949.06 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 1p | 77528 |  | Glass Work | Level 3 to 31 | Design-1399-04 | 1 | 5 | 1.8 | 8.8 | 1 | m2-LxH | 44 | 2022-11-23 |  | 0% | 100% | 0% | 4.7143 | 0 | 0.77 | 0 | 159.72 | 0 | 100% | 159.72 |  | 159.72 | Tas Quote -2439-2-2 rev1 | 159.72 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 1q | 77528 |  | Glass Work | Level 3 to 31 | Design-1399-04 | 1 | 7 | 2.75 | 1 | 1 | m2-LxW | 19.25 | 2022-11-23 |  | 0% | 100% | 0% | 4.7143 | 0 | 6.72 | 0 | 609.84 | 0 | 100% | 609.84 |  | 609.84 | Tas Quote -2439-2-2 rev1 | 609.84 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 8 | 77651 |  | Glass Work | Level 26 | Design-1399-04 | 1 | 152.4 | 1 | 1 |  | lm | 152.4 | 2022-10-10 |  | 0% | 100% | 0% | 11 | 0 | 1.4 | 0 | 2346.96 | 0 | 100% | 2346.96 |  | 2346.96 | Tas Quote -2439-2-2 rev1 | 2346.96 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 8 | 77651 |  | Glass Work | Level 26 | Sheeting | 1 | 280.8 | 1 | 1 |  | m2-LxH | 280.8 | 2022-10-10 |  | 0% | 100% | 0% | 11 | 0 | 0 | 0 | 0 | 0 | 100% | 0 |  | 0 | Tas Quote -2439-2-2 rev1 | 0 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 8 | 77651 |  | Glass Work | Level 26 | Hilti | 1 | 80 | 1 | 1 |  | lm | 80 | 2022-10-10 |  | 0% | 100% | 0% | 11 | 0 | 17.15 | 0 | 15092 | 0 | 100% | 15092 |  | 15092 | Tas Quote -2439-2-2 rev1 | 15092 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 8l | 77660 |  | Glass Lifting Frame | Level 26 | Design-1399-04 | 1 | 6 | 1 | 1 |  | lm | 6 | 2022-10-10 |  | 0% | 100% | 0% | 11 | 0 | 1.4 | 0 | 92.4 | 0 | 100% | 92.4 |  | 92.4 | Tas Quote -2439-2-2 rev1 | 92.4 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 2 | 74661 |  | Ceiling Work | Level 30 | Design -1399-05 | 1 | 21.1 | 9 | 9.2 | 1 | m3 | 1747.08 | 2022-09-22 |  | 0% | 100% | 0% | 13.5714 | 0 | 0.49 | 0 | 11618.08 | 0 | 100% | 11618.08 |  | 11618.08 | Tas Quote -2439-2-2 rev1 | 11618.08 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 3 | 74667 |  | Ceiling Work | Level 29 | Design -1399-05 | 1 | 22.9 | 3.4 | 14 | 1 | m3 | 1090.04 | 2022-09-27 |  | 0% | 100% | 0% | 12.8571 | 0 | 0.49 | 0 | 6867.25 | 0 | 100% | 6867.25 |  | 6867.25 | Tas Quote -2439-2-2 rev1 | 6867.25 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 3 | 74667 |  | Ceiling Work | Level 30 | Design -1399-05 | 1 | 22.9 | 7.2 | 7.5 | 1 | m3 | 1236.6 | 2022-09-27 |  | 0% | 100% | 0% | 12.8571 | 0 | 0.49 | 0 | 7790.58 | 0 | 100% | 7790.58 |  | 7790.58 | Tas Quote -2439-2-2 rev1 | 7790.58 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 3 | 74667 |  | Ceiling Work | Level 30 | Design -1399-05 | 1 | 72 | 1 | 1 |  | lm | 72 | 2022-09-27 |  | 0% | 100% | 0% | 12.8571 | 0 | 1.4 | 0 | 1296 | 0 | 100% | 1296 |  | 1296 | Tas Quote -2439-2-2 rev1 | 2073.6 | 777.6 | 37.5%
CONTRACT - 201A22002/49 | RESIDENCE | 3 | 74667 |  | Ceiling Work | Level 30 | H20 Beam - Bottom | 1 | 22.9 | 2.4 | 1 |  | m3 | 54.96 | 2022-09-27 |  | 0% | 100% | 0% | 12.8571 | 0 | 10.15 | 0 | 7172.28 | 0 | 100% | 7172.28 |  | 7172.28 | Tas Quote -2439-2-2 rev1 | 7172.28 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 10 | 74681 |  | Back Propping | Level 28 | Design - 1399-15 | 1 | 24.7 | 1.3 | 4.2 | 1 | m2-LxH | 103.74 | 2022-10-12 |  | 0% | 100% | 0% | 10.7143 | 0 | 0.49 | 0 | 544.64 | 0 | 100% | 544.64 |  | 544.64 | Tas Quote -2439-2-2 rev1 | 778.05 | 233.41 | 30%
CONTRACT - 201A22002/49 | RESIDENCE | 10 | 74681 |  | Back Propping | Level 28 | H20 Beam - Bottom | 1 | 24.7 | 1.3 | 1 |  | m3 | 32.11 | 2022-10-12 |  | 0% | 100% | 0% | 10.7143 | 0 | 10.15 | 0 | 3491.96 | 0 | 100% | 3491.96 |  | 3491.96 | Tas Quote -2439-2-2 rev1 | 3491.96 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 9 | 74680 |  | Back Propping | Level 29 | Design -1399-16 | 1 | 18.8 | 3.6 | 4.7 |  | m3 | 318.1 | 2022-10-12 |  | 0% | 100% | 0% | 10.7143 | 0 | 0.49 | 0 | 1670.03 | 0 | 100% | 1670.03 |  | 1670.03 | Tas Quote -2439-2-2 rev1 | 1670.03 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 9 | 74680 |  | Back Propping | Level 29 | H20 Beam - Bottom | 1 | 18.8 | 3.6 | 1 |  | m3 | 67.68 | 2022-10-12 |  | 0% | 100% | 0% | 10.7143 | 0 | 10.15 | 0 | 7360.2 | 0 | 100% | 7360.2 |  | 7360.2 | Tas Quote -2439-2-2 rev1 | 7360.2 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 108 | 77542 |  | Canal side Balcony Back Propping | Level 27 to 28 | Design -1399-28 | 1 | 12.6 | 1.3 | 8.8 | 1 | m2-LxH | 110.88 | 2022-11-30 |  | 0% | 100% | 0% | 3.7143 | 0 | 0.49 | 0 | 201.8 | 0 | 100% | 201.8 |  | 201.8 | Tas Quote -2439-2-2 rev1 | 201.8 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 108 | 77542 |  | Canal side Balcony Back Propping | Level 27 to 28 | H20 Beam - Bottom | 1 | 12.6 | 1.3 | 1 |  | m3 | 16.38 | 2022-11-30 |  | 0% | 100% | 0% | 3.7143 | 0 | 10.15 | 0 | 617.53 | 0 | 100% | 617.53 |  | 617.53 | Tas Quote -2439-2-2 rev1 | 617.53 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 109&a | 77543 |  | Canal side Balcony Back Propping | Level 27 | Design -1399-28 | 1 | 3.6 | 1.8 | 3 |  | m2-LxH | 10.8 | 2022-11-30 |  | 0% | 100% | 0% | 3.7143 | 0 | 0.49 | 0 | 19.66 | 0 | 100% | 19.66 |  | 19.66 | Tas Quote -2439-2-2 rev1 | 19.66 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 109&a | 77542 |  | Canal side Balcony Back Propping | Level 27 | H20 Beam - Bottom | 1 | 3.6 | 1.3 | 1 |  | m3 | 4.68 | 2022-11-30 |  | 0% | 100% | 0% | 3.7143 | 0 | 10.15 | 0 | 176.44 | 0 | 0% | 0 |  | 0 | Tas Quote -2439-2-2 rev1 | 176.44 | 176.44 | 100%
CONTRACT - 201A22002/49 | RESIDENCE | 109&a | 77542 |  | Canal side Balcony Back Propping | Level 27 | H20 Beam - Bottom | 1 | 3.6 | 1.8 | 1 |  | m3 | 6.48 | 2022-11-30 |  | 0% | 100% | 0% | 3.7143 | 0 | 10.15 | 0 | 244.3 | 0 | 0% | 0 |  | 0 | Tas Quote -2439-2-2 rev1 | 244.3 | 244.3 | 100%
CONTRACT - 201A22002/49 | RESIDENCE | 3e | 79142 |  | Canopy Work | Level 31 | Design -1399 -19 | 1 | 11 | 3.5 | 1 | 1 | m2-LxW | 38.5 | 2022-12-14 |  | 0% | 100% | 0% | 1.7143 | 0 | 8.61 | 0 | 568.26 | 0 | 100% | 568.26 |  | 568.26 | Tas Quote -2439-2-2 rev1 | 568.26 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 3e | 79142 |  | Canopy Work | Level 31 | Design -1399 -19 | 6 | 10.8 | 1 | 1 |  | lm | 64.8 | 2022-12-14 |  | 0% | 100% | 0% | 1.7143 | 0 | 1.4 | 0 | 155.52 | 0 | 100% | 155.52 |  | 155.52 | Tas Quote -2439-2-2 rev1 | 155.52 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 3e | 79142 |  | Canopy Work | Level 31 | Design -1399 -19 | 12 | 6 | 1 | 1 |  | lm | 72 | 2022-12-14 |  | 0% | 100% | 0% | 1.7143 | 0 | 1.4 | 0 | 172.8 | 0 | 100% | 172.8 |  | 172.8 | Tas Quote -2439-2-2 rev1 | 172.8 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 3e | 79142 |  | Canopy Work | Level 31 | Design -1399 -19 | 1 | 8 | 2.6 | 1 |  | m2-LxW | 20.8 | 2022-12-14 |  | 0% | 100% | 0% | 1.7143 | 0 | 6.37 | 0 | 227.14 | 0 | 100% | 227.14 |  | 227.14 | Tas Quote -2439-2-2 rev1 | 227.14 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 3c | 79108 |  | Canopy Work | Level 31 to 32 | Design -1399 -19 | 6 | 10.8 | 1 | 1 |  | lm | 64.8 | 2022-12-07 |  | 0% | 100% | 0% | 2.7143 | 0 | 1.4 | 0 | 246.24 | 0 | 100% | 246.24 |  | 246.24 | Tas Quote -2439-2-2 rev1 | 246.24 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 3c | 79108 |  | Canopy Work | Level 31 to 32 | Design -1399 -19 | 1 | 8 | 5 | 1 |  | m2-LxW | 40 | 2022-12-07 |  | 0% | 100% | 0% | 2.7143 | 0 | 12.25 | 0 | 1330 | 0 | 100% | 1330 |  | 1330 | Tas Quote -2439-2-2 rev1 | 1330 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 3c | 79108 |  | Canopy Work | Level 31 to 32 | Design -1399 -19 | 12 | 6 | 1 | 1 |  | lm | 72 | 2022-12-07 |  | 0% | 100% | 0% | 2.7143 | 0 | 1.4 | 0 | 273.6 | 0 | 100% | 273.6 |  | 273.6 | Tas Quote -2439-2-2 rev1 | 273.6 | 0 | 0%
CONTRACT - 201A22002/49 | RESIDENCE | 3c | 79108 |  | Canopy Work | Level 31 to 32 | Design -1399 -19 | 1 | 8 | 2.6 | 1 |  | m2-LxW | 20.8 | 2022-12-07 |  | 0% | 100% | 0% | 2.7143 | 0 | 6.37 | 0 | 359.63 | 0 | 100% | 359.63 |  | 359.63 | Tas Quote -2439-2-2 rev1 | 359.63 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 1b | 74653 | 76751 | Glass Channel Fixing | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 25.2 | 1.2 | 1 | 1 | m2-LxW | 30.24 | 2022-09-20 | 2022-09-26 | 100% | 100% | 100% | 1 | 36.52 | 2.94 | 773.06 | 88.91 | 331.31 | 100% | 1193.28 | 1193.28 | 0 |  | 1193.28 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 1f | 74654 |  | Glass Channel Fixing | Level 29 | Cantilever (0 < 0.5m width) | 1 | 5 | 0.5 | 1 | 1 | m2-LxW | 2.5 | 2022-09-20 |  | 100% | 100% | 0% | 13.8571 | 32.75 | 1.05 | 57.31 | 36.38 | 0 | 100% | 93.69 | 82.44 | 11.25 |  | 93.69 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 1h | 74655 | 76752 | Glass Channel Fixing | Level 30 | Cantilever (0 < 0.5m width) | 1 | 16.2 | 0.5 | 1 | 1 | m2-LxW | 8.1 | 2022-09-21 | 2022-09-27 | 100% | 100% | 100% | 1 | 32.75 | 1.05 | 185.69 | 8.51 | 79.58 | 100% | 273.78 | 273.78 | 0 |  | 273.78 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 1i | 74660 | 76753 | Glass Channel Fixing | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 1.8 | 1 | 1 | 1 | m2-LxW | 1.8 | 2022-09-24 | 2022-09-26 | 100% | 100% | 100% | 0.42857 | 36.52 | 2.94 | 46.02 | 2.27 | 19.72 | 100% | 68.01 | 68.01 | 0 |  | 68.01 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 1j | 74666 | 76754 | Glass Channel Fixing | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 23.4 | 0.75 | 1 | 1 | m2-LxW | 17.55 | 2022-09-26 | 2022-09-28 | 100% | 100% | 100% | 0.42857 | 36.52 | 2.94 | 448.65 | 22.11 | 192.28 | 100% | 663.04 | 663.04 | 0 |  | 663.04 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 1k | 74670 |  | Glass Channel Fixing | Level 30 | Cantilever (0 < 0.5m width) | 2 | 9.8 | 0.5 | 1 | 1 | m2-LxW | 9.8 | 2022-09-28 |  | 100% | 100% | 0% | 12.7143 | 32.75 | 1.05 | 224.67 | 130.83 | 0 | 100% | 355.5 | 311.4 | 44.1 |  | 355.5 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 1l | 74671 |  | Glass Channel Fixing | Level 30 | Cantilever (0 < 0.5m width) | 1 | 13.8 | 0.5 | 1 | 1 | m2-LxW | 6.9 | 2022-09-28 |  | 100% | 100% | 0% | 12.7143 | 32.75 | 1.05 | 158.18 | 92.12 | 0 | 100% | 250.3 | 219.25 | 31.05 |  | 250.3 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 2a | 74662 |  | Glass Channel Fixing | Level 30 | Additional Boarding | 4 | 10.8 | 1.8 | 1 | 4 | m2-LxW | 77.76 | 2022-09-22 |  | 100% | 100% | 0% | 13.5714 | 6.63 | 0.7 | 360.88 | 738.72 | 0 | 100% | 1099.6 | 866.32 | 233.28 |  | 1099.6 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 2b | 74663 | 76758 | Colum G-3 Painting Works | Level 30 | Additional Boarding | 4 | 3.6 | 3.6 | 1 | 4 | m2-LxW | 51.84 | 2022-09-22 | 2022-10-15 | 100% | 100% | 100% | 3.4286 | 6.63 | 0.7 | 240.59 | 124.42 | 103.11 | 100% | 468.12 | 468.12 | 0 |  | 468.12 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 2c | 74664 | 76759 | Colum F-3 Painting Works | Level 30 | Additional Boarding | 4 | 3.6 | 3.6 | 1 | 4 | m2-LxW | 51.84 | 2022-09-22 | 2022-10-15 | 100% | 100% | 100% | 3.4286 | 6.63 | 0.7 | 240.59 | 124.42 | 103.11 | 100% | 468.12 | 468.12 | 0 |  | 468.12 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 2d | 74665 | 76760 | Colum D-3 Painting Works | Level 30 | Additional Boarding | 4 | 3.6 | 3.6 | 1 | 4 | m2-LxW | 51.84 | 2022-09-22 | 2022-10-15 | 100% | 100% | 100% | 3.4286 | 6.63 | 0.7 | 240.59 | 124.42 | 103.11 | 100% | 468.12 | 468.12 | 0 |  | 468.12 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 3a | 74668 | 76761 | Colum D-2 Painting Works | Level 29 | Additional Boarding | 6 | 3.5 | 3.5 | 1 | 6 | m2-LxW | 73.5 | 2022-09-27 | 2022-10-15 | 100% | 100% | 100% | 2.7143 | 6.63 | 0.7 | 341.11 | 139.65 | 146.19 | 100% | 626.95 | 626.95 | 0 |  | 626.95 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 3b | 74669 | 76762 | Colum F-G/2 Painting Works | Level 29 | Additional Boarding | 6 | 9 | 3.5 | 1 | 6 | m2-LxW | 189 | 2022-09-27 | 2022-10-15 | 100% | 100% | 100% | 2.7143 | 6.63 | 0.7 | 877.15 | 359.1 | 375.92 | 100% | 1612.17 | 1612.17 | 0 |  | 1612.17 | 0 | 0%
E11/K149/SK/dm/239 | RESIDENCE | 4 | 74673 | 76788 | EIFS Removel & Reinstate Works | Ramp | Design-1399-07 rev-B | 1 |  |  |  |  | unit | 1 | 2022-10-01 | 2022-11-05 | 100% | 100% | 100% | 5.1429 | 15626.48 | 625.97 | 10938.54 | 3219.27 | 4687.94 | 100% | 18845.75 | 18845.75 | 0 | Tas Quote - 2439-8-2 | 18845.75 | 0 | 0%
E11/K149/SK/dm/238 | RESIDENCE | 5 | 74675 | 76768 | Level -30 Lobby Room Shaft-09 | Level 30 | Design -1399-10 rev-A | 1 |  |  |  |  | unit | 1 | 2022-10-03 | 2022-10-22 | 100% | 100% | 100% | 2.8571 | 5727.13 | 317.71 | 4008.99 | 907.74 | 1718.14 | 100% | 6634.87 | 6634.87 | 0 | Tas Quote - 2439-5-1 | 6634.87 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 2e | 74676 | 76755 | Level - 30 Balcony Side Glass frame work | Level 30 | Additional Boarding | 1 | 3.6 | 1.8 | 1 | 1 | m2-LxW | 6.48 | 2022-10-04 | 2022-10-07 | 100% | 100% | 100% | 0.57143 | 6.63 | 0.7 | 30.07 | 2.59 | 12.89 | 100% | 45.55 | 45.55 | 0 |  | 45.55 | 0 | 0%
E11/K149/HN/dm/285 | RESIDENCE | 6 | 74677 |  | Loading Bay Above Planter Trench | Ground Level | Design -1399-12 rev-A | 1 |  |  |  |  | unit | 1 | 2022-10-10 |  | 100% | 100% | 0% | 11 | 4959.77 | 123.48 | 3471.84 | 1358.28 | 0 | 100% | 4830.12 | 4300.92 | 529.2 | Tas Quote - 2439-10-1 | 4830.12 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 7 | 74678 | 80573 | Level -4 Planter Box Soil Filling | Level 4 | Independent | 1 | 15 | 1.5 | 0.8 | 1 | m2-LxH | 12 | 2022-10-10 | 2022-12-16 | 100% | 100% | 100% | 9.7143 | 12.01 | 0.49 | 100.88 | 57.12 | 43.24 | 100% | 201.24 | 140.36 | 60.88 |  | 201.24 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 8h | 74679 | 76756 | Pool Area Glass work | Level 26 | Additional Boarding | 1 | 4 | 1 | 1 | 1 | m2-LxW | 4 | 2022-10-10 | 2022-10-11 | 100% | 100% | 100% | 0.28571 | 6.63 | 0.7 | 18.56 | 0.8 | 7.96 | 100% | 27.32 | 27.32 | 0 |  | 27.32 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 8i | 74682 |  | Level -30 Glass Frame work | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 19 | 0.75 | 1 | 1 | m2-LxW | 14.25 | 2022-10-12 |  | 100% | 100% | 0% | 10.7143 | 36.52 | 2.94 | 364.29 | 448.88 | 0 | 100% | 813.17 | 633.62 | 179.55 |  | 813.17 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 8j | 74683 | 76764 | Level -30 Glass Frame work | Level 30 | Cantilever (0 < 0.5m width) | 1 | 19.8 | 0.5 | 1 | 1 | m2-LxW | 9.9 | 2022-10-12 | 2022-10-21 | 100% | 100% | 100% | 1.4286 | 32.75 | 1.05 | 226.96 | 14.85 | 97.27 | 100% | 339.08 | 339.08 | 0 |  | 339.08 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 11 | 74684 | 76757 | Level -30 Shaft Mep Services | Level 30 | Independent | 1 | 3.6 | 1.2 | 2.5 | 1 | m2-LxH | 9 | 2022-10-13 | 2022-10-15 | 100% | 100% | 100% | 0.42857 | 12.01 | 0.49 | 75.66 | 1.89 | 32.43 | 100% | 109.98 | 109.98 | 0 |  | 109.98 | 0 | 0%
E11/K149/HN/dm/285 | RESIDENCE | 12 | 74685 |  | Loading Bay Above Planter Trench | Ground Level | Design -1399-12 rev-A | 1 |  |  |  |  | unit | 1 | 2022-10-14 |  | 100% | 100% | 0% | 10.4286 | 4959.77 | 123.48 | 3471.84 | 1287.72 | 0 | 100% | 4759.56 | 4230.36 | 529.2 | Tas Quote - 2439-10-1 | 4759.56 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 13 | 74686 | 80503 | Pool Plant Room (KMEP Work) | Level 3 | Independent | 1 | 7.3 | 1.3 | 1.7 | 1 | m2-LxH | 12.41 | 2022-10-14 | 2022-11-10 | 100% | 100% | 100% | 4 | 12.01 | 0.49 | 104.33 | 24.32 | 44.71 | 100% | 173.36 | 173.36 | 0 | KMEP | 173.36 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 14 | 74687 | 76763 | Colum Nut bolt Installation | Level 3 | Independent | 1 | 5.1 | 1.3 | 1.6 | 1 | m2-LxH | 8.16 | 2022-10-15 | 2022-10-17 | 100% | 100% | 100% | 0.42857 | 12.01 | 0.49 | 68.6 | 1.71 | 29.4 | 100% | 99.71 | 99.71 | 0 |  | 99.71 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 15 | 74688 | 80504 | Pool Plant Room (KMEP Work) | Level 3 | Independent | 1 | 5 | 1.2 | 2 | 1 | m2-LxH | 10 | 2022-10-17 | 2022-11-10 | 100% | 100% | 100% | 3.5714 | 12.01 | 0.49 | 84.07 | 17.5 | 36.03 | 100% | 137.6 | 137.6 | 0 | KMEP | 137.6 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 16 | 74689 | 76766 | Shaft -6 Kmep Duct Extension | Level 31 | Tower | 1 | 2.5 | 1.8 | 2.3 | 1 | rm | 2.3 | 2022-10-17 | 2022-10-22 | 100% | 100% | 100% | 0.85714 | 63.34 | 7.28 | 101.98 | 14.35 | 43.7 | 100% | 160.03 | 160.03 | 0 | KMEP | 160.03 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 16 | 74689 | 76766 | Shaft -6 Kmep Duct Extension | Level 31 | Additional Boarding | 1 | 2.5 | 1.8 | 1 | 1 | m2-LxW | 4.5 | 2022-10-17 | 2022-10-22 | 100% | 100% | 100% | 0.85714 | 6.63 | 0.7 | 20.88 | 2.7 | 8.95 | 100% | 32.53 | 32.53 | 0 | KMEP | 32.53 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 17 | 74690 | 76769 | Level -2 Retail Unit 34 For (Kmep) | Level 2 | Birdcage | 1 | 17.5 | 10 | 6.2 | 1 | m3 | 1085 | 2022-10-18 | 2022-10-26 | 100% | 100% | 100% | 1.2857 | 7.08 | 0.49 | 5377.26 | 683.55 | 2304.54 | 100% | 8365.35 | 8365.35 | 0 | KMEP | 8365.35 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 18 | 74691 | 80506 | Basement 1 (Kmep work) | Basement 1 | Tower | 1 | 1.8 | 1.3 | 2.5 | 1 | rm | 2.5 | 2022-10-18 | 2022-11-12 | 100% | 100% | 100% | 3.7143 | 63.34 | 7.28 | 110.85 | 67.6 | 47.51 | 100% | 225.96 | 225.96 | 0 | KMEP | 225.96 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 19 | 74692 | 80535 | Staircase -4 For Water coring tank work | Level 31 | Independent | 1 | 4 | 1.3 | 6.3 | 1 | m2-LxH | 25.2 | 2022-10-18 | 2022-11-28 | 100% | 100% | 100% | 6 | 12.01 | 0.49 | 211.86 | 74.09 | 90.8 | 100% | 376.75 | 280.66 | 96.09 |  | 376.75 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 19a | 74700 | 76793 | Staircase -4 For Water coring tank work | Level 31 | Independent | 1 | 4 | 1.3 | 2 | 1 | m2-LxH | 8 | 2022-10-19 | 2022-11-05 | 100% | 100% | 100% | 2.5714 | 12.01 | 0.49 | 67.26 | 10.08 | 28.82 | 100% | 106.16 | 106.16 | 0 |  | 106.16 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 20 | 74693 | 80515 | Basement 1 (Kmep work) | Basement 1 | Tower | 1 | 2.5 | 2.5 | 3 | 1 | rm | 3 | 2022-10-18 | 2022-11-15 | 100% | 100% | 100% | 4.1429 | 63.34 | 7.28 | 133.01 | 90.48 | 57.01 | 100% | 280.5 | 280.5 | 0 |  | 280.5 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 16a | 74694 | 76767 | Second Lift Duct Extension work | Level 31 | Tower | 1 | 2.5 | 1.8 | 2 | 1 | rm | 2 | 2022-10-19 | 2022-10-22 | 100% | 100% | 100% | 0.57143 | 63.34 | 7.28 | 88.68 | 8.32 | 38 | 100% | 135 | 135 | 0 |  | 135 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 1n | 74695 | 76771 | Fire Fifhting Sprinkler Work | Level 31 | Additional Boarding | 1 | 11.5 | 1.8 | 1 | 1 | m2-LxW | 20.7 | 2022-10-19 | 2022-10-26 | 100% | 100% | 100% | 1.1429 | 6.63 | 0.7 | 96.07 | 16.56 | 41.17 | 100% | 153.8 | 153.8 | 0 |  | 153.8 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 21 | 74696 | 76792 | Basement 1 (Kmep work) | Basement 1 | Tower | 1 | 2.5 | 1.8 | 3 | 1 | rm | 3 | 2022-10-19 | 2022-11-07 | 100% | 100% | 100% | 2.8571 | 63.34 | 7.28 | 133.01 | 62.4 | 57.01 | 100% | 252.42 | 252.42 | 0 | KMEP | 252.42 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 22 | 74697 | 76776 | Basement 1 (Kmep work) | Basement 1 | Independent | 1 | 3.1 | 1.3 | 3 | 1 | m2-LxH | 9.3 | 2022-10-19 | 2022-11-02 | 100% | 100% | 100% | 2.1429 | 12.01 | 0.49 | 78.19 | 9.77 | 33.51 | 100% | 121.47 | 121.47 | 0 | KMEP | 121.47 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 23 | 74698 | 80538 | Basement 1 (Kmep work) | Basement 1 | Independent 1.8m wide | 1 | 3.1 | 1.8 | 4.5 | 1 | m2-LxH | 13.95 | 2022-10-19 | 2022-11-26 | 100% | 100% | 100% | 5.5714 | 12.01 | 0.77 | 117.28 | 59.85 | 50.26 | 100% | 227.39 | 175.59 | 51.8 | KMEP | 227.39 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 24 | 74699 | 80516 | Basement 1 (Kmep work) | Basement 1 | Tower | 1 | 2.5 | 2.5 | 4.5 | 1 | rm | 4.5 | 2022-10-19 | 2022-11-15 | 100% | 100% | 100% | 4 | 63.34 | 7.28 | 199.52 | 131.04 | 85.51 | 100% | 416.07 | 416.07 | 0 | KMEP | 416.07 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 25 | 77652 | 76777 | Basement 1 (Kmep work) | Basement 1 | Independent 1.8m wide | 1 | 3.8 | 2.5 | 4.5 | 1 | m2-LxH | 17.1 | 2022-10-19 | 2022-11-02 | 100% | 100% | 100% | 2.1429 | 16.76 | 0.77 | 200.62 | 28.22 | 85.98 | 100% | 314.82 | 314.82 | 0 | KMEP | 314.82 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 8k | 77653 | 76775 | Glass Channel Fixing | Level 31 | Cantilever (0 < 0.5m width) | 1 | 18 | 0.5 | 1 | 1 | m2-LxW | 9 | 2022-10-19 | 2022-10-29 | 100% | 100% | 100% | 1.5714 | 32.75 | 1.05 | 206.33 | 14.85 | 88.43 | 100% | 309.61 | 309.61 | 0 |  | 309.61 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 26 | 77654 | 80501 | Mockup For Bracket Fixing | Level 6 | Tower | 1 | 1.8 | 1 | 2 | 1 | rm | 2 | 2022-10-19 | 2022-11-04 | 100% | 100% | 100% | 2.4286 | 63.34 | 7.28 | 88.68 | 35.36 | 38 | 100% | 162.04 | 162.04 | 0 |  | 162.04 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 27 | 77655 | 80525 | Basement 1 (Kmep work) | Basement 1 | Independent | 1 | 5 | 1.3 | 4.5 | 1 | m2-LxH | 22.5 | 2022-10-19 | 2022-11-16 | 100% | 100% | 100% | 4.1429 | 12.01 | 0.49 | 189.16 | 45.68 | 81.07 | 100% | 315.91 | 315.91 | 0 | KMEP | 315.91 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 28 | 77656 | 80507 | Basement 1 (Kmep work) | Basement 1 | Tower | 1 | 2.5 | 1.8 | 4.5 | 1 | rm | 4.5 | 2022-10-20 | 2022-11-11 | 100% | 100% | 100% | 3.2857 | 63.34 | 7.28 | 199.52 | 107.64 | 85.51 | 100% | 392.67 | 392.67 | 0 | KMEP | 392.67 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 28 | 77656 | 80507 | Basement 1 (Kmep work) | Basement 1 | Additional Boarding | 1 | 2.5 | 1.8 |  | 1 | m2-LxW | 4.5 | 2022-10-20 | 2022-11-11 | 100% | 100% | 100% | 3.2857 | 6.63 | 0.7 | 20.88 | 10.35 | 8.95 | 100% | 40.18 | 40.18 | 0 | KMEP | 40.18 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 29 | 77657 | 80557 | Basement 1 (Kmep work) | Basement 1 | Tower | 1 | 2.5 | 1.8 | 4.5 | 1 | rm | 4.5 | 2022-10-20 | 2022-12-10 | 100% | 100% | 100% | 7.4286 | 63.34 | 7.28 | 199.52 | 243.36 | 85.51 | 100% | 528.39 | 372.68 | 155.71 | KMEP | 528.39 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 2g | 77661 | 76774 | Glass Fixing work | Level 30 | Cantilever (0 < 0.5m width) | 1 | 10.8 | 0.5 | 1 | 1 | m2-LxW | 5.4 | 2022-10-21 | 2022-10-29 | 100% | 100% | 100% | 1.2857 | 32.75 | 1.05 | 123.8 | 7.29 | 53.06 | 100% | 184.15 | 184.15 | 0 |  | 184.15 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 2f | 77662 |  | Glass Fixing work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 3.6 | 0.75 | 1 | 1 | m2-LxW | 2.7 | 2022-10-21 |  | 100% | 100% | 0% | 9.4286 | 36.52 | 2.94 | 69.02 | 74.84 | 0 | 100% | 143.86 | 109.84 | 34.02 |  | 143.86 | 0 | 0%
E11/K149/SK/dm/365 | RESIDENCE | 30 | 77667 |  | EIFS Fixing Work | Level 23 | Independent | 1 | 4 | 1.3 | 2 | 1 | unit | 1 | 2022-10-21 |  | 100% | 100% | 0% | 9.4286 | 916.08 | 3.92 | 641.26 | 36.96 | 0 | 100% | 678.22 | 661.42 | 16.8 | Tas Quote - 2439-14-1 (item-1) | 678.22 | 0 | 0%
E11/K149/SK/dm/365 | RESIDENCE | 30a | 77668 |  | EIFS Fixing Work | Level 23 | Independent | 1 | 8 | 1.3 | 3 | 2 | unit | 1 | 2022-10-21 |  | 100% | 100% | 0% | 9.4286 | 2093.27 | 22.96 | 1465.29 | 216.48 | 0 | 100% | 1681.77 | 1583.37 | 98.4 | Tas Quote - 2439-14-1 (item-2) | 1681.77 | 0 | 0%
E11/K149/SK/dm/350 | RESIDENCE | 31 | 77669 |  | Above Air Extract trench Loading Bay | Ground Level | Design 1399-14 | 1 | 22.5 | 3.6 |  | 1 | unit | 1 | 2022-10-21 |  | 100% | 100% | 0% | 9.4286 | 13343.06 | 660.1 | 9340.14 | 6223.8 | 0 | 100% | 15563.94 | 12734.94 | 2829 | Tas Quote - 2439-13-1 | 15563.94 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 32 | 77663 | 76779 | Hotel Side Block Work | Level 31 | Independent | 1 | 3.6 | 1.3 | 4 | 1 | m2-LxH | 14.4 | 2022-10-22 | 2022-11-03 | 100% | 100% | 100% | 1.8571 | 12.01 | 0.49 | 121.06 | 13.1 | 51.88 | 100% | 186.04 | 186.04 | 0 |  | 186.04 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 32 | 77663 | 76779 | Hotel Side Block Work | Level 31 | Additional Boarding | 1 | 3.6 | 1.3 | 1 | 1 | m2-LxW | 4.68 | 2022-10-22 | 2022-11-03 | 100% | 100% | 100% | 1.8571 | 6.63 | 0.7 | 21.72 | 6.08 | 9.31 | 100% | 37.11 | 37.11 | 0 |  | 37.11 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 33 | 77664 | 76772 | Canal Side wall Cladding opening Work | Level 14 | Tower | 1 | 1.8 | 1.3 | 1 | 1 | rm | 1 | 2022-10-22 | 2022-10-27 | 100% | 100% | 100% | 0.85714 | 63.34 | 7.28 | 44.34 | 6.24 | 19 | 100% | 69.58 | 69.58 | 0 |  | 69.58 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 34 | 77665 |  | Canal Side wall Cladding opening Work | Level 14 | Tower | 1 | 1.8 | 1.3 | 1 | 1 | rm | 1 | 2022-10-22 |  | 100% | 100% | 0% | 9.2857 | 63.34 | 7.28 | 44.34 | 67.6 | 0 | 100% | 111.94 | 80.74 | 31.2 |  | 111.94 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 4d | 77670 | 76786 | EIFS work | Ground Level to Level 2 | Additional Boarding | 3 | 1.8 | 1.8 | 1 | 3 | m2-LxW | 9.72 | 2022-10-25 | 2022-11-05 | 100% | 100% | 100% | 1.7143 | 6.63 | 0.7 | 45.11 | 11.66 | 19.33 | 100% | 76.1 | 76.1 | 0 |  | 76.1 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 2 | 74603 | 76828 | Plant Room Façade Fin Supporting work | Level 5 | Independent 1.8m wide | 1 | 4.9 | 1.8 | 4.2 | 1 | m2-LxH | 20.58 | 2022-10-04 | 2022-11-21 | 100% | 100% | 100% | 7 | 16.76 | 0.77 | 241.44 | 110.93 | 103.48 | 100% | 455.85 | 455.85 | 0 |  | 455.85 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 2a | 74604 |  | Plant Room Façade Fin Supporting work | Level 5 | Independent 1.8m wide | 1 | 15.1 | 1.8 | 4.2 | 1 | m2-LxH | 63.42 | 2022-10-05 |  | 100% | 100% | 0% | 11.7143 | 16.76 | 0.77 | 744.04 | 572.05 | 0 | 100% | 1316.09 | 1106.8 | 209.29 |  | 1316.09 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 2b | 74605 | 80819 | Plant Room For AC Duct Work | Level 5 | Additional Boarding | 1 | 6.8 | 1.8 | 1 | 1 | m2-LxW | 12.24 | 2022-10-05 | 2022-12-20 | 100% | 100% | 100% | 11 | 6.63 | 0.7 | 56.81 | 94.25 | 24.35 | 100% | 175.41 | 120.46 | 54.95 |  | 175.41 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 2c | 74606 | 80818 | Plant Room Façade Fin Supporting work | Level 5 | Cantilever (0.5 > 1.2m width) | 1 | 1 | 0.75 | 1 | 1 | m2-LxW | 0.75 | 2022-10-05 | 2022-12-20 | 100% | 100% | 100% | 11 | 36.52 | 2.94 | 19.17 | 24.26 | 8.22 | 100% | 51.65 | 35.55 | 16.1 |  | 51.65 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 3 | 74607 | 80820 | Plant Room Façade Fin Supporting work | Level 5 | Independent 1.8m wide | 1 | 7.5 | 1.8 | 4.2 | 1 | m2-LxH | 31.5 | 2022-10-05 | 2022-12-20 | 100% | 100% | 100% | 11 | 16.76 | 0.77 | 369.56 | 266.81 | 158.38 | 100% | 794.75 | 549.74 | 245.01 |  | 794.75 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 3a | 74608 | 80821 | Plant Room Façade Fin Supporting work | Level 5 | Cantilever (0 < 0.5m width) | 1 | 5 | 0.25 | 1 | 1 | m2-LxW | 1.25 | 2022-10-05 | 2022-12-20 | 100% | 100% | 100% | 11 | 32.75 | 1.05 | 28.66 | 14.44 | 12.28 | 100% | 55.38 | 38.41 | 16.97 |  | 55.38 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 4 | 74609 | 76802 | Air Extract Gratting Installation | Basement 1 | Independent | 1 | 9.3 | 1.3 | 5.9 | 1 | m2-LxH | 54.87 | 2022-10-07 | 2022-10-12 | 100% | 100% | 100% | 0.85714 | 12.01 | 0.49 | 461.29 | 23.05 | 197.7 | 100% | 682.04 | 682.04 | 0 |  | 682.04 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 4a | 74610 | 76803 | Air Extract Gratting Installation | Basement 1 | Cantilever (0 < 0.5m width) | 1 | 9.8 | 0.5 | 1 | 1 | m2-LxW | 4.9 | 2022-10-07 | 2022-10-12 | 100% | 100% | 100% | 0.85714 | 32.75 | 1.05 | 112.33 | 4.41 | 48.14 | 100% | 164.88 | 164.88 | 0 |  | 164.88 | 0 | 0%
E11/K149/SK/dm/300 | HOTEL | 5 | 74611 | 76801 | Cradle Beam Support | Roof | Design 1399-13 rev-A | 1 | 4 | 2.5 | 2 | 1 | unit | 1 | 2022-10-07 | 2022-10-10 | 100% | 100% | 100% | 0.57143 | 4033.1 | 49.28 | 2823.17 | 28.16 | 1209.93 | 100% | 4061.26 | 4061.26 | 0 | Tas Quote - 2439-11-2 | 4061.26 | 0 | 0%
E11/K149/SK/dm/300 | HOTEL | 6 | 74612 | 76804 | Cradle Beam Support (Re-erction) | Roof | Design 1399-13 rev-A | 1 | 4 | 2.5 | 2 | 1 | unit | 1 | 2022-10-10 | 2022-10-26 | 100% | 100% | 100% | 2.4286 | 4033.1 | 49.28 | 2823.17 | 119.68 | 1209.93 | 100% | 4152.78 | 4152.78 | 0 | Tas Quote - 2439-11-2 | 4152.78 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 7 | 74613 | 76807 | Planter Drain Connection (mep) | Basement 1 | Tower | 1 | 1.8 | 1.3 | 2.5 | 1 | rm | 2.5 | 2022-10-12 | 2022-11-03 | 100% | 100% | 100% | 3.2857 | 63.34 | 7.28 | 110.85 | 59.8 | 47.51 | 100% | 218.16 | 218.16 | 0 |  | 218.16 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 2d | 74614 | 80822 | Planter Room Fin Supportting work | Level 5 | Additional Boarding | 1 | 4.3 | 1.5 | 1 | 1 | m2-LxW | 6.45 | 2022-10-12 | 2022-12-20 | 100% | 100% | 100% | 10 | 6.63 | 0.7 | 29.93 | 45.15 | 12.83 | 100% | 87.91 | 58.96 | 28.95 |  | 87.91 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 3b | 74615 | 80823 | Planter Room Fin Supportting work | Level 5 | Independent 1.8m wide | 1 | 3 | 1.8 | 4.2 | 1 | m2-LxH | 12.6 | 2022-10-12 | 2022-12-20 | 100% | 100% | 100% | 10 | 16.76 | 0.77 | 147.82 | 97.02 | 63.35 | 100% | 308.19 | 210.19 | 98 |  | 308.19 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 3c | 74616 | 80824 | Planter Room Fin Supportting work | Level 5 | Independent | 1 | 5 | 1.3 | 4.2 | 1 | m2-LxH | 21 | 2022-10-12 | 2022-12-20 | 100% | 100% | 100% | 10 | 12.01 | 0.49 | 176.55 | 102.9 | 75.66 | 100% | 355.11 | 242.7 | 112.41 |  | 355.11 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 8 | 74617 | 80813 | Planter Room Fin Supportting work | Level 5 | Independent 1.8m wide | 1 | 10.8 | 1.8 | 3.8 | 1 | m2-LxH | 41.04 | 2022-10-13 | 2022-12-20 | 100% | 100% | 100% | 9.8571 | 16.76 | 0.77 | 481.48 | 311.49 | 206.35 | 100% | 999.32 | 680.11 | 319.21 |  | 999.32 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 8a | 74618 | 80814 | Planter Room Fin Supportting work | Level 5 | Cantilever (0 < 0.5m width) | 1 | 10.8 | 0.5 | 1 | 1 | m2-LxW | 5.4 | 2022-10-13 | 2022-12-20 | 100% | 100% | 100% | 9.8571 | 32.75 | 1.05 | 123.8 | 55.89 | 53.06 | 100% | 232.75 | 159.44 | 73.31 |  | 232.75 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 3d | 74619 | 80817 | Plant Room For Kmep Work | Level 5 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-10-15 | 2022-12-20 | 100% | 100% | 100% | 9.5714 | 36.52 | 2.94 | 38.35 | 42.21 | 16.43 | 100% | 96.99 | 64.81 | 32.18 | KMEP | 96.99 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 8b | 74620 | 80815 | Plant Room For Kmep Work | Level 5 | Tower | 1 | 2.5 | 1.8 | 3.5 | 1 | rm | 3.5 | 2022-10-15 | 2022-12-20 | 100% | 100% | 100% | 9.5714 | 63.34 | 7.28 | 155.18 | 243.88 | 66.51 | 100% | 465.57 | 308.06 | 157.51 | KMEP | 465.57 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 8c | 74621 | 80816 | Plant Room For Kmep Work | Level 5 | Cantilever (0 < 0.5m width) | 1 | 4.8 | 0.5 | 1 | 1 | m2-LxW | 2.4 | 2022-10-15 | 2022-12-20 | 100% | 100% | 100% | 9.5714 | 32.75 | 1.05 | 55.02 | 24.12 | 23.58 | 100% | 102.72 | 70.14 | 32.58 | KMEP | 102.72 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 9 | 74622 | 80825 | Plant Room For Kmep Work | Level 5 | Independent | 1 | 4.5 | 1.5 | 2.3 | 1 | m2-LxH | 10.35 | 2022-10-15 | 2022-12-20 | 100% | 100% | 100% | 9.5714 | 12.01 | 0.49 | 87.01 | 48.54 | 37.29 | 100% | 172.84 | 117.44 | 55.4 | KMEP | 172.84 | 0 | 0%
E11/K149/SK/dm/259 | HOTEL | 10 | 74633 |  | Inverted Scaffold | Level 29 | Design 1399 -06 rev-B | 1 | 50 | 1.8 | 4 | 1 | lm | 50 | 2022-10-20 |  | 100% | 100% | 0% | 9.5714 | 1002.22 | 98.12 | 35077.7 | 46957.43 | 0 | 100% | 82035.13 | 61009.41 | 21025.72 | Tas Quote - 2439-6-1 | 82035.13 | 0 | 0%
E11/K149/SK/dm/341 | HOTEL | 11 | 74623 | 80803 | Balcony Floor Drain Work | Level 13 | Independent | 1 | 5.7 | 1.3 | 1.5 | 1 | unit | 1 | 2022-10-20 | 2022-12-15 | 100% | 100% | 100% | 8.1429 | 1368.99 | 6.17 | 958.29 | 50.24 | 410.7 | 100% | 1419.23 | 990.9 | 428.33 | Tas Quote - 2439-12-2 (item-2) | 1419.23 | 0 | 0%
E11/K149/SK/dm/341 | HOTEL | 12 | 74625 | 80834 | Balcony Floor Drain Work | Level 12 | Independent | 1 | 5.7 | 1.3 | 1.5 | 1 | unit | 1 | 2022-10-20 | 2022-12-21 | 100% | 100% | 100% | 9 | 1368.99 | 6.17 | 958.29 | 55.53 | 410.7 | 100% | 1424.52 | 990.9 | 433.62 | Tas Quote - 2439-12-2 (item-2) | 1424.52 | 0 | 0%
E11/K149/SK/dm/341 | HOTEL | 13 | 74624 | 80809 | Balcony Floor Drain Work | Level 14 | Independent | 1 | 5.7 | 1.3 | 1.5 | 1 | unit | 1 | 2022-10-21 | 2022-12-17 | 100% | 100% | 100% | 8.2857 | 1368.99 | 6.17 | 958.29 | 51.12 | 410.7 | 100% | 1420.11 | 990.02 | 430.09 | Tas Quote - 2439-12-2 (item-2) | 1420.11 | 0 | 0%
E11/K149/SK/dm/341 | HOTEL | 14 | 74626 | 80804 | Balcony Floor Drain Work | Level 15 | Independent | 1 | 5.7 | 1.3 | 1.5 | 1 | unit | 1 | 2022-10-21 | 2022-12-15 | 100% | 100% | 100% | 8 | 1368.99 | 6.17 | 958.29 | 49.36 | 410.7 | 100% | 1418.35 | 990.02 | 428.33 | Tas Quote - 2439-12-2 (item-2) | 1418.35 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 10a | 74635 | 76805 | Trench Inside for Parapet Cutting | Level 29 | Additional Boarding | 1 | 50 | 1 | 1 | 1 | m2-LxW | 50 | 2022-10-20 | 2022-10-31 | 100% | 100% | 100% | 1.7143 | 6.63 | 0.7 | 232.05 | 60 | 99.45 | 100% | 391.5 | 391.5 | 0 |  | 391.5 | 0 | 0%
E11/K149/SK/dm/259 | HOTEL | 15 | 74634 |  | Inverted Scaffold | Level 29 | Design 1399 -06 rev-B | 1 | 33 | 1.8 | 4 | 1 | lm | 33 | 2022-10-22 |  | 100% | 100% | 0% | 9.2857 | 1002.22 | 98.12 | 23151.28 | 30066.77 | 0 | 100% | 53218.05 | 39341.08 | 13876.97 | Tas Quote - 2439-6-1 | 53218.05 | 0 | 0%
E11/K149/SK/dm/259 | HOTEL | 15 | 74634 |  | Inverted Scaffold | Level 29 | Third Party Inspection ( Additional) | 1 |  |  |  |  | unit | 1 | 2022-10-22 | 2022-10-22 | 100% | 100% | 100% | 0.14286 | 1230 | 0 | 1230 | 0 | 0 | 100% | 1230 | 1230 | 0 | Additional Inspection | 1230 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 15a | 74636 | 76806 | Trench Inside for Parapet Cutting | Level 29 | Additional Boarding | 1 | 33 | 1 | 1 | 1 | m2-LxW | 33 | 2022-10-22 | 2022-11-01 | 100% | 100% | 100% | 1.5714 | 6.63 | 0.7 | 153.15 | 36.3 | 65.64 | 100% | 255.09 | 255.09 | 0 |  | 255.09 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 16 | 74627 | 76810 | EIFS work Damac side Elevation | Level 2 | Independent 1.8m wide | 1 | 6.8 | 1.8 | 8 | 1 | m2-LxH | 54.4 | 2022-10-24 | 2022-11-09 | 100% | 100% | 100% | 2.4286 | 16.76 | 0.77 | 638.22 | 101.73 | 273.52 | 100% | 1013.47 | 1013.47 | 0 |  | 1013.47 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 16a | 74628 | 76811 | EIFS work Damac side Elevation | Level 4 | Cantilever (0.5 > 1.2m width) | 1 | 6.8 | 1 | 1 | 1 | m2-LxW | 6.8 | 2022-10-24 | 2022-11-09 | 100% | 100% | 100% | 2.4286 | 36.52 | 2.94 | 173.84 | 48.55 | 74.5 | 100% | 296.89 | 296.89 | 0 |  | 296.89 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 16b | 74629 | 76812 | EIFS work Damac side Elevation | Level 2 | Butress | 1 | 2.5 | 1.8 | 5 |  | m3 | 22.5 | 2022-10-24 | 2022-11-09 | 100% | 100% | 100% | 2.4286 | 5.29 | 0.35 | 83.32 | 19.13 | 35.71 | 100% | 138.16 | 138.16 | 0 |  | 138.16 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 9a | 74630 | 80826 | Plant Room Kmep Work | Level 5 | Additional Boarding | 1 | 4.5 | 1 | 1 | 1 | m2-LxW | 4.5 | 2022-10-24 | 2022-12-20 | 100% | 100% | 100% | 8.2857 | 6.63 | 0.7 | 20.88 | 26.1 | 8.95 | 100% | 55.93 | 35.73 | 20.2 | KMEP | 55.93 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 9b | 74632 | 80827 | Plant Room Kmep Work | Level 5 | Additional Boarding | 1 | 2.5 | 0.75 | 1 | 1 | m2-LxW | 1.88 | 2022-10-24 | 2022-12-20 | 100% | 100% | 100% | 8.2857 | 6.63 | 0.7 | 8.73 | 10.9 | 3.74 | 100% | 23.37 | 14.93 | 8.44 | KMEP | 23.37 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 17 | 74637 | 80828 | Plant Room Kmep Work | Level 5 | Tower | 1 | 2.5 | 1.3 | 2.5 | 1 | rm | 2.5 | 2022-10-25 | 2022-12-20 | 100% | 100% | 100% | 8.1429 | 63.34 | 7.28 | 110.85 | 148.2 | 47.51 | 100% | 306.56 | 194.05 | 112.51 | KMEP | 306.56 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 17a | 74638 | 80829 | Plant Room Kmep Work | Level 5 | Cantilever (0 < 0.5m width) | 1 | 1.5 | 0.5 | 1 | 1 | m2-LxW | 0.75 | 2022-10-25 | 2022-12-20 | 100% | 100% | 100% | 8.1429 | 32.75 | 1.05 | 17.19 | 6.41 | 7.37 | 100% | 30.97 | 20.79 | 10.18 | KMEP | 30.97 | 0 | 0%
E11/K149/MS/dm/396 | RESIDENCE | 35 | 77666 | 80509 | Master Pump Room Work | Level 23 | Birdcage | 1 | 5 | 4.3 | 3 | 2 | unit | 1 | 2022-10-24 | 2022-11-12 | 100% | 100% | 100% | 2.8571 | 2391.43 | 57.19 | 1674 | 163.4 | 717.43 | 100% | 2554.83 | 2554.83 | 0 | Tas Quote - 2439-18-1 (item-1) | 2554.83 | 0 | 0%
E11/K149/HN/dm/285 | RESIDENCE | 36 | 77671 |  | Loading Bay Above Planter Trench | Ground Level | Design -1399-12 rev-A | 1 |  |  |  |  | unit | 1 | 2022-10-26 |  | 100% | 100% | 0% | 8.7143 | 4959.77 | 123.48 | 3471.84 | 1076.04 | 0 | 100% | 4547.88 | 4018.68 | 529.2 | Tas Quote - 2439-10-1 | 4547.88 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 8m | 77672 | 76773 | Glass Fixing work | Level 31 | Additional Boarding | 1 | 10.8 | 0.5 | 1 | 1 | m2-LxW | 5.4 | 2022-10-26 | 2022-10-28 | 100% | 100% | 100% | 0.42857 | 6.63 | 0.7 | 25.06 | 1.62 | 10.74 | 100% | 37.42 | 37.42 | 0 |  | 37.42 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 8n | 77673 |  | Glass Fixing work | Level 31 | Additional Boarding | 2 | 10.8 | 0.25 | 1 | 2 | m2-LxW | 5.4 | 2022-10-26 |  | 100% | 100% | 0% | 8.7143 | 6.63 | 0.7 | 25.06 | 32.94 | 0 | 100% | 58 | 41.8 | 16.2 |  | 58 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 37 | 77674 |  | Glass Fixing work | Level 7 | Tower | 1 | 2.5 | 1.3 | 1 | 1 | rm | 1 | 2022-10-28 |  | 100% | 100% | 0% | 8.4286 | 63.34 | 7.28 | 44.34 | 61.36 | 0 | 100% | 105.7 | 74.5 | 31.2 |  | 105.7 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 38 | 77675 | 76795 | Entrance Lobby Block Demolishing Work | Ground Level | Independent | 1 | 3.1 | 1.3 | 4.2 | 1 | m2-LxH | 13.02 | 2022-10-28 | 2022-11-04 | 100% | 100% | 100% | 1.1429 | 12.01 | 0.49 | 109.46 | 7.29 | 46.91 | 100% | 163.66 | 163.66 | 0 |  | 163.66 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 38 | 77675 | 76795 | Entrance Lobby Block Demolishing Work | Ground Level | Additional Boarding | 1 | 3.1 | 1.3 |  | 1 | m2-LxW | 4.03 | 2022-10-28 | 2022-11-04 | 100% | 100% | 100% | 1.1429 | 6.63 | 0.7 | 18.7 | 3.22 | 8.02 | 100% | 29.94 | 29.94 | 0 |  | 29.94 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 39 | 77676 |  | Existing Pipe Removal Work | Basement 1 | Birdcage | 1 | 3 | 3 | 5 | 1 | m3 | 45 | 2022-10-28 |  | 100% | 100% | 0% | 8.4286 | 7.08 | 0.49 | 223.02 | 185.85 | 0 | 100% | 408.87 | 314.37 | 94.5 |  | 408.87 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 40 | 77677 |  | Edge Protection | Level 31 | Double Handrail | 1 | 10 |  | 1 |  | lm | 10 | 2022-10-29 |  | 100% | 100% | 0% | 8.2857 | 12 | 0.7 | 84 | 58 | 0 | 100% | 142 | 112 | 30 |  | 142 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 8o | 77678 |  | Glass Fixing work | Level 30 | Cantilever (0 < 0.5m width) | 1 | 10.8 | 0.5 | 1 | 1 | m2-LxW | 5.4 | 2022-10-29 |  | 100% | 100% | 0% | 8.2857 | 32.75 | 1.05 | 123.8 | 46.98 | 0 | 100% | 170.78 | 146.48 | 24.3 |  | 170.78 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 41 | 77679 | 76796 | Block Demolishing Work | Ground Level | Independent | 1 | 5.4 | 1.3 | 4 | 1 | m2-LxH | 21.6 | 2022-10-29 | 2022-11-09 | 100% | 100% | 100% | 1.7143 | 12.01 | 0.49 | 181.59 | 18.14 | 77.82 | 100% | 277.55 | 277.55 | 0 |  | 277.55 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 41 | 77679 | 76796 | Block Demolishing Work | Ground Level | Additional Boarding | 1 | 5.4 | 1.3 | 1 | 1 | m2-LxW | 7.02 | 2022-10-29 | 2022-11-09 | 100% | 100% | 100% | 1.7143 | 6.63 | 0.7 | 32.58 | 8.42 | 13.96 | 100% | 54.96 | 54.96 | 0 |  | 54.96 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 41a | 77680 | 76785 | Block Demolishing Work | Ground Level | Cantilever (0 < 0.5m width) | 2 | 2 | 0.5 | 1 | 2 | m2-LxW | 2 | 2022-10-29 | 2022-11-03 | 100% | 100% | 100% | 0.85714 | 32.75 | 1.05 | 45.85 | 1.8 | 19.65 | 100% | 67.3 | 67.3 | 0 |  | 67.3 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 38a | 77681 | 76778 | Block Demolishing Work | Ground Level | Cantilever (0 < 0.5m width) | 2 | 2 | 0.5 | 1 | 2 | m2-LxW | 2 | 2022-10-29 | 2022-11-02 | 100% | 100% | 100% | 0.71429 | 32.75 | 1.05 | 45.85 | 1.5 | 19.65 | 100% | 67 | 67 | 0 |  | 67 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 39a | 77682 |  | Existing Pipe Removal Work | Basement 1 | Additional Boarding | 1 | 3 | 1.5 | 1 | 1 | m2-LxW | 4.5 | 2022-10-29 |  | 100% | 100% | 0% | 8.2857 | 6.63 | 0.7 | 20.88 | 26.1 | 0 | 100% | 46.98 | 33.48 | 13.5 |  | 46.98 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 32a | 77683 | 76780 | Block Work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-10-29 | 2022-11-03 | 100% | 100% | 100% | 0.85714 | 36.52 | 2.94 | 38.35 | 3.78 | 16.43 | 100% | 58.56 | 58.56 | 0 |  | 58.56 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 4i | 77686 | 76787 | EIFS Painting up to Groove | Ground Level | Tower | 1 | 1.8 | 0.9 | 12.3 | 1 | rm | 12.3 | 2022-10-29 | 2022-11-05 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 545.36 | 102.34 | 233.72 | 100% | 881.42 | 881.42 | 0 |  | 881.42 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 4i | 77686 | 76787 | EIFS Painting up to Groove | Ground Level | Additional Boarding | 5 | 1.8 | 0.9 | 1 | 5 | m2-LxW | 8.1 | 2022-10-29 | 2022-11-05 | 100% | 100% | 100% | 1.1429 | 6.63 | 0.7 | 37.59 | 6.48 | 16.11 | 100% | 60.18 | 60.18 | 0 |  | 60.18 | 0 | 0%
E11/K149/JJ/dm/377 | RESIDENCE | 42 | 77687 |  | Back Propping For Mast Climber | Basement 1 | Design - 1399-20 | 1 |  |  |  |  | unit | 1 | 2022-10-31 |  | 100% | 100% | 0% | 8 | 7695.22 | 511.06 | 5386.65 | 4088.48 | 0 | 100% | 9475.13 | 7284.87 | 2190.26 | Tas Quote 2439-16-3 (item-1) | 9475.13 | 0 | 0%
E11/K149/JJ/dm/377 | RESIDENCE | 43 | 77688 |  | Back Propping For Mast Climber | Basement 1 | Design - 1399-20 | 1 |  |  |  |  | unit | 1 | 2022-10-31 |  | 100% | 100% | 0% | 8 | 7695.22 | 511.06 | 5386.65 | 4088.48 | 0 | 100% | 9475.13 | 7284.87 | 2190.26 | Tas Quote 2439-16-3 (item-1) | 9475.13 | 0 | 0%
E11/K149/JJ/dm/377 | RESIDENCE | 44 | 77689 |  | Back Propping For Mast Climber | Ground Level | Design - 1399-20 | 1 |  |  |  |  | unit | 1 | 2022-10-31 |  | 100% | 100% | 0% | 8 | 7695.22 | 511.06 | 5386.65 | 4088.48 | 0 | 100% | 9475.13 | 7284.87 | 2190.26 | Tas Quote 2439-16-3 (item-1) | 9475.13 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 32b | 77690 | 76781 | Block Shifting Work | Level 31 | Tower | 1 | 1.5 | 1.5 | 1 | 1 | rm | 1 | 2022-11-01 | 2022-11-03 | 100% | 100% | 100% | 0.42857 | 63.34 | 7.28 | 44.34 | 3.12 | 19 | 100% | 66.46 | 66.46 | 0 |  | 66.46 | 0 | 0%
E11/K149/JJ/dm/377 | RESIDENCE | 45 | 77691 |  | Back Propping For Mast Climber | Ground Level | Design - 1399-20 | 1 |  |  |  |  | unit | 1 | 2022-11-01 |  | 100% | 100% | 0% | 7.8571 | 7695.22 | 511.06 | 5386.65 | 4015.47 | 0 | 100% | 9402.12 | 7211.86 | 2190.26 | Tas Quote 2439-16-3 (item-1) | 9402.12 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 19b | 77692 | 80536 | Shaft -9 For Ducting Work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 0.75 | 1 | 2 | m2-LxW | 1.13 | 2022-10-29 | 2022-11-28 | 100% | 100% | 100% | 4.4286 | 36.52 | 2.94 | 28.89 | 14.71 | 12.38 | 100% | 55.98 | 42.18 | 13.8 |  | 55.98 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 19c | 77693 | 76790 | Shaft -9 For Ducting Work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-11-02 | 2022-11-04 | 100% | 100% | 100% | 0.42857 | 36.52 | 2.94 | 38.35 | 1.89 | 16.43 | 100% | 56.67 | 56.67 | 0 |  | 56.67 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 46 | 77694 | 80539 | Electrical & Plumbing Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 4 | 1 | rm | 4 | 2022-11-03 | 2022-11-26 | 100% | 100% | 100% | 3.4286 | 63.34 | 7.28 | 177.35 | 99.84 | 76.01 | 100% | 353.2 | 273.03 | 80.17 |  | 353.2 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 46 | 77694 | 80539 | Electrical & Plumbing Work | Basement 1 | Additional Boarding | 1 | 2.5 | 1.3 | 1 | 1 | m2-LxW | 3.25 | 2022-11-03 | 2022-11-26 | 100% | 100% | 100% | 3.4286 | 6.63 | 0.7 | 15.08 | 7.8 | 6.46 | 100% | 29.34 | 22.56 | 6.78 |  | 29.34 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 47 | 77695 | 80578 | Block Work | Basement 1 | Tower | 1 | 2.5 | 1.5 | 3 | 1 | rm | 3 | 2022-11-03 | 2022-12-20 | 100% | 100% | 100% | 6.8571 | 63.34 | 7.28 | 133.01 | 149.76 | 57.01 | 100% | 339.78 | 204.77 | 135.01 |  | 339.78 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 48 | 77696 | 80526 | Column Cove Installation Work | Ground Level | Birdcage | 1 | 11.8 | 3.8 | 3.5 | 1 | m3 | 156.94 | 2022-11-03 | 2022-11-17 | 100% | 100% | 100% | 2.1429 | 7.08 | 0.49 | 777.79 | 164.79 | 333.34 | 100% | 1275.92 | 1275.92 | 0 |  | 1275.92 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 49 | 77697 | 80508 | Electrical Service Work (BMS) | Basement 1 | Tower | 1 | 2.5 | 1.3 | 4.2 | 1 | rm | 4.2 | 2022-11-03 | 2022-11-12 | 100% | 100% | 100% | 1.4286 | 63.34 | 7.28 | 186.22 | 43.68 | 79.81 | 100% | 309.71 | 309.71 | 0 |  | 309.71 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 49 | 77697 | 80508 | Electrical Service Work (BMS) | Basement 1 | Additional Boarding | 1 | 2.5 | 1.3 | 1 | 1 | m2-LxW | 3.25 | 2022-11-03 | 2022-11-12 | 100% | 100% | 100% | 1.4286 | 6.63 | 0.7 | 15.08 | 3.25 | 6.46 | 100% | 24.79 | 24.79 | 0 |  | 24.79 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 50 | 77698 | 80529 | Column Cove Installation Work | Ground Level | Tower | 1 | 2.5 | 2.5 | 3.5 | 1 | rm | 3.5 | 2022-11-03 | 2022-11-18 | 100% | 100% | 100% | 2.2857 | 63.34 | 7.28 | 155.18 | 58.24 | 66.51 | 100% | 279.93 | 279.93 | 0 |  | 279.93 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 51 | 77699 | 80510 | Column Cove Installation Work | Ground Level | Tower | 1 | 2.5 | 2.5 | 3.5 | 1 | rm | 3.5 | 2022-11-03 | 2022-11-11 | 100% | 100% | 100% | 1.2857 | 63.34 | 7.28 | 155.18 | 32.76 | 66.51 | 100% | 254.45 | 254.45 | 0 |  | 254.45 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 8p | 77700 |  | Glass Fixing work | Level 31 | Cantilever (0 < 0.5m width) | 1 | 9 | 0.25 | 1 | 2 | m2-LxW | 2.25 | 2022-11-03 |  | 100% | 100% | 0% | 7.5714 | 32.75 | 1.05 | 51.58 | 17.89 | 0 | 100% | 69.47 | 59.34 | 10.13 |  | 69.47 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 8q | 77551 | 76791 | Glass Fixing work | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 10.8 | 1 | 1 | 1 | m2-LxW | 10.8 | 2022-11-03 | 2022-11-05 | 100% | 100% | 100% | 0.42857 | 36.52 | 2.94 | 276.09 | 13.61 | 118.32 | 100% | 408.02 | 408.02 | 0 |  | 408.02 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 38b | 77552 | 76797 | Entrance Lobby Block Work | Ground Level | Tower | 1 | 1 | 1 | 1.5 | 1 | rm | 1.5 | 2022-11-03 | 2022-11-09 | 100% | 100% | 100% | 1 | 63.34 | 7.28 | 66.51 | 10.92 | 28.5 | 100% | 105.93 | 105.93 | 0 |  | 105.93 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 38c | 77553 | 76798 | Entrance Lobby Block Work | Ground Level | Tower | 1 | 1 | 1 | 1.5 | 1 | rm | 1.5 | 2022-11-03 | 2022-11-09 | 100% | 100% | 100% | 1 | 63.34 | 7.28 | 66.51 | 10.92 | 28.5 | 100% | 105.93 | 105.93 | 0 |  | 105.93 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 52 | 77554 | 80523 | Column Cove Installation Work | Ground Level | Tower | 1 | 2.5 | 2.5 | 3.5 | 1 | rm | 3.5 | 2022-11-04 | 2022-11-16 | 100% | 100% | 100% | 1.8571 | 63.34 | 7.28 | 155.18 | 47.32 | 66.51 | 100% | 269.01 | 269.01 | 0 |  | 269.01 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 19d | 77555 | 80502 | Shaft - 9 Ducting Work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 2 | 1.5 | 1 | 1 | m2-LxW | 3 | 2022-11-04 | 2022-11-09 | 100% | 100% | 100% | 0.85714 | 36.52 | 2.94 | 76.69 | 7.56 | 32.87 | 100% | 117.12 | 117.12 | 0 |  | 117.12 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 53 | 77556 | 80511 | Balcony Side Edge Protection | Level 27 | Butress | 1 | 2.5 | 1.8 | 2 |  | m3 | 9 | 2022-11-04 | 2022-11-11 | 100% | 100% | 100% | 1.1429 | 5.29 | 0.35 | 33.33 | 3.6 | 14.28 | 100% | 51.21 | 51.21 | 0 |  | 51.21 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 53a | 77557 | 80511 | Balustrade Glass Edge Protection | Level 27 | Tripple Hnadrail | 1 | 6 |  | 1.5 |  | lm | 6 | 2022-11-04 | 2022-11-11 | 100% | 100% | 100% | 1.1429 | 15 | 0.91 | 63 | 6.24 | 27 | 100% | 96.24 | 96.24 | 0 |  | 96.24 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 54 | 77558 | 80527 | Column Cove Installation Work | Ground Level | Tower | 1 | 2.5 | 2.5 | 3.5 | 1 | rm | 3.5 | 2022-11-04 | 2022-11-17 | 100% | 100% | 100% | 2 | 63.34 | 7.28 | 155.18 | 50.96 | 66.51 | 100% | 272.65 | 272.65 | 0 |  | 272.65 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 46a | 77559 | 80540 | Electrical Services Work | Basement 1 | Tower | 1 | 1.8 | 1.3 | 4 | 1 | rm | 4 | 2022-11-05 | 2022-11-26 | 100% | 100% | 100% | 3.1429 | 63.34 | 7.28 | 177.35 | 91.52 | 76.01 | 100% | 344.88 | 264.71 | 80.17 |  | 344.88 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 55 | 77560 | 80517 | Electrical Services Work | Basement 1 | Independent | 1 | 3.8 | 1.3 | 2.5 | 1 | m2-LxH | 9.5 | 2022-11-05 | 2022-11-15 | 100% | 100% | 100% | 1.5714 | 12.01 | 0.49 | 79.87 | 7.32 | 34.23 | 100% | 121.42 | 121.42 | 0 |  | 121.42 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 56 | 77561 |  | Plant Room Kmep Work | Level 5 | Tower | 1 | 2.5 | 1.8 | 4 | 1 | rm | 4 | 2022-11-05 |  | 100% | 100% | 0% | 7.2857 | 63.34 | 7.28 | 177.35 | 212.16 | 0 | 100% | 389.51 | 264.71 | 124.8 |  | 389.51 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 56 | 77561 |  | Plant Room Kmep Work | Level 5 | Additional Boarding | 1 | 2.5 | 1.8 | 1 | 1 | m2-LxW | 4.5 | 2022-11-05 |  | 100% | 100% | 0% | 7.2857 | 6.63 | 0.7 | 20.88 | 22.95 | 0 | 100% | 43.83 | 30.33 | 13.5 |  | 43.83 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 38d | 77562 | 76799 | Entrance Lobby Block Work | Ground Level | Tower | 1 | 1 | 1 | 1.5 | 1 | rm | 1.5 | 2022-11-05 | 2022-11-09 | 100% | 100% | 100% | 0.71429 | 63.34 | 7.28 | 66.51 | 7.8 | 28.5 | 100% | 102.81 | 102.81 | 0 |  | 102.81 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 38e | 77563 | 76800 | Entrance Lobby Block Work | Ground Level | Tower | 1 | 1 | 1 | 1.5 | 1 | rm | 1.5 | 2022-11-05 | 2022-11-09 | 100% | 100% | 100% | 0.71429 | 63.34 | 7.28 | 66.51 | 7.8 | 28.5 | 100% | 102.81 | 102.81 | 0 |  | 102.81 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 57 | 77564 | 80549 | Electrical Services Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3.8 | 1 | rm | 3.8 | 2022-11-05 | 2022-12-05 | 100% | 100% | 100% | 4.4286 | 63.34 | 7.28 | 168.48 | 122.51 | 72.21 | 100% | 363.2 | 251.47 | 111.73 |  | 363.2 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 58 | 77565 | 80528 | Column Cove Installation Work | Ground Level | Independent 1.8m wide | 1 | 3.8 | 2.5 | 3.5 | 1 | m2-LxH | 13.3 | 2022-11-07 | 2022-11-17 | 100% | 100% | 100% | 1.5714 | 16.76 | 0.77 | 156.04 | 16.09 | 66.87 | 100% | 239 | 239 | 0 |  | 239 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 59 | 77566 | 76794 | Cable Tray Removal Work | Basement 1 | Independent | 1 | 8.1 | 1.3 | 3 | 1 | m2-LxH | 24.3 | 2022-11-07 | 2022-11-08 | 100% | 100% | 100% | 0.28571 | 12.01 | 0.49 | 204.29 | 3.4 | 87.55 | 100% | 295.24 | 295.24 | 0 |  | 295.24 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 8r | 77567 | 80533 | Glass Fixing work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 10.8 | 1 | 1 | 1 | m2-LxW | 10.8 | 2022-11-05 | 2022-11-25 | 100% | 100% | 100% | 3 | 36.52 | 2.94 | 276.09 | 95.26 | 118.32 | 100% | 489.67 | 489.67 | 0 |  | 489.67 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 60 | 77568 | 80512 | Balustrade Glass Edge Protection | Level 25 | Butress | 1 | 2.5 | 1.8 | 2 |  | m3 | 9 | 2022-11-07 | 2022-11-11 | 100% | 100% | 100% | 0.71429 | 5.29 | 0.35 | 33.33 | 2.25 | 14.28 | 100% | 49.86 | 49.86 | 0 |  | 49.86 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 60a | 77569 | 80512 | Balustrade Glass Edge Protection | Level 25 | Tripple Hnadrail | 1 | 3 |  | 1.5 |  | lm | 3 | 2022-11-07 | 2022-11-11 | 100% | 100% | 100% | 0.71429 | 15 | 0.91 | 31.5 | 1.95 | 13.5 | 100% | 46.95 | 46.95 | 0 |  | 46.95 | 0 | 0%
E11/K149/PK/dm/400 | RESIDENCE | 61 | 77578 | 80513 | OME Corridoor Mep Work | Ground Level | Design - 1399-22 | 1 | 24.3 | 1 | 4 | 1 | m2-LxH | 97.2 | 2022-11-07 | 2022-11-14 | 100% | 100% | 100% | 1.1429 | 115.4699 | 2.27 | 7856.57 | 252.16 | 3367.1 | 100% | 11475.83 | 11475.83 | 0 | Prorate Tas Quote - 2439-19-1 | 11475.83 | 0 | 0%
| RESIDENCE | 62 | 77570 |  | Back Propping For Mast Climber | Basement 1 | Design - 1399-24 | 1 |  |  |  |  | unit | 1 | 2022-11-08 |  | 100% | 100% | 0% | 6.8571 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| RESIDENCE | 63 | 77571 |  | Back Propping For Mast Climber | Basement 1 | Design - 1399-24 | 1 |  |  |  |  | unit | 1 | 2022-11-08 |  | 100% | 100% | 0% | 6.8571 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| RESIDENCE | 64 | 77572 |  | Back Propping For Mast Climber | Basement 2 | Design - 1399-20E | 1 |  |  |  |  | unit | 1 | 2022-11-09 |  | 100% | 100% | 0% | 6.7143 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| RESIDENCE | 65 | 77573 |  | Back Propping For Mast Climber | Basement 2 | Design - 1399-20E | 1 |  |  |  |  | unit | 1 | 2022-11-09 |  | 100% | 100% | 0% | 6.7143 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 19e | 77574 | 80522 | Shaft - 9 Ducting Work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 2 | 1 | 1 | 1 | m2-LxW | 2 | 2022-11-09 | 2022-11-14 | 100% | 100% | 100% | 0.85714 | 36.52 | 2.94 | 51.13 | 5.04 | 21.91 | 100% | 78.08 | 78.08 | 0 |  | 78.08 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 61a | 77582 | 80514 | Corridor KMEP Work | Ground Level | Independent 1.8m wide | 1 | 4 | 2.5 | 4 | 1 | m2-LxH | 16 | 2022-11-09 | 2022-11-14 | 100% | 100% | 100% | 0.85714 | 16.76 | 0.77 | 187.71 | 10.56 | 80.45 | 100% | 278.72 | 278.72 | 0 |  | 278.72 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 19f | 77575 | 80505 | Shaft - 9 Ducting Work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-11-10 | 2022-11-10 | 100% | 100% | 100% | 0.14286 | 36.52 | 2.94 | 38.35 | 0.63 | 16.43 | 100% | 55.41 | 55.41 | 0 |  | 55.41 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 66 | 77576 |  | Pool Plant Room (KMEP Work) | Level 3 | Tower | 1 | 2.5 | 1.8 | 2 | 1 | rm | 2 | 2022-11-10 |  | 100% | 100% | 0% | 6.5714 | 63.34 | 7.28 | 88.68 | 95.68 | 0 | 100% | 184.36 | 121.96 | 62.4 | (BW-0754) | 184.36 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 67 | 77577 | 80530 | Entrance Area Glass Work | Ground Level | Birdcage | 1 | 3.1 | 2.6 | 4 | 1 | m3 | 32.24 | 2022-11-10 | 2022-11-19 | 100% | 100% | 100% | 1.4286 | 7.08 | 0.49 | 159.78 | 22.57 | 68.48 | 100% | 250.83 | 250.83 | 0 | (Glass Line - BW-002) | 250.83 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 68 | 77579 |  | Staircase - Electrical Work | Level 2 to 3 | Independent | 1 | 6.3 | 1.3 | 3 | 1 | m2-LxH | 18.9 | 2022-11-10 |  | 100% | 100% | 0% | 6.5714 | 12.01 | 0.49 | 158.89 | 60.86 | 0 | 100% | 219.75 | 180.06 | 39.69 | (BW-0754) | 219.75 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 68a | 77580 |  | Staircase - Electrical Work | Level 2 to 3 | Independent | 1 | 3.5 | 1.3 | 4.5 | 1 | m2-LxH | 15.75 | 2022-11-10 |  | 100% | 100% | 0% | 6.5714 | 12.01 | 0.49 | 132.41 | 50.72 | 0 | 100% | 183.13 | 150.05 | 33.08 | (BW-0754) | 183.13 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 69 | 77581 | 80518 | Electrical Service Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 4 | 1 | rm | 4 | 2022-11-11 | 2022-11-14 | 100% | 100% | 100% | 0.57143 | 63.34 | 7.28 | 177.35 | 16.64 | 76.01 | 100% | 270 | 270 | 0 |  | 270 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 70 | 77583 | 80554 | Entrance Storage room (KMEP) | Ground Level | Tower | 1 | 1.3 | 0.9 | 4 | 1 | rm | 4 | 2022-11-11 | 2022-12-06 | 100% | 100% | 100% | 3.7143 | 63.34 | 7.28 | 177.35 | 108.16 | 76.01 | 100% | 361.52 | 239.75 | 121.77 |  | 361.52 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 70 | 77583 | 80554 | Entrance Storage room (KMEP) | Ground Level | Additional Boarding | 1 | 1.3 | 0.9 | 1 | 1 | m2-LxW | 1.17 | 2022-11-11 | 2022-12-06 | 100% | 100% | 100% | 3.7143 | 6.63 | 0.7 | 5.43 | 3.04 | 2.33 | 100% | 10.8 | 7.19 | 3.61 |  | 10.8 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 71 | 77584 | 80520 | BOH Corridor Block Work | Ground Level | Tower | 1 | 2.5 | 1.3 | 4 | 1 | rm | 4 | 2022-11-11 | 2022-11-15 | 100% | 100% | 100% | 0.71429 | 63.34 | 7.28 | 177.35 | 20.8 | 76.01 | 100% | 274.16 | 274.16 | 0 |  | 274.16 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 71 | 77584 | 80520 | BOH Corridor Block Work | Ground Level | Additional Boarding | 1 | 2.5 | 1.3 | 1 | 1 | m2-LxW | 3.25 | 2022-11-11 | 2022-11-15 | 100% | 100% | 100% | 0.71429 | 6.63 | 0.7 | 15.08 | 1.63 | 6.46 | 100% | 23.17 | 23.17 | 0 |  | 23.17 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 72 | 77585 |  | Lift Lobby Fire Curtain Work | Ground Level | Tower | 1 | 2.5 | 1.3 | 2.2 | 1 | rm | 2.2 | 2022-11-11 |  | 100% | 100% | 0% | 6.4286 | 63.34 | 7.28 | 97.54 | 102.96 | 0 | 100% | 200.5 | 131.86 | 68.64 |  | 200.5 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 73 | 77586 | 80521 | BOH Corridor Block Work | Ground Level | Tower | 1 | 1.8 | 1.3 | 4.5 | 1 | rm | 4.5 | 2022-11-11 | 2022-11-15 | 100% | 100% | 100% | 0.71429 | 63.34 | 7.28 | 199.52 | 23.4 | 85.51 | 100% | 308.43 | 308.43 | 0 |  | 308.43 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 73 | 77586 | 80521 | BOH Corridor Block Work | Ground Level | Additional Boarding | 1 | 1.8 | 1.3 | 1 | 1 | m2-LxW | 2.34 | 2022-11-11 | 2022-11-15 | 100% | 100% | 100% | 0.71429 | 6.63 | 0.7 | 10.86 | 1.17 | 4.65 | 100% | 16.68 | 16.68 | 0 |  | 16.68 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 74 | 77587 | 80524 | BOH Corridor Shaft Block Work | Ground Level | Tower | 1 | 1.8 | 1.3 | 4 | 1 | rm | 4 | 2022-11-11 | 2022-11-16 | 100% | 100% | 100% | 0.85714 | 63.34 | 7.28 | 177.35 | 24.96 | 76.01 | 100% | 278.32 | 278.32 | 0 |  | 278.32 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 74 | 77587 | 80524 | BOH Corridor Shaft Block Work | Ground Level | Additional Boarding | 1 | 1.8 | 1.3 | 1 | 2 | m2-LxW | 2.34 | 2022-11-11 | 2022-11-16 | 100% | 100% | 100% | 0.85714 | 6.63 | 0.7 | 10.86 | 1.4 | 4.65 | 100% | 16.91 | 16.91 | 0 |  | 16.91 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 75 | 77588 | 80519 | Electrical Services Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 2 | 1 | rm | 2 | 2022-11-12 | 2022-11-15 | 100% | 100% | 100% | 0.57143 | 63.34 | 7.28 | 88.68 | 8.32 | 38 | 100% | 135 | 135 | 0 |  | 135 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 76 | 77589 | 80546 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3.5 | 1 | rm | 3.5 | 2022-11-14 | 2022-11-29 | 100% | 100% | 100% | 2.2857 | 63.34 | 7.28 | 155.18 | 58.24 | 66.51 | 100% | 279.93 | 198.86 | 81.07 |  | 279.93 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 1o | 77501 | 80556 | Drainge Pipe Connection | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 1.8 | 1 | 1 | 1 | m2-LxW | 1.8 | 2022-11-14 | 2022-12-06 | 100% | 100% | 100% | 3.2857 | 36.52 | 2.94 | 46.02 | 17.39 | 19.72 | 100% | 83.13 | 55.09 | 28.04 |  | 83.13 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 77 | 77503 | 80564 | Chill Water Pipe For (KMEP) | Level 2 | Independent 1.8m wide | 1 | 4 | 2.5 | 1.5 | 1 | m2-LxH | 6 | 2022-11-15 | 2022-12-10 | 100% | 100% | 100% | 3.7143 | 16.76 | 0.77 | 70.39 | 17.16 | 30.17 | 100% | 117.72 | 77.65 | 40.07 |  | 117.72 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 78 | 77504 | 80532 | Lift 3 Gypsum Work | Level 2 | Tower | 1 | 1.8 | 1.3 | 2 | 1 | rm | 2 | 2022-11-15 | 2022-11-19 | 100% | 100% | 100% | 0.71429 | 63.34 | 7.28 | 88.68 | 10.4 | 38 | 100% | 137.08 | 137.08 | 0 |  | 137.08 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 79 | 77590 | 80551 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 2.5 | 2.5 | 1 | rm | 2.5 | 2022-11-15 | 2022-12-05 | 100% | 100% | 100% | 3 | 63.34 | 7.28 | 110.85 | 54.6 | 47.51 | 100% | 212.96 | 139.45 | 73.51 |  | 212.96 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 79a | 77591 | 80552 | Cable Pulling Work | Basement 1 | Tower | 1 | 2 | 1 | 3 | 1 | rm | 3 | 2022-11-15 | 2022-12-05 | 100% | 100% | 100% | 3 | 63.34 | 7.28 | 133.01 | 65.52 | 57.01 | 100% | 255.54 | 167.33 | 88.21 |  | 260.93 | 5.39 | 2.066%
E11/K149/SK/dm/213 | RESIDENCE | 80 | 77592 | 80550 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 1.8 | 3.7 | 1 | rm | 3.7 | 2022-11-15 | 2022-12-05 | 100% | 100% | 100% | 3 | 63.34 | 7.28 | 164.05 | 80.81 | 70.31 | 100% | 315.17 | 206.38 | 108.79 |  | 315.17 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 81 | 77593 | 80543 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3.7 | 1 | rm | 3.7 | 2022-11-15 | 2022-11-29 | 100% | 100% | 100% | 2.1429 | 63.34 | 7.28 | 164.05 | 57.72 | 70.31 | 100% | 292.08 | 206.38 | 85.7 |  | 292.08 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 81 | 77593 | 80543 | Cable Pulling Work | Basement 1 | Additional Boarding | 1 | 2.5 | 1.3 | 1 | 1 | m2-LxW | 3.25 | 2022-11-15 | 2022-11-29 | 100% | 100% | 100% | 2.1429 | 6.63 | 0.7 | 15.08 | 4.88 | 6.46 | 100% | 26.42 | 18.66 | 7.76 |  | 26.42 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 82 | 77594 | 80544 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3 | 1 | rm | 3 | 2022-11-15 | 2022-11-29 | 100% | 100% | 100% | 2.1429 | 63.34 | 7.28 | 133.01 | 46.8 | 57.01 | 100% | 236.82 | 167.33 | 69.49 |  | 236.82 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 83 | 77595 | 80547 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3.5 | 1 | rm | 3.5 | 2022-11-15 | 2022-11-29 | 100% | 100% | 100% | 2.1429 | 63.34 | 7.28 | 155.18 | 54.6 | 66.51 | 100% | 276.29 | 195.22 | 81.07 |  | 276.29 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 19g | 77502 | 80537 | Shaft 9 Duct Fixing Work | Level 31 | Cantilever (0 < 0.5m width) | 1 | 4.5 | 0.5 | 1 | 1 | m2-LxW | 2.25 | 2022-11-14 | 2022-11-28 | 100% | 100% | 100% | 2.1429 | 32.75 | 1.05 | 51.58 | 5.06 | 22.11 | 100% | 78.75 | 55.63 | 23.12 |  | 78.75 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 84 | 77505 |  | Ceiling Opening and Closing for (KMEP) | Ground Level | Mobile Tower | 1 | 2.5 | 1.8 | 3.7 | 1 | rm | 3.7 | 2022-11-16 |  | 100% | 100% | 0% | 5.7143 | 103.33 | 10.29 | 267.62 | 217.56 | 0 | 100% | 485.18 | 322.01 | 163.17 |  | 485.18 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 85 | 77506 | 80560 | Duct Fixing Work | Basement 1 | Independent | 1 | 6.3 | 1.3 | 2 | 1 | m2-LxH | 12.6 | 2022-11-16 | 2022-12-10 | 100% | 100% | 100% | 3.5714 | 12.01 | 0.49 | 105.93 | 22.05 | 45.4 | 100% | 173.38 | 114.75 | 58.63 |  | 173.38 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 86 | 77507 | 80531 | Lift 3 Gypsum Work | Level 2 | Tower | 1 | 1.3 | 0.9 | 2 | 1 | rm | 2 | 2022-11-16 | 2022-11-19 | 100% | 100% | 100% | 0.57143 | 63.34 | 7.28 | 88.68 | 8.32 | 38 | 100% | 135 | 135 | 0 |  | 135 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 87 | 77508 | 80572 | Lift Lobby Glass Line Work | Ground Level | Tower | 1 | 2.5 | 1.3 | 4 | 1 | rm | 4 | 2022-11-17 | 2022-12-13 | 100% | 100% | 100% | 3.8571 | 63.34 | 7.28 | 177.35 | 112.32 | 76.01 | 100% | 365.68 | 214.79 | 150.89 |  | 365.68 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 87 | 77508 | 80572 | Lift Lobby Glass Line Work | Ground Level | Additional Boarding | 1 | 2.5 | 1.3 | 1 | 1 | m2-LxW | 3.25 | 2022-11-17 | 2022-12-13 | 100% | 100% | 100% | 3.8571 | 6.63 | 0.7 | 15.08 | 8.78 | 6.46 | 100% | 30.32 | 18.01 | 12.31 |  | 30.32 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 88 | 77509 |  | BOH Corridor Lift 1&2 Wall Finishing Work | Ground Level | Independent | 1 | 14.6 | 1.3 | 4 | 1 | m2-LxH | 58.4 | 2022-11-17 |  | 100% | 100% | 0% | 5.5714 | 12.01 | 0.49 | 490.97 | 159.43 | 0 | 100% | 650.4 | 527.76 | 122.64 |  | 650.4 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 88 | 77509 |  | BOH Corridor Lift 1&2 Wall Finishing Work | Ground Level | Additional Boarding | 1 | 14.6 | 1.3 | 1 | 1 | m2-LxW | 18.98 | 2022-11-17 |  | 100% | 100% | 0% | 5.5714 | 6.63 | 0.7 | 88.09 | 74.02 | 0 | 100% | 162.11 | 105.17 | 56.94 |  | 162.11 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 8s | 77510 |  | Glass Fixing work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 3.5 | 1 | 1 | 1 | m2-LxW | 3.5 | 2022-11-17 |  | 100% | 100% | 0% | 5.5714 | 36.52 | 2.94 | 89.47 | 57.33 | 0 | 100% | 146.8 | 102.7 | 44.1 |  | 146.8 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 89 | 77511 |  | BOH Corridor Lift 1&2 Wall Finishing Work | Ground Level | Independent 1.8m wide | 1 | 5.8 | 2.5 | 4 | 1 | m2-LxH | 23.2 | 2022-11-18 |  | 100% | 100% | 0% | 5.4286 | 16.76 | 0.77 | 272.18 | 96.98 | 0 | 100% | 369.16 | 292.6 | 76.56 |  | 369.16 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 89 | 77511 |  | BOH Corridor Lift 1&2 Wall Finishing Work | Ground Level | Additional Boarding | 1 | 5.8 | 2.5 | 1 | 1 | m2-LxW | 14.5 | 2022-11-18 |  | 100% | 100% | 0% | 5.4286 | 6.63 | 0.7 | 67.29 | 55.1 | 0 | 100% | 122.39 | 78.89 | 43.5 |  | 122.39 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 89a | 77512 |  | BOH Corridor Lift 1&2 Wall Finishing Work | Ground Level | Tower | 1 | 1 | 0.9 | 4 | 1 | rm | 4 | 2022-11-18 |  | 100% | 100% | 0% | 5.4286 | 63.34 | 7.28 | 177.35 | 158.08 | 0 | 100% | 335.43 | 210.63 | 124.8 |  | 335.43 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 89a | 77512 |  | BOH Corridor Lift 1&2 Wall Finishing Work | Ground Level | Additional Boarding | 1 | 1 | 0.9 | 1 | 1 | m2-LxW | 0.9 | 2022-11-18 |  | 100% | 100% | 0% | 5.4286 | 6.63 | 0.7 | 4.18 | 3.42 | 0 | 100% | 7.6 | 4.9 | 2.7 |  | 7.6 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 90 | 77513 | 80574 | Chill Water Pipe For (KMEP) | Ground Level | Birdcage | 1 | 5 | 3.1 | 4 | 1 | m3 | 62 | 2022-11-19 | 2022-12-16 | 100% | 100% | 100% | 4 | 7.08 | 0.49 | 307.27 | 121.52 | 131.69 | 100% | 560.48 | 337.65 | 222.83 |  | 560.48 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 90 | 77513 | 80574 | Chill Water Pipe For (KMEP) | Ground Level | Additional Boarding | 1 | 5 | 3.1 | 1 | 1 | m2-LxW | 15.5 | 2022-11-19 | 2022-12-16 | 100% | 100% | 100% | 4 | 6.63 | 0.7 | 71.94 | 43.4 | 30.83 | 100% | 146.17 | 82.79 | 63.38 |  | 146.17 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 91 | 77514 | 80541 | Lift Lobby Block Shifting Work | Ground Level | Tower | 1 | 1.3 | 0.9 | 1 | 1 | rm | 1 | 2022-11-19 | 2022-11-28 | 100% | 100% | 100% | 1.4286 | 63.34 | 7.28 | 44.34 | 10.4 | 19 | 100% | 73.74 | 51.62 | 22.12 |  | 73.74 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 87a | 77515 | 80542 | Block Work | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 2.5 | 0.75 | 1 | 1 | m2-LxW | 1.88 | 2022-11-19 | 2022-11-28 | 100% | 100% | 100% | 1.4286 | 36.52 | 2.94 | 48.06 | 7.9 | 20.6 | 100% | 76.56 | 53.59 | 22.97 |  | 76.56 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 90a | 77516 | 80575 | BOH Corridor For Chill Pipe (KMEP) | Ground Level | Tower | 1 | 2 | 1.3 | 3.5 | 1 | rm | 3.5 | 2022-11-21 | 2022-12-16 | 100% | 100% | 100% | 3.7143 | 63.34 | 7.28 | 155.18 | 94.64 | 66.51 | 100% | 316.33 | 173.38 | 142.95 |  | 316.33 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 92 | 77517 |  | Balcony Side Glass Installation | Level 1 | Tower | 1 | 2.5 | 1.8 | 5.5 | 1 | rm | 5.5 | 2022-11-21 |  | 100% | 100% | 0% | 5 | 63.34 | 7.28 | 243.86 | 200.2 | 0 | 100% | 444.06 | 272.46 | 171.6 |  | 444.06 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 92 | 77517 |  | Balcony Side Glass Installation | Level 1 | Additional Boarding | 1 | 2.5 | 1.8 | 1 | 1 | m2-LxW | 4.5 | 2022-11-21 |  | 100% | 100% | 0% | 5 | 6.63 | 0.7 | 20.88 | 15.75 | 0 | 100% | 36.63 | 23.13 | 13.5 |  | 36.63 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 93 | 77518 |  | Canal Side For Ceiling Work (KMEP- BW 0804) | Ground Level | Mobile Tower | 1 | 2.5 | 1.8 | 3.7 | 1 | rm | 3.7 | 2022-11-22 |  | 100% | 100% | 0% | 4.8571 | 103.33 | 10.29 | 267.62 | 184.93 | 0 | 100% | 452.55 | 289.38 | 163.17 |  | 452.55 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 94 | 77519 |  | KCE Site Office area Chill Water Pipe (KMEP-BW 767) | Ground Level | Independent | 1 | 5.4 | 1.3 | 4 | 1 | m2-LxH | 21.6 | 2022-11-22 |  | 100% | 100% | 0% | 4.8571 | 12.01 | 0.49 | 181.59 | 51.41 | 0 | 100% | 233 | 187.64 | 45.36 |  | 233 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 94a | 77520 |  | KCE Site Office area Chill Water Pipe (KMEP-BW 767) | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 5.4 | 0.75 | 1 | 1 | m2-LxW | 4.05 | 2022-11-22 |  | 100% | 100% | 0% | 4.8571 | 36.52 | 2.94 | 103.53 | 57.83 | 0 | 100% | 161.36 | 110.33 | 51.03 |  | 161.36 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 94b | 77521 |  | KCE Site Office area Chill Water Pipe (KMEP-BW 767) | Ground Level | Independent 1.8m wide | 1 | 4.9 | 2.5 | 4 | 1 | m2-LxH | 19.6 | 2022-11-22 |  | 100% | 100% | 0% | 4.8571 | 16.76 | 0.77 | 229.95 | 73.3 | 0 | 100% | 303.25 | 238.57 | 64.68 |  | 303.25 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 94c | 77522 |  | KCE Site Office area Chill Water Pipe (KMEP-BW 767) | Ground Level | Tower | 1 | 2.5 | 1.8 | 4 | 1 | rm | 4 | 2022-11-22 |  | 100% | 100% | 0% | 4.8571 | 63.34 | 7.28 | 177.35 | 141.44 | 0 | 100% | 318.79 | 193.99 | 124.8 |  | 318.79 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 95 | 77523 |  | Shaft Water Meter Room For (KMEP-BW 797) | Level 4 | Tower | 1 | 1 | 0.6 | 2 | 1 | rm | 2 | 2022-11-23 |  | 100% | 100% | 0% | 4.7143 | 63.34 | 7.28 | 88.68 | 68.64 | 0 | 100% | 157.32 | 94.92 | 62.4 |  | 157.32 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 96 | 77524 |  | Pump Room For Water Master (BW 024) | Level 3 | Independent 1.8m wide | 1 | 8 | 2.5 | 1.5 | 1 | m2-LxH | 12 | 2022-11-23 |  | 100% | 100% | 0% | 4.7143 | 16.76 | 0.77 | 140.78 | 43.56 | 0 | 100% | 184.34 | 144.74 | 39.6 |  | 184.34 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 97 | 77525 | 80569 | Pump Room For Water Master (BW 024) | Level 3 | Tower | 1 | 2.5 | 1.3 | 1.5 | 1 | rm | 1.5 | 2022-11-23 | 2022-12-14 | 100% | 100% | 100% | 3.1429 | 63.34 | 7.28 | 66.51 | 34.32 | 28.5 | 100% | 129.33 | 71.19 | 58.14 |  | 129.33 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 98 | 77526 |  | Shaft Water Meter Room For (KMEP-BW 797) | Level 2 | Tower | 1 | 1 | 0.6 | 2 | 1 | rm | 2 | 2022-11-23 |  | 100% | 100% | 0% | 4.7143 | 63.34 | 7.28 | 88.68 | 68.64 | 0 | 100% | 157.32 | 94.92 | 62.4 |  | 157.32 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 92a | 77527 | 80534 | Road Side Access For Glass Fixing | Level 2 | Cantilever (0 < 0.5m width) | 1 | 2.5 | 0.5 | 1 | 1 | m2-LxW | 1.25 | 2022-11-23 | 2022-11-24 | 100% | 100% | 100% | 0.28571 | 32.75 | 1.05 | 28.66 | 0.38 | 12.28 | 100% | 41.32 | 41.32 | 0 |  | 41.32 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 99 | 77529 | 80553 | Canal Side For Excavation Access | Ground Level | Tower | 1 | 1.3 | 1.3 | 1 | 1 | rm | 1 | 2022-11-24 | 2022-12-06 | 100% | 100% | 100% | 1.8571 | 63.34 | 7.28 | 44.34 | 13.52 | 19 | 100% | 76.86 | 46.42 | 30.44 |  | 76.86 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 100 | 77530 |  | Shaft Water Meter Room For (KMEP-BW 797) | Ground Level | Tower | 1 | 1 | 0.75 | 4 | 2 | rm | 4 | 2022-11-24 |  | 100% | 100% | 0% | 4.5714 | 63.34 | 7.28 | 177.35 | 133.12 | 0 | 100% | 310.47 | 185.67 | 124.8 |  | 310.47 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 72a | 77531 |  | Lift Lobby For Fire Curtain Work | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 2.5 | 0.75 | 1 | 1 | m2-LxW | 1.88 | 2022-11-24 |  | 100% | 100% | 0% | 4.5714 | 36.52 | 2.94 | 48.06 | 25.27 | 0 | 100% | 73.33 | 49.64 | 23.69 |  | 73.33 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 101 | 77532 |  | Shaft Water Meter Room For (KMEP-BW 797) | Level 5 | Tower | 1 | 1 | 0.5 | 4 | 2 | rm | 4 | 2022-11-25 |  | 100% | 100% | 0% | 4.4286 | 63.34 | 7.28 | 177.35 | 128.96 | 0 | 100% | 306.31 | 181.51 | 124.8 |  | 306.31 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 8t | 77533 |  | Glass Fixing work | Level 30 | Cantilever (0 < 0.5m width) | 1 | 10.8 | 0.5 | 1 | 1 | m2-LxW | 5.4 | 2022-11-25 |  | 100% | 100% | 0% | 4.4286 | 32.75 | 1.05 | 123.8 | 25.11 | 0 | 100% | 148.91 | 124.61 | 24.3 |  | 148.91 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 18 | 74639 | 76808 | Staircase 7 For Electrical Work | Basement 1 | Tower | 1 | 1.8 | 1.3 | 2 | 1 | rm | 2 | 2022-10-27 | 2022-11-05 | 100% | 100% | 100% | 1.4286 | 63.34 | 7.28 | 88.68 | 20.8 | 38 | 100% | 147.48 | 147.48 | 0 |  | 147.48 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 19 | 74640 | 76809 | Staircase 7 For Electrical Work | Basement 1 | Tower | 1 | 1.8 | 1.3 | 2.3 | 1 | rm | 2.3 | 2022-10-27 | 2022-11-05 | 100% | 100% | 100% | 1.4286 | 63.34 | 7.28 | 101.98 | 23.92 | 43.7 | 100% | 169.6 | 169.6 | 0 |  | 169.6 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 20 | 74641 | 76817 | Canal Side Column Cove Work | Ground Level | Tower | 1 | 2.5 | 2.5 | 5.5 | 1 | rm | 5.5 | 2022-10-31 | 2022-11-11 | 100% | 100% | 100% | 1.7143 | 63.34 | 7.28 | 243.86 | 68.64 | 104.51 | 100% | 417.01 | 417.01 | 0 |  | 417.01 | 0 | 0%
E11/K149/SK/dm/259 | HOTEL | 21 | 74644 |  | Inverted Scaffold | Level 29 | Design 1399 -06 rev-B | 1 | 23.5 | 1.8 | 4 | 1 | lm | 23.5 | 2022-10-31 |  | 100% | 100% | 0% | 8 | 1002.22 | 98.12 | 16486.52 | 18446.56 | 0 | 100% | 34933.08 | 25050.99 | 9882.09 | Tas Quote - 2439-6-1 | 34933.08 | 0 | 0%
E11/K149/SK/dm/259 | HOTEL | 21 |  |  | Inverted Scaffold | Level 29 | Third Party Inspection ( Additional) | 1 |  |  |  |  | unit | 1 | 2022-10-31 | 2022-10-31 | 100% | 100% | 100% | 0.14286 | 1230 | 0 | 1230 | 0 | 0 | 100% | 1230 | 1230 | 0 | Additional Inspection | 1230 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 22 | 74642 | 76818 | Column Cove Installation Work | Ground Level | Tower | 1 | 2.5 | 2.5 | 5.5 | 1 | rm | 5.5 | 2022-10-31 | 2022-11-11 | 100% | 100% | 100% | 1.7143 | 63.34 | 7.28 | 243.86 | 68.64 | 104.51 | 100% | 417.01 | 417.01 | 0 |  | 417.01 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 23 | 74643 | 76819 | Column Cove Installation Work | Ground Level | Tower | 1 | 2.5 | 2.5 | 5.5 | 1 | rm | 5.5 | 2022-10-31 | 2022-11-12 | 100% | 100% | 100% | 1.8571 | 63.34 | 7.28 | 243.86 | 74.36 | 104.51 | 100% | 422.73 | 422.73 | 0 |  | 422.73 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 21a | 74645 | 76821 | Canal Side for Wall Cutting Work | Level 29 | Additional Boarding | 1 | 23.5 | 1 | 1 | 1 | m2-LxW | 23.5 | 2022-10-31 | 2022-11-11 | 100% | 100% | 100% | 1.7143 | 6.63 | 0.7 | 109.06 | 28.2 | 46.74 | 100% | 184 | 184 | 0 |  | 184 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 24 | 74646 | 76820 | Column Cove Installation Work | Ground Level | Independent 1.8m wide | 1 | 3.8 | 2.5 | 4.5 | 1 | m2-LxH | 17.1 | 2022-11-01 | 2022-11-11 | 100% | 100% | 100% | 1.5714 | 16.76 | 0.77 | 200.62 | 20.69 | 85.98 | 100% | 307.29 | 307.29 | 0 |  | 307.29 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 12a | 74647 | 80835 | Balcony Side Grc Removel & Pipe Connection | Level 12 | Cantilever (0 < 0.5m width) | 1 | 1.5 | 0.5 | 1 | 1 | m2-LxW | 0.75 | 2022-11-01 | 2022-12-21 | 100% | 100% | 100% | 7.2857 | 32.75 | 1.05 | 17.19 | 5.74 | 7.37 | 100% | 30.3 | 20 | 10.3 |  | 30.3 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 11a | 74648 | 80805 | Balcony Side Grc Work | Level 13 | Cantilever (0 < 0.5m width) | 1 | 1.5 | 0.5 | 1 | 1 | m2-LxW | 0.75 | 2022-11-01 | 2022-12-15 | 100% | 100% | 100% | 6.4286 | 32.75 | 1.05 | 17.19 | 5.06 | 7.37 | 100% | 29.62 | 20 | 9.62 |  | 29.62 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 14a | 74649 | 80806 | Balcony Side RFI-130 | Level 15 | Cantilever (0 < 0.5m width) | 1 | 1.5 | 0.5 | 1 | 1 | m2-LxW | 0.75 | 2022-11-02 | 2022-12-15 | 100% | 100% | 100% | 6.2857 | 32.75 | 1.05 | 17.19 | 4.95 | 7.37 | 100% | 29.51 | 19.89 | 9.62 |  | 29.51 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 25 | 77601 | 80807 | EIFS & Wall Finishing Work | Basement 1 | Independent | 1 | 9.3 | 1.3 | 6 | 1 | m2-LxH | 55.8 | 2022-11-02 | 2022-12-15 | 100% | 100% | 100% | 6.2857 | 12.01 | 0.49 | 469.11 | 171.86 | 201.05 | 100% | 842.02 | 562.85 | 279.17 |  | 842.02 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 25 | 77601 | 80807 | EIFS & Wall Finishing Work | Basement 1 | Additional Boarding | 1 | 9.3 | 1.3 | 1 | 1 | m2-LxW | 12.09 | 2022-11-02 | 2022-12-15 | 100% | 100% | 100% | 6.2857 | 6.63 | 0.7 | 56.11 | 53.2 | 24.05 | 100% | 133.36 | 85.13 | 48.23 |  | 133.36 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 25a | 77602 | 80808 | EIFS & Wall Finishing Work | Basement 1 | Independent | 1 | 10.5 | 1.3 | 4 | 1 | m2-LxH | 42 | 2022-11-02 | 2022-12-15 | 100% | 100% | 100% | 6.2857 | 12.01 | 0.49 | 353.09 | 129.36 | 151.33 | 100% | 633.78 | 423.65 | 210.13 |  | 633.78 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 26 | 77604 | 80839 | Plant Room For CHW Pipe | Level 5 | Independent | 1 | 6 | 1.5 | 2 | 1 | m2-LxH | 12 | 2022-11-04 | 2022-12-21 | 100% | 100% | 100% | 6.8571 | 12.01 | 0.49 | 100.88 | 40.32 | 43.24 | 100% | 184.44 | 119.36 | 65.08 |  | 184.44 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 26a | 77605 | 80840 | Plant Room For CHW Pipe | Level 5 | Independent 1.8m wide | 1 | 6 | 2 | 2.5 | 1 | m2-LxH | 15 | 2022-11-04 | 2022-12-21 | 100% | 100% | 100% | 6.8571 | 16.76 | 0.77 | 175.98 | 79.2 | 75.42 | 100% | 330.6 | 212.28 | 118.32 |  | 330.6 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 26b | 77606 | 80841 | Plant Room For CHW Pipe | Level 5 | Tower | 1 | 1.8 | 1.8 | 1 | 1 | rm | 1 | 2022-11-04 | 2022-12-21 | 100% | 100% | 100% | 6.8571 | 63.34 | 7.28 | 44.34 | 49.92 | 19 | 100% | 113.26 | 67.22 | 46.04 |  | 113.26 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 27 | 77607 | 76816 | Electrical Services Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 4 | 1 | rm | 4 | 2022-11-04 | 2022-11-11 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 177.35 | 33.28 | 76.01 | 100% | 286.64 | 286.64 | 0 |  | 286.64 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 28 | 77608 | 76824 | Bond Ceiling Work | Level 4 | Tower | 1 | 2.5 | 0.9 | 1.2 | 1 | rm | 1.2 | 2022-11-04 | 2022-11-11 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 53.21 | 9.98 | 22.8 | 100% | 85.99 | 85.99 | 0 |  | 85.99 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 29 | 77609 | 76825 | Bond Ceiling Work | Level 4 | Tower | 1 | 2.5 | 0.9 | 1.2 | 1 | rm | 1.2 | 2022-11-04 | 2022-11-11 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 53.21 | 9.98 | 22.8 | 100% | 85.99 | 85.99 | 0 |  | 85.99 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 30 | 77610 | 76826 | Bond Ceiling Work | Level 4 | Tower | 1 | 2.5 | 0.9 | 1.2 | 1 | rm | 1.2 | 2022-11-04 | 2022-11-11 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 53.21 | 9.98 | 22.8 | 100% | 85.99 | 85.99 | 0 |  | 85.99 | 0 | 0%
E11/K149/SK/dm/259 | HOTEL | 31 | 77611 |  | Inverted Scaffold | Level 29 | Design 1399 -06 rev-B | 1 | 22 | 1.8 | 4 | 1 | lm | 22 | 2022-11-04 |  | 100% | 100% | 0% | 7.4286 | 1002.22 | 98.12 | 15434.19 | 16035.61 | 0 | 100% | 31469.8 | 22218.49 | 9251.31 | Tas Quote - 2439-6-1 | 31469.8 | 0 | 0%
E11/K149/SK/dm/259 | HOTEL | 31 |  |  | Inverted Scaffold | Level 29 | Third Party Inspection ( Additional) | 1 |  |  |  |  | unit | 1 | 2022-11-04 |  | 100% | 100% | 0% | 7.4286 | 1230 | 0 | 1230 | 0 | 0 | 100% | 1230 | 1230 | 0 | Additional Inspection | 1230 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 31a | 77612 | 76822 | Inverted Scaffold | Level 29 | Additional Boarding | 1 | 22 | 1 | 1 | 1 | m2-LxW | 22 | 2022-11-04 | 2022-11-11 | 100% | 100% | 100% | 1.1429 | 6.63 | 0.7 | 102.1 | 17.6 | 43.76 | 100% | 163.46 | 163.46 | 0 |  | 163.46 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 32 | 77613 | 76814 | Electrical Services Work | Basement 1 | Independent | 1 | 3.8 | 1.3 | 2.5 | 1 | m2-LxH | 9.5 | 2022-11-04 | 2022-11-10 | 100% | 100% | 100% | 1 | 12.01 | 0.49 | 79.87 | 4.66 | 34.23 | 100% | 118.76 | 118.76 | 0 |  | 118.76 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 32a | 77614 | 76815 | Electrical Services Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 2.3 | 1 | rm | 2.3 | 2022-11-04 | 2022-11-10 | 100% | 100% | 100% | 1 | 63.34 | 7.28 | 101.98 | 16.74 | 43.7 | 100% | 162.42 | 162.42 | 0 |  | 162.42 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 33 | 77615 | 76827 | Bond Ceiling Work | Level 4 | Independent | 1 | 3 | 0.5 | 1.5 | 1 | m2-LxH | 4.5 | 2022-11-04 | 2022-11-11 | 100% | 100% | 100% | 1.1429 | 12.01 | 0.49 | 37.83 | 2.52 | 16.21 | 100% | 56.56 | 56.56 | 0 |  | 56.56 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 34 | 77616 |  | Electrical Services Work | Basement 1 | Independent 1.8m wide | 1 | 3.8 | 2.5 | 3 | 1 | m2-LxH | 11.4 | 2022-11-07 |  | 100% | 100% | 0% | 7 | 16.76 | 0.77 | 133.74 | 61.45 | 0 | 100% | 195.19 | 157.57 | 37.62 |  | 195.19 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 35 | 77617 |  | Electrical Services Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3.2 | 1 | rm | 3.2 | 2022-11-08 |  | 100% | 100% | 0% | 6.8571 | 63.34 | 7.28 | 141.88 | 159.74 | 0 | 100% | 301.62 | 201.78 | 99.84 |  | 301.62 | 0 | 0%
E11/K149/SK/dm/341 | HOTEL | 36 | 77618 | 76847 | Balcony Floor Drain Work | Level 18 to 20 | Independent 1.8m wide | 1 | 6 | 1.8 | 7 | 1 | unit | 1 | 2022-11-09 | 2022-12-12 | 100% | 100% | 100% | 4.8571 | 5277.5 | 48.26 | 3694.25 | 234.41 | 1583.25 | 100% | 5511.91 | 3811.45 | 1700.46 | Tas Quote - 2439-12-2 (item-1) | 5511.91 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 13a | 77619 | 80810 | Balcony Side Grc Removel & Ceiling Board Work | Level 14 | Cantilever (0 < 0.5m width) | 1 | 1.5 | 0.5 | 1 | 1 | m2-LxW | 0.75 | 2022-11-09 | 2022-12-17 | 100% | 100% | 100% | 5.5714 | 32.75 | 1.05 | 17.19 | 4.39 | 7.37 | 100% | 28.95 | 19.1 | 9.85 |  | 28.95 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 21b | 77620 |  | Inverted Scaffold | Level 29 | Design 1399 -23 | 1 | 3 | 1.8 | 1 | 1 | m2-LxW | 5.4 | 2022-11-09 |  | 100% | 100% | 0% | 6.7143 | 36.52 | 2.94 | 138.05 | 106.6 | 0 | 100% | 244.65 | 176.61 | 68.04 |  | 244.65 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 10b | 77621 |  | Inverted Scaffold | Level 29 | Design 1399 -23 | 1 | 1.8 | 1.5 | 1 | 1 | m2-LxW | 2.7 | 2022-11-09 |  | 100% | 100% | 0% | 6.7143 | 36.52 | 2.94 | 69.02 | 53.3 | 0 | 100% | 122.32 | 88.3 | 34.02 |  | 122.32 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 31b | 77622 | 76823 | Edge Protection | Level 29 | Single Handrail | 1 | 41 | 1 | 1 |  | lm | 41 | 2022-11-09 | 2022-11-11 | 100% | 100% | 100% | 0.42857 | 7 | 0.42 | 200.9 | 7.38 | 86.1 | 100% | 294.38 | 294.38 | 0 |  | 294.38 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 37 | 77623 | 76813 | Chill Water line Pipe For Water Proof | Ground Level | Independent | 1 | 3 | 1.5 | 1 | 1 | m2-LxH | 3 | 2022-11-09 | 2022-11-10 | 100% | 100% | 100% | 0.28571 | 12.01 | 0.49 | 25.22 | 0.42 | 10.81 | 100% | 36.45 | 36.45 | 0 |  | 36.45 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 25b | 77624 |  | EIFS & Wall Finishing Work | Basement 1 | Independent | 1 | 5 | 1.3 | 2.2 | 1 | m2-LxH | 11 | 2022-11-10 |  | 100% | 100% | 0% | 6.5714 | 12.01 | 0.49 | 92.48 | 35.42 | 0 | 100% | 127.9 | 104.8 | 23.1 |  | 127.9 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 25c | 77625 |  | EIFS & Wall Finishing Work | Basement 1 | Independent | 1 | 8.3 | 1.3 | 2.2 | 1 | m2-LxH | 18.26 | 2022-11-10 |  | 100% | 100% | 0% | 6.5714 | 12.01 | 0.49 | 153.51 | 58.8 | 0 | 100% | 212.31 | 173.96 | 38.35 |  | 212.31 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 38 | 77626 | 76839 | Electrical Services Work | Basement 1 | Independent | 1 | 3.8 | 1.3 | 2.8 | 1 | m2-LxH | 10.64 | 2022-11-11 | 2022-12-05 | 100% | 100% | 100% | 3.5714 | 12.01 | 0.49 | 89.45 | 18.62 | 38.34 | 100% | 146.41 | 100.62 | 45.79 |  | 146.41 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 39 | 77627 | 80801 | Column Cove Installation Work | Ground Level | Independent 1.8m wide | 1 | 3.8 | 2.5 | 4 | 1 | m2-LxH | 15.2 | 2022-11-11 | 2022-11-17 | 100% | 100% | 100% | 1 | 16.76 | 0.77 | 178.33 | 11.7 | 76.43 | 100% | 266.46 | 266.46 | 0 |  | 266.46 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 40 | 77628 | 76833 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3.5 | 1 | rm | 3.5 | 2022-11-12 | 2022-11-29 | 100% | 100% | 100% | 2.5714 | 63.34 | 7.28 | 155.18 | 65.52 | 66.51 | 100% | 287.21 | 206.14 | 81.07 |  | 287.21 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 41 | 77629 | 76834 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3 | 1 | rm | 3 | 2022-11-12 | 2022-11-29 | 100% | 100% | 100% | 2.5714 | 63.34 | 7.28 | 133.01 | 56.16 | 57.01 | 100% | 246.18 | 176.69 | 69.49 |  | 246.18 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 42 | 77630 | 76829 | Cable Pulling Work | Basement 1 | Tower | 1 | 1.8 | 1.3 | 2.5 | 1 | rm | 2.5 | 2022-11-12 | 2022-11-29 | 100% | 100% | 100% | 2.5714 | 63.34 | 7.28 | 110.85 | 46.8 | 47.51 | 100% | 205.16 | 147.25 | 57.91 |  | 205.16 | 0 | 0%
E11/K149/PK/dm/378 | HOTEL | 43&43a | 77633 |  | Ramp Area GRC Pannel Fixing Work | Ground Level | Design 1399-21 | 1 | 9.1 | 1.3 | 5 | 1 | m2-LxH | 45.5 | 2022-11-14 |  | 100% | 100% | 0% | 6 | 95.9 | 13.9 | 3054.42 | 3794.7 | 0 | 100% | 6849.12 | 4138.62 | 2710.5 | Tas Quote - 2439-15-1 (item-1 Prorate) | 6849.12 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 44 | 77631 | 76835 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 4 | 1 | rm | 4 | 2022-11-15 | 2022-11-29 | 100% | 100% | 100% | 2.1429 | 63.34 | 7.28 | 177.35 | 62.4 | 76.01 | 100% | 315.76 | 223.11 | 92.65 |  | 315.76 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 45 | 77632 | 76830 | Cable Pulling Work | Basement 1 | Independent 1.8m wide | 1 | 5 | 2.5 | 3.25 | 1 | m2-LxH | 16.25 | 2022-11-15 | 2022-11-29 | 100% | 100% | 100% | 2.1429 | 16.76 | 0.77 | 190.65 | 26.81 | 81.71 | 100% | 299.17 | 210.31 | 88.86 |  | 299.17 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 2e | 77634 | 80830 | Duct Fixing Work (KMEP) | Level 5 | Additional Boarding | 1 | 3 | 1 | 1 | 1 | m2-LxW | 3 | 2022-11-16 | 2022-12-20 | 100% | 100% | 100% | 5 | 6.63 | 0.7 | 13.92 | 10.5 | 5.97 | 100% | 30.39 | 16.92 | 13.47 |  | 30.39 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 46 | 77635 | 76831 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 2.5 | 3 | 1 | rm | 3 | 2022-11-17 | 2022-11-29 | 100% | 100% | 100% | 1.8571 | 63.34 | 7.28 | 133.01 | 40.56 | 57.01 | 100% | 230.58 | 161.09 | 69.49 |  | 230.58 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 46a | 77636 | 76832 | Cable Pulling Work | Basement 1 | Butress | 1 | 2.5 | 2.5 | 3 |  | m3 | 18.75 | 2022-11-17 | 2022-11-29 | 100% | 100% | 100% | 1.8571 | 5.29 | 0.35 | 69.43 | 12.19 | 29.76 | 100% | 111.38 | 77.87 | 33.51 |  | 111.38 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 47 | 77637 | 76836 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 2.5 | 4.2 | 1 | rm | 4.2 | 2022-11-17 | 2022-11-29 | 100% | 100% | 100% | 1.8571 | 63.34 | 7.28 | 186.22 | 56.78 | 79.81 | 100% | 322.81 | 225.53 | 97.28 |  | 322.81 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 48 | 77638 | 80837 | GRC Divider Removel | Level 12 | Tower | 1 | 1.8 | 1.8 | 1.5 | 1 | rm | 1.5 | 2022-11-17 | 2022-12-21 | 100% | 100% | 100% | 5 | 63.34 | 7.28 | 66.51 | 54.6 | 28.5 | 100% | 149.61 | 80.55 | 69.06 |  | 149.61 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 48a | 77638 | 80837 | GRC Divider Removel | Level 12 | Cantilever (0 < 0.5m width) | 1 | 3.5 | 0.5 | 1 | 1 | m2-LxW | 1.75 | 2022-11-17 | 2022-12-21 | 100% | 100% | 100% | 5 | 32.75 | 1.05 | 40.12 | 9.19 | 17.19 | 100% | 66.5 | 42.48 | 24.02 |  | 66.5 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 48a | 77638 | 80837 | GRC Divider Removel | Level 12 | Netting Supply & Install | 1 | 9 | 1 | 1 | 1 | m2-LxH | 9 | 2022-11-17 | 2022-12-21 | 100% | 100% | 100% | 5 | 8.52 | 0 | 53.68 | 0 | 23 | 100% | 76.68 | 53.68 | 23 |  | 76.68 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 36a | 77639 | 76848 | GRC Divider Removel | Level 18 to 20 | Tower | 1 | 1.8 | 1.8 | 7 | 1 | rm | 7 | 2022-11-17 | 2022-12-12 | 100% | 100% | 100% | 3.7143 | 63.34 | 7.28 | 310.37 | 189.28 | 133.01 | 100% | 632.66 | 375.89 | 256.77 |  | 632.66 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 36b | 77639 | 76849 | GRC Divider Removel | Level 18 to 20 | Cantilever (0 < 0.5m width) | 1 | 3 | 0.5 | 1 | 1 | m2-LxW | 1.5 | 2022-11-17 | 2022-12-12 | 100% | 100% | 100% | 3.7143 | 32.75 | 1.05 | 34.39 | 5.85 | 14.74 | 100% | 54.98 | 36.42 | 18.56 |  | 54.98 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 36b | 77639 | 76849 | GRC Divider Removel | Level 18 to 20 | Netting Supply & Install | 1 | 37.8 | 1 | 1 |  | m2-LxH | 37.8 | 2022-11-17 | 2022-12-12 | 100% | 100% | 100% | 3.7143 | 8.52 |  | 225.44 | 0 | 96.62 | 100% | 322.06 | 225.44 | 96.62 |  | 322.06 | 0 | 0%
E11/K149/SK/dm/259 | HOTEL | 49 | 77640 |  | Inverted Scaffold | Level 29 | Design 1399-26 | 1 | 21 | 1.8 | 4 | 1 | lm | 21 | 2022-11-17 |  | 100% | 100% | 0% | 5.5714 | 1002.22 | 98.12 | 14732.63 | 11480.04 | 0 | 100% | 26212.67 | 17381.87 | 8830.8 | Tas Quote - 2439-6-1 | 26212.67 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 49a | 77641 |  | Wall Cutting Work | Level 29 | Additional Boarding | 1 | 15 | 1 | 1 | 1 | m2-LxW | 15 | 2022-11-17 |  | 100% | 100% | 0% | 5.5714 | 6.63 | 0.7 | 69.62 | 58.5 | 0 | 100% | 128.12 | 83.12 | 45 |  | 128.12 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 50 | 77642 | 76837 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 2.5 | 4 | 1 | rm | 4 | 2022-11-18 | 2022-11-29 | 100% | 100% | 100% | 1.7143 | 63.34 | 7.28 | 177.35 | 49.92 | 76.01 | 100% | 303.28 | 210.63 | 92.65 |  | 303.28 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 51 | 77643 |  | Staircase 7 For Electrical Work | Ground Level | Independent 1.8m wide | 1 | 3.8 | 2.5 | 2.8 | 1 | m2-LxH | 10.64 | 2022-11-18 |  | 100% | 100% | 0% | 5.4286 | 16.76 | 0.77 | 124.83 | 44.48 | 0 | 100% | 169.31 | 134.19 | 35.12 |  | 169.31 | 0 | 0%
E11/K149/JA/dm/429 | HOTEL | 52 | 77645 |  | Balcony Access | Level 20 | Tower | 1 | 2.5 | 1.3 | 3.5 | 1 | unit | 1 | 2022-11-18 |  | 100% | 100% | 0% | 5.4286 | 1278.36 | 29.12 | 894.85 | 158.08 | 0 | 100% | 921.3138 | 928.13 | -6.8162 | Tas Quote -2439-20-1 (item#7) | 1052.93 | 131.6163 | 12.5%
E11/K149/SK/dm/213 | HOTEL | 52a | 77645 |  | Balcony Access | Level 21 | Cantilever (0.5 > 1.2m width) | 1 | 1.3 | 0.75 | 1 | 1 | m2-LxW | 0.98 | 2022-11-18 |  | 100% | 100% | 0% | 5.4286 | 36.52 | 2.94 | 25.05 | 15.64 | 0 | 100% | 40.69 | 28.34 | 12.35 |  | 40.69 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 13b | 77646 | 80811 | GRC Divider Removel | Level 14 | Tower | 1 | 1.5 | 0.5 | 1.5 | 1 | rm | 1.5 | 2022-11-18 | 2022-12-17 | 100% | 100% | 100% | 4.2857 | 63.34 | 7.28 | 66.51 | 46.8 | 28.5 | 100% | 141.81 | 78.99 | 62.82 |  | 141.81 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 25d | 77647 | 76845 | Wall Finishing Work | Basement 1 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-11-19 | 2022-12-10 | 100% | 100% | 100% | 3.1429 | 36.52 | 2.94 | 38.35 | 13.86 | 16.43 | 100% | 68.64 | 42.76 | 25.88 |  | 68.64 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 51a | 77644 |  | Staircase 7 For Electrical Work | Ground Level | Tower | 1 | 2.5 | 0.9 | 2.5 | 1 | rm | 2.5 | 2022-11-18 |  | 100% | 100% | 0% | 5.4286 | 63.34 | 7.28 | 110.85 | 98.8 | 0 | 100% | 209.65 | 131.65 | 78 |  | 209.65 | 0 | 0%
E11/K149/PK/dm/378 | HOTEL | 43b&43c | 77648 |  | Ramp Area GRC Pannel Fixing Work | Ground Level | Design 1399-21 | 1 | 5.1 | 1.3 | 5 | 1 | m2-LxH | 25.5 | 2022-11-21 |  | 100% | 100% | 0% | 5 | 95.9 | 13.9 | 1711.82 | 1772.25 | 0 | 100% | 3484.07 | 1965 | 1519.07 | Tas Quote - 2439-15-1 (item-1 Prorate) | 3484.07 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 53 | 77649 | 80831 | Plant Room For Duct Work | Level 5 | Independent 1.8m wide | 1 | 4.3 | 1.8 | 4.5 | 1 | m2-LxH | 19.35 | 2022-11-21 | 2022-12-20 | 100% | 100% | 100% | 4.2857 | 16.76 | 0.77 | 227.01 | 63.86 | 97.29 | 100% | 388.16 | 237.65 | 150.51 |  | 388.16 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 53a | 79051 | 80832 | Plant Room For Duct Work | Level 5 | Tower | 1 | 2.5 | 1.8 | 2.5 | 1 | rm | 2.5 | 2022-11-22 | 2022-12-20 | 100% | 100% | 100% | 4.1429 | 63.34 | 7.28 | 110.85 | 75.4 | 47.51 | 100% | 233.76 | 121.25 | 112.51 |  | 233.76 | 0 | 0%
E11/K149/JA/dm/429 | HOTEL | 54 | 79052 |  | Balcony Access | Level 10 | Tower | 1 | 2.5 | 1.3 | 4 | 1 | unit | 1 | 2022-11-22 |  | 100% | 100% | 0% | 4.8571 | 1278.36 | 29.12 | 894.85 | 141.44 | 0 | 100% | 1036.29 | 911.49 | 124.8 | Tas Quote -2439-20-1 (item#2) | 1036.29 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 54a | 79052 |  | Balcony Access | Level 10 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1.3 | 1 | 1 | m2-LxW | 1.95 | 2022-11-22 |  | 100% | 100% | 0% | 4.8571 | 36.52 | 2.94 | 49.85 | 27.85 | 0 | 100% | 77.7 | 53.13 | 24.57 |  | 77.7 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 55 | 79053 | 80812 | GRC Divider Removel | Level 13 | Tower | 1 | 2.5 | 1 | 4.7 | 1 | rm | 4.7 | 2022-11-22 | 2022-12-17 | 100% | 100% | 100% | 3.7143 | 63.34 | 7.28 | 208.39 | 127.09 | 89.31 | 100% | 424.79 | 227.94 | 196.85 |  | 424.79 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 55a | 79053 | 80812 | GRC Divider Removel | Level 13 | Cantilever (0 < 0.5m width) | 1 | 1 | 0.5 | 1 | 1 | m2-LxW | 0.5 | 2022-11-22 | 2022-12-17 | 100% | 100% | 100% | 3.7143 | 32.75 | 1.05 | 11.46 | 1.95 | 4.91 | 100% | 18.32 | 11.76 | 6.56 |  | 18.32 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 55 | 79053 | 80812 | GRC Divider Removel | Level 13 | Netting Supply & Install | 1 | 25 | 1 | 1 | 1 | m2-LxH | 25 | 2022-11-22 | 2022-12-17 | 100% | 100% | 100% | 3.7143 | 8.52 | 0 | 149.1 | 0 | 63.9 | 100% | 213 | 149.1 | 63.9 |  | 213 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 36c | 79054 | 76850 | GRC Divider Removel | Level 18 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1.2 | 1 | 1 | m2-LxW | 1.8 | 2022-11-22 | 2022-12-12 | 100% | 100% | 100% | 3 | 36.52 | 2.94 | 46.02 | 15.88 | 19.72 | 100% | 81.62 | 49.04 | 32.58 |  | 81.62 | 0 | 0%
E11/K149/JA/dm/429 | HOTEL | 56 | 79055 |  | Balcony Access | Level 15 | Tower | 1 | 2.5 | 1 | 3.5 | 1 | unit | 1 | 2022-11-23 |  | 100% | 100% | 0% | 4.7143 | 1278.36 | 29.12 | 894.85 | 137.28 | 0 | 100% | 903.1138 | 907.33 | -4.2162 | Tas Quote -2439-20-1 (item#4) | 1032.13 | 129.0163 | 12.5%
E11/K149/SK/dm/213 | HOTEL | 56a | 79055 |  | Balcony Access | Level 15 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-11-23 |  | 100% | 100% | 0% | 4.7143 | 36.52 | 2.94 | 38.35 | 20.79 | 0 | 100% | 59.14 | 40.24 | 18.9 |  | 59.14 | 0 | 0%
E11/K149/JA/dm/429 | HOTEL | 57 | 79056 |  | Balcony Access | Level 18 | Tower | 1 | 2.5 | 1 | 6 | 3 | unit | 1 | 2022-11-23 |  | 100% | 100% | 0% | 4.7143 | 1783.37 | 40.04 | 1248.36 | 188.76 | 0 | 100% | 1437.12 | 1265.52 | 171.6 | Tas Quote -2439-20-1 (item#6) | 1437.12 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 57a | 79056 |  | Balcony Access | Level 18 | Cantilever (0.5 > 1.2m width) | 1 | 1 | 1 | 1 | 1 | m2-LxW | 1 | 2022-11-23 |  | 100% | 100% | 0% | 4.7143 | 36.52 | 2.94 | 25.56 | 13.86 | 0 | 100% | 39.42 | 26.82 | 12.6 |  | 39.42 | 0 | 0%
E11/K149/JA/dm/429 | HOTEL | 58 | 79057 |  | Balcony Access | Level 7 | Tower | 1 | 2.5 | 1 | 3.5 | 1 | unit | 1 | 2022-11-23 |  | 100% | 100% | 0% | 4.7143 | 1278.36 | 29.12 | 894.85 | 137.28 | 0 | 100% | 903.1138 | 907.33 | -4.2162 | Tas Quote -2439-20-1 (item#1) | 1032.13 | 129.0163 | 12.5%
E11/K149/SK/dm/213 | HOTEL | 58a | 79057 |  | Balcony Access | Level 7 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-11-23 |  | 100% | 100% | 0% | 4.7143 | 36.52 | 2.94 | 38.35 | 20.79 | 0 | 100% | 59.14 | 40.24 | 18.9 |  | 59.14 | 0 | 0%
E11/K149/JA/dm/429 | HOTEL | 59 | 79058 |  | Balcony Access | Level 13 | Tower | 1 | 2.5 | 1 | 3.5 | 1 | unit | 1 | 2022-11-24 |  | 100% | 100% | 0% | 4.5714 | 1278.36 | 29.12 | 894.85 | 133.12 | 0 | 100% | 899.4737 | 903.17 | -3.6962 | Tas Quote -2439-20-1 (item#3) | 1027.97 | 128.4963 | 12.5%
E11/K149/SK/dm/213 | HOTEL | 59a | 79058 |  | Balcony Access | Level 13 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-11-24 |  | 100% | 100% | 0% | 4.5714 | 36.52 | 2.94 | 38.35 | 20.16 | 0 | 100% | 58.51 | 39.61 | 18.9 |  | 58.51 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 25e | 79059 | 76846 | Wall Finishing Work | Basement 1 | Independent | 1 | 4.1 | 1.3 | 1.5 | 1 | m2-LxH | 6.15 | 2022-11-24 | 2022-12-10 | 100% | 100% | 100% | 2.4286 | 12.01 | 0.49 | 51.7 | 7.32 | 22.16 | 100% | 81.18 | 52.56 | 28.62 |  | 81.18 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 102 | 77534 |  | KMEP BW-829 | Ground Level | Tower | 1 | 2.5 | 1.8 | 4 | 1 | rm | 4 | 2022-11-26 |  | 100% | 100% | 0% | 4.2857 | 63.34 | 7.28 | 177.35 | 124.8 | 0 | 100% | 302.15 |  | 302.15 |  | 302.15 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 103 | 77535 |  | Planter Area For Water Tank Access | Ground Level | Independent 1.8m wide | 1 | 3 | 2.5 | 2.5 | 1 | m2-LxH | 7.5 | 2022-11-26 |  | 100% | 100% | 0% | 4.2857 | 16.76 | 0.77 | 87.99 | 24.75 | 0 | 100% | 112.74 |  | 112.74 |  | 112.74 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 104 | 77536 | 80548 | Crane Extension Platform | Roof | Birdcage | 1 | 5.4 | 3.8 | 2 | 1 | m3 | 41.04 | 2022-11-26 | 2022-12-05 | 100% | 100% | 100% | 1.4286 | 7.08 | 0.49 | 203.39 | 28.73 | 87.17 | 100% | 319.29 |  | 319.29 |  | 319.29 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 104 | 77536 | 80548 | Crane Extension Platform | Roof | Netting Supply & Install | 1 | 18.4 | 1 | 1 |  | m2-LxH | 18.4 | 2022-11-26 | 2022-12-05 | 100% | 100% | 100% | 1.4286 | 8.52 | 0 | 109.74 | 0 | 47.03 | 100% | 156.77 |  | 156.77 |  | 156.77 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 105 | 77537 | 80558 | OME Office For Chill Water Pipe Work (KMEP BW-767) | Level 2 | Independent | 1 | 5 | 1.3 | 2.5 | 1 | m2-LxH | 12.5 | 2022-11-26 | 2022-12-10 | 100% | 100% | 100% | 2.1429 | 12.01 | 0.49 | 105.09 | 13.13 | 45.04 | 100% | 163.26 |  | 163.26 |  | 163.26 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 105a | 77538 | 80559 | OME Office For Chill Water Pipe Work (KMEP BW-767) | Level 2 | Tower | 1 | 2.5 | 1.8 | 2.5 | 1 | rm | 2.5 | 2022-11-26 | 2022-12-10 | 100% | 100% | 100% | 2.1429 | 63.34 | 7.28 | 110.85 | 39 | 47.51 | 100% | 197.36 |  | 197.36 |  | 197.36 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 106 | 77539 |  | Planter Area For Water Tank Access | Ground Level | Independent 1.8m wide | 1 | 3 | 2 | 3.5 | 1 | m2-LxH | 10.5 | 2022-11-26 |  | 100% | 100% | 0% | 4.2857 | 16.76 | 0.77 | 123.19 | 34.65 | 0 | 100% | 157.84 |  | 157.84 |  | 157.84 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 107 | 77540 | 80565 | Ramp Area For Wall Concret Work | Ground Level | Independent | 1 | 18.4 | 0.9 | 2 | 1 | m2-LxH | 36.8 | 2022-11-29 | 2022-12-12 | 100% | 100% | 100% | 2 | 12.01 | 0.49 | 309.38 | 36.06 | 132.59 | 100% | 478.03 |  | 478.03 |  | 478.03 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 107 | 77540 | 80565 | Ramp Area For Wall Concret Work | Ground Level | Netting Supply & Install | 1 | 97.9 | 1 | 1 |  | m2-LxH | 97.9 | 2022-11-29 | 2022-12-12 | 100% | 100% | 100% | 2 | 8.52 | 0 | 583.88 | 0 | 250.23 | 100% | 834.11 |  | 834.11 |  | 834.11 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 1r | 77541 |  | Canal Side For Glass Frame Installation | Level 30 | Cantilever (0 < 0.5m width) | 2 | 8.5 | 0.5 | 1 | 2 | m2-LxW | 8.5 | 2022-11-29 |  | 100% | 100% | 0% | 3.8571 | 32.75 | 1.05 | 194.86 | 34.43 | 0 | 100% | 229.29 |  | 229.29 |  | 313.68 | 84.39 | 26.9%
E11/K149/SK/dm/213 | RESIDENCE | 1s | 77544 |  | Canal Side Glass Fixing Work | Level 30 to 31 | Additional Boarding | 4 | 5 | 1.8 | 1 | 4 | m2-LxW | 36 | 2022-11-30 |  | 100% | 100% | 0% | 3.7143 | 6.63 | 0.7 | 167.08 | 93.6 | 0 | 100% | 260.68 |  | 260.68 |  | 260.68 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 1s | 77544 |  | Canal Side Glass Fixing Work | Level 30 to 31 | Netting Supply & Install | 1 | 36 | 1 | 1 |  | m2-LxH | 36 | 2022-11-30 |  | 100% | 100% | 0% | 3.7143 | 8.52 | 0 | 214.7 | 0 | 0 | 100% | 214.7 |  | 214.7 |  | 214.7 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 110 | 77545 |  | KMEP BW | Level 2 | Tower | 1 | 2.5 | 1.3 | 6 | 3 | rm | 6 | 2022-11-30 |  | 100% | 100% | 0% | 3.7143 | 63.34 | 7.28 | 266.03 | 162.24 | 0 | 100% | 428.27 |  | 428.27 |  | 428.27 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 110 | 77545 |  | KMEP BW | Level 2 | Additional Boarding | 2 | 2.5 | 1.3 | 1 | 2 | m2-LxW | 6.5 | 2022-11-30 |  | 100% | 100% | 0% | 3.7143 | 6.63 | 0.7 | 30.17 | 16.9 | 0 | 100% | 47.07 |  | 47.07 |  | 47.07 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 110a | 77545 |  | KMEP BW | Level 2 | Butress | 1 | 2.5 | 2.5 | 3.5 |  | m3 | 21.88 | 2022-11-30 |  | 100% | 100% | 0% | 3.7143 | 5.29 | 0.35 | 81.02 | 28.44 | 0 | 100% | 109.46 |  | 109.46 |  | 109.46 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 110b | 77546 |  | KMEP BW | Level 2 | Cantilever (0 < 0.5m width) | 3 | 1.3 | 0.5 | 1 | 3 | m2-LxW | 1.95 | 2022-11-30 |  | 100% | 100% | 0% | 3.7143 | 32.75 | 1.05 | 44.7 | 7.61 | 0 | 100% | 52.31 |  | 52.31 |  | 52.31 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 8u | 77547 |  | Balcony For Access | Level 29 | Additional Boarding | 2 | 1.8 | 1.8 | 1 | 2 | m2-LxW | 6.48 | 2022-12-05 |  | 100% | 100% | 0% | 3 | 6.63 | 0.7 | 30.07 | 13.61 | 0 | 100% | 43.68 |  | 43.68 |  | 43.68 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 8v | 77548 |  | Balcony For Access | Level 29 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1.5 | 1 | 1 | m2-LxW | 2.25 | 2022-12-05 |  | 100% | 100% | 0% | 3 | 36.52 | 2.94 | 57.52 | 19.85 | 0 | 100% | 77.37 |  | 77.37 |  | 77.37 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 1t | 77549 |  | Glass Fixing work | Level 31 | Cantilever (0 < 0.5m width) | 3 | 8.5 | 0.5 | 1 | 3 | m2-LxW | 12.75 | 2022-12-06 |  | 100% | 100% | 0% | 2.8571 | 32.75 | 1.05 | 292.29 | 38.25 | 0 | 100% | 330.54 |  | 330.54 |  | 330.54 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 1v | 79102 |  | Canal Side Glass Fixing Work | Level 30 | Additional Boarding | 1 | 7.2 | 1.8 | 1 | 1 | m2-LxW | 12.96 | 2022-12-06 |  | 100% | 100% | 0% | 2.8571 | 6.63 | 0.7 | 60.15 | 25.92 | 0 | 100% | 86.07 |  | 86.07 |  | 86.07 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 107a | 79118 | 80555 | Ramp Area For Wall Concret Work | Ground Level | Independent | 1 | 18.4 | 0.9 | 2 | 1 | m2-LxH | 36.8 | 2022-12-06 | 2022-12-07 | 100% | 100% | 100% | 0.28571 | 12.01 | 0.49 | 309.38 | 5.15 | 132.59 | 100% | 447.12 |  | 447.12 |  | 447.12 | 0 | 0%
E11/K149/SK/dm/468 | RESIDENCE | 111 | 79106 |  | EIFS Fixing Work | Level 10 | Independent | 1 | 20 | 0.6 | 2.5 | 1 | unit | 1 | 2022-12-07 |  | 100% | 100% | 0% | 2.7143 | 3253.14 | 303.8 | 2277.2 | 824.6 | 0 | 100% | 2584.8333 |  | 2584.8333 | Tas Quote - 2439-21-1 (Item #1) | 3101.8 | 516.9667 | 16.67%
E11/K149/SK/dm/468 | RESIDENCE | 111a | 79107 |  | EIFS Fixing Work | Level 10 | Independent | 1 | 2.6 | 1.3 | 3.5 | 2 | unit | 1 | 2022-12-07 |  | 100% | 100% | 0% | 2.7143 | 1093.55 | 110.25 | 765.49 | 299.25 | 0 | 100% | 645.9423 |  | 645.9423 | Tas Quote - 2439-21-1 (Item #2) | 1064.74 | 418.7977 | 39.33%
E11/K149/SK/dm/213 | RESIDENCE | 112 | 79105 |  | House Keeping Lobby (KMEP BW-886) | Level 5 | Tower | 1 | 1.8 | 1.8 | 3.5 | 1 | rm | 3.5 | 2022-12-07 |  | 100% | 100% | 0% | 2.7143 | 63.34 | 7.28 | 155.18 | 69.16 | 0 | 100% | 224.34 |  | 224.34 |  | 224.34 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 113 | 79110 | 80561 | Staircase 3 (KMEP BW-886) | Level 5 | Tower | 1 | 2.5 | 1 | 1.5 | 1 | rm | 1.5 | 2022-12-08 | 2022-12-10 | 100% | 100% | 100% | 0.42857 | 63.34 | 7.28 | 66.51 | 4.68 | 28.5 | 100% | 99.69 |  | 99.69 |  | 99.69 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 113a | 79111 | 80562 | Staircase 3 (KMEP BW-886) | Level 5 | Independent | 1 | 3 | 0.6 | 1.5 | 1 | m2-LxH | 4.5 | 2022-12-08 | 2022-12-10 | 100% | 100% | 100% | 0.42857 | 12.01 | 0.49 | 37.83 | 0.95 | 16.21 | 100% | 54.99 |  | 54.99 |  | 54.99 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 114 | 79112 | 80563 | Staircase 3 (KMEP BW-886) | Level 5 | Tower | 1 | 2.5 | 1 | 1.5 | 1 | rm | 1.5 | 2022-12-08 | 2022-12-10 | 100% | 100% | 100% | 0.42857 | 63.34 | 7.28 | 66.51 | 4.68 | 28.5 | 100% | 99.69 |  | 99.69 |  | 99.69 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 115 | 79113 |  | Electrical Room - (KMEP BW-882) | Level 4 | Tower | 1 | 1.3 | 1.3 | 2 | 1 | rm | 2 | 2022-12-08 |  | 100% | 100% | 0% | 2.5714 | 63.34 | 7.28 | 88.68 | 37.44 | 0 | 100% | 126.12 |  | 126.12 |  | 126.12 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 116 | 79114 | 80570 | Near Gate 1 For Wall Plaster | Ground Level | Independent | 1 | 10 | 1.3 | 1.5 | 1 | m2-LxH | 15 | 2022-12-08 | 2022-12-14 | 100% | 100% | 100% | 1 | 12.01 | 0.49 | 126.11 | 7.35 | 54.05 | 100% | 187.51 |  | 187.51 |  | 187.51 | 0 | 0%
E11/K149/MS/dm/497 | RESIDENCE | 117 | 79116 | 80580 | House Keeping Lobby Shaft Lobby | Level 31 | Design 1399-31 | 1 | 3 | 1 | 2.3 | 1 | unit | 1 | 2022-12-08 | 2022-12-19 | 100% | 100% | 100% | 1.7143 | 4070.27 | 60.66 | 2849.19 | 103.99 | 1221.08 | 100% | 3555.8511 |  | 3555.8511 | Tas Quote - 2439-23-1 (Item 3) | 4174.26 | 618.4089 | 14.81%
E11/K149/SK/dm/213 | RESIDENCE | 118 | 79115 |  | Canal Side For Beam Drilling Work | Level 31 | Tower | 2 | 1 | 0.75 | 1 | 1 | rm | 2 | 2022-12-08 |  | 100% | 100% | 0% | 2.5714 | 63.34 | 7.28 | 88.68 | 37.44 | 0 | 100% | 126.12 |  | 126.12 |  | 126.12 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 1w | 79117 |  | Canal Side For Glass Fixing Work | Level 31 | Cantilever (0 < 0.5m width) | 2 | 1.8 | 0.5 | 1 | 2 | m2-LxW | 1.8 | 2022-12-08 |  | 100% | 100% | 0% | 2.5714 | 32.75 | 1.05 | 41.27 | 4.86 | 0 | 100% | 46.13 |  | 46.13 |  | 46.13 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 119 | 79119 | 80579 | Curtain Wall Glass Frame Work | Ground Level | Tower | 1 | 2.5 | 1.3 | 4 | 1 | rm | 4 | 2022-12-09 | 2022-12-19 | 100% | 100% | 100% | 1.5714 | 63.34 | 7.28 | 177.35 | 45.76 | 76.01 | 100% | 299.12 |  | 299.12 |  | 299.12 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 119a | 79119 | 80579 | Curtain Wall Glass Frame Work | Ground Level | Cantilever (0 < 0.5m width) | 1 | 2.5 | 0.25 | 1 | 1 | m2-LxW | 0.63 | 2022-12-09 | 2022-12-19 | 100% | 100% | 100% | 1.5714 | 32.75 | 1.05 | 14.44 | 1.04 | 6.19 | 100% | 21.67 |  | 21.67 |  | 21.67 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 120 | 79120 | 80571 | Near Gate 1 For Wall Concret Work | Ground Level | Independent | 1 | 5 | 1.3 | 1.5 | 1 | m2-LxH | 7.5 | 2022-12-09 | 2022-12-14 | 100% | 100% | 100% | 0.85714 | 12.01 | 0.49 | 63.05 | 3.15 | 27.02 | 100% | 93.22 |  | 93.22 |  | 93.22 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 121 | 79121 | 80566 | Staircase 3 (KMEP BW-885) | Level 4 | Tower | 1 | 2.5 | 1 | 2.5 | 1 | rm | 2.5 | 2022-12-10 | 2022-12-12 | 100% | 100% | 100% | 0.42857 | 63.34 | 7.28 | 110.85 | 7.8 | 47.51 | 100% | 166.16 |  | 166.16 |  | 166.16 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 121a | 79122 | 80567 | Staircase 3 (KMEP BW-885) | Level 4 | Tower | 1 | 2.5 | 0.6 | 1.5 | 1 | rm | 1.5 | 2022-12-10 | 2022-12-12 | 100% | 100% | 100% | 0.42857 | 63.34 | 7.28 | 66.51 | 4.68 | 28.5 | 100% | 99.69 |  | 99.69 |  | 99.69 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 122 | 79123 | 80568 | Staircase 3 (KMEP BW-885) | Level 4 | Tower | 1 | 2.5 | 1 | 2 | 1 | rm | 2 | 2022-12-10 | 2022-12-12 | 100% | 100% | 100% | 0.42857 | 63.34 | 7.28 | 88.68 | 6.24 | 38 | 100% | 132.92 |  | 132.92 |  | 132.92 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 123 | 79124 |  | Electrical Work (BW -868) | Ground Level | Independent 1.8m wide | 1 | 5 | 1.8 | 3 | 1 | m2-LxH | 15 | 2022-12-10 |  | 100% | 100% | 0% | 2.2857 | 16.76 | 0.77 | 175.98 | 26.4 | 0 | 100% | 202.38 |  | 202.38 |  | 202.38 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 123a | 79124 |  | Electrical Work (BW -868) | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 2 | 1.5 | 1 | 1 | m2-LxW | 3 | 2022-12-10 |  | 100% | 100% | 0% | 2.2857 | 36.52 | 2.94 | 76.69 | 20.16 | 0 | 100% | 96.85 |  | 96.85 |  | 96.85 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 124 | 79125 |  | KMEP - BW 858 | Ground Level | Tower | 1 | 1.8 | 1.3 | 3 | 1 | rm | 3 | 2022-12-12 |  | 100% | 100% | 0% | 2 | 63.34 | 7.28 | 133.01 | 43.68 | 0 | 100% | 176.69 |  | 176.69 |  | 176.69 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 125 | 79126 |  | LPG Tank For Wall Plaster Work | Ground Level | Independent | 1 | 4.3 | 1.3 | 1.5 | 1 | m2-LxH | 6.45 | 2022-12-12 |  | 100% | 100% | 0% | 2 | 12.01 | 0.49 | 54.23 | 6.32 | 0 | 100% | 60.55 |  | 60.55 |  | 60.55 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 126 | 79127 |  | Shaft For (KMEP - BW 892) | Level 5 | Tower | 1 | 1 | 0.6 | 4 | 2 | rm | 4 | 2022-12-12 |  | 100% | 100% | 0% | 2 | 63.34 | 7.28 | 177.35 | 58.24 | 0 | 100% | 235.59 |  | 235.59 |  | 235.59 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 127 | 79128 |  | Shaft For (KMEP - BW 892) | Level 4 | Tower | 1 | 1 | 0.6 | 2.5 | 1 | rm | 2.5 | 2022-12-12 |  | 100% | 100% | 0% | 2 | 63.34 | 7.28 | 110.85 | 36.4 | 0 | 100% | 147.25 |  | 147.25 |  | 147.25 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 128 | 79129 | 80585 | Mechanical Work (KMEP - BW 887) | Basement 1 | Independent 1.8m wide | 1 | 11.8 | 2.5 | 3 | 1 | m2-LxH | 35.4 | 2022-12-12 | 2022-12-22 | 100% | 100% | 100% | 1.5714 | 16.76 | 0.77 | 415.31 | 42.83 | 177.99 | 100% | 636.13 |  | 636.13 |  | 636.13 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 128a | 79130 | 80586 | Mechanical Work (KMEP - BW 887) | Basement 1 | Independent 1.8m wide | 1 | 4.3 | 2.5 | 2 | 1 | m2-LxH | 8.6 | 2022-12-12 | 2022-12-22 | 100% | 100% | 100% | 1.5714 | 16.76 | 0.77 | 100.9 | 10.41 | 43.24 | 100% | 154.55 |  | 154.55 |  | 154.55 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 129 | 79131 |  | Ramp Area For Access | Ground Level | Tower | 1 | 2.5 | 0.9 | 1.2 | 1 | rm | 1.2 | 2022-12-12 |  | 100% | 100% | 0% | 2 | 63.34 | 7.28 | 53.21 | 17.47 | 0 | 100% | 70.68 |  | 70.68 |  | 70.68 | 0 | 0%
E11/K149/SK/SR/517 | RESIDENCE | 130&130a | 79132 | 80576 | Balcony Ceiling Work | Level 21 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-13 | 2022-12-17 | 100% | 100% | 100% | 0.71429 | 3620.37 | 54.93 | 2534.26 | 39.24 | 1086.11 | 100% | 1591.1348 |  | 1591.1348 | Tas Quote 2439-25-1 (item#5) | 3659.61 | 2068.4752 | 56.52%
E11/K149/SK/dm/213 | RESIDENCE | 123b | 79133 |  | Corridor For Electrical Work (BW - 868) | Ground Level | Independent 1.8m wide | 1 | 11.8 | 1.8 | 3 | 1 | m2-LxH | 35.4 | 2022-12-13 |  | 100% | 100% | 0% | 1.8571 | 16.76 | 0.77 | 415.31 | 50.62 | 0 | 100% | 465.93 |  | 465.93 |  | 465.93 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 123c | 79134 |  | Corridor For Electrical Work (BW - 868) | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 6 | 1 | 1 | 1 | m2-LxW | 6 | 2022-12-13 |  | 100% | 100% | 0% | 1.8571 | 36.52 | 2.94 | 153.38 | 32.76 | 0 | 100% | 186.14 |  | 186.14 |  | 186.14 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 131 | 79135 |  | Over Head Protection | Ground Level | Independent 1.8m wide | 1 | 17.5 | 2.5 | 2 | 1 | m2-LxH | 35 | 2022-12-13 |  | 100% | 100% | 0% | 1.8571 | 16.76 | 0.77 | 410.62 | 50.05 | 0 | 100% | 460.67 |  | 460.67 |  | 460.67 | 0 | 0%
E11/K149/MS/dm/497 | RESIDENCE | 132 | 79136 |  | Water Pool Glass Lifting Work | Level 10 | Design 1399-30 | 1 | 10.8 | 1.3 | 4.2 | 1 | unit | 1 | 2022-12-13 |  | 100% | 100% | 0% | 1.8571 | 8208.92 | 728.01 | 5746.24 | 1352.02 | 0 | 100% | 5110.7472 |  | 5110.7472 | Tas Quote 2439-23-1 (Item #02) | 7098.26 | 1987.5128 | 28%
E11/K149/MS/dm/497 | RESIDENCE | 132a | 79137 | 80577 | Water Pool Glass Lifting Work | Level 10 | Design 1399-30 | 1 | 5.4 | 1.3 | 4.2 | 1 | unit | 1 | 2022-12-13 | 2022-12-16 | 100% | 100% | 100% | 0.57143 | 0 | 0 | 0 | 0 | 0 | 100% | 0 |  | 0 | Tas Quote 2439-23-1 (Item #02) | 0 | 0 | #DIV/0!
E11/K149/SK/dm/213 | RESIDENCE | 133 | 79138 |  | Electrical Work (KMEP - BW 893) | Basement 1 | Independent | 1 | 7.3 | 1.3 | 5 | 1 | m2-LxH | 36.5 | 2022-12-14 |  | 100% | 100% | 0% | 1.7143 | 12.01 | 0.49 | 306.86 | 30.66 | 0 | 100% | 337.52 |  | 337.52 |  | 337.52 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 133 | 79138 |  | Electrical Work (KMEP - BW 893) | Basement 1 | Additional Boarding | 1 | 7.3 | 1.3 | 1 | 1 | m2-LxW | 9.49 | 2022-12-14 |  | 100% | 100% | 0% | 1.7143 | 6.63 | 0.7 | 44.04 | 11.39 | 0 | 100% | 55.43 |  | 55.43 |  | 55.43 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 133a | 79138 |  | Electrical Work (KMEP - BW 893) | Basement 1 | Cantilever (0 < 0.5m width) | 1 | 7.3 | 0.5 | 1 | 1 | m2-LxW | 3.65 | 2022-12-14 |  | 100% | 100% | 0% | 1.7143 | 32.75 | 1.05 | 83.68 | 6.57 | 0 | 100% | 90.25 |  | 90.25 |  | 90.25 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 128b | 79139 | 80587 | Mechanical Work (KMEP - BW 887) | Basement 1 | Tower | 1 | 2.5 | 2.5 | 3 | 1 | rm | 3 | 2022-12-14 | 2022-12-22 | 100% | 100% | 100% | 1.2857 | 63.34 | 7.28 | 133.01 | 28.08 | 57.01 | 100% | 218.1 |  | 218.1 |  | 218.1 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 134 | 79140 |  | EIFS Fixing Work | Ground Level | Independent | 1 | 3.8 | 1.3 | 4 | 1 | m2-LxH | 15.2 | 2022-12-14 |  | 100% | 100% | 0% | 1.7143 | 12.01 | 0.49 | 127.79 | 12.77 | 0 | 100% | 140.56 |  | 140.56 |  | 140.56 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 134 | 79140 |  | EIFS Fixing Work | Ground Level | Additional Boarding | 1 | 3.8 | 1.3 | 1 | 1 | m2-LxW | 4.94 | 2022-12-14 |  | 100% | 100% | 0% | 1.7143 | 6.63 | 0.7 | 22.93 | 5.93 | 0 | 100% | 28.86 |  | 28.86 |  | 28.86 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 135 | 79141 |  | EIFS Fixing Work | Ground Level | Independent | 1 | 11.8 | 1.3 | 4 | 1 | m2-LxH | 47.2 | 2022-12-14 |  | 100% | 100% | 0% | 1.7143 | 12.01 | 0.49 | 396.81 | 39.65 | 0 | 100% | 436.46 |  | 436.46 |  | 436.46 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 135 | 79141 |  | EIFS Fixing Work | Ground Level | Additional Boarding | 1 | 11.8 | 1.3 | 1 | 1 | m2-LxW | 15.34 | 2022-12-14 |  | 100% | 100% | 0% | 1.7143 | 6.63 | 0.7 | 71.19 | 18.41 | 0 | 100% | 89.6 |  | 89.6 |  | 89.6 | 0 | 0%
E11/K149/SK/SR/517 | RESIDENCE | 139&139a | 79144 | 80589 | Balcony Ceiling Work | Level 19 | Design 1399 - 35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-15 | 2022-12-22 | 100% | 100% | 100% | 1.1429 | 3620.37 | 54.93 | 2534.26 | 62.78 | 1086.11 | 100% | 1601.3696 |  | 1601.3696 | Tas Quote 2439-25-1 (item#5) | 3683.15 | 2081.7804 | 56.52%
E11/K149/SK/dm/213 | RESIDENCE | 44a | 79147 |  | EIFS Wall Finishing Work | Ground Level | Additional Boarding | 1 | 4 | 1 | 1 | 1 | m2-LxW | 4 | 2022-12-15 |  | 100% | 100% | 0% | 1.5714 | 6.63 | 0.7 | 18.56 | 4.4 | 0 | 100% | 22.96 |  | 22.96 |  | 22.96 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 45a | 79148 |  | EIFS Wall Finishing Work | Ground Level | Additional Boarding | 1 | 4 | 1 | 1 | 1 | m2-LxW | 4 | 2022-12-15 |  | 100% | 100% | 0% | 1.5714 | 6.63 | 0.7 | 18.56 | 4.4 | 0 | 100% | 22.96 |  | 22.96 |  | 22.96 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 137 | 79149 |  | Planter Access | Ground Level | Independent | 1 | 3.5 | 1.3 | 1 | 1 | m2-LxH | 3.5 | 2022-12-15 |  | 100% | 100% | 0% | 1.5714 | 12.01 | 0.49 | 29.42 | 2.7 | 0 | 100% | 32.12 |  | 32.12 |  | 32.12 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 138 | 79150 |  | Staircase Edge Protection | Ground Level | Double Handrail | 1 | 37.5 |  | 1 |  | lm | 37.5 | 2022-12-15 |  | 100% | 100% | 0% | 1.5714 | 15 | 0.91 | 393.75 | 53.63 | 0 | 100% | 447.38 |  | 447.38 |  | 447.38 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 136 | 79152 |  | Over Head Protection | Level 2 | Independent 1.8m wide | 1 | 10.8 | 2.5 | 2.5 | 1 | m2-LxH | 27 | 2022-12-14 |  | 100% | 100% | 0% | 1.7143 | 16.76 | 0.77 | 316.76 | 35.64 | 0 | 100% | 352.4 |  | 352.4 |  | 352.4 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 136a | 79152 |  | Over Head Protection | Level 2 | Butress | 1 | 4.3 | 1.8 | 7 |  | m3 | 54.18 | 2022-12-14 |  | 100% | 100% | 0% | 1.7143 | 5.29 | 0.35 | 200.63 | 32.51 | 0 | 100% | 233.14 |  | 233.14 |  | 233.14 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 136e | 79162 |  | Over Head Protection | ground Level | Independent 1.8m wide | 1 | 3.8 | 2.5 | 4 | 1 | m2-LxH | 15.2 | 2022-12-14 |  | 100% | 100% | 0% | 1.7143 | 16.76 | 0.77 | 178.33 | 20.06 | 0 | 100% | 198.39 |  | 198.39 |  | 198.39 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 136f | 79162 |  | Over Head Protection | ground Level | Independent 1.8m wide | 1 | 3.6 | 2.5 | 5 | 1 | m2-LxH | 18 | 2022-12-14 |  | 100% | 100% | 0% | 1.7143 | 16.76 | 0.77 | 211.18 | 23.76 | 0 | 100% | 234.94 |  | 234.94 |  | 234.94 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 128c | 79154 | 80588 | Mechanical Work (KMEP - BW 887) | Basement 1 | Independent | 1 | 4.3 | 1 | 1.5 | 1 | m2-LxH | 6.45 | 2022-12-15 | 2022-12-22 | 100% | 100% | 100% | 1.1429 | 12.01 | 0.49 | 54.23 | 3.61 | 23.24 | 100% | 81.08 |  | 81.08 |  | 81.08 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 140 | 79155 | 80581 | KMEP - BW 797 | Level 5 | Tower | 1 | 1.8 | 1.3 | 1.5 | 1 | rm | 1.5 | 2022-12-16 | 2022-12-19 | 100% | 100% | 100% | 0.57143 | 63.34 | 7.28 | 66.51 | 6.24 | 28.5 | 100% | 101.25 |  | 101.25 |  | 101.25 | 0 | 0%
E11/K149/SK/SR/517 | RESIDENCE | 141&141a | 79156 | 80583 | Balcony Ceiling Work | Level 18 | Design 1399 - 35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-16 | 2022-12-21 | 100% | 100% | 100% | 0.85714 | 3620.37 | 54.93 | 2534.26 | 47.08 | 1086.11 | 100% | 1594.5435 |  | 1594.5435 | Tas Quote 2439-25-1 (item#5) | 3667.45 | 2072.9065 | 56.52%
E11/K149/SK/SR/517 | RESIDENCE | 142&142a | 79157 | 80584 | Balcony Ceiling Work | Level 18 | Design 1399 - 35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-16 | 2022-12-21 | 100% | 100% | 100% | 0.85714 | 3620.37 | 54.93 | 2534.26 | 47.08 | 1086.11 | 100% | 1594.5435 |  | 1594.5435 | Tas Quote 2439-25-1 (item#5) | 3667.45 | 2072.9065 | 56.52%
E11/K149/SK/dm/213 | RESIDENCE | 143 | 79159 |  | Beam Drilling Work | Level 31 | Tower | 3 | 1 | 0.75 | 0.6 | 1 | rm | 1.8 | 2022-12-17 |  | 100% | 100% | 0% | 1.2857 | 63.34 | 7.28 | 79.81 | 16.85 | 0 | 100% | 96.66 |  | 96.66 |  | 96.66 | 0 | 0%
E11/K149/SK/dm/480 | RESIDENCE | 144 | 79160 |  | Shaft 9 Slab Concrete | Level 31 | Design 1399 - 25a | 1 |  |  |  |  | unit | 1 | 2022-12-17 |  | 100% | 100% | 0% | 1.2857 | 3381.02 | 181.02 | 2366.71 | 232.74 | 0 | 100% | 2599.45 |  | 2599.45 | Tas Quote 2439-22-1 (Item # 1) | 2599.45 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 136b | 79161 |  | Over Head Protection | Ground Level | Butress | 1 | 3.6 | 1.3 | 4 |  | m3 | 18.72 | 2022-12-14 |  | 100% | 100% | 0% | 1.7143 | 5.29 | 0.35 | 69.32 | 11.23 | 0 | 100% | 80.55 |  | 80.55 |  | 80.55 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 136c | 79161 |  | Over Head Protection | Ground Level | Butress | 1 | 3.6 | 1.3 | 2.5 |  | m3 | 11.7 | 2022-12-14 |  | 100% | 100% | 0% | 1.7143 | 5.29 | 0.35 | 43.33 | 7.02 | 0 | 100% | 50.35 |  | 50.35 |  | 50.35 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 136d | 79161 |  | Over Head Protection | Ground Level | Butress | 1 | 3.8 | 0.9 | 3 |  | m3 | 10.26 | 2022-12-14 |  | 100% | 100% | 0% | 1.7143 | 5.29 | 0.35 | 37.99 | 6.16 | 0 | 100% | 44.15 |  | 44.15 |  | 44.15 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 123d | 79163 |  | Electrical Work (BW -868) | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 6 | 1 | 1 | 1 | m2-LxW | 6 | 2022-12-19 |  | 100% | 100% | 0% | 1 | 36.52 | 2.94 | 153.38 | 17.64 | 0 | 100% | 171.02 |  | 171.02 |  | 171.02 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 145 | 79164 |  | GRC Panel Work | Level 31 | Independent 1.8m wide | 1 | 17.8 | 1.8 | 5 | 1 | m2-LxH | 89 | 2022-12-19 |  | 100% | 100% | 0% | 1 | 12.01 | 0.49 | 748.22 | 43.61 | 0 | 100% | 791.83 |  | 791.83 |  | 791.83 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 146 | 79165 |  | Beam Drilling Work | Level 31 | Tower | 1 | 1 | 1 | 1 | 1 | rm | 1 | 2022-12-19 |  | 100% | 100% | 0% | 1 | 63.34 | 7.28 | 44.34 | 7.28 | 0 | 100% | 51.62 |  | 51.62 |  | 51.62 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 147 | 79166 |  | Beam Drilling Work | Level 31 | Tower | 1 | 1 | 1 | 1 | 1 | rm | 1 | 2022-12-19 |  | 100% | 100% | 0% | 1 | 63.34 | 7.28 | 44.34 | 7.28 | 0 | 100% | 51.62 |  | 51.62 |  | 51.62 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 148 | 79167 |  | EIFS Wall Finishing Work | Ground Level | Independent | 1 | 6.3 | 1.3 | 4 | 1 | m2-LxH | 25.2 | 2022-12-20 |  | 100% | 100% | 0% | 0.85714 | 12.01 | 0.49 | 211.86 | 10.58 | 0 | 100% | 222.44 |  | 222.44 |  | 222.44 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 68b | 79168 |  | Electrical Work (KMEP - BW 754) | Level 2 | Additional Boarding | 1 | 2.5 | 1.3 | 1 | 1 | m2-LxW | 3.25 | 2022-12-20 |  | 100% | 100% | 0% | 0.85714 | 6.63 | 0.7 | 15.08 | 1.95 | 0 | 100% | 17.03 |  | 17.03 |  | 17.03 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 149 | 79169 |  | Near KCE Office For Access | Ground Level | Tower | 1 | 1.8 | 1.3 | 1.25 | 1 | rm | 1.25 | 2022-12-21 |  | 100% | 100% | 0% | 0.71429 | 63.34 | 7.28 | 55.42 | 6.5 | 0 | 100% | 61.92 |  | 61.92 |  | 61.92 | 0 | 0%
E11/K149/SK/SR/503 | RESIDENCE | 150 Ext - a,b | 79170 |  | Block and EIFS Work | Level 10 to 17 | Design 1399 - 29 | 1 |  |  |  |  | unit | 1 | 2022-12-21 |  | 100% | 100% | 0% | 0.71429 | 34922.6 | 1384.55 | 24445.82 | 988.96 | 0 | 100% | 25434.78 |  | 25434.78 | Tas Quote 2439-24-1 (Item #4) | 25434.78 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 8x | 79171 |  | Balcony Access | Level 27/28 | Additional Boarding | 1 | 1.8 | 1.8 | 1 | 1 | m2-LxW | 3.24 | 2022-12-21 |  | 100% | 100% | 0% | 0.71429 | 6.63 | 0.7 | 15.04 | 1.62 | 0 | 100% | 16.66 |  | 16.66 |  | 16.66 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 8y | 79172 |  | Balcony Access | Level 27/28 | Cantilever (0.5 > 1.2m width) | 1 | 1.8 | 1 | 1 | 1 | m2-LxW | 1.8 | 2022-12-21 |  | 100% | 100% | 0% | 0.71429 | 36.52 | 2.94 | 46.02 | 3.78 | 0 | 100% | 49.8 |  | 49.8 |  | 49.8 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 151 | 79173 |  | Balcony Ceiling Work | Level 26 | Tower | 1 | 2.5 | 1.3 | 2 | 1 | rm | 2 | 2022-12-22 |  | 100% | 100% | 0% | 0.57143 | 63.34 | 7.28 | 88.68 | 8.32 | 0 | 100% | 97 |  | 97 |  | 97 | 0 | 0%
E11/K149/SK/dm/213 | RESIDENCE | 152 | 79174 |  | Balcony Ceiling Work | Level 27 | Tower | 1 | 2.5 | 1.3 | 2 | 1 | rm | 2 | 2022-12-22 |  | 100% | 100% | 0% | 0.57143 | 63.34 | 7.28 | 88.68 | 8.32 | 0 | 100% | 97 |  | 97 |  | 97 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 48b | 79060 | 80836 | Balcony Floor Drain Work | Level 12 | Tower | 1 | 2.5 | 1.3 | 1.5 | 1 | rm | 1.5 | 2022-11-26 | 2022-12-21 | 100% | 100% | 100% | 3.7143 | 63.34 | 7.28 | 66.51 | 40.56 | 28.5 | 100% | 135.57 |  | 135.57 |  | 135.57 | 0 | 0%
E11/K149/JA/dm/429 | HOTEL | 60 | 79061 |  | Balcony Access | Level 22 | Tower | 1 | 2.5 | 1.3 | 3.7 | 1 | unit | 1 | 2022-11-26 |  | 100% | 100% | 0% | 4.2857 | 1278.36 | 29.12 | 894.85 | 124.8 | 0 | 100% | 943.1762 |  | 943.1762 | Tas Quote 2439-20-1 (Item #08) | 1019.65 | 76.4737 | 7.5%
E11/K149/SK/dm/213 | HOTEL | 60a | 79061 |  | Balcony Access | Level 22 | Cantilever (0.5 > 1.2m width) | 1 | 2 | 1.3 | 1 | 1 | m2-LxW | 2.6 | 2022-11-26 |  | 100% | 100% | 0% | 4.2857 | 36.52 | 2.94 | 66.47 | 32.76 | 0 | 100% | 99.23 |  | 99.23 |  | 99.23 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 61 | 79062 | 76840 | Electrical Service Work | Basement 1 | Independent 1.8m wide | 1 | 29.3 | 2.5 | 2 | 1 | m2-LxH | 58.6 | 2022-11-28 | 2022-12-05 | 100% | 100% | 100% | 1.1429 | 16.76 | 0.77 | 687.5 | 51.57 | 294.64 | 100% | 1033.71 |  | 1033.71 |  | 1033.71 | 0 | 0%
E11/K149/JA/dm/429 | HOTEL | 62 | 79063 |  | Balcony For Access | Level 17 | Tower | 1 | 2.5 | 1.8 | 4 | 1 | unit | 1 | 2022-11-28 |  | 100% | 100% | 0% | 4 | 1278.36 | 29.12 | 894.85 | 116.48 | 0 | 100% | 1011.33 |  | 1011.33 | Tas Quote 2439-20-1 (Item #05) | 1011.33 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 62a | 79063 |  | Balcony For Access | Level 17 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-11-28 |  | 100% | 100% | 0% | 4 | 36.52 | 2.94 | 38.35 | 17.64 | 0 | 100% | 55.99 |  | 55.99 |  | 55.99 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 63 | 79064 | 76841 | FAHU Oil Leakge (BW -783) | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3.5 | 1 | rm | 3.5 | 2022-11-29 | 2022-12-05 | 100% | 100% | 100% | 1 | 63.34 | 7.28 | 155.18 | 25.48 | 66.51 | 100% | 247.17 |  | 247.17 |  | 247.17 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 61a | 79065 | 76838 | Electrical Service Work | Basement 1 | Independent 1.8m wide | 1 | 15 | 2.5 | 2.3 | 1 | m2-LxH | 34.5 | 2022-11-29 | 2022-11-30 | 100% | 100% | 100% | 0.28571 | 16.76 | 0.77 | 404.75 | 7.59 | 173.47 | 100% | 585.81 |  | 585.81 |  | 585.81 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 62b | 79066 |  | Edge Protection | Level 18 | Double Handrail | 1 | 8 | 1 | 1 |  | lm | 8 | 2022-11-30 |  | 100% | 100% | 0% | 3.7143 | 15 | 0.91 | 84 | 27.04 | 0 | 100% | 111.04 |  | 111.04 |  | 111.04 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 57b | 79067 |  | Balcony Drain Pipe Work | Level 19 | Tower | 1 | 2.5 | 1 | 1.5 | 1 | rm | 1.5 | 2022-11-30 |  | 100% | 100% | 0% | 3.7143 | 63.34 | 7.28 | 66.51 | 40.56 | 0 | 100% | 107.07 |  | 107.07 |  | 107.07 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 43d | 79068 |  | EIFS Work | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 14.5 | 0.75 | 1 | 1 | m2-LxW | 10.88 | 2022-12-05 |  | 100% | 100% | 0% | 3 | 36.52 | 2.94 | 278.14 | 95.96 | 0 | 100% | 374.1 |  | 374.1 |  | 374.1 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 64 | 79069 |  | Plant Room For Wall Finishing Work | Ground Level | Independent | 1 | 6.8 | 0.9 | 3 | 1 | m2-LxH | 20.4 | 2022-12-07 |  | 100% | 100% | 0% | 2.7143 | 12.01 | 0.49 | 171.5 | 27.13 | 0 | 100% | 198.63 |  | 198.63 |  | 198.63 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 64a | 79069 |  | Plant Room For Wall Finishing Work | Ground Level | Additional Boarding | 1 | 2.5 | 0.9 | 1 | 1 | m2-LxW | 2.25 | 2022-12-07 |  | 100% | 100% | 0% | 2.7143 | 6.63 | 0.7 | 10.44 | 4.28 | 0 | 100% | 14.72 |  | 14.72 |  | 14.72 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 65 | 79070 |  | EIFS Finishing Work (Hotel Behind Kitchen) | Level 2 | Independent | 1 | 4 | 1 | 5.5 | 1 | m2-LxH | 22 | 2022-12-09 |  | 100% | 100% | 0% | 2.4286 | 12.01 | 0.49 | 184.95 | 26.18 | 0 | 100% | 211.13 |  | 211.13 |  | 211.13 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 65 | 79070 |  | EIFS Finishing Work (Hotel Behind Kitchen) | Level 2 | Additional Boarding | 2 | 4 | 1 | 1 | 2 | m2-LxW | 8 | 2022-12-09 |  | 100% | 100% | 0% | 2.4286 | 6.63 | 0.7 | 37.13 | 13.6 | 0 | 100% | 50.73 |  | 50.73 |  | 50.73 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 66 | 79071 |  | EIFS Damac Side Elevation | Level 2 | Independent | 1 | 13.6 | 0.9 | 1.5 | 1 | m2-LxH | 20.4 | 2022-12-09 |  | 100% | 100% | 0% | 2.4286 | 12.01 | 0.49 | 171.5 | 24.28 | 0 | 100% | 195.78 |  | 195.78 |  | 195.78 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 66a | 79072 |  | EIFS Damac Side Elevation | Level 2 | Cantilever (0 < 0.5m width) | 1 | 14.5 | 0.5 | 1 | 1 | m2-LxW | 7.25 | 2022-12-09 |  | 100% | 100% | 0% | 2.4286 | 32.75 | 1.05 | 166.21 | 18.49 | 0 | 100% | 184.7 |  | 184.7 |  | 184.7 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 66b | 79073 |  | EIFS Damac Side Elevation | Level 2 | Cantilever (0.5 > 1.2m width) | 1 | 1.8 | 1.4 | 1 | 1 | m2-LxW | 2.52 | 2022-12-09 |  | 100% | 100% | 0% | 2.4286 | 32.75 | 1.05 | 57.77 | 6.43 | 0 | 100% | 64.2 |  | 64.2 |  | 64.2 | 0 | 0%
E11/K149/JA/dm/429 | HOTEL | 67 | 79074 |  | Balcony Access | Level 26 | Tower | 1 | 2.5 | 1.3 | 3.5 | 1 | unit | 1 | 2022-12-09 |  | 100% | 100% | 0% | 2.4286 | 1278.36 | 29.12 | 894.85 | 70.72 | 0 | 100% | 844.8738 |  | 844.8738 | Tas Quote 2439-20-1 (Item #10) | 965.57 | 120.6962 | 12.5%
E11/K149/SK/dm/213 | HOTEL | 67a | 79074 |  | Balcony Access | Level 27 | Cantilever (0.5 > 1.2m width) | 1 | 2 | 1.5 | 1 | 1 | m2-LxW | 3 | 2022-12-09 |  | 100% | 100% | 0% | 2.4286 | 32.75 | 1.05 | 68.78 | 7.65 | 0 | 100% | 76.43 |  | 76.43 |  | 76.43 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 68 | 79075 | 80842 | Canal Side Balcony For Grc Work | Level 24 | Independent | 1 | 8.1 | 1.5 | 2.5 | 1 | m2-LxH | 20.25 | 2022-12-09 | 2022-12-22 | 100% | 100% | 100% | 2 | 12.01 | 0.49 | 170.24 | 19.85 | 72.96 | 100% | 263.05 |  | 263.05 |  | 263.05 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 43e | 79076 |  | Ramp Area For Wall Plaster Work | Ground Level | Independent | 1 | 13 | 1 | 1.5 | 1 | m2-LxH | 19.5 | 2022-12-10 |  | 100% | 100% | 0% | 2.2857 | 12.01 | 0.49 | 163.94 | 21.84 | 0 | 100% | 185.78 |  | 185.78 |  | 185.78 | 0 | 0%
E11/K149/SK/SR/517 | HOTEL | 69 | 79077 |  | Balcony Ceiling Work | Level 7 | Design 1399-35b | 1 | 5.3 | 1 | 1 | 1 | unit | 1 | 2022-12-17 |  | 100% | 100% | 0% | 1.2857 | 3620.37 | 54.93 | 2534.26 | 70.62 | 0 | 100% | 1395.9418 |  | 1395.9418 | Tas Quote 2439-25-1 (item#5) | 2604.88 | 1208.9382 | 46.41%
E11/K149/SK/dm/213 | HOTEL | 70 | 79078 |  | Electrical Work For (KMEP - BW917) | Ground Level | Independent | 1 | 6.3 | 1.3 | 4 | 1 | m2-LxH | 25.2 | 2022-12-17 |  | 100% | 100% | 0% | 1.2857 | 12.01 | 0.49 | 211.86 | 15.88 | 0 | 100% | 227.74 |  | 227.74 |  | 227.74 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 70a | 79079 |  | Electrical Work For (KMEP - BW917) | Ground Level | Tower | 1 | 2.5 | 2.5 | 4 | 1 | rm | 4 | 2022-12-17 |  | 100% | 100% | 0% | 1.2857 | 7.08 | 0.49 | 19.82 | 2.52 | 0 | 100% | 22.34 |  | 22.34 |  | 214.79 | 192.45 | 89.6%
E11/K149/SK/SR/517 | HOTEL | 71&71a | 79082 |  | Balcony Ceiling Work | Level 9 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-17 |  | 100% | 100% | 0% | 1.2857 | 3620.37 | 54.93 | 2534.26 | 70.62 | 0 | 100% | 1132.5565 |  | 1132.5565 | Tas Quote 2439-25-1 (item#5) | 2604.88 | 1472.3235 | 56.52%
E11/K149/SK/SR/517 | HOTEL | 72&72a | 79083 |  | Balcony Ceiling Work | Level 9 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-17 |  | 100% | 100% | 0% | 1.2857 | 3620.37 | 54.93 | 2534.26 | 70.62 | 0 | 100% | 1132.5565 |  | 1132.5565 | Tas Quote 2439-25-1 (item#5) | 2604.88 | 1472.3235 | 56.52%
E11/K149/SK/SR/517 | HOTEL | 73&73a | 79084 |  | Balcony Ceiling Work | Level 11 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-20 |  | 100% | 100% | 0% | 0.85714 | 3620.37 | 54.93 | 2534.26 | 47.08 | 0 | 100% | 1122.3217 |  | 1122.3217 | Tas Quote 2439-25-1 (item#5) | 2604.88 | 1482.5583 | 56.91%
E11/K149/SK/SR/517 | HOTEL | 74&74a | 79085 |  | Balcony Ceiling Work | Level 11 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-20 |  | 100% | 100% | 0% | 0.85714 | 3620.37 | 54.93 | 2534.26 | 47.08 | 0 | 100% | 1122.3217 |  | 1122.3217 | Tas Quote 2439-25-1 (item#5) | 2604.88 | 1482.5583 | 56.91%
E11/K149/SK/dm/213 | HOTEL | 75 | 79086 |  | Staircase 7 For (KMEP - BW 793) | Ground Level | Tower | 1 | 1.8 | 1 | 1.2 | 1 | rm | 1.2 | 2022-12-20 |  | 100% | 100% | 0% | 0.85714 | 63.34 | 7.28 | 53.21 | 7.49 | 0 | 100% | 60.7 |  | 60.7 |  | 60.7 | 0 | 0%
E11/K149/SK/SR/517 | HOTEL | 76&76a | 79087 |  | Balcony Ceiling Work | Level 10 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-21 |  | 100% | 100% | 0% | 0.71429 | 3620.37 | 54.93 | 2534.26 | 39.24 | 0 | 100% | 1118.913 |  | 1118.913 | Tas Quote 2439-25-1 (item#5) | 2573.5 | 1454.587 | 56.52%
E11/K149/SK/dm/213 | HOTEL | 70b | 79088 |  | Electrical Work (KMEP - BW 917) | Ground Level | Additional Boarding | 1 | 3.8 | 1.3 | 1 | 1 | m2-LxW | 4.94 | 2022-12-21 |  | 100% | 100% | 0% | 0.71429 | 6.63 | 0.7 | 22.93 | 2.47 | 0 | 100% | 25.4 |  | 25.4 |  | 25.4 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 70c | 79089 |  | Electrical Work (KMEP - BW 917) | Ground Level | Cantilever (0 < 0.5m width) | 1 | 4 | 0.5 | 1 | 1 | m2-LxW | 2 | 2022-12-21 |  | 100% | 100% | 0% | 0.71429 | 32.75 | 1.05 | 45.85 | 1.5 | 0 | 100% | 47.35 |  | 47.35 |  | 47.35 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 77 | 79090 |  | Entrance Area (KMEP - BW 917) | Ground Level | Tower | 1 | 1.3 | 1.3 | 4 | 2 | rm | 4 | 2022-12-22 |  | 100% | 100% | 0% | 0.57143 | 63.34 | 7.28 | 177.35 | 16.64 | 0 | 100% | 193.99 |  | 193.99 |  | 193.99 | 0 | 0%
E11/K149/SK/dm/213 | HOTEL | 51b | 79091 |  | Staircase 7 For (KMEP - BW 793) | Ground Level | Additional Boarding | 1 | 2.5 | 1.3 | 1 | 1 | m2-LxW | 3.25 | 2022-12-22 |  | 100% | 100% | 0% | 0.57143 | 6.63 | 0.7 | 15.08 | 1.3 | 0 | 100% | 16.38 |  | 16.38 |  | 16.38 | 0 | 0%
E11/K149/SK/SR/517 | HOTEL | 78&78a | 79092 |  | Balcony Ceiling Work | Level 10 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-22 |  | 100% | 100% | 0% | 0.57143 | 3620.37 | 54.93 | 2534.26 | 31.39 | 0 | 100% | 1115.5 |  | 1115.5 | Tas Quote 2439-25-1 (item#5) | 2565.65 | 1450.15 | 56.52%
E11/K149/SK/SR/550 | HOTEL |  |  |  | Hire of Aluminium Tower | NA | NA | 1 |  |  |  |  | unit | 1 | 2022-12-19 |  | 0% | 100% | 0% | 1 | 0 | 200 | 0 | 200 | 0 | 100% | 200 |  | 200 |  | 200 | 0 | 0%
E11/K149/SK/SR/560 | HOTEL |  |  |  | Hire of Aluminium Tower | NA | NA | 1 |  |  |  |  | unit | 1 | 2022-12-21 |  | 0% | 100% | 0% | 0.71429 | 0 | 200 | 0 | 142.86 | 0 | 100% | 142.86 |  | 142.86 |  | 142.86 | 0 | 0%
E11/K149/SK/SR/560 | HOTEL |  |  |  | Hire of Aluminium Tower | NA | NA | 1 |  |  |  |  | unit | 1 | 2022-12-22 |  | 0% | 100% | 0% | 0.57143 | 0 | 200 | 0 | 114.29 | 0 | 100% | 114.29 |  | 114.29 |  | 114.29 | 0 | 0%
Total |  |  | 478 | 243 | [18 empty] | 595327.86 | 390678.64 | 37453.16 |  | 1000509.4915 | 600243.73 | 400265.7615 |  | 1025378.7 | #VALUE! | #DIV/0!
Note on V13: Himal Kosala: Deduct 109&a H20 Beam - Bottom
Note on J32: Himal Kosala: Check this
Note on K32: Himal Kosala: Check this
Note on J51: Himal Kosala: Check this
Note on W53: Himal Kosala: Check the rate
Note on AA60: Himal Kosala: As Discuss
Note on AA61: Himal Kosala: As Discuss
Note on Q244: Himal Kosala: Date not added
Note on AB345: Himal Kosala: This design scaffolding for 4m height but accual height is 3.5m
Note on AB359: Himal Kosala: This design scaffolding for 4m height but accual height is 3.5m
Note on AB363: Himal Kosala: This design scaffolding for 4m height but accual height is 3.5m
Note on AB365: Himal Kosala: This design scaffolding for 4m height but accual height is 3.5m
Note on V377: Himal Kosala: Check the rate
Note on W377: Himal Kosala: Check the rate
Note on AB389: Himal Kosala: Design Scaffolding height is 3m, but accual height is 2.5m
Note on AB390: Himal Kosala: Design scaffolding length is 5m but accual length 2.6m
Note on AB397: Himal Kosala: As per accual qty
Note on AB415: Himal Kosala: Base on accual qty
Note on AB419: Himal Kosala: Base on accual qty
Note on AB429: Himal Kosala: Base on accual qty
Note on AB440: Himal Kosala: Base on accual qty
Note on AB441: Himal Kosala: Base on accual qty
Note on H457: Himal Kosala: In HOC sheet this mention as design scaffold (1399-35b)
Note on H458: Himal Kosala: In HOC sheet this mention as design scaffold (1399-35b)
Note on AB460: Himal Kosala: This design scaffolding is for 4m height but accual height is 3.7m
Note on AB477: Himal Kosala: This design scaffolding for 4m height but accual height is 3.5m
Note on AB481: Himal Kosala: Base on accual qty
Note on AB484: Himal Kosala: Base on accual qty
Note on AB485: Himal Kosala: Base on accual qty
Note on P486: Himal Kosala: Check date
Note on AB486: Himal Kosala: Base on accual qty
Note on P487: Himal Kosala: Check date
Note on AB487: Himal Kosala: Base on accual qty
Note on AB489: Himal Kosala: Base on accual qty
Note on AB494: Himal Kosala: Base on accual qty

## Order References
Rate Card Ref | Order Reference | Scaffolding Type | Fixed Duration | Item | Unit | Rate IN AED
1 | E11/K149/SK/dm/213 | Static tower | 0 | Erect & Dismantle | Rising Meter | 63.34
2 | E11/K149/SK/dm/213 | Static tower | 0 | Hire per Week | Rising Meter | 7.28
3 | E11/K149/SK/dm/213 | Mobile Tower | 0 | Erect & Dismantle | Rising Meter | 103.33
4 | E11/K149/SK/dm/213 | Mobile Tower | 0 | Hire per Week | Rising Meter | 10.29
5 | E11/K149/SK/dm/213 | Heavy duty tower | 0 | Erect & Dismantle | Rising Meter | 148
6 | E11/K149/SK/dm/213 | Heavy duty tower | 0 | Hire per Week | Rising Meter | 12.88
7 | E11/K149/SK/dm/213 | Independent 1.2m wide | 0 | Erect & Dismantle | M2 (LxH) | 12.01
8 | E11/K149/SK/dm/213 | Independent 1.2m wide | 0 | Hire per Week | M2 (LxH) | 0.49
9 | E11/K149/SK/dm/213 | Independent 1.8m wide | 0 | Erect & Dismantle | M2 (LxH) | 16.76
10 | E11/K149/SK/dm/213 | Independent 1.8m wide | 0 | Hire per Week | M2 (LxH) | 0.77
11 | E11/K149/SK/dm/213 | Birdcage | 0 | Erect & Dismantle | M3 | 7.08
12 | E11/K149/SK/dm/213 | Birdcage | 0 | Hire per Week | M3/Day | 0.49
13 | E11/K149/SK/dm/213 | Heavy duty birdcage | 0 | Erect & Dismantle | M3 | 10
14 | E11/K149/SK/dm/213 | Heavy duty birdcage | 0 | Hire per Week | M3/Day | 0.91
15 | E11/K149/SK/dm/213 | Buttress | 0 | Erect & Dismantle | M3 | 5.29
16 | E11/K149/SK/dm/213 | Buttress | 0 | Hire per Week | M3/Day | 0.35
17 | E11/K149/SK/dm/213 | Boarded lift | 0 | Erect & Dismantle | M2 (LxW) | 6.63
18 | E11/K149/SK/dm/213 | Boarded lift | 0 | Hire per Week | M2 (LxW) | 0.7
19 | E11/K149/SK/dm/213 | Cantilever (0 < 0.5m width) | 0 | Erect & Dismantle | M2 (LxW) | 32.75
20 | E11/K149/SK/dm/213 | Cantilever (0 < 0.5m width) | 0 | Hire per Week | M2 (LxW) | 1.05
21 | E11/K149/SK/dm/213 | Cantilever (0.5 > 1.2m width) | 0 | Erect & Dismantle | M2 (LxW) | 36.52
22 | E11/K149/SK/dm/213 | Cantilever (0.5 > 1.2m width) | 0 | Hire per Week | M2 (LxW) | 2.94
23 | E11/K149/SK/dm/213 | Bridge | 0 | Erect & Dismantle | Linear Meter | 37.43
24 | E11/K149/SK/dm/213 | Bridge | 0 | Hire per Week | Linear Meter | 1.4
25 | E11/K149/SK/dm/213 | Counterweight (Scaffold Tubes) | 0 | Erect & Dismantle | Linear Meter | 0.3
26 | E11/K149/SK/dm/213 | Counterweight (Scaffold Tubes) | 0 | Hire per Week | Linear Meter | 0.14
27 | E11/K149/SK/dm/213 | Edge protection - A Frame Single | 0 | Erect & Dismantle | Linear Meter | 7
28 | E11/K149/SK/dm/213 | Edge protection - A Frame Single | 0 | Hire per Week | Linear Meter | 0.42
29 | E11/K149/SK/dm/213 | Edge protection - A Frame double | 0 | Erect & Dismantle | Linear Meter | 12
30 | E11/K149/SK/dm/213 | Edge protection - A Frame double | 0 | Hire per Week | Linear Meter | 0.7
31 | E11/K149/SK/dm/213 | Edge Protection - Double | 0 | Erect & Dismantle | Linear Meter | 15
32 | E11/K149/SK/dm/213 | Edge Protection - Double | 0 | Hire per Week | Linear Meter | 0.91
33 | E11/K149/SK/dm/213 | Edge Protection - Double (Hilti) | 0 | Erect & Dismantle | Linear Meter | 24
34 | E11/K149/SK/dm/213 | Edge Protection - Double (Hilti) | 0 | Hire per Week | Linear Meter | 0.7
35 | E11/K149/SK/dm/213 | Netting supply - Beige Colour | 0 | Supply only | M2 (LxH) | 4.52
36 | E11/K149/SK/dm/213 | Netting install | 0 | Supply only | M2 (LxH) | 4
37 | E11/K149/SK/dm/213 | Staircase Supported by structure | 0 | Erect & Dismantle | Rising Meter | 250
38 | E11/K149/SK/dm/213 | Staircase Supported by structure | 0 | Hire per Week | Rising Meter | 14.35
39 | E11/K149/SK/dm/213 | Staircase supported by Buttress | 0 | Erect & Dismantle | Rising Meter | 376.2
40 | E11/K149/SK/dm/213 | Staircase supported by Buttress | 0 | Hire per Week | Rising Meter | 40.11
41 | E11/K149/SK/dm/213 | Manpower - Scaffolder | 0 | Dayworks | Hour | 20.5
42 | E11/K149/SK/dm/213 | Manpower - Foreman | 0 | Dayworks | Hour | 24
43 | E11/K149/SK/dm/216 | Aluminium Tower | 0 | Erect & Dismantle | Set | 0
44 | E11/K149/SK/dm/216 | Aluminium Tower | 0 | Hire per Week | Set | 28.5714
45 | E11/K149/SK/dm/238 | Design - TAS-1399-10A | 1 | Erect & Dismantle | Lumpsum | 6044.84
46 | E11/K149/SK/dm/238 | Design - TAS-1399-10A | 1 | Hire per Week | Hire per Week | 45.3871
47 | E11/K149/SK/dm/239 | Design - TAS-1399-7 | 1 | Erect & Dismantle | Lumpsum | 16252.45
48 | E11/K149/SK/dm/239 | Design - TAS-1399-7 | 1 | Hire per Week | Hire per Week | 89.4243
49 | E11/K149/SK/dm/256 | Balcony Scaffold - Type1 | 1 | Erect & Dismantle | Lumpsum | 4844.83
50 | E11/K149/SK/dm/256 | Balcony Scaffold - Type1 | 1 | Hire per Week | Hire per Week | 15.99
51 | E11/K149/SK/dm/256 | Balcony Scaffold - Type2 | 1 | Erect & Dismantle | Lumpsum | 4990.83
52 | E11/K149/SK/dm/256 | Balcony Scaffold - Type2 | 1 | Hire per Week | Hire per Week | 17.4214
53 | E11/K149/SK/dm/256 | Balcony Scaffold - Type3 | 1 | Erect & Dismantle | Lumpsum | 5095.97
54 | E11/K149/SK/dm/256 | Balcony Scaffold - Type3 | 1 | Hire per Week | Hire per Week | 18.45
55 | E11/K149/SK/dm/256 | Balcony Scaffold - Type4 | 1 | Erect & Dismantle | Lumpsum | 4127.36
56 | E11/K149/SK/dm/256 | Balcony Scaffold - Type4 | 1 | Hire per Week | Hire per Week | 8.4371
57 | E11/K149/SK/dm/256 | Balcony Scaffold - Type5 | 1 | Erect & Dismantle | Lumpsum | 8714.14
58 | E11/K149/SK/dm/256 | Balcony Scaffold - Type5 | 1 | Hire per Week | Hire per Week | 38.73
59 | E11/K149/SK/dm/256 | Balcony Scaffold - Type6 | 1 | Erect & Dismantle | Lumpsum | 5210.58
60 | E11/K149/SK/dm/256 | Balcony Scaffold - Type6 | 1 | Hire per Week | Hire per Week | 19.3229
61 | E11/K149/SK/dm/256 | Balcony Scaffold - Type7 | 1 | Erect & Dismantle | Lumpsum | 5900.72
62 | E11/K149/SK/dm/256 | Balcony Scaffold - Type7 | 1 | Hire per Week | Hire per Week | 26.07
63 | E11/K149/SK/dm/257 | Design - TAS-1399-02D | 1 | Erect & Dismantle | Lumpsum | 53510.26
64 | E11/K149/SK/dm/257 | Design - TAS-1399-02D | 1 | Hire per Week | Hire per Week | 401
65 | E11/K149/SK/dm/259 | Design - TAS-1399-06B | 1 | Erect & Dismantle | Lumpsum | 158449.11
66 | E11/K149/SK/dm/259 | Design - TAS-1399-06B | 1 | Hire per Week | Hire per Week | 2018.4243
67 | CONTRACT - 201A22002/49
68 | E11/K149/HN/dm/285 | Design-TAS-1399-12 | 1 | Erect & Dismantle | Lumpsum | 5083.25
69 | E11/K149/HN/dm/285 | Design-TAS-1399-12 | 1 | Hire per Week | Hire per Week | 123.48
70 | E11/K149/SK/dm/365 |  | 1 | Erect & Dismantle | Lumpsum | 5979.17
71 | E11/K149/SK/dm/350 | Design-TAS-1399-14 | 1 | Erect & Dismantle | Lumpsum | 14003.16
72 | E11/K149/SK/dm/350 | Design-TAS-1399-14 | 1 | Hire per Week | Hire per Week | 660.1
73 | E11/K149/SK/dm/300 | Design-Tas-1399-13A | 1 | Erect & Dismantle | Lumpsum | 4082.38
74 | E11/K149/SK/dm/300 | Design-Tas-1399-13A | 1 | Hire per Week | Hire per Week | 49.28
75 | E11/K149/SK/dm/341 |  | 1 | Erect & Dismantle | Lumpsum | 5325.76
76 | E11/K149/SK/dm/341 |  | 1 | Hire per Week | Hire per Week | 48.26
77 | E11/K149/SK/dm/341 |  | 1 | Erect & Dismantle | Lumpsum | 1375.16
78 | E11/K149/SK/dm/341 |  | 1 | Hire per Week | Hire per Week | 6.17
79 | E11/K149/MS/dm/396 |  | 1 | Erect & Dismantle | Lumpsum | 2448.62
80 | E11/K149/MS/dm/396 |  | 1 | Hire per Week | Hire per Week | 57.19
81 | E11/K149/PK/dm/400 | Design-Tas-1399-22 | 1 | Erect & Dismantle | Lumpsum | 15415.16
82 | E11/K149/PK/dm/400 | Design-Tas-1399-22 | 1 | Hire per Week | Hire per Week | 297.83
83 | E11/K149/PK/dm/378 | Design -Tas-1399-21 | 1 | Erect & Dismantle | Lumpsum | 11289.34
84 | E11/K149/PK/dm/378 | Design -Tas-1399-21 | 1 | Hire per Week | Hire per Week | 1429.84
85 | E11/K149/JA/dm/429 |  | 1 | Erect & Dismantle | Lumpsum | 13590.73
86 | E11/K149/JA/dm/429 |  | 1 | Hire per Week | Hire per Week | 302.12
87 | E11/K149/JJ/dm/377 | Design -Tas-1399-20a | 1 | Erect & Dismantle | Lumpsum | 32825.12
88 | E11/K149/JJ/dm/377 | Design -Tas-1399-20a | 1 | Hire per Week | Hire per Week | 2044.24
89 | E11/K149/SK/dm/468 |  | 1 | Erect & Dismantle | Lumpsum | 4760.74
90 | E11/K149/SK/dm/468 |  | 1 | Hire per Week | Hire per Week | 414.05
91 | E11/K149/MS/dm/497 | Design -Tas-1399-30&31 | 1 | Erect & Dismantle | Lumpsum | 13067.86
92 | E11/K149/MS/dm/497 | Design -Tas-1399-30&31 | 1 | Hire per Week | Hire per Week | 788.67
93 | E11/K149/SK/SR/517 | Design - Tas-1399-35b | 1 | Erect & Dismantle | Lumpsum | 3675.3
94 | E11/K149/SK/SR/517 | Design - Tas-1399-35b | 1 | Hire per Week | Hire per Week | 54.93
95 | E11/K149/SK/dm/480 | Design - Tas- 1399-25a | 1 | Erect & Dismantle | Lumpsum | 3562.04
96 | E11/K149/SK/dm/480 | Design - Tas- 1399-25a | 1 | Hire per Week | Hire per Week | 181.02
97 | E11/K149/SK/SR/503 | Design - Tas - 1399-29 | 1 | Erect & Dismantle | Lumpsum | 36307.15
98 | E11/K149/SK/SR/503 | Design - Tas - 1399-29 | 1 | Hire per Week | Hire per Week | 1384.55
99 | E11/K149/SK/SR/550 | Aluminium Tower |  | Erect & Dismantle | Set | 0
100 | E11/K149/SK/SR/550 | Aluminium Tower |  | Hire per Week | Set | 275
101 | E11/K149/SK/SR/560 | Aluminium Tower |  | Erect & Dismantle | Set | 0
102 | E11/K149/SK/SR/560 | Aluminium Tower |  | Hire per Week | Set | 275
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174

## Modification
Khansaheb Civil Engineering LLC
Application No.: | 4
Project Name: | Dorchester Hotel & Residences (Completion Works)
Order Reference: | 201A22002/49
As On Date: | 2022-12-25
Dayworks
DTS | Date | Hrs | Total | Previous | Net Amount
62652 | 2022-09-18 | 26 | 533 | 533 | 0
62653 | 2022-09-30 | 6 | 123 | 123 | 0
62654 | 2022-10-10 | 30 | 615 | 615 | 0
62655 | 2022-11-16 | 8 | 164 | 164 | 0
62657 | 2022-11-21 | 54 | 1107 | 1107 | 0
62658 | 2022-11-21 | 16 | 328 | 328 | 0
62661 | 2022-12-22 | 5 | 102.5 | 0 | 102.5
62662 | 2022-12-23 | 10 | 205 | 0 | 205
Total |  | 155 | 3177.5 | 1,271.00 | 307.5

## Manpower (hidden)
Client: | Khansaheb Civil Engineering LLC
Application No.: | 4
Project Name: | Dorchester Hotel & Residences (Completion Works)
Site: | #REF!
As Of: | 2022-12-25
Modification Hours
DTS | Date | Scaffolder | Foreman | Cumulative | Previous | Net
Total |  |  |  | 0 | 0 | 0

## SCOPE (hidden)
SCOPE OF WORKS & ADDITIONAL WORKS RATES
Reference | Description | Number | L | W | H | BL | Item Price | Period (Wks) | Extra Hire per Week

## PASummary (hidden)
Client: | Khansaheb Civil Engineering LLC
Project Name: | Dorchester Hotel & Residences (Completion Works)
Contract Ref: | 201A22002/49
PAYMENT APPLICATION SUMMARY
Application No. | Application Date | Works Carried Out | Day Works | Total | Remarks
1 | 2022-09-30 | 125287.35 | 0 | 125287.35
2 | 2022-10-31 | 221656.79 | 1,271.00 | 222927.79
3 | 2022-11-25 | 254058.2 | 1599 | 255657.2
0
0
0
0
0
Total |  | 601002.34 | 1599 | 603872.34 | 0