## PA Front Sheet
PAYMENT APPLICATION
Application # 6
Khansaheb Civil Engineering L.L.C. |  | Date | 2023-02-28 |  | HOTEL
PO Box - 2716 |  | Period As on | 2023-02-25 |  | RESIDENCE
Dubai |  | Type | Scaffolding Services
United Arab Emirates |  | Our Bankers | Bank Of Sharjah
Tel : 971 04 605 7200
Fax : 971 04 285 7539 |  | Account No. | 013 06 278065 01
Attn: Mr. Saman Kulasooriya
Dorchester Hotel & Residences (Completion Works) - 201A22002/49
Description |  | Previous Invoiced (AED) | This Application Value (AED) | Total Invoiced Net To Date (AED)
Contract Ref 201A22002/49
Scope Of Work |  | 478047.96 | 74660.06 | 552708.02
Variations |  | 859338.0705 | 212718.4995 | 1072056.57
Dayworks |  | 9163.5 | 4366.5 | 13530
*** From now on only 95% of Variations will paid until, OME approve the variations
Total |  | 1346549.5305 | 291745.0595 | 1638294.59
AED : three hundred two thousand six hundred twenty-eight and twenty-five Fils Only
(for Client use only) |  | Authorized Signatory
Technical Access Services LLC
The above amount is not inclusive of VAT
| KCE Claim | 1396036.15 | 302628.25 | 1698664.4
| Difference | -49486.6195 | -10883.1905 | -60369.81

## Evaluation
Invoice Schedule
Khansaheb Civil Engineering LLC
Application No.: | 6
Project Name: | Dorchester Hotel & Residences (Completion Works)
Order Reference: | 201A22002/49
As On Date: | 2023-02-25
Billing Reference | Location | Tag No. | HOC | OHC | Description | Founding Level | Scaffold Type | Number | Length | Width | Height | Board Lift | Unit of Measure | Quantity | HOC Date | OHC Date | Erection % | Hire % | Dismantle % | Hire Weeks | E&D Rate per unit | Hire Rate per week | Erect Charges | Hire Charges | Dismantle Charges | Total Amount | Previous Amount | Net Amount | Remarks
E11/K149/SK/dm/257 | HOTEL | 1 | 74602 |  | Level-28/29 Block & Glass Work | Level 28-29 | Design-1399-02 rev-D | 1 |  |  |  |  | unit | 1 | 2022-09-26 |  | 100% | 100% | 0% | 21.8571 | 50703.26 | 2807 | 35492.28 | 61353 | 0 | 96845.28 | 84414.28 | 12431 | Tas Quote-2439-4-3 rev1 | 2022-09-26 | TRUE
E11/K149/SK/dm/216 | RESIDENCE |  |  |  | Hire of Aluminium Tower | NA | NA | 1 |  |  |  |  | unit | 1 | 2022-09-15 | 2022-10-01 | 0% | 100% | 0% | 2.4286 | 0 | 200 | 0 | 485.71 | 0 | 485.71 | 485.71 | 0 | TAS/HIRE/4969/SM | #N/A | #N/A
CONTRACT - 201A22002/49 | RESIDENCE |  |  |  | Contract Scope - Progressive Billing |  |  | 1 |  |  |  |  | unit | 1 | 2022-09-20 | 2022-11-25 | 95% | 95% | 0% | 9.5714 | 191160 | 6716 | 0 | 0 | 0 | 0 | 0 | 0 |  | #N/A | #N/A
CONTRACT - 201A22002/49 | RESIDENCE |  |  |  | Contract Scope - Progressive Billing |  |  | 1 |  |  |  |  | unit | 1 | 2022-09-20 |  | 100% | 0% | 0% | 22.7143 | 256937.1474 |  | 179856 | 0 | 0 | 179856 | 179358.46 | 497.54 | Tas Quote -2439-2-2 rev1 | #N/A | #N/A
CONTRACT - 201A22002/49 | RESIDENCE |  |  |  | Item - 9,10,11,12 |  |  | 1 |  |  |  |  | unit | 1 | 2022-09-20 |  | 100% | 0% | 0% | 22.7143 | 80440 |  | 56308 | 0 | 0 | 56308 | 56308 | 0 | Tas Quote -2439-2-2 rev1 | #N/A | #N/A
CONTRACT - 201A22002/49 | RESIDENCE | 1 | 74652 |  | Glass Work | 29 to 31 | Design-1399-01 rev-G | 1 | 34.2 | 1.3 | 5 | 1 | m2-LxH | 171 | 2022-09-20 |  | 0% | 100% | 0% | 22.7143 | 0 | 0.49 | 0 | 1903.23 | 0 | 1903.23 | 1532.16 | 371.07 | Tas Quote -2439-2-2 rev1 | 2022-09-20 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 1 | 74652 |  | Glass Work | 29 to 31 | Design-1399-01 rev-G | 1 | 25.2 | 1.8 | 10.5 | 5 | m2-LxH | 264.6 | 2022-09-20 |  | 0% | 100% | 0% | 22.7143 | 0 | 0.77 | 0 | 4627.85 | 0 | 4627.85 | 3725.57 | 902.28 | Tas Quote -2439-2-2 rev1 | 2022-09-20 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 1 | 74652 |  | Glass Work | 29 to 31 | Design-1399-01 rev-G | 4 | 25.2 | 1.8 | 1 | 4 | m2-LxW | 181.44 | 2022-09-20 |  | 0% | 100% | 0% | 22.7143 | 0 | 0.7 | 0 | 2884.9 | 0 | 2884.9 | 2322.43 | 562.47 | Tas Quote -2439-2-2 rev1 | 2022-09-20 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 1 | 74652 |  | Glass Work | 29 to 31 | Design-1399-01 rev-G | 1 | 7.2 | 1.8 | 15.5 | 1 | m2-LxH | 111.6 | 2022-09-20 |  | 0% | 100% | 0% | 22.7143 | 0 | 0.77 | 0 | 1951.88 | 0 | 1951.88 | 1571.33 | 380.55 | Tas Quote -2439-2-2 rev1 | 2022-09-20 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 1 | 74652 |  | Glass Work | 29 to 31 | Design-1399-01 rev-G | 1 | 14.4 | 1.8 | 4.2 | 1 | m2-LxH | 60.48 | 2022-09-20 |  | 0% | 100% | 0% | 22.7143 | 0 | 0.77 | 0 | 1057.8 | 0 | 1057.8 | 851.56 | 206.24 | Tas Quote -2439-2-2 rev1 | 2022-09-20 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 1 | 74652 |  | Glass Work | 29 to 31 | Design-1399-01 rev-G | 1 | 14.4 | 1.8 | 6 | 2 | m2-LxH | 86.4 | 2022-09-20 |  | 0% | 100% | 0% | 22.7143 | 0 | 0.77 | 0 | 1511.14 | 0 | 1511.14 | 1216.51 | 294.63 | Tas Quote -2439-2-2 rev1 | 2022-09-20 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 1 | 74652 |  | Glass Work | 29 to 31 | Design-1399-01 rev-G | 1 | 14.4 | 1.8 | 1 | 1 | m2-LxW | 25.92 | 2022-09-20 |  | 0% | 100% | 0% | 22.7143 | 0 | 0.7 | 0 | 412.13 | 0 | 412.13 | 331.78 | 80.35 | Tas Quote -2439-2-2 rev1 | 2022-09-20 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 1g | 74656 |  | Glass Work | 29 to 31 | Design-1399-01 rev-G | 1 | 9 | 1.8 | 10.5 | 1 | m2-LxH | 94.5 | 2022-09-21 |  | 0% | 100% | 0% | 22.5714 | 0 | 0.77 | 0 | 1642.41 | 0 | 1642.41 | 1320.17 | 322.24 | Tas Quote -2439-2-2 rev1 | 2022-09-21 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 1m | 74674 |  | Glass Work | 29 to 31 | Design-1399-01 rev-G | 1 | 23.4 | 2.75 | 1 | 1 | m2-LxW | 64.35 | 2022-10-01 |  | 0% | 100% | 0% | 21.1429 | 0 | 6.72 | 0 | 9142.85 | 0 | 9142.85 | 7227.79 | 1915.06 | Tas Quote -2439-2-2 rev1 | 2022-10-01 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 1u | 79101 |  | Glass Work | 29 to 31 | Design-1399-01 rev-G | 1 | 20 | 2.75 | 1 | 1 | m2-LxW | 55 | 2022-12-06 |  | 0% | 100% | 0% | 11.7143 | 0 | 6.72 | 0 | 4329.6 | 0 | 4329.6 | 2692.8 | 1636.8 | Tas Quote -2439-2-2 rev1 | 2022-12-06 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 8w | 79146 |  | Glass Work | 29 to 31 | Design-1399-01 rev-G | 1 | 6 | 2.5 | 1 | 1 | m2-LxW | 15 | 2022-12-15 |  | 0% | 100% | 0% | 10.4286 | 0 | 6.72 | 0 | 1051.2 | 0 | 1051.2 | 604.8 | 446.4 | Tas Quote -2439-2-2 rev1 | 2022-12-15 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 1 | 74652 |  | Glass Work | 29 to 31 | H20 Beam - Bottom | 1 | 50.4 | 1.3 | 1 |  | m3 | 65.52 | 2022-09-20 |  | 0% | 100% | 0% | 22.7143 | 0 | 10.15 | 0 | 15105.64 | 0 | 15105.64 | 12160.51 | 2945.13 | Tas Quote -2439-2-2 rev1 | 2022-09-20 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 1 | 74652 |  | Glass Work | 29 to 31 | Hilti | 1 | 224 | 1 | 1 |  | lm | 224 | 2022-09-20 |  | 0% | 100% | 0% | 22.7143 | 0 | 17.15 | 0 | 87259.2 | 0 | 87259.2 | 70246.4 | 17012.8 | Tas Quote -2439-2-2 rev1 | 2022-09-20 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 3d | 79109 |  | Glass Work | 31to32 | Design-1399-03 | 1 | 20 | 2.75 | 1 | 1 | m2-LxW | 55 | 2022-12-07 |  | 0% | 100% | 0% | 11.5714 | 0 | 6.72 | 0 | 4276.8 | 0 | 4276.8 | 2640 | 1636.8 | Tas Quote -2439-2-2 rev1 | 2022-12-07 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 2h | 79158 |  | Glass Work | 31 | Design-1399-03 | 1 | 5 | 2.75 | 1 | 1 | m2-LxW | 13.75 | 2022-12-16 |  | 0% | 100% | 0% | 10.2857 | 0 | 6.72 | 0 | 950.4 | 0 | 950.4 | 541.2 | 409.2 | Tas Quote -2439-2-2 rev1 | 2022-12-16 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 3f | 79143 |  | Glass Work | 31 | Design-1399-03 | 1 | 12 | 2.75 | 1 | 1 | m2-LxW | 33 | 2022-12-14 |  | 0% | 100% | 0% | 10.5714 | 0 | 6.72 | 0 | 2344.32 | 0 | 2344.32 | 1362.24 | 982.08 | Tas Quote -2439-2-2 rev1 | 2022-12-14 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 3d | 79109 |  | Glass Work | 31to32 | Design-1399-03 | 1 | 12 | 5 | 1 | 1 | m2-LxW | 60 | 2022-12-07 |  | 0% | 100% | 0% | 11.5714 | 0 | 12.25 | 0 | 8505 | 0 | 8505 | 5250 | 3255 | Tas Quote -2439-2-2 rev1 | 2022-12-07 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 3f | 79143 |  | Glass Work | 31 | Design-1399-03 | 1 | 12 | 2.75 | 1 | 1 | m2-LxW | 33 | 2022-12-14 |  | 0% | 100% | 0% | 10.5714 | 0 | 8.61 | 0 | 3003.66 | 0 | 3003.66 | 1745.37 | 1258.29 | Tas Quote -2439-2-2 rev1 | 2022-12-14 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE |  |  |  | Glass Work | 31 | Sheeting-22 | 1 | 52 | 1 | 1 |  | m2-LxH | 52 | 2022-12-14 |  | 0% | 100% | 0% | 10.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Tas Quote -2439-2-2 rev1 | #N/A | #N/A
CONTRACT - 201A22002/49 | RESIDENCE | 8 | 77651 |  | Glass Work | Level 26 | Design-1399-04 | 1 | 6.8 | 1.8 | 4 | 1 | m2-LxH | 27.2 | 2022-10-10 |  | 0% | 100% | 0% | 19.8571 | 0 | 0.77 | 0 | 415.89 | 0 | 415.89 | 323.14 | 92.75 | Tas Quote -2439-2-2 rev1 | 2022-10-10 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 8a | 77651 |  | Glass Work | Level 26 to 31 | Design-1399-04 | 1 | 23.4 | 3.6 | 24 | 1 | m3 | 2021.76 | 2022-10-10 |  | 0% | 100% | 0% | 19.8571 | 0 | 0.49 | 0 | 19671.72 | 0 | 19671.72 | 15284.51 | 4387.21 | Tas Quote -2439-2-2 rev1 | 2022-10-10 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 8b | 77651 |  | Glass Work | Level 26 | Design-1399-04 | 1 | 18.6 | 0.6 | 4 | 1 | m2-LxH | 74.4 | 2022-10-10 |  | 0% | 100% | 0% | 19.8571 | 0 | 0.49 | 0 | 723.91 | 0 | 723.91 | 562.46 | 161.45 | Tas Quote -2439-2-2 rev1 | 2022-10-10 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 8c | 77651 |  | Glass Work | Level 26 | Design-1399-04 | 1 | 10.8 | 0.6 | 4 | 1 | m2-LxH | 43.2 | 2022-10-10 |  | 0% | 100% | 0% | 19.8571 | 0 | 0.49 | 0 | 420.34 | 0 | 420.34 | 326.59 | 93.75 | Tas Quote -2439-2-2 rev1 | 2022-10-10 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 8d | 77651 |  | Glass Work | Level 26 | Design-1399-04 | 1 | 6.8 | 0.9 | 4 | 1 | m2-LxH | 27.2 | 2022-10-10 |  | 0% | 100% | 0% | 19.8571 | 0 | 0.49 | 0 | 264.66 | 0 | 264.66 | 205.63 | 59.03 | Tas Quote -2439-2-2 rev1 | 2022-10-10 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 8e | 77651 |  | Glass Work | Level 26 to 31 | Design-1399-04 | 6 | 23.4 | 0.5 | 1 | 6 | m2-LxW | 70.2 | 2022-10-10 |  | 0% | 100% | 0% | 19.8571 | 0 | 1.05 | 0 | 1463.67 | 0 | 1463.67 | 1137.24 | 326.43 | Tas Quote -2439-2-2 rev1 | 2022-10-10 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 8f | 77651 |  | Glass Work | Level 26 to 31 | Design-1399-04 | 5 | 23.4 | 1.8 | 1 | 5 | m2-LxW | 210.6 | 2022-10-10 |  | 0% | 100% | 0% | 19.8571 | 0 | 0.7 | 0 | 2927.34 | 0 | 2927.34 | 2274.48 | 652.86 | Tas Quote -2439-2-2 rev1 | 2022-10-10 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 8g | 77651 |  | Glass Work | Level 26 | Design-1399-04 | 1 | 22.5 | 2.5 | 9 |  | m3 | 506.25 | 2022-10-10 |  | 0% | 100% | 0% | 19.8571 | 0 | 0.35 | 0 | 3518.44 | 0 | 3518.44 | 2733.75 | 784.69 | Tas Quote -2439-2-2 rev1 | 2022-10-10 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 1p | 77528 |  | Glass Work | Level 3 to 31 | Design-1399-04 | 1 | 5 | 1.8 | 8.8 | 1 | m2-LxH | 44 | 2022-11-23 |  | 0% | 100% | 0% | 13.5714 | 0 | 0.77 | 0 | 459.8 | 0 | 459.8 | 309.76 | 150.04 | Tas Quote -2439-2-2 rev1 | 2022-11-23 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 1q | 77528 |  | Glass Work | Level 3 to 31 | Design-1399-04 | 1 | 7 | 2.75 | 1 | 1 | m2-LxW | 19.25 | 2022-11-23 |  | 0% | 100% | 0% | 13.5714 | 0 | 6.72 | 0 | 1755.6 | 0 | 1755.6 | 1182.72 | 572.88 | Tas Quote -2439-2-2 rev1 | 2022-11-23 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 8 | 77651 |  | Glass Work | Level 26 | Design-1399-04 | 1 | 152.4 | 1 | 1 |  | lm | 152.4 | 2022-10-10 |  | 0% | 100% | 0% | 19.8571 | 0 | 1.4 | 0 | 4236.72 | 0 | 4236.72 | 3291.84 | 944.88 | Tas Quote -2439-2-2 rev1 | 2022-10-10 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 8 | 77651 |  | Glass Work | Level 26 | Sheeting | 1 | 280.8 | 1 | 1 |  | m2-LxH | 280.8 | 2022-10-10 |  | 0% | 100% | 0% | 19.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Tas Quote -2439-2-2 rev1 | 2022-10-10 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 8 | 77651 |  | Glass Work | Level 26 | Hilti | 1 | 80 | 1 | 1 |  | lm | 80 | 2022-10-10 |  | 0% | 100% | 0% | 19.8571 | 0 | 17.15 | 0 | 27244 | 0 | 27244 | 21168 | 6076 | Tas Quote -2439-2-2 rev1 | 2022-10-10 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 8l | 77660 |  | Glass Lifting Frame | Level 26 | Design-1399-04 | 1 | 6 | 1 | 1 |  | lm | 6 | 2022-10-10 |  | 0% | 100% | 0% | 19.8571 | 0 | 1.4 | 0 | 166.8 | 0 | 166.8 | 129.6 | 37.2 | Tas Quote -2439-2-2 rev1 | 2022-10-10 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 2 | 74661 |  | Ceiling Work | Level 30 | Design -1399-05 | 1 | 21.1 | 9 | 9.2 | 1 | m3 | 1747.08 | 2022-09-22 |  | 0% | 100% | 0% | 22.4286 | 0 | 0.49 | 0 | 19200.41 | 0 | 19200.41 | 15409.25 | 3791.16 | Tas Quote -2439-2-2 rev1 | 2022-09-22 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 3 | 74667 |  | Ceiling Work | Level 29 | Design -1399-05 | 1 | 22.9 | 3.4 | 14 | 1 | m3 | 1090.04 | 2022-09-27 |  | 0% | 100% | 0% | 21.7143 | 0 | 0.49 | 0 | 11598.03 | 0 | 11598.03 | 9232.64 | 2365.39 | Tas Quote -2439-2-2 rev1 | 2022-09-27 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 3 | 74667 |  | Ceiling Work | Level 30 | Design -1399-05 | 1 | 22.9 | 7.2 | 7.5 | 1 | m3 | 1236.6 | 2022-09-27 |  | 0% | 100% | 0% | 21.7143 | 0 | 0.49 | 0 | 13157.42 | 0 | 13157.42 | 10474 | 2683.42 | Tas Quote -2439-2-2 rev1 | 2022-09-27 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 3 | 74667 |  | Ceiling Work | Level 30 | Design -1399-05 | 1 | 72 | 11 | 1 |  | lm | 72 | 2022-09-27 |  | 0% | 100% | 0% | 21.7143 | 0 | 1.4 | 0 | 2188.8 | 0 | 2188.8 | 1742.4 | 446.4 | Tas Quote -2439-2-2 rev1 | 2022-09-27 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 3 | 74667 |  | Ceiling Work | Level 30 | H20 Beam - Bottom | 1 | 22.9 | 2.4 | 1 |  | m3 | 54.96 | 2022-09-27 |  | 0% | 100% | 0% | 21.7143 | 0 | 10.15 | 0 | 12113.18 | 0 | 12113.18 | 9642.73 | 2470.45 | Tas Quote -2439-2-2 rev1 | 2022-09-27 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 10 | 74681 |  | Back Propping | Level 28 | Design - 1399-15 | 1 | 24.7 | 1.3 | 4.2 | 1 | m2-LxH | 103.74 | 2022-10-12 |  | 0% | 100% | 0% | 19.5714 | 0 | 0.49 | 0 | 994.87 | 0 | 994.87 | 769.75 | 225.12 | Tas Quote -2439-2-2 rev1 | 2022-10-12 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 10 | 74681 |  | Back Propping | Level 28 | H20 Beam - Bottom | 1 | 24.7 | 1.3 | 1 |  | m3 | 32.11 | 2022-10-12 |  | 0% | 100% | 0% | 19.5714 | 0 | 10.15 | 0 | 6378.65 | 0 | 6378.65 | 4935.31 | 1443.34 | Tas Quote -2439-2-2 rev1 | 2022-10-12 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 9 | 74680 |  | Back Propping | Level 29 | Design -1399-16 | 1 | 18.8 | 3.6 | 4.7 |  | m3 | 318.1 | 2022-10-12 |  | 0% | 100% | 0% | 19.5714 | 0 | 0.49 | 0 | 3050.58 | 0 | 3050.58 | 2360.3 | 690.28 | Tas Quote -2439-2-2 rev1 | 2022-10-12 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 9 | 74680 |  | Back Propping | Level 29 | H20 Beam - Bottom | 1 | 18.8 | 3.6 | 1 |  | m3 | 67.68 | 2022-10-12 |  | 0% | 100% | 0% | 19.5714 | 0 | 10.15 | 0 | 13444.63 | 0 | 13444.63 | 10402.42 | 3042.21 | Tas Quote -2439-2-2 rev1 | 2022-10-12 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 108 | 77542 |  | Canal side Balcony Back Propping | Level 27 to 28 | Design -1399-28 | 1 | 12.6 | 1.3 | 8.8 | 1 | m2-LxH | 110.88 | 2022-11-30 |  | 0% | 100% | 0% | 12.5714 | 0 | 0.49 | 0 | 683.02 | 0 | 683.02 | 442.41 | 240.61 | Tas Quote -2439-2-2 rev1 | 2022-11-30 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 108 | 77542 |  | Canal side Balcony Back Propping | Level 27 to 28 | H20 Beam - Bottom | 1 | 12.6 | 1.3 | 1 |  | m3 | 16.38 | 2022-11-30 |  | 0% | 100% | 0% | 12.5714 | 0 | 10.15 | 0 | 2090.09 | 0 | 2090.09 | 1353.81 | 736.28 | Tas Quote -2439-2-2 rev1 | 2022-11-30 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 109&a | 77543 |  | Canal side Balcony Back Propping | Level 27 | Design -1399-28 | 1 | 3.6 | 1.8 | 3 |  | m2-LxH | 10.8 | 2022-11-30 |  | 0% | 100% | 0% | 12.5714 | 0 | 0.49 | 0 | 66.53 | 0 | 66.53 | 43.09 | 23.44 | Tas Quote -2439-2-2 rev1 | 2022-11-30 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 109&a | 77542 |  | Canal side Balcony Back Propping | Level 27 | H20 Beam - Bottom | 1 | 3.6 | 1.3 | 1 |  | m3 | 4.68 | 2022-11-30 |  | 0% | 0% | 0% | 12.5714 | 0 | 10.15 | 0 | 0 | 0 | 0 | 0 | 0 | Tas Quote -2439-2-2 rev1 | 2022-11-30 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 109&a | 77542 |  | Canal side Balcony Back Propping | Level 27 | H20 Beam - Bottom | 1 | 3.6 | 1.8 | 1 |  | m3 | 6.48 | 2022-11-30 |  | 0% | 0% | 0% | 12.5714 | 0 | 10.15 | 0 | 0 | 0 | 0 | 0 | 0 | Tas Quote -2439-2-2 rev1 | 2022-11-30 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 3e | 79142 |  | Canopy Work | Level 31 | Design -1399 -19 | 1 | 11 | 3.5 | 1 | 1 | m2-LxW | 38.5 | 2022-12-14 |  | 0% | 100% | 0% | 10.5714 | 0 | 8.61 | 0 | 3504.27 | 0 | 3504.27 | 2036.27 | 1468 | Tas Quote -2439-2-2 rev1 | 2022-12-14 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 3e | 79142 |  | Canopy Work | Level 31 | Design -1399 -19 | 6 | 10.8 | 1 | 1 |  | lm | 64.8 | 2022-12-14 |  | 0% | 100% | 0% | 10.5714 | 0 | 1.4 | 0 | 959.04 | 0 | 959.04 | 557.28 | 401.76 | Tas Quote -2439-2-2 rev1 | 2022-12-14 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 3e | 79142 |  | Canopy Work | Level 31 | Design -1399 -19 | 12 | 6 | 1 | 1 |  | lm | 72 | 2022-12-14 |  | 0% | 100% | 0% | 10.5714 | 0 | 1.4 | 0 | 1065.6 | 0 | 1065.6 | 619.2 | 446.4 | Tas Quote -2439-2-2 rev1 | 2022-12-14 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 3e | 79142 |  | Canopy Work | Level 31 | Design -1399 -19 | 1 | 8 | 2.6 | 1 |  | m2-LxW | 20.8 | 2022-12-14 |  | 0% | 100% | 0% | 10.5714 | 0 | 6.37 | 0 | 1400.67 | 0 | 1400.67 | 813.9 | 586.77 | Tas Quote -2439-2-2 rev1 | 2022-12-14 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 3c | 79108 |  | Canopy Work | Level 31 to 32 | Design -1399 -19 | 6 | 10.8 | 1 | 1 |  | lm | 64.8 | 2022-12-07 |  | 0% | 100% | 0% | 11.5714 | 0 | 1.4 | 0 | 1049.76 | 0 | 1049.76 | 108 | 941.76 | Tas Quote -2439-2-2 rev1 | 2022-12-07 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 3c | 79108 |  | Canopy Work | Level 31 to 32 | Design -1399 -19 | 1 | 8 | 5 | 1 |  | m2-LxW | 40 | 2022-12-07 |  | 0% | 100% | 0% | 11.5714 | 0 | 12.25 | 0 | 5670 | 0 | 5670 | 3500 | 2170 | Tas Quote -2439-2-2 rev1 | 2022-12-07 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 3c | 79108 |  | Canopy Work | Level 31 to 32 | Design -1399 -19 | 12 | 6 | 1 | 1 |  | lm | 72 | 2022-12-07 |  | 0% | 100% | 0% | 11.5714 | 0 | 1.4 | 0 | 1166.4 | 0 | 1166.4 | 720 | 446.4 | Tas Quote -2439-2-2 rev1 | 2022-12-07 | TRUE
CONTRACT - 201A22002/49 | RESIDENCE | 3c | 79108 |  | Canopy Work | Level 31 to 32 | Design -1399 -19 | 1 | 8 | 2.6 | 1 |  | m2-LxW | 20.8 | 2022-12-07 |  | 0% | 100% | 0% | 11.5714 | 0 | 6.37 | 0 | 1533.17 | 0 | 1533.17 | 946.4 | 586.77 | Tas Quote -2439-2-2 rev1 | 2022-12-07 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 1b | 74653 | 76751 | Glass Channel Fixing | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 25.2 | 1.2 | 1 | 1 | m2-LxW | 30.24 | 2022-09-20 | 2022-09-26 | 100% | 100% | 100% | 1 | 36.52 | 2.94 | 773.06 | 88.91 | 331.31 | 1193.28 | 1193.28 | 0 |  | 2022-09-20 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 1f | 74654 |  | Glass Channel Fixing | Level 29 | Cantilever (0 < 0.5m width) | 1 | 5 | 0.5 | 1 | 1 | m2-LxW | 2.5 | 2022-09-20 |  | 100% | 100% | 0% | 22.7143 | 32.75 | 1.05 | 57.31 | 59.63 | 0 | 116.94 | 105.31 | 11.63 |  | 2022-09-20 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 1h | 74655 | 76752 | Glass Channel Fixing | Level 30 | Cantilever (0 < 0.5m width) | 1 | 16.2 | 0.5 | 1 | 1 | m2-LxW | 8.1 | 2022-09-21 | 2022-09-27 | 100% | 100% | 100% | 1 | 32.75 | 1.05 | 185.69 | 8.51 | 79.58 | 273.78 | 273.78 | 0 |  | 2022-09-21 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 1i | 74660 | 76753 | Glass Channel Fixing | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 1.8 | 1 | 1 | 1 | m2-LxW | 1.8 | 2022-09-24 | 2022-09-26 | 100% | 100% | 100% | 0.42857 | 36.52 | 2.94 | 46.02 | 2.27 | 19.72 | 68.01 | 68.01 | 0 |  | 2022-09-24 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 1j | 74666 | 76754 | Glass Channel Fixing | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 23.4 | 0.75 | 1 | 1 | m2-LxW | 17.55 | 2022-09-26 | 2022-09-28 | 100% | 100% | 100% | 0.42857 | 36.52 | 2.94 | 448.65 | 22.11 | 192.28 | 663.04 | 663.04 | 0 |  | 2022-09-26 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 1k | 74670 |  | Glass Channel Fixing | Level 30 | Cantilever (0 < 0.5m width) | 2 | 9.8 | 0.5 | 1 | 1 | m2-LxW | 9.8 | 2022-09-28 |  | 100% | 100% | 0% | 21.5714 | 32.75 | 1.05 | 224.67 | 221.97 | 0 | 446.64 | 401.07 | 45.57 |  | 2022-09-28 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 1l | 74671 |  | Glass Channel Fixing | Level 30 | Cantilever (0 < 0.5m width) | 1 | 13.8 | 0.5 | 1 | 1 | m2-LxW | 6.9 | 2022-09-28 |  | 100% | 100% | 0% | 21.5714 | 32.75 | 1.05 | 158.18 | 156.29 | 0 | 314.47 | 282.38 | 32.09 |  | 2022-09-28 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 2a | 74662 |  | Glass Channel Fixing | Level 30 | Additional Boarding | 4 | 10.8 | 1.8 | 1 | 4 | m2-LxW | 77.76 | 2022-09-22 |  | 100% | 100% | 0% | 22.4286 | 6.63 | 0.7 | 360.88 | 1220.83 | 0 | 1581.71 | 1340.66 | 241.05 |  | 2022-09-22 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 2b | 74663 | 76758 | Colum G-3 Painting Works | Level 30 | Additional Boarding | 4 | 3.6 | 3.6 | 1 | 4 | m2-LxW | 51.84 | 2022-09-22 | 2022-10-15 | 100% | 100% | 100% | 3.4286 | 6.63 | 0.7 | 240.59 | 124.42 | 103.11 | 468.12 | 468.12 | 0 |  | 2022-09-22 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 2c | 74664 | 76759 | Colum F-3 Painting Works | Level 30 | Additional Boarding | 4 | 3.6 | 3.6 | 1 | 4 | m2-LxW | 51.84 | 2022-09-22 | 2022-10-15 | 100% | 100% | 100% | 3.4286 | 6.63 | 0.7 | 240.59 | 124.42 | 103.11 | 468.12 | 468.12 | 0 |  | 2022-09-22 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 2d | 74665 | 76760 | Colum D-3 Painting Works | Level 30 | Additional Boarding | 4 | 3.6 | 3.6 | 1 | 4 | m2-LxW | 51.84 | 2022-09-22 | 2022-10-15 | 100% | 100% | 100% | 3.4286 | 6.63 | 0.7 | 240.59 | 124.42 | 103.11 | 468.12 | 468.12 | 0 |  | 2022-09-22 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 3a | 74668 | 76761 | Colum D-2 Painting Works | Level 29 | Additional Boarding | 6 | 3.5 | 3.5 | 1 | 6 | m2-LxW | 73.5 | 2022-09-27 | 2022-10-15 | 100% | 100% | 100% | 2.7143 | 6.63 | 0.7 | 341.11 | 139.65 | 146.19 | 626.95 | 626.95 | 0 |  | 2022-09-27 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 3b | 74669 | 76762 | Colum F-G/2 Painting Works | Level 29 | Additional Boarding | 6 | 9 | 3.5 | 1 | 6 | m2-LxW | 189 | 2022-09-27 | 2022-10-15 | 100% | 100% | 100% | 2.7143 | 6.63 | 0.7 | 877.15 | 359.1 | 375.92 | 1612.17 | 1612.17 | 0 |  | 2022-09-27 | TRUE
E11/K149/SK/dm/239 | RESIDENCE | 4 | 74673 | 76788 | EIFS Removel & Reinstate Works | Ramp | Design-1399-07 rev-B | 1 |  |  |  |  | unit | 1 | 2022-10-01 | 2022-11-05 | 100% | 100% | 100% | 5.1429 | 15626.48 | 625.97 | 10938.54 | 3219.27 | 4687.94 | 18845.75 | 18845.75 | 0 | Tas Quote - 2439-8-2 | 2022-10-01 | TRUE
E11/K149/SK/dm/238 | RESIDENCE | 5 | 74675 | 76768 | Level -30 Lobby Room Shaft-09 | Level 30 | Design -1399-10 rev-A | 1 |  |  |  |  | unit | 1 | 2022-10-03 | 2022-10-22 | 100% | 100% | 100% | 2.8571 | 5727.13 | 317.71 | 4008.99 | 907.74 | 1718.14 | 6634.87 | 6634.87 | 0 | Tas Quote - 2439-5-1 | 2022-10-03 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 2e | 74676 | 76755 | Level - 30 Balcony Side Glass frame work | Level 30 | Additional Boarding | 1 | 3.6 | 1.8 | 1 | 1 | m2-LxW | 6.48 | 2022-10-04 | 2022-10-07 | 100% | 100% | 100% | 0.57143 | 6.63 | 0.7 | 30.07 | 2.59 | 12.89 | 45.55 | 45.55 | 0 |  | 2022-10-04 | TRUE
E11/K149/HN/dm/285 | RESIDENCE | 6 | 74677 | 80851 | Loading Bay Above Planter Trench | Ground Level | Design -1399-12 rev-A | 1 |  |  |  |  | unit | 1 | 2022-10-10 | 2023-01-02 | 100% | 100% | 100% | 12.1429 | 4959.77 | 123.48 | 3471.84 | 1499.4 | 1487.93 | 6459.17 | 6459.17 | 0 | Tas Quote - 2439-10-1 | 2022-10-10 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 7 | 74678 | 80573 | Level -4 Planter Box Soil Filling | Level 4 | Independent | 1 | 15 | 1.5 | 0.8 | 1 | m2-LxH | 12 | 2022-10-10 | 2022-12-16 | 100% | 100% | 100% | 9.7143 | 12.01 | 0.49 | 100.88 | 57.12 | 43.24 | 201.24 | 201.24 | 0 |  | 2022-10-10 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 8h | 74679 | 76756 | Pool Area Glass work | Level 26 | Additional Boarding | 1 | 4 | 1 | 1 | 1 | m2-LxW | 4 | 2022-10-10 | 2022-10-11 | 100% | 100% | 100% | 0.28571 | 6.63 | 0.7 | 18.56 | 0.8 | 7.96 | 27.32 | 27.32 | 0 |  | 2022-10-10 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 8i | 74682 |  | Level -30 Glass Frame work | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 19 | 0.75 | 1 | 1 | m2-LxW | 14.25 | 2022-10-12 |  | 100% | 100% | 0% | 19.5714 | 36.52 | 2.94 | 364.29 | 819.95 | 0 | 1184.24 | 998.7 | 185.54 |  | 2022-10-12 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 8j | 74683 | 76764 | Level -30 Glass Frame work | Level 30 | Cantilever (0 < 0.5m width) | 1 | 19.8 | 0.5 | 1 | 1 | m2-LxW | 9.9 | 2022-10-12 | 2022-10-21 | 100% | 100% | 100% | 1.4286 | 32.75 | 1.05 | 226.96 | 14.85 | 97.27 | 339.08 | 339.08 | 0 |  | 2022-10-12 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 11 | 74684 | 76757 | Level -30 Shaft Mep Services | Level 30 | Independent | 1 | 3.6 | 1.2 | 2.5 | 1 | m2-LxH | 9 | 2022-10-13 | 2022-10-15 | 100% | 100% | 100% | 0.42857 | 12.01 | 0.49 | 75.66 | 1.89 | 32.43 | 109.98 | 109.98 | 0 |  | 2022-10-13 | TRUE
E11/K149/HN/dm/285 | RESIDENCE | 12 | 74685 | 80889 | Loading Bay Above Planter Trench | Ground Level | Design -1399-12 rev-A | 1 |  |  |  |  | unit | 1 | 2022-10-14 | 2023-01-17 | 100% | 100% | 100% | 13.7143 | 4959.77 | 123.48 | 3471.84 | 1693.44 | 1487.93 | 6653.21 | 6653.21 | 0 | Tas Quote - 2439-10-1 | 2022-10-14 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 13 | 74686 | 80503 | Pool Plant Room (KMEP Work) | Level 3 | Independent | 1 | 7.3 | 1.3 | 1.7 | 1 | m2-LxH | 12.41 | 2022-10-14 | 2022-11-10 | 100% | 100% | 100% | 4 | 12.01 | 0.49 | 104.33 | 24.32 | 44.71 | 173.36 | 173.36 | 0 | KMEP | 2022-10-14 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 14 | 74687 | 76763 | Colum Nut bolt Installation | Level 3 | Independent | 1 | 5.1 | 1.3 | 1.6 | 1 | m2-LxH | 8.16 | 2022-10-15 | 2022-10-17 | 100% | 100% | 100% | 0.42857 | 12.01 | 0.49 | 68.6 | 1.71 | 29.4 | 99.71 | 99.71 | 0 |  | 2022-10-15 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 15 | 74688 | 80504 | Pool Plant Room (KMEP Work) | Level 3 | Independent | 1 | 5 | 1.2 | 2 | 1 | m2-LxH | 10 | 2022-10-17 | 2022-11-10 | 100% | 100% | 100% | 3.5714 | 12.01 | 0.49 | 84.07 | 17.5 | 36.03 | 137.6 | 137.6 | 0 | KMEP | 2022-10-17 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 16 | 74689 | 76766 | Shaft -6 Kmep Duct Extension | Level 31 | Tower | 1 | 2.5 | 1.8 | 2.3 | 1 | rm | 2.3 | 2022-10-17 | 2022-10-22 | 100% | 100% | 100% | 0.85714 | 63.34 | 7.28 | 101.98 | 14.35 | 43.7 | 160.03 | 160.03 | 0 | KMEP | 2022-10-17 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 16 | 74689 | 76766 | Shaft -6 Kmep Duct Extension | Level 31 | Additional Boarding | 1 | 2.5 | 1.8 | 1 | 1 | m2-LxW | 4.5 | 2022-10-17 | 2022-10-22 | 100% | 100% | 100% | 0.85714 | 6.63 | 0.7 | 20.88 | 2.7 | 8.95 | 32.53 | 32.53 | 0 | KMEP | 2022-10-17 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 17 | 74690 | 76769 | Level -2 Retail Unit 34 For (Kmep) | Level 2 | Birdcage | 1 | 17.5 | 10 | 6.2 | 1 | m3 | 1085 | 2022-10-18 | 2022-10-26 | 100% | 100% | 100% | 1.2857 | 7.08 | 0.49 | 5377.26 | 683.55 | 2304.54 | 8365.35 | 8365.35 | 0 | KMEP | 2022-10-18 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 18 | 74691 | 80506 | Basement 1 (Kmep work) | Basement 1 | Tower | 1 | 1.8 | 1.3 | 2.5 | 1 | rm | 2.5 | 2022-10-18 | 2022-11-12 | 100% | 100% | 100% | 3.7143 | 63.34 | 7.28 | 110.85 | 67.6 | 47.51 | 225.96 | 225.96 | 0 | KMEP | 2022-10-18 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 19 | 74692 | 80535 | Staircase -4 For Water coring tank work | Level 31 | Independent | 1 | 4 | 1.3 | 6.3 | 1 | m2-LxH | 25.2 | 2022-10-18 | 2022-11-28 | 100% | 100% | 100% | 6 | 12.01 | 0.49 | 211.86 | 74.09 | 90.8 | 376.75 | 376.75 | 0 |  | 2022-10-18 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 19a | 74700 | 76793 | Staircase -4 For Water coring tank work | Level 31 | Independent | 1 | 4 | 1.3 | 2 | 1 | m2-LxH | 8 | 2022-10-19 | 2022-11-05 | 100% | 100% | 100% | 2.5714 | 12.01 | 0.49 | 67.26 | 10.08 | 28.82 | 106.16 | 106.16 | 0 |  | 2022-10-19 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 20 | 74693 | 80515 | Basement 1 (Kmep work) | Basement 1 | Tower | 1 | 2.5 | 2.5 | 3 | 1 | rm | 3 | 2022-10-18 | 2022-11-15 | 100% | 100% | 100% | 4.1429 | 63.34 | 7.28 | 133.01 | 90.48 | 57.01 | 280.5 | 280.5 | 0 |  | 2022-10-18 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 16a | 74694 | 76767 | Second Lift Duct Extension work | Level 31 | Tower | 1 | 2.5 | 1.8 | 2 | 1 | rm | 2 | 2022-10-19 | 2022-10-22 | 100% | 100% | 100% | 0.57143 | 63.34 | 7.28 | 88.68 | 8.32 | 38 | 135 | 135 | 0 |  | 2022-10-19 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 1n | 74695 | 76771 | Fire Fifhting Sprinkler Work | Level 31 | Additional Boarding | 1 | 11.5 | 1.8 | 1 | 1 | m2-LxW | 20.7 | 2022-10-19 | 2022-10-26 | 100% | 100% | 100% | 1.1429 | 6.63 | 0.7 | 96.07 | 16.56 | 41.17 | 153.8 | 153.8 | 0 |  | 2022-10-19 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 21 | 74696 | 76792 | Basement 1 (Kmep work) | Basement 1 | Tower | 1 | 2.5 | 1.8 | 3 | 1 | rm | 3 | 2022-10-19 | 2022-11-07 | 100% | 100% | 100% | 2.8571 | 63.34 | 7.28 | 133.01 | 62.4 | 57.01 | 252.42 | 252.42 | 0 | KMEP | 2022-10-19 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 22 | 74697 | 76776 | Basement 1 (Kmep work) | Basement 1 | Independent | 1 | 3.1 | 1.3 | 3 | 1 | m2-LxH | 9.3 | 2022-10-19 | 2022-11-02 | 100% | 100% | 100% | 2.1429 | 12.01 | 0.49 | 78.19 | 9.77 | 33.51 | 121.47 | 121.47 | 0 | KMEP | 2022-10-19 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 23 | 74698 | 80538 | Basement 1 (Kmep work) | Basement 1 | Independent 1.8m wide | 1 | 3.1 | 1.8 | 4.5 | 1 | m2-LxH | 13.95 | 2022-10-19 | 2022-11-26 | 100% | 100% | 100% | 5.5714 | 12.01 | 0.77 | 117.28 | 59.85 | 50.26 | 227.39 | 227.39 | 0 | KMEP | 2022-10-19 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 24 | 74699 | 80516 | Basement 1 (Kmep work) | Basement 1 | Tower | 1 | 2.5 | 2.5 | 4.5 | 1 | rm | 4.5 | 2022-10-19 | 2022-11-15 | 100% | 100% | 100% | 4 | 63.34 | 7.28 | 199.52 | 131.04 | 85.51 | 416.07 | 416.07 | 0 | KMEP | 2022-10-19 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 25 | 77652 | 76777 | Basement 1 (Kmep work) | Basement 1 | Independent 1.8m wide | 1 | 3.8 | 2.5 | 4.5 | 1 | m2-LxH | 17.1 | 2022-10-19 | 2022-11-02 | 100% | 100% | 100% | 2.1429 | 16.76 | 0.77 | 200.62 | 28.22 | 85.98 | 314.82 | 314.82 | 0 | KMEP | 2022-10-19 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 8k | 77653 | 76775 | Glass Channel Fixing | Level 31 | Cantilever (0 < 0.5m width) | 1 | 18 | 0.5 | 1 | 1 | m2-LxW | 9 | 2022-10-19 | 2022-10-29 | 100% | 100% | 100% | 1.5714 | 32.75 | 1.05 | 206.33 | 14.85 | 88.43 | 309.61 | 309.61 | 0 |  | 2022-10-19 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 26 | 77654 | 80501 | Mockup For Bracket Fixing | Level 6 | Tower | 1 | 1.8 | 1 | 2 | 1 | rm | 2 | 2022-10-19 | 2022-11-04 | 100% | 100% | 100% | 2.4286 | 63.34 | 7.28 | 88.68 | 35.36 | 38 | 162.04 | 162.04 | 0 |  | 2022-10-19 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 27 | 77655 | 80525 | Basement 1 (Kmep work) | Basement 1 | Independent | 1 | 5 | 1.3 | 4.5 | 1 | m2-LxH | 22.5 | 2022-10-19 | 2022-11-16 | 100% | 100% | 100% | 4.1429 | 12.01 | 0.49 | 189.16 | 45.68 | 81.07 | 315.91 | 315.91 | 0 | KMEP | 2022-10-19 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 28 | 77656 | 80507 | Basement 1 (Kmep work) | Basement 1 | Tower | 1 | 2.5 | 1.8 | 4.5 | 1 | rm | 4.5 | 2022-10-20 | 2022-11-11 | 100% | 100% | 100% | 3.2857 | 63.34 | 7.28 | 199.52 | 107.64 | 85.51 | 392.67 | 392.67 | 0 | KMEP | 2022-10-20 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 28 | 77656 | 80507 | Basement 1 (Kmep work) | Basement 1 | Additional Boarding | 1 | 2.5 | 1.8 |  | 1 | m2-LxW | 4.5 | 2022-10-20 | 2022-11-11 | 100% | 100% | 100% | 3.2857 | 6.63 | 0.7 | 20.88 | 10.35 | 8.95 | 40.18 | 40.18 | 0 | KMEP | 2022-10-20 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 29 | 77657 | 80557 | Basement 1 (Kmep work) | Basement 1 | Tower | 1 | 2.5 | 1.8 | 4.5 | 1 | rm | 4.5 | 2022-10-20 | 2022-12-10 | 100% | 100% | 100% | 7.4286 | 63.34 | 7.28 | 199.52 | 243.36 | 85.51 | 528.39 | 528.39 | 0 | KMEP | 2022-10-20 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 2g | 77661 | 76774 | Glass Fixing work | Level 30 | Cantilever (0 < 0.5m width) | 1 | 10.8 | 0.5 | 1 | 1 | m2-LxW | 5.4 | 2022-10-21 | 2022-10-29 | 100% | 100% | 100% | 1.2857 | 32.75 | 1.05 | 123.8 | 7.29 | 53.06 | 184.15 | 184.15 | 0 |  | 2022-10-21 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 2f | 77662 |  | Glass Fixing work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 3.6 | 0.75 | 1 | 1 | m2-LxW | 2.7 | 2022-10-21 |  | 100% | 100% | 0% | 18.2857 | 36.52 | 2.94 | 69.02 | 145.15 | 0 | 214.17 | 179.02 | 35.15 |  | 2022-10-21 | TRUE
E11/K149/SK/dm/365 | RESIDENCE | 30 | 77667 | 80865 | EIFS Fixing Work | Level 23 | Independent | 1 | 4 | 1.3 | 2 | 1 | unit | 1 | 2022-10-21 | 2023-01-04 | 100% | 100% | 100% | 10.8571 | 916.08 | 3.92 | 641.26 | 42.56 | 274.82 | 958.64 | 958.64 | 0 | Tas Quote - 2439-14-1 (item-1) | 2022-10-21 | TRUE
E11/K149/SK/dm/365 | RESIDENCE | 30a | 77668 | 80867 | EIFS Fixing Work | Level 23 | Independent | 1 | 8 | 1.3 | 3 | 2 | unit | 1 | 2022-10-21 | 2023-01-04 | 100% | 100% | 100% | 10.8571 | 2093.27 | 22.96 | 1465.29 | 249.28 | 627.98 | 2342.55 | 2342.55 | 0 | Tas Quote - 2439-14-1 (item-2) | 2022-10-21 | TRUE
E11/K149/SK/dm/350 | RESIDENCE | 31 | 77669 |  | Above Air Extract trench Loading Bay | Ground Level | Design 1399-14 | 1 | 22.5 | 3.6 |  | 1 | unit | 1 | 2022-10-21 |  | 100% | 100% | 0% | 18.2857 | 13343.06 | 660.1 | 9340.14 | 12070.4 | 0 | 21410.54 | 18487.24 | 2923.3 | Tas Quote - 2439-13-1 | 2022-10-21 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 32 | 77663 | 76779 | Hotel Side Block Work | Level 31 | Independent | 1 | 3.6 | 1.3 | 4 | 1 | m2-LxH | 14.4 | 2022-10-22 | 2022-11-03 | 100% | 100% | 100% | 1.8571 | 12.01 | 0.49 | 121.06 | 13.1 | 51.88 | 186.04 | 186.04 | 0 |  | 2022-10-22 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 32 | 77663 | 76779 | Hotel Side Block Work | Level 31 | Additional Boarding | 1 | 3.6 | 1.3 | 1 | 1 | m2-LxW | 4.68 | 2022-10-22 | 2022-11-03 | 100% | 100% | 100% | 1.8571 | 6.63 | 0.7 | 21.72 | 6.08 | 9.31 | 37.11 | 37.11 | 0 |  | 2022-10-22 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 33 | 77664 | 76772 | Canal Side wall Cladding opening Work | Level 14 | Tower | 1 | 1.8 | 1.3 | 1 | 1 | rm | 1 | 2022-10-22 | 2022-10-27 | 100% | 100% | 100% | 0.85714 | 63.34 | 7.28 | 44.34 | 6.24 | 19 | 69.58 | 69.58 | 0 |  | 2022-10-22 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 34 | 77665 | 80871 | Canal Side wall Cladding opening Work | Level 14 | Tower | 1 | 1.8 | 1.3 | 1 | 1 | rm | 1 | 2022-10-22 | 2023-01-06 | 100% | 100% | 100% | 11 | 63.34 | 7.28 | 44.34 | 80.08 | 19 | 143.42 | 143.42 | 0 |  | 2022-10-22 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 4d | 77670 | 76786 | EIFS work | Ground Level to Level 2 | Additional Boarding | 3 | 1.8 | 1.8 | 1 | 3 | m2-LxW | 9.72 | 2022-10-25 | 2022-11-05 | 100% | 100% | 100% | 1.7143 | 6.63 | 0.7 | 45.11 | 11.66 | 19.33 | 76.1 | 76.1 | 0 |  | 2022-10-25 | TRUE
E11/K149/SK/dm/213 | HOTEL | 2 | 74603 | 76828 | Plant Room Façade Fin Supporting work | Level 5 | Independent 1.8m wide | 1 | 4.9 | 1.8 | 4.2 | 1 | m2-LxH | 20.58 | 2022-10-04 | 2022-11-21 | 100% | 100% | 100% | 7 | 16.76 | 0.77 | 241.44 | 110.93 | 103.48 | 455.85 | 455.85 | 0 |  | 2022-10-04 | TRUE
E11/K149/SK/dm/213 | HOTEL | 2a | 74604 |  | Plant Room Façade Fin Supporting work | Level 5 | Independent 1.8m wide | 1 | 15.1 | 1.8 | 4.2 | 1 | m2-LxH | 63.42 | 2022-10-05 |  | 100% | 100% | 0% | 20.5714 | 16.76 | 0.77 | 744.04 | 1004.57 | 0 | 1748.61 | 1532.35 | 216.26 |  | 2022-10-05 | TRUE
E11/K149/SK/dm/213 | HOTEL | 2b | 74605 | 80819 | Plant Room For AC Duct Work | Level 5 | Additional Boarding | 1 | 6.8 | 1.8 | 1 | 1 | m2-LxW | 12.24 | 2022-10-05 | 2022-12-20 | 100% | 100% | 100% | 11 | 6.63 | 0.7 | 56.81 | 94.25 | 24.35 | 175.41 | 175.41 | 0 |  | 2022-10-05 | TRUE
E11/K149/SK/dm/213 | HOTEL | 2c | 74606 | 80818 | Plant Room Façade Fin Supporting work | Level 5 | Cantilever (0.5 > 1.2m width) | 1 | 1 | 0.75 | 1 | 1 | m2-LxW | 0.75 | 2022-10-05 | 2022-12-20 | 100% | 100% | 100% | 11 | 36.52 | 2.94 | 19.17 | 24.26 | 8.22 | 51.65 | 51.65 | 0 |  | 2022-10-05 | TRUE
E11/K149/SK/dm/213 | HOTEL | 3 | 74607 | 80820 | Plant Room Façade Fin Supporting work | Level 5 | Independent 1.8m wide | 1 | 7.5 | 1.8 | 4.2 | 1 | m2-LxH | 31.5 | 2022-10-05 | 2022-12-20 | 100% | 100% | 100% | 11 | 16.76 | 0.77 | 369.56 | 266.81 | 158.38 | 794.75 | 794.75 | 0 |  | 2022-10-05 | TRUE
E11/K149/SK/dm/213 | HOTEL | 3a | 74608 | 80821 | Plant Room Façade Fin Supporting work | Level 5 | Cantilever (0 < 0.5m width) | 1 | 5 | 0.25 | 1 | 1 | m2-LxW | 1.25 | 2022-10-05 | 2022-12-20 | 100% | 100% | 100% | 11 | 32.75 | 1.05 | 28.66 | 14.44 | 12.28 | 55.38 | 55.38 | 0 |  | 2022-10-05 | TRUE
E11/K149/SK/dm/213 | HOTEL | 4 | 74609 | 76802 | Air Extract Gratting Installation | Basement 1 | Independent | 1 | 9.3 | 1.3 | 5.9 | 1 | m2-LxH | 54.87 | 2022-10-07 | 2022-10-12 | 100% | 100% | 100% | 0.85714 | 12.01 | 0.49 | 461.29 | 23.05 | 197.7 | 682.04 | 682.04 | 0 |  | 2022-10-07 | TRUE
E11/K149/SK/dm/213 | HOTEL | 4a | 74610 | 76803 | Air Extract Gratting Installation | Basement 1 | Cantilever (0 < 0.5m width) | 1 | 9.8 | 0.5 | 1 | 1 | m2-LxW | 4.9 | 2022-10-07 | 2022-10-12 | 100% | 100% | 100% | 0.85714 | 32.75 | 1.05 | 112.33 | 4.41 | 48.14 | 164.88 | 164.88 | 0 |  | 2022-10-07 | TRUE
E11/K149/SK/dm/300 | HOTEL | 5 | 74611 | 76801 | Cradle Beam Support | Roof | Design 1399-13 rev-A | 1 | 4 | 2.5 | 2 | 1 | unit | 1 | 2022-10-07 | 2022-10-10 | 100% | 100% | 100% | 0.57143 | 4033.1 | 49.28 | 2823.17 | 28.16 | 1209.93 | 4061.26 | 4061.26 | 0 | Tas Quote - 2439-11-2 | 2022-10-07 | TRUE
E11/K149/SK/dm/300 | HOTEL | 6 | 74612 | 76804 | Cradle Beam Support (Re-erction) | Roof | Design 1399-13 rev-A | 1 | 4 | 2.5 | 2 | 1 | unit | 1 | 2022-10-10 | 2022-10-26 | 100% | 100% | 100% | 2.4286 | 4033.1 | 49.28 | 2823.17 | 119.68 | 1209.93 | 4152.78 | 4152.78 | 0 | Tas Quote - 2439-11-2 | 2022-10-10 | TRUE
E11/K149/SK/dm/213 | HOTEL | 7 | 74613 | 76807 | Planter Drain Connection (mep) | Basement 1 | Tower | 1 | 1.8 | 1.3 | 2.5 | 1 | rm | 2.5 | 2022-10-12 | 2022-11-03 | 100% | 100% | 100% | 3.2857 | 63.34 | 7.28 | 110.85 | 59.8 | 47.51 | 218.16 | 218.16 | 0 |  | 2022-10-12 | TRUE
E11/K149/SK/dm/213 | HOTEL | 2d | 74614 | 80822 | Planter Room Fin Supportting work | Level 5 | Additional Boarding | 1 | 4.3 | 1.5 | 1 | 1 | m2-LxW | 6.45 | 2022-10-12 | 2022-12-20 | 100% | 100% | 100% | 10 | 6.63 | 0.7 | 29.93 | 45.15 | 12.83 | 87.91 | 87.91 | 0 |  | 2022-10-12 | TRUE
E11/K149/SK/dm/213 | HOTEL | 3b | 74615 | 80823 | Planter Room Fin Supportting work | Level 5 | Independent 1.8m wide | 1 | 3 | 1.8 | 4.2 | 1 | m2-LxH | 12.6 | 2022-10-12 | 2022-12-20 | 100% | 100% | 100% | 10 | 16.76 | 0.77 | 147.82 | 97.02 | 63.35 | 308.19 | 308.19 | 0 |  | 2022-10-12 | TRUE
E11/K149/SK/dm/213 | HOTEL | 3c | 74616 | 80824 | Planter Room Fin Supportting work | Level 5 | Independent | 1 | 5 | 1.3 | 4.2 | 1 | m2-LxH | 21 | 2022-10-12 | 2022-12-20 | 100% | 100% | 100% | 10 | 12.01 | 0.49 | 176.55 | 102.9 | 75.66 | 355.11 | 355.11 | 0 |  | 2022-10-12 | TRUE
E11/K149/SK/dm/213 | HOTEL | 8 | 74617 | 80813 | Planter Room Fin Supportting work | Level 5 | Independent 1.8m wide | 1 | 10.8 | 1.8 | 3.8 | 1 | m2-LxH | 41.04 | 2022-10-13 | 2022-12-20 | 100% | 100% | 100% | 9.8571 | 16.76 | 0.77 | 481.48 | 311.49 | 206.35 | 999.32 | 999.32 | 0 |  | 2022-10-13 | TRUE
E11/K149/SK/dm/213 | HOTEL | 8a | 74618 | 80814 | Planter Room Fin Supportting work | Level 5 | Cantilever (0 < 0.5m width) | 1 | 10.8 | 0.5 | 1 | 1 | m2-LxW | 5.4 | 2022-10-13 | 2022-12-20 | 100% | 100% | 100% | 9.8571 | 32.75 | 1.05 | 123.8 | 55.89 | 53.06 | 232.75 | 232.75 | 0 |  | 2022-10-13 | TRUE
E11/K149/SK/dm/213 | HOTEL | 3d | 74619 | 80817 | Plant Room For Kmep Work | Level 5 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-10-15 | 2022-12-20 | 100% | 100% | 100% | 9.5714 | 36.52 | 2.94 | 38.35 | 42.21 | 16.43 | 96.99 | 96.99 | 0 | KMEP | 2022-10-15 | TRUE
E11/K149/SK/dm/213 | HOTEL | 8b | 74620 | 80815 | Plant Room For Kmep Work | Level 5 | Tower | 1 | 2.5 | 1.8 | 3.5 | 1 | rm | 3.5 | 2022-10-15 | 2022-12-20 | 100% | 100% | 100% | 9.5714 | 63.34 | 7.28 | 155.18 | 243.88 | 66.51 | 465.57 | 465.57 | 0 | KMEP | 2022-10-15 | TRUE
E11/K149/SK/dm/213 | HOTEL | 8c | 74621 | 80816 | Plant Room For Kmep Work | Level 5 | Cantilever (0 < 0.5m width) | 1 | 4.8 | 0.5 | 1 | 1 | m2-LxW | 2.4 | 2022-10-15 | 2022-12-20 | 100% | 100% | 100% | 9.5714 | 32.75 | 1.05 | 55.02 | 24.12 | 23.58 | 102.72 | 102.72 | 0 | KMEP | 2022-10-15 | TRUE
E11/K149/SK/dm/213 | HOTEL | 9 | 74622 | 80825 | Plant Room For Kmep Work | Level 5 | Independent | 1 | 4.5 | 1.5 | 2.3 | 1 | m2-LxH | 10.35 | 2022-10-15 | 2022-12-20 | 100% | 100% | 100% | 9.5714 | 12.01 | 0.49 | 87.01 | 48.54 | 37.29 | 172.84 | 172.84 | 0 | KMEP | 2022-10-15 | TRUE
E11/K149/SK/dm/259 | HOTEL | 10 | 74633 | 80937 | Inverted Scaffold | Level 29 | Design 1399 -06 rev-B | 1 | 50 | 1.8 | 4 | 1 | lm | 50 | 2022-10-20 | 2023-01-31 | 100% | 100% | 100% | 14.8571 | 1002.22 | 98.12 | 35077.7 | 72889.14 | 15033.3 | 123000.14 | 103761.7 | 19238.44 | Tas Quote - 2439-6-1 | 2022-10-20 | TRUE | 50 | TRUE
E11/K149/SK/dm/341 | HOTEL | 11 | 74623 | 80803 | Balcony Floor Drain Work | Level 13 | Independent | 1 | 5.7 | 1.3 | 1.5 | 1 | unit | 1 | 2022-10-20 | 2022-12-15 | 100% | 100% | 100% | 8.1429 | 1368.99 | 6.17 | 958.29 | 50.24 | 410.7 | 1419.23 | 1419.23 | 0 | Tas Quote - 2439-12-2 (item-2) | 2022-10-20 | TRUE | 1 | TRUE
E11/K149/SK/dm/341 | HOTEL | 12 | 74625 | 80834 | Balcony Floor Drain Work | Level 12 | Independent | 1 | 5.7 | 1.3 | 1.5 | 1 | unit | 1 | 2022-10-20 | 2022-12-21 | 100% | 100% | 100% | 9 | 1368.99 | 6.17 | 958.29 | 55.53 | 410.7 | 1424.52 | 1424.52 | 0 | Tas Quote - 2439-12-2 (item-2) | 2022-10-20 | TRUE | 1 | TRUE
E11/K149/SK/dm/341 | HOTEL | 13 | 74624 | 80809 | Balcony Floor Drain Work | Level 14 | Independent | 1 | 5.7 | 1.3 | 1.5 | 1 | unit | 1 | 2022-10-21 | 2022-12-17 | 100% | 100% | 100% | 8.2857 | 1368.99 | 6.17 | 958.29 | 51.12 | 410.7 | 1420.11 | 1420.11 | 0 | Tas Quote - 2439-12-2 (item-2) | 2022-10-21 | TRUE | 1 | TRUE
E11/K149/SK/dm/341 | HOTEL | 14 | 74626 | 80804 | Balcony Floor Drain Work | Level 15 | Independent | 1 | 5.7 | 1.3 | 1.5 | 1 | unit | 1 | 2022-10-21 | 2022-12-15 | 100% | 100% | 100% | 8 | 1368.99 | 6.17 | 958.29 | 49.36 | 410.7 | 1418.35 | 1418.35 | 0 | Tas Quote - 2439-12-2 (item-2) | 2022-10-21 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | HOTEL | 10a | 74635 | 76805 | Trench Inside for Parapet Cutting | Level 29 | Additional Boarding | 1 | 50 | 1 | 1 | 1 | m2-LxW | 50 | 2022-10-20 | 2022-10-31 | 100% | 100% | 100% | 1.7143 | 6.63 | 0.7 | 232.05 | 60 | 99.45 | 391.5 | 391.5 | 0 |  | 2022-10-20 | TRUE | 50 | TRUE
E11/K149/SK/dm/259 | HOTEL | 15 | 74634 | 78553 | Inverted Scaffold | Level 29 | Design 1399 -06 rev-B | 1 | 33 | 1.8 | 4 | 1 | lm | 33 | 2022-10-22 | 2023-02-04 | 100% | 100% | 100% | 15.1429 | 1002.22 | 98.12 | 23151.28 | 49031.97 | 9921.98 | 82105.23 | 67557.59 | 14547.64 | Tas Quote - 2439-6-1 | 2022-10-22 | TRUE | 33 | TRUE
E11/K149/SK/dm/259 | HOTEL | 15 | 74634 |  | Inverted Scaffold | Level 29 | Third Party Inspection ( Additional) | 1 |  |  |  |  | unit | 1 | 2022-10-22 | 2022-10-22 | 100% | 100% | 100% | 0.14286 | 1230 | 0 | 1230 | 0 | 0 | 1230 | 1230 | 0 | Additional Inspection | 2022-10-22 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | HOTEL | 15a | 74636 | 76806 | Trench Inside for Parapet Cutting | Level 29 | Additional Boarding | 1 | 33 | 1 | 1 | 1 | m2-LxW | 33 | 2022-10-22 | 2022-11-01 | 100% | 100% | 100% | 1.5714 | 6.63 | 0.7 | 153.15 | 36.3 | 65.64 | 255.09 | 255.09 | 0 |  | 2022-10-22 | TRUE | 33 | TRUE
E11/K149/SK/dm/213 | HOTEL | 16 | 74627 | 76810 | EIFS work Damac side Elevation | Level 2 | Independent 1.8m wide | 1 | 6.8 | 1.8 | 8 | 1 | m2-LxH | 54.4 | 2022-10-24 | 2022-11-09 | 100% | 100% | 100% | 2.4286 | 16.76 | 0.77 | 638.22 | 101.73 | 273.52 | 1013.47 | 1013.47 | 0 |  | 2022-10-24 | TRUE | 54.4 | TRUE
E11/K149/SK/dm/213 | HOTEL | 16a | 74628 | 76811 | EIFS work Damac side Elevation | Level 4 | Cantilever (0.5 > 1.2m width) | 1 | 6.8 | 1 | 1 | 1 | m2-LxW | 6.8 | 2022-10-24 | 2022-11-09 | 100% | 100% | 100% | 2.4286 | 36.52 | 2.94 | 173.84 | 48.55 | 74.5 | 296.89 | 296.89 | 0 |  | 2022-10-24 | TRUE | 6.8 | TRUE
E11/K149/SK/dm/213 | HOTEL | 16b | 74629 | 76812 | EIFS work Damac side Elevation | Level 2 | Buttress | 1 | 2.5 | 1.8 | 5 |  | m3 | 22.5 | 2022-10-24 | 2022-11-09 | 100% | 100% | 100% | 2.4286 | 5.29 | 0.35 | 83.32 | 19.13 | 35.71 | 138.16 | 138.16 | 0 |  | 2022-10-24 | TRUE | 22.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 9a | 74630 | 80826 | Plant Room Kmep Work | Level 5 | Additional Boarding | 1 | 4.5 | 1 | 1 | 1 | m2-LxW | 4.5 | 2022-10-24 | 2022-12-20 | 100% | 100% | 100% | 8.2857 | 6.63 | 0.7 | 20.88 | 26.1 | 8.95 | 55.93 | 55.93 | 0 | KMEP | 2022-10-24 | TRUE | 4.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 9b | 74632 | 80827 | Plant Room Kmep Work | Level 5 | Additional Boarding | 1 | 2.5 | 0.75 | 1 | 1 | m2-LxW | 1.88 | 2022-10-24 | 2022-12-20 | 100% | 100% | 100% | 8.2857 | 6.63 | 0.7 | 8.73 | 10.9 | 3.74 | 23.37 | 23.37 | 0 | KMEP | 2022-10-24 | TRUE | 1.88 | TRUE
E11/K149/SK/dm/213 | HOTEL | 17 | 74637 | 80828 | Plant Room Kmep Work | Level 5 | Tower | 1 | 2.5 | 1.3 | 2.5 | 1 | rm | 2.5 | 2022-10-25 | 2022-12-20 | 100% | 100% | 100% | 8.1429 | 63.34 | 7.28 | 110.85 | 148.2 | 47.51 | 306.56 | 306.56 | 0 | KMEP | 2022-10-25 | TRUE | 2.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 17a | 74638 | 80829 | Plant Room Kmep Work | Level 5 | Cantilever (0 < 0.5m width) | 1 | 1.5 | 0.5 | 1 | 1 | m2-LxW | 0.75 | 2022-10-25 | 2022-12-20 | 100% | 100% | 100% | 8.1429 | 32.75 | 1.05 | 17.19 | 6.41 | 7.37 | 30.97 | 30.97 | 0 | KMEP | 2022-10-25 | TRUE | 0.75 | TRUE
E11/K149/MS/dm/396 | RESIDENCE | 35 | 77666 | 80509 | Master Pump Room Work | Level 23 | Birdcage | 1 | 5 | 4.3 | 3 | 2 | unit | 1 | 2022-10-24 | 2022-11-12 | 100% | 100% | 100% | 2.8571 | 2391.43 | 57.19 | 1674 | 163.4 | 717.43 | 2554.83 | 2554.83 | 0 | Tas Quote - 2439-18-1 (item-1) | 2022-10-24 | TRUE | 1 | TRUE
E11/K149/HN/dm/285 | RESIDENCE | 36 | 77671 | 80894 | Loading Bay Above Planter Trench | Ground Level | Design -1399-12 rev-A | 1 |  |  |  |  | unit | 1 | 2022-10-26 | 2023-01-23 | 100% | 100% | 100% | 12.8571 | 4959.77 | 123.48 | 3471.84 | 1587.6 | 1487.93 | 6547.37 | 6547.37 | 0 | Tas Quote - 2439-10-1 | 2022-10-26 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 8m | 77672 | 76773 | Glass Fixing work | Level 31 | Additional Boarding | 1 | 10.8 | 0.5 | 1 | 1 | m2-LxW | 5.4 | 2022-10-26 | 2022-10-28 | 100% | 100% | 100% | 0.42857 | 6.63 | 0.7 | 25.06 | 1.62 | 10.74 | 37.42 | 37.42 | 0 |  | 2022-10-26 | TRUE | 5.4 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 8n | 77673 |  | Glass Fixing work | Level 31 | Additional Boarding | 2 | 10.8 | 0.25 | 1 | 2 | m2-LxW | 5.4 | 2022-10-26 |  | 100% | 100% | 0% | 17.5714 | 6.63 | 0.7 | 25.06 | 66.42 | 0 | 91.48 | 74.74 | 16.74 |  | 2022-10-26 | TRUE | 5.4 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 37 | 77674 |  | Glass Fixing work | Level 7 | Tower | 1 | 2.5 | 1.3 | 1 | 1 | rm | 1 | 2022-10-28 |  | 100% | 100% | 0% | 17.2857 | 63.34 | 7.28 | 44.34 | 125.84 | 0 | 170.18 | 137.94 | 32.24 |  | 2022-10-28 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 38 | 77675 | 76795 | Entrance Lobby Block Demolishing Work | Ground Level | Independent | 1 | 3.1 | 1.3 | 4.2 | 1 | m2-LxH | 13.02 | 2022-10-28 | 2022-11-04 | 100% | 100% | 100% | 1.1429 | 12.01 | 0.49 | 109.46 | 7.29 | 46.91 | 163.66 | 163.66 | 0 |  | 2022-10-28 | TRUE | 13.02 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 38 | 77675 | 76795 | Entrance Lobby Block Demolishing Work | Ground Level | Additional Boarding | 1 | 3.1 | 1.3 |  | 1 | m2-LxW | 4.03 | 2022-10-28 | 2022-11-04 | 100% | 100% | 100% | 1.1429 | 6.63 | 0.7 | 18.7 | 3.22 | 8.02 | 29.94 | 29.94 | 0 |  | 2022-10-28 | TRUE | 4.03 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 39 | 77676 |  | Existing Pipe Removal Work | Basement 1 | Birdcage | 1 | 3 | 3 | 5 | 1 | m3 | 45 | 2022-10-28 |  | 100% | 100% | 0% | 17.2857 | 7.08 | 0.49 | 223.02 | 381.15 | 0 | 604.17 | 506.52 | 97.65 |  | 2022-10-28 | TRUE | 45 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 40 | 77677 |  | Edge Protection | Level 31 | Double Handrail | 1 | 10 |  | 1 |  | lm | 10 | 2022-10-29 |  | 100% | 100% | 0% | 17.1429 | 12 | 0.7 | 84 | 120 | 0 | 204 | 173 | 31 |  | 2022-10-29 | TRUE | 10 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 8o | 77678 |  | Glass Fixing work | Level 30 | Cantilever (0 < 0.5m width) | 1 | 10.8 | 0.5 | 1 | 1 | m2-LxW | 5.4 | 2022-10-29 |  | 100% | 100% | 0% | 17.1429 | 32.75 | 1.05 | 123.8 | 97.2 | 0 | 221 | 195.89 | 25.11 |  | 2022-10-29 | TRUE | 5.4 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 41 | 77679 | 76796 | Block Demolishing Work | Ground Level | Independent | 1 | 5.4 | 1.3 | 4 | 1 | m2-LxH | 21.6 | 2022-10-29 | 2022-11-09 | 100% | 100% | 100% | 1.7143 | 12.01 | 0.49 | 181.59 | 18.14 | 77.82 | 277.55 | 277.55 | 0 |  | 2022-10-29 | TRUE | 21.6 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 41 | 77679 | 76796 | Block Demolishing Work | Ground Level | Additional Boarding | 1 | 5.4 | 1.3 | 1 | 1 | m2-LxW | 7.02 | 2022-10-29 | 2022-11-09 | 100% | 100% | 100% | 1.7143 | 6.63 | 0.7 | 32.58 | 8.42 | 13.96 | 54.96 | 54.96 | 0 |  | 2022-10-29 | TRUE | 7.02 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 41a | 77680 | 76785 | Block Demolishing Work | Ground Level | Cantilever (0 < 0.5m width) | 2 | 2 | 0.5 | 1 | 2 | m2-LxW | 2 | 2022-10-29 | 2022-11-03 | 100% | 100% | 100% | 0.85714 | 32.75 | 1.05 | 45.85 | 1.8 | 19.65 | 67.3 | 67.3 | 0 |  | 2022-10-29 | TRUE | 2 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 38a | 77681 | 76778 | Block Demolishing Work | Ground Level | Cantilever (0 < 0.5m width) | 2 | 2 | 0.5 | 1 | 2 | m2-LxW | 2 | 2022-10-29 | 2022-11-02 | 100% | 100% | 100% | 0.71429 | 32.75 | 1.05 | 45.85 | 1.5 | 19.65 | 67 | 67 | 0 |  | 2022-10-29 | TRUE | 2 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 39a | 77682 |  | Existing Pipe Removal Work | Basement 1 | Additional Boarding | 1 | 3 | 1.5 | 1 | 1 | m2-LxW | 4.5 | 2022-10-29 |  | 100% | 100% | 0% | 17.1429 | 6.63 | 0.7 | 20.88 | 54 | 0 | 74.88 | 60.93 | 13.95 |  | 2022-10-29 | TRUE | 4.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 32a | 77683 | 76780 | Block Work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-10-29 | 2022-11-03 | 100% | 100% | 100% | 0.85714 | 36.52 | 2.94 | 38.35 | 3.78 | 16.43 | 58.56 | 58.56 | 0 |  | 2022-10-29 | TRUE | 1.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 4i | 77686 | 76787 | EIFS Painting up to Groove | Ground Level | Tower | 1 | 1.8 | 0.9 | 12.3 | 1 | rm | 12.3 | 2022-10-29 | 2022-11-05 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 545.36 | 102.34 | 233.72 | 881.42 | 881.42 | 0 |  | 2022-10-29 | TRUE | 12.3 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 4i | 77686 | 76787 | EIFS Painting up to Groove | Ground Level | Additional Boarding | 5 | 1.8 | 0.9 | 1 | 5 | m2-LxW | 8.1 | 2022-10-29 | 2022-11-05 | 100% | 100% | 100% | 1.1429 | 6.63 | 0.7 | 37.59 | 6.48 | 16.11 | 60.18 | 60.18 | 0 |  | 2022-10-29 | TRUE | 8.1 | TRUE
E11/K149/JJ/dm/377 | RESIDENCE | 42 | 77687 |  | Back Propping For Mast Climber | Basement 1 | Design - 1399-20 | 1 |  |  |  |  | unit | 1 | 2022-10-31 |  | 100% | 100% | 0% | 16.8571 | 7695.22 | 511.06 | 5386.65 | 8615.01 | 0 | 14001.66 | 11738.4 | 2263.26 | Tas Quote 2439-16-3 (item-1) | 2022-10-31 | TRUE | 1 | TRUE
E11/K149/JJ/dm/377 | RESIDENCE | 43 | 77688 |  | Back Propping For Mast Climber | Basement 1 | Design - 1399-20 | 1 |  |  |  |  | unit | 1 | 2022-10-31 |  | 100% | 100% | 0% | 16.8571 | 7695.22 | 511.06 | 5386.65 | 8615.01 | 0 | 14001.66 | 11738.4 | 2263.26 | Tas Quote 2439-16-3 (item-1) | 2022-10-31 | TRUE | 1 | TRUE
E11/K149/JJ/dm/377 | RESIDENCE | 44 | 77689 |  | Back Propping For Mast Climber | Ground Level | Design - 1399-20 | 1 |  |  |  |  | unit | 1 | 2022-10-31 |  | 100% | 100% | 0% | 16.8571 | 7695.22 | 511.06 | 5386.65 | 8615.01 | 0 | 14001.66 | 11738.4 | 2263.26 | Tas Quote 2439-16-3 (item-1) | 2022-10-31 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 32b | 77690 | 76781 | Block Shifting Work | Level 31 | Tower | 1 | 1.5 | 1.5 | 1 | 1 | rm | 1 | 2022-11-01 | 2022-11-03 | 100% | 100% | 100% | 0.42857 | 63.34 | 7.28 | 44.34 | 3.12 | 19 | 66.46 | 66.46 | 0 |  | 2022-11-01 | TRUE | 1 | TRUE
E11/K149/JJ/dm/377 | RESIDENCE | 45 | 77691 |  | Back Propping For Mast Climber | Ground Level | Design - 1399-20 | 1 |  |  |  |  | unit | 1 | 2022-11-01 |  | 100% | 100% | 0% | 16.7143 | 7695.22 | 511.06 | 5386.65 | 8542 | 0 | 13928.65 | 11665.39 | 2263.26 | Tas Quote 2439-16-3 (item-1) | 2022-11-01 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 19b | 77692 | 80536 | Shaft -9 For Ducting Work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 0.75 | 1 | 2 | m2-LxW | 1.13 | 2022-10-29 | 2022-11-28 | 100% | 100% | 100% | 4.4286 | 36.52 | 2.94 | 28.89 | 14.71 | 12.38 | 55.98 | 55.98 | 0 |  | 2022-10-29 | TRUE | 1.13 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 19c | 77693 | 76790 | Shaft -9 For Ducting Work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-11-02 | 2022-11-04 | 100% | 100% | 100% | 0.42857 | 36.52 | 2.94 | 38.35 | 1.89 | 16.43 | 56.67 | 56.67 | 0 |  | 2022-11-02 | TRUE | 1.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 46 | 77694 | 80539 | Electrical & Plumbing Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 4 | 1 | rm | 4 | 2022-11-03 | 2022-11-26 | 100% | 100% | 100% | 3.4286 | 63.34 | 7.28 | 177.35 | 99.84 | 76.01 | 353.2 | 353.2 | 0 |  | 2022-11-03 | TRUE | 4 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 46 | 77694 | 80539 | Electrical & Plumbing Work | Basement 1 | Additional Boarding | 1 | 2.5 | 1.3 | 1 | 1 | m2-LxW | 3.25 | 2022-11-03 | 2022-11-26 | 100% | 100% | 100% | 3.4286 | 6.63 | 0.7 | 15.08 | 7.8 | 6.46 | 29.34 | 29.34 | 0 |  | 2022-11-03 | TRUE | 3.25 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 47 | 77695 | 80578 | Block Work | Basement 1 | Tower | 1 | 2.5 | 1.5 | 3 | 1 | rm | 3 | 2022-11-03 | 2022-12-20 | 100% | 100% | 100% | 6.8571 | 63.34 | 7.28 | 133.01 | 149.76 | 57.01 | 339.78 | 339.78 | 0 |  | 2022-11-03 | TRUE | 3 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 48 | 77696 | 80526 | Column Cove Installation Work | Ground Level | Birdcage | 1 | 11.8 | 3.8 | 3.5 | 1 | m3 | 156.94 | 2022-11-03 | 2022-11-17 | 100% | 100% | 100% | 2.1429 | 7.08 | 0.49 | 777.79 | 164.79 | 333.34 | 1275.92 | 1275.92 | 0 |  | 2022-11-03 | TRUE | 156.94 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 49 | 77697 | 80508 | Electrical Service Work (BMS) | Basement 1 | Tower | 1 | 2.5 | 1.3 | 4.2 | 1 | rm | 4.2 | 2022-11-03 | 2022-11-12 | 100% | 100% | 100% | 1.4286 | 63.34 | 7.28 | 186.22 | 43.68 | 79.81 | 309.71 | 309.71 | 0 |  | 2022-11-03 | TRUE | 4.2 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 49 | 77697 | 80508 | Electrical Service Work (BMS) | Basement 1 | Additional Boarding | 1 | 2.5 | 1.3 | 1 | 1 | m2-LxW | 3.25 | 2022-11-03 | 2022-11-12 | 100% | 100% | 100% | 1.4286 | 6.63 | 0.7 | 15.08 | 3.25 | 6.46 | 24.79 | 24.79 | 0 |  | 2022-11-03 | TRUE | 3.25 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 50 | 77698 | 80529 | Column Cove Installation Work | Ground Level | Tower | 1 | 2.5 | 2.5 | 3.5 | 1 | rm | 3.5 | 2022-11-03 | 2022-11-18 | 100% | 100% | 100% | 2.2857 | 63.34 | 7.28 | 155.18 | 58.24 | 66.51 | 279.93 | 279.93 | 0 |  | 2022-11-03 | TRUE | 3.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 51 | 77699 | 80510 | Column Cove Installation Work | Ground Level | Tower | 1 | 2.5 | 2.5 | 3.5 | 1 | rm | 3.5 | 2022-11-03 | 2022-11-11 | 100% | 100% | 100% | 1.2857 | 63.34 | 7.28 | 155.18 | 32.76 | 66.51 | 254.45 | 254.45 | 0 |  | 2022-11-03 | TRUE | 3.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 8p | 77700 |  | Glass Fixing work | Level 31 | Cantilever (0 < 0.5m width) | 1 | 9 | 0.25 | 1 | 2 | m2-LxW | 2.25 | 2022-11-03 |  | 100% | 100% | 0% | 16.4286 | 32.75 | 1.05 | 51.58 | 38.81 | 0 | 90.39 | 79.93 | 10.46 |  | 2022-11-03 | TRUE | 2.25 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 8q | 77551 | 76791 | Glass Fixing work | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 10.8 | 1 | 1 | 1 | m2-LxW | 10.8 | 2022-11-03 | 2022-11-05 | 100% | 100% | 100% | 0.42857 | 36.52 | 2.94 | 276.09 | 13.61 | 118.32 | 408.02 | 408.02 | 0 |  | 2022-11-03 | TRUE | 10.8 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 38b | 77552 | 76797 | Entrance Lobby Block Work | Ground Level | Tower | 1 | 1 | 1 | 1.5 | 1 | rm | 1.5 | 2022-11-03 | 2022-11-09 | 100% | 100% | 100% | 1 | 63.34 | 7.28 | 66.51 | 10.92 | 28.5 | 105.93 | 105.93 | 0 |  | 2022-11-03 | TRUE | 1.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 38c | 77553 | 76798 | Entrance Lobby Block Work | Ground Level | Tower | 1 | 1 | 1 | 1.5 | 1 | rm | 1.5 | 2022-11-03 | 2022-11-09 | 100% | 100% | 100% | 1 | 63.34 | 7.28 | 66.51 | 10.92 | 28.5 | 105.93 | 105.93 | 0 |  | 2022-11-03 | TRUE | 1.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 52 | 77554 | 80523 | Column Cove Installation Work | Ground Level | Tower | 1 | 2.5 | 2.5 | 3.5 | 1 | rm | 3.5 | 2022-11-04 | 2022-11-16 | 100% | 100% | 100% | 1.8571 | 63.34 | 7.28 | 155.18 | 47.32 | 66.51 | 269.01 | 269.01 | 0 |  | 2022-11-04 | TRUE | 3.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 19d | 77555 | 80502 | Shaft - 9 Ducting Work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 2 | 1.5 | 1 | 1 | m2-LxW | 3 | 2022-11-04 | 2022-11-09 | 100% | 100% | 100% | 0.85714 | 36.52 | 2.94 | 76.69 | 7.56 | 32.87 | 117.12 | 117.12 | 0 |  | 2022-11-04 | TRUE | 3 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 53 | 77556 | 80511 | Balcony Side Edge Protection | Level 27 | Buttress | 1 | 2.5 | 1.8 | 2 |  | m3 | 9 | 2022-11-04 | 2022-11-11 | 100% | 100% | 100% | 1.1429 | 5.29 | 0.35 | 33.33 | 3.6 | 14.28 | 51.21 | 51.21 | 0 |  | 2022-11-04 | TRUE | 9 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 53a | 77557 | 80511 | Balustrade Glass Edge Protection | Level 27 | Tripple Hnadrail | 1 | 6 |  | 1.5 |  | lm | 6 | 2022-11-04 | 2022-11-11 | 100% | 100% | 100% | 1.1429 | 15 | 0.91 | 63 | 6.24 | 27 | 96.24 | 96.24 | 0 |  | 2022-11-04 | TRUE | 6 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 54 | 77558 | 80527 | Column Cove Installation Work | Ground Level | Tower | 1 | 2.5 | 2.5 | 3.5 | 1 | rm | 3.5 | 2022-11-04 | 2022-11-17 | 100% | 100% | 100% | 2 | 63.34 | 7.28 | 155.18 | 50.96 | 66.51 | 272.65 | 272.65 | 0 |  | 2022-11-04 | TRUE | 3.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 46a | 77559 | 80540 | Electrical Services Work | Basement 1 | Tower | 1 | 1.8 | 1.3 | 4 | 1 | rm | 4 | 2022-11-05 | 2022-11-26 | 100% | 100% | 100% | 3.1429 | 63.34 | 7.28 | 177.35 | 91.52 | 76.01 | 344.88 | 344.88 | 0 |  | 2022-11-05 | TRUE | 4 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 55 | 77560 | 80517 | Electrical Services Work | Basement 1 | Independent | 1 | 3.8 | 1.3 | 2.5 | 1 | m2-LxH | 9.5 | 2022-11-05 | 2022-11-15 | 100% | 100% | 100% | 1.5714 | 12.01 | 0.49 | 79.87 | 7.32 | 34.23 | 121.42 | 121.42 | 0 |  | 2022-11-05 | TRUE | 9.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 56 | 77561 | 78638 | Plant Room Kmep Work | Level 5 | Tower | 1 | 2.5 | 1.8 | 4 | 1 | rm | 4 | 2022-11-05 | 2023-02-06 | 100% | 100% | 100% | 13.4286 | 63.34 | 7.28 | 177.35 | 391.04 | 76.01 | 644.4 | 518.47 | 125.93 |  | 2022-11-05 | TRUE | 4 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 56 | 77561 | 78638 | Plant Room Kmep Work | Level 5 | Additional Boarding | 1 | 2.5 | 1.8 | 1 | 1 | m2-LxW | 4.5 | 2022-11-05 | 2023-02-06 | 100% | 100% | 100% | 13.4286 | 6.63 | 0.7 | 20.88 | 42.3 | 8.95 | 72.13 | 57.78 | 14.35 |  | 2022-11-05 | TRUE | 4.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 38d | 77562 | 76799 | Entrance Lobby Block Work | Ground Level | Tower | 1 | 1 | 1 | 1.5 | 1 | rm | 1.5 | 2022-11-05 | 2022-11-09 | 100% | 100% | 100% | 0.71429 | 63.34 | 7.28 | 66.51 | 7.8 | 28.5 | 102.81 | 102.81 | 0 |  | 2022-11-05 | TRUE | 1.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 38e | 77563 | 76800 | Entrance Lobby Block Work | Ground Level | Tower | 1 | 1 | 1 | 1.5 | 1 | rm | 1.5 | 2022-11-05 | 2022-11-09 | 100% | 100% | 100% | 0.71429 | 63.34 | 7.28 | 66.51 | 7.8 | 28.5 | 102.81 | 102.81 | 0 |  | 2022-11-05 | TRUE | 1.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 57 | 77564 | 80549 | Electrical Services Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3.8 | 1 | rm | 3.8 | 2022-11-05 | 2022-12-05 | 100% | 100% | 100% | 4.4286 | 63.34 | 7.28 | 168.48 | 122.51 | 72.21 | 363.2 | 363.2 | 0 |  | 2022-11-05 | TRUE | 3.8 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 58 | 77565 | 80528 | Column Cove Installation Work | Ground Level | Independent 1.8m wide | 1 | 3.8 | 2.5 | 3.5 | 1 | m2-LxH | 13.3 | 2022-11-07 | 2022-11-17 | 100% | 100% | 100% | 1.5714 | 16.76 | 0.77 | 156.04 | 16.09 | 66.87 | 239 | 239 | 0 |  | 2022-11-07 | TRUE | 13.3 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 59 | 77566 | 76794 | Cable Tray Removal Work | Basement 1 | Independent | 1 | 8.1 | 1.3 | 3 | 1 | m2-LxH | 24.3 | 2022-11-07 | 2022-11-08 | 100% | 100% | 100% | 0.28571 | 12.01 | 0.49 | 204.29 | 3.4 | 87.55 | 295.24 | 295.24 | 0 |  | 2022-11-07 | TRUE | 24.3 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 8r | 77567 | 80533 | Glass Fixing work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 10.8 | 1 | 1 | 1 | m2-LxW | 10.8 | 2022-11-05 | 2022-11-25 | 100% | 100% | 100% | 3 | 36.52 | 2.94 | 276.09 | 95.26 | 118.32 | 489.67 | 489.67 | 0 |  | 2022-11-05 | TRUE | 10.8 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 60 | 77568 | 80512 | Balustrade Glass Edge Protection | Level 25 | Buttress | 1 | 2.5 | 1.8 | 2 |  | m3 | 9 | 2022-11-07 | 2022-11-11 | 100% | 100% | 100% | 0.71429 | 5.29 | 0.35 | 33.33 | 2.25 | 14.28 | 49.86 | 49.86 | 0 |  | 2022-11-07 | TRUE | 9 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 60a | 77569 | 80512 | Balustrade Glass Edge Protection | Level 25 | Tripple Hnadrail | 1 | 3 |  | 1.5 |  | lm | 3 | 2022-11-07 | 2022-11-11 | 100% | 100% | 100% | 0.71429 | 15 | 0.91 | 31.5 | 1.95 | 13.5 | 46.95 | 46.95 | 0 |  | 2022-11-07 | TRUE | 3 | TRUE
E11/K149/PK/dm/400 | RESIDENCE | 61 | 77578 | 80513 | OME Corridoor Mep Work | Ground Level | Design - 1399-22 | 1 | 24.3 | 1 | 4 | 1 | m2-LxH | 97.2 | 2022-11-07 | 2022-11-14 | 100% | 100% | 100% | 1.1429 | 115.4699 | 2.27 | 7856.57 | 252.16 | 3367.1 | 11475.83 | 11475.83 | 0 | Prorate Tas Quote - 2439-19-1 | 2022-11-07 | TRUE | 97.2 | TRUE
| RESIDENCE | 62 | 77570 |  | Back Propping For Mast Climber | Basement 1 | Design - 1399-24 | 1 |  |  |  |  | unit | 1 | 2022-11-08 |  | 100% | 100% | 0% | 15.7143 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 2022-11-08 | TRUE | 1 | TRUE
| RESIDENCE | 63 | 77571 |  | Back Propping For Mast Climber | Basement 1 | Design - 1399-24 | 1 |  |  |  |  | unit | 1 | 2022-11-08 |  | 100% | 100% | 0% | 15.7143 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 2022-11-08 | TRUE | 1 | TRUE
| RESIDENCE | 64 | 77572 |  | Back Propping For Mast Climber | Basement 2 | Design - 1399-20E | 1 |  |  |  |  | unit | 1 | 2022-11-09 |  | 100% | 100% | 0% | 15.5714 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 2022-11-09 | TRUE | 1 | TRUE
| RESIDENCE | 65 | 77573 |  | Back Propping For Mast Climber | Basement 2 | Design - 1399-20E | 1 |  |  |  |  | unit | 1 | 2022-11-09 |  | 100% | 100% | 0% | 15.5714 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 2022-11-09 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 19e | 77574 | 80522 | Shaft - 9 Ducting Work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 2 | 1 | 1 | 1 | m2-LxW | 2 | 2022-11-09 | 2022-11-14 | 100% | 100% | 100% | 0.85714 | 36.52 | 2.94 | 51.13 | 5.04 | 21.91 | 78.08 | 78.08 | 0 |  | 2022-11-09 | TRUE | 2 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 61a | 77582 | 80514 | Corridor KMEP Work | Ground Level | Independent 1.8m wide | 1 | 4 | 2.5 | 4 | 1 | m2-LxH | 16 | 2022-11-09 | 2022-11-14 | 100% | 100% | 100% | 0.85714 | 16.76 | 0.77 | 187.71 | 10.56 | 80.45 | 278.72 | 278.72 | 0 |  | 2022-11-09 | TRUE | 16 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 19f | 77575 | 80505 | Shaft - 9 Ducting Work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-11-10 | 2022-11-10 | 100% | 100% | 100% | 0.14286 | 36.52 | 2.94 | 38.35 | 0.63 | 16.43 | 55.41 | 55.41 | 0 |  | 2022-11-10 | TRUE | 1.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 66 | 77576 | 80872 | Pool Plant Room (KMEP Work) | Level 3 | Tower | 1 | 2.5 | 1.8 | 2 | 1 | rm | 2 | 2022-11-10 | 2023-01-09 | 100% | 100% | 100% | 8.7143 | 63.34 | 7.28 | 88.68 | 126.88 | 38 | 253.56 | 253.56 | 0 | (BW-0754) | 2022-11-10 | TRUE | 2 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 67 | 77577 | 80530 | Entrance Area Glass Work | Ground Level | Birdcage | 1 | 3.1 | 2.6 | 4 | 1 | m3 | 32.24 | 2022-11-10 | 2022-11-19 | 100% | 100% | 100% | 1.4286 | 7.08 | 0.49 | 159.78 | 22.57 | 68.48 | 250.83 | 250.83 | 0 | (Glass Line - BW-002) | 2022-11-10 | TRUE | 32.24 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 68 | 77579 |  | Staircase - Electrical Work | Level 2 to 3 | Independent | 1 | 6.3 | 1.3 | 3 | 1 | m2-LxH | 18.9 | 2022-11-10 |  | 100% | 100% | 0% | 15.4286 | 12.01 | 0.49 | 158.89 | 142.88 | 0 | 301.77 | 260.76 | 41.01 | (BW-0754) | 2022-11-10 | TRUE | 18.9 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 68a | 77580 |  | Staircase - Electrical Work | Level 2 to 3 | Independent | 1 | 3.5 | 1.3 | 4.5 | 1 | m2-LxH | 15.75 | 2022-11-10 |  | 100% | 100% | 0% | 15.4286 | 12.01 | 0.49 | 132.41 | 119.07 | 0 | 251.48 | 217.3 | 34.18 | (BW-0754) | 2022-11-10 | TRUE | 15.75 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 69 | 77581 | 80518 | Electrical Service Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 4 | 1 | rm | 4 | 2022-11-11 | 2022-11-14 | 100% | 100% | 100% | 0.57143 | 63.34 | 7.28 | 177.35 | 16.64 | 76.01 | 270 | 270 | 0 |  | 2022-11-11 | TRUE | 4 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 70 | 77583 | 80554 | Entrance Storage room (KMEP) | Ground Level | Tower | 1 | 1.3 | 0.9 | 4 | 1 | rm | 4 | 2022-11-11 | 2022-12-06 | 100% | 100% | 100% | 3.7143 | 63.34 | 7.28 | 177.35 | 108.16 | 76.01 | 361.52 | 361.52 | 0 |  | 2022-11-11 | TRUE | 4 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 70 | 77583 | 80554 | Entrance Storage room (KMEP) | Ground Level | Additional Boarding | 1 | 1.3 | 0.9 | 1 | 1 | m2-LxW | 1.17 | 2022-11-11 | 2022-12-06 | 100% | 100% | 100% | 3.7143 | 6.63 | 0.7 | 5.43 | 3.04 | 2.33 | 10.8 | 10.8 | 0 |  | 2022-11-11 | TRUE | 1.17 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 71 | 77584 | 80520 | BOH Corridor Block Work | Ground Level | Tower | 1 | 2.5 | 1.3 | 4 | 1 | rm | 4 | 2022-11-11 | 2022-11-15 | 100% | 100% | 100% | 0.71429 | 63.34 | 7.28 | 177.35 | 20.8 | 76.01 | 274.16 | 274.16 | 0 |  | 2022-11-11 | TRUE | 4 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 71 | 77584 | 80520 | BOH Corridor Block Work | Ground Level | Additional Boarding | 1 | 2.5 | 1.3 | 1 | 1 | m2-LxW | 3.25 | 2022-11-11 | 2022-11-15 | 100% | 100% | 100% | 0.71429 | 6.63 | 0.7 | 15.08 | 1.63 | 6.46 | 23.17 | 23.17 | 0 |  | 2022-11-11 | TRUE | 3.25 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 72 | 77585 | 80890 | Lift Lobby Fire Curtain Work | Ground Level | Tower | 1 | 2.5 | 1.3 | 2.2 | 1 | rm | 2.2 | 2022-11-11 | 2023-01-17 | 100% | 100% | 100% | 9.7143 | 63.34 | 7.28 | 97.54 | 155.58 | 41.8 | 294.92 | 294.92 | 0 |  | 2022-11-11 | TRUE | 2.2 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 73 | 77586 | 80521 | BOH Corridor Block Work | Ground Level | Tower | 1 | 1.8 | 1.3 | 4.5 | 1 | rm | 4.5 | 2022-11-11 | 2022-11-15 | 100% | 100% | 100% | 0.71429 | 63.34 | 7.28 | 199.52 | 23.4 | 85.51 | 308.43 | 308.43 | 0 |  | 2022-11-11 | TRUE | 4.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 73 | 77586 | 80521 | BOH Corridor Block Work | Ground Level | Additional Boarding | 1 | 1.8 | 1.3 | 1 | 1 | m2-LxW | 2.34 | 2022-11-11 | 2022-11-15 | 100% | 100% | 100% | 0.71429 | 6.63 | 0.7 | 10.86 | 1.17 | 4.65 | 16.68 | 16.68 | 0 |  | 2022-11-11 | TRUE | 2.34 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 74 | 77587 | 80524 | BOH Corridor Shaft Block Work | Ground Level | Tower | 1 | 1.8 | 1.3 | 4 | 1 | rm | 4 | 2022-11-11 | 2022-11-16 | 100% | 100% | 100% | 0.85714 | 63.34 | 7.28 | 177.35 | 24.96 | 76.01 | 278.32 | 278.32 | 0 |  | 2022-11-11 | TRUE | 4 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 74 | 77587 | 80524 | BOH Corridor Shaft Block Work | Ground Level | Additional Boarding | 1 | 1.8 | 1.3 | 1 | 2 | m2-LxW | 2.34 | 2022-11-11 | 2022-11-16 | 100% | 100% | 100% | 0.85714 | 6.63 | 0.7 | 10.86 | 1.4 | 4.65 | 16.91 | 16.91 | 0 |  | 2022-11-11 | TRUE | 2.34 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 75 | 77588 | 80519 | Electrical Services Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 2 | 1 | rm | 2 | 2022-11-12 | 2022-11-15 | 100% | 100% | 100% | 0.57143 | 63.34 | 7.28 | 88.68 | 8.32 | 38 | 135 | 135 | 0 |  | 2022-11-12 | TRUE | 2 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 76 | 77589 | 80546 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3.5 | 1 | rm | 3.5 | 2022-11-14 | 2022-11-29 | 100% | 100% | 100% | 2.2857 | 63.34 | 7.28 | 155.18 | 58.24 | 66.51 | 279.93 | 279.93 | 0 |  | 2022-11-14 | TRUE | 3.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 1o | 77501 | 80556 | Drainge Pipe Connection | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 1.8 | 1 | 1 | 1 | m2-LxW | 1.8 | 2022-11-14 | 2022-12-06 | 100% | 100% | 100% | 3.2857 | 36.52 | 2.94 | 46.02 | 17.39 | 19.72 | 83.13 | 83.13 | 0 |  | 2022-11-14 | TRUE | 1.8 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 77 | 77503 | 80564 | Chill Water Pipe For (KMEP) | Level 2 | Independent 1.8m wide | 1 | 4 | 2.5 | 1.5 | 1 | m2-LxH | 6 | 2022-11-15 | 2022-12-10 | 100% | 100% | 100% | 3.7143 | 16.76 | 0.77 | 70.39 | 17.16 | 30.17 | 117.72 | 117.72 | 0 |  | 2022-11-15 | TRUE | 6 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 78 | 77504 | 80532 | Lift 3 Gypsum Work | Level 2 | Tower | 1 | 1.8 | 1.3 | 2 | 1 | rm | 2 | 2022-11-15 | 2022-11-19 | 100% | 100% | 100% | 0.71429 | 63.34 | 7.28 | 88.68 | 10.4 | 38 | 137.08 | 137.08 | 0 |  | 2022-11-15 | TRUE | 2 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 79 | 77590 | 80551 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 2.5 | 2.5 | 1 | rm | 2.5 | 2022-11-15 | 2022-12-05 | 100% | 100% | 100% | 3 | 63.34 | 7.28 | 110.85 | 54.6 | 47.51 | 212.96 | 212.96 | 0 |  | 2022-11-15 | TRUE | 2.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 79a | 77591 | 80552 | Cable Pulling Work | Basement 1 | Tower | 1 | 2 | 1 | 3 | 1 | rm | 3 | 2022-11-15 | 2022-12-05 | 100% | 100% | 100% | 3 | 63.34 | 7.28 | 133.01 | 65.52 | 57.01 | 255.54 | 255.54 | 0 |  | 2022-11-15 | TRUE | 3 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 80 | 77592 | 80550 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 1.8 | 3.7 | 1 | rm | 3.7 | 2022-11-15 | 2022-12-05 | 100% | 100% | 100% | 3 | 63.34 | 7.28 | 164.05 | 80.81 | 70.31 | 315.17 | 315.17 | 0 |  | 2022-11-15 | TRUE | 3.7 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 81 | 77593 | 80543 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3.7 | 1 | rm | 3.7 | 2022-11-15 | 2022-11-29 | 100% | 100% | 100% | 2.1429 | 63.34 | 7.28 | 164.05 | 57.72 | 70.31 | 292.08 | 292.08 | 0 |  | 2022-11-15 | TRUE | 3.7 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 81 | 77593 | 80543 | Cable Pulling Work | Basement 1 | Additional Boarding | 1 | 2.5 | 1.3 | 1 | 1 | m2-LxW | 3.25 | 2022-11-15 | 2022-11-29 | 100% | 100% | 100% | 2.1429 | 6.63 | 0.7 | 15.08 | 4.88 | 6.46 | 26.42 | 26.42 | 0 |  | 2022-11-15 | TRUE | 3.25 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 82 | 77594 | 80544 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3 | 1 | rm | 3 | 2022-11-15 | 2022-11-29 | 100% | 100% | 100% | 2.1429 | 63.34 | 7.28 | 133.01 | 46.8 | 57.01 | 236.82 | 236.82 | 0 |  | 2022-11-15 | TRUE | 3 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 83 | 77595 | 80547 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3.5 | 1 | rm | 3.5 | 2022-11-15 | 2022-11-29 | 100% | 100% | 100% | 2.1429 | 63.34 | 7.28 | 155.18 | 54.6 | 66.51 | 276.29 | 276.29 | 0 |  | 2022-11-15 | TRUE | 3.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 19g | 77502 | 80537 | Shaft 9 Duct Fixing Work | Level 31 | Cantilever (0 < 0.5m width) | 1 | 4.5 | 0.5 | 1 | 1 | m2-LxW | 2.25 | 2022-11-14 | 2022-11-28 | 100% | 100% | 100% | 2.1429 | 32.75 | 1.05 | 51.58 | 5.06 | 22.11 | 78.75 | 78.75 | 0 |  | 2022-11-14 | TRUE | 2.25 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 84 | 77505 | 80892 | Ceiling Opening and Closing for (KMEP) | Ground Level | Mobile Tower | 1 | 2.5 | 1.8 | 3.7 | 1 | rm | 3.7 | 2022-11-16 | 2023-01-17 | 100% | 100% | 100% | 9 | 103.33 | 10.29 | 267.62 | 342.66 | 114.7 | 724.98 | 724.98 | 0 |  | 2022-11-16 | TRUE | 3.7 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 85 | 77506 | 80560 | Duct Fixing Work | Basement 1 | Independent | 1 | 6.3 | 1.3 | 2 | 1 | m2-LxH | 12.6 | 2022-11-16 | 2022-12-10 | 100% | 100% | 100% | 3.5714 | 12.01 | 0.49 | 105.93 | 22.05 | 45.4 | 173.38 | 173.38 | 0 |  | 2022-11-16 | TRUE | 12.6 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 86 | 77507 | 80531 | Lift 3 Gypsum Work | Level 2 | Tower | 1 | 1.3 | 0.9 | 2 | 1 | rm | 2 | 2022-11-16 | 2022-11-19 | 100% | 100% | 100% | 0.57143 | 63.34 | 7.28 | 88.68 | 8.32 | 38 | 135 | 135 | 0 |  | 2022-11-16 | TRUE | 2 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 87 | 77508 | 80572 | Lift Lobby Glass Line Work | Ground Level | Tower | 1 | 2.5 | 1.3 | 4 | 1 | rm | 4 | 2022-11-17 | 2022-12-13 | 100% | 100% | 100% | 3.8571 | 63.34 | 7.28 | 177.35 | 112.32 | 76.01 | 365.68 | 365.68 | 0 |  | 2022-11-17 | TRUE | 4 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 87 | 77508 | 80572 | Lift Lobby Glass Line Work | Ground Level | Additional Boarding | 1 | 2.5 | 1.3 | 1 | 1 | m2-LxW | 3.25 | 2022-11-17 | 2022-12-13 | 100% | 100% | 100% | 3.8571 | 6.63 | 0.7 | 15.08 | 8.78 | 6.46 | 30.32 | 30.32 | 0 |  | 2022-11-17 | TRUE | 3.25 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 88 | 77509 |  | BOH Corridor Lift 1&2 Wall Finishing Work | Ground Level | Independent | 1 | 14.6 | 1.3 | 4 | 1 | m2-LxH | 58.4 | 2022-11-17 |  | 100% | 100% | 0% | 14.4286 | 12.01 | 0.49 | 490.97 | 412.89 | 0 | 903.86 | 777.13 | 126.73 |  | 2022-11-17 | TRUE | 58.4 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 88 | 77509 |  | BOH Corridor Lift 1&2 Wall Finishing Work | Ground Level | Additional Boarding | 1 | 14.6 | 1.3 | 1 | 1 | m2-LxW | 18.98 | 2022-11-17 |  | 100% | 100% | 0% | 14.4286 | 6.63 | 0.7 | 88.09 | 191.7 | 0 | 279.79 | 220.95 | 58.84 |  | 2022-11-17 | TRUE | 18.98 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 8s | 77510 | 78609 | Glass Fixing work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 3.5 | 1 | 1 | 1 | m2-LxW | 3.5 | 2022-11-17 | 2023-01-28 | 100% | 100% | 100% | 10.4286 | 36.52 | 2.94 | 89.47 | 107.31 | 38.35 | 235.13 | 192.37 | 42.76 |  | 2022-11-17 | TRUE | 3.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 89 | 77511 |  | BOH Corridor Lift 1&2 Wall Finishing Work | Ground Level | Independent 1.8m wide | 1 | 5.8 | 2.5 | 4 | 1 | m2-LxH | 23.2 | 2022-11-18 |  | 100% | 100% | 0% | 14.2857 | 16.76 | 0.77 | 272.18 | 255.2 | 0 | 527.38 | 448.27 | 79.11 |  | 2022-11-18 | TRUE | 23.2 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 89 | 77511 |  | BOH Corridor Lift 1&2 Wall Finishing Work | Ground Level | Additional Boarding | 1 | 5.8 | 2.5 | 1 | 1 | m2-LxW | 14.5 | 2022-11-18 |  | 100% | 100% | 0% | 14.2857 | 6.63 | 0.7 | 67.29 | 145 | 0 | 212.29 | 167.34 | 44.95 |  | 2022-11-18 | TRUE | 14.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 89a | 77512 |  | BOH Corridor Lift 1&2 Wall Finishing Work | Ground Level | Tower | 1 | 1 | 0.9 | 4 | 1 | rm | 4 | 2022-11-18 |  | 100% | 100% | 0% | 14.2857 | 63.34 | 7.28 | 177.35 | 416 | 0 | 593.35 | 464.39 | 128.96 |  | 2022-11-18 | TRUE | 4 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 89a | 77512 |  | BOH Corridor Lift 1&2 Wall Finishing Work | Ground Level | Additional Boarding | 1 | 1 | 0.9 | 1 | 1 | m2-LxW | 0.9 | 2022-11-18 |  | 100% | 100% | 0% | 14.2857 | 6.63 | 0.7 | 4.18 | 9 | 0 | 13.18 | 10.39 | 2.79 |  | 2022-11-18 | TRUE | 0.9 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 90 | 77513 | 80574 | Chill Water Pipe For (KMEP) | Ground Level | Birdcage | 1 | 5 | 3.1 | 4 | 1 | m3 | 62 | 2022-11-19 | 2022-12-16 | 100% | 100% | 100% | 4 | 7.08 | 0.49 | 307.27 | 121.52 | 131.69 | 560.48 | 560.48 | 0 |  | 2022-11-19 | TRUE | 62 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 90 | 77513 | 80574 | Chill Water Pipe For (KMEP) | Ground Level | Additional Boarding | 1 | 5 | 3.1 | 1 | 1 | m2-LxW | 15.5 | 2022-11-19 | 2022-12-16 | 100% | 100% | 100% | 4 | 6.63 | 0.7 | 71.94 | 43.4 | 30.83 | 146.17 | 146.17 | 0 |  | 2022-11-19 | TRUE | 15.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 91 | 77514 | 80541 | Lift Lobby Block Shifting Work | Ground Level | Tower | 1 | 1.3 | 0.9 | 1 | 1 | rm | 1 | 2022-11-19 | 2022-11-28 | 100% | 100% | 100% | 1.4286 | 63.34 | 7.28 | 44.34 | 10.4 | 19 | 73.74 | 73.74 | 0 |  | 2022-11-19 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 87a | 77515 | 80542 | Block Work | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 2.5 | 0.75 | 1 | 1 | m2-LxW | 1.88 | 2022-11-19 | 2022-11-28 | 100% | 100% | 100% | 1.4286 | 36.52 | 2.94 | 48.06 | 7.9 | 20.6 | 76.56 | 76.56 | 0 |  | 2022-11-19 | TRUE | 1.88 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 90a | 77516 | 80575 | BOH Corridor For Chill Pipe (KMEP) | Ground Level | Tower | 1 | 2 | 1.3 | 3.5 | 1 | rm | 3.5 | 2022-11-21 | 2022-12-16 | 100% | 100% | 100% | 3.7143 | 63.34 | 7.28 | 155.18 | 94.64 | 66.51 | 316.33 | 316.33 | 0 |  | 2022-11-21 | TRUE | 3.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 92 | 77517 | 78610 | Balcony Side Glass Installation | Level 1 | Tower | 1 | 2.5 | 1.8 | 5.5 | 1 | rm | 5.5 | 2022-11-21 | 2023-01-30 | 100% | 100% | 100% | 10.1429 | 63.34 | 7.28 | 243.86 | 406.12 | 104.51 | 754.49 | 621.38 | 133.11 |  | 2022-11-21 | TRUE | 5.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 92 | 77517 | 78610 | Balcony Side Glass Installation | Level 1 | Additional Boarding | 1 | 2.5 | 1.8 | 1 | 1 | m2-LxW | 4.5 | 2022-11-21 | 2023-01-30 | 100% | 100% | 100% | 10.1429 | 6.63 | 0.7 | 20.88 | 31.95 | 8.95 | 61.78 | 50.58 | 11.2 |  | 2022-11-21 | TRUE | 4.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 93 | 77518 | 80883 | Canal Side For Ceiling Work (KMEP- BW 0804) | Ground Level | Mobile Tower | 1 | 2.5 | 1.8 | 3.7 | 1 | rm | 3.7 | 2022-11-22 | 2023-01-10 | 100% | 100% | 100% | 7.1429 | 103.33 | 10.29 | 267.62 | 271.95 | 114.7 | 654.27 | 654.27 | 0 |  | 2022-11-22 | TRUE | 3.7 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 94 | 77519 |  | KCE Site Office area Chill Water Pipe (KMEP-BW 767) | Ground Level | Independent | 1 | 5.4 | 1.3 | 4 | 1 | m2-LxH | 21.6 | 2022-11-22 |  | 100% | 100% | 0% | 13.7143 | 12.01 | 0.49 | 181.59 | 145.15 | 0 | 326.74 | 279.87 | 46.87 |  | 2022-11-22 | TRUE | 21.6 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 94a | 77520 |  | KCE Site Office area Chill Water Pipe (KMEP-BW 767) | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 5.4 | 0.75 | 1 | 1 | m2-LxW | 4.05 | 2022-11-22 |  | 100% | 100% | 0% | 13.7143 | 36.52 | 2.94 | 103.53 | 163.3 | 0 | 266.83 | 214.1 | 52.73 |  | 2022-11-22 | TRUE | 4.05 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 94b | 77521 |  | KCE Site Office area Chill Water Pipe (KMEP-BW 767) | Ground Level | Independent 1.8m wide | 1 | 4.9 | 2.5 | 4 | 1 | m2-LxH | 19.6 | 2022-11-22 |  | 100% | 100% | 0% | 13.7143 | 16.76 | 0.77 | 229.95 | 206.98 | 0 | 436.93 | 370.09 | 66.84 |  | 2022-11-22 | TRUE | 19.6 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 94c | 77522 |  | KCE Site Office area Chill Water Pipe (KMEP-BW 767) | Ground Level | Tower | 1 | 2.5 | 1.8 | 4 | 1 | rm | 4 | 2022-11-22 |  | 100% | 100% | 0% | 13.7143 | 63.34 | 7.28 | 177.35 | 399.36 | 0 | 576.71 | 447.75 | 128.96 |  | 2022-11-22 | TRUE | 4 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 95 | 77523 | 80873 | Shaft Water Meter Room For (KMEP-BW 797) | Level 4 | Tower | 1 | 1 | 0.6 | 2 | 1 | rm | 2 | 2022-11-23 | 2023-01-09 | 100% | 100% | 100% | 6.8571 | 63.34 | 7.28 | 88.68 | 99.84 | 38 | 226.52 | 226.52 | 0 |  | 2022-11-23 | TRUE | 2 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 96 | 77524 | 80874 | Pump Room For Water Master (BW 024) | Level 3 | Independent 1.8m wide | 1 | 8 | 2.5 | 1.5 | 1 | m2-LxH | 12 | 2022-11-23 | 2023-01-09 | 100% | 100% | 100% | 6.8571 | 16.76 | 0.77 | 140.78 | 63.36 | 60.34 | 264.48 | 264.48 | 0 |  | 2022-11-23 | TRUE | 12 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 97 | 77525 | 80569 | Pump Room For Water Master (BW 024) | Level 3 | Tower | 1 | 2.5 | 1.3 | 1.5 | 1 | rm | 1.5 | 2022-11-23 | 2022-12-14 | 100% | 100% | 100% | 3.1429 | 63.34 | 7.28 | 66.51 | 34.32 | 28.5 | 129.33 | 129.33 | 0 |  | 2022-11-23 | TRUE | 1.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 98 | 77526 | 80876 | Shaft Water Meter Room For (KMEP-BW 797) | Level 2 | Tower | 1 | 1 | 0.6 | 2 | 1 | rm | 2 | 2022-11-23 | 2023-01-09 | 100% | 100% | 100% | 6.8571 | 63.34 | 7.28 | 88.68 | 99.84 | 38 | 226.52 | 226.52 | 0 |  | 2022-11-23 | TRUE | 2 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 92a | 77527 | 80534 | Road Side Access For Glass Fixing | Level 2 | Cantilever (0 < 0.5m width) | 1 | 2.5 | 0.5 | 1 | 1 | m2-LxW | 1.25 | 2022-11-23 | 2022-11-24 | 100% | 100% | 100% | 0.28571 | 32.75 | 1.05 | 28.66 | 0.38 | 12.28 | 41.32 | 41.32 | 0 |  | 2022-11-23 | TRUE | 1.25 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 99 | 77529 | 80553 | Canal Side For Excavation Access | Ground Level | Tower | 1 | 1.3 | 1.3 | 1 | 1 | rm | 1 | 2022-11-24 | 2022-12-06 | 100% | 100% | 100% | 1.8571 | 63.34 | 7.28 | 44.34 | 13.52 | 19 | 76.86 | 76.86 | 0 |  | 2022-11-24 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 100 | 77530 | 78604 | Shaft Water Meter Room For (KMEP-BW 797) | Ground Level | Tower | 1 | 1 | 0.75 | 4 | 2 | rm | 4 | 2022-11-24 | 2023-01-26 | 100% | 100% | 100% | 9.1429 | 63.34 | 7.28 | 177.35 | 266.24 | 76.01 | 519.6 | 439.43 | 80.17 |  | 2022-11-24 | TRUE | 4 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 72a | 77531 | 80887 | Lift Lobby For Fire Curtain Work | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 2.5 | 0.75 | 1 | 1 | m2-LxW | 1.88 | 2022-11-24 | 2023-01-16 | 100% | 100% | 100% | 7.7143 | 36.52 | 2.94 | 48.06 | 42.64 | 20.6 | 111.3 | 111.3 | 0 |  | 2022-11-24 | TRUE | 1.88 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 101 | 77532 | 80885 | Shaft Water Meter Room For (KMEP-BW 797) | Level 5 | Tower | 1 | 1 | 0.5 | 4 | 2 | rm | 4 | 2022-11-25 | 2023-01-12 | 100% | 100% | 100% | 7 | 63.34 | 7.28 | 177.35 | 203.84 | 76.01 | 457.2 | 457.2 | 0 |  | 2022-11-25 | TRUE | 4 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 8t | 77533 |  | Glass Fixing work | Level 30 | Cantilever (0 < 0.5m width) | 1 | 10.8 | 0.5 | 1 | 1 | m2-LxW | 5.4 | 2022-11-25 |  | 100% | 100% | 0% | 13.2857 | 32.75 | 1.05 | 123.8 | 75.33 | 0 | 199.13 | 174.02 | 25.11 |  | 2022-11-25 | TRUE | 5.4 | TRUE
E11/K149/SK/dm/213 | HOTEL | 18 | 74639 | 76808 | Staircase 7 For Electrical Work | Basement 1 | Tower | 1 | 1.8 | 1.3 | 2 | 1 | rm | 2 | 2022-10-27 | 2022-11-05 | 100% | 100% | 100% | 1.4286 | 63.34 | 7.28 | 88.68 | 20.8 | 38 | 147.48 | 147.48 | 0 |  | 2022-10-27 | TRUE | 2 | TRUE
E11/K149/SK/dm/213 | HOTEL | 19 | 74640 | 76809 | Staircase 7 For Electrical Work | Basement 1 | Tower | 1 | 1.8 | 1.3 | 2.3 | 1 | rm | 2.3 | 2022-10-27 | 2022-11-05 | 100% | 100% | 100% | 1.4286 | 63.34 | 7.28 | 101.98 | 23.92 | 43.7 | 169.6 | 169.6 | 0 |  | 2022-10-27 | TRUE | 2.3 | TRUE
E11/K149/SK/dm/213 | HOTEL | 20 | 74641 | 76817 | Canal Side Column Cove Work | Ground Level | Tower | 1 | 2.5 | 2.5 | 5.5 | 1 | rm | 5.5 | 2022-10-31 | 2022-11-11 | 100% | 100% | 100% | 1.7143 | 63.34 | 7.28 | 243.86 | 68.64 | 104.51 | 417.01 | 417.01 | 0 |  | 2022-10-31 | TRUE | 5.5 | TRUE
E11/K149/SK/dm/259 | HOTEL | 21 | 74644 | 80946 | Inverted Scaffold | Level 29 | Design 1399 -06 rev-B | 1 | 23.5 | 1.8 | 4 | 1 | lm | 23.5 | 2022-10-31 | 2023-02-02 | 100% | 100% | 100% | 13.5714 | 1002.22 | 98.12 | 16486.52 | 31293.27 | 7065.65 | 54845.44 | 45144.57 | 9700.87 | Tas Quote - 2439-6-1 | 2022-10-31 | TRUE | 23.5 | TRUE
E11/K149/SK/dm/259 | HOTEL | 21 |  |  | Inverted Scaffold | Level 29 | Third Party Inspection ( Additional) | 1 |  |  |  |  | unit | 1 | 2022-10-31 | 2022-10-31 | 100% | 100% | 100% | 0.14286 | 1230 | 0 | 1230 | 0 | 0 | 1230 | 1230 | 0 | Additional Inspection | #N/A | #N/A | #N/A | #N/A
E11/K149/SK/dm/213 | HOTEL | 22 | 74642 | 76818 | Column Cove Installation Work | Ground Level | Tower | 1 | 2.5 | 2.5 | 5.5 | 1 | rm | 5.5 | 2022-10-31 | 2022-11-11 | 100% | 100% | 100% | 1.7143 | 63.34 | 7.28 | 243.86 | 68.64 | 104.51 | 417.01 | 417.01 | 0 |  | 2022-10-31 | TRUE | 5.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 23 | 74643 | 76819 | Column Cove Installation Work | Ground Level | Tower | 1 | 2.5 | 2.5 | 5.5 | 1 | rm | 5.5 | 2022-10-31 | 2022-11-12 | 100% | 100% | 100% | 1.8571 | 63.34 | 7.28 | 243.86 | 74.36 | 104.51 | 422.73 | 422.73 | 0 |  | 2022-10-31 | TRUE | 5.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 21a | 74645 | 76821 | Canal Side for Wall Cutting Work | Level 29 | Additional Boarding | 1 | 23.5 | 1 | 1 | 1 | m2-LxW | 23.5 | 2022-10-31 | 2022-11-11 | 100% | 100% | 100% | 1.7143 | 6.63 | 0.7 | 109.06 | 28.2 | 46.74 | 184 | 184 | 0 |  | 2022-10-31 | TRUE | 23.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 24 | 74646 | 76820 | Column Cove Installation Work | Ground Level | Independent 1.8m wide | 1 | 3.8 | 2.5 | 4.5 | 1 | m2-LxH | 17.1 | 2022-11-01 | 2022-11-11 | 100% | 100% | 100% | 1.5714 | 16.76 | 0.77 | 200.62 | 20.69 | 85.98 | 307.29 | 307.29 | 0 |  | 2022-11-01 | TRUE | 17.1 | TRUE
E11/K149/SK/dm/213 | HOTEL | 12a | 74647 | 80835 | Balcony Side Grc Removel & Pipe Connection | Level 12 | Cantilever (0 < 0.5m width) | 1 | 1.5 | 0.5 | 1 | 1 | m2-LxW | 0.75 | 2022-11-01 | 2022-12-21 | 100% | 100% | 100% | 7.2857 | 32.75 | 1.05 | 17.19 | 5.74 | 7.37 | 30.3 | 30.3 | 0 |  | 2022-11-01 | TRUE | 0.75 | TRUE
E11/K149/SK/dm/213 | HOTEL | 11a | 74648 | 80805 | Balcony Side Grc Work | Level 13 | Cantilever (0 < 0.5m width) | 1 | 1.5 | 0.5 | 1 | 1 | m2-LxW | 0.75 | 2022-11-01 | 2022-12-15 | 100% | 100% | 100% | 6.4286 | 32.75 | 1.05 | 17.19 | 5.06 | 7.37 | 29.62 | 29.62 | 0 |  | 2022-11-01 | TRUE | 0.75 | TRUE
E11/K149/SK/dm/213 | HOTEL | 14a | 74649 | 80806 | Balcony Side RFI-130 | Level 15 | Cantilever (0 < 0.5m width) | 1 | 1.5 | 0.5 | 1 | 1 | m2-LxW | 0.75 | 2022-11-02 | 2022-12-15 | 100% | 100% | 100% | 6.2857 | 32.75 | 1.05 | 17.19 | 4.95 | 7.37 | 29.51 | 29.51 | 0 |  | 2022-11-02 | TRUE | 0.75 | TRUE
E11/K149/SK/dm/213 | HOTEL | 25 | 77601 | 80807 | EIFS & Wall Finishing Work | Basement 1 | Independent | 1 | 9.3 | 1.3 | 6 | 1 | m2-LxH | 55.8 | 2022-11-02 | 2022-12-15 | 100% | 100% | 100% | 6.2857 | 12.01 | 0.49 | 469.11 | 171.86 | 201.05 | 842.02 | 842.02 | 0 |  | 2022-11-02 | TRUE | 55.8 | TRUE
E11/K149/SK/dm/213 | HOTEL | 25 | 77601 | 80807 | EIFS & Wall Finishing Work | Basement 1 | Additional Boarding | 1 | 9.3 | 1.3 | 1 | 1 | m2-LxW | 12.09 | 2022-11-02 | 2022-12-15 | 100% | 100% | 100% | 6.2857 | 6.63 | 0.7 | 56.11 | 53.2 | 24.05 | 133.36 | 133.36 | 0 |  | 2022-11-02 | TRUE | 12.09 | TRUE
E11/K149/SK/dm/213 | HOTEL | 25a | 77602 | 80808 | EIFS & Wall Finishing Work | Basement 1 | Independent | 1 | 10.5 | 1.3 | 4 | 1 | m2-LxH | 42 | 2022-11-02 | 2022-12-15 | 100% | 100% | 100% | 6.2857 | 12.01 | 0.49 | 353.09 | 129.36 | 151.33 | 633.78 | 633.78 | 0 |  | 2022-11-02 | TRUE | 42 | TRUE
E11/K149/SK/dm/213 | HOTEL | 26 | 77604 | 80839 | Plant Room For CHW Pipe | Level 5 | Independent | 1 | 6 | 1.5 | 2 | 1 | m2-LxH | 12 | 2022-11-04 | 2022-12-21 | 100% | 100% | 100% | 6.8571 | 12.01 | 0.49 | 100.88 | 40.32 | 43.24 | 184.44 | 184.44 | 0 |  | 2022-11-04 | TRUE | 12 | TRUE
E11/K149/SK/dm/213 | HOTEL | 26a | 77605 | 80840 | Plant Room For CHW Pipe | Level 5 | Independent 1.8m wide | 1 | 6 | 2 | 2.5 | 1 | m2-LxH | 15 | 2022-11-04 | 2022-12-21 | 100% | 100% | 100% | 6.8571 | 16.76 | 0.77 | 175.98 | 79.2 | 75.42 | 330.6 | 330.6 | 0 |  | 2022-11-04 | TRUE | 15 | TRUE
E11/K149/SK/dm/213 | HOTEL | 26b | 77606 | 80841 | Plant Room For CHW Pipe | Level 5 | Tower | 1 | 1.8 | 1.8 | 1 | 1 | rm | 1 | 2022-11-04 | 2022-12-21 | 100% | 100% | 100% | 6.8571 | 63.34 | 7.28 | 44.34 | 49.92 | 19 | 113.26 | 113.26 | 0 |  | 2022-11-04 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | HOTEL | 27 | 77607 | 76816 | Electrical Services Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 4 | 1 | rm | 4 | 2022-11-04 | 2022-11-11 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 177.35 | 33.28 | 76.01 | 286.64 | 286.64 | 0 |  | 2022-11-04 | TRUE | 4 | TRUE
E11/K149/SK/dm/213 | HOTEL | 28 | 77608 | 76824 | Bond Ceiling Work | Level 4 | Tower | 1 | 2.5 | 0.9 | 1.2 | 1 | rm | 1.2 | 2022-11-04 | 2022-11-11 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 53.21 | 9.98 | 22.8 | 85.99 | 85.99 | 0 |  | 2022-11-04 | TRUE | 1.2 | TRUE
E11/K149/SK/dm/213 | HOTEL | 29 | 77609 | 76825 | Bond Ceiling Work | Level 4 | Tower | 1 | 2.5 | 0.9 | 1.2 | 1 | rm | 1.2 | 2022-11-04 | 2022-11-11 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 53.21 | 9.98 | 22.8 | 85.99 | 85.99 | 0 |  | 2022-11-04 | TRUE | 1.2 | TRUE
E11/K149/SK/dm/213 | HOTEL | 30 | 77610 | 76826 | Bond Ceiling Work | Level 4 | Tower | 1 | 2.5 | 0.9 | 1.2 | 1 | rm | 1.2 | 2022-11-04 | 2022-11-11 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 53.21 | 9.98 | 22.8 | 85.99 | 85.99 | 0 |  | 2022-11-04 | TRUE | 1.2 | TRUE
E11/K149/SK/dm/259 | HOTEL | 31 | 77611 | 78577 | Inverted Scaffold | Level 29 | Design 1399 -06 rev-B | 1 | 22 | 1.8 | 4 | 1 | lm | 22 | 2022-11-04 | 2023-02-14 | 100% | 100% | 100% | 14.7143 | 1002.22 | 98.12 | 15434.19 | 31762.85 | 6614.65 | 53811.69 | 41029.49 | 12782.2 | Tas Quote - 2439-6-1 | 2022-11-04 | TRUE | 22 | TRUE
E11/K149/SK/dm/259 | HOTEL | 31 |  |  | Inverted Scaffold | Level 29 | Third Party Inspection ( Additional) | 1 |  |  |  |  | unit | 1 | 2022-11-04 |  | 100% | 100% | 0% | 16.2857 | 1230 | 0 | 1230 | 0 | 0 | 1230 | 1230 | 0 | Additional Inspection | #N/A | #N/A | #N/A | #N/A
E11/K149/SK/dm/213 | HOTEL | 31a | 77612 | 76822 | Inverted Scaffold | Level 29 | Additional Boarding | 1 | 22 | 1 | 1 | 1 | m2-LxW | 22 | 2022-11-04 | 2022-11-11 | 100% | 100% | 100% | 1.1429 | 6.63 | 0.7 | 102.1 | 17.6 | 43.76 | 163.46 | 163.46 | 0 |  | 2022-11-04 | TRUE | 22 | TRUE
E11/K149/SK/dm/213 | HOTEL | 32 | 77613 | 76814 | Electrical Services Work | Basement 1 | Independent | 1 | 3.8 | 1.3 | 2.5 | 1 | m2-LxH | 9.5 | 2022-11-04 | 2022-11-10 | 100% | 100% | 100% | 1 | 12.01 | 0.49 | 79.87 | 4.66 | 34.23 | 118.76 | 118.76 | 0 |  | 2022-11-04 | TRUE | 9.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 32a | 77614 | 76815 | Electrical Services Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 2.3 | 1 | rm | 2.3 | 2022-11-04 | 2022-11-10 | 100% | 100% | 100% | 1 | 63.34 | 7.28 | 101.98 | 16.74 | 43.7 | 162.42 | 162.42 | 0 |  | 2022-11-04 | TRUE | 2.3 | TRUE
E11/K149/SK/dm/213 | HOTEL | 33 | 77615 | 76827 | Bond Ceiling Work | Level 4 | Independent | 1 | 3 | 0.5 | 1.5 | 1 | m2-LxH | 4.5 | 2022-11-04 | 2022-11-11 | 100% | 100% | 100% | 1.1429 | 12.01 | 0.49 | 37.83 | 2.52 | 16.21 | 56.56 | 56.56 | 0 |  | 2022-11-04 | TRUE | 4.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 34 | 77616 | 80844 | Electrical Services Work | Basement 1 | Independent 1.8m wide | 1 | 3.8 | 2.5 | 3 | 1 | m2-LxH | 11.4 | 2022-11-07 | 2022-12-29 | 100% | 100% | 100% | 7.5714 | 16.76 | 0.77 | 133.74 | 66.46 | 57.32 | 257.52 | 257.52 | 0 |  | 2022-11-07 | TRUE | 11.4 | TRUE
E11/K149/SK/dm/213 | HOTEL | 35 | 77617 | 80845 | Electrical Services Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3.2 | 1 | rm | 3.2 | 2022-11-08 | 2022-12-29 | 100% | 100% | 100% | 7.4286 | 63.34 | 7.28 | 141.88 | 173.06 | 60.81 | 375.75 | 375.75 | 0 |  | 2022-11-08 | TRUE | 3.2 | TRUE
E11/K149/SK/dm/341 | HOTEL | 36 | 77618 | 76847 | Balcony Floor Drain Work | Level 18 to 20 | Independent 1.8m wide | 1 | 6 | 1.8 | 7 | 1 | unit | 1 | 2022-11-09 | 2022-12-12 | 100% | 100% | 100% | 4.8571 | 5277.5 | 48.26 | 3694.25 | 234.41 | 1583.25 | 5511.91 | 5511.91 | 0 | Tas Quote - 2439-12-2 (item-1) | 2022-11-09 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | HOTEL | 13a | 77619 | 80810 | Balcony Side Grc Removel & Ceiling Board Work | Level 14 | Cantilever (0 < 0.5m width) | 1 | 1.5 | 0.5 | 1 | 1 | m2-LxW | 0.75 | 2022-11-09 | 2022-12-17 | 100% | 100% | 100% | 5.5714 | 32.75 | 1.05 | 17.19 | 4.39 | 7.37 | 28.95 | 28.95 | 0 |  | 2022-11-09 | TRUE | 0.75 | TRUE
E11/K149/SK/dm/213 | HOTEL | 21b | 77620 | 80946 | Inverted Scaffold | Level 29 | Design 1399 -23 | 1 | 3 | 1.8 | 1 | 1 | m2-LxW | 5.4 | 2022-11-09 | 2023-02-02 | 100% | 100% | 100% | 12.2857 | 36.52 | 2.94 | 138.05 | 195.05 | 59.16 | 392.26 | 314.95 | 77.31 |  | 2022-11-09 | TRUE | 5.4 | TRUE
E11/K149/SK/dm/213 | HOTEL | 10b | 77621 | 80938 | Inverted Scaffold | Level 29 | Design 1399 -23 | 1 | 1.8 | 1.5 | 1 | 1 | m2-LxW | 2.7 | 2022-11-09 | 2023-01-31 | 100% | 100% | 100% | 12 | 36.52 | 2.94 | 69.02 | 95.26 | 29.58 | 193.86 | 157.47 | 36.39 |  | 2022-11-09 | TRUE | 2.7 | TRUE
E11/K149/SK/dm/213 | HOTEL | 31b | 77622 | 76823 | Edge Protection | Level 29 | Single Handrail | 1 | 41 | 1 | 1 |  | lm | 41 | 2022-11-09 | 2022-11-11 | 100% | 100% | 100% | 0.42857 | 7 | 0.42 | 200.9 | 7.38 | 86.1 | 294.38 | 294.38 | 0 |  | 2022-11-09 | TRUE | 41 | TRUE
E11/K149/SK/dm/213 | HOTEL | 37 | 77623 | 76813 | Chill Water line Pipe For Water Proof | Ground Level | Independent | 1 | 3 | 1.5 | 1 | 1 | m2-LxH | 3 | 2022-11-09 | 2022-11-10 | 100% | 100% | 100% | 0.28571 | 12.01 | 0.49 | 25.22 | 0.42 | 10.81 | 36.45 | 36.45 | 0 |  | 2022-11-09 | TRUE | 3 | TRUE
E11/K149/SK/dm/213 | HOTEL | 25b | 77624 |  | EIFS & Wall Finishing Work | Basement 1 | Independent | 1 | 5 | 1.3 | 2.2 | 1 | m2-LxH | 11 | 2022-11-10 |  | 100% | 100% | 0% | 15.4286 | 12.01 | 0.49 | 92.48 | 83.16 | 0 | 175.64 | 151.77 | 23.87 |  | 2022-11-10 | TRUE | 11 | TRUE
E11/K149/SK/dm/213 | HOTEL | 25c | 77625 |  | EIFS & Wall Finishing Work | Basement 1 | Independent | 1 | 8.3 | 1.3 | 2.2 | 1 | m2-LxH | 18.26 | 2022-11-10 |  | 100% | 100% | 0% | 15.4286 | 12.01 | 0.49 | 153.51 | 138.05 | 0 | 291.56 | 251.93 | 39.63 |  | 2022-11-10 | TRUE | 18.26 | TRUE
E11/K149/SK/dm/213 | HOTEL | 38 | 77626 | 76839 | Electrical Services Work | Basement 1 | Independent | 1 | 3.8 | 1.3 | 2.8 | 1 | m2-LxH | 10.64 | 2022-11-11 | 2022-12-05 | 100% | 100% | 100% | 3.5714 | 12.01 | 0.49 | 89.45 | 18.62 | 38.34 | 146.41 | 146.41 | 0 |  | 2022-11-11 | TRUE | 10.64 | TRUE
E11/K149/SK/dm/213 | HOTEL | 39 | 77627 | 80801 | Column Cove Installation Work | Ground Level | Independent 1.8m wide | 1 | 3.8 | 2.5 | 4 | 1 | m2-LxH | 15.2 | 2022-11-11 | 2022-11-17 | 100% | 100% | 100% | 1 | 16.76 | 0.77 | 178.33 | 11.7 | 76.43 | 266.46 | 266.46 | 0 |  | 2022-11-11 | TRUE | 15.2 | TRUE
E11/K149/SK/dm/213 | HOTEL | 40 | 77628 | 76833 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3.5 | 1 | rm | 3.5 | 2022-11-12 | 2022-11-29 | 100% | 100% | 100% | 2.5714 | 63.34 | 7.28 | 155.18 | 65.52 | 66.51 | 287.21 | 287.21 | 0 |  | 2022-11-12 | TRUE | 3.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 41 | 77629 | 76834 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3 | 1 | rm | 3 | 2022-11-12 | 2022-11-29 | 100% | 100% | 100% | 2.5714 | 63.34 | 7.28 | 133.01 | 56.16 | 57.01 | 246.18 | 246.18 | 0 |  | 2022-11-12 | TRUE | 3 | TRUE
E11/K149/SK/dm/213 | HOTEL | 42 | 77630 | 76829 | Cable Pulling Work | Basement 1 | Tower | 1 | 1.8 | 1.3 | 2.5 | 1 | rm | 2.5 | 2022-11-12 | 2022-11-29 | 100% | 100% | 100% | 2.5714 | 63.34 | 7.28 | 110.85 | 46.8 | 47.51 | 205.16 | 205.16 | 0 |  | 2022-11-12 | TRUE | 2.5 | TRUE
E11/K149/PK/dm/378 | HOTEL | 43&43a | 77633 | 80931 | Ramp Area GRC Pannel Fixing Work | Ground Level | Design 1399-21 | 1 | 9.1 | 1.3 | 5 | 1 | m2-LxH | 45.5 | 2022-11-14 | 2023-01-30 | 100% | 100% | 100% | 11.1429 | 95.9 | 13.9 | 3054.42 | 7047.3 | 1309.04 | 11410.76 | 9649.97 | 1760.79 | Tas Quote - 2439-15-1 (item-1 Prorate) | 2022-11-14 | TRUE | 45.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 44 | 77631 | 76835 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 4 | 1 | rm | 4 | 2022-11-15 | 2022-11-29 | 100% | 100% | 100% | 2.1429 | 63.34 | 7.28 | 177.35 | 62.4 | 76.01 | 315.76 | 315.76 | 0 |  | 2022-11-15 | TRUE | 4 | TRUE
E11/K149/SK/dm/213 | HOTEL | 45 | 77632 | 76830 | Cable Pulling Work | Basement 1 | Independent 1.8m wide | 1 | 5 | 2.5 | 3.25 | 1 | m2-LxH | 16.25 | 2022-11-15 | 2022-11-29 | 100% | 100% | 100% | 2.1429 | 16.76 | 0.77 | 190.65 | 26.81 | 81.71 | 299.17 | 299.17 | 0 |  | 2022-11-15 | TRUE | 16.25 | TRUE
E11/K149/SK/dm/213 | HOTEL | 2e | 77634 | 80830 | Duct Fixing Work (KMEP) | Level 5 | Additional Boarding | 1 | 3 | 1 | 1 | 1 | m2-LxW | 3 | 2022-11-16 | 2022-12-20 | 100% | 100% | 100% | 5 | 6.63 | 0.7 | 13.92 | 10.5 | 5.97 | 30.39 | 30.39 | 0 |  | 2022-11-16 | TRUE | 3 | TRUE
E11/K149/SK/dm/213 | HOTEL | 46 | 77635 | 76831 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 2.5 | 3 | 1 | rm | 3 | 2022-11-17 | 2022-11-29 | 100% | 100% | 100% | 1.8571 | 63.34 | 7.28 | 133.01 | 40.56 | 57.01 | 230.58 | 230.58 | 0 |  | 2022-11-17 | TRUE | 3 | TRUE
E11/K149/SK/dm/213 | HOTEL | 46a | 77636 | 76832 | Cable Pulling Work | Basement 1 | Buttress | 1 | 2.5 | 2.5 | 3 |  | m3 | 18.75 | 2022-11-17 | 2022-11-29 | 100% | 100% | 100% | 1.8571 | 5.29 | 0.35 | 69.43 | 12.19 | 29.76 | 111.38 | 111.38 | 0 |  | 2022-11-17 | TRUE | 18.75 | TRUE
E11/K149/SK/dm/213 | HOTEL | 47 | 77637 | 76836 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 2.5 | 4.2 | 1 | rm | 4.2 | 2022-11-17 | 2022-11-29 | 100% | 100% | 100% | 1.8571 | 63.34 | 7.28 | 186.22 | 56.78 | 79.81 | 322.81 | 322.81 | 0 |  | 2022-11-17 | TRUE | 4.2 | TRUE
E11/K149/SK/dm/213 | HOTEL | 48 | 77638 | 80837 | GRC Divider Removel | Level 12 | Tower | 1 | 1.8 | 1.8 | 1.5 | 1 | rm | 1.5 | 2022-11-17 | 2022-12-21 | 100% | 100% | 100% | 5 | 63.34 | 7.28 | 66.51 | 54.6 | 28.5 | 149.61 | 149.61 | 0 |  | 2022-11-17 | TRUE | 1.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 48a | 77638 | 80837 | GRC Divider Removel | Level 12 | Cantilever (0 < 0.5m width) | 1 | 3.5 | 0.5 | 1 | 1 | m2-LxW | 1.75 | 2022-11-17 | 2022-12-21 | 100% | 100% | 100% | 5 | 32.75 | 1.05 | 40.12 | 9.19 | 17.19 | 66.5 | 66.5 | 0 |  | 2022-11-17 | TRUE | 1.75 | TRUE
E11/K149/SK/dm/213 | HOTEL | 48a | 77638 | 80837 | GRC Divider Removel | Level 12 | Netting Supply & Install | 1 | 9 | 1 | 1 | 1 | m2-LxH | 9 | 2022-11-17 | 2022-12-21 | 100% | 100% | 100% | 5 | 8.52 | 0 | 53.68 | 0 | 23 | 76.68 | 76.68 | 0 |  | 2022-11-17 | TRUE | 9 | TRUE
E11/K149/SK/dm/213 | HOTEL | 36a | 77639 | 76848 | GRC Divider Removel | Level 18 to 20 | Tower | 1 | 1.8 | 1.8 | 7 | 1 | rm | 7 | 2022-11-17 | 2022-12-12 | 100% | 100% | 100% | 3.7143 | 63.34 | 7.28 | 310.37 | 189.28 | 133.01 | 632.66 | 632.66 | 0 |  | 2022-11-17 | TRUE | 7 | TRUE
E11/K149/SK/dm/213 | HOTEL | 36b | 77639 | 76849 | GRC Divider Removel | Level 18 to 20 | Cantilever (0 < 0.5m width) | 1 | 3 | 0.5 | 1 | 1 | m2-LxW | 1.5 | 2022-11-17 | 2022-12-12 | 100% | 100% | 100% | 3.7143 | 32.75 | 1.05 | 34.39 | 5.85 | 14.74 | 54.98 | 54.98 | 0 |  | 2022-11-17 | TRUE | 1.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 36b | 77639 | 76849 | GRC Divider Removel | Level 18 to 20 | Netting Supply & Install | 1 | 37.8 | 1 | 1 |  | m2-LxH | 37.8 | 2022-11-17 | 2022-12-12 | 100% | 100% | 100% | 3.7143 | 8.52 |  | 225.44 | 0 | 96.62 | 322.06 | 322.06 | 0 |  | 2022-11-17 | TRUE | 37.8 | TRUE
E11/K149/SK/dm/259 | HOTEL | 49 | 77640 | 78551 | Inverted Scaffold | Level 29 | Design 1399-26 | 1 | 21 | 1.8 | 4 | 1 | lm | 21 | 2022-11-17 | 2023-02-06 | 100% | 100% | 100% | 11.7143 | 1002.22 | 98.12 | 14732.63 | 24137.52 | 6313.99 | 45184.14 | 35337.83 | 9846.31 | Tas Quote - 2439-6-1 | 2022-11-17 | TRUE | 21 | TRUE
E11/K149/SK/dm/213 | HOTEL | 49a | 77641 | 78551 | Wall Cutting Work | Level 29 | Additional Boarding | 1 | 15 | 1 | 1 | 1 | m2-LxW | 15 | 2022-11-17 | 2023-02-06 | 100% | 100% | 100% | 11.7143 | 6.63 | 0.7 | 69.62 | 123 | 29.84 | 222.46 | 174.62 | 47.84 |  | 2022-11-17 | TRUE | 15 | TRUE
E11/K149/SK/dm/213 | HOTEL | 50 | 77642 | 76837 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 2.5 | 4 | 1 | rm | 4 | 2022-11-18 | 2022-11-29 | 100% | 100% | 100% | 1.7143 | 63.34 | 7.28 | 177.35 | 49.92 | 76.01 | 303.28 | 303.28 | 0 |  | 2022-11-18 | TRUE | 4 | TRUE
E11/K149/SK/dm/213 | HOTEL | 51 | 77643 | 79801 | Staircase 7 For Electrical Work | Ground Level | Independent 1.8m wide | 1 | 3.8 | 2.5 | 2.8 | 1 | m2-LxH | 10.64 | 2022-11-18 | 2023-02-22 | 100% | 100% | 100% | 13.8571 | 16.76 | 0.77 | 124.83 | 113.53 | 53.5 | 291.86 | 205.59 | 86.27 |  | 2022-11-18 | TRUE | 10.64 | TRUE
E11/K149/JA/dm/429 | HOTEL | 52 | 77645 |  | Balcony Access | Level 20 | Tower | 1 | 2.5 | 1.3 | 3.5 | 1 | unit | 1 | 2022-11-18 |  | 100% | 100% | 0% | 14.2857 | 1118.57 | 25.48 | 783 | 364 | 0 | 1147 | 1034.16 | 112.84 | Tas Quote -2439-20-1 (item#7) | 2022-11-18 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | HOTEL | 52a | 77645 |  | Balcony Access | Level 21 | Cantilever (0.5 > 1.2m width) | 1 | 1.3 | 0.75 | 1 | 1 | m2-LxW | 0.98 | 2022-11-18 |  | 100% | 100% | 0% | 14.2857 | 36.52 | 2.94 | 25.05 | 41.16 | 0 | 66.21 | 53.45 | 12.76 |  | 2022-11-18 | TRUE | 0.98 | TRUE
E11/K149/SK/dm/213 | HOTEL | 13b | 77646 | 80811 | GRC Divider Removel | Level 14 | Tower | 1 | 1.5 | 0.5 | 1.5 | 1 | rm | 1.5 | 2022-11-18 | 2022-12-17 | 100% | 100% | 100% | 4.2857 | 63.34 | 7.28 | 66.51 | 46.8 | 28.5 | 141.81 | 141.81 | 0 |  | 2022-11-18 | TRUE | 1.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 25d | 77647 | 76845 | Wall Finishing Work | Basement 1 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-11-19 | 2022-12-10 | 100% | 100% | 100% | 3.1429 | 36.52 | 2.94 | 38.35 | 13.86 | 16.43 | 68.64 | 68.64 | 0 |  | 2022-11-19 | TRUE | 1.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 51a | 77644 | 79802 | Staircase 7 For Electrical Work | Ground Level | Tower | 1 | 2.5 | 0.9 | 2.5 | 1 | rm | 2.5 | 2022-11-18 | 2023-02-22 | 100% | 100% | 100% | 13.8571 | 63.34 | 7.28 | 110.85 | 252.2 | 47.51 | 410.56 | 290.25 | 120.31 |  | 2022-11-18 | TRUE | 2.5 | TRUE
E11/K149/PK/dm/378 | HOTEL | 43b&43c | 77648 | 80931 | Ramp Area GRC Pannel Fixing Work | Ground Level | Design 1399-21 | 1 | 5.1 | 1.3 | 5 | 1 | m2-LxH | 25.5 | 2022-11-21 | 2023-01-30 | 100% | 100% | 100% | 10.1429 | 95.9 | 13.9 | 1711.82 | 3595.14 | 733.64 | 6040.6 | 5053.78 | 986.82 | Tas Quote - 2439-15-1 (item-1 Prorate) | 2022-11-21 | TRUE | 25.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 53 | 77649 | 80831 | Plant Room For Duct Work | Level 5 | Independent 1.8m wide | 1 | 4.3 | 1.8 | 4.5 | 1 | m2-LxH | 19.35 | 2022-11-21 | 2022-12-20 | 100% | 100% | 100% | 4.2857 | 16.76 | 0.77 | 227.01 | 63.86 | 97.29 | 388.16 | 388.16 | 0 |  | 2022-11-21 | TRUE | 19.35 | TRUE
E11/K149/SK/dm/213 | HOTEL | 53a | 79051 | 80832 | Plant Room For Duct Work | Level 5 | Tower | 1 | 2.5 | 1.8 | 2.5 | 1 | rm | 2.5 | 2022-11-22 | 2022-12-20 | 100% | 100% | 100% | 4.1429 | 63.34 | 7.28 | 110.85 | 75.4 | 47.51 | 233.76 | 233.76 | 0 |  | 2022-11-22 | TRUE | 2.5 | TRUE
E11/K149/JA/dm/429 | HOTEL | 54 | 79052 |  | Balcony Access | Level 10 | Tower | 1 | 2.5 | 1.3 | 4 | 1 | unit | 1 | 2022-11-22 |  | 100% | 100% | 0% | 13.7143 | 1278.36 | 29.12 | 894.85 | 399.36 | 0 | 1294.21 | 1165.25 | 128.96 | Tas Quote -2439-20-1 (item#2) | 2022-11-22 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | HOTEL | 54a | 79052 |  | Balcony Access | Level 10 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1.3 | 1 | 1 | m2-LxW | 1.95 | 2022-11-22 |  | 100% | 100% | 0% | 13.7143 | 36.52 | 2.94 | 49.85 | 78.62 | 0 | 128.47 | 103.09 | 25.38 |  | 2022-11-22 | TRUE | 1.95 | TRUE
E11/K149/SK/dm/213 | HOTEL | 55 | 79053 | 80812 | GRC Divider Removel | Level 13 | Tower | 1 | 2.5 | 1 | 4.7 | 1 | rm | 4.7 | 2022-11-22 | 2022-12-17 | 100% | 100% | 100% | 3.7143 | 63.34 | 7.28 | 208.39 | 127.09 | 89.31 | 424.79 | 424.79 | 0 |  | 2022-11-22 | TRUE | 4.7 | TRUE
E11/K149/SK/dm/213 | HOTEL | 55a | 79053 | 80812 | GRC Divider Removel | Level 13 | Cantilever (0 < 0.5m width) | 1 | 1 | 0.5 | 1 | 1 | m2-LxW | 0.5 | 2022-11-22 | 2022-12-17 | 100% | 100% | 100% | 3.7143 | 32.75 | 1.05 | 11.46 | 1.95 | 4.91 | 18.32 | 18.32 | 0 |  | 2022-11-22 | TRUE | 0.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 55 | 79053 | 80812 | GRC Divider Removel | Level 13 | Netting Supply & Install | 1 | 25 | 1 | 1 | 1 | m2-LxH | 25 | 2022-11-22 | 2022-12-17 | 100% | 100% | 100% | 3.7143 | 8.52 | 0 | 149.1 | 0 | 63.9 | 213 | 213 | 0 |  | 2022-11-22 | TRUE | 25 | TRUE
E11/K149/SK/dm/213 | HOTEL | 36c | 79054 | 76850 | GRC Divider Removel | Level 18 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1.2 | 1 | 1 | m2-LxW | 1.8 | 2022-11-22 | 2022-12-12 | 100% | 100% | 100% | 3 | 36.52 | 2.94 | 46.02 | 15.88 | 19.72 | 81.62 | 81.62 | 0 |  | 2022-11-22 | TRUE | 1.8 | TRUE
E11/K149/JA/dm/429 | HOTEL | 56 | 79055 |  | Balcony Access | Level 15 | Tower | 1 | 2.5 | 1 | 3.5 | 1 | unit | 1 | 2022-11-23 |  | 100% | 100% | 0% | 13.5714 | 1246.69 | 25.48 | 872.68 | 345.8 | 0 | 1218.48 | 1105.64 | 112.84 | Tas Quote -2439-20-1 (item#4) | 2022-11-23 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | HOTEL | 56a | 79055 |  | Balcony Access | Level 15 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-11-23 |  | 100% | 100% | 0% | 13.5714 | 36.52 | 2.94 | 38.35 | 59.85 | 0 | 98.2 | 78.67 | 19.53 |  | 2022-11-23 | TRUE | 1.5 | TRUE
E11/K149/JA/dm/429 | HOTEL | 57 | 79056 |  | Balcony Access | Level 18 | Tower | 1 | 2.5 | 1 | 6 | 3 | unit | 1 | 2022-11-23 |  | 100% | 100% | 0% | 13.5714 | 1783.37 | 40.04 | 1248.36 | 543.4 | 0 | 1791.76 | 1614.44 | 177.32 | Tas Quote -2439-20-1 (item#6) | 2022-11-23 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | HOTEL | 57a | 79056 |  | Balcony Access | Level 18 | Cantilever (0.5 > 1.2m width) | 1 | 1 | 1 | 1 | 1 | m2-LxW | 1 | 2022-11-23 |  | 100% | 100% | 0% | 13.5714 | 36.52 | 2.94 | 25.56 | 39.9 | 0 | 65.46 | 52.44 | 13.02 |  | 2022-11-23 | TRUE | 1 | TRUE
E11/K149/JA/dm/429 | HOTEL | 58 | 79057 |  | Balcony Access | Level 7 | Tower | 1 | 2.5 | 1 | 3.5 | 1 | unit | 1 | 2022-11-23 |  | 100% | 100% | 0% | 13.5714 | 1246.69 | 25.48 | 872.68 | 345.8 | 0 | 1218.48 | 1105.64 | 112.84 | Tas Quote -2439-20-1 (item#1) | 2022-11-23 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | HOTEL | 58a | 79057 |  | Balcony Access | Level 7 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-11-23 |  | 100% | 100% | 0% | 13.5714 | 36.52 | 2.94 | 38.35 | 59.85 | 0 | 98.2 | 78.67 | 19.53 |  | 2022-11-23 | TRUE | 1.5 | TRUE
E11/K149/JA/dm/429 | HOTEL | 59 | 79058 |  | Balcony Access | Level 13 | Tower | 1 | 2.5 | 1 | 3.5 | 1 | unit | 1 | 2022-11-24 |  | 100% | 100% | 0% | 13.4286 | 1246.69 | 25.48 | 872.68 | 342.16 | 0 | 1214.84 | 1102 | 112.84 | Tas Quote -2439-20-1 (item#3) | 2022-11-24 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | HOTEL | 59a | 79058 |  | Balcony Access | Level 13 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-11-24 |  | 100% | 100% | 0% | 13.4286 | 36.52 | 2.94 | 38.35 | 59.22 | 0 | 97.57 | 78.04 | 19.53 |  | 2022-11-24 | TRUE | 1.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 25e | 79059 | 76846 | Wall Finishing Work | Basement 1 | Independent | 1 | 4.1 | 1.3 | 1.5 | 1 | m2-LxH | 6.15 | 2022-11-24 | 2022-12-10 | 100% | 100% | 100% | 2.4286 | 12.01 | 0.49 | 51.7 | 7.32 | 22.16 | 81.18 | 81.18 | 0 |  | 2022-11-24 | TRUE | 6.15 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 102 | 77534 |  | KMEP BW-829 | Ground Level | Tower | 1 | 2.5 | 1.8 | 4 | 1 | rm | 4 | 2022-11-26 |  | 100% | 100% | 0% | 13.1429 | 63.34 | 7.28 | 177.35 | 382.72 | 0 | 560.07 | 431.11 | 128.96 |  | 2022-11-26 | TRUE | 4 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 103 | 77535 | 80591 | Planter Area For Water Tank Access | Ground Level | Independent 1.8m wide | 1 | 3 | 2.5 | 2.5 | 1 | m2-LxH | 7.5 | 2022-11-26 | 2022-12-27 | 100% | 100% | 100% | 4.5714 | 16.76 | 0.77 | 87.99 | 26.4 | 37.71 | 152.1 | 152.1 | 0 |  | 2022-11-26 | TRUE | 7.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 104 | 77536 | 80548 | Crane Extension Platform | Roof | Birdcage | 1 | 5.4 | 3.8 | 2 | 1 | m3 | 41.04 | 2022-11-26 | 2022-12-05 | 100% | 100% | 100% | 1.4286 | 7.08 | 0.49 | 203.39 | 28.73 | 87.17 | 319.29 | 319.29 | 0 |  | 2022-11-26 | TRUE | 41.04 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 104 | 77536 | 80548 | Crane Extension Platform | Roof | Netting Supply & Install | 1 | 18.4 | 1 | 1 |  | m2-LxH | 18.4 | 2022-11-26 | 2022-12-05 | 100% | 100% | 100% | 1.4286 | 8.52 | 0 | 109.74 | 0 | 47.03 | 156.77 | 156.77 | 0 |  | 2022-11-26 | TRUE | 18.4 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 105 | 77537 | 80558 | OME Office For Chill Water Pipe Work (KMEP BW-767) | Level 2 | Independent | 1 | 5 | 1.3 | 2.5 | 1 | m2-LxH | 12.5 | 2022-11-26 | 2022-12-10 | 100% | 100% | 100% | 2.1429 | 12.01 | 0.49 | 105.09 | 13.13 | 45.04 | 163.26 | 163.26 | 0 |  | 2022-11-26 | TRUE | 12.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 105a | 77538 | 80559 | OME Office For Chill Water Pipe Work (KMEP BW-767) | Level 2 | Tower | 1 | 2.5 | 1.8 | 2.5 | 1 | rm | 2.5 | 2022-11-26 | 2022-12-10 | 100% | 100% | 100% | 2.1429 | 63.34 | 7.28 | 110.85 | 39 | 47.51 | 197.36 | 197.36 | 0 |  | 2022-11-26 | TRUE | 2.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 106 | 77539 | 80592 | Planter Area For Water Tank Access | Ground Level | Independent 1.8m wide | 1 | 3 | 2 | 3.5 | 1 | m2-LxH | 10.5 | 2022-11-26 | 2022-12-27 | 100% | 100% | 100% | 4.5714 | 16.76 | 0.77 | 123.19 | 36.96 | 52.79 | 212.94 | 212.94 | 0 |  | 2022-11-26 | TRUE | 10.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 107 | 77540 | 80565 | Ramp Area For Wall Concret Work | Ground Level | Independent | 1 | 18.4 | 0.9 | 2 | 1 | m2-LxH | 36.8 | 2022-11-29 | 2022-12-12 | 100% | 100% | 100% | 2 | 12.01 | 0.49 | 309.38 | 36.06 | 132.59 | 478.03 | 478.03 | 0 |  | 2022-11-29 | TRUE | 36.8 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 107 | 77540 | 80565 | Ramp Area For Wall Concret Work | Ground Level | Netting Supply & Install | 1 | 97.9 | 1 | 1 |  | m2-LxH | 97.9 | 2022-11-29 | 2022-12-12 | 100% | 100% | 100% | 2 | 8.52 | 0 | 583.88 | 0 | 250.23 | 834.11 | 834.11 | 0 |  | 2022-11-29 | TRUE | 97.9 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 1r | 77541 |  | Canal Side For Glass Frame Installation | Level 30 | Cantilever (0 < 0.5m width) | 2 | 8.5 | 0.5 | 1 | 2 | m2-LxW | 8.5 | 2022-11-29 |  | 100% | 100% | 0% | 12.7143 | 32.75 | 1.05 | 194.86 | 113.48 | 0 | 308.34 | 268.81 | 39.53 |  | 2022-11-29 | TRUE | 8.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 1s | 77544 |  | Canal Side Glass Fixing Work | Level 30 to 31 | Additional Boarding | 4 | 5 | 1.8 | 1 | 4 | m2-LxW | 36 | 2022-11-30 |  | 100% | 100% | 0% | 12.5714 | 6.63 | 0.7 | 167.08 | 316.8 | 0 | 483.88 | 372.28 | 111.6 |  | 2022-11-30 | TRUE | 36 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 1s | 77544 |  | Canal Side Glass Fixing Work | Level 30 to 31 | Netting Supply & Install | 1 | 36 | 1 | 1 |  | m2-LxH | 36 | 2022-11-30 |  | 100% | 100% | 0% | 12.5714 | 8.52 | 0 | 214.7 | 0 | 0 | 214.7 | 214.7 | 0 |  | 2022-11-30 | TRUE | 36 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 110 | 77545 |  | KMEP BW | Level 2 | Tower | 1 | 2.5 | 1.3 | 6 | 1 | rm | 6 | 2022-11-30 |  | 100% | 100% | 0% | 12.5714 | 63.34 | 7.28 | 266.03 | 549.12 | 0 | 815.15 | 621.71 | 193.44 |  | 2022-11-30 | TRUE | 6 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 110 | 77545 |  | KMEP BW | Level 2 | Additional Boarding | 2 | 2.5 | 1.3 | 1 | 2 | m2-LxW | 6.5 | 2022-11-30 |  | 100% | 100% | 0% | 12.5714 | 6.63 | 0.7 | 30.17 | 57.2 | 0 | 87.37 | 67.22 | 20.15 |  | 2022-11-30 | TRUE | 6.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 110a | 77545 | 80875 | KMEP BW | Level 2 | Buttress | 1 | 2.5 | 2.5 | 3.5 |  | m3 | 21.88 | 2022-11-30 | 2023-01-06 | 100% | 100% | 100% | 5.4286 | 5.29 | 0.35 | 81.02 | 41.57 | 34.72 | 157.31 | 157.31 | 0 |  | 2022-11-30 | TRUE | 21.88 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 110b | 77546 |  | KMEP BW | Level 2 | Cantilever (0 < 0.5m width) | 3 | 1.3 | 0.5 | 1 | 3 | m2-LxW | 1.95 | 2022-11-30 |  | 100% | 100% | 0% | 12.5714 | 32.75 | 1.05 | 44.7 | 25.74 | 0 | 70.44 | 61.37 | 9.07 |  | 2022-11-30 | TRUE | 1.95 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 8u | 77547 |  | Balcony For Access | Level 29 | Additional Boarding | 2 | 1.8 | 1.8 | 1 | 2 | m2-LxW | 6.48 | 2022-12-05 |  | 100% | 100% | 0% | 11.8571 | 6.63 | 0.7 | 30.07 | 53.78 | 0 | 83.85 | 63.77 | 20.08 |  | 2022-12-05 | TRUE | 6.48 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 8v | 77548 |  | Balcony For Access | Level 29 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1.5 | 1 | 1 | m2-LxW | 2.25 | 2022-12-05 |  | 100% | 100% | 0% | 11.8571 | 36.52 | 2.94 | 57.52 | 78.44 | 0 | 135.96 | 106.66 | 29.3 |  | 2022-12-05 | TRUE | 2.25 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 1t | 77549 |  | Glass Fixing work | Level 31 | Cantilever (0 < 0.5m width) | 3 | 8.5 | 0.5 | 1 | 3 | m2-LxW | 12.75 | 2022-12-06 |  | 100% | 100% | 0% | 11.7143 | 32.75 | 1.05 | 292.29 | 156.83 | 0 | 449.12 | 389.83 | 59.29 |  | 2022-12-06 | TRUE | 12.75 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 1v | 79102 |  | Canal Side Glass Fixing Work | Level 30 | Additional Boarding | 1 | 7.2 | 1.8 | 1 | 1 | m2-LxW | 12.96 | 2022-12-06 |  | 100% | 100% | 0% | 11.7143 | 6.63 | 0.7 | 60.15 | 106.27 | 0 | 166.42 | 126.25 | 40.17 |  | 2022-12-06 | TRUE | 12.96 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 107a | 79118 | 80555 | Ramp Area For Wall Concret Work | Ground Level | Independent | 1 | 18.4 | 0.9 | 2 | 1 | m2-LxH | 36.8 | 2022-12-06 | 2022-12-07 | 100% | 100% | 100% | 0.28571 | 12.01 | 0.49 | 309.38 | 5.15 | 132.59 | 447.12 | 447.12 | 0 |  | 2022-12-06 | TRUE | 36.8 | TRUE
E11/K149/SK/dm/468 | RESIDENCE | 111 | 79106 |  | EIFS Fixing Work | Level 10 | Independent | 1 | 20 | 0.6 | 2.5 | 1 | unit | 1 | 2022-12-07 |  | 100% | 100% | 0% | 11.5714 | 2710.95 | 253.17 | 1897.67 | 2929.54 | 0 | 4827.21 | 3706.03 | 1121.18 | Tas Quote - 2439-21-1 (Item #1) | 2022-12-07 | TRUE | 1 | TRUE
E11/K149/SK/dm/468 | RESIDENCE | 111a | 79107 |  | EIFS Fixing Work | Level 10 | Independent | 1 | 2.6 | 1.3 | 2.6 | 2 | unit | 1 | 2022-12-07 |  | 100% | 100% | 0% | 11.5714 | 947.74 | 95.55 | 663.42 | 1105.65 | 0 | 1769.07 | 1345.92 | 423.15 | Tas Quote - 2439-21-1 (Item #2) | 2022-12-07 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 112 | 79105 | 78611 | House Keeping Lobby (KMEP BW-886) | Level 5 | Tower | 1 | 1.8 | 1.8 | 3.5 | 1 | rm | 3.5 | 2022-12-07 | 2023-01-30 | 100% | 100% | 100% | 7.8571 | 63.34 | 7.28 | 155.18 | 200.2 | 66.51 | 421.89 | 337.18 | 84.71 |  | 2022-12-07 | TRUE | 3.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 113 | 79110 | 80561 | Staircase 3 (KMEP BW-886) | Level 5 | Tower | 1 | 2.5 | 1 | 1.5 | 1 | rm | 1.5 | 2022-12-08 | 2022-12-10 | 100% | 100% | 100% | 0.42857 | 63.34 | 7.28 | 66.51 | 4.68 | 28.5 | 99.69 | 99.69 | 0 |  | 2022-12-08 | TRUE | 1.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 113a | 79111 | 80562 | Staircase 3 (KMEP BW-886) | Level 5 | Independent | 1 | 3 | 0.6 | 1.5 | 1 | m2-LxH | 4.5 | 2022-12-08 | 2022-12-10 | 100% | 100% | 100% | 0.42857 | 12.01 | 0.49 | 37.83 | 0.95 | 16.21 | 54.99 | 54.99 | 0 |  | 2022-12-08 | TRUE | 4.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 114 | 79112 | 80563 | Staircase 3 (KMEP BW-886) | Level 5 | Tower | 1 | 2.5 | 1 | 1.5 | 1 | rm | 1.5 | 2022-12-08 | 2022-12-10 | 100% | 100% | 100% | 0.42857 | 63.34 | 7.28 | 66.51 | 4.68 | 28.5 | 99.69 | 99.69 | 0 |  | 2022-12-08 | TRUE | 1.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 115 | 79113 | 80852 | Electrical Room - (KMEP BW-882) | Level 4 | Tower | 1 | 1.3 | 1.3 | 2 | 1 | rm | 2 | 2022-12-08 | 2023-01-03 | 100% | 100% | 100% | 3.8571 | 63.34 | 7.28 | 88.68 | 56.16 | 38 | 182.84 | 182.84 | 0 |  | 2022-12-08 | TRUE | 2 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 116 | 79114 | 80570 | Near Gate 1 For Wall Plaster | Ground Level | Independent | 1 | 10 | 1.3 | 1.5 | 1 | m2-LxH | 15 | 2022-12-08 | 2022-12-14 | 100% | 100% | 100% | 1 | 12.01 | 0.49 | 126.11 | 7.35 | 54.05 | 187.51 | 187.51 | 0 |  | 2022-12-08 | TRUE | 15 | TRUE
E11/K149/MS/dm/497 | RESIDENCE | 117 | 79116 | 80580 | House Keeping Lobby Shaft Lobby | Level 31 | Design 1399-31 | 1 | 3 | 1 | 2.3 | 1 | unit | 1 | 2022-12-08 | 2022-12-19 | 100% | 100% | 100% | 1.7143 | 3467.267 | 51.6733 | 2427.09 | 88.58 | 1040.18 | 3555.85 | 3555.85 | 0 | Tas Quote - 2439-23-1 (Item 3) | 2022-12-08 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 118 | 79115 |  | Canal Side For Beam Drilling Work | Level 31 | Tower | 2 | 1 | 0.75 | 1 | 1 | rm | 2 | 2022-12-08 |  | 100% | 100% | 0% | 11.4286 | 63.34 | 7.28 | 88.68 | 166.4 | 0 | 255.08 | 190.6 | 64.48 |  | 2022-12-08 | TRUE | 2 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 1w | 79117 |  | Canal Side For Glass Fixing Work | Level 31 | Cantilever (0 < 0.5m width) | 2 | 1.8 | 0.5 | 1 | 2 | m2-LxW | 1.8 | 2022-12-08 |  | 100% | 100% | 0% | 11.4286 | 32.75 | 1.05 | 41.27 | 21.6 | 0 | 62.87 | 54.5 | 8.37 |  | 2022-12-08 | TRUE | 1.8 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 119 | 79119 | 80579 | Curtain Wall Glass Frame Work | Ground Level | Tower | 1 | 2.5 | 1.3 | 4 | 1 | rm | 4 | 2022-12-09 | 2022-12-19 | 100% | 100% | 100% | 1.5714 | 63.34 | 7.28 | 177.35 | 45.76 | 76.01 | 299.12 | 299.12 | 0 |  | 2022-12-09 | TRUE | 4 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 119a | 79119 | 80579 | Curtain Wall Glass Frame Work | Ground Level | Cantilever (0 < 0.5m width) | 1 | 2.5 | 0.25 | 1 | 1 | m2-LxW | 0.63 | 2022-12-09 | 2022-12-19 | 100% | 100% | 100% | 1.5714 | 32.75 | 1.05 | 14.44 | 1.04 | 6.19 | 21.67 | 21.67 | 0 |  | 2022-12-09 | TRUE | 0.63 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 120 | 79120 | 80571 | Near Gate 1 For Wall Concret Work | Ground Level | Independent | 1 | 5 | 1.3 | 1.5 | 1 | m2-LxH | 7.5 | 2022-12-09 | 2022-12-14 | 100% | 100% | 100% | 0.85714 | 12.01 | 0.49 | 63.05 | 3.15 | 27.02 | 93.22 | 93.22 | 0 |  | 2022-12-09 | TRUE | 7.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 121 | 79121 | 80566 | Staircase 3 (KMEP BW-885) | Level 4 | Tower | 1 | 2.5 | 1 | 2.5 | 1 | rm | 2.5 | 2022-12-10 | 2022-12-12 | 100% | 100% | 100% | 0.42857 | 63.34 | 7.28 | 110.85 | 7.8 | 47.51 | 166.16 | 166.16 | 0 |  | 2022-12-10 | TRUE | 2.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 121a | 79122 | 80567 | Staircase 3 (KMEP BW-885) | Level 4 | Tower | 1 | 2.5 | 0.6 | 1.5 | 1 | rm | 1.5 | 2022-12-10 | 2022-12-12 | 100% | 100% | 100% | 0.42857 | 63.34 | 7.28 | 66.51 | 4.68 | 28.5 | 99.69 | 99.69 | 0 |  | 2022-12-10 | TRUE | 1.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 122 | 79123 | 80568 | Staircase 3 (KMEP BW-885) | Level 4 | Tower | 1 | 2.5 | 1 | 2 | 1 | rm | 2 | 2022-12-10 | 2022-12-12 | 100% | 100% | 100% | 0.42857 | 63.34 | 7.28 | 88.68 | 6.24 | 38 | 132.92 | 132.92 | 0 |  | 2022-12-10 | TRUE | 2 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 123 | 79124 | 80593 | Electrical Work (BW -868) | Ground Level | Independent 1.8m wide | 1 | 5 | 1.8 | 3 | 1 | m2-LxH | 15 | 2022-12-10 | 2022-12-28 | 100% | 100% | 100% | 2.7143 | 16.76 | 0.77 | 175.98 | 31.35 | 75.42 | 282.75 | 282.75 | 0 |  | 2022-12-10 | TRUE | 15 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 123a | 79124 | 80594 | Electrical Work (BW -868) | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 2 | 1.5 | 1 | 1 | m2-LxW | 3 | 2022-12-10 | 2022-12-27 | 100% | 100% | 100% | 2.5714 | 36.52 | 2.94 | 76.69 | 22.68 | 32.87 | 132.24 | 132.24 | 0 |  | 2022-12-10 | TRUE | 3 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 124 | 79125 | 80888 | KMEP - BW 858 | Ground Level | Tower | 1 | 1.8 | 1.3 | 3 | 1 | rm | 3 | 2022-12-12 | 2023-01-16 | 100% | 100% | 100% | 5.1429 | 63.34 | 7.28 | 133.01 | 112.32 | 57.01 | 302.34 | 302.34 | 0 |  | 2022-12-12 | TRUE | 3 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 125 | 79126 | 80590 | LPG Tank For Wall Plaster Work | Ground Level | Independent | 1 | 4.3 | 1.3 | 1.5 | 1 | m2-LxH | 6.45 | 2022-12-12 | 2022-12-26 | 100% | 100% | 100% | 2.1429 | 12.01 | 0.49 | 54.23 | 6.77 | 23.24 | 84.24 | 84.24 | 0 |  | 2022-12-12 | TRUE | 6.45 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 126 | 79127 |  | Shaft For (KMEP - BW 892) | Level 5 | Tower | 1 | 1 | 0.6 | 4 | 2 | rm | 4 | 2022-12-12 |  | 100% | 100% | 0% | 10.8571 | 63.34 | 7.28 | 177.35 | 316.16 | 0 | 493.51 | 364.55 | 128.96 |  | 2022-12-12 | TRUE | 4 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 127 | 79128 |  | Shaft For (KMEP - BW 892) | Level 4 | Tower | 1 | 1 | 0.6 | 2.5 | 1 | rm | 2.5 | 2022-12-12 |  | 100% | 100% | 0% | 10.8571 | 63.34 | 7.28 | 110.85 | 197.6 | 0 | 308.45 | 227.85 | 80.6 |  | 2022-12-12 | TRUE | 2.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 128 | 79129 | 80585 | Mechanical Work (KMEP - BW 887) | Basement 1 | Independent 1.8m wide | 1 | 11.8 | 2.5 | 3 | 1 | m2-LxH | 35.4 | 2022-12-12 | 2022-12-22 | 100% | 100% | 100% | 1.5714 | 16.76 | 0.77 | 415.31 | 42.83 | 177.99 | 636.13 | 636.13 | 0 |  | 2022-12-12 | TRUE | 35.4 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 128a | 79130 | 80586 | Mechanical Work (KMEP - BW 887) | Basement 1 | Independent 1.8m wide | 1 | 4.3 | 2.5 | 2 | 1 | m2-LxH | 8.6 | 2022-12-12 | 2022-12-22 | 100% | 100% | 100% | 1.5714 | 16.76 | 0.77 | 100.9 | 10.41 | 43.24 | 154.55 | 154.55 | 0 |  | 2022-12-12 | TRUE | 8.6 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 129 | 79131 | 80877 | Ramp Area For Access | Ground Level | Tower | 1 | 2.5 | 0.9 | 1.2 | 1 | rm | 1.2 | 2022-12-12 | 2023-01-06 | 100% | 100% | 100% | 3.7143 | 63.34 | 7.28 | 53.21 | 32.45 | 22.8 | 108.46 | 108.46 | 0 |  | 2022-12-12 | TRUE | 1.2 | TRUE
E11/K149/SK/SR/517 | RESIDENCE | 130&130a | 79132 | 80576 | Balcony Ceiling Work | Level 21 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-13 | 2022-12-17 | 100% | 100% | 100% | 0.71429 | 1772.5845 | 52.192 | 1240.81 | 37.28 | 531.78 | 1809.87 | 1809.87 | 0 | Tas Quote 2439-25-1 (item#5) | 2022-12-13 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 123b | 79133 | 80595 | Corridor For Electrical Work (BW - 868) | Ground Level | Independent 1.8m wide | 1 | 11.8 | 1.8 | 3 | 1 | m2-LxH | 35.4 | 2022-12-13 | 2022-12-28 | 100% | 100% | 100% | 2.2857 | 16.76 | 0.77 | 415.31 | 62.3 | 177.99 | 655.6 | 655.6 | 0 |  | 2022-12-13 | TRUE | 35.4 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 123c | 79134 | 80596 | Corridor For Electrical Work (BW - 868) | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 6 | 1 | 1 | 1 | m2-LxW | 6 | 2022-12-13 | 2022-12-27 | 100% | 100% | 100% | 2.1429 | 36.52 | 2.94 | 153.38 | 37.8 | 65.74 | 256.92 | 256.92 | 0 |  | 2022-12-13 | TRUE | 6 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 131 | 79135 | 80597 | Over Head Protection | Ground Level | Independent 1.8m wide | 1 | 17.5 | 2.5 | 2 | 1 | m2-LxH | 35 | 2022-12-13 | 2022-12-28 | 100% | 100% | 100% | 2.2857 | 16.76 | 0.77 | 410.62 | 61.6 | 175.98 | 648.2 | 648.2 | 0 |  | 2022-12-13 | TRUE | 35 | TRUE
E11/K149/MS/dm/497 | RESIDENCE | 132 | 79136 | 80897 | Water Pool Glass Lifting Work | Level 10 | Design 1399-30 | 1 | 10.8 | 1.3 | 4.2 | 1 | unit | 1 | 2022-12-13 | 2023-01-13 | 100% | 100% | 100% | 4.5714 | 6054.579 | 536.9518 | 4238.21 | 2454.64 | 1816.37 | 8509.22 | 8509.22 | 0 | Tas Quote 2439-23-1 (Item #02) | 2022-12-13 | TRUE | 1 | TRUE
E11/K149/MS/dm/497 | RESIDENCE | 132a | 79137 | 80577 | Water Pool Glass Lifting Work | Level 10 | Design 1399-30 | 1 | 5.4 | 1.3 | 4.2 | 1 | unit | 1 | 2022-12-13 | 2022-12-16 | 100% | 100% | 100% | 0.57143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Tas Quote 2439-23-1 (Item #02) | 2022-12-13 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 133 | 79138 | 80853 | Electrical Work (KMEP - BW 893) | Basement 1 | Independent | 1 | 7.3 | 1.3 | 5 | 1 | m2-LxH | 36.5 | 2022-12-14 | 2023-01-03 | 100% | 100% | 100% | 3 | 12.01 | 0.49 | 306.86 | 53.66 | 131.51 | 492.03 | 492.03 | 0 |  | 2022-12-14 | TRUE | 36.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 133 | 79138 | 80853 | Electrical Work (KMEP - BW 893) | Basement 1 | Additional Boarding | 1 | 7.3 | 1.3 | 1 | 1 | m2-LxW | 9.49 | 2022-12-14 | 2023-01-03 | 100% | 100% | 100% | 3 | 6.63 | 0.7 | 44.04 | 19.93 | 18.88 | 82.85 | 82.85 | 0 |  | 2022-12-14 | TRUE | 9.49 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 133a | 79138 | 80853 | Electrical Work (KMEP - BW 893) | Basement 1 | Cantilever (0 < 0.5m width) | 1 | 7.3 | 0.5 | 1 | 1 | m2-LxW | 3.65 | 2022-12-14 | 2023-01-03 | 100% | 100% | 100% | 3 | 32.75 | 1.05 | 83.68 | 11.5 | 35.86 | 131.04 | 131.04 | 0 |  | 2022-12-14 | TRUE | 3.65 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 128b | 79139 | 80587 | Mechanical Work (KMEP - BW 887) | Basement 1 | Tower | 1 | 2.5 | 2.5 | 3 | 1 | rm | 3 | 2022-12-14 | 2022-12-22 | 100% | 100% | 100% | 1.2857 | 63.34 | 7.28 | 133.01 | 28.08 | 57.01 | 218.1 | 218.1 | 0 |  | 2022-12-14 | TRUE | 3 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 134 | 79140 | 78621 | EIFS Fixing Work | Ground Level | Independent | 1 | 3.8 | 1.3 | 4 | 1 | m2-LxH | 15.2 | 2022-12-14 | 2023-02-02 | 100% | 100% | 100% | 7.2857 | 12.01 | 0.49 | 127.79 | 54.26 | 54.77 | 236.82 | 173.54 | 63.28 |  | 2022-12-14 | TRUE | 15.2 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 134 | 79140 | 78621 | EIFS Fixing Work | Ground Level | Additional Boarding | 1 | 3.8 | 1.3 | 1 | 1 | m2-LxW | 4.94 | 2022-12-14 | 2023-02-02 | 100% | 100% | 100% | 7.2857 | 6.63 | 0.7 | 22.93 | 25.19 | 9.83 | 57.95 | 44.17 | 13.78 |  | 2022-12-14 | TRUE | 4.94 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 135 | 79141 | 78622 | EIFS Fixing Work | Ground Level | Independent | 1 | 11.8 | 1.3 | 4 | 1 | m2-LxH | 47.2 | 2022-12-14 | 2023-02-02 | 100% | 100% | 0% | 7.2857 | 12.01 | 0.49 | 396.81 | 168.5 | 0 | 565.31 | 538.88 | 26.43 |  | 2022-12-14 | TRUE | 47.2 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 135 | 79141 | 78622 | EIFS Fixing Work | Ground Level | Additional Boarding | 1 | 11.8 | 1.3 | 1 | 1 | m2-LxW | 15.34 | 2022-12-14 | 2023-02-02 | 100% | 100% | 0% | 7.2857 | 6.63 | 0.7 | 71.19 | 78.23 | 0 | 149.42 | 137.15 | 12.27 |  | 2022-12-14 | TRUE | 15.34 | TRUE
E11/K149/SK/SR/517 | RESIDENCE | 139&139a | 79144 | 80589 | Balcony Ceiling Work | Level 19 | Design 1399 - 35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-15 | 2022-12-22 | 100% | 100% | 100% | 1.1429 | 1772.5845 | 52.192 | 1240.81 | 59.65 | 531.78 | 1832.24 | 1832.24 | 0 | Tas Quote 2439-25-1 (item#5) | 2022-12-15 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 44a | 79147 | 78623 | EIFS Wall Finishing Work | Ground Level | Additional Boarding | 1 | 4 | 1 | 1 | 1 | m2-LxW | 4 | 2022-12-15 | 2023-02-01 | 100% | 100% | 100% | 7 | 6.63 | 0.7 | 18.56 | 19.6 | 7.96 | 46.12 | 35.36 | 10.76 |  | 2022-12-15 | TRUE | 4 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 45a | 79148 | 78624 | EIFS Wall Finishing Work | Ground Level | Additional Boarding | 1 | 4 | 1 | 1 | 1 | m2-LxW | 4 | 2022-12-15 | 2023-02-02 | 100% | 100% | 100% | 7.1429 | 6.63 | 0.7 | 18.56 | 20 | 7.96 | 46.52 | 35.36 | 11.16 |  | 2022-12-15 | TRUE | 4 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 137 | 79149 | 80854 | Planter Access | Ground Level | Independent | 1 | 3.5 | 1.3 | 1 | 1 | m2-LxH | 3.5 | 2022-12-15 | 2023-01-03 | 100% | 100% | 100% | 2.8571 | 12.01 | 0.49 | 29.42 | 4.9 | 12.61 | 46.93 | 46.93 | 0 |  | 2022-12-15 | TRUE | 3.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 138 | 79150 |  | Staircase Edge Protection | Ground Level | Double Handrail | 1 | 37.5 |  | 1 |  | lm | 37.5 | 2022-12-15 |  | 100% | 100% | 0% | 10.4286 | 15 | 0.91 | 393.75 | 355.88 | 0 | 749.63 | 598.5 | 151.13 |  | 2022-12-15 | TRUE | 37.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 136 | 79152 |  | Over Head Protection | Level 2 | Independent 1.8m wide | 1 | 10.8 | 2.5 | 2.5 | 1 | m2-LxH | 27 | 2022-12-14 |  | 100% | 100% | 0% | 10.5714 | 16.76 | 0.77 | 316.76 | 219.78 | 0 | 536.54 | 444.47 | 92.07 |  | 2022-12-14 | TRUE | 27 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 136a | 79152 |  | Over Head Protection | Level 2 | Buttress | 1 | 4.3 | 1.8 | 7 |  | m3 | 54.18 | 2022-12-14 |  | 100% | 100% | 0% | 10.5714 | 5.29 | 0.35 | 200.63 | 200.47 | 0 | 401.1 | 317.12 | 83.98 |  | 2022-12-14 | TRUE | 54.18 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 136e | 79162 |  | Over Head Protection | ground Level | Independent 1.8m wide | 1 | 3.8 | 2.5 | 4 | 1 | m2-LxH | 15.2 | 2022-12-14 |  | 100% | 100% | 0% | 10.5714 | 16.76 | 0.77 | 178.33 | 123.73 | 0 | 302.06 | 250.23 | 51.83 |  | 2022-12-14 | TRUE | 15.2 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 136f | 79162 |  | Over Head Protection | ground Level | Independent 1.8m wide | 1 | 3.6 | 2.5 | 5 | 1 | m2-LxH | 18 | 2022-12-14 |  | 100% | 100% | 0% | 10.5714 | 16.76 | 0.77 | 211.18 | 146.52 | 0 | 357.7 | 296.32 | 61.38 |  | 2022-12-14 | TRUE | 18 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 128c | 79154 | 80588 | Mechanical Work (KMEP - BW 887) | Basement 1 | Independent | 1 | 4.3 | 1 | 1.5 | 1 | m2-LxH | 6.45 | 2022-12-15 | 2022-12-22 | 100% | 100% | 100% | 1.1429 | 12.01 | 0.49 | 54.23 | 3.61 | 23.24 | 81.08 | 81.08 | 0 |  | 2022-12-15 | TRUE | 6.45 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 140 | 79155 | 80581 | KMEP - BW 797 | Level 5 | Tower | 1 | 1.8 | 1.3 | 1.5 | 1 | rm | 1.5 | 2022-12-16 | 2022-12-19 | 100% | 100% | 100% | 0.57143 | 63.34 | 7.28 | 66.51 | 6.24 | 28.5 | 101.25 | 101.25 | 0 |  | 2022-12-16 | TRUE | 1.5 | TRUE
E11/K149/SK/SR/517 | RESIDENCE | 141&141a | 79156 | 80583 | Balcony Ceiling Work | Level 18 | Design 1399 - 35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-16 | 2022-12-21 | 100% | 100% | 100% | 0.85714 | 1772.5845 | 52.192 | 1240.81 | 44.74 | 531.78 | 1817.33 | 1817.33 | 0 | Tas Quote 2439-25-1 (item#5) | 2022-12-16 | TRUE | 1 | TRUE
E11/K149/SK/SR/517 | RESIDENCE | 142&142a | 79157 | 80584 | Balcony Ceiling Work | Level 18 | Design 1399 - 35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-16 | 2022-12-21 | 100% | 100% | 100% | 0.85714 | 1772.5845 | 52.192 | 1240.81 | 44.74 | 531.78 | 1817.33 | 1817.33 | 0 | Tas Quote 2439-25-1 (item#5) | 2022-12-16 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 143 | 79159 |  | Beam Drilling Work | Level 31 | Tower | 3 | 1 | 0.75 | 0.6 | 1 | rm | 1.8 | 2022-12-17 |  | 100% | 100% | 0% | 10.1429 | 63.34 | 7.28 | 79.81 | 132.91 | 0 | 212.72 | 154.69 | 58.03 |  | 2022-12-17 | TRUE | 1.8 | TRUE
E11/K149/SK/dm/480 | RESIDENCE | 144 | 79160 | 808666 | Shaft 9 Slab Concrete | Level 31 | Design 1399 - 25a | 1 |  |  |  |  | unit | 1 | 2022-12-17 | 2023-01-04 | 100% | 100% | 100% | 2.7143 | 3381.02 | 181.02 | 2366.71 | 491.34 | 1014.31 | 3872.36 | 3872.36 | 0 | Tas Quote 2439-22-1 (Item # 1) | 2022-12-17 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 136b | 79161 |  | Over Head Protection | Ground Level | Buttress | 1 | 3.6 | 1.3 | 4 |  | m3 | 18.72 | 2022-12-14 |  | 100% | 100% | 0% | 10.5714 | 5.29 | 0.35 | 69.32 | 69.26 | 0 | 138.58 | 109.57 | 29.01 |  | 2022-12-14 | TRUE | 18.72 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 136c | 79161 |  | Over Head Protection | Ground Level | Buttress | 1 | 3.6 | 1.3 | 2.5 |  | m3 | 11.7 | 2022-12-14 |  | 100% | 100% | 0% | 10.5714 | 5.29 | 0.35 | 43.33 | 43.29 | 0 | 86.62 | 68.49 | 18.13 |  | 2022-12-14 | TRUE | 11.7 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 136d | 79161 |  | Over Head Protection | Ground Level | Buttress | 1 | 3.8 | 0.9 | 3 |  | m3 | 10.26 | 2022-12-14 |  | 100% | 100% | 0% | 10.5714 | 5.29 | 0.35 | 37.99 | 37.96 | 0 | 75.95 | 60.05 | 15.9 |  | 2022-12-14 | TRUE | 10.26 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 123d | 79163 | 80598 | Electrical Work (BW -868) | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 6 | 1 | 1 | 1 | m2-LxW | 6 | 2022-12-19 | 2022-12-28 | 100% | 100% | 100% | 1.4286 | 36.52 | 2.94 | 153.38 | 25.2 | 65.74 | 244.32 | 244.32 | 0 |  | 2022-12-19 | TRUE | 6 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 145 | 79164 |  | GRC Panel Work | Level 31 | Independent 1.8m wide | 1 | 17.8 | 1.8 | 5 | 1 | m2-LxH | 89 | 2022-12-19 |  | 100% | 100% | 0% | 9.8571 | 12.01 | 0.49 | 748.22 | 429.87 | 0 | 1178.09 | 984.96 | 193.13 |  | 2022-12-19 | TRUE | 89 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 146 | 79165 | 80882 | Beam Drilling Work | Level 31 | Tower | 1 | 1 | 1 | 1 | 1 | rm | 1 | 2022-12-19 | 2023-01-11 | 100% | 100% | 100% | 3.4286 | 63.34 | 7.28 | 44.34 | 24.96 | 19 | 88.3 | 88.3 | 0 |  | 2022-12-19 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 147 | 79166 | 78602 | Beam Drilling Work | Level 31 | Tower | 1 | 1 | 1 | 1 | 1 | rm | 1 | 2022-12-19 | 2023-01-24 | 100% | 100% | 100% | 5.2857 | 63.34 | 7.28 | 44.34 | 38.48 | 19 | 101.82 | 101.82 | 0 |  | 2022-12-19 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 148 | 79167 | 78625 | EIFS Wall Finishing Work | Ground Level | Independent | 1 | 6.3 | 1.3 | 4 | 1 | m2-LxH | 25.2 | 2022-12-20 | 2023-02-02 | 100% | 100% | 100% | 6.4286 | 12.01 | 0.49 | 211.86 | 79.38 | 90.8 | 382.04 | 277.13 | 104.91 |  | 2022-12-20 | TRUE | 25.2 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 68b | 79168 |  | Electrical Work (KMEP - BW 754) | Level 2 | Additional Boarding | 1 | 2.5 | 1.3 | 1 | 1 | m2-LxW | 3.25 | 2022-12-20 |  | 100% | 100% | 0% | 9.7143 | 6.63 | 0.7 | 15.08 | 22.1 | 0 | 37.18 | 27.11 | 10.07 |  | 2022-12-20 | TRUE | 3.25 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 149 | 79169 | 78644 | Near KCE Office For Access | Ground Level | Tower | 1 | 1.8 | 1.3 | 1.25 | 1 | rm | 1.25 | 2022-12-21 | 2023-02-10 | 100% | 100% | 100% | 7.4286 | 63.34 | 7.28 | 55.42 | 67.6 | 23.75 | 146.77 | 102.22 | 44.55 |  | 2022-12-21 | TRUE | 1.25 | TRUE
E11/K149/SK/SR/503 | RESIDENCE | 150 Ext - a,b | 79170 | 78648 | Block and EIFS Work | Level 10 to 17 | Design 1399 - 29 | 1 |  |  |  |  | unit | 1 | 2022-12-21 | 2023-02-14 | 100% | 100% | 100% | 8 | 34922.6 | 1384.55 | 24445.82 | 11076.4 | 10476.78 | 45999 | 31566.36 | 14432.64 | Tas Quote 2439-24-1 (Item #4) | 2022-12-21 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 8x | 79171 |  | Balcony Access | Level 27/28 | Additional Boarding | 1 | 1.8 | 1.8 | 1 | 1 | m2-LxW | 3.24 | 2022-12-21 |  | 100% | 100% | 0% | 9.5714 | 6.63 | 0.7 | 15.04 | 21.71 | 0 | 36.75 | 26.7 | 10.05 |  | 2022-12-21 | TRUE | 3.24 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 8y | 79172 |  | Balcony Access | Level 27/28 | Cantilever (0.5 > 1.2m width) | 1 | 1.8 | 1 | 1 | 1 | m2-LxW | 1.8 | 2022-12-21 |  | 100% | 100% | 0% | 9.5714 | 36.52 | 2.94 | 46.02 | 50.65 | 0 | 96.67 | 73.24 | 23.43 |  | 2022-12-21 | TRUE | 1.8 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 151 | 79173 |  | Balcony Ceiling Work | Level 26 | Tower | 1 | 2.5 | 1.3 | 2 | 1 | rm | 2 | 2022-12-22 |  | 100% | 100% | 0% | 9.4286 | 63.34 | 7.28 | 88.68 | 137.28 | 0 | 225.96 | 161.48 | 64.48 |  | 2022-12-22 | TRUE | 2 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 152 | 79174 |  | Balcony Ceiling Work | Level 27 | Tower | 1 | 2.5 | 1.3 | 2 | 1 | rm | 2 | 2022-12-22 |  | 100% | 100% | 0% | 9.4286 | 63.34 | 7.28 | 88.68 | 137.28 | 0 | 225.96 | 161.48 | 64.48 |  | 2022-12-22 | TRUE | 2 | TRUE
E11/K149/SK/dm/213 | HOTEL | 48b | 79060 | 80836 | Balcony Floor Drain Work | Level 12 | Tower | 1 | 2.5 | 1.3 | 1.5 | 1 | rm | 1.5 | 2022-11-26 | 2022-12-21 | 100% | 100% | 100% | 3.7143 | 63.34 | 7.28 | 66.51 | 40.56 | 28.5 | 135.57 | 135.57 | 0 |  | 2022-11-26 | TRUE | 1.5 | TRUE
E11/K149/JA/dm/429 | HOTEL | 60 | 79061 |  | Balcony Access | Level 22 | Tower | 1 | 2.5 | 1.3 | 3.7 | 1 | unit | 1 | 2022-11-26 |  | 100% | 100% | 0% | 13.1429 | 1182.48 | 26.94 | 827.74 | 354.07 | 0 | 1181.81 | 1062.5 | 119.31 | Tas Quote 2439-20-1 (Item #08) | 2022-11-26 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | HOTEL | 60a | 79061 |  | Balcony Access | Level 22 | Cantilever (0.5 > 1.2m width) | 1 | 2 | 1.3 | 1 | 1 | m2-LxW | 2.6 | 2022-11-26 |  | 100% | 100% | 0% | 13.1429 | 36.52 | 2.94 | 66.47 | 100.46 | 0 | 166.93 | 133.08 | 33.85 |  | 2022-11-26 | TRUE | 2.6 | TRUE
E11/K149/SK/dm/213 | HOTEL | 61 | 79062 | 76840 | Electrical Service Work | Basement 1 | Independent 1.8m wide | 1 | 29.3 | 2.5 | 2 | 1 | m2-LxH | 58.6 | 2022-11-28 | 2022-12-05 | 100% | 100% | 100% | 1.1429 | 16.76 | 0.77 | 687.5 | 51.57 | 294.64 | 1033.71 | 1033.71 | 0 |  | 2022-11-28 | TRUE | 58.6 | TRUE
E11/K149/JA/dm/429 | HOTEL | 62 | 79063 |  | Balcony For Access | Level 17 | Tower | 1 | 2.5 | 1.8 | 4 | 1 | unit | 1 | 2022-11-28 |  | 100% | 100% | 0% | 12.8571 | 1278.36 | 29.12 | 894.85 | 374.4 | 0 | 1269.25 | 1140.29 | 128.96 | Tas Quote 2439-20-1 (Item #05) | 2022-11-28 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | HOTEL | 62a | 79063 |  | Balcony For Access | Level 17 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-11-28 |  | 100% | 100% | 0% | 12.8571 | 36.52 | 2.94 | 38.35 | 56.7 | 0 | 95.05 | 75.52 | 19.53 |  | 2022-11-28 | TRUE | 1.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 63 | 79064 | 76841 | FAHU Oil Leakge (BW -783) | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3.5 | 1 | rm | 3.5 | 2022-11-29 | 2022-12-05 | 100% | 100% | 100% | 1 | 63.34 | 7.28 | 155.18 | 25.48 | 66.51 | 247.17 | 247.17 | 0 |  | 2022-11-29 | TRUE | 3.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 61a | 79065 | 76838 | Electrical Service Work | Basement 1 | Independent 1.8m wide | 1 | 15 | 2.5 | 2.3 | 1 | m2-LxH | 34.5 | 2022-11-29 | 2022-11-30 | 100% | 100% | 100% | 0.28571 | 16.76 | 0.77 | 404.75 | 7.59 | 173.47 | 585.81 | 585.81 | 0 |  | 2022-11-29 | TRUE | 34.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 62b | 79066 |  | Edge Protection | Level 18 | Double Handrail | 1 | 8 | 1 | 1 |  | lm | 8 | 2022-11-30 |  | 100% | 100% | 0% | 12.5714 | 15 | 0.91 | 84 | 91.52 | 0 | 175.52 | 143.28 | 32.24 |  | 2022-11-30 | TRUE | 8 | TRUE
E11/K149/SK/dm/213 | HOTEL | 57b | 79067 | 80846 | Balcony Drain Pipe Work | Level 19 | Tower | 1 | 2.5 | 1 | 1.5 | 1 | rm | 1.5 | 2022-11-30 | 2022-12-29 | 100% | 100% | 100% | 4.2857 | 63.34 | 7.28 | 66.51 | 46.8 | 28.5 | 141.81 | 141.81 | 0 |  | 2022-11-30 | TRUE | 1.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 43d | 79068 | 80932 | EIFS Work | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 14.5 | 0.75 | 1 | 1 | m2-LxW | 10.88 | 2022-12-05 | 2023-01-30 | 100% | 100% | 100% | 8.1429 | 36.52 | 2.94 | 278.14 | 260.47 | 119.2 | 657.81 | 515.76 | 142.05 |  | 2022-12-05 | TRUE | 10.88 | TRUE
E11/K149/SK/dm/213 | HOTEL | 64 | 79069 |  | Plant Room For Wall Finishing Work | Ground Level | Independent | 1 | 6.8 | 0.9 | 3 | 1 | m2-LxH | 20.4 | 2022-12-07 |  | 100% | 100% | 0% | 11.5714 | 12.01 | 0.49 | 171.5 | 115.67 | 0 | 287.17 | 242.9 | 44.27 |  | 2022-12-07 | TRUE | 20.4 | TRUE
E11/K149/SK/dm/213 | HOTEL | 64a | 79069 |  | Plant Room For Wall Finishing Work | Ground Level | Additional Boarding | 1 | 2.5 | 0.9 | 1 | 1 | m2-LxW | 2.25 | 2022-12-07 |  | 100% | 100% | 0% | 11.5714 | 6.63 | 0.7 | 10.44 | 18.23 | 0 | 28.67 | 21.69 | 6.98 |  | 2022-12-07 | TRUE | 2.25 | TRUE
E11/K149/SK/dm/213 | HOTEL | 65 | 79070 | 80848 | EIFS Finishing Work (Hotel Behind Kitchen) | Level 2 | Independent | 1 | 4 | 1 | 5.5 | 1 | m2-LxH | 22 | 2022-12-09 | 2022-12-30 | 100% | 100% | 100% | 3.1429 | 12.01 | 0.49 | 184.95 | 33.88 | 79.27 | 298.1 | 298.1 | 0 |  | 2022-12-09 | TRUE | 22 | TRUE
E11/K149/SK/dm/213 | HOTEL | 65 | 79070 | 80848 | EIFS Finishing Work (Hotel Behind Kitchen) | Level 2 | Additional Boarding | 2 | 4 | 1 | 1 | 2 | m2-LxW | 8 | 2022-12-09 | 2022-12-30 | 100% | 100% | 100% | 3.1429 | 6.63 | 0.7 | 37.13 | 17.6 | 15.91 | 70.64 | 70.64 | 0 |  | 2022-12-09 | TRUE | 8 | TRUE
E11/K149/SK/dm/213 | HOTEL | 66 | 79071 | 80909 | EIFS Damac Side Elevation | Level 2 | Independent | 1 | 13.6 | 0.9 | 1.5 | 1 | m2-LxH | 20.4 | 2022-12-09 | 2023-01-12 | 100% | 100% | 100% | 5 | 12.01 | 0.49 | 171.5 | 49.98 | 73.5 | 294.98 | 294.98 | 0 |  | 2022-12-09 | TRUE | 20.4 | TRUE
E11/K149/SK/dm/213 | HOTEL | 66a | 79072 | 80909 | EIFS Damac Side Elevation | Level 2 | Cantilever (0 < 0.5m width) | 1 | 14.5 | 0.5 | 1 | 1 | m2-LxW | 7.25 | 2022-12-09 | 2023-01-12 | 100% | 100% | 100% | 5 | 32.75 | 1.05 | 166.21 | 38.06 | 71.23 | 275.5 | 275.5 | 0 |  | 2022-12-09 | TRUE | 7.25 | TRUE
E11/K149/SK/dm/213 | HOTEL | 66b | 79073 | 80910 | EIFS Damac Side Elevation | Level 2 | Cantilever (0.5 > 1.2m width) | 1 | 1.8 | 1.4 | 1 | 1 | m2-LxW | 2.52 | 2022-12-09 | 2023-01-12 | 100% | 100% | 100% | 5 | 32.75 | 1.05 | 57.77 | 13.23 | 24.76 | 95.76 | 95.76 | 0 |  | 2022-12-09 | TRUE | 2.52 | TRUE
E11/K149/JA/dm/429 | HOTEL | 67 | 79074 |  | Balcony Access | Level 26 | Tower | 1 | 2.5 | 1.3 | 3.5 | 1 | unit | 1 | 2022-12-09 |  | 100% | 100% | 0% | 11.2857 | 1118.565 | 25.48 | 783 | 287.56 | 0 | 1070.56 | 957.72 | 112.84 | Tas Quote 2439-20-1 (Item #10) | 2022-12-09 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | HOTEL | 67a | 79074 |  | Balcony Access | Level 27 | Cantilever (0.5 > 1.2m width) | 1 | 2 | 1.5 | 1 | 1 | m2-LxW | 3 | 2022-12-09 |  | 100% | 100% | 0% | 11.2857 | 32.75 | 1.05 | 68.78 | 35.55 | 0 | 104.33 | 90.38 | 13.95 |  | 2022-12-09 | TRUE | 3 | TRUE
E11/K149/SK/dm/213 | HOTEL | 68 | 79075 | 80842 | Canal Side Balcony For Grc Work | Level 24 | Independent | 1 | 8.1 | 1.5 | 2.5 | 1 | m2-LxH | 20.25 | 2022-12-09 | 2022-12-22 | 100% | 100% | 100% | 2 | 12.01 | 0.49 | 170.24 | 19.85 | 72.96 | 263.05 | 263.05 | 0 |  | 2022-12-09 | TRUE | 20.25 | TRUE
E11/K149/SK/dm/213 | HOTEL | 43e | 79076 | 80933 | Ramp Area For Wall Plaster Work | Ground Level | Independent | 1 | 13 | 1 | 1.5 | 1 | m2-LxH | 19.5 | 2022-12-10 | 2023-01-30 | 100% | 100% | 100% | 7.4286 | 12.01 | 0.49 | 163.94 | 70.98 | 70.26 | 305.18 | 228.1 | 77.08 |  | 2022-12-10 | TRUE | 19.5 | TRUE
E11/K149/SK/SR/517 | HOTEL | 69 | 79077 | 80849 | Balcony Ceiling Work | Level 7 | Design 1399-35b | 1 | 5.3 | 1 | 1 | 1 | unit | 1 | 2022-12-17 | 2022-12-31 | 100% | 100% | 100% | 2.1429 | 2184.8135 | 64.3297 | 1529.37 | 137.85 | 655.44 | 2322.66 | 2322.66 | 0 | Tas Quote 2439-25-1 (item#5) | 2022-12-17 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | HOTEL | 70 | 79078 |  | Electrical Work For (KMEP - BW917) | Ground Level | Independent | 1 | 6.3 | 1.3 | 4 | 1 | m2-LxH | 25.2 | 2022-12-17 |  | 100% | 100% | 0% | 10.1429 | 12.01 | 0.49 | 211.86 | 125.24 | 0 | 337.1 | 282.42 | 54.68 |  | 2022-12-17 | TRUE | 25.2 | TRUE
E11/K149/SK/dm/213 | HOTEL | 70a | 79079 |  | Electrical Work For (KMEP - BW917) | Ground Level | Tower | 1 | 2.5 | 2.5 | 4 | 1 | rm | 4 | 2022-12-17 |  | 100% | 100% | 0% | 10.1429 | 63.34 | 7.28 | 177.35 | 295.36 | 0 | 472.71 | 343.75 | 128.96 |  | 2022-12-17 | TRUE | 4 | TRUE
E11/K149/SK/SR/517 | HOTEL | 71&71a | 79082 | 80850 | Balcony Ceiling Work | Level 9 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-17 | 2022-12-31 | 100% | 100% | 100% | 2.1429 | 1772.5845 | 52.192 | 1240.81 | 111.84 | 531.78 | 1884.43 | 1884.43 | 0 | Tas Quote 2439-25-1 (item#5) | 2022-12-17 | TRUE | 1 | TRUE
E11/K149/SK/SR/517 | HOTEL | 72&72a | 79083 | 80901 | Balcony Ceiling Work | Level 9 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-17 | 2022-12-31 | 100% | 100% | 100% | 2.1429 | 1772.5845 | 52.192 | 1240.81 | 111.84 | 531.78 | 1884.43 | 1884.43 | 0 | Tas Quote 2439-25-1 (item#5) | 2022-12-17 | TRUE | 1 | TRUE
E11/K149/SK/SR/517 | HOTEL | 73&73a | 79084 |  | Balcony Ceiling Work | Level 11 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-17 |  | 100% | 100% | 0% | 10.1429 | 1772.5845 | 52.192 | 1240.81 | 529.38 | 0 | 1770.19 | 1539.05 | 231.14 | Tas Quote 2439-25-1 (item#5) | 2022-12-17 | TRUE | 1 | TRUE
E11/K149/SK/SR/517 | HOTEL | 74&74a | 79085 |  | Balcony Ceiling Work | Level 11 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-17 |  | 100% | 100% | 0% | 10.1429 | 1772.5845 | 52.192 | 1240.81 | 529.38 | 0 | 1770.19 | 1539.05 | 231.14 | Tas Quote 2439-25-1 (item#5) | 2022-12-17 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | HOTEL | 75 | 79086 | 80843 | Staircase 7 For (KMEP - BW 793) | Ground Level | Tower | 1 | 1.8 | 1 | 1.2 | 1 | rm | 1.2 | 2022-12-20 | 2022-12-26 | 100% | 100% | 100% | 1 | 63.34 | 7.28 | 53.21 | 8.74 | 22.8 | 84.75 | 84.75 | 0 |  | 2022-12-20 | TRUE | 1.2 | TRUE
E11/K149/SK/SR/517 | HOTEL | 76&76a | 79087 | 80904 | Balcony Ceiling Work | Level 10 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-21 | 2023-01-11 | 100% | 100% | 100% | 3.1429 | 1772.5845 | 52.192 | 1240.81 | 164.03 | 531.78 | 1936.62 | 1936.62 | 0 | Tas Quote 2439-25-1 (item#5) | 2022-12-21 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | HOTEL | 70b | 79088 |  | Electrical Work (KMEP - BW 917) | Ground Level | Additional Boarding | 1 | 3.8 | 1.3 | 1 | 1 | m2-LxW | 4.94 | 2022-12-21 |  | 100% | 100% | 0% | 9.5714 | 6.63 | 0.7 | 22.93 | 33.1 | 0 | 56.03 | 40.71 | 15.32 |  | 2022-12-21 | TRUE | 4.94 | TRUE
E11/K149/SK/dm/213 | HOTEL | 70c | 79089 |  | Electrical Work (KMEP - BW 917) | Ground Level | Cantilever (0 < 0.5m width) | 1 | 4 | 0.5 | 1 | 1 | m2-LxW | 2 | 2022-12-21 |  | 100% | 100% | 0% | 9.5714 | 32.75 | 1.05 | 45.85 | 20.1 | 0 | 65.95 | 56.65 | 9.3 |  | 2022-12-21 | TRUE | 2 | TRUE
E11/K149/SK/dm/213 | HOTEL | 77 | 79090 |  | Entrance Area (KMEP - BW 917) | Ground Level | Tower | 1 | 1.3 | 1.3 | 4 | 2 | rm | 4 | 2022-12-22 |  | 100% | 100% | 0% | 9.4286 | 63.34 | 7.28 | 177.35 | 274.56 | 0 | 451.91 | 322.95 | 128.96 |  | 2022-12-22 | TRUE | 4 | TRUE
E11/K149/SK/dm/213 | HOTEL | 51b | 79091 | 78600 | Staircase 7 For (KMEP - BW 793) | Ground Level | Additional Boarding | 1 | 2.5 | 1.3 | 1 | 1 | m2-LxW | 3.25 | 2022-12-22 | 2023-02-22 | 100% | 100% | 100% | 9 | 6.63 | 0.7 | 15.08 | 20.48 | 6.46 | 42.02 | 26.46 | 15.56 |  | 2022-12-22 | TRUE | 3.25 | TRUE
E11/K149/SK/SR/517 | HOTEL | 78&78a | 79092 | 80905 | Balcony Ceiling Work | Level 10 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-22 | 2023-01-11 | 100% | 100% | 100% | 3 | 1772.5845 | 52.192 | 1240.81 | 156.58 | 531.78 | 1929.17 | 1929.17 | 0 | Tas Quote 2439-25-1 (item#5) | 2022-12-22 | TRUE | 1 | TRUE
E11/K149/SK/SR/550 | HOTEL |  |  |  | Hire of Aluminium Tower | NA | NA | 1 |  |  |  |  | unit | 1 | 2022-12-19 |  | 0% | 100% | 0% | 9.8571 | 0 | 200 | 0 | 1971.43 | 0 | 1971.43 | 1085.71 | 885.72 |  | #N/A | #N/A | #N/A | #N/A
E11/K149/SK/SR/560 | HOTEL |  |  |  | Hire of Aluminium Tower | NA | NA | 1 |  |  |  |  | unit | 1 | 2022-12-21 |  | 0% | 100% | 0% | 9.5714 | 0 | 200 | 0 | 1914.29 | 0 | 1914.29 | 1028.57 | 885.72 |  | #N/A | #N/A | #N/A | #N/A
E11/K149/SK/SR/560 | HOTEL |  |  |  | Hire of Aluminium Tower | NA | NA | 1 |  |  |  |  | unit | 1 | 2022-12-22 |  | 0% | 100% | 0% | 9.4286 | 0 | 200 | 0 | 1885.71 | 0 | 1885.71 | 1000 | 885.71 |  | #N/A | #N/A | #N/A | #N/A
E11/K149/SK/dm/213 | RESIDENCE | 153 | 79175 |  | Electrical Work (KMEP - BW 0948) | Ground Level | Tower | 1 | 1.8 | 1.3 | 4 | 1 | rm | 4 | 2022-12-26 |  | 100% | 100% | 0% | 8.8571 | 63.34 | 7.28 | 177.35 | 257.92 | 0 | 435.27 | 306.31 | 128.96 |  | 2022-12-26 | TRUE | 4 | TRUE
E11/K149/SK/SR/517 | RESIDENCE | 154&154a | 79176 | 80599 | Balcony Ceiling Work | Level 12 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-26 | 2022-12-29 | 100% | 100% | 100% | 0.57143 | 1772.5845 | 52.192 | 1240.81 | 29.82 | 531.78 | 1802.41 | 1802.41 | 0 | Tas Quote 2439-25-1 (item#5) | 2022-12-26 | TRUE | 1 | TRUE
E11/K149/SK/SR/517 | RESIDENCE | 155&155a | 79177 | 80600 | Balcony Ceiling Work | Level 12 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-26 | 2022-12-29 | 100% | 100% | 100% | 0.57143 | 1772.5845 | 52.192 | 1240.81 | 29.82 | 531.78 | 1802.41 | 1802.41 | 0 | Tas Quote 2439-25-1 (item#5) | 2022-12-26 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 156&156a | 79178 | 80855 | Mechanical Work | Basement 1 | Independent | 1 | 25.1 | 1.3 | 3 | 1 | m2-LxH | 75.3 | 2022-12-26 | 2023-01-02 | 100% | 100% | 100% | 1.1429 | 12.01 | 0.49 | 633.05 | 42.17 | 271.31 | 946.53 | 946.53 | 0 |  | 2022-12-26 | TRUE | 75.3 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 156&156a | 79178 | 80856 | Mechanical Work | Basement 1 | Additional Boarding | 1 | 6 | 1 | 1 | 1 | m2-LxW | 6 | 2022-12-26 | 2023-01-02 | 100% | 100% | 100% | 1.1429 | 6.63 | 0.7 | 27.85 | 4.8 | 11.93 | 44.58 | 44.58 | 0 |  | 2022-12-26 | TRUE | 6 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 156b | 79179 | 80856 | Mechanical Work | Basement 1 | Cantilever (0 < 0.5m width) | 1 | 8 | 0.5 | 1 | 1 | m2-LxW | 4 | 2022-12-26 | 2023-01-02 | 100% | 100% | 100% | 1.1429 | 32.75 | 1.05 | 91.7 | 4.8 | 39.3 | 135.8 | 135.8 | 0 |  | 2022-12-26 | TRUE | 4 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 93a | 79180 | 80883 | KMEP Work | Ground Level | Additional Boarding | 1 | 2.5 | 1.8 | 1 | 1 | m2-LxW | 4.5 | 2022-12-26 | 2023-01-10 | 100% | 100% | 100% | 2.2857 | 6.63 | 0.7 | 20.88 | 7.2 | 8.95 | 37.03 | 37.03 | 0 |  | 2022-12-26 | TRUE | 4.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 157 | 79181 | 80878 | Electrical Work (KMEP - BW 0948) | Ground Level | Independent 1.8m wide | 1 | 11.8 | 1.8 | 4 | 1 | m2-LxH | 47.2 | 2022-12-27 | 2023-01-09 | 100% | 100% | 100% | 2 | 16.76 | 0.77 | 553.75 | 72.69 | 237.32 | 863.76 | 863.76 | 0 |  | 2022-12-27 | TRUE | 47.2 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 157a | 79181 | 80878 | Electrical Work (KMEP - BW 0948) | Ground Level | Cantilever (0 < 0.5m width) | 1 | 11.8 | 0.5 | 1 | 1 | m2-LxW | 5.9 | 2022-12-27 | 2023-01-09 | 100% | 100% | 100% | 2 | 32.75 | 1.05 | 135.26 | 12.39 | 57.97 | 205.62 | 205.62 | 0 |  | 2022-12-27 | TRUE | 5.9 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 8z | 79182 |  | Electrical Work (KMEP - BW 0948) | Level 30 | 1399-37A | 5 | 2 | 1.5 | 1 | 5 | m2-LxW | 15 | 2022-12-27 |  | 100% | 100% | 0% | 8.7143 | 36.52 | 2.94 | 383.46 | 384.3 | 0 | 767.76 | 572.46 | 195.3 |  | 2022-12-27 | TRUE | 15 | TRUE
E11/K149/SK/SR/517 | RESIDENCE | 158&158a | 79183 | 80857 | Balcony Ceiling Work | Level 13 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-28 | 2022-12-30 | 100% | 100% | 100% | 0.42857 | 1772.5845 | 52.192 | 1240.81 | 22.37 | 531.78 | 1794.96 | 1794.96 | 0 | Tas Quote 2439-25-1 (item#5) | 2022-12-28 | TRUE | 1 | TRUE
E11/K149/SK/SR/517 | RESIDENCE | 159&159a | 79184 | 80859 | Balcony Ceiling Work | Level 13 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-28 | 2023-01-02 | 100% | 100% | 100% | 0.85714 | 1772.5845 | 52.192 | 1240.81 | 44.74 | 531.78 | 1817.33 | 1817.33 | 0 | Tas Quote 2439-25-1 (item#5) | 2022-12-28 | TRUE | 1 | TRUE
E11/K149/SK/SR/517 | RESIDENCE | 160&160a | 79185 | 80858 | Balcony Ceiling Work | Level 21 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-28 | 2022-12-31 | 100% | 100% | 100% | 0.57143 | 1772.5845 | 52.192 | 1240.81 | 29.82 | 531.78 | 1802.41 | 1802.41 | 0 | Tas Quote 2439-25-1 (item#5) | 2022-12-28 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 161 | 79186 |  | Electrical Work (KMEP - BW 0948) | Ground Level | Tower | 1 | 2.5 | 1.3 | 2 | 1 | rm | 2 | 2022-12-28 |  | 100% | 100% | 0% | 8.5714 | 63.34 | 7.28 | 88.68 | 124.8 | 0 | 213.48 | 149 | 64.48 |  | 2022-12-28 | TRUE | 2 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 161a | 79187 |  | Electrical Work (KMEP - BW 0948) | Ground Level | Tower | 1 | 1.5 | 0.9 | 2 | 1 | rm | 2 | 2022-12-28 |  | 100% | 100% | 0% | 8.5714 | 63.34 | 7.28 | 88.68 | 124.8 | 0 | 213.48 | 149 | 64.48 |  | 2022-12-28 | TRUE | 2 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 161b | 79187 |  | Electrical Work (KMEP - BW 0948) | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 1 | 0.75 | 1 | 1 | m2-LxW | 0.75 | 2022-12-28 |  | 100% | 100% | 0% | 8.5714 | 36.52 | 2.94 | 19.17 | 18.9 | 0 | 38.07 | 28.31 | 9.76 |  | 2022-12-28 | TRUE | 0.75 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 162 | 79188 | 78626 | Door Frame Fixing Work | Ground Level | Independent | 1 | 4.3 | 1.3 | 4 | 1 | m2-LxH | 17.2 | 2022-12-28 | 2023-02-02 | 100% | 100% | 100% | 5.2857 | 12.01 | 0.49 | 144.6 | 44.55 | 61.97 | 251.12 | 179.52 | 71.6 |  | 2022-12-28 | TRUE | 17.2 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 162a | 79188 | 80868 | Door Frame Fixing Work | Ground Level | Cantilever (0 < 0.5m width) | 1 | 2.6 | 0.5 | 1 | 1 | m2-LxW | 1.3 | 2022-12-28 | 2023-01-04 | 100% | 100% | 100% | 1.1429 | 32.75 | 1.05 | 29.8 | 1.56 | 12.77 | 44.13 | 44.13 | 0 |  | 2022-12-28 | TRUE | 1.3 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 163 | 79189 |  | KCE Office Area (KMEP - BW 934) | Ground Level | Birdcage | 1 | 11.1 | 7.5 | 4 | 1 | m3 | 333 | 2022-12-28 |  | 100% | 100% | 0% | 8.5714 | 7.08 | 0.49 | 1650.35 | 1398.6 | 0 | 3048.95 | 2326.34 | 722.61 |  | 2022-12-28 | TRUE | 333 | TRUE
E11/K149/SK/SR/517 | RESIDENCE | 164&164a | 79190 | 80860 | Balcony Ceiling Work | Level 20 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-29 | 2023-01-03 | 100% | 100% | 100% | 0.85714 | 1772.5845 | 52.192 | 1240.81 | 44.74 | 531.78 | 1817.33 | 1817.33 | 0 | Tas Quote 2439-25-1 (item#5) | 2022-12-29 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 165 | 79191 | 80864 | Entrance Area Frame Fixing Work | Ground Level | Tower | 1 | 1.8 | 1.8 | 3.5 | 1 | rm | 3.5 | 2022-12-29 | 2022-12-30 | 100% | 100% | 100% | 0.28571 | 63.34 | 7.28 | 155.18 | 7.28 | 66.51 | 228.97 | 228.97 | 0 |  | 2022-12-29 | TRUE | 3.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 166 | 79192 | 80886 | Road Side Overhead Protection | Ground Level | Birdcage | 1 | 30 | 5 | 2 | 1 | m3 | 300 | 2022-12-29 | 2023-01-14 | 100% | 100% | 100% | 2.4286 | 7.08 | 0.49 | 1486.8 | 357 | 637.2 | 2481 | 2481 | 0 |  | 2022-12-29 | TRUE | 300 | TRUE
E11/K149/SK/SR/517 | RESIDENCE | 167&167a | 79193 | 80861 | Balcony Ceiling Work | Level 20 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-29 | 2023-01-03 | 100% | 100% | 100% | 0.85714 | 1772.5845 | 52.192 | 1240.81 | 44.74 | 531.78 | 1817.33 | 1817.33 | 0 | Tas Quote 2439-25-1 (item#5) | 2022-12-29 | TRUE | 1 | TRUE
E11/K149/SK/SR/517 | RESIDENCE | 168&168a | 79194 | 80862 | Balcony Ceiling Work | Level 15 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-30 | 2023-01-04 | 100% | 100% | 100% | 0.85714 | 1772.5845 | 52.192 | 1240.81 | 44.74 | 531.78 | 1817.33 | 1817.33 | 0 | Tas Quote 2439-25-1 (item#5) | 2022-12-30 | TRUE | 1 | TRUE
E11/K149/SK/SR/517 | RESIDENCE | 169&169a | 79195 | 80863 | Balcony Ceiling Work | Level 15 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-30 | 2023-01-04 | 100% | 100% | 100% | 0.85714 | 1772.5845 | 52.192 | 1240.81 | 44.74 | 531.78 | 1817.33 | 1817.33 | 0 | Tas Quote 2439-25-1 (item#5) | 2022-12-30 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 150c | 79196 | 78649 | Block Work | Level 17 | Additional Boarding | 1 | 8.8 | 0.75 | 1 | 1 | m2-LxW | 6.6 | 2022-12-30 | 2023-02-14 | 100% | 100% | 100% | 6.7143 | 6.63 | 0.7 | 30.63 | 31.02 | 13.13 | 74.78 | 48.45 | 26.33 |  | 2022-12-30 | TRUE | 6.6 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 170 | 79197 | 80869 | Door Frame Fixing Work | Ground Level | Tower | 1 | 1.8 | 1.8 | 3.5 | 1 | rm | 3.5 | 2022-12-31 | 2023-01-04 | 100% | 100% | 100% | 0.71429 | 63.34 | 7.28 | 155.18 | 18.2 | 66.51 | 239.89 | 239.89 | 0 |  | 2022-12-31 | TRUE | 3.5 | TRUE
E11/K149/SK/SR/517 | RESIDENCE | 171&171a | 79198 | 80870 | Balcony Ceiling Work | Level 14 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2023-01-02 | 2023-01-05 | 100% | 100% | 100% | 0.57143 | 1772.5845 | 52.192 | 1240.81 | 29.82 | 531.78 | 1802.41 | 1802.41 | 0 | Tas Quote 2439-25-1 (item#5) | 2023-01-02 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 172 | 79200 |  | Glass Instalation Work | Ground Level | Independent | 1 | 5 | 1.3 | 4.5 | 1 | m2-LxH | 22.5 | 2023-01-03 |  | 100% | 100% | 0% | 7.7143 | 12.01 | 0.49 | 189.16 | 85.05 | 0 | 274.21 | 225.39 | 48.82 |  | 2023-01-03 | TRUE | 22.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 172a | 79200 |  | Glass Instalation Work | Ground Level | Independent | 1 | 6.3 | 1.3 | 2.5 | 1 | m2-LxH | 15.75 | 2023-01-03 |  | 100% | 100% | 0% | 7.7143 | 12.01 | 0.49 | 132.41 | 59.54 | 0 | 191.95 | 157.77 | 34.18 |  | 2023-01-03 | TRUE | 15.75 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 172b | 79200 |  | Glass Instalation Work | Ground Level | Independent | 1 | 8 | 1.3 | 2 | 1 | m2-LxH | 16 | 2023-01-03 |  | 100% | 100% | 0% | 7.7143 | 12.01 | 0.49 | 134.51 | 60.48 | 0 | 194.99 | 160.27 | 34.72 |  | 2023-01-03 | TRUE | 16 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 173 | 75751 |  | Glass Instalation Work | Ground Level | Independent | 1 | 6.3 | 1.3 | 4.5 | 1 | m2-LxH | 28.35 | 2023-01-03 |  | 100% | 100% | 0% | 7.7143 | 12.01 | 0.49 | 238.34 | 107.16 | 0 | 345.5 | 283.98 | 61.52 |  | 2023-01-03 | TRUE | 28.35 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 173a | 75751 |  | Glass Instalation Work | Ground Level | Independent | 1 | 5 | 1.3 | 2.5 | 1 | m2-LxH | 12.5 | 2023-01-03 |  | 100% | 100% | 0% | 7.7143 | 12.01 | 0.49 | 105.09 | 47.25 | 0 | 152.34 | 125.22 | 27.12 |  | 2023-01-03 | TRUE | 12.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 173b | 75751 |  | Glass Instalation Work | Ground Level | Independent | 1 | 3.5 | 1 | 1.5 | 1 | m2-LxH | 5.25 | 2023-01-03 |  | 100% | 100% | 0% | 7.7143 | 12.01 | 0.49 | 44.14 | 19.85 | 0 | 63.99 | 52.59 | 11.4 |  | 2023-01-03 | TRUE | 5.25 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 124a | 75752 | 80888 | Near Shaft 9 (KMEP - BW 0858) | Ground Level | Cantilever (0 < 0.5m width) | 1 | 1.8 | 0.5 | 1 | 1 | m2-LxW | 0.9 | 2023-01-03 | 2023-01-16 | 100% | 100% | 100% | 2 | 32.75 | 1.05 | 20.63 | 1.89 | 8.84 | 31.36 | 31.36 | 0 |  | 2023-01-03 | TRUE | 0.9 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 174 | 75753 | 80879 | KMEP Work | Basement 1 | Independent | 1 | 30 | 1.3 | 3 | 1 | m2-LxH | 90 | 2023-01-03 | 2023-01-06 | 100% | 100% | 100% | 0.57143 | 12.01 | 0.49 | 756.63 | 25.2 | 324.27 | 1106.1 | 1106.1 | 0 |  | 2023-01-03 | TRUE | 90 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 174a | 75753 | 80879 | KMEP Work | Basement 1 | Cantilever (0 < 0.5m width) | 1 | 16 | 0.5 | 1 | 1 | m2-LxW | 8 | 2023-01-03 | 2023-01-06 | 100% | 100% | 100% | 0.57143 | 32.75 | 1.05 | 183.4 | 4.8 | 78.6 | 266.8 | 266.8 | 0 |  | 2023-01-03 | TRUE | 8 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 163a | 75754 |  | KCE Office Area (KMEP - BW 934) | Ground Level | Birdcage | 1 | 15.5 | 3.1 | 4 | 1 | m3 | 192.2 | 2023-01-03 |  | 100% | 100% | 0% | 7.7143 | 7.08 | 0.49 | 952.54 | 726.52 | 0 | 1679.06 | 1261.98 | 417.08 |  | 2023-01-03 | TRUE | 192.2 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 163b | 75755 |  | KCE Office Area (KMEP - BW 934) | Ground Level | Birdcage | 1 | 12.2 | 7 | 4 | 1 | m3 | 341.6 | 2023-01-03 |  | 100% | 100% | 0% | 7.7143 | 7.08 | 0.49 | 1692.97 | 1291.25 | 0 | 2984.22 | 2242.95 | 741.27 |  | 2023-01-03 | TRUE | 341.6 | TRUE
E11/K149/SK/SR/517 | RESIDENCE | 175&175a | 75756 | 80880 | Balcony Ceiling Work | Level 14 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2023-01-03 | 2023-01-07 | 100% | 100% | 100% | 0.71429 | 1772.5845 | 52.192 | 1240.81 | 37.28 | 531.78 | 1809.87 | 1809.87 | 0 | Tas Quote 2439-25-1 (item#5) | 2023-01-03 | TRUE | 1 | TRUE
E11/K149/SK/SR/517 | RESIDENCE | 176&176a | 75757 |  | Balcony Ceiling Work | Level 16 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2023-01-04 |  | 100% | 100% | 0% | 7.5714 | 1772.5845 | 52.192 | 1240.81 | 395.17 | 0 | 1635.98 | 1404.84 | 231.14 | Tas Quote 2439-25-1 (item#5) | 2023-01-04 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 177 | 75758 | 80881 | Electrical KMEP-BW 948 | Ground Level | Independent 1.8m wide | 1 | 7 | 1.8 | 4 | 1 | m2-LxH | 28 | 2023-01-04 | 2023-01-09 | 100% | 100% | 100% | 0.85714 | 16.76 | 0.77 | 328.5 | 18.48 | 140.78 | 487.76 | 487.76 | 0 |  | 2023-01-04 | TRUE | 28 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 177a | 75758 | 80881 | Electrical KMEP-BW 948 | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 2 | 1.5 | 1 | 1 | m2-LxW | 3 | 2023-01-04 | 2023-01-09 | 100% | 100% | 100% | 0.85714 | 36.52 | 2.94 | 76.69 | 7.56 | 32.87 | 117.12 | 117.12 | 0 |  | 2023-01-04 | TRUE | 3 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 178 | 75759 | 78647 | Shaft 9 KMEP-BW 0858 | Ground Level | Tower | 1 | 1.8 | 1.8 | 12.5 | 1 | rm | 12.5 | 2023-01-04 | 2023-02-09 | 100% | 100% | 100% | 5.2857 | 63.34 | 7.28 | 554.23 | 481 | 237.53 | 1272.76 | 840.23 | 432.53 |  | 2023-01-04 | TRUE | 12.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 178 | 75759 | 78647 | Shaft 9 KMEP-BW 0858 | Ground Level | Additional Boarding | 4 | 1.8 | 1.8 | 1 | 4 | m2-LxW | 12.96 | 2023-01-04 | 2023-02-09 | 100% | 100% | 100% | 5.2857 | 6.63 | 0.7 | 60.15 | 47.95 | 25.78 | 133.88 | 88.66 | 45.22 |  | 2023-01-04 | TRUE | 12.96 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 178a | 75759 | 78647 | Shaft 9 KMEP-BW 0858 | Ground Level | Cantilever (0 < 0.5m width) | 1 | 4.1 | 0.5 | 1 | 1 | m2-LxW | 2.05 | 2023-01-04 | 2023-02-09 | 100% | 100% | 100% | 5.2857 | 32.75 | 1.05 | 47 | 11.38 | 20.14 | 78.52 | 53.77 | 24.75 |  | 2023-01-04 | TRUE | 2.05 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 163c | 75760 |  | KCE Office Area (KMEP - BW 946) | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 6.8 | 1.2 | 1 | 1 | m2-LxW | 8.16 | 2023-01-04 |  | 100% | 100% | 0% | 7.5714 | 36.52 | 2.94 | 208.6 | 181.64 | 0 | 390.24 | 284 | 106.24 |  | 2023-01-04 | TRUE | 8.16 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 163d | 75761 |  | KCE Office Area (KMEP - BW 946) | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 4 | 1.5 | 1 | 1 | m2-LxW | 6 | 2023-01-04 |  | 100% | 100% | 0% | 7.5714 | 36.52 | 2.94 | 153.38 | 133.56 | 0 | 286.94 | 208.82 | 78.12 |  | 2023-01-04 | TRUE | 6 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 179 | 75762 | 80884 | Shaft 9 KMEP-BW 0858 | Ground Level | Tower | 1 | 2.5 | 0.6 | 2 | 1 | rm | 2 | 2023-01-05 | 2023-01-11 | 100% | 100% | 100% | 1 | 63.34 | 7.28 | 88.68 | 14.56 | 38 | 141.24 | 141.24 | 0 |  | 2023-01-05 | TRUE | 2 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 180 | 75763 |  | Electrical KMEP-BW 0987 | Ground Level | Independent 1.8m wide | 1 | 10 | 2.5 | 6.2 | 1 | m2-LxH | 62 | 2023-01-06 |  | 100% | 100% | 0% | 7.2857 | 16.76 | 0.77 | 727.38 | 347.82 | 0 | 1075.2 | 863.78 | 211.42 |  | 2023-01-06 | TRUE | 62 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 181 | 75764 | 82161 | Electrical Work | Ground Level | Tower | 1 | 2 | 0.9 | 2 | 1 | rm | 2 | 2023-01-07 | 2023-02-18 | 100% | 100% | 100% | 6.1429 | 63.34 | 7.28 | 88.68 | 89.44 | 38 | 216.12 | 128.2 | 87.92 |  | 2023-01-07 | TRUE | 2 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 182 | 75765 | 82172 | Electrical Work | Ground Level | Tower | 1 | 2 | 1.5 | 3.5 | 1 | rm | 3.5 | 2023-01-07 | 2023-02-20 | 100% | 100% | 100% | 6.4286 | 63.34 | 7.28 | 155.18 | 163.8 | 66.51 | 385.49 | 224.34 | 161.15 |  | 2023-01-07 | TRUE | 3.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 182 | 75765 | 82172 | Electrical Work | Ground Level | Additional Boarding | 1 | 2 | 1.5 |  | 1 | m2-LxW | 3 | 2023-01-07 | 2023-02-20 | 100% | 100% | 100% | 6.4286 | 6.63 | 0.7 | 13.92 | 13.5 | 5.97 | 33.39 | 19.62 | 13.77 |  | 2023-01-07 | TRUE | 3 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 180a | 75766 |  | Electrical KMEP-BW 0987 | Ground Level | Independent 1.8m wide | 1 | 15 | 2.5 | 6.2 | 1 | m2-LxW | 37.5 | 2023-01-07 |  | 100% | 100% | 0% | 7.1429 | 16.76 | 0.77 | 439.95 | 206.25 | 0 | 646.2 | 518.33 | 127.87 |  | 2023-01-07 | TRUE | 37.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 8a1 | 75767 | 78614 | Glass Instalation Work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 12.6 | 0.75 | 1 | 1 | m2-LxW | 9.45 | 2023-01-07 | 2023-01-28 | 100% | 100% | 100% | 3.1429 | 36.52 | 2.94 | 241.58 | 87.32 | 103.53 | 432.43 | 316.99 | 115.44 |  | 2023-01-07 | TRUE | 9.45 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 183 | 75768 | 78615 | Electrical KMEP-BW 0972 | Basement 1 | Tower | 1 | 2.5 | 2.5 | 2.5 | 1 | rm | 2.5 | 2023-01-10 | 2023-01-31 | 100% | 100% | 100% | 3.1429 | 63.34 | 7.28 | 110.85 | 57.2 | 47.51 | 215.56 | 152.45 | 63.11 |  | 2023-01-10 | TRUE | 2.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 184 | 75769 | 80895 | mechanical Work BW 0972 | Basement 1 | Tower | 1 | 2.5 | 2.5 | 3 | 1 | rm | 3 | 2023-01-10 | 2023-01-23 | 100% | 100% | 100% | 2 | 63.34 | 7.28 | 133.01 | 43.68 | 57.01 | 233.7 | 233.7 | 0 |  | 2023-01-10 | TRUE | 3 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 184a | 75769 | 80895 | mechanical Work BW 0972 | Basement 1 | Additional Boarding | 1 | 2.5 | 1.3 | 1 | 1 | m2-LxW | 3.25 | 2023-01-10 | 2023-01-23 | 100% | 100% | 100% | 2 | 6.63 | 0.7 | 15.08 | 4.55 | 6.46 | 26.09 | 26.09 | 0 |  | 2023-01-10 | TRUE | 3.25 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 185 | 75770 | 78605 | Road Side Access | Level 29 | Tower | 1 | 1.8 | 1.3 | 2 | 1 | rm | 2 | 2023-01-10 | 2023-01-27 | 100% | 100% | 100% | 2.5714 | 63.34 | 7.28 | 88.68 | 37.44 | 38 | 164.12 | 121.96 | 42.16 |  | 2023-01-10 | TRUE | 2 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 186 | 75771 | 80891 | KCE Office Area Access | Ground Level | Independent | 1 | 3.5 | 1.3 | 1 | 1 | m2-LxH | 3.5 | 2023-01-10 | 2023-01-19 | 100% | 100% | 100% | 1.4286 | 12.01 | 0.49 | 29.42 | 2.45 | 12.61 | 44.48 | 44.48 | 0 |  | 2023-01-10 | TRUE | 3.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 8a2 | 75772 |  | Glass Fixing work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 2 | 1.5 | 1 | 1 | m2-LxW | 3 | 2023-01-10 |  | 100% | 100% | 0% | 6.7143 | 36.52 | 2.94 | 76.69 | 59.22 | 0 | 135.91 | 96.85 | 39.06 |  | 2023-01-10 | TRUE | 3 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 187 | 75773 | 78616 | mechanical Work BW 0972 | Basement 1 | Independent | 1 | 6.2 | 1 | 3 | 1 | m2-LxH | 18.6 | 2023-01-11 | 2023-01-31 | 100% | 100% | 100% | 3 | 12.01 | 0.49 | 156.37 | 27.34 | 67.02 | 250.73 | 175.9 | 74.83 |  | 2023-01-11 | TRUE | 18.6 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 187a | 75773 | 78616 | mechanical Work BW 0972 | Basement 1 | Cantilever (0.5 > 1.2m width) | 1 | 6.2 | 1 |  | 1 | m2-LxW | 6.2 | 2023-01-11 | 2023-01-31 | 100% | 100% | 100% | 3 | 36.52 | 2.94 | 158.5 | 54.68 | 67.93 | 281.11 | 98.78 | 182.33 |  | 2023-01-11 | TRUE | 3.1 | FALSE
E11/K149/SK/dm/213 | RESIDENCE | 187b | 75774 | 78617 | mechanical Work BW 0972 | Basement 1 | Tower | 1 | 1.8 | 1.3 | 2 | 1 | rm | 2 | 2023-01-11 | 2023-01-31 | 100% | 100% | 100% | 3 | 63.34 | 7.28 | 88.68 | 43.68 | 38 | 170.36 | 119.88 | 50.48 |  | 2023-01-11 | TRUE | 2 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 188 | 75775 |  | KCE Office Area (KMEP - BW 934) | Level 2 | Independent | 1 | 12.5 | 2.5 | 2.5 | 1 | m2-LxH | 31.25 | 2023-01-11 |  | 100% | 100% | 0% | 6.5714 | 12.01 | 0.49 | 262.72 | 100.63 | 0 | 363.35 | 295.53 | 67.82 |  | 2023-01-11 | TRUE | 31.25 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 188a | 75776 |  | KCE Office Area (KMEP - BW 934) | Level 2 | Independent | 1 | 4 | 1 | 2.5 | 1 | m2-LxH | 10 | 2023-01-11 |  | 100% | 100% | 0% | 6.5714 | 12.01 | 0.49 | 84.07 | 32.2 | 0 | 116.27 | 94.57 | 21.7 |  | 2023-01-11 | TRUE | 10 | TRUE
E11/K149/SK/dm/598 | RESIDENCE | 189&190 | 75777&78 | 78601&80896 | Concrete Cutting Work | Level 24 | 1399-40 | 1 |  |  |  |  | unit | 1 | 2023-01-11 | 2023-01-23 | 100% | 100% | 100% | 1.8571 | 4657 | 183.44 | 3259.9 | 340.67 | 1397.1 | 4997.67 | 4997.67 | 0 | 2439-31-1 (Item-11) | 2023-01-11 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 189 | 75777 | 78601&80896 | Concrete Cutting Work | Level 24 | Netting Supply & Install | 1 | 5.5 | 1 | 1 |  | m2-LxH | 5.5 | 2023-01-11 |  | 100% | 100% | 100% | 6.5714 | 8.52 | 0 | 32.8 | 0 | 14.06 | 46.86 | 46.86 | 0 |  | 2023-01-11 | TRUE | 5.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 191 | 75779 |  | GlassFixing Work | Level 28 | Tower | 1 | 2.5 | 1.3 | 2 | 1 | rm | 2 | 2023-01-12 |  | 100% | 100% | 0% | 6.4286 | 63.34 | 7.28 | 88.68 | 93.6 | 0 | 182.28 | 117.8 | 64.48 |  | 2023-01-12 | TRUE | 2 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 192 | 75780 | 78650 | Pipe Cutting Work | Level 5 | Tower | 1 | 1.8 | 1.3 | 4.5 | 1 | rm | 4.5 | 2023-01-13 | 2023-02-14 | 100% | 100% | 100% | 4.7143 | 63.34 | 7.28 | 199.52 | 154.44 | 85.51 | 439.47 | 260.36 | 179.11 |  | 2023-01-13 | TRUE | 4.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 192 | 75780 | 78650 | Pipe Cutting Work | Level 5 | Additional Boarding | 1 | 1.8 | 1.3 |  | 1 | m2-LxW | 2.34 | 2023-01-13 | 2023-02-14 | 100% | 100% | 100% | 4.7143 | 6.63 | 0.7 | 10.86 | 7.72 | 4.65 | 23.23 | 13.9 | 9.33 |  | 2023-01-13 | TRUE | 2.34 | TRUE
E11/K149/SK/dm/598 | RESIDENCE | 193&193a | 75778 | 78618 | Concrete Cutting Work | Level 23 | 1399-40 | 1 |  |  |  | 1 | unit | 1 | 2023-01-13 | 2023-01-28 | 50% | 50% | 50% | 2.2857 | 4657 | 183.44 | 1629.95 | 209.65 | 698.55 | 2538.15 | 1800.29 | 737.86 | 2439-31-1 (Item-11) | #N/A | #N/A | #N/A | #N/A
E11/K149/SK/dm/213 | RESIDENCE | 194 | 75782 | 78619 | GlassFixing Work | Level 26 | Buttress | 1 | 1.3 | 1.3 | 1.5 |  | m3 | 2.54 | 2023-01-13 | 2023-01-28 | 100% | 100% | 100% | 2.2857 | 5.29 | 0.35 | 9.41 | 2.03 | 4.03 | 15.47 | 11.06 | 4.41 |  | 2023-01-13 | TRUE | 2.54 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 194a | 75782 | 78619 | GlassFixing Work | Level 26 | Tripple Hnadrail | 1 | 1.5 |  | 1.5 |  | lm | 1.5 | 2023-01-13 | 2023-01-28 | 100% | 100% | 100% | 2.2857 | 15 | 0.91 | 15.75 | 3.12 | 6.75 | 25.62 | 18.29 | 7.33 |  | 2023-01-13 | TRUE | 1.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 195 | 75783 |  | Electrical KMEP-BW 0934 | Level 2 | Birdcage | 1 | 15 | 5 | 2.5 | 1 | m3 | 187.5 | 2023-01-13 |  | 100% | 100% | 0% | 6.2857 | 7.08 | 0.49 | 929.25 | 577.5 | 0 | 1506.75 | 1099.88 | 406.87 |  | 2023-01-13 | TRUE | 187.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 195a | 75784 |  | Electrical KMEP-BW 0934 | Level 2 | Independent | 1 | 6.1 | 1.3 | 2.5 | 1 | m2-LxH | 15.25 | 2023-01-13 |  | 100% | 100% | 0% | 6.2857 | 12.01 | 0.49 | 128.21 | 46.97 | 0 | 175.18 | 142.09 | 33.09 |  | 2023-01-13 | TRUE | 15.25 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 195b | 75785 |  | Electrical KMEP-BW 0934 | Level 2 | Birdcage | 1 | 4.3 | 3.6 | 2.5 | 1 | m3 | 38.7 | 2023-01-13 |  | 100% | 100% | 0% | 6.2857 | 7.08 | 0.49 | 191.8 | 119.2 | 0 | 311 | 227.02 | 83.98 |  | 2023-01-13 | TRUE | 38.7 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 195c | 75786 |  | Electrical KMEP-BW 0934 | Level 2 | Tower | 1 | 2.5 | 2.5 | 3 | 1 | rm | 3 | 2023-01-13 |  | 100% | 100% | 0% | 6.2857 | 63.34 | 7.28 | 133.01 | 137.28 | 0 | 270.29 | 173.57 | 96.72 |  | 2023-01-13 | TRUE | 3 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 195c | 75786 |  | Electrical KMEP-BW 0934 | Level 2 | Tower | 1 | 2.5 | 2.5 | 3 | 1 | rm | 3 | 2023-01-13 |  | 100% | 100% | 0% | 6.2857 | 63.34 | 7.28 | 133.01 | 137.28 | 0 | 270.29 | 173.57 | 96.72 |  | 2023-01-13 | TRUE | 3 | TRUE
E11/K149/SK/SR/517 | RESIDENCE | 196&196a | 75787 |  | Balcony Ceiling Work | Level 10 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2023-01-14 |  | 100% | 100% | 0% | 6.1429 | 1772.5845 | 52.192 | 1240.81 | 320.61 | 0 | 1561.42 | 1330.28 | 231.14 | Tas Quote 2439-25-1 (item#5) | 2023-01-14 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 197 | 75788 |  | Access Scaffold | Level 10 | Tower | 1 | 1.8 | 1.3 | 3.5 | 1 | rm | 3.5 | 2023-01-14 |  | 100% | 100% | 0% | 6.1429 | 63.34 | 7.28 | 155.18 | 156.52 | 0 | 311.7 | 198.86 | 112.84 |  | 2023-01-14 | TRUE | 3.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 197a | 75788 |  | Access Scaffold | Level 10 | Cantilever (0.5 > 1.2m width) | 1 | 1.3 | 1 |  | 1 | m2-LxW | 1.3 | 2023-01-14 |  | 100% | 100% | 0% | 6.1429 | 36.52 | 2.94 | 33.23 | 23.48 | 0 | 56.71 | 39.78 | 16.93 |  | 2023-01-14 | TRUE | 1.3 | TRUE
E11/K149/SK/SR/517 | RESIDENCE | 198&198a | 75789 |  | Balcony Ceiling Work | Level 16 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2023-01-14 |  | 100% | 100% | 0% | 6.1429 | 1772.5845 | 52.192 | 1240.81 | 320.61 | 0 | 1561.42 | 1330.28 | 231.14 | Tas Quote 2439-25-1 (item#5) | 2023-01-14 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 199 | 75788 |  | EFIS Instalation Work | Level 10 | Independent | 1 | 10 | 0.9 | 3.5 | 1 | m2-LxH | 35 | 2023-01-16 |  | 100% | 100% | 0% | 5.8571 | 12.01 | 0.49 | 294.25 | 100.45 | 0 | 394.7 | 318.75 | 75.95 |  | #N/A | #N/A | #N/A | #N/A
E11/K149/SK/dm/213 | RESIDENCE | 199 | 75788 |  | EFIS Instalation Work | Level 10 | Additional Boarding | 1 | 10 | 0.9 |  | 1 | m2-LxW | 9 | 2023-01-16 |  | 100% | 100% | 0% | 5.8571 | 6.63 | 0.7 | 41.77 | 36.9 | 0 | 78.67 | 50.77 | 27.9 |  | #N/A | #N/A | #N/A | #N/A
E11/K149/SK/dm/213 | RESIDENCE | 199a | 75792 |  | EFIS Instalation Work | Level 10 | Independent | 1 | 8.8 | 0.9 | 1 | 1 | m2-LxH | 8.8 | 2023-01-16 |  | 100% | 100% | 0% | 5.8571 | 12.01 | 0.49 | 73.98 | 25.26 | 0 | 99.24 | 80.14 | 19.1 |  | 2023-01-16 | TRUE | 8.8 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 200 | 75791 | 78627 | Electrical KMEP-BW 1042 | Ground Level | Tower | 1 | 1.8 | 1.3 | 3.5 | 1 | rm | 3.5 | 2023-01-16 | 2023-02-02 | 100% | 100% | 100% | 2.5714 | 63.34 | 7.28 | 155.18 | 65.52 | 66.51 | 287.21 | 191.58 | 95.63 |  | 2023-01-16 | TRUE | 3.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 200 | 75791 | 78627 | Electrical KMEP-BW 1042 | Ground Level | Additional Boarding | 1 | 1.8 | 1.3 |  | 1 | m2-LxW | 2.34 | 2023-01-16 | 2023-02-02 | 100% | 100% | 100% | 2.5714 | 6.63 | 0.7 | 10.86 | 4.21 | 4.65 | 19.72 | 13.2 | 6.52 |  | 2023-01-16 | TRUE | 2.34 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 150e | 75793 |  | EFIS Instalation Work | Level 10 | Additional Boarding | 1 | 8.8 | 0.9 |  | 1 | m2-LxW | 7.92 | 2023-01-16 |  | 100% | 100% | 0% | 5.8571 | 6.63 | 0.7 | 36.76 | 32.47 | 0 | 69.23 | 44.68 | 24.55 |  | 2023-01-16 | TRUE | 7.92 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 201 | 75794 | 78603 | Wall Finishing Work | Level 31 | Tower | 1 | 1.8 | 1.3 | 0.5 | 1 | rm | 0.5 | 2023-01-16 | 2023-01-24 | 100% | 100% | 100% | 1.2857 | 63.34 | 7.28 | 22.17 | 4.68 | 9.5 | 36.35 | 36.35 | 0 |  | 2023-01-16 | TRUE | 0.5 | TRUE
E11/K149/MS/MV/564 | RESIDENCE | 202 | 75795 |  | GRC Instalation Work | Level 10 | 1399-34b | 1 |  |  |  | 1 | unit | 1 | 2023-01-16 |  | 100% | 100% | 0% | 5.8571 | 15779.64 | 1079.32 | 11045.75 | 6321.73 | 0 | 17367.48 | 12587.64 | 4779.84 | 2439-26-1(Item-6) | 2023-01-16 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 203 | 75796 | 82151 | Electrical KMEP BW-1042 | Ground Level | Independent | 1 | 5 | 1.3 | 4 | 1 | m2-LxH | 20 | 2023-01-17 | 2023-02-09 | 100% | 100% | 100% | 3.4286 | 12.01 | 0.49 | 168.14 | 33.6 | 72.06 | 273.8 | 180.74 | 93.06 |  | 2023-01-17 | TRUE | 20 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 203 | 75796 | 82151 | Electrical KMEP BW-1042 | Ground Level | Additional Boarding | 1 | 5 | 1.3 |  | 1 | m2-LxW | 6.5 | 2023-01-17 | 2023-02-09 | 100% | 100% | 100% | 3.4286 | 6.63 | 0.7 | 30.17 | 15.6 | 12.93 | 58.7 | 36.02 | 22.68 |  | 2023-01-17 | TRUE | 6.5 | TRUE
E11/K149/NA/dm/612 | RESIDENCE | 204 | 75797 | 78606 | Wall Finishing Work | Ground Level | 1399-44 | 1 | 8 | 1.5 | 3 | 1 | m2-LxH | 24 | 2023-01-17 | 2023-01-27 | 100% | 100% | 100% | 1.5714 | 326.29 | 26.113 | 5481.67 | 984.83 | 2349.29 | 8815.79 | 6287.44 | 2528.35 | Prorate 2439-32-1 (Item-12) | 2023-01-17 | TRUE | 24 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 205 | 75798 | 80898 | Electrical KMEP BW-0987 | Level 2 | Tower | 2.5 | 1.8 | 6 | 1 | 1 | rm | 2.5 | 2023-01-17 | 2023-01-23 | 100% | 100% | 100% | 1 | 63.34 | 7.28 | 110.85 | 18.2 | 47.51 | 176.56 | 176.56 | 0 |  | 2023-01-17 | TRUE | 2.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 205 | 75798 | 80898 | Electrical KMEP BW-0987 | Level 2 | Additional Boarding | 1 | 2.5 | 1.8 |  | 1 | m2-LxW | 4.5 | 2023-01-17 | 2023-01-23 | 100% | 100% | 100% | 1 | 6.63 | 0.7 | 20.88 | 3.15 | 8.95 | 32.98 | 32.98 | 0 |  | 2023-01-17 | TRUE | 4.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 205a | 75798 | 80898 | Electrical KMEP BW-0987 | Level 2 | Cantilever (0 < 0.5m width) | 1 | 2.5 | 0.5 |  | 1 | m2-LxW | 1.25 | 2023-01-17 | 2023-01-23 | 100% | 100% | 100% | 1 | 32.75 | 1.05 | 28.66 | 1.31 | 12.28 | 42.25 | 42.25 | 0 |  | 2023-01-17 | TRUE | 1.25 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 206 | 75799 | 80900 | Block Work | Level 2 | Tower | 2.5 | 1.3 | 3.8 | 1 | 1 | rm | 2.5 | 2023-01-18 | 2023-01-23 | 100% | 100% | 100% | 0.85714 | 63.34 | 7.28 | 110.85 | 15.6 | 47.51 | 173.96 | 173.96 | 0 |  | 2023-01-18 | TRUE | 2.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 206 | 75799 | 80900 | Block Work | Level 2 | Additional Boarding | 1 | 2.5 | 1.3 |  | 1 | m2-LxW | 3.25 | 2023-01-18 | 2023-01-23 | 100% | 100% | 100% | 0.85714 | 6.63 | 0.7 | 15.08 | 1.95 | 6.46 | 23.49 | 23.49 | 0 |  | 2023-01-18 | TRUE | 3.25 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 207 | 75800 | 80899 | Block Work | Level 2 | Independent | 3.6 | 1.3 | 1.5 | 1 | 1 | m2-LxH | 4.68 | 2023-01-18 | 2023-01-23 | 100% | 100% | 100% | 0.85714 | 12.01 | 0.49 | 39.34 | 1.97 | 16.86 | 58.17 | 58.17 | 0 |  | 2023-01-18 | TRUE | 4.68 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 208 | 75853 | 78607 | Loading Bay Work | Roof | Independent 1.8m wide | 1 | 4 | 2 | 0.5 | 1 | m2-LxH | 2 | 2023-01-18 | 2023-01-26 | 100% | 100% | 100% | 1.2857 | 16.76 | 0.77 | 23.46 | 1.98 | 10.06 | 35.5 | 25.22 | 10.28 |  | 2023-01-18 | TRUE | 2 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 209 | 75854 | 78608 | Canopy Frame Instalation Work | Roof | Independent | 1 | 10 | 1.5 | 1.5 | 1 | m2-LxH | 15 | 2023-01-18 | 2023-01-26 | 100% | 100% | 100% | 1.2857 | 12.01 | 0.49 | 126.11 | 9.45 | 54.05 | 189.61 | 134.51 | 55.1 |  | 2023-01-18 | TRUE | 15 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 181a | 75855 | 82162 | Electrical Work | Ground Level | Tower | 1 | 2 | 1 | 2 | 1 | rm | 2 | 2023-01-19 | 2023-02-18 | 100% | 100% | 100% | 4.4286 | 63.34 | 7.28 | 88.68 | 64.48 | 38 | 191.16 | 103.24 | 87.92 |  | 2023-01-19 | TRUE | 2 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 181b | 75855 | 82162 | Electrical Work | Ground Level | Cantilever (0 < 0.5m width) | 1 | 2 | 0.25 |  | 1 | m2-LxW | 0.5 | 2023-01-19 | 2023-02-18 | 100% | 100% | 100% | 4.4286 | 32.75 | 1.05 | 11.46 | 2.33 | 4.91 | 18.7 | 11.99 | 6.71 |  | 2023-01-19 | TRUE | 0.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 195d | 75857 |  | Electrical Work BW-0934 | Level 2 | Birdcage | 1 | 17 | 3 | 2.5 | 1 | m3 | 127.5 | 2023-01-19 |  | 100% | 100% | 0% | 5.4286 | 7.08 | 0.49 | 631.89 | 339.15 | 0 | 971.04 | 694.37 | 276.67 |  | 2023-01-19 | TRUE | 127.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 195e | 75858 |  | Electrical Work BW-0934 | Level 2 | Independent | 1 | 8.8 | 1.3 | 2.5 | 1 | m2-LxH | 22 | 2023-01-19 |  | 100% | 100% | 0% | 5.4286 | 12.01 | 0.49 | 184.95 | 58.52 | 0 | 243.47 | 195.73 | 47.74 |  | 2023-01-19 | TRUE | 22 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 195f | 75859 |  | Electrical Work BW-0934 | Level 2 | Independent | 1 | 6.3 | 2.5 | 2.5 | 1 | m2-LxH | 15.75 | 2023-01-19 |  | 100% | 100% | 0% | 5.4286 | 12.01 | 0.49 | 132.41 | 41.9 | 0 | 174.31 | 140.13 | 34.18 |  | 2023-01-19 | TRUE | 15.75 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 195g | 75860 |  | Electrical Work BW-0934 | Level 2 | Independent | 1 | 3.8 | 1.3 | 2.5 | 1 | m2-LxH | 9.5 | 2023-01-19 |  | 100% | 100% | 0% | 5.4286 | 12.01 | 0.49 | 79.87 | 25.27 | 0 | 105.14 | 84.53 | 20.61 |  | 2023-01-19 | TRUE | 9.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 207a | 75861 | 80899 | Block Work | Level 2 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1.3 |  | 1 | m2-LxW | 1.95 | 2023-01-19 | 2023-01-23 | 100% | 100% | 100% | 0.71429 | 36.52 | 2.94 | 49.85 | 4.1 | 21.36 | 75.31 | 75.31 | 0 |  | 2023-01-19 | TRUE | 1.95 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 211 | 75862 | 78637 | Wall Repair Work | Basement 1 | Tower | 1 | 2.5 | 1 | 1.5 | 1 | rm | 1.5 | 2023-01-20 | 2023-02-06 | 100% | 100% | 100% | 2.5714 | 63.34 | 7.28 | 66.51 | 28.08 | 28.5 | 123.09 | 75.87 | 47.22 |  | 2023-01-20 | TRUE | 1.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 212 | 75863 | 78643 | Wall Repair Work | Basement 2 | Independent | 1 | 3.8 | 0.9 | 1 | 1 | m2-LxH | 3.8 | 2023-01-20 | 2023-02-06 | 100% | 100% | 100% | 2.5714 | 12.01 | 0.49 | 31.95 | 4.79 | 13.69 | 50.43 | 33.55 | 16.88 |  | 2023-01-20 | TRUE | 3.8 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 213 | 75864 | 78632 | Edge Protection | Roof | Tripple Hnadrail | 1 | 20 |  | 1.5 |  | lm | 20 | 2023-01-20 | 2023-02-06 | 100% | 100% | 100% | 2.5714 | 15 | 0.91 | 210 | 46.8 | 90 | 346.8 | 225.6 | 121.2 |  | 2023-01-20 | TRUE | 20 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 214 | 75865 | 78628 | Board Fixing Work | Ground Level | Tower | 1 | 2.5 | 1.3 | 3.5 | 1 | rm | 3.5 | 2023-01-20 | 2023-02-06 | 100% | 100% | 100% | 2.5714 | 63.34 | 7.28 | 155.18 | 65.52 | 66.51 | 287.21 | 177.02 | 110.19 |  | 2023-01-20 | TRUE | 3.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 214 | 75865 | 78628 | Board Fixing Work | Ground Level | Additional Boarding | 1 | 2.5 | 1.3 |  | 1 | m2-LxW | 3.25 | 2023-01-20 | 2023-02-06 | 100% | 100% | 100% | 2.5714 | 6.63 | 0.7 | 15.08 | 5.85 | 6.46 | 27.39 | 17.03 | 10.36 |  | 2023-01-20 | TRUE | 3.25 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 215 | 75866 | 78629 | Board Fixing Work | Ground Level | Tower | 1 | 1.8 | 1.3 | 3.5 | 1 | rm | 3.5 | 2023-01-20 | 2023-02-06 | 100% | 100% | 100% | 2.5714 | 63.34 | 7.28 | 155.18 | 65.52 | 66.51 | 287.21 | 177.02 | 110.19 |  | 2023-01-20 | TRUE | 3.5 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 215 | 75866 | 78629 | Board Fixing Work | Ground Level | Additional Boarding | 1 | 1.8 | 1.3 |  | 1 | m2-LxW | 2.34 | 2023-01-20 | 2023-02-06 | 100% | 100% | 100% | 2.5714 | 6.63 | 0.7 | 10.86 | 4.21 | 4.65 | 19.72 | 12.26 | 7.46 |  | 2023-01-20 | TRUE | 2.34 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 216 | 75867 | 78630 | Wall Repair Work | Basement 2 | Independent | 1 | 3.8 | 0.9 | 1.5 | 1 | m2-LxH | 5.7 | 2023-01-21 | 2023-02-04 | 100% | 100% | 100% | 2.1429 | 12.01 | 0.49 | 47.92 | 5.99 | 20.54 | 74.45 | 49.92 | 24.53 |  | 2023-01-21 | TRUE | 5.7 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 216a | 75867 | 78630 | Wall Repair Work | Basement 2 | Independent | 1 | 7 | 0.9 | 2 | 1 | m2-LxH | 14 | 2023-01-21 | 2023-02-04 | 100% | 100% | 100% | 2.1429 | 12.01 | 0.49 | 117.7 | 14.7 | 50.44 | 182.84 | 122.6 | 60.24 |  | 2023-01-21 | TRUE | 14 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 216b | 75868 | 78631 | Wall Repair Work | Basement 1 | Independent | 1 | 7.5 | 0.9 | 2.5 | 1 | m2-LxH | 18.75 | 2023-01-21 | 2023-02-04 | 100% | 100% | 100% | 2.1429 | 12.01 | 0.49 | 157.63 | 19.69 | 67.56 | 244.88 | 164.19 | 80.69 |  | 2023-01-21 | TRUE | 18.75 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 216b | 75868 | 78631 | Wall Repair Work | Basement 1 | Additional Boarding | 1 | 7.5 | 0.9 |  | 1 | m2-LxW | 6.75 | 2023-01-21 | 2023-02-04 | 100% | 100% | 100% | 2.1429 | 6.63 | 0.7 | 31.33 | 10.13 | 13.43 | 54.89 | 34.71 | 20.18 |  | 2023-01-21 | TRUE | 6.75 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 216c | 75869 | 78631 | Wall Repair Work | Basement 1 | Independent | 1 | 7.5 | 0.9 | 2.5 | 1 | m2-LxH | 18.75 | 2023-01-21 | 2023-02-04 | 100% | 100% | 100% | 2.1429 | 12.01 | 0.49 | 157.63 | 19.69 | 67.56 | 244.88 | 164.19 | 80.69 |  | 2023-01-21 | TRUE | 18.75 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 216c | 75869 | 78631 | Wall Repair Work | Basement 1 | Additional Boarding | 1 | 7.5 | 0.9 |  | 1 | m2-LxW | 6.75 | 2023-01-21 | 2023-02-04 | 100% | 100% | 100% | 2.1429 | 6.63 | 0.7 | 31.33 | 10.13 | 13.43 | 54.89 | 34.71 | 20.18 |  | 2023-01-21 | TRUE | 6.75 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 216d | 75869 | 78633 | Wall Repair Work | Basement 1 | Independent | 1 | 6 | 0.9 | 2.5 | 1 | m2-LxH | 15 | 2023-01-21 | 2023-02-04 | 100% | 100% | 100% | 2.1429 | 12.01 | 0.49 | 126.11 | 15.75 | 54.05 | 195.91 | 131.36 | 64.55 |  | 2023-01-21 | TRUE | 15 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 216d | 75869 | 78633 | Wall Repair Work | Basement 1 | Additional Boarding | 1 | 6 | 0.9 |  | 1 | m2-LxW | 5.4 | 2023-01-21 | 2023-02-04 | 100% | 100% | 100% | 2.1429 | 6.63 | 0.7 | 25.06 | 8.1 | 10.74 | 43.9 | 27.76 | 16.14 |  | 2023-01-21 | TRUE | 5.4 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 216e | 75870 | 78633 | Wall Repair Work | Basement 1 | Independent | 1 | 6.3 | 0.9 | 2.5 | 1 | m2-LxH | 15.75 | 2023-01-21 | 2023-02-04 | 100% | 100% | 100% | 2.1429 | 12.01 | 0.49 | 132.41 | 16.54 | 56.75 | 205.7 | 137.92 | 67.78 |  | 2023-01-21 | TRUE | 15.75 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 216e | 75870 | 78633 | Wall Repair Work | Basement 1 | Additional Boarding | 1 | 6.3 | 0.9 |  | 1 | m2-LxW | 5.67 | 2023-01-21 | 2023-02-04 | 100% | 100% | 100% | 2.1429 | 6.63 | 0.7 | 26.31 | 8.51 | 11.28 | 46.1 | 29.15 | 16.95 |  | 2023-01-21 | TRUE | 5.67 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 217 | 75871 | 78639 | Access Scaffold | Ground Level | Independent | 1 | 5.1 | 1.3 | 1 | 1 | m2-LxH | 5.1 | 2023-01-21 | 2023-02-07 | 100% | 100% | 100% | 2.5714 | 12.01 | 0.49 | 42.88 | 6.43 | 18.38 | 67.69 | 44.67 | 23.02 |  | 2023-01-21 | TRUE | 5.1 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 218 | 75872 | 78634 | Wall Finishing Work | Ground Level | Independent | 1 | 6 | 0.9 | 2.5 | 1 | m2-LxH | 15 | 2023-01-23 | 2023-02-04 | 100% | 100% | 100% | 1.8571 | 12.01 | 0.49 | 126.11 | 13.65 | 54.05 | 193.81 | 129.26 | 64.55 |  | 2023-01-23 | TRUE | 15 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 218 | 75872 | 78634 | Wall Finishing Work | Ground Level | Additional Boarding | 1 | 6 | 0.9 |  | 1 | m2-LxW | 5.4 | 2023-01-23 | 2023-02-04 | 100% | 100% | 100% | 1.8571 | 6.63 | 0.7 | 25.06 | 7.02 | 10.74 | 42.82 | 26.68 | 16.14 |  | 2023-01-23 | TRUE | 5.4 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 218a | 75873 | 78634 | Wall Finishing Work | Ground Level | Independent | 1 | 6.8 | 0.9 | 2.5 | 1 | m2-LxH | 17 | 2023-01-23 | 2023-02-04 | 100% | 100% | 100% | 1.8571 | 12.01 | 0.49 | 142.92 | 15.47 | 61.25 | 219.64 | 146.49 | 73.15 |  | 2023-01-23 | TRUE | 17 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 218a | 75873 | 78634 | Wall Finishing Work | Ground Level | Additional Boarding | 1 | 6.8 | 0.9 |  | 1 | m2-LxW | 6.12 | 2023-01-23 | 2023-02-04 | 100% | 100% | 100% | 1.8571 | 6.63 | 0.7 | 28.4 | 7.96 | 12.17 | 48.53 | 30.24 | 18.29 |  | 2023-01-23 | TRUE | 6.12 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 218b | 75874 | 78635 | Wall Finishing Work | Level 1 | Independent | 1 | 5 | 0.9 | 2 | 1 | m2-LxH | 10 | 2023-01-23 | 2023-02-04 | 100% | 100% | 100% | 1.8571 | 12.01 | 0.49 | 84.07 | 9.1 | 36.03 | 129.2 | 86.17 | 43.03 |  | 2023-01-23 | TRUE | 10 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 219 | 75875 | 78636 | Wall Finishing Work | Level 3 | Independent | 1 | 6 | 0.9 | 2.5 | 1 | m2-LxH | 15 | 2023-01-23 | 2023-02-04 | 100% | 100% | 100% | 1.8571 | 12.01 | 0.49 | 126.11 | 13.65 | 54.05 | 193.81 | 129.26 | 64.55 |  | 2023-01-23 | TRUE | 15 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 219 | 75875 | 78636 | Wall Finishing Work | Level 3 | Additional Boarding | 1 | 6 | 0.9 |  | 1 | m2-LxW | 5.4 | 2023-01-23 | 2023-02-04 | 100% | 100% | 100% | 1.8571 | 6.63 | 0.7 | 25.06 | 7.02 | 10.74 | 42.82 | 26.68 | 16.14 |  | 2023-01-23 | TRUE | 5.4 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 220 | 75876 |  | Edge Protection | Ground Level | Tripple Hnadrail | 1 | 24 |  | 1.5 |  | lm | 24 | 2023-01-24 |  | 100% | 100% | 0% | 4.7143 | 15 | 0.91 | 252 | 102.96 | 0 | 354.96 | 258.24 | 96.72 |  | 2023-01-24 | TRUE | 24 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 221 | 75877 |  | Water Proofing Work | Level 31 | Independent | 1 | 3.6 | 1.3 | 4 | 1 | m2-LxH | 14.4 | 2023-01-25 |  | 100% | 100% | 0% | 4.5714 | 12.01 | 0.49 | 121.06 | 32.26 | 0 | 153.32 | 122.07 | 31.25 |  | 2023-01-25 | TRUE | 14.4 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 221 | 75877 |  | Water Proofing Work | Level 31 | Additional Boarding | 1 | 3.6 | 1.3 |  | 1 | m2-LxW | 4.68 | 2023-01-25 |  | 100% | 100% | 0% | 4.5714 | 6.63 | 0.7 | 21.72 | 14.98 | 0 | 36.7 | 22.19 | 14.51 |  | 2023-01-25 | TRUE | 4.68 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 221a | 75877 |  | Water Proofing Work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 4.8 | 0.75 |  | 1 | m2-LxW | 3.6 | 2023-01-25 |  | 100% | 100% | 0% | 4.5714 | 36.52 | 2.94 | 92.03 | 48.38 | 0 | 140.41 | 93.54 | 46.87 |  | 2023-01-25 | TRUE | 3.6 | TRUE
E11/K149/SK/dm/213 | HOTEL | 79 | 79093 |  | Electrical KMEP-BW 0917 | Ground Level | Independent | 1 | 5.3 | 1.3 | 3.8 | 1 | m2-LxH | 20.14 | 2022-12-26 |  | 100% | 100% | 0% | 8.8571 | 12.01 | 0.49 | 169.32 | 87.41 | 0 | 256.73 | 213.02 | 43.71 |  | 2022-12-26 | TRUE | 20.14 | TRUE
E11/K149/SK/dm/213 | HOTEL | 79 | 79093 |  | Electrical KMEP-BW 0917 | Ground Level | Additional Boarding | 1 | 5.3 | 1.3 |  | 1 | m2-LxW | 6.89 | 2022-12-26 |  | 100% | 100% | 0% | 8.8571 | 6.63 | 0.7 | 31.98 | 42.72 | 0 | 74.7 | 53.34 | 21.36 |  | 2022-12-26 | TRUE | 6.89 | TRUE
E11/K149/SK/dm/213 | HOTEL | 80 | 79094 |  | Wall Concrete Work | Level 2 | Independent | 1 | 4.8 | 1.3 | 5 | 1 | m2-LxH | 24 | 2022-12-26 |  | 100% | 100% | 0% | 8.8571 | 12.01 | 0.49 | 201.77 | 104.16 | 0 | 305.93 | 253.85 | 52.08 |  | 2022-12-26 | TRUE | 24 | TRUE
E11/K149/SK/dm/213 | HOTEL | 80 | 79094 |  | Wall Concrete Work | Level 2 | Additional Boarding | 1 | 4.8 | 1.3 |  | 1 | m2-LxW | 6.24 | 2022-12-26 |  | 100% | 100% | 0% | 8.8571 | 6.63 | 0.7 | 28.96 | 38.69 | 0 | 67.65 | 48.3 | 19.35 |  | 2022-12-26 | TRUE | 6.24 | TRUE
E11/K149/SK/dm/213 | HOTEL | 80a | 79095 |  | Wall Concrete Work | Level 2 | Tower | 1 | 1.3 | 1 | 3.5 | 1 | rm | 3.5 | 2022-12-26 |  | 100% | 100% | 0% | 8.8571 | 63.34 | 7.28 | 155.18 | 225.68 | 0 | 380.86 | 268.02 | 112.84 |  | 2022-12-26 | TRUE | 3.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 80a | 79095 |  | Wall Concrete Work | Level 2 | Additional Boarding | 1 | 1 | 1 |  | 1 | m2-LxW | 1 | 2022-12-26 |  | 100% | 100% | 0% | 8.8571 | 6.63 | 0.7 | 4.64 | 6.2 | 0 | 10.84 | 7.74 | 3.1 |  | 2022-12-26 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | HOTEL | 81 | 79096 | 78599 | Staircase 7 For (KMEP - BW 793) | Ground Level | Tower | 1 | 1.8 | 1 | 2.7 | 1 | rm | 2.7 | 2022-12-26 | 2023-02-22 | 100% | 100% | 100% | 8.4286 | 63.34 | 7.28 | 119.71 | 165.67 | 51.31 | 336.69 | 206.76 | 129.93 |  | 2022-12-26 | TRUE | 2.7 | TRUE
E11/K149/SK/dm/213 | HOTEL | 82 | 79097 |  | Canopy EFIS Fixing Work | Level 29 | Independent 1.8m wide | 1 | 22.5 | 1.8 | 8 | 1 | m2-LxH | 180 | 2022-12-28 |  | 100% | 100% | 0% | 8.5714 | 16.76 | 0.77 | 2111.76 | 1188 | 0 | 3299.76 | 2685.96 | 613.8 |  | 2022-12-28 | TRUE | 180 | TRUE
E11/K149/SK/dm/213 | HOTEL | 82a | 79097 | 80935 | Canopy EFIS Fixing Work | Level 29 | Cantilever (0 < 0.5m width) | 1 | 22.5 | 0.5 | 1 | 1 | m2-LxW | 11.25 | 2022-12-28 | 2023-01-28 | 100% | 100% | 100% | 4.5714 | 32.75 | 1.05 | 257.91 | 54 | 110.53 | 422.44 | 306.85 | 115.59 |  | 2022-12-28 | TRUE | 11.25 | TRUE
E11/K149/SK/dm/553 | HOTEL | 83 | 79098 | 80908 | Parapet FIFS Plaster Work | Level 2 | 1399-38 | 1 | 24 | 1.8 | 3 | 1 | m2-LxH | 72 | 2022-12-28 | 2023-01-12 | 100% | 100% | 100% | 2.2857 | 475.573 | 37.29 | 23968.88 | 6136.87 | 10272.38 | 40378.13 | 40378.13 | 0 |  | 2022-12-28 | TRUE | 72 | TRUE
E11/K149/SK/dm/213 | HOTEL | 84 | 79099 | 78593 | Canopy Instalation Work | Level 29 | Independent 1.8m wide | 1 | 12.5 | 1.8 | 3.5 | 1 | m2-LxH | 43.75 | 2022-12-30 | 2023-02-18 | 100% | 100% | 100% | 7.2857 | 16.76 | 0.77 | 513.28 | 245.44 | 219.98 | 978.7 | 643.22 | 335.48 |  | 2022-12-30 | TRUE | 43.75 | TRUE
E11/K149/SK/dm/213 | HOTEL | 84a | 79099 | 78593 | Canopy Instalation Work | Level 29 | Cantilever (0 < 0.5m width) | 1 | 8 | 0.5 | 1 | 1 | m2-LxW | 4 | 2022-12-30 | 2023-02-18 | 100% | 100% | 100% | 7.2857 | 32.75 | 1.05 | 91.7 | 30.6 | 39.3 | 161.6 | 107.9 | 53.7 |  | 2022-12-30 | TRUE | 4 | TRUE
E11/K149/SK/SR/517 | HOTEL | 85&85a | 79100 | 80920 | Balcony Ceiling Work | Level 19 | Design 1399-35b | 1 | 6.1 | 1 | 1 | 1 | unit | 1 | 2022-12-30 | 2023-01-26 | 100% | 100% | 100% | 4 | 2514.5966 | 74.0398 | 1760.22 | 296.16 | 754.38 | 2810.76 | 2045.8 | 764.96 | Tas Quote 2439-25-1 (item#5) | 2022-12-30 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | HOTEL | 150d | 79199 | 78613 | Access Scaffold | Level 17 | Tower | 1 | 2 | 1 | 2 | 1 | rm | 2 | 2023-01-02 | 2023-01-30 | 100% | 100% | 100% | 4.1429 | 63.34 | 7.28 | 88.68 | 60.32 | 38 | 187 | 138.6 | 48.4 |  | 2023-01-02 | TRUE | 2 | TRUE
E11/K149/SK/dm/213 | HOTEL | 84b | 75801 |  | Canopy Instalation Work | Level 29 | Independent 1.8m wide | 1 | 10 | 1.8 | 3.5 | 1 | m2-LxH | 35 | 2023-01-02 |  | 100% | 100% | 0% | 7.8571 | 16.76 | 0.77 | 410.62 | 211.75 | 0 | 622.37 | 503.02 | 119.35 |  | 2023-01-02 | TRUE | 35 | TRUE
E11/K149/SK/dm/213 | HOTEL | 84c | 75801 | 78594 | Canopy Instalation Work | Level 29 | Cantilever (0 < 0.5m width) | 1 | 10 | 0.5 | 1 | 1 | m2-LxW | 5 | 2023-01-02 | 2023-02-18 | 100% | 100% | 100% | 6.8571 | 32.75 | 1.05 | 114.63 | 36 | 49.13 | 199.76 | 132.63 | 67.13 |  | 2023-01-02 | TRUE | 5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 84d | 75802 | 80911 | EFIS Finshing Work | Level 29 | Cantilever (0.5 > 1.2m width) | 1 | 17 | 1.5 | 1 | 1 | m2-LxW | 25.5 | 2023-01-02 | 2023-01-16 | 100% | 100% | 100% | 2.1429 | 36.52 | 2.94 | 651.88 | 160.65 | 279.38 | 1091.91 | 1091.91 | 0 |  | 2023-01-02 | TRUE | 25.5 | TRUE
E11/K149/PK/dm/378 | HOTEL | 43f&43g | 75803 | 80934 | GRC Panel Work | Ground Level | 1399-21 | 1 | 2.5 | 1.3 | 5 | 1 | m2-LxH | 12.5 | 2023-01-02 | 2023-01-30 | 100% | 100% | 100% | 4.1429 | 95.9 | 13.9 | 839.13 | 719.82 | 359.63 | 1918.58 | 1434.84 | 483.74 | Tas Quote - 2439-15-1 (item-1 Prorate) | 2023-01-02 | TRUE | 12.5 | TRUE
E11/K149/SK/SR/517 | HOTEL | 86&86a | 75804 | 80916 | Balcony Ceiling Work | Level 13 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2023-01-03 | 2023-01-20 | 100% | 100% | 100% | 2.5714 | 1772.5845 | 52.192 | 1240.81 | 134.21 | 531.78 | 1906.8 | 1906.8 | 0 | Tas Quote 2439-25-1 (item#5) | 2023-01-03 | TRUE | 1 | TRUE
E11/K149/SK/SR/517 | HOTEL | 87&87a | 75805 | 80917 | Balcony Ceiling Work | Level 14 | Design 1399-35b | 1 | 6.1 | 1 | 1 | 1 | unit | 1 | 2023-01-04 | 2023-01-23 | 100% | 100% | 100% | 2.8571 | 2514.5966 | 74.0398 | 1760.22 | 211.54 | 754.38 | 2726.14 | 2726.14 | 0 | Tas Quote 2439-25-1 (item#5) | 2023-01-04 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | HOTEL | 88 | 75806 | 78560 | Wall Painting Work | basement 2 | Independent | 1 | 4 | 1.3 | 2 | 1 | m2-LxH | 8 | 2023-01-05 | 2023-02-13 | 100% | 100% | 100% | 5.7143 | 12.01 | 0.49 | 67.26 | 22.4 | 28.82 | 118.48 | 79.02 | 39.46 |  | 2023-01-05 | TRUE | 8 | TRUE
E11/K149/SK/dm/213 | HOTEL | 88a | 75807 | 78560 | Wall Painting Work | basement 2 | Tower | 1 | 2.5 | 0.9 | 2 | 1 | rm | 2 | 2023-01-05 | 2023-02-13 | 100% | 100% | 100% | 5.7143 | 63.34 | 7.28 | 88.68 | 83.2 | 38 | 209.88 | 132.36 | 77.52 |  | 2023-01-05 | TRUE | 2 | TRUE
E11/K149/SK/dm/213 | HOTEL | 88b | 75808 | 78561 | Wall Painting Work | basement 2 | Independent | 1 | 3.1 | 1.3 | 1.5 | 1 | m2-LxH | 4.65 | 2023-01-05 | 2023-02-13 | 100% | 100% | 100% | 5.7143 | 12.01 | 0.49 | 39.09 | 13.02 | 16.75 | 68.86 | 45.93 | 22.93 |  | 2023-01-05 | TRUE | 4.65 | TRUE
E11/K149/SK/dm/213 | HOTEL | 88c | 75809 | 78561 | Wall Painting Work | basement 1 | Independent | 1 | 6.1 | 0.9 | 1.5 | 1 | m2-LxH | 9.15 | 2023-01-05 | 2023-02-13 | 100% | 100% | 100% | 5.7143 | 12.01 | 0.49 | 76.92 | 25.62 | 32.97 | 135.51 | 90.37 | 45.14 |  | 2023-01-05 | TRUE | 9.15 | TRUE
E11/K149/SK/dm/213 | HOTEL | 88d | 75810 | 78562 | Wall Painting Work | basement 1 | Independent | 1 | 6.8 | 0.9 | 1.5 | 1 | m2-LxH | 10.2 | 2023-01-05 | 2023-02-13 | 100% | 100% | 100% | 5.7143 | 12.01 | 0.49 | 85.75 | 28.56 | 36.75 | 151.06 | 100.74 | 50.32 |  | 2023-01-05 | TRUE | 10.2 | TRUE
E11/K149/SK/dm/213 | HOTEL | 88e | 75811 | 78562 | Wall Painting Work | basement 1 | Independent | 1 | 6.3 | 0.9 | 3 | 1 | m2-LxH | 18.9 | 2023-01-05 | 2023-02-13 | 100% | 100% | 100% | 5.7143 | 12.01 | 0.49 | 158.89 | 52.92 | 68.1 | 279.91 | 186.67 | 93.24 |  | 2023-01-05 | TRUE | 18.9 | TRUE
E11/K149/SK/dm/213 | HOTEL | 88e | 75811 | 78562 | Wall Painting Work | basement 1 | Additional Boarding | 1 | 6.3 | 0.9 |  | 1 | m2-LxW | 5.67 | 2023-01-05 | 2023-02-13 | 100% | 100% | 100% | 5.7143 | 6.63 | 0.7 | 26.31 | 22.68 | 11.28 | 60.27 | 38.22 | 22.05 |  | 2023-01-05 | TRUE | 5.67 | TRUE
E11/K149/SK/dm/213 | HOTEL | 88f | 75811 | 78563 | Wall Painting Work | basement 1 | Independent | 1 | 6.8 | 0.9 | 3.5 | 1 | m2-LxH | 23.8 | 2023-01-05 | 2023-02-13 | 100% | 100% | 100% | 5.7143 | 12.01 | 0.49 | 200.09 | 66.64 | 85.75 | 352.48 | 235.08 | 117.4 |  | #N/A | #N/A | #N/A | #N/A
E11/K149/SK/dm/213 | HOTEL | 88f | 75811 | 78563 | Wall Painting Work | basement 1 | Additional Boarding | 1 | 6.8 | 0.9 |  | 1 | m2-LxW | 6.12 | 2023-01-05 | 2023-02-13 | 100% | 100% | 100% | 5.7143 | 6.63 | 0.7 | 28.4 | 24.48 | 12.17 | 65.05 | 41.25 | 23.8 |  | #N/A | #N/A | #N/A | #N/A
E11/K149/SK/dm/213 | HOTEL | 89 | 75813 |  | Wall Painting Work | Ground Level | Tower | 1 | 1.3 | 1 | 2.5 | 1 | rm | 2.5 | 2023-01-05 |  | 100% | 100% | 0% | 7.4286 | 63.34 | 7.28 | 110.85 | 135.2 | 0 | 246.05 | 165.45 | 80.6 |  | 2023-01-05 | TRUE | 2.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 90 | 75814 | 80921 | Road Side Access | Level 28 | Tower | 1 | 1.3 | 0.9 | 1.5 | 1 | rm | 1.5 | 2023-01-06 | 2023-01-26 | 100% | 100% | 100% | 3 | 63.34 | 7.28 | 66.51 | 32.76 | 28.5 | 127.77 | 97.71 | 30.06 |  | 2023-01-06 | TRUE | 1.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 91 | 75815 |  | Road Side Access | Roof | Independent | 1 | 3 | 1.3 | 1 | 1 | m2-LxH | 3 | 2023-01-06 |  | 100% | 100% | 0% | 7.2857 | 12.01 | 0.49 | 25.22 | 10.71 | 0 | 35.93 | 29.42 | 6.51 |  | 2023-01-06 | TRUE | 3 | TRUE
E11/K149/SK/dm/595 | HOTEL | 92&92a | 75816 | 78591 | View Deck Loading Platform | Level 29 | 1399-41A | 1 |  |  |  | 1 | unit | 1 | 2023-01-06 | 2023-02-18 | 100% | 100% | 100% | 6.2857 | 7493.729 | 639.6768 | 5245.61 | 4020.83 | 2248.12 | 11514.56 | 7073.26 | 4441.3 | 2439-30-1 Item--10) | 2023-01-06 | TRUE | 1 | TRUE
E11/K149/SK/SR/517 | HOTEL | 93&93a | 75817 | 80922 | Balcony Ceiling Work | Level 15 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2023-01-07 | 2023-01-27 | 100% | 100% | 100% | 3 | 1772.5845 | 52.192 | 1240.81 | 156.58 | 531.78 | 1929.17 | 1382.47 | 546.7 | Tas Quote 2439-25-1 (item#5) | 2023-01-07 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | HOTEL | 94 | 75818 | 80906 | Electrical Work | basement 1 | Tower | 1 | 2.5 | 1.3 | 2.5 | 1 | rm | 2.5 | 2023-01-09 | 2023-01-10 | 100% | 100% | 100% | 0.28571 | 63.34 | 7.28 | 110.85 | 5.2 | 47.51 | 163.56 | 163.56 | 0 |  | 2023-01-09 | TRUE | 2.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 95 | 75819 | 80943 | Electrical Work BW 0973 | basement 1 | Independent | 1 | 3.8 | 1.3 | 2 | 1 | m2-LxH | 7.6 | 2023-01-09 | 2023-01-28 | 100% | 100% | 100% | 2.8571 | 12.01 | 0.49 | 63.89 | 10.64 | 27.38 | 101.91 | 72.93 | 28.98 |  | 2023-01-09 | TRUE | 7.6 | TRUE
E11/K149/SK/dm/213 | HOTEL | 96 | 75820 | 80912 | Electrical Work BW 0973 | basement 1 | Tower | 1 | 2.5 | 1.3 | 2 | 1 | rm | 2 | 2023-01-09 | 2023-01-16 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 88.68 | 16.64 | 38 | 143.32 | 143.32 | 0 |  | 2023-01-09 | TRUE | 2 | TRUE
E11/K149/SK/SR/517 | HOTEL | 97&97a | 75821 | 80923 | Balcony Ceiling Work | Level 26 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2023-01-09 | 2023-01-26 | 100% | 100% | 100% | 2.5714 | 1772.5845 | 52.192 | 1240.81 | 134.21 | 531.78 | 1906.8 | 1367.56 | 539.24 | Tas Quote 2439-25-1 (item#5) | 2023-01-09 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | HOTEL | 98 | 75822 | 80944 | Electrical Work BW 0973 | basement 1 | Independent 1.8m wide | 1 | 3.6 | 2.5 | 3 | 1 | m2-LxH | 10.8 | 2023-01-10 | 2023-02-01 | 100% | 100% | 100% | 3.2857 | 16.76 | 0.77 | 126.71 | 27.32 | 54.3 | 208.33 | 145.72 | 62.61 |  | 2023-01-10 | TRUE | 10.8 | TRUE
E11/K149/SK/dm/213 | HOTEL | 99 | 75823 | 80903 | Wall Concrete Work | Ground Level | Independent | 1 | 15.7 | 1 | 1 | 1 | m2-LxH | 15.7 | 2023-01-10 | 2023-01-10 | 100% | 100% | 100% | 0.14286 | 12.01 | 0.49 | 131.99 | 1.1 | 56.57 | 189.66 | 189.66 | 0 |  | 2023-01-10 | TRUE | 15.7 | TRUE
E11/K149/SK/SR/517 | HOTEL | 100&100a | 75824 | 80924 | Balcony Ceiling Work | Level 25 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2023-01-10 | 2023-01-27 | 100% | 100% | 100% | 2.5714 | 1772.5845 | 52.192 | 1240.81 | 134.21 | 531.78 | 1906.8 | 1360.11 | 546.69 | Tas Quote 2439-25-1 (item#5) | 2023-01-10 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | HOTEL | 101 | 75826 | 80907 | Electrical Work | basement 1 | Tower | 1 | 2.5 | 1.3 | 2.5 | 1 | rm | 2.5 | 2023-01-10 | 2023-01-12 | 100% | 100% | 100% | 0.42857 | 63.34 | 7.28 | 110.85 | 7.8 | 47.51 | 166.16 | 166.16 | 0 |  | 2023-01-10 | TRUE | 2.5 | TRUE
E11/K149/SK/SR/517 | HOTEL | 102&102a | 75827 | 80925 | Balcony Ceiling Work | Level 26 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2023-01-11 | 2023-01-26 | 100% | 100% | 100% | 2.2857 | 1772.5845 | 52.192 | 1240.81 | 119.3 | 531.78 | 1891.89 | 1352.65 | 539.24 | Tas Quote 2439-25-1 (item#5) | 2023-01-11 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | HOTEL | 103 | 75828 | 80945 | Generator Room AC Chiller Work | basement 1 | Independent | 1 | 5 | 0.6 | 1.5 | 1 | m2-LxH | 7.5 | 2023-01-11 | 2023-01-31 | 100% | 100% | 100% | 3 | 12.01 | 0.49 | 63.05 | 11.03 | 27.02 | 101.1 | 70.93 | 30.17 |  | 2023-01-11 | TRUE | 7.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 104 | 75829 | 80913 | Electrical Work BW 0973 | basement 1 | Independent | 1 | 3.8 | 1.3 | 2.3 | 1 | m2-LxH | 8.74 | 2023-01-11 | 2023-01-16 | 100% | 100% | 100% | 0.85714 | 12.01 | 0.49 | 73.48 | 3.67 | 31.49 | 108.64 | 108.64 | 0 |  | 2023-01-11 | TRUE | 8.74 | TRUE
E11/K149/SK/SR/517 | HOTEL | 105&105a | 75830 | 80926 | Balcony Ceiling Work | Level 20 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2023-01-12 | 2023-01-26 | 100% | 100% | 100% | 2.1429 | 1772.5845 | 52.192 | 1240.81 | 111.84 | 531.78 | 1884.43 | 1345.19 | 539.24 | Tas Quote 2439-25-1 (item#5) | 2023-01-12 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | HOTEL | 82b | 75831 |  | Balcony Ceiling Work | Level 29 | Independent 1.8m wide | 1 | 3.8 | 1.8 | 3.5 | 1 | m2-LxH | 13.3 | 2023-01-12 |  | 100% | 100% | 0% | 6.4286 | 16.76 | 0.77 | 156.04 | 65.84 | 0 | 221.88 | 176.52 | 45.36 |  | 2023-01-12 | TRUE | 13.3 | TRUE
E11/K149/SK/dm/213 | HOTEL | 82c | 75831 |  | Balcony Ceiling Work | Level 29 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 0.75 | 1 | 1 | m2-LxW | 1.13 | 2023-01-12 |  | 100% | 100% | 0% | 6.4286 | 36.52 | 2.94 | 28.89 | 21.36 | 0 | 50.25 | 35.53 | 14.72 |  | 2023-01-12 | TRUE | 1.13 | TRUE
E11/K149/SK/dm/213 | HOTEL | 106 | 75832 | 78564 | Wall Corring Work | Level 29 | Tower | 1 | 2.5 | 1 | 3 | 1 | rm | 3 | 2023-01-12 | 2023-02-09 | 100% | 100% | 100% | 4.1429 | 63.34 | 7.28 | 133.01 | 90.48 | 57.01 | 280.5 | 176.69 | 103.81 |  | 2023-01-12 | TRUE | 3 | TRUE
E11/K149/SK/dm/595 | HOTEL | 107 | 75833 | 79808 | View Deck Loading Platform | Level 29 | 1399-42 | 1 |  |  |  | 1 | unit | 1 | 2023-01-12 | 2023-02-22 | 100% | 100% | 100% | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2439-30-1 Item--10), Charged under Tag 92&92a | 2023-01-12 | TRUE | 1 | TRUE
E11/K149/SK/dm/640 | HOTEL | 108 To 108e | 75838 | 80929 | Steel Column Lifting Work (1399-45a) | Level 29 | Independent | 1 |  |  |  |  | unit | 1 | 2023-01-13 | 2023-01-28 | 75% | 75% | 75% | 2.2857 | 19801.4293 | 837.8213 | 10395.75 | 1436.27 | 4455.32 | 16287.34 | 11562.72 | 4724.62 | Tas Quote 2439-34-1 | 2023-01-13 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | HOTEL | 109 | 75834 |  | Electrical KMEP-BW 1012 | Level 5 | Independent | 1 | 4.3 | 1.3 | 4 | 1 | m2-LxH | 17.2 | 2023-01-13 |  | 100% | 100% | 0% | 6.2857 | 12.01 | 0.49 | 144.6 | 52.98 | 0 | 197.58 | 160.25 | 37.33 |  | 2023-01-13 | TRUE | 17.2 | TRUE
E11/K149/SK/dm/213 | HOTEL | 110 | 75835 |  | Electrical KMEP-BW 1012 | Level 5 | Tower | 1 | 2.5 | 2.5 | 4.5 | 1 | rm | 4.5 | 2023-01-13 |  | 100% | 100% | 0% | 6.2857 | 63.34 | 7.28 | 199.52 | 205.92 | 0 | 405.44 | 260.36 | 145.08 |  | 2023-01-13 | TRUE | 4.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 80b | 75839 |  | Ceiling Work KMEP-BW 1012 | Level 2 | Tower | 1 | 2.5 | 2.5 | 5.5 | 1 | rm | 5.5 | 2023-01-14 |  | 100% | 100% | 0% | 6.1429 | 63.34 | 7.28 | 243.86 | 245.96 | 0 | 489.82 | 312.5 | 177.32 |  | 2023-01-14 | TRUE | 5.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 111 | 75836 |  | Ceiling Work KMEP-BW 1012 | Level 5 | Tower | 1 | 2.5 | 1.3 | 4.5 | 1 | rm | 4.5 | 2023-01-14 |  | 100% | 100% | 0% | 6.1429 | 63.34 | 7.28 | 199.52 | 201.24 | 0 | 400.76 | 255.68 | 145.08 |  | 2023-01-14 | TRUE | 4.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 111 | 75836 |  | Ceiling Work KMEP-BW 1012 | Level 5 | Additional Boarding | 1 | 2.5 | 1.3 |  | 1 | m2-LxW | 3.25 | 2023-01-14 |  | 100% | 100% | 0% | 6.1429 | 6.63 | 0.7 | 15.08 | 13.98 | 0 | 29.06 | 18.98 | 10.08 |  | 2023-01-14 | TRUE | 3.25 | TRUE
E11/K149/SK/dm/213 | HOTEL | 43h | 75837 |  | Wall Plaster Work | Ground Level | Additional Boarding | 1 | 1.5 | 1.5 |  | 1 | m2-LxW | 2.25 | 2023-01-14 | 2023-01-30 | 100% | 100% | 100% | 2.4286 | 6.63 | 0.7 | 10.44 | 3.83 | 4.48 | 18.75 | 13.14 | 5.61 |  | 2023-01-14 | TRUE | 2.25 | TRUE
E11/K149/SK/dm/213 | HOTEL | 112 | 75840 |  | Plant Room Kmep Work | Level 5 | Tower | 1 | 2.5 | 1.8 | 3.2 | 1 | rm | 3.2 | 2023-01-16 |  | 100% | 100% | 0% | 5.8571 | 63.34 | 7.28 | 141.88 | 136.45 | 0 | 278.33 | 175.16 | 103.17 |  | 2023-01-16 | TRUE | 3.2 | TRUE
E11/K149/SK/dm/213 | HOTEL | 112 | 75840 |  | Plant Room Kmep Work | Level 5 | Additional Boarding | 1 | 2.5 | 1.8 |  | 1 | m2-LxW | 4.5 | 2023-01-16 |  | 100% | 100% | 0% | 5.8571 | 6.63 | 0.7 | 20.88 | 18.45 | 0 | 39.33 | 0 | 39.33 |  | 2023-01-16 | TRUE | 0 | FALSE
E11/K149/SK/dm/213 | HOTEL | 112a | 75840 |  | Plant Room Kmep Work | Level 5 | Cantilever (0.5 > 1.2m width) | 1 | 1.8 | 0.75 |  | 1 | m2-LxW | 1.35 | 2023-01-16 |  | 100% | 100% | 0% | 5.8571 | 36.52 | 2.94 | 34.51 | 23.25 | 0 | 57.76 | 40.18 | 17.58 |  | 2023-01-16 | TRUE | 1.35 | TRUE
E11/K149/SK/dm/213 | HOTEL | 113 | 75841 |  | Plant Room Kmep Work | Level 5 | Independent | 1 | 4 | 1.5 | 2.3 | 1 | m2-LxH | 9.2 | 2023-01-16 |  | 100% | 100% | 0% | 5.8571 | 12.01 | 0.49 | 77.34 | 26.4 | 0 | 103.74 | 83.78 | 19.96 |  | 2023-01-16 | TRUE | 9.2 | TRUE
E11/K149/SK/dm/213 | HOTEL | 114 | 75842 | 80915 | Road Side Access | Level 29 | Tower | 1 | 2.5 | 1.3 | 1.5 | 1 | rm | 1.5 | 2023-01-16 | 2023-01-19 | 100% | 100% | 100% | 0.57143 | 63.34 | 7.28 | 66.51 | 6.24 | 28.5 | 101.25 | 101.25 | 0 |  | 2023-01-16 | TRUE | 1.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 115 | 75843 |  | Road Side Access | Level 29 | Independent 1.8m wide | 1 | 11.8 | 2.5 | 3 | 1 | m2-LxH | 35.4 | 2023-01-16 |  | 100% | 100% | 0% | 5.8571 | 16.76 | 0.77 | 415.31 | 159.65 | 0 | 574.96 | 454.25 | 120.71 |  | 2023-01-16 | TRUE | 35.4 | TRUE
E11/K149/SK/dm/213 | HOTEL | 115a | 75843 | 78565 | Road Side Access | Level 29 | Cantilever (0 < 0.5m width) | 1 | 10 | 0.5 |  | 1 | m2-LxW | 5 | 2023-01-16 | 2023-02-13 | 100% | 100% | 100% | 4.1429 | 32.75 | 1.05 | 114.63 | 21.75 | 49.13 | 185.51 | 122.13 | 63.38 |  | 2023-01-16 | TRUE | 5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 116 | 75844 | 80914 | Edge Protection | Level 29 | Tripple Hnadrail | 1 | 20 |  | 1.5 | 1 | lm | 20 | 2023-01-17 | 2023-01-18 | 100% | 100% | 100% | 0.28571 | 15 | 0.91 | 210 | 5.2 | 90 | 305.2 | 305.2 | 0 |  | 2023-01-17 | TRUE | 20 | TRUE
E11/K149/SK/dm/213 | HOTEL | 117 | 75845 |  | Canopy Instalation Work | Roof | Independent 1.8m wide | 1 | 8 | 2.5 | 1.5 | 1 | m2-LxH | 12 | 2023-01-18 |  | 100% | 100% | 0% | 5.5714 | 16.76 | 0.77 | 140.78 | 51.48 | 0 | 192.26 | 151.34 | 40.92 |  | 2023-01-18 | TRUE | 12 | TRUE
E11/K149/SK/dm/213 | HOTEL | 117a | 75845 | 78566 | Canopy Instalation Work | Roof | Cantilever (0 < 0.5m width) | 1 | 8 | 0.5 |  | 1 | m2-LxW | 4 | 2023-01-18 | 2023-02-13 | 100% | 100% | 100% | 3.8571 | 32.75 | 1.05 | 91.7 | 16.2 | 39.3 | 147.2 | 96.5 | 50.7 |  | 2023-01-18 | TRUE | 4 | TRUE
E11/K149/SK/dm/213 | HOTEL | 82d | 75846 |  | Canopy Instalation Work | Level 29 | Cantilever (0.5 > 1.2m width) | 1 | 4 | 1 |  | 1 | m2-LxW | 4 | 2023-01-18 |  | 100% | 100% | 0% | 5.5714 | 36.52 | 2.94 | 102.26 | 65.52 | 0 | 167.78 | 115.7 | 52.08 |  | 2023-01-18 | TRUE | 4 | TRUE
E11/K149/SK/dm/213 | HOTEL | 118 | 75847 |  | Edge Protection | Level 29 | Tripple Hnadrail | 1 | 20 |  | 1.5 | 1 | lm | 20 | 2023-01-18 |  | 100% | 100% | 0% | 5.5714 | 15 | 0.91 | 210 | 101.4 | 0 | 311.4 | 230.8 | 80.6 |  | 2023-01-18 | TRUE | 20 | TRUE
E11/K149/SK/dm/213 | HOTEL | 119 | 75848 | 80939 | Access Scaffold | Level 30 | Tower | 1 | 2.5 | 1.3 | 1.3 | 1 | rm | 1.3 | 2023-01-18 | 2023-01-31 | 100% | 100% | 100% | 2 | 63.34 | 7.28 | 57.64 | 18.93 | 24.7 | 101.27 | 68.46 | 32.81 |  | 2023-01-18 | TRUE | 1.3 | TRUE
E11/K149/SK/dm/213 | HOTEL | 119a | 75848 | 80939 | Access Scaffold | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 2 | 0.75 |  | 1 | m2-LxW | 1.5 | 2023-01-18 | 2023-01-31 | 100% | 100% | 100% | 2 | 36.52 | 2.94 | 38.35 | 8.82 | 16.43 | 63.6 | 43.39 | 20.21 |  | 2023-01-18 | TRUE | 1.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 82e | 75849 |  | EFIS Instalation Work | Level 29 | Additional Boarding | 2 | 22.5 | 1.8 |  | 2 | m2-LxW | 81 | 2023-01-18 |  | 100% | 100% | 0% | 5.5714 | 6.63 | 0.7 | 375.92 | 315.9 | 0 | 691.82 | 440.72 | 251.1 |  | 2023-01-18 | TRUE | 81 | TRUE
E11/K149/SK/dm/213 | HOTEL | 120 | 75850 |  | Electrical BOND MEP Work | Level 28 | Birdcage | 1 | 19.3 | 6 | 3.5 | 1 | m3 | 405.3 | 2023-01-19 |  | 100% | 100% | 0% | 5.4286 | 7.08 | 0.49 | 2008.67 | 1078.1 | 0 | 3086.77 | 2207.27 | 879.5 |  | 2023-01-19 | TRUE | 405.3 | TRUE
E11/K149/SK/SR/582 | HOTEL | 121&121a | 75901 | 78588 | Lift Shaft RC Slab Extention Work | Level 29 | Design 1399-39 | 1 | 2.5 | 1.3 | 5.5 | 1 | unit | 1 | 2023-01-19 | 2023-02-18 | 100% | 100% | 100% | 4.4286 | 4805.88 | 212.24 | 3364.12 | 939.92 | 1441.76 | 5745.8 | 3576.36 | 2169.44 | 2439-29-1 (Item-9) | 2023-01-19 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | HOTEL | 121b | 75902 | 78590 | Access Scaffold | Level 29 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 |  | 1 | m2-LxW | 1.5 | 2023-01-19 | 2023-02-18 | 100% | 100% | 100% | 4.4286 | 36.52 | 2.94 | 38.35 | 19.53 | 16.43 | 74.31 | 42.76 | 31.55 |  | 2023-01-19 | TRUE | 1.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 210 | 75856 | 80893 | Column Finishing Work | Ground Level | Birdcage | 1 | 5 | 3.8 | 12.2 | 1 | m3 | 231.8 | 2023-01-19 | 2023-01-21 | 100% | 100% | 100% | 0.42857 | 7.08 | 0.49 | 1148.8 | 48.68 | 492.34 | 1689.82 | 1689.82 | 0 |  | 2023-01-19 | TRUE | 231.8 | TRUE
E11/K149/SK/dm/213 | HOTEL | 210 | 75856 | 80893 | Column Finishing Work | Ground Level | Additional Boarding | 5 | 5 | 3.8 |  | 5 | m2-LxW | 95 | 2023-01-19 | 2023-01-21 | 100% | 100% | 100% | 0.42857 | 6.63 | 0.7 | 440.9 | 28.5 | 188.96 | 658.36 | 658.36 | 0 |  | 2023-01-19 | TRUE | 95 | TRUE
E11/K149/SK/dm/213 | HOTEL | 122 | 75905 | 80927 | KMEP Work BW-01036 | Level 5 | Tower | 1 | 2.5 | 1.3 | 2.5 | 1 | rm | 2.5 | 2023-01-20 | 2023-01-26 | 100% | 100% | 100% | 1 | 63.34 | 7.28 | 110.85 | 18.2 | 47.51 | 176.56 | 126.45 | 50.11 |  | 2023-01-20 | TRUE | 2.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 123 | 75906 |  | KMEP Work BW-01012 | Level 5 | Tower | 1 | 2.5 | 1.3 | 2.5 | 1 | rm | 2.5 | 2023-01-20 |  | 100% | 100% | 0% | 5.2857 | 63.34 | 7.28 | 110.85 | 96.2 | 0 | 207.05 | 126.45 | 80.6 |  | 2023-01-20 | TRUE | 2.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 123a | 75906 |  | KMEP Work BW-01012 | Level 5 | Cantilever (0.5 > 1.2m width) | 1 | 2.5 | 0.75 |  | 1 | m2-LxW | 1.88 | 2023-01-20 |  | 100% | 100% | 0% | 5.2857 | 36.52 | 2.94 | 48.06 | 29.22 | 0 | 77.28 | 52.8 | 24.48 |  | 2023-01-20 | TRUE | 1.88 | TRUE
E11/K149/SK/dm/213 | HOTEL | 124 | 75907 | 80928 | KMEP Work | Level 5 | Tower | 1 | 2.5 | 1.3 | 2 | 1 | rm | 2 | 2023-01-20 | 2023-01-26 | 100% | 100% | 100% | 1 | 63.34 | 7.28 | 88.68 | 14.56 | 38 | 141.24 | 101.16 | 40.08 |  | 2023-01-20 | TRUE | 2 | TRUE
E11/K149/SK/dm/213 | HOTEL | 125 | 75908 | 78552 | Wall Repair Work | Basement 1 | Tower | 1 | 1.8 | 1 | 0.5 | 1 | rm | 0.5 | 2023-01-20 | 2023-02-06 | 100% | 100% | 100% | 2.5714 | 63.34 | 7.28 | 22.17 | 9.36 | 9.5 | 41.03 | 25.29 | 15.74 |  | 2023-01-20 | TRUE | 0.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 126 | 75909 |  | Electrical BOND MEP Work | Level 28 | Tower | 1 | 2.5 | 1.3 | 3 | 1 | rm | 3 | 2023-01-20 |  | 100% | 100% | 0% | 5.2857 | 63.34 | 7.28 | 133.01 | 115.44 | 0 | 248.45 | 151.73 | 96.72 |  | 2023-01-20 | TRUE | 3 | TRUE
E11/K149/SK/dm/213 | HOTEL | 127 | 75910 |  | Edge Protection | Level 29 | Tripple Hnadrail | 1 | 20 |  | 1.5 |  | lm | 20 | 2023-01-20 |  | 100% | 100% | 0% | 5.2857 | 15 | 0.91 | 210 | 96.2 | 0 | 306.2 | 225.6 | 80.6 |  | 2023-01-20 | TRUE | 20 | TRUE
E11/K149/SK/SR/517 | HOTEL | 128&128a | 75911 | 80941 | Balcony Ceiling Work | Level 14 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2023-01-21 | 2023-01-31 | 100% | 100% | 100% | 1.5714 | 1772.5845 | 52.192 | 1240.81 | 82.02 | 531.78 | 1854.61 | 1278.09 | 576.52 | Tas Quote 2439-25-1 (item#5) | 2023-01-21 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | HOTEL | 129 | 75912 | 80936 | BW-0026 | Level 2 | Tower | 1 | 2.5 | 1.3 | 5 | 1 | rm | 5 | 2023-01-23 | 2023-01-30 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 221.69 | 41.6 | 95.01 | 358.3 | 237.29 | 121.01 |  | 2023-01-23 | TRUE | 5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 129 | 75912 | 80936 | KMEP Work | Level 2 | Additional Boarding | 1 | 2.5 | 1.3 |  | 1 | m2-LxW | 3.25 | 2023-01-23 | 2023-01-30 | 100% | 100% | 100% | 1.1429 | 6.63 | 0.7 | 15.08 | 2.6 | 6.46 | 24.14 | 16.06 | 8.08 |  | 2023-01-23 | TRUE | 3.25 | TRUE
E11/K149/SK/dm/213 | HOTEL | 129a | 75912 | 80936 | KMEP Work | Level 2 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1.3 |  | 1 | m2-LxW | 1.95 | 2023-01-23 | 2023-01-30 | 100% | 100% | 100% | 1.1429 | 36.52 | 2.94 | 49.85 | 6.55 | 21.36 | 77.76 | 52.31 | 25.45 |  | 2023-01-23 | TRUE | 1.95 | TRUE
E11/K149/SK/dm/213 | HOTEL | 130 | 75915 |  | Access Scaffold | Level 2 | Tower | 1 | 1.3 | 1.3 | 1.5 | 1 | rm | 1.5 | 2023-01-23 |  | 100% | 100% | 0% | 4.8571 | 63.34 | 7.28 | 66.51 | 53.04 | 0 | 119.55 | 71.19 | 48.36 |  | 2023-01-23 | TRUE | 1.5 | TRUE
E11/K149/SK/dm/213 | HOTEL | 131 | 75913 | 78554 | Wall Finishing Work | Ground Level | Independent | 1 | 5.9 | 0.9 | 2 | 1 | m2-LxH | 11.8 | 2023-01-23 | 2023-02-08 | 100% | 100% | 100% | 2.4286 | 12.01 | 0.49 | 99.2 | 14.04 | 42.52 | 155.76 | 101.68 | 54.08 |  | 2023-01-23 | TRUE | 11.8 | TRUE
E11/K149/SK/dm/213 | HOTEL | 131a | 75914 | 78554 | Wall Finishing Work | Level 1 | Independent | 1 | 6.8 | 0.9 | 2 | 1 | m2-LxH | 13.6 | 2023-01-23 | 2023-02-08 | 100% | 100% | 100% | 2.4286 | 12.01 | 0.49 | 114.34 | 16.18 | 49 | 179.52 | 117.2 | 62.32 |  | 2023-01-23 | TRUE | 13.6 | TRUE
E11/K149/SK/SR/517 | HOTEL | 132&132a | 75916 | 80942 | Balcony Ceiling Work | Level 19 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2023-01-24 | 2023-01-31 | 100% | 100% | 100% | 1.1429 | 1772.5845 | 52.192 | 1240.81 | 59.65 | 531.78 | 1832.24 | 1255.72 | 576.52 | Tas Quote 2439-25-1 (item#5) | 2023-01-24 | TRUE | 1 | TRUE
E11/K149/SK/dm/213 | HOTEL | 133 | 75917 | 80918 | Wall Concrete Work | Ground Level | Independent | 1 | 5 | 1.3 | 1.2 | 1 | m2-LxH | 6 | 2023-01-24 | 2023-01-25 | 100% | 100% | 100% | 0.28571 | 12.01 | 0.49 | 50.44 | 0.84 | 21.62 | 72.9 | 72.9 | 0 |  | 2023-01-24 | TRUE
E11/K149/SK/dm/213 | HOTEL | 134 | 75918 | 80919 | Wall Concrete Work | Ground Level | Tower | 1 | 1.8 | 1.8 | 1.5 | 1 | rm | 1.5 | 2023-01-24 | 2023-01-25 | 100% | 100% | 100% | 0.28571 | 63.34 | 7.28 | 66.51 | 3.12 | 28.5 | 98.13 | 98.13 | 0 |  | 2023-01-24 | TRUE
E11/K149/SK/SR/585 | AL QUOZ METAL YARD | 1 | 75851 |  | KMEP Pipe Storage | Ground Level | Frame | 1 | 5.2 | 3.9 | 2 |  | unit | 1 | 2023-01-06 |  | 100% | 100% |  | 7.2857 | 1820.72 | 95.83 | 1274.5 | 698.19 | 0 | 0 | 0 | 0 | Tas Quot 2671-1-1 (Item-1) | 2023-01-06 | TRUE
E11/K149/SK/SR/585 | AL QUOZ METAL YARD | 2 | 75852 |  | KMEP Pipe Storage | Ground Level | Frame | 1 | 5.2 | 3.9 | 2 |  | unit | 1 | 2023-01-06 |  | 100% | 100% |  | 7.2857 | 1820.72 | 95.83 | 1274.5 | 698.19 | 0 | 0 | 0 | 0 | Tas Quot 2671-1-1 (Item-1) | 2023-01-06 | TRUE
E11/K149/SK/dm/213 | RESIDENCE | 215a | 75878 | 78629 | Wall Board Fixing Work | Ground Level | Additional Boarding | 1 | 1.8 | 1.3 |  | 1 | m2-LxW | 2.34 | 2023-01-26 | 2023-02-06 | 100% | 100% | 100% | 1.7143 | 6.63 | 0.7 | 10.86 | 2.81 | 4.65 | 18.32 |  | 18.32
E11/K149/SK/dm/213 | RESIDENCE | 214a | 75879 | 78628 | Wall Board Fixing Work | Ground Level | Additional Boarding | 1 | 2.5 | 1.3 |  | 1 | m2-LxW | 3.25 | 2023-01-26 | 2023-02-06 | 100% | 100% | 100% | 1.7143 | 6.63 | 0.7 | 15.08 | 3.9 | 6.46 | 25.44 |  | 25.44
E11/K149/SK/dm/213 | RESIDENCE | 219a | 75880 | 78636 | Staircase - 3 Wall Finishing Work | Level 3 | Independent | 1 | 6.8 | 0.9 | 2 | 1 | m2-LxH | 13.6 | 2023-01-26 | 2023-02-04 | 100% | 100% | 100% | 1.4286 | 12.01 | 0.49 | 114.34 | 9.52 | 49 | 172.86 |  | 172.86
E11/K149/SK/dm/213 | RESIDENCE | 222 | 75881 |  | Concrete Cutting Work | Level 28 | Tower | 1 | 1.3 | 1 | 2.5 | 1 | rm | 2.5 | 2023-01-26 |  | 100% | 100% |  | 4.4286 | 63.34 | 7.28 | 110.85 | 80.6 | 0 | 191.45 |  | 191.45
E11/K149/SK/dm/213 | RESIDENCE | 222a | 75881 |  | Concrete Cutting Work | Level 28 | Cantilever (0 < 0.5m width) | 1 | 3 | 0.5 |  | 1 | m2-LxW | 1.5 | 2023-01-26 |  | 100% | 100% |  | 4.4286 | 32.75 | 1.05 | 34.39 | 6.98 | 0 | 41.37 |  | 41.37
E11/K149/SK/dm/213 | RESIDENCE | 223 | 75882 | 82152 | Repairing Led Light | Ground Level | Independent 1.8m wide | 1 | 3.8 | 1.8 | 3 | 1 | m2-LxH | 11.4 | 2023-01-26 | 2023-02-09 | 100% | 100% | 100% | 2.1429 | 16.76 | 0.77 | 133.74 | 18.81 | 57.32 | 209.87 |  | 209.87
E11/K149/SK/dm/213 | RESIDENCE | 223a | 75882 | 82152 | Repairing Led Light | Ground Level | Cantilever (0 < 0.5m width) | 1 | 5 | 0.25 |  | 1 | m2-LxW | 1.25 | 2023-01-26 | 2023-02-09 | 100% | 100% | 100% | 2.1429 | 32.75 | 1.05 | 28.66 | 2.81 | 12.28 | 43.75 |  | 43.75
E11/K149/SK/dm/213 | RESIDENCE | 223b | 75883 | 82153 | Repairing Led Light | Ground Level | Independent | 1 | 5 | 1.3 | 3 | 1 | m2-LxH | 15 | 2023-01-26 | 2023-02-09 | 100% | 100% | 100% | 2.1429 | 12.01 | 0.49 | 126.11 | 15.75 | 54.05 | 195.91 |  | 195.91
E11/K149/SK/dm/213 | RESIDENCE | 223c | 75883 | 82153 | Repairing Led Light | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 2 | 1 |  | 1 | m2-LxW | 2 | 2023-01-26 | 2023-02-09 | 100% | 100% | 100% | 2.1429 | 36.52 | 2.94 | 51.13 | 12.6 | 21.91 | 85.64 |  | 85.64
E11/K149/SK/dm/213 | RESIDENCE | 224 | 75884 | 82154 | Repairing Led Light | Ground Level | Independent 1.8m wide | 1 | 10 | 1.8 | 3 | 1 | m2-LxH | 30 | 2023-01-26 | 2023-02-09 | 100% | 100% | 100% | 2.1429 | 16.76 | 0.77 | 351.96 | 49.5 | 150.84 | 552.3 |  | 552.3
E11/K149/SK/dm/213 | RESIDENCE | 224a | 75884 | 82154 | Repairing Led Light | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 6 | 1 |  | 1 | m2-LxW | 6 | 2023-01-26 | 2023-02-09 | 100% | 100% | 100% | 2.1429 | 36.52 | 2.94 | 153.38 | 37.8 | 65.74 | 256.92 |  | 256.92
E11/K149/SK/dm/213 | RESIDENCE | 225 | 75885 | 78640 | BTU Meter Wire Pulling Work | Ground Level | Tower | 1 | 2.5 | 1.3 | 3.5 | 1 | rm | 3.5 | 2023-01-27 | 2023-02-07 | 100% | 100% | 100% | 1.7143 | 63.34 | 7.28 | 155.18 | 43.68 | 66.51 | 265.37 |  | 265.37
E11/K149/SK/dm/213 | RESIDENCE | 226 | 75886 | 78641 | BTU Meter Wire Pulling Work | Ground Level | Tower | 1 | 2.5 | 1.8 | 3.5 | 1 | rm | 3.5 | 2023-01-27 | 2023-02-07 | 100% | 100% | 100% | 1.7143 | 63.34 | 7.28 | 155.18 | 43.68 | 66.51 | 265.37 |  | 265.37
E11/K149/SK/dm/213 | RESIDENCE | 227 | 75887 |  | Neae Lift Loby Shaft Wall Partition | Ground Level | Tower | 1 | 1.3 | 0.6 | 4 | 2 | rm | 4 | 2023-01-27 |  | 100% | 100% | 0% | 4.2857 | 63.34 | 7.28 | 177.35 | 124.8 | 0 | 302.15 |  | 302.15
E11/K149/SK/dm/213 | RESIDENCE | 228 | 75888 | 82179 | Balcony For Mast Climber Access | Level 23 | Independent | 1 | 3.2 | 1.3 | 2 | 1 | m2-LxH | 6.4 | 2023-01-28 | 2023-02-24 | 100% | 100% | 100% | 4 | 12.01 | 0.49 | 53.8 | 12.54 | 23.06 | 89.4 |  | 89.4
E11/K149/SK/dm/213 | RESIDENCE | 8a3 | 75889 |  | Hotel Side Glass Work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 17 | 0.75 |  | 1 | m2-LxW | 12.75 | 2023-01-28 |  | 100% | 100% | 0% | 4.1429 | 36.52 | 2.94 | 325.94 | 155.3 | 0 | 481.24 |  | 481.24
E11/K149/SK/dm/213 | RESIDENCE | 1x | 75890 |  | Canal Side Glass Fixing Work | Level 31 | Cantilever (0 < 0.5m width) | 1 | 15 | 0.5 |  | 1 | m2-LxW | 7.5 | 2023-01-28 |  | 100% | 100% | 0% | 4.1429 | 32.75 | 1.05 | 171.94 | 32.63 | 0 | 204.57 |  | 204.57
E11/K149/SK/dm/213 | RESIDENCE | 229 | 75891 | 82167 | EIFS Work | Level 23 | Independent | 1 | 6.3 | 1.3 | 3.5 | 1 | m2-LxH | 22.05 | 2023-01-28 | 2023-02-18 | 100% | 100% | 100% | 3.1429 | 12.01 | 0.49 | 185.37 | 33.96 | 79.45 | 298.78 |  | 298.78
E11/K149/SK/dm/213 | RESIDENCE | 229 | 75891 | 82167 | EIFS Work | Level 23 | Additional Boarding | 1 | 6.3 | 1.3 |  | 1 | m2-LxW | 8.19 | 2023-01-28 | 2023-02-18 | 100% | 100% | 100% | 3.1429 | 6.63 | 0.7 | 38.01 | 18.02 | 16.29 | 72.32 |  | 72.32
E11/K149/SK/dm/213 | RESIDENCE | 229a | 75892 | 82168 | EIFS Work | Level 23 | Independent | 1 | 7.5 | 1.3 | 2 | 1 | m2-LxH | 15 | 2023-01-28 | 2023-02-18 | 100% | 100% | 100% | 3.1429 | 12.01 | 0.49 | 126.11 | 23.1 | 54.05 | 203.26 |  | 203.26
E11/K149/SK/dm/213 | RESIDENCE | 229b | 75892 | 82168 | EIFS Work | Level 23 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 |  | 1 | m2-LxW | 1.5 | 2023-01-28 | 2023-02-18 | 100% | 100% | 100% | 3.1429 | 36.52 | 2.94 | 38.35 | 13.86 | 16.43 | 68.64 |  | 68.64
E11/K149/SK/dm/213 | RESIDENCE | 230 | 75893 |  | Shaft For Wall Partition | Level 2 | Tower | 1 | 1 | 0.6 | 2 | 1 | rm | 2 | 2023-01-30 |  | 100% | 100% | 0% | 3.8571 | 63.34 | 7.28 | 88.68 | 56.16 | 0 | 144.84 |  | 144.84
E11/K149/SK/dm/213 | RESIDENCE | 231 | 75894 | 82155 | Shaft For Wall Partition | Level 3 | Tower | 1 | 1.3 | 0.6 | 2 | 1 | rm | 2 | 2023-01-30 | 2023-02-09 | 100% | 100% | 100% | 1.5714 | 63.34 | 7.28 | 88.68 | 22.88 | 38 | 149.56 |  | 149.56
E11/K149/SK/dm/213 | RESIDENCE | 232 | 75895 |  | Shaft For Wall Partition | Level 4 | Tower | 1 | 1 | 0.6 | 2 | 1 | rm | 2 | 2023-01-30 |  | 100% | 100% | 0% | 3.8571 | 63.34 | 7.28 | 88.68 | 56.16 | 0 | 144.84 |  | 144.84
E11/K149/SK/dm/213 | RESIDENCE | 233 | 75896 |  | Shaft For Wall Partition | Level 5 | Tower | 1 | 1 | 0.6 | 2 | 1 | rm | 2 | 2023-01-30 |  | 100% | 100% | 0% | 3.8571 | 63.34 | 7.28 | 88.68 | 56.16 | 0 | 144.84 |  | 144.84
E11/K149/SK/dm/213 | RESIDENCE | 1y | 75897 |  | GRC Panel Work | Level 31 | Single Handrail | 1 | 136 |  | 1 |  | lm | 136 | 2023-01-28 |  | 100% | 100% | 0% | 4.1429 | 7 | 0.42 | 666.4 | 236.64 | 0 | 903.04 |  | 903.04
E11/K149/SK/dm/213 | RESIDENCE | 202e | 76901 |  | GRC Panel Work | Level 10 | Independent | 1 | 9 | 1.3 | 1 | 1 | m2-LxH | 9 | 2023-02-01 |  | 100% | 100% | 0% | 3.5714 | 12.01 | 0.49 | 75.66 | 15.75 | 0 | 91.41 |  | 91.41
E11/K149/SK/dm/213 | RESIDENCE | 178b | 76902 | 82156 | Shaft 9 For Kmep Work | Level 4 to 5 | Tower | 1 | 2 | 2 | 7.5 | 1 | rm | 7.5 | 2023-02-02 | 2023-02-09 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 332.54 | 62.4 | 142.52 | 537.46 |  | 537.46
E11/K149/SK/dm/213 | RESIDENCE | 178b | 76902 | 82156 | Shaft 9 For Kmep Work | Level 4 to 5 | Additional Boarding | 2 | 2 | 2 |  | 2 | m2-LxW | 8 | 2023-02-02 | 2023-02-09 | 100% | 100% | 100% | 1.1429 | 6.63 | 0.7 | 37.13 | 6.4 | 15.91 | 59.44 |  | 59.44
E11/K149/MS/DM/647 | RESIDENCE | 234 | 76903 |  | Glass Panel Fixing Work | Level 30 to 32 | Design 1399-37a | 1 |  |  |  |  | unit | 1 | 2023-02-02 |  | 100% | 100% | 0% | 3.4286 | 7648.53 | 125.44 | 5353.97 | 430.08 | 0 | 5784.05 |  | 5784.05 | Tas Quote 2439-28-1
E11/K149/SK/dm/213 | RESIDENCE | 235 | 76904 |  | KMEP Work | Level 2 | Independent | 1 | 3 | 0.75 | 2.3 | 1 | m2-LxH | 6.9 | 2023-02-02 |  | 100% | 100% | 0% | 3.4286 | 12.01 | 0.49 | 58.01 | 11.59 | 0 | 69.6 |  | 69.6
E11/K149/SK/dm/213 | RESIDENCE | 235a | 76904 |  | KMEP Work | Level 2 | Cantilever (0.5 > 1.2m width) | 1 | 1 | 1 |  | 1 | m2-LxW | 1 | 2023-02-02 |  | 100% | 100% | 0% | 3.4286 | 36.52 | 2.94 | 25.56 | 10.08 | 0 | 35.64 |  | 35.64
E11/K149/SK/dm/213 | RESIDENCE | 236 | 76905 | 82171 | Entrance Area Access | Ground Level | Independent | 1 | 5.4 | 1.3 | 1 | 1 | m2-LxH | 5.4 | 2023-02-06 | 2023-02-21 | 100% | 100% | 100% | 2.2857 | 12.01 | 0.49 | 45.4 | 6.05 | 19.46 | 70.91 |  | 70.91
E11/K149/SK/dm/213 | RESIDENCE | 237 | 76906 | 78642 | Wall Concrete Work | Ground Level | Independent | 1 | 15.5 | 1 | 1.5 | 1 | m2-LxH | 23.25 | 2023-02-06 | 2023-02-07 | 100% | 100% | 100% | 0.28571 | 12.01 | 0.49 | 195.46 | 3.26 | 83.77 | 282.49 |  | 282.49
E11/K149/SK/dm/213 | RESIDENCE | 224b | 76908 | 82157 | Lift Lobby Led Light Repairing | Ground Level | Tower | 1 | 2.5 | 1.8 | 2.5 | 1 | rm | 2.5 | 2023-02-07 | 2023-02-09 | 100% | 100% | 100% | 0.42857 | 63.34 | 7.28 | 110.85 | 7.8 | 47.51 | 166.16 |  | 166.16
E11/K149/SK/dm/213 | RESIDENCE | 238 | 76910 | 82158 | Wall Board Fixing Work | Ground Level | Independent | 1 | 5 | 1.3 | 3.5 | 1 | m2-LxH | 17.5 | 2023-02-07 | 2023-02-13 | 100% | 100% | 100% | 1 | 12.01 | 0.49 | 147.12 | 8.58 | 63.05 | 218.75 |  | 218.75
E11/K149/SK/dm/213 | RESIDENCE | 238 | 76910 | 82158 | Wall Board Fixing Work | Ground Level | Additional Boarding | 1 | 5 | 1.3 | 1 | 1 | m2-LxW | 6.5 | 2023-02-07 | 2023-02-13 | 100% | 100% | 100% | 1 | 6.63 | 0.7 | 30.17 | 4.55 | 12.93 | 47.65 |  | 47.65
E11/K149/SK/dm/213 | RESIDENCE | 3g | 76914 |  | Canopy Instalation Work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 2.75 | 1 |  | 1 | m2-LxW | 2.75 | 2023-02-02 |  | 100% | 100% | 0% | 3.4286 | 36.52 | 2.94 | 70.3 | 27.72 | 0 | 98.02 |  | 98.02
E11/K149/SK/dm/213 | RESIDENCE | 188b | 76911 |  | KMEP | Level 2 | Birdcage | 1 | 4.5 | 3.6 | 2.5 | 1 | m3 | 40.5 | 2023-02-07 |  | 100% | 100% | 0% | 2.7143 | 7.08 | 0.49 | 200.72 | 53.87 | 0 | 254.59 |  | 254.59
E11/K149/SK/dm/213 | RESIDENCE | 188c | 76912 |  | KMEP | Level 2 | Birdcage | 1 | 5 | 3 | 2.5 | 1 | m3 | 37.5 | 2023-02-07 |  | 100% | 100% | 0% | 2.7143 | 7.08 | 0.49 | 185.85 | 49.88 | 0 | 235.73 |  | 235.73
E11/K149/SK/dm/213 | RESIDENCE | 188d | 76913 |  | KMEP | Level 2 | Birdcage | 1 | 6 | 3.1 | 2.5 | 1 | m3 | 46.5 | 2023-02-07 |  | 100% | 100% | 0% | 2.7143 | 7.08 | 0.49 | 230.45 | 61.85 | 0 | 292.3 |  | 292.3
E11/K149/SK/dm/213 | RESIDENCE | 195h | 76915 |  | KMEP | Level 2 | Independent 1.8m wide | 1 | 3 | 2 | 2.5 | 1 | m2-LxH | 7.5 | 2023-02-08 |  | 100% | 100% | 0% | 2.5714 | 16.76 | 0.77 | 87.99 | 14.85 | 0 | 102.84 |  | 102.84
E11/K149/SK/dm/213 | RESIDENCE | 8a4 | 76916 |  | Glass Work |  | Additional Boarding | 6 | 10.8 | 1.8 |  | 1 | m2-LxW | 116.64 | 2023-02-08 |  | 100% | 100% | 0% | 2.5714 | 6.63 | 0.7 | 541.33 | 209.95 | 0 | 751.28 |  | 751.28
E11/K149/SK/dm/213 | RESIDENCE | 8a5 | 76917 |  | Glass Work | Level 28 to 29 | Cantilever (0 < 0.5m width) | 1 | 16.2 | 0.5 |  | 1 | m2-LxW | 8.1 | 2023-02-08 |  | 100% | 100% | 0% | 2.5714 | 32.75 | 1.05 | 185.69 | 21.87 | 0 | 207.56 |  | 207.56
E11/K149/SK/dm/213 | RESIDENCE | 239 | 76918 |  | KMEP Work | Ground Level | Tower | 1 | 1.3 | 0.9 | 3 | 1 | rm | 3 | 2023-02-09 |  | 100% | 100% | 0% | 2.4286 | 63.34 | 7.28 | 133.01 | 53.04 | 0 | 186.05 |  | 186.05
E11/K149/SK/dm/213 | RESIDENCE | 238a | 76919 | 82159 | Entrance Area Partition Board Fixing | Ground Level | Tower | 1 | 1.8 | 1.3 | 3 | 2 | rm | 3 | 2023-02-09 | 2023-02-13 | 100% | 100% | 100% | 0.71429 | 63.34 | 7.28 | 133.01 | 15.6 | 57.01 | 205.62 |  | 205.62
E11/K149/SK/dm/213 | RESIDENCE | 240 | 76920 | 82173 | Wall Finishing Work | Level 4 to 5 | Independent | 1 | 5 | 0.9 | 2 | 1 | m2-LxH | 10 | 2023-02-10 | 2023-02-22 | 100% | 100% | 100% | 1.8571 | 12.01 | 0.49 | 84.07 | 9.1 | 36.03 | 129.2 |  | 129.2
E11/K149/SK/dm/213 | RESIDENCE | 240a | 76920 | 82174 | Wall Finishing Work | Level 4 to 5 | Independent | 1 | 6 | 0.9 | 2 | 1 | m2-LxH | 12 | 2023-02-10 | 2023-02-22 | 100% | 100% | 100% | 1.8571 | 12.01 | 0.49 | 100.88 | 10.92 | 43.24 | 155.04 |  | 155.04
E11/K149/SK/dm/213 | RESIDENCE | 240b | 76921 | 82175 | Wall Finishing Work | Level 5 to 6 | Independent | 1 | 6.8 | 0.9 | 1.5 | 1 | m2-LxH | 10.2 | 2023-02-10 | 2023-02-22 | 100% | 100% | 100% | 1.8571 | 12.01 | 0.49 | 85.75 | 9.28 | 36.75 | 131.78 |  | 131.78
E11/K149/SK/dm/213 | RESIDENCE | 240c | 76921 | 82176 | Wall Finishing Work | Level 5 to 6 | Independent | 1 | 6 | 0.9 | 1.5 | 1 | m2-LxH | 9 | 2023-02-10 | 2023-02-22 | 100% | 100% | 100% | 1.8571 | 12.01 | 0.49 | 75.66 | 8.19 | 32.43 | 116.28 |  | 116.28
E11/K149/SK/dm/213 | RESIDENCE | 240d | 76922 | 82177 | Wall Finishing Work | Level 5 to 6 | Independent | 1 | 6.8 | 0.9 | 1.5 | 1 | m2-LxH | 10.2 | 2023-02-10 | 2023-02-22 | 100% | 100% | 100% | 1.8571 | 12.01 | 0.49 | 85.75 | 9.28 | 36.75 | 131.78 |  | 131.78
E11/K149/SK/dm/213 | RESIDENCE | 240e | 76922 | 82178 | Wall Finishing Work | Level 5 to 6 | Independent | 1 | 6 | 0.9 | 1.5 | 1 | m2-LxH | 9 | 2023-02-10 | 2023-02-22 | 100% | 100% | 100% | 1.8571 | 12.01 | 0.49 | 75.66 | 8.19 | 32.43 | 116.28 |  | 116.28
E11/K149/SK/dm/213 | RESIDENCE | 229c | 76923 | 82169 | Canal Side Wall Painting Work | Level 23 | Tower | 1 | 1.3 | 1.3 | 3.5 | 2 | rm | 3.5 | 2023-02-10 | 2023-02-18 | 100% | 100% | 100% | 1.2857 | 12.01 | 0.49 | 29.42 | 2.21 | 12.61 | 44.24 |  | 44.24
E11/K149/SK/dm/213 | RESIDENCE | 241 | 76924 |  | Ceiling Work | Ground Level | Independent | 1 | 32.5 | 1.3 | 4.2 | 1 | m2-LxH | 136.5 | 2023-02-11 |  | 100% | 100% | 0% | 2.1429 | 12.01 | 0.49 | 1147.56 | 143.33 | 0 | 1290.89 |  | 1290.89
E11/K149/SK/dm/213 | RESIDENCE | 241a | 76924 |  | Ceiling Work | Ground Level | Tower | 1 | 2.5 | 1.3 | 2.2 | 1 | rm | 2.2 | 2023-02-11 |  | 100% | 100% | 0% | 2.1429 | 63.34 | 7.28 | 97.54 | 34.32 | 0 | 131.86 |  | 131.86
E11/K149/SK/dm/213 | RESIDENCE | 180b | 76925 |  | KMEP Work | Level 2 | Cantilever (0.5 > 1.2m width) | 1 | 2.5 | 1.5 |  | 1 | m2-LxW | 3.75 | 2023-02-11 |  | 100% | 100% | 0% | 2.1429 | 36.52 | 2.94 | 95.87 | 23.63 | 0 | 119.5 |  | 119.5
E11/K149/SK/dm/213 | RESIDENCE | 242 | 76931 | 82160 | Lift Lobby For Block Work | Ground Level | Independent | 1 | 3.1 | 1.8 | 3 | 1 | m2-LxH | 9.3 | 2023-02-13 | 2023-02-15 | 100% | 100% | 100% | 0.42857 | 16.76 | 0.77 | 109.11 | 3.07 | 46.76 | 158.94 |  | 158.94
E11/K149/SK/dm/213 | RESIDENCE | 242a | 76931 | 82160 | Lift Lobby For Block Work | Ground Level | Additional Boarding | 1 | 2.8 | 1.3 |  | 1 | m2-LxW | 3.64 | 2023-02-13 | 2023-02-15 | 100% | 100% | 100% | 0.42857 | 6.63 | 0.7 | 16.89 | 1.09 | 7.24 | 25.22 |  | 25.22
E11/K149/SK/dm/213 | RESIDENCE | 243 | 76927 | 82164 | Staircase 3 Wall Painting Work | Level 27 | Independent | 1 | 3.3 | 1 | 2 | 1 | m2-LxH | 6.6 | 2023-02-13 | 2023-02-16 | 100% | 100% | 100% | 0.57143 | 12.01 | 0.49 | 55.49 | 1.85 | 23.78 | 81.12 |  | 81.12
E11/K149/SK/dm/213 | RESIDENCE | 244 | 76928 | 82165 | Staircase 3 Wall Painting Work | Level 26 | Independent | 1 | 3.5 | 1 | 2 | 2 | m2-LxH | 7 | 2023-02-13 | 2023-02-16 | 100% | 100% | 100% | 0.57143 | 12.01 | 0.49 | 58.85 | 1.96 | 25.22 | 86.03 |  | 86.03
E11/K149/SK/dm/213 | RESIDENCE | 245 | 76929 | 82166 | Staircase 3 Wall Painting Work | Level 28 | Independent | 1 | 3.3 | 1 | 2 | 1 | m2-LxH | 6.6 | 2023-02-14 | 2023-02-16 | 100% | 100% | 100% | 0.42857 | 12.01 | 0.49 | 55.49 | 1.39 | 23.78 | 80.66 |  | 80.66
E11/K149/SK/dm/213 | RESIDENCE | 246 | 76930 |  | Planter Area Shaft For MEP Work | Ground Level | Tower | 1 | 1.3 | 0.6 | 4 | 2 | rm | 4 | 2023-02-14 |  | 100% | 100% | 0% | 1.7143 | 63.34 | 7.28 | 177.35 | 49.92 | 0 | 227.27 |  | 227.27
E11/K149/SK/dm/213 | RESIDENCE | 247 | 76932 |  | Edge Protection | Level 7 to 31 | Double Handrail | 1 | 24 |  | 1 |  | lm | 24 | 2023-02-14 |  | 100% | 100% | 0% | 1.7143 | 15 | 0.91 | 252 | 37.44 | 0 | 289.44 |  | 289.44
E11/K149/SK/dm/213 | RESIDENCE | 221b | 76933 |  | EIFS Work | Level 31 | Additional Boarding | 2 | 1.3 | 1.2 |  | 1 | m2-LxW | 3.12 | 2023-02-14 |  | 100% | 100% | 0% | 1.7143 | 6.63 | 0.7 | 14.48 | 3.74 | 0 | 18.22 |  | 18.22
E11/K149/SK/dm/213 | RESIDENCE | 145a | 76934 |  | EIFS Work | Level 31 | Additional Boarding | 1 | 2.5 | 1.5 |  | 1 | m2-LxW | 3.75 | 2023-02-14 |  | 100% | 100% | 0% | 1.7143 | 6.63 | 0.7 | 17.4 | 4.5 | 0 | 21.9 |  | 21.9
E11/K149/SK/dm/213 | RESIDENCE | 145b | 76934 |  | EIFS Work | Level 31 | Additional Boarding | 1 | 1.5 | 1 |  | 1 | m2-LxW | 1.5 | 2023-02-14 |  | 100% | 100% | 0% | 1.7143 | 6.63 | 0.7 | 6.96 | 1.8 | 0 | 8.76 |  | 8.76
E11/K149/SK/dm/213 | RESIDENCE | 248 | 76935 |  | Telicom Room KMEP Work | Level 2 | Tower | 1 | 1.8 | 1.8 | 2.2 | 1 | rm | 2.2 | 2023-02-14 |  | 100% | 100% | 0% | 1.7143 | 63.34 | 7.28 | 97.54 | 27.46 | 0 | 125 |  | 125
E11/K149/SK/dm/213 | RESIDENCE | 248a | 76935 |  | Telicom Room KMEP Work | Level 2 | Cantilever (0 < 0.5m width) | 1 | 1.8 | 0.5 |  | 1 | m2-LxW | 0.9 | 2023-02-14 |  | 100% | 100% | 0% | 1.7143 | 32.75 | 1.05 | 20.63 | 1.62 | 0 | 22.25 |  | 22.25
E11/K149/SK/dm/213 | RESIDENCE | 249 | 76936 |  | Telicom Room KMEP Work | Level 5 | Tower | 1 | 1.8 | 1.8 | 4.5 | 2 | rm | 4.5 | 2023-02-15 |  | 100% | 100% | 0% | 1.5714 | 63.34 | 7.28 | 199.52 | 51.48 | 0 | 251 |  | 251
E11/K149/SK/dm/213 | RESIDENCE | 249a | 76936 |  | Telicom Room KMEP Work | Level 5 | Cantilever (0 < 0.5m width) | 2 | 1.8 | 0.5 |  | 2 | m2-LxW | 1.8 | 2023-02-15 |  | 100% | 100% | 0% | 1.5714 | 32.75 | 1.05 | 41.27 | 2.97 | 0 | 44.24 |  | 44.24
E11/K149/SK/dm/213 | RESIDENCE | 250 | 76937 | 82163 | Telicom Room KMEP Work | Level 2 | Tower | 1 | 1 | 1 | 2 | 1 | rm | 2 | 2023-02-15 | 2023-02-17 | 100% | 100% | 100% | 0.42857 | 63.34 | 7.28 | 88.68 | 6.24 | 38 | 132.92 |  | 132.92
E11/K149/SK/dm/213 | RESIDENCE | 251 | 76938 | 82170 | Block Work | Ground Level | Tower | 1 | 1.3 | 1.3 | 4 | 2 | rm | 4 | 2023-02-16 | 2023-02-20 | 100% | 100% | 100% | 0.71429 | 63.34 | 7.28 | 177.35 | 20.8 | 76.01 | 274.16 |  | 274.16
E11/K149/SK/dm/213 | RESIDENCE | 8a6 | 76939 |  | Glass Work | Level 27 | Cantilever (0 < 0.5m width) | 2 | 9.5 | 0.5 |  | 2 | m2-LxW | 9.5 | 2023-02-16 |  | 100% | 100% | 0% | 1.4286 | 32.75 | 1.05 | 217.79 | 14.25 | 0 | 232.04 |  | 232.04
E11/K149/SK/dm/213 | RESIDENCE | 252 | 76940 |  | Wall Finishing Work | Basement 1 | Independent | 1 | 6.3 | 0.9 | 4 | 1 | m2-LxH | 25.2 | 2023-02-17 |  | 100% | 100% | 0% | 1.2857 | 12.01 | 0.49 | 211.86 | 15.88 | 0 | 227.74 |  | 227.74
E11/K149/SK/dm/213 | RESIDENCE | 252 | 76940 |  | Wall Finishing Work | Basement 1 | Additional Boarding | 1 | 6.3 | 0.9 |  | 1 | m2-LxW | 5.67 | 2023-02-17 |  | 100% | 100% | 0% | 1.2857 | 6.63 | 0.7 | 26.31 | 5.1 | 0 | 31.41 |  | 31.41
E11/K149/SK/dm/213 | RESIDENCE | 252a | 76940 |  | Wall Finishing Work | Basement 1 | Additional Boarding | 1 | 2.5 | 0.9 |  | 1 | m2-LxW | 2.25 | 2023-02-17 |  | 100% | 100% | 0% | 1.2857 | 6.63 | 0.7 | 10.44 | 2.03 | 0 | 12.47 |  | 12.47
E11/K149/SK/dm/213 | RESIDENCE | 253 | 76941 |  | Ceiling Work (BW-1148) | Level 5 | Tower | 1 | 2.5 | 1.3 | 4 | 2 | rm | 4 | 2023-02-18 |  | 100% | 100% | 0% | 1.1429 | 63.34 | 7.28 | 177.35 | 33.28 | 0 | 210.63 |  | 210.63
E11/K149/SK/dm/213 | RESIDENCE | 253a | 76942 |  | Ceiling Work (BW-1148) | Level 5 | Tower | 1 | 1.8 | 1.8 | 4 | 1 | rm | 4 | 2023-02-18 |  | 100% | 100% | 0% | 1.1429 | 63.34 | 7.28 | 177.35 | 33.28 | 0 | 210.63 |  | 210.63
E11/K149/SK/dm/213 | RESIDENCE | 253b | 76942 |  | Ceiling Work (BW-1148) | Level 5 | Cantilever (0.5 > 1.2m width) | 1 | 1.8 | 0.75 |  | 1 | m2-LxW | 1.35 | 2023-02-18 |  | 100% | 100% | 0% | 1.1429 | 36.52 | 2.94 | 34.51 | 4.54 | 0 | 39.05 |  | 39.05
E11/K149/SK/dm/213 | RESIDENCE | 8a7 | 76943 |  | Glass Work | Level 26 | Additional Boarding | 2 | 4.6 | 0.75 |  | 2 | m2-LxW | 6.9 | 2023-02-18 |  | 100% | 100% | 0% | 1.1429 | 6.63 | 0.7 | 32.02 | 5.52 | 0 | 37.54 |  | 37.54
E11/K149/SK/dm/213 | RESIDENCE | 252b | 76944 |  | Stair 1 For Wall Finishing Work | Basement 1 | Independent | 1 | 6.3 | 0.9 | 1.5 | 1 | m2-LxH | 9.45 | 2023-02-18 |  | 100% | 100% | 0% | 1.1429 | 12.01 | 0.49 | 79.45 | 5.29 | 0 | 84.74 |  | 84.74
E11/K149/SK/dm/213 | RESIDENCE | 252c | 76944 |  | Stair 1 For Wall Finishing Work | Basement 2 | Additional Boarding | 1 | 3.8 | 0.9 |  | 1 | m2-LxW | 3.42 | 2023-02-18 |  | 100% | 100% | 0% | 1.1429 | 6.63 | 0.7 | 15.87 | 2.74 | 0 | 18.61 |  | 18.61
E11/K149/SK/dm/213 | RESIDENCE | 8a8 | 76945 |  | Glass Work | Level 29 | Cantilever (0.5 > 1.2m width) | 1 | 7.2 | 0.75 |  | 1 | m2-LxW | 5.4 | 2023-02-18 |  | 100% | 100% | 0% | 1.1429 | 36.52 | 2.94 | 138.05 | 18.14 | 0 | 156.19 |  | 156.19
E11/K149/SK/dm/213 | RESIDENCE | 8a9 | 76946 |  | Glass Work | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 5.4 | 0.75 |  | 1 | m2-LxW | 4.05 | 2023-02-18 |  | 100% | 100% | 0% | 1.1429 | 36.52 | 2.94 | 103.53 | 13.61 | 0 | 117.14 |  | 117.14
E11/K149/SK/dm/213 | RESIDENCE | 8a10 | 76947 |  | Glass Work | Level 27 | Additional Boarding | 1 | 1.8 | 1.8 |  | 1 | m2-LxW | 3.24 | 2023-02-20 |  | 100% | 100% | 0% | 0.85714 | 6.63 | 0.7 | 15.04 | 1.94 | 0 | 16.98 |  | 16.98
E11/K149/SK/dm/213 | RESIDENCE | 254 | 76948 |  | Glass Work | Level 26 | Independent | 1 | 8.5 | 1 | 2 | 1 | m2-LxH | 17 | 2023-02-21 |  | 100% | 100% | 0% | 0.71429 | 12.01 | 0.49 | 142.92 | 5.95 | 0 | 148.87 |  | 148.87
E11/K149/SK/dm/213 | RESIDENCE | 255 | 76949 |  |  | Ground Level | Independent | 1 | 5.4 | 1.3 | 1 | 1 | m2-LxH | 5.4 | 2023-02-22 |  | 100% | 100% | 0% | 0.57143 | 12.01 | 0.49 | 45.4 | 1.51 | 0 | 46.91 |  | 46.91
E11/K149/SK/dm/213 | RESIDENCE | 256 | 76950 |  | Signage Removing Work | Level 23 | Independent | 1 | 18.8 | 1.3 | 2.2 | 1 | m2-LxH | 41.36 | 2023-02-22 |  | 100% | 100% | 0% | 0.57143 | 12.01 | 0.49 | 347.71 | 11.58 | 0 | 359.29 |  | 359.29
E11/K149/SK/dm/213 | RESIDENCE | 257 | 77401 |  | Staircase 4 For Fire Line Work | Ground Level | Tower | 1 | 2.5 | 0.9 | 2 | 1 | rm | 2 | 2023-02-24 |  | 100% | 100% | 0% | 0.28571 | 63.34 | 7.28 | 88.68 | 4.16 | 0 | 92.84 |  | 92.84
E11/K149/SK/dm/213 | RESIDENCE | 257a | 77402 |  | Staircase 4 For Fire Line Work | Ground Level | Tower | 1 | 2.5 | 1.3 | 2 | 1 | rm | 2 | 2023-02-24 |  | 100% | 100% | 0% | 0.28571 | 63.34 | 7.28 | 88.68 | 4.16 | 0 | 92.84 |  | 92.84
E11/K149/SK/dm/213 | RESIDENCE | 258 | 77403 |  | Fire Line Work | Ground Level | Tower | 1 | 2.5 | 1.3 | 4 | 2 | rm | 4 | 2023-02-24 |  | 100% | 100% | 0% | 0.28571 | 63.34 | 7.28 | 177.35 | 8.32 | 0 | 185.67 |  | 185.67
E11/K149/SK/dm/213 | RESIDENCE | 258a | 77404 |  | Fire Line Work | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 1.3 | 1 |  | 1 | m2-LxW | 1.3 | 2023-02-25 |  | 100% | 100% | 0% | 0.14286 | 36.52 | 2.94 | 33.23 | 0.55 | 0 | 33.78 |  | 33.78
E11/K149/SK/dm/213 | RESIDENCE | 258b | 77405 |  | Fire Line Work | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 1.3 | 1 |  | 1 | m2-LxW | 1.3 | 2023-02-25 |  | 100% | 100% | 0% | 0.14286 | 36.52 | 2.94 | 33.23 | 0.55 | 0 | 33.78 |  | 33.78
E11/K149/SK/dm/213 | RESIDENCE | 259 | 77406 |  | Water Tank Access | Ground Level | Tower | 1 | 2.5 | 1.3 | 1.7 | 1 | rm | 1.7 | 2023-02-25 |  | 100% | 100% | 0% | 0.14286 | 63.34 | 7.28 | 75.37 | 1.77 | 0 | 77.14 |  | 77.14
E11/K149/SK/dm/213 | HOTEL | 135 | 75919 | 78555 | Staircase 8 For Wall Finishing Work | Level 1 to 2 | Independent | 1 | 6 | 0.9 | 1.5 | 1 | m2-LxH | 9 | 2023-01-26 | 2023-02-08 | 100% | 100% | 100% | 2 | 12.01 | 0.49 | 75.66 | 8.82 | 32.43 | 116.91 |  | 116.91
E11/K149/SK/dm/213 | HOTEL | 135a | 75919 | 78555 | Staircase 8 For Wall Finishing Work | Level 1 to 2 | Independent | 1 | 6.8 | 0.9 | 2 | 1 | m2-LxH | 13.6 | 2023-01-26 | 2023-02-08 | 100% | 100% | 100% | 2 | 12.01 | 0.49 | 114.34 | 13.33 | 49 | 176.67 |  | 176.67
E11/K149/SK/dm/213 | HOTEL | 135b | 75920 | 78556 | Staircase 8 For Wall Finishing Work | Level 3 | Independent | 1 | 6 | 0.9 | 2.5 | 1 | m2-LxH | 15 | 2023-01-26 | 2023-02-08 | 100% | 100% | 100% | 2 | 12.01 | 0.49 | 126.11 | 14.7 | 54.05 | 194.86 |  | 194.86
E11/K149/SK/dm/213 | HOTEL | 135b | 75920 | 78556 | Staircase 8 For Wall Finishing Work | Level 3 | Additional Boarding | 1 | 6 | 0.9 |  | 1 | m2-LxW | 5.4 | 2023-01-26 | 2023-02-08 | 100% | 100% | 100% | 2 | 6.63 | 0.7 | 25.06 | 7.56 | 10.74 | 43.36 |  | 43.36
E11/K149/SK/dm/213 | HOTEL | 135c | 75920 | 78556 | Staircase 8 For Wall Finishing Work | Level 3 | Independent | 1 | 6.8 | 0.9 | 2.5 | 1 | m2-LxH | 17 | 2023-01-26 | 2023-02-08 | 100% | 100% | 100% | 2 | 12.01 | 0.49 | 142.92 | 16.66 | 61.25 | 220.83 |  | 220.83
E11/K149/SK/dm/213 | HOTEL | 135c | 75920 | 78556 | Staircase 8 For Wall Finishing Work | Level 3 | Additional Boarding | 1 | 6.8 | 0.9 |  | 1 | m2-LxW | 6.12 | 2023-01-26 | 2023-02-08 | 100% | 100% | 100% | 2 | 6.63 | 0.7 | 28.4 | 8.57 | 12.17 | 49.14 |  | 49.14
E11/K149/SK/dm/213 | HOTEL | 136 | 75921 | 78587 | Glass Line ACP Fixing | Roof | Independent | 1 | 3 | 1.3 | 1.5 | 1 | m2-LxH | 4.5 | 2023-01-26 | 2023-02-18 | 100% | 100% | 100% | 3.4286 | 12.01 | 0.49 | 37.83 | 7.56 | 16.21 | 61.6 |  | 61.6
E11/K149/SK/dm/640 | HOTEL | 108g | 75922 | 79809 | Steel Column Lifting Work (1399-45a) | Level 29 | Design 1399-45a | 1 |  |  |  |  | unit | 1 | 2023-01-26 | 2023-02-22 | 25% | 25% | 25% | 4 | 19801.43 | 837.82 | 3465.25 | 837.82 | 1485.11 | 5788.18 |  | 5788.18 | Tas Quote 2439-34-1
E11/K149/SK/dm/213 | HOTEL | 137 | 75923 | 78567 | Plant Room Fire Seelent Work | Level 1 | Tower | 1 | 1.8 | 1.8 | 2 | 1 | rm | 2 | 2023-01-26 | 2023-02-13 | 100% | 100% | 100% | 2.7143 | 63.34 | 7.28 | 88.68 | 39.52 | 38 | 166.2 |  | 166.2
E11/K149/SK/dm/213 | HOTEL | 138 | 75924 |  | Plant Room Fire Seelent Work | Level 1 | Tower | 1 | 1.8 | 1.8 | 1.5 | 1 | rm | 1.5 | 2023-01-26 |  | 100% | 100% | 0% | 4.4286 | 63.34 | 7.28 | 66.51 | 48.36 | 0 | 114.87 |  | 114.87
E11/K149/SK/SR/517 | HOTEL | 139 | 75925 |  | Balcony Ceiling Work | Level 21 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2023-01-26 |  | 100% | 100% | 0% | 4.4286 | 1772.5845 | 52.192 | 1240.81 | 231.14 | 0 | 1471.95 |  | 1471.95 | Tas Quote 2439-25-1 (item#5)
E11/K149/SK/dm/213 | HOTEL | 135d | 75926 | 78557 | Staircase 8 For Wall Finishing Work | Level 3 to 4 | Independent | 1 | 6 | 0.9 | 2.5 | 1 | m2-LxH | 15 | 2023-01-27 | 2023-02-08 | 100% | 100% | 100% | 1.8571 | 12.01 | 0.49 | 126.11 | 13.65 | 54.05 | 193.81 |  | 193.81
E11/K149/SK/dm/213 | HOTEL | 135d | 75926 | 78557 | Staircase 8 For Wall Finishing Work | Level 3 to 4 | Additional Boarding | 1 | 6 | 0.9 |  | 1 | m2-LxW | 5.4 | 2023-01-27 | 2023-02-08 | 100% | 100% | 100% | 1.8571 | 6.63 | 0.7 | 25.06 | 7.02 | 10.74 | 42.82 |  | 42.82
E11/K149/SK/dm/213 | HOTEL | 135e | 75927 | 78557 | Staircase 8 For Wall Finishing Work | Level 4 to 5 | Independent | 1 | 6.8 | 0.9 | 2.5 | 1 | m2-LxH | 17 | 2023-01-27 | 2023-02-08 | 100% | 100% | 100% | 1.8571 | 12.01 | 0.49 | 142.92 | 15.47 | 61.25 | 219.64 |  | 219.64
E11/K149/SK/dm/213 | HOTEL | 135f | 75927 | 78558 | Staircase 8 For Wall Finishing Work | Level 4 to 5 | Independent | 1 | 6 | 0.9 | 2.5 | 1 | m2-LxH | 15 | 2023-01-27 | 2023-02-08 | 100% | 100% | 100% | 1.8571 | 12.01 | 0.49 | 126.11 | 13.65 | 54.05 | 193.81 |  | 193.81
E11/K149/SK/dm/213 | HOTEL | 135g | 75928 | 78568 | Staircase 8 For Wall Finishing Work | Level 5 to 6 | Independent | 1 | 6.8 | 0.9 | 2.5 | 1 | m2-LxH | 17 | 2023-01-27 | 2023-02-14 | 100% | 100% | 100% | 2.7143 | 12.01 | 0.49 | 142.92 | 22.61 | 61.25 | 226.78 |  | 226.78
E11/K149/SK/dm/213 | HOTEL | 140 | 75929 | 78570 | Near Ramp For Concret Cutting | Basement 1 | Tower | 1 | 2.5 | 2.5 | 10 | 1 | rm | 10 | 2023-01-27 | 2023-02-14 | 100% | 100% | 100% | 2.7143 | 63.34 | 7.28 | 443.38 | 197.6 | 190.02 | 831 |  | 831
E11/K149/SK/dm/213 | HOTEL | 140a | 75929 | 78570 | Near Ramp For Concret Cutting | Basement 1 | Buttress | 1 | 2.5 | 2.5 | 4 |  | m3 | 25 | 2023-01-27 | 2023-02-14 | 100% | 100% | 100% | 2.7143 | 5.29 | 0.35 | 92.58 | 23.75 | 39.68 | 156.01 |  | 156.01
E11/K149/SK/dm/213 | HOTEL | 135h | 75930 | 78568 | Staircase 8 For Wall Finishing Work | Level 5 to 6 | Independent | 1 | 5.3 | 0.9 | 2.5 | 1 | m2-LxH | 13.25 | 2023-01-28 | 2023-02-14 | 100% | 100% | 100% | 2.5714 | 12.01 | 0.49 | 111.39 | 16.7 | 47.74 | 175.83 |  | 175.83
E11/K149/SK/dm/213 | HOTEL | 135h | 75930 | 78568 | Staircase 8 For Wall Finishing Work | Level 5 to 6 | Additional Boarding | 1 | 5.3 | 0.9 |  | 1 | m2-LxW | 4.77 | 2023-01-28 | 2023-02-14 | 100% | 100% | 100% | 2.5714 | 6.63 | 0.7 | 22.14 | 8.59 | 9.49 | 40.22 |  | 40.22
E11/K149/SK/dm/213 | HOTEL | 135i | 75931 | 78569 | Staircase 8 For Wall Finishing Work | Level 6 to 7 | Independent | 1 | 6 | 0.9 | 2 | 1 | m2-LxH | 12 | 2023-01-28 | 2023-02-14 | 100% | 100% | 100% | 2.5714 | 12.01 | 0.49 | 100.88 | 15.12 | 43.24 | 159.24 |  | 159.24
E11/K149/SK/dm/213 | HOTEL | 135j | 75932 | 78569 | Staircase 8 For Wall Finishing Work | Level 6 to 7 | Independent | 1 | 5 | 0.9 | 2 | 1 | m2-LxH | 10 | 2023-01-28 | 2023-02-14 | 100% | 100% | 100% | 2.5714 | 12.01 | 0.49 | 84.07 | 12.6 | 36.03 | 132.7 |  | 132.7
E11/K149/SK/dm/213 | HOTEL | 119b | 75933 | 80940 | Lift Machine Room Riser Wall Block Work | Level 30 | Tower | 1 | 2.5 | 1.3 | 2 | 1 | rm | 2 | 2023-01-28 | 2023-01-31 | 100% | 100% | 100% | 0.57143 | 63.34 | 7.28 | 88.68 | 8.32 | 38 | 135 |  | 135
E11/K149/SK/dm/213 | HOTEL | 108h | 75934 | 79807 | Cabana Structure Work | Level 29 | Independent | 1 | 10.7 | 1.8 | 1.5 | 1 | m2-LxH | 16.05 | 2023-01-28 | 2023-02-22 | 100% | 100% | 100% | 3.7143 | 16.76 | 0.77 | 188.3 | 45.9 | 80.7 | 314.9 |  | 314.9
E11/K149/SMF/DM/641 | HOTEL | 141 to a,b | 75935 |  | Canopy & EIFS Work | Level 28 to 30 | Design-1399-43 | 1 |  |  |  |  | unit | 1 | 2023-01-28 |  | 100% | 100% | 0% | 4.1429 | 7845.02 | 212.35 | 5491.51 | 879.74 | 0 | 6371.25 |  | 6371.25 | Tas Quote 2439-33-1
E11/K149/SK/dm/213 | HOTEL | 142 | 75936 |  | Mast Climber Access | Level 17 | Tower | 1 | 1.8 | 1 | 1 | 1 | rm | 1 | 2023-01-30 |  | 100% | 100% | 0% | 3.8571 | 63.34 | 7.28 | 44.34 | 28.08 | 0 | 72.42 |  | 72.42
E11/K149/SK/dm/213 | HOTEL | 150f | 75937 | 78572 | External EIFS Work | Level 17 | Tower | 1 | 1.8 | 0.75 | 0.5 | 1 | rm | 0.5 | 2023-01-30 | 2023-02-14 | 100% | 100% | 100% | 2.2857 | 63.34 | 7.28 | 22.17 | 8.32 | 9.5 | 39.99 |  | 39.99
E11/K149/SK/dm/213 | HOTEL | 143 | 75938 |  | Planter Area edge protection | Level 4 | Double Handrail | 1 | 31 |  | 1 |  | lm | 31 | 2023-01-30 |  | 100% | 100% | 0% | 3.8571 | 15 | 0.91 | 325.5 | 108.81 | 0 | 434.31 |  | 434.31
E11/K149/SK/dm/213 | HOTEL | 144 | 75939 | 79810 | EIFS Work | Level 30 | Independent | 1 | 7 | 1 | 2 | 1 | m2-LxH | 14 | 2023-01-31 | 2023-02-24 | 100% | 100% | 100% | 3.5714 | 12.01 | 0.49 | 117.7 | 24.5 | 50.44 | 192.64 |  | 192.64
E11/K149/SK/dm/213 | HOTEL | 144a | 75939 | 79811 | EIFS Work | Level 30 | Independent | 1 | 11 | 0.5 | 2 | 1 | m2-LxH | 22 | 2023-01-31 | 2023-02-24 | 100% | 100% | 100% | 3.5714 | 12.01 | 0.49 | 184.95 | 38.5 | 79.27 | 302.72 |  | 302.72
E11/K149/SK/dm/213 | HOTEL | 144b | 75940 | 79812 | EIFS Work | Level 30 | Tower | 1 | 2 | 1 | 1 | 1 | rm | 1 | 2023-01-31 | 2023-02-24 | 100% | 100% | 100% | 3.5714 | 63.34 | 7.28 | 44.34 | 26 | 19 | 89.34 |  | 89.34
E11/K149/SK/dm/213 | HOTEL | 145 | 75941 | 79806 | EIFS Work | Level 29 | Independent | 1 | 7 | 1.3 | 3 | 1 | m2-LxH | 21 | 2023-01-31 | 2023-02-22 | 100% | 100% | 100% | 3.2857 | 12.01 | 0.49 | 176.55 | 33.81 | 75.66 | 286.02 |  | 286.02
E11/K149/SK/dm/213 | HOTEL | 145a | 75941 | 79805 | EIFS Work | Level 29 | Independent | 1 | 3.5 | 1 | 3 | 1 | m2-LxH | 10.5 | 2023-01-31 | 2023-02-22 | 100% | 100% | 100% | 3.2857 | 12.01 | 0.49 | 88.27 | 16.91 | 37.83 | 143.01 |  | 143.01
E11/K149/SK/dm/213 | HOTEL | 115b | 75942 |  | EIFS Work | Upper Roof | Additional Boarding | 1 | 9.5 | 1 |  | 1 | m2-LxW | 9.5 | 2023-01-31 |  | 100% | 100% | 0% | 3.7143 | 6.63 | 0.7 | 44.09 | 24.7 | 0 | 68.79 |  | 68.79
E11/K149/SK/dm/213 | HOTEL | 115c | 75943 |  | ACP Panel Work | Upper Roof | Independent | 1 | 4 | 0.75 | 4 | 1 | m2-LxH | 16 | 2023-01-31 |  | 100% | 100% | 0% | 3.7143 | 12.01 | 0.49 | 134.51 | 29.12 | 0 | 163.63 |  | 163.63
E11/K149/SK/dm/213 | HOTEL | 146 | 75944 |  | Lift Machine Room EIFS Work | Level 30 | Independent | 1 | 7.5 | 1.2 | 4 | 1 | m2-LxH | 30 | 2023-02-01 |  | 100% | 100% | 0% | 3.5714 | 12.01 | 0.49 | 252.21 | 52.5 | 0 | 304.71 |  | 304.71
E11/K149/SK/dm/213 | HOTEL | 146a | 75944 |  | Lift Machine Room EIFS Work | Level 30 | Independent | 1 | 9 | 1 | 4 | 1 | m2-LxH | 36 | 2023-02-01 |  | 100% | 100% | 0% | 3.5714 | 12.01 | 0.49 | 302.65 | 63 | 0 | 365.65 |  | 365.65
E11/K149/SK/dm/213 | HOTEL | 147 | 75945 | 78598 | Pool Side GRC Panel Work | Level 29 | Mobile Tower | 1 | 2.5 | 1.3 | 2.3 | 2 | rm | 2.3 | 2023-02-01 | 2023-02-22 | 100% | 100% | 100% | 3.1429 | 103.33 | 10.29 | 166.36 | 74.38 | 71.3 | 312.04 |  | 312.04
E11/K149/SK/dm/213 | HOTEL | 141d | 75946 |  | EIFS Work | Level 29 | Cantilever (0.5 > 1.2m width) | 1 | 6 | 1 |  | 1 | m2-LxW | 6 | 2023-02-01 |  | 100% | 100% | 0% | 3.5714 | 36.52 | 2.94 | 153.38 | 63 | 0 | 216.38 |  | 216.38
E11/K149/SK/dm/213 | HOTEL | 148 | 75947 |  | Wall Finishing Work | Ground Level | Independent | 1 | 8.8 | 1.3 | 3.5 | 1 | m2-LxH | 30.8 | 2023-02-02 |  | 100% | 100% | 0% | 3.4286 | 12.01 | 0.49 | 258.94 | 51.74 | 0 | 310.68 |  | 310.68
E11/K149/SK/dm/213 | HOTEL | 148 | 75947 |  | Wall Finishing Work | Ground Level | Additional Boarding | 1 | 8.8 | 1.3 |  | 1 | m2-LxW | 11.44 | 2023-02-02 |  | 100% | 100% | 0% | 3.4286 | 6.63 | 0.7 | 53.09 | 27.46 | 0 | 80.55 |  | 80.55
E11/K149/SK/dm/213 | HOTEL | 148a | 75947 |  | Wall Finishing Work | Ground Level | Independent | 1 | 10 | 1.3 | 3 | 1 | m2-LxH | 30 | 2023-02-02 |  | 100% | 100% | 0% | 3.4286 | 12.01 | 0.49 | 252.21 | 50.4 | 0 | 302.61 |  | 302.61
E11/K149/SK/dm/213 | HOTEL | 148a | 75947 |  | Wall Finishing Work | Ground Level | Additional Boarding | 1 | 10 | 1.3 |  | 1 | m2-LxW | 13 | 2023-02-02 |  | 100% | 100% | 0% | 3.4286 | 6.63 | 0.7 | 60.33 | 31.2 | 0 | 91.53 |  | 91.53
E11/K149/SK/dm/213 | HOTEL | 82f | 75948 |  | Glass Line Frame Work | Level 29 | Cantilever (0.5 > 1.2m width) | 1 | 4 | 0.75 |  | 1 | m2-LxW | 3 | 2023-02-02 |  | 100% | 100% | 0% | 3.4286 | 36.52 | 2.94 | 76.69 | 30.24 | 0 | 106.93 |  | 106.93
E11/K149/SK/dm/213 | HOTEL | 149 | 75949 |  | Wall Finishing Work | Ground Level | Independent | 1 | 14 | 1.3 | 3.5 | 1 | m2-LxH | 49 | 2023-02-03 |  | 100% | 100% | 0% | 3.2857 | 12.01 | 0.49 | 411.94 | 78.89 | 0 | 490.83 |  | 490.83
E11/K149/SK/dm/213 | HOTEL | 149 | 75949 |  | Wall Finishing Work | Ground Level | Additional Boarding | 1 | 14 | 1.3 |  | 1 | m2-LxW | 18.2 | 2023-02-03 |  | 100% | 100% | 0% | 3.2857 | 6.63 | 0.7 | 84.47 | 41.86 | 0 | 126.33 |  | 126.33
E11/K149/SK/dm/213 | HOTEL | 141c | 75950 |  | EIFS Work | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 5.4 | 1 |  | 1 | m2-LxW | 5.4 | 2023-01-28 |  | 100% | 100% | 0% | 4.1429 | 36.52 | 2.94 | 138.05 | 65.77 | 0 | 203.82 |  | 203.82
E11/K149/SK/dm/213 | HOTEL | 150 | 76801 | 79814 | Wall Finishing Work | Ground Level | Independent | 1 | 18.5 | 1.3 | 2.2 | 1 | m2-LxH | 40.7 | 2023-02-03 | 2023-02-25 | 100% | 100% | 100% | 3.2857 | 12.01 | 0.49 | 342.16 | 65.53 | 146.64 | 554.33 |  | 554.33
E11/K149/SK/dm/213 | HOTEL | 107a | 76802 | 78586 | View Deck Loading Platform | Level 29 | Design-1399-42 | 1 |  |  |  | 1 | unit | 1 | 2023-02-03 | 2023-02-21 | 0% | 0% | 0% | 2.7143 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2439-30-1 Item--10), Charged under Tag 92&92a
E11/K149/SK/dm/213 | HOTEL | 151 | 76803 |  | Edge Protection | Level 29 | Double Handrail | 1 | 70 |  | 1.5 |  | lm | 70 | 2023-02-03 |  | 100% | 100% | 0% | 3.2857 | 15 | 0.91 | 735 | 209.3 | 0 | 944.3 |  | 944.3
E11/K149/SK/dm/213 | HOTEL | 115d | 76804 |  | ACP Panel Work | Upper Roof | Cantilever (0.5 > 1.2m width) | 1 | 4 | 0.75 |  | 1 | m2-LxW | 3 | 2023-02-04 |  | 100% | 100% | 0% | 3.1429 | 36.52 | 2.94 | 76.69 | 27.72 | 0 | 104.41 |  | 104.41
E11/K149/SK/dm/213 | HOTEL | 150g | 76805 | 78573 | Glass Cleaning & ceiling work | Level 17 | Cantilever (0.5 > 1.2m width) | 1 | 1 | 1 |  | 1 | m2-LxW | 1 | 2023-02-06 | 2023-02-14 | 100% | 100% | 100% | 1.2857 | 36.52 | 2.94 | 25.56 | 3.78 | 10.96 | 40.3 |  | 40.3
E11/K149/SK/dm/213 | HOTEL | 152 | 76806 | 78559 | Decking Access | Level 29 | Tower | 1 | 1.5 | 1.3 | 4 | 2 | rm | 4 | 2023-02-07 | 2023-02-08 | 100% | 100% | 100% | 0.28571 | 63.34 | 7.28 | 177.35 | 8.32 | 76.01 | 261.68 |  | 261.68
E11/K149/SK/dm/213 | HOTEL | 153 | 76813 | 79803 | Decking Access | Level 29 | Independent | 1 | 6 | 1.3 | 4 | 1 | m2-LxH | 24 | 2023-02-08 | 2023-02-22 | 100% | 100% | 100% | 2.1429 | 12.01 | 0.49 | 201.77 | 25.2 | 86.47 | 313.44 |  | 313.44
E11/K149/SK/dm/213 | HOTEL | 148b | 76807 |  | Wall Finishing Work | Ground Level | Independent | 1 | 17.5 | 0.9 | 2.5 | 1 | m2-LxH | 43.75 | 2023-02-07 |  | 100% | 100% | 0% | 2.7143 | 12.01 | 0.49 | 367.81 | 58.19 | 0 | 426 |  | 426
E11/K149/SK/dm/213 | HOTEL | 145b | 76808 | 79804 | Corner Side ACP Panel | Level 29 | Independent | 1 | 4 | 2.3 | 2 | 1 | m2-LxH | 8 | 2023-02-07 | 2023-02-22 | 100% | 100% | 100% | 2.2857 | 16.76 | 0.77 | 93.86 | 14.08 | 40.22 | 148.16 |  | 148.16
E11/K149/SK/dm/213 | HOTEL | 113a | 76809 |  | Plant Room For Painting Work | Level 5 | Cantilever (0.5 > 1.2m width) | 1 | 7 | 1 |  | 1 | m2-LxW | 7 | 2023-02-08 |  | 100% | 100% | 0% | 2.5714 | 36.52 | 2.94 | 178.95 | 52.92 | 0 | 231.87 |  | 231.87
E11/K149/SK/dm/213 | HOTEL | 2f | 76810 |  | Plant Room For Painting Work | Level 5 | Independent | 1 | 2.6 | 1.8 | 4 | 2 | m2-LxH | 10.4 | 2023-02-08 |  | 100% | 100% | 0% | 2.5714 | 12.01 | 0.49 | 87.43 | 13.1 | 0 | 100.53 |  | 100.53
E11/K149/SK/dm/213 | HOTEL | 2g | 76810 |  | Plant Room For Painting Work | Level 5 | Additional Boarding | 1 | 2.5 | 1.8 |  | 1 | m2-LxW | 4.5 | 2023-02-08 |  | 100% | 100% | 0% | 2.5714 | 6.63 | 0.7 | 20.88 | 8.1 | 0 | 28.98 |  | 28.98
E11/K149/SK/dm/213 | HOTEL | 2h | 76811 |  | Plant Room For Painting Work | Level 5 | Tower | 1 | 2.5 | 1.8 | 4 | 1 | rm | 4 | 2023-02-08 |  | 100% | 100% | 0% | 2.5714 | 63.34 | 7.28 | 177.35 | 74.88 | 0 | 252.23 |  | 252.23
E11/K149/SK/dm/213 | HOTEL | 2h | 76811 |  | Plant Room For Painting Work | Level 5 | Additional Boarding | 1 | 2.5 | 1.8 |  | 1 | m2-LxW | 4.5 | 2023-02-08 |  | 100% | 100% | 0% | 2.5714 | 6.63 | 0.7 | 20.88 | 8.1 | 0 | 28.98 |  | 28.98
E11/K149/SK/dm/213 | HOTEL | 109a | 76812 |  | Plant Room For Painting Work | Level 5 | Cantilever (0 < 0.5m width) | 1 | 1.8 | 0.5 |  | 1 | m2-LxW | 0.9 | 2023-02-08 |  | 100% | 100% | 0% | 2.5714 | 32.75 | 1.05 | 20.63 | 2.43 | 0 | 23.06 |  | 23.06
E11/K149/SK/dm/213 | HOTEL | 109b | 76812 |  | Plant Room For Painting Work | Level 5 | Additional Boarding | 1 | 1.8 | 1.3 |  | 1 | m2-LxW | 2.34 | 2023-02-08 |  | 100% | 100% | 0% | 2.5714 | 6.63 | 0.7 | 10.86 | 4.21 | 0 | 15.07 |  | 15.07
E11/K149/SK/dm/213 | HOTEL | 121c | 76814 | 78574 | KID Ceiling Work | Level 29 | Independent | 1 | 5.5 | 2.5 | 3.5 | 1 | m2-LxH | 19.25 | 2023-02-08 | 2023-02-11 | 100% | 100% | 100% | 0.57143 | 16.76 | 0.77 | 225.84 | 8.47 | 96.79 | 331.1 |  | 331.1
E11/K149/SK/SR/582 | HOTEL | 154 & a,b | 76815 | 78575 | Lift Shaft RC Slab Extention Work | Level 29 | Design 1399-39 | 1 |  |  |  |  | unit | 1 | 2023-02-09 | 2023-02-13 | 100% | 100% | 100% | 0.71429 | 4805.88 | 212.24 | 3364.12 | 151.6 | 1441.76 | 4957.48 |  | 4957.48 | 2439-29-1 (Item-9)
E11/K149/SK/dm/213 | HOTEL | 80c | 76816 | 78578 | Entrance For Ceiling Work | Level 2 | Tower | 1 | 2.5 | 1.8 | 5 | 1 | rm | 5 | 2023-02-09 | 2023-02-15 | 100% | 100% | 100% | 1 | 63.34 | 7.28 | 221.69 | 36.4 | 95.01 | 353.1 |  | 353.1
E11/K149/SK/dm/213 | HOTEL | 80d | 76816 | 78578 | Entrance For Ceiling Work | Level 2 | Cantilever (0 < 0.5m width) | 1 | 1.8 | 0.5 |  | 1 | m2-LxW | 0.9 | 2023-02-09 | 2023-02-15 | 100% | 100% | 100% | 1 | 32.75 | 1.05 | 20.63 | 0.95 | 8.84 | 30.42 |  | 30.42
E11/K149/SK/dm/213 | HOTEL | 80e | 76817 | 78579 | Entrance For Ceiling Work | Level 2 | Cantilever (0 < 0.5m width) | 1 | 2.5 | 0.25 |  | 1 | m2-LxW | 0.63 | 2023-02-09 | 2023-02-15 | 100% | 100% | 100% | 1 | 32.75 | 1.05 | 14.44 | 0.66 | 6.19 | 21.29 |  | 21.29
E11/K149/SK/dm/213 | HOTEL | 80f | 76817 | 78579 | Entrance For Ceiling Work | Level 2 | Cantilever (0.5 > 1.2m width) | 1 | 1 | 1 |  | 1 | m2-LxW | 1 | 2023-02-09 | 2023-02-15 | 100% | 100% | 100% | 1 | 36.52 | 2.94 | 25.56 | 2.94 | 10.96 | 39.46 |  | 39.46
E11/K149/SK/dm/213 | HOTEL | 151a | 76818 |  | Infinity Pool Edge Protection | Level 29 | Double Handrail | 1 | 45 |  | 1.5 |  | lm | 45 | 2023-02-09 |  | 100% | 100% | 0% | 2.4286 | 15 | 0.91 | 472.5 | 99.45 | 0 | 571.95 |  | 571.95
E11/K149/SK/dm/213 | HOTEL | 148c | 76819 |  | Over Head Protection | Ground Level | Independent | 1 | 18.8 | 0.9 | 2 | 1 | m2-LxH | 37.6 | 2023-02-10 |  | 100% | 100% | 0% | 2.2857 | 12.01 | 0.49 | 316.1 | 42.11 | 0 | 358.21 |  | 358.21
E11/K149/SK/dm/213 | HOTEL | 148d | 76819 |  | Over Head Protection | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 18.8 | 1 |  | 1 | m2-LxW | 18.8 | 2023-02-10 |  | 100% | 100% | 0% | 2.2857 | 36.52 | 2.94 | 480.6 | 126.34 | 0 | 606.94 |  | 606.94
E11/K149/SK/dm/213 | HOTEL | 155 | 76820 | 78576 | View Deck For Welding Work | Level 29 | Independent 1.8m wide | 1 | 5 | 2 | 0.5 | 1 | m2-LxH | 2.5 | 2023-02-10 | 2023-02-11 | 100% | 100% | 100% | 0.28571 | 16.76 | 0.77 | 29.33 | 0.55 | 12.57 | 42.45 |  | 42.45
E11/K149/SK/dm/213 | HOTEL | 156 | 76821 |  | View Deck Edge Protection | Level 29 | Double Handrail | 1 | 18 |  | 1 |  | lm | 18 | 2023-02-10 |  | 100% | 100% | 0% | 2.2857 | 15 | 0.91 | 189 | 37.44 | 0 | 226.44 |  | 226.44
E11/K149/SK/dm/213 | HOTEL | 141e | 76822 |  | EIFS Work | Level 29 | Cantilever (0 < 0.5m width) | 2 | 1 | 0.5 |  | 2 | m2-LxW | 1 | 2023-02-10 |  | 100% | 100% | 0% | 2.2857 | 32.75 | 1.05 | 22.93 | 2.4 | 0 | 25.33 |  | 25.33
E11/K149/SK/dm/213 | HOTEL | 67b | 76823 |  | Material Shifting Access | Level 27 | Tower | 1 | 1.5 | 1 | 1.5 | 1 | rm | 1.5 | 2023-02-10 |  | 100% | 100% | 0% | 2.2857 | 63.34 | 7.28 | 66.51 | 24.96 | 0 | 91.47 |  | 91.47
E11/K149/SK/dm/213 | HOTEL | 84e | 76824 | 78585 | Silicon Work Canopy | Level 29 | Cantilever (0.5 > 1.2m width) | 1 | 5.5 | 1.2 |  | 1 | m2-LxW | 6.6 | 2023-02-11 | 2023-02-18 | 100% | 100% | 100% | 1.1429 | 36.52 | 2.94 | 168.72 | 22.18 | 72.31 | 263.21 |  | 263.21
E11/K149/SK/dm/213 | HOTEL | 157 | 76825 |  | Corridor For Painting Work | Level 28 | Independent | 1 | 19 | 1.3 | 2 | 1 | m2-LxH | 38 | 2023-02-11 |  | 100% | 100% | 0% | 2.1429 | 12.01 | 0.49 | 319.47 | 39.9 | 0 | 359.37 |  | 359.37
E11/K149/SK/dm/213 | HOTEL | 158 | 76826 |  | Column For Ceiling Work | Ground Level | Tower | 1 | 1.8 | 1.3 | 4 | 2 | rm | 4 | 2023-02-11 |  | 100% | 100% | 0% | 2.1429 | 63.34 | 7.28 | 177.35 | 62.4 | 0 | 239.75 |  | 239.75
E11/K149/SK/dm/213 | HOTEL | 159 | 76827 | 78580 | View Deck Access | Level 29 | Independent | 1 | 3.3 | 1.5 | 1 | 1 | m2-LxH | 3.3 | 2023-02-11 | 2023-02-15 | 100% | 100% | 100% | 0.71429 | 12.01 | 0.49 | 27.74 | 1.16 | 11.89 | 40.79 |  | 40.79
E11/K149/SK/dm/213 | HOTEL | 70d | 76828 |  | Entrance For Ceiling Work | Ground Level | Independent 1.8m wide | 1 | 3.4 | 1.8 | 4 | 1 | m2-LxH | 13.6 | 2023-02-11 |  | 100% | 100% | 0% | 2.1429 | 16.76 | 0.77 | 159.56 | 22.44 | 0 | 182 |  | 182
E11/K149/SK/dm/213 | HOTEL | 160 | 76829 |  | Corridor For Painting Work | Level 28 | Tower | 1 | 2.5 | 1.3 | 2 | 1 | rm | 2 | 2023-02-13 |  | 100% | 100% | 0% | 1.8571 | 63.34 | 7.28 | 88.68 | 27.04 | 0 | 115.72 |  | 115.72
E11/K149/SK/SR/582 | HOTEL | 161 & a,b | 76830 | 78584 | Lift Shaft RC Slab Extention Work | Level 29 | Design 1399-39 | 1 |  |  |  |  | unit | 1 | 2023-02-14 | 2023-02-17 | 100% | 100% | 100% | 0.57143 | 4805.88 | 212.24 | 3364.12 | 121.28 | 1441.76 | 4927.16 |  | 4927.16 | 2439-29-1 (Item-9)
E11/K149/SK/dm/213 | HOTEL | 162 | 76831 | 78597 | GRC Panel Work | Level 29 | Mobile Tower | 1 | 1.3 | 1.3 | 2.3 | 2 | rm | 2.3 | 2023-02-14 | 2023-02-22 | 100% | 100% | 100% | 1.2857 | 103.33 | 10.29 | 166.36 | 30.43 | 71.3 | 268.09 |  | 268.09
E11/K149/SK/dm/213 | HOTEL | 140b | 76832 | 78571 | Ramp Area For Concret Slab Cuttinhg | Basement 1 | Cantilever (0.5 > 1.2m width) | 1 | 2.5 | 1.5 |  | 1 | m2-LxW | 3.75 | 2023-02-13 | 2023-02-14 | 100% | 100% | 100% | 0.28571 | 36.52 | 2.94 | 95.87 | 3.15 | 41.09 | 140.11 |  | 140.11
E11/K149/SK/dm/213 | HOTEL | 84f | 76833 | 78581 | Silicon Work Canopy (Damac Side) | Level 29 | Cantilever (0.5 > 1.2m width) | 1 | 10 | 1 |  | 1 | m2-LxW | 10 | 2023-02-14 | 2023-02-18 | 100% | 100% | 100% | 0.71429 | 36.52 | 2.94 | 255.64 | 21 | 109.56 | 386.2 |  | 386.2
E11/K149/SK/dm/213 | HOTEL | 163 | 76834 |  | Ceiling Work | Level 24 | Independent | 1 | 4.3 | 0.9 | 1 | 1 | m2-LxH | 4.3 | 2023-02-15 |  | 100% | 100% | 0% | 1.5714 | 12.01 | 0.49 | 36.15 | 3.31 | 0 | 39.46 |  | 39.46
E11/K149/SK/dm/213 | HOTEL | 164 | 76835 |  | Balcony Access | Level 24 | Tower | 1 | 2.5 | 1.3 | 3.5 | 1 | rm | 3.5 | 2023-02-15 |  | 100% | 100% | 0% | 1.5714 | 63.34 | 7.28 | 155.18 | 40.04 | 0 | 195.22 |  | 195.22
E11/K149/SK/dm/213 | HOTEL | 164a | 76835 |  | Balcony Access | Level 24 | Cantilever (0.5 > 1.2m width) | 1 | 1.3 | 0.9 |  | 1 | m2-LxW | 1.17 | 2023-02-15 |  | 100% | 100% | 0% | 1.5714 | 36.52 | 2.94 | 29.91 | 5.41 | 0 | 35.32 |  | 35.32
E11/K149/SK/dm/213 | HOTEL | 148e | 76837 |  | Wall Finishing Work | Ground Level | Additional Boarding | 1 | 17.5 | 0.9 |  | 1 | m2-LxW | 15.75 | 2023-02-17 |  | 100% | 100% | 0% | 1.2857 | 6.63 | 0.7 | 73.1 | 14.18 | 0 | 87.28 |  | 87.28
E11/K149/SK/dm/213 | HOTEL | 165 | 76838 |  | Balcony Ceiling Work | Level 24 | Independent | 1 | 4.3 | 0.9 | 1 | 1 | m2-LxH | 4.3 | 2023-02-17 |  | 100% | 100% | 0% | 1.2857 | 12.01 | 0.49 | 36.15 | 2.71 | 0 | 38.86 |  | 38.86
E11/K149/SK/dm/213 | HOTEL | 147a | 76839 | 78596 | GRC Panel Work | Level 29 | Additional Boarding | 1 | 2.5 | 0.75 |  | 1 | m2-LxW | 1.88 | 2023-02-17 | 2023-02-22 | 100% | 100% | 100% | 0.85714 | 6.63 | 0.7 | 8.73 | 1.13 | 3.74 | 13.6 |  | 13.6
E11/K149/SK/dm/213 | HOTEL | 162a | 76840 | 78595 | GRC Panel Work | Level 29 | Additional Boarding | 1 | 1.3 | 0.75 |  | 1 | m2-LxW | 0.98 | 2023-02-17 | 2023-02-22 | 100% | 100% | 100% | 0.85714 | 6.63 | 0.7 | 4.55 | 0.59 | 1.95 | 7.09 |  | 7.09
E11/K149/SK/dm/213 | HOTEL | 84g | 76841 |  | EIFS Work | Level 29 | Cantilever (0.5 > 1.2m width) | 1 | 4.5 | 0.75 |  | 1 | m2-LxW | 3.38 | 2023-02-18 |  | 100% | 100% | 0% | 1.1429 | 36.52 | 2.94 | 86.41 | 11.36 | 0 | 97.77 |  | 97.77
E11/K149/SK/dm/213 | HOTEL | 141f | 76842 |  | EIFS Work | Level 29 | Cantilever (0.5 > 1.2m width) | 1 | 3 | 1 |  | 1 | m2-LxW | 3 | 2023-02-18 |  | 100% | 100% | 0% | 1.1429 | 36.52 | 2.94 | 76.69 | 10.08 | 0 | 86.77 |  | 86.77
E11/K149/SK/dm/213 | HOTEL | 166 | 76843 | 79813 | KMEP Work | Level 28 | Tower | 1 | 1 | 0.9 | 3 | 2 | rm | 3 | 2023-02-20 | 2023-02-25 | 100% | 100% | 100% | 0.85714 | 63.34 | 7.28 | 133.01 | 18.72 | 57.01 | 208.74 |  | 208.74
E11/K149/SK/dm/213 | HOTEL | 167 | 76844 |  | KMEP Work | Level 28 | Tower | 1 | 0.9 | 0.6 | 3 | 1 | rm | 3 | 2023-02-21 |  | 100% | 100% | 0% | 0.71429 | 63.34 | 7.28 | 133.01 | 15.6 | 0 | 148.61 |  | 148.61
E11/K149/SK/dm/213 | HOTEL | 168 | 76845 |  | KMEP Work | Level 28 | Tower | 1 | 0.9 | 0.9 | 3 | 1 | rm | 3 | 2023-02-21 |  | 100% | 100% | 0% | 0.71429 | 63.34 | 7.28 | 133.01 | 15.6 | 0 | 148.61 |  | 148.61
E11/K149/SK/dm/213 | HOTEL | 169 | 76846 |  | Mast Climber | Level 27 | Independent | 1 | 5.3 | 0.9 | 1.3 | 1 | m2-LxH | 6.89 | 2023-02-22 |  | 100% | 100% | 0% | 0.57143 | 12.01 | 0.49 | 57.92 | 1.93 | 0 | 59.85 |  | 59.85
E11/K149/SK/dm/213 | HOTEL | 170 | 76847 |  | KMEP Work | Level 28 | Tower | 1 | 1.3 | 1.3 | 3.3 | 2 | rm | 3.3 | 2023-02-23 |  | 100% | 100% | 0% | 0.42857 | 63.34 | 7.28 | 146.32 | 10.3 | 0 | 156.62 |  | 156.62
E11/K149/SK/dm/213 | HOTEL | 118a | 76848 |  | Edge Protection | Level 29 | Double Handrail | 1 | 14 |  | 1 |  | lm | 14 | 2023-02-23 |  | 100% | 100% | 0% | 0.42857 | 15 | 0.91 | 147 | 5.46 | 0 | 152.46 |  | 152.46
E11/K149/SK/dm/213 | HOTEL | 171 | 76849 |  | GRC Panel Work | Level 22 | Independent | 1 | 6.1 | 1 | 1 | 1 | m2-LxH | 6.1 | 2023-02-24 |  | 100% | 100% | 0% | 0.28571 | 12.01 | 0.49 | 51.28 | 0.85 | 0 | 52.13 |  | 52.13
E11/K149/SK/dm/213 | HOTEL | 172 | 76850 |  | GRC Panel Work | Level 25 | Independent | 1 | 6.1 | 1 | 1 | 1 | m2-LxH | 6.1 | 2023-02-24 |  | 100% | 100% | 0% | 0.28571 | 12.01 | 0.49 | 51.28 | 0.85 | 0 | 52.13 |  | 52.13
E11/K149/SMF/DM/756 | HOTEL | 173 | 77301 |  | GRC Panel Work | Level 26 | Independent | 1 | 6 | 1 | 1 | 1 | unit | 1 | 2023-02-24 |  | 100% | 100% | 0% | 0.28571 | 2022.88 | 17.43 | 1416.02 | 4.98 | 0 | 1421 |  | 1421 | Tas Quote 2439-35-1
E11/K149/SK/dm/213 | HOTEL | 174 | 77304 |  | KMEP Work | Level 28 | Tower | 1 | 1.3 | 1.3 | 2.8 | 1 | rm | 2.8 | 2023-02-25 |  | 100% | 100% | 0% | 0.14286 | 63.34 | 7.28 | 124.15 | 2.91 | 0 | 127.06 |  | 127.06
E11/K149/SK/dm/213 | HOTEL | 175 | 77305 |  | KMEP Work | Level 28 | Tower | 1 | 0.9 | 0.6 | 2.8 | 1 | rm | 2.8 | 2023-02-25 |  | 100% | 100% | 0% | 0.14286 | 63.34 | 7.28 | 124.15 | 2.91 | 0 | 127.06 |  | 127.06
E11/K149/SK/dm/213 | HOTEL | 176 | 77306 |  | KMEP Work | Level 28 | Tower | 1 | 1.8 | 1.3 | 3.5 | 2 | rm | 3.5 | 2023-02-25 |  | 100% | 100% | 0% | 0.14286 | 63.34 | 7.28 | 155.18 | 3.64 | 0 | 158.82 |  | 158.82
E11/K149/SK/dm/213 | HOTEL | 177 | 77307 |  | KMEP Work | Level 28 | Tower | 1 | 1.3 | 1.3 | 3.5 | 2 | rm | 3.5 | 2023-02-25 |  | 100% | 100% | 0% | 0.14286 | 63.34 | 7.28 | 155.18 | 3.64 | 0 | 158.82 |  | 158.82
Total |  |  | 914 | 568 | [18 empty] | 764117.81 | 763997.1 | 157019.09 | 1681188.62 | 1382614.35 | 298574.27 |  |  | 707
[31 empty] | 0 |  | 2

## Modification
Khansaheb Civil Engineering LLC
Application No.: | 6
Project Name: | Dorchester Hotel & Residences (Completion Works)
Order Reference: | 201A22002/49
As On Date: | 2023-02-25
Dayworks
DTS | Date | Hrs | Total | Previous | Net Amount
62652 | 2022-09-18 | 26 | 533 | 533 | 0
62653 | 2022-09-30 | 6 | 123 | 123 | 0
62654 | 2022-10-10 | 30 | 615 | 615 | 0
62655 | 2022-11-16 | 8 | 164 | 164 | 0
62657 | 2022-11-21 | 54 | 1107 | 1107 | 0
62658 | 2022-11-21 | 16 | 328 | 328 | 0
62661 | 2022-12-22 | 5 | 102.5 | 102.5 | 0
62662 | 2022-12-23 | 10 | 205 | 205 | 0
62663 | 2022-12-26 | 30 | 615 | 615 | 0
62664 | 2022-12-26 | 24 | 492 | 492 | 0
62665 | 2023-01-09 | 20 | 410 | 410 | 0
62667 | 2023-01-10 | 6 | 123 | 123 | 0
62668 | 2023-01-21 | 47.5 | 973.75 | 973.75 | 0
62670 | 2023-01-21 | 12 | 246 | 246 | 0
62671 | 2023-01-21 | 32.5 | 666.25 | 666.25 | 0
62669 | 2023-01-23 | 47.5 | 973.75 | 973.75 | 0
62673 | 2023-01-23 | 25 | 512.5 | 512.5 | 0
62672 | 2023-01-24 | 47.5 | 973.75 | 973.75 | 0
62674 | 2023-01-26 | 16 | 328 |  | 328
62675 | 2023-01-28 | 8 | 164 |  | 164
62676 | 2023-01-28 | 8 | 164 |  | 164
62677 | 2023-02-01 | 76 | 1558 |  | 1558
62678 | 2023-02-02 | 24 | 492 |  | 492
62679 | 2023-02-04 | 5 | 102.5 |  | 102.5
62680 | 2023-02-09 | 16 | 328 |  | 328
62693 | 2023-02-11 | 8 | 164 |  | 164
62694 | 2023-02-13 | 3 | 61.5 |  | 61.5
62681 | 2023-02-14 | 6 | 123 |  | 123
62682 | 2023-02-15 | 9 | 184.5 |  | 184.5
62683 | 2023-02-20 | 16 | 328 |  | 328
62684 | 2023-02-20 | 6 | 123 |  | 123
62685 | 2023-02-21 | 12 | 246 |  | 246
Total |  | 660 | 13530 | 9163.5 | 4366.5

## Order References
Rate Card Ref | Order Reference | Scaffolding Type | Fixed Duration | Item | Unit | Rate IN AED
1 | E11/K149/SK/dm/213 | Static tower | 0 | Erect & Dismantle | Rising Meter | 63.34
2 | E11/K149/SK/dm/213 | Static tower | 0 | Hire per Week | Rising Meter | 7.28
3 | E11/K149/SK/dm/213 | Mobile Tower | 0 | Erect & Dismantle | Rising Meter | 103.33
4 | E11/K149/SK/dm/213 | Mobile Tower | 0 | Hire per Week | Rising Meter | 10.29
5 | E11/K149/SK/dm/213 | Heavy duty tower | 0 | Erect & Dismantle | Rising Meter | 148
6 | E11/K149/SK/dm/213 | Heavy duty tower | 0 | Hire per Week | Rising Meter | 12.88
7 | E11/K149/SK/dm/213 | Independent 1.2m wide | 0 | Erect & Dismantle | M2 (LxH) | 12.01
8 | E11/K149/SK/dm/213 | Independent 1.2m wide | 0 | Hire per Week | M2 (LxH) | 0.49
9 | E11/K149/SK/dm/213 | Independent 1.8m wide | 0 | Erect & Dismantle | M2 (LxH) | 16.76
10 | E11/K149/SK/dm/213 | Independent 1.8m wide | 0 | Hire per Week | M2 (LxH) | 0.77
11 | E11/K149/SK/dm/213 | Birdcage | 0 | Erect & Dismantle | M3 | 7.08
12 | E11/K149/SK/dm/213 | Birdcage | 0 | Hire per Week | M3/Day | 0.49
13 | E11/K149/SK/dm/213 | Heavy duty birdcage | 0 | Erect & Dismantle | M3 | 10
14 | E11/K149/SK/dm/213 | Heavy duty birdcage | 0 | Hire per Week | M3/Day | 0.91
15 | E11/K149/SK/dm/213 | Buttress | 0 | Erect & Dismantle | M3 | 5.29
16 | E11/K149/SK/dm/213 | Buttress | 0 | Hire per Week | M3/Day | 0.35
17 | E11/K149/SK/dm/213 | Boarded lift | 0 | Erect & Dismantle | M2 (LxW) | 6.63
18 | E11/K149/SK/dm/213 | Boarded lift | 0 | Hire per Week | M2 (LxW) | 0.7
19 | E11/K149/SK/dm/213 | Cantilever (0 < 0.5m width) | 0 | Erect & Dismantle | M2 (LxW) | 32.75
20 | E11/K149/SK/dm/213 | Cantilever (0 < 0.5m width) | 0 | Hire per Week | M2 (LxW) | 1.05
21 | E11/K149/SK/dm/213 | Cantilever (0.5 > 1.2m width) | 0 | Erect & Dismantle | M2 (LxW) | 36.52
22 | E11/K149/SK/dm/213 | Cantilever (0.5 > 1.2m width) | 0 | Hire per Week | M2 (LxW) | 2.94
23 | E11/K149/SK/dm/213 | Bridge | 0 | Erect & Dismantle | Linear Meter | 37.43
24 | E11/K149/SK/dm/213 | Bridge | 0 | Hire per Week | Linear Meter | 1.4
25 | E11/K149/SK/dm/213 | Counterweight (Scaffold Tubes) | 0 | Erect & Dismantle | Linear Meter | 0.3
26 | E11/K149/SK/dm/213 | Counterweight (Scaffold Tubes) | 0 | Hire per Week | Linear Meter | 0.14
27 | E11/K149/SK/dm/213 | Edge protection - A Frame Single | 0 | Erect & Dismantle | Linear Meter | 7
28 | E11/K149/SK/dm/213 | Edge protection - A Frame Single | 0 | Hire per Week | Linear Meter | 0.42
29 | E11/K149/SK/dm/213 | Edge protection - A Frame double | 0 | Erect & Dismantle | Linear Meter | 12
30 | E11/K149/SK/dm/213 | Edge protection - A Frame double | 0 | Hire per Week | Linear Meter | 0.7
31 | E11/K149/SK/dm/213 | Edge Protection - Double | 0 | Erect & Dismantle | Linear Meter | 15
32 | E11/K149/SK/dm/213 | Edge Protection - Double | 0 | Hire per Week | Linear Meter | 0.91
33 | E11/K149/SK/dm/213 | Edge Protection - Double (Hilti) | 0 | Erect & Dismantle | Linear Meter | 24
34 | E11/K149/SK/dm/213 | Edge Protection - Double (Hilti) | 0 | Hire per Week | Linear Meter | 0.7
35 | E11/K149/SK/dm/213 | Netting supply - Beige Colour | 0 | Supply only | M2 (LxH) | 4.52
36 | E11/K149/SK/dm/213 | Netting install | 0 | Supply only | M2 (LxH) | 4
37 | E11/K149/SK/dm/213 | Staircase Supported by structure | 0 | Erect & Dismantle | Rising Meter | 250
38 | E11/K149/SK/dm/213 | Staircase Supported by structure | 0 | Hire per Week | Rising Meter | 14.35
39 | E11/K149/SK/dm/213 | Staircase supported by Buttress | 0 | Erect & Dismantle | Rising Meter | 376.2
40 | E11/K149/SK/dm/213 | Staircase supported by Buttress | 0 | Hire per Week | Rising Meter | 40.11
41 | E11/K149/SK/dm/213 | Manpower - Scaffolder | 0 | Dayworks | Hour | 20.5
42 | E11/K149/SK/dm/213 | Manpower - Foreman | 0 | Dayworks | Hour | 24
43 | E11/K149/SK/dm/216 | Aluminium Tower | 0 | Erect & Dismantle | Set | 0
44 | E11/K149/SK/dm/216 | Aluminium Tower | 0 | Hire per Week | Set | 28.5714
45 | E11/K149/SK/dm/238 | Design - TAS-1399-10A | 1 | Erect & Dismantle | Lumpsum | 6044.84
46 | E11/K149/SK/dm/238 | Design - TAS-1399-10A | 1 | Hire per Week | Hire per Week | 45.3871
47 | E11/K149/SK/dm/239 | Design - TAS-1399-7 | 1 | Erect & Dismantle | Lumpsum | 16252.45
48 | E11/K149/SK/dm/239 | Design - TAS-1399-7 | 1 | Hire per Week | Hire per Week | 89.4243
49 | E11/K149/SK/dm/256 | Balcony Scaffold - Type1 | 1 | Erect & Dismantle | Lumpsum | 4844.83
50 | E11/K149/SK/dm/256 | Balcony Scaffold - Type1 | 1 | Hire per Week | Hire per Week | 15.99
51 | E11/K149/SK/dm/256 | Balcony Scaffold - Type2 | 1 | Erect & Dismantle | Lumpsum | 4990.83
52 | E11/K149/SK/dm/256 | Balcony Scaffold - Type2 | 1 | Hire per Week | Hire per Week | 17.4214
53 | E11/K149/SK/dm/256 | Balcony Scaffold - Type3 | 1 | Erect & Dismantle | Lumpsum | 5095.97
54 | E11/K149/SK/dm/256 | Balcony Scaffold - Type3 | 1 | Hire per Week | Hire per Week | 18.45
55 | E11/K149/SK/dm/256 | Balcony Scaffold - Type4 | 1 | Erect & Dismantle | Lumpsum | 4127.36
56 | E11/K149/SK/dm/256 | Balcony Scaffold - Type4 | 1 | Hire per Week | Hire per Week | 8.4371
57 | E11/K149/SK/dm/256 | Balcony Scaffold - Type5 | 1 | Erect & Dismantle | Lumpsum | 8714.14
58 | E11/K149/SK/dm/256 | Balcony Scaffold - Type5 | 1 | Hire per Week | Hire per Week | 38.73
59 | E11/K149/SK/dm/256 | Balcony Scaffold - Type6 | 1 | Erect & Dismantle | Lumpsum | 5210.58
60 | E11/K149/SK/dm/256 | Balcony Scaffold - Type6 | 1 | Hire per Week | Hire per Week | 19.3229
61 | E11/K149/SK/dm/256 | Balcony Scaffold - Type7 | 1 | Erect & Dismantle | Lumpsum | 5900.72
62 | E11/K149/SK/dm/256 | Balcony Scaffold - Type7 | 1 | Hire per Week | Hire per Week | 26.07
63 | E11/K149/SK/dm/257 | Design - TAS-1399-02D | 1 | Erect & Dismantle | Lumpsum | 53510.26
64 | E11/K149/SK/dm/257 | Design - TAS-1399-02D | 1 | Hire per Week | Hire per Week | 401
65 | E11/K149/SK/dm/259 | Design - TAS-1399-06B | 1 | Erect & Dismantle | Lumpsum | 158449.11
66 | E11/K149/SK/dm/259 | Design - TAS-1399-06B | 1 | Hire per Week | Hire per Week | 2018.4243
67 | CONTRACT - 201A22002/49
68 | E11/K149/HN/dm/285 | Design-TAS-1399-12 | 1 | Erect & Dismantle | Lumpsum | 5083.25
69 | E11/K149/HN/dm/285 | Design-TAS-1399-12 | 1 | Hire per Week | Hire per Week | 123.48
70 | E11/K149/SK/dm/365 |  | 1 | Erect & Dismantle | Lumpsum | 5979.17
71 | E11/K149/SK/dm/350 | Design-TAS-1399-14 | 1 | Erect & Dismantle | Lumpsum | 14003.16
72 | E11/K149/SK/dm/350 | Design-TAS-1399-14 | 1 | Hire per Week | Hire per Week | 660.1
73 | E11/K149/SK/dm/300 | Design-Tas-1399-13A | 1 | Erect & Dismantle | Lumpsum | 4082.38
74 | E11/K149/SK/dm/300 | Design-Tas-1399-13A | 1 | Hire per Week | Hire per Week | 49.28
75 | E11/K149/SK/dm/341 |  | 1 | Erect & Dismantle | Lumpsum | 5325.76
76 | E11/K149/SK/dm/341 |  | 1 | Hire per Week | Hire per Week | 48.26
77 | E11/K149/SK/dm/341 |  | 1 | Erect & Dismantle | Lumpsum | 1375.16
78 | E11/K149/SK/dm/341 |  | 1 | Hire per Week | Hire per Week | 6.17
79 | E11/K149/MS/dm/396 |  | 1 | Erect & Dismantle | Lumpsum | 2448.62
80 | E11/K149/MS/dm/396 |  | 1 | Hire per Week | Hire per Week | 57.19
81 | E11/K149/PK/dm/400 | Design-Tas-1399-22 | 1 | Erect & Dismantle | Lumpsum | 15415.16
82 | E11/K149/PK/dm/400 | Design-Tas-1399-22 | 1 | Hire per Week | Hire per Week | 297.83
83 | E11/K149/PK/dm/378 | Design -Tas-1399-21 | 1 | Erect & Dismantle | Lumpsum | 11289.34
84 | E11/K149/PK/dm/378 | Design -Tas-1399-21 | 1 | Hire per Week | Hire per Week | 1429.84
85 | E11/K149/JA/dm/429 |  | 1 | Erect & Dismantle | Lumpsum | 13590.73
86 | E11/K149/JA/dm/429 |  | 1 | Hire per Week | Hire per Week | 302.12
87 | E11/K149/JJ/dm/377 | Design -Tas-1399-20a | 1 | Erect & Dismantle | Lumpsum | 32825.12
88 | E11/K149/JJ/dm/377 | Design -Tas-1399-20a | 1 | Hire per Week | Hire per Week | 2044.24
89 | E11/K149/SK/dm/468 |  | 1 | Erect & Dismantle | Lumpsum | 4760.74
90 | E11/K149/SK/dm/468 |  | 1 | Hire per Week | Hire per Week | 414.05
91 | E11/K149/MS/dm/497 | Design -Tas-1399-30&31 | 1 | Erect & Dismantle | Lumpsum | 13067.86
92 | E11/K149/MS/dm/497 | Design -Tas-1399-30&31 | 1 | Hire per Week | Hire per Week | 788.67
93 | E11/K149/SK/SR/517 | Design - Tas-1399-35b | 1 | Erect & Dismantle | Lumpsum | 3675.3
94 | E11/K149/SK/SR/517 | Design - Tas-1399-35b | 1 | Hire per Week | Hire per Week | 54.93
95 | E11/K149/SK/dm/480 | Design - Tas- 1399-25a | 1 | Erect & Dismantle | Lumpsum | 3562.04
96 | E11/K149/SK/dm/480 | Design - Tas- 1399-25a | 1 | Hire per Week | Hire per Week | 181.02
97 | E11/K149/SK/SR/503 | Design - Tas - 1399-29 | 1 | Erect & Dismantle | Lumpsum | 36307.15
98 | E11/K149/SK/SR/503 | Design - Tas - 1399-29 | 1 | Hire per Week | Hire per Week | 1384.55
99 | E11/K149/SK/SR/550 | Aluminium Tower |  | Erect & Dismantle | Set | 0
100 | E11/K149/SK/SR/550 | Aluminium Tower |  | Hire per Week | Set | 275
101 | E11/K149/SK/SR/560 | Aluminium Tower |  | Erect & Dismantle | Set | 0
102 | E11/K149/SK/SR/560 | Aluminium Tower |  | Hire per Week | Set | 275
103 | E11/K149/SK/SR/582 | Design - TAS-1399-39 |  | Erect & Dismantle | Lumpsum | 5018.12
104 | E11/K149/SK/SR/582 | Design - TAS-1399-39 |  | Hire per Week | Hire per Week | 212.24
105 | E11/K149/SK/SR/585 | Temp. Rack |  | Erect & Dismantle | Lumpsum | 3833.1
106 | E11/K149/SK/SR/585 | Temp. Rack |  | Hire per Week | Hire per Week | 95.83
107 | E11/K149/MS/DM/647 | Design -Tas-1399-37a |  | Erect & Dismantle | Lumpsum | 7773.97
108 | E11/K149/MS/DM/647 | Design -Tas-1399-37a |  | Hire per Week | Hire per Week | 125.44
109 | E11/K149/SMF/DM/641 | Design-Tas-1399-43 |  | Erect & Dismantle | Lumpsum | 8057.37
110 | E11/K149/SMF/DM/641 | Design-Tas-1399-43 |  | Hire per Week | Hire per Week | 212.35
111 | E11/K149/SMF/DM/756 | Design-Tas-1399-48 |  | Erect & Dismantle | Lumpsum | 2040.31
112 | E11/K149/SMF/DM/756 | Design-Tas-1399-48 |  | Hire per Week | Hire per Week | 17.43
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174

## Manpower (hidden)
Client: | Khansaheb Civil Engineering LLC
Application No.: | 6
Project Name: | Dorchester Hotel & Residences (Completion Works)
Site: | #REF!
As Of: | 2023-02-25
Modification Hours
DTS | Date | Scaffolder | Foreman | Cumulative | Previous | Net
Total |  |  |  | 0 | 0 | 0

## SCOPE (hidden)
SCOPE OF WORKS & ADDITIONAL WORKS RATES
Reference | Description | Number | L | W | H | BL | Item Price | Period (Wks) | Extra Hire per Week

## PASummary (hidden)
Client: | Khansaheb Civil Engineering LLC
Project Name: | Dorchester Hotel & Residences (Completion Works)
Contract Ref: | 201A22002/49
PAYMENT APPLICATION SUMMARY
Application No. | Application Date | Works Carried Out | Day Works | Total | Remarks
1 | 2022-09-30 | 125287.35 | 0 | 125287.35
2 | 2022-10-31 | 221656.79 | 1,271.00 | 222927.79
3 | 2022-11-25 | 254058.2 | 1599 | 255657.2
0
0
0
0
0
Total |  | 601002.34 | 1599 | 603872.34 | 0