## PA Front Sheet
PAYMENT APPLICATION
Application # 3
Khansaheb Civil Engineering L.L.C. | Date | 2022-11-30 |  |  |  |  | HOTEL
PO Box - 2716 | Period As on | 2022-11-25 |  |  |  |  | RESIDENCE
Dubai | Type | Scaffolding Services
United Arab Emirates | Our Bankers | Bank Of Sharjah
Tel : 971 04 605 7200
Fax : 971 04 285 7539 | Account No. | 013 06 278065 01
Attn: Mr. Saman Kulasooriya
Dorchester Hotel & Residences (Completion Works) - 201A22002/49
Certified Amount
Description | Previous Invoiced (AED) | This Application Value (AED) | Total Invoiced Net To Date (AED) | Previous Invoiced (AED) | This Application Value (AED) | Total Invoiced Net To Date (AED)
Contract Ref 201A22002/49
Scope Of Work | 159933.86 | 28255.17 | 188189.03 | 159933.86 | 28255.17 | 188189.03
Varitaions | 187009.85 | 225803.03 | 412812.88 | 186524.14 | 225044.85 | 411568.99
Dayworks | 1271 | 1599 | 2870 | 1271 | 1599 | 2870
Total | 347729 | 255657.2 | 603871.91 | 347729 | 254899.02 | 602628.02
AED : Two Hundred Fifty-Five Thousand Six Hundred Fifty-Seven and Twenty Fils Only
(for Client use only) | Authorised Signatory
Technical Access Services LLC
The above amount is not inclusive of VAT

## Evaluation
Invoice Schedule
Khansaheb Civil Engineering LLC
Application No.: | 3
Project Name: | Dorchester Hotel & Residences (Completion Works)
Order Reference: | 201A22002/49
As On Date: | 2022-11-25
Billing Reference | Location | Tag No. | HOC | OHC | Description | Founding Level | Scaffold Type | Number | Length | Width | Height | Board Lift | Unit of Measure | Quantity | HOC Date | OHC Date | Erection % | Hire % | Dismantle % | Hire Weeks | E&D Rate per unit | Hire Rate per week | Erect Charges | Hire Charges | Dismantle Charges | Total Amount | Previous Amount | Net Amount | Remarks | Certified Amount (Previous) | Certified Amount (This Month) | Certified Amount (Cum) | Comments
E11/K149/SK/dm/257 | HOTEL | 1 | 74602 |  | Level-28/29 Block & Glass Work | Level 28-29 | Design-1399-02 rev-D | 1 |  |  |  |  | unit | 1 | 2022-09-26 |  | 100% | 100% | 0% | 8.7143 | 50703.26 | 2807 | 35492.28 | 24461 | 0 | 59953.28 | 47522.28 | 12431 | Tas Quote-2439-4-3 rev1 | 47522.28 | 12431 | 59953.28 | 0
E11/K149/SK/dm/216 | RESIDENCE |  |  |  | Hire of Aluminium Tower | NA | NA | 1 |  |  |  |  | unit | 1 | 2022-09-15 | 2022-10-01 | 0% | 100% | 0% | 2.4286 | 0 | 200 | 0 | 485.71 | 0 | 485.71 | 485.71 | 0 | TAS/HIRE/4969/SM | 485.71 | 0 | 485.71 | 0
CONTRACT - 201A22002/49 | RESIDENCE |  |  |  | Contract Scope - Progressive Billing |  |  | 1 |  |  |  |  | unit | 1 | 2022-09-20 |  | 95% | 95% | 0% | 9.5714 | 191160 | 6716 | 127121.4 | 61067.63 | 0 | 188189.03 | 159933.86 | 28255.17 |  | 159933.86 | 28255.17 | 188189.03 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1b | 74653 | 76751 | Glass Channel Fixing | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 25.2 | 1.2 | 1 | 1 | m2-LxW | 30.24 | 2022-09-20 | 2022-09-26 | 100% | 100% | 100% | 1 | 36.52 | 2.94 | 773.06 | 88.91 | 331.31 | 1193.28 | 1193.28 | 0 |  | 1193.28 | 0 | 1193.28 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1f | 74654 |  | Glass Channel Fixing | Level 29 | Cantilever (0 < 0.5m width) | 1 | 5 | 0.5 | 1 | 1 | m2-LxW | 2.5 | 2022-09-20 |  | 100% | 100% | 0% | 9.5714 | 32.75 | 1.05 | 57.31 | 25.13 | 0 | 82.44 | 70.81 | 11.63 |  | 70.81 | 11.63 | 82.44 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1h | 74655 | 76752 | Glass Channel Fixing | Level 30 | Cantilever (0 < 0.5m width) | 1 | 16.2 | 0.5 | 1 | 1 | m2-LxW | 8.1 | 2022-09-21 | 2022-09-27 | 100% | 100% | 100% | 1 | 32.75 | 1.05 | 185.69 | 8.51 | 79.58 | 273.78 | 273.78 | 0 |  | 273.78 | 0 | 273.78 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1i | 74660 | 76753 | Glass Channel Fixing | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 1.8 | 1 | 1 | 1 | m2-LxW | 1.8 | 2022-09-24 | 2022-09-26 | 100% | 100% | 100% | 0.42857 | 36.52 | 2.94 | 46.02 | 2.27 | 19.72 | 68.01 | 68.01 | 0 |  | 68.01 | 0 | 68.01 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1j | 74666 | 76754 | Glass Channel Fixing | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 23.4 | 0.75 | 1 | 1 | m2-LxW | 17.55 | 2022-09-26 | 2022-09-28 | 100% | 100% | 100% | 0.42857 | 36.52 | 2.94 | 448.65 | 22.11 | 192.28 | 663.04 | 663.04 | 0 |  | 663.04 | 0 | 663.04 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1k | 74670 |  | Glass Channel Fixing | Level 30 | Cantilever (0 < 0.5m width) | 2 | 9.8 | 0.5 | 1 | 1 | m2-LxW | 9.8 | 2022-09-28 |  | 100% | 100% | 0% | 8.4286 | 32.75 | 1.05 | 224.67 | 86.73 | 0 | 311.4 | 291.69 | 19.71 |  | 291.69 | 19.71 | 311.4 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1l | 74671 |  | Glass Channel Fixing | Level 30 | Cantilever (0 < 0.5m width) | 1 | 13.8 | 0.5 | 1 | 1 | m2-LxW | 6.9 | 2022-09-28 |  | 100% | 100% | 0% | 8.4286 | 32.75 | 1.05 | 158.18 | 61.07 | 0 | 219.25 | 187.16 | 32.09 |  | 187.16 | 32.09 | 219.25 | 0
E11/K149/SK/dm/213 | RESIDENCE | 2a | 74662 |  | Glass Channel Fixing | Level 30 | Additional Boarding | 4 | 10.8 | 1.8 | 1 | 4 | m2-LxW | 77.76 | 2022-09-22 |  | 100% | 100% | 0% | 9.2857 | 6.63 | 0.7 | 360.88 | 505.44 | 0 | 866.32 | 625.26 | 241.06 |  | 625.26 | 241.06 | 866.32 | 0
E11/K149/SK/dm/213 | RESIDENCE | 2b | 74663 | 76758 | Colum G-3 Painting Works | Level 30 | Additional Boarding | 4 | 3.6 | 3.6 | 1 | 4 | m2-LxW | 51.84 | 2022-09-22 | 2022-10-15 | 100% | 100% | 100% | 3.4286 | 6.63 | 0.7 | 240.59 | 124.42 | 103.11 | 468.12 | 468.12 | 0 |  | 468.12 | 0 | 468.12 | 0
E11/K149/SK/dm/213 | RESIDENCE | 2c | 74664 | 76759 | Colum F-3 Painting Works | Level 30 | Additional Boarding | 4 | 3.6 | 3.6 | 1 | 4 | m2-LxW | 51.84 | 2022-09-22 | 2022-10-15 | 100% | 100% | 100% | 3.4286 | 6.63 | 0.7 | 240.59 | 124.42 | 103.11 | 468.12 | 468.12 | 0 |  | 468.12 | 0 | 468.12 | 0
E11/K149/SK/dm/213 | RESIDENCE | 2d | 74665 | 76760 | Colum D-3 Painting Works | Level 30 | Additional Boarding | 4 | 3.6 | 3.6 | 1 | 4 | m2-LxW | 51.84 | 2022-09-22 | 2022-10-15 | 100% | 100% | 100% | 3.4286 | 6.63 | 0.7 | 240.59 | 124.42 | 103.11 | 468.12 | 468.12 | 0 |  | 468.12 | 0 | 468.12 | 0
E11/K149/SK/dm/213 | RESIDENCE | 3a | 74668 | 76761 | Colum D-2 Painting Works | Level 29 | Additional Boarding | 6 | 3.5 | 3.5 | 1 | 6 | m2-LxW | 73.5 | 2022-09-27 | 2022-10-15 | 100% | 100% | 100% | 2.7143 | 6.63 | 0.7 | 341.11 | 139.65 | 146.19 | 626.95 | 626.95 | 0 |  | 626.95 | 0 | 626.95 | 0
E11/K149/SK/dm/213 | RESIDENCE | 3b | 74669 | 76762 | Colum F-G/2 Painting Works | Level 29 | Additional Boarding | 6 | 9 | 3.5 | 1 | 6 | m2-LxW | 189 | 2022-09-27 | 2022-10-15 | 100% | 100% | 100% | 2.7143 | 6.63 | 0.7 | 877.15 | 359.1 | 375.92 | 1612.17 | 1612.17 | 0 |  | 1612.17 | 0 | 1612.17 | 0
E11/K149/SK/dm/239 | RESIDENCE | 4 | 74673 | 76788 | EIFS Removel & Reinstate Works | Ramp | Design-1399-07 rev-B | 1 |  |  |  |  | unit | 1 | 2022-10-01 | 2022-11-05 | 100% | 100% | 100% | 5.1429 | 15626.48 | 625.97 | 10938.54 | 3219.27 | 4687.94 | 18845.75 | 13174.15 | 5671.6 | Tas Quote - 2439-8-2 | 13174.15 | 5671.6 | 18845.75 | 0
E11/K149/SK/dm/238 | RESIDENCE | 5 | 74675 | 76768 | Level -30 Lobby Room Shaft-09 | Level 30 | Design -1399-10 rev-A | 1 |  |  |  |  | unit | 1 | 2022-10-03 | 2022-10-22 | 100% | 100% | 100% | 2.8571 | 5727.13 | 317.71 | 4008.99 | 907.74 | 1718.14 | 6634.87 | 6634.87 | 0 | Tas Quote - 2439-5-1 | 6634.87 | 0 | 6634.87 | 0
E11/K149/SK/dm/213 | RESIDENCE | 2e | 74676 | 76755 | Level - 30 Balcony Side Glass frame work | Level 30 | Additional Boarding | 1 | 3.6 | 1.8 | 1 | 1 | m2-LxW | 6.48 | 2022-10-04 | 2022-10-07 | 100% | 100% | 100% | 0.57143 | 6.63 | 0.7 | 30.07 | 2.59 | 12.89 | 45.55 | 45.55 | 0 |  | 45.55 | 0 | 45.55 | 0
E11/K149/HN/dm/285 | RESIDENCE | 6 | 74677 |  | Loading Bay Above Planter Trench | Ground Level | Design -1399-12 rev-A | 1 |  |  |  |  | unit | 1 | 2022-10-10 |  | 100% | 100% | 0% | 6.7143 | 4959.77 | 123.48 | 3471.84 | 829.08 | 0 | 4300.92 | 3754.08 | 546.84 | Tas Quote - 2439-10-1 | 3754.08 | 546.84 | 4300.92 | 0
E11/K149/SK/dm/213 | RESIDENCE | 7 | 74678 |  | Level -4 Planter Box Soil Filling | Level 4 | Independent | 1 | 15 | 1.5 | 0.8 | 1 | m2-LxH | 12 | 2022-10-10 |  | 100% | 100% | 0% | 6.7143 | 12.01 | 0.49 | 100.88 | 39.48 | 0 | 140.36 | 114.32 | 26.04 |  | 114.32 | 26.04 | 140.36 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8h | 74679 | 76756 | Pool Area Glass work | Level 26 | Additional Boarding | 1 | 4 | 1 | 1 | 1 | m2-LxW | 4 | 2022-10-10 | 2022-10-11 | 100% | 100% | 100% | 0.28571 | 6.63 | 0.7 | 18.56 | 0.8 | 7.96 | 27.32 | 27.32 | 0 |  | 27.32 | 0 | 27.32 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8i | 74682 |  | Level -30 Glass Frame work | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 19 | 0.75 | 1 | 1 | m2-LxW | 14.25 | 2022-10-12 |  | 100% | 100% | 0% | 6.4286 | 36.52 | 2.94 | 364.29 | 269.33 | 0 | 633.62 | 448.08 | 185.54 |  | 448.08 | 185.54 | 633.62 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8j | 74683 | 76764 | Level -30 Glass Frame work | Level 30 | Cantilever (0 < 0.5m width) | 1 | 19.8 | 0.5 | 1 | 1 | m2-LxW | 9.9 | 2022-10-12 | 2022-10-21 | 100% | 100% | 100% | 1.4286 | 32.75 | 1.05 | 226.96 | 14.85 | 97.27 | 339.08 | 339.08 | 0 |  | 339.08 | 0 | 339.08 | 0
E11/K149/SK/dm/213 | RESIDENCE | 11 | 74684 | 76757 | Level -30 Shaft Mep Services | Level 30 | Independent | 1 | 3.6 | 1.2 | 2.5 | 1 | m2-LxH | 9 | 2022-10-13 | 2022-10-15 | 100% | 100% | 100% | 0.42857 | 12.01 | 0.49 | 75.66 | 1.89 | 32.43 | 109.98 | 109.98 | 0 |  | 109.98 | 0 | 109.98 | 0
E11/K149/HN/dm/285 | RESIDENCE | 12 | 74685 |  | Loading Bay Above Planter Trench | Ground Level | Design -1399-12 rev-A | 1 |  |  |  |  | unit | 1 | 2022-10-14 |  | 100% | 100% | 0% | 6.1429 | 4959.77 | 123.48 | 3471.84 | 758.52 | 0 | 4230.36 | 3683.52 | 546.84 | Tas Quote - 2439-10-1 | 3683.52 | 546.84 | 4230.36 | 0
E11/K149/SK/dm/213 | RESIDENCE | 13 | 74686 | 80503 | Pool Plant Room (KMEP Work) | Level 3 | Independent | 1 | 7.3 | 1.3 | 1.7 | 1 | m2-LxH | 12.41 | 2022-10-14 | 2022-11-10 | 100% | 100% | 100% | 4 | 12.01 | 0.49 | 104.33 | 24.32 | 44.71 | 173.36 | 114.75 | 58.61 | KMEP | 114.75 | 58.61 | 173.36 | 0
E11/K149/SK/dm/213 | RESIDENCE | 14 | 74687 | 76763 | Colum Nut bolt Installation | Level 3 | Independent | 1 | 5.1 | 1.3 | 1.6 | 1 | m2-LxH | 8.16 | 2022-10-15 | 2022-10-17 | 100% | 100% | 100% | 0.42857 | 12.01 | 0.49 | 68.6 | 1.71 | 29.4 | 99.71 | 99.71 | 0 |  | 99.71 | 0 | 99.71 | 0
E11/K149/SK/dm/213 | RESIDENCE | 15 | 74688 | 80504 | Pool Plant Room (KMEP Work) | Level 3 | Independent | 1 | 5 | 1.2 | 2 | 1 | m2-LxH | 10 | 2022-10-17 | 2022-11-10 | 100% | 100% | 100% | 3.5714 | 12.01 | 0.49 | 84.07 | 17.5 | 36.03 | 137.6 | 90.37 | 47.23 | KMEP | 90.37 | 47.23 | 137.6 | 0
E11/K149/SK/dm/213 | RESIDENCE | 16 | 74689 | 76766 | Shaft -6 Kmep Duct Extension | Level 31 | Tower | 1 | 2.5 | 1.8 | 2.3 | 1 | rm | 2.3 | 2022-10-17 | 2022-10-22 | 100% | 100% | 100% | 0.85714 | 63.34 | 7.28 | 101.98 | 14.35 | 43.7 | 160.03 | 160.03 | 0 | KMEP | 160.03 | 0 | 160.03 | 0
E11/K149/SK/dm/213 | RESIDENCE | 16 | 74689 | 76766 | Shaft -6 Kmep Duct Extension | Level 31 | Additional Boarding | 1 | 2.5 | 1.8 | 1 | 1 | m2-LxW | 4.5 | 2022-10-17 | 2022-10-22 | 100% | 100% | 100% | 0.85714 | 6.63 | 0.7 | 20.88 | 2.7 | 8.95 | 32.53 | 32.53 | 0 | KMEP | 32.53 | 0 | 32.53 | 0
E11/K149/SK/dm/213 | RESIDENCE | 17 | 74690 | 76769 | Level -2 Retail Unit 34 For (Kmep) | Level 2 | Birdcage | 1 | 17.5 | 10 | 6.2 | 1 | m3 | 1085 | 2022-10-18 | 2022-10-26 | 100% | 100% | 100% | 1.2857 | 7.08 | 0.49 | 5377.26 | 683.55 | 2304.54 | 8365.35 | 5984.86 | 2380.49 | KMEP | 5984.86 | 2380.49 | 8365.35 | 0
E11/K149/SK/dm/213 | RESIDENCE | 18 | 74691 | 80506 | Basement 1 (Kmep work) | Basement 1 | Tower | 1 | 1.8 | 1.3 | 2.5 | 1 | rm | 2.5 | 2022-10-18 | 2022-11-12 | 100% | 100% | 100% | 3.7143 | 63.34 | 7.28 | 110.85 | 67.6 | 47.51 | 225.96 | 131.65 | 94.31 | KMEP | 131.65 | 94.31 | 225.96 | 0
E11/K149/SK/dm/213 | RESIDENCE | 19 | 74692 |  | Staircase -4 For Water coring tank work | Level 31 | Independent | 1 | 4 | 1.3 | 6.3 | 1 | m2-LxH | 25.2 | 2022-10-18 |  | 100% | 100% | 0% | 5.5714 | 12.01 | 0.49 | 211.86 | 68.8 | 0 | 280.66 | 225.97 | 54.69 |  | 225.97 | 54.69 | 280.66 | 0
E11/K149/SK/dm/213 | RESIDENCE | 19a | 74700 | 76793 | Staircase -4 For Water coring tank work | Level 31 | Independent | 1 | 4 | 1.3 | 2 | 1 | m2-LxH | 8 | 2022-10-19 | 2022-11-05 | 100% | 100% | 100% | 2.5714 | 12.01 | 0.49 | 67.26 | 10.08 | 28.82 | 106.16 | 71.18 | 34.98 |  | 71.18 | 34.98 | 106.16 | 0
E11/K149/SK/dm/213 | RESIDENCE | 20 | 74693 | 80515 | Basement 1 (Kmep work) | Basement 1 | Tower | 1 | 2.5 | 2.5 | 3 | 1 | rm | 3 | 2022-10-18 | 2022-11-15 | 100% | 100% | 100% | 4.1429 | 63.34 | 7.28 | 133.01 | 90.48 | 57.01 | 280.5 | 157.97 | 122.53 |  | 157.97 | 122.53 | 280.5 | 0
E11/K149/SK/dm/213 | RESIDENCE | 16a | 74694 | 76767 | Second Lift Duct Extension work | Level 31 | Tower | 1 | 2.5 | 1.8 | 2 | 1 | rm | 2 | 2022-10-19 | 2022-10-22 | 100% | 100% | 100% | 0.57143 | 63.34 | 7.28 | 88.68 | 8.32 | 38 | 135 | 135 | 0 |  | 135 | 0 | 135 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1n | 74695 | 76771 | Fire Fifhting Sprinkler Work | Level 31 | Additional Boarding | 1 | 11.5 | 1.8 | 1 | 1 | m2-LxW | 20.7 | 2022-10-19 | 2022-10-26 | 100% | 100% | 100% | 1.1429 | 6.63 | 0.7 | 96.07 | 16.56 | 41.17 | 153.8 | 110.56 | 43.24 |  | 110.56 | 43.24 | 153.8 | 0
E11/K149/SK/dm/213 | RESIDENCE | 21 | 74696 | 76792 | Basement 1 (Kmep work) | Basement 1 | Tower | 1 | 2.5 | 1.8 | 3 | 1 | rm | 3 | 2022-10-19 | 2022-11-07 | 100% | 100% | 100% | 2.8571 | 63.34 | 7.28 | 133.01 | 62.4 | 57.01 | 252.42 | 154.85 | 97.57 | KMEP | 154.85 | 97.57 | 252.42 | 0
E11/K149/SK/dm/213 | RESIDENCE | 22 | 74697 | 76776 | Basement 1 (Kmep work) | Basement 1 | Independent | 1 | 3.1 | 1.3 | 3 | 1 | m2-LxH | 9.3 | 2022-10-19 | 2022-11-02 | 100% | 100% | 100% | 2.1429 | 12.01 | 0.49 | 78.19 | 9.77 | 33.51 | 121.47 | 82.75 | 38.72 | KMEP | 82.75 | 38.72 | 121.47 | 0
E11/K149/SK/dm/213 | RESIDENCE | 23 | 74698 |  | Basement 1 (Kmep work) | Basement 1 | Independent 1.8m wide | 1 | 3.1 | 1.8 | 4.5 | 1 | m2-LxH | 13.95 | 2022-10-19 |  | 100% | 100% | 0% | 5.4286 | 12.01 | 0.77 | 117.28 | 58.31 | 0 | 175.59 | 128.02 | 47.57 | KMEP | 128.02 | 47.57 | 175.59 | 0
E11/K149/SK/dm/213 | RESIDENCE | 24 | 74699 | 80516 | Basement 1 (Kmep work) | Basement 1 | Tower | 1 | 2.5 | 2.5 | 4.5 | 1 | rm | 4.5 | 2022-10-19 | 2022-11-15 | 100% | 100% | 100% | 4 | 63.34 | 7.28 | 199.52 | 131.04 | 85.51 | 416.07 | 232.28 | 183.79 | KMEP | 232.28 | 183.79 | 416.07 | 0
E11/K149/SK/dm/213 | RESIDENCE | 25 | 77652 | 76777 | Basement 1 (Kmep work) | Basement 1 | Independent 1.8m wide | 1 | 3.8 | 2.5 | 4.5 | 1 | m2-LxH | 17.1 | 2022-10-19 | 2022-11-02 | 100% | 100% | 100% | 2.1429 | 16.76 | 0.77 | 200.62 | 28.22 | 85.98 | 314.82 | 213.79 | 101.03 | KMEP | 213.79 | 101.03 | 314.82 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8k | 77653 | 76775 | Glass Channel Fixing | Level 31 | Cantilever (0 < 0.5m width) | 1 | 18 | 0.5 | 1 | 1 | m2-LxW | 9 | 2022-10-19 | 2022-10-29 | 100% | 100% | 100% | 1.5714 | 32.75 | 1.05 | 206.33 | 14.85 | 88.43 | 309.61 | 215.78 | 93.83 |  | 215.78 | 93.83 | 309.61 | 0
E11/K149/SK/dm/213 | RESIDENCE | 26 | 77654 | 80501 | Mockup For Bracket Fixing | Level 6 | Tower | 1 | 1.8 | 1 | 2 | 1 | rm | 2 | 2022-10-19 | 2022-11-04 | 100% | 100% | 100% | 2.4286 | 63.34 | 7.28 | 88.68 | 35.36 | 38 | 162.04 | 103.24 | 58.8 |  | 103.24 | 58.8 | 162.04 | 0
E11/K149/SK/dm/213 | RESIDENCE | 27 | 77655 | 80525 | Basement 1 (Kmep work) | Basement 1 | Independent | 1 | 5 | 1.3 | 4.5 | 1 | m2-LxH | 22.5 | 2022-10-19 | 2022-11-16 | 100% | 100% | 100% | 4.1429 | 12.01 | 0.49 | 189.16 | 45.68 | 81.07 | 315.91 | 200.19 | 115.72 | KMEP | 200.19 | 115.72 | 315.91 | 0
E11/K149/SK/dm/213 | RESIDENCE | 28 | 77656 | 80507 | Basement 1 (Kmep work) | Basement 1 | Tower | 1 | 2.5 | 1.8 | 4.5 | 1 | rm | 4.5 | 2022-10-20 | 2022-11-11 | 100% | 100% | 100% | 3.2857 | 63.34 | 7.28 | 199.52 | 107.64 | 85.51 | 392.67 | 227.6 | 165.07 | KMEP | 227.6 | 165.07 | 392.67 | 0
E11/K149/SK/dm/213 | RESIDENCE | 28 | 77656 | 80507 | Basement 1 (Kmep work) | Basement 1 | Additional Boarding | 1 | 2.5 | 1.8 |  | 1 | m2-LxW | 4.5 | 2022-10-20 | 2022-11-11 | 100% | 100% | 100% | 3.2857 | 6.63 | 0.7 | 20.88 | 10.35 | 8.95 | 40.18 | 23.58 | 16.6 | KMEP | 23.58 | 16.6 | 40.18 | 0
E11/K149/SK/dm/213 | RESIDENCE | 29 | 77657 |  | Basement 1 (Kmep work) | Basement 1 | Tower | 1 | 2.5 | 1.8 | 4.5 | 1 | rm | 4.5 | 2022-10-20 |  | 100% | 100% | 0% | 5.2857 | 63.34 | 7.28 | 199.52 | 173.16 | 0 | 372.68 | 227.6 | 145.08 | KMEP | 227.6 | 145.08 | 372.68 | 0
E11/K149/SK/dm/213 | RESIDENCE | 2g | 77661 | 76774 | Glass Fixing work | Level 30 | Cantilever (0 < 0.5m width) | 1 | 10.8 | 0.5 | 1 | 1 | m2-LxW | 5.4 | 2022-10-21 | 2022-10-29 | 100% | 100% | 100% | 1.2857 | 32.75 | 1.05 | 123.8 | 7.29 | 53.06 | 184.15 | 127.85 | 56.3 |  | 127.85 | 56.3 | 184.15 | 0
E11/K149/SK/dm/213 | RESIDENCE | 2f | 77662 |  | Glass Fixing work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 3.6 | 0.75 | 1 | 1 | m2-LxW | 2.7 | 2022-10-21 |  | 100% | 100% | 0% | 5.1429 | 36.52 | 2.94 | 69.02 | 40.82 | 0 | 109.84 | 74.69 | 35.15 |  | 74.69 | 35.15 | 109.84 | 0
E11/K149/SK/dm/365 | RESIDENCE | 30 | 77667 |  | EIFS Fixing Work | Level 23 | Independent | 1 | 4 | 1.3 | 2 | 1 | unit | 1 | 2022-10-21 |  | 100% | 100% | 0% | 5.1429 | 916.08 | 3.92 | 641.26 | 20.16 | 0 | 661.42 | 644.06 | 17.36 | Tas Quote - 2439-14-1 (item-1) | 644.06 | 17.36 | 661.42 | 0
E11/K149/SK/dm/365 | RESIDENCE | 30a | 77668 |  | EIFS Fixing Work | Level 23 | Independent | 1 | 8 | 1.3 | 3 | 2 | unit | 1 | 2022-10-21 |  | 100% | 100% | 0% | 5.1429 | 2093.27 | 22.96 | 1465.29 | 118.08 | 0 | 1583.37 | 1481.69 | 101.68 | Tas Quote - 2439-14-1 (item-2) | 1481.69 | 101.68 | 1583.37 | 0
E11/K149/SK/dm/350 | RESIDENCE | 31 | 77669 |  | Above Air Extract trench Loading Bay | Ground Level | Design 1399-14 | 1 | 22.5 | 3.6 |  | 1 | unit | 1 | 2022-10-21 |  | 100% | 100% | 0% | 5.1429 | 13343.06 | 660.1 | 9340.14 | 3394.8 | 0 | 12734.94 | 9811.64 | 2923.3 | Tas Quote - 2439-13-1 | 9811.64 | 2923.3 | 12734.94 | 0
E11/K149/SK/dm/213 | RESIDENCE | 32 | 77663 | 76779 | Hotel Side Block Work | Level 31 | Independent | 1 | 3.6 | 1.3 | 4 | 1 | m2-LxH | 14.4 | 2022-10-22 | 2022-11-03 | 100% | 100% | 100% | 1.8571 | 12.01 | 0.49 | 121.06 | 13.1 | 51.88 | 186.04 | 125.09 | 60.95 |  | 125.09 | 60.95 | 186.04 | 0
E11/K149/SK/dm/213 | RESIDENCE | 32 | 77663 | 76779 | Hotel Side Block Work | Level 31 | Additional Boarding | 1 | 3.6 | 1.3 | 1 | 1 | m2-LxW | 4.68 | 2022-10-22 | 2022-11-03 | 100% | 100% | 100% | 1.8571 | 6.63 | 0.7 | 21.72 | 6.08 | 9.31 | 37.11 | 23.59 | 13.52 |  | 23.59 | 13.52 | 37.11 | 0
E11/K149/SK/dm/213 | RESIDENCE | 33 | 77664 | 76772 | Canal Side wall Cladding opening Work | Level 14 | Tower | 1 | 1.8 | 1.3 | 1 | 1 | rm | 1 | 2022-10-22 | 2022-10-27 | 100% | 100% | 100% | 0.85714 | 63.34 | 7.28 | 44.34 | 6.24 | 19 | 69.58 | 48.5 | 21.08 |  | 48.5 | 21.08 | 69.58 | 0
E11/K149/SK/dm/213 | RESIDENCE | 34 | 77665 |  | Canal Side wall Cladding opening Work | Level 14 | Tower | 1 | 1.8 | 1.3 | 1 | 1 | rm | 1 | 2022-10-22 |  | 100% | 100% | 0% | 5 | 63.34 | 7.28 | 44.34 | 36.4 | 0 | 80.74 | 48.5 | 32.24 |  | 48.5 | 32.24 | 80.74 | 0
E11/K149/SK/dm/213 | RESIDENCE | 4d | 77670 | 76786 | EIFS work | Ground Level to Level 2 | Additional Boarding | 3 | 1.8 | 1.8 | 1 | 3 | m2-LxW | 9.72 | 2022-10-25 | 2022-11-05 | 100% | 100% | 100% | 1.7143 | 6.63 | 0.7 | 45.11 | 11.66 | 19.33 | 76.1 | 46.08 | 30.02 |  | 46.08 | 30.02 | 76.1 | 0
E11/K149/SK/dm/213 | HOTEL | 2 | 74603 | 76828 | Plant Room Façade Fin Supporting work | Level 5 | Independent 1.8m wide | 1 | 4.9 | 1.8 | 4.2 | 1 | m2-LxH | 20.58 | 2022-10-04 | 2022-11-21 | 100% | 100% | 100% | 7 | 16.76 | 0.77 | 241.44 | 110.93 | 103.48 | 455.85 | 291.24 | 164.61 |  | 291.24 | 164.61 | 455.85 | 0
E11/K149/SK/dm/213 | HOTEL | 2a | 74604 |  | Plant Room Façade Fin Supporting work | Level 5 | Independent 1.8m wide | 1 | 15.1 | 1.8 | 4.2 | 1 | m2-LxH | 63.42 | 2022-10-05 |  | 100% | 100% | 0% | 7.4286 | 16.76 | 0.77 | 744.04 | 362.76 | 0 | 1106.8 | 890.54 | 216.26 |  | 890.54 | 216.26 | 1106.8 | 0
E11/K149/SK/dm/213 | HOTEL | 2b | 74605 |  | Plant Room For AC Duct Work | Level 5 | Additional Boarding | 1 | 6.8 | 1.8 | 1 | 1 | m2-LxW | 12.24 | 2022-10-05 |  | 100% | 100% | 0% | 7.4286 | 6.63 | 0.7 | 56.81 | 63.65 | 0 | 120.46 | 82.51 | 37.95 |  | 82.51 | 37.95 | 120.46 | 0
E11/K149/SK/dm/213 | HOTEL | 2c | 74606 |  | Plant Room Façade Fin Supporting work | Level 5 | Cantilever (0.5 > 1.2m width) | 1 | 1 | 0.75 | 1 | 1 | m2-LxW | 0.75 | 2022-10-05 |  | 100% | 100% | 0% | 7.4286 | 36.52 | 2.94 | 19.17 | 16.38 | 0 | 35.55 | 25.79 | 9.76 |  | 25.79 | 9.76 | 35.55 | 0
E11/K149/SK/dm/213 | HOTEL | 3 | 74607 |  | Plant Room Façade Fin Supporting work | Level 5 | Independent 1.8m wide | 1 | 7.5 | 1.8 | 4.2 | 1 | m2-LxH | 31.5 | 2022-10-05 |  | 100% | 100% | 0% | 7.4286 | 16.76 | 0.77 | 369.56 | 180.18 | 0 | 549.74 | 442.33 | 107.41 |  | 442.33 | 107.41 | 549.74 | 0
E11/K149/SK/dm/213 | HOTEL | 3a | 74608 |  | Plant Room Façade Fin Supporting work | Level 5 | Cantilever (0 < 0.5m width) | 1 | 5 | 0.25 | 1 | 1 | m2-LxW | 1.25 | 2022-10-05 |  | 100% | 100% | 0% | 7.4286 | 32.75 | 1.05 | 28.66 | 9.75 | 0 | 38.41 | 32.6 | 5.81 |  | 32.6 | 5.81 | 38.41 | 0
E11/K149/SK/dm/213 | HOTEL | 4 | 74609 | 76802 | Air Extract Gratting Installation | Basement 1 | Independent | 1 | 9.3 | 1.3 | 5.9 | 1 | m2-LxH | 54.87 | 2022-10-07 | 2022-10-12 | 100% | 100% | 100% | 0.85714 | 12.01 | 0.49 | 461.29 | 23.05 | 197.7 | 682.04 | 682.04 | 0 |  | 682.04 | 0 | 682.04 | 0
E11/K149/SK/dm/213 | HOTEL | 4a | 74610 | 76803 | Air Extract Gratting Installation | Basement 1 | Cantilever (0 < 0.5m width) | 1 | 9.8 | 0.5 | 1 | 1 | m2-LxW | 4.9 | 2022-10-07 | 2022-10-12 | 100% | 100% | 100% | 0.85714 | 32.75 | 1.05 | 112.33 | 4.41 | 48.14 | 164.88 | 164.88 | 0 |  | 164.88 | 0 | 164.88 | 0
E11/K149/SK/dm/300 | HOTEL | 5 | 74611 | 76801 | Cradle Beam Support | Roof | Design 1399-13 rev-A | 1 | 4 | 2.5 | 2 | 1 | unit | 1 | 2022-10-07 | 2022-10-10 | 100% | 100% | 100% | 0.57143 | 4033.1 | 49.28 | 2823.17 | 28.16 | 1209.93 | 4061.26 | 4061.26 | 0 | Tas Quote - 2439-11-2 | 4061.26 | 0 | 4061.26 | 0
E11/K149/SK/dm/300 | HOTEL | 6 | 74612 | 76804 | Cradle Beam Support (Re-erction) | Roof | Design 1399-13 rev-A | 1 | 4 | 2.5 | 2 | 1 | unit | 1 | 2022-10-10 | 2022-10-26 | 100% | 100% | 100% | 2.4286 | 4033.1 | 49.28 | 2823.17 | 119.68 | 1209.93 | 4152.78 | 2935.81 | 1216.97 | Tas Quote - 2439-11-2 | 2935.81 | 1216.97 | 4152.78 | 0
E11/K149/SK/dm/213 | HOTEL | 7 | 74613 | 76807 | Planter Drain Connection (mep) | Basement 1 | Tower | 1 | 1.8 | 1.3 | 2.5 | 1 | rm | 2.5 | 2022-10-12 | 2022-11-03 | 100% | 100% | 100% | 3.2857 | 63.34 | 7.28 | 110.85 | 59.8 | 47.51 | 218.16 | 147.25 | 70.91 |  | 147.25 | 70.91 | 218.16 | 0
E11/K149/SK/dm/213 | HOTEL | 2d | 74614 |  | Planter Room Fin Supportting work | Level 5 | Additional Boarding | 1 | 4.3 | 1.5 | 1 | 1 | m2-LxW | 6.45 | 2022-10-12 |  | 100% | 100% | 0% | 6.4286 | 6.63 | 0.7 | 29.93 | 29.03 | 0 | 58.96 | 38.96 | 20 |  | 38.96 | 20 | 58.96 | 0
E11/K149/SK/dm/213 | HOTEL | 3b | 74615 |  | Planter Room Fin Supportting work | Level 5 | Independent 1.8m wide | 1 | 3 | 1.8 | 4.2 | 1 | m2-LxH | 12.6 | 2022-10-12 |  | 100% | 100% | 0% | 6.4286 | 16.76 | 0.77 | 147.82 | 62.37 | 0 | 210.19 | 167.22 | 42.97 |  | 167.22 | 42.97 | 210.19 | 0
E11/K149/SK/dm/213 | HOTEL | 3c | 74616 |  | Planter Room Fin Supportting work | Level 5 | Independent | 1 | 5 | 1.3 | 4.2 | 1 | m2-LxH | 21 | 2022-10-12 |  | 100% | 100% | 0% | 6.4286 | 12.01 | 0.49 | 176.55 | 66.15 | 0 | 242.7 | 197.13 | 45.57 |  | 197.13 | 45.57 | 242.7 | 0
E11/K149/SK/dm/213 | HOTEL | 8 | 74617 |  | Planter Room Fin Supportting work | Level 5 | Independent 1.8m wide | 1 | 10.8 | 1.8 | 3.8 | 1 | m2-LxH | 41.04 | 2022-10-13 |  | 100% | 100% | 0% | 6.2857 | 16.76 | 0.77 | 481.48 | 198.63 | 0 | 680.11 | 540.17 | 139.94 |  | 540.17 | 139.94 | 680.11 | 0
E11/K149/SK/dm/213 | HOTEL | 8a | 74618 |  | Planter Room Fin Supportting work | Level 5 | Cantilever (0 < 0.5m width) | 1 | 10.8 | 0.5 | 1 | 1 | m2-LxW | 5.4 | 2022-10-13 |  | 100% | 100% | 0% | 6.2857 | 32.75 | 1.05 | 123.8 | 35.64 | 0 | 159.44 | 134.33 | 25.11 |  | 134.33 | 25.11 | 159.44 | 0
E11/K149/SK/dm/213 | HOTEL | 3d | 74619 |  | Plant Room For Kmep Work | Level 5 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-10-15 |  | 100% | 100% | 0% | 6 | 36.52 | 2.94 | 38.35 | 26.46 | 0 | 64.81 | 45.28 | 19.53 | KMEP | 45.28 | 19.53 | 64.81 | 0
E11/K149/SK/dm/213 | HOTEL | 8b | 74620 |  | Plant Room For Kmep Work | Level 5 | Tower | 1 | 2.5 | 1.8 | 3.5 | 1 | rm | 3.5 | 2022-10-15 |  | 100% | 100% | 0% | 6 | 63.34 | 7.28 | 155.18 | 152.88 | 0 | 308.06 | 195.22 | 112.84 | KMEP | 195.22 | 112.84 | 308.06 | 0
E11/K149/SK/dm/213 | HOTEL | 8c | 74621 |  | Plant Room For Kmep Work | Level 5 | Cantilever (0 < 0.5m width) | 1 | 4.8 | 0.5 | 1 | 1 | m2-LxW | 2.4 | 2022-10-15 |  | 100% | 100% | 0% | 6 | 32.75 | 1.05 | 55.02 | 15.12 | 0 | 70.14 | 58.98 | 11.16 | KMEP | 58.98 | 11.16 | 70.14 | 0
E11/K149/SK/dm/213 | HOTEL | 9 | 74622 |  | Plant Room For Kmep Work | Level 5 | Independent | 1 | 4.5 | 1.5 | 2.3 | 1 | m2-LxH | 10.35 | 2022-10-15 |  | 100% | 100% | 0% | 6 | 12.01 | 0.49 | 87.01 | 30.43 | 0 | 117.44 | 94.98 | 22.46 | KMEP | 94.98 | 22.46 | 117.44 | 0
E11/K149/SK/dm/259 | HOTEL | 10 | 74633 |  | Inverted Scaffold | Level 29 | Design 1399 -06 rev-B | 1 | 50 | 1.8 | 4 | 1 | lm | 50 | 2022-10-20 |  | 100% | 100% | 0% | 5.2857 | 1002.22 | 98.12 | 35077.7 | 25931.71 | 0 | 61009.41 | 39282.84 | 21726.57 | Tas Quote - 2439-6-1 | 39282.41 | 21727 | 61009.41 | 0
E11/K149/SK/dm/341 | HOTEL | 11 | 74623 |  | Balcony Floor Drain Work | Level 13 | Independent | 1 | 5.7 | 1.3 | 1.5 | 1 | unit | 1 | 2022-10-20 |  | 100% | 100% | 0% | 5.2857 | 1368.99 | 6.17 | 958.29 | 32.61 | 0 | 990.9 | 963.58 | 27.32 | Tas Quote - 2439-12-2 (item-2) | 963.58 | 27.32 | 990.9 | 0
E11/K149/SK/dm/341 | HOTEL | 12 | 74625 |  | Balcony Floor Drain Work | Level 12 | Independent | 1 | 5.7 | 1.3 | 1.5 | 1 | unit | 1 | 2022-10-20 |  | 100% | 100% | 0% | 5.2857 | 1368.99 | 6.17 | 958.29 | 32.61 | 0 | 990.9 | 963.58 | 27.32 | Tas Quote - 2439-12-2 (item-2) | 963.58 | 27.32 | 990.9 | 0
E11/K149/SK/dm/341 | HOTEL | 13 | 74624 |  | Balcony Floor Drain Work | Level 14 | Independent | 1 | 5.7 | 1.3 | 1.5 | 1 | unit | 1 | 2022-10-21 |  | 100% | 100% | 0% | 5.1429 | 1368.99 | 6.17 | 958.29 | 31.73 | 0 | 990.02 | 962.7 | 27.32 | Tas Quote - 2439-12-2 (item-2) | 962.7 | 27.32 | 990.02 | 0
E11/K149/SK/dm/341 | HOTEL | 14 | 74626 |  | Balcony Floor Drain Work | Level 15 | Independent | 1 | 5.7 | 1.3 | 1.5 | 1 | unit | 1 | 2022-10-21 |  | 100% | 100% | 0% | 5.1429 | 1368.99 | 6.17 | 958.29 | 31.73 | 0 | 990.02 | 962.7 | 27.32 | Tas Quote - 2439-12-2 (item-2) | 962.7 | 27.32 | 990.02 | 0
E11/K149/SK/dm/213 | HOTEL | 10a | 74635 | 76805 | Trench Inside for Parapet Cutting | Level 29 | Additional Boarding | 1 | 50 | 1 | 1 | 1 | m2-LxW | 50 | 2022-10-20 | 2022-10-31 | 100% | 100% | 100% | 1.7143 | 6.63 | 0.7 | 232.05 | 60 | 99.45 | 391.5 | 262.05 | 129.45 |  | 262.05 | 129.45 | 391.5 | 0
E11/K149/SK/dm/259 | HOTEL | 15 | 74634 |  | Inverted Scaffold | Level 29 | Design 1399 -06 rev-B | 1 | 33 | 1.8 | 4 | 1 | lm | 33 | 2022-10-22 |  | 100% | 100% | 0% | 5 | 1002.22 | 98.12 | 23151.28 | 16189.8 | 0 | 39341.08 | 25001.54 | 14339.54 | Tas Quote - 2439-6-1 | 25001.54 | 14339.54 | 39341.08 | 0
E11/K149/SK/dm/259 | HOTEL | 15 | 74634 |  | Inverted Scaffold | Level 29 | Third Party Inspection ( Additional) | 1 |  |  |  |  | unit | 1 | 2022-10-22 | 2022-10-22 | 100% | 100% | 100% | 0.14286 | 1230 | 0 | 1230 | 0 | 0 | 1230 | 1230 | 0 | Additional Inspection | 1230 | 0 | 1230 | 0
E11/K149/SK/dm/213 | HOTEL | 15a | 74636 | 76806 | Trench Inside for Parapet Cutting | Level 29 | Additional Boarding | 1 | 33 | 1 | 1 | 1 | m2-LxW | 33 | 2022-10-22 | 2022-11-01 | 100% | 100% | 100% | 1.5714 | 6.63 | 0.7 | 153.15 | 36.3 | 65.64 | 255.09 | 166.35 | 88.74 |  | 166.35 | 88.74 | 255.09 | 0
E11/K149/SK/dm/213 | HOTEL | 16 | 74627 | 76810 | EIFS work Damac side Elevation | Level 2 | Independent 1.8m wide | 1 | 6.8 | 1.8 | 8 | 1 | m2-LxH | 54.4 | 2022-10-24 | 2022-11-09 | 100% | 100% | 100% | 2.4286 | 16.76 | 0.77 | 638.22 | 101.73 | 273.52 | 1013.47 | 650.19 | 363.28 |  | 650.19 | 363.28 | 1013.47 | 0
E11/K149/SK/dm/213 | HOTEL | 16a | 74628 | 76811 | EIFS work Damac side Elevation | Level 4 | Cantilever (0.5 > 1.2m width) | 1 | 6.8 | 1 | 1 | 1 | m2-LxW | 6.8 | 2022-10-24 | 2022-11-09 | 100% | 100% | 100% | 2.4286 | 36.52 | 2.94 | 173.84 | 48.55 | 74.5 | 296.89 | 179.55 | 117.34 |  | 179.55 | 117.34 | 296.89 | 0
E11/K149/SK/dm/213 | HOTEL | 16b | 74629 | 76812 | EIFS work Damac side Elevation | Level 2 | Butress | 1 | 2.5 | 1.8 | 5 |  | m3 | 22.5 | 2022-10-24 | 2022-11-09 | 100% | 100% | 100% | 2.4286 | 5.29 | 0.35 | 83.32 | 19.13 | 35.71 | 138.16 | 83.64 | 54.52 |  | 83.64 | 54.52 | 138.16 | 0
E11/K149/SK/dm/213 | HOTEL | 9a | 74630 |  | Plant Room Kmep Work | Level 5 | Additional Boarding | 1 | 4.5 | 1 | 1 | 1 | m2-LxW | 4.5 | 2022-10-24 |  | 100% | 100% | 0% | 4.7143 | 6.63 | 0.7 | 20.88 | 14.85 | 0 | 35.73 | 21.78 | 13.95 | KMEP | 21.78 | 13.95 | 35.73 | 0
E11/K149/SK/dm/213 | HOTEL | 9b | 74632 |  | Plant Room Kmep Work | Level 5 | Additional Boarding | 1 | 2.5 | 0.75 | 1 | 1 | m2-LxW | 1.88 | 2022-10-24 |  | 100% | 100% | 0% | 4.7143 | 6.63 | 0.7 | 8.73 | 6.2 | 0 | 14.93 | 9.11 | 5.82 | KMEP | 9.11 | 5.82 | 14.93 | 0
E11/K149/SK/dm/213 | HOTEL | 17 | 74637 |  | Plant Room Kmep Work | Level 5 | Tower | 1 | 2.5 | 1.3 | 2.5 | 1 | rm | 2.5 | 2022-10-25 |  | 100% | 100% | 0% | 4.5714 | 63.34 | 7.28 | 110.85 | 83.2 | 0 | 194.05 | 113.45 | 80.6 | KMEP | 113.45 | 80.6 | 194.05 | 0
E11/K149/SK/dm/213 | HOTEL | 17a | 74638 |  | Plant Room Kmep Work | Level 5 | Cantilever (0 < 0.5m width) | 1 | 1.5 | 0.5 | 1 | 1 | m2-LxW | 0.75 | 2022-10-25 |  | 100% | 100% | 0% | 4.5714 | 32.75 | 1.05 | 17.19 | 3.6 | 0 | 20.79 | 17.3 | 3.49 | KMEP | 17.3 | 3.49 | 20.79 | 0
E11/K149/MS/dm/396 | RESIDENCE | 35 | 77666 | 80509 | Master Pump Room Work | Level 23 | Birdcage | 1 | 5 | 4.3 | 3 | 2 | unit | 1 | 2022-10-24 | 2022-11-12 | 100% | 100% | 100% | 2.8571 | 2391.43 | 57.19 | 1674 | 163.4 | 717.43 | 2554.83 |  | 2554.83 | Tas Quote - 2439-18-1 (item-1) |  | 2554.83 | 2554.83 | 0 | 2448.62 | 2554.83 | 2448.62
E11/K149/HN/dm/285 | RESIDENCE | 36 | 77671 |  | Loading Bay Above Planter Trench | Ground Level | Design -1399-12 rev-A | 1 |  |  |  |  | unit | 1 | 2022-10-26 |  | 100% | 100% | 0% | 4.4286 | 4959.77 | 123.48 | 3471.84 | 546.84 | 0 | 4018.68 |  | 4018.68 | Tas Quote - 2439-10-1 |  | 4018.68 | 4018.68 | 0 | 5083.25 | 4018.68
E11/K149/SK/dm/213 | RESIDENCE | 8m | 77672 | 76773 | Glass Fixing work | Level 31 | Additional Boarding | 1 | 10.8 | 0.5 | 1 | 1 | m2-LxW | 5.4 | 2022-10-26 | 2022-10-28 | 100% | 100% | 100% | 0.42857 | 6.63 | 0.7 | 25.06 | 1.62 | 10.74 | 37.42 |  | 37.42 |  |  | 37.42 | 37.42 | 0 | 7.33 | 37.42
E11/K149/SK/dm/213 | RESIDENCE | 8n | 77673 |  | Glass Fixing work | Level 31 | Additional Boarding | 2 | 10.8 | 0.25 | 1 | 2 | m2-LxW | 5.4 | 2022-10-26 |  | 100% | 100% | 0% | 4.4286 | 6.63 | 0.7 | 25.06 | 16.74 | 0 | 41.8 |  | 41.8 |  |  | 41.8 | 41.8 | 0 | 7.33 | 41.8
E11/K149/SK/dm/213 | RESIDENCE | 37 | 77674 |  | Glass Fixing work | Level 7 | Tower | 1 | 2.5 | 1.3 | 1 | 1 | rm | 1 | 2022-10-28 |  | 100% | 100% | 0% | 4.1429 | 63.34 | 7.28 | 44.34 | 30.16 | 0 | 74.5 |  | 74.5 |  |  | 74.5 | 74.5 | 0 | 70.62 | 74.5
E11/K149/SK/dm/213 | RESIDENCE | 38 | 77675 | 76795 | Entrance Lobby Block Demolishing Work | Ground Level | Independent | 1 | 3.1 | 1.3 | 4.2 | 1 | m2-LxH | 13.02 | 2022-10-28 | 2022-11-04 | 100% | 100% | 100% | 1.1429 | 12.01 | 0.49 | 109.46 | 7.29 | 46.91 | 163.66 |  | 163.66 |  |  | 163.66 | 163.66 | 0 | 12.5 | 163.66
E11/K149/SK/dm/213 | RESIDENCE | 38 | 77675 | 76795 | Entrance Lobby Block Demolishing Work | Ground Level | Additional Boarding | 1 | 3.1 | 1.3 |  | 1 | m2-LxW | 4.03 | 2022-10-28 | 2022-11-04 | 100% | 100% | 100% | 1.1429 | 6.63 | 0.7 | 18.7 | 3.22 | 8.02 | 29.94 |  | 29.94 |  |  | 29.94 | 29.94 | 0 | 7.33 | 29.94
E11/K149/SK/dm/213 | RESIDENCE | 39 | 77676 |  | Existing Pipe Removal Work | Basement 1 | Birdcage | 1 | 3 | 3 | 5 | 1 | m3 | 45 | 2022-10-28 |  | 100% | 100% | 0% | 4.1429 | 7.08 | 0.49 | 223.02 | 91.35 | 0 | 314.37 |  | 314.37 |  |  | 314.37 | 314.37 | 0 | 7.57 | 314.37
E11/K149/SK/dm/213 | RESIDENCE | 40 | 77677 |  | Edge Protection | Level 31 | Double Handrail | 1 | 10 |  | 1 |  | lm | 10 | 2022-10-29 |  | 100% | 100% | 0% | 4 | 12 | 0.7 | 84 | 28 | 0 | 112 |  | 112 |  |  | 112 | 112 | 0 | 12.7 | 112
E11/K149/SK/dm/213 | RESIDENCE | 8o | 77678 |  | Glass Fixing work | Level 30 | Cantilever (0 < 0.5m width) | 1 | 10.8 | 0.5 | 1 | 1 | m2-LxW | 5.4 | 2022-10-29 |  | 100% | 100% | 0% | 4 | 32.75 | 1.05 | 123.8 | 22.68 | 0 | 146.48 |  | 146.48 |  |  | 146.48 | 146.48 | 0 | 33.8 | 146.48
E11/K149/SK/dm/213 | RESIDENCE | 41 | 77679 | 76796 | Block Demolishing Work | Ground Level | Independent | 1 | 5.4 | 1.3 | 4 | 1 | m2-LxH | 21.6 | 2022-10-29 | 2022-11-09 | 100% | 100% | 100% | 1.7143 | 12.01 | 0.49 | 181.59 | 18.14 | 77.82 | 277.55 |  | 277.55 |  |  | 277.55 | 277.55 | 0 | 12.5 | 277.55
E11/K149/SK/dm/213 | RESIDENCE | 41 | 77679 | 76796 | Block Demolishing Work | Ground Level | Additional Boarding | 1 | 5.4 | 1.3 | 1 | 1 | m2-LxW | 7.02 | 2022-10-29 | 2022-11-09 | 100% | 100% | 100% | 1.7143 | 6.63 | 0.7 | 32.58 | 8.42 | 13.96 | 54.96 |  | 54.96 |  |  | 54.96 | 54.96 | 0 | 7.33 | 54.96
E11/K149/SK/dm/213 | RESIDENCE | 41a | 77680 | 76785 | Block Demolishing Work | Ground Level | Cantilever (0 < 0.5m width) | 2 | 2 | 0.5 | 1 | 2 | m2-LxW | 2 | 2022-10-29 | 2022-11-03 | 100% | 100% | 100% | 0.85714 | 32.75 | 1.05 | 45.85 | 1.8 | 19.65 | 67.3 |  | 67.3 |  |  | 67.3 | 67.3 | 0 | 33.8 | 67.3
E11/K149/SK/dm/213 | RESIDENCE | 38a | 77681 | 76778 | Block Demolishing Work | Ground Level | Cantilever (0 < 0.5m width) | 2 | 2 | 0.5 | 1 | 2 | m2-LxW | 2 | 2022-10-29 | 2022-11-02 | 100% | 100% | 100% | 0.71429 | 32.75 | 1.05 | 45.85 | 1.5 | 19.65 | 67 |  | 67 |  |  | 67 | 67 | 0 | 33.8 | 67
E11/K149/SK/dm/213 | RESIDENCE | 39a | 77682 |  | Existing Pipe Removal Work | Basement 1 | Additional Boarding | 1 | 3 | 1.5 | 1 | 1 | m2-LxW | 4.5 | 2022-10-29 |  | 100% | 100% | 0% | 4 | 6.63 | 0.7 | 20.88 | 12.6 | 0 | 33.48 |  | 33.48 |  |  | 33.48 | 33.48 | 0 | 7.33 | 33.48
E11/K149/SK/dm/213 | RESIDENCE | 32a | 77683 | 76780 | Block Work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-10-29 | 2022-11-03 | 100% | 100% | 100% | 0.85714 | 36.52 | 2.94 | 38.35 | 3.78 | 16.43 | 58.56 |  | 58.56 |  |  | 58.56 | 58.56 | 0 | 39.46 | 58.56
E11/K149/SK/dm/213 | RESIDENCE | 4i | 77686 | 76787 | EIFS Painting up to Groove | Ground Level | Tower | 1 | 1.8 | 0.9 | 12.3 | 1 | rm | 12.3 | 2022-10-29 | 2022-11-05 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 545.36 | 102.34 | 233.72 | 881.42 |  | 881.42 |  |  | 881.42 | 881.42 | 0 | 70.62 | 881.42
E11/K149/SK/dm/213 | RESIDENCE | 4i | 77686 | 76787 | EIFS Painting up to Groove | Ground Level | Additional Boarding | 5 | 1.8 | 0.9 | 1 | 5 | m2-LxW | 8.1 | 2022-10-29 | 2022-11-05 | 100% | 100% | 100% | 1.1429 | 6.63 | 0.7 | 37.59 | 6.48 | 16.11 | 60.18 |  | 60.18 |  |  | 60.18 | 60.18 | 0 | 7.33 | 60.18
E11/K149/JJ/dm/377 | RESIDENCE | 42 | 77687 |  | Back Propping For Mast Climber | Basement 1 | Design - 1399-20 | 1 |  |  |  |  | unit | 1 | 2022-10-31 |  | 100% | 100% | 0% | 3.7143 | 7695.22 | 511.06 | 5386.65 | 1898.22 | 0 | 7284.87 |  | 7284.87 | Tas Quote 2439-16-3 (item-1) |  | 7284.87 | 7284.87 | 0 | 8206.28 | 7284.87
E11/K149/JJ/dm/377 | RESIDENCE | 43 | 77688 |  | Back Propping For Mast Climber | Basement 1 | Design - 1399-20 | 1 |  |  |  |  | unit | 1 | 2022-10-31 |  | 100% | 100% | 0% | 3.7143 | 7695.22 | 511.06 | 5386.65 | 1898.22 | 0 | 7284.87 |  | 7284.87 | Tas Quote 2439-16-3 (item-1) |  | 7284.87 | 7284.87 | 0 | 8206.28 | 7284.87
E11/K149/JJ/dm/377 | RESIDENCE | 44 | 77689 |  | Back Propping For Mast Climber | Ground Level | Design - 1399-20 | 1 |  |  |  |  | unit | 1 | 2022-10-31 |  | 100% | 100% | 0% | 3.7143 | 7695.22 | 511.06 | 5386.65 | 1898.22 | 0 | 7284.87 |  | 7284.87 | Tas Quote 2439-16-3 (item-1) |  | 7284.87 | 7284.87 | 0 | 8206.28 | 7284.87
E11/K149/SK/dm/213 | RESIDENCE | 32b | 77690 | 76781 | Block Shifting Work | Level 31 | Tower | 1 | 1.5 | 1.5 | 1 | 1 | rm | 1 | 2022-11-01 | 2022-11-03 | 100% | 100% | 100% | 0.42857 | 63.34 | 7.28 | 44.34 | 3.12 | 19 | 66.46 |  | 66.46 |  |  | 66.46 | 66.46 | 0 | 70.62 | 66.46
E11/K149/JJ/dm/377 | RESIDENCE | 45 | 77691 |  | Back Propping For Mast Climber | Ground Level | Design - 1399-20 | 1 |  |  |  |  | unit | 1 | 2022-11-01 |  | 100% | 100% | 0% | 3.5714 | 7695.22 | 511.06 | 5386.65 | 1825.21 | 0 | 7211.86 |  | 7211.86 | Tas Quote 2439-16-3 (item-1) |  | 7211.86 | 7211.86 | 0 | 8206.28 | 7211.86
E11/K149/SK/dm/213 | RESIDENCE | 19b | 77692 |  | Shaft -9 For Ducting Work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 0.75 | 1 | 2 | m2-LxW | 1.13 | 2022-10-29 |  | 100% | 100% | 0% | 4 | 36.52 | 2.94 | 28.89 | 13.29 | 0 | 42.18 |  | 42.18 |  |  | 42.18 | 42.18 | 0 | 39.46 | 42.18
E11/K149/SK/dm/213 | RESIDENCE | 19c | 77693 | 76790 | Shaft -9 For Ducting Work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-11-02 | 2022-11-04 | 100% | 100% | 100% | 0.42857 | 36.52 | 2.94 | 38.35 | 1.89 | 16.43 | 56.67 |  | 56.67 |  |  | 56.67 | 56.67 | 0 | 39.46 | 56.67
E11/K149/SK/dm/213 | RESIDENCE | 46 | 77694 |  | Electrical & Plumbing Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 4 | 1 | rm | 4 | 2022-11-03 |  | 100% | 100% | 0% | 3.2857 | 63.34 | 7.28 | 177.35 | 95.68 | 0 | 273.03 |  | 273.03 |  |  | 273.03 | 273.03 | 0 | 70.62 | 273.03
E11/K149/SK/dm/213 | RESIDENCE | 46 | 77694 |  | Electrical & Plumbing Work | Basement 1 | Additional Boarding | 1 | 2.5 | 1.3 | 1 | 1 | m2-LxW | 3.25 | 2022-11-03 |  | 100% | 100% | 0% | 3.2857 | 6.63 | 0.7 | 15.08 | 7.48 | 0 | 22.56 |  | 22.56 |  |  | 22.56 | 22.56 | 0 | 7.33 | 22.56
E11/K149/SK/dm/213 | RESIDENCE | 47 | 77695 |  | Block Work | Basement 1 | Tower | 1 | 2.5 | 1.5 | 3 | 1 | rm | 3 | 2022-11-03 |  | 100% | 100% | 0% | 3.2857 | 63.34 | 7.28 | 133.01 | 71.76 | 0 | 204.77 |  | 204.77 |  |  | 204.77 | 204.77 | 0 | 70.62 | 204.77
E11/K149/SK/dm/213 | RESIDENCE | 48 | 77696 | 80526 | Column Cove Installation Work | Ground Level | Birdcage | 1 | 11.8 | 3.8 | 3.5 | 1 | m3 | 156.94 | 2022-11-03 | 2022-11-17 | 100% | 100% | 100% | 2.1429 | 7.08 | 0.49 | 777.79 | 164.79 | 333.34 | 1275.92 |  | 1275.92 |  |  | 1275.92 | 1275.92 | 0 | 7.57 | 1275.92
E11/K149/SK/dm/213 | RESIDENCE | 49 | 77697 | 80508 | Electrical Service Work (BMS) | Basement 1 | Tower | 1 | 2.5 | 1.3 | 4.2 | 1 | rm | 4.2 | 2022-11-03 | 2022-11-12 | 100% | 100% | 100% | 1.4286 | 63.34 | 7.28 | 186.22 | 43.68 | 79.81 | 309.71 |  | 309.71 |  |  | 309.71 | 309.71 | 0 | 70.62 | 309.71
E11/K149/SK/dm/213 | RESIDENCE | 49 | 77697 | 80508 | Electrical Service Work (BMS) | Basement 1 | Additional Boarding | 1 | 2.5 | 1.3 | 1 | 1 | m2-LxW | 3.25 | 2022-11-03 | 2022-11-12 | 100% | 100% | 100% | 1.4286 | 6.63 | 0.7 | 15.08 | 3.25 | 6.46 | 24.79 |  | 24.79 |  |  | 24.79 | 24.79 | 0 | 7.33 | 24.79
E11/K149/SK/dm/213 | RESIDENCE | 50 | 77698 | 80529 | Column Cove Installation Work | Ground Level | Tower | 1 | 2.5 | 2.5 | 3.5 | 1 | rm | 3.5 | 2022-11-03 | 2022-11-18 | 100% | 100% | 100% | 2.2857 | 63.34 | 7.28 | 155.18 | 58.24 | 66.51 | 279.93 |  | 279.93 |  |  | 279.93 | 279.93 | 0 | 70.62 | 279.93
E11/K149/SK/dm/213 | RESIDENCE | 51 | 77699 | 80510 | Column Cove Installation Work | Ground Level | Tower | 1 | 2.5 | 2.5 | 3.5 | 1 | rm | 3.5 | 2022-11-03 | 2022-11-11 | 100% | 100% | 100% | 1.2857 | 63.34 | 7.28 | 155.18 | 32.76 | 66.51 | 254.45 |  | 254.45 |  |  | 254.45 | 254.45 | 0 | 70.62 | 254.45
E11/K149/SK/dm/213 | RESIDENCE | 8p | 77700 |  | Glass Fixing work | Level 31 | Cantilever (0 < 0.5m width) | 1 | 9 | 0.25 | 1 | 2 | m2-LxW | 2.25 | 2022-11-03 |  | 100% | 100% | 0% | 3.2857 | 32.75 | 1.05 | 51.58 | 7.76 | 0 | 59.34 |  | 59.34 |  |  | 59.34 | 59.34 | 0 | 33.8 | 59.34
E11/K149/SK/dm/213 | RESIDENCE | 8q | 77551 | 76791 | Glass Fixing work | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 10.8 | 1 | 1 | 1 | m2-LxW | 10.8 | 2022-11-03 | 2022-11-05 | 100% | 100% | 100% | 0.42857 | 36.52 | 2.94 | 276.09 | 13.61 | 118.32 | 408.02 |  | 408.02 |  |  | 408.02 | 408.02 | 0 | 39.46 | 408.02
E11/K149/SK/dm/213 | RESIDENCE | 38b | 77552 | 76797 | Entrance Lobby Block Work | Ground Level | Tower | 1 | 1 | 1 | 1.5 | 1 | rm | 1.5 | 2022-11-03 | 2022-11-09 | 100% | 100% | 100% | 1 | 63.34 | 7.28 | 66.51 | 10.92 | 28.5 | 105.93 |  | 105.93 |  |  | 105.93 | 105.93 | 0 | 70.62 | 105.93
E11/K149/SK/dm/213 | RESIDENCE | 38c | 77553 | 76798 | Entrance Lobby Block Work | Ground Level | Tower | 1 | 1 | 1 | 1.5 | 1 | rm | 1.5 | 2022-11-03 | 2022-11-09 | 100% | 100% | 100% | 1 | 63.34 | 7.28 | 66.51 | 10.92 | 28.5 | 105.93 |  | 105.93 |  |  | 105.93 | 105.93 | 0 | 70.62 | 105.93
E11/K149/SK/dm/213 | RESIDENCE | 52 | 77554 | 80523 | Column Cove Installation Work | Ground Level | Tower | 1 | 2.5 | 2.5 | 3.5 | 1 | rm | 3.5 | 2022-11-04 | 2022-11-16 | 100% | 100% | 100% | 1.8571 | 63.34 | 7.28 | 155.18 | 47.32 | 66.51 | 269.01 |  | 269.01 |  |  | 269.01 | 269.01 | 0 | 70.62 | 269.01
E11/K149/SK/dm/213 | RESIDENCE | 19d | 77555 | 80502 | Shaft - 9 Ducting Work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 2 | 1.5 | 1 | 1 | m2-LxW | 3 | 2022-11-04 | 2022-11-09 | 100% | 100% | 100% | 0.85714 | 36.52 | 2.94 | 76.69 | 7.56 | 32.87 | 117.12 |  | 117.12 |  |  | 117.12 | 117.12 | 0 | 39.46 | 117.12
E11/K149/SK/dm/213 | RESIDENCE | 53 | 77556 | 80511 | Balcony Side Edge Protection | Level 27 | Butress | 1 | 2.5 | 1.8 | 2 |  | m3 | 9 | 2022-11-04 | 2022-11-11 | 100% | 100% | 100% | 1.1429 | 5.29 | 0.35 | 33.33 | 3.6 | 14.28 | 51.21 |  | 51.21 |  |  | 51.21 | 51.21 | 0 | 5.64 | 51.21
E11/K149/SK/dm/213 | RESIDENCE | 53a | 77557 | 80511 | Balustrade Glass Edge Protection | Level 27 | Tripple Hnadrail | 1 | 6 |  | 1.5 |  | lm | 6 | 2022-11-04 | 2022-11-11 | 100% | 100% | 100% | 1.1429 | 15 | 0.91 | 63 | 6.24 | 27 | 96.24 |  | 96.24 |  |  | 96.24 | 96.24 | 0 | 15.91 | 96.24
E11/K149/SK/dm/213 | RESIDENCE | 54 | 77558 | 80527 | Column Cove Installation Work | Ground Level | Tower | 1 | 2.5 | 2.5 | 3.5 | 1 | rm | 3.5 | 2022-11-04 | 2022-11-17 | 100% | 100% | 100% | 2 | 63.34 | 7.28 | 155.18 | 50.96 | 66.51 | 272.65 |  | 272.65 |  |  | 272.65 | 272.65 | 0 | 70.62 | 272.65
E11/K149/SK/dm/213 | RESIDENCE | 46a | 77559 |  | Electrical Services Work | Basement 1 | Tower | 1 | 1.8 | 1.3 | 4 | 1 | rm | 4 | 2022-11-05 |  | 100% | 100% | 0% | 3 | 63.34 | 7.28 | 177.35 | 87.36 | 0 | 264.71 |  | 264.71 |  |  | 264.71 | 264.71 | 0 | 70.62 | 264.71
E11/K149/SK/dm/213 | RESIDENCE | 55 | 77560 | 80517 | Electrical Services Work | Basement 1 | Independent | 1 | 3.8 | 1.3 | 2.5 | 1 | m2-LxH | 9.5 | 2022-11-05 | 2022-11-15 | 100% | 100% | 100% | 1.5714 | 12.01 | 0.49 | 79.87 | 7.32 | 34.23 | 121.42 |  | 121.42 |  |  | 121.42 | 121.42 | 0 | 12.5 | 121.42
E11/K149/SK/dm/213 | RESIDENCE | 56 | 77561 |  | Plant Room Kmep Work | Level 5 | Tower | 1 | 2.5 | 1.8 | 4 | 1 | rm | 4 | 2022-11-05 |  | 100% | 100% | 0% | 3 | 63.34 | 7.28 | 177.35 | 87.36 | 0 | 264.71 |  | 264.71 |  |  | 264.71 | 264.71 | 0 | 70.62 | 264.71
E11/K149/SK/dm/213 | RESIDENCE | 56 | 77561 |  | Plant Room Kmep Work | Level 5 | Additional Boarding | 1 | 2.5 | 1.8 | 1 | 1 | m2-LxW | 4.5 | 2022-11-05 |  | 100% | 100% | 0% | 3 | 6.63 | 0.7 | 20.88 | 9.45 | 0 | 30.33 |  | 30.33 |  |  | 30.33 | 30.33 | 0 | 7.33 | 30.33
E11/K149/SK/dm/213 | RESIDENCE | 38d | 77562 | 76799 | Entrance Lobby Block Work | Ground Level | Tower | 1 | 1 | 1 | 1.5 | 1 | rm | 1.5 | 2022-11-05 | 2022-11-09 | 100% | 100% | 100% | 0.71429 | 63.34 | 7.28 | 66.51 | 7.8 | 28.5 | 102.81 |  | 102.81 |  |  | 102.81 | 102.81 | 0 | 70.62 | 102.81
E11/K149/SK/dm/213 | RESIDENCE | 38e | 77563 | 76800 | Entrance Lobby Block Work | Ground Level | Tower | 1 | 1 | 1 | 1.5 | 1 | rm | 1.5 | 2022-11-05 | 2022-11-09 | 100% | 100% | 100% | 0.71429 | 63.34 | 7.28 | 66.51 | 7.8 | 28.5 | 102.81 |  | 102.81 |  |  | 102.81 | 102.81 | 0 | 70.62 | 102.81
E11/K149/SK/dm/213 | RESIDENCE | 57 | 77564 |  | Electrical Services Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3.8 | 1 | rm | 3.8 | 2022-11-05 |  | 100% | 100% | 0% | 3 | 63.34 | 7.28 | 168.48 | 82.99 | 0 | 251.47 |  | 251.47 |  |  | 251.47 | 251.47 | 0 | 70.62 | 251.47
E11/K149/SK/dm/213 | RESIDENCE | 58 | 77565 | 80528 | Column Cove Installation Work | Ground Level | Independent 1.8m wide | 1 | 3.8 | 2.5 | 3.5 | 1 | m2-LxH | 13.3 | 2022-11-07 | 2022-11-17 | 100% | 100% | 100% | 1.5714 | 16.76 | 0.77 | 156.04 | 16.09 | 66.87 | 239 |  | 239 |  |  | 239 | 239 | 0 | 17.53 | 239
E11/K149/SK/dm/213 | RESIDENCE | 59 | 77566 | 76794 | Cable Tray Removal Work | Basement 1 | Independent | 1 | 8.1 | 1.3 | 3 | 1 | m2-LxH | 24.3 | 2022-11-07 | 2022-11-08 | 100% | 100% | 100% | 0.28571 | 12.01 | 0.49 | 204.29 | 3.4 | 87.55 | 295.24 |  | 295.24 |  |  | 295.24 | 295.24 | 0 | 12.5 | 295.24
E11/K149/SK/dm/213 | RESIDENCE | 8r | 77567 | 80533 | Glass Fixing work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 10.8 | 1 | 1 | 1 | m2-LxW | 10.8 | 2022-11-05 | 2022-11-25 | 100% | 100% | 100% | 3 | 36.52 | 2.94 | 276.09 | 95.26 | 118.32 | 489.67 |  | 489.67 |  |  | 489.67 | 489.67 | 0 | 39.46 | 489.67
E11/K149/SK/dm/213 | RESIDENCE | 60 | 77568 | 80512 | Balustrade Glass Edge Protection | Level 25 | Butress | 1 | 2.5 | 1.8 | 2 |  | m3 | 9 | 2022-11-07 | 2022-11-11 | 100% | 100% | 100% | 0.71429 | 5.29 | 0.35 | 33.33 | 2.25 | 14.28 | 49.86 |  | 49.86 |  |  | 49.86 | 49.86 | 0 | 5.64 | 49.86 |  |  | 15415.15 |  | S# | Erect Charge | Hire Chrge
E11/K149/SK/dm/213 | RESIDENCE | 60a | 77569 | 80512 | Balustrade Glass Edge Protection | Level 25 | Tripple Hnadrail | 1 | 3 |  | 1.5 |  | lm | 3 | 2022-11-07 | 2022-11-11 | 100% | 100% | 100% | 0.71429 | 15 | 0.91 | 31.5 | 1.95 | 13.5 | 46.95 |  | 46.95 |  |  | 46.95 | 46.95 | 0 | 15.91 | 46.95 |  |  |  |  | 1a | 1572.35 | 64.15
E11/K149/PK/dm/400 | RESIDENCE | 61 | 77578 | 80513 | OME Corridoor Mep Work | Ground Level | Design - 1399-22 | 1 | 24.3 | 1 | 4 | 1 | m2-LxH | 97.2 | 2022-11-07 | 2022-11-14 | 100% | 100% | 100% | 1.1429 | 115.4699 | 2.27 | 7856.57 | 252.16 | 3367.1 | 12234.44 |  | 12234.44 | Prorate Tas Quote - 2439-19-1 |  | 11475.83 | 11475.83 | -758.61 | 14842.9343 | 11475.83 |  |  | 9.01 |  | 2a | 1572.35 | 64.15
| RESIDENCE | 62 | 77570 |  | Back Propping For Mast Climber | Basement 1 | Design - 1399-24 | 1 |  |  |  |  | unit | 1 | 2022-11-08 |  | 100% | 100% | 0% | 2.5714 |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
| RESIDENCE | 63 | 77571 |  | Back Propping For Mast Climber | Basement 1 | Design - 1399-24 | 1 |  |  |  |  | unit | 1 | 2022-11-08 |  | 100% | 100% | 0% | 2.5714 |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 97.1 | 3.08
| RESIDENCE | 64 | 77572 |  | Back Propping For Mast Climber | Basement 2 | Design - 1399-20E | 1 |  |  |  |  | unit | 1 | 2022-11-09 |  | 100% | 100% | 0% | 2.4286 |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
| RESIDENCE | 65 | 77573 |  | Back Propping For Mast Climber | Basement 2 | Design - 1399-20E | 1 |  |  |  |  | unit | 1 | 2022-11-09 |  | 100% | 100% | 0% | 2.4286 |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 19e | 77574 | 80522 | Shaft - 9 Ducting Work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 2 | 1 | 1 | 1 | m2-LxW | 2 | 2022-11-09 | 2022-11-14 | 100% | 100% | 100% | 0.85714 | 36.52 | 2.94 | 51.13 | 5.04 | 21.91 | 78.08 |  | 78.08 |  |  | 78.08 | 78.08 | 0 | 99.99 | 78.08 |  |  |  |  | 3a | 2694.96 | 100.8
E11/K149/SK/dm/213 | RESIDENCE | 61a | 77582 | 80514 | Corridor KMEP Work | Ground Level | Independent 1.8m wide | 1 | 4 | 2.5 | 4 | 1 | m2-LxH | 16 | 2022-11-09 | 2022-11-14 | 100% | 100% | 100% | 0.85714 | 16.76 | 0.77 | 187.71 | 10.56 | 80.45 | 278.72 |  | 278.72 |  |  | 278.72 | 278.72 | 0 | 359.17 | 278.72 |  |  |  |  | 4a | 651 | 68.73
E11/K149/SK/dm/213 | RESIDENCE | 19f | 77575 | 80505 | Shaft - 9 Ducting Work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-11-10 | 2022-11-10 | 100% | 100% | 100% | 0.14286 | 36.52 | 2.94 | 38.35 | 0.63 | 16.43 | 55.41 |  | 55.41 |  |  | 55.41 | 55.41 | 0 | 71.84 | 55.41 |  |  |  |  | 5 | 836.66
E11/K149/SK/dm/213 | RESIDENCE | 66 | 77576 |  | Pool Plant Room (KMEP Work) | Level 3 | Tower | 1 | 2.5 | 1.8 | 2 | 1 | rm | 2 | 2022-11-10 |  | 100% | 100% | 0% | 2.2857 | 63.34 | 7.28 | 88.68 | 33.28 | 0 | 121.96 |  | 121.96 | (BW-0754) |  | 121.96 | 121.96 | 0 | 159.96 | 121.96 |  |  |  |  | 6 | 6560
E11/K149/SK/dm/213 | RESIDENCE | 67 | 77577 | 80530 | Entrance Area Glass Work | Ground Level | Birdcage | 1 | 3.1 | 2.6 | 4 | 1 | m3 | 32.24 | 2022-11-10 | 2022-11-19 | 100% | 100% | 100% | 1.4286 | 7.08 | 0.49 | 159.78 | 22.57 | 68.48 | 250.83 |  | 250.83 | (Glass Line - BW-002) |  | 250.83 | 250.83 | 0 | 319.3092 | 250.83 |  | 3080.72
E11/K149/SK/dm/213 | RESIDENCE | 68 | 77579 |  | Staircase - Electrical Work | Level 2 to 3 | Independent | 1 | 6.3 | 1.3 | 3 | 1 | m2-LxH | 18.9 | 2022-11-10 |  | 100% | 100% | 0% | 2.2857 | 12.01 | 0.49 | 158.89 | 21.17 | 0 | 180.06 |  | 180.06 | (BW-0754) |  | 180.06 | 180.06 | 0 | 248.159 | 180.06 | [5 empty] | 13887.32 | 297.83
E11/K149/SK/dm/213 | RESIDENCE | 68a | 77580 |  | Staircase - Electrical Work | Level 2 to 3 | Independent | 1 | 3.5 | 1.3 | 4.5 | 1 | m2-LxH | 15.75 | 2022-11-10 |  | 100% | 100% | 0% | 2.2857 | 12.01 | 0.49 | 132.41 | 17.64 | 0 | 150.05 |  | 150.05 | (BW-0754) |  | 150.05 | 150.05 | 0 | 206.7975 | 150.05
E11/K149/SK/dm/213 | RESIDENCE | 69 | 77581 | 80518 | Electrical Service Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 4 | 1 | rm | 4 | 2022-11-11 | 2022-11-14 | 100% | 100% | 100% | 0.57143 | 63.34 | 7.28 | 177.35 | 16.64 | 76.01 | 270 |  | 270 |  |  | 270 | 270 | 0 | 346.01 | 270
E11/K149/SK/dm/213 | RESIDENCE | 70 | 77583 |  | Entrance Storage room (KMEP) | Ground Level | Tower | 1 | 1.3 | 0.9 | 4 | 1 | rm | 4 | 2022-11-11 |  | 100% | 100% | 0% | 2.1429 | 63.34 | 7.28 | 177.35 | 62.4 | 0 | 239.75 |  | 239.75 |  |  | 239.75 | 239.75 | 0 | 315.76 | 239.75
E11/K149/SK/dm/213 | RESIDENCE | 70 | 77583 |  | Entrance Storage room (KMEP) | Ground Level | Additional Boarding | 1 | 1.3 | 0.9 | 1 | 1 | m2-LxW | 1.17 | 2022-11-11 |  | 100% | 100% | 0% | 2.1429 | 6.63 | 0.7 | 5.43 | 1.76 | 0 | 7.19 |  | 7.19 |  |  | 7.19 | 7.19 | 0 | 9.5171 | 7.19
E11/K149/SK/dm/213 | RESIDENCE | 71 | 77584 | 80520 | BOH Corridor Block Work | Ground Level | Tower | 1 | 2.5 | 1.3 | 4 | 1 | rm | 4 | 2022-11-11 | 2022-11-15 | 100% | 100% | 100% | 0.71429 | 63.34 | 7.28 | 177.35 | 20.8 | 76.01 | 274.16 |  | 274.16 |  |  | 274.16 | 274.16 | 0 | 350.17 | 274.16
E11/K149/SK/dm/213 | RESIDENCE | 71 | 77584 | 80520 | BOH Corridor Block Work | Ground Level | Additional Boarding | 1 | 2.5 | 1.3 | 1 | 1 | m2-LxW | 3.25 | 2022-11-11 | 2022-11-15 | 100% | 100% | 100% | 0.71429 | 6.63 | 0.7 | 15.08 | 1.63 | 6.46 | 23.17 |  | 23.17 |  |  | 23.17 | 23.17 | 0 | 29.6375 | 23.17
E11/K149/SK/dm/213 | RESIDENCE | 72 | 77585 |  | Lift Lobby Fire Curtain Work | Ground Level | Tower | 1 | 2.5 | 1.3 | 2.2 | 1 | rm | 2.2 | 2022-11-11 |  | 100% | 100% | 0% | 2.1429 | 63.34 | 7.28 | 97.54 | 34.32 | 0 | 131.86 |  | 131.86 |  |  | 131.86 | 131.86 | 0 | 173.668 | 131.86
E11/K149/SK/dm/213 | RESIDENCE | 73 | 77586 | 80521 | BOH Corridor Block Work | Ground Level | Tower | 1 | 1.8 | 1.3 | 4.5 | 1 | rm | 4.5 | 2022-11-11 | 2022-11-15 | 100% | 100% | 100% | 0.71429 | 63.34 | 7.28 | 199.52 | 23.4 | 85.51 | 308.43 |  | 308.43 |  |  | 308.43 | 308.43 | 0 | 393.94 | 308.43
E11/K149/SK/dm/213 | RESIDENCE | 73 | 77586 | 80521 | BOH Corridor Block Work | Ground Level | Additional Boarding | 1 | 1.8 | 1.3 | 1 | 1 | m2-LxW | 2.34 | 2022-11-11 | 2022-11-15 | 100% | 100% | 100% | 0.71429 | 6.63 | 0.7 | 10.86 | 1.17 | 4.65 | 16.68 |  | 16.68 |  |  | 16.68 | 16.68 | 0 | 21.3342 | 16.68
E11/K149/SK/dm/213 | RESIDENCE | 74 | 77587 | 80524 | BOH Corridor Shaft Block Work | Ground Level | Tower | 1 | 1.8 | 1.3 | 4 | 1 | rm | 4 | 2022-11-11 | 2022-11-16 | 100% | 100% | 100% | 0.85714 | 63.34 | 7.28 | 177.35 | 24.96 | 76.01 | 278.32 |  | 278.32 |  |  | 278.32 | 278.32 | 0 | 354.33 | 278.32
E11/K149/SK/dm/213 | RESIDENCE | 74 | 77587 | 80524 | BOH Corridor Shaft Block Work | Ground Level | Additional Boarding | 1 | 1.8 | 1.3 | 1 | 2 | m2-LxW | 2.34 | 2022-11-11 | 2022-11-16 | 100% | 100% | 100% | 0.85714 | 6.63 | 0.7 | 10.86 | 1.4 | 4.65 | 16.91 |  | 16.91 |  |  | 16.91 | 16.91 | 0 | 21.5642 | 16.91
E11/K149/SK/dm/213 | RESIDENCE | 75 | 77588 | 80519 | Electrical Services Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 2 | 1 | rm | 2 | 2022-11-12 | 2022-11-15 | 100% | 100% | 100% | 0.57143 | 63.34 | 7.28 | 88.68 | 8.32 | 38 | 135 |  | 135 |  |  | 135 | 135 | 0 | 173 | 135
E11/K149/SK/dm/213 | RESIDENCE | 76 | 77589 |  | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3.5 | 1 | rm | 3.5 | 2022-11-14 |  | 100% | 100% | 0% | 1.7143 | 63.34 | 7.28 | 155.18 | 43.68 | 0 | 198.86 |  | 198.86 |  |  | 198.86 | 198.86 | 0 | 265.37 | 198.86
E11/K149/SK/dm/213 | RESIDENCE | 1o | 77501 |  | Drainge Pipe Connection | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 1.8 | 1 | 1 | 1 | m2-LxW | 1.8 | 2022-11-14 |  | 100% | 100% | 0% | 1.7143 | 36.52 | 2.94 | 46.02 | 9.07 | 0 | 55.09 |  | 55.09 |  |  | 55.09 | 55.09 | 0 | 74.806 | 55.09
E11/K149/SK/dm/213 | RESIDENCE | 77 | 77503 |  | Chill Water Pipe For (KMEP) | Level 2 | Independent 1.8m wide | 1 | 4 | 2.5 | 1.5 | 1 | m2-LxH | 6 | 2022-11-15 |  | 100% | 100% | 0% | 1.5714 | 16.76 | 0.77 | 70.39 | 7.26 | 0 | 77.65 |  | 77.65 |  |  | 77.65 | 77.65 | 0 | 107.82 | 77.65
E11/K149/SK/dm/213 | RESIDENCE | 78 | 77504 | 80532 | Lift 3 Gypsum Work | Level 2 | Tower | 1 | 1.8 | 1.3 | 2 | 1 | rm | 2 | 2022-11-15 | 2022-11-19 | 100% | 100% | 100% | 0.71429 | 63.34 | 7.28 | 88.68 | 10.4 | 38 | 137.08 |  | 137.08 |  |  | 137.08 | 137.08 | 0 | 175.08 | 137.08
E11/K149/SK/dm/213 | RESIDENCE | 79 | 77590 |  | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 2.5 | 2.5 | 1 | rm | 2.5 | 2022-11-15 |  | 100% | 100% | 0% | 1.5714 | 63.34 | 7.28 | 110.85 | 28.6 | 0 | 139.45 |  | 139.45 |  |  | 139.45 | 139.45 | 0 | 186.95 | 139.45
E11/K149/SK/dm/213 | RESIDENCE | 79a | 77591 |  | Cable Pulling Work | Basement 1 | Tower | 1 | 2 | 1 | 3 | 1 | rm | 3 | 2022-11-15 |  | 100% | 100% | 0% | 1.5714 | 63.34 | 7.28 | 133.01 | 34.32 | 0 | 167.33 |  | 167.33 |  |  | 167.33 | 167.33 | 0 | 224.34 | 167.33
E11/K149/SK/dm/213 | RESIDENCE | 80 | 77592 |  | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 1.8 | 3.7 | 1 | rm | 3.7 | 2022-11-15 |  | 100% | 100% | 0% | 1.5714 | 63.34 | 7.28 | 164.05 | 42.33 | 0 | 206.38 |  | 206.38 |  |  | 206.38 | 206.38 | 0 | 276.688 | 206.38
E11/K149/SK/dm/213 | RESIDENCE | 81 | 77593 |  | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3.7 | 1 | rm | 3.7 | 2022-11-15 |  | 100% | 100% | 0% | 1.5714 | 63.34 | 7.28 | 164.05 | 42.33 | 0 | 206.38 |  | 206.38 |  |  | 206.38 | 206.38 | 0 | 276.688 | 206.38
E11/K149/SK/dm/213 | RESIDENCE | 81 | 77593 |  | Cable Pulling Work | Basement 1 | Additional Boarding | 1 | 2.5 | 1.3 | 1 | 1 | m2-LxW | 3.25 | 2022-11-15 |  | 100% | 100% | 0% | 1.5714 | 6.63 | 0.7 | 15.08 | 3.58 | 0 | 18.66 |  | 18.66 |  |  | 18.66 | 18.66 | 0 | 25.1275 | 18.66
E11/K149/SK/dm/213 | RESIDENCE | 82 | 77594 |  | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3 | 1 | rm | 3 | 2022-11-15 |  | 100% | 100% | 0% | 1.5714 | 63.34 | 7.28 | 133.01 | 34.32 | 0 | 167.33 |  | 167.33 |  |  | 167.33 | 167.33 | 0 | 224.34 | 167.33
E11/K149/SK/dm/213 | RESIDENCE | 83 | 77595 |  | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3.5 | 1 | rm | 3.5 | 2022-11-15 |  | 100% | 100% | 0% | 1.5714 | 63.34 | 7.28 | 155.18 | 40.04 | 0 | 195.22 |  | 195.22 |  |  | 195.22 | 195.22 | 0 | 261.73 | 195.22
E11/K149/SK/dm/213 | RESIDENCE | 19g | 77502 |  | Shaft 9 Duct Fixing Work | Level 31 | Cantilever (0 < 0.5m width) | 1 | 4.5 | 0.5 | 1 | 1 | m2-LxW | 2.25 | 2022-11-14 |  | 100% | 100% | 0% | 1.7143 | 32.75 | 1.05 | 51.58 | 4.05 | 0 | 55.63 |  | 55.63 |  |  | 55.63 | 55.63 | 0 | 77.7375 | 55.63
E11/K149/SK/dm/213 | RESIDENCE | 84 | 77505 |  | Ceiling Opening and Closing for (KMEP) | Ground Level | Mobile Tower | 1 | 2.5 | 1.8 | 3.7 | 1 | rm | 3.7 | 2022-11-16 |  | 100% | 100% | 0% | 1.4286 | 103.33 | 10.29 | 267.62 | 54.39 | 0 | 322.01 |  | 322.01 |  |  | 322.01 | 322.01 | 0 | 436.711 | 322.01
E11/K149/SK/dm/213 | RESIDENCE | 85 | 77506 |  | Duct Fixing Work | Basement 1 | Independent | 1 | 6.3 | 1.3 | 2 | 1 | m2-LxH | 12.6 | 2022-11-16 |  | 100% | 100% | 0% | 1.4286 | 12.01 | 0.49 | 105.93 | 8.82 | 0 | 114.75 |  | 114.75 |  |  | 114.75 | 114.75 | 0 | 160.146 | 114.75
E11/K149/SK/dm/213 | RESIDENCE | 86 | 77507 | 80531 | Lift 3 Gypsum Work | Level 2 | Tower | 1 | 1.3 | 0.9 | 2 | 1 | rm | 2 | 2022-11-16 | 2022-11-19 | 100% | 100% | 100% | 0.57143 | 63.34 | 7.28 | 88.68 | 8.32 | 38 | 135 |  | 135 |  |  | 135 | 135 | 0 | 173 | 135
E11/K149/SK/dm/213 | RESIDENCE | 87 | 77508 |  | Lift Lobby Glass Line Work | Ground Level | Tower | 1 | 2.5 | 1.3 | 4 | 1 | rm | 4 | 2022-11-17 |  | 100% | 100% | 0% | 1.2857 | 63.34 | 7.28 | 177.35 | 37.44 | 0 | 214.79 |  | 214.79 |  |  | 214.79 | 214.79 | 0 | 290.8 | 214.79
E11/K149/SK/dm/213 | RESIDENCE | 87 | 77508 |  | Lift Lobby Glass Line Work | Ground Level | Additional Boarding | 1 | 2.5 | 1.3 | 1 | 1 | m2-LxW | 3.25 | 2022-11-17 |  | 100% | 100% | 0% | 1.2857 | 6.63 | 0.7 | 15.08 | 2.93 | 0 | 18.01 |  | 18.01 |  |  | 18.01 | 18.01 | 0 | 24.4775 | 18.01
E11/K149/SK/dm/213 | RESIDENCE | 88 | 77509 |  | BOH Corridor Lift 1&2 Wall Finishing Work | Ground Level | Independent | 1 | 14.6 | 1.3 | 4 | 1 | m2-LxH | 58.4 | 2022-11-17 |  | 100% | 100% | 0% | 1.2857 | 12.01 | 0.49 | 490.97 | 36.79 | 0 | 527.76 |  | 527.76 |  |  | 527.76 | 527.76 | 0 | 738.174 | 527.76
E11/K149/SK/dm/213 | RESIDENCE | 88 | 77509 |  | BOH Corridor Lift 1&2 Wall Finishing Work | Ground Level | Additional Boarding | 1 | 14.6 | 1.3 | 1 | 1 | m2-LxW | 18.98 | 2022-11-17 |  | 100% | 100% | 0% | 1.2857 | 6.63 | 0.7 | 88.09 | 17.08 | 0 | 105.17 |  | 105.17 |  |  | 105.17 | 105.17 | 0 | 142.9174 | 105.17
E11/K149/SK/dm/213 | RESIDENCE | 8s | 77510 |  | Glass Fixing work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 3.5 | 1 | 1 | 1 | m2-LxW | 3.5 | 2022-11-17 |  | 100% | 100% | 0% | 1.2857 | 36.52 | 2.94 | 89.47 | 13.23 | 0 | 102.7 |  | 102.7 |  |  | 102.7 | 102.7 | 0 | 141.05 | 102.7
E11/K149/SK/dm/213 | RESIDENCE | 89 | 77511 |  | BOH Corridor Lift 1&2 Wall Finishing Work | Ground Level | Independent 1.8m wide | 1 | 5.8 | 2.5 | 4 | 1 | m2-LxH | 23.2 | 2022-11-18 |  | 100% | 100% | 0% | 1.1429 | 16.76 | 0.77 | 272.18 | 20.42 | 0 | 292.6 |  | 292.6 |  |  | 292.6 | 292.6 | 0 | 409.252 | 292.6
E11/K149/SK/dm/213 | RESIDENCE | 89 | 77511 |  | BOH Corridor Lift 1&2 Wall Finishing Work | Ground Level | Additional Boarding | 1 | 5.8 | 2.5 | 1 | 1 | m2-LxW | 14.5 | 2022-11-18 |  | 100% | 100% | 0% | 1.1429 | 6.63 | 0.7 | 67.29 | 11.6 | 0 | 78.89 |  | 78.89 |  |  | 78.89 | 78.89 | 0 | 107.735 | 78.89
E11/K149/SK/dm/213 | RESIDENCE | 89a | 77512 |  | BOH Corridor Lift 1&2 Wall Finishing Work | Ground Level | Tower | 1 | 1 | 0.9 | 4 | 1 | rm | 4 | 2022-11-18 |  | 100% | 100% | 0% | 1.1429 | 63.34 | 7.28 | 177.35 | 33.28 | 0 | 210.63 |  | 210.63 |  |  | 210.63 | 210.63 | 0 | 286.64 | 210.63
E11/K149/SK/dm/213 | RESIDENCE | 89a | 77512 |  | BOH Corridor Lift 1&2 Wall Finishing Work | Ground Level | Additional Boarding | 1 | 1 | 0.9 | 1 | 1 | m2-LxW | 0.9 | 2022-11-18 |  | 100% | 100% | 0% | 1.1429 | 6.63 | 0.7 | 4.18 | 0.72 | 0 | 4.9 |  | 4.9 |  |  | 4.9 | 4.9 | 0 | 6.687 | 4.9
E11/K149/SK/dm/213 | RESIDENCE | 90 | 77513 |  | Chill Water Pipe For (KMEP) | Ground Level | Birdcage | 1 | 5 | 3.1 | 4 | 1 | m3 | 62 | 2022-11-19 |  | 100% | 100% | 0% | 1 | 7.08 | 0.49 | 307.27 | 30.38 | 0 | 337.65 |  | 337.65 |  |  | 337.65 | 337.65 | 0 | 469.34 | 337.65
E11/K149/SK/dm/213 | RESIDENCE | 90 | 77513 |  | Chill Water Pipe For (KMEP) | Ground Level | Additional Boarding | 1 | 5 | 3.1 | 1 | 1 | m2-LxW | 15.5 | 2022-11-19 |  | 100% | 100% | 0% | 1 | 6.63 | 0.7 | 71.94 | 10.85 | 0 | 82.79 |  | 82.79 |  |  | 82.79 | 82.79 | 0 | 113.615 | 82.79
E11/K149/SK/dm/213 | RESIDENCE | 91 | 77514 |  | Lift Lobby Block Shifting Work | Ground Level | Tower | 1 | 1.3 | 0.9 | 1 | 1 | rm | 1 | 2022-11-19 |  | 100% | 100% | 0% | 1 | 63.34 | 7.28 | 44.34 | 7.28 | 0 | 51.62 |  | 51.62 |  |  | 51.62 | 51.62 | 0 | 70.62 | 51.62
E11/K149/SK/dm/213 | RESIDENCE | 87a | 77515 |  | Block Work | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 2.5 | 0.75 | 1 | 1 | m2-LxW | 1.88 | 2022-11-19 |  | 100% | 100% | 0% | 1 | 36.52 | 2.94 | 48.06 | 5.53 | 0 | 53.59 |  | 53.59 |  |  | 53.59 | 53.59 | 0 | 74.1876 | 53.59
E11/K149/SK/dm/213 | RESIDENCE | 90a | 77516 |  | BOH Corridor For Chill Pipe (KMEP) | Ground Level | Tower | 1 | 2 | 1.3 | 3.5 | 1 | rm | 3.5 | 2022-11-21 |  | 100% | 100% | 0% | 0.71429 | 63.34 | 7.28 | 155.18 | 18.2 | 0 | 173.38 |  | 173.38 |  |  | 173.38 | 173.38 | 0 | 239.89 | 173.38
E11/K149/SK/dm/213 | RESIDENCE | 92 | 77517 |  | Balcony Side Glass Installation | Level 1 | Tower | 1 | 2.5 | 1.8 | 5.5 | 1 | rm | 5.5 | 2022-11-21 |  | 100% | 100% | 0% | 0.71429 | 63.34 | 7.28 | 243.86 | 28.6 | 0 | 272.46 |  | 272.46 |  |  | 272.46 | 272.46 | 0 | 376.97 | 272.46
E11/K149/SK/dm/213 | RESIDENCE | 92 | 77517 |  | Balcony Side Glass Installation | Level 1 | Additional Boarding | 1 | 2.5 | 1.8 | 1 | 1 | m2-LxW | 4.5 | 2022-11-21 |  | 100% | 100% | 0% | 0.71429 | 6.63 | 0.7 | 20.88 | 2.25 | 0 | 23.13 |  | 23.13 |  |  | 23.13 | 23.13 | 0 | 32.085 | 23.13
E11/K149/SK/dm/213 | RESIDENCE | 93 | 77518 |  | Canal Side For Ceiling Work (KMEP- BW 0804) | Ground Level | Mobile Tower | 1 | 2.5 | 1.8 | 3.7 | 1 | rm | 3.7 | 2022-11-22 |  | 100% | 100% | 0% | 0.57143 | 103.33 | 10.29 | 267.62 | 21.76 | 0 | 289.38 |  | 289.38 |  |  | 289.38 | 289.38 | 0 | 404.081 | 289.38
E11/K149/SK/dm/213 | RESIDENCE | 94 | 77519 |  | KCE Site Office area Chill Water Pipe (KMEP-BW 767) | Ground Level | Independent | 1 | 5.4 | 1.3 | 4 | 1 | m2-LxH | 21.6 | 2022-11-22 |  | 100% | 100% | 0% | 0.57143 | 12.01 | 0.49 | 181.59 | 6.05 | 0 | 187.64 |  | 187.64 |  |  | 187.64 | 187.64 | 0 | 265.466 | 187.64
E11/K149/SK/dm/213 | RESIDENCE | 94a | 77520 |  | KCE Site Office area Chill Water Pipe (KMEP-BW 767) | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 5.4 | 0.75 | 1 | 1 | m2-LxW | 4.05 | 2022-11-22 |  | 100% | 100% | 0% | 0.57143 | 36.52 | 2.94 | 103.53 | 6.8 | 0 | 110.33 |  | 110.33 |  |  | 110.33 | 110.33 | 0 | 154.706 | 110.33
E11/K149/SK/dm/213 | RESIDENCE | 94b | 77521 |  | KCE Site Office area Chill Water Pipe (KMEP-BW 767) | Ground Level | Independent 1.8m wide | 1 | 4.9 | 2.5 | 4 | 1 | m2-LxH | 19.6 | 2022-11-22 |  | 100% | 100% | 0% | 0.57143 | 16.76 | 0.77 | 229.95 | 8.62 | 0 | 238.57 |  | 238.57 |  |  | 238.57 | 238.57 | 0 | 337.116 | 238.57
E11/K149/SK/dm/213 | RESIDENCE | 94c | 77522 |  | KCE Site Office area Chill Water Pipe (KMEP-BW 767) | Ground Level | Tower | 1 | 2.5 | 1.8 | 4 | 1 | rm | 4 | 2022-11-22 |  | 100% | 100% | 0% | 0.57143 | 63.34 | 7.28 | 177.35 | 16.64 | 0 | 193.99 |  | 193.99 |  |  | 193.99 | 193.99 | 0 | 270 | 193.99
E11/K149/SK/dm/213 | RESIDENCE | 95 | 77523 |  | Shaft Water Meter Room For (KMEP-BW 797) | Level 4 | Tower | 1 | 1 | 0.6 | 2 | 1 | rm | 2 | 2022-11-23 |  | 100% | 100% | 0% | 0.42857 | 63.34 | 7.28 | 88.68 | 6.24 | 0 | 94.92 |  | 94.92 |  |  | 94.92 | 94.92 | 0 | 132.92 | 94.92
E11/K149/SK/dm/213 | RESIDENCE | 96 | 77524 |  | Pump Room For Water Master (BW 024) | Level 3 | Independent 1.8m wide | 1 | 8 | 2.5 | 1.5 | 1 | m2-LxH | 12 | 2022-11-23 |  | 100% | 100% | 0% | 0.42857 | 16.76 | 0.77 | 140.78 | 3.96 | 0 | 144.74 |  | 144.74 |  |  | 144.74 | 144.74 | 0 | 205.08 | 144.74
E11/K149/SK/dm/213 | RESIDENCE | 97 | 77525 |  | Pump Room For Water Master (BW 024) | Level 3 | Tower | 1 | 2.5 | 1.3 | 1.5 | 1 | rm | 1.5 | 2022-11-23 |  | 100% | 100% | 0% | 0.42857 | 63.34 | 7.28 | 66.51 | 4.68 | 0 | 71.19 |  | 71.19 |  |  | 71.19 | 71.19 | 0 | 99.69 | 71.19
E11/K149/SK/dm/213 | RESIDENCE | 98 | 77526 |  | Shaft Water Meter Room For (KMEP-BW 797) | Level 2 | Tower | 1 | 1 | 0.6 | 2 | 1 | rm | 2 | 2022-11-23 |  | 100% | 100% | 0% | 0.42857 | 63.34 | 7.28 | 88.68 | 6.24 | 0 | 94.92 |  | 94.92 |  |  | 94.92 | 94.92 | 0 | 132.92 | 94.92
E11/K149/SK/dm/213 | RESIDENCE | 92a | 77527 | 80534 | Road Side Access For Glass Fixing | Level 2 | Cantilever (0 < 0.5m width) | 1 | 2.5 | 0.5 | 1 | 1 | m2-LxW | 1.25 | 2022-11-23 | 2022-11-24 | 100% | 100% | 100% | 0.28571 | 32.75 | 1.05 | 28.66 | 0.38 | 12.28 | 41.32 |  | 41.32 |  |  | 41.32 | 41.32 | 0 | 53.5975 | 41.32
E11/K149/SK/dm/213 | RESIDENCE | 99 | 77529 |  | Canal Side For Excavation Access | Ground Level | Tower | 1 | 1.3 | 1.3 | 1 | 1 | rm | 1 | 2022-11-24 |  | 100% | 100% | 0% | 0.28571 | 63.34 | 7.28 | 44.34 | 2.08 | 0 | 46.42 |  | 46.42 |  |  | 46.42 | 46.42 | 0 | 65.42 | 46.42
E11/K149/SK/dm/213 | RESIDENCE | 100 | 77530 |  | Shaft Water Meter Room For (KMEP-BW 797) | Ground Level | Tower | 1 | 1 | 0.75 | 4 | 2 | rm | 4 | 2022-11-24 |  | 100% | 100% | 0% | 0.28571 | 63.34 | 7.28 | 177.35 | 8.32 | 0 | 185.67 |  | 185.67 |  |  | 185.67 | 185.67 | 0 | 261.68 | 185.67
E11/K149/SK/dm/213 | RESIDENCE | 72a | 77531 |  | Lift Lobby For Fire Curtain Work | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 2.5 | 0.75 | 1 | 1 | m2-LxW | 1.88 | 2022-11-24 |  | 100% | 100% | 0% | 0.28571 | 36.52 | 2.94 | 48.06 | 1.58 | 0 | 49.64 |  | 49.64 |  |  | 49.64 | 49.64 | 0 | 70.2376 | 49.64
E11/K149/SK/dm/213 | RESIDENCE | 101 | 77532 |  | Shaft Water Meter Room For (KMEP-BW 797) | Level 5 | Tower | 1 | 1 | 0.5 | 4 | 2 | rm | 4 | 2022-11-25 |  | 100% | 100% | 0% | 0.14286 | 63.34 | 7.28 | 177.35 | 4.16 | 0 | 181.51 |  | 181.51 |  |  | 181.51 | 181.51 | 0 | 257.52 | 181.51
E11/K149/SK/dm/213 | RESIDENCE | 8t | 77533 |  | Glass Fixing work | Level 30 | Cantilever (0 < 0.5m width) | 1 | 10.8 | 0.5 | 1 | 1 | m2-LxW | 5.4 | 2022-11-25 |  | 100% | 100% | 0% | 0.14286 | 32.75 | 1.05 | 123.8 | 0.81 | 0 | 124.61 |  | 124.61 |  |  | 124.61 | 124.61 | 0 | 177.66 | 124.61
E11/K149/SK/dm/213 | HOTEL | 18 | 74639 | 76808 | Staircase 7 For Electrical Work | Basement 1 | Tower | 1 | 1.8 | 1.3 | 2 | 1 | rm | 2 | 2022-10-27 | 2022-11-05 | 100% | 100% | 100% | 1.4286 | 63.34 | 7.28 | 88.68 | 20.8 | 38 | 147.48 |  | 147.48 |  |  | 147.48 | 147.48 | 0 | 185.48 | 147.48
E11/K149/SK/dm/213 | HOTEL | 19 | 74640 | 76809 | Staircase 7 For Electrical Work | Basement 1 | Tower | 1 | 1.8 | 1.3 | 2.3 | 1 | rm | 2.3 | 2022-10-27 | 2022-11-05 | 100% | 100% | 100% | 1.4286 | 63.34 | 7.28 | 101.98 | 23.92 | 43.7 | 169.6 |  | 169.6 |  |  | 169.6 | 169.6 | 0 | 213.302 | 169.6
E11/K149/SK/dm/213 | HOTEL | 20 | 74641 | 76817 | Canal Side Column Cove Work | Ground Level | Tower | 1 | 2.5 | 2.5 | 5.5 | 1 | rm | 5.5 | 2022-10-31 | 2022-11-11 | 100% | 100% | 100% | 1.7143 | 63.34 | 7.28 | 243.86 | 68.64 | 104.51 | 417.01 |  | 417.01 |  |  | 417.01 | 417.01 | 0 | 521.52 | 417.01
E11/K149/SK/dm/259 | HOTEL | 21 | 74644 |  | Inverted Scaffold | Level 29 | Design 1399 -06 rev-B | 1 | 23.5 | 1.8 | 4 | 1 | lm | 23.5 | 2022-10-31 |  | 100% | 100% | 0% | 3.7143 | 1002.22 | 98.12 | 16486.52 | 8564.47 | 0 | 25050.99 |  | 25050.99 | Tas Quote - 2439-6-1 |  | 25050.99 | 25050.99 | 0 | 32116.64 | 25050.99
E11/K149/SK/dm/259 | HOTEL | 21 |  |  | Inverted Scaffold | Level 29 | Third Party Inspection ( Additional) | 1 |  |  |  |  | unit | 1 | 2022-10-31 | 2022-10-31 | 100% | 100% | 100% | 0.14286 | 1230 | 0 | 1230 | 0 | 0 | 1230 |  | 1230 | Additional Inspection |  | 1230 | 1230 | 0 | 1230 | 1230
E11/K149/SK/dm/213 | HOTEL | 22 | 74642 | 76818 | Column Cove Installation Work | Ground Level | Tower | 1 | 2.5 | 2.5 | 5.5 | 1 | rm | 5.5 | 2022-10-31 | 2022-11-11 | 100% | 100% | 100% | 1.7143 | 63.34 | 7.28 | 243.86 | 68.64 | 104.51 | 417.01 |  | 417.01 |  |  | 417.01 | 417.01 | 0 | 70.62 | 417.01
E11/K149/SK/dm/213 | HOTEL | 23 | 74643 | 76819 | Column Cove Installation Work | Ground Level | Tower | 1 | 2.5 | 2.5 | 5.5 | 1 | rm | 5.5 | 2022-10-31 | 2022-11-12 | 100% | 100% | 100% | 1.8571 | 63.34 | 7.28 | 243.86 | 74.36 | 104.51 | 422.73 |  | 422.73 |  |  | 422.73 | 422.73 | 0 | 70.62 | 422.73
E11/K149/SK/dm/213 | HOTEL | 21a | 74645 | 76821 | Canal Side for Wall Cutting Work | Level 29 | Additional Boarding | 1 | 23.5 | 1 | 1 | 1 | m2-LxW | 23.5 | 2022-10-31 | 2022-11-11 | 100% | 100% | 100% | 1.7143 | 6.63 | 0.7 | 109.06 | 28.2 | 46.74 | 184 |  | 184 |  |  | 184 | 184 | 0 | 7.33 | 184
E11/K149/SK/dm/213 | HOTEL | 24 | 74646 | 76820 | Column Cove Installation Work | Ground Level | Independent 1.8m wide | 1 | 3.8 | 2.5 | 4.5 | 1 | m2-LxH | 17.1 | 2022-11-01 | 2022-11-11 | 100% | 100% | 100% | 1.5714 | 16.76 | 0.77 | 200.62 | 20.69 | 85.98 | 307.29 |  | 307.29 |  |  | 307.29 | 307.29 | 0 | 17.53 | 307.29
E11/K149/SK/dm/213 | HOTEL | 12a | 74647 |  | Balcony Side Grc Removel & Pipe Connection | Level 12 | Cantilever (0 < 0.5m width) | 1 | 1.5 | 0.5 | 1 | 1 | m2-LxW | 0.75 | 2022-11-01 |  | 100% | 100% | 0% | 3.5714 | 32.75 | 1.05 | 17.19 | 2.81 | 0 | 20 |  | 20 |  |  | 20 | 20 | 0 | 33.8 | 20
E11/K149/SK/dm/213 | HOTEL | 11a | 74648 |  | Balcony Side Grc Work | Level 13 | Cantilever (0 < 0.5m width) | 1 | 1.5 | 0.5 | 1 | 1 | m2-LxW | 0.75 | 2022-11-01 |  | 100% | 100% | 0% | 3.5714 | 32.75 | 1.05 | 17.19 | 2.81 | 0 | 20 |  | 20 |  |  | 20 | 20 | 0 | 33.8 | 20
E11/K149/SK/dm/213 | HOTEL | 14a | 74649 |  | Balcony Side RFI-130 | Level 15 | Cantilever (0 < 0.5m width) | 1 | 1.5 | 0.5 | 1 | 1 | m2-LxW | 0.75 | 2022-11-02 |  | 100% | 100% | 0% | 3.4286 | 32.75 | 1.05 | 17.19 | 2.7 | 0 | 19.89 |  | 19.89 |  |  | 19.89 | 19.89 | 0 | 33.8 | 19.89
E11/K149/SK/dm/213 | HOTEL | 25 | 77601 |  | EIFS & Wall Finishing Work | Basement 1 | Independent | 1 | 9.3 | 1.3 | 6 | 1 | m2-LxH | 55.8 | 2022-11-02 |  | 100% | 100% | 0% | 3.4286 | 12.01 | 0.49 | 469.11 | 93.74 | 0 | 562.85 |  | 562.85 |  |  | 562.85 | 562.85 | 0 | 12.5 | 562.85
E11/K149/SK/dm/213 | HOTEL | 25 | 77601 |  | EIFS & Wall Finishing Work | Basement 1 | Additional Boarding | 1 | 9.3 | 1.3 | 1 | 1 | m2-LxW | 12.09 | 2022-11-02 |  | 100% | 100% | 0% | 3.4286 | 6.63 | 0.7 | 56.11 | 29.02 | 0 | 85.13 |  | 85.13 |  |  | 85.13 | 85.13 | 0 | 7.33 | 85.13
E11/K149/SK/dm/213 | HOTEL | 25a | 77602 |  | EIFS & Wall Finishing Work | Basement 1 | Independent | 1 | 10.5 | 1.3 | 4 | 1 | m2-LxH | 42 | 2022-11-02 |  | 100% | 100% | 0% | 3.4286 | 12.01 | 0.49 | 353.09 | 70.56 | 0 | 423.65 |  | 423.65 |  |  | 423.65 | 423.65 | 0 | 12.5 | 423.65
E11/K149/SK/dm/213 | HOTEL | 26 | 77604 |  | Plant Room For CHW Pipe | Level 5 | Independent | 1 | 6 | 1.5 | 2 | 1 | m2-LxH | 12 | 2022-11-04 |  | 100% | 100% | 0% | 3.1429 | 12.01 | 0.49 | 100.88 | 18.48 | 0 | 119.36 |  | 119.36 |  |  | 119.36 | 119.36 | 0 | 12.5 | 119.36
E11/K149/SK/dm/213 | HOTEL | 26a | 77605 |  | Plant Room For CHW Pipe | Level 5 | Independent 1.8m wide | 1 | 6 | 2 | 2.5 | 1 | m2-LxH | 15 | 2022-11-04 |  | 100% | 100% | 0% | 3.1429 | 16.76 | 0.77 | 175.98 | 36.3 | 0 | 212.28 |  | 212.28 |  |  | 212.28 | 212.28 | 0 | 17.53 | 212.28
E11/K149/SK/dm/213 | HOTEL | 26b | 77606 |  | Plant Room For CHW Pipe | Level 5 | Tower | 1 | 1.8 | 1.8 | 1 | 1 | rm | 1 | 2022-11-04 |  | 100% | 100% | 0% | 3.1429 | 63.34 | 7.28 | 44.34 | 22.88 | 0 | 67.22 |  | 67.22 |  |  | 67.22 | 67.22 | 0 | 70.62 | 67.22
E11/K149/SK/dm/213 | HOTEL | 27 | 77607 | 76816 | Electrical Services Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 4 | 1 | rm | 4 | 2022-11-04 | 2022-11-11 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 177.35 | 33.28 | 76.01 | 286.64 |  | 286.64 |  |  | 286.64 | 286.64 | 0 | 70.62 | 286.64
E11/K149/SK/dm/213 | HOTEL | 28 | 77608 | 76824 | Bond Ceiling Work | Level 4 | Tower | 1 | 2.5 | 0.9 | 1.2 | 1 | rm | 1.2 | 2022-11-04 | 2022-11-11 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 53.21 | 9.98 | 22.8 | 85.99 |  | 85.99 |  |  | 85.99 | 85.99 | 0 | 70.62 | 85.99
E11/K149/SK/dm/213 | HOTEL | 29 | 77609 | 76825 | Bond Ceiling Work | Level 4 | Tower | 1 | 2.5 | 0.9 | 1.2 | 1 | rm | 1.2 | 2022-11-04 | 2022-11-11 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 53.21 | 9.98 | 22.8 | 85.99 |  | 85.99 |  |  | 85.99 | 85.99 | 0 | 70.62 | 85.99 |  |  |  | 472.32
E11/K149/SK/dm/213 | HOTEL | 30 | 77610 | 76826 | Bond Ceiling Work | Level 4 | Tower | 1 | 2.5 | 0.9 | 1.2 | 1 | rm | 1.2 | 2022-11-04 | 2022-11-11 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 53.21 | 9.98 | 22.8 | 85.99 |  | 85.99 |  |  | 85.99 | 85.99 | 0 | 70.62 | 85.99
E11/K149/SK/dm/259 | HOTEL | 31 | 77611 |  | Inverted Scaffold | Level 29 | Design 1399 -06 rev-B | 1 | 22 | 1.8 | 4 | 1 | lm | 22 | 2022-11-04 |  | 100% | 100% | 0% | 3.1429 | 1002.22 | 98.12 | 15434.19 | 6784.3 | 0 | 22218.49 |  | 22218.49 | Tas Quote - 2439-6-1 |  | 22218.49 | 22218.49 | 0 | 1100.34 | 22218.49 | 28.56
E11/K149/SK/dm/259 | HOTEL | 31 |  |  | Inverted Scaffold | Level 29 | Third Party Inspection ( Additional) | 1 |  |  |  |  | unit | 1 | 2022-11-04 |  | 100% | 100% | 0% | 3.1429 | 1230 | 0 | 1230 | 0 | 0 | 1230 |  | 1230 | Additional Inspection |  | 1230 | 1230 | 0 | 1230 | 1230
E11/K149/SK/dm/213 | HOTEL | 31a | 77612 | 76822 | Inverted Scaffold | Level 29 | Additional Boarding | 1 | 22 | 1 | 1 | 1 | m2-LxW | 22 | 2022-11-04 | 2022-11-11 | 100% | 100% | 100% | 1.1429 | 6.63 | 0.7 | 102.1 | 17.6 | 43.76 | 163.46 |  | 163.46 |  |  | 163.46 | 163.46 | 0 | 7.33 | 163.46
E11/K149/SK/dm/213 | HOTEL | 32 | 77613 | 76814 | Electrical Services Work | Basement 1 | Independent | 1 | 3.8 | 1.3 | 2.5 | 1 | m2-LxH | 9.5 | 2022-11-04 | 2022-11-10 | 100% | 100% | 100% | 1 | 12.01 | 0.49 | 79.87 | 4.66 | 34.23 | 118.76 |  | 118.76 |  |  | 118.76 | 118.76 | 0 | 12.5 | 118.76
E11/K149/SK/dm/213 | HOTEL | 32a | 77614 | 76815 | Electrical Services Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 2.3 | 1 | rm | 2.3 | 2022-11-04 | 2022-11-10 | 100% | 100% | 100% | 1 | 63.34 | 7.28 | 101.98 | 16.74 | 43.7 | 162.42 |  | 162.42 |  |  | 162.42 | 162.42 | 0 | 70.62 | 162.42
E11/K149/SK/dm/213 | HOTEL | 33 | 77615 | 76827 | Bond Ceiling Work | Level 4 | Independent | 1 | 3 | 0.5 | 1.5 | 1 | m2-LxH | 4.5 | 2022-11-04 | 2022-11-11 | 100% | 100% | 100% | 1.1429 | 12.01 | 0.49 | 37.83 | 2.52 | 16.21 | 56.56 |  | 56.56 |  |  | 56.56 | 56.56 | 0 | 12.5 | 56.56
E11/K149/SK/dm/213 | HOTEL | 34 | 77616 |  | Electrical Services Work | Basement 1 | Independent 1.8m wide | 1 | 3.8 | 2.5 | 3 | 1 | m2-LxH | 11.4 | 2022-11-07 |  | 100% | 100% | 0% | 2.7143 | 16.76 | 0.77 | 133.74 | 23.83 | 0 | 157.57 |  | 157.57 |  |  | 157.57 | 157.57 | 0 | 17.53 | 157.57
E11/K149/SK/dm/213 | HOTEL | 35 | 77617 |  | Electrical Services Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3.2 | 1 | rm | 3.2 | 2022-11-08 |  | 100% | 100% | 0% | 2.5714 | 63.34 | 7.28 | 141.88 | 59.9 | 0 | 201.78 |  | 201.78 |  |  | 201.78 | 201.78 | 0 | 70.62 | 201.78
E11/K149/SK/dm/341 | HOTEL | 36 | 77618 |  | Balcony Floor Drain Work | Level 18 to 20 | Independent 1.8m wide | 1 | 6 | 1.8 | 7 | 1 | unit | 1 | 2022-11-09 |  | 100% | 100% | 0% | 2.4286 | 5277.5 | 48.26 | 3694.25 | 117.2 | 0 | 3811.45 |  | 3811.45 | Tas Quote - 2439-12-2 (item-1) |  | 3811.45 | 3811.45 | 0 | 5325.76 | 3811.45
E11/K149/SK/dm/213 | HOTEL | 13a | 77619 |  | Balcony Side Grc Removel & Ceiling Board Work | Level 14 | Cantilever (0 < 0.5m width) | 1 | 1.5 | 0.5 | 1 | 1 | m2-LxW | 0.75 | 2022-11-09 |  | 100% | 100% | 0% | 2.4286 | 32.75 | 1.05 | 17.19 | 1.91 | 0 | 19.1 |  | 19.1 |  |  | 19.1 | 19.1 | 0 | 33.8 | 19.1
E11/K149/SK/dm/213 | HOTEL | 21b | 77620 |  | Inverted Scaffold | Level 29 | Cantilever (0.5m< width) | 1 | 3 | 1.8 | 1 | 1 | m2-LxW | 5.4 | 2022-11-09 |  | 100% | 100% | 0% | 2.4286 | 36.52 | 2.94 | 138.05 | 38.56 | 0 | 176.61 |  | 176.61 |  |  | 176.61 | 176.61 | 0 | 39.46 | 176.61
E11/K149/SK/dm/213 | HOTEL | 10b | 77621 |  | Inverted Scaffold | Level 29 | Cantilever (0.5m< width) | 1 | 1.8 | 1.5 | 1 | 1 | m2-LxW | 2.7 | 2022-11-09 |  | 100% | 100% | 0% | 2.4286 | 36.52 | 2.94 | 69.02 | 19.28 | 0 | 88.3 |  | 88.3 |  |  | 88.3 | 88.3 | 0 | 39.46 | 88.3
E11/K149/SK/dm/213 | HOTEL | 31b | 77622 | 76823 | Edge Protection | Level 29 | Single Handrail | 1 | 41 | 1 | 1 |  | lm | 41 | 2022-11-09 | 2022-11-11 | 100% | 100% | 100% | 0.42857 | 7 | 0.42 | 200.9 | 7.38 | 86.1 | 294.38 |  | 294.38 |  |  | 294.38 | 294.38 | 0 | 7.42 | 294.38
E11/K149/SK/dm/213 | HOTEL | 37 | 77623 | 76813 | Chill Water line Pipe For Water Proof | Ground Level | Independent | 1 | 3 | 1.5 | 1 | 1 | m2-LxH | 3 | 2022-11-09 | 2022-11-10 | 100% | 100% | 100% | 0.28571 | 12.01 | 0.49 | 25.22 | 0.42 | 10.81 | 36.45 |  | 36.45 |  |  | 36.45 | 36.45 | 0 | 12.5 | 36.45
E11/K149/SK/dm/213 | HOTEL | 25b | 77624 |  | EIFS & Wall Finishing Work | Basement 1 | Independent | 1 | 5 | 1.3 | 2.2 | 1 | m2-LxH | 11 | 2022-11-10 |  | 100% | 100% | 0% | 2.2857 | 12.01 | 0.49 | 92.48 | 12.32 | 0 | 104.8 |  | 104.8 |  |  | 104.8 | 104.8 | 0 | 12.5 | 104.8
E11/K149/SK/dm/213 | HOTEL | 25c | 77625 |  | EIFS & Wall Finishing Work | Basement 1 | Independent | 1 | 8.3 | 1.3 | 2.2 | 1 | m2-LxH | 18.26 | 2022-11-10 |  | 100% | 100% | 0% | 2.2857 | 12.01 | 0.49 | 153.51 | 20.45 | 0 | 173.96 |  | 173.96 |  |  | 173.96 | 173.96 | 0 | 12.5 | 173.96
E11/K149/SK/dm/213 | HOTEL | 38 | 77626 |  | Electrical Services Work | Basement 1 | Independent | 1 | 3.8 | 1.3 | 2.8 | 1 | m2-LxH | 10.64 | 2022-11-11 |  | 100% | 100% | 0% | 2.1429 | 12.01 | 0.49 | 89.45 | 11.17 | 0 | 100.62 |  | 100.62 |  |  | 100.62 | 100.62 | 0 | 12.5 | 100.62
E11/K149/SK/dm/213 | HOTEL | 39 | 77627 | 80801 | Column Cove Installation Work | Ground Level | Independent 1.8m wide | 1 | 3.8 | 2.5 | 4 | 1 | m2-LxH | 15.2 | 2022-11-11 | 2022-11-17 | 100% | 100% | 100% | 1 | 16.76 | 0.77 | 178.33 | 11.7 | 76.43 | 266.46 |  | 266.46 |  |  | 266.46 | 266.46 | 0 | 17.53 | 266.46
E11/K149/SK/dm/213 | HOTEL | 40 | 77628 |  | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3.5 | 1 | rm | 3.5 | 2022-11-12 |  | 100% | 100% | 0% | 2 | 63.34 | 7.28 | 155.18 | 50.96 | 0 | 206.14 |  | 206.14 |  |  | 206.14 | 206.14 | 0 | 70.62 | 206.14
E11/K149/SK/dm/213 | HOTEL | 41 | 77629 |  | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3 | 1 | rm | 3 | 2022-11-12 |  | 100% | 100% | 0% | 2 | 63.34 | 7.28 | 133.01 | 43.68 | 0 | 176.69 |  | 176.69 |  |  | 176.69 | 176.69 | 0 | 70.62 | 176.69
E11/K149/SK/dm/213 | HOTEL | 42 | 77630 |  | Cable Pulling Work | Basement 1 | Tower | 1 | 1.8 | 1.3 | 2.5 | 1 | rm | 2.5 | 2022-11-12 |  | 100% | 100% | 0% | 2 | 63.34 | 7.28 | 110.85 | 36.4 | 0 | 147.25 |  | 147.25 |  |  | 147.25 | 147.25 | 0 | 70.62 | 147.25
E11/K149/PK/dm/378 | HOTEL | 43&43a | 77633 |  | Ramp Area GRC Pannel Fixing Work | Ground Level | Design 1399-21 | 1 | 9.1 | 1.3 | 5 | 1 | m2-LxH | 45.5 | 2022-11-14 |  | 100% | 100% | 0% | 1.7143 | 95.9 | 13.9 | 3054.42 | 1084.2 | 0 | 4138.62 |  | 4138.62 | Tas Quote - 2439-15-1 (item-1 Prorate) |  | 4138.62 | 4138.62 | 0 | 109.8 | 4138.62
E11/K149/SK/dm/213 | HOTEL | 44 | 77631 |  | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 4 | 1 | rm | 4 | 2022-11-15 |  | 100% | 100% | 0% | 1.5714 | 63.34 | 7.28 | 177.35 | 45.76 | 0 | 223.11 |  | 223.11 |  |  | 223.11 | 223.11 | 0 | 70.62 | 223.11
E11/K149/SK/dm/213 | HOTEL | 45 | 77632 |  | Cable Pulling Work | Basement 1 | Independent 1.8m wide | 1 | 5 | 2.5 | 3.25 | 1 | m2-LxH | 16.25 | 2022-11-15 |  | 100% | 100% | 0% | 1.5714 | 16.76 | 0.77 | 190.65 | 19.66 | 0 | 210.31 |  | 210.31 |  |  | 210.31 | 210.31 | 0 | 17.53 | 210.31
E11/K149/SK/dm/213 | HOTEL | 2e | 77634 |  | Duct Fixing Work (KMEP) | Level 5 | Additional Boarding | 1 | 3 | 1 | 1 | 1 | m2-LxW | 3 | 2022-11-16 |  | 100% | 100% | 0% | 1.4286 | 6.63 | 0.7 | 13.92 | 3 | 0 | 16.92 |  | 16.92 |  |  | 16.92 | 16.92 | 0 | 7.33 | 16.92
E11/K149/SK/dm/213 | HOTEL | 46 | 77635 |  | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 2.5 | 3 | 1 | rm | 3 | 2022-11-17 |  | 100% | 100% | 0% | 1.2857 | 63.34 | 7.28 | 133.01 | 28.08 | 0 | 161.09 |  | 161.09 |  |  | 161.09 | 161.09 | 0 | 70.62 | 161.09
E11/K149/SK/dm/213 | HOTEL | 46a | 77636 |  | Cable Pulling Work | Basement 1 | Butress | 1 | 2.5 | 2.5 | 3 |  | m3 | 18.75 | 2022-11-17 |  | 100% | 100% | 0% | 1.2857 | 5.29 | 0.35 | 69.43 | 8.44 | 0 | 77.87 |  | 77.87 |  |  | 77.87 | 77.87 | 0 | 5.64 | 77.87
E11/K149/SK/dm/213 | HOTEL | 47 | 77637 |  | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 2.5 | 4.2 | 1 | rm | 4.2 | 2022-11-17 |  | 100% | 100% | 0% | 1.2857 | 63.34 | 7.28 | 186.22 | 39.31 | 0 | 225.53 |  | 225.53 |  |  | 225.53 | 225.53 | 0 | 70.62 | 225.53
E11/K149/SK/dm/213 | HOTEL | 48 | 77638 |  | GRC Divider Removel | Level 12 | Tower | 1 | 1.8 | 1.8 | 1.5 | 1 | rm | 1.5 | 2022-11-17 |  | 100% | 100% | 0% | 1.2857 | 63.34 | 7.28 | 66.51 | 14.04 | 0 | 80.55 |  | 80.55 |  |  | 80.55 | 80.55 | 0 | 70.62 | 80.55
E11/K149/SK/dm/213 | HOTEL | 48a | 77638 |  | GRC Divider Removel | Level 12 | Cantilever (0 < 0.5m width) | 1 | 3.5 | 0.5 | 1 | 1 | m2-LxW | 1.75 | 2022-11-17 |  | 100% | 100% | 0% | 1.2857 | 32.75 | 1.05 | 40.12 | 2.36 | 0 | 42.48 |  | 42.48 |  |  | 42.48 | 42.48 | 0 | 33.8 | 42.48
E11/K149/SK/dm/213 | HOTEL | 48a | 77638 |  | GRC Divider Removel | Level 12 | Netting Supply & Install | 1 | 9 | 1 | 1 | 1 | m2-LxH | 9 | 2022-11-17 |  | 100% | 100% | 0% | 1.2857 | 8.52 | 0 | 53.68 | 0 | 0 | 53.68 |  | 53.68 |  |  | 53.68 | 53.68 | 0 | 8.52 | 53.68
E11/K149/SK/dm/213 | HOTEL | 36a | 77639 |  | GRC Divider Removel | Level 18 to 20 | Tower | 1 | 1.8 | 1.8 | 7 | 1 | rm | 7 | 2022-11-17 |  | 100% | 100% | 0% | 1.2857 | 63.34 | 7.28 | 310.37 | 65.52 | 0 | 375.89 |  | 375.89 |  |  | 375.89 | 375.89 | 0 | 70.62 | 375.89
E11/K149/SK/dm/213 | HOTEL | 36b | 77639 |  | GRC Divider Removel | Level 18 to 20 | Cantilever (0 < 0.5m width) | 1 | 3 | 0.5 | 1 | 1 | m2-LxW | 1.5 | 2022-11-17 |  | 100% | 100% | 0% | 1.2857 | 32.75 | 1.05 | 34.39 | 2.03 | 0 | 36.42 |  | 36.42 |  |  | 36.42 | 36.42 | 0 | 33.8 | 36.42
E11/K149/SK/dm/213 | HOTEL | 36b | 77639 |  | GRC Divider Removel | Level 18 to 20 | Netting Supply & Install | 1 | 37.8 | 1 | 1 |  | m2-LxH | 37.8 | 2022-11-17 |  | 100% | 100% | 0% | 1.2857 | 8.52 |  | 225.44 | 0 | 0 | 225.44 |  | 225.44 |  |  | 225.44 | 225.44 | 0 | 8.52 | 225.44
E11/K149/SK/dm/259 | HOTEL | 49 | 77640 |  | Inverted Scaffold | Level 29 | Design 1399-26 | 1 | 21 | 1.8 | 4 | 1 | lm | 21 | 2022-11-17 |  | 100% | 100% | 0% | 1.2857 | 1002.22 | 98.12 | 14732.63 | 2649.24 | 0 | 17381.87 |  | 17381.87 | Tas Quote - 2439-6-1 |  | 17381.87 | 17381.87 | 0 | 1100.34 | 17381.87
E11/K149/SK/dm/213 | HOTEL | 49a | 77641 |  | Wall Cutting Work | Level 29 | Additional Boarding | 1 | 15 | 1 | 1 | 1 | m2-LxW | 15 | 2022-11-17 |  | 100% | 100% | 0% | 1.2857 | 6.63 | 0.7 | 69.62 | 13.5 | 0 | 83.12 |  | 83.12 |  |  | 83.12 | 83.12 | 0 | 7.33 | 83.12
E11/K149/SK/dm/213 | HOTEL | 50 | 77642 |  | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 2.5 | 4 | 1 | rm | 4 | 2022-11-18 |  | 100% | 100% | 0% | 1.1429 | 63.34 | 7.28 | 177.35 | 33.28 | 0 | 210.63 |  | 210.63 |  |  | 210.63 | 210.63 | 0 | 70.62 | 210.63
E11/K149/SK/dm/213 | HOTEL | 51 | 77643 |  | Staircase 7 For Electrical Work | Ground Level | Independent 1.8m wide | 1 | 3.8 | 2.5 | 2.8 | 1 | m2-LxH | 10.64 | 2022-11-18 |  | 100% | 100% | 0% | 1.1429 | 16.76 | 0.77 | 124.83 | 9.36 | 0 | 134.19 |  | 134.19 |  |  | 134.19 | 134.19 | 0 | 17.53 | 134.19
E11/K149/JA/dm/429 | HOTEL | 52 | 77645 |  | Balcony Access | Level 20 | Tower | 1 | 2.5 | 1.3 | 3.5 | 1 | unit | 1 | 2022-11-18 |  | 100% | 100% | 0% | 1.1429 | 1278.36 | 29.12 | 894.85 | 33.28 | 0 | 928.13 |  | 928.13 | Tas Quote -2439-20-1 (item#7) |  | 928.13 | 928.13 | 0 | 1307.48 | 928.13
E11/K149/SK/dm/213 | HOTEL | 52a | 77645 |  | Balcony Access | Level 21 | Cantilever (0.5 > 1.2m width) | 1 | 1.3 | 0.75 | 1 | 1 | m2-LxW | 0.98 | 2022-11-18 |  | 100% | 100% | 0% | 1.1429 | 36.52 | 2.94 | 25.05 | 3.29 | 0 | 28.34 |  | 28.34 |  |  | 28.34 | 28.34 | 0 | 39.46 | 28.34 |  |  | 85.96
E11/K149/SK/dm/213 | HOTEL | 13b | 77646 |  | GRC Divider Removel | Level 14 | Tower | 1 | 1.5 | 0.5 | 1.5 | 1 | rm | 1.5 | 2022-11-18 |  | 100% | 100% | 0% | 1.1429 | 63.34 | 7.28 | 66.51 | 12.48 | 0 | 78.99 |  | 78.99 |  |  | 78.99 | 78.99 | 0 | 70.62 | 78.99
E11/K149/SK/dm/213 | HOTEL | 25d | 77647 |  | Wall Finishing Work | Basement 1 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-11-19 |  | 100% | 100% | 0% | 1 | 36.52 | 2.94 | 38.35 | 4.41 | 0 | 42.76 |  | 42.76 |  |  | 42.76 | 42.76 | 0 | 39.46 | 42.76 |  | 13.14
E11/K149/SK/dm/213 | HOTEL | 51a | 77644 |  | Staircase 7 For Electrical Work | Ground Level | Tower | 1 | 2.5 | 0.9 | 2.5 | 1 | rm | 2.5 | 2022-11-18 |  | 100% | 100% | 0% | 1.1429 | 63.34 | 7.28 | 110.85 | 20.8 | 0 | 131.65 |  | 131.65 |  |  | 131.65 | 131.65 | 0 | 70.62 | 131.65 |  |  |  | E & D Rate | Hire Charge
E11/K149/PK/dm/378 | HOTEL | 43b&43c | 77648 |  | Ramp Area GRC Pannel Fixing Work | Ground Level | Design 1399-21 | 1 | 5.1 | 1.3 | 5 | 1 | m2-LxH | 25.5 | 2022-11-21 |  | 100% | 100% | 0% | 0.71429 | 95.9 | 13.9 | 1711.82 | 253.18 | 0 | 1965 |  | 1965 | Tas Quote - 2439-15-1 (item-1 Prorate) |  | 1965 | 1965 | 0 | 109.8 | 1965 |  |  |  | 1234.63 | 50.37
E11/K149/SK/dm/213 | HOTEL | 53 | 77649 |  | Plant Room For Duct Work | Level 5 | Independent 1.8m wide | 1 | 4.3 | 1.8 | 4.5 | 1 | m2-LxH | 19.35 | 2022-11-21 |  | 100% | 100% | 0% | 0.71429 | 16.76 | 0.77 | 227.01 | 10.64 | 0 | 237.65 |  | 237.65 |  |  | 237.65 | 237.65 | 0 | 17.53 | 237.65 |  |  |  | 370.39 | 15.11
E11/K149/SK/dm/213 | HOTEL | 53a | 79051 |  | Plant Room For Duct Work | Level 5 | Tower | 1 | 2.5 | 1.8 | 2.5 | 1 | rm | 2.5 | 2022-11-22 |  | 100% | 100% | 0% | 0.57143 | 63.34 | 7.28 | 110.85 | 10.4 | 0 | 121.25 |  | 121.25 |  |  | 121.25 | 121.25 | 0 | 70.62 | 121.25 |  |  |  | 1347.48 | 50.4
E11/K149/JA/dm/429 | HOTEL | 54 | 79052 |  | Balcony Access | Level 10 | Tower | 1 | 2.5 | 1.3 | 4 | 1 | unit | 1 | 2022-11-22 |  | 100% | 100% | 0% | 0.57143 | 1278.36 | 29.12 | 894.85 | 16.64 | 0 | 911.49 |  | 911.49 | Tas Quote -2439-20-1 (item#2) |  | 911.49 | 911.49 | 0 | 1307.48 | 911.49 |  |  |  | 750.85 | 60.45
E11/K149/SK/dm/213 | HOTEL | 54a | 79052 |  | Balcony Access | Level 10 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1.3 | 1 | 1 | m2-LxW | 1.95 | 2022-11-22 |  | 100% | 100% | 0% | 0.57143 | 36.52 | 2.94 | 49.85 | 3.28 | 0 | 53.13 |  | 53.13 |  |  | 53.13 | 53.13 | 0 | 39.46 | 53.13 |  |  |  | 177.21 | 18.71
E11/K149/SK/dm/213 | HOTEL | 55 | 79053 |  | GRC Divider Removel | Level 13 | Tower | 1 | 2.5 | 1 | 4.7 | 1 | rm | 4.7 | 2022-11-22 |  | 100% | 100% | 0% | 0.57143 | 63.34 | 7.28 | 208.39 | 19.55 | 0 | 227.94 |  | 227.94 |  |  | 227.94 | 227.94 | 0 | 70.62 | 227.94 |  |  |  |  | 195.04
E11/K149/SK/dm/213 | HOTEL | 55a | 79053 |  | GRC Divider Removel | Level 13 | Cantilever (0 < 0.5m width) | 1 | 1 | 0.5 | 1 | 1 | m2-LxW | 0.5 | 2022-11-22 |  | 100% | 100% | 0% | 0.57143 | 32.75 | 1.05 | 11.46 | 0.3 | 0 | 11.76 |  | 11.76 |  |  | 11.76 | 11.76 | 0 | 33.8 | 11.76 |  |  |  | 3880.56
E11/K149/SK/dm/213 | HOTEL | 55 | 79053 |  | GRC Divider Removel | Level 13 | Netting Supply & Install | 1 | 25 | 1 | 1 | 1 | m2-LxH | 25 | 2022-11-22 |  | 100% | 100% | 0% | 0.57143 | 8.52 | 0 | 149.1 | 0 | 0 | 149.1 |  | 149.1 |  |  | 149.1 | 149.1 | 0 | 8.52 | 149.1
E11/K149/SK/dm/213 | HOTEL | 36c | 79054 |  | GRC Divider Removel | Level 18 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1.2 | 1 | 1 | m2-LxW | 1.8 | 2022-11-22 |  | 100% | 100% | 0% | 0.57143 | 36.52 | 2.94 | 46.02 | 3.02 | 0 | 49.04 |  | 49.04 |  |  | 49.04 | 49.04 | 0 | 39.46 | 49.04
E11/K149/JA/dm/429 | HOTEL | 56 | 79055 |  | Balcony Access | Level 15 | Tower | 1 | 2.5 | 1 | 3.5 | 1 | unit | 1 | 2022-11-23 |  | 100% | 100% | 0% | 0.42857 | 1278.36 | 29.12 | 894.85 | 12.48 | 0 | 907.33 |  | 907.33 | Tas Quote -2439-20-1 (item#4) |  | 907.33 | 907.33 | 0 | 1307.48 | 907.33
E11/K149/SK/dm/213 | HOTEL | 56a | 79055 |  | Balcony Access | Level 15 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-11-23 |  | 100% | 100% | 0% | 0.42857 | 36.52 | 2.94 | 38.35 | 1.89 | 0 | 40.24 |  | 40.24 |  |  | 40.24 | 40.24 | 0 | 39.46 | 40.24
E11/K149/JA/dm/429 | HOTEL | 57 | 79056 |  | Balcony Access | Level 18 | Tower | 1 | 2.5 | 1 | 6 | 3 | unit | 1 | 2022-11-23 |  | 100% | 100% | 0% | 0.42857 | 1783.37 | 40.04 | 1248.36 | 17.16 | 0 | 1265.52 |  | 1265.52 | Tas Quote -2439-20-1 (item#6) |  | 1265.52 | 1265.52 | 0 | 1823.41 | 1265.52
E11/K149/SK/dm/213 | HOTEL | 57a | 79056 |  | Balcony Access | Level 18 | Cantilever (0.5 > 1.2m width) | 1 | 1 | 1 | 1 | 1 | m2-LxW | 1 | 2022-11-23 |  | 100% | 100% | 0% | 0.42857 | 36.52 | 2.94 | 25.56 | 1.26 | 0 | 26.82 |  | 26.82 |  |  | 26.82 | 26.82 | 0 | 39.46 | 26.82
E11/K149/JA/dm/429 | HOTEL | 58 | 79057 |  | Balcony Access | Level 7 | Tower | 1 | 2.5 | 1 | 3.5 | 1 | unit | 1 | 2022-11-23 |  | 100% | 100% | 0% | 0.42857 | 1278.36 | 29.12 | 894.85 | 12.48 | 0 | 907.33 |  | 907.33 | Tas Quote -2439-20-1 (item#1) |  | 907.33 | 907.33 | 0 | 1307.48 | 907.33
E11/K149/SK/dm/213 | HOTEL | 58a | 79057 |  | Balcony Access | Level 7 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-11-23 |  | 100% | 100% | 0% | 0.42857 | 36.52 | 2.94 | 38.35 | 1.89 | 0 | 40.24 |  | 40.24 |  |  | 40.24 | 40.24 | 0 | 39.46 | 40.24
E11/K149/JA/dm/429 | HOTEL | 59 | 79058 |  | Balcony Access | Level 13 | Tower | 1 | 2.5 | 1 | 3.5 | 1 | unit | 1 | 2022-11-24 |  | 100% | 100% | 0% | 0.28571 | 1278.36 | 29.12 | 894.85 | 8.32 | 0 | 903.17 |  | 903.17 | Tas Quote -2439-20-1 (item#3) |  | 903.17 | 903.17 | 0 | 1307.48 | 903.17
E11/K149/SK/dm/213 | HOTEL | 59a | 79058 |  | Balcony Access | Level 13 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-11-24 |  | 100% | 100% | 0% | 0.28571 | 36.52 | 2.94 | 38.35 | 1.26 | 0 | 39.61 |  | 39.61 |  |  | 39.61 | 39.61 | 0
E11/K149/SK/dm/213 | HOTEL | 25e | 79059 |  | Wall Finishing Work | Basement 1 | Independent | 1 | 4.1 | 1.3 | 1.5 | 1 | m2-LxH | 6.15 | 2022-11-24 |  | 100% | 100% | 0% | 0.28571 | 12.01 | 0.49 | 51.7 | 0.86 | 0 | 52.56 |  | 52.56 |  |  | 52.56 | 52.56 | 0
Total |  |  | 297 | 119 | [18 empty] | 402731.7 | 175202.88 | 22309.15 | 601002.34 | 346944.14 | 254058.2 |  |  | 253300.02 | 600243.73 | -758.61
Note on W159: Himal Kosala: Please refer your supporting

## Order References
Rate Card Ref | Order Reference | Scaffolding Type | Fixed Duration | Item | Unit | Rate IN AED
1 | E11/K149/SK/dm/213 | Static tower | 0 | Erect & Dismantle | Rising Meter | 63.34
2 | E11/K149/SK/dm/213 | Static tower | 0 | Hire per Week | Rising Meter | 7.28
3 | E11/K149/SK/dm/213 | Mobile Tower | 0 | Erect & Dismantle | Rising Meter | 103.33
4 | E11/K149/SK/dm/213 | Mobile Tower | 0 | Hire per Week | Rising Meter | 10.29
5 | E11/K149/SK/dm/213 | Heavy duty tower | 0 | Erect & Dismantle | Rising Meter | 148
6 | E11/K149/SK/dm/213 | Heavy duty tower | 0 | Hire per Week | Rising Meter | 12.88
7 | E11/K149/SK/dm/213 | Independent 1.2m wide | 0 | Erect & Dismantle | M2 (LxH) | 12.01
8 | E11/K149/SK/dm/213 | Independent 1.2m wide | 0 | Hire per Week | M2 (LxH) | 0.49
9 | E11/K149/SK/dm/213 | Independent 1.8m wide | 0 | Erect & Dismantle | M2 (LxH) | 16.76
10 | E11/K149/SK/dm/213 | Independent 1.8m wide | 0 | Hire per Week | M2 (LxH) | 0.77
11 | E11/K149/SK/dm/213 | Birdcage | 0 | Erect & Dismantle | M3 | 7.08
12 | E11/K149/SK/dm/213 | Birdcage | 0 | Hire per Week | M3/Day | 0.49
13 | E11/K149/SK/dm/213 | Heavy duty birdcage | 0 | Erect & Dismantle | M3 | 10
14 | E11/K149/SK/dm/213 | Heavy duty birdcage | 0 | Hire per Week | M3/Day | 0.91
15 | E11/K149/SK/dm/213 | Buttress | 0 | Erect & Dismantle | M3 | 5.29
16 | E11/K149/SK/dm/213 | Buttress | 0 | Hire per Week | M3/Day | 0.35
17 | E11/K149/SK/dm/213 | Boarded lift | 0 | Erect & Dismantle | M2 (LxW) | 6.63
18 | E11/K149/SK/dm/213 | Boarded lift | 0 | Hire per Week | M2 (LxW) | 0.7
19 | E11/K149/SK/dm/213 | Cantilever (0 < 0.5m width) | 0 | Erect & Dismantle | M2 (LxW) | 32.75
20 | E11/K149/SK/dm/213 | Cantilever (0 < 0.5m width) | 0 | Hire per Week | M2 (LxW) | 1.05
21 | E11/K149/SK/dm/213 | Cantilever (0.5 > 1.2m width) | 0 | Erect & Dismantle | M2 (LxW) | 36.52
22 | E11/K149/SK/dm/213 | Cantilever (0.5 > 1.2m width) | 0 | Hire per Week | M2 (LxW) | 2.94
23 | E11/K149/SK/dm/213 | Bridge | 0 | Erect & Dismantle | Linear Meter | 37.43
24 | E11/K149/SK/dm/213 | Bridge | 0 | Hire per Week | Linear Meter | 1.4
25 | E11/K149/SK/dm/213 | Counterweight (Scaffold Tubes) | 0 | Erect & Dismantle | Linear Meter | 0.3
26 | E11/K149/SK/dm/213 | Counterweight (Scaffold Tubes) | 0 | Hire per Week | Linear Meter | 0.14
27 | E11/K149/SK/dm/213 | Edge protection - A Frame Single | 0 | Erect & Dismantle | Linear Meter | 7
28 | E11/K149/SK/dm/213 | Edge protection - A Frame Single | 0 | Hire per Week | Linear Meter | 0.42
29 | E11/K149/SK/dm/213 | Edge protection - A Frame double | 0 | Erect & Dismantle | Linear Meter | 12
30 | E11/K149/SK/dm/213 | Edge protection - A Frame double | 0 | Hire per Week | Linear Meter | 0.7
31 | E11/K149/SK/dm/213 | Edge Protection - Double | 0 | Erect & Dismantle | Linear Meter | 15
32 | E11/K149/SK/dm/213 | Edge Protection - Double | 0 | Hire per Week | Linear Meter | 0.91
33 | E11/K149/SK/dm/213 | Edge Protection - Double (Hilti) | 0 | Erect & Dismantle | Linear Meter | 24
34 | E11/K149/SK/dm/213 | Edge Protection - Double (Hilti) | 0 | Hire per Week | Linear Meter | 0.7
35 | E11/K149/SK/dm/213 | Netting supply - Beige Colour | 0 | Supply only | M2 (LxH) | 4.52
36 | E11/K149/SK/dm/213 | Netting install | 0 | Supply only | M2 (LxH) | 4
37 | E11/K149/SK/dm/213 | Staircase Supported by structure | 0 | Erect & Dismantle | Rising Meter | 250
38 | E11/K149/SK/dm/213 | Staircase Supported by structure | 0 | Hire per Week | Rising Meter | 14.35
39 | E11/K149/SK/dm/213 | Staircase supported by Buttress | 0 | Erect & Dismantle | Rising Meter | 376.2
40 | E11/K149/SK/dm/213 | Staircase supported by Buttress | 0 | Hire per Week | Rising Meter | 40.11
41 | E11/K149/SK/dm/213 | Manpower - Scaffolder | 0 | Dayworks | Hour | 20.5
42 | E11/K149/SK/dm/213 | Manpower - Foreman | 0 | Dayworks | Hour | 24
43 | E11/K149/SK/dm/216 | Aluminium Tower | 0 | Erect & Dismantle | Set | 0
44 | E11/K149/SK/dm/216 | Aluminium Tower | 0 | Hire per Week | Set | 28.5714
45 | E11/K149/SK/dm/238 | Design - TAS-1399-10A | 1 | Erect & Dismantle | Lumpsum | 6044.84
46 | E11/K149/SK/dm/238 | Design - TAS-1399-10A | 1 | Hire per Week | Hire per Week | 45.3871
47 | E11/K149/SK/dm/239 | Design - TAS-1399-7 | 1 | Erect & Dismantle | Lumpsum | 16252.45
48 | E11/K149/SK/dm/239 | Design - TAS-1399-7 | 1 | Hire per Week | Hire per Week | 89.4243
49 | E11/K149/SK/dm/256 | Balcony Scaffold - Type1 | 1 | Erect & Dismantle | Lumpsum | 4844.83
50 | E11/K149/SK/dm/256 | Balcony Scaffold - Type1 | 1 | Hire per Week | Hire per Week | 15.99
51 | E11/K149/SK/dm/256 | Balcony Scaffold - Type2 | 1 | Erect & Dismantle | Lumpsum | 4990.83
52 | E11/K149/SK/dm/256 | Balcony Scaffold - Type2 | 1 | Hire per Week | Hire per Week | 17.4214
53 | E11/K149/SK/dm/256 | Balcony Scaffold - Type3 | 1 | Erect & Dismantle | Lumpsum | 5095.97
54 | E11/K149/SK/dm/256 | Balcony Scaffold - Type3 | 1 | Hire per Week | Hire per Week | 18.45
55 | E11/K149/SK/dm/256 | Balcony Scaffold - Type4 | 1 | Erect & Dismantle | Lumpsum | 4127.36
56 | E11/K149/SK/dm/256 | Balcony Scaffold - Type4 | 1 | Hire per Week | Hire per Week | 8.4371
57 | E11/K149/SK/dm/256 | Balcony Scaffold - Type5 | 1 | Erect & Dismantle | Lumpsum | 8714.14
58 | E11/K149/SK/dm/256 | Balcony Scaffold - Type5 | 1 | Hire per Week | Hire per Week | 38.73
59 | E11/K149/SK/dm/256 | Balcony Scaffold - Type6 | 1 | Erect & Dismantle | Lumpsum | 5210.58
60 | E11/K149/SK/dm/256 | Balcony Scaffold - Type6 | 1 | Hire per Week | Hire per Week | 19.3229
61 | E11/K149/SK/dm/256 | Balcony Scaffold - Type7 | 1 | Erect & Dismantle | Lumpsum | 5900.72
62 | E11/K149/SK/dm/256 | Balcony Scaffold - Type7 | 1 | Hire per Week | Hire per Week | 26.07
63 | E11/K149/SK/dm/257 | Design - TAS-1399-02D | 1 | Erect & Dismantle | Lumpsum | 53510.26
64 | E11/K149/SK/dm/257 | Design - TAS-1399-02D | 1 | Hire per Week | Hire per Week | 401
65 | E11/K149/SK/dm/259 | Design - TAS-1399-06B | 1 | Erect & Dismantle | Lumpsum | 158449.11
66 | E11/K149/SK/dm/259 | Design - TAS-1399-06B | 1 | Hire per Week | Hire per Week | 2018.4243
67 | CONTRACT - 201A22002/49
68 | E11/K149/HN/dm/285 | Design-TAS-1399-12 | 1 | Erect & Dismantle | Lumpsum | 5083.25
69 | E11/K149/HN/dm/285 | Design-TAS-1399-12 | 1 | Hire per Week | Hire per Week | 123.48
70 | E11/K149/SK/dm/365 |  | 1 | Erect & Dismantle | Lumpsum | 5979.17
71 | E11/K149/SK/dm/350 | Design-TAS-1399-14 | 1 | Erect & Dismantle | Lumpsum | 14003.16
72 | E11/K149/SK/dm/350 | Design-TAS-1399-14 | 1 | Hire per Week | Hire per Week | 660.1
73 | E11/K149/SK/dm/300 | Design-Tas-1399-13A | 1 | Erect & Dismantle | Lumpsum | 4082.38
74 | E11/K149/SK/dm/300 | Design-Tas-1399-13A | 1 | Hire per Week | Hire per Week | 49.28
75 | E11/K149/SK/dm/341 |  | 1 | Erect & Dismantle | Lumpsum | 5325.76
76 | E11/K149/SK/dm/341 |  | 1 | Hire per Week | Hire per Week | 48.26
77 | E11/K149/SK/dm/341 |  | 1 | Erect & Dismantle | Lumpsum | 1375.16
78 | E11/K149/SK/dm/341 |  | 1 | Hire per Week | Hire per Week | 6.17
79 | E11/K149/MS/dm/396 |  | 1 | Erect & Dismantle | Lumpsum | 2448.62
80 | E11/K149/MS/dm/396 |  | 1 | Hire per Week | Hire per Week | 57.19
81 | E11/K149/PK/dm/400 | Design-Tas-1399-22 | 1 | Erect & Dismantle | Lumpsum | 15415.16
82 | E11/K149/PK/dm/400 | Design-Tas-1399-22 | 1 | Hire per Week | Hire per Week | 297.83
83 | E11/K149/PK/dm/378 | Design -Tas-1399-21 | 1 | Erect & Dismantle | Lumpsum | 11289.34
84 | E11/K149/PK/dm/378 | Design -Tas-1399-21 | 1 | Hire per Week | Hire per Week | 1429.84
85 | E11/K149/JA/dm/429 |  | 1 | Erect & Dismantle | Lumpsum | 13590.73
86 | E11/K149/JA/dm/429 |  | 1 | Hire per Week | Hire per Week | 302.12
87 | E11/K149/JJ/dm/377 | Design -Tas-1399-20a | 1 | Erect & Dismantle | Lumpsum | 32825.12
88 | E11/K149/JJ/dm/377 | Design -Tas-1399-20a | 1 | Hire per Week | Hire per Week | 2044.24
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174

## Modification
Khansaheb Civil Engineering LLC
Application No.: | 3
Project Name: | Dorchester Hotel & Residences (Completion Works)
Order Reference: | 201A22002/49
As On Date: | 2022-11-25
Dayworks
DTS | Date | Hrs | Total | Previous | Net Amount
62652 | 2022-09-18 | 26 | 533 | 533 | 0
62653 | 2022-09-30 | 6 | 123 | 123 | 0
62654 | 2022-10-10 | 30 | 615 | 615 | 0
62655 | 2022-11-16 | 8 | 164 | 0 | 164
62657 | 2022-11-21 | 54 | 1107 | 0 | 1107
62658 | 2022-11-21 | 16 | 328 | 0 | 328
Total |  | 140 | 2870 | 1,271.00 | 1599
Note on B2: LGee: Update these informations

## Manpower (hidden)
Client: | Khansaheb Civil Engineering LLC
Application No.: | 3
Project Name: | Dorchester Hotel & Residences (Completion Works)
Site: | #REF!
As Of: | 2022-11-25
Modification Hours
DTS | Date | Scaffolder | Foreman | Cumulative | Previous | Net
Total |  |  |  | 0 | 0 | 0

## SCOPE (hidden)
SCOPE OF WORKS & ADDITIONAL WORKS RATES
Reference | Description | Number | L | W | H | BL | Item Price | Period (Wks) | Extra Hire per Week

## PASummary (hidden)
Client: | Khansaheb Civil Engineering LLC
Project Name: | Dorchester Hotel & Residences (Completion Works)
Contract Ref: | 201A22002/49
PAYMENT APPLICATION SUMMARY
Application No. | Application Date | Works Carried Out | Day Works | Total | Remarks
1 | 2022-09-30 | 125287.35 | 0 | 125287.35
2 | 2022-10-31 | 221656.79 | 1,271.00 | 222927.79
3 | 2022-11-25 | 254058.2 | 1599 | 255657.2
0
0
0
0
0
Total |  | 601002.34 | 1599 | 603872.34 | 0