## PA Front Sheet
PAYMENT APPLICATION
Application # 2
Khansaheb Civil Engineering L.L.C. | Date | 2022-10-31 |  | HOTEL
PO Box - 2716 | Period As on | 2022-10-25 |  | RESIDENCE
Dubai | Type | Scaffolding Services
United Arab Emirates | Our Bankers | Bank Of Sharjah
Tel : 971 04 605 7200
Fax : 971 04 285 7539 | Account No. | 013 06 278065 01
Attn: Mr. Saman Kulasooriya
Dorchester Hotel & Residences (Completion Works) - 201A22002/49
Description | Previous Invoiced (AED) | This Application Value (AED) | Total Invoiced Net To Date (AED)
Contract Ref 201A22002/49
Scope Of Work | 86977.8 | 72956.06 | 159933.86
Varitaions | 37852.41 | 148671.73 | 186524.14
Dayworks | 0 | 1271 | 1271
Total | 124830.21 | 222898.79 | 347729
AED : Two Hundred Twenty-Six Thousand Three Hundred Sixty-Six and Ninety-Two Fils Only
(for Client use only) | Authorised Signatory
Technical Access Services LLC
The above amount is not inclusive of VAT

## Evaluation
Invoice Schedule
Khansaheb Civil Engineering LLC
Application No.: | 2
Project Name: | Dorchester Hotel & Residences (Completion Works)
Order Reference: | 201A22002/49 |  |  |  |  | Please check these
As On Date: | 2022-10-25 |  |  |  |  | Okay | [13 empty] | 16 | 2.2857
Billing Reference | Location | Tag No. | HOC | OHC | Description | Founding Level | Scaffold Type | Number | Length | Width | Height | Board Lift | Unit of Measure | Quantity | HOC Date | OHC Date | Erection % | Hire % | Dismantle % | Hire Weeks | E&D Rate per unit | Hire Rate per week | Erect Charges | Hire Charges | Dismantle Charges | Total Amount | Previous Amount | Net Amount | Remarks | Certified Amount (Previous) | Certified Amount (This Month) | Certified Amount (Cum) | Comments
E11/K149/SK/dm/257 | HOTEL | 1 | 74602 |  | Level-28/29 Block & Glass Work | Level 28-29 | Design-1399-02 rev-D | 1 |  |  |  |  | unit | 1 | 2022-09-26 |  | 100% | 100% | 0% | 4.2857 | 50703.26 | 2807 | 35492.28 | 12030 | 0 | 47522.28 | 37497.28 | 10025 | Tas Quote-2439-4-3 rev1 | 37497.28 | 10025 | 47522.28 | 0
E11/K149/SK/dm/216 | RESIDENCE |  |  |  | Hire of Aluminium Tower | NA | NA | 1 |  |  |  |  | unit | 1 | 2022-09-15 | 2022-10-01 | 0% | 100% | 0% | 2.4286 | 0 | 200 | 0 | 485.71 | 0 | 485.71 | 457.14 | 28.57 | TAS/HIRE/4969/SM | 0 | 485.71 | 485.71 | 0
CONTRACT - 201A22002/49 | RESIDENCE |  | 74652 |  | Contract Scope - Progressive Billing |  |  | 1 |  |  |  |  | unit | 1 | 2022-09-20 |  | 95% | 95% | 0% | 5.1429 | 191160 | 6716 | 127121.4 | 32812.46 | 0 | 159933.86 | 86977.8 | 72956.06 |  | 86977.8 | 72956.06 | 159933.86 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1b | 74653 | 76751 | Glass Channel Fixing | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 25.2 | 1.2 | 1 | 1 | m2-LxW | 30.24 | 2022-09-20 | 2022-09-26 | 100% | 100% | 100% | 1 | 36.52 | 2.94 | 773.06 | 88.91 | 331.31 | 1193.28 | 125.43 | 1067.85 |  | 125.43 | 1067.85 | 1193.28 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1f | 74654 |  | Glass Channel Fixing | Level 29 | Cantilever (0 < 0.5m width) | 1 | 5 | 0.5 | 1 | 1 | m2-LxW | 2.5 | 2022-09-20 |  | 100% | 100% | 0% | 5.1429 | 32.75 | 1.05 | 57.31 | 13.5 | 0 | 70.81 | 27.06 | 43.75 |  | 27.06 | 43.75 | 70.81 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1h | 74655 | 76752 | Glass Channel Fixing | Level 30 | Cantilever (0 < 0.5m width) | 1 | 16.2 | 0.5 | 1 | 1 | m2-LxW | 8.1 | 2022-09-21 | 2022-09-27 | 100% | 100% | 100% | 1 | 32.75 | 1.05 | 185.69 | 8.51 | 79.58 | 273.78 | 41.27 | 232.51 |  | 41.27 | 232.51 | 273.78 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1i | 74660 | 76753 | Glass Channel Fixing | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 1.8 | 1 | 1 | 1 | m2-LxW | 1.8 | 2022-09-24 | 2022-09-26 | 100% | 100% | 100% | 0.42857 | 36.52 | 2.94 | 46.02 | 2.27 | 19.72 | 68.01 | 38.79 | 29.22 |  | 38.79 | 29.22 | 68.01 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1j | 74666 | 76754 | Glass Channel Fixing | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 23.4 | 0.75 | 1 | 1 | m2-LxW | 17.55 | 2022-09-26 | 2022-09-28 | 100% | 100% | 100% | 0.42857 | 36.52 | 2.94 | 448.65 | 22.11 | 192.28 | 663.04 | 58.63 | 604.41 |  | 58.63 | 604.41 | 663.04 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1k | 74670 |  | Glass Channel Fixing | Level 30 | Cantilever (0 < 0.5m width) | 2 | 9.8 | 0.5 | 1 | 1 | m2-LxW | 9.8 | 2022-09-28 |  | 100% | 100% | 0% | 4 | 36.52 | 1.05 | 250.53 | 41.16 | 0 | 291.69 | 37.91 | 253.78 |  | 37.91 | 253.78 | 291.69 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1l | 74671 |  | Glass Channel Fixing | Level 30 | Cantilever (0 < 0.5m width) | 1 | 13.8 | 0.5 | 1 | 1 | m2-LxW | 6.9 | 2022-09-28 |  | 100% | 100% | 0% | 4 | 32.75 | 1.05 | 158.18 | 28.98 | 0 | 187.16 | 26.04 | 161.12 |  | 26.04 | 161.12 | 187.16 | 0
E11/K149/SK/dm/213 | RESIDENCE | 2a | 74662 |  | Glass Channel Fixing | Level 30 | Additional Boarding | 4 | 10.8 | 1.8 | 1 | 4 | m2-LxW | 77.76 | 2022-09-22 |  | 100% | 100% | 0% | 4.8571 | 6.63 | 0.7 | 360.88 | 264.38 | 0 | 625.26 | 0 | 625.26 |  |  | 625.26 | 625.26 | 0
E11/K149/SK/dm/213 | RESIDENCE | 2b | 74663 | 76758 | Colum G-3 Painting Works | Level 30 | Additional Boarding | 4 | 3.6 | 3.6 | 1 | 4 | m2-LxW | 51.84 | 2022-09-22 | 2022-10-15 | 100% | 100% | 100% | 3.4286 | 6.63 | 0.7 | 240.59 | 124.42 | 103.11 | 468.12 | 0 | 468.12 |  |  | 468.12 | 468.12 | 0
E11/K149/SK/dm/213 | RESIDENCE | 2c | 74664 | 76759 | Colum F-3 Painting Works | Level 30 | Additional Boarding | 4 | 3.6 | 3.6 | 1 | 4 | m2-LxW | 51.84 | 2022-09-22 | 2022-10-15 | 100% | 100% | 100% | 3.4286 | 6.63 | 0.7 | 240.59 | 124.42 | 103.11 | 468.12 | 0 | 468.12 |  |  | 468.12 | 468.12 | 0
E11/K149/SK/dm/213 | RESIDENCE | 2d | 74665 | 76760 | Colum D-3 Painting Works | Level 30 | Additional Boarding | 4 | 3.6 | 3.6 | 1 | 4 | m2-LxW | 51.84 | 2022-09-22 | 2022-10-15 | 100% | 100% | 100% | 3.4286 | 6.63 | 0.7 | 240.59 | 124.42 | 103.11 | 468.12 | 0 | 468.12 |  |  | 468.12 | 468.12 | 0
E11/K149/SK/dm/213 | RESIDENCE | 3a | 74668 | 76761 | Colum D-2 Painting Works | Level 29 | Additional Boarding | 6 | 3.5 | 3.5 | 1 | 6 | m2-LxW | 73.5 | 2022-09-27 | 2022-10-15 | 100% | 100% | 100% | 2.7143 | 6.63 | 0.7 | 341.11 | 139.65 | 146.19 | 626.95 | 0 | 626.95 |  |  | 626.95 | 626.95 | 0
E11/K149/SK/dm/213 | RESIDENCE | 3b | 74669 | 76762 | Colum F-G/2 Painting Works | Level 29 | Additional Boarding | 6 | 9 | 3.5 | 1 | 6 | m2-LxW | 189 | 2022-09-27 | 2022-10-15 | 100% | 100% | 100% | 2.7143 | 6.63 | 0.7 | 877.15 | 359.1 | 375.92 | 1612.17 | 0 | 1612.17 |  |  | 1612.17 | 1612.17 | 0
E11/K149/SK/dm/239 | RESIDENCE | 4 | 74673 |  | EIFS Removel & Reinstate Works | Ramp | Design-1399-07 rev-B | 1 |  |  |  |  | unit | 1 | 2022-10-01 |  | 100% | 100% | 0% | 3.5714 | 15626.48 | 625.97 | 10938.54 | 2235.61 | 0 | 13174.15 | 0 | 13174.15 | Tas Quote - 2439-8-2 |  | 13174.15 | 13174.15 | 0
E11/K149/SK/dm/238 | RESIDENCE | 5 | 74675 | 76768 | Level -30 Lobby Room Shaft-09 | Level 30 | Design -1399-10 rev-A | 1 |  |  |  |  | unit | 1 | 2022-10-03 | 2022-10-22 | 100% | 100% | 100% | 2.8571 | 5727.13 | 317.71 | 4008.99 | 907.74 | 1718.14 | 6634.87 | 0 | 6634.87 | Tas Quote - 2439-5-1 |  | 6634.87 | 6634.87 | 0
E11/K149/SK/dm/213 | RESIDENCE | 2e | 74676 | 76755 | Level - 30 Balcony Side Glass frame work | Level 30 | Additional Boarding | 1 | 3.6 | 1.8 | 1 | 1 | m2-LxW | 6.48 | 2022-10-04 | 2022-10-07 | 100% | 100% | 100% | 0.57143 | 6.63 | 0.7 | 30.07 | 2.59 | 12.89 | 45.55 | 0 | 45.55 |  |  | 45.55 | 45.55 | 0
E11/K149/HN/dm/285 | RESIDENCE | 6 | 74677 |  | Loading Bay Above Planter Trench | Ground Level | Design -1399-12 rev-A | 1 |  |  |  |  | unit | 1 | 2022-10-10 |  | 100% | 100% | 0% | 2.2857 | 4959.77 | 123.48 | 3471.84 | 282.24 | 0 | 3754.08 | 0 | 3754.08 | Tas Quote - 2439-10-1 |  | 3754.08 | 3754.08 | 0
E11/K149/SK/dm/213 | RESIDENCE | 7 | 74678 |  | Level -4 Planter Box Soil Filling | Level 4 | Independent | 1 | 15 | 1.5 | 0.8 | 1 | m2-LxH | 12 | 2022-10-10 |  | 100% | 100% | 0% | 2.2857 | 12.01 | 0.49 | 100.88 | 13.44 | 0 | 114.32 | 0 | 114.32 |  |  | 114.32 | 114.32 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8h | 74679 | 76756 | Pool Area Glass work | Level 26 | Additional Boarding | 1 | 4 | 1 | 1 | 1 | m2-LxW | 4 | 2022-10-10 | 2022-10-11 | 100% | 100% | 100% | 0.28571 | 6.63 | 0.7 | 18.56 | 0.8 | 7.96 | 27.32 | 0 | 27.32 |  |  | 27.32 | 27.32 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8i | 74682 |  | Level -30 Glass Frame work | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 19 | 0.75 | 1 | 1 | m2-LxW | 14.25 | 2022-10-12 |  | 100% | 100% | 0% | 2 | 36.52 | 2.94 | 364.29 | 83.79 | 0 | 448.08 | 0 | 448.08 |  |  | 448.08 | 448.08 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8j | 74683 | 76764 | Level -30 Glass Frame work | Level 30 | Cantilever (0 < 0.5m width) | 1 | 19.8 | 0.5 | 1 | 1 | m2-LxW | 9.9 | 2022-10-12 | 2022-10-21 | 100% | 100% | 100% | 1.4286 | 32.75 | 1.05 | 226.96 | 14.85 | 97.27 | 339.08 | 0 | 339.08 |  |  | 339.08 | 339.08 | 0
E11/K149/SK/dm/213 | RESIDENCE | 11 | 74684 | 76757 | Level -30 Shaft Mep Services | Level 30 | Independent | 1 | 3.6 | 1.2 | 2.5 | 1 | m2-LxH | 9 | 2022-10-13 | 2022-10-15 | 100% | 100% | 100% | 0.42857 | 12.01 | 0.49 | 75.66 | 1.89 | 32.43 | 109.98 | 0 | 109.98 |  |  | 109.98 | 109.98 | 0
E11/K149/HN/dm/285 | RESIDENCE | 12 | 74685 |  | Loading Bay Above Planter Trench | Ground Level | Design -1399-12 rev-A | 1 |  |  |  |  | unit | 1 | 2022-10-14 |  | 100% | 100% | 0% | 1.7143 | 4959.77 | 123.48 | 3471.84 | 211.68 | 0 | 3683.52 | 0 | 3683.52 | Tas Quote - 2439-10-1 |  | 3683.52 | 3683.52 | 0
E11/K149/SK/dm/213 | RESIDENCE | 13 | 74686 |  | Pool Plant Room (KMEP Work) | Level 3 | Independent | 1 | 7.3 | 1.3 | 1.7 | 1 | m2-LxH | 12.41 | 2022-10-14 |  | 100% | 100% | 0% | 1.7143 | 12.01 | 0.49 | 104.33 | 10.42 | 0 | 114.75 | 0 | 114.75 | KMEP |  | 114.75 | 114.75 | 0
E11/K149/SK/dm/213 | RESIDENCE | 14 | 74687 | 76763 | Colum Nut bolt Installation | Level 3 | Independent | 1 | 5.1 | 1.3 | 1.6 | 1 | m2-LxH | 8.16 | 2022-10-15 | 2022-10-17 | 100% | 100% | 100% | 0.42857 | 12.01 | 0.49 | 68.6 | 1.71 | 29.4 | 99.71 | 0 | 99.71 |  |  | 99.71 | 99.71 | 0
E11/K149/SK/dm/213 | RESIDENCE | 15 | 74688 |  | Pool Plant Room (KMEP Work) | Level 3 | Independent | 1 | 5 | 1.2 | 2 | 1 | m2-LxH | 10 | 2022-10-17 |  | 100% | 100% | 0% | 1.2857 | 12.01 | 0.49 | 84.07 | 6.3 | 0 | 90.37 | 0 | 90.37 | KMEP |  | 90.37 | 90.37 | 0
E11/K149/SK/dm/213 | RESIDENCE | 16 | 74689 | 76766 | Shaft -6 Kmep Duct Extension | Level 31 | Tower | 1 | 2.5 | 1.8 | 2.3 | 1 | rm | 2.3 | 2022-10-17 | 2022-10-22 | 100% | 100% | 100% | 0.85714 | 63.34 | 7.28 | 101.98 | 14.35 | 43.7 | 160.03 | 0 | 160.03 | KMEP |  | 160.03 | 160.03 | 0
E11/K149/SK/dm/213 | RESIDENCE | 16 | 74689 | 76766 | Shaft -6 Kmep Duct Extension | Level 31 | Additional Boarding | 1 | 2.5 | 1.8 | 1 | 1 | m2-LxW | 4.5 | 2022-10-17 | 2022-10-22 | 100% | 100% | 100% | 0.85714 | 6.63 | 0.7 | 20.88 | 2.7 | 8.95 | 32.53 | 0 | 32.53 | KMEP |  | 32.53 | 32.53 | 0
E11/K149/SK/dm/213 | RESIDENCE | 17 | 74690 |  | Level -2 Retail Unit 34 For (Kmep) | Level 2 | Birdcage | 1 | 17.5 | 10 | 6.2 | 1 | m3 | 1085 | 2022-10-18 |  | 100% | 100% | 0% | 1.1429 | 7.08 | 0.49 | 5377.26 | 607.6 | 0 | 5984.86 | 0 | 5984.86 | KMEP |  | 5984.86 | 5984.86 | 0
E11/K149/SK/dm/213 | RESIDENCE | 18 | 74691 |  | Basement 1 (Kmep work) | Basement 1 | Tower | 1 | 1.8 | 1.3 | 2.5 | 1 | rm | 2.5 | 2022-10-18 |  | 100% | 100% | 0% | 1.1429 | 63.34 | 7.28 | 110.85 | 20.8 | 0 | 131.65 | 0 | 131.65 | KMEP |  | 131.65 | 131.65 | 0
E11/K149/SK/dm/213 | RESIDENCE | 19 | 74692 |  | Staircase -4 For Water coring tank work | Level 31 | Independent | 1 | 4 | 1.3 | 6.3 | 1 | m2-LxH | 25.2 | 2022-10-18 |  | 100% | 100% | 0% | 1.1429 | 12.01 | 0.49 | 211.86 | 14.11 | 0 | 225.97 | 0 | 225.97 |  |  | 225.97 | 225.97 | 0
E11/K149/SK/dm/213 | RESIDENCE | 19a | 74700 |  | Staircase -4 For Water coring tank work | Level 31 | Independent | 1 | 4 | 1.3 | 2 | 1 | m2-LxH | 8 | 2022-10-19 |  | 100% | 100% | 0% | 1 | 12.01 | 0.49 | 67.26 | 3.92 | 0 | 71.18 | 0 | 71.18 |  |  | 71.18 | 71.18 | 0
E11/K149/SK/dm/213 | RESIDENCE | 20 | 74693 |  | Basement 1 (Kmep work) | Basement 1 | Tower | 1 | 2.5 | 2.5 | 3 | 1 | rm | 3 | 2022-10-18 |  | 100% | 100% | 0% | 1.1429 | 63.34 | 7.28 | 133.01 | 24.96 | 0 | 157.97 | 0 | 157.97 |  |  | 157.97 | 157.97 | 0
E11/K149/SK/dm/213 | RESIDENCE | 16a | 74694 | 76767 | Second Lift Duct Extension work | Level 31 | Tower | 1 | 2.5 | 1.8 | 2 | 1 | rm | 2 | 2022-10-19 | 2022-10-22 | 100% | 100% | 100% | 0.57143 | 63.34 | 7.28 | 88.68 | 8.32 | 38 | 135 | 0 | 135 |  |  | 135 | 135 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1n | 74695 |  | Fire Fifhting Sprinkler Work | Level 31 | Additional Boarding | 1 | 11.5 | 1.8 | 1 | 1 | m2-LxW | 20.7 | 2022-10-19 |  | 100% | 100% | 0% | 1 | 6.63 | 0.7 | 96.07 | 14.49 | 0 | 110.56 | 0 | 110.56 |  |  | 110.56 | 110.56 | 0
E11/K149/SK/dm/213 | RESIDENCE | 21 | 74696 |  | Basement 1 (Kmep work) | Basement 1 | Tower | 1 | 2.5 | 1.8 | 3 | 1 | rm | 3 | 2022-10-19 |  | 100% | 100% | 0% | 1 | 63.34 | 7.28 | 133.01 | 21.84 | 0 | 154.85 | 0 | 154.85 | KMEP |  | 154.85 | 154.85 | 0
E11/K149/SK/dm/213 | RESIDENCE | 22 | 74697 |  | Basement 1 (Kmep work) | Basement 1 | Independent | 1 | 3.1 | 1.3 | 3 | 1 | m2-LxH | 9.3 | 2022-10-19 |  | 100% | 100% | 0% | 1 | 12.01 | 0.49 | 78.19 | 4.56 | 0 | 82.75 | 0 | 82.75 | KMEP |  | 82.75 | 82.75 | 0
E11/K149/SK/dm/213 | RESIDENCE | 23 | 74698 |  | Basement 1 (Kmep work) | Basement 1 | Independent | 1 | 3.1 | 1.8 | 4.5 | 1 | m2-LxH | 13.95 | 2022-10-19 |  | 100% | 100% | 0% | 1 | 12.01 | 0.77 | 117.28 | 10.74 | 0 | 128.02 | 0 | 128.02 | KMEP |  | 128.02 | 128.02 | 0
E11/K149/SK/dm/213 | RESIDENCE | 24 | 74699 |  | Basement 1 (Kmep work) | Basement 1 | Tower | 1 | 2.5 | 2.5 | 4.5 | 1 | rm | 4.5 | 2022-10-19 |  | 100% | 100% | 0% | 1 | 63.34 | 7.28 | 199.52 | 32.76 | 0 | 232.28 | 0 | 232.28 | KMEP |  | 232.28 | 232.28 | 0
E11/K149/SK/dm/213 | RESIDENCE | 25 | 77652 |  | Basement 1 (Kmep work) | Basement 1 | Independent | 1 | 3.8 | 2.5 | 4.5 | 1 | m2-LxH | 17.1 | 2022-10-19 |  | 100% | 100% | 0% | 1 | 16.76 | 0.77 | 200.62 | 13.17 | 0 | 213.79 | 0 | 213.79 | KMEP |  | 213.79 | 213.79 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8k | 77653 |  | Glass Channel Fixing | Level 31 | Cantilever (0 < 0.5m width) | 1 | 18 | 0.5 | 1 | 1 | m2-LxW | 9 | 2022-10-19 |  | 100% | 100% | 0% | 1 | 32.75 | 1.05 | 206.33 | 9.45 | 0 | 215.78 | 0 | 215.78 |  |  | 215.78 | 215.78 | 0
E11/K149/SK/dm/213 | RESIDENCE | 26 | 77654 |  | Mockup For Bracket Fixing | Level 6 | Tower | 1 | 1.8 | 1 | 2 | 1 | rm | 2 | 2022-10-19 |  | 100% | 100% | 0% | 1 | 63.34 | 7.28 | 88.68 | 14.56 | 0 | 103.24 | 0 | 103.24 |  |  | 103.24 | 103.24 | 0
E11/K149/SK/dm/213 | RESIDENCE | 27 | 77655 |  | Basement 1 (Kmep work) | Basement 1 | Independent | 1 | 5 | 1.3 | 4.5 | 1 | m2-LxH | 22.5 | 2022-10-19 |  | 100% | 100% | 0% | 1 | 12.01 | 0.49 | 189.16 | 11.03 | 0 | 200.19 | 0 | 200.19 | KMEP |  | 200.19 | 200.19 | 0
E11/K149/SK/dm/213 | RESIDENCE | 28 | 77656 |  | Basement 1 (Kmep work) | Basement 1 | Tower | 1 | 2.5 | 1.8 | 4.5 | 1 | rm | 4.5 | 2022-10-20 |  | 100% | 100% | 0% | 0.85714 | 63.34 | 7.28 | 199.52 | 28.08 | 0 | 227.6 | 0 | 227.6 | KMEP |  | 227.6 | 227.6 | 0
E11/K149/SK/dm/213 | RESIDENCE | 28 | 77656 |  | Basement 1 (Kmep work) | Basement 1 | Additional Boarding | 1 | 2.5 | 1.8 |  | 1 | m2-LxW | 4.5 | 2022-10-20 |  | 100% | 100% | 0% | 0.85714 | 6.63 | 0.7 | 20.88 | 2.7 | 0 | 23.58 | 0 | 23.58 | KMEP |  | 23.58 | 23.58 | 0
E11/K149/SK/dm/213 | RESIDENCE | 29 | 77657 |  | Basement 1 (Kmep work) | Basement 1 | Tower | 1 | 2.5 | 1.8 | 4.5 | 1 | rm | 4.5 | 2022-10-20 |  | 100% | 100% | 0% | 0.85714 | 63.34 | 7.28 | 199.52 | 28.08 | 0 | 227.6 | 0 | 227.6 | KMEP |  | 227.6 | 227.6 | 0
E11/K149/SK/dm/213 | RESIDENCE | 2g | 77661 |  | Glass Fixing work | Level 30 | Cantilever (0 < 0.5m width) | 1 | 10.8 | 0.5 | 1 | 1 | m2-LxW | 5.4 | 2022-10-21 |  | 100% | 100% | 0% | 0.71429 | 32.75 | 1.05 | 123.8 | 4.05 | 0 | 127.85 | 0 | 127.85 |  |  | 127.85 | 127.85 | 0
E11/K149/SK/dm/213 | RESIDENCE | 2f | 77662 |  | Glass Fixing work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 3.6 | 0.75 | 1 | 1 | m2-LxW | 2.7 | 2022-10-21 |  | 100% | 100% | 0% | 0.71429 | 36.52 | 2.94 | 69.02 | 5.67 | 0 | 74.69 | 0 | 74.69 |  |  | 74.69 | 74.69 | 0
E11/K149/SK/dm/365 | RESIDENCE | 30 | 77667 |  | EIFS Fixing Work | Level 23 | Independent | 1 | 4 | 1.3 | 2 | 1 | unit | 1 | 2022-10-21 |  | 100% | 100% | 0% | 0.71429 | 916.08 | 3.92 | 641.26 | 2.8 | 0 | 644.06 | 0 | 644.06 | Tas Quote - 2439-14-1 (item-1) |  | 644.06 | 644.06 | 0
E11/K149/SK/dm/365 | RESIDENCE | 30a | 77668 |  | EIFS Fixing Work | Level 23 | Independent | 1 | 8 | 1.3 | 3 | 2 | unit | 1 | 2022-10-21 |  | 100% | 100% | 0% | 0.71429 | 2093.27 | 22.96 | 1465.29 | 16.4 | 0 | 1481.69 | 0 | 1481.69 | Tas Quote - 2439-14-1 (item-2) |  | 1481.69 | 1481.69 | 0
E11/K149/SK/dm/350 | RESIDENCE | 31 | 77669 |  | Above Air Extract trench Loading Bay | Ground Level | Design 1399-14 | 1 | 22.5 | 3.6 |  | 1 | unit | 1 | 2022-10-21 |  | 100% | 100% | 0% | 0.71429 | 13343.06 | 660.1 | 9340.14 | 471.5 | 0 | 9811.64 | 0 | 9811.64 | Tas Quote - 2439-13-1 |  | 9811.64 | 9811.64 | 0
E11/K149/SK/dm/213 | RESIDENCE | 32 | 77663 |  | Hotel Side Block Work | Level 31 | Independent | 1 | 3.6 | 1.3 | 4 | 1 | m2-LxH | 14.4 | 2022-10-22 |  | 100% | 100% | 0% | 0.57143 | 12.01 | 0.49 | 121.06 | 4.03 | 0 | 125.09 | 0 | 125.09 |  |  | 125.09 | 125.09 | 0
E11/K149/SK/dm/213 | RESIDENCE | 32 | 77663 |  | Hotel Side Block Work | Level 31 | Additional Boarding | 1 | 3.6 | 1.3 | 1 | 1 | m2-LxW | 4.68 | 2022-10-22 |  | 100% | 100% | 0% | 0.57143 | 6.63 | 0.7 | 21.72 | 1.87 | 0 | 23.59 | 0 | 23.59 |  |  | 23.59 | 23.59 | 0
E11/K149/SK/dm/213 | RESIDENCE | 33 | 77664 |  | Canal Side wall Cladding opening Work | Level 14 | Tower | 1 | 1.8 | 1.3 | 1 | 1 | rm | 1 | 2022-10-22 |  | 100% | 100% | 0% | 0.57143 | 63.34 | 7.28 | 44.34 | 4.16 | 0 | 48.5 | 0 | 48.5 |  |  | 48.5 | 48.5 | 0
E11/K149/SK/dm/213 | RESIDENCE | 34 | 77665 |  | Canal Side wall Cladding opening Work | Level 14 | Tower | 1 | 1.8 | 1.3 | 1 | 1 | rm | 1 | 2022-10-22 |  | 100% | 100% | 0% | 0.57143 | 63.34 | 7.28 | 44.34 | 4.16 | 0 | 48.5 | 0 | 48.5 |  |  | 48.5 | 48.5 | 0
E11/K149/SK/dm/213 | RESIDENCE | 4d | 77670 |  | EIFS work | Ground Level to Level 2 | Additional Boarding | 3 | 1.8 | 1.8 | 1 | 3 | m2-LxW | 9.72 | 2022-10-25 |  | 100% | 100% | 0% | 0.14286 | 6.63 | 0.7 | 45.11 | 0.97 | 0 | 46.08 | 0 | 46.08 |  |  | 46.08 | 46.08 | 0
E11/K149/SK/dm/213 | HOTEL | 2 | 74603 |  | Plant Room Façade Fin Supporting work | Level 5 | Independent | 1 | 4.9 | 1.8 | 4.2 | 1 | m2-LxH | 20.58 | 2022-10-04 |  | 100% | 100% | 0% | 3.1429 | 16.76 | 0.77 | 241.44 | 49.8 | 0 | 291.24 | 0 | 291.24 |  |  | 291.24 | 291.24 | 0
E11/K149/SK/dm/213 | HOTEL | 2a | 74604 |  | Plant Room Façade Fin Supporting work | Level 5 | Independent | 1 | 15.1 | 1.8 | 4.2 | 1 | m2-LxH | 63.42 | 2022-10-05 |  | 100% | 100% | 0% | 3 | 16.76 | 0.77 | 744.04 | 146.5 | 0 | 890.54 | 0 | 890.54 |  |  | 890.54 | 890.54 | 0
E11/K149/SK/dm/213 | HOTEL | 2b | 74605 |  | Plant Room For AC Duct Work | Level 5 | Additional Boarding | 1 | 6.8 | 1.8 | 1 | 1 | m2-LxW | 12.24 | 2022-10-05 |  | 100% | 100% | 0% | 3 | 6.63 | 0.7 | 56.81 | 25.7 | 0 | 82.51 | 0 | 82.51 |  |  | 82.51 | 82.51 | 0
E11/K149/SK/dm/213 | HOTEL | 2c | 74606 |  | Plant Room Façade Fin Supporting work | Level 5 | Cantilever (0.5 > 1.2m width) | 1 | 1 | 0.75 | 1 | 1 | m2-LxW | 0.75 | 2022-10-05 |  | 100% | 100% | 0% | 3 | 36.52 | 2.94 | 19.17 | 6.62 | 0 | 25.79 | 0 | 25.79 |  |  | 25.79 | 25.79 | 0
E11/K149/SK/dm/213 | HOTEL | 3 | 74607 |  | Plant Room Façade Fin Supporting work | Level 5 | Independent | 1 | 7.5 | 1.8 | 4.2 | 1 | m2-LxH | 31.5 | 2022-10-05 |  | 100% | 100% | 0% | 3 | 16.76 | 0.77 | 369.56 | 72.77 | 0 | 442.33 | 0 | 442.33 |  |  | 442.33 | 442.33 | 0
E11/K149/SK/dm/213 | HOTEL | 3a | 74608 |  | Plant Room Façade Fin Supporting work | Level 5 | Cantilever (0 < 0.5m width) | 1 | 5 | 0.25 | 1 | 1 | m2-LxW | 1.25 | 2022-10-05 |  | 100% | 100% | 0% | 3 | 32.75 | 1.05 | 28.66 | 3.94 | 0 | 32.6 | 0 | 32.6 |  |  | 32.6 | 32.6 | 0
E11/K149/SK/dm/213 | HOTEL | 4 | 74609 | 76802 | Air Extract Gratting Installation | Basement 1 | Independent | 1 | 9.3 | 1.3 | 5.9 | 1 | m2-LxH | 54.87 | 2022-10-07 | 2022-10-12 | 100% | 100% | 100% | 0.85714 | 12.01 | 0.49 | 461.29 | 23.05 | 197.7 | 682.04 | 0 | 682.04 |  |  | 682.04 | 682.04 | 0
E11/K149/SK/dm/213 | HOTEL | 4a | 74610 | 76803 | Air Extract Gratting Installation | Basement 1 | Cantilever (0 < 0.5m width) | 1 | 9.8 | 0.5 | 1 | 1 | m2-LxW | 4.9 | 2022-10-07 | 2022-10-12 | 100% | 100% | 100% | 0.85714 | 32.75 | 1.05 | 112.33 | 4.41 | 48.14 | 164.88 | 0 | 164.88 |  |  | 164.88 | 164.88 | 0
E11/K149/SK/dm/300 | HOTEL | 5 | 74611 | 76801 | Cradle Beam Support | Roof | Design 1399-13 rev-A | 1 | 4 | 2.5 | 2 | 1 | unit | 1 | 2022-10-07 | 2022-10-10 | 100% | 100% | 100% | 0.57143 | 4033.1 | 49.28 | 2823.17 | 28.16 | 1209.93 | 4061.26 | 0 | 4061.26 | Tas Quote - 2439-11-2 |  | 4061.26 | 4061.26 | 0
E11/K149/SK/dm/300 | HOTEL | 6 | 74612 |  | Cradle Beam Support (Re-erction) | Roof | Design 1399-13 rev-A | 1 | 4 | 2.5 | 2 | 1 | unit | 1 | 2022-10-10 |  | 100% | 100% | 0% | 2.2857 | 4033.1 | 49.28 | 2823.17 | 112.64 | 0 | 2935.81 | 0 | 2935.81 | Tas Quote - 2439-11-2 |  | 2935.81 | 2935.81 | 0
E11/K149/SK/dm/213 | HOTEL | 7 | 74613 |  | Planter Drain Connection (mep) | Basement 1 | Tower | 1 | 1.8 | 1.3 | 2.5 | 1 | rm | 2.5 | 2022-10-12 |  | 100% | 100% | 0% | 2 | 63.34 | 7.28 | 110.85 | 36.4 | 0 | 147.25 | 0 | 147.25 |  |  | 147.25 | 147.25 | 0
E11/K149/SK/dm/213 | HOTEL | 2d | 74614 |  | Planter Room Fin Supportting work | Level 5 | Additional Boarding | 1 | 4.3 | 1.5 | 1 | 1 | m2-LxW | 6.45 | 2022-10-12 |  | 100% | 100% | 0% | 2 | 6.63 | 0.7 | 29.93 | 9.03 | 0 | 38.96 | 0 | 38.96 |  |  | 38.96 | 38.96 | 0
E11/K149/SK/dm/213 | HOTEL | 3b | 74615 |  | Planter Room Fin Supportting work | Level 5 | Independent | 1 | 3 | 1.8 | 4.2 | 1 | m2-LxH | 12.6 | 2022-10-12 |  | 100% | 100% | 0% | 2 | 16.76 | 0.77 | 147.82 | 19.4 | 0 | 167.22 | 0 | 167.22 |  |  | 167.22 | 167.22 | 0
E11/K149/SK/dm/213 | HOTEL | 3c | 74616 |  | Planter Room Fin Supportting work | Level 5 | Independent | 1 | 5 | 1.3 | 4.2 | 1 | m2-LxH | 21 | 2022-10-12 |  | 100% | 100% | 0% | 2 | 12.01 | 0.49 | 176.55 | 20.58 | 0 | 197.13 | 0 | 197.13 |  |  | 197.13 | 197.13 | 0
E11/K149/SK/dm/213 | HOTEL | 8 | 74617 |  | Planter Room Fin Supportting work | Level 5 | Independent | 1 | 10.8 | 1.8 | 3.8 | 1 | m2-LxH | 41.04 | 2022-10-13 |  | 100% | 100% | 0% | 1.8571 | 16.76 | 0.77 | 481.48 | 58.69 | 0 | 544.68 | 0 | 544.68 |  |  | 540.17 | 540.17 | -4.51
E11/K149/SK/dm/213 | HOTEL | 8a | 74618 |  | Planter Room Fin Supportting work | Level 5 | Cantilever (0 < 0.5m width) | 1 | 10.8 | 0.5 | 1 | 1 | m2-LxW | 5.4 | 2022-10-13 |  | 100% | 100% | 0% | 1.8571 | 32.75 | 1.05 | 123.8 | 10.53 | 0 | 135.14 | 0 | 135.14 |  |  | 134.33 | 134.33 | -0.81
E11/K149/SK/dm/213 | HOTEL | 3d | 74619 |  | Plant Room For Kmep Work | Level 5 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-10-15 |  | 100% | 100% | 0% | 1.5714 | 36.52 | 2.94 | 38.35 | 6.93 | 0 | 45.28 | 0 | 45.28 | KMEP |  | 45.28 | 45.28 | 0
E11/K149/SK/dm/213 | HOTEL | 8b | 74620 |  | Plant Room For Kmep Work | Level 5 | Tower | 1 | 2.5 | 1.8 | 3.5 | 1 | rm | 3.5 | 2022-10-15 |  | 100% | 100% | 0% | 1.5714 | 63.34 | 7.28 | 155.18 | 40.04 | 0 | 195.22 | 0 | 195.22 | KMEP |  | 195.22 | 195.22 | 0
E11/K149/SK/dm/213 | HOTEL | 8c | 74621 |  | Plant Room For Kmep Work | Level 5 | Cantilever (0 < 0.5m width) | 1 | 4.8 | 0.5 | 1 | 1 | m2-LxW | 2.4 | 2022-10-15 |  | 100% | 100% | 0% | 1.5714 | 32.75 | 1.05 | 55.02 | 3.96 | 0 | 58.98 | 0 | 58.98 | KMEP |  | 58.98 | 58.98 | 0
E11/K149/SK/dm/213 | HOTEL | 9 | 74622 |  | Plant Room For Kmep Work | Level 5 | Independent | 1 | 4.5 | 1.5 | 2.3 | 1 | m2-LxH | 10.35 | 2022-10-15 |  | 100% | 100% | 0% | 1.5714 | 12.01 | 0.49 | 87.01 | 7.97 | 0 | 94.98 | 0 | 94.98 | KMEP |  | 94.98 | 94.98 | 0
E11/K149/SK/dm/259 | HOTEL | 10 | 74633 |  | Inverted Scaffold | Level 29 | Design 1399 -06 rev-B | 1 | 50 | 1.8 | 4 | 1 | lm | 50 | 2022-10-20 |  | 100% | 100% | 0% | 0.85714 | 1002.22 | 98.11 | 35077.7 | 4204.71 | 0 | 42716.65 | 0 | 42716.65 | Tas Quote - 2439-6-1 |  | 39282.41 | 39282.41 | -3434.24
E11/K149/SK/dm/341 | HOTEL | 11 | 74623 |  | Balcony Floor Drain Work | Level 13 | Independent | 1 | 5.7 | 1.3 | 1.5 | 1 | unit | 1 | 2022-10-20 |  | 100% | 100% | 0% | 0.85714 | 1368.99 | 6.17 | 958.29 | 5.29 | 0 | 963.58 | 0 | 963.58 | Tas Quote - 2439-12-2 (item-2) |  | 963.58 | 963.58 | 0
E11/K149/SK/dm/341 | HOTEL | 12 | 74625 |  | Balcony Floor Drain Work | Level 12 | Independent | 1 | 5.7 | 1.3 | 1.5 | 1 | unit | 1 | 2022-10-20 |  | 100% | 100% | 0% | 0.85714 | 1368.99 | 6.17 | 958.29 | 5.29 | 0 | 963.58 | 0 | 963.58 | Tas Quote - 2439-12-2 (item-2) |  | 963.58 | 963.58 | 0
E11/K149/SK/dm/341 | HOTEL | 13 | 74624 |  | Balcony Floor Drain Work | Level 14 | Independent | 1 | 5.7 | 1.3 | 1.5 | 1 | unit | 1 | 2022-10-21 |  | 100% | 100% | 0% | 0.71429 | 1368.99 | 6.17 | 958.29 | 4.41 | 0 | 962.7 | 0 | 962.7 | Tas Quote - 2439-12-2 (item-2) |  | 962.7 | 962.7 | 0
E11/K149/SK/dm/341 | HOTEL | 14 | 74626 |  | Balcony Floor Drain Work | Level 15 | Independent | 1 | 5.7 | 1.3 | 1.5 | 1 | unit | 1 | 2022-10-21 |  | 100% | 100% | 0% | 0.71429 | 1368.99 | 6.17 | 958.29 | 4.41 | 0 | 962.7 | 0 | 962.7 | Tas Quote - 2439-12-2 (item-2) |  | 962.7 | 962.7 | 0
E11/K149/SK/dm/213 | HOTEL | 10a | 74635 |  | Trench Inside for Parapet Cutting | Level 29 | Additional Boarding | 1 | 50 | 1 | 1 | 1 | m2-LxW | 50 | 2022-10-20 |  | 100% | 100% | 0% | 0.85714 | 6.63 | 0.7 | 232.05 | 30 | 0 | 262.05 | 0 | 262.05 |  |  | 262.05 | 262.05 | 0
E11/K149/SK/dm/259 | HOTEL | 15 | 74634 |  | Inverted Scaffold | Level 29 | Design 1399 -06 rev-B | 1 | 33 | 1.8 | 4 | 1 | lm | 33 | 2022-10-22 |  | 100% | 100% | 0% | 0.57143 | 1002.22 | 98.12 | 23151.28 | 1850.26 | 0 | 25001.54 | 0 | 25001.54 | Tas Quote - 2439-6-1 |  | 25001.54 | 25001.54 | 0
E11/K149/SK/dm/259 | HOTEL | 15 | 74634 |  | Inverted Scaffold | Level 29 | Third Party Inspection ( Additional) | 1 |  |  |  |  | unit | 1 | 2022-10-22 |  | 100% | 100% | 100% | 0.57143 | 1230 | 0 | 1230 | 0 | 0 | 1230 | 0 | 1230 | Additional Inspection |  | 1230 | 1230 | 0
E11/K149/SK/dm/213 | HOTEL | 15a | 74636 |  | Trench Inside for Parapet Cutting | Level 29 | Additional Boarding | 1 | 33 | 1 | 1 | 1 | m2-LxW | 33 | 2022-10-22 |  | 100% | 100% | 0% | 0.57143 | 6.63 | 0.7 | 153.15 | 13.2 | 0 | 166.35 | 0 | 166.35 |  |  | 166.35 | 166.35 | 0
E11/K149/SK/dm/213 | HOTEL | 16 | 74627 |  | EIFS work Damac side Elevation | Level 2 | Independent | 1 | 6.8 | 1.8 | 8 | 1 | m2-LxH | 54.4 | 2022-10-24 |  | 100% | 100% | 0% | 0.28571 | 16.76 | 0.77 | 638.22 | 11.97 | 0 | 650.19 | 0 | 650.19 |  |  | 650.19 | 650.19 | 0
E11/K149/SK/dm/213 | HOTEL | 16a | 74628 |  | EIFS work Damac side Elevation | Level 4 | Cantilever (0.5 > 1.2m width) | 1 | 6.8 | 1 | 1 | 1 | m2-LxW | 6.8 | 2022-10-24 |  | 100% | 100% | 0% | 0.28571 | 36.52 | 2.94 | 173.84 | 5.71 | 0 | 179.55 | 0 | 179.55 |  |  | 179.55 | 179.55 | 0
E11/K149/SK/dm/213 | HOTEL | 16b | 74629 |  | EIFS work Damac side Elevation | Level 2 | Butress | 1 | 2.5 | 1.8 | 5 |  | m3 | 22.5 | 2022-10-24 |  | 100% | 100% | 0% | 0.28571 | 5.29 | 0.05 | 83.32 | 0.32 | 0 | 83.64 | 0 | 83.64 |  |  | 83.64 | 83.64 | 0
E11/K149/SK/dm/213 | HOTEL | 9a | 74630 |  | Plant Room Kmep Work | Level 5 | Additional Boarding | 1 | 4.5 | 1 | 1 | 1 | m2-LxW | 4.5 | 2022-10-24 |  | 100% | 100% | 0% | 0.28571 | 6.63 | 0.7 | 20.88 | 0.9 | 0 | 21.78 | 0 | 21.78 | KMEP |  | 21.78 | 21.78 | 0
E11/K149/SK/dm/213 | HOTEL | 9b | 74632 |  | Plant Room Kmep Work | Level 5 | Additional Boarding | 1 | 2.5 | 0.75 | 1 | 1 | m2-LxW | 1.88 | 2022-10-24 |  | 100% | 100% | 0% | 0.28571 | 6.63 | 0.7 | 8.73 | 0.38 | 0 | 9.11 | 0 | 9.11 | KMEP |  | 9.11 | 9.11 | 0
E11/K149/SK/dm/213 | HOTEL | 17 | 74637 |  | Plant Room Kmep Work | Level 5 | Tower | 1 | 2.5 | 1.3 | 2.5 | 1 | rm | 2.5 | 2022-10-25 |  | 100% | 100% | 0% | 0.14286 | 63.34 | 7.28 | 110.85 | 2.6 | 0 | 113.45 | 0 | 113.45 | KMEP |  | 113.45 | 113.45 | 0
E11/K149/SK/dm/213 | HOTEL | 17a | 74638 |  | Plant Room Kmep Work | Level 5 | Cantilever (0 < 0.5m width) | 1 | 1.5 | 0.5 | 1 | 1 | m2-LxW | 0.75 | 2022-10-25 |  | 100% | 100% | 0% | 0.14286 | 32.75 | 1.05 | 17.19 | 0.11 | 0 | 17.3 | 0 | 17.3 | KMEP |  | 17.3 | 17.3 | 0
Total |  |  | 94 | 21 | [18 empty] | 283371.3 | 58673.57 | 4898.84 | 350383.27 | 125287.35 | 225095.92 |  | 124830.21 | 222113.5 | 346943.71
Note on B4: LGee: Update these informations
Note on P83: Himal Kosala: Check the dates
Note on P84: Himal Kosala: Check the dates
Note on V89: Himal Kosala: Check the rate, TAS include the hire rate as well

## Order References
Rate Card Ref | Order Reference | Scaffolding Type | Fixed Duration | Item | Unit | Rate IN AED
1 | E11/K149/SK/dm/213 | Static tower | 0 | Erect & Dismantle | Rising Meter | 63.34
2 | E11/K149/SK/dm/213 | Static tower | 0 | Hire per Week | Rising Meter | 7.28 | 1.04
3 | E11/K149/SK/dm/213 | Mobile Tower | 0 | Erect & Dismantle | Rising Meter | 103.33
4 | E11/K149/SK/dm/213 | Mobile Tower | 0 | Hire per Week | Rising Meter | 10.29 | 1.47
5 | E11/K149/SK/dm/213 | Heavy duty tower | 0 | Erect & Dismantle | Rising Meter | 148
6 | E11/K149/SK/dm/213 | Heavy duty tower | 0 | Hire per Week | Rising Meter | 12.88 | 1.84
7 | E11/K149/SK/dm/213 | Independent 1.2m wide | 0 | Erect & Dismantle | M2 (LxH) | 12.01
8 | E11/K149/SK/dm/213 | Independent 1.2m wide | 0 | Hire per Week | M2 (LxH) | 0.49 | 0.07
9 | E11/K149/SK/dm/213 | Independent 1.8m wide | 0 | Erect & Dismantle | M2 (LxH) | 16.76
10 | E11/K149/SK/dm/213 | Independent 1.8m wide | 0 | Hire per Week | M2 (LxH) | 0.77 | 0.11
11 | E11/K149/SK/dm/213 | Birdcage | 0 | Erect & Dismantle | M3 | 7.08
12 | E11/K149/SK/dm/213 | Birdcage | 0 | Hire per Week | M3/Day | 0.07 | 0.01
13 | E11/K149/SK/dm/213 | Heavy duty birdcage | 0 | Erect & Dismantle | M3 | 10
14 | E11/K149/SK/dm/213 | Heavy duty birdcage | 0 | Hire per Week | M3/Day | 0.13 | 0.018571
15 | E11/K149/SK/dm/213 | Buttress | 0 | Erect & Dismantle | M3 | 5.29
16 | E11/K149/SK/dm/213 | Buttress | 0 | Hire per Week | M3/Day | 0.05 | 0.0071429
17 | E11/K149/SK/dm/213 | Boarded lift | 0 | Erect & Dismantle | M2 (LxW) | 6.63
18 | E11/K149/SK/dm/213 | Boarded lift | 0 | Hire per Week | M2 (LxW) | 0.7 | 0.1
19 | E11/K149/SK/dm/213 | Cantilever (0 < 0.5m width) | 0 | Erect & Dismantle | M2 (LxW) | 32.75
20 | E11/K149/SK/dm/213 | Cantilever (0 < 0.5m width) | 0 | Hire per Week | M2 (LxW) | 1.05 | 0.15
21 | E11/K149/SK/dm/213 | Cantilever (0.5 > 1.2m width) | 0 | Erect & Dismantle | M2 (LxW) | 36.52
22 | E11/K149/SK/dm/213 | Cantilever (0.5 > 1.2m width) | 0 | Hire per Week | M2 (LxW) | 2.94 | 0.42
23 | E11/K149/SK/dm/213 | Bridge | 0 | Erect & Dismantle | Linear Meter | 37.43
24 | E11/K149/SK/dm/213 | Bridge | 0 | Hire per Week | Linear Meter | 1.4 | 0.2
25 | E11/K149/SK/dm/213 | Counterweight (Scaffold Tubes) | 0 | Erect & Dismantle | Linear Meter | 0.3
26 | E11/K149/SK/dm/213 | Counterweight (Scaffold Tubes) | 0 | Hire per Week | Linear Meter | 0.14 | 0.02
27 | E11/K149/SK/dm/213 | Edge protection - A Frame Single | 0 | Erect & Dismantle | Linear Meter | 7
28 | E11/K149/SK/dm/213 | Edge protection - A Frame Single | 0 | Hire per Week | Linear Meter | 0.42 | 0.06
29 | E11/K149/SK/dm/213 | Edge protection - A Frame double | 0 | Erect & Dismantle | Linear Meter | 12
30 | E11/K149/SK/dm/213 | Edge protection - A Frame double | 0 | Hire per Week | Linear Meter | 0.7 | 0.1
31 | E11/K149/SK/dm/213 | Edge Protection - Double | 0 | Erect & Dismantle | Linear Meter | 15
32 | E11/K149/SK/dm/213 | Edge Protection - Double | 0 | Hire per Week | Linear Meter | 0.91 | 0.13
33 | E11/K149/SK/dm/213 | Edge Protection - Double (Hilti) | 0 | Erect & Dismantle | Linear Meter | 24
34 | E11/K149/SK/dm/213 | Edge Protection - Double (Hilti) | 0 | Hire per Week | Linear Meter | 0.7 | 0.1
35 | E11/K149/SK/dm/213 | Netting supply - Beige Colour | 0 | Supply only | M2 (LxH) | 4.52
36 | E11/K149/SK/dm/213 | Netting install | 0 | Supply only | M2 (LxH) | 4
37 | E11/K149/SK/dm/213 | Staircase Supported by structure | 0 | Erect & Dismantle | Rising Meter | 250
38 | E11/K149/SK/dm/213 | Staircase Supported by structure | 0 | Hire per Week | Rising Meter | 14.35 | 2.05
39 | E11/K149/SK/dm/213 | Staircase supported by Buttress | 0 | Erect & Dismantle | Rising Meter | 376.2
40 | E11/K149/SK/dm/213 | Staircase supported by Buttress | 0 | Hire per Week | Rising Meter | 40.11 | 5.73
41 | E11/K149/SK/dm/213 | Manpower - Scaffolder | 0 | Dayworks | Hour | 20.5
42 | E11/K149/SK/dm/213 | Manpower - Foreman | 0 | Dayworks | Hour | 24
43 | E11/K149/SK/dm/216 | Aluminium Tower | 0 | Erect & Dismantle | Set | 0
44 | E11/K149/SK/dm/216 | Aluminium Tower | 0 | Hire per Week | Set | 28.5714
45 | E11/K149/SK/dm/238 | Design - TAS-1399-10A | 1 | Erect & Dismantle | Lumpsum | 6044.84
46 | E11/K149/SK/dm/238 | Design - TAS-1399-10A | 1 | Hire per Week | Hire per Week | 45.3871
47 | E11/K149/SK/dm/239 | Design - TAS-1399-7 | 1 | Erect & Dismantle | Lumpsum | 16252.45
48 | E11/K149/SK/dm/239 | Design - TAS-1399-7 | 1 | Hire per Week | Hire per Week | 89.4243
49 | E11/K149/SK/dm/256 | Balcony Scaffold - Type1 | 1 | Erect & Dismantle | Lumpsum | 4844.83
50 | E11/K149/SK/dm/256 | Balcony Scaffold - Type1 | 1 | Hire per Week | Hire per Week | 15.99
51 | E11/K149/SK/dm/256 | Balcony Scaffold - Type2 | 1 | Erect & Dismantle | Lumpsum | 4990.83
52 | E11/K149/SK/dm/256 | Balcony Scaffold - Type2 | 1 | Hire per Week | Hire per Week | 17.4214
53 | E11/K149/SK/dm/256 | Balcony Scaffold - Type3 | 1 | Erect & Dismantle | Lumpsum | 5095.97
54 | E11/K149/SK/dm/256 | Balcony Scaffold - Type3 | 1 | Hire per Week | Hire per Week | 18.45
55 | E11/K149/SK/dm/256 | Balcony Scaffold - Type4 | 1 | Erect & Dismantle | Lumpsum | 4127.36
56 | E11/K149/SK/dm/256 | Balcony Scaffold - Type4 | 1 | Hire per Week | Hire per Week | 8.4371
57 | E11/K149/SK/dm/256 | Balcony Scaffold - Type5 | 1 | Erect & Dismantle | Lumpsum | 8714.14
58 | E11/K149/SK/dm/256 | Balcony Scaffold - Type5 | 1 | Hire per Week | Hire per Week | 38.73
59 | E11/K149/SK/dm/256 | Balcony Scaffold - Type6 | 1 | Erect & Dismantle | Lumpsum | 5210.58
60 | E11/K149/SK/dm/256 | Balcony Scaffold - Type6 | 1 | Hire per Week | Hire per Week | 19.3229
61 | E11/K149/SK/dm/256 | Balcony Scaffold - Type7 | 1 | Erect & Dismantle | Lumpsum | 5900.72
62 | E11/K149/SK/dm/256 | Balcony Scaffold - Type7 | 1 | Hire per Week | Hire per Week | 26.07
63 | E11/K149/SK/dm/257 | Design - TAS-1399-02D | 1 | Erect & Dismantle | Lumpsum | 53510.26
64 | E11/K149/SK/dm/257 | Design - TAS-1399-02D | 1 | Hire per Week | Hire per Week | 401
65 | E11/K149/SK/dm/259 | Design - TAS-1399-06B | 1 | Erect & Dismantle | Lumpsum | 158449.11
66 | E11/K149/SK/dm/259 | Design - TAS-1399-06B | 1 | Hire per Week | Hire per Week | 2018.4243
67 | CONTRACT - 201A22002/49
68 | E11/K149/HN/dm/285 | Design-TAS-1399-12 | 1 | Erect & Dismantle | Lumpsum | 5083.25
69 | E11/K149/HN/dm/285 | Design-TAS-1399-12 | 1 | Hire per Week | Hire per Week | 123.48
70 | E11/K149/SK/dm/365 |  | 1 | Erect & Dismantle | Lumpsum | 5979.17
71 | E11/K149/SK/dm/350 | Design-TAS-1399-14 | 1 | Erect & Dismantle | Lumpsum | 14003.16
72 | E11/K149/SK/dm/350 | Design-TAS-1399-14 | 1 | Hire per Week | Hire per Week | 660.1
73 | E11/K149/SK/dm/300 | Design-Tas-1399-13A | 1 | Erect & Dismantle | Lumpsum | 4082.38
74 | E11/K149/SK/dm/300 | Design-Tas-1399-13A | 1 | Hire per Week | Hire per Week | 49.28
75 | E11/K149/SK/dm/341 |  | 1 | Erect & Dismantle | Lumpsum | 5325.76
76 | E11/K149/SK/dm/341 |  | 1 | Hire per Week | Hire per Week | 48.26
77 | E11/K149/SK/dm/341 |  | 1 | Erect & Dismantle | Lumpsum | 1375.16
78 | E11/K149/SK/dm/341 |  | 1 | Hire per Week | Hire per Week | 6.17
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174

## Modification
Khansaheb Civil Engineering LLC
Application No.: | 2
Project Name: | Dorchester Hotel & Residences (Completion Works)
Order Reference: | 201A22002/49
As On Date: | 2022-10-25
Dayworks
DTS | Date | Hrs | Total | Net
62652 | 2022-09-18 | 26 | 533 | 533
62653 | 2022-09-30 | 6 | 123 | 123
62654 | 2022-10-10 | 30 | 615 | 615
0
|  |  | 0 | 0
Total |  | 62 | 1271 | 1271
Note on B2: LGee: Update these informations

## Manpower (hidden)
Client: | Khansaheb Civil Engineering LLC
Application No.: | 2
Project Name: | Dorchester Hotel & Residences (Completion Works)
Site: | #REF!
As Of: | 2022-10-25
Modification Hours
DTS | Date | Scaffolder | Foreman | Cumulative | Previous | Net
Total |  |  |  | 0 | 0 | 0

## SCOPE (hidden)
SCOPE OF WORKS & ADDITIONAL WORKS RATES
Reference | Description | Number | L | W | H | BL | Item Price | Period (Wks) | Extra Hire per Week

## PASummary (hidden)
Client: | Khansaheb Civil Engineering LLC
Project Name: | Dorchester Hotel & Residences (Completion Works)
Contract Ref: | 201A22002/49
PAYMENT APPLICATION SUMMARY
Application No. | Application Date | Works Carried Out | Day Works | Total | Remarks
Total |  | 0 | 0 | 0 | 0