## Domestic
No | Subcontractor | Contract Type | Original Scope | Contract Amount | Certified Amount (until IPC 13) | % | Variation Amount | Variation Certified Amount (until IPC 13) | % | Remark
Subcontractors (Domestic)
1 | Blue Sky LLC | Remeasurement | Supply of MEP Maintenance team | 396000 | 433200 | 109.4% |  | 426097.55
2 | Data Link Technical Services LLC | Remeasurement | Wild Air Partitions | 54387.15 | 64747.5515 | 119% | 465061.02 | 449858.94 | 96.73%
3 | Al Rawda General Maint. & Decoration Co LLC | Lump Sum | Ceiling & Partition repairs, painting works | 26960 | 34460 | 127.8%
4 | Firestop Middle East | Remeasurement | Firestopping works | 441760 | 276436.3618 | 62.58% | 0 | 0 | N/A
5 | Creative House Scaffolding | Remeasurement | Scaffolding | 157030 | 2984260.5606 | 1900% | 0 | 0 | N/A
6 | Corecut Engineering LLC | Remeasurement | Coring & Scanning | 35410 | 226368 | 639.3% | 321648.45 | 321648.45 | 100%
7 | Inventure Façade Contracting LLC | Remeasurement | Glass Balustrade works | 1331893 | 1981268.165 | 148.8% | 474780 | 358675 | 75.55%
8 | TWIC Insulation Materials Supply LLC | Remeasurement | Epoxy Coating & Dust Sealer works | 570509.8 | 45653.7723 | 8.002% | 1501824.83 | 493595.65 | 32.87%
9 | Al Maraya Marble & Granite Factory LLC | Remeasurement | Tile Installation | 514481.6 | 250361.08 | 48.66%
10 | German Concrete Works & Building Contracting LLC | Remeasurement | Screed & Insulation works | 645526.09 | 536170.61 | 83.06% | 406546.06 | 213632.1605 | 52.55%
11 | Greenwood General Trading LLC | Remeasurement | Wooden Flooring | 353975.01 | 0 | 0% | 110300 | 55150 | 50% | Advance for variation
12 | Al Hayat Fiberglass Ind LLC | Lump Sum | GRP Lining works | 313333.4 | 131172 | 41.86% | 0 | 0 | N/A
13 | Vulcan Industries LLC | Remeasurement | Steel Doors | 685405 | 133526.7524 | 19.48%
14 | Polaris International Industries LLC | Lump Sum | Timber Doors | 961039 | 731553 | 76.12% | 112024.4599 | 89070.209 | 79.51%
15 | Center Core Professional Technical Services LLC | Lump Sum | Slab cutting & strengthening works | 88900 | 88900 | 100%
16 | Weserve Technical Services LLC | Lump Sum | Miscellaneous Steel works | 47794.8 | 44063 | 92.19% | 850424.5875 | 850424.5875 | 100%
17 | Venus Engineering LLC | Lump Sum | RC column removal & strengthening works | 110965 | 105416.75 | 95% | 133500 | 120150 | 90%
18 | Global Composites Solutions LLC | Lump Sum | GRP Cladding to Planter Wall | 225683 | 0 | 0% | 0 | 0
19 | Indiga Tech Trading LLC | Remeasurement | Steel Doors | 154496.05 | 36427.5772 | 23.58% | 292667.34 | 94641.85 | 32.34%
20 | Monrac LLC | Lump Sum | Ceiling & Partition repairs, painting works | 918183.61 | 880523.36 | 95.9% | 144411.85 | 77807.945 | 53.88%
21 | Hygenic Solutions LLC | Remeasurement | MMA Flooring | 474794 | 139855 | 29.46% | 0 | 0 | N/A
22 | Technical Access Services (L.L.C.) | Remeasurement | Scaffolding Works | 265036 | 566238.02 | 213.6% | 1128480.6 | 1072056.57 | 95%
23 | Progress Fabrication | Remeasurement & Lump Sum | Metal Cladding Works and Misc Metal Works | 1264100.14 | 552871.22 | 43.74% | 633672.14 | 281196 | 44.38%
24 | Ferco Shutters LLC | Lump Sum | Fire Curtains | 33685 | 23579.5 | 70% | 0 | 0 | N/A
25 | Jeel Alfan Technical Services | Remeasurement | Decorative Paint | 128266 | 0 | 0% | 0 | 0 | N/A
26 | Technoserve Technical works LLC | Remeasurement | Painting works | 73379.6 | 31514.6587 | 42.95% | 0 | 0 | N/A
27 | Dormakaba Middle East | Lump Sum | Movable Partition Works- AHK Balance | 366250 | 293000 | 80% | 0 | 0 | N/A
28 | Khansaheb Joinery DIvision ( KJD ) | Lump Sum | Joinery Works- AHK Balance | 2105729.87 | 810993.5956 | 38.51% | 3593643.8655 | 527631.6326 | 14.68%
29 | Al Burhani General Trading LLC | Lump Sum | Wooden Flooring & Carpet works- AHK | 133457 | 119416.96 | 89.48% | 5978 | 5978 | 100%
30 | Rattan House Factory for Furniture and Decoration | Lump Sum | Res Lobbies, Joinery works- AHK Balance | 279759 | 181862.152 | 65.01% | 0 | 0 | N/A
31 | International Foundation Group LLC | Lump Sum | Waterproofing Concrete works | 450000 | 450000 | 100%
32 | X-Calibur Emirates LLC | Remeasurement | Stair nosing works | 221889 | 173913 | 78.38%
33 | Master Rubber Manufacturing | Remeasurement | Wall & Corner Guard works | 169068.5 | 0 | 0%
34 | DNK Engineering Equipment Trading LLC | Lump Sum | Rolling Shutter works | 75530 | 69930 | 92.59% | 14000 | 7000 | 50%
35 | Vijayraj Contracting Co LLC | Remeasurement | Plastering works | 206250 | 231320.1 | 112.2% | 0 | 0 | N/A
36 | Doormax Building Material Trading LLC | Remeasurement | Glass Door works | 128000 | 89600 | 70% | 12000 | 12000 | 100%
37 | KTC International Cont LLC | Remeasurement | RTA works | 1043942 | 82181.9321 | 7.872% | 0 | 0 | N/A
38 | Urban Science Building Contracting LLC | Lump Sum | Joinery- Cupboards | 533125 | 0 | 0%
39 | Berkeley | Lump Sum | Final Cleaning | 993456 | 29470 | 2.966% | 13400 | 13400 | 100%
40 | Elite Skills Technical Services LLC | Remeasurement | Steel Door Repainting Works | 75430 | 50274 | 66.65% | 1842000 | 72044.8 | 3.911%
41 | Smart Roof Shade Systems LLC |  | Retractable Pergola System | 400000 | 0 | 0%
42 | Terra Firma Trading LLC |  | Plant Room Acoustics | 51170 | 0 | 0%
43 | Total Solution Engineering LLC |  | Stainless Steel Column skirting works | 133050 | 0 | 0%

## PS
No | Subcontractor | Contract Type | Original Scope | Contract Amount | Certified Amount (until IPC 13) | % | Variation Amount | Variation Certified Amount (until IPC 13) | % | Remark
Subcontractors ( PS )
1 | Watermaster Technical Services LLC | Lump Sum | Swimming Pool & Water Feature works | 2128651 | 1787139.6997 | 83.96% | 0 | 0 | 0%
2 | Arcadia Metal Industries | Lump Sum | External Metal works | 3330440 | 1731750.577 | 52% | 6426901.48 | 3505723.4642 | 54.55%
3 | Dar Al Rokham LLC | Lump Sum | Internal Stone works | 4111821 | 3396621.79 | 82.61% | 1459469.33 | 492133.0284 | 33.72%
4 | Al Shirawi Contracting Co LLC | Lump Sum | Waterproofing works | 1391469 | 838018.15 | 60.23% | 74470.87 | 67938.93 | 91.23%
5 | Alshafar Interiors Co LLC | Lump Sum | Joinery to Guest Rooms | 5230409 | 4047346.7916 | 77.38% | 68273.97 | -44172.6711 | -64.7%
6 | Isam Kabbani & Partners | Lump Sum | Guniting & Waterproofing works | 1155933 | 435538.7332 | 37.68% | 0 | 0 | 0%
7 | Fiona Environs UAE | Lump Sum | Soft Landscaping & Irrigation works | 3313028.6 | 2056328.42 | 62.07% | 921945.15 | 460972.575 | 50%
8 | Al Reem Marble & Granite LLC | Lump Sum | External Stoneworks | 4556481 | 2944569.2514 | 64.62% | 4541160.29 | 1363601.2759 | 30.03%
9 | Joyz Overseas Technical Services LLC | Lump Sum | EIFS works | 1538156.94 | 816284.7023 | 53.07% | 1296819.145 | 645821.3073 | 49.8%
10 | Bond Interiors Design LLC | Lump Sum | Fitout of Hotel Lobby, All Day Dining & Spa Works | 4325954.46 | 3208319.8527 | 74.16% | 0 | 0 | 0%
11 | Al Rawda General Maint. & Decoration Co LLC | Lump Sum | Partition & Ceiling works | 1954843 | 1180937.0012 | 60.41% | 4114126.531 | 2503305.28 | 60.85%
12 | Joseph Advertisers LLC | Lump Sum | Signage works | 999150 | 0 | 0% | 0 | 0 | 0%
13 | Joseph Decorative Glass | Lump Sum | Internal Glazing works | 1262387 | 513495.293 | 40.68% | 0 | 0 | 0%
14 | Walltracts | Lump Sum | Wall Coverings | 712173.7 | 406956.4 | 57.14% |  |  | 0% | M@S
15 | Goodrich Global Trading LLC | Lump Sum | Carpets to Guest Rooms | 839675.05 | 555878.32 | 66.2% |  |  | 0%
16 | Arabian Profile Company Ltd | Lump Sum | GRC Works | 4155655 | 1736791 | 41.79% | 661491 | 160731.7 | 24.3%
17 | Glass Line Aluminium LLC | Lump Sum | Aluminium & Glazing Façade works | 10273402 | 5657949.24 | 55.07% | 745458.8 | 390905.2406 | 52.44%
18 | EW COX Middle East LLC | Lump Sum | BMU System | 628861 | 204605.8 | 32.54% |  |  | 0%
19 | Mohammed Tayyeb Khoory & Sons | Lump Sum | Garbage & Linen Chutes | 287122 | 140609.4 | 48.97% |  |  | 0%
20 | HTS Carpets Trading LLC | Lump Sum | Carpets to lift lobbies & Corridors | 356512.42 | 261442.44 | 73.33% |  |  | 0%
21 | Khansaheb Interior DIvision ( KID ) |  | Restaurant Works