## IPA -07 (hidden)
INTERIM PAYMENT APPLICATION NO. 07
Project Title | Dorchester Hotel & Residences Project, Dubai, UAE.
Employer | M/S Khansaheb Civil Engineering L.L.C.
Contractor | Polaris International Industries LLC
P.O No. | 201A22002/SW/ARM/175 |  | Date of Application | 2023-02-28
Dated | 2022-06-13 |  | Payment Application no. | 7
Quote Ref | Nil |  | Date of Application | 2023-08-27
Contract Price: | 961039
Variation | 112024.4599
Anticipated Cont Price | 1073063.4599
WORK DONE | Value of Work Done- (Refer Appendix A) |  | Contract | Amount of Work Done
| a. Contract Works |  | 961039 | 792547
| b. Variation |  | 112024.4599 | 89070.209
| Subtotal (Value of Workdone) |  | 1073063.4599 | 881617.209
ADVANCE PAYMENT | Addition
| Advance Payment on Contract Works |  | 10% | 96103.9
Deductions
| Advance Recovery on Contract Works |  | Fully recovered | -96103.9
| Advance Payable | B |  | 0
DEDUCTIONS | Omission
| Retention on Work Done at 10% |  |  | -88161.7209
AMOUNT PAYABLE | Gross amount Payable A+B |  |  | 793455.4881
PREVIOUS CERTIFIED
| Previous Amount Certified |  |  | -603863.38
NET AMOUNT | Net Payment Payable | (VAT Excluded) |  | 189592.1081
Amount in Words: | Arab Emirates Dirhams One Hundred Ninty Two Thousand Thirty Nine and Fils 12 only
Project Manager |  |  |  | Commercial Manager

## Summary
No | Description | Previous | This Month | Cumulative
| Contract Works | 687966 | 43587 | 731553
| Variations | 54355.329 | 34714.88 | 89070.209
|  | 742321.329 | 78301.88 | 820623.209
| Advance Recovery (12%) | -89078.5595 | -7025.3405 | -96103.9 | 96103.9
|  | 653242.7695 | 71276.5395 | 724519.309
| KCE Claim | 797551.2928 | 86784.8172 | 884336.11
| Difference | -144308.5233 | -15508.2777 | -159816.801

## BOQ - Doors
DORCHESTER HOTEL | [21 empty] | INTERIM PAYMENT APPLICATION | 7 | [5 empty] | 12
PACKAGE : SUPPLY & INSTALLATION OF FOH-BOH TIMBER DOORS (EXCL. IRONMONGERY SUPPLY) Balance Works | [21 empty] | PERIOD ENDING | 2023-02-28 | [5 empty] | 20
BILL OF QUANTITIES
Item | Description | Qty. | Unit | Original BOQ Rate | % Certified | Amount Certified | Balance Amount with Original rate |  | Balance % to certified | Revised Rate | Balance amount as per revised rate | Frames |  | Doors |  | Completion |  | Percentage |  |  | Amount |  |  | Certified |  | MIR Ref. | WIR Ref. | Remarks
|  |  |  | AED |  | AED | AED |  |  | AED | AED | Delivery (70%) | Installation(30%) | Delivery (70%) | Installation(30%) | Balance Works completion | Approvals | Previous Percentage | Currnet Percentage | Cumulative Percentage | Previous Amount | Current Amount | Cumulative Amount | This Month | Cumulative
[12 empty] | 30% |  | 50% |  | 20%
[12 empty] | 21% | 9% | 35% | 15% | 14% | 6%
TIMBER DOORS
Supply and installation of FOH-BOH Timber Doors (excluding ironmongery supply)
1 | Door mark L0101 to CORRIDOR | 1 | Nos. | 2933.0215 | 0% | 0 | 2933.0215 | 100% | 100% | 3666.2769 | 3666.2769 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | [5 empty] | No Dwg
2 | Door mark L0103 to CORRIDOR | 1 | Nos. | 2038.381 | 0% | 0 | 2038.381 | 100% | 100% | 2547.9763 | 2547.9763 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | [5 empty] | No Dwg
3 | Door mark L0104 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2446.4812 | 0% | 0 | 2446.4812 | 100% | 100% | 3058.1016 | 3058.1016 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | [5 empty] | No Dwg
4 | Door mark L0106 to STAIR 08 | 1 | Nos. | 2933.0215 | 0% | 0 | 2933.0215 | 100% | 100% | 3666.2769 | 3666.2769 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | [5 empty] | No Dwg
5 | Door mark L0107 to CIRCULATION | 1 | Nos. | 2038.381 | 0% | 0 | 2038.381 | 100% | 100% | 2547.9763 | 2547.9763 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 |  | 0 |  |  |  | No Dwg
6 | Door mark L0111 to PLANT | 1 | Nos. | 3023.1215 | 0% | 0 | 3023.1215 | 100% | 100% | 3778.9019 | 3778.9019 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 |  | 0 |  |  |  | No Dwg
7 | Door mark L0112 to PLANT | 1 | Nos. | 3023.1215 | 0% | 0 | 3023.1215 | 100% | 100% | 3778.9019 | 3778.9019 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 |  | 0 |  |  |  | No Dwg
8 | Door mark L0116 to CIRCULATION | 1 | Nos. | 2052.161 | 0% | 0 | 2052.161 | 100% | 100% | 2565.2013 | 2565.2013 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 |  | 0 |  |  |  | No Dwg
9 | Door mark L0121 to AV CONTROL ROOM | 1 | Nos. | 1667.3808 | 0% | 0 | 1667.3808 | 100% | 100% | 2084.2261 | 2084.2261 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 |  | 0 |  |  |  | No Dwg
10 | Door mark L0123 to LIFT LOBBY | 1 | Nos. | 1667.3808 | 0% | 0 | 1667.3808 | 100% | 100% | 2084.2261 | 2084.2261 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 |  | 0 |  |  |  | No Dwg
11 | Door mark L02107 to CORRIDOR | 1 | Nos. | 2903.3415 |  | 0 | Rate Only | 100% |  | 3629.1768 | Rate Only
12 | Door mark L02108 to SECRET BAR PANTRY | 1 | Nos. | 3345.3617 |  | 0 | Rate Only | 100% |  | 4181.7021 | Rate Only
13 | Door mark L02122 to LOBBY LOUNGE SUPPORT | 1 | Nos. | 2708.3014 |  | 0 | Rate Only | 100% |  | 3385.3767 | Rate Only
14 | Door mark L0263 to HOTEL LOBBY | 1 | Nos. | 2903.3415 |  | 0 | Rate Only | 100% |  | 3629.1768 | Rate Only
15 | Door mark L0401 to STAIR-03 | 1 | Nos. | 3223.4616 | 0% | 0 | 3223.4616 | 100% | 100% | 4029.327 | 4029.327 | 21% | 0% | 35% | 0% | 0% | 0% | 56% | 0% | 56% | 2256.4231 | 0 | 2256.4231 | 0 | 2256.4231 | PII-AX-MR-ML-00025
16 | Door mark L0403 to FF LOBBY | 1 | Nos. | 3242.5416 | 0% | 0 | 3242.5416 | 100% | 100% | 4053.1771 | 4053.1771 | 21% | 0% | 35% | 0% | 0% | 0% | 56% | 0% | 56% | 2269.7792 | 0 | 2269.7792 | 0 | 2269.7792 | PII-AX-MR-ML-00025
17 | Door mark L0404 to WM ROOM | 1 | Nos. | 2044.741 | 0% | 0 | 2044.741 | 100% | 100% | 2555.9263 | 2555.9263 | 21% | 0% | 35% | 0% | 0% | 0% | 56% | 0% | 56% | 1431.3187 | 0 | 1431.3187 | 0 | 1431.3187 | PII-AX-MR-ML-00024 |  |  | MIR not approved
18 | Door mark L0405 to HOUSE KEEPING LOBBY | 1 | Nos. | 2215.4011 | 0% | 0 | 2215.4011 | 100% | 100% | 2769.2514 | 2769.2514 | 21% | 0% | 35% | 0% | 0% | 0% | 56% | 0% | 56% | 1550.7808 | 0 | 1550.7808 | 0 | 1550.7808 | PII-AX-MR-ML-00025
19 | Door mark L0408 to | 1 | Nos. | 0 |  | 0 | Excluded | 100% | 100% | Excluded | Excluded | [12 empty] | 0 | 0
20 | Door mark L0409 to STAIR-04 | 1 | Nos. | 3223.4616 | 0% | 0 | 3223.4616 | 100% | 100% | 4029.327 | 4029.327 | 21% | 0% | 35% | 0% | 0% | 0% | 56% | 0% | 56% | 2256.4231 | 0 | 2256.4231 | 0 | 2256.4231 | PII-AX-MR-ML-00025
21 | Door mark L0410 to STAIR 07 | 1 | Nos. | 2905.4615 |  | 0 | Rate Only | 100% | 100% | 3631.8268 | Rate Only | [13 empty] | 0
22 | Door mark L0415 to STAIR-08 | 1 | Nos. | 2905.4615 |  | 0 | Rate Only | 100% | 100% | 3631.8268 | Rate Only | [13 empty] | 0
23 | Door mark L0416 to HOUSEKEEPING LOBBY | 1 | Nos. | 1916.481 |  | 0 | Rate Only | 100% | 100% | 2395.6012 | Rate Only | [13 empty] | 0
24 | Door mark L0420 to FF LOBBY | 1 | Nos. | 1916.481 |  | 0 | Rate Only | 100% | 100% | 2395.6012 | Rate Only | [13 empty] | 0
25 | Door mark L0421 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 1916.481 |  | 0 | Rate Only | 100% | 100% | 2395.6012 | Rate Only | [13 empty] | 0
26 | Door mark L0455 to RESTAURANT BOH & ROOM SERVICE | 1 | Nos. | 2407.2612 |  | 0 | Rate Only | 100% | 100% | 3009.0765 | Rate Only | [13 empty] | 0
27 | Door mark L0474 to | 1 | Nos. | 0 |  | 0 | Excluded | 100% | 100% | 0 | Excluded | [13 empty] | 0
28 | Door mark L06R01 to STAIR-03 | 1 | Nos. | 3226.6416 | 50% | 1613.3208 | 1613.3208 | 100% | 50% | 3226.6416 | 1613.3208 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 1266.4568 | 185.5319 | 1451.9887 | 185.5319 | 1451.9887 |  | PII-AX-WR-L06-00025
29 | Door mark L06R03 to FF LOBBY | 1 | Nos. | 3252.0816 | 50% | 1626.0408 | 1626.0408 | 100% | 50% | 3252.0816 | 1626.0408 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 1300.8327 | 162.6041 | 1463.4367 | 162.6041 | 1463.4367 | PII-AX-MR-ML-00013 | PII-AX-WR-L06-00025
30 | Door mark L06R05 to WM ROOM | 1 | Nos. | 2422.1012 | 0% | 0 | 2422.1012 | 100% | 100% | 3027.6265 | 3027.6265 | 21% | 9% | 35% | 15% | 0% | 0% | 65% | 15% | 80% | 1967.9572 | 454.144 | 2422.1012 | 454.144 | 2422.1012 | At Factory
31 | Door mark L06R08 to ELEC RM | 1 | Nos. | 2673.3214 | 0% | 0 | 2673.3214 | 100% | 100% | 3341.6517 | 3341.6517 | 21% | 9% | 35% | 15% | 0% | 0% | 65% | 15% | 80% | 2172.0736 | 501.2478 | 2673.3214 | 501.2478 | 2673.3214 |  |  |  | MIR no. by CJ
32 | Door mark L06R09 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.6416 | 50% | 1613.3208 | 1613.3208 | 100% | 50% | 3226.6416 | 1613.3208 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 1290.6567 | 161.3321 | 1451.9887 | 161.3321 | 1451.9887 | PII-AX-MR-ML-00014 | PII-AX-WR-L06-00025 | Frame was delivered during previous contract
33 | Door mark L06R12 to STAIR-04 | 1 | Nos. | 3226.6416 | 50% | 1613.3208 | 1613.3208 | 100% | 50% | 3226.6416 | 1613.3208 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 1266.4568 | 185.5319 | 1451.9887 | 185.5319 | 1451.9887 |  | PII-AX-WR-L06-00025 |  | WIR on Hold
34 | Door mark L06R14 to TELECOM | 1 | Nos. | Deleted as per Email dated 29 June 2022 | [19 empty] | 0 | 0
35 | Door mark L07H01 to STAIR-07 | 1 | Nos. | 3090.9616 | 50% | 1545.4808 | 1545.4808 | 100% | 50% | 3090.9616 | 1545.4808 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 1236.3846 | 309.0962 | 1545.4808 | 309.0962 | 1545.4808 |  | PII-AX-WR-L07-00080
36 | Door mark L07H03 to FF LOBBY | 1 | Nos. | 2422.1012 | 50% | 1211.0506 | 1211.0506 | 100% | 50% | 2422.1012 | 1211.0506 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 968.8405 | 242.2101 | 1211.0506 | 242.2101 | 1211.0506 |  | PII-AX-WR-L07-00080 |  | WIR by CJ
37 | Door mark L07H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1012 | 50% | 1211.0506 | 1211.0506 | 100% | 50% | 2422.1012 | 1211.0506 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 968.8405 | 242.2101 | 1211.0506 | 242.2101 | 1211.0506 |  | PII-AX-WR-L07-00080
38 | Door mark L07H06 to STAIR-08 | 1 | Nos. | 3090.9616 | 50% | 1545.4808 | 1545.4808 | 100% | 50% | 3090.9616 | 1545.4808 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 1236.3846 | 309.0962 | 1545.4808 | 309.0962 | 1545.4808 |  | PII-AX-WR-L07-00080
39 | Door mark L07H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1012 | 50% | 1211.0506 | 1211.0506 | 100% | 50% | 2422.1012 | 1211.0506 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 968.8405 | 242.2101 | 1211.0506 | 242.2101 | 1211.0506 |  | PII-AX-WR-L07-00080
40 | Door mark L07R01 to STAIR-03 | 1 | Nos. | 3226.6416 | 60% | 1935.985 | 1290.6567 | 100% | 40% | 3226.6416 | 1290.6567 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 1032.5253 | 129.0657 | 1161.591 | 129.0657 | 1161.591 |  | PII-AX-WR-L07-00080 | Frame was delivered during previous contract
41 | Door mark L07R03 to FF LOBBY | 1 | Nos. | 3252.0816 | 50% | 1626.0408 | 1626.0408 | 100% | 50% | 3252.0816 | 1626.0408 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 1300.8327 | 162.6041 | 1463.4367 | 162.6041 | 1463.4367 | PII-AX-MR-ML-00013 | PII-AX-WR-L07-00026-03
42 | Door mark L07R05 to WM ROOM | 1 | Nos. | 2422.1012 | 0% | 0 | 2422.1012 | 100% | 100% | 3027.6265 | 3027.6265 | 21% | 9% | 35% | 15% | 0% | 0% | 65% | 15% | 80% | 1967.9572 | 454.144 | 2422.1012 | 454.144 | 2422.1012 | PII-AX-MR-ML-00025
43 | Door mark L07R08 to ELEC RM | 1 | Nos. | 2673.3214 | 0% | 0 | 2673.3214 | 100% | 100% | 3341.6517 | 3341.6517 | 21% | 9% | 35% | 15% | 0% | 0% | 65% | 15% | 80% | 2172.0736 | 501.2478 | 2673.3214 | 501.2478 | 2673.3214
44 | Door mark L07R09 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.6416 | 50% | 1613.3208 | 1613.3208 | 100% | 50% | 3226.6416 | 1613.3208 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 1290.6567 | 161.3321 | 1451.9887 | 161.3321 | 1451.9887 | PII-AX-MR-ML-00014 | PII-AX-WR-L07-00026 | Frame was delivered during previous contract
45 | Door mark L07R12 to STAIR-04 | 1 | Nos. | 3226.6416 | 50% | 1613.3208 | 1613.3208 | 100% | 50% | 3226.6416 | 1613.3208 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 1290.6567 | 161.3321 | 1451.9887 | 161.3321 | 1451.9887 |  | PII-AX-WR-L07-00026
| To Collection Dhs. |  |  |  |  | 19978.7841 | 67296.3601 | 100% |  | 0 | 79287.0862 | [9 empty] | 33463.1517 | 4564.94 | 38028.0917 | 4564.94 | 38028.0917
| TIMBER DOORS (CONT'D) | [6 empty] | 100%
100%
| Supply and installation of FOH-BOH Timber Doors (excluding ironmongery supply) | [6 empty] | 100%
100%
46 | Door mark L07R14 to TELECOM | 1 | Nos. | Deleted as per Email dated 29 June 2022
47 | Door mark L08H01 to STAIR-07 | 1 | Nos. | 3090.96 | 66% | 2040.0336 | 1050.9264 | 100% | 34% | 3090.96 | 1050.9264 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 824.9772 | 120.8565 | 945.8338 | 120.8565 | 945.8338 |  | PII-AX-WR-L08-00054 PII-AX-WR-L08-00101 | Frame was delivered during previous contract
48 | Door mark L08H03 to FF LOBBY | 1 | Nos. | 2422.1 | 50% | 1211.05 | 1211.05 | 100% | 50% | 2422.1 | 1211.05 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 950.6742 | 139.2708 | 1089.945 | 139.2708 | 1089.945 |  | PII-AX-WR-L08-00054 PII-AX-WR-L08-00101
49 | Door mark L08H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 66% | 1598.586 | 823.514 | 100% | 34% | 2422.1 | 823.514 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 646.4585 | 94.7041 | 741.1626 | 94.7041 | 741.1626 |  | PII-AX-WR-L08-00054 PII-AX-WR-L08-00101 | Frame was delivered during previous contract
50 | Door mark L08H06 to STAIR-08 | 1 | Nos. | 3090.96 | 50% | 1545.48 | 1545.48 | 100% | 50% | 3090.96 | 1545.48 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 1213.2018 | 177.7302 | 1390.932 | 177.7302 | 1390.932 | PII-AX-MR-ML-00014 | PII-AX-WR-L08-00054 PII-AX-WR-L08-00101
51 | Door mark L08H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 66% | 1598.586 | 823.514 | 100% | 34% | 2422.1 | 823.514 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 646.4585 | 94.7041 | 741.1626 | 94.7041 | 741.1626 |  | PII-AX-WR-L08-00054 PII-AX-WR-L08-00101
52 | Door mark L08R01 to STAIR-03 | 1 | Nos. | 3226.64 | 50% | 1613.32 | 1613.32 | 100% | 50% | 3226.64 | 1613.32 | 21% | 9% | 35% | 15% |  | 0% | 65% | 15% | 80% | 1048.658 | 241.998 | 1290.656 | 241.998 | 1290.656
53 | Door mark L08R03 to FF LOBBY | 1 | Nos. | 3252.08 | 50% | 1626.04 | 1626.04 | 100% | 50% | 3252.08 | 1626.04 | 21% | 9% | 35% | 15% |  | 0% | 65% | 15% | 80% | 1056.926 | 243.906 | 1300.832 | 243.906 | 1300.832 | PII-AX-MR-ML-00013
54 | Door mark L08R04 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% |  | 0% | 65% | 15% | 80% | 4357.925 | 1005.675 | 5363.6 | 1005.675 | 5363.6
55 | Door mark L08R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% |  | 0% | 65% | 15% | 80% | 1967.9562 | 454.1438 | 2422.1 | 454.1438 | 2422.1
56 | Door mark L08R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 9% | 35% | 15% |  | 0% | 65% | 15% | 80% | 2172.0725 | 501.2475 | 2673.32 | 501.2475 | 2673.32
57 | Door mark L08R09 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 50% | 1613.32 | 1613.32 | 100% | 50% | 3226.64 | 1613.32 | 21% |  | 35% |  |  | 0% | 56% | 0% | 56% | 903.4592 | 0 | 903.4592 | 0 | 903.4592 | PII-AX-MR-ML-00014
58 | Door mark L08R12 to STAIR-04 | 1 | Nos. | 3226.64 | 50% | 1613.32 | 1613.32 | 100% | 50% | 3226.64 | 1613.32 | 21% |  | 35% |  |  | 0% | 56% | 0% | 56% | 903.4592 | 0 | 903.4592 | 0 | 903.4592
59 | Door mark L08R14 to TELECOM | 1 | Nos. | Deleted as per Email dated 29 June 2022 | [16 empty] | 0 |  |  | 0 | 0
60 | Door mark L09H01 to STAIR-07 | 1 | Nos. | 3090.96 | 50% | 1545.48 | 1545.48 | 100% | 50% | 3090.96 | 1545.48 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 1213.2018 | 177.7302 | 1390.932 | 177.7302 | 1390.932 | PII-AX-MR-ML-00014 | PII-AX-WR-L09-00055 PII-AX-WR-L09-00081 | Frame was delivered during previous contract
61 | Door mark L09H03 to FF LOBBY | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 14% | 6% | 78.5% | 21.5% | 100% | 2376.6856 | 650.9394 | 3027.625 | 650.9394 | 3027.625 |  | PII-AX-WR-L09-00055 PII-AX-WR-L09-00081
62 | Door mark L09H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 50% | 1211.05 | 1211.05 | 100% | 50% | 2422.1 | 1211.05 | 21% | 9% | 35% | 15% | 14% | 6% | 78.5% | 21.5% | 100% | 950.6742 | 260.3758 | 1211.05 | 260.3758 | 1211.05 |  | PII-AX-WR-L09-00055 PII-AX-WR-L09-00081 | Frame was delivered during previous contract
63 | Door mark L09H06 to STAIR-08 | 1 | Nos. | 3090.96 | 50% | 1545.48 | 1545.48 | 100% | 50% | 3090.96 | 1545.48 | 21% | 9% | 35% | 15% | 14% | 6% | 78.5% | 21.5% | 100% | 1213.2018 | 332.2782 | 1545.48 | 332.2782 | 1545.48 | PII-AX-MR-ML-00014 | PII-AX-WR-L09-00055 PII-AX-WR-L09-00081
64 | Door mark L09H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 50% | 1211.05 | 1211.05 | 100% | 50% | 2422.1 | 1211.05 | 21% | 9% | 35% | 15% | 14% | 6% | 78.5% | 21.5% | 100% | 950.6742 | 260.3758 | 1211.05 | 260.3758 | 1211.05 |  | PII-AX-WR-L09-00055 PII-AX-WR-L09-00081
65 | Door mark L09R01 to STAIR-03 | 1 | Nos. | 3226.64 | 50% | 1613.32 | 1613.32 | 100% | 50% | 3226.64 | 1613.32 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 1290.656 | 161.332 | 1451.988 | 161.332 | 1451.988 |  | PII-AX-WR-L09-00027
66 | Door mark L09R03 to FF LOBBY | 1 | Nos. | 3252.08 | 50% | 1626.04 | 1626.04 | 100% | 50% | 3252.08 | 1626.04 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 9% | 90% | 1300.832 | 162.604 | 1463.436 | 162.604 | 1463.436 | PII-AX-MR-ML-00013 PII-AX-MR-ML-00015 | PII-AX-WR-L09-00027
67 | Door mark L09R04 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 0% | 0% | 65% | 15% | 80% | 4357.925 | 1005.675 | 5363.6 | 1005.675 | 5363.6
68 | Door mark L09R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 0% | 0% | 0% | 80% | 80% | 0 | 2422.1 | 2422.1 | 2422.1 | 2422.1 |  |  |  | MIR by CJ
69 | Door mark L09R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 9% | 35% | 15% | 0% | 0% | 56% | 24% | 80% | 1871.324 | 801.996 | 2673.32 | 801.996 | 2673.32 | Door and frame delivered
70 | Door mark L09R09 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 66% | 2129.5824 | 1097.0576 | 100% | 34% | 3226.64 | 1097.0576 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 877.6461 | 109.7058 | 987.3518 | 109.7058 | 987.3518 | PII-AX-MR-ML-00014 | PII-AX-WR-L09-00027 | Frame was delivered during previous contract
71 | Door mark L09R12 to STAIR-04 | 1 | Nos. | 3226.64 | 50% | 1613.32 | 1613.32 | 100% | 50% | 3226.64 | 1613.32 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 1290.656 | 161.332 | 1451.988 | 161.332 | 1451.988 |  | PII-AX-WR-L09-00027
72 | Door mark L09R14 to TELECOM | 1 | Nos. | Deleted as per Email dated 29 June 2022 | [19 empty] | 0 | 0
73 | Door mark L10H01 to STAIR-07 | 1 | Nos. | 3090.96 | 60% | 1854.576 | 1236.384 | 100% | 40% | 3090.96 | 1236.384 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 970.5614 | 142.1842 | 1112.7456 | 142.1842 | 1112.7456 |  | PII-AX-WR-L10-00056 | Frame was delivered during previous contract
74 | Door mark L10H03 to FF LOBBY | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 2376.6856 | 348.1769 | 2724.8625 | 348.1769 | 2724.8625 |  | PII-AX-WR-L10-00056
75 | Door mark L10H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 50% | 1211.05 | 1211.05 | 100% | 50% | 2422.1 | 1211.05 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 950.6742 | 139.2708 | 1089.945 | 139.2708 | 1089.945 |  | PII-AX-WR-L10-00056 | Frame was delivered during previous contract
76 | Door mark L10H06 to STAIR-08 | 1 | Nos. | 3090.96 | 50% | 1545.48 | 1545.48 | 100% | 50% | 3090.96 | 1545.48 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 1213.2018 | 177.7302 | 1390.932 | 177.7302 | 1390.932 | PII-AX-MR-ML-00014 | PII-AX-WR-L10-00056
77 | Door mark L10H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 50% | 1211.05 | 1211.05 | 100% | 50% | 2422.1 | 1211.05 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 950.6742 | 139.2708 | 1089.945 | 139.2708 | 1089.945 |  | PII-AX-WR-L10-00056 PII-AX-WR-L10-00092 PII-AX-WR-L10-00092
78 | Door mark L10R01 to STAIR-03 | 1 | Nos. | 3226.64 | 50% | 1613.32 | 1613.32 | 100% | 50% | 3226.64 | 1613.32 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 1290.656 | 161.332 | 1451.988 | 161.332 | 1451.988 |  | PII-AX-WR-L10-00028 | Frame was delivered during previous contract
79 | Door mark L10R03 to FF LOBBY | 1 | Nos. | 3252.08 | 50% | 1626.04 | 1626.04 | 100% | 50% | 3252.08 | 1626.04 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 1300.832 | 162.604 | 1463.436 | 162.604 | 1463.436 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013 | PII-AX-WR-L10-00028-2
80 | Door mark L10R04 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 0% | 0% | 80% | 0% | 80% | 5363.6 | 0 | 5363.6 | 0 | 5363.6
81 | Door mark L10R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 0% | 0% | 0% | 80% | 80% | 0 | 2422.1 | 2422.1 | 2422.1 | 2422.1 |  |  |  | MIR by CJ
82 | Door mark L10R09 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 9% | 35% | 15% | 0% | 0% | 56% | 24% | 80% | 1871.324 | 801.996 | 2673.32 | 801.996 | 2673.32
83 | Door mark L10R10 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 50% | 1613.32 | 1613.32 | 100% | 50% | 3226.64 | 1613.32 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 1290.656 | 161.332 | 1451.988 | 161.332 | 1451.988 | PII-AX-MR-ML-00014 | PII-AX-WR-L10-00028 PII-AX-WR-L10-00028 | Frame was delivered during previous contract
84 | Door mark L10R13 to STAIR-04 | 1 | Nos. | 3226.64 | 50% | 1613.32 | 1613.32 | 100% | 50% | 3226.64 | 1613.32 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 1290.656 | 161.332 | 1451.988 | 161.332 | 1451.988 |  | PII-AX-WR-L10-00028
85 | Door mark L11H01 to STAIR-07 | 1 | Nos. | 3090.96 | 50% | 1545.48 | 1545.48 | 100% | 50% | 3090.96 | 1545.48 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 1213.2018 | 177.7302 | 1390.932 | 177.7302 | 1390.932 |  | PII-AX-WR-L11-00057 | Frame was delivered during previous contract | PII-AX-WR-L10-00057
86 | Door mark L11H03 to FF LOBBY | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 2376.6856 | 348.1769 | 2724.8625 | 348.1769 | 2724.8625 |  | PII-AX-WR-L11-00057
87 | Door mark L11H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 50% | 1211.05 | 1211.05 | 100% | 50% | 2422.1 | 1211.05 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 950.6742 | 139.2708 | 1089.945 | 139.2708 | 1089.945 |  | PII-AX-WR-L11-00057 | Frame was delivered during previous contract
88 | Door mark L11H06 to STAIR-08 | 1 | Nos. | 3090.96 | 50% | 1545.48 | 1545.48 | 100% | 50% | 3090.96 | 1545.48 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 1213.2018 | 177.7302 | 1390.932 | 177.7302 | 1390.932 | PII-AX-MR-ML-00014 | PII-AX-WR-L11-00057
[8 empty] | 100% | [15 empty] | 0 | 0
[8 empty] | 100% | [15 empty] | 0 | 0
| To Collection Dhs. |  |  |  |  | 43545.224 | 77998.616 | 100% |  |  | 87659.456 | [9 empty] | 59008.988 | 15240.9168 | 74249.9048 | 15240.9168 | 74249.9048
| TIMBER DOORS (CONT'D) | [6 empty] | 100% | [15 empty] | 0 | 0
89 | Door mark L11H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 50% | 1211.05 | 1211.05 | 100% | 50% | 2422.1 | 1211.05 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 950.6742 | 139.2708 | 1089.945 | 139.2708 | 1089.945 |  | PII-AX-WR-L11-00057 | Frame was delivered during previous contract
90 | Door mark L11R01 to STAIR-03 | 1 | Nos. | 3226.64 | 50% | 1613.32 | 1613.32 | 100% | 50% | 3226.64 | 1613.32 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 1290.656 | 161.332 | 1451.988 | 161.332 | 1451.988 |  | PII-AX-WR-L11-00029 PII-AX-WR-L11-00029
91 | Door mark L11R03 to FF LOBBY | 1 | Nos. | 3252.08 | 50% | 1626.04 | 1626.04 | 100% | 50% | 3252.08 | 1626.04 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 1300.832 | 162.604 | 1463.436 | 162.604 | 1463.436 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013 | PII-AX-WR-L11-00045/ PII-AX-WR-L11-00029
92 | Door mark L11R04 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 10% | 0% | 56% | 34% | 90% | 3754.52 | 2279.53 | 6034.05 | 2279.53 | 6034.05 |  | PII-AX-WR-L11-00029 |  | WIR by CJ
93 | Door mark L11R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 0% | 0% | 0% | 80% | 80% | 0 | 2422.1 | 2422.1 | 2422.1 | 2422.1 |  |  |  | MIR by CJ
94 | Door mark L11R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 9% | 35% | 15% | 0% | 0% | 56% | 24% | 80% | 1871.324 | 801.996 | 2673.32 | 801.996 | 2673.32
95 | Door mark L11R10 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 50% | 1613.32 | 1613.32 | 100% | 50% | 3226.64 | 1613.32 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 1290.656 | 161.332 | 1451.988 | 161.332 | 1451.988 | PII-AX-MR-ML-00014 | PII-AX-WR-L11-00029 | Frame was delivered during previous contract
96 | Door mark L11R13 to STAIR-04 | 1 | Nos. | 3226.64 | 50% | 1613.32 | 1613.32 | 100% | 50% | 3226.64 | 1613.32 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 1290.656 | 161.332 | 1451.988 | 161.332 | 1451.988 |  | PII-AX-WR-L11-00029
97 | Door mark L12H01 to STAIR-07 | 1 | Nos. | 3090.96 | 50% | 1545.48 | 1545.48 | 100% | 50% | 3090.96 | 1545.48 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 1213.2018 | 177.7302 | 1390.932 | 177.7302 | 1390.932 |  | PII-AX-WR-L12-00058 | Frame was deliverd during previous contract
14 | Door mark L12H03 to FF LOBBY | 1 | Nos. | 2422.1 | 50% | 1211.05 | 1211.05 | 100% | 50% | 2422.1 | 1211.05 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 950.6742 | 139.2708 | 1089.945 | 139.2708 | 1089.945 |  | PII-AX-WR-L12-00058
99 | Door mark L12H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 2376.6856 | 348.1769 | 2724.8625 | 348.1769 | 2724.8625 |  | PII-AX-WR-L12-00058
100 | Door mark L12H06 to STAIR-08 | 1 | Nos. | 3090.96 | 50% | 1545.48 | 1545.48 | 100% | 50% | 3090.96 | 1545.48 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 1213.2018 | 177.7302 | 1390.932 | 177.7302 | 1390.932 | PII-AX-MR-ML-00014 | PII-AX-WR-L12-00058 | Frame was deliverd during previous contract
101 | Door mark L12H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 50% | 1211.05 | 1211.05 | 100% | 50% | 2422.1 | 1211.05 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 950.6742 | 139.2708 | 1089.945 | 139.2708 | 1089.945 | PII-AX-MR-ML-00014 | PII-AX-WR-L12-00058
102 | Door mark L12H11 to STAIR-06 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 0% | 0% | 80% | 0% | 80% | 3090.96 | 0 | 3090.96 | 0 | 3090.96 | PII-AX-MR-ML-00072
103 | Door mark L12R01 to STAIR-03 | 1 | Nos. | 3226.64 | 66% | 2129.5824 | 1097.0576 | 100% | 34% | 3226.64 | 1097.0576 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 877.6461 | 219.4115 | 1097.0576 | 219.4115 | 1097.0576 | PII-AX-MR-ML-00014 | PII-AX-WR-L12-00030 PII-AX-WR-L12-00102
104 | Door mark L12R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 3252.08 | 813.02 | 4065.1 | 813.02 | 4065.1 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013 | PII-AX-MR-ML-00013 PII-AX-WR-L12-00102
105 | Door mark L12R04 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 5363.6 | 1340.9 | 6704.5 | 1340.9 | 6704.5 |  | PII-AX-WR-L12-00102
106 | Door mark L12R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 14% | 6% | 0% | 100% | 100% | 0 | 3027.625 | 3027.625 | 3027.625 | 3027.625 |  | PII-AX-WR-L12-00102 |  | MIR by CJ
107 | Door mark L12R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 0% | 35% | 0% | 0% | 0% | 56% | 0% | 56% | 1871.324 | 0 | 1871.324 | 0 | 1871.324
108 | Door mark L12R10 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 50% | 1613.32 | 1613.32 | 100% | 50% | 3226.64 | 1613.32 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 1290.656 | 322.664 | 1613.32 | 322.664 | 1613.32 | PII-AX-MR-ML-00014 | PII-AX-WR-L12-00030 PII-AX-WR-L12-00091 | Frame was delivered during previous contract
109 | Door mark L12R13 to STAIR-04 | 1 | Nos. | 3226.64 | 50% | 1613.32 | 1613.32 | 100% | 50% | 3226.64 | 1613.32 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 1290.656 | 322.664 | 1613.32 | 322.664 | 1613.32 |  | PII-AX-WR-L12-00030 PII-AX-WR-L12-00091
110 | Door mark L14H01 to STAIR-07 | 1 | Nos. | 3090.96 | 50% | 1545.48 | 1545.48 | 100% | 50% | 3090.96 | 1545.48 | 21% | 9% | 35% | 15% | 14% | 0% | 78.5% | 15.5% | 94% | 1213.2018 | 239.5494 | 1452.7512 | 239.5494 | 1452.7512 |  | PII-AX-WR-L13-00059 PII-AX-WR-L13-00095 | Frame was delivered during previous contract
111 | Door mark L14H03 to FF LOBBY | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 14% | 6% | 78.5% | 21.5% | 100% | 2376.6856 | 650.9394 | 3027.625 | 650.9394 | 3027.625 | PII-AX-MR-ML-00016 | PII-AX-WR-L13-00059 PII-AX-WR-L13-00095
112 | Door mark L14H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 50% | 1211.05 | 1211.05 | 100% | 50% | 2422.1 | 1211.05 | 21% | 9% | 35% | 15% | 14% | 6% | 78.5% | 21.5% | 100% | 950.6742 | 260.3758 | 1211.05 | 260.3758 | 1211.05 |  | PII-AX-WR-L13-00059 PII-AX-WR-L13-00095 | Frame was delivered during previous contract
113 | Door mark L14H06 to STAIR-08 | 1 | Nos. | 3090.96 | 50% | 1545.48 | 1545.48 | 100% | 50% | 3090.96 | 1545.48 | 21% | 9% | 35% | 15% | 14% | 6% | 78.5% | 21.5% | 100% | 1213.2018 | 332.2782 | 1545.48 | 332.2782 | 1545.48 |  | PII-AX-WR-L13-00059 PII-AX-WR-L13-00095
114 | Door mark L14H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 50% | 1211.05 | 1211.05 | 100% | 50% | 2422.1 | 1211.05 | 21% | 9% | 35% | 15% | 14% | 6% | 78.5% | 21.5% | 100% | 950.6742 | 260.3758 | 1211.05 | 260.3758 | 1211.05 |  | PII-AX-WR-L13-00059 PII-AX-WR-L13-00095 | Frame was delivered during previous contract
115 | Door mark L14H11 to STAIR-06 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 3090.96 | 386.37 | 3477.33 | 386.37 | 3477.33 | PII-AX-MR-ML-00072 | PII-AX-WR-L13-00059
116 | Door mark L14R01 to STAIR-03 | 1 | Nos. | 3226.64 | 50% | 1613.32 | 1613.32 | 100% | 50% | 3226.64 | 1613.32 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 1290.656 | 322.664 | 1613.32 | 322.664 | 1613.32 |  | PII-AX-WR-L14-00031 PII-AX-WR-L13-00096 | Frame was deliverd during previous contract
117 | Door mark L14R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 3252.08 | 813.02 | 4065.1 | 813.02 | 4065.1 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013 | PII-AX-WR-L13-00096
118 | Door mark L14R04 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 5363.6 | 1340.9 | 6704.5 | 1340.9 | 6704.5 |  | PII-AX-WR-L13-00096
119 | Door mark L14R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 14% | 6% | 0% | 100% | 100% | 0 | 3027.625 | 3027.625 | 3027.625 | 3027.625 |  | PII-AX-WR-L13-00096 |  | MIR by CJ
120 | Door mark L14R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 9% | 35% | 15% | 0% | 0% | 56% | 24% | 80% | 1871.324 | 801.996 | 2673.32 | 801.996 | 2673.32
121 | Door mark L14R10 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 50% | 1613.32 | 1613.32 | 100% | 50% | 3226.64 | 1613.32 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 1290.656 | 322.664 | 1613.32 | 322.664 | 1613.32 | PII-AX-MR-ML-00014 | PII-AX-WR-L14-00031 PII-AX-WR-L13-00096 | Frame was deliverd during previous contract
122 | Door mark L14R13 to STAIR-04 | 1 | Nos. | 3226.64 | 60% | 1935.984 | 1290.656 | 100% | 40% | 3226.64 | 1290.656 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 1032.5248 | 258.1312 | 1290.656 | 258.1312 | 1290.656 |  | PII-AX-WR-L14-00031 PII-AX-WR-L13-00096
123 | Door mark L15H01 to STAIR-07 | 1 | Nos. | 3090.96 | 60% | 1854.576 | 1236.384 | 100% | 40% | 3090.96 | 1236.384 | 21% | 9% | 35% | 15% | 14% | 0% | 78.5% | 15.5% | 94% | 970.5614 | 191.6395 | 1162.201 | 191.6395 | 1162.201 |  | PII-AX-WR-L14-00060 PII-AX-WR-L14-00074
124 | Door mark L15H03 to FF LOBBY | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 14% | 6% | 78.5% | 21.5% | 100% | 2376.6856 | 650.9394 | 3027.625 | 650.9394 | 3027.625 |  | PII-AX-WR-L14-00060 PII-AX-WR-L14-00107
125 | Door mark L15H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 60% | 1453.26 | 968.84 | 100% | 40% | 2422.1 | 968.84 | 21% | 9% | 35% | 15% | 14% | 6% | 78.5% | 21.5% | 100% | 760.5394 | 208.3006 | 968.84 | 208.3006 | 968.84 |  | PII-AX-WR-L14-00060 PII-AX-WR-L14-00074 PII-AX-WR-L14-00107 | Frame was deliverd during previous contract
126 | Door mark L15H06 to STAIR-08 | 1 | Nos. | 3090.96 | 60% | 1854.576 | 1236.384 | 100% | 40% | 3090.96 | 1236.384 | 21% | 9% | 35% | 15% | 14% | 6% | 78.5% | 21.5% | 100% | 970.5614 | 265.8226 | 1236.384 | 265.8226 | 1236.384 |  | PII-AX-WR-L14-00060 PII-AX-WR-L14-00107
127 | Door mark L15H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 60% | 1453.26 | 968.84 | 100% | 40% | 2422.1 | 968.84 | 21% | 9% | 35% | 15% | 14% | 6% | 78.5% | 21.5% | 100% | 760.5394 | 208.3006 | 968.84 | 208.3006 | 968.84 | PII-AX-MR-ML-00014 | PII-AX-WR-L14-00060 PII-AX-WR-L14-00107 | Frame was deliverd during previous contract
128 | Door mark L15H11 to STAIR-06 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 3090.96 | 386.37 | 3477.33 | 386.37 | 3477.33 | PII-AX-MR-ML-00072 | PII-AX-WR-L14-00097
129 | Door mark L15R01 to STAIR-03 | 1 | Nos. | 3226.64 | 60% | 1935.984 | 1290.656 | 100% | 40% | 3226.64 | 1290.656 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 1032.5248 | 258.1312 | 1290.656 | 258.1312 | 1290.656 |  | PII-AX-WR-L14-00074
130 | Door mark L15R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 3252.08 | 813.02 | 4065.1 | 813.02 | 4065.1 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013 | PII-AX-WR-L14-00097
131 | Door mark L15R04 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 5363.6 | 1340.9 | 6704.5 | 1340.9 | 6704.5 |  | PII-AX-WR-L14-00074
132 | Door mark L15R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 14% | 6% | 0% | 100% | 100% | 0 | 3027.625 | 3027.625 | 3027.625 | 3027.625 |  | PII-AX-WR-L14-00074 |  | MIR by CJ
133 | Door mark L15R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 9% | 35% | 15% | 14% | 6% | 56% | 44% | 100% | 1871.324 | 1470.326 | 3341.65 | 1470.326 | 3341.65 |  | PII-AX-WR-L14-00097
134 | Door mark L15R10 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 60% | 1935.984 | 1290.656 | 100% | 40% | 3226.64 | 1290.656 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 1032.5248 | 258.1312 | 1290.656 | 258.1312 | 1290.656 | PII-AX-MR-ML-00014 | PII-AX-WR-L14-00097
100%
[7 empty] | 0 | 100%
| To Collection Dhs. |  |  |  |  | 39709.6564 | 102667.4236 | 100% |  | 0 | 119700.2986 | [9 empty] | 80868.8175 | 31414.3548 | 112283.1723 | 31414.3548 | 112283.1723
| TIMBER DOORS (CONT'D) | [6 empty] | 100%
135 | Door mark L15R13 to STAIR-04 | 1 | Nos. | 3226.64 | 60% | 1935.984 | 1290.656 | 100% | 40% | 3226.64 | 1290.656 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 1032.5248 | 258.1312 | 1290.656 | 258.1312 | 1290.656 |  | PII-AX-WR-L14-00097
136 | Door mark L16H01 to STAIR-07 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 14% | 6% | 78.5% | 21.5% | 100% | 3033.0045 | 830.6955 | 3863.7 | 830.6955 | 3863.7 |  | PII-AX-WR-L15-00061
137 | Door mark L16H03 to FF LOBBY | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 14% | 6% | 78.5% | 21.5% | 100% | 2376.6856 | 650.9394 | 3027.625 | 650.9394 | 3027.625 |  | PII-AX-WR-L15-00106
138 | Door mark L16H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 60% | 1453.26 | 968.84 | 100% | 40% | 2422.1 | 968.84 | 21% | 9% | 35% | 15% | 14% | 6% | 78.5% | 21.5% | 100% | 760.5394 | 208.3006 | 968.84 | 208.3006 | 968.84 | PII-AX-MR-ML-00014 | PII-AX-WR-L15-00106 | Frame was delivered during previous contract
139 | Door mark L16H06 to STAIR-08 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 14% | 6% | 78.5% | 21.5% | 100% | 3033.0045 | 830.6955 | 3863.7 | 830.6955 | 3863.7 |  | PII-AX-WR-L15-00106
140 | Door mark L16H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 60% | 1453.26 | 968.84 | 100% | 40% | 2422.1 | 968.84 | 21% | 9% | 35% | 15% | 14% | 6% | 78.5% | 21.5% | 100% | 760.5394 | 208.3006 | 968.84 | 208.3006 | 968.84 |  | PII-AX-WR-L15-00106
141 | Door mark L16H11 to STAIR-06 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 0% | 0% | 80% | 0% | 80% | 3090.96 | 0 | 3090.96 | 0 | 3090.96 | PII-AX-MR-ML-00072
142 | Door mark L16R01 to STAIR-03 | 1 | Nos. | 3226.64 | 60% | 1935.984 | 1290.656 | 100% | 40% | 3226.64 | 1290.656 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 1032.5248 | 258.1312 | 1290.656 | 258.1312 | 1290.656 |  | PII-AX-WR-L15-00098 | Frame was delivered during previous contract
143 | Door mark L16R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 3252.08 | 813.02 | 4065.1 | 813.02 | 4065.1 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013 | PII-AX-WR-L15-00098
144 | Door mark L16R04 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 5363.6 | 670.45 | 6034.05 | 670.45 | 6034.05 |  | PII-AX-WR-L15-00075
145 | Door mark L16R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | MIR by CJ
146 | Door mark L16R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 2673.32 | 668.33 | 3341.65 | 668.33 | 3341.65 |  | PII-AX-WR-L15-00098
147 | Door mark L16R10 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 60% | 1935.984 | 1290.656 | 100% | 40% | 3226.64 | 1290.656 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 1032.5248 | 258.1312 | 1290.656 | 258.1312 | 1290.656 | PII-AX-MR-ML-00014 | PII-AX-WR-L15-00098 | Frame was delivered during previous contract
148 | Door mark L16R13 to STAIR-04 | 1 | Nos. | 3226.64 | 60% | 1935.984 | 1290.656 | 100% | 40% | 3226.64 | 1290.656 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 1032.5248 | 129.0656 | 1161.5904 | 129.0656 | 1161.5904 |  | PII-AX-WR-L15-00098
149 | Door mark L17H01 to STAIR-07 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 3033.0045 | 444.3255 | 3477.33 | 444.3255 | 3477.33 |  | PII-AX-WR-L16-00062
150 | Door mark L17H03 to FF LOBBY | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 2376.6856 | 348.1769 | 2724.8625 | 348.1769 | 2724.8625 | PII-AX-MR-ML-00013 | PII-AX-WR-L16-00113
151 | Door mark L17H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 60% | 1453.26 | 968.84 | 100% | 40% | 2422.1 | 968.84 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 760.5394 | 111.4166 | 871.956 | 111.4166 | 871.956 | PII-AX-MR-ML-00013 | PII-AX-WR-L16-00113
152 | Door mark L17H06 to STAIR-08 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 3033.0045 | 444.3255 | 3477.33 | 444.3255 | 3477.33 | PII-AX-MR-ML-00013 | PII-AX-WR-L16-00113
153 | Door mark L17H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 60% | 1453.26 | 968.84 | 100% | 40% | 2422.1 | 968.84 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 760.5394 | 111.4166 | 871.956 | 111.4166 | 871.956 | PII-AX-MR-ML-00014 PII-AX-MR-ML-00013 | PII-AX-WR-L16-00113 | Frame was delivered during previous contract
154 | Door mark L17H11 to STAIR-06 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 0% | 0% | 56% | 24% | 80% | 2163.672 | 927.288 | 3090.96 | 927.288 | 3090.96 | PII-AX-MR-ML-00072
155 | Door mark L17R01 to STAIR-03 | 1 | Nos. | 3226.64 | 60% | 1935.984 | 1290.656 | 100% | 40% | 3226.64 | 1290.656 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 1032.5248 | 129.0656 | 1161.5904 | 129.0656 | 1161.5904 |  | PII-AX-WR-L16-00076 PII-AX-WR-L16-00099 | Frame was delivered during previous contract
156 | Door mark L17R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 3252.08 | 406.51 | 3658.59 | 406.51 | 3658.59 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013 | PII-AX-WR-L16-00099
157 | Door mark L17R04 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 5363.6 | 670.45 | 6034.05 | 670.45 | 6034.05 |  | PII-AX-WR-L16-00076
158 | Door mark L17R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 10% | 0% | 0% | 90% | 90% | 0 | 2724.8625 | 2724.8625 | 2724.8625 | 2724.8625 |  | PII-AX-WR-L16-00099 |  | MIR by CJ
159 | Door mark L17R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 2673.32 | 334.165 | 3007.485 | 334.165 | 3007.485 |  | PII-AX-WR-L16-00099
160 | Door mark L17R10 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 60% | 1935.984 | 1290.656 | 100% | 40% | 3226.64 | 1290.656 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 1032.5248 | 129.0656 | 1161.5904 | 129.0656 | 1161.5904 | PII-AX-MR-ML-00014 | PII-AX-WR-L16-00099 | Frame was delivered during previous contract
161 | Door mark L17R13 to STAIR-04 | 1 | Nos. | 3226.64 | 60% | 1935.984 | 1290.656 | 100% | 40% | 3226.64 | 1290.656 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 1032.5248 | 129.0656 | 1161.5904 | 129.0656 | 1161.5904 | PII-AX-MR-ML-00014 | PII-AX-WR-L16-00099
162 | Door mark L18R01 to STAIR-03 | 1 | Nos. | 3226.64 | 60% | 1935.984 | 1290.656 | 100% | 40% | 3226.64 | 1290.656 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 1032.5248 | 258.1312 | 1290.656 | 258.1312 | 1290.656 |  | PII-AX-WR-L18-00044
163 | Door mark L18R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 3252.08 | 813.02 | 4065.1 | 813.02 | 4065.1 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013 | PII-AX-WR-L17-00044
164 | Door mark L18R04 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 0% | 0% | 56% | 24% | 80% | 3754.52 | 1609.08 | 5363.6 | 1609.08 | 5363.6 |  |  |  | WIR to be raised
165 | Door mark L18R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 0% | 0% | 0% | 80% | 80% | 0 | 2422.1 | 2422.1 | 2422.1 | 2422.1 |  |  |  | MIR by CJ
166 | Door mark L18R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 9% | 35% | 15% | 0% | 0% | 56% | 24% | 80% | 1871.324 | 801.996 | 2673.32 | 801.996 | 2673.32
167 | Door mark L18R10 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 60% | 1935.984 | 1290.656 | 100% | 40% | 3226.64 | 1290.656 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 1032.5248 | 258.1312 | 1290.656 | 258.1312 | 1290.656 | PII-AX-MR-ML-00014 | PII-AX-WR-L18-00044 | Frame was delivered during previous contract
168 | Door mark L18R13 to STAIR-04 | 1 | Nos. | 3226.64 | 60% | 1935.984 | 1290.656 | 100% | 40% | 3226.64 | 1290.656 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 1032.5248 | 258.1312 | 1290.656 | 258.1312 | 1290.656 | PII-AX-MR-ML-00014 | PII-AX-WR-L18-00044 |  | WIR to be raised
169 | Door mark L19R01 to STAIR-03 | 1 | Nos. | 3226.64 | 60% | 1935.984 | 1290.656 | 100% | 40% | 3226.64 | 1290.656 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 1032.5248 | 129.0656 | 1161.5904 | 129.0656 | 1161.5904 |  | PII-AX-WR-L18-00045
170 | Door mark L19R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 3252.08 | 406.51 | 3658.59 | 406.51 | 3658.59 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013 | PII-AX-WR-L18-00045
171 | Door mark L19R04 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 5363.6 | 670.45 | 6034.05 | 670.45 | 6034.05 |  | PII-AX-WR-L18-00087
172 | Door mark L19R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 0% | 0% | 0% | 80% | 80% | 0 | 2422.1 | 2422.1 | 2422.1 | 2422.1 |  |  |  | MIR by CJ
173 | Door mark L19R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 9% | 35% | 15% | 0% | 0% | 56% | 24% | 80% | 1871.324 | 801.996 | 2673.32 | 801.996 | 2673.32
174 | Door mark L19R09 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 60% | 1935.984 | 1290.656 | 100% | 40% | 3226.64 | 1290.656 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 1032.5248 | 258.1312 | 1290.656 | 258.1312 | 1290.656 | PII-AX-MR-ML-00014 | PII-AX-WR-L18-00045
175 | Door mark L19R12 to STAIR-04 | 1 | Nos. | 3226.64 | 60% | 1935.984 | 1290.656 | 100% | 40% | 3226.64 | 1290.656 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 1032.5248 | 258.1312 | 1290.656 | 258.1312 | 1290.656 | PII-AX-MR-ML-00014 | PII-AX-WR-L18-00045
176 | Door mark L19R14 to TELECOM | 1 | Nos. | Deleted as per Email dated 29 June 2022 | [19 empty] | 0 | 0
177 | Door mark L20H01 to STAIR-07 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 3090.96 | 386.37 | 3477.33 | 386.37 | 3477.33 | PII-AX-MR-ML-00015 | PII-AX-WR-L19-00063
178 | Door mark L20H03 to FF LOBBY | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 2422.1 | 302.7625 | 2724.8625 | 302.7625 | 2724.8625 |  | PII-AX-WR-L19-00114
179 | Door mark L20H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 60% | 1453.26 | 968.84 | 100% | 40% | 2422.1 | 968.84 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 775.072 | 96.884 | 871.956 | 96.884 | 871.956 | PII-AX-MR-ML-00014 | PII-AX-WR-L19-00063 PII-AX-WR-L19-00114 | Frame was delivered during previous contract
180 | Door mark L20H06 to STAIR-08 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 3090.96 | 386.37 | 3477.33 | 386.37 | 3477.33 |  | PII-AX-WR-L19-00063 PII-AX-WR-L19-00114
181 | Door mark L20H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 60% | 1453.26 | 968.84 | 100% | 40% | 2422.1 | 968.84 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 775.072 | 96.884 | 871.956 | 96.884 | 871.956 | PII-AX-MR-ML-00014 | PII-AX-WR-L19-00114 | Frame was delivered during previous contract
100%
100%
| To Collection Dhs. |  |  |  |  | 33887.352 | 109429.948 | 100% |  | 0 | 131139.543 | [9 empty] | 90702.0933 | 25330.5682 | 116032.6615 | 25330.5682 | 116032.6615
| TIMBER DOORS (CONT'D) | [6 empty] | 100%
182 | Door mark L20R01 to STAIR-03 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 3226.64 | 806.66 | 4033.3 | 806.66 | 4033.3 | PII-AX-MR-ML-00016 | PII-AX-WR-L19-00077 | Frame was delivered during previous contract
183 | Door mark L20R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 3252.08 | 406.51 | 3658.59 | 406.51 | 3658.59 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013 | PII-AX-WR-L19-00077
184 | Door mark L20R04 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 5363.6 | 670.45 | 6034.05 | 670.45 | 6034.05 |  | PII-AX-WR-L19-00088
185 | Door mark L20R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 14% | 6% | 56% | 44% | 100% | 1695.47 | 1332.155 | 3027.625 | 1332.155 | 3027.625 |  | PII-AX-WR-L19-00077 |  | MIR by CJ
186 | Door mark L20R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 9% | 35% | 15% | 0% | 0% | 56% | 24% | 80% | 1871.324 | 801.996 | 2673.32 | 801.996 | 2673.32
187 | Door mark L20R09 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 30% | 967.992 | 2258.648 | 100% | 70% | 3226.64 | 2258.648 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 1806.9184 | 451.7296 | 2258.648 | 451.7296 | 2258.648 | PII-AX-MR-ML-00016 | PII-AX-WR-L19-00077
188 | Door mark L20R12 to STAIR-04 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 3226.64 | 806.66 | 4033.3 | 806.66 | 4033.3 | PII-AX-MR-ML-00014 | PII-AX-WR-L19-00077
189 | Door mark L20R14 to TELECOM | 1 | Nos. | Deleted as per Email dated 29 June 2022 | [19 empty] | 0 | 0
190 | Door mark L21H01 to STAIR-07 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 3033.0045 | 444.3255 | 3477.33 | 444.3255 | 3477.33 |  | PII-AX-WR-L20-00064
191 | Door mark L21H03 to FF LOBBY | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 2376.6856 | 348.1769 | 2724.8625 | 348.1769 | 2724.8625 |  | PII-AX-WR-L20-00064 PII-AX-WR-L21-00115
192 | Door mark L21H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 25% | 605.525 | 1816.575 | 100% | 75% | 2422.1 | 1816.575 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 1426.0114 | 208.9061 | 1634.9175 | 208.9061 | 1634.9175 | PII-AX-MR-ML-00014 | PII-AX-WR-L20-00064 PII-AX-WR-L21-00115
193 | Door mark L21H06 to STAIR-08 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 3033.0045 | 444.3255 | 3477.33 | 444.3255 | 3477.33 |  | PII-AX-WR-L20-00064 PII-AX-WR-L21-00115
194 | Door mark L21H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 30% | 726.63 | 1695.47 | 100% | 70% | 2422.1 | 1695.47 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 1330.9439 | 194.9791 | 1525.923 | 194.9791 | 1525.923 | PII-AX-MR-ML-00014 | PII-AX-WR-L20-00064 PII-AX-WR-L21-00115
195 | Door mark L21R01 to STAIR-03 | 1 | Nos. | 3226.64 | 30% | 967.992 | 2258.648 | 100% | 70% | 3226.64 | 2258.648 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 1806.9184 | 451.7296 | 2258.648 | 451.7296 | 2258.648 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016 | PII-AX-WR-L20-00078
196 | Door mark L21R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 3252.08 | 406.51 | 3658.59 | 406.51 | 3658.59 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013 | PII-AX-WR-L20-00078
197 | Door mark L21R04 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 10% | 0% | 56% | 34% | 90% | 3754.52 | 2279.53 | 6034.05 | 2279.53 | 6034.05 |  | PII-AX-WR-L20-00089 |  | WIR by CJ
198 | Door mark L21R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 14% | 6% | 0% | 100% | 100% | 0 | 3027.625 | 3027.625 | 3027.625 | 3027.625 |  | PII-AX-WR-L20-00078 |  | WIR by CJ
199 | Door mark L21R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 9% | 35% | 15% | 0% | 0% | 56% | 24% | 80% | 1871.324 | 801.996 | 2673.32 | 801.996 | 2673.32
200 | Door mark L21R09 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 3226.64 | 806.66 | 4033.3 | 806.66 | 4033.3 | PII-AX-MR-ML-00016 | PII-AX-WR-L20-00078
201 | Door mark L21R12 to STAIR-04 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 3226.64 | 806.66 | 4033.3 | 806.66 | 4033.3 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016 | PII-AX-WR-L20-00078
202 | Door mark L21R14 to TELECOM | 1 | Nos. | Deleted as per Email dated 29 June 2022 | [11 empty] | 0% | 0% | [6 empty] | 0 | 0
203 | Door mark L22H01 to STAIR-07 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 3033.0045 | 444.3255 | 3477.33 | 444.3255 | 3477.33 |  | PII-AX-WR-L21-00065
204 | Door mark L22H03 to FF LOBBY | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 2376.6856 | 348.1769 | 2724.8625 | 348.1769 | 2724.8625 |  | PII-AX-WR-L21-00065 PII-AX-WR-L21-00116
205 | Door mark L22H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 25% | 605.525 | 1816.575 | 100% | 75% | 2422.1 | 1816.575 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 1426.0114 | 208.9061 | 1634.9175 | 208.9061 | 1634.9175 | PII-AX-MR-ML-00014 | PII-AX-WR-L21-00065 PII-AX-WR-L21-00116 | Frame was delivered during previous contract
206 | Door mark L22H06 to STAIR-08 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 3033.0045 | 444.3255 | 3477.33 | 444.3255 | 3477.33 |  | PII-AX-WR-L21-00065 PII-AX-WR-L21-00116
207 | Door mark L22H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 22% | 532.862 | 1889.238 | 100% | 78% | 2422.1 | 1889.238 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 1483.0518 | 217.2624 | 1700.3142 | 217.2624 | 1700.3142 | PII-AX-MR-ML-00014 | PII-AX-WR-L21-00065 PII-AX-WR-L21-00116 | Frame was delivered during previous contract
208 | Door mark L22R01 to STAIR-03 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 3226.64 | 806.66 | 4033.3 | 806.66 | 4033.3 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016 | PII-AX-WR-L21-00079
209 | Door mark L22R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 3252.08 | 813.02 | 4065.1 | 813.02 | 4065.1 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013 | PII-AX-WR-L21-00079
210 | Door mark L22R04 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 5363.6 | 1340.9 | 6704.5 | 1340.9 | 6704.5 |  | PII-AX-WR-L21-00090
211 | Door mark L22R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 0% | 0% | 0% | 80% | 80% | 0 | 2422.1 | 2422.1 | 2422.1 | 2422.1 |  |  |  | MIR & WIR by CJ
212 | Door mark L22R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 2673.32 | 334.165 | 3007.485 | 334.165 | 3007.485 |  | PII-AX-WR-L22-00024
213 | Door mark L22R09 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 3226.64 | 806.66 | 4033.3 | 806.66 | 4033.3 | PII-AX-MR-ML-00016 | PII-AX-WR-L21-00079
214 | Door mark L22R12 to STAIR-04 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 3226.64 | 806.66 | 4033.3 | 806.66 | 4033.3 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016 | PII-AX-WR-L21-00079
215 | Door mark L22R14 to TELECOM | 1 | Nos. | Deleted as per Email dated 29 June 2022 | [19 empty] | 0 | 0
216 | Door mark L23H01 to STAIR-07 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 3033.0045 | 444.3255 | 3477.33 | 444.3255 | 3477.33 |  | PII-AX-WR-L22-00066
217 | Door mark L23H03 to FF LOBBY | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 2422.1 | 302.7625 | 2724.8625 | 302.7625 | 2724.8625 |  | PII-AX-WR-L22-00117
218 | Door mark L23H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 23% | 557.083 | 1865.017 | 100% | 77% | 2422.1 | 1865.017 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 1492.0136 | 186.5017 | 1678.5153 | 186.5017 | 1678.5153 | PII-AX-MR-ML-00014 | PII-AX-WR-L22-00117
219 | Door mark L23H06 to STAIR-08 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 3033.0045 | 444.3255 | 3477.33 | 444.3255 | 3477.33 |  | PII-AX-WR-L22-00066 PII-AX-WR-L22-00117
220 | Door mark L23H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 20.34% | 492.6551 | 1929.4449 | 100% | 79.66% | 2422.1 | 1929.4449 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 1514.6142 | 221.8862 | 1736.5004 | 221.8862 | 1736.5004 | PII-AX-MR-ML-00014 | PII-AX-WR-L22-00066 PII-AX-WR-L22-00117 | Frame was delivered during previous contract
221 | Door mark L23R01 to STAIR-03 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 3226.64 | 403.33 | 3629.97 | 403.33 | 3629.97 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016 | PII-AX-WR-L22-00085
222 | Door mark L23R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 3252.08 | 813.02 | 4065.1 | 813.02 | 4065.1 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013 | PII-AX-WR-L22-00085
223 | Door mark L23R04 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 5363.6 | 1340.9 | 6704.5 | 1340.9 | 6704.5 |  | PII-AX-WR-L22-00085
224 | Door mark L23R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 14% | 6% | 0% | 100% | 100% | 0 | 3027.625 | 3027.625 | 3027.625 | 3027.625 |  | PII-AX-WR-L22-00085 |  | MIR & WIR by CJ
225 | Door mark L23R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 2673.32 | 668.33 | 3341.65 | 668.33 | 3341.65 |  | PII-AX-WR-L22-00085 |  | MIR & WIR by CJ
226 | Door mark L23R09 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 3226.64 | 806.66 | 4033.3 | 806.66 | 4033.3 | PII-AX-MR-ML-00016 | PII-AX-WR-L22-00085
227 | Door mark L23R12 to STAIR-04 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 3226.64 | 403.33 | 3629.97 | 403.33 | 3629.97 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016 | PII-AX-WR-L22-00085
228 | Door mark L23R14 to TELECOM | 1 | Nos. | Deleted as per Email dated 29 June 2022 | [19 empty] | 0 | 0
229 | Door mark L24H01 to STAIR-07 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 3033.0045 | 444.3255 | 3477.33 | 444.3255 | 3477.33 |  | PII-AX-WR-L23-00067
100%
100%
| To Collection Dhs. |  |  |  |  | 5456.2641 | 131543.4359 | 100% |  |  | 160546.8909 | [9 empty] | 116597.7839 | 33998.0675 | 150595.8514 | 33998.0675 | 150595.8514
| TIMBER DOORS (CONT'D) | [6 empty] | 100%
100%
230 | Door mark L24H03 to FF LOBBY | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 2376.6856 | 348.1769 | 2724.8625 | 348.1769 | 2724.8625 |  | PII-AX-WR-L23-00067 PII-AX-WR-L23-00118
231 | Door mark L24H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 22% | 532.862 | 1889.238 | 100% | 78% | 2422.1 | 1889.238 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 1483.0518 | 217.2624 | 1700.3142 | 217.2624 | 1700.3142 | PII-AX-MR-ML-00014 | PII-AX-WR-L23-00067 PII-AX-WR-L23-00118 | Frame was delivered during previous contract
232 | Door mark L24H06 to STAIR-08 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 3033.0045 | 444.3255 | 3477.33 | 444.3255 | 3477.33 |  | PII-AX-WR-L23-00067 PII-AX-WR-L23-00118
233 | Door mark L24H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 22% | 532.862 | 1889.238 | 100% | 78% | 2422.1 | 1889.238 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 1483.0518 | 217.2624 | 1700.3142 | 217.2624 | 1700.3142 |  | PII-AX-WR-L23-00067 PII-AX-WR-L23-00118 | Frame was delivered during previous contract
234 | Door mark L24R11 to HOUSEKEEPING LOBBY | 1 | Nos. | 2226 | 0% | 0 | 2226 | 100% | 100% | 2782.5 | 2782.5 | 21% | 9% | 35% | 15% | 0% | 0% | 56% | 24% | 80% | 1558.2 | 667.8 | 2226 | 667.8 | 2226 | PII-AX-MR-ML-00025 |  |  | MIR by CJ
235 | Door mark L24R14 to STAIR-04 | 1 | Nos. | 2226 | 0% | 0 | 2226 | 100% | 100% | 2782.5 | 2782.5 | 21% | 9% | 35% | 15% | 0% | 0% | 56% | 24% | 80% | 1558.2 | 667.8 | 2226 | 667.8 | 2226 | PII-AX-MR-ML-00025
236 | Door mark L24R15 to PANTRY | 1 | Nos. | 1955.7 | 0% | 0 | 1955.7 | 100% | 100% | 2444.625 | 2444.625 | 21% | 9% | 35% | 15% | 0% | 0% | 0% | 80% | 80% | 0 | 1955.7 | 1955.7 | 1955.7 | 1955.7
237 | Door mark L24R16 to TELECOM | 1 | Nos. | Deleted as per Email dated 29 June 2022 | [19 empty] | 0 | 0
238 | Door mark L25H01 to STAIR-07 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 3033.0045 | 444.3255 | 3477.33 | 444.3255 | 3477.33 |  | PII-AX-WR-L24-00068
239 | Door mark L25H03 to FF LOBBY | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 2376.6856 | 348.1769 | 2724.8625 | 348.1769 | 2724.8625 |  | PII-AX-WR-L24-00068
240 | Door mark L25H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 22% | 532.862 | 1889.238 | 100% | 78% | 2422.1 | 1889.238 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 1483.0518 | 217.2624 | 1700.3142 | 217.2624 | 1700.3142 |  | PII-AX-WR-L24-00068
241 | Door mark L25H06 to STAIR-08 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 3033.0045 | 444.3255 | 3477.33 | 444.3255 | 3477.33 |  | PII-AX-WR-L24-00068
242 | Door mark L25H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 22% | 532.862 | 1889.238 | 100% | 78% | 2422.1 | 1889.238 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 1483.0518 | 217.2624 | 1700.3142 | 217.2624 | 1700.3142 | PII-AX-MR-ML-00014 | PII-AX-WR-L24-00068
243 | Door mark L25H11 to STAIR-06 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 0% | 0% | 71% | 9% | 80% | 2743.227 | 347.733 | 3090.96 | 347.733 | 3090.96 | PII-AX-MR-ML-00073 |  |  | WIR by CJ
244 | Door mark L25R01 to STAIR-03 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 0% | 35% | 0% | 0% | 0% | 56% | 0% | 56% | 2258.648 | 0 | 2258.648 | 0 | 2258.648 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016
245 | Door mark L25R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 15% | 0% | 0% | 71% | 9% | 80% | 2886.221 | 365.859 | 3252.08 | 365.859 | 3252.08 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013
246 | Door mark L25R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 0% | 0% | 21% | 59% | 80% | 635.8012 | 1786.2987 | 2422.1 | 1786.2987 | 2422.1 |  |  |  | MIR by CJ
247 | Door mark L25R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 9% | 35% | 15% | 0% | 0% | 56% | 24% | 80% | 1871.324 | 801.996 | 2673.32 | 801.996 | 2673.32
248 | Door mark L25R10 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 0% | 0% | 80% | 0% | 80% | 3226.64 | 0 | 3226.64 | 0 | 3226.64 | PII-AX-MR-ML-00016 |  |  | WIR to be raised
249 | Door mark L25R13 to STAIR-04 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 0% | 0% | 80% | 0% | 80% | 3226.64 | 0 | 3226.64 | 0 | 3226.64 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016 |  |  | WIR to be raised
250 | Door mark L25R18 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 0% | 0% | 80% | 0% | 80% | 5363.6 | 0 | 5363.6 | 0 | 5363.6
251 | Door mark L26H02 to STAIR-07 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 3033.0045 | 444.3255 | 3477.33 | 444.3255 | 3477.33 |  | PII-AX-WR-L25-00069
252 | Door mark L26H03 to FF LOBBY | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 2376.6856 | 348.1769 | 2724.8625 | 348.1769 | 2724.8625 |  | PII-AX-WR-L25-00069 PII-AX-WR-L25-00120
253 | Door mark L26H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 22% | 532.862 | 1889.238 | 100% | 78% | 2422.1 | 1889.238 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 1483.0518 | 217.2624 | 1700.3142 | 217.2624 | 1700.3142 |  | PII-AX-WR-L25-00069 PII-AX-WR-L25-00120 | Frame was delivered during previous contract
254 | Door mark L26H06 to STAIR-08 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 3033.0045 | 444.3255 | 3477.33 | 444.3255 | 3477.33 |  | PII-AX-WR-L25-00069 PII-AX-WR-L25-00120
255 | Door mark L26H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 22% | 532.862 | 1889.238 | 100% | 78% | 2422.1 | 1889.238 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 1483.0518 | 217.2624 | 1700.3142 | 217.2624 | 1700.3142 | PII-AX-MR-ML-00014 | PII-AX-WR-L25-00069 PII-AX-WR-L25-00120 | Frame was delivered during previous contract
256 | Door mark L26H11 to STAIR-06 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 0% | 0% | 80% | 0% | 80% | 3090.96 | 0 | 3090.96 | 0 | 3090.96 | PII-AX-MR-ML-00073
257 | Door mark L26R01 to STAIR-03 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 10% | 0% | 65% | 25% | 90% | 2621.645 | 1008.325 | 3629.97 | 1008.325 | 3629.97 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016 | PII-AX-WR-L25-00111
258 | Door mark L26R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 15% | 0% | 0% | 80% | 0% | 80% | 3252.08 | 0 | 3252.08 | 0 | 3252.08 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013
259 | Door mark L26R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 10% | 0% | 0% | 90% | 90% | 0 | 2724.8625 | 2724.8625 | 2724.8625 | 2724.8625 |  | PII-AX-WR-L25-00111 |  | MIR by CJ
260 | Door mark L26R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 9% | 35% | 15% | 0% | 0% | 56% | 24% | 80% | 1871.324 | 801.996 | 2673.32 | 801.996 | 2673.32
261 | Door mark L26R10 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 3226.64 | 403.33 | 3629.97 | 403.33 | 3629.97 | PII-AX-MR-ML-00016 | PII-AX-WR-L26-00039 PII-AX-WR-L25-00111 |  | WIR to be raised
262 | Door mark L26R13 to STAIR-04 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 3226.64 | 403.33 | 3629.97 | 403.33 | 3629.97 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016 | PII-AX-WR-L25-00111 |  | WIR to be raised
263 | Door mark L26R18 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 5363.6 | 670.45 | 6034.05 | 670.45 | 6034.05 |  | PII-AX-WR-L25-00111 |  | WIR to be raised
264 | Door mark L27H01 to STAIR-07 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 3033.0045 | 444.3255 | 3477.33 | 444.3255 | 3477.33 | PII-AX-MR-ML-00016 | PII-AX-WR-L26-00082
265 | Door mark L27H03 to FF LOBBY | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 2376.6856 | 348.1769 | 2724.8625 | 348.1769 | 2724.8625 |  | PII-AX-WR-L26-00082
266 | Door mark L27H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 22% | 532.862 | 1889.238 | 100% | 78% | 2422.1 | 1889.238 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 1483.0518 | 217.2624 | 1700.3142 | 217.2624 | 1700.3142 |  | PII-AX-WR-L26-00082
267 | Door mark L27H06 to STAIR-08 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 3033.0045 | 444.3255 | 3477.33 | 444.3255 | 3477.33 |  | PII-AX-WR-L26-00082
268 | Door mark L27H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 22% | 532.862 | 1889.238 | 100% | 78% | 2422.1 | 1889.238 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 1483.0518 | 217.2624 | 1700.3142 | 217.2624 | 1700.3142 | PII-AX-MR-ML-00014 | PII-AX-WR-L26-00082
269 | Door mark L27H11 to STAIR-06 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 3090.96 | 386.37 | 3477.33 | 386.37 | 3477.33 | PII-AX-MR-ML-00073 | PII-AX-WR-L26-00082 |  | WIR to be raised
270 | Door mark L27R01 to STAIR-03 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 10% | 0% | 65% | 25% | 90% | 2621.645 | 1008.325 | 3629.97 | 1008.325 | 3629.97 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016 | PII-AX-WR-L26-00112
271 | Door mark L27R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 3252.08 | 813.02 | 4065.1 | 813.02 | 4065.1 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013 | PII-AX-WR-L26-00112
272 | Door mark L27R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 0% | 0% | 56% | 24% | 80% | 1695.47 | 726.63 | 2422.1 | 726.63 | 2422.1
273 | Door mark L27R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 9% | 35% | 15% | 0% | 0% | 56% | 24% | 80% | 1871.324 | 801.996 | 2673.32 | 801.996 | 2673.32
274 | Door mark L27R10 to HOUSEKEEPING LOBBY | 1 | Nos. | 2550.36 | 0% | 0 | 2550.36 | 100% | 100% | 3187.95 | 3187.95 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 2550.36 | 637.59 | 3187.95 | 637.59 | 3187.95 | PII-AX-MR-ML-00016 | PII-AX-WR-L26-00040 PII-AX-WR-L26-00112 |  | WIR to be raised
275 | Door mark L27R13 to STAIR-04 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 3226.64 | 806.66 | 4033.3 | 806.66 | 4033.3 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016 | PII-AX-WR-L26-00112 |  | WIR to be raised
276 | Door mark L27R14 to TELECOM | 1 | Nos. | Deleted as per Email dated 29 June 2022
100%
100%
| To Collection Dhs. |  |  |  |  | 4262.896 | 126252.784 | 100% |  | 0 | 154037.504 | [9 empty] | 108892.0579 | 24027.1562 | 132919.2141 | 24027.1562 | 132919.2141
| TIMBER DOORS (CONT'D) | [6 empty] | 100%
100%
277 | Door mark L27R20 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 5363.6 | 1340.9 | 6704.5 | 1340.9 | 6704.5 |  | PII-AX-WR-L26-00112
278 | Door mark L28H02 to STAIR-07 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 3033.0045 | 444.3255 | 3477.33 | 444.3255 | 3477.33 | PII-AX-MR-ML-00016 | PII-AX-WR-L27-00083
279 | Door mark L28H03 to FF LOBBY | 1 | Nos. | 2422.1 | 0% | 0 | 94.61 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 2376.6856 | 348.1769 | 2724.8625 | 348.1769 | 2724.8625 |  | PII-AX-WR-L27-00083
280 | Door mark L28H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 22% | 532.862 | 1889.238 | 100% | 78% | 2422.1 | 1889.238 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 1483.0518 | 217.2624 | 1700.3142 | 217.2624 | 1700.3142 |  | PII-AX-WR-L27-00083
281 | Door mark L28H06 to STAIR-08 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 3033.0045 | 444.3255 | 3477.33 | 444.3255 | 3477.33 |  | PII-AX-WR-L27-00071
282 | Door mark L28H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 22% | 532.862 | 1889.238 | 100% | 78% | 2422.1 | 1889.238 | 21% | 9% | 35% | 15% | 10% | 0% | 78.5% | 11.5% | 90% | 1483.0518 | 217.2624 | 1700.3142 | 217.2624 | 1700.3142 | PII-AX-MR-ML-00014 | PII-AX-WR-L27-00083
283 | Door mark L28H11 to STAIR-06 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 0% | 0% | 80% | 0% | 80% | 3090.96 | 0 | 3090.96 | 0 | 3090.96 | PII-AX-MR-ML-00073 |  |  | WIR to be raised
284 | Door mark L28R01 to STAIR-03 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 0% | 0% | 80% | 0% | 80% | 3226.64 | 0 | 3226.64 | 0 | 3226.64 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016 |  |  | WIR to be raised
285 | Door mark L28R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 15% | 0% | 0% | 80% | 0% | 80% | 3252.08 | 0 | 3252.08 | 0 | 3252.08 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013
286 | Door mark L28R06 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 0% | 0% | 56% | 24% | 80% | 1695.47 | 726.63 | 2422.1 | 726.63 | 2422.1 |  |  |  | MIR by CJ
287 | Door mark L28R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 9% | 35% | 15% | 0% | 0% | 56% | 24% | 80% | 1871.324 | 801.996 | 2673.32 | 801.996 | 2673.32
288 | Door mark L28R10 to HOUSEKEEPING LOBBY | 1 | Nos. | 2550.36 | 0% | 0 | 2550.36 | 100% | 100% | 3187.95 | 3187.95 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 2550.36 | 318.795 | 2869.155 | 318.795 | 2869.155 | PII-AX-MR-ML-00016 | PII-AX-WR-L28-00041
289 | Door mark L28R13 to STAIR-04 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 0% | 0% | 80% | 0% | 80% | 3226.64 | 0 | 3226.64 | 0 | 3226.64 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016 |  |  | WIR to be raised
290 | Door mark L28R14 to TELECOM | 1 | Nos. | Deleted as per Email dated 29 June 2022 | [19 empty] | 0 | 0
291 | Door mark L28R19 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 0% | 0% | 80% | 0% | 80% | 5363.6 | 0 | 5363.6 | 0 | 5363.6
292 | Door mark L29H01 to STAIR-07 | 1 | Nos. | 2933.02 |  | 0 |  | 100% |  |  | Excluded | [12 empty] | 0
293 | Door mark L29H03 to FF LOBBY | 1 | Nos. | 2038.38 |  | 0 |  | 100% |  |  | Excluded | [12 empty] | 0
294 | Door mark L29H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2038.38 |  | 0 |  | 100% |  |  | Excluded | [12 empty] | 0
295 | Door mark L29H20 to MEP PLANT ROOM | 1 | Nos. | 2603.36 |  | 0 |  | 100% |  |  | Excluded | [12 empty] | 0
296 | Door mark L29R01 to STAIR-03 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 0% | 0% | 80% | 0% | 80% | 3226.64 | 0 | 3226.64 | 0 | 3226.64 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016 |  |  | WIR to be raised
297 | Door mark L29R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 15% | 0% | 0% | 80% | 0% | 80% | 3252.08 | 0 | 3252.08 | 0 | 3252.08 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013
298 | Door mark L29R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 0% | 0% | 0% | 80% | 80% | 0 | 2422.1 | 2422.1 | 2422.1 | 2422.1 |  |  |  | MIR by CJ
299 | Door mark L29R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 9% | 35% | 15% | 0% | 0% | 56% | 24% | 80% | 1871.324 | 801.996 | 2673.32 | 801.996 | 2673.32
300 | Door mark L29R10 to HOUSEKEEPING LOBBY | 1 | Nos. | 2550.36 | 0% | 0 | 2550.36 | 100% | 100% | 3187.95 | 3187.95 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 2550.36 | 318.795 | 2869.155 | 318.795 | 2869.155 | PII-AX-MR-ML-00016 | PII-AX-WR-L29-00042
301 | Door mark L29R13 to STAIR-04 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 0% | 0% | 80% | 0% | 80% | 3226.64 | 0 | 3226.64 | 0 | 3226.64 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016 |  |  | WIR to be raised
302 | Door mark L29R14 to TELECOM | 1 | Nos. | Deleted as per Email dated 29 June 2022 | [7 empty] | 21% | 9% | 35% | 15% | 0% | 0% | [6 empty] | 0 | 0
303 | Door mark L29R18 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 0% | 0% | 80% | 0% | 80% | 5363.6 | 0 | 5363.6 | 0 | 5363.6
304 | Door mark L30R01 to STAIR-03 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 0% | 0% | 80% | 0% | 80% | 3226.64 | 0 | 3226.64 | 0 | 3226.64 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016
305 | Door mark L30R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 15% | 0% | 0% | 80% | 0% | 80% | 3252.08 | 0 | 3252.08 | 0 | 3252.08 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013
306 | Door mark L30R05 to WM ROOM | 1 | Nos. | 2995.56 | 0% | 0 | 2995.56 | 100% | 100% | 3744.45 | 3744.45 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | MIR by CJ
307 | Door mark L30R06 to HOUSEKEEPING LOBBY | 1 | Nos. | 2550.36 | 0% | 0 | 2550.36 | 100% | 100% | 3187.95 | 3187.95 | 21% | 9% | 35% | 15% | 10% | 0% | 80% | 10% | 90% | 2550.36 | 318.795 | 2869.155 | 318.795 | 2869.155 | PII-AX-MR-ML-00016 | PII-AX-WR-L30-00043
308 | Door mark L30R09 to STAIR-04 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 0% | 0% | 80% | 0% | 80% | 3226.64 | 0 | 3226.64 | 0 | 3226.64 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016
309 | Door mark L30R13 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 9% | 35% | 0% | 0% | 0% | 65% | 0% | 65% | 2172.0725 | 0 | 2172.0725 | 0 | 2172.0725
310 | Door mark L30R17 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 0% | 0% | 0% | 65% | 0% | 65% | 4357.925 | 0 | 4357.925 | 0 | 4357.925 |  |  |  | WIR to be raised
311 | Door mark L31R02 to STAIR-03 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 0% | 35% | 0% | 0% | 0% | 56% | 0% | 56% | 2258.648 | 0 | 2258.648 | 0 | 2258.648 |  |  |  | MIR by CJ
312 | Door mark L31R04 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 0% | 0% | 0% | 65% | 0% | 65% | 2642.315 | 0 | 2642.315 | 0 | 2642.315 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013
313 | Door mark L31R07 to WM ROOM | 1 | Nos. | 2995.56 | 0% | 0 | 2995.56 | 100% | 100% | 3744.45 | 3744.45 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | MIR by CJ
314 | Door mark L31R09 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 0% | 35% | 0% | 0% | 0% | 56% | 0% | 56% | 1871.324 | 0 | 1871.324 | 0 | 1871.324
315 | Door mark L31R10 to HOUSEKEEPING LOBBY | 1 | Nos. | 2550.36 | 0% | 0 | 2550.36 | 100% | 100% | 3187.95 | 3187.95 | 21% | 9% | 35% | 15% | 0% | 0% | 80% | 0% | 80% | 2550.36 | 0 | 2550.36 | 0 | 2550.36 | PII-AX-MR-ML-00016
316 | Door mark L31R13 to STAIR-04 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 0% | 0% | 0% | 65% | 0% | 65% | 2621.645 | 0 | 2621.645 | 0 | 2621.645 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016
317 | Door mark L31R17 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 0% | 35% | 0% | 0% | 0% | 56% | 0% | 56% | 3754.52 | 0 | 3754.52 | 0 | 3754.52
318 | Door mark LGF121 to MECH ROOM | 1 | Nos. | 2603.36 | 0% | 0 | 2603.36 | 100% | 100% | 3254.2 | 3254.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | MIR by CJ
319 | Door mark LGF14 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | MIR by CJ
320 | Door mark LGF197 to ACCESS STAIR TO MEP | 1 | Nos. | 2048.98 | 0% | 0 | 2048.98 | 100% | 100% | 2561.225 | 2561.225 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
321 | Door mark LGF25 to FTR | 1 | Nos. | 2175.12 | 0% | 0 | 2175.12 | 100% | 100% | 2718.9 | 2718.9 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | MIR by CJ
322 | Door mark L18H06 to STAIR-08 | 1 | Nos. | 2946.8 | 0% | 0 | 2946.8 | 100% | 100% | 3683.5 | 3683.5 | 21% | 0% | 35% | 0% | 0% | 0% | 56% | 0% | 56% | 2062.76 | 0 | 2062.76 | 0 | 2062.76 | PII-AX-MR-ML-00016
323 | Door mark L18H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2336.24 | 0% | 0 | 2336.24 | 100% | 100% | 2920.3 | 2920.3 | 21% | 0% | 35% | 0% | 0% | 0% | 56% | 0% | 56% | 1635.368 | 0 | 1635.368 | 0 | 1635.368
324 | Door mark L06R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 |  | 0
325 | Door mark L07R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 |  | 0 |  |  |  | `
100%
| To Collection Dhs. |  |  |  |  | 1065.724 | 130501.746 | 100% |  |  | 165091.926 | [9 empty] | 98722.7738 | 8721.3596 | 107444.1334 | 8721.3596 | 107444.1334
| TIMBER DOORS (CONT'D) | [6 empty] | 100%
100%
326 | Door mark L08R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 |  | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
327 | Door mark L09R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
328 | Door mark L10R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
329 | Door mark L11R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
330 | Door mark L12R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
331 | Door mark L14R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
332 | Door mark L15R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
333 | Door mark L16R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
334 | Door mark L17R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
335 | Door mark L18R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
336 | Door mark L19R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
337 | Door mark L20R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
338 | Door mark L21R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
339 | Door mark L22R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
340 | Door mark L23R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
341 | Door mark L24R09 to KITCHEN EXTRACT RISER | 1 | Nos. | Deleted as per Email dated 29 June 2022 | [7 empty] | 0% | 0% | 0% | 0% | 0% | [7 empty] | 0 | 0
342 | Door mark L25R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
343 | Door mark L26R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
344 | Door mark L27R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
345 | Door mark L28R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
346 | Door mark L29R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
347 | Door mark L30R14 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
348 | Door mark L31R08 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
349 | Door mark LGF129 to CEF EXHAUST ACCESS | 1 | Nos. | - | 0% |  | Excluded | 100%
100%
100%
[8 empty] | 100% |  |  | 0
| To Collection Dhs. |  |  |  |  | 0 | 50860.92 | 100% |  |  | 63576.15 | [9 empty] | 0 | 0 | 0 | 0 | 0
100%
| TIMBER DOORS (CONT'D) | [6 empty] | 100%
100%
| COLLECTION | [6 empty] | 100%
100%
| Page 1/1 |  |  |  |  | 19978.7841 | 67296.3601 | 100% |  |  | 79287.0862 | [9 empty] | 33463.1517 | 4564.94 | 38028.0917 | 4564.94 | 38028.0917
100%
| Page 1/2 |  |  |  |  | 43545.224 | 77998.616 | 100% |  |  | 87659.456 | [9 empty] | 59008.988 | 15240.9168 | 74249.9048 | 15240.9168 | 74249.9048
100%
| Page 1/3 |  |  |  |  | 39709.6564 | 102667.4236 | 100% |  |  | 119700.2986 | [9 empty] | 80868.8175 | 31414.3548 | 112283.1723 | 31414.3548 | 112283.1723
100%
| Page 1/4 |  |  |  |  | 33887.352 | 109429.948 | 100% |  |  | 131139.543 | [9 empty] | 90702.0933 | 25330.5682 | 116032.6615 | 25330.5682 | 116032.6615
100%
| Page 1/5 |  |  |  |  | 5456.2641 | 131543.4359 | 100% |  |  | 160546.8909 | [9 empty] | 116597.7839 | 33998.0675 | 150595.8514 | 33998.0675 | 150595.8514
100%
| Page 1/6 |  |  |  |  | 4262.896 | 126252.784 | 100% |  |  | 154037.504 | [9 empty] | 108892.0579 | 24027.1562 | 132919.2141 | 24027.1562 | 132919.2141
100%
| Page 1/7 |  |  |  |  | 1065.724 | 130501.746 | 100% |  |  | 165091.926 | [9 empty] | 98722.7738 | 8721.3596 | 107444.1334 | 8721.3596 | 107444.1334
100%
| Page 1/8 |  |  |  |  | 0 | 50860.92 | 100% |  |  | 63576.15 | [9 empty] | 0 | 0 | 0 | 0 | 0
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
| To Main Summary |  |  |  |  | 147905.9007 | 796551.2336 | 100% |  |  | 961039 | [9 empty] | 588256 | 143297 | 731553 | 143297 | 731553
[12 empty] | 278 | 264 | 278 | 260 | 108.5714 | 73
[7 empty] | 0 | [15 empty] | 76.12%
[12 empty] | Frames |  | Doors |  | Completion
[12 empty] | Delivery (70%) | Installation(30%) | Delivery (70%) | Installation(30%) | Balance Works completion | Approvals
[6 empty] | 944457.1343 | 986039
955861.4803
Note on AB40: Himal Kosala: WIR for frame only
Note on AB41: Himal Kosala: Frame + Door
Note on AB44: Himal Kosala: Frame + Door
Note on AB45: Himal Kosala: Frame only
Note on AB52: Himal Kosala: Wrong WIR PII-AX-WR-L07-00026-03
Note on AB79: Himal Kosala: This not approved under mention WIR
Note on AB133: Himal Kosala: Rejected from WIR
Note on AB138: Himal Kosala: This door not included in WIR
Note on AB151: Himal Kosala: Wrong WIR
Note on M172: Himal Kosala: no supporting
Note on AB175: Himal Kosala: Rejected
Note on AB196: Himal Kosala: Rejected
Note on AB197: Himal Kosala: Rejected
Note on AB214: Himal Kosala: Rejected
Note on AB227: Himal Kosala: Rejected
Note on AB252: Himal Kosala: Rejected
Note on AB258: Himal Kosala: Rejected
Note on AB306: Himal Kosala: Rejected
Note on M339: Himal Kosala: no supporting

## Variations
DORCHESTER HOTEL | [9 empty] | INTERIM PAYMENT APPLICATION | 7 |  | 12
PACKAGE : SUPPLY & INSTALLATION OF FOH-BOH TIMBER DOORS (EXCL. IRONMONGERY SUPPLY) Balance Works | [9 empty] | PERIOD ENDING | 2023-02-28 |  | 20
VARIATIONS
Item | Description | Qty. | Unit | Rate | Amount | Percentage |  |  | Amount |  |  | Remarks
[5 empty] | AED | Previous Percentage | Current Percentage | Cumulative Percentage | Previous Amount | Current Amount | Cumulative Amount
VARIATION -1
1 | Change in Thickness of Frame at WM room | 25 | Nos | 395.148 | 9878.7 | 100% | 0% | 100% | 9878.7 | 0 | 9878.7 |  |  | 395.148
2 | Change in Thickness of Frame at Electric Room | 37 | Nos | 395.148 | 14620.476 | 100% | 0% | 100% | 14620.476 | 0 | 14620.476 |  |  |  | 0.62162
3 | Change in Thickness of Frame at Empower Meter Room | 22 | Nos | 613.2005 | 13490.411 | 100% | 0% | 100% | 13490.411 | 0 | 13490.411 |  |  | 613.2005 | 0.95455
VARIATION -3
1 | Door mark L02130 to FRONT OFFICE(900 x 2100mm H)(D-04a) | 1 | Nos. | 2084.23 | 2084.23 | 90% | 0% | 90% | 1875.807 | 0 | 1875.807
2 | Door mark L0299 to BOH OFFICE (900 x 2100mm H)(D-04j) | 1 | Nos. | 2084.23 | 2084.23 | 90% | 0% | 90% | 1875.807 | 0 | 1875.807
3 | Door mark L0233 to CONCEIGE CORRIDOR (900 x 2100mm H)(D-04j) | 1 | Nos. | 2084.23 | 2084.23 | 90% | 0% | 90% | 1875.807 | 0 | 1875.807
4 | Door mark L0363 to BOH PANTRY (900 x 2100mm H)(D-04j) | 1 | Nos. | 2084.23 | 2084.23 | 90% | 0% | 90% | 1875.807 | 0 | 1875.807
5 | Door mark L0364 to MEETING ROOM (1000 x 2400mm H)(D-04c) | 1 | Nos. | 2911.3054 | 2911.3054 | 70% | 0% | 70% | 2037.9138 | 0 | 2037.9138
6 | Door mark L0365 to ADA WC (800 x 2100mm H)(D-04a) | 1 | Nos. | 2335.7919 | 2335.7919 | 90% | 0% | 90% | 2102.2127 | 0 | 2102.2127
7 | Door mark L0366 to MALE WC (800 x 2100mm H)(D-04a) | 1 | Nos. | 2335.7919 | 2335.7919 | 90% | 0% | 90% | 2102.2127 | 0 | 2102.2127
8 | Door mark L0364 to STORE ROOM (1000 x 2400mm H)(D-04c) | 1 | Nos. | 2911.3054 | 2911.3054 | 90% | 0% | 90% | 2620.1749 | 0 | 2620.1749
VARIATION -4
1 | FTR Door at Level 06 | 1 | Nos. | 2718.9 | 2718.9 | 0% | 90% | 90% | 0 | 2447.01 | 2447.01
2 | FTR Door at Level 07 | 1 | Nos. | 2718.9 | 2718.9 | 0% | 90% | 90% | 0 | 2447.01 | 2447.01
3 | FTR Door at Level 08 | 1 | Nos. | 2718.9 | 2718.9 | 0% | 90% | 90% | 0 | 2447.01 | 2447.01
4 | FTR Door at Level 09 | 1 | Nos. | 2718.9 | 2718.9 | 0% | 90% | 90% | 0 | 2447.01 | 2447.01
5 | FTR Door at Level 18 | 1 | Nos. | 2718.9 | 2718.9 | 0% | 90% | 90% | 0 | 2447.01 | 2447.01
6 | FTR Door at Level 19 | 1 | Nos. | 2718.9 | 2718.9 | 0% | 90% | 90% | 0 | 2447.01 | 2447.01
7 | FTR Door at Level 20 | 1 | Nos. | 2718.9 | 2718.9 | 0% | 90% | 90% | 0 | 2447.01 | 2447.01
8 | FTR Door at Level 21 | 1 | Nos. | 2718.9 | 2718.9 | 0% | 90% | 90% | 0 | 2447.01 | 2447.01
9 | FTR Door at Level 22 | 1 | Nos. | 2718.9 | 2718.9 | 0% | 90% | 90% | 0 | 2447.01 | 2447.01
10 | FTR Door at Level 23 | 1 | Nos. | 2718.9 | 2718.9 | 0% | 90% | 90% | 0 | 2447.01 | 2447.01
[5 empty] | 84009.7015 |  |  |  | 54355.329 | 24470.1 | 78825.429
VARIATION -5
1 | General Manager Office Door at Level 3 | 1 | Nos. | 2931.66 | 2931.66 | 0% | 0% | 0% | 0 | 0 | 0
VARIATION -6
TIMBER DOORS
Supply and installation of level 6 & 7 Empower meter room Timber Doors (excluding ironmongery supply)
1 | Empower meter room at level 6 &7 | 2 | no. | 6704.5 | 13409 | 0% | 70% | 70% | 0 | 9386.3 | 9386.3
2 | Change in thikness of frame at Empower meter room | 2 | no. | 613.2 | 1226.4 | 0% | 70% | 70% | 0 | 858.48 | 858.48
VARIATION -7
Door Jambs
Fabrication Supply and installation of door jambs for level 04& 23 at residence as per the attached mark up drawing.
Level 04
1 | For L 04 Door Size-1200X2100 | 3 | no. | 1249.4543 | 3748.3628 | 0% | 0% | 0% | 0 | 0 | 0
2 | For L 04 Door Size-2000X2100 | 1 | no. | 1462.1904 | 1462.1904 | 0% | 0% | 0% | 0 | 0 | 0
Level 23
3 | For L 23 Door Size-950X2100 | 2 | no. | 1182.9742 | 2365.9484 | 0% | 0% | 0% | 0 | 0 | 0
Additional Doors
4 | At Level 04 Water Meter room Size-2600X2100 | 1 | no. | 1621.7425 | 1621.7425 | 0% | 0% | 0% | 0 | 0 | 0
5 | At Level 23 at Telephone(FTR) room Size-1200X2100 | 1 | no. | 1249.4543 | 1249.4543 | 0% | 0% | 0% | 0 | 0 | 0
[5 empty] | 28014.7584 |  |  |  | 0 | 10244.78 | 10244.78
| Page 1/2 |  |  |  | 84009.7015 |  |  |  | 54355.329 | 24470.1 | 78825.429
| Page 2/2 |  |  |  | 28014.7584 |  |  |  | 0 | 10244.78 | 10244.78
| TOTAL AMOUNT (in AED) |  |  |  | 112024.4599 |  |  |  | 54355.329 | 34714.88 | 89070.209
Note on I17: Himal Kosala: Please provide the supporting documents
Note on I18: Himal Kosala: Please provide the supporting documents
Note on I19: Himal Kosala: Please provide the supporting documents
Note on I20: Himal Kosala: Please provide the supporting documents
Note on I22: Himal Kosala: Please provide the supporting documents
Note on I23: Himal Kosala: Please provide the supporting documents
Note on I24: Himal Kosala: Please provide the supporting documents
Note on I27: Himal Kosala: Please provide the supporting documents
Note on I28: Himal Kosala: Please provide the supporting documents
Note on I29: Himal Kosala: Please provide the supporting documents
Note on I30: Himal Kosala: Please provide the supporting documents
Note on I31: Himal Kosala: Please provide the supporting documents
Note on I32: Himal Kosala: Please provide the supporting documents
Note on I33: Himal Kosala: Please provide the supporting documents
Note on I34: Himal Kosala: Please provide the supporting documents
Note on I35: Himal Kosala: Please provide the supporting documents
Note on I36: Himal Kosala: Please provide the supporting documents