## IPA -06 (hidden)
INTERIM PAYMENT APPLICATION NO. 06
Project Title | Dorchester Hotel & Residences Project, Dubai, UAE.
Employer | M/S Khansaheb Civil Engineering L.L.C.
Contractor | Polaris International Industries LLC
P.O No. | 201A22002/SW/ARM/175 |  | Date of Application | 2023-01-27
Dated | 2022-06-13 |  | Payment Application no. | 6
Quote Ref | Nil |  | Period upto | 2023-01-31
Contract Price: | 961039
Variations | 86941.3615 | [6 empty] | `
Revised Anticipated | 1047980.3615
WORK DONE | Value of Work Done- (Refer Appendix A) |  | Contract | Amount of Work Done | 586355.44
| a. Contract Works |  | 961039 | 666313 | 69.33% |  | 371564.29 | 18578.2145
b. Provisional Sums
c. Commercial Discount
| Contract Amount | A | 961039 | 666313 | 0.69333 | 145205.85
| Variations (refer attached BOQ ) |  |  |  |  | 89374
| 1. Variations Frame thickness |  | 86941.3615 | 54355.329 | 0.6252 | 10724.88
3. Variation Additional Doors -8 nos
4. Variation Additional Doors -10 nos
5. Variation Additional Doors -1 nos
8937.4
| Subtotal (Value of Workdone) |  | 1047980.3615 | 720668.329 | 0.68767 | 69711.72
ADVANCE PAYMENT | Addition
| Advance Payment on Contract Works |  | 10% | 96103.9
| Advance Recovery on Contract Works |  | 12% | -79957.56
| Advance Payable | B |  | 16146.34
DEDUCTIONS | Omission
| Retention on Work Done at 10% |  |  | -72066.8329
AMOUNT PAYABLE | Gross amount Payable A+B |  |  | 610392.5071
PREVIOUS CERTIFIED | [5 empty] | 96103.9
| Previous Amount Certified |  |  | -559004.17 | -254398.66 | 69741.36
88523.76
66309.98
NET AMOUNT | Net Payment Payable | (VAT Excluded) |  | 51388.3371 |  | 320679
Amount in Words: | Arab Emirates Dirhams One Hundred Nine Thousand Six Hundred Three and Fifty Six Fils Only |  |  |  |  | 372067.3371
Project Manager |  |  |  | Commercial Manager
S
51388.3371
0 | 0 | 0 | 5 | 1 | 3 | 8 | 8 | 3 | 3
|  |  | Fifty | One Thousand | Three Hundred | Eighty | Eight | and Thirty | Three fils only.
Arab Emirates Dirhams Fifty One Thousand Three Hundred Eighty Eight and Thirty Three fils only.
(ARAB EMIRATES DIRHAMS FIFTY ONE THOUSAND THREE HUNDRED EIGHTY EIGHT AND THIRTY THREE FILS ONLY.)
|  |  | Hotel Frame | 116 | 103 | 88.79% | 30% | 26.64%
|  |  | Hotel Leaf | 116 | 102 | 87.93% | 50% | 43.97%
|  |  | Residence Frame | 171 | 134 | 78.36% | 30% | 23.51%
|  |  | Residence Leaf | 171 | 128 | 74.85% | 50% | 37.43%

## Summary
No | Description | Previous | This Month | Cumulative
| Contract Works | 622273.75 | 47301.25 | 669575
| Variations | 26074.56 | 28280.769 | 54355.329
|  | 648348.31 | 75582.019 | 723930.329
| Advance Recovery (12%) | -77801.7972 | -9069.8423 | -86871.6395
|  | 570546.5128 | 66512.1767 | 637058.6895

## BOQ - Doors
DORCHESTER HOTEL | [21 empty] | INTERIM PAYMENT APPLICATION | 6 | [5 empty] | 12
PACKAGE : SUPPLY & INSTALLATION OF FOH-BOH TIMBER DOORS (EXCL. IRONMONGERY SUPPLY) Balance Works | [21 empty] | PERIOD ENDING | 2023-01-31 | [5 empty] | 20
BILL OF QUANTITIES
Item | Description | Qty. | Unit | Original BOQ Rate | % Certified | Amount Certified | Balance Amount with Original rate |  | Balance % to certified | Revised Rate | Balance amount as per revised rate | Frames |  | Doors |  | Completion |  | Percentage |  |  | Amount |  |  | Certified |  | MIR Ref. | WIR Ref. | Remarks
|  |  |  | AED |  | AED | AED |  |  | AED | AED | Delivery (70%) | Installation(30%) | Delivery (70%) | Installation(30%) | Balance Works completion | Approvals | Previous Percentage | Currnet Percentage | Cumulative Percentage | Previous Amount | Current Amount | Cumulative Amount | This Month | Cumulative
[12 empty] | 30% |  | 50% |  | 20%
[12 empty] | 21% | 9% | 35% | 15% | 14% | 6%
TIMBER DOORS
Supply and installation of FOH-BOH Timber Doors (excluding ironmongery supply)
1 | Door mark L0101 to CORRIDOR | 1 | Nos. | 2933.0215 | 0% | 0 | 2933.0215 | 100% | 100% | 3666.2769 | 3666.2769 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | [5 empty] | No Dwg
2 | Door mark L0103 to CORRIDOR | 1 | Nos. | 2038.381 | 0% | 0 | 2038.381 | 100% | 100% | 2547.9763 | 2547.9763 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | [5 empty] | No Dwg
3 | Door mark L0104 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2446.4812 | 0% | 0 | 2446.4812 | 100% | 100% | 3058.1016 | 3058.1016 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | [5 empty] | No Dwg
4 | Door mark L0106 to STAIR 08 | 1 | Nos. | 2933.0215 | 0% | 0 | 2933.0215 | 100% | 100% | 3666.2769 | 3666.2769 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | [5 empty] | No Dwg
5 | Door mark L0107 to CIRCULATION | 1 | Nos. | 2038.381 | 0% | 0 | 2038.381 | 100% | 100% | 2547.9763 | 2547.9763 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | [5 empty] | No Dwg
6 | Door mark L0111 to PLANT | 1 | Nos. | 3023.1215 | 0% | 0 | 3023.1215 | 100% | 100% | 3778.9019 | 3778.9019 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | [5 empty] | No Dwg
7 | Door mark L0112 to PLANT | 1 | Nos. | 3023.1215 | 0% | 0 | 3023.1215 | 100% | 100% | 3778.9019 | 3778.9019 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | [5 empty] | No Dwg
8 | Door mark L0116 to CIRCULATION | 1 | Nos. | 2052.161 | 0% | 0 | 2052.161 | 100% | 100% | 2565.2013 | 2565.2013 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | [5 empty] | No Dwg
9 | Door mark L0121 to AV CONTROL ROOM | 1 | Nos. | 1667.3808 | 0% | 0 | 1667.3808 | 100% | 100% | 2084.2261 | 2084.2261 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | [5 empty] | No Dwg
10 | Door mark L0123 to LIFT LOBBY | 1 | Nos. | 1667.3808 | 0% | 0 | 1667.3808 | 100% | 100% | 2084.2261 | 2084.2261 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | [5 empty] | No Dwg
11 | Door mark L02107 to CORRIDOR | 1 | Nos. | 2903.3415 |  | 0 | Rate Only | 100% |  | 3629.1768 | Rate Only
12 | Door mark L02108 to SECRET BAR PANTRY | 1 | Nos. | 3345.3617 |  | 0 | Rate Only | 100% |  | 4181.7021 | Rate Only
13 | Door mark L02122 to LOBBY LOUNGE SUPPORT | 1 | Nos. | 2708.3014 |  | 0 | Rate Only | 100% |  | 3385.3767 | Rate Only
14 | Door mark L0263 to HOTEL LOBBY | 1 | Nos. | 2903.3415 |  | 0 | Rate Only | 100% |  | 3629.1768 | Rate Only
15 | Door mark L0401 to STAIR-03 | 1 | Nos. | 3223.4616 | 0% | 0 | 3223.4616 | 100% | 100% | 4029.327 | 4029.327 | 21% | 0% | 35% | 0% | 0% | 0% | 0% | 56% | 56% | 0 | 2256.4231 | 2256.4231 | 2256.4231 | 2256.4231 | PII-AX-MR-ML-00025
16 | Door mark L0403 to FF LOBBY | 1 | Nos. | 3242.5416 | 0% | 0 | 3242.5416 | 100% | 100% | 4053.1771 | 4053.1771 | 21% | 0% | 35% | 0% | 0% | 0% | 0% | 56% | 56% | 0 | 2269.7792 | 2269.7792 | 2269.7792 | 2269.7792 | PII-AX-MR-ML-00025
17 | Door mark L0404 to WM ROOM | 1 | Nos. | 2044.741 | 0% | 0 | 2044.741 | 100% | 100% | 2555.9263 | 2555.9263 | 21% | 0% | 35% | 0% | 0% | 0% | 0% | 56% | 56% | 0 | 1431.3187 | 1431.3187 | 1431.3187 | 1431.3187 | PII-AX-MR-ML-00024 |  |  | MIR not approved
18 | Door mark L0405 to HOUSE KEEPING LOBBY | 1 | Nos. | 2215.4011 | 0% | 0 | 2215.4011 | 100% | 100% | 2769.2514 | 2769.2514 | 21% | 0% | 35% | 0% | 0% | 0% | 0% | 56% | 56% | 0 | 1550.7808 | 1550.7808 | 1550.7808 | 1550.7808 | PII-AX-MR-ML-00025
19 | Door mark L0408 to | 1 | Nos. | 0 |  | 0 | Excluded | 100% | 100% | Excluded | Excluded | [12 empty] | 0 | 0
20 | Door mark L0409 to STAIR-04 | 1 | Nos. | 3223.4616 | 0% | 0 | 3223.4616 | 100% | 100% | 4029.327 | 4029.327 | 21% | 0% | 35% | 0% | 0% | 0% | 0% | 56% | 56% | 0 | 2256.4231 | 2256.4231 | 2256.4231 | 2256.4231 | PII-AX-MR-ML-00025
21 | Door mark L0410 to STAIR 07 | 1 | Nos. | 2905.4615 |  | 0 | Rate Only | 100% | 100% | 3631.8268 | Rate Only | [13 empty] | 0
22 | Door mark L0415 to STAIR-08 | 1 | Nos. | 2905.4615 |  | 0 | Rate Only | 100% | 100% | 3631.8268 | Rate Only | [13 empty] | 0
23 | Door mark L0416 to HOUSEKEEPING LOBBY | 1 | Nos. | 1916.481 |  | 0 | Rate Only | 100% | 100% | 2395.6012 | Rate Only | [13 empty] | 0
24 | Door mark L0420 to FF LOBBY | 1 | Nos. | 1916.481 |  | 0 | Rate Only | 100% | 100% | 2395.6012 | Rate Only | [13 empty] | 0
25 | Door mark L0421 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 1916.481 |  | 0 | Rate Only | 100% | 100% | 2395.6012 | Rate Only | [13 empty] | 0
26 | Door mark L0455 to RESTAURANT BOH & ROOM SERVICE | 1 | Nos. | 2407.2612 |  | 0 | Rate Only | 100% | 100% | 3009.0765 | Rate Only | [13 empty] | 0
27 | Door mark L0474 to | 1 | Nos. | 0 |  | 0 | Excluded | 100% | 100% | 0 | Excluded | [13 empty] | 0
28 | Door mark L06R01 to STAIR-03 | 1 | Nos. | 3226.6416 | 50% | 1613.3208 | 1613.3208 | 100% | 50% | 3226.6416 | 1613.3208 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1468.1219 | 1.6133 | 1469.7353 | 1.6133 | 1469.7353 |  | PII-AX-WR-L06-00025
29 | Door mark L06R03 to FF LOBBY | 1 | Nos. | 3252.0816 | 50% | 1626.0408 | 1626.0408 | 100% | 50% | 3252.0816 | 1626.0408 | 21% | 9% | 35% | 15% | 12.6% | 0% | 85% | 7.6% | 92.6% | 1382.1347 | 123.5791 | 1505.7138 | 123.5791 | 1505.7138 | PII-AX-MR-ML-00013 | PII-AX-WR-L06-00025
30 | Door mark L06R05 to WM ROOM | 1 | Nos. | 2422.1012 | 0% | 0 | 2422.1012 | 100% | 100% | 3027.6265 | 3027.6265 | 21% | 9% | 35% |  |  | 0% | 65% | 0% | 65% | 1967.9572 | 0 | 1967.9572 | 0 | 1967.9572 | At Factory
31 | Door mark L06R08 to ELEC RM | 1 | Nos. | 2673.3214 | 0% | 0 | 2673.3214 | 100% | 100% | 3341.6517 | 3341.6517 | 21% | 9% | 35% | 0% | 0% | 0% | 30% | 35% | 65% | 1002.4955 | 1169.5781 | 2172.0736 | 1169.5781 | 2172.0736 |  |  |  | MIR no. by CJ
32 | Door mark L06R09 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.6416 | 50% | 1613.3208 | 1613.3208 | 100% | 50% | 3226.6416 | 1613.3208 | 21% | 9% | 35% | 15% | 12.6% | 0% | 85% | 7.6% | 92.6% | 1371.3227 | 122.6124 | 1493.9351 | 122.6124 | 1493.9351 | PII-AX-MR-ML-00014 | PII-AX-WR-L06-00025 | Frame was delivered during previous contract
33 | Door mark L06R12 to STAIR-04 | 1 | Nos. | 3226.6416 | 50% | 1613.3208 | 1613.3208 | 100% | 50% | 3226.6416 | 1613.3208 | 21% | 9% | 35% | 13.5% |  |  | 65% | 13.5% | 78.5% | 1048.6585 | 217.7983 | 1266.4568 | 217.7983 | 1266.4568 |  | PII-AX-WR-L06-00025 |  | WIR on Hold
34 | Door mark L06R14 to TELECOM | 1 | Nos. | Deleted as per Email dated 29 June 2022 | [19 empty] | 0 | 0
35 | Door mark L07H01 to STAIR-07 | 1 | Nos. | 3090.9616 | 50% | 1545.4808 | 1545.4808 | 100% | 50% | 3090.9616 | 1545.4808 | 21% | 9% | 35% | 15% | 14% | 6% | 91% | 9% | 100% | 1406.3875 | 139.0933 | 1545.4808 | 139.0933 | 1545.4808 |  | PII-AX-WR-L07-00080
36 | Door mark L07H03 to FF LOBBY | 1 | Nos. | 2422.1012 | 50% | 1211.0506 | 1211.0506 | 100% | 50% | 2422.1012 | 1211.0506 | 21% | 9% | 35% | 15% | 14% | 6% | 85% | 15% | 100% | 1029.393 | 181.6576 | 1211.0506 | 181.6576 | 1211.0506 |  | PII-AX-WR-L07-00080 |  | WIR by CJ
37 | Door mark L07H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1012 | 50% | 1211.0506 | 1211.0506 | 100% | 50% | 2422.1012 | 1211.0506 | 21% | 9% | 35% | 15% | 14% | 6% | 91% | 9% | 100% | 1102.0561 | 108.9946 | 1211.0506 | 108.9946 | 1211.0506 |  | PII-AX-WR-L07-00080
38 | Door mark L07H06 to STAIR-08 | 1 | Nos. | 3090.9616 | 50% | 1545.4808 | 1545.4808 | 100% | 50% | 3090.9616 | 1545.4808 | 21% | 9% | 35% | 15% | 14% | 6% | 91% | 9% | 100% | 1406.3875 | 139.0933 | 1545.4808 | 139.0933 | 1545.4808 |  | PII-AX-WR-L07-00080
39 | Door mark L07H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1012 | 50% | 1211.0506 | 1211.0506 | 100% | 50% | 2422.1012 | 1211.0506 | 21% | 9% | 35% | 15% | 14% | 6% | 91% | 9% | 100% | 1102.0561 | 108.9946 | 1211.0506 | 108.9946 | 1211.0506 |  | PII-AX-WR-L07-00080
40 | Door mark L07R01 to STAIR-03 | 1 | Nos. | 3226.6416 | 60% | 1935.985 | 1290.6567 | 100% | 40% | 3226.6416 | 1290.6567 | 21% | 9% | 35% | 15% | 14% | 6% | 91% | 9% | 100% | 1174.4976 | 116.1591 | 1290.6567 | 116.1591 | 1290.6567 |  | PII-AX-WR-L07-00080 | Frame was delivered during previous contract
41 | Door mark L07R03 to FF LOBBY | 1 | Nos. | 3252.0816 | 50% | 1626.0408 | 1626.0408 | 100% | 50% | 3252.0816 | 1626.0408 | 21% | 9% | 35% | 15% | 12.6% | 0% | 91% | 1.6% | 92.6% | 1479.6972 | 26.0167 | 1505.7138 | 26.0167 | 1505.7138 | PII-AX-MR-ML-00013 | PII-AX-WR-L07-00026-03
42 | Door mark L07R05 to WM ROOM | 1 | Nos. | 2422.1012 | 0% | 0 | 2422.1012 | 100% | 100% | 3027.6265 | 3027.6265 | 21% | 9% | 35% | 0% | 0% | 0% | 30% | 35% | 65% | 908.288 | 1059.6693 | 1967.9572 | 1059.6693 | 1967.9572 | PII-AX-MR-ML-00025
43 | Door mark L07R08 to ELEC RM | 1 | Nos. | 2673.3214 | 0% | 0 | 2673.3214 | 100% | 100% | 3341.6517 | 3341.6517 | 21% | 9% | 35% | 0% | 0% | 0% | 65% | 0% | 65% | 2172.0736 | 0 | 2172.0736 | 0 | 2172.0736
44 | Door mark L07R09 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.6416 | 50% | 1613.3208 | 1613.3208 | 100% | 50% | 3226.6416 | 1613.3208 | 21% | 9% | 35% | 15% | 12.6% | 0% | 91% | 1.6% | 92.6% | 1468.1219 | 25.8131 | 1493.9351 | 25.8131 | 1493.9351 | PII-AX-MR-ML-00014 | PII-AX-WR-L07-00026 | Frame was delivered during previous contract
45 | Door mark L07R12 to STAIR-04 | 1 | Nos. | 3226.6416 | 50% | 1613.3208 | 1613.3208 | 100% | 50% | 3226.6416 | 1613.3208 | 21% | 9% | 35% | 15% | 12.6% | 0% | 91% | 1.6% | 92.6% | 1468.1219 | 25.8131 | 1493.9351 | 25.8131 | 1493.9351 |  | PII-AX-WR-L07-00026
| To Collection Dhs. |  |  |  |  | 19978.7841 | 67296.3601 | 100% |  | 0 | 79287.0862 | [9 empty] | 22957.771 | 13331.2107 | 36288.9817 | 13331.2107 | 36288.9817
| TIMBER DOORS (CONT'D) | [6 empty] | 100%
100%
| Supply and installation of FOH-BOH Timber Doors (excluding ironmongery supply) | [6 empty] | 100%
100%
46 | Door mark L07R14 to TELECOM | 1 | Nos. | Deleted as per Email dated 29 June 2022
47 | Door mark L08H01 to STAIR-07 | 1 | Nos. | 3090.96 | 66% | 2040.0336 | 1050.9264 | 100% | 34% | 3090.96 | 1050.9264 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 956.343 | 1.0509 | 957.394 | 1.0509 | 957.394 |  | PII-AX-WR-L08-00054 | Frame was delivered during previous contract
48 | Door mark L08H03 to FF LOBBY | 1 | Nos. | 2422.1 | 50% | 1211.05 | 1211.05 | 100% | 50% | 2422.1 | 1211.05 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1102.0555 | 1.211 | 1103.2665 | 1.211 | 1103.2665 |  | PII-AX-WR-L08-00054
49 | Door mark L08H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 66% | 1598.586 | 823.514 | 100% | 34% | 2422.1 | 823.514 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 749.3977 | 0.82351 | 750.2213 | 0.82351 | 750.2213 |  | PII-AX-WR-L08-00054 | Frame was delivered during previous contract
50 | Door mark L08H06 to STAIR-08 | 1 | Nos. | 3090.96 | 50% | 1545.48 | 1545.48 | 100% | 50% | 3090.96 | 1545.48 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1406.3868 | 1.5455 | 1407.9323 | 1.5455 | 1407.9323 | PII-AX-MR-ML-00014 | PII-AX-WR-L08-00054
51 | Door mark L08H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 66% | 1598.586 | 823.514 | 100% | 34% | 2422.1 | 823.514 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 749.3977 | 0.82351 | 750.2213 | 0.82351 | 750.2213 |  | PII-AX-WR-L08-00054
52 | Door mark L08R01 to STAIR-03 | 1 | Nos. | 3226.64 | 50% | 1613.32 | 1613.32 | 100% | 50% | 3226.64 | 1613.32 | 21% | 9% | 35% |  |  | 0% | 65% | 0% | 65% | 1048.658 | 0 | 1048.658 | 0 | 1048.658
53 | Door mark L08R03 to FF LOBBY | 1 | Nos. | 3252.08 | 50% | 1626.04 | 1626.04 | 100% | 50% | 3252.08 | 1626.04 | 21% | 9% | 35% |  |  | 0% | 65% | 0% | 65% | 1056.926 | 0 | 1056.926 | 0 | 1056.926 | PII-AX-MR-ML-00013
54 | Door mark L08R04 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% |  |  | 0% | 65% | 0% | 65% | 4357.925 | 0 | 4357.925 | 0 | 4357.925
55 | Door mark L08R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% |  |  | 0% | 65% | 0% | 65% | 1967.9562 | 0 | 1967.9562 | 0 | 1967.9562
56 | Door mark L08R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 9% | 35% |  |  | 0% | 65% | 0% | 65% | 2172.0725 | 0 | 2172.0725 | 0 | 2172.0725
57 | Door mark L08R09 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 50% | 1613.32 | 1613.32 | 100% | 50% | 3226.64 | 1613.32 | 21% |  | 35% |  |  | 0% | 56% | 0% | 56% | 903.4592 | 0 | 903.4592 | 0 | 903.4592 | PII-AX-MR-ML-00014
58 | Door mark L08R12 to STAIR-04 | 1 | Nos. | 3226.64 | 50% | 1613.32 | 1613.32 | 100% | 50% | 3226.64 | 1613.32 | 21% |  | 35% |  |  | 0% | 56% | 0% | 56% | 903.4592 | 0 | 903.4592 | 0 | 903.4592
59 | Door mark L08R14 to TELECOM | 1 | Nos. | Deleted as per Email dated 29 June 2022 | [19 empty] | 0 | 0
60 | Door mark L09H01 to STAIR-07 | 1 | Nos. | 3090.96 | 50% | 1545.48 | 1545.48 | 100% | 50% | 3090.96 | 1545.48 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1406.3868 | 1.5455 | 1407.9323 | 1.5455 | 1407.9323 | PII-AX-MR-ML-00014 | PII-AX-WR-L09-00055 | Frame was delivered during previous contract
61 | Door mark L09H03 to FF LOBBY | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 2755.1387 | 3.0276 | 2758.1664 | 3.0276 | 2758.1664 |  | PII-AX-WR-L09-00055
62 | Door mark L09H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 50% | 1211.05 | 1211.05 | 100% | 50% | 2422.1 | 1211.05 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1102.0555 | 1.211 | 1103.2665 | 1.211 | 1103.2665 |  | PII-AX-WR-L09-00055 | Frame was delivered during previous contract
63 | Door mark L09H06 to STAIR-08 | 1 | Nos. | 3090.96 | 50% | 1545.48 | 1545.48 | 100% | 50% | 3090.96 | 1545.48 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1406.3868 | 1.5455 | 1407.9323 | 1.5455 | 1407.9323 | PII-AX-MR-ML-00014 | PII-AX-WR-L09-00055
64 | Door mark L09H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 50% | 1211.05 | 1211.05 | 100% | 50% | 2422.1 | 1211.05 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1102.0555 | 1.211 | 1103.2665 | 1.211 | 1103.2665 |  | PII-AX-WR-L09-00055
65 | Door mark L09R01 to STAIR-03 | 1 | Nos. | 3226.64 | 50% | 1613.32 | 1613.32 | 100% | 50% | 3226.64 | 1613.32 | 21% | 9% | 35% | 15% | 12.6% | 0% | 91% | 1.6% | 92.6% | 1468.1212 | 25.8131 | 1493.9343 | 25.8131 | 1493.9343 |  | PII-AX-WR-L09-00027
66 | Door mark L09R03 to FF LOBBY | 1 | Nos. | 3252.08 | 50% | 1626.04 | 1626.04 | 100% | 50% | 3252.08 | 1626.04 | 21% | 9% | 35% | 15% | 12.6% | 0% | 91% | 1.6% | 92.6% | 1479.6964 | 26.0166 | 1505.713 | 26.0166 | 1505.713 | PII-AX-MR-ML-00013 PII-AX-MR-ML-00015 | PII-AX-WR-L09-00027
67 | Door mark L09R04 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 0% | 14% | 6% | 85% | 0% | 85% | 5698.825 | 0 | 5698.825 | 0 | 5698.825
68 | Door mark L09R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | MIR by CJ
69 | Door mark L09R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 0% | 35% | 0% | 0% | 0% | 56% | 0% | 56% | 1871.324 | 0 | 1871.324 | 0 | 1871.324 | Door and frame delivered
70 | Door mark L09R09 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 66% | 2129.5824 | 1097.0576 | 100% | 34% | 3226.64 | 1097.0576 | 21% | 9% | 35% | 15% | 12.6% | 0% | 91% | 1.6% | 92.6% | 998.3224 | 17.5529 | 1015.8753 | 17.5529 | 1015.8753 | PII-AX-MR-ML-00014 | PII-AX-WR-L09-00027 | Frame was delivered during previous contract
71 | Door mark L09R12 to STAIR-04 | 1 | Nos. | 3226.64 | 50% | 1613.32 | 1613.32 | 100% | 50% | 3226.64 | 1613.32 | 21% | 9% | 35% | 15% | 12.6% | 0% | 91% | 1.6% | 92.6% | 1468.1212 | 25.8131 | 1493.9343 | 25.8131 | 1493.9343 |  | PII-AX-WR-L09-00027
72 | Door mark L09R14 to TELECOM | 1 | Nos. | Deleted as per Email dated 29 June 2022 | [19 empty] | 0 | 0
73 | Door mark L10H01 to STAIR-07 | 1 | Nos. | 3090.96 | 60% | 1854.576 | 1236.384 | 100% | 40% | 3090.96 | 1236.384 | 21% | 9% | 35% | 15% | 14% | 0% | 91% | 3% | 94% | 1125.1094 | 37.0915 | 1162.201 | 37.0915 | 1162.201 |  | PII-AX-WR-L10-00092 | Frame was delivered during previous contract
74 | Door mark L10H03 to FF LOBBY | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 14% | 0% | 91% | 3% | 94% | 2755.1387 | 90.8288 | 2845.9675 | 90.8288 | 2845.9675 |  | PII-AX-WR-L10-00092
75 | Door mark L10H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 50% | 1211.05 | 1211.05 | 100% | 50% | 2422.1 | 1211.05 | 21% | 9% | 35% | 15% | 14% | 0% | 91% | 3% | 94% | 1102.0555 | 36.3315 | 1138.387 | 36.3315 | 1138.387 |  | PII-AX-WR-L10-00092 | Frame was delivered during previous contract
76 | Door mark L10H06 to STAIR-08 | 1 | Nos. | 3090.96 | 50% | 1545.48 | 1545.48 | 100% | 50% | 3090.96 | 1545.48 | 21% | 9% | 35% | 15% | 14% | 0% | 91% | 3% | 94% | 1406.3868 | 46.3644 | 1452.7512 | 46.3644 | 1452.7512 | PII-AX-MR-ML-00014 | PII-AX-WR-L10-00092
77 | Door mark L10H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 50% | 1211.05 | 1211.05 | 100% | 50% | 2422.1 | 1211.05 | 21% | 9% | 35% | 15% | 14% | 0% | 85% | 9% | 94% | 1029.3925 | 108.9945 | 1138.387 | 108.9945 | 1138.387 |  | PII-AX-WR-L10-00092
78 | Door mark L10R01 to STAIR-03 | 1 | Nos. | 3226.64 | 50% | 1613.32 | 1613.32 | 100% | 50% | 3226.64 | 1613.32 | 21% | 9% | 35% | 15% | 12.6% | 0% | 91% | 1.6% | 92.6% | 1468.1212 | 25.8131 | 1493.9343 | 25.8131 | 1493.9343 |  | PII-AX-WR-L10-00028 | Frame was delivered during previous contract
79 | Door mark L10R03 to FF LOBBY | 1 | Nos. | 3252.08 | 50% | 1626.04 | 1626.04 | 100% | 50% | 3252.08 | 1626.04 | 21% | 9% | 35% | 15% | 12.6% | 0% | 91% | 1.6% | 92.6% | 1479.6964 | 26.0166 | 1505.713 | 26.0166 | 1505.713 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013 | PII-AX-WR-L10-00028-2
80 | Door mark L10R04 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 0% | 0% | 91% | -11% | 80% | 6101.095 | -737.495 | 5363.6 | 0 | 6101.095
81 | Door mark L10R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | MIR by CJ
82 | Door mark L10R09 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 0% | 35% |  | 0% | 0% | 56% | 0% | 56% | 1871.324 | 0 | 1871.324 | 0 | 1871.324
83 | Door mark L10R10 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 50% | 1613.32 | 1613.32 | 100% | 50% | 3226.64 | 1613.32 | 21% | 9% | 35% | 15% | 12.6% | 0% | 91% | 1.6% | 92.6% | 1468.1212 | 25.8131 | 1493.9343 | 25.8131 | 1493.9343 | PII-AX-MR-ML-00014 | PII-AX-WR-L10-00028 | Frame was delivered during previous contract
84 | Door mark L10R13 to STAIR-04 | 1 | Nos. | 3226.64 | 50% | 1613.32 | 1613.32 | 100% | 50% | 3226.64 | 1613.32 | 21% | 9% | 35% | 15% | 12.6% | 0% | 91% | 1.6% | 92.6% | 1468.1212 | 25.8131 | 1493.9343 | 25.8131 | 1493.9343 |  | PII-AX-WR-L10-00028
85 | Door mark L11H01 to STAIR-07 | 1 | Nos. | 3090.96 | 50% | 1545.48 | 1545.48 | 100% | 50% | 3090.96 | 1545.48 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1406.3868 | 1.5455 | 1407.9323 | 1.5455 | 1407.9323 |  | PII-AX-WR-L11-00057 | Frame was delivered during previous contract | PII-AX-WR-L10-00057
86 | Door mark L11H03 to FF LOBBY | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 2755.1387 | 3.0276 | 2758.1664 | 3.0276 | 2758.1664 |  | PII-AX-WR-L11-00057
87 | Door mark L11H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 50% | 1211.05 | 1211.05 | 100% | 50% | 2422.1 | 1211.05 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1102.0555 | 1.211 | 1103.2665 | 1.211 | 1103.2665 |  | PII-AX-WR-L11-00057 | Frame was delivered during previous contract
88 | Door mark L11H06 to STAIR-08 | 1 | Nos. | 3090.96 | 50% | 1545.48 | 1545.48 | 100% | 50% | 3090.96 | 1545.48 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1406.3868 | 1.5455 | 1407.9323 | 1.5455 | 1407.9323 | PII-AX-MR-ML-00014 | PII-AX-WR-L11-00057
[8 empty] | 100% | [15 empty] | 0 | 0
[8 empty] | 100% | [15 empty] | 0 | 0
| To Collection Dhs. |  |  |  |  | 43545.224 | 77998.616 | 100% |  |  | 87659.456 | [9 empty] | 66075.0004 | -197.9077 | 65877.0926 | 539.5873 | 66614.5876
| TIMBER DOORS (CONT'D) | [6 empty] | 100% | [15 empty] | 0 | 0
89 | Door mark L11H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 50% | 1211.05 | 1211.05 | 100% | 50% | 2422.1 | 1211.05 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1102.0555 | 1.211 | 1103.2665 | 1.211 | 1103.2665 |  | PII-AX-WR-L11-00057 | Frame was delivered during previous contract
90 | Door mark L11R01 to STAIR-03 | 1 | Nos. | 3226.64 | 50% | 1613.32 | 1613.32 | 100% | 50% | 3226.64 | 1613.32 | 21% | 9% | 35% | 15% | 12.6% | 0% | 91% | 1.6% | 92.6% | 1468.1212 | 25.8131 | 1493.9343 | 25.8131 | 1493.9343 |  | PII-AX-WR-L11-00029
91 | Door mark L11R03 to FF LOBBY | 1 | Nos. | 3252.08 | 50% | 1626.04 | 1626.04 | 100% | 50% | 3252.08 | 1626.04 | 21% | 9% | 35% | 15% | 12.6% | 0% | 91% | 1.6% | 92.6% | 1479.6964 | 26.0166 | 1505.713 | 26.0166 | 1505.713 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013 | PII-AX-WR-L11-00045/ PII-AX-WR-L11-00029
92 | Door mark L11R04 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 0% | 35% | 0% | 0% | 0% | 56% | 0% | 56% | 3754.52 | 0 | 3754.52 | 0 | 3754.52 |  |  |  | WIR by CJ
93 | Door mark L11R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | MIR by CJ
94 | Door mark L11R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 0% | 35% | 0% | 0% | 0% | 56% | 0% | 56% | 1871.324 | 0 | 1871.324 | 0 | 1871.324
95 | Door mark L11R10 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 50% | 1613.32 | 1613.32 | 100% | 50% | 3226.64 | 1613.32 | 21% | 9% | 35% | 15% | 12.6% | 0% | 91% | 1.6% | 92.6% | 1468.1212 | 25.8131 | 1493.9343 | 25.8131 | 1493.9343 | PII-AX-MR-ML-00014 | PII-AX-WR-L11-00029 | Frame was delivered during previous contract
96 | Door mark L11R13 to STAIR-04 | 1 | Nos. | 3226.64 | 50% | 1613.32 | 1613.32 | 100% | 50% | 3226.64 | 1613.32 | 21% | 9% | 35% | 15% | 12.6% | 0% | 91% | 1.6% | 92.6% | 1468.1212 | 25.8131 | 1493.9343 | 25.8131 | 1493.9343 |  | PII-AX-WR-L11-00029
97 | Door mark L12H01 to STAIR-07 | 1 | Nos. | 3090.96 | 50% | 1545.48 | 1545.48 | 100% | 50% | 3090.96 | 1545.48 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1406.3868 | 1.5455 | 1407.9323 | 1.5455 | 1407.9323 |  | PII-AX-WR-L12-00058 | Frame was deliverd during previous contract
98 | Door mark L12H03 to FF LOBBY | 1 | Nos. | 2422.1 | 50% | 1211.05 | 1211.05 | 100% | 50% | 2422.1 | 1211.05 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1102.0555 | 1.211 | 1103.2665 | 1.211 | 1103.2665 |  | PII-AX-WR-L12-00058
99 | Door mark L12H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 2755.1387 | 3.0276 | 2758.1664 | 3.0276 | 2758.1664 |  | PII-AX-WR-L12-00058
100 | Door mark L12H06 to STAIR-08 | 1 | Nos. | 3090.96 | 50% | 1545.48 | 1545.48 | 100% | 50% | 3090.96 | 1545.48 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1406.3868 | 1.5455 | 1407.9323 | 1.5455 | 1407.9323 | PII-AX-MR-ML-00014 | PII-AX-WR-L12-00058 | Frame was deliverd during previous contract
101 | Door mark L12H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 50% | 1211.05 | 1211.05 | 100% | 50% | 2422.1 | 1211.05 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1102.0555 | 1.211 | 1103.2665 | 1.211 | 1103.2665 | PII-AX-MR-ML-00014 | PII-AX-WR-L12-00058
102 | Door mark L12H11 to STAIR-06 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 85% | 6.1% | 91.1% | 3284.145 | 235.6857 | 3519.8307 | 235.6857 | 3519.8307 | PII-AX-MR-ML-00072 | PII-AX-WR-ML-00072
103 | Door mark L12R01 to STAIR-03 | 1 | Nos. | 3226.64 | 66% | 2129.5824 | 1097.0576 | 100% | 34% | 3226.64 | 1097.0576 | 21% | 9% | 35% | 15% | 12.6% | 0% | 91% | 1.6% | 92.6% | 998.3224 | 17.5529 | 1015.8753 | 17.5529 | 1015.8753 | PII-AX-MR-ML-00014 | PII-AX-WR-L12-00030
104 | Door mark L12R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 15% | 12.6% | 0% | 91% | 1.6% | 92.6% | 3699.241 | 65.0416 | 3764.2826 | 65.0416 | 3764.2826 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013 | PII-AX-MR-ML-00013
105 | Door mark L12R04 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 14% | 0% | 91% | 3% | 94% | 6101.095 | 201.135 | 6302.23 | 201.135 | 6302.23
106 | Door mark L12R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | MIR by CJ
107 | Door mark L12R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 0% | 35% | 0% | 0% | 0% | 56% | 0% | 56% | 1871.324 | 0 | 1871.324 | 0 | 1871.324
108 | Door mark L12R10 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 50% | 1613.32 | 1613.32 | 100% | 50% | 3226.64 | 1613.32 | 21% | 9% | 35% | 15% | 14% | 6% | 91% | 9% | 100% | 1468.1212 | 145.1988 | 1613.32 | 145.1988 | 1613.32 | PII-AX-MR-ML-00014 | PII-AX-WR-L12-00091 | Frame was delivered during previous contract
109 | Door mark L12R13 to STAIR-04 | 1 | Nos. | 3226.64 | 50% | 1613.32 | 1613.32 | 100% | 50% | 3226.64 | 1613.32 | 21% | 9% | 35% | 15% | 14% | 6% | 91% | 9% | 100% | 1468.1212 | 145.1988 | 1613.32 | 145.1988 | 1613.32 |  | PII-AX-WR-L12-00091
110 | Door mark L14H01 to STAIR-07 | 1 | Nos. | 3090.96 | 50% | 1545.48 | 1545.48 | 100% | 50% | 3090.96 | 1545.48 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1406.3868 | 1.5455 | 1407.9323 | 1.5455 | 1407.9323 |  | PII-AX-WR-L13-00059 | Frame was delivered during previous contract
111 | Door mark L14H03 to FF LOBBY | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 2755.1387 | 3.0276 | 2758.1664 | 3.0276 | 2758.1664 | PII-AX-MR-ML-00016 | PII-AX-WR-L13-00059
112 | Door mark L14H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 50% | 1211.05 | 1211.05 | 100% | 50% | 2422.1 | 1211.05 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1102.0555 | 1.211 | 1103.2665 | 1.211 | 1103.2665 |  | PII-AX-WR-L13-00059 | Frame was delivered during previous contract
113 | Door mark L14H06 to STAIR-08 | 1 | Nos. | 3090.96 | 50% | 1545.48 | 1545.48 | 100% | 50% | 3090.96 | 1545.48 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1406.3868 | 1.5455 | 1407.9323 | 1.5455 | 1407.9323 |  | PII-AX-WR-L13-00059
114 | Door mark L14H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 50% | 1211.05 | 1211.05 | 100% | 50% | 2422.1 | 1211.05 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1102.0555 | 1.211 | 1103.2665 | 1.211 | 1103.2665 |  | PII-AX-WR-L13-00059 | Frame was delivered during previous contract
115 | Door mark L14H11 to STAIR-06 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 12.6% | 0% | 85% | 7.6% | 92.6% | 3284.145 | 293.6412 | 3577.7862 | 293.6412 | 3577.7862 | PII-AX-MR-ML-00072 | PII-AX-WR-L13-00059
116 | Door mark L14R01 to STAIR-03 | 1 | Nos. | 3226.64 | 50% | 1613.32 | 1613.32 | 100% | 50% | 3226.64 | 1613.32 | 21% | 9% | 35% | 15% | 12.6% | 0% | 91% | 1.6% | 92.6% | 1468.1212 | 25.8131 | 1493.9343 | 25.8131 | 1493.9343 |  | PII-AX-WR-L14-00031 | Frame was deliverd during previous contract
117 | Door mark L14R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 15% | 14% | 6% | 91% | 9% | 100% | 3699.241 | 365.859 | 4065.1 | 365.859 | 4065.1 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013 | PII-AX-MR-ML-00013
118 | Door mark L14R04 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 14% | 0% | 91% | 3% | 94% | 6101.095 | 201.135 | 6302.23 | 201.135 | 6302.23
119 | Door mark L14R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | MIR by CJ
120 | Door mark L14R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 0% | 35% | 0% | 0% | 0% | 61% | -5% | 56% | 2038.4065 | -167.0825 | 1871.324 | 0 | 2038.4065
121 | Door mark L14R10 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 50% | 1613.32 | 1613.32 | 100% | 50% | 3226.64 | 1613.32 | 21% | 9% | 35% | 15% | 12.6% | 0% | 91% | 1.6% | 92.6% | 1468.1212 | 25.8131 | 1493.9343 | 25.8131 | 1493.9343 | PII-AX-MR-ML-00014 | PII-AX-WR-L14-00031 | Frame was deliverd during previous contract
122 | Door mark L14R13 to STAIR-04 | 1 | Nos. | 3226.64 | 60% | 1935.984 | 1290.656 | 100% | 40% | 3226.64 | 1290.656 | 21% | 9% | 35% | 15% | 12.6% | 0% | 91% | 1.6% | 92.6% | 1174.497 | 20.6505 | 1195.1475 | 20.6505 | 1195.1475 |  | PII-AX-WR-L14-00031
123 | Door mark L15H01 to STAIR-07 | 1 | Nos. | 3090.96 | 60% | 1854.576 | 1236.384 | 100% | 40% | 3090.96 | 1236.384 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1125.1094 | 1.2364 | 1126.3458 | 1.2364 | 1126.3458 |  | PII-AX-WR-L14-00060
124 | Door mark L15H03 to FF LOBBY | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 2755.1387 | 3.0276 | 2758.1664 | 3.0276 | 2758.1664 |  | PII-AX-WR-L14-00060
125 | Door mark L15H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 60% | 1453.26 | 968.84 | 100% | 40% | 2422.1 | 968.84 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 881.6444 | 0.96884 | 882.6132 | 0.96884 | 882.6132 |  | PII-AX-WR-L14-00060 | Frame was deliverd during previous contract
126 | Door mark L15H06 to STAIR-08 | 1 | Nos. | 3090.96 | 60% | 1854.576 | 1236.384 | 100% | 40% | 3090.96 | 1236.384 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1125.1094 | 1.2364 | 1126.3458 | 1.2364 | 1126.3458 |  | PII-AX-WR-L14-00060
127 | Door mark L15H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 60% | 1453.26 | 968.84 | 100% | 40% | 2422.1 | 968.84 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 881.6444 | 0.96884 | 882.6132 | 0.96884 | 882.6132 | PII-AX-MR-ML-00014 | PII-AX-WR-L14-00060 | Frame was deliverd during previous contract
128 | Door mark L15H11 to STAIR-06 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 65% | 26.1% | 91.1% | 2511.405 | 1008.4257 | 3519.8307 | 1008.4257 | 3519.8307 | PII-AX-MR-ML-00072 | PII-AX-WR-ML-00072
129 | Door mark L15R01 to STAIR-03 | 1 | Nos. | 3226.64 | 60% | 1935.984 | 1290.656 | 100% | 40% | 3226.64 | 1290.656 | 21% | 9% | 35% | 15% | 12.6% | 0% | 80% | 12.6% | 92.6% | 1032.5248 | 162.6227 | 1195.1475 | 162.6227 | 1195.1475 |  | PII-AX-WR-L14-00074
130 | Door mark L15R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 3252.08 | 813.02 | 4065.1 | 813.02 | 4065.1 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013 | PII-AX-WR-L14-00097
131 | Door mark L15R04 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 12.6% | 0% | 80% | 12.6% | 92.6% | 5363.6 | 844.767 | 6208.367 | 844.767 | 6208.367 |  | PII-AX-WR-L14-00074
132 | Door mark L15R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | MIR by CJ
133 | Door mark L15R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 9% | 35% | 15% | 14% | 6% | 56% | 44% | 100% | 1871.324 | 1470.326 | 3341.65 | 1470.326 | 3341.65 |  | PII-AX-WR-L14-00097
134 | Door mark L15R10 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 60% | 1935.984 | 1290.656 | 100% | 40% | 3226.64 | 1290.656 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 1032.5248 | 258.1312 | 1290.656 | 258.1312 | 1290.656 | PII-AX-MR-ML-00014 | PII-AX-WR-L14-00097
100%
[7 empty] | 0 | 100%
| To Collection Dhs. |  |  |  |  | 39709.6564 | 102667.4236 | 100% |  | 0 | 119700.2986 | [9 empty] | 88112.1079 | 6262.1213 | 94374.2292 | 6429.2038 | 94541.3117
| TIMBER DOORS (CONT'D) | [6 empty] | 100%
135 | Door mark L15R13 to STAIR-04 | 1 | Nos. | 3226.64 | 60% | 1935.984 | 1290.656 | 100% | 40% | 3226.64 | 1290.656 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 1032.5248 | 258.1312 | 1290.656 | 258.1312 | 1290.656 |  | PII-AX-WR-L14-00097
136 | Door mark L16H01 to STAIR-07 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 3515.967 | 3.8637 | 3519.8307 | 3.8637 | 3519.8307 |  | PII-AX-WR-L15-00061
137 | Door mark L16H03 to FF LOBBY | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 2755.1387 | 3.0276 | 2758.1664 | 3.0276 | 2758.1664 |  | PII-AX-WR-L15-00061
138 | Door mark L16H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 60% | 1453.26 | 968.84 | 100% | 40% | 2422.1 | 968.84 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 881.6444 | 0.96884 | 882.6132 | 0.96884 | 882.6132 | PII-AX-MR-ML-00014 | PII-AX-WR-L15-00061 | Frame was delivered during previous contract
139 | Door mark L16H06 to STAIR-08 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 3515.967 | 3.8637 | 3519.8307 | 3.8637 | 3519.8307 |  | PII-AX-WR-L15-00061
140 | Door mark L16H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 60% | 1453.26 | 968.84 | 100% | 40% | 2422.1 | 968.84 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 881.6444 | 0.96884 | 882.6132 | 0.96884 | 882.6132 |  | PII-AX-WR-L15-00061
141 | Door mark L16H11 to STAIR-06 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 65% | 26.1% | 91.1% | 2511.405 | 1008.4257 | 3519.8307 | 1008.4257 | 3519.8307 | PII-AX-MR-ML-00072 | PII-AX-WR-ML-00072
142 | Door mark L16R01 to STAIR-03 | 1 | Nos. | 3226.64 | 60% | 1935.984 | 1290.656 | 100% | 40% | 3226.64 | 1290.656 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 1032.5248 | 258.1312 | 1290.656 | 258.1312 | 1290.656 |  | PII-AX-WR-L15-00098 | Frame was delivered during previous contract
143 | Door mark L16R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 3252.08 | 813.02 | 4065.1 | 813.02 | 4065.1 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013 | PII-AX-WR-L15-00098
144 | Door mark L16R04 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 12.6% | 0% | 80% | 12.6% | 92.6% | 5363.6 | 844.767 | 6208.367 | 844.767 | 6208.367 |  | PII-AX-WR-L15-00075
145 | Door mark L16R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | MIR by CJ
146 | Door mark L16R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 9% | 35% | 15% | 14% | 6% | 56% | 44% | 100% | 1871.324 | 1470.326 | 3341.65 | 1470.326 | 3341.65 |  | PII-AX-WR-L15-00098
147 | Door mark L16R10 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 60% | 1935.984 | 1290.656 | 100% | 40% | 3226.64 | 1290.656 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 1032.5248 | 258.1312 | 1290.656 | 258.1312 | 1290.656 | PII-AX-MR-ML-00014 | PII-AX-WR-L15-00098 | Frame was delivered during previous contract
148 | Door mark L16R13 to STAIR-04 | 1 | Nos. | 3226.64 | 60% | 1935.984 | 1290.656 | 100% | 40% | 3226.64 | 1290.656 | 21% | 9% | 35% | 15% | 14% | 0% | 80% | 14% | 94% | 1032.5248 | 180.6918 | 1213.2166 | 180.6918 | 1213.2166 |  | PII-AX-WR-L15-00098
149 | Door mark L17H01 to STAIR-07 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 3515.967 | 3.8637 | 3519.8307 | 3.8637 | 3519.8307 |  | PII-AX-WR-L16-00062
150 | Door mark L17H03 to FF LOBBY | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 2755.1387 | 3.0276 | 2758.1664 | 3.0276 | 2758.1664 |  | PII-AX-WR-L16-00062
151 | Door mark L17H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 60% | 1453.26 | 968.84 | 100% | 40% | 2422.1 | 968.84 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 881.6444 | 0.96884 | 882.6132 | 0.96884 | 882.6132 |  | PII-AX-WR-L16-00062
152 | Door mark L17H06 to STAIR-08 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 3515.967 | 3.8637 | 3519.8307 | 3.8637 | 3519.8307 |  | PII-AX-WR-L16-00062
153 | Door mark L17H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 60% | 1453.26 | 968.84 | 100% | 40% | 2422.1 | 968.84 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 881.6444 | 0.96884 | 882.6132 | 0.96884 | 882.6132 | PII-AX-MR-ML-00014 | PII-AX-WR-L16-00062 | Frame was delivered during previous contract
154 | Door mark L17H11 to STAIR-06 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 56% | 35.1% | 91.1% | 2163.672 | 1356.1587 | 3519.8307 | 1356.1587 | 3519.8307 | PII-AX-MR-ML-00072 | PII-AX-WR-ML-00072
155 | Door mark L17R01 to STAIR-03 | 1 | Nos. | 3226.64 | 60% | 1935.984 | 1290.656 | 100% | 40% | 3226.64 | 1290.656 | 21% | 9% | 35% | 15% | 12.6% | 0% | 80% | 12.6% | 92.6% | 1032.5248 | 162.6227 | 1195.1475 | 162.6227 | 1195.1475 |  | PII-AX-WR-L16-00076 | Frame was delivered during previous contract
156 | Door mark L17R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 15% | 12.6% | 0% | 80% | 12.6% | 92.6% | 3252.08 | 512.2026 | 3764.2826 | 512.2026 | 3764.2826 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013 | PII-AX-WR-L16-00076
157 | Door mark L17R04 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 12.6% | 0% | 80% | 12.6% | 92.6% | 5363.6 | 844.767 | 6208.367 | 844.767 | 6208.367 |  | PII-AX-WR-L16-00076
158 | Door mark L17R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | MIR by CJ
159 | Door mark L17R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 9% | 35% | 15% | 12.6% | 0% | 56% | 36.6% | 92.6% | 1871.324 | 1223.0439 | 3094.3679 | 1223.0439 | 3094.3679 |  | PII-AX-WR-L16-00099
160 | Door mark L17R10 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 60% | 1935.984 | 1290.656 | 100% | 40% | 3226.64 | 1290.656 | 21% | 9% | 35% | 15% | 12.6% | 0% | 80% | 12.6% | 92.6% | 1032.5248 | 162.6227 | 1195.1475 | 162.6227 | 1195.1475 | PII-AX-MR-ML-00014 | PII-AX-WR-L16-00076 | Frame was delivered during previous contract
161 | Door mark L17R13 to STAIR-04 | 1 | Nos. | 3226.64 | 60% | 1935.984 | 1290.656 | 100% | 40% | 3226.64 | 1290.656 | 21% | 9% | 35% | 15% | 12.6% | 0% | 80% | 12.6% | 92.6% | 1032.5248 | 162.6227 | 1195.1475 | 162.6227 | 1195.1475 | PII-AX-MR-ML-00014 | PII-AX-WR-L16-00076
162 | Door mark L18R01 to STAIR-03 | 1 | Nos. | 3226.64 | 60% | 1935.984 | 1290.656 | 100% | 40% | 3226.64 | 1290.656 | 21% | 9% | 35% | 15% | 12.6% | 0% | 91% | 1.6% | 92.6% | 1174.497 | 20.6505 | 1195.1475 | 20.6505 | 1195.1475 |  | PII-AX-WR-L17-00044
163 | Door mark L18R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 15% | 14% | 6% | 91% | 9% | 100% | 3699.241 | 365.859 | 4065.1 | 365.859 | 4065.1 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013 | PII-AX-WR-L17-00044
164 | Door mark L18R04 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 0% | 35% | 0% | 0% | 0% | 56% | 0% | 56% | 3754.52 | 0 | 3754.52 | 0 | 3754.52 |  |  |  | WIR to be raised
165 | Door mark L18R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | MIR by CJ
166 | Door mark L18R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 0% | 35% | 0% | 0% | 0% | 56% | 0% | 56% | 1871.324 | 0 | 1871.324 | 0 | 1871.324
167 | Door mark L18R10 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 60% | 1935.984 | 1290.656 | 100% | 40% | 3226.64 | 1290.656 | 21% | 9% | 35% | 15% | 14% | 6% | 91% | 9% | 100% | 1174.497 | 116.159 | 1290.656 | 116.159 | 1290.656 | PII-AX-MR-ML-00014 | PII-AX-WR-L17-00044 | Frame was delivered during previous contract
168 | Door mark L18R13 to STAIR-04 | 1 | Nos. | 3226.64 | 60% | 1935.984 | 1290.656 | 100% | 40% | 3226.64 | 1290.656 | 21% | 9% | 35% | 15% | 14% | 6% | 65% | 35% | 100% | 838.9264 | 451.7296 | 1290.656 | 451.7296 | 1290.656 | PII-AX-MR-ML-00014 | PII-AX-WR-L17-00044 |  | WIR to be raised
169 | Door mark L19R01 to STAIR-03 | 1 | Nos. | 3226.64 | 60% | 1935.984 | 1290.656 | 100% | 40% | 3226.64 | 1290.656 | 21% | 9% | 35% | 15% | 12.6% | 0% | 85% | 7.6% | 92.6% | 1097.0576 | 98.0899 | 1195.1475 | 98.0899 | 1195.1475 |  | PII-AX-WR-L18-00045
170 | Door mark L19R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 15% | 12.6% | 0% | 91% | 1.6% | 92.6% | 3699.241 | 65.0416 | 3764.2826 | 65.0416 | 3764.2826 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013 | PII-AX-WR-L18-00045
171 | Door mark L19R04 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 0% | 0% | 91% | -11% | 80% | 6101.095 | -737.495 | 5363.6 | 0 | 6101.095
172 | Door mark L19R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | MIR by CJ
173 | Door mark L19R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 0% | 35% | 0% | 0% | 0% | 56% | 0% | 56% | 1871.324 | 0 | 1871.324 | 0 | 1871.324
174 | Door mark L19R09 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 60% | 1935.984 | 1290.656 | 100% | 40% | 3226.64 | 1290.656 | 21% | 9% | 35% | 15% | 14% | 6% | 91% | 9% | 100% | 1174.497 | 116.159 | 1290.656 | 116.159 | 1290.656 | PII-AX-MR-ML-00014 | PII-AX-WR-L18-00045
175 | Door mark L19R12 to STAIR-04 | 1 | Nos. | 3226.64 | 60% | 1935.984 | 1290.656 | 100% | 40% | 3226.64 | 1290.656 | 21% | 9% | 35% | 15% | 14% | 6% | 65% | 35% | 100% | 838.9264 | 451.7296 | 1290.656 | 451.7296 | 1290.656 | PII-AX-MR-ML-00014 | PII-AX-WR-L18-00045
176 | Door mark L19R14 to TELECOM | 1 | Nos. | Deleted as per Email dated 29 June 2022 | [19 empty] | 0 | 0
177 | Door mark L20H01 to STAIR-07 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 12.6% | 0% | 91% | 1.6% | 92.6% | 3515.967 | 61.8192 | 3577.7862 | 61.8192 | 3577.7862 | PII-AX-MR-ML-00015 | PII-AX-WR-L19-00063
178 | Door mark L20H03 to FF LOBBY | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 0% | 0% | 65% | 15% | 80% | 1967.9562 | 454.1438 | 2422.1 | 454.1438 | 2422.1
179 | Door mark L20H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 60% | 1453.26 | 968.84 | 100% | 40% | 2422.1 | 968.84 | 21% | 9% | 35% | 15% | 12.6% | 0% | 91% | 1.6% | 92.6% | 881.6444 | 15.5014 | 897.1458 | 15.5014 | 897.1458 | PII-AX-MR-ML-00014 | PII-AX-WR-L19-00063 | Frame was delivered during previous contract
180 | Door mark L20H06 to STAIR-08 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 15% | 12.6% | 0% | 91% | 1.6% | 92.6% | 3515.967 | 61.8192 | 3577.7862 | 61.8192 | 3577.7862 |  | PII-AX-WR-L19-00063
181 | Door mark L20H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 60% | 1453.26 | 968.84 | 100% | 40% | 2422.1 | 968.84 | 21% | 9% | 35% | 15% | 12.6% | 0% | 91% | 1.6% | 92.6% | 881.6444 | 15.5014 | 897.1458 | 15.5014 | 897.1458 | PII-AX-MR-ML-00014 | PII-AX-WR-L19-00063 | Frame was delivered during previous contract
100%
100%
| To Collection Dhs. |  |  |  |  | 33887.352 | 109429.948 | 100% |  | 0 | 131139.543 | [9 empty] | 94035.807 | 11097.758 | 105133.565 | 11835.253 | 105871.06
| TIMBER DOORS (CONT'D) | [6 empty] | 100%
182 | Door mark L20R01 to STAIR-03 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 12.6% | 0% | 80% | 12.6% | 92.6% | 3226.64 | 508.1958 | 3734.8358 | 508.1958 | 3734.8358 | PII-AX-MR-ML-00016 | PII-AX-WR-L19-00077 | Frame was delivered during previous contract
183 | Door mark L20R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 15% | 12.6% | 0% | 80% | 12.6% | 92.6% | 3252.08 | 512.2026 | 3764.2826 | 512.2026 | 3764.2826 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013 | PII-AX-WR-L19-00077
184 | Door mark L20R04 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 0% | 0% | 56% | 24% | 80% | 3754.52 | 1609.08 | 5363.6 | 1609.08 | 5363.6 |  | PII-AX-WR-L19-00077
185 | Door mark L20R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 0% | 35% | 0% | 0% | 0% | 0% | 56% | 56% | 0 | 1695.47 | 1695.47 | 1695.47 | 1695.47 |  |  |  | MIR by CJ
186 | Door mark L20R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 0% | 35% | 0% | 0% | 0% | 56% | 0% | 56% | 1871.324 | 0 | 1871.324 | 0 | 1871.324
187 | Door mark L20R09 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 30% | 967.992 | 2258.648 | 100% | 70% | 3226.64 | 2258.648 | 21% | 9% | 35% | 15% | 12.6% | 0% | 80% | 12.6% | 92.6% | 1806.9184 | 284.5896 | 2091.508 | 284.5896 | 2091.508 | PII-AX-MR-ML-00016 | PII-AX-WR-L19-00077
188 | Door mark L20R12 to STAIR-04 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 12.6% | 0% | 80% | 12.6% | 92.6% | 3226.64 | 508.1958 | 3734.8358 | 508.1958 | 3734.8358 | PII-AX-MR-ML-00014 | PII-AX-WR-L19-00077
189 | Door mark L20R14 to TELECOM | 1 | Nos. | Deleted as per Email dated 29 June 2022 | [19 empty] | 0 | 0
190 | Door mark L21H01 to STAIR-07 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 3515.967 | 3.8637 | 3519.8307 | 3.8637 | 3519.8307 |  | PII-AX-WR-L20-00064
191 | Door mark L21H03 to FF LOBBY | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 2755.1387 | 3.0276 | 2758.1664 | 3.0276 | 2758.1664 |  | PII-AX-WR-L20-00064
192 | Door mark L21H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 25% | 605.525 | 1816.575 | 100% | 75% | 2422.1 | 1816.575 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1653.0832 | 1.8166 | 1654.8998 | 1.8166 | 1654.8998 | PII-AX-MR-ML-00014 | PII-AX-WR-L20-00064
193 | Door mark L21H06 to STAIR-08 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 3515.967 | 3.8637 | 3519.8307 | 3.8637 | 3519.8307 |  | PII-AX-WR-L20-00064
194 | Door mark L21H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 30% | 726.63 | 1695.47 | 100% | 70% | 2422.1 | 1695.47 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1542.8777 | 1.6955 | 1544.5732 | 1.6955 | 1544.5732 | PII-AX-MR-ML-00014 | PII-AX-WR-L20-00064
195 | Door mark L21R01 to STAIR-03 | 1 | Nos. | 3226.64 | 30% | 967.992 | 2258.648 | 100% | 70% | 3226.64 | 2258.648 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 1806.9184 | 451.7296 | 2258.648 | 451.7296 | 2258.648 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016 | PII-AX-WR-L20-00078
196 | Door mark L21R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 3252.08 | 813.02 | 4065.1 | 813.02 | 4065.1 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013 | PII-AX-WR-L20-00078
197 | Door mark L21R04 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 0% | 35% | 0% | 0% | 0% | 56% | 0% | 56% | 3754.52 | 0 | 3754.52 | 0 | 3754.52 |  |  |  | WIR by CJ
198 | Door mark L21R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | WIR by CJ
199 | Door mark L21R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 0% | 35% | 0% | 0% | 0% | 56% | 0% | 56% | 1871.324 | 0 | 1871.324 | 0 | 1871.324
200 | Door mark L21R09 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 3226.64 | 806.66 | 4033.3 | 806.66 | 4033.3 | PII-AX-MR-ML-00016 | PII-AX-WR-L20-00078
201 | Door mark L21R12 to STAIR-04 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 0% | 0% | 80% | 0% | 80% | 3226.64 | 0 | 3226.64 | 0 | 3226.64 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016 | PII-AX-WR-L20-00078
202 | Door mark L21R14 to TELECOM | 1 | Nos. | Deleted as per Email dated 29 June 2022 | [11 empty] | 0% | 0% | [6 empty] | 0 | 0
203 | Door mark L22H01 to STAIR-07 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 3515.967 | 3.8637 | 3519.8307 | 3.8637 | 3519.8307 |  | PII-AX-WR-L21-00065
204 | Door mark L22H03 to FF LOBBY | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 2755.1387 | 3.0276 | 2758.1664 | 3.0276 | 2758.1664 |  | PII-AX-WR-L21-00065
205 | Door mark L22H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 25% | 605.525 | 1816.575 | 100% | 75% | 2422.1 | 1816.575 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1653.0832 | 1.8166 | 1654.8998 | 1.8166 | 1654.8998 | PII-AX-MR-ML-00014 | PII-AX-WR-L21-00065 | Frame was delivered during previous contract
206 | Door mark L22H06 to STAIR-08 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 3515.967 | 3.8637 | 3519.8307 | 3.8637 | 3519.8307 |  | PII-AX-WR-L21-00065
207 | Door mark L22H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 22% | 532.862 | 1889.238 | 100% | 78% | 2422.1 | 1889.238 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1719.2066 | 1.8892 | 1721.0958 | 1.8892 | 1721.0958 | PII-AX-MR-ML-00014 | PII-AX-WR-L21-00065 | Frame was delivered during previous contract
208 | Door mark L22R01 to STAIR-03 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 3226.64 | 806.66 | 4033.3 | 806.66 | 4033.3 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016 | PII-AX-WR-L21-00079
209 | Door mark L22R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 3252.08 | 813.02 | 4065.1 | 813.02 | 4065.1 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013 | PII-AX-WR-L21-00079
210 | Door mark L22R04 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 5363.6 | 1340.9 | 6704.5 | 1340.9 | 6704.5 |  | PII-AX-WR-L21-00090
211 | Door mark L22R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | MIR & WIR by CJ
212 | Door mark L22R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 9% | 35% | 15% | 12.6% | 0% | 80% | 12.6% | 92.6% | 2673.32 | 421.0479 | 3094.3679 | 421.0479 | 3094.3679 |  | PII-AX-WR-L22-00024
213 | Door mark L22R09 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 3226.64 | 806.66 | 4033.3 | 806.66 | 4033.3 | PII-AX-MR-ML-00016 | PII-AX-WR-L21-00079
214 | Door mark L22R12 to STAIR-04 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 14% | 6% | 80% | 20% | 100% | 3226.64 | 806.66 | 4033.3 | 806.66 | 4033.3 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016 | PII-AX-WR-L21-00079
215 | Door mark L22R14 to TELECOM | 1 | Nos. | Deleted as per Email dated 29 June 2022 | [19 empty] | 0 | 0
216 | Door mark L23H01 to STAIR-07 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 3515.967 | 3.8637 | 3519.8307 | 3.8637 | 3519.8307 |  | PII-AX-WR-L22-00066
217 | Door mark L23H03 to FF LOBBY | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 14% | 0% | 85% | 9% | 94% | 2573.4812 | 272.4862 | 2845.9675 | 272.4862 | 2845.9675
218 | Door mark L23H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 23% | 557.083 | 1865.017 | 100% | 77% | 2422.1 | 1865.017 | 21% | 9% | 35% | 15% | 14% | 0% | 85% | 9% | 94% | 1585.2644 | 167.8515 | 1753.116 | 167.8515 | 1753.116 | PII-AX-MR-ML-00014
219 | Door mark L23H06 to STAIR-08 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 3515.967 | 3.8637 | 3519.8307 | 3.8637 | 3519.8307 |  | PII-AX-WR-L22-00066
220 | Door mark L23H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 20.34% | 492.6551 | 1929.4449 | 100% | 79.66% | 2422.1 | 1929.4449 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1755.7948 | 1.9294 | 1757.7243 | 1.9294 | 1757.7243 | PII-AX-MR-ML-00014 | PII-AX-WR-L22-00066 | Frame was delivered during previous contract
221 | Door mark L23R01 to STAIR-03 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 14% | 0% | 91% | 3% | 94% | 3670.303 | 120.999 | 3791.302 | 120.999 | 3791.302 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016 | PII-AX-WR-L22-00085
222 | Door mark L23R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 15% | 14% | 6% | 85% | 15% | 100% | 3455.335 | 609.765 | 4065.1 | 609.765 | 4065.1 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013 | PII-AX-WR-L22-00085
223 | Door mark L23R04 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 14% | 6% | 85% | 15% | 100% | 5698.825 | 1005.675 | 6704.5 | 1005.675 | 6704.5 |  | PII-AX-WR-L22-00085
224 | Door mark L23R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 15% | 14% | 6% | 0% | 100% | 100% | 0 | 3027.625 | 3027.625 | 3027.625 | 3027.625 |  | PII-AX-WR-L22-00085 |  | MIR & WIR by CJ
225 | Door mark L23R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 9% | 35% | 15% | 14% | 6% | 65% | 35% | 100% | 2172.0725 | 1169.5775 | 3341.65 | 1169.5775 | 3341.65 |  | PII-AX-WR-L22-00085 |  | MIR & WIR by CJ
226 | Door mark L23R09 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 14% | 6% | 85% | 15% | 100% | 3428.305 | 604.995 | 4033.3 | 604.995 | 4033.3 | PII-AX-MR-ML-00016 | PII-AX-WR-L22-00085
227 | Door mark L23R12 to STAIR-04 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 14% | 0% | 85% | 9% | 94% | 3428.305 | 362.997 | 3791.302 | 362.997 | 3791.302 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016 | PII-AX-WR-L22-00085
228 | Door mark L23R14 to TELECOM | 1 | Nos. | Deleted as per Email dated 29 June 2022 | [19 empty] | 0 | 0
229 | Door mark L24H01 to STAIR-07 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 3515.967 | 3.8637 | 3519.8307 | 3.8637 | 3519.8307 |  | PII-AX-WR-L23-00067
100%
100%
| To Collection Dhs. |  |  |  |  | 5456.2641 | 131543.4359 | 100% |  |  | 160546.8909 | [9 empty] | 119703.1481 | 19568.3111 | 139271.4592 | 19568.3111 | 139271.4592
| TIMBER DOORS (CONT'D) | [6 empty] | 100%
100%
230 | Door mark L24H03 to FF LOBBY | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 2755.1387 | 3.0276 | 2758.1664 | 3.0276 | 2758.1664 |  | PII-AX-WR-L23-00067
231 | Door mark L24H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 22% | 532.862 | 1889.238 | 100% | 78% | 2422.1 | 1889.238 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1719.2066 | 1.8892 | 1721.0958 | 1.8892 | 1721.0958 | PII-AX-MR-ML-00014 | PII-AX-WR-L23-00067 | Frame was delivered during previous contract
232 | Door mark L24H06 to STAIR-08 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 3515.967 | 3.8637 | 3519.8307 | 3.8637 | 3519.8307 |  | PII-AX-WR-L23-00067
233 | Door mark L24H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 22% | 532.862 | 1889.238 | 100% | 78% | 2422.1 | 1889.238 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1719.2066 | 1.8892 | 1721.0958 | 1.8892 | 1721.0958 |  | PII-AX-WR-L23-00067 | Frame was delivered during previous contract
234 | Door mark L24R11 to HOUSEKEEPING LOBBY | 1 | Nos. | 2226 | 0% | 0 | 2226 | 100% | 100% | 2782.5 | 2782.5 | 21% | 0% | 35% | 0% | 0% | 6% | 6% | 56% | 62% | 166.95 | 1558.2 | 1725.15 | 1558.2 | 1725.15 | PII-AX-MR-ML-00025 |  |  | MIR by CJ
235 | Door mark L24R14 to STAIR-04 | 1 | Nos. | 2226 | 0% | 0 | 2226 | 100% | 100% | 2782.5 | 2782.5 | 21% | 0% | 35% | 0% | 0% | 0% | 0% | 56% | 56% | 0 | 1558.2 | 1558.2 | 1558.2 | 1558.2 | PII-AX-MR-ML-00025
236 | Door mark L24R15 to PANTRY | 1 | Nos. | 1955.7 | 0% | 0 | 1955.7 | 100% | 100% | 2444.625 | 2444.625 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
237 | Door mark L24R16 to TELECOM | 1 | Nos. | Deleted as per Email dated 29 June 2022 | [19 empty] | 0 | 0
238 | Door mark L25H01 to STAIR-07 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 3515.967 | 3.8637 | 3519.8307 | 3.8637 | 3519.8307 |  | PII-AX-WR-L24-00068
239 | Door mark L25H03 to FF LOBBY | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 2755.1387 | 3.0276 | 2758.1664 | 3.0276 | 2758.1664 |  | PII-AX-WR-L24-00068
240 | Door mark L25H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 22% | 532.862 | 1889.238 | 100% | 78% | 2422.1 | 1889.238 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1719.2066 | 1.8892 | 1721.0958 | 1.8892 | 1721.0958 |  | PII-AX-WR-L24-00068
241 | Door mark L25H06 to STAIR-08 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 3515.967 | 3.8637 | 3519.8307 | 3.8637 | 3519.8307 |  | PII-AX-WR-L24-00068
242 | Door mark L25H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 22% | 532.862 | 1889.238 | 100% | 78% | 2422.1 | 1889.238 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1719.2066 | 1.8892 | 1721.0958 | 1.8892 | 1721.0958 | PII-AX-MR-ML-00014 | PII-AX-WR-L24-00068
243 | Door mark L25H11 to STAIR-06 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 65% | 26.1% | 91.1% | 2511.405 | 1008.4257 | 3519.8307 | 1008.4257 | 3519.8307 | PII-AX-MR-ML-00073 | PII-AX-WR-ML-00073 |  | WIR by CJ
244 | Door mark L25R01 to STAIR-03 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 0% | 35% | 0% | 0% | 0% | 56% | 0% | 56% | 2258.648 | 0 | 2258.648 | 0 | 2258.648 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016
245 | Door mark L25R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 0% | 35% | 15% | 14% | 6% | 91% | 0% | 91% | 3699.241 | 0 | 3699.241 | 0 | 3699.241 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013
246 | Door mark L25R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 0% | 0% | 0% | 0% | 0% | 21% | 0% | 21% | 635.8012 | 0 | 635.8012 | 0 | 635.8012 |  |  |  | MIR by CJ
247 | Door mark L25R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 0% | 35% | 0% | 0% | 0% | 56% | 0% | 56% | 1871.324 | 0 | 1871.324 | 0 | 1871.324
248 | Door mark L25R10 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 0% | 0% | 56% | 24% | 80% | 2258.648 | 967.992 | 3226.64 | 967.992 | 3226.64 | PII-AX-MR-ML-00016 |  |  | WIR to be raised
249 | Door mark L25R13 to STAIR-04 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 0% | 0% | 65% | 15% | 80% | 2621.645 | 604.995 | 3226.64 | 604.995 | 3226.64 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016 |  |  | WIR to be raised
250 | Door mark L25R18 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 0% | 0% | 80% | 0% | 80% | 5363.6 | 0 | 5363.6 | 0 | 5363.6
251 | Door mark L26H02 to STAIR-07 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 3515.967 | 3.8637 | 3519.8307 | 3.8637 | 3519.8307 |  | PII-AX-WR-L25-00069
252 | Door mark L26H03 to FF LOBBY | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 2755.1387 | 3.0276 | 2758.1664 | 3.0276 | 2758.1664 |  | PII-AX-WR-L25-00069
253 | Door mark L26H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 22% | 532.862 | 1889.238 | 100% | 78% | 2422.1 | 1889.238 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1719.2066 | 1.8892 | 1721.0958 | 1.8892 | 1721.0958 |  | PII-AX-WR-L25-00069 | Frame was delivered during previous contract
254 | Door mark L26H06 to STAIR-08 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 3515.967 | 3.8637 | 3519.8307 | 3.8637 | 3519.8307 |  | PII-AX-WR-L25-00069
255 | Door mark L26H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 22% | 532.862 | 1889.238 | 100% | 78% | 2422.1 | 1889.238 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1719.2066 | 1.8892 | 1721.0958 | 1.8892 | 1721.0958 | PII-AX-MR-ML-00014 | PII-AX-WR-L25-00069 | Frame was delivered during previous contract
256 | Door mark L26H11 to STAIR-06 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 65% | 26.1% | 91.1% | 2511.405 | 1008.4257 | 3519.8307 | 1008.4257 | 3519.8307 | PII-AX-MR-ML-00073 | PII-AX-WR-ML-00073
257 | Door mark L26R01 to STAIR-03 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 0% | 0% | 0% | 65% | 0% | 65% | 2621.645 | 0 | 2621.645 | 0 | 2621.645 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016
258 | Door mark L26R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 15% | 14% | 6% | 85% | 15% | 100% | 3455.335 | 609.765 | 4065.1 | 609.765 | 4065.1 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013
259 | Door mark L26R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | MIR by CJ
260 | Door mark L26R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 0% | 35% | 0% | 0% | 0% | 56% | 0% | 56% | 1871.324 | 0 | 1871.324 | 0 | 1871.324
261 | Door mark L26R10 to HOUSEKEEPING LOBBY | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 0% | 0% | 56% | 24% | 80% | 2258.648 | 967.992 | 3226.64 | 967.992 | 3226.64 | PII-AX-MR-ML-00016 | PII-AX-WR-L26-00039 |  | WIR to be raised
262 | Door mark L26R13 to STAIR-04 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 0% | 0% | 65% | 15% | 80% | 2621.645 | 604.995 | 3226.64 | 604.995 | 3226.64 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016 |  |  | WIR to be raised
263 | Door mark L26R18 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 0% | 0% | 65% | 15% | 80% | 4357.925 | 1005.675 | 5363.6 | 1005.675 | 5363.6 |  |  |  | WIR to be raised
264 | Door mark L27H01 to STAIR-07 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 3515.967 | 3.8637 | 3519.8307 | 3.8637 | 3519.8307 | PII-AX-MR-ML-00016 | PII-AX-WR-L26-00070
265 | Door mark L27H03 to FF LOBBY | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 2755.1387 | 3.0276 | 2758.1664 | 3.0276 | 2758.1664 |  | PII-AX-WR-L26-00070
266 | Door mark L27H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 22% | 532.862 | 1889.238 | 100% | 78% | 2422.1 | 1889.238 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1719.2066 | 1.8892 | 1721.0958 | 1.8892 | 1721.0958 |  | PII-AX-WR-L26-00070
267 | Door mark L27H06 to STAIR-08 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 3515.967 | 3.8637 | 3519.8307 | 3.8637 | 3519.8307 |  | PII-AX-WR-L26-00070
268 | Door mark L27H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 22% | 532.862 | 1889.238 | 100% | 78% | 2422.1 | 1889.238 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1719.2066 | 1.8892 | 1721.0958 | 1.8892 | 1721.0958 | PII-AX-MR-ML-00014 | PII-AX-WR-L26-00070
269 | Door mark L27H11 to STAIR-06 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 65% | 26.1% | 91.1% | 2511.405 | 1008.4257 | 3519.8307 | 1008.4257 | 3519.8307 | PII-AX-MR-ML-00073 | PII-AX-WR-ML-00073 |  | WIR to be raised
270 | Door mark L27R01 to STAIR-03 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 0% | 0% | 0% | 65% | 0% | 65% | 2621.645 | 0 | 2621.645 | 0 | 2621.645 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016
271 | Door mark L27R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 15% | 0% | 0% | 91% | -11% | 80% | 3699.241 | -447.161 | 3252.08 | 0 | 3699.241 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013
272 | Door mark L27R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 0% | 35% | 0% | 0% | 0% | 0% | 56% | 56% | 0 | 1695.47 | 1695.47 | 1695.47 | 1695.47
273 | Door mark L27R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 0% | 35% | 0% | 0% | 0% | 56% | 0% | 56% | 1871.324 | 0 | 1871.324 | 0 | 1871.324
274 | Door mark L27R10 to HOUSEKEEPING LOBBY | 1 | Nos. | 2550.36 | 0% | 0 | 2550.36 | 100% | 100% | 3187.95 | 3187.95 | 21% | 9% | 35% | 15% | 0% | 0% | 56% | 24% | 80% | 1785.252 | 765.108 | 2550.36 | 765.108 | 2550.36 | PII-AX-MR-ML-00016 | PII-AX-WR-L27-00040 |  | WIR to be raised
275 | Door mark L27R13 to STAIR-04 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 0% | 0% | 65% | 15% | 80% | 2621.645 | 604.995 | 3226.64 | 604.995 | 3226.64 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016 |  |  | WIR to be raised
276 | Door mark L27R14 to TELECOM | 1 | Nos. | Deleted as per Email dated 29 June 2022
100%
100%
| To Collection Dhs. |  |  |  |  | 4262.896 | 126252.784 | 100% |  | 0 | 154037.504 | [9 empty] | 105581.6779 | 13575.7734 | 119157.4513 | 14022.9344 | 119604.6123
| TIMBER DOORS (CONT'D) | [6 empty] | 100%
100%
277 | Door mark L27R20 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 14% | 6% | 91% | 9% | 100% | 6101.095 | 603.405 | 6704.5 | 603.405 | 6704.5
278 | Door mark L28H02 to STAIR-07 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 3515.967 | 3.8637 | 3519.8307 | 3.8637 | 3519.8307 | PII-AX-MR-ML-00016 | PII-AX-WR-L27-00071
279 | Door mark L28H03 to FF LOBBY | 1 | Nos. | 2422.1 | 0% | 0 | 94.61 | 100% | 100% | 3027.625 | 3027.625 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 2755.1387 | 3.0276 | 2758.1664 | 3.0276 | 2758.1664 |  | PII-AX-WR-L27-00071
280 | Door mark L28H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2422.1 | 22% | 532.862 | 1889.238 | 100% | 78% | 2422.1 | 1889.238 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1719.2066 | 1.8892 | 1721.0958 | 1.8892 | 1721.0958 |  | PII-AX-WR-L27-00071
281 | Door mark L28H06 to STAIR-08 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 3515.967 | 3.8637 | 3519.8307 | 3.8637 | 3519.8307 |  | PII-AX-WR-L27-00071
282 | Door mark L28H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2422.1 | 22% | 532.862 | 1889.238 | 100% | 78% | 2422.1 | 1889.238 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 91% | 0.1% | 91.1% | 1719.2066 | 1.8892 | 1721.0958 | 1.8892 | 1721.0958 | PII-AX-MR-ML-00014 | PII-AX-WR-L27-00071
283 | Door mark L28H11 to STAIR-06 | 1 | Nos. | 3090.96 | 0% | 0 | 3090.96 | 100% | 100% | 3863.7 | 3863.7 | 21% | 9% | 35% | 13.5% | 12.6% | 0% | 65% | 26.1% | 91.1% | 2511.405 | 1008.4257 | 3519.8307 | 1008.4257 | 3519.8307 | PII-AX-MR-ML-00073 | PII-AX-WR-ML-00073 |  | WIR to be raised
284 | Door mark L28R01 to STAIR-03 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 0% | 0% | 65% | 15% | 80% | 2621.645 | 604.995 | 3226.64 | 604.995 | 3226.64 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016 |  |  | WIR to be raised
285 | Door mark L28R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 15% | 0% | 0% | 85% | -5% | 80% | 3455.335 | -203.255 | 3252.08 | 0 | 3455.335 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013
286 | Door mark L28R06 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 21% | 0% | 35% | 0% | 0% | 0% | 0% | 56% | 56% | 0 | 1695.47 | 1695.47 | 1695.47 | 1695.47 |  |  |  | MIR by CJ
287 | Door mark L28R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 0% | 35% | 0% | 0% | 0% | 56% | 0% | 56% | 1871.324 | 0 | 1871.324 | 0 | 1871.324
288 | Door mark L28R10 to HOUSEKEEPING LOBBY | 1 | Nos. | 2550.36 | 0% | 0 | 2550.36 | 100% | 100% | 3187.95 | 3187.95 | 21% | 9% | 35% | 15% | 12.6% | 0% | 91% | 1.6% | 92.6% | 2901.0345 | 51.0072 | 2952.0417 | 51.0072 | 2952.0417 | PII-AX-MR-ML-00016 | PII-AX-WR-L28-00041
289 | Door mark L28R13 to STAIR-04 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 0% | 0% | 65% | 15% | 80% | 2621.645 | 604.995 | 3226.64 | 604.995 | 3226.64 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016 |  |  | WIR to be raised
290 | Door mark L28R14 to TELECOM | 1 | Nos. | Deleted as per Email dated 29 June 2022 | [19 empty] | 0 | 0
291 | Door mark L28R19 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 14% | 6% | 91% | 9% | 100% | 6101.095 | 603.405 | 6704.5 | 603.405 | 6704.5
292 | Door mark L29H01 to STAIR-07 | 1 | Nos. | 2933.02 |  | 0 |  | 100% |  |  | Excluded | [12 empty] | 0 | 0
293 | Door mark L29H03 to FF LOBBY | 1 | Nos. | 2038.38 |  | 0 |  | 100% |  |  | Excluded | [12 empty] | 0 | 0
294 | Door mark L29H04 to ROOM SERVICE SUPPORT AREA | 1 | Nos. | 2038.38 |  | 0 |  | 100% |  |  | Excluded | [12 empty] | 0 | 0
295 | Door mark L29H20 to MEP PLANT ROOM | 1 | Nos. | 2603.36 |  | 0 |  | 100% |  |  | Excluded | [12 empty] | 0 | 0
296 | Door mark L29R01 to STAIR-03 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 0% | 0% | 65% | 15% | 80% | 2621.645 | 604.995 | 3226.64 | 604.995 | 3226.64 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016 |  |  | WIR to be raised
297 | Door mark L29R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 15% | 0% | 0% | 85% | -5% | 80% | 3455.335 | -203.255 | 3252.08 | 0 | 3455.335 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013
298 | Door mark L29R05 to WM ROOM | 1 | Nos. | 2422.1 | 0% | 0 | 2422.1 | 100% | 100% | 3027.625 | 3027.625 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | MIR by CJ
299 | Door mark L29R08 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 0% | 35% | 0% | 0% | 0% | 56% | 0% | 56% | 1871.324 | 0 | 1871.324 | 0 | 1871.324
300 | Door mark L29R10 to HOUSEKEEPING LOBBY | 1 | Nos. | 2550.36 | 0% | 0 | 2550.36 | 100% | 100% | 3187.95 | 3187.95 | 21% | 9% | 35% | 15% | 12.6% | 0% | 91% | 1.6% | 92.6% | 2901.0345 | 51.0072 | 2952.0417 | 51.0072 | 2952.0417 | PII-AX-MR-ML-00016 | PII-AX-WR-L29-00042
301 | Door mark L29R13 to STAIR-04 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 0% | 0% | 71% | 9% | 80% | 2863.643 | 362.997 | 3226.64 | 362.997 | 3226.64 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016 |  |  | WIR to be raised
302 | Door mark L29R14 to TELECOM | 1 | Nos. | Deleted as per Email dated 29 June 2022 | [7 empty] | 21% | 9% | 35% | 15% | 14% | 0% | [6 empty] | 0 | 0
303 | Door mark L29R18 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 15% | 14% | 6% | 91% | 9% | 100% | 6101.095 | 603.405 | 6704.5 | 603.405 | 6704.5
304 | Door mark L30R01 to STAIR-03 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 0% | 0% | 85% | -5% | 80% | 3428.305 | -201.665 | 3226.64 | 0 | 3428.305 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016
305 | Door mark L30R03 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 15% | 0% | 0% | 85% | -5% | 80% | 3455.335 | -203.255 | 3252.08 | 0 | 3455.335 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013
306 | Door mark L30R05 to WM ROOM | 1 | Nos. | 2995.56 | 0% | 0 | 2995.56 | 100% | 100% | 3744.45 | 3744.45 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | MIR by CJ
307 | Door mark L30R06 to HOUSEKEEPING LOBBY | 1 | Nos. | 2550.36 | 0% | 0 | 2550.36 | 100% | 100% | 3187.95 | 3187.95 | 21% | 9% | 35% | 15% | 12.6% | 0% | 91% | 1.6% | 92.6% | 2901.0345 | 51.0072 | 2952.0417 | 51.0072 | 2952.0417 | PII-AX-MR-ML-00016 | PII-AX-WR-L30-00043
308 | Door mark L30R09 to STAIR-04 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 15% | 0% | 0% | 85% | -5% | 80% | 3428.305 | -201.665 | 3226.64 | 0 | 3428.305 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016
309 | Door mark L30R13 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 9% | 35% | 0% | 0% | 0% | 65% | 0% | 65% | 2172.0725 | 0 | 2172.0725 | 0 | 2172.0725
310 | Door mark L30R17 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 9% | 35% | 0% | 0% | 0% | 65% | 0% | 65% | 4357.925 | 0 | 4357.925 | 0 | 4357.925 |  |  |  | WIR to be raised
311 | Door mark L31R02 to STAIR-03 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 0% | 35% | 0% | 0% | 0% | 30% | 26% | 56% | 1209.99 | 1048.658 | 2258.648 | 1048.658 | 2258.648 |  |  |  | MIR by CJ
312 | Door mark L31R04 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 21% | 9% | 35% | 0% | 0% | 0% | 65% | 0% | 65% | 2642.315 | 0 | 2642.315 | 0 | 2642.315 | PII-AX-MR-ML-00012 PII-AX-MR-ML-00013
313 | Door mark L31R07 to WM ROOM | 1 | Nos. | 2995.56 | 0% | 0 | 2995.56 | 100% | 100% | 3744.45 | 3744.45 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | MIR by CJ
314 | Door mark L31R09 to ELEC RM | 1 | Nos. | 2673.32 | 0% | 0 | 2673.32 | 100% | 100% | 3341.65 | 3341.65 | 21% | 0% | 35% | 0% | 0% | 0% | 56% | 0% | 56% | 1871.324 | 0 | 1871.324 | 0 | 1871.324
315 | Door mark L31R10 to HOUSEKEEPING LOBBY | 1 | Nos. | 2550.36 | 0% | 0 | 2550.36 | 100% | 100% | 3187.95 | 3187.95 | 21% | 9% | 35% | 15% | 0% | 0% | 85% | -5% | 80% | 2709.7575 | -159.3975 | 2550.36 | 0 | 2709.7575 | PII-AX-MR-ML-00016
316 | Door mark L31R13 to STAIR-04 | 1 | Nos. | 3226.64 | 0% | 0 | 3226.64 | 100% | 100% | 4033.3 | 4033.3 | 21% | 9% | 35% | 0% | 0% | 0% | 65% | 0% | 65% | 2621.645 | 0 | 2621.645 | 0 | 2621.645 | PII-AX-MR-ML-00015 PII-AX-MR-ML-00016
317 | Door mark L31R17 to EMPOWER METRE | 1 | Nos. | 5363.6 | 0% | 0 | 5363.6 | 100% | 100% | 6704.5 | 6704.5 | 21% | 0% | 35% | 0% | 0% | 0% | 56% | 0% | 56% | 3754.52 | 0 | 3754.52 | 0 | 3754.52
318 | Door mark LGF121 to MECH ROOM | 1 | Nos. | 2603.36 | 0% | 0 | 2603.36 | 100% | 100% | 3254.2 | 3254.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | MIR by CJ
319 | Door mark LGF14 to FF LOBBY | 1 | Nos. | 3252.08 | 0% | 0 | 3252.08 | 100% | 100% | 4065.1 | 4065.1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | MIR by CJ
320 | Door mark LGF197 to ACCESS STAIR TO MEP | 1 | Nos. | 2048.98 | 0% | 0 | 2048.98 | 100% | 100% | 2561.225 | 2561.225 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
321 | Door mark LGF25 to FTR | 1 | Nos. | 2175.12 | 0% | 0 | 2175.12 | 100% | 100% | 2718.9 | 2718.9 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | MIR by CJ
322 | Door mark L18H06 to STAIR-08 | 1 | Nos. | 2946.8 | 0% | 0 | 2946.8 | 100% | 100% | 3683.5 | 3683.5 | 21% | 0% | 35% | 0% | 0% | 0% | 56% | 0% | 56% | 2062.76 | 0 | 2062.76 | 0 | 2062.76 | PII-AX-MR-ML-00016
323 | Door mark L18H07 to HOUSEKEEPING AND LINEN ROOM | 1 | Nos. | 2336.24 | 0% | 0 | 2336.24 | 100% | 100% | 2920.3 | 2920.3 | 21% | 0% | 35% | 0% | 0% | 0% | 56% | 0% | 56% | 1635.368 | 0 | 1635.368 | 0 | 1635.368
324 | Door mark L06R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0
325 | Door mark L07R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | [5 empty] | `
100%
| To Collection Dhs. |  |  |  |  | 1065.724 | 130501.746 | 100% |  |  | 165091.926 | [9 empty] | 99474.7974 | 6735.8133 | 106210.6107 | 7908.3058 | 107383.1032
| TIMBER DOORS (CONT'D) | [6 empty] | 100%
100%
326 | Door mark L08R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 |  | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
327 | Door mark L09R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
328 | Door mark L10R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
329 | Door mark L11R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
330 | Door mark L12R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
331 | Door mark L14R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
332 | Door mark L15R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
333 | Door mark L16R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
334 | Door mark L17R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
335 | Door mark L18R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
336 | Door mark L19R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
337 | Door mark L20R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
338 | Door mark L21R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
339 | Door mark L22R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
340 | Door mark L23R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
341 | Door mark L24R09 to KITCHEN EXTRACT RISER | 1 | Nos. | Deleted as per Email dated 29 June 2022 | [7 empty] | 0% | 0% | 0% | 0% | 0% | [7 empty] | 0 | 0
342 | Door mark L25R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
343 | Door mark L26R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
344 | Door mark L27R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
345 | Door mark L28R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
346 | Door mark L29R07 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
347 | Door mark L30R14 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
348 | Door mark L31R08 to KITCHEN EXTRACT RISER | 1 | Nos. | 2311.86 | 0% | 0 | 2311.86 | 100% | 100% | 2889.825 | 2889.825 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
349 | Door mark LGF129 to CEF EXHAUST ACCESS | 1 | Nos. | - | 0% |  | Excluded | 100%
100%
100%
[8 empty] | 100% |  |  | 0
| To Collection Dhs. |  |  |  |  | 0 | 50860.92 | 100% |  |  | 63576.15 | [9 empty] | 0 | 0 | 0 | 0 | 0
100%
| TIMBER DOORS (CONT'D) | [6 empty] | 100%
100%
| COLLECTION | [6 empty] | 100%
100%
| Page 1/1 |  |  |  |  | 19978.7841 | 67296.3601 | 100% |  |  | 79287.0862 | [9 empty] | 22957.771 | 13331.2107 | 36288.9817 | 13331.2107 | 36288.9817
100%
| Page 1/2 |  |  |  |  | 43545.224 | 77998.616 | 100% |  |  | 87659.456 | [9 empty] | 66075.0004 | -197.9077 | 65877.0926 | 539.5873 | 66614.5876
100%
| Page 1/3 |  |  |  |  | 39709.6564 | 102667.4236 | 100% |  |  | 119700.2986 | [9 empty] | 88112.1079 | 6262.1213 | 94374.2292 | 6429.2038 | 94541.3117
100%
| Page 1/4 |  |  |  |  | 33887.352 | 109429.948 | 100% |  |  | 131139.543 | [9 empty] | 94035.807 | 11097.758 | 105133.565 | 11835.253 | 105871.06
100%
| Page 1/5 |  |  |  |  | 5456.2641 | 131543.4359 | 100% |  |  | 160546.8909 | [9 empty] | 119703.1481 | 19568.3111 | 139271.4592 | 19568.3111 | 139271.4592
100%
| Page 1/6 |  |  |  |  | 4262.896 | 126252.784 | 100% |  |  | 154037.504 | [9 empty] | 105581.6779 | 13575.7734 | 119157.4513 | 14022.9344 | 119604.6123
100%
| Page 1/7 |  |  |  |  | 1065.724 | 130501.746 | 100% |  |  | 165091.926 | [9 empty] | 99474.7974 | 6735.8133 | 106210.6107 | 7908.3058 | 107383.1032
100%
| Page 1/8 |  |  |  |  | 0 | 50860.92 | 100% |  |  | 63576.15 | [9 empty] | 0 | 0 | 0 | 0 | 0
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
100%
| To Main Summary |  |  |  |  | 147905.9007 | 796551.2336 | 100% |  |  | 961039 | [9 empty] | 595940 | 70373 | 666313 | 73635 | 669575
[12 empty] | 264 | 227 | 263 | 203.2 | 116.4 | 42
[7 empty] | 0 | [15 empty] | 69.33%
[12 empty] | Frames |  | Doors |  | Completion
[12 empty] | Delivery (70%) | Installation(30%) | Delivery (70%) | Installation(30%) | Balance Works completion | Approvals
[6 empty] | 944457.1343 | 986039
955861.4803
Note on P42: Himal Kosala: WIR for frame only
Note on Q42: Himal Kosala: WIR not approved
Note on R42: Himal Kosala: WIR not approved
Note on Q43: Himal Kosala: WIR not approved
Note on R43: Himal Kosala: WIR not approved
Note on Q46: Himal Kosala: WIR not approved
Note on R46: Himal Kosala: WIR not approved
Note on P47: Himal Kosala: WIR for frame only
Note on Q55: Himal Kosala: WIR not approved
Note on R55: Himal Kosala: WIR not approved
Note on Q58: Himal Kosala: WIR not approved
Note on R58: Himal Kosala: WIR not approved
Note on Q59: Himal Kosala: WIR not approved
Note on R59: Himal Kosala: WIR not approved
Note on P68: Himal Kosala: WIR approved only for frame
Note on Q68: Himal Kosala: WIR approved only for frame
Note on R68: Himal Kosala: Full door not approved yet
Note on P69: Himal Kosala: WIR approved only for frame
Note on Q69: Himal Kosala: WIR approved only for frame
Note on R69: Himal Kosala: Full door not approved yet
Note on P70: Himal Kosala: WIR approved only for frame
Note on Q70: Himal Kosala: WIR approved only for frame
Note on R70: Himal Kosala: Full door not approved yet
Note on P71: Himal Kosala: WIR approved only for frame
Note on Q71: Himal Kosala: WIR approved only for frame
Note on R71: Himal Kosala: Full door not approved yet
Note on P72: Himal Kosala: WIR approved only for frame
Note on Q72: Himal Kosala: WIR approved only for frame
Note on R72: Himal Kosala: Full door not approved yet
Note on P81: Himal Kosala: WIR approved only for frame
Note on Q81: Himal Kosala: WIR approved only for frame
Note on R81: Himal Kosala: Full door not approved yet
Note on P82: Himal Kosala: WIR approved only for frame
Note on Q82: Himal Kosala: WIR approved only for frame
Note on R82: Himal Kosala: Full door not approved yet
Note on P83: Himal Kosala: WIR approved only for frame
Note on Q83: Himal Kosala: WIR approved only for frame
Note on R83: Himal Kosala: Full door not approved yet
Note on P84: Himal Kosala: WIR approved only for frame
Note on Q84: Himal Kosala: WIR approved only for frame
Note on R84: Himal Kosala: Full door not approved yet
Note on P85: Himal Kosala: WIR approved only for frame
Note on Q85: Himal Kosala: WIR approved only for frame
Note on R85: Himal Kosala: Full door not approved yet
Note on Q86: Himal Kosala: WIR not approved
Note on R86: Himal Kosala: WIR not approved
Note on Q87: Himal Kosala: WIR not approved
Note on R87: Himal Kosala: WIR not approved
Note on P88: Himal Kosala: no Supporting
Note on M89: Himal Kosala: no Supporting
Note on O89: Himal Kosala: no Supporting
Note on Q91: Himal Kosala: WIR not approved
Note on R91: Himal Kosala: WIR not approved
Note on Q92: Himal Kosala: WIR not approved
Note on R92: Himal Kosala: WIR not approved
Note on P94: Himal Kosala: WIR approved only for frame
Note on R94: Himal Kosala: Full door not approved yet
Note on R95: Himal Kosala: Full door not approved yet
Note on R96: Himal Kosala: Full door not approved yet
Note on R97: Himal Kosala: Full door not approved yet
Note on R98: Himal Kosala: Full door not approved yet
Note on Q99: Himal Kosala: WIR not approved
Note on R99: Himal Kosala: WIR not approved
Note on Q100: Himal Kosala: WIR not approved
Note on R100: Himal Kosala: WIR not approved
Note on Q101: Himal Kosala: no Supporting
Note on R101: Himal Kosala: no Supporting
Note on M102: Himal Kosala: no Supporting
Note on O102: Himal Kosala: no Supporting
Note on Q104: Himal Kosala: WIR not approved
Note on R104: Himal Kosala: WIR not approved
Note on Q105: Himal Kosala: WIR not approved
Note on R105: Himal Kosala: WIR not approved
Note on P106: Himal Kosala: WIR approved only for frame
Note on Q106: Himal Kosala: WIR approved only for frame
Note on R106: Himal Kosala: Full door not approved yet
Note on P107: Himal Kosala: WIR approved only for frame
Note on Q107: Himal Kosala: WIR approved only for frame
Note on R107: Himal Kosala: Full door not approved yet
Note on P108: Himal Kosala: WIR approved only for frame
Note on Q108: Himal Kosala: WIR approved only for frame
Note on R108: Himal Kosala: Full door not approved yet
Note on P109: Himal Kosala: WIR approved only for frame
Note on Q109: Himal Kosala: WIR approved only for frame
Note on R109: Himal Kosala: Full door not approved yet
Note on P114: Himal Kosala: WIR approved only for frame
Note on Q114: Himal Kosala: WIR approved only for frame
Note on R114: Himal Kosala: Full door not approved yet
Note on Q115: Himal Kosala: WIR not approved
Note on R115: Himal Kosala: WIR not approved
Note on Q116: Himal Kosala: WIR not approved
Note on R116: Himal Kosala: WIR not approved
Note on N117: Himal Kosala: no Supporting
Note on P117: Himal Kosala: no Supporting
Note on M118: Himal Kosala: no Supporting
Note on O118: Himal Kosala: no Supporting
Note on Q120: Himal Kosala: WIR not approved
Note on R120: Himal Kosala: WIR not approved
Note on Q121: Himal Kosala: WIR not approved
Note on R121: Himal Kosala: WIR not approved
Note on P122: Himal Kosala: WIR approved only for frame
Note on Q122: Himal Kosala: WIR approved only for frame
Note on R122: Himal Kosala: Full door not approved yet
Note on P123: Himal Kosala: WIR approved only for frame
Note on Q123: Himal Kosala: WIR approved only for frame
Note on R123: Himal Kosala: Full door not approved yet
Note on P124: Himal Kosala: WIR approved only for frame
Note on Q124: Himal Kosala: WIR approved only for frame
Note on R124: Himal Kosala: Full door not approved yet
Note on P125: Himal Kosala: WIR approved only for frame
Note on Q125: Himal Kosala: WIR approved only for frame
Note on R125: Himal Kosala: Full door not approved yet
Note on P126: Himal Kosala: WIR approved only for frame
Note on Q126: Himal Kosala: WIR approved only for frame
Note on R126: Himal Kosala: Full door not approved yet
Note on P127: Himal Kosala: WIR approved only for frame
Note on Q127: Himal Kosala: WIR approved only for frame
Note on R127: Himal Kosala: Full door not approved yet
Note on Q128: Himal Kosala: WIR not approved
Note on R128: Himal Kosala: WIR not approved
Note on Q129: Himal Kosala: WIR not approved
Note on R129: Himal Kosala: WIR not approved
Note on R130: Himal Kosala: no Supporting
Note on M131: Himal Kosala: no Supporting
Note on O131: Himal Kosala: no Supporting
Note on P135: Himal Kosala: WIR approved only for frame
Note on Q135: Himal Kosala: WIR approved only for frame
Note on R135: Himal Kosala: Full door not approved yet
Note on P136: Himal Kosala: WIR approved only for frame
Note on Q136: Himal Kosala: WIR approved only for frame
Note on R136: Himal Kosala: Full door not approved yet
Note on P137: Himal Kosala: WIR approved only for frame
Note on Q137: Himal Kosala: WIR approved only for frame
Note on R137: Himal Kosala: Full door not approved yet
Note on P138: Himal Kosala: WIR approved only for frame
Note on Q138: Himal Kosala: WIR approved only for frame
Note on R138: Himal Kosala: Full door not approved yet
Note on P139: Himal Kosala: WIR approved only for frame
Note on Q139: Himal Kosala: WIR approved only for frame
Note on R139: Himal Kosala: Full door not approved yet
Note on Q140: Himal Kosala: WIR not approved
Note on R140: Himal Kosala: WIR not approved
Note on Q141: Himal Kosala: WIR not approved
Note on R141: Himal Kosala: WIR not approved
Note on R143: Himal Kosala: no Supporting
Note on M144: Himal Kosala: no Supporting
Note on O144: Himal Kosala: no Supporting
Note on Q145: Himal Kosala: no Supporting
Note on Q146: Himal Kosala: WIR not approved
Note on R146: Himal Kosala: WIR not approved
Note on Q147: Himal Kosala: WIR not approved
Note on R147: Himal Kosala: WIR not approved
Note on P148: Himal Kosala: WIR approved only for frame
Note on Q148: Himal Kosala: WIR approved only for frame
Note on R148: Himal Kosala: Full door not approved yet
Note on P149: Himal Kosala: WIR approved only for frame
Note on Q149: Himal Kosala: WIR approved only for frame
Note on R149: Himal Kosala: Full door not approved yet
Note on P150: Himal Kosala: WIR approved only for frame
Note on Q150: Himal Kosala: WIR approved only for frame
Note on R150: Himal Kosala: Full door not approved yet
Note on P151: Himal Kosala: WIR approved only for frame
Note on Q151: Himal Kosala: WIR approved only for frame
Note on R151: Himal Kosala: Full door not approved yet
Note on P152: Himal Kosala: WIR approved only for frame
Note on Q152: Himal Kosala: WIR approved only for frame
Note on R152: Himal Kosala: Full door not approved yet
Note on P153: Himal Kosala: WIR approved only for frame
Note on Q153: Himal Kosala: WIR approved only for frame
Note on R153: Himal Kosala: Full door not approved yet
Note on Q154: Himal Kosala: WIR not approved
Note on R154: Himal Kosala: WIR not approved
Note on Q156: Himal Kosala: WIR not approved
Note on R156: Himal Kosala: WIR not approved
Note on M157: Himal Kosala: no supporting
Note on O157: Himal Kosala: no supporting
Note on P165: Himal Kosala: WIR approved only for frame
Note on Q165: Himal Kosala: WIR approved only for frame
Note on R165: Himal Kosala: Full door not approved yet
Note on P166: Himal Kosala: WIR approved only for frame
Note on Q166: Himal Kosala: WIR approved only for frame
Note on R166: Himal Kosala: Full door not approved yet
Note on P167: Himal Kosala: WIR approved only for frame
Note on Q167: Himal Kosala: WIR approved only for frame
Note on R167: Himal Kosala: Full door not approved yet
Note on P168: Himal Kosala: WIR approved only for frame
Note on Q168: Himal Kosala: WIR approved only for frame
Note on R168: Himal Kosala: Full door not approved yet
Note on P169: Himal Kosala: WIR approved only for frame
Note on Q169: Himal Kosala: WIR approved only for frame
Note on R169: Himal Kosala: Full door not approved yet
Note on P170: Himal Kosala: WIR approved only for frame
Note on Q170: Himal Kosala: WIR approved only for frame
Note on R170: Himal Kosala: Full door not approved yet
Note on Q173: Himal Kosala: WIR not approved
Note on R173: Himal Kosala: WIR not approved
Note on M174: Himal Kosala: no supporting
Note on O174: Himal Kosala: no supporting
Note on R177: Himal Kosala: Rejected
Note on P178: Himal Kosala: WIR approved only for frame
Note on Q178: Himal Kosala: WIR approved only for frame
Note on R178: Himal Kosala: Full door not approved yet
Note on P179: Himal Kosala: WIR approved only for frame
Note on Q179: Himal Kosala: WIR approved only for frame
Note on R179: Himal Kosala: Full door not approved yet
Note on P180: Himal Kosala: WIR approved only for frame
Note on Q180: Himal Kosala: WIR approved only for frame
Note on R180: Himal Kosala: Full door not approved yet
Note on P181: Himal Kosala: WIR approved only for frame
Note on Q181: Himal Kosala: WIR approved only for frame
Note on R181: Himal Kosala: Full door not approved yet
Note on P182: Himal Kosala: WIR approved only for frame
Note on Q182: Himal Kosala: WIR approved only for frame
Note on R182: Himal Kosala: Full door not approved yet
Note on P183: Himal Kosala: WIR approved only for frame
Note on Q183: Himal Kosala: WIR approved only for frame
Note on R183: Himal Kosala: Full door not approved yet
Note on Q184: Himal Kosala: WIR not approved
Note on R184: Himal Kosala: WIR not approved
Note on Q185: Himal Kosala: WIR not approved
Note on R185: Himal Kosala: WIR not approved
Note on Q186: Himal Kosala: WIR not approved
Note on R186: Himal Kosala: WIR not approved
Note on M187: Himal Kosala: no supporting
Note on O187: Himal Kosala: no supporting
Note on Q188: Himal Kosala: WIR not approved
Note on R188: Himal Kosala: WIR not approved
Note on Q189: Himal Kosala: WIR not approved
Note on R189: Himal Kosala: WIR not approved
Note on Q190: Himal Kosala: WIR not approved
Note on R190: Himal Kosala: WIR not approved
Note on Q191: Himal Kosala: WIR not approved
Note on R191: Himal Kosala: WIR not approved
Note on N193: Himal Kosala: no supporting
Note on P193: Himal Kosala: no supporting
Note on M194: Himal Kosala: no supporting
Note on O194: Himal Kosala: no supporting
Note on Q198: Himal Kosala: WIR reject
Note on R198: Himal Kosala: no supporting
Note on Q199: Himal Kosala: WIR reject
Note on R199: Himal Kosala: no supporting
Note on Q200: Himal Kosala: no supporting
Note on R200: Himal Kosala: no supporting
Note on M201: Himal Kosala: no supporting
Note on O201: Himal Kosala: no supporting
Note on Q206: Himal Kosala: WIR approved only for frame
Note on R206: Himal Kosala: Full door not approved yet
Note on Q208: Himal Kosala: WIR approved only for frame
Note on R208: Himal Kosala: Full door not approved yet
Note on Q209: Himal Kosala: WIR approved only for frame
Note on R209: Himal Kosala: Full door not approved yet
Note on Q210: Himal Kosala: WIR approved only for frame
Note on R210: Himal Kosala: Full door not approved yet
Note on Q215: Himal Kosala: WIR not approved
Note on R215: Himal Kosala: WIR not approved
Note on Q216: Himal Kosala: WIR not approved
Note on R216: Himal Kosala: WIR not approved
Note on Q220: Himal Kosala: WIR not approved
Note on R220: Himal Kosala: WIR not approved
Note on Q221: Himal Kosala: WIR not approved
Note on R221: Himal Kosala: WIR not approved
Note on P223: Himal Kosala: WIR approved only for frame
Note on Q223: Himal Kosala: WIR approved only for frame
Note on R223: Himal Kosala: Full door not approved yet
Note on P224: Himal Kosala: WIR approved only for frame
Note on Q224: Himal Kosala: WIR approved only for frame
Note on R224: Himal Kosala: Full door not approved yet
Note on P225: Himal Kosala: WIR approved only for frame
Note on Q225: Himal Kosala: WIR approved only for frame
Note on R225: Himal Kosala: Full door not approved yet
Note on P226: Himal Kosala: WIR approved only for frame
Note on Q226: Himal Kosala: WIR approved only for frame
Note on R226: Himal Kosala: Full door not approved yet
Note on P227: Himal Kosala: WIR approved only for frame
Note on Q227: Himal Kosala: WIR approved only for frame
Note on R227: Himal Kosala: Full door not approved yet
Note on N230: Himal Kosala: no supporting
Note on P230: Himal Kosala: no supporting
Note on M231: Himal Kosala: no supporting
Note on N231: Himal Kosala: no supporting
Note on O231: Himal Kosala: no supporting
Note on P231: Himal Kosala: no supporting
Note on Q234: Himal Kosala: no supporting
Note on R234: Himal Kosala: no supporting
Note on Q235: Himal Kosala: no supporting
Note on R235: Himal Kosala: no supporting
Note on P236: Himal Kosala: WIR approved only for frame
Note on Q236: Himal Kosala: WIR approved only for frame
Note on R236: Himal Kosala: Full door not approved yet
Note on P237: Himal Kosala: WIR approved only for frame
Note on Q237: Himal Kosala: WIR approved only for frame
Note on R237: Himal Kosala: Full door not approved yet
Note on P238: Himal Kosala: WIR approved only for frame
Note on Q238: Himal Kosala: WIR approved only for frame
Note on R238: Himal Kosala: Full door not approved yet
Note on P239: Himal Kosala: WIR approved only for frame
Note on Q239: Himal Kosala: WIR approved only for frame
Note on R239: Himal Kosala: Full door not approved yet
Note on P240: Himal Kosala: WIR approved only for frame
Note on Q240: Himal Kosala: WIR approved only for frame
Note on R240: Himal Kosala: Full door not approved yet
Note on M244: Himal Kosala: no supporting
Note on N244: Himal Kosala: no supporting
Note on O244: Himal Kosala: no supporting
Note on P244: Himal Kosala: no supporting
Note on Q245: Himal Kosala: WIR not approved
Note on R245: Himal Kosala: WIR not approved
Note on P249: Himal Kosala: WIR approved only for frame
Note on Q249: Himal Kosala: WIR approved only for frame
Note on R249: Himal Kosala: Full door not approved yet
Note on P252: Himal Kosala: WIR approved only for frame
Note on Q252: Himal Kosala: WIR approved only for frame
Note on R252: Himal Kosala: Full door not approved yet
Note on P253: Himal Kosala: WIR approved only for frame
Note on Q253: Himal Kosala: WIR approved only for frame
Note on R253: Himal Kosala: Full door not approved yet
Note on R254: Himal Kosala: Rejected
Note on R260: Himal Kosala: Rejected
Note on P262: Himal Kosala: WIR approved only for frame
Note on Q262: Himal Kosala: WIR approved only for frame
Note on R262: Himal Kosala: Full door not approved yet
Note on P268: Himal Kosala: WIR approved only for frame
Note on Q268: Himal Kosala: WIR approved only for frame
Note on R268: Himal Kosala: Full door not approved yet
Note on P269: Himal Kosala: WIR approved only for frame
Note on Q269: Himal Kosala: WIR approved only for frame
Note on R269: Himal Kosala: Full door not approved yet
Note on P270: Himal Kosala: WIR approved only for frame
Note on Q270: Himal Kosala: WIR approved only for frame
Note on R270: Himal Kosala: Full door not approved yet
Note on P271: Himal Kosala: WIR approved only for frame
Note on Q271: Himal Kosala: WIR approved only for frame
Note on R271: Himal Kosala: Full door not approved yet
Note on P276: Himal Kosala: WIR approved only for frame
Note on Q276: Himal Kosala: WIR approved only for frame
Note on R276: Himal Kosala: Full door not approved yet
Note on P277: Himal Kosala: WIR approved only for frame
Note on Q277: Himal Kosala: WIR approved only for frame
Note on R277: Himal Kosala: Full door not approved yet
Note on P278: Himal Kosala: WIR approved only for frame
Note on Q278: Himal Kosala: WIR approved only for frame
Note on R278: Himal Kosala: Full door not approved yet
Note on P279: Himal Kosala: WIR approved only for frame
Note on Q279: Himal Kosala: WIR approved only for frame
Note on R279: Himal Kosala: Full door not approved yet
Note on P280: Himal Kosala: WIR approved only for frame
Note on Q280: Himal Kosala: WIR approved only for frame
Note on R280: Himal Kosala: Full door not approved yet
Note on P281: Himal Kosala: WIR approved only for frame
Note on Q281: Himal Kosala: WIR approved only for frame
Note on R281: Himal Kosala: Full door not approved yet
Note on N283: Himal Kosala: no supporting
Note on O284: Himal Kosala: no supporting
Note on P289: Himal Kosala: WIR approved only for frame
Note on Q289: Himal Kosala: WIR approved only for frame
Note on R289: Himal Kosala: Full door not approved yet
Note on P290: Himal Kosala: WIR approved only for frame
Note on Q290: Himal Kosala: WIR approved only for frame
Note on R290: Himal Kosala: Full door not approved yet
Note on P291: Himal Kosala: WIR approved only for frame
Note on Q291: Himal Kosala: WIR approved only for frame
Note on R291: Himal Kosala: Full door not approved yet
Note on P292: Himal Kosala: WIR approved only for frame
Note on Q292: Himal Kosala: WIR approved only for frame
Note on R292: Himal Kosala: Full door not approved yet
Note on P293: Himal Kosala: WIR approved only for frame
Note on Q293: Himal Kosala: WIR approved only for frame
Note on R293: Himal Kosala: Full door not approved yet
Note on P294: Himal Kosala: WIR approved only for frame
Note on Q294: Himal Kosala: WIR approved only for frame
Note on R294: Himal Kosala: Full door not approved yet
Note on M297: Himal Kosala: no supporting
Note on O297: Himal Kosala: no supporting
Note on P302: Himal Kosala: WIR approved only for frame
Note on Q302: Himal Kosala: WIR approved only for frame
Note on R302: Himal Kosala: Full door not approved yet
Note on P303: Himal Kosala: WIR approved only for frame
Note on Q303: Himal Kosala: WIR approved only for frame
Note on R303: Himal Kosala: Full door not approved yet
Note on P304: Himal Kosala: WIR approved only for frame
Note on Q304: Himal Kosala: WIR approved only for frame
Note on R304: Himal Kosala: Full door not approved yet
Note on P305: Himal Kosala: WIR approved only for frame
Note on Q305: Himal Kosala: WIR approved only for frame
Note on R305: Himal Kosala: Full door not approved yet
Note on P306: Himal Kosala: WIR approved only for frame
Note on Q306: Himal Kosala: WIR approved only for frame
Note on R306: Himal Kosala: Full door not approved yet
Note on P307: Himal Kosala: WIR approved only for frame
Note on Q307: Himal Kosala: WIR approved only for frame
Note on R307: Himal Kosala: Full door not approved yet
Note on N308: Himal Kosala: no supporting
Note on Q309: Himal Kosala: no supporting
Note on R309: Himal Kosala: no supporting
Note on P321: Himal Kosala: WIR approved only for frame
Note on Q321: Himal Kosala: WIR approved only for frame
Note on R321: Himal Kosala: Full door not approved yet
Note on P322: Himal Kosala: WIR approved only for frame
Note on Q322: Himal Kosala: WIR approved only for frame
Note on R322: Himal Kosala: Full door not approved yet
Note on P323: Himal Kosala: WIR approved only for frame
Note on Q323: Himal Kosala: WIR approved only for frame
Note on R323: Himal Kosala: Full door not approved yet
Note on P324: Himal Kosala: WIR approved only for frame
Note on Q324: Himal Kosala: WIR approved only for frame
Note on R324: Himal Kosala: Full door not approved yet
Note on P325: Himal Kosala: WIR approved only for frame
Note on Q325: Himal Kosala: WIR approved only for frame
Note on R325: Himal Kosala: Full door not approved yet
Note on P326: Himal Kosala: WIR approved only for frame
Note on Q326: Himal Kosala: WIR approved only for frame
Note on R326: Himal Kosala: Full door not approved yet
Note on Q328: Himal Kosala: no supporting
Note on R328: Himal Kosala: no supporting
Note on Q331: Himal Kosala: WIR not approved
Note on R331: Himal Kosala: WIR not approved
Note on Q340: Himal Kosala: no supporting
Note on M341: Himal Kosala: no supporting
Note on O341: Himal Kosala: no supporting
Note on Q343: Himal Kosala: WIR not approved
Note on R343: Himal Kosala: WIR not approved
Note on Q347: Himal Kosala: no supporting
Note on R347: Himal Kosala: no supporting
Note on Q348: Himal Kosala: no supporting
Note on R348: Himal Kosala: no supporting
Note on M349: Himal Kosala: no supporting
Note on O349: Himal Kosala: no supporting
Note on Q350: Himal Kosala: WIR not approved
Note on R350: Himal Kosala: WIR not approved
Note on Q351: Himal Kosala: no supporting
Note on P353: Himal Kosala: no supporting
Note on N354: Himal Kosala: no supporting
Note on M356: Himal Kosala: no supporting
Note on O356: Himal Kosala: no supporting
Note on Q358: Himal Kosala: no supporting
Note on M361: Himal Kosala: no supporting
Note on O361: Himal Kosala: no supporting
Note on M362: Himal Kosala: no supporting
Note on O362: Himal Kosala: no supporting
Note on M364: Himal Kosala: no supporting
Note on O364: Himal Kosala: no supporting

## Variations
DORCHESTER HOTEL | [9 empty] | INTERIM PAYMENT APPLICATION | 6 |  | 12
PACKAGE : SUPPLY & INSTALLATION OF FOH-BOH TIMBER DOORS (EXCL. IRONMONGERY SUPPLY) Balance Works | [9 empty] | PERIOD ENDING | 2023-01-31 |  | 20
VARIATIONS
Item | Description | Qty. | Unit | Rate | Amount | Percentage |  |  | Amount |  |  | Remarks
[5 empty] | AED | Previous Percentage | Current Percentage | Cumulative Percentage | Previous Amount | Current Amount | Cumulative Amount
VARIATION -1
1 | Change in Thickness of Frame at WM room | 25 | Nos | 395.148 | 9878.7 | 50% | 50% | 100% | 4939.35 | 4939.35 | 9878.7 |  |  | 395.148
2 | Change in Thickness of Frame at Electric Room | 37 | Nos | 395.148 | 14620.476 | 50% | 50% | 100% | 7310.238 | 7310.238 | 14620.476 |  |  |  | 0.62162
3 | Change in Thickness of Frame at Empower Meter Room | 22 | Nos | 613.2005 | 13490.411 | 0% | 100% | 100% | 0 | 13490.411 | 13490.411 |  |  | 613.2005 | 0.95455
VARIATION -3
1 | Door mark L02130 to FRONT OFFICE(900 x 2100mm H)(D-04a) | 1 | Nos. | 2084.23 | 2084.23 | 50% | 40% | 90% | 1042.115 | 833.692 | 1875.807
2 | Door mark L0299 to BOH OFFICE (900 x 2100mm H)(D-04j) | 1 | Nos. | 2084.23 | 2084.23 | 50% | 40% | 90% | 1042.115 | 833.692 | 1875.807
3 | Door mark L0233 to CONCEIGE CORRIDOR (900 x 2100mm H)(D-04j) | 1 | Nos. | 2084.23 | 2084.23 | 50% | 40% | 90% | 1042.115 | 833.692 | 1875.807
4 | Door mark L0363 to BOH PANTRY (900 x 2100mm H)(D-04j) | 1 | Nos. | 2084.23 | 2084.23 | 50% | 40% | 90% | 1042.115 | 833.692 | 1875.807 | PII-AX-WR-L3-00100
5 | Door mark L0364 to MEETING ROOM (1000 x 2400mm H)(D-04c) | 1 | Nos. | 2911.3054 | 2911.3054 | 50% | 20% | 70% | 1455.6527 | 582.2611 | 2037.9138
6 | Door mark L0365 to ADA WC (800 x 2100mm H)(D-04a) | 1 | Nos. | 2335.7919 | 2335.7919 | 0% | 90% | 90% | 0 | 2102.2127 | 2102.2127 | PII-AX-WR-L3-00100
7 | Door mark L0366 to MALE WC (800 x 2100mm H)(D-04a) | 1 | Nos. | 2335.7919 | 2335.7919 | 0% | 90% | 90% | 0 | 2102.2127 | 2102.2127
8 | Door mark L0364 to STORE ROOM (1000 x 2400mm H)(D-04c) | 1 | Nos. | 2911.3054 | 2911.3054 | 50% | 40% | 90% | 1455.6527 | 1164.5222 | 2620.1749
VARIATION -4
1 | FTR Door at Level 06 | 1 | Nos. | 2718.9 | 2718.9 | 0% | 0% | 0% | 0 | 0 | 0
2 | FTR Door at Level 07 | 1 | Nos. | 2718.9 | 2718.9 | 0% | 0% | 0% | 0 | 0 | 0
3 | FTR Door at Level 08 | 1 | Nos. | 2718.9 | 2718.9 | 0% | 0% | 0% | 0 | 0 | 0
4 | FTR Door at Level 09 | 1 | Nos. | 2718.9 | 2718.9 | 0% | 0% | 0% | 0 | 0 | 0
5 | FTR Door at Level 18 | 1 | Nos. | 2718.9 | 2718.9 | 0% | 0% | 0% | 0 | 0 | 0
6 | FTR Door at Level 19 | 1 | Nos. | 2718.9 | 2718.9 | 0% | 0% | 0% | 0 | 0 | 0
7 | FTR Door at Level 20 | 1 | Nos. | 2718.9 | 2718.9 | 0% | 0% | 0% | 0 | 0 | 0
8 | FTR Door at Level 21 | 1 | Nos. | 2718.9 | 2718.9 | 0% | 0% | 0% | 0 | 0 | 0
9 | FTR Door at Level 22 | 1 | Nos. | 2718.9 | 2718.9 | 0% | 0% | 0% | 0 | 0 | 0
10 | FTR Door at Level 23 | 1 | Nos. | 2718.9 | 2718.9 | 0% | 0% | 0% | 0 | 0 | 0
VARIATION -5
1 | General Manager Office Door at Level 3 | 1 | Nos. | 2931.66 | 2931.66 | 0% | 0% | 0% | 0 | 0 | 0
| TOTAL AMOUNT (in AED) |  |  |  | 86941.3615 |  |  |  | 19329.3534 | 35025.9756 | 54355.329
Note on I17: Himal Kosala: Please provide the supporting documents
Note on I18: Himal Kosala: Please provide the supporting documents
Note on I19: Himal Kosala: Please provide the supporting documents
Note on I20: Himal Kosala: Please provide the supporting documents
Note on I22: Himal Kosala: Please provide the supporting documents
Note on I23: Himal Kosala: Please provide the supporting documents
Note on I24: Himal Kosala: Please provide the supporting documents